## DOER
Company Name | City/Town | Facility ID | Zip Code | Design Capacity (kW) | Export Capacity (kW) UNITIL Only | Import Capacity (kW) UNITIL Only | Fuel Type | Battery Energy Storage System (BESS) UNITIL ONLY | Circuit Name | Date Application Received | Date Application Deemed Complete | Application Receipt Total Time Lapsed (Workdays) | Application Receipt Customer Time Lapsed (Workdays) | Application Receipt Utility Time Lapsed (Workdays) | Date of Screen Study Began | Date of Screen Study Completed | Screen Review Total Time Lapsed (Workdays) | Screen Review Customer Time Lapsed (Workdays) | Screen Review Utility Time Lapsed (Workdays) | Date Supplemental Review Began | Date Supplemental Review Complete | Supplemental Review Total Time Lapsed (Workdays) | Supplemental Review Customer Time Lapsed (Workdays) | Supplemental Review Utility Time Lapsed (Workdays) | Date Standard Process Initial Review Began | Date Standard Process Initial Review Complete | Standard Process Total Time Lapsed (Workdays) | Standard Process Customer Time Lapsed (Workdays) | Standard Process Utility Time Lapsed (Workdays) | Date Impact Study Begun (NGRID IS MISSING) | Date Impact Study Sent | Impact Study Total Time Lapsed (Workdays) | Impact Study Customer Time Lapsed (Workdays) | Impact Study Utility Time Lapsed (Workdays) | Date Detailed Study Began | Date Detailed Study Sent | Detailed Study Total Time Lapsed (Workdays) | Detailed Study Customer Time Lapsed (Workdays) | Detailed Study Utility Time Lapsed (Workdays) | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/Standard/Complex Project | Construction Timeline Commitment (Workdays) | Date Construction Began | Date Construction Completed | Construction Total Time Lapsed (Workdays) | Construction Customer Time Lapsed (Workdays) | Construction Utility Time Lapsed (Workdays) | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Status | Private/Gov't | Net Metered? (Y/N) | Group Study | Group_Name | ASO_Group_Name | Group Study Designation | Limiting Export Max Size kW | Substation_Name
National Grid | ATHOL | 195816 | 01331 | 4200 |  |  | Solar |  | 05_09_705W4 | 09/14/2018 | 10/05/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2018 | 11/08/2018 | 62 | 14 | 48 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Execute ISAs - Pending Customer Decision
National Grid | BEVERLY | 327199 | 01915 | 10 |  |  | Solar |  | 05_12_51T1 | 11/19/2020 | 11/25/2020 | 3 | 0 | 3 | 11/27/2020 | 11/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/19/2020 | 4/26/2022 | Y | EXP | 365 | 04/09/2021 | 04/20/2021 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | TOPSFIELD | 267108 | 01983 | 0 |  |  | Battery Add-On |  | 05_14_33L1 | 11/25/2019 | 01/02/2020 | 23 | 17 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 4/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTFORD | 541791 | 01886 | 15.2 |  |  | Solar |  | 05_14_58L1 | 07/18/2023 | 07/24/2023 | 4 | 2 | 2 | 07/25/2023 | 07/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 | 07/18/2023 | 1/24/2025 | Y | EXP | 365 | 03/29/2024 | 06/05/2024 | 69 | 0 | 69 |  |  | 6/15/2024 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTFORD | 473412 | 01886 | 15.2 |  |  | Solar |  | 05_14_73L2 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/01/2022 | 12/19/2023 | Y | EXP | 365 | 01/28/2023 | 02/15/2023 | 19 | 0 | 19 |  |  | 6/13/2023 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | BILLERICA | 177716 | 01821 | 112 |  |  | Solar |  | 05_14_92L3 | 07/26/2017 | 07/26/2017 | 6 | 6 | 0 | 08/04/2017 | 08/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N | Barre-Athol |  |  | Execute ISAs - Pending Customer Decision
National Grid | WORCESTER | 309000 | 01606 | 7.6 |  |  | Solar |  | 05_01_24W5 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Barre-Athol |  |  | Execute ISAs
National Grid | DUDLEY | 176931 | 01571 | 22.8 |  |  | Solar |  | 05_01_412L4 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 4/2/2017 | N | EXP | 422 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 11/17/2016 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | WESTMINSTER | 176901 | 01473 | 6 |  |  | Solar |  | 05_01_602W2 | 01/27/2016 | 01/27/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/1/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 4/11/2016 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | FALL RIVER | 661519 | 02721 | 3.2 |  |  | Solar |  | 05_05_115W45 | 12/18/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/18/2024 | 4/21/2026 | Y | EXP | 365 | 05/10/2025 | 05/09/2025 | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | PETERSHAM | 195814 | 01366 | 3000 |  |  | Solar |  | 05_09_705W4 | 09/14/2018 | 10/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 11/08/2018 | 65 | 35 | 30 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | BEVERLY | 354200 | 01915 | 250 |  |  | Solar |  | 05_12_51T1 | 05/07/2021 | 05/26/2021 | 13 | 8 | 5 | 05/27/2021 | 05/27/2021 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2021 |  | 10/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | BOXFORD | 283459 | 01921 | 10 |  |  | Solar |  | 05_14_33L1 | 03/12/2020 | 03/19/2020 | 5 | 5 | 0 | 03/20/2020 | 03/20/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2020 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | WESTFORD | 547989 | 01886 | 15.2 |  |  | Solar |  | 05_14_58L1 | 08/14/2023 | 08/15/2023 | 2 | 1 | 1 | 08/16/2023 | 08/16/2023 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2024 | Connected |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | CHELMSFORD | 642436 | 01863 | 10 |  |  | Solar |  | 05_14_73L2 | 09/29/2024 | 10/17/2024 | 5 | 2 | 3 | 10/18/2024 | 10/18/2024 | 47 | 3 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 09/29/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | BILLERICA | 644567 | 01821 | 10 |  |  | Solar |  | 05_14_92L3 | 10/02/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | WORCESTER | 396684 | 01606 | 0 |  |  | Other |  | 05_01_24W5 | 04/28/2022 | 05/19/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton |  |  | Closed
National Grid | DUDLEY | 176959 | 01571 | 9 |  |  | Solar |  | 05_01_412L4 | 07/16/2016 | 07/16/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/16/2016 | 7/23/2017 | Y | EXP | 362 | 03/24/2017 | 05/04/2017 | 28 | 0 | 28 | 6/27/2017 | 6/27/2017 | 6/27/2017 | Connected |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | HUBBARDSTON | 177318 | 01452 | 2000 |  |  | Solar |  | 05_01_602W2 | 02/14/2017 | 02/14/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2017 | 03/27/2017 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | FALL RIVER | 667660 | 02724 | 7.6 |  |  | Solar |  | 05_05_115W45 | 01/24/2025 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | AMESBURY | 704916 | 01913 | 50 |  |  | Solar |  | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | MANCHESTER | 365294 | 01944 | 9.86 |  |  | Solar |  | 05_12_51T1 | 06/23/2021 | 07/16/2021 | 17 | 14 | 3 | 07/19/2021 | 07/19/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2021 |  | 9/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | BOXFORD | 294246 | 01921 | 0 |  |  | Solar |  | 05_14_33L1 | 06/01/2020 | 06/02/2020 | 0 | 0 | 0 | 06/03/2020 | 06/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2021 | Connected |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | WESTFORD | 549217 | 01886 | 7.6 |  |  | Solar |  | 05_14_58L1 | 08/17/2023 | 08/21/2023 | 2 | 1 | 1 | 08/22/2023 | 08/22/2023 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | CHELMSFORD | 648149 | 01824 | 23 |  |  | Solar |  | 05_14_73L2 | 10/18/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | BILLERICA | 646579 | 01821 | 10 |  |  | Solar |  | 05_14_92L3 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | WORCESTER | 415781 | 01606 | 8.41 |  |  | Solar |  | 05_01_24W5 | 07/11/2022 |  | 30 | 27 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | DUDLEY | 176996 | 01571 | 3.8 |  |  | Solar |  | 05_01_412L4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | HUBBARDSTON | 178021 | 01452 | 900 |  |  | Solar |  | 05_01_602W2 | 08/29/2017 | 08/29/2017 | 8 | 8 | 0 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | FALL RIVER | 671676 | 02721 | 7.6 |  |  | Solar |  | 05_05_115W45 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/12/2025 | 4/9/2026 | Y | EXP | 365 | 05/02/2025 | 06/06/2025 | 36 | 0 | 36 |  |  | 6/23/2025 | Connected |  | N | MPL-East |  |  | Time Frame Suspension
National Grid | AMESBURY | 704904 | 01913 | 50 |  |  | Solar |  | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | MPL-East |  |  | Time Frame Suspension
National Grid | BEVERLY | 376945 | 01915 | 6.96 |  |  | Solar |  | 05_12_51T1 | 08/19/2021 | 01/04/2022 | 2 | 0 | 2 | 08/24/2021 | 08/24/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2022 | Connected |  | Y | MPL-East |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | BOXFORD | 306879 | 01921 | 20 |  |  | Solar |  | 05_14_33L1 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 | 08/14/2020 | 8/17/2021 | Y | EXP | 365 | 02/05/2021 | 02/04/2021 | 0 | 0 | 0 |  |  | 2/9/2021 | Connected |  | N | MPL-East |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | WESTFORD | 555011 | 01886 | 9.57 |  |  | Solar |  | 05_14_58L1 | 09/25/2023 | 09/28/2023 | 4 | 1 | 3 | 09/29/2023 | 09/29/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 650207 | 01863 | 12.16 |  |  | Solar |  | 05_14_73L2 | 10/28/2024 | 11/26/2024 | 9 | 6 | 3 | 11/27/2024 | 11/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Time Frame Suspension
National Grid | BILLERICA | 648246 | 01821 | 10 |  |  | Solar |  | 05_14_92L3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/18/2024 | 1/1/2026 | Y | EXP | 365 | 03/15/2025 | 03/24/2025 | 10 | 0 | 10 |  |  | 3/27/2025 | Connected |  | N | MPL-East |  |  | Time Frame Suspension
National Grid | WORCESTER | 440578 | 01606 | 8.41 |  |  | Solar |  | 05_01_24W5 | 07/20/2022 | 08/03/2022 | 11 | 8 | 3 | 08/04/2022 | 08/04/2022 | 28 | 7 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 07/20/2022 | 6/8/2024 | Y | EXP | 365 | 05/24/2023 | 06/08/2023 | 16 | 0 | 16 |  |  | 6/30/2023 | Connected |  | Y | MPL-East |  |  | Time Frame Suspension
National Grid | DUDLEY | 177938 | 01571 | 96 |  |  | Solar |  | 05_01_412L4 | 06/26/2017 | 06/26/2017 | 28 | 27 | 1 | 08/07/2017 | 08/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2017 |  | 7/2/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | WESTMINSTER | 178134 | 01473 | 15.2 |  |  | Solar |  | 05_01_602W2 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | WESTPORT | 687395 | 02790 | 498 |  |  | Solar |  | 05_05_115W45 | 05/16/2025 | 07/08/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2025 | 08/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | AMESBURY | 175401 | 01913 | 17 |  |  | Solar |  | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 15 | 0 | 12/15/2014 | 12/15/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | BEVERLY | 382216 | 01915 | 9.772 |  |  | Solar |  | 05_12_51T1 | 09/15/2021 | 09/20/2021 | 4 | 3 | 1 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2022 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | TOPSFIELD | 463152 | 01983 | 7.6 |  |  | Solar |  | 05_14_33L1 | 12/07/2022 | 12/08/2022 | 1 | 0 | 1 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 12/07/2022 | 5/29/2024 | Y | EXP | 365 | 03/28/2023 | 05/30/2023 | 64 | 0 | 64 |  |  | 6/2/2023 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | WESTFORD | 637421 | 01886 | 5.525 |  |  | Solar |  | 05_14_58L1 | 09/04/2024 | 09/24/2024 | 8 | 4 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | WESTFORD | 657626 | 01886 | 3.8 |  |  | Solar |  | 05_14_73L2 | 11/29/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | BILLERICA | 670042 | 01821 | 10 |  |  | Solar |  | 05_14_92L3 | 02/11/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | WORCESTER | 552074 | 01606 | 5.985 |  |  | Solar |  | 05_01_24W5 | 10/25/2023 | 12/08/2023 | 30 | 25 | 5 | 12/11/2023 | 12/11/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 10/25/2023 | 3/15/2025 | Y | EXP | 365 | 05/15/2024 | 07/03/2024 | 50 | 0 | 50 |  |  | 8/13/2024 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | DUDLEY | 178095 | 01571 | 7.6 |  |  | Solar |  | 05_01_412L4 | 07/10/2017 | 07/19/2017 | 7 | 6 | 1 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/15/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | HUBBARDSTON | 178224 | 01452 | 2375 |  |  | Solar |  | 05_01_602W2 | 04/16/2018 | 04/16/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | FALL RIVER | 663198 | 02721 | 999.9 |  |  | Solar |  | 05_05_115W52 | 02/06/2025 | 04/24/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/22/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | AMESBURY | 175681 | 01913 | 17 |  |  | Solar |  | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 0 | 15 | 12/15/2014 | 12/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2015 |  | 1/31/2015 | N | EXP | 24 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/29/2015 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | BEVERLY | 393606 | 01915 | 10 |  |  | Solar |  | 05_12_51T1 | 11/19/2021 | 11/23/2021 | 3 | 1 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | BOXFORD | 462041 | 01921 | 14.79 |  |  | Solar |  | 05_14_33L1 | 11/17/2022 | 11/23/2022 | 4 | 1 | 3 | 11/25/2022 | 11/25/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2023 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 427890 | 01824 | 875 |  |  | Solar |  | 05_14_58L2 | 08/25/2022 | 12/13/2022 | 74 | 64 | 10 |  |  | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | WESTFORD | 658155 | 01886 | 0 |  |  | Battery Add-On |  | 05_14_73L2 | 12/03/2024 | 12/05/2024 | 2 | 0 | 2 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 12/03/2024 | 3/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | BILLERICA | 197046 | 01821 | 2500 |  |  | Natural Gas |  | 05_14_92L4 | 10/04/2019 | 11/07/2019 | 23 | 19 | 4 |  |  | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 10/04/2019 | 4/14/2026 | Y | STD | 855 | 10/28/2020 | 09/23/2021 | 134 | 0 | 134 |  |  |  | Completion Documents |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | WORCESTER | 554530 | 01606 | 3.8 |  |  | Solar |  | 05_01_24W5 | 09/12/2023 | 09/18/2023 | 4 | 0 | 4 | 09/19/2023 | 09/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | DUDLEY | 178192 | 01571 | 3630 |  |  | Solar |  | 05_01_412L4 | 01/02/2018 | 02/23/2018 | 35 | 9 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 04/02/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2020 | 01/02/2018 | 6/28/2024 | Y | STD | 45 | 07/07/2023 | 09/21/2023 | 77 | 0 | 77 |  |  | 6/10/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | HUBBARDSTON | 178326 | 01452 | 5000 |  |  | Solar |  | 05_01_602W2 | 03/26/2018 | 03/26/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/04/2018 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | FALL RIVER | 683283 | 02721 | 3.8 |  |  | Solar |  | 05_05_115W52 | 04/07/2025 | 04/24/2025 | 3 | 0 | 3 | 05/07/2025 | 05/07/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 04/07/2025 | 6/24/2026 | Y | EXP | 365 | 07/09/2025 | 08/29/2025 | 52 | 0 | 52 |  |  |  | Completion Documents |  | Y | Webster-Southbridge-Charlton |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | AMESBURY | 339779 | 01913 | 133.2 |  |  | Solar |  | 05_14_5J14 | 02/12/2021 | 03/04/2021 | 12 | 3 | 9 | 03/05/2021 | 03/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Time Frame Suspension
National Grid | MANCHESTER | 392637 | 01944 | 0 |  |  | Other |  | 05_12_51T1 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Closed
National Grid | BOXFORD | 479868 | 01921 | 22.8 |  |  | Solar |  | 05_14_33L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Closed
National Grid | CHELMSFORD | 710905 | 01824 | 4.93 |  |  | Solar |  | 05_14_58L2 | 08/10/2025 | 09/17/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-West |  |  | Closed
National Grid | WESTFORD | 664749 | 01886 | 5.7 |  |  | Solar |  | 05_14_73L2 | 01/09/2025 | 02/06/2025 | 13 | 8 | 5 | 02/07/2025 | 02/07/2025 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N | Hopedale-West |  |  | Closed
National Grid | BILLERICA | 705471 | 01821 | 13.36 |  |  | Solar |  | 05_14_92L4 | 07/21/2025 | 08/21/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | Y | Hopedale-West |  |  | Closed - Draft
National Grid | WORCESTER | 587312 | 01606 | 7.6 |  |  | Solar |  | 05_01_24W5 | 02/03/2024 | 02/05/2024 | 1 | 0 | 1 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/03/2024 | 2/22/2025 | Y | EXP | 365 | 05/04/2024 | 08/15/2024 | 104 | 0 | 104 |  |  | 10/25/2024 | Connected |  | N | Hopedale-West |  |  | Closed
National Grid | DUDLEY | 178264 | 01571 | 1250 |  |  | Solar |  | 05_01_412L4 | 04/18/2018 | 04/30/2018 | 8 | 8 | 0 |  |  | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 | 04/18/2018 | 4/14/2025 | Y | STD | 485 | 08/20/2024 | 02/13/2025 | 178 | 178 | 0 |  |  | 3/26/2025 | Connected |  | N | Hopedale-West |  |  | Closed
National Grid | GARDNER | 178567 | 01440 | 4950 |  |  | Solar |  | 05_01_602W2 | 12/07/2017 | 01/08/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/07/2018 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Closed
National Grid | WESTPORT | 685905 | 02790 | 7.6 |  |  | Solar |  | 05_05_115W52 | 04/17/2025 | 07/08/2025 | 9 | 7 | 2 | 07/24/2025 | 07/24/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 11/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-West |  |  | Closed
National Grid | AMESBURY | 425281 | 01913 | 133.2 |  |  | Solar |  | 05_14_5J14 | 04/20/2022 | 05/04/2022 | 10 | 0 | 10 |  |  | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Closed
National Grid | MANCHESTER | 394507 | 01944 | 360 |  |  | Solar |  | 05_12_51T1 | 12/17/2021 | 02/02/2022 | 32 | 24 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Closed - Construction Hold
National Grid | BOXFORD | 500918 | 01921 | 22.8 |  |  | Solar |  | 05_14_33L1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Shutesbury |  |  | Time Frame Suspension
National Grid | WESTFORD | 174602 | 01886 | 95 |  |  | Solar |  | 05_14_58L2 | 09/20/2011 | 09/20/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2011 |  | 1/20/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 1/20/2012 | Connected |  | N | Shutesbury |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 683559 | 01824 | 23 |  |  | Solar |  | 05_14_73L2 | 04/09/2025 | 04/11/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N | Shutesbury |  |  | Time Frame Suspension
National Grid | BILLERICA | 174891 | 01821 | 990 |  |  | Solar |  | 05_14_92L4 | 08/14/2013 | 08/14/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/22/2013 | 11/22/2013 | 22 | 0 | 22 | 08/23/2013 | 10/01/2013 | 26 | 0 | 26 |  | 11/22/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/2/2013 |  | 12/31/2013 | N | STD | 29 |  |  | 0 | 0 | 0 | 12/28/2013 | 12/28/2013 | 12/31/2013 | Connected |  | N | Shutesbury |  |  | Time Frame Suspension
National Grid | WORCESTER | 615561 | 01606 | 3.8 |  |  | Solar |  | 05_01_24W5 | 06/04/2024 | 06/27/2024 | 12 | 11 | 1 | 06/28/2024 | 06/28/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Shutesbury |  |  | Time Frame Suspension
National Grid | DUDLEY | 178355 | 01571 | 2990 |  |  | Solar |  | 05_01_412L4 | 02/28/2018 | 02/28/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2018 | 06/15/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East |  |  | Scoping Meeting
National Grid | GARDNER | 178614 | 01440 | 2000 |  |  | Solar |  | 05_01_602W2 | 12/14/2017 | 01/29/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 02/20/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/01/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East |  |  | Scoping Meeting
National Grid | FALL RIVER | 692739 | 02720 | 20 |  |  | Solar |  | 05_05_115W52 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 51 | 25 | 26 | 11/04/2025 | 01/07/2026 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  | 01/07/2026 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | AMESBURY | 673138 | 01913 | 30 |  |  | Solar |  | 05_14_5J14 | 05/12/2025 | 05/14/2025 | 2 | 0 | 2 | 05/15/2025 | 05/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | MANCHESTER | 400010 | 01944 | 8.027 |  |  | Solar |  | 05_12_51T1 | 12/08/2021 | 01/05/2022 | 19 | 17 | 2 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2022 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | TOPSFIELD | 590429 | 01983 | 23 |  |  | Solar |  | 05_14_33L1 | 02/15/2024 | 02/22/2024 | 4 | 0 | 4 | 02/23/2024 | 02/23/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | CHELMSFORD | 175285 | 01824 | 30 |  |  | Solar |  | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 5 | 1 | 4 | 11/14/2014 | 11/14/2014 | 147 | 4 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 1/30/2015 | Y | EXP | 50 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | WESTFORD | 719098 | 01886 | 11.5 |  |  | Battery Add-On |  | 05_14_73L2 | 09/16/2025 | 09/24/2025 | 5 | 3 | 2 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | BILLERICA | 201405 | 01821 | 15.2 |  |  | Solar |  | 05_14_92L4 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/16/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | WORCESTER | 643869 | 01606 | 10 |  |  | Solar |  | 05_01_24W5 | 10/04/2024 | 10/17/2024 | 4 | 0 | 4 | 10/18/2024 | 10/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/04/2024 | 12/9/2025 | Y | EXP | 365 | 02/13/2025 | 03/21/2025 | 37 | 0 | 37 |  |  | 4/16/2025 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | DUDLEY | 178442 | 01571 | 9 |  |  | Solar |  | 05_01_412L4 | 04/02/2018 | 04/10/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/02/2018 | 5/6/2019 | Y | EXP | 333 | 03/30/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 5/2/2019 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | WESTMINSTER | 206349 | 01473 | 2340 |  |  | Solar |  | 05_01_602W2 | 02/06/2019 |  | 140 | 26 | 114 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | WESTPORT | 711421 | 02790 | 11.4 |  |  | Solar |  | 05_05_115W52 | 09/09/2025 | 10/01/2025 | 15 | 9 | 6 | 10/02/2025 | 10/02/2025 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | GLOUCESTER | 689590 | 01930 | 0 |  |  | Battery Add-On |  | 05_12_24J10 | 05/05/2025 | 06/02/2025 | 19 | 15 | 4 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | BEVERLY | 426053 | 01915 | 22.272 |  |  | Solar |  | 05_12_51T1 | 04/25/2022 | 06/07/2022 | 30 | 26 | 4 | 06/08/2022 | 06/08/2022 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | TOPSFIELD | 620928 | 01983 | 23 |  |  | Solar |  | 05_14_33L1 | 06/27/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/27/2024 | 7/25/2025 | Y | EXP | 365 | 10/04/2024 | 11/14/2024 | 42 | 0 | 42 |  |  | 10/8/2024 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | CHELMSFORD | 175898 | 01824 | 476 |  |  | Solar |  | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | METHUEN | 444190 | 01844 | 499 |  |  | Solar |  | 05_14_74L1 | 09/26/2022 | 10/31/2022 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/02/2022 | 12/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | MPL-Northwest |  |  | Study Complete
National Grid | BILLERICA | 372447 | 01821 | 9.8 |  |  | Solar |  | 05_14_92L4 | 08/05/2021 | 12/10/2021 | 2 | 1 | 1 | 08/09/2021 | 08/09/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | WORCESTER | 665488 | 01606 | 3.8 |  |  | Solar |  | 05_01_24W5 | 01/14/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | DUDLEY | 195056 | 01571 | 7.6 |  |  | Solar |  | 05_01_412L4 | 09/04/2018 | 10/26/2018 | 21 | 21 | 0 | 10/29/2018 | 10/29/2018 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 09/04/2018 | 11/8/2019 | Y | EXP | 359 | 07/11/2019 | 09/16/2019 | 67 | 0 | 67 |  |  | 10/9/2019 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | HUBBARDSTON | 282891 | 01565 | 4950 |  |  | Other |  | 05_01_602W2 | 03/19/2020 | 03/27/2020 | 5 | 1 | 4 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/29/2020 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | WESTPORT | 714265 | 02790 | 2000 |  |  | Solar |  | 05_05_115W52 | 09/09/2025 | 10/02/2025 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2025 | 10/17/2025 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | MPL-Northwest |  |  | Study Complete
National Grid | GLOUCESTER | 731829 | 01930 | 16.24 |  |  | Solar |  | 05_12_24J10 | 12/04/2025 |  | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | MANCHESTER | 425303 | 01944 | 15.2 |  |  | Solar |  | 05_12_51T1 | 04/20/2022 | 05/11/2022 | 15 | 14 | 1 | 05/12/2022 | 05/12/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | TOPSFIELD | 624766 | 01983 | 9.86 |  |  | Solar |  | 05_14_33L1 | 07/15/2024 | 08/28/2024 | 3 | 1 | 2 | 08/29/2024 | 08/29/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 07/15/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | CHELMSFORD | 175897 | 01824 | 1988 |  |  | Solar |  | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton |  |  | Closed
National Grid | METHUEN | 457510 | 01844 | 100 |  |  | Solar |  | 05_14_74L1 | 10/10/2022 | 01/04/2023 | 59 | 49 | 10 | 01/05/2023 | 01/05/2023 | 23 | 0 | 23 | 07/10/2025 | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 9/5/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | MPL-Northwest |  |  | Study Complete
National Grid | BILLERICA | 465206 | 01821 | 15.2 |  |  | Solar |  | 05_14_92L4 | 10/02/2022 | 10/05/2022 | 4 | 3 | 1 | 10/06/2022 | 10/06/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2023 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | WORCESTER | 672053 | 01606 | 5.76 |  |  | Solar |  | 05_01_24W5 | 02/13/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension - Construction Hold
National Grid | DUDLEY | 268311 | 01571 | 10 |  |  | Solar |  | 05_01_412L4 | 01/17/2020 | 02/10/2020 | 1 | 1 | 0 | 02/11/2020 | 02/11/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  | 2/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland |  |  | Scoping Meeting
National Grid | HUBBARDSTON | 287828 | 01452 | 0 |  |  | Other |  | 05_01_602W2 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/20/2020 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | WESTPORT | 720034 | 02790 | 11.4 |  |  | Solar |  | 05_05_115W52 | 09/18/2025 | 10/03/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | GLOUCESTER | 175642 | 01930 | 17 |  |  | Solar |  | 05_12_24J10 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 2/6/2015 | N | EXP | 88 |  |  | 0 | 0 | 0 | 6/9/2016 | 6/9/2016 | 6/14/2016 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | GLOUCESTER | 426149 | 01930 | 7.6 |  |  | Solar |  | 05_12_51T1 | 06/13/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension - Draft
National Grid | TOPSFIELD | 630827 | 01983 | 4.64 |  |  | Solar |  | 05_14_33L1 | 08/07/2024 | 08/13/2024 | 7 | 3 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 08/07/2024 | 1/3/2026 | Y | EXP | 365 | 01/23/2025 | 01/30/2025 | 8 | 0 | 8 |  |  | 2/5/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | CHELMSFORD | 175896 | 01824 | 476 |  |  | Solar |  | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | METHUEN | 559307 | 01844 | 240 |  |  | Solar |  | 05_14_74L1 | 11/17/2023 | 12/08/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 11/17/2023 | 4/17/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | BILLERICA | 702356 | 01821 | 20 |  |  | Solar |  | 05_14_92L6 | 07/02/2025 | 08/04/2025 | 13 | 11 | 2 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | Hopedale-West |  |  | Closed - Draft
National Grid | AUBURN | 673375 | 01501 | 999 |  |  | Solar |  | 05_01_26W1 | 11/07/2025 |  | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 299874 | 01571 | 9.36 |  |  | Solar |  | 05_01_412L4 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTMINSTER | 290747 | 01473 | 0 |  |  | Other |  | 05_01_602W2 | 08/31/2020 | 09/16/2020 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2020 | 10/08/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest |  |  | Study Complete
National Grid | WESTPORT | 741857 | 02790 | 11.4 |  |  | Solar |  | 05_05_115W52 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | GLOUCESTER | 176689 | 01930 | 10 |  |  | Solar |  | 05_12_24J10 | 02/19/2016 | 02/19/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/16/2016 | 8/16/2016 | 8/16/2016 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | GLOUCESTER | 431218 | 01930 | 10 |  |  | Solar |  | 05_12_51T1 | 05/17/2022 | 05/18/2022 | 1 | 0 | 1 | 05/19/2022 | 05/19/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | TOPSFIELD | 649671 | 01983 | 7.6 |  |  | Solar |  | 05_14_33L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 176030 | 01824 | 30 |  |  | Solar |  | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 3 | 0 | 3 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 9/30/2015 | Y | EXP | 293 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | METHUEN | 559191 | 01844 | 240 |  |  | Solar |  | 05_14_74L1 | 11/03/2023 | 11/21/2023 | 12 | 0 | 12 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 11/03/2023 | 4/16/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | BILLERICA | 710907 | 01821 | 15.68 |  |  | Solar |  | 05_14_92L6 | 09/10/2025 | 09/22/2025 | 7 | 4 | 3 | 09/23/2025 | 09/23/2025 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | AUBURN | 716350 | 01501 | 11.517 |  |  | Solar |  | 05_01_26W1 | 09/03/2025 | 09/29/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | DUDLEY | 320511 | 01571 | 9.8 |  |  | Solar |  | 05_01_412L4 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | GARDNER | 291986 | 01440 | 5.76 |  |  | Solar |  | 05_01_602W2 | 05/14/2020 | 05/15/2020 | 0 | 0 | 0 | 05/18/2020 | 05/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | WESTPORT | 175769 | 02790 | 4800 |  |  | Solar |  | 05_05_115W52 | 06/10/2014 | 06/10/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2014 | 07/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 12/31/2016 | N | STD | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | GLOUCESTER | 183953 | 01930 | 6.44 |  |  | Solar |  | 05_12_24J10 | 05/09/2018 | 05/09/2018 | 8 | 0 | 8 | 05/22/2018 | 05/22/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  | 6/24/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | MANCHESTER | 432837 | 01944 | 220 |  |  | Solar |  | 05_12_51T1 | 06/23/2022 | 07/29/2022 | 25 | 15 | 10 |  |  | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 06/23/2022 | 10/31/2024 | Y | STD | 290 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | BOXFORD | 680660 | 01921 | 15.2 |  |  | Solar |  | 05_14_33L1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | WESTFORD | 176726 | 01886 | 179 |  |  | Solar |  | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2016 | 03/22/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2016 |  | 2/28/2017 | N | STD | 210 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland |  |  | Scoping Meeting
National Grid | METHUEN | 571764 | 01844 | 240 |  |  | Solar |  | 05_14_74L1 | 11/17/2023 | 12/06/2023 | 12 | 3 | 9 | 12/07/2023 | 12/07/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 11/17/2023 | 7/10/2026 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | BILLERICA | 174140 | 01821 | 82.3 |  |  | Solar |  | 05_14_92L6 | 04/11/2012 | 04/11/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 7/6/2012 | N | EXP | -31 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 12/27/2012 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | AUBURN | 719926 | 01501 | 11.5 |  |  | Solar |  | 05_01_26W1 | 09/17/2025 | 09/30/2025 | 5 | 3 | 2 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 375104 | 01571 | 9.8 |  |  | Solar |  | 05_01_412L4 | 09/28/2021 | 12/16/2021 | 4 | 0 | 4 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2022 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | HUBBARDSTON | 294861 | 01452 | 0 |  |  | Other |  | 05_01_602W2 | 09/09/2020 | 09/22/2020 | 8 | 1 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTPORT | 175819 | 02790 | 2000 |  |  | Solar |  | 05_05_115W52 | 07/30/2015 | 07/30/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2015 | 09/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 07/30/2015 | 7/15/2017 | Y | STD | 333 | 03/01/2017 | 06/23/2017 | 80 | 0 | 80 | 6/27/2017 | 6/27/2017 | 7/31/2017 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | GLOUCESTER | 325646 | 01930 | 10 |  |  | Solar |  | 05_12_24J11 | 11/12/2020 | 01/27/2021 | 49 | 47 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | GLOUCESTER | 456681 | 01930 | 15.2 |  |  | Solar |  | 05_12_51T1 | 09/06/2022 | 09/07/2022 | 1 | 0 | 1 | 09/08/2022 | 09/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | BOXFORD | 701737 | 01921 | 17.6 |  |  | Solar |  | 05_14_33L1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 176756 | 01824 | 20.86 |  |  | Solar |  | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 3/1/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/1/2016 | 11/1/2016 | 11/1/2016 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | METHUEN | 660642 | 01844 | 5.76 |  |  | Solar |  | 05_14_74L1 | 12/13/2024 | 01/30/2025 | 27 | 25 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 12/13/2024 | 4/10/2026 | Y | EXP | 365 | 05/07/2025 | 12/22/2025 | 230 | 0 | 230 |  |  |  | Completion Documents |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | BILLERICA | 175938 | 01821 | 16 |  |  | Solar |  | 05_14_92L6 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 6/15/2016 | Connected |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | AUBURN | 728456 | 01501 | 10 |  |  | Solar |  | 05_01_26W1 | 10/22/2025 | 10/26/2025 | 8 | 6 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Hopedale-West |  |  | Closed - Construction Hold
National Grid | DUDLEY | 391345 | 01571 | 7.6 |  |  | Solar |  | 05_01_412L4 | 11/11/2021 | 12/28/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 11/11/2021 | 8/26/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting - Completion Documents Hold
National Grid | HUBBARDSTON | 319090 | 01452 | 15.2 |  |  | Solar |  | 05_01_602W2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 03/02/2021 | 03/19/2021 | 17 | 0 | 17 |  |  | 7/15/2021 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTPORT | 176227 | 02790 | 10 |  |  | Solar |  | 05_05_115W52 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 01/21/2016 | 01/28/2016 | 5 | 0 | 5 | 9/23/2015 | 9/23/2015 | 5/5/2016 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | GLOUCESTER | 677404 | 01930 | 8.36 |  |  | Solar |  | 05_12_24J11 | 03/12/2025 | 03/26/2025 | 10 | 6 | 4 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | BEVERLY | 456466 | 01915 | 0 |  |  | Solar |  | 05_12_51T1 | 09/26/2022 | 09/30/2022 | 4 | 3 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | TOPSFIELD | 724078 | 01983 | 16 |  |  | Solar |  | 05_14_33L1 | 10/04/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N | Shutesbury |  |  | Closed
National Grid | WESTFORD | 177190 | 01886 | 323 |  |  | Solar |  | 05_14_58L2 | 08/21/2015 | 08/21/2015 | 4 | 0 | 4 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 11/05/2015 | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 |  | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 8/1/2017 | Y | EXP | 539 | 06/15/2017 | 09/06/2017 | 57 | 0 | 57 | 8/30/2017 | 8/30/2017 | 9/7/2017 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | METHUEN | 176225 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 05/06/2016 | 09/02/2016 | 82 | 0 | 82 | 9/23/2015 | 9/23/2015 | 9/13/2016 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | BILLERICA | 729908 | 01821 | 5.76 |  |  | Solar |  | 05_01_26W1 | 10/29/2025 | 12/01/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Ayer-Clinton |  |  | Closed
National Grid | AUBURN | 440471 | 01501 | 15.2 |  |  | Solar |  | 05_01_412L4 | 06/27/2022 | 06/30/2022 | 3 | 0 | 3 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Closed
National Grid | DUDLEY | 326400 | 01571 | 84 |  |  | Solar |  | 05_01_602W2 | 11/17/2020 | 02/18/2021 | 62 | 54 | 8 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 02/19/2021 | 02/23/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | Closed
National Grid | HUBBARDSTON | 176895 | 01452 | 1500 |  |  | Solar |  | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/6/2018 | Y | STD | 842 |  |  | 0 | 0 | 0 |  |  | 12/3/2018 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | WESTPORT | 691429 | 02790 | 14.79 |  |  | Solar |  | 05_12_24J11 | 05/14/2025 | 05/29/2025 | 9 | 3 | 6 | 05/30/2025 | 05/30/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 05/14/2025 | 7/14/2026 | Y | EXP | 365 | 09/26/2025 | 11/18/2025 | 54 | 0 | 54 |  |  | 11/21/2025 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | GLOUCESTER | 456448 | 01930 | 22.8 |  |  | Solar |  | 05_12_51T1 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 | 11/18/2022 | 7/16/2024 | Y | EXP | 550 | 04/05/2023 | 06/12/2023 | 69 | 0 | 69 |  |  | 5/20/2024 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | MANCHESTER | 720945 | 01944 | 23 |  |  | Solar |  | 05_14_33L1 | 09/22/2025 | 09/24/2025 | 2 | 0 | 2 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Scituate |  |  | Closed
National Grid | TOPSFIELD | 178313 | 01983 | 875 |  |  | Solar |  | 05_14_58L2 | 02/26/2018 | 02/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 04/06/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 02/26/2018 | 4/4/2022 | Y | STD | 100 | 04/20/2021 | 10/12/2021 | 175 | 3 | 172 |  |  | 3/28/2022 | Connected |  | N | Scituate |  |  | Closed
National Grid | CHELMSFORD | 720467 | 01824 | 15.2 |  |  | Solar |  | 05_14_74L1 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Brockton-South |  |  | Closed
National Grid | HAVERHILL | 176469 | 01832 | 10 |  |  | Solar |  | 05_14_92L6 | 03/17/2016 | 03/17/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/17/2016 | 3/23/2017 | Y | EXP | 345 | 06/21/2016 | 07/29/2016 | 27 | 0 | 27 | 9/20/2016 | 9/20/2016 | 9/23/2016 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | BILLERICA | 175987 | 01821 | 1000 |  |  | Solar |  | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | -412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Closed
National Grid | AUBURN | 443970 | 01501 | 0 |  |  | Other |  | 05_01_412L4 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Closed
National Grid | WEBSTER | 342428 | 01570 | 9.6 |  |  | Solar |  | 05_01_602W2 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | WESTMINSTER | 176894 | 01473 | 4000.002 |  |  | Solar |  | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 | 05/05/2018 | 10/03/2018 | 151 | 0 | 151 |  |  | 11/30/2018 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | WESTPORT | 177146 | 02790 | 25 |  |  | Solar |  | 05_12_24J2 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 | 08/09/2016 | 08/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 8/14/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | GLOUCESTER | 480578 | 01930 | 0 |  |  | Solar |  | 05_12_51T1 | 11/28/2022 | 11/29/2022 | 1 | 0 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2023 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | BEVERLY | 731440 | 01915 | 14.44 |  |  | Solar |  | 05_14_33L2 | 11/05/2025 | 11/05/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Marlborough |  |  | Closed
National Grid | BOXFORD | 378906 | 01921 | 11.4 |  |  | Solar |  | 05_14_58L2 | 08/30/2021 | 10/07/2021 | 27 | 26 | 1 | 10/08/2021 | 10/08/2021 | 81 | 58 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  | 5/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2022 | Connected |  | N | Marlborough |  |  | Closed
National Grid | CHELMSFORD | 733696 | 01824 | 3.8 |  |  | Solar |  | 05_14_74L1 | 11/13/2025 | 11/14/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Fall River-South |  |  | Closed
National Grid | METHUEN | 199034 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 10/19/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-South |  |  | Closed
National Grid | BILLERICA | 175986 | 01821 | 1000 |  |  | Solar |  | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | -412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Fall River-South |  |  | Closed
National Grid | AUBURN | 445324 | 01501 | 7.6 |  |  | Solar |  | 05_01_412L4 | 09/27/2022 | 10/12/2022 | 10 | 7 | 3 | 10/13/2022 | 10/13/2022 | 18 | 0 | 18 | 11/29/2022 | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 10/25/2024 | N | EXP | 365 | 04/10/2024 | 06/13/2024 | 65 | 0 | 65 |  |  | 7/8/2024 | Connected |  | N | Fall River-South |  |  | Closed
National Grid | DUDLEY | 342936 | 01571 | 7.68 |  |  | Solar |  | 05_01_602W2 | 03/02/2021 | 03/08/2021 | 4 | 4 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | Y | Bridgewater |  |  | Closed
National Grid | GARDNER | 176902 | 01440 | 750 |  |  | Solar |  | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N | Bridgewater |  |  | Closed
National Grid | WESTPORT | 396049 | 02790 | 0 |  |  | Other |  | 05_12_24J2 | 01/04/2022 | 01/19/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/01/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro |  |  | Closed
National Grid | GLOUCESTER | 486700 | 01930 | 0 |  |  | Solar |  | 05_12_51T1 | 12/21/2022 | 12/27/2022 | 4 | 3 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N | Attleboro |  |  | Closed
National Grid | BEVERLY | 177680 | 01965 | 45.6 |  |  | Solar |  | 05_14_33L2 | 07/25/2017 | 07/25/2017 | 35 | 33 | 2 | 09/13/2017 | 09/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2017 |  | 7/30/2018 | N | EXP | 320 |  |  | 0 | 0 | 0 | 2/13/2018 | 2/13/2018 | 2/13/2018 | Connected |  | N | Attleboro |  |  | Closed - Awaiting Payment
National Grid | BOXFORD | 410741 | 01921 | 6 |  |  | Solar |  | 05_14_58L2 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/21/2022 | 2/15/2024 | Y | EXP | 365 | 01/28/2023 | 02/14/2023 | 18 | 0 | 18 |  |  | 3/10/2023 | Connected |  | N | Hanover |  |  | Closed
National Grid | CHELMSFORD | 734937 | 01824 | 11.5 |  |  | Solar |  | 05_14_74L1 | 11/19/2025 | 12/01/2025 | 8 | 7 | 1 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hanover |  |  | Closed
National Grid | METHUEN | 221173 | 01844 |  |  |  | Solar |  | 05_14_92L6 | 04/19/2019 |  | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Closed
National Grid | BILLERICA | 175985 | 01821 | 1000 |  |  | Solar |  | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | -412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Closed
National Grid | AUBURN | 484394 | 01501 | 7.6 |  |  | Solar |  | 05_01_412L4 | 12/09/2022 | 12/14/2022 | 3 | 1 | 2 | 12/15/2022 | 12/15/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Closed
National Grid | DUDLEY | 346682 | 01571 | 22.8 |  |  | Solar |  | 05_01_602W2 | 03/18/2021 | 04/01/2021 | 10 | 10 | 0 | 04/02/2021 | 04/02/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/18/2021 | 4/1/2022 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Closed
National Grid | HUBBARDSTON | 176922 | 01452 | 996 |  |  | Solar |  | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | FALL RIVER | 615112 | 02720 | 6 |  |  | Solar |  | 05_12_24J2 | 06/05/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/05/2024 | 8/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2024 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | GLOUCESTER | 495086 | 01930 | 0 |  |  | Solar |  | 05_12_51T1 | 01/27/2023 | 03/16/2023 | 33 | 32 | 1 | 03/17/2023 | 03/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 7/23/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | MANCHESTER | 178574 | 01944 | 11.4 |  |  | Solar |  | 05_14_33L2 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 7/15/2020 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 3/23/2020 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | TOPSFIELD | 576775 | 01983 | 23 |  |  | Solar |  | 05_14_58L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 03/05/2024 | 03/05/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 174576 | 01824 | 1000 |  |  | Solar |  | 05_14_74L1 | 04/01/2011 | 04/01/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 06/22/2011 | 08/20/2012 | 289 | 0 | 289 | 05/04/2011 | 06/15/2011 | 29 | 0 | 29 |  | 08/20/2012 | 289 | 0 | 289 |  |  | 0 | 0 | 0 | 10/11/2012 | 04/01/2011 | 10/31/2012 | Y | STD | 20 | 05/14/2013 | 09/16/2013 | 85 | 0 | 85 | 7/9/2013 | 7/9/2013 | 7/25/2013 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | METHUEN | 230013 | 01844 | 15.2 |  |  | Solar |  | 05_14_92L6 | 05/21/2019 | 05/28/2019 | 3 | 1 | 2 | 05/29/2019 | 05/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 05/21/2019 | 11/1/2019 | Y | EXP | 147 | 07/25/2019 | 10/02/2019 | 69 | 0 | 69 |  |  | 10/8/2019 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | BILLERICA | 175984 | 01821 | 1000 |  |  | Solar |  | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/21/2015 | N | STD | -421 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | AUBURN | 516711 | 01540 | 9.28 |  |  | Solar |  | 05_01_412L4 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/29/2023 | 12/7/2024 | Y | EXP | 365 | 03/01/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 5/2/2024 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | DUDLEY | 351897 | 01571 | 3.8 |  |  | Solar |  | 05_01_602W2 | 05/10/2021 | 05/14/2021 | 3 | 0 | 3 | 05/17/2021 | 05/17/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Somerset |  |  | Closed
National Grid | GARDNER | 176921 | 01440 | 996 |  |  | Solar |  | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N | Somerset |  |  | Closed
National Grid | FALL RIVER | 664113 | 02720 | 5.76 |  |  | Solar |  | 05_12_24J2 | 01/07/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Time Frame Suspension - Design Hold
National Grid | GLOUCESTER | 496638 | 01930 | 7.6 |  |  | Solar |  | 05_12_51T1 | 02/24/2023 | 02/28/2023 | 2 | 0 | 2 | 03/01/2023 | 03/01/2023 | 167 | 127 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2023 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | BEVERLY | 348454 | 01915 | 10 |  |  | Solar |  | 05_14_33L2 | 04/14/2021 | 04/14/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 | 04/14/2021 | 4/14/2022 | Y | EXP | 365 | 07/14/2021 | 07/13/2021 | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | TOPSFIELD | 579860 | 01983 | 7.875 |  |  | Solar |  | 05_14_58L2 | 01/18/2024 | 02/01/2024 | 11 | 9 | 2 | 02/02/2024 | 02/02/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/18/2024 | 2/26/2025 | Y | EXP | 365 | 03/20/2024 | 04/09/2024 | 21 | 0 | 21 |  |  | 4/12/2024 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | CHELMSFORD | 175052 | 01824 | 2000 |  |  | Solar |  | 05_14_74L1 | 07/20/2011 | 07/20/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2011 | 09/13/2011 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2012 | 07/20/2011 | 6/30/2014 | Y | STD | 740 | 04/01/2014 | 06/18/2014 | 53 | 0 | 53 | 6/25/2014 | 6/25/2014 | 6/23/2014 | Connected |  | N | Marlborough |  |  | Closed
National Grid | METHUEN | 354556 | 01844 | 10 |  |  | Solar |  | 05_14_92L6 | 04/26/2021 | 05/04/2021 | 5 | 5 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2021 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | BILLERICA | 175983 | 01821 | 4875 |  |  | Solar |  | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 03/20/2015 | 5/25/2022 | Y | STD | 610 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | AUBURN | 517480 | 01501 | 14.79 |  |  | Solar |  | 05_01_412L4 | 04/06/2023 | 04/10/2023 | 2 | 0 | 2 | 04/11/2023 | 04/11/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 452437 | 01571 | 8.12 |  |  | Solar |  | 05_01_602W2 | 10/04/2022 | 10/28/2022 | 18 | 14 | 4 | 10/31/2022 | 10/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 10/04/2022 | 5/4/2024 | Y | EXP | 365 | 04/20/2023 | 05/03/2023 | 14 | 0 | 14 |  |  | 5/12/2023 | Connected |  | N | Fall River-South |  |  | Closed
National Grid | HUBBARDSTON | 176947 | 01452 | 11.4 |  |  | Solar |  | 05_05_115W52 | 03/06/2017 | 03/06/2017 | 8 | 7 | 1 | 03/17/2017 | 03/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 |  | 1/21/2020 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 1/11/2020 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTPORT | 672436 | 02790 | 5.76 |  |  | Solar |  | 05_12_24J2 | 02/17/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Closed
National Grid | GLOUCESTER | 514443 | 01930 | 0 |  |  | Solar |  | 05_12_51T1 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 72 | 54 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Execute ISAs
National Grid | MANCHESTER | 499234 | 01944 | 15 |  |  | Solar |  | 05_14_33L2 | 02/07/2023 | 02/21/2023 | 10 | 9 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2023 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | BOXFORD | 636327 | 01921 | 5 |  |  | Solar |  | 05_14_58L2 | 08/29/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | WESTFORD | 176057 | 01886 | 996 |  |  | Solar |  | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 | 03/27/2015 | 8/1/2015 | Y | STD | -132 | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 | 11/16/2017 | 11/16/2017 | 11/16/2017 | Connected |  | N | Bridgewater |  |  | Closed
National Grid | HAVERHILL | 367329 | 01832 | 7.6 |  |  | Solar |  | 05_14_92L6 | 07/20/2021 | 07/21/2021 | 0 | 0 | 0 | 07/22/2021 | 07/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2021 | 07/20/2021 | 5/20/2023 | Y | EXP | 365 | 01/18/2022 | 05/20/2022 | 123 | 0 | 123 |  |  | 6/8/2022 | Connected |  | N | Methuen |  |  | Closed
National Grid | BILLERICA | 176341 | 01821 | 8.6 |  |  | Solar |  | 05_01_26W1 | 02/25/2015 | 02/25/2015 | 9 | 6 | 3 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/18/2016 | 03/14/2016 | 17 | 0 | 17 | 3/17/2015 | 3/17/2015 | 5/5/2016 | Connected |  | N | Methuen |  |  | Closed
National Grid | AUBURN | 556681 | 01501 | 10 |  |  | Solar |  | 05_01_412L4 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 09/25/2023 | 12/20/2024 | Y | EXP | 365 | 03/06/2024 | 04/17/2024 | 43 | 0 | 43 |  |  | 5/22/2024 | Connected |  | N | Fall River-North |  |  | Closed
National Grid | DUDLEY | 438280 | 01571 | 15.2 |  |  | Solar |  | 05_01_602W2 | 03/12/2024 | 07/04/2022 | 15 | 13 | 2 | 04/02/2024 | 04/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N | Fall River-South |  |  | Closed
National Grid | GARDNER | 176941 | 01440 | 7.6 |  |  | Solar |  | 05_05_115W52 | 12/19/2016 | 12/19/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 | 12/19/2016 | 2/28/2018 | Y | EXP | 421 | 09/15/2017 | 12/11/2017 | 53 | 0 | 53 | 2/20/2018 | 2/20/2018 | 3/6/2018 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | FALL RIVER | 177120 | 02721 | 420 |  |  | Solar |  | 05_12_24J8 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 44 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Closed
National Grid | GLOUCESTER | 516409 | 01930 | 15.007 |  |  | Solar |  | 05_12_51T1 | 04/14/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Closed
National Grid | GLOUCESTER | 566735 | 01930 | 34.2 |  |  | Solar |  | 05_14_33L2 | 02/28/2024 | 07/12/2024 | 93 | 90 | 3 | 07/15/2024 | 07/15/2024 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | BOXFORD | 695649 | 01921 | 5.76 |  |  | Solar |  | 05_14_58L2 | 06/09/2025 | 06/12/2025 | 3 | 0 | 3 | 06/13/2025 | 06/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N | Worcester North - Dont Use |  |  | Closed
National Grid | WESTFORD | 176056 | 01886 | 980 |  |  | Solar |  | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 |  |  |  | Withdrawn |  | N | Worcester North - Dont Use |  |  | Closed
National Grid | HAVERHILL | 638125 | 01832 | 10 |  |  | Solar |  | 05_14_92L6 | 09/05/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South |  |  | Closed
National Grid | BILLERICA | 177031 | 01821 | 3.8 |  |  | Solar |  | 05_01_26W1 | 03/20/2017 | 03/20/2017 | 6 | 5 | 1 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/25/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N | Somerset |  |  | Closed
National Grid | AUBURN | 558380 | 01501 | 15.2 |  |  | Solar |  | 05_01_412L4 | 10/02/2023 | 10/23/2023 | 15 | 14 | 1 | 10/24/2023 | 10/24/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N | Cape Ann |  |  | Closed
National Grid | DUDLEY | 473103 | 01571 | 14.79 |  |  | Solar |  | 05_01_602W2 | 11/03/2022 |  | 171 | 72 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | GARDNER | 177142 | 01440 | 6 |  |  | Solar |  | 05_05_115W52 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 | 05/27/2016 | 6/6/2017 | Y | EXP | 350 | 09/01/2016 | 09/12/2016 | 6 | 0 | 6 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N | Cape Ann |  |  | Closed
National Grid | WESTPORT | 728080 | 02790 | 11.5 |  |  | Solar |  | 05_12_24W1 | 10/28/2025 | 11/03/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Cape Ann |  |  | Closed
National Grid | LYNN | 554842 | 01904 | 10 |  |  | Solar |  | 05_12_51T1 | 09/12/2023 | 09/14/2023 | 2 | 0 | 2 | 09/15/2023 | 09/15/2023 | 134 | 51 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | BEVERLY | 667060 | 01915 | 23 |  |  | Solar |  | 05_14_33L2 | 01/21/2025 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | BOXFORD | 613783 | 01921 | 0 |  |  | Battery Add-On |  | 05_14_58L3 | 05/28/2024 | 06/20/2024 | 16 | 13 | 3 | 06/21/2024 | 06/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Terminated |  | Y | Cape Ann |  |  | Closed
National Grid | WESTFORD | 176913 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed - Pending
National Grid | METHUEN | 643835 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 10/01/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | BILLERICA | 177489 | 01821 | 288 |  |  | Solar |  | 05_01_26W1 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 10/1/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/14/2017 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | AUBURN | 527634 | 01501 | 6 |  |  | Solar |  | 05_01_412L4 | 10/24/2023 | 05/25/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 65 | 42 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 487740 | 01571 | 9.86 |  |  | Solar |  | 05_01_602W2 | 01/05/2023 | 01/09/2023 | 2 | 0 | 2 | 01/10/2023 | 01/10/2023 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica |  |  | Closed
National Grid | WESTMINSTER | 177134 | 01473 | 15.2 |  |  | Solar |  | 05_05_115W52 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 11/17/2017 | Connected |  | N | North Andover |  |  | Closed
National Grid | WESTPORT | 175225 | 02790 | 11.25 |  |  | Solar |  | 05_12_24W1 | 01/06/2015 | 01/06/2015 | 10 | 7 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 7/6/2015 | Connected |  | N | North Andover |  |  | Closed
National Grid | LYNN | 567996 | 01904 | 10 |  |  | Solar |  | 05_12_51T1 | 11/15/2023 | 11/27/2023 | 7 | 0 | 7 | 11/28/2023 | 11/28/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed
National Grid | ESSEX | 670708 | 01929 | 10 |  |  | Solar |  | 05_14_33L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed
National Grid | TOPSFIELD | 698097 | 01983 | 9.5 |  |  | Solar |  | 05_14_58L3 | 06/12/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 72 | 47 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | North Andover |  |  | Closed
National Grid | WESTFORD | 176972 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 10/05/2016 | 10/05/2016 | 2 | 2 | 0 | 10/10/2016 | 10/10/2016 | 91 | 0 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/11/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed
National Grid | METHUEN | 645912 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/18/2024 | 1/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N | Tewksbury |  |  | Closed
National Grid | BILLERICA | 177645 | 01821 | 10 |  |  | Solar |  | 05_01_26W1 | 09/25/2017 | 11/13/2017 | 27 | 27 | 0 | 11/13/2017 | 11/13/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/1/2018 | N | EXP | 321 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N | Beverly |  |  | Closed
National Grid | AUBURN | 547469 | 01501 | 6 |  |  | Solar |  | 05_01_412L4 | 08/23/2023 | 08/28/2023 | 3 | 1 | 2 | 08/29/2023 | 08/29/2023 | 53 | 26 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Beverly |  |  | Closed
National Grid | DUDLEY | 493004 | 01571 | 15.95 |  |  | Solar |  | 05_01_602W2 | 01/17/2023 | 02/08/2023 | 16 | 15 | 1 | 02/09/2023 | 02/09/2023 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 01/17/2023 | 7/26/2024 | Y | EXP | 365 | 08/15/2023 | 09/22/2023 | 39 | 0 | 39 |  |  | 10/3/2023 | Connected |  | N | Adams-Deerfield |  |  | Closed
National Grid | WESTMINSTER | 177294 | 01473 | 17.6 |  |  | Solar |  | 05_05_115W52 | 08/24/2016 | 08/24/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/3/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Adams-Deerfield |  |  | Closed
National Grid | WESTPORT | 175968 | 02790 | 6 |  |  | Solar |  | 05_12_24W1 | 08/06/2015 | 08/06/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Leominster |  |  | Closed
National Grid | LYNN | 575964 | 01904 | 8.99 |  |  | Solar |  | 05_12_51T1 | 12/05/2023 | 12/11/2023 | 4 | 3 | 1 | 12/12/2023 | 12/12/2023 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N | Leominster |  |  | Closed
National Grid | GLOUCESTER | 686801 | 01930 | 11.78 |  |  | Solar |  | 05_14_33L2 | 04/22/2025 | 07/25/2025 | 37 | 24 | 13 | 07/28/2025 | 07/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Southwest |  |  | Closed
National Grid | BOXFORD | 710796 | 01921 | 200 |  |  | Solar |  | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 69 | 62 | 7 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-Southwest |  |  | Closed
National Grid | WESTFORD | 177164 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 88 | 0 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Northampton |  |  | Closed
National Grid | METHUEN | 646409 | 01844 | 5.76 |  |  | Solar |  | 05_14_92L6 | 10/25/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/25/2024 | 1/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | BILLERICA | 178467 | 01821 | 299.7 |  |  | Solar |  | 05_01_26W1 | 01/23/2018 | 02/22/2018 | 2 | 2 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 2/28/2020 | N | EXP | 518 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | AUBURN | 552482 | 01501 | 10 |  |  | Solar |  | 05_01_412L4 | 09/13/2023 | 09/19/2023 | 4 | 2 | 2 | 09/20/2023 | 09/20/2023 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | DUDLEY | 511164 | 01571 | 9.57 |  |  | Solar |  | 05_01_602W2 | 03/15/2023 | 04/21/2023 | 26 | 25 | 1 | 04/24/2023 | 04/24/2023 | 90 | 73 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | HUBBARDSTON | 178128 | 01452 | 7.6 |  |  | Solar |  | 05_05_115W52 | 07/11/2017 | 07/11/2017 | 5 | 5 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | Y | Hopedale-East |  |  | Closed
National Grid | WESTPORT | 176777 | 02790 | 8.5 |  |  | Solar |  | 05_12_24W1 | 11/04/2015 | 11/04/2015 | 3 | 3 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 11/9/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 1/10/2017 | Connected |  | N | Marlborough |  |  | Closed
National Grid | LYNN | 590822 | 01904 | 8.7 |  |  | Solar |  | 05_12_51T1 | 03/01/2024 | 03/08/2024 | 5 | 3 | 2 | 03/11/2024 | 03/11/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/01/2024 | 4/21/2025 | Y | EXP | 365 | 05/16/2024 | 10/02/2024 | 140 | 1 | 139 |  |  | 8/14/2024 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | ESSEX | 697072 | 01929 | 20.16 |  |  | Solar |  | 05_14_33L2 | 06/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | BOXFORD | 710791 | 01921 | 240 |  |  | Solar |  | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 69 | 62 | 7 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Chelmsford/Westford |  |  | Closed
National Grid | WESTFORD | 177621 | 01886 | 15.2 |  |  | Solar |  | 05_14_74L1 | 11/09/2017 | 11/09/2017 | 11 | 10 | 1 | 11/29/2017 | 11/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 11/15/2018 | N | EXP | 520 |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | METHUEN | 653778 | 01844 | 10 |  |  | Solar |  | 05_14_92L6 | 11/18/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/18/2024 | 3/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | BILLERICA | 194297 | 01821 | 250 |  |  | Solar |  | 05_01_26W1 | 08/24/2018 | 08/28/2018 | 1 | 0 | 1 | 08/29/2018 | 08/29/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford |  |  | Closed
National Grid | AUBURN | 552358 | 01501 | 6 |  |  | Solar |  | 05_01_412L4 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/01/2023 | 10/27/2024 | Y | EXP | 365 | 01/27/2024 | 04/03/2024 | 68 | 0 | 68 |  |  | 4/16/2024 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | DUDLEY | 523055 | 01571 | 7.6 |  |  | Solar |  | 05_01_602W2 | 05/15/2023 | 05/15/2023 | 0 | 0 | 0 | 05/16/2023 | 05/16/2023 | 195 | 34 | 161 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica |  |  | Closed
National Grid | WESTMINSTER | 178175 | 01473 | 15.2 |  |  | Solar |  | 05_05_115W52 | 03/23/2018 | 03/23/2018 | 2 | 1 | 1 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 3/31/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N | North Andover |  |  | Closed
National Grid | WESTPORT | 177282 | 02790 | 10 |  |  | Solar |  | 05_12_24W1 | 06/14/2016 | 06/14/2016 | 1 | 1 | 0 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N | North Andover |  |  | Closed
National Grid | LYNN | 610191 | 01904 | 5.76 |  |  | Solar |  | 05_12_51T1 | 05/14/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater |  |  | Closed
National Grid | MANCHESTER | 177297 | 01944 | 16 |  |  | Solar |  | 05_14_34M1 | 08/26/2016 | 08/26/2016 | 7 | 7 | 0 | 09/08/2016 | 09/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/3/2017 | N | EXP | 359 |  |  | 0 | 0 | 0 | 11/21/2016 | 11/21/2016 | 11/23/2016 | Connected |  | N | Marlborough |  |  | Closed
National Grid | BYFIELD | 710790 | 01922 | 240 |  |  | Solar |  | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 69 | 62 | 7 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Ayer-Clinton |  |  | Closed
National Grid | WESTFORD | 177732 | 01886 | 8.32 |  |  | Solar |  | 05_14_74L1 | 03/22/2017 | 03/22/2017 | 27 | 27 | 0 | 05/01/2017 | 05/01/2017 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/27/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen |  |  | Closed
National Grid | METHUEN | 654416 | 01844 | 5 |  |  | Solar |  | 05_14_92L6 | 11/14/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/14/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | BILLERICA | 205077 | 01821 | 7.6 |  |  | Solar |  | 05_01_26W1 | 02/07/2019 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Beverly |  |  | Closed
National Grid | AUBURN | 572497 | 01501 | 7.25 |  |  | Solar |  | 05_01_412L4 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 31 | 6 | 25 | 02/09/2024 | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/7/2025 | N | EXP | 365 | 03/08/2024 | 04/19/2024 | 43 | 0 | 43 |  |  | 5/30/2024 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | DUDLEY | 553543 | 01571 | 6 |  |  | Solar |  | 05_01_602W2 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 12/2/2024 | Y | EXP | 365 | 05/03/2024 | 05/18/2024 | 16 | 0 | 16 |  |  | 5/23/2024 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | HUBBARDSTON | 178687 | 01452 | 3500 |  |  | Solar |  | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/5/2018 | Y | STD | 261 | 08/03/2018 | 10/09/2018 | 67 | 0 | 67 |  |  | 11/27/2018 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTPORT | 177814 | 02790 | 3.8 |  |  | Solar |  | 05_12_24W1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 219 | 0 | 219 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Worcester North/South |  |  | Closed - Completion Documents Hold
National Grid | LYNN | 613784 | 01904 | 21.125 |  |  | Solar |  | 05_12_51T1 | 06/11/2024 | 06/14/2024 | 4 | 1 | 3 | 06/17/2024 | 06/17/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | BEVERLY | 277157 | 01915 | 0 |  |  | Battery Add-On |  | 05_14_34M1 | 01/30/2020 | 01/31/2020 | 1 | 1 | 0 | 02/03/2020 | 02/03/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2020 | Connected |  | N | Bridgewater |  |  | Closed
National Grid | NEWBURY | 710780 | 01985 | 67.3 |  |  | Solar |  | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 69 | 62 | 7 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hanover |  |  | Closed
National Grid | WESTFORD | 178372 | 01886 | 20 |  |  | Solar |  | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N | Hanover |  |  | Closed
National Grid | METHUEN | 655710 | 01844 | 3.8 |  |  | Solar |  | 05_14_92L6 | 11/20/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 11/20/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N | Hanover |  |  | Closed
National Grid | BILLERICA | 208525 | 01821 | 2340 |  |  | Solar |  | 05_01_26W1 | 02/13/2019 |  | 176 | 51 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed
National Grid | AUBURN | 573922 | 01501 | 10 |  |  | Solar |  | 05_01_412L4 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/01/2023 | 4/14/2025 | Y | EXP | 365 | 05/02/2024 | 08/23/2024 | 114 | 0 | 114 |  |  | 11/24/2024 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | DUDLEY | 561273 | 01571 | 6.38 |  |  | Solar |  | 05_01_602W2 | 11/14/2023 | 01/10/2024 | 39 | 31 | 8 | 01/11/2024 | 01/11/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Closed
National Grid | HUBBARDSTON | 178686 | 01452 | 1500 |  |  | Solar |  | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/6/2018 | Y | STD | 262 | 08/03/2018 | 02/20/2020 | 566 | 0 | 566 |  |  | 12/6/2018 | Connected |  | N | Hanover |  |  | Closed
National Grid | WESTPORT | 177896 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 06/15/2017 | 06/15/2017 | 9 | 9 | 0 | 06/28/2017 | 06/28/2017 | 150 | 0 | 150 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2017 |  | 6/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | Closed
National Grid | LYNN | 644032 | 01904 | 10 |  |  | Solar |  | 05_12_51T1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N | Bridgewater |  |  | Closed
National Grid | MANCHESTER | 418217 | 01944 | 9.772 |  |  | Solar |  | 05_14_34M1 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2022 | 05/11/2022 | 8/23/2023 | Y | EXP | 365 | 10/06/2022 | 11/03/2022 | 29 | 0 | 29 |  |  | 11/10/2022 | Connected |  | N | Chelmsford/Westford |  |  | Closed - Design Hold
National Grid | NEWBURY | 725182 | 01985 | 15.2 |  |  | Solar |  | 05_14_58L3 | 10/09/2025 | 10/20/2025 | 5 | 0 | 5 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-East |  |  | Closed
National Grid | WESTFORD | 178371 | 01886 | 20 |  |  | Solar |  | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 5/24/2019 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | METHUEN | 656812 | 01844 | 5.76 |  |  | Solar |  | 05_14_92L6 | 11/25/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/25/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N | Somerset |  |  | Closed
National Grid | BILLERICA | 223683 | 01821 | 10 |  |  | Solar |  | 05_01_26W1 | 04/30/2019 | 05/07/2019 | 4 | 0 | 4 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2019 | 04/30/2019 | 8/16/2022 | Y | EXP | 1100 | 09/23/2020 | 11/18/2020 | 56 | 0 | 56 |  |  |  | Withdrawn |  | N | Bridgewater |  |  | Closed
National Grid | AUBURN | 574933 | 01501 | 499 |  |  | Solar |  | 05_01_412L4 | 01/19/2024 |  | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North - Dont Use |  |  | Closed - Completion Documents Hold
National Grid | DUDLEY | 565997 | 01571 | 10 |  |  | Solar |  | 05_01_602W2 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/07/2023 | 1/10/2025 | Y | EXP | 365 | 03/23/2024 | 04/22/2024 | 31 | 0 | 31 |  |  | 4/30/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | WESTMINSTER | 178798 | 01473 | 6 |  |  | Solar |  | 05_05_115W52 | 02/14/2018 | 02/14/2018 | 18 | 0 | 18 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 |  | 2/19/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | WESTPORT | 201447 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 12/12/2018 | 4/14/2021 | Y | EXP | 365 | 11/03/2020 | 02/08/2021 | 97 | 0 | 97 |  |  | 3/17/2021 | Connected |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | LYNN | 653896 | 01904 | 7.6 |  |  | Solar |  | 05_12_51T1 | 11/15/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | BEVERLY | 605342 | 01915 | 10 |  |  | Solar |  | 05_14_34M1 | 06/05/2024 | 06/11/2024 | 1 | 0 | 1 | 06/12/2024 | 06/12/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 | 06/05/2024 | 7/19/2025 | Y | EXP | 365 | 10/12/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 11/14/2024 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension - Group Member Withdraw
National Grid | NEWBURY | 729434 | 01985 | 5.76 |  |  | Solar |  | 05_14_58L3 | 10/27/2025 | 10/29/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Fall River-North |  |  | Closed
National Grid | WESTFORD | 178370 | 01886 | 20 |  |  | Solar |  | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 11/26/2018 | N | EXP | 300 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N | Leominster |  |  | Closed
National Grid | METHUEN | 656807 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N | Tewksbury |  |  | Closed
National Grid | BILLERICA | 247021 | 01821 | 10 |  |  | Solar |  | 05_01_26W1 | 08/19/2019 | 08/26/2019 | 4 | 3 | 1 | 08/27/2019 | 08/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2019 |  | 11/25/2019 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N | Chelmsford/Westford |  |  | Closed
National Grid | AUBURN | 587291 | 01501 | 4.93 |  |  | Solar |  | 05_01_412L4 | 02/13/2024 | 02/15/2024 | 2 | 0 | 2 | 02/16/2024 | 02/16/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica |  |  | Closed
National Grid | DUDLEY | 566632 | 01571 | 2000 |  |  | Solar |  | 05_01_602W2 | 11/01/2023 |  | 95 | 55 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | HUBBARDSTON | 186693 | 01452 | 3300 |  |  | Solar |  | 05_05_115W52 | 08/07/2018 | 09/21/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 11/01/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Worcester North/South |  |  | Closed - Completion Documents Hold
National Grid | WESTPORT | 223585 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 | 06/05/2019 | 6/3/2020 | Y | EXP | 365 | 12/05/2019 | 12/16/2019 | 11 | 0 | 11 |  |  | 3/13/2020 | Connected |  | N | Hopedale-East |  |  | Closed
National Grid | LYNN | 657144 | 01904 | 7.6 |  |  | Solar |  | 05_12_51T1 | 11/26/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y | Hopedale-East |  |  | Closed
National Grid | BEVERLY | 641381 | 01915 | 10 |  |  | Solar |  | 05_14_34M1 | 09/18/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 09/18/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N | Tewksbury |  |  | Closed
National Grid | BYFIELD | 174768 | 01922 | 75 |  |  | Solar |  | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | -139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N | Fall River-South |  |  | Closed
National Grid | WESTFORD | 178369 | 01886 | 20 |  |  | Solar |  | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 8 | 36 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 3/22/2019 | N | EXP | 416 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | METHUEN | 658010 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 12/03/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 12/03/2024 | 8/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Closed
National Grid | BILLERICA | 248514 | 01821 | 10 |  |  | Solar |  | 05_01_26W1 | 09/04/2019 | 09/05/2019 | 0 | 0 | 0 | 09/06/2019 | 09/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 09/04/2019 | 5/11/2020 | Y | EXP | 237 | 12/21/2019 | 01/24/2020 | 34 | 0 | 34 |  |  | 2/10/2020 | Connected |  | N | Fall River-North |  |  | Closed - Completion Documents Hold
National Grid | AUBURN | 595397 | 01501 | 7.296 |  |  | Solar |  | 05_01_412L4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/01/2024 | 7/2/2025 | Y | EXP | 365 | 08/01/2024 | 08/19/2024 | 19 | 0 | 19 |  |  | 8/22/2024 | Connected |  | N | North Andover |  |  | Closed
National Grid | DUDLEY | 570427 | 01571 | 10 |  |  | Solar |  | 05_01_602W2 | 11/21/2023 | 11/30/2023 | 7 | 4 | 3 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Closed - Completion Documents Hold
National Grid | WESTMINSTER | 191028 | 01473 | 233.1 |  |  | Solar |  | 05_05_115W52 | 08/27/2018 | 09/10/2018 | 8 | 1 | 7 | 09/11/2018 | 09/11/2018 | 63 | 30 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Somerset |  |  | Closed
National Grid | FALL RIVER | 277587 | 02722 | 10 |  |  | Solar |  | 05_12_24W1 | 03/04/2020 | 03/16/2020 | 7 | 3 | 4 | 03/17/2020 | 03/17/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 | 03/04/2020 | 12/21/2022 | Y | EXP | 365 | 12/10/2020 | 03/11/2021 | 91 | 0 | 91 |  |  | 9/22/2022 | Connected |  | N | Somerset |  |  | Closed
National Grid | LYNN | 678570 | 01904 | 150 |  |  | Solar |  | 05_12_51T1 | 03/19/2025 | 04/30/2025 | 30 | 20 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Closed
National Grid | MANCHESTER | 454032 | 01944 | 21.75 |  |  | Solar |  | 05_14_36J2 | 09/01/2022 | 09/08/2022 | 4 | 4 | 0 | 09/09/2022 | 09/09/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Closed
National Grid | NEWBURY | 174767 | 01950 | 100 |  |  | Solar |  | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | -139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N | Hopedale-East |  |  | Closed - Construction Hold
National Grid | WESTFORD | 178489 | 01886 | 7 |  |  | Solar |  | 05_14_74L1 | 11/30/2017 | 11/30/2017 | 0 | 0 | 0 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/6/2018 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | METHUEN | 662600 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | BILLERICA | 338558 | 01821 | 7.6 |  |  | Solar |  | 05_01_26W1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/12/2021 | 1/20/2023 | Y | EXP | 365 | 12/15/2021 | 01/19/2022 | 36 | 0 | 36 |  |  | 1/25/2022 | Connected |  | N | Ayer-Clinton |  |  | Closed - Awaiting Payment
National Grid | AUBURN | 605221 | 01501 | 7.6 |  |  | Solar |  | 05_01_412L4 | 04/23/2024 | 05/14/2024 | 12 | 10 | 2 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N | Attleboro |  |  | Closed
National Grid | DUDLEY | 569809 | 01571 | 0 |  |  | Solar |  | 05_01_602W2 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 9/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | HUBBARDSTON | 196024 | 01452 | 7.6 |  |  | Solar |  | 05_05_115W52 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Closed
National Grid | WESTPORT | 515479 | 02790 | 3.8 |  |  | Solar |  | 05_12_24W1 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N | Brockton-North |  |  | Closed
National Grid | LYNN | 683594 | 01904 | 10 |  |  | Solar |  | 05_12_51T1 | 04/08/2025 | 05/19/2025 | 3 | 0 | 3 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/08/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | Y | Beverly |  |  | Closed
National Grid | ESSEX | 451338 | 01929 | 67.3 |  |  | Solar |  | 05_14_36J6 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 | 09/20/2022 | 09/20/2022 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | NEWBURY | 174796 | 01950 | 13 |  |  | Solar |  | 05_14_58L3 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2012 |  | 11/30/2012 | N | EXP | -1 |  |  | 0 | 0 | 0 | 2/7/2013 | 2/7/2013 | 2/21/2013 | Connected |  | N | Worcester North/South |  |  | Closed - Construction Hold
National Grid | WESTFORD | 178539 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 01/26/2018 | 01/26/2018 | 9 | 1 | 8 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 | 01/26/2018 | 1/31/2019 | Y | EXP | 356 | 06/12/2018 | 06/21/2018 | 9 | 0 | 9 |  |  | 8/20/2018 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | METHUEN | 663221 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 12/31/2024 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N | Bridgewater |  |  | Closed
National Grid | BILLERICA | 438906 | 01821 | 9.86 |  |  | Solar |  | 05_01_26W1 | 07/22/2022 | 07/26/2022 | 2 | 2 | 0 | 07/27/2022 | 07/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/22/2022 | 9/1/2023 | Y | EXP | 365 | 10/20/2022 | 03/08/2023 | 140 | 0 | 140 |  |  | 3/9/2023 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | AUBURN | 606033 | 01501 | 10 |  |  | Solar |  | 05_01_412L4 | 04/26/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N | North Andover |  |  | Closed
National Grid | DUDLEY | 579357 | 01571 | 5.22 |  |  | Solar |  | 05_01_602W2 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/26/2024 | 3/19/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | HUBBARDSTON | 199068 | 01452 | 10 |  |  | Solar |  | 05_05_115W52 | 10/21/2018 | 11/08/2018 | 12 | 6 | 6 | 11/09/2018 | 11/09/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTPORT | 560141 | 02790 | 6 |  |  | Solar |  | 05_12_24W1 | 10/19/2023 | 11/13/2023 | 17 | 15 | 2 | 11/14/2023 | 11/14/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | LYNN | 692067 | 01904 | 13.3 |  |  | Solar |  | 05_12_51T1 | 05/15/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 05/15/2025 | 8/14/2026 | Y | EXP | 365 | 10/17/2025 |  | 77 | 0 | 77 |  |  | 11/26/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | GLOUCESTER | 728333 | 01930 | 23 |  |  | Solar |  | 05_14_36L1 | 10/22/2025 | 10/27/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro |  |  | Closed
National Grid | NEWBURY | 177122 | 01950 | 0 |  |  | Solar |  | 05_14_58L3 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 02/03/2017 | 70 | 58 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Worcester North/South |  |  | Closed
National Grid | WESTFORD | 186105 | 01886 | 15.2 |  |  | Solar |  | 05_14_74L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South |  |  | Closed
National Grid | METHUEN | 714061 | 01844 | 7.6 |  |  | Solar |  | 05_14_92L6 | 08/29/2025 | 10/23/2025 | 5 | 0 | 5 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | BILLERICA | 478360 | 01821 | 13.34 |  |  | Solar |  | 05_01_26W1 | 12/07/2022 | 12/14/2022 | 5 | 2 | 3 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | AUBURN | 660754 | 01505 | 10 |  |  | Solar |  | 05_01_412L4 | 12/16/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 155 | 137 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 599345 | 01571 | 0 |  |  | Solar |  | 05_01_602W2 | 03/26/2024 | 04/26/2024 | 22 | 20 | 2 | 04/29/2024 | 04/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | WESTMINSTER | 204363 | 01473 | 0 |  |  | Solar |  | 05_05_115W52 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N | Attleboro |  |  | Closed
National Grid | WESTPORT | 565880 | 02790 | 10 |  |  | Solar |  | 05_12_24W1 | 11/03/2023 | 11/07/2023 | 2 | 0 | 2 | 11/08/2023 | 11/08/2023 | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 11/03/2023 | 4/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N | Ayer-Clinton |  |  | Closed - Group Member Withdraw
National Grid | LYNN | 698492 | 01904 | 11.4 |  |  | Solar |  | 05_12_51T1 | 06/13/2025 | 06/30/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | BEVERLY | 175095 | 01915 | 12 |  |  | Solar |  | 05_14_36L1 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 | 11/19/2012 | 11/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2013 |  | 1/31/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 3/14/2013 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | NEWBURY | 202799 | 01950 | 10 |  |  | Solar |  | 05_14_58L3 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 2/6/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N | Tewksbury |  |  | Closed
National Grid | WESTFORD | 187541 | 01886 | 11.4 |  |  | Solar |  | 05_14_74L1 | 06/08/2018 | 06/08/2018 | 10 | 0 | 10 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 6/8/2020 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | METHUEN | 686883 | 01844 | 12 |  |  | Solar |  | 05_14_9J1 | 04/30/2025 | 07/21/2025 | 54 | 50 | 4 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | CHELMSFORD | 480883 | 01824 | 0 |  |  | Solar |  | 05_01_26W1 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton |  |  | Closed
National Grid | AUBURN | 664981 | 01501 | 10 |  |  | Solar |  | 05_01_412L4 | 01/10/2025 | 01/28/2025 | 7 | 2 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 01/10/2025 | 7/12/2026 | Y | EXP | 365 | 06/12/2025 | 07/08/2025 | 27 | 0 | 27 |  |  | 10/28/2025 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | DUDLEY | 625690 | 01571 | 6 |  |  | Solar |  | 05_01_602W2 | 07/19/2024 | 08/05/2024 | 5 | 3 | 2 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 9/11/2025 | Y | EXP | 365 | 10/10/2024 | 10/31/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | GARDNER | 257375 | 01440 | 10 |  |  | Solar |  | 05_05_115W52 | 10/14/2019 | 10/21/2019 | 5 | 5 | 0 | 10/22/2019 | 10/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 10/14/2019 | 7/7/2020 | Y | EXP | 365 | 12/20/2019 | 02/19/2020 | 61 | 0 | 61 |  |  | 2/20/2020 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | WESTPORT | 573665 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 12/11/2023 | 12/12/2023 | 1 | 0 | 1 | 12/13/2023 | 12/13/2023 | 64 | 40 | 24 | 05/03/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | LYNN | 704375 | 01904 | 24.7 |  |  | Solar |  | 05_12_51T1 | 07/14/2025 | 07/30/2025 | 10 | 8 | 2 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | BEVERLY | 218135 | 01915 | 18.85 |  |  | Solar |  | 05_14_36L1 | 04/09/2019 | 04/12/2019 | 3 | 3 | 0 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 8/20/2019 | N | EXP | 125 |  |  | 0 | 0 | 0 |  |  | 8/15/2019 | Connected |  | N | Northampton |  |  | Closed
National Grid | NEWBURY | 247730 | 01950 | 10 |  |  | Solar |  | 05_14_58L3 | 08/12/2019 | 08/13/2019 | 0 | 0 | 0 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 8/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N | Fall River-South |  |  | Closed - Design Hold
National Grid | WESTFORD | 205269 | 01886 | 1500 |  |  | Solar |  | 05_14_74L1 | 01/04/2019 | 02/08/2019 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/11/2019 | 03/06/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest |  |  | Study Complete
National Grid | METHUEN | 175760 | 01844 | 75 |  |  | Solar |  | 05_14_9J1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 04/28/2015 | 35 | 0 | 35 | 6/2/2015 | 6/2/2015 | 6/2/2015 | Connected |  | N | Billerica |  |  | Closed
National Grid | CHELMSFORD | 514516 | 01824 | 14.79 |  |  | Solar |  | 05_01_26W1 | 04/07/2023 | 04/20/2023 | 8 | 7 | 1 | 04/21/2023 | 04/21/2023 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 |  | 9/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N | Spencer-Rutland |  |  | Time Frame Suspension
National Grid | AUBURN | 669061 | 01501 | 11.5 |  |  | Solar |  | 05_01_412L4 | 02/04/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/04/2025 | 4/14/2026 | Y | EXP | 365 | 05/06/2025 | 07/11/2025 | 67 | 0 | 67 |  |  | 7/30/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | DUDLEY | 626147 | 01571 | 6 |  |  | Solar |  | 05_01_602W2 | 07/22/2024 | 08/19/2024 | 7 | 5 | 2 | 08/20/2024 | 08/20/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | WESTMINSTER | 280942 | 01473 | 3.8 |  |  | Solar |  | 05_05_115W52 | 03/02/2020 | 03/11/2020 | 7 | 3 | 4 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2020 | 03/02/2020 | 2/26/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2020 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | FALL RIVER | 586866 | 02721 | 7.6 |  |  | Solar |  | 05_12_24W1 | 03/08/2024 | 03/11/2024 | 1 | 0 | 1 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/08/2024 | 4/24/2025 | Y | EXP | 365 | 05/11/2024 | 07/06/2024 | 57 | 0 | 57 |  |  | 7/13/2024 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | LYNN | 711434 | 01904 | 11.5 |  |  | Solar |  | 05_12_51T1 | 08/12/2025 | 08/15/2025 | 3 | 0 | 3 | 08/18/2025 | 08/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | ESSEX | 258094 | 01929 | 3.8 |  |  | Solar |  | 05_14_36L1 | 10/10/2019 | 10/21/2019 | 5 | 0 | 5 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 10/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | NEWBURY | 263958 | 01950 | 0 |  |  | Solar |  | 05_14_58L3 | 11/05/2019 | 11/05/2019 | 0 | 0 | 0 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N | Beverly |  |  | Closed
National Grid | WESTFORD | 208621 | 01886 | 900 |  |  | Solar |  | 05_14_74L1 | 03/27/2019 | 04/20/2019 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2019 | 05/17/2019 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | Closed - Completion Documents Hold
National Grid | METHUEN | 418712 | 01844 | 6 |  |  | Solar |  | 05_14_9J1 | 07/26/2022 | 07/28/2022 | 2 | 0 | 2 | 07/29/2022 | 07/29/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/26/2022 | 5/10/2024 | Y | EXP | 365 | 02/22/2023 | 05/10/2023 | 78 | 0 | 78 |  |  | 5/23/2023 | Connected |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | CHELMSFORD | 518028 | 01824 | 6 |  |  | Solar |  | 05_01_26W1 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed - Design Hold
National Grid | AUBURN | 685553 | 01501 | 11.4 |  |  | Solar |  | 05_01_412L4 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension - Completion Documents Hold
National Grid | DUDLEY | 644276 | 01571 | 5.76 |  |  | Solar |  | 05_01_602W2 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | GARDNER | 301536 | 01440 | 3.8 |  |  | Solar |  | 05_05_115W52 | 07/16/2020 | 07/22/2020 | 3 | 0 | 3 | 07/23/2020 | 07/23/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro |  |  | Closed
National Grid | WESTPORT | 592974 | 02790 | 10.73 |  |  | Solar |  | 05_12_24W1 | 03/06/2024 | 03/21/2024 | 12 | 8 | 4 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | LYNN | 713829 | 01904 | 17.6 |  |  | Solar |  | 05_12_51T1 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N | Billerica |  |  | Closed
National Grid | MANCHESTER | 432857 | 01944 | 0 |  |  | Solar |  | 05_14_36L1 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 7/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N | Billerica |  |  | Closed
National Grid | NEWBURY | 353145 | 01950 | 5.8 |  |  | Solar |  | 05_14_58L3 | 04/16/2021 | 05/10/2021 | 15 | 13 | 2 | 05/11/2021 | 05/11/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTFORD | 208566 | 01886 | 3.8 |  |  | Solar |  | 05_14_74L1 | 02/18/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed
National Grid | METHUEN | 432583 | 01844 | 15.2 |  |  | Solar |  | 05_14_9J1 | 05/23/2022 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Scituate |  |  | Closed
National Grid | CHELMSFORD | 523508 | 01824 | 3 |  |  | Solar |  | 05_01_26W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/05/2023 | 6/21/2024 | Y | EXP | 365 | 08/19/2023 | 09/29/2023 | 42 | 0 | 42 |  |  | 10/10/2023 | Connected |  | N | Somerset |  |  | Closed
National Grid | AUBURN | 693374 | 01501 | 12.54 |  |  | Solar |  | 05_01_412L4 | 05/28/2025 |  | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann |  |  | Closed - Start Study
National Grid | DUDLEY | 656989 | 01571 | 7.6 |  |  | Solar |  | 05_01_602W2 | 11/26/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | GARDNER | 320315 | 01440 | 15.6 |  |  | Solar |  | 05_05_115W52 | 10/20/2020 | 01/27/2021 | 66 | 59 | 7 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 10/20/2020 | 7/16/2022 | Y | EXP | 365 | 04/03/2021 | 05/17/2021 | 44 | 0 | 44 |  |  | 10/26/2021 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WESTPORT | 606154 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 04/23/2024 | 05/07/2024 | 3 | 0 | 3 | 05/08/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | Y | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | LYNN | 732153 | 01904 | 23 |  |  | Solar |  | 05_12_51T1 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | BEVERLY | 438236 | 01915 | 15.2 |  |  | Solar |  | 05_14_36L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2022 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | NEWBURY | 369368 | 01950 | 7.6 |  |  | Solar |  | 05_14_58L3 | 07/13/2021 | 08/24/2021 | 30 | 26 | 4 | 08/25/2021 | 08/25/2021 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2022 | Connected |  | N | Fall River-North |  |  | Closed
National Grid | WESTFORD | 277815 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 03/03/2020 | 03/09/2020 | 3 | 0 | 3 | 03/10/2020 | 03/10/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2020 | 03/03/2020 |  | Y | EXP | 365 | 02/06/2021 | 02/12/2021 | 6 | 0 | 6 |  |  | 4/27/2021 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | METHUEN | 437921 | 01844 | 15.2 |  |  | Solar |  | 05_14_9J1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | CHELMSFORD | 568871 | 01824 | 10 |  |  | Solar |  | 05_01_26W1 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | AUBURN | 697368 | 01501 | 15.58 |  |  | Solar |  | 05_01_412L4 | 06/10/2025 | 06/24/2025 | 9 | 6 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | DUDLEY | 664441 | 01571 | 0 |  |  | Solar |  | 05_01_602W2 | 01/08/2025 | 02/17/2025 | 7 | 2 | 5 | 02/18/2025 | 02/18/2025 | 15 | 0 | 15 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | HUBBARDSTON | 450178 | 01452 | 10 |  |  | Solar |  | 05_05_115W52 | 08/26/2022 | 09/22/2022 | 18 | 15 | 3 | 09/23/2022 | 09/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 08/26/2022 | 2/8/2024 | Y | EXP | 365 | 01/07/2023 | 02/07/2023 | 32 | 0 | 32 |  |  | 3/23/2023 | Connected |  | N | Billerica |  |  | Closed
National Grid | WESTPORT | 610904 | 02790 | 10 |  |  | Solar |  | 05_12_24W1 | 05/14/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/14/2024 | 8/7/2025 | Y | EXP | 365 | 09/27/2024 | 01/09/2025 | 105 | 0 | 105 |  |  | 1/14/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | LYNN | 445040 | 01904 | 250 |  |  | Solar |  | 05_12_51T2 | 08/08/2022 | 08/31/2022 | 17 | 7 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y | Amesbury Newburyport |  |  | Closed
National Grid | HAMILTON | 463499 | 01982 | 15.2 |  |  | Solar |  | 05_14_36L1 | 09/27/2022 | 10/04/2022 | 6 | 5 | 1 | 10/05/2022 | 10/05/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 |  | 1/10/2024 | N | EXP | 430 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | 160 Day Study
National Grid | NEWBURY | 401888 | 01950 | 15.2 |  |  | Solar |  | 05_14_58L3 | 12/17/2021 | 12/23/2021 | 5 | 3 | 2 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | WESTFORD | 283578 | 01886 | 9.57 |  |  | Solar |  | 05_14_74L1 | 06/17/2020 | 06/19/2020 | 1 | 0 | 1 | 06/22/2020 | 06/22/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/17/2020 | 6/17/2021 | Y | EXP | 365 | 02/10/2021 | 04/09/2021 | 58 | 0 | 58 |  |  | 4/13/2021 | Connected |  | N | Beverly |  |  | Closed
National Grid | METHUEN | 176716 | 01844 | 10 |  |  | Solar |  | 05_14_9J3 | 01/11/2016 | 01/11/2016 | 1 | 1 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/17/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/7/2016 | 3/7/2016 | 8/11/2016 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | CHELMSFORD | 569888 | 01824 | 10 |  |  | Solar |  | 05_01_26W1 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/20/2023 | 1/25/2025 | Y | EXP | 365 | 03/16/2024 | 06/18/2024 | 95 | 0 | 95 |  |  | 7/1/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | AUBURN | 725829 | 01501 | 7.6 |  |  | Solar |  | 05_01_412L4 | 10/10/2025 | 10/24/2025 | 8 | 2 | 6 | 10/27/2025 | 10/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | DUDLEY | 666513 | 01571 | 23 |  |  | Solar |  | 05_01_602W2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WESTMINSTER | 380699 | 01473 | 480 |  |  | Solar |  | 05_05_115W52 | 10/29/2021 | 12/15/2021 | 30 | 20 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | FALL RIVER | 615444 | 02723 | 10.15 |  |  | Solar |  | 05_12_24W1 | 06/04/2024 | 06/14/2024 | 5 | 4 | 1 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N | MPL-Northwest |  |  | Study Complete
National Grid | LYNN | 515409 | 01904 | 34.6 |  |  | Solar |  | 05_12_51T2 | 05/24/2023 | 07/14/2023 | 34 | 24 | 10 | 07/17/2023 | 07/17/2023 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 | 05/24/2023 | 4/29/2026 | Y | EXP | 220 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y | Scituate |  |  | Closed
National Grid | HAMILTON | 555470 | 01982 | 7.54 |  |  | Solar |  | 05_14_36L1 | 09/14/2023 | 09/18/2023 | 3 | 1 | 2 | 09/19/2023 | 09/19/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 10/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed - Initial Review
National Grid | NEWBURY | 401105 | 01950 | 0 |  |  | Other |  | 05_14_58L3 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 02/10/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East |  |  | Scoping Meeting
National Grid | WESTFORD | 321316 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater |  |  | 160 Day Study
National Grid | METHUEN | 178384 | 01844 | 3.8 |  |  | Solar |  | 05_14_9J3 | 01/15/2018 | 01/15/2018 | 32 | 3 | 29 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 1/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | CHELMSFORD | 581921 | 01824 | 6.38 |  |  | Solar |  | 05_01_26W1 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | AUBURN | 704897 | 01501 | 15.2 |  |  | Solar |  | 05_01_412L5 | 07/15/2025 | 08/07/2025 | 17 | 12 | 5 | 08/08/2025 | 08/08/2025 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | DUDLEY | 692073 | 01571 | 10 |  |  | Solar |  | 05_01_602W2 | 06/02/2025 | 06/16/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed - Internal Review
National Grid | GARDNER | 454988 | 01440 | 6.96 |  |  | Solar |  | 05_05_115W52 | 11/16/2022 | 01/03/2023 | 29 | 25 | 4 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 | 11/16/2022 | 6/25/2024 | Y | EXP | 365 | 03/29/2023 | 05/03/2023 | 36 | 0 | 36 |  |  | 7/20/2023 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | WESTPORT | 625257 | 02790 | 5 |  |  | Solar |  | 05_12_24W1 | 07/18/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | LYNN | 653313 | 01904 | 240 |  |  | Solar |  | 05_12_51T2 | 11/13/2024 | 12/10/2024 | 18 | 8 | 10 |  |  | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Leominster |  |  | 160 Day Study
National Grid | WENHAM | 578652 | 01984 | 11.4 |  |  | Solar |  | 05_14_36L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/27/2023 | 2/27/2025 | Y | EXP | 365 | 03/16/2024 | 04/10/2024 | 26 | 0 | 26 |  |  | 4/16/2024 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | NEWBURY | 402235 | 01950 | 0 |  |  | Solar |  | 05_14_58L3 | 12/20/2021 | 12/21/2021 | 1 | 0 | 1 | 12/22/2021 | 12/22/2021 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 | 12/20/2021 | 4/11/2023 | Y | EXP | 365 | 03/09/2022 | 04/11/2022 | 34 | 0 | 34 |  |  | 5/12/2022 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | WESTFORD | 323842 | 01886 | 9.8 |  |  | Solar |  | 05_14_74L1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest |  |  | Closed
National Grid | METHUEN | 249645 | 01844 | 3.8 |  |  | Solar |  | 05_14_9J3 | 08/30/2019 | 09/04/2019 | 1 | 0 | 1 | 09/05/2019 | 09/05/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 08/30/2019 | 10/13/2021 | Y | EXP | 365 | 08/04/2020 | 08/21/2020 | 17 | 0 | 17 |  |  | 11/18/2020 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | CHELMSFORD | 599053 | 01824 | 15.2 |  |  | Solar |  | 05_01_26W1 | 04/18/2024 | 06/21/2024 | 45 | 43 | 2 | 06/24/2024 | 06/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 04/18/2024 | 7/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-Northwest |  |  | Closed
National Grid | AUBURN | 731941 | 01501 | 13.36 |  |  | Solar |  | 05_01_412L5 | 11/06/2025 | 11/24/2025 | 11 | 8 | 3 | 11/25/2025 | 11/25/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 693699 | 01571 | 3.8 |  |  | Solar |  | 05_01_602W2 | 05/27/2025 | 07/03/2025 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | HUBBARDSTON | 465035 | 01452 | 4.06 |  |  | Solar |  | 05_05_115W52 | 09/30/2022 | 10/20/2022 | 13 | 12 | 1 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2023 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTPORT | 630212 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 08/05/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | LYNN | 714498 | 01904 | 20 |  |  | Solar |  | 05_12_51T2 | 08/25/2025 | 09/03/2025 | 6 | 1 | 5 | 09/04/2025 | 09/04/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/25/2025 | 11/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Fall River-North |  |  | Closed - Completion Documents Hold
National Grid | HAMILTON | 628681 | 01982 | 19 |  |  | Solar |  | 05_14_36L1 | 07/30/2024 | 08/01/2024 | 2 | 0 | 2 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N | Amesbury Newburyport |  |  | Closed
National Grid | NEWBURY | 427118 | 01950 | 15.2 |  |  | Solar |  | 05_14_58L3 | 04/28/2022 | 06/09/2022 | 29 | 29 | 0 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 04/28/2022 | 1/30/2024 | Y | EXP | 365 | 01/07/2023 | 01/30/2023 | 24 | 0 | 24 |  |  | 4/27/2023 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WESTFORD | 334306 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 01/13/2021 | 01/29/2021 | 11 | 11 | 0 | 02/01/2021 | 02/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 | 01/13/2021 | 9/29/2022 | Y | EXP | 365 | 09/11/2021 | 09/24/2021 | 14 | 0 | 14 |  |  | 3/3/2022 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | METHUEN | 393377 | 01844 | 9.772 |  |  | Solar |  | 05_14_9J3 | 11/04/2021 | 11/16/2021 | 8 | 5 | 3 | 11/17/2021 | 11/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y | Webster-Southbridge-Charlton |  |  | Closed
National Grid | CHELMSFORD | 664182 | 01824 | 3.8 |  |  | Solar |  | 05_01_26W1 | 01/07/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | AUBURN | 739666 | 01501 | 15.2 |  |  | Solar |  | 05_01_412L5 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Millbury-Grafton |  |  | Closed
National Grid | DUDLEY | 318674 | 01571 | 0 |  |  | Other |  | 05_01_602W3 | 04/06/2021 | 04/30/2021 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | WESTMINSTER | 473743 | 01473 | 10 |  |  | Solar |  | 05_05_115W52 | 12/20/2022 | 12/27/2022 | 4 | 2 | 2 | 12/28/2022 | 12/28/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 | 12/20/2022 | 4/6/2024 | Y | EXP | 365 | 04/22/2023 | 05/25/2023 | 34 | 0 | 34 |  |  | 6/1/2023 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | WESTPORT | 645964 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W1 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/7/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/28/2025 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | LYNN | 724733 | 01904 | 0 |  |  | Solar |  | 05_12_51T2 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Methuen/Haverhill |  |  | Closed
National Grid | HAMILTON | 629011 | 01982 | 23 |  |  | Solar |  | 05_14_36L1 | 07/31/2024 | 08/05/2024 | 6 | 5 | 1 | 09/27/2024 | 09/27/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/31/2024 | 11/21/2025 | Y | EXP | 365 | 01/11/2025 | 02/24/2025 | 45 | 0 | 45 |  |  | 3/5/2025 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Payment Processed
National Grid | NEWBURY | 534351 | 01950 | 15.2 |  |  | Solar |  | 05_14_58L3 | 06/15/2023 | 06/27/2023 | 7 | 5 | 2 | 06/28/2023 | 06/28/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | WESTFORD | 338817 | 01886 | 937.5 |  |  | Solar |  | 05_14_74L1 | 05/17/2021 | 08/04/2021 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2021 | 09/08/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Scituate |  |  | Closed
National Grid | METHUEN | 719817 | 01844 | 3.8 |  |  | Solar |  | 05_12_5C3 | 09/17/2025 | 11/04/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Fall River-North |  |  | Closed
National Grid | MALDEN | 696569 | 02148 | 15.96 |  |  | Solar |  | 05_01_26W1 | 06/05/2025 | 06/09/2025 | 2 | 0 | 2 | 06/10/2025 | 06/10/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension - Construction Hold
National Grid | AUBURN | 176210 | 01501 | 5 |  |  | Solar |  | 05_01_412L5 | 04/27/2015 | 04/27/2015 | 0 | 0 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2015 |  | 9/30/2015 | N | EXP | 153 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 3/29/2016 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 656529 | 01571 | 8.36 |  |  | Solar |  | 05_01_602W3 | 11/24/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/24/2024 | 3/26/2026 | Y | EXP | 365 | 06/11/2025 |  | 205 | 0 | 205 |  |  |  | Completion Documents |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | WESTMINSTER | 523454 | 01473 | 10 |  |  | Solar |  | 05_05_115W52 | 06/05/2023 | 06/12/2023 | 5 | 4 | 1 | 06/13/2023 | 06/13/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 06/05/2023 | 7/16/2024 | Y | EXP | 365 | 08/16/2023 | 10/11/2023 | 57 | 0 | 57 |  |  | 10/16/2023 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | WESTPORT | 660596 | 02790 | 2.03 |  |  | Solar |  | 05_12_24W1 | 12/13/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | LYNN | 729870 | 01904 | 9.28 |  |  | Solar |  | 05_12_51T2 | 11/02/2025 | 11/18/2025 | 10 | 5 | 5 | 11/19/2025 | 11/19/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Scituate |  |  | Closed
National Grid | ESSEX | 656931 | 01929 | 0 |  |  | Battery Add-On |  | 05_14_36L1 | 11/26/2024 | 12/23/2024 | 6 | 1 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | NEWBURY | 554429 | 01950 | 0 |  |  | Battery Add-On |  | 05_14_58L3 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed
National Grid | WESTFORD | 340566 | 01886 | 6 |  |  | Solar |  | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | 160 Day Study
National Grid | METHUEN | 176869 | 01844 | 10 |  |  | Solar |  | 05_12_5C3 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/7/2017 | N | EXP | 323 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y | Walpole/Foxboro |  |  | Closed - Design Hold
National Grid | MALDEN | 710851 | 02148 | 5.76 |  |  | Solar |  | 05_01_26W1 | 08/08/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N | Walpole/Foxboro |  |  | Closed - Construction Hold
National Grid | AUBURN | 177367 | 01501 | 528 |  |  | Solar |  | 05_01_412L5 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2016 | 08/23/2016 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/3/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater |  |  | 160 Day Study
National Grid | WEBSTER | 661234 | 01570 | 5000 |  |  | Solar |  | 05_01_602W3 | 04/28/2025 | 11/21/2025 | 142 | 132 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 01/06/2026 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Somerset |  |  | Closed
National Grid | WESTMINSTER | 560606 | 01473 | 15.08 |  |  | Solar |  | 05_05_115W52 | 10/05/2023 | 10/09/2023 | 2 | 0 | 2 | 10/10/2023 | 10/10/2023 | 63 | 41 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 3/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N | Somerset |  |  | Closed
National Grid | WESTPORT | 668006 | 02790 | 5.76 |  |  | Solar |  | 05_12_24W1 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/27/2025 | 4/11/2026 | Y | EXP | 365 | 07/03/2025 | 07/02/2025 | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N | Somerset |  |  | Closed
National Grid | LYNN | 169987 | 01904 | 10 |  |  | Solar |  | 05_12_51T2 | 07/09/2018 | 07/24/2018 | 11 | 8 | 3 | 07/25/2018 | 07/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 07/09/2018 | 10/1/2019 | Y | EXP | 432 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N | Somerset |  |  | Closed
National Grid | ESSEX | 659827 | 01929 | 3.8 |  |  | Solar |  | 05_14_36L1 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Closed
National Grid | NEWBURY | 650740 | 01950 | 8.376 |  |  | Solar |  | 05_14_58L3 | 10/30/2024 | 12/02/2024 | 10 | 5 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 10/30/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N | Dracut |  |  | Closed
National Grid | WESTFORD | 346362 | 01886 | 7.6 |  |  | Solar |  | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/26/2021 | 10/19/2022 | Y | EXP | 365 | 09/29/2021 | 10/29/2021 | 31 | 4 | 27 |  |  | 11/30/2021 | Connected |  | Y | Dracut |  |  | Closed
National Grid | METHUEN | 177760 | 01844 | 468 |  |  | Solar |  | 05_12_5C3 | 08/02/2017 | 08/02/2017 | 95 | 95 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2017 | 01/25/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Beverly |  |  | Closed - Completion Documents Hold
National Grid | MALDEN | 587625 | 02148 | 200 |  |  | Solar |  | 05_01_26W2 | 03/14/2024 | 07/10/2025 | 328 | 322 | 6 |  |  | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y | Brockton-North |  |  | Time Frame Suspension
National Grid | AUBURN | 178735 | 01501 | 3.8 |  |  | Solar |  | 05_01_412L5 | 02/12/2018 | 03/15/2018 | 12 | 0 | 12 | 03/15/2018 | 03/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 | 02/12/2018 | 11/21/2019 | Y | EXP | 615 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | WEBSTER | 725531 | 01570 | 62.7 |  |  | Solar |  | 05_01_602W3 | 10/22/2025 | 12/30/2025 | 46 | 36 | 10 | 12/31/2025 | 12/31/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Fall River-North |  |  | Closed
National Grid | WESTMINSTER | 583847 | 01473 | 480 |  |  | Solar |  | 05_05_115W52 | 02/22/2024 | 05/22/2024 | 63 | 53 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | FALL RIVER | 679840 | 02723 | 3.8 |  |  | Solar |  | 05_12_24W1 | 04/10/2025 | 06/06/2025 | 12 | 9 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | LYNN | 174123 | 01904 | 128.25 |  |  | Solar |  | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Closed
National Grid | HAMILTON | 665116 | 01982 | 10 |  |  | Solar |  | 05_14_36L1 | 01/10/2025 | 01/14/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | NEWBURY | 657428 | 01950 | 7.6 |  |  | Solar |  | 05_14_58L3 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N | Scituate |  |  | Closed
National Grid | WESTFORD | 364103 | 01886 | 4.08 |  |  | Solar |  | 05_14_74L1 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | METHUEN | 563209 | 01844 | 10 |  |  | Solar |  | 05_12_5C3 | 12/06/2023 | 03/07/2024 | 52 | 50 | 2 | 03/08/2024 | 03/08/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 5/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | MALDEN | 641473 | 02148 | 125 |  |  | Solar |  | 05_01_26W2 | 09/19/2024 | 10/29/2024 | 27 | 18 | 9 | 10/30/2024 | 10/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 3/9/2026 | N | EXP | 120 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster |  |  | Closed
National Grid | AUBURN | 187735 | 01501 | 466.6 |  |  | Solar |  | 05_01_412L5 | 06/28/2018 | 06/28/2018 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2018 | 08/14/2018 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 731396 | 01571 | 9.5 |  |  | Solar |  | 05_01_602W3 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Ayer-Clinton |  |  | Closed - Awaiting Payment
National Grid | WESTMINSTER | 598026 | 01473 | 2.9 |  |  | Solar |  | 05_05_115W52 | 04/11/2024 | 05/01/2024 | 13 | 10 | 3 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/11/2024 | 5/20/2025 | Y | EXP | 365 | 07/03/2024 | 08/08/2024 | 37 | 0 | 37 |  |  | 9/28/2024 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | FALL RIVER | 684334 | 02721 | 10 |  |  | Solar |  | 05_12_24W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/10/2025 | 6/12/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 11/27/2025 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | LYNN | 174122 | 01904 | 250 |  |  | Solar |  | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Walpole/Foxboro |  |  | Closed - Design Hold
National Grid | HAMILTON | 667873 | 01982 | 10.15 |  |  | Solar |  | 05_14_36L1 | 01/26/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N | Somerset |  |  | Closed - Construction Hold
National Grid | NEWBURY | 663371 | 01950 | 17.6 |  |  | Solar |  | 05_14_58L3 | 01/02/2025 | 01/06/2025 | 3 | 1 | 2 | 01/07/2025 | 01/07/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 01/02/2025 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | WESTFORD | 395653 | 01886 | 6 |  |  | Solar |  | 05_14_74L1 | 12/06/2021 | 01/07/2022 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 12/06/2021 | 6/28/2023 | Y | EXP | 365 | 05/24/2022 | 06/28/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | METHUEN | 683574 | 01844 | 16.53 |  |  | Solar |  | 05_12_5C3 | 04/08/2025 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | MALDEN | 649613 | 02148 | 200 |  |  | Solar |  | 05_01_26W2 | 05/06/2025 | 07/25/2025 | 55 | 45 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | AUBURN | 201618 | 01501 | 10 |  |  | Solar |  | 05_01_412L5 | 11/19/2018 | 01/03/2019 | 3 | 0 | 3 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 11/19/2018 | 1/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2021 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | WEBSTER | 739400 | 01570 | 7.6 |  |  | Solar |  | 05_01_602W3 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | WESTMINSTER | 601783 | 01473 | 0 |  |  | Solar |  | 05_05_115W52 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | WESTPORT | 703102 | 02790 | 15.2 |  |  | Solar |  | 05_12_24W1 | 07/07/2025 | 07/11/2025 | 38 | 38 | 0 | 08/29/2025 | 08/29/2025 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | Time Frame Suspension - Completion Documents Hold
National Grid | LYNN | 174411 | 01904 | 14 |  |  | Solar |  | 05_12_51T2 | 06/22/2012 | 06/22/2012 | 10 | 0 | 10 | 07/09/2012 | 07/09/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 9/6/2012 | N | EXP | -96 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/11/2012 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | WENHAM | 669838 | 01984 | 6.84 |  |  | Solar |  | 05_14_36L1 | 02/04/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N | Cape Ann |  |  | Closed
National Grid | NEWBURY | 551107 | 01950 | 240 |  |  | Solar |  | 05_14_59L1 | 01/05/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2024 | 02/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y | Bridgewater |  |  | 160 Day Study
National Grid | ANDOVER | 409865 | 01810 | 6.67 |  |  | Solar |  | 05_14_74L1 | 03/24/2022 | 04/06/2022 | 10 | 9 | 1 | 04/07/2022 | 04/07/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/24/2022 | 7/8/2023 | Y | EXP | 365 | 06/08/2022 | 06/28/2022 | 21 | 0 | 21 |  |  | 8/1/2022 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | METHUEN | 730479 | 01844 | 3.8 |  |  | Solar |  | 05_12_67J1 | 10/30/2025 | 11/05/2025 | 4 | 0 | 4 | 11/06/2025 | 11/06/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | MEDFORD | 742221 | 02155 | 15.76 |  |  | Solar |  | 05_01_26W2 | 12/25/2025 | 12/31/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Fall River-South |  |  | Closed
National Grid | AUBURN | 203677 | 01501 | 9.57 |  |  | Solar |  | 05_01_412L5 | 12/31/2018 | 01/11/2019 | 7 | 1 | 6 | 01/18/2019 | 01/18/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  | 2/12/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2019 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | DUDLEY | 174307 | 01571 | 500 |  |  | Solar |  | 05_01_602W3 | 01/10/2012 | 01/10/2012 | 23 | 0 | 23 | 02/13/2012 | 02/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2012 |  | 7/1/2012 | N | EXP | -8 |  |  | 0 | 0 | 0 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N | Billerica |  |  | Closed
National Grid | WESTMINSTER | 603266 | 01473 | 4.06 |  |  | Solar |  | 05_05_115W52 | 04/11/2024 | 05/10/2024 | 8 | 3 | 5 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N | North Andover |  |  | Closed
National Grid | FALL RIVER | 741965 | 02721 | 15.2 |  |  | Solar |  | 05_12_24W2 | 12/23/2025 | 12/24/2025 | 1 | 0 | 1 | 12/26/2025 | 12/26/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Scituate |  |  | Closed
National Grid | LYNN | 175123 | 01904 | 18 |  |  | Solar |  | 05_12_51T2 | 08/16/2012 | 08/16/2012 | 5 | 0 | 5 | 08/24/2012 | 08/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/16/2012 | 11/30/2012 | Y | EXP | -12 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 4/2/2013 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | ESSEX | 710902 | 01929 | 15.2 |  |  | Solar |  | 05_14_36L1 | 08/10/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | NEWBURY | 174889 | 01950 | 20 |  |  | Solar |  | 05_14_59L1 | 08/13/2013 | 08/13/2013 | 7 | 0 | 7 | 08/23/2013 | 08/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2013 |  | 9/25/2013 | N | EXP | 9 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 2/10/2014 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | ANDOVER | 474114 | 01810 | 10 |  |  | Solar |  | 05_14_74L1 | 12/20/2022 | 12/21/2022 | 1 | 0 | 1 | 12/22/2022 | 12/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/20/2022 | 4/19/2024 | Y | EXP | 365 | 03/14/2023 | 04/19/2023 | 37 | 0 | 37 |  |  | 5/15/2023 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | METHUEN | 331978 | 01844 | 7.6 |  |  | Solar |  | 05_12_67J1 | 12/16/2020 | 01/08/2021 | 15 | 12 | 3 | 01/11/2021 | 01/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | MEDFORD | 174587 | 02155 | 22.8 |  |  | Solar |  | 05_01_26W2 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 6/28/2012 | N | EXP | 227 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 6/28/2012 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | AUBURN | 208138 | 01501 | 10 |  |  | Solar |  | 05_01_412L5 | 02/19/2019 | 02/19/2019 | 0 | 0 | 0 | 02/20/2019 | 02/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/19/2019 | 11/5/2019 | Y | EXP | 257 | 09/17/2019 | 09/18/2019 | 1 | 0 | 1 |  |  | 9/23/2019 | Connected |  | N | Attleboro |  |  | Closed
National Grid | DUDLEY | 175778 | 01571 | 480 |  |  | Solar |  | 05_01_602W3 | 08/20/2014 | 08/20/2014 | 7 | 0 | 7 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 | 10/21/2014 | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/31/2014 | 08/20/2014 | 9/1/2015 | Y | EXP | 244 | 09/18/2015 | 11/03/2015 | 31 | 0 | 31 | 10/23/2015 | 10/23/2015 | 11/16/2015 | Connected |  | N | Attleboro |  |  | Closed
National Grid | WESTMINSTER | 647197 | 01473 | 7.6 |  |  | Solar |  | 05_05_115W52 | 10/17/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 12/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | FALL RIVER | 176935 | 02720 | 6 |  |  | Solar |  | 05_12_24W2 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 01/29/2016 | 2/6/2017 | Y | EXP | 336 |  |  | 0 | 0 | 0 | 9/19/2016 | 9/19/2016 | 9/19/2016 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Completion Documents Hold
National Grid | LYNN | 175750 | 01904 | 17.2 |  |  | Solar |  | 05_12_51T2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2014 |  | 3/31/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 1/12/2015 | 1/12/2015 | 9/17/2015 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | HAMILTON | 549712 | 01982 | 4998 |  |  | Other |  | 05_14_36L2 | 10/25/2023 | 11/16/2023 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 02/16/2024 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | NEWBURY | 174979 | 01950 | 950 |  |  | Solar |  | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | -12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | TEWKSBURY | 492624 | 01876 | 17.45 |  |  | Solar |  | 05_14_74L1 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/16/2023 | 6/14/2024 | Y | EXP | 470 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | Time Frame Suspension - Awaiting Payment
National Grid | METHUEN | 331636 | 01844 | 10 |  |  | Solar |  | 05_12_67J1 | 01/08/2021 | 01/12/2021 | 2 | 2 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/08/2021 | 1/11/2022 | Y | EXP | 365 | 03/25/2021 | 06/24/2021 | 91 | 0 | 91 |  |  | 6/30/2021 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | MEDFORD | 175624 | 02155 | 684 |  |  | Solar |  | 05_01_26W2 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 10/2/2014 | 05/05/2014 | 12/31/2015 | Y | EXP | 455 | 08/25/2015 | 11/23/2015 | 61 | 0 | 61 | 11/18/2015 | 11/18/2015 | 12/16/2015 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | MILLBURY | 207488 | 01527 | 10 |  |  | Solar |  | 05_01_412L5 | 01/30/2019 | 02/04/2019 | 3 | 3 | 0 | 02/05/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 01/30/2019 | 11/25/2019 | Y | EXP | 292 | 05/25/2019 | 07/12/2019 | 48 | 0 | 48 |  |  | 9/10/2019 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | DUDLEY | 176816 | 01571 | 2200 |  |  | Solar |  | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | WESTMINSTER | 677831 | 01473 | 5.76 |  |  | Solar |  | 05_05_115W52 | 03/13/2025 | 03/25/2025 | 8 | 4 | 4 | 03/26/2025 | 03/26/2025 | 56 | 38 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 03/13/2025 | 6/30/2026 | Y | EXP | 365 | 08/23/2025 | 10/01/2025 | 40 | 0 | 40 |  |  | 10/13/2025 | Connected |  | N | Billerica |  |  | Closed
National Grid | WESTPORT | 195033 | 02790 | 22.8 |  |  | Solar |  | 05_12_24W2 | 09/04/2018 | 10/17/2018 | 10 | 10 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Worcester North/South |  |  | Closed
National Grid | LYNN | 175937 | 01904 | 750 |  |  | Solar |  | 05_12_51T2 | 01/20/2015 | 01/20/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2015 | 02/25/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Closed
National Grid | GLOUCESTER | 701387 | 01930 | 17.6 |  |  | Solar |  | 05_14_36L2 | 07/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro |  |  | Closed - Construction Hold
National Grid | NEWBURY | 174978 | 01950 | 950 |  |  | Solar |  | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | -12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N | Northampton |  |  | Closed
National Grid | TEWKSBURY | 515458 | 01876 | 12.6 |  |  | Solar |  | 05_14_74L1 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 04/24/2023 | 11/5/2024 | Y | EXP | 365 | 09/12/2023 | 10/24/2023 | 43 | 0 | 43 |  |  | 11/18/2023 | Connected |  | N | Northampton |  |  | Closed - Design Hold
National Grid | METHUEN | 502077 | 01844 | 15.744 |  |  | Solar |  | 05_12_67J1 | 03/06/2023 | 03/14/2023 | 6 | 5 | 1 | 03/15/2023 | 03/15/2023 | 30 | 5 | 25 | 05/12/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 6/22/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N | Northampton |  |  | Closed
National Grid | MEDFORD | 175849 | 02155 | 1000 |  |  | Solar |  | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 02/10/2017 | 06/30/2016 | 0 | 0 | 0 | 8/3/2016 |  | 9/30/2017 | N | STD | 423 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | MILLBURY | 315053 | 01527 | 50 |  |  | Solar |  | 05_01_412L5 | 09/25/2020 | 10/06/2020 | 6 | 1 | 5 | 10/07/2020 | 10/07/2020 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 176815 | 01570 | 2200 |  |  | Solar |  | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WESTMINSTER | 680103 | 01473 | 7.6 |  |  | Solar |  | 05_05_115W52 | 03/24/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 251755 | 02721 | 10 |  |  | Solar |  | 05_12_24W2 | 10/17/2019 | 10/21/2019 | 1 | 0 | 1 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/17/2019 | 10/17/2020 | Y | EXP | 365 | 02/25/2020 | 04/13/2020 | 48 | 0 | 48 |  |  | 4/29/2020 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | LYNN | 176160 | 01904 | 17.4 |  |  | Solar |  | 05_12_51T2 | 02/05/2015 | 02/05/2015 | 4 | 1 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 6/30/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 3/6/2015 | 3/6/2015 | 9/25/2015 | Connected |  | N | Ayer-Clinton |  |  | Closed - Awaiting Payment
National Grid | BEVERLY | 704769 | 01915 | 210 |  |  | Solar |  | 05_14_36L2 | 07/14/2025 | 08/07/2025 | 18 | 8 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | NEWBURY | 175015 | 01950 | 950 |  |  | Solar |  | 05_14_59L1 | 08/29/2011 | 08/29/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2011 | 11/03/2011 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/29/2011 | 11/30/2012 | Y | STD | -12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | ANDOVER | 558385 | 01810 | 990 |  |  | Solar |  | 05_14_74L1 | 12/04/2023 |  | 181 | 172 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | Closed
National Grid | METHUEN | 555081 | 01844 | 10 |  |  | Solar |  | 05_12_67J1 | 09/15/2023 | 09/19/2023 | 3 | 2 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 | 09/15/2023 | 10/26/2024 | Y | EXP | 365 | 02/16/2024 | 05/21/2024 | 96 | 0 | 96 |  |  | 8/3/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | MEDFORD | 177238 | 02155 | 186.6 |  |  | Solar |  | 05_01_26W2 | 02/03/2017 | 02/03/2017 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | Closed - Initial Review
National Grid | AUBURN | 329818 | 01501 | 15.2 |  |  | Solar |  | 05_01_412L5 | 12/05/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 4/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2022 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed - Initial Review
National Grid | DUDLEY | 176813 | 01571 | 2000 |  |  | Solar |  | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/07/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | WESTMINSTER | 694610 | 01473 | 15.96 |  |  | Solar |  | 05_05_115W52 | 06/23/2025 | 07/28/2025 | 23 | 22 | 1 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | WESTPORT | 309907 | 02790 | 7.6 |  |  | Solar |  | 05_12_24W2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | LYNN | 177044 | 01904 | 630 |  |  | Solar |  | 05_12_51T2 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Closed
National Grid | HAMILTON | 729925 | 01982 | 34.6 |  |  | Solar |  | 05_14_36L2 | 11/06/2025 | 11/20/2025 | 9 | 7 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster |  |  | 160 Day Study
National Grid | NEWBURY | 175240 | 01950 | 15.2 |  |  | Solar |  | 05_14_59L1 | 08/21/2014 | 08/21/2014 | 7 | 0 | 7 | 09/03/2014 | 09/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 12/8/2014 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | ANDOVER | 628731 | 01810 | 11.5 |  |  | Solar |  | 05_12_67J1 | 07/30/2024 | 09/20/2024 | 49 | 44 | 5 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | METHUEN | 177496 | 01844 | 15.2 |  |  | Solar |  | 05_01_26W2 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2016 |  | 12/19/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | MALDEN | 332213 | 02148 | 7.6 |  |  | Solar |  | 05_01_412L5 | 01/12/2021 | 01/15/2021 | 2 | 0 | 2 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/12/2021 | 3/8/2022 | Y | EXP | 365 | 09/23/2021 | 01/19/2022 | 119 | 4 | 115 |  |  | 2/5/2022 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | AUBURN | 176848 | 01501 | 480 |  |  | Solar |  | 05_01_602W3 | 11/09/2015 | 11/09/2015 | 1 | 1 | 0 | 11/10/2015 | 11/10/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Billerica |  |  | Closed
National Grid | WEBSTER | 700073 | 01570 | 17.6 |  |  | Solar |  | 05_05_115W52 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | WESTMINSTER | 362370 | 01473 | 10 |  |  | Solar |  | 05_12_24W2 | 06/09/2021 | 06/15/2021 | 4 | 3 | 1 | 06/16/2021 | 06/16/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 | 06/09/2021 | 10/12/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 24 | 0 | 24 |  |  | 10/18/2021 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | WESTPORT | 177335 | 02790 | 186.5 |  |  | Solar |  | 05_12_51T2 | 08/31/2016 | 08/31/2016 | 2 | 2 | 0 | 09/02/2016 | 09/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/5/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | LYNN | 737803 | 01904 | 11.5 |  |  | Solar |  | 05_14_36L2 | 12/03/2025 | 12/05/2025 | 1 | 0 | 1 | 01/05/2026 | 01/05/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | HAMILTON | 177624 | 01982 | 15.2 |  |  | Solar |  | 05_14_59L1 | 11/09/2017 | 11/09/2017 | 1 | 0 | 1 | 12/05/2017 | 12/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | NEWBURY | 539516 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | ANDOVER | 637387 | 01810 | 6.4 |  |  | Solar |  | 05_12_67J1 | 09/03/2024 | 09/06/2024 | 6 | 2 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2025 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | METHUEN | 177735 | 01844 | 1000 |  |  | Solar |  | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 05/12/2016 | 06/30/2016 | 33 | 0 | 33 | 8/3/2016 | 05/20/2015 | 9/21/2018 | Y | STD | 779 |  |  | 0 | 0 | 0 |  |  | 9/10/2018 | Connected |  | N | Brockton-South |  |  | Closed
National Grid | MEDFORD | 346007 | 02155 | 7.6 |  |  | Solar |  | 05_01_412L5 | 03/19/2021 | 03/22/2021 | 0 | 0 | 0 | 03/23/2021 | 03/23/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed
National Grid | MILLBURY | 184587 | 01527 | 3000 |  |  | Solar |  | 05_01_602W3 | 06/04/2018 | 06/04/2018 | 11 | 0 | 11 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 06/20/2018 | 07/11/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest |  |  | Study Complete
National Grid | DUDLEY | 177926 | 01571 | 7.6 |  |  | Solar |  | 05_05_115W53 | 04/18/2017 | 04/18/2017 | 4 | 4 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/23/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 10/26/2017 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | WESTMINSTER | 367457 | 01473 | 7.6 |  |  | Solar |  | 05_12_24W2 | 07/09/2021 | 07/12/2021 | 1 | 0 | 1 | 07/13/2021 | 07/13/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/09/2021 | 8/16/2022 | Y | EXP | 365 | 01/13/2022 | 03/31/2022 | 78 | 0 | 78 |  |  | 4/11/2022 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | FALL RIVER | 177599 | 02721 | 28.75 |  |  | Solar |  | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/14/2017 | 09/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 7/24/2018 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | LYNN | 742426 | 01904 | 50 |  |  | Solar |  | 05_14_36L2 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Cape Ann |  |  | Closed - Study Hold
National Grid | ESSEX | 247404 | 01929 | 0 |  |  | Solar |  | 05_14_59L1 | 08/07/2019 | 08/07/2019 | 0 | 0 | 0 | 08/08/2019 | 08/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 10/11/2019 | N | EXP | 57 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N | Beverly |  |  | Closed
National Grid | NEWBURY | 551686 | 01950 | 6.38 |  |  | Solar |  | 05_14_74L1 | 08/29/2023 | 08/31/2023 | 2 | 0 | 2 | 09/01/2023 | 09/01/2023 | 25 | 0 | 25 | 10/13/2023 | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Somerset |  |  | Closed
National Grid | ANDOVER | 688261 | 01810 | 5.76 |  |  | Solar |  | 05_12_67J1 | 05/01/2025 |  | 65 | 63 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Fall River-South |  |  | Closed
National Grid | METHUEN | 178054 | 01844 | 10 |  |  | Solar |  | 05_01_26W2 | 07/05/2017 | 07/05/2017 | 25 | 25 | 0 | 08/10/2017 | 08/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/11/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  | 5/25/2018 | Connected |  | N | Leominster |  |  | 160 Day Study
National Grid | MEDFORD | 442567 | 02155 | 15.2 |  |  | Solar |  | 05_01_412L5 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2022 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | AUBURN | 189902 | 01501 | 950 |  |  | Solar |  | 05_01_602W3 | 07/25/2018 | 09/17/2018 | 101 | 12 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 12/19/2018 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | DUDLEY | 178132 | 01571 | 3.8 |  |  | Solar |  | 05_05_115W53 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | WESTMINSTER | 438823 | 01473 | 7.6 |  |  | Solar |  | 05_12_24W2 | 08/18/2022 | 08/23/2022 | 4 | 3 | 1 | 08/24/2022 | 08/24/2022 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | FALL RIVER | 177600 | 02721 | 28.75 |  |  | Solar |  | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/15/2017 | 09/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2017 |  | 7/24/2018 | N | EXP | 312 |  |  | 0 | 0 | 0 | 3/16/2018 | 3/16/2018 | 4/25/2018 | Connected |  | N | Cape Ann |  |  | Closed - Start Study
National Grid | LYNN | 174790 | 01904 | 1020 |  |  | Diesel |  | 05_14_36L2 | 06/16/2011 | 06/16/2011 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 5/2/2012 | N | STD | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 5/2/2012 | Connected |  | N | Fall River-South |  |  | Closed - Completion Documents Hold
National Grid | ESSEX | 272817 | 01929 | 0 |  |  | Solar |  | 05_14_59L1 | 01/10/2020 | 01/21/2020 | 5 | 0 | 5 | 01/22/2020 | 01/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 1/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N | Fall River-South |  |  | Closed - Completion Documents Hold
National Grid | NEWBURY | 551550 | 01950 | 12 |  |  | Solar |  | 05_14_74L1 | 09/05/2023 |  | 110 | 53 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Awaiting Initial Payments for Common System Modifications - Completion Documents Hold
National Grid | ANDOVER | 578624 | 01810 | 200 |  |  | Solar |  | 05_01_HT56B | 02/06/2024 | 01/17/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill |  |  | Closed
National Grid | METHUEN | 178522 | 01844 | 2297.7 |  |  | Solar |  | 05_01_26W2 | 04/04/2018 | 04/05/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 477663 | 01604 | 15.2 |  |  | Solar |  | 05_01_412L5 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2023 | Connected |  | N | Beverly |  |  | Closed
National Grid | AUBURN | 201267 | 01501 | 996 |  |  | Solar |  | 05_01_602W3 | 01/11/2019 | 02/11/2019 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2019 | 03/18/2019 | 24 | 18 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro |  |  | Time Frame Suspension
National Grid | DUDLEY | 178394 | 01571 | 2470 |  |  | Solar |  | 05_05_115W53 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/12/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | North Andover |  |  | Closed - Conditional Approval Hold
National Grid | WESTMINSTER | 552287 | 01473 | 10 |  |  | Solar |  | 05_12_24W2 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 | 10/11/2023 | 2/14/2025 | Y | EXP | 365 | 04/11/2024 | 04/29/2024 | 19 | 0 | 19 |  |  | 5/5/2024 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | FALL RIVER | 178038 | 02721 | 17.6 |  |  | Solar |  | 05_12_51T2 | 10/27/2017 | 10/27/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 3/30/2019 | N | EXP | 410 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | Time Frame Suspension
National Grid | LYNN | 174865 | 01904 | 30 |  |  | Solar |  | 05_14_36L2 | 04/08/2011 | 04/08/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 04/08/2011 | 5/2/2012 | Y | EXP | 0 | 02/21/2012 | 03/13/2012 | 15 | 0 | 15 | 8/9/2012 | 8/9/2012 | 5/2/2012 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | ESSEX | 279685 | 01929 | 10 |  |  | Solar |  | 05_14_59L1 | 02/24/2020 | 02/25/2020 | 0 | 0 | 0 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2020 |  | 2/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2020 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | NEWBURY | 552256 | 01950 | 0 |  |  | Solar |  | 05_14_74L1 | 08/30/2023 | 09/08/2023 | 6 | 4 | 2 | 09/11/2023 | 09/11/2023 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 680413 | 01810 | 7.6 |  |  | Solar |  | 05_01_216W4 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 04/07/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Scituate |  |  | Closed
National Grid | METHUEN | 194034 | 01844 | 150 |  |  | Solar |  | 05_01_26W2 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | LANCASTER | 483367 | 01523 | 7.6 |  |  | Solar |  | 05_01_412L5 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 89 | 65 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y | Cape Ann |  |  | Closed
National Grid | AUBURN | 321925 | 01501 | 7.6 |  |  | Solar |  | 05_01_602W3 | 10/27/2020 | 10/28/2020 | 0 | 0 | 0 | 10/29/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/19/2022 | N | EXP | 510 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | DUDLEY | 193191 | 01571 | 199.9 |  |  | Solar |  | 05_05_115W53 | 08/13/2018 | 10/15/2018 | 21 | 17 | 4 | 10/16/2018 | 10/16/2018 | 23 | 0 | 23 | 12/07/2018 | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | WESTMINSTER | 567702 | 01473 | 5 |  |  | Solar |  | 05_12_24W2 | 02/26/2024 | 03/12/2024 | 11 | 6 | 5 | 03/13/2024 | 03/13/2024 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2024 | Connected |  | N | Dracut |  |  | Closed - Construction Hold
National Grid | FALL RIVER | 205162 | 02721 | 0 |  |  | Solar |  | 05_12_51T2 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N | Leominster |  |  | Closed
National Grid | LYNN | 175714 | 01904 | 64 |  |  | Solar |  | 05_14_36L2 | 12/24/2014 | 12/24/2014 | 7 | 4 | 3 | 01/06/2015 | 01/06/2015 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 12/31/2016 | N | EXP | 683 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 |  | Withdrawn |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | HAMILTON | 301740 | 01982 | 15.2 |  |  | Solar |  | 05_14_59L1 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 |  | 5/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2021 | Connected |  | N | Leominster |  |  | Closed
National Grid | NEWBURY | 591226 | 01950 | 6 |  |  | Solar |  | 05_14_74L1 | 08/22/2024 | 08/27/2024 | 3 | 0 | 3 | 08/28/2024 | 08/28/2024 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 721352 | 01810 | 9.074 |  |  | Solar |  | 05_01_216W4 | 09/27/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/27/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | METHUEN | 204134 | 01844 | 333 |  |  | Solar |  | 05_01_26W2 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | LANCASTER | 489902 | 01523 | 15.2 |  |  | Solar |  | 05_01_412L5 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | AUBURN | 345465 | 01501 | 500 |  |  | Solar |  | 05_01_602W3 | 04/07/2021 |  | 314 | 158 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater |  |  | 160 Day Study
National Grid | DUDLEY | 193337 | 01571 | 290 |  |  | Solar |  | 05_05_115W53 | 08/13/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 26 | 5 | 21 | 12/07/2018 | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | WESTMINSTER | 588113 | 01473 | 10 |  |  | Solar |  | 05_12_24W2 | 02/12/2024 | 02/22/2024 | 7 | 4 | 3 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/12/2024 | 4/4/2025 | Y | EXP | 365 | 05/17/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 6/25/2024 | Connected |  | N | Leominster |  |  | Closed
National Grid | FALL RIVER | 238751 | 02721 | 10 |  |  | Solar |  | 05_12_51T2 | 06/19/2019 | 06/20/2019 | 0 | 0 | 0 | 06/21/2019 | 06/21/2019 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  | 9/6/2019 | N | EXP | 67 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | LYNN | 177069 | 01904 | 150 |  |  | Solar |  | 05_14_36L2 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 07/29/2016 | 07/29/2016 | 315 | 26 | 289 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/29/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Scituate |  |  | Closed
National Grid | ESSEX | 306442 | 01929 | 0 |  |  | Solar |  | 05_14_59L1 | 08/12/2020 | 09/14/2020 | 21 | 21 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/12/2020 | 9/14/2021 | Y | EXP | 365 | 01/05/2021 | 01/19/2021 | 14 | 0 | 14 |  |  | 3/2/2021 | Connected |  | N | North Andover |  |  | Closed
National Grid | NEWBURY | 593838 | 01950 | 15.2 |  |  | Solar |  | 05_14_74L1 | 03/01/2024 | 04/15/2024 | 28 | 25 | 3 | 04/16/2024 | 04/16/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 725215 | 01810 | 60 |  |  | Solar |  | 05_01_216W4 | 10/09/2025 | 10/29/2025 | 13 | 6 | 7 |  |  | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Brockton-South |  |  | Execute Group Study Agreement - Awaiting Other Group Members
National Grid | METHUEN | 312600 | 01844 | 10 |  |  | Solar |  | 05_01_26W2 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | LANCASTER | 517520 | 01523 | 10 |  |  | Solar |  | 05_01_412L5 | 08/22/2023 | 04/15/2023 | 5 | 4 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2023 | 08/22/2023 | 10/23/2024 | Y | EXP | 365 | 03/13/2024 | 03/22/2024 | 10 | 0 | 10 |  |  | 3/25/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | AUBURN | 556865 | 01501 | 4998 |  |  | Solar |  | 05_01_602W3 | 07/02/2024 |  | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | Notice Period - Awaiting Payment
National Grid | DUDLEY | 193334 | 01571 | 119.9 |  |  | Solar |  | 05_05_115W53 | 08/13/2018 | 10/22/2018 | 6 | 1 | 5 | 10/23/2018 | 10/23/2018 | 45 | 29 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | Notice Period - Draft Ready
National Grid | WESTMINSTER | 599697 | 01473 | 10 |  |  | Solar |  | 05_12_24W2 | 04/12/2024 | 04/15/2024 | 0 | 0 | 0 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/12/2024 | 6/14/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 9/12/2024 | Connected |  | N | Marlborough |  |  | Notice Period - Draft Ready
National Grid | FALL RIVER | 242810 | 02721 | 7.6 |  |  | Solar |  | 05_12_51T2 | 07/16/2019 | 07/17/2019 | 0 | 0 | 0 | 07/18/2019 | 07/18/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2019 |  | 7/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N | Marlborough |  |  | Notice Period - Awaiting Payment
National Grid | LYNN | 177596 | 01904 | 180 |  |  | Solar |  | 05_14_36L2 | 07/18/2017 | 07/18/2017 | 73 | 69 | 4 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2018 | 07/18/2017 | 8/31/2021 | Y | STD | 533 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | ESSEX | 308036 | 01929 | 0 |  |  | Battery Add-On |  | 05_14_59L1 | 09/30/2020 | 10/16/2020 | 11 | 9 | 2 | 10/19/2020 | 10/19/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 4/15/2022 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | NEWBURY | 596597 | 01950 | 6 |  |  | Solar |  | 05_14_74L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/18/2024 | 4/29/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/7/2024 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | ANDOVER | 174206 | 01810 | 2450 |  |  | Solar |  | 05_01_216W4 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 |  | 1/1/2013 | N | STD | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | METHUEN | 339198 | 01844 | 9.8 |  |  | Solar |  | 05_01_26W2 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | BOLTON | 523805 | 01740 | 6.67 |  |  | Solar |  | 05_01_412L5 | 05/08/2023 | 05/12/2023 | 4 | 2 | 2 | 05/15/2023 | 05/15/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/08/2023 | 7/12/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N | Marlborough |  |  | Notice Period
National Grid | AUBURN | 608973 | 01501 | 10 |  |  | Solar |  | 05_01_602W3 | 05/06/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | Notice Period
National Grid | DUDLEY | 206944 | 01571 | 420 |  |  | Solar |  | 05_05_115W53 | 01/24/2019 | 02/07/2019 | 8 | 6 | 2 | 02/08/2019 | 02/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | WESTMINSTER | 599918 | 01473 | 6 |  |  | Solar |  | 05_12_24W2 | 04/09/2024 | 04/16/2024 | 5 | 1 | 4 | 04/17/2024 | 04/17/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 7/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | Notice Period
National Grid | FALL RIVER | 260576 | 02721 | 13.6 |  |  | Solar |  | 05_12_51T2 | 10/17/2019 | 10/24/2019 | 5 | 3 | 2 | 10/25/2019 | 10/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2020 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | LYNN | 177863 | 01904 | 990 |  |  | Solar |  | 05_14_36L2 | 06/13/2017 | 06/13/2017 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2017 | 07/31/2017 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 | 06/13/2017 | 3/15/2024 | Y | STD | 753 | 05/29/2020 | 03/31/2021 | 306 | 5 | 301 |  |  |  | Withdrawn |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 309991 | 01936 | 9.6 |  |  | Solar |  | 05_14_59L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2021 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement
National Grid | NEWBURY | 597545 | 01950 | 7.6 |  |  | Solar |  | 05_14_74L1 | 03/21/2024 | 04/30/2024 | 28 | 25 | 3 | 05/01/2024 | 05/01/2024 | 10 | 3 | 7 | 05/17/2024 | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed - Completion Documents Hold
National Grid | ANDOVER | 176516 | 01810 | 10 |  |  | Solar |  | 05_01_216W4 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 | 10/05/2015 | 10/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 12/29/2015 | 12/29/2015 | 1/12/2016 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | METHUEN | 344165 | 01844 | 2000 |  |  | Solar |  | 05_01_26W2 | 07/28/2021 | 08/23/2021 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2021 | 11/23/2021 | 79 | 59 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | Notice Period - Pending Customer Decision
National Grid | LANCASTER | 535016 | 01523 | 15.2 |  |  | Solar |  | 05_01_412L5 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 75 | 61 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | MILLBURY | 650633 | 01527 | 3.77 |  |  | Solar |  | 05_01_602W3 | 10/29/2024 | 11/06/2024 | 3 | 0 | 3 | 11/07/2024 | 11/07/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Fall River-North |  |  | Closed
National Grid | DUDLEY | 210964 | 01571 | 7.6 |  |  | Solar |  | 05_05_115W53 | 03/17/2019 | 03/19/2019 | 1 | 1 | 0 | 03/20/2019 | 03/20/2019 | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Completion Documents Hold
National Grid | WESTMINSTER | 602977 | 01473 | 3.8 |  |  | Solar |  | 05_12_24W2 | 04/23/2024 | 04/26/2024 | 3 | 0 | 3 | 04/29/2024 | 04/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Completion Documents Hold
National Grid | FALL RIVER | 283128 | 02721 | 8.7 |  |  | Solar |  | 05_12_51T2 | 03/10/2020 | 03/11/2020 | 0 | 0 | 0 | 03/12/2020 | 03/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 3/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | LYNN | 177940 | 01904 | 125 |  |  | Solar |  | 05_14_36L2 | 06/22/2017 | 06/22/2017 | 0 | 0 | 0 | 02/12/2018 | 02/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 06/22/2017 | 12/31/2019 | Y | EXP | 675 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N | Marlborough |  |  | Notice Period - Awaiting Payment
National Grid | WENHAM | 397084 | 01984 | 1375 |  |  | Solar |  | 05_14_59L1 | 03/15/2022 | 02/08/2023 | 57 | 48 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2022 | 06/30/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | Notice Period - Pending Customer Decision
National Grid | NEWBURY | 600465 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 04/04/2024 | 04/16/2024 | 8 | 7 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 5/25/2025 | Y | EXP | 365 | 08/01/2024 | 01/02/2025 | 155 | 0 | 155 |  |  | 4/1/2025 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement
National Grid | TEWKSBURY | 176510 | 01876 | 10 |  |  | Solar |  | 05_01_216W4 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/11/2016 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | METHUEN | 358733 | 01844 | 133.2 |  |  | Solar |  | 05_01_26W2 | 09/03/2021 | 05/12/2022 | 172 | 162 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/25/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N | Millbury-Grafton |  |  | Closed - Study Hold
National Grid | CLINTON | 548244 | 01510 | 6 |  |  | Solar |  | 05_01_412L5 | 08/23/2023 | 08/24/2023 | 1 | 0 | 1 | 08/25/2023 | 08/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 12/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | MILLBURY | 652673 | 01527 | 4.06 |  |  | Solar |  | 05_01_602W3 | 11/06/2024 | 12/02/2024 | 8 | 4 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 214093 | 01571 | 7.36 |  |  | Solar |  | 05_05_115W53 | 05/17/2019 | 05/30/2019 | 7 | 1 | 6 | 05/31/2019 | 05/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 05/17/2019 | 6/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | WESTMINSTER | 605616 | 01473 | 3.8 |  |  | Solar |  | 05_12_24W2 | 04/22/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 04/22/2024 | 6/24/2025 | Y | EXP | 365 | 09/07/2024 | 11/01/2024 | 56 | 0 | 56 |  |  | 11/15/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | FALL RIVER | 293270 | 02721 | 0 |  |  | Battery Add-On |  | 05_12_51T2 | 05/27/2020 | 06/08/2020 | 7 | 7 | 0 | 06/09/2020 | 06/09/2020 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 05/27/2020 | 4/9/2022 | Y | EXP | 365 | 03/10/2021 | 04/05/2021 | 26 | 0 | 26 |  |  |  | Withdrawn |  | N | Methuen/Haverhill |  |  | Closed
National Grid | LYNN | 187091 | 01904 | 86.4 |  |  | Solar |  | 05_14_36L2 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  | 7/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period - Awaiting Payment
National Grid | ESSEX | 408840 | 01929 | 0 |  |  | Battery Add-On |  | 05_14_59L1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/02/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Beverly |  |  | Closed
National Grid | NEWBURY | 605469 | 01950 | 11.4 |  |  | Solar |  | 05_14_74L1 | 04/23/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 12 | 5 | 7 | 06/03/2024 | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 6/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed - Draft Agreement
National Grid | ANDOVER | 186590 | 01810 | 15.2 |  |  | Solar |  | 05_01_216W4 | 05/29/2018 | 05/29/2018 | 8 | 0 | 8 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | METHUEN | 432998 | 01844 | 100 |  |  | Solar |  | 05_01_26W2 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | LANCASTER | 551716 | 01561 | 15.2 |  |  | Solar |  | 05_01_412L5 | 09/05/2023 | 09/07/2023 | 3 | 1 | 2 | 09/08/2023 | 09/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2023 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | AUBURN | 614910 | 01501 | 4000 |  |  | Solar |  | 05_01_607W1 | 09/25/2024 | 10/30/2024 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 12/02/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 278494 | 01571 | 5 |  |  | Solar |  | 05_05_115W53 | 03/04/2020 | 03/18/2020 | 10 | 7 | 3 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2020 | 03/04/2020 |  | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/25/2020 | Connected |  | N | Marlborough |  |  | Notice Period - Pending Customer Decision
National Grid | GARDNER | 632460 | 01440 | 7.6 |  |  | Solar |  | 05_12_24W2 | 08/15/2024 | 08/23/2024 | 1 | 0 | 1 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | Notice Period
National Grid | FALL RIVER | 293961 | 02721 | 15.08 |  |  | Solar |  | 05_12_51T2 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 92 | 82 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2021 | Connected |  | N | Marlborough |  |  | Notice Period - Completion Documents Hold
National Grid | LYNN | 210060 | 01904 | 7.6 |  |  | Solar |  | 05_14_36L2 | 03/19/2019 |  | 142 | 26 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | WENHAM | 412219 | 01984 | 0 |  |  | Battery Add-On |  | 05_14_59L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 609378 | 01950 | 5.76 |  |  | Solar |  | 05_14_74L1 | 05/07/2024 | 05/14/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N | Billerica |  |  | Pending - Construction Hold
National Grid | ANDOVER | 430312 | 01810 | 0 |  |  | Other |  | 05_01_216W4 | 01/04/2023 | 01/19/2023 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 455849 | 01844 | 299.7 |  |  | Solar |  | 05_01_26W2 | 05/05/2023 |  | 120 | 112 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Fall River-North |  |  | Closed
National Grid | LANCASTER | 565284 | 01523 | 6 |  |  | Solar |  | 05_01_412L5 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/01/2023 | 1/1/2025 | Y | EXP | 365 | 05/02/2024 | 06/06/2024 | 36 | 0 | 36 |  |  | 6/13/2024 | Connected |  | N | Fall River-North |  |  | Closed - Completion Documents Hold
National Grid | AUBURN | 673050 | 01501 | 5.76 |  |  | Solar |  | 05_01_607W1 | 02/20/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | Fall River-North |  |  | Closed
National Grid | WEBSTER | 281069 | 01570 | 5 |  |  | Solar |  | 05_05_115W53 | 04/06/2020 | 04/20/2020 | 9 | 9 | 0 | 04/21/2020 | 04/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/06/2020 | 4/19/2021 | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/12/2020 | Connected |  | Y | Fall River-North |  |  | Closed
National Grid | GARDNER | 634313 | 01440 | 8.125 |  |  | Solar |  | 05_12_24W2 | 08/21/2024 | 09/17/2024 | 10 | 6 | 4 | 09/18/2024 | 09/18/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 | 08/21/2024 | 10/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N | Fall River-North |  |  | Closed
National Grid | FALL RIVER | 301864 | 02721 | 7.6 |  |  | Solar |  | 05_12_51T2 | 08/14/2020 | 08/18/2020 | 1 | 0 | 1 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 | 08/14/2020 | 2/5/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N | Fall River-North |  |  | Closed - Awaiting Payment
National Grid | LYNN | 243484 | 01904 | 53 |  |  | Solar |  | 05_14_36L2 | 07/15/2019 | 07/30/2019 | 11 | 3 | 8 | 07/31/2019 | 07/31/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 457561 | 01982 | 9.6 |  |  | Solar |  | 05_14_59L1 | 09/09/2022 | 09/27/2022 | 13 | 12 | 1 | 09/28/2022 | 09/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 610663 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 05/14/2024 | 05/29/2024 | 1 | 0 | 1 | 05/30/2024 | 05/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 05/14/2024 | 12/31/2025 | Y | EXP | 365 | 08/28/2025 |  | 127 | 0 | 127 |  |  | 11/24/2025 | Connected |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 438016 | 01810 | 10 |  |  | Solar |  | 05_01_216W4 | 07/18/2022 | 07/20/2022 | 2 | 0 | 2 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/18/2022 | 8/25/2023 | Y | EXP | 365 | 10/11/2022 | 12/21/2022 | 72 | 0 | 72 |  |  | 1/10/2023 | Connected |  | N | Tewksbury |  |  | Closed
National Grid | METHUEN | 513820 | 01844 | 0 |  |  | Other |  | 05_01_26W2 | 07/11/2023 | 08/25/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 11/28/2023 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed - Internal Review
National Grid | LANCASTER | 564963 | 01523 | 6 |  |  | Solar |  | 05_01_412L5 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 46 | 21 | 25 | 04/01/2024 | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/23/2025 | N | EXP | 365 | 07/25/2024 | 12/19/2024 | 148 | 0 | 148 |  |  | 12/31/2024 | Connected |  | N | Tewksbury |  |  | Closed - Completion Documents Hold
National Grid | AUBURN | 704606 | 01501 | 3.8 |  |  | Solar |  | 05_01_607W1 | 07/14/2025 | 09/11/2025 | 5 | 1 | 4 | 09/12/2025 | 09/12/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 07/14/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Ayer-Clinton |  |  | Required Reviews
National Grid | DUDLEY | 280777 | 01571 | 3.8 |  |  | Solar |  | 05_05_115W53 | 03/10/2020 | 03/18/2020 | 5 | 0 | 5 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Required Reviews
National Grid | GARDNER | 666059 | 01440 | 10 |  |  | Solar |  | 05_12_24W2 | 01/15/2025 | 02/24/2025 | 5 | 1 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 | 01/15/2025 | 5/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N | Ayer-Clinton |  |  | Required Reviews
National Grid | FALL RIVER | 330460 | 02721 | 9.8 |  |  | Solar |  | 05_12_51T2 | 01/21/2021 | 12/07/2021 | 1 | 0 | 1 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/21/2021 | 4/9/2023 | Y | EXP | 365 | 07/31/2021 | 08/26/2021 | 26 | 1 | 25 |  |  | 7/20/2022 | Connected |  | N | Ayer-Clinton |  |  | Required Reviews
National Grid | LYNN | 259475 | 01904 | 53 |  |  | Solar |  | 05_14_36L2 | 10/25/2019 | 11/18/2019 | 15 | 13 | 2 | 11/19/2019 | 11/19/2019 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2020 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 501458 | 01982 | 15.2 |  |  | Solar |  | 05_14_59L1 | 02/13/2023 | 02/14/2023 | 1 | 0 | 1 | 02/15/2023 | 02/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 611903 | 01950 | 7.6 |  |  | Solar |  | 05_14_74L1 | 07/04/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 481067 | 01810 | 6.38 |  |  | Solar |  | 05_01_216W4 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/15/2022 | 5/16/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 522113 | 01844 | 15.08 |  |  | Solar |  | 05_01_26W2 | 11/29/2023 | 05/05/2023 | 7 | 6 | 1 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | LANCASTER | 577506 | 01523 | 7.6 |  |  | Solar |  | 05_01_412L5 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 739577 | 01501 | 7.6 |  |  | Solar |  | 05_01_607W1 | 12/11/2025 | 12/12/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 317453 | 01571 | 50 |  |  | Solar |  | 05_05_115W53 | 10/06/2020 | 11/03/2020 | 18 | 13 | 5 | 11/04/2020 | 11/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 701422 | 01440 | 7.6 |  |  | Solar |  | 05_12_24W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 330933 | 02721 | 5 |  |  | Solar |  | 05_12_51T2 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/13/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2021 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Payment Processed
National Grid | LYNN | 270895 | 01904 | 10 |  |  | Solar |  | 05_14_36L2 | 12/31/2019 | 01/10/2020 | 6 | 0 | 6 | 01/13/2020 | 01/13/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | ESSEX | 504001 | 01929 | 0 |  |  | Solar |  | 05_14_59L1 | 02/24/2023 | 02/27/2023 | 1 | 0 | 1 | 02/28/2023 | 02/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2023 | 02/24/2023 | 7/27/2024 | Y | EXP | 365 | 08/29/2023 | 10/04/2023 | 37 | 0 | 37 |  |  | 11/20/2023 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | NEWBURY | 617697 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 06/13/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 32 | 21 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | ANDOVER | 506925 | 01810 | 8.7 |  |  | Solar |  | 05_01_216W4 | 05/25/2023 | 06/05/2023 | 6 | 4 | 2 | 06/06/2023 | 06/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/25/2023 | 8/12/2024 | Y | EXP | 365 | 05/07/2024 | 05/14/2024 | 8 | 0 | 8 |  |  | 5/15/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | METHUEN | 524124 | 01844 | 8.41 |  |  | Solar |  | 05_01_26W2 | 05/16/2023 | 05/30/2023 | 9 | 8 | 1 | 05/31/2023 | 05/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | LANCASTER | 585721 | 01523 | 8.12 |  |  | Solar |  | 05_01_412L5 | 02/19/2024 | 04/18/2024 | 43 | 40 | 3 | 04/19/2024 | 04/19/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 | 02/19/2024 | 6/21/2025 | Y | EXP | 365 | 07/03/2024 | 07/02/2024 | 0 | 0 | 0 |  |  | 7/16/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | AUBURN | 174398 | 01501 | 1000 |  |  | Solar |  | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/26/2012 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Methuen/Haverhill |  |  | Closed
National Grid | DUDLEY | 391147 | 01571 | 10 |  |  | Solar |  | 05_05_115W53 | 11/03/2021 | 01/10/2022 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/03/2021 | 5/3/2023 | Y | EXP | 365 | 03/11/2022 | 04/29/2022 | 50 | 0 | 50 |  |  | 7/9/2022 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Start Study
National Grid | GARDNER | 716298 | 01440 | 0 |  |  | Battery Add-On |  | 05_12_25W1 | 09/03/2025 | 10/17/2025 | 3 | 0 | 3 | 10/20/2025 | 10/20/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Methuen/Haverhill |  |  | Closed
National Grid | FALL RIVER | 333234 | 02721 | 7.6 |  |  | Solar |  | 05_12_51T2 | 01/27/2021 | 12/08/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | SAUGUS | 324647 | 01906 | 15.2 |  |  | Solar |  | 05_14_36L2 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2021 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | HAMILTON | 512029 | 01982 | 15.2 |  |  | Solar |  | 05_14_59L1 | 03/16/2023 | 03/20/2023 | 2 | 0 | 2 | 03/21/2023 | 03/21/2023 | 59 | 39 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2024 | Connected |  | N | Cape Ann |  |  | Closed - Start Study
National Grid | NEWBURY | 619049 | 01951 | 3.8 |  |  | Solar |  | 05_14_74L1 | 06/19/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 67 | 52 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 06/19/2024 | 1/1/2026 | Y | EXP | 365 | 12/11/2024 |  | 385 | 82 | 303 |  |  | 8/29/2025 | Connected |  | N | Cape Ann |  |  | Closed - Start Study
National Grid | ANDOVER | 640010 | 01810 | 3.77 |  |  | Solar |  | 05_01_216W4 | 09/13/2024 | 09/25/2024 | 5 | 2 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/13/2024 | 12/2/2025 | Y | EXP | 365 | 04/15/2025 | 11/09/2025 | 209 | 0 | 209 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed
National Grid | LAWRENCE | 557228 | 01844 | 12.18 |  |  | Solar |  | 05_01_26W2 | 09/21/2023 | 09/21/2023 | 0 | 0 | 0 | 09/22/2023 | 09/22/2023 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N | Cape Ann |  |  | Closed - Study Hold
National Grid | CLINTON | 592892 | 01510 | 6 |  |  | Solar |  | 05_01_412L5 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/21/2024 | 7/26/2025 | Y | EXP | 365 | 06/28/2024 | 07/02/2024 | 5 | 0 | 5 |  |  | 11/14/2024 | Connected |  | N | Cape Ann |  |  | Closed
National Grid | AUBURN | 174397 | 01501 | 1000 |  |  | Solar |  | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann |  |  | Closed
National Grid | DUDLEY | 440461 | 01571 | 250 |  |  | Solar |  | 05_05_115W53 | 07/25/2022 | 08/10/2022 | 12 | 2 | 10 | 08/11/2022 | 08/11/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 07/25/2022 | 10/22/2025 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann |  |  | Closed - Study Hold
National Grid | GARDNER | 174925 | 01440 | 1000 |  |  | Solar |  | 05_12_25W1 | 02/25/2013 | 02/25/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/09/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | FALL RIVER | 341902 | 02721 | 15.2 |  |  | Solar |  | 05_12_51T2 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N | Millbury-Grafton |  |  | Closed - Completion Documents Hold
National Grid | SAUGUS | 354525 | 01906 | 100 |  |  | Solar |  | 05_14_36L2 | 05/27/2021 | 07/02/2021 | 24 | 14 | 10 | 07/06/2021 | 07/06/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 4/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | ESSEX | 541519 | 01929 | 9.57 |  |  | Solar |  | 05_14_59L1 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 11/22/2024 | Y | EXP | 365 | 03/26/2024 | 07/23/2024 | 120 | 0 | 120 |  |  | 7/25/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 630260 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 08/05/2024 | 08/21/2024 | 9 | 6 | 3 | 08/22/2024 | 08/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/05/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 650594 | 01810 | 10 |  |  | Solar |  | 05_01_216W4 | 11/11/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/11/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Completion Documents Hold
National Grid | METHUEN | 569868 | 01844 | 10 |  |  | Solar |  | 05_01_26W2 | 12/06/2023 | 12/14/2023 | 6 | 3 | 3 | 12/15/2023 | 12/15/2023 | 41 | 19 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Closed - Study Hold
National Grid | LANCASTER | 609568 | 01523 | 3.8 |  |  | Solar |  | 05_01_412L5 | 05/08/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/08/2024 | 6/14/2025 | Y | EXP | 365 | 09/19/2024 | 09/30/2024 | 12 | 0 | 12 |  |  | 11/5/2024 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | AUBURN | 174396 | 01501 | 2000 |  |  | Solar |  | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/24/2012 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 06/14/2012 | 2/11/2014 | Y | STD | 270 | 11/27/2013 | 04/25/2014 | 100 | 0 | 100 | 5/6/2014 | 5/6/2014 | 5/23/2014 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | DUDLEY | 492560 | 01571 | 7.6 |  |  | Solar |  | 05_05_115W53 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 | 02/01/2023 | 7/1/2024 | Y | EXP | 365 | 07/13/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 11/21/2023 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | GARDNER | 175253 | 01440 | 8.82 |  |  | Solar |  | 05_12_25W1 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 9/4/2015 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | FALL RIVER | 347745 | 02721 | 10 |  |  | Solar |  | 05_12_51T2 | 04/15/2021 | 05/05/2021 | 13 | 12 | 1 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | SAUGUS | 668934 | 01906 | 0 |  |  | Battery Add-On |  | 05_14_36L2 | 01/30/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | Time Frame Suspension
National Grid | HAMILTON | 564915 | 01982 | 0 |  |  | Solar |  | 05_14_59L1 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 90 | 78 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 10/20/2023 | 3/20/2025 | Y | EXP | 365 | 07/06/2024 | 09/03/2024 | 60 | 0 | 60 |  |  | 9/10/2024 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | NEWBURY | 631163 | 01950 | 10 |  |  | Solar |  | 05_14_74L1 | 08/08/2024 | 08/20/2024 | 4 | 0 | 4 | 08/21/2024 | 08/21/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/08/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | ANDOVER | 670659 | 01810 | 13.3 |  |  | Solar |  | 05_01_216W4 | 02/08/2025 | 02/18/2025 | 6 | 1 | 5 | 02/19/2025 | 02/19/2025 | 56 | 35 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/08/2025 | 5/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | METHUEN | 572356 | 01844 | 7.6 |  |  | Solar |  | 05_01_26W2 | 01/09/2024 | 01/24/2024 | 11 | 7 | 4 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/09/2024 | 4/17/2025 | Y | EXP | 365 | 05/22/2024 | 09/07/2024 | 109 | 0 | 109 |  |  | 9/17/2024 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | LANCASTER | 613091 | 01523 | 9.56 |  |  | Solar |  | 05_01_412L5 | 05/23/2024 | 06/04/2024 | 3 | 0 | 3 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/23/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/21/2024 | 50 | 0 | 50 |  |  | 1/29/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | AUBURN | 174707 | 01501 | 60 |  |  | Natural Gas |  | 05_01_607W1 | 06/17/2013 | 06/17/2013 | 13 | 5 | 8 | 07/08/2013 | 07/08/2013 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2013 |  | 12/1/2017 | N | EXP | 1592 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Scituate |  |  | 100 Day Study
National Grid | DUDLEY | 501441 | 01571 | 14.79 |  |  | Solar |  | 05_05_115W53 | 06/13/2023 | 02/23/2023 | 13 | 9 | 4 | 07/05/2023 | 07/05/2023 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Scituate |  |  | 100 Day Study
National Grid | GARDNER | 176097 | 01440 | 1296 |  |  | Solar |  | 05_12_25W1 | 04/06/2015 | 04/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2015 | 05/11/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 04/06/2015 | 9/29/2017 | Y | STD | 541 |  |  | 0 | 0 | 0 | 9/7/2017 | 9/7/2017 | 9/8/2017 | Connected |  | N | Scituate |  |  | 100 Day Study
National Grid | FALL RIVER | 368281 | 02721 | 7.6 |  |  | Solar |  | 05_12_51T2 | 07/23/2021 | 01/07/2022 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 07/23/2021 | 1/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2022 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | SAUGUS | 710220 | 01906 | 26.6 |  |  | Solar |  | 05_14_36L2 | 08/06/2025 | 08/28/2025 | 16 | 14 | 2 | 08/29/2025 | 08/29/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | Y | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | ESSEX | 608981 | 01929 | 23 |  |  | Battery Add-On |  | 05_14_59L1 | 05/06/2024 | 05/07/2024 | 1 | 0 | 1 | 05/08/2024 | 05/08/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | NEWBURY | 632110 | 01951 | 10 |  |  | Solar |  | 05_14_74L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/21/2024 | 10/29/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | ANDOVER | 685367 | 01810 | 16.34 |  |  | Solar |  | 05_01_216W4 | 04/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | METHUEN | 587534 | 01844 | 200 |  |  | Solar |  | 05_01_26W2 | 03/14/2024 |  | 56 | 50 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Execute Group Study Agreement
National Grid | LANCASTER | 677277 | 01523 | 7.6 |  |  | Solar |  | 05_01_412L5 | 03/11/2025 | 03/25/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | AUBURN | 175258 | 01501 | 42 |  |  | Solar |  | 05_01_607W1 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 425 | 0 | 425 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 |  | Withdrawn |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 519921 | 01570 | 6 |  |  | Solar |  | 05_05_115W53 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | GARDNER | 176438 | 01440 | 10 |  |  | Solar |  | 05_12_25W1 | 03/16/2016 | 03/16/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/22/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 7/29/2016 | 7/29/2016 | 7/29/2016 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 369753 | 02721 | 8.376 |  |  | Solar |  | 05_12_51T2 | 08/17/2021 | 08/27/2021 | 9 | 8 | 1 | 08/30/2021 | 08/30/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2021 |  | 11/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2022 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 558936 | 01906 | 240 |  |  | Solar |  | 05_14_3J4 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/29/2023 | 3/2/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 627752 | 01915 | 23.725 |  |  | Solar |  | 05_14_59L1 | 08/23/2024 | 08/27/2024 | 2 | 0 | 2 | 08/28/2024 | 08/28/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N | Brockton-South |  |  | Execute Group Study Agreement - Pending Countersignature
National Grid | LOWELL | 644612 | 01852 | 10 |  |  | Solar |  | 05_14_74L1 | 10/02/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 52 | 34 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 10/02/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N | Brockton-South |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | ANDOVER | 686227 | 01810 | 10 |  |  | Solar |  | 05_01_216W4 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Execute Group Study Agreement
National Grid | METHUEN | 588475 | 01844 | 125 |  |  | Solar |  | 05_01_26W2 | 04/17/2024 |  | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland |  |  | Scoping Meeting
National Grid | CLINTON | 678787 | 01510 | 11.52 |  |  | Solar |  | 05_01_412L5 | 03/18/2025 | 04/01/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 03/18/2025 | 7/11/2026 | Y | EXP | 365 | 09/17/2025 | 10/10/2025 | 24 | 0 | 24 |  |  | 10/22/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | AUBURN | 176116 | 01501 | 7.6 |  |  | Solar |  | 05_01_607W1 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/29/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 3/18/2016 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | DUDLEY | 546881 | 01571 | 10 |  |  | Solar |  | 05_05_115W53 | 09/05/2023 | 08/15/2023 | 4 | 0 | 4 | 09/12/2023 | 09/12/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | GARDNER | 176708 | 01440 | 10 |  |  | Solar |  | 05_12_25W1 | 10/27/2015 | 10/27/2015 | 1 | 1 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 10/27/2015 | 11/3/2016 | Y | EXP | 344 | 09/21/2016 | 10/11/2016 | 13 | 0 | 13 | 11/25/2015 | 11/25/2015 | 10/26/2016 | Connected |  | N | Billerica |  |  | Closed
National Grid | FALL RIVER | 372473 | 02721 | 6.96 |  |  | Solar |  | 05_12_51T2 | 07/28/2021 | 07/29/2021 | 1 | 0 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2021 | Connected |  | N | Cape Ann |  |  | Closed - Design Hold
National Grid | SAUGUS | 735290 | 01906 | 17.6 |  |  | Solar |  | 05_14_3J4 | 11/24/2025 | 12/01/2025 | 4 | 0 | 4 | 12/02/2025 | 12/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | BEVERLY | 631986 | 01915 | 0 |  |  | Solar |  | 05_14_59L1 | 08/12/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 101 | 77 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N | Dracut |  |  | Closed
National Grid | LOWELL | 645335 | 01852 | 3.8 |  |  | Solar |  | 05_14_74L1 | 10/07/2024 | 12/04/2024 | 25 | 20 | 5 | 12/05/2024 | 12/05/2024 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/07/2024 | 2/25/2026 | Y | EXP | 365 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | ANDOVER | 696423 | 01810 | 10 |  |  | Solar |  | 05_01_216W4 | 06/09/2025 | 06/18/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Start Study
National Grid | METHUEN | 608555 | 01844 | 10 |  |  | Solar |  | 05_01_26W2 | 05/03/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro |  |  | Time Frame Suspension
National Grid | CLINTON | 635538 | 01510 | 0 |  |  | Other |  | 05_01_412L6 | 11/08/2024 | 12/12/2024 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Dracut |  |  | Closed
National Grid | AUBURN | 176507 | 01501 | 6 |  |  | Solar |  | 05_01_607W1 | 03/24/2016 | 03/24/2016 | 36 | 36 | 0 | 05/17/2016 | 05/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 03/24/2016 | 3/30/2017 | Y | EXP | 297 | 07/28/2016 | 09/23/2016 | 40 | 0 | 40 | 11/8/2016 | 11/8/2016 | 11/10/2016 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | WEBSTER | 575780 | 01570 | 9.765 |  |  | Solar |  | 05_05_115W53 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/11/2023 | 2/25/2025 | Y | EXP | 365 | 07/02/2024 | 08/02/2024 | 32 | 0 | 32 |  |  | 8/20/2024 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | GARDNER | 176712 | 01440 | 8.75 |  |  | Solar |  | 05_12_25W1 | 01/07/2016 | 01/07/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 1/13/2017 | N | EXP | 360 |  |  | 0 | 0 | 0 | 2/22/2016 | 2/22/2016 | 2/25/2016 | Connected |  | N | Billerica |  |  | Closed - Awaiting Payment
National Grid | FALL RIVER | 396471 | 02721 | 0 |  |  | Other |  | 05_12_51T2 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 397015 | 01906 | 200 |  |  | Solar |  | 05_14_3J4 | 11/24/2021 | 12/06/2021 | 7 | 0 | 7 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  | 6/2/2023 | N | STD | 65 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | ESSEX | 662547 | 01929 | 7.6 |  |  | Solar |  | 05_14_59L1 | 01/02/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N | Worcester North/South |  |  | Closed
National Grid | LOWELL | 646267 | 01852 | 10 |  |  | Solar |  | 05_14_74L1 | 10/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/21/2024 | 1/19/2026 | Y | EXP | 365 | 03/04/2025 | 03/03/2025 | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | TEWKSBURY | 546068 | 01876 | 500 |  |  | Solar |  | 05_01_216W5 | 09/07/2023 | 10/12/2023 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | METHUEN | 658756 | 01844 | 7.6 |  |  | Solar |  | 05_01_26W2 | 12/05/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/05/2024 | 2/13/2026 | Y | EXP | 365 | 05/22/2025 | 05/21/2025 | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | CLINTON | 718416 | 01510 | 0 |  |  | Other |  | 05_01_412L6 | 10/27/2025 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | AUBURN | 177059 | 01501 | 900 |  |  | Solar |  | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WEBSTER | 577963 | 01570 | 10 |  |  | Solar |  | 05_05_115W53 | 12/18/2023 | 01/02/2024 | 8 | 6 | 2 | 01/03/2024 | 01/03/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/18/2023 | 2/6/2025 | Y | EXP | 365 | 03/26/2024 | 03/25/2024 | 0 | 0 | 0 |  |  | 4/23/2024 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | WINCHENDON | 176752 | 01475 | 34.2 |  |  | Solar |  | 05_12_25W1 | 01/12/2016 | 01/12/2016 | 8 | 8 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/12/2016 | 1/18/2017 | Y | EXP | 344 | 05/27/2016 | 06/03/2016 | 4 | 0 | 4 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | FALL RIVER | 401039 | 02721 | 15.2 |  |  | Solar |  | 05_12_51T2 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-West |  |  | Time Frame Suspension
National Grid | SAUGUS | 174366 | 01906 | 45.6 |  |  | Solar |  | 05_14_3J40 | 05/21/2012 | 05/21/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2012 |  | 8/1/2012 | N | EXP | -2 |  |  | 0 | 0 | 0 | 10/1/2012 | 10/1/2012 | 10/19/2012 | Connected |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | HAMILTON | 664232 | 01982 | 0 |  |  | Battery Add-On |  | 05_14_59L1 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | ANDOVER | 647971 | 01810 | 7.6 |  |  | Solar |  | 05_14_74L1 | 10/17/2024 | 01/22/2025 | 3 | 0 | 3 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 10/17/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | ANDOVER | 174377 | 01810 | 1000 |  |  | Solar |  | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2013 | N | STD |  | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | METHUEN | 696813 | 01844 | 15.2 |  |  | Solar |  | 05_01_26W2 | 06/10/2025 | 06/17/2025 | 5 | 0 | 5 | 06/18/2025 | 06/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N | Beverly |  |  | Closed
National Grid | CLINTON | 176664 | 01510 | 660 |  |  | Solar |  | 05_01_412L6 | 10/20/2015 | 10/20/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 10/25/2016 | N | STD | -237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | AUBURN | 177058 | 01501 | 4500 |  |  | Solar |  | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed
National Grid | WEBSTER | 617210 | 01570 | 7.6 |  |  | Solar |  | 05_05_115W53 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/11/2024 | 8/7/2025 | Y | EXP | 365 | 09/25/2024 | 10/16/2024 | 22 | 0 | 22 |  |  | 10/29/2024 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | WINCHENDON | 176963 | 01475 | 15.2 |  |  | Solar |  | 05_12_25W1 | 07/18/2016 | 07/18/2016 | 0 | 0 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/18/2016 | 10/12/2018 | Y | EXP | 808 | 01/18/2018 | 03/05/2018 | 30 | 0 | 30 |  |  | 9/26/2018 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 421351 | 02721 | 0 |  |  | Solar |  | 05_12_51T2 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 174644 | 01906 | 18 |  |  | Solar |  | 05_14_3J40 | 12/17/2013 | 12/17/2013 | 5 | 0 | 5 | 12/27/2013 | 12/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2014 |  | 2/28/2014 | N | EXP | 57 |  |  | 0 | 0 | 0 | 1/13/2014 | 1/13/2014 | 4/25/2014 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | ESSEX | 678283 | 01929 | 5.76 |  |  | Solar |  | 05_14_59L1 | 03/19/2025 | 03/28/2025 | 8 | 3 | 5 | 03/31/2025 | 03/31/2025 | 116 | 94 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 648935 | 01810 | 5.76 |  |  | Solar |  | 05_14_74L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 | 03/15/2025 | 03/25/2025 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | TEWKSBURY | 174376 | 01876 | 1954 |  |  | Solar |  | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 | 03/26/2014 | 03/26/2014 | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 8/31/2017 | Y | STD | 1631 | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 | 6/27/2017 | 6/27/2017 | 9/29/2017 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | METHUEN | 683563 | 01844 | 13.8 |  |  | Solar |  | 05_01_26W3 | 04/16/2025 | 08/29/2025 | 29 | 24 | 5 | 09/02/2025 | 09/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 04/16/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | CLINTON | 176663 | 01510 | 1000 |  |  | Solar |  | 05_01_412L6 | 10/20/2015 | 10/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 | 10/20/2015 | 6/10/2021 | Y | STD | 316 | 10/03/2020 | 02/26/2021 | 146 | 0 | 146 |  |  | 6/8/2021 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | AUBURN | 177090 | 01501 | 4500 |  |  | Solar |  | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/10/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WEBSTER | 634387 | 01570 | 10 |  |  | Solar |  | 05_05_115W53 | 08/21/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 | 08/21/2024 | 10/28/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | WINCHENDON | 185047 | 01475 | 13.6 |  |  | Solar |  | 05_12_25W1 | 07/09/2018 | 07/18/2018 | 7 | 3 | 4 | 07/19/2018 | 07/19/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 7/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | FALL RIVER | 433980 | 02721 | 7.6 |  |  | Solar |  | 05_12_51T2 | 06/14/2022 | 06/15/2022 | 2 | 1 | 1 | 06/16/2022 | 06/16/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2023 | Connected |  | N | North Andover |  |  | Closed
National Grid | SAUGUS | 479312 | 01906 | 15.2 |  |  | Solar |  | 05_14_3J41 | 11/21/2022 | 11/23/2022 | 2 | 0 | 2 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period - Awaiting Payment
National Grid | HAMILTON | 681004 | 01982 | 13.8 |  |  | Solar |  | 05_14_59L1 | 03/28/2025 | 04/09/2025 | 3 | 0 | 3 | 04/17/2025 | 04/17/2025 | 22 | 0 | 22 | 06/17/2025 | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 7/28/2025 | 03/28/2025 | 7/31/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 11/24/2025 | Connected |  | N | Beverly |  |  | Closed
National Grid | ANDOVER | 650926 | 01810 | 10 |  |  | Solar |  | 05_14_74L1 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N | Millbury-Grafton |  |  | Closed
National Grid | TEWKSBURY | 177492 | 01876 | 7.6 |  |  | Solar |  | 05_01_216W5 | 12/13/2016 | 12/13/2016 | 6 | 6 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 |  | 12/18/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | METHUEN | 201422 | 01844 | 500 |  |  | Solar |  | 05_01_412L6 | 12/07/2018 | 01/05/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2019 | 02/05/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Bridgewater |  |  | 160 Day Study
National Grid | CLINTON | 177393 | 01510 | 4950 |  |  | Solar |  | 05_01_607W1 | 02/17/2017 | 02/27/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2017 | 03/14/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 02/17/2017 | 12/31/2020 | Y | STD | 838 | 12/12/2019 | 12/31/2020 | 385 | 5 | 380 | 12/30/2020 | 12/31/2020 | 12/31/2019 | Connected |  | N | North Andover |  |  | Closed
National Grid | AUBURN | 640654 | 01501 | 7.6 |  |  | Solar |  | 05_05_115W53 | 09/18/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 2/18/2025 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 219604 | 01570 | 7.6 |  |  | Solar |  | 05_12_25W1 | 04/12/2019 | 10/02/2019 | 119 | 114 | 5 | 10/03/2019 | 10/03/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | GARDNER | 433829 | 01440 | 5.76 |  |  | Solar |  | 05_12_51T2 | 06/07/2022 | 06/15/2022 | 6 | 5 | 1 | 06/16/2022 | 06/16/2022 | 74 | 42 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 577657 | 02721 | 23 |  |  | Solar |  | 05_14_3J44 | 12/13/2023 | 12/18/2023 | 3 | 2 | 1 | 12/19/2023 | 12/19/2023 | 83 | 28 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 681911 | 01906 | 15.2 |  |  | Solar |  | 05_14_59L1 | 04/01/2025 | 04/10/2025 | 8 | 3 | 5 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ESSEX | 650870 | 01929 | 10 |  |  | Solar |  | 05_14_74L1 | 11/11/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/11/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 178289 | 01810 | 11.4 |  |  | Solar |  | 05_01_216W5 | 03/28/2018 | 03/28/2018 | 7 | 7 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/3/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-Northwest |  |  | Closed
National Grid | ANDOVER | 690816 | 01810 | 499 |  |  | Other |  | 05_01_26W3 | 07/11/2025 | 08/29/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 10/15/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y | Chelmsford/Westford |  |  | Notice Period
National Grid | METHUEN | 311549 | 01844 | 250 |  |  | Hydro |  | 05_01_412L6 | 02/22/2022 | 05/27/2022 | 67 | 59 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/21/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 | 02/22/2022 | 12/31/2024 | Y | STD | 306 | 10/01/2024 | 10/31/2024 | 31 | 0 | 31 |  |  | 1/9/2025 | Connected |  | Y | Beverly |  |  | Closed
National Grid | CLINTON | 177538 | 01510 | 4990 |  |  | Solar |  | 05_01_607W1 | 11/06/2017 | 12/15/2017 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2017 | 01/10/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | AUBURN | 644253 | 01501 | 7.6 |  |  | Solar |  | 05_05_115W53 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | WEBSTER | 234682 | 01570 | 3.8 |  |  | Solar |  | 05_12_25W1 | 07/24/2019 | 08/30/2019 | 27 | 26 | 1 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 |  | 12/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | GARDNER | 448083 | 01440 | 7.6 |  |  | Solar |  | 05_12_51T2 | 08/17/2022 | 08/22/2022 | 17 | 9 | 8 | 08/23/2022 | 08/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2023 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | FALL RIVER | 646072 | 02721 | 7.6 |  |  | Solar |  | 05_14_3J44 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/14/2026 | Y | EXP | 365 | 03/27/2025 | 05/07/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | SAUGUS | 686755 | 01906 | 19.14 |  |  | Solar |  | 05_14_59L1 | 04/22/2025 | 04/29/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N | Brockton-North |  |  | Time Frame Suspension
National Grid | BEVERLY | 651514 | 01915 | 5.76 |  |  | Solar |  | 05_14_74L1 | 11/21/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | ANDOVER | 178323 | 01810 | 249.8 |  |  | Solar |  | 05_01_216W5 | 03/29/2018 | 03/29/2018 | 9 | 0 | 9 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  | 12/31/2020 | N | EXP | 373 |  |  | 0 | 0 | 0 |  |  | 2/19/2021 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ANDOVER | 704637 | 01810 | 480 |  |  | Solar |  | 05_01_26W3 | 10/29/2025 | 11/10/2025 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | METHUEN | 455151 | 01844 | 100 |  |  | Solar |  | 05_01_412L6 | 11/15/2022 |  | 237 | 229 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | CLINTON | 177882 | 01510 | 3300 |  |  | Solar |  | 05_01_607W1 | 10/18/2017 | 12/21/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 12/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 10/24/2018 | N | STD | 43 | 10/10/2018 | 03/01/2019 | 142 | 0 | 142 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | AUBURN | 647339 | 01501 | 10 |  |  | Solar |  | 05_05_115W53 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/15/2024 | 11/27/2025 | Y | EXP | 365 | 01/07/2025 | 01/06/2025 | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 276489 | 01570 | 400 |  |  | Solar |  | 05_12_25W1 | 04/09/2020 | 04/22/2020 | 7 | 2 | 5 |  |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2020 | 04/09/2020 | 5/13/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | WINCHENDON | 457042 | 01475 | 15.2 |  |  | Solar |  | 05_12_51T2 | 09/07/2022 | 09/08/2022 | 1 | 0 | 1 | 09/09/2022 | 09/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 662149 | 02721 | 5.76 |  |  | Solar |  | 05_14_3J45 | 12/23/2024 | 01/15/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 12/23/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 709203 | 01906 | 22.8 |  |  | Solar |  | 05_14_59L1 | 08/03/2025 | 08/21/2025 | 13 | 10 | 3 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N | Ayer-Clinton |  |  | Closed
National Grid | HAMILTON | 655742 | 01982 | 3.8 |  |  | Solar |  | 05_14_74L1 | 11/20/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N | Dracut |  |  | Closed
National Grid | ANDOVER | 256639 | 01810 | 7.6 |  |  | Solar |  | 05_01_216W5 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/14/2019 | 10/21/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2021 | Connected |  | N | Attleboro |  |  | Time Frame Suspension
National Grid | ANDOVER | 711413 | 01810 | 15.2 |  |  | Solar |  | 05_01_26W3 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 08/12/2025 | 10/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Chelmsford/Westford |  |  | Notice Period - Awaiting Payment
National Grid | METHUEN | 605768 | 01844 | 6 |  |  | Solar |  | 05_01_412L6 | 04/24/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 09/06/2024 | 10/11/2024 | 36 | 0 | 36 |  |  | 10/18/2024 | Connected |  | N | MPL-Northwest |  |  | Closed
National Grid | CLINTON | 177919 | 01510 | 3300 |  |  | Solar |  | 05_01_607W1 | 10/23/2017 | 10/23/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 |  | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Cape Ann |  |  | Closed - Study Hold
National Grid | AUBURN | 651440 | 01501 | 4.35 |  |  | Solar |  | 05_05_115W53 | 11/01/2024 | 12/09/2024 | 8 | 4 | 4 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/01/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N | North Andover |  |  | Closed
National Grid | WEBSTER | 374165 | 01570 | 9.98 |  |  | Solar |  | 05_12_25W1 | 11/05/2021 |  | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Methuen/Haverhill |  |  | Closed
National Grid | GARDNER | 459143 | 01440 | 15.2 |  |  | Solar |  | 05_12_51T2 | 09/15/2022 | 09/19/2022 | 2 | 0 | 2 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | N | Methuen/Haverhill |  |  | Closed
National Grid | FALL RIVER | 488581 | 02721 | 300 |  |  | Solar |  | 05_14_3J5 | 02/24/2023 |  | 302 | 204 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Millbury-Grafton |  |  | Closed
National Grid | SAUGUS | 176542 | 01906 | 10 |  |  | Solar |  | 05_14_59L3 | 03/30/2016 | 03/30/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Spencer-Rutland |  |  | Scoping Meeting
National Grid | ESSEX | 657618 | 01929 | 10 |  |  | Solar |  | 05_14_74L1 | 11/29/2024 | 01/10/2025 | 2 | 0 | 2 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/29/2024 | 3/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N | Dracut |  |  | Closed
National Grid | LOWELL | 497623 | 01852 | 18.27 |  |  | Solar |  | 05_01_216W5 | 02/01/2023 | 02/03/2023 | 3 | 2 | 1 | 02/06/2023 | 02/06/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 | 02/01/2023 | 3/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | TEWKSBURY | 176827 | 01876 | 10 |  |  | Solar |  | 05_01_26W3 | 01/18/2016 | 01/18/2016 | 5 | 5 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 1/30/2017 | N | EXP | 320 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | Time Frame Suspension - Completion Documents Hold
National Grid | METHUEN | 633327 | 01844 | 5 |  |  | Solar |  | 05_01_412L6 | 08/19/2024 | 09/03/2024 | 2 | 1 | 1 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/19/2024 | 11/6/2025 | Y | EXP | 365 | 11/19/2024 | 02/28/2025 | 102 | 0 | 102 |  |  | 3/27/2025 | Connected |  | N | Beverly |  |  | Closed
National Grid | CLINTON | 177998 | 01510 | 660 |  |  | Solar |  | 05_01_607W1 | 10/25/2017 | 01/05/2018 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/19/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | AUBURN | 654700 | 01501 | 3.8 |  |  | Solar |  | 05_05_115W53 | 11/19/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/19/2024 | 3/18/2026 | Y | EXP | 365 | 04/02/2025 | 04/18/2025 | 17 | 0 | 17 |  |  | 5/3/2025 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | WEBSTER | 410526 | 01570 | 0 |  |  | Solar |  | 05_12_25W1 | 02/04/2022 | 02/08/2022 | 2 | 1 | 1 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2022 | Connected |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | WINCHENDON | 476277 | 01475 | 0 |  |  | Solar |  | 05_12_51T2 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/15/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | Closed
National Grid | FALL RIVER | 707495 | 02721 | 10 |  |  | Solar |  | 05_14_3J7 | 07/25/2025 | 09/12/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 | 07/25/2025 | 10/24/2026 | Y | EXP | 365 | 12/18/2025 |  | 15 | 0 | 15 |  |  |  | Construction |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | MELROSE | 176927 | 02176 | 7.6 |  |  | Solar |  | 05_14_59L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/25/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/19/2016 | 5/19/2016 | 5/23/2016 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | HAMILTON | 663020 | 01982 | 5.76 |  |  | Solar |  | 05_14_74L1 | 12/30/2024 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 12/30/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | LOWELL | 521794 | 01852 | 13 |  |  | Solar |  | 05_01_216W5 | 04/28/2023 | 05/08/2023 | 7 | 5 | 2 | 05/09/2023 | 05/09/2023 | 65 | 47 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2023 | Connected |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | TEWKSBURY | 177912 | 01876 | 9 |  |  | Solar |  | 05_01_26W3 | 08/17/2017 | 08/17/2017 | 8 | 2 | 6 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/22/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | METHUEN | 644967 | 01844 | 10 |  |  | Solar |  | 05_01_412L6 | 10/04/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/04/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | CLINTON | 178113 | 01510 | 4990 |  |  | Solar |  | 05_01_607W1 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | AUBURN | 660461 | 01501 | 4.64 |  |  | Solar |  | 05_05_115W53 | 12/13/2024 | 01/30/2025 | 28 | 25 | 3 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | WEBSTER | 537105 | 01570 | 10 |  |  | Solar |  | 05_12_25W1 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 | 08/01/2023 | 11/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | GARDNER | 477583 | 01440 | 9.57 |  |  | Solar |  | 05_12_51T2 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  | 1/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N | Hanover |  |  | Awaiting Initial Payments for Common System Modifications
National Grid | FALL RIVER | 647453 | 02721 | 6.67 |  |  | Solar |  | 05_14_3J7 | 10/16/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Adams-Deerfield |  |  | Closed
National Grid | SAUGUS | 177144 | 01906 | 10 |  |  | Solar |  | 05_14_59L3 | 05/29/2016 | 05/29/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 164 | 0 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-South |  |  | Awaiting Full Payments for Common System Modifications
National Grid | ESSEX | 667339 | 01929 | 5.76 |  |  | Solar |  | 05_14_74L1 | 01/23/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/23/2025 | 3/28/2026 | Y | EXP | 365 | 06/18/2025 | 12/22/2025 | 188 | 0 | 188 |  |  | 12/4/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | LOWELL | 641059 | 01852 | 5 |  |  | Solar |  | 05_01_216W5 | 09/19/2024 | 10/15/2024 | 3 | 0 | 3 | 10/16/2024 | 10/16/2024 | 57 | 40 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 09/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N | North Andover |  |  | Closed
National Grid | TEWKSBURY | 178217 | 01876 | 3.8 |  |  | Solar |  | 05_01_26W3 | 04/13/2018 | 04/13/2018 | 9 | 0 | 9 | 07/16/2018 | 07/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 4/21/2019 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | North Andover |  |  | Closed
National Grid | METHUEN | 661555 | 01844 | 5.76 |  |  | Solar |  | 05_01_412L6 | 12/18/2024 | 01/09/2025 | 5 | 0 | 5 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 05/15/2025 | 05/14/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | North Andover |  |  | Closed
National Grid | CLINTON | 178530 | 01510 | 1250 |  |  | Solar |  | 05_01_607W1 | 12/04/2017 | 12/04/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/01/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | North Andover |  |  | Closed
National Grid | AUBURN | 578612 | 01501 | 8.7 |  |  | Solar |  | 05_12_25W1 | 01/08/2024 | 01/11/2024 | 3 | 0 | 3 | 01/12/2024 | 01/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | North Andover |  |  | Closed
National Grid | WEBSTER | 483824 | 01570 | 0 |  |  | Solar |  | 05_12_51T2 | 12/08/2022 | 12/15/2022 | 6 | 4 | 2 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N | Tewksbury |  |  | Closed - Internal Review
National Grid | WINCHENDON | 647340 | 01475 | 8.12 |  |  | Solar |  | 05_14_3J7 | 10/21/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | FALL RIVER | 177325 | 02721 | 6 |  |  | Solar |  | 05_14_59L3 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/22/2016 | 06/22/2016 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2016 |  | 6/26/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 668089 | 01906 | 3.8 |  |  | Solar |  | 05_14_74L1 | 01/27/2025 | 02/18/2025 | 1 | 0 | 1 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N | Fall River-North |  |  | Closed - Awaiting Payment
National Grid | ESSEX | 649301 | 01929 | 5.76 |  |  | Solar |  | 05_01_216W5 | 11/05/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 11/05/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Billerica |  |  | Closed
National Grid | LOWELL | 178678 | 01852 | 7.6 |  |  | Solar |  | 05_01_26W3 | 04/11/2018 | 04/11/2018 | 29 | 28 | 1 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/17/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford |  |  | Notice Period
National Grid | TEWKSBURY | 672975 | 01876 | 17.6 |  |  | Solar |  | 05_01_412L6 | 03/03/2025 | 03/14/2025 | 10 | 5 | 5 | 03/17/2025 | 03/17/2025 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/03/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N | Bridgewater |  |  | 160 Day Study
National Grid | METHUEN | 178646 | 01844 | 4980 |  |  | Solar |  | 05_01_607W1 | 12/15/2017 | 09/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2018 | 05/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | Time Frame Suspension
National Grid | CLINTON | 661398 | 01510 | 3.8 |  |  | Solar |  | 05_05_115W53 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Tewksbury |  |  | Closed - Completion Documents Hold
National Grid | OXFORD | 647190 | 01540 | 6 |  |  | Solar |  | 05_12_25W1 | 10/15/2024 | 10/18/2024 | 1 | 0 | 1 | 10/21/2024 | 10/21/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N | Methuen/Haverhill |  |  | Closed - Completion Documents Hold
National Grid | WEBSTER | 485658 | 01570 | 7.6 |  |  | Solar |  | 05_12_51T2 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 63 | 40 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | Y | Chelmsford/Westford |  |  | Notice Period - Study Hold
National Grid | WINCHENDON | 648266 | 01475 | 5.76 |  |  | Solar |  | 05_14_3J7 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/8/2026 | Y | EXP | 365 | 03/04/2025 | 05/14/2025 | 72 | 0 | 72 |  |  | 5/23/2025 | Connected |  | N | Hopedale-East |  |  | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 177655 | 02721 | 2838 |  |  | Solar |  | 05_14_59L3 | 11/09/2017 | 11/09/2017 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/30/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 11/09/2017 | 4/10/2022 | Y | STD | 266 | 11/17/2021 | 01/13/2022 | 57 | 0 | 57 |  |  | 2/18/2022 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | SAUGUS | 668858 | 01906 | 10 |  |  | Solar |  | 05_14_74L1 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N | Marlborough |  |  | Notice Period
National Grid | ESSEX | 654500 | 01929 | 10 |  |  | Solar |  | 05_01_216W5 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N | Chelmsford/Westford |  |  | Notice Period - Awaiting Payment
National Grid | LOWELL | 189789 | 01852 | 15.2 |  |  | Solar |  | 05_01_26W3 | 07/02/2018 | 07/02/2018 | 5 | 4 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | Closed
National Grid | TEWKSBURY | 680767 | 01876 | 3.8 |  |  | Solar |  | 05_01_412L6 | 03/26/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Tewksbury |  |  | Closed - Sent to Customer
National Grid | METHUEN | 663847 | 01844 | 3.8 |  |  | Solar |  | 05_05_115W53 | 01/06/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Ayer-Clinton |  |  | Closed
National Grid | CLINTON | 656366 | 01510 | 10 |  |  | Solar |  | 05_12_25W1 | 11/22/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | Closed
National Grid | AUBURN | 501092 | 01501 | 5.76 |  |  | Solar |  | 05_12_51T2 | 03/30/2023 | 04/03/2023 | 2 | 0 | 2 | 04/04/2023 | 04/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/30/2023 | 5/21/2024 | Y | EXP | 365 | 07/20/2023 | 07/24/2023 | 5 | 0 | 5 |  |  | 8/1/2023 | Connected |  | Y | Bridgewater |  |  | 160 Day Study
National Grid | WEBSTER | 653837 | 01570 | 3.8 |  |  | Solar |  | 05_14_3J7 | 11/13/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N | Lowell |  |  | Time Frame Suspension
National Grid | WINCHENDON | 178219 | 01475 | 7.6 |  |  | Solar |  | 05_14_59L3 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Lowell |  |  | Time Frame Suspension
National Grid | FALL RIVER | 673277 | 02721 | 23 |  |  | Solar |  | 05_14_74L1 | 02/20/2025 | 06/05/2025 | 72 | 38 | 34 | 06/06/2025 | 06/06/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N | Lowell |  |  | Time Frame Suspension
National Grid | SAUGUS | 656839 | 01906 | 5.76 |  |  | Solar |  | 05_01_216W5 | 11/25/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Lowell |  |  | Time Frame Suspension
National Grid | ESSEX | 189536 | 01929 | 17.6 |  |  | Solar |  | 05_01_26W3 | 06/28/2018 | 06/28/2018 | 13 | 11 | 2 | 07/19/2018 | 07/19/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  | 8/23/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2019 | Connected |  | N | Scituate |  |  | 100 Day Study
National Grid | LOWELL | 687053 | 01852 | 3.8 |  |  | Solar |  | 05_01_412L6 | 04/23/2025 | 07/09/2025 | 52 | 48 | 4 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N | Scituate |  |  | 100 Day Study
National Grid | TEWKSBURY | 195209 | 01876 | 8290 |  |  | Solar |  | 05_01_607W1 | 10/22/2018 | 10/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/06/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Ayer-Clinton |  |  | Required Reviews
National Grid | METHUEN | 669664 | 01844 | 5.76 |  |  | Solar |  | 05_05_115W53 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 02/03/2025 | 4/7/2026 | Y | EXP | 365 | 04/29/2025 | 06/24/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | CLINTON | 665766 | 01510 | 7.6 |  |  | Solar |  | 05_12_25W1 | 01/15/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/15/2025 | 3/21/2026 | Y | EXP | 365 | 10/28/2025 | 10/29/2025 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | AUBURN | 524266 | 01501 | 9.28 |  |  | Solar |  | 05_12_51T2 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | WEBSTER | 662094 | 01570 | 6.46 |  |  | Solar |  | 05_14_3J7 | 12/20/2024 | 03/17/2025 | 53 | 49 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | GARDNER | 178637 | 01440 | 7.6 |  |  | Solar |  | 05_14_59L3 | 04/09/2018 | 04/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-South |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | FALL RIVER | 679348 | 02721 | 7.6 |  |  | Solar |  | 05_14_74L1 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 668947 | 01906 | 5 |  |  | Solar |  | 05_01_216W5 | 01/30/2025 | 04/25/2025 | 14 | 11 | 3 | 04/28/2025 | 04/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 | 01/30/2025 | 7/3/2026 | Y | EXP | 365 | 09/05/2025 | 09/04/2025 | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 194766 | 01982 | 650 |  |  | Solar |  | 05_01_26W3 | 09/19/2018 | 10/16/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/20/2018 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 466552 | 01852 | 250 |  |  | Solar |  | 05_01_413L1 | 10/21/2022 | 11/07/2022 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2022 | 12/05/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 261017 | 01876 | 10 |  |  | Solar |  | 05_01_607W1 | 11/20/2019 | 11/26/2019 | 3 | 0 | 3 | 11/27/2019 | 11/27/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | HAVERHILL | 673224 | 01832 | 7.6 |  |  | Solar |  | 05_05_115W53 | 02/25/2025 | 03/14/2025 | 13 | 9 | 4 | 03/17/2025 | 03/17/2025 | 126 | 25 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford |  |  | Required Reviews
National Grid | CLINTON | 673544 | 01510 | 10 |  |  | Solar |  | 05_12_25W1 | 02/21/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/21/2025 | 6/7/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  | 1/5/2026 | Connected |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 526797 | 01501 | 15.2 |  |  | Solar |  | 05_12_51T2 | 05/16/2023 | 05/18/2023 | 2 | 0 | 2 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | SOUTHBRIDGE | 183612 | 01550 | 7.6 |  |  | Solar |  | 05_14_59L3 | 04/23/2018 | 04/23/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2019 | Connected |  | N | Millbury-Grafton |  |  | 100 Day Study
National Grid | GARDNER | 682711 | 01440 | 5.76 |  |  | Solar |  | 05_14_74L1 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N | Millbury-Grafton |  |  | 100 Day Study - Start Study
National Grid | FALL RIVER | 686255 | 02721 | 15.76 |  |  | Solar |  | 05_01_216W5 | 04/18/2025 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | 100 Day Study
National Grid | SAUGUS | 196917 | 01906 | 9.2 |  |  | Solar |  | 05_01_26W3 | 09/25/2018 | 10/11/2018 | 10 | 9 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2018 | 09/25/2018 | 3/8/2019 | Y | EXP | 147 | 12/25/2018 | 01/08/2019 | 14 | 0 | 14 |  |  | 3/4/2019 | Connected |  | N | Millbury-Grafton |  |  | 100 Day Study
National Grid | HAMILTON | 643826 | 01982 | 5.76 |  |  | Solar |  | 05_01_413L1 | 09/30/2024 | 10/11/2024 | 5 | 1 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 1/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 355755 | 01852 | 10 |  |  | Solar |  | 05_01_607W1 | 06/07/2021 | 06/15/2021 | 6 | 0 | 6 | 06/16/2021 | 06/16/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 673848 | 01876 | 4.93 |  |  | Solar |  | 05_05_115W53 | 02/24/2025 | 03/27/2025 | 4 | 2 | 2 | 03/28/2025 | 03/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/24/2025 | 8/29/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 10/10/2025 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement
National Grid | METHUEN | 686943 | 01844 | 3.8 |  |  | Solar |  | 05_12_25W1 | 04/22/2025 | 05/08/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Execute Group Study Agreement
National Grid | CLINTON | 566169 | 01510 | 0 |  |  | Solar |  | 05_12_51T2 | 10/25/2023 | 11/02/2023 | 6 | 3 | 3 | 11/03/2023 | 11/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 12/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | OXFORD | 666688 | 01540 | 3.8 |  |  | Solar |  | 05_14_3J7 | 01/20/2025 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 189478 | 01550 | 7.6 |  |  | Solar |  | 05_14_59L3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 | 07/02/2018 | 07/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | GARDNER | 689896 | 01440 | 11.5 |  |  | Solar |  | 05_14_74L1 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | FALL RIVER | 693561 | 02721 | 11.5 |  |  | Solar |  | 05_01_216W5 | 05/22/2025 | 06/04/2025 | 2 | 0 | 2 | 06/11/2025 | 06/11/2025 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 05/22/2025 | 9/2/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/3/2025 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | SAUGUS | 197089 | 01906 | 3.8 |  |  | Solar |  | 05_01_26W3 | 09/27/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | ESSEX | 661362 | 01929 | 5.76 |  |  | Solar |  | 05_01_413L1 | 12/18/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 450860 | 01852 | 5 |  |  | Solar |  | 05_01_607W1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 | 10/11/2022 | 9/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2023 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | TEWKSBURY | 684035 | 01876 | 7.6 |  |  | Solar |  | 05_05_115W53 | 04/14/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 650631 | 01844 | 7.6 |  |  | Solar |  | 05_12_25W2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/29/2024 | 1/7/2026 | Y | EXP | 365 | 04/15/2025 | 09/09/2025 | 148 | 0 | 148 |  |  |  | Completion Documents |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | CLINTON | 562855 | 01510 | 16.065 |  |  | Solar |  | 05_12_51T2 | 10/17/2023 | 10/31/2023 | 10 | 7 | 3 | 11/01/2023 | 11/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | AUBURN | 669223 | 01501 | 6 |  |  | Solar |  | 05_14_3J7 | 01/31/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Cape Ann |  |  | Pending
National Grid | SOUTHBRIDGE | 321076 | 01550 | 6.38 |  |  | Solar |  | 05_14_59L3 | 10/22/2020 | 10/23/2020 | 1 | 1 | 0 | 10/26/2020 | 10/26/2020 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 | 10/22/2020 | 10/22/2021 | Y | EXP | 365 | 03/19/2021 | 03/18/2021 | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 700558 | 01440 | 15.2 |  |  | Solar |  | 05_14_74L1 | 06/23/2025 | 07/25/2025 | 22 | 17 | 5 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N | Chelmsford/Westford |  |  | Required Reviews
National Grid | FALL RIVER | 598176 | 02721 | 11.5 |  |  | Solar |  | 05_01_216W6 | 03/20/2024 | 04/11/2024 | 16 | 13 | 3 | 04/12/2024 | 04/12/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | MELROSE | 258441 | 02176 | 10 |  |  | Solar |  | 05_01_26W3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/17/2019 | 3/4/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N | Lowell |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 695187 | 01982 | 15.2 |  |  | Solar |  | 05_01_413L1 | 06/13/2025 | 06/24/2025 | 5 | 2 | 3 | 06/25/2025 | 06/25/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Lowell |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 372586 | 01852 | 9.8 |  |  | Solar |  | 05_01_607W1 | 08/04/2021 | 08/05/2021 | 1 | 0 | 1 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/04/2021 | 11/24/2022 | Y | EXP | 365 | 10/15/2021 | 11/23/2021 | 40 | 4 | 36 |  |  | 12/1/2021 | Connected |  | Y | Hanover |  |  | Execute Group Study Agreement
National Grid | TEWKSBURY | 687844 | 01876 | 10.24 |  |  | Solar |  | 05_05_115W53 | 04/28/2025 | 05/28/2025 | 2 | 0 | 2 | 05/29/2025 | 05/29/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/28/2025 | 7/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | HAVERHILL | 726138 | 01832 | 17.2 |  |  | Solar |  | 05_12_25W2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | BOLTON | 574209 | 01740 | 490 |  |  | Solar |  | 05_12_51T2 | 12/15/2023 | 01/09/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2024 | 03/11/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | AUBURN | 700371 | 01501 | 11.02 |  |  | Solar |  | 05_14_3J7 | 06/23/2025 | 08/13/2025 | 5 | 3 | 2 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Chelmsford/Westford |  |  | Required Reviews
National Grid | SOUTHBRIDGE | 349329 | 01550 | 3.8 |  |  | Solar |  | 05_14_59L3 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | GARDNER | 713543 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L1 | 08/20/2025 | 09/10/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 659631 | 02721 | 27.55 |  |  | Solar |  | 05_01_216W6 | 12/16/2024 | 01/28/2025 | 28 | 26 | 2 | 01/29/2025 | 01/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y | Chelmsford/Westford |  |  | Required Reviews
National Grid | MELROSE | 286480 | 02176 | 7.6 |  |  | Solar |  | 05_01_26W3 | 05/26/2020 | 06/03/2020 | 5 | 0 | 5 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 739089 | 01982 | 20 |  |  | Solar |  | 05_01_413L1 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | LOWELL | 389904 | 01852 | 9.57 |  |  | Solar |  | 05_01_607W1 | 10/26/2021 | 12/16/2021 | 2 | 2 | 0 | 10/29/2021 | 10/29/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/26/2021 | 5/26/2023 | Y | EXP | 365 | 04/27/2022 | 05/04/2022 | 8 | 0 | 8 |  |  | 6/29/2022 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | TEWKSBURY | 696536 | 01876 | 7.6 |  |  | Solar |  | 05_05_115W54 | 06/05/2025 | 06/17/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | METHUEN | 174932 | 01844 | 278.4 |  |  | Solar |  | 05_12_25W2 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 08/29/2013 | 10/31/2014 | Y | EXP | 378 | 12/19/2014 | 02/12/2015 | 36 | 0 | 36 | 4/1/2015 | 4/1/2015 | 4/6/2015 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | BOLTON | 625514 | 01740 | 0 |  |  | Battery Add-On |  | 05_12_51T2 | 07/17/2024 | 10/11/2024 | 60 | 50 | 10 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 557014 | 01501 | 200 |  |  | Solar |  | 05_14_3L2 | 09/21/2023 | 10/06/2023 | 11 | 2 | 9 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/21/2023 | 7/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 396310 | 01550 | 0 |  |  | Other |  | 05_14_59L3 | 02/17/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2022 | 04/05/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 727180 | 01440 | 5.76 |  |  | Solar |  | 05_14_74L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | FALL RIVER | 714691 | 02724 | 25 |  |  | Solar |  | 05_01_216W6 | 08/28/2025 | 09/09/2025 | 6 | 4 | 2 | 09/10/2025 | 09/10/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y | Barre-Athol |  |  | Scoping Meeting
National Grid | SAUGUS | 337541 | 01906 | 9.8 |  |  | Solar |  | 05_01_26W3 | 01/19/2021 | 01/25/2021 | 3 | 0 | 3 | 01/26/2021 | 01/26/2021 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 3/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2021 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 175324 | 01982 | 256.2 |  |  | Solar |  | 05_01_413L1 | 11/07/2014 | 11/07/2014 | 6 | 0 | 6 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 3/31/2015 | N | EXP | 105 |  |  | 0 | 0 | 0 | 10/20/2015 | 10/20/2015 | 10/21/2015 | Connected |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 389245 | 01852 | 3.84 |  |  | Solar |  | 05_01_607W1 | 12/15/2021 | 01/07/2022 | 2 | 0 | 2 | 12/20/2021 | 12/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | ANDOVER | 418915 | 01876 | 15.2 |  |  | Solar |  | 05_05_115W54 | 03/21/2022 | 03/25/2022 | 4 | 3 | 1 | 03/28/2022 | 03/28/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | METHUEN | 178186 | 01844 | 15.2 |  |  | Solar |  | 05_12_25W2 | 04/13/2018 | 04/13/2018 | 6 | 0 | 6 | 04/25/2018 | 04/25/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | BOLTON | 641444 | 01740 | 8.775 |  |  | Solar |  | 05_12_51T2 | 09/19/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 | 10/22/2024 | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 10/30/2024 |  | 11/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 674259 | 01501 | 220 |  |  | Solar |  | 05_14_3L2 | 02/28/2025 | 03/14/2025 | 10 | 0 | 10 | 03/17/2025 | 03/17/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 | 02/28/2025 | 3/2/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 525204 | 01550 | 4.41 |  |  | Solar |  | 05_14_59L3 | 05/16/2023 | 05/17/2023 | 1 | 0 | 1 | 05/18/2023 | 05/18/2023 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 8/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | Y | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 665501 | 01440 | 999 |  |  | Solar |  | 05_14_74L2 | 01/29/2025 | 02/24/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/25/2025 | 03/25/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N | Millbury-Grafton |  |  | 100 Day Study
National Grid | FALL RIVER | 724889 | 02721 |  |  |  | Battery Add-On |  | 05_01_216W6 | 10/15/2025 | 10/24/2025 | 6 | 2 | 4 | 10/27/2025 | 10/27/2025 | 44 | 30 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N | MPL-East |  |  | Scoping Meeting
National Grid | SAUGUS | 450660 | 01906 | 19 |  |  | Solar |  | 05_01_26W3 | 08/10/2022 | 09/12/2022 | 22 | 22 | 0 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 | 12/07/2022 | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 3/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | ESSEX | 176176 | 01929 | 1000 |  |  | Solar |  | 05_01_413L1 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2015 | 07/02/2015 | 7/11/2016 | Y | STD | 201 | 08/04/2017 | 09/20/2017 | 32 | 0 | 32 | 10/16/2017 | 10/16/2017 | 10/13/2015 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | LOWELL | 395576 | 01852 | 20.355 |  |  | Solar |  | 05_01_607W1 | 11/17/2021 | 12/22/2021 | 2 | 0 | 2 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | TEWKSBURY | 439740 | 01876 | 15.2 |  |  | Solar |  | 05_05_115W54 | 06/23/2022 |  | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | METHUEN | 178740 | 01844 | 15.2 |  |  | Solar |  | 05_12_25W2 | 04/18/2018 | 04/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/24/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | BOLTON | 643245 | 01740 | 7.6 |  |  | Solar |  | 05_12_51T2 | 09/26/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 38 | 15 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 1/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | AUBURN | 734040 | 01501 | 16.53 |  |  | Solar |  | 05_14_3L2 | 11/14/2025 | 11/20/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | SOUTHBRIDGE | 585728 | 01550 | 0 |  |  | Solar |  | 05_14_59L3 | 01/26/2024 | 02/01/2024 | 5 | 3 | 2 | 02/02/2024 | 02/02/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 688247 | 01440 | 100 |  |  | Solar |  | 05_14_74L2 | 10/17/2025 |  | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 736348 | 02721 | 7.6 |  |  | Solar |  | 05_01_216W6 | 11/25/2025 | 12/10/2025 | 10 | 7 | 3 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-East |  |  | Scoping Meeting
National Grid | SAUGUS | 404298 | 01906 | 6 |  |  | Solar |  | 05_01_26W3 | 01/13/2022 | 01/18/2022 | 2 | 0 | 2 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/13/2022 | 7/13/2023 | Y | EXP | 365 | 05/27/2022 | 06/13/2022 | 18 | 0 | 18 |  |  | 7/26/2022 | Connected |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | ESSEX | 177030 | 01929 | 224 |  |  | Solar |  | 05_01_413L1 | 03/19/2017 | 03/19/2017 | 69 | 68 | 1 | 06/27/2017 | 06/27/2017 | 0 | 0 | 0 | 12/07/2017 | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 |  | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 3/30/2018 | N | EXP | 197 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/14/2018 | Connected |  | N | Millbury-Grafton |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 524121 | 01852 | 14.5 |  |  | Solar |  | 05_01_607W1 | 05/04/2023 | 06/07/2023 | 24 | 22 | 2 | 06/08/2023 | 06/08/2023 | 64 | 44 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | Y | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 649641 | 01876 | 6.72 |  |  | Solar |  | 05_05_115W54 | 10/25/2024 | 11/15/2024 | 12 | 7 | 5 | 11/18/2024 | 11/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 327874 | 01844 | 7.6 |  |  | Solar |  | 05_12_25W2 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 | 11/23/2020 | 9/10/2022 | Y | EXP | 365 | 04/22/2021 | 08/10/2021 | 110 | 0 | 110 |  |  | 9/24/2021 | Connected |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | HARVARD | 644917 | 01451 | 6 |  |  | Solar |  | 05_12_51T2 | 10/07/2024 | 10/28/2024 | 10 | 6 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/07/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 424685 | 01501 | 6.09 |  |  | Solar |  | 05_14_3L2 | 05/13/2022 | 05/16/2022 | 1 | 0 | 1 | 05/17/2022 | 05/17/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 05/13/2022 | 8/19/2024 | Y | EXP | 365 | 04/16/2023 | 05/03/2023 | 18 | 0 | 18 |  |  | 10/12/2023 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | SOUTHBRIDGE | 606299 | 01550 | 7.6 |  |  | Solar |  | 05_14_59L3 | 04/24/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 07/24/2024 | 02/26/2025 | 218 | 0 | 218 |  |  | 3/7/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | GARDNER | 722959 | 01440 | 3.8 |  |  | Solar |  | 05_14_74L2 | 10/01/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/01/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | FALL RIVER | 174686 | 02721 | 5.3 |  |  | Solar |  | 05_01_216W6 | 01/24/2011 | 01/24/2011 | 8 | 0 | 8 | 02/04/2011 | 02/04/2011 | 451 | 0 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | MELROSE | 403477 | 02176 | 9.57 |  |  | Solar |  | 05_01_26W3 | 08/01/2022 | 01/13/2022 | 21 | 21 | 0 | 08/31/2022 | 08/31/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2023 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | HAMILTON | 178353 | 01982 | 5 |  |  | Solar |  | 05_01_413L1 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/06/2018 | 03/06/2018 | 239 | 0 | 239 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 3/5/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/12/2018 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement - Awaiting Other Group Members
National Grid | TEWKSBURY | 558965 | 01876 | 11.5 |  |  | Solar |  | 05_01_607W1 | 01/11/2024 | 03/04/2024 | 35 | 31 | 4 | 03/05/2024 | 03/05/2024 | 24 | 22 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 01/11/2024 | 4/19/2025 | Y | EXP | 365 | 05/11/2024 | 05/15/2024 | 5 | 0 | 5 |  |  | 8/9/2024 | Connected |  | N | Hanover |  |  | Execute Group Study Agreement
National Grid | TEWKSBURY | 671800 | 01876 | 3.8 |  |  | Solar |  | 05_05_115W54 | 02/12/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N | Chelmsford/Westford |  |  | Required Reviews
National Grid | METHUEN | 475161 | 01844 | 15.2 |  |  | Solar |  | 05_12_25W2 | 11/07/2022 | 11/08/2022 | 2 | 1 | 1 | 11/09/2022 | 11/09/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | HARVARD | 652283 | 01451 | 10 |  |  | Solar |  | 05_12_51T2 | 11/14/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | MILLBURY | 583375 | 01527 | 10 |  |  | Solar |  | 05_14_3L2 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 57 | 45 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 01/26/2024 | 6/3/2025 | Y | EXP | 365 | 09/14/2024 | 11/04/2024 | 52 | 0 | 52 |  |  | 11/18/2024 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | SOUTHBRIDGE | 612327 | 01550 | 7.6 |  |  | Solar |  | 05_14_59L3 | 05/20/2024 | 06/03/2024 | 3 | 0 | 3 | 06/04/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 | 05/20/2024 | 7/25/2025 | Y | EXP | 365 | 08/29/2024 | 10/23/2024 | 56 | 0 | 56 |  |  | 12/4/2024 | Connected |  | N | Barre-Athol |  |  | Scoping Meeting
National Grid | GARDNER | 734586 | 01440 | 11.5 |  |  | Solar |  | 05_14_74L2 | 11/18/2025 | 11/19/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 174815 | 02724 | 995 |  |  | Solar |  | 05_01_216W6 | 07/31/2013 | 07/31/2013 | 7 | 0 | 7 | 08/12/2013 | 08/12/2013 | 0 | 0 | 0 | 01/14/2014 | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 3/14/2014 |  | 12/31/2013 | N | EXP | -73 |  |  | 0 | 0 | 0 | 12/24/2014 | 12/24/2014 | 12/30/2014 | Connected |  | N | MPL-Northwest |  |  | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 430569 | 01906 | 11.02 |  |  | Solar |  | 05_01_26W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 11/16/2023 | Y | EXP | 365 | 10/12/2022 | 11/14/2022 | 34 | 0 | 34 |  |  | 12/7/2022 | Connected |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 184817 | 01982 | 478 |  |  | Solar |  | 05_01_413L1 | 01/04/2019 | 01/08/2019 | 1 | 0 | 1 |  |  | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 533436 | 01852 | 0 |  |  | Battery Add-On |  | 05_01_607W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 90 | 25 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 689895 | 01876 | 7.6 |  |  | Solar |  | 05_05_115W55 | 05/06/2025 | 06/26/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/06/2025 | 10/10/2026 | Y | EXP | 365 | 01/06/2026 | 01/05/2026 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N | MPL-East |  |  | Scoping Meeting
National Grid | METHUEN | 608064 | 01844 | 0 |  |  | Battery Add-On |  | 05_12_25W2 | 05/09/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 05/09/2024 | 6/20/2025 | Y | EXP | 365 | 07/31/2024 | 12/05/2024 | 127 | 0 | 127 |  |  | 12/11/2024 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | BOLTON | 652513 | 01740 | 13.05 |  |  | Solar |  | 05_12_51T2 | 11/13/2024 | 12/05/2024 | 1 | 0 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 641313 | 01501 | 7.6 |  |  | Solar |  | 05_14_3L2 | 09/18/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/18/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 642192 | 01550 | 0 |  |  | Battery Add-On |  | 05_14_59L3 | 09/27/2024 | 10/02/2024 | 3 | 0 | 3 | 10/03/2024 | 10/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | GARDNER | 176004 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/19/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/25/2017 | 1/25/2017 | 1/25/2017 | Connected |  | N | Gardner-Winchendon |  |  | Scoping Meeting
National Grid | FALL RIVER | 175571 | 02724 | 6 |  |  | Solar |  | 05_01_216W6 | 10/10/2014 | 10/10/2014 | 10 | 7 | 3 | 10/28/2014 | 10/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 | 10/10/2014 | 4/22/2015 | Y | EXP | 153 | 03/11/2015 | 03/16/2015 | 3 | 0 | 3 | 3/12/2015 | 3/12/2015 | 6/1/2015 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | MELROSE | 433265 | 02176 | 150 |  |  | Solar |  | 05_01_26W3 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | HAMILTON | 193984 | 01982 | 72 |  |  | Solar |  | 05_01_413L1 | 10/23/2018 | 10/25/2018 | 178 | 28 | 150 | 12/14/2018 | 12/14/2018 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 555974 | 01852 | 10 |  |  | Solar |  | 05_01_607W1 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 | 09/26/2023 | 11/18/2024 | Y | EXP | 365 | 01/18/2024 | 01/23/2024 | 6 | 0 | 6 |  |  | 2/26/2024 | Connected |  | N | Brockton-North |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 741858 | 01876 | 7.6 |  |  | Solar |  | 05_05_115W55 | 12/22/2025 | 12/29/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N | Bridgewater |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 625229 | 01844 | 15.2 |  |  | Solar |  | 05_12_25W2 | 07/18/2024 | 07/25/2024 | 5 | 3 | 2 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | HARVARD | 669106 | 01451 | 10 |  |  | Solar |  | 05_12_51T2 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N | Spencer-Rutland |  |  | Scoping Meeting
National Grid | AUBURN | 647155 | 01501 | 6 |  |  | Solar |  | 05_14_3L2 | 10/24/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N | MPL-East |  |  | Scoping Meeting
National Grid | SOUTHBRIDGE | 647522 | 01550 | 7.6 |  |  | Solar |  | 05_14_59L3 | 10/22/2024 | 11/19/2024 | 7 | 5 | 2 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 177002 | 01440 | 195 |  |  | Solar |  | 05_14_74L2 | 07/21/2016 | 07/21/2016 | 0 | 0 | 0 | 07/22/2016 | 07/22/2016 | 389 | 6 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2016 |  | 2/28/2018 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Millbury-Grafton |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 177884 | 02724 | 38 |  |  | Solar |  | 05_01_216W6 | 10/19/2017 | 10/19/2017 | 10 | 10 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/25/2018 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 476717 | 01906 | 160 |  |  | Solar |  | 05_01_26W3 | 12/13/2022 | 02/20/2023 | 45 | 38 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 12/13/2022 | 3/9/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 196406 | 01915 | 66.6 |  |  | Solar |  | 05_01_413L1 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 5/1/2020 | N | EXP | 379 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hopedale-West |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 564080 | 01852 | 0 |  |  | Battery Add-On |  | 05_01_607W1 | 10/19/2023 |  | 222 | 222 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 175360 | 01876 | 20 |  |  | Solar |  | 05_05_115W55 | 11/12/2014 | 11/12/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Barre-Athol |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 628432 | 01844 | 23 |  |  | Solar |  | 05_12_25W2 | 07/29/2024 | 07/31/2024 | 2 | 0 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N | Spencer-Rutland |  |  | On Hold Behind Preceding Group Study
National Grid | CLINTON | 678202 | 01510 | 5.76 |  |  | Solar |  | 05_12_51T2 | 03/17/2025 | 03/24/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 03/17/2025 | 5/29/2026 | Y | EXP | 365 | 08/19/2025 | 11/05/2025 | 79 | 0 | 79 |  |  | 11/14/2025 | Connected |  | Y | MPL-East |  |  | On Hold Behind Preceding Group Study
National Grid | AUBURN | 649912 | 01501 | 3.8 |  |  | Solar |  | 05_14_3L2 | 11/06/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/06/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N | MPL-East |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 648085 | 01550 | 3 |  |  | Solar |  | 05_14_59L3 | 10/18/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N | MPL-East |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 177887 | 01440 | 300 |  |  | Natural Gas |  | 05_14_74L2 | 04/11/2017 | 04/11/2017 | 40 | 40 | 0 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 4/17/2018 | N | EXP | 284 |  |  | 0 | 0 | 0 | 4/5/2018 | 4/5/2018 | 4/5/2018 | Connected |  | N | MPL-East |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 188838 | 02724 | 1560 |  |  | Solar |  | 05_01_216W6 | 07/16/2018 | 07/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/20/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | MPL-East |  |  | On Hold Behind Preceding Group Study
National Grid | MELROSE | 520551 | 02176 | 0 |  |  | Solar |  | 05_01_26W3 | 04/20/2023 | 04/27/2023 | 5 | 3 | 2 | 04/28/2023 | 04/28/2023 | 231 | 210 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Spencer-Rutland |  |  | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 293474 | 01915 | 7.92 |  |  | Solar |  | 05_01_413L1 | 06/17/2020 | 07/09/2020 | 16 | 12 | 4 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 593301 | 01852 | 7.6 |  |  | Solar |  | 05_01_607W1 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 07/25/2024 | 07/29/2024 | 5 | 0 | 5 |  |  | 8/20/2024 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 177153 | 01876 | 60 |  |  | Solar |  | 05_05_115W55 | 08/12/2016 | 08/12/2016 | 1 | 1 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/17/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/12/2016 | 12/14/2016 | Connected |  | N | Attleboro |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 644449 | 01844 | 3.8 |  |  | Solar |  | 05_12_25W2 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Hanover |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | BOLTON | 689316 | 01740 | 15.2 |  |  | Solar |  | 05_12_51T2 | 05/02/2025 | 05/22/2025 | 14 | 11 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N | Hopedale-East |  |  | Execute Group Study Agreement - Pending Customer Decision
National Grid | AUBURN | 651647 | 01501 | 7.6 |  |  | Solar |  | 05_14_3L2 | 11/13/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/13/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 651393 | 01550 | 3.8 |  |  | Solar |  | 05_14_59L3 | 11/22/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N | Chelmsford/Westford |  |  | Required Reviews
National Grid | GARDNER | 177993 | 01440 | 15.2 |  |  | Solar |  | 05_14_74L2 | 10/24/2017 | 10/24/2017 | 14 | 14 | 0 | 11/27/2017 | 11/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/1/2018 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N | Chelmsford/Westford |  |  | Required Reviews - Screening Review Hold
National Grid | FALL RIVER | 196197 | 02724 | 15.2 |  |  | Solar |  | 05_01_216W6 | 09/25/2018 | 10/04/2018 | 12 | 11 | 1 | 10/11/2018 | 10/11/2018 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N | Chelmsford/Westford |  |  | Required Reviews
National Grid | MELROSE | 520407 | 02176 | 15 |  |  | Solar |  | 05_01_26W3 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 8/18/2025 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Chelmsford/Westford |  |  | Required Reviews
National Grid | HAMILTON | 419438 | 01982 | 7.6 |  |  | Solar |  | 05_01_413L1 | 03/23/2022 | 05/05/2022 | 31 | 30 | 1 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 593486 | 01852 | 7.6 |  |  | Solar |  | 05_01_607W1 | 03/18/2024 | 03/21/2024 | 3 | 0 | 3 | 03/22/2024 | 03/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/18/2024 | 5/9/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N | Spencer-Rutland |  |  | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 549206 | 01876 | 25 |  |  | Solar |  | 05_05_115W55 | 09/12/2023 | 09/16/2023 | 4 | 2 | 2 | 09/18/2023 | 09/18/2023 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N | Leominster |  |  | On Hold Behind Preceding Group Study
National Grid | METHUEN | 646179 | 01844 | 7.6 |  |  | Solar |  | 05_12_25W2 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/18/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N | Millbury-Grafton |  |  | On Hold Behind Preceding Group Study
National Grid | BOLTON | 691103 | 01740 | 15.2 |  |  | Solar |  | 05_12_51T2 | 06/02/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N | Ayer-Clinton |  |  | Required Reviews
National Grid | AUBURN | 661000 | 01501 | 8.74 |  |  | Solar |  | 05_14_3L2 | 12/18/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/18/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | SOUTHBRIDGE | 653564 | 01550 | 5.76 |  |  | Solar |  | 05_14_59L3 | 11/15/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | GARDNER | 184808 | 01440 | 25.2 |  |  | Solar |  | 05_14_74L2 | 05/08/2018 | 05/08/2018 | 6 | 0 | 6 | 05/17/2018 | 05/17/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 212493 | 02724 | 0 |  |  | Solar |  | 05_01_216W6 | 03/05/2019 | 03/12/2019 | 4 | 0 | 4 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 03/05/2019 | 3/6/2020 | Y | EXP | 365 | 09/05/2019 | 09/11/2019 | 6 | 0 | 6 |  |  | 2/4/2020 | Connected |  | N | Marlborough |  |  | On Hold Behind Preceding Group Study
National Grid | MELROSE | 544706 | 02176 | 10 |  |  | Solar |  | 05_01_26W3 | 08/08/2023 | 08/10/2023 | 2 | 0 | 2 | 08/11/2023 | 08/11/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2023 | 08/08/2023 | 10/10/2024 | Y | EXP | 365 | 03/05/2024 | 03/04/2024 | 0 | 0 | 0 |  |  | 3/26/2024 | Connected |  | N | Webster-Southbridge-Charlton |  |  | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 482280 | 01982 | 18.816 |  |  | Solar |  | 05_01_413L1 | 01/03/2023 | 01/25/2023 | 15 | 14 | 1 | 01/26/2023 | 01/26/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N | Hopedale-East |  |  | On Hold Behind Preceding Group Study
National Grid | LOWELL | 605406 | 01852 | 3.8 |  |  | Solar |  | 05_01_607W1 | 04/19/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y | MPL-East |  |  | Scoping Meeting
National Grid | TEWKSBURY | 550284 | 01876 | 10 |  |  | Solar |  | 05_05_115W55 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/25/2023 | 11/29/2024 | Y | EXP | 365 | 01/10/2024 | 02/28/2024 | 50 | 0 | 50 |  |  | 5/30/2024 | Connected |  | N | Ayer-Clinton |  |  | Required Reviews - Screening Review
National Grid | METHUEN | 651937 | 01844 | 6.84 |  |  | Solar |  | 05_12_25W2 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | Y
National Grid | HARVARD | 700744 | 01451 | 0 |  |  | Solar |  | 05_12_51T2 | 06/24/2025 | 06/30/2025 | 4 | 0 | 4 | 07/01/2025 | 07/01/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 8/15/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 11/21/2025 | Connected |  | N
National Grid | AUBURN | 666669 | 01501 | 7.6 |  |  | Solar |  | 05_14_3L2 | 01/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/20/2025 | 4/14/2026 | Y | EXP | 365 | 07/24/2025 |  | 162 | 0 | 162 |  |  | 12/4/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 659218 | 01550 | 9.6 |  |  | Solar |  | 05_14_59L3 | 12/09/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/09/2024 | 4/14/2026 | Y | EXP | 365 | 05/23/2025 | 05/22/2025 | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | GARDNER | 222991 | 01440 | 153.3 |  |  | Solar |  | 05_14_74L2 | 04/26/2019 | 05/16/2019 | 14 | 9 | 5 | 05/17/2019 | 05/17/2019 | 18 | 4 | 14 | 08/13/2019 | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP | 734 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 243391 | 02724 | 0 |  |  | Solar |  | 05_01_216W6 | 07/17/2019 | 07/18/2019 | 0 | 0 | 0 | 07/19/2019 | 07/19/2019 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 | 07/17/2019 | 3/4/2020 | Y | EXP | 211 | 11/14/2019 | 11/26/2019 | 12 | 0 | 12 |  |  | 1/28/2020 | Connected |  | N
National Grid | MELROSE | 553735 | 02176 | 6.912 |  |  | Solar |  | 05_01_26W3 | 09/25/2023 | 10/12/2023 | 12 | 5 | 7 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/25/2023 | 2/25/2025 | Y | EXP | 365 | 05/16/2024 | 06/11/2024 | 27 | 0 | 27 |  |  | 6/20/2024 | Connected |  | N
National Grid | HAMILTON | 573990 | 01982 | 6 |  |  | Solar |  | 05_01_413L1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 642870 | 01852 | 7.83 |  |  | Solar |  | 05_01_607W1 | 09/25/2024 | 11/05/2024 | 13 | 8 | 5 | 11/06/2024 | 11/06/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/25/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | TEWKSBURY | 582671 | 01876 | 1.74 |  |  | Solar |  | 05_05_115W55 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | METHUEN | 662178 | 01844 | 12.92 |  |  | Solar |  | 05_12_25W2 | 12/23/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2025 | Connected |  | N
National Grid | BOLTON | 708571 | 01740 | 9.86 |  |  | Solar |  | 05_12_51T2 | 07/30/2025 | 09/15/2025 | 32 | 29 | 3 | 09/16/2025 | 09/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | AUBURN | 679992 | 01501 | 11.52 |  |  | Solar |  | 05_14_3L2 | 03/24/2025 | 04/11/2025 | 10 | 6 | 4 | 04/30/2025 | 04/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 664658 | 01550 | 6.84 |  |  | Solar |  | 05_14_59L3 | 01/09/2025 | 01/31/2025 | 7 | 2 | 5 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 4/10/2026 | Y | EXP | 365 | 06/07/2025 | 06/06/2025 | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | GARDNER | 327655 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 12/08/2020 | 12/09/2020 | 0 | 0 | 0 | 12/10/2020 | 12/10/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 12/08/2020 |  | Y | EXP | 365 | 05/05/2021 | 06/18/2021 | 44 | 0 | 44 |  |  | 8/24/2021 | Connected |  | N
National Grid | FALL RIVER | 248297 | 02724 | 0 |  |  | Solar |  | 05_01_216W6 | 08/12/2019 | 08/21/2019 | 7 | 7 | 0 | 08/22/2019 | 08/22/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2019 |  | 11/22/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 10/22/2019 | Connected |  | N
National Grid | SAUGUS | 570140 | 01906 | 13.325 |  |  | Solar |  | 05_01_26W3 | 12/04/2023 | 12/07/2023 | 3 | 0 | 3 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/04/2023 | 3/12/2025 | Y | EXP | 365 | 04/16/2024 | 07/12/2024 | 88 | 0 | 88 |  |  | 7/22/2024 | Connected |  | N
National Grid | WENHAM | 579815 | 01984 | 7.25 |  |  | Solar |  | 05_01_413L1 | 01/05/2024 | 01/12/2024 | 5 | 3 | 2 | 01/16/2024 | 01/16/2024 | 170 | 25 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 651319 | 01852 | 5.76 |  |  | Solar |  | 05_01_607W1 | 11/12/2024 | 01/13/2025 | 22 | 17 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/12/2024 | 3/14/2026 | Y | EXP | 365 | 06/11/2025 | 10/04/2025 | 116 | 0 | 116 |  |  | 11/24/2025 | Connected |  | N
National Grid | TEWKSBURY | 627842 | 01876 | 3.8 |  |  | Solar |  | 05_05_115W55 | 07/25/2024 | 08/05/2024 | 6 | 5 | 1 | 08/06/2024 | 08/06/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 07/25/2024 | 9/11/2025 | Y | EXP | 365 | 09/25/2024 | 10/11/2024 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 672929 | 01844 | 7.6 |  |  | Solar |  | 05_12_25W2 | 02/19/2025 | 03/24/2025 | 5 | 0 | 5 | 03/25/2025 | 03/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | BOLTON | 714207 | 01740 | 15.04 |  |  | Solar |  | 05_12_51T2 | 08/22/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | AUBURN | 707901 | 01501 | 3.8 |  |  | Solar |  | 05_14_3L2 | 07/28/2025 | 08/29/2025 | 5 | 0 | 5 | 09/02/2025 | 09/02/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 668537 | 01550 | 5.76 |  |  | Solar |  | 05_14_59L3 | 01/29/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 348265 | 01440 | 499.9 |  |  | Solar |  | 05_14_74L2 | 06/10/2021 |  | 315 | 315 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 251196 | 02724 | 7.6 |  |  | Solar |  | 05_01_216W6 | 08/28/2019 | 10/14/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 08/28/2019 | 10/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | SAUGUS | 588492 | 01906 | 9.135 |  |  | Solar |  | 05_01_26W3 | 02/23/2024 | 03/01/2024 | 5 | 1 | 4 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 4/18/2025 | Y | EXP | 365 | 05/02/2024 | 07/15/2024 | 75 | 0 | 75 |  |  | 8/23/2024 | Connected |  | N
National Grid | BEVERLY | 585346 | 01915 | 8.12 |  |  | Solar |  | 05_01_413L1 | 03/15/2024 | 03/20/2024 | 3 | 0 | 3 | 03/21/2024 | 03/21/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 03/15/2024 | 4/23/2025 | Y | EXP | 365 | 07/17/2024 | 08/13/2024 | 28 | 0 | 28 |  |  | 8/31/2024 | Connected |  | N
National Grid | LOWELL | 651317 | 01852 | 3.8 |  |  | Solar |  | 05_01_607W1 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | TEWKSBURY | 630792 | 01876 | 5.76 |  |  | Solar |  | 05_05_115W55 | 08/07/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/07/2024 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 10/07/2024 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 673521 | 01844 | 5.76 |  |  | Solar |  | 05_12_25W2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 703588 | 01510 | 0 |  |  | Solar |  | 05_12_51T3 | 07/08/2025 | 07/14/2025 | 3 | 1 | 2 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 710001 | 01501 | 5.933 |  |  | Solar |  | 05_14_3L2 | 08/06/2025 | 08/26/2025 | 3 | 0 | 3 | 09/03/2025 | 09/03/2025 | 62 | 47 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 671372 | 01550 | 10 |  |  | Solar |  | 05_14_59L3 | 02/11/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | GARDNER | 348029 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 05/04/2021 | 2/28/2023 | Y | EXP | 365 | 11/25/2021 | 01/24/2022 | 61 | 0 | 61 |  |  | 3/9/2022 | Connected |  | N
National Grid | FALL RIVER | 263665 | 02724 | 0 |  |  | Solar |  | 05_01_216W6 | 11/04/2019 | 11/08/2019 | 3 | 0 | 3 | 11/12/2019 | 11/12/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 | 11/04/2019 | 11/4/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | SAUGUS | 614949 | 01906 | 10 |  |  | Solar |  | 05_01_26W3 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/04/2024 | 7/25/2025 | Y | EXP | 365 | 09/18/2024 | 10/21/2024 | 34 | 0 | 34 |  |  | 10/24/2024 | Connected |  | N
National Grid | ROCKPORT | 657508 | 01966 | 9.88 |  |  | Solar |  | 05_01_413L1 | 11/27/2024 | 12/29/2024 | 12 | 8 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 659940 | 01852 | 7.6 |  |  | Solar |  | 05_01_607W1 | 12/11/2024 | 12/18/2024 | 2 | 0 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/11/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | TEWKSBURY | 633673 | 01876 | 9.88 |  |  | Solar |  | 05_05_115W55 | 08/19/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 26 | 11 | 15 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 12/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 681135 | 01844 | 17.1 |  |  | Solar |  | 05_12_25W2 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | BOLTON | 738933 | 01740 | 11.52 |  |  | Solar |  | 05_12_51T3 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 642855 | 01540 | 120 |  |  | Solar |  | 05_14_3L4 | 09/30/2024 | 01/30/2025 | 81 | 73 | 8 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 09/30/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 684665 | 01550 | 23 |  |  | Solar |  | 05_14_59L3 | 04/11/2025 | 05/01/2025 | 13 | 10 | 3 | 05/02/2025 | 05/02/2025 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | Y
National Grid | GARDNER | 361148 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 07/04/2021 | 07/07/2021 | 2 | 0 | 2 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/04/2021 | 3/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2022 | Connected |  | Y
National Grid | FALL RIVER | 289076 | 02724 | 7.68 |  |  | Solar |  | 05_01_216W6 | 04/23/2020 | 04/27/2020 | 1 | 0 | 1 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/23/2020 | 8/18/2022 | Y | EXP | 759 | 12/02/2020 | 12/11/2020 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 647810 | 02176 | 10 |  |  | Solar |  | 05_01_26W3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/18/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | GLOUCESTER | 663621 | 01930 | 10 |  |  | Solar |  | 05_01_413L1 | 01/03/2025 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | LOWELL | 670136 | 01852 | 5.76 |  |  | Solar |  | 05_01_607W1 | 02/05/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | TEWKSBURY | 657557 | 01876 | 6 |  |  | Solar |  | 05_05_115W55 | 11/28/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | METHUEN | 685291 | 01844 | 15.2 |  |  | Solar |  | 05_12_25W2 | 04/21/2025 | 05/12/2025 | 14 | 10 | 4 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | HARVARD | 175636 | 01451 | 45 |  |  | Solar |  | 05_12_51T3 | 10/19/2014 | 10/19/2014 | 6 | 2 | 4 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 1/15/2015 | 1/15/2015 | 2/13/2015 | Connected |  | N
National Grid | OXFORD | 659689 | 01540 | 7.6 |  |  | Solar |  | 05_14_3L4 | 12/10/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 710883 | 01550 | 9.92 |  |  | Solar |  | 05_14_59L3 | 08/09/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | GARDNER | 365469 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 07/13/2021 | 07/16/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 | 07/13/2021 | 8/16/2024 | Y | EXP | 365 | 01/18/2022 | 02/22/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 293500 | 02724 | 200 |  |  | Solar |  | 05_01_216W6 | 05/27/2020 | 06/16/2020 | 14 | 12 | 2 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 650772 | 02176 | 10 |  |  | Solar |  | 05_01_26W3 | 10/30/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | GLOUCESTER | 663838 | 01930 | 3.8 |  |  | Solar |  | 05_01_413L1 | 01/06/2025 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 686443 | 01852 | 15.2 |  |  | Solar |  | 05_01_607W1 | 04/21/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 682467 | 01876 | 6.08 |  |  | Solar |  | 05_05_115W55 | 04/04/2025 | 04/28/2025 | 0 | 0 | 0 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | METHUEN | 689325 | 01844 | 20 |  |  | Solar |  | 05_12_25W2 | 05/06/2025 | 05/16/2025 | 7 | 2 | 5 | 05/19/2025 | 05/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | HARVARD | 175788 | 01451 | 200 |  |  | Solar |  | 05_12_51T3 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/17/2015 | 9/23/2016 | Y | EXP | 366 |  |  | 0 | 0 | 0 | 4/15/2016 | 4/15/2016 | 5/3/2016 | Connected |  | N
National Grid | AUBURN | 679179 | 01501 | 250 |  |  | Solar |  | 05_14_3L4 | 04/14/2025 | 05/19/2025 | 24 | 14 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SOUTHBRIDGE | 178363 | 01550 | 4920 |  |  | Solar |  | 05_14_59L4 | 03/30/2018 | 03/30/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 04/18/2019 | 260 | 9 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 392129 | 01440 | 7.6 |  |  | Solar |  | 05_14_74L2 | 10/29/2021 | 11/09/2021 | 5 | 5 | 0 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2023 | Connected |  | N
National Grid | FALL RIVER | 295570 | 02724 | 0 |  |  | Solar |  | 05_01_216W6 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/26/2020 | 10/25/2022 | Y | EXP | 365 | 04/07/2021 | 04/28/2021 | 21 | 0 | 21 |  |  | 7/27/2022 | Connected |  | N
National Grid | SAUGUS | 674775 | 01906 | 5.76 |  |  | Solar |  | 05_01_26W3 | 02/27/2025 | 03/18/2025 | 2 | 0 | 2 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/27/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 10/27/2025 | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | GLOUCESTER | 673133 | 01930 | 10 |  |  | Solar |  | 05_01_413L1 | 02/21/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/21/2025 | 4/11/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | LOWELL | 657316 | 01852 | 160 |  |  | Solar |  | 05_01_607W2 | 12/03/2024 | 12/20/2024 | 14 | 9 | 5 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ANDOVER | 174478 | 01810 | 164 |  |  | Solar |  | 05_12_25W3 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 6/27/2012 | Connected |  | N
National Grid | METHUEN | 176028 | 01844 | 30.25 |  |  | Solar |  | 05_12_51T3 | 06/16/2015 | 06/16/2015 | 4 | 4 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/21/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | BOLTON | 387537 | 01740 | 18.148 |  |  | Solar |  | 05_14_3L4 | 10/12/2021 | 01/07/2022 | 6 | 0 | 6 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | MILLBURY | 724788 | 01527 | 5.76 |  |  | Solar |  | 05_14_59L5 | 10/08/2025 | 10/22/2025 | 9 | 8 | 1 | 10/23/2025 | 10/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 405990 | 01550 | 0 |  |  | Battery Add-On |  | 05_14_74L2 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/14/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 298017 | 01440 | 10 |  |  | Solar |  | 05_01_216W6 | 06/24/2020 | 06/29/2020 | 2 | 0 | 2 | 06/30/2020 | 06/30/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2020 | Connected |  | N
National Grid | FALL RIVER | 707156 | 02724 | 11.31 |  |  | Solar |  | 05_01_26W3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | SAUGUS | 686535 | 01906 | 20 |  |  | Solar |  | 05_01_413L1 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 708125 | 01930 | 15.58 |  |  | Solar |  | 05_01_607W2 | 07/29/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 721391 | 01852 | 11.5 |  |  | Solar |  | 05_05_115W55 | 09/23/2025 | 10/08/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 177207 | 01876 | 259.8 |  |  | Solar |  | 05_12_25W3 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176270 | 01844 | 17.42 |  |  | Solar |  | 05_12_51T3 | 02/18/2015 | 02/18/2015 | 4 | 0 | 4 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/30/2015 | Connected |  | N
National Grid | HARVARD | 422062 | 01451 | 0 |  |  | Battery Add-On |  | 05_14_3L4 | 10/05/2022 | 06/22/2023 | 176 | 166 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 07/18/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 175357 | 01501 | 30 |  |  | Solar |  | 05_14_59L5 | 09/08/2014 | 09/08/2014 | 17 | 14 | 3 | 10/02/2014 | 10/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/30/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 8/20/2015 | Connected |  | N
National Grid | SOUTHBRIDGE | 414167 | 01550 | 10 |  |  | Solar |  | 05_14_74L2 | 03/22/2022 |  | 328 | 156 | 172 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 311915 | 01440 | 14.5 |  |  | Solar |  | 05_01_216W6 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 722655 | 02724 | 10 |  |  | Solar |  | 05_01_26W4 | 09/29/2025 | 10/02/2025 | 3 | 0 | 3 | 10/03/2025 | 10/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | SAUGUS | 688107 | 01906 | 15.2 |  |  | Solar |  | 05_01_413L1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 174639 | 01930 | 60 |  |  | Solar |  | 05_01_607W2 | 05/23/2013 | 05/23/2013 | 7 | 0 | 7 | 06/05/2013 | 06/05/2013 | 1121 | 0 | 1121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2013 |  | 10/14/2020 | N | EXP | 1745 |  |  | 0 | 0 | 0 | 3/3/2015 | 3/3/2015 | 10/14/2020 | Connected |  | N
National Grid | LOWELL | 562342 | 01852 | 4990 |  |  | Solar |  | 05_05_11W81 | 12/05/2023 | 01/19/2024 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 03/28/2024 | 48 | 30 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 12/05/2023 | 11/1/2026 | Y | STD | 406 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | TEWKSBURY | 178123 | 01876 | 300 |  |  | Natural Gas |  | 05_12_25W3 | 05/12/2017 | 05/12/2017 | 22 | 19 | 3 | 06/14/2017 | 06/14/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2017 |  | 9/7/2018 | N | EXP | 423 |  |  | 0 | 0 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | METHUEN | 176530 | 01844 | 108 |  |  | Solar |  | 05_12_51T3 | 12/16/2015 | 12/16/2015 | 0 | 0 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/22/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | BOLTON | 500890 | 01740 | 100 |  |  | Solar |  | 05_14_3L4 | 02/24/2023 | 04/07/2023 | 30 | 21 | 9 | 04/10/2023 | 04/10/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 | 02/24/2023 | 1/27/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 175492 | 01501 | 1800 |  |  | Solar |  | 05_14_59L5 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/03/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 | 07/25/2014 | 3/1/2016 | Y | STD | 354 | 10/28/2015 | 07/13/2017 | 424 | 0 | 424 | 5/24/2017 | 5/24/2017 | 6/26/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 529105 | 01550 | 3.8 |  |  | Solar |  | 05_14_74L2 | 06/21/2023 | 06/26/2023 | 3 | 0 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 336027 | 01440 | 200 |  |  | Solar |  | 05_01_216W6 | 01/11/2021 | 12/07/2021 | 9 | 1 | 8 | 02/03/2021 | 02/03/2021 | 74 | 51 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | SWANSEA | 347070 | 02777 | 26 |  |  | Solar |  | 05_01_27W1 | 03/31/2022 | 04/11/2022 | 7 | 0 | 7 | 04/12/2022 | 04/12/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/11/2026 | N | EXP | 10 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 197148 | 01906 | 996 |  |  | Solar |  | 05_01_413L2 | 10/04/2018 | 11/02/2018 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2018 | 12/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2020 | 10/04/2018 | 3/7/2026 | Y | STD | 476 | 12/23/2025 |  | 10 | 0 | 10 |  |  |  | Construction |  | N
National Grid | GLOUCESTER | 178322 | 01930 | 2510 |  |  | Solar |  | 05_01_607W2 | 03/29/2018 | 04/03/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/25/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 693170 | 01852 | 5.76 |  |  | Solar |  | 05_05_11W81 | 06/02/2025 | 07/15/2025 | 7 | 4 | 3 | 08/06/2025 | 08/06/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 204173 | 01810 | 259.8 |  |  | Solar |  | 05_12_25W3 | 12/18/2018 | 01/17/2019 | 19 | 12 | 7 | 01/18/2019 | 01/18/2019 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 177374 | 01844 | 345 |  |  | Solar |  | 05_12_51T3 | 09/08/2016 | 09/08/2016 | 2 | 2 | 0 | 09/12/2016 | 09/12/2016 | 361 | 2 | 359 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 6/29/2018 | N | EXP | 640 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 556411 | 01451 | 250 |  |  | Solar |  | 05_14_3L4 | 12/01/2023 | 12/26/2023 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175822 | 01604 | 120 |  |  | Solar |  | 05_14_59L5 | 08/03/2015 | 08/03/2015 | 10 | 10 | 0 | 08/17/2015 | 08/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 |  | 2/15/2016 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/11/2016 | 2/11/2016 | 2/17/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 571180 | 01550 | 10 |  |  | Solar |  | 05_14_74L2 | 12/08/2023 | 12/13/2023 | 3 | 1 | 2 | 12/14/2023 | 12/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 356319 | 01452 | 9.28 |  |  | Solar |  | 05_01_216W6 | 05/05/2021 | 05/11/2021 | 4 | 4 | 0 | 05/12/2021 | 05/12/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | SWANSEA | 661842 | 02777 | 3.8 |  |  | Solar |  | 05_01_27W1 | 01/06/2025 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/06/2025 | 4/8/2026 | Y | EXP | 365 | 06/14/2025 |  | 202 | 0 | 202 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 406202 | 01906 | 249 |  |  | Solar |  | 05_01_413L2 | 01/14/2022 | 03/03/2022 | 32 | 24 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 01/14/2022 | 3/8/2026 | Y | STD | 224 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 192422 | 01930 | 100 |  |  | Solar |  | 05_01_607W2 | 08/01/2018 | 08/20/2018 | 11 | 0 | 11 | 08/21/2018 | 08/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 1/7/2020 | N | EXP | 475 | 11/13/2019 | 11/12/2019 | 0 | 0 | 0 |  |  | 1/7/2020 | Connected |  | N
National Grid | LOWELL | 730560 | 01852 | 23 |  |  | Solar |  | 05_05_11W81 | 10/31/2025 | 11/04/2025 | 2 | 0 | 2 | 11/05/2025 | 11/05/2025 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TEWKSBURY | 253386 | 01876 | 262.5 |  |  | Natural Gas |  | 05_12_25W3 | 09/24/2019 | 11/04/2019 | 27 | 24 | 3 | 11/05/2019 | 11/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177959 | 01844 | 20 |  |  | Solar |  | 05_12_51T3 | 10/24/2017 | 10/24/2017 | 2 | 0 | 2 | 11/06/2017 | 11/06/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/31/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | BOLTON | 551159 | 01740 | 6 |  |  | Solar |  | 05_14_3L4 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | WORCESTER | 176048 | 01604 | 300 |  |  | Solar |  | 05_14_59L5 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 646050 | 01566 | 6 |  |  | Solar |  | 05_14_74L2 | 10/09/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/09/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | GARDNER | 366741 | 01440 | 7.6 |  |  | Solar |  | 05_01_216W6 | 06/29/2021 | 06/30/2021 | 1 | 0 | 1 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 10/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2022 | Connected |  | N
National Grid | SWANSEA | 665454 | 02777 | 60 |  |  | Solar |  | 05_01_27W1 | 02/10/2025 | 03/26/2025 | 31 | 22 | 9 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 4/10/2026 | N | EXP | 120 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 419334 | 01906 | 240 |  |  | Solar |  | 05_01_413L2 | 05/26/2022 | 06/13/2022 | 11 | 6 | 5 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 05/26/2022 | 4/10/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 482643 | 01930 | 17.4 |  |  | Solar |  | 05_01_607W2 | 02/06/2023 | 03/24/2023 | 33 | 32 | 1 | 03/27/2023 | 03/27/2023 | 72 | 52 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 174269 | 01852 | 300 |  |  | Solar |  | 05_05_11W81 | 12/19/2011 | 12/19/2011 | 30 | 0 | 30 | 02/02/2012 | 02/02/2012 | 486 | 0 | 486 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 |  | 6/1/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 302630 | 01876 | 262.5 |  |  | Natural Gas |  | 05_12_25W3 | 08/05/2020 | 09/30/2020 | 39 | 28 | 11 | 10/01/2020 | 10/01/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2020 |  | 2/21/2022 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | N
National Grid | METHUEN | 186691 | 01844 | 6 |  |  | Solar |  | 05_12_51T3 | 06/15/2018 | 06/15/2018 | 9 | 5 | 4 | 06/29/2018 | 06/29/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 5/30/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/16/2018 | Connected |  | N
National Grid | BOLTON | 595183 | 01740 | 3.8 |  |  | Solar |  | 05_14_3L4 | 03/13/2024 | 03/14/2024 | 1 | 0 | 1 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 03/13/2024 | 4/1/2025 | Y | EXP | 365 | 05/07/2024 | 08/08/2024 | 94 | 0 | 94 |  |  | 9/16/2024 | Connected |  | N
National Grid | WORCESTER | 176478 | 01604 | 133.2 |  |  | Solar |  | 05_14_59L5 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 428 | 0 | 428 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 |  | 2/28/2018 | N | EXP | 617 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 648151 | 01566 | 5.76 |  |  | Solar |  | 05_14_74L2 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 367483 | 01440 | 0 |  |  | Solar |  | 05_01_216W6 | 07/02/2021 | 07/06/2021 | 1 | 0 | 1 | 07/07/2021 | 07/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2022 | Connected |  | N
National Grid | SWANSEA | 710806 | 02777 | 7.22 |  |  | Solar |  | 05_01_27W1 | 08/29/2025 | 10/13/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SAUGUS | 431376 | 01906 | 500 |  |  | Solar |  | 05_01_413L2 | 06/06/2022 | 06/22/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/06/2022 | 5/28/2026 | Y | STD | 397 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GLOUCESTER | 620468 | 01930 | 3.8 |  |  | Solar |  | 05_01_607W2 | 06/25/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | LOWELL | 174873 | 01852 | 2000 |  |  | Solar |  | 05_05_11W81 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 11/27/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 357487 | 01876 | 240 |  |  | Solar |  | 05_12_25W3 | 05/14/2021 | 06/23/2021 | 26 | 16 | 10 | 06/24/2021 | 06/24/2021 | 343 | 319 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 396042 | 01844 | 0 |  |  | Other |  | 05_12_51T3 | 01/04/2022 | 02/04/2022 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 03/02/2022 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 601232 | 01451 | 6 |  |  | Solar |  | 05_14_3L4 | 04/08/2024 | 04/10/2024 | 2 | 0 | 2 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 405741 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_59L5 | 01/23/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 03/02/2022 | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 658199 | 01566 | 5.76 |  |  | Solar |  | 05_14_74L2 | 12/04/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | GARDNER | 374977 | 01440 | 11.4 |  |  | Solar |  | 05_01_216W6 | 08/10/2021 | 09/07/2021 | 19 | 18 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2022 | Connected |  | N
National Grid | SWANSEA | 723925 | 02777 | 7.6 |  |  | Solar |  | 05_01_27W1 | 10/03/2025 | 12/09/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 708984 | 01906 | 0 |  |  | Other |  | 05_01_413L2 | 10/08/2025 | 11/20/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GLOUCESTER | 312828 | 01930 | 762 |  |  | Solar |  | 05_01_607W3 | 04/29/2021 | 10/03/2021 | 108 | 98 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2021 | 12/04/2021 | 42 | 4 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 | 04/29/2021 | 1/1/2026 | Y | STD | 2 | 01/01/2026 | 12/31/2025 | 0 | 0 | 0 |  |  | 12/31/2025 | Completion Documents |  | N
National Grid | LOWELL | 174930 | 01852 | 50 |  |  | Solar |  | 05_05_11W81 | 08/26/2013 | 08/26/2013 | 11 | 4 | 7 | 09/13/2013 | 09/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2013 |  | 12/31/2013 | N | EXP | 96 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 | 12/12/2013 | Connected |  | N
National Grid | TEWKSBURY | 419316 | 01876 | 240 |  |  | Solar |  | 05_12_25W3 | 05/26/2022 | 06/27/2022 | 20 | 14 | 6 | 06/28/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | METHUEN | 419846 | 01844 | 0 |  |  | Other |  | 05_12_51T3 | 06/14/2022 | 07/19/2022 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/20/2022 | 08/08/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 641328 | 01740 | 6 |  |  | Solar |  | 05_14_3L4 | 09/20/2024 | 09/30/2024 | 4 | 0 | 4 | 10/01/2024 | 10/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/20/2024 | 11/20/2025 | Y | EXP | 365 | 02/19/2025 | 03/12/2025 | 22 | 0 | 22 |  |  | 3/19/2025 | Connected |  | Y
National Grid | WORCESTER | 586370 | 01604 | 2890 |  |  | Battery Add-On |  | 05_14_59L5 | 02/01/2024 |  | 264 | 254 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 668418 | 01566 | 3.8 |  |  | Solar |  | 05_14_74L2 | 01/28/2025 | 03/18/2025 | 25 | 20 | 5 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 | 01/28/2025 | 4/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 376566 | 01440 | 7.6 |  |  | Solar |  | 05_01_216W6 | 11/04/2021 | 12/06/2021 | 21 | 18 | 3 | 12/07/2021 | 12/07/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2022 | Connected |  | N
National Grid | SWANSEA | 735996 | 02777 | 5.76 |  |  | Solar |  | 05_01_27W1 | 11/24/2025 | 12/22/2025 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 741674 | 01906 | 11.5 |  |  | Solar |  | 05_01_413L2 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GLOUCESTER | 674436 | 01930 | 3.8 |  |  | Solar |  | 05_01_607W3 | 02/26/2025 | 04/25/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 02/26/2025 | 7/17/2026 | Y | EXP | 365 | 08/07/2025 | 10/24/2025 | 79 | 0 | 79 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 175116 | 01852 | 25 |  |  | Solar |  | 05_05_11W81 | 10/16/2013 | 10/16/2013 | 6 | 0 | 6 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2013 |  | 9/1/2014 | N | EXP | 299 |  |  | 0 | 0 | 0 | 5/27/2014 | 5/27/2014 | 7/3/2014 | Connected |  | N
National Grid | ANDOVER | 476349 | 01810 | 240 |  |  | Solar |  | 05_12_25W3 | 02/23/2023 | 08/22/2023 | 36 | 26 | 10 | 08/23/2023 | 08/23/2023 | 179 | 93 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 496619 | 01844 | 110 |  |  | Solar |  | 05_12_51T3 | 02/21/2023 | 04/21/2023 | 41 | 31 | 10 |  |  | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 646620 | 01740 | 5.76 |  |  | Solar |  | 05_14_3L4 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 3/27/2025 | Connected |  | N
National Grid | WORCESTER | 587585 | 01604 | 23 |  |  | Solar |  | 05_14_59L5 | 02/02/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 685217 | 01550 | 10 |  |  | Solar |  | 05_14_74L2 | 04/15/2025 | 05/13/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/15/2025 | 7/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | GARDNER | 379354 | 01440 | 0 |  |  | Solar |  | 05_01_216W6 | 09/01/2021 | 09/13/2021 | 7 | 7 | 0 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2021 | Connected |  | N
National Grid | SWANSEA | 174418 | 02777 | 110 |  |  | Solar |  | 05_01_27W1 | 10/20/2011 | 10/20/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2011 | 10/20/2011 | 5/4/2012 | Y | EXP | 137 | 03/12/2012 | 04/12/2012 | 22 | 0 | 22 | 1/25/2013 | 1/25/2013 | 5/4/2012 | Connected |  | N
National Grid | SAUGUS | 174118 | 01906 | 1725 |  |  | Solar |  | 05_01_413L2 | 03/15/2012 | 03/15/2012 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 175152 | 01930 | 750 |  |  | Solar |  | 05_01_607W3 | 11/01/2013 | 11/20/2013 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 01/02/2014 |  | 1053 | 203 | 850 | 11/20/2013 | 01/02/2014 | 28 | 28 | 0 |  |  | 1053 | 203 | 850 |  |  | 0 | 0 | 0 | 9/11/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 175934 | 01852 | 8.6 |  |  | Solar |  | 05_05_11W81 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/15/2016 | N | EXP | 349 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/16/2016 | Connected |  | N
National Grid | ANDOVER | 488519 | 01810 | 480 |  |  | Solar |  | 05_12_25W3 | 02/24/2023 | 06/28/2023 | 85 | 74 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 572797 | 01844 | 7.6 |  |  | Solar |  | 05_12_51T3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/12/2024 | 3/24/2025 | Y | EXP | 365 | 08/01/2024 | 09/25/2024 | 56 | 0 | 56 |  |  | 10/29/2024 | Connected |  | N
National Grid | BOLTON | 652013 | 01740 | 15.2 |  |  | Solar |  | 05_14_3L4 | 11/04/2024 | 11/25/2024 | 14 | 10 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WORCESTER | 609316 | 01604 | 23 |  |  | Solar |  | 05_14_59L5 | 05/07/2024 | 05/17/2024 | 9 | 7 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 637381 | 01550 | 7.6 |  |  | Solar |  | 05_14_74L3 | 09/03/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/03/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 395135 | 01440 | 250 |  |  | Solar |  | 05_01_216W6 | 12/14/2021 | 01/03/2022 | 14 | 8 | 6 |  |  | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175075 | 02777 | 75 |  |  | Solar |  | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2013 |  | 11/10/2016 | N | EXP | 1122 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/15/2016 | Connected |  | N
National Grid | SAUGUS | 175101 | 01906 | 2000 |  |  | Solar |  | 05_01_413L2 | 10/25/2012 | 10/25/2012 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 12/31/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/13/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 178561 | 01930 | 1666 |  |  | Solar |  | 05_01_607W3 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 10/26/2018 | 137 | 70 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176169 | 01852 | 476 |  |  | Solar |  | 05_05_11W81 | 04/17/2015 | 04/17/2015 | 1 | 1 | 0 | 04/22/2015 | 04/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2015 | 04/17/2015 | 12/31/2016 | Y | EXP | 582 | 08/30/2016 | 12/12/2016 | 70 | 0 | 70 | 5/29/2015 | 5/29/2015 | 12/13/2016 | Connected |  | N
National Grid | ANDOVER | 657521 | 01810 | 7.6 |  |  | Solar |  | 05_12_25W4 | 11/27/2024 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 615411 | 01844 | 25 |  |  | Solar |  | 05_12_51T3 | 06/10/2024 | 11/07/2024 | 104 | 95 | 9 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | BOLTON | 652158 | 01740 | 3.8 |  |  | Solar |  | 05_14_3L4 | 11/05/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 645946 | 01604 | 10 |  |  | Solar |  | 05_14_59L5 | 10/10/2024 | 10/28/2024 | 12 | 10 | 2 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | STURBRIDGE | 656139 | 01566 | 6.175 |  |  | Solar |  | 05_14_74L3 | 11/28/2024 | 03/17/2025 | 28 | 26 | 2 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WINCHENDON | 404028 | 01475 | 12.86 |  |  | Solar |  | 05_01_216W6 | 12/29/2021 | 01/03/2022 | 3 | 0 | 3 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2022 | Connected |  | N
National Grid | SWANSEA | 175074 | 02777 | 100 |  |  | Solar |  | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2013 |  | 12/5/2016 | N | EXP | 1119 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/6/2016 | Connected |  | N
National Grid | MELROSE | 175596 | 02176 | 480 |  |  | Solar |  | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 | 08/12/2014 | 08/12/2014 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/15/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 200441 | 01966 | 4998 |  |  | Solar |  | 05_01_607W3 | 11/15/2018 | 11/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 | 01/25/2019 | 57 | 20 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176583 | 01852 | 7.6 |  |  | Solar |  | 05_05_11W81 | 04/07/2016 | 04/07/2016 | 4 | 4 | 0 | 04/13/2016 | 04/13/2016 | 199 | 0 | 199 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/12/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 728422 | 01876 | 5.44 |  |  | Solar |  | 05_12_25W4 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/22/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LAWRENCE | 700819 | 01841 | 15.76 |  |  | Solar |  | 05_12_51T3 | 07/02/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 07/02/2025 | 8/4/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 12/8/2025 | Connected |  | N
National Grid | BOLTON | 652366 | 01740 | 3.8 |  |  | Solar |  | 05_14_3L4 | 11/14/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 1/23/2026 | Y | EXP | 365 | 03/11/2025 | 03/24/2025 | 14 | 0 | 14 |  |  | 5/3/2025 | Connected |  | N
National Grid | WORCESTER | 667034 | 01604 | 10 |  |  | Solar |  | 05_14_59L5 | 02/03/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 407694 | 01566 | 10 |  |  | Solar |  | 05_01_216W6 | 01/20/2022 | 01/24/2022 | 3 | 1 | 2 | 01/25/2022 | 01/25/2022 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 | 01/20/2022 | 8/31/2023 | Y | EXP | 365 | 05/07/2022 | 08/25/2022 | 108 | 0 | 108 |  |  | 9/1/2022 | Connected |  | N
National Grid | WINCHENDON | 189268 | 01475 | 15.2 |  |  | Solar |  | 05_01_27W1 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 06/26/2018 | 10/13/2019 | Y | EXP | 500 | 05/02/2020 | 05/01/2020 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175595 | 02777 | 996 |  |  | Solar |  | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 09/09/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/01/2014 | 4/1/2016 | Y | STD | 340 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | MELROSE | 282444 | 02176 | 831 |  |  | Natural Gas |  | 05_01_607W3 | 05/20/2020 | 07/06/2020 | 31 | 25 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 176748 | 01930 | 5 |  |  | Solar |  | 05_05_11W81 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 9/1/2016 | Connected |  | N
National Grid | LOWELL | 176158 | 01852 | 15.2 |  |  | Solar |  | 05_12_25W4 | 01/29/2015 | 01/29/2015 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 703384 | 01876 | 90 |  |  | Solar |  | 05_12_51T3 | 07/10/2025 | 08/07/2025 | 20 | 11 | 9 | 08/08/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 653437 | 01841 | 5.76 |  |  | Solar |  | 05_14_3L4 | 11/18/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 55 | 33 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 724647 | 01740 | 0 |  |  | Solar |  | 05_14_59L6 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 668860 | 01604 | 10 |  |  | Solar |  | 05_14_74L3 | 01/30/2025 | 03/28/2025 | 6 | 1 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STURBRIDGE | 435624 | 01566 | 15.2 |  |  | Solar |  | 05_01_216W6 | 06/06/2022 | 06/24/2022 | 13 | 11 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | GARDNER | 197109 | 01440 | 7.6 |  |  | Solar |  | 05_01_27W1 | 09/27/2018 | 10/18/2018 | 4 | 3 | 1 | 10/19/2018 | 10/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 8/30/2019 | N | EXP | 247 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | SWANSEA | 175664 | 02777 | 996 |  |  | Solar |  | 05_01_413L2 | 08/11/2014 | 08/11/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/09/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/11/2014 | 3/15/2016 | Y | STD | 323 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | MELROSE | 439984 | 02176 | 9.86 |  |  | Solar |  | 05_01_607W3 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 177167 | 01930 | 2.75 |  |  | Solar |  | 05_05_11W81 | 01/25/2017 | 01/25/2017 | 80 | 78 | 2 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 01/25/2017 | 1/31/2018 | Y | EXP | 253 | 07/18/2017 | 07/24/2017 | 4 | 0 | 4 | 11/3/2017 | 11/3/2017 | 11/3/2017 | Connected |  | N
National Grid | LOWELL | 177407 | 01852 | 56 |  |  | Solar |  | 05_12_25W4 | 09/09/2016 | 09/09/2016 | 17 | 17 | 0 | 10/04/2016 | 10/04/2016 | 60 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 7/31/2018 | N | EXP | 573 |  |  | 0 | 0 | 0 |  |  | 12/12/2018 | Connected |  | N
National Grid | ANDOVER | 628375 | 01810 | 34.5 |  |  | Battery Add-On |  | 05_12_52J2 | 07/29/2024 | 08/01/2024 | 3 | 0 | 3 | 08/02/2024 | 08/02/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | METHUEN | 653277 | 01844 | 7.6 |  |  | Solar |  | 05_14_3L4 | 11/14/2024 | 01/16/2025 | 31 | 25 | 6 | 01/17/2025 | 01/17/2025 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 730098 | 01740 | 10 |  |  | Solar |  | 05_14_59L6 | 10/29/2025 | 10/30/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 681130 | 01607 | 3.8 |  |  | Solar |  | 05_14_74L3 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 08/11/2025 | 08/11/2025 | 63 | 63 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STURBRIDGE | 515975 | 01566 | 7.6 |  |  | Solar |  | 05_01_216W6 | 05/09/2023 | 08/16/2023 | 68 | 66 | 2 | 08/17/2023 | 08/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2023 | Connected |  | N
National Grid | GARDNER | 201073 | 01440 | 396 |  |  | Solar |  | 05_01_27W1 | 11/15/2018 | 11/21/2018 | 4 | 2 | 2 | 11/26/2018 | 11/26/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 176660 | 02777 | 1440 |  |  | Solar |  | 05_01_413L2 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 641030 | 02176 | 9.86 |  |  | Solar |  | 05_01_607W3 | 09/17/2024 | 11/05/2024 | 11 | 9 | 2 | 11/06/2024 | 11/06/2024 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2024 | Connected |  | N
National Grid | GLOUCESTER | 177423 | 01930 | 1260 |  |  | Solar |  | 05_05_11W81 | 12/06/2016 | 12/06/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 01/12/2017 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2017 |  | 6/11/2020 | N | STD | 1052 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 191843 | 01852 | 50 |  |  | Solar |  | 05_12_25W4 | 08/21/2018 | 09/17/2018 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2019 |  | 11/29/2019 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | ANDOVER | 657154 | 01810 | 3.8 |  |  | Solar |  | 05_12_52L1 | 11/26/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 654034 | 01841 | 5.76 |  |  | Solar |  | 05_14_3L4 | 11/13/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | CLINTON | 738704 | 01510 | 22.8 |  |  | Solar |  | 05_14_59L6 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 692028 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 05/26/2025 | 06/16/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 543308 | 01550 | 15 |  |  | Solar |  | 05_01_216W6 | 07/24/2023 | 07/25/2023 | 1 | 0 | 1 | 07/26/2023 | 07/26/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | GARDNER | 206484 | 01440 | 480 |  |  | Solar |  | 05_01_27W1 | 03/13/2019 | 04/27/2019 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2019 | 05/23/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 03/13/2019 | 6/30/2023 | Y | STD | 644 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | SWANSEA | 177438 | 02777 | 260 |  |  | Solar |  | 05_01_413L2 | 07/01/2016 | 07/01/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 07/01/2016 | 10/6/2017 | Y | EXP | 382 | 07/17/2017 | 09/27/2017 | 51 | 0 | 51 | 9/29/2017 | 9/29/2017 | 9/29/2017 | Connected |  | N
National Grid | MELROSE | 644604 | 02176 | 10 |  |  | Solar |  | 05_01_607W3 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/02/2024 | 12/24/2025 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 177710 | 01930 | 7.6 |  |  | Solar |  | 05_05_11W81 | 05/30/2017 | 05/30/2017 | 7 | 7 | 0 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 | 05/30/2017 | 6/4/2018 | Y | EXP | 360 | 09/28/2017 | 10/13/2017 | 10 | 0 | 10 | 10/25/2017 | 10/25/2017 | 10/30/2017 | Connected |  | N
National Grid | LOWELL | 206824 | 01852 | 0 |  |  | Solar |  | 05_12_25W4 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | ANDOVER | 691723 | 01810 | 11.5 |  |  | Solar |  | 05_12_52L1 | 06/12/2025 | 07/22/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 60 | 46 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 657027 | 01844 | 7.6 |  |  | Solar |  | 05_14_3L4 | 11/26/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | BOLTON | 175499 | 01740 | 29.455 |  |  | Solar |  | 05_14_59L6 | 09/26/2014 | 09/26/2014 | 6 | 0 | 6 | 10/07/2014 | 10/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 | 09/26/2014 | 12/31/2016 | Y | EXP | 641 | 10/22/2015 | 02/01/2016 | 67 | 0 | 67 | 5/17/2016 | 5/17/2016 | 6/2/2016 | Connected |  | N
National Grid | WORCESTER | 709517 | 01604 | 5.76 |  |  | Solar |  | 05_14_74L3 | 08/04/2025 | 08/28/2025 | 2 | 0 | 2 | 08/29/2025 | 08/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 568830 | 01550 | 15.435 |  |  | Solar |  | 05_01_216W6 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2024 | Connected |  | N
National Grid | WINCHENDON | 260892 | 01475 | 6 |  |  | Solar |  | 05_01_27W1 | 11/01/2019 | 01/02/2020 | 40 | 38 | 2 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/01/2019 | 9/3/2021 | Y | EXP | 365 | 05/06/2021 | 06/10/2021 | 35 | 0 | 35 |  |  | 8/10/2021 | Connected |  | N
National Grid | SWANSEA | 178281 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 02/23/2018 | 02/23/2018 | 4 | 4 | 0 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2018 |  | 3/3/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | MELROSE | 656728 | 02176 | 5.76 |  |  | Solar |  | 05_01_607W3 | 11/25/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | GLOUCESTER | 177751 | 01930 | 5.2 |  |  | Solar |  | 05_05_11W81 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2017 | 07/27/2017 | 8/1/2018 | Y | EXP | 348 | 08/24/2017 | 09/09/2017 | 11 | 0 | 11 | 11/27/2017 | 11/27/2017 | 12/1/2017 | Connected |  | N
National Grid | LOWELL | 447514 | 01852 | 15.66 |  |  | Solar |  | 05_12_25W4 | 08/25/2022 | 09/13/2022 | 13 | 12 | 1 | 09/14/2022 | 09/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2023 | Connected |  | N
National Grid | ANDOVER | 724732 | 01810 | 19.2 |  |  | Solar |  | 05_12_52L1 | 10/13/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 658318 | 01844 | 3.8 |  |  | Solar |  | 05_14_3L4 | 12/04/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | BOLTON | 177121 | 01740 | 540 |  |  | Solar |  | 05_14_59L6 | 10/19/2016 | 10/19/2016 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 02/03/2017 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 735225 | 01604 | 15.76 |  |  | Solar |  | 05_14_74L3 | 11/20/2025 | 11/26/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 570119 | 01566 | 9.45 |  |  | Solar |  | 05_01_216W6 | 01/31/2024 | 02/06/2024 | 4 | 1 | 3 | 02/07/2024 | 02/07/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 01/31/2024 | 4/26/2025 | Y | EXP | 365 | 07/10/2024 | 07/16/2024 | 7 | 0 | 7 |  |  | 7/26/2024 | Connected |  | N
National Grid | GARDNER | 336430 | 01440 | 6 |  |  | Solar |  | 05_01_27W1 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2021 | Connected |  | N
National Grid | SWANSEA | 178286 | 02777 | 5 |  |  | Solar |  | 05_01_413L2 | 03/28/2018 | 03/28/2018 | 6 | 0 | 6 | 04/06/2018 | 04/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/28/2018 | 4/3/2019 | Y | EXP | 336 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | MELROSE | 659120 | 02176 | 0 |  |  | Battery Add-On |  | 05_01_607W3 | 12/06/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 178549 | 01930 | 5 |  |  | Solar |  | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 22 | 0 | 22 | 04/27/2018 | 04/27/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/18/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | LOWELL | 475633 | 01852 | 50 |  |  | Solar |  | 05_12_25W4 | 11/10/2022 | 11/23/2022 | 8 | 0 | 8 | 11/25/2022 | 11/25/2022 | 44 | 24 | 20 | 02/02/2023 | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 11/29/2024 | N | EXP | 365 | 10/21/2023 | 12/05/2023 | 46 | 0 | 46 |  |  | 8/23/2024 | Connected |  | N
National Grid | ANDOVER | 175870 | 01810 | 25 |  |  | Solar |  | 05_12_52L1 | 09/25/2015 | 09/25/2015 | 1 | 1 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2015 |  | 10/3/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 1/29/2016 | 1/29/2016 | 2/3/2016 | Connected |  | N
National Grid | LAWRENCE | 661851 | 01841 | 3.8 |  |  | Solar |  | 05_14_3L4 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 177730 | 01740 | 20 |  |  | Solar |  | 05_14_59L6 | 10/05/2017 | 10/05/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 10/10/2018 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | WORCESTER | 738712 | 01604 | 10 |  |  | Solar |  | 05_14_74L3 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 574056 | 01550 | 0 |  |  | Battery Add-On |  | 05_01_216W6 | 11/28/2023 | 01/02/2024 | 23 | 17 | 6 | 01/03/2024 | 01/03/2024 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | GARDNER | 396408 | 01440 | 9.772 |  |  | Solar |  | 05_01_27W1 | 11/22/2021 | 12/22/2021 | 6 | 3 | 3 | 12/02/2021 | 12/02/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 5/31/2023 | N | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 6/6/2023 | Connected |  | N
National Grid | SWANSEA | 191126 | 02777 | 3.8 |  |  | Solar |  | 05_01_413L2 | 07/19/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 673971 | 02176 | 11.5 |  |  | Solar |  | 05_01_607W3 | 02/27/2025 | 03/10/2025 | 7 | 4 | 3 | 03/11/2025 | 03/11/2025 | 108 | 85 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 178548 | 01930 | 6 |  |  | Solar |  | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 24 | 24 | 0 | 04/27/2018 | 04/27/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 3/18/2019 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | LOWELL | 491299 | 01852 | 6.48 |  |  | Solar |  | 05_12_25W4 | 01/20/2023 | 01/24/2023 | 2 | 0 | 2 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 | 03/28/2023 | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | ANDOVER | 177815 | 01810 | 15.2 |  |  | Solar |  | 05_12_52L1 | 03/31/2017 | 03/31/2017 | 7 | 4 | 3 | 04/11/2017 | 04/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2017 | 03/31/2017 | 8/10/2018 | Y | EXP | 485 | 01/24/2018 | 02/23/2018 | 21 | 0 | 21 |  |  | 7/30/2018 | Connected |  | N
National Grid | METHUEN | 663246 | 01844 | 3.8 |  |  | Solar |  | 05_14_3L4 | 01/10/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | BOLTON | 243231 | 01740 | 10 |  |  | Solar |  | 05_14_59L6 | 08/15/2019 | 08/21/2019 | 3 | 0 | 3 | 08/22/2019 | 08/22/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/15/2019 | 8/15/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | WORCESTER | 174308 | 01604 | 190 |  |  | Solar |  | 05_14_74L3 | 12/09/2011 | 12/09/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2012 | 12/09/2011 | 2/1/2012 | Y | EXP | -41 | 05/08/2012 | 05/09/2012 | 1 | 0 | 1 | 5/11/2012 | 5/11/2012 | 5/23/2012 | Connected |  | N
National Grid | STURBRIDGE | 582430 | 01566 | 15.2 |  |  | Solar |  | 05_01_216W6 | 01/09/2024 | 01/11/2024 | 2 | 0 | 2 | 01/12/2024 | 01/12/2024 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 4/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | GARDNER | 467875 | 01440 | 6 |  |  | Solar |  | 05_01_27W1 | 11/28/2022 |  | 239 | 65 | 174 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 199144 | 02777 | 11.4 |  |  | Solar |  | 05_01_413L2 | 10/22/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 459174 | 02176 | 240 |  |  | Solar |  | 05_01_607W4 | 09/23/2022 | 10/17/2022 | 16 | 8 | 8 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GLOUCESTER | 178609 | 01930 | 6 |  |  | Solar |  | 05_05_11W81 | 12/13/2017 | 12/13/2017 | 49 | 35 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 12/18/2018 | N | EXP | 295 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | Y
National Grid | LOWELL | 536960 | 01852 | 10 |  |  | Solar |  | 05_12_25W4 | 07/10/2023 | 07/11/2023 | 1 | 0 | 1 | 07/12/2023 | 07/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 274362 | 01810 | 4.32 |  |  | Solar |  | 05_12_52L1 | 02/12/2020 | 02/26/2020 | 8 | 8 | 0 | 02/27/2020 | 02/27/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 02/12/2020 | 2/26/2021 | Y | EXP | 365 | 07/23/2020 | 09/15/2020 | 55 | 5 | 50 |  |  | 9/16/2020 | Connected |  | N
National Grid | METHUEN | 674880 | 01844 | 9.86 |  |  | Solar |  | 05_14_3L4 | 02/28/2025 | 03/12/2025 | 2 | 1 | 1 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/28/2025 | 5/29/2026 | Y | EXP | 365 | 09/17/2025 | 09/16/2025 | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | BOLTON | 257906 | 01740 | 11.4 |  |  | Solar |  | 05_14_59L6 | 10/02/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N
National Grid | WORCESTER | 176470 | 01604 | 252 |  |  | Solar |  | 05_14_74L3 | 03/20/2016 | 03/20/2016 | 13 | 13 | 0 | 04/07/2016 | 04/07/2016 | 383 | 0 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 12/31/2017 | N | EXP | 611 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 582976 | 01566 | 8.775 |  |  | Solar |  | 05_01_216W6 | 01/29/2024 | 02/08/2024 | 9 | 8 | 1 | 02/09/2024 | 02/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | GARDNER | 556062 | 01440 | 7.6 |  |  | Solar |  | 05_01_27W1 | 03/15/2024 | 09/22/2023 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | SWANSEA | 204532 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 01/10/2019 | 8/19/2020 | Y | EXP | 365 | 06/24/2020 | 06/30/2020 | 6 | 0 | 6 |  |  | 7/30/2020 | Connected |  | N
National Grid | MELROSE | 722236 | 02176 | 10 |  |  | Solar |  | 05_01_607W4 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 199525 | 01930 | 1000 |  |  | Solar |  | 05_05_11W81 | 10/26/2018 | 11/16/2018 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2018 | 12/18/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 613279 | 01852 | 6.825 |  |  | Solar |  | 05_12_25W4 | 05/28/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 | 05/28/2024 | 7/19/2025 | Y | EXP | 365 | 09/19/2024 | 10/28/2024 | 40 | 0 | 40 |  |  | 5/14/2025 | Connected |  | N
National Grid | ANDOVER | 303344 | 01810 | 15.2 |  |  | Solar |  | 05_12_52L1 | 07/27/2020 | 08/28/2020 | 24 | 24 | 0 | 08/31/2020 | 08/31/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 4/11/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 2/10/2022 | Connected |  | N
National Grid | METHUEN | 647611 | 01844 | 0 |  |  | Hydro |  | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOLTON | 306710 | 01740 | 133.2 |  |  | Solar |  | 05_14_59L6 | 08/18/2020 | 10/05/2020 | 33 | 28 | 5 | 10/06/2020 | 10/06/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 1/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176680 | 01604 | 6 |  |  | Solar |  | 05_14_74L3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/11/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 | 5/24/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 588321 | 01550 | 6.282 |  |  | Solar |  | 05_01_216W6 | 03/05/2024 | 03/27/2024 | 17 | 16 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | GARDNER | 573451 | 01440 | 5.51 |  |  | Solar |  | 05_01_27W1 | 12/12/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | SWANSEA | 225333 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 05/07/2019 | 07/19/2019 | 54 | 53 | 1 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 174498 | 02176 | 3300 |  |  | Wind |  | 05_01_607W4 | 06/10/2010 | 06/10/2010 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 06/10/2010 | 10/31/2012 | Y | STD | -42 |  |  | 0 | 0 | 0 | 4/12/2013 | 4/12/2013 | 4/4/2013 | Connected |  | N
National Grid | GLOUCESTER | 315459 | 01930 | 998 |  |  | Solar |  | 05_05_11W81 | 02/22/2021 | 04/30/2021 | 48 | 39 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2021 | 06/15/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 640889 | 01852 | 9 |  |  | Solar |  | 05_12_25W4 | 09/18/2024 | 11/01/2024 | 17 | 11 | 6 | 11/04/2024 | 11/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | ANDOVER | 371202 | 01810 | 7.6 |  |  | Solar |  | 05_12_52L1 | 08/03/2021 | 08/18/2021 | 12 | 11 | 1 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2021 | Connected |  | N
National Grid | METHUEN | 647609 | 01844 | 0 |  |  | Hydro |  | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOLTON | 309079 | 01740 | 3.8 |  |  | Solar |  | 05_14_59L6 | 08/26/2020 | 09/15/2020 | 13 | 13 | 0 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2021 | Connected |  | N
National Grid | WORCESTER | 176823 | 01604 | 6 |  |  | Solar |  | 05_14_74L3 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/20/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/25/2016 | Connected |  | N
National Grid | STURBRIDGE | 609347 | 01566 | 100 |  |  | Solar |  | 05_01_216W6 | 05/29/2024 | 08/20/2024 | 57 | 48 | 9 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 05/29/2024 | 11/16/2025 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N
National Grid | GARDNER | 596342 | 01440 | 0 |  |  | Solar |  | 05_01_27W1 | 03/28/2024 | 04/01/2024 | 7 | 3 | 4 | 04/09/2024 | 04/09/2024 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2024 | Connected |  | N
National Grid | SWANSEA | 260850 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 10/28/2019 | 10/31/2019 | 3 | 3 | 0 | 11/01/2019 | 11/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/28/2019 | 10/28/2020 | Y | EXP | 365 | 02/19/2020 | 03/03/2020 | 13 | 0 | 13 |  |  | 3/6/2020 | Connected |  | N
National Grid | MELROSE | 176405 | 02176 | 1500 |  |  | Wind |  | 05_01_607W4 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/06/2016 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 349385 | 01966 | 7.6 |  |  | Solar |  | 05_05_11W81 | 04/05/2021 | 04/14/2021 | 6 | 0 | 6 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | LOWELL | 645195 | 01852 | 7.6 |  |  | Solar |  | 05_12_25W4 | 10/25/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 375231 | 01810 | 11.4 |  |  | Solar |  | 05_12_52L1 | 08/11/2021 | 08/31/2021 | 14 | 13 | 1 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2021 | 08/11/2021 | 2/14/2023 | Y | EXP | 365 | 01/06/2022 | 02/14/2022 | 40 | 0 | 40 |  |  | 4/19/2022 | Connected |  | Y
National Grid | METHUEN | 647617 | 01844 | 0 |  |  | Hydro |  | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOLTON | 360062 | 01740 | 130 |  |  | Natural Gas |  | 05_14_59L6 | 06/09/2021 | 07/20/2021 | 28 | 18 | 10 |  |  | 54 | 29 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 06/09/2021 | 8/20/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | WORCESTER | 176884 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 638189 | 01566 | 10 |  |  | Solar |  | 05_01_216W6 | 09/06/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 09/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | GARDNER | 600309 | 01440 | 5 |  |  | Solar |  | 05_01_27W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 313745 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 10/07/2020 | 10/27/2020 | 13 | 12 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | MELROSE | 176399 | 02176 | 7.6 |  |  | Solar |  | 05_01_607W4 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2016 | 03/10/2016 | 3/19/2017 | Y | EXP | 328 | 07/18/2016 | 08/11/2016 | 18 | 0 | 18 | 4/25/2016 | 4/25/2016 | 9/8/2016 | Connected |  | N
National Grid | ROCKPORT | 443975 | 01966 | 0 |  |  | Other |  | 05_05_11W81 | 11/09/2022 | 01/31/2023 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 647977 | 01852 | 6.67 |  |  | Solar |  | 05_12_25W4 | 10/17/2024 | 11/26/2024 | 6 | 1 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | ANDOVER | 380590 | 01810 | 7.6 |  |  | Solar |  | 05_12_52L1 | 11/16/2021 | 12/20/2021 | 23 | 22 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175719 | 01844 | 120.9 |  |  | Solar |  | 05_14_3L5 | 12/29/2014 | 12/29/2014 | 8 | 6 | 2 | 01/12/2015 | 01/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/29/2014 | 5/31/2015 | Y | EXP | 117 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 11/25/2015 | Connected |  | N
National Grid | BOLTON | 398978 | 01740 | 11.4 |  |  | Solar |  | 05_14_59L6 | 01/04/2022 | 01/07/2022 | 3 | 0 | 3 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | WORCESTER | 176943 | 01604 | 5.75 |  |  | Solar |  | 05_14_74L3 | 12/12/2016 | 12/12/2016 | 1 | 1 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/12/2016 | 12/25/2017 | Y | EXP | 368 | 06/20/2017 | 07/05/2017 | 10 | 0 | 10 | 9/21/2017 | 9/21/2017 | 9/21/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 645214 | 01550 | 6.175 |  |  | Solar |  | 05_01_216W6 | 10/08/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 600630 | 01440 | 6 |  |  | Solar |  | 05_01_27W1 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 335828 | 02777 | 0 |  |  | Other |  | 05_01_413L2 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 176568 | 02176 | 7.6 |  |  | Solar |  | 05_01_607W4 | 12/23/2015 | 12/23/2015 | 20 | 20 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 12/23/2015 | 12/29/2016 | Y | EXP | 310 | 07/18/2016 | 08/16/2016 | 21 | 0 | 21 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | GLOUCESTER | 489747 | 01930 | 10 |  |  | Solar |  | 05_05_11W81 | 01/09/2023 | 01/11/2023 | 2 | 0 | 2 | 01/12/2023 | 01/12/2023 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 | 01/09/2023 | 5/3/2024 | Y | EXP | 365 | 04/11/2023 | 05/02/2023 | 22 | 0 | 22 |  |  | 6/21/2023 | Connected |  | Y
National Grid | LOWELL | 648629 | 01852 | 7.6 |  |  | Solar |  | 05_12_25W4 | 10/22/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/22/2024 | 3/7/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | ANDOVER | 412422 | 01810 | 15.2 |  |  | Solar |  | 05_12_52L1 | 02/23/2022 | 02/24/2022 | 2 | 1 | 1 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | LAWRENCE | 177150 | 01841 | 7.56 |  |  | Solar |  | 05_14_3L5 | 08/10/2016 | 08/10/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 08/10/2016 | 8/16/2017 | Y | EXP | 362 | 12/14/2016 | 01/06/2017 | 15 | 0 | 15 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | BOLTON | 405190 | 01740 | 0 |  |  | Battery Add-On |  | 05_14_59L6 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176936 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/6/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/4/2016 | 8/4/2016 | 8/8/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 655285 | 01550 | 7.6 |  |  | Solar |  | 05_01_216W6 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | GARDNER | 604510 | 01440 | 5.76 |  |  | Solar |  | 05_01_27W1 | 04/17/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/17/2024 | 6/7/2025 | Y | EXP | 365 | 08/16/2024 | 10/29/2024 | 75 | 0 | 75 |  |  | 11/12/2024 | Connected |  | N
National Grid | SWANSEA | 418074 | 02777 | 15.2 |  |  | Solar |  | 05_01_413L2 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | MELROSE | 177006 | 02176 | 10 |  |  | Solar |  | 05_01_607W4 | 10/11/2016 | 10/13/2016 | 1 | 1 | 0 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/11/2016 | 9/30/2019 | Y | EXP | 1078 | 05/05/2017 | 05/05/2017 | 39 | 0 | 39 | 3/13/2018 | 3/13/2018 | 9/13/2019 | Connected |  | N
National Grid | GLOUCESTER | 533802 | 01930 | 2400 |  |  | Solar |  | 05_05_11W81 | 07/24/2023 | 09/08/2023 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 09/18/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 665545 | 01852 | 7.6 |  |  | Solar |  | 05_12_25W4 | 01/14/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | ANDOVER | 485413 | 01810 | 7.6 |  |  | Solar |  | 05_12_52L1 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 12/31/2024 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 370918 | 01844 | 100 |  |  | Solar |  | 05_14_3L5 | 08/16/2021 | 09/10/2021 | 18 | 8 | 10 | 09/13/2021 | 09/13/2021 | 66 | 13 | 53 | 12/30/2021 | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/3/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2022 | Connected |  | N
National Grid | BOLTON | 414820 | 01740 | 7.6 |  |  | Solar |  | 05_14_59L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177053 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2017 |  | 1/16/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | STURBRIDGE | 657684 | 01566 | 10 |  |  | Solar |  | 05_01_216W6 | 12/02/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 605299 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 04/19/2024 | 04/26/2024 | 4 | 0 | 4 | 04/29/2024 | 04/29/2024 | 57 | 47 | 10 | 08/05/2024 | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 9/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 471227 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 155 | 21 | 134 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 177832 | 02176 | 900 |  |  | Solar |  | 05_01_607W4 | 08/08/2017 | 08/08/2017 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2017 | 09/26/2017 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 | 08/08/2017 | 10/8/2021 | Y | STD | 555 | 01/07/2021 | 09/21/2021 | 258 | 80 | 178 | 9/22/2021 | 9/30/2021 | 10/7/2021 | Connected |  | N
National Grid | GLOUCESTER | 564941 | 01930 | 10 |  |  | Solar |  | 05_05_11W81 | 11/03/2023 | 12/12/2023 | 26 | 23 | 3 | 12/13/2023 | 12/13/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/03/2023 | 5/2/2025 | Y | EXP | 365 | 04/19/2024 | 05/17/2024 | 29 | 0 | 29 |  |  | 7/19/2024 | Connected |  | N
National Grid | LOWELL | 665306 | 01852 | 5.76 |  |  | Solar |  | 05_12_25W4 | 01/13/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 6/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | ANDOVER | 488780 | 01810 | 15.2 |  |  | Solar |  | 05_12_52L1 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 642148 | 01844 | 3.84 |  |  | Solar |  | 05_14_3L5 | 09/23/2024 | 09/27/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 | 09/23/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BOLTON | 486898 | 01740 | 16 |  |  | Solar |  | 05_14_59L6 | 01/11/2023 | 01/24/2023 | 9 | 8 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | WORCESTER | 178183 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 04/13/2018 | 04/13/2018 | 21 | 21 | 0 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 678256 | 01550 | 17.6 |  |  | Solar |  | 05_01_216W6 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 03/21/2025 | 5/2/2026 | Y | EXP | 365 | 07/04/2025 | 11/17/2025 | 137 | 0 | 137 |  |  | 12/4/2025 | Connected |  | N
National Grid | WESTMINSTER | 610041 | 01473 | 7.6 |  |  | Solar |  | 05_01_27W1 | 05/09/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 471147 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 8/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2023 | Connected |  | N
National Grid | MELROSE | 193550 | 02176 | 250 |  |  | Solar |  | 05_01_607W4 | 08/15/2018 | 08/27/2018 | 6 | 0 | 6 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 562469 | 01930 | 5 |  |  | Solar |  | 05_05_11W81 | 11/06/2023 | 11/28/2023 | 14 | 12 | 2 | 11/29/2023 | 11/29/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 671938 | 01852 | 9.88 |  |  | Solar |  | 05_12_25W4 | 02/13/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | ANDOVER | 570135 | 01810 | 15.2 |  |  | Solar |  | 05_12_52L1 | 11/09/2023 | 11/27/2023 | 11 | 9 | 2 | 11/28/2023 | 11/28/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | Y
National Grid | METHUEN | 656613 | 01844 | 7.6 |  |  | Solar |  | 05_14_3L5 | 11/25/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | BOLTON | 499224 | 01740 | 15.08 |  |  | Solar |  | 05_14_59L6 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y
National Grid | WORCESTER | 193240 | 01604 | 6 |  |  | Solar |  | 05_14_74L3 | 08/10/2018 | 11/30/2018 | 42 | 34 | 8 | 12/03/2018 | 12/03/2018 | 21 | 10 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 8/10/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 699612 | 01550 | 15.2 |  |  | Solar |  | 05_01_216W6 | 06/25/2025 | 06/30/2025 | 10 | 7 | 3 | 07/14/2025 | 07/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2025 | Connected |  | N
National Grid | GARDNER | 610657 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 05/14/2024 | 05/21/2024 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 478408 | 02777 | 8.7 |  |  | Solar |  | 05_01_413L2 | 01/20/2023 | 01/23/2023 | 1 | 0 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | MELROSE | 195651 | 02176 | 5 |  |  | Solar |  | 05_01_607W4 | 09/11/2018 | 10/24/2018 | 15 | 15 | 0 | 10/25/2018 | 10/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/11/2018 | 4/26/2019 | Y | EXP | 176 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | GLOUCESTER | 569149 | 01930 | 15 |  |  | Solar |  | 05_05_11W81 | 11/06/2023 | 11/17/2023 | 9 | 6 | 3 | 11/20/2023 | 11/20/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2024 | Connected |  | N
National Grid | LOWELL | 694846 | 01852 | 11.4 |  |  | Solar |  | 05_12_25W4 | 06/12/2025 | 06/20/2025 | 4 | 0 | 4 | 06/23/2025 | 06/23/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | ANDOVER | 574937 | 01810 | 23 |  |  | Solar |  | 05_12_52L1 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 114 | 90 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | LAWRENCE | 658847 | 01841 | 3.8 |  |  | Solar |  | 05_14_3L5 | 12/05/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 530104 | 01451 | 9.86 |  |  | Solar |  | 05_14_59L6 | 06/17/2023 | 06/20/2023 | 13 | 8 | 5 | 06/21/2023 | 06/21/2023 | 21 | 0 | 21 | 08/09/2023 | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 10/10/2024 | N | EXP | 365 | 10/06/2023 | 10/05/2023 | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | Y
National Grid | WORCESTER | 221314 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 04/19/2019 | 06/05/2019 | 0 | 0 | 0 | 06/06/2019 | 06/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2019 | 04/19/2019 | 7/16/2020 | Y | EXP | 365 | 03/04/2020 | 05/21/2020 | 78 | 0 | 78 |  |  | 6/5/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 706361 | 01550 | 10 |  |  | Solar |  | 05_01_216W6 | 07/22/2025 | 08/06/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | GARDNER | 612619 | 01440 | 5 |  |  | Solar |  | 05_01_27W1 | 05/29/2024 | 06/13/2024 | 1 | 0 | 1 | 06/14/2024 | 06/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2024 | Connected |  | N
National Grid | SWANSEA | 480272 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 12/07/2022 | 01/12/2023 | 25 | 22 | 3 | 01/13/2023 | 01/13/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 | 12/07/2022 | 8/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | MELROSE | 192916 | 02176 | 2040 |  |  | Solar |  | 05_01_607W4 | 10/25/2018 |  | 232 | 26 | 206 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 632418 | 01930 | 10 |  |  | Solar |  | 05_05_11W81 | 08/13/2024 | 08/16/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 08/13/2024 | 3/4/2026 | Y | EXP | 365 | 03/27/2025 | 04/17/2025 | 22 | 0 | 22 |  |  | 4/22/2025 | Connected |  | N
National Grid | LOWELL | 699634 | 01852 | 7.678 |  |  | Solar |  | 05_12_25W4 | 06/18/2025 | 07/02/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | ANDOVER | 581847 | 01810 | 0 |  |  | Solar |  | 05_12_52L1 | 01/08/2024 | 02/07/2024 | 22 | 19 | 3 | 02/08/2024 | 02/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 660925 | 01841 | 7.6 |  |  | Solar |  | 05_14_3L5 | 12/16/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/15/2025 | Connected |  | N
National Grid | BOLTON | 554641 | 01740 | 15 |  |  | Solar |  | 05_14_59L6 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | WORCESTER | 215214 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 04/17/2019 | 04/24/2019 | 4 | 0 | 4 | 04/25/2019 | 04/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 04/17/2019 | 9/17/2020 | Y | EXP | 365 | 03/04/2020 | 03/19/2020 | 15 | 0 | 15 |  |  | 7/10/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 720645 | 01550 | 11.78 |  |  | Solar |  | 05_01_216W6 | 09/21/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | GARDNER | 614361 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 05/30/2024 | 06/10/2024 | 3 | 0 | 3 | 06/11/2024 | 06/11/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 520785 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 05/12/2023 | 05/16/2023 | 2 | 0 | 2 | 05/17/2023 | 05/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/12/2023 | 6/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | MELROSE | 371045 | 02176 | 7.6 |  |  | Solar |  | 05_01_607W4 | 08/03/2021 | 12/30/2021 | 1 | 0 | 1 | 08/05/2021 | 08/05/2021 | 53 | 29 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 11/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | GLOUCESTER | 654991 | 01930 | 3.8 |  |  | Solar |  | 05_05_11W81 | 11/19/2024 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | LOWELL | 658099 | 01852 | 3.8 |  |  | Solar |  | 05_12_25W5 | 12/03/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 593568 | 01810 | 0 |  |  | Solar |  | 05_12_52L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | LAWRENCE | 668859 | 01841 | 6 |  |  | Solar |  | 05_14_3L5 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 555740 | 01451 | 10 |  |  | Solar |  | 05_14_59L6 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 21 | 0 | 21 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/2/2025 | N | EXP | 365 | 05/04/2024 | 01/30/2025 | 272 | 0 | 272 |  |  | 3/6/2025 | Connected |  | N
National Grid | WORCESTER | 255172 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 09/27/2019 | 10/02/2019 | 2 | 1 | 1 | 10/03/2019 | 10/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2019 | 09/27/2019 | 9/27/2020 | Y | EXP | 365 | 02/12/2020 | 03/12/2020 | 29 | 0 | 29 |  |  | 6/16/2020 | Connected |  | N
National Grid | STURBRIDGE | 178695 | 01566 | 500 |  |  | Solar |  | 05_01_219W1 | 02/06/2018 | 02/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 06/21/2018 | 07/19/2018 | 19 | 0 | 19 | 03/05/2018 | 04/11/2018 | 28 | 8 | 20 |  | 07/19/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/25/2018 |  | 11/1/2019 | N | STD | 464 |  |  | 0 | 0 | 0 |  |  | 12/23/2019 | Connected |  | N
National Grid | GARDNER | 615988 | 01440 | 5.76 |  |  | Solar |  | 05_01_27W1 | 06/06/2024 | 06/14/2024 | 0 | 0 | 0 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/06/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/07/2024 | 36 | 0 | 36 |  |  | 12/19/2024 | Connected |  | N
National Grid | SWANSEA | 521609 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 407933 | 02176 | 6 |  |  | Solar |  | 05_01_607W4 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/04/2022 | 4/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | GLOUCESTER | 655862 | 01930 | 10 |  |  | Solar |  | 05_05_11W81 | 11/21/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | LOWELL | 707442 | 01852 | 7.6 |  |  | Solar |  | 05_12_25W5 | 07/25/2025 | 08/13/2025 | 4 | 0 | 4 | 09/16/2025 | 09/16/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 635534 | 01810 | 5.76 |  |  | Solar |  | 05_12_52L1 | 09/04/2024 | 09/06/2024 | 3 | 1 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | METHUEN | 647458 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L2 | 10/22/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 2/19/2026 | Y | EXP | 365 | 04/08/2025 | 12/22/2025 | 259 | 12 | 247 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 568051 | 01453 | 0 |  |  | Solar |  | 05_14_59L6 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2024 | Connected |  | N
National Grid | WORCESTER | 261505 | 01604 | 0 |  |  | Solar |  | 05_14_74L3 | 10/22/2019 | 10/27/2019 | 3 | 0 | 3 | 10/28/2019 | 10/28/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 | 10/22/2019 | 11/15/2020 | Y | EXP | 365 | 04/25/2020 | 07/06/2020 | 72 | 0 | 72 |  |  | 2/8/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 340774 | 01550 | 25.52 |  |  | Solar |  | 05_01_219W1 | 02/09/2021 | 04/19/2021 | 47 | 46 | 1 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N
National Grid | GARDNER | 622781 | 01440 | 9.8 |  |  | Solar |  | 05_01_27W1 | 07/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | SWANSEA | 545544 | 02777 | 15.2 |  |  | Solar |  | 05_01_413L2 | 08/02/2023 | 08/09/2023 | 6 | 5 | 1 | 08/10/2023 | 08/10/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 08/02/2023 | 1/31/2025 | Y | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | MELROSE | 437898 | 02176 | 10 |  |  | Solar |  | 05_01_607W4 | 06/28/2022 |  | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 666526 | 01930 | 7.6 |  |  | Solar |  | 05_05_11W81 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/05/2025 | 4/23/2026 | Y | EXP | 365 | 05/29/2025 | 08/01/2025 | 65 | 0 | 65 |  |  | 8/11/2025 | Connected |  | N
National Grid | HAVERHILL | 175387 | 01832 | 90 |  |  | Solar |  | 05_12_25W5 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/15/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 1/15/2015 | Connected |  | N
National Grid | ANDOVER | 640394 | 01810 | 3 |  |  | Solar |  | 05_12_52L1 | 09/24/2024 | 11/26/2024 | 28 | 27 | 1 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 09/24/2024 | 3/18/2026 | Y | EXP | 365 | 04/24/2025 | 08/06/2025 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 671248 | 01841 | 5.76 |  |  | Solar |  | 05_14_43L2 | 02/10/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 70 | 25 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 594025 | 01453 | 10 |  |  | Solar |  | 05_14_59L6 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 270454 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 12/26/2019 | 01/06/2020 | 5 | 0 | 5 | 01/07/2020 | 01/07/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2020 | 12/26/2019 | 12/26/2020 | Y | EXP | 365 | 09/23/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 10/27/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 427478 | 01550 | 0 |  |  | Other |  | 05_01_219W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/14/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 625256 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 07/16/2024 | 07/29/2024 | 3 | 0 | 3 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | SWANSEA | 568896 | 02777 | 6 |  |  | Solar |  | 05_01_413L2 | 01/08/2024 | 01/23/2024 | 11 | 9 | 2 | 01/24/2024 | 01/24/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/08/2024 | 5/24/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | MELROSE | 527513 | 02176 | 10 |  |  | Solar |  | 05_01_607W4 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 671235 | 01930 | 3.8 |  |  | Solar |  | 05_05_11W81 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | METHUEN | 176038 | 01844 | 10 |  |  | Solar |  | 05_12_25W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 6/22/2016 | 6/22/2016 | 8/5/2016 | Connected |  | N
National Grid | ANDOVER | 643700 | 01810 | 5.76 |  |  | Solar |  | 05_12_52L1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 01/06/2025 | 02/11/2025 | 36 | 0 | 36 |  |  | 2/28/2025 | Connected |  | N
National Grid | METHUEN | 710789 | 01844 | 10 |  |  | Solar |  | 05_14_43L2 | 08/08/2025 | 10/20/2025 | 4 | 0 | 4 | 10/21/2025 | 10/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 | 08/08/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LEOMINSTER | 607739 | 01453 |  |  |  | Battery Add-On |  | 05_14_59L6 | 04/30/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | WORCESTER | 298830 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 701156 | 01550 | 6 |  |  | Solar |  | 05_01_219W1 | 06/25/2025 | 07/23/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 9/25/2026 | Y | EXP | 365 | 09/20/2025 | 09/19/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | WESTMINSTER | 625053 | 01473 | 3.8 |  |  | Solar |  | 05_01_27W1 | 07/16/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/16/2024 | 8/6/2025 | Y | EXP | 365 | 08/29/2024 | 08/28/2024 | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | SWANSEA | 601302 | 02777 | 10 |  |  | Solar |  | 05_01_413L2 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/04/2024 | 4/22/2025 | Y | EXP | 365 | 05/11/2024 | 06/04/2024 | 25 | 0 | 25 |  |  | 11/14/2024 | Connected |  | N
National Grid | MELROSE | 600531 | 02176 | 7.6 |  |  | Solar |  | 05_01_607W4 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 6/4/2025 | Y | EXP | 365 | 08/21/2024 | 09/09/2024 | 20 | 0 | 20 |  |  | 9/14/2024 | Connected |  | N
National Grid | GLOUCESTER | 700720 | 01930 | 15.2 |  |  | Solar |  | 05_05_11W81 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178553 | 01832 | 120 |  |  | Solar |  | 05_12_25W5 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 11/14/2019 | N | EXP | 393 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | ANDOVER | 645714 | 01810 | 10 |  |  | Solar |  | 05_12_52L1 | 10/10/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | LAWRENCE | 714209 | 01841 | 15.2 |  |  | Solar |  | 05_14_43L2 | 08/24/2025 | 09/17/2025 | 16 | 15 | 1 | 09/18/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 652980 | 01453 | 5.76 |  |  | Solar |  | 05_14_59L6 | 11/14/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | WORCESTER | 312794 | 01604 | 3.84 |  |  | Solar |  | 05_14_74L3 | 10/27/2020 |  | 61 | 26 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 682588 | 01550 | 11.866 |  |  | Solar |  | 05_01_219W2 | 04/10/2025 | 06/26/2025 | 7 | 3 | 4 | 07/15/2025 | 07/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | GARDNER | 625527 | 01440 | 5 |  |  | Solar |  | 05_01_27W1 | 07/18/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 602467 | 02777 | 9.88 |  |  | Solar |  | 05_01_413L2 | 04/12/2024 | 04/18/2024 | 3 | 0 | 3 | 04/19/2024 | 04/19/2024 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | MELROSE | 601448 | 02176 | 3.8 |  |  | Solar |  | 05_01_607W4 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | GLOUCESTER | 707625 | 01930 | 11.4 |  |  | Solar |  | 05_05_11W81 | 07/27/2025 | 08/21/2025 | 18 | 15 | 3 | 08/22/2025 | 08/22/2025 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 | 07/27/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | HAVERHILL | 195099 | 01832 | 7.6 |  |  | Solar |  | 05_12_25W5 | 09/05/2018 | 09/26/2018 | 3 | 3 | 0 | 09/27/2018 | 09/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 656918 | 01810 | 6.282 |  |  | Solar |  | 05_12_52L1 | 11/27/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 724254 | 01844 | 11.4 |  |  | Solar |  | 05_14_43L2 | 10/06/2025 | 12/18/2025 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LEOMINSTER | 679799 | 01453 | 3.8 |  |  | Solar |  | 05_14_59L6 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 318214 | 01604 | 6.38 |  |  | Solar |  | 05_14_74L3 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | STURBRIDGE | 696159 | 01566 | 5.76 |  |  | Solar |  | 05_01_219W2 | 06/11/2025 | 06/26/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 632259 | 01440 | 10 |  |  | Solar |  | 05_01_27W1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 609343 | 02777 | 3.8 |  |  | Solar |  | 05_01_413L2 | 05/07/2024 | 05/14/2024 | 5 | 0 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 10/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | MELROSE | 660589 | 02176 | 10 |  |  | Solar |  | 05_01_607W4 | 12/13/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/13/2024 | 2/21/2026 | Y | EXP | 365 | 05/08/2025 | 10/11/2025 | 157 | 0 | 157 |  |  | 11/21/2025 | Connected |  | N
National Grid | GLOUCESTER | 175614 | 01930 | 0 |  |  | Solar |  | 05_05_11W82 | 12/16/2014 | 12/16/2014 | 4 | 2 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2015 | 12/16/2014 | 4/30/2015 | Y | EXP | 97 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Terminated |  | N
National Grid | HAVERHILL | 192454 | 01832 | 10 |  |  | Solar |  | 05_12_25W5 | 08/02/2018 | 08/11/2018 | 2 | 2 | 0 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | Connected |  | N
National Grid | ANDOVER | 662099 | 01810 | 3.8 |  |  | Solar |  | 05_12_52L1 | 12/20/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 178362 | 01844 | 3.8 |  |  | Solar |  | 05_14_43L2 | 03/30/2018 | 03/30/2018 | 5 | 5 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 4/7/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 712505 | 01453 | 6.08 |  |  | Solar |  | 05_14_59L6 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | WORCESTER | 401100 | 01604 | 0 |  |  | Other |  | 05_14_74L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 715054 | 01550 | 7.6 |  |  | Solar |  | 05_01_219W2 | 09/10/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 634251 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 08/21/2024 | 09/18/2024 | 15 | 13 | 2 | 09/19/2024 | 09/19/2024 | 83 | 66 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | SOMERSET | 618333 | 02726 | 10 |  |  | Solar |  | 05_01_413L2 | 01/17/2025 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | MELROSE | 678299 | 02176 | 5.76 |  |  | Solar |  | 05_01_607W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 562551 | 01930 | 3125 |  |  | Solar |  | 05_05_11W82 | 02/20/2024 | 07/22/2024 | 105 | 96 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2024 | 09/04/2024 | 31 | 18 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 222080 | 01844 | 7.6 |  |  | Solar |  | 05_12_25W5 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 | 06/05/2019 | 9/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | ANDOVER | 668880 | 01810 | 3.8 |  |  | Solar |  | 05_12_52L1 | 02/03/2025 | 03/11/2025 | 14 | 9 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/03/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 11/24/2025 | 28 | 0 | 28 |  |  | 12/10/2025 | Connected |  | N
National Grid | METHUEN | 178551 | 01844 | 9 |  |  | Solar |  | 05_14_43L2 | 03/09/2018 | 03/09/2018 | 18 | 18 | 0 | 04/12/2018 | 04/12/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/18/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 607813 | 01453 | 175 |  |  | Solar |  | 05_14_5J11 | 05/01/2024 | 07/25/2024 | 59 | 52 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2024 | 08/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 461031 | 01604 | 6 |  |  | Solar |  | 05_14_74L3 | 09/28/2022 | 10/06/2022 | 6 | 3 | 3 | 10/07/2022 | 10/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 12/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | STURBRIDGE | 717728 | 01566 | 3.8 |  |  | Solar |  | 05_01_219W2 | 09/09/2025 | 09/23/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 09/09/2025 | 12/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GARDNER | 636951 | 01440 | 3.8 |  |  | Solar |  | 05_01_27W1 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 624915 | 02777 | 7.6 |  |  | Solar |  | 05_01_413L2 | 07/15/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 699431 | 02176 | 18.48 |  |  | Solar |  | 05_01_607W4 | 07/02/2025 | 07/24/2025 | 14 | 10 | 4 | 07/25/2025 | 07/25/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | GLOUCESTER | 639826 | 01930 | 240 |  |  | Solar |  | 05_05_11W82 | 04/02/2025 | 04/29/2025 | 18 | 8 | 10 | 04/30/2025 | 04/30/2025 | 56 | 31 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 269791 | 01844 | 3 |  |  | Solar |  | 05_12_25W5 | 12/20/2019 | 01/02/2020 | 6 | 0 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | AMESBURY | 715316 | 01913 | 20 |  |  | Solar |  | 05_12_52L1 | 08/28/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | METHUEN | 178603 | 01844 | 3.8 |  |  | Solar |  | 05_14_43L2 | 04/09/2018 | 04/09/2018 | 13 | 0 | 13 | 04/27/2018 | 04/27/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 | 04/09/2018 | 11/29/2019 | Y | EXP | 568 | 09/12/2019 | 10/15/2019 | 33 | 0 | 33 |  |  | 10/23/2019 | Connected |  | N
National Grid | LEOMINSTER | 174139 | 01453 | 22.8 |  |  | Solar |  | 05_14_5J11 | 04/10/2012 | 04/10/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2012 |  | 6/1/2012 | N | EXP | -60 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 11/19/2012 | Connected |  | N
National Grid | WORCESTER | 460980 | 01604 | 3.8 |  |  | Solar |  | 05_14_74L3 | 09/29/2022 | 10/10/2022 | 7 | 3 | 4 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 09/29/2022 | 7/19/2024 | Y | EXP | 390 | 01/24/2023 | 02/01/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 729072 | 01566 | 11.5 |  |  | Solar |  | 05_01_219W2 | 11/04/2025 | 11/10/2025 | 4 | 0 | 4 | 11/12/2025 | 11/12/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GARDNER | 636882 | 01440 | 10 |  |  | Solar |  | 05_01_27W1 | 08/30/2024 | 09/11/2024 | 1 | 0 | 1 | 09/12/2024 | 09/12/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 641629 | 02726 | 10 |  |  | Solar |  | 05_01_413L2 | 10/02/2024 | 10/23/2024 | 7 | 4 | 3 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 1/3/2026 | Y | EXP | 365 | 06/11/2025 | 07/30/2025 | 50 | 0 | 50 |  |  | 10/7/2025 | Connected |  | N
National Grid | MELROSE | 707825 | 02176 | 18.81 |  |  | Solar |  | 05_01_607W4 | 07/28/2025 | 08/01/2025 | 4 | 0 | 4 | 08/04/2025 | 08/04/2025 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 725092 | 01930 | 7.6 |  |  | Solar |  | 05_05_11W82 | 10/08/2025 | 10/30/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 294223 | 01844 | 0 |  |  | Solar |  | 05_12_25W5 | 06/01/2020 | 06/04/2020 | 3 | 3 | 0 | 06/05/2020 | 06/05/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2020 | Connected |  | N
National Grid | AMESBURY | 644938 | 01913 | 4.225 |  |  | Solar |  | 05_12_5C2 | 10/03/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/03/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 194175 | 01844 | 65 |  |  | Solar |  | 05_14_43L2 | 08/23/2018 | 10/16/2018 | 35 | 0 | 35 | 10/17/2018 | 10/17/2018 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176451 | 01453 | 52.8 |  |  | Solar |  | 05_14_5J11 | 12/08/2015 | 12/08/2015 | 7 | 7 | 0 | 12/17/2015 | 12/17/2015 | 122 | 0 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 468024 | 01604 | 10 |  |  | Solar |  | 05_14_74L3 | 10/20/2022 | 10/24/2022 | 2 | 0 | 2 | 10/25/2022 | 10/25/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 733103 | 01550 | 10 |  |  | Solar |  | 05_01_219W2 | 11/12/2025 | 12/26/2025 | 2 | 0 | 2 | 12/29/2025 | 12/29/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 654101 | 01440 | 11.89 |  |  | Solar |  | 05_01_27W1 | 11/25/2024 | 01/14/2025 | 19 | 17 | 2 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | Y
National Grid | SOMERSET | 647245 | 02726 | 5.76 |  |  | Solar |  | 05_01_413L2 | 10/15/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/15/2024 | 12/23/2025 | Y | EXP | 365 | 08/22/2025 | 08/28/2025 | 7 | 0 | 7 |  |  | 9/15/2025 | Connected |  | N
National Grid | MELROSE | 385049 | 02176 | 4920 |  |  | Solar |  | 05_01_609W1 | 10/29/2021 | 12/02/2021 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MALDEN | 172587 | 02148 | 3.8 |  |  | Solar |  | 05_05_11W82 | 05/22/2018 | 05/22/2018 | 11 | 2 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 | 05/22/2018 | 7/12/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | Connected |  | N
National Grid | METHUEN | 334088 | 01844 | 10 |  |  | Solar |  | 05_12_25W5 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | AMESBURY | 174340 | 01913 | 50 |  |  | Solar |  | 05_12_5C5 | 12/13/2011 | 12/13/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2012 |  | 3/30/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 7/18/2012 | Connected |  | N
National Grid | LAWRENCE | 305828 | 01841 | 9.6 |  |  | Solar |  | 05_14_43L2 | 08/10/2020 | 09/15/2020 | 25 | 23 | 2 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | LEOMINSTER | 177462 | 01453 | 43.2 |  |  | Solar |  | 05_14_5J11 | 12/12/2016 | 12/12/2016 | 7 | 7 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/17/2017 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N
National Grid | WORCESTER | 475239 | 01604 | 7.6 |  |  | Solar |  | 05_14_74L3 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 174697 | 01550 | 2000 |  |  | Solar |  | 05_01_219W2 | 12/31/2012 | 12/31/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2013 | 03/20/2013 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2014 | 12/31/2012 | 1/31/2014 | Y | STD | -67 | 12/26/2014 | 04/14/2015 | 73 | 0 | 73 | 4/9/2015 | 4/9/2015 | 4/9/2015 | Connected |  | N
National Grid | WESTMINSTER | 656846 | 01473 | 6 |  |  | Solar |  | 05_01_27W1 | 11/26/2024 | 03/20/2025 | 21 | 16 | 5 | 02/24/2025 | 02/24/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/26/2024 | 4/14/2026 | Y | EXP | 365 | 06/24/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 7/22/2025 | Connected |  | N
National Grid | SOMERSET | 648427 | 02726 | 3.8 |  |  | Solar |  | 05_01_413L2 | 11/07/2024 | 11/21/2024 | 4 | 0 | 4 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 11/07/2024 | 2/18/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | MELROSE | 617857 | 02176 | 4999 |  |  | Solar |  | 05_01_609W1 | 08/14/2024 | 11/14/2024 | 65 | 55 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 05/09/2025 | 119 | 98 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MALDEN | 176184 | 02148 | 1143 |  |  | Solar |  | 05_05_11W82 | 08/28/2015 | 08/28/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 12/17/2015 | 71 | 37 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2016 | 08/28/2015 | 9/6/2016 | Y | STD | 138 | 08/11/2016 | 11/07/2016 | 60 | 0 | 60 | 6/27/2017 | 6/27/2017 | 5/17/2017 | Connected |  | N
National Grid | HAVERHILL | 376077 | 01832 | 15.2 |  |  | Solar |  | 05_12_25W5 | 09/06/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 9/13/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 185756 | 01913 | 150 |  |  | Solar |  | 05_12_5J10 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/31/2018 | 05/31/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2018 |  | 12/2/2019 | N | EXP | 536 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | LAWRENCE | 364023 | 01841 | 9.8 |  |  | Solar |  | 05_14_43L2 | 06/28/2021 | 12/15/2021 | 1 | 0 | 1 | 06/30/2021 | 06/30/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 | 06/28/2021 | 12/26/2023 | Y | EXP | 365 | 01/18/2022 | 07/26/2022 | 189 | 0 | 189 |  |  | 8/3/2023 | Connected |  | N
National Grid | LEOMINSTER | 195497 | 01453 | 7.6 |  |  | Solar |  | 05_14_5J11 | 09/10/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 09/10/2018 | 10/30/2020 | Y | EXP | 400 | 02/14/2020 | 02/18/2020 | 4 | 0 | 4 |  |  | 5/4/2020 | Connected |  | N
National Grid | WORCESTER | 505172 | 01604 | 6 |  |  | Solar |  | 05_14_74L3 | 03/09/2023 | 03/16/2023 | 5 | 0 | 5 | 03/17/2023 | 03/17/2023 | 23 | 0 | 23 | 04/27/2023 | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175935 | 01550 | 10 |  |  | Solar |  | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 2 | 2 | 08/12/2015 | 08/12/2015 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 658492 | 01452 | 7.6 |  |  | Solar |  | 05_01_27W1 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | SOMERSET | 655030 | 02726 | 8.99 |  |  | Solar |  | 05_01_413L2 | 11/18/2024 | 03/10/2025 | 26 | 25 | 1 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | MELROSE | 629414 | 02176 | 4980 |  |  | Solar |  | 05_01_609W1 | 09/23/2024 | 12/05/2024 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2024 | 02/10/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MALDEN | 176875 | 02148 | 7.6 |  |  | Solar |  | 05_05_11W82 | 03/02/2016 | 03/02/2016 | 30 | 30 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 03/02/2016 | 3/7/2017 | Y | EXP | 315 | 09/06/2016 | 09/21/2016 | 11 | 0 | 11 | 11/4/2016 | 11/4/2016 | 11/9/2016 | Connected |  | N
National Grid | HAVERHILL | 410315 | 01832 | 8.99 |  |  | Solar |  | 05_12_25W5 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | AMESBURY | 587973 | 01913 | 550 |  |  | Natural Gas |  | 05_12_5J9 | 02/28/2024 | 08/06/2024 | 110 | 101 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 378895 | 01841 | 6 |  |  | Solar |  | 05_14_43L2 | 09/16/2021 | 12/21/2021 | 3 | 0 | 3 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2022 | Connected |  | Y
National Grid | LEOMINSTER | 191148 | 01453 | 6.96 |  |  | Solar |  | 05_14_5J11 | 07/19/2018 | 07/31/2018 | 0 | 0 | 0 | 08/01/2018 | 08/01/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 7/31/2019 | N | EXP | 309 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | Connected |  | N
National Grid | WORCESTER | 516649 | 01604 | 10 |  |  | Solar |  | 05_14_74L3 | 05/19/2023 | 05/22/2023 | 2 | 1 | 1 | 05/23/2023 | 05/23/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 05/19/2023 | 8/16/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 2/28/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 176076 | 01550 | 10 |  |  | Solar |  | 05_01_219W2 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/20/2015 | 08/20/2015 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/25/2016 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 662937 | 01473 | 7.6 |  |  | Solar |  | 05_01_27W1 | 12/30/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | SOMERSET | 688130 | 02726 | 7.6 |  |  | Solar |  | 05_01_609W1 | 04/28/2025 | 07/10/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MELROSE | 178007 | 02176 | 15 |  |  | Solar |  | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2017 |  | 5/3/2018 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/7/2017 | Connected |  | N
National Grid | MALDEN | 437932 | 02148 | 9.984 |  |  | Solar |  | 05_12_25W5 | 06/15/2022 | 06/24/2022 | 3 | 1 | 2 | 06/30/2022 | 06/30/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | HAVERHILL | 667538 | 01832 | 7.6 |  |  | Solar |  | 05_12_64J1 | 01/31/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 120 | 104 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | AMESBURY | 396668 | 01913 | 0 |  |  | Other |  | 05_14_43L2 | 01/04/2022 | 01/14/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 451807 | 01841 | 10 |  |  | Solar |  | 05_14_5J11 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/20/2022 | 11/23/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2023 | Connected |  | N
National Grid | LEOMINSTER | 539231 | 01453 | 5.76 |  |  | Solar |  | 05_14_74L3 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 11/13/2024 | N | EXP | 365 | 04/17/2024 | 05/28/2024 | 42 | 0 | 42 |  |  | 6/10/2024 | Connected |  | N
National Grid | WORCESTER | 176257 | 01604 | 252 |  |  | Solar |  | 05_01_219W2 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 | 09/07/2015 | 09/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2015 | 09/03/2015 | 9/12/2016 | Y | EXP | 354 | 06/22/2016 | 08/30/2016 | 48 | 0 | 48 | 9/24/2015 | 9/24/2015 | 10/7/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 668077 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W1 | 01/27/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WESTMINSTER | 658241 | 01473 | 5.76 |  |  | Solar |  | 05_01_413L2 | 12/03/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | SWANSEA | 708824 | 02777 | 7.6 |  |  | Solar |  | 05_01_609W1 | 09/08/2025 | 09/23/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/08/2025 | 11/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MELROSE | 178006 | 02176 | 20 |  |  | Solar |  | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2017 |  | 5/3/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/8/2017 | Connected |  | N
National Grid | MEDFORD | 530600 | 02155 | 0 |  |  | Solar |  | 05_12_25W5 | 10/09/2023 | 06/13/2023 | 5 | 4 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 11/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | METHUEN | 561812 | 01844 | 6.3 |  |  | Solar |  | 05_12_64J1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | AMESBURY | 400900 | 01913 | 16.53 |  |  | Solar |  | 05_14_43L2 | 02/01/2022 | 02/03/2022 | 2 | 0 | 2 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 6/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | METHUEN | 727510 | 01844 | 11.5 |  |  | Solar |  | 05_14_5J11 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 544833 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 08/16/2023 | 08/21/2023 | 3 | 0 | 3 | 08/22/2023 | 08/22/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 9/24/2024 | Y | EXP | 365 | 03/26/2024 | 04/23/2024 | 29 | 0 | 29 |  |  | 6/1/2024 | Connected |  | N
National Grid | WORCESTER | 176439 | 01604 | 10 |  |  | Solar |  | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 0 | 4 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 3/17/2016 | 3/17/2016 | 7/19/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 679786 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W1 | 03/21/2025 | 06/03/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 44 | 32 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 658103 | 01473 | 7.6 |  |  | Solar |  | 05_01_413L2 | 12/03/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 716246 | 02777 | 3.8 |  |  | Solar |  | 05_01_609W1 | 09/03/2025 | 09/22/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MELROSE | 263922 | 02176 | 8.7 |  |  | Solar |  | 05_05_11W82 | 11/15/2019 | 11/18/2019 | 0 | 0 | 0 | 11/19/2019 | 11/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/15/2019 | 7/22/2020 | Y | EXP | 365 | 01/10/2020 | 02/26/2020 | 46 | 0 | 46 |  |  | 2/27/2020 | Connected |  | N
National Grid | MEDFORD | 545446 | 02155 | 6 |  |  | Solar |  | 05_12_25W5 | 08/08/2023 | 08/11/2023 | 3 | 0 | 3 | 08/14/2023 | 08/14/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 9/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2023 | Connected |  | N
National Grid | METHUEN | 562644 | 01844 | 2.52 |  |  | Solar |  | 05_12_64J1 | 12/13/2023 | 12/20/2023 | 5 | 3 | 2 | 12/21/2023 | 12/21/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | AMESBURY | 406366 | 01913 | 470 |  |  | Solar |  | 05_14_43L2 | 01/28/2022 | 05/02/2022 | 64 | 54 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2023 | 01/28/2022 | 8/27/2024 | Y | STD | 209 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | METHUEN | 616963 | 01844 | 6 |  |  | Solar |  | 05_14_5J12 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2024 | Connected |  | N
National Grid | LEOMINSTER | 544120 | 01453 | 5.04 |  |  | Solar |  | 05_14_74L3 | 09/05/2023 | 09/06/2023 | 1 | 0 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 | 10/24/2023 | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 11/29/2024 | N | EXP | 365 | 02/01/2024 | 04/19/2024 | 79 | 0 | 79 |  |  | 5/6/2024 | Connected |  | N
National Grid | WORCESTER | 176738 | 01604 | 900 |  |  | Solar |  | 05_01_219W2 | 10/29/2015 | 10/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 12/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/4/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 701051 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W1 | 06/25/2025 | 07/10/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 | 06/25/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 659432 | 01473 | 7.68 |  |  | Solar |  | 05_01_413L2 | 12/10/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 174268 | 02777 | 300 |  |  | Solar |  | 05_01_609W1 | 12/26/2011 | 12/26/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 271016 | 02176 | 999 |  |  | Solar |  | 05_05_11W82 | 01/06/2020 | 01/17/2020 | 9 | 7 | 2 |  |  | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 560633 | 02155 | 9.57 |  |  | Solar |  | 05_12_25W5 | 10/04/2023 | 10/05/2023 | 2 | 1 | 1 | 10/06/2023 | 10/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2024 | Connected |  | N
National Grid | HAVERHILL | 637288 | 01832 | 6.98 |  |  | Solar |  | 05_12_64J1 | 09/03/2024 | 12/19/2024 | 29 | 23 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 09/03/2024 | 2/10/2026 | Y | EXP | 365 | 05/07/2025 | 08/06/2025 | 92 | 0 | 92 |  |  | 8/15/2025 | Connected |  | N
National Grid | AMESBURY | 425587 | 01913 | 498 |  |  | Solar |  | 05_14_43L2 | 08/31/2022 | 09/20/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2022 | 10/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 201623 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J13 | 11/19/2018 |  | 197 | 26 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 547080 | 01453 | 6 |  |  | Solar |  | 05_14_74L3 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 11/14/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 3/18/2024 | Connected |  | N
National Grid | WORCESTER | 176747 | 01604 | 3 |  |  | Solar |  | 05_01_219W2 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 4/2/2017 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 177653 | 01550 | 464 |  |  | Solar |  | 05_01_27W2 | 09/29/2017 | 09/29/2017 | 14 | 8 | 6 | 10/20/2017 | 10/20/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 659732 | 01473 | 7.6 |  |  | Solar |  | 05_01_413L2 | 12/10/2024 | 01/01/2025 | 5 | 0 | 5 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/10/2024 | 2/20/2026 | Y | EXP | 365 | 04/30/2025 | 08/04/2025 | 97 | 0 | 97 |  |  | 9/8/2025 | Connected |  | N
National Grid | SOMERSET | 174322 | 02726 | 1125 |  |  | Solar |  | 05_01_609W1 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/23/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 412047 | 02176 | 0 |  |  | Other |  | 05_05_11W82 | 03/30/2022 | 04/21/2022 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2022 | 04/21/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 603372 | 02155 | 7.54 |  |  | Solar |  | 05_12_25W5 | 04/19/2024 | 05/07/2024 | 13 | 11 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | HAVERHILL | 357707 | 01832 | 66.6 |  |  | Solar |  | 05_12_64J2 | 05/17/2021 | 05/11/2022 | 248 | 244 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 05/17/2021 | 7/11/2024 | Y | EXP | 90 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | AMESBURY | 433206 | 01913 | 10 |  |  | Solar |  | 05_14_43L2 | 06/07/2022 | 06/09/2022 | 2 | 0 | 2 | 06/10/2022 | 06/10/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 | 06/07/2022 | 10/20/2023 | Y | EXP | 365 | 09/28/2022 | 10/19/2022 | 22 | 0 | 22 |  |  | 11/17/2022 | Connected |  | N
National Grid | LAWRENCE | 203345 | 01841 | 13.8 |  |  | Solar |  | 05_14_5J13 | 12/21/2018 | 01/25/2019 | 22 | 22 | 0 | 01/25/2019 | 01/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 | 12/21/2018 | 3/26/2020 | Y | EXP | 422 | 10/18/2019 | 02/21/2020 | 126 | 0 | 126 |  |  | 2/25/2020 | Connected |  | N
National Grid | LEOMINSTER | 551612 | 01453 | 6.09 |  |  | Solar |  | 05_14_74L3 | 09/05/2023 | 09/25/2023 | 15 | 14 | 1 | 09/26/2023 | 09/26/2023 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 | 09/05/2023 | 2/9/2025 | Y | EXP | 365 | 01/31/2024 | 03/22/2024 | 52 | 0 | 52 |  |  | 6/13/2024 | Connected |  | N
National Grid | WORCESTER | 177417 | 01605 | 7.6 |  |  | Solar |  | 05_01_219W2 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 | 11/29/2016 | 12/6/2017 | Y | EXP | 365 | 07/25/2017 | 09/26/2017 | 44 | 0 | 44 | 10/23/2017 | 10/23/2017 | 10/20/2017 | Connected |  | N
National Grid | STURBRIDGE | 193702 | 01566 | 832.5 |  |  | Solar |  | 05_01_27W2 | 09/18/2018 | 10/31/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 04/01/2019 | 101 | 82 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 09/18/2018 | 4/25/2024 | Y | STD | 1142 | 05/18/2023 | 04/22/2024 | 339 | 144 | 195 |  |  | 4/15/2024 | Connected |  | N
National Grid | HUBBARDSTON | 673435 | 01452 | 5.76 |  |  | Solar |  | 05_01_413L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | SWANSEA | 174685 | 02777 | 7.6 |  |  | Solar |  | 05_01_609W1 | 03/09/2011 | 03/09/2011 | 423 | 60 | 363 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 416604 | 02176 | 250 |  |  | Solar |  | 05_05_11W82 | 04/04/2022 | 04/11/2022 | 5 | 0 | 5 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/04/2022 | 3/25/2025 | Y | STD | 455 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | MEDFORD | 623061 | 02155 | 6 |  |  | Solar |  | 05_12_25W5 | 07/08/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 661943 | 01844 | 5.76 |  |  | Solar |  | 05_12_64J3 | 12/20/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | AMESBURY | 443275 | 01913 | 15.2 |  |  | Solar |  | 05_14_43L2 | 07/11/2022 | 07/13/2022 | 2 | 0 | 2 | 07/14/2022 | 07/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | METHUEN | 290419 | 01844 | 10 |  |  | Solar |  | 05_14_5J13 | 05/04/2020 | 05/06/2020 | 2 | 2 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2020 | Connected |  | N
National Grid | LEOMINSTER | 560972 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L3 | 10/05/2023 | 05/07/2024 | 2 | 0 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 10/05/2023 | 6/12/2025 | Y | EXP | 365 | 07/31/2024 | 09/30/2024 | 62 | 0 | 62 |  |  | 10/17/2024 | Connected |  | N
National Grid | WORCESTER | 178627 | 01605 | 7.6 |  |  | Solar |  | 05_01_219W2 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/21/2019 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 197375 | 01550 | 10 |  |  | Solar |  | 05_01_27W2 | 10/08/2018 | 10/29/2018 | 13 | 13 | 0 | 10/30/2018 | 10/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 677981 | 01473 | 10 |  |  | Solar |  | 05_01_413L2 | 03/13/2025 | 09/15/2025 | 118 | 25 | 93 | 09/16/2025 | 09/16/2025 | 53 | 52 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 174973 | 02726 | 91.2 |  |  | Solar |  | 05_01_609W1 | 09/26/2011 | 09/26/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | -12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 424766 | 02176 | 7.6 |  |  | Solar |  | 05_05_11W82 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2022 | Connected |  | Y
National Grid | MEDFORD | 644273 | 02155 | 5.76 |  |  | Solar |  | 05_12_25W5 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | HAVERHILL | 664919 | 01832 | 10 |  |  | Solar |  | 05_12_64J3 | 01/10/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 562970 | 01913 | 10 |  |  | Solar |  | 05_14_43L2 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 34 | 12 | 22 | 02/13/2024 | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 | 05/22/2024 | 01/31/2025 | 267 | 0 | 267 |  |  | 1/31/2025 | Connected |  | N
National Grid | LAWRENCE | 525541 | 01841 | 15 |  |  | Solar |  | 05_14_5J13 | 05/10/2023 | 05/12/2023 | 2 | 0 | 2 | 05/15/2023 | 05/15/2023 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y
National Grid | LEOMINSTER | 567261 | 01453 | 5 |  |  | Solar |  | 05_14_74L3 | 03/28/2024 | 12/26/2023 | 12 | 9 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 5/23/2025 | Y | EXP | 365 | 06/05/2024 | 08/20/2024 | 77 | 0 | 77 |  |  | 10/11/2024 | Connected |  | N
National Grid | WORCESTER | 200671 | 01605 | 7.6 |  |  | Solar |  | 05_01_219W2 | 11/07/2018 | 12/17/2018 | 21 | 13 | 8 | 12/18/2018 | 12/18/2018 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 495536 | 01550 | 11.4 |  |  | Solar |  | 05_01_27W2 | 02/04/2023 | 02/06/2023 | 26 | 25 | 1 | 03/14/2023 | 03/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | N
National Grid | WESTMINSTER | 688350 | 01473 | 10 |  |  | Solar |  | 05_01_413L2 | 04/29/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/29/2025 | 8/4/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 12/3/2025 | Connected |  | N
National Grid | SOMERSET | 175522 | 02726 | 499 |  |  | Solar |  | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | MELROSE | 429706 | 02176 | 240 |  |  | Solar |  | 05_05_11W82 | 06/01/2022 | 06/30/2022 | 20 | 15 | 5 | 07/01/2022 | 07/01/2022 | 524 | 500 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERVILLE | 652699 | 02145 | 5.76 |  |  | Solar |  | 05_12_25W5 | 11/07/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/07/2024 | 2/14/2026 | Y | EXP | 365 | 07/02/2025 | 10/11/2025 | 102 | 0 | 102 |  |  | 11/14/2025 | Connected |  | N
National Grid | HAVERHILL | 195969 | 01832 | 240 |  |  | Solar |  | 05_12_64J4 | 10/04/2018 | 10/26/2018 | 15 | 15 | 0 | 10/29/2018 | 10/29/2018 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2019 |  | 12/16/2019 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | AMESBURY | 622796 | 01913 | 7.6 |  |  | Solar |  | 05_14_43L2 | 07/05/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 07/05/2024 | 11/24/2025 | Y | EXP | 365 | 09/19/2024 | 12/02/2024 | 75 | 0 | 75 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 625454 | 01841 | 10 |  |  | Solar |  | 05_14_5J13 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/17/2024 | 10/8/2025 | Y | EXP | 365 | 11/13/2024 | 01/13/2025 | 62 | 0 | 62 |  |  | 1/30/2025 | Connected |  | N
National Grid | LEOMINSTER | 580225 | 01453 | 5.8 |  |  | Solar |  | 05_14_74L3 | 01/11/2024 | 01/22/2024 | 7 | 6 | 1 | 01/23/2024 | 01/23/2024 | 88 | 71 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 01/11/2024 | 6/4/2025 | Y | EXP | 365 | 09/19/2024 | 11/06/2024 | 49 | 0 | 49 |  |  | 11/19/2024 | Connected |  | N
National Grid | WORCESTER | 211055 | 01605 | 50 |  |  | Solar |  | 05_01_219W2 | 02/22/2019 | 03/11/2019 | 10 | 7 | 3 | 03/12/2019 | 03/12/2019 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 500916 | 01550 | 100 |  |  | Solar |  | 05_01_27W2 | 02/24/2023 | 04/07/2023 | 31 | 21 | 10 | 04/10/2023 | 04/10/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 705879 | 01473 | 10 |  |  | Solar |  | 05_01_413L2 | 07/18/2025 | 08/04/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 07/18/2025 | 9/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | SOMERSET | 175521 | 02726 | 499 |  |  | Solar |  | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 12/5/2017 | 12/5/2017 | 3/19/2018 | Connected |  | N
National Grid | MELROSE | 443979 | 02176 | 0 |  |  | Other |  | 05_05_11W82 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 684394 | 02155 | 7.6 |  |  | Solar |  | 05_12_25W5 | 04/10/2025 | 05/30/2025 | 1 | 0 | 1 | 06/02/2025 | 06/02/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 223134 | 01844 | 106 |  |  | Solar |  | 05_12_64J5 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 |  | 6/21/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | AMESBURY | 632056 | 01913 | 7.6 |  |  | Solar |  | 05_14_43L2 | 08/13/2024 | 09/24/2024 | 8 | 3 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 08/13/2024 | 12/31/2025 | Y | EXP | 365 | 01/25/2025 | 09/12/2025 | 231 | 0 | 231 |  |  | 11/7/2025 | Connected |  | N
National Grid | LAWRENCE | 177256 | 01841 | 43.2 |  |  | Solar |  | 05_14_5J15 | 08/17/2016 | 08/17/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 8/22/2017 | N | EXP | 321 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | LEOMINSTER | 586831 | 01453 | 7.83 |  |  | Solar |  | 05_14_74L3 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 7/24/2025 | Y | EXP | 465 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WORCESTER | 283064 | 01605 | 7.6 |  |  | Solar |  | 05_01_219W2 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 8/11/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 11 | 0 | 11 |  |  | 2/25/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 648354 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W2 | 10/30/2024 | 05/05/2025 | 3 | 1 | 2 | 05/06/2025 | 05/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 585545 | 01473 | 498 |  |  | Solar |  | 05_01_413L3 | 02/14/2024 | 05/01/2024 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 175523 | 02726 | 499 |  |  | Solar |  | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | MELROSE | 468426 | 02176 | 10 |  |  | Solar |  | 05_05_11W82 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | MEDFORD | 704751 | 02155 | 15.2 |  |  | Solar |  | 05_12_26L1 | 07/14/2025 | 07/15/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 394755 | 01832 | 0 |  |  | Solar |  | 05_12_64J5 | 12/16/2021 | 01/05/2022 | 13 | 10 | 3 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2022 |  | 3/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | AMESBURY | 637795 | 01913 | 10 |  |  | Solar |  | 05_14_43L2 | 09/04/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/04/2024 | 11/2/2025 | Y | EXP | 365 | 12/19/2024 | 03/15/2025 | 86 | 0 | 86 |  |  | 3/22/2025 | Connected |  | N
National Grid | LAWRENCE | 299817 | 01841 | 7.6 |  |  | Solar |  | 05_14_5J15 | 02/04/2021 | 02/08/2021 | 1 | 0 | 1 | 02/09/2021 | 02/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 597076 | 01453 | 8.12 |  |  | Solar |  | 05_14_74L3 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 285851 | 01605 | 6 |  |  | Solar |  | 05_01_219W2 | 04/22/2020 | 04/27/2020 | 3 | 1 | 2 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/22/2020 | 4/28/2022 | Y | EXP | 365 | 05/07/2021 | 06/23/2021 | 47 | 0 | 47 |  |  | 9/24/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 666140 | 01550 | 5.76 |  |  | Solar |  | 05_01_27W2 | 01/16/2025 | 02/04/2025 | 8 | 4 | 4 | 02/05/2025 | 02/05/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 649017 | 01473 | 7.6 |  |  | Solar |  | 05_01_413L3 | 11/04/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/04/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 175773 | 02726 | 480 |  |  | Solar |  | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 475485 | 01983 | 15.08 |  |  | Solar |  | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 711334 | 02155 | 11.5 |  |  | Battery Add-On |  | 05_12_26L1 | 08/12/2025 | 08/18/2025 | 4 | 0 | 4 | 08/19/2025 | 08/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 177360 | 01844 | 43.2 |  |  | Solar |  | 05_12_67J3 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/28/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/23/2017 | 5/23/2017 | 5/23/2017 | Connected |  | N
National Grid | AMESBURY | 647179 | 01913 | 5.12 |  |  | Solar |  | 05_14_43L2 | 10/15/2024 | 10/25/2024 | 4 | 1 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 10/15/2024 | 12/12/2025 | Y | EXP | 365 | 02/14/2025 | 04/28/2025 | 74 | 0 | 74 |  |  | 4/30/2025 | Connected |  | N
National Grid | METHUEN | 307055 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J15 | 08/28/2020 | 08/31/2020 | 0 | 0 | 0 | 09/01/2020 | 09/01/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 | 08/28/2020 | 8/30/2021 | Y | EXP | 365 | 12/19/2020 | 01/21/2021 | 33 | 0 | 33 |  |  | 5/25/2021 | Connected |  | N
National Grid | LEOMINSTER | 607376 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L3 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/30/2024 | 6/4/2025 | Y | EXP | 365 | 07/31/2024 | 10/01/2024 | 63 | 0 | 63 |  |  | 10/8/2024 | Connected |  | N
National Grid | WORCESTER | 341966 | 01605 | 3.8 |  |  | Solar |  | 05_01_219W2 | 02/22/2021 | 02/23/2021 | 0 | 0 | 0 | 02/24/2021 | 02/24/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  | 2/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 670172 | 01571 | 10 |  |  | Solar |  | 05_01_27W2 | 02/05/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | HUBBARDSTON | 669716 | 01452 | 0 |  |  | Other |  | 05_01_413L3 | 03/07/2025 | 03/31/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 175772 | 02726 | 480 |  |  | Solar |  | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 475488 | 01983 | 15.08 |  |  | Solar |  | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 717527 | 02176 | 18.85 |  |  | Solar |  | 05_12_26L1 | 09/08/2025 | 09/18/2025 | 6 | 2 | 4 | 09/19/2025 | 09/19/2025 | 71 | 55 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 327303 | 01832 | 43.2 |  |  | Solar |  | 05_12_67J3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 3/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 649032 | 01913 | 13.975 |  |  | Solar |  | 05_14_43L2 | 10/22/2024 | 11/05/2024 | 10 | 7 | 3 | 11/06/2024 | 11/06/2024 | 61 | 25 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | METHUEN | 533655 | 01844 | 10 |  |  | Solar |  | 05_14_5J16 | 06/20/2023 | 06/28/2023 | 6 | 4 | 2 | 06/29/2023 | 06/29/2023 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/20/2023 | 9/28/2024 | Y | EXP | 365 | 01/04/2024 | 01/18/2024 | 15 | 0 | 15 |  |  | 1/29/2024 | Connected |  | N
National Grid | LEOMINSTER | 619623 | 01453 | 6 |  |  | Solar |  | 05_14_74L3 | 06/21/2024 | 07/02/2024 | 3 | 0 | 3 | 07/03/2024 | 07/03/2024 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 352779 | 01605 | 5.76 |  |  | Solar |  | 05_01_219W2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 685699 | 01550 | 5.76 |  |  | Solar |  | 05_01_27W2 | 04/28/2025 | 05/13/2025 | 7 | 2 | 5 | 06/12/2025 | 06/12/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | HUBBARDSTON | 674825 | 01452 | 7.6 |  |  | Solar |  | 05_01_413L3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 175836 | 02726 | 990 |  |  | Solar |  | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 510632 | 01983 | 30 |  |  | Solar |  | 05_05_11W82 | 05/14/2023 | 05/30/2023 | 11 | 2 | 9 | 05/31/2023 | 05/31/2023 | 66 | 42 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 |  | 11/29/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | MELROSE | 175550 | 02176 | 33.3 |  |  | Solar |  | 05_12_26L1 | 04/11/2014 | 04/11/2014 | 6 | 0 | 6 | 04/23/2014 | 04/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 8/29/2014 | N | EXP | 108 |  |  | 0 | 0 | 0 | 6/17/2014 | 6/17/2014 | 9/2/2014 | Connected |  | N
National Grid | METHUEN | 349034 | 01844 | 9.8 |  |  | Solar |  | 05_12_67J4 | 04/15/2021 | 04/19/2021 | 1 | 0 | 1 | 04/20/2021 | 04/20/2021 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 11/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2021 | Connected |  | N
National Grid | AMESBURY | 650321 | 01913 | 10 |  |  | Solar |  | 05_14_43L2 | 11/07/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LAWRENCE | 677063 | 01841 | 100 |  |  | Solar |  | 05_14_5J40 | 03/31/2025 | 05/06/2025 | 25 | 16 | 9 | 05/07/2025 | 05/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 | 03/31/2025 | 2/1/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 627966 | 01453 | 5.22 |  |  | Solar |  | 05_14_74L3 | 07/26/2024 | 09/05/2024 | 19 | 18 | 1 | 09/06/2024 | 09/06/2024 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 451693 | 01605 | 6 |  |  | Solar |  | 05_01_219W2 | 08/25/2022 | 08/30/2022 | 3 | 0 | 3 | 08/31/2022 | 08/31/2022 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 378510 | 01571 | 3000 |  |  | Natural Gas |  | 05_01_27W3 | 04/12/2022 | 05/16/2022 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2022 | 06/15/2022 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 04/12/2022 | 2/10/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HUBBARDSTON | 680048 | 01452 | 10 |  |  | Solar |  | 05_01_413L3 | 03/26/2025 | 04/30/2025 | 24 | 22 | 2 | 05/01/2025 | 05/01/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 175834 | 02726 | 990 |  |  | Solar |  | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 616104 | 01983 | 250 |  |  | Solar |  | 05_05_11W82 | 08/08/2024 | 02/05/2025 | 120 | 110 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2025 | 03/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 177483 | 02148 | 19 |  |  | Solar |  | 05_12_26L1 | 09/22/2016 | 09/22/2016 | 2 | 2 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/13/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 9/26/2017 | 9/26/2017 | 9/26/2017 | Connected |  | N
National Grid | METHUEN | 468598 | 01844 | 6 |  |  | Solar |  | 05_12_67J4 | 10/21/2022 | 10/28/2022 | 5 | 2 | 3 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 652297 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L2 | 11/14/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 501981 | 01841 | 11.02 |  |  | Solar |  | 05_14_5J40 | 02/14/2023 | 03/21/2023 | 25 | 23 | 2 | 03/22/2023 | 03/22/2023 | 129 | 109 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | LEOMINSTER | 636179 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 08/28/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | WORCESTER | 367884 | 01602 | 10 |  |  | Solar |  | 05_01_219W2 | 07/13/2021 | 12/20/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 | 07/13/2021 | 8/8/2023 | Y | EXP | 365 | 05/03/2022 | 05/17/2022 | 15 | 0 | 15 |  |  | 8/17/2022 | Connected |  | Y
National Grid | SOUTHBRIDGE | 174467 | 01550 | 250 |  |  | Natural Gas |  | 05_01_27W3 | 07/20/2011 | 07/20/2011 | 43 | 0 | 43 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 |  | 12/31/2016 | N | EXP | 1852 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 685196 | 01452 | 10 |  |  | Solar |  | 05_01_413L3 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 176313 | 02726 | 96 |  |  | Solar |  | 05_01_609W1 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 | 05/11/2015 | 05/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 |  | 10/30/2015 | N | EXP | 170 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/10/2016 | Connected |  | N
National Grid | TOPSFIELD | 630480 | 01983 | 7.83 |  |  | Solar |  | 05_05_11W82 | 08/06/2024 | 09/09/2024 | 17 | 13 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/06/2024 | 10/28/2025 | Y | EXP | 365 | 11/13/2024 | 12/05/2024 | 23 | 0 | 23 |  |  | 2/8/2025 | Connected |  | N
National Grid | MALDEN | 178107 | 02148 | 103.5 |  |  | Solar |  | 05_12_26L1 | 11/03/2017 | 11/03/2017 | 41 | 41 | 0 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 9/16/2019 | N | EXP | 616 |  |  | 0 | 0 | 0 |  |  | 9/23/2019 | Connected |  | N
National Grid | HAVERHILL | 649994 | 01832 | 3.8 |  |  | Solar |  | 05_12_67J4 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 652375 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L2 | 12/04/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/04/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | METHUEN | 534674 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J40 | 06/28/2023 | 07/05/2023 | 5 | 4 | 1 | 07/06/2023 | 07/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | LEOMINSTER | 636115 | 01453 | 6 |  |  | Solar |  | 05_14_74L3 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 420950 | 01604 | 8.99 |  |  | Solar |  | 05_01_219W2 | 04/06/2022 | 04/21/2022 | 11 | 10 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 198897 | 01507 | 3000 |  |  | Natural Gas |  | 05_01_27W3 | 07/11/2019 | 08/30/2019 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2019 | 10/14/2019 | 29 | 21 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 701578 | 01452 | 4980 |  |  | Solar |  | 05_01_413L3 | 12/24/2025 |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SOMERSET | 176505 | 02726 | 540 |  |  | Solar |  | 05_01_609W1 | 03/24/2016 | 03/29/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2016 | 05/26/2016 | 41 | 37 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 03/24/2016 | 12/31/2018 | Y | STD | 746 | 12/12/2018 | 01/02/2019 | 21 | 0 | 21 |  |  | 12/31/2018 | Connected |  | N
National Grid | TOPSFIELD | 633722 | 01983 | 7.6 |  |  | Solar |  | 05_05_11W82 | 08/19/2024 | 12/30/2024 | 18 | 13 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 08/19/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | MALDEN | 191835 | 02148 | 22.8 |  |  | Solar |  | 05_12_26L1 | 07/25/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 47 | 36 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 12/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2019 | Connected |  | N
National Grid | HAVERHILL | 685446 | 01832 | 3.84 |  |  | Solar |  | 05_12_67J4 | 04/16/2025 | 05/23/2025 | 3 | 1 | 2 | 05/27/2025 | 05/27/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/16/2025 | 6/16/2026 | Y | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  | 11/25/2025 | Connected |  | N
National Grid | METHUEN | 656096 | 01844 | 3.8 |  |  | Solar |  | 05_14_43L2 | 11/21/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/21/2024 | 3/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LAWRENCE | 534198 | 01841 | 6.912 |  |  | Solar |  | 05_14_5J40 | 03/20/2024 | 04/15/2024 | 18 | 15 | 3 | 04/16/2024 | 04/16/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 636493 | 01453 | 5.22 |  |  | Solar |  | 05_14_74L3 | 08/29/2024 | 12/12/2024 | 21 | 19 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 437201 | 01602 | 5.76 |  |  | Solar |  | 05_01_219W2 | 07/18/2022 | 07/19/2022 | 1 | 0 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/18/2022 | 2/1/2024 | Y | EXP | 365 | 01/07/2023 | 02/01/2023 | 26 | 0 | 26 |  |  | 5/8/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 676963 | 01550 | 960 |  |  | Solar |  | 05_01_27W4 | 04/10/2025 | 06/10/2025 | 41 | 31 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTMINSTER | 703963 | 01473 | 475 |  |  | Solar |  | 05_01_413L3 | 08/11/2025 | 09/17/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2025 | 10/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 176744 | 02726 | 2000 |  |  | Solar |  | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 662986 | 01983 | 8.36 |  |  | Solar |  | 05_05_11W82 | 12/30/2024 | 02/11/2025 | 5 | 2 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/30/2024 | 4/7/2026 | Y | EXP | 365 | 04/16/2025 | 05/20/2025 | 35 | 0 | 35 |  |  | 6/3/2025 | Connected |  | N
National Grid | MALDEN | 203602 | 02148 | 10 |  |  | Solar |  | 05_12_26L1 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 242 | 19 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 | 12/18/2018 | 3/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2020 | Connected |  | N
National Grid | METHUEN | 701479 | 01844 | 6.72 |  |  | Solar |  | 05_12_6J2 | 06/28/2025 | 07/14/2025 | 5 | 0 | 5 | 07/28/2025 | 07/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/28/2025 | 9/10/2026 | Y | EXP | 365 | 11/14/2025 | 12/15/2025 | 32 | 0 | 32 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 660296 | 01844 | 15.2 |  |  | Solar |  | 05_14_43L2 | 12/19/2024 | 01/08/2025 | 13 | 9 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/19/2024 | 3/21/2026 | Y | EXP | 365 | 07/02/2025 | 07/24/2025 | 22 | 0 | 22 |  |  | 8/21/2025 | Connected |  | N
National Grid | LAWRENCE | 574631 | 01841 | 6.38 |  |  | Solar |  | 05_14_5J40 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 79 | 54 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 | 01/23/2024 | 6/3/2025 | Y | EXP | 365 | 10/15/2024 | 01/03/2025 | 81 | 0 | 81 |  |  | 1/24/2025 | Connected |  | Y
National Grid | LEOMINSTER | 639000 | 01453 | 9.28 |  |  | Solar |  | 05_14_74L3 | 09/10/2024 | 10/08/2024 | 11 | 10 | 1 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 440596 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 07/14/2022 | 07/15/2022 | 2 | 1 | 1 | 07/18/2022 | 07/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 679785 | 01550 | 117.3 |  |  | Solar |  | 05_01_27W4 | 09/03/2025 | 10/03/2025 | 22 | 14 | 8 | 10/06/2025 | 10/06/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HUBBARDSTON | 711116 | 01452 | 150 |  |  | Solar |  | 05_01_413L3 | 08/11/2025 | 09/08/2025 | 19 | 9 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 176743 | 02726 | 2200 |  |  | Solar |  | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 679803 | 01983 | 7.6 |  |  | Solar |  | 05_05_11W82 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 | 03/21/2025 | 6/2/2026 | Y | EXP | 365 | 07/24/2025 | 07/24/2025 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 208665 | 01905 | 15 |  |  | Solar |  | 05_12_26L1 | 02/06/2019 | 02/12/2019 | 3 | 0 | 3 | 02/13/2019 | 02/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 715339 | 01844 | 2.7 |  |  | Solar |  | 05_12_6J2 | 08/29/2025 | 09/19/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 670504 | 01844 | 7.54 |  |  | Solar |  | 05_14_43L2 | 02/06/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 596274 | 01841 | 5 |  |  | Solar |  | 05_14_5J40 | 04/01/2024 | 05/08/2024 | 26 | 23 | 3 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/01/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 09/25/2024 | 72 | 0 | 72 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 639679 | 01453 | 5.856 |  |  | Solar |  | 05_14_74L3 | 09/12/2024 | 10/04/2024 | 8 | 2 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/12/2024 | 11/14/2025 | Y | EXP | 365 | 01/30/2025 | 04/24/2025 | 85 | 0 | 85 |  |  | 4/28/2025 | Connected |  | N
National Grid | WORCESTER | 513551 | 01605 | 0 |  |  | Solar |  | 05_01_219W2 | 03/21/2023 | 03/22/2023 | 1 | 0 | 1 | 03/23/2023 | 03/23/2023 | 54 | 33 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 706238 | 01550 | 200 |  |  | Solar |  | 05_01_27W4 | 08/11/2025 | 09/18/2025 | 27 | 17 | 10 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HUBBARDSTON | 742664 | 01452 | 11.4 |  |  | Solar |  | 05_01_413L3 | 12/30/2025 | 01/02/2026 | 1 | 0 | 1 | 01/05/2026 | 01/05/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 177289 | 02726 | 174 |  |  | Hydro |  | 05_01_609W1 | 06/17/2016 | 07/06/2016 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2016 | 09/06/2016 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/17/2016 | 9/25/2020 | Y | STD | 1176 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | TOPSFIELD | 613222 | 01983 | 3320 |  |  | Solar |  | 05_05_11W83 | 07/11/2024 | 07/30/2024 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LYNN | 208186 | 01905 | 10 |  |  | Solar |  | 05_12_26L1 | 02/13/2019 | 02/19/2019 | 3 | 3 | 0 | 02/20/2019 | 02/20/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 | 02/13/2019 | 10/30/2019 | Y | EXP | 236 | 06/28/2019 | 07/24/2019 | 26 | 0 | 26 |  |  | 7/27/2019 | Connected |  | N
National Grid | HAVERHILL | 241200 | 01832 | 7.6 |  |  | Solar |  | 05_12_6J2 | 07/03/2019 | 07/10/2019 | 3 | 0 | 3 | 07/11/2019 | 07/11/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/03/2019 | 8/3/2020 | Y | EXP | 365 | 05/20/2020 | 06/17/2020 | 28 | 0 | 28 |  |  | 7/21/2020 | Connected |  | N
National Grid | METHUEN | 683783 | 01844 | 0 |  |  | Battery Add-On |  | 05_14_43L2 | 04/08/2025 | 04/21/2025 | 8 | 4 | 4 | 04/22/2025 | 04/22/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | LAWRENCE | 597978 | 01841 | 3.8 |  |  | Solar |  | 05_14_5J40 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/18/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 643551 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 09/27/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WORCESTER | 527887 | 01605 | 6 |  |  | Solar |  | 05_01_219W2 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 716552 | 01550 | 67.3 |  |  | Solar |  | 05_01_27W4 | 09/23/2025 | 10/20/2025 | 17 | 8 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WESTMINSTER | 175014 | 01473 | 1500 |  |  | Solar |  | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 20 | 03/04/2014 | 03/07/2014 | 3 | 0 | 3 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | SWANSEA | 177715 | 02777 | 4686 |  |  | Solar |  | 05_01_609W1 | 07/26/2017 | 10/06/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2017 | 10/25/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 07/26/2017 | 10/31/2022 | Y | STD | 273 | 08/26/2022 | 10/12/2022 | 48 | 0 | 48 | 10/13/2022 | 11/4/2022 | 11/18/2022 | Connected |  | N
National Grid | TOPSFIELD | 712019 | 01983 | 7.329 |  |  | Solar |  | 05_05_11W83 | 08/14/2025 | 09/09/2025 | 3 | 0 | 3 | 09/10/2025 | 09/10/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LYNN | 214988 | 01905 | 20.8 |  |  | Solar |  | 05_12_26L1 | 03/22/2019 | 03/28/2019 | 3 | 0 | 3 | 03/29/2019 | 03/29/2019 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 4/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | HAVERHILL | 342995 | 01832 | 7.6 |  |  | Solar |  | 05_12_6J2 | 03/02/2021 |  | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 704923 | 01844 | 200 |  |  | Solar |  | 05_14_43L3 | 07/15/2025 | 09/10/2025 | 40 | 31 | 9 | 09/11/2025 | 09/11/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 651593 | 01841 | 3.8 |  |  | Solar |  | 05_14_5J40 | 11/12/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/12/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 646410 | 01453 | 11.4 |  |  | Solar |  | 05_14_74L3 | 10/17/2024 | 11/12/2024 | 14 | 11 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | WORCESTER | 571393 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 11/24/2023 | 12/11/2023 | 12 | 11 | 1 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 716453 | 01550 | 100 |  |  | Solar |  | 05_01_27W4 | 09/23/2025 | 10/14/2025 | 14 | 5 | 9 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WESTMINSTER | 175013 | 01473 | 1500 |  |  | Solar |  | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 20 |  |  | 0 | 0 | 0 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | SWANSEA | 178022 | 02777 | 500 |  |  | Solar |  | 05_01_609W1 | 08/29/2017 | 09/13/2017 | 8 | 8 | 0 |  |  | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 737037 | 01983 | 15.2 |  |  | Solar |  | 05_05_11W83 | 12/01/2025 | 12/08/2025 | 4 | 2 | 2 | 12/09/2025 | 12/09/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  | 1/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 243633 | 01905 | 9.84 |  |  | Solar |  | 05_12_26L1 | 07/19/2019 | 07/26/2019 | 5 | 5 | 0 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 11/11/2019 | N | EXP | 96 |  |  | 0 | 0 | 0 |  |  | 10/16/2019 | Connected |  | N
National Grid | HAVERHILL | 613313 | 01835 | 5 |  |  | Solar |  | 05_12_6J2 | 05/28/2024 | 06/18/2024 | 3 | 1 | 2 | 06/20/2024 | 06/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | METHUEN | 176543 | 01844 | 476 |  |  | Solar |  | 05_14_43L3 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 0 | 457 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 10/31/2017 | N | EXP | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 656760 | 01844 | 10 |  |  | Solar |  | 05_14_5J40 | 12/03/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 649008 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | WORCESTER | 604880 | 01605 | 5.76 |  |  | Solar |  | 05_01_219W2 | 04/18/2024 | 05/21/2024 | 19 | 14 | 5 | 05/22/2024 | 05/22/2024 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/18/2024 | 7/25/2025 | Y | EXP | 365 | 09/04/2024 | 09/12/2024 | 9 | 0 | 9 |  |  | 12/12/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 174500 | 01550 | 300 |  |  | Natural Gas |  | 05_01_27W4 | 11/17/2009 | 11/17/2009 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2010 |  | 10/31/2012 | N | EXP | 1010 |  |  | 0 | 0 | 0 | 9/18/2012 | 9/18/2012 | 7/7/2010 | Connected |  | Y
National Grid | HUBBARDSTON | 175096 | 01452 | 500 |  |  | Solar |  | 05_01_413L3 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 | 11/19/2012 | 11/19/2012 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 178110 | 02777 | 8730 |  |  | Solar |  | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 174178 | 01983 | 20 |  |  | Solar |  | 05_05_11W83 | 03/05/2012 | 03/05/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2012 |  | 5/16/2012 | N | EXP | -20 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 8/2/2012 | Connected |  | N
National Grid | LYNN | 243526 | 01905 | 4000 |  |  | Solar |  | 05_12_26L1 | 08/15/2019 | 09/12/2019 | 19 | 11 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2019 | 10/07/2019 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 630759 | 01835 | 10 |  |  | Solar |  | 05_12_6J2 | 08/07/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177341 | 01844 | 750 |  |  | Solar |  | 05_14_43L3 | 11/18/2016 | 11/18/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 12/28/2016 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 692129 | 01841 | 11.52 |  |  | Solar |  | 05_14_5J41 | 05/29/2025 | 08/08/2025 | 1 | 0 | 1 | 08/18/2025 | 08/18/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 650775 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 11/11/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 621331 | 01605 | 9.45 |  |  | Solar |  | 05_01_219W2 | 07/03/2024 | 07/05/2024 | 7 | 5 | 2 | 10/03/2024 | 10/03/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2024 | 07/03/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 174641 | 01550 | 82.8 |  |  | Solar |  | 05_01_27W4 | 12/04/2013 | 12/04/2013 | 5 | 0 | 5 | 12/11/2013 | 12/11/2013 | 941 | 6 | 935 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/04/2013 | 12/31/2016 | Y | EXP | 1100 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 175248 | 01452 | 1000 |  |  | Solar |  | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 |  |  | 7/26/2018 | Connected |  | N
National Grid | SWANSEA | 178109 | 02777 | 3396 |  |  | Solar |  | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 176000 | 01983 | 10 |  |  | Solar |  | 05_05_11W83 | 06/11/2015 | 06/11/2015 | 0 | 0 | 0 | 06/16/2015 | 06/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 6/21/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/28/2016 | Connected |  | N
National Grid | LYNN | 393102 | 01905 | 11.4 |  |  | Solar |  | 05_12_26L1 | 11/03/2021 | 11/04/2021 | 1 | 0 | 1 | 11/05/2021 | 11/05/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | HAVERHILL | 657888 | 01835 | 7.6 |  |  | Solar |  | 05_12_6J2 | 12/02/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177479 | 01844 | 75.6 |  |  | Solar |  | 05_14_43L3 | 07/06/2016 | 07/06/2016 | 35 | 35 | 0 | 08/26/2016 | 08/26/2016 | 244 | 55 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 |  | 8/31/2017 | N | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 742521 | 01844 | 150 |  |  | Solar |  | 05_14_5J41 | 12/31/2025 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LEOMINSTER | 657183 | 01453 | 5.76 |  |  | Solar |  | 05_14_74L3 | 11/26/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 639575 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 09/12/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/12/2024 | 12/3/2025 | Y | EXP | 365 | 12/19/2024 | 01/07/2025 | 20 | 0 | 20 |  |  | 1/17/2025 | Connected |  | N
National Grid | DUDLEY | 175270 | 01571 | 336 |  |  | Solar |  | 05_01_27W4 | 06/16/2014 | 06/16/2014 | 7 | 0 | 7 | 06/27/2014 | 06/27/2014 | 687 | 32 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2014 |  | 11/28/2014 | N | EXP | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 175245 | 01452 | 1000 |  |  | Solar |  | 05_01_413L3 | 08/28/2014 | 08/28/2014 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/07/2014 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 08/28/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/11/2018 | 6/20/2018 | 7/18/2018 | Connected |  | N
National Grid | SWANSEA | 178332 | 02777 | 1875 |  |  | Solar |  | 05_01_609W1 | 11/16/2017 | 02/23/2018 | 65 | 53 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/27/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 177145 | 01983 | 15.2 |  |  | Solar |  | 05_05_11W83 | 08/08/2016 | 08/08/2016 | 4 | 4 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 8/14/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/6/2017 | Connected |  | N
National Grid | LYNN | 495464 | 01905 | 16.53 |  |  | Solar |  | 05_12_26L1 | 01/27/2023 | 02/03/2023 | 5 | 2 | 3 | 02/06/2023 | 02/06/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 3/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2023 | Connected |  | N
National Grid | HAVERHILL | 712486 | 01832 | 10.47 |  |  | Solar |  | 05_12_6J2 | 08/22/2025 | 08/26/2025 | 2 | 0 | 2 | 08/27/2025 | 08/27/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | METHUEN | 201984 | 01844 | 3.8 |  |  | Solar |  | 05_14_43L3 | 11/26/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176466 | 01844 | 408 |  |  | Solar |  | 05_14_5J41 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 657165 | 01453 | 5.76 |  |  | Solar |  | 05_14_74L3 | 11/26/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 644853 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/03/2024 | 12/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | DUDLEY | 176705 | 01571 | 6 |  |  | Solar |  | 05_01_27W4 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 368 | 0 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 358 | 05/19/2016 | 06/01/2016 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175249 | 01473 | 1000 |  |  | Solar |  | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/12/2018 | 6/20/2018 | 7/26/2018 | Connected |  | N
National Grid | SWANSEA | 217237 | 02777 | 10 |  |  | Solar |  | 05_01_609W1 | 04/03/2019 | 04/04/2019 | 0 | 0 | 0 | 04/05/2019 | 04/05/2019 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 |  | 6/28/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 6/5/2019 | Connected |  | N
National Grid | TOPSFIELD | 177194 | 01983 | 28 |  |  | Solar |  | 05_05_11W83 | 10/31/2016 | 10/31/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/6/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/18/2017 | 5/18/2017 | 5/22/2017 | Connected |  | N
National Grid | LYNN | 569963 | 01905 | 2500 |  |  | Solar |  | 05_12_26L1 | 06/07/2024 |  | 277 | 267 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 226580 | 01835 | 1950 |  |  | Natural Gas |  | 05_12_72L1 | 07/25/2019 | 10/29/2019 | 65 | 58 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 | 01/31/2020 | 63 | 31 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2021 | 07/25/2019 | 6/11/2026 | Y | STD | 161 | 10/09/2024 |  | 450 | 450 | 0 |  |  |  | Construction |  | Y
National Grid | METHUEN | 322749 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L3 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 11/12/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 6/29/2021 | Connected |  | N
National Grid | LAWRENCE | 418542 | 01841 | 7.6 |  |  | Solar |  | 05_14_5J41 | 03/21/2022 | 03/25/2022 | 4 | 0 | 4 | 03/28/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/21/2022 | 5/27/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | N
National Grid | LEOMINSTER | 657640 | 01453 | 9.1 |  |  | Solar |  | 05_14_74L3 | 12/11/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | WORCESTER | 647479 | 01605 | 5.76 |  |  | Solar |  | 05_01_219W2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/29/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | DUDLEY | 177829 | 01571 | 7.6 |  |  | Solar |  | 05_01_27W4 | 08/04/2017 | 08/04/2017 | 4 | 0 | 4 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/12/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | WESTMINSTER | 175794 | 01473 | 1000 |  |  | Solar |  | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 257644 | 02777 | 0 |  |  | Battery Add-On |  | 05_01_609W1 | 10/07/2019 | 11/06/2019 | 0 | 0 | 0 | 11/07/2019 | 11/07/2019 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/07/2019 | 6/24/2020 | Y | EXP | 365 | 01/03/2020 | 01/09/2020 | 6 | 0 | 6 |  |  | 3/4/2020 | Connected |  | N
National Grid | TOPSFIELD | 178193 | 01983 | 6.6 |  |  | Solar |  | 05_05_11W83 | 01/02/2018 | 01/02/2018 | 24 | 0 | 24 | 02/07/2018 | 02/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 1/8/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | Connected |  | N
National Grid | BEVERLY | 609102 | 01915 | 15.2 |  |  | Solar |  | 05_12_26L1 | 05/06/2024 | 05/08/2024 | 2 | 0 | 2 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 10/01/2024 | 01/02/2025 | 94 | 0 | 94 |  |  | 1/13/2025 | Connected |  | N
National Grid | HAVERHILL | 724946 | 01835 | 1000 |  |  | Solar |  | 05_12_72L1 | 12/08/2025 |  | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | METHUEN | 342609 | 01844 | 5 |  |  | Solar |  | 05_14_43L3 | 03/04/2021 | 03/09/2021 | 2 | 0 | 2 | 03/10/2021 | 03/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/04/2021 | 10/5/2022 | Y | EXP | 365 | 09/11/2021 | 09/21/2021 | 6 | 0 | 6 |  |  | 9/29/2021 | Connected |  | N
National Grid | LAWRENCE | 456175 | 01841 | 5 |  |  | Solar |  | 05_14_5J41 | 10/11/2022 | 10/24/2022 | 10 | 9 | 1 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/11/2022 | 1/6/2024 | Y | EXP | 365 | 03/15/2023 | 03/31/2023 | 17 | 0 | 17 |  |  | 4/3/2023 | Connected |  | N
National Grid | LEOMINSTER | 663368 | 01453 | 8.96 |  |  | Solar |  | 05_14_74L3 | 01/02/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WORCESTER | 647432 | 01605 | 3.8 |  |  | Solar |  | 05_01_219W2 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 178284 | 01550 | 684 |  |  | Solar |  | 05_01_27W4 | 03/28/2018 | 03/28/2018 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175793 | 01473 | 760 |  |  | Solar |  | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 257344 | 02777 | 9.765 |  |  | Solar |  | 05_01_609W1 | 12/09/2019 | 12/11/2019 | 2 | 2 | 0 | 12/12/2019 | 12/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 12/09/2019 | 12/9/2020 | Y | EXP | 365 | 05/29/2020 | 06/15/2020 | 17 | 0 | 17 |  |  | 9/22/2020 | Connected |  | N
National Grid | TOPSFIELD | 178395 | 01983 | 7.6 |  |  | Solar |  | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/11/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | BEVERLY | 611833 | 01915 | 6.38 |  |  | Solar |  | 05_12_26L1 | 05/20/2024 | 05/29/2024 | 2 | 1 | 1 | 05/30/2024 | 05/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/20/2024 | 9/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | Y
National Grid | HAVERHILL | 177522 | 01835 | 24 |  |  | Solar |  | 05_12_72L1 | 02/11/2016 | 02/11/2016 | 3 | 0 | 3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 10/4/2017 | N | EXP | 595 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 10/5/2016 | Connected |  | N
National Grid | METHUEN | 412233 | 01844 | 0 |  |  | Battery Add-On |  | 05_14_43L3 | 05/28/2022 | 08/09/2022 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2022 | 09/07/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 592556 | 01841 | 3.8 |  |  | Solar |  | 05_14_5J41 | 03/01/2024 | 04/18/2024 | 33 | 32 | 1 | 04/19/2024 | 04/19/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | LEOMINSTER | 665241 | 01453 | 15.2 |  |  | Solar |  | 05_14_74L3 | 01/16/2025 | 01/31/2025 | 10 | 4 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/16/2025 | 3/18/2026 | Y | EXP | 365 | 08/09/2025 | 08/18/2025 | 10 | 0 | 10 |  |  | 8/26/2025 | Connected |  | N
National Grid | WORCESTER | 648304 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/21/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 357062 | 01550 | 7.6 |  |  | Solar |  | 05_01_27W4 | 05/26/2021 | 06/03/2021 | 4 | 0 | 4 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 175874 | 01452 | 25 |  |  | Solar |  | 05_01_413L3 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 382 | 0 | 382 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 12/31/2016 | N | EXP | 655 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 283891 | 02777 | 0 |  |  | Battery Add-On |  | 05_01_609W1 | 03/30/2020 | 04/06/2020 | 5 | 5 | 0 | 04/07/2020 | 04/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2020 | Connected |  | N
National Grid | TOPSFIELD | 178392 | 01983 | 10 |  |  | Solar |  | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 41 | 40 | 1 | 04/04/2018 | 04/04/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2018 |  | 3/7/2019 | N | EXP | 175 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 649651 | 01915 | 9.28 |  |  | Solar |  | 05_12_26L1 | 10/25/2024 | 11/12/2024 | 8 | 3 | 5 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/25/2024 | 1/21/2026 | Y | EXP | 365 | 02/18/2025 | 03/03/2025 | 14 | 0 | 14 |  |  | 3/11/2025 | Connected |  | N
National Grid | HAVERHILL | 177914 | 01835 | 365 |  |  | Natural Gas |  | 05_12_72L1 | 10/20/2017 | 10/20/2017 | 55 | 0 | 55 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  | 6/28/2019 | N | STD | 252 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | METHUEN | 498937 | 01844 | 5.04 |  |  | Solar |  | 05_14_43L3 | 02/28/2023 | 03/07/2023 | 5 | 3 | 2 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 02/28/2023 | 11/29/2024 | Y | EXP | 365 | 06/09/2023 | 02/03/2024 | 240 | 3 | 237 |  |  | 2/6/2024 | Connected |  | N
National Grid | METHUEN | 606739 | 01844 | 10 |  |  | Solar |  | 05_14_5J41 | 04/25/2024 | 05/03/2024 | 1 | 0 | 1 | 05/06/2024 | 05/06/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/25/2024 | 5/30/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/12/2024 | Connected |  | N
National Grid | LEOMINSTER | 669715 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L3 | 02/03/2025 | 03/12/2025 | 20 | 16 | 4 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | WORCESTER | 655579 | 01605 | 3.8 |  |  | Solar |  | 05_01_219W2 | 11/20/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 442781 | 01550 | 10 |  |  | Solar |  | 05_01_27W4 | 07/14/2022 | 07/18/2022 | 2 | 0 | 2 | 07/19/2022 | 07/19/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/14/2022 | 8/25/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 175996 | 01452 | 18.75 |  |  | Solar |  | 05_01_413L3 | 06/11/2015 | 06/11/2015 | 6 | 6 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/17/2016 | N | EXP | 352 |  |  | 0 | 0 | 0 | 11/6/2015 | 11/6/2015 | 11/6/2015 | Connected |  | N
National Grid | SWANSEA | 289990 | 02777 | 4950 |  |  | Other |  | 05_01_609W1 | 05/16/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 178672 | 01983 | 7.6 |  |  | Solar |  | 05_05_11W83 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/26/2019 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 657173 | 01915 | 10 |  |  | Solar |  | 05_12_26L1 | 11/26/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | HAVERHILL | 178031 | 01835 | 5.2 |  |  | Solar |  | 05_12_72L1 | 10/25/2017 | 10/25/2017 | 24 | 24 | 0 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 10/25/2017 | 10/15/2019 | Y | EXP | 673 | 08/08/2018 | 10/05/2018 | 58 | 0 | 58 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 529552 | 01844 | 10 |  |  | Solar |  | 05_14_43L3 | 05/26/2023 | 06/05/2023 | 5 | 1 | 4 | 06/06/2023 | 06/06/2023 | 238 | 218 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | Y
National Grid | LAWRENCE | 607882 | 01841 | 5.04 |  |  | Solar |  | 05_14_5J41 | 05/01/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 05/01/2024 | 4/22/2026 | Y | EXP | 365 | 05/16/2025 | 09/15/2025 | 123 | 0 | 123 |  |  | 10/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 670532 | 01453 | 3.8 |  |  | Solar |  | 05_14_74L3 | 02/06/2025 | 03/25/2025 | 25 | 20 | 5 | 03/26/2025 | 03/26/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/06/2025 | 5/20/2026 | Y | EXP | 365 | 06/24/2025 | 07/28/2025 | 35 | 0 | 35 |  |  | 8/1/2025 | Connected |  | N
National Grid | WORCESTER | 659724 | 01605 | 2.32 |  |  | Solar |  | 05_01_219W2 | 12/10/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | CHARLTON | 459363 | 01507 | 3.8 |  |  | Solar |  | 05_01_27W4 | 01/05/2023 |  | 213 | 213 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 176639 | 01452 | 1000 |  |  | Solar |  | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | SWANSEA | 291210 | 02777 | 0 |  |  | Other |  | 05_01_609W1 | 08/31/2020 | 09/23/2020 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2020 | 10/16/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 193254 | 01983 | 6 |  |  | Solar |  | 05_05_11W83 | 08/10/2018 | 10/08/2018 | 15 | 15 | 0 | 10/09/2018 | 10/09/2018 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 08/10/2018 | 10/30/2019 | Y | EXP | 378 | 05/08/2019 | 05/07/2019 | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | BEVERLY | 659886 | 01915 | 9.57 |  |  | Solar |  | 05_12_26L1 | 12/11/2024 | 12/24/2024 | 9 | 5 | 4 | 12/26/2024 | 12/26/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | HAVERHILL | 178181 | 01835 | 3.8 |  |  | Solar |  | 05_12_72L1 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/02/2018 | 05/02/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/18/2019 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 637884 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L3 | 10/24/2024 | 11/01/2024 | 5 | 1 | 4 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/24/2024 | 3/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | LAWRENCE | 617581 | 01841 | 3.8 |  |  | Solar |  | 05_14_5J41 | 06/12/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/12/2024 | 7/19/2025 | Y | EXP | 365 | 11/13/2024 | 11/26/2024 | 14 | 0 | 14 |  |  | 12/6/2024 | Connected |  | N
National Grid | LEOMINSTER | 676986 | 01453 | 3.8 |  |  | Solar |  | 05_14_74L3 | 03/10/2025 | 03/22/2025 | 1 | 0 | 1 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/10/2025 | 5/13/2026 | Y | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  | 12/18/2025 | Connected |  | N
National Grid | WORCESTER | 660535 | 01605 | 10 |  |  | Solar |  | 05_01_219W2 | 12/13/2024 | 01/08/2025 | 1 | 0 | 1 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 582263 | 01550 | 10.44 |  |  | Solar |  | 05_01_27W4 | 01/09/2024 | 01/11/2024 | 3 | 1 | 2 | 01/12/2024 | 01/12/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | HUBBARDSTON | 176638 | 01452 | 1000 |  |  | Solar |  | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 299584 | 02777 | 7.68 |  |  | Solar |  | 05_01_609W1 | 07/02/2020 | 07/08/2020 | 3 | 0 | 3 | 07/09/2020 | 07/09/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2020 |  | 7/6/2022 | N | EXP | 629 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 320884 | 01983 | 10.56 |  |  | Solar |  | 05_05_11W83 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 676798 | 01915 | 22.8 |  |  | Solar |  | 05_12_26L1 | 03/11/2025 | 03/14/2025 | 3 | 0 | 3 | 03/17/2025 | 03/17/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | HAVERHILL | 178590 | 01835 | 3.2 |  |  | Solar |  | 05_12_72L1 | 03/14/2018 | 03/14/2018 | 0 | 0 | 0 | 04/24/2018 | 04/24/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/20/2019 | N | EXP | 313 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 654621 | 01844 | 10 |  |  | Solar |  | 05_14_43L3 | 11/15/2024 | 12/17/2024 | 8 | 4 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/15/2024 | 3/18/2026 | Y | EXP | 365 | 04/22/2025 | 04/30/2025 | 9 | 0 | 9 |  |  | 4/5/2025 | Connected |  | N
National Grid | METHUEN | 618583 | 01844 | 10 |  |  | Solar |  | 05_14_5J41 | 06/17/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 682830 | 01453 | 8.027 |  |  | Solar |  | 05_14_74L3 | 04/04/2025 | 05/12/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | WORCESTER | 663860 | 01605 | 3.8 |  |  | Solar |  | 05_01_219W2 | 01/06/2025 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 01/06/2025 | 3/17/2026 | Y | EXP | 365 | 04/30/2025 | 10/24/2025 | 178 | 0 | 178 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 623960 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W4 | 07/10/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/10/2024 | 8/14/2025 | Y | EXP | 365 | 09/19/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 11/26/2024 | Connected |  | N
National Grid | WESTMINSTER | 176637 | 01473 | 1000 |  |  | Solar |  | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | SWANSEA | 299242 | 02777 | 0 |  |  | Solar |  | 05_01_609W1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 348833 | 01983 | 499 |  |  | Solar |  | 05_05_11W83 | 04/20/2021 | 05/04/2021 | 9 | 0 | 9 |  |  | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 693020 | 01915 | 31.04 |  |  | Solar |  | 05_12_26L1 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | HAVERHILL | 196655 | 01835 | 3.8 |  |  | Solar |  | 05_12_72L1 | 09/21/2018 | 10/16/2018 | 5 | 5 | 0 | 10/17/2018 | 10/17/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 655934 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L3 | 11/21/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | LAWRENCE | 625945 | 01841 | 15.2 |  |  | Solar |  | 05_14_5J41 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/18/2024 | 12/9/2025 | Y | EXP | 365 | 01/25/2025 |  | 342 | 104 | 238 |  |  | 6/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 684455 | 01453 | 10 |  |  | Solar |  | 05_14_74L3 | 04/10/2025 | 05/02/2025 | 15 | 12 | 3 | 05/05/2025 | 05/05/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/10/2025 | 8/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | WORCESTER | 670221 | 01605 | 39.9 |  |  | Solar |  | 05_01_219W2 | 03/18/2025 | 03/27/2025 | 7 | 4 | 3 | 03/28/2025 | 03/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 623801 | 01550 | 5.76 |  |  | Solar |  | 05_01_27W4 | 07/10/2024 | 08/02/2024 | 4 | 3 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | WESTMINSTER | 176768 | 01473 | 1872 |  |  | Solar |  | 05_01_413L3 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 05/31/2016 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 311144 | 02777 | 9.6 |  |  | Solar |  | 05_01_609W1 | 09/07/2020 | 09/08/2020 | 0 | 0 | 0 | 09/09/2020 | 09/09/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/07/2020 | 9/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2021 | Connected |  | N
National Grid | TOPSFIELD | 524644 | 01983 | 0 |  |  | Solar |  | 05_05_11W83 | 05/09/2023 | 05/10/2023 | 1 | 0 | 1 | 05/11/2023 | 05/11/2023 | 197 | 176 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | BEVERLY | 714746 | 01915 | 0 |  |  | Solar |  | 05_12_28L2 | 08/28/2025 | 09/10/2025 | 8 | 4 | 4 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 468924 | 01835 | 10 |  |  | Solar |  | 05_12_72L1 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 60 | 42 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 | 11/01/2022 | 7/2/2024 | Y | EXP | 365 | 04/22/2023 | 06/30/2023 | 70 | 0 | 70 |  |  | 8/9/2023 | Connected |  | N
National Grid | METHUEN | 657119 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L3 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | METHUEN | 637475 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J41 | 09/09/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 09/09/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | LEOMINSTER | 556519 | 01453 | 340 |  |  | Natural Gas |  | 05_14_74L4 | 02/20/2024 | 07/03/2025 | 341 | 331 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2025 | 08/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | WORCESTER | 693924 | 01605 | 6.96 |  |  | Solar |  | 05_01_219W2 | 05/23/2025 | 06/03/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 633504 | 01550 | 5 |  |  | Solar |  | 05_01_27W4 | 08/19/2024 | 08/22/2024 | 2 | 1 | 1 | 08/23/2024 | 08/23/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/19/2024 | 10/6/2025 | Y | EXP | 365 | 12/07/2024 | 04/24/2025 | 139 | 0 | 139 |  |  | 5/14/2025 | Connected |  | N
National Grid | WESTMINSTER | 177748 | 01473 | 1500 |  |  | Solar |  | 05_01_413L3 | 05/26/2017 | 06/09/2017 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/07/2017 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 | 05/26/2017 | 10/31/2020 | Y | STD | 1174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 343989 | 02777 | 7.6 |  |  | Solar |  | 05_01_609W1 | 02/25/2021 | 03/01/2021 | 1 | 0 | 1 | 03/02/2021 | 03/02/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 559394 | 01930 | 5 |  |  | Solar |  | 05_05_11W83 | 10/02/2023 | 10/16/2023 | 10 | 7 | 3 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 10/02/2023 | 11/10/2024 | Y | EXP | 365 | 01/12/2024 | 02/21/2024 | 41 | 0 | 41 |  |  | 5/7/2024 | Connected |  | N
National Grid | BEVERLY | 725607 | 01915 | 0 |  |  | Solar |  | 05_12_28L2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 516020 | 01835 | 5 |  |  | Solar |  | 05_12_72L1 | 04/26/2023 | 05/26/2023 | 22 | 21 | 1 | 05/30/2023 | 05/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/26/2023 | 8/18/2024 | Y | EXP | 365 | 10/25/2023 | 10/25/2023 | 1 | 0 | 1 |  |  | 11/17/2023 | Connected |  | N
National Grid | METHUEN | 657060 | 01844 | 10 |  |  | Solar |  | 05_14_43L3 | 11/26/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 646096 | 01841 | 11.02 |  |  | Solar |  | 05_14_5J41 | 10/22/2024 | 11/26/2024 | 11 | 7 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 10/22/2024 | 2/5/2026 | Y | EXP | 365 | 04/15/2025 | 07/11/2025 | 88 | 0 | 88 |  |  | 7/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 672131 | 01453 | 180 |  |  | Solar |  | 05_14_74L4 | 04/04/2025 |  | 184 | 31 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | WORCESTER | 701355 | 01605 | 11.5 |  |  | Solar |  | 05_01_219W2 | 06/27/2025 | 07/08/2025 | 6 | 3 | 3 | 07/09/2025 | 07/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 643734 | 01550 | 7.6 |  |  | Solar |  | 05_01_27W4 | 10/01/2024 | 11/18/2024 | 18 | 13 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | WESTMINSTER | 178534 | 01473 | 3744 |  |  | Solar |  | 05_01_413L3 | 12/05/2017 | 12/05/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 | 12/05/2017 | 12/31/2020 | Y | STD | 784 | 06/12/2020 | 11/23/2020 | 165 | 5 | 160 | 12/14/2020 | 12/22/2020 | 12/31/2020 | Connected |  | N
National Grid | SWANSEA | 402697 | 02777 | 0 |  |  | Solar |  | 05_01_609W1 | 12/21/2021 | 01/10/2022 | 13 | 12 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 3/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | GLOUCESTER | 638473 | 01930 | 10 |  |  | Solar |  | 05_05_11W83 | 09/06/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/06/2024 | 12/26/2025 | Y | EXP | 365 | 12/19/2024 | 02/05/2025 | 49 | 0 | 49 |  |  | 3/27/2025 | Connected |  | N
National Grid | BEVERLY | 176498 | 01915 | 22.8 |  |  | Solar |  | 05_12_28L2 | 02/09/2016 | 02/09/2016 | 1 | 1 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/15/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 10/24/2016 | Connected |  | N
National Grid | HAVERHILL | 565683 | 01835 | 3.8 |  |  | Solar |  | 05_12_72L1 | 10/24/2023 | 11/14/2023 | 3 | 1 | 2 | 11/15/2023 | 11/15/2023 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 658163 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L3 | 12/03/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/03/2024 | 2/21/2026 | Y | EXP | 365 | 02/20/2025 | 03/19/2025 | 28 | 14 | 14 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 662588 | 01840 | 10 |  |  | Solar |  | 05_14_5J41 | 01/03/2025 | 01/21/2025 | 5 | 2 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 677996 | 01453 | 15.2 |  |  | Solar |  | 05_14_74L4 | 03/17/2025 | 03/24/2025 | 5 | 1 | 4 | 03/25/2025 | 03/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 435107 | 01605 | 0 |  |  | Other |  | 05_01_219W3 | 07/05/2022 | 10/20/2022 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/08/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOUTHBRIDGE | 647137 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W4 | 10/23/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | HUBBARDSTON | 194187 | 01452 | 333 |  |  | Solar |  | 05_01_413L3 | 08/23/2018 | 08/23/2018 | 0 | 0 | 0 | 08/24/2018 | 08/24/2018 | 20 | 19 | 1 | 11/15/2018 | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 426230 | 02777 | 7.6 |  |  | Solar |  | 05_01_609W1 | 06/01/2022 | 06/06/2022 | 4 | 2 | 2 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2022 | Connected |  | N
National Grid | MANCHESTER | 662103 | 01944 | 10 |  |  | Solar |  | 05_05_11W83 | 12/20/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/20/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 176791 | 01915 | 7.6 |  |  | Solar |  | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/20/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/2/2016 | Connected |  | N
National Grid | HAVERHILL | 596850 | 01835 | 3.77 |  |  | Solar |  | 05_12_72L1 | 03/19/2024 | 03/21/2024 | 2 | 1 | 1 | 03/22/2024 | 03/22/2024 | 8 | 6 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 661220 | 01844 | 10 |  |  | Solar |  | 05_14_43L3 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | LAWRENCE | 688562 | 01841 | 5.76 |  |  | Solar |  | 05_14_5J41 | 04/30/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | LEOMINSTER | 712563 | 01453 | 15.2 |  |  | Solar |  | 05_14_74L4 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | Y
National Grid | WORCESTER | 174600 | 01605 | 225 |  |  | Solar |  | 05_01_219W3 | 10/03/2011 | 10/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2011 | 10/03/2011 | 3/1/2012 | Y | EXP | 87 | 02/16/2012 | 02/24/2012 | 5 | 0 | 5 | 8/9/2012 | 8/9/2012 | 3/1/2012 | Connected |  | N
National Grid | SOUTHBRIDGE | 680013 | 01550 | 15.76 |  |  | Solar |  | 05_01_27W4 | 03/24/2025 | 03/26/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 241223 | 01473 | 400 |  |  | Solar |  | 05_01_413L3 | 04/14/2020 | 05/11/2020 | 17 | 11 | 6 |  |  | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 472538 | 02777 | 7.6 |  |  | Solar |  | 05_01_609W1 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/18/2022 | 3/2/2024 | Y | EXP | 365 | 02/23/2023 | 03/02/2023 | 8 | 0 | 8 |  |  | 6/24/2023 | Connected |  | N
National Grid | GLOUCESTER | 662100 | 01930 | 5.76 |  |  | Solar |  | 05_05_11W83 | 12/20/2024 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | BEVERLY | 176789 | 01915 | 7.6 |  |  | Solar |  | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/20/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 641368 | 01835 | 10 |  |  | Solar |  | 05_12_72L1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 11/20/2025 | Y | EXP | 365 | 01/29/2025 | 02/06/2025 | 9 | 0 | 9 |  |  | 2/25/2025 | Connected |  | Y
National Grid | METHUEN | 662220 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L3 | 12/23/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 728326 | 01841 | 5.76 |  |  | Solar |  | 05_14_5J42 | 11/17/2025 | 11/20/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 727868 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L4 | 10/20/2025 | 10/23/2025 | 3 | 0 | 3 | 10/24/2025 | 10/24/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 176977 | 01605 | 35 |  |  | Solar |  | 05_01_219W3 | 12/27/2016 | 12/27/2016 | 4 | 3 | 1 | 01/03/2017 | 01/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 |  | 1/2/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 678914 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W5 | 03/18/2025 | 03/26/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 03/18/2025 | 6/16/2026 | Y | EXP | 365 | 08/05/2025 | 09/30/2025 | 57 | 0 | 57 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 273618 | 01473 | 5000 |  |  | Other |  | 05_01_413L3 | 03/03/2020 | 03/17/2020 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 542295 | 02777 | 0 |  |  | Other |  | 05_01_609W1 | 08/28/2023 | 09/12/2023 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2023 | 10/11/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 663923 | 01930 | 7.6 |  |  | Solar |  | 05_05_11W83 | 01/06/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 01/06/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | BEVERLY | 178625 | 01915 | 11.4 |  |  | Solar |  | 05_12_28L2 | 03/15/2018 | 03/15/2018 | 14 | 0 | 14 | 04/05/2018 | 04/05/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/21/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 9/6/2019 | Connected |  | N
National Grid | HAVERHILL | 351267 | 01835 | 100 |  |  | Solar |  | 05_12_79J1 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 662119 | 01844 | 3.8 |  |  | Solar |  | 05_14_43L3 | 12/21/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | METHUEN | 178227 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J42 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 1/10/2019 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 174279 | 01453 | 491 |  |  | Solar |  | 05_14_74L4 | 12/13/2011 | 12/13/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 12/13/2011 | 3/1/2012 | Y | EXP | -62 | 06/06/2012 | 07/16/2012 | 26 | 0 | 26 | 6/26/2012 | 6/26/2012 | 7/2/2012 | Connected |  | N
National Grid | WORCESTER | 193664 | 01604 | 7.6 |  |  | Solar |  | 05_01_219W3 | 08/15/2018 | 09/05/2018 | 4 | 4 | 0 | 09/06/2018 | 09/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 689732 | 01550 | 5.76 |  |  | Solar |  | 05_01_27W5 | 05/05/2025 | 05/16/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTMINSTER | 282071 | 01473 | 4950 |  |  | Other |  | 05_01_413L3 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/10/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 552766 | 02777 | 0 |  |  | Solar |  | 05_01_609W1 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 667625 | 01930 | 7.6 |  |  | Solar |  | 05_05_11W83 | 01/24/2025 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | NAHANT | 203910 | 01908 | 0 |  |  | Solar |  | 05_12_28L2 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 1/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | HAVERHILL | 387711 | 01835 | 15.2 |  |  | Solar |  | 05_12_79J1 | 10/11/2021 | 10/13/2021 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 2/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | METHUEN | 494666 | 01844 | 360 |  |  | Solar |  | 05_14_43L4 | 07/11/2023 | 09/01/2023 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2023 | 10/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LAWRENCE | 178338 | 01840 | 5 |  |  | Solar |  | 05_14_5J42 | 11/17/2017 | 11/17/2017 | 48 | 47 | 1 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 11/25/2018 | N | EXP | 298 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 174828 | 01453 | 100 |  |  | Solar |  | 05_14_74L4 | 08/15/2011 | 08/15/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2011 | 08/15/2011 | 3/6/2012 | Y | EXP | 81 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 3/6/2012 | Connected |  | N
National Grid | WORCESTER | 322879 | 01604 | 43.2 |  |  | Solar |  | 05_01_219W3 | 11/02/2020 | 11/13/2020 | 7 | 0 | 7 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 698095 | 01550 | 13.36 |  |  | Solar |  | 05_01_27W5 | 07/09/2025 | 08/06/2025 | 20 | 16 | 4 | 09/09/2025 | 09/09/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HUBBARDSTON | 300622 | 01452 | 0 |  |  | Other |  | 05_01_413L3 | 09/22/2020 | 10/01/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2020 | 10/29/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 560920 | 02777 | 5.235 |  |  | Solar |  | 05_01_609W1 | 11/07/2023 | 11/14/2023 | 4 | 3 | 1 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/07/2023 | 1/29/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | MANCHESTER | 465846 | 01944 | 0 |  |  | Other |  | 05_05_11W84 | 02/17/2023 | 05/03/2023 | 51 | 43 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2023 | 06/07/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 02/17/2023 | 10/12/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NAHANT | 203625 | 01908 | 3.8 |  |  | Solar |  | 05_12_28L2 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 490037 | 01844 | 4.06 |  |  | Solar |  | 05_12_79J1 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 4/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | METHUEN | 672915 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 02/19/2025 | 04/08/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 320041 | 01840 | 9.8 |  |  | Solar |  | 05_14_5J42 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/30/2020 | 9/3/2022 | Y | EXP | 365 | 08/19/2021 | 10/12/2021 | 40 | 3 | 37 |  |  | 6/2/2022 | Connected |  | N
National Grid | LEOMINSTER | 175933 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 362 | 0 | 362 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | Y
National Grid | WORCESTER | 520020 | 01604 | 250 |  |  | Solar |  | 05_01_219W4 | 05/09/2023 | 07/25/2023 | 53 | 43 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SOUTHBRIDGE | 706568 | 01550 | 15.76 |  |  | Solar |  | 05_01_27W5 | 07/23/2025 | 07/29/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 307951 | 01473 | 9.6 |  |  | Solar |  | 05_01_413L3 | 08/20/2020 | 08/21/2020 | 0 | 0 | 0 | 08/24/2020 | 08/24/2020 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2020 | 08/20/2020 | 11/2/2021 | Y | EXP | 365 | 03/11/2021 | 03/15/2021 | 4 | 0 | 4 |  |  | 4/12/2021 | Connected |  | N
National Grid | SWANSEA | 566961 | 02777 | 5 |  |  | Solar |  | 05_01_609W1 | 11/08/2023 | 11/09/2023 | 1 | 0 | 1 | 11/13/2023 | 11/13/2023 | 38 | 14 | 24 | 03/01/2024 | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/23/2025 | N | EXP | 365 | 05/31/2024 | 07/05/2024 | 36 | 0 | 36 |  |  | 8/9/2024 | Connected |  | N
National Grid | GLOUCESTER | 707245 | 01930 | 250 |  |  | Solar |  | 05_05_11W84 | 12/13/2025 |  | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NAHANT | 293839 | 01908 | 10 |  |  | Solar |  | 05_12_28L2 | 05/28/2020 | 06/15/2020 | 12 | 12 | 0 | 06/16/2020 | 06/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2020 | Connected |  | N
National Grid | METHUEN | 711878 | 01844 | 17.6 |  |  | Solar |  | 05_12_79J1 | 08/15/2025 | 08/21/2025 | 4 | 0 | 4 | 08/22/2025 | 08/22/2025 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | METHUEN | 678808 | 01844 | 5.76 |  |  | Solar |  | 05_14_43L4 | 03/18/2025 | 09/04/2025 | 7 | 2 | 5 | 09/19/2025 | 09/19/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 03/18/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | METHUEN | 558417 | 01844 | 10 |  |  | Solar |  | 05_14_5J42 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | LEOMINSTER | 176269 | 01453 | 17.6 |  |  | Solar |  | 05_14_74L4 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/13/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 7/25/2016 | Connected |  | N
National Grid | WORCESTER | 667799 | 01604 | 450 |  |  | Solar |  | 05_01_219W4 | 03/14/2025 | 04/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2025 | 05/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | DUDLEY | 711138 | 01571 | 8 |  |  | Solar |  | 05_01_27W5 | 08/18/2025 | 09/05/2025 | 17 | 13 | 4 | 10/03/2025 | 10/03/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/18/2025 | 12/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTMINSTER | 318399 | 01473 | 19.2 |  |  | Solar |  | 05_01_413L3 | 10/09/2020 |  | 40 | 39 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 569500 | 02725 | 7.6 |  |  | Solar |  | 05_01_609W1 | 11/27/2023 | 11/29/2023 | 3 | 2 | 1 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | GLOUCESTER | 709427 | 01930 | 9.56 |  |  | Solar |  | 05_05_11W84 | 08/04/2025 | 08/27/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/04/2025 | 10/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NAHANT | 359131 | 01908 | 5.22 |  |  | Solar |  | 05_12_28L2 | 05/19/2021 | 06/07/2021 | 12 | 11 | 1 | 06/08/2021 | 06/08/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N
National Grid | METHUEN | 710901 | 01844 | 9.6 |  |  | Solar |  | 05_12_79J2 | 08/20/2025 | 09/15/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 704124 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 07/10/2025 | 07/25/2025 | 3 | 0 | 3 | 08/06/2025 | 08/06/2025 | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 533962 | 01844 | 10 |  |  | Solar |  | 05_14_5J42 | 07/06/2023 | 07/13/2023 | 6 | 5 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 | 07/06/2023 | 9/2/2024 | Y | EXP | 365 | 02/17/2024 | 02/16/2024 | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | LEOMINSTER | 176665 | 01453 | 17.25 |  |  | Solar |  | 05_14_74L4 | 10/19/2015 | 10/19/2015 | 7 | 7 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 |  | 10/26/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/9/2016 | 8/9/2016 | 8/9/2016 | Connected |  | N
National Grid | WORCESTER | 678562 | 01604 | 420 |  |  | Solar |  | 05_01_219W4 | 06/18/2025 | 10/29/2025 | 91 | 82 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DUDLEY | 735538 | 01571 | 10 |  |  | Solar |  | 05_01_27W5 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WESTMINSTER | 324361 | 01473 | 0 |  |  | Solar |  | 05_01_413L3 | 11/06/2020 | 12/18/2020 | 28 | 27 | 1 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 11/06/2020 | 12/17/2021 | Y | EXP | 365 | 05/20/2021 | 06/25/2021 | 36 | 0 | 36 |  |  | 6/29/2021 | Connected |  | N
National Grid | SOMERSET | 578023 | 02725 | 9.86 |  |  | Solar |  | 05_01_609W1 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 41 | 35 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 174266 | 01944 | 26 |  |  | Solar |  | 05_05_11W84 | 12/28/2011 | 12/28/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2012 |  | 2/25/2012 | N | EXP | -47 |  |  | 0 | 0 | 0 | 5/8/2012 | 5/8/2012 | 5/16/2012 | Connected |  | N
National Grid | NAHANT | 453090 | 01908 | 8.7 |  |  | Solar |  | 05_12_28L2 | 09/26/2022 | 09/29/2022 | 3 | 2 | 1 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 12/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2023 | Connected |  | N
National Grid | METHUEN | 392553 | 01844 | 13.96 |  |  | Solar |  | 05_12_79J2 | 11/22/2021 | 01/06/2022 | 10 | 6 | 4 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 11/22/2021 | 7/27/2023 | Y | EXP | 365 | 04/28/2022 | 06/02/2022 | 36 | 0 | 36 |  |  | 8/9/2022 | Connected |  | N
National Grid | METHUEN | 709253 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 08/04/2025 | 09/02/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 08/04/2025 | 11/3/2026 | Y | EXP | 365 | 12/18/2025 |  | 15 | 0 | 15 |  |  |  | Construction |  | N
National Grid | METHUEN | 534971 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J42 | 07/06/2023 | 07/25/2023 | 14 | 13 | 1 | 07/26/2023 | 07/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/06/2023 | 9/20/2024 | Y | EXP | 365 | 01/24/2024 | 02/14/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 194731 | 01453 | 10 |  |  | Solar |  | 05_14_74L4 | 08/31/2018 | 09/18/2018 | 4 | 4 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 | 08/31/2018 | 5/21/2019 | Y | EXP | 238 | 03/09/2019 | 04/09/2019 | 31 | 0 | 31 |  |  | 4/16/2019 | Connected |  | N
National Grid | WORCESTER | 738314 | 01604 | 17.86 |  |  | Solar |  | 05_01_219W4 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 176244 | 01550 | 96 |  |  | Solar |  | 05_01_27W5 | 04/30/2015 | 04/30/2015 | 1 | 1 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 12/2/2016 | Connected |  | N
National Grid | WESTMINSTER | 335832 | 01473 | 0 |  |  | Other |  | 05_01_413L3 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 593641 | 02725 | 0 |  |  | Battery Add-On |  | 05_01_609W1 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 03/08/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | GLOUCESTER | 174457 | 01930 | 623 |  |  | Solar |  | 05_05_11W84 | 10/13/2011 | 10/13/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/01/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 | 10/13/2011 | 10/31/2012 | Y | STD | 330 |  |  | 0 | 0 | 0 | 5/30/2013 | 5/30/2013 | 6/13/2013 | Connected |  | N
National Grid | NAHANT | 373988 | 01908 | 9.86 |  |  | Solar |  | 05_12_28L2 | 08/04/2021 | 08/09/2021 | 4 | 2 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | LAWRENCE | 398056 | 01841 | 15.2 |  |  | Solar |  | 05_12_79J2 | 11/29/2021 | 12/08/2021 | 7 | 6 | 1 | 12/09/2021 | 12/09/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  | 5/1/2023 | N | EXP | 420 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 715619 | 01844 | 13.12 |  |  | Solar |  | 05_14_43L4 | 08/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 596892 | 01844 | 5 |  |  | Solar |  | 05_14_5J42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/19/2024 | 8/29/2025 | Y | EXP | 405 | 10/03/2024 | 10/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 200801 | 01453 | 7.6 |  |  | Solar |  | 05_14_74L4 | 11/08/2018 | 12/31/2018 | 2 | 2 | 0 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 3/10/2020 | Y | EXP | 418 | 09/05/2019 | 09/26/2019 | 21 | 0 | 21 |  |  | 10/9/2019 | Connected |  | N
National Grid | WORCESTER | 739118 | 01604 | 23 |  |  | Solar |  | 05_01_219W4 | 12/11/2025 | 12/22/2025 | 6 | 4 | 2 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 209675 | 01550 | 7.6 |  |  | Solar |  | 05_01_27W5 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 02/21/2019 | 10/10/2019 | Y | EXP | 223 | 05/30/2019 | 07/15/2019 | 46 | 0 | 46 |  |  | 8/27/2019 | Connected |  | N
National Grid | HUBBARDSTON | 399464 | 01452 | 2625 |  |  | Solar |  | 05_01_413L3 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 598052 | 02725 | 15.2 |  |  | Solar |  | 05_01_609W1 | 03/23/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/23/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/31/2024 | 29 | 0 | 29 |  |  | 10/2/2024 | Connected |  | N
National Grid | MANCHESTER | 174647 | 01944 | 3000 |  |  | Solar |  | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NAHANT | 397029 | 01908 | 20 |  |  | Solar |  | 05_12_28L2 | 12/09/2021 | 12/20/2021 | 8 | 6 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 1/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 404987 | 01841 | 15.356 |  |  | Solar |  | 05_12_79J2 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2022 | 01/05/2022 | 6/9/2023 | Y | EXP | 365 | 04/28/2022 | 06/08/2022 | 42 | 0 | 42 |  |  | 6/15/2022 | Connected |  | N
National Grid | METHUEN | 725772 | 01844 | 15.2 |  |  | Solar |  | 05_14_43L4 | 10/10/2025 | 10/27/2025 | 9 | 6 | 3 | 10/28/2025 | 10/28/2025 | 43 | 30 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 639677 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J42 | 09/12/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/12/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 215445 | 01453 | 10 |  |  | Solar |  | 05_14_74L4 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175288 | 01604 | 225 |  |  | Solar |  | 05_01_219W4 | 11/06/2014 | 11/06/2014 | 5 | 0 | 5 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2014 |  | 4/1/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 12/19/2014 | 12/19/2014 | 10/22/2015 | Connected |  | Y
National Grid | SOUTHBRIDGE | 210574 | 01550 | 10 |  |  | Solar |  | 05_01_27W5 | 03/14/2019 | 03/15/2019 | 0 | 0 | 0 | 03/18/2019 | 03/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/14/2019 | 11/19/2019 | Y | EXP | 243 | 05/21/2019 | 05/29/2019 | 8 | 0 | 8 |  |  | 6/19/2019 | Connected |  | N
National Grid | WESTMINSTER | 424618 | 01473 | 7.54 |  |  | Solar |  | 05_01_413L3 | 05/04/2022 | 05/09/2022 | 4 | 1 | 3 | 05/10/2022 | 05/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 05/04/2022 | 1/10/2024 | Y | EXP | 365 | 12/28/2022 | 01/10/2023 | 14 | 0 | 14 |  |  | 1/13/2023 | Connected |  | N
National Grid | SOMERSET | 634319 | 02726 | 10 |  |  | Solar |  | 05_01_609W1 | 08/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 08/21/2024 | 1/27/2026 | Y | EXP | 365 | 04/30/2025 |  | 247 | 0 | 247 |  |  | 12/4/2025 | Connected |  | N
National Grid | GLOUCESTER | 174646 | 01930 | 3000 |  |  | Solar |  | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/17/2013 | 6/30/2014 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NAHANT | 422580 | 01908 | 0 |  |  | Solar |  | 05_12_28L2 | 04/08/2022 | 04/21/2022 | 9 | 8 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 |  | 5/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | LAWRENCE | 422671 | 01841 | 15.2 |  |  | Solar |  | 05_12_79J2 | 04/07/2022 | 04/08/2022 | 1 | 0 | 1 | 04/11/2022 | 04/11/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 | 04/07/2022 | 6/6/2024 | Y | EXP | 365 | 05/18/2023 | 06/07/2023 | 21 | 0 | 21 |  |  | 7/10/2023 | Connected |  | N
National Grid | METHUEN | 728924 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 10/24/2025 | 10/27/2025 | 10 | 8 | 2 | 12/09/2025 | 12/09/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 644236 | 01844 | 5.76 |  |  | Solar |  | 05_14_5J42 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 268864 | 01453 | 10 |  |  | Solar |  | 05_14_74L4 | 12/17/2019 | 12/20/2019 | 2 | 0 | 2 | 12/23/2019 | 12/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 | 12/17/2019 | 12/17/2020 | Y | EXP | 365 | 07/16/2020 | 08/19/2020 | 34 | 0 | 34 |  |  | 10/28/2020 | Connected |  | N
National Grid | WORCESTER | 175419 | 01604 | 30 |  |  | Solar |  | 05_01_219W4 | 07/11/2014 | 07/11/2014 | 6 | 0 | 6 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 11/28/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 7/29/2014 | 7/29/2014 | 12/18/2014 | Connected |  | N
National Grid | SOUTHBRIDGE | 243356 | 01550 | 3.8 |  |  | Solar |  | 05_01_27W5 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 | 07/24/2019 | 7/23/2020 | Y | EXP | 365 | 04/17/2020 | 06/09/2020 | 53 | 0 | 53 |  |  | 6/25/2020 | Connected |  | N
National Grid | HUBBARDSTON | 447179 | 01452 | 7.6 |  |  | Solar |  | 05_01_413L3 | 08/31/2022 | 10/14/2022 | 30 | 30 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 | 08/31/2022 | 2/15/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 10/20/2023 | Connected |  | N
National Grid | SOMERSET | 651918 | 02726 | 12.54 |  |  | Solar |  | 05_01_609W1 | 11/04/2024 | 12/05/2024 | 7 | 2 | 5 | 12/06/2024 | 12/06/2024 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 174875 | 01944 | 3000 |  |  | Solar |  | 05_05_11W84 | 09/11/2012 | 09/11/2012 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2012 | 12/24/2012 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/14/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NAHANT | 430870 | 01908 | 15.2 |  |  | Solar |  | 05_12_28L2 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 07/12/2022 | 07/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 538674 | 01844 | 15.2 |  |  | Solar |  | 05_12_79J2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 735576 | 01844 |  |  |  | Solar |  | 05_14_43L4 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | METHUEN | 655097 | 01844 | 10 |  |  | Solar |  | 05_14_5J42 | 11/21/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/21/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 273564 | 01453 | 360 |  |  | Natural Gas |  | 05_14_74L4 | 05/12/2020 | 06/04/2020 | 16 | 10 | 6 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175892 | 01604 | 5 |  |  | Solar |  | 05_01_219W4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 357 | 05/24/2016 | 06/22/2016 | 19 | 0 | 19 | 8/19/2015 | 8/19/2015 | 8/29/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 369971 | 01550 | 7.6 |  |  | Solar |  | 05_01_27W5 | 07/15/2021 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 457748 | 01473 | 0 |  |  | Other |  | 05_01_413L3 | 11/23/2022 | 12/21/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2022 | 01/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 665038 | 02777 | 7.25 |  |  | Solar |  | 05_01_609W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | GLOUCESTER | 175105 | 01930 | 400 |  |  | Solar |  | 05_05_11W84 | 04/08/2013 | 04/08/2013 | 7 | 2 | 5 | 04/22/2013 | 04/22/2013 | 361 | 0 | 361 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NAHANT | 612259 | 01908 | 15.2 |  |  | Solar |  | 05_12_79J2 | 05/20/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | METHUEN | 174281 | 01844 | 55 |  |  | Solar |  | 05_14_43L4 | 12/31/2011 | 12/31/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 03/07/2012 | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 | 12/31/2011 | 1/24/2012 | Y | EXP | -85 | 05/14/2012 | 05/18/2012 | 4 | 0 | 4 | 6/15/2012 | 6/15/2012 | 7/3/2012 | Connected |  | N
National Grid | METHUEN | 660963 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J42 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 281460 | 01841 | 10 |  |  | Solar |  | 05_14_74L4 | 03/11/2020 | 03/23/2020 | 0 | 0 | 0 | 03/24/2020 | 03/24/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/11/2020 | 3/22/2021 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | LEOMINSTER | 184325 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W4 | 05/24/2018 | 05/24/2018 | 21 | 20 | 1 | 06/21/2018 | 06/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 398037 | 01604 | 3.8 |  |  | Solar |  | 05_01_27W5 | 12/17/2021 | 01/07/2022 | 2 | 0 | 2 | 12/22/2021 | 12/22/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 471682 | 01550 | 3.8 |  |  | Solar |  | 05_01_413L3 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 12/05/2022 | 3/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | HUBBARDSTON | 665954 | 01452 | 10 |  |  | Solar |  | 05_01_609W1 | 01/15/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175127 | 02777 | 1760 |  |  | Solar |  | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 558123 | 01930 | 3.8 |  |  | Solar |  | 05_12_28L2 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 52 | 30 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | NAHANT | 639120 | 01908 | 7.36 |  |  | Solar |  | 05_12_7J1 | 09/10/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | METHUEN | 177608 | 01844 | 42 |  |  | Solar |  | 05_14_43L4 | 09/20/2017 | 09/20/2017 | 12 | 11 | 1 | 10/09/2017 | 10/09/2017 | 1 | 0 | 1 | 02/09/2018 | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/26/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 7/16/2018 | Connected |  | N
National Grid | METHUEN | 729809 | 01844 | 10 |  |  | Solar |  | 05_14_5J43 | 10/28/2025 | 10/29/2025 | 18 | 15 | 3 | 12/09/2025 | 12/09/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 590983 | 01844 | 6 |  |  | Solar |  | 05_14_74L4 | 03/11/2024 | 03/13/2024 | 2 | 0 | 2 | 03/14/2024 | 03/14/2024 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 03/11/2024 | 7/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | LEOMINSTER | 194293 | 01453 | 250 |  |  | Solar |  | 05_01_219W4 | 08/24/2018 | 09/04/2018 | 3 | 0 | 3 | 09/05/2018 | 09/05/2018 | 304 | 56 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 462891 | 01604 | 480 |  |  | Solar |  | 05_01_27W5 | 01/20/2023 | 04/10/2023 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 611319 | 01571 | 20 |  |  | Solar |  | 05_01_413L3 | 05/23/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | WESTMINSTER | 668956 | 01473 | 15.2 |  |  | Solar |  | 05_01_609W1 | 01/30/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/30/2025 | 4/3/2026 | Y | EXP | 365 | 06/14/2025 |  | 202 | 0 | 202 |  |  | 11/25/2025 | Connected |  | N
National Grid | SWANSEA | 175126 | 02777 | 1656 |  |  | Solar |  | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2013 | 08/20/2012 | 9/8/2017 | Y | STD | 1456 | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 | 8/29/2017 | 8/29/2017 | 8/31/2017 | Connected |  | N
National Grid | GLOUCESTER | 555498 | 01930 | 23.8 |  |  | Solar |  | 05_12_28L2 | 09/14/2023 | 10/25/2023 | 28 | 23 | 5 | 10/26/2023 | 10/26/2023 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | REVERE | 234799 | 02151 | 10 |  |  | Solar |  | 05_12_7J2 | 07/19/2019 | 07/30/2019 | 6 | 0 | 6 | 07/31/2019 | 07/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | LAWRENCE | 186476 | 01841 | 15.04 |  |  | Solar |  | 05_14_43L4 | 06/04/2018 | 06/04/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2018 | Connected |  | N
National Grid | METHUEN | 515931 | 01844 | 3.8 |  |  | Solar |  | 05_14_5J43 | 04/07/2023 |  | 149 | 148 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 593130 | 01844 | 10 |  |  | Solar |  | 05_14_74L4 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/03/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 11/18/2024 | 126 | 0 | 126 |  |  | 12/21/2024 | Connected |  | N
National Grid | LEOMINSTER | 245798 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W4 | 10/09/2019 | 10/15/2019 | 2 | 0 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 09/16/2020 | 09/21/2020 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 469690 | 01527 | 9.84 |  |  | Solar |  | 05_01_27W5 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/11/2022 | 9/13/2024 | Y | EXP | 365 | 07/20/2023 | 09/14/2023 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 615697 | 01550 | 20 |  |  | Solar |  | 05_01_413L3 | 06/05/2024 | 06/14/2024 | 7 | 5 | 2 | 06/17/2024 | 06/17/2024 | 61 | 50 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 675973 | 01452 | 5.76 |  |  | Solar |  | 05_01_609W1 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 83 | 67 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 175229 | 02777 | 483 |  |  | Solar |  | 05_05_11W84 | 01/07/2015 | 01/07/2015 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 5/31/2015 | N | STD | -36 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 | 2/1/2016 | Connected |  | N
National Grid | GLOUCESTER | 560873 | 01930 | 23 |  |  | Solar |  | 05_12_28L2 | 10/05/2023 | 10/06/2023 | 1 | 0 | 1 | 10/10/2023 | 10/10/2023 | 112 | 91 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2024 | Connected |  | N
National Grid | REVERE | 553820 | 02151 | 8.725 |  |  | Solar |  | 05_12_7J2 | 11/22/2023 | 12/29/2023 | 25 | 20 | 5 | 01/02/2024 | 01/02/2024 | 179 | 25 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 193103 | 01844 | 650 |  |  | Solar |  | 05_14_43L4 | 08/22/2018 | 10/25/2018 | 45 | 3 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 01/31/2019 | 62 | 26 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 588136 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J43 | 04/05/2024 | 04/17/2024 | 7 | 4 | 3 | 04/18/2024 | 04/18/2024 | 91 | 79 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 621133 | 01844 | 15.2 |  |  | Solar |  | 05_14_74L4 | 06/29/2024 | 07/11/2024 | 8 | 6 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 377934 | 01453 | 700 |  |  | Natural Gas |  | 05_01_219W4 | 03/10/2022 | 05/26/2022 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2022 | 11/18/2022 | 120 | 101 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 526849 | 01604 | 9.57 |  |  | Solar |  | 05_01_27W5 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 18 | 0 | 18 | 06/28/2023 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 7/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 648192 | 01507 | 3.8 |  |  | Solar |  | 05_01_413L3 | 10/30/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | WESTMINSTER | 679660 | 01473 | 7.6 |  |  | Solar |  | 05_01_609W1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 175247 | 02777 | 999 |  |  | Solar |  | 05_05_11W84 | 11/04/2014 | 11/04/2014 | 21 | 19 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2014 | 01/05/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 586229 | 01944 | 6 |  |  | Solar |  | 05_12_28L2 | 02/05/2024 | 02/07/2024 | 2 | 0 | 2 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/05/2024 | 3/18/2025 | Y | EXP | 365 | 05/08/2024 | 05/20/2024 | 13 | 0 | 13 |  |  | 7/19/2024 | Connected |  | N
National Grid | REVERE | 583707 | 02151 | 7.6 |  |  | Solar |  | 05_12_7J2 | 01/29/2024 | 02/02/2024 | 5 | 4 | 1 | 02/05/2024 | 02/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/29/2024 | 3/17/2025 | Y | EXP | 365 | 05/09/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 8/20/2024 | Connected |  | N
National Grid | METHUEN | 219512 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 11/14/2019 | 11/20/2019 | 3 | 2 | 1 | 11/21/2019 | 11/21/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 |  | 7/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | METHUEN | 608023 | 01844 | 3.8 |  |  | Solar |  | 05_14_5J43 | 05/02/2024 | 05/09/2024 | 1 | 0 | 1 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 | 05/02/2024 | 8/3/2025 | Y | EXP | 365 | 09/19/2024 | 10/29/2024 | 41 | 0 | 41 |  |  | 1/17/2025 | Connected |  | N
National Grid | LAWRENCE | 624281 | 01841 | 10 |  |  | Solar |  | 05_14_74L4 | 07/15/2024 | 07/23/2024 | 1 | 0 | 1 | 07/24/2024 | 07/24/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 427472 | 01453 | 0 |  |  | Other |  | 05_01_219W4 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 562649 | 01604 | 7.6 |  |  | Solar |  | 05_01_27W5 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/24/2023 | 11/29/2024 | Y | EXP | 365 | 02/23/2024 | 03/26/2024 | 33 | 0 | 33 |  |  | 4/12/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 649412 | 01550 | 3.8 |  |  | Solar |  | 05_01_413L3 | 11/05/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 713491 | 01452 | 11.4 |  |  | Solar |  | 05_01_609W1 | 08/29/2025 | 09/08/2025 | 5 | 0 | 5 | 09/09/2025 | 09/09/2025 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | SWANSEA | 175392 | 02777 | 19.13 |  |  | Solar |  | 05_05_11W84 | 09/15/2014 | 09/15/2014 | 13 | 5 | 8 | 10/03/2014 | 10/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2014 |  | 11/28/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 11/20/2015 | Connected |  | N
National Grid | GLOUCESTER | 624869 | 01930 | 6.825 |  |  | Solar |  | 05_12_28L2 | 07/15/2024 | 03/25/2025 | 4 | 1 | 3 | 03/26/2025 | 03/26/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | REVERE | 638214 | 02151 | 19.76 |  |  | Solar |  | 05_12_7J2 | 09/06/2024 | 09/11/2024 | 3 | 1 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | N
National Grid | LAWRENCE | 326326 | 01841 | 7.6 |  |  | Solar |  | 05_14_43L4 | 01/08/2021 | 01/11/2021 | 0 | 0 | 0 | 01/12/2021 | 01/12/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2021 | 01/08/2021 |  | Y | EXP | 365 | 05/25/2021 | 06/18/2021 | 24 | 0 | 24 |  |  | 8/27/2021 | Connected |  | N
National Grid | METHUEN | 616382 | 01844 | 3.8 |  |  | Solar |  | 05_14_5J43 | 06/07/2024 | 06/28/2024 | 1 | 0 | 1 | 07/01/2024 | 07/01/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/07/2024 | 8/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | METHUEN | 626258 | 01844 | 10 |  |  | Solar |  | 05_14_74L4 | 07/19/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/19/2024 | 8/26/2025 | Y | EXP | 365 | 11/26/2024 | 03/25/2025 | 120 | 0 | 120 |  |  | 4/7/2025 | Connected |  | N
National Grid | LEOMINSTER | 429601 | 01453 | 15.2 |  |  | Solar |  | 05_01_219W4 | 05/11/2022 | 05/16/2022 | 4 | 3 | 1 | 05/17/2022 | 05/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | WORCESTER | 581603 | 01604 | 10 |  |  | Solar |  | 05_01_27W5 | 01/19/2024 | 01/23/2024 | 2 | 0 | 2 | 01/24/2024 | 01/24/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N
National Grid | CHARLTON | 655973 | 01507 | 0 |  |  | Battery Add-On |  | 05_01_413L3 | 11/21/2024 | 11/25/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 58 | 33 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 11/21/2024 | 3/14/2026 | Y | EXP | 365 | 07/26/2025 | 07/29/2025 | 4 | 0 | 4 |  |  | 11/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 301762 | 01473 | 2300 |  |  | Solar |  | 05_01_609W2 | 07/27/2020 | 08/03/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2020 | 08/28/2020 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SWANSEA | 175810 | 02777 | 5 |  |  | Solar |  | 05_05_11W84 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2015 |  | 10/30/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 650150 | 01944 | 23 |  |  | Solar |  | 05_12_28L2 | 10/28/2024 | 11/20/2024 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | REVERE | 638789 | 02151 | 3.8 |  |  | Solar |  | 05_12_7J2 | 09/09/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | METHUEN | 347618 | 01844 | 6.09 |  |  | Solar |  | 05_14_43L4 | 04/15/2021 | 04/22/2021 | 3 | 1 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 625674 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J43 | 07/17/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | METHUEN | 640113 | 01844 | 10 |  |  | Solar |  | 05_14_74L4 | 09/13/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 439536 | 01453 | 18.56 |  |  | Solar |  | 05_01_219W4 | 06/23/2022 | 07/12/2022 | 12 | 10 | 2 | 07/13/2022 | 07/13/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y
National Grid | WORCESTER | 628532 | 01604 | 5.76 |  |  | Solar |  | 05_01_27W5 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/29/2024 | 8/23/2025 | Y | EXP | 365 | 03/06/2025 | 06/06/2025 | 93 | 0 | 93 |  |  | 8/19/2025 | Connected |  | N
National Grid | CHARLTON | 699104 | 01507 | 13.8 |  |  | Solar |  | 05_01_413L3 | 06/24/2025 | 07/22/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/24/2025 | 8/26/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 11/26/2025 | Connected |  | N
National Grid | WESTMINSTER | 695376 | 01473 | 13.96 |  |  | Solar |  | 05_01_609W2 | 06/01/2025 | 10/21/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 175851 | 02725 | 17.6 |  |  | Solar |  | 05_05_11W84 | 05/20/2015 | 05/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 651396 | 01944 | 9.86 |  |  | Solar |  | 05_12_28L2 | 11/01/2024 | 12/02/2024 | 5 | 0 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/01/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 6/20/2025 | Connected |  | N
National Grid | REVERE | 643463 | 02151 | 21.4 |  |  | Solar |  | 05_12_7J2 | 10/22/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/22/2024 | 12/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | METHUEN | 349417 | 01844 | 9.8 |  |  | Solar |  | 05_14_43L4 | 05/13/2021 | 05/21/2021 | 5 | 0 | 5 | 05/24/2021 | 05/24/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | METHUEN | 177329 | 01844 | 120 |  |  | Solar |  | 05_14_5J44 | 06/21/2016 | 06/21/2016 | 2 | 2 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 320 | 02/15/2017 | 02/28/2017 | 8 | 0 | 8 | 4/19/2017 | 4/19/2017 | 4/19/2017 | Connected |  | N
National Grid | METHUEN | 640945 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L4 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 492026 | 01453 | 450 |  |  | Solar |  | 05_01_219W4 | 03/17/2023 |  | 246 | 236 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 635563 | 01604 | 10 |  |  | Solar |  | 05_01_27W5 | 08/26/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 08/26/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 10/01/2025 | 112 | 0 | 112 |  |  | 10/28/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 321753 | 01550 | 0 |  |  | Other |  | 05_01_413L4 | 04/13/2021 | 04/30/2021 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WESTMINSTER | 717106 | 01473 | 3.8 |  |  | Solar |  | 05_01_609W2 | 09/11/2025 | 09/26/2025 | 2 | 0 | 2 | 10/20/2025 | 10/20/2025 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 175880 | 02777 | 450 |  |  | Solar |  | 05_05_11W84 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 101 | 6 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 659984 | 01944 | 11.7 |  |  | Solar |  | 05_12_28L2 | 12/11/2024 | 03/26/2025 | 4 | 1 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | REVERE | 682939 | 02151 | 3.8 |  |  | Solar |  | 05_12_7J2 | 04/04/2025 | 05/05/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/04/2025 | 6/12/2026 | Y | EXP | 365 | 09/11/2025 | 12/01/2025 | 82 | 0 | 82 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 373213 | 01841 | 10 |  |  | Solar |  | 05_14_43L4 | 09/10/2021 | 01/06/2022 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 | 09/10/2021 | 7/27/2023 | Y | EXP | 365 | 06/09/2022 | 06/08/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 258970 | 01844 | 10 |  |  | Solar |  | 05_14_5J44 | 10/24/2019 | 10/25/2019 | 0 | 0 | 0 | 10/28/2019 | 10/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/24/2019 | 10/24/2020 | Y | EXP | 365 | 02/27/2020 | 03/03/2020 | 5 | 0 | 5 |  |  | 3/4/2020 | Connected |  | N
National Grid | LAWRENCE | 642225 | 01841 | 10 |  |  | Solar |  | 05_14_74L4 | 09/23/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 98 | 78 | 20 | 03/31/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/23/2024 | 5/28/2026 | Y | EXP | 365 | 06/28/2025 | 12/22/2025 | 178 | 0 | 178 |  |  | 12/15/2025 | Connected |  | N
National Grid | LEOMINSTER | 652365 | 01453 | 10 |  |  | Solar |  | 05_01_219W4 | 11/14/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 639402 | 01604 | 7.6 |  |  | Solar |  | 05_01_27W5 | 09/11/2024 | 09/24/2024 | 3 | 0 | 3 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | CHARLTON | 684764 | 01507 | 11.4 |  |  | Solar |  | 05_01_413L4 | 06/09/2025 | 07/25/2025 | 10 | 7 | 3 | 08/20/2025 | 08/20/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | WESTMINSTER | 743472 | 01473 | 10 |  |  | Solar |  | 05_01_609W2 | 01/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 176059 | 02777 | 980 |  |  | Solar |  | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2015 | N | STD |  | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 664791 | 01944 | 4.64 |  |  | Solar |  | 05_12_28L2 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | REVERE | 178628 | 02151 | 3.8 |  |  | Solar |  | 05_12_7J3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 378603 | 01844 | 9.8 |  |  | Solar |  | 05_14_43L4 | 09/10/2021 | 01/03/2022 | 3 | 2 | 1 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 290050 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J44 | 05/05/2020 |  | 48 | 48 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 657516 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L4 | 11/27/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/7/2026 | N | EXP | 365 | 03/11/2025 | 03/25/2025 | 15 | 0 | 15 |  |  | 5/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 679496 | 01453 | 5.76 |  |  | Solar |  | 05_01_219W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 644294 | 01604 | 3.8 |  |  | Solar |  | 05_01_27W5 | 10/02/2024 | 11/07/2024 | 13 | 11 | 2 | 11/08/2024 | 11/08/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 709185 | 01550 | 4.537 |  |  | Solar |  | 05_01_413L4 | 08/06/2025 | 08/26/2025 | 15 | 11 | 4 | 10/28/2025 | 10/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTMINSTER | 174115 | 01473 | 2000 |  |  | Solar |  | 05_01_609W2 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176058 | 02777 | 996 |  |  | Solar |  | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 2/24/2016 | 03/27/2015 | 10/15/2017 | Y | STD | 599 | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 | 10/12/2017 | 10/12/2017 | 10/17/2017 | Connected |  | N
National Grid | GLOUCESTER | 676411 | 01930 | 15.2 |  |  | Solar |  | 05_12_28L2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 407783 | 02151 | 3.84 |  |  | Solar |  | 05_12_7J3 | 02/21/2022 | 02/22/2022 | 1 | 0 | 1 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 381715 | 01844 | 11.04 |  |  | Solar |  | 05_14_43L4 | 09/16/2021 | 09/20/2021 | 2 | 0 | 2 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 304996 | 01844 | 7.6 |  |  | Solar |  | 05_14_5J44 | 08/04/2020 | 08/06/2020 | 1 | 0 | 1 | 08/07/2020 | 08/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 661078 | 01844 | 5 |  |  | Solar |  | 05_14_74L4 | 12/17/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 495510 | 01453 | 1600 |  |  | Solar |  | 05_01_219W5 | 04/16/2023 | 06/29/2023 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/26/2023 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 644817 | 01604 | 5.76 |  |  | Solar |  | 05_01_27W5 | 10/03/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 708616 | 01550 | 24.576 |  |  | Solar |  | 05_01_413L4 | 08/06/2025 | 08/14/2025 | 5 | 2 | 3 | 08/15/2025 | 08/15/2025 | 20 | 5 | 15 | 09/26/2025 |  | 65 | 24 | 41 |  |  | 0 | 0 | 0 |  |  | 65 | 24 | 41 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | WESTMINSTER | 174702 | 01473 | 13.5 |  |  | Solar |  | 05_01_609W2 | 01/03/2013 | 01/03/2013 | 16 | 9 | 7 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2013 |  | 3/29/2013 | N | EXP | -55 |  |  | 0 | 0 | 0 | 6/5/2013 | 6/5/2013 | 8/15/2013 | Connected |  | N
National Grid | SWANSEA | 176328 | 02777 | 3.8 |  |  | Solar |  | 05_05_11W84 | 07/20/2015 | 07/20/2015 | 4 | 4 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 07/20/2015 | 7/26/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 5/3/2016 | 5/3/2016 | 5/3/2016 | Connected |  | N
National Grid | GLOUCESTER | 683914 | 01930 | 11.05 |  |  | Solar |  | 05_12_28L2 | 04/09/2025 | 05/07/2025 | 6 | 3 | 3 | 05/08/2025 | 05/08/2025 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | REVERE | 210788 | 02151 | 7.6 |  |  | Solar |  | 05_12_7J4 | 03/04/2019 | 03/05/2019 | 0 | 0 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/04/2019 | 7/21/2020 | Y | EXP | 365 | 02/25/2020 | 03/19/2020 | 23 | 0 | 23 |  |  | 5/26/2020 | Connected |  | N
National Grid | METHUEN | 390053 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 10/26/2021 | 11/02/2021 | 5 | 0 | 5 | 11/03/2021 | 11/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/26/2021 | 2/7/2023 | Y | EXP | 365 | 01/19/2022 | 02/07/2022 | 20 | 0 | 20 |  |  | 2/15/2022 | Connected |  | N
National Grid | METHUEN | 426328 | 01844 | 5.51 |  |  | Solar |  | 05_14_5J44 | 05/11/2022 | 05/24/2022 | 10 | 7 | 3 | 05/25/2022 | 05/25/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2022 | Connected |  | N
National Grid | LAWRENCE | 665950 | 01841 | 0 |  |  | Solar |  | 05_14_74L4 | 01/15/2025 | 01/16/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/15/2025 | 6/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 176008 | 01453 | 6 |  |  | Solar |  | 05_01_219W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 647364 | 01604 | 7.6 |  |  | Solar |  | 05_01_27W5 | 10/30/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 724466 | 01550 | 5.76 |  |  | Solar |  | 05_01_413L4 | 10/06/2025 | 10/13/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/06/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WESTMINSTER | 174879 | 01473 | 1800 |  |  | Solar |  | 05_01_609W2 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176755 | 02725 | 300 |  |  | Solar |  | 05_05_11W84 | 01/13/2016 | 01/13/2016 | 3 | 3 | 0 | 01/19/2016 | 01/19/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/18/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 691827 | 01944 | 23.8 |  |  | Solar |  | 05_12_28L2 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | REVERE | 184583 | 02151 | 15.2 |  |  | Solar |  | 05_12_7J6 | 07/15/2018 | 07/18/2018 | 1 | 0 | 1 | 07/19/2018 | 07/19/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2019 | Connected |  | N
National Grid | METHUEN | 395186 | 01844 | 6 |  |  | Solar |  | 05_14_43L4 | 11/18/2021 | 01/06/2022 | 2 | 0 | 2 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 6/16/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2022 | Connected |  | Y
National Grid | METHUEN | 671959 | 01844 | 11.52 |  |  | Solar |  | 05_14_5J44 | 02/13/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | METHUEN | 668181 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L4 | 01/27/2025 | 02/17/2025 | 15 | 14 | 1 | 02/18/2025 | 02/18/2025 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 176033 | 01453 | 6.45 |  |  | Solar |  | 05_01_219W5 | 06/19/2015 | 06/19/2015 | 2 | 2 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 6/24/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 4/7/2016 | 4/7/2016 | 4/13/2016 | Connected |  | N
National Grid | WORCESTER | 647973 | 01604 | 7.6 |  |  | Solar |  | 05_01_27W5 | 10/28/2024 | 12/12/2024 | 23 | 20 | 3 | 12/13/2024 | 12/13/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 174325 | 01550 | 2000 |  |  | Solar |  | 05_01_413L4 | 01/18/2012 | 01/18/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 06/19/2014 | 34 | 0 | 34 |  |  | 6/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176737 | 01473 | 496 |  |  | Solar |  | 05_01_609W2 | 10/29/2015 | 10/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2015 | 12/04/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 11/3/2016 | N | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177033 | 02725 | 225 |  |  | Solar |  | 05_05_11W84 | 07/26/2016 | 07/26/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 09/15/2016 | 10/13/2016 | 19 | 0 | 19 | 07/28/2016 | 08/25/2016 | 20 | 0 | 20 |  | 10/13/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 713834 | 01930 | 15.2 |  |  | Solar |  | 05_12_28L2 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 08/21/2025 | 10/24/2026 | Y | EXP | 365 | 11/21/2025 |  | 42 | 0 | 42 |  |  | 12/13/2025 | Connected |  | N
National Grid | REVERE | 309830 | 02151 | 10 |  |  | Solar |  | 05_12_7J6 | 09/23/2020 |  | 62 | 54 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 401101 | 01844 | 0 |  |  | Other |  | 05_14_43L4 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/02/2022 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 193954 | 01844 | 357 |  |  | Hydro |  | 05_14_5J45 | 08/31/2018 | 09/27/2018 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 |  | 2/26/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  | 2/12/2021 | Connected |  | N
National Grid | METHUEN | 679170 | 01844 | 10 |  |  | Solar |  | 05_14_74L4 | 03/19/2025 | 05/22/2025 | 4 | 0 | 4 | 05/23/2025 | 05/23/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176908 | 01453 | 231 |  |  | Solar |  | 05_01_219W5 | 03/07/2016 | 03/07/2016 | 4 | 4 | 0 | 03/11/2016 | 03/11/2016 | 425 | 14 | 411 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2016 |  | 3/12/2017 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 660823 | 01604 | 5.76 |  |  | Solar |  | 05_01_27W5 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | Y
National Grid | SOUTHBRIDGE | 174717 | 01550 | 52.8 |  |  | Solar |  | 05_01_413L4 | 01/13/2014 | 01/13/2014 | 6 | 0 | 6 | 01/24/2014 | 01/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2014 |  | 3/31/2014 | N | EXP | 60 |  |  | 0 | 0 | 0 | 3/10/2014 | 3/10/2014 | 7/21/2015 | Connected |  | N
National Grid | WESTMINSTER | 178301 | 01473 | 1440 |  |  | Solar |  | 05_01_609W2 | 11/16/2017 | 11/16/2017 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177209 | 02725 | 10 |  |  | Solar |  | 05_05_11W84 | 06/06/2016 | 06/06/2016 | 1 | 1 | 0 | 06/08/2016 | 06/08/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/12/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 700420 | 01944 | 7.6 |  |  | Solar |  | 05_12_29W1 | 07/01/2025 | 07/15/2025 | 3 | 0 | 3 | 07/24/2025 | 07/24/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 07/01/2025 | 10/4/2026 | Y | EXP | 365 | 11/14/2025 | 11/14/2025 | 1 | 0 | 1 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 330995 | 02151 | 10 |  |  | Solar |  | 05_12_7J6 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 435737 | 01844 | 15.2 |  |  | Solar |  | 05_14_43L4 | 06/06/2022 | 06/16/2022 | 9 | 8 | 1 | 06/17/2022 | 06/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | N
National Grid | METHUEN | 178560 | 01844 | 432.9 |  |  | Solar |  | 05_14_60L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 44 | 19 | 25 | 07/02/2018 | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 | 4/12/2019 | 04/05/2018 | 6/4/2026 | Y | STD | 154 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | METHUEN | 681572 | 01844 | 0 |  |  | Solar |  | 05_14_74L4 | 04/02/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176925 | 01453 | 500 |  |  | Solar |  | 05_01_219W5 | 11/20/2015 | 11/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/06/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 | 8/2/2016 | 11/20/2015 | 4/27/2018 | Y | STD | 633 | 10/23/2017 | 03/02/2018 | 83 | 0 | 83 | 4/11/2018 | 4/11/2018 | 4/27/2018 | Connected |  | N
National Grid | WORCESTER | 667511 | 01604 | 11.4 |  |  | Solar |  | 05_01_27W5 | 02/04/2025 | 03/11/2025 | 16 | 12 | 4 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | CHARLTON | 174814 | 01507 | 60 |  |  | Solar |  | 05_01_413L4 | 07/30/2013 | 07/30/2013 | 6 | 0 | 6 | 08/08/2013 | 08/08/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2013 |  | 1/31/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N
National Grid | WESTMINSTER | 178331 | 01473 | 3000 |  |  | Solar |  | 05_01_609W2 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/19/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/16/2017 | 3/26/2021 | Y | STD | 564 | 06/05/2020 | 03/05/2021 | 273 | 41 | 232 | 2/18/2021 | 3/4/2021 | 3/12/2021 | Connected |  | N
National Grid | SWANSEA | 177350 | 02777 | 7.6 |  |  | Solar |  | 05_05_11W84 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/20/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 703718 | 01905 | 6.72 |  |  | Solar |  | 05_12_29W1 | 07/09/2025 | 07/29/2025 | 9 | 3 | 6 | 09/30/2025 | 09/30/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 07/09/2025 | 12/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 333059 | 02151 | 7.6 |  |  | Solar |  | 05_12_7J6 | 03/08/2021 | 03/10/2021 | 1 | 0 | 1 | 03/11/2021 | 03/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/5/2022 | N | EXP | 480 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 470911 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 11/17/2022 |  | 162 | 50 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 555669 | 01951 | 0 |  |  | Solar |  | 05_14_60L1 | 09/14/2023 | 09/19/2023 | 4 | 3 | 1 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/14/2026 | N | EXP | 1095 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 685925 | 01844 | 11.52 |  |  | Solar |  | 05_14_74L4 | 04/17/2025 | 07/21/2025 | 7 | 2 | 5 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 177974 | 01453 | 6 |  |  | Solar |  | 05_01_219W5 | 06/27/2017 | 06/27/2017 | 37 | 36 | 1 | 08/18/2017 | 08/18/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/2/2018 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 680717 | 01604 | 7.6 |  |  | Solar |  | 05_01_27W5 | 03/26/2025 | 04/11/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 175235 | 01507 | 480 |  |  | Solar |  | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/18/2016 | 04/01/2016 | 51 | 0 | 51 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 272136 | 01473 | 5000 |  |  | Other |  | 05_01_609W2 | 03/03/2020 | 03/17/2020 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 177712 | 02777 | 1000 |  |  | Solar |  | 05_05_11W84 | 07/25/2017 | 07/25/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2017 | 12/15/2017 | 79 | 0 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 717420 | 01905 | 5.76 |  |  | Solar |  | 05_12_29W1 | 09/10/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/10/2025 | 11/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 471831 | 02151 | 15.2 |  |  | Solar |  | 05_12_7J6 | 10/27/2022 | 10/28/2022 | 1 | 0 | 1 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | LAWRENCE | 479994 | 01841 | 7.6 |  |  | Solar |  | 05_14_43L4 | 12/19/2022 | 12/26/2022 | 5 | 0 | 5 | 12/27/2022 | 12/27/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 703373 | 01951 | 6.64 |  |  | Solar |  | 05_14_60L1 | 07/08/2025 | 07/10/2025 | 2 | 0 | 2 | 07/11/2025 | 07/11/2025 | 101 | 88 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LAWRENCE | 688618 | 01841 | 3.8 |  |  | Solar |  | 05_14_74L4 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 09/25/2025 |  | 99 | 0 | 99 |  |  | 12/3/2025 | Connected |  | N
National Grid | LEOMINSTER | 178765 | 01453 | 495 |  |  | Solar |  | 05_01_219W5 | 07/29/2013 | 07/29/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2013 | 03/03/2014 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2014 |  | 1/31/2014 | N | STD | -41 |  |  | 0 | 0 | 0 | 7/14/2014 | 7/14/2014 | 7/24/2014 | Connected |  | N
National Grid | WORCESTER | 681379 | 01604 | 15.2 |  |  | Solar |  | 05_01_27W5 | 03/28/2025 | 04/01/2025 | 2 | 0 | 2 | 04/02/2025 | 04/02/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175237 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 310476 | 01473 | 10 |  |  | Hydro |  | 05_01_609W2 | 09/03/2020 | 10/07/2020 | 23 | 17 | 6 | 10/08/2020 | 10/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | SOMERSET | 177736 | 02725 | 3.6 |  |  | Solar |  | 05_05_11W84 | 03/23/2017 | 03/23/2017 | 6 | 6 | 0 | 03/31/2017 | 03/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/23/2017 | 3/28/2018 | Y | EXP | 358 | 08/09/2017 | 08/14/2017 | 3 | 0 | 3 | 3/1/2018 | 3/1/2018 | 3/23/2018 | Connected |  | N
National Grid | LYNN | 721288 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 09/23/2025 | 10/21/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 567022 | 02151 | 6.96 |  |  | Solar |  | 05_12_7J6 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N
National Grid | METHUEN | 486205 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 12/27/2022 | 12/29/2022 | 2 | 0 | 2 | 12/30/2022 | 12/30/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | NEWBURY | 175109 | 01951 | 1992 |  |  | Solar |  | 05_14_60L1 | 04/22/2013 | 04/22/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2013 | 06/24/2013 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2014 | 04/22/2013 | 12/31/2016 | Y | STD | 943 | 01/03/2017 | 04/18/2017 | 72 | 0 | 72 |  |  | 5/4/2017 | Connected |  | N
National Grid | LAWRENCE | 703871 | 01841 | 17.16 |  |  | Solar |  | 05_14_74L5 | 07/09/2025 | 07/31/2025 | 12 | 8 | 4 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 186058 | 01453 | 4600 |  |  | Solar |  | 05_01_219W5 | 06/28/2018 | 06/28/2018 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 6/28/2021 | N | STD | 613 | 12/04/2020 | 06/10/2021 | 188 | 0 | 188 |  |  | 6/21/2021 | Connected |  | N
National Grid | WORCESTER | 684979 | 01604 | 15.2 |  |  | Solar |  | 05_01_27W5 | 04/14/2025 | 04/23/2025 | 4 | 1 | 3 | 04/24/2025 | 04/24/2025 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 175236 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 311776 | 01473 | 4990 |  |  | Solar |  | 05_01_609W2 | 10/05/2020 | 10/14/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2020 | 11/09/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177848 | 02725 | 300 |  |  | Natural Gas |  | 05_05_11W84 | 04/06/2017 | 04/06/2017 | 54 | 54 | 0 | 06/26/2017 | 06/26/2017 | 189 | 53 | 136 | 08/17/2017 | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 | 12/15/2017 |  | 4/12/2018 | N | EXP | 118 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 731709 | 01905 | 3.8 |  |  | Solar |  | 05_12_29W1 | 11/05/2025 | 11/19/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 562600 | 02151 | 6 |  |  | Solar |  | 05_12_7J6 | 10/16/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 87 | 69 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 489999 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 02/10/2023 |  | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 175203 | 01951 | 3000 |  |  | Solar |  | 05_14_60L1 | 11/30/2012 | 11/30/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2012 | 01/14/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 177322 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L5 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/3/2016 | 11/3/2016 | 11/7/2016 | Connected |  | N
National Grid | LANCASTER | 373151 | 01523 | 7.6 |  |  | Solar |  | 05_01_219W5 | 08/18/2021 | 08/31/2021 | 8 | 3 | 5 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 689710 | 01604 | 5.76 |  |  | Solar |  | 05_01_27W5 | 05/05/2025 | 05/20/2025 | 2 | 0 | 2 | 05/28/2025 | 05/28/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 175264 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 660 | 03/29/2016 | 04/01/2016 | 3 | 0 | 3 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | WESTMINSTER | 356001 | 01473 | 7.68 |  |  | Solar |  | 05_01_609W2 | 05/03/2021 | 05/04/2021 | 0 | 0 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 5/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | SOMERSET | 178036 | 02726 | 9.86 |  |  | Solar |  | 05_05_11W84 | 10/27/2017 | 10/27/2017 | 39 | 39 | 0 | 01/04/2018 | 01/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 11/5/2018 | N | EXP | 301 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | LYNN | 742453 | 01905 | 17.16 |  |  | Solar |  | 05_12_29W1 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 599877 | 02151 | 6 |  |  | Solar |  | 05_12_7J6 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/15/2024 | 4/25/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/19/2025 | Connected |  | Y
National Grid | METHUEN | 491242 | 01844 | 7.83 |  |  | Solar |  | 05_14_43L4 | 01/20/2023 | 01/25/2023 | 3 | 1 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/20/2023 | 8/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | NEWBURY | 176968 | 01951 | 20 |  |  | Solar |  | 05_14_60L1 | 10/04/2016 | 10/04/2016 | 2 | 2 | 0 | 10/06/2016 | 10/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 |  | 10/9/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/31/2017 | 8/31/2017 | 8/31/2017 | Connected |  | N
National Grid | METHUEN | 177355 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L5 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | LEOMINSTER | 438321 | 01453 | 5.22 |  |  | Solar |  | 05_01_219W5 | 06/21/2022 | 06/23/2022 | 2 | 1 | 1 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/21/2022 | 4/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | WORCESTER | 175928 | 01604 | 99 |  |  | Solar |  | 05_01_2J328 | 08/05/2015 | 08/05/2015 | 2 | 2 | 0 | 08/10/2015 | 08/10/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/11/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175396 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 11/17/2014 | 11/17/2014 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 371839 | 01473 | 15.2 |  |  | Solar |  | 05_01_609W2 | 07/23/2021 | 07/28/2021 | 4 | 3 | 1 | 07/29/2021 | 07/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | SOMERSET | 178046 | 02725 | 3.8 |  |  | Solar |  | 05_05_11W84 | 05/05/2017 | 05/05/2017 | 2 | 2 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2017 |  | 5/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | LYNN | 176207 | 01904 | 11.4 |  |  | Solar |  | 05_12_29W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/30/2015 | 04/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 08/29/2016 | 09/30/2016 | 23 | 0 | 23 | 9/12/2016 | 9/12/2016 | 9/12/2016 | Connected |  | N
National Grid | REVERE | 602832 | 02151 | 6 |  |  | Solar |  | 05_12_7J6 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 512389 | 01844 | 9.86 |  |  | Solar |  | 05_14_43L4 | 05/10/2023 | 05/15/2023 | 3 | 0 | 3 | 05/16/2023 | 05/16/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 178071 | 01950 | 15.2 |  |  | Solar |  | 05_14_60L1 | 10/31/2017 | 10/31/2017 | 0 | 0 | 0 | 11/06/2017 | 11/06/2017 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 11/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177904 | 01832 | 20 |  |  | Solar |  | 05_14_74L5 | 08/15/2017 | 08/15/2017 | 15 | 15 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 8/20/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | LEOMINSTER | 472241 | 01453 | 6.38 |  |  | Solar |  | 05_01_219W5 | 11/17/2022 | 01/30/2023 | 47 | 46 | 1 | 01/31/2023 | 01/31/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 5/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2023 | Connected |  | N
National Grid | WORCESTER | 376505 | 01602 | 43.2 |  |  | Solar |  | 05_01_2J328 | 08/18/2021 | 09/10/2021 | 16 | 6 | 10 |  |  | 200 | 172 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  | 11/20/2023 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 175474 | 01550 | 984 |  |  | Solar |  | 05_01_413L4 | 12/05/2014 | 12/05/2014 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/09/2015 | 18 | 18 | 0 |  |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 39 | 39 | 0 | 2/5/2016 | 12/05/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | WESTMINSTER | 373050 | 01473 | 7.68 |  |  | Solar |  | 05_01_609W2 | 08/05/2021 | 08/27/2021 | 17 | 16 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 1/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N
National Grid | SWANSEA | 178101 | 02777 | 3.8 |  |  | Solar |  | 05_05_11W84 | 09/08/2017 | 09/08/2017 | 7 | 7 | 0 | 09/19/2017 | 09/19/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 9/13/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/25/2018 | Connected |  | N
National Grid | LYNN | 176763 | 01904 | 6 |  |  | Solar |  | 05_12_29W1 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 5/1/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 |  | Withdrawn |  | Y
National Grid | REVERE | 189881 | 02151 | 3.8 |  |  | Solar |  | 05_12_7J7 | 07/03/2018 | 07/03/2018 | 5 | 0 | 5 | 10/31/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 521781 | 01844 | 11.04 |  |  | Solar |  | 05_14_43L4 | 04/27/2023 |  | 136 | 135 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 178240 | 01951 | 10 |  |  | Solar |  | 05_14_60L1 | 02/20/2018 | 02/20/2018 | 6 | 6 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 |  | 2/25/2019 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 10/17/2018 | Connected |  | N
National Grid | METHUEN | 178343 | 01844 | 500 |  |  | Solar |  | 05_14_74L5 | 01/10/2018 | 01/10/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 05/10/2018 | 11/16/2018 | 133 | 109 | 24 | 03/12/2018 | 04/09/2018 | 15 | 0 | 15 |  | 11/16/2018 | 133 | 109 | 24 |  |  | 0 | 0 | 0 | 12/20/2018 |  | 11/15/2019 | N | STD | 330 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 505826 | 01453 | 6 |  |  | Solar |  | 05_01_219W5 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 646548 | 01602 | 3.8 |  |  | Solar |  | 05_01_2J328 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 15 | 0 | 15 | 12/05/2024 | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 175473 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 12/02/2014 | 12/02/2014 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 01/09/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 38 | 1 | 37 | 2/5/2016 | 12/02/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | WESTMINSTER | 413977 | 01473 | 13.05 |  |  | Solar |  | 05_01_609W2 | 06/28/2022 | 07/01/2022 | 3 | 0 | 3 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/28/2022 | 1/18/2024 | Y | EXP | 365 | 01/07/2023 | 01/14/2023 | 8 | 0 | 8 |  |  | 6/29/2023 | Connected |  | N
National Grid | SWANSEA | 178265 | 02777 | 4998 |  |  | Solar |  | 05_05_11W84 | 01/08/2018 | 03/06/2018 | 27 | 20 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/10/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 |  | 7/9/2020 | N | STD | 660 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177003 | 01905 | 6.6 |  |  | Solar |  | 05_12_29W1 | 10/07/2016 | 10/07/2016 | 1 | 1 | 0 | 10/11/2016 | 10/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/07/2016 | 3/30/2018 | Y | EXP | 529 | 10/09/2017 | 10/11/2017 | 1 | 0 | 1 | 2/12/2018 | 2/12/2018 | 3/23/2018 | Connected |  | N
National Grid | REVERE | 225696 | 02151 | 7.6 |  |  | Solar |  | 05_12_7J7 | 06/12/2019 | 06/18/2019 | 3 | 0 | 3 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/12/2019 | 4/23/2021 | Y | EXP | 365 | 10/03/2020 | 11/18/2020 | 46 | 0 | 46 |  |  | 1/8/2021 | Connected |  | N
National Grid | METHUEN | 524638 | 01844 | 6 |  |  | Solar |  | 05_14_43L4 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 178380 | 01951 | 20 |  |  | Solar |  | 05_14_60L1 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 04/10/2018 | 04/10/2018 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2018 |  | 1/20/2019 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 193466 | 01832 | 15.2 |  |  | Solar |  | 05_14_74L5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 540185 | 01453 | 4.35 |  |  | Solar |  | 05_01_219W5 | 08/31/2023 | 09/01/2023 | 1 | 0 | 1 | 09/05/2023 | 09/05/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/31/2023 | 10/13/2024 | Y | EXP | 365 | 01/18/2024 | 02/07/2024 | 21 | 0 | 21 |  |  | 2/7/2024 | Connected |  | N
National Grid | WORCESTER | 340607 | 01602 | 726.6 |  |  | Solar |  | 05_01_2J335 | 10/13/2021 | 02/28/2022 | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2022 | 03/01/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 | 10/13/2021 | 1/21/2026 | Y | STD | 245 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 175559 | 01550 | 480 |  |  | Solar |  | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 461669 | 01473 | 7.68 |  |  | Solar |  | 05_01_609W2 | 10/05/2022 | 10/10/2022 | 3 | 0 | 3 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 10/05/2022 |  | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 178294 | 02777 | 2050 |  |  | Solar |  | 05_05_11W84 | 11/14/2017 | 11/14/2017 | 49 | 49 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 03/23/2018 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177253 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 06/14/2016 | 6/20/2017 | Y | EXP | 358 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | REVERE | 659647 | 02151 | 5.76 |  |  | Solar |  | 05_12_7J7 | 12/10/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 527661 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 190362 | 01951 | 15.2 |  |  | Solar |  | 05_14_60L1 | 07/25/2018 | 08/28/2018 | 23 | 23 | 0 | 08/29/2018 | 08/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  | 9/6/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2019 | Connected |  | N
National Grid | HAVERHILL | 296655 | 01832 | 7.6 |  |  | Solar |  | 05_14_74L5 | 06/18/2020 | 06/23/2020 | 2 | 0 | 2 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 546565 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W5 | 08/08/2023 |  | 120 | 120 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 725024 | 01602 | 7.6 |  |  | Solar |  | 05_01_2J335 | 10/08/2025 | 11/11/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 175558 | 01507 | 480 |  |  | Solar |  | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/3/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 473722 | 01473 | 8.99 |  |  | Solar |  | 05_01_609W2 | 11/23/2022 | 11/29/2022 | 3 | 1 | 2 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 6/8/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 6/16/2023 | Connected |  | Y
National Grid | SOMERSET | 197466 | 02725 | 480 |  |  | Solar |  | 05_05_11W84 | 01/16/2019 | 02/04/2019 | 12 | 4 | 8 | 02/05/2019 | 02/05/2019 | 23 | 11 | 12 | 04/10/2019 | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 5/4/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 204587 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 01/07/2019 | 01/18/2019 | 8 | 0 | 8 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/07/2019 | 9/16/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | REVERE | 725831 | 02151 | 5.76 |  |  | Solar |  | 05_12_7J901 | 10/10/2025 | 12/10/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 527935 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 296240 | 01951 | 3.8 |  |  | Solar |  | 05_14_60L1 | 07/03/2020 | 07/08/2020 | 2 | 0 | 2 | 07/09/2020 | 07/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 357875 | 01832 | 9.8 |  |  | Solar |  | 05_14_74L5 | 05/25/2021 | 05/26/2021 | 0 | 0 | 0 | 05/27/2021 | 05/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2021 |  | 8/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | LEOMINSTER | 554393 | 01453 | 12.285 |  |  | Solar |  | 05_01_219W5 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | WORCESTER | 743680 | 01602 | 13.36 |  |  | Solar |  | 05_01_2J335 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHARLTON | 175600 | 01507 | 1000 |  |  | Solar |  | 05_01_413L4 | 08/04/2014 | 08/04/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2014 | 09/15/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 08/04/2014 | 7/30/2018 | Y | STD | 980 | 11/28/2016 | 03/28/2017 | 82 | 0 | 82 |  |  | 7/20/2018 | Connected |  | N
National Grid | WESTMINSTER | 485301 | 01473 | 11.4 |  |  | Solar |  | 05_01_609W2 | 12/28/2022 |  | 136 | 59 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 259604 | 02777 | 7.6 |  |  | Solar |  | 05_05_11W84 | 10/29/2019 | 10/30/2019 | 0 | 0 | 0 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 205264 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 02/04/2019 | 02/07/2019 | 3 | 3 | 0 | 02/08/2019 | 02/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176380 | 01905 | 1520 |  |  | Solar |  | 05_12_7J901 | 11/23/2015 | 11/23/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 12/18/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 11/29/2016 | N | STD | 251 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/12/2016 | Connected |  | Y
National Grid | METHUEN | 534617 | 01844 | 11.31 |  |  | Solar |  | 05_14_43L4 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/27/2023 | 10/31/2024 | Y | EXP | 365 | 12/06/2023 | 12/12/2023 | 7 | 0 | 7 |  |  | 1/12/2024 | Connected |  | N
National Grid | NEWBURY | 316180 | 01951 | 6 |  |  | Solar |  | 05_14_60L1 | 10/15/2020 | 10/20/2020 | 2 | 0 | 2 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/15/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2021 | Connected |  | N
National Grid | METHUEN | 375924 | 01844 | 9.8 |  |  | Solar |  | 05_14_74L5 | 08/26/2021 | 12/07/2021 | 3 | 0 | 3 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2022 | Connected |  | N
National Grid | LEOMINSTER | 642791 | 01453 | 15.2 |  |  | Solar |  | 05_01_219W5 | 03/11/2025 | 03/27/2025 | 12 | 8 | 4 | 03/28/2025 | 03/28/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | WORCESTER | 742117 | 01602 | 20 |  |  | Solar |  | 05_01_2J335 | 12/23/2025 | 01/02/2026 | 5 | 2 | 3 | 01/05/2026 | 01/05/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 175654 | 01507 | 480 |  |  | Solar |  | 05_01_413L4 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 46 | 8 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2014 |  | 10/31/2014 | N | EXP | 128 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 557260 | 01473 | 0 |  |  | Solar |  | 05_01_609W2 | 09/21/2023 | 10/06/2023 | 11 | 10 | 1 | 10/10/2023 | 10/10/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | SOMERSET | 274437 | 02725 | 6 |  |  | Solar |  | 05_05_11W84 | 01/30/2020 | 02/11/2020 | 7 | 3 | 4 | 02/12/2020 | 02/12/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/30/2020 | 2/5/2021 | Y | EXP | 365 | 06/25/2020 | 08/12/2020 | 48 | 0 | 48 |  |  | 10/16/2020 | Connected |  | N
National Grid | LYNN | 207594 | 01904 | 6 |  |  | Solar |  | 05_12_29W1 | 02/05/2019 | 02/13/2019 | 6 | 6 | 0 | 02/14/2019 | 02/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/05/2019 | 2/5/2020 | Y | EXP | 349 | 09/25/2019 | 11/19/2019 | 55 | 0 | 55 |  |  | 12/3/2019 | Connected |  | N
National Grid | LYNN | 280354 | 01905 | 7.6 |  |  | Solar |  | 05_12_7J901 | 03/04/2020 | 06/02/2020 | 63 | 62 | 1 | 06/03/2020 | 06/03/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 | 03/04/2020 | 6/2/2021 | Y | EXP | 365 | 12/11/2020 | 03/16/2021 | 95 | 0 | 95 |  |  | 3/19/2021 | Connected |  | N
National Grid | METHUEN | 553269 | 01844 | 6 |  |  | Solar |  | 05_14_43L4 | 09/15/2023 | 09/28/2023 | 9 | 7 | 2 | 09/29/2023 | 09/29/2023 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 344862 | 01951 | 7.6 |  |  | Solar |  | 05_14_60L1 | 03/03/2021 | 03/04/2021 | 0 | 0 | 0 | 03/05/2021 | 03/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2022 | Connected |  | N
National Grid | HAVERHILL | 401112 | 01832 | 0 |  |  | Other |  | 05_14_74L5 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 651521 | 01453 | 10 |  |  | Solar |  | 05_01_219W5 | 11/13/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | WORCESTER | 475993 | 01602 | 15.08 |  |  | Solar |  | 05_01_2J335 | 11/09/2022 | 12/07/2022 | 18 | 17 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 2/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | CHARLTON | 176353 | 01507 | 2500 |  |  | Solar |  | 05_01_413L4 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 11/25/2015 | 12/23/2015 | 19 | 0 | 19 | 12/23/2015 | 05/15/2015 | 10/30/2015 | Y | STD | -54 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | WESTMINSTER | 605267 | 01473 | 20 |  |  | Solar |  | 05_01_609W2 | 04/24/2024 | 05/01/2024 | 5 | 4 | 1 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 290789 | 02777 | 10 |  |  | Solar |  | 05_05_11W84 | 05/06/2020 | 05/14/2020 | 5 | 5 | 0 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 | 05/06/2020 | 5/7/2021 | Y | EXP | 365 | 07/02/2020 | 08/31/2020 | 59 | 0 | 59 |  |  | 9/2/2020 | Connected |  | N
National Grid | LYNN | 252203 | 01905 | 11.4 |  |  | Solar |  | 05_12_29W1 | 10/01/2019 | 11/06/2019 | 25 | 25 | 0 | 11/07/2019 | 11/07/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/01/2019 | 12/7/2020 | Y | EXP | 365 | 08/05/2020 | 11/16/2020 | 104 | 5 | 99 |  |  | 11/24/2020 | Connected |  | N
National Grid | LYNN | 603654 | 01905 | 3.8 |  |  | Solar |  | 05_12_7J901 | 04/15/2024 | 04/23/2024 | 7 | 3 | 4 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 04/15/2024 | 5/16/2025 | Y | EXP | 365 | 08/29/2024 | 12/05/2024 | 99 | 0 | 99 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 564231 | 01841 | 7.6 |  |  | Solar |  | 05_14_43L4 | 11/08/2023 | 11/17/2023 | 6 | 3 | 3 | 11/20/2023 | 11/20/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | NEWBURY | 349237 | 01951 | 0 |  |  | Solar |  | 05_14_60L1 | 04/08/2021 | 04/27/2021 | 12 | 12 | 0 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 8/24/2022 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 565286 | 01832 | 11.97 |  |  | Solar |  | 05_14_74L5 | 01/05/2024 | 01/08/2024 | 1 | 0 | 1 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 | 01/05/2024 | 2/14/2025 | Y | EXP | 365 | 06/28/2024 | 07/01/2024 | 4 | 0 | 4 |  |  | 8/16/2024 | Connected |  | N
National Grid | LEOMINSTER | 655465 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W5 | 11/20/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 523999 | 01609 | 6.09 |  |  | Solar |  | 05_01_2J335 | 09/14/2023 | 09/15/2023 | 1 | 0 | 1 | 09/18/2023 | 09/18/2023 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176661 | 01507 | 720 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2016 | 06/02/2016 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 646003 | 01473 | 5 |  |  | Solar |  | 05_01_609W2 | 10/10/2024 | 11/04/2024 | 5 | 0 | 5 | 11/05/2024 | 11/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/10/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SWANSEA | 292543 | 02777 | 3.8 |  |  | Solar |  | 05_05_11W84 | 06/25/2020 | 06/29/2020 | 1 | 0 | 1 | 06/30/2020 | 06/30/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 06/25/2020 | 8/1/2021 | Y | EXP | 365 | 12/16/2020 | 01/25/2021 | 40 | 0 | 40 |  |  | 2/9/2021 | Connected |  | N
National Grid | LYNN | 307291 | 01904 | 6.72 |  |  | Solar |  | 05_12_29W1 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 10/20/2020 | 9/25/2022 | Y | EXP | 365 | 09/09/2021 | 09/23/2021 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 657216 | 01905 | 2.9 |  |  | Solar |  | 05_12_7J901 | 11/27/2024 | 02/25/2025 | 6 | 3 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | LAWRENCE | 578821 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 07/15/2024 | 01/08/2024 | 6 | 1 | 5 | 07/24/2024 | 07/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | NEWBURY | 367210 | 01951 | 7.6 |  |  | Solar |  | 05_14_60L1 | 07/01/2021 | 11/01/2021 | 84 | 63 | 21 | 11/02/2021 | 11/02/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 10/31/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 569971 | 01844 | 16.53 |  |  | Solar |  | 05_14_74L5 | 11/08/2023 | 11/21/2023 | 8 | 5 | 3 | 11/22/2023 | 11/22/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 680944 | 01453 | 20 |  |  | Solar |  | 05_01_219W5 | 03/27/2025 | 04/14/2025 | 12 | 8 | 4 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 609781 | 01602 |  |  |  | Solar |  | 05_01_2J335 | 11/26/2024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 176659 | 01550 | 936 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 656341 | 01473 | 10 |  |  | Solar |  | 05_01_609W2 | 11/22/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 298454 | 02725 | 23.4 |  |  | Solar |  | 05_05_11W84 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | LYNN | 311321 | 01905 | 6.48 |  |  | Solar |  | 05_12_29W1 | 10/12/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 60 | 41 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2021 | Connected |  | N
National Grid | LYNN | 657861 | 01905 | 5.76 |  |  | Solar |  | 05_12_7J901 | 12/05/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | LAWRENCE | 585644 | 01841 | 9.28 |  |  | Solar |  | 05_14_43L4 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 3/6/2025 | Y | EXP | 365 | 07/16/2024 | 11/04/2024 | 112 | 0 | 112 |  |  | 11/9/2024 | Connected |  | N
National Grid | NEWBURY | 421113 | 01951 | 0 |  |  | Solar |  | 05_14_60L1 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  | 4/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | METHUEN | 642704 | 01844 | 10 |  |  | Solar |  | 05_14_74L5 | 09/25/2024 | 10/02/2024 | 5 | 0 | 5 | 10/03/2024 | 10/03/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/25/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/17/2025 | 3 | 0 | 3 |  |  | 5/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 683085 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W5 | 04/04/2025 | 05/08/2025 | 24 | 22 | 2 | 05/09/2025 | 05/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 645982 | 01602 | 8.32 |  |  | Solar |  | 05_01_2J335 | 10/09/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 176693 | 01550 | 1872 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 666877 | 01473 | 7.6 |  |  | Solar |  | 05_01_609W2 | 01/21/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | SWANSEA | 318194 | 02777 | 5.76 |  |  | Solar |  | 05_05_11W84 | 10/08/2020 | 10/20/2020 | 7 | 6 | 1 | 10/21/2020 | 10/21/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | LYNN | 313176 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 11/02/2020 | 11/03/2020 | 0 | 0 | 0 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 11/02/2020 | 11/2/2021 | Y | EXP | 365 | 03/25/2021 | 08/16/2021 | 144 | 0 | 144 |  |  | 9/7/2021 | Connected |  | N
National Grid | LYNN | 691255 | 01905 | 3.8 |  |  | Solar |  | 05_12_7J901 | 05/13/2025 | 05/23/2025 | 1 | 0 | 1 | 06/16/2025 | 06/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/13/2025 | 7/15/2026 | Y | EXP | 365 | 10/01/2025 | 11/18/2025 | 49 | 0 | 49 |  |  | 12/15/2025 | Connected |  | N
National Grid | METHUEN | 589208 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/23/2024 | 4/23/2025 | Y | EXP | 365 | 07/16/2024 | 09/20/2024 | 67 | 0 | 67 |  |  | 10/23/2024 | Connected |  | N
National Grid | NEWBURY | 508264 | 01951 | 9.57 |  |  | Solar |  | 05_14_60L1 | 03/28/2023 | 03/30/2023 | 2 | 1 | 1 | 03/31/2023 | 03/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 5/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | METHUEN | 643144 | 01844 | 5.76 |  |  | Solar |  | 05_14_74L5 | 09/26/2024 | 11/09/2024 | 13 | 11 | 2 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 | 12/31/2024 | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 09/26/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 725691 | 01453 | 5.76 |  |  | Solar |  | 05_01_219W6 | 10/10/2025 | 11/07/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 662096 | 01602 | 3.8 |  |  | Solar |  | 05_01_2J335 | 12/20/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 176692 | 01550 | 1872 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 673174 | 01473 | 10 |  |  | Solar |  | 05_01_609W2 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 97 | 57 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 322573 | 02777 | 22.05 |  |  | Solar |  | 05_05_11W84 | 02/08/2021 | 02/25/2021 | 11 | 8 | 3 | 02/26/2021 | 02/26/2021 | 66 | 41 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 9/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | Y
National Grid | LYNN | 362142 | 01905 | 7.6 |  |  | Solar |  | 05_12_29W1 | 07/01/2021 | 01/06/2022 | 6 | 0 | 6 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 | 07/01/2021 | 8/21/2024 | Y | EXP | 365 | 03/22/2022 | 08/18/2023 | 515 | 0 | 515 |  |  | 9/8/2023 | Connected |  | N
National Grid | LYNN | 177808 | 01905 | 7.6 |  |  | Solar |  | 05_12_7J903 | 10/12/2017 | 10/12/2017 | 8 | 0 | 8 | 10/25/2017 | 10/25/2017 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/18/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 591270 | 01844 | 6 |  |  | Solar |  | 05_14_43L4 | 02/23/2024 | 02/26/2024 | 1 | 0 | 1 | 02/27/2024 | 02/27/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 02/23/2024 | 3/27/2025 | Y | EXP | 365 | 05/30/2024 | 07/17/2024 | 49 | 0 | 49 |  |  | 7/19/2024 | Connected |  | N
National Grid | NEWBURY | 520810 | 01532 | 0 |  |  | Other |  | 05_14_60L1 | 06/02/2023 | 06/22/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 08/14/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 648578 | 01832 | 3.8 |  |  | Solar |  | 05_14_74L5 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 176432 | 01453 | 1965 |  |  | Natural Gas |  | 05_01_219W6 | 03/14/2016 | 03/14/2016 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2016 | 06/23/2016 | 56 | 38 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 | 03/14/2016 | 6/30/2019 | Y | STD | 832 | 10/11/2017 | 04/04/2018 | 103 | 0 | 103 | 6/8/2018 | 10/20/2018 | 8/8/2018 | Connected |  | N
National Grid | WORCESTER | 662500 | 01602 | 9.75 |  |  | Solar |  | 05_01_2J335 | 12/24/2024 | 01/22/2025 | 13 | 11 | 2 | 01/23/2025 | 01/23/2025 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 176691 | 01550 | 936 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 691407 | 01473 | 11.4 |  |  | Solar |  | 05_01_609W2 | 06/03/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 78 | 55 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | SOMERSET | 348299 | 02725 | 433.3 |  |  | Solar |  | 05_05_11W84 | 06/09/2021 | 08/11/2021 | 44 | 35 | 9 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 380798 | 01905 | 5 |  |  | Solar |  | 05_12_29W1 | 09/10/2021 | 09/24/2021 | 1 | 0 | 1 | 09/27/2021 | 09/27/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/10/2021 | 2/27/2023 | Y | EXP | 365 | 01/13/2022 | 02/24/2022 | 43 | 0 | 43 |  |  | 3/3/2022 | Connected |  | N
National Grid | SAUGUS | 178676 | 01906 | 7.6 |  |  | Solar |  | 05_12_7J903 | 04/10/2018 | 04/10/2018 | 0 | 0 | 0 | 04/30/2018 | 04/30/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 1/8/2020 | N | EXP | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 595579 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 03/13/2024 | 4/17/2025 | Y | EXP | 365 | 04/16/2024 | 09/03/2024 | 141 | 0 | 141 |  |  | 9/26/2024 | Connected |  | N
National Grid | NEWBURY | 603110 | 01922 | 46 |  |  | Solar |  | 05_14_60L1 | 04/10/2024 | 05/29/2024 | 27 | 25 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | HAVERHILL | 650791 | 01832 | 10 |  |  | Solar |  | 05_14_74L5 | 10/31/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 196233 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W6 | 09/18/2018 | 08/09/2019 | 147 | 145 | 2 | 08/12/2019 | 08/12/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | WORCESTER | 667803 | 01602 | 3.8 |  |  | Solar |  | 05_01_2J335 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 115 | 97 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 176732 | 01550 | 936 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 04/20/2016 | 12/31/2020 | Y | STD | 384 | 08/22/2020 | 11/25/2020 | 95 | 0 | 95 | 12/3/2020 | 12/10/2020 | 12/31/2020 | Connected |  | N
National Grid | WESTMINSTER | 697495 | 01473 | 11.4 |  |  | Solar |  | 05_01_609W2 | 06/10/2025 | 06/24/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/10/2025 | 8/11/2026 | Y | EXP | 365 | 10/22/2025 |  | 72 | 0 | 72 |  |  | 11/26/2025 | Connected |  | N
National Grid | SOMERSET | 383131 | 02725 | 0 |  |  | Other |  | 05_05_11W84 | 11/29/2021 | 03/24/2022 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/25/2022 | 03/27/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 379716 | 01905 | 9.8 |  |  | Solar |  | 05_12_29W1 | 09/23/2021 | 12/16/2021 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 194313 | 01906 | 7.6 |  |  | Solar |  | 05_12_7J903 | 09/19/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 09/19/2018 | 10/12/2020 | Y | EXP | 450 | 05/02/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 2/7/2020 | Connected |  | N
National Grid | LAWRENCE | 595995 | 01841 | 7.6 |  |  | Solar |  | 05_14_43L4 | 04/05/2024 | 04/15/2024 | 6 | 2 | 4 | 04/16/2024 | 04/16/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/05/2024 | 4/25/2025 | Y | EXP | 365 | 06/05/2024 | 06/21/2024 | 17 | 0 | 17 |  |  | 7/18/2024 | Connected |  | N
National Grid | NEWBURY | 613820 | 01950 | 5.22 |  |  | Solar |  | 05_14_60L1 | 05/28/2024 | 06/04/2024 | 1 | 0 | 1 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 650671 | 01844 | 10 |  |  | Solar |  | 05_14_74L5 | 11/04/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 193270 | 01453 | 3.8 |  |  | Solar |  | 05_01_219W6 | 08/11/2018 | 09/24/2018 | 3 | 3 | 0 | 09/25/2018 | 09/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 671129 | 01602 | 5.76 |  |  | Solar |  | 05_01_2J335 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 106 | 90 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 176731 | 01550 | 999 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/02/2016 | 26 | 15 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 | 04/20/2016 | 12/31/2020 | Y | STD | 889 | 08/22/2020 | 12/03/2020 | 103 | 0 | 103 | 12/14/2020 | 12/16/2020 | 12/30/2020 | Connected |  | N
National Grid | WESTMINSTER | 487743 | 01473 | 0 |  |  | Other |  | 05_01_610W3 | 04/26/2023 | 05/08/2023 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2023 | 05/31/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SWANSEA | 394593 | 02777 | 78.8 |  |  | Solar |  | 05_05_11W84 | 11/15/2021 | 11/30/2021 | 10 | 2 | 8 | 12/01/2021 | 12/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 | 11/15/2021 | 4/10/2023 | Y | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 2/16/2023 | Connected |  | N
National Grid | LYNN | 407981 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 02/15/2022 | 02/16/2022 | 1 | 0 | 1 | 02/17/2022 | 02/17/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/15/2022 | 11/2/2023 | Y | EXP | 365 | 06/03/2022 | 06/10/2022 | 8 | 0 | 8 |  |  | 11/9/2022 | Connected |  | N
National Grid | SAUGUS | 199443 | 01906 | 3.8 |  |  | Solar |  | 05_12_7J903 | 11/02/2018 | 11/29/2018 | 7 | 0 | 7 | 11/30/2018 | 11/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 1/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | METHUEN | 597509 | 01844 | 13.325 |  |  | Solar |  | 05_14_43L4 | 04/03/2024 | 04/17/2024 | 9 | 6 | 3 | 04/18/2024 | 04/18/2024 | 37 | 32 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 624569 | 01950 | 10 |  |  | Solar |  | 05_14_60L1 | 07/26/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/25/2025 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | HAVERHILL | 651903 | 01832 | 5.76 |  |  | Solar |  | 05_14_74L5 | 11/25/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 199248 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W6 | 11/08/2018 | 12/03/2018 | 13 | 10 | 3 | 12/04/2018 | 12/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 682678 | 01602 | 11.4 |  |  | Solar |  | 05_01_2J335 | 04/03/2025 | 04/23/2025 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 176767 | 01550 | 936 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 | 04/20/2016 | 12/18/2020 | Y | STD | 461 | 07/08/2020 | 10/14/2020 | 99 | 5 | 94 |  |  | 12/16/2020 | Connected |  | N
National Grid | WESTMINSTER | 487745 | 01473 | 2000 |  |  | Solar |  | 05_01_610W3 | 01/27/2023 | 02/22/2023 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2023 | 03/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 433811 | 02726 | 10 |  |  | Solar |  | 05_05_11W84 | 05/27/2022 | 07/21/2022 | 0 | 0 | 0 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 | 05/27/2022 | 1/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | LYNN | 420646 | 01904 | 10 |  |  | Solar |  | 05_12_29W1 | 03/31/2022 | 04/25/2022 | 16 | 13 | 3 | 04/26/2022 | 04/26/2022 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | SAUGUS | 214350 | 01906 | 3.8 |  |  | Solar |  | 05_12_7J903 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 597079 | 01841 | 2.32 |  |  | Solar |  | 05_14_43L4 | 03/22/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | NEWBURY | 627652 | 01951 | 5.76 |  |  | Solar |  | 05_14_60L1 | 07/25/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 9/4/2025 | Y | EXP | 365 | 10/11/2024 | 10/11/2024 | 1 | 0 | 1 |  |  | 11/4/2024 | Connected |  | N
National Grid | METHUEN | 657128 | 01844 | 7.6 |  |  | Solar |  | 05_14_74L5 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 230771 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W6 | 06/18/2019 | 06/24/2019 | 3 | 0 | 3 | 06/25/2019 | 06/25/2019 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 323572 | 01602 | 7.92 |  |  | Solar |  | 05_01_2J345 | 11/03/2020 | 12/07/2020 | 21 | 19 | 2 | 12/08/2020 | 12/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 12/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 176766 | 01550 | 1872 |  |  | Solar |  | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 739544 | 01473 | 15.2 |  |  | Solar |  | 05_01_610W3 | 12/11/2025 | 12/16/2025 | 3 | 0 | 3 | 12/17/2025 | 12/17/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 433519 | 02777 | 10 |  |  | Solar |  | 05_05_11W84 | 07/14/2022 | 07/21/2022 | 5 | 0 | 5 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2023 | Connected |  | N
National Grid | LYNN | 542019 | 01905 | 3.8 |  |  | Solar |  | 05_12_29W1 | 07/26/2023 | 07/27/2023 | 1 | 0 | 1 | 07/28/2023 | 07/28/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/26/2023 | 8/24/2024 | Y | EXP | 365 | 10/20/2023 | 11/03/2023 | 15 | 0 | 15 |  |  | 11/15/2023 | Connected |  | N
National Grid | SAUGUS | 501622 | 01906 | 7.6 |  |  | Solar |  | 05_12_7J903 | 05/01/2023 | 05/04/2023 | 3 | 1 | 2 | 05/05/2023 | 05/05/2023 | 23 | 0 | 23 | 06/14/2023 | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/27/2024 | N | EXP | 365 | 12/07/2023 | 12/06/2023 | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N
National Grid | LAWRENCE | 602477 | 01841 | 11.4 |  |  | Solar |  | 05_14_43L4 | 04/17/2024 | 06/25/2024 | 47 | 47 | 0 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 04/17/2024 | 8/12/2025 | Y | EXP | 365 | 10/03/2024 | 11/26/2024 | 55 | 0 | 55 |  |  | 12/18/2024 | Connected |  | N
National Grid | NEWBURY | 629796 | 01951 | 3.8 |  |  | Solar |  | 05_14_60L1 | 08/19/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 08/19/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | Y
National Grid | METHUEN | 665424 | 01844 | 3.8 |  |  | Solar |  | 05_14_74L5 | 01/13/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 606789 | 01453 | 10 |  |  | Solar |  | 05_01_219W6 | 04/26/2024 | 05/16/2024 | 10 | 9 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 04/26/2024 | 7/23/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 657160 | 01602 | 5.76 |  |  | Solar |  | 05_01_2J345 | 11/26/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 177502 | 01550 | 2000 |  |  |  |  | 05_01_413L4 | 03/06/2017 | 03/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 743645 | 01473 | 11.4 |  |  | Solar |  | 05_01_610W3 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 471482 | 02777 | 7.6 |  |  | Solar |  | 05_05_11W84 | 11/18/2022 | 11/28/2022 | 6 | 4 | 2 | 11/29/2022 | 11/29/2022 | 393 | 51 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 552539 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 09/20/2023 | 09/22/2023 | 3 | 2 | 1 | 09/25/2023 | 09/25/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N
National Grid | SAUGUS | 519264 | 01906 | 3.8 |  |  | Solar |  | 05_12_7J903 | 05/03/2023 | 05/08/2023 | 3 | 0 | 3 | 05/09/2023 | 05/09/2023 | 21 | 0 | 21 | 06/14/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/22/2024 | N | EXP | 365 | 01/03/2024 | 01/09/2024 | 7 | 0 | 7 |  |  | 1/13/2024 | Connected |  | N
National Grid | METHUEN | 610901 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 05/31/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 642862 | 01951 | 7.6 |  |  | Solar |  | 05_14_60L1 | 09/26/2024 | 09/30/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 672317 | 01832 | 10 |  |  | Solar |  | 05_14_74L5 | 02/16/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 608585 | 01453 | 23 |  |  | Solar |  | 05_01_219W6 | 05/06/2024 | 05/14/2024 | 7 | 4 | 3 | 05/15/2024 | 05/15/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/06/2024 | 6/20/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | WORCESTER | 677870 | 01602 | 3.839 |  |  | Solar |  | 05_01_2J349 | 03/13/2025 | 04/07/2025 | 11 | 7 | 4 | 04/07/2025 | 04/07/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOUTHBRIDGE | 178044 | 01550 | 4900 |  |  | Solar |  | 05_01_413L4 | 05/04/2017 | 05/04/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2017 | 06/02/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 174375 | 01473 | 600 |  |  | Solar |  | 05_01_610W3 | 05/29/2012 | 05/29/2012 | 11 | 0 | 11 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 12/31/2016 | Y | EXP | 1388 | 10/01/2015 | 10/09/2015 | 6 | 0 | 6 | 6/3/2012 | 6/3/2012 | 12/24/2015 | Connected |  | N
National Grid | SWANSEA | 485618 | 02777 | 10 |  |  | Solar |  | 05_05_11W84 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 01/10/2023 | 4/22/2024 | Y | EXP | 365 | 07/04/2023 | 07/12/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 554746 | 01904 | 10 |  |  | Solar |  | 05_12_29W1 | 09/25/2023 | 09/29/2023 | 4 | 0 | 4 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/25/2023 | 12/10/2024 | Y | EXP | 365 | 02/09/2024 | 05/01/2024 | 83 | 0 | 83 |  |  | 8/4/2024 | Connected |  | N
National Grid | SAUGUS | 562325 | 01906 | 3.8 |  |  | Solar |  | 05_12_7J903 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | METHUEN | 629865 | 01844 | 6 |  |  | Solar |  | 05_14_43L4 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 01/09/2025 | 01/08/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 645437 | 01951 | 23 |  |  | Solar |  | 05_14_60L1 | 10/07/2024 | 10/16/2024 | 5 | 3 | 2 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | HAVERHILL | 679744 | 01832 | 13.8 |  |  | Solar |  | 05_14_74L5 | 03/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2025 | 03/21/2025 | 5/30/2026 | Y | EXP | 365 | 06/13/2025 | 08/22/2025 | 71 | 0 | 71 |  |  | 9/12/2025 | Connected |  | N
National Grid | LEOMINSTER | 636595 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W6 | 08/29/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | WORCESTER | 534979 | 01603 | 14.21 |  |  | Solar |  | 05_01_2J349 | 06/19/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2023 |  | 8/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | CHARLTON | 198216 | 01507 | 3000 |  |  | Solar |  | 05_01_413L4 | 08/13/2020 | 10/15/2020 | 42 | 40 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 11/10/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/13/2020 | 2/16/2025 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175446 | 01473 | 450 |  |  | Solar |  | 05_01_610W3 | 03/10/2014 | 03/10/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2014 | 04/09/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 03/10/2014 | 6/9/2016 | Y | STD | 546 | 06/20/2016 | 09/08/2016 | 56 | 0 | 56 |  |  | 9/27/2016 | Connected |  | N
National Grid | SOMERSET | 494490 | 02725 | 10 |  |  | Solar |  | 05_05_11W84 | 01/26/2023 | 01/30/2023 | 2 | 0 | 2 | 01/31/2023 | 01/31/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/26/2023 | 9/14/2024 | Y | EXP | 365 | 06/24/2023 | 09/14/2023 | 83 | 0 | 83 |  |  | 9/20/2023 | Connected |  | N
National Grid | LYNN | 566137 | 01905 | 6 |  |  | Solar |  | 05_12_29W1 | 11/06/2023 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 587947 | 01906 | 3.8 |  |  | Solar |  | 05_12_7J903 | 02/10/2024 | 02/12/2024 | 1 | 0 | 1 | 02/13/2024 | 02/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 2/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | METHUEN | 631324 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 08/08/2024 | 08/21/2024 | 5 | 0 | 5 | 08/22/2024 | 08/22/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 10/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | NEWBURY | 651238 | 01951 | 17.6 |  |  | Solar |  | 05_14_60L1 | 11/04/2024 | 01/15/2025 | 40 | 36 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/4/2026 | Y | EXP | 365 | 08/26/2025 | 09/03/2025 | 9 | 0 | 9 |  |  | 9/23/2025 | Connected |  | N
National Grid | HAVERHILL | 706445 | 01832 | 7.6 |  |  | Solar |  | 05_14_74L5 | 07/22/2025 | 08/28/2025 | 1 | 0 | 1 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | LEOMINSTER | 656186 | 01453 | 7.6 |  |  | Solar |  | 05_01_219W6 | 11/21/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | WORCESTER | 661625 | 01603 | 3.8 |  |  | Solar |  | 05_01_2J349 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 265989 | 01550 | 0 |  |  | Other |  | 05_01_413L4 | 02/27/2020 | 03/17/2020 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/27/2020 |  | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175731 | 01473 | 499 |  |  | Solar |  | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | SWANSEA | 515758 | 02777 | 15.2 |  |  | Solar |  | 05_05_11W84 | 07/17/2023 | 04/07/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 100 | 78 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 1/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2024 | Connected |  | N
National Grid | LYNN | 563069 | 01904 | 2.9 |  |  | Solar |  | 05_12_29W1 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 77 | 61 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | SAUGUS | 174990 | 01906 | 75 |  |  | Diesel |  | 05_12_7W1 | 03/06/2013 | 03/06/2013 | 5 | 0 | 5 | 03/18/2013 | 03/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2013 |  | 6/28/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/17/2013 | Connected |  | Y
National Grid | METHUEN | 633402 | 01844 | 5 |  |  | Solar |  | 05_14_43L4 | 08/19/2024 | 10/04/2024 | 31 | 25 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 652089 | 01951 | 2.9 |  |  | Solar |  | 05_14_60L1 | 11/06/2024 | 01/22/2025 | 5 | 3 | 2 | 01/23/2025 | 01/23/2025 | 70 | 25 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 712554 | 01844 | 17.6 |  |  | Solar |  | 05_14_74L5 | 08/25/2025 | 08/26/2025 | 1 | 0 | 1 | 08/27/2025 | 08/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 677866 | 01453 | 13.8 |  |  | Solar |  | 05_01_219W6 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 123 | 103 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 698530 | 01603 | 11.4 |  |  | Solar |  | 05_01_2J353 | 06/27/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | CHARLTON | 281257 | 01507 | 0 |  |  | Other |  | 05_01_413L4 | 03/17/2020 | 04/24/2020 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/17/2020 | 3/5/2025 | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175730 | 01473 | 1000 |  |  | Solar |  | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | SWANSEA | 532784 | 02777 | 0 |  |  | Other |  | 05_05_11W84 | 08/15/2023 | 10/05/2023 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2023 | 12/06/2023 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 572647 | 01905 | 5.8 |  |  | Solar |  | 05_12_29W1 | 11/27/2023 | 11/30/2023 | 3 | 2 | 1 | 12/01/2023 | 12/01/2023 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | REVERE | 177794 | 02151 | 7.6 |  |  | Solar |  | 05_12_7W1 | 08/02/2017 | 08/02/2017 | 4 | 0 | 4 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/8/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  | 8/1/2018 | Connected |  | N
National Grid | LAWRENCE | 636570 | 01841 | 5.76 |  |  | Solar |  | 05_14_43L4 | 08/29/2024 | 09/23/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 08/29/2024 | 10/30/2025 | Y | EXP | 365 | 12/19/2024 | 03/03/2025 | 75 | 0 | 75 |  |  | 3/12/2025 | Connected |  | N
National Grid | NEWBURY | 655001 | 01951 | 5.2 |  |  | Solar |  | 05_14_60L1 | 11/19/2024 | 12/09/2024 | 6 | 3 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | METHUEN | 590405 | 01844 | 25 |  |  | Solar |  | 05_14_74L6 | 02/15/2024 | 06/24/2024 | 87 | 86 | 1 | 06/25/2024 | 06/25/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/1/2026 | N | EXP | 700 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 371682 | 01453 | 1000 |  |  | Solar |  | 05_01_21W1 | 10/15/2021 | 01/03/2022 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/04/2022 | 08/02/2023 | 394 | 379 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 619089 | 01602 | 5.76 |  |  | Solar |  | 05_01_2J353 | 06/19/2024 | 06/26/2024 | 0 | 0 | 0 | 06/27/2024 | 06/27/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 280097 | 01507 | 8.64 |  |  | Solar |  | 05_01_413L4 | 02/19/2020 | 02/25/2020 | 3 | 0 | 3 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2020 | 02/19/2020 | 2/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | WESTMINSTER | 175830 | 01473 | 6 |  |  | Solar |  | 05_01_610W3 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/27/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 5/12/2016 | Connected |  | N
National Grid | SWANSEA | 549535 | 02777 | 0 |  |  | Solar |  | 05_05_11W84 | 08/23/2023 | 08/30/2023 | 6 | 4 | 2 | 08/31/2023 | 08/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 572266 | 01905 | 7.6 |  |  | Solar |  | 05_12_29W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/07/2023 | 1/31/2025 | Y | EXP | 365 | 04/17/2024 | 06/17/2024 | 62 | 0 | 62 |  |  | 7/4/2024 | Connected |  | N
National Grid | REVERE | 394618 | 02151 | 28.8 |  |  | Solar |  | 05_12_7W1 | 01/13/2022 | 01/26/2022 | 9 | 7 | 2 | 01/27/2022 | 01/27/2022 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  | 3/18/2024 | N | EXP | 700 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | METHUEN | 637943 | 01844 | 6.98 |  |  | Solar |  | 05_14_43L4 | 09/05/2024 | 10/16/2024 | 4 | 0 | 4 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/05/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | NEWBURY | 655842 | 01951 | 3.8 |  |  | Solar |  | 05_14_60L1 | 11/20/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/20/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | LAWRENCE | 605450 | 01840 | 11.4 |  |  | Solar |  | 05_14_74L6 | 04/24/2024 | 07/19/2024 | 39 | 39 | 0 | 07/22/2024 | 07/22/2024 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 04/24/2024 | 12/31/2025 | Y | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SPENCER | 418278 | 01562 | 2000 |  |  | Solar |  | 05_01_21W1 | 02/17/2023 | 07/13/2023 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2023 | 08/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 661853 | 01602 | 5.76 |  |  | Solar |  | 05_01_2J353 | 12/19/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | Y
National Grid | CHARLTON | 282050 | 01507 | 4950 |  |  | Other |  | 05_01_413L4 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175891 | 01473 | 5 |  |  | Solar |  | 05_01_610W3 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 379 | 0 | 379 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2015 |  | 8/10/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 565023 | 02725 | 5 |  |  | Solar |  | 05_05_11W84 | 10/25/2023 | 10/30/2023 | 4 | 2 | 2 | 10/31/2023 | 10/31/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 583921 | 01905 | 5.22 |  |  | Solar |  | 05_12_29W1 | 02/12/2024 | 02/20/2024 | 5 | 2 | 3 | 02/21/2024 | 02/21/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | REVERE | 616872 | 02151 | 7.6 |  |  | Solar |  | 05_12_7W1 | 06/11/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | LAWRENCE | 643784 | 01841 | 13.12 |  |  | Solar |  | 05_14_43L4 | 09/30/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 659314 | 01951 | 7.6 |  |  | Solar |  | 05_14_60L1 | 12/09/2024 | 01/03/2025 | 16 | 11 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | METHUEN | 719923 | 01844 | 5.76 |  |  | Solar |  | 05_14_74L6 | 09/22/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SPENCER | 707464 | 01562 | 12.672 |  |  | Solar |  | 05_01_21W1 | 07/30/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 | 07/30/2025 | 10/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 692871 | 01602 | 9.28 |  |  | Solar |  | 05_01_2J353 | 05/20/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | CHARLTON | 416620 | 01507 | 10 |  |  | Solar |  | 05_01_413L4 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 | 03/14/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | WESTMINSTER | 175905 | 01473 | 5.94 |  |  | Solar |  | 05_01_610W3 | 10/01/2015 | 10/01/2015 | 4 | 4 | 0 | 10/07/2015 | 10/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 | 10/01/2015 | 10/6/2016 | Y | EXP | 350 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 | 10/22/2015 | 10/22/2015 | 6/17/2016 | Connected |  | N
National Grid | SWANSEA | 575399 | 02777 | 6 |  |  | Solar |  | 05_05_11W84 | 12/12/2023 | 12/19/2023 | 5 | 2 | 3 | 12/20/2023 | 12/20/2023 | 26 | 6 | 20 | 02/13/2024 | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 2/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 587528 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 648905 | 02151 | 7.68 |  |  | Solar |  | 05_12_7W1 | 10/22/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LAWRENCE | 644259 | 01841 | 3.8 |  |  | Solar |  | 05_14_43L4 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 705439 | 01951 | 5.85 |  |  | Solar |  | 05_14_60L1 | 07/21/2025 | 08/06/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | METHUEN | 177324 | 01844 | 10 |  |  | Solar |  | 05_14_74L6 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 | 06/21/2016 | 06/21/2016 | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2016 |  | 6/26/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 174335 | 01562 | 2000 |  |  | Solar |  | 05_01_21W1 | 01/25/2012 | 01/25/2012 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2012 | 05/16/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 728739 | 01602 | 17.6 |  |  | Solar |  | 05_01_2J393 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBRIDGE | 560222 | 01550 | 7.749 |  |  | Solar |  | 05_01_413L4 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 11/01/2023 | 2/3/2025 | Y | EXP | 365 | 04/18/2024 | 05/29/2024 | 42 | 0 | 42 |  |  | 7/4/2024 | Connected |  | N
National Grid | WESTMINSTER | 176131 | 01473 | 19 |  |  | Solar |  | 05_01_610W3 | 04/14/2015 | 04/14/2015 | 1 | 1 | 0 | 04/16/2015 | 04/16/2015 | 445 | 0 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 8/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 626348 | 02777 | 9.92 |  |  | Solar |  | 05_05_11W84 | 07/19/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/18/2024 | 13 | 0 | 13 |  |  | 10/31/2024 | Connected |  | N
National Grid | LYNN | 588428 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 02/21/2024 | 04/17/2024 | 28 | 25 | 3 | 04/18/2024 | 04/18/2024 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | REVERE | 666990 | 02151 | 3.2 |  |  | Solar |  | 05_12_7W1 | 01/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/21/2025 | 5/16/2026 | Y | EXP | 365 | 08/08/2025 |  | 146 | 1 | 145 |  |  | 12/1/2025 | Connected |  | N
National Grid | METHUEN | 645461 | 01844 | 7.54 |  |  | Solar |  | 05_14_43L4 | 10/11/2024 | 10/21/2024 | 2 | 0 | 2 | 10/22/2024 | 10/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 11/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | NEWBURY | 694244 | 01950 | 22.8 |  |  | Solar |  | 05_14_60L2 | 05/27/2025 | 06/16/2025 | 13 | 11 | 2 | 06/17/2025 | 06/17/2025 | 19 | 0 | 19 | 07/24/2025 | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 177643 | 01844 | 10 |  |  | Solar |  | 05_14_74L6 | 07/20/2017 | 07/20/2017 | 5 | 0 | 5 | 07/28/2017 | 07/28/2017 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/26/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 174573 | 01562 | 1000 |  |  | Solar |  | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 648206 | 01610 | 5.76 |  |  | Solar |  | 05_01_2J393 | 10/30/2024 |  | 75 | 71 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 548793 | 01550 | 15 |  |  | Solar |  | 05_01_413L4 | 08/18/2023 | 08/21/2023 | 1 | 0 | 1 | 08/22/2023 | 08/22/2023 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 08/18/2023 | 10/22/2024 | Y | EXP | 365 | 12/08/2023 | 01/24/2024 | 48 | 3 | 45 |  |  | 2/3/2024 | Connected |  | N
National Grid | WESTMINSTER | 177663 | 01473 | 4980 |  |  | Solar |  | 05_01_610W3 | 11/13/2017 | 11/13/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2017 | 12/20/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  | 11/19/2018 | N | STD | 125 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 633817 | 02725 | 7.475 |  |  | Solar |  | 05_05_11W84 | 08/20/2024 | 08/23/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 08/20/2024 | 12/18/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 1/23/2025 | Connected |  | N
National Grid | LYNN | 590460 | 01904 | 5 |  |  | Solar |  | 05_12_29W1 | 03/01/2024 | 05/28/2024 | 16 | 16 | 0 | 05/29/2024 | 05/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | REVERE | 683414 | 02151 | 14.95 |  |  | Solar |  | 05_12_7W1 | 04/23/2025 | 05/23/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 649010 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 11/18/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | BYFIELD | 725530 | 01922 | 23 |  |  | Solar |  | 05_14_60L2 | 10/09/2025 | 10/17/2025 | 5 | 3 | 2 | 10/20/2025 | 10/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 178226 | 01844 | 11.4 |  |  | Solar |  | 05_14_74L6 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 01/03/2018 | 1/10/2019 | Y | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 12/12/2019 | Connected |  | N
National Grid | SPENCER | 174572 | 01562 | 1000 |  |  | Solar |  | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 649074 | 01602 | 5.584 |  |  | Solar |  | 05_01_2J393 | 10/23/2024 | 01/01/2025 | 31 | 26 | 5 | 01/02/2025 | 01/02/2025 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 555308 | 01550 | 5 |  |  | Solar |  | 05_01_413L4 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | WESTMINSTER | 178300 | 01473 | 4875 |  |  | Solar |  | 05_01_610W3 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/17/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2018 | 11/16/2017 | 3/31/2023 | Y | STD | 725 | 08/12/2022 | 01/03/2023 | 145 | 0 | 145 | 3/9/2023 | 3/23/2023 | 3/31/2023 | Connected |  | N
National Grid | SWANSEA | 644735 | 02777 | 3.8 |  |  | Solar |  | 05_05_11W84 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | LYNN | 596319 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 03/20/2024 | 03/25/2024 | 3 | 0 | 3 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 03/20/2024 | 5/29/2025 | Y | EXP | 365 | 10/17/2024 | 02/12/2025 | 68 | 0 | 68 |  |  | 12/31/2024 | Connected |  | Y
National Grid | REVERE | 176039 | 02151 | 2.58 |  |  | Solar |  | 05_12_7W2 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/19/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/12/2016 | 5/12/2016 | 6/27/2016 | Connected |  | N
National Grid | LAWRENCE | 649801 | 01841 | 5.2 |  |  | Solar |  | 05_14_43L4 | 10/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | BYFIELD | 176109 | 01922 | 47.1 |  |  | Solar |  | 05_14_60L2 | 06/26/2015 | 06/26/2015 | 2 | 2 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 |  | 7/1/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/22/2015 | 7/22/2015 | 11/3/2015 | Connected |  | N
National Grid | LAWRENCE | 178524 | 01841 | 10 |  |  | Solar |  | 05_14_74L6 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/18/2018 | 05/18/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2018 |  | 4/10/2019 | N | EXP | 316 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 174571 | 01562 | 2000 |  |  | Solar |  | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/20/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2012 | 10/11/2011 | 10/31/2012 | Y | STD | 38 | 04/09/2013 | 06/21/2013 | 50 | 0 | 50 | 6/21/2013 | 6/21/2013 | 8/7/2013 | Connected |  | N
National Grid | WORCESTER | 649633 | 01602 | 4.93 |  |  | Solar |  | 05_01_2J393 | 10/25/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 18 | 0 | 18 | 12/17/2024 | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 |  | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 591210 | 01550 | 6 |  |  | Solar |  | 05_01_413L4 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | WESTMINSTER | 178378 | 01473 | 5000 |  |  | Solar |  | 05_01_610W3 | 11/22/2017 | 11/22/2017 | 44 | 35 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 02/25/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 645472 | 02725 | 2.03 |  |  | Solar |  | 05_05_11W84 | 10/31/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 25 | 0 | 25 | 01/17/2025 | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 600626 | 01905 | 3.8 |  |  | Solar |  | 05_12_29W1 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176339 | 02151 | 3.8 |  |  | Solar |  | 05_12_7W2 | 09/17/2015 | 09/17/2015 | 5 | 5 | 0 | 09/24/2015 | 09/24/2015 | 330 | 0 | 330 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 |  | 9/22/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 651165 | 01844 | 6.825 |  |  | Solar |  | 05_14_43L4 | 10/31/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/31/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NEWBURY | 177160 | 01951 | 32 |  |  | Solar |  | 05_14_60L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 |  | 11/2/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/21/2017 | 3/21/2017 | 3/21/2017 | Connected |  | N
National Grid | LAWRENCE | 178591 | 01841 | 3.8 |  |  | Solar |  | 05_14_74L6 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 3/20/2019 | N | EXP | 302 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 174617 | 01562 | 22.8 |  |  | Solar |  | 05_01_21W1 | 12/14/2010 | 12/14/2010 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2011 |  | 2/8/2012 | N | EXP | 309 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/8/2012 | Connected |  | N
National Grid | WORCESTER | 654942 | 01610 | 5.76 |  |  | Solar |  | 05_01_2J393 | 11/18/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 592756 | 01550 | 7.6 |  |  | Solar |  | 05_01_413L4 | 02/28/2024 | 05/22/2024 | 53 | 50 | 3 | 05/23/2024 | 05/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 02/28/2024 | 12/31/2025 | Y | EXP | 365 | 09/30/2025 | 09/29/2025 | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | WESTMINSTER | 192451 | 01473 | 3780 |  |  | Solar |  | 05_01_610W3 | 09/18/2018 | 10/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2018 | 11/17/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 647182 | 02725 | 10 |  |  | Solar |  | 05_05_11W84 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | LYNN | 605243 | 01905 | 6.96 |  |  | Solar |  | 05_12_29W1 | 04/19/2024 | 06/11/2024 | 22 | 20 | 2 | 06/12/2024 | 06/12/2024 | 155 | 25 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176788 | 02151 | 11.4 |  |  | Solar |  | 05_12_7W2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 01/14/2016 | 10/31/2017 | Y | EXP | 616 | 09/18/2017 | 11/14/2017 | 34 | 0 | 34 | 4/28/2017 | 4/28/2017 | 11/16/2017 | Connected |  | N
National Grid | METHUEN | 652499 | 01844 | 9.5 |  |  | Solar |  | 05_14_43L4 | 11/06/2024 | 11/26/2024 | 4 | 1 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 270193 | 01922 | 10 |  |  | Solar |  | 05_14_60L2 | 01/06/2020 | 01/07/2020 | 0 | 0 | 0 | 01/08/2020 | 01/08/2020 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 1/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 7/9/2020 | Connected |  | N
National Grid | LAWRENCE | 215537 | 01841 | 10 |  |  | Solar |  | 05_14_74L6 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 | 04/02/2019 | 2/5/2020 | Y | EXP | 296 | 11/06/2019 | 11/22/2019 | 16 | 0 | 16 |  |  | 11/26/2019 | Connected |  | N
National Grid | LEICESTER | 175220 | 01524 | 17.5 |  |  | Solar |  | 05_01_21W1 | 11/03/2014 | 11/03/2014 | 6 | 1 | 5 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 1/30/2015 | N | EXP | 77 |  |  | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 3/8/2016 | Connected |  | N
National Grid | WORCESTER | 655707 | 01602 | 3.8 |  |  | Solar |  | 05_01_2J393 | 11/20/2024 | 12/06/2024 | 6 | 1 | 5 | 12/09/2024 | 12/09/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 633183 | 01550 | 10 |  |  | Solar |  | 05_01_413L4 | 08/15/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 200898 | 01473 | 4998 |  |  | Solar |  | 05_01_610W3 | 11/12/2018 | 11/30/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/25/2019 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 652291 | 02725 | 15 |  |  | Solar |  | 05_05_11W84 | 11/05/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/05/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LYNN | 607470 | 01905 | 7.6 |  |  | Solar |  | 05_12_29W1 | 04/30/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 04/30/2024 | 12/31/2025 | Y | EXP | 365 | 02/19/2025 | 10/03/2025 | 227 | 0 | 227 |  |  | 10/29/2025 | Connected |  | N
National Grid | REVERE | 177141 | 02151 | 10 |  |  | Solar |  | 05_12_7W2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 162 | 0 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 657188 | 01844 | 15.2 |  |  | Solar |  | 05_14_43L4 | 11/26/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | BYFIELD | 291579 | 01922 | 10 |  |  | Solar |  | 05_14_60L2 | 06/15/2020 | 06/18/2020 | 3 | 2 | 1 | 06/19/2020 | 06/19/2020 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 6/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | LAWRENCE | 261851 | 01841 | 7.6 |  |  | Solar |  | 05_14_74L6 | 11/05/2019 | 01/08/2020 | 40 | 33 | 7 | 01/09/2020 | 01/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/05/2019 | 1/15/2021 | Y | EXP | 365 | 07/07/2020 | 07/10/2020 | 3 | 0 | 3 |  |  | 1/11/2021 | Connected |  | N
National Grid | SPENCER | 175263 | 01562 | 1000 |  |  | Solar |  | 05_01_21W1 | 01/13/2015 | 01/13/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 02/20/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174551 | 01602 | 1500 |  |  | Solar |  | 05_01_304W2 | 11/16/2011 | 11/16/2011 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2012 | 02/27/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2012 | 11/16/2011 | 10/31/2012 | Y | STD | 62 | 08/08/2013 | 10/18/2013 | 49 | 0 | 49 | 9/24/2013 | 9/24/2013 | 10/11/2013 | Connected |  | N
National Grid | CHARLTON | 644414 | 01507 | 5.76 |  |  | Solar |  | 05_01_413L4 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/02/2024 | 2/3/2026 | Y | EXP | 365 | 01/04/2025 | 02/11/2025 | 39 | 0 | 39 |  |  | 4/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 370345 | 01473 | 11.4 |  |  | Solar |  | 05_01_610W3 | 07/16/2021 | 08/19/2021 | 24 | 23 | 1 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 07/16/2021 | 7/15/2023 | Y | EXP | 365 | 02/17/2022 | 02/28/2022 | 12 | 0 | 12 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 655751 | 02777 | 11.5 |  |  | Solar |  | 05_05_11W84 | 11/20/2024 | 11/21/2024 | 1 | 0 | 1 | 11/22/2024 | 11/22/2024 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | LYNN | 613294 | 01904 | 3.8 |  |  | Solar |  | 05_12_29W1 | 05/31/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 177738 | 02151 | 6 |  |  | Solar |  | 05_12_7W2 | 03/24/2017 | 03/24/2017 | 4 | 4 | 0 | 03/31/2017 | 03/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/24/2017 | 8/10/2018 | Y | EXP | 493 | 10/24/2017 | 11/29/2017 | 19 | 0 | 19 |  |  | 8/29/2018 | Connected |  | N
National Grid | METHUEN | 660661 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 12/14/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | BYFIELD | 347069 | 01922 | 8.7 |  |  | Solar |  | 05_14_60L2 | 04/19/2021 | 04/22/2021 | 2 | 0 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 7/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | LAWRENCE | 289216 | 01841 | 7.6 |  |  | Solar |  | 05_14_74L6 | 05/21/2020 | 05/27/2020 | 2 | 0 | 2 | 05/28/2020 | 05/28/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/21/2020 | 9/17/2021 | Y | EXP | 365 | 01/20/2021 | 01/28/2021 | 8 | 0 | 8 |  |  | 7/16/2021 | Connected |  | N
National Grid | LEICESTER | 175903 | 01524 | 224 |  |  | Solar |  | 05_01_21W1 | 09/28/2015 | 09/28/2015 | 0 | 0 | 0 | 09/30/2015 | 09/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 09/28/2015 | 10/5/2016 | Y | EXP | 330 | 12/23/2015 | 12/28/2015 | 2 | 0 | 2 | 2/17/2016 | 2/17/2016 | 3/24/2016 | Connected |  | N
National Grid | GRAFTON | 175211 | 01519 | 12.255 |  |  | Solar |  | 05_01_304W2 | 12/04/2012 | 12/04/2012 | 11 | 8 | 3 | 12/21/2012 | 12/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 2/28/2013 | N | EXP | -8 |  |  | 0 | 0 | 0 | 3/8/2013 | 3/8/2013 | 4/22/2013 | Connected |  | N
National Grid | SOUTHBRIDGE | 669910 | 01550 | 7.8 |  |  | Solar |  | 05_01_413L4 | 02/04/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 74 | 57 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 382185 | 01473 | 15.2 |  |  | Solar |  | 05_01_610W3 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 11/3/2023 | Y | EXP | 365 | 09/02/2022 | 10/26/2022 | 55 | 0 | 55 |  |  | 12/13/2022 | Connected |  | N
National Grid | SWANSEA | 657190 | 02777 | 5.76 |  |  | Solar |  | 05_05_11W84 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/26/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | LYNN | 619178 | 01905 | 5 |  |  | Solar |  | 05_12_29W1 | 06/19/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 | 06/19/2024 | 7/30/2025 | Y | EXP | 365 | 09/06/2024 | 12/19/2024 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 178212 | 02151 | 3.8 |  |  | Solar |  | 05_12_7W2 | 03/23/2018 | 03/23/2018 | 9 | 0 | 9 | 05/14/2018 | 05/14/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 | 03/23/2018 | 7/31/2019 | Y | EXP | 408 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 661675 | 01844 | 10 |  |  | Solar |  | 05_14_43L4 | 12/20/2024 | 01/22/2025 | 5 | 1 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/20/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | BYFIELD | 378339 | 01922 | 11.4 |  |  | Solar |  | 05_14_60L2 | 08/26/2021 | 09/21/2021 | 17 | 16 | 1 | 09/22/2021 | 09/22/2021 | 62 | 39 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2022 | Connected |  | N
National Grid | LAWRENCE | 334597 | 01841 | 7.6 |  |  | Solar |  | 05_14_74L6 | 01/13/2021 | 02/05/2021 | 16 | 16 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/13/2021 | 9/2/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | SPENCER | 175943 | 01562 | 1000 |  |  | Solar |  | 05_01_21W1 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/26/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 | 01/21/2015 | 9/28/2018 | Y | STD | 1134 | 04/09/2018 | 08/27/2018 | 130 | 0 | 130 |  |  | 9/6/2018 | Connected |  | N
National Grid | SUTTON | 175576 | 01590 | 20 |  |  | Solar |  | 05_01_304W2 | 12/09/2014 | 12/09/2014 | 4 | 2 | 2 | 12/16/2014 | 12/16/2014 | 223 | 0 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 2/28/2015 | N | EXP | 74 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 682067 | 01550 | 10 |  |  | Solar |  | 05_01_413L4 | 04/01/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | WESTMINSTER | 423419 | 01473 | 2.33 |  |  | Solar |  | 05_01_610W3 | 02/13/2023 | 02/15/2023 | 2 | 0 | 2 | 02/16/2023 | 02/16/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 672553 | 02777 | 5.76 |  |  | Solar |  | 05_05_11W84 | 02/18/2025 | 04/09/2025 | 2 | 0 | 2 | 04/17/2025 | 04/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/18/2025 | 6/10/2026 | Y | EXP | 365 | 08/01/2025 | 07/31/2025 | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | LYNN | 628547 | 01904 | 7.6 |  |  | Solar |  | 05_12_29W1 | 09/17/2024 | 11/25/2024 | 26 | 25 | 1 | 11/26/2024 | 11/26/2024 | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 09/17/2024 | 4/10/2026 | Y | EXP | 365 | 07/24/2025 | 11/18/2025 | 118 | 0 | 118 |  |  | 12/1/2025 | Connected |  | N
National Grid | REVERE | 178452 | 02151 | 10 |  |  | Solar |  | 05_12_7W2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 11/29/2017 | 11/25/2019 | Y | EXP | 640 | 01/08/2019 | 04/19/2019 | 101 | 0 | 101 |  |  | 11/6/2019 | Connected |  | N
National Grid | METHUEN | 662855 | 01844 | 7.6 |  |  | Solar |  | 05_14_43L4 | 12/27/2024 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | NEWBURY | 443818 | 01922 | 50 |  |  | Solar |  | 05_14_60L2 | 07/15/2022 | 07/29/2022 | 10 | 0 | 10 | 08/01/2022 | 08/01/2022 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 |  | 2/23/2024 | N | EXP | 275 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | METHUEN | 501293 | 01844 | 6 |  |  | Solar |  | 05_14_74L6 | 04/13/2023 |  | 202 | 198 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 176203 | 01524 | 3.8 |  |  | Solar |  | 05_01_21W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 06/17/2016 | 06/15/2016 | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 5/26/2016 | Connected |  | N
National Grid | SUTTON | 175728 | 01590 | 1000 |  |  | Solar |  | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 693150 | 01550 | 7.6 |  |  | Solar |  | 05_01_413L4 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 05/21/2025 | 8/11/2026 | Y | EXP | 365 | 11/22/2025 |  | 41 | 0 | 41 |  |  | 12/4/2025 | Connected |  | N
National Grid | WESTMINSTER | 468590 | 01473 | 16.24 |  |  | Solar |  | 05_01_610W3 | 11/26/2022 | 12/01/2022 | 4 | 2 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2023 | Connected |  | N
National Grid | SWANSEA | 719327 | 02777 | 15.2 |  |  | Solar |  | 05_05_11W84 | 09/16/2025 | 10/06/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 09/16/2025 | 11/26/2026 | Y | EXP | 365 | 11/26/2025 |  | 36 | 12 | 24 |  |  | 12/31/2025 | Connected |  | N
National Grid | LYNN | 184518 | 01905 | 10 |  |  | Solar |  | 05_12_7W2 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 6/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2018 | Connected |  | N
National Grid | REVERE | 669208 | 02151 | 3.8 |  |  | Solar |  | 05_14_43L4 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/03/2025 | 4/12/2026 | Y | EXP | 365 | 05/15/2025 | 11/03/2025 | 172 | 3 | 169 |  |  | 7/29/2025 | Connected |  | N
National Grid | METHUEN | 488659 | 01844 | 10.752 |  |  | Solar |  | 05_14_60L2 | 02/08/2023 | 02/09/2023 | 2 | 1 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | BYFIELD | 516167 | 01922 | 6 |  |  | Solar |  | 05_14_74L6 | 06/20/2023 | 06/22/2023 | 3 | 1 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 9/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176216 | 01841 | 1000 |  |  | Solar |  | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SPENCER | 175727 | 01562 | 1000 |  |  | Solar |  | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 339091 | 01519 | 4999 |  |  | Solar |  | 05_01_413L6 | 04/07/2021 | 04/28/2021 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2021 | 05/28/2021 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SOUTHBRIDGE | 477503 | 01550 | 7.6 |  |  | Solar |  | 05_01_610W3 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | WESTMINSTER | 724378 | 01472 | 23 |  |  | Solar |  | 05_05_11W84 | 10/06/2025 | 10/21/2025 | 9 | 6 | 3 | 10/22/2025 | 10/22/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | SWANSEA | 632467 | 02777 | 3.8 |  |  | Solar |  | 05_12_29W1 | 08/15/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/15/2024 | 9/10/2025 | Y | EXP | 365 | 10/30/2024 | 04/14/2025 | 167 | 0 | 167 |  |  | 5/6/2025 | Connected |  | N
National Grid | LYNN | 195384 | 01905 | 499.9 |  |  | Solar |  | 05_12_7W2 | 09/12/2018 | 09/21/2018 | 5 | 0 | 5 | 09/24/2018 | 09/24/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 12/31/2020 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | REVERE | 672120 | 02151 | 7.6 |  |  | Solar |  | 05_14_43L4 | 02/14/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | METHUEN | 643637 | 01844 | 10 |  |  | Solar |  | 05_14_60L2 | 09/30/2024 | 10/29/2024 | 1 | 0 | 1 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/30/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N
National Grid | BYFIELD | 558017 | 01922 | 7.6 |  |  | Solar |  | 05_14_74L6 | 10/04/2023 | 10/09/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/04/2023 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2024 | Connected |  | N
National Grid | LAWRENCE | 176215 | 01841 | 1000 |  |  | Solar |  | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SPENCER | 176224 | 01562 | 7.6 |  |  | Solar |  | 05_01_304W2 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 438733 | 01519 | 0 |  |  | Natural Gas |  | 05_01_413L6 | 08/16/2022 | 10/26/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | SOUTHBRIDGE | 494286 | 01550 | 7.6 |  |  | Solar |  | 05_01_610W3 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2023 | Connected |  | Y
National Grid | WESTMINSTER | 494888 | 01473 | 1500 |  |  | Solar |  | 05_05_11W85 | 07/12/2023 | 07/28/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2023 | 09/18/2023 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/12/2023 | 10/22/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SWANSEA | 641041 | 02777 | 7.6 |  |  | Solar |  | 05_12_29W1 | 11/08/2024 | 03/12/2025 | 10 | 7 | 3 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LYNN | 192939 | 01904 | 7.6 |  |  | Solar |  | 05_12_7W2 | 08/08/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 673315 | 02151 | 10 |  |  | Solar |  | 05_14_43L4 | 02/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 646226 | 01844 | 5.76 |  |  | Solar |  | 05_14_60L2 | 10/21/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/24/2025 | Y | EXP | 365 | 02/26/2025 | 02/25/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | BYFIELD | 552870 | 01922 | 10 |  |  | Solar |  | 05_14_74L6 | 11/06/2023 | 11/15/2023 | 6 | 4 | 2 | 11/16/2023 | 11/16/2023 | 48 | 41 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/06/2023 | 4/17/2025 | Y | EXP | 365 | 07/31/2024 | 10/23/2024 | 85 | 0 | 85 |  |  | 11/13/2024 | Connected |  | N
National Grid | LAWRENCE | 177040 | 01841 | 2592 |  |  | Solar |  | 05_01_21W1 | 07/27/2016 | 08/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 5/31/2021 | Y | STD | 1251 | 11/05/2020 | 04/15/2021 | 110 | 0 | 110 | 5/3/2021 | 5/26/2021 | 6/15/2021 | Connected |  | N
National Grid | SPENCER | 176366 | 01562 | 10 |  |  | Solar |  | 05_01_304W2 | 03/09/2016 | 03/09/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 3/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | GRAFTON | 175098 | 01519 | 2000 |  |  | Solar |  | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 536407 | 01507 | 15.2 |  |  | Solar |  | 05_01_610W3 | 06/30/2023 | 07/05/2023 | 2 | 1 | 1 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | WESTMINSTER | 494886 | 01473 | 2000 |  |  | Solar |  | 05_05_11W85 | 07/06/2023 | 08/24/2023 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2023 | 09/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/06/2023 | 10/22/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SWANSEA | 642538 | 02777 | 7.54 |  |  | Solar |  | 05_12_29W1 | 09/24/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 197019 | 01905 | 7.6 |  |  | Solar |  | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 677373 | 02151 | 5.76 |  |  | Solar |  | 05_14_43L4 | 03/12/2025 | 03/26/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | METHUEN | 681996 | 01844 | 22.8 |  |  | Solar |  | 05_14_60L2 | 04/01/2025 | 04/23/2025 | 15 | 12 | 3 | 04/24/2025 | 04/24/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | BYFIELD | 562808 | 01922 | 6 |  |  | Solar |  | 05_14_74L6 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 | 11/01/2023 | 12/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | LAWRENCE | 177038 | 01841 | 800 |  |  | Solar |  | 05_01_21W1 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 176400 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/18/2016 | 03/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | GRAFTON | 175097 | 01560 | 1000 |  |  | Solar |  | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 623437 | 01550 | 1.74 |  |  | Solar |  | 05_01_610W3 | 07/09/2024 | 07/19/2024 | 2 | 0 | 2 | 07/22/2024 | 07/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2024 | Connected |  | N
National Grid | WESTMINSTER | 174338 | 01473 | 260 |  |  | Solar |  | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/1/2013 |  | 2/15/2012 | N | STD | -380 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 5/8/2015 | Connected |  | N
National Grid | SWANSEA | 643215 | 02777 | 10 |  |  | Solar |  | 05_12_29W1 | 09/26/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/26/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LYNN | 197013 | 01904 | 3 |  |  | Solar |  | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 09/27/2018 | 5/20/2019 | Y | EXP | 213 | 02/12/2019 | 04/11/2019 | 58 | 0 | 58 |  |  | 4/27/2019 | Connected |  | N
National Grid | REVERE | 678663 | 02151 | 15.96 |  |  | Solar |  | 05_14_43L4 | 03/18/2025 | 04/07/2025 | 14 | 9 | 5 | 04/08/2025 | 04/08/2025 | 33 | 19 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | LAWRENCE | 426194 | 01841 | 460 |  |  | Solar |  | 05_14_60L3 | 05/18/2022 | 07/14/2022 | 38 | 31 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 05/18/2022 | 5/1/2026 | Y | STD | 500 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BYFIELD | 578472 | 01922 | 2.03 |  |  | Solar |  | 05_14_74L6 | 01/02/2024 | 01/05/2024 | 3 | 0 | 3 | 01/08/2024 | 01/08/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  | 2/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | LAWRENCE | 177271 | 01841 | 40 |  |  | Solar |  | 05_01_21W1 | 11/14/2016 | 11/14/2016 | 1 | 1 | 0 | 11/16/2016 | 11/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 |  | 11/20/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 2/17/2017 | 2/17/2017 | 2/16/2017 | Connected |  | N
National Grid | LEICESTER | 176463 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | SUTTON | 176301 | 01590 | 1126 |  |  | Natural Gas |  | 05_01_413L6 | 09/11/2015 | 09/11/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2015 | 10/30/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 7/1/2018 | N | STD | 305 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 8/27/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 623866 | 01550 | 3.8 |  |  | Solar |  | 05_01_610W3 | 07/10/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 174337 | 01473 | 499 |  |  | Solar |  | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 |  | 4/14/2012 | N | STD | -285 |  |  | 0 | 0 | 0 | 1/29/2015 | 1/29/2015 | 2/18/2015 | Connected |  | N
National Grid | SWANSEA | 652674 | 02777 | 7.6 |  |  | Solar |  | 05_12_29W1 | 11/06/2024 | 12/04/2024 | 10 | 5 | 5 | 12/05/2024 | 12/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | N
National Grid | LYNN | 196955 | 01904 | 3.8 |  |  | Solar |  | 05_12_7W2 | 11/26/2018 | 02/04/2019 | 49 | 44 | 5 | 02/05/2019 | 02/05/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 11/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 684767 | 02151 | 11.4 |  |  | Solar |  | 05_14_43L4 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 8/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LAWRENCE | 475737 | 01841 | 100 |  |  | Solar |  | 05_14_60L3 | 12/15/2022 | 01/18/2023 | 21 | 12 | 9 | 01/19/2023 | 01/19/2023 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 12/15/2022 | 10/7/2026 | Y | EXP | 326 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 580061 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | LAWRENCE | 177846 | 01841 | 1460 |  |  | Solar |  | 05_01_21W1 | 10/17/2017 | 10/17/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 176489 | 01562 | 7.6 |  |  | Solar |  | 05_01_304W2 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/14/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | GRAFTON | 192559 | 01560 | 5786 |  |  | Solar |  | 05_01_413L6 | 08/23/2018 | 09/17/2018 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2019 | 03/28/2019 | 110 | 110 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 655947 | 01550 | 10 |  |  | Solar |  | 05_01_610W3 | 11/21/2024 | 01/06/2025 | 16 | 12 | 4 | 01/07/2025 | 01/07/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | WESTMINSTER | 174334 | 01473 | 185.6 |  |  | Solar |  | 05_05_11W85 | 01/24/2012 | 01/24/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 2/15/2012 | N | EXP | -301 |  |  | 0 | 0 | 0 | 11/21/2012 | 11/21/2012 | 12/13/2012 | Connected |  | N
National Grid | SWANSEA | 653618 | 02777 | 4.56 |  |  | Solar |  | 05_12_29W1 | 11/12/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 198416 | 01904 | 3.8 |  |  | Solar |  | 05_12_7W2 | 11/09/2018 | 11/20/2018 | 5 | 0 | 5 | 11/21/2018 | 11/21/2018 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N
National Grid | REVERE | 685249 | 02151 | 7.6 |  |  | Solar |  | 05_14_43L4 | 04/15/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 510521 | 01841 | 480 |  |  | Solar |  | 05_14_60L3 | 08/01/2023 | 09/08/2023 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 12/11/2023 | 63 | 45 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 08/01/2023 | 12/15/2026 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NEWBURY | 603429 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/17/2024 | 6/24/2025 | Y | EXP | 365 | 10/23/2024 | 12/02/2024 | 41 | 0 | 41 |  |  | 12/6/2024 | Connected |  | N
National Grid | LAWRENCE | 178344 | 01841 | 498 |  |  | Solar |  | 05_01_21W1 | 01/11/2018 | 02/12/2018 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/01/2018 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 176514 | 01542 | 10 |  |  | Solar |  | 05_01_304W2 | 10/01/2015 | 10/01/2015 | 1 | 1 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/20/2016 | 4/20/2016 | 4/27/2016 | Connected |  | N
National Grid | GRAFTON | 174130 | 01560 | 2000 |  |  | Solar |  | 05_01_413L7 | 05/01/2012 | 05/01/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2012 | 08/16/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 554299 | 01550 | 1999.998 |  |  | Solar |  | 05_01_612W1 | 04/23/2024 | 10/18/2024 | 123 | 116 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTMINSTER | 174454 | 01473 | 3260 |  |  | Solar |  | 05_05_11W85 | 07/13/2012 | 07/13/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 655690 | 02777 | 6 |  |  | Solar |  | 05_12_29W1 | 11/20/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | LYNN | 198866 | 01904 | 7.6 |  |  | Solar |  | 05_12_7W2 | 10/19/2018 | 11/05/2018 | 7 | 1 | 6 | 11/06/2018 | 11/06/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 | 10/19/2018 | 1/27/2020 | Y | EXP | 365 | 06/05/2019 | 06/22/2019 | 17 | 0 | 17 |  |  | 1/16/2020 | Connected |  | N
National Grid | REVERE | 684928 | 02151 | 7.6 |  |  | Solar |  | 05_14_43L4 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/14/2025 | 7/8/2026 | Y | EXP | 365 | 09/25/2025 | 10/30/2025 | 36 | 0 | 36 |  |  | 11/7/2025 | Connected |  | N
National Grid | METHUEN | 176280 | 01844 | 42 |  |  | Solar |  | 05_14_60L3 | 05/06/2015 | 05/06/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 | 05/06/2015 | 10/30/2015 | Y | EXP | 161 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/13/2016 | Connected |  | N
National Grid | NEWBURY | 609579 | 01950 | 13.6 |  |  | Solar |  | 05_14_74L6 | 05/09/2024 | 05/16/2024 | 3 | 0 | 3 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/09/2024 | 8/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | LAWRENCE | 192241 | 01841 | 10 |  |  | Solar |  | 05_01_21W1 | 07/30/2018 | 09/27/2018 | 24 | 23 | 1 | 09/28/2018 | 09/28/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 176877 | 01524 | 995 |  |  | Solar |  | 05_01_304W2 | 05/04/2016 | 05/04/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2016 | 06/20/2016 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 |  | 9/1/2018 | N | STD | 680 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 178064 | 01560 | 9 |  |  | Solar |  | 05_01_413L7 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 | 09/05/2017 | 09/05/2017 | 140 | 15 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/10/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 553455 | 01566 | 120 |  |  | Solar |  | 05_01_612W1 | 09/11/2023 | 09/29/2023 | 15 | 5 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WINCHENDON | 174708 | 01475 | 500 |  |  | Solar |  | 05_05_11W85 | 06/17/2013 | 06/17/2013 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 688867 | 02777 | 11.4 |  |  | Solar |  | 05_12_29W1 | 05/01/2025 | 06/18/2025 | 13 | 8 | 5 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/01/2025 | 7/28/2026 | Y | EXP | 365 | 08/21/2025 | 10/29/2025 | 70 | 0 | 70 |  |  | 11/5/2025 | Connected |  | N
National Grid | LYNN | 200168 | 01904 | 3.8 |  |  | Solar |  | 05_12_7W2 | 11/05/2018 | 11/20/2018 | 3 | 3 | 0 | 11/21/2018 | 11/21/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | REVERE | 547085 | 02151 | 50 |  |  | Solar |  | 05_14_43L6 | 11/14/2023 | 02/07/2024 | 57 | 47 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 1/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 177073 | 01844 | 36 |  |  | Solar |  | 05_14_60L3 | 08/03/2016 | 08/03/2016 | 1 | 0 | 1 | 08/05/2016 | 08/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 8/9/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/27/2016 | Connected |  | Y
National Grid | NEWBURY | 614816 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 06/04/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 192732 | 01841 | 4580 |  |  | Solar |  | 05_01_21W1 | 08/06/2018 | 08/27/2018 | 256 | 20 | 236 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 10/17/2018 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 184400 | 01562 | 6 |  |  | Solar |  | 05_01_304W2 | 05/11/2018 | 05/11/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 200645 | 01519 | 20 |  |  | Solar |  | 05_01_413L7 | 02/21/2019 | 04/12/2019 | 36 | 25 | 11 | 04/15/2019 | 04/15/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 |  | 4/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | STURBRIDGE | 579723 | 01566 | 3000 |  |  | Solar |  | 05_01_612W1 | 04/26/2024 | 10/18/2024 | 120 | 111 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WINCHENDON | 175268 | 01475 | 130 |  |  | Solar |  | 05_05_11W85 | 06/20/2014 | 06/20/2014 | 9 | 7 | 2 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 |  | 10/31/2014 | N | EXP | 88 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 12/22/2014 | Connected |  | N
National Grid | SWANSEA | 691976 | 02777 | 5.12 |  |  | Solar |  | 05_12_29W1 | 05/15/2025 | 06/18/2025 | 5 | 1 | 4 | 07/03/2025 | 07/03/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/15/2025 | 10/10/2026 | Y | EXP | 365 | 10/07/2025 | 10/17/2025 | 11 | 0 | 11 |  |  | 11/25/2025 | Connected |  | N
National Grid | LYNN | 200027 | 01904 | 10 |  |  | Solar |  | 05_12_7W2 | 11/01/2018 | 11/21/2018 | 2 | 1 | 1 | 11/26/2018 | 11/26/2018 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/01/2018 | 7/17/2020 | Y | EXP | 365 | 07/26/2019 | 07/31/2019 | 5 | 0 | 5 |  |  | 7/13/2020 | Connected |  | N
National Grid | REVERE | 681823 | 02151 | 6.5 |  |  | Solar |  | 05_14_43L6 | 04/02/2025 | 04/18/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 72 | 58 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HAVERHILL | 177456 | 01832 | 594 |  |  | Solar |  | 05_14_60L3 | 12/07/2016 | 12/07/2016 | 40 | 25 | 15 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 | 05/22/2017 | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2017 |  | 12/12/2017 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/11/2017 | 10/11/2017 | 10/17/2017 | Connected |  | Y
National Grid | NEWBURY | 625512 | 01950 | 5.76 |  |  | Solar |  | 05_14_74L6 | 07/17/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | LAWRENCE | 199985 | 01841 | 7.6 |  |  | Solar |  | 05_01_21W1 | 11/01/2018 | 12/31/2018 | 8 | 0 | 8 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 185479 | 01524 | 5 |  |  | Solar |  | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 11 | 7 | 4 | 07/13/2018 | 07/13/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | SUTTON | 204724 | 01590 | 7.6 |  |  | Solar |  | 05_01_413L7 | 01/11/2019 | 02/11/2019 | 19 | 10 | 9 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 01/11/2019 | 2/27/2020 | Y | EXP | 365 | 04/18/2019 | 05/28/2019 | 40 | 0 | 40 |  |  | 6/29/2019 | Connected |  | N
National Grid | STURBRIDGE | 637211 | 01566 | 3.8 |  |  | Solar |  | 05_01_612W1 | 09/03/2024 | 10/08/2024 | 3 | 2 | 1 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/03/2024 | 11/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WINCHENDON | 207776 | 01475 | 60 |  |  | Solar |  | 05_05_11W85 | 02/08/2019 | 02/22/2019 | 9 | 4 | 5 | 02/25/2019 | 02/25/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2019 | Connected |  | N
National Grid | SWANSEA | 605827 | 02777 | 250 |  |  | Solar |  | 05_12_29W2 | 05/13/2024 | 07/15/2024 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2024 | 07/16/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 3/8/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LYNN | 200644 | 01904 | 10 |  |  | Solar |  | 05_12_7W2 | 11/08/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176497 | 02151 | 34.2 |  |  | Solar |  | 05_14_43L6 | 02/07/2016 | 02/07/2016 | 5 | 5 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 | 02/07/2016 | 2/13/2017 | Y | EXP | 348 | 06/28/2016 | 07/05/2016 | 4 | 0 | 4 | 4/11/2016 | 4/11/2016 | 8/11/2016 | Connected |  | N
National Grid | HAVERHILL | 216789 | 01832 | 55 |  |  | Solar |  | 05_14_60L3 | 04/02/2019 | 04/11/2019 | 6 | 5 | 1 | 04/12/2019 | 04/12/2019 | 3 | 0 | 3 | 05/23/2019 | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/12/2019 |  | 7/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 629733 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 11/22/2024 | 12/05/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 200549 | 01841 | 363.2 |  |  | Solar |  | 05_01_21W1 | 04/09/2019 | 06/29/2019 | 22 | 21 | 1 | 07/01/2019 | 07/01/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 185476 | 01524 | 6 |  |  | Solar |  | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 5 | 2 | 3 | 07/05/2018 | 07/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 06/26/2018 | 7/1/2019 | Y | EXP | 343 | 04/10/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 6/20/2019 | Connected |  | N
National Grid | GRAFTON | 284646 | 01519 | 9.84 |  |  | Solar |  | 05_01_413L7 | 03/23/2020 | 04/13/2020 | 0 | 0 | 0 | 04/14/2020 | 04/14/2020 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2020 | 03/23/2020 | 4/13/2021 | Y | EXP | 365 | 07/30/2020 | 09/10/2020 | 42 | 5 | 37 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 729943 | 01566 |  |  |  | Battery Add-On |  | 05_01_612W1 | 10/29/2025 | 11/11/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINCHENDON | 291768 | 01475 | 0 |  |  | Other |  | 05_05_11W85 | 10/28/2020 | 12/21/2020 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 01/19/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 605829 | 02777 | 484.6 |  |  | Solar |  | 05_12_29W2 | 05/13/2024 | 07/02/2024 | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2024 | 07/16/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 3/8/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SALEM | 203133 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176496 | 02151 | 17.6 |  |  | Solar |  | 05_14_43L6 | 02/05/2016 | 02/05/2016 | 8 | 8 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2016 |  | 2/13/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/20/2016 | 9/20/2016 | 9/20/2016 | Connected |  | N
National Grid | HAVERHILL | 276671 | 01832 | 400 |  |  | Solar |  | 05_14_60L3 | 05/29/2020 | 07/09/2020 | 29 | 23 | 6 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 630908 | 01950 | 3.8 |  |  | Solar |  | 05_14_74L6 | 08/07/2024 | 11/04/2024 | 1 | 0 | 1 | 11/05/2024 | 11/05/2024 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 289979 | 01841 | 0 |  |  | Other |  | 05_01_21W1 | 01/14/2021 | 02/25/2021 | 27 | 18 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 190346 | 01562 | 10 |  |  | Solar |  | 05_01_304W2 | 07/10/2018 | 08/28/2018 | 19 | 0 | 19 | 08/29/2018 | 08/29/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 449561 | 01519 | 19 |  |  | Solar |  | 05_01_413L7 | 08/04/2022 | 08/12/2022 | 6 | 3 | 3 | 08/15/2022 | 08/15/2022 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | STURBRIDGE | 174657 | 01566 | 2000 |  |  | Solar |  | 05_01_612W1 | 03/28/2011 | 03/28/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/28/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 398023 | 01475 | 0 |  |  | Other |  | 05_05_11W85 | 12/06/2021 | 02/04/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 02/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 697403 | 02777 | 12.92 |  |  | Solar |  | 05_12_29W2 | 06/10/2025 | 09/18/2025 | 7 | 2 | 5 | 10/03/2025 | 10/03/2025 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 204942 | 01970 | 3.8 |  |  | Solar |  | 05_12_7W2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 142 | 0 | 142 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176538 | 02151 | 34.2 |  |  | Solar |  | 05_14_43L6 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 434 | 0 | 434 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 11/20/2017 | N | EXP | 628 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 349427 | 01832 | 9.8 |  |  | Solar |  | 05_14_60L3 | 04/21/2021 | 04/26/2021 | 2 | 0 | 2 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 637230 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 09/03/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 78 | 42 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | METHUEN | 306359 | 01844 | 5 |  |  | Solar |  | 05_01_21W1 | 09/10/2020 | 10/06/2020 | 17 | 14 | 3 | 10/07/2020 | 10/07/2020 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/10/2020 | 12/24/2021 | Y | EXP | 365 | 11/09/2021 | 01/25/2022 | 78 | 0 | 78 |  |  | 2/12/2022 | Connected |  | N
National Grid | LEICESTER | 287978 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 04/15/2020 | 05/06/2020 | 11 | 9 | 2 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Connected |  | N
National Grid | GRAFTON | 365963 | 01519 | 7.6 |  |  | Solar |  | 05_01_413L7 | 08/10/2021 | 01/05/2022 | 2 | 0 | 2 | 08/13/2021 | 08/13/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 08/10/2021 | 6/3/2023 | Y | EXP | 365 | 03/01/2022 | 03/28/2022 | 28 | 0 | 28 |  |  | 6/15/2022 | Connected |  | N
National Grid | STURBRIDGE | 174753 | 01566 | 24.73 |  |  | Solar |  | 05_01_612W1 | 01/31/2014 | 01/31/2014 | 6 | 0 | 6 | 02/11/2014 | 02/11/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 |  | 4/30/2014 | N | EXP | 6 |  |  | 0 | 0 | 0 | 7/10/2014 | 7/10/2014 | 8/26/2014 | Connected |  | N
National Grid | WINCHENDON | 443980 | 01475 | 0 |  |  | Other |  | 05_05_11W85 | 01/30/2023 | 02/14/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2023 | 03/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 725929 | 02777 | 5.76 |  |  | Solar |  | 05_12_29W2 | 10/13/2025 | 10/20/2025 | 7 | 5 | 2 | 11/10/2025 | 11/10/2025 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 234798 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 07/10/2019 | 07/18/2019 | 5 | 0 | 5 | 07/19/2019 | 07/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 7/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | REVERE | 193994 | 02151 | 540 |  |  | Solar |  | 05_14_43L6 | 09/18/2018 | 10/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 396682 | 01832 | 0 |  |  | Other |  | 05_14_60L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/03/2022 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 640464 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 09/17/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/17/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | METHUEN | 307858 | 01844 | 15.2 |  |  | Solar |  | 05_01_21W1 | 08/27/2020 | 09/01/2020 | 2 | 0 | 2 | 09/02/2020 | 09/02/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/27/2020 | 11/15/2023 | Y | EXP |  | 06/16/2021 | 01/17/2022 | 216 | 7 | 209 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 322290 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 02/03/2021 | 03/26/2021 | 35 | 34 | 1 | 03/29/2021 | 03/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 3/25/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 404096 | 01590 | 7.6 |  |  | Solar |  | 05_01_413L7 | 12/30/2021 | 01/26/2022 | 17 | 15 | 2 | 01/27/2022 | 01/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  | 8/2/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | STURBRIDGE | 176230 | 01566 | 500 |  |  | Solar |  | 05_01_612W1 | 02/11/2015 | 02/11/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 | 04/09/2015 | 07/24/2015 | 72 | 0 | 72 | 02/23/2015 | 03/24/2015 | 20 | 0 | 20 |  | 07/24/2015 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 668365 | 01475 | 60 |  |  | Solar |  | 05_05_11W85 | 03/05/2025 | 04/11/2025 | 28 | 18 | 10 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | SWANSEA | 177353 | 02777 | 3.8 |  |  | Solar |  | 05_12_29W2 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 | 02/15/2017 | 7/17/2019 | Y | EXP | 870 | 05/24/2018 | 05/24/2018 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 301272 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  | 8/4/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 193993 | 02151 | 650 |  |  | Solar |  | 05_14_43L6 | 09/12/2018 | 10/02/2018 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 521128 | 01835 | 0 |  |  | Other |  | 05_14_60L3 | 08/11/2023 | 08/28/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 02/09/2024 | 112 | 93 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 645132 | 01950 | 1.74 |  |  | Solar |  | 05_14_74L6 | 10/04/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | METHUEN | 337144 | 01844 | 1100 |  |  | Solar |  | 05_01_21W1 | 05/14/2021 | 06/23/2021 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2021 | 10/14/2022 | 288 | 171 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 324435 | 01562 | 7.6 |  |  | Solar |  | 05_01_304W2 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 436971 | 01519 | 10 |  |  | Solar |  | 05_01_413L7 | 06/10/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | STURBRIDGE | 176256 | 01566 | 2000 |  |  | Solar |  | 05_01_612W1 | 07/09/2015 | 07/09/2015 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/26/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/01/2016 | 07/20/2016 | 12 | 0 | 12 | 7/6/2016 | 07/09/2015 | 8/31/2018 | Y | STD | 786 | 04/30/2018 | 06/05/2018 | 36 | 0 | 36 |  |  | 8/10/2018 | Connected |  | N
National Grid | WINCHENDON | 703902 | 01475 | 11.52 |  |  | Solar |  | 05_05_17J1 | 07/10/2025 | 08/13/2025 | 10 | 6 | 4 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SWANSEA | 196948 | 02777 | 8.64 |  |  | Solar |  | 05_12_29W2 | 09/25/2018 | 10/17/2018 | 13 | 7 | 6 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 311805 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 313668 | 02151 | 6 |  |  | Solar |  | 05_14_43L6 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2020 |  | 9/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 665620 | 01835 | 67.3 |  |  | Solar |  | 05_14_60L3 | 01/22/2025 | 02/14/2025 | 17 | 7 | 10 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 1/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | N
National Grid | NEWBURY | 645336 | 01922 | 7.6 |  |  | Solar |  | 05_14_74L6 | 10/07/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | METHUEN | 341311 | 01844 | 13.8 |  |  | Solar |  | 05_01_21W1 | 02/09/2021 | 03/08/2021 | 17 | 14 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 332953 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 12/18/2020 | 01/07/2021 | 12 | 11 | 1 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 7/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | GRAFTON | 477664 | 01519 | 9.57 |  |  | Solar |  | 05_01_413L7 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/22/2023 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | N
National Grid | STURBRIDGE | 176274 | 01566 | 984 |  |  | Solar |  | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/15/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | WINCHENDON | 671086 | 01475 | 5.76 |  |  | Solar |  | 05_05_17J1 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | SOMERSET | 208985 | 02726 | 7.6 |  |  | Solar |  | 05_12_29W2 | 03/15/2019 | 03/18/2019 | 1 | 1 | 0 | 03/19/2019 | 03/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/15/2019 | 2/21/2020 | Y | EXP | 337 | 08/16/2019 | 10/02/2019 | 47 | 0 | 47 |  |  | 10/31/2019 | Connected |  | N
National Grid | SALEM | 318712 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 10/27/2020 | 11/02/2020 | 3 | 0 | 3 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 375768 | 02151 | 7.6 |  |  | Solar |  | 05_14_43L6 | 08/13/2021 | 08/30/2021 | 12 | 11 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 426844 | 01832 | 4998 |  |  | Solar |  | 05_14_60L4 | 05/31/2022 | 07/25/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 05/31/2022 | 8/17/2026 | Y | CMPX | 308 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NEWBURY | 651851 | 01950 | 10 |  |  | Solar |  | 05_14_74L6 | 11/13/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | LAWRENCE | 449868 | 01841 | 10 |  |  | Solar |  | 05_01_21W1 | 12/29/2022 | 01/04/2023 | 3 | 0 | 3 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 337127 | 01562 | 9.86 |  |  | Solar |  | 05_01_304W2 | 01/15/2021 | 01/22/2021 | 3 | 0 | 3 | 01/25/2021 | 01/25/2021 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2021 | 01/15/2021 | 1/21/2022 | Y | EXP | 365 | 05/04/2021 | 05/21/2021 | 17 | 0 | 17 |  |  | 8/5/2021 | Connected |  | N
National Grid | SUTTON | 505691 | 01590 | 15 |  |  | Solar |  | 05_01_413L7 | 03/02/2023 | 04/20/2023 | 34 | 25 | 9 | 04/21/2023 | 04/21/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 |  | 6/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2023 | Connected |  | N
National Grid | STURBRIDGE | 176273 | 01566 | 984 |  |  | Solar |  | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/9/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | WINCHENDON | 691231 | 01475 | 20 |  |  | Solar |  | 05_05_17J1 | 05/13/2025 | 05/20/2025 | 5 | 0 | 5 | 05/21/2025 | 05/21/2025 | 23 | 0 | 23 | 07/29/2025 | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 | 8/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 216823 | 02726 | 3.8 |  |  | Solar |  | 05_12_29W2 | 04/02/2019 | 04/23/2019 | 14 | 10 | 4 | 04/24/2019 | 04/24/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | SALEM | 462753 | 01970 | 7.6 |  |  | Solar |  | 05_12_7W2 | 10/06/2022 | 10/12/2022 | 4 | 1 | 3 | 10/13/2022 | 10/13/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 416288 | 02151 | 7.6 |  |  | Solar |  | 05_14_43L6 | 12/20/2022 | 01/05/2023 | 10 | 10 | 0 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | HAVERHILL | 174776 | 01832 | 3000 |  |  | Solar |  | 05_14_60L4 | 01/22/2013 | 01/22/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2013 | 05/21/2013 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 653191 | 01951 | 10 |  |  | Solar |  | 05_14_74L6 | 11/12/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 2/26/2026 | Y | EXP | 365 | 05/24/2025 |  | 223 | 0 | 223 |  |  | 11/24/2025 | Connected |  | N
National Grid | METHUEN | 452991 | 01844 | 10 |  |  | Solar |  | 05_01_21W1 | 11/02/2022 | 11/09/2022 | 6 | 4 | 2 | 11/10/2022 | 11/10/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/02/2022 | 8/5/2024 | Y | EXP | 365 | 06/16/2023 | 08/03/2023 | 49 | 0 | 49 |  |  | 8/29/2023 | Connected |  | N
National Grid | LEICESTER | 374481 | 01524 | 7.6 |  |  | Solar |  | 05_01_304W2 | 08/06/2021 | 09/09/2021 | 23 | 13 | 10 | 09/10/2021 | 09/10/2021 | 139 | 115 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 594094 | 01590 | 9.86 |  |  | Solar |  | 05_01_413L7 | 03/19/2024 | 04/18/2024 | 22 | 19 | 3 | 04/19/2024 | 04/19/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 176430 | 01566 | 2000 |  |  | Solar |  | 05_01_612W1 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2016 | 03/07/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 702804 | 01475 | 22.04 |  |  | Solar |  | 05_05_17J1 | 07/03/2025 | 07/10/2025 | 4 | 0 | 4 | 07/11/2025 | 07/11/2025 | 71 | 58 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 230204 | 02726 | 0 |  |  | Solar |  | 05_12_29W2 | 05/22/2019 | 05/30/2019 | 4 | 0 | 4 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2019 | Connected |  | N
National Grid | SALEM | 503442 | 01970 | 10 |  |  | Solar |  | 05_12_7W2 | 03/19/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 25 | 0 | 25 | 05/08/2023 | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/31/2024 | N | EXP | 365 | 08/01/2023 | 07/31/2023 | 0 | 0 | 0 |  |  | 8/8/2023 | Connected |  | Y
National Grid | REVERE | 418171 | 02151 | 149.9 |  |  | Solar |  | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/8/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/8/2023 | Connected |  | N
National Grid | HAVERHILL | 175389 | 01832 | 100 |  |  | Solar |  | 05_14_60L4 | 09/11/2014 | 09/11/2014 | 7 | 0 | 7 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 12/19/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/5/2015 | 2/5/2015 | 2/18/2015 | Connected |  | N
National Grid | NEWBURY | 657035 | 01951 | 7.6 |  |  | Solar |  | 05_14_74L6 | 11/28/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 367365 | 01844 | 3.8 |  |  | Solar |  | 05_01_21W1 | 07/08/2021 | 07/13/2021 | 3 | 0 | 3 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2022 | Connected |  | N
National Grid | SPENCER | 382046 | 01562 | 7.6 |  |  | Solar |  | 05_01_304W2 | 01/20/2022 | 02/14/2022 | 17 | 13 | 4 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 595438 | 01519 | 46 |  |  | Solar |  | 05_01_413L7 | 03/08/2024 | 03/12/2024 | 2 | 0 | 2 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 176700 | 01566 | 1980 |  |  | Solar |  | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/03/2016 | 27 | 21 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 741251 | 01475 | 7.6 |  |  | Solar |  | 05_05_17J3 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 228309 | 02726 | 10 |  |  | Solar |  | 05_12_29W2 | 05/15/2019 | 05/22/2019 | 4 | 3 | 1 | 05/23/2019 | 05/23/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 |  | 7/30/2019 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | SALEM | 516902 | 01970 | 6.38 |  |  | Solar |  | 05_12_7W2 | 08/07/2023 |  | 84 | 26 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 418169 | 02151 | 133.2 |  |  | Solar |  | 05_14_43L6 | 03/17/2022 | 04/11/2022 | 17 | 11 | 6 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | HAVERHILL | 178375 | 01832 | 7.6 |  |  | Solar |  | 05_14_60L4 | 11/21/2017 | 11/21/2017 | 10 | 0 | 10 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2017 |  | 2/15/2019 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | NEWBURY | 682135 | 01950 | 20 |  |  | Solar |  | 05_14_74L6 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | METHUEN | 382477 | 01844 | 15.2 |  |  | Solar |  | 05_01_21W1 | 09/29/2021 | 12/29/2021 | 22 | 19 | 3 | 11/02/2021 | 11/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | SPENCER | 425991 | 01562 | 7.25 |  |  | Solar |  | 05_01_304W2 | 06/26/2022 | 07/18/2022 | 16 | 13 | 3 | 07/19/2022 | 07/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/26/2022 | 4/3/2024 | Y | EXP | 365 | 03/25/2023 | 04/04/2023 | 11 | 0 | 11 |  |  | 4/5/2023 | Connected |  | N
National Grid | GRAFTON | 615975 | 01519 | 17.48 |  |  | Solar |  | 05_01_413L7 | 06/10/2024 | 07/11/2024 | 22 | 19 | 3 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | STURBRIDGE | 176699 | 01566 | 288 |  |  | Solar |  | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 05/27/2016 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 640868 | 01475 | 15.2 |  |  | Solar |  | 05_05_17J3 | 11/13/2024 | 11/19/2024 | 5 | 3 | 2 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2025 | Connected |  | N
National Grid | SOMERSET | 278977 | 02726 | 9.36 |  |  | Solar |  | 05_12_29W2 | 03/05/2020 | 03/11/2020 | 3 | 0 | 3 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 530131 | 01970 | 8.12 |  |  | Solar |  | 05_12_7W2 | 07/12/2023 | 08/02/2023 | 16 | 15 | 1 | 08/03/2023 | 08/03/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 418150 | 02151 | 149.9 |  |  | Solar |  | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | HAVERHILL | 178464 | 01832 | 199.8 |  |  | Solar |  | 05_14_60L4 | 01/22/2018 | 01/22/2018 | 0 | 0 | 0 | 03/21/2018 | 03/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/28/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 6/28/2018 | Connected |  | N
National Grid | NEWBURY | 640887 | 01950 | 5.76 |  |  | Solar |  | 05_14_75L1 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 520923 | 01844 | 0 |  |  | Solar |  | 05_01_21W1 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 349 | 196 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 427817 | 01562 | 7.54 |  |  | Solar |  | 05_01_304W2 | 08/17/2022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 623119 | 01519 | 9.86 |  |  | Solar |  | 05_01_413L7 | 07/08/2024 | 07/31/2024 | 14 | 12 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/08/2024 | 8/26/2025 | Y | EXP | 365 | 08/30/2024 | 10/03/2024 | 35 | 0 | 35 |  |  | 10/24/2024 | Connected |  | N
National Grid | STURBRIDGE | 176920 | 01566 | 3100 |  |  | Solar |  | 05_01_612W1 | 11/16/2015 | 11/16/2015 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 | 12/28/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 04/12/2017 | 05/15/2018 | 275 | 0 | 275 | 8/25/2016 | 11/16/2015 | 10/22/2018 | Y | STD | 788 | 05/02/2018 | 07/05/2018 | 64 | 0 | 64 |  |  | 9/25/2018 | Connected |  | N
National Grid | WINCHENDON | 175863 | 01475 | 7.6 |  |  | Solar |  | 05_05_18J5 | 09/21/2015 | 09/21/2015 | 2 | 2 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/28/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 4/29/2016 | Connected |  | N
National Grid | SOMERSET | 286474 | 02726 | 3.8 |  |  | Solar |  | 05_12_29W2 | 04/17/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 | 04/17/2020 | 10/21/2021 | Y | EXP | 365 | 04/13/2021 | 05/03/2021 | 20 | 0 | 20 |  |  | 9/3/2021 | Connected |  | N
National Grid | SALEM | 591484 | 01970 | 3.8 |  |  | Solar |  | 05_12_7W2 | 02/27/2024 | 04/11/2024 | 30 | 25 | 5 | 04/12/2024 | 04/12/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 532437 | 02151 | 6 |  |  | Solar |  | 05_14_43L6 | 06/14/2023 | 06/16/2023 | 2 | 0 | 2 | 06/20/2023 | 06/20/2023 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178529 | 01832 | 5000 |  |  | Solar |  | 05_14_60L4 | 12/04/2017 | 12/04/2017 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2018 | 02/08/2018 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 705538 | 01950 | 13.68 |  |  | Solar |  | 05_14_75L1 | 07/18/2025 | 09/15/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 536765 | 01850 | 13.8 |  |  | Solar |  | 05_01_21W1 | 07/11/2023 | 11/07/2023 | 82 | 72 | 10 | 11/08/2023 | 11/08/2023 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 506760 | 01524 | 18.85 |  |  | Solar |  | 05_01_304W2 | 03/06/2023 | 03/07/2023 | 1 | 0 | 1 | 03/08/2023 | 03/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | GRAFTON | 642171 | 01560 | 23 |  |  | Solar |  | 05_01_413L7 | 10/18/2024 | 10/23/2024 | 4 | 2 | 2 | 10/24/2024 | 10/24/2024 | 70 | 58 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | STURBRIDGE | 177177 | 01566 | 144 |  |  | Solar |  | 05_01_612W1 | 06/02/2016 | 06/02/2016 | 5 | 5 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2016 |  | 6/8/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N
National Grid | WINCHENDON | 176359 | 01475 | 5 |  |  | Solar |  | 05_05_18J5 | 03/07/2016 | 03/07/2016 | 2 | 2 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/07/2016 | 3/13/2017 | Y | EXP | 325 | 07/27/2016 | 08/15/2016 | 13 | 0 | 13 | 4/22/2016 | 4/22/2016 | 10/19/2016 | Connected |  | N
National Grid | SOMERSET | 583402 | 02726 | 10 |  |  | Solar |  | 05_12_29W2 | 01/19/2024 | 02/13/2024 | 18 | 16 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/19/2024 | 3/1/2025 | Y | EXP | 365 | 05/15/2024 | 05/28/2024 | 14 | 0 | 14 |  |  | 5/31/2024 | Connected |  | N
National Grid | SALEM | 550928 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 18 | 0 | 18 | 12/12/2023 | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 |  | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 636277 | 02151 | 18.525 |  |  | Solar |  | 05_14_60L4 | 08/29/2024 | 09/04/2024 | 3 | 1 | 2 | 09/05/2024 | 09/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 9/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2024 | Connected |  | N
National Grid | HAVERHILL | 717529 | 01835 | 7.6 |  |  | Solar |  | 05_14_75L1 | 09/10/2025 | 09/29/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 16 | 1 | 15 | 11/05/2025 | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NEWBURY | 620137 | 01951 | 7.6 |  |  | Solar |  | 05_01_21W1 | 06/24/2024 | 07/23/2024 | 5 | 0 | 5 | 07/24/2024 | 07/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 06/24/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LOWELL | 514181 | 01850 | 10 |  |  | Solar |  | 05_01_304W2 | 03/23/2023 | 03/24/2023 | 1 | 0 | 1 | 03/27/2023 | 03/27/2023 | 253 | 25 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 691149 | 01524 | 15.2 |  |  | Solar |  | 05_01_413L7 | 05/19/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | GRAFTON | 177187 | 01519 | 498 |  |  | Solar |  | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176564 | 01566 | 42 |  |  | Solar |  | 05_05_18J5 | 12/22/2015 | 12/22/2015 | 22 | 22 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 |  | 12/27/2016 | N | EXP | 335 |  |  | 0 | 0 | 0 | 2/4/2016 | 2/4/2016 | 6/16/2016 | Connected |  | N
National Grid | WINCHENDON | 632118 | 01475 | 10 |  |  | Solar |  | 05_12_29W2 | 08/23/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | SOMERSET | 600033 | 02726 | 10 |  |  | Solar |  | 05_12_7W2 | 03/29/2024 | 04/15/2024 | 11 | 8 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/29/2024 | 5/14/2025 | Y | EXP | 365 | 07/31/2024 | 08/30/2024 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 593129 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 03/16/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 6 | 1 | 5 | 04/16/2024 | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/22/2025 | N | EXP | 365 | 07/10/2024 | 08/30/2024 | 52 | 0 | 52 |  |  | 10/12/2024 | Connected |  | N
National Grid | REVERE | 201742 | 02151 | 372 |  |  | Solar |  | 05_14_61L1 | 11/21/2018 | 11/29/2018 | 4 | 4 | 0 | 11/30/2018 | 11/30/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 7/30/2021 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 717230 | 01835 | 11.5 |  |  | Solar |  | 05_14_75L1 | 09/05/2025 | 09/16/2025 | 14 | 10 | 4 | 10/23/2025 | 10/23/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 640689 | 01950 | 4.35 |  |  | Solar |  | 05_01_21W1 | 09/17/2024 | 10/08/2024 | 10 | 7 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 12/19/2025 | Y | EXP | 365 | 01/23/2025 | 06/20/2025 | 149 | 0 | 149 |  |  | 6/30/2025 | Connected |  | N
National Grid | DRACUT | 523641 | 01826 | 5 |  |  | Solar |  | 05_01_304W2 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 05/17/2023 | 4/18/2025 | Y | EXP | 465 | 01/10/2024 | 02/23/2024 | 45 | 0 | 45 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 306145 | 01562 | 0 |  |  | Other |  | 05_01_415L1 | 09/08/2020 | 10/02/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2020 | 10/26/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 |  | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRAFTON | 177186 | 01519 | 498 |  |  | Solar |  | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176988 | 01566 | 3.8 |  |  | Solar |  | 05_05_18J5 | 03/10/2017 | 03/10/2017 | 4 | 2 | 2 | 03/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/15/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 6/5/2017 | 6/5/2017 | 6/7/2017 | Connected |  | N
National Grid | WINCHENDON | 636021 | 01475 | 4.93 |  |  | Solar |  | 05_12_29W2 | 08/28/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | SOMERSET | 604225 | 02726 | 3.48 |  |  | Solar |  | 05_12_7W2 | 04/16/2024 |  | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 605419 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 04/22/2024 | 05/01/2024 | 8 | 7 | 1 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/22/2024 | 5/23/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/6/2025 | Connected |  | N
National Grid | REVERE | 285209 | 02151 | 4.08 |  |  | Solar |  | 05_14_61L1 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 4/3/2021 | Y | EXP | 365 | 11/17/2020 | 02/08/2021 | 83 | 0 | 83 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 733331 | 01832 | 5.76 |  |  | Solar |  | 05_14_75L1 | 11/12/2025 | 12/10/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 656080 | 01843 | 3.8 |  |  | Solar |  | 05_01_21W1 | 11/21/2024 | 01/10/2025 | 28 | 22 | 6 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 523131 | 01850 | 9.216 |  |  | Solar |  | 05_01_304W2 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 637437 | 01524 | 499.9 |  |  | Solar |  | 05_01_415L1 | 09/17/2024 | 11/04/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2024 | 03/13/2025 | 87 | 67 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SUTTON | 177215 | 01590 | 60 |  |  | Solar |  | 05_01_612W1 | 06/10/2016 | 06/10/2016 | 7 | 7 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 6/18/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/15/2016 | 11/15/2016 | Connected |  | N
National Grid | CHARLTON | 188458 | 01507 | 8.36 |  |  | Solar |  | 05_05_18J5 | 07/05/2018 | 08/03/2018 | 21 | 0 | 21 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 647623 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W2 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | SOMERSET | 613662 | 02726 | 11.4 |  |  | Solar |  | 05_12_7W2 | 05/29/2024 | 06/11/2024 | 6 | 4 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 | 05/29/2024 | 8/6/2025 | Y | EXP | 365 | 08/21/2024 | 10/03/2024 | 44 | 0 | 44 |  |  | 2/8/2025 | Connected |  | N
National Grid | SALEM | 608805 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 05/04/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 336498 | 02151 | 10 |  |  | Solar |  | 05_14_61L1 | 06/10/2021 | 08/30/2021 | 56 | 55 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 178139 | 01835 | 7.6 |  |  | Solar |  | 05_14_75L1 | 03/22/2018 | 03/22/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 3/28/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 8/5/2019 | Connected |  | N
National Grid | LAWRENCE | 659461 | 01843 | 3.8 |  |  | Solar |  | 05_01_21W1 | 12/09/2024 | 01/03/2025 | 17 | 14 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 591813 | 01826 | 3.8 |  |  | Solar |  | 05_01_304W2 | 02/26/2024 | 03/07/2024 | 8 | 3 | 5 | 03/08/2024 | 03/08/2024 | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 | 02/26/2024 | 5/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | SPENCER | 656358 | 01562 | 487.5 |  |  | Solar |  | 05_01_415L1 | 12/06/2024 | 02/12/2025 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2025 | 03/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SUTTON | 177429 | 01590 | 4980 |  |  | Solar |  | 05_01_612W1 | 02/27/2017 | 03/29/2017 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/14/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/27/2017 | 2/28/2020 | Y | STD | 771 | 10/04/2019 | 12/20/2019 | 77 | 0 | 77 |  |  | 1/30/2020 | Connected |  | N
National Grid | STURBRIDGE | 200437 | 01566 | 10 |  |  | Solar |  | 05_05_18J5 | 11/06/2018 | 02/14/2019 | 58 | 57 | 1 | 02/15/2019 | 02/15/2019 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 11/06/2018 | 12/6/2019 | Y | EXP | 275 | 06/06/2019 | 07/19/2019 | 43 | 0 | 43 |  |  | 8/6/2019 | Connected |  | N
National Grid | WINCHENDON | 648716 | 01475 | 5.76 |  |  | Solar |  | 05_12_29W2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | SOMERSET | 616866 | 02726 | 3 |  |  | Solar |  | 05_12_7W2 | 06/10/2024 |  | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 619180 | 01970 | 10 |  |  | Solar |  | 05_14_43L6 | 06/19/2024 | 07/10/2024 | 5 | 1 | 4 | 07/11/2024 | 07/11/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | REVERE | 450745 | 02151 | 6 |  |  | Solar |  | 05_14_61L1 | 08/15/2022 | 08/31/2022 | 12 | 10 | 2 | 09/01/2022 | 09/01/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2022 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 184581 | 01832 | 15.2 |  |  | Solar |  | 05_14_75L1 | 07/10/2018 | 07/12/2018 | 1 | 0 | 1 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | LAWRENCE | 659845 | 01843 | 10 |  |  | Solar |  | 05_01_21W1 | 12/11/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | DRACUT | 626207 | 01826 | 10 |  |  | Solar |  | 05_01_304W2 | 07/19/2024 | 09/17/2024 | 31 | 25 | 6 | 09/18/2024 | 09/18/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 681472 | 01524 | 12.18 |  |  | Solar |  | 05_01_415L1 | 04/01/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 94 | 75 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRAFTON | 178389 | 01519 | 15.2 |  |  | Solar |  | 05_01_612W1 | 03/01/2018 | 04/03/2018 | 11 | 11 | 0 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 291755 | 01566 | 7.6 |  |  | Solar |  | 05_05_18J5 | 05/19/2020 | 05/20/2020 | 0 | 0 | 0 | 05/21/2020 | 05/21/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 672412 | 01475 | 5.76 |  |  | Solar |  | 05_12_29W2 | 02/17/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | Y
National Grid | SOMERSET | 623418 | 02726 | 4.64 |  |  | Solar |  | 05_12_7W2 | 07/09/2024 | 07/31/2024 | 11 | 8 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 620785 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 06/26/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 10/19/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 407121 | 02151 | 7.54 |  |  | Solar |  | 05_14_61L1 | 03/24/2022 | 04/05/2022 | 9 | 7 | 2 | 04/06/2022 | 04/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 03/24/2022 | 8/20/2023 | Y | EXP | 365 | 06/08/2022 | 07/14/2022 | 37 | 0 | 37 |  |  | 9/1/2022 | Connected |  | N
National Grid | HAVERHILL | 187051 | 01832 | 9.92 |  |  | Solar |  | 05_14_75L1 | 06/04/2018 | 06/04/2018 | 8 | 0 | 8 | 06/16/2018 | 06/16/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2019 | Connected |  | N
National Grid | LAWRENCE | 661410 | 01843 | 5.76 |  |  | Solar |  | 05_01_21W1 | 12/18/2024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 638284 | 01826 | 15.2 |  |  | Solar |  | 05_01_304W2 | 09/09/2024 | 09/23/2024 | 5 | 2 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | Y
National Grid | LEICESTER | 697596 | 01524 | 15.08 |  |  | Solar |  | 05_01_415L1 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRAFTON | 190055 | 01519 | 2000 |  |  | Solar |  | 05_01_612W1 | 07/18/2018 | 09/17/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 01/03/2019 | 144 | 72 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 324590 | 01566 | 7.6 |  |  | Solar |  | 05_05_18J5 | 11/25/2020 | 11/30/2020 | 1 | 0 | 1 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 176276 | 01475 | 79 |  |  | Solar |  | 05_12_29W3 | 05/04/2015 | 05/04/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 |  | Withdrawn |  | N
National Grid | SOMERSET | 632337 | 02726 | 6 |  |  | Solar |  | 05_12_7W2 | 08/13/2024 | 08/30/2024 | 2 | 0 | 2 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | SALEM | 629859 | 01970 | 7.6 |  |  | Solar |  | 05_14_43L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 8/28/2025 | Y | EXP | 365 | 02/28/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 4/1/2025 | Connected |  | N
National Grid | REVERE | 407034 | 02151 | 9.57 |  |  | Solar |  | 05_14_61L1 | 03/24/2022 | 03/28/2022 | 2 | 1 | 1 | 03/29/2022 | 03/29/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 7/13/2023 | N | EXP | 365 | 06/08/2022 | 07/12/2022 | 35 | 0 | 35 |  |  | 7/23/2022 | Connected |  | N
National Grid | HAVERHILL | 203291 | 01832 | 3.8 |  |  | Solar |  | 05_14_75L1 | 12/19/2018 | 12/21/2018 | 1 | 0 | 1 | 12/24/2018 | 12/24/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 667337 | 01843 | 10 |  |  | Solar |  | 05_01_21W1 | 01/23/2025 | 02/14/2025 | 7 | 3 | 4 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 4/24/2026 | Y | EXP | 365 | 06/13/2025 | 06/23/2025 | 11 | 0 | 11 |  |  | 6/26/2025 | Connected |  | N
National Grid | DRACUT | 651889 | 01826 | 18.85 |  |  | Solar |  | 05_01_304W2 | 11/27/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | SPENCER | 731442 | 01562 | 11.5 |  |  | Solar |  | 05_01_415L1 | 11/13/2025 | 11/20/2025 | 5 | 4 | 1 | 11/21/2025 | 11/21/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GRAFTON | 192564 | 01560 | 4950 |  |  | Solar |  | 05_01_612W1 | 08/21/2018 | 08/27/2018 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 09/28/2018 | 69 | 3 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 467759 | 01507 | 6 |  |  | Solar |  | 05_05_18J5 | 10/14/2022 | 10/21/2022 | 6 | 5 | 1 | 10/24/2022 | 10/24/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 176604 | 01475 | 4.25 |  |  | Solar |  | 05_12_29W3 | 12/30/2015 | 12/30/2015 | 3 | 3 | 0 | 01/05/2016 | 01/05/2016 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/4/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 642706 | 02726 | 5.76 |  |  | Solar |  | 05_12_7W2 | 09/25/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 68 | 44 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | LYNN | 632034 | 01905 | 3.8 |  |  | Solar |  | 05_14_43L6 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2024 | Connected |  | N
National Grid | REVERE | 530025 | 02151 | 5.85 |  |  | Solar |  | 05_14_61L1 | 06/08/2023 | 06/28/2023 | 14 | 12 | 2 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2023 | Connected |  | N
National Grid | HAVERHILL | 317751 | 01832 | 9.6 |  |  | Solar |  | 05_14_75L1 | 10/20/2020 | 12/15/2020 | 38 | 37 | 1 | 12/16/2020 | 12/16/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 689892 | 01843 | 3.8 |  |  | Solar |  | 05_01_21W1 | 05/06/2025 | 05/20/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 663082 | 01826 | 10 |  |  | Solar |  | 05_01_304W2 | 12/30/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | SPENCER | 741796 | 01562 | 15.2 |  |  | Solar |  | 05_01_415L1 | 12/22/2025 | 12/23/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRAFTON | 205568 | 01560 | 984 |  |  | Solar |  | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 522489 | 01507 | 6 |  |  | Solar |  | 05_05_18J5 | 07/18/2023 | 08/10/2023 | 18 | 15 | 3 | 08/11/2023 | 08/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 07/18/2023 | 10/5/2024 | Y | EXP | 365 | 12/07/2023 | 12/07/2023 | 1 | 0 | 1 |  |  | 12/28/2023 | Connected |  | N
National Grid | WINCHENDON | 177962 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 10/24/2017 | 10/24/2017 | 15 | 14 | 1 | 11/27/2017 | 11/27/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 643644 | 02726 | 2.61 |  |  | Solar |  | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 632339 | 01905 | 3.8 |  |  | Solar |  | 05_14_43L6 | 09/11/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 | 09/11/2024 | 10/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | REVERE | 535614 | 02151 | 3 |  |  | Solar |  | 05_14_61L1 | 07/04/2023 | 07/10/2023 | 4 | 3 | 1 | 07/11/2023 | 07/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 330115 | 01832 | 5.76 |  |  | Solar |  | 05_14_75L1 | 12/14/2020 | 02/12/2021 | 41 | 38 | 3 | 02/16/2021 | 02/16/2021 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2021 | 12/14/2020 | 9/2/2022 | Y | EXP | 365 | 05/28/2021 | 09/01/2021 | 95 | 3 | 92 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 691681 | 01843 | 11.4 |  |  | Solar |  | 05_01_21W1 | 05/14/2025 | 05/27/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 672732 | 01850 | 3.8 |  |  | Solar |  | 05_01_304W2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | SPENCER | 174213 | 01562 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 206008 | 01590 | 500 |  |  | Solar |  | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 140 | 75 | 65 |  |  | 0 | 0 | 0 | 08/05/2019 | 08/02/2019 | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176821 | 01507 | 6 |  |  | Solar |  | 05_05_18J7 | 01/14/2016 | 01/14/2016 | 2 | 2 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/6/2016 | Connected |  | N
National Grid | WINCHENDON | 189736 | 01475 | 7.6 |  |  | Solar |  | 05_12_29W3 | 07/02/2018 | 07/02/2018 | 2 | 0 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/02/2018 | 11/15/2019 | Y | EXP | 463 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | SOMERSET | 643619 | 02726 | 8.99 |  |  | Solar |  | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 12/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | LYNN | 637411 | 01905 | 5.76 |  |  | Solar |  | 05_14_43L6 | 09/03/2024 | 09/26/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/03/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | REVERE | 541415 | 02151 | 11.31 |  |  | Solar |  | 05_14_61L1 | 08/14/2023 | 08/28/2023 | 11 | 10 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/14/2023 | 10/18/2024 | Y | EXP | 365 | 01/24/2024 | 02/02/2024 | 10 | 0 | 10 |  |  | 2/6/2024 | Connected |  | N
National Grid | HAVERHILL | 382184 | 01832 | 16.56 |  |  | Solar |  | 05_14_75L1 | 09/15/2021 | 09/17/2021 | 2 | 0 | 2 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | LAWRENCE | 701290 | 01843 | 15.2 |  |  | Solar |  | 05_01_21W1 | 06/26/2025 | 07/14/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | LOWELL | 678189 | 01850 | 3.8 |  |  | Solar |  | 05_01_304W2 | 03/14/2025 | 03/20/2025 | 4 | 0 | 4 | 03/21/2025 | 03/21/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | SPENCER | 174212 | 01562 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 318681 | 01560 | 0 |  |  | Other |  | 05_01_612W1 | 11/05/2020 | 12/10/2020 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2020 | 12/10/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176860 | 01508 | 7.6 |  |  | Solar |  | 05_05_18J7 | 01/20/2016 | 01/20/2016 | 3 | 3 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/25/2017 | N | EXP | 337 |  |  | 0 | 0 | 0 | 7/13/2016 | 7/13/2016 | 7/18/2016 | Connected |  | N
National Grid | WINCHENDON | 220688 | 01475 | 3 |  |  | Solar |  | 05_12_29W3 | 04/24/2019 | 04/29/2019 | 4 | 4 | 0 | 04/30/2019 | 04/30/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 656953 | 02726 | 7.6 |  |  | Solar |  | 05_12_7W2 | 11/26/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/26/2024 | 2/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LYNN | 644208 | 01905 | 5.76 |  |  | Solar |  | 05_14_43L6 | 10/01/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/01/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 549692 | 02151 | 480 |  |  | Solar |  | 05_14_61L1 | 09/01/2023 | 10/12/2023 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 383819 | 01832 | 9.8 |  |  | Solar |  | 05_14_75L1 | 10/14/2021 | 12/16/2021 | 4 | 0 | 4 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 718922 | 01843 | 18.56 |  |  | Solar |  | 05_01_21W1 | 09/14/2025 | 09/29/2025 | 10 | 5 | 5 | 09/30/2025 | 09/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 694781 | 01850 | 5.76 |  |  | Solar |  | 05_01_304W2 | 06/06/2025 | 06/13/2025 | 5 | 0 | 5 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | LEICESTER | 174211 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 325150 | 01590 | 0 |  |  | Other |  | 05_01_612W1 | 12/31/2020 | 01/06/2021 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2021 | 01/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 178512 | 01508 | 16.6 |  |  | Solar |  | 05_05_18J7 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 3/13/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 242778 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 660061 | 02726 | 10 |  |  | Solar |  | 05_12_7W2 | 12/20/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | LYNN | 646547 | 01904 | 3.8 |  |  | Solar |  | 05_14_43L6 | 10/21/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 03/15/2025 | 04/10/2025 | 27 | 0 | 27 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 587226 | 02151 | 6 |  |  | Solar |  | 05_14_61L1 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 543272 | 01835 | 160 |  |  | Solar |  | 05_14_75L1 | 08/01/2023 | 08/21/2023 | 14 | 3 | 11 | 08/22/2023 | 08/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 08/01/2023 | 12/31/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | Y
National Grid | LAWRENCE | 712833 | 01840 | 7.6 |  |  | Solar |  | 05_01_21W2 | 08/27/2025 | 09/15/2025 | 12 | 9 | 3 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 735413 | 01826 | 5.76 |  |  | Solar |  | 05_01_304W3 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 174362 | 01562 | 17 |  |  | Solar |  | 05_01_415L1 | 05/17/2012 | 05/17/2012 | 6 | 0 | 6 | 05/30/2012 | 05/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/31/2012 | N | EXP | -134 |  |  | 0 | 0 | 0 | 9/7/2012 | 9/7/2012 | 4/1/2013 | Connected |  | N
National Grid | GRAFTON | 330507 | 01560 | 15.2 |  |  | Solar |  | 05_01_612W1 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/08/2020 | 2/8/2023 | Y | EXP | 365 | 09/04/2021 | 10/21/2021 | 48 | 0 | 48 |  |  | 3/28/2022 | Connected |  | N
National Grid | CHARLTON | 221739 | 01508 | 0 |  |  | Solar |  | 05_05_18J7 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | WINCHENDON | 255456 | 01475 | 7.6 |  |  | Solar |  | 05_12_29W3 | 10/07/2019 | 10/08/2019 | 0 | 0 | 0 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2019 |  | 10/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N
National Grid | SOMERSET | 662068 | 02726 | 11.5 |  |  | Solar |  | 05_12_7W2 | 12/20/2024 | 12/30/2024 | 6 | 2 | 4 | 12/31/2024 | 12/31/2024 | 39 | 16 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 647008 | 01905 | 5.76 |  |  | Solar |  | 05_14_43L6 | 10/29/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/10/2025 | Connected |  | N
National Grid | REVERE | 597488 | 02151 | 10.075 |  |  | Solar |  | 05_14_61L1 | 03/19/2024 | 03/28/2024 | 7 | 5 | 2 | 03/29/2024 | 03/29/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 03/19/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | HAVERHILL | 543762 | 01832 | 220 |  |  | Solar |  | 05_14_75L1 | 07/31/2023 | 08/17/2023 | 13 | 4 | 9 | 08/18/2023 | 08/18/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 07/31/2023 | 12/31/2025 | Y | EXP | 119 | 06/19/2025 | 06/18/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | LAWRENCE | 720360 | 01843 | 10 |  |  | Solar |  | 05_01_21W2 | 09/19/2025 | 09/25/2025 | 4 | 1 | 3 | 09/26/2025 | 09/26/2025 | 27 | 15 | 12 | 11/21/2025 | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | LOWELL | 736690 | 01850 | 21.28 |  |  | Solar |  | 05_01_304W3 | 11/26/2025 | 12/01/2025 | 2 | 0 | 2 | 12/02/2025 | 12/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 174548 | 01507 | 1000 |  |  | Solar |  | 05_01_415L1 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 361142 | 01527 | 17.6 |  |  | Solar |  | 05_01_612W1 | 06/07/2021 | 01/07/2022 | 51 | 50 | 1 | 08/18/2021 | 08/18/2021 | 155 | 127 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 636152 | 01507 | 16.24 |  |  | Solar |  | 05_05_18J7 | 08/29/2024 | 09/05/2024 | 5 | 3 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 286083 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 05/08/2020 | 05/27/2020 | 12 | 12 | 0 | 05/28/2020 | 05/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/08/2020 | 5/26/2021 | Y | EXP | 365 | 12/05/2020 | 01/06/2021 | 32 | 0 | 32 |  |  | 1/7/2021 | Connected |  | N
National Grid | SOMERSET | 669313 | 02726 | 1.625 |  |  | Solar |  | 05_12_7W2 | 02/10/2025 | 03/19/2025 | 2 | 0 | 2 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 646952 | 01905 | 3.8 |  |  | Solar |  | 05_14_43L6 | 01/13/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 608292 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L1 | 05/02/2024 | 05/21/2024 | 3 | 0 | 3 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | HAVERHILL | 553986 | 01832 | 10 |  |  | Solar |  | 05_14_75L1 | 09/21/2023 | 10/23/2023 | 22 | 20 | 2 | 10/24/2023 | 10/24/2023 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174330 | 01843 | 14.28 |  |  | Solar |  | 05_01_21W2 | 01/17/2012 | 01/17/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2012 |  | 2/20/2012 | N | EXP | -46 |  |  | 0 | 0 | 0 | 4/30/2012 | 4/30/2012 | 7/18/2012 | Connected |  | N
National Grid | LOWELL | 173709 | 01850 | 3.8 |  |  | Solar |  | 05_01_304W3 | 04/16/2018 | 04/16/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174547 | 01507 | 1000 |  |  | Solar |  | 05_01_415L1 | 11/09/2011 | 11/09/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 427507 | 01527 | 13 |  |  | Solar |  | 05_01_612W1 | 05/13/2022 | 05/13/2022 | 0 | 0 | 0 | 05/16/2022 | 05/16/2022 | 74 | 55 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 676835 | 01507 | 22.272 |  |  | Solar |  | 05_05_18J7 | 03/10/2025 | 03/21/2025 | 10 | 6 | 4 | 03/24/2025 | 03/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WINCHENDON | 310786 | 01475 | 7.68 |  |  | Solar |  | 05_12_29W3 | 10/19/2020 | 10/20/2020 | 1 | 1 | 0 | 10/21/2020 | 10/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 | 10/19/2020 | 4/21/2022 | Y | EXP | 365 | 01/20/2021 | 03/12/2021 | 51 | 0 | 51 |  |  | 10/14/2021 | Connected |  | N
National Grid | SOMERSET | 669803 | 02726 | 3.8 |  |  | Solar |  | 05_12_7W2 | 02/04/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LYNN | 651431 | 01904 | 7.6 |  |  | Solar |  | 05_14_43L6 | 11/13/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/27/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | REVERE | 618440 | 02151 | 10 |  |  | Solar |  | 05_14_61L1 | 06/17/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 06/17/2024 | 7/23/2025 | Y | EXP | 365 | 08/09/2024 | 10/21/2024 | 74 | 0 | 74 |  |  | 10/25/2024 | Connected |  | N
National Grid | HAVERHILL | 592767 | 01832 | 10 |  |  | Solar |  | 05_14_75L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174430 | 01843 | 3000 |  |  | Solar |  | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 173360 | 01850 | 7.6 |  |  | Solar |  | 05_01_304W3 | 07/31/2018 | 08/06/2018 | 1 | 0 | 1 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/31/2018 | 8/8/2019 | Y | EXP | 365 | 04/03/2019 | 04/02/2019 | 0 | 0 | 0 |  |  | 4/18/2019 | Connected |  | N
National Grid | LEICESTER | 174737 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 441942 | 01527 | 7.54 |  |  | Solar |  | 05_01_612W1 | 07/22/2022 | 07/26/2022 | 2 | 1 | 1 | 07/27/2022 | 07/27/2022 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2022 | 07/22/2022 | 9/2/2023 | Y | EXP | 365 | 09/21/2022 | 11/01/2022 | 41 | 0 | 41 |  |  | 1/20/2023 | Connected |  | N
National Grid | CHARLTON | 717271 | 01507 | 22.8 |  |  | Solar |  | 05_05_19W72 | 09/06/2025 | 09/09/2025 | 2 | 0 | 2 | 09/10/2025 | 09/10/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WINCHENDON | 378521 | 01475 | 5.76 |  |  | Solar |  | 05_12_29W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2021 |  | 11/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | SOMERSET | 673349 | 02762 | 3.8 |  |  | Solar |  | 05_12_7W2 | 02/21/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 652555 | 01904 | 5.76 |  |  | Solar |  | 05_14_43L6 | 11/06/2024 | 12/02/2024 | 6 | 0 | 6 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 627408 | 02151 | 12.16 |  |  | Solar |  | 05_14_61L1 | 07/24/2024 | 08/01/2024 | 2 | 1 | 1 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | HAVERHILL | 617236 | 01832 | 10 |  |  | Solar |  | 05_14_75L1 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | LAWRENCE | 174428 | 01843 | 4883 |  |  | Solar |  | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2014 | 03/18/2014 | 0 | 0 | 0 | 3/14/2012 | 11/18/2011 | 6/1/2014 | Y | STD | 809 |  |  | 0 | 0 | 0 | 1/23/2015 | 1/23/2015 | 1/29/2015 | Connected |  | N
National Grid | DRACUT | 175254 | 01826 | 6.88 |  |  | Solar |  | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 147 | 0 | 147 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2014 |  | 1/30/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174736 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 474354 | 01527 | 3.8 |  |  | Solar |  | 05_01_612W1 | 11/16/2022 | 12/20/2022 | 23 | 21 | 2 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 11/16/2022 | 3/8/2024 | Y | EXP | 365 | 03/02/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 4/4/2023 | Connected |  | N
National Grid | CHARLTON | 740920 | 01508 | 11.4 |  |  | Solar |  | 05_05_19W72 | 12/19/2025 | 12/22/2025 | 1 | 0 | 1 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINCHENDON | 488328 | 01475 | 6 |  |  | Solar |  | 05_12_29W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 | 01/10/2023 | 6/13/2024 | Y | EXP | 365 | 06/09/2023 | 06/09/2023 | 1 | 0 | 1 |  |  | 7/11/2023 | Connected |  | N
National Grid | SOMERSET | 683296 | 02726 | 5.76 |  |  | Solar |  | 05_12_7W2 | 04/07/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/07/2025 | 8/1/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 12/2/2025 | Connected |  | N
National Grid | LYNN | 652542 | 01905 | 4.35 |  |  | Solar |  | 05_14_43L6 | 11/06/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | REVERE | 632220 | 02151 | 6 |  |  | Solar |  | 05_14_61L1 | 08/20/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/20/2024 | 1/18/2026 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | HAVERHILL | 627744 | 01832 | 10 |  |  | Solar |  | 05_14_75L1 | 07/25/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 | 07/25/2024 | 9/26/2025 | Y | EXP | 365 | 11/01/2024 | 11/08/2024 | 8 | 0 | 8 |  |  | 12/6/2024 | Connected |  | N
National Grid | LAWRENCE | 175244 | 01843 | 684 |  |  | Solar |  | 05_01_21W2 | 08/27/2014 | 08/27/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/06/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2015 | 08/27/2014 | 6/30/2016 | Y | STD | 422 | 02/19/2016 | 06/28/2016 | 88 | 0 | 88 | 6/22/2016 | 6/22/2016 | 6/29/2016 | Connected |  | N
National Grid | DRACUT | 175251 | 01826 | 17.2 |  |  | Solar |  | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/19/2016 | Connected |  | N
National Grid | LEICESTER | 174735 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 497546 | 01527 | 6.528 |  |  | Solar |  | 05_01_612W1 | 03/10/2023 | 03/14/2023 | 2 | 0 | 2 | 03/15/2023 | 03/15/2023 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2023 | Connected |  | N
National Grid | CHARLTON | 174604 | 01508 | 42 |  |  | Solar |  | 05_05_19W72 | 08/24/2011 | 08/24/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 3/2/2012 | N | EXP | 66 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 6/27/2012 | Connected |  | N
National Grid | WINCHENDON | 573455 | 01475 | 5.8 |  |  | Solar |  | 05_12_29W3 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/20/2023 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 11/18/2025 | 435 | 0 | 435 |  |  | 11/25/2025 | Connected |  | N
National Grid | SOMERSET | 701317 | 02726 | 10.24 |  |  | Solar |  | 05_12_7W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LYNN | 653571 | 01904 | 7.6 |  |  | Solar |  | 05_14_43L6 | 11/13/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 640683 | 02151 | 4.16 |  |  | Solar |  | 05_14_61L1 | 09/17/2024 | 10/23/2024 | 20 | 17 | 3 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | HAVERHILL | 646841 | 01832 | 3.8 |  |  | Solar |  | 05_14_75L1 | 10/29/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | LAWRENCE | 175336 | 01843 | 1000 |  |  | Solar |  | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2015 | 04/13/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/07/2016 | 12/22/2016 | 177 | 0 | 177 |  |  | 11/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175362 | 01850 | 336 |  |  | Solar |  | 05_01_304W3 | 11/14/2014 | 11/14/2014 | 4 | 1 | 3 | 11/21/2014 | 11/21/2014 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 |  | 3/31/2015 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175533 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 522629 | 01527 | 10 |  |  | Solar |  | 05_01_612W1 | 05/10/2023 | 05/15/2023 | 3 | 2 | 1 | 05/16/2023 | 05/16/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 | 05/10/2023 | 6/20/2024 | Y | EXP | 365 | 07/07/2023 | 08/08/2023 | 33 | 0 | 33 |  |  | 8/25/2023 | Connected |  | N
National Grid | CHARLTON | 175180 | 01508 | 3130 |  |  | Solar |  | 05_05_19W72 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2013 | 06/24/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2014 | 05/06/2013 | 7/7/2017 | Y | STD | 990 | 03/17/2017 | 06/30/2017 | 73 | 0 | 73 | 6/29/2017 | 6/29/2017 | 7/13/2017 | Connected |  | N
National Grid | WINCHENDON | 574706 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | DIGHTON | 704708 | 02715 | 3.8 |  |  | Solar |  | 05_12_7W2 | 07/14/2025 | 07/29/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 73 | 59 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 661414 | 01904 | 5.76 |  |  | Solar |  | 05_14_43L6 | 12/18/2024 | 01/03/2025 | 11 | 7 | 4 | 01/06/2025 | 01/06/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | REVERE | 652584 | 02151 | 3.8 |  |  | Solar |  | 05_14_61L1 | 11/14/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | HAVERHILL | 656128 | 01832 | 3.8 |  |  | Solar |  | 05_14_75L1 | 11/23/2024 | 01/27/2025 | 7 | 2 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/23/2024 | 3/18/2026 | Y | EXP | 365 | 05/16/2025 | 10/01/2025 | 139 | 0 | 139 |  |  | 6/14/2025 | Connected |  | N
National Grid | LAWRENCE | 175335 | 01843 | 800 |  |  | Solar |  | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176069 | 01850 | 6 |  |  | Solar |  | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2015 |  | 6/27/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 7/29/2016 | Connected |  | N
National Grid | LEICESTER | 175532 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 529144 | 01527 | 5.76 |  |  | Solar |  | 05_01_612W1 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 | 06/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | CHARLTON | 175398 | 01507 | 475 |  |  | Solar |  | 05_05_19W72 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 12/29/2014 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 12/31/2016 | N | STD | 520 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 585391 | 01475 | 2.03 |  |  | Solar |  | 05_12_29W3 | 01/29/2024 | 01/30/2024 | 1 | 0 | 1 | 01/31/2024 | 01/31/2024 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 653572 | 02715 | 8.125 |  |  | Solar |  | 05_12_7W3 | 11/22/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/22/2024 | 7/14/2026 | Y | EXP | 365 | 10/01/2025 | 10/29/2025 | 29 | 0 | 29 |  |  |  | Completion Documents |  | Y
National Grid | LYNN | 664963 | 01904 | 9.86 |  |  | Solar |  | 05_14_43L6 | 01/21/2025 | 02/18/2025 | 7 | 2 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/21/2025 | 3/26/2026 | Y | EXP | 365 | 06/12/2025 | 08/19/2025 | 69 | 0 | 69 |  |  | 8/22/2025 | Connected |  | N
National Grid | REVERE | 659408 | 02151 | 10 |  |  | Solar |  | 05_14_61L1 | 12/09/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 656241 | 01832 | 5.76 |  |  | Solar |  | 05_14_75L1 | 11/22/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | LAWRENCE | 175334 | 01843 | 800 |  |  | Solar |  | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176101 | 01850 | 7.6 |  |  | Solar |  | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 4/19/2016 | Connected |  | N
National Grid | LEICESTER | 175531 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 640886 | 01527 | 34.6 |  |  | Solar |  | 05_01_612W1 | 09/18/2024 | 10/22/2024 | 23 | 17 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 175613 | 01507 | 258 |  |  | Solar |  | 05_05_19W72 | 12/16/2014 | 12/16/2014 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 588850 | 01475 | 5 |  |  | Solar |  | 05_12_29W3 | 02/23/2024 | 03/06/2024 | 9 | 8 | 1 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 6/24/2025 | Y | EXP | 365 | 07/25/2024 | 10/30/2024 | 98 | 0 | 98 |  |  | 11/14/2024 | Connected |  | N
National Grid | DIGHTON | 395249 | 02715 | 34.6 |  |  | Solar |  | 05_12_7W3 | 02/17/2022 | 03/22/2022 | 22 | 20 | 2 | 03/23/2022 | 03/23/2022 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 |  | 3/31/2024 | N | EXP | 620 |  |  | 0 | 0 | 0 |  |  | 3/25/2024 | Connected |  | N
National Grid | LYNN | 665201 | 01905 | 3.8 |  |  | Solar |  | 05_14_43L6 | 01/13/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 01/13/2025 | 3/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 661281 | 02151 | 10 |  |  | Solar |  | 05_14_61L1 | 12/17/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | HAVERHILL | 657304 | 01832 | 3.8 |  |  | Solar |  | 05_14_75L1 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LAWRENCE | 175641 | 01843 | 16 |  |  | Solar |  | 05_01_21W2 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 768 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 10/20/2016 | Connected |  | N
National Grid | DRACUT | 176140 | 01826 | 6.88 |  |  | Solar |  | 05_01_304W3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 6/22/2016 | Connected |  | N
National Grid | LEICESTER | 175530 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 11/05/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 645430 | 01527 | 10 |  |  | Solar |  | 05_01_612W1 | 10/08/2024 | 10/10/2024 | 2 | 0 | 2 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | CHARLTON | 175855 | 01507 | 10 |  |  | Solar |  | 05_05_19W72 | 08/03/2015 | 08/03/2015 | 4 | 4 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/9/2016 | N | EXP | 343 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 2/18/2016 | Connected |  | N
National Grid | WINCHENDON | 595104 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 04/09/2024 | 04/10/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/09/2024 | 5/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | SOMERSET | 464788 | 02726 | 8.99 |  |  | Solar |  | 05_12_7W3 | 11/15/2022 | 11/18/2022 | 3 | 0 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  | 12/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | LYNN | 695537 | 01905 | 7.6 |  |  | Solar |  | 05_14_43L6 | 06/04/2025 | 06/16/2025 | 13 | 11 | 2 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | REVERE | 666707 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L1 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | HAVERHILL | 662567 | 01832 | 10 |  |  | Solar |  | 05_14_75L1 | 12/26/2024 | 01/21/2025 | 10 | 8 | 2 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/26/2024 | 3/7/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 12/4/2025 | Connected |  | N
National Grid | LAWRENCE | 176144 | 01843 | 17.6 |  |  | Solar |  | 05_01_21W2 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 344 | 02/08/2017 | 02/22/2017 | 9 | 0 | 9 | 7/28/2015 | 7/28/2015 | 3/20/2017 | Connected |  | N
National Grid | DRACUT | 176387 | 01826 | 11.4 |  |  | Solar |  | 05_01_304W3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 260 | 0 | 260 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/6/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 175538 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 10/06/2014 | 10/06/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 650021 | 01527 | 4.06 |  |  | Solar |  | 05_01_612W1 | 10/28/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/28/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | CHARLTON | 175893 | 01507 | 7.6 |  |  | Solar |  | 05_05_19W72 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/10/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 8/31/2015 | 8/31/2015 | 1/28/2016 | Connected |  | N
National Grid | WINCHENDON | 602833 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 5/18/2025 | Y | EXP | 365 | 08/22/2024 | 02/12/2025 | 175 | 0 | 175 |  |  | 3/20/2025 | Connected |  | N
National Grid | SOMERSET | 565408 | 02726 | 25 |  |  | Solar |  | 05_12_7W3 | 11/03/2023 | 01/31/2024 | 59 | 55 | 4 | 02/01/2024 | 02/01/2024 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 704610 | 01905 | 480 |  |  | Solar |  | 05_14_43L8 | 10/17/2025 | 10/31/2025 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 | 11/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | REVERE | 696253 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L1 | 06/05/2025 | 07/08/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/05/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | HAVERHILL | 663641 | 01832 | 15.2 |  |  | Solar |  | 05_14_75L1 | 01/06/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | LAWRENCE | 176183 | 01843 | 517 |  |  | Solar |  | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176551 | 01850 | 7.6 |  |  | Solar |  | 05_01_304W3 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2015 |  | 10/13/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | LEICESTER | 175652 | 01524 | 499 |  |  | Solar |  | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 652565 | 01527 | 15.2 |  |  | Solar |  | 05_01_612W1 | 11/13/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 11/13/2024 | 1/8/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/21/2025 | Connected |  | N
National Grid | CHARLTON | 175974 | 01507 | 258 |  |  | Solar |  | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 345 | 0 | 345 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 12/31/2016 | N | EXP | 624 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 616805 | 01475 | 2.9 |  |  | Solar |  | 05_12_29W3 | 06/10/2024 |  | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 587779 | 02726 | 7.6 |  |  | Solar |  | 05_12_7W3 | 02/05/2024 | 02/13/2024 | 6 | 0 | 6 | 02/14/2024 | 02/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2024 | Connected |  | N
National Grid | LYNN | 174270 | 01904 | 229.68 |  |  | Solar |  | 05_14_43L8 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/1/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 6/26/2013 | Connected |  | N
National Grid | REVERE | 699828 | 02151 | 240 |  |  | Solar |  | 05_14_61L2 | 08/18/2025 | 09/04/2025 | 10 | 4 | 6 | 09/05/2025 | 09/05/2025 | 34 | 16 | 18 | 11/18/2025 |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | HAVERHILL | 664382 | 01835 | 3.8 |  |  | Solar |  | 05_14_75L1 | 01/08/2025 | 01/15/2025 | 2 | 0 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 176182 | 01843 | 499 |  |  | Solar |  | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176946 | 01850 | 3.8 |  |  | Solar |  | 05_01_304W3 | 12/21/2016 | 12/21/2016 | 4 | 3 | 1 | 12/28/2016 | 12/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 12/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 8/17/2017 | 8/17/2017 | 8/16/2017 | Connected |  | N
National Grid | LEICESTER | 175651 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/29/2018 | Y | STD | 851 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 685264 | 01527 | 15.2 |  |  | Solar |  | 05_01_612W1 | 05/09/2025 | 05/16/2025 | 4 | 0 | 4 | 05/19/2025 | 05/19/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176485 | 01507 | 6 |  |  | Solar |  | 05_05_19W72 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 10/03/2016 | 10/13/2016 | 7 | 0 | 7 | 2/16/2017 | 2/16/2017 | 2/16/2017 | Connected |  | N
National Grid | WINCHENDON | 622079 | 01475 | 10 |  |  | Solar |  | 05_12_29W3 | 07/02/2024 | 07/18/2024 | 9 | 8 | 1 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/02/2024 | 8/7/2025 | Y | EXP | 365 | 10/04/2024 | 02/20/2025 | 140 | 0 | 140 |  |  | 3/3/2025 | Connected |  | N
National Grid | SOMERSET | 636110 | 02726 | 8.12 |  |  | Solar |  | 05_12_7W3 | 08/28/2024 | 09/10/2024 | 1 | 0 | 1 | 09/11/2024 | 09/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LYNN | 176413 | 01905 | 92.4 |  |  | Solar |  | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 0 | 5 | 11/20/2015 | 11/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 |  | 11/18/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/3/2016 | 3/3/2016 | 3/3/2016 | Connected |  | N
National Grid | REVERE | 175960 | 02151 | 227 |  |  | Solar |  | 05_14_61L2 | 06/04/2015 | 06/04/2015 | 2 | 2 | 0 | 06/08/2015 | 06/08/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 | 06/04/2015 | 6/30/2016 | Y | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 667677 | 01835 | 3.8 |  |  | Solar |  | 05_14_75L1 | 01/24/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/24/2025 | 4/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | ANDOVER | 176181 | 01845 | 2886 |  |  | Solar |  | 05_01_21W2 | 07/06/2015 | 07/06/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/09/2016 | 10/06/2016 | 41 | 0 | 41 | 3/10/2017 | 07/06/2015 | 7/11/2018 | Y | STD | 488 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 | 3/30/2018 | 3/30/2018 | 4/5/2018 | Connected |  | N
National Grid | LOWELL | 177867 | 01850 | 7.6 |  |  | Solar |  | 05_01_304W3 | 08/09/2017 | 08/09/2017 | 4 | 4 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/15/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/29/2018 | 3/29/2018 | 3/29/2018 | Connected |  | N
National Grid | LEICESTER | 175687 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 12/23/2014 | 12/23/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/23/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILLBURY | 685677 | 01527 | 4980 |  |  | Solar |  | 05_01_612W1 | 05/06/2025 | 06/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176479 | 01507 | 288 |  |  | Solar |  | 05_05_19W72 | 05/19/2016 | 05/19/2016 | 20 | 20 | 0 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 08/16/2016 | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 | 3/3/2017 |  | 7/15/2017 | N | EXP | 134 |  |  | 0 | 0 | 0 | 6/28/2017 | 6/28/2017 | 8/3/2017 | Connected |  | N
National Grid | WINCHENDON | 630545 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 08/09/2024 | 08/21/2024 | 3 | 0 | 3 | 08/22/2024 | 08/22/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | SOMERSET | 636904 | 02726 | 5 |  |  | Solar |  | 05_12_7W3 | 08/30/2024 | 10/11/2024 | 4 | 2 | 2 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176854 | 01902 | 92.4 |  |  | Solar |  | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 5 | 0 | 11/20/2015 | 11/20/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 | 11/12/2015 | 11/18/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176749 | 02151 | 6.45 |  |  | Solar |  | 05_14_61L2 | 01/11/2016 | 01/11/2016 | 5 | 5 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/11/2016 | 1/17/2017 | Y | EXP | 343 | 07/07/2016 | 08/01/2016 | 17 | 0 | 17 | 10/21/2016 | 10/21/2016 | 10/25/2016 | Connected |  | N
National Grid | HAVERHILL | 678762 | 01835 | 10 |  |  | Solar |  | 05_14_75L1 | 03/18/2025 | 03/24/2025 | 5 | 2 | 3 | 03/25/2025 | 03/25/2025 | 194 | 174 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 176214 | 01843 | 499 |  |  | Solar |  | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2015 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 184779 | 01850 | 249.8 |  |  | Solar |  | 05_01_304W3 | 05/08/2018 | 05/08/2018 | 20 | 4 | 16 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 | 05/08/2018 | 7/16/2020 | Y | EXP | 663 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175678 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 696246 | 01527 | 17.92 |  |  | Solar |  | 05_01_612W1 | 06/19/2025 | 07/15/2025 | 16 | 13 | 3 | 07/16/2025 | 07/16/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176648 | 01507 | 7.6 |  |  | Solar |  | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/23/2017 | Y | EXP | 339 | 07/18/2016 | 07/26/2016 | 6 | 0 | 6 | 3/21/2016 | 3/21/2016 | 10/13/2016 | Connected |  | N
National Grid | WINCHENDON | 631549 | 01475 | 7.6 |  |  | Solar |  | 05_12_29W3 | 08/09/2024 | 09/12/2024 | 5 | 4 | 1 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | SOMERSET | 637079 | 02726 | 5.76 |  |  | Solar |  | 05_12_7W3 | 09/02/2024 | 09/16/2024 | 5 | 4 | 1 | 09/17/2024 | 09/17/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 185057 | 01904 | 250 |  |  | Solar |  | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 2 | 0 | 2 | 05/17/2018 | 05/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 206222 | 02151 | 3.8 |  |  | Solar |  | 05_14_61L2 | 02/11/2019 | 02/20/2019 | 5 | 0 | 5 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 684922 | 01835 | 15.76 |  |  | Solar |  | 05_14_75L1 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176213 | 01843 | 499 |  |  | Solar |  | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 186422 | 01826 | 15.2 |  |  | Solar |  | 05_01_304W3 | 05/25/2018 | 05/25/2018 | 9 | 0 | 9 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 175706 | 01524 | 1000 |  |  | Solar |  | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 704688 | 01527 | 4980 |  |  | Solar |  | 05_01_612W1 | 08/13/2025 | 08/27/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176645 | 01507 | 5 |  |  | Solar |  | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/22/2017 | Y | EXP | 338 | 06/01/2016 | 06/10/2016 | 7 | 0 | 7 | 3/21/2016 | 3/21/2016 | 1/3/2017 | Connected |  | N
National Grid | WINCHENDON | 633685 | 01475 | 10 |  |  | Solar |  | 05_12_29W3 | 08/19/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y
National Grid | SOMERSET | 647963 | 02726 | 15.2 |  |  | Solar |  | 05_12_7W3 | 10/17/2024 | 11/04/2024 | 12 | 10 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/17/2024 | 1/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 184923 | 01905 | 250 |  |  | Solar |  | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 6 | 0 | 6 | 05/18/2018 | 05/18/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | REVERE | 318215 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L2 | 10/28/2020 | 11/02/2020 | 2 | 0 | 2 | 11/03/2020 | 11/03/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 174877 | 01835 | 30 |  |  | Solar |  | 05_14_75L2 | 10/25/2011 | 10/25/2011 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2012 |  | 12/31/2012 | N | EXP | 273 |  |  | 0 | 0 | 0 | 4/16/2012 | 4/16/2012 | 4/17/2012 | Terminated |  | N
National Grid | LAWRENCE | 176211 | 01843 | 499 |  |  | Solar |  | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/09/2016 | 01/19/2017 | 110 | 0 | 110 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 200350 | 01850 | 7.6 |  |  | Solar |  | 05_01_304W3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 3/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | LEICESTER | 176018 | 01524 | 7.6 |  |  | Solar |  | 05_01_415L1 | 03/20/2015 | 03/20/2015 | 2 | 1 | 1 | 03/25/2015 | 03/25/2015 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/20/2015 | N | EXP | 115 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 706143 | 01527 | 15.2 |  |  | Solar |  | 05_01_612W1 | 07/21/2025 | 07/22/2025 | 1 | 0 | 1 | 07/23/2025 | 07/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2025 | Connected |  | N
National Grid | CHARLTON | 176684 | 01507 | 6 |  |  | Solar |  | 05_05_19W72 | 02/18/2016 | 02/18/2016 | 1 | 1 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/18/2016 | 2/24/2017 | Y | EXP | 340 | 07/18/2016 | 08/05/2016 | 14 | 0 | 14 | 12/29/2016 | 12/29/2016 | 1/4/2017 | Connected |  | N
National Grid | WINCHENDON | 655348 | 01475 | 6.72 |  |  | Solar |  | 05_12_29W3 | 11/19/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | SOMERSET | 649136 | 02726 | 7.6 |  |  | Solar |  | 05_12_7W3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 194218 | 01905 | 300 |  |  | Solar |  | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 426133 | 02151 | 4.06 |  |  | Solar |  | 05_14_61L2 | 04/28/2022 | 05/05/2022 | 5 | 2 | 3 | 05/06/2022 | 05/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 04/28/2022 | 1/3/2024 | Y | EXP | 365 | 12/22/2022 | 01/03/2023 | 13 | 0 | 13 |  |  | 1/7/2023 | Connected |  | N
National Grid | HAVERHILL | 175932 | 01835 | 4.3 |  |  | Solar |  | 05_14_75L2 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 | 08/06/2015 | 8/15/2016 | Y | EXP | 349 | 04/25/2016 | 05/17/2016 | 16 | 0 | 16 | 6/20/2016 | 6/20/2016 | 6/22/2016 | Connected |  | N
National Grid | LAWRENCE | 176285 | 01843 | 1000 |  |  | Solar |  | 05_01_21W2 | 07/09/2015 | 07/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2015 | 08/07/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/05/2017 | 10/06/2016 | 0 | 0 | 0 | 10/6/2016 | 07/09/2015 | 7/15/2016 | Y | STD | -83 | 08/07/2017 | 10/27/2017 | 57 | 0 | 57 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | LOWELL | 201445 | 01852 | 7.6 |  |  | Solar |  | 05_01_304W3 | 11/17/2018 | 12/03/2018 | 7 | 5 | 2 | 12/04/2018 | 12/04/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 10/21/2019 | N | EXP | 304 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | LEICESTER | 176323 | 01524 | 30 |  |  | Solar |  | 05_01_415L1 | 07/15/2015 | 07/15/2015 | 3 | 3 | 0 | 07/20/2015 | 07/20/2015 | 390 | 0 | 390 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 | 07/15/2015 | 7/20/2017 | Y | EXP | 713 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 7/31/2015 | 7/31/2015 |  | Withdrawn |  | N
National Grid | MILLBURY | 709014 | 01527 | 15.76 |  |  | Solar |  | 05_01_612W1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | CHARLTON | 176701 | 01507 | 12 |  |  | Solar |  | 05_05_19W72 | 10/26/2015 | 10/26/2015 | 9 | 9 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2015 |  | 10/31/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/17/2016 | Connected |  | N
National Grid | WINCHENDON | 660896 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | SOMERSET | 655714 | 02726 | 7.6 |  |  | Solar |  | 05_12_7W3 | 11/20/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2025 | Connected |  | N
National Grid | LYNN | 194214 | 01905 | 100 |  |  | Solar |  | 05_14_43L8 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 | 10/16/2018 | 10/16/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 501424 | 02151 | 10 |  |  | Solar |  | 05_14_61L2 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  | 8/21/2024 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176005 | 01835 | 10.32 |  |  | Solar |  | 05_14_75L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/19/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/8/2016 | Connected |  | N
National Grid | LAWRENCE | 177930 | 01843 | 2000 |  |  | Solar |  | 05_01_21W2 | 04/19/2017 | 04/19/2017 | 235 | 234 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/25/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 202103 | 01826 | 3.8 |  |  | Solar |  | 05_01_304W3 | 11/27/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 | 11/27/2018 | 5/14/2020 | Y | EXP | 482 | 11/23/2019 | 01/03/2020 | 41 | 0 | 41 |  |  | 2/27/2020 | Connected |  | N
National Grid | LEICESTER | 177175 | 01524 | 22.8 |  |  | Solar |  | 05_01_415L1 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2016 | 06/01/2016 | 6/6/2017 | Y | EXP | 370 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 6/1/2016 | 6/1/2016 | 5/15/2017 | Connected |  | N
National Grid | MILLBURY | 721110 | 01527 | 15.2 |  |  | Solar |  | 05_01_612W1 | 09/23/2025 | 09/29/2025 | 3 | 1 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | CHARLTON | 176835 | 01507 | 3.8 |  |  | Solar |  | 05_05_19W72 | 02/29/2016 | 02/29/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/6/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 8/9/2016 | Connected |  | N
National Grid | WINCHENDON | 660840 | 01475 | 5.76 |  |  | Solar |  | 05_12_29W3 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | DIGHTON | 669707 | 02715 | 3.8 |  |  | Solar |  | 05_12_7W3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 194210 | 01905 | 120 |  |  | Solar |  | 05_14_43L8 | 08/22/2018 | 10/15/2018 | 36 | 0 | 36 | 10/16/2018 | 10/16/2018 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 533130 | 02151 | 3.8 |  |  | Solar |  | 05_14_61L2 | 06/14/2023 | 06/15/2023 | 1 | 0 | 1 | 06/16/2023 | 06/16/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177911 | 01835 | 7.6 |  |  | Solar |  | 05_14_75L2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/30/2017 | 09/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/21/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 255873 | 01843 | 5000 |  |  | Solar |  | 05_01_21W2 | 11/20/2019 | 12/01/2019 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2019 | 12/09/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 207293 | 01826 | 10 |  |  | Solar |  | 05_01_304W3 | 01/31/2019 | 02/11/2019 | 6 | 6 | 0 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 01/31/2019 | 10/17/2019 | Y | EXP | 238 | 04/23/2019 | 05/30/2019 | 37 | 0 | 37 |  |  | 6/24/2019 | Connected |  | N
National Grid | LEICESTER | 177536 | 01524 | 19 |  |  | Solar |  | 05_01_415L1 | 09/14/2017 | 09/14/2017 | 13 | 13 | 0 | 09/28/2017 | 09/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2017 |  | 9/19/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/2/2018 | Connected |  | N
National Grid | MILLBURY | 616454 | 01527 | 4000 |  |  | Solar |  | 05_01_612W3 | 08/01/2024 | 11/25/2024 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 06/30/2025 | 146 | 127 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CHARLTON | 176896 | 01507 | 2000 |  |  | Solar |  | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 03/23/2017 |  | 254 | 0 | 254 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 662949 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W3 | 12/30/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 687889 | 02726 | 10 |  |  | Solar |  | 05_12_7W3 | 04/28/2025 | 07/31/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | Y
National Grid | LYNN | 194207 | 01904 | 180 |  |  | Solar |  | 05_14_43L8 | 08/22/2018 | 08/29/2018 | 4 | 0 | 4 | 08/30/2018 | 08/30/2018 | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 552329 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L2 | 09/01/2023 | 09/08/2023 | 5 | 2 | 3 | 09/11/2023 | 09/11/2023 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/01/2023 | 12/2/2024 | Y | EXP | 365 | 03/26/2024 | 05/15/2024 | 51 | 0 | 51 |  |  | 5/21/2024 | Connected |  | N
National Grid | HAVERHILL | 198227 | 01835 | 6 |  |  | Solar |  | 05_14_75L2 | 11/08/2018 | 12/13/2018 | 21 | 17 | 4 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 11/08/2018 | 9/16/2019 | Y | EXP | 262 | 04/05/2019 | 04/18/2019 | 13 | 0 | 13 |  |  | 9/10/2019 | Connected |  | N
National Grid | LAWRENCE | 272127 | 01843 | 4950 |  |  | Other |  | 05_01_21W2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 209039 | 01826 | 10 |  |  | Solar |  | 05_01_304W3 | 02/19/2019 | 03/29/2019 | 27 | 26 | 1 | 04/01/2019 | 04/01/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 | 02/19/2019 | 5/17/2021 | Y | EXP | 365 | 10/02/2020 | 12/08/2020 | 67 | 0 | 67 |  |  | 4/30/2021 | Connected |  | N
National Grid | LEICESTER | 178004 | 01524 | 3500 |  |  | Solar |  | 05_01_415L1 | 04/26/2017 | 04/26/2017 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 657817 | 01527 | 5.76 |  |  | Solar |  | 05_01_612W3 | 12/02/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STURBRIDGE | 176897 | 01566 | 2000 |  |  | Solar |  | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 04/04/2017 | 04/17/2017 | 9 | 0 | 9 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 664528 | 01475 | 7.6 |  |  | Solar |  | 05_12_29W3 | 01/09/2025 | 02/26/2025 | 4 | 1 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 175084 | 02715 | 144.3 |  |  | Solar |  | 05_12_7W4 | 08/14/2012 | 08/14/2012 | 5 | 0 | 5 | 08/22/2012 | 08/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2013 |  | 11/15/2012 | N | EXP | -88 |  |  | 0 | 0 | 0 | 2/11/2013 | 2/11/2013 | 8/8/2014 | Connected |  | N
National Grid | LYNN | 194203 | 01905 | 240 |  |  | Solar |  | 05_14_43L8 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 568004 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L2 | 11/30/2023 | 12/05/2023 | 3 | 0 | 3 | 12/06/2023 | 12/06/2023 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 200569 | 01835 | 7.6 |  |  | Solar |  | 05_14_75L2 | 11/06/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 293665 | 01843 | 8.4 |  |  | Solar |  | 05_01_21W2 | 06/11/2020 | 06/29/2020 | 11 | 6 | 5 | 06/30/2020 | 06/30/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | DRACUT | 219923 | 01826 | 7.6 |  |  | Solar |  | 05_01_304W3 | 06/07/2019 | 06/18/2019 | 6 | 0 | 6 | 06/19/2019 | 06/19/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/07/2019 | 9/16/2020 | Y | EXP | 365 | 05/29/2020 | 06/23/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | LEICESTER | 178003 | 01524 | 4500 |  |  | Solar |  | 05_01_415L1 | 04/26/2017 | 05/22/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2018 | 04/26/2017 | 8/24/2020 | Y | STD | 617 | 02/26/2020 | 08/24/2020 | 180 | 0 | 180 |  |  | 8/24/2020 | Connected |  | N
National Grid | MILLBURY | 715711 | 01527 | 7.6 |  |  | Solar |  | 05_01_612W3 | 08/29/2025 | 09/12/2025 | 12 | 9 | 3 | 12/08/2025 | 12/08/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 176981 | 01507 | 5.2 |  |  | Solar |  | 05_05_19W72 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 05/01/2017 | 06/08/2017 | 27 | 0 | 27 | 6/28/2017 | 6/28/2017 | 6/30/2017 | Connected |  | N
National Grid | WINCHENDON | 568043 | 01475 | 60 |  |  | Solar |  | 05_12_29W4 | 06/12/2024 | 07/09/2024 | 17 | 9 | 8 | 07/10/2024 | 07/10/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DIGHTON | 175320 | 02715 | 417.6 |  |  | Solar |  | 05_12_7W4 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | LYNN | 194190 | 01904 | 240 |  |  | Solar |  | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 579602 | 02151 | 8.7 |  |  | Solar |  | 05_14_61L2 | 01/23/2024 | 01/25/2024 | 2 | 0 | 2 | 01/26/2024 | 01/26/2024 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/13/2025 | Y | EXP | 365 | 05/16/2024 | 06/08/2024 | 24 | 0 | 24 |  |  | 6/14/2024 | Connected |  | N
National Grid | HAVERHILL | 266776 | 01835 | 6.67 |  |  | Solar |  | 05_14_75L2 | 11/22/2019 | 11/25/2019 | 0 | 0 | 0 | 11/26/2019 | 11/26/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | LAWRENCE | 336469 | 01843 | 10 |  |  | Solar |  | 05_01_21W2 | 01/22/2021 | 01/10/2022 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/22/2021 | 5/13/2023 | Y | EXP | 365 | 02/22/2022 | 04/11/2022 | 48 | 0 | 48 |  |  | 5/20/2022 | Connected |  | N
National Grid | LOWELL | 219134 | 01852 | 4.56 |  |  | Solar |  | 05_01_304W3 | 07/01/2019 | 08/02/2019 | 22 | 18 | 4 | 08/05/2019 | 08/05/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 | 07/01/2019 | 8/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | LEICESTER | 178154 | 01542 | 5000 |  |  | Solar |  | 05_01_415L1 | 12/21/2017 | 12/21/2017 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2018 | 02/21/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 724158 | 01527 | 7.6 |  |  | Solar |  | 05_01_612W3 | 11/05/2025 | 11/05/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 177262 | 01507 | 270 |  |  | Solar |  | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 0 | 0 | 0 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 | 01/20/2015 | 8/28/2017 | Y | EXP | 864 | 05/13/2016 | 06/20/2016 | 24 | 0 | 24 | 11/2/2016 | 11/2/2016 | 11/7/2016 | Connected |  | N
National Grid | WINCHENDON | 701959 | 01475 | 3.8 |  |  | Solar |  | 05_12_29W4 | 06/30/2025 | 09/23/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 61 | 48 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 178244 | 02726 | 153.2 |  |  | Solar |  | 05_12_7W4 | 02/20/2018 | 02/20/2018 | 3 | 0 | 3 | 06/14/2018 | 06/14/2018 | 18 | 14 | 4 | 04/04/2018 | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 |  | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/31/2021 | N | EXP | 984 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | SALEM | 193992 | 01970 | 650 |  |  | Solar |  | 05_14_43L8 | 09/11/2018 | 10/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 01/31/2019 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 583839 | 02151 | 4.06 |  |  | Solar |  | 05_14_61L2 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/22/2024 | 4/16/2025 | Y | EXP | 365 | 04/16/2024 | 06/18/2024 | 64 | 0 | 64 |  |  | 7/12/2024 | Connected |  | N
National Grid | HAVERHILL | 273439 | 01835 | 0 |  |  | Solar |  | 05_14_75L2 | 01/23/2020 | 01/27/2020 | 2 | 2 | 0 | 01/28/2020 | 01/28/2020 | 33 | 29 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 01/23/2020 | 1/25/2021 | Y | EXP | 365 | 06/06/2020 | 06/13/2020 | 7 | 0 | 7 |  |  | 6/15/2020 | Connected |  | N
National Grid | LAWRENCE | 384247 | 01843 | 0 |  |  | Other |  | 05_01_21W2 | 03/30/2022 | 04/27/2022 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2022 | 06/01/2022 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 265736 | 01810 | 10 |  |  | Solar |  | 05_01_304W3 | 11/20/2019 | 11/21/2019 | 0 | 0 | 0 | 11/22/2019 | 11/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 | 11/20/2019 | 7/22/2020 | Y | EXP | 365 | 03/28/2020 | 03/30/2020 | 2 | 0 | 2 |  |  | 4/6/2020 | Connected |  | N
National Grid | LEICESTER | 178297 | 01524 | 2640 |  |  | Solar |  | 05_01_415L1 | 11/15/2017 | 01/18/2018 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/13/2018 | 25 | 14 | 11 |  |  | 0 | 0 | 0 | 08/14/2018 | 11/06/2018 | 60 | 0 | 60 | 7/6/2018 | 11/15/2017 |  | Y | STD | 966 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 737858 | 01527 | 10 |  |  | Solar |  | 05_01_612W3 | 12/03/2025 | 12/10/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 177733 | 01507 | 3.8 |  |  | Solar |  | 05_05_19W72 | 03/22/2017 | 03/22/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/22/2017 | 3/27/2018 | Y | EXP | 363 | 08/09/2017 | 09/12/2017 | 23 | 0 | 23 | 10/16/2017 | 10/16/2017 | 10/18/2017 | Connected |  | N
National Grid | WINCHENDON | 706810 | 01475 | 11.5 |  |  | Solar |  | 05_12_29W4 | 08/25/2025 | 09/02/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 596446 | 02726 | 6 |  |  | Solar |  | 05_12_7W4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | LYNN | 194241 | 01904 | 120 |  |  | Solar |  | 05_14_43L8 | 08/23/2018 | 08/29/2018 | 3 | 0 | 3 | 08/30/2018 | 08/30/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 594483 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L2 | 03/05/2024 | 06/11/2024 | 7 | 5 | 2 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 | 03/05/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | HAVERHILL | 325076 | 01835 | 7.6 |  |  | Solar |  | 05_14_75L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 396703 | 01843 | 250 |  |  | Solar |  | 05_01_21W2 | 12/27/2021 |  | 215 | 208 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 330585 | 01876 | 3.12 |  |  | Solar |  | 05_01_304W3 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 178454 | 01524 | 4430 |  |  | Solar |  | 05_01_415L1 | 12/01/2017 | 12/01/2017 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/03/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174544 | 01527 | 2000 |  |  | Solar |  | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 178080 | 01507 | 2800 |  |  | Solar |  | 05_05_19W72 | 05/08/2017 | 05/08/2017 | 121 | 121 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/29/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2018 | 05/08/2017 | 12/2/2020 | Y | STD | 680 | 10/12/2019 | 09/21/2020 | 346 | 126 | 220 |  |  | 12/7/2020 | Connected |  | N
National Grid | WINCHENDON | 175227 | 01475 | 7.6 |  |  | Solar |  | 05_12_29W4 | 01/06/2015 | 01/06/2015 | 4 | 0 | 4 | 01/13/2015 | 01/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 | 01/06/2015 | 12/31/2016 | Y | EXP | 687 | 11/16/2015 | 12/29/2015 | 29 | 0 | 29 | 4/16/2015 | 4/16/2015 | 6/14/2016 | Connected |  | N
National Grid | SOMERSET | 657102 | 02726 | 3.8 |  |  | Solar |  | 05_12_7W4 | 12/02/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 195374 | 01907 | 240 |  |  | Solar |  | 05_14_43L8 | 09/12/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 616821 | 02151 | 3.8 |  |  | Solar |  | 05_14_61L2 | 06/10/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 340366 | 01835 | 15.2 |  |  | Solar |  | 05_14_75L2 | 02/03/2021 | 02/22/2021 | 12 | 11 | 1 | 02/23/2021 | 02/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | LAWRENCE | 457727 | 01843 | 5.22 |  |  | Solar |  | 05_01_21W2 | 09/27/2022 | 09/30/2022 | 3 | 0 | 3 | 10/03/2022 | 10/03/2022 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/27/2022 | 5/19/2024 | Y | EXP | 365 | 04/21/2023 | 05/19/2023 | 29 | 0 | 29 |  |  | 6/9/2023 | Connected |  | N
National Grid | LOWELL | 331259 | 01852 | 7.6 |  |  | Solar |  | 05_01_304W3 | 01/04/2021 | 01/21/2021 | 12 | 11 | 1 | 01/22/2021 | 01/22/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/04/2021 | 6/24/2023 | Y | EXP | 365 | 03/25/2022 | 06/17/2022 | 85 | 0 | 85 |  |  | 8/30/2022 | Connected |  | N
National Grid | LEICESTER | 178578 | 01542 | 4950 |  |  | Solar |  | 05_01_415L1 | 01/30/2018 | 03/14/2018 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2018 | 05/18/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 01/30/2018 | 4/22/2022 | Y | STD | 1197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174543 | 01527 | 2000 |  |  | Solar |  | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 178605 | 01507 | 10 |  |  | Solar |  | 05_05_19W72 | 12/12/2017 | 12/12/2017 | 14 | 0 | 14 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/18/2018 | N | EXP | 347 | 05/30/2018 | 06/25/2018 | 26 | 0 | 26 |  |  | 7/11/2018 | Connected |  | N
National Grid | WINCHENDON | 175298 | 01475 | 5 |  |  | Solar |  | 05_12_29W4 | 01/15/2015 | 01/15/2015 | 43 | 43 | 0 | 03/24/2015 | 03/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 5/31/2015 | N | EXP | 65 |  |  | 0 | 0 | 0 | 1/8/2016 | 1/8/2016 | 1/8/2016 | Connected |  | N
National Grid | DIGHTON | 317386 | 02715 | 10 |  |  | Solar |  | 05_12_96W1 | 01/27/2021 | 02/02/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 3/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 250814 | 01904 | 230.4 |  |  | Solar |  | 05_14_43L8 | 09/05/2019 | 10/07/2019 | 21 | 17 | 4 | 10/08/2019 | 10/08/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 4/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 621422 | 02151 | 7.6 |  |  | Solar |  | 05_14_61L2 | 06/28/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 411194 | 01835 | 9.57 |  |  | Solar |  | 05_14_75L2 | 03/21/2022 | 05/10/2022 | 36 | 35 | 1 | 05/11/2022 | 05/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 03/21/2022 | 8/26/2023 | Y | EXP | 365 | 08/09/2022 | 08/25/2022 | 17 | 0 | 17 |  |  | 9/15/2022 | Connected |  | N
National Grid | LAWRENCE | 449447 | 01843 | 16.896 |  |  | Solar |  | 05_01_304W3 | 08/04/2022 | 08/31/2022 | 19 | 18 | 1 | 09/01/2022 | 09/01/2022 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 178771 | 01876 | 1980 |  |  | Solar |  | 05_01_415L1 | 01/03/2012 | 01/03/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2012 | 09/25/2013 | 402 | 0 | 402 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2014 | 01/03/2012 | 12/31/2016 | Y | STD | 955 | 03/08/2016 | 09/02/2016 | 123 | 0 | 123 | 9/1/2016 | 9/1/2016 | 10/7/2016 | Connected |  | N
National Grid | LEICESTER | 174542 | 01524 | 2000 |  |  | Solar |  | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 190436 | 01527 | 250 |  |  | Solar |  | 05_05_19W72 | 07/11/2018 | 08/15/2018 | 5 | 0 | 5 | 08/16/2018 | 08/16/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 175646 | 01507 | 5.16 |  |  | Solar |  | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/21/2015 | Connected |  | N
National Grid | WINCHENDON | 329452 | 01475 | 7.6 |  |  | Solar |  | 05_12_96W1 | 02/26/2021 | 03/08/2021 | 5 | 0 | 5 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 196059 | 02726 | 2000 |  |  | Solar |  | 05_14_47L1 | 09/21/2018 | 11/07/2018 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2018 | 01/07/2019 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 | 09/21/2018 | 2/9/2026 | Y | STD | 553 | 12/10/2024 |  | 388 | 214 | 174 |  |  |  | Construction |  | N
National Grid | LYNN | 637450 | 01904 | 6.195 |  |  | Solar |  | 05_14_61L2 | 09/04/2024 | 12/18/2024 | 25 | 21 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | WINTHROP | 420643 | 02152 | 0 |  |  | Battery Add-On |  | 05_14_75L2 | 08/10/2022 | 08/26/2022 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2022 | 09/23/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 470048 | 01835 | 20 |  |  | Solar |  | 05_01_21W2 | 10/21/2022 | 10/27/2022 | 4 | 2 | 2 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2022 | 10/21/2022 | 6/11/2024 | Y | EXP | 365 | 05/16/2023 | 06/12/2023 | 28 | 0 | 28 |  |  | 6/21/2023 | Connected |  | N
National Grid | LAWRENCE | 427594 | 01843 | 15.66 |  |  | Solar |  | 05_01_304W3 | 06/26/2022 | 08/30/2022 | 47 | 44 | 3 | 08/31/2022 | 08/31/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 |  | 10/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 213693 | 01876 | 30 |  |  | Solar |  | 05_01_415L1 | 03/21/2019 | 05/21/2019 | 43 | 40 | 3 | 05/22/2019 | 05/22/2019 | 267 | 73 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174980 | 01524 | 1000 |  |  | Solar |  | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 239803 | 01527 | 6 |  |  | Solar |  | 05_05_19W72 | 06/26/2019 | 07/08/2019 | 7 | 3 | 4 | 07/09/2019 | 07/09/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 | 06/26/2019 | 6/26/2020 | Y | EXP | 365 | 11/07/2019 | 12/19/2019 | 42 | 0 | 42 |  |  | 1/21/2020 | Connected |  | N
National Grid | CHARLTON | 175645 | 01507 | 5.16 |  |  | Solar |  | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/21/2015 | Connected |  | N
National Grid | WINCHENDON | 330348 | 01475 | 7.6 |  |  | Solar |  | 05_12_96W1 | 12/08/2020 | 12/29/2020 | 13 | 8 | 5 | 12/30/2020 | 12/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  | 12/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | SOMERSET | 413785 | 02726 | 312.5 |  |  | Solar |  | 05_14_47L1 | 12/01/2022 | 07/12/2023 | 151 | 144 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2023 | 09/15/2023 | 46 | 28 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 12/01/2022 | 1/29/2026 | Y | STD | 308 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SALEM | 651306 | 01970 | 7.6 |  |  | Solar |  | 05_14_61L2 | 10/31/2024 | 11/12/2024 | 6 | 1 | 5 | 11/13/2024 | 11/13/2024 | 94 | 73 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 10/31/2024 | 5/20/2026 | Y | EXP | 365 | 07/24/2025 |  | 161 | 40 | 121 |  |  | 1/7/2026 | Connected |  | N
National Grid | WINTHROP | 465832 | 02152 | 14.5 |  |  | Solar |  | 05_14_75L2 | 10/20/2022 | 10/31/2022 | 7 | 6 | 1 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2022 | 10/20/2022 | 1/24/2024 | Y | EXP | 365 | 03/22/2023 | 04/05/2023 | 15 | 0 | 15 |  |  | 6/30/2023 | Connected |  | N
National Grid | HAVERHILL | 479173 | 01830 | 15.2 |  |  | Solar |  | 05_01_21W2 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 460302 | 01843 | 13.92 |  |  | Solar |  | 05_01_304W3 | 10/19/2022 | 10/24/2022 | 3 | 0 | 3 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 214422 | 01752 | 3.655 |  |  | Solar |  | 05_01_415L1 | 03/20/2019 | 06/05/2019 | 23 | 19 | 4 | 06/06/2019 | 06/06/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 9/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175008 | 01611 | 1900 |  |  | Solar |  | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/07/2011 | 11/30/2012 | Y | STD | -12 |  |  | 0 | 0 | 0 | 3/6/2014 | 3/6/2014 | 3/7/2014 | Connected |  | N
National Grid | MILLBURY | 278585 | 01527 | 7.6 |  |  | Solar |  | 05_05_19W72 | 04/14/2020 | 04/16/2020 | 2 | 2 | 0 | 04/17/2020 | 04/17/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2020 | 04/14/2020 | 4/15/2021 | Y | EXP | 365 | 06/24/2020 | 08/27/2020 | 64 | 0 | 64 |  |  | 10/5/2020 | Connected |  | Y
National Grid | CHARLTON | 176142 | 01507 | 7.75 |  |  | Solar |  | 05_12_29W4 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 398 | 0 | 398 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2015 |  | 7/6/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/27/2015 | 7/27/2015 |  | Withdrawn |  | Y
National Grid | WINCHENDON | 366061 | 01475 | 6 |  |  | Solar |  | 05_12_96W1 | 08/06/2021 | 01/03/2022 | 18 | 16 | 2 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 | 08/06/2021 | 6/8/2023 | Y | EXP | 365 | 02/11/2022 | 03/29/2022 | 47 | 0 | 47 |  |  | 8/16/2022 | Connected |  | Y
National Grid | SOMERSET | 737669 | 02726 | 13.3 |  |  | Solar |  | 05_14_47L1 | 12/02/2025 |  | 21 | 18 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALEM | 663551 | 01970 | 5.76 |  |  | Solar |  | 05_14_61L2 | 01/03/2025 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 472086 | 02152 | 15.2 |  |  | Solar |  | 05_14_75L2 | 10/28/2022 | 10/31/2022 | 1 | 0 | 1 | 11/01/2022 | 11/01/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2023 | Connected |  | Y
National Grid | NEWBURY | 485085 | 01985 | 6 |  |  | Solar |  | 05_01_21W2 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2023 | Connected |  | N
National Grid | LAWRENCE | 471063 | 01843 | 6 |  |  | Solar |  | 05_01_304W3 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 265490 | 01876 | 4950 |  |  | Other |  | 05_01_415L1 | 03/17/2020 | 04/24/2020 | 27 | 24 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/11/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 176569 | 01524 | 7.6 |  |  | Solar |  | 05_01_612W3 | 12/24/2015 | 12/24/2015 | 4 | 4 | 0 | 12/31/2015 | 12/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/29/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 9/12/2016 | Connected |  | N
National Grid | MILLBURY | 289859 | 01527 | 10 |  |  | Solar |  | 05_05_19W72 | 06/19/2020 | 07/21/2020 | 21 | 17 | 4 | 07/22/2020 | 07/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 06/19/2020 | 8/1/2021 | Y | EXP | 365 | 01/06/2021 | 02/23/2021 | 48 | 0 | 48 |  |  | 3/9/2021 | Connected |  | N
National Grid | STURBRIDGE | 176626 | 01566 | 7.6 |  |  | Solar |  | 05_12_29W4 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2016 | 04/15/2016 | 10/30/2017 | Y | EXP | 467 | 04/26/2017 | 08/02/2017 | 68 | 0 | 68 | 4/20/2017 | 4/20/2017 | 8/18/2017 | Connected |  | N
National Grid | WINCHENDON | 383495 | 01475 | 9.8 |  |  | Solar |  | 05_12_96W1 | 11/09/2021 | 12/20/2021 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 |  | 12/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2022 | Connected |  | Y
National Grid | SOMERSET | 174888 | 02726 | 630 |  |  | Solar |  | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2013 | 11/16/2012 | 6/30/2014 | Y | STD | 294 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 667365 | 01970 | 7.6 |  |  | Solar |  | 05_14_61L2 | 01/23/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 524377 | 02152 | 7.6 |  |  | Solar |  | 05_14_75L2 | 05/15/2023 | 05/18/2023 | 3 | 0 | 3 | 05/19/2023 | 05/19/2023 | 23 | 0 | 23 | 06/26/2023 | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 11/29/2024 | N | EXP | 365 | 11/04/2023 | 12/13/2023 | 40 | 0 | 40 |  |  | 12/28/2023 | Connected |  | Y
National Grid | NEWBURY | 523512 | 01985 | 4000 |  |  | Solar |  | 05_01_21W2 | 07/06/2023 | 08/28/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 10/13/2023 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 526963 | 01843 | 7.6 |  |  | Solar |  | 05_01_304W3 | 05/24/2023 | 06/12/2023 | 13 | 12 | 1 | 06/13/2023 | 06/13/2023 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 265320 | 01826 | 0 |  |  | Other |  | 05_01_415L1 | 02/14/2020 | 03/23/2020 | 25 | 22 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 03/24/2020 | 03/23/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 176754 | 01524 | 10 |  |  | Solar |  | 05_01_612W3 | 01/12/2016 | 01/12/2016 | 4 | 4 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2016 |  | 1/18/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/27/2016 | 1/27/2016 | 5/27/2016 | Connected |  | N
National Grid | MILLBURY | 300899 | 01527 | 10 |  |  | Solar |  | 05_05_19W72 | 09/25/2020 | 11/03/2020 | 26 | 24 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 09/25/2020 | 11/3/2021 | Y | EXP | 365 | 02/05/2021 | 04/06/2021 | 60 | 0 | 60 |  |  | 4/8/2021 | Connected |  | N
National Grid | CHARLTON | 176880 | 01507 | 10 |  |  | Solar |  | 05_12_29W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 349 | 03/22/2017 | 04/10/2017 | 13 | 0 | 13 | 4/20/2017 | 4/20/2017 | 4/25/2017 | Connected |  | N
National Grid | WINCHENDON | 533569 | 01475 | 0 |  |  | Solar |  | 05_12_96W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | SOMERSET | 175171 | 02726 | 800 |  |  | Solar |  | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 11/16/2012 | 12/31/2016 | Y | STD | 1237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 671905 | 01970 | 7.25 |  |  | Solar |  | 05_14_61L2 | 02/13/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | WINTHROP | 569622 | 02152 | 6 |  |  | Solar |  | 05_14_75L2 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 526652 | 01830 | 14.5 |  |  | Solar |  | 05_01_21W2 | 06/27/2023 | 06/28/2023 | 1 | 1 | 0 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 | 06/27/2023 | 7/31/2024 | Y | EXP | 365 | 09/14/2023 | 10/10/2023 | 27 | 0 | 27 |  |  | 10/16/2023 | Connected |  | N
National Grid | LAWRENCE | 536757 | 01843 | 10 |  |  | Solar |  | 05_01_304W3 | 06/27/2023 |  | 71 | 25 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 273360 | 01852 | 5000 |  |  | Other |  | 05_01_415L1 | 03/19/2020 | 03/25/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2020 | 04/07/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 177431 | 01542 | 0 |  |  | Solar |  | 05_01_612W3 | 02/27/2017 | 02/27/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 330085 | 01527 | 6 |  |  | Solar |  | 05_05_19W72 | 01/05/2021 | 01/07/2021 | 1 | 0 | 1 | 01/08/2021 | 01/08/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 | 01/05/2021 |  | Y | EXP | 365 | 05/27/2021 | 07/08/2021 | 42 | 0 | 42 |  |  | 8/6/2021 | Connected |  | N
National Grid | CHARLTON | 177620 | 01507 | 10 |  |  | Solar |  | 05_12_29W4 | 11/08/2017 | 11/08/2017 | 99 | 89 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 562542 | 01477 | 10 |  |  | Solar |  | 05_12_96W1 | 10/17/2023 | 10/20/2023 | 4 | 1 | 3 | 10/23/2023 | 10/23/2023 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | SOMERSET | 175806 | 02726 | 27.6 |  |  | Solar |  | 05_14_47L1 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2015 | 05/15/2015 | 12/31/2016 | Y | EXP | 576 | 05/10/2016 | 05/13/2016 | 3 | 0 | 3 | 7/20/2015 | 7/20/2015 | 7/15/2016 | Connected |  | N
National Grid | SALEM | 647544 | 01970 | 5.76 |  |  | Solar |  | 05_14_61L3 | 10/22/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/22/2024 | 2/25/2026 | Y | EXP | 365 | 12/20/2025 |  | 13 | 0 | 13 |  |  |  | Construction |  | Y
National Grid | WINTHROP | 569134 | 02152 | 6 |  |  | Solar |  | 05_14_75L2 | 11/10/2023 | 11/27/2023 | 10 | 4 | 6 | 11/28/2023 | 11/28/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 566580 | 01830 | 17.6 |  |  | Solar |  | 05_01_21W2 | 12/14/2023 | 12/27/2023 | 8 | 4 | 4 | 12/28/2023 | 12/28/2023 | 83 | 62 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | LAWRENCE | 593460 | 01843 | 7.6 |  |  | Solar |  | 05_01_304W3 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 03/05/2024 | 3/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | DRACUT | 308478 | 01826 | 0 |  |  | Other |  | 05_01_415L1 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 11/17/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 | 2/17/2025 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 177430 | 01524 | 1000 |  |  | Solar |  | 05_01_612W3 | 02/27/2017 | 03/23/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 02/27/2017 | 12/31/2020 | Y | STD | 1142 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 331847 | 01527 | 8.75 |  |  | Solar |  | 05_05_19W72 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 | 01/04/2021 |  | Y | EXP | 365 | 08/03/2021 | 08/17/2021 | 15 | 0 | 15 |  |  | 8/26/2021 | Connected |  | N
National Grid | CHARLTON | 184469 | 01507 | 3.8 |  |  | Solar |  | 05_12_29W4 | 06/07/2018 | 06/07/2018 | 16 | 7 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 588443 | 01475 | 22.8 |  |  | Solar |  | 05_12_96W1 | 08/05/2024 | 08/19/2024 | 10 | 9 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/05/2024 | 9/27/2025 | Y | EXP | 365 | 12/03/2024 | 01/08/2025 | 37 | 0 | 37 |  |  | 1/21/2025 | Connected |  | Y
National Grid | SOMERSET | 176540 | 02726 | 1250 |  |  | Solar |  | 05_14_47L1 | 02/10/2016 | 02/10/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/16/2016 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 |  | 2/16/2017 | N | STD | 104 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 674367 | 01904 | 10 |  |  | Solar |  | 05_14_61L3 | 03/03/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 03/03/2025 | 10/13/2026 | Y | EXP | 365 | 12/31/2025 |  | 2 | 0 | 2 |  |  |  | Construction |  | N
National Grid | WINTHROP | 585135 | 02152 | 10 |  |  | Solar |  | 05_14_75L2 | 01/26/2024 | 02/13/2024 | 12 | 11 | 1 | 02/14/2024 | 02/14/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/26/2024 | 3/1/2025 | Y | EXP | 365 | 04/23/2024 | 06/27/2024 | 66 | 0 | 66 |  |  | 6/29/2024 | Connected |  | N
National Grid | NEWBURY | 575102 | 01985 | 9.6 |  |  | Solar |  | 05_01_21W2 | 12/19/2023 | 12/20/2023 | 1 | 1 | 0 | 12/21/2023 | 12/21/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LAWRENCE | 626487 | 01843 | 7.6 |  |  | Solar |  | 05_01_304W3 | 07/22/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/22/2024 | 12/31/2025 | Y | EXP | 365 | 02/25/2025 | 10/23/2025 | 241 | 0 | 241 |  |  | 11/17/2025 | Connected |  | N
National Grid | DRACUT | 308485 | 01826 | 0 |  |  | Other |  | 05_01_415L1 | 09/08/2020 | 09/21/2020 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 177469 | 01611 | 4979.98 |  |  | Solar |  | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  |  | 0 | 0 | 0 | 12/16/2017 | 10/10/2018 | 74 | 0 | 74 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 351 | 09/14/2019 | 12/26/2019 | 103 | 0 | 103 |  |  | 12/26/2019 | Connected |  | N
National Grid | MILLBURY | 341066 | 01527 | 10 |  |  | Solar |  | 05_05_19W72 | 03/04/2021 | 03/10/2021 | 4 | 1 | 3 | 03/11/2021 | 03/11/2021 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/04/2021 |  | Y | EXP | 365 | 06/04/2021 | 06/03/2021 | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | CHARLTON | 185702 | 01507 | 7.6 |  |  | Solar |  | 05_12_29W4 | 06/13/2018 | 06/13/2018 | 30 | 25 | 5 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 | 06/13/2018 | 9/20/2019 | Y | EXP | 416 | 05/17/2019 | 05/16/2019 | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | WINCHENDON | 645728 | 01475 | 5.76 |  |  | Solar |  | 05_12_96W1 | 10/08/2024 | 10/29/2024 | 2 | 1 | 1 | 10/31/2024 | 10/31/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/08/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | SOMERSET | 177495 | 02726 | 12.2 |  |  | Solar |  | 05_14_47L1 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/13/2016 | 12/19/2017 | Y | EXP | 363 | 07/05/2017 | 07/24/2017 | 13 | 0 | 13 | 11/13/2017 | 11/13/2017 | 9/25/2017 | Connected |  | N
National Grid | SALEM | 709911 | 01970 | 7.6 |  |  | Solar |  | 05_14_61L3 | 08/05/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 40 | 24 | 16 | 11/19/2025 | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WINTHROP | 611949 | 02152 | 3.8 |  |  | Solar |  | 05_14_75L2 | 05/17/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | HAVERHILL | 643792 | 01830 | 5.76 |  |  | Solar |  | 05_01_21W2 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LAWRENCE | 628108 | 01843 | 3.8 |  |  | Solar |  | 05_01_304W3 | 07/26/2024 | 08/15/2024 | 1 | 0 | 1 | 08/16/2024 | 08/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | DRACUT | 315126 | 01826 | 0 |  |  | Other |  | 05_01_415L1 | 01/02/2021 | 02/04/2021 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2021 | 03/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 177468 | 01524 | 3150 |  |  | Solar |  | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 330 | 08/29/2019 | 12/26/2019 | 119 | 0 | 119 |  |  | 12/26/2019 | Connected |  | N
National Grid | MILLBURY | 387698 | 01527 | 10 |  |  | Solar |  | 05_05_19W72 | 10/15/2021 | 12/29/2021 | 3 | 0 | 3 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/15/2021 | 8/18/2023 | Y | EXP | 365 | 05/14/2022 | 07/13/2022 | 61 | 0 | 61 |  |  | 9/23/2022 | Connected |  | N
National Grid | CHARLTON | 187782 | 01507 | 7.6 |  |  | Solar |  | 05_12_29W4 | 06/25/2018 | 06/25/2018 | 27 | 26 | 1 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/25/2018 | 8/8/2019 | Y | EXP | 365 | 12/27/2018 | 01/03/2019 | 7 | 0 | 7 |  |  | 5/10/2019 | Connected |  | N
National Grid | WINCHENDON | 657458 | 01475 | 3.8 |  |  | Solar |  | 05_12_96W1 | 11/27/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | SOMERSET | 177505 | 02726 | 7.6 |  |  | Solar |  | 05_14_47L1 | 03/06/2017 | 03/06/2017 | 9 | 3 | 6 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/06/2017 | 3/11/2018 | Y | EXP | 355 | 07/10/2017 | 07/31/2017 | 15 | 0 | 15 | 9/8/2017 | 9/8/2017 | 9/8/2017 | Connected |  | N
National Grid | LYNN | 712782 | 01904 | 11.5 |  |  | Solar |  | 05_14_61L3 | 08/18/2025 | 01/06/2026 | 34 | 24 | 10 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINTHROP | 645072 | 02152 | 7.6 |  |  | Solar |  | 05_14_75L2 | 10/04/2024 | 10/15/2024 | 2 | 0 | 2 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 645392 | 01830 | 7.6 |  |  | Solar |  | 05_01_21W2 | 10/07/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 1/22/2026 | Y | EXP | 365 | 06/24/2025 | 07/08/2025 | 15 | 0 | 15 |  |  | 8/23/2025 | Connected |  | N
National Grid | LAWRENCE | 643329 | 01843 | 7.6 |  |  | Solar |  | 05_01_304W3 | 09/27/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | DRACUT | 365577 | 01826 | 7.6 |  |  | Solar |  | 05_01_415L1 | 06/23/2021 | 07/20/2021 | 18 | 14 | 4 | 07/21/2021 | 07/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2021 |  | 9/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | Y
National Grid | LEICESTER | 177470 | 01524 | 0 |  |  | Solar |  | 05_01_612W3 | 02/28/2017 | 02/28/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/20/2017 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 484722 | 01527 | 7.6 |  |  | Solar |  | 05_05_19W72 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 191643 | 01507 | 10 |  |  | Solar |  | 05_12_29W4 | 07/24/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 658693 | 01475 | 5.76 |  |  | Solar |  | 05_12_96W1 | 12/05/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | SOMERSET | 177942 | 02726 | 3.8 |  |  | Solar |  | 05_14_47L1 | 06/26/2017 | 06/26/2017 | 6 | 5 | 1 | 07/06/2017 | 07/06/2017 | 163 | 0 | 163 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/2/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 717411 | 01902 | 7.6 |  |  | Solar |  | 05_14_61L3 | 09/08/2025 | 09/23/2025 | 23 | 22 | 1 | 11/17/2025 | 11/17/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINTHROP | 671138 | 02152 | 10 |  |  | Solar |  | 05_14_75L2 | 02/10/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 81 | 1 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | HAVERHILL | 646994 | 01830 | 7.6 |  |  | Solar |  | 05_01_21W2 | 10/28/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 645157 | 01843 | 7.6 |  |  | Solar |  | 05_01_304W3 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | TEWKSBURY | 377511 | 01876 | 999 |  |  | Solar |  | 05_01_415L1 | 04/26/2022 | 05/18/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/19/2022 | 06/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 177920 | 01524 | 9765 |  |  | Solar |  | 05_01_612W3 | 10/23/2017 | 11/21/2017 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/19/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/23/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 565151 | 01527 | 13.262 |  |  | Solar |  | 05_05_19W72 | 11/15/2023 | 12/06/2023 | 15 | 13 | 2 | 12/07/2023 | 12/07/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 11/15/2023 | 2/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | CHARLTON | 198918 | 01507 | 7.6 |  |  | Solar |  | 05_12_29W4 | 11/05/2018 | 11/05/2018 | 0 | 0 | 0 | 11/06/2018 | 11/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 11/05/2018 | 11/5/2020 | Y | EXP | 450 | 11/15/2019 | 11/27/2019 | 12 | 0 | 12 |  |  | 1/16/2020 | Connected |  | N
National Grid | WINCHENDON | 672877 | 01475 | 5.76 |  |  | Solar |  | 05_12_96W1 | 02/19/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/19/2025 | 5/16/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | DIGHTON | 178511 | 02715 | 7.6 |  |  | Solar |  | 05_14_47L1 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/13/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 176512 | 01907 | 7.6 |  |  | Solar |  | 05_14_61L3 | 03/29/2016 | 03/29/2016 | 2 | 2 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 03/29/2016 | 8/4/2017 | Y | EXP | 472 | 08/26/2016 | 01/11/2017 | 92 | 0 | 92 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | WINTHROP | 672050 | 02152 | 7.6 |  |  | Solar |  | 05_14_75L2 | 02/13/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 662098 | 01830 | 0 |  |  | Solar |  | 05_01_21W2 | 01/09/2025 | 01/10/2025 | 1 | 0 | 1 | 01/13/2025 | 01/13/2025 | 75 | 44 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | LAWRENCE | 655225 | 01843 | 3.8 |  |  | Solar |  | 05_01_304W3 | 11/19/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | DRACUT | 409406 | 01826 | 7.6 |  |  | Solar |  | 05_01_415L1 | 10/28/2022 | 01/24/2023 | 57 | 51 | 6 | 01/25/2023 | 01/25/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 10/28/2022 | 5/29/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 8/24/2023 | Connected |  | N
National Grid | LEICESTER | 178258 | 01524 | 4999 |  |  | Solar |  | 05_01_612W3 | 04/17/2018 | 04/17/2018 | 4 | 3 | 1 |  |  | 79 | 67 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 590736 | 01527 | 3.8 |  |  | Solar |  | 05_05_19W72 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/22/2024 | 4/4/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | CHARLTON | 206834 | 01507 | 3.8 |  |  | Solar |  | 05_12_29W4 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2019 | Connected |  | N
National Grid | WINCHENDON | 644686 | 01475 | 3.8 |  |  | Solar |  | 05_12_9C1 | 10/03/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | Y
National Grid | SOMERSET | 183620 | 02726 | 15.2 |  |  | Solar |  | 05_14_47L1 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 | 06/25/2018 |  | Y | EXP | 505 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | LYNN | 177202 | 01902 | 3.8 |  |  | Solar |  | 05_14_61L3 | 02/01/2017 | 02/01/2017 | 0 | 0 | 0 | 02/17/2017 | 02/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 7/31/2018 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | Connected |  | N
National Grid | WINTHROP | 466563 | 02152 | 600 |  |  | Other |  | 05_14_75L3 | 04/27/2023 | 06/29/2023 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 04/27/2023 | 8/3/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NEWBURY | 667331 | 01985 | 10 |  |  | Solar |  | 05_01_21W2 | 01/23/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/23/2025 | 4/7/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 11/20/2025 | Connected |  | N
National Grid | LAWRENCE | 659616 | 01843 | 6.825 |  |  | Solar |  | 05_01_304W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | DRACUT | 414142 | 01826 | 0 |  |  | Solar |  | 05_01_415L1 | 02/24/2022 | 04/15/2022 | 36 | 35 | 1 | 04/19/2022 | 04/19/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 7/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 178601 | 01507 | 4998 |  |  | Solar |  | 05_01_612W3 | 04/06/2018 | 04/06/2018 | 22 | 9 | 13 |  |  | 1905 | 0 | 1905 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 609919 | 01527 | 6 |  |  | Solar |  | 05_05_19W72 | 05/09/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 59 | 50 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 224995 | 01566 | 3.8 |  |  | Solar |  | 05_12_29W4 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 178026 | 01475 | 166.75 |  |  | Solar |  | 05_12_9C2 | 08/31/2017 | 08/31/2017 | 21 | 20 | 1 | 10/03/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2017 |  | 12/16/2019 | N | EXP | 804 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | SOMERSET | 188160 | 02726 | 15.2 |  |  | Solar |  | 05_14_47L1 | 06/14/2018 | 06/14/2018 | 5 | 0 | 5 | 06/25/2018 | 06/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 177722 | 01902 | 6 |  |  | Solar |  | 05_14_61L3 | 10/04/2017 | 10/04/2017 | 19 | 17 | 2 | 11/08/2017 | 11/08/2017 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 |  | 10/9/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 727475 | 02155 | 11.5 |  |  | Solar |  | 05_14_75L3 | 10/17/2025 | 10/24/2025 | 4 | 3 | 1 | 10/27/2025 | 10/27/2025 | 45 | 24 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 670752 | 01985 | 7.6 |  |  | Solar |  | 05_01_21W2 | 02/07/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 667220 | 01843 | 0 |  |  | Battery Add-On |  | 05_01_304W3 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | DRACUT | 418661 | 01826 | 8.12 |  |  | Solar |  | 05_01_415L1 | 04/20/2022 | 04/21/2022 | 1 | 0 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 04/20/2022 | 4/12/2024 | Y | EXP | 365 | 04/06/2023 | 04/12/2023 | 7 | 0 | 7 |  |  | 5/15/2023 | Connected |  | N
National Grid | LEICESTER | 178728 | 01611 | 1000 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 643901 | 01527 | 3.8 |  |  | Solar |  | 05_05_19W72 | 10/01/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 241818 | 01507 | 10 |  |  | Solar |  | 05_12_29W4 | 07/12/2019 | 07/24/2019 | 8 | 8 | 0 | 07/25/2019 | 07/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 2/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | WINCHENDON | 225166 | 01475 | 0 |  |  | Other |  | 05_12_9C2 | 05/07/2019 | 07/02/2019 | 8 | 7 | 1 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 05/07/2019 | 2/6/2022 | Y | STD | 104 | 07/23/2021 | 07/22/2021 | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | SOMERSET | 189468 | 02726 | 2800 |  |  | Solar |  | 05_14_47L1 | 10/09/2018 | 10/15/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 11/13/2018 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 | 10/09/2018 | 11/20/2025 | Y | STD | 809 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 200394 | 01970 | 3.8 |  |  | Solar |  | 05_14_61L3 | 11/05/2018 | 12/17/2018 | 18 | 9 | 9 | 12/18/2018 | 12/18/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174327 | 02155 | 1500 |  |  | Solar |  | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 680083 | 01985 | 22.672 |  |  | Solar |  | 05_01_21W2 | 04/15/2025 | 04/25/2025 | 7 | 0 | 7 | 04/28/2025 | 04/28/2025 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | LAWRENCE | 673393 | 01843 | 5.76 |  |  | Solar |  | 05_01_304W3 | 02/25/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 429910 | 01826 | 15.2 |  |  | Solar |  | 05_01_415L1 | 05/11/2022 | 05/17/2022 | 5 | 4 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2022 | Connected |  | N
National Grid | LEICESTER | 178727 | 01524 | 1990 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 45 | 9 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 679843 | 01527 | 20 |  |  | Solar |  | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 | 03/25/2025 | 6/8/2026 | Y | EXP | 365 | 07/01/2025 | 07/29/2025 | 29 | 0 | 29 |  |  | 8/13/2025 | Connected |  | N
National Grid | STURBRIDGE | 254139 | 01566 | 10 |  |  | Solar |  | 05_12_29W4 | 10/11/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/11/2019 | 10/19/2021 | Y | EXP | 365 | 05/27/2020 | 06/12/2020 | 16 | 0 | 16 |  |  | 10/21/2020 | Connected |  | N
National Grid | WINCHENDON | 290620 | 01475 | 60 |  |  | Solar |  | 05_12_9C2 | 06/05/2020 | 08/10/2020 | 46 | 39 | 7 | 08/11/2020 | 08/11/2020 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2021 | Connected |  | N
National Grid | DIGHTON | 192934 | 02715 | 7.6 |  |  | Solar |  | 05_14_47L1 | 08/07/2018 | 08/28/2018 | 3 | 3 | 0 | 08/29/2018 | 08/29/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 202318 | 01902 | 7.6 |  |  | Solar |  | 05_14_61L3 | 11/28/2018 | 01/09/2019 | 7 | 0 | 7 | 01/10/2019 | 01/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 | 11/28/2018 | 11/28/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2020 | Connected |  | N
National Grid | MEDFORD | 174326 | 02155 | 1000 |  |  | Solar |  | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 09/04/2014 | 87 | 0 | 87 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 680372 | 01830 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 03/25/2025 | 05/22/2025 | 40 | 36 | 4 | 05/23/2025 | 05/23/2025 | 114 | 96 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 697399 | 01843 | 8.7 |  |  | Solar |  | 05_01_304W3 | 06/10/2025 | 07/02/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 435573 | 01826 | 7.6 |  |  | Solar |  | 05_01_415L1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 | 06/14/2022 | 6/22/2024 | Y | EXP | 365 | 05/10/2023 | 06/22/2023 | 44 | 0 | 44 |  |  | 6/30/2023 | Connected |  | N
National Grid | LEICESTER | 178726 | 01542 | 4990 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/14/2018 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 680454 | 01527 | 17.16 |  |  | Solar |  | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 24 | 1 | 23 | 05/07/2025 | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 7/10/2026 | N | EXP | 365 | 08/21/2025 | 09/03/2025 | 14 | 0 | 14 |  |  | 9/12/2025 | Connected |  | N
National Grid | STURBRIDGE | 290811 | 01566 | 10 |  |  | Solar |  | 05_12_29W4 | 06/26/2020 | 07/06/2020 | 5 | 0 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 409266 | 01475 | 17.11 |  |  | Solar |  | 05_12_9C3 | 03/15/2022 | 03/24/2022 | 7 | 2 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | DIGHTON | 260717 | 02715 | 20 |  |  | Solar |  | 05_14_47L1 | 10/17/2019 | 12/02/2019 | 29 | 28 | 1 | 12/03/2019 | 12/03/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 10/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 205028 | 01902 | 7.6 |  |  | Solar |  | 05_14_61L3 | 01/22/2019 | 02/06/2019 | 10 | 0 | 10 | 02/07/2019 | 02/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 01/22/2019 | 10/21/2020 | Y | EXP | 365 | 04/25/2020 | 05/26/2020 | 31 | 0 | 31 |  |  | 6/18/2020 | Connected |  | N
National Grid | MEDFORD | 174961 | 02155 | 60 |  |  | Solar |  | 05_14_75L3 | 03/05/2013 | 03/05/2013 | 4 | 0 | 4 | 03/15/2013 | 03/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2013 | 03/05/2013 | 6/14/2013 | Y | EXP | -108 | 01/30/2014 | 03/11/2014 | 27 | 0 | 27 | 4/24/2014 | 4/24/2014 | 4/24/2014 | Connected |  | N
National Grid | NEWBURY | 685002 | 01985 | 0 |  |  | Solar |  | 05_01_225W1 | 12/19/2025 |  | 8 | 6 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 299022 | 01843 | 1000 |  |  | Solar |  | 05_01_304W4 | 09/08/2020 | 10/05/2020 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 | 11/3/2025 | Y | STD | 371 | 05/09/2025 | 11/24/2025 | 223 | 0 | 223 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 466862 | 01826 | 20 |  |  | Solar |  | 05_01_415L1 | 10/10/2022 | 11/03/2022 | 18 | 17 | 1 | 11/04/2022 | 11/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 9/2/2024 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 178725 | 01740 | 1000 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 694616 | 01527 | 5.76 |  |  | Solar |  | 05_05_19W72 | 05/29/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 302539 | 01566 | 10 |  |  | Solar |  | 05_12_29W4 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | WINCHENDON | 175106 | 01475 | 20 |  |  | Solar |  | 05_12_9C4 | 04/18/2013 | 04/18/2013 | 6 | 0 | 6 | 04/30/2013 | 04/30/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2013 |  | 6/21/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 10/28/2013 | 10/28/2013 | 11/12/2013 | Connected |  | N
National Grid | SOMERSET | 263544 | 02726 | 15 |  |  | Solar |  | 05_14_47L1 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | LYNN | 206502 | 01904 | 7.6 |  |  | Solar |  | 05_14_61L3 | 03/04/2019 | 03/12/2019 | 5 | 0 | 5 | 03/13/2019 | 03/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 175207 | 02155 | 12 |  |  | Solar |  | 05_14_75L3 | 12/04/2012 | 12/04/2012 | 7 | 0 | 7 | 12/17/2012 | 12/17/2012 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 3/1/2013 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 684346 | 01985 | 7.6 |  |  | Solar |  | 05_01_225W1 | 04/10/2025 | 04/29/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 683158 | 01843 | 6.46 |  |  | Solar |  | 05_01_304W4 | 04/06/2025 | 04/25/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 484990 | 01826 | 5.51 |  |  | Solar |  | 05_01_415L1 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | LANCASTER | 178724 | 01523 | 1990 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 704382 | 01527 | 10 |  |  | Solar |  | 05_05_19W72 | 07/11/2025 | 07/28/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | CHARLTON | 313757 | 01507 | 7.83 |  |  | Solar |  | 05_12_29W4 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/20/2020 | 8/31/2022 | Y | EXP | 365 | 06/30/2021 | 07/26/2021 | 27 | 0 | 27 |  |  | 9/27/2021 | Connected |  | Y
National Grid | WINCHENDON | 177371 | 01475 | 60 |  |  | Solar |  | 05_12_9C4 | 09/06/2016 | 09/06/2016 | 5 | 5 | 0 | 09/14/2016 | 09/14/2016 | 46 | 45 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/13/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 310000 | 02726 | 7.6 |  |  | Solar |  | 05_14_47L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | LYNN | 213800 | 01904 | 6 |  |  | Solar |  | 05_14_61L3 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2019 | 04/02/2019 | 7/30/2019 | Y | EXP | 105 | 07/09/2019 | 07/16/2019 | 7 | 0 | 7 |  |  | 7/18/2019 | Connected |  | N
National Grid | MEDFORD | 175812 | 02155 | 17.63 |  |  | Solar |  | 05_14_75L3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 7/13/2015 | 7/13/2015 | 11/20/2015 | Connected |  | N
National Grid | NEWBURY | 692829 | 01985 | 999 |  |  | Solar |  | 05_01_225W1 | 11/18/2025 | 12/09/2025 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 01/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 175804 | 01843 | 990 |  |  | Solar |  | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 498882 | 01826 | 12.6 |  |  | Solar |  | 05_01_415L1 | 04/06/2023 | 04/26/2023 | 14 | 12 | 2 | 04/27/2023 | 04/27/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | BOLTON | 178723 | 01740 | 4990 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/01/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 721805 | 01527 | 17.1 |  |  | Solar |  | 05_05_19W72 | 09/25/2025 | 09/29/2025 | 2 | 0 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | STURBRIDGE | 451712 | 01566 | 10 |  |  | Solar |  | 05_12_29W4 | 12/19/2022 | 12/20/2022 | 1 | 0 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 12/19/2022 | 9/10/2024 | Y | EXP | 365 | 08/09/2023 | 08/29/2023 | 21 | 0 | 21 |  |  | 9/26/2023 | Connected |  | N
National Grid | WINCHENDON | 248807 | 01475 | 216 |  |  | Solar |  | 05_12_9C4 | 08/14/2019 | 08/30/2019 | 11 | 4 | 7 | 09/03/2019 | 09/03/2019 | 18 | 9 | 9 | 10/09/2019 | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 12/6/2019 | 08/14/2019 | 4/1/2022 | Y | EXP | 403 | 05/07/2021 | 05/14/2021 | 7 | 0 | 7 |  |  | 2/9/2022 | Connected |  | N
National Grid | SOMERSET | 320289 | 02726 | 9.8 |  |  | Solar |  | 05_14_47L1 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 2/23/2022 | Y | EXP | 365 | 05/26/2021 | 06/30/2021 | 35 | 0 | 35 |  |  | 9/24/2021 | Connected |  | N
National Grid | LYNN | 240228 | 01902 | 10 |  |  | Solar |  | 05_14_61L3 | 10/23/2019 | 10/30/2019 | 4 | 0 | 4 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 178497 | 02155 | 7.6 |  |  | Solar |  | 05_14_75L3 | 12/04/2017 | 12/04/2017 | 64 | 59 | 5 | 03/26/2018 | 03/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2018 |  | 12/10/2018 | N | EXP | 259 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 714705 | 01985 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 08/26/2025 | 09/16/2025 | 12 | 9 | 3 | 09/17/2025 | 09/17/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 176092 | 01843 | 980 |  |  | Solar |  | 05_01_304W4 | 04/06/2015 | 04/06/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2015 | 04/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 536279 | 01826 | 7.6 |  |  | Solar |  | 05_01_415L1 | 08/28/2023 | 08/30/2023 | 2 | 0 | 2 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 178722 | 01523 | 1000 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 557478 | 01527 | 2512 |  |  | Solar |  | 05_05_19W73 | 12/07/2023 | 01/18/2024 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2024 | 05/24/2024 | 89 | 70 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | STURBRIDGE | 391442 | 01566 | 3.8 |  |  | Solar |  | 05_12_29W4 | 11/24/2021 | 01/07/2022 | 13 | 9 | 4 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/24/2021 | 8/2/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2022 | Connected |  | Y
National Grid | WINCHENDON | 562890 | 01475 | 6.96 |  |  | Solar |  | 05_12_9C6 | 12/01/2023 | 12/06/2023 | 4 | 2 | 2 | 12/07/2023 | 12/07/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 12/01/2023 | 1/18/2025 | Y | EXP | 365 | 04/25/2024 | 10/07/2024 | 166 | 0 | 166 |  |  | 8/4/2024 | Connected |  | N
National Grid | SOMERSET | 340844 | 02726 | 0 |  |  | Solar |  | 05_14_47L1 | 02/12/2021 | 03/09/2021 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2021 | 03/29/2021 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 248995 | 01907 | 250 |  |  | Solar |  | 05_14_61L3 | 08/15/2019 | 08/30/2019 | 10 | 2 | 8 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2020 | Connected |  | N
National Grid | MEDFORD | 178631 | 02155 | 7.6 |  |  | Solar |  | 05_14_75L3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 3/21/2019 | N | EXP | 311 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 715560 | 01985 | 13.36 |  |  | Solar |  | 05_01_225W1 | 09/03/2025 | 09/10/2025 | 5 | 1 | 4 | 09/11/2025 | 09/11/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 176166 | 01843 | 990 |  |  | Solar |  | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 528584 | 01826 | 11.34 |  |  | Solar |  | 05_01_415L1 | 05/26/2023 | 06/01/2023 | 3 | 0 | 3 | 06/02/2023 | 06/02/2023 | 62 | 44 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | HARVARD | 178721 | 01451 | 1990 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 717276 | 01527 | 10 |  |  | Solar |  | 05_05_19W73 | 09/07/2025 | 10/08/2025 | 3 | 0 | 3 | 10/29/2025 | 10/29/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 424741 | 01507 | 220 |  |  | Solar |  | 05_12_29W4 | 05/23/2022 | 06/15/2022 | 17 | 8 | 9 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 603258 | 01475 | 200 |  |  | Solar |  | 05_12_9J1 | 05/13/2024 | 08/09/2024 | 61 | 53 | 8 |  |  | 57 | 51 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 | 05/13/2024 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | SWANSEA | 356972 | 02777 | 7.6 |  |  | Solar |  | 05_14_47L1 | 05/20/2021 | 05/21/2021 | 0 | 0 | 0 | 05/24/2021 | 05/24/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 5/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 256506 | 01970 | 7.6 |  |  | Solar |  | 05_14_61L3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 199466 | 02155 | 10 |  |  | Solar |  | 05_14_75L3 | 10/25/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 77 | 35 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 718559 | 01830 | 11.5 |  |  | Other |  | 05_01_225W1 | 09/11/2025 | 09/16/2025 | 3 | 0 | 3 | 09/17/2025 | 09/17/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 176228 | 01843 | 6 |  |  | Solar |  | 05_01_304W4 | 09/02/2015 | 09/02/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/02/2015 | 9/12/2016 | Y | EXP | 355 | 07/29/2016 | 08/06/2016 | 6 | 0 | 6 | 9/23/2015 | 9/23/2015 | 8/23/2016 | Connected |  | N
National Grid | METHUEN | 572984 | 01844 | 7.6 |  |  | Solar |  | 05_01_415L1 | 11/21/2023 | 11/30/2023 | 10 | 8 | 2 | 07/08/2024 | 07/08/2024 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 11/21/2023 | 8/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | HARVARD | 178729 | 01451 | 3900 |  |  | Solar |  | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 12/20/2017 | 1/24/2025 | Y | STD | 610 | 12/31/2021 | 05/03/2022 | 124 | 78 | 46 |  |  | 1/15/2025 | Connected |  | N
National Grid | MILLBURY | 733709 | 01527 | 3.8 |  |  | Solar |  | 05_05_19W73 | 11/13/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 429973 | 01566 | 6 |  |  | Solar |  | 05_12_29W4 | 05/27/2022 | 06/02/2022 | 3 | 1 | 2 | 06/03/2022 | 06/03/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 619859 | 01475 | 7.6 |  |  | Solar |  | 05_12_9J1 | 06/25/2024 | 06/27/2024 | 4 | 0 | 4 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 06/25/2024 | 1/30/2026 | Y | EXP | 365 | 10/01/2025 | 10/18/2025 | 18 | 0 | 18 |  |  |  | Completion Documents |  | Y
National Grid | SWANSEA | 418273 | 02777 | 500 |  |  | Solar |  | 05_14_47L1 | 09/30/2022 | 02/14/2023 | 89 | 79 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2023 | 03/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 278404 | 01970 | 5.76 |  |  | Solar |  | 05_14_61L3 | 04/21/2021 | 04/28/2021 | 4 | 0 | 4 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 12/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2022 | Connected |  | N
National Grid | SWAMPSCOTT | 211523 | 01907 | 23.4 |  |  | Solar |  | 05_14_75L3 | 03/19/2019 | 03/26/2019 | 5 | 3 | 2 | 03/27/2019 | 03/27/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 |  | 3/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2020 | Connected |  | N
National Grid | NEWBURY | 720104 | 01985 | 11.5 |  |  | Solar |  | 05_01_225W1 | 09/18/2025 | 10/16/2025 | 2 | 0 | 2 | 10/23/2025 | 10/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 176282 | 01843 | 19 |  |  | Solar |  | 05_01_304W4 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | DRACUT | 575137 | 01826 | 6 |  |  | Solar |  | 05_01_415L1 | 12/28/2023 | 01/02/2024 | 2 | 0 | 2 | 01/03/2024 | 01/03/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/28/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 184650 | 01451 | 990 |  |  | Solar |  | 05_01_612W3 | 05/11/2018 | 05/11/2018 | 1 | 0 | 1 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 06/05/2018 | 06/14/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 738982 | 01527 | 10 |  |  | Solar |  | 05_05_19W73 | 12/09/2025 | 12/11/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 435355 | 01507 | 7.6 |  |  | Solar |  | 05_12_29W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 242 | 216 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 566018 | 01475 | 200 |  |  | Solar |  | 05_12_9J1 | 11/15/2023 | 12/08/2023 | 16 | 6 | 10 | 12/11/2023 | 12/11/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 466928 | 02715 | 20 |  |  | Solar |  | 05_14_47L1 | 10/24/2022 |  | 226 | 25 | 201 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 293829 | 01904 | 3.8 |  |  | Solar |  | 05_14_61L3 | 06/08/2020 | 06/10/2020 | 1 | 0 | 1 | 06/11/2020 | 06/11/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 06/08/2020 | 11/11/2021 | Y | EXP | 365 | 11/18/2020 | 12/09/2020 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 212099 | 01907 | 10 |  |  | Solar |  | 05_14_75L3 | 04/12/2019 | 05/28/2019 | 30 | 30 | 0 | 05/29/2019 | 05/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 04/12/2019 | 2/21/2020 | Y | EXP | 259 | 12/19/2019 | 01/29/2020 | 41 | 0 | 41 |  |  | 1/31/2020 | Connected |  | N
National Grid | HAVERHILL | 721741 | 01830 | 7.6 |  |  | Solar |  | 05_01_225W1 | 10/05/2025 | 11/12/2025 | 8 | 4 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 176446 | 01843 | 72 |  |  | Solar |  | 05_01_304W4 | 05/17/2016 | 05/17/2016 | 20 | 20 | 0 | 06/15/2016 | 06/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2016 |  | 5/22/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 | 10/3/2016 | 10/3/2016 | 10/3/2016 | Connected |  | N
National Grid | DRACUT | 606685 | 01826 | 10 |  |  | Solar |  | 05_01_415L1 | 04/25/2024 | 05/01/2024 | 2 | 0 | 2 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 192506 | 01451 | 6.4 |  |  | Solar |  | 05_01_612W3 | 09/17/2018 | 12/14/2018 | 11 | 11 | 0 | 11/05/2018 | 11/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 11/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2019 | Connected |  | N
National Grid | MILLBURY | 742528 | 01527 | 3.8 |  |  | Solar |  | 05_05_19W73 | 12/30/2025 | 01/05/2026 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 448048 | 01507 | 6 |  |  | Solar |  | 05_12_29W4 | 08/15/2022 | 08/23/2022 | 7 | 6 | 1 | 08/24/2022 | 08/24/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | WINCHENDON | 496631 | 01475 | 10 |  |  | Solar |  | 05_14_47L1 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 296132 | 02777 | 5.04 |  |  | Solar |  | 05_14_61L3 | 07/02/2020 | 07/07/2020 | 2 | 0 | 2 | 07/08/2020 | 07/08/2020 | 71 | 50 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 |  | 10/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 218706 | 01970 | 7.6 |  |  | Solar |  | 05_14_75L3 | 05/16/2019 | 05/24/2019 | 5 | 0 | 5 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 721546 | 01907 | 5.76 |  |  | Solar |  | 05_01_225W1 | 09/30/2025 | 10/06/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 176464 | 01985 | 4.3 |  |  | Solar |  | 05_01_304W4 | 02/05/2016 | 02/05/2016 | 4 | 4 | 0 | 02/12/2016 | 02/12/2016 | 235 | 0 | 235 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/13/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 612835 | 01843 | 9.86 |  |  | Solar |  | 05_01_415L1 | 05/22/2024 | 06/03/2024 | 6 | 5 | 1 | 06/04/2024 | 06/04/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2024 | Connected |  | N
National Grid | DRACUT | 256917 | 01826 | 7.6 |  |  | Solar |  | 05_01_612W3 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | N
National Grid | BOLTON | 170590 | 01740 | 15.4 |  |  | Solar |  | 05_05_19W73 | 06/07/2018 | 06/07/2018 | 8 | 8 | 0 | 06/26/2018 | 06/26/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 | 06/07/2018 | 12/24/2019 | Y | EXP | 550 | 07/06/2019 | 08/01/2019 | 26 | 0 | 26 |  |  | 12/11/2019 | Connected |  | N
National Grid | MILLBURY | 520372 | 01527 | 6 |  |  | Solar |  | 05_12_29W4 | 04/28/2023 | 05/02/2023 | 3 | 1 | 2 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 625493 | 01566 | 200 |  |  | Solar |  | 05_12_9J1 | 08/06/2024 | 10/14/2024 | 48 | 38 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 543688 | 01475 | 15.2 |  |  | Solar |  | 05_14_47L1 | 07/26/2023 | 07/30/2023 | 3 | 0 | 3 | 07/31/2023 | 07/31/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2024 | Connected |  | N
National Grid | DIGHTON | 302207 | 02715 | 7.6 |  |  | Solar |  | 05_14_61L3 | 08/19/2020 | 08/26/2020 | 4 | 0 | 4 | 08/27/2020 | 08/27/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | SALEM | 223770 | 01970 | 10 |  |  | Solar |  | 05_14_75L3 | 06/05/2019 | 06/12/2019 | 4 | 0 | 4 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 | 06/05/2019 | 10/20/2021 | Y | EXP | 365 | 09/05/2020 | 09/28/2020 | 23 | 0 | 23 |  |  | 1/8/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 726260 | 01907 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 10/14/2025 | 10/16/2025 | 2 | 0 | 2 | 10/17/2025 | 10/17/2025 | 51 | 24 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 176619 | 01985 | 10 |  |  | Solar |  | 05_01_304W4 | 04/11/2016 | 04/11/2016 | 2 | 2 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/11/2016 | 10/17/2017 | Y | EXP | 539 | 06/30/2017 | 06/28/2017 | 0 | 0 | 0 | 7/14/2017 | 7/14/2017 | 7/14/2017 | Connected |  | N
National Grid | LAWRENCE | 622514 | 01843 | 3.8 |  |  | Solar |  | 05_01_415L1 | 07/03/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/03/2024 | 8/28/2025 | Y | EXP | 365 | 09/19/2024 | 05/28/2025 | 252 | 0 | 252 |  |  | 8/22/2025 | Connected |  | N
National Grid | DRACUT | 581103 | 01826 | 7.6 |  |  | Solar |  | 05_01_612W3 | 01/25/2024 | 01/29/2024 | 3 | 1 | 2 | 01/30/2024 | 01/30/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/25/2024 | 3/19/2025 | Y | EXP | 365 | 05/21/2024 | 05/20/2024 | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | BOLTON | 170569 | 01740 | 15.4 |  |  | Solar |  | 05_05_19W73 | 07/17/2018 | 08/13/2018 | 19 | 7 | 12 | 08/14/2018 | 08/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 12/24/2019 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 12/11/2019 | Connected |  | N
National Grid | MILLBURY | 536037 | 01527 | 3.8 |  |  | Solar |  | 05_12_29W4 | 08/21/2023 | 08/29/2023 | 7 | 5 | 2 | 08/30/2023 | 08/30/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | STURBRIDGE | 714650 | 01566 | 30 |  |  | Solar |  | 05_12_9J2 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WINCHENDON | 563377 | 01475 | 0 |  |  | Solar |  | 05_14_47L1 | 10/16/2023 | 10/17/2023 | 1 | 0 | 1 | 10/18/2023 | 10/18/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2024 | Connected |  | N
National Grid | DIGHTON | 317759 | 02715 | 7.6 |  |  | Solar |  | 05_14_61L3 | 10/29/2020 | 11/02/2020 | 1 | 0 | 1 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/29/2020 |  | Y | EXP | 365 | 04/17/2021 | 09/01/2021 | 136 | 3 | 133 |  |  | 9/8/2021 | Connected |  | N
National Grid | LYNN | 234804 | 01902 | 10 |  |  | Solar |  | 05_14_75L3 | 07/15/2019 | 07/16/2019 | 0 | 0 | 0 | 07/17/2019 | 07/17/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2019 | 07/15/2019 | 12/7/2020 | Y | EXP | 365 | 10/28/2020 | 11/09/2020 | 12 | 0 | 12 |  |  | 11/17/2020 | Connected |  | N
National Grid | SWAMPSCOTT | 727783 | 01907 | 5.76 |  |  | Solar |  | 05_01_225W1 | 10/27/2025 | 10/29/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 178124 | 01985 | 1000 |  |  | Solar |  | 05_01_304W4 | 05/15/2017 | 05/15/2017 | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 05/15/2017 | 6/28/2019 | Y | STD | 596 | 12/13/2018 | 05/23/2019 | 161 | 0 | 161 |  |  | 6/27/2019 | Connected |  | N
National Grid | LAWRENCE | 625725 | 01843 | 7.6 |  |  | Solar |  | 05_01_415L1 | 07/17/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 10/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | DRACUT | 663132 | 01826 | 7.25 |  |  | Solar |  | 05_01_612W3 | 12/31/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/31/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | BOLTON | 174564 | 01740 | 500 |  |  | Solar |  | 05_05_19W73 | 08/08/2011 | 08/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2012 | 08/08/2011 | 10/31/2012 | Y | STD | 229 | 08/27/2012 | 01/18/2013 | 83 | 0 | 83 | 12/5/2012 | 12/5/2012 | 12/10/2012 | Connected |  | N
National Grid | MILLBURY | 553302 | 01527 | 5 |  |  | Solar |  | 05_12_29W4 | 09/18/2023 | 10/02/2023 | 10 | 8 | 2 | 10/03/2023 | 10/03/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 289689 | 01566 | 12.96 |  |  | Solar |  | 05_12_9J2 | 04/28/2020 | 05/05/2020 | 4 | 1 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | WINCHENDON | 626005 | 01475 | 50 |  |  | Solar |  | 05_14_47L1 | 07/22/2024 | 09/27/2024 | 48 | 39 | 9 | 09/30/2024 | 09/30/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 2/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | DIGHTON | 320644 | 02715 | 3.8 |  |  | Solar |  | 05_14_61L3 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 260249 | 01904 | 9.86 |  |  | Solar |  | 05_14_75L3 | 10/20/2019 | 11/08/2019 | 14 | 9 | 5 | 11/12/2019 | 11/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 10/20/2019 | 10/20/2020 | Y | EXP | 365 | 04/21/2020 | 05/13/2020 | 22 | 0 | 22 |  |  | 8/25/2020 | Connected |  | N
National Grid | SWAMPSCOTT | 739094 | 01907 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 178699 | 01985 | 2000 |  |  | Solar |  | 05_01_304W4 | 02/07/2018 | 03/26/2018 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2018 | 04/23/2018 | 164 | 42 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 645265 | 01843 | 10 |  |  | Solar |  | 05_01_415L1 | 10/07/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | Y
National Grid | DRACUT | 690406 | 01826 | 7.6 |  |  | Solar |  | 05_01_612W3 | 05/07/2025 | 06/05/2025 | 4 | 0 | 4 | 06/25/2025 | 06/25/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174691 | 01523 | 1500 |  |  | Solar |  | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N
National Grid | MILLBURY | 560742 | 01527 | 10 |  |  | Solar |  | 05_12_29W4 | 10/11/2023 | 10/13/2023 | 3 | 2 | 1 | 10/16/2023 | 10/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 1/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | STURBRIDGE | 309022 | 01566 | 7.6 |  |  | Solar |  | 05_12_9J2 | 08/26/2020 | 08/27/2020 | 0 | 0 | 0 | 08/28/2020 | 08/28/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | WINCHENDON | 627775 | 01475 | 23 |  |  | Battery Add-On |  | 05_14_47L1 | 07/25/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | SWANSEA | 321550 | 02777 | 3.6 |  |  | Solar |  | 05_14_61L3 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/09/2020 | 12/21/2021 | Y | EXP | 365 | 08/06/2021 | 10/11/2021 | 60 | 3 | 57 |  |  | 10/21/2021 | Connected |  | N
National Grid | LYNN | 263447 | 01904 | 10 |  |  | Solar |  | 05_14_75L3 | 11/01/2019 | 11/06/2019 | 2 | 0 | 2 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 11/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2020 | Connected |  | N
National Grid | SWAMPSCOTT | 174116 | 01907 | 2000 |  |  | Solar |  | 05_01_225W1 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 186042 | 01985 | 3400 |  |  | Solar |  | 05_01_304W4 | 06/07/2018 | 07/18/2018 | 28 | 26 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/30/2018 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2019 | 06/07/2018 | 8/4/2023 | Y | STD | 488 | 04/02/2022 | 01/13/2023 | 287 | 0 | 287 | 6/7/2023 | 6/27/2023 | 7/25/2023 | Connected |  | N
National Grid | LAWRENCE | 657791 | 01843 | 11.5 |  |  | Solar |  | 05_01_415L1 | 12/02/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/02/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | METHUEN | 653327 | 01844 | 10 |  |  | Solar |  | 05_01_6J304 | 11/08/2024 | 11/27/2024 | 1 | 0 | 1 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | Y
National Grid | LANCASTER | 174690 | 01523 | 1000 |  |  | Solar |  | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/5/2012 | Connected |  | N
National Grid | GRAFTON | 572629 | 01536 | 10 |  |  | Solar |  | 05_12_29W4 | 12/01/2023 | 12/04/2023 | 1 | 0 | 1 | 12/05/2023 | 12/05/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/01/2023 | 1/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | STURBRIDGE | 380086 | 01566 | 15.2 |  |  | Solar |  | 05_12_9J2 | 09/05/2021 | 09/27/2021 | 15 | 14 | 1 | 09/28/2021 | 09/28/2021 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | WINCHENDON | 636761 | 01475 | 5.76 |  |  | Solar |  | 05_14_47L1 | 08/30/2024 | 09/16/2024 | 2 | 0 | 2 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 08/30/2024 | 11/25/2025 | Y | EXP | 365 | 02/05/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 4/29/2025 | Connected |  | N
National Grid | SWANSEA | 342956 | 02777 | 11.4 |  |  | Solar |  | 05_14_61L3 | 02/18/2021 | 02/19/2021 | 0 | 0 | 0 | 02/22/2021 | 02/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/18/2021 | 2/18/2022 | Y | EXP | 365 | 05/26/2021 | 07/08/2021 | 43 | 0 | 43 |  |  | 8/13/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 292693 | 01902 | 7.6 |  |  | Solar |  | 05_14_75L3 | 06/23/2020 | 06/24/2020 | 0 | 0 | 0 | 06/25/2020 | 06/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 | 06/23/2020 | 11/26/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | SWAMPSCOTT | 174229 | 01907 | 26 |  |  | Solar |  | 05_01_225W1 | 12/08/2011 | 12/08/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 12/30/2011 | N | EXP | -76 |  |  | 0 | 0 | 0 | 4/24/2012 | 4/24/2012 | 4/24/2012 | Connected |  | N
National Grid | HAVERHILL | 189157 | 01830 | 200 |  |  | Solar |  | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 658052 | 01843 | 20 |  |  | Solar |  | 05_01_415L1 | 12/04/2024 | 12/17/2024 | 9 | 5 | 4 | 12/18/2024 | 12/18/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | DRACUT | 728152 | 01826 | 7.98 |  |  | Solar |  | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 7 | 6 | 1 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LANCASTER | 175157 | 01523 | 2000 |  |  | Solar |  | 05_05_19W73 | 07/25/2011 | 07/25/2011 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 | 02/25/2014 | 523 | 0 | 523 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 576101 | 01527 | 6 |  |  | Solar |  | 05_12_29W4 | 12/19/2023 |  | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 405582 | 01507 | 0 |  |  | Solar |  | 05_12_9J2 | 01/09/2022 | 01/10/2022 | 1 | 0 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 646391 | 01603 | 5.76 |  |  | Solar |  | 05_14_47L1 | 10/16/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/16/2024 | 12/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | SWANSEA | 449817 | 02777 | 9.45 |  |  | Solar |  | 05_14_61L3 | 08/09/2022 | 08/12/2022 | 3 | 0 | 3 | 08/15/2022 | 08/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 | 08/09/2022 | 2/24/2024 | Y | EXP | 365 | 01/24/2023 | 02/07/2023 | 15 | 0 | 15 |  |  | 6/8/2023 | Connected |  | N
National Grid | LYNN | 377474 | 01902 | 237.5 |  |  | Solar |  | 05_14_75L3 | 08/30/2021 | 10/07/2021 | 28 | 18 | 10 | 10/08/2021 | 10/08/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 174208 | 01907 | 450 |  |  | Solar |  | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 189148 | 01985 | 200 |  |  | Solar |  | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 662122 | 01810 | 3.8 |  |  | Solar |  | 05_01_415L1 | 12/21/2024 | 01/16/2025 | 3 | 0 | 3 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 728147 | 01826 | 6.84 |  |  | Solar |  | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | LANCASTER | 175622 | 01523 | 996 |  |  | Solar |  | 05_05_19W73 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 06/02/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/05/2014 | 12/31/2016 | Y | STD | 575 | 12/01/2016 | 12/30/2016 | 20 | 0 | 20 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | MONSON | 599284 | 01057 | 0 |  |  | Battery Add-On |  | 05_12_29W4 | 03/25/2024 | 03/28/2024 | 3 | 1 | 2 | 03/29/2024 | 03/29/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 03/25/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | STURBRIDGE | 349109 | 01566 | 150 |  |  | Solar |  | 05_14_12J1 | 03/26/2021 | 04/13/2021 | 11 | 2 | 9 | 06/16/2021 | 06/16/2021 | 109 | 84 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 03/26/2021 | 7/12/2022 | Y | EXP | 147 | 03/13/2022 | 04/07/2022 | 26 | 0 | 26 |  |  | 5/26/2022 | Connected |  | N
National Grid | WORCESTER | 653693 | 01610 | 0 |  |  | Solar |  | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 116 | 91 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | DIGHTON | 450807 | 02715 | 5 |  |  | Solar |  | 05_14_61L3 | 09/27/2022 | 09/30/2022 | 4 | 1 | 3 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 09/27/2022 | 1/21/2024 | Y | EXP | 365 | 01/21/2023 | 01/20/2023 | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | SALEM | 387839 | 01970 | 50 |  |  | Solar |  | 05_14_75L3 | 11/01/2021 | 12/16/2021 | 31 | 23 | 8 | 12/17/2021 | 12/17/2021 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2022 | 11/01/2021 | 6/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | Y
National Grid | SWAMPSCOTT | 174207 | 01907 | 500 |  |  | Solar |  | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 189080 | 01985 | 200 |  |  | Solar |  | 05_01_304W4 | 06/25/2018 | 06/25/2018 | 1 | 0 | 1 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 674999 | 01843 | 20 |  |  | Solar |  | 05_01_415L1 | 03/04/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 36 | 15 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/04/2025 | 5/27/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 12/9/2025 | Connected |  | N
National Grid | METHUEN | 670775 | 01844 | 7.6 |  |  | Solar |  | 05_01_6J312 | 02/07/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2025 | Connected |  | N
National Grid | BOLTON | 175763 | 01740 | 684 |  |  | Solar |  | 05_05_19W73 | 06/05/2014 | 06/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2014 | 09/04/2014 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 607416 | 01069 | 0 |  |  | Battery Add-On |  | 05_12_29W4 | 04/29/2024 | 05/23/2024 | 18 | 14 | 4 | 05/24/2024 | 05/24/2024 | 56 | 41 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 699707 | 01566 | 40.85 |  |  | Solar |  | 05_14_13J2 | 06/19/2025 | 07/08/2025 | 12 | 10 | 2 | 07/09/2025 | 07/09/2025 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 653594 | 01610 | 7.6 |  |  | Solar |  | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 426525 | 02715 | 10 |  |  | Solar |  | 05_14_61L3 | 05/13/2022 | 05/17/2022 | 2 | 0 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 | 05/13/2022 | 10/19/2023 | Y | EXP | 365 | 08/16/2022 | 10/19/2022 | 65 | 0 | 65 |  |  | 11/2/2022 | Connected |  | N
National Grid | LYNN | 396830 | 01902 | 16 |  |  | Solar |  | 05_14_75L3 | 11/24/2021 | 12/22/2021 | 36 | 28 | 8 | 11/30/2021 | 11/30/2021 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 1/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | WESTFORD | 174205 | 01886 | 4950 |  |  | Solar |  | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 | 02/29/2012 | 1/1/2013 | Y | STD | 33 | 10/11/2013 | 12/03/2013 | 34 | 0 | 34 | 12/12/2013 | 12/12/2013 | 12/12/2013 | Connected |  | N
National Grid | NEWBURY | 224988 | 01985 | 2.4 |  |  | Solar |  | 05_01_304W4 | 06/25/2019 | 10/15/2019 | 104 | 102 | 2 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 06/25/2019 | 6/10/2021 | Y | EXP | 365 | 01/12/2021 | 02/04/2021 | 23 | 0 | 23 |  |  | 2/17/2021 | Connected |  | N
National Grid | LAWRENCE | 675967 | 01843 | 15.2 |  |  | Solar |  | 05_01_415L1 | 03/05/2025 | 03/12/2025 | 5 | 1 | 4 | 03/13/2025 | 03/13/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | METHUEN | 187209 | 01844 | 200 |  |  | Solar |  | 05_01_6J316 | 06/05/2018 | 06/05/2018 | 3 | 0 | 3 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 175926 | 01740 | 16 |  |  | Solar |  | 05_05_19W73 | 06/01/2015 | 06/01/2015 | 11 | 11 | 0 | 06/17/2015 | 06/17/2015 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 6/30/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 |  | Withdrawn |  | N
National Grid | MONSON | 615475 | 01057 | 6 |  |  | Solar |  | 05_12_29W4 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | CHARLTON | 174628 | 01507 | 44 |  |  | Solar |  | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | WORCESTER | 654681 | 01603 | 22.8 |  |  | Solar |  | 05_14_47L1 | 11/15/2024 | 01/07/2025 | 27 | 25 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | SWANSEA | 433662 | 02777 | 10 |  |  | Solar |  | 05_14_61L3 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 403697 | 01902 | 0 |  |  | Solar |  | 05_14_75L3 | 12/28/2021 | 01/05/2022 | 6 | 2 | 4 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | LOWELL | 174878 | 01854 | 1800 |  |  | Solar |  | 05_01_225W1 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 228730 | 01830 | 7.6 |  |  | Solar |  | 05_01_304W4 | 07/05/2019 | 10/03/2019 | 63 | 58 | 5 | 10/04/2019 | 10/04/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 |  | 7/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 699606 | 01843 | 5.76 |  |  | Solar |  | 05_01_415L1 | 06/20/2025 | 07/07/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 599616 | 01826 | 7.6 |  |  | Solar |  | 05_01_6J316 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 96 | 25 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 175915 | 01740 | 2000 |  |  | Solar |  | 05_05_19W73 | 03/11/2015 | 03/11/2015 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/22/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2016 | 03/11/2015 | 12/31/2017 | Y | STD | 642 | 09/19/2017 | 12/14/2017 | 54 | 0 | 54 | 12/15/2017 | 12/15/2017 | 12/19/2017 | Connected |  | N
National Grid | MILLBURY | 649937 | 01527 | 7.6 |  |  | Solar |  | 05_12_29W4 | 10/29/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | CHARLTON | 174627 | 01507 | 66 |  |  | Solar |  | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 2/10/2012 | Y | EXP | 176 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 2/10/2012 | Connected |  | N
National Grid | WORCESTER | 436374 | 01603 | 3.8 |  |  | Solar |  | 05_14_61L3 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 | 06/21/2022 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 405449 | 02777 | 7.54 |  |  | Solar |  | 05_14_75L3 | 03/01/2022 | 05/05/2022 | 47 | 45 | 2 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 03/01/2022 | 10/1/2023 | Y | EXP | 365 | 09/20/2022 | 09/28/2022 | 9 | 0 | 9 |  |  | 1/17/2023 | Connected |  | N
National Grid | LYNN | 175575 | 01904 | 22.8 |  |  | Solar |  | 05_01_225W1 | 12/09/2014 | 12/09/2014 | 4 | 3 | 1 | 12/16/2014 | 12/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2014 |  | 2/28/2015 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/9/2015 | 4/9/2015 | 9/25/2015 | Connected |  | N
National Grid | LOWELL | 242650 | 01852 | 3.8 |  |  | Solar |  | 05_01_304W4 | 07/24/2019 | 08/02/2019 | 6 | 5 | 1 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 07/24/2019 | 8/3/2020 | Y | EXP | 365 | 02/01/2020 | 02/26/2020 | 25 | 0 | 25 |  |  | 3/2/2020 | Connected |  | N
National Grid | NEWBURY | 716574 | 01985 | 21.4 |  |  | Solar |  | 05_01_415L1 | 09/10/2025 | 09/15/2025 | 3 | 0 | 3 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | LAWRENCE | 669726 | 01843 | 3.8 |  |  | Solar |  | 05_01_6J316 | 02/03/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | DRACUT | 176025 | 01826 | 980 |  |  | Solar |  | 05_05_19W73 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 653916 | 01523 | 3.8 |  |  | Solar |  | 05_12_29W4 | 11/15/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/15/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | MILLBURY | 174626 | 01527 | 15 |  |  | Solar |  | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | CHARLTON | 655659 | 01507 | 10 |  |  | Solar |  | 05_14_47L1 | 11/20/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/20/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | WORCESTER | 439483 | 01603 | 6 |  |  | Solar |  | 05_14_61L3 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/29/2022 | 4/13/2024 | Y | EXP | 365 | 03/15/2023 | 04/12/2023 | 29 | 0 | 29 |  |  | 6/12/2023 | Connected |  | N
National Grid | DIGHTON | 423047 | 02715 | 150 |  |  | Solar |  | 05_14_75L3 | 04/14/2022 | 05/24/2022 | 27 | 19 | 8 | 05/25/2022 | 05/25/2022 | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  | 11/27/2023 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  | 10/18/2023 | Connected |  | N
National Grid | LYNN | 175801 | 01904 | 1980 |  |  | Solar |  | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 12/31/2016 | Y | STD | 494 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/22/2016 | 12/22/2016 | 12/27/2016 | Connected |  | N
National Grid | LOWELL | 244233 | 01854 | 3.8 |  |  | Solar |  | 05_01_304W4 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 12/2/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | NEWBURY | 308483 | 01985 | 0 |  |  | Other |  | 05_01_415L2 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 |  | Y | STD | 707 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 710713 | 01843 | 7.6 |  |  | Solar |  | 05_01_6J316 | 08/08/2025 | 09/02/2025 | 1 | 0 | 1 | 09/17/2025 | 09/17/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176085 | 01844 | 499 |  |  | Solar |  | 05_05_19W73 | 02/04/2015 | 02/04/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 03/19/2015 | 02/14/2017 | 474 | 0 | 474 | 02/11/2015 | 03/18/2015 | 23 | 0 | 23 |  | 02/14/2017 | 474 | 0 | 474 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 655303 | 01523 | 10 |  |  | Solar |  | 05_12_29W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | Y
National Grid | MILLBURY | 174625 | 01527 | 15 |  |  | Solar |  | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | CHARLTON | 660760 | 01507 | 15.76 |  |  | Solar |  | 05_14_47L1 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | WORCESTER | 442804 | 01603 | 7.6 |  |  | Solar |  | 05_14_61L3 | 08/04/2022 | 08/05/2022 | 1 | 0 | 1 | 08/08/2022 | 08/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 454191 | 02777 | 3.48 |  |  | Solar |  | 05_14_75L3 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | LYNN | 176132 | 01902 | 495 |  |  | Solar |  | 05_01_225W1 | 04/14/2015 | 04/14/2015 | 4 | 4 | 0 | 04/22/2015 | 04/22/2015 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 286667 | 01854 | 10 |  |  | Solar |  | 05_01_304W4 | 05/18/2020 | 05/19/2020 | 0 | 0 | 0 | 05/20/2020 | 05/20/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 493328 | 01985 | 2000 |  |  | Solar |  | 05_01_415L2 | 02/21/2024 | 07/29/2024 | 109 | 52 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2024 | 08/14/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 661862 | 01843 | 5.76 |  |  | Solar |  | 05_01_6J318 | 12/19/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | DRACUT | 176362 | 01826 | 10 |  |  | Solar |  | 05_05_19W73 | 03/08/2016 | 03/08/2016 | 1 | 1 | 0 | 03/11/2016 | 03/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2016 |  | 3/15/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/15/2016 | 7/15/2016 | 7/15/2016 | Connected |  | N
National Grid | BOLTON | 663743 | 01740 | 5.76 |  |  | Solar |  | 05_12_29W4 | 01/03/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/03/2025 | 3/11/2026 | Y | EXP | 365 | 06/26/2025 | 06/28/2025 | 3 | 0 | 3 |  |  | 7/18/2025 | Connected |  | N
National Grid | MILLBURY | 556428 | 01527 | 480 |  |  | Solar |  | 05_14_13L1 | 11/22/2023 | 12/18/2023 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 02/14/2024 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 667332 | 01507 | 7.6 |  |  | Solar |  | 05_14_47L1 | 01/23/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 5/1/2026 | Y | EXP | 365 | 10/01/2025 | 11/25/2025 | 56 | 0 | 56 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 477774 | 01603 | 11.89 |  |  | Solar |  | 05_14_61L3 | 01/25/2023 | 01/26/2023 | 1 | 0 | 1 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 557324 | 02715 | 3.8 |  |  | Solar |  | 05_14_75L3 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 79 | 24 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176465 | 01904 | 99.9 |  |  | Solar |  | 05_01_225W1 | 02/05/2016 | 02/05/2016 | 0 | 0 | 0 | 02/08/2016 | 02/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 2/13/2017 | N | EXP | 370 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 11/18/2016 | Connected |  | N
National Grid | LOWELL | 440801 | 01854 | 11.89 |  |  | Solar |  | 05_01_304W4 | 07/27/2022 | 08/01/2022 | 4 | 3 | 1 | 08/02/2022 | 08/02/2022 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | NEWBURY | 174966 | 01985 | 154 |  |  | Solar |  | 05_01_6J319 | 09/03/2013 | 09/03/2013 | 9 | 0 | 9 | 09/17/2013 | 09/17/2013 | 353 | 3 | 350 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2013 |  | 8/1/2014 | N | EXP | 303 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176537 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 02/10/2016 | 02/10/2016 | 15 | 15 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 | 02/10/2016 | 2/16/2017 | Y | EXP | 321 | 08/16/2016 | 08/30/2016 | 10 | 0 | 10 | 10/24/2016 | 10/24/2016 | 10/26/2016 | Connected |  | N
National Grid | METHUEN | 675838 | 01844 | 15.2 |  |  | Solar |  | 05_12_29W4 | 03/05/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 566922 | 01523 | 250 |  |  | Solar |  | 05_14_13L1 | 12/01/2023 | 12/26/2023 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/26/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 12/01/2023 | 4/17/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | GRAFTON | 691485 | 01536 | 7.6 |  |  | Solar |  | 05_14_47L1 | 05/23/2025 | 06/13/2025 | 6 | 2 | 4 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 483461 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 12/13/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/13/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | WORCESTER | 559163 | 01603 | 250 |  |  | Solar |  | 05_14_75L3 | 11/03/2023 | 11/21/2023 | 10 | 0 | 10 |  |  | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 177345 | 02715 | 15.2 |  |  | Solar |  | 05_01_225W1 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/2/2017 | Connected |  | N
National Grid | SALEM | 505155 | 01970 | 7.6 |  |  | Solar |  | 05_01_304W4 | 03/09/2023 | 03/20/2023 | 7 | 0 | 7 | 03/21/2023 | 03/21/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | LOWELL | 665982 | 01852 | 7.6 |  |  | Solar |  | 05_01_415L2 | 01/15/2025 | 03/21/2025 | 9 | 5 | 4 | 03/24/2025 | 03/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 01/15/2025 | 7/27/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NEWBURY | 363819 | 01985 | 100 |  |  | Solar |  | 05_01_6J319 | 12/29/2021 | 10/19/2022 | 202 | 202 | 0 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/29/2021 | 12/31/2024 | Y | STD | 130 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | LAWRENCE | 176655 | 01843 | 4.25 |  |  | Solar |  | 05_05_19W73 | 04/18/2016 | 04/18/2016 | 2 | 2 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 | 04/18/2016 | 4/24/2017 | Y | EXP | 355 | 05/11/2017 | 05/31/2017 | 13 | 0 | 13 | 6/2/2017 | 6/2/2017 | 6/6/2017 | Connected |  | N
National Grid | DRACUT | 680507 | 01826 | 10 |  |  | Solar |  | 05_12_29W4 | 04/09/2025 | 04/29/2025 | 13 | 11 | 2 | 05/21/2025 | 05/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 580139 | 01523 | 200 |  |  | Solar |  | 05_14_13L1 | 01/15/2024 | 05/15/2024 | 85 | 74 | 11 | 05/16/2024 | 05/16/2024 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 4/20/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | GRAFTON | 683265 | 01536 | 4998 |  |  | Other |  | 05_14_47L2 | 10/16/2025 | 12/10/2025 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 494773 | 01507 | 6 |  |  | Solar |  | 05_14_61L3 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 10/5/2024 | Y | EXP | 365 | 08/12/2023 | 10/05/2023 | 55 | 0 | 55 |  |  | 10/12/2023 | Connected |  | N
National Grid | WORCESTER | 559958 | 01610 | 10 |  |  | Solar |  | 05_14_75L3 | 10/19/2023 | 10/26/2023 | 5 | 4 | 1 | 10/27/2023 | 10/27/2023 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 10/19/2023 | 1/7/2025 | Y | EXP | 365 | 03/06/2024 | 03/26/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 177807 | 02715 | 20 |  |  | Solar |  | 05_01_225W1 | 10/12/2017 | 10/12/2017 | 10 | 0 | 10 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | LYNN | 529519 | 01902 | 12.6 |  |  | Solar |  | 05_01_304W4 | 05/26/2023 | 05/30/2023 | 1 | 0 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2024 | Connected |  | N
National Grid | LOWELL | 740995 | 01852 | 19 |  |  | Solar |  | 05_01_415L2 | 12/18/2025 | 01/04/2026 | 5 | 2 | 3 | 01/05/2026 | 01/05/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 650619 | 01985 | 10 |  |  | Solar |  | 05_01_6J319 | 10/30/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/30/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | LAWRENCE | 177463 | 01843 | 528 |  |  | Solar |  | 05_05_19W73 | 03/01/2017 | 03/01/2017 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2017 | 05/09/2017 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 03/01/2017 | 5/7/2019 | Y | STD | 782 | 05/22/2018 | 07/30/2018 | 68 | 0 | 68 | 12/6/2018 | 2/15/2019 | 5/7/2019 | Connected |  | N
National Grid | METHUEN | 695694 | 01844 | 12.48 |  |  | Solar |  | 05_12_29W4 | 06/03/2025 | 07/14/2025 | 3 | 1 | 2 | 07/21/2025 | 07/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 178225 | 01740 | 10 |  |  | Solar |  | 05_14_14L1 | 01/03/2018 | 01/03/2018 | 38 | 32 | 6 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/10/2019 | N | EXP | 310 | 05/09/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 11/15/2018 | Connected |  | N
National Grid | GRAFTON | 733360 | 01536 | 17.28 |  |  | Solar |  | 05_14_47L2 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 518138 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 04/17/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 538861 | 01610 | 15 |  |  | Solar |  | 05_14_75L3 | 07/12/2023 | 07/17/2023 | 3 | 0 | 3 | 07/18/2023 | 07/18/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2023 | Connected |  | Y
National Grid | DIGHTON | 178028 | 02715 | 69 |  |  | Solar |  | 05_01_225W1 | 08/31/2017 | 08/31/2017 | 1 | 0 | 1 | 09/05/2017 | 09/05/2017 | 103 | 0 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/6/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 570827 | 01904 | 23 |  |  | Solar |  | 05_01_304W4 | 11/13/2023 | 11/15/2023 | 2 | 0 | 2 | 11/16/2023 | 11/16/2023 | 74 | 50 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | LOWELL | 743675 | 01852 | 20.52 |  |  | Solar |  | 05_01_415L2 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NEWBURY | 706197 | 01950 | 6.08 |  |  | Solar |  | 05_01_6J319 | 07/21/2025 | 08/07/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | LAWRENCE | 177486 | 01843 | 8 |  |  | Solar |  | 05_05_19W73 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 367 | 03/31/2017 | 04/13/2017 | 9 | 0 | 9 | 5/1/2017 | 5/1/2017 | 5/3/2017 | Connected |  | N
National Grid | DRACUT | 701437 | 01826 | 8.64 |  |  | Solar |  | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N
National Grid | BOLTON | 278152 | 01740 | 383 |  |  | Solar |  | 05_14_14L1 | 02/05/2020 | 02/13/2020 | 5 | 0 | 5 | 02/14/2020 | 02/14/2020 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRAFTON | 738893 | 01536 | 3.49 |  |  | Solar |  | 05_14_47L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 519281 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 04/26/2023 | 05/02/2023 | 4 | 0 | 4 | 05/03/2023 | 05/03/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 04/26/2023 | 8/2/2024 | Y | EXP | 365 | 09/12/2023 | 10/05/2023 | 24 | 0 | 24 |  |  | 10/16/2023 | Connected |  | N
National Grid | WORCESTER | 542582 | 01603 | 6.67 |  |  | Solar |  | 05_14_75L3 | 08/21/2023 | 09/19/2023 | 21 | 19 | 2 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 178357 | 02764 | 1980 |  |  | Solar |  | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 3/6/2019 | Y | STD | 1289 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/23/2016 | 12/23/2016 | 12/27/2016 | Connected |  | N
National Grid | LYNN | 616690 | 01904 | 7.6 |  |  | Solar |  | 05_01_304W4 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 24 | 10 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | TEWKSBURY | 174193 | 01876 | 14.19 |  |  | Solar |  | 05_01_415L2 | 03/16/2012 | 03/16/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2012 |  | 4/19/2012 | N | EXP | -53 |  |  | 0 | 0 | 0 | 6/11/2012 | 6/11/2012 | 8/3/2012 | Connected |  | N
National Grid | NEWBURY | 504930 | 01985 | 20 |  |  | Solar |  | 05_01_6J326 | 03/01/2023 | 03/21/2023 | 14 | 4 | 10 | 03/22/2023 | 03/22/2023 | 252 | 233 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177696 | 01843 | 11.4 |  |  | Solar |  | 05_05_19W73 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/26/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/12/2018 | Connected |  | N
National Grid | DRACUT | 701469 | 01826 | 7.68 |  |  | Solar |  | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 381249 | 01523 | 10 |  |  | Solar |  | 05_14_14L1 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 9/2/2023 | Y | EXP | 365 | 07/01/2022 | 08/02/2022 | 33 | 0 | 33 |  |  | 10/12/2022 | Connected |  | N
National Grid | GRAFTON | 175224 | 01536 | 19 |  |  | Solar |  | 05_14_47L2 | 01/06/2015 | 01/06/2015 | 43 | 40 | 3 | 03/11/2015 | 03/11/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 5/1/2015 | N | EXP | 50 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 543499 | 01507 | 6 |  |  | Solar |  | 05_14_61L3 | 07/28/2023 | 07/31/2023 | 1 | 0 | 1 | 08/01/2023 | 08/01/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 574265 | 01603 | 6 |  |  | Solar |  | 05_14_75L3 | 12/04/2023 | 12/06/2023 | 2 | 0 | 2 | 12/07/2023 | 12/07/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/04/2023 | 3/5/2025 | Y | EXP | 365 | 09/05/2024 | 10/17/2024 | 43 | 0 | 43 |  |  | 10/24/2024 | Connected |  | N
National Grid | DIGHTON | 253910 | 02715 | 22.8 |  |  | Solar |  | 05_01_225W1 | 09/13/2019 | 09/19/2019 | 4 | 4 | 0 | 09/20/2019 | 09/20/2019 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2019 |  | 4/15/2021 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 1/5/2021 | Connected |  | N
National Grid | LYNN | 625716 | 01902 | 210 |  |  | Solar |  | 05_01_304W4 | 07/19/2024 | 09/06/2024 | 35 | 28 | 7 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174546 | 01876 | 2000 |  |  | Solar |  | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | -160 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | NEWBURY | 596707 | 01985 | 3.8 |  |  | Solar |  | 05_01_6J326 | 03/13/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | LAWRENCE | 177823 | 01843 | 15.2 |  |  | Solar |  | 05_05_19W73 | 06/06/2017 | 06/06/2017 | 4 | 4 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 6/12/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/24/2017 | Connected |  | N
National Grid | DRACUT | 650659 | 01826 | 8.45 |  |  | Solar |  | 05_12_29W5 | 11/06/2024 | 02/24/2025 | 18 | 14 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/06/2024 | 7/29/2026 | Y | EXP | 365 | 09/25/2025 | 11/05/2025 | 42 | 0 | 42 |  |  |  | Meter Installation |  | N
National Grid | BOLTON | 469773 | 01740 | 15.2 |  |  | Solar |  | 05_14_14L1 | 10/20/2022 | 11/08/2022 | 14 | 13 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | GRAFTON | 175431 | 01536 | 354 |  |  | Solar |  | 05_14_47L2 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 | 09/29/2014 | 09/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 | 09/18/2014 | 6/1/2015 | Y | EXP | 208 | 10/07/2015 | 11/23/2015 | 31 | 0 | 31 | 11/5/2014 | 11/5/2014 | 11/23/2015 | Connected |  | N
National Grid | CHARLTON | 543146 | 01507 | 9.6 |  |  | Solar |  | 05_14_61L3 | 08/30/2023 | 09/08/2023 | 6 | 5 | 1 | 09/11/2023 | 09/11/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 08/30/2023 | 11/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2024 | Connected |  | N
National Grid | WORCESTER | 592634 | 01610 | 50 |  |  | Solar |  | 05_14_75L3 | 02/26/2024 | 04/03/2024 | 27 | 18 | 9 | 04/04/2024 | 04/04/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | DIGHTON | 262760 | 02764 | 19.2 |  |  | Solar |  | 05_01_225W1 | 10/29/2019 | 11/04/2019 | 3 | 3 | 0 | 11/05/2019 | 11/05/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2020 | Connected |  | N
National Grid | LYNN | 643375 | 01902 | 7.6 |  |  | Solar |  | 05_01_304W4 | 09/27/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/27/2024 | 1/30/2026 | Y | EXP | 365 | 02/26/2025 | 08/21/2025 | 176 | 49 | 127 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 174545 | 01876 | 2000 |  |  | Solar |  | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | -160 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | NEWBURY | 650995 | 01985 | 10 |  |  | Solar |  | 05_01_6J326 | 11/07/2024 | 11/25/2024 | 6 | 3 | 3 | 11/26/2024 | 11/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LAWRENCE | 177995 | 01843 | 20 |  |  | Solar |  | 05_05_19W73 | 10/24/2017 | 10/24/2017 | 8 | 8 | 0 | 11/16/2017 | 11/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2017 |  | 11/1/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 1/5/2018 | Connected |  | N
National Grid | DRACUT | 710848 | 01826 | 7.6 |  |  | Solar |  | 05_12_29W5 | 08/08/2025 | 09/19/2025 | 3 | 0 | 3 | 09/22/2025 | 09/22/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 668835 | 01451 | 5.76 |  |  | Solar |  | 05_14_14L1 | 01/29/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 175784 | 01527 | 14 |  |  | Solar |  | 05_14_47L2 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 8/1/2016 | N | EXP | 244 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 9/25/2017 | Connected |  | N
National Grid | CHARLTON | 546077 | 01507 | 3.8 |  |  | Solar |  | 05_14_61L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 20 | 1 | 19 | 09/15/2023 | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 12/31/2024 | N | EXP | 365 | 01/20/2024 | 01/19/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 631905 | 01610 | 14.5 |  |  | Solar |  | 05_14_75L3 | 08/14/2024 | 08/23/2024 | 7 | 4 | 3 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | DIGHTON | 277546 | 02764 | 9.6 |  |  | Solar |  | 05_01_225W1 | 01/31/2020 | 02/06/2020 | 3 | 0 | 3 | 02/07/2020 | 02/07/2020 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2020 |  | 1/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | Connected |  | N
National Grid | LYNN | 667645 | 01902 | 3.8 |  |  | Solar |  | 05_01_304W4 | 01/24/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 22 | 0 | 22 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 175243 | 01876 | 17 |  |  | Solar |  | 05_01_415L2 | 08/25/2014 | 08/25/2014 | 7 | 0 | 7 | 09/05/2014 | 09/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/25/2014 | 12/10/2014 | Y | EXP | 70 | 01/14/2015 | 01/06/2015 | 0 | 0 | 0 | 1/13/2015 | 1/13/2015 | 3/6/2015 | Connected |  | N
National Grid | NEWBURY | 661648 | 01985 | 5.76 |  |  | Solar |  | 05_01_6J326 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | LAWRENCE | 178125 | 01843 | 3.8 |  |  | Solar |  | 05_05_19W73 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | DRACUT | 177658 | 01826 | 66.6 |  |  | Solar |  | 05_12_29W5 | 11/13/2017 | 11/13/2017 | 49 | 49 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 4/19/2019 | N | EXP | 445 |  |  | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | HARVARD | 702081 | 01451 | 3.04 |  |  | Solar |  | 05_14_14L1 | 06/30/2025 | 08/05/2025 | 11 | 6 | 5 | 09/25/2025 | 09/25/2025 | 67 | 51 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 177603 | 01527 | 12 |  |  | Solar |  | 05_14_47L2 | 07/19/2017 | 07/19/2017 | 11 | 11 | 0 | 08/03/2017 | 08/03/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/24/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 566020 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 11/15/2023 | 12/05/2023 | 13 | 8 | 5 | 12/06/2023 | 12/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/15/2023 | 8/12/2025 | Y | EXP | 365 | 06/06/2024 | 09/16/2024 | 103 | 0 | 103 |  |  | 4/1/2025 | Connected |  | N
National Grid | WORCESTER | 644476 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L3 | 10/16/2024 | 11/01/2024 | 3 | 0 | 3 | 11/04/2024 | 11/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | DIGHTON | 289477 | 02715 | 12 |  |  | Solar |  | 05_01_225W1 | 05/12/2020 | 05/13/2020 | 0 | 0 | 0 | 05/14/2020 | 05/14/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2020 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 670474 | 01902 | 4999.2 |  |  | Solar |  | 05_01_304W5 | 03/20/2025 | 05/12/2025 | 37 | 27 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | TEWKSBURY | 175323 | 01876 | 630 |  |  | Solar |  | 05_01_415L2 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/19/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 656764 | 01985 | 3.8 |  |  | Solar |  | 05_01_6J342 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | LAWRENCE | 178656 | 01843 | 4875 |  |  | Solar |  | 05_05_19W73 | 02/02/2018 | 02/02/2018 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 178626 | 01826 |  |  |  | Solar |  | 05_12_29W5 | 03/15/2018 | 03/15/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 174727 | 01740 | 260 |  |  | Solar |  | 05_14_14L2 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | -40 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | MILLBURY | 178075 | 01527 | 3375 |  |  | Solar |  | 05_14_47L2 | 11/03/2017 | 11/03/2017 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/09/2018 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 561606 | 01507 | 3.8 |  |  | Solar |  | 05_14_61L3 | 10/10/2023 | 10/16/2023 | 5 | 3 | 2 | 10/17/2023 | 10/17/2023 | 34 | 16 | 18 | 12/11/2023 | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 11/30/2025 | N | EXP | 600 | 05/02/2024 | 05/29/2024 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 651164 | 01603 | 9.28 |  |  | Solar |  | 05_14_75L3 | 10/31/2024 | 11/21/2024 | 3 | 1 | 2 | 11/22/2024 | 11/22/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | SWANSEA | 290294 | 02777 | 15.2 |  |  | Solar |  | 05_01_225W1 | 05/04/2020 | 05/11/2020 | 5 | 5 | 0 | 05/12/2020 | 05/12/2020 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | LYNN | 686006 | 01904 | 3.8 |  |  | Solar |  | 05_01_304W5 | 04/17/2025 | 04/25/2025 | 5 | 0 | 5 | 04/28/2025 | 04/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | TEWKSBURY | 175578 | 01876 | 30 |  |  | Solar |  | 05_01_415L2 | 12/09/2014 | 12/09/2014 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 676125 | 01950 | 5.76 |  |  | Solar |  | 05_01_6J342 | 03/06/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | LAWRENCE | 185430 | 01843 | 4998 |  |  | Solar |  | 05_05_19W73 | 05/29/2018 | 05/29/2018 | 61 | 44 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 09/21/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 183811 | 01826 | 5 |  |  | Solar |  | 05_12_29W5 | 04/30/2018 | 04/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 198677 | 01740 | 0 |  |  | Solar |  | 05_14_14L2 | 11/13/2018 | 12/03/2018 | 11 | 4 | 7 | 12/04/2018 | 12/04/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 178312 | 01527 | 7.6 |  |  | Solar |  | 05_14_47L2 | 02/26/2018 | 02/26/2018 | 4 | 4 | 0 | 03/05/2018 | 03/05/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 3/3/2019 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  | 10/11/2019 | Connected |  | N
National Grid | CHARLTON | 562630 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 10/12/2023 | 11/02/2023 | 15 | 12 | 3 | 11/03/2023 | 11/03/2023 | 87 | 66 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 10/12/2023 | 3/23/2025 | Y | EXP | 365 | 05/16/2024 | 06/03/2024 | 19 | 0 | 19 |  |  | 6/7/2024 | Connected |  | N
National Grid | WORCESTER | 671868 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | DIGHTON | 291401 | 02715 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 08/27/2020 | 09/10/2020 | 14 | 0 | 14 |  |  | 12/9/2020 | Connected |  | N
National Grid | LYNN | 688408 | 01902 | 10 |  |  | Solar |  | 05_01_304W5 | 04/29/2025 | 05/06/2025 | 5 | 2 | 3 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 176201 | 01876 | 2000 |  |  | Solar |  | 05_01_415L2 | 02/11/2015 | 02/11/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 12/11/2015 | 02/11/2015 | 2/8/2018 | Y | STD | 790 | 03/20/2018 | 03/20/2018 | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | NEWBURY | 684243 | 01985 | 77.3 |  |  | Solar |  | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 19 | 10 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 188745 | 01843 | 129.6 |  |  | Solar |  | 05_05_19W73 | 06/20/2018 | 06/20/2018 | 10 | 0 | 10 | 08/21/2018 | 08/21/2018 | 32 | 31 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 191753 | 01844 | 7.6 |  |  | Solar |  | 05_12_29W5 | 07/24/2018 | 10/03/2018 | 41 | 38 | 3 | 10/04/2018 | 10/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 437891 | 01740 | 15.2 |  |  | Solar |  | 05_14_14L2 | 06/15/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | Y
National Grid | MILLBURY | 178352 | 01527 | 10 |  |  | Solar |  | 05_14_47L2 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 3/5/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | CHARLTON | 573321 | 01507 | 3.8 |  |  | Solar |  | 05_14_61L3 | 01/12/2024 | 01/30/2024 | 11 | 8 | 3 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/12/2024 | 4/10/2025 | Y | EXP | 365 | 05/16/2024 | 08/21/2024 | 98 | 0 | 98 |  |  | 8/31/2024 | Connected |  | N
National Grid | WORCESTER | 674866 | 01603 | 3.8 |  |  | Solar |  | 05_14_75L3 | 03/06/2025 | 03/26/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 297124 | 02764 | 15.2 |  |  | Solar |  | 05_01_225W1 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | Y
National Grid | LYNN | 713450 | 01902 | 11.4 |  |  | Solar |  | 05_01_304W5 | 08/20/2025 | 09/04/2025 | 10 | 8 | 2 | 09/05/2025 | 09/05/2025 | 53 | 37 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 11/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | TEWKSBURY | 176243 | 01876 | 275 |  |  | Solar |  | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/19/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 |  | 10/30/2015 | N | STD | -255 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 684212 | 01985 | 77.3 |  |  | Solar |  | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 19 | 10 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 195428 | 01843 | 1500 |  |  | Solar |  | 05_05_19W73 | 09/13/2017 | 09/25/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 07/29/2019 | 37 | 6 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 216929 | 01844 | 7.6 |  |  | Solar |  | 05_12_29W5 | 05/07/2019 | 05/08/2019 | 0 | 0 | 0 | 05/09/2019 | 05/09/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/07/2019 | 5/12/2021 | Y | EXP | 365 | 05/27/2020 | 10/24/2020 | 151 | 5 | 146 |  |  | 2/5/2021 | Connected |  | N
National Grid | HARVARD | 199222 | 01451 | 820 |  |  | Solar |  | 05_14_14L3 | 11/20/2018 | 11/28/2018 | 3 | 0 | 3 |  |  | 68 | 43 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 198160 | 01590 | 7.6 |  |  | Solar |  | 05_14_47L2 | 11/16/2018 | 11/19/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 581506 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 01/04/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 681276 | 01603 | 0 |  |  | Solar |  | 05_14_75L3 | 03/31/2025 | 05/06/2025 | 26 | 23 | 3 | 05/07/2025 | 05/07/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 310710 | 02715 | 0 |  |  | Solar |  | 05_01_225W1 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 7/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | LYNN | 174666 | 01902 | 19.99 |  |  | Solar |  | 05_01_304W5 | 12/18/2012 | 12/18/2012 | 8 | 0 | 8 | 01/02/2013 | 01/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 3/8/2013 | N | EXP | -10 |  |  | 0 | 0 | 0 | 5/22/2013 | 5/22/2013 | 6/11/2013 | Connected |  | N
National Grid | TEWKSBURY | 176242 | 01876 | 2000 |  |  | Solar |  | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/11/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 | 04/29/2015 | 4/1/2018 | Y | STD | 629 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 | 3/15/2018 | 3/15/2018 | 3/15/2018 | Connected |  | N
National Grid | NEWBURY | 731603 | 01985 | 17.92 |  |  | Solar |  | 05_01_6J356 | 11/07/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 235724 | 01843 | 7.6 |  |  | Solar |  | 05_05_19W73 | 07/03/2019 | 07/16/2019 | 8 | 8 | 0 | 07/17/2019 | 07/17/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 10/21/2019 | N | EXP | 82 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | Connected |  | N
National Grid | DRACUT | 265737 | 01826 | 7.6 |  |  | Solar |  | 05_12_29W5 | 12/04/2019 | 12/10/2019 | 3 | 0 | 3 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 517633 | 01740 | 72 |  |  | Solar |  | 05_14_16L1 | 04/29/2023 | 01/07/2024 | 172 | 162 | 10 |  |  | 57 | 35 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MILLBURY | 198970 | 01527 | 7.6 |  |  | Solar |  | 05_14_47L2 | 12/21/2018 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 582729 | 01507 | 9.86 |  |  | Solar |  | 05_14_61L3 | 02/21/2024 | 04/09/2024 | 34 | 25 | 9 | 04/10/2024 | 04/10/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 682755 | 01603 | 5.76 |  |  | Solar |  | 05_14_75L3 | 04/03/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 312902 | 02777 | 22.8 |  |  | Solar |  | 05_01_225W1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 11/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2021 | Connected |  | N
National Grid | LYNN | 174701 | 01902 | 11.5 |  |  | Solar |  | 05_01_304W5 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 4/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/3/2013 | 6/3/2013 | 6/6/2013 | Connected |  | N
National Grid | TEWKSBURY | 176331 | 01876 | 40 |  |  | Solar |  | 05_01_415L2 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 388 | 0 | 388 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 |  | 7/27/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/7/2015 | 8/7/2015 |  | Withdrawn |  | Y
National Grid | NEWBURY | 741220 | 01950 | 3.8 |  |  | Solar |  | 05_01_6W1 | 12/18/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 285962 | 01843 | 15.2 |  |  | Solar |  | 05_05_19W73 | 03/31/2020 | 04/01/2020 | 0 | 0 | 0 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | DRACUT | 289054 | 01826 | 3 |  |  | Solar |  | 05_12_29W5 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 | 05/06/2020 | 10/21/2021 | Y | EXP | 365 | 03/20/2021 | 05/04/2021 | 45 | 0 | 45 |  |  | 5/13/2021 | Connected |  | N
National Grid | BOLTON | 174748 | 01740 | 75 |  |  | Solar |  | 05_14_16L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2013 |  | 9/1/2014 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 199289 | 01527 | 7.6 |  |  | Solar |  | 05_14_47L2 | 10/24/2018 | 12/20/2018 | 20 | 19 | 1 | 12/21/2018 | 12/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 10/24/2018 | 12/20/2019 | Y | EXP | 365 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/15/2019 | Connected |  | N
National Grid | CHARLTON | 590957 | 01507 | 3.8 |  |  | Solar |  | 05_14_61L3 | 02/29/2024 | 03/06/2024 | 5 | 2 | 3 | 03/07/2024 | 03/07/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 02/29/2024 | 3/21/2025 | Y | EXP | 365 | 05/16/2024 | 05/21/2024 | 6 | 0 | 6 |  |  | 5/23/2024 | Connected |  | N
National Grid | WORCESTER | 691425 | 01603 | 19.195 |  |  | Solar |  | 05_14_75L3 | 05/19/2025 | 06/04/2025 | 10 | 6 | 4 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | DIGHTON | 338763 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 03/05/2021 | 03/08/2021 | 0 | 0 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 | 03/05/2021 | 3/7/2022 | Y | EXP | 365 | 06/17/2021 | 08/17/2021 | 61 | 0 | 61 |  |  | 8/25/2021 | Connected |  | N
National Grid | LYNN | 174906 | 01902 | 15 |  |  | Solar |  | 05_01_304W5 | 09/14/2012 | 09/14/2012 | 7 | 4 | 3 | 09/26/2012 | 09/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | -27 |  |  | 0 | 0 | 0 | 2/8/2013 | 2/8/2013 | 3/2/2013 | Connected |  | N
National Grid | CHELMSFORD | 176584 | 01824 | 9.5 |  |  | Solar |  | 05_01_415L2 | 04/07/2016 | 04/07/2016 | 31 | 31 | 0 | 05/24/2016 | 05/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 04/07/2016 | 4/13/2017 | Y | EXP | 311 | 11/30/2016 | 12/08/2016 | 6 | 0 | 6 | 5/10/2017 | 5/10/2017 | 5/15/2017 | Connected |  | N
National Grid | NEWBURY | 174950 | 01950 | 1000 |  |  | Solar |  | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 328690 | 01843 | 8.19 |  |  | Solar |  | 05_05_19W73 | 12/22/2020 | 12/28/2020 | 2 | 2 | 0 | 12/29/2020 | 12/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/22/2020 | 5/30/2022 | Y | EXP | 365 | 03/25/2021 | 04/30/2021 | 36 | 0 | 36 |  |  | 12/13/2021 | Connected |  | N
National Grid | DRACUT | 450088 | 01826 | 6 |  |  | Solar |  | 05_12_29W5 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 661964 | 01740 | 6.08 |  |  | Solar |  | 05_14_16L1 | 12/20/2024 | 12/29/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | MILLBURY | 201008 | 01527 | 10 |  |  | Solar |  | 05_14_47L2 | 03/06/2019 | 03/18/2019 | 7 | 0 | 7 | 03/19/2019 | 03/19/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/06/2019 | 4/3/2020 | Y | EXP | 365 | 09/06/2019 | 09/23/2019 | 17 | 0 | 17 |  |  | 10/25/2019 | Connected |  | N
National Grid | CHARLTON | 595150 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 03/29/2024 | 04/16/2024 | 11 | 7 | 4 | 04/17/2024 | 04/17/2024 | 25 | 21 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 194135 | 01603 | 130 |  |  | Solar |  | 05_14_75L4 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 103 | 26 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 338749 | 02764 | 7.6 |  |  | Solar |  | 05_01_225W1 | 01/26/2021 | 01/29/2021 | 2 | 0 | 2 | 02/01/2021 | 02/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | LYNN | 175169 | 01902 | 20 |  |  | Solar |  | 05_01_304W5 | 11/14/2012 | 11/14/2012 | 7 | 1 | 6 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2013 |  | 1/31/2013 | N | EXP | -13 |  |  | 0 | 0 | 0 | 2/13/2013 | 2/13/2013 | 4/12/2013 | Connected |  | N
National Grid | CHELMSFORD | 176600 | 01824 | 1000 |  |  | Solar |  | 05_01_415L2 | 12/29/2015 | 12/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 03/29/2016 | 07/05/2016 | 66 | 17 | 49 | 7/19/2016 | 12/29/2015 | 1/4/2017 | Y | STD | 169 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N
National Grid | NEWBURY | 174949 | 01950 | 2000 |  |  | Solar |  | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 342952 | 01843 | 11.4 |  |  | Solar |  | 05_05_19W73 | 02/18/2021 | 02/25/2021 | 4 | 0 | 4 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | METHUEN | 370923 | 01844 | 3.8 |  |  | Solar |  | 05_12_29W5 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 642166 | 01451 | 500 |  |  | Solar |  | 05_14_16L2 | 12/23/2024 |  | 258 | 62 | 196 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SUTTON | 207035 | 01590 | 7.6 |  |  | Solar |  | 05_14_47L2 | 02/10/2019 | 03/20/2019 | 26 | 26 | 0 | 03/21/2019 | 03/21/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 600825 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 04/04/2024 | 05/23/2024 | 6 | 6 | 0 | 05/24/2024 | 05/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 04/04/2024 | 6/20/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/18/2025 | Connected |  | N
National Grid | LEICESTER | 311773 | 01524 | 150 |  |  | Solar |  | 05_14_75L4 | 09/10/2020 | 09/16/2020 | 3 | 0 | 3 | 09/17/2020 | 09/17/2020 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 340547 | 02777 | 10 |  |  | Solar |  | 05_01_225W1 | 03/11/2021 | 03/31/2021 | 13 | 11 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/11/2021 | 12/8/2022 | Y | EXP | 365 | 08/10/2021 | 10/08/2021 | 57 | 3 | 54 |  |  | 12/1/2021 | Connected |  | N
National Grid | LYNN | 175160 | 01902 | 3000 |  |  | Solar |  | 05_01_304W5 | 08/04/2011 | 08/04/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 02/24/2012 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/04/2011 | 12/31/2012 | Y | STD | -73 | 11/13/2013 | 03/12/2014 | 80 | 0 | 80 | 2/28/2014 | 2/28/2014 | 3/6/2014 | Connected |  | N
National Grid | CHELMSFORD | 177235 | 01824 | 54.2 |  |  | Solar |  | 05_01_415L2 | 11/07/2016 | 11/07/2016 | 2 | 2 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2017 |  | 11/13/2017 | N | EXP | 307 |  |  | 0 | 0 | 0 | 5/24/2017 | 5/24/2017 | 5/24/2017 | Connected |  | N
National Grid | NEWBURY | 176281 | 01950 | 16.32 |  |  | Solar |  | 05_01_6W1 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | LAWRENCE | 342591 | 01843 | 499 |  |  | Solar |  | 05_05_19W73 | 03/22/2021 | 04/22/2021 | 22 | 12 | 10 |  |  | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 544488 | 01844 | 7.83 |  |  | Solar |  | 05_12_29W5 | 11/20/2023 |  | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 637603 | 01523 | 480 |  |  | Solar |  | 05_14_16L2 | 04/11/2025 | 06/23/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/24/2025 | 07/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SUTTON | 213962 | 01590 | 0 |  |  | Solar |  | 05_14_47L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | CHARLTON | 611921 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 05/22/2024 | 06/21/2024 | 7 | 4 | 3 | 06/24/2024 | 06/24/2024 | 56 | 39 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 318966 | 01524 | 249 |  |  | Solar |  | 05_14_75L4 | 10/13/2020 | 01/04/2022 | 19 | 12 | 7 | 11/10/2020 | 11/10/2020 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 1/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 342501 | 02715 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 02/17/2021 |  | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175680 | 01902 | 97.5 |  |  | Solar |  | 05_01_304W5 | 12/19/2014 | 12/19/2014 | 5 | 0 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2015 | 12/19/2014 | 12/31/2016 | Y | EXP | 719 | 12/10/2015 | 01/19/2016 | 25 | 0 | 25 | 4/1/2015 | 4/1/2015 | 4/8/2016 | Connected |  | N
National Grid | LOWELL | 177317 | 01852 | 1393 |  |  | Solar |  | 05_01_415L2 | 02/14/2017 | 03/10/2017 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 04/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 5/29/2020 | N | STD | 651 | 06/08/2019 | 11/21/2019 | 166 | 0 | 166 |  |  | 6/5/2020 | Connected |  | N
National Grid | NEWBURY | 176484 | 01950 | 7.6 |  |  | Solar |  | 05_01_6W1 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 5/30/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 381880 | 01843 | 7.54 |  |  | Solar |  | 05_05_19W73 | 09/16/2021 | 12/30/2021 | 15 | 13 | 2 | 10/08/2021 | 10/08/2021 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/16/2021 | 1/20/2023 | Y | EXP | 365 | 01/04/2022 | 01/13/2022 | 10 | 0 | 10 |  |  | 2/4/2022 | Connected |  | N
National Grid | METHUEN | 550054 | 01844 | 6 |  |  | Solar |  | 05_12_29W5 | 08/23/2023 | 08/28/2023 | 3 | 2 | 1 | 08/29/2023 | 08/29/2023 | 25 | 0 | 25 | 10/18/2023 | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/1/2025 | N | EXP | 365 | 03/14/2024 | 09/11/2024 | 159 | 0 | 159 |  |  | 8/20/2024 | Connected |  | N
National Grid | HARVARD | 714530 | 01451 | 1000 |  |  | Solar |  | 05_14_16L2 | 10/10/2025 | 11/12/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILLBURY | 223680 | 01527 | 7 |  |  | Solar |  | 05_14_47L2 | 04/30/2019 | 09/11/2019 | 40 | 36 | 4 | 09/12/2019 | 09/12/2019 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 |  | 9/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N
National Grid | CHARLTON | 612901 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 05/29/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2024 | 05/29/2024 | 8/5/2025 | Y | EXP | 365 | 01/29/2025 | 01/28/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | AUBURN | 379113 | 01501 | 7.6 |  |  | Solar |  | 05_14_75L4 | 11/01/2021 | 01/14/2022 | 52 | 50 | 2 | 01/18/2022 | 01/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 361381 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 06/01/2021 | 08/10/2021 | 48 | 46 | 2 | 08/11/2021 | 08/11/2021 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | LYNN | 176351 | 01902 | 7 |  |  | Solar |  | 05_01_304W5 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 575 | 03/17/2016 | 03/25/2016 | 5 | 0 | 5 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | LOWELL | 177363 | 01852 | 6.67 |  |  | Solar |  | 05_01_415L2 | 06/23/2016 | 06/23/2016 | 7 | 7 | 0 | 07/07/2016 | 07/07/2016 | 145 | 0 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/2/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 300516 | 01985 | 8.64 |  |  | Solar |  | 05_01_6W1 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 8/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | LAWRENCE | 392747 | 01843 | 9.8 |  |  | Solar |  | 05_05_19W73 | 11/24/2021 | 01/06/2022 | 3 | 0 | 3 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 551927 | 01844 | 7.54 |  |  | Solar |  | 05_12_29W5 | 09/28/2023 | 11/15/2023 | 32 | 29 | 3 | 11/16/2023 | 11/16/2023 | 105 | 40 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 174629 | 01451 | 500 |  |  | Solar |  | 05_14_16L2 | 05/17/2011 | 05/17/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2011 | 05/17/2011 | 1/23/2012 | Y | EXP | 217 | 10/19/2011 | 11/18/2011 | 21 | 0 | 21 | 8/6/2012 | 8/6/2012 | 1/23/2012 | Connected |  | N
National Grid | MILLBURY | 248584 | 01527 | 10 |  |  | Solar |  | 05_14_47L2 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 10/21/2019 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | CHARLTON | 614068 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 05/29/2024 | 06/18/2024 | 12 | 11 | 1 | 06/20/2024 | 06/20/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/29/2024 | 7/23/2025 | Y | EXP | 365 | 08/29/2024 | 12/03/2024 | 97 | 0 | 97 |  |  | 3/18/2025 | Connected |  | N
National Grid | WORCESTER | 668677 | 01603 | 20 |  |  | Solar |  | 05_14_75L4 | 01/29/2025 | 02/04/2025 | 5 | 2 | 3 | 02/05/2025 | 02/05/2025 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 362751 | 02777 | 10 |  |  | Solar |  | 05_01_225W1 | 06/15/2021 | 06/16/2021 | 1 | 0 | 1 | 06/17/2021 | 06/17/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | Y
National Grid | LYNN | 176378 | 01902 | 16 |  |  | Solar |  | 05_01_304W5 | 11/20/2015 | 11/20/2015 | 1 | 1 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 11/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/2/2016 | 3/2/2016 | 3/9/2016 | Connected |  | N
National Grid | LOWELL | 177552 | 01852 | 3500 |  |  | Solar |  | 05_01_415L2 | 05/15/2017 | 06/12/2017 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/14/2017 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2018 | 05/15/2017 | 12/20/2022 | Y | STD | 586 |  |  | 0 | 0 | 0 |  |  | 12/19/2022 | Connected |  | N
National Grid | NEWBURY | 321984 | 01985 | 250 |  |  | Solar |  | 05_01_6W1 | 07/21/2021 | 08/04/2021 | 10 | 0 | 10 | 08/05/2021 | 08/05/2021 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2021 | 07/21/2021 | 2/2/2023 | Y | EXP | 304 |  |  | 0 | 0 | 0 |  |  | 12/8/2022 | Connected |  | N
National Grid | LAWRENCE | 437709 | 01843 | 999 |  |  | Solar |  | 05_05_19W73 | 08/15/2022 | 09/13/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2022 | 10/05/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2024 | 08/15/2022 | 10/31/2025 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 591596 | 01844 | 6 |  |  | Solar |  | 05_12_29W5 | 03/07/2024 | 03/11/2024 | 2 | 0 | 2 | 03/12/2024 | 03/12/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2024 | Connected |  | N
National Grid | LANCASTER | 177800 | 01523 | 266.4 |  |  | Solar |  | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/24/2017 | 08/24/2017 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 11/30/2020 | Y | EXP | 879 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | MILLBURY | 283910 | 01527 | 10 |  |  | Solar |  | 05_14_47L2 | 03/17/2020 | 04/01/2020 | 10 | 7 | 3 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2020 | Connected |  | Y
National Grid | CHARLTON | 634009 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 09/10/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | AUBURN | 682085 | 01501 | 15.2 |  |  | Solar |  | 05_14_75L4 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 35 | 17 | 18 | 06/17/2025 | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/03/2025 | 8/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | DIGHTON | 377961 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 08/25/2021 | 10/06/2021 | 29 | 28 | 1 | 10/07/2021 | 10/07/2021 | 70 | 47 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 10/5/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176403 | 01902 | 3.8 |  |  | Solar |  | 05_01_304W5 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 234 | 0 | 234 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 |  | 3/19/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 177818 | 01851 | 13.76 |  |  | Solar |  | 05_01_415L2 | 04/04/2017 | 04/04/2017 | 218 | 216 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 373959 | 01985 | 3.8 |  |  | Solar |  | 05_01_6W1 | 08/09/2021 | 08/12/2021 | 3 | 0 | 3 | 08/13/2021 | 08/13/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 461180 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2023 | Connected |  | Y
National Grid | METHUEN | 592433 | 01844 | 6 |  |  | Solar |  | 05_12_29W5 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | LANCASTER | 177798 | 01523 | 233.1 |  |  | Solar |  | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/18/2017 | 08/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 8/9/2018 | Y | EXP | 336 | 02/12/2018 | 03/07/2018 | 13 | 0 | 13 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N
National Grid | MILLBURY | 408613 | 01527 | 15.2 |  |  | Solar |  | 05_14_47L2 | 01/26/2022 | 02/03/2022 | 7 | 6 | 1 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 7/15/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 635906 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WORCESTER | 666789 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L5 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 85 | 65 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 396398 | 02715 | 0 |  |  | Solar |  | 05_01_225W1 | 11/18/2021 | 11/23/2021 | 4 | 2 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2022 | Connected |  | N
National Grid | LYNN | 178381 | 01902 | 8.96 |  |  | Solar |  | 05_01_304W5 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 02/27/2018 | 02/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 1/21/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 7/31/2018 | Connected |  | N
National Grid | LOWELL | 177922 | 01852 | 4980 |  |  | Solar |  | 05_01_415L2 | 10/24/2017 | 10/24/2017 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 | 12/08/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 595595 | 01950 | 5.76 |  |  | Solar |  | 05_01_6W1 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 480346 | 01843 | 5.22 |  |  | Solar |  | 05_05_19W73 | 01/09/2023 | 01/27/2023 | 13 | 10 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/09/2023 | 6/23/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | Y
National Grid | METHUEN | 601269 | 01844 | 11.4 |  |  | Solar |  | 05_12_29W5 | 04/09/2024 | 06/25/2024 | 44 | 40 | 4 | 06/26/2024 | 06/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 178588 | 01740 | 350 |  |  | Solar |  | 05_14_16L2 | 03/13/2018 | 03/13/2018 | 1 | 0 | 1 | 05/16/2018 | 05/16/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 12/2/2019 | N | EXP | 551 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | MILLBURY | 461606 | 01527 | 7.6 |  |  | Solar |  | 05_14_47L2 | 09/29/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 09/29/2022 | 6/27/2024 | Y | EXP | 365 | 08/10/2023 | 08/22/2023 | 13 | 0 | 13 |  |  | 9/11/2023 | Connected |  | N
National Grid | CHARLTON | 637769 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 731105 | 01603 | 3.8 |  |  | Solar |  | 05_14_75L5 | 11/03/2025 | 11/04/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 416510 | 02715 | 0 |  |  | Solar |  | 05_01_225W1 | 03/09/2022 | 03/10/2022 | 1 | 0 | 1 | 03/11/2022 | 03/11/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 4/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | LYNN | 178488 | 01902 | 499.5 |  |  | Solar |  | 05_01_304W5 | 12/01/2017 | 01/23/2018 | 36 | 13 | 23 |  |  | 51 | 51 | 0 | 02/27/2018 | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 8/20/2020 | 12/01/2017 | 9/28/2022 | Y | STD | 550 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | LOWELL | 178290 | 01851 | 1000 |  |  | Solar |  | 05_01_415L2 | 03/28/2018 | 03/28/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/10/2018 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 605951 | 01950 | 3.8 |  |  | Solar |  | 05_01_6W1 | 04/23/2024 | 05/01/2024 | 4 | 0 | 4 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 482133 | 01843 | 8.12 |  |  | Solar |  | 05_05_19W73 | 12/16/2022 | 12/20/2022 | 3 | 2 | 1 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/16/2022 | 3/20/2024 | Y | EXP | 365 | 02/11/2023 | 03/17/2023 | 35 | 0 | 35 |  |  | 6/16/2023 | Connected |  | N
National Grid | DRACUT | 603809 | 01826 | 6 |  |  | Solar |  | 05_12_29W5 | 04/16/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 75 | 66 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | BOLTON | 314332 | 01740 | 10 |  |  | Solar |  | 05_14_16L2 | 10/08/2020 | 10/12/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 1/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 464397 | 01527 | 9.86 |  |  | Solar |  | 05_14_47L2 | 10/14/2022 | 10/27/2022 | 9 | 0 | 9 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 | 10/14/2022 | 12/5/2023 | Y | EXP | 365 | 01/25/2023 | 02/01/2023 | 8 | 0 | 8 |  |  | 4/7/2023 | Connected |  | N
National Grid | CHARLTON | 641933 | 01507 | 6 |  |  | Solar |  | 05_14_61L3 | 09/20/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WORCESTER | 732423 | 01603 | 5.76 |  |  | Solar |  | 05_14_75L5 | 11/12/2025 | 11/13/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DIGHTON | 422557 | 02715 | 15.2 |  |  | Solar |  | 05_01_225W1 | 04/14/2022 | 04/20/2022 | 4 | 3 | 1 | 04/21/2022 | 04/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2022 | Connected |  | N
National Grid | LYNN | 178572 | 01902 | 4980 |  |  | Solar |  | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2018 | 03/07/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2018 | 12/08/2017 | 10/28/2022 | Y | STD | 553 | 01/22/2022 | 05/03/2022 | 102 | 0 | 102 | 9/21/2022 | 10/19/2022 | 10/26/2022 | Connected |  | N
National Grid | LOWELL | 188710 | 01852 | 250 |  |  | Solar |  | 05_01_415L2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 647056 | 01985 | 10 |  |  | Solar |  | 05_01_6W1 | 10/23/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/23/2024 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | LAWRENCE | 484704 | 01843 | 8.7 |  |  | Solar |  | 05_05_19W73 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 | 01/10/2023 | 4/14/2024 | Y | EXP | 365 | 03/04/2023 | 04/13/2023 | 41 | 0 | 41 |  |  | 7/17/2023 | Connected |  | N
National Grid | LOWELL | 604998 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W5 | 04/18/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | BOLTON | 599266 | 01740 | 6 |  |  | Solar |  | 05_14_16L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/26/2024 | 4/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | MILLBURY | 550096 | 01527 | 9.984 |  |  | Solar |  | 05_14_47L2 | 01/10/2024 | 09/07/2023 | 0 | 0 | 0 | 01/23/2024 | 01/23/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2024 | Connected |  | N
National Grid | CHARLTON | 643919 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 09/30/2024 | 11/04/2024 | 13 | 11 | 2 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 09/30/2024 | 1/8/2026 | Y | EXP | 365 | 08/07/2025 | 09/06/2025 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176870 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L5 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 323 | 09/30/2016 | 10/18/2016 | 11 | 0 | 11 | 4/18/2016 | 4/18/2016 | 10/17/2016 | Connected |  | N
National Grid | DIGHTON | 424363 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 05/11/2022 | 05/18/2022 | 6 | 5 | 1 | 05/19/2022 | 05/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 8/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | N
National Grid | LYNN | 178571 | 01902 |  |  |  | Solar |  | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/16/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 195208 | 01824 | 6930 |  |  | Solar |  | 05_01_415L2 | 10/01/2018 | 10/22/2018 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/04/2018 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 648471 | 01985 | 10 |  |  | Solar |  | 05_01_6W1 | 12/23/2024 | 01/21/2025 | 19 | 15 | 4 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | LAWRENCE | 486122 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 2/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | DRACUT | 605339 | 01826 | 5 |  |  | Solar |  | 05_12_29W5 | 04/20/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 72 | 66 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 639458 | 01523 | 5.76 |  |  | Solar |  | 05_14_16L2 | 09/11/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/11/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | MILLBURY | 566203 | 01527 | 86.4 |  |  | Solar |  | 05_14_47L2 | 12/05/2023 | 02/20/2024 | 51 | 41 | 10 | 02/21/2024 | 02/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/05/2023 | 2/8/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | Y
National Grid | CHARLTON | 645579 | 01507 | 3.9 |  |  | Solar |  | 05_14_61L3 | 10/08/2024 | 10/17/2024 | 1 | 0 | 1 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/08/2024 | 12/1/2025 | Y | EXP | 365 | 02/13/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/21/2025 | Connected |  | N
National Grid | AUBURN | 186665 | 01501 | 3.8 |  |  | Solar |  | 05_14_75L5 | 05/30/2018 | 05/30/2018 | 10 | 9 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 7/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2019 | Connected |  | N
National Grid | DIGHTON | 428357 | 02764 | 9.57 |  |  | Solar |  | 05_01_225W1 | 05/04/2022 | 05/05/2022 | 1 | 1 | 0 | 05/06/2022 | 05/06/2022 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 | 05/04/2022 | 11/10/2023 | Y | EXP | 365 | 09/30/2022 | 11/09/2022 | 41 | 0 | 41 |  |  | 6/14/2023 | Connected |  | N
National Grid | LYNN | 178681 | 01902 | 4950 |  |  | Solar |  | 05_01_304W5 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 139 | 119 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 202001 | 01852 | 0 |  |  | Solar |  | 05_01_415L2 | 01/15/2019 | 02/25/2019 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2019 | 06/27/2019 | 87 | 72 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 650193 | 01985 | 5.76 |  |  | Solar |  | 05_01_6W1 | 11/07/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 11/07/2024 | 3/1/2026 | Y | EXP | 365 | 04/15/2025 | 08/08/2025 | 116 | 0 | 116 |  |  | 10/9/2025 | Connected |  | N
National Grid | LAWRENCE | 498979 | 01843 | 7.54 |  |  | Solar |  | 05_05_19W73 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | DRACUT | 613150 | 01826 | 3.8 |  |  | Solar |  | 05_12_29W5 | 05/23/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 671565 | 01740 | 3.8 |  |  | Solar |  | 05_14_16L2 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | MILLBURY | 600694 | 01527 | 15.2 |  |  | Solar |  | 05_14_47L2 | 04/05/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 647901 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 199149 | 01603 | 10 |  |  | Solar |  | 05_14_75L5 | 12/04/2018 | 01/10/2019 | 24 | 16 | 8 | 01/11/2019 | 01/11/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 | 12/04/2018 | 10/2/2019 | Y | EXP | 253 | 05/01/2019 | 06/11/2019 | 41 | 0 | 41 |  |  | 9/3/2019 | Connected |  | N
National Grid | DIGHTON | 442327 | 02764 | 15 |  |  | Solar |  | 05_01_225W1 | 07/18/2022 | 07/20/2022 | 3 | 2 | 1 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 |  | 9/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2022 | Connected |  | N
National Grid | LYNN | 193416 | 01902 | 24 |  |  | Solar |  | 05_01_304W5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 08/14/2018 |  | Y | EXP | 427 | 08/21/2019 | 09/11/2019 | 21 | 0 | 21 |  |  | 12/5/2019 | Connected |  | N
National Grid | LOWELL | 244622 | 01851 | 10 |  |  | Solar |  | 05_01_415L2 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 9/30/2019 | N | EXP | 56 |  |  | 0 | 0 | 0 |  |  | 9/26/2019 | Connected |  | N
National Grid | NEWBURY | 650851 | 01950 | 6.175 |  |  | Solar |  | 05_01_6W1 | 10/30/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/30/2024 | 4/4/2026 | Y | EXP | 365 | 01/23/2025 | 08/08/2025 | 198 | 0 | 198 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 578440 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 12/20/2023 | 01/03/2024 | 7 | 3 | 4 | 01/04/2024 | 01/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 2/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | LOWELL | 624218 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W5 | 07/11/2024 | 09/18/2024 | 25 | 20 | 5 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y
National Grid | HARVARD | 556991 | 01451 | 80 |  |  | Solar |  | 05_14_16L3 | 09/21/2023 | 10/12/2023 | 14 | 3 | 11 |  |  | 92 | 71 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | SUTTON | 602560 | 01590 | 15.2 |  |  | Solar |  | 05_14_47L2 | 04/08/2024 | 05/07/2024 | 21 | 19 | 2 | 05/08/2024 | 05/08/2024 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | N
National Grid | CHARLTON | 651538 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 11/12/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/12/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | AUBURN | 217114 | 01501 | 10 |  |  | Solar |  | 05_14_75L5 | 04/10/2019 | 04/25/2019 | 11 | 11 | 0 | 04/26/2019 | 04/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 | 04/10/2019 | 3/31/2020 | Y | EXP | 336 | 09/27/2019 | 10/23/2019 | 26 | 0 | 26 |  |  | 10/28/2019 | Connected |  | N
National Grid | DIGHTON | 444227 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 07/14/2022 | 07/25/2022 | 3 | 0 | 3 | 11/03/2022 | 11/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 07/14/2022 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | LYNN | 199870 | 01902 | 10 |  |  | Solar |  | 05_01_304W5 | 10/31/2018 | 12/31/2018 | 3 | 1 | 2 | 01/02/2019 | 01/02/2019 | 52 | 47 | 5 | 05/13/2020 | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/31/2018 | 1/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | LOWELL | 327784 | 01851 | 9.8 |  |  | Solar |  | 05_01_415L2 | 12/28/2020 | 12/31/2020 | 2 | 0 | 2 | 01/04/2021 | 01/04/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 2/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 652101 | 01985 | 7.6 |  |  | Solar |  | 05_01_6W1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/14/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LAWRENCE | 580411 | 01843 | 3.8 |  |  | Solar |  | 05_05_19W73 | 01/16/2024 | 01/19/2024 | 3 | 0 | 3 | 01/22/2024 | 01/22/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/16/2024 | 2/20/2025 | Y | EXP | 365 | 04/17/2024 | 05/31/2024 | 45 | 0 | 45 |  |  | 10/14/2024 | Connected |  | N
National Grid | DRACUT | 625525 | 01826 | 5.76 |  |  | Solar |  | 05_12_29W5 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 558959 | 01740 | 240 |  |  | Solar |  | 05_14_16L3 | 09/29/2023 | 10/23/2023 | 15 | 5 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILLBURY | 613760 | 01527 | 5.76 |  |  | Solar |  | 05_14_47L2 | 05/28/2024 | 06/05/2024 | 1 | 0 | 1 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 11/30/2025 | Y | EXP | 365 | 09/28/2024 | 09/27/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 651823 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 11/13/2024 | 03/13/2025 | 68 | 63 | 5 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | WORCESTER | 284540 | 01603 | 5.67 |  |  | Solar |  | 05_14_75L5 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/5/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 460092 | 02764 | 7.6 |  |  | Solar |  | 05_01_225W1 | 09/19/2022 | 10/03/2022 | 10 | 5 | 5 | 10/04/2022 | 10/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N
National Grid | LYNN | 229816 | 01902 | 10 |  |  | Solar |  | 05_01_304W5 | 05/21/2019 | 05/30/2019 | 5 | 0 | 5 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | LOWELL | 349183 | 01851 | 7.6 |  |  | Solar |  | 05_01_415L2 | 05/04/2021 | 05/07/2021 | 2 | 0 | 2 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 10/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y
National Grid | NEWBURY | 654308 | 01950 | 5.76 |  |  | Solar |  | 05_01_6W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/15/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LAWRENCE | 622852 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 07/09/2024 | 08/13/2024 | 4 | 1 | 3 | 08/14/2024 | 08/14/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 635728 | 01850 | 4.06 |  |  | Solar |  | 05_12_29W5 | 08/27/2024 | 10/04/2024 | 19 | 16 | 3 | 10/07/2024 | 10/07/2024 | 191 | 173 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 664845 | 01740 | 140 |  |  | Solar |  | 05_14_16L3 | 01/13/2025 | 03/19/2025 | 45 | 36 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MILLBURY | 634503 | 01527 | 0 |  |  | Battery Add-On |  | 05_14_47L2 | 09/06/2024 | 01/16/2025 | 18 | 13 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 09/06/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | CHARLTON | 651661 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 11/12/2024 | 02/18/2025 | 58 | 56 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WORCESTER | 307087 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L5 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 484329 | 02715 | 0 |  |  | Solar |  | 05_01_225W1 | 12/09/2022 | 02/10/2023 | 42 | 35 | 7 | 02/13/2023 | 02/13/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 301583 | 01904 | 7.92 |  |  | Solar |  | 05_01_304W5 | 07/16/2020 | 08/04/2020 | 12 | 12 | 0 | 08/05/2020 | 08/05/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 8/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | LOWELL | 356489 | 01851 | 21.36 |  |  | Solar |  | 05_01_415L2 | 05/05/2021 | 05/12/2021 | 4 | 2 | 2 | 05/13/2021 | 05/13/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2021 |  | 1/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | NEWBURY | 735202 | 01950 | 23 |  |  | Solar |  | 05_01_6W1 | 11/20/2025 | 11/25/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 623790 | 01843 | 5.76 |  |  | Solar |  | 05_05_19W73 | 07/10/2024 | 07/30/2024 | 2 | 0 | 2 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 644942 | 01850 | 5.76 |  |  | Solar |  | 05_12_29W5 | 10/04/2024 | 02/13/2025 | 5 | 1 | 4 | 02/14/2025 | 02/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LANCASTER | 676981 | 01523 | 750 |  |  | Solar |  | 05_14_16L3 | 04/07/2025 | 06/10/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILLBURY | 638266 | 01527 | 0 |  |  | Battery Add-On |  | 05_14_47L2 | 09/06/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | CHARLTON | 654440 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 11/14/2024 | 01/29/2025 | 3 | 0 | 3 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | AUBURN | 349177 | 01501 | 7.6 |  |  | Solar |  | 05_14_75L5 | 04/15/2021 | 04/26/2021 | 5 | 0 | 5 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2021 |  | 6/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 483675 | 02764 | 13.92 |  |  | Solar |  | 05_01_225W1 | 12/14/2022 | 12/20/2022 | 4 | 1 | 3 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 5/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | LYNN | 303514 | 01902 | 0 |  |  | Other |  | 05_01_304W5 | 09/15/2020 | 10/09/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 | 11/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 |  | Y | STD | 539 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 396888 | 01851 | 7.68 |  |  | Solar |  | 05_01_415L2 | 01/24/2022 | 01/25/2022 | 1 | 0 | 1 | 01/26/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2022 | 01/24/2022 | 7/27/2023 | Y | EXP | 365 | 06/30/2022 | 07/26/2022 | 27 | 0 | 27 |  |  | 9/7/2022 | Connected |  | N
National Grid | NEWBURY | 656032 | 01950 | 7.6 |  |  | Solar |  | 05_01_6W2 | 11/21/2024 | 04/07/2025 | 29 | 27 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 630724 | 01843 | 10 |  |  | Solar |  | 05_05_19W73 | 08/07/2024 | 09/24/2024 | 13 | 10 | 3 | 09/25/2024 | 09/25/2024 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 08/07/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 646085 | 01850 | 5.76 |  |  | Solar |  | 05_12_29W5 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | HARVARD | 718425 | 01451 | 12.215 |  |  | Solar |  | 05_14_16L3 | 09/16/2025 | 09/29/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 09/16/2025 | 11/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MILLBURY | 651318 | 01527 | 10 |  |  | Solar |  | 05_14_47L2 | 11/12/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 | 02/25/2025 | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 3/31/2025 | 11/12/2024 | 4/7/2026 | Y | EXP | 365 | 09/10/2025 | 09/16/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | CHARLTON | 655150 | 01507 | 10 |  |  | Solar |  | 05_14_61L3 | 11/20/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 383082 | 01603 | 6 |  |  | Solar |  | 05_14_75L5 | 10/13/2021 | 12/21/2021 | 4 | 0 | 4 | 10/20/2021 | 10/20/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2022 | Connected |  | N
National Grid | DIGHTON | 485679 | 02715 | 15.6 |  |  | Solar |  | 05_01_225W1 | 12/15/2022 | 02/09/2023 | 37 | 36 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2023 | Connected |  | N
National Grid | LYNN | 311604 | 01902 | 19 |  |  | Solar |  | 05_01_304W5 | 09/09/2020 | 09/14/2020 | 3 | 3 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/09/2020 | 6/2/2022 | Y | EXP | 475 | 01/12/2021 | 02/05/2021 | 24 | 0 | 24 |  |  | 4/22/2022 | Connected |  | N
National Grid | LOWELL | 398624 | 01851 | 19 |  |  | Solar |  | 05_01_415L2 | 12/09/2021 | 12/14/2021 | 3 | 0 | 3 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 2/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2022 | Connected |  | N
National Grid | NEWBURY | 689362 | 01950 | 990 |  |  | Solar |  | 05_01_6W2 | 06/23/2025 | 09/10/2025 | 55 | 48 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2025 | 09/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LAWRENCE | 643457 | 01843 | 7.6 |  |  | Solar |  | 05_05_19W73 | 09/27/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 09/27/2024 | 2/14/2026 | Y | EXP | 365 | 03/19/2025 | 04/21/2025 | 34 | 0 | 34 |  |  | 5/16/2025 | Connected |  | N
National Grid | LOWELL | 647380 | 01850 | 3.8 |  |  | Solar |  | 05_12_29W5 | 10/15/2024 | 11/01/2024 | 8 | 3 | 5 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/15/2024 | 11/26/2025 | Y | EXP | 365 | 02/26/2025 | 03/24/2025 | 27 | 0 | 27 |  |  | 3/28/2025 | Connected |  | N
National Grid | BOLTON | 175900 | 01740 | 100 |  |  | Solar |  | 05_14_16L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/11/2016 | Connected |  | N
National Grid | MILLBURY | 662520 | 01527 | 5.76 |  |  | Solar |  | 05_14_47L2 | 12/26/2024 | 02/03/2025 | 7 | 1 | 6 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | CHARLTON | 657463 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 11/27/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WORCESTER | 521839 | 01602 | 4.93 |  |  | Solar |  | 05_14_75L5 | 04/26/2023 | 07/17/2023 | 55 | 54 | 1 | 07/18/2023 | 07/18/2023 | 149 | 126 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | DIGHTON | 488296 | 02715 | 0 |  |  | Solar |  | 05_01_225W1 | 12/27/2022 | 01/03/2023 | 4 | 1 | 3 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 319874 | 01905 | 15.2 |  |  | Solar |  | 05_01_304W5 | 10/16/2020 | 10/23/2020 | 4 | 4 | 0 | 10/26/2020 | 10/26/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 | 10/16/2020 | 3/26/2022 | Y | EXP | 365 | 03/05/2021 | 03/16/2021 | 11 | 0 | 11 |  |  | 9/10/2021 | Connected |  | N
National Grid | LOWELL | 423224 | 01851 | 13.12 |  |  | Solar |  | 05_01_415L2 | 04/28/2022 | 05/02/2022 | 2 | 1 | 1 | 05/03/2022 | 05/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 166072 | 01950 | 7.6 |  |  | Solar |  | 05_01_6W2 | 04/24/2018 | 04/24/2018 | 9 | 0 | 9 | 07/27/2018 | 07/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  | 11/18/2020 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | LAWRENCE | 646259 | 01843 | 3.8 |  |  | Solar |  | 05_05_19W73 | 10/17/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | LOWELL | 650334 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W5 | 11/07/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/07/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | BOLTON | 200444 | 01740 | 201.6 |  |  | Solar |  | 05_14_16L3 | 11/05/2018 | 11/08/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 06/13/2019 | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2019 | 11/05/2018 | 11/8/2024 | Y | EXP | 70 | 03/01/2024 | 10/08/2024 | 222 | 182 | 40 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 713199 | 01590 | 20 |  |  | Solar |  | 05_14_47L2 | 08/19/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 70 | 56 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 662558 | 01507 | 11.4 |  |  | Solar |  | 05_14_61L3 | 12/27/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/27/2024 | 4/28/2026 | Y | EXP | 365 | 08/19/2025 | 08/19/2025 | 1 | 0 | 1 |  |  | 8/22/2025 | Connected |  | N
National Grid | WORCESTER | 543771 | 01603 | 9.6 |  |  | Solar |  | 05_14_75L5 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/25/2023 | 10/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | DIGHTON | 495716 | 02764 | 0 |  |  | Solar |  | 05_01_225W1 | 01/27/2023 | 02/01/2023 | 4 | 3 | 1 | 02/02/2023 | 02/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | LYNN | 324458 | 01902 | 0 |  |  | Solar |  | 05_01_304W5 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 2/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 482703 | 01851 | 23.49 |  |  | Solar |  | 05_01_415L2 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/05/2022 | 1/24/2024 | Y | EXP | 365 | 05/05/2023 | 06/08/2023 | 35 | 0 | 35 |  |  | 7/27/2023 | Connected |  | N
National Grid | NEWBURY | 174126 | 01985 | 135 |  |  | Solar |  | 05_01_6W2 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2013 |  | 8/9/2012 | N | EXP | -232 |  |  | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 1/6/2014 | Connected |  | N
National Grid | LAWRENCE | 653935 | 01843 | 5.76 |  |  | Solar |  | 05_05_19W73 | 11/18/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/18/2024 | 2/6/2026 | Y | EXP | 365 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 4/22/2025 | Connected |  | N
National Grid | DRACUT | 654196 | 01826 | 5.76 |  |  | Solar |  | 05_12_29W5 | 11/18/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/18/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | HARVARD | 202097 | 01451 | 3.8 |  |  | Solar |  | 05_14_16L3 | 11/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 11/27/2018 | 11/27/2020 | Y | EXP | 365 | 07/17/2020 | 08/12/2020 | 26 | 0 | 26 |  |  | 8/17/2020 | Connected |  | N
National Grid | MILLBURY | 714914 | 01527 | 15.2 |  |  | Solar |  | 05_14_47L2 | 09/02/2025 | 09/19/2025 | 11 | 6 | 5 | 09/22/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2026 | Connected |  | Y
National Grid | CHARLTON | 670838 | 01507 | 3.8 |  |  | Solar |  | 05_14_61L3 | 02/07/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 576217 | 01603 | 15.2 |  |  | Solar |  | 05_14_75L5 | 12/06/2023 | 12/27/2023 | 13 | 10 | 3 | 12/28/2023 | 12/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 506817 | 02777 | 13.34 |  |  | Solar |  | 05_01_225W1 | 03/20/2023 | 03/23/2023 | 3 | 0 | 3 | 03/24/2023 | 03/24/2023 | 25 | 0 | 25 | 06/21/2023 | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 8/14/2024 | N | EXP | 365 | 10/05/2023 | 10/18/2023 | 14 | 0 | 14 |  |  | 10/27/2023 | Connected |  | Y
National Grid | LYNN | 339473 | 01904 | 3.8 |  |  | Solar |  | 05_01_304W5 | 01/29/2021 | 03/30/2021 | 38 | 37 | 1 | 03/31/2021 | 03/31/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 01/29/2021 | 7/23/2022 | Y | EXP | 365 | 06/12/2021 | 07/06/2021 | 19 | 0 | 19 |  |  | 7/8/2022 | Connected |  | N
National Grid | LOWELL | 487520 | 01851 | 8.7 |  |  | Solar |  | 05_01_415L2 | 01/06/2023 | 01/12/2023 | 4 | 0 | 4 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | NEWBURY | 174417 | 01985 | 142 |  |  | Solar |  | 05_01_6W2 | 06/21/2012 | 06/21/2012 | 6 | 0 | 6 | 07/03/2012 | 07/03/2012 | 293 | 0 | 293 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/10/2012 | N | EXP | -93 |  |  | 0 | 0 | 0 | 9/25/2012 | 9/25/2012 |  | Withdrawn |  | N
National Grid | LAWRENCE | 673697 | 01843 | 3.8 |  |  | Solar |  | 05_05_19W73 | 02/24/2025 | 03/14/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 104 | 90 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 664824 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W5 | 01/10/2025 | 02/03/2025 | 10 | 5 | 5 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 | 03/10/2025 | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2025 | Connected |  | N
National Grid | BOLTON | 260377 | 01740 | 5 |  |  | Solar |  | 05_14_16L3 | 11/12/2019 | 11/18/2019 | 3 | 0 | 3 | 11/19/2019 | 11/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 11/12/2019 | 3/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N
National Grid | SUTTON | 711691 | 01590 | 4.537 |  |  | Solar |  | 05_14_48L1 | 08/15/2025 | 09/04/2025 | 16 | 12 | 4 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 672008 | 01507 | 15.2 |  |  | Solar |  | 05_14_61L3 | 02/13/2025 | 03/05/2025 | 14 | 10 | 4 | 03/06/2025 | 03/06/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 584135 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L5 | 02/06/2024 | 02/07/2024 | 1 | 0 | 1 | 02/08/2024 | 02/08/2024 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 5/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2024 | Connected |  | N
National Grid | DIGHTON | 524294 | 02715 | 15.2 |  |  | Solar |  | 05_01_225W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | LYNN | 352535 | 01902 | 7.54 |  |  | Solar |  | 05_01_304W5 | 04/14/2021 | 04/15/2021 | 0 | 0 | 0 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2021 | Connected |  | N
National Grid | LOWELL | 521797 | 01851 | 12.288 |  |  | Solar |  | 05_01_415L2 | 07/10/2023 | 07/12/2023 | 3 | 1 | 2 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 | 07/10/2023 | 9/8/2024 | Y | EXP | 365 | 10/24/2023 | 12/13/2023 | 51 | 0 | 51 |  |  | 7/9/2024 | Connected |  | N
National Grid | NEWBURY | 174924 | 01985 | 75 |  |  | Solar |  | 05_01_6W2 | 02/26/2013 | 02/26/2013 | 5 | 1 | 4 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2013 |  | 7/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 7/3/2013 | 7/3/2013 | 7/19/2013 | Connected |  | N
National Grid | LAWRENCE | 700565 | 01843 | 11.4 |  |  | Solar |  | 05_05_19W73 | 06/24/2025 | 08/01/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 9/7/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | LOWELL | 698445 | 01850 | 5.76 |  |  | Solar |  | 05_12_29W5 | 06/18/2025 | 07/18/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 06/18/2025 | 11/14/2026 | Y | EXP | 365 | 09/04/2025 | 09/03/2025 | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | BOLTON | 270083 | 01740 | 95.4 |  |  | Solar |  | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 70 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 733818 | 01590 | 3.8 |  |  | Solar |  | 05_14_48L1 | 11/14/2025 | 12/02/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 673492 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 02/21/2025 | 03/26/2025 | 15 | 12 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/21/2025 | 5/12/2026 | Y | EXP | 365 | 07/24/2025 |  | 162 | 0 | 162 |  |  | 12/26/2025 | Connected |  | N
National Grid | WORCESTER | 637007 | 01602 | 5.76 |  |  | Solar |  | 05_14_75L5 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 08/30/2024 | 10/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/19/2025 | 148 | 14 | 134 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 556180 | 02715 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 09/18/2023 | 10/11/2023 | 17 | 16 | 1 | 10/12/2023 | 10/12/2023 | 223 | 205 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 397095 | 01902 | 1500 |  |  | Solar |  | 05_01_304W5 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 557025 | 01851 | 0 |  |  | Solar |  | 05_01_415L2 | 12/22/2023 | 01/02/2024 | 5 | 2 | 3 | 01/03/2024 | 01/03/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | HAVERHILL | 175045 | 01832 | 246.5 |  |  | Solar |  | 05_01_6W2 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 335 | 0 | 335 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2014 |  | 9/1/2015 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 704932 | 01843 | 17.48 |  |  | Solar |  | 05_05_19W74 | 07/15/2025 | 09/08/2025 | 37 | 32 | 5 | 09/09/2025 | 09/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 710194 | 01850 | 240 |  |  | Solar |  | 05_12_29W6 | 08/12/2025 | 09/11/2025 | 21 | 11 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BOLTON | 270081 | 01740 | 37.8 |  |  | Solar |  | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 70 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 735545 | 01590 | 200 |  |  | Solar |  | 05_14_48L1 | 11/25/2025 | 01/06/2026 | 24 | 18 | 6 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 673460 | 01507 | 13.8 |  |  | Solar |  | 05_14_61L3 | 02/21/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/21/2025 | 5/27/2026 | Y | EXP | 365 | 10/25/2025 |  | 69 | 0 | 69 |  |  | 12/9/2025 | Connected |  | N
National Grid | LEICESTER | 636786 | 01524 | 10 |  |  | Solar |  | 05_14_75L5 | 08/30/2024 | 09/23/2024 | 3 | 0 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 532056 | 02715 | 15 |  |  | Solar |  | 05_01_225W1 | 06/07/2023 | 06/27/2023 | 13 | 12 | 1 | 06/28/2023 | 06/28/2023 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2024 | Connected |  | N
National Grid | LYNN | 486689 | 01902 | 4999 |  |  | Other |  | 05_01_304W5 | 01/19/2023 | 02/03/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2023 | 03/27/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 548536 | 01851 | 7.6 |  |  | Solar |  | 05_01_415L2 | 08/25/2023 | 08/29/2023 | 3 | 2 | 1 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2023 | 08/25/2023 | 11/9/2024 | Y | EXP | 365 | 03/09/2024 | 04/10/2024 | 33 | 0 | 33 |  |  | 6/27/2024 | Connected |  | N
National Grid | HAVERHILL | 175640 | 01830 | 354 |  |  | Solar |  | 05_01_6W2 | 10/20/2014 | 10/20/2014 | 8 | 4 | 4 | 10/31/2014 | 10/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/1/2016 | N | EXP | 528 |  |  | 0 | 0 | 0 | 10/23/2014 | 10/23/2014 | 6/16/2016 | Connected |  | Y
National Grid | LAWRENCE | 719867 | 01843 | 23 |  |  | Solar |  | 05_05_19W74 | 09/17/2025 | 10/17/2025 | 19 | 17 | 2 | 10/20/2025 | 10/20/2025 | 52 | 41 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 720948 | 01850 | 150 |  |  | Solar |  | 05_12_29W6 | 09/23/2025 | 10/31/2025 | 27 | 20 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BOLTON | 379349 | 01740 | 5 |  |  | Solar |  | 05_14_16L3 | 10/08/2021 | 01/04/2022 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 2/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | MILLBURY | 174294 | 01527 | 300 |  |  | Solar |  | 05_14_48L1 | 12/15/2011 | 12/15/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2012 |  | 1/28/2012 | N | EXP | -30 |  |  | 0 | 0 | 0 | 6/1/2012 | 6/1/2012 | 6/4/2012 | Connected |  | N
National Grid | CHARLTON | 673361 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 02/21/2025 | 02/26/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 638053 | 01603 | 10.89 |  |  | Solar |  | 05_14_75L5 | 09/05/2024 | 09/26/2024 | 7 | 3 | 4 | 09/27/2024 | 09/27/2024 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/05/2024 | 11/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | DIGHTON | 535567 | 02764 | 15.12 |  |  | Solar |  | 05_01_225W1 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | SALEM | 519333 | 01970 | 0 |  |  | Battery Add-On |  | 05_01_304W5 | 04/14/2023 | 04/24/2023 | 5 | 0 | 5 | 04/25/2023 | 04/25/2023 | 226 | 204 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LOWELL | 614260 | 01851 | 6 |  |  | Solar |  | 05_01_415L2 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 7/9/2025 | Y | EXP | 365 | 08/06/2024 | 08/15/2024 | 10 | 0 | 10 |  |  | 12/20/2024 | Connected |  | N
National Grid | HAVERHILL | 175981 | 01832 | 28 |  |  | Solar |  | 05_01_6W2 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/23/2015 | 6/23/2015 | 7/7/2015 | Connected |  | N
National Grid | LAWRENCE | 721916 | 01843 | 20 |  |  | Solar |  | 05_05_19W74 | 10/16/2025 | 10/22/2025 | 3 | 1 | 2 | 10/23/2025 | 10/23/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DRACUT | 720438 | 01826 | 150 |  |  | Solar |  | 05_12_29W6 | 09/22/2025 | 11/14/2025 | 37 | 29 | 8 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BOLTON | 405329 | 01740 | 150 |  |  | Solar |  | 05_14_16L3 | 02/16/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 02/16/2022 | 10/26/2024 | Y | STD | 98 | 07/09/2024 | 02/13/2025 | 220 | 19 | 201 |  |  | 10/21/2024 | Connected |  | N
National Grid | MILLBURY | 174816 | 01527 | 3000 |  |  | Solar |  | 05_14_48L1 | 07/31/2013 | 07/31/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2013 | 09/24/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2014 | 07/31/2013 | 9/15/2017 | Y | STD | 1187 |  |  | 0 | 0 | 0 | 9/15/2017 | 9/15/2017 | 9/27/2017 | Connected |  | N
National Grid | CHARLTON | 683655 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 04/08/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 637809 | 01603 | 3.8 |  |  | Solar |  | 05_14_75L5 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 537573 | 02764 | 50 |  |  | Solar |  | 05_01_225W1 | 06/28/2023 | 01/07/2024 | 130 | 120 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 525794 | 01970 | 10 |  |  | Solar |  | 05_01_304W5 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 07/05/2023 | 10/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2024 | Connected |  | N
National Grid | LOWELL | 666943 | 01851 | 10.47 |  |  | Solar |  | 05_01_415L2 | 01/24/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | HAVERHILL | 176334 | 01832 | 6.67 |  |  | Solar |  | 05_01_6W2 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/21/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 727861 | 01843 | 15.2 |  |  | Solar |  | 05_05_19W74 | 10/21/2025 | 10/23/2025 | 2 | 0 | 2 | 10/24/2025 | 10/24/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 177264 | 01826 | 784 |  |  | Solar |  | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 513162 | 01740 | 5.67 |  |  | Solar |  | 05_14_16L3 | 04/13/2023 | 04/19/2023 | 3 | 1 | 2 | 04/20/2023 | 04/20/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 04/13/2023 | 6/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | SUTTON | 175551 | 01590 | 196 |  |  | Solar |  | 05_14_48L1 | 04/07/2014 | 04/07/2014 | 8 | 0 | 8 | 04/18/2014 | 04/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 10/1/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/18/2014 | 6/18/2014 | 5/27/2015 | Connected |  | N
National Grid | CHARLTON | 689858 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 05/06/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 05/06/2025 | 7/25/2026 | Y | EXP | 365 | 11/04/2025 |  | 58 | 1 | 57 |  |  | 12/23/2025 | Connected |  | N
National Grid | WORCESTER | 643195 | 01602 | 7.6 |  |  | Solar |  | 05_14_75L5 | 09/27/2024 | 10/16/2024 | 5 | 2 | 3 | 10/17/2024 | 10/17/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 09/27/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | DIGHTON | 569141 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 11/14/2023 | 11/27/2023 | 2 | 0 | 2 | 11/28/2023 | 11/28/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2024 | 11/14/2023 | 1/11/2025 | Y | EXP | 365 | 02/17/2024 | 03/19/2024 | 32 | 0 | 32 |  |  | 4/16/2024 | Connected |  | N
National Grid | SALEM | 556313 | 01970 | 15 |  |  | Solar |  | 05_01_304W5 | 09/21/2023 | 10/02/2023 | 7 | 6 | 1 | 10/03/2023 | 10/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | LOWELL | 668885 | 01851 | 10 |  |  | Solar |  | 05_01_415L2 | 01/30/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | HAVERHILL | 176843 | 01832 | 6 |  |  | Solar |  | 05_01_6W2 | 05/02/2016 | 05/02/2016 | 2 | 2 | 0 | 05/05/2016 | 05/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 1/8/2018 | Y | EXP | 606 | 10/31/2016 | 10/25/2016 | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | LAWRENCE | 731625 | 01843 | 22.8 |  |  | Solar |  | 05_05_19W74 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 177927 | 01850 | 784 |  |  | Solar |  | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2017 |  | 6/15/2018 | N | STD | 262 |  |  | 0 | 0 | 0 |  |  | 6/14/2018 | Connected |  | N
National Grid | LANCASTER | 556253 | 01523 | 0 |  |  | Battery Add-On |  | 05_14_16L3 | 09/18/2023 | 10/06/2023 | 15 | 14 | 1 | 10/10/2023 | 10/10/2023 | 86 | 69 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | MILLBURY | 185025 | 01527 | 14.72 |  |  | Solar |  | 05_14_48L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 6/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | CHARLTON | 691695 | 01507 | 11.52 |  |  | Solar |  | 05_14_61L3 | 05/21/2025 | 05/30/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/21/2025 | 7/28/2026 | Y | EXP | 365 | 09/25/2025 |  | 99 | 0 | 99 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 646399 | 01603 | 5.76 |  |  | Solar |  | 05_14_75L5 | 10/16/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/16/2024 | 12/24/2025 | Y | EXP | 365 | 01/16/2025 | 02/18/2025 | 33 | 0 | 33 |  |  | 3/14/2025 | Connected |  | N
National Grid | DIGHTON | 574015 | 02764 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 11/28/2023 | 12/05/2023 | 6 | 5 | 1 | 12/06/2023 | 12/06/2023 | 78 | 62 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | SALEM | 566450 | 01970 | 10 |  |  | Solar |  | 05_01_304W5 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 | 01/31/2024 | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 |  | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 688903 | 01851 | 10 |  |  | Solar |  | 05_01_415L2 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 07/31/2025 | 07/30/2025 | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | HAVERHILL | 177158 | 01832 | 10 |  |  | Solar |  | 05_01_6W2 | 10/26/2016 | 10/26/2016 | 3 | 3 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2016 | 10/26/2016 | 11/1/2017 | Y | EXP | 363 | 04/17/2017 | 04/25/2017 | 5 | 0 | 5 | 5/18/2017 | 5/18/2017 | 5/18/2017 | Connected |  | N
National Grid | LAWRENCE | 741060 | 01843 | 7.6 |  |  | Solar |  | 05_05_19W74 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 188370 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W6 | 07/03/2018 | 07/03/2018 | 3 | 0 | 3 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 558659 | 01740 | 200 |  |  | Solar |  | 05_14_16L3 | 10/05/2023 | 10/23/2023 | 12 | 2 | 10 |  |  | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 187781 | 01527 | 179.9 |  |  | Solar |  | 05_14_48L1 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 | 06/14/2018 | 06/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 11/28/2019 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | CHARLTON | 701747 | 01507 | 7.6 |  |  | Solar |  | 05_14_61L3 | 06/28/2025 | 07/25/2025 | 9 | 5 | 4 | 08/08/2025 | 08/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/28/2025 | 9/9/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 646853 | 01602 | 5.76 |  |  | Solar |  | 05_14_75L5 | 10/29/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | DIGHTON | 582536 | 02715 | 24.375 |  |  | Solar |  | 05_01_225W1 | 01/12/2024 | 01/17/2024 | 3 | 1 | 2 | 01/18/2024 | 01/18/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | SALEM | 575814 | 01970 | 0 |  |  | Solar |  | 05_01_304W5 | 01/23/2024 | 03/14/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2024 | 04/11/2024 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178200 | 01851 | 4999 |  |  | Solar |  | 05_01_415L3 | 02/15/2018 | 02/22/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2018 | 03/20/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 | 02/15/2018 |  | Y | STD | 747 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | HAVERHILL | 178137 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 03/22/2018 | 04/05/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/28/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174648 | 01843 | 499 |  |  | Solar |  | 05_05_19W74 | 12/24/2013 | 12/24/2013 | 6 | 0 | 6 | 01/06/2014 | 01/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 12/24/2013 | 4/8/2016 | Y | EXP | 801 | 01/28/2016 | 03/25/2016 | 39 | 0 | 39 | 1/25/2016 | 1/25/2016 | 4/14/2016 | Connected |  | N
National Grid | DRACUT | 195677 | 01826 | 5 |  |  | Solar |  | 05_12_29W6 | 09/11/2018 | 11/09/2018 | 12 | 11 | 1 | 11/13/2018 | 11/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 592199 | 01740 | 7.6 |  |  | Solar |  | 05_14_16L3 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 4 | 2 | 2 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 191116 | 01527 | 1594 |  |  | Solar |  | 05_14_48L1 | 07/20/2018 | 08/24/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2018 | 10/15/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 07/20/2018 | 3/22/2024 | Y | STD | 275 | 08/29/2023 | 01/05/2024 | 130 | 3 | 127 |  |  | 2/28/2024 | Connected |  | N
National Grid | CHARLTON | 703776 | 01507 | 5.76 |  |  | Solar |  | 05_14_61L3 | 07/09/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 651011 | 01603 | 6 |  |  | Solar |  | 05_14_75L5 | 11/12/2024 | 02/05/2025 | 30 | 25 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | DIGHTON | 601438 | 02764 | 0 |  |  | Solar |  | 05_01_225W1 | 04/03/2024 | 05/02/2024 | 21 | 19 | 2 | 05/03/2024 | 05/03/2024 | 91 | 88 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | SALEM | 590002 | 01906 | 7.6 |  |  | Solar |  | 05_01_304W5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 08/08/2024 | 10/02/2024 | 56 | 0 | 56 |  |  | 10/11/2024 | Connected |  | N
National Grid | LOWELL | 663974 | 01851 | 200 |  |  | Solar |  | 05_01_415L3 | 01/13/2025 | 02/03/2025 | 15 | 5 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | HAVERHILL | 178216 | 01832 | 7.6 |  |  | Solar |  | 05_01_6W2 | 04/13/2018 | 04/13/2018 | 14 | 0 | 14 | 05/04/2018 | 05/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 4/21/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175198 | 01843 | 2000 |  |  | Solar |  | 05_05_19W74 | 04/26/2011 | 04/26/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2011 | 06/28/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2014 |  | 12/31/2016 | N | STD | 901 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 343901 | 01826 | 7.6 |  |  | Solar |  | 05_12_29W6 | 04/02/2021 | 04/06/2021 | 1 | 0 | 1 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | HARVARD | 598212 | 01451 | 3.8 |  |  | Solar |  | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 357413 | 01527 | 290 |  |  | Solar |  | 05_14_48L1 | 06/24/2021 | 12/01/2021 | 109 | 99 | 10 |  |  | 121 | 96 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2022 | 06/24/2021 | 10/10/2024 | Y | STD | 408 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | CHARLTON | 715329 | 01507 | 11.84 |  |  | Solar |  | 05_14_62L2 | 09/02/2025 | 11/07/2025 | 9 | 5 | 4 | 11/10/2025 | 11/10/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 651149 | 01603 | 5.76 |  |  | Solar |  | 05_14_75L5 | 11/12/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | DIGHTON | 612134 | 02715 | 50 |  |  | Solar |  | 05_01_225W1 | 05/20/2024 | 05/21/2024 | 1 | 0 | 1 | 05/22/2024 | 05/22/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 7/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | SALEM | 604919 | 01970 | 7.6 |  |  | Solar |  | 05_01_304W5 | 04/19/2024 | 05/09/2024 | 5 | 1 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/19/2024 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 12/05/2024 | 87 | 0 | 87 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174387 | 01851 | 2000 |  |  | Solar |  | 05_01_415L3 | 06/01/2012 | 06/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2012 | 08/20/2012 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 178252 | 01832 | 11.4 |  |  | Solar |  | 05_01_6W2 | 03/27/2018 | 04/03/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/27/2018 | 4/10/2020 | Y | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 3/20/2020 | Connected |  | N
National Grid | LAWRENCE | 175717 | 01843 | 1000 |  |  | Solar |  | 05_05_19W74 | 12/26/2014 | 12/26/2014 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 348179 | 01850 | 499.9 |  |  | Solar |  | 05_12_29W6 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 598082 | 01451 | 3.8 |  |  | Solar |  | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 595357 | 01527 | 9.57 |  |  | Solar |  | 05_14_48L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/13/2024 | 4/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | STURBRIDGE | 175840 | 01566 | 16 |  |  | Solar |  | 05_14_62L2 | 03/04/2015 | 03/04/2015 | 10 | 6 | 4 | 03/20/2015 | 03/20/2015 | 346 | 0 | 346 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/31/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 654398 | 01602 | 5.32 |  |  | Solar |  | 05_14_75L5 | 11/14/2024 | 01/06/2025 | 28 | 24 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 3/21/2026 | N | EXP | 365 | 02/21/2025 | 04/29/2025 | 68 | 27 | 41 |  |  | 5/6/2025 | Connected |  | N
National Grid | DIGHTON | 631386 | 02764 | 0 |  |  | Battery Add-On |  | 05_01_225W1 | 08/09/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 08/09/2024 | 10/13/2025 | Y | EXP | 405 | 01/07/2025 |  | 360 | 0 | 360 |  |  | 11/21/2025 | Connected |  | N
National Grid | SALEM | 608984 | 01970 | 2.61 |  |  | Solar |  | 05_01_304W5 | 05/16/2024 | 06/14/2024 | 21 | 20 | 1 | 06/17/2024 | 06/17/2024 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 174874 | 01851 | 1000 |  |  | Solar |  | 05_01_415L3 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/10/2012 | 6/13/2016 | Y | STD | 1036 |  |  | 0 | 0 | 0 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | HAVERHILL | 178734 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 02/12/2018 | 03/07/2018 | 0 | 0 | 0 | 03/07/2018 | 03/07/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 |  | 2/18/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175837 | 01810 | 15.2 |  |  | Solar |  | 05_05_19W74 | 03/04/2015 | 03/04/2015 | 5 | 1 | 4 | 03/12/2015 | 03/12/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 |  | 7/31/2015 | N | EXP | 140 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 364600 | 01850 | 6 |  |  | Solar |  | 05_12_29W6 | 06/28/2021 | 09/02/2021 | 48 | 47 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 06/28/2021 | 5/13/2023 | Y | EXP | 365 | 03/24/2022 | 04/21/2022 | 29 | 0 | 29 |  |  | 5/16/2022 | Connected |  | N
National Grid | LANCASTER | 623126 | 01523 | 5.76 |  |  | Solar |  | 05_14_16L3 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 | 08/21/2024 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 | 09/28/2024 | 02/07/2025 | 133 | 0 | 133 |  |  | 3/12/2025 | Connected |  | N
National Grid | MILLBURY | 627023 | 01527 | 10 |  |  | Solar |  | 05_14_48L1 | 07/23/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/23/2024 | 9/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | STURBRIDGE | 177883 | 01566 | 20 |  |  | Solar |  | 05_14_62L2 | 10/19/2017 | 10/19/2017 | 58 | 52 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 654202 | 01602 | 7.6 |  |  | Solar |  | 05_14_75L5 | 11/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/13/2024 | 3/27/2026 | Y | EXP | 365 | 05/24/2025 | 11/17/2025 | 178 | 0 | 178 |  |  | 7/21/2025 | Connected |  | N
National Grid | DIGHTON | 635160 | 02715 | 9.88 |  |  | Solar |  | 05_01_225W1 | 08/26/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 10/6/2025 | Y | EXP | 365 | 11/07/2024 | 11/19/2024 | 13 | 0 | 13 |  |  | 2/13/2025 | Connected |  | N
National Grid | SALEM | 630164 | 01970 | 32.88 |  |  | Solar |  | 05_01_304W5 | 08/05/2024 | 08/07/2024 | 3 | 1 | 2 | 08/08/2024 | 08/08/2024 | 91 | 74 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | LOWELL | 174907 | 01851 | 1000 |  |  | Solar |  | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 6/13/2016 | Y | STD | 1036 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 197997 | 01830 | 6 |  |  | Solar |  | 05_01_6W2 | 11/05/2018 | 01/14/2019 | 6 | 0 | 6 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175827 | 01810 | 7.6 |  |  | Solar |  | 05_05_19W74 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 9/27/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/24/2016 | Connected |  | N
National Grid | LOWELL | 364264 | 01850 | 0 |  |  | Solar |  | 05_12_29W6 | 07/14/2021 | 07/29/2021 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2021 | 09/01/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 644209 | 01740 | 5.76 |  |  | Solar |  | 05_14_16L3 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | MILLBURY | 632030 | 01527 | 7.6 |  |  | Solar |  | 05_14_48L1 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 186432 | 01566 | 0 |  |  | Solar |  | 05_14_62L2 | 06/20/2018 | 06/20/2018 | 42 | 35 | 7 | 08/21/2018 | 08/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2019 | Connected |  | N
National Grid | WORCESTER | 657885 | 01603 | 6.38 |  |  | Solar |  | 05_14_75L5 | 12/02/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | DIGHTON | 641650 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 11/13/2024 | 12/05/2024 | 9 | 5 | 4 | 12/06/2024 | 12/06/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | SALEM | 641209 | 01970 | 7.6 |  |  | Solar |  | 05_01_304W5 | 09/18/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 1/13/2026 | Y | EXP | 365 | 04/15/2025 | 08/15/2025 | 123 | 0 | 123 |  |  | 9/30/2025 | Connected |  | N
National Grid | LOWELL | 175328 | 01851 | 540 |  |  | Solar |  | 05_01_415L3 | 11/10/2014 | 11/10/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/17/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 204022 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 02/21/2019 | 03/07/2019 | 10 | 10 | 0 | 03/08/2019 | 03/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176302 | 01810 | 490 |  |  | Solar |  | 05_05_19W74 | 09/15/2015 | 09/15/2015 | 0 | 0 | 0 | 09/15/2015 | 09/15/2015 | 243 | 0 | 243 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/20/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 493073 | 01850 | 0 |  |  | Other |  | 05_12_29W6 | 05/01/2023 | 10/23/2023 | 118 | 109 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 12/09/2023 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 644966 | 01523 | 7.6 |  |  | Solar |  | 05_14_16L3 | 10/04/2024 | 11/11/2024 | 12 | 7 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/04/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MILLBURY | 652477 | 01527 | 5.76 |  |  | Solar |  | 05_14_48L1 | 11/19/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 194474 | 01566 | 480 |  |  | Solar |  | 05_14_62L2 | 08/27/2018 | 09/04/2018 | 5 | 5 | 0 | 09/05/2018 | 09/05/2018 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 9/4/2020 | N | EXP | 541 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661283 | 01603 | 15.2 |  |  | Solar |  | 05_14_75L5 | 02/11/2025 |  | 101 | 80 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 644960 | 02726 | 8.12 |  |  | Solar |  | 05_01_225W1 | 10/03/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2025 | Connected |  | N
National Grid | SALEM | 643175 | 01970 | 0 |  |  | Other |  | 05_01_304W5 | 12/10/2024 | 01/31/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2025 | 03/10/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 176124 | 01851 | 540 |  |  | Solar |  | 05_01_415L3 | 01/29/2015 | 01/29/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/29/2015 | 7/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 218065 | 01830 | 792.6 |  |  | Solar |  | 05_01_6W2 | 06/07/2019 | 09/17/2019 | 70 | 69 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2019 | 10/04/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 06/07/2019 | 4/27/2023 | Y | STD | 782 | 06/04/2021 | 03/09/2023 | 644 | 7 | 637 | 3/10/2023 | 4/3/2023 | 4/17/2023 | Connected |  | N
National Grid | ANDOVER | 176535 | 01810 | 6 |  |  | Solar |  | 05_05_19W74 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 6/16/2016 | 6/16/2016 | 6/23/2016 | Connected |  | N
National Grid | DRACUT | 573931 | 01826 | 10.47 |  |  | Solar |  | 05_12_29W6 | 11/28/2023 | 12/20/2023 | 16 | 16 | 0 | 12/21/2023 | 12/21/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | LANCASTER | 649171 | 01523 | 8.7 |  |  | Solar |  | 05_14_16L3 | 10/25/2024 | 11/04/2024 | 3 | 0 | 3 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 10/25/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | MILLBURY | 683789 | 01527 | 5.76 |  |  | Solar |  | 05_14_48L1 | 04/08/2025 | 04/28/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/08/2025 | 7/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | STURBRIDGE | 200806 | 01566 | 4.8 |  |  | Solar |  | 05_14_62L2 | 11/08/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 |  | 1/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | WORCESTER | 661713 | 01603 | 3.8 |  |  | Solar |  | 05_14_75L5 | 12/19/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 646978 | 02764 | 10 |  |  | Solar |  | 05_01_225W1 | 10/29/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 645815 | 01907 | 6.72 |  |  | Solar |  | 05_01_304W5 | 10/09/2024 | 10/17/2024 | 2 | 0 | 2 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 10/09/2024 | 4/16/2026 | Y | EXP | 365 | 03/06/2025 |  | 302 | 0 | 302 |  |  | 6/10/2025 | Connected |  | N
National Grid | LOWELL | 176481 | 01851 | 57.6 |  |  | Solar |  | 05_01_415L3 | 05/20/2016 | 05/20/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 356 | 05/01/2017 | 05/09/2017 | 6 | 0 | 6 | 6/21/2017 | 6/21/2017 | 6/28/2017 | Connected |  | N
National Grid | HAVERHILL | 219190 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 04/11/2019 | 06/26/2019 | 4 | 0 | 4 | 06/27/2019 | 06/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176649 | 01810 | 6 |  |  | Solar |  | 05_05_19W74 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 2/23/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 6/6/2016 | Connected |  | N
National Grid | LOWELL | 610926 | 01850 | 9.57 |  |  | Solar |  | 05_12_29W6 | 05/14/2024 | 08/21/2024 | 5 | 2 | 3 | 08/22/2024 | 08/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 10/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | BOLTON | 649125 | 01740 | 10 |  |  | Solar |  | 05_14_16L3 | 10/23/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | SUTTON | 705677 | 01590 | 8.027 |  |  | Solar |  | 05_14_48L1 | 07/17/2025 | 08/04/2025 | 7 | 3 | 4 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | STURBRIDGE | 233871 | 01566 | 10 |  |  | Solar |  | 05_14_62L2 | 06/06/2019 | 06/28/2019 | 16 | 13 | 3 | 07/01/2019 | 07/01/2019 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | WORCESTER | 654679 | 01603 | 7.6 |  |  | Solar |  | 05_14_75L6 | 11/15/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DIGHTON | 648121 | 02764 | 9.88 |  |  | Solar |  | 05_01_225W1 | 10/18/2024 | 11/06/2024 | 13 | 10 | 3 | 11/07/2024 | 11/07/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | SALEM | 648088 | 01970 | 15.2 |  |  | Solar |  | 05_01_304W5 | 10/21/2024 | 10/23/2024 | 2 | 1 | 1 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | LOWELL | 176677 | 01851 | 112 |  |  | Solar |  | 05_01_415L3 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 | 06/28/2016 | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 | 10/31/2016 | 01/05/2016 | 1/11/2018 | Y | EXP | 437 | 07/26/2017 | 07/28/2017 | 2 | 0 | 2 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | HAVERHILL | 236417 | 01832 | 7.6 |  |  | Solar |  | 05_01_6W2 | 06/27/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2019 | 06/27/2019 | 6/27/2020 | Y | EXP | 365 | 03/28/2020 | 04/22/2020 | 25 | 0 | 25 |  |  | 4/24/2020 | Connected |  | N
National Grid | ANDOVER | 177124 | 01810 | 2000 |  |  | Solar |  | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 01/04/2017 | 49 | 35 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 4/22/2019 | Y | STD | 640 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 621136 | 01850 | 7.6 |  |  | Solar |  | 05_12_29W6 | 06/27/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | BOLTON | 652993 | 01740 | 3.84 |  |  | Solar |  | 05_14_16L3 | 11/08/2024 | 11/13/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 707574 | 01527 | 17.48 |  |  | Solar |  | 05_14_48L1 | 07/25/2025 | 07/29/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | STURBRIDGE | 300290 | 01566 | 0 |  |  | Solar |  | 05_14_62L2 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2020 | Connected |  | N
National Grid | WORCESTER | 698874 | 01603 | 4200 |  |  | Other |  | 05_14_75L6 | 10/16/2025 | 11/26/2025 | 29 | 22 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2025 | 12/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SOMERSET | 651005 | 02726 | 7.6 |  |  | Solar |  | 05_01_225W1 | 11/12/2024 | 12/27/2024 | 24 | 20 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 | 02/27/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | SALEM | 654542 | 01970 | 7.6 |  |  | Solar |  | 05_01_304W5 | 11/18/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | LOWELL | 178084 | 01851 | 1000 |  |  | Solar |  | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 5/14/2018 | Y | STD | 1736 | 04/13/2015 | 08/29/2017 | 593 | 0 | 593 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | HAVERHILL | 256583 | 01830 | 3.8 |  |  | Solar |  | 05_01_6W2 | 10/08/2019 | 10/09/2019 | 0 | 0 | 0 | 10/10/2019 | 10/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2020 | Connected |  | N
National Grid | ANDOVER | 177123 | 01810 | 3625 |  |  | Solar |  | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 01/04/2017 | 48 | 35 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 6/27/2024 | Y | STD | 404 | 09/29/2023 | 02/05/2024 | 129 | 45 | 84 |  |  | 6/24/2024 | Connected |  | N
National Grid | METHUEN | 652997 | 01844 | 7.6 |  |  | Solar |  | 05_12_29W6 | 11/14/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/14/2024 | 2/26/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/15/2025 | Connected |  | N
National Grid | BOLTON | 661655 | 01740 | 5.76 |  |  | Solar |  | 05_14_16L3 | 12/19/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | MILLBURY | 619097 | 01527 | 10 |  |  | Solar |  | 05_14_48L2 | 06/20/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 06/20/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | CHARLTON | 328453 | 01507 | 0 |  |  | Solar |  | 05_14_62L2 | 11/25/2020 | 01/26/2021 | 39 | 38 | 1 | 01/27/2021 | 01/27/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 6/23/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | WORCESTER | 737727 | 01603 | 5.76 |  |  | Solar |  | 05_14_75L6 | 12/03/2025 | 12/17/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 650897 | 02715 | 11.5 |  |  | Solar |  | 05_01_225W1 | 10/30/2024 | 12/02/2024 | 13 | 10 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | SALEM | 661844 | 01970 | 5.76 |  |  | Solar |  | 05_01_304W5 | 12/19/2024 | 02/24/2025 | 22 | 17 | 5 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 437621 | 01851 | 4482 |  |  | Solar |  | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 03/27/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 265671 | 01830 | 7.6 |  |  | Solar |  | 05_01_6W2 | 12/04/2019 | 12/17/2019 | 9 | 9 | 0 | 12/18/2019 | 12/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2019 |  | 5/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | ANDOVER | 177288 | 01810 | 233.1 |  |  | Solar |  | 05_05_19W74 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 09/15/2016 | 21 | 4 | 17 | 06/20/2016 | 07/15/2016 | 18 | 5 | 13 |  | 09/15/2016 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 6/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 669791 | 01826 | 7.6 |  |  | Solar |  | 05_12_29W6 | 02/04/2025 | 03/19/2025 | 18 | 14 | 4 | 03/20/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | BOLTON | 666095 | 01740 | 5.76 |  |  | Solar |  | 05_14_16L3 | 01/16/2025 | 03/05/2025 | 17 | 12 | 5 | 03/06/2025 | 03/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | MILLBURY | 648633 | 01527 | 5.76 |  |  | Solar |  | 05_14_48L2 | 11/01/2024 | 12/03/2024 | 13 | 9 | 4 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STURBRIDGE | 331152 | 01566 | 0 |  |  | Solar |  | 05_14_62L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 | 12/11/2020 | 9/5/2023 | Y | EXP | 475 | 08/15/2021 | 09/16/2021 | 32 | 3 | 29 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174341 | 01602 | 225 |  |  | Solar |  | 05_14_75L6 | 01/30/2012 | 01/30/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 655903 | 02715 | 15 |  |  | Solar |  | 05_01_225W1 | 11/21/2024 | 12/02/2024 | 3 | 1 | 2 | 12/03/2024 | 12/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | SALEM | 679629 | 01970 | 3.8 |  |  | Solar |  | 05_01_304W5 | 03/21/2025 | 06/18/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 437435 | 01851 | 0 |  |  | Other |  | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 04/18/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 274538 | 01830 | 48 |  |  | Natural Gas |  | 05_01_6W2 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 | 03/08/2021 | 03/08/2021 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 6/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | ANDOVER | 177465 | 01810 | 192 |  |  | Solar |  | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 42 | 28 | 14 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | METHUEN | 674089 | 01844 | 14.82 |  |  | Solar |  | 05_12_29W6 | 02/25/2025 | 03/05/2025 | 7 | 4 | 3 | 03/06/2025 | 03/06/2025 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | HARVARD | 671508 | 01451 | 10 |  |  | Solar |  | 05_14_16L3 | 02/13/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | SUTTON | 703899 | 01590 | 6 |  |  | Solar |  | 05_14_48L2 | 07/10/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 | 07/10/2025 | 10/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STURBRIDGE | 370322 | 01566 | 7.6 |  |  | Solar |  | 05_14_62L2 | 07/16/2021 |  | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177114 | 01602 | 3.8 |  |  | Solar |  | 05_14_75L6 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 125 | 0 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 |  | 8/14/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 665152 | 02715 | 7.6 |  |  | Solar |  | 05_01_225W1 | 01/13/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 702694 | 01970 | 17.101 |  |  | Solar |  | 05_01_304W5 | 07/08/2025 | 07/14/2025 | 4 | 0 | 4 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | LOWELL | 533391 | 01851 | 16.24 |  |  | Solar |  | 05_01_415L3 | 06/13/2023 | 06/20/2023 | 4 | 2 | 2 | 06/21/2023 | 06/21/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2023 | Connected |  | N
National Grid | HAVERHILL | 291970 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 06/16/2020 | 06/17/2020 | 0 | 0 | 0 | 06/18/2020 | 06/18/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2020 |  | 6/16/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177464 | 01810 | 96 |  |  | Solar |  | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 13 | 0 | 13 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 5/22/2018 | Connected |  | N
National Grid | METHUEN | 657092 | 01844 | 5.76 |  |  | Solar |  | 05_12_2W1 | 11/26/2024 | 01/30/2025 | 2 | 0 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 11/26/2024 | 3/18/2026 | Y | EXP | 365 | 06/14/2025 | 09/12/2025 | 91 | 0 | 91 |  |  |  | Completion Documents |  | Y
National Grid | LANCASTER | 682361 | 01532 | 15.2 |  |  | Solar |  | 05_14_16L3 | 04/02/2025 | 04/25/2025 | 16 | 12 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | MILLBURY | 730051 | 01527 | 150 |  |  | Solar |  | 05_14_48L2 | 10/30/2025 | 11/24/2025 | 16 | 6 | 10 | 11/25/2025 | 11/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 380185 | 01507 | 7.6 |  |  | Solar |  | 05_14_62L2 | 09/06/2021 |  | 75 | 69 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177251 | 01602 | 6 |  |  | Solar |  | 05_14_75L6 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 241 | 0 | 241 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 665518 | 02764 | 20 |  |  | Solar |  | 05_01_225W1 | 01/14/2025 | 01/16/2025 | 2 | 0 | 2 | 01/17/2025 | 01/17/2025 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | SALEM | 644551 | 01970 | 10 |  |  | Solar |  | 05_01_304W6 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 1/28/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 657366 | 01851 | 7.6 |  |  | Solar |  | 05_01_415L3 | 11/27/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/27/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 318228 | 01830 | 10 |  |  | Solar |  | 05_01_6W2 | 11/02/2020 | 11/13/2020 | 7 | 6 | 1 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/02/2020 | 10/14/2022 | Y | EXP | 365 | 07/02/2021 | 10/13/2021 | 104 | 3 | 101 |  |  | 1/10/2022 | Connected |  | N
National Grid | ANDOVER | 177891 | 01810 | 3.8 |  |  | Solar |  | 05_05_19W74 | 04/13/2017 | 04/13/2017 | 6 | 6 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | METHUEN | 724976 | 01844 | 6.72 |  |  | Solar |  | 05_12_2W1 | 10/08/2025 | 10/31/2025 | 15 | 13 | 2 | 11/03/2025 | 11/03/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 682707 | 01523 | 15.2 |  |  | Solar |  | 05_14_16L3 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | SUTTON | 176994 | 01590 | 82 |  |  | Solar |  | 05_14_48L2 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2016 |  | 7/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | STURBRIDGE | 394876 | 01566 | 7.6 |  |  | Solar |  | 05_14_62L2 | 11/11/2021 | 12/20/2021 | 27 | 24 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  | 8/2/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177396 | 01602 | 6 |  |  | Solar |  | 05_14_75L6 | 02/21/2017 | 02/21/2017 | 6 | 1 | 5 | 03/01/2017 | 03/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2017 | 02/21/2017 | 2/26/2018 | Y | EXP | 360 | 10/16/2017 | 10/20/2017 | 4 | 0 | 4 | 6/27/2017 | 6/27/2017 | 11/2/2017 | Connected |  | N
National Grid | DIGHTON | 665398 | 02764 | 3.8 |  |  | Solar |  | 05_01_225W1 | 01/14/2025 | 02/10/2025 | 6 | 2 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | SALEM | 654741 | 01970 | 240 |  |  | Solar |  | 05_01_304W6 | 11/15/2024 | 02/10/2025 | 56 | 46 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LOWELL | 681045 | 01851 | 11.5 |  |  | Solar |  | 05_01_415L3 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2025 | Connected |  | N
National Grid | HAVERHILL | 324658 | 01832 | 3.8 |  |  | Solar |  | 05_01_6W2 | 11/27/2020 | 12/02/2020 | 2 | 0 | 2 | 12/03/2020 | 12/03/2020 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 178015 | 01810 | 15.2 |  |  | Solar |  | 05_05_19W74 | 06/29/2017 | 06/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/4/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176002 | 01844 | 8.17 |  |  | Solar |  | 05_12_2W1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 8/19/2016 | Y | EXP | 346 | 08/19/2016 | 09/21/2016 | 22 | 0 | 22 | 5/10/2016 | 5/10/2016 | 10/28/2016 | Connected |  | N
National Grid | LANCASTER | 688012 | 01523 | 7.6 |  |  | Solar |  | 05_14_16L3 | 04/29/2025 | 06/13/2025 | 3 | 0 | 3 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | SUTTON | 177118 | 01590 | 510 |  |  | Solar |  | 05_14_48L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 404321 | 01566 | 7.6 |  |  | Solar |  | 05_14_62L2 | 01/02/2022 | 01/04/2022 | 1 | 0 | 1 | 01/05/2022 | 01/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 6/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | WORCESTER | 177646 | 01603 | 11.4 |  |  | Solar |  | 05_14_75L6 | 09/26/2017 | 09/26/2017 | 7 | 7 | 0 | 10/06/2017 | 10/06/2017 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 10/2/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | SOMERSET | 666895 | 02726 | 20.48 |  |  | Solar |  | 05_01_225W1 | 01/28/2025 | 02/18/2025 | 14 | 11 | 3 | 02/19/2025 | 02/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | SALEM | 712153 | 01970 | 7.6 |  |  | Solar |  | 05_01_304W6 | 08/14/2025 | 09/16/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 174965 | 01851 | 130 |  |  | Solar |  | 05_01_4J324 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2013 |  | 11/29/2013 | N | EXP | 63 |  |  | 0 | 0 | 0 | 2/20/2014 | 2/20/2014 | 2/20/2014 | Connected |  | N
National Grid | HAVERHILL | 325927 | 01830 | 7.68 |  |  | Solar |  | 05_01_6W2 | 01/29/2021 | 02/08/2021 | 5 | 5 | 0 | 02/09/2021 | 02/09/2021 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2021 | Connected |  | N
National Grid | ANDOVER | 178164 | 01810 | 617 |  |  | Solar |  | 05_05_19W74 | 02/13/2018 | 02/13/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 | 02/13/2018 | 5/13/2022 | Y | STD | 82 | 05/27/2020 | 08/31/2021 | 461 | 8 | 453 |  |  | 5/13/2022 | Connected |  | N
National Grid | METHUEN | 176624 | 01844 | 6 |  |  | Solar |  | 05_12_2W1 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 |  | 4/24/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 708313 | 01523 | 12.54 |  |  | Solar |  | 05_14_16L3 | 07/30/2025 | 09/15/2025 | 26 | 24 | 2 | 09/16/2025 | 09/16/2025 | 53 | 50 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 177188 | 01527 | 51 |  |  | Solar |  | 05_14_48L2 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 1/21/2018 | N | EXP | 510 |  |  | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 1/8/2018 | Connected |  | N
National Grid | STURBRIDGE | 442063 | 01566 | 13.6 |  |  | Solar |  | 05_14_62L2 | 08/02/2022 | 08/03/2022 | 2 | 1 | 1 | 08/04/2022 | 08/04/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 | 08/02/2022 | 8/30/2023 | Y | EXP | 365 | 09/28/2022 | 12/21/2022 | 85 | 0 | 85 |  |  | 1/5/2023 | Connected |  | N
National Grid | WORCESTER | 177837 | 01603 | 15.2 |  |  | Solar |  | 05_14_75L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | SOMERSET | 670869 | 02726 | 5.76 |  |  | Solar |  | 05_01_225W1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | SALEM | 730087 | 01970 | 10 |  |  | Solar |  | 05_01_304W6 | 10/30/2025 | 10/30/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/30/2025 | 12/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LOWELL | 175149 | 01851 | 50 |  |  | Solar |  | 05_01_4J324 | 10/21/2013 | 10/21/2013 | 8 | 0 | 8 | 11/01/2013 | 11/01/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2014 |  | 1/6/2017 | N | EXP | 1085 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 336649 | 01832 | 7.6 |  |  | Solar |  | 05_01_6W2 | 01/25/2021 | 01/27/2021 | 1 | 0 | 1 | 01/28/2021 | 01/28/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 | 01/25/2021 | 1/26/2022 | Y | EXP | 365 | 05/27/2021 | 05/28/2021 | 1 | 0 | 1 |  |  | 8/11/2021 | Connected |  | N
National Grid | ANDOVER | 178152 | 01810 | 2700 |  |  | Solar |  | 05_05_19W74 | 12/21/2017 | 12/21/2017 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2018 | 02/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 12/21/2017 | 9/29/2025 | Y | STD | 414 | 06/04/2021 | 12/31/2021 | 211 | 10 | 201 |  |  | 9/4/2025 | Connected |  | N
National Grid | DRACUT | 177088 | 01826 | 432.6 |  |  | Solar |  | 05_12_2W1 | 01/18/2017 | 01/18/2017 | 2 | 0 | 2 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 1/24/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 8/8/2017 | 8/8/2017 | 8/8/2017 | Connected |  | N
National Grid | BOLTON | 177362 | 01740 | 150 |  |  | Solar |  | 05_14_48L2 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2016 |  | 6/28/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | WHITINSVILLE | 470177 | 01588 | 15.2 |  |  | Solar |  | 05_14_62L2 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/21/2022 | 1/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | WORCESTER | 192225 | 01610 | 7.6 |  |  | Solar |  | 05_14_75L6 | 07/30/2018 | 09/19/2018 | 2 | 0 | 2 | 09/20/2018 | 09/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 676081 | 01603 | 20 |  |  | Solar |  | 05_01_225W1 | 03/12/2025 | 04/14/2025 | 24 | 21 | 3 | 04/15/2025 | 04/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | SOMERSET | 737133 | 02726 | 17.16 |  |  | Solar |  | 05_01_304W6 | 12/01/2025 | 12/03/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 178291 | 01970 | 200 |  |  | Solar |  | 05_01_4J324 | 03/28/2018 | 04/20/2018 | 15 | 15 | 0 | 04/20/2018 | 04/20/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 12/2/2019 | N | EXP | 382 |  |  | 0 | 0 | 0 |  |  | 11/7/2019 | Connected |  | N
National Grid | LOWELL | 336435 | 01851 | 10 |  |  | Solar |  | 05_01_6W2 | 03/17/2021 | 03/24/2021 | 4 | 0 | 4 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178213 | 01830 | 2000 |  |  | Solar |  | 05_05_19W74 | 03/26/2018 | 03/26/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 03/26/2018 | 5/5/2024 | Y | STD | 555 | 01/14/2022 | 02/01/2024 | 748 | 680 | 68 |  |  | 4/15/2024 | Connected |  | N
National Grid | ANDOVER | 177135 | 01810 | 3.8 |  |  | Solar |  | 05_12_2W1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/11/2018 | 1/11/2018 | 1/11/2018 | Connected |  | N
National Grid | METHUEN | 517634 | 01844 | 100 |  |  | Solar |  | 05_14_16L4 | 04/29/2023 | 07/20/2023 | 56 | 46 | 10 |  |  | 118 | 97 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | LANCASTER | 188201 | 01523 | 150 |  |  | Solar |  | 05_14_48L2 | 06/15/2018 | 06/15/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 12/2/2019 | N | EXP | 524 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | SUTTON | 483147 | 01590 | 15.2 |  |  | Solar |  | 05_14_62L2 | 12/28/2022 | 01/18/2023 | 14 | 13 | 1 | 01/19/2023 | 01/19/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 447195 | 01610 | 10 |  |  | Solar |  | 05_14_75L6 | 08/02/2022 | 08/03/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 681615 | 01603 | 10.64 |  |  | Solar |  | 05_01_225W1 | 04/02/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 62 | 37 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | DIGHTON | 174356 | 02715 | 143 |  |  | Natural Gas |  | 05_01_304W6 | 05/11/2012 | 05/11/2012 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 184789 | 01970 | 249.8 |  |  | Solar |  | 05_01_4J324 | 05/08/2017 | 05/08/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/23/2018 | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 |  | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 357858 | 01851 | 2.88 |  |  | Solar |  | 05_01_6W2 | 05/20/2021 | 05/25/2021 | 2 | 0 | 2 | 05/26/2021 | 05/26/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  | 11/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2023 | Connected |  | N
National Grid | HAVERHILL | 178393 | 01830 | 10 |  |  | Solar |  | 05_05_19W74 | 03/02/2018 | 03/02/2018 | 8 | 0 | 8 | 03/29/2018 | 03/29/2018 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 | 03/02/2018 | 3/11/2019 | Y | EXP | 186 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | ANDOVER | 177151 | 01810 | 5.2 |  |  | Solar |  | 05_12_2W1 | 08/11/2016 | 08/11/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/16/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 669042 | 01844 | 0 |  |  | Battery Add-On |  | 05_14_16L4 | 02/03/2025 | 02/05/2025 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 84 | 60 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 248292 | 01523 | 7.6 |  |  | Solar |  | 05_14_48L2 | 08/12/2019 | 08/14/2019 | 0 | 0 | 0 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 08/12/2019 | 11/6/2020 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | SUTTON | 481649 | 01590 | 9.984 |  |  | Solar |  | 05_14_62L2 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 10/27/2024 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 9/25/2024 | Connected |  | N
National Grid | WORCESTER | 457130 | 01608 | 0 |  |  | Other |  | 05_14_75L6 | 11/15/2022 | 02/08/2023 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2023 | 03/29/2023 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 683232 | 01603 | 7.6 |  |  | Solar |  | 05_01_225W1 | 04/15/2025 | 07/15/2025 | 29 | 24 | 5 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | DIGHTON | 174658 | 02764 | 150 |  |  | Natural Gas |  | 05_01_304W6 | 12/10/2012 | 12/10/2012 | 20 | 14 | 6 | 01/10/2013 | 01/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 10/15/2014 | N | EXP | 576 |  |  | 0 | 0 | 0 | 6/15/2015 | 6/15/2015 | 6/30/2015 | Connected |  | Y
National Grid | SALEM | 197101 | 01970 | 25 |  |  | Solar |  | 05_01_4J324 | 09/27/2018 | 10/04/2018 | 8 | 5 | 3 | 10/11/2018 | 10/11/2018 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 390140 | 01824 | 9.8 |  |  | Solar |  | 05_01_6W2 | 11/11/2021 | 12/16/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 11/11/2021 | 6/8/2023 | Y | EXP | 365 | 03/31/2022 | 06/03/2022 | 65 | 0 | 65 |  |  | 7/8/2022 | Connected |  | N
National Grid | HAVERHILL | 178694 | 01830 | 5.2 |  |  | Solar |  | 05_05_19W74 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 03/14/2018 | 03/14/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/12/2019 | N | EXP | 286 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 186237 | 01810 | 3.8 |  |  | Solar |  | 05_12_2W1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 679246 | 01826 | 15.2 |  |  | Solar |  | 05_14_16L4 | 04/02/2025 | 04/14/2025 | 9 | 6 | 3 | 04/15/2025 | 04/15/2025 | 33 | 22 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BOLTON | 300239 | 01740 | 3.8 |  |  | Solar |  | 05_14_48L2 | 07/17/2020 | 07/27/2020 | 5 | 0 | 5 | 07/28/2020 | 07/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 | 07/17/2020 | 6/18/2021 | Y | EXP | 365 | 01/13/2021 | 01/19/2021 | 6 | 0 | 6 |  |  | 2/12/2021 | Connected |  | N
National Grid | SUTTON | 489268 | 01590 | 22.75 |  |  | Solar |  | 05_14_62L2 | 01/13/2023 | 01/18/2023 | 3 | 1 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | WORCESTER | 512343 | 01608 | 5.76 |  |  | Solar |  | 05_14_75L6 | 03/17/2023 | 07/23/2024 | 5 | 3 | 2 | 07/24/2024 | 07/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WORCESTER | 174996 | 01602 | 1250 |  |  | Solar |  | 05_01_304W6 | 03/08/2013 | 03/08/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2013 | 04/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 202335 | 02764 | 72 |  |  | Solar |  | 05_01_4J324 | 11/29/2018 | 12/04/2018 | 2 | 0 | 2 | 12/05/2018 | 12/05/2018 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 12/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 445228 | 01970 | 9.57 |  |  | Solar |  | 05_01_6W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 | 08/03/2022 | 5/9/2024 | Y | EXP | 365 | 04/20/2023 | 05/04/2023 | 15 | 0 | 15 |  |  | 5/21/2023 | Connected |  | N
National Grid | CHELMSFORD | 195446 | 01824 | 2000 |  |  | Solar |  | 05_05_19W74 | 02/07/2020 |  | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 186574 | 01832 | 3.8 |  |  | Solar |  | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 2 | 1 | 1 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 727121 | 01810 | 19 |  |  | Solar |  | 05_14_16L4 | 10/28/2025 | 11/12/2025 | 3 | 3 | 0 | 11/13/2025 | 11/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DRACUT | 376194 | 01826 | 7.6 |  |  | Solar |  | 05_14_48L2 | 08/16/2021 | 10/15/2021 | 19 | 18 | 1 | 10/18/2021 | 10/18/2021 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 08/16/2021 | 4/16/2023 | Y | EXP | 365 | 01/12/2022 | 02/09/2022 | 29 | 0 | 29 |  |  | 4/22/2022 | Connected |  | N
National Grid | BOLTON | 571929 | 01740 | 0 |  |  | Solar |  | 05_14_62L2 | 11/16/2023 | 11/27/2023 | 6 | 0 | 6 | 11/28/2023 | 11/28/2023 | 71 | 51 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | SUTTON | 524863 | 01590 | 7.68 |  |  | Solar |  | 05_14_75L6 | 05/22/2023 | 05/23/2023 | 1 | 0 | 1 | 05/24/2023 | 05/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | Y
National Grid | WORCESTER | 722322 | 01609 | 20.242 |  |  | Solar |  | 05_01_225W1 | 09/30/2025 | 10/08/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | WORCESTER | 175250 | 01603 | 24.94 |  |  | Solar |  | 05_01_304W6 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 11/19/2015 | 11/19/2015 | 11/19/2015 | Connected |  | N
National Grid | DIGHTON | 321058 | 02715 | 75 |  |  | Natural Gas |  | 05_01_4J324 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 187 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | SALEM | 444419 | 01970 | 0 |  |  | Other |  | 05_01_6W2 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/09/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 215929 | 01824 | 2970 |  |  | Solar |  | 05_05_19W74 | 04/24/2019 | 05/09/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/06/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 187385 | 01832 | 3.8 |  |  | Solar |  | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 7 | 4 | 3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 571517 | 01810 | 3.8 |  |  | Solar |  | 05_14_48L2 | 02/05/2024 | 02/05/2024 | 0 | 0 | 0 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/05/2024 | 3/15/2025 | Y | EXP | 365 | 05/30/2024 | 10/29/2024 | 153 | 0 | 153 |  |  | 12/3/2024 | Connected |  | N
National Grid | METHUEN | 572719 | 01844 | 22.8 |  |  | Solar |  | 05_14_62L2 | 11/20/2023 | 12/11/2023 | 14 | 13 | 1 | 12/12/2023 | 12/12/2023 | 32 | 12 | 20 | 01/31/2024 | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/5/2025 | N | EXP | 365 | 05/18/2024 | 06/28/2024 | 42 | 0 | 42 |  |  | 7/3/2024 | Connected |  | Y
National Grid | BOLTON | 558735 | 01740 | 350 |  |  | Solar |  | 05_14_75L6 | 12/04/2023 | 01/04/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2024 | 01/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 174154 | 01590 | 1000 |  |  | Solar |  | 05_01_225W2 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2012 | 06/22/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175459 | 01610 | 499 |  |  | Solar |  | 05_01_304W6 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 | 10/01/2014 | 10/01/2014 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174963 | 01602 | 60 |  |  | Solar |  | 05_01_4J336 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2013 |  | 11/29/2013 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 2/28/2014 | Connected |  | N
National Grid | DIGHTON | 492821 | 02715 | 7.6 |  |  | Solar |  | 05_01_6W2 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 6/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | SALEM | 232600 | 01970 | 15.2 |  |  | Solar |  | 05_05_19W74 | 05/31/2019 | 06/12/2019 | 7 | 0 | 7 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2020 | Connected |  | N
National Grid | CHELMSFORD | 188870 | 01824 | 3.8 |  |  | Solar |  | 05_12_2W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174786 | 01832 | 300 |  |  | Solar |  | 05_14_16L4 | 08/06/2013 | 08/06/2013 | 1 | 0 | 1 | 08/07/2013 | 08/07/2013 | 566 | 5 | 561 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 9/14/2014 | N | EXP | 383 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 586282 | 01810 | 15.2 |  |  | Solar |  | 05_14_48L2 | 01/31/2024 | 02/20/2024 | 13 | 10 | 3 | 02/21/2024 | 02/21/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | METHUEN | 604796 | 01844 | 0 |  |  | Battery Add-On |  | 05_14_62L2 | 04/22/2024 | 05/20/2024 | 21 | 20 | 1 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 597814 | 01740 | 14.3 |  |  | Solar |  | 05_14_75L6 | 03/28/2024 | 04/02/2024 | 4 | 2 | 2 | 04/03/2024 | 04/03/2024 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 8/11/2025 | Y | EXP | 365 | 02/15/2025 | 03/14/2025 | 28 | 0 | 28 |  |  | 4/4/2025 | Connected |  | N
National Grid | SUTTON | 176327 | 01590 | 2800 |  |  | Solar |  | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 7/1/2016 | N | STD | 221 |  |  | 0 | 0 | 0 |  |  | 12/19/2016 | Withdrawn |  | N
National Grid | WORCESTER | 175603 | 01610 | 990 |  |  | Solar |  | 05_01_304W6 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/19/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 | 10/15/2014 | 12/31/2016 | Y | STD | 599 | 07/12/2017 | 07/12/2017 | 0 | 0 | 0 | 8/15/2017 | 8/15/2017 | 8/15/2017 | Connected |  | N
National Grid | WORCESTER | 514581 | 01603 | 9.6 |  |  | Solar |  | 05_01_4J336 | 03/30/2023 | 05/30/2023 | 41 | 40 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 | 08/07/2023 | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 |  | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 558041 | 02779 | 7.6 |  |  | Solar |  | 05_01_6W2 | 09/29/2023 | 10/05/2023 | 4 | 0 | 4 | 10/06/2023 | 10/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/29/2023 | 11/19/2024 | Y | EXP | 365 | 04/24/2024 | 09/04/2024 | 134 | 0 | 134 |  |  | 9/10/2024 | Connected |  | N
National Grid | SALEM | 383763 | 01970 | 233.3 |  |  | Solar |  | 05_05_19W74 | 09/27/2021 | 10/12/2021 | 10 | 2 | 8 |  |  | 36 | 4 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 |  | 5/4/2024 | N | STD | 203 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | CHELMSFORD | 192482 | 01824 | 7.6 |  |  | Solar |  | 05_12_2W1 | 08/01/2018 | 10/01/2018 | 22 | 22 | 0 | 10/02/2018 | 10/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 08/01/2018 | 4/22/2020 | Y | EXP | 568 | 11/15/2019 | 12/23/2019 | 38 | 0 | 38 |  |  | 1/6/2020 | Connected |  | N
National Grid | HAVERHILL | 174780 | 01830 | 100 |  |  | Solar |  | 05_14_16L4 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 583 | 7 | 576 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 12/31/2016 | N | EXP | 1222 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 587167 | 01810 | 10.24 |  |  | Solar |  | 05_14_48L2 | 02/01/2024 | 02/08/2024 | 3 | 1 | 2 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 02/01/2024 | 3/6/2026 | Y | EXP | 365 | 07/02/2025 | 07/11/2025 | 10 | 0 | 10 |  |  | 7/15/2025 | Connected |  | N
National Grid | METHUEN | 670001 | 01844 | 5.76 |  |  | Solar |  | 05_14_62L2 | 02/11/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 618488 | 01523 | 7.6 |  |  | Solar |  | 05_14_75L6 | 06/28/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | GRAFTON | 177388 | 01519 | 2800 |  |  | Solar |  | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 07/17/2015 | 7/20/2018 | Y | STD | 970 | 08/28/2017 | 06/18/2018 | 145 | 0 | 145 |  |  | 7/20/2017 | Connected |  | N
National Grid | WORCESTER | 175617 | 01610 | 114 |  |  | Solar |  | 05_01_304W6 | 04/24/2014 | 04/24/2014 | 6 | 0 | 6 | 05/05/2014 | 05/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2014 | 04/24/2014 | 9/30/2014 | Y | EXP | 118 | 10/15/2014 | 12/17/2014 | 43 | 0 | 43 | 7/21/2014 | 7/21/2014 | 12/19/2014 | Connected |  | N
National Grid | WORCESTER | 616884 | 01603 | 5.76 |  |  | Solar |  | 05_01_4J336 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | DIGHTON | 536053 | 02764 | 850 |  |  | Solar |  | 05_01_6W2 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 03/28/2024 | 145 | 94 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 390978 | 01970 | 150 |  |  | Solar |  | 05_05_19W74 | 10/29/2021 | 11/11/2021 | 8 | 0 | 8 |  |  | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 | 10/29/2021 | 5/2/2024 | Y | STD | 203 | 11/30/2023 | 01/22/2024 | 54 | 0 | 54 |  |  | 4/30/2024 | Connected |  | N
National Grid | CHELMSFORD | 203384 | 01824 | 10 |  |  | Solar |  | 05_12_2W1 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 175753 | 01830 | 300 |  |  | Solar |  | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 118 | 03/10/2015 | 06/26/2015 | 74 | 0 | 74 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | ANDOVER | 592029 | 01810 | 3.8 |  |  | Solar |  | 05_14_48L2 | 02/22/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 15 | 10 | 5 | 06/10/2024 | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | METHUEN | 702798 | 01844 | 3 |  |  | Solar |  | 05_14_63L1 | 07/07/2025 | 07/23/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 56 | 44 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 634167 | 01453 | 7.6 |  |  | Solar |  | 05_14_75L6 | 08/20/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | SUTTON | 453761 | 01590 | 499 |  |  | Solar |  | 05_01_225W2 | 09/08/2022 | 10/04/2022 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/31/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175745 | 01610 | 496.8 |  |  | Solar |  | 05_01_304W6 | 10/28/2014 | 10/28/2014 | 5 | 0 | 5 | 11/05/2014 | 11/05/2014 | 151 | 16 | 135 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 3/31/2015 | N | EXP | -27 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 636464 | 01602 | 6 |  |  | Solar |  | 05_01_4J336 | 09/16/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | DIGHTON | 542169 | 02715 | 7.6 |  |  | Solar |  | 05_01_6W2 | 08/05/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 08/05/2023 | 11/11/2024 | Y | EXP | 365 | 02/16/2024 | 04/11/2024 | 56 | 0 | 56 |  |  | 5/6/2024 | Connected |  | N
National Grid | SALEM | 393641 | 01970 | 10 |  |  | Solar |  | 05_05_19W74 | 12/06/2021 | 12/07/2021 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  | 1/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | CHELMSFORD | 223128 | 01824 | 120 |  |  | Solar |  | 05_12_2W1 | 04/27/2019 | 05/21/2019 | 17 | 17 | 0 | 05/22/2019 | 05/22/2019 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 8/13/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | HAVERHILL | 175754 | 01830 | 100 |  |  | Solar |  | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | ANDOVER | 604752 | 01810 | 10 |  |  | Solar |  | 05_14_48L2 | 04/17/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 04/17/2024 | 8/5/2025 | Y | EXP | 365 | 09/12/2024 | 03/31/2025 | 201 | 0 | 201 |  |  | 4/10/2025 | Connected |  | N
National Grid | METHUEN | 710704 | 01844 | 15.32 |  |  | Solar |  | 05_14_63L1 | 08/08/2025 | 08/15/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 637971 | 01453 | 7.6 |  |  | Solar |  | 05_14_75L6 | 09/09/2024 | 09/30/2024 | 6 | 5 | 1 | 10/01/2024 | 10/01/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 582926 | 01590 | 0 |  |  | Solar |  | 05_01_225W3 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 175807 | 01610 | 27.95 |  |  | Solar |  | 05_01_304W6 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 |  | 10/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 1/22/2016 | Connected |  | N
National Grid | WORCESTER | 636567 | 01602 | 10 |  |  | Solar |  | 05_01_4J336 | 08/29/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | DIGHTON | 581993 | 02715 | 9.86 |  |  | Solar |  | 05_01_6W2 | 01/22/2024 | 01/23/2024 | 1 | 0 | 1 | 01/24/2024 | 01/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2024 | Connected |  | N
National Grid | SALEM | 402596 | 01970 | 2.03 |  |  | Solar |  | 05_05_19W74 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 5/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2022 | Connected |  | N
National Grid | CHELMSFORD | 235959 | 01824 | 3.8 |  |  | Solar |  | 05_12_2W1 | 07/22/2019 | 07/25/2019 | 3 | 3 | 0 | 07/26/2019 | 07/26/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 8/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | HAVERHILL | 178333 | 01830 | 7.6 |  |  | Solar |  | 05_14_16L4 | 11/17/2017 | 11/17/2017 | 37 | 36 | 1 | 01/12/2018 | 01/12/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 |  | 11/22/2018 | N | EXP | 310 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 627679 | 01844 | 6 |  |  | Solar |  | 05_14_48L2 | 07/25/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 8/27/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | DRACUT | 717012 | 01826 | 10 |  |  | Solar |  | 05_14_63L1 | 09/05/2025 | 09/16/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 645604 | 01453 | 11.4 |  |  | Solar |  | 05_14_75L6 | 10/08/2024 |  | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 676973 | 01590 | 840 |  |  | Solar |  | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2025 | 07/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 175861 | 01603 | 100 |  |  | Solar |  | 05_01_304W6 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 |  | 8/10/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/19/2015 | 8/19/2015 | 12/18/2015 | Connected |  | N
National Grid | WORCESTER | 651217 | 01603 | 7.6 |  |  | Solar |  | 05_01_4J336 | 11/01/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 | 12/31/2024 | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | DIGHTON | 583917 | 02764 | 4.93 |  |  | Solar |  | 05_01_6W2 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | SALEM | 425019 | 01970 | 7.68 |  |  | Solar |  | 05_05_19W74 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 290 | 270 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 06/27/2022 | 9/13/2024 | Y | EXP | 365 | 11/28/2023 | 01/16/2024 | 50 | 3 | 47 |  |  | 1/20/2024 | Connected |  | N
National Grid | CHELMSFORD | 256763 | 01824 | 5 |  |  | Solar |  | 05_12_2W1 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 | 06/10/2020 | 06/22/2020 | 12 | 0 | 12 |  |  | 7/6/2020 | Connected |  | N
National Grid | HAVERHILL | 178633 | 01832 | 9 |  |  | Solar |  | 05_14_16L4 | 04/09/2018 | 04/09/2018 | 7 | 7 | 0 | 04/25/2018 | 04/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 633406 | 01844 | 3.8 |  |  | Solar |  | 05_14_48L2 | 08/20/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 08/20/2024 | 1/8/2026 | Y | EXP | 365 | 08/28/2025 |  | 127 | 0 | 127 |  |  | 12/4/2025 | Connected |  | N
National Grid | METHUEN | 722551 | 01844 | 5.584 |  |  | Solar |  | 05_14_63L1 | 09/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 652506 | 01523 | 12.18 |  |  | Solar |  | 05_14_75L6 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | SUTTON | 684731 | 01590 | 6.67 |  |  | Solar |  | 05_01_225W3 | 04/11/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 175902 | 01603 | 308 |  |  | Solar |  | 05_01_304W6 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 254 | 0 | 254 | 01/04/2016 | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 10/4/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 656348 | 01603 | 7.6 |  |  | Solar |  | 05_01_4J336 | 11/22/2024 | 03/04/2025 | 55 | 50 | 5 | 03/05/2025 | 03/05/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | DIGHTON | 592273 | 02715 | 3 |  |  | Solar |  | 05_01_6W2 | 03/08/2024 | 03/29/2024 | 16 | 13 | 3 | 04/01/2024 | 04/01/2024 | 81 | 67 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 03/08/2024 | 7/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 458078 | 01970 | 13 |  |  | Solar |  | 05_05_19W74 | 09/15/2022 | 09/16/2022 | 1 | 0 | 1 | 09/19/2022 | 09/19/2022 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 263264 | 01824 | 6 |  |  | Solar |  | 05_12_2W1 | 12/05/2019 | 12/15/2019 | 6 | 0 | 6 | 12/16/2019 | 12/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/05/2019 | 12/5/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | HAVERHILL | 194082 | 01830 | 9 |  |  | Solar |  | 05_14_16L4 | 09/19/2018 | 10/09/2018 | 1 | 0 | 1 | 10/10/2018 | 10/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/19/2018 | 10/31/2019 | Y | EXP | 365 | 03/07/2019 | 03/19/2019 | 12 | 0 | 12 |  |  | 5/25/2019 | Connected |  | N
National Grid | METHUEN | 641356 | 01844 | 4.64 |  |  | Solar |  | 05_14_48L2 | 09/20/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/20/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | METHUEN | 722050 | 01844 |  |  |  | Battery Add-On |  | 05_14_63L1 | 10/15/2025 | 10/31/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 654316 | 01453 | 8.91 |  |  | Solar |  | 05_14_75L6 | 11/14/2024 | 12/17/2024 | 10 | 6 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/14/2024 | 2/19/2026 | Y | EXP | 365 | 04/16/2025 |  | 261 | 0 | 261 |  |  | 3/28/2025 | Connected |  | N
National Grid | SUTTON | 683667 | 01590 | 10 |  |  | Solar |  | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 25 | 24 | 1 | 08/21/2025 | 08/21/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 04/08/2025 | 9/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 175978 | 01610 | 95 |  |  | Solar |  | 05_01_304W6 | 01/23/2015 | 01/23/2015 | 24 | 22 | 2 | 03/02/2015 | 03/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2015 |  | 6/30/2015 | N | EXP | 84 |  |  | 0 | 0 | 0 | 4/8/2015 | 4/8/2015 | 6/11/2015 | Connected |  | Y
National Grid | WORCESTER | 656746 | 01602 | 5.76 |  |  | Solar |  | 05_01_4J336 | 11/25/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | DIGHTON | 605256 | 02764 | 5 |  |  | Solar |  | 05_01_6W2 | 05/01/2024 | 05/02/2024 | 2 | 1 | 1 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 | 05/01/2024 | 6/12/2025 | Y | EXP | 365 | 10/18/2024 | 10/24/2024 | 7 | 0 | 7 |  |  | 10/28/2024 | Connected |  | N
National Grid | SALEM | 532519 | 01970 | 11.4 |  |  | Solar |  | 05_05_19W74 | 06/13/2023 | 06/26/2023 | 8 | 5 | 3 | 06/27/2023 | 06/27/2023 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | CHELMSFORD | 266036 | 01824 | 7.6 |  |  | Solar |  | 05_12_2W1 | 09/24/2020 | 09/25/2020 | 0 | 0 | 0 | 09/28/2020 | 09/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 09/24/2020 | 10/15/2021 | Y | EXP |  | 02/05/2021 | 03/17/2021 | 40 | 0 | 40 |  |  | 3/20/2021 | Connected |  | N
National Grid | HAVERHILL | 196414 | 01830 | 9.6 |  |  | Solar |  | 05_14_16L4 | 11/09/2018 | 12/07/2018 | 16 | 15 | 1 | 12/10/2018 | 12/10/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 642251 | 01844 | 10 |  |  | Solar |  | 05_14_48L2 | 09/25/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/25/2024 | 11/27/2025 | Y | EXP | 365 | 03/15/2025 | 09/06/2025 | 176 | 0 | 176 |  |  | 9/18/2025 | Connected |  | N
National Grid | METHUEN | 725342 | 01844 | 3.8 |  |  | Solar |  | 05_14_63L1 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 34 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 | 10/09/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 654188 | 01453 | 7.6 |  |  | Solar |  | 05_14_75L6 | 11/18/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/12/2026 | Y | EXP | 365 | 05/07/2025 | 07/10/2025 | 65 | 0 | 65 |  |  | 7/25/2025 | Connected |  | N
National Grid | MILLBURY | 711810 | 01527 | 10 |  |  | Solar |  | 05_01_225W3 | 08/13/2025 | 08/26/2025 | 8 | 5 | 3 | 08/27/2025 | 08/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 177386 | 01603 | 17.25 |  |  | Solar |  | 05_01_304W6 | 11/29/2016 | 11/29/2016 | 14 | 14 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/5/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | LEICESTER | 730887 | 01611 | 11.52 |  |  | Solar |  | 05_01_4J339 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 607670 | 02715 | 7.6 |  |  | Solar |  | 05_01_6W2 | 04/30/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 19 | 7 | 12 | 06/17/2024 | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 8/1/2024 | 04/30/2024 | 10/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | SALEM | 541084 | 01970 | 10 |  |  | Solar |  | 05_05_19W74 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 58 | 37 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 | 07/18/2023 | 10/18/2024 | Y | EXP | 365 | 10/25/2023 | 01/22/2024 | 90 | 3 | 87 |  |  | 1/25/2024 | Connected |  | N
National Grid | CHELMSFORD | 270246 | 01824 | 6.3 |  |  | Solar |  | 05_12_2W1 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/02/2020 | 5/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2021 | Connected |  | N
National Grid | HAVERHILL | 203428 | 01830 | 3.8 |  |  | Solar |  | 05_14_16L4 | 12/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 647358 | 01841 | 15.2 |  |  | Solar |  | 05_14_48L2 | 11/07/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | METHUEN | 730850 | 01844 | 5.76 |  |  | Solar |  | 05_14_63L1 | 11/03/2025 | 11/10/2025 | 5 | 0 | 5 | 11/12/2025 | 11/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 657523 | 01453 | 5.76 |  |  | Solar |  | 05_14_75L6 | 11/28/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | SUTTON | 718439 | 01590 | 5.76 |  |  | Solar |  | 05_01_225W3 | 09/11/2025 | 09/26/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 178598 | 01603 | 2500 |  |  | Solar |  | 05_01_304W6 | 04/06/2018 | 04/06/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/21/2018 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 643519 | 01603 | 19 |  |  | Solar |  | 05_01_4J339 | 10/01/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 165 | 25 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 616449 | 02764 | 3.8 |  |  | Solar |  | 05_01_6W2 | 06/07/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | SALEM | 543936 | 01970 | 7.68 |  |  | Solar |  | 05_05_19W74 | 07/28/2023 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 279630 | 01824 | 10 |  |  | Solar |  | 05_12_2W1 | 02/25/2020 | 02/26/2020 | 0 | 0 | 0 | 02/27/2020 | 02/27/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2020 | 02/25/2020 | 2/25/2021 | Y | EXP | 365 | 05/15/2020 | 06/03/2020 | 19 | 0 | 19 |  |  | 6/4/2020 | Connected |  | N
National Grid | HAVERHILL | 290312 | 01832 | 9.6 |  |  | Solar |  | 05_14_16L4 | 05/07/2020 | 05/13/2020 | 3 | 0 | 3 | 05/13/2020 | 05/13/2020 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2020 |  | 4/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | METHUEN | 650991 | 01844 | 5.76 |  |  | Solar |  | 05_14_48L2 | 11/12/2024 | 12/09/2024 | 1 | 0 | 1 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | METHUEN | 738581 | 01844 | 11.5 |  |  | Solar |  | 05_14_63L1 | 12/08/2025 | 12/19/2025 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 661225 | 01453 | 5.76 |  |  | Solar |  | 05_14_75L6 | 12/17/2024 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 12/17/2024 | 4/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | SUTTON | 724994 | 01590 | 7.6 |  |  | Solar |  | 05_01_225W3 | 10/08/2025 | 10/14/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 178682 | 01610 | 4000 |  |  | Solar |  | 05_01_304W6 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 137 | 0 | 137 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 647997 | 01603 | 15.2 |  |  | Solar |  | 05_01_4J339 | 10/17/2024 | 11/12/2024 | 17 | 15 | 2 | 11/13/2024 | 11/13/2024 | 74 | 49 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | SOMERSET | 622524 | 02726 | 10 |  |  | Solar |  | 05_01_6W2 | 07/03/2024 | 07/16/2024 | 3 | 0 | 3 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/29/2025 | Y | EXP | 365 | 10/10/2024 | 10/23/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | SALEM | 565988 | 01970 | 10 |  |  | Solar |  | 05_05_19W74 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 281332 | 01824 | 12 |  |  | Solar |  | 05_12_2W1 | 02/27/2020 | 03/04/2020 | 3 | 3 | 0 | 03/05/2020 | 03/05/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2020 |  | 3/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N
National Grid | HAVERHILL | 337957 | 01832 | 7.6 |  |  | Solar |  | 05_14_16L4 | 01/21/2021 | 02/17/2021 | 18 | 17 | 1 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | METHUEN | 653889 | 01844 | 3.8 |  |  | Solar |  | 05_14_48L2 | 12/04/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/04/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | METHUEN | 175873 | 01844 | 16 |  |  | Solar |  | 05_14_63L1 | 03/09/2015 | 03/09/2015 | 11 | 9 | 2 | 03/26/2015 | 03/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 8/10/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 7/21/2015 | 7/21/2015 | 12/9/2015 | Connected |  | N
National Grid | LEOMINSTER | 661267 | 01453 | 2.32 |  |  | Solar |  | 05_14_75L6 | 12/17/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 725837 | 01527 | 200 |  |  | Solar |  | 05_01_225W3 | 11/26/2025 |  | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 184056 | 01610 | 999 |  |  | Battery Add-On |  | 05_01_304W6 | 05/01/2018 | 05/01/2018 | 6 | 0 | 6 |  |  | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661902 | 01602 | 5.76 |  |  | Solar |  | 05_01_4J339 | 12/20/2024 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | Y
National Grid | DIGHTON | 636208 | 02764 | 3.8 |  |  | Solar |  | 05_01_6W2 | 08/28/2024 | 09/09/2024 | 4 | 0 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | SALEM | 611840 | 01970 | 3 |  |  | Solar |  | 05_05_19W74 | 05/31/2024 | 06/21/2024 | 7 | 6 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | CHELMSFORD | 314997 | 01824 | 3.8 |  |  | Solar |  | 05_12_2W1 | 10/07/2020 | 10/12/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 10/07/2020 | 7/7/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2021 | Connected |  | Y
National Grid | HAVERHILL | 398325 | 01832 | 9.772 |  |  | Solar |  | 05_14_16L4 | 11/30/2021 | 12/20/2021 | 14 | 13 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 11/30/2021 | 4/15/2023 | Y | EXP | 365 | 04/12/2022 | 04/13/2022 | 2 | 0 | 2 |  |  | 5/20/2022 | Connected |  | N
National Grid | METHUEN | 657537 | 01844 | 3.8 |  |  | Solar |  | 05_14_48L2 | 11/28/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 | 05/30/2025 | 12/01/2025 | 186 | 0 | 186 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176711 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 01/07/2016 | 01/07/2016 | 10 | 10 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/13/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 5/9/2016 | Connected |  | N
National Grid | LEOMINSTER | 675285 | 01453 | 10 |  |  | Solar |  | 05_14_75L6 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 174125 | 01590 | 3000 |  |  | Solar |  | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2012 | 06/22/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2013 | 04/06/2012 | 12/1/2012 | Y | STD | -34 | 10/22/2013 | 02/22/2014 | 83 | 0 | 83 | 11/29/2013 | 11/29/2013 | 11/30/2013 | Connected |  | N
National Grid | WORCESTER | 184748 | 01610 | 594 |  |  | Solar |  | 05_01_304W6 | 05/31/2018 | 08/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/22/2018 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  | 8/21/2020 | N | STD | 403 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 686548 | 01602 | 17.86 |  |  | Solar |  | 05_01_4J339 | 05/30/2025 | 06/05/2025 | 4 | 0 | 4 | 06/06/2025 | 06/06/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | DIGHTON | 636971 | 02715 | 3.8 |  |  | Solar |  | 05_01_6W2 | 08/30/2024 | 12/04/2024 | 57 | 56 | 1 | 12/05/2024 | 12/05/2024 | 25 | 0 | 25 | 01/22/2025 | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 | 05/02/2025 | 05/30/2025 | 29 | 0 | 29 |  |  | 7/10/2025 | Connected |  | N
National Grid | SALEM | 614244 | 01970 | 11.4 |  |  | Solar |  | 05_05_19W74 | 05/30/2024 | 06/11/2024 | 9 | 7 | 2 | 06/12/2024 | 06/12/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 | 05/30/2024 | 8/5/2025 | Y | EXP | 365 | 08/29/2024 | 09/24/2024 | 27 | 0 | 27 |  |  | 9/25/2024 | Connected |  | N
National Grid | CHELMSFORD | 318458 | 01824 | 9.36 |  |  | Solar |  | 05_12_2W1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/10/2020 | 7/8/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2022 | Connected |  | N
National Grid | HAVERHILL | 402022 | 01830 | 187.5 |  |  | Solar |  | 05_14_16L4 | 12/20/2021 | 01/06/2022 | 13 | 5 | 8 |  |  | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 11/28/2024 | N | STD | 21 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | METHUEN | 658084 | 01844 | 5.76 |  |  | Solar |  | 05_14_48L2 | 12/03/2024 | 03/17/2025 | 61 | 57 | 4 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176841 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/05/2016 | 05/05/2016 | 449 | 0 | 449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 7/31/2018 | Y | EXP | 810 | 07/11/2017 | 07/28/2017 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 676647 | 01453 | 5.8 |  |  | Solar |  | 05_14_75L6 | 03/18/2025 | 03/26/2025 | 8 | 6 | 2 | 04/09/2025 | 04/09/2025 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 174136 | 01590 | 1000 |  |  | Solar |  | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 189175 | 01610 | 2050 |  |  | Solar |  | 05_01_304W6 | 09/11/2018 | 10/18/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 11/23/2018 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 699261 | 01602 | 5.76 |  |  | Solar |  | 05_01_4J339 | 06/18/2025 | 07/02/2025 | 33 | 30 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | DIGHTON | 643927 | 02715 | 5.76 |  |  | Solar |  | 05_01_6W2 | 10/01/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | SALEM | 616349 | 01970 | 7.6 |  |  | Solar |  | 05_05_19W74 | 06/07/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 13 | 6 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 06/07/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | CHELMSFORD | 326340 | 01824 | 8.7 |  |  | Solar |  | 05_12_2W1 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 | 02/03/2021 | 1/11/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | HAVERHILL | 418467 | 01830 | 6 |  |  | Solar |  | 05_14_16L4 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/08/2022 | 9/11/2023 | Y | EXP | 365 | 08/09/2022 | 08/29/2022 | 21 | 0 | 21 |  |  | 12/9/2022 | Connected |  | N
National Grid | METHUEN | 177252 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 157 | 0 | 157 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 693695 | 01844 | 20 |  |  | Solar |  | 05_14_75L6 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2025 | Connected |  | N
National Grid | LANCASTER | 174908 | 01523 | 499 |  |  | Solar |  | 05_01_225W3 | 09/14/2012 | 09/14/2012 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 202902 | 01590 | 0 |  |  | Battery Add-On |  | 05_01_304W6 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 1/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | Connected |  | N
National Grid | WORCESTER | 611044 | 01610 | 6.09 |  |  | Solar |  | 05_01_4J340 | 05/28/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N
National Grid | WORCESTER | 655083 | 01603 | 5.76 |  |  | Solar |  | 05_01_6W2 | 11/18/2024 | 01/30/2025 | 40 | 34 | 6 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 5/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | Y
National Grid | DIGHTON | 628852 | 02715 | 5 |  |  | Solar |  | 05_05_19W74 | 07/30/2024 | 08/13/2024 | 4 | 3 | 1 | 08/14/2024 | 08/14/2024 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | SALEM | 328907 | 01970 | 8.64 |  |  | Solar |  | 05_12_2W1 | 12/01/2020 | 12/08/2020 | 4 | 0 | 4 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 12/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2021 | Connected |  | N
National Grid | CHELMSFORD | 441231 | 01824 | 6 |  |  | Solar |  | 05_14_16L4 | 07/28/2022 | 07/29/2022 | 1 | 0 | 1 | 08/01/2022 | 08/01/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/28/2022 | 12/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N
National Grid | HAVERHILL | 660636 | 01830 | 3.8 |  |  | Solar |  | 05_14_48L2 | 12/13/2024 | 03/26/2025 | 56 | 52 | 4 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 12/13/2024 | 5/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177425 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 12/06/2016 | 12/06/2016 | 3 | 2 | 1 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 365 | 10/16/2017 | 11/16/2017 | 17 | 0 | 17 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | METHUEN | 618791 | 01844 | 160 |  |  | Solar |  | 05_14_76L1 | 07/11/2024 | 11/25/2024 | 94 | 85 | 9 | 11/26/2024 | 11/26/2024 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 6/16/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LANCASTER | 175018 | 01523 | 500 |  |  | Solar |  | 05_01_225W3 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 286 | 223 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 292740 | 01590 | 192 |  |  | Solar |  | 05_01_304W6 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 459951 | 01610 | 4999 |  |  | Solar |  | 05_01_525L1 | 11/02/2022 | 11/17/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 657449 | 01603 | 3.8 |  |  | Solar |  | 05_01_6W2 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 06/12/2025 | 07/15/2025 | 34 | 0 | 34 |  |  | 7/26/2025 | Connected |  | N
National Grid | SOMERSET | 647648 | 02726 | 3.8 |  |  | Solar |  | 05_05_19W74 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | SALEM | 379550 | 01970 | 0 |  |  | Solar |  | 05_12_2W1 | 09/02/2021 | 09/07/2021 | 2 | 0 | 2 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | CHELMSFORD | 468824 | 01824 | 6.144 |  |  | Solar |  | 05_14_16L4 | 03/22/2023 | 03/24/2023 | 2 | 0 | 2 | 03/27/2023 | 03/27/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/22/2023 | 7/13/2024 | Y | EXP | 365 | 07/06/2023 | 07/13/2023 | 8 | 0 | 8 |  |  | 9/23/2023 | Connected |  | N
National Grid | HAVERHILL | 660965 | 01830 | 3.8 |  |  | Solar |  | 05_14_48L2 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | METHUEN | 177824 | 01844 | 9.6 |  |  | Solar |  | 05_14_63L1 | 06/06/2017 | 06/06/2017 | 3 | 3 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/06/2017 | 6/13/2018 | Y | EXP | 365 | 08/08/2017 | 08/16/2017 | 6 | 0 | 6 | 2/14/2018 | 2/14/2018 | 2/20/2018 | Connected |  | N
National Grid | METHUEN | 722747 | 01844 | 22.8 |  |  | Solar |  | 05_14_76L1 | 09/30/2025 | 10/02/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 176193 | 01453 | 260 |  |  | Solar |  | 05_01_225W3 | 02/09/2015 | 02/09/2015 | 4 | 0 | 4 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 7/31/2015 | N | EXP | 156 |  |  | 0 | 0 | 0 | 10/7/2015 | 10/7/2015 | 10/7/2015 | Connected |  | N
National Grid | SUTTON | 294263 | 01590 | 10 |  |  | Solar |  | 05_01_304W6 | 06/02/2020 | 06/15/2020 | 8 | 8 | 0 | 06/16/2020 | 06/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | N
National Grid | WORCESTER | 715897 | 01610 | 5.76 |  |  | Solar |  | 05_01_525L1 | 09/01/2025 | 09/19/2025 | 26 | 22 | 4 | 11/13/2025 | 11/13/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 657837 | 01602 | 3.8 |  |  | Solar |  | 05_01_6W2 | 12/02/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 677411 | 02726 | 5.76 |  |  | Solar |  | 05_05_19W74 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 387155 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 10/27/2021 | 11/08/2021 | 9 | 5 | 4 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 | 10/27/2021 | 6/3/2023 | Y | EXP | 365 | 04/22/2022 | 05/26/2022 | 35 | 0 | 35 |  |  | 6/29/2022 | Connected |  | N
National Grid | CHELMSFORD | 555930 | 01824 | 10 |  |  | Solar |  | 05_14_16L4 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 | 12/05/2023 | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 682063 | 01830 | 5.76 |  |  | Solar |  | 05_14_48L2 | 04/01/2025 | 06/10/2025 | 28 | 24 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 | 04/01/2025 | 7/18/2026 | Y | EXP | 365 | 11/21/2025 |  | 42 | 0 | 42 |  |  | 12/9/2025 | Connected |  | N
National Grid | METHUEN | 178126 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 07/11/2017 | 07/11/2017 | 3 | 3 | 0 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2017 |  | 7/17/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/18/2017 | Connected |  | N
National Grid | HAVERHILL | 175917 | 01830 | 1000 |  |  | Solar |  | 05_14_76L1 | 03/12/2015 | 03/12/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 |  | 12/14/2016 | N | STD | 442 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176674 | 01453 | 100 |  |  | Solar |  | 05_01_225W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/10/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 1/6/2017 | 1/6/2017 | 1/4/2017 | Connected |  | N
National Grid | SUTTON | 305873 | 01590 | 1750 |  |  | Solar |  | 05_01_304W6 | 10/05/2020 | 10/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2020 | 11/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 730670 | 01535 | 15.2 |  |  | Solar |  | 05_01_525L1 | 11/06/2025 | 12/05/2025 | 19 | 16 | 3 | 12/08/2025 | 12/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 661445 | 01611 | 4.64 |  |  | Solar |  | 05_01_6W2 | 12/18/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 685887 | 02764 | 15.2 |  |  | Solar |  | 05_05_19W74 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 406678 | 01970 | 15.2 |  |  | Solar |  | 05_12_2W1 | 01/14/2022 | 01/18/2022 | 1 | 0 | 1 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 589144 | 01824 | 3.8 |  |  | Solar |  | 05_14_16L4 | 02/22/2024 | 02/26/2024 | 3 | 1 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 06/19/2024 | 07/25/2024 | 37 | 0 | 37 |  |  | 8/21/2024 | Connected |  | N
National Grid | HAVERHILL | 698019 | 01830 | 4.48 |  |  | Solar |  | 05_14_48L2 | 06/12/2025 | 07/29/2025 | 2 | 0 | 2 | 08/11/2025 | 08/11/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 188740 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 07/10/2018 | 09/04/2018 | 39 | 33 | 6 | 12/17/2018 | 12/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 07/10/2018 | 2/18/2020 | Y | EXP | 365 | 05/21/2019 | 07/12/2019 | 52 | 0 | 52 |  |  | 1/10/2020 | Connected |  | N
National Grid | HAVERHILL | 196058 | 01830 | 240 |  |  | Solar |  | 05_14_76L1 | 10/16/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 11/21/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/16/2018 | 3/9/2027 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176871 | 01453 | 6 |  |  | Solar |  | 05_01_225W3 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 319 | 07/07/2016 | 07/27/2016 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | SUTTON | 308498 | 01590 | 4990 |  |  | Solar |  | 05_01_304W6 | 09/14/2020 | 09/28/2020 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2020 | 10/24/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 174425 | 01535 | 1000 |  |  | Solar |  | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 662668 | 01603 | 4.225 |  |  | Solar |  | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 9 | 7 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | DIGHTON | 688155 | 02715 | 15.58 |  |  | Solar |  | 05_05_19W74 | 04/28/2025 | 05/05/2025 | 5 | 1 | 4 | 05/06/2025 | 05/06/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 04/28/2025 | 7/11/2026 | Y | EXP | 365 | 08/19/2025 | 10/03/2025 | 46 | 0 | 46 |  |  | 11/1/2025 | Connected |  | N
National Grid | SALEM | 415655 | 01970 | 10 |  |  | Solar |  | 05_12_2W1 | 03/14/2022 | 03/23/2022 | 7 | 3 | 4 | 03/24/2022 | 03/24/2022 | 54 | 26 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 637093 | 01824 | 10 |  |  | Solar |  | 05_14_16L4 | 09/02/2024 | 09/16/2024 | 1 | 0 | 1 | 09/17/2024 | 09/17/2024 | 20 | 13 | 7 | 12/13/2024 | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/23/2026 | N | EXP | 365 | 06/06/2025 | 06/13/2025 | 8 | 0 | 8 |  |  | 7/9/2025 | Connected |  | N
National Grid | HAVERHILL | 707779 | 01830 | 6.08 |  |  | Solar |  | 05_14_48L2 | 07/30/2025 | 08/04/2025 | 3 | 0 | 3 | 08/05/2025 | 08/05/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | METHUEN | 194880 | 01844 | 3.8 |  |  | Solar |  | 05_14_63L1 | 08/31/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 196057 | 01830 | 960 |  |  | Solar |  | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178266 | 01453 | 990 |  |  | Solar |  | 05_01_225W3 | 01/08/2018 | 01/08/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2018 | 01/08/2018 | 8/17/2020 | Y | STD | 399 | 01/17/2020 | 06/04/2020 | 139 | 0 | 139 | 6/18/2020 | 6/22/2020 | 8/10/2020 | Connected |  | N
National Grid | SUTTON | 310798 | 01590 | 4990 |  |  | Solar |  | 05_01_304W6 | 09/17/2020 | 09/30/2020 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 174424 | 01535 | 1000 |  |  | Solar |  | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 662627 | 01602 | 6.825 |  |  | Solar |  | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 12/26/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | DIGHTON | 690064 | 02764 | 18.62 |  |  | Solar |  | 05_05_19W74 | 05/06/2025 | 05/16/2025 | 7 | 0 | 7 | 05/19/2025 | 05/19/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 05/06/2025 | 6/12/2026 | Y | EXP | 365 | 06/25/2025 | 07/23/2025 | 29 | 0 | 29 |  |  | 9/6/2025 | Connected |  | N
National Grid | SALEM | 437523 | 01970 | 15.2 |  |  | Solar |  | 05_12_2W1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 06/14/2022 | 2/29/2024 | Y | EXP | 365 | 01/25/2023 | 04/17/2023 | 83 | 0 | 83 |  |  | 5/22/2023 | Connected |  | N
National Grid | CHELMSFORD | 644852 | 01824 | 7.6 |  |  | Solar |  | 05_14_16L4 | 10/03/2024 | 10/31/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/03/2024 | 12/17/2025 | Y | EXP | 365 | 01/16/2025 | 03/03/2025 | 46 | 0 | 46 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 618825 | 01830 | 7.6 |  |  | Solar |  | 05_14_48L3 | 06/18/2024 | 06/24/2024 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 06/18/2024 | 8/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 198050 | 01844 | 5 |  |  | Solar |  | 05_14_63L1 | 10/09/2018 | 10/22/2018 | 7 | 6 | 1 | 10/23/2018 | 10/23/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 | 10/09/2018 | 5/22/2019 | Y | EXP | 198 | 01/29/2019 | 02/05/2019 | 7 | 0 | 7 |  |  | 3/15/2019 | Connected |  | N
National Grid | HAVERHILL | 196056 | 01830 | 3600 |  |  | Solar |  | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 197643 | 01453 | 10 |  |  | Solar |  | 05_01_225W3 | 11/13/2018 | 04/22/2019 | 108 | 103 | 5 | 04/23/2019 | 04/23/2019 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 348697 | 01590 | 9.28 |  |  | Solar |  | 05_01_304W6 | 04/06/2021 | 04/07/2021 | 0 | 0 | 0 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2022 | Connected |  | N
National Grid | NORTH BROOKFIELD | 174422 | 01535 | 3000 |  |  | Solar |  | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 | 11/23/2011 | 10/31/2012 | Y | STD | -34 | 02/13/2014 | 06/13/2014 | 82 | 0 | 82 | 6/16/2014 | 6/16/2014 | 6/16/2014 | Connected |  | N
National Grid | WORCESTER | 663489 | 01603 | 3.8 |  |  | Solar |  | 05_01_6W2 | 01/02/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/02/2025 | 3/14/2026 | Y | EXP | 365 | 05/16/2025 |  | 231 | 0 | 231 |  |  | 12/9/2025 | Connected |  | N
National Grid | SOMERSET | 689939 | 02726 | 23.18 |  |  | Solar |  | 05_05_19W74 | 05/06/2025 | 05/21/2025 | 10 | 7 | 3 | 05/22/2025 | 05/22/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 8/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | SALEM | 460824 | 01970 | 6 |  |  | Solar |  | 05_12_2W1 | 09/26/2022 | 09/28/2022 | 2 | 0 | 2 | 09/29/2022 | 09/29/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/26/2022 | 9/3/2024 | Y | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 666027 | 01824 | 13.36 |  |  | Solar |  | 05_14_16L4 | 01/17/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 28 | 8 | 20 | 04/22/2025 | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 6/10/2025 | 01/17/2025 | 6/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | HAVERHILL | 177399 | 01830 | 75 |  |  | Solar |  | 05_14_48L3 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 | 06/29/2016 | 06/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/28/2016 | 7/5/2017 | Y | EXP | 310 | 08/03/2016 | 09/21/2016 | 34 | 0 | 34 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | METHUEN | 204929 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 02/06/2019 | 02/28/2019 | 14 | 7 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2019 | Connected |  | N
National Grid | HAVERHILL | 245548 | 01830 | 17.6 |  |  | Solar |  | 05_14_76L1 | 07/26/2019 | 07/29/2019 | 0 | 0 | 0 | 07/30/2019 | 07/30/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 7/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 204026 | 01523 | 500 |  |  | Solar |  | 05_01_225W3 | 01/16/2019 | 02/07/2019 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2019 | 02/27/2019 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 382260 | 01590 | 7.6 |  |  | Solar |  | 05_01_304W6 | 09/15/2021 | 09/17/2021 | 2 | 1 | 1 | 09/20/2021 | 09/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 3/17/2023 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 175219 | 01535 | 18 |  |  | Solar |  | 05_01_525L1 | 11/03/2014 | 11/03/2014 | 6 | 2 | 4 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 6/1/2015 | N | EXP | 199 |  |  | 0 | 0 | 0 | 2/18/2015 | 2/18/2015 | 9/30/2015 | Connected |  | N
National Grid | WORCESTER | 667926 | 01602 | 7.6 |  |  | Solar |  | 05_01_6W2 | 01/27/2025 | 02/14/2025 | 5 | 0 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | DIGHTON | 715587 | 02764 | 30 |  |  | Solar |  | 05_05_19W74 | 08/29/2025 | 09/09/2025 | 5 | 3 | 2 | 09/10/2025 | 09/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | SALEM | 557503 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 10/18/2023 | 10/23/2023 | 3 | 0 | 3 | 10/24/2023 | 10/24/2023 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 672940 | 01824 | 3.8 |  |  | Solar |  | 05_14_16L4 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 100 | 86 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 196416 | 01830 | 66.6 |  |  | Solar |  | 05_14_48L3 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 7/1/2020 | N | EXP | 406 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 205072 | 01844 | 5 |  |  | Solar |  | 05_14_63L1 | 02/07/2019 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 295965 | 01830 | 9.36 |  |  | Solar |  | 05_14_76L1 | 06/11/2020 | 07/06/2020 | 16 | 11 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | LEOMINSTER | 233067 | 01453 | 7.6 |  |  | Solar |  | 05_01_225W3 | 07/05/2019 | 07/08/2019 | 0 | 0 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 07/05/2019 | 5/28/2020 | Y | EXP | 365 | 12/17/2019 | 01/24/2020 | 38 | 0 | 38 |  |  | 2/14/2020 | Connected |  | N
National Grid | SUTTON | 457862 | 01590 | 1800 |  |  | Solar |  | 05_01_304W6 | 11/03/2022 | 11/17/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 175629 | 01535 | 120 |  |  | Solar |  | 05_01_525L1 | 08/06/2014 | 08/06/2014 | 7 | 0 | 7 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2014 |  | 1/30/2015 | N | EXP | 135 |  |  | 0 | 0 | 0 | 9/17/2014 | 9/17/2014 | 2/20/2015 | Connected |  | N
National Grid | WORCESTER | 670286 | 01602 | 3.49 |  |  | Solar |  | 05_01_6W2 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | DIGHTON | 711394 | 02764 | 13.8 |  |  | Solar |  | 05_05_1J1 | 08/12/2025 | 09/11/2025 | 2 | 0 | 2 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 | 08/12/2025 | 11/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SALEM | 569404 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 11/27/2023 | 11/28/2023 | 1 | 0 | 1 | 11/29/2023 | 11/29/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/27/2023 | 4/20/2025 | Y | EXP | 365 | 08/07/2024 | 10/24/2024 | 79 | 0 | 79 |  |  | 10/30/2024 | Connected |  | N
National Grid | LOWELL | 677854 | 01851 | 7.6 |  |  | Solar |  | 05_14_16L4 | 03/17/2025 | 03/20/2025 | 3 | 0 | 3 | 03/21/2025 | 03/21/2025 | 100 | 80 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 413354 | 01830 | 3.8 |  |  | Solar |  | 05_14_48L3 | 02/25/2022 | 03/01/2022 | 2 | 0 | 2 | 03/02/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2022 | Connected |  | N
National Grid | METHUEN | 211661 | 01844 | 5 |  |  | Solar |  | 05_14_63L1 | 03/05/2019 | 03/06/2019 | 0 | 0 | 0 | 03/07/2019 | 03/07/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 448164 | 01830 | 30 |  |  | Solar |  | 05_14_76L1 | 07/31/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 231390 | 01453 | 10 |  |  | Solar |  | 05_01_225W3 | 05/28/2019 | 06/27/2019 | 22 | 17 | 5 | 06/28/2019 | 06/28/2019 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | SUTTON | 473792 | 01590 | 9.28 |  |  | Solar |  | 05_01_304W6 | 12/07/2022 | 12/14/2022 | 6 | 5 | 1 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | NORTH BROOKFIELD | 177746 | 01535 | 15 |  |  | Solar |  | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 48 | 48 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 6/5/2018 | N | EXP | 286 |  |  | 0 | 0 | 0 | 12/26/2017 | 12/26/2017 | 12/26/2017 | Connected |  | N
National Grid | WORCESTER | 680789 | 01603 | 15.08 |  |  | Solar |  | 05_01_6W2 | 03/26/2025 | 03/28/2025 | 3 | 1 | 2 | 03/31/2025 | 03/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | DIGHTON | 721844 | 02764 | 10 |  |  | Solar |  | 05_05_1J1 | 09/25/2025 | 10/13/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 597666 | 01970 | 3.8 |  |  | Solar |  | 05_12_2W1 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 4/16/2025 | Y | EXP | 365 | 05/24/2024 | 08/21/2024 | 90 | 0 | 90 |  |  | 8/5/2024 | Connected |  | N
National Grid | CHELMSFORD | 624477 | 01824 | 200 |  |  | Solar |  | 05_14_16L7 | 07/25/2024 | 08/26/2024 | 22 | 16 | 6 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HAVERHILL | 669659 | 01830 | 0 |  |  | Battery Add-On |  | 05_14_48L3 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 59 | 2 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | METHUEN | 219723 | 01844 | 5 |  |  | Solar |  | 05_14_63L1 | 05/01/2019 | 05/01/2019 | 0 | 0 | 0 | 05/02/2019 | 05/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 05/01/2019 | 1/21/2020 | Y | EXP | 263 | 07/16/2019 | 08/12/2019 | 27 | 0 | 27 |  |  | 10/8/2019 | Connected |  | N
National Grid | HAVERHILL | 461652 | 01830 | 0 |  |  | Solar |  | 05_14_76L1 | 09/28/2022 | 10/04/2022 | 4 | 3 | 1 | 10/05/2022 | 10/05/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 246795 | 01453 | 10 |  |  | Solar |  | 05_01_225W3 | 11/20/2019 | 03/12/2020 | 76 | 76 | 0 | 03/13/2020 | 03/13/2020 | 68 | 46 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2020 |  | 11/20/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 570231 | 01527 | 10 |  |  | Solar |  | 05_01_304W6 | 11/16/2023 | 11/21/2023 | 3 | 1 | 2 | 11/22/2023 | 11/22/2023 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 11/16/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 08/28/2024 | 85 | 0 | 85 |  |  | 9/5/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 177743 | 01535 | 5 |  |  | Solar |  | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 47 | 47 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 5/31/2018 | N | EXP | 281 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/20/2017 | Connected |  | N
National Grid | WORCESTER | 683397 | 01602 | 7.6 |  |  | Solar |  | 05_01_6W2 | 04/07/2025 | 04/24/2025 | 4 | 1 | 3 | 05/08/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/07/2025 | 6/12/2026 | Y | EXP | 365 | 10/02/2025 | 10/03/2025 | 2 | 0 | 2 |  |  | 10/7/2025 | Connected |  | N
National Grid | ATTLEBORO | 470212 | 02703 | 6 |  |  | Solar |  | 05_05_1J1 | 01/24/2023 | 01/26/2023 | 2 | 0 | 2 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/24/2023 | 6/7/2024 | Y | EXP | 365 | 05/16/2023 | 06/08/2023 | 24 | 0 | 24 |  |  | 7/10/2023 | Connected |  | N
National Grid | SALEM | 641278 | 01970 | 5.76 |  |  | Solar |  | 05_12_2W1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 11/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | CHELMSFORD | 346400 | 01824 | 250 |  |  | Solar |  | 05_14_16L7 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 134 | 109 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 691118 | 01830 | 13.8 |  |  | Solar |  | 05_14_48L3 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | METHUEN | 216261 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 06/10/2019 | 06/21/2019 | 8 | 2 | 6 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/10/2019 | 9/16/2020 | Y | EXP | 365 | 05/27/2020 | 06/01/2020 | 5 | 0 | 5 |  |  | 7/2/2020 | Connected |  | N
National Grid | HAVERHILL | 500093 | 01830 | 15.36 |  |  | Solar |  | 05_14_76L1 | 02/07/2023 | 02/24/2023 | 13 | 12 | 1 | 02/27/2023 | 02/27/2023 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 02/07/2023 | 6/27/2024 | Y | EXP | 365 | 07/27/2023 | 10/25/2023 | 91 | 0 | 91 |  |  | 10/27/2023 | Connected |  | N
National Grid | LEOMINSTER | 272614 | 01453 | 499.9 |  |  | Solar |  | 05_01_225W3 | 02/20/2020 | 02/27/2020 | 5 | 2 | 3 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 | 02/20/2020 | 4/1/2024 | Y | STD | 1112 | 01/26/2024 | 04/22/2024 | 88 | 36 | 52 |  |  | 3/25/2024 | Connected |  | N
National Grid | SUTTON | 634466 | 01590 | 15.705 |  |  | Solar |  | 05_01_304W6 | 08/27/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 178239 | 01535 | 2000 |  |  | Solar |  | 05_01_525L1 | 02/20/2018 | 02/20/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2018 |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/25/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 687066 | 01603 | 15.2 |  |  | Solar |  | 05_01_6W2 | 04/23/2025 | 05/06/2025 | 9 | 5 | 4 | 05/07/2025 | 05/07/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | ATTLEBORO | 493074 | 02703 | 6 |  |  | Solar |  | 05_05_1J1 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 02/15/2023 | 7/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | SALEM | 648870 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 176414 | 01824 | 480 |  |  | Solar |  | 05_14_18L1 | 11/30/2015 | 11/30/2015 | 0 | 0 | 0 | 12/03/2015 | 12/03/2015 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 6/28/2018 | N | EXP | 786 |  |  | 0 | 0 | 0 |  |  | 6/22/2018 | Connected |  | N
National Grid | HAVERHILL | 685494 | 01830 | 180 |  |  | Solar |  | 05_14_48L4 | 04/16/2025 | 05/23/2025 | 26 | 17 | 9 | 05/27/2025 | 05/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 04/16/2025 | 4/22/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | METHUEN | 228343 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 07/08/2019 | 07/17/2019 | 6 | 6 | 0 | 07/18/2019 | 07/18/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 519947 | 01830 | 0 |  |  | Solar |  | 05_14_76L1 | 04/18/2023 | 04/21/2023 | 3 | 0 | 3 | 04/24/2023 | 04/24/2023 | 211 | 192 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | LEOMINSTER | 291030 | 01453 | 4948 |  |  | Other |  | 05_01_225W3 | 09/15/2020 | 09/24/2020 | 5 | 0 | 5 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 657952 | 01590 | 10 |  |  | Solar |  | 05_01_304W6 | 12/02/2024 |  | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 178298 | 01535 | 4980 |  |  | Solar |  | 05_01_525L1 | 11/15/2017 | 01/08/2018 | 34 | 23 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/09/2018 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2018 |  | 12/31/2019 | N | STD | 502 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 692430 | 01603 | 10 |  |  | Solar |  | 05_01_6W2 | 08/22/2025 | 09/11/2025 | 12 | 9 | 3 | 09/11/2025 | 09/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | ATTLEBORO | 647523 | 02703 | 7.6 |  |  | Solar |  | 05_05_1J1 | 10/22/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 10/22/2024 | 2/19/2026 | Y | EXP | 365 | 02/28/2025 | 07/16/2025 | 139 | 0 | 139 |  |  | 7/31/2025 | Connected |  | N
National Grid | SALEM | 652022 | 01970 | 5.76 |  |  | Solar |  | 05_12_2W1 | 11/13/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LOWELL | 177575 | 01852 | 480 |  |  | Solar |  | 05_14_18L1 | 09/19/2017 | 09/19/2017 | 28 | 19 | 9 | 11/03/2017 | 11/03/2017 | 12 | 12 | 0 | 02/09/2018 | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 3/23/2018 |  | 9/24/2018 | N | EXP | 185 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | HAVERHILL | 710023 | 01830 | 240 |  |  | Solar |  | 05_14_48L4 | 08/07/2025 | 09/16/2025 | 27 | 17 | 10 | 09/17/2025 | 09/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 242735 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 08/28/2019 | 08/29/2019 | 1 | 1 | 0 | 08/30/2019 | 08/30/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 | 08/28/2019 | 6/11/2020 | Y | EXP | 365 | 01/16/2020 | 02/20/2020 | 35 | 0 | 35 |  |  | 2/24/2020 | Connected |  | N
National Grid | HAVERHILL | 621040 | 01830 | 120 |  |  | Solar |  | 05_14_76L1 | 06/27/2024 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 310355 | 01453 | 6 |  |  | Solar |  | 05_01_225W3 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 05/25/2021 | 06/15/2021 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | SUTTON | 660387 | 01590 | 10 |  |  | Solar |  | 05_01_304W6 | 12/12/2024 | 12/30/2024 | 3 | 1 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 178480 | 01535 | 4999 |  |  | Solar |  | 05_01_525L1 | 04/03/2018 | 04/04/2018 | 12 | 12 | 0 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 711191 | 01603 | 5.76 |  |  | Solar |  | 05_01_6W2 | 08/11/2025 | 08/29/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | ATTLEBORO | 654221 | 02703 | 9.5 |  |  | Solar |  | 05_05_1J1 | 11/14/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 655422 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 11/21/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/21/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | BILLERICA | 189998 | 01821 | 15.2 |  |  | Solar |  | 05_14_18L1 | 07/05/2018 | 07/05/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 8/12/2019 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | HAVERHILL | 735933 | 01830 | 10 |  |  | Solar |  | 05_14_48L4 | 11/24/2025 | 11/25/2025 | 2 | 0 | 2 | 12/16/2025 | 12/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 239280 | 01841 | 7.6 |  |  | Solar |  | 05_14_63L1 | 06/27/2019 | 07/01/2019 | 2 | 2 | 0 | 07/02/2019 | 07/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/27/2019 | 4/22/2020 | Y | EXP | 287 | 01/03/2020 | 01/02/2020 | 0 | 0 | 0 |  |  | 1/10/2020 | Connected |  | N
National Grid | HAVERHILL | 623525 | 01830 | 10 |  |  | Solar |  | 05_14_76L1 | 07/09/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 07/09/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | LANCASTER | 317408 | 01523 | 7.25 |  |  | Solar |  | 05_01_225W3 | 10/16/2020 | 10/20/2020 | 1 | 0 | 1 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 667531 | 01590 | 4990 |  |  | Other |  | 05_01_304W6 | 02/25/2025 | 03/31/2025 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 184669 | 01585 | 1800 |  |  | Solar |  | 05_01_525L1 | 05/09/2018 | 05/09/2018 | 4 | 0 | 4 |  |  | 43 | 41 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 716720 | 01611 | 7.6 |  |  | Solar |  | 05_01_7J386 | 09/04/2025 | 09/22/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 09/04/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 699205 | 02703 | 5.7 |  |  | Solar |  | 05_05_1J1 | 06/30/2025 | 07/11/2025 | 7 | 4 | 3 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | SALEM | 663678 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W1 | 01/03/2025 | 02/05/2025 | 11 | 6 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 268241 | 01821 | 3.8 |  |  | Solar |  | 05_14_18L1 | 12/05/2019 | 12/10/2019 | 3 | 3 | 0 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2019 |  | 12/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176406 | 01832 | 720 |  |  | Solar |  | 05_14_48L4 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/13/2016 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 250742 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | HAVERHILL | 650180 | 01830 | 5.76 |  |  | Solar |  | 05_14_76L1 | 11/07/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 337622 | 01453 | 9.57 |  |  | Solar |  | 05_01_225W3 | 03/12/2021 | 03/18/2021 | 3 | 0 | 3 | 03/19/2021 | 03/19/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  | 9/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | SUTTON | 686174 | 01590 | 20 |  |  | Solar |  | 05_01_304W6 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | SPENCER | 195871 | 01562 | 2000 |  |  | Solar |  | 05_01_525L1 | 12/04/2018 | 12/24/2018 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 01/24/2019 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 730496 | 01602 | 5.76 |  |  | Solar |  | 05_01_7J386 | 10/30/2025 | 11/01/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 357772 | 02703 | 133.2 |  |  | Solar |  | 05_05_1J3 | 07/14/2021 | 08/10/2021 | 19 | 10 | 9 |  |  | 67 | 7 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 07/14/2021 | 3/23/2024 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 670542 | 01970 | 3.77 |  |  | Solar |  | 05_12_2W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | BILLERICA | 268931 | 01821 | 3.8 |  |  | Solar |  | 05_14_18L1 | 12/18/2019 | 12/18/2019 | 0 | 0 | 0 | 12/19/2019 | 12/19/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 |  | 12/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2020 | Connected |  | N
National Grid | HAVERHILL | 176573 | 01832 | 1462 |  |  | Solar |  | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 251517 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 10/10/2019 | 10/15/2019 | 14 | 12 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 |  | 10/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 651643 | 01830 | 7.6 |  |  | Solar |  | 05_14_76L1 | 11/13/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 396879 | 01453 | 1500 |  |  | Solar |  | 05_01_225W3 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 711907 | 01590 | 32.5 |  |  | Solar |  | 05_01_304W6 | 08/13/2025 | 08/18/2025 | 3 | 0 | 3 | 08/19/2025 | 08/19/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 385041 | 01005 | 2000 |  |  | Solar |  | 05_01_525L1 | 10/29/2021 | 12/02/2021 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178422 | 01603 | 4000 |  |  | Solar |  | 05_01_7J386 | 01/16/2018 | 02/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 03/20/2018 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 646703 | 02703 | 7.6 |  |  | Solar |  | 05_05_1J3 | 10/25/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 706875 | 01970 | 5.76 |  |  | Solar |  | 05_12_2W1 | 07/24/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 07/24/2025 | 9/25/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 12/17/2025 | Connected |  | N
National Grid | BILLERICA | 408871 | 01821 | 0 |  |  | Battery Add-On |  | 05_14_18L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/06/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176616 | 01832 | 1335.6 |  |  | Solar |  | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2016 |  | 2/22/2017 | N | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 273652 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 02/03/2020 | 02/06/2020 | 2 | 0 | 2 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 672054 | 01830 | 10 |  |  | Solar |  | 05_14_76L1 | 02/14/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 416915 | 01453 | 9.772 |  |  | Solar |  | 05_01_225W3 | 03/11/2022 | 03/29/2022 | 13 | 12 | 1 | 03/30/2022 | 03/30/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | SUTTON | 722290 | 01590 | 15.76 |  |  | Solar |  | 05_01_304W6 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 10/06/2025 | 10/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 406582 | 01535 | 6 |  |  | Solar |  | 05_01_525L1 | 02/09/2022 | 02/14/2022 | 3 | 0 | 3 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/09/2022 | 5/26/2023 | Y | EXP | 365 | 04/29/2022 | 05/19/2022 | 21 | 0 | 21 |  |  | 6/2/2022 | Connected |  | Y
National Grid | WORCESTER | 190628 | 01603 | 5 |  |  | Solar |  | 05_01_7J386 | 07/13/2018 | 08/29/2018 | 23 | 0 | 23 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 699742 | 02703 | 13.36 |  |  | Solar |  | 05_05_1J4 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 1/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | SALEM | 175372 | 01970 | 820 |  |  | Natural Gas |  | 05_12_2W2 | 02/19/2014 | 02/19/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2014 | 03/21/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 7/31/2014 | N | STD | -70 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/3/2015 | Connected |  | N
National Grid | BILLERICA | 672467 | 01821 | 5.76 |  |  | Solar |  | 05_14_18L1 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | HAVERHILL | 184579 | 01832 | 37.6 |  |  | Solar |  | 05_14_48L4 | 05/07/2018 | 05/07/2018 | 0 | 0 | 0 | 05/17/2018 | 05/17/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 282749 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 04/09/2020 | 04/21/2020 | 6 | 4 | 2 | 04/22/2020 | 04/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 | 04/09/2020 | 3/12/2021 | Y | EXP | 365 | 08/25/2020 | 10/13/2020 | 49 | 0 | 49 |  |  | 10/22/2020 | Connected |  | N
National Grid | HAVERHILL | 690910 | 01830 | 9.88 |  |  | Solar |  | 05_14_76L1 | 05/09/2025 | 05/29/2025 | 2 | 0 | 2 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/09/2025 | 6/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | LANCASTER | 426808 | 01523 | 9.57 |  |  | Solar |  | 05_01_225W3 | 07/14/2022 | 08/04/2022 | 16 | 9 | 7 | 08/05/2022 | 08/05/2022 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2023 | Connected |  | N
National Grid | SUTTON | 367448 | 01590 | 7.6 |  |  | Solar |  | 05_01_3J371 | 07/23/2021 | 12/20/2021 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | NORTH BROOKFIELD | 534547 | 01535 | 0 |  |  | Solar |  | 05_01_525L1 | 06/16/2023 | 06/23/2023 | 4 | 3 | 1 | 06/26/2023 | 06/26/2023 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 195599 | 01501 | 7.6 |  |  | Solar |  | 05_01_7J386 | 09/11/2018 | 12/03/2018 | 26 | 20 | 6 | 12/04/2018 | 12/04/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 188562 | 02703 | 15.2 |  |  | Solar |  | 05_05_1J4 | 06/19/2018 | 06/19/2018 | 2 | 0 | 2 | 06/29/2018 | 06/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2019 | Connected |  | N
National Grid | SALEM | 176003 | 01970 | 9.46 |  |  | Solar |  | 05_12_2W2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 7/27/2018 | Y | EXP | 1053 | 11/07/2017 | 05/03/2018 | 177 | 0 | 177 |  |  | 7/25/2018 | Connected |  | N
National Grid | BILLERICA | 687181 | 01821 | 7.6 |  |  | Solar |  | 05_14_18L1 | 04/23/2025 | 05/12/2025 | 3 | 0 | 3 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 | 06/25/2025 | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/23/2025 | 9/4/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/3/2025 | Connected |  | N
National Grid | HAVERHILL | 191108 | 01832 | 52.2 |  |  | Solar |  | 05_14_48L4 | 07/18/2018 | 08/06/2018 | 13 | 11 | 2 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 287307 | 01841 | 6 |  |  | Solar |  | 05_14_63L1 | 05/06/2020 | 05/08/2020 | 1 | 0 | 1 | 05/11/2020 | 05/11/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 554496 | 01832 | 480 |  |  | Solar |  | 05_14_76L3 | 10/06/2023 | 10/23/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 09/25/2024 | 232 | 216 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 10/06/2023 | 9/1/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 437424 | 01453 | 0 |  |  | Other |  | 05_01_225W3 | 09/22/2022 | 10/18/2022 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 11/09/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 728709 | 01590 | 15.7 |  |  | Solar |  | 05_01_3J372 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTH BROOKFIELD | 571567 | 01535 | 10 |  |  | Solar |  | 05_01_525L1 | 12/29/2023 | 02/07/2024 | 27 | 26 | 1 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 12/29/2023 | 2/28/2025 | Y | EXP | 365 | 04/30/2024 | 05/14/2024 | 15 | 0 | 15 |  |  | 7/3/2024 | Connected |  | N
National Grid | WORCESTER | 201180 | 01603 | 5 |  |  | Solar |  | 05_01_7J386 | 11/14/2018 | 11/15/2018 | 7 | 0 | 7 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 11/14/2018 | 11/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | ATTLEBORO | 476497 | 02703 | 240 |  |  | Solar |  | 05_05_2468W1 | 12/07/2022 | 01/06/2023 | 20 | 11 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 12/07/2022 | 4/4/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SALEM | 198887 | 01970 | 900 |  |  | Natural Gas |  | 05_12_2W2 | 10/19/2018 | 11/09/2018 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 04/02/2019 | 96 | 76 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/19/2018 |  | Y | STD | 365 | 02/25/2020 | 02/24/2020 | 0 | 0 | 0 |  |  | 4/3/2020 | Connected |  | N
National Grid | BILLERICA | 705483 | 01821 | 8.32 |  |  | Solar |  | 05_14_18L1 | 07/17/2025 | 08/15/2025 | 8 | 2 | 6 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | HAVERHILL | 267314 | 01830 | 37.8 |  |  | Solar |  | 05_14_48L4 | 06/18/2020 | 07/13/2020 | 17 | 17 | 0 | 07/14/2020 | 07/14/2020 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2020 |  | 6/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | METHUEN | 289256 | 01844 | 3.8 |  |  | Solar |  | 05_14_63L1 | 05/06/2020 | 05/07/2020 | 0 | 0 | 0 | 05/08/2020 | 05/08/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 670636 | 01830 | 11.5 |  |  | Solar |  | 05_14_76L3 | 02/14/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 466225 | 01453 | 13.824 |  |  | Solar |  | 05_01_225W3 | 10/18/2022 | 11/01/2022 | 10 | 8 | 2 | 11/02/2022 | 11/02/2022 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | WORCESTER | 446320 | 01602 | 16.24 |  |  | Solar |  | 05_01_3J372 | 08/30/2022 | 09/15/2022 | 11 | 9 | 2 | 09/16/2022 | 09/16/2022 | 134 | 117 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 646275 | 01535 | 5.76 |  |  | Solar |  | 05_01_525L1 | 10/10/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | WORCESTER | 227161 | 01603 | 5 |  |  | Solar |  | 05_01_7J386 | 05/20/2019 | 05/28/2019 | 63 | 11 | 52 | 05/29/2019 | 05/29/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 475897 | 02703 | 240 |  |  | Solar |  | 05_05_2468W1 | 11/18/2022 | 01/17/2023 | 38 | 28 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 11/18/2022 | 4/13/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SALEM | 213359 | 01970 | 0 |  |  | Solar |  | 05_12_2W2 | 03/12/2019 | 03/21/2019 | 6 | 0 | 6 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | BILLERICA | 176623 | 01821 | 3 |  |  | Solar |  | 05_14_18L2 | 04/14/2016 | 04/14/2016 | 2 | 2 | 0 | 04/19/2016 | 04/19/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/19/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 438729 | 01830 | 6 |  |  | Solar |  | 05_14_48L4 | 06/29/2022 | 07/05/2022 | 3 | 0 | 3 | 07/06/2022 | 07/06/2022 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 | 06/29/2022 | 8/25/2023 | Y | EXP | 365 | 10/13/2022 | 10/25/2022 | 13 | 0 | 13 |  |  | 10/31/2022 | Connected |  | Y
National Grid | LAWRENCE | 292786 | 01841 | 15.705 |  |  | Solar |  | 05_14_63L1 | 09/22/2020 | 03/23/2021 | 126 | 125 | 1 | 03/24/2021 | 03/24/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 10/9/2022 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | HAVERHILL | 686382 | 01830 | 33.725 |  |  | Solar |  | 05_14_76L3 | 04/21/2025 | 05/13/2025 | 15 | 11 | 4 | 05/14/2025 | 05/14/2025 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 491913 | 01453 | 3.8 |  |  | Solar |  | 05_01_225W3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 02/01/2023 | 6/7/2024 | Y | EXP | 365 | 05/02/2023 | 06/08/2023 | 38 | 0 | 38 |  |  | 8/10/2023 | Connected |  | N
National Grid | WORCESTER | 446313 | 01610 | 14.5 |  |  | Solar |  | 05_01_3J372 | 08/30/2022 | 10/11/2022 | 28 | 27 | 1 | 10/12/2022 | 10/12/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2022 |  | 6/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 670518 | 01535 | 3.8 |  |  | Solar |  | 05_01_525L1 | 02/06/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WORCESTER | 340849 | 01603 | 15.2 |  |  | Solar |  | 05_01_7J386 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 | 02/05/2021 | 1/20/2023 | Y | EXP | 475 | 10/05/2022 | 11/14/2022 | 41 | 0 | 41 |  |  | 12/21/2022 | Connected |  | N
National Grid | FOXBOROUGH | 509726 | 02035 | 240 |  |  | Solar |  | 05_05_2468W1 | 03/15/2023 | 04/07/2023 | 17 | 7 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 03/15/2023 | 7/2/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SALEM | 676951 | 01970 | 10 |  |  | Solar |  | 05_12_2W2 | 03/10/2025 | 04/03/2025 | 2 | 0 | 2 | 04/14/2025 | 04/14/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | BILLERICA | 177548 | 01821 | 11.4 |  |  | Solar |  | 05_14_18L2 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/28/2017 | 11/28/2017 | 11/28/2017 | Connected |  | N
National Grid | HAVERHILL | 488061 | 01832 | 7.6 |  |  | Solar |  | 05_14_48L4 | 02/24/2023 | 01/01/2023 | 3 | 0 | 3 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/1/2023 | 02/24/2023 | 5/14/2024 | Y | EXP | 365 | 08/12/2023 | 10/09/2023 | 59 | 0 | 59 |  |  | 10/18/2023 | Connected |  | Y
National Grid | LAWRENCE | 306473 | 01841 | 10 |  |  | Solar |  | 05_14_63L1 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176961 | 01830 | 0 |  |  | Solar |  | 05_14_76L3 | 07/18/2016 | 07/18/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/23/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 564107 | 01523 | 10 |  |  | Solar |  | 05_01_225W3 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/08/2023 | 1/2/2025 | Y | EXP | 365 | 05/16/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 7/5/2024 | Connected |  | N
National Grid | WORCESTER | 649062 | 01610 | 7.6 |  |  | Solar |  | 05_01_3J373 | 10/23/2024 | 11/13/2024 | 7 | 1 | 6 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 681289 | 01535 | 15 |  |  | Solar |  | 05_01_525L1 | 03/31/2025 | 05/23/2025 | 39 | 35 | 4 | 05/27/2025 | 05/27/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | WORCESTER | 341888 | 01603 | 7.6 |  |  | Solar |  | 05_01_7J386 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/11/2021 | 7/21/2023 | Y | EXP | 365 | 09/23/2021 | 01/17/2022 | 117 | 4 | 113 |  |  | 10/12/2022 | Connected |  | N
National Grid | FOXBOROUGH | 448988 | 02035 | 250 |  |  | Solar |  | 05_05_28W40 | 08/26/2022 | 10/28/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 4/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SALEM | 676829 | 01970 | 7.6 |  |  | Solar |  | 05_12_2W2 | 03/10/2025 | 03/27/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/10/2025 | 6/16/2026 | Y | EXP | 365 | 08/28/2025 | 10/29/2025 | 63 | 0 | 63 |  |  | 11/13/2025 | Connected |  | N
National Grid | BILLERICA | 189415 | 01821 | 15.2 |  |  | Solar |  | 05_14_18L2 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 2/21/2020 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | HAVERHILL | 586272 | 01832 | 3.19 |  |  | Solar |  | 05_14_48L4 | 02/07/2024 | 02/12/2024 | 3 | 0 | 3 | 02/13/2024 | 02/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 06/06/2024 | 11/02/2024 | 150 | 0 | 150 |  |  | 11/16/2024 | Connected |  | N
National Grid | METHUEN | 316168 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2020 | 10/21/2020 | 10/21/2021 | Y | EXP | 365 | 02/10/2021 | 04/05/2021 | 54 | 0 | 54 |  |  | 4/27/2021 | Connected |  | N
National Grid | HAVERHILL | 177296 | 01835 | 60 |  |  | Solar |  | 05_14_76L3 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 9/3/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/27/2017 | 3/27/2017 | 3/27/2017 | Connected |  | N
National Grid | LEOMINSTER | 587327 | 01453 | 19 |  |  | Solar |  | 05_01_225W3 | 02/01/2024 | 02/06/2024 | 3 | 1 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 667941 | 01610 | 5.76 |  |  | Solar |  | 05_01_3J373 | 01/27/2025 | 03/26/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 01/27/2025 | 5/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 360612 | 01535 | 1625 |  |  | Solar |  | 05_01_525L2 | 09/16/2021 | 12/13/2021 | 60 | 50 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 627279 | 01611 | 4.06 |  |  | Solar |  | 05_01_7J386 | 07/24/2024 | 07/30/2024 | 3 | 2 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/24/2024 | 8/13/2025 | Y | EXP | 365 | 10/29/2024 | 10/28/2024 | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | FOXBOROUGH | 696064 | 02035 | 180 |  |  | Solar |  | 05_05_28W40 | 07/21/2025 | 10/21/2025 | 64 | 55 | 9 | 10/22/2025 | 10/22/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 311130 | 01970 | 7.6 |  |  | Solar |  | 05_12_35J1 | 09/30/2020 | 10/06/2020 | 3 | 0 | 3 | 10/07/2020 | 10/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 225966 | 01821 | 6 |  |  | Solar |  | 05_14_18L2 | 05/09/2019 | 05/13/2019 | 2 | 1 | 1 | 05/14/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/09/2019 | 7/31/2020 | Y | EXP | 365 | 04/15/2020 | 04/16/2020 | 1 | 0 | 1 |  |  | 4/20/2020 | Connected |  | N
National Grid | HAVERHILL | 626731 | 01832 | 9.86 |  |  | Solar |  | 05_14_48L4 | 07/22/2024 | 07/31/2024 | 5 | 3 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/22/2024 | 8/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | METHUEN | 314982 | 01844 | 9.765 |  |  | Solar |  | 05_14_63L1 | 12/04/2020 | 12/07/2020 | 0 | 0 | 0 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/04/2020 | 11/22/2022 | Y | EXP | 365 | 08/06/2021 | 12/07/2021 | 123 | 63 | 60 |  |  | 12/9/2021 | Connected |  | N
National Grid | HAVERHILL | 177403 | 01830 | 10 |  |  | Solar |  | 05_14_76L3 | 06/30/2016 | 06/30/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 595356 | 01453 | 7.6 |  |  | Solar |  | 05_01_225W3 | 03/15/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/15/2024 | 4/4/2025 | Y | EXP | 365 | 06/11/2024 | 06/18/2024 | 8 | 0 | 8 |  |  | 6/27/2024 | Connected |  | Y
National Grid | WORCESTER | 697845 | 01610 | 7.6 |  |  | Solar |  | 05_01_3J373 | 06/11/2025 | 06/24/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 650533 | 01535 | 4980 |  |  | Solar |  | 05_01_525L2 | 01/13/2025 | 01/29/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2025 | 03/10/2025 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 636729 | 01611 | 5.76 |  |  | Solar |  | 05_01_7J386 | 08/30/2024 | 09/06/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | FALL RIVER | 739135 | 02720 | 20.96 |  |  | Solar |  | 05_05_28W40 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 514805 | 01970 | 6 |  |  | Solar |  | 05_12_35J1 | 04/07/2023 | 04/10/2023 | 1 | 0 | 1 | 04/11/2023 | 04/11/2023 | 25 | 0 | 25 | 06/26/2023 | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 8/24/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 372933 | 01821 | 7.6 |  |  | Solar |  | 05_14_18L2 | 08/06/2021 | 08/09/2021 | 2 | 1 | 1 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/06/2021 | 3/29/2023 | Y | EXP | 365 | 01/19/2022 | 02/11/2022 | 24 | 0 | 24 |  |  | 12/17/2022 | Connected |  | N
National Grid | HAVERHILL | 637124 | 01832 | 7.6 |  |  | Solar |  | 05_14_48L4 | 09/02/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 09/02/2024 | 10/29/2025 | Y | EXP | 365 | 06/27/2025 | 06/26/2025 | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | LAWRENCE | 327152 | 01841 | 7.6 |  |  | Solar |  | 05_14_63L1 | 12/14/2020 | 12/18/2020 | 3 | 0 | 3 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/14/2020 | 3/2/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 18 | 0 | 18 |  |  | 12/9/2021 | Connected |  | N
National Grid | HAVERHILL | 177899 | 01830 | 8.4 |  |  | Solar |  | 05_14_76L3 | 06/15/2017 | 06/15/2017 | 107 | 107 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/21/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 614607 | 01523 | 10 |  |  | Solar |  | 05_01_225W3 | 05/31/2024 | 06/06/2024 | 3 | 1 | 2 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/31/2024 | 6/24/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | WORCESTER | 737387 | 01610 | 10 |  |  | Solar |  | 05_01_3J374 | 12/02/2025 | 12/04/2025 | 2 | 0 | 2 | 12/05/2025 | 12/05/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEW BRAINTREE | 654404 | 01531 | 0 |  |  | Solar |  | 05_01_525L2 | 04/23/2025 | 06/20/2025 | 40 | 29 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2025 | 07/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 654479 | 01603 | 5.76 |  |  | Solar |  | 05_01_7J386 | 11/18/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174536 | 02720 | 950 |  |  | Solar |  | 05_05_28W40 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 544704 | 02151 | 100 |  |  | Solar |  | 05_12_35J1 | 08/02/2023 | 10/24/2023 | 57 | 48 | 9 | 10/25/2023 | 10/25/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 9/22/2024 | N | EXP | 86 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | BILLERICA | 413120 | 01821 | 15.2 |  |  | Solar |  | 05_14_18L2 | 02/18/2022 | 02/24/2022 | 4 | 2 | 2 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | HAVERHILL | 668948 | 01832 | 10.44 |  |  | Solar |  | 05_14_48L4 | 02/06/2025 | 02/12/2025 | 4 | 0 | 4 | 02/13/2025 | 02/13/2025 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 10/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | Y
National Grid | LAWRENCE | 326918 | 01841 | 9.8 |  |  | Solar |  | 05_14_63L1 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178408 | 01830 | 10 |  |  | Solar |  | 05_14_76L3 | 11/22/2017 | 11/22/2017 | 52 | 51 | 1 | 02/12/2018 | 02/12/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 11/22/2017 | 12/2/2018 | Y | EXP | 293 | 06/19/2018 | 07/17/2018 | 28 | 0 | 28 |  |  | 8/23/2018 | Connected |  | N
National Grid | LEOMINSTER | 622239 | 01453 | 5.76 |  |  | Solar |  | 05_01_225W3 | 07/02/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 50 | 31 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 07/02/2024 | 10/10/2025 | Y | EXP | 365 | 12/03/2024 | 12/16/2024 | 14 | 0 | 14 |  |  | 4/5/2025 | Connected |  | N
National Grid | WORCESTER | 570742 | 01610 | 10 |  |  | Solar |  | 05_01_3J374 | 12/19/2023 | 04/17/2024 | 81 | 77 | 4 | 04/18/2024 | 04/18/2024 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 685405 | 01585 | 10 |  |  | Solar |  | 05_01_525L2 | 06/04/2025 | 06/10/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 06/04/2025 | 8/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 662745 | 01603 | 10 |  |  | Solar |  | 05_01_7J386 | 12/27/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 141 | 117 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174744 | 02720 | 2000 |  |  | Solar |  | 05_05_28W40 | 07/02/2013 | 07/02/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2013 | 08/09/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2014 | 07/02/2013 | 6/30/2014 | Y | STD | 88 | 03/10/2015 | 04/02/2015 | 16 | 0 | 16 | 4/30/2015 | 4/30/2015 | 5/7/2015 | Connected |  | N
National Grid | REVERE | 598590 | 02151 | 7.6 |  |  | Solar |  | 05_12_35J1 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | BILLERICA | 653923 | 01821 | 3.8 |  |  | Solar |  | 05_14_18L2 | 11/18/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | HAVERHILL | 725190 | 01832 | 10 |  |  | Solar |  | 05_14_50L1 | 10/08/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 329444 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/29/2020 | 12/22/2022 | Y | EXP | 365 | 08/06/2021 | 10/12/2021 | 61 | 3 | 58 |  |  | 12/1/2021 | Connected |  | Y
National Grid | HAVERHILL | 199477 | 01830 | 7.6 |  |  | Solar |  | 05_14_76L3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 653119 | 01453 | 11.78 |  |  | Solar |  | 05_01_225W3 | 11/08/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 634549 | 01609 | 9.57 |  |  | Solar |  | 05_01_3J374 | 08/22/2024 | 10/14/2024 | 14 | 13 | 1 | 10/15/2024 | 10/15/2024 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 713186 | 01585 | 10 |  |  | Solar |  | 05_01_525L2 | 08/19/2025 |  | 52 | 24 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 655540 | 01603 | 3.8 |  |  | Solar |  | 05_01_7J387 | 11/19/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 175033 | 02720 | 900 |  |  | Wind |  | 05_05_28W40 | 03/25/2013 | 03/25/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2013 | 06/14/2013 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 632210 | 02151 | 10 |  |  | Solar |  | 05_12_35J1 | 08/13/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/13/2024 | 3/25/2026 | Y | EXP | 365 | 12/21/2024 | 09/10/2025 | 264 | 0 | 264 |  |  | 9/17/2025 | Connected |  | N
National Grid | BILLERICA | 660841 | 01821 | 10 |  |  | Solar |  | 05_14_18L2 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 | 02/21/2025 | 04/16/2025 | 55 | 0 | 55 |  |  | 4/24/2025 | Connected |  | N
National Grid | HAVERHILL | 176001 | 01832 | 20 |  |  | Solar |  | 05_14_50L1 | 06/15/2015 | 06/15/2015 | 16 | 16 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2015 |  | 6/21/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 9/23/2015 | 9/23/2015 | 9/29/2015 | Connected |  | N
National Grid | METHUEN | 330332 | 01844 | 9.8 |  |  | Solar |  | 05_14_63L1 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 01/04/2021 | 3/7/2022 | Y | EXP | 365 | 09/14/2021 | 10/14/2021 | 31 | 0 | 31 |  |  | 12/13/2021 | Connected |  | Y
National Grid | HAVERHILL | 368286 | 01830 | 15.2 |  |  | Solar |  | 05_14_76L3 | 07/07/2021 | 08/18/2021 | 31 | 30 | 1 | 08/19/2021 | 08/19/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2021 | Connected |  | N
National Grid | LEOMINSTER | 666473 | 01453 | 18.24 |  |  | Solar |  | 05_01_225W3 | 01/17/2025 | 03/05/2025 | 20 | 15 | 5 | 03/06/2025 | 03/06/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | WORCESTER | 636727 | 01609 | 10 |  |  | Solar |  | 05_01_3J374 | 08/30/2024 | 09/06/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 715702 | 01585 | 10 |  |  | Solar |  | 05_01_525L2 | 08/29/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/29/2025 | 11/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 715579 | 01603 | 10 |  |  | Solar |  | 05_01_7J387 | 08/29/2025 | 10/08/2025 | 14 | 11 | 3 | 11/06/2025 | 11/06/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 228014 | 02720 | 10 |  |  | Solar |  | 05_05_28W40 | 06/21/2019 | 07/03/2019 | 7 | 7 | 0 | 07/05/2019 | 07/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 10/10/2019 | Y | EXP | 84 | 08/30/2019 | 09/13/2019 | 14 | 0 | 14 |  |  | 9/23/2019 | Connected |  | N
National Grid | REVERE | 633469 | 02151 | 6 |  |  | Solar |  | 05_12_35J1 | 08/19/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | BILLERICA | 669702 | 01821 | 1.74 |  |  | Solar |  | 05_14_18L2 | 02/04/2025 | 02/07/2025 | 3 | 0 | 3 | 02/10/2025 | 02/10/2025 | 133 | 121 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178145 | 01810 | 10 |  |  | Solar |  | 05_14_50L1 | 04/12/2018 | 04/12/2018 | 374 | 34 | 340 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 335650 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 01/22/2021 |  | 31 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 465137 | 01830 | 3.8 |  |  | Solar |  | 05_14_76L3 | 10/07/2022 | 10/11/2022 | 1 | 0 | 1 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 10/07/2022 | 4/30/2024 | Y | EXP | 365 | 04/11/2023 | 04/28/2023 | 18 | 0 | 18 |  |  | 6/6/2023 | Connected |  | N
National Grid | LEOMINSTER | 673213 | 01453 | 23 |  |  | Solar |  | 05_01_225W3 | 02/20/2025 | 05/06/2025 | 52 | 25 | 27 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | WORCESTER | 658582 | 01609 | 9.57 |  |  | Solar |  | 05_01_3J374 | 12/05/2024 | 12/19/2024 | 8 | 6 | 2 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 719575 | 01585 | 7.6 |  |  | Solar |  | 05_01_525L2 | 10/06/2025 | 11/18/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 721057 | 01603 | 1.45 |  |  | Solar |  | 05_01_7J387 | 09/23/2025 | 10/02/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 225621 | 02720 | 233.3 |  |  | Solar |  | 05_05_28W40 | 06/29/2020 | 07/06/2020 | 5 | 4 | 1 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | REVERE | 641020 | 02151 | 6 |  |  | Solar |  | 05_12_35J1 | 09/17/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/17/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 710356 | 01821 | 8.32 |  |  | Solar |  | 05_14_18L2 | 08/08/2025 | 08/28/2025 | 3 | 2 | 1 | 09/19/2025 | 09/19/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 203934 | 01810 | 0 |  |  | Battery Add-On |  | 05_14_50L1 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | METHUEN | 339133 | 01844 | 7.92 |  |  | Solar |  | 05_14_63L1 | 03/26/2021 | 04/06/2021 | 6 | 0 | 6 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 478125 | 01830 | 15.2 |  |  | Solar |  | 05_14_76L3 | 12/01/2022 | 12/07/2022 | 4 | 2 | 2 | 12/08/2022 | 12/08/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | LEOMINSTER | 675974 | 01453 | 5.76 |  |  | Solar |  | 05_01_225W3 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 482717 | 01609 | 24.779 |  |  | Solar |  | 05_01_3J375 | 12/05/2022 | 12/08/2022 | 4 | 1 | 3 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | BROOKFIELD | 729007 | 01506 | 7.6 |  |  | Solar |  | 05_01_525L2 | 10/24/2025 | 10/30/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 189805 | 01603 | 10 |  |  | Solar |  | 05_01_7J387 | 07/02/2018 | 07/02/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 07/02/2018 | 12/5/2019 | Y | EXP | 398 | 07/17/2019 | 09/04/2019 | 49 | 0 | 49 |  |  | 10/29/2019 | Connected |  | N
National Grid | FALL RIVER | 388401 | 02720 | 15.2 |  |  | Solar |  | 05_05_28W40 | 10/13/2021 | 10/20/2021 | 5 | 5 | 0 | 10/21/2021 | 10/21/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | Y
National Grid | REVERE | 664554 | 02151 | 4.64 |  |  | Solar |  | 05_12_35J1 | 01/24/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 | 01/24/2025 | 4/8/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | BILLERICA | 690634 | 01821 | 10 |  |  | Solar |  | 05_14_18L3 | 05/08/2025 | 07/01/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 05/08/2025 | 9/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ANDOVER | 213038 | 01810 | 10 |  |  | Solar |  | 05_14_50L1 | 03/08/2019 | 03/11/2019 | 5 | 0 | 5 | 04/08/2019 | 04/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 3/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2019 | Connected |  | N
National Grid | METHUEN | 342738 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 02/24/2021 | 03/16/2021 | 14 | 14 | 0 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 02/24/2021 | 9/17/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | HAVERHILL | 491622 | 01830 | 6 |  |  | Solar |  | 05_14_76L3 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/23/2023 | 9/4/2024 | Y | EXP | 365 | 07/01/2023 | 09/05/2023 | 67 | 0 | 67 |  |  | 9/18/2023 | Connected |  | Y
National Grid | LEOMINSTER | 679537 | 01453 | 15.2 |  |  | Solar |  | 05_01_225W3 | 03/24/2025 | 06/05/2025 | 0 | 0 | 0 | 06/06/2025 | 06/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | WORCESTER | 575082 | 01609 | 9.6 |  |  | Solar |  | 05_01_3J375 | 03/05/2024 | 03/11/2024 | 4 | 1 | 3 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 | 03/29/2024 | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 730718 | 01506 | 10 |  |  | Solar |  | 05_01_525L2 | 11/02/2025 | 11/03/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 189778 | 01603 | 10 |  |  | Solar |  | 05_01_7J387 | 11/13/2018 | 07/02/2018 | 11 | 7 | 4 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 531727 | 02720 | 9.984 |  |  | Solar |  | 05_05_28W40 | 06/08/2023 | 06/14/2023 | 4 | 1 | 3 | 06/15/2023 | 06/15/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/08/2023 | 8/17/2024 | Y | EXP | 365 | 08/31/2023 | 09/02/2023 | 3 | 0 | 3 |  |  | 11/15/2023 | Connected |  | N
National Grid | REVERE | 175751 | 02151 | 21.07 |  |  | Solar |  | 05_12_35J2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2014 | 10/31/2014 | 12/31/2016 | Y | EXP | 757 | 04/29/2016 | 04/30/2016 | 1 | 0 | 1 | 1/28/2015 | 1/28/2015 | 5/20/2016 | Connected |  | N
National Grid | BILLERICA | 732460 | 01821 | 3.8 |  |  | Solar |  | 05_14_18L3 | 11/10/2025 | 11/12/2025 | 1 | 0 | 1 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 227099 | 01810 | 0 |  |  | Solar |  | 05_14_50L1 | 05/13/2019 | 05/14/2019 | 0 | 0 | 0 | 05/15/2019 | 05/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N
National Grid | LAWRENCE | 379714 | 01841 | 6 |  |  | Solar |  | 05_14_63L1 | 09/20/2021 | 12/09/2021 | 4 | 0 | 4 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 559445 | 01830 | 11.05 |  |  | Solar |  | 05_14_76L3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 84 | 29 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 687754 | 01453 | 10 |  |  | Solar |  | 05_01_225W3 | 05/01/2025 | 05/15/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | WORCESTER | 621063 | 01609 | 7.6 |  |  | Solar |  | 05_01_3J375 | 06/27/2024 | 07/29/2024 | 17 | 16 | 1 | 07/30/2024 | 07/30/2024 | 123 | 25 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 734531 | 01506 | 11.52 |  |  | Solar |  | 05_01_525L2 | 11/18/2025 | 11/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 190326 | 01603 | 10 |  |  | Solar |  | 05_01_7J387 | 07/13/2018 | 08/24/2018 | 27 | 0 | 27 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 07/13/2018 |  | Y | EXP | 421 | 10/17/2019 | 10/16/2019 | 0 | 0 | 0 |  |  | 11/6/2019 | Connected |  | N
National Grid | FALL RIVER | 599193 | 02720 | 7.6 |  |  | Solar |  | 05_05_28W40 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 9 | 4 | 5 | 05/03/2024 | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 6/13/2025 | N | EXP | 365 | 07/15/2024 | 08/08/2024 | 25 | 0 | 25 |  |  | 8/28/2024 | Connected |  | N
National Grid | REVERE | 240171 | 02151 | 10 |  |  | Solar |  | 05_12_35J2 | 07/11/2019 | 07/19/2019 | 6 | 6 | 0 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 11/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | BILLERICA | 175826 | 01821 | 7.6 |  |  | Solar |  | 05_14_18L3 | 09/18/2015 | 09/18/2015 | 3 | 3 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 09/18/2015 | 9/26/2016 | Y | EXP | 350 | 04/04/2016 | 05/13/2016 | 28 | 0 | 28 | 5/4/2016 | 5/4/2016 | 6/17/2016 | Connected |  | N
National Grid | ANDOVER | 326510 | 01810 | 10 |  |  | Solar |  | 05_14_50L1 | 11/17/2020 | 12/03/2020 | 10 | 8 | 2 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2021 | Connected |  | N
National Grid | METHUEN | 393677 | 01844 | 7.25 |  |  | Solar |  | 05_14_63L1 | 11/05/2021 | 12/13/2021 | 4 | 2 | 2 | 12/14/2021 | 12/14/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 | 11/05/2021 | 7/28/2023 | Y | EXP | 365 | 05/13/2022 | 06/07/2022 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 566963 | 01830 | 7.6 |  |  | Solar |  | 05_14_76L3 | 11/10/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2023 | 11/10/2023 | 5/16/2025 | Y | EXP | 500 | 06/06/2024 | 02/19/2025 | 259 | 0 | 259 |  |  | 3/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 695812 | 01453 | 10 |  |  | Solar |  | 05_01_225W3 | 06/05/2025 | 07/01/2025 | 2 | 0 | 2 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2025 | Connected |  | N
National Grid | WORCESTER | 643130 | 01609 | 3.8 |  |  | Solar |  | 05_01_3J375 | 09/26/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | BROOKFIELD | 174181 | 01506 | 800 |  |  | Solar |  | 05_01_525L2 | 10/14/2011 | 10/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2013 | 10/14/2011 | 3/1/2014 | Y | STD | 325 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/19/2015 | Connected |  | N
National Grid | WORCESTER | 196395 | 01603 | 100 |  |  | Solar |  | 05_01_7J387 | 09/19/2018 | 10/01/2018 | 3 | 0 | 3 | 10/02/2018 | 10/02/2018 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 600530 | 02720 | 7.6 |  |  | Solar |  | 05_05_28W40 | 03/29/2024 | 06/25/2024 | 5 | 1 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | REVERE | 298672 | 02151 | 4.32 |  |  | Solar |  | 05_12_35J2 | 07/10/2020 | 07/17/2020 | 4 | 0 | 4 | 07/20/2020 | 07/20/2020 | 75 | 49 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2020 |  | 3/29/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 176859 | 01862 | 30 |  |  | Hydrogen |  | 05_14_18L3 | 01/20/2016 | 01/20/2016 | 1 | 1 | 0 | 01/21/2016 | 01/21/2016 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 11/16/2020 | N | EXP | 1358 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | ANDOVER | 424059 | 01810 | 9.772 |  |  | Solar |  | 05_14_50L1 | 04/24/2022 | 05/05/2022 | 10 | 9 | 1 | 05/06/2022 | 05/06/2022 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/24/2022 | 8/11/2023 | Y | EXP | 365 | 07/07/2022 | 08/11/2022 | 36 | 0 | 36 |  |  | 10/21/2022 | Connected |  | N
National Grid | METHUEN | 410011 | 01844 | 4.8 |  |  | Solar |  | 05_14_63L1 | 02/18/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/18/2022 | 2/7/2024 | Y | EXP | 365 | 05/24/2022 | 06/21/2022 | 29 | 0 | 29 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 591663 | 01830 | 0 |  |  | Battery Add-On |  | 05_14_76L3 | 03/06/2024 | 03/20/2024 | 11 | 9 | 2 | 03/21/2024 | 03/21/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | LEOMINSTER | 294875 | 01453 | 4947 |  |  | Other |  | 05_01_225W4 | 10/05/2020 | 10/07/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2020 | 11/02/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/05/2020 | 9/24/2027 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WORCESTER | 654226 | 01609 | 10 |  |  | Solar |  | 05_01_3J375 | 11/15/2024 | 01/08/2025 | 13 | 10 | 3 | 01/09/2025 | 01/09/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 174180 | 01585 | 1400 |  |  | Solar |  | 05_01_525L2 | 10/17/2011 | 10/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2014 | 10/17/2011 | 12/31/2016 | Y | STD | 1023 |  |  | 0 | 0 | 0 | 1/28/2016 | 1/28/2016 | 1/29/2016 | Connected |  | N
National Grid | WORCESTER | 198809 | 01603 | 7.6 |  |  | Solar |  | 05_01_7J387 | 10/17/2018 | 11/08/2018 | 5 | 0 | 5 | 11/09/2018 | 11/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 604010 | 02720 | 497.5 |  |  | Solar |  | 05_05_28W40 | 04/18/2024 | 05/24/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2024 | 07/17/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 457238 | 02151 | 7.6 |  |  | Solar |  | 05_12_35J2 | 09/07/2022 | 09/09/2022 | 2 | 0 | 2 | 09/12/2022 | 09/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | BILLERICA | 177535 | 01821 | 999 |  |  | Solar |  | 05_14_18L3 | 09/14/2017 | 09/14/2017 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 11/09/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 9/19/2019 | N | STD | 458 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 431159 | 01810 | 15.2 |  |  | Solar |  | 05_14_50L1 | 05/18/2022 | 05/19/2022 | 1 | 0 | 1 | 05/20/2022 | 05/20/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2023 | Connected |  | Y
National Grid | METHUEN | 415153 | 01844 | 9.28 |  |  | Solar |  | 05_14_63L1 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | HAVERHILL | 638521 | 01830 | 6 |  |  | Solar |  | 05_14_76L3 | 09/10/2024 | 10/08/2024 | 16 | 11 | 5 | 10/09/2024 | 10/09/2024 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 627849 | 01453 | 6 |  |  | Solar |  | 05_01_225W4 | 07/27/2024 | 08/08/2024 | 1 | 0 | 1 | 08/09/2024 | 08/09/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 07/27/2024 | 12/15/2025 | Y | EXP | 365 | 11/06/2024 | 11/18/2024 | 13 | 0 | 13 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 666721 | 01609 | 5.76 |  |  | Solar |  | 05_01_3J375 | 01/20/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 174550 | 01585 | 39 |  |  | Solar |  | 05_01_525L2 | 07/25/2012 | 07/25/2012 | 7 | 0 | 7 | 08/06/2012 | 08/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 07/25/2012 | 10/31/2012 | Y | EXP | -42 | 03/29/2013 | 03/29/2013 | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 4/16/2013 | Connected |  | N
National Grid | WORCESTER | 224318 | 01603 | 7.6 |  |  | Solar |  | 05_01_7J387 | 05/09/2019 | 05/15/2019 | 4 | 4 | 0 | 05/16/2019 | 05/16/2019 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 05/09/2019 | 2/28/2020 | Y | EXP | 268 | 08/31/2019 | 09/13/2019 | 13 | 0 | 13 |  |  | 11/7/2019 | Connected |  | N
National Grid | FALL RIVER | 607518 | 02720 | 5.76 |  |  | Solar |  | 05_05_28W40 | 04/29/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 04/29/2024 | 8/20/2025 | Y | EXP | 365 | 10/12/2024 | 01/17/2025 | 98 | 0 | 98 |  |  | 1/24/2025 | Connected |  | Y
National Grid | REVERE | 487786 | 02151 | 6 |  |  | Solar |  | 05_12_35J2 | 01/11/2023 | 01/12/2023 | 2 | 1 | 1 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | BILLERICA | 254107 | 01821 | 100 |  |  | Solar |  | 05_14_18L3 | 11/27/2019 | 12/13/2019 | 9 | 0 | 9 | 12/16/2019 | 12/16/2019 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/27/2019 |  | Y | EXP | 365 | 08/04/2020 | 08/27/2020 | 23 | 0 | 23 |  |  | 9/21/2020 | Connected |  | N
National Grid | ANDOVER | 433986 | 01810 | 19 |  |  | Solar |  | 05_14_50L1 | 05/27/2022 | 06/24/2022 | 19 | 18 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2023 | Connected |  | Y
National Grid | METHUEN | 465385 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 10/06/2022 |  | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 645705 | 01830 | 6.72 |  |  | Solar |  | 05_14_76L3 | 10/08/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/08/2024 | 1/23/2026 | Y | EXP | 365 | 05/10/2025 |  | 237 | 0 | 237 |  |  | 12/2/2025 | Connected |  | N
National Grid | LEOMINSTER | 665675 | 01453 | 0 |  |  | Other |  | 05_01_225W4 | 07/22/2025 | 09/15/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 709748 | 01609 | 5.76 |  |  | Solar |  | 05_01_3J375 | 08/07/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 174597 | 01585 | 300 |  |  | Solar |  | 05_01_525L2 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 10/13/2011 | 3/28/2012 | Y | EXP | 99 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 3/28/2012 | Connected |  | N
National Grid | WORCESTER | 256144 | 01603 | 10 |  |  | Solar |  | 05_01_7J387 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 | 11/08/2019 | 11/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 11/07/2019 | 7/8/2020 | Y | EXP | 365 | 02/14/2020 | 03/03/2020 | 18 | 0 | 18 |  |  | 5/5/2020 | Connected |  | N
National Grid | FALL RIVER | 621029 | 02720 | 6.08 |  |  | Solar |  | 05_05_28W40 | 06/27/2024 | 07/25/2024 | 14 | 12 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 684658 | 02151 | 3.8 |  |  | Solar |  | 05_12_35J2 | 04/11/2025 | 05/05/2025 | 1 | 0 | 1 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/11/2025 | 6/9/2026 | Y | EXP | 365 | 10/03/2025 |  | 91 | 0 | 91 |  |  | 12/3/2025 | Connected |  | N
National Grid | BILLERICA | 253359 | 01821 | 7.6 |  |  | Solar |  | 05_14_18L3 | 09/24/2019 | 09/25/2019 | 0 | 0 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 485562 | 01810 | 15.2 |  |  | Solar |  | 05_14_50L1 | 01/20/2023 | 01/27/2023 | 5 | 5 | 0 | 01/30/2023 | 01/30/2023 | 136 | 25 | 111 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 488617 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 | 01/20/2023 | 01/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/18/2023 | 7/2/2024 | Y | EXP | 365 | 04/18/2023 | 06/30/2023 | 74 | 0 | 74 |  |  | 7/12/2023 | Connected |  | N
National Grid | HAVERHILL | 648301 | 01830 | 5.76 |  |  | Solar |  | 05_14_76L3 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 705025 | 01453 | 0 |  |  | Other |  | 05_01_225W4 | 09/24/2025 | 11/06/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/07/2025 | 12/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 648676 | 01610 | 999 |  |  | Solar |  | 05_01_406L1 | 12/11/2024 | 03/07/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 |  | 205 | 25 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BROOKFIELD | 175312 | 01585 | 1414 |  |  | Solar |  | 05_01_525L2 | 06/27/2014 | 06/27/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2014 | 08/07/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 08/11/2016 | 08/11/2016 | 0 | 0 | 0 | 3/23/2015 | 06/27/2014 | 2/18/2016 | Y | STD | 332 | 03/31/2016 | 06/08/2016 | 47 | 0 | 47 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | WORCESTER | 273828 | 01603 | 7.6 |  |  | Solar |  | 05_01_7J387 | 01/23/2020 | 02/18/2020 | 16 | 14 | 2 | 02/19/2020 | 02/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2020 | 01/23/2020 | 8/12/2021 | Y | EXP | 365 | 02/03/2021 | 03/15/2021 | 40 | 0 | 40 |  |  | 4/7/2021 | Connected |  | N
National Grid | FALL RIVER | 636299 | 02720 | 6 |  |  | Solar |  | 05_05_28W40 | 08/29/2024 | 09/24/2024 | 1 | 0 | 1 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 173414 | 02151 | 7.6 |  |  | Solar |  | 05_12_35J3 | 04/11/2018 | 04/11/2018 | 0 | 0 | 0 | 05/09/2018 | 05/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 330833 | 01821 | 4125 |  |  | Solar |  | 05_14_18L3 | 12/17/2021 | 01/26/2022 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 503342 | 01810 | 18.85 |  |  | Solar |  | 05_14_50L1 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | METHUEN | 491261 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 3 | 2 | 1 | 06/06/2023 | 06/06/2023 | 75 | 43 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 655955 | 01830 | 10 |  |  | Solar |  | 05_14_76L3 | 11/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 174798 | 01453 | 400 |  |  | Solar |  | 05_01_225W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 652194 | 01610 | 0 |  |  | Solar |  | 05_01_406L1 | 12/05/2024 | 12/30/2024 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 251 | 25 | 226 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BROOKFIELD | 175469 | 01585 | 2250 |  |  | Solar |  | 05_01_525L2 | 11/25/2014 | 11/25/2014 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 427946 | 01603 | 11.4 |  |  | Solar |  | 05_01_7J387 | 05/03/2022 | 05/03/2022 | 0 | 0 | 0 | 05/04/2022 | 05/04/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N
National Grid | FALL RIVER | 642560 | 02720 | 10 |  |  | Solar |  | 05_05_28W40 | 09/30/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 175520 | 02151 | 266 |  |  | Solar |  | 05_12_35J3 | 04/09/2014 | 04/09/2014 | 10 | 4 | 6 | 04/25/2014 | 04/25/2014 | 608 | 2 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2014 | 04/09/2014 | 2/4/2016 | Y | EXP | 639 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 406505 | 01821 | 8.027 |  |  | Solar |  | 05_14_18L3 | 04/19/2022 | 04/27/2022 | 6 | 6 | 0 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 04/19/2022 | 11/19/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | ANDOVER | 520199 | 01810 | 10 |  |  | Solar |  | 05_14_50L1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 103 | 25 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 503150 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 23 | 0 | 23 | 04/18/2023 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 703835 | 01830 | 6.46 |  |  | Solar |  | 05_14_76L3 | 07/11/2025 | 07/14/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | LEOMINSTER | 174890 | 01453 | 300 |  |  | Solar |  | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 916 | 0 | 916 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 10/31/2013 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 677898 | 01542 | 100 |  |  | Solar |  | 05_01_406L1 | 04/24/2025 | 06/06/2025 | 30 | 20 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEST BROOKFIELD | 175494 | 01585 | 480 |  |  | Solar |  | 05_01_525L2 | 07/23/2014 | 07/23/2014 | 7 | 0 | 7 | 08/05/2014 | 08/05/2014 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 496344 | 01603 | 9.86 |  |  | Solar |  | 05_01_7J387 | 02/08/2023 | 02/09/2023 | 1 | 0 | 1 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 | 02/08/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | FALL RIVER | 646767 | 02720 | 10 |  |  | Solar |  | 05_05_28W40 | 10/14/2024 | 12/04/2024 | 3 | 0 | 3 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | REVERE | 177083 | 02151 | 750 |  |  | Solar |  | 05_12_35J3 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/09/2017 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 413213 | 01821 | 9.57 |  |  | Solar |  | 05_14_18L3 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | ANDOVER | 556272 | 01810 | 0 |  |  | Battery Add-On |  | 05_14_50L1 | 09/18/2023 | 10/10/2023 | 15 | 14 | 1 | 10/11/2023 | 10/11/2023 | 157 | 28 | 129 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 515091 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 04/03/2023 | 04/05/2023 | 2 | 0 | 2 | 04/06/2023 | 04/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2023 | 04/03/2023 | 9/19/2024 | Y | EXP | 365 | 08/12/2023 | 09/20/2023 | 40 | 0 | 40 |  |  | 9/22/2023 | Connected |  | N
National Grid | HAVERHILL | 699607 | 01830 | 9.28 |  |  | Solar |  | 05_14_77L1 | 06/18/2025 | 07/02/2025 | 2 | 0 | 2 | 09/05/2025 | 09/05/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 175026 | 01453 | 400 |  |  | Solar |  | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 704 | 0 | 704 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 6/3/2013 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 724654 | 01611 | 23 |  |  | Solar |  | 05_01_406L1 | 10/07/2025 | 10/13/2025 | 3 | 0 | 3 | 10/14/2025 | 10/14/2025 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BROOKFIELD | 175792 | 01585 | 1000 |  |  | Solar |  | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 | 09/16/2015 | 9/23/2016 | Y | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | WORCESTER | 567253 | 01603 | 6 |  |  | Solar |  | 05_01_7J387 | 11/15/2023 | 11/17/2023 | 2 | 0 | 2 | 11/20/2023 | 11/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | FALL RIVER | 649643 | 02720 | 5.76 |  |  | Solar |  | 05_05_28W40 | 10/24/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 215113 | 02151 | 7.6 |  |  | Solar |  | 05_12_35J3 | 05/15/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 59 | 48 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 10/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 434023 | 01821 | 0 |  |  | Other |  | 05_14_18L3 | 09/07/2022 | 09/28/2022 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2022 | 10/26/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 528645 | 01810 | 9.86 |  |  | Solar |  | 05_14_50L1 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid | METHUEN | 516114 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 05/30/2023 | 06/02/2023 | 3 | 1 | 2 | 06/05/2023 | 06/05/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | HAVERHILL | 705084 | 01830 | 3.8 |  |  | Solar |  | 05_14_77L1 | 07/15/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 | 07/15/2025 | 10/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 175736 | 01453 | 27 |  |  | Solar |  | 05_01_225W4 | 08/14/2014 | 08/14/2014 | 7 | 0 | 7 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/14/2014 | 11/28/2014 | Y | EXP | 58 | 12/10/2014 | 12/23/2014 | 9 | 0 | 9 | 10/6/2014 | 10/6/2014 | 1/12/2015 | Connected |  | N
National Grid | OXFORD | 174214 | 01537 | 1000 |  |  | Solar |  | 05_01_406L1 | 12/20/2011 | 12/20/2011 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 175791 | 01515 | 1000 |  |  | Solar |  | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 9/23/2016 | N | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | WORCESTER | 586363 | 01603 | 5.76 |  |  | Solar |  | 05_01_7J387 | 02/14/2024 | 02/21/2024 | 4 | 2 | 2 | 02/22/2024 | 02/22/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/14/2024 | 4/17/2025 | Y | EXP | 365 | 07/10/2024 | 11/07/2024 | 121 | 0 | 121 |  |  | 10/28/2024 | Connected |  | N
National Grid | FALL RIVER | 660889 | 02720 | 10 |  |  | Solar |  | 05_05_28W40 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | REVERE | 231907 | 02151 | 5 |  |  | Solar |  | 05_12_35J3 | 05/30/2019 | 06/26/2019 | 4 | 4 | 0 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 503842 | 01821 | 10 |  |  | Solar |  | 05_14_18L3 | 03/09/2023 | 03/10/2023 | 2 | 1 | 1 | 03/13/2023 | 03/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/09/2023 | 5/25/2024 | Y | EXP | 365 | 09/26/2023 | 10/12/2023 | 17 | 0 | 17 |  |  | 10/16/2023 | Connected |  | N
National Grid | ANDOVER | 534892 | 01810 | 15.2 |  |  | Solar |  | 05_14_50L1 | 06/26/2023 | 06/29/2023 | 4 | 3 | 1 | 06/30/2023 | 06/30/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2023 | Connected |  | N
National Grid | LAWRENCE | 521435 | 01841 | 10.368 |  |  | Solar |  | 05_14_63L1 | 05/10/2023 | 05/25/2023 | 11 | 8 | 3 | 05/26/2023 | 05/26/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 742161 | 01854 | 5.76 |  |  | Solar |  | 05_14_77L1 | 12/24/2025 | 12/29/2025 | 2 | 0 | 2 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 176068 | 01453 | 7.6 |  |  | Solar |  | 05_01_225W4 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 | 06/19/2015 | 6/27/2016 | Y | EXP | 346 | 03/14/2016 | 03/23/2016 | 6 | 0 | 6 | 11/13/2015 | 11/13/2015 | 4/27/2016 | Connected |  | N
National Grid | OXFORD | 174473 | 01537 | 32.4 |  |  | Solar |  | 05_01_406L1 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 7/2/2012 | Connected |  | N
National Grid | NORTH BROOKFIELD | 176288 | 01535 | 17.4 |  |  | Solar |  | 05_01_525L2 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 394 | 0 | 394 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2015 |  | 7/18/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 622055 | 01603 | 3.8 |  |  | Solar |  | 05_01_7J387 | 07/02/2024 | 07/09/2024 | 1 | 0 | 1 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 07/02/2024 | 7/31/2025 | Y | EXP | 365 | 10/04/2024 | 10/17/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | FALL RIVER | 704820 | 02720 | 1.16 |  |  | Solar |  | 05_05_28W40 | 07/14/2025 | 09/22/2025 | 49 | 45 | 4 | 09/23/2025 | 09/23/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2025 | Connected |  | N
National Grid | REVERE | 270600 | 02151 | 3.8 |  |  | Solar |  | 05_12_35J3 | 01/21/2020 | 03/09/2020 | 32 | 29 | 3 | 03/10/2020 | 03/10/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2020 | 01/21/2020 | 11/1/2022 | Y | EXP | 935 | 10/03/2020 | 12/15/2020 | 73 | 0 | 73 |  |  | 10/26/2022 | Connected |  | N
National Grid | BILLERICA | 559528 | 01821 | 13.34 |  |  | Solar |  | 05_14_18L3 | 10/03/2023 | 10/12/2023 | 6 | 4 | 2 | 10/13/2023 | 10/13/2023 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 538685 | 01810 | 15 |  |  | Solar |  | 05_14_50L1 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2023 |  | 10/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2023 | Connected |  | N
National Grid | METHUEN | 525627 | 01844 | 6 |  |  | Solar |  | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 2 | 1 | 1 | 06/06/2023 | 06/06/2023 | 57 | 38 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 | 06/01/2023 | 10/3/2024 | Y | EXP | 365 | 12/09/2023 | 12/30/2023 | 22 | 3 | 19 |  |  | 1/18/2024 | Connected |  | N
National Grid | LOWELL | 176630 | 01854 | 10 |  |  | Solar |  | 05_14_77L1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/21/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | LEOMINSTER | 176260 | 01453 | 10 |  |  | Solar |  | 05_01_225W4 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 3/17/2016 | Connected |  | N
National Grid | CHARLTON | 174794 | 01507 | 1000 |  |  | Solar |  | 05_01_406L1 | 07/05/2011 | 07/05/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2012 | 07/05/2011 | 7/24/2012 | Y | STD | 10 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/24/2012 | Connected |  | N
National Grid | NORTH BROOKFIELD | 176669 | 01535 | 499 |  |  | Solar |  | 05_01_525L2 | 10/20/2015 | 10/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 10/26/2016 | N | STD | 181 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 628232 | 01603 | 5.76 |  |  | Solar |  | 05_01_7J387 | 07/29/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | FALL RIVER | 388520 | 02720 | 400 |  |  | Solar |  | 05_05_28W41 | 01/12/2022 | 04/13/2022 | 63 | 51 | 12 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 01/12/2022 | 3/8/2026 | Y | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 294945 | 02151 | 10 |  |  | Solar |  | 05_12_35J3 | 06/15/2020 | 06/18/2020 | 2 | 0 | 2 | 06/19/2020 | 06/19/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/15/2020 | 4/8/2022 | Y | EXP | 365 | 01/21/2021 | 02/18/2021 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 587504 | 01821 | 7.25 |  |  | Solar |  | 05_14_18L3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/12/2024 | 2/28/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/24/2024 | Connected |  | N
National Grid | ANDOVER | 560942 | 01810 | 0 |  |  | Solar |  | 05_14_50L1 | 11/20/2023 | 11/27/2023 | 4 | 2 | 2 | 11/28/2023 | 11/28/2023 | 67 | 44 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | LAWRENCE | 525411 | 01841 | 6 |  |  | Solar |  | 05_14_63L1 | 06/12/2023 | 08/06/2023 | 38 | 33 | 5 | 08/07/2023 | 08/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 | 06/12/2023 | 9/23/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 2/21/2024 | Connected |  | N
National Grid | LOWELL | 176717 | 01854 | 5 |  |  | Solar |  | 05_14_77L1 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 8/1/2016 | 8/1/2016 | 8/2/2016 | Connected |  | N
National Grid | LEOMINSTER | 176887 | 01453 | 10 |  |  | Solar |  | 05_01_225W4 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 187 | 0 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 |  | 11/18/2016 | N | EXP | 350 |  |  | 0 | 0 | 0 | 12/4/2015 | 12/4/2015 |  | Withdrawn |  | N
National Grid | OXFORD | 174835 | 01537 | 0 |  |  | Solar |  | 05_01_406L1 | 08/03/2011 | 08/03/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2012 | 08/03/2011 | 12/31/2012 | Y | STD | 277 | 07/09/2012 | 10/18/2012 | 71 | 0 | 71 | 9/27/2012 | 9/27/2012 | 10/16/2012 | Connected |  | N
National Grid | WEST BROOKFIELD | 176811 | 01585 | 2000 |  |  | Solar |  | 05_01_525L2 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 646407 | 01603 | 3.8 |  |  | Solar |  | 05_01_7J387 | 10/16/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 51 | 25 | 26 | 02/07/2025 | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 4/10/2025 | 10/16/2024 | 4/11/2026 | Y | EXP | 365 | 05/09/2025 | 09/02/2025 | 117 | 0 | 117 |  |  | 9/4/2025 | Connected |  | N
National Grid | FALL RIVER | 174436 | 02720 | 75 |  |  | Solar |  | 05_05_28W41 | 06/27/2012 | 06/27/2012 | 7 | 0 | 7 | 07/12/2012 | 07/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/22/2012 | N | EXP | -51 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/14/2012 | Connected |  | N
National Grid | REVERE | 488509 | 02151 | 9.8 |  |  | Solar |  | 05_12_35J3 | 11/23/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/23/2024 | 2/24/2026 | Y | EXP | 365 | 06/12/2025 | 10/02/2025 | 113 | 0 | 113 |  |  | 10/16/2025 | Connected |  | N
National Grid | BILLERICA | 609946 | 01821 | 19.175 |  |  | Solar |  | 05_14_18L3 | 05/14/2024 | 05/28/2024 | 10 | 8 | 2 | 05/29/2024 | 05/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/14/2024 | 7/22/2025 | Y | EXP | 365 | 08/09/2024 | 08/28/2024 | 20 | 0 | 20 |  |  | 9/12/2024 | Connected |  | N
National Grid | ANDOVER | 566383 | 01844 | 0 |  |  | Solar |  | 05_14_50L1 | 10/26/2023 | 10/27/2023 | 1 | 0 | 1 | 10/30/2023 | 10/30/2023 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 546709 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 08/30/2023 |  | 70 | 54 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178127 | 01854 | 10 |  |  | Solar |  | 05_14_77L1 | 07/11/2017 | 07/11/2017 | 4 | 4 | 0 | 07/18/2017 | 07/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N
National Grid | LEOMINSTER | 176962 | 01453 | 3.8 |  |  | Solar |  | 05_01_225W4 | 07/18/2016 | 07/18/2016 | 1 | 1 | 0 | 07/20/2016 | 07/20/2016 | 254 | 0 | 254 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 |  | 7/24/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174948 | 01507 | 1000 |  |  | Solar |  | 05_01_406L1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 177650 | 01535 | 500 |  |  | Solar |  | 05_01_525L2 | 09/27/2017 | 09/27/2017 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2018 | 02/01/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 680111 | 01603 | 3.8 |  |  | Solar |  | 05_01_8J364 | 03/24/2025 | 04/04/2025 | 1 | 0 | 1 | 04/18/2025 | 04/18/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 174539 | 02720 | 950 |  |  | Solar |  | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 499811 | 02151 | 50 |  |  | Solar |  | 05_12_35J3 | 02/17/2023 | 05/10/2023 | 56 | 48 | 8 | 05/11/2023 | 05/11/2023 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | BILLERICA | 649590 | 01862 | 7.6 |  |  | Solar |  | 05_14_18L3 | 10/24/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 569243 | 01810 | 0 |  |  | Solar |  | 05_14_50L1 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 554723 | 01844 | 7.6 |  |  | Solar |  | 05_14_63L1 | 09/27/2023 | 09/28/2023 | 1 | 0 | 1 | 09/29/2023 | 09/29/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/27/2023 | 12/5/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 3/5/2024 | Connected |  | N
National Grid | LOWELL | 196418 | 01854 | 100 |  |  | Solar |  | 05_14_77L1 | 09/19/2018 | 10/04/2018 | 2 | 0 | 2 | 10/05/2018 | 10/05/2018 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 7/6/2020 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176995 | 01453 | 6 |  |  | Solar |  | 05_01_225W4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175031 | 01524 | 1000 |  |  | Solar |  | 05_01_406L1 | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2013 | 05/07/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 177789 | 01535 | 4500 |  |  | Solar |  | 05_01_525L2 | 06/05/2017 | 06/12/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/05/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 06/05/2017 | 7/15/2020 | Y | STD | 632 | 06/28/2019 | 06/01/2020 | 339 | 0 | 339 |  |  | 7/14/2020 | Connected |  | N
National Grid | WORCESTER | 176338 | 01603 | 308 |  |  | Solar |  | 05_01_8J364 | 09/17/2015 | 09/17/2015 | 3 | 3 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2015 |  | 9/22/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 2/8/2016 | 2/8/2016 | 2/12/2016 | Connected |  | N
National Grid | FALL RIVER | 174538 | 02720 | 950 |  |  | Solar |  | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 537998 | 02151 | 2.32 |  |  | Solar |  | 05_12_35J3 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 662428 | 01862 | 5.76 |  |  | Solar |  | 05_14_18L3 | 12/23/2024 | 03/12/2025 | 19 | 14 | 5 | 03/13/2025 | 03/13/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 582479 | 01810 | 6 |  |  | Solar |  | 05_14_50L1 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/01/2024 | 4/12/2025 | Y | EXP | 365 | 06/06/2024 | 07/24/2024 | 49 | 0 | 49 |  |  | 9/21/2024 | Connected |  | N
National Grid | METHUEN | 570739 | 01844 | 9.28 |  |  | Solar |  | 05_14_63L1 | 11/22/2023 | 11/29/2023 | 5 | 2 | 3 | 11/30/2023 | 11/30/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/22/2023 | 1/21/2025 | Y | EXP | 365 | 05/14/2024 | 06/07/2024 | 25 | 0 | 25 |  |  | 6/14/2024 | Connected |  | N
National Grid | LOWELL | 374425 | 01854 | 7.68 |  |  | Solar |  | 05_14_77L1 | 01/12/2022 | 01/18/2022 | 3 | 0 | 3 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/12/2022 | 1/14/2024 | Y | EXP | 365 | 05/26/2022 | 01/13/2023 | 232 | 0 | 232 |  |  | 1/25/2023 | Connected |  | N
National Grid | LEOMINSTER | 177095 | 01453 | 7.6 |  |  | Solar |  | 05_01_225W4 | 01/20/2017 | 01/20/2017 | 2 | 2 | 0 | 01/25/2017 | 01/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 | 01/20/2017 | 1/28/2018 | Y | EXP | 366 | 06/15/2017 | 07/28/2017 | 30 | 0 | 30 | 8/28/2017 | 8/28/2017 | 8/28/2017 | Connected |  | N
National Grid | LEICESTER | 175133 | 01524 | 500 |  |  | Solar |  | 05_01_406L1 | 11/08/2012 | 11/08/2012 | 4 | 0 | 4 | 11/26/2012 | 11/26/2012 | 435 | 0 | 435 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/16/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 178421 | 01506 | 3375 |  |  | Solar |  | 05_01_525L2 | 01/17/2018 | 02/01/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/26/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 | 01/17/2018 | 4/16/2022 | Y | STD | 439 | 03/14/2021 | 12/02/2021 | 264 | 7 | 257 | 12/3/2021 | 12/16/2021 | 12/27/2021 | Connected |  | N
National Grid | WORCESTER | 680491 | 01607 | 3.8 |  |  | Solar |  | 05_01_8J364 | 03/25/2025 | 04/07/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174537 | 02720 | 950 |  |  | Solar |  | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 601237 | 02151 | 5 |  |  | Solar |  | 05_12_35J3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/09/2024 | 6/4/2025 | Y | EXP | 365 | 09/27/2024 | 11/26/2024 | 61 | 0 | 61 |  |  | 1/30/2025 | Connected |  | N
National Grid | BILLERICA | 679351 | 01821 | 13.25 |  |  | Solar |  | 05_14_18L3 | 03/22/2025 | 03/27/2025 | 4 | 1 | 3 | 03/28/2025 | 03/28/2025 | 55 | 40 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | Y
National Grid | ANDOVER | 597748 | 01810 | 1.45 |  |  | Solar |  | 05_14_50L1 | 04/02/2024 | 06/11/2024 | 48 | 47 | 1 | 06/12/2024 | 06/12/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 7/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | METHUEN | 572865 | 01844 | 3.8 |  |  | Solar |  | 05_14_63L1 | 11/29/2023 | 12/05/2023 | 4 | 0 | 4 | 12/06/2023 | 12/06/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | LOWELL | 480217 | 01854 | 7.6 |  |  | Solar |  | 05_14_77L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 2 | 19 | 02/23/2023 | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | LEOMINSTER | 178543 | 01453 | 3.8 |  |  | Solar |  | 05_01_225W4 | 01/29/2018 | 01/29/2018 | 19 | 0 | 19 | 02/27/2018 | 02/27/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 2/4/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | Connected |  | N
National Grid | LEICESTER | 175340 | 01524 | 1000 |  |  | Solar |  | 05_01_406L1 | 01/16/2015 | 01/16/2015 | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2015 | 04/21/2015 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 09/30/2015 | 10/29/2015 | 20 | 0 | 20 | 10/29/2015 | 01/16/2015 | 3/31/2018 | Y | STD | 884 |  |  | 0 | 0 | 0 | 7/24/2017 | 7/24/2017 | 3/26/2018 | Connected |  | N
National Grid | WEST BROOKFIELD | 185007 | 01585 | 1000 |  |  | Solar |  | 05_01_525L2 | 05/17/2018 | 05/17/2018 | 32 | 15 | 17 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 07/05/2018 | 09/11/2018 | 36 | 5 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 681766 | 01607 | 3.8 |  |  | Solar |  | 05_01_8J364 | 04/01/2025 | 04/24/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | FALL RIVER | 176173 | 02720 | 972 |  |  | Solar |  | 05_05_28W41 | 04/23/2015 | 04/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2015 | 05/26/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 11/18/2015 | 12/21/2015 | 22 | 0 | 22 | 1/22/2016 | 04/23/2015 | 9/30/2015 | Y | STD | -114 | 07/12/2016 | 10/17/2016 | 67 | 0 | 67 | 10/21/2016 | 10/21/2016 | 10/28/2016 | Connected |  | N
National Grid | REVERE | 641513 | 02151 | 10 |  |  | Solar |  | 05_12_35J3 | 09/19/2024 | 10/10/2024 | 7 | 6 | 1 | 10/11/2024 | 10/11/2024 | 69 | 45 | 24 | 02/24/2025 | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 |  | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 | 8/8/2025 | 09/19/2024 | 8/18/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/10/2025 | Connected |  | N
National Grid | BILLERICA | 178218 | 01862 | 10 |  |  | Solar |  | 05_14_1J1 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/21/2019 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 600002 | 01810 | 23 |  |  | Solar |  | 05_14_50L1 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 5/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | Y
National Grid | METHUEN | 579133 | 01844 | 9.57 |  |  | Solar |  | 05_14_63L1 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 543280 | 01854 | 240 |  |  | Solar |  | 05_14_77L1 | 08/01/2023 | 08/16/2023 | 11 | 0 | 11 | 08/17/2023 | 08/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 08/01/2023 | 1/10/2026 | Y | EXP | 49 | 04/11/2025 | 04/18/2025 | 8 | 0 | 8 |  |  | 12/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 194206 | 01453 | 10 |  |  | Solar |  | 05_01_225W4 | 08/22/2018 | 08/13/2019 | 248 | 248 | 0 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 175439 | 01507 | 1000 |  |  | Solar |  | 05_01_406L1 | 11/24/2014 | 11/24/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 01/02/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 8/30/2016 | N | STD | 411 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 186901 | 01506 | 4980 |  |  | Solar |  | 05_01_525L2 | 06/01/2018 | 06/01/2018 | 0 | 0 | 0 |  |  | 54 | 43 | 11 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 696783 | 01607 | 7.6 |  |  | Solar |  | 05_01_8J364 | 06/23/2025 | 09/18/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 64 | 46 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 177659 | 02720 | 240 |  |  | Solar |  | 05_05_28W41 | 11/13/2017 | 11/13/2017 | 51 | 42 | 9 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 11/19/2018 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | REVERE | 645906 | 02151 | 10 |  |  | Solar |  | 05_12_35J4 | 10/17/2024 | 12/12/2024 | 27 | 25 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 546449 | 01821 | 4.93 |  |  | Solar |  | 05_14_1J1 | 08/23/2023 | 09/06/2023 | 10 | 9 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 11/18/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | ANDOVER | 604454 | 01810 | 0 |  |  | Battery Add-On |  | 05_14_50L1 | 07/16/2024 | 07/31/2024 | 11 | 9 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 580403 | 01844 | 10 |  |  | Solar |  | 05_14_63L1 | 01/12/2024 | 03/04/2024 | 27 | 25 | 2 | 03/05/2024 | 03/05/2024 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 01/12/2024 | 4/4/2025 | Y | EXP | 365 | 06/06/2024 | 09/11/2024 | 98 | 0 | 98 |  |  | 10/7/2024 | Connected |  | N
National Grid | LOWELL | 576639 | 01854 | 9.984 |  |  | Solar |  | 05_14_77L1 | 12/14/2023 | 01/22/2024 | 24 | 23 | 1 | 01/23/2024 | 01/23/2024 | 82 | 65 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 199725 | 01453 | 10 |  |  | Solar |  | 05_01_225W4 | 12/11/2018 | 12/19/2018 | 5 | 0 | 5 | 12/20/2018 | 12/20/2018 | 247 | 0 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 175598 | 01524 | 772.8 |  |  | Solar |  | 05_01_406L1 | 08/01/2014 | 08/01/2014 | 15 | 10 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2014 | 09/22/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 |  | 12/31/2016 | N | STD | 739 |  |  | 0 | 0 | 0 | 6/20/2016 | 6/20/2016 | 7/20/2016 | Connected |  | N
National Grid | BROOKFIELD | 190339 | 01515 | 250 |  |  | Solar |  | 05_01_525L2 | 07/10/2018 | 08/20/2018 | 28 | 0 | 28 | 08/21/2018 | 08/21/2018 | 91 | 21 | 70 | 12/10/2018 | 01/03/2019 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  | 01/03/2019 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 730871 | 01607 | 15.2 |  |  | Solar |  | 05_01_8J365 | 11/03/2025 | 12/11/2025 | 1 | 1 | 0 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 177932 | 02720 | 180 |  |  | Solar |  | 05_05_28W41 | 04/20/2017 | 04/20/2017 | 14 | 13 | 1 | 05/10/2017 | 05/10/2017 | 0 | 0 | 0 | 06/29/2017 | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 4/25/2018 | N | EXP | 217 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/15/2017 | Connected |  | N
National Grid | REVERE | 612368 | 02151 | 5.76 |  |  | Solar |  | 05_14_1J1 | 05/20/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LAWRENCE | 606583 | 01843 | 23 |  |  | Solar |  | 05_14_50L1 | 04/25/2024 | 05/03/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | ANDOVER | 580779 | 01810 | 5.8 |  |  | Solar |  | 05_14_63L1 | 02/08/2024 | 02/21/2024 | 9 | 5 | 4 | 02/22/2024 | 02/22/2024 | 9 | 6 | 3 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/25/2025 | N | EXP | 365 | 06/06/2024 | 02/12/2025 | 126 | 0 | 126 |  |  | 10/29/2024 | Connected |  | N
National Grid | METHUEN | 579700 | 01844 | 6 |  |  | Solar |  | 05_14_77L1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | LOWELL | 204484 | 01854 | 0 |  |  | Solar |  | 05_01_225W4 | 01/17/2019 | 02/01/2019 | 9 | 0 | 9 | 02/04/2019 | 02/04/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175650 | 01453 | 18 |  |  | Solar |  | 05_01_406L1 | 12/17/2014 | 12/17/2014 | 5 | 1 | 4 | 12/26/2014 | 12/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 | 12/17/2014 | 12/31/2016 | Y | EXP | 710 |  |  | 0 | 0 | 0 | 8/30/2016 | 8/30/2016 | 8/30/2016 | Connected |  | N
National Grid | CHARLTON | 213652 | 01507 | 7.36 |  |  | Solar |  | 05_01_525L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 178275 | 01083 | 990 |  |  | Solar |  | 05_05_28W41 | 02/21/2018 | 02/21/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 05/08/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 200545 | 01610 | 10 |  |  | Solar |  | 05_12_35J4 | 11/08/2018 | 11/28/2018 | 6 | 3 | 3 | 11/29/2018 | 11/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 641339 | 02720 | 7.6 |  |  | Solar |  | 05_14_1J1 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | REVERE | 616825 | 02151 |  |  |  | Battery Add-On |  | 05_14_50L1 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | LAWRENCE | 590846 | 01843 | 5 |  |  | Solar |  | 05_14_63L1 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/07/2024 | 8/29/2025 | Y | EXP | 365 | 10/03/2024 | 03/07/2025 | 156 | 0 | 156 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 598862 | 01810 | 7.6 |  |  | Solar |  | 05_14_77L1 | 04/05/2024 | 04/12/2024 | 5 | 0 | 5 | 04/16/2024 | 04/16/2024 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | METHUEN | 264869 | 01844 | 0 |  |  | Solar |  | 05_01_225W4 | 11/11/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 11/11/2019 | 3/16/2021 | Y | EXP | 365 | 06/24/2020 | 06/24/2020 | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | LOWELL | 175729 | 01854 | 996 |  |  | Solar |  | 05_01_406L1 | 06/03/2014 | 06/03/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2014 | 07/10/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 06/03/2014 | 4/23/2016 | Y | STD | 516 | 10/20/2015 | 04/27/2016 | 128 | 0 | 128 | 6/5/2014 | 6/5/2014 | 5/12/2016 | Connected |  | N
National Grid | LEOMINSTER | 272131 | 01453 | 0 |  |  | Other |  | 05_01_525L2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 189617 | 01507 | 249.8 |  |  | Solar |  | 05_05_28W41 | 06/29/2018 | 06/29/2018 | 6 | 5 | 1 | 07/11/2018 | 07/11/2018 | 43 | 21 | 22 | 09/28/2018 | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 |  | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 | 3/18/2019 | 06/29/2018 | 12/30/2021 | Y | EXP | 389 | 10/23/2021 | 11/19/2021 | 28 | 4 | 24 |  |  | 12/30/2021 | Connected |  | N
National Grid | WEST BROOKFIELD | 314661 | 01585 | 3.8 |  |  | Solar |  | 05_12_35J4 | 10/01/2020 | 10/05/2020 | 1 | 0 | 1 | 10/06/2020 | 10/06/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 | 10/01/2020 | 11/5/2021 | Y | EXP | 365 | 01/21/2021 | 04/08/2021 | 77 | 0 | 77 |  |  | 7/14/2021 | Connected |  | N
National Grid | WORCESTER | 174789 | 01610 | 60 |  |  | Solar |  | 05_14_1J2 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2011 |  | 3/12/2012 | N | EXP | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | FALL RIVER | 618866 | 02720 | 23 |  |  | Battery Add-On |  | 05_14_50L1 | 06/18/2024 | 06/24/2024 | 3 | 0 | 3 | 06/25/2024 | 06/25/2024 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | REVERE | 600702 | 02151 | 5 |  |  | Solar |  | 05_14_63L1 | 07/02/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | LAWRENCE | 628395 | 01843 | 7.6 |  |  | Solar |  | 05_14_77L1 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 07/29/2024 | 10/8/2025 | Y | EXP | 365 | 10/04/2024 | 11/22/2024 | 50 | 0 | 50 |  |  | 3/13/2025 | Connected |  | Y
National Grid | ANDOVER | 288685 | 01810 | 10 |  |  | Solar |  | 05_01_225W4 | 07/20/2020 | 07/27/2020 | 4 | 0 | 4 | 07/28/2020 | 07/28/2020 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/20/2020 | 4/3/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 2/19/2021 | Connected |  | N
National Grid | METHUEN | 175808 | 01844 | 100 |  |  | Solar |  | 05_01_406L1 | 05/18/2015 | 05/18/2015 | 5 | 5 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2015 |  | 12/31/2016 | N | EXP | 540 |  |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 9/16/2016 | Connected |  | N
National Grid | LOWELL | 281385 | 01854 | 0 |  |  | Other |  | 05_01_525L2 | 08/31/2020 | 09/24/2020 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 206485 | 01453 | 210 |  |  | Solar |  | 05_01_8J365 | 03/19/2019 | 03/22/2019 | 2 | 0 | 2 |  |  | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 | 03/19/2019 | 6/22/2023 | Y | STD | 927 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N
National Grid | CHARLTON | 203810 | 01507 | 250 |  |  | Solar |  | 05_05_28W41 | 01/11/2019 | 01/02/2019 | 7 | 4 | 3 | 01/03/2019 | 01/03/2019 | 5 | 0 | 5 | 02/12/2019 | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 617299 | 01083 | 5.76 |  |  | Solar |  | 05_12_35J4 | 06/14/2024 | 07/16/2024 | 16 | 15 | 1 | 07/17/2024 | 07/17/2024 | 22 | 10 | 12 | 09/06/2024 | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 11/13/2025 | N | EXP | 365 | 02/26/2025 |  | 310 | 0 | 310 |  |  | 12/6/2025 | Connected |  | N
National Grid | WORCESTER | 178293 | 01610 | 160 |  |  | Solar |  | 05_14_1J2 | 11/14/2017 | 11/14/2017 | 35 | 26 | 9 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2018 |  | 12/23/2019 | N | EXP | 713 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 625996 | 02720 |  |  |  | Battery Add-On |  | 05_14_50L1 | 07/18/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2024 | Connected |  | N
National Grid | REVERE | 604153 | 02151 | 5.76 |  |  | Solar |  | 05_14_63L1 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/18/2024 | 5/8/2025 | Y | EXP | 365 | 07/18/2024 | 11/18/2024 | 124 | 0 | 124 |  |  | 2/6/2025 | Connected |  | N
National Grid | LAWRENCE | 642143 | 01843 | 5.76 |  |  | Solar |  | 05_14_77L1 | 09/23/2024 | 11/12/2024 | 14 | 12 | 2 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | ANDOVER | 327211 | 01810 | 7.6 |  |  | Solar |  | 05_01_225W4 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175878 | 01841 | 1000 |  |  | Solar |  | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | LOWELL | 283873 | 01854 | 0 |  |  | Other |  | 05_01_525L2 | 09/02/2020 | 09/21/2020 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 594220 | 01453 | 7.6 |  |  | Solar |  | 05_01_8J365 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | OXFORD | 646539 | 01540 | 2850 |  |  | Solar |  | 05_05_28W50 | 03/28/2025 | 05/07/2025 | 27 | 16 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2025 | 06/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NORTH BROOKFIELD | 658236 | 01535 | 3.8 |  |  | Solar |  | 05_12_35J4 | 12/03/2024 |  | 131 | 25 | 106 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 504462 | 01610 | 0 |  |  | Other |  | 05_14_1J2 | 09/13/2023 | 11/07/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2023 | 12/09/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 644839 | 02720 |  |  |  | Battery Add-On |  | 05_14_50L1 | 10/03/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | REVERE | 614412 | 02151 | 5.76 |  |  | Solar |  | 05_14_63L1 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2025 | Connected |  | N
National Grid | LAWRENCE | 646859 | 01843 | 7.6 |  |  | Solar |  | 05_14_77L1 | 10/28/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/28/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 331301 | 01810 | 9.8 |  |  | Solar |  | 05_01_225W4 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175877 | 01841 | 2000 |  |  | Solar |  | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | LOWELL | 289281 | 01854 | 4950 |  |  | Other |  | 05_01_525L2 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2020 | 06/23/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 600333 | 01453 | 10 |  |  | Solar |  | 05_01_8J365 | 03/29/2024 | 04/02/2024 | 2 | 0 | 2 | 04/03/2024 | 04/03/2024 | 15 | 9 | 6 | 05/22/2024 | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/3/2025 | N | EXP | 365 | 08/13/2024 | 01/16/2025 | 157 | 0 | 157 |  |  | 1/30/2025 | Connected |  | N
National Grid | OXFORD | 174477 | 01540 | 203 |  |  | Solar |  | 05_05_28W50 | 04/27/2011 | 04/27/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 687658 | 01506 | 7.6 |  |  | Solar |  | 05_12_37J3 | 04/25/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 685230 | 01604 | 7.68 |  |  | Solar |  | 05_14_1J4 | 04/15/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 04/15/2025 | 8/22/2026 | Y | EXP | 365 | 10/30/2025 |  | 64 | 0 | 64 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 690506 | 02720 |  |  |  | Solar |  | 05_14_50L1 | 05/27/2025 | 06/10/2025 | 9 | 5 | 4 | 06/11/2025 | 06/11/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | REVERE | 618251 | 02151 | 6 |  |  | Solar |  | 05_14_63L1 | 06/17/2024 | 07/02/2024 | 1 | 0 | 1 | 07/03/2024 | 07/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | LAWRENCE | 647929 | 01843 | 9.6 |  |  | Solar |  | 05_14_77L1 | 10/18/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 335169 | 01810 | 5.76 |  |  | Solar |  | 05_01_225W4 | 02/17/2021 | 03/24/2021 | 24 | 24 | 0 | 03/25/2021 | 03/25/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 | 02/17/2021 | 3/24/2022 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175875 | 01841 | 2000 |  |  | Solar |  | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | LOWELL | 330996 | 01854 | 9.8 |  |  | Solar |  | 05_01_525L2 | 12/30/2020 | 01/04/2021 | 1 | 0 | 1 | 01/05/2021 | 01/05/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 645707 | 01453 | 11.5 |  |  | Solar |  | 05_01_8J365 | 10/09/2024 | 11/07/2024 | 2 | 0 | 2 | 11/08/2024 | 11/08/2024 | 18 | 1 | 17 | 01/15/2025 | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 |  | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174472 | 01524 | 250 |  |  | Solar |  | 05_05_28W50 | 04/28/2011 | 04/28/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 9/28/2011 | Connected |  | N
National Grid | WEST BROOKFIELD | 177347 | 01585 | 7.6 |  |  | Solar |  | 05_12_37J3 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/17/2017 | 4/17/2017 | 4/24/2017 | Connected |  | N
National Grid | WORCESTER | 651856 | 01607 | 3.8 |  |  | Solar |  | 05_14_1J4 | 11/04/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | FALL RIVER | 266407 | 02720 | 17.6 |  |  | Solar |  | 05_14_50L2 | 01/31/2020 | 02/06/2020 | 4 | 3 | 1 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | REVERE | 619181 | 02151 | 10 |  |  | Solar |  | 05_14_63L1 | 06/20/2024 | 07/15/2024 | 4 | 0 | 4 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/20/2024 | 8/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LAWRENCE | 654048 | 01843 | 9.6 |  |  | Solar |  | 05_14_77L1 | 11/13/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 351150 | 01810 | 7.6 |  |  | Solar |  | 05_01_225W4 | 04/29/2021 | 05/06/2021 | 4 | 0 | 4 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176149 | 01841 | 6 |  |  | Solar |  | 05_01_406L1 | 08/25/2015 | 08/25/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 606 | 0 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 9/5/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 343332 | 01854 | 9.8 |  |  | Solar |  | 05_01_525L2 | 03/05/2021 | 03/16/2021 | 6 | 4 | 2 | 03/17/2021 | 03/17/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 03/05/2021 | 6/20/2022 | Y | EXP | 365 | 08/10/2021 | 09/03/2021 | 23 | 3 | 20 |  |  | 11/5/2021 | Connected |  | N
National Grid | LEOMINSTER | 680752 | 01453 | 10 |  |  | Solar |  | 05_01_8J365 | 03/26/2025 | 04/03/2025 | 7 | 5 | 2 | 04/04/2025 | 04/04/2025 | 49 | 29 | 20 | 08/04/2025 | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 |  | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | LEICESTER | 174535 | 01524 | 2850 |  |  | Solar |  | 05_05_28W50 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2013 | 10/18/2011 | 10/31/2012 | Y | STD | -160 | 11/22/2013 | 12/19/2013 | 18 | 0 | 18 | 12/19/2013 | 12/19/2013 | 12/23/2013 | Connected |  | N
National Grid | BROOKFIELD | 178067 | 01515 | 240 |  |  | Solar |  | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 352 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/13/2021 | Connected |  | N
National Grid | WORCESTER | 641530 | 01607 | 11.52 |  |  | Solar |  | 05_14_1J6 | 09/19/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/19/2024 | 4/16/2026 | Y | EXP | 365 | 07/08/2025 |  | 178 | 0 | 178 |  |  | 11/26/2025 | Connected |  | N
National Grid | FALL RIVER | 176393 | 02720 | 56 |  |  | Solar |  | 05_14_50L3 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 9/8/2017 | N | EXP | 576 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 6/23/2017 | Connected |  | N
National Grid | EVERETT | 622624 | 02149 | 3.8 |  |  | Solar |  | 05_14_63L1 | 07/04/2024 | 07/11/2024 | 2 | 0 | 2 | 07/12/2024 | 07/12/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | LAWRENCE | 657225 | 01843 | 6.38 |  |  | Solar |  | 05_14_77L1 | 12/02/2024 | 12/29/2024 | 7 | 3 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/02/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | ANDOVER | 388913 | 01810 | 10 |  |  | Solar |  | 05_01_225W4 | 11/22/2021 | 01/06/2022 | 5 | 0 | 5 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2021 | 11/22/2021 | 10/26/2023 | Y | EXP | 365 | 04/13/2022 | 10/26/2022 | 197 | 0 | 197 |  |  | 11/14/2022 | Connected |  | N
National Grid | METHUEN | 176593 | 01844 | 496 |  |  | Solar |  | 05_01_406L1 | 10/09/2015 | 10/12/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 06/04/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 07/15/2016 | 06/04/2018 | 44 | 5 | 39 | 2/21/2017 | 10/09/2015 | 1/31/2020 | Y | STD | 982 | 03/14/2019 | 12/02/2019 | 263 | 81 | 182 |  |  | 1/14/2020 | Connected |  | N
National Grid | LOWELL | 353809 | 01854 | 15.2 |  |  | Solar |  | 05_01_525L2 | 08/18/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 | 08/18/2021 | 7/15/2023 | Y | EXP | 390 | 02/09/2022 | 03/23/2022 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 691733 | 01453 | 7.6 |  |  | Solar |  | 05_01_8J365 | 05/14/2025 | 06/03/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 50 | 38 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 175803 | 01524 | 990 |  |  | Solar |  | 05_05_28W50 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 178098 | 01585 | 240 |  |  | Solar |  | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/14/2021 | Connected |  | N
National Grid | WORCESTER | 681430 | 01610 | 10 |  |  | Solar |  | 05_14_1J7 | 04/01/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 176499 | 02720 | 98 |  |  | Solar |  | 05_14_50L3 | 02/08/2016 | 02/08/2016 | 5 | 5 | 0 | 02/18/2016 | 02/18/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 4/30/2018 | N | EXP | 794 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 4/29/2018 | Connected |  | N
National Grid | EVERETT | 627956 | 02149 | 7.6 |  |  | Solar |  | 05_14_63L1 | 07/26/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/26/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LAWRENCE | 664857 | 01843 | 6.5 |  |  | Solar |  | 05_14_77L1 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/09/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | ANDOVER | 421215 | 01810 | 0 |  |  | Solar |  | 05_01_225W4 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176688 | 01844 | 6 |  |  | Solar |  | 05_01_406L1 | 02/18/2016 | 02/18/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N
National Grid | LOWELL | 449501 | 01854 | 3.8 |  |  | Solar |  | 05_01_525L2 | 05/22/2023 | 09/01/2022 | 2 | 0 | 2 | 05/25/2023 | 05/25/2023 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2023 | Connected |  | N
National Grid | LEOMINSTER | 177481 | 01453 | 150 |  |  | Solar |  | 05_01_8J389 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 7/16/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 | 3/20/2017 | 3/20/2017 | 3/20/2017 | Connected |  | N
National Grid | CHARLTON | 177533 | 01507 | 9.92 |  |  | Solar |  | 05_05_28W50 | 09/11/2017 | 09/11/2017 | 22 | 22 | 0 | 10/13/2017 | 10/13/2017 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 09/11/2017 | 11/30/2018 | Y | EXP | 410 | 07/26/2018 | 08/21/2018 | 26 | 0 | 26 |  |  | 11/26/2018 | Connected |  | N
National Grid | BROOKFIELD | 464132 | 01506 | 80 |  |  | Solar |  | 05_12_37J3 | 10/26/2022 | 02/14/2023 | 74 | 63 | 11 | 02/15/2023 | 02/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 | 10/26/2022 | 7/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | WORCESTER | 661824 | 01610 | 7.6 |  |  | Solar |  | 05_14_1J7 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/19/2024 | 4/2/2026 | Y | EXP | 365 | 04/30/2025 | 10/07/2025 | 161 | 0 | 161 |  |  | 10/8/2025 | Connected |  | N
National Grid | FALL RIVER | 202797 | 02720 | 0 |  |  | Solar |  | 05_14_50L3 | 12/06/2018 | 12/18/2018 | 7 | 0 | 7 | 12/19/2018 | 12/19/2018 | 149 | 21 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 633390 | 02188 | 5 |  |  | Solar |  | 05_14_63L1 | 08/19/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/19/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LAWRENCE | 670340 | 01843 | 7.6 |  |  | Solar |  | 05_14_77L1 | 02/10/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 02/10/2025 | 4/21/2026 | Y | EXP | 365 | 07/24/2025 |  | 162 | 0 | 162 |  |  | 11/24/2025 | Connected |  | N
National Grid | ANDOVER | 443788 | 01810 | 11.02 |  |  | Solar |  | 05_01_225W4 | 07/19/2022 | 07/25/2022 | 4 | 2 | 2 | 07/26/2022 | 07/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 2/2/2024 | Y | EXP | 365 | 02/02/2023 | 02/01/2023 | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | LAWRENCE | 176885 | 01841 | 11.4 |  |  | Solar |  | 05_01_406L1 | 11/12/2015 | 11/12/2015 | 89 | 89 | 0 | 03/25/2016 | 03/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 11/12/2015 | 11/18/2016 | Y | EXP | 220 | 11/09/2016 | 11/16/2016 | 4 | 0 | 4 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N
National Grid | LOWELL | 389963 | 01854 | 6 |  |  | Solar |  | 05_01_525L2 | 11/03/2021 | 01/06/2022 | 5 | 1 | 4 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 584498 | 01453 | 10 |  |  | Solar |  | 05_01_8J389 | 02/14/2024 | 02/16/2024 | 2 | 0 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | CHARLTON | 177913 | 01507 | 2000 |  |  | Solar |  | 05_05_28W50 | 07/11/2017 | 07/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2017 | 08/22/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2018 |  | 6/24/2019 | N | STD | 445 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 662378 | 01585 | 10 |  |  | Solar |  | 05_12_37J4 | 01/10/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | WORCESTER | 177026 | 01610 | 23 |  |  | Solar |  | 05_14_1J8 | 08/05/2016 | 08/05/2016 | 1 | 0 | 1 | 08/17/2016 | 08/17/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 6/29/2018 | N | EXP | 669 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 311831 | 02720 | 250 |  |  | Solar |  | 05_14_50L3 | 09/11/2020 | 09/16/2020 | 2 | 0 | 2 | 09/17/2020 | 09/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 8/20/2025 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 635398 | 02188 | 7.6 |  |  | Solar |  | 05_14_63L1 | 08/26/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 110 | 24 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 558966 | 01843 | 200 |  |  | Solar |  | 05_14_77L2 | 10/05/2023 | 10/23/2023 | 11 | 2 | 9 | 10/24/2023 | 10/24/2023 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 10/05/2023 | 3/1/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | ANDOVER | 455958 | 01810 | 9.6 |  |  | Solar |  | 05_01_225W4 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 | 09/13/2022 | 2/3/2024 | Y | EXP | 365 | 02/03/2023 | 02/02/2023 | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | METHUEN | 177091 | 01844 | 7.6 |  |  | Solar |  | 05_01_406L1 | 01/18/2017 | 01/18/2017 | 4 | 3 | 1 | 01/25/2017 | 01/25/2017 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 |  | 1/24/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 414330 | 01854 | 7.6 |  |  | Solar |  | 05_01_525L2 | 02/25/2022 | 02/28/2022 | 1 | 0 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2022 | Connected |  | N
National Grid | LEOMINSTER | 176189 | 01453 | 0 |  |  | Battery Add-On |  | 05_01_8W1 | 09/01/2015 | 09/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 10/06/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 5/2/2016 | 09/01/2015 | 9/8/2016 | Y | STD | 129 | 04/19/2017 | 06/08/2017 | 35 | 0 | 35 | 8/1/2017 | 8/1/2017 | 8/29/2017 | Terminated |  | N
National Grid | CHARLTON | 177977 | 01507 | 480 |  |  | Solar |  | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 11/28/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | WEST BROOKFIELD | 578954 | 01585 | 200 |  |  | Solar |  | 05_12_37W1 | 01/03/2024 | 01/11/2024 | 6 | 0 | 6 | 01/12/2024 | 01/12/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/16/2026 | N | EXP | 180 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 177189 | 01607 | 23 |  |  | Solar |  | 05_14_1J8 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 12/21/2017 | N | EXP | 479 |  |  | 0 | 0 | 0 | 11/29/2017 | 11/29/2017 | 11/29/2017 | Connected |  | N
National Grid | FALL RIVER | 406250 | 02720 | 10 |  |  | Solar |  | 05_14_50L3 | 05/04/2022 | 06/06/2022 | 22 | 19 | 3 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 05/04/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | Y
National Grid | EVERETT | 637653 | 02149 | 10 |  |  | Solar |  | 05_14_63L1 | 09/04/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 09/04/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 558618 | 01843 | 240 |  |  | Solar |  | 05_14_77L2 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 09/29/2023 | 7/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | ANDOVER | 490204 | 01810 | 7.68 |  |  | Solar |  | 05_01_225W4 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | Y
National Grid | METHUEN | 177213 | 01844 | 1000 |  |  | Solar |  | 05_01_406L1 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2016 | 07/26/2016 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/14/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 414012 | 01854 | 15.2 |  |  | Solar |  | 05_01_525L2 | 02/24/2022 | 03/01/2022 | 4 | 3 | 1 | 03/02/2022 | 03/02/2022 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 684730 | 01453 | 5.76 |  |  | Solar |  | 05_01_8W1 | 04/11/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 177976 | 01507 | 960 |  |  | Solar |  | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | WEST BROOKFIELD | 658074 | 01585 | 84.6 |  |  | Solar |  | 05_12_37W1 | 01/09/2025 |  | 243 | 58 | 185 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | WORCESTER | 198686 | 01607 | 7.6 |  |  | Solar |  | 05_14_1J9 | 10/16/2018 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 484404 | 02720 | 14.5 |  |  | Solar |  | 05_14_50L3 | 03/06/2023 | 03/24/2023 | 14 | 12 | 2 | 03/27/2023 | 03/27/2023 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | EVERETT | 642797 | 02149 | 15.2 |  |  | Solar |  | 05_14_63L1 | 09/25/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 118 | 78 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 | 09/25/2024 | 5/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | LAWRENCE | 733768 | 01843 | 14.72 |  |  | Solar |  | 05_14_77L2 | 11/17/2025 | 12/10/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 503390 | 01810 | 16.24 |  |  | Solar |  | 05_01_225W4 | 02/20/2023 | 03/16/2023 | 19 | 18 | 1 | 03/17/2023 | 03/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 | 02/20/2023 | 4/26/2024 | Y | EXP | 365 | 07/06/2023 | 08/15/2023 | 41 | 0 | 41 |  |  | 1/31/2024 | Connected |  | N
National Grid | LAWRENCE | 177278 | 01841 | 1980 |  |  | Solar |  | 05_01_406L1 | 02/08/2017 | 03/27/2017 | 30 | 28 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2017 | 05/04/2017 | 28 | 14 | 14 |  |  | 0 | 0 | 0 | 01/13/2018 | 02/14/2020 | 523 | 0 | 523 | 10/20/2017 | 02/08/2017 | 1/31/2020 | Y | STD | 741 | 05/03/2019 | 01/22/2020 | 263 | 0 | 263 |  |  | 1/22/2020 | Connected |  | N
National Grid | LOWELL | 424701 | 01854 | 3.8 |  |  | Solar |  | 05_01_525L2 | 04/22/2022 | 04/29/2022 | 5 | 3 | 2 | 05/02/2022 | 05/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 724366 | 01453 | 3.8 |  |  | Solar |  | 05_01_8W1 | 10/06/2025 | 10/13/2025 | 4 | 1 | 3 | 10/14/2025 | 10/14/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 177975 | 01507 | 660 |  |  | Solar |  | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 09/08/2018 | 11/08/2018 | 61 | 0 | 61 |  |  | 11/27/2018 | Connected |  | N
National Grid | WEST BROOKFIELD | 192277 | 01585 | 340 |  |  | Solar |  | 05_12_37W1 | 09/11/2018 | 09/13/2018 | 1 | 0 | 1 | 09/14/2018 | 09/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 5/10/2021 | N | EXP | 409 | 02/13/2020 | 05/06/2021 | 449 | 5 | 444 |  |  | 5/19/2021 | Connected |  | N
National Grid | WORCESTER | 200094 | 01604 | 10 |  |  | Solar |  | 05_14_1J9 | 11/02/2018 | 12/03/2018 | 9 | 2 | 7 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 492109 | 02720 | 9.86 |  |  | Solar |  | 05_14_50L3 | 01/24/2023 | 02/06/2023 | 10 | 9 | 1 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 4/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | MEDFORD | 645251 | 02155 | 5.76 |  |  | Solar |  | 05_14_63L1 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | LAWRENCE | 178138 | 01843 | 3.8 |  |  | Solar |  | 05_14_77L2 | 03/22/2018 | 03/22/2018 | 4 | 4 | 0 | 03/29/2018 | 03/29/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 3/28/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/4/2019 | Connected |  | N
National Grid | ANDOVER | 502848 | 01810 | 14.79 |  |  | Solar |  | 05_01_225W4 | 04/12/2023 | 04/17/2023 | 3 | 1 | 2 | 04/18/2023 | 04/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 | 04/12/2023 | 5/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2023 | Connected |  | N
National Grid | LAWRENCE | 177409 | 01841 | 1980 |  |  | Solar |  | 05_01_406L1 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/11/2016 | 12/31/2020 | Y | STD | 365 | 09/29/2020 | 12/02/2020 | 64 | 0 | 64 |  |  | 12/21/2020 | Connected |  | N
National Grid | LOWELL | 457878 | 01854 | 3.77 |  |  | Solar |  | 05_01_525L2 | 10/13/2022 | 10/18/2022 | 4 | 1 | 3 | 10/19/2022 | 10/19/2022 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/13/2022 | 8/6/2024 | Y | EXP | 365 | 07/19/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 8/24/2023 | Connected |  | N
National Grid | LEOMINSTER | 174487 | 01453 | 300 |  |  | Solar |  | 05_01_8W1 | 11/12/2010 | 11/12/2010 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2011 | 11/12/2010 | 10/31/2012 | Y | EXP | 610 | 05/30/2012 | 07/30/2012 | 41 | 0 | 41 | 1/18/2013 | 1/18/2013 | 8/17/2012 | Connected |  | N
National Grid | CHARLTON | 369869 | 01507 | 66.6 |  |  | Solar |  | 05_05_28W50 | 07/22/2021 | 01/04/2022 | 7 | 0 | 7 | 08/02/2021 | 08/02/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2021 |  | 10/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | BROOKFIELD | 280051 | 01506 | 462.5 |  |  | Solar |  | 05_12_37W1 | 04/24/2020 | 05/12/2020 | 12 | 8 | 4 |  |  | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 202595 | 01607 | 7.6 |  |  | Solar |  | 05_14_1J9 | 02/07/2019 | 02/13/2019 | 4 | 4 | 0 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/07/2019 | 5/28/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 2/11/2020 | Connected |  | N
National Grid | FALL RIVER | 682703 | 02720 | 0 |  |  | Battery Add-On |  | 05_14_50L3 | 04/03/2025 | 05/02/2025 | 21 | 17 | 4 | 05/05/2025 | 05/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/03/2025 | 7/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | MEDFORD | 645235 | 02155 | 8.41 |  |  | Solar |  | 05_14_63L1 | 10/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 199543 | 01843 | 10 |  |  | Solar |  | 05_14_77L2 | 10/26/2018 | 01/03/2019 | 32 | 28 | 4 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 6/17/2019 | N | EXP | 151 |  |  | 0 | 0 | 0 |  |  | 6/1/2019 | Connected |  | N
National Grid | ANDOVER | 578035 | 01810 | 8.7 |  |  | Solar |  | 05_01_225W4 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 23 | 0 | 23 | 04/05/2024 | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | METHUEN | 177477 | 01844 | 20 |  |  | Solar |  | 05_01_406L1 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2016 | 07/06/2016 | 8/31/2017 | Y | EXP | 398 | 06/03/2017 | 08/25/2017 | 58 | 0 | 58 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | LOWELL | 496520 | 01854 | 15.2 |  |  | Solar |  | 05_01_525L2 | 01/30/2023 | 02/17/2023 | 15 | 14 | 1 | 02/21/2023 | 02/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | LEOMINSTER | 175354 | 01453 | 2100 |  |  | Solar |  | 05_01_8W1 | 09/09/2014 | 09/09/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2014 | 10/17/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 | 09/09/2014 | 12/31/2016 | Y | STD | 579 | 12/28/2016 | 09/09/2017 | 176 | 0 | 176 | 5/17/2017 | 5/17/2017 | 5/17/2017 | Connected |  | N
National Grid | CHARLTON | 397063 | 01507 | 1750 |  |  | Solar |  | 05_05_28W50 | 03/14/2022 |  | 162 | 153 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 315641 | 01506 | 7.68 |  |  | Solar |  | 05_12_37W1 | 09/28/2020 | 10/19/2020 | 14 | 12 | 2 | 10/20/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 10/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | WORCESTER | 208645 | 01607 | 10 |  |  | Solar |  | 05_14_1J9 | 02/13/2019 | 02/22/2019 | 5 | 0 | 5 | 02/25/2019 | 02/25/2019 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 699800 | 02720 | 9.69 |  |  | Solar |  | 05_14_50L3 | 06/19/2025 | 07/02/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | MALDEN | 649440 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L1 | 11/11/2024 | 12/19/2024 | 11 | 5 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | LAWRENCE | 416317 | 01843 | 7.68 |  |  | Solar |  | 05_14_77L2 | 03/16/2022 | 03/23/2022 | 5 | 0 | 5 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 598623 | 01810 | 15.2 |  |  | Solar |  | 05_01_225W4 | 03/21/2024 | 03/26/2024 | 14 | 12 | 2 | 08/12/2024 | 08/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | METHUEN | 177508 | 01844 | 99.9 |  |  | Solar |  | 05_01_406L1 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2017 |  | 8/31/2017 | N | EXP | 160 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/3/2017 | Connected |  | N
National Grid | LOWELL | 514350 | 01854 | 13.92 |  |  | Solar |  | 05_01_525L2 | 04/04/2023 | 04/05/2023 | 1 | 0 | 1 | 04/06/2023 | 04/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175690 | 01453 | 225 |  |  | Solar |  | 05_01_8W1 | 05/23/2014 | 05/23/2014 | 6 | 0 | 6 | 06/04/2014 | 06/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 |  | 8/29/2014 | N | EXP | 63 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/29/2014 | Connected |  | N
National Grid | CHARLTON | 455939 | 01507 | 196.175 |  |  | Solar |  | 05_05_28W50 | 09/02/2022 | 10/04/2022 | 22 | 13 | 9 |  |  | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 563473 | 01585 | 10 |  |  | Solar |  | 05_12_37W1 | 11/15/2023 | 11/16/2023 | 1 | 0 | 1 | 11/17/2023 | 11/17/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 | 11/15/2023 | 1/26/2025 | Y | EXP | 365 | 03/14/2024 | 06/14/2024 | 93 | 0 | 93 |  |  | 7/18/2024 | Connected |  | N
National Grid | MILLBURY | 301209 | 01527 | 10 |  |  | Solar |  | 05_14_1J9 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 | 02/03/2021 | 3/29/2022 | Y | EXP | 365 | 09/02/2021 | 01/27/2022 | 148 | 4 | 144 |  |  | 1/31/2022 | Connected |  | Y
National Grid | FALL RIVER | 586777 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J1 | 02/26/2024 | 05/08/2024 | 51 | 48 | 3 | 05/09/2024 | 05/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/29/2026 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 652252 | 02155 | 10 |  |  | Solar |  | 05_14_63L1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 481185 | 01843 | 201.9 |  |  | Solar |  | 05_14_77L2 | 12/20/2022 | 03/14/2023 | 56 | 47 | 9 | 03/15/2023 | 03/15/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2023 | 12/20/2022 | 10/21/2024 | Y | EXP | 380 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | ANDOVER | 612544 | 01810 | 5.76 |  |  | Solar |  | 05_01_225W4 | 05/21/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 05/21/2024 | 7/31/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | METHUEN | 177726 | 01844 | 7.6 |  |  | Solar |  | 05_01_406L1 | 10/04/2017 | 10/04/2017 | 9 | 8 | 1 | 10/19/2017 | 10/19/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 572056 | 01854 | 5.22 |  |  | Solar |  | 05_01_525L2 | 11/21/2023 | 11/28/2023 | 4 | 0 | 4 | 11/29/2023 | 11/29/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/21/2023 | 2/17/2025 | Y | EXP | 365 | 06/05/2024 | 07/29/2024 | 55 | 0 | 55 |  |  | 8/29/2024 | Connected |  | N
National Grid | LEOMINSTER | 177625 | 01453 | 0 |  |  | Solar |  | 05_01_8W1 | 05/23/2017 | 05/23/2017 | 12 | 11 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 487714 | 01537 | 3.8 |  |  | Solar |  | 05_05_28W50 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2023 | Connected |  | N
National Grid | BROOKFIELD | 639527 | 01506 | 7.6 |  |  | Solar |  | 05_12_37W1 | 09/11/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/11/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | WORCESTER | 347908 | 01602 | 7.6 |  |  | Solar |  | 05_14_1J9 | 04/06/2021 | 04/14/2021 | 5 | 0 | 5 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2021 | Connected |  | N
National Grid | FALL RIVER | 642635 | 02720 | 10 |  |  | Solar |  | 05_14_53J1 | 09/24/2024 |  | 19 | 16 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 655004 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L1 | 11/19/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 656692 | 01843 | 7.6 |  |  | Solar |  | 05_14_77L2 | 11/25/2024 | 01/17/2025 | 22 | 16 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 661154 | 01810 | 2.61 |  |  | Solar |  | 05_01_225W4 | 12/17/2024 | 01/24/2025 | 9 | 4 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 12/17/2024 | 3/14/2026 | Y | EXP | 365 | 05/17/2025 | 05/28/2025 | 12 | 0 | 12 |  |  | 6/7/2025 | Connected |  | N
National Grid | METHUEN | 177741 | 01844 | 1740 |  |  | Solar |  | 05_01_406L1 | 05/30/2017 | 11/01/2017 | 105 | 100 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2017 | 12/06/2017 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 572189 | 01854 | 9.28 |  |  | Solar |  | 05_01_525L2 | 01/10/2024 | 03/11/2024 | 41 | 37 | 4 | 03/12/2024 | 03/12/2024 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178575 | 01453 | 15.2 |  |  | Solar |  | 05_01_8W1 | 12/11/2017 | 12/11/2017 | 12 | 0 | 12 | 01/02/2018 | 01/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/18/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | CHARLTON | 521951 | 01507 | 6 |  |  | Solar |  | 05_05_28W50 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 658042 | 01585 | 84.6 |  |  | Solar |  | 05_12_37W1 | 01/09/2025 |  | 93 | 83 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 644454 | 01607 | 2.32 |  |  | Solar |  | 05_14_1J9 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 41 | 22 | 19 | 01/09/2025 | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 699429 | 02720 | 10 |  |  | Solar |  | 05_14_53J1 | 06/18/2025 | 07/03/2025 | 19 | 15 | 4 | 08/12/2025 | 08/12/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | MEDFORD | 656998 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L1 | 11/26/2024 | 01/03/2025 | 15 | 11 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 11/26/2024 | 4/16/2026 | Y | EXP | 365 | 05/15/2025 | 05/20/2025 | 6 | 0 | 6 |  |  | 9/9/2025 | Connected |  | N
National Grid | LAWRENCE | 669826 | 01843 | 3.8 |  |  | Solar |  | 05_14_77L2 | 02/04/2025 | 02/14/2025 | 2 | 0 | 2 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | LAWRENCE | 666188 | 01840 | 10 |  |  | Solar |  | 05_01_225W4 | 01/16/2025 | 02/14/2025 | 5 | 1 | 4 | 02/18/2025 | 02/18/2025 | 103 | 88 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177847 | 01841 | 900 |  |  | Solar |  | 05_01_406L1 | 10/17/2017 | 11/15/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/17/2017 | 10/1/2019 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 574688 | 01854 | 0 |  |  | Battery Add-On |  | 05_01_525L2 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 196 | 25 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178666 | 01453 | 2112 |  |  | Solar |  | 05_01_8W1 | 03/16/2018 | 03/16/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 537229 | 01507 | 4.93 |  |  | Solar |  | 05_05_28W50 | 08/21/2023 | 08/29/2023 | 7 | 6 | 1 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 668952 | 01585 | 7.6 |  |  | Solar |  | 05_12_37W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | WORCESTER | 647960 | 01607 | 3 |  |  | Solar |  | 05_14_1J9 | 10/17/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/17/2024 | 1/6/2026 | Y | EXP | 365 | 04/15/2025 | 11/13/2025 | 213 | 0 | 213 |  |  | 11/17/2025 | Connected |  | N
National Grid | FALL RIVER | 662479 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J2 | 12/24/2024 | 03/04/2025 | 0 | 0 | 0 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 657611 | 02155 | 10 |  |  | Solar |  | 05_14_63L1 | 11/29/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/14/2025 |  | 202 | 0 | 202 |  |  | 12/3/2025 | Connected |  | N
National Grid | LAWRENCE | 722435 | 01843 | 23 |  |  | Solar |  | 05_14_77L3 | 10/31/2025 | 11/12/2025 | 6 | 1 | 5 | 11/13/2025 | 11/13/2025 | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 417558 | 01841 | 4999.2 |  |  | Solar |  | 05_01_226L1 | 04/20/2022 | 06/21/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/20/2022 | 6/18/2027 | Y | STD | 673 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | METHUEN | 178172 | 01844 | 7800 |  |  | Solar |  | 05_01_406L1 | 03/23/2018 | 03/23/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2018 | 06/26/2018 | 59 | 43 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 641967 | 01854 | 10 |  |  | Solar |  | 05_01_525L2 | 09/20/2024 | 10/23/2024 | 1 | 0 | 1 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 193914 | 01453 | 60 |  |  | Solar |  | 05_01_8W1 | 08/20/2018 | 08/29/2018 | 6 | 0 | 6 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 582560 | 01524 | 20 |  |  | Battery Add-On |  | 05_05_28W50 | 01/10/2024 | 01/22/2024 | 7 | 4 | 3 | 04/11/2024 | 04/11/2024 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 707738 | 01585 | 7.6 |  |  | Solar |  | 05_12_37W10 | 08/01/2025 | 08/22/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/01/2025 | 10/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 653186 | 01607 | 6.72 |  |  | Solar |  | 05_14_1J9 | 11/08/2024 | 12/03/2024 | 11 | 8 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | FALL RIVER | 710450 | 02720 | 10 |  |  | Solar |  | 05_14_53J2 | 08/07/2025 | 09/17/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 19 | 2 | 17 | 10/30/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MEDFORD | 657645 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L1 | 11/29/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/29/2024 | 5/13/2026 | Y | EXP | 365 | 08/19/2025 |  | 136 | 0 | 136 |  |  | 12/2/2025 | Connected |  | N
National Grid | LAWRENCE | 722072 | 01843 | 11.5 |  |  | Solar |  | 05_14_77L3 | 10/02/2025 | 10/13/2025 | 6 | 3 | 3 | 10/14/2025 | 10/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 541794 | 01841 | 999 |  |  | Solar |  | 05_01_226L1 | 10/13/2023 | 12/18/2023 | 45 | 36 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 03/14/2025 | 54 | 0 | 54 | 10/4/2024 | 10/13/2023 | 8/29/2026 | Y | CMPX | 358 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LAWRENCE | 178255 | 01841 | 1375 |  |  | Solar |  | 05_01_406L1 | 04/16/2018 | 04/16/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 645312 | 01854 | 3.8 |  |  | Solar |  | 05_01_525L2 | 10/07/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/07/2024 | 2/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 192232 | 01453 | 199.8 |  |  | Solar |  | 05_01_8W1 | 08/07/2018 | 08/22/2018 | 10 | 0 | 10 | 08/23/2018 | 08/23/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 08/07/2018 | 2/17/2021 | Y | EXP | 433 | 12/21/2019 | 03/01/2021 | 437 | 268 | 169 |  |  | 3/16/2021 | Connected |  | N
National Grid | LEICESTER | 614273 | 01542 | 3.8 |  |  | Solar |  | 05_05_28W50 | 05/30/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 11/30/2025 | Y | EXP | 365 | 07/26/2024 | 09/03/2024 | 40 | 0 | 40 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 254430 | 01585 | 3.8 |  |  | Solar |  | 05_12_37W10 | 10/02/2019 | 10/07/2019 | 2 | 0 | 2 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 547517 | 01604 | 360 |  |  | Solar |  | 05_14_211L1 | 09/22/2023 | 10/16/2023 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 11/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 09/22/2023 | 6/14/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FALL RIVER | 723314 | 02720 | 12.76 |  |  | Solar |  | 05_14_53J2 | 10/01/2025 | 10/17/2025 | 1 | 0 | 1 | 10/30/2025 | 10/30/2025 | 26 | 9 | 17 | 12/12/2025 | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MEDFORD | 660632 | 02155 | 5.76 |  |  | Solar |  | 05_14_63L1 | 12/23/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174165 | 01843 | 566 |  |  | Solar |  | 05_14_77L3 | 04/24/2012 | 04/24/2012 | 13 | 0 | 13 | 05/11/2012 | 05/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 |  | 7/31/2012 | N | EXP | -111 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 5/21/2013 | Connected |  | N
National Grid | LAWRENCE | 701906 | 01841 | 10.64 |  |  | Solar |  | 05_01_226L1 | 07/05/2025 | 07/23/2025 | 5 | 2 | 3 | 08/04/2025 | 08/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 07/05/2025 | 9/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 178479 | 01841 | 5000 |  |  | Solar |  | 05_01_406L1 | 04/03/2018 | 04/03/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 647627 | 01854 | 22.8 |  |  | Solar |  | 05_01_525L2 | 11/06/2024 | 11/12/2024 | 4 | 1 | 3 | 11/13/2024 | 11/13/2024 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | PEPPERELL | 206477 | 01463 | 360 |  |  | Solar |  | 05_01_8W1 | 03/21/2019 | 04/02/2019 | 8 | 7 | 1 | 04/03/2019 | 04/03/2019 | 35 | 21 | 14 | 10/16/2019 | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 619689 | 01501 | 7.6 |  |  | Solar |  | 05_05_28W50 | 06/21/2024 | 07/05/2024 | 6 | 2 | 4 | 07/08/2024 | 07/08/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/21/2024 | 7/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | BROOKFIELD | 313741 | 01506 | 7.6 |  |  | Solar |  | 05_12_37W10 | 10/01/2020 | 10/06/2020 | 2 | 0 | 2 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 10/01/2020 | 11/13/2021 | Y | EXP | 365 | 08/02/2021 | 08/11/2021 | 9 | 0 | 9 |  |  | 9/15/2021 | Connected |  | Y
National Grid | WORCESTER | 690375 | 01607 | 875 |  |  | Solar |  | 05_14_211L1 | 06/10/2025 | 08/21/2025 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2025 | 09/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 177566 | 02720 | 15.2 |  |  | Solar |  | 05_14_53J2 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | MALDEN | 665076 | 02148 | 0 |  |  | Battery Add-On |  | 05_14_63L1 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | LAWRENCE | 177405 | 01843 | 7.6 |  |  | Solar |  | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 723303 | 01841 | 13.611 |  |  | Solar |  | 05_01_226L1 | 10/07/2025 | 10/14/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | METHUEN | 178565 | 01844 | 4998 |  |  | Solar |  | 05_01_406L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/09/2018 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 651760 | 01854 | 3.8 |  |  | Solar |  | 05_01_525L2 | 11/13/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | PEPPERELL | 307513 | 01463 | 3.8 |  |  | Solar |  | 05_01_8W1 | 10/21/2020 | 10/26/2020 | 2 | 0 | 2 | 10/27/2020 | 10/27/2020 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 620166 | 01501 | 7.6 |  |  | Solar |  | 05_05_28W50 | 06/24/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 532886 | 01585 | 6 |  |  | Solar |  | 05_12_37W10 | 09/13/2023 | 09/19/2023 | 5 | 2 | 3 | 09/20/2023 | 09/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 724263 | 01607 |  |  |  | Solar |  | 05_14_211L1 | 10/06/2025 | 11/06/2025 | 22 | 15 | 7 | 11/07/2025 | 11/07/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 521243 | 02720 | 10 |  |  | Solar |  | 05_14_53J2 | 05/25/2023 | 05/26/2023 | 1 | 0 | 1 | 05/30/2023 | 05/30/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 666060 | 02149 | 7.6 |  |  | Solar |  | 05_14_63L1 | 01/15/2025 | 03/11/2025 | 3 | 0 | 3 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 01/15/2025 | 4/17/2026 | Y | EXP | 365 | 06/14/2025 |  | 202 | 0 | 202 |  |  | 12/4/2025 | Connected |  | N
National Grid | TYNGSBORO | 177401 | 01879 | 3.44 |  |  | Solar |  | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175223 | 01841 | 5 |  |  | Solar |  | 05_01_226L1 | 01/05/2015 | 01/05/2015 | 28 | 25 | 3 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 5/31/2015 | N | EXP | 103 |  |  | 0 | 0 | 0 | 5/11/2015 | 5/11/2015 | 2/11/2016 | Connected |  | N
National Grid | METHUEN | 191612 | 01844 | 272 |  |  | Solar |  | 05_01_406L1 | 11/27/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 108 | 56 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 654347 | 01854 | 10 |  |  | Solar |  | 05_01_525L2 | 11/14/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/14/2024 | 3/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | PEPPERELL | 360536 | 01463 | 7.6 |  |  | Solar |  | 05_01_8W1 | 06/17/2021 | 06/21/2021 | 2 | 0 | 2 | 06/22/2021 | 06/22/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  | 8/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 646203 | 01540 | 3.839 |  |  | Solar |  | 05_05_28W50 | 10/10/2024 | 11/06/2024 | 15 | 10 | 5 | 11/07/2024 | 11/07/2024 | 73 | 50 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 640115 | 01585 | 3.8 |  |  | Solar |  | 05_12_37W10 | 09/13/2024 | 10/10/2024 | 3 | 0 | 3 | 10/11/2024 | 10/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/13/2024 | 12/30/2025 | Y | EXP | 365 | 02/26/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 4/2/2025 | Connected |  | N
National Grid | WORCESTER | 735051 | 01607 |  |  |  | Solar |  | 05_14_211L1 | 11/27/2025 |  | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | FALL RIVER | 538670 | 02720 | 12.76 |  |  | Solar |  | 05_14_53J2 | 09/05/2023 | 02/07/2024 | 105 | 95 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 | 02/27/2024 | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 4/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 667679 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L1 | 01/24/2025 | 03/05/2025 | 12 | 8 | 4 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | TYNGSBORO | 178339 | 01879 | 10 |  |  | Solar |  | 05_14_77L3 | 11/20/2017 | 11/20/2017 | 33 | 32 | 1 | 01/09/2018 | 01/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2018 | 11/20/2017 | 11/25/2018 | Y | EXP | 319 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | LAWRENCE | 175461 | 01841 | 499 |  |  | Solar |  | 05_01_226L1 | 09/23/2014 | 09/23/2014 | 32 | 27 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/04/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 198041 | 01844 | 15.2 |  |  | Solar |  | 05_01_406L1 | 10/09/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | LOWELL | 657273 | 01854 | 9.57 |  |  | Solar |  | 05_01_525L2 | 11/29/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/29/2024 | 1/28/2026 | Y | EXP | 365 | 07/02/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 7/24/2025 | Connected |  | N
National Grid | PEPPERELL | 396740 | 01463 | 3486 |  |  | Other |  | 05_01_8W1 | 07/07/2023 | 09/05/2023 | 41 | 31 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2023 | 01/22/2024 | 93 | 75 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 651174 | 01537 | 7.6 |  |  | Solar |  | 05_05_28W50 | 11/11/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/11/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 644021 | 01585 | 23 |  |  | Solar |  | 05_12_37W10 | 10/01/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 10/01/2024 | 3/21/2026 | Y | EXP | 365 | 06/27/2025 | 09/08/2025 | 74 | 0 | 74 |  |  | 10/21/2025 | Connected |  | N
National Grid | WORCESTER | 174305 | 01610 | 475 |  |  | Solar |  | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 5/16/2012 | N | EXP | -23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 600641 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J2 | 04/12/2024 | 05/30/2024 | 1 | 0 | 1 | 05/31/2024 | 05/31/2024 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 04/12/2024 | 10/4/2025 | Y | EXP | 365 | 08/22/2024 | 09/11/2024 | 21 | 0 | 21 |  |  | 12/6/2024 | Connected |  | N
National Grid | MALDEN | 668519 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L1 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | TYNGSBORO | 188816 | 01879 | 10 |  |  | Solar |  | 05_14_77L3 | 06/21/2018 | 06/21/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 06/21/2018 | 7/22/2020 | Y | EXP | 600 | 10/04/2019 | 10/22/2019 | 18 | 0 | 18 |  |  | 7/3/2020 | Connected |  | N
National Grid | LAWRENCE | 175774 | 01841 | 990 |  |  | Solar |  | 05_01_226L1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/26/2014 | 09/25/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 10/08/2015 | 10/28/2015 | 13 | 13 | 0 | 12/11/2015 | 08/15/2014 | 7/30/2016 | Y | STD | 232 | 04/06/2016 | 07/28/2016 | 77 | 0 | 77 | 7/21/2016 | 7/21/2016 | 7/28/2016 | Connected |  | N
National Grid | METHUEN | 204158 | 01844 | 306.4 |  |  | Solar |  | 05_01_406L1 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 657862 | 01854 | 10 |  |  | Solar |  | 05_01_525L2 | 12/02/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 12/02/2024 | 4/6/2026 | Y | EXP | 365 | 09/26/2025 | 09/25/2025 | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | PEPPERELL | 396738 | 01463 | 0 |  |  | Other |  | 05_01_8W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 657561 | 01507 | 5.76 |  |  | Solar |  | 05_05_28W50 | 11/28/2024 | 01/15/2025 | 20 | 16 | 4 | 01/16/2025 | 01/16/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 11/28/2024 | 3/11/2026 | Y | EXP | 365 | 03/20/2025 | 05/29/2025 | 71 | 0 | 71 |  |  | 7/30/2025 | Connected |  | N
National Grid | BROOKFIELD | 652275 | 01506 | 3.8 |  |  | Solar |  | 05_12_37W10 | 11/05/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WORCESTER | 175050 | 01607 | 37.8 |  |  | Solar |  | 05_14_211L1 | 08/10/2012 | 08/10/2012 | 5 | 0 | 5 | 08/20/2012 | 08/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | -27 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 12/9/2013 | Connected |  | N
National Grid | FALL RIVER | 623222 | 02720 | 3.8 |  |  | Solar |  | 05_14_53J2 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/08/2024 | 8/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | EVERETT | 673030 | 02149 | 5.76 |  |  | Solar |  | 05_14_63L1 | 02/19/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | TYNGSBORO | 197115 | 01879 | 3.8 |  |  | Solar |  | 05_14_77L3 | 09/27/2018 | 11/02/2018 | 3 | 3 | 0 | 11/05/2018 | 11/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/27/2018 | 4/22/2020 | Y | EXP | 512 | 11/14/2019 | 11/15/2019 | 1 | 0 | 1 |  |  | 1/22/2020 | Connected |  | N
National Grid | LAWRENCE | 175871 | 01841 | 7.6 |  |  | Solar |  | 05_01_226L1 | 09/25/2015 | 09/25/2015 | 2 | 2 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/4/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 12/2/2015 | 12/2/2015 | 12/2/2015 | Connected |  | N
National Grid | METHUEN | 245016 | 01844 | 10 |  |  | Solar |  | 05_01_406L1 | 07/23/2019 | 10/08/2019 | 4 | 3 | 1 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 | 07/23/2019 | 7/7/2020 | Y | EXP | 365 | 02/19/2020 | 02/20/2020 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 666204 | 01854 | 7.6 |  |  | Solar |  | 05_01_525L2 | 01/16/2025 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 396692 | 01463 | 0 |  |  | Other |  | 05_01_8W1 | 09/19/2022 | 10/24/2022 | 24 | 13 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 662945 | 01507 | 6 |  |  | Solar |  | 05_05_28W50 | 12/30/2024 | 04/09/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 661110 | 01535 | 15.2 |  |  | Solar |  | 05_12_37W10 | 12/19/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175350 | 01607 | 491 |  |  | Solar |  | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2014 | 01/01/2012 | 12/31/2014 | Y | EXP | 117 | 05/04/2015 | 05/22/2015 | 14 | 0 | 14 | 9/17/2014 | 9/17/2014 | 5/27/2015 | Connected |  | N
National Grid | FALL RIVER | 637397 | 02720 | 5.76 |  |  | Solar |  | 05_14_53J2 | 09/03/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 09/03/2024 | 11/1/2025 | Y | EXP | 365 | 05/07/2025 | 05/20/2025 | 14 | 0 | 14 |  |  | 6/13/2025 | Connected |  | N
National Grid | EVERETT | 674155 | 02149 | 5.76 |  |  | Solar |  | 05_14_63L1 | 02/25/2025 | 03/06/2025 | 3 | 0 | 3 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 201056 | 01879 | 7.6 |  |  | Solar |  | 05_14_77L3 | 11/13/2018 | 01/30/2019 | 41 | 34 | 7 | 01/31/2019 | 01/31/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176103 | 01841 | 6 |  |  | Solar |  | 05_01_226L1 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 12/1/2015 | Connected |  | N
National Grid | METHUEN | 281119 | 01844 | 2400 |  |  | Natural Gas |  | 05_01_406L1 | 06/09/2020 | 07/14/2020 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2020 | 08/04/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 06/09/2020 | 9/19/2023 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 670491 | 01854 | 15.04 |  |  | Solar |  | 05_01_525L2 | 02/06/2025 | 06/09/2025 | 11 | 6 | 5 | 06/10/2025 | 06/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | PEPPERELL | 398501 | 01463 | 9.8 |  |  | Solar |  | 05_01_8W1 | 02/03/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 02/03/2022 | 8/12/2023 | Y | EXP | 365 | 07/15/2022 | 08/11/2022 | 28 | 0 | 28 |  |  | 9/6/2022 | Connected |  | N
National Grid | OXFORD | 713232 | 01537 | 20 |  |  | Solar |  | 05_05_28W50 | 08/19/2025 | 08/26/2025 | 5 | 0 | 5 | 08/27/2025 | 08/27/2025 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | BROOKFIELD | 667228 | 01506 | 15.2 |  |  | Solar |  | 05_12_37W10 | 02/07/2025 | 02/19/2025 | 7 | 3 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175496 | 01607 | 68.4 |  |  | Solar |  | 05_14_211L1 | 09/25/2014 | 09/25/2014 | 6 | 0 | 6 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 09/25/2014 | 12/31/2014 | Y | EXP | 51 | 01/23/2015 | 02/19/2015 | 18 | 0 | 18 | 2/26/2015 | 2/26/2015 | 4/16/2015 | Connected |  | N
National Grid | FALL RIVER | 639334 | 02720 | 2.32 |  |  | Solar |  | 05_14_53J2 | 09/11/2024 | 09/23/2024 | 2 | 0 | 2 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | MALDEN | 674798 | 02148 | 11.4 |  |  | Solar |  | 05_14_63L1 | 04/10/2025 | 04/28/2025 | 10 | 6 | 4 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | TYNGSBORO | 251766 | 01879 | 7.6 |  |  | Solar |  | 05_14_77L3 | 09/11/2019 | 09/16/2019 | 2 | 2 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 09/11/2019 | 6/17/2021 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  | 1/26/2021 | Connected |  | N
National Grid | LAWRENCE | 177228 | 01841 | 38 |  |  | Solar |  | 05_01_226L1 | 11/02/2016 | 11/02/2016 | 2 | 2 | 0 | 11/07/2016 | 11/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/8/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | LAWRENCE | 292506 | 01841 | 0 |  |  | Other |  | 05_01_406L1 | 09/16/2020 | 09/29/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/30/2020 | 10/24/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 676836 | 01854 | 15.2 |  |  | Solar |  | 05_01_525L2 | 03/10/2025 | 03/26/2025 | 5 | 1 | 4 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | PEPPERELL | 408866 | 01463 | 0 |  |  | Battery Add-On |  | 05_01_8W1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 09/02/2022 | 135 | 129 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 409703 | 01540 | 0 |  |  | Other |  | 05_05_28W51 | 03/22/2022 | 04/01/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/22/2022 | 12/1/2026 | Y | STD | 413 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BROOKFIELD | 724792 | 01506 | 15.2 |  |  | Solar |  | 05_12_37W10 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175775 | 01607 | 60 |  |  | Solar |  | 05_14_211L1 | 08/15/2014 | 08/15/2014 | 7 | 0 | 7 | 08/27/2014 | 08/27/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/19/2014 | 9/19/2014 | 11/24/2014 | Connected |  | N
National Grid | FALL RIVER | 639669 | 02720 | 13.12 |  |  | Solar |  | 05_14_53J2 | 09/12/2024 | 10/03/2024 | 5 | 3 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 | 09/12/2024 | 2/4/2026 | Y | EXP | 365 | 02/20/2025 | 08/18/2025 | 180 | 0 | 180 |  |  | 8/30/2025 | Connected |  | N
National Grid | MALDEN | 674773 | 02148 | 11.5 |  |  | Solar |  | 05_14_63L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | TYNGSBORO | 261453 | 01879 | 7.6 |  |  | Solar |  | 05_14_77L3 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 03/04/2020 | 04/08/2020 | 35 | 0 | 35 |  |  | 7/30/2020 | Connected |  | N
National Grid | LAWRENCE | 177520 | 01841 | 1132.2 |  |  | Solar |  | 05_01_226L1 | 09/27/2016 | 09/27/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/27/2016 | 52 | 40 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 295119 | 01841 | 0 |  |  | Other |  | 05_01_406L1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 705957 | 01854 | 4980 |  |  | Solar |  | 05_01_525L2 | 08/26/2025 | 09/05/2025 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2025 | 09/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 559181 | 01463 | 10 |  |  | Solar |  | 05_01_8W1 | 10/09/2023 | 10/13/2023 | 5 | 4 | 1 | 10/16/2023 | 10/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 10/09/2023 | 12/23/2024 | Y | EXP | 365 | 01/12/2024 | 01/18/2024 | 7 | 0 | 7 |  |  | 3/6/2024 | Connected |  | N
National Grid | LEICESTER | 581883 | 01524 | 100 |  |  | Solar |  | 05_05_28W51 | 01/19/2024 | 02/08/2024 | 14 | 3 | 11 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | BROOKFIELD | 174415 | 01585 | 833 |  |  | Solar |  | 05_12_37W2 | 06/25/2012 | 06/25/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/05/2012 | 10/05/2012 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 176422 | 01501 | 2000 |  |  | Solar |  | 05_14_211L1 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 03/08/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 640559 | 02720 | 15.2 |  |  | Solar |  | 05_14_53J2 | 09/24/2024 | 10/03/2024 | 8 | 6 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 |  | 11/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | MALDEN | 677396 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L1 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 333029 | 01879 | 7.6 |  |  | Solar |  | 05_14_77L3 | 12/18/2020 | 12/21/2020 | 0 | 0 | 0 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 177839 | 01841 | 266.4 |  |  | Solar |  | 05_01_226L1 | 10/13/2017 | 10/13/2017 | 54 | 50 | 4 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 | 02/28/2018 | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 10/21/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 313292 | 01841 | 10 |  |  | Solar |  | 05_01_406L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N
National Grid | LOWELL | 492345 | 01854 | 5000 |  |  | Solar |  | 05_01_552L1 | 02/24/2023 | 03/21/2023 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2023 | 05/16/2023 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 559088 | 01463 | 10 |  |  | Solar |  | 05_01_8W1 | 10/03/2023 | 10/06/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 106 | 28 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 174517 | 01507 | 1000 |  |  | Solar |  | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 504 | 12/10/2012 | 12/13/2012 | 3 | 0 | 3 | 10/18/2013 | 10/18/2013 | 2/22/2013 | Connected |  | N
National Grid | WEST BROOKFIELD | 174795 | 01585 | 50 |  |  | Solar |  | 05_12_37W2 | 10/02/2009 | 10/02/2009 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2009 |  | 12/31/2012 | N | EXP | 1111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177132 | 01604 | 566.1 |  |  | Solar |  | 05_14_211L1 | 01/23/2017 | 01/23/2017 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/29/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 642771 | 02720 | 15.2 |  |  | Solar |  | 05_14_53J2 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/25/2024 | 10/24/2025 | Y | EXP | 365 | 01/09/2025 | 06/10/2025 | 153 | 0 | 153 |  |  | 7/1/2025 | Connected |  | N
National Grid | MALDEN | 679876 | 02148 | 11.5 |  |  | Solar |  | 05_14_63L1 | 03/21/2025 | 04/23/2025 | 23 | 20 | 3 | 04/24/2025 | 04/24/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 558692 | 01879 | 7.6 |  |  | Solar |  | 05_14_77L3 | 10/03/2023 | 10/05/2023 | 2 | 0 | 2 | 10/06/2023 | 10/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 | 10/03/2023 | 11/16/2024 | Y | EXP | 365 | 05/07/2024 | 07/24/2024 | 79 | 0 | 79 |  |  | 8/9/2024 | Connected |  | N
National Grid | LAWRENCE | 177871 | 01841 | 160 |  |  | Solar |  | 05_01_226L1 | 08/11/2017 | 08/11/2017 | 3 | 3 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/16/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/4/2018 | Connected |  | N
National Grid | METHUEN | 350779 | 01844 | 24 |  |  | Solar |  | 05_01_406L1 | 05/05/2021 | 01/07/2022 | 0 | 0 | 0 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 | 05/05/2021 | 3/9/2023 | Y | EXP | 365 | 01/14/2022 | 01/14/2022 | 1 | 0 | 1 |  |  | 4/5/2022 | Connected |  | N
National Grid | LOWELL | 661587 | 01854 | 3.8 |  |  | Solar |  | 05_01_552L1 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 568724 | 01463 | 7.6 |  |  | Solar |  | 05_01_8W1 | 11/10/2023 | 11/15/2023 | 3 | 1 | 2 | 11/16/2023 | 11/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 |  | 5/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | OXFORD | 174516 | 01537 | 1000 |  |  | Solar |  | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 504 | 10/19/2012 | 12/26/2012 | 30 | 0 | 30 | 1/25/2013 | 1/25/2013 | 2/22/2013 | Connected |  | N
National Grid | BROOKFIELD | 177293 | 01506 | 64 |  |  | Solar |  | 05_12_37W2 | 08/25/2016 | 08/25/2016 | 1 | 0 | 1 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2016 |  | 8/31/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/15/2017 | 11/15/2017 | 11/15/2017 | Connected |  | N
National Grid | WORCESTER | 178607 | 01607 | 150 |  |  | Solar |  | 05_14_211L1 | 12/12/2017 | 12/12/2017 | 24 | 12 | 12 | 01/19/2018 | 01/19/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2018 |  | 12/18/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | FALL RIVER | 659995 | 02720 | 12.76 |  |  | Solar |  | 05_14_53J2 | 12/11/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 681026 | 02155 | 11.5 |  |  | Solar |  | 05_14_63L1 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 536046 | 01879 | 900 |  |  | Solar |  | 05_14_77L3 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 12/04/2023 | 67 | 48 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 178659 | 01841 | 415 |  |  | Solar |  | 05_01_226L1 | 02/05/2018 | 02/05/2018 | 9 | 0 | 9 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 07/11/2018 | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 8/13/2018 |  | 10/21/2020 | N | EXP | 566 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | METHUEN | 419196 | 01844 | 9.28 |  |  | Solar |  | 05_01_406L1 | 04/28/2022 |  | 303 | 21 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 680821 | 01854 | 20 |  |  | Solar |  | 05_01_552L1 | 03/26/2025 | 04/02/2025 | 6 | 2 | 4 | 04/03/2025 | 04/03/2025 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 | 03/26/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 571635 | 01463 | 6 |  |  | Solar |  | 05_01_8W1 | 12/04/2023 | 12/05/2023 | 1 | 0 | 1 | 12/06/2023 | 12/06/2023 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/04/2023 | 5/10/2025 | Y | EXP | 365 | 06/08/2024 | 07/17/2024 | 40 | 0 | 40 |  |  | 9/11/2024 | Connected |  | N
National Grid | CHARLTON | 174541 | 01507 | 475 |  |  | Solar |  | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 177365 | 01562 | 390 |  |  | Solar |  | 05_12_37W2 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2016 | 06/24/2016 | 7/2/2017 | Y | EXP | 290 | 12/12/2016 | 01/28/2017 | 32 | 0 | 32 | 3/10/2017 | 3/10/2017 | 3/9/2017 | Connected |  | N
National Grid | WORCESTER | 178719 | 01607 | 86.19 |  |  | Solar |  | 05_14_211L1 | 04/12/2018 | 04/12/2018 | 380 | 24 | 356 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 670934 | 02720 | 4.56 |  |  | Solar |  | 05_14_53J2 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | MEDFORD | 685181 | 02155 | 5.76 |  |  | Solar |  | 05_14_63L1 | 04/15/2025 | 04/25/2025 | 8 | 4 | 4 | 04/28/2025 | 04/28/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 576999 | 01879 | 5.51 |  |  | Solar |  | 05_14_77L3 | 01/16/2024 | 12/14/2023 | 2 | 0 | 2 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 | 03/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 4/11/2024 | 01/16/2024 | 5/29/2025 | Y | EXP | 365 | 05/18/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 9/6/2024 | Connected |  | N
National Grid | LAWRENCE | 185818 | 01841 | 999 |  |  | Solar |  | 05_01_226L1 | 06/27/2018 | 06/27/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2018 | 07/19/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 420713 | 01844 | 240 |  |  | Solar |  | 05_01_406L1 | 06/22/2022 | 10/07/2022 | 74 | 64 | 10 |  |  | 322 | 298 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 694028 | 01854 | 5.76 |  |  | Solar |  | 05_01_552L1 | 05/29/2025 | 08/13/2025 | 51 | 47 | 4 | 08/14/2025 | 08/14/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 05/29/2025 | 12/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | PEPPERELL | 609603 | 01463 | 10 |  |  | Solar |  | 05_01_8W1 | 05/08/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | CHARLTON | 174540 | 01507 | 950 |  |  | Solar |  | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 252582 | 01562 | 200 |  |  | Solar |  | 05_12_37W2 | 09/06/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 88 | 26 | 62 | 10/30/2019 | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 185409 | 01607 | 4999 |  |  | Solar |  | 05_14_211L1 | 06/15/2018 | 06/15/2018 | 32 | 32 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/17/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2019 | 06/15/2018 | 8/6/2021 | Y | STD | 498 | 03/04/2020 | 05/27/2021 | 450 | 5 | 445 |  |  | 8/2/2021 | Connected |  | N
National Grid | FALL RIVER | 685070 | 02720 | 13.8 |  |  | Solar |  | 05_14_53J2 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/22/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MEDFORD | 692844 | 02155 | 10 |  |  | Solar |  | 05_14_63L1 | 05/20/2025 | 06/23/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/20/2025 | 8/29/2026 | Y | EXP | 365 | 11/21/2025 |  | 42 | 0 | 42 |  |  | 11/24/2025 | Connected |  | N
National Grid | TYNGSBORO | 583929 | 01879 | 5.22 |  |  | Solar |  | 05_14_77L3 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 12 | 0 | 12 | 03/29/2024 | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 6/25/2025 | N | EXP | 365 | 10/24/2024 | 11/07/2024 | 15 | 0 | 15 |  |  | 12/16/2024 | Connected |  | N
National Grid | LAWRENCE | 186572 | 01841 | 1590 |  |  | Solar |  | 05_01_226L1 | 04/15/2019 | 06/05/2019 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2019 | 07/02/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 427518 | 01844 | 996 |  |  | Solar |  | 05_01_406L1 | 12/20/2022 | 04/06/2023 | 73 | 73 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2023 | 05/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 702237 | 01854 | 21.75 |  |  | Solar |  | 05_01_552L1 | 07/01/2025 | 08/25/2025 | 37 | 32 | 5 | 08/26/2025 | 08/26/2025 | 41 | 22 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 616890 | 01463 | 5.76 |  |  | Solar |  | 05_01_8W1 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | OXFORD | 174534 | 01540 | 950 |  |  | Solar |  | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 | 10/18/2011 | 10/31/2012 | Y | STD | -142 | 11/04/2013 | 03/18/2014 | 89 | 0 | 89 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | SPENCER | 384625 | 01562 | 298.8 |  |  | Solar |  | 05_12_37W2 | 08/11/2022 | 11/08/2022 | 61 | 51 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2022 | 09/21/2023 | 216 | 197 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 185918 | 01604 | 37.8 |  |  | Solar |  | 05_14_211L1 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 5/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2019 | Connected |  | N
National Grid | FALL RIVER | 652357 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J3 | 01/22/2025 | 02/19/2025 | 9 | 4 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/22/2025 | 3/28/2026 | Y | EXP | 365 | 06/12/2025 | 09/18/2025 | 99 | 0 | 99 |  |  | 10/7/2025 | Connected |  | N
National Grid | MEDFORD | 646555 | 02155 | 9.86 |  |  | Solar |  | 05_14_63L2 | 10/15/2024 | 10/28/2024 | 6 | 3 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/15/2024 | 12/19/2025 | Y | EXP | 365 | 04/01/2025 | 10/15/2025 | 198 | 0 | 198 |  |  |  | Completion Documents |  | Y
National Grid | TYNGSBORO | 599934 | 01879 | 15.2 |  |  | Solar |  | 05_14_77L3 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 188134 | 01841 | 1000 |  |  | Solar |  | 05_01_226L1 | 06/18/2018 | 06/18/2018 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2018 | 07/24/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 433800 | 01844 | 9.984 |  |  | Solar |  | 05_01_406L1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 705952 | 01854 | 996 |  |  | Solar |  | 05_01_552L1 | 08/14/2025 | 09/02/2025 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2025 | 10/16/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 619190 | 01463 | 5.76 |  |  | Solar |  | 05_01_8W1 | 06/20/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 174614 | 01507 | 2000 |  |  | Wind |  | 05_05_28W51 | 11/30/2010 | 11/30/2010 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/20/2012 | N | STD | 203 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/20/2012 | Connected |  | N
National Grid | SPENCER | 648827 | 01562 | 4.35 |  |  | Solar |  | 05_12_37W2 | 10/22/2024 | 11/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | WORCESTER | 186232 | 01607 | 249.8 |  |  | Solar |  | 05_14_211L1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 05/31/2018 | 05/31/2018 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 | 05/24/2018 | 8/31/2021 | Y | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 8/20/2021 | Connected |  | N
National Grid | FALL RIVER | 662820 | 02720 | 9.1 |  |  | Solar |  | 05_14_53J3 | 12/27/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/27/2024 | 4/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | MEDFORD | 711911 | 02155 | 249 |  |  | Solar |  | 05_14_63L2 | 08/13/2025 | 09/05/2025 | 16 | 7 | 9 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | TYNGSBORO | 616157 | 01879 | 13.6 |  |  | Solar |  | 05_14_77L3 | 06/06/2024 | 06/25/2024 | 3 | 1 | 2 | 06/26/2024 | 06/26/2024 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/06/2024 | 10/12/2025 | Y | EXP | 365 | 10/30/2024 | 01/23/2025 | 86 | 0 | 86 |  |  | 2/13/2025 | Connected |  | N
National Grid | LAWRENCE | 213711 | 01841 | 8.64 |  |  | Solar |  | 05_01_226L1 | 03/19/2019 | 03/29/2019 | 8 | 8 | 0 | 04/01/2019 | 04/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 5/30/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | LAWRENCE | 439718 | 01841 | 15.2 |  |  | Solar |  | 05_01_406L1 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | LOWELL | 712983 | 01854 | 7.6 |  |  | Solar |  | 05_01_552L1 | 08/19/2025 | 10/02/2025 | 7 | 3 | 4 | 10/22/2025 | 10/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 08/19/2025 | 12/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 639442 | 01463 | 5.76 |  |  | Solar |  | 05_01_8W1 | 09/11/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/11/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | OXFORD | 175108 | 01537 | 1500 |  |  | Solar |  | 05_05_28W51 | 04/22/2013 | 04/22/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2013 | 06/05/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2013 | 04/22/2013 | 9/2/2013 | Y | STD | -73 | 10/03/2014 | 12/08/2014 | 43 | 0 | 43 | 4/22/2013 | 4/22/2013 | 12/18/2014 | Connected |  | N
National Grid | SPENCER | 742314 | 01562 | 11.5 |  |  | Battery Add-On |  | 05_12_37W3 | 12/26/2025 | 01/05/2026 | 3 | 0 | 3 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 186708 | 01604 | 249.8 |  |  | Solar |  | 05_14_211L1 | 05/30/2018 | 05/30/2018 | 1 | 0 | 1 | 06/04/2018 | 06/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 | 05/30/2018 | 10/30/2020 | Y | EXP | 598 | 09/25/2020 | 09/24/2020 | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | FALL RIVER | 667264 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J3 | 02/04/2025 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174297 | 02155 | 1800 |  |  | Solar |  | 05_14_63L2 | 12/23/2011 | 12/23/2011 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2012 | 04/25/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2012 | 12/23/2011 | 9/1/2012 | Y | STD | -114 | 10/21/2013 | 01/02/2014 | 49 | 0 | 49 | 12/31/2013 | 12/31/2013 | 2/7/2014 | Connected |  | N
National Grid | TYNGSBORO | 644945 | 01879 | 3.8 |  |  | Solar |  | 05_14_77L3 | 10/03/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | Y
National Grid | LAWRENCE | 272824 | 01841 | 3.8 |  |  | Solar |  | 05_01_226L1 | 02/21/2020 | 04/30/2020 | 50 | 49 | 1 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 4/29/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 483875 | 01844 | 10 |  |  | Solar |  | 05_01_406L1 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 7/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2023 | Connected |  | N
National Grid | TYNGSBORO | 712272 | 01879 | 5.76 |  |  | Solar |  | 05_01_552L1 | 08/14/2025 | 09/05/2025 | 3 | 0 | 3 | 12/11/2025 | 12/11/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 645066 | 01463 | 3.8 |  |  | Solar |  | 05_01_8W1 | 10/04/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | CHARLTON | 175675 | 01507 | 500 |  |  | Solar |  | 05_05_28W51 | 10/21/2014 | 10/21/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 | 1/26/2018 | 1/26/2018 |  | Withdrawn |  | N
National Grid | SPENCER | 178470 | 01562 | 60 |  |  | Solar |  | 05_12_37W3 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  |  | N | EXP | 692 |  |  | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | AUBURN | 200571 | 01501 | 883.2 |  |  | Solar |  | 05_14_211L1 | 06/04/2019 | 07/29/2019 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2019 | 08/28/2019 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 319285 | 02720 | 8.12 |  |  | Solar |  | 05_14_53J4 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2020 | 11/12/2020 | 11/12/2021 | Y | EXP | 365 | 04/14/2021 | 05/20/2021 | 36 | 0 | 36 |  |  | 5/21/2021 | Connected |  | N
National Grid | MEDFORD | 176912 | 02155 | 10 |  |  | Solar |  | 05_14_63L2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 253 | 0 | 253 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 173451 | 01879 | 11.4 |  |  | Solar |  | 05_14_78L1 | 04/11/2018 | 04/11/2018 | 10 | 5 | 5 | 07/11/2018 | 07/11/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 04/11/2018 | 8/30/2019 | Y | EXP | 409 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/8/2019 | Connected |  | N
National Grid | LAWRENCE | 287295 | 01841 | 200 |  |  | Solar |  | 05_01_226L1 | 04/17/2020 | 05/29/2020 | 27 | 21 | 6 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 |  | 9/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | METHUEN | 538718 | 01844 | 20.01 |  |  | Solar |  | 05_01_406L1 | 07/05/2023 | 07/11/2023 | 4 | 3 | 1 | 07/12/2023 | 07/12/2023 | 114 | 25 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 715142 | 01879 | 0 |  |  | Battery Add-On |  | 05_01_552L1 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 646909 | 01463 | 7.6 |  |  | Solar |  | 05_01_8W1 | 10/31/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/31/2024 | 1/17/2026 | Y | EXP | 365 | 02/15/2025 | 06/04/2025 | 110 | 0 | 110 |  |  | 6/24/2025 | Connected |  | N
National Grid | CHARLTON | 175725 | 01507 | 500 |  |  | Solar |  | 05_05_28W51 | 05/27/2014 | 05/27/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2014 | 07/10/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/27/2014 | 11/28/2014 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 599355 | 01562 | 50 |  |  | Solar |  | 05_12_37W3 | 04/26/2024 | 05/17/2024 | 16 | 8 | 8 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2024 | Connected |  | N
National Grid | WORCESTER | 203063 | 01607 | 250 |  |  | Solar |  | 05_14_211L1 | 12/06/2018 | 01/02/2019 | 14 | 10 | 4 | 01/03/2019 | 01/03/2019 | 17 | 0 | 17 | 07/12/2019 | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  | 6/9/2021 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | FALL RIVER | 322607 | 02720 | 5 |  |  | Solar |  | 05_14_53J4 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/22/2020 | 4/3/2022 | Y | EXP | 365 | 08/15/2021 | 09/24/2021 | 40 | 3 | 37 |  |  | 11/9/2021 | Connected |  | N
National Grid | MEDFORD | 177064 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 03/20/2017 | 03/20/2017 | 9 | 8 | 1 | 03/31/2017 | 03/31/2017 | 224 | 0 | 224 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 |  | 3/25/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 175869 | 01879 | 22.8 |  |  | Solar |  | 05_14_78L1 | 09/25/2015 | 09/25/2015 | 3 | 3 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/3/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | LAWRENCE | 314437 | 01841 | 3.8 |  |  | Solar |  | 05_01_226L1 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | METHUEN | 550427 | 01844 | 6 |  |  | Solar |  | 05_01_406L1 | 08/23/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 743429 | 01879 | 12 |  |  | Solar |  | 05_01_552L1 | 01/05/2026 |  | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PEPPERELL | 651778 | 01463 | 10 |  |  | Solar |  | 05_01_8W1 | 11/13/2024 | 03/06/2025 | 59 | 53 | 6 | 03/07/2025 | 03/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | OXFORD | 176454 | 01537 | 3 |  |  | Solar |  | 05_05_28W51 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/14/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/9/2016 | 9/9/2016 | 9/13/2016 | Connected |  | N
National Grid | SPENCER | 662041 | 01562 | 11.5 |  |  | Solar |  | 05_12_37W3 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 207367 | 01604 | 72 |  |  | Solar |  | 05_14_211L1 | 01/28/2019 | 02/26/2019 | 7 | 2 | 5 | 02/27/2019 | 02/27/2019 | 30 | 21 | 9 | 04/22/2019 | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 |  | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 | 8/29/2019 | 01/28/2019 | 12/28/2021 | Y | EXP | 739 | 12/10/2021 | 12/09/2021 | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | FALL RIVER | 540408 | 02720 | 6 |  |  | Solar |  | 05_14_53J4 | 07/26/2023 | 08/22/2023 | 20 | 19 | 1 | 08/23/2023 | 08/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 177138 | 02155 | 6 |  |  | Solar |  | 05_14_63L2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2016 |  | 6/6/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 9/28/2016 | 9/28/2016 | 10/4/2016 | Connected |  | N
National Grid | TYNGSBORO | 177087 | 01879 | 170 |  |  | Solar |  | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2016 | 10/14/2016 | 6/11/2019 | Y | EXP | 910 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | METHUEN | 355070 | 01844 | 20 |  |  | Solar |  | 05_01_226L1 | 04/28/2021 | 12/15/2021 | 0 | 0 | 0 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/28/2021 | 12/2/2022 | Y | EXP | 365 | 11/16/2021 | 11/23/2021 | 8 | 0 | 8 |  |  | 12/21/2021 | Connected |  | N
National Grid | METHUEN | 586275 | 01844 | 20.01 |  |  | Solar |  | 05_01_406L1 | 02/19/2024 | 04/25/2024 | 48 | 46 | 2 | 04/26/2024 | 04/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 174248 | 01826 | 1000 |  |  | Solar |  | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 684478 | 01463 | 10 |  |  | Solar |  | 05_01_8W1 | 04/11/2025 | 05/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 | 04/11/2025 | 7/30/2026 | Y | EXP | 365 | 10/18/2025 | 10/30/2025 | 13 | 0 | 13 |  |  | 11/26/2025 | Connected |  | N
National Grid | OXFORD | 177098 | 01537 | 3 |  |  | Solar |  | 05_05_28W51 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 676058 | 01562 | 45.6 |  |  | Solar |  | 05_12_37W4 | 04/03/2025 | 04/25/2025 | 15 | 11 | 4 | 04/28/2025 | 04/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 268890 | 01607 | 249.5 |  |  | Solar |  | 05_14_211L1 | 02/21/2020 | 03/27/2020 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/24/2020 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 589338 | 02720 | 10 |  |  | Solar |  | 05_14_53J4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 07/18/2024 | 78 | 0 | 78 |  |  | 8/2/2024 | Connected |  | N
National Grid | MALDEN | 177698 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L2 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/31/2017 | 03/31/2017 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/21/2017 | 3/27/2018 | Y | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 177116 | 01879 | 150 |  |  | Solar |  | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2017 | 10/14/2016 | 3/11/2019 | Y | EXP | 774 |  |  | 0 | 0 | 0 |  |  | 2/26/2019 | Connected |  | N
National Grid | LAWRENCE | 388303 | 01841 | 7.6 |  |  | Solar |  | 05_01_226L1 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 638065 | 01844 | 10.44 |  |  | Solar |  | 05_01_406L1 | 01/17/2025 | 03/20/2025 | 8 | 3 | 5 | 03/21/2025 | 03/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | DRACUT | 174246 | 01826 | 1000 |  |  | Solar |  | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 684348 | 01463 | 3.19 |  |  | Solar |  | 05_01_8W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | N
National Grid | OXFORD | 217169 | 01540 | 240 |  |  | Solar |  | 05_05_28W51 | 05/06/2019 | 05/21/2019 | 8 | 0 | 8 | 05/22/2019 | 05/22/2019 | 15 | 2 | 13 | 07/03/2019 | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 9/4/2019 |  | 6/12/2020 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 4/16/2020 | Connected |  | N
National Grid | SPENCER | 708255 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 07/29/2025 | 08/15/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 6 | 13 | 10/14/2025 | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WORCESTER | 316773 | 01604 | 7.6 |  |  | Solar |  | 05_14_211L1 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/11/2020 | 3/13/2022 | Y | EXP | 365 | 05/19/2021 | 11/08/2021 | 174 | 7 | 167 |  |  | 1/11/2022 | Connected |  | N
National Grid | FALL RIVER | 590580 | 02720 | 10 |  |  | Solar |  | 05_14_53J4 | 02/23/2024 | 02/27/2024 | 2 | 0 | 2 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/23/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 09/11/2024 | 133 | 0 | 133 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 185125 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/13/2018 | 06/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 6/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | TYNGSBORO | 178082 | 01879 | 16.08 |  |  | Solar |  | 05_14_78L1 | 05/09/2017 | 05/09/2017 | 195 | 195 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 471136 | 01841 | 15.2 |  |  | Solar |  | 05_01_226L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 1/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2023 | Connected |  | N
National Grid | METHUEN | 641186 | 01844 | 17.11 |  |  | Solar |  | 05_01_406L1 | 09/27/2024 | 10/17/2024 | 13 | 11 | 2 | 10/18/2024 | 10/18/2024 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | DRACUT | 174527 | 01826 | 1000 |  |  | Solar |  | 05_01_552L1 | 09/12/2011 | 09/12/2011 | 99 | 0 | 99 | 02/06/2012 | 02/06/2012 | 655 | 0 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 611947 | 01463 | 240 |  |  | Solar |  | 05_01_8W2 | 06/03/2024 | 08/13/2024 | 49 | 25 | 24 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | OXFORD | 282338 | 01537 | 0 |  |  | Other |  | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2020 | 08/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2021 | 05/18/2020 | 11/29/2024 | Y | STD | 413 | 04/20/2022 | 03/07/2024 | 688 | 537 | 151 |  |  | 9/20/2024 | Connected |  | N
National Grid | SPENCER | 175484 | 01562 | 75 |  |  | Natural Gas |  | 05_12_37W4 | 03/18/2014 | 03/18/2014 | 8 | 2 | 6 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2014 |  | 9/30/2014 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/15/2014 | 10/15/2014 | 10/28/2014 | Connected |  | Y
National Grid | WORCESTER | 343831 | 01607 | 0 |  |  | Solar |  | 05_14_211L1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 | 03/12/2021 | 9/1/2022 | Y | EXP | 365 | 08/04/2021 | 08/31/2021 | 26 | 3 | 23 |  |  | 3/14/2022 | Connected |  | N
National Grid | FALL RIVER | 598618 | 02720 | 9.56 |  |  | Solar |  | 05_14_53J4 | 03/27/2024 | 04/03/2024 | 5 | 2 | 3 | 04/04/2024 | 04/04/2024 | 24 | 20 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | MEDFORD | 188327 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 06/18/2018 | 06/18/2018 | 7 | 3 | 4 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 6/28/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | TYNGSBORO | 178663 | 01879 | 42 |  |  | Solar |  | 05_14_78L1 | 03/16/2018 | 03/16/2018 | 5 | 0 | 5 | 03/23/2018 | 03/23/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 3/21/2019 | N | EXP | 316 | 10/31/2018 | 02/07/2019 | 99 | 0 | 99 |  |  | 5/1/2019 | Connected |  | N
National Grid | METHUEN | 477267 | 01844 | 17.45 |  |  | Solar |  | 05_01_226L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | METHUEN | 650479 | 01844 | 9.423 |  |  | Solar |  | 05_01_406L1 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | DRACUT | 174577 | 01826 | 3000 |  |  | Solar |  | 05_01_552L1 | 02/14/2011 | 02/14/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2011 | 03/23/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 2/28/2012 | 02/14/2011 | 12/31/2016 | Y | STD | 1768 | 11/29/2016 | 08/29/2017 | 188 | 0 | 188 | 3/10/2017 | 3/10/2017 | 3/10/2017 | Connected |  | N
National Grid | PEPPERELL | 728191 | 01463 | 10 |  |  | Solar |  | 05_01_8W2 | 10/22/2025 | 12/19/2025 | 2 | 0 | 2 | 12/31/2025 | 12/31/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 335842 | 01507 | 5.52 |  |  | Solar |  | 05_05_28W51 | 01/18/2021 | 12/16/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 64 | 40 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 | 01/18/2021 | 9/16/2022 | Y | EXP | 365 | 03/31/2022 | 04/12/2022 | 13 | 0 | 13 |  |  | 6/4/2022 | Connected |  | N
National Grid | SPENCER | 176729 | 01562 | 150 |  |  | Solar |  | 05_12_37W4 | 04/25/2016 | 04/25/2016 | 1 | 1 | 0 | 04/27/2016 | 04/27/2016 | 279 | 9 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/1/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 450750 | 01607 | 11.4 |  |  | Solar |  | 05_14_211L1 | 12/06/2022 | 12/07/2022 | 1 | 0 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 1/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | Y
National Grid | FALL RIVER | 613386 | 02720 | 10 |  |  | Solar |  | 05_14_53J4 | 05/29/2024 | 06/21/2024 | 2 | 0 | 2 | 06/24/2024 | 06/24/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 188961 | 02155 | 1750 |  |  | Solar |  | 05_14_63L2 | 07/06/2018 | 09/05/2018 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2018 | 10/10/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 | 07/06/2018 | 9/27/2021 | Y | STD | 483 | 06/22/2021 | 08/02/2021 | 42 | 0 | 42 |  |  | 9/22/2021 | Connected |  | N
National Grid | TYNGSBORO | 178685 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 12/18/2017 | 12/18/2017 | 8 | 0 | 8 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/24/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | METHUEN | 491024 | 01844 | 10 |  |  | Solar |  | 05_01_226L1 | 03/14/2023 | 03/20/2023 | 4 | 0 | 4 | 03/21/2023 | 03/21/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 658838 | 01844 | 5.76 |  |  | Solar |  | 05_01_406L1 | 12/05/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 12/05/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 174632 | 01826 | 1500 |  |  | Solar |  | 05_01_552L1 | 05/13/2013 | 05/13/2013 | 218 | 212 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 174185 | 01463 | 91.2 |  |  | Solar |  | 05_01_8W2 | 10/23/2011 | 10/23/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2012 | 10/23/2011 | 5/1/2012 | Y | EXP | -62 | 10/05/2012 | 01/15/2013 | 52 | 0 | 52 | 6/20/2012 | 6/20/2012 | 4/24/2013 | Connected |  | N
National Grid | OXFORD | 397056 | 01537 | 625 |  |  | Solar |  | 05_05_28W51 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 177838 | 01562 | 3.8 |  |  | Solar |  | 05_12_37W4 | 10/13/2017 | 10/13/2017 | 11 | 10 | 1 | 10/31/2017 | 10/31/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/18/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 398399 | 01527 | 43.2 |  |  | Solar |  | 05_14_211L1 | 12/02/2021 | 12/28/2021 | 19 | 12 | 7 | 12/29/2021 | 12/29/2021 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | Y
National Grid | FALL RIVER | 622922 | 02720 | 7.6 |  |  | Solar |  | 05_14_53J4 | 07/05/2024 | 08/15/2024 | 2 | 0 | 2 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 07/05/2024 | 8/28/2025 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | MALDEN | 194325 | 02148 | 7.6 |  |  | Solar |  | 05_14_63L2 | 11/18/2018 | 11/29/2018 | 6 | 0 | 6 | 11/30/2018 | 11/30/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  | 11/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | TYNGSBORO | 188124 | 01879 | 15.2 |  |  | Solar |  | 05_14_78L1 | 06/14/2018 | 06/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 493769 | 01844 | 24.94 |  |  | Solar |  | 05_01_226L1 | 01/20/2023 | 01/23/2023 | 2 | 1 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | METHUEN | 660796 | 01844 | 10 |  |  | Solar |  | 05_01_406L1 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | DRACUT | 175566 | 01826 | 997.6 |  |  | Solar |  | 05_01_552L1 | 10/06/2014 | 10/06/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 9/1/2016 | N | STD | 447 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 174739 | 01463 | 300 |  |  | Solar |  | 05_01_8W2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 | 01/25/2013 | 01/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2013 |  | 6/28/2013 | N | EXP | 99 |  |  | 0 | 0 | 0 | 3/26/2013 | 3/26/2013 | 8/20/2013 | Connected |  | N
National Grid | LEICESTER | 401103 | 01542 | 0 |  |  | Other |  | 05_05_28W51 | 01/04/2022 | 01/27/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2022 | 02/02/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 233361 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 07/05/2019 | 07/15/2019 | 5 | 0 | 5 | 07/16/2019 | 07/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/05/2019 | 8/20/2021 | Y | EXP | 365 | 10/15/2020 | 08/09/2021 | 293 | 0 | 293 |  |  | 8/14/2021 | Connected |  | N
National Grid | WORCESTER | 555818 | 01607 | 6 |  |  | Solar |  | 05_14_211L1 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 102 | 25 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 639127 | 02720 | 8.7 |  |  | Solar |  | 05_14_53J4 | 09/10/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | MEDFORD | 195141 | 02155 | 15.2 |  |  | Solar |  | 05_14_63L2 | 09/05/2018 | 10/17/2018 | 31 | 26 | 5 | 10/18/2018 | 10/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2018 |  | 7/5/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 6/21/2019 | Connected |  | N
National Grid | TYNGSBORO | 196115 | 01879 | 10 |  |  | Solar |  | 05_14_78L1 | 09/17/2018 | 10/30/2018 | 19 | 18 | 1 | 10/31/2018 | 10/31/2018 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/17/2018 | 5/27/2019 | Y | EXP | 181 | 02/21/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 5/13/2019 | Connected |  | N
National Grid | LAWRENCE | 532028 | 01841 | 10 |  |  | Solar |  | 05_01_226L1 | 07/07/2023 | 07/11/2023 | 2 | 0 | 2 | 07/12/2023 | 07/12/2023 | 22 | 0 | 22 | 10/02/2023 | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 12/11/2024 | N | EXP | 365 | 12/22/2023 | 01/24/2024 | 34 | 0 | 34 |  |  | 2/1/2024 | Connected |  | Y
National Grid | METHUEN | 661695 | 01844 | 10 |  |  | Solar |  | 05_01_406L1 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 175715 | 01826 | 1500 |  |  | Solar |  | 05_01_552L1 | 12/30/2014 | 12/30/2014 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2015 | 02/24/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 174946 | 01463 | 142 |  |  | Solar |  | 05_01_8W2 | 09/24/2012 | 09/24/2012 | 7 | 0 | 7 | 10/04/2012 | 10/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2013 |  | 12/3/2012 | N | EXP | -43 |  |  | 0 | 0 | 0 | 1/15/2013 | 1/15/2013 | 2/8/2013 | Connected |  | N
National Grid | OXFORD | 424613 | 01537 | 10 |  |  | Solar |  | 05_05_28W51 | 04/21/2022 | 04/27/2022 | 4 | 0 | 4 | 04/28/2022 | 04/28/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/21/2022 | 9/20/2023 | Y | EXP | 365 | 08/19/2022 | 09/19/2022 | 32 | 0 | 32 |  |  | 9/27/2022 | Connected |  | Y
National Grid | SPENCER | 243069 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 10/25/2019 | 10/30/2019 | 2 | 0 | 2 | 10/31/2019 | 10/31/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 583467 | 01607 | 10 |  |  | Solar |  | 05_14_211L1 | 01/15/2024 | 03/07/2024 | 37 | 28 | 9 | 03/08/2024 | 03/08/2024 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | FALL RIVER | 650617 | 02720 | 17.28 |  |  | Solar |  | 05_14_53J4 | 10/29/2024 | 11/01/2024 | 3 | 1 | 2 | 11/04/2024 | 11/04/2024 | 131 | 111 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | MEDFORD | 195563 | 02155 | 180 |  |  | Solar |  | 05_14_63L2 | 09/11/2018 | 10/03/2018 | 15 | 0 | 15 | 10/04/2018 | 10/04/2018 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | TYNGSBORO | 192918 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 08/07/2018 | 10/26/2018 | 7 | 7 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 577018 | 01841 | 6.67 |  |  | Solar |  | 05_01_226L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 667149 | 01844 | 12.54 |  |  | Solar |  | 05_01_406L1 | 01/22/2025 | 02/13/2025 | 6 | 1 | 5 | 02/14/2025 | 02/14/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/22/2025 | 4/16/2026 | Y | EXP | 365 | 07/02/2025 | 10/23/2025 | 114 | 0 | 114 |  |  | 10/24/2025 | Connected |  | N
National Grid | DRACUT | 175966 | 01826 | 18 |  |  | Solar |  | 05_01_552L1 | 08/06/2015 | 08/06/2015 | 4 | 4 | 0 | 08/14/2015 | 08/14/2015 | 216 | 0 | 216 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/15/2016 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 175176 | 01463 | 18 |  |  | Solar |  | 05_01_8W2 | 04/30/2013 | 04/30/2013 | 7 | 1 | 6 | 05/10/2013 | 05/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 7/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/25/2013 | Connected |  | N
National Grid | CHARLTON | 484084 | 01507 | 126.3 |  |  | Solar |  | 05_05_28W51 | 12/14/2022 | 02/10/2023 | 39 | 29 | 10 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 250240 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 08/22/2019 | 09/18/2019 | 18 | 18 | 0 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 590700 | 01527 | 7.6 |  |  | Solar |  | 05_14_211L1 | 03/04/2024 | 03/11/2024 | 5 | 1 | 4 | 03/12/2024 | 03/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | FALL RIVER | 652019 | 02720 | 15.2 |  |  | Solar |  | 05_14_53J4 | 11/04/2024 | 11/20/2024 | 12 | 10 | 2 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | MEDFORD | 197393 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 10/01/2018 | 10/26/2018 | 4 | 4 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 193202 | 01879 | 15.2 |  |  | Solar |  | 05_14_78L1 | 08/10/2018 | 09/10/2018 | 6 | 6 | 0 | 09/11/2018 | 09/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 08/10/2018 | 7/7/2020 | Y | EXP | 500 | 02/14/2019 | 03/11/2019 | 25 | 0 | 25 |  |  | 6/19/2020 | Connected |  | N
National Grid | LAWRENCE | 586042 | 01841 | 8.41 |  |  | Solar |  | 05_01_226L1 | 02/09/2024 | 02/13/2024 | 2 | 0 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/09/2024 | 3/1/2025 | Y | EXP | 365 | 04/16/2024 | 06/05/2024 | 51 | 0 | 51 |  |  | 6/13/2024 | Connected |  | N
National Grid | METHUEN | 671156 | 01844 | 9.28 |  |  | Solar |  | 05_01_406L1 | 02/10/2025 | 03/15/2025 | 14 | 10 | 4 | 03/17/2025 | 03/17/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 176251 | 01826 | 499 |  |  | Solar |  | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 620 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | PEPPERELL | 176546 | 01463 | 1992 |  |  | Solar |  | 05_01_8W2 | 04/03/2016 | 04/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2016 | 05/09/2016 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 04/03/2016 | 11/14/2018 | Y | STD | 807 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N
National Grid | CHARLTON | 646688 | 01507 | 0 |  |  | Solar |  | 05_05_28W51 | 10/11/2024 | 12/09/2024 | 8 | 5 | 3 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | SPENCER | 258934 | 01562 | 3.8 |  |  | Solar |  | 05_12_37W4 | 10/12/2019 | 10/14/2019 | 0 | 0 | 0 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 633351 | 01527 | 7.6 |  |  | Solar |  | 05_14_211L1 | 08/19/2024 | 08/22/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 08/19/2024 | 11/15/2025 | Y | EXP | 365 | 12/19/2024 | 02/24/2025 | 68 | 0 | 68 |  |  | 2/28/2025 | Connected |  | N
National Grid | FALL RIVER | 661153 | 02720 | 10 |  |  | Solar |  | 05_14_53J4 | 12/17/2024 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 205248 | 02155 | 10 |  |  | Solar |  | 05_14_63L2 | 01/25/2019 | 03/14/2019 | 32 | 26 | 6 | 03/15/2019 | 03/15/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 214576 | 01879 | 3 |  |  | Solar |  | 05_14_78L1 | 03/22/2019 | 03/29/2019 | 4 | 0 | 4 | 04/01/2019 | 04/01/2019 | 125 | 25 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 623421 | 01841 | 2100 |  |  | Solar |  | 05_01_226L1 | 07/11/2024 |  | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 671401 | 01844 | 23 |  |  | Solar |  | 05_01_406L1 | 02/11/2025 | 02/14/2025 | 4 | 1 | 3 | 02/18/2025 | 02/18/2025 | 123 | 102 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 176250 | 01826 | 499 |  |  | Solar |  | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 620 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | PEPPERELL | 177041 | 01463 | 4400 |  |  | Solar |  | 05_01_8W2 | 10/18/2016 | 10/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 |  | 10/23/2016 | N | STD | -3 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | CHARLTON | 674818 | 01507 | 7.6 |  |  | Solar |  | 05_05_28W51 | 03/05/2025 | 03/10/2025 | 3 | 0 | 3 | 03/11/2025 | 03/11/2025 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | SPENCER | 323871 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 01/11/2021 | 01/22/2021 | 7 | 7 | 0 | 01/25/2021 | 01/25/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 1/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 635683 | 01607 | 150 |  |  | Solar |  | 05_14_211L1 | 09/11/2024 | 10/04/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2024 | 06/04/2025 | 162 | 75 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 679548 | 02720 | 10 |  |  | Solar |  | 05_14_53J4 | 03/21/2025 | 04/16/2025 | 16 | 9 | 7 | 05/20/2025 | 05/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 03/21/2025 | 7/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MEDFORD | 204947 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 01/16/2019 | 01/30/2019 | 9 | 8 | 1 | 01/31/2019 | 01/31/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 218549 | 01879 | 3 |  |  | Solar |  | 05_14_78L1 | 05/08/2019 | 05/17/2019 | 7 | 7 | 0 | 05/20/2019 | 05/20/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/08/2019 | 3/31/2020 | Y | EXP | 301 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/1/2019 | Connected |  | N
National Grid | LAWRENCE | 648781 | 01841 | 10 |  |  | Solar |  | 05_01_226L1 | 10/22/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/22/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | METHUEN | 676130 | 01844 | 20 |  |  | Solar |  | 05_01_406L1 | 03/07/2025 | 03/17/2025 | 6 | 0 | 6 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 176305 | 01826 | 16.5 |  |  | Solar |  | 05_01_552L1 | 02/20/2015 | 02/20/2015 | 10 | 5 | 5 | 03/07/2015 | 03/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 7/31/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 7/29/2015 | Connected |  | N
National Grid | PEPPERELL | 177204 | 01463 | 299.8 |  |  | Solar |  | 05_01_8W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176268 | 01507 | 17.6 |  |  | Solar |  | 05_05_2J1 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 480 | 0 | 480 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 331642 | 01562 | 10 |  |  | Solar |  | 05_12_37W4 | 12/15/2020 | 12/21/2020 | 3 | 0 | 3 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 | 12/15/2020 | 12/16/2021 | Y | EXP | 365 | 04/16/2021 | 05/04/2021 | 18 | 0 | 18 |  |  | 6/28/2021 | Connected |  | N
National Grid | WORCESTER | 666071 | 01607 | 0 |  |  | Battery Add-On |  | 05_14_211L1 | 01/15/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 703816 | 02720 | 6 |  |  | Solar |  | 05_14_53J4 | 07/09/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | MEDFORD | 244231 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 07/23/2019 | 08/02/2019 | 7 | 2 | 5 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 8/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | TYNGSBORO | 229113 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 08/30/2019 | 09/04/2019 | 2 | 2 | 0 | 09/05/2019 | 09/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  | 9/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2020 | Connected |  | N
National Grid | LAWRENCE | 653619 | 01841 | 8.125 |  |  | Solar |  | 05_01_226L1 | 11/12/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | METHUEN | 703419 | 01844 | 7.6 |  |  | Solar |  | 05_01_406L1 | 07/10/2025 | 07/23/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 | 07/10/2025 | 9/8/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 176428 | 01826 | 10 |  |  | Solar |  | 05_01_552L1 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/9/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 204126 | 01463 | 313.2 |  |  | Solar |  | 05_01_8W2 | 12/18/2018 | 01/22/2019 | 21 | 17 | 4 | 01/23/2019 | 01/23/2019 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 484664 | 01537 | 6 |  |  | Solar |  | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2023 | 01/31/2023 | 7/26/2024 | Y | EXP | 365 | 07/01/2023 | 07/27/2023 | 27 | 0 | 27 |  |  | 8/2/2023 | Connected |  | N
National Grid | SPENCER | 347803 | 01562 | 4.64 |  |  | Solar |  | 05_12_37W4 | 04/07/2021 | 01/06/2022 | 4 | 0 | 4 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 1/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2022 | Connected |  | N
National Grid | WORCESTER | 706405 | 01602 | 0 |  |  | Solar |  | 05_14_211L1 | 07/22/2025 | 07/24/2025 | 2 | 0 | 2 | 07/25/2025 | 07/25/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | FALL RIVER | 688403 | 02720 | 12.54 |  |  | Solar |  | 05_14_53J5 | 05/05/2025 | 06/09/2025 | 22 | 18 | 4 | 06/10/2025 | 06/10/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 05/05/2025 | 10/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MEDFORD | 259289 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 10/17/2019 | 10/22/2019 | 2 | 0 | 2 | 10/23/2019 | 10/23/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 | 10/17/2019 | 7/7/2020 | Y | EXP | 365 | 03/13/2020 | 06/01/2020 | 80 | 0 | 80 |  |  | 6/5/2020 | Connected |  | N
National Grid | TYNGSBORO | 242622 | 01879 | 5 |  |  | Solar |  | 05_14_78L1 | 07/18/2019 | 08/14/2019 | 19 | 19 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 7/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2020 | Connected |  | N
National Grid | LAWRENCE | 684832 | 01841 | 17.6 |  |  | Solar |  | 05_01_226L1 | 04/14/2025 | 04/21/2025 | 4 | 1 | 3 | 04/22/2025 | 04/22/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | METHUEN | 679432 | 01844 | 0 |  |  | Battery Add-On |  | 05_01_406L2 | 04/14/2025 | 04/25/2025 | 7 | 3 | 4 | 04/28/2025 | 04/28/2025 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 176541 | 01826 | 900 |  |  | Solar |  | 05_01_552L1 | 02/10/2016 | 02/16/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/08/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 | 02/10/2016 | 2/11/2022 | Y | STD | 1348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 309736 | 01463 | 7.6 |  |  | Solar |  | 05_01_8W2 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 484658 | 01507 | 6 |  |  | Solar |  | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | SPENCER | 359749 | 01562 | 15 |  |  | Solar |  | 05_12_37W4 | 08/24/2021 | 04/28/2022 | 168 | 159 | 9 | 04/29/2022 | 04/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 564846 | 01607 | 200 |  |  | Solar |  | 05_14_211L2 | 10/24/2023 | 11/07/2023 | 10 | 0 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 10/24/2023 | 1/4/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ATTLEBORO | 699286 | 02703 | 7.6 |  |  | Solar |  | 05_14_53J5 | 06/19/2025 | 07/03/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 53 | 38 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MEDFORD | 269213 | 02155 | 9.84 |  |  | Solar |  | 05_14_63L2 | 12/11/2019 | 12/13/2019 | 2 | 2 | 0 | 12/16/2019 | 12/16/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | TYNGSBORO | 250354 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 08/26/2019 | 09/03/2019 | 4 | 4 | 0 | 09/04/2019 | 09/04/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 | 08/26/2019 | 8/26/2020 | Y | EXP | 365 | 03/13/2020 | 06/02/2020 | 81 | 0 | 81 |  |  | 7/24/2020 | Connected |  | N
National Grid | LAWRENCE | 696444 | 01841 | 9.5 |  |  | Solar |  | 05_01_226L1 | 06/05/2025 | 06/25/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | METHUEN | 684121 | 01844 | 11.4 |  |  | Solar |  | 05_01_406L2 | 04/14/2025 | 04/18/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 176750 | 01826 | 11.4 |  |  | Solar |  | 05_01_552L1 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 265 | 0 | 265 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/17/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 382570 | 01463 | 350 |  |  | Solar |  | 05_01_8W2 | 11/11/2021 | 12/16/2021 | 24 | 15 | 9 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 505519 | 01507 | 7.6 |  |  | Solar |  | 05_05_2J1 | 03/15/2023 | 03/22/2023 | 5 | 4 | 1 | 03/23/2023 | 03/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 469990 | 01562 | 0 |  |  | Solar |  | 05_12_37W4 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 4/20/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174740 | 01607 | 5500 |  |  | Solar |  | 05_14_211L2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2013 | 04/04/2013 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 381732 | 02703 | 6 |  |  | Solar |  | 05_14_53J5 | 09/23/2021 | 01/03/2022 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 09/23/2021 | 5/28/2023 | Y | EXP | 365 | 04/14/2022 | 05/21/2022 | 36 | 0 | 36 |  |  | 6/30/2022 | Connected |  | Y
National Grid | MEDFORD | 278631 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 03/05/2020 |  | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 253040 | 01879 | 17.6 |  |  | Solar |  | 05_14_78L1 | 09/09/2019 | 09/11/2019 | 1 | 0 | 1 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | METHUEN | 712303 | 01844 | 22.8 |  |  | Solar |  | 05_01_226L2 | 10/02/2025 | 10/10/2025 | 6 | 4 | 2 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 726973 | 01844 | 7.6 |  |  | Solar |  | 05_01_406L2 | 10/16/2025 | 11/13/2025 | 3 | 0 | 3 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 177078 | 01826 | 22.8 |  |  | Solar |  | 05_01_552L1 | 10/17/2016 | 10/17/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/17/2016 | 10/23/2017 | Y | EXP | 364 | 03/28/2017 | 05/22/2017 | 38 | 0 | 38 | 8/29/2017 | 8/29/2017 | 9/1/2017 | Connected |  | N
National Grid | PEPPERELL | 644286 | 01463 | 5.76 |  |  | Solar |  | 05_01_8W2 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | AUBURN | 608945 | 01501 | 10 |  |  | Solar |  | 05_05_2J2 | 05/06/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 05/06/2024 | 6/6/2025 | Y | EXP | 365 | 08/21/2024 | 09/26/2024 | 37 | 0 | 37 |  |  | 10/25/2024 | Connected |  | N
National Grid | SPENCER | 541845 | 01562 | 15.66 |  |  | Solar |  | 05_12_37W4 | 07/24/2023 |  | 96 | 70 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177013 | 01607 | 7.6 |  |  | Solar |  | 05_14_211L2 | 01/05/2017 | 01/05/2017 | 8 | 8 | 0 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2017 |  | 1/10/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/2/2017 | Connected |  | N
National Grid | ATTLEBORO | 522777 | 02703 | 3.8 |  |  | Solar |  | 05_14_53J5 | 05/17/2023 | 05/19/2023 | 2 | 2 | 0 | 05/22/2023 | 05/22/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | MEDFORD | 360395 | 02155 | 8.99 |  |  | Solar |  | 05_14_63L2 | 07/27/2021 | 12/28/2021 | 10 | 8 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 07/27/2021 |  | Y | EXP | 365 | 03/08/2022 | 03/30/2022 | 23 | 0 | 23 |  |  | 4/7/2022 | Connected |  | N
National Grid | TYNGSBORO | 301330 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 08/07/2020 | 08/10/2020 | 0 | 0 | 0 | 08/11/2020 | 08/11/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/07/2020 | 8/9/2021 | Y | EXP | 365 | 10/28/2020 | 11/10/2020 | 13 | 0 | 13 |  |  | 1/25/2021 | Connected |  | N
National Grid | LAWRENCE | 716113 | 01841 | 13.36 |  |  | Solar |  | 05_01_226L2 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 174703 | 01844 | 492 |  |  | Solar |  | 05_01_406L2 | 06/10/2013 | 06/10/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2013 | 07/22/2013 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 06/10/2013 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 177415 | 01826 | 995 |  |  | Landfill Gas |  | 05_01_552L1 | 09/15/2016 | 09/26/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2016 | 10/18/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/15/2016 | 11/12/2019 | Y | STD | 928 | 01/09/2019 | 02/24/2019 | 46 | 0 | 46 |  |  | 10/31/2019 | Connected |  | N
National Grid | PEPPERELL | 652196 | 01463 | 7.6 |  |  | Solar |  | 05_01_8W2 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | AUBURN | 174441 | 01501 | 1875 |  |  | Solar |  | 05_05_2J3 | 06/28/2012 | 06/28/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2012 | 08/21/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 578165 | 01562 | 10 |  |  | Solar |  | 05_12_37W4 | 12/20/2023 | 01/04/2024 | 8 | 8 | 0 | 01/05/2024 | 01/05/2024 | 19 | 0 | 19 | 02/05/2024 | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/26/2025 | N | EXP | 365 | 03/16/2024 | 07/23/2024 | 130 | 29 | 101 |  |  | 8/5/2024 | Connected |  | N
National Grid | WORCESTER | 177845 | 01607 | 910 |  |  | Solar |  | 05_14_211L2 | 10/17/2017 | 10/17/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 500876 | 02703 | 200 |  |  | Solar |  | 05_14_54L3 | 03/31/2023 | 04/17/2023 | 10 | 0 | 10 | 04/18/2023 | 04/18/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 03/31/2023 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | MEDFORD | 367847 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 07/19/2021 | 07/22/2021 | 3 | 0 | 3 | 07/23/2021 | 07/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 | 07/19/2021 |  | Y | EXP | 365 | 01/21/2022 | 01/24/2022 | 4 | 0 | 4 |  |  | 4/4/2022 | Connected |  | N
National Grid | TYNGSBORO | 339584 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2021 | Connected |  | N
National Grid | LAWRENCE | 722437 | 01841 | 15.2 |  |  | Solar |  | 05_01_226L2 | 09/26/2025 | 10/06/2025 | 5 | 3 | 2 | 10/07/2025 | 10/07/2025 | 39 | 22 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 175330 | 01844 | 996 |  |  | Solar |  | 05_01_406L2 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 177649 | 01826 | 7.6 |  |  | Solar |  | 05_01_552L1 | 09/27/2017 | 09/27/2017 | 8 | 8 | 0 | 10/10/2017 | 10/10/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2017 |  | 10/2/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | Connected |  | N
National Grid | PEPPERELL | 709990 | 01463 | 7.98 |  |  | Solar |  | 05_01_8W2 | 08/06/2025 | 09/18/2025 | 9 | 4 | 5 | 09/19/2025 | 09/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | AUBURN | 177231 | 01501 | 72 |  |  | Solar |  | 05_05_2J3 | 11/03/2016 | 11/03/2016 | 8 | 8 | 0 | 11/17/2016 | 11/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/03/2016 | 11/9/2017 | Y | EXP | 352 | 03/02/2017 | 03/20/2017 | 12 | 0 | 12 | 5/16/2017 | 5/16/2017 | 5/22/2017 | Connected |  | N
National Grid | SPENCER | 580959 | 01562 | 23 |  |  | Solar |  | 05_12_37W4 | 01/02/2024 | 03/14/2024 | 44 | 43 | 1 | 03/15/2024 | 03/15/2024 | 41 | 36 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 01/02/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/18/2024 | 16 | 0 | 16 |  |  | 9/25/2024 | Connected |  | N
National Grid | WORCESTER | 187599 | 01607 | 240 |  |  | Solar |  | 05_14_211L2 | 06/08/2018 | 06/12/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  | 7/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | ATTLEBORO | 604615 | 02703 | 17.6 |  |  | Solar |  | 05_14_54L3 | 06/07/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 392062 | 02155 | 8.7 |  |  | Solar |  | 05_14_63L2 | 11/29/2021 | 02/07/2022 | 48 | 44 | 4 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 356821 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 06/03/2021 | 01/07/2022 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 | 06/03/2021 | 3/8/2023 | Y | EXP | 365 | 01/26/2022 | 03/07/2022 | 41 | 0 | 41 |  |  | 8/11/2022 | Connected |  | Y
National Grid | METHUEN | 725613 | 01844 | 4.56 |  |  | Solar |  | 05_01_226L2 | 10/10/2025 | 10/16/2025 | 1 | 0 | 1 | 10/28/2025 | 10/28/2025 | 44 | 27 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 175412 | 01844 | 2000 |  |  | Solar |  | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 177634 | 01826 | 2000 |  |  | Solar |  | 05_01_552L1 | 07/19/2017 | 08/01/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2017 | 08/21/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 | 07/19/2017 | 6/26/2020 | Y | STD | 645 | 10/29/2019 | 05/20/2020 | 202 | 0 | 202 |  |  | 6/26/2020 | Connected |  | N
National Grid | PEPPERELL | 657038 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J302 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | OXFORD | 555478 | 01540 | 240 |  |  | Solar |  | 05_05_310W3 | 09/15/2023 | 09/29/2023 | 10 | 1 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/15/2023 | 4/18/2026 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SPENCER | 608550 | 01562 | 6 |  |  | Solar |  | 05_12_37W4 | 05/03/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/03/2024 | 7/3/2025 | Y | EXP | 365 | 08/20/2024 | 01/20/2025 | 154 | 0 | 154 |  |  | 2/3/2025 | Connected |  | N
National Grid | WORCESTER | 190345 | 01607 | 7.6 |  |  | Solar |  | 05_14_211L2 | 07/10/2018 | 07/13/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 694492 | 02703 | 10 |  |  | Solar |  | 05_14_54L3 | 06/02/2025 | 06/16/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 37 | 23 | 14 | 08/22/2025 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | MEDFORD | 402955 | 02155 | 99.9 |  |  | Solar |  | 05_14_63L2 | 07/12/2022 | 09/07/2022 | 41 | 30 | 11 | 09/08/2022 | 09/08/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 359517 | 01879 | 15.12 |  |  | Solar |  | 05_14_78L1 | 05/20/2021 | 07/22/2021 | 42 | 35 | 7 | 07/23/2021 | 07/23/2021 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 730024 | 01810 | 1000 |  |  | Solar |  | 05_01_226L2 | 11/03/2025 | 11/20/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | METHUEN | 175411 | 01844 | 1992 |  |  | Solar |  | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 178079 | 01826 | 2199 |  |  | Solar |  | 05_01_552L1 | 05/05/2017 | 08/24/2017 | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2017 | 09/28/2017 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2018 | 05/05/2017 | 6/6/2025 | Y | STD | 144 | 02/21/2020 | 05/08/2024 | 1539 | 15 | 1524 |  |  | 6/25/2025 | Connected |  | N
National Grid | PEPPERELL | 689482 | 01463 | 16.64 |  |  | Solar |  | 05_01_9J302 | 05/06/2025 | 05/12/2025 | 4 | 0 | 4 | 05/13/2025 | 05/13/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | OXFORD | 174781 | 01540 | 480 |  |  | Solar |  | 05_05_310W3 | 07/08/2013 | 07/08/2013 | 8 | 0 | 8 | 07/19/2013 | 07/19/2013 | 0 | 0 | 0 | 11/05/2013 | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 2/11/2014 | 07/08/2013 | 12/20/2017 | Y | EXP | 1408 | 09/22/2017 | 10/16/2017 | 15 | 0 | 15 | 9/18/2017 | 9/18/2017 | 12/1/2017 | Connected |  | N
National Grid | SPENCER | 618725 | 01562 | 6 |  |  | Solar |  | 05_12_37W4 | 06/18/2024 | 07/03/2024 | 5 | 4 | 1 | 07/05/2024 | 07/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | WORCESTER | 193772 | 01607 | 15.2 |  |  | Solar |  | 05_14_211L2 | 08/17/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 702988 | 02703 | 11.78 |  |  | Solar |  | 05_14_54L3 | 07/06/2025 | 09/04/2025 | 43 | 42 | 1 | 09/05/2025 | 09/05/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MEDFORD | 408867 | 02155 | 0 |  |  | Other |  | 05_14_63L2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 377505 | 01879 | 4.93 |  |  | Solar |  | 05_14_78L1 | 09/13/2021 | 01/07/2022 | 2 | 0 | 2 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 | 09/13/2021 |  | Y | EXP | 365 | 02/22/2022 | 03/10/2022 | 16 | 0 | 16 |  |  | 3/29/2022 | Connected |  | N
National Grid | ANDOVER | 174867 | 01810 | 11 |  |  | Solar |  | 05_01_226L2 | 08/06/2012 | 08/06/2012 | 6 | 0 | 6 | 08/16/2012 | 08/16/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | -12 |  |  | 0 | 0 | 0 | 12/21/2012 | 12/21/2012 | 2/14/2013 | Connected |  | N
National Grid | METHUEN | 175410 | 01844 | 1992 |  |  | Solar |  | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 12/1/2016 | Connected |  | N
National Grid | DRACUT | 178481 | 01826 | 5000 |  |  | Solar |  | 05_01_552L1 | 04/03/2018 | 04/03/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 578629 | 01463 | 299 |  |  | Solar |  | 05_01_9J303 | 01/29/2024 |  | 470 | 25 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 176778 | 01540 | 576 |  |  | Solar |  | 05_05_310W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2015 | 12/09/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 637464 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 09/03/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/03/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WORCESTER | 240929 | 01604 | 10 |  |  | Solar |  | 05_14_211L2 | 08/07/2019 | 08/13/2019 | 3 | 0 | 3 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 734376 | 01772 | 37.82 |  |  | Solar |  | 05_14_54L3 | 11/17/2025 | 11/18/2025 | 1 | 0 | 1 | 11/19/2025 | 11/19/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MEDFORD | 414323 | 02155 | 499 |  |  | Solar |  | 05_14_63L2 | 04/01/2022 | 05/25/2022 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/01/2022 | 1/20/2025 | Y | STD | 43 | 04/19/2024 | 08/16/2024 | 120 | 28 | 92 |  |  | 1/17/2025 | Connected |  | N
National Grid | TYNGSBORO | 402327 | 01879 | 15.2 |  |  | Solar |  | 05_14_78L1 | 12/20/2021 | 12/23/2021 | 3 | 2 | 1 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  | 2/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176589 | 01810 | 19.75 |  |  | Solar |  | 05_01_226L2 | 10/08/2015 | 10/08/2015 | 0 | 0 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2015 |  | 10/14/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 12/24/2015 | 12/24/2015 | 12/24/2015 | Connected |  | N
National Grid | METHUEN | 175409 | 01844 | 996 |  |  | Solar |  | 05_01_406L2 | 03/04/2014 | 03/04/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/04/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 178736 | 01826 | 7.6 |  |  | Solar |  | 05_01_552L1 | 02/12/2018 | 03/15/2018 | 0 | 0 | 0 | 03/15/2018 | 03/15/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 2/18/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 595193 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J303 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 8 | 0 | 8 | 04/23/2024 | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/15/2025 | N | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | OXFORD | 373284 | 01540 | 10 |  |  | Solar |  | 05_05_310W3 | 08/02/2021 | 08/05/2021 | 3 | 2 | 1 | 08/06/2021 | 08/06/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N
National Grid | SPENCER | 639222 | 01562 | 6 |  |  | Solar |  | 05_12_37W4 | 09/10/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/10/2024 | 11/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WORCESTER | 254655 | 01604 | 10 |  |  | Solar |  | 05_14_211L2 | 10/01/2019 | 10/04/2019 | 2 | 2 | 0 | 10/07/2019 | 10/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/01/2019 | 10/1/2020 | Y | EXP | 365 | 01/09/2020 | 04/17/2020 | 99 | 0 | 99 |  |  | 5/19/2020 | Connected |  | N
National Grid | SOUTHBOROUGH | 732162 | 01772 | 13.8 |  |  | Solar |  | 05_14_54L3 | 11/06/2025 | 11/07/2025 | 2 | 0 | 2 | 11/19/2025 | 11/19/2025 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MEDFORD | 458326 | 02155 | 7.83 |  |  | Solar |  | 05_14_63L2 | 10/27/2022 | 11/21/2022 | 16 | 14 | 2 | 11/22/2022 | 11/22/2022 | 21 | 0 | 21 | 01/17/2023 | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 2/2/2023 |  | 11/30/2024 | N | EXP | 365 | 06/15/2023 | 01/26/2024 | 226 | 3 | 223 |  |  | 3/9/2024 | Connected |  | N
National Grid | TYNGSBORO | 425044 | 01879 | 10 |  |  | Solar |  | 05_14_78L1 | 05/09/2022 | 05/09/2022 | 0 | 0 | 0 | 05/10/2022 | 05/10/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 05/09/2022 | 7/20/2023 | Y | EXP | 365 | 07/16/2022 | 07/18/2022 | 3 | 0 | 3 |  |  | 5/1/2023 | Connected |  | Y
National Grid | ANDOVER | 176760 | 01810 | 10 |  |  | Solar |  | 05_01_226L2 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 07/06/2016 | 08/27/2016 | 38 | 0 | 38 | 4/4/2016 | 4/4/2016 | 11/4/2016 | Connected |  | N
National Grid | METHUEN | 175408 | 01844 | 2000 |  |  | Solar |  | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 178773 | 01826 | 1980 |  |  | Solar |  | 05_01_552L1 | 04/29/2013 | 04/29/2013 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2013 | 07/22/2013 | 25 | 17 | 8 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 5/21/2014 | 04/29/2013 | 12/31/2016 | Y | STD | 955 | 06/24/2016 | 09/27/2016 | 65 | 0 | 65 | 10/26/2016 | 10/26/2016 | 10/28/2016 | Connected |  | N
National Grid | PEPPERELL | 602571 | 01463 | 6 |  |  | Solar |  | 05_01_9J303 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 417351 | 01540 | 11.4 |  |  | Solar |  | 05_05_310W3 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 651801 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W4 | 11/04/2024 | 11/27/2024 | 14 | 10 | 4 | 12/02/2024 | 12/02/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/04/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | WORCESTER | 368610 | 01604 | 6 |  |  | Solar |  | 05_14_211L2 | 07/12/2021 | 07/13/2021 | 1 | 0 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175182 | 01752 | 490 |  |  | Solar |  | 05_14_54L3 | 05/09/2013 | 05/09/2013 | 7 | 0 | 7 | 05/21/2013 | 05/21/2013 | 419 | 4 | 415 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2013 |  | 12/31/2013 | N | EXP | 181 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 480100 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 104 | 83 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 428394 | 01879 | 5.8 |  |  | Solar |  | 05_14_78L1 | 05/09/2022 | 05/11/2022 | 2 | 0 | 2 | 05/12/2022 | 05/12/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 |  | 7/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2022 | Connected |  | N
National Grid | ANDOVER | 177411 | 01810 | 20 |  |  | Solar |  | 05_01_226L2 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/26/2016 | 09/26/2016 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 9/17/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175667 | 01844 | 470 |  |  | Solar |  | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 184382 | 01826 | 7.6 |  |  | Solar |  | 05_01_552L1 | 05/02/2018 | 05/02/2018 | 2 | 0 | 2 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 632680 | 01463 | 6 |  |  | Solar |  | 05_01_9J303 | 08/14/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | OXFORD | 439607 | 01540 | 15.2 |  |  | Solar |  | 05_05_310W3 | 06/23/2022 | 06/29/2022 | 4 | 0 | 4 | 06/30/2022 | 06/30/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2023 | Connected |  | N
National Grid | SPENCER | 669101 | 01562 | 4.06 |  |  | Solar |  | 05_12_37W4 | 01/31/2025 | 02/13/2025 | 6 | 2 | 4 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WORCESTER | 475793 | 01604 | 3.8 |  |  | Solar |  | 05_14_211L2 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 12/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 175885 | 01772 | 6.75 |  |  | Solar |  | 05_14_54L3 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 8/26/2015 | 8/26/2015 | 9/1/2015 | Connected |  | N
National Grid | MEDFORD | 524456 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 05/15/2023 | 05/16/2023 | 1 | 0 | 1 | 05/17/2023 | 05/17/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 430404 | 01879 | 6 |  |  | Solar |  | 05_14_78L1 | 05/24/2022 | 06/02/2022 | 7 | 5 | 2 | 06/03/2022 | 06/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2022 | 05/24/2022 | 10/13/2023 | Y | EXP | 365 | 09/28/2022 | 10/12/2022 | 15 | 0 | 15 |  |  | 10/24/2022 | Connected |  | N
National Grid | ANDOVER | 178118 | 01810 | 10 |  |  | Solar |  | 05_01_226L2 | 05/11/2017 | 05/11/2017 | 4 | 4 | 0 | 05/17/2017 | 05/17/2017 | 181 | 0 | 181 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 |  | 5/16/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175666 | 01844 | 996 |  |  | Solar |  | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 189203 | 01826 | 3.8 |  |  | Solar |  | 05_01_552L1 | 06/26/2018 | 06/26/2018 | 24 | 0 | 24 | 08/15/2018 | 08/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 645660 | 01463 | 5.76 |  |  | Solar |  | 05_01_9J303 | 10/25/2024 | 11/12/2024 | 7 | 2 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | OXFORD | 448026 | 01540 | 10 |  |  | Solar |  | 05_05_310W3 | 07/29/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2022 | 07/29/2022 | 9/6/2023 | Y | EXP | 365 | 10/11/2022 | 03/03/2023 | 144 | 0 | 144 |  |  | 3/7/2023 | Connected |  | N
National Grid | CHARLTON | 677804 | 01507 | 5.8 |  |  | Solar |  | 05_12_37W4 | 03/18/2025 | 03/31/2025 | 1 | 0 | 1 | 04/14/2025 | 04/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2025 | Connected |  | N
National Grid | WORCESTER | 576580 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_211L2 | 12/07/2023 | 02/08/2024 | 43 | 39 | 4 | 02/09/2024 | 02/09/2024 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 | 12/07/2023 | 4/29/2025 | Y | EXP | 365 | 05/23/2024 | 05/22/2024 | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 177008 | 01772 | 494.5 |  |  | Solar |  | 05_14_54L3 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 02/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 | 10/13/2016 | 4/9/2018 | Y | EXP | 374 | 06/01/2017 | 06/01/2017 | 0 | 0 | 0 | 4/3/2018 | 4/3/2018 | 4/3/2018 | Connected |  | N
National Grid | MEDFORD | 527876 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 499858 | 01879 | 10 |  |  | Solar |  | 05_14_78L1 | 02/16/2023 | 02/23/2023 | 4 | 3 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | ANDOVER | 178432 | 01810 | 636 |  |  | Solar |  | 05_01_226L2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175665 | 01844 | 996 |  |  | Solar |  | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 189868 | 01826 | 4800 |  |  | Solar |  | 05_01_552L1 | 09/10/2018 | 10/18/2018 | 26 | 17 | 9 |  |  | 33 | 14 | 19 |  |  | 0 | 0 | 0 | 10/19/2018 | 12/08/2018 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 650688 | 01463 | 5.76 |  |  | Solar |  | 05_01_9J303 | 11/11/2024 | 01/14/2025 | 0 | 0 | 0 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | OXFORD | 485238 | 01540 | 15.2 |  |  | Solar |  | 05_05_310W3 | 12/13/2022 | 12/14/2022 | 1 | 0 | 1 | 12/15/2022 | 12/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | SPENCER | 686001 | 01562 | 5.76 |  |  | Solar |  | 05_12_37W4 | 04/17/2025 | 05/21/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | WORCESTER | 644867 | 01604 | 8.45 |  |  | Solar |  | 05_14_211L2 | 10/03/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 3 | 15 | 11/14/2024 | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/25/2025 | N | EXP | 365 | 01/14/2025 | 03/28/2025 | 74 | 0 | 74 |  |  | 4/2/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 178419 | 01772 | 19 |  |  | Solar |  | 05_14_54L3 | 01/16/2018 | 01/16/2018 | 23 | 0 | 23 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 1/22/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | MEDFORD | 568866 | 02155 | 10 |  |  | Solar |  | 05_14_63L2 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 36 | 12 | 24 | 04/01/2024 | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 4/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 521189 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 05/02/2023 | 05/03/2023 | 1 | 0 | 1 | 05/04/2023 | 05/04/2023 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 7/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | ANDOVER | 178743 | 01810 | 990 |  |  | Solar |  | 05_01_226L2 | 05/30/2018 | 07/18/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 08/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175815 | 01844 | 360 |  |  | Solar |  | 05_01_406L2 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 625 | 0 | 625 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 8/24/2018 | N | EXP | 1120 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 189663 | 01826 | 15.2 |  |  | Solar |  | 05_01_552L1 | 06/29/2018 | 06/29/2018 | 8 | 7 | 1 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 678617 | 01463 | 13.36 |  |  | Solar |  | 05_01_9J303 | 03/17/2025 | 04/04/2025 | 2 | 0 | 2 | 04/10/2025 | 04/10/2025 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 | 03/17/2025 | 5/20/2026 | Y | EXP | 365 | 11/07/2025 | 12/01/2025 | 25 | 0 | 25 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 556943 | 01540 | 0 |  |  | Solar |  | 05_05_310W3 | 09/20/2023 | 10/05/2023 | 12 | 11 | 1 | 10/06/2023 | 10/06/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 3/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | SPENCER | 657513 | 01562 | 3.8 |  |  | Solar |  | 05_12_37W5 | 11/27/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 649505 | 01604 | 8.12 |  |  | Solar |  | 05_14_211L2 | 10/26/2024 | 12/03/2024 | 8 | 6 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 178410 | 01772 | 34.5 |  |  | Solar |  | 05_14_54L3 | 11/22/2017 | 11/22/2017 | 8 | 0 | 8 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 12/2/2018 | N | EXP | 193 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 599558 | 02155 | 10.075 |  |  | Solar |  | 05_14_63L2 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | TYNGSBORO | 559780 | 01879 | 8.505 |  |  | Solar |  | 05_14_78L1 | 11/13/2023 | 11/28/2023 | 10 | 6 | 4 | 11/29/2023 | 11/29/2023 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 11/13/2023 | 2/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | ANDOVER | 185273 | 01810 | 5310 |  |  | Solar |  | 05_01_226L2 | 07/23/2018 | 08/08/2018 | 12 | 12 | 0 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 08/09/2018 | 08/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175945 | 01844 | 1000 |  |  | Solar |  | 05_01_406L2 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 195817 | 01826 | 0 |  |  | Solar |  | 05_01_552L1 | 11/07/2018 |  | 151 | 25 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 608618 | 01463 | 10 |  |  | Solar |  | 05_01_9J306 | 05/03/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | Y
National Grid | OXFORD | 613596 | 01540 | 7.6 |  |  | Solar |  | 05_05_310W3 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | Y
National Grid | SPENCER | 691591 | 01535 | 7.6 |  |  | Solar |  | 05_12_37W5 | 05/14/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 657556 | 01604 | 10 |  |  | Solar |  | 05_14_211L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/28/2024 | 2/12/2026 | Y | EXP | 365 | 07/30/2025 |  | 156 | 0 | 156 |  |  | 11/21/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 190956 | 01772 | 77 |  |  | Solar |  | 05_14_54L3 | 07/17/2018 | 08/03/2018 | 9 | 6 | 3 | 08/06/2018 | 08/06/2018 | 9 | 0 | 9 | 10/05/2018 | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  | 10/1/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | MEDFORD | 619212 | 02155 | 14.95 |  |  | Solar |  | 05_14_63L2 | 06/22/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 06/22/2024 | 9/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | TYNGSBORO | 531489 | 01879 | 15.2 |  |  | Solar |  | 05_14_78L1 | 06/05/2023 | 06/06/2023 | 1 | 0 | 1 | 06/07/2023 | 06/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 198924 | 01810 | 10 |  |  | Solar |  | 05_01_226L2 | 10/18/2018 | 03/18/2019 | 39 | 35 | 4 | 03/19/2019 | 03/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/18/2018 | 1/14/2021 | Y | EXP | 365 | 06/03/2020 | 06/18/2020 | 15 | 0 | 15 |  |  | 7/3/2020 | Connected |  | N
National Grid | METHUEN | 176363 | 01844 | 7.6 |  |  | Solar |  | 05_01_406L2 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 | 03/08/2016 | 1/15/2018 | Y | EXP | 656 | 05/19/2017 | 06/02/2017 | 9 | 0 | 9 | 8/11/2017 | 8/11/2017 | 8/11/2017 | Connected |  | N
National Grid | DRACUT | 193213 | 01826 | 2988 |  |  | Solar |  | 05_01_552L1 | 01/09/2019 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/27/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 610910 | 01463 | 16.4 |  |  | Solar |  | 05_01_9J306 | 05/17/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2024 | Connected |  | N
National Grid | OXFORD | 616124 | 01540 | 15.2 |  |  | Solar |  | 05_05_310W3 | 06/06/2024 | 06/14/2024 | 6 | 4 | 2 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | SPENCER | 711000 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W5 | 08/11/2025 | 10/03/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 659846 | 01604 | 7.6 |  |  | Solar |  | 05_14_211L2 | 12/11/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 194950 | 01772 | 10 |  |  | Solar |  | 05_14_54L3 | 10/03/2018 | 10/04/2018 | 0 | 0 | 0 | 10/05/2018 | 10/05/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  | 10/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2019 | Connected |  | N
National Grid | MEDFORD | 641365 | 02155 | 7.6 |  |  | Solar |  | 05_14_63L2 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | TYNGSBORO | 569358 | 01879 | 6.09 |  |  | Solar |  | 05_14_78L1 | 11/14/2023 | 11/20/2023 | 4 | 1 | 3 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 11/14/2023 | 1/1/2025 | Y | EXP | 365 | 05/30/2024 | 07/15/2024 | 47 | 0 | 47 |  |  | 7/26/2024 | Connected |  | N
National Grid | ANDOVER | 204874 | 01810 | 7.6 |  |  | Solar |  | 05_01_226L2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2019 | Connected |  | N
National Grid | METHUEN | 176545 | 01844 | 10 |  |  | Solar |  | 05_01_406L2 | 03/31/2016 | 03/31/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 208846 | 01826 | 6 |  |  | Solar |  | 05_01_552L1 | 03/26/2019 |  | 69 | 26 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 665392 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J306 | 01/13/2025 | 02/14/2025 | 19 | 14 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/13/2025 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 174829 | 01501 | 270 |  |  | Solar |  | 05_05_310W4 | 12/01/2011 | 12/01/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2012 | 12/01/2011 | 7/9/2012 | Y | EXP | 178 | 06/20/2012 | 06/28/2012 | 6 | 0 | 6 | 8/8/2012 | 8/8/2012 | 7/9/2012 | Connected |  | N
National Grid | SPENCER | 722271 | 01562 | 10 |  |  | Solar |  | 05_12_37W5 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/20/2025 | 11/20/2025 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 672483 | 01604 | 6 |  |  | Solar |  | 05_14_211L2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 02/18/2025 | 6/6/2026 | Y | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  | 12/4/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 206827 | 01772 | 0 |  |  | Solar |  | 05_14_54L3 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 07/30/2019 | 07/30/2019 | 249 | 121 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/14/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 646960 | 02155 | 10 |  |  | Solar |  | 05_14_63L2 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | TYNGSBORO | 613831 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 05/28/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | ANDOVER | 218005 | 01845 | 15.2 |  |  | Solar |  | 05_01_226L2 | 04/05/2019 | 04/12/2019 | 4 | 0 | 4 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 4/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | METHUEN | 178498 | 01844 | 276.4 |  |  | Solar |  | 05_01_406L2 | 01/23/2018 | 02/22/2018 | 0 | 0 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 12/31/2019 | N | EXP | 504 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | DRACUT | 220677 | 01826 | 5.12 |  |  | Solar |  | 05_01_552L1 | 05/20/2019 | 08/27/2019 | 68 | 67 | 1 | 08/28/2019 | 08/28/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 595739 | 01463 | 10 |  |  | Solar |  | 05_01_9J307 | 03/15/2024 | 06/11/2024 | 52 | 50 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | AUBURN | 175202 | 01501 | 110 |  |  | Solar |  | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SPENCER | 730332 | 01562 | 9.6 |  |  | Solar |  | 05_12_37W5 | 10/30/2025 | 10/30/2025 | 5 | 1 | 4 | 11/13/2025 | 11/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WORCESTER | 676121 | 01610 | 11.4 |  |  | Solar |  | 05_14_211L2 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 292996 | 01772 | 10 |  |  | Solar |  | 05_14_54L3 | 05/21/2020 | 05/22/2020 | 0 | 0 | 0 | 05/26/2020 | 05/26/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 |  | 5/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | MEDFORD | 657546 | 02155 | 5.76 |  |  | Solar |  | 05_14_63L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | TYNGSBORO | 619601 | 01879 | 10 |  |  | Solar |  | 05_14_78L1 | 06/21/2024 | 07/18/2024 | 8 | 6 | 2 | 07/19/2024 | 07/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 06/21/2024 | 9/18/2025 | Y | EXP | 365 | 02/28/2025 | 04/21/2025 | 53 | 0 | 53 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 257041 | 01845 | 4890 |  |  | Solar |  | 05_01_226L2 | 04/13/2020 | 05/19/2020 | 25 | 21 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2020 | 06/18/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 191422 | 01844 | 10 |  |  | Solar |  | 05_01_406L2 | 08/04/2018 | 09/13/2018 | 3 | 3 | 0 | 09/14/2018 | 09/14/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 08/04/2018 | 6/28/2019 | Y | EXP | 275 | 03/26/2019 | 04/01/2019 | 6 | 0 | 6 |  |  | 6/24/2019 | Connected |  | N
National Grid | DRACUT | 231646 | 01826 | 6.4 |  |  | Solar |  | 05_01_552L1 | 07/02/2019 | 07/17/2019 | 10 | 10 | 0 | 07/18/2019 | 07/18/2019 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2019 |  | 7/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | PEPPERELL | 670182 | 01463 | 10 |  |  | Solar |  | 05_01_9J307 | 02/05/2025 | 04/07/2025 | 5 | 0 | 5 | 04/08/2025 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 175196 | 01501 | 100 |  |  | Solar |  | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | Y
National Grid | SPENCER | 733641 | 01562 | 5.76 |  |  | Solar |  | 05_12_37W5 | 11/13/2025 | 11/19/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 708614 | 01610 | 23 |  |  | Solar |  | 05_14_211L2 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | MARLBOROUGH | 299887 | 01752 | 6 |  |  | Solar |  | 05_14_54L3 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | MEDFORD | 668345 | 02155 | 3.8 |  |  | Solar |  | 05_14_63L2 | 01/28/2025 | 03/17/2025 | 9 | 3 | 6 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/28/2025 | 4/25/2026 | Y | EXP | 365 | 07/24/2025 |  | 162 | 0 | 162 |  |  | 11/24/2025 | Connected |  | N
National Grid | TYNGSBORO | 625470 | 01879 | 6 |  |  | Solar |  | 05_14_78L1 | 07/17/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 312534 | 01810 | 7.6 |  |  | Solar |  | 05_01_226L2 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/06/2020 | 10/1/2021 | Y | EXP | 365 | 07/23/2021 | 07/26/2021 | 4 | 0 | 4 |  |  | 8/12/2021 | Connected |  | N
National Grid | METHUEN | 320744 | 01844 | 10 |  |  | Solar |  | 05_01_406L2 | 11/23/2020 | 01/07/2022 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/23/2020 | 10/10/2022 | Y | EXP | 365 | 01/18/2022 | 03/04/2022 | 46 | 0 | 46 |  |  | 3/30/2022 | Connected |  | Y
National Grid | DRACUT | 234351 | 01826 | 10 |  |  | Solar |  | 05_01_552L1 | 07/16/2019 | 07/25/2019 | 7 | 7 | 0 | 07/26/2019 | 07/26/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2020 | Connected |  | N
National Grid | PEPPERELL | 175980 | 01463 | 42 |  |  | Solar |  | 05_01_9J315 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2015 |  | 6/30/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 | 8/20/2015 | 8/20/2015 | 8/21/2015 | Connected |  | N
National Grid | AUBURN | 175850 | 01501 | 300 |  |  | Solar |  | 05_05_310W4 | 05/20/2015 | 05/20/2015 | 2 | 2 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 | 07/30/2015 | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 9/22/2015 |  | 12/31/2016 | N | EXP | 466 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 1/9/2017 | Connected |  | N
National Grid | SPENCER | 734653 | 01562 | 3.8 |  |  | Solar |  | 05_12_37W5 | 11/18/2025 | 11/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 660873 | 01604 | 5.76 |  |  | Solar |  | 05_14_21L1 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/16/2024 | 4/11/2026 | Y | EXP | 365 | 07/08/2025 |  | 178 | 0 | 178 |  |  |  | Completion Documents |  | Y
National Grid | MARLBOROUGH | 301678 | 01752 | 10 |  |  | Solar |  | 05_14_54L3 | 07/16/2020 | 07/21/2020 | 3 | 3 | 0 | 07/22/2020 | 07/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | MEDFORD | 682966 | 02155 | 0 |  |  | Solar |  | 05_14_63L2 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 635771 | 01879 | 5.76 |  |  | Solar |  | 05_14_78L1 | 08/27/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 9/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  | 1/24/2025 | Connected |  | Y
National Grid | ANDOVER | 321315 | 01845 | 8.41 |  |  | Solar |  | 05_01_226L2 | 10/23/2020 | 11/18/2020 | 16 | 15 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/18/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 359795 | 01844 | 9.6 |  |  | Solar |  | 05_01_406L2 | 05/21/2021 | 05/24/2021 | 0 | 0 | 0 | 05/25/2021 | 05/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | DRACUT | 256903 | 01826 | 10 |  |  | Solar |  | 05_01_552L1 | 10/09/2019 | 10/11/2019 | 1 | 1 | 0 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 02/05/2020 | 03/02/2020 | 26 | 0 | 26 |  |  | 4/22/2020 | Connected |  | N
National Grid | DUNSTABLE | 552028 | 01827 | 5.8 |  |  | Solar |  | 05_01_9J321 | 11/16/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 177333 | 01501 | 784 |  |  | Solar |  | 05_05_310W4 | 08/30/2016 | 08/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2016 | 09/28/2016 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 206779 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W5 | 02/11/2019 | 02/14/2019 | 3 | 3 | 0 | 02/15/2019 | 02/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/11/2019 | 5/28/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/14/2020 | Connected |  | N
National Grid | WORCESTER | 706895 | 01604 | 7.6 |  |  | Solar |  | 05_14_21L1 | 07/23/2025 | 10/15/2025 | 7 | 4 | 3 | 11/13/2025 | 11/13/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 320280 | 01752 | 8 |  |  | Solar |  | 05_14_54L3 | 10/20/2020 | 11/10/2020 | 14 | 13 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | MEDFORD | 699916 | 02155 | 16.72 |  |  | Solar |  | 05_14_63L2 | 06/23/2025 | 06/27/2025 | 4 | 0 | 4 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 06/23/2025 | 8/8/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 12/11/2025 | Connected |  | N
National Grid | TYNGSBORO | 643912 | 01879 | 7.6 |  |  | Solar |  | 05_14_78L1 | 10/02/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | ANDOVER | 334209 | 01810 | 17.6 |  |  | Solar |  | 05_01_226L2 | 01/29/2021 | 02/17/2021 | 12 | 12 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2021 | Connected |  | N
National Grid | METHUEN | 395838 | 01844 | 9.8 |  |  | Solar |  | 05_01_406L2 | 11/22/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/22/2021 | 6/7/2023 | Y | EXP | 365 | 04/23/2022 | 06/07/2022 | 46 | 0 | 46 |  |  | 6/9/2022 | Connected |  | N
National Grid | DRACUT | 265279 | 01826 | 0 |  |  | Other |  | 05_01_552L1 | 02/24/2020 | 03/17/2020 | 15 | 11 | 4 |  |  | 6 | 6 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 642954 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J321 | 09/27/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 177480 | 01501 | 952 |  |  | Solar |  | 05_05_310W4 | 07/07/2016 | 07/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2016 | 09/19/2016 | 50 | 29 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/13/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 235994 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W5 | 06/21/2019 | 06/28/2019 | 4 | 0 | 4 | 07/01/2019 | 07/01/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 6/21/2020 | Y | EXP | 365 | 03/06/2020 | 03/09/2020 | 3 | 0 | 3 |  |  | 5/1/2020 | Connected |  | N
National Grid | WORCESTER | 174509 | 01604 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 326749 | 01752 | 10 |  |  | Solar |  | 05_14_54L3 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2021 | Connected |  | N
National Grid | MEDFORD | 208615 | 02155 | 500 |  |  | Solar |  | 05_14_65L1 | 03/25/2019 | 04/23/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2019 | 03/17/2020 | 213 | 42 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 643820 | 01826 | 7.6 |  |  | Solar |  | 05_14_78L1 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/26/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 343268 | 01810 | 10 |  |  | Solar |  | 05_01_226L2 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | METHUEN | 402308 | 01844 | 9.8 |  |  | Solar |  | 05_01_406L2 | 01/24/2022 | 02/01/2022 | 6 | 0 | 6 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 | 01/24/2022 | 8/17/2023 | Y | EXP | 365 | 07/15/2022 | 08/16/2022 | 33 | 0 | 33 |  |  | 9/1/2022 | Connected |  | N
National Grid | DRACUT | 264202 | 01826 | 5000 |  |  | Other |  | 05_01_552L1 | 02/12/2020 | 03/16/2020 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2020 | 04/01/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 175684 | 01463 | 75.6 |  |  | Solar |  | 05_01_9J327 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 102 | 3 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/24/2014 | 5/31/2015 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 374486 | 01501 | 9.6 |  |  | Solar |  | 05_05_310W4 | 08/11/2021 | 08/18/2021 | 5 | 1 | 4 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 08/11/2021 | 12/22/2023 | Y | EXP | 365 | 04/07/2022 | 12/21/2022 | 259 | 0 | 259 |  |  | 1/26/2023 | Connected |  | N
National Grid | SPENCER | 456275 | 01562 | 10 |  |  | Solar |  | 05_12_37W5 | 09/16/2022 | 10/14/2022 | 19 | 19 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/13/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174508 | 01604 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 326283 | 01752 | 11.4 |  |  | Solar |  | 05_14_54L3 | 11/16/2020 | 11/18/2020 | 1 | 0 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 2/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | MEDFORD | 653568 | 02155 | 3.8 |  |  | Solar |  | 05_14_65L1 | 11/12/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 644842 | 01826 | 5.76 |  |  | Solar |  | 05_14_78L1 | 10/03/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 357623 | 01810 | 9.8 |  |  | Solar |  | 05_01_226L2 | 05/12/2021 | 05/13/2021 | 1 | 1 | 0 | 05/14/2021 | 05/14/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/12/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | METHUEN | 414703 | 01844 | 9.86 |  |  | Solar |  | 05_01_406L2 | 02/28/2022 | 03/11/2022 | 9 | 8 | 1 | 03/14/2022 | 03/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 | 02/28/2022 | 8/27/2023 | Y | EXP | 365 | 07/16/2022 | 08/26/2022 | 42 | 0 | 42 |  |  | 3/9/2023 | Connected |  | N
National Grid | DRACUT | 281057 | 01826 | 10 |  |  | Solar |  | 05_01_552L1 | 04/06/2020 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 714065 | 01463 | 10 |  |  | Solar |  | 05_01_9J337 | 08/22/2025 | 09/15/2025 | 8 | 2 | 6 | 10/22/2025 | 10/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 473967 | 01501 | 15.2 |  |  | Solar |  | 05_05_310W4 | 11/03/2022 | 11/08/2022 | 2 | 0 | 2 | 11/09/2022 | 11/09/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2022 |  | 1/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | N
National Grid | SPENCER | 463128 | 01562 | 15 |  |  | Solar |  | 05_12_37W5 | 10/05/2022 | 10/13/2022 | 5 | 3 | 2 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 1/8/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174507 | 01604 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 338222 | 01752 | 11.52 |  |  | Solar |  | 05_14_54L3 | 01/22/2021 | 01/28/2021 | 4 | 4 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | MEDFORD | 659339 | 02155 | 7.6 |  |  | Solar |  | 05_14_65L1 | 12/10/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 649061 | 01826 | 3.8 |  |  | Solar |  | 05_14_78L1 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 399819 | 01810 | 7.6 |  |  | Solar |  | 05_01_226L2 | 12/16/2021 | 12/20/2021 | 2 | 0 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 12/16/2021 | 6/8/2023 | Y | EXP | 365 | 05/11/2022 | 06/07/2022 | 28 | 0 | 28 |  |  | 6/16/2022 | Connected |  | N
National Grid | HAVERHILL | 473720 | 01830 | 5.76 |  |  | Solar |  | 05_01_406L2 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 12/08/2022 | 4/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2023 | Connected |  | N
National Grid | DRACUT | 288064 | 01826 | 0 |  |  | Other |  | 05_01_552L1 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 09/27/2020 | 24 | 20 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 719601 | 01463 | 11.5 |  |  | Solar |  | 05_01_9J337 | 09/23/2025 | 10/23/2025 | 20 | 17 | 3 | 10/24/2025 | 10/24/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 617968 | 01501 | 11.4 |  |  | Solar |  | 05_05_310W4 | 06/14/2024 | 07/03/2024 | 10 | 9 | 1 | 07/05/2024 | 07/05/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 499173 | 01562 | 15.2 |  |  | Solar |  | 05_12_37W5 | 03/15/2023 | 03/16/2023 | 1 | 0 | 1 | 03/17/2023 | 03/17/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/15/2023 | 9/1/2024 | Y | EXP | 365 | 07/28/2023 | 08/28/2023 | 32 | 0 | 32 |  |  | 9/20/2023 | Connected |  | N
National Grid | WORCESTER | 174506 | 01609 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 359718 | 01752 | 54.6 |  |  | Solar |  | 05_14_54L3 | 05/26/2021 | 06/08/2021 | 7 | 1 | 6 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | MEDFORD | 657492 | 02155 | 5.76 |  |  | Solar |  | 05_14_65L3 | 11/27/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DRACUT | 650608 | 01826 | 12.16 |  |  | Solar |  | 05_14_78L1 | 10/29/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 49 | 24 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 401910 | 01810 | 0 |  |  | Battery Add-On |  | 05_01_226L2 | 12/29/2021 | 01/04/2022 | 3 | 0 | 3 | 01/05/2022 | 01/05/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 564813 | 01830 | 7.6 |  |  | Solar |  | 05_01_406L2 | 10/24/2023 | 11/07/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 10/24/2023 | 2/2/2025 | Y | EXP | 365 | 05/02/2024 | 09/07/2024 | 129 | 0 | 129 |  |  | 10/8/2024 | Connected |  | N
National Grid | DRACUT | 330669 | 01826 | 9.8 |  |  | Solar |  | 05_01_552L1 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | PEPPERELL | 742840 | 01463 | 11.52 |  |  | Solar |  | 05_01_9J337 | 01/02/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | AUBURN | 649246 | 01501 | 11.4 |  |  | Solar |  | 05_05_310W4 | 10/26/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 506789 | 01562 | 5.04 |  |  | Solar |  | 05_12_37W5 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N
National Grid | WORCESTER | 174505 | 01604 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 405836 | 01752 | 0 |  |  | Battery Add-On |  | 05_14_54L3 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 727455 | 02155 | 5.76 |  |  | Solar |  | 05_14_65L3 | 10/17/2025 | 10/24/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 650662 | 01826 | 5.76 |  |  | Solar |  | 05_14_78L1 | 11/11/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/11/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ANDOVER | 426686 | 01845 | 0 |  |  | Solar |  | 05_01_226L2 | 04/27/2022 | 07/21/2022 | 58 | 49 | 9 | 07/22/2022 | 07/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | HAVERHILL | 590501 | 01830 | 5.8 |  |  | Solar |  | 05_01_406L2 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/13/2026 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 346050 | 01826 | 11.4 |  |  | Solar |  | 05_01_552L1 | 03/10/2021 | 03/16/2021 | 3 | 0 | 3 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 7/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2021 | Connected |  | N
National Grid | PEPPERELL | 175283 | 01463 | 42.57 |  |  | Solar |  | 05_01_9J337 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/4/2015 | Connected |  | N
National Grid | AUBURN | 343005 | 01501 | 208.2 |  |  | Solar |  | 05_05_310W5 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 |  |  | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 | 02/19/2021 | 11/26/2026 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SPENCER | 522539 | 01562 | 15.2 |  |  | Solar |  | 05_12_37W5 | 04/28/2023 | 06/07/2023 | 27 | 26 | 1 | 06/08/2023 | 06/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2023 | Connected |  | N
National Grid | WORCESTER | 174504 | 01604 | 33.3 |  |  | Solar |  | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | MARLBOROUGH | 464540 | 01752 | 23.32 |  |  | Solar |  | 05_14_54L3 | 09/29/2022 | 10/04/2022 | 3 | 0 | 3 | 10/05/2022 | 10/05/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2023 | Connected |  | N
National Grid | MEDFORD | 176146 | 02155 | 1700 |  |  | Solar |  | 05_14_65L3 | 08/24/2015 | 08/24/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/29/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/27/2016 |  | 457 | 21 | 436 | 5/12/2016 |  | 8/12/2016 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 651579 | 01826 | 3.8 |  |  | Solar |  | 05_14_78L1 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/12/2024 | 4/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | ANDOVER | 433783 | 01810 | 15.2 |  |  | Solar |  | 05_01_226L2 | 06/08/2022 | 06/09/2022 | 1 | 0 | 1 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | HAVERHILL | 614107 | 01835 | 7.6 |  |  | Solar |  | 05_01_406L2 | 05/30/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | DRACUT | 452168 | 01826 | 5 |  |  | Solar |  | 05_01_552L1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 236472 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J337 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 12/30/2019 | N | EXP | 46 |  |  | 0 | 0 | 0 |  |  | 12/10/2019 | Connected |  | N
National Grid | AUBURN | 342944 | 01501 | 191.6 |  |  | Solar |  | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 | 02/18/2021 | 9/19/2026 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SPENCER | 563912 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W5 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 11/07/2023 | 1/8/2025 | Y | EXP | 365 | 05/10/2024 | 05/14/2024 | 5 | 0 | 5 |  |  | 5/31/2024 | Connected |  | N
National Grid | WORCESTER | 176937 | 01604 | 6 |  |  | Solar |  | 05_14_21L1 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/6/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 6/10/2016 | Connected |  | N
National Grid | MARLBOROUGH | 485876 | 01752 | 0 |  |  | Solar |  | 05_14_54L3 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/15/2022 | 4/26/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 1/17/2024 | Connected |  | N
National Grid | MEDFORD | 270545 | 02155 | 0 |  |  | Solar |  | 05_14_65L3 | 12/20/2019 | 12/30/2019 | 4 | 0 | 4 | 12/31/2019 | 12/31/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 | 03/10/2020 | 04/02/2020 | 23 | 0 | 23 |  |  | 9/14/2020 | Connected |  | N
National Grid | DRACUT | 652420 | 01826 | 3.8 |  |  | Solar |  | 05_14_78L1 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ANDOVER | 435399 | 01810 | 10 |  |  | Solar |  | 05_01_226L2 | 06/23/2022 | 07/21/2022 | 20 | 16 | 4 | 07/22/2022 | 07/22/2022 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2023 | Connected |  | N
National Grid | HAVERHILL | 621138 | 01835 | 3.8 |  |  | Solar |  | 05_01_406L2 | 06/27/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | DRACUT | 367879 | 01826 | 7.6 |  |  | Solar |  | 05_01_552L1 | 07/22/2021 | 07/29/2021 | 6 | 5 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2021 | Connected |  | N
National Grid | PEPPERELL | 279312 | 01463 | 7.6 |  |  | Solar |  | 05_01_9J337 | 04/20/2020 | 04/27/2020 | 4 | 4 | 0 | 04/28/2020 | 04/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | AUBURN | 650007 | 01501 | 0 |  |  | Other |  | 05_05_310W5 | 05/02/2025 | 07/11/2025 | 47 | 42 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SPENCER | 575277 | 01562 | 25 |  |  | Solar |  | 05_12_37W5 | 01/08/2024 | 01/22/2024 | 9 | 6 | 3 | 01/23/2024 | 01/23/2024 | 105 | 88 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | WORCESTER | 178450 | 01604 | 3.8 |  |  | Solar |  | 05_14_21L1 | 11/29/2017 | 11/29/2017 | 39 | 36 | 3 | 01/29/2018 | 01/29/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/31/2020 | N | EXP | 422 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 492260 | 01752 | 14.79 |  |  | Solar |  | 05_14_54L3 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 |  |  | 222 | 204 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 330625 | 02155 | 15.2 |  |  | Solar |  | 05_14_65L3 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 653219 | 01826 | 6.08 |  |  | Solar |  | 05_14_78L1 | 11/08/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/08/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | ANDOVER | 440673 | 01810 | 9.28 |  |  | Solar |  | 05_01_226L2 | 06/30/2022 | 07/01/2022 | 1 | 0 | 1 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 668558 | 01830 | 7.6 |  |  | Solar |  | 05_01_406L2 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/14/2026 | Y | EXP | 365 | 07/08/2025 |  | 178 | 0 | 178 |  |  | 12/24/2025 | Connected |  | N
National Grid | DRACUT | 405685 | 01826 | 9.8 |  |  | Solar |  | 05_01_552L1 | 02/03/2022 | 02/07/2022 | 2 | 0 | 2 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 | 02/03/2022 | 5/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | PEPPERELL | 601301 | 01463 | 3.8 |  |  | Solar |  | 05_01_9J337 | 04/10/2024 | 04/30/2024 | 14 | 13 | 1 | 05/01/2024 | 05/01/2024 | 30 | 25 | 5 | 07/24/2024 | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 685105 | 01501 | 9.6 |  |  | Solar |  | 05_05_310W5 | 04/24/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 |  | 7/16/2026 | N | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 581300 | 01562 | 0 |  |  | Battery Add-On |  | 05_12_37W5 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2024 | Connected |  | N
National Grid | WORCESTER | 178635 | 01604 | 0 |  |  | Solar |  | 05_14_21L1 | 04/09/2018 | 04/09/2018 | 6 | 0 | 6 | 04/18/2018 | 04/18/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | Connected |  | N
National Grid | MARLBOROUGH | 495148 | 01752 | 15.2 |  |  | Solar |  | 05_14_54L3 | 05/11/2023 | 05/15/2023 | 2 | 0 | 2 | 05/16/2023 | 05/16/2023 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 487600 | 02155 | 7.54 |  |  | Solar |  | 05_14_65L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 184 | 162 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 655515 | 01826 | 5.76 |  |  | Solar |  | 05_14_78L1 | 11/19/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ANDOVER | 473320 | 01810 | 3.48 |  |  | Solar |  | 05_01_226L2 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/18/2022 | 4/19/2024 | Y | EXP | 365 | 04/12/2023 | 04/19/2023 | 8 | 0 | 8 |  |  | 6/23/2023 | Connected |  | N
National Grid | HAVERHILL | 678760 | 01835 | 7.6 |  |  | Solar |  | 05_01_406L2 | 03/18/2025 | 05/02/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 | 03/18/2025 | 7/30/2026 | Y | EXP | 365 | 10/30/2025 |  | 64 | 0 | 64 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 412613 | 01826 | 10 |  |  | Solar |  | 05_01_552L1 | 03/16/2022 | 03/24/2022 | 6 | 1 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/16/2022 | 6/15/2023 | Y | EXP | 365 | 05/17/2022 | 06/14/2022 | 29 | 0 | 29 |  |  | 8/11/2022 | Connected |  | N
National Grid | PEPPERELL | 652266 | 01463 | 4.225 |  |  | Solar |  | 05_01_9J337 | 11/05/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 83 | 63 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 720992 | 01501 | 75 |  |  | Solar |  | 05_05_310W5 | 09/22/2025 |  | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SPENCER | 635886 | 01562 | 7.6 |  |  | Solar |  | 05_12_37W5 | 08/29/2024 | 09/16/2024 | 7 | 4 | 3 | 09/17/2024 | 09/17/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 193380 | 01604 | 7.6 |  |  | Solar |  | 05_14_21L1 | 10/18/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 10/18/2018 | 7/15/2021 | Y | EXP | 365 | 11/14/2020 | 12/10/2020 | 26 | 0 | 26 |  |  | 12/29/2020 | Connected |  | N
National Grid | MARLBOROUGH | 502282 | 01752 | 15.2 |  |  | Solar |  | 05_14_54L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2024 | Connected |  | N
National Grid | MEDFORD | 586417 | 02155 | 0 |  |  | Battery Add-On |  | 05_14_65L3 | 01/30/2024 | 02/15/2024 | 12 | 9 | 3 | 02/16/2024 | 02/16/2024 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | DRACUT | 657540 | 01826 | 10 |  |  | Solar |  | 05_14_78L1 | 11/28/2024 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 478031 | 01810 | 4.64 |  |  | Solar |  | 05_01_226L2 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2023 | Connected |  | N
National Grid | HAVERHILL | 706259 | 01835 | 15.2 |  |  | Solar |  | 05_01_406L2 | 07/22/2025 | 07/25/2025 | 3 | 0 | 3 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | DRACUT | 431528 | 01826 | 15.66 |  |  | Solar |  | 05_01_552L1 | 06/29/2022 | 08/01/2022 | 23 | 22 | 1 | 08/02/2022 | 08/02/2022 | 42 | 21 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | PEPPERELL | 653577 | 01463 | 15.2 |  |  | Solar |  | 05_01_9J337 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | AUBURN | 174443 | 01501 | 30 |  |  | Solar |  | 05_05_310W5 | 07/06/2012 | 07/06/2012 | 8 | 0 | 8 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | -12 |  |  | 0 | 0 | 0 | 10/4/2012 | 10/4/2012 | 1/9/2013 | Connected |  | N
National Grid | SPENCER | 651935 | 01562 | 5.32 |  |  | Solar |  | 05_12_37W5 | 11/04/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 11/04/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | WORCESTER | 285172 | 01604 | 5 |  |  | Solar |  | 05_14_21L1 | 04/01/2020 | 05/28/2020 | 5 | 4 | 1 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 04/01/2020 | 5/28/2021 | Y | EXP | 365 | 10/24/2020 | 11/19/2020 | 26 | 0 | 26 |  |  | 11/20/2020 | Connected |  | N
National Grid | MARLBOROUGH | 518526 | 01752 | 8.99 |  |  | Solar |  | 05_14_54L3 | 04/11/2023 | 04/12/2023 | 2 | 1 | 1 | 04/13/2023 | 04/13/2023 | 34 | 12 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2023 | Connected |  | N
National Grid | MEDFORD | 655978 | 02155 | 3.8 |  |  | Solar |  | 05_14_65L3 | 11/21/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | DRACUT | 662302 | 01826 | 5.76 |  |  | Solar |  | 05_14_78L1 | 12/23/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/23/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | ANDOVER | 488269 | 01810 | 20.591 |  |  | Solar |  | 05_01_226L2 | 12/27/2022 |  | 42 | 41 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 574156 | 01835 | 480 |  |  | Solar |  | 05_01_406L3 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2024 | 02/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 445609 | 01826 | 24 |  |  | Solar |  | 05_01_552L1 | 07/20/2022 | 07/21/2022 | 29 | 20 | 9 | 12/01/2022 | 12/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2023 | Connected |  | N
National Grid | PEPPERELL | 695515 | 01463 | 6.98 |  |  | Solar |  | 05_01_9J337 | 06/02/2025 | 06/20/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 79 | 71 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | AUBURN | 175274 | 01501 | 42.57 |  |  | Solar |  | 05_05_310W5 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 4/30/2015 | Connected |  | N
National Grid | SPENCER | 653334 | 01562 | 3.8 |  |  | Solar |  | 05_12_37W5 | 11/08/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | WORCESTER | 368249 | 01604 | 7.6 |  |  | Solar |  | 05_14_21L1 | 07/07/2021 | 07/29/2021 | 17 | 16 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 9/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | MARLBOROUGH | 543279 | 01752 | 14.79 |  |  | Solar |  | 05_14_54L3 | 07/24/2023 | 07/26/2023 | 2 | 0 | 2 | 07/27/2023 | 07/27/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 | 07/24/2023 | 11/29/2024 | Y | EXP | 365 | 12/04/2023 | 01/16/2024 | 44 | 3 | 41 |  |  | 1/19/2024 | Connected |  | N
National Grid | MEDFORD | 671344 | 02155 | 5.76 |  |  | Solar |  | 05_14_65L3 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | DRACUT | 711464 | 01826 | 7.6 |  |  | Solar |  | 05_14_78L1 | 08/12/2025 | 09/08/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 498726 | 01845 | 12.47 |  |  | Solar |  | 05_01_226L2 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | Y
National Grid | HAVERHILL | 693199 | 01835 | 499 |  |  | Other |  | 05_01_406L3 | 09/03/2025 | 10/17/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 | 11/04/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 731961 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J352 | 11/06/2025 | 11/19/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 175639 | 01463 | 16 |  |  | Solar |  | 05_05_310W5 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2014 |  | 2/6/2015 | N | EXP | 92 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/16/2016 | Connected |  | N
National Grid | AUBURN | 174623 | 01501 | 200 |  |  | Solar |  | 05_12_37W6 | 04/14/2011 | 04/14/2011 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 6/29/2012 | N | EXP | 214 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 6/29/2012 | Connected |  | N
National Grid | SPENCER | 372068 | 01562 | 15.2 |  |  | Solar |  | 05_14_21L1 | 07/26/2021 | 07/28/2021 | 3 | 2 | 1 | 07/29/2021 | 07/29/2021 | 64 | 43 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 07/26/2021 | 9/5/2023 | Y | EXP | 365 | 01/18/2022 | 09/02/2022 | 227 | 0 | 227 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 569398 | 01604 | 7.6 |  |  | Solar |  | 05_14_54L3 | 11/07/2023 | 02/13/2024 | 65 | 63 | 2 | 02/14/2024 | 02/14/2024 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | MARLBOROUGH | 673956 | 01752 | 5.76 |  |  | Solar |  | 05_14_65L3 | 02/24/2025 | 03/04/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 02/24/2025 | 4/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | MEDFORD | 714136 | 02155 | 7.6 |  |  | Solar |  | 05_14_78L3 | 08/22/2025 | 10/02/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 55 | 40 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 559025 | 01826 | 9.57 |  |  | Solar |  | 05_01_226L2 | 09/29/2023 | 10/12/2023 | 9 | 8 | 1 | 10/13/2023 | 10/13/2023 | 75 | 52 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | ANDOVER | 734311 | 01810 | 7.6 |  |  | Solar |  | 05_01_406L3 | 11/20/2025 | 11/26/2025 | 5 | 2 | 3 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 448029 | 01835 | 10 |  |  | Solar |  | 05_01_552L1 | 08/10/2022 | 08/15/2022 | 4 | 3 | 1 | 08/16/2022 | 08/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 10/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2022 | Connected |  | N
National Grid | DRACUT | 611572 | 01826 | 6 |  |  | Solar |  | 05_01_9J352 | 05/17/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | PEPPERELL | 175964 | 01463 | 9.25 |  |  | Solar |  | 05_05_310W5 | 06/05/2015 | 06/05/2015 | 1 | 1 | 0 | 06/09/2015 | 06/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 6/30/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/2/2015 | 7/2/2015 | 8/12/2015 | Connected |  | N
National Grid | CHARLTON | 175081 | 01507 | 30 |  |  | Solar |  | 05_12_37W6 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2013 |  | 12/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 12/23/2013 | 12/23/2013 | 12/27/2013 | Connected |  | N
National Grid | SPENCER | 403830 | 01562 | 50 |  |  | Solar |  | 05_14_21L1 | 01/11/2022 | 02/02/2022 | 16 | 10 | 6 | 02/03/2022 | 02/03/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 | 01/11/2022 | 10/9/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | WORCESTER | 576984 | 01604 | 0 |  |  | Solar |  | 05_14_54L3 | 12/11/2023 | 12/13/2023 | 2 | 0 | 2 | 12/14/2023 | 12/14/2023 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 691483 | 01752 | 17.11 |  |  | Solar |  | 05_14_65L3 | 05/13/2025 | 05/16/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/13/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | MEDFORD | 723417 | 02155 | 6.282 |  |  | Solar |  | 05_14_78L3 | 10/02/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TYNGSBORO | 559004 | 01879 | 30 |  |  | Solar |  | 05_01_226L2 | 09/29/2023 | 10/06/2023 | 5 | 4 | 1 | 10/10/2023 | 10/10/2023 | 117 | 92 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 09/29/2023 | 4/9/2025 | Y | EXP | 365 | 08/21/2024 | 10/17/2024 | 58 | 0 | 58 |  |  | 10/23/2024 | Connected |  | N
National Grid | ANDOVER | 174421 | 01810 | 950 |  |  | Solar |  | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | -135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | HAVERHILL | 460324 | 01835 | 15.66 |  |  | Solar |  | 05_01_552L1 | 10/04/2022 | 10/31/2022 | 19 | 17 | 2 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2023 | Connected |  | N
National Grid | DRACUT | 636156 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J352 | 09/03/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | PEPPERELL | 176107 | 01463 | 250 |  |  | Natural Gas |  | 05_05_310W5 | 06/25/2015 | 06/25/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 6/30/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/18/2015 | Connected |  | N
National Grid | OXFORD | 177276 | 01540 | 5.2 |  |  | Solar |  | 05_12_37W6 | 02/06/2017 | 02/06/2017 | 4 | 4 | 0 | 02/13/2017 | 02/13/2017 | 194 | 0 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2017 |  | 2/12/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 414979 | 01562 | 15.2 |  |  | Solar |  | 05_14_21L1 | 03/02/2022 | 03/23/2022 | 16 | 15 | 1 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 606384 | 01604 |  |  |  | Battery Add-On |  | 05_14_54L3 | 04/24/2024 | 04/29/2024 | 3 | 0 | 3 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | MARLBOROUGH | 715617 | 01752 | 17.6 |  |  | Solar |  | 05_14_65L3 | 09/08/2025 | 09/10/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 56 | 43 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 189632 | 02149 | 11.4 |  |  | Solar |  | 05_14_78L3 | 07/10/2019 | 06/29/2018 | 134 | 126 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 550348 | 01879 | 0 |  |  | Solar |  | 05_01_226L2 | 08/24/2023 | 08/25/2023 | 1 | 0 | 1 | 08/28/2023 | 08/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 | 08/24/2023 | 11/10/2024 | Y | EXP | 365 | 06/04/2024 | 06/03/2024 | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | ANDOVER | 174420 | 01810 | 950 |  |  | Solar |  | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | -135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | HAVERHILL | 546629 | 01835 | 4.64 |  |  | Solar |  | 05_01_552L1 | 08/09/2023 | 08/22/2023 | 9 | 9 | 0 | 08/23/2023 | 08/23/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/09/2023 | 10/10/2024 | Y | EXP | 365 | 10/28/2023 | 01/29/2024 | 94 | 3 | 91 |  |  | 2/1/2024 | Connected |  | N
National Grid | DRACUT | 645610 | 01826 | 3.8 |  |  | Solar |  | 05_01_9J352 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | PEPPERELL | 176261 | 01463 | 6 |  |  | Solar |  | 05_05_310W5 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 2/12/2016 | Connected |  | N
National Grid | OXFORD | 178386 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W6 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/21/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | SPENCER | 490227 | 01562 | 7.6 |  |  | Solar |  | 05_14_21L1 | 01/06/2023 | 01/09/2023 | 1 | 0 | 1 | 01/10/2023 | 01/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 619582 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_54L3 | 06/21/2024 | 06/25/2024 | 2 | 0 | 2 | 06/26/2024 | 06/26/2024 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 174723 | 01772 | 35 |  |  | Solar |  | 05_14_66L1 | 07/29/2010 | 07/29/2010 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 | 3/13/2017 | 3/13/2017 |  | Withdrawn |  | Y
National Grid | EVERETT | 194002 | 02149 | 15.2 |  |  | Solar |  | 05_14_78L3 | 08/20/2018 | 09/04/2018 | 20 | 10 | 10 | 10/11/2018 | 10/11/2018 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 570251 | 01826 | 6 |  |  | Solar |  | 05_01_226L2 | 12/18/2023 | 01/02/2024 | 9 | 3 | 6 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 12/18/2023 | 7/31/2025 | Y | EXP | 535 | 05/24/2024 | 08/28/2024 | 97 | 0 | 97 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 174918 | 01810 | 13.12 |  |  | Solar |  | 05_01_406L3 | 02/26/2013 | 02/26/2013 | 7 | 2 | 5 | 03/13/2013 | 03/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 |  | 5/31/2013 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/4/2013 | 9/4/2013 | 11/20/2013 | Connected |  | N
National Grid | HAVERHILL | 562432 | 01835 | 9.074 |  |  | Solar |  | 05_01_552L1 | 10/16/2023 | 10/19/2023 | 4 | 2 | 2 | 10/20/2023 | 10/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/16/2023 | 11/19/2024 | Y | EXP | 365 | 12/14/2023 | 02/07/2024 | 56 | 3 | 53 |  |  | 2/8/2024 | Connected |  | N
National Grid | DRACUT | 660942 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J352 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | Y
National Grid | PEPPERELL | 185773 | 01463 | 7000 |  |  | Solar |  | 05_05_310W5 | 09/07/2018 |  | 62 | 32 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 329274 | 01507 | 5 |  |  | Solar |  | 05_12_37W6 | 01/08/2021 | 01/12/2021 | 1 | 0 | 1 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/08/2021 | 8/3/2022 | Y | EXP | 365 | 06/02/2021 | 12/09/2021 | 191 | 7 | 184 |  |  | 12/22/2021 | Connected |  | N
National Grid | SPENCER | 626584 | 01562 | 3.8 |  |  | Solar |  | 05_14_21L1 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/22/2024 | 8/29/2025 | Y | EXP | 365 | 09/19/2024 | 10/11/2024 | 23 | 0 | 23 |  |  | 11/22/2024 | Connected |  | N
National Grid | WORCESTER | 624612 | 01604 | 22.8 |  |  | Solar |  | 05_14_54L3 | 07/15/2024 | 07/17/2024 | 2 | 0 | 2 | 07/18/2024 | 07/18/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 178684 | 01752 | 20 |  |  | Solar |  | 05_14_66L1 | 12/18/2017 | 12/18/2017 | 17 | 17 | 0 | 02/01/2018 | 02/01/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2018 |  | 12/24/2018 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  | 5/1/2018 | Connected |  | N
National Grid | EVERETT | 194659 | 02149 | 7.6 |  |  | Solar |  | 05_14_78L3 | 08/28/2018 | 09/13/2018 | 8 | 0 | 8 | 09/14/2018 | 09/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 599998 | 01826 | 3.8 |  |  | Solar |  | 05_01_226L2 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 04/01/2024 | 5/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | ANDOVER | 175066 | 01810 | 1500 |  |  | Solar |  | 05_01_406L3 | 03/28/2013 | 03/28/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2013 | 06/24/2013 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2014 | 03/28/2013 | 5/11/2018 | Y | STD | 1572 |  |  | 0 | 0 | 0 | 4/16/2018 | 4/16/2018 | 5/10/2018 | Connected |  | N
National Grid | HAVERHILL | 568209 | 01835 | 13.05 |  |  | Solar |  | 05_01_552L1 | 11/06/2023 | 11/13/2023 | 4 | 2 | 2 | 11/14/2023 | 11/14/2023 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | DRACUT | 671945 | 01826 | 3.8 |  |  | Solar |  | 05_01_9J352 | 02/20/2025 | 03/26/2025 | 8 | 4 | 4 | 03/27/2025 | 03/27/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 225197 | 01463 | 10 |  |  | Solar |  | 05_05_310W5 | 10/28/2019 |  | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 454546 | 01507 | 15.744 |  |  | Solar |  | 05_12_37W6 | 08/26/2022 | 09/23/2022 | 20 | 19 | 1 | 09/26/2022 | 09/26/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | SPENCER | 626563 | 01562 | 0 |  |  | Battery Add-On |  | 05_14_21L1 | 07/23/2024 | 08/14/2024 | 6 | 0 | 6 | 08/15/2024 | 08/15/2024 | 33 | 21 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WORCESTER | 645228 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_54L3 | 10/05/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 58 | 40 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | MARLBOROUGH | 688941 | 01752 | 12.92 |  |  | Solar |  | 05_14_66L1 | 05/08/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | EVERETT | 264017 | 02149 | 0 |  |  | Solar |  | 05_14_78L3 | 11/05/2019 | 11/08/2019 | 2 | 0 | 2 | 11/12/2019 | 11/12/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 11/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2020 | Connected |  | N
National Grid | DRACUT | 615849 | 01826 | 3.8 |  |  | Solar |  | 05_01_226L2 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 | 06/05/2024 | 1/21/2026 | Y | EXP | 365 | 03/06/2025 |  | 302 | 0 | 302 |  |  | 3/18/2025 | Connected |  | N
National Grid | ANDOVER | 175246 | 01810 | 800 |  |  | Solar |  | 05_01_406L3 | 11/04/2014 | 11/04/2014 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 571014 | 01913 | 10 |  |  | Solar |  | 05_01_552L1 | 12/21/2023 | 11/27/2023 | 5 | 0 | 5 | 01/02/2024 | 01/02/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/21/2023 | 5/3/2025 | Y | EXP | 365 | 06/11/2024 | 08/15/2024 | 66 | 0 | 66 |  |  | 9/24/2024 | Connected |  | N
National Grid | DRACUT | 722531 | 01826 | 15.36 |  |  | Solar |  | 05_01_9J352 | 09/29/2025 | 10/27/2025 | 19 | 17 | 2 | 10/28/2025 | 10/28/2025 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | PEPPERELL | 233162 | 01463 | 133.2 |  |  | Solar |  | 05_05_310W5 | 03/23/2020 | 03/31/2020 | 3 | 0 | 3 | 04/01/2020 | 04/01/2020 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 5/18/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N
National Grid | OXFORD | 566763 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W6 | 11/02/2023 | 11/08/2023 | 4 | 2 | 2 | 11/09/2023 | 11/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 640655 | 01562 | 7.475 |  |  | Solar |  | 05_14_21L1 | 09/17/2024 | 10/03/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/17/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | WORCESTER | 657336 | 01604 | 10 |  |  | Solar |  | 05_14_54L3 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 04/24/2025 | 04/23/2025 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | MARLBOROUGH | 722850 | 01752 | 16.403 |  |  | Solar |  | 05_14_66L2 | 10/03/2025 | 10/13/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EVERETT | 299147 | 02149 | 10 |  |  | Solar |  | 05_14_78L3 | 07/13/2020 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 619525 | 01826 | 7.6 |  |  | Solar |  | 05_01_226L2 | 06/20/2024 | 06/25/2024 | 3 | 1 | 2 | 10/29/2024 | 10/29/2024 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175505 | 01810 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 588485 | 01913 | 7.6 |  |  | Solar |  | 05_01_552L1 | 02/12/2024 | 02/15/2024 | 4 | 2 | 2 | 02/16/2024 | 02/16/2024 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | DRACUT | 721533 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J360 | 09/24/2025 | 10/08/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 250657 | 01463 | 7.6 |  |  | Solar |  | 05_05_310W5 | 08/26/2019 | 11/01/2019 | 0 | 0 | 0 | 11/04/2019 | 11/04/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 591336 | 01540 | 10 |  |  | Solar |  | 05_12_37W6 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/27/2024 | 11/30/2025 | Y | EXP | 365 | 09/19/2024 | 10/02/2025 | 379 | 0 | 379 |  |  | 11/7/2025 | Connected |  | N
National Grid | SPENCER | 647295 | 01562 | 5.76 |  |  | Solar |  | 05_14_21L1 | 10/22/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | WORCESTER | 657602 | 01604 | 10 |  |  | Solar |  | 05_14_54L3 | 11/29/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/29/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | MARLBOROUGH | 193104 | 01752 | 455 |  |  | Solar |  | 05_14_66L2 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 |  |  | 101 | 22 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 381009 | 02149 | 7.6 |  |  | Solar |  | 05_14_78L3 | 10/08/2021 | 01/10/2022 | 0 | 0 | 0 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N
National Grid | TYNGSBORO | 629731 | 01879 | 10 |  |  | Solar |  | 05_01_226L2 | 08/02/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/02/2024 | 9/11/2025 | Y | EXP | 365 | 10/24/2024 | 11/08/2024 | 16 | 0 | 16 |  |  | 12/21/2024 | Connected |  | N
National Grid | ANDOVER | 175504 | 01810 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 603808 | 01913 | 10 |  |  | Solar |  | 05_01_552L1 | 04/16/2024 | 05/02/2024 | 5 | 0 | 5 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/16/2024 | 7/22/2025 | Y | EXP | 365 | 08/08/2024 | 09/12/2024 | 36 | 0 | 36 |  |  | 11/22/2024 | Connected |  | N
National Grid | DRACUT | 723299 | 01826 | 15.2 |  |  | Solar |  | 05_01_9J360 | 10/01/2025 | 10/09/2025 | 5 | 0 | 5 | 10/10/2025 | 10/10/2025 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 10/01/2025 | 11/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 295368 | 01463 | 8.7 |  |  | Solar |  | 05_05_310W5 | 06/08/2020 | 06/12/2020 | 3 | 2 | 1 | 06/15/2020 | 06/15/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2020 | Connected |  | N
National Grid | OXFORD | 596442 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W6 | 03/21/2024 | 03/27/2024 | 4 | 0 | 4 | 03/28/2024 | 03/28/2024 | 101 | 96 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 654926 | 01562 | 3.8 |  |  | Solar |  | 05_14_21L1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | WORCESTER | 666604 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_54L3 | 01/17/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | MARLBOROUGH | 520212 | 01752 | 15.08 |  |  | Solar |  | 05_14_6J1 | 04/19/2023 | 04/20/2023 | 1 | 0 | 1 | 04/21/2023 | 04/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 |  | 7/16/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 405981 | 02149 | 0 |  |  | Battery Add-On |  | 05_14_78L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 644163 | 01826 | 5.76 |  |  | Solar |  | 05_01_226L2 | 10/01/2024 | 10/28/2024 | 4 | 1 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/11/2025 | 27 | 0 | 27 |  |  | 2/19/2025 | Connected |  | N
National Grid | ANDOVER | 175510 | 01810 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 613530 | 01913 | 36 |  |  | Solar |  | 05_01_552L1 | 08/18/2024 | 10/28/2024 | 49 | 41 | 8 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | DRACUT | 177344 | 01826 | 15.2 |  |  | Solar |  | 05_01_9J360 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 1/26/2018 | N | EXP | 422 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | PEPPERELL | 295196 | 01463 | 0 |  |  | Battery Add-On |  | 05_05_310W5 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N
National Grid | CHARLTON | 633047 | 01507 | 3.8 |  |  | Solar |  | 05_12_37W6 | 08/15/2024 | 08/30/2024 | 3 | 0 | 3 | 09/03/2024 | 09/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 657560 | 01562 | 5.76 |  |  | Solar |  | 05_14_21L1 | 11/28/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/28/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WORCESTER | 674675 | 01604 | 10 |  |  | Solar |  | 05_14_54L3 | 03/03/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | MARLBOROUGH | 552102 | 01752 | 150 |  |  | Solar |  | 05_14_6J1 | 09/01/2023 | 09/24/2023 | 15 | 6 | 9 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 417105 | 02149 | 362.5 |  |  | Solar |  | 05_14_78L3 | 03/25/2022 | 06/15/2022 | 56 | 47 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2022 | 07/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 648356 | 01879 | 3.8 |  |  | Solar |  | 05_01_226L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | ANDOVER | 175509 | 01810 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 619978 | 01913 | 5.76 |  |  | Solar |  | 05_01_552L1 | 06/24/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/24/2024 | 9/12/2025 | Y | EXP | 365 | 11/15/2024 | 01/16/2025 | 63 | 0 | 63 |  |  | 1/24/2025 | Connected |  | N
National Grid | DRACUT | 197281 | 01826 | 10 |  |  | Solar |  | 05_01_9J360 | 10/01/2018 | 10/22/2018 | 3 | 3 | 0 | 10/23/2018 | 10/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 10/01/2018 | 6/4/2019 | Y | EXP | 224 | 03/21/2019 | 03/20/2019 | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | PEPPERELL | 312249 | 01463 | 15.2 |  |  | Solar |  | 05_05_310W5 | 09/11/2020 | 09/14/2020 | 0 | 0 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 10/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 635118 | 01507 | 4.35 |  |  | Solar |  | 05_12_37W6 | 08/26/2024 | 10/14/2024 | 5 | 0 | 5 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 668768 | 01562 | 10 |  |  | Solar |  | 05_14_21L1 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/04/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | WORCESTER | 696418 | 01604 | 0 |  |  | Battery Add-On |  | 05_14_54L3 | 06/05/2025 | 06/20/2025 | 10 | 6 | 4 | 06/23/2025 | 06/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 635232 | 01772 | 7.6 |  |  | Solar |  | 05_14_6J1 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 9/30/2025 | Y | EXP | 365 | 06/18/2025 | 06/17/2025 | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | EVERETT | 483029 | 02149 | 0 |  |  | Other |  | 05_14_78L3 | 01/12/2023 | 02/15/2023 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2023 | 03/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 650386 | 01826 | 8.45 |  |  | Solar |  | 05_01_226L2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/29/2024 | 1/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ANDOVER | 175540 | 01845 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 621844 | 01841 | 7.6 |  |  | Solar |  | 05_01_552L1 | 07/01/2024 |  | 86 | 40 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 232897 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 06/19/2019 | 07/08/2019 | 12 | 12 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/19/2019 | 7/20/2020 | Y | EXP | 365 | 04/09/2020 | 05/15/2020 | 34 | 0 | 34 |  |  | 5/18/2020 | Connected |  | N
National Grid | PEPPERELL | 333500 | 01463 | 52.2 |  |  | Solar |  | 05_05_310W5 | 03/01/2021 | 12/07/2021 | 9 | 0 | 9 | 03/16/2021 | 03/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 10/9/2023 | N | EXP | 750 | 08/19/2021 | 09/15/2021 | 26 | 3 | 23 |  |  | 8/24/2023 | Connected |  | N
National Grid | OXFORD | 637627 | 01540 | 10 |  |  | Solar |  | 05_12_37W6 | 09/04/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/04/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | SPENCER | 670942 | 01562 | 11.52 |  |  | Solar |  | 05_14_21L1 | 02/07/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/07/2025 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | WORCESTER | 706271 | 01604 | 3.8 |  |  | Solar |  | 05_14_54L3 | 07/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 653900 | 01772 | 5.76 |  |  | Solar |  | 05_14_6J1 | 11/29/2024 | 12/31/2024 | 9 | 5 | 4 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 491978 | 02149 | 7.6 |  |  | Solar |  | 05_14_78L3 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 03/03/2023 | 6/29/2024 | Y | EXP | 365 | 06/13/2023 | 06/30/2023 | 18 | 0 | 18 |  |  | 7/13/2023 | Connected |  | N
National Grid | DRACUT | 651609 | 01826 | 10 |  |  | Solar |  | 05_01_226L2 | 11/13/2024 | 12/13/2024 | 2 | 0 | 2 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/13/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ANDOVER | 175653 | 01810 | 684 |  |  | Solar |  | 05_01_406L3 | 05/05/2014 | 05/05/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 09/04/2014 | 76 | 20 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2015 | 05/05/2014 | 12/30/2015 | Y | STD | 285 | 10/22/2015 | 12/22/2015 | 41 | 0 | 41 | 12/11/2015 | 12/11/2015 | 12/30/2015 | Connected |  | N
National Grid | LAWRENCE | 635360 | 01841 | 0 |  |  | Solar |  | 05_01_552L1 | 08/26/2024 | 08/28/2024 | 2 | 0 | 2 | 08/29/2024 | 08/29/2024 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 11/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2024 | Connected |  | N
National Grid | DRACUT | 241416 | 01826 | 7.36 |  |  | Solar |  | 05_01_9J360 | 07/16/2019 | 07/17/2019 | 1 | 1 | 0 | 07/18/2019 | 07/18/2019 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/16/2019 | 11/9/2020 | Y | EXP | 365 | 08/22/2020 | 10/02/2020 | 41 | 0 | 41 |  |  | 11/4/2020 | Connected |  | N
National Grid | PEPPERELL | 342922 | 01463 | 203.3 |  |  | Solar |  | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 647126 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W6 | 10/23/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | SPENCER | 685406 | 01562 | 5.76 |  |  | Solar |  | 05_14_21L1 | 04/17/2025 | 04/23/2025 | 3 | 0 | 3 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | WORCESTER | 708145 | 01604 | 17.6 |  |  | Solar |  | 05_14_54L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 175682 | 01772 | 115.2 |  |  | Solar |  | 05_14_6J2 | 12/24/2014 | 12/24/2014 | 4 | 0 | 4 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/24/2014 | 1/19/2016 | Y | EXP | 350 | 11/12/2015 | 09/01/2016 | 200 | 0 | 200 | 2/4/2015 | 2/4/2015 | 12/22/2015 | Connected |  | N
National Grid | EVERETT | 602555 | 02149 | 0 |  |  | Battery Add-On |  | 05_14_78L3 | 04/10/2024 | 05/09/2024 | 20 | 16 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/10/2024 | 12/31/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 653239 | 01826 | 10 |  |  | Solar |  | 05_01_226L2 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175716 | 01810 | 1000 |  |  | Solar |  | 05_01_406L3 | 12/26/2014 | 12/26/2014 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2015 | 02/13/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 |  | 8/1/2016 | N | STD | 301 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 641036 | 01841 | 5.76 |  |  | Solar |  | 05_01_552L1 | 09/17/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | DRACUT | 257227 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 10/14/2019 | 10/15/2019 | 0 | 0 | 0 | 10/16/2019 | 10/16/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | Connected |  | N
National Grid | PEPPERELL | 396057 | 01463 | 0 |  |  | Other |  | 05_05_310W5 | 01/25/2022 | 02/07/2022 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | CMPX |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 176325 | 01540 | 495 |  |  | Solar |  | 05_12_37W7 | 07/14/2015 | 07/14/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/21/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 699289 | 01562 | 15.2 |  |  | Solar |  | 05_14_21L1 | 06/17/2025 | 06/27/2025 | 6 | 4 | 2 | 06/30/2025 | 06/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | WORCESTER | 712170 | 01604 | 15.2 |  |  | Solar |  | 05_14_54L3 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177413 | 01752 | 3.8 |  |  | Solar |  | 05_14_6J2 | 09/12/2016 | 09/12/2016 | 1 | 1 | 0 | 09/14/2016 | 09/14/2016 | 282 | 0 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 09/12/2016 | 11/18/2017 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 629864 | 02149 | 5.76 |  |  | Solar |  | 05_14_78L3 | 08/02/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/02/2024 | 9/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | DRACUT | 654523 | 01826 | 23 |  |  | Battery Add-On |  | 05_01_226L2 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | ANDOVER | 175931 | 01810 | 10.75 |  |  | Solar |  | 05_01_406L3 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/15/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/3/2016 | 2/3/2016 | 1/3/2018 | Connected |  | N
National Grid | LAWRENCE | 642534 | 01841 | 5.76 |  |  | Solar |  | 05_01_552L1 | 09/24/2024 | 10/08/2024 | 1 | 0 | 1 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | DRACUT | 623844 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 07/10/2024 | 07/16/2024 | 1 | 0 | 1 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | PEPPERELL | 485595 | 01463 | 0 |  |  | Solar |  | 05_05_310W5 | 12/14/2022 | 12/19/2022 | 3 | 2 | 1 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 2/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N
National Grid | CHARLTON | 221781 | 01507 | 100 |  |  | Solar |  | 05_12_37W7 | 04/23/2019 | 04/25/2019 | 1 | 0 | 1 | 04/26/2019 | 04/26/2019 | 11 | 3 | 8 | 06/25/2019 | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 8/3/2020 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  | 3/9/2020 | Connected |  | N
National Grid | SPENCER | 720590 | 01562 | 10 |  |  | Solar |  | 05_14_21L2 | 09/19/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 09/19/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WORCESTER | 713352 | 01604 | 10.88 |  |  | Solar |  | 05_14_54L3 | 09/10/2025 | 09/22/2025 | 7 | 3 | 4 | 09/23/2025 | 09/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177910 | 01752 | 7.6 |  |  | Solar |  | 05_14_6J2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/25/2020 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 636599 | 02149 | 5.76 |  |  | Solar |  | 05_14_78L3 | 08/29/2024 | 09/26/2024 | 7 | 4 | 3 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 08/29/2024 | 11/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | DRACUT | 654994 | 01826 | 5.76 |  |  | Solar |  | 05_01_226L2 | 12/02/2024 | 01/01/2025 | 10 | 4 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/02/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176139 | 01810 | 8.39 |  |  | Solar |  | 05_01_406L3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/3/2015 | 8/3/2015 | 1/28/2016 | Connected |  | N
National Grid | LAWRENCE | 648467 | 01841 | 0 |  |  | Solar |  | 05_01_552L1 | 10/21/2024 | 10/24/2024 | 4 | 2 | 2 | 10/25/2024 | 10/25/2024 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | DRACUT | 633459 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J360 | 08/19/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | PEPPERELL | 516469 | 01463 | 6 |  |  | Solar |  | 05_05_310W5 | 04/17/2023 | 04/18/2023 | 1 | 0 | 1 | 04/19/2023 | 04/19/2023 | 89 | 67 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | OXFORD | 448424 | 01540 | 67.3 |  |  | Solar |  | 05_12_37W7 | 08/08/2022 | 08/17/2022 | 7 | 0 | 7 | 08/18/2022 | 08/18/2022 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | SPENCER | 722100 | 01562 | 3.8 |  |  | Solar |  | 05_14_21L2 | 10/14/2025 | 11/14/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 650727 | 01604 | 23 |  |  | Solar |  | 05_14_55L1 | 10/31/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/31/2024 | 4/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MARLBOROUGH | 197441 | 01752 | 3.8 |  |  | Solar |  | 05_14_6J2 | 10/04/2018 |  | 203 | 23 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 641351 | 02148 | 5.76 |  |  | Solar |  | 05_14_78L3 | 09/18/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 660803 | 01826 | 5.76 |  |  | Solar |  | 05_01_226L2 | 12/18/2024 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176751 | 01810 | 6 |  |  | Solar |  | 05_01_406L3 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/27/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 648713 | 01841 | 10 |  |  | Solar |  | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/04/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/17/2025 | Connected |  | N
National Grid | DRACUT | 636201 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J360 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 553692 | 01463 | 10 |  |  | Solar |  | 05_05_310W5 | 09/12/2023 | 09/18/2023 | 4 | 2 | 2 | 09/19/2023 | 09/19/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 476941 | 01540 | 9.074 |  |  | Solar |  | 05_12_37W7 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 11/11/2022 | 1/23/2024 | Y | EXP | 365 | 07/01/2023 | 11/03/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | SPENCER | 177701 | 01562 | 7.6 |  |  | Solar |  | 05_14_21L2 | 03/21/2017 | 03/21/2017 | 6 | 6 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/27/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | WORCESTER | 725323 | 01604 | 15.2 |  |  | Solar |  | 05_14_55L1 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBOROUGH | 297222 | 01772 | 249 |  |  | Solar |  | 05_14_6J2 | 06/18/2020 | 06/24/2020 | 4 | 3 | 1 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 647602 | 02148 | 6 |  |  | Solar |  | 05_14_78L3 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | LOWELL | 676260 | 01854 | 7.6 |  |  | Solar |  | 05_01_226L2 | 03/07/2025 |  | 76 | 73 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176845 | 01810 | 15 |  |  | Solar |  | 05_01_406L3 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/06/2016 | 05/06/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 5/8/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 648709 | 01841 | 10 |  |  | Solar |  | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | DRACUT | 641893 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J360 | 09/20/2024 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | PEPPERELL | 574084 | 01463 | 0 |  |  | Battery Add-On |  | 05_05_310W5 | 11/28/2023 | 11/29/2023 | 1 | 0 | 1 | 11/30/2023 | 11/30/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | OXFORD | 656154 | 01540 | 10 |  |  | Solar |  | 05_12_37W7 | 11/25/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | SPENCER | 424750 | 01562 | 7.6 |  |  | Solar |  | 05_14_21L2 | 07/21/2022 | 08/09/2022 | 13 | 10 | 3 | 08/10/2022 | 08/10/2022 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2023 | Connected |  | N
National Grid | WORCESTER | 740761 | 01604 | 15.2 |  |  | Solar |  | 05_14_55L1 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 335011 | 01772 | 166.6 |  |  | Solar |  | 05_14_6J2 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 658910 | 02148 | 5.76 |  |  | Solar |  | 05_14_78L3 | 12/06/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/06/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 684274 | 01850 | 7.6 |  |  | Solar |  | 05_01_226L2 | 04/14/2025 | 04/25/2025 | 8 | 5 | 3 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176939 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 12/16/2016 | 12/16/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2016 |  | 12/24/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | LAWRENCE | 656206 | 01841 | 7.6 |  |  | Solar |  | 05_01_552L1 | 11/22/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/22/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | DRACUT | 650128 | 01826 | 6 |  |  | Solar |  | 05_01_9J360 | 10/28/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | PEPPERELL | 574904 | 01463 | 0 |  |  | Battery Add-On |  | 05_05_310W5 | 11/30/2023 | 01/03/2024 | 22 | 13 | 9 | 01/04/2024 | 01/04/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 701523 | 01540 | 6.631 |  |  | Solar |  | 05_12_37W8 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SPENCER | 441257 | 01562 | 3.48 |  |  | Solar |  | 05_14_21L2 | 07/15/2022 | 07/19/2022 | 2 | 0 | 2 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/15/2022 | 3/1/2024 | Y | EXP | 365 | 02/17/2023 | 02/28/2023 | 12 | 0 | 12 |  |  | 9/6/2023 | Connected |  | Y
National Grid | WORCESTER | 174994 | 01604 | 13 |  |  | Solar |  | 05_14_55L1 | 03/13/2013 | 03/13/2013 | 6 | 0 | 6 | 03/25/2013 | 03/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2013 |  | 6/28/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 4/15/2013 | 4/15/2013 | 6/5/2013 | Connected |  | N
National Grid | SOUTHBOROUGH | 506007 | 01772 | 17.6 |  |  | Solar |  | 05_14_6J2 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2023 | 03/07/2023 | 6/6/2024 | Y | EXP | 365 | 08/12/2023 | 10/11/2023 | 61 | 0 | 61 |  |  | 10/14/2023 | Connected |  | N
National Grid | MALDEN | 660373 | 02148 | 7.6 |  |  | Solar |  | 05_14_78L3 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 686777 | 01826 | 19 |  |  | Solar |  | 05_01_226L2 | 04/23/2025 | 05/01/2025 | 6 | 2 | 4 | 05/02/2025 | 05/02/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177113 | 01845 | 936 |  |  | Solar |  | 05_01_406L3 | 08/04/2016 | 08/04/2016 | 128 | 128 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/14/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 662768 | 01841 | 3.8 |  |  | Solar |  | 05_01_552L1 | 12/27/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 652574 | 01826 | 8.41 |  |  | Solar |  | 05_01_9J360 | 11/06/2024 | 12/11/2024 | 13 | 7 | 6 | 12/12/2024 | 12/12/2024 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 624754 | 01463 | 15.3 |  |  | Solar |  | 05_05_310W5 | 07/15/2024 | 07/18/2024 | 3 | 0 | 3 | 07/19/2024 | 07/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2024 | Connected |  | N
National Grid | OXFORD | 304213 | 01540 | 6 |  |  | Solar |  | 05_12_37W8 | 09/24/2020 | 12/23/2020 | 61 | 40 | 21 | 12/24/2020 | 12/24/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 493449 | 01562 | 6 |  |  | Solar |  | 05_14_21L2 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177989 | 01604 | 15.2 |  |  | Solar |  | 05_14_55L1 | 08/28/2017 | 08/28/2017 | 27 | 26 | 1 | 10/10/2017 | 10/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/4/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | SOUTHBOROUGH | 549133 | 01772 | 6 |  |  | Solar |  | 05_14_6J2 | 09/06/2023 | 09/11/2023 | 4 | 3 | 1 | 09/12/2023 | 09/12/2023 | 46 | 22 | 24 | 11/28/2023 | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 |  | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 662183 | 02148 | 3.8 |  |  | Solar |  | 05_14_78L3 | 12/23/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 712231 | 01850 | 17.16 |  |  | Solar |  | 05_01_226L2 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177412 | 01845 | 1740 |  |  | Solar |  | 05_01_406L3 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 | 09/11/2016 | 8/24/2020 | Y | STD | 993 | 08/29/2019 | 11/22/2019 | 85 | 0 | 85 |  |  | 8/12/2020 | Connected |  | N
National Grid | LAWRENCE | 668644 | 01841 | 7.6 |  |  | Solar |  | 05_01_552L1 | 01/29/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | DRACUT | 655724 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 11/20/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | PEPPERELL | 638803 | 01463 | 10 |  |  | Solar |  | 05_05_310W5 | 09/09/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/09/2024 | 1/8/2026 | Y | EXP | 365 | 12/19/2024 | 02/13/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 387541 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W8 | 10/10/2021 |  | 147 | 137 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 574472 | 01562 | 10 |  |  | Solar |  | 05_14_21L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | WORCESTER | 198292 | 01604 | 9.92 |  |  | Solar |  | 05_14_55L1 | 10/11/2018 | 11/01/2018 | 11 | 4 | 7 | 11/02/2018 | 11/02/2018 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2018 |  | 4/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2020 | Connected |  | N
National Grid | SOUTHBOROUGH | 582362 | 01772 | 2.9 |  |  | Solar |  | 05_14_6J2 | 01/17/2024 | 01/19/2024 | 2 | 0 | 2 | 01/22/2024 | 01/22/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 668197 | 02148 | 7.68 |  |  | Solar |  | 05_14_78L3 | 02/03/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | DRACUT | 582916 | 01826 | 0 |  |  | Solar |  | 05_01_227W1 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOXFORD | 177669 | 01921 | 2000 |  |  | Solar |  | 05_01_406L3 | 05/25/2017 | 05/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/26/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 05/25/2017 | 6/29/2020 | Y | STD | 621 | 12/12/2019 | 06/12/2020 | 183 | 0 | 183 |  |  | 6/29/2020 | Connected |  | N
National Grid | LAWRENCE | 673877 | 01841 | 10 |  |  | Solar |  | 05_01_552L1 | 02/24/2025 | 03/17/2025 | 3 | 0 | 3 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 688483 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 04/29/2025 | 05/14/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 58 | 45 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 638771 | 01463 | 0 |  |  | Solar |  | 05_05_310W5 | 09/09/2024 | 09/11/2024 | 2 | 0 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2024 | Connected |  | N
National Grid | OXFORD | 662091 | 01540 | 3.8 |  |  | Solar |  | 05_12_37W8 | 12/20/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 644522 | 01562 | 5.76 |  |  | Solar |  | 05_14_21L2 | 10/02/2024 | 10/29/2024 | 10 | 7 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | WORCESTER | 247814 | 01604 | 0 |  |  | Solar |  | 05_14_55L1 | 08/22/2019 | 08/22/2019 | 0 | 0 | 0 | 08/23/2019 | 08/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/22/2019 | 9/17/2020 | Y | EXP | 365 | 01/11/2020 | 02/07/2020 | 27 | 0 | 27 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 643758 | 01752 | 4.64 |  |  | Solar |  | 05_14_6J2 | 09/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | MALDEN | 668055 | 02148 | 5.76 |  |  | Solar |  | 05_14_78L3 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 705049 | 01850 | 15.68 |  |  | Solar |  | 05_01_227W1 | 07/15/2025 | 08/07/2025 | 17 | 11 | 6 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 178103 | 01845 | 249.8 |  |  | Solar |  | 05_01_406L3 | 09/08/2017 | 02/12/2018 | 10 | 0 | 10 | 02/12/2018 | 02/12/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 9/16/2019 | N | EXP | 452 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 676225 | 01841 | 7.6 |  |  | Solar |  | 05_01_552L1 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | DRACUT | 699741 | 01826 | 5.76 |  |  | Solar |  | 05_01_9J360 | 06/19/2025 | 07/02/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | PEPPERELL | 657547 | 01463 | 10 |  |  | Solar |  | 05_05_310W5 | 11/28/2024 | 01/14/2025 | 21 | 17 | 4 | 01/15/2025 | 01/15/2025 | 26 | 0 | 26 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | OXFORD | 662931 | 01540 | 3.8 |  |  | Solar |  | 05_12_37W8 | 12/30/2024 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 645288 | 01562 | 7.6 |  |  | Solar |  | 05_14_21L2 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | WORCESTER | 310835 | 01604 | 10 |  |  | Solar |  | 05_14_55L1 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | MARLBOROUGH | 661733 | 01752 | 10 |  |  | Solar |  | 05_14_6J2 | 12/19/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | MALDEN | 685222 | 02148 | 6.282 |  |  | Solar |  | 05_14_78L3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 65 | 49 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 740278 | 01826 | 0 |  |  | Battery Add-On |  | 05_01_227W1 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 178302 | 01845 | 0 |  |  | Solar |  | 05_01_406L3 | 01/09/2018 | 03/09/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/05/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 678598 | 01841 | 5.76 |  |  | Solar |  | 05_01_552L1 | 03/17/2025 | 04/03/2025 | 8 | 6 | 2 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/21/2025 | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 701039 | 01826 | 7.6 |  |  | Solar |  | 05_01_9J360 | 06/25/2025 | 07/14/2025 | 4 | 0 | 4 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 8/14/2026 | Y | EXP | 365 | 10/02/2025 | 10/06/2025 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 661259 | 01523 | 5.76 |  |  | Solar |  | 05_05_310W5 | 12/17/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | CHARLTON | 178254 | 01507 | 33.3 |  |  | Solar |  | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 28 | 0 | 28 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N
National Grid | SPENCER | 649324 | 01562 | 10 |  |  | Solar |  | 05_14_21L2 | 11/05/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | WORCESTER | 375312 | 01604 | 8.376 |  |  | Solar |  | 05_14_55L1 | 08/17/2021 | 08/19/2021 | 2 | 0 | 2 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 10/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 682496 | 01772 | 15.2 |  |  | Solar |  | 05_14_6J3 | 04/03/2025 | 04/14/2025 | 7 | 5 | 2 | 04/15/2025 | 04/15/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MALDEN | 718161 | 02148 | 11.375 |  |  | Solar |  | 05_14_78L3 | 09/10/2025 | 09/24/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | LOWELL | 174132 | 01854 | 300 |  |  | Solar |  | 05_01_227W1 | 05/03/2012 | 05/03/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/29/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 201189 | 01921 | 3.8 |  |  | Solar |  | 05_01_406L3 | 08/15/2019 | 08/15/2019 | 0 | 0 | 0 | 08/16/2019 | 08/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2019 |  | 10/14/2019 | N | EXP | 52 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | LAWRENCE | 682377 | 01841 | 13.36 |  |  | Solar |  | 05_01_552L1 | 04/02/2025 | 07/02/2025 | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 176249 | 01826 | 140 |  |  | Solar |  | 05_01_HT15 | 07/08/2015 | 07/08/2015 | 2 | 2 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 07/08/2015 | 7/13/2016 | Y | EXP | 343 | 12/10/2015 | 03/17/2016 | 66 | 0 | 66 | 8/15/2016 | 8/15/2016 | 8/15/2016 | Connected |  | N
National Grid | SHIRLEY | 686547 | 01464 | 9.86 |  |  | Solar |  | 05_05_310W6 | 04/24/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/24/2025 | 7/24/2026 | Y | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 178283 | 01540 | 133.2 |  |  | Solar |  | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 8 | 0 | 8 | 05/09/2018 | 05/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N
National Grid | SPENCER | 655399 | 01562 | 4.06 |  |  | Solar |  | 05_14_21L2 | 11/19/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/19/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | WORCESTER | 379389 | 01604 | 9.57 |  |  | Solar |  | 05_14_55L1 | 09/02/2021 |  | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 285114 | 01772 | 7.6 |  |  | Solar |  | 05_14_6J3 | 04/01/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 715946 | 02148 | 6.84 |  |  | Solar |  | 05_14_78L9 | 09/02/2025 | 09/23/2025 | 14 | 9 | 5 | 09/24/2025 | 09/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174187 | 01826 | 500 |  |  | Solar |  | 05_01_227W1 | 03/12/2012 | 03/12/2012 | 11 | 0 | 11 | 04/05/2012 | 04/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 | 03/12/2012 | 6/1/2012 | Y | EXP | -237 | 07/15/2013 | 09/27/2013 | 53 | 0 | 53 | 9/26/2013 | 9/26/2013 | 9/27/2013 | Connected |  | N
National Grid | ANDOVER | 209264 | 01845 | 17.28 |  |  | Solar |  | 05_01_406L3 | 02/11/2019 | 04/22/2019 | 49 | 49 | 0 | 04/23/2019 | 04/23/2019 | 242 | 241 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2020 |  | 1/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | LAWRENCE | 688712 | 01841 | 15.2 |  |  | Solar |  | 05_01_552L1 | 05/01/2025 | 05/19/2025 | 7 | 3 | 4 | 07/10/2025 | 07/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | DRACUT | 186780 | 01826 | 788 |  |  | Solar |  | 05_01_HT15 | 06/06/2018 | 06/06/2018 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2018 | 08/17/2018 | 46 | 31 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 |  | 12/25/2020 | N | STD | 534 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 174836 | 01523 | 1450 |  |  | Solar |  | 05_05_310W6 | 08/31/2012 | 08/31/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2012 | 11/27/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 178308 | 01540 | 3807.99 |  |  | Natural Gas |  | 05_12_37W9 | 01/10/2018 | 03/30/2018 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2018 | 04/26/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 6/7/2019 | N | STD | 149 |  |  | 0 | 0 | 0 | 5/31/2019 | 5/30/2019 | 6/7/2019 | Connected |  | N
National Grid | SPENCER | 667886 | 01562 | 21.4 |  |  | Solar |  | 05_14_21L2 | 01/26/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/26/2025 | 5/12/2026 | Y | EXP | 365 | 06/26/2025 |  | 190 | 0 | 190 |  |  | 11/21/2025 | Connected |  | N
National Grid | WORCESTER | 387061 | 01604 | 9.57 |  |  | Solar |  | 05_14_55L1 | 10/07/2021 | 10/14/2021 | 4 | 4 | 0 | 10/15/2021 | 10/15/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | MARLBOROUGH | 315756 | 01752 | 7.6 |  |  | Solar |  | 05_14_6J3 | 10/13/2020 |  | 39 | 38 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 723653 | 02149 | 3.8 |  |  | Solar |  | 05_14_78L9 | 10/03/2025 | 10/13/2025 | 5 | 1 | 4 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 174231 | 01850 | 2000 |  |  | Solar |  | 05_01_227W1 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 6/19/2014 | 6/19/2014 | 6/19/2014 | Connected |  | N
National Grid | ANDOVER | 243055 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 10/07/2019 | 10/14/2019 | 4 | 4 | 0 | 10/15/2019 | 10/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/07/2019 | 10/7/2020 | Y | EXP | 365 | 07/14/2020 | 08/21/2020 | 38 | 0 | 38 |  |  | 9/4/2020 | Connected |  | N
National Grid | LAWRENCE | 693410 | 01841 | 4.94 |  |  | Solar |  | 05_01_552L1 | 05/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 197318 | 01826 | 200 |  |  | Solar |  | 05_01_HT15 | 10/01/2018 | 10/08/2018 | 5 | 3 | 2 | 10/09/2018 | 10/09/2018 | 63 | 35 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175281 | 01453 | 42.57 |  |  | Solar |  | 05_05_310W6 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 4/30/2015 | Connected |  | N
National Grid | OXFORD | 253372 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W9 | 09/14/2019 | 09/17/2019 | 1 | 1 | 0 | 09/18/2019 | 09/18/2019 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 676616 | 01562 | 11.4 |  |  | Solar |  | 05_14_21L2 | 03/27/2025 | 04/11/2025 | 11 | 8 | 3 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 393293 | 01610 | 6.38 |  |  | Solar |  | 05_14_55L1 | 12/17/2021 | 01/06/2022 | 13 | 12 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2022 |  | 3/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 177072 | 01772 | 75 |  |  | Solar |  | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | EVERETT | 731066 | 02149 | 240 |  |  | Solar |  | 05_14_78L9 | 11/10/2025 | 12/09/2025 | 19 | 11 | 8 | 12/10/2025 | 12/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | DRACUT | 174595 | 01826 | 82 |  |  | Solar |  | 05_01_227W1 | 10/19/2011 | 10/19/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2011 |  | 2/21/2012 | N | EXP | 62 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 2/21/2012 | Connected |  | N
National Grid | ANDOVER | 244524 | 01845 | 249.8 |  |  | Solar |  | 05_01_406L3 | 07/22/2019 | 07/26/2019 | 4 | 3 | 1 |  |  | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 | 07/22/2019 | 11/10/2023 | Y | STD | 278 | 11/01/2022 | 05/03/2023 | 184 | 0 | 184 |  |  | 10/17/2023 | Connected |  | N
National Grid | LAWRENCE | 697891 | 01841 | 15.2 |  |  | Solar |  | 05_01_552L1 | 06/11/2025 | 06/23/2025 | 7 | 4 | 3 | 06/24/2025 | 06/24/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | DRACUT | 438934 | 01826 | 150 |  |  | Solar |  | 05_01_HT17 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 175478 | 01523 | 250 |  |  | Solar |  | 05_05_310W6 | 03/13/2014 | 03/13/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 384620 | 01507 | 1266 |  |  | Solar |  | 05_12_37W9 | 08/10/2022 |  | 231 | 63 | 168 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 646886 | 01562 | 5.76 |  |  | Solar |  | 05_14_21L3 | 10/14/2024 | 12/18/2024 | 37 | 34 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | WORCESTER | 479560 | 01610 | 15.2 |  |  | Solar |  | 05_14_55L1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 177070 | 01772 | 108 |  |  | Solar |  | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | EVERETT | 730658 | 02149 | 11.5 |  |  | Solar |  | 05_14_78L9 | 10/31/2025 | 11/03/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 175314 | 01826 | 594.4 |  |  | Solar |  | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 343654 | 01845 | 7.6 |  |  | Solar |  | 05_01_406L3 | 03/16/2021 | 03/17/2021 | 0 | 0 | 0 | 03/18/2021 | 03/18/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/16/2021 | 12/8/2022 | Y | EXP | 365 | 07/24/2021 | 12/08/2021 | 138 | 7 | 131 |  |  | 1/4/2022 | Connected |  | N
National Grid | LAWRENCE | 703266 | 01841 | 18.829 |  |  | Solar |  | 05_01_552L1 | 07/07/2025 | 07/10/2025 | 3 | 0 | 3 | 07/11/2025 | 07/11/2025 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 320344 | 01826 | 75 |  |  | Natural Gas |  | 05_01_HT20 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | LANCASTER | 176834 | 01523 | 650 |  |  | Solar |  | 05_05_310W6 | 02/29/2016 | 02/29/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2016 | 05/10/2016 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2017 |  | 12/8/2017 | N | STD | 294 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/14/2017 | Connected |  | N
National Grid | OXFORD | 592425 | 01540 | 6 |  |  | Solar |  | 05_12_37W9 | 03/04/2024 | 03/05/2024 | 1 | 0 | 1 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 03/04/2024 | 3/12/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 692133 | 01562 | 10 |  |  | Solar |  | 05_14_21L3 | 05/30/2025 | 07/08/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 | 09/23/2025 | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WORCESTER | 572292 | 01610 | 480 |  |  | Solar |  | 05_14_55L1 | 12/07/2023 | 02/01/2024 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2024 | 02/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 317552 | 01772 | 33.3 |  |  | Solar |  | 05_14_6J4 | 10/06/2020 | 11/06/2020 | 23 | 15 | 8 | 11/09/2020 | 11/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | EVERETT | 175382 | 02149 | 18 |  |  | Solar |  | 05_14_78L9 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2014 |  | 9/30/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 9/12/2014 | 9/12/2014 | 10/31/2014 | Connected |  | N
National Grid | DRACUT | 175313 | 01826 | 587.2 |  |  | Solar |  | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 353715 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 05/18/2022 | 01/06/2022 | 6 | 4 | 2 | 05/26/2022 | 05/26/2022 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 | 05/18/2022 | 6/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | Y
National Grid | LAWRENCE | 725840 | 01841 | 5.76 |  |  | Solar |  | 05_01_552L1 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | DRACUT | 174554 | 01826 | 1333 |  |  | Solar |  | 05_01_HT22 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 176890 | 01464 | 54 |  |  | Solar |  | 05_05_310W6 | 11/13/2015 | 11/13/2015 | 24 | 24 | 0 | 12/21/2015 | 12/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2016 |  | 11/21/2016 | N | EXP | 321 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/3/2017 | Connected |  | N
National Grid | OXFORD | 638410 | 01540 | 10 |  |  | Solar |  | 05_12_37W9 | 09/06/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | SPENCER | 723479 | 01562 | 20 |  |  | Solar |  | 05_14_21L3 | 10/01/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 575743 | 01610 | 240 |  |  | Solar |  | 05_14_55L1 | 12/08/2023 | 02/01/2024 | 36 | 25 | 11 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 604190 | 01772 | 6.09 |  |  | Solar |  | 05_14_6J4 | 04/17/2024 | 04/23/2024 | 5 | 2 | 3 | 04/24/2024 | 04/24/2024 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 175670 | 02149 | 7.6 |  |  | Solar |  | 05_14_78L9 | 10/21/2014 | 10/21/2014 | 6 | 0 | 6 | 10/30/2014 | 10/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 766 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 8/17/2016 | Connected |  | N
National Grid | LOWELL | 175454 | 01854 | 1500 |  |  | Solar |  | 05_01_227W1 | 07/16/2014 | 07/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 07/16/2014 | 6/1/2016 | Y | STD | 531 | 02/03/2017 | 03/03/2017 | 19 | 0 | 19 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | ANDOVER | 418004 | 01845 | 15.2 |  |  | Solar |  | 05_01_406L3 | 03/16/2022 | 03/17/2022 | 1 | 0 | 1 | 03/18/2022 | 03/18/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2022 | Connected |  | N
National Grid | LAWRENCE | 301406 | 01840 | 400 |  |  | Natural Gas |  | 05_01_552L3 | 12/09/2020 | 12/21/2020 | 7 | 0 | 7 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | DRACUT | 178047 | 01826 | 800 |  |  | Solar |  | 05_01_HT22 | 05/05/2017 | 05/30/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 01/18/2018 | 04/06/2020 | 556 | 0 | 556 | 2/15/2018 | 05/05/2017 | 6/17/2021 | Y | STD | 450 | 10/16/2020 | 04/21/2021 | 187 | 0 | 187 |  |  | 6/2/2021 | Connected |  | N
National Grid | LANCASTER | 177181 | 01523 | 650 |  |  | Solar |  | 05_05_310W6 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2016 | 10/18/2016 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2017 | 08/12/2016 | 2/23/2018 | Y | STD | 347 | 07/06/2017 | 12/19/2017 | 109 | 0 | 109 | 2/15/2018 | 2/15/2018 | 2/16/2018 | Connected |  | N
National Grid | OXFORD | 639926 | 01540 | 7.6 |  |  | Solar |  | 05_12_37W9 | 09/12/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2025 | Connected |  | N
National Grid | SPENCER | 174624 | 01562 | 40 |  |  | Solar |  | 05_14_21L3 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/12/2011 | 12/12/2011 | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | WORCESTER | 640040 | 01609 | 23.8 |  |  | Solar |  | 05_14_55L1 | 09/13/2024 | 09/17/2024 | 3 | 1 | 2 | 09/18/2024 | 09/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 659147 | 01772 | 11.4 |  |  | Solar |  | 05_14_6J4 | 12/08/2024 |  | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 176654 | 02149 | 7.6 |  |  | Solar |  | 05_14_78L9 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 4/24/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 175579 | 01854 | 150 |  |  | Solar |  | 05_01_227W1 | 12/10/2014 | 12/10/2014 | 27 | 6 | 21 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 2/28/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/22/2015 | Connected |  | N
National Grid | ANDOVER | 428180 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 05/04/2022 | 06/10/2022 | 15 | 13 | 2 | 06/13/2022 | 06/13/2022 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 05/04/2022 | 4/3/2024 | Y | EXP | 365 | 03/09/2023 | 04/03/2023 | 26 | 0 | 26 |  |  | 4/12/2023 | Connected |  | N
National Grid | LAWRENCE | 626719 | 01841 | 23 |  |  | Solar |  | 05_01_552L3 | 07/22/2024 | 07/25/2024 | 3 | 0 | 3 | 07/26/2024 | 07/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/22/2024 | 12/31/2025 | Y | EXP | 365 | 01/18/2025 | 08/11/2025 | 206 | 0 | 206 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174342 | 01826 | 7500 |  |  | Natural Gas |  | 05_01_HT25 | 11/08/2010 | 11/08/2010 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 11/08/2010 | 10/31/2012 | Y | STD | -42 | 11/10/2011 | 03/05/2012 | 75 | 0 | 75 | 1/24/2013 | 1/24/2013 | 5/7/2013 | Connected |  | N
National Grid | LANCASTER | 186377 | 01523 | 740 |  |  | Solar |  | 05_05_310W6 | 06/25/2018 | 06/25/2018 | 38 | 28 | 10 | 08/20/2018 | 08/20/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2018 |  | 12/31/2020 | N | EXP | 499 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | Y
National Grid | CHARLTON | 650947 | 01507 | 5.76 |  |  | Solar |  | 05_12_37W9 | 11/04/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | SPENCER | 175458 | 01562 | 60 |  |  | Natural Gas |  | 05_14_21L3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2014 |  | 10/31/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 11/4/2014 | 11/4/2014 | 11/10/2014 | Connected |  | N
National Grid | WORCESTER | 654018 | 01603 | 17.6 |  |  | Solar |  | 05_14_55L1 | 11/20/2024 | 12/02/2024 | 6 | 2 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | MARLBOROUGH | 665348 | 01752 | 6.09 |  |  | Solar |  | 05_14_6J4 | 01/13/2025 | 03/04/2025 | 18 | 13 | 5 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | EVERETT | 176709 | 02149 | 3.8 |  |  | Solar |  | 05_14_78L9 | 10/28/2015 | 10/28/2015 | 3 | 3 | 0 | 11/03/2015 | 11/03/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 |  | 11/3/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176051 | 01854 | 184 |  |  | Solar |  | 05_01_227W1 | 01/12/2015 | 01/12/2015 | 11 | 0 | 11 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 7/31/2015 | N | EXP | 168 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 2/4/2016 | Connected |  | N
National Grid | ANDOVER | 440487 | 01845 | 3.8 |  |  | Solar |  | 05_01_406L3 | 07/01/2022 | 07/05/2022 | 1 | 0 | 1 | 07/06/2022 | 07/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | LAWRENCE | 652843 | 01841 | 6 |  |  | Solar |  | 05_01_552L3 | 11/07/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DRACUT | 175683 | 01826 | 75.6 |  |  | Solar |  | 05_01_HT26 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 | 12/24/2014 | 5/31/2015 | Y | EXP | 116 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 10/28/2015 | Connected |  | N
National Grid | SHIRLEY | 254944 | 01464 | 15.2 |  |  | Solar |  | 05_05_310W6 | 09/18/2019 | 09/20/2019 | 1 | 1 | 0 | 09/23/2019 | 09/23/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 09/18/2019 | 5/11/2020 | Y | EXP | 230 | 11/13/2019 | 01/07/2020 | 55 | 0 | 55 |  |  | 1/14/2020 | Connected |  | N
National Grid | OXFORD | 368844 | 01540 | 100.8 |  |  | Solar |  | 05_12_3J1 | 08/24/2021 | 09/15/2021 | 15 | 6 | 9 |  |  | 42 | 12 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 176420 | 01562 | 6 |  |  | Solar |  | 05_14_21L3 | 12/07/2015 | 12/07/2015 | 2 | 2 | 0 | 12/10/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 12/13/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/2/2016 | Connected |  | N
National Grid | WORCESTER | 657089 | 01610 | 10 |  |  | Solar |  | 05_14_55L1 | 11/26/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 174705 | 01772 | 250 |  |  | Solar |  | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 192 | 0 | 192 | 07/12/2013 | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 8/15/2013 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 177476 | 02149 | 10 |  |  | Solar |  | 05_14_78L9 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 07/06/2016 | 12/12/2017 | Y | EXP | 511 | 05/16/2017 | 06/05/2017 | 13 | 0 | 13 | 7/28/2017 | 7/28/2017 | 7/28/2017 | Connected |  | N
National Grid | LOWELL | 176714 | 01854 | 15.2 |  |  | Solar |  | 05_01_227W1 | 01/08/2016 | 01/08/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/13/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/19/2016 | Connected |  | N
National Grid | ANDOVER | 473594 | 01845 | 8.41 |  |  | Solar |  | 05_01_406L3 | 12/08/2022 | 12/20/2022 | 8 | 7 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 3/28/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 681154 | 01843 | 15.2 |  |  | Solar |  | 05_01_552L3 | 03/31/2025 | 04/01/2025 | 1 | 0 | 1 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 535525 | 01826 | 990 |  |  | Solar |  | 05_01_HT26 | 11/21/2023 |  | 117 | 109 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 369538 | 01523 | 220 |  |  | Solar |  | 05_05_310W6 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2022 | 07/21/2021 | 7/9/2024 | Y | STD | 440 | 03/23/2024 | 03/27/2024 | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | OXFORD | 368795 | 01540 | 151.2 |  |  | Solar |  | 05_12_3J1 | 07/12/2021 | 08/03/2021 | 16 | 9 | 7 |  |  | 72 | 46 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 | 07/12/2021 | 5/22/2024 | Y | STD | 250 | 01/30/2024 | 01/29/2024 | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | BROOKFIELD | 176495 | 01515 | 6 |  |  | Solar |  | 05_14_21L3 | 12/11/2015 | 12/11/2015 | 2 | 2 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/16/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/22/2016 | Connected |  | N
National Grid | WORCESTER | 674728 | 01604 | 19 |  |  | Solar |  | 05_14_55L1 | 02/28/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175136 | 01752 | 100 |  |  | Solar |  | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 177689 | 02149 | 100 |  |  | Solar |  | 05_14_78L9 | 10/03/2017 | 10/03/2017 | 2 | 2 | 0 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/8/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | LOWELL | 177900 | 01852 | 3875 |  |  | Solar |  | 05_01_227W1 | 06/15/2017 | 06/15/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2017 | 09/22/2017 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 06/15/2017 | 6/18/2021 | Y | STD | 340 | 11/04/2020 | 03/12/2021 | 128 | 0 | 128 | 5/20/2021 | 5/28/2021 | 6/11/2021 | Connected |  | N
National Grid | ANDOVER | 495957 | 01845 | 6.96 |  |  | Solar |  | 05_01_406L3 | 02/03/2023 | 02/08/2023 | 3 | 1 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/03/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | N
National Grid | LAWRENCE | 174944 | 01841 | 333 |  |  | Solar |  | 05_01_552L3 | 09/29/2011 | 09/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2012 | 09/29/2011 | 11/30/2012 | Y | STD | 109 | 07/29/2013 | 09/13/2013 | 33 | 0 | 33 | 9/11/2013 | 9/11/2013 | 9/11/2013 | Connected |  | N
National Grid | DRACUT | 613305 | 01826 | 870 |  |  | Solar |  | 05_01_HT26 | 06/17/2024 | 07/24/2024 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2024 | 09/23/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 426147 | 01453 | 10 |  |  | Solar |  | 05_05_310W6 | 06/01/2022 | 06/30/2022 | 20 | 18 | 2 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/01/2022 | 6/13/2024 | Y | EXP | 365 | 10/11/2022 | 06/14/2023 | 247 | 0 | 247 |  |  | 8/7/2023 | Connected |  | Y
National Grid | OXFORD | 647145 | 01540 | 10 |  |  | Solar |  | 05_12_3J2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | BROOKFIELD | 176706 | 01515 | 6.8 |  |  | Solar |  | 05_14_21L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 351 | 05/11/2016 | 05/26/2016 | 11 | 0 | 11 | 11/17/2015 | 11/17/2015 | 10/25/2016 | Connected |  | N
National Grid | WORCESTER | 690737 | 01604 | 7.6 |  |  | Solar |  | 05_14_55L1 | 05/09/2025 | 05/22/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 44 | 28 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 175134 | 01772 | 100 |  |  | Solar |  | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2013 | 11/11/2012 | 1/31/2013 | Y | EXP | -169 | 02/06/2014 | 04/14/2014 | 45 | 0 | 45 | 8/5/2013 | 8/5/2013 | 4/24/2014 | Connected |  | N
National Grid | SALEM | 353172 | 01970 | 3.8 |  |  | Solar |  | 05_14_78L9 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 184857 | 01854 | 4980 |  |  | Solar |  | 05_01_227W1 | 05/09/2018 | 06/06/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2018 | 07/25/2018 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 05/09/2018 | 1/17/2024 | Y | STD | 880 | 08/12/2022 | 01/18/2023 | 160 | 0 | 160 | 12/15/2023 | 12/19/2023 | 12/29/2023 | Connected |  | N
National Grid | ANDOVER | 524689 | 01845 | 0 |  |  | Solar |  | 05_01_406L3 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 199 | 180 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175797 | 01840 | 990 |  |  | Solar |  | 05_01_552L3 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 192164 | 01826 | 249.8 |  |  | Solar |  | 05_01_HT27 | 08/06/2018 | 09/04/2018 | 18 | 0 | 18 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 618186 | 01453 | 9.765 |  |  | Solar |  | 05_05_310W6 | 07/26/2024 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 698376 | 01507 | 9.88 |  |  | Solar |  | 05_12_3J2 | 06/13/2025 | 06/27/2025 | 4 | 2 | 2 | 07/09/2025 | 07/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/13/2025 | 8/25/2026 | Y | EXP | 365 | 10/25/2025 | 11/05/2025 | 12 | 0 | 12 |  |  | 11/14/2025 | Connected |  | N
National Grid | BROOKFIELD | 176926 | 01515 | 10 |  |  | Solar |  | 05_14_21L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 11/25/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 | 9/14/2016 | Connected |  | N
National Grid | WORCESTER | 198828 | 01610 | 10 |  |  | Solar |  | 05_14_55L2 | 10/19/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 |  | 7/1/2019 | N | EXP | 230 |  |  | 0 | 0 | 0 |  |  | 6/19/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 178531 | 01772 | 60 |  |  | Solar |  | 05_14_6J5 | 12/05/2017 | 12/05/2017 | 18 | 0 | 18 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/10/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/10/2018 | Connected |  | N
National Grid | SALEM | 557592 | 01970 | 7.6 |  |  | Solar |  | 05_14_78L9 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 188006 | 01854 | 11.4 |  |  | Solar |  | 05_01_227W1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 | 06/21/2018 | 06/21/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 526264 | 01845 | 7.6 |  |  | Solar |  | 05_01_406L3 | 05/22/2023 | 05/25/2023 | 3 | 0 | 3 | 05/26/2023 | 05/26/2023 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/22/2023 | 7/9/2024 | Y | EXP | 365 | 08/10/2023 | 09/11/2023 | 33 | 0 | 33 |  |  | 10/4/2023 | Connected |  | N
National Grid | LAWRENCE | 176145 | 01840 | 100 |  |  | Solar |  | 05_01_552L3 | 06/30/2015 | 06/30/2015 | 2 | 2 | 0 | 07/03/2015 | 07/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2015 |  | 7/6/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 2/18/2016 | Connected |  | N
National Grid | DRACUT | 438978 | 01826 | 100 |  |  | Solar |  | 05_01_HT27 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 631656 | 01523 | 10 |  |  | Solar |  | 05_05_310W6 | 08/09/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 700251 | 01540 | 11.4 |  |  | Solar |  | 05_12_3J2 | 06/23/2025 | 07/23/2025 | 7 | 3 | 4 | 07/24/2025 | 07/24/2025 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 177872 | 01506 | 6 |  |  | Solar |  | 05_14_21L3 | 08/14/2017 | 08/14/2017 | 170 | 0 | 170 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 348152 | 01610 | 7.25 |  |  | Solar |  | 05_14_55L2 | 03/22/2021 | 03/25/2021 | 3 | 3 | 0 | 03/26/2021 | 03/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2021 |  | 3/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 314998 | 01772 | 7.6 |  |  | Solar |  | 05_14_6J5 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/03/2020 |  | Y | EXP | 365 | 04/14/2021 | 06/30/2021 | 77 | 0 | 77 |  |  | 8/10/2021 | Connected |  | N
National Grid | SALEM | 537415 | 01970 | 8.064 |  |  | Solar |  | 05_14_78L9 | 07/07/2023 | 09/19/2023 | 51 | 50 | 1 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 07/07/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/15/2024 | 63 | 0 | 63 |  |  | 5/23/2024 | Connected |  | N
National Grid | LOWELL | 272564 | 01854 | 0 |  |  | Solar |  | 05_01_227W1 | 02/05/2020 | 02/20/2020 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2020 | 03/13/2020 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 | 02/05/2020 | 9/8/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 568197 | 01845 | 0 |  |  | Battery Add-On |  | 05_01_406L3 | 11/02/2023 | 12/13/2023 | 27 | 24 | 3 | 12/14/2023 | 12/14/2023 | 93 | 69 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | LAWRENCE | 176143 | 01840 | 76 |  |  | Solar |  | 05_01_552L3 | 06/29/2015 | 06/29/2015 | 1 | 1 | 0 | 07/02/2015 | 07/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 350 | 11/12/2015 | 11/30/2015 | 11 | 0 | 11 | 7/22/2015 | 7/22/2015 | 1/15/2016 | Connected |  | N
National Grid | DRACUT | 617208 | 01826 | 250 |  |  | Solar |  | 05_01_HT28 | 09/23/2024 | 11/21/2024 | 42 | 32 | 10 |  |  | 86 | 61 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LANCASTER | 638307 | 01523 | 11.517 |  |  | Solar |  | 05_05_310W6 | 09/12/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | OXFORD | 672445 | 01540 | 10 |  |  | Solar |  | 05_12_3J6 | 02/17/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROOKFIELD | 177958 | 01515 | 6 |  |  | Solar |  | 05_14_21L3 | 10/26/2017 | 10/26/2017 | 80 | 79 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 553486 | 01603 | 15.2 |  |  | Solar |  | 05_14_55L2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | Y
National Grid | SOUTHBOROUGH | 633921 | 01772 | 10 |  |  | Solar |  | 05_14_6J5 | 08/20/2024 | 08/30/2024 | 6 | 0 | 6 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/20/2024 | 9/17/2025 | Y | EXP | 365 | 12/11/2024 | 02/25/2025 | 77 | 0 | 77 |  |  | 2/28/2025 | Connected |  | N
National Grid | SALEM | 596726 | 01970 | 10 |  |  | Solar |  | 05_14_78L9 | 04/15/2024 | 04/19/2024 | 5 | 4 | 1 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 04/15/2024 | 6/15/2025 | Y | EXP | 365 | 08/01/2024 | 09/12/2024 | 43 | 0 | 43 |  |  | 10/17/2024 | Connected |  | N
National Grid | LOWELL | 287827 | 01854 | 4950 |  |  | Other |  | 05_01_227W1 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/02/2020 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 568942 | 01845 | 14.79 |  |  | Solar |  | 05_01_406L3 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2023 | 11/08/2023 | 12/20/2024 | Y | EXP | 365 | 02/16/2024 | 02/16/2024 | 1 | 0 | 1 |  |  | 4/3/2024 | Connected |  | N
National Grid | LAWRENCE | 176690 | 01840 | 496 |  |  | Solar |  | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/13/2018 | Connected |  | N
National Grid | DRACUT | 196401 | 01826 | 66.6 |  |  | Solar |  | 05_01_HT28 | 09/19/2018 | 08/01/2019 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 |  | 6/30/2020 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 660473 | 01523 | 5.76 |  |  | Solar |  | 05_05_310W6 | 12/13/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | OXFORD | 230775 | 01540 | 66.6 |  |  | Solar |  | 05_12_3J6 | 07/16/2020 | 07/31/2020 | 11 | 5 | 6 | 08/03/2020 | 08/03/2020 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 10/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 178024 | 01515 | 5.47 |  |  | Solar |  | 05_14_21L3 | 08/31/2017 | 08/31/2017 | 29 | 27 | 2 | 10/13/2017 | 10/13/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 |  | 9/5/2018 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 598369 | 01610 | 14.208 |  |  | Solar |  | 05_14_55L2 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 643271 | 01745 | 10 |  |  | Solar |  | 05_14_6J5 | 09/27/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | SALEM | 647856 | 01970 | 7.6 |  |  | Solar |  | 05_14_78L9 | 10/17/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 315362 | 01854 | 0 |  |  | Other |  | 05_01_227W1 | 11/05/2020 | 11/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 11/30/2020 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/05/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 579001 | 01845 | 140 |  |  | Solar |  | 05_01_406L3 | 12/21/2023 | 01/07/2024 | 10 | 0 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 176719 | 01841 | 496 |  |  | Solar |  | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/24/2018 | Connected |  | N
National Grid | DRACUT | 177112 | 01826 | 4400 |  |  | Natural Gas |  | 05_01_HT31 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 8/30/2018 | N | STD | 702 | 05/28/2018 | 05/27/2018 | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | LANCASTER | 670809 | 01523 | 7.6 |  |  | Solar |  | 05_05_310W6 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 655816 | 01540 | 7.6 |  |  | Solar |  | 05_12_3J6 | 11/20/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | BROOKFIELD | 178418 | 01515 | 6 |  |  | Solar |  | 05_14_21L3 | 01/16/2018 | 01/16/2018 | 22 | 0 | 22 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2018 |  | 1/22/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N
National Grid | WORCESTER | 661473 | 01604 | 7.6 |  |  | Solar |  | 05_14_55L2 | 12/18/2024 | 02/21/2025 | 11 | 7 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 648222 | 01772 | 10 |  |  | Solar |  | 05_14_6J5 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 | 04/15/2025 | 05/06/2025 | 22 | 0 | 22 |  |  | 5/23/2025 | Connected |  | N
National Grid | SALEM | 655530 | 01970 | 3.8 |  |  | Solar |  | 05_14_78L9 | 11/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 11/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | LOWELL | 336841 | 01854 | 6 |  |  | Solar |  | 05_01_227W1 | 02/04/2021 | 02/11/2021 | 4 | 1 | 3 | 02/12/2021 | 02/12/2021 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 | 02/04/2021 | 5/1/2022 | Y | EXP | 365 | 07/09/2021 | 10/05/2021 | 74 | 3 | 71 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 578775 | 01845 | 6.09 |  |  | Solar |  | 05_01_406L3 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | LAWRENCE | 177414 | 01841 | 20.2 |  |  | Solar |  | 05_01_552L3 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/12/2016 | 9/18/2017 | Y | EXP | 354 | 12/28/2016 | 01/05/2017 | 5 | 0 | 5 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | DRACUT | 514546 | 01826 | 0 |  |  | Natural Gas |  | 05_01_HT41 | 05/26/2023 | 06/28/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/21/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 04/09/2024 | 02/21/2025 | 216 | 0 | 216 | 3/20/2024 |  | 10/10/2026 | N | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 671407 | 01523 | 7.6 |  |  | Solar |  | 05_05_310W6 | 02/12/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | OXFORD | 665449 | 01540 | 5.76 |  |  | Solar |  | 05_12_3J901 | 01/15/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 01/15/2025 | 5/10/2026 | Y | EXP | 365 | 07/12/2025 | 10/15/2025 | 96 | 0 | 96 |  |  | 11/26/2025 | Connected |  | N
National Grid | BROOKFIELD | 198546 | 01506 | 7.6 |  |  | Solar |  | 05_14_21L3 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 671315 | 01604 | 7.6 |  |  | Solar |  | 05_14_55L2 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 660639 | 01772 | 7.6 |  |  | Solar |  | 05_14_6J5 | 12/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | SALEM | 661689 | 01970 | 5.76 |  |  | Solar |  | 05_14_78L9 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/27/2024 | 2/28/2026 | Y | EXP | 365 | 10/02/2025 | 10/29/2025 | 28 | 0 | 28 |  |  | 12/2/2025 | Connected |  | N
National Grid | LOWELL | 431629 | 01854 | 11.4 |  |  | Solar |  | 05_01_227W1 | 07/13/2022 | 07/15/2022 | 2 | 0 | 2 | 07/18/2022 | 07/18/2022 | 62 | 42 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 594064 | 01845 | 7.6 |  |  | Solar |  | 05_01_406L3 | 03/06/2024 | 03/12/2024 | 4 | 0 | 4 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | LAWRENCE | 177614 | 01841 | 1000 |  |  | Solar |  | 05_01_552L3 | 09/22/2017 | 10/09/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2017 | 10/31/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 | 09/22/2017 | 12/21/2020 | Y | STD | 644 | 05/20/2020 | 09/11/2020 | 115 | 5 | 110 |  |  | 12/14/2020 | Connected |  | N
National Grid | DRACUT | 174157 | 01826 | 2016 |  |  | Natural Gas |  | 05_01_HT41 | 04/24/2012 | 04/24/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 05/13/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2012 |  | 12/31/2016 | N | STD | 1482 |  |  | 0 | 0 | 0 |  |  | 7/14/2017 | Connected |  | N
National Grid | LANCASTER | 706145 | 01523 | 15.356 |  |  | Solar |  | 05_05_310W6 | 07/24/2025 | 07/31/2025 | 5 | 1 | 4 | 08/01/2025 | 08/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 07/24/2025 | 9/9/2026 | Y | EXP | 365 | 10/04/2025 |  | 90 | 0 | 90 |  |  | 11/24/2025 | Connected |  | N
National Grid | CHARLTON | 670878 | 01507 | 7.6 |  |  | Solar |  | 05_12_3J901 | 02/07/2025 | 03/13/2025 | 13 | 9 | 4 | 03/14/2025 | 03/14/2025 | 117 | 100 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 305218 | 01506 | 10 |  |  | Solar |  | 05_14_21L3 | 08/31/2020 | 09/03/2020 | 2 | 0 | 2 | 09/04/2020 | 09/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/31/2020 | 8/2/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2021 | Connected |  | N
National Grid | WORCESTER | 567932 | 01606 | 60 |  |  | Solar |  | 05_14_56L1 | 06/04/2024 | 07/02/2024 | 19 | 12 | 7 | 07/03/2024 | 07/03/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBOROUGH | 664939 | 01772 | 5.76 |  |  | Solar |  | 05_14_6J5 | 01/10/2025 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/10/2025 | 3/11/2026 | Y | EXP | 365 | 04/29/2025 | 05/06/2025 | 8 | 0 | 8 |  |  | 6/17/2025 | Connected |  | Y
National Grid | SALEM | 686572 | 01970 | 4.8 |  |  | Solar |  | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | LOWELL | 441594 | 01854 | 0 |  |  | Other |  | 05_01_227W1 | 09/20/2022 | 10/20/2022 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 594844 | 01845 | 6 |  |  | Solar |  | 05_01_406L3 | 03/06/2024 | 03/26/2024 | 15 | 12 | 3 | 03/27/2024 | 03/27/2024 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 03/06/2024 | 4/30/2025 | Y | EXP | 365 | 06/11/2024 | 08/19/2024 | 70 | 0 | 70 |  |  | 8/20/2024 | Connected |  | N
National Grid | LAWRENCE | 177893 | 01841 | 2490 |  |  | Solar |  | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 |  | 7/9/2020 | N | STD | 685 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 321061 | 01826 | 75 |  |  | Natural Gas |  | 05_01_HT41 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 403 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | SHIRLEY | 659021 | 01464 | 0 |  |  | Other |  | 05_05_311W1 | 03/31/2025 | 06/18/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2025 | 07/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | OXFORD | 668521 | 01540 | 3.8 |  |  | Solar |  | 05_12_3J903 | 01/29/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/29/2025 | 6/2/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  |  | Completion Documents |  | N
National Grid | BROOKFIELD | 330497 | 01515 | 3.8 |  |  | Solar |  | 05_14_21L3 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/21/2020 | 9/26/2022 | Y | EXP | 365 | 08/25/2021 | 10/05/2021 | 36 | 0 | 36 |  |  | 6/15/2022 | Connected |  | N
National Grid | WORCESTER | 726653 | 01610 | 11.5 |  |  | Solar |  | 05_14_56L1 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 177071 | 01752 | 90 |  |  | Solar |  | 05_14_6J6 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/25/2017 | 4/25/2017 | 4/25/2017 | Connected |  | N
National Grid | LYNN | 686563 | 01902 | 7.6 |  |  | Solar |  | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 50 | 36 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | LOWELL | 477515 | 01854 | 15.2 |  |  | Solar |  | 05_01_227W1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | ANDOVER | 635916 | 01845 | 6 |  |  | Solar |  | 05_01_406L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/8/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | LAWRENCE | 177892 | 01841 | 4200 |  |  | Solar |  | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 | 04/13/2017 | 6/7/2021 | Y | STD | 685 | 09/23/2020 | 04/14/2021 | 203 | 0 | 203 |  |  | 6/4/2021 | Connected |  | N
National Grid | DRACUT | 174618 | 01826 | 200 |  |  | Solar |  | 05_01_HT42 | 02/07/2011 | 02/07/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2011 | 02/07/2011 | 1/11/2012 | Y | EXP | 245 | 08/02/2011 | 01/28/2012 | 122 | 0 | 122 | 8/3/2012 | 8/3/2012 | 1/11/2012 | Connected |  | N
National Grid | LEOMINSTER | 730626 | 01453 | 10 |  |  | Solar |  | 05_05_311W1 | 11/11/2025 | 11/21/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | OXFORD | 349185 | 01540 | 7.6 |  |  | Solar |  | 05_12_3J903 | 04/28/2021 | 05/03/2021 | 2 | 0 | 2 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 406690 | 01515 | 43.2 |  |  | Solar |  | 05_14_21L3 | 01/19/2022 | 01/21/2022 | 3 | 1 | 2 | 01/24/2022 | 01/24/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 3/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | WORCESTER | 725726 | 01610 | 46 |  |  | Solar |  | 05_14_56L1 | 11/12/2025 | 11/14/2025 | 2 | 1 | 1 | 11/17/2025 | 11/17/2025 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 600180 | 01772 | 6 |  |  | Solar |  | 05_14_6J6 | 04/06/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2024 | Connected |  | N
National Grid | LYNN | 246224 | 01902 | 7.6 |  |  | Solar |  | 05_14_7J1 | 08/12/2019 | 08/28/2019 | 12 | 11 | 1 | 08/29/2019 | 08/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  | 2/26/2020 | N | EXP | 168 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | LOWELL | 504134 | 01854 | 7.6 |  |  | Solar |  | 05_01_227W1 | 02/23/2023 |  | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 636073 | 01845 | 7.6 |  |  | Solar |  | 05_01_406L3 | 08/28/2024 | 10/10/2024 | 17 | 13 | 4 | 10/11/2024 | 10/11/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177945 | 01841 | 42.3 |  |  | Solar |  | 05_01_552L3 | 08/21/2017 | 08/21/2017 | 57 | 49 | 8 | 11/20/2017 | 11/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 |  | 8/26/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | DRACUT | 177587 | 01826 | 300 |  |  | Natural Gas |  | 05_01_HT45 | 05/17/2017 | 05/17/2017 | 18 | 15 | 3 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 5/23/2018 | N | EXP | 320 |  |  | 0 | 0 | 0 | 4/12/2018 | 4/12/2018 | 4/12/2018 | Connected |  | N
National Grid | LEOMINSTER | 175172 | 01453 | 85 |  |  | Solar |  | 05_05_311W1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 | 12/05/2012 | 12/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2013 | 11/16/2012 | 4/1/2013 | Y | EXP | 39 |  |  | 0 | 0 | 0 | 2/21/2013 | 2/21/2013 | 7/12/2013 | Connected |  | N
National Grid | OXFORD | 584871 | 01540 | 7.6 |  |  | Solar |  | 05_12_3J903 | 02/01/2024 | 02/16/2024 | 12 | 10 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 409499 | 01535 | 6 |  |  | Solar |  | 05_14_21L3 | 04/12/2022 |  | 63 | 27 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 738785 | 01603 | 0 |  |  | Battery Add-On |  | 05_14_56L1 | 12/08/2025 | 12/11/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 646983 | 01752 | 7.6 |  |  | Solar |  | 05_14_6J6 | 11/22/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/22/2024 | 1/28/2026 | Y | EXP | 365 | 08/26/2025 | 09/17/2025 | 23 | 0 | 23 |  |  | 9/23/2025 | Connected |  | N
National Grid | LYNN | 663217 | 01902 | 11.5 |  |  | Solar |  | 05_14_7J1 | 01/02/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | LOWELL | 532473 | 01854 | 15.2 |  |  | Solar |  | 05_01_227W1 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2023 | Connected |  | N
National Grid | ANDOVER | 637279 | 01845 | 6 |  |  | Solar |  | 05_01_406L3 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | LAWRENCE | 178060 | 01841 | 4980 |  |  | Solar |  | 05_01_552L3 | 09/01/2017 | 09/21/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2017 | 11/03/2017 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 | 09/01/2017 | 7/6/2021 | Y | STD | 708 | 04/02/2020 | 09/11/2020 | 163 | 5 | 158 |  |  | 7/6/2021 | Connected |  | N
National Grid | DRACUT | 265164 | 01826 | 125 |  |  | Natural Gas |  | 05_01_HT46 | 08/10/2020 | 09/16/2020 | 26 | 20 | 6 |  |  | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 177943 | 01464 | 333.2 |  |  | Solar |  | 05_05_311W1 | 08/18/2017 | 08/18/2017 | 127 | 91 | 36 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2018 | 08/18/2017 | 2/10/2021 | Y | EXP | 680 |  |  | 0 | 0 | 0 |  |  | 2/10/2021 | Connected |  | N
National Grid | OXFORD | 584595 | 01540 | 5 |  |  | Solar |  | 05_12_3J903 | 02/09/2024 | 02/12/2024 | 2 | 1 | 1 | 02/13/2024 | 02/13/2024 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 02/09/2024 | 4/23/2025 | Y | EXP | 365 | 08/21/2024 | 10/10/2024 | 51 | 0 | 51 |  |  | 10/4/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 493495 | 01535 | 16680 |  |  | Hydro |  | 05_14_21L3 | 01/19/2023 | 04/17/2023 | 60 | 51 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 06/05/2023 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174528 | 01603 | 500 |  |  | Solar |  | 05_14_56L1 | 08/09/2011 | 08/09/2011 | 29 | 0 | 29 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2011 |  | 12/31/2016 | N | EXP | 1915 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 500858 | 01752 | 60 |  |  | Solar |  | 05_14_6J8 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176081 | 01902 | 27 |  |  | Solar |  | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 589295 | 01854 | 14.21 |  |  | Solar |  | 05_01_227W1 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | ANDOVER | 638781 | 01845 | 5.76 |  |  | Solar |  | 05_01_406L3 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/09/2024 | 3/5/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/1/2025 | Connected |  | N
National Grid | LAWRENCE | 178157 | 01841 | 990 |  |  | Solar |  | 05_01_552L3 | 12/22/2017 | 02/05/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/28/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 12/31/2018 | N | STD | 174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 372126 | 01845 | 100 |  |  | Solar |  | 05_01_HT46 | 07/28/2021 | 11/08/2021 | 71 | 62 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 196371 | 01523 | 100 |  |  | Solar |  | 05_05_311W1 | 09/19/2018 | 10/05/2018 | 7 | 0 | 7 | 10/08/2018 | 10/08/2018 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  | 6/1/2020 | N | EXP | 530 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 592529 | 01540 | 3.8 |  |  | Solar |  | 05_12_3J903 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | SPENCER | 537411 | 01562 | 10 |  |  | Solar |  | 05_14_21L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 290152 | 01606 | 10 |  |  | Solar |  | 05_14_56L1 | 05/01/2020 | 05/04/2020 | 0 | 0 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | MARLBOROUGH | 550550 | 01752 | 200 |  |  | Solar |  | 05_14_6J8 | 08/25/2023 | 09/08/2023 | 9 | 1 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 | 08/25/2023 | 6/1/2026 | Y | STD | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176110 | 01902 | 27 |  |  | Solar |  | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 591793 | 01854 | 15.2 |  |  | Solar |  | 05_01_227W1 | 02/21/2024 | 03/14/2024 | 16 | 11 | 5 | 03/15/2024 | 03/15/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 644256 | 01845 | 5.76 |  |  | Solar |  | 05_01_406L3 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 03/01/2025 | 03/20/2025 | 12 | 0 | 12 |  |  | 4/7/2025 | Connected |  | N
National Grid | LAWRENCE | 178194 | 01841 | 2450 |  |  | Solar |  | 05_01_552L3 | 01/03/2018 | 02/01/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 04/17/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 01/03/2018 | 3/20/2020 | Y | STD | 423 | 12/06/2019 | 02/19/2020 | 75 | 0 | 75 |  |  | 3/16/2020 | Connected |  | N
National Grid | ANDOVER | 177605 | 01845 | 1530.048 |  |  | Solar |  | 05_01_HT48 | 09/19/2017 | 02/26/2018 | 102 | 102 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 06/22/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 | 09/19/2017 | 8/27/2025 | Y | STD | 156 | 10/12/2023 | 08/14/2025 | 672 | 3 | 669 |  |  | 8/28/2025 | Connected |  | N
National Grid | LANCASTER | 233077 | 01523 | 25 |  |  | Solar |  | 05_05_311W1 | 06/19/2019 | 06/20/2019 | 1 | 1 | 0 | 06/21/2019 | 06/21/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | OXFORD | 599564 | 01540 | 3.8 |  |  | Solar |  | 05_12_3J903 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/04/2024 | 7/21/2025 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | BROOKFIELD | 588627 | 01515 | 15 |  |  | Solar |  | 05_14_21L3 | 02/12/2024 | 03/06/2024 | 17 | 15 | 2 | 03/07/2024 | 03/07/2024 | 11 | 8 | 3 | 08/28/2024 | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 9/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 339459 | 01609 | 0 |  |  | Battery Add-On |  | 05_14_56L1 | 01/29/2021 | 02/01/2021 | 0 | 0 | 0 | 02/02/2021 | 02/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2021 |  | 3/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | MARLBOROUGH | 579731 | 01752 | 7.6 |  |  | Solar |  | 05_14_6J8 | 12/29/2023 | 01/16/2024 | 11 | 8 | 3 | 01/17/2024 | 01/17/2024 | 33 | 12 | 21 | 04/24/2024 | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/9/2025 | N | EXP | 365 | 05/16/2024 | 06/12/2024 | 28 | 0 | 28 |  |  | 7/6/2024 | Connected |  | N
National Grid | LYNN | 176421 | 01902 | 25 |  |  | Solar |  | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 2/29/2016 | 2/29/2016 | 3/28/2016 | Connected |  | N
National Grid | LOWELL | 598492 | 01852 | 20 |  |  | Solar |  | 05_01_227W1 | 03/21/2024 | 04/02/2024 | 8 | 6 | 2 | 04/03/2024 | 04/03/2024 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | ANDOVER | 644606 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/03/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 178267 | 01841 | 4980 |  |  | Solar |  | 05_01_552L3 | 01/08/2018 | 01/08/2018 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/10/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178456 | 01845 | 496 |  |  | Solar |  | 05_01_HT48 | 11/30/2017 | 11/30/2017 | 34 | 12 | 22 |  |  | 51 | 0 | 51 | 03/19/2018 | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 251090 | 01464 | 75 |  |  | Natural Gas |  | 05_05_311W1 | 12/06/2019 | 12/26/2019 | 12 | 7 | 5 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 12/06/2019 | 6/2/2022 | Y | STD | 323 | 08/21/2021 | 03/21/2022 | 213 | 21 | 192 |  |  | 5/5/2022 | Connected |  | Y
National Grid | OXFORD | 625884 | 01540 | 5.76 |  |  | Solar |  | 05_12_3J903 | 07/18/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | NORTH BROOKFIELD | 600344 | 01535 | 3.8 |  |  | Solar |  | 05_14_21L3 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 04/05/2024 | 5/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | WORCESTER | 451464 | 01609 | 50 |  |  | Solar |  | 05_14_56L1 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 594507 | 01752 | 3.8 |  |  | Solar |  | 05_14_6J8 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176450 | 01902 | 27 |  |  | Solar |  | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/28/2016 | 3/28/2016 | 3/1/2016 | Connected |  | N
National Grid | LOWELL | 623849 | 01854 | 7.6 |  |  | Solar |  | 05_01_227W1 | 07/10/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 644594 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 10/02/2024 | 11/04/2024 | 4 | 0 | 4 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | LAWRENCE | 178307 | 01841 | 996 |  |  | Solar |  | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 724047 | 01845 | 67.3 |  |  | Solar |  | 05_01_HT5 | 10/03/2025 | 10/27/2025 | 15 | 8 | 7 | 10/28/2025 | 10/28/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHIRLEY | 287875 | 01464 | 17.7 |  |  | Solar |  | 05_05_311W1 | 04/15/2020 | 06/03/2020 | 8 | 7 | 1 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N
National Grid | CHARLTON | 644776 | 01507 | 3.8 |  |  | Solar |  | 05_12_3J903 | 10/03/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 601226 | 01562 | 5 |  |  | Solar |  | 05_14_21L3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/09/2024 | 4/23/2025 | Y | EXP | 365 | 05/22/2024 | 07/23/2024 | 63 | 0 | 63 |  |  | 8/21/2024 | Connected |  | N
National Grid | WORCESTER | 378880 | 01606 | 15.2 |  |  | Solar |  | 05_14_56L1 | 08/30/2021 | 08/31/2021 | 1 | 0 | 1 | 09/01/2021 | 09/01/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 637388 | 01752 | 7.6 |  |  | Solar |  | 05_14_6J8 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177511 | 01902 | 27 |  |  | Solar |  | 05_14_7J3 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 7/17/2017 | N | EXP | 370 |  |  | 0 | 0 | 0 | 7/12/2016 | 7/12/2016 | 7/25/2016 | Connected |  | N
National Grid | LOWELL | 631955 | 01854 | 15.2 |  |  | Solar |  | 05_01_227W1 | 08/23/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | ANDOVER | 656827 | 01845 | 7.6 |  |  | Solar |  | 05_01_406L3 | 12/12/2024 | 12/16/2024 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 12/12/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | LAWRENCE | 178304 | 01841 | 2780 |  |  | Solar |  | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 1/15/2019 | N | STD | 203 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175132 | 01845 | 75 |  |  | Solar |  | 05_01_HT50 | 11/06/2012 | 11/06/2012 | 7 | 7 | 0 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2013 |  | 1/31/2013 | N | EXP | -6 | 03/14/2013 | 04/24/2013 | 27 | 0 | 27 | 2/20/2014 | 2/20/2014 | 4/2/2014 | Connected |  | N
National Grid | LANCASTER | 389739 | 01523 | 0 |  |  | Other |  | 05_05_311W1 | 11/10/2021 | 01/05/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 657446 | 01507 | 13.775 |  |  | Solar |  | 05_12_3J903 | 11/27/2024 | 12/24/2024 | 11 | 7 | 4 | 12/26/2024 | 12/26/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 617219 | 01535 | 7.6 |  |  | Solar |  | 05_14_21L3 | 06/11/2024 | 06/28/2024 | 3 | 0 | 3 | 07/01/2024 | 07/01/2024 | 18 | 8 | 10 | 08/16/2024 | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/23/2024 | 06/11/2024 |  | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 473878 | 01605 | 22.8 |  |  | Solar |  | 05_14_56L1 | 11/02/2022 | 11/03/2022 | 1 | 0 | 1 | 11/04/2022 | 11/04/2022 | 325 | 266 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 673283 | 01752 | 6.825 |  |  | Solar |  | 05_14_6J8 | 02/20/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | LYNN | 332646 | 01902 | 7.6 |  |  | Solar |  | 05_14_7J4 | 01/06/2021 | 01/11/2021 | 2 | 0 | 2 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 644731 | 01854 | 5.76 |  |  | Solar |  | 05_01_227W1 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | ANDOVER | 667517 | 01845 | 17.3 |  |  | Solar |  | 05_01_406L3 | 01/28/2025 | 02/21/2025 | 18 | 14 | 4 | 02/24/2025 | 02/24/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | LAWRENCE | 178483 | 01841 | 4999 |  |  | Solar |  | 05_01_552L3 | 04/03/2018 | 04/05/2018 | 18 | 18 | 0 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177349 | 01845 | 88 |  |  | Solar |  | 05_01_HT50 | 11/23/2016 | 11/23/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2016 | 12/05/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 12/3/2017 | N | STD | -206 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 586186 | 01464 | 150 |  |  | Solar |  | 05_05_311W1 | 02/01/2024 | 03/25/2024 | 36 | 28 | 8 | 03/26/2024 | 03/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 670620 | 01507 | 7.6 |  |  | Solar |  | 05_12_3J903 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 632778 | 01535 | 10 |  |  | Solar |  | 05_14_21L3 | 08/14/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N
National Grid | WORCESTER | 604257 | 01609 | 23 |  |  | Solar |  | 05_14_56L1 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 81 | 56 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 547089 | 01752 | 240 |  |  | Solar |  | 05_14_70L1 | 12/12/2023 | 02/05/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2024 | 02/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 | 12/12/2023 | 6/9/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LYNN | 200995 | 01902 | 7.6 |  |  | Solar |  | 05_14_7L1 | 11/14/2018 | 01/09/2019 | 39 | 37 | 2 | 01/10/2019 | 01/10/2019 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  | 1/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | LOWELL | 645128 | 01854 | 7.6 |  |  | Solar |  | 05_01_227W1 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | ANDOVER | 677208 | 01845 | 10 |  |  | Solar |  | 05_01_406L3 | 03/11/2025 | 03/22/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/11/2025 | 5/29/2026 | Y | EXP | 365 | 07/22/2025 | 07/22/2025 | 1 | 0 | 1 |  |  | 8/13/2025 | Connected |  | N
National Grid | METHUEN | 205262 | 01844 | 7.6 |  |  | Solar |  | 05_01_552L3 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2019 | Connected |  | N
National Grid | ANDOVER | 592110 | 01845 | 60 |  |  | Solar |  | 05_01_HT52 | 03/11/2024 | 03/20/2024 | 8 | 2 | 6 | 03/21/2024 | 03/21/2024 | 154 | 140 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 656819 | 01523 | 10 |  |  | Solar |  | 05_05_311W1 | 11/25/2024 | 02/27/2025 | 40 | 37 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 676181 | 01540 | 15.2 |  |  | Solar |  | 05_12_3J903 | 03/06/2025 | 04/18/2025 | 31 | 28 | 3 | 04/22/2025 | 04/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 639539 | 01535 | 3.8 |  |  | Solar |  | 05_14_21L3 | 09/11/2024 | 10/22/2024 | 26 | 23 | 3 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/11/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WORCESTER | 659758 | 01608 | 23 |  |  | Solar |  | 05_14_56L1 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 701468 | 01752 | 10.725 |  |  | Solar |  | 05_14_70L1 | 06/26/2025 | 09/03/2025 | 12 | 10 | 2 | 09/04/2025 | 09/04/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | LYNN | 301380 | 01902 | 3.8 |  |  | Solar |  | 05_14_7L1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/31/2020 | 5/20/2021 | Y | EXP | 365 | 12/11/2020 | 01/04/2021 | 23 | 0 | 23 |  |  | 5/11/2021 | Connected |  | N
National Grid | LOWELL | 660768 | 01854 | 5.76 |  |  | Solar |  | 05_01_227W1 | 12/16/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/16/2024 | 3/11/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | ANDOVER | 683569 | 01845 | 15.2 |  |  | Solar |  | 05_01_406L3 | 04/08/2025 | 04/10/2025 | 2 | 0 | 2 | 04/11/2025 | 04/11/2025 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/08/2025 | 6/9/2026 | Y | EXP | 365 | 09/19/2025 | 10/27/2025 | 39 | 0 | 39 |  |  | 10/29/2025 | Connected |  | N
National Grid | LAWRENCE | 211642 | 01841 | 4980 |  |  | Solar |  | 05_01_552L3 | 02/27/2019 | 04/02/2019 | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2019 | 04/24/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175078 | 01845 | 200 |  |  | Solar |  | 05_01_HT55 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2013 |  | 12/5/2016 | N | EXP | 1141 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/5/2016 | Connected |  | N
National Grid | LUNENBURG | 661545 | 01462 | 10 |  |  | Solar |  | 05_05_311W1 | 12/30/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/30/2024 | 6/5/2026 | Y | EXP | 365 | 08/21/2025 |  | 134 | 0 | 134 |  |  | 12/9/2025 | Connected |  | N
National Grid | OXFORD | 176236 | 01540 | 15 |  |  | Solar |  | 05_12_40J2 | 02/17/2015 | 02/17/2015 | 5 | 0 | 5 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2015 |  | 6/30/2015 | N | EXP | 124 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 7/2/2015 | Connected |  | N
National Grid | BROOKFIELD | 655534 | 01515 | 3.8 |  |  | Solar |  | 05_14_21L3 | 11/19/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WORCESTER | 661777 | 01608 | 5.76 |  |  | Solar |  | 05_14_56L1 | 12/19/2024 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 727534 | 01752 | 5.8 |  |  | Solar |  | 05_14_70L1 | 10/18/2025 | 10/23/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LYNN | 409895 | 01902 | 7.6 |  |  | Solar |  | 05_14_7L1 | 04/14/2022 | 04/21/2022 | 5 | 4 | 1 | 04/22/2022 | 04/22/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 661472 | 01854 | 10 |  |  | Solar |  | 05_01_227W1 | 12/18/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 | 07/10/2025 | 29 | 0 | 29 |  |  | 7/17/2025 | Connected |  | N
National Grid | ANDOVER | 684312 | 01845 | 15.2 |  |  | Solar |  | 05_01_406L3 | 04/10/2025 | 04/14/2025 | 2 | 0 | 2 | 04/15/2025 | 04/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | TEWKSBURY | 289954 | 01876 | 0 |  |  | Other |  | 05_01_552L3 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 27 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 174174 | 01952 | 135 |  |  | Solar |  | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/20/2012 | N | EXP | -114 |  |  | 0 | 0 | 0 | 6/12/2015 | 6/12/2015 | 3/2/2013 | Connected |  | N
National Grid | SHIRLEY | 662117 | 01464 | 5.76 |  |  | Solar |  | 05_05_311W1 | 12/21/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | OXFORD | 177497 | 01540 | 15.2 |  |  | Solar |  | 05_12_40J2 | 12/14/2016 | 12/14/2016 | 4 | 3 | 1 | 12/20/2016 | 12/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/14/2016 | 10/12/2018 | Y | EXP | 660 | 05/28/2016 | 02/03/2017 | 169 | 3 | 166 |  |  | 10/3/2018 | Connected |  | N
National Grid | BROOKFIELD | 666729 | 01506 | 7.6 |  |  | Solar |  | 05_14_21L3 | 01/20/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 4/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | WORCESTER | 693032 | 01605 | 13.05 |  |  | Solar |  | 05_14_56L1 | 05/20/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175483 | 01752 | 4999 |  |  | Solar |  | 05_14_70L1 | 03/14/2014 | 03/14/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2014 | 05/14/2014 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 440658 | 01902 | 7.6 |  |  | Solar |  | 05_14_7L1 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/29/2022 | 8/30/2023 | Y | EXP | 365 | 11/02/2022 | 11/08/2022 | 7 | 0 | 7 |  |  | 11/10/2022 | Connected |  | N
National Grid | DRACUT | 667845 | 01826 | 10 |  |  | Solar |  | 05_01_227W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 69 | 49 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 685072 | 01845 | 23 |  |  | Solar |  | 05_01_406L3 | 04/15/2025 | 05/08/2025 | 16 | 12 | 4 | 05/09/2025 | 05/09/2025 | 52 | 30 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 04/15/2025 | 8/6/2026 | Y | EXP | 365 | 09/19/2025 | 10/07/2025 | 19 | 0 | 19 |  |  | 10/8/2025 | Connected |  | N
National Grid | TEWKSBURY | 290420 | 01876 | 0 |  |  | Other |  | 05_01_552L3 | 10/27/2020 | 12/22/2020 | 38 | 30 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2020 | 01/19/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 174173 | 01952 | 75 |  |  | Solar |  | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 5/15/2012 | N | EXP | -211 |  |  | 0 | 0 | 0 | 2/6/2013 | 2/6/2013 | 3/2/2013 | Connected |  | N
National Grid | LEOMINSTER | 663953 | 01453 | 10 |  |  | Solar |  | 05_05_311W2 | 01/06/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | OXFORD | 320446 | 01540 | 8 |  |  | Solar |  | 05_12_40J2 | 10/20/2020 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 649096 | 01535 | 11.5 |  |  | Solar |  | 05_14_24L1 | 10/24/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 10/24/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 704185 | 01605 | 15.76 |  |  | Solar |  | 05_14_56L1 | 07/16/2025 | 07/18/2025 | 2 | 0 | 2 | 07/21/2025 | 07/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175480 | 01752 | 4999 |  |  | Solar |  | 05_14_70L1 | 03/21/2014 | 03/21/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2014 | 05/14/2014 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/21/2014 | 3/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 628133 | 01966 | 7.6 |  |  | Solar |  | 05_14_7L1 | 07/30/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 683029 | 01854 | 3.8 |  |  | Solar |  | 05_01_227W1 | 04/04/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/04/2025 | 6/24/2026 | Y | EXP | 365 | 09/03/2025 | 10/28/2025 | 56 | 0 | 56 |  |  | 11/4/2025 | Connected |  | N
National Grid | ANDOVER | 384307 | 01845 | 75 |  |  | Solar |  | 05_01_406L4 | 10/13/2021 | 11/17/2021 | 24 | 14 | 10 |  |  | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BILLERICA | 366176 | 01862 | 10 |  |  | Solar |  | 05_01_552L3 | 07/30/2021 | 08/05/2021 | 5 | 2 | 3 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  | 10/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2021 | Connected |  | N
National Grid | SALISBURY | 674157 | 01952 | 84.6 |  |  | Solar |  | 05_01_HT6 | 03/11/2025 |  | 99 | 48 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 667325 | 01523 | 14.625 |  |  | Solar |  | 05_05_311W2 | 01/29/2025 | 02/05/2025 | 0 | 0 | 0 | 12/11/2025 | 12/11/2025 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 336432 | 01507 | 7.44 |  |  | Solar |  | 05_12_40J2 | 01/12/2021 | 01/13/2021 | 0 | 0 | 0 | 01/14/2021 | 01/14/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/12/2021 | 1/12/2022 | Y | EXP | 365 | 04/21/2021 | 04/20/2021 | 0 | 0 | 0 |  |  | 5/25/2021 | Connected |  | N
National Grid | SPENCER | 731515 | 01562 | 15.2 |  |  | Solar |  | 05_14_24L1 | 11/05/2025 | 11/10/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 688268 | 01602 | 20 |  |  | Solar |  | 05_14_56L2 | 05/01/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MARLBOROUGH | 176006 | 01752 | 7.6 |  |  | Solar |  | 05_14_70L1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 375 | 0 | 375 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 718084 | 01966 | 9.6 |  |  | Solar |  | 05_14_7L2 | 09/10/2025 | 10/01/2025 | 1 | 0 | 1 | 10/08/2025 | 10/08/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 688672 | 01854 | 12.16 |  |  | Solar |  | 05_01_227W1 | 05/07/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | ANDOVER | 647870 | 01845 | 5.76 |  |  | Solar |  | 05_01_406L4 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 376647 | 01862 | 3.8 |  |  | Solar |  | 05_01_552L3 | 09/16/2021 | 10/12/2021 | 18 | 17 | 1 | 10/13/2021 | 10/13/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 10/11/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 175192 | 01952 | 150 |  |  | Natural Gas |  | 05_01_HT61 | 11/21/2013 | 11/21/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2013 |  | 3/31/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 | 6/2/2014 | 6/2/2014 | 6/2/2014 | Connected |  | Y
National Grid | LEOMINSTER | 742966 | 01453 | 7.6 |  |  | Solar |  | 05_05_311W2 | 01/02/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | OXFORD | 376072 | 01540 | 10 |  |  | Solar |  | 05_12_40J2 | 09/02/2021 | 09/02/2021 | 12 | 10 | 2 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2021 | 09/02/2021 | 1/28/2023 | Y | EXP | 365 | 12/10/2021 | 01/27/2022 | 49 | 0 | 49 |  |  | 1/31/2022 | Connected |  | N
National Grid | NORTH BROOKFIELD | 740250 | 01535 | 10 |  |  | Solar |  | 05_14_24L1 | 12/16/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 733362 | 01602 | 20 |  |  | Solar |  | 05_14_56L2 | 11/12/2025 | 11/18/2025 | 4 | 0 | 4 | 11/19/2025 | 11/19/2025 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 176041 | 01752 | 11.4 |  |  | Solar |  | 05_14_70L1 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/22/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | ROCKPORT | 730322 | 01966 | 3.8 |  |  | Solar |  | 05_14_7L2 | 10/31/2025 | 11/05/2025 | 3 | 0 | 3 | 11/06/2025 | 11/06/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 345461 | 01824 | 800 |  |  | Solar |  | 05_01_227W3 | 04/07/2021 | 11/15/2021 | 127 | 122 | 5 |  |  | 101 | 64 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 713750 | 01845 | 17.6 |  |  | Solar |  | 05_01_406L4 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 78 | 51 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 447837 | 01862 | 7.25 |  |  | Solar |  | 05_01_552L3 | 08/24/2022 | 08/30/2022 | 4 | 0 | 4 | 08/31/2022 | 08/31/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 175436 | 01952 | 150 |  |  | Natural Gas |  | 05_01_HT61 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 | 12/03/2014 | 12/03/2014 | 0 | 0 | 0 | 09/10/2015 | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 |  | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 12/31/2016 | N | EXP | 283 |  |  | 0 | 0 | 0 | 4/26/2016 | 4/26/2016 | 5/5/2016 | Connected |  | Y
National Grid | LEOMINSTER | 176966 | 01453 | 6 |  |  | Solar |  | 05_05_311W2 | 10/03/2016 | 10/03/2016 | 0 | 0 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 10/03/2016 | 5/12/2017 | Y | EXP | 213 | 11/22/2016 | 11/23/2016 | 1 | 0 | 1 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | OXFORD | 398018 | 01540 | 5.52 |  |  | Solar |  | 05_12_40J2 | 11/29/2021 | 11/30/2021 | 1 | 1 | 0 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 12/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2022 | Connected |  | N
National Grid | NORTH BROOKFIELD | 175186 | 01535 | 335 |  |  | Solar |  | 05_14_24L1 | 11/18/2013 | 11/18/2013 | 1 | 0 | 1 | 11/20/2013 | 11/20/2013 | 494 | 0 | 494 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2013 |  | 4/30/2014 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 735129 | 01609 | 15.04 |  |  | Solar |  | 05_14_56L2 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 176226 | 01752 | 10 |  |  | Solar |  | 05_14_70L1 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 174732 | 01966 | 32.9 |  |  | Solar |  | 05_14_7L2 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 | 01/04/2013 | 3/29/2013 | Y | EXP | 11 |  |  | 0 | 0 | 0 | 4/17/2013 | 4/17/2013 | 8/15/2013 | Connected |  | Y
National Grid | CHELMSFORD | 394134 | 01824 | 700 |  |  | Solar |  | 05_01_227W3 | 01/17/2022 | 05/24/2022 | 87 | 77 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2022 | 06/27/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ANDOVER | 715605 | 01845 | 20 |  |  | Solar |  | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 4 | 2 | 2 | 09/10/2025 | 09/10/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | TEWKSBURY | 547263 | 01876 | 10 |  |  | Solar |  | 05_01_552L3 | 09/07/2023 | 10/10/2023 | 23 | 22 | 1 | 10/11/2023 | 10/11/2023 | 5 | 0 | 5 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 176397 | 01952 | 2649 |  |  | Natural Gas |  | 05_01_HT61 | 03/10/2016 | 03/10/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2016 | 06/13/2016 | 60 | 44 | 16 |  |  | 0 | 0 | 0 | 10/04/2016 | 12/13/2016 | 47 | 13 | 34 | 1/25/2017 | 03/10/2016 | 1/31/2019 | Y | STD | 736 | 01/03/2018 | 07/26/2018 | 204 | 0 | 204 | 1/25/2018 | 1/25/2018 | 1/10/2019 | Connected |  | N
National Grid | SHIRLEY | 177011 | 01464 | 10 |  |  | Solar |  | 05_05_311W2 | 10/14/2016 | 10/14/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/14/2016 | 10/23/2017 | Y | EXP | 364 | 01/20/2017 | 03/02/2017 | 28 | 0 | 28 | 3/29/2017 | 3/29/2017 | 3/31/2017 | Connected |  | N
National Grid | OXFORD | 418962 | 01540 | 0 |  |  | Solar |  | 05_12_40J2 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  | 4/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2022 | Connected |  | N
National Grid | BROOKFIELD | 175755 | 01515 | 325 |  |  | Solar |  | 05_14_24L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 5/22/2015 | 5/22/2015 | 5/26/2015 | Connected |  | N
National Grid | WORCESTER | 174365 | 01605 | 7.5 |  |  | Solar |  | 05_14_56L2 | 05/21/2012 | 05/21/2012 | 8 | 0 | 8 | 06/05/2012 | 06/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2012 | 05/21/2012 | 8/1/2012 | Y | EXP | -106 | 10/04/2012 | 11/19/2012 | 15 | 0 | 15 | 11/15/2012 | 11/15/2012 | 11/15/2012 | Connected |  | N
National Grid | MARLBOROUGH | 176550 | 01752 | 10 |  |  | Solar |  | 05_14_70L1 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 357 | 09/06/2016 | 09/14/2016 | 6 | 0 | 6 | 12/7/2016 | 12/7/2016 | 12/7/2016 | Connected |  | N
National Grid | ROCKPORT | 177074 | 01966 | 10 |  |  | Solar |  | 05_14_7L2 | 08/03/2016 | 08/03/2016 | 1 | 1 | 0 | 08/05/2016 | 08/05/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2016 | 08/03/2016 | 8/9/2017 | Y | EXP | 363 | 10/17/2016 | 10/26/2016 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 434882 | 01824 | 2400 |  |  | Solar |  | 05_01_227W3 | 01/12/2023 | 04/25/2023 | 70 | 61 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2023 | 05/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 730948 | 01845 | 15.2 |  |  | Solar |  | 05_01_406L4 | 11/03/2025 | 11/07/2025 | 4 | 0 | 4 | 11/10/2025 | 11/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 547258 | 01862 | 10 |  |  | Solar |  | 05_01_552L3 | 09/07/2023 | 09/13/2023 | 4 | 3 | 1 | 09/14/2023 | 09/14/2023 | 23 | 0 | 23 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 11/19/2024 | N | EXP | 365 | 01/18/2024 | 03/07/2024 | 50 | 0 | 50 |  |  | 4/1/2024 | Connected |  | N
National Grid | SALISBURY | 419356 | 01952 | 240 |  |  | Solar |  | 05_05_106W42 | 05/26/2022 | 06/13/2022 | 11 | 3 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2023 | 05/26/2022 | 4/6/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SHIRLEY | 177457 | 01464 | 3.8 |  |  | Solar |  | 05_05_311W2 | 12/07/2016 | 12/07/2016 | 1 | 1 | 0 | 12/12/2016 | 12/12/2016 | 323 | 0 | 323 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/07/2016 | 12/30/2018 | Y | EXP | 745 | 12/27/2017 | 10/26/2018 | 303 | 0 | 303 |  |  | 10/26/2018 | Connected |  | N
National Grid | AUBURN | 420293 | 01501 | 10 |  |  | Solar |  | 05_12_40J2 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2022 | Connected |  | N
National Grid | BROOKFIELD | 176456 | 01515 | 7.6 |  |  | Solar |  | 05_14_24L1 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2016 |  | 12/14/2016 | N | EXP | 342 |  |  | 0 | 0 | 0 | 6/10/2016 | 6/10/2016 | 6/16/2016 | Connected |  | N
National Grid | WORCESTER | 175130 | 01608 | 12 |  |  | Solar |  | 05_14_56L2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 | 11/20/2012 | 11/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2013 |  | 2/15/2013 | N | EXP | -4 |  |  | 0 | 0 | 0 | 2/19/2013 | 2/19/2013 | 5/7/2013 | Connected |  | N
National Grid | MARLBOROUGH | 177569 | 01752 | 15.2 |  |  | Solar |  | 05_14_70L1 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 6/7/2018 | Connected |  | N
National Grid | ROCKPORT | 177273 | 01966 | 20 |  |  | Solar |  | 05_14_7L2 | 02/06/2017 | 02/06/2017 | 6 | 2 | 4 | 02/14/2017 | 02/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | CHELMSFORD | 644479 | 01824 | 160 |  |  | Solar |  | 05_01_227W3 | 10/02/2024 | 01/28/2025 | 77 | 67 | 10 | 01/29/2025 | 01/29/2025 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | ANDOVER | 738891 | 01845 | 10 |  |  | Solar |  | 05_01_406L4 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TEWKSBURY | 547266 | 01876 | 10 |  |  | Solar |  | 05_01_552L3 | 09/07/2023 | 10/06/2023 | 21 | 20 | 1 | 10/10/2023 | 10/10/2023 | 6 | 0 | 6 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 175293 | 01952 | 20 |  |  | Solar |  | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 |  | 2/27/2015 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/16/2015 | 4/16/2015 | 4/16/2015 | Connected |  | N
National Grid | SHIRLEY | 177786 | 01464 | 3.8 |  |  | Solar |  | 05_05_311W2 | 06/01/2017 | 06/01/2017 | 7 | 5 | 2 | 06/13/2017 | 06/13/2017 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/01/2017 | 12/28/2018 | Y | EXP | 563 |  |  | 0 | 0 | 0 |  |  | 10/26/2018 | Connected |  | N
National Grid | OXFORD | 442681 | 01540 | 5.8 |  |  | Solar |  | 05_12_40J2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 | 07/19/2022 | 4/23/2024 | Y | EXP | 365 | 12/22/2022 | 04/24/2023 | 124 | 0 | 124 |  |  | 4/27/2023 | Connected |  | N
National Grid | SPENCER | 176621 | 01562 | 7.6 |  |  | Solar |  | 05_14_24L1 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 08/16/2016 | 08/31/2016 | 11 | 0 | 11 | 3/1/2017 | 3/1/2017 | 3/1/2017 | Connected |  | N
National Grid | WORCESTER | 177954 | 01605 | 20 |  |  | Solar |  | 05_14_56L2 | 10/23/2017 | 10/23/2017 | 101 | 100 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177756 | 01752 | 324 |  |  | Solar |  | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 83 | 83 | 0 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 177398 | 01966 | 57.6 |  |  | Solar |  | 05_14_7L2 | 06/28/2016 | 06/28/2016 | 7 | 7 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2016 |  | 7/5/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 9/22/2016 | Connected |  | Y
National Grid | CHELMSFORD | 678660 | 01824 | 15.2 |  |  | Solar |  | 05_01_227W3 | 03/17/2025 | 03/25/2025 | 6 | 2 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 173764 | 01845 | 10 |  |  | Solar |  | 05_01_406L4 | 04/17/2018 | 04/17/2018 | 0 | 0 | 0 | 07/10/2018 | 07/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 561832 | 01862 | 10 |  |  | Solar |  | 05_01_552L3 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | SALISBURY | 175292 | 01952 | 20 |  |  | Solar |  | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 2/27/2015 | N | EXP | 80 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/17/2015 | Connected |  | N
National Grid | SHIRLEY | 178441 | 01464 | 5 |  |  | Solar |  | 05_05_311W2 | 04/02/2018 | 04/02/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 4/8/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 5/29/2019 | Connected |  | N
National Grid | OXFORD | 523300 | 01540 | 10 |  |  | Solar |  | 05_12_40J2 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 160 | 137 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | SPENCER | 176675 | 01562 | 10 |  |  | Solar |  | 05_14_24L1 | 01/04/2016 | 01/04/2016 | 1 | 1 | 0 | 01/06/2016 | 01/06/2016 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/10/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 178069 | 02721 | 20 |  |  | Solar |  | 05_14_56L2 | 10/30/2017 | 10/30/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 11/5/2018 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 10/16/2018 | Connected |  | N
National Grid | MARLBOROUGH | 177755 | 01752 | 396 |  |  | Solar |  | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 84 | 84 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 12/20/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 178230 | 01966 | 7.6 |  |  | Solar |  | 05_14_7L2 | 01/03/2018 | 01/03/2018 | 21 | 15 | 6 | 02/06/2018 | 02/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 1/10/2019 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 727101 | 01824 | 3.8 |  |  | Solar |  | 05_01_227W3 | 10/17/2025 | 11/03/2025 | 10 | 5 | 5 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 174250 | 01845 | 95 |  |  | Solar |  | 05_01_406L4 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 6/1/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 6/29/2012 | Connected |  | N
National Grid | BILLERICA | 562496 | 01862 | 5 |  |  | Solar |  | 05_01_552L3 | 10/20/2023 | 11/09/2023 | 14 | 11 | 3 | 11/13/2023 | 11/13/2023 | 21 | 0 | 21 | 12/21/2023 | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 |  | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 | 4/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 177918 | 01952 | 312 |  |  | Solar |  | 05_05_106W42 | 10/20/2017 | 10/20/2017 | 5 | 0 | 5 | 11/03/2017 | 11/03/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 |  | 10/28/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 8/3/2018 | Connected |  | N
National Grid | SHIRLEY | 178533 | 01464 | 110 |  |  | Solar |  | 05_05_311W2 | 12/05/2017 | 12/05/2017 | 26 | 9 | 17 | 01/16/2018 | 01/16/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 12/11/2018 | N | EXP | 306 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | OXFORD | 534135 | 01540 | 14.79 |  |  | Solar |  | 05_12_40J2 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 52 | 29 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | SPENCER | 177455 | 01562 | 10 |  |  | Solar |  | 05_14_24L1 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 362 | 10/03/2017 | 10/17/2017 | 9 | 0 | 9 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | FALL RIVER | 189257 | 02721 | 15.2 |  |  | Solar |  | 05_14_56L2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177965 | 01752 | 480 |  |  | Solar |  | 05_14_70L1 | 04/21/2017 | 04/21/2017 | 25 | 22 | 3 | 05/30/2017 | 05/30/2017 | 189 | 46 | 143 | 10/05/2017 | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 198767 | 01966 | 13.8 |  |  | Solar |  | 05_14_7L2 | 12/03/2018 | 12/13/2018 | 7 | 0 | 7 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 734559 | 01824 | 0 |  |  | Battery Add-On |  | 05_01_227W3 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 174261 | 01845 | 94.25 |  |  | Solar |  | 05_01_406L4 | 02/29/2012 | 02/29/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2012 |  | 6/1/2012 | N | EXP | -122 |  |  | 0 | 0 | 0 | 10/19/2012 | 10/19/2012 | 11/26/2012 | Connected |  | N
National Grid | BILLERICA | 570255 | 01862 | 10 |  |  | Solar |  | 05_01_552L3 | 12/18/2023 | 01/02/2024 | 9 | 7 | 2 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 | 12/18/2023 | 2/7/2025 | Y | EXP | 365 | 03/08/2024 | 05/17/2024 | 71 | 0 | 71 |  |  | 10/9/2024 | Connected |  | N
National Grid | SALISBURY | 178620 | 01952 | 144 |  |  | Solar |  | 05_05_106W42 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 2/7/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | SHIRLEY | 193822 | 01464 | 15.2 |  |  | Solar |  | 05_05_311W2 | 08/17/2018 |  | 82 | 26 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 551438 | 01540 | 10 |  |  | Solar |  | 05_12_40J2 | 11/16/2023 | 11/20/2023 | 2 | 0 | 2 | 11/21/2023 | 11/21/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2024 | Connected |  | N
National Grid | SPENCER | 177491 | 01562 | 330 |  |  | Solar |  | 05_14_24L1 | 12/12/2016 | 12/12/2016 | 3 | 3 | 0 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 | 03/21/2017 | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 |  | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 3/20/2019 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | Connected |  | N
National Grid | FALL RIVER | 284143 | 02721 | 12 |  |  | Solar |  | 05_14_56L2 | 03/17/2020 | 04/06/2020 | 13 | 13 | 0 | 04/07/2020 | 04/07/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178438 | 01752 | 7.6 |  |  | Solar |  | 05_14_70L1 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 3/12/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 213965 | 01966 | 0 |  |  | Solar |  | 05_14_7L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | CHELMSFORD | 742930 | 01824 |  |  |  | Battery Add-On |  | 05_01_227W3 | 01/02/2026 | 01/06/2026 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 174329 | 01845 | 1750 |  |  | Solar |  | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 9/1/2012 | Y | STD | -88 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 575455 | 01862 | 15.2 |  |  | Solar |  | 05_01_552L3 | 12/13/2023 | 01/04/2024 | 15 | 8 | 7 | 01/05/2024 | 01/05/2024 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | SALISBURY | 212413 | 01952 | 233.3 |  |  | Solar |  | 05_05_106W42 | 03/04/2019 | 03/15/2019 | 8 | 4 | 4 | 03/18/2019 | 03/18/2019 | 7 | 3 | 4 | 04/17/2019 | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 191496 | 01464 | 10 |  |  | Solar |  | 05_05_311W2 | 08/01/2018 | 08/21/2018 | 9 | 4 | 5 | 08/22/2018 | 08/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 562901 | 01537 | 9.86 |  |  | Solar |  | 05_12_40J2 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/01/2023 | 12/28/2024 | Y | EXP | 365 | 03/21/2024 | 04/03/2024 | 14 | 0 | 14 |  |  | 6/22/2024 | Connected |  | N
National Grid | SPENCER | 177929 | 01562 | 396 |  |  | Solar |  | 05_14_24L1 | 04/19/2017 | 04/19/2017 | 9 | 8 | 1 | 05/02/2017 | 05/02/2017 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2017 | 04/19/2017 | 2/11/2019 | Y | EXP | 607 |  |  | 0 | 0 | 0 |  |  | 2/11/2019 | Connected |  | N
National Grid | FALL RIVER | 284117 | 02721 | 11.4 |  |  | Solar |  | 05_14_56L2 | 03/17/2020 |  | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 178546 | 01752 | 604 |  |  | Solar |  | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 306671 | 01966 | 9.8 |  |  | Solar |  | 05_14_7L2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 12/14/2022 | Y | EXP | 365 | 06/29/2021 | 08/06/2021 | 38 | 0 | 38 |  |  | 9/10/2021 | Connected |  | Y
National Grid | CHELMSFORD | 174230 | 01824 | 2500 |  |  | Solar |  | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 1/9/2014 | 1/9/2014 | 1/9/2014 | Connected |  | N
National Grid | ANDOVER | 174328 | 01845 | 2750 |  |  | Solar |  | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 6/21/2014 | Y | STD | 570 | 03/10/2014 | 05/15/2014 | 46 | 0 | 46 | 6/24/2014 | 6/24/2014 | 7/2/2014 | Connected |  | N
National Grid | BILLERICA | 628778 | 01862 | 10 |  |  | Solar |  | 05_01_552L3 | 07/30/2024 | 08/19/2024 | 4 | 0 | 4 | 08/20/2024 | 08/20/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | SALISBURY | 581461 | 01952 | 6 |  |  | Solar |  | 05_05_106W42 | 02/08/2024 | 02/21/2024 | 8 | 5 | 3 | 02/22/2024 | 02/22/2024 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | SHIRLEY | 255015 | 01464 | 7.6 |  |  | Solar |  | 05_05_311W2 | 09/18/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 |  | 9/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2020 | Connected |  | N
National Grid | OXFORD | 630449 | 01540 | 4.06 |  |  | Solar |  | 05_12_40J2 | 08/06/2024 | 09/17/2024 | 1 | 0 | 1 | 09/18/2024 | 09/18/2024 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | BROOKFIELD | 184582 | 01515 | 233.1 |  |  | Solar |  | 05_14_24L1 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/31/2018 | 05/31/2018 | 339 | 66 | 273 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 285219 | 02721 | 23.78 |  |  | Solar |  | 05_14_56L2 | 03/25/2020 | 04/01/2020 | 4 | 0 | 4 | 04/02/2020 | 04/02/2020 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2020 | Connected |  | N
National Grid | MARLBOROUGH | 178584 | 01752 | 158 |  |  | Solar |  | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 23 | 3 | 20 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 345471 | 01966 | 500 |  |  | Solar |  | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 169 | 33 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 174232 | 01824 | 2000 |  |  | Solar |  | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 |  | 11/1/2012 | N | STD | -82 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175286 | 01845 | 19.78 |  |  | Solar |  | 05_01_406L4 | 11/06/2014 | 11/06/2014 | 5 | 3 | 2 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 4/27/2016 | Connected |  | N
National Grid | BILLERICA | 670551 | 01862 | 5.76 |  |  | Solar |  | 05_01_552L3 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/06/2025 | 4/4/2026 | Y | EXP | 365 | 07/19/2025 | 08/04/2025 | 17 | 0 | 17 |  |  | 9/25/2025 | Connected |  | N
National Grid | SALISBURY | 661388 | 01952 | 7.6 |  |  | Solar |  | 05_05_106W42 | 12/24/2024 | 01/29/2025 | 9 | 4 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/24/2024 | 3/24/2026 | Y | EXP | 365 | 05/02/2025 | 07/16/2025 | 76 | 0 | 76 |  |  | 7/22/2025 | Connected |  | N
National Grid | SHIRLEY | 268191 | 01464 | 7.6 |  |  | Solar |  | 05_05_311W2 | 12/09/2019 | 12/15/2019 | 4 | 0 | 4 | 12/16/2019 | 12/16/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 2/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 659692 | 01540 | 7.83 |  |  | Solar |  | 05_12_40J2 | 12/10/2024 | 12/29/2024 | 9 | 4 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/10/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 185021 | 01535 | 3.8 |  |  | Solar |  | 05_14_24L1 | 05/10/2018 | 05/10/2018 | 4 | 0 | 4 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 315160 | 02724 | 15.2 |  |  | Solar |  | 05_14_56L2 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178580 | 01752 | 402 |  |  | Solar |  | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 25 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 346665 | 01966 | 250 |  |  | Solar |  | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 193 | 192 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 174493 | 01824 | 232 |  |  | Solar |  | 05_01_227W3 | 06/13/2011 | 06/13/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2011 |  | 3/7/2012 | N | STD | 156 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/7/2012 | Connected |  | N
National Grid | ANDOVER | 175331 | 01845 | 3000 |  |  | Solar |  | 05_01_406L4 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 671085 | 01876 | 5.76 |  |  | Solar |  | 05_01_552L3 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SALISBURY | 663644 | 01952 | 10 |  |  | Solar |  | 05_05_106W42 | 01/03/2025 | 01/16/2025 | 7 | 3 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/03/2025 | 3/17/2026 | Y | EXP | 365 | 03/08/2025 | 08/12/2025 | 158 | 0 | 158 |  |  | 8/29/2025 | Connected |  | N
National Grid | LANCASTER | 291983 | 01523 | 249 |  |  | Solar |  | 05_05_311W2 | 05/14/2020 | 05/21/2020 | 4 | 0 | 4 | 05/22/2020 | 05/22/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 706632 | 01540 | 20.475 |  |  | Solar |  | 05_12_40J2 | 07/22/2025 | 08/14/2025 | 16 | 13 | 3 | 08/15/2025 | 08/15/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | BROOKFIELD | 243846 | 01515 | 0 |  |  | Solar |  | 05_14_24L1 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 07/24/2019 | 7/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2020 | Connected |  | N
National Grid | FALL RIVER | 319343 | 02724 | 15.2 |  |  | Solar |  | 05_14_56L2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 01/22/2021 | 02/04/2021 | 13 | 0 | 13 |  |  | 6/7/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178577 | 01752 | 316 |  |  | Solar |  | 05_14_70L1 | 01/30/2018 | 01/30/2018 | 24 | 3 | 21 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 467964 | 01966 | 15.2 |  |  | Solar |  | 05_14_7L2 | 10/13/2022 | 12/12/2022 | 40 | 39 | 1 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | CHELMSFORD | 175662 | 01824 | 996 |  |  | Solar |  | 05_01_227W3 | 08/07/2014 | 08/07/2014 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/19/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 | 08/07/2014 | 6/15/2016 | Y | STD | 422 | 11/03/2015 | 01/30/2016 | 59 | 0 | 59 | 12/31/2015 | 12/31/2015 | 12/31/2015 | Connected |  | N
National Grid | ANDOVER | 175395 | 01845 | 10 |  |  | Solar |  | 05_01_406L4 | 09/16/2014 | 09/16/2014 | 7 | 0 | 7 | 09/26/2014 | 09/26/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 692136 | 01876 | 5.76 |  |  | Solar |  | 05_01_552L3 | 06/02/2025 | 06/13/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/02/2025 | 8/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | SALISBURY | 518149 | 01952 | 250 |  |  | Natural Gas |  | 05_05_106W43 | 08/17/2023 | 06/24/2024 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2024 | 07/19/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  | 4/29/2026 | N | STD | 120 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 298911 | 01523 | 24.78 |  |  | Solar |  | 05_05_311W2 | 08/14/2020 | 08/17/2020 | 0 | 0 | 0 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N
National Grid | OXFORD | 713056 | 01540 | 9.772 |  |  | Solar |  | 05_12_40J2 | 10/06/2025 | 10/08/2025 | 2 | 0 | 2 | 10/09/2025 | 10/09/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 |  | 11/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2025 | Connected |  | N
National Grid | BROOKFIELD | 255612 | 01506 | 3.8 |  |  | Solar |  | 05_14_24L1 | 09/23/2019 | 09/24/2019 | 0 | 0 | 0 | 09/25/2019 | 09/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 | 09/23/2019 | 5/19/2020 | Y | EXP | 236 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 3/31/2020 | Connected |  | N
National Grid | FALL RIVER | 327991 | 02721 | 7.6 |  |  | Solar |  | 05_14_56L2 | 11/24/2020 | 12/02/2020 | 4 | 0 | 4 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 11/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178576 | 01752 | 524 |  |  | Solar |  | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 615634 | 01966 | 3.8 |  |  | Solar |  | 05_14_7L2 | 06/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 06/05/2024 | 8/26/2025 | Y | EXP | 365 | 11/02/2024 | 11/12/2024 | 11 | 0 | 11 |  |  | 11/13/2024 | Connected |  | N
National Grid | CHELMSFORD | 175671 | 01824 | 1008 |  |  | Solar |  | 05_01_227W3 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2014 | 11/19/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175686 | 01845 | 17 |  |  | Solar |  | 05_01_406L4 | 12/23/2014 | 12/23/2014 | 8 | 5 | 3 | 01/07/2015 | 01/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2015 |  | 4/30/2015 | N | EXP | 90 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 11/12/2015 | Connected |  | N
National Grid | TEWKSBURY | 174385 | 01876 | 2650 |  |  | Solar |  | 05_01_55K11 | 05/31/2012 | 05/31/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2012 | 10/03/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 | 02/18/2015 | 06/29/2016 | 338 | 0 | 338 | 12/23/2014 | 05/31/2012 | 2/3/2016 | Y | STD | 407 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 174885 | 01952 | 40 |  |  | Solar |  | 05_05_106W43 | 02/16/2013 | 02/16/2013 | 7 | 0 | 7 | 02/28/2013 | 02/28/2013 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2013 |  | 5/31/2013 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 |  | Withdrawn |  | N
National Grid | AYER | 300432 | 01432 | 10 |  |  | Solar |  | 05_05_311W2 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | OXFORD | 556928 | 01540 | 6 |  |  | Solar |  | 05_12_40J4 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 10/27/2023 | 12/7/2024 | Y | EXP | 365 | 03/30/2024 | 06/18/2024 | 81 | 0 | 81 |  |  | 7/11/2024 | Connected |  | N
National Grid | SPENCER | 257941 | 01562 | 10 |  |  | Solar |  | 05_14_24L1 | 10/08/2019 | 10/15/2019 | 3 | 0 | 3 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/08/2019 | 10/8/2020 | Y | EXP | 365 | 03/10/2020 | 03/11/2020 | 1 | 0 | 1 |  |  | 5/15/2020 | Connected |  | N
National Grid | FALL RIVER | 335404 | 02721 | 9.36 |  |  | Solar |  | 05_14_56L2 | 01/06/2021 | 01/25/2021 | 12 | 12 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/06/2021 | 1/24/2022 | Y | EXP | 365 | 05/12/2021 | 06/02/2021 | 21 | 0 | 21 |  |  | 7/23/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178616 | 01752 | 444 |  |  | Solar |  | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 30 | 5 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 654131 | 01966 | 9.86 |  |  | Solar |  | 05_14_7L2 | 11/21/2024 | 12/13/2024 | 9 | 6 | 3 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/21/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | CHELMSFORD | 175811 | 01824 | 15.2 |  |  | Solar |  | 05_01_227W3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 1/5/2018 | N | EXP | 938 |  |  | 0 | 0 | 0 | 6/22/2015 | 6/22/2015 |  | Withdrawn |  | Y
National Grid | ANDOVER | 175721 | 01845 | 100 |  |  | Solar |  | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/3/2015 | N | EXP | 89 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 | 1/20/2015 | Connected |  | N
National Grid | BILLERICA | 175669 | 01862 | 1000 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 176154 | 01952 | 56 |  |  | Solar |  | 05_05_106W43 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/5/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | SHIRLEY | 328171 | 01464 | 15.2 |  |  | Solar |  | 05_05_311W2 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | OXFORD | 681602 | 01540 | 50 |  |  | Solar |  | 05_12_40L1 | 05/20/2025 | 05/23/2025 | 3 | 0 | 3 | 05/27/2025 | 05/27/2025 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROOKFIELD | 415288 | 01515 | 11.4 |  |  | Solar |  | 05_14_24L1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 4/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2022 | Connected |  | N
National Grid | FALL RIVER | 347328 | 02720 | 0 |  |  | Solar |  | 05_14_56L2 | 03/17/2021 | 03/18/2021 | 0 | 0 | 0 | 03/19/2021 | 03/19/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/17/2021 | 3/17/2022 | Y | EXP | 365 | 05/26/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 7/30/2021 | Connected |  | N
National Grid | MARLBOROUGH | 178720 | 01752 | 1950 |  |  | Solar |  | 05_14_70L1 | 04/12/2018 | 04/12/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 05/26/2018 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  | 7/29/2021 | N | STD | 728 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 711942 | 01966 | 5.76 |  |  | Solar |  | 05_14_7L4 | 08/13/2025 | 09/17/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 175924 | 01824 | 997.6 |  |  | Solar |  | 05_01_227W3 | 05/29/2015 | 05/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 07/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 | 05/29/2015 | 11/30/2015 | Y | STD | -58 |  |  | 0 | 0 | 0 | 8/1/2017 | 8/1/2017 | 8/1/2017 | Connected |  | N
National Grid | ANDOVER | 175770 | 01845 | 100 |  |  | Solar |  | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 96 | 0 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 12/31/2014 | N | EXP | 86 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 175702 | 01876 | 2000 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 176863 | 01952 | 40.25 |  |  | Solar |  | 05_05_106W43 | 01/21/2016 | 01/21/2016 | 4 | 4 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/18/2016 | 10/24/2016 | Connected |  | N
National Grid | SHIRLEY | 449265 | 01464 | 10 |  |  | Solar |  | 05_05_311W2 | 08/12/2022 | 08/19/2022 | 5 | 4 | 1 | 08/22/2022 | 08/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 366436 | 01540 | 6.96 |  |  | Solar |  | 05_12_40L1 | 06/28/2021 | 06/30/2021 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 426459 | 01562 | 15.2 |  |  | Solar |  | 05_14_24L1 | 05/23/2022 | 06/10/2022 | 14 | 13 | 1 | 06/13/2022 | 06/13/2022 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 | 05/23/2022 | 11/14/2023 | Y | EXP | 365 | 10/19/2022 | 11/14/2022 | 27 | 0 | 27 |  |  | 12/15/2022 | Connected |  | N
National Grid | FALL RIVER | 363866 | 02721 | 9.8 |  |  | Solar |  | 05_14_56L2 | 06/15/2021 | 06/17/2021 | 2 | 0 | 2 | 06/18/2021 | 06/18/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  | 8/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2022 | Connected |  | N
National Grid | MARLBOROUGH | 243050 | 01752 | 7.6 |  |  | Solar |  | 05_14_70L1 | 08/09/2019 | 01/17/2020 | 111 | 111 | 0 | 01/21/2020 | 01/21/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2020 |  | 8/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 726965 | 01966 | 0 |  |  | Battery Add-On |  | 05_14_7L4 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 176391 | 01824 | 168 |  |  | Solar |  | 05_01_227W3 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 02/03/2016 | 02/03/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 2/8/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176419 | 01845 | 1250 |  |  | Solar |  | 05_01_406L4 | 12/07/2015 | 12/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/07/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 175701 | 01862 | 2000 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 401104 | 01952 | 0 |  |  | Other |  | 05_05_106W43 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 01/27/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 421735 | 01464 | 12 |  |  | Solar |  | 05_05_311W2 | 05/10/2022 | 05/12/2022 | 3 | 2 | 1 | 05/13/2022 | 05/13/2022 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2022 | Connected |  | N
National Grid | OXFORD | 430455 | 01540 | 15.2 |  |  | Solar |  | 05_12_40L1 | 05/19/2022 | 05/20/2022 | 1 | 0 | 1 | 05/23/2022 | 05/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | SPENCER | 439488 | 01562 | 5.76 |  |  | Solar |  | 05_14_24L1 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 385253 | 02720 | 9.8 |  |  | Solar |  | 05_14_56L2 | 09/29/2021 | 10/04/2021 | 4 | 3 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | MARLBOROUGH | 295835 | 01752 | 7.6 |  |  | Solar |  | 05_14_70L1 | 06/13/2020 | 06/18/2020 | 3 | 0 | 3 | 06/19/2020 | 06/19/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | ROCKPORT | 731443 | 01966 | 5.76 |  |  | Solar |  | 05_14_7L4 | 11/04/2025 | 11/05/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 176808 | 01824 | 13.6 |  |  | Solar |  | 05_01_227W3 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/3/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176458 | 01845 | 6 |  |  | Solar |  | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 |  | 12/14/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/10/2016 | Connected |  | N
National Grid | BILLERICA | 175700 | 01862 | 860 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 2/3/2016 | Y | STD | -142 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | SALISBURY | 602713 | 01952 | 7.6 |  |  | Solar |  | 05_05_106W43 | 04/09/2024 | 04/13/2024 | 1 | 0 | 1 | 08/07/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2024 | 04/09/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 10/4/2024 | Connected |  | N
National Grid | SHIRLEY | 424366 | 01464 | 0 |  |  | Solar |  | 05_05_311W2 | 04/22/2022 | 04/25/2022 | 2 | 1 | 1 | 04/26/2022 | 04/26/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 434717 | 01540 | 10 |  |  | Solar |  | 05_12_40L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 5/15/2024 | N | EXP | 365 | 01/07/2023 | 05/15/2023 | 129 | 0 | 129 |  |  | 5/24/2023 | Connected |  | N
National Grid | SPENCER | 475619 | 01562 | 100 |  |  | Solar |  | 05_14_24L1 | 11/08/2022 | 12/12/2022 | 23 | 13 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 396669 | 02721 | 0 |  |  | Other |  | 05_14_56L2 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 325147 | 01752 | 7.68 |  |  | Solar |  | 05_14_70L1 | 01/06/2021 | 02/17/2021 | 28 | 28 | 0 | 02/18/2021 | 02/18/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2021 |  | 2/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 731423 | 01966 | 22.8 |  |  | Solar |  | 05_14_7L4 | 11/05/2025 | 11/12/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 177274 | 01824 | 0 |  |  | Solar |  | 05_01_227W3 | 02/06/2017 | 02/06/2017 | 45 | 44 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2017 | 04/24/2017 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 | 02/06/2017 | 2/18/2023 | Y | STD | 1017 | 10/30/2019 | 10/29/2019 | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | ANDOVER | 176491 | 01845 | 2000 |  |  | Solar |  | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 |  | 12/15/2016 | N | STD | -137 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 175699 | 01862 | 629 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N
National Grid | SALISBURY | 641015 | 01952 | 10 |  |  | Solar |  | 05_05_106W43 | 09/25/2024 | 10/25/2024 | 10 | 9 | 1 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 1/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | SHIRLEY | 441361 | 01464 | 15.2 |  |  | Solar |  | 05_05_311W2 | 06/30/2022 | 07/07/2022 | 4 | 3 | 1 | 07/08/2022 | 07/08/2022 | 79 | 51 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 471710 | 01540 | 5.22 |  |  | Solar |  | 05_12_40L1 | 11/14/2022 | 11/22/2022 | 6 | 3 | 3 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/14/2022 | 11/15/2024 | Y | EXP | 365 | 05/17/2023 | 11/06/2023 | 174 | 0 | 174 |  |  | 12/6/2023 | Connected |  | Y
National Grid | SPENCER | 511233 | 01562 | 0 |  |  | Solar |  | 05_14_24L1 | 03/15/2023 | 09/28/2023 | 135 | 132 | 3 | 09/29/2023 | 09/29/2023 | 98 | 65 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 372170 | 02721 | 7.6 |  |  | Solar |  | 05_14_70L1 | 08/09/2021 | 08/10/2021 | 1 | 0 | 1 | 08/11/2021 | 08/11/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 9/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | MARLBOROUGH | 174822 | 01752 | 30 |  |  | Solar |  | 05_14_7L4 | 08/02/2013 | 08/02/2013 | 7 | 1 | 6 | 08/14/2013 | 08/14/2013 | 156 | 3 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2013 |  | 11/29/2013 | N | EXP | 84 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 |  | Withdrawn |  | N
National Grid | ROCKPORT | 177337 | 01966 | 16 |  |  | Solar |  | 05_01_227W3 | 09/01/2016 | 09/01/2016 | 12 | 12 | 0 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 9/6/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N
National Grid | CHELMSFORD | 176490 | 01824 | 4000.002 |  |  | Solar |  | 05_01_406L4 | 12/08/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 | 12/08/2015 | 2/14/2020 | Y | STD | 805 | 10/16/2019 | 01/14/2020 | 90 | 0 | 90 |  |  | 2/13/2020 | Connected |  | N
National Grid | ANDOVER | 175698 | 01845 | 393 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N
National Grid | BILLERICA | 729508 | 01862 | 240 |  |  | Solar |  | 05_05_106W44 | 10/31/2025 | 12/03/2025 | 20 | 11 | 9 | 12/04/2025 | 12/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALISBURY | 479117 | 01952 | 7.6 |  |  | Solar |  | 05_05_311W2 | 11/21/2022 | 11/22/2022 | 1 | 0 | 1 | 11/23/2022 | 11/23/2022 | 56 | 32 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 522876 | 01464 | 10 |  |  | Solar |  | 05_12_40L1 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 05/08/2023 | 6/20/2024 | Y | EXP | 365 | 08/19/2023 | 10/18/2023 | 61 | 0 | 61 |  |  | 10/23/2023 | Connected |  | N
National Grid | OXFORD | 532374 | 01540 | 9.765 |  |  | Solar |  | 05_14_24L1 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 21 | 0 | 21 | 08/04/2023 | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 11/29/2024 | N | EXP | 365 | 02/02/2024 | 04/26/2024 | 85 | 0 | 85 |  |  | 5/3/2024 | Connected |  | N
National Grid | SPENCER | 421208 | 01562 | 15.2 |  |  | Solar |  | 05_14_56L2 | 05/04/2022 | 05/10/2022 | 4 | 0 | 4 | 05/11/2022 | 05/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | Y
National Grid | FALL RIVER | 401363 | 02720 | 0 |  |  | Battery Add-On |  | 05_14_70L1 | 05/11/2022 | 06/16/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 175002 | 01752 | 150 |  |  | Solar |  | 05_14_7L4 | 09/12/2013 | 09/12/2013 | 6 | 0 | 6 | 09/23/2013 | 09/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2013 |  | 11/29/2013 | N | EXP | 36 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 3/7/2014 | Connected |  | N
National Grid | ROCKPORT | 184835 | 01966 | 7.6 |  |  | Solar |  | 05_01_227W3 | 05/23/2018 | 05/23/2018 | 8 | 0 | 8 | 06/06/2018 | 06/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2018 |  | 8/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2018 | Connected |  | N
National Grid | CHELMSFORD | 176531 | 01824 | 252 |  |  | Solar |  | 05_01_406L4 | 12/17/2015 | 12/17/2015 | 27 | 27 | 0 | 01/28/2016 | 01/28/2016 | 192 | 0 | 192 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/22/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175697 | 01845 | 2000 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | LOWELL | 739526 | 01852 | 22.8 |  |  | Solar |  | 05_05_106W44 | 12/11/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALISBURY | 488924 | 01952 | 6.09 |  |  | Solar |  | 05_05_311W2 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N
National Grid | SHIRLEY | 559826 | 01464 |  |  |  | Solar |  | 05_12_40L1 | 10/18/2023 | 10/20/2023 | 3 | 1 | 2 | 10/23/2023 | 10/23/2023 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | OXFORD | 642866 | 01540 | 8.45 |  |  | Solar |  | 05_14_24L1 | 09/25/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 12/2/2025 | Y | EXP | 365 | 01/04/2025 | 01/24/2025 | 21 | 0 | 21 |  |  | 2/3/2025 | Connected |  | N
National Grid | SPENCER | 446210 | 01562 | 15.2 |  |  | Solar |  | 05_14_56L2 | 07/22/2022 | 07/22/2022 | 0 | 0 | 0 | 07/25/2022 | 07/25/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | FALL RIVER | 414875 | 02720 | 15.2 |  |  | Solar |  | 05_14_70L1 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175524 | 01752 | 500 |  |  | Solar |  | 05_14_7L4 | 07/28/2014 | 07/28/2014 | 7 | 0 | 7 | 08/07/2014 | 08/07/2014 | 0 | 0 | 0 | 09/24/2014 | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 2/6/2015 | 07/28/2014 | 12/31/2016 | Y | EXP | 694 | 05/30/2017 | 06/24/2017 | 19 | 0 | 19 | 8/1/2017 | 8/1/2017 | 8/4/2017 | Connected |  | N
National Grid | ROCKPORT | 199446 | 01966 | 250 |  |  | Solar |  | 05_01_227W3 | 10/26/2018 | 10/30/2018 | 1 | 0 | 1 | 10/31/2018 | 10/31/2018 | 10 | 0 | 10 | 11/16/2018 | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 177404 | 01824 | 6 |  |  | Solar |  | 05_01_406L4 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 |  | 7/5/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175704 | 01845 | 1750 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 | 11/28/2016 | 11/28/2016 | 11/28/2016 | Connected |  | N
National Grid | BILLERICA | 174596 | 01862 | 26 |  |  | Solar |  | 05_05_106W44 | 10/18/2011 | 10/18/2011 | 2 | 0 | 2 | 11/15/2011 | 11/15/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 4/13/2012 | N | EXP | 108 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 4/13/2012 | Connected |  | N
National Grid | SALISBURY | 517555 | 01952 | 15.2 |  |  | Solar |  | 05_05_311W2 | 04/06/2023 | 04/07/2023 | 1 | 0 | 1 | 04/10/2023 | 04/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 | 04/06/2023 | 5/10/2024 | Y | EXP | 365 | 07/04/2023 | 11/06/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | SHIRLEY | 608732 | 01464 | 3.8 |  |  | Solar |  | 05_12_40L1 | 05/03/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/03/2024 | 7/9/2025 | Y | EXP | 365 | 08/15/2024 | 11/06/2024 | 83 | 0 | 83 |  |  | 11/20/2024 | Connected |  | N
National Grid | OXFORD | 657505 | 01540 | 7.6 |  |  | Solar |  | 05_14_24L1 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 466523 | 01562 | 6 |  |  | Solar |  | 05_14_56L2 | 10/06/2022 | 10/12/2022 | 3 | 1 | 2 | 10/13/2022 | 10/13/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 | 10/06/2022 | 11/10/2023 | Y | EXP | 365 | 12/21/2022 | 12/21/2022 | 1 | 0 | 1 |  |  | 4/14/2023 | Connected |  | N
National Grid | FALL RIVER | 419848 | 02723 | 0 |  |  | Other |  | 05_14_70L1 | 06/29/2022 | 07/12/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2022 | 08/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176047 | 01752 | 42 |  |  | Solar |  | 05_14_7L4 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 6/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 3/31/2015 | Connected |  | N
National Grid | ROCKPORT | 232315 | 01966 | 250 |  |  | Solar |  | 05_01_227W3 | 12/11/2019 | 01/14/2020 | 20 | 15 | 5 | 01/15/2020 | 01/15/2020 | 56 | 36 | 20 | 05/19/2020 | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 |  | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 12/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 177886 | 01824 | 10 |  |  | Solar |  | 05_01_406L4 | 04/11/2017 | 04/11/2017 | 2 | 0 | 2 | 04/14/2017 | 04/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2017 | 04/11/2017 | 4/17/2018 | Y | EXP | 365 | 08/04/2017 | 09/05/2017 | 21 | 0 | 21 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | ANDOVER | 175703 | 01845 | 1400 |  |  | Solar |  | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | -148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | TEWKSBURY | 175252 | 01876 | 20.64 |  |  | Solar |  | 05_05_106W44 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 710 | 0 | 710 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 12/1/2017 | N | EXP | 1107 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | Y
National Grid | SALISBURY | 534257 | 01952 | 0 |  |  | Solar |  | 05_05_311W2 | 07/21/2023 | 07/26/2023 | 3 | 1 | 2 | 07/27/2023 | 07/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 10/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2024 | Connected |  | N
National Grid | SHIRLEY | 640630 | 01464 | 6.09 |  |  | Solar |  | 05_12_40L1 | 09/16/2024 | 11/15/2024 | 30 | 26 | 4 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 685057 | 01540 | 10 |  |  | Solar |  | 05_14_24L1 | 04/17/2025 |  | 120 | 25 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 529680 | 01562 | 7.875 |  |  | Solar |  | 05_14_56L2 | 06/20/2023 | 06/29/2023 | 21 | 16 | 5 | 06/30/2023 | 06/30/2023 | 17 | 0 | 17 | 09/29/2023 | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 10/13/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 444078 | 02723 | 9.8 |  |  | Solar |  | 05_14_70L1 | 07/20/2022 |  | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177992 | 01752 | 7.6 |  |  | Solar |  | 05_14_7L4 | 10/24/2017 | 10/24/2017 | 5 | 5 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 11/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 2/5/2019 | Connected |  | N
National Grid | ROCKPORT | 231499 | 01966 | 250 |  |  | Solar |  | 05_01_227W3 | 12/09/2019 | 01/14/2020 | 19 | 14 | 5 | 03/16/2020 | 03/16/2020 | 15 | 15 | 0 | 05/19/2020 | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 |  | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 178569 | 01824 | 10 |  |  | Solar |  | 05_01_406L4 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/13/2018 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | ANDOVER | 178660 | 01845 | 1000 |  |  | Solar |  | 05_01_55K11 | 02/06/2018 | 04/06/2018 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 | 02/06/2018 | 11/22/2021 | Y | STD | 416 | 01/09/2021 | 10/21/2021 | 285 | 3 | 282 |  |  | 11/3/2021 | Connected |  | N
National Grid | BILLERICA | 306648 | 01862 | 3.8 |  |  | Solar |  | 05_05_106W44 | 08/13/2020 | 08/17/2020 | 1 | 0 | 1 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 5/3/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 538691 | 01952 | 11.05 |  |  | Solar |  | 05_05_311W2 | 10/09/2023 | 10/10/2023 | 1 | 0 | 1 | 10/11/2023 | 10/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 663214 | 01464 | 4.55 |  |  | Solar |  | 05_12_40L1 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | OXFORD | 686019 | 01540 | 20 |  |  | Solar |  | 05_14_24L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | SPENCER | 572842 | 01562 | 250 |  |  | Solar |  | 05_14_56L2 | 12/07/2023 | 02/04/2024 | 38 | 29 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 578847 | 02723 | 0 |  |  | Solar |  | 05_14_70L1 | 01/22/2024 | 01/24/2024 | 2 | 0 | 2 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | MARLBOROUGH | 178166 | 01752 | 11.4 |  |  | Solar |  | 05_14_7L4 | 02/14/2018 | 02/14/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 2/20/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | ROCKPORT | 346662 | 01966 | 500 |  |  | Solar |  | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 10 | 0 | 10 |  |  | 240 | 218 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 198666 | 01824 | 6 |  |  | Solar |  | 05_01_406L4 | 12/13/2018 | 12/24/2018 | 6 | 0 | 6 | 12/26/2018 | 12/26/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 671566 | 01845 | 10 |  |  | Solar |  | 05_01_55W1 | 02/11/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/11/2025 | 5/11/2026 | Y | EXP | 365 | 08/28/2025 |  | 127 | 6 | 121 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 605320 | 01862 | 5.76 |  |  | Solar |  | 05_05_106W44 | 04/20/2024 | 04/25/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/20/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | SALISBURY | 562727 | 01952 | 0 |  |  | Battery Add-On |  | 05_05_311W2 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 4/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2024 | Connected |  | N
National Grid | SHIRLEY | 688401 | 01464 | 4.537 |  |  | Solar |  | 05_12_40L1 | 07/09/2025 | 07/25/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | OXFORD | 699938 | 01540 | 15.2 |  |  | Solar |  | 05_14_24L1 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/25/2025 | 8/5/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/6/2025 | Connected |  | N
National Grid | SPENCER | 581516 | 01562 | 7.6 |  |  | Solar |  | 05_14_56L2 | 01/04/2024 | 01/23/2024 | 12 | 7 | 5 | 01/24/2024 | 01/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 605506 | 02723 | 10 |  |  | Solar |  | 05_14_70L1 | 04/23/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/23/2024 | 5/20/2025 | Y | EXP | 365 | 06/26/2024 | 08/09/2024 | 45 | 0 | 45 |  |  | 8/22/2024 | Connected |  | N
National Grid | MARLBOROUGH | 178204 | 01752 | 4000 |  |  | Solar |  | 05_14_7L4 | 02/07/2018 | 02/07/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 04/18/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 | 02/07/2018 | 2/25/2021 | Y | STD | 833 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 346659 | 01966 | 250 |  |  | Solar |  | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 92 | 29 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 306142 | 01824 | 0 |  |  | Other |  | 05_01_406L4 | 09/16/2020 | 09/30/2020 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 682705 | 01845 | 24.7 |  |  | Solar |  | 05_01_55W1 | 04/03/2025 | 04/08/2025 | 4 | 1 | 3 | 04/09/2025 | 04/09/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | TEWKSBURY | 649038 | 01876 | 5.76 |  |  | Solar |  | 05_05_106W44 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | SALISBURY | 581937 | 01952 | 5.376 |  |  | Solar |  | 05_05_311W2 | 01/23/2024 | 02/06/2024 | 11 | 10 | 1 | 02/07/2024 | 02/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/23/2024 | 4/1/2025 | Y | EXP | 365 | 04/30/2024 | 07/03/2024 | 65 | 0 | 65 |  |  | 12/5/2024 | Connected |  | N
National Grid | SHIRLEY | 622085 | 01464 | 60 |  |  | Solar |  | 05_12_49W2 | 07/08/2024 | 12/12/2024 | 108 | 100 | 8 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 1/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 704907 | 01540 | 7.6 |  |  | Solar |  | 05_14_24L1 | 07/15/2025 | 09/15/2025 | 6 | 1 | 5 | 09/25/2025 | 09/25/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | SPENCER | 600029 | 01562 | 0 |  |  | Battery Add-On |  | 05_14_56L2 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2024 | Connected |  | N
National Grid | FALL RIVER | 605258 | 02723 | 10 |  |  | Solar |  | 05_14_70L1 | 05/23/2024 | 05/28/2024 | 2 | 0 | 2 | 05/29/2024 | 05/29/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 184636 | 01752 | 7.6 |  |  | Solar |  | 05_14_7L4 | 05/10/2018 | 05/10/2018 | 11 | 0 | 11 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 | 05/10/2018 | 6/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | ROCKPORT | 361884 | 01966 | 9.8 |  |  | Solar |  | 05_01_227W3 | 06/03/2021 | 06/08/2021 | 3 | 2 | 1 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 8/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | CHELMSFORD | 373487 | 01824 | 9.8 |  |  | Solar |  | 05_01_406L4 | 08/05/2021 | 12/13/2021 | 2 | 0 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 | 08/05/2021 | 11/5/2023 | Y | EXP | 365 | 03/29/2022 | 06/22/2022 | 86 | 0 | 86 |  |  | 2/3/2023 | Connected |  | N
National Grid | ANDOVER | 714377 | 01845 | 0 |  |  | Other |  | 05_01_55W1 | 09/26/2025 | 11/12/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BILLERICA | 663614 | 01862 | 4.8 |  |  | Solar |  | 05_05_106W44 | 01/03/2025 | 01/28/2025 | 2 | 0 | 2 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | SALISBURY | 599668 | 01952 | 11 |  |  | Solar |  | 05_05_311W2 | 04/24/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 644663 | 01464 | 10 |  |  | Solar |  | 05_12_49W2 | 10/03/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | OXFORD | 657917 | 01540 | 3.8 |  |  | Solar |  | 05_14_24L2 | 12/02/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | RUTLAND | 608440 | 01543 | 7.54 |  |  | Solar |  | 05_14_56L2 | 05/03/2024 | 06/26/2024 | 36 | 35 | 1 | 06/27/2024 | 06/27/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | FALL RIVER | 621445 | 02723 | 18.115 |  |  | Solar |  | 05_14_70L1 | 06/28/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | MARLBOROUGH | 193070 | 01752 | 246.5 |  |  | Solar |  | 05_14_7L4 | 08/08/2018 | 08/22/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/26/2018 | 11/01/2018 | 5 | 1 | 4 | 08/23/2018 | 09/26/2018 | 24 | 6 | 18 |  | 11/01/2018 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 4/15/2020 | 08/08/2018 | 11/23/2022 | Y | STD | 98 |  |  | 0 | 0 | 0 |  |  | 10/25/2022 | Connected |  | N
National Grid | ROCKPORT | 562155 | 01966 | 10 |  |  | Solar |  | 05_01_227W3 | 11/29/2023 | 12/19/2023 | 14 | 10 | 4 | 12/20/2023 | 12/20/2023 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 11/29/2023 | 4/1/2025 | Y | EXP | 365 | 06/18/2024 | 07/10/2024 | 23 | 0 | 23 |  |  | 7/22/2024 | Connected |  | Y
National Grid | CHELMSFORD | 386256 | 01824 | 7.6 |  |  | Solar |  | 05_01_406L4 | 10/04/2021 |  | 31 | 26 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 724459 | 01845 | 7.6 |  |  | Solar |  | 05_01_55W1 | 10/08/2025 | 11/20/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 689724 | 01852 | 200 |  |  | Solar |  | 05_05_106W44 | 05/08/2025 | 08/26/2025 | 74 | 65 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 609713 | 01952 | 10 |  |  | Solar |  | 05_05_311W2 | 05/08/2024 | 05/16/2024 | 6 | 5 | 1 | 05/17/2024 | 05/17/2024 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 05/08/2024 | 7/2/2025 | Y | EXP | 365 | 09/10/2024 | 10/16/2024 | 37 | 0 | 37 |  |  | 2/28/2025 | Connected |  | N
National Grid | SHIRLEY | 674332 | 01464 | 450 |  |  | Solar |  | 05_12_49W2 | 06/10/2025 | 09/11/2025 | 63 | 54 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2025 | 12/03/2025 | 56 | 37 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | OXFORD | 711798 | 01540 | 3.8 |  |  | Solar |  | 05_14_24L2 | 08/13/2025 | 09/05/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 71 | 57 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 645686 | 01543 | 23 |  |  | Solar |  | 05_14_56L2 | 10/09/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/09/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 648217 | 02723 | 7.6 |  |  | Solar |  | 05_14_70L1 | 10/30/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 10/30/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | MARLBOROUGH | 252060 | 01752 | 7.6 |  |  | Solar |  | 05_14_7L4 | 09/11/2019 | 09/18/2019 | 4 | 0 | 4 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/11/2019 | 9/11/2020 | Y | EXP | 365 | 02/01/2020 | 02/05/2020 | 4 | 0 | 4 |  |  | 2/14/2020 | Connected |  | N
National Grid | SALEM | 612875 | 01970 | 11.5 |  |  | Solar |  | 05_01_227W3 | 05/23/2024 | 05/31/2024 | 5 | 2 | 3 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/23/2024 | 8/8/2025 | Y | EXP | 365 | 06/10/2025 | 08/11/2025 | 63 | 0 | 63 |  |  | 8/16/2025 | Connected |  | N
National Grid | CHELMSFORD | 398616 | 01824 | 11.4 |  |  | Solar |  | 05_01_406L4 | 07/06/2022 | 07/11/2022 | 3 | 2 | 1 | 07/12/2022 | 07/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 727815 | 01845 | 5.76 |  |  | Solar |  | 05_01_55W1 | 10/20/2025 | 11/14/2025 | 17 | 15 | 2 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 691599 | 01862 | 75 |  |  | Solar |  | 05_05_106W45 | 05/20/2025 | 09/25/2025 | 88 | 79 | 9 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALISBURY | 611935 | 01952 | 20 |  |  | Solar |  | 05_05_311W2 | 05/22/2024 | 06/24/2024 | 21 | 20 | 1 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | SHIRLEY | 730129 | 01464 | 60 |  |  | Solar |  | 05_12_49W2 | 11/10/2025 | 12/24/2025 | 30 | 22 | 8 | 12/26/2025 | 12/26/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 725938 | 01540 | 23.034 |  |  | Solar |  | 05_14_24L2 | 10/21/2025 | 10/27/2025 | 4 | 0 | 4 | 10/28/2025 | 10/28/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 652213 | 01543 | 7.6 |  |  | Solar |  | 05_14_56L2 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 648708 | 02723 | 10 |  |  | Solar |  | 05_14_70L1 | 11/04/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 277711 | 01752 | 5 |  |  | Solar |  | 05_14_7L4 | 02/06/2020 | 02/18/2020 | 6 | 6 | 0 | 02/19/2020 | 02/19/2020 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 | 02/06/2020 | 2/18/2021 | Y | EXP | 365 | 06/09/2020 | 06/11/2020 | 2 | 0 | 2 |  |  | 6/13/2020 | Connected |  | N
National Grid | SALEM | 624233 | 01970 | 10 |  |  | Solar |  | 05_01_227W3 | 07/11/2024 | 08/01/2024 | 1 | 0 | 1 | 08/02/2024 | 08/02/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 07/11/2024 | 9/27/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | CHELMSFORD | 403041 | 01824 | 5.51 |  |  | Solar |  | 05_01_406L4 | 12/28/2021 | 01/03/2022 | 4 | 0 | 4 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 12/28/2021 | 9/6/2023 | Y | EXP | 365 | 06/16/2022 | 07/18/2022 | 33 | 0 | 33 |  |  | 10/27/2022 | Connected |  | N
National Grid | ANDOVER | 174218 | 01845 | 11.38 |  |  | Solar |  | 05_01_55W1 | 01/31/2012 | 01/31/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 |  | 3/1/2012 | N | EXP | -43 |  |  | 0 | 0 | 0 | 7/23/2012 | 7/23/2012 | 8/7/2012 | Connected |  | N
National Grid | BILLERICA | 175777 | 01862 | 85 |  |  | Solar |  | 05_05_106W45 | 08/20/2014 | 08/20/2014 | 7 | 3 | 4 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2014 |  | 12/31/2014 | N | EXP | 112 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 | 12/4/2014 | Connected |  | N
National Grid | SALISBURY | 624368 | 01952 | 10 |  |  | Solar |  | 05_05_311W2 | 07/12/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 174825 | 01464 | 164 |  |  | Solar |  | 05_12_49W2 | 07/20/2011 | 07/20/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/24/2012 | N | EXP | 207 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/24/2012 | Connected |  | N
National Grid | OXFORD | 725617 | 01540 | 7.6 |  |  | Solar |  | 05_14_24L2 | 11/03/2025 | 11/05/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 670110 | 01543 | 10 |  |  | Solar |  | 05_14_56L2 | 02/05/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | FALL RIVER | 652988 | 02723 | 3.8 |  |  | Solar |  | 05_14_70L1 | 11/14/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 301879 | 01752 | 0 |  |  | Solar |  | 05_14_7L4 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2020 | Connected |  | N
National Grid | SALEM | 639462 | 01970 | 7.6 |  |  | Solar |  | 05_01_227W3 | 09/13/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/13/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | CHELMSFORD | 409267 | 01824 | 0 |  |  | Other |  | 05_01_406L4 | 02/14/2023 |  | 104 | 46 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 174355 | 01845 | 1000 |  |  | Solar |  | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 197438 | 01862 | 1400 |  |  | Natural Gas |  | 05_05_106W45 | 09/20/2019 | 11/07/2019 | 33 | 28 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2019 | 12/09/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 666520 | 01952 | 0 |  |  | Battery Add-On |  | 05_05_311W2 | 02/06/2025 | 02/19/2025 | 8 | 3 | 5 | 02/20/2025 | 02/20/2025 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | SHIRLEY | 175188 | 01464 | 18 |  |  | Solar |  | 05_12_49W2 | 11/19/2013 | 11/19/2013 | 4 | 0 | 4 | 11/26/2013 | 11/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 12/17/2013 | 12/17/2013 | 8/1/2014 | Connected |  | N
National Grid | OXFORD | 743169 | 01540 | 10 |  |  | Solar |  | 05_14_24L2 | 01/02/2026 | 01/06/2026 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 684866 | 01543 | 0 |  |  | Solar |  | 05_14_56L2 | 04/14/2025 | 05/20/2025 | 23 | 17 | 6 | 05/21/2025 | 05/21/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | FALL RIVER | 655124 | 02720 | 3.8 |  |  | Solar |  | 05_14_70L1 | 11/20/2024 | 02/25/2025 | 43 | 41 | 2 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 311019 | 01752 | 7.6 |  |  | Solar |  | 05_14_7L4 | 09/22/2020 | 09/23/2020 | 0 | 0 | 0 | 09/24/2020 | 09/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 10/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 646743 | 01970 | 7.6 |  |  | Solar |  | 05_01_227W3 | 10/14/2024 | 11/12/2024 | 11 | 4 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/14/2024 | 12/24/2025 | Y | EXP | 365 | 02/12/2025 | 03/04/2025 | 21 | 0 | 21 |  |  | 3/11/2025 | Connected |  | N
National Grid | CHELMSFORD | 471444 | 01824 | 6.38 |  |  | Solar |  | 05_01_406L4 | 11/01/2022 | 11/14/2022 | 8 | 3 | 5 | 11/15/2022 | 11/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/01/2022 | 3/30/2024 | Y | EXP | 365 | 02/23/2023 | 03/30/2023 | 36 | 0 | 36 |  |  | 5/1/2023 | Connected |  | N
National Grid | ANDOVER | 174354 | 01845 | 2000 |  |  | Solar |  | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  |  | 0 | 0 | 0 | 03/28/2014 | 03/28/2014 | 0 | 0 | 0 | 9/12/2013 | 05/17/2012 | 12/31/2012 | Y | STD | -255 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 11/3/2015 | Connected |  | N
National Grid | BILLERICA | 649212 | 01862 | 3.8 |  |  | Solar |  | 05_05_106W45 | 10/23/2024 | 12/02/2024 | 20 | 17 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/23/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | SALISBURY | 667203 | 01952 | 0 |  |  | Solar |  | 05_05_311W2 | 01/23/2025 | 02/13/2025 | 9 | 4 | 5 | 02/14/2025 | 02/14/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | SHIRLEY | 177361 | 01464 | 75 |  |  | Natural Gas |  | 05_12_49W2 | 06/22/2016 | 06/22/2016 | 18 | 18 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2016 |  | 6/28/2017 | N | EXP | 289 |  |  | 0 | 0 | 0 | 11/17/2016 | 11/17/2016 | 12/7/2016 | Connected |  | N
National Grid | OXFORD | 174747 | 01540 | 225 |  |  | Solar |  | 05_14_24L2 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 407 | 1 | 406 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 8/1/2014 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 705068 | 01543 | 17.799 |  |  | Solar |  | 05_14_56L2 | 07/17/2025 | 07/22/2025 | 3 | 0 | 3 | 07/23/2025 | 07/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | FALL RIVER | 329558 | 02720 | 7.6 |  |  | Solar |  | 05_14_7L4 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 | 12/21/2020 | 9/14/2022 | Y | EXP | 365 | 07/20/2021 | 09/10/2021 | 52 | 3 | 49 |  |  | 9/27/2021 | Connected |  | N
National Grid | MARLBOROUGH | 650217 | 01752 | 17.6 |  |  | Solar |  | 05_01_227W3 | 11/07/2024 | 11/12/2024 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | SALEM | 489250 | 01970 | 7.6 |  |  | Solar |  | 05_01_406L4 | 05/01/2023 |  | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 174384 | 01824 | 4 |  |  | Solar |  | 05_01_55W1 | 05/31/2012 | 05/31/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2012 |  | 8/31/2012 | N | EXP | -24 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 9/24/2012 | Connected |  | N
National Grid | ANDOVER | 672503 | 01845 | 5.76 |  |  | Solar |  | 05_05_106W45 | 02/18/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/18/2025 | 5/1/2026 | Y | EXP | 365 | 04/29/2025 | 06/03/2025 | 36 | 0 | 36 |  |  | 10/10/2025 | Connected |  | N
National Grid | BILLERICA | 727052 | 01862 | 7.6 |  |  | Solar |  | 05_05_311W2 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 186726 | 01952 | 88 |  |  | Solar |  | 05_12_49W2 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 5/26/2020 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  | 6/9/2020 | Connected |  | N
National Grid | SHIRLEY | 175759 | 01464 | 225 |  |  | Solar |  | 05_14_24L2 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/11/2015 | 04/24/2015 | 30 | 0 | 30 | 5/26/2015 | 5/26/2015 | 5/26/2015 | Connected |  | N
National Grid | HAVERHILL | 707961 | 01832 | 17.6 |  |  | Solar |  | 05_14_56L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 08/01/2025 | 10/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | RUTLAND | 507609 | 01543 | 450 |  |  | Solar |  | 05_14_70L2 | 07/07/2023 | 07/25/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2023 | 08/21/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 371237 | 02720 | 10 |  |  | Solar |  | 05_14_7L4 | 07/21/2021 | 09/28/2021 | 48 | 38 | 10 | 09/29/2021 | 09/29/2021 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 9/27/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 661266 | 01752 | 10 |  |  | Solar |  | 05_01_227W3 | 12/17/2024 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/17/2024 | 4/4/2026 | Y | EXP | 365 | 06/11/2025 | 10/20/2025 | 132 | 0 | 132 |  |  | 11/20/2025 | Connected |  | N
National Grid | SALEM | 505438 | 01970 | 15 |  |  | Solar |  | 05_01_406L4 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 117 | 95 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | CHELMSFORD | 174431 | 01824 | 4680 |  |  | Solar |  | 05_01_55W1 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 10/09/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/27/2012 | 10/12/2017 | Y | STD | 967 | 03/15/2017 | 08/18/2017 | 109 | 0 | 109 | 8/23/2017 | 8/23/2017 | 9/29/2017 | Connected |  | N
National Grid | ANDOVER | 431700 | 01845 | 160 |  |  | Solar |  | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 587963 | 01876 | 325 |  |  | Natural Gas |  | 05_05_311W3 | 02/23/2024 | 08/02/2024 | 111 | 101 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2024 | 08/27/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 4/29/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 194178 | 01952 | 146 |  |  | Solar |  | 05_12_49W2 | 08/24/2018 | 08/29/2018 | 0 | 0 | 0 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 5/26/2020 | N | EXP | 417 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | SHIRLEY | 175833 | 01464 | 16.34 |  |  | Solar |  | 05_14_24L2 | 03/03/2015 | 03/03/2015 | 8 | 5 | 3 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2015 |  | 7/14/2015 | N | EXP | 120 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/15/2015 | Connected |  | N
National Grid | OXFORD | 707764 | 01540 | 19.12 |  |  | Solar |  | 05_14_56L3 | 08/06/2025 | 08/27/2025 | 14 | 9 | 5 | 08/28/2025 | 08/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | RUTLAND | 708850 | 01543 | 17.16 |  |  | Solar |  | 05_14_70L2 | 08/08/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 19 | 0 | 19 | 10/30/2025 | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 427409 | 02720 | 60 |  |  | Solar |  | 05_14_7L4 | 05/09/2022 | 05/19/2022 | 8 | 0 | 8 | 05/20/2022 | 05/20/2022 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 05/09/2022 | 9/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N
National Grid | MARLBOROUGH | 711842 | 01752 | 20.9 |  |  | Solar |  | 05_01_227W3 | 08/13/2025 | 08/22/2025 | 6 | 1 | 5 | 08/25/2025 | 08/25/2025 | 88 | 60 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 536014 | 01970 | 7.6 |  |  | Solar |  | 05_01_406L4 | 06/22/2023 | 08/06/2023 | 4 | 1 | 3 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 06/22/2023 | 7/10/2025 | Y | EXP | 365 | 09/11/2024 | 10/10/2024 | 30 | 0 | 30 |  |  | 10/22/2024 | Connected |  | N
National Grid | CHELMSFORD | 174555 | 01824 | 3000 |  |  | Solar |  | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2013 |  | 10/31/2012 | N | STD | -275 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 431612 | 01845 | 240 |  |  | Solar |  | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 651954 | 01876 | 8.99 |  |  | Solar |  | 05_05_311W3 | 11/04/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | SALISBURY | 290730 | 01952 | 100 |  |  | Solar |  | 05_12_49W2 | 05/26/2020 | 06/16/2020 | 15 | 12 | 3 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 8/10/2022 | N | EXP | 625 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | SHIRLEY | 178000 | 01464 | 7.6 |  |  | Solar |  | 05_14_24L2 | 10/25/2017 | 10/25/2017 | 62 | 62 | 0 | 02/06/2018 | 02/06/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 11/1/2018 | N | EXP | 267 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 707133 | 01540 | 21.38 |  |  | Solar |  | 05_14_56L3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | RUTLAND | 725438 | 01543 | 8.725 |  |  | Solar |  | 05_14_70L2 | 10/14/2025 | 10/22/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 521126 | 02720 | 0 |  |  | Solar |  | 05_14_7L4 | 04/24/2023 | 04/28/2023 | 4 | 1 | 3 | 05/01/2023 | 05/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 707291 | 01752 | 10 |  |  | Solar |  | 05_01_23W1 | 07/24/2025 | 08/19/2025 | 3 | 0 | 3 | 08/25/2025 | 08/25/2025 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SALEM | 543392 | 01970 | 6 |  |  | Solar |  | 05_01_406L4 | 08/11/2023 | 08/14/2023 | 1 | 0 | 1 | 08/15/2023 | 08/15/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2023 | Connected |  | N
National Grid | CHELMSFORD | 174642 | 01824 | 21 |  |  | Solar |  | 05_01_55W1 | 12/06/2013 | 12/06/2013 | 8 | 0 | 8 | 12/19/2013 | 12/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2013 |  | 1/31/2014 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/21/2014 | 1/21/2014 | 1/30/2015 | Connected |  | N
National Grid | BOXFORD | 660363 | 01921 | 499.9 |  |  | Solar |  | 05_05_106W46 | 02/06/2025 | 03/27/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2025 | 07/31/2025 | 86 | 67 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 676908 | 01821 | 3.8 |  |  | Solar |  | 05_05_311W3 | 03/10/2025 | 03/22/2025 | 17 | 13 | 4 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 03/10/2025 | 6/10/2026 | Y | EXP | 365 | 07/19/2025 | 09/18/2025 | 62 | 0 | 62 |  |  |  | Completion Documents |  | Y
National Grid | SALISBURY | 291146 | 01952 | 7.54 |  |  | Solar |  | 05_12_49W2 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 09/11/2020 | 09/22/2020 | 11 | 0 | 11 |  |  | 11/18/2020 | Connected |  | N
National Grid | SHIRLEY | 178611 | 01464 | 0 |  |  | Other |  | 05_14_24L2 | 12/14/2017 | 12/14/2017 | 0 | 0 | 0 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/15/2018 | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 |  | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 4/30/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N
National Grid | OXFORD | 725463 | 01540 | 15.2 |  |  | Solar |  | 05_14_56L3 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 193712 | 01543 | 1491 |  |  | Solar |  | 05_14_70L2 | 09/24/2018 | 11/13/2018 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 04/02/2019 | 145 | 77 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 529466 | 02720 | 15.2 |  |  | Solar |  | 05_14_7L4 | 05/26/2023 | 05/30/2023 | 2 | 1 | 1 | 05/31/2023 | 05/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | MARLBOROUGH | 725080 | 01752 | 7.6 |  |  | Solar |  | 05_01_23W1 | 10/08/2025 | 10/20/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 579324 | 01970 | 1.45 |  |  | Solar |  | 05_01_406L4 | 02/01/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 02/01/2024 | 5/7/2025 | Y | EXP | 365 | 06/05/2024 | 08/29/2024 | 86 | 0 | 86 |  |  | 9/26/2024 | Connected |  | N
National Grid | CHELMSFORD | 174714 | 01824 | 70 |  |  | Solar |  | 05_01_55W1 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2014 | 01/09/2014 | 8/29/2014 | Y | EXP | 219 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 8/6/2015 | Connected |  | N
National Grid | BOXFORD | 660362 | 01921 | 499.9 |  |  | Solar |  | 05_05_106W46 | 02/06/2025 | 03/25/2025 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2025 | 07/31/2025 | 88 | 69 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 716400 | 01821 | 17.6 |  |  | Solar |  | 05_05_311W3 | 09/08/2025 | 09/11/2025 | 3 | 0 | 3 | 09/12/2025 | 09/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AMESBURY | 292831 | 01913 | 100 |  |  | Solar |  | 05_12_49W2 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 256 | 26 | 230 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 312556 | 01464 | 7.6 |  |  | Solar |  | 05_14_24L2 | 09/14/2020 | 09/16/2020 | 1 | 0 | 1 | 09/17/2020 | 09/17/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | OXFORD | 724912 | 01540 | 16 |  |  | Solar |  | 05_14_56L3 | 10/08/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RUTLAND | 256057 | 01543 | 10 |  |  | Solar |  | 05_14_70L2 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/10/2019 | 7/7/2020 | Y | EXP | 365 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 6/8/2020 | Connected |  | N
National Grid | FALL RIVER | 566104 | 02720 | 70 |  |  | Solar |  | 05_14_7L4 | 11/06/2023 | 11/21/2023 | 10 | 0 | 10 | 11/22/2023 | 11/22/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 11/06/2023 | 5/6/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | Y
National Grid | MARLBOROUGH | 177934 | 01752 | 15.2 |  |  | Solar |  | 05_01_23W1 | 06/19/2017 | 06/19/2017 | 27 | 27 | 0 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2017 |  | 6/25/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | SALEM | 585919 | 01970 | 23.4 |  |  | Solar |  | 05_01_406L4 | 01/31/2024 | 02/23/2024 | 16 | 14 | 2 | 02/26/2024 | 02/26/2024 | 32 | 29 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | CHELMSFORD | 174773 | 01824 | 57.5 |  |  | Solar |  | 05_01_55W1 | 01/17/2013 | 01/17/2013 | 10 | 8 | 2 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 5/1/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 | 10/4/2013 | Connected |  | N
National Grid | ANDOVER | 697565 | 01845 | 19 |  |  | Solar |  | 05_05_106W46 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 718553 | 01821 | 4995 |  |  | Other |  | 05_05_311W3 | 09/29/2025 | 10/30/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 12/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALISBURY | 371169 | 01952 | 100 |  |  | Solar |  | 05_12_49W2 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 | 07/21/2021 | 12/28/2022 | Y | STD | 61 |  |  | 0 | 0 | 0 |  |  | 12/30/2022 | Connected |  | N
National Grid | WORCESTER | 317800 | 01602 | 10 |  |  | Solar |  | 05_14_24L2 | 10/07/2020 | 11/04/2020 | 19 | 17 | 2 | 11/05/2020 | 11/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2021 | Connected |  | N
National Grid | OXFORD | 731974 | 01540 | 20 |  |  | Solar |  | 05_14_56L3 | 11/06/2025 | 11/12/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RUTLAND | 406289 | 01543 | 0 |  |  | Battery Add-On |  | 05_14_70L2 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 574923 | 02720 | 10 |  |  | Solar |  | 05_14_7L4 | 04/03/2024 | 12/07/2023 | 5 | 3 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/03/2024 | 5/14/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/19/2024 | Connected |  | N
National Grid | MARLBOROUGH | 178256 | 01752 | 900 |  |  | Solar |  | 05_01_23W1 | 04/16/2018 | 04/16/2018 | 15 | 15 | 0 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 04/16/2018 | 8/16/2023 | Y | STD | 1180 | 01/13/2021 | 08/03/2023 | 933 | 7 | 926 | 7/21/2023 | 8/3/2023 | 8/14/2023 | Connected |  | N
National Grid | SALEM | 602577 | 01970 | 10 |  |  | Solar |  | 05_01_406L4 | 04/12/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 174943 | 01824 | 3000 |  |  | Solar |  | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 732455 | 01921 | 15.2 |  |  | Solar |  | 05_05_106W46 | 11/12/2025 | 11/17/2025 | 2 | 0 | 2 | 11/18/2025 | 11/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 725014 | 01821 | 5.76 |  |  | Solar |  | 05_05_311W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 488516 | 01952 | 80 |  |  | Solar |  | 05_12_49W2 | 12/29/2022 | 01/23/2023 | 15 | 6 | 9 | 01/24/2023 | 01/24/2023 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/24/2025 | N | EXP | 105 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | WORCESTER | 343183 | 01609 | 9.6 |  |  | Solar |  | 05_14_24L2 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | OXFORD | 736628 | 01540 | 10 |  |  | Solar |  | 05_14_56L3 | 12/29/2025 |  | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | RUTLAND | 652181 | 01543 | 7.6 |  |  | Solar |  | 05_14_70L2 | 02/14/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | FALL RIVER | 608674 | 02720 | 3.8 |  |  | Solar |  | 05_14_7L4 | 05/03/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/03/2024 | 7/16/2025 | Y | EXP | 365 | 10/24/2024 | 11/20/2024 | 28 | 0 | 28 |  |  | 1/23/2025 | Connected |  | N
National Grid | MARLBOROUGH | 385653 | 01752 | 3.8 |  |  | Solar |  | 05_01_23W1 | 11/09/2021 | 01/07/2022 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/09/2021 | 5/7/2023 | Y | EXP | 485 | 04/13/2022 | 04/12/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 605711 | 01970 | 15.2 |  |  | Solar |  | 05_01_406L4 | 05/03/2024 | 05/09/2024 | 4 | 3 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N
National Grid | CHELMSFORD | 174942 | 01824 | 286 |  |  | Solar |  | 05_01_55W1 | 10/05/2011 | 10/05/2011 | 485 | 274 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 174254 | 01921 | 95 |  |  | Solar |  | 05_05_106W46 | 02/27/2012 | 02/27/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 02/27/2012 | 6/1/2012 | Y | EXP | -194 | 12/04/2012 | 12/17/2012 | 9 | 0 | 9 | 8/14/2012 | 8/14/2012 | 5/3/2013 | Connected |  | N
National Grid | BILLERICA | 726755 | 01821 | 15.2 |  |  | Solar |  | 05_05_311W3 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 511480 | 01952 | 15.2 |  |  | Solar |  | 05_12_49W2 | 03/22/2023 | 03/23/2023 | 1 | 0 | 1 | 03/24/2023 | 03/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 03/22/2023 | 4/26/2024 | Y | EXP | 365 | 07/28/2023 | 08/09/2023 | 13 | 0 | 13 |  |  | 8/14/2023 | Connected |  | N
National Grid | WORCESTER | 344721 | 01602 | 11.4 |  |  | Solar |  | 05_14_24L2 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 174172 | 01540 | 1000 |  |  | Solar |  | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 679382 | 01543 | 11.5 |  |  | Solar |  | 05_14_70L2 | 03/21/2025 | 03/25/2025 | 2 | 0 | 2 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2025 | Connected |  | N
National Grid | FALL RIVER | 635953 | 02720 | 5.76 |  |  | Solar |  | 05_14_7L4 | 08/28/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/28/2024 | 9/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | MARLBOROUGH | 425866 | 01752 | 9.074 |  |  | Solar |  | 05_01_23W1 | 05/05/2022 | 05/09/2022 | 2 | 0 | 2 | 05/10/2022 | 05/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2023 | Connected |  | N
National Grid | SALEM | 639121 | 01970 | 10 |  |  | Solar |  | 05_01_406L4 | 09/10/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 175139 | 01824 | 300 |  |  | Bio Gas |  | 05_01_55W1 | 04/23/2013 | 04/23/2013 | 6 | 0 | 6 | 05/02/2013 | 05/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2013 |  | 8/30/2013 | N | EXP | -89 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 4/16/2014 | Connected |  | N
National Grid | BOXFORD | 175001 | 01921 | 60 |  |  | Solar |  | 05_05_106W46 | 09/11/2013 | 09/11/2013 | 10 | 3 | 7 | 09/26/2013 | 09/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 |  | 9/26/2016 | N | EXP | 25 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/26/2016 | Connected |  | N
National Grid | BILLERICA | 727492 | 01862 | 20.14 |  |  | Solar |  | 05_05_311W3 | 10/17/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALISBURY | 559364 | 01952 | 5 |  |  | Solar |  | 05_12_49W2 | 10/17/2023 | 10/19/2023 | 2 | 0 | 2 | 10/20/2023 | 10/20/2023 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2024 | Connected |  | N
National Grid | WORCESTER | 379424 | 01603 | 7.6 |  |  | Solar |  | 05_14_24L2 | 09/21/2021 | 12/16/2021 | 3 | 0 | 3 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 174171 | 01540 | 1000 |  |  | Solar |  | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 176707 | 01543 | 3.8 |  |  | Solar |  | 05_14_70L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2015 |  | 11/2/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 7/26/2016 | Connected |  | N
National Grid | FALL RIVER | 653448 | 02720 | 7.6 |  |  | Solar |  | 05_14_7L4 | 12/06/2024 | 12/27/2024 | 8 | 2 | 6 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | MARLBOROUGH | 445969 | 01752 | 7.6 |  |  | Solar |  | 05_01_23W1 | 07/21/2022 | 07/22/2022 | 1 | 0 | 1 | 07/25/2022 | 07/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | SALEM | 646413 | 01970 | 10 |  |  | Solar |  | 05_01_406L4 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/18/2024 | 2/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 175272 | 01824 | 997.6 |  |  | Solar |  | 05_01_55W1 | 06/23/2014 | 06/23/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/23/2014 | 6/1/2016 | Y | STD | 469 | 11/29/2016 | 01/16/2017 | 32 | 0 | 32 | 1/13/2017 | 1/13/2017 | 1/13/2017 | Connected |  | N
National Grid | BOXFORD | 273678 | 01921 | 4200 |  |  | Solar |  | 05_05_106W46 | 01/30/2020 | 02/19/2020 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2020 | 03/24/2020 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 739918 | 01821 | 10 |  |  | Solar |  | 05_05_311W3 | 12/12/2025 | 12/17/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALISBURY | 628651 | 01952 | 3.8 |  |  | Solar |  | 05_12_49W2 | 08/06/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | WORCESTER | 408495 | 01609 | 0 |  |  | Solar |  | 05_14_24L2 | 11/29/2022 |  | 220 | 204 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 174156 | 01540 | 1000 |  |  | Solar |  | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/5/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 178184 | 01543 | 3.8 |  |  | Solar |  | 05_14_70L3 | 04/13/2018 | 04/13/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  | 4/21/2019 | N | EXP | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 501405 | 02720 | 180 |  |  | Solar |  | 05_14_8L1 | 05/10/2023 | 05/31/2023 | 14 | 5 | 9 | 06/01/2023 | 06/01/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 502980 | 01752 | 15.2 |  |  | Solar |  | 05_01_23W1 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | SALEM | 646924 | 01970 | 5.76 |  |  | Solar |  | 05_01_406L4 | 10/29/2024 | 12/03/2024 | 11 | 5 | 6 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 10/29/2024 | 1/24/2026 | Y | EXP | 365 | 02/15/2025 | 02/27/2025 | 13 | 0 | 13 |  |  | 4/12/2025 | Connected |  | N
National Grid | CHELMSFORD | 175296 | 01824 | 19.25 |  |  | Solar |  | 05_01_55W1 | 01/14/2015 | 01/14/2015 | 4 | 2 | 2 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/10/2015 | Connected |  | N
National Grid | ANDOVER | 396688 | 01845 | 0 |  |  | Other |  | 05_05_106W46 | 01/04/2022 | 01/13/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 01/27/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 175946 | 01821 | 2.4 |  |  | Solar |  | 05_05_311W3 | 03/17/2015 | 03/17/2015 | 3 | 2 | 1 | 03/23/2015 | 03/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/17/2015 | N | EXP | 113 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 5/5/2017 | Connected |  | N
National Grid | SALISBURY | 640219 | 01952 | 3.8 |  |  | Solar |  | 05_12_49W2 | 09/13/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WORCESTER | 517472 | 01602 | 8.7 |  |  | Solar |  | 05_14_24L2 | 05/22/2023 | 05/26/2023 | 4 | 0 | 4 | 05/30/2023 | 05/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 7/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | Y
National Grid | OXFORD | 174155 | 01540 | 1000 |  |  | Solar |  | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 190106 | 01543 | 6 |  |  | Solar |  | 05_14_70L3 | 07/11/2018 | 07/18/2018 | 0 | 0 | 0 | 07/19/2018 | 07/19/2018 | 49 | 1 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 725174 | 02720 | 7.6 |  |  | Solar |  | 05_14_8L1 | 10/08/2025 | 11/17/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 553654 | 01752 | 3.8 |  |  | Solar |  | 05_01_23W1 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 108 | 28 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 650792 | 01970 | 8.41 |  |  | Solar |  | 05_01_406L4 | 11/01/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | CHELMSFORD | 175294 | 01824 | 6 |  |  | Solar |  | 05_01_55W1 | 01/13/2015 | 01/13/2015 | 28 | 27 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 5/31/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 4/28/2015 | 4/28/2015 | 11/12/2015 | Connected |  | N
National Grid | ANDOVER | 410239 | 01845 | 500 |  |  | Solar |  | 05_05_106W46 | 03/10/2022 | 04/06/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2022 | 04/20/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176678 | 01852 | 6 |  |  | Solar |  | 05_05_311W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/11/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 7/26/2016 | 7/26/2016 | 8/23/2016 | Connected |  | N
National Grid | SALISBURY | 647501 | 01952 | 5.76 |  |  | Solar |  | 05_12_49W2 | 10/22/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/22/2024 | 1/6/2026 | Y | EXP | 365 | 02/12/2025 | 03/01/2025 | 18 | 0 | 18 |  |  | 5/2/2025 | Connected |  | N
National Grid | WORCESTER | 566273 | 01609 | 4.095 |  |  | Solar |  | 05_14_24L2 | 10/31/2023 | 11/02/2023 | 2 | 0 | 2 | 11/03/2023 | 11/03/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 10/31/2023 | 12/26/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | OXFORD | 175071 | 01540 | 11.61 |  |  | Solar |  | 05_14_56L3 | 04/08/2013 | 04/08/2013 | 5 | 0 | 5 | 04/17/2013 | 04/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2013 |  | 7/31/2013 | N | EXP | 85 |  |  | 0 | 0 | 0 | 5/7/2013 | 5/7/2013 | 7/29/2013 | Connected |  | N
National Grid | RUTLAND | 253690 | 01543 | 10 |  |  | Solar |  | 05_14_70L3 | 09/17/2019 | 09/30/2019 | 8 | 2 | 6 | 10/01/2019 | 10/01/2019 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 9/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2020 | Connected |  | N
National Grid | FALL RIVER | 728119 | 02720 | 10 |  |  | Solar |  | 05_14_8L1 | 10/21/2025 | 11/03/2025 | 8 | 2 | 6 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 622231 | 01752 | 7.6 |  |  | Solar |  | 05_01_23W1 | 07/02/2024 | 07/12/2024 | 4 | 0 | 4 | 07/15/2024 | 07/15/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/02/2024 | 12/31/2025 | Y | EXP | 365 | 05/10/2025 |  | 237 | 0 | 237 |  |  | 12/22/2025 | Connected |  | N
National Grid | SALEM | 657763 | 01970 | 10 |  |  | Solar |  | 05_01_406L4 | 12/02/2024 | 01/13/2025 | 16 | 11 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | CHELMSFORD | 175339 | 01824 | 222 |  |  | Solar |  | 05_01_55W1 | 01/20/2015 | 01/20/2015 | 5 | 1 | 4 | 01/28/2015 | 01/28/2015 | 581 | 0 | 581 | 03/27/2015 | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 5/5/2015 | 01/20/2015 | 12/31/2016 | Y | EXP | 606 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 537794 | 01845 | 7.6 |  |  | Solar |  | 05_05_106W46 | 07/12/2023 | 07/13/2023 | 1 | 0 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | Y
National Grid | CHELMSFORD | 184521 | 01824 | 17.6 |  |  | Solar |  | 05_05_311W3 | 05/04/2018 | 05/04/2018 | 16 | 2 | 14 | 06/06/2018 | 06/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | ANDOVER | 688394 | 01810 | 15.2 |  |  | Solar |  | 05_12_49W2 | 04/29/2025 | 05/01/2025 | 2 | 0 | 2 | 05/02/2025 | 05/02/2025 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 638354 | 01609 | 15.356 |  |  | Solar |  | 05_14_24L2 | 09/13/2024 | 09/18/2024 | 3 | 0 | 3 | 09/19/2024 | 09/19/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/1/2025 | Y | EXP | 365 | 12/18/2024 |  | 380 | 1 | 379 |  |  | 3/11/2025 | Connected |  | N
National Grid | OXFORD | 175388 | 01540 | 15.2 |  |  | Solar |  | 05_14_56L3 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/1/2014 | N | EXP | 54 |  |  | 0 | 0 | 0 | 10/8/2014 | 10/8/2014 | 12/26/2014 | Connected |  | N
National Grid | RUTLAND | 313391 | 01543 | 10 |  |  | Solar |  | 05_14_70L3 | 09/17/2020 | 10/27/2020 | 26 | 25 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | Y
National Grid | FALL RIVER | 177700 | 02720 | 7.6 |  |  | Solar |  | 05_14_8L1 | 03/21/2017 | 03/21/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2017 |  | 3/27/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/20/2017 | 6/20/2017 | 7/12/2017 | Connected |  | N
National Grid | MARLBOROUGH | 629723 | 01752 | 3.8 |  |  | Solar |  | 05_01_23W1 | 08/02/2024 | 09/18/2024 | 28 | 25 | 3 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2024 | Connected |  | N
National Grid | SALEM | 683430 | 01970 | 7.6 |  |  | Solar |  | 05_01_406L4 | 04/10/2025 | 04/28/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/10/2025 | 6/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | CHELMSFORD | 175371 | 01824 | 46.08 |  |  | Solar |  | 05_01_55W1 | 02/14/2014 | 02/14/2014 | 5 | 0 | 5 | 02/25/2014 | 02/25/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2014 | 02/14/2014 | 8/29/2014 | Y | EXP | 57 | 01/06/2015 | 01/06/2015 | 0 | 0 | 0 | 3/2/2015 | 3/2/2015 | 3/5/2015 | Connected |  | N
National Grid | ANDOVER | 619984 | 01845 | 50 |  |  | Solar |  | 05_05_106W46 | 07/01/2024 | 09/16/2024 | 53 | 45 | 8 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 |  | 4/11/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | Y
National Grid | LOWELL | 190641 | 01852 | 11.4 |  |  | Solar |  | 05_05_311W3 | 07/13/2018 | 09/10/2018 | 23 | 9 | 14 | 09/11/2018 | 09/11/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 07/13/2018 | 10/10/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2019 | Connected |  | N
National Grid | LAWRENCE | 641227 | 01843 | 0 |  |  | Other |  | 05_12_49W4 | 07/12/2025 | 11/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 656616 | 01602 | 9.28 |  |  | Solar |  | 05_14_24L2 | 11/25/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y
National Grid | OXFORD | 175526 | 01540 | 750 |  |  | Solar |  | 05_14_56L3 | 07/29/2014 | 07/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/21/2014 | 12/01/2014 | 27 | 1 | 26 | 08/07/2014 | 09/05/2014 | 20 | 0 | 20 |  | 12/01/2014 | 27 | 1 | 26 |  |  | 0 | 0 | 0 | 4/3/2015 | 07/29/2014 | 9/8/2017 | Y | STD | 889 | 02/24/2017 | 09/12/2017 | 138 | 0 | 138 | 8/18/2017 | 8/18/2017 | 9/15/2017 | Connected |  | N
National Grid | RUTLAND | 449194 | 01543 | 15.2 |  |  | Solar |  | 05_14_70L3 | 08/03/2022 | 08/11/2022 | 6 | 4 | 2 | 08/12/2022 | 08/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 |  | 11/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2023 | Connected |  | N
National Grid | FALL RIVER | 178499 | 02720 | 20 |  |  | Solar |  | 05_14_8L1 | 01/23/2018 | 01/23/2018 | 11 | 0 | 11 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/29/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 8/2/2018 | Connected |  | N
National Grid | MARLBOROUGH | 690729 | 01752 | 7.6 |  |  | Solar |  | 05_01_23W1 | 05/09/2025 | 05/28/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 694012 | 01970 | 7.6 |  |  | Solar |  | 05_01_406L4 | 05/29/2025 | 06/20/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 10/11/2025 | 10/10/2025 | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | CHELMSFORD | 175471 | 01824 | 4.75 |  |  | Solar |  | 05_01_55W1 | 12/01/2014 | 12/01/2014 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2014 | 01/02/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2015 |  | 4/30/2015 | N | STD | 118 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/10/2015 | Connected |  | N
National Grid | BOXFORD | 650823 | 01921 | 3.8 |  |  | Solar |  | 05_05_106W46 | 10/30/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 193918 | 01862 | 6 |  |  | Solar |  | 05_05_311W3 | 08/20/2018 | 10/12/2018 | 27 | 24 | 3 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | LAWRENCE | 687682 | 01843 | 15.2 |  |  | Solar |  | 05_14_24L2 | 04/25/2025 | 04/29/2025 | 2 | 0 | 2 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | WORCESTER | 176627 | 01602 | 1000 |  |  | Solar |  | 05_14_56L3 | 10/15/2015 | 10/15/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2017 | 10/15/2015 | 3/22/2019 | Y | STD | 695 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 449174 | 01540 | 15.2 |  |  | Solar |  | 05_14_70L3 | 08/03/2022 | 08/19/2022 | 13 | 12 | 1 | 08/22/2022 | 08/22/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 08/03/2022 | 10/10/2023 | Y | EXP | 365 | 10/19/2022 | 10/28/2022 | 10 | 0 | 10 |  |  | 8/30/2023 | Connected |  | N
National Grid | RUTLAND | 184904 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 05/28/2018 | 05/28/2018 | 1 | 0 | 1 | 05/31/2018 | 05/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 1/8/2020 | N | EXP | 448 | 10/24/2019 | 11/04/2019 | 11 | 0 | 11 |  |  | 11/20/2019 | Connected |  | N
National Grid | FALL RIVER | 172485 | 02720 | 6 |  |  | Solar |  | 05_01_23W2 | 04/12/2018 | 04/12/2018 | 9 | 0 | 9 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 | 04/12/2018 | 7/23/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | MARLBOROUGH | 701278 | 01752 | 18.24 |  |  | Solar |  | 05_01_406L4 | 07/02/2025 | 07/17/2025 | 9 | 7 | 2 | 07/18/2025 | 07/18/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 175638 | 01970 | 15.8 |  |  | Solar |  | 05_01_55W1 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2014 |  | 2/6/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 5/27/2016 | Connected |  | N
National Grid | CHELMSFORD | 664362 | 01824 | 5.76 |  |  | Solar |  | 05_05_106W46 | 01/08/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/08/2025 | 3/17/2026 | Y | EXP | 365 | 04/15/2025 | 05/13/2025 | 29 | 0 | 29 |  |  | 7/8/2025 | Connected |  | N
National Grid | BOXFORD | 194787 | 01921 | 7.6 |  |  | Solar |  | 05_05_311W3 | 08/30/2018 | 11/14/2018 | 29 | 25 | 4 | 11/15/2018 | 11/15/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 683682 | 01852 | 0 |  |  | Other |  | 05_12_49W4 | 12/29/2025 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 707310 | 01843 | 23 |  |  | Solar |  | 05_14_24L2 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | WORCESTER | 177771 | 01609 | 15.2 |  |  | Solar |  | 05_14_56L3 | 10/10/2017 | 10/10/2017 | 13 | 4 | 9 | 11/06/2017 | 11/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/16/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 5/23/2018 | Connected |  | N
National Grid | OXFORD | 396676 | 01540 | 0 |  |  | Battery Add-On |  | 05_14_70L3 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/16/2022 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 197977 | 01543 | 10 |  |  | Solar |  | 05_14_8L1 | 10/08/2018 | 11/26/2018 | 16 | 16 | 0 | 11/27/2018 | 11/27/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 | 10/08/2018 | 8/28/2019 | Y | EXP | 257 | 04/23/2019 | 05/03/2019 | 10 | 0 | 10 |  |  | 7/23/2019 | Connected |  | N
National Grid | FALL RIVER | 207061 | 02720 | 15.2 |  |  | Solar |  | 05_01_23W2 | 01/30/2019 | 02/12/2019 | 7 | 0 | 7 | 02/13/2019 | 02/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 |  | 2/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | MARLBOROUGH | 710676 | 01752 | 15.58 |  |  | Solar |  | 05_01_406L4 | 08/08/2025 | 08/18/2025 | 5 | 0 | 5 | 08/19/2025 | 08/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | PEPPERELL | 175720 | 01463 | 499 |  |  | Solar |  | 05_01_55W1 | 12/31/2014 | 12/31/2014 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/15/2015 | 02/12/2015 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 667950 | 01824 | 5.76 |  |  | Solar |  | 05_05_106W46 | 01/27/2025 | 03/28/2025 | 13 | 8 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 201858 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 11/21/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2020 | Connected |  | N
National Grid | CHELMSFORD | 290691 | 01824 | 0 |  |  | Battery Add-On |  | 05_12_49W4 | 05/06/2020 | 05/06/2020 | 0 | 0 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2020 | Connected |  | N
National Grid | ANDOVER | 656244 | 01810 | 5.76 |  |  | Solar |  | 05_14_24L3 | 11/22/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/22/2024 | 3/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 177817 | 01609 | 11.4 |  |  | Solar |  | 05_14_56L3 | 04/04/2017 | 04/04/2017 | 2 | 0 | 2 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N
National Grid | OXFORD | 431972 | 01540 | 11.4 |  |  | Solar |  | 05_14_70L3 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N
National Grid | RUTLAND | 199566 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 10/26/2018 | 11/20/2018 | 13 | 7 | 6 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 10/26/2018 | 12/11/2019 | Y | EXP | 365 | 06/05/2019 | 06/04/2019 | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | FALL RIVER | 209250 | 02720 | 9.92 |  |  | Solar |  | 05_01_23W2 | 03/19/2019 | 03/28/2019 | 6 | 0 | 6 | 03/29/2019 | 03/29/2019 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2019 | 03/19/2019 | 4/29/2020 | Y | EXP | 365 | 02/22/2020 | 02/21/2020 | 0 | 0 | 0 |  |  | 4/21/2020 | Connected |  | N
National Grid | MARLBOROUGH | 716071 | 01752 | 15.2 |  |  | Solar |  | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | Y
National Grid | PEPPERELL | 175828 | 01463 | 10 |  |  | Solar |  | 05_01_55W1 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/27/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/4/2016 | 4/4/2016 | 4/8/2016 | Connected |  | N
National Grid | CHELMSFORD | 688748 | 01824 | 18.24 |  |  | Solar |  | 05_05_106W46 | 04/30/2025 | 05/01/2025 | 1 | 0 | 1 | 05/02/2025 | 05/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/30/2025 | 7/17/2026 | Y | EXP | 365 | 08/15/2025 | 10/08/2025 | 55 | 0 | 55 |  |  | 10/10/2025 | Connected |  | N
National Grid | ANDOVER | 233442 | 01845 | 400 |  |  | Solar |  | 05_05_311W3 | 04/15/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/15/2020 | 11/30/2021 | Y | STD | 120 | 09/08/2021 | 09/07/2021 | 0 | 0 | 0 |  |  | 11/24/2021 | Connected |  | N
National Grid | CHELMSFORD | 357389 | 01824 | 200 |  |  | Solar |  | 05_12_49W4 | 05/28/2021 | 03/18/2022 | 202 | 186 | 16 | 03/21/2022 | 03/21/2022 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 05/28/2021 | 11/25/2023 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | LAWRENCE | 677775 | 01843 | 13.36 |  |  | Solar |  | 05_14_24L3 | 03/13/2025 | 03/24/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/13/2025 | 6/12/2026 | Y | EXP | 365 | 08/22/2025 |  | 133 | 2 | 131 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 178587 | 01609 | 20 |  |  | Solar |  | 05_14_56L3 | 03/13/2018 | 03/13/2018 | 13 | 0 | 13 | 04/02/2018 | 04/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/19/2019 | N | EXP | 312 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 482365 | 01540 | 7.6 |  |  | Solar |  | 05_14_70L3 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | RUTLAND | 256188 | 01543 | 24 |  |  | Solar |  | 05_14_8L1 | 10/20/2019 |  | 99 | 95 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 310622 | 02720 | 11.4 |  |  | Solar |  | 05_01_23W2 | 06/23/2021 | 06/25/2021 | 2 | 0 | 2 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 648624 | 01752 | 4990 |  |  | Other |  | 05_01_408L1 | 02/20/2025 | 04/30/2025 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2025 | 05/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALEM | 175887 | 01970 | 7.6 |  |  | Solar |  | 05_01_55W1 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 9/22/2015 | 9/22/2015 | 10/2/2015 | Connected |  | N
National Grid | CHELMSFORD | 663333 | 01824 | 2.32 |  |  | Solar |  | 05_05_106W81 | 01/02/2025 | 01/23/2025 | 11 | 7 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 233157 | 01921 | 166.6 |  |  | Solar |  | 05_05_311W3 | 03/25/2020 | 03/31/2020 | 3 | 0 | 3 |  |  | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 03/25/2020 | 10/20/2021 | Y | STD | 112 | 08/20/2021 | 08/19/2021 | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | BILLERICA | 431968 | 01862 | 7.83 |  |  | Solar |  | 05_12_49W4 | 06/30/2022 | 07/05/2022 | 3 | 2 | 1 | 07/06/2022 | 07/06/2022 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/30/2022 | 5/22/2024 | Y | EXP | 365 | 11/15/2022 | 05/19/2023 | 186 | 0 | 186 |  |  | 6/17/2023 | Connected |  | N
National Grid | LAWRENCE | 174751 | 01843 | 150 |  |  | Solar |  | 05_14_24L3 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 39 | 529 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2013 |  | 9/30/2014 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 189024 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 08/24/2018 | 09/26/2018 | 22 | 15 | 7 | 09/27/2018 | 09/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 | 08/24/2018 |  | Y | EXP | 365 | 03/22/2019 | 03/21/2019 | 0 | 0 | 0 |  |  | 7/3/2019 | Connected |  | N
National Grid | OXFORD | 503539 | 01540 | 6.3 |  |  | Solar |  | 05_14_70L3 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 6/22/2024 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 332871 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 371778 | 02720 | 11.4 |  |  | Solar |  | 05_01_23W2 | 07/23/2021 | 07/26/2021 | 1 | 0 | 1 | 07/27/2021 | 07/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  | 3/24/2023 | N | EXP | 535 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175914 | 01752 | 1500 |  |  | Solar |  | 05_01_408L1 | 03/12/2015 | 03/12/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2015 | 05/12/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 07/12/2016 | 10/06/2016 | 61 | 0 | 61 | 10/11/2016 | 03/12/2015 | 10/31/2017 | Y | STD | 385 | 06/22/2017 | 02/28/2018 | 165 | 0 | 165 | 10/18/2017 | 10/18/2017 | 11/29/2017 | Connected |  | N
National Grid | SALEM | 176009 | 01970 | 2230 |  |  | Solar |  | 05_01_55W1 | 08/13/2015 | 08/18/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 | 08/13/2015 | 9/19/2019 | Y | STD | 846 | 11/09/2018 | 01/31/2019 | 83 | 0 | 83 | 6/7/2019 | 6/19/2019 | 8/28/2019 | Connected |  | N
National Grid | CHELMSFORD | 175183 | 01824 | 60 |  |  | Natural Gas |  | 05_05_106W81 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 | 05/17/2013 | 05/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2013 |  | 9/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/31/2013 | Connected |  | N
National Grid | BOXFORD | 249197 | 01921 | 7.6 |  |  | Solar |  | 05_05_311W3 | 10/03/2019 | 10/11/2019 | 6 | 5 | 1 | 10/15/2019 | 10/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 444421 | 01824 | 0 |  |  | Other |  | 05_12_49W4 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175758 | 01843 | 150 |  |  | Solar |  | 05_14_24L3 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | WORCESTER | 198628 | 01609 | 20 |  |  | Solar |  | 05_14_56L3 | 10/17/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | Connected |  | N
National Grid | AUBURN | 544628 | 01501 | 0 |  |  | Solar |  | 05_14_70L3 | 07/31/2023 | 08/01/2023 | 1 | 0 | 1 | 08/02/2023 | 08/02/2023 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 9/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | RUTLAND | 342617 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 04/02/2021 | 04/15/2021 | 8 | 0 | 8 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | FALL RIVER | 371327 | 02720 | 19 |  |  | Solar |  | 05_01_23W2 | 07/21/2021 | 08/17/2021 | 19 | 18 | 1 | 08/18/2021 | 08/18/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | MARLBOROUGH | 193813 | 01752 | 86.4 |  |  | Solar |  | 05_01_408L1 | 08/17/2018 | 08/23/2018 | 3 | 0 | 3 | 08/24/2018 | 08/24/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176053 | 01970 | 22.58 |  |  | Solar |  | 05_01_55W1 | 01/29/2015 | 01/29/2015 | 5 | 4 | 1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/10/2015 | 3/10/2015 | 6/10/2015 | Connected |  | N
National Grid | CHELMSFORD | 176482 | 01824 | 144 |  |  | Solar |  | 05_05_106W81 | 05/20/2016 | 05/20/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 337 | 10/10/2016 | 11/04/2016 | 18 | 0 | 18 | 12/6/2016 | 12/6/2016 | 12/8/2016 | Connected |  | N
National Grid | BOXFORD | 287957 | 01921 | 200 |  |  | Solar |  | 05_05_311W3 | 04/16/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/16/2020 | 9/6/2022 | Y | STD | 300 | 05/10/2022 | 05/09/2022 | 0 | 0 | 0 |  |  | 5/19/2022 | Connected |  | N
National Grid | CHELMSFORD | 492195 | 01824 | 750 |  |  | Solar |  | 05_12_49W4 | 04/07/2023 | 06/12/2023 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2023 | 07/12/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 199628 | 01810 | 3.8 |  |  | Solar |  | 05_14_24L3 | 10/29/2018 | 12/18/2018 | 25 | 24 | 1 | 12/19/2018 | 12/19/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2019 |  | 10/11/2019 | N | EXP | 238 |  |  | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | WORCESTER | 203369 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | STURBRIDGE | 655143 | 01518 | 7.6 |  |  | Solar |  | 05_14_70L3 | 11/20/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | RUTLAND | 349605 | 01543 | 6 |  |  | Solar |  | 05_14_8L1 | 04/23/2021 | 01/06/2022 | 2 | 0 | 2 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 379039 | 02720 | 15.2 |  |  | Solar |  | 05_01_23W2 | 08/31/2021 | 09/20/2021 | 13 | 13 | 0 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 7/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 191478 | 01752 | 15.2 |  |  | Solar |  | 05_01_408L1 | 07/23/2018 | 08/29/2018 | 26 | 0 | 26 | 08/30/2018 | 08/30/2018 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 176118 | 01970 | 6 |  |  | Solar |  | 05_01_55W1 | 08/21/2015 | 08/21/2015 | 13 | 13 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2015 |  | 8/30/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 4/14/2016 | 4/14/2016 | 4/25/2016 | Connected |  | N
National Grid | CHELMSFORD | 364046 | 01824 | 6.24 |  |  | Solar |  | 05_05_106W81 | 07/12/2021 | 07/13/2021 | 2 | 1 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2021 | 07/12/2021 | 2/8/2023 | Y | EXP | 365 | 12/03/2021 | 02/08/2022 | 68 | 0 | 68 |  |  | 2/10/2022 | Connected |  | N
National Grid | BOXFORD | 297691 | 01921 | 66.6 |  |  | Solar |  | 05_05_311W3 | 06/30/2020 | 07/27/2020 | 18 | 18 | 0 | 07/28/2020 | 07/28/2020 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | BILLERICA | 530784 | 01862 | 7.6 |  |  | Solar |  | 05_12_49W4 | 06/12/2023 | 06/14/2023 | 2 | 0 | 2 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 341279 | 01843 | 133.2 |  |  | Solar |  | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 7/31/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | WORCESTER | 213064 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 03/11/2019 | 03/21/2019 | 7 | 0 | 7 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | STURBRIDGE | 662120 | 01566 | 7.6 |  |  | Solar |  | 05_14_70L3 | 12/21/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 396873 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 12/08/2021 | 01/06/2022 | 5 | 4 | 1 | 12/15/2021 | 12/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 485090 | 02720 | 17.45 |  |  | Solar |  | 05_01_23W2 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2023 | Connected |  | N
National Grid | MARLBOROUGH | 503087 | 01752 | 22.62 |  |  | Solar |  | 05_01_408L1 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N
National Grid | SALEM | 176129 | 01970 | 4.3 |  |  | Solar |  | 05_01_55W1 | 04/13/2015 | 04/13/2015 | 3 | 2 | 1 | 04/16/2015 | 04/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 8/31/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 8/26/2015 | Connected |  | N
National Grid | CHELMSFORD | 451467 | 01824 | 5.76 |  |  | Solar |  | 05_05_106W81 | 10/27/2022 | 11/13/2022 | 11 | 9 | 2 | 11/14/2022 | 11/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | Y
National Grid | BOXFORD | 311908 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 09/10/2020 | 09/11/2020 | 0 | 0 | 0 | 09/14/2020 | 09/14/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2020 |  | 9/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 618836 | 01824 | 0 |  |  | Battery Add-On |  | 05_12_49W4 | 06/18/2024 | 06/21/2024 | 3 | 1 | 2 | 06/24/2024 | 06/24/2024 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | LAWRENCE | 341278 | 01843 | 166.6 |  |  | Solar |  | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/14/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | WORCESTER | 236527 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 06/13/2019 | 06/18/2019 | 2 | 0 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/13/2019 | 6/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2020 | Connected |  | N
National Grid | STURBRIDGE | 306207 | 01566 | 246.6 |  |  | Solar |  | 05_14_70L4 | 02/03/2021 | 02/17/2021 | 8 | 0 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 | 02/03/2021 | 5/21/2026 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RUTLAND | 426466 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 06/01/2022 | 06/07/2022 | 4 | 0 | 4 | 06/08/2022 | 06/08/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 542998 | 02720 | 22.8 |  |  | Solar |  | 05_01_23W2 | 09/22/2023 | 10/05/2023 | 9 | 8 | 1 | 10/06/2023 | 10/06/2023 | 81 | 34 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 516424 | 01752 | 7.6 |  |  | Solar |  | 05_01_408L1 | 04/04/2023 | 04/10/2023 | 5 | 4 | 1 | 04/11/2023 | 04/11/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2023 |  | 6/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2023 | Connected |  | N
National Grid | SALEM | 176264 | 01970 | 380 |  |  | Landfill Gas |  | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2015 | 10/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/14/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 456820 | 01824 | 6 |  |  | Solar |  | 05_05_106W81 | 01/26/2023 | 05/02/2023 | 65 | 65 | 0 | 05/03/2023 | 05/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | BOXFORD | 328441 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 11/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | CHELMSFORD | 652802 | 01824 | 10 |  |  | Solar |  | 05_12_49W4 | 12/11/2024 | 12/30/2024 | 12 | 9 | 3 | 12/31/2024 | 12/31/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | LAWRENCE | 341277 | 01843 | 180 |  |  | Solar |  | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/10/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | WORCESTER | 285483 | 01609 | 9.28 |  |  | Solar |  | 05_14_56L3 | 03/27/2020 | 03/31/2020 | 2 | 2 | 0 | 04/01/2020 | 04/01/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 03/27/2020 | 3/31/2021 | Y | EXP | 365 | 06/09/2020 | 06/25/2020 | 16 | 0 | 16 |  |  | 10/7/2020 | Connected |  | N
National Grid | STURBRIDGE | 636406 | 01518 | 200 |  |  | Solar |  | 05_14_70L4 | 09/06/2024 | 10/23/2024 | 32 | 23 | 9 | 10/24/2024 | 10/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/06/2024 | 5/29/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | RUTLAND | 431131 | 01543 | 6 |  |  | Solar |  | 05_14_8L1 | 05/26/2022 | 05/31/2022 | 2 | 0 | 2 | 06/01/2022 | 06/01/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 575450 | 02720 | 7.6 |  |  | Solar |  | 05_01_23W2 | 12/04/2023 | 01/09/2024 | 25 | 24 | 1 | 01/10/2024 | 01/10/2024 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 567984 | 01752 | 4956 |  |  | Solar |  | 05_01_408L1 | 04/15/2024 |  | 170 | 160 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176262 | 01970 | 10 |  |  | Solar |  | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | CHELMSFORD | 512760 | 01824 | 6 |  |  | Solar |  | 05_05_106W81 | 07/18/2023 |  | 81 | 79 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 333111 | 01921 | 5.76 |  |  | Solar |  | 05_05_311W3 | 03/22/2021 | 03/24/2021 | 1 | 1 | 0 | 03/25/2021 | 03/25/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 4/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid | LOWELL | 657217 | 01852 | 3.8 |  |  | Solar |  | 05_12_49W4 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | LAWRENCE | 605610 | 01843 | 12.35 |  |  | Solar |  | 05_14_24L3 | 04/23/2024 | 05/15/2024 | 11 | 9 | 2 | 05/16/2024 | 05/16/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/23/2024 | 6/7/2025 | Y | EXP | 365 | 07/02/2024 | 07/02/2024 | 1 | 0 | 1 |  |  | 8/8/2024 | Connected |  | N
National Grid | WORCESTER | 290378 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 05/04/2020 | 05/12/2020 | 5 | 0 | 5 | 05/13/2020 | 05/13/2020 | 66 | 56 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 11/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | STURBRIDGE | 714533 | 01566 | 500 |  |  | Solar |  | 05_14_70L4 | 10/10/2025 | 11/10/2025 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | RUTLAND | 507185 | 01543 | 0 |  |  | Solar |  | 05_14_8L1 | 05/02/2023 | 06/12/2023 | 28 | 25 | 3 | 06/13/2023 | 06/13/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 05/02/2023 | 8/11/2025 | Y | EXP | 730 | 04/30/2024 | 05/29/2024 | 30 | 0 | 30 |  |  | 10/1/2024 | Connected |  | N
National Grid | FALL RIVER | 581452 | 02720 | 7.6 |  |  | Solar |  | 05_01_23W2 | 01/04/2024 | 01/17/2024 | 9 | 7 | 2 | 01/18/2024 | 01/18/2024 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | MARLBOROUGH | 623841 | 01752 | 10 |  |  | Solar |  | 05_01_408L1 | 07/10/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 07/10/2024 | 12/3/2025 | Y | EXP | 365 | 04/15/2025 | 10/27/2025 | 196 | 0 | 196 |  |  | 10/28/2025 | Connected |  | N
National Grid | SALEM | 176290 | 01970 | 22.8 |  |  | Solar |  | 05_01_55W1 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 07/10/2015 | 7/18/2016 | Y | EXP | 354 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 1/19/2017 | Connected |  | N
National Grid | CHELMSFORD | 607663 | 01824 | 6 |  |  | Solar |  | 05_05_106W81 | 04/30/2024 | 05/16/2024 | 4 | 0 | 4 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/30/2024 | 7/9/2025 | Y | EXP | 365 | 09/17/2024 | 12/17/2024 | 92 | 0 | 92 |  |  | 1/6/2025 | Connected |  | Y
National Grid | BOXFORD | 416970 | 01921 | 19 |  |  | Solar |  | 05_05_311W3 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2022 | 03/10/2022 | 6/3/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | BILLERICA | 646626 | 01862 | 170 |  |  | Solar |  | 05_12_49W6 | 11/04/2024 | 12/13/2024 | 26 | 17 | 9 | 12/16/2024 | 12/16/2024 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 11/04/2024 | 7/5/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LAWRENCE | 734759 | 01843 | 23 |  |  | Solar |  | 05_14_275L2 | 11/19/2025 | 11/20/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 317831 | 01609 | 25 |  |  | Solar |  | 05_14_56L3 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | STURBRIDGE | 175414 | 01566 | 76 |  |  | Solar |  | 05_14_70L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 | 07/09/2014 | 11/28/2014 | Y | EXP | 116 | 03/27/2015 | 05/11/2015 | 30 | 0 | 30 | 8/7/2014 | 8/7/2014 | 7/20/2015 | Connected |  | N
National Grid | RUTLAND | 519443 | 01543 | 11.375 |  |  | Solar |  | 05_14_8L1 | 09/14/2023 | 09/29/2023 | 11 | 10 | 1 | 10/02/2023 | 10/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 615221 | 02720 | 9.88 |  |  | Solar |  | 05_01_23W2 | 06/03/2024 | 07/03/2024 | 5 | 2 | 3 | 07/05/2024 | 07/05/2024 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/03/2024 | 7/19/2026 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 632114 | 01752 | 7.6 |  |  | Solar |  | 05_01_408L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/21/2024 | 9/20/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | SALEM | 176356 | 01970 | 5 |  |  | Solar |  | 05_01_55W1 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 10/1/2015 | Connected |  | N
National Grid | CHELMSFORD | 630417 | 01824 | 5.76 |  |  | Solar |  | 05_05_106W81 | 08/06/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/06/2024 | 8/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | ANDOVER | 491445 | 01845 | 15.2 |  |  | Solar |  | 05_05_311W3 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 47 | 25 | 22 | 04/25/2023 | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 8/16/2024 | N | EXP | 365 | 07/26/2023 | 08/10/2023 | 16 | 0 | 16 |  |  | 10/16/2023 | Connected |  | Y
National Grid | BILLERICA | 707425 | 01862 | 50 |  |  | Solar |  | 05_12_49W6 | 08/01/2025 | 08/08/2025 | 4 | 2 | 2 | 08/11/2025 | 08/11/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 174700 | 01843 | 595 |  |  | Solar |  | 05_14_275L2 | 01/03/2013 | 01/03/2013 | 7 | 0 | 7 | 01/15/2013 | 01/15/2013 | 332 | 0 | 332 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 5/31/2013 | N | EXP | 29 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 |  | Withdrawn |  | N
National Grid | WORCESTER | 318384 | 01609 | 10 |  |  | Solar |  | 05_14_56L3 | 10/09/2020 | 10/14/2020 | 2 | 2 | 0 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | STURBRIDGE | 177237 | 01518 | 472.9 |  |  | Solar |  | 05_14_70L4 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 537292 | 01543 | 0 |  |  | Solar |  | 05_14_8L1 | 06/28/2023 | 10/19/2023 | 77 | 77 | 0 | 10/20/2023 | 10/20/2023 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 624586 | 02720 | 21.38 |  |  | Solar |  | 05_01_23W2 | 07/18/2024 | 07/22/2024 | 2 | 0 | 2 | 09/12/2024 | 09/12/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/18/2024 | 9/21/2025 | Y | EXP | 365 | 10/29/2024 | 11/01/2024 | 4 | 0 | 4 |  |  | 5/22/2025 | Connected |  | N
National Grid | MARLBOROUGH | 651529 | 01752 | 5.76 |  |  | Solar |  | 05_01_408L1 | 11/12/2024 | 12/13/2024 | 7 | 4 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 176383 | 01970 | 28 |  |  | Solar |  | 05_01_55W1 | 11/25/2015 | 11/25/2015 | 8 | 8 | 0 | 12/08/2015 | 12/08/2015 | 511 | 72 | 439 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2016 |  | 6/29/2018 | N | EXP | 815 |  |  | 0 | 0 | 0 |  |  | 8/30/2018 | Connected |  | N
National Grid | CHELMSFORD | 646610 | 01824 | 7.6 |  |  | Solar |  | 05_05_106W81 | 10/18/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | BOXFORD | 503948 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 8/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2023 | Connected |  | N
National Grid | BILLERICA | 707396 | 01862 | 67.3 |  |  | Solar |  | 05_12_49W6 | 08/01/2025 | 09/10/2025 | 27 | 18 | 9 | 09/11/2025 | 09/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 174806 | 01843 | 300 |  |  | Solar |  | 05_14_275L2 | 01/23/2013 | 01/23/2013 | 7 | 0 | 7 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2013 |  | 6/28/2013 | N | EXP | 92 |  |  | 0 | 0 | 0 | 3/28/2013 | 3/28/2013 | 8/22/2013 | Connected |  | N
National Grid | WORCESTER | 347094 | 01605 | 9.966 |  |  | Solar |  | 05_14_56L3 | 03/26/2021 | 04/09/2021 | 10 | 10 | 0 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 | 03/26/2021 | 8/17/2022 | Y | EXP | 365 | 08/04/2021 | 08/12/2021 | 9 | 0 | 9 |  |  | 11/3/2021 | Connected |  | N
National Grid | STURBRIDGE | 204163 | 01518 | 453 |  |  | Solar |  | 05_14_70L4 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 566189 | 01543 | 5 |  |  | Solar |  | 05_14_8L1 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/01/2023 | 3/13/2025 | Y | EXP | 365 | 05/15/2024 | 05/31/2024 | 17 | 0 | 17 |  |  | 6/6/2024 | Connected |  | N
National Grid | FALL RIVER | 736356 | 02720 | 10 |  |  | Solar |  | 05_01_23W3 | 11/25/2025 | 11/26/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 692690 | 01752 | 15.2 |  |  | Solar |  | 05_01_408L1 | 05/19/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | SALEM | 176511 | 01970 | 10 |  |  | Solar |  | 05_01_55W1 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/31/2016 | 8/31/2016 | 8/31/2016 | Connected |  | N
National Grid | AMESBURY | 649794 | 01913 | 7.6 |  |  | Solar |  | 05_05_106W81 | 10/25/2024 | 11/12/2024 | 8 | 2 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | BOXFORD | 559734 | 01921 | 400 |  |  | Solar |  | 05_05_311W3 | 10/12/2023 | 12/08/2023 | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 | 01/26/2024 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 727468 | 01862 | 84.6 |  |  | Solar |  | 05_12_49W6 | 10/20/2025 | 11/10/2025 | 14 | 5 | 9 | 11/12/2025 | 11/12/2025 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 176392 | 01843 | 300 |  |  | Solar |  | 05_14_275L2 | 02/02/2016 | 02/02/2016 | 1 | 1 | 0 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 | 03/16/2016 | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 9/15/2016 | N | EXP | 183 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 9/30/2016 | Connected |  | N
National Grid | WORCESTER | 365918 | 01609 | 15.36 |  |  | Solar |  | 05_14_56L3 | 06/24/2021 | 06/30/2021 | 4 | 0 | 4 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 613720 | 01566 | 4.06 |  |  | Solar |  | 05_14_70L4 | 05/28/2024 | 07/31/2024 | 5 | 2 | 3 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 05/28/2024 | 10/1/2025 | Y | EXP | 365 | 11/15/2024 | 12/18/2024 | 34 | 0 | 34 |  |  | 1/9/2025 | Connected |  | Y
National Grid | RUTLAND | 581109 | 01543 | 0 |  |  | Battery Add-On |  | 05_14_8L1 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | FALL RIVER | 174253 | 02720 | 1095 |  |  | Solar |  | 05_01_23W3 | 02/27/2012 | 02/27/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/21/2012 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 694502 | 01752 | 17.6 |  |  | Solar |  | 05_01_408L1 | 05/28/2025 | 06/09/2025 | 2 | 0 | 2 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176609 | 01970 | 616 |  |  | Solar |  | 05_01_55W1 | 02/12/2016 | 02/12/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 666670 | 01913 | 10 |  |  | Solar |  | 05_05_106W82 | 01/20/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 8/13/2026 | Y | EXP | 365 | 06/13/2025 |  | 203 | 91 | 112 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 528910 | 01845 | 360 |  |  | Solar |  | 05_05_311W3 | 09/29/2023 | 10/30/2023 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 743612 | 01862 | 12 |  |  | Solar |  | 05_12_49W6 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 177136 | 01843 | 7.6 |  |  | Solar |  | 05_14_275L2 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 6/5/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/23/2016 | 9/23/2016 | 9/28/2016 | Connected |  | N
National Grid | WORCESTER | 378271 | 01609 | 0 |  |  | Solar |  | 05_14_56L3 | 08/26/2021 | 09/14/2021 | 13 | 10 | 3 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2022 | Connected |  | N
National Grid | STURBRIDGE | 673217 | 01518 | 960 |  |  | Solar |  | 05_14_70L5 | 05/23/2025 | 06/26/2025 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | RUTLAND | 584528 | 01543 | 11.4 |  |  | Solar |  | 05_14_8L1 | 02/01/2024 | 02/12/2024 | 8 | 6 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2024 | Connected |  | N
National Grid | FALL RIVER | 174992 | 02720 | 13.11 |  |  | Solar |  | 05_01_23W3 | 03/11/2013 | 03/11/2013 | 5 | 0 | 5 | 03/20/2013 | 03/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2013 |  | 7/5/2013 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/3/2013 | 4/3/2013 | 5/24/2013 | Connected |  | N
National Grid | MARLBOROUGH | 178274 | 01752 | 4998 |  |  | Solar |  | 05_01_408L2 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 05/24/2018 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2018 | 02/21/2018 | 8/14/2027 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SALEM | 176629 | 01970 | 6 |  |  | Solar |  | 05_01_55W1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2015 |  | 10/21/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 4/29/2016 | Connected |  | N
National Grid | AMESBURY | 729535 | 01913 | 150 |  |  | Solar |  | 05_05_106W82 | 10/31/2025 | 12/03/2025 | 20 | 13 | 7 | 12/04/2025 | 12/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BOXFORD | 569808 | 01921 | 6 |  |  | Solar |  | 05_05_311W3 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 11/20/2023 | 2/4/2026 | Y | EXP | 730 | 07/25/2024 | 09/12/2024 | 50 | 0 | 50 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 177085 | 01862 | 540 |  |  | Solar |  | 05_12_49W6 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177161 | 01810 | 80 |  |  | Solar |  | 05_14_275L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 | 10/28/2016 | 11/6/2017 | Y | EXP | 362 | 01/09/2017 | 05/09/2017 | 83 | 0 | 83 | 6/12/2017 | 6/12/2017 | 6/12/2017 | Connected |  | N
National Grid | WORCESTER | 382988 | 01602 | 15.2 |  |  | Solar |  | 05_14_56L3 | 09/19/2021 | 11/09/2021 | 36 | 29 | 7 | 11/10/2021 | 11/10/2021 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 | 09/19/2021 | 3/17/2023 | Y | EXP | 365 | 02/23/2022 | 03/17/2022 | 23 | 0 | 23 |  |  | 4/21/2022 | Connected |  | N
National Grid | STURBRIDGE | 175886 | 01518 | 3.8 |  |  | Solar |  | 05_14_70L5 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 11/16/2015 | 11/16/2015 | 11/19/2015 | Connected |  | N
National Grid | RUTLAND | 593454 | 01543 | 6 |  |  | Solar |  | 05_14_8L1 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 03/25/2024 | 5/6/2025 | Y | EXP | 365 | 07/31/2024 | 09/19/2024 | 51 | 0 | 51 |  |  | 10/31/2024 | Connected |  | N
National Grid | FALL RIVER | 176357 | 02720 | 10 |  |  | Solar |  | 05_01_23W3 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/23/2015 | 7/23/2015 | 11/24/2015 | Connected |  | N
National Grid | MARLBOROUGH | 578928 | 01752 | 996 |  |  | Solar |  | 05_01_408L2 | 02/29/2024 | 06/07/2024 | 69 | 60 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2024 | 06/18/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALEM | 176698 | 01970 | 380 |  |  | Bio Gas |  | 05_01_55W1 | 04/25/2016 | 05/16/2016 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2016 | 07/06/2016 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2016 | 04/25/2016 | 7/5/2022 | Y | STD | 70 | 03/09/2019 | 09/26/2019 | 202 | 107 | 95 |  |  | 3/16/2022 | Connected |  | N
National Grid | AMESBURY | 189412 | 01913 | 740 |  |  | Solar |  | 05_05_106W82 | 08/08/2018 | 10/17/2018 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 11/15/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 570780 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 | 11/20/2023 | 4/18/2025 | Y | EXP | 365 | 06/08/2024 | 09/03/2024 | 88 | 0 | 88 |  |  | 11/2/2024 | Connected |  | N
National Grid | BILLERICA | 177244 | 01862 | 191 |  |  | Solar |  | 05_12_49W6 | 02/06/2017 | 02/06/2017 | 4 | 0 | 4 | 02/10/2017 | 02/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 | 07/27/2017 | 07/31/2017 | 2 | 0 | 2 | 10/5/2017 | 10/5/2017 | 10/18/2017 | Connected |  | N
National Grid | ANDOVER | 202349 | 01810 | 7.6 |  |  | Solar |  | 05_14_275L2 | 01/09/2019 | 01/18/2019 | 6 | 0 | 6 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/09/2019 | 9/16/2020 | Y | EXP | 365 | 04/17/2020 | 05/12/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | WORCESTER | 398752 | 01602 | 15.2 |  |  | Solar |  | 05_14_56L3 | 12/01/2021 | 12/02/2021 | 1 | 0 | 1 | 12/03/2021 | 12/03/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 4/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2022 | Connected |  | N
National Grid | STURBRIDGE | 177357 | 01566 | 168 |  |  | Solar |  | 05_14_70L5 | 02/16/2017 | 02/16/2017 | 1 | 0 | 1 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 2/21/2018 | N | EXP | 247 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 1/8/2018 | Connected |  | N
National Grid | RUTLAND | 607693 | 01543 | 0 |  |  | Solar |  | 05_14_8L1 | 04/30/2024 | 06/11/2024 | 29 | 28 | 1 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 176882 | 02723 | 7.53 |  |  | Solar |  | 05_01_23W3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2016 |  | 5/10/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2016 | 10/27/2016 | 10/27/2016 | Connected |  | N
National Grid | MARLBOROUGH | 706760 | 01752 | 240 |  |  | Solar |  | 05_01_408L2 | 08/21/2025 | 09/10/2025 | 13 | 8 | 5 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALEM | 176872 | 01970 | 10 |  |  | Solar |  | 05_01_55W1 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 3/7/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/2/2016 | 8/2/2016 | 8/8/2016 | Connected |  | N
National Grid | AMESBURY | 203924 | 01913 | 10 |  |  | Solar |  | 05_05_106W82 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 584824 | 01921 | 7.6 |  |  | Solar |  | 05_05_311W3 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 273131 | 01862 | 0 |  |  | Solar |  | 05_12_49W6 | 01/14/2020 | 01/14/2020 | 0 | 0 | 0 | 01/15/2020 | 01/15/2020 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2020 |  | 1/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2020 | Connected |  | N
National Grid | ANDOVER | 208390 | 01810 | 7.6 |  |  | Solar |  | 05_14_275L2 | 03/01/2019 | 03/04/2019 | 0 | 0 | 0 | 03/05/2019 | 03/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/01/2019 | 9/1/2020 | Y | EXP | 414 | 04/18/2020 | 05/06/2020 | 18 | 0 | 18 |  |  | 8/19/2020 | Connected |  | N
National Grid | LEICESTER | 410771 | 01524 | 10 |  |  | Solar |  | 05_14_56L3 | 02/07/2022 | 02/09/2022 | 3 | 1 | 2 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2022 | Connected |  | N
National Grid | BROOKFIELD | 177550 | 01506 | 10 |  |  | Solar |  | 05_14_70L5 | 05/15/2017 | 05/15/2017 | 4 | 3 | 1 | 05/22/2017 | 05/22/2017 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 |  | 5/21/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 613634 | 01543 | 23 |  |  | Battery Add-On |  | 05_14_8L1 | 05/28/2024 | 06/03/2024 | 5 | 3 | 2 | 06/04/2024 | 06/04/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | FALL RIVER | 177039 | 02723 | 800 |  |  | Solar |  | 05_01_23W3 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 738783 | 01752 | 7.6 |  |  | Solar |  | 05_01_408L2 | 12/08/2025 | 12/10/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 177129 | 01970 | [5 empty] | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/28/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 220893 | 01913 | 489 |  |  | Solar |  | 05_05_106W82 | 04/19/2019 | 04/23/2019 | 1 | 0 | 1 | 04/24/2019 | 04/24/2019 | 10 | 0 | 10 | 05/23/2019 | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 603043 | 01921 | 10 |  |  | Solar |  | 05_05_311W3 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 277189 | 01862 | 3.36 |  |  | Solar |  | 05_12_49W6 | 04/27/2020 | 04/30/2020 | 2 | 0 | 2 | 05/01/2020 | 05/01/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 245163 | 01843 | 4990 |  |  | Solar |  | 05_14_275L2 | 03/05/2020 | 03/26/2020 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2020 | 05/21/2020 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 03/05/2020 | 5/15/2030 | Y | STD | 2190 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 412304 | 01602 | 7.6 |  |  | Solar |  | 05_14_56L3 | 02/24/2022 | 02/28/2022 | 2 | 0 | 2 | 03/01/2022 | 03/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/24/2022 | 6/13/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 178469 | 01585 | 11.4 |  |  | Solar |  | 05_14_70L5 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 5/17/2021 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | RUTLAND | 615299 | 01543 | 10 |  |  | Solar |  | 05_14_8L1 | 06/04/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/04/2024 | 8/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | FALL RIVER | 178253 | 02723 | 7.6 |  |  | Solar |  | 05_01_23W3 | 03/27/2018 | 03/27/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/2/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174315 | 01752 | 25 |  |  | Solar |  | 05_01_408L2 | 01/17/2012 | 01/17/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2012 | 01/17/2012 | 3/30/2012 | Y | EXP | -28 | 04/26/2012 | 07/27/2012 | 63 | 0 | 63 | 8/3/2012 | 8/3/2012 | 8/10/2012 | Connected |  | N
National Grid | SALEM | 177130 | 01970 | 7.25 |  |  | Solar |  | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 10 | 9 | 1 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 1/28/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | AMESBURY | 337864 | 01913 | 7.6 |  |  | Solar |  | 05_05_106W82 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2021 | Connected |  | N
National Grid | BOXFORD | 625953 | 01921 | 3.8 |  |  | Solar |  | 05_05_311W3 | 07/18/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 07/18/2024 | 9/24/2025 | Y | EXP | 365 | 10/11/2024 | 12/03/2024 | 54 | 0 | 54 |  |  | 12/27/2024 | Connected |  | N
National Grid | BILLERICA | 296513 | 01862 | 3.36 |  |  | Solar |  | 05_12_49W6 | 07/13/2020 | 07/17/2020 | 3 | 0 | 3 | 07/20/2020 | 07/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 300662 | 01843 | 7.6 |  |  | Solar |  | 05_14_275L2 | 08/06/2020 | 08/11/2020 | 3 | 1 | 2 | 08/12/2020 | 08/12/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/06/2020 | 12/6/2021 | Y | EXP | 365 | 03/24/2021 | 04/06/2021 | 13 | 0 | 13 |  |  | 10/5/2021 | Connected |  | N
National Grid | WORCESTER | 466707 | 01602 | 22.8 |  |  | Solar |  | 05_14_56L3 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 325 | 302 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | STURBRIDGE | 185699 | 01518 | 360 |  |  | Solar |  | 05_14_70L5 | 05/18/2018 | 05/18/2018 | 53 | 47 | 6 | 06/22/2018 | 06/22/2018 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 616792 | 01543 | 10 |  |  | Solar |  | 05_14_8L1 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 184545 | 02723 | 7.6 |  |  | Solar |  | 05_01_23W3 | 05/31/2018 | 05/31/2018 | 3 | 0 | 3 | 06/07/2018 | 06/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174616 | 01752 | 300 |  |  | Solar |  | 05_01_408L2 | 12/29/2010 | 12/29/2010 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/29/2012 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/29/2012 | Connected |  | N
National Grid | SALEM | 177173 | 01970 | 5.59 |  |  | Solar |  | 05_01_55W1 | 05/31/2016 | 05/31/2016 | 17 | 17 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2016 |  | 6/6/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | AMESBURY | 379546 | 01913 | 10 |  |  | Solar |  | 05_05_106W82 | 09/09/2021 | 09/28/2021 | 4 | 3 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/09/2021 | 1/3/2023 | Y | EXP | 365 | 12/04/2021 | 01/03/2022 | 31 | 0 | 31 |  |  | 2/5/2022 | Connected |  | N
National Grid | BOXFORD | 641237 | 01921 | 5.76 |  |  | Solar |  | 05_05_311W3 | 09/18/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 02/11/2025 | 03/04/2025 | 22 | 0 | 22 |  |  | 4/1/2025 | Connected |  | N
National Grid | BILLERICA | 302107 | 01821 | 86.4 |  |  | Solar |  | 05_12_49W6 | 07/21/2020 | 07/29/2020 | 5 | 0 | 5 | 07/30/2020 | 07/30/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 1/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2021 | Connected |  | N
National Grid | ANDOVER | 348110 | 01810 | 9.8 |  |  | Solar |  | 05_14_275L2 | 04/08/2021 | 04/12/2021 | 1 | 0 | 1 | 04/13/2021 | 04/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/12/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 475112 | 01524 | 15.2 |  |  | Solar |  | 05_14_56L3 | 11/07/2022 | 11/08/2022 | 1 | 0 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | STURBRIDGE | 304749 | 01518 | 10 |  |  | Solar |  | 05_14_70L5 | 08/12/2020 | 08/17/2020 | 2 | 0 | 2 | 08/18/2020 | 08/18/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/12/2020 | 5/3/2021 | Y | EXP | 365 | 12/11/2020 | 01/05/2021 | 25 | 0 | 25 |  |  | 2/11/2021 | Connected |  | N
National Grid | RUTLAND | 646024 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 10/10/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/10/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | FALL RIVER | 186320 | 02723 | 3.8 |  |  | Solar |  | 05_01_23W3 | 06/13/2018 | 06/13/2018 | 28 | 0 | 28 | 07/26/2018 | 07/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174615 | 01752 | 585 |  |  | Solar |  | 05_01_408L2 | 12/14/2010 | 12/14/2010 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/27/2012 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/27/2012 | Connected |  | N
National Grid | SALEM | 177420 | 01970 | 5 |  |  | Solar |  | 05_01_55W1 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2016 |  | 12/11/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/7/2017 | 3/7/2017 | 3/7/2017 | Connected |  | N
National Grid | AMESBURY | 460340 | 01913 | 5.51 |  |  | Solar |  | 05_05_106W82 | 09/27/2022 | 09/29/2022 | 3 | 1 | 2 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | Y
National Grid | ANDOVER | 645368 | 01845 | 3.8 |  |  | Solar |  | 05_05_311W3 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 63 | 39 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 10/07/2024 | 3/4/2026 | Y | EXP | 365 | 04/30/2025 | 06/05/2025 | 37 | 0 | 37 |  |  | 6/5/2025 | Connected |  | N
National Grid | BILLERICA | 342002 | 01862 | 40 |  |  | Solar |  | 05_12_49W6 | 03/30/2021 | 04/22/2021 | 14 | 9 | 5 | 04/23/2021 | 04/23/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2021 | Connected |  | N
National Grid | LAWRENCE | 574491 | 01843 | 10 |  |  | Solar |  | 05_14_275L2 | 01/12/2024 | 01/22/2024 | 5 | 4 | 1 | 01/23/2024 | 01/23/2024 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/12/2024 | 2/14/2025 | Y | EXP | 365 | 04/24/2024 | 05/07/2024 | 14 | 0 | 14 |  |  | 5/14/2024 | Connected |  | N
National Grid | WORCESTER | 525009 | 01602 | 13.824 |  |  | Solar |  | 05_14_56L3 | 05/10/2023 | 05/18/2023 | 6 | 4 | 2 | 05/19/2023 | 05/19/2023 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | BRIMFIELD | 339771 | 01010 | 11.4 |  |  | Solar |  | 05_14_70L5 | 02/01/2021 | 06/03/2021 | 85 | 80 | 5 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2022 | Connected |  | Y
National Grid | RUTLAND | 651615 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 11/12/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 32 | 7 | 25 | 03/21/2025 | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | FALL RIVER | 198437 | 02723 | 3.8 |  |  | Solar |  | 05_01_23W3 | 10/12/2018 |  | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175628 | 01752 | 1000 |  |  | Solar |  | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 37 | 36 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2014 | 10/29/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/29/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178189 | 01970 | 296 |  |  | Solar |  | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 10 | 0 | 10 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 | 10/25/2018 | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/7/2018 |  | 2/3/2020 | N | EXP | 208 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | AMESBURY | 518145 | 01913 | 14.5 |  |  | Solar |  | 05_05_106W82 | 04/15/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | N
National Grid | BOXFORD | 657483 | 01921 | 3.8 |  |  | Solar |  | 05_05_311W3 | 11/27/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 | 03/29/2025 | 03/28/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 370832 | 01862 | 250 |  |  | Solar |  | 05_12_49W6 | 08/06/2021 | 08/20/2021 | 10 | 0 | 10 |  |  | 30 | 3 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 | 08/06/2021 | 8/1/2023 | Y | STD | 41 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | LAWRENCE | 613959 | 01843 | 10 |  |  | Solar |  | 05_14_275L2 | 05/30/2024 | 06/24/2024 | 11 | 7 | 4 | 06/25/2024 | 06/25/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 557784 | 01602 | 13.8 |  |  | Solar |  | 05_14_56L3 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 42 | 20 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2024 | Connected |  | N
National Grid | STURBRIDGE | 357954 | 01518 | 0 |  |  | Solar |  | 05_14_70L5 | 05/24/2021 | 05/25/2021 | 0 | 0 | 0 | 05/26/2021 | 05/26/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2021 |  | 5/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2021 | Connected |  | N
National Grid | RUTLAND | 658814 | 01543 | 0 |  |  | Solar |  | 05_14_8L1 | 12/06/2024 | 01/07/2025 | 21 | 18 | 3 | 01/08/2025 | 01/08/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | FALL RIVER | 198669 | 02723 | 5 |  |  | Solar |  | 05_01_23W3 | 10/16/2018 | 02/20/2019 | 87 | 83 | 4 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175735 | 01752 | 500 |  |  | Solar |  | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/19/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 5/1/2016 | N | STD | 376 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178188 | 01970 | 294 |  |  | Solar |  | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 2/3/2020 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | AMESBURY | 529857 | 01913 | 3.8 |  |  | Solar |  | 05_05_106W82 | 07/06/2023 | 08/03/2023 | 21 | 20 | 1 | 08/04/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/06/2023 | 11/26/2024 | Y | EXP | 365 | 10/24/2023 | 12/01/2023 | 39 | 0 | 39 |  |  | 12/4/2023 | Connected |  | N
National Grid | BOXFORD | 673014 | 01921 | 3.8 |  |  | Solar |  | 05_05_311W3 | 02/19/2025 | 03/26/2025 | 17 | 12 | 5 | 04/23/2025 | 04/23/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | BILLERICA | 647135 | 01821 | 7.6 |  |  | Solar |  | 05_12_49W6 | 10/29/2024 | 10/31/2024 | 17 | 15 | 2 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 653578 | 01843 | 16 |  |  | Solar |  | 05_14_275L2 | 11/11/2024 | 11/27/2024 | 12 | 10 | 2 | 12/02/2024 | 12/02/2024 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 546601 | 01602 | 15.08 |  |  | Solar |  | 05_14_56L3 | 08/07/2023 |  | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 425627 | 01518 | 9.8 |  |  | Solar |  | 05_14_70L5 | 05/04/2022 | 05/09/2022 | 3 | 1 | 2 | 05/10/2022 | 05/10/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 05/04/2022 | 1/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | RUTLAND | 661249 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 12/20/2024 | 12/27/2024 | 4 | 0 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | FALL RIVER | 206478 | 02723 | 250 |  |  | Solar |  | 05_01_23W3 | 03/12/2019 | 03/14/2019 | 1 | 1 | 0 |  |  | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 03/12/2019 | 3/23/2023 | Y | STD | 823 | 10/05/2021 | 08/19/2022 | 319 | 4 | 315 |  |  | 3/9/2023 | Connected |  | N
National Grid | MARLBOROUGH | 177703 | 01752 | 1500 |  |  | Solar |  | 05_01_408L2 | 05/25/2017 | 05/25/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/21/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 05/25/2017 | 6/15/2020 | Y | STD | 435 | 10/03/2019 | 12/27/2019 | 85 | 0 | 85 |  |  | 6/15/2020 | Connected |  | N
National Grid | SALEM | 178262 | 01970 | 7.6 |  |  | Solar |  | 05_01_55W1 | 04/17/2018 | 04/17/2018 | 19 | 0 | 19 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 569078 | 01913 | 3.8 |  |  | Solar |  | 05_05_106W82 | 11/30/2023 | 12/05/2023 | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 673800 | 01921 | 7.6 |  |  | Solar |  | 05_05_311W3 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | BILLERICA | 657099 | 01821 | 75 |  |  | Solar |  | 05_12_49W6 | 12/11/2024 | 01/17/2025 | 25 | 16 | 9 | 01/21/2025 | 01/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 9/19/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | LAWRENCE | 655738 | 01843 | 3.8 |  |  | Solar |  | 05_14_275L2 | 11/20/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WORCESTER | 587700 | 01602 | 21.735 |  |  | Solar |  | 05_14_56L3 | 02/06/2024 | 02/29/2024 | 16 | 14 | 2 | 03/01/2024 | 03/01/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | BRIMFIELD | 590690 | 01010 | 10 |  |  | Solar |  | 05_14_70L5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 661637 | 01543 | 10 |  |  | Solar |  | 05_14_8L1 | 12/19/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/19/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | FALL RIVER | 230757 | 02723 | 7.6 |  |  | Solar |  | 05_01_23W3 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 10/15/2019 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  | 9/10/2019 | Connected |  | N
National Grid | MARLBOROUGH | 178484 | 01752 | 3000 |  |  | Solar |  | 05_01_408L2 | 04/03/2018 | 04/18/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/10/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  | 6/27/2023 | N | STD | 553 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178233 | 01970 | 133.2 |  |  | Solar |  | 05_01_55W1 | 01/07/2018 | 01/07/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2018 |  | 4/16/2021 | N | EXP | 490 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | AMESBURY | 580036 | 01913 | 6 |  |  | Solar |  | 05_05_106W82 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 4/17/2025 | Y | EXP | 365 | 07/17/2024 | 08/27/2024 | 42 | 0 | 42 |  |  | 10/18/2024 | Connected |  | N
National Grid | BOXFORD | 681814 | 01921 | 5.76 |  |  | Solar |  | 05_05_311W3 | 04/01/2025 | 05/20/2025 | 30 | 25 | 5 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 708169 | 01821 | 17.101 |  |  | Solar |  | 05_12_49W6 | 08/22/2025 | 08/28/2025 | 4 | 0 | 4 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | ANDOVER | 664839 | 01810 | 15.2 |  |  | Solar |  | 05_14_275L2 | 01/10/2025 | 02/11/2025 | 16 | 11 | 5 | 02/12/2025 | 02/12/2025 | 54 | 37 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/10/2025 | 5/28/2026 | Y | EXP | 365 | 09/30/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 11/4/2025 | Connected |  | N
National Grid | WORCESTER | 593058 | 01602 | 15.2 |  |  | Solar |  | 05_14_56L3 | 02/27/2024 | 04/09/2024 | 1 | 0 | 1 | 04/10/2024 | 04/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 02/27/2024 | 5/8/2025 | Y | EXP | 365 | 05/23/2024 | 12/17/2024 | 209 | 0 | 209 |  |  | 8/3/2024 | Connected |  | N
National Grid | BRIMFIELD | 633944 | 01010 | 5.76 |  |  | Solar |  | 05_14_70L5 | 08/20/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 08/20/2024 | 10/10/2025 | Y | EXP | 365 | 11/28/2024 | 12/26/2024 | 29 | 0 | 29 |  |  | 1/6/2025 | Connected |  | N
National Grid | RUTLAND | 669874 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | FALL RIVER | 424314 | 02723 | 3.8 |  |  | Solar |  | 05_01_23W3 | 04/15/2022 | 05/27/2022 | 1 | 0 | 1 | 05/31/2022 | 05/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 | 04/15/2022 | 9/9/2023 | Y | EXP | 365 | 08/25/2022 | 09/07/2022 | 14 | 0 | 14 |  |  | 9/12/2022 | Connected |  | N
National Grid | MARLBOROUGH | 178586 | 01752 | 1.84 |  |  | Solar |  | 05_01_408L2 | 03/13/2018 | 03/13/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/19/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178361 | 01970 | 3000 |  |  | Solar |  | 05_01_55W1 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 591268 | 01913 | 6 |  |  | Solar |  | 05_05_106W82 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | BOXFORD | 644500 | 01921 | 10 |  |  | Solar |  | 05_05_311W4 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 2/10/2026 | Y | EXP | 425 | 01/07/2025 | 02/13/2025 | 38 | 0 | 38 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 591000 | 01821 | 10 |  |  | Solar |  | 05_12_4J2 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 686893 | 01810 | 10 |  |  | Solar |  | 05_14_275L2 | 05/01/2025 | 05/21/2025 | 4 | 0 | 4 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 | 05/01/2025 | 6/17/2026 | Y | EXP | 365 | 10/01/2025 | 10/07/2025 | 7 | 0 | 7 |  |  | 10/11/2025 | Connected |  | N
National Grid | WORCESTER | 597914 | 01602 | 7.68 |  |  | Solar |  | 05_14_56L3 | 05/20/2024 | 08/13/2024 | 19 | 17 | 2 | 08/14/2024 | 08/14/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | WARREN | 643883 | 01083 | 5.76 |  |  | Solar |  | 05_14_70L5 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 672761 | 01543 | 10 |  |  | Solar |  | 05_14_8L1 | 02/18/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 83 | 64 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 527877 | 02723 | 10 |  |  | Solar |  | 05_01_23W3 | 05/31/2023 | 06/05/2023 | 4 | 3 | 1 | 06/06/2023 | 06/06/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 | 05/31/2023 | 8/3/2024 | Y | EXP | 365 | 08/10/2023 | 08/28/2023 | 19 | 0 | 19 |  |  | 10/6/2023 | Connected |  | N
National Grid | MARLBOROUGH | 312005 | 01752 | 15.2 |  |  | Solar |  | 05_01_408L2 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N
National Grid | SALEM | 178532 | 01970 | 7.6 |  |  | Solar |  | 05_01_55W1 | 12/05/2017 | 12/05/2017 | 83 | 82 | 1 | 06/06/2018 | 06/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  | 12/10/2018 | N | EXP | 188 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 635301 | 01913 | 5.76 |  |  | Solar |  | 05_05_106W82 | 08/26/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/26/2024 | 10/21/2025 | Y | EXP | 365 | 12/21/2024 | 01/18/2025 | 29 | 0 | 29 |  |  | 1/28/2025 | Connected |  | N
National Grid | BOXFORD | 659874 | 01921 | 3.8 |  |  | Solar |  | 05_05_311W4 | 12/11/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/11/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 605660 | 01821 | 15.2 |  |  | Solar |  | 05_12_4J2 | 05/02/2024 | 05/10/2024 | 7 | 5 | 2 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/02/2024 | 6/20/2025 | Y | EXP | 365 | 10/03/2024 | 12/18/2024 | 77 | 0 | 77 |  |  | 1/10/2025 | Connected |  | N
National Grid | ANDOVER | 710143 | 01810 | 7.15 |  |  | Solar |  | 05_14_275L2 | 08/07/2025 | 09/11/2025 | 6 | 0 | 6 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | Y
National Grid | WORCESTER | 605204 | 01602 | 10 |  |  | Solar |  | 05_14_56L3 | 04/19/2024 | 04/22/2024 | 1 | 0 | 1 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | WARREN | 647631 | 01083 | 7.6 |  |  | Solar |  | 05_14_70L5 | 10/21/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 675590 | 01543 | 7.6 |  |  | Solar |  | 05_14_8L1 | 03/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 575782 | 02723 | 7.83 |  |  | Solar |  | 05_01_23W3 | 12/27/2023 | 12/28/2023 | 1 | 0 | 1 | 12/29/2023 | 12/29/2023 | 22 | 0 | 22 | 02/27/2024 | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 379733 | 01752 | 15.2 |  |  | Solar |  | 05_01_408L2 | 09/02/2021 | 09/03/2021 | 1 | 0 | 1 | 09/07/2021 | 09/07/2021 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 639123 | 01970 | 0 |  |  | Solar |  | 05_05_106W82 | 09/10/2024 | 10/02/2024 | 10 | 5 | 5 | 10/03/2024 | 10/03/2024 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | AMESBURY | 175299 | 01913 | 300 |  |  | Solar |  | 05_05_311W4 | 01/15/2015 | 01/15/2015 | 3 | 1 | 2 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 9/18/2015 | Connected |  | N
National Grid | BOXFORD | 620144 | 01921 | 7.6 |  |  | Solar |  | 05_12_4J2 | 06/25/2024 | 07/10/2024 | 1 | 0 | 1 | 07/11/2024 | 07/11/2024 | 181 | 160 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 343628 | 01821 | 499 |  |  | Solar |  | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 |  | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ANDOVER | 620829 | 01810 | 15.2 |  |  | Solar |  | 05_14_56L3 | 06/28/2024 | 07/11/2024 | 9 | 7 | 2 | 07/12/2024 | 07/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | WORCESTER | 685276 | 01602 | 15.76 |  |  | Solar |  | 05_14_8L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 65 | 24 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 599599 | 01518 | 7.6 |  |  | Solar |  | 05_01_23W3 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 432891 | 01543 | 15.2 |  |  | Solar |  | 05_01_408L2 | 09/15/2022 | 09/15/2022 | 0 | 0 | 0 | 09/16/2022 | 09/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 178535 | 02723 | 7.6 |  |  | Solar |  | 05_01_55W1 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 | 12/07/2017 | 3/22/2019 | Y | EXP | 441 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | MARLBOROUGH | 655843 | 01752 | 4.35 |  |  | Solar |  | 05_05_106W82 | 12/20/2024 | 01/09/2025 | 4 | 2 | 2 | 01/10/2025 | 01/10/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LYNN | 175990 | 01902 | 12 |  |  | Solar |  | 05_05_311W4 | 03/18/2015 | 03/18/2015 | 4 | 0 | 4 | 03/25/2015 | 03/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2015 |  | 12/31/2016 | N | EXP | 631 |  |  | 0 | 0 | 0 | 4/10/2015 | 4/10/2015 | 10/5/2016 | Connected |  | N
National Grid | AMESBURY | 643453 | 01913 | 5.8 |  |  | Solar |  | 05_12_4J2 | 09/27/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 107 | 83 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 616127 | 01921 | 1996 |  |  | Solar |  | 05_14_275L4 | 08/12/2024 | 09/04/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 623174 | 01821 | 0 |  |  | Solar |  | 05_14_56L3 | 07/08/2024 | 07/10/2024 | 2 | 0 | 2 | 07/11/2024 | 07/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 10/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | LAWRENCE | 648641 | 01843 | 10 |  |  | Solar |  | 05_14_70L5 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 04/12/2025 | 04/22/2025 | 11 | 0 | 11 |  |  | 4/29/2025 | Connected |  | N
National Grid | WORCESTER | 658936 | 01602 | 499 |  |  | Solar |  | 05_14_8L2 | 04/08/2025 | 04/24/2025 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/28/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STURBRIDGE | 618070 | 01518 | 6 |  |  | Solar |  | 05_01_23W3 | 06/17/2024 | 07/09/2024 | 8 | 5 | 3 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 586660 | 01543 | 10 |  |  | Solar |  | 05_01_408L2 | 02/08/2024 | 02/09/2024 | 1 | 0 | 1 | 02/12/2024 | 02/12/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | FALL RIVER | 178563 | 02723 | 2500 |  |  | Solar |  | 05_01_55W1 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/20/2018 | 68 | 52 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 677978 | 01752 | 3.42 |  |  | Solar |  | 05_05_106W82 | 03/14/2025 | 04/08/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 177257 | 01902 | 396 |  |  | Solar |  | 05_05_311W4 | 08/17/2016 | 08/17/2016 | 2 | 2 | 0 | 08/22/2016 | 08/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 8/23/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 4/28/2017 | Connected |  | N
National Grid | AMESBURY | 658811 | 01913 | 5.76 |  |  | Solar |  | 05_12_4J2 | 12/09/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 723192 | 01921 | 10 |  |  | Solar |  | 05_14_275L4 | 10/01/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 646412 | 01862 | 10 |  |  | Solar |  | 05_14_56L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LAWRENCE | 648920 | 01843 | 5.76 |  |  | Solar |  | 05_14_70L5 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 11/05/2024 | 1/2/2026 | Y | EXP | 365 | 02/12/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/26/2025 | Connected |  | N
National Grid | WORCESTER | 723961 | 01602 | 9.56 |  |  | Solar |  | 05_14_8L2 | 10/03/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | STURBRIDGE | 631649 | 01518 | 5.12 |  |  | Solar |  | 05_01_23W3 | 08/09/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/09/2024 | 9/25/2025 | Y | EXP | 365 | 01/07/2025 | 05/21/2025 | 135 | 0 | 135 |  |  | 6/4/2025 | Connected |  | N
National Grid | RUTLAND | 620652 | 01543 | 23 |  |  | Solar |  | 05_01_408L2 | 07/03/2024 | 07/11/2024 | 5 | 3 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/6/2025 | Y | EXP | 365 | 08/30/2024 | 09/12/2024 | 14 | 0 | 14 |  |  | 1/17/2025 | Connected |  | N
National Grid | FALL RIVER | 185992 | 02723 | 8.4 |  |  | Solar |  | 05_01_55W1 | 07/17/2018 | 08/14/2018 | 19 | 0 | 19 | 08/15/2018 | 08/15/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  | 9/25/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | Y
National Grid | MARLBOROUGH | 707962 | 01752 | 6.46 |  |  | Solar |  | 05_05_106W82 | 07/28/2025 | 08/13/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N
National Grid | LYNN | 178581 | 01902 | 10 |  |  | Solar |  | 05_05_311W4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 11/25/2019 | N | EXP | 614 | 07/28/2018 | 08/29/2018 | 32 | 0 | 32 |  |  | 10/7/2019 | Connected |  | N
National Grid | AMESBURY | 439647 | 01913 | 480 |  |  | Solar |  | 05_12_51L1 | 02/06/2023 | 02/16/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2023 | 03/21/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 12/15/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 174182 | 01921 | 190 |  |  | Solar |  | 05_14_275L4 | 11/14/2011 | 11/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 3/19/2012 | N | EXP | 5 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid | BILLERICA | 655111 | 01862 | 5.76 |  |  | Solar |  | 05_14_56L3 | 11/20/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/20/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 652490 | 01843 | 7.6 |  |  | Solar |  | 05_14_70L5 | 11/14/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 6/11/2026 | Y | EXP | 365 | 04/01/2025 | 04/23/2025 | 23 | 0 | 23 |  |  | 8/29/2025 | Connected |  | N
National Grid | WORCESTER | 726407 | 01602 | 7.6 |  |  | Solar |  | 05_14_8L2 | 10/14/2025 | 12/04/2025 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 634790 | 01518 | 10 |  |  | Solar |  | 05_01_23W3 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/22/2024 | 9/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/21/2025 | 149 | 0 | 149 |  |  | 4/12/2025 | Connected |  | N
National Grid | RUTLAND | 662427 | 01543 | 9.86 |  |  | Solar |  | 05_01_408L2 | 01/02/2025 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | FALL RIVER | 190717 | 02723 | 10 |  |  | Solar |  | 05_01_55W1 | 07/13/2018 | 10/23/2018 | 30 | 24 | 6 | 10/24/2018 | 10/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 07/13/2018 | 8/28/2019 | Y | EXP | 302 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 5/23/2019 | Connected |  | N
National Grid | MARLBOROUGH | 177384 | 01752 | 12 |  |  | Solar |  | 05_05_108W51 | 11/28/2016 | 11/28/2016 | 2 | 2 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2016 |  | 12/4/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/19/2017 | Connected |  | N
National Grid | LYNN | 186667 | 01902 | 7.6 |  |  | Solar |  | 05_05_311W4 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 665571 | 01913 | 84.6 |  |  | Solar |  | 05_12_51L1 | 02/14/2025 | 03/28/2025 | 29 | 20 | 9 | 03/31/2025 | 03/31/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 174265 | 01921 | 19.89 |  |  | Solar |  | 05_14_275L4 | 11/16/2011 | 11/16/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 1/14/2012 | N | EXP | -60 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/16/2012 | Connected |  | N
National Grid | BILLERICA | 660528 | 01862 | 8.12 |  |  | Solar |  | 05_14_56L3 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 660576 | 01844 | 4.55 |  |  | Solar |  | 05_14_70L5 | 12/13/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WORCESTER | 726315 | 01602 | 20 |  |  | Solar |  | 05_14_8L2 | 10/14/2025 | 10/24/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 667463 | 01518 | 0 |  |  | Other |  | 05_01_23W3 | 02/25/2025 | 03/28/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2025 | 04/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 662789 | 01543 | 9.75 |  |  | Solar |  | 05_01_408L2 | 12/27/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/27/2024 | 5/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | FALL RIVER | 195060 | 02723 | 10 |  |  | Solar |  | 05_01_55W1 | 09/04/2018 | 10/12/2018 | 11 | 10 | 1 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177504 | 01752 | 10 |  |  | Solar |  | 05_05_108W51 | 03/06/2017 | 03/06/2017 | 9 | 7 | 2 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/11/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/30/2017 | 8/30/2017 | 9/6/2017 | Connected |  | N
National Grid | LYNN | 219586 | 01902 | 800 |  |  | Solar |  | 05_05_311W4 | 04/19/2019 | 08/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2019 | 10/29/2019 | 54 | 40 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 703620 | 01913 | 0 |  |  | Other |  | 05_12_51L1 | 09/22/2025 | 11/24/2025 | 41 | 34 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 12/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BOXFORD | 174476 | 01921 | 500 |  |  | Solar |  | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 661934 | 01821 | 8.74 |  |  | Solar |  | 05_14_56L3 | 12/20/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/20/2024 | 3/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | LAWRENCE | 666064 | 01841 | 6 |  |  | Solar |  | 05_14_70L5 | 01/15/2025 | 02/04/2025 | 5 | 1 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2025 | 01/15/2025 | 3/20/2026 | Y | EXP | 365 | 04/12/2025 | 07/07/2025 | 87 | 0 | 87 |  |  | 7/15/2025 | Connected |  | N
National Grid | WORCESTER | 726834 | 01602 | 11.52 |  |  | Solar |  | 05_14_8L2 | 10/23/2025 |  | 45 | 28 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WARREN | 686697 | 01083 | 7.6 |  |  | Solar |  | 05_01_23W3 | 04/23/2025 |  | 88 | 84 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 679369 | 01543 | 3.8 |  |  | Solar |  | 05_01_408L2 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | FALL RIVER | 197026 | 02723 | 8.4 |  |  | Solar |  | 05_01_55W1 | 09/26/2018 | 11/08/2018 | 27 | 17 | 10 | 11/09/2018 | 11/09/2018 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 | 09/26/2018 | 12/23/2019 | Y | EXP | 365 | 06/18/2019 | 06/17/2019 | 0 | 0 | 0 |  |  | 8/1/2019 | Connected |  | N
National Grid | MARLBOROUGH | 177664 | 01752 | 15.2 |  |  | Solar |  | 05_05_108W51 | 05/24/2017 | 05/24/2017 | 2 | 2 | 0 | 05/30/2017 | 05/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 | 12/15/2017 | 12/15/2017 | 12/27/2017 | Connected |  | N
National Grid | BEVERLY | 721660 | 01915 | 38.08 |  |  | Solar |  | 05_12_51L1 | 10/01/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALISBURY | 174475 | 01952 | 2000 |  |  | Solar |  | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 10/17/2012 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 671510 | 01921 | 10 |  |  | Solar |  | 05_14_56L3 | 02/11/2025 | 02/20/2025 | 6 | 3 | 3 | 02/21/2025 | 02/21/2025 | 161 | 140 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 671256 | 01821 | 3.8 |  |  | Solar |  | 05_14_70L5 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 733514 | 01841 | 3.8 |  |  | Solar |  | 05_14_8L2 | 11/13/2025 | 11/17/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 735526 | 01602 | 3.8 |  |  | Solar |  | 05_01_23W4 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 174409 | 01518 | 11.18 |  |  | Solar |  | 05_01_412L1 | 06/20/2012 | 06/20/2012 | 5 | 0 | 5 | 06/29/2012 | 06/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/17/2012 | N | EXP | -86 |  |  | 0 | 0 | 0 | 9/19/2012 | 9/19/2012 | 1/3/2013 | Connected |  | N
National Grid | RUTLAND | 199337 | 01543 | 4998 |  |  | Solar |  | 05_01_55W1 | 11/19/2018 | 12/05/2018 | 9 | 0 | 9 |  |  | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 402732 | 02019 | 3.48 |  |  | Solar |  | 05_05_108W51 | 01/28/2022 | 02/07/2022 | 6 | 3 | 3 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 9/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N
National Grid | MARLBOROUGH | 299754 | 01752 | 10 |  |  | Solar |  | 05_05_311W4 | 09/02/2020 | 09/18/2020 | 11 | 11 | 0 | 09/21/2020 | 09/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 09/02/2020 | 10/15/2021 | Y | EXP | 365 | 12/29/2020 | 03/01/2021 | 62 | 0 | 62 |  |  | 3/3/2021 | Connected |  | N
National Grid | BEVERLY | 727172 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | SALISBURY | 175416 | 01952 | 4500 |  |  | Solar |  | 05_14_275L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2014 | 08/14/2014 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 07/09/2014 | 12/31/2016 | Y | STD | 655 | 08/30/2016 | 01/30/2017 | 102 | 0 | 102 | 12/14/2016 | 12/14/2016 | 12/22/2016 | Connected |  | N
National Grid | ANDOVER | 693640 | 01845 | 17.6 |  |  | Solar |  | 05_14_56L3 | 06/03/2025 | 06/05/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | BILLERICA | 733690 | 01821 | 10 |  |  | Solar |  | 05_14_70L6 | 11/13/2025 | 11/14/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 738886 | 01841 | 3.8 |  |  | Solar |  | 05_14_8L2 | 12/09/2025 | 12/11/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 737971 | 01524 | 3.8 |  |  | Solar |  | 05_01_23W4 | 12/03/2025 | 12/05/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 175205 | 01518 | 1380 |  |  | Solar |  | 05_01_412L1 | 12/07/2012 | 12/07/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 01/15/2013 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 12/07/2012 | 1/20/2016 | Y | STD | 572 | 07/30/2015 | 12/20/2016 | 346 | 0 | 346 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | RUTLAND | 199325 | 01543 | 4998 |  |  | Solar |  | 05_01_55W1 | 11/19/2018 | 11/28/2018 | 4 | 0 | 4 |  |  | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 551974 | 02019 | 10 |  |  | Solar |  | 05_05_108W51 | 09/11/2023 | 09/18/2023 | 5 | 0 | 5 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 | 09/11/2023 | 12/31/2024 | Y | EXP | 365 | 04/25/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 6/12/2025 | Connected |  | N
National Grid | MARLBOROUGH | 436246 | 01752 | 9.984 |  |  | Solar |  | 05_05_311W4 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 |  | Y | EXP | 365 | 09/15/2022 | 10/18/2022 | 34 | 0 | 34 |  |  | 5/19/2023 | Connected |  | N
National Grid | BEVERLY | 174524 | 01915 | 75 |  |  | Natural Gas |  | 05_12_51L1 | 04/14/2011 | 04/14/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 4/13/2011 | 4/13/2011 | 4/13/2011 | Connected |  | N
National Grid | SALISBURY | 176775 | 01952 | 2800 |  |  | Solar |  | 05_14_275L4 | 11/03/2015 | 11/03/2015 | 53 | 53 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/04/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 717140 | 01921 | 7.6 |  |  | Solar |  | 05_14_56L3 | 09/11/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/11/2025 | 11/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | BILLERICA | 733043 | 01862 | 22.42 |  |  | Solar |  | 05_14_70L6 | 11/11/2025 | 11/14/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 175079 | 01841 | 300 |  |  | Solar |  | 05_14_8L2 | 09/30/2013 | 09/30/2013 | 7 | 0 | 7 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2013 |  | 12/31/2013 | N | EXP | 11 |  |  | 0 | 0 | 0 | 3/17/2014 | 3/17/2014 | 5/27/2014 | Connected |  | N
National Grid | WORCESTER | 380094 | 01602 | 7.6 |  |  | Solar |  | 05_01_23W4 | 09/05/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 09/05/2021 | 2/15/2023 | Y | EXP | 365 | 01/19/2022 | 02/14/2022 | 27 | 0 | 27 |  |  | 5/27/2022 | Connected |  | N
National Grid | STURBRIDGE | 175512 | 01518 | 75 |  |  | Solar |  | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 1 | 3 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 |  | 4/30/2015 | N | EXP | 139 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 7/10/2015 | Connected |  | N
National Grid | RUTLAND | 208913 | 01543 | 7.6 |  |  | Solar |  | 05_01_55W1 | 02/08/2019 | 02/20/2019 | 6 | 0 | 6 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/08/2019 | 7/22/2020 | Y | EXP | 365 | 10/05/2019 | 12/02/2019 | 58 | 0 | 58 |  |  | 2/28/2020 | Connected |  | N
National Grid | BELLINGHAM | 564861 | 02019 | 10 |  |  | Solar |  | 05_05_108W51 | 11/10/2023 | 11/14/2023 | 2 | 0 | 2 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 11/10/2023 | 1/22/2025 | Y | EXP | 365 | 03/07/2024 | 04/20/2024 | 45 | 0 | 45 |  |  | 5/16/2024 | Connected |  | N
National Grid | MARLBOROUGH | 668317 | 01752 | 3.8 |  |  | Solar |  | 05_05_311W4 | 01/30/2025 | 03/19/2025 | 16 | 11 | 5 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | BEVERLY | 175151 | 01915 | 224 |  |  | Solar |  | 05_12_51L1 | 10/30/2013 | 10/30/2013 | 5 | 0 | 5 | 11/07/2013 | 11/07/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 10/30/2013 | 5/30/2014 | Y | EXP | 170 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 | 8/6/2014 | 8/6/2014 | 8/7/2014 | Connected |  | N
National Grid | SALISBURY | 177418 | 01952 | 1050 |  |  | Solar |  | 05_14_275L4 | 12/01/2016 | 12/01/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2016 | 03/03/2017 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 | 12/01/2016 | 1/6/2020 | Y | STD | 620 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 701035 | 01845 | 34.5 |  |  | Solar |  | 05_14_57L1 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 62 | 41 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 175994 | 01821 | 16.35 |  |  | Solar |  | 05_14_70L6 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/16/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 10/6/2016 | 10/6/2016 | 10/6/2016 | Connected |  | N
National Grid | LAWRENCE | 176483 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 05/23/2016 | 05/23/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 11/28/2016 | 12/14/2016 | 12 | 0 | 12 | 4/20/2017 | 4/20/2017 | 4/26/2017 | Connected |  | Y
National Grid | WORCESTER | 494547 | 01602 | 18.432 |  |  | Solar |  | 05_01_23W4 | 01/24/2023 | 05/25/2023 | 85 | 81 | 4 |  |  | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 175511 | 01570 | 140 |  |  | Solar |  | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 4 | 0 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 12/05/2014 | 4/30/2015 | Y | EXP | 64 | 06/01/2015 | 07/08/2015 | 25 | 0 | 25 | 2/25/2015 | 2/25/2015 | 8/21/2015 | Connected |  | N
National Grid | RUTLAND | 210006 | 01543 | 7.6 |  |  | Solar |  | 05_01_55W1 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 658856 | 02019 | 3.8 |  |  | Solar |  | 05_05_108W51 | 12/05/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 3/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 668726 | 01752 | 5.12 |  |  | Solar |  | 05_05_311W4 | 01/29/2025 | 02/13/2025 | 5 | 2 | 3 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | BEVERLY | 175168 | 01915 | 60 |  |  | Solar |  | 05_12_51L1 | 11/14/2012 | 11/14/2012 | 15 | 9 | 6 | 12/11/2012 | 12/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2013 |  | 1/31/2013 | N | EXP | -41 |  |  | 0 | 0 | 0 | 6/25/2013 | 6/25/2013 | 8/21/2013 | Connected |  | N
National Grid | AMESBURY | 177880 | 01913 | 15.2 |  |  | Solar |  | 05_14_275L4 | 10/18/2017 | 10/18/2017 | 7 | 6 | 1 | 10/31/2017 | 10/31/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/24/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | BOXFORD | 712528 | 01921 | 0 |  |  | Solar |  | 05_14_57L1 | 08/15/2025 | 08/25/2025 | 6 | 3 | 3 | 08/26/2025 | 08/26/2025 | 71 | 54 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 176246 | 01821 | 17.2 |  |  | Solar |  | 05_14_70L6 | 04/30/2015 | 04/30/2015 | 5 | 5 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | LAWRENCE | 178185 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 04/13/2018 | 04/13/2018 | 5 | 0 | 5 | 04/23/2018 | 04/23/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 550048 | 01602 | 9.5 |  |  | Solar |  | 05_01_23W4 | 08/22/2023 | 08/23/2023 | 1 | 0 | 1 | 08/24/2023 | 08/24/2023 | 125 | 106 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 175799 | 01570 | 16 |  |  | Solar |  | 05_01_412L1 | 02/27/2015 | 02/27/2015 | 6 | 1 | 5 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 7/31/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 12/23/2015 | Connected |  | N
National Grid | RUTLAND | 245447 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 8/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | BELLINGHAM | 670566 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W51 | 02/06/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | MARLBOROUGH | 511796 | 01752 | 249 |  |  | Solar |  | 05_05_311W5 | 07/06/2023 | 09/01/2023 | 41 | 32 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 07/06/2023 | 6/20/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BEVERLY | 175845 | 01915 | 401 |  |  | Solar |  | 05_12_51L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/22/2015 | 05/22/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 178340 | 01913 | 3294 |  |  | Solar |  | 05_14_275L4 | 11/20/2017 | 11/20/2017 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/28/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 11/20/2017 | 12/31/2019 | Y | STD | 390 | 10/11/2019 | 05/20/2020 | 222 | 0 | 222 |  |  | 12/26/2019 | Connected |  | N
National Grid | BOXFORD | 719310 | 01921 | 20.62 |  |  | Solar |  | 05_14_57L1 | 09/16/2025 | 09/17/2025 | 1 | 0 | 1 | 09/18/2025 | 09/18/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 09/16/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 177836 | 01821 | 15.2 |  |  | Solar |  | 05_14_70L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/16/2018 | Connected |  | N
National Grid | LAWRENCE | 178228 | 01841 | 10.4 |  |  | Solar |  | 05_14_8L2 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 1/10/2019 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | WORCESTER | 577496 | 01602 | 6 |  |  | Solar |  | 05_01_23W4 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | WEBSTER | 177171 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 01/27/2017 | 01/27/2017 | 4 | 4 | 0 | 02/03/2017 | 02/03/2017 | 200 | 0 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/4/2018 | N | EXP | 363 | 06/19/2017 | 08/09/2017 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 282553 | 01543 | 4950 |  |  | Other |  | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 640399 | 02019 | 0 |  |  | Battery Add-On |  | 05_05_108W60 | 09/16/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 703220 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 07/08/2025 | 07/31/2025 | 2 | 0 | 2 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 175842 | 01915 | 100 |  |  | Solar |  | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2015 | N | EXP |  | 07/28/2016 | 03/12/2015 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 178415 | 01913 | 6.6 |  |  | Solar |  | 05_14_275L4 | 11/27/2017 | 11/27/2017 | 32 | 31 | 1 | 01/16/2018 | 01/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 | 11/27/2017 | 12/3/2018 | Y | EXP | 321 | 06/22/2018 | 08/03/2018 | 42 | 0 | 42 |  |  | 11/15/2018 | Connected |  | N
National Grid | WESTFORD | 723177 | 01886 | 17.6 |  |  | Solar |  | 05_14_57L1 | 10/01/2025 | 10/13/2025 | 7 | 3 | 4 | 10/14/2025 | 10/14/2025 | 54 | 24 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 189305 | 01821 | 7.6 |  |  | Solar |  | 05_14_70L6 | 06/27/2018 | 06/27/2018 | 9 | 6 | 3 | 09/14/2018 | 09/14/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 178295 | 01841 | 15.2 |  |  | Solar |  | 05_14_8L2 | 11/15/2017 | 11/15/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 11/21/2018 | N | EXP | 153 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 652348 | 01602 | 7.6 |  |  | Solar |  | 05_01_23W4 | 11/05/2024 | 11/20/2024 | 5 | 1 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 5/28/2026 | Y | EXP | 365 | 02/25/2025 |  | 311 | 118 | 193 |  |  | 7/11/2025 | Connected |  | N
National Grid | WEBSTER | 177168 | 01570 | 4980 |  |  | Solar |  | 05_01_412L1 | 01/26/2017 | 02/01/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2017 | 04/05/2017 | 45 | 33 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  |  | N | STD | 1202 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 284371 | 01543 | 4950 |  |  | Other |  | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 171881 | 02019 | 10 |  |  | Solar |  | 05_05_108W60 | 07/01/2018 | 07/01/2018 | 5 | 5 | 0 | 07/11/2018 | 07/11/2018 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 739106 | 01752 | 10 |  |  | Solar |  | 05_05_311W5 | 12/09/2025 | 12/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BEVERLY | 175841 | 01915 | 100 |  |  | Solar |  | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 756 | 0 | 756 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/06/2015 | 6/29/2018 | Y | EXP | 1128 | 07/28/2016 |  | 416 | 0 | 416 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | SALISBURY | 178618 | 01952 | 7.6 |  |  | Solar |  | 05_14_275L4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 | 01/31/2018 | 11/29/2019 | Y | EXP | 631 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | WESTFORD | 733497 | 01886 | 19 |  |  | Solar |  | 05_14_57L1 | 01/02/2026 |  | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BILLERICA | 343928 | 01821 | 19 |  |  | Solar |  | 05_14_70L6 | 02/25/2021 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 190234 | 01841 | 70.2 |  |  | Solar |  | 05_14_8L2 | 08/10/2018 | 08/28/2018 | 11 | 0 | 11 | 08/29/2018 | 08/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 674211 | 01602 | 5.7 |  |  | Solar |  | 05_01_23W4 | 02/25/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DOUGLAS | 177197 | 01516 | 7.6 |  |  | Solar |  | 05_01_412L1 | 11/01/2016 | 11/01/2016 | 3 | 3 | 0 | 11/07/2016 | 11/07/2016 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/01/2016 | 5/7/2018 | Y | EXP | 538 | 10/20/2017 | 04/11/2018 | 101 | 0 | 101 |  |  | 5/21/2018 | Connected |  | N
National Grid | RUTLAND | 294525 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2020 | 06/06/2020 | 10/7/2021 | Y | EXP | 365 | 04/07/2021 | 04/15/2021 | 8 | 0 | 8 |  |  | 8/14/2021 | Connected |  | N
National Grid | BELLINGHAM | 175746 | 02019 | 20 |  |  | Solar |  | 05_05_108W60 | 10/29/2014 | 10/29/2014 | 5 | 3 | 2 | 11/10/2014 | 11/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 1/15/2015 | N | EXP | 64 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 3/3/2015 | Connected |  | N
National Grid | MARLBOROUGH | 158029 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 01/26/2016 | 01/26/2016 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 175920 | 01915 | 9.8 |  |  | Solar |  | 05_12_51L1 | 05/28/2015 | 05/28/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 187940 | 01913 | 999.9 |  |  | Solar |  | 05_14_275L4 | 06/13/2018 | 06/13/2018 | 4 | 3 | 1 |  |  | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 | 06/13/2018 | 5/17/2021 | Y | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176080 | 01886 | 323 |  |  | Solar |  | 05_14_57L1 | 08/21/2015 | 08/21/2015 | 0 | 0 | 0 | 08/21/2015 | 08/21/2015 | 306 | 14 | 292 | 11/05/2015 | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 |  | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 4/15/2017 | Y | EXP | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 367044 | 01821 | 19 |  |  | Solar |  | 05_14_70L6 | 06/30/2021 | 07/01/2021 | 1 | 0 | 1 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 199996 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 11/01/2018 | 11/19/2018 | 1 | 0 | 1 | 11/20/2018 | 11/20/2018 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 196201 | 01602 | 7.6 |  |  | Solar |  | 05_01_24W1 | 09/18/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 57 | 54 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 177263 | 01570 | 19 |  |  | Solar |  | 05_01_412L1 | 08/23/2016 | 08/23/2016 | 2 | 2 | 0 | 08/26/2016 | 08/26/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 8/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 309418 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 08/27/2020 | 08/28/2020 | 1 | 1 | 0 | 08/31/2020 | 08/31/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2020 | Connected |  | N
National Grid | BELLINGHAM | 175939 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W60 | 01/21/2015 | 01/21/2015 | 23 | 22 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 5/31/2015 | N | EXP | 83 |  |  | 0 | 0 | 0 | 3/13/2015 | 3/13/2015 | 12/7/2015 | Connected |  | N
National Grid | MARLBOROUGH | 175319 | 01752 | 440.8 |  |  | Solar |  | 05_05_311W5 | 08/29/2014 | 08/29/2014 | 6 | 2 | 4 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | BEVERLY | 175991 | 01915 | 100 |  |  | Solar |  | 05_12_51L1 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 | 03/26/2015 | 03/26/2015 | 749 | 0 | 749 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/23/2015 | 5/31/2018 | Y | EXP | 1099 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | SALISBURY | 194215 | 01952 | 325 |  |  | Solar |  | 05_14_275L4 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 1 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176617 | 01886 | 200 |  |  | Solar |  | 05_14_57L1 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2016 |  | 2/22/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 5/31/2016 | 5/31/2016 | 5/31/2016 | Connected |  | Y
National Grid | BILLERICA | 412558 | 01821 | 9.8 |  |  | Solar |  | 05_14_70L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/01/2022 | 9/20/2023 | Y | EXP | 365 | 08/18/2022 | 09/15/2022 | 29 | 0 | 29 |  |  | 1/4/2023 | Connected |  | N
National Grid | LAWRENCE | 207111 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 02/21/2019 | 03/05/2019 | 7 | 0 | 7 | 03/06/2019 | 03/06/2019 | 15 | 8 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 02/21/2019 | 7/22/2020 | Y | EXP | 365 | 01/16/2020 | 02/28/2020 | 43 | 0 | 43 |  |  | 6/18/2020 | Connected |  | N
National Grid | WORCESTER | 193107 | 01602 | 10 |  |  | Solar |  | 05_01_24W1 | 08/08/2018 | 10/26/2018 | 38 | 28 | 10 | 10/29/2018 | 10/29/2018 | 36 | 8 | 28 | 11/06/2018 | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 |  | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 | 12/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 177697 | 01570 | 3990 |  |  | Solar |  | 05_01_412L1 | 03/21/2017 | 03/21/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 04/24/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 312260 | 01543 | 5.52 |  |  | Solar |  | 05_01_55W1 | 09/29/2020 | 12/03/2020 | 43 | 40 | 3 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 | 09/29/2020 | 12/24/2022 | Y | EXP | 550 | 01/28/2021 | 02/25/2021 | 28 | 0 | 28 |  |  | 12/8/2022 | Connected |  | N
National Grid | BELLINGHAM | 176333 | 02019 | 6 |  |  | Solar |  | 05_05_108W60 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 09/15/2015 | 9/21/2016 | Y | EXP | 348 | 10/18/2016 | 10/27/2016 | 7 | 0 | 7 | 12/13/2016 | 12/13/2016 | 12/16/2016 | Connected |  | N
National Grid | MARLBOROUGH | 176533 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/15/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/8/2016 | 7/8/2016 | 7/12/2016 | Connected |  | N
National Grid | BEVERLY | 176135 | 01915 | 3520 |  |  | Solar |  | 05_12_51L1 | 04/16/2015 | 04/16/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/20/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/06/2017 | 07/27/2018 | 224 | 0 | 224 | 8/4/2016 | 04/16/2015 | 12/31/2020 | Y | STD | 1310 | 05/22/2020 | 10/26/2020 | 158 | 5 | 153 |  |  | 12/23/2020 | Connected |  | N
National Grid | AMESBURY | 333336 | 01913 | 5.04 |  |  | Solar |  | 05_14_275L4 | 12/21/2020 | 12/22/2020 | 0 | 0 | 0 | 12/23/2020 | 12/23/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 12/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2021 | Connected |  | N
National Grid | WESTFORD | 242635 | 01886 | 0 |  |  | Solar |  | 05_14_57L1 | 07/09/2019 | 07/15/2019 | 3 | 0 | 3 | 07/16/2019 | 07/16/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 7/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | BILLERICA | 430494 | 01821 | 15.2 |  |  | Solar |  | 05_14_70L6 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | LAWRENCE | 209338 | 01841 | 11.4 |  |  | Solar |  | 05_14_8L2 | 04/22/2019 | 04/26/2019 | 3 | 0 | 3 | 04/29/2019 | 04/29/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/22/2019 | 7/22/2020 | Y | EXP | 365 | 04/25/2020 | 06/12/2020 | 48 | 0 | 48 |  |  | 7/7/2020 | Connected |  | N
National Grid | WORCESTER | 261638 | 01602 | 10 |  |  | Solar |  | 05_01_24W1 | 10/25/2019 | 10/28/2019 | 0 | 0 | 0 | 10/29/2019 | 10/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 | 10/25/2019 | 10/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2020 | Connected |  | N
National Grid | WEBSTER | 178538 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 01/25/2018 | 02/08/2018 | 9 | 0 | 9 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/31/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | RUTLAND | 318655 | 01543 | 0 |  |  | Other |  | 05_01_55W1 | 12/04/2020 | 01/05/2021 | 20 | 16 | 4 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/09/2021 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 176365 | 01504 | 3.8 |  |  | Solar |  | 05_05_108W60 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 |  | 3/15/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177888 | 01752 | 300 |  |  | Natural Gas |  | 05_05_311W5 | 04/11/2017 | 04/11/2017 | 55 | 52 | 3 | 06/30/2017 | 06/30/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 4/17/2018 | N | EXP | 264 |  |  | 0 | 0 | 0 |  |  | 9/27/2018 | Connected |  | N
National Grid | BEVERLY | 176345 | 01915 | 6.67 |  |  | Solar |  | 05_12_51L1 | 02/25/2015 | 02/25/2015 | 9 | 5 | 4 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/11/2016 | 04/30/2016 | 54 | 0 | 54 | 3/17/2015 | 3/17/2015 | 10/12/2016 | Connected |  | N
National Grid | AMESBURY | 339860 | 01913 | 10 |  |  | Solar |  | 05_14_275L4 | 02/01/2021 | 02/03/2021 | 1 | 0 | 1 | 02/04/2021 | 02/04/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 |  | 2/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | WESTFORD | 283707 | 01886 | 600 |  |  | Natural Gas |  | 05_14_57L1 | 12/02/2021 | 01/13/2022 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 03/14/2022 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 | 12/02/2021 | 11/6/2024 | Y | STD | 279 | 04/04/2024 | 04/18/2024 | 15 | 0 | 15 |  |  | 9/24/2024 | Connected |  | N
National Grid | BILLERICA | 460075 | 01821 | 15.2 |  |  | Solar |  | 05_14_70L6 | 09/19/2022 | 09/22/2022 | 3 | 0 | 3 | 09/23/2022 | 09/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 3/6/2024 | N | EXP | 365 | 01/07/2023 | 03/03/2023 | 56 | 0 | 56 |  |  | 5/24/2023 | Connected |  | N
National Grid | LAWRENCE | 212812 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 03/23/2019 | 03/25/2019 | 0 | 0 | 0 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  | 8/30/2019 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | WORCESTER | 293766 | 01605 | 0 |  |  | Battery Add-On |  | 05_01_24W1 | 05/28/2020 | 05/29/2020 | 0 | 0 | 0 | 06/01/2020 | 06/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/28/2020 | 5/28/2021 | Y | EXP | 365 | 09/01/2020 | 09/29/2020 | 28 | 0 | 28 |  |  | 9/30/2020 | Connected |  | N
National Grid | WEBSTER | 184051 | 01570 | 2375 |  |  | Solar |  | 05_01_412L1 | 04/30/2018 | 04/30/2018 | 14 | 13 | 1 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 452194 | 01543 | 6.09 |  |  | Solar |  | 05_01_55W1 | 10/27/2022 | 11/22/2022 | 17 | 15 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2022 | 10/27/2022 | 6/14/2024 | Y | EXP | 365 | 06/06/2023 | 06/14/2023 | 9 | 0 | 9 |  |  | 7/12/2023 | Connected |  | N
National Grid | BLACKSTONE | 176355 | 01504 | 6 |  |  | Solar |  | 05_05_108W60 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2015 | 05/14/2015 | 12/31/2016 | Y | EXP | 578 | 11/19/2015 | 12/15/2015 | 17 | 0 | 17 | 3/22/2016 | 3/22/2016 | 3/28/2016 | Connected |  | N
National Grid | MARLBOROUGH | 178141 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 03/22/2018 | 03/22/2018 | 18 | 9 | 9 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 3/28/2019 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 176394 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2016 |  | 2/8/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 343629 | 01913 | 499 |  |  | Solar |  | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 | 12/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 295174 | 01886 | 7.68 |  |  | Solar |  | 05_14_57L1 | 06/05/2020 | 07/09/2020 | 24 | 23 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | BILLERICA | 579214 | 01821 | 34.5 |  |  | Solar |  | 05_14_70L6 | 12/20/2023 |  | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 212730 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/20/2019 | 6/17/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 4/17/2020 | Connected |  | N
National Grid | WORCESTER | 429602 | 01605 | 8.7 |  |  | Solar |  | 05_01_24W1 | 06/09/2022 | 06/22/2022 | 8 | 6 | 2 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/09/2022 | 11/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | WEBSTER | 189710 | 01570 | 2000 |  |  | Solar |  | 05_01_412L1 | 07/16/2018 | 08/06/2018 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2018 | 11/30/2018 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 367324 | 01543 | 11.025 |  |  | Solar |  | 05_01_55W1 | 07/25/2021 | 09/03/2021 | 30 | 30 | 0 | 09/07/2021 | 09/07/2021 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | BLACKSTONE | 176417 | 01504 | 10 |  |  | Solar |  | 05_05_108W60 | 12/02/2015 | 12/02/2015 | 3 | 3 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/8/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/15/2015 | 12/15/2015 | 6/6/2016 | Connected |  | N
National Grid | MARLBOROUGH | 178593 | 01752 | 240 |  |  | Solar |  | 05_05_311W5 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 | 04/10/2018 | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 177713 | 01915 | 108 |  |  | Solar |  | 05_12_51L1 | 07/26/2017 | 07/26/2017 | 30 | 29 | 1 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 | 07/26/2017 | 7/31/2018 | Y | EXP | 322 | 09/12/2017 | 09/12/2017 | 29 | 29 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | AMESBURY | 366611 | 01913 | 10 |  |  | Solar |  | 05_14_275L4 | 07/28/2021 | 08/17/2021 | 14 | 13 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | WESTFORD | 311522 | 01886 | 11.4 |  |  | Solar |  | 05_14_57L1 | 01/20/2021 | 01/25/2021 | 2 | 0 | 2 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/20/2021 | 4/5/2022 | Y | EXP | 365 | 08/06/2021 | 12/29/2021 | 146 | 7 | 139 |  |  | 2/9/2022 | Connected |  | N
National Grid | BILLERICA | 588066 | 01821 | 9.765 |  |  | Solar |  | 05_14_70L6 | 02/12/2024 | 02/21/2024 | 7 | 5 | 2 | 02/22/2024 | 02/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/12/2024 | 4/24/2025 | Y | EXP | 365 | 05/23/2024 | 09/13/2024 | 93 | 0 | 93 |  |  | 7/26/2024 | Connected |  | N
National Grid | LAWRENCE | 225186 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 05/03/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 05/03/2019 | 10/23/2021 | Y | EXP | 365 | 12/09/2020 | 01/08/2021 | 30 | 0 | 30 |  |  | 5/27/2021 | Connected |  | N
National Grid | WORCESTER | 442032 | 01605 | 3.8 |  |  | Solar |  | 05_01_24W1 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N
National Grid | WEBSTER | 202707 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 12/06/2018 | 01/14/2019 | 25 | 20 | 5 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2019 | 12/06/2018 | 10/30/2019 | Y | EXP | 280 | 06/26/2019 | 08/26/2019 | 61 | 0 | 61 |  |  | 9/16/2019 | Connected |  | N
National Grid | RUTLAND | 368515 | 01543 | 4300 |  |  | Solar |  | 05_01_55W1 | 08/10/2021 | 09/07/2021 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2021 | 10/05/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 176794 | 01504 | 7.6 |  |  | Solar |  | 05_05_108W60 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 329 | 06/28/2016 | 09/15/2016 | 55 | 0 | 55 | 4/6/2016 | 4/6/2016 | 11/18/2016 | Connected |  | N
National Grid | MARLBOROUGH | 178613 | 01752 | 240 |  |  | Solar |  | 05_05_311W5 | 12/14/2017 | 12/14/2017 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 177916 | 01915 | 144 |  |  | Solar |  | 05_12_51L1 | 10/20/2017 | 10/20/2017 | 4 | 0 | 4 | 10/27/2017 | 10/27/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 10/28/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | AMESBURY | 478526 | 01913 | 22.8 |  |  | Solar |  | 05_14_275L4 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 318483 | 01886 | 20 |  |  | Solar |  | 05_14_57L1 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2021 | Connected |  | N
National Grid | BILLERICA | 604030 | 01821 | 5 |  |  | Solar |  | 05_14_70L6 | 04/18/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 242394 | 01844 | 3.8 |  |  | Solar |  | 05_14_8L2 | 08/01/2019 | 08/01/2019 | 0 | 0 | 0 | 08/02/2019 | 08/02/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | WORCESTER | 447540 | 01605 | 3.8 |  |  | Solar |  | 05_01_24W1 | 12/09/2022 | 02/14/2023 | 44 | 42 | 2 | 02/15/2023 | 02/15/2023 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2023 | Connected |  | N
National Grid | WEBSTER | 306367 | 01570 | 6 |  |  | Solar |  | 05_01_412L1 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 9/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 378372 | 01543 | 5.52 |  |  | Solar |  | 05_01_55W1 | 10/11/2021 | 10/19/2021 | 6 | 6 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/11/2021 | 10/21/2023 | Y | EXP | 555 | 02/01/2022 | 02/14/2022 | 14 | 0 | 14 |  |  | 8/23/2023 | Connected |  | N
National Grid | BELLINGHAM | 176831 | 02019 | 6 |  |  | Solar |  | 05_05_108W60 | 02/25/2016 | 02/25/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/5/2017 | N | EXP | 327 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 2/22/2017 | Connected |  | N
National Grid | MARLBOROUGH | 194004 | 01752 | 136 |  |  | Solar |  | 05_05_311W5 | 08/30/2018 | 09/27/2018 | 8 | 5 | 3 | 09/28/2018 | 09/28/2018 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 322713 | 01915 | 14.805 |  |  | Solar |  | 05_12_51L1 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/13/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2021 | Connected |  | N
National Grid | AMESBURY | 502722 | 01913 | 2000 |  |  | Solar |  | 05_14_275L4 | 03/29/2023 | 08/25/2023 | 103 | 93 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/18/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 03/29/2023 | 10/20/2025 | Y | STD | 252 | 01/14/2025 | 08/04/2025 | 203 | 0 | 203 |  |  | 9/30/2025 | Connected |  | N
National Grid | WESTFORD | 330673 | 01886 | 15.2 |  |  | Solar |  | 05_14_57L1 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  | 11/3/2022 | N | EXP | 630 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 610202 | 01821 | 4.188 |  |  | Solar |  | 05_14_70L6 | 05/14/2024 | 07/09/2024 | 16 | 9 | 7 | 07/10/2024 | 07/10/2024 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 05/14/2024 | 9/10/2025 | Y | EXP | 365 | 09/26/2024 | 10/24/2024 | 29 | 0 | 29 |  |  | 12/4/2024 | Connected |  | N
National Grid | LAWRENCE | 278952 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 02/27/2020 |  | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 519419 | 01605 | 12.47 |  |  | Solar |  | 05_01_24W1 | 07/14/2023 | 07/17/2023 | 1 | 0 | 1 | 07/18/2023 | 07/18/2023 | 23 | 0 | 23 | 09/20/2023 | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/25/2023 |  | 11/26/2024 | N | EXP | 365 | 01/03/2024 | 02/23/2024 | 52 | 0 | 52 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 312153 | 01570 | 5.76 |  |  | Solar |  | 05_01_412L1 | 12/01/2020 | 12/03/2020 | 1 | 0 | 1 | 12/04/2020 | 12/04/2020 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/01/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 390938 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 11/08/2021 | 12/13/2021 | 3 | 1 | 2 | 11/12/2021 | 11/12/2021 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/08/2021 |  | Y | EXP | 365 | 03/08/2022 | 04/11/2022 | 35 | 0 | 35 |  |  | 4/19/2022 | Connected |  | N
National Grid | BELLINGHAM | 177051 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W60 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2017 | 01/11/2017 | 1/18/2018 | Y | EXP | 364 | 03/08/2017 | 03/01/2017 | 0 | 0 | 0 | 6/19/2017 | 6/19/2017 | 6/22/2017 | Connected |  | N
National Grid | MARLBOROUGH | 200830 | 01752 | 10 |  |  | Solar |  | 05_05_311W5 | 11/09/2018 | 11/20/2018 | 4 | 0 | 4 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  | 12/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | BEVERLY | 326457 | 01915 | 9.86 |  |  | Solar |  | 05_12_51L1 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2021 | Connected |  | N
National Grid | AMESBURY | 586162 | 01913 | 1375 |  |  | Solar |  | 05_14_275L4 | 02/05/2024 | 02/22/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2024 | 02/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 391848 | 01886 | 0 |  |  | Other |  | 05_14_57L1 | 12/16/2021 | 01/05/2022 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 02/03/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 645607 | 01821 | 5.76 |  |  | Solar |  | 05_14_70L6 | 11/20/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | LAWRENCE | 290049 | 01841 | 8.19 |  |  | Solar |  | 05_14_8L2 | 06/09/2020 | 06/15/2020 | 3 | 0 | 3 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/09/2020 | 2/25/2022 | Y | EXP | 365 | 04/14/2021 | 09/22/2021 | 161 | 3 | 158 |  |  | 11/17/2021 | Connected |  | Y
National Grid | WORCESTER | 525753 | 01605 | 6 |  |  | Solar |  | 05_01_24W1 | 06/21/2023 | 06/21/2023 | 0 | 0 | 0 | 06/22/2023 | 06/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 365160 | 01570 | 15.6 |  |  | Solar |  | 05_01_412L1 | 06/21/2021 | 06/23/2021 | 2 | 0 | 2 | 06/24/2021 | 06/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2021 | 06/21/2021 | 11/5/2023 | Y | EXP | 365 | 07/15/2022 | 08/26/2022 | 43 | 0 | 43 |  |  | 12/7/2022 | Connected |  | N
National Grid | RUTLAND | 417891 | 01543 | 6.528 |  |  | Solar |  | 05_01_55W1 | 04/29/2022 | 04/29/2022 | 0 | 0 | 0 | 05/02/2022 | 05/02/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2022 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N
National Grid | BELLINGHAM | 177115 | 02019 | 10 |  |  | Solar |  | 05_05_108W60 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 | 08/05/2016 | 8/14/2017 | Y | EXP | 364 | 12/05/2016 | 01/16/2017 | 28 | 0 | 28 | 3/16/2017 | 3/16/2017 | 3/20/2017 | Connected |  | N
National Grid | MARLBOROUGH | 205105 | 01752 | 5 |  |  | Solar |  | 05_05_311W5 | 01/17/2019 | 01/30/2019 | 8 | 8 | 0 | 01/31/2019 | 01/31/2019 | 152 | 0 | 152 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 333031 | 01915 | 100 |  |  | Solar |  | 05_12_51L1 | 03/19/2021 | 12/08/2021 | 11 | 0 | 11 | 04/06/2021 | 04/06/2021 | 129 | 106 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 603133 | 01913 | 17.6 |  |  | Solar |  | 05_14_275L4 | 04/10/2024 | 04/29/2024 | 13 | 9 | 4 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | WESTFORD | 467561 | 01886 | 0 |  |  | Battery Add-On |  | 05_14_57L1 | 04/04/2023 | 05/22/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 06/23/2023 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 650194 | 01821 | 18.24 |  |  | Solar |  | 05_14_70L6 | 10/28/2024 | 10/30/2024 | 2 | 0 | 2 | 10/31/2024 | 10/31/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | LAWRENCE | 291189 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 05/08/2020 | 05/11/2020 | 0 | 0 | 0 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/11/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 532272 | 01606 | 7.68 |  |  | Solar |  | 05_01_24W1 | 06/14/2023 | 06/20/2023 | 4 | 0 | 4 | 06/21/2023 | 06/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 371739 | 01570 | 15.2 |  |  | Solar |  | 05_01_412L1 | 07/23/2021 | 07/26/2021 | 2 | 1 | 1 | 07/27/2021 | 07/27/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2022 | Connected |  | N
National Grid | RUTLAND | 505628 | 01543 | 7.83 |  |  | Solar |  | 05_01_55W1 | 03/03/2023 | 03/07/2023 | 2 | 0 | 2 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 8/1/2024 | Y | EXP | 365 | 10/04/2023 | 10/16/2023 | 13 | 0 | 13 |  |  | 10/30/2023 | Connected |  | N
National Grid | BELLINGHAM | 177305 | 02019 | 50.4 |  |  | Solar |  | 05_05_108W60 | 11/15/2016 | 11/15/2016 | 10 | 10 | 0 | 11/30/2016 | 11/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2016 |  | 11/21/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/17/2017 | Connected |  | N
National Grid | MARLBOROUGH | 289784 | 01752 | 8.41 |  |  | Solar |  | 05_05_311W5 | 04/29/2020 | 05/05/2020 | 3 | 0 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | BEVERLY | 335686 | 01915 | 7.68 |  |  | Solar |  | 05_12_51L1 | 01/20/2021 | 02/10/2021 | 15 | 14 | 1 | 02/11/2021 | 02/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 | 01/20/2021 | 2/10/2022 | Y | EXP | 365 | 05/15/2021 | 05/14/2021 | 0 | 0 | 0 |  |  | 5/18/2021 | Connected |  | N
National Grid | AMESBURY | 626752 | 01913 | 3.8 |  |  | Solar |  | 05_14_275L4 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 07/22/2024 | 9/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | WESTFORD | 638330 | 01886 | 9.28 |  |  | Solar |  | 05_14_57L1 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 661714 | 01821 | 10 |  |  | Solar |  | 05_14_70L6 | 12/19/2024 | 01/27/2025 | 13 | 10 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | LAWRENCE | 296373 | 01841 | 6.93 |  |  | Solar |  | 05_14_8L2 | 06/30/2020 | 07/14/2020 | 10 | 7 | 3 | 07/15/2020 | 07/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  | 6/29/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 541036 | 01605 | 3.8 |  |  | Solar |  | 05_01_24W1 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 379708 | 01570 | 9.8 |  |  | Solar |  | 05_01_412L1 | 09/15/2021 | 12/20/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 4/26/2023 | Y | EXP | 365 | 03/31/2022 | 04/26/2022 | 27 | 0 | 27 |  |  | 5/24/2022 | Connected |  | N
National Grid | RUTLAND | 504707 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 177521 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W60 | 09/29/2016 | 09/29/2016 | 3 | 3 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/29/2016 | 10/4/2017 | Y | EXP | 364 | 01/03/2017 | 01/16/2017 | 9 | 0 | 9 | 2/16/2017 | 2/16/2017 | 2/22/2017 | Connected |  | N
National Grid | MARLBOROUGH | 324974 | 01752 | 115.2 |  |  | Solar |  | 05_05_311W5 | 11/10/2020 |  | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 335860 | 01915 | 5.52 |  |  | Solar |  | 05_12_51L1 | 01/18/2021 | 01/25/2021 | 4 | 0 | 4 | 04/13/2021 | 04/13/2021 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 631814 | 01913 | 7.6 |  |  | Solar |  | 05_14_275L4 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/12/2024 | 11/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 646518 | 01886 | 10 |  |  | Solar |  | 05_14_57L1 | 10/11/2024 | 10/17/2024 | 3 | 0 | 3 | 10/18/2024 | 10/18/2024 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | BILLERICA | 672015 | 01821 | 6.08 |  |  | Solar |  | 05_14_70L6 | 02/13/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | LAWRENCE | 306308 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 08/28/2020 | 09/02/2020 | 2 | 0 | 2 | 09/03/2020 | 09/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 553080 | 01605 | 11.5 |  |  | Solar |  | 05_01_24W1 | 09/06/2023 | 09/07/2023 | 1 | 0 | 1 | 09/08/2023 | 09/08/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 473685 | 01570 | 11.02 |  |  | Solar |  | 05_01_412L1 | 11/17/2022 | 12/20/2022 | 22 | 20 | 2 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | RUTLAND | 506739 | 01543 | 6.96 |  |  | Solar |  | 05_01_55W1 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 5/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | BELLINGHAM | 177602 | 02019 | 7.04 |  |  | Solar |  | 05_05_108W60 | 07/19/2017 | 07/19/2017 | 7 | 6 | 1 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/24/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 10/3/2017 | Connected |  | N
National Grid | MARLBOROUGH | 329523 | 01752 | 100.8 |  |  | Solar |  | 05_05_311W5 | 12/14/2020 | 12/21/2020 | 4 | 0 | 4 | 12/22/2020 | 12/22/2020 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 12/14/2020 |  | Y | EXP |  | 04/07/2021 | 12/20/2021 | 257 | 7 | 250 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 377712 | 01915 | 67 |  |  | Solar |  | 05_12_51L1 | 09/10/2021 | 11/17/2021 | 46 | 36 | 10 | 11/18/2021 | 11/18/2021 | 99 | 51 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 09/10/2021 | 4/30/2023 | Y | EXP | 157 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | AMESBURY | 659939 | 01913 | 17.1 |  |  | Solar |  | 05_14_275L4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | WESTFORD | 651800 | 01886 | 7.6 |  |  | Solar |  | 05_14_57L1 | 11/04/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/12/2026 | Y | EXP | 365 | 05/16/2025 |  | 231 | 0 | 231 |  |  | 11/24/2025 | Connected |  | N
National Grid | BILLERICA | 712233 | 01821 | 17.92 |  |  | Solar |  | 05_14_70L6 | 08/18/2025 | 08/19/2025 | 1 | 0 | 1 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | LAWRENCE | 322575 | 01841 | 10 |  |  | Solar |  | 05_14_8L2 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/22/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 5/29/2021 | Connected |  | N
National Grid | WORCESTER | 568633 | 01605 | 7.6 |  |  | Solar |  | 05_01_24W1 | 11/21/2023 | 11/30/2023 | 6 | 2 | 4 | 12/01/2023 | 12/01/2023 | 86 | 66 | 20 | 06/05/2024 | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/12/2025 | N | EXP | 365 | 09/13/2024 | 09/21/2024 | 9 | 0 | 9 |  |  | 10/18/2024 | Connected |  | N
National Grid | WEBSTER | 490569 | 01570 | 5.235 |  |  | Solar |  | 05_01_412L1 | 03/06/2024 |  | 108 | 94 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 526469 | 01543 | 9.86 |  |  | Solar |  | 05_01_55W1 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 58 | 38 | 20 | 09/26/2023 | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 3/4/2025 | N | EXP | 365 | 04/19/2024 | 05/14/2024 | 26 | 0 | 26 |  |  | 6/6/2024 | Connected |  | N
National Grid | BELLINGHAM | 177667 | 02019 | 10 |  |  | Solar |  | 05_05_108W60 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/02/2017 | 11/30/2017 | 35 | 0 | 35 | 12/20/2017 | 12/20/2017 | 1/5/2018 | Connected |  | N
National Grid | MARLBOROUGH | 355075 | 01752 | 166.6 |  |  | Solar |  | 05_05_311W5 | 05/21/2021 | 06/06/2021 | 9 | 0 | 9 |  |  | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 495132 | 01915 | 7.6 |  |  | Solar |  | 05_12_51L1 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 65 | 50 | 15 | 06/16/2023 | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 12/16/2024 | N | EXP | 365 | 01/03/2024 | 01/02/2024 | 0 | 0 | 0 |  |  | 1/24/2024 | Connected |  | N
National Grid | AMESBURY | 662699 | 01913 | 7.83 |  |  | Solar |  | 05_14_275L4 | 12/26/2024 | 01/21/2025 | 5 | 1 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/26/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WESTFORD | 665155 | 01886 | 10 |  |  | Solar |  | 05_14_57L1 | 01/13/2025 | 02/25/2025 | 19 | 15 | 4 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | BILLERICA | 174143 | 01821 | 2000 |  |  | Solar |  | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 349178 | 01844 | 9.8 |  |  | Solar |  | 05_14_8L2 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 582505 | 01606 | 10 |  |  | Solar |  | 05_01_24W1 | 02/16/2024 | 02/23/2024 | 4 | 0 | 4 | 02/26/2024 | 02/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 519952 | 01570 | 11.4 |  |  | Solar |  | 05_01_412L1 | 04/19/2023 | 04/26/2023 | 6 | 5 | 1 |  |  | 70 | 51 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 534007 | 01543 | 6 |  |  | Solar |  | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 2 | 0 | 2 | 07/03/2023 | 07/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 177874 | 02019 | 3600 |  |  | Solar |  | 05_05_108W60 | 08/14/2017 | 08/14/2017 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2017 | 09/25/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2018 | 08/14/2017 | 9/26/2022 | Y | STD | 505 | 01/22/2022 | 06/01/2022 | 131 | 0 | 131 |  |  | 8/3/2022 | Connected |  | N
National Grid | MARLBOROUGH | 365643 | 01752 | 7.54 |  |  | Solar |  | 05_05_311W5 | 07/07/2021 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 518913 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 09/29/2023 | 10/06/2023 | 6 | 3 | 3 | 10/10/2023 | 10/10/2023 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 667969 | 01913 | 7.6 |  |  | Solar |  | 05_14_275L4 | 01/27/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 673926 | 01886 | 0 |  |  | Battery Add-On |  | 05_14_57L1 | 02/24/2025 | 03/17/2025 | 15 | 12 | 3 | 03/18/2025 | 03/18/2025 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | BILLERICA | 174142 | 01821 | 2000 |  |  | Solar |  | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 413386 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 03/08/2022 | 03/09/2022 | 1 | 0 | 1 | 03/10/2022 | 03/10/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 03/08/2022 | 7/12/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 8/25/2023 | Connected |  | N
National Grid | WORCESTER | 595776 | 01605 | 3.8 |  |  | Solar |  | 05_01_24W1 | 03/15/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N
National Grid | DOUGLAS | 535445 | 01516 | 3 |  |  | Solar |  | 05_01_412L1 | 06/21/2023 | 06/26/2023 | 3 | 1 | 2 | 06/27/2023 | 06/27/2023 | 463 | 138 | 325 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 536354 | 01543 | 5 |  |  | Solar |  | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 3 | 1 | 2 | 07/03/2023 | 07/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 | 06/28/2023 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | BLACKSTONE | 177909 | 01504 | 11.4 |  |  | Solar |  | 05_05_108W60 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/16/2017 | 8/21/2018 | Y | EXP | 348 | 01/18/2018 | 02/14/2018 | 19 | 0 | 19 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N
National Grid | MARLBOROUGH | 592139 | 01752 | 6 |  |  | Solar |  | 05_05_311W5 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/27/2024 | 3/22/2026 | Y | EXP | 365 | 04/17/2024 | 04/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 521346 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 04/26/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 672950 | 01913 | 15.2 |  |  | Solar |  | 05_14_275L4 | 02/24/2025 | 03/03/2025 | 5 | 2 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | WESTFORD | 692947 | 01886 | 15.2 |  |  | Solar |  | 05_14_57L1 | 05/20/2025 | 05/27/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | BILLERICA | 174565 | 01821 | 4999 |  |  | Solar |  | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2012 | 09/21/2012 | 0 | 0 | 0 | 12/12/2012 | 08/05/2011 | 12/1/2014 | Y | STD | 719 | 05/19/2014 | 11/12/2014 | 121 | 0 | 121 | 7/31/2014 | 7/31/2014 | 8/13/2014 | Connected |  | N
National Grid | LAWRENCE | 428539 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 05/19/2022 | 05/24/2022 | 4 | 3 | 1 | 05/25/2022 | 05/25/2022 | 122 | 105 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 05/19/2022 | 4/9/2024 | Y | EXP | 365 | 03/15/2023 | 04/08/2023 | 25 | 0 | 25 |  |  | 6/12/2023 | Connected |  | N
National Grid | WORCESTER | 595773 | 01605 | 6.09 |  |  | Solar |  | 05_01_24W1 | 04/08/2024 | 05/17/2024 | 7 | 5 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | WEBSTER | 555700 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 09/18/2023 | 09/19/2023 | 1 | 0 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2024 | Connected |  | N
National Grid | RUTLAND | 561632 | 01543 | 7.6 |  |  | Solar |  | 05_01_55W1 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 10/13/2023 | 5/4/2025 | Y | EXP | 365 | 10/02/2024 | 10/10/2024 | 9 | 0 | 9 |  |  | 10/24/2024 | Connected |  | N
National Grid | BLACKSTONE | 178247 | 01504 | 4990 |  |  | Solar |  | 05_05_108W60 | 03/27/2018 | 03/27/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 647601 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 10/18/2024 | 11/19/2024 | 8 | 5 | 3 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | BEVERLY | 575451 | 01915 | 3.48 |  |  | Solar |  | 05_12_51L1 | 02/08/2024 | 02/14/2024 | 4 | 0 | 4 | 02/15/2024 | 02/15/2024 | 84 | 79 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | AMESBURY | 690639 | 01913 | 5.76 |  |  | Solar |  | 05_14_275L4 | 05/09/2025 | 06/02/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 726835 | 01886 | 17.48 |  |  | Solar |  | 05_14_57L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 174575 | 01821 | 2000 |  |  | Solar |  | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 459549 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 11/18/2022 | 11/27/2022 | 5 | 0 | 5 | 11/28/2022 | 11/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2022 | 11/18/2022 | 5/16/2024 | Y | EXP | 365 | 09/12/2023 | 10/04/2023 | 23 | 0 | 23 |  |  | 10/10/2023 | Connected |  | N
National Grid | WORCESTER | 612371 | 01605 | 6 |  |  | Solar |  | 05_01_24W1 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/20/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | WEBSTER | 562803 | 01570 | 23 |  |  | Solar |  | 05_01_412L1 | 10/13/2023 | 10/30/2023 | 12 | 11 | 1 | 10/31/2023 | 10/31/2023 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 569867 | 01543 | 10 |  |  | Solar |  | 05_01_55W1 | 12/05/2023 | 12/07/2023 | 3 | 2 | 1 | 12/08/2023 | 12/08/2023 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | BLACKSTONE | 178519 | 01504 | 7.6 |  |  | Solar |  | 05_05_108W60 | 04/04/2018 | 04/04/2018 | 14 | 0 | 14 | 05/17/2018 | 05/17/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/04/2018 | 11/30/2019 | Y | EXP | 541 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N
National Grid | MARLBOROUGH | 664880 | 01752 | 7.6 |  |  | Solar |  | 05_05_311W5 | 01/09/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 3/19/2026 | Y | EXP | 365 | 03/25/2025 | 09/10/2025 | 170 | 0 | 170 |  |  | 10/14/2025 | Connected |  | N
National Grid | BEVERLY | 578751 | 01915 | 0 |  |  | Solar |  | 05_12_51L1 | 12/19/2023 | 12/22/2023 | 2 | 2 | 0 | 12/26/2023 | 12/26/2023 | 38 | 16 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | AMESBURY | 727151 | 01913 | 28 |  |  | Solar |  | 05_14_2J2 | 10/17/2025 | 10/21/2025 | 2 | 0 | 2 | 10/22/2025 | 10/22/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 683366 | 01886 | 4998 |  |  | Other |  | 05_14_57L2 | 10/16/2025 | 12/04/2025 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 174574 | 01821 | 999 |  |  | Solar |  | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | STD | -42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 476315 | 01841 | 0 |  |  | Solar |  | 05_14_8L2 | 06/08/2023 | 08/15/2023 | 46 | 45 | 1 | 08/16/2023 | 08/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  | 9/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 619203 | 01605 | 11.4 |  |  | Solar |  | 05_01_24W1 | 10/28/2024 | 11/14/2024 | 9 | 6 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 | 01/06/2025 | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/25/2026 | N | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | WEBSTER | 576129 | 01570 | 11.4 |  |  | Solar |  | 05_01_412L1 | 01/22/2024 | 02/21/2024 | 21 | 19 | 2 | 02/22/2024 | 02/22/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 01/22/2024 | 6/1/2025 | Y | EXP | 365 | 05/11/2024 | 08/16/2024 | 98 | 0 | 98 |  |  | 10/24/2024 | Connected |  | N
National Grid | RUTLAND | 578149 | 01543 | 2.32 |  |  | Solar |  | 05_01_55W1 | 01/08/2024 | 01/10/2024 | 1 | 1 | 0 | 01/11/2024 | 01/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | BLACKSTONE | 178665 | 01504 | 4200 |  |  | Solar |  | 05_05_108W60 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/17/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2018 | 03/16/2018 | 8/5/2022 | Y | STD | 505 | 02/09/2022 | 07/06/2022 | 146 | 0 | 146 |  |  | 7/19/2022 | Connected |  | N
National Grid | MARLBOROUGH | 475389 | 01752 | 0 |  |  | Other |  | 05_05_311W6 | 12/08/2022 | 02/01/2023 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BEVERLY | 622202 | 01915 | 6 |  |  | Solar |  | 05_12_51L1 | 07/04/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/04/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | SALISBURY | 225517 | 01952 | 23.4 |  |  | Solar |  | 05_14_2J2 | 05/23/2019 | 06/21/2019 | 19 | 12 | 7 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | WESTFORD | 718919 | 01886 | 0 |  |  | Solar |  | 05_14_57L2 | 09/14/2025 | 09/18/2025 | 4 | 0 | 4 | 09/19/2025 | 09/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 175159 | 01821 | 2000 |  |  | Solar |  | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2012 | 08/11/2014 | 444 | 0 | 444 | 12/12/2012 | 08/05/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 533125 | 01841 | 10 |  |  | Solar |  | 05_14_8L2 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/16/2023 | 8/4/2024 | Y | EXP | 365 | 12/06/2023 | 12/26/2023 | 21 | 3 | 18 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 622805 | 01605 | 5.76 |  |  | Solar |  | 05_01_24W1 | 07/19/2024 | 09/03/2024 | 22 | 21 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | WEBSTER | 604870 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 04/18/2024 | 04/30/2024 | 4 | 0 | 4 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/18/2024 | 5/16/2025 | Y | EXP | 365 | 08/15/2024 | 08/14/2024 | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | RUTLAND | 584251 | 01543 | 3.8 |  |  | Solar |  | 05_01_55W1 | 02/01/2024 | 02/05/2024 | 2 | 0 | 2 | 02/06/2024 | 02/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 185770 | 01504 | 11.4 |  |  | Solar |  | 05_05_108W60 | 05/18/2018 | 05/18/2018 | 5 | 0 | 5 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 | 05/18/2018 |  | Y | EXP | 466 | 07/11/2019 | 07/10/2019 | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | MARLBOROUGH | 724550 | 01752 | 20.14 |  |  | Solar |  | 05_05_311W6 | 10/07/2025 | 10/20/2025 | 7 | 3 | 4 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 629790 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 08/02/2024 | 08/30/2024 | 16 | 14 | 2 | 09/03/2024 | 09/03/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 196571 | 01913 | 43.2 |  |  | Solar |  | 05_14_2J3 | 10/04/2018 | 11/01/2018 | 18 | 1 | 17 | 11/02/2018 | 11/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2020 | Connected |  | N
National Grid | WESTFORD | 740323 | 01886 | 23 |  |  | Solar |  | 05_14_57L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 175562 | 01821 | 12 |  |  | Solar |  | 05_14_70L8 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 |  | 10/31/2014 | N | EXP | 59 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 5/19/2015 | Connected |  | N
National Grid | LAWRENCE | 537941 | 01841 | 8.7 |  |  | Solar |  | 05_14_8L2 | 12/04/2023 |  | 42 | 30 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 634322 | 01605 | 19 |  |  | Solar |  | 05_01_24W1 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 9/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | DOUGLAS | 608295 | 01516 | 23 |  |  | Solar |  | 05_01_412L1 | 05/02/2024 | 05/16/2024 | 10 | 8 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | RUTLAND | 591901 | 01543 | 6 |  |  | Solar |  | 05_01_55W1 | 02/27/2024 | 02/29/2024 | 3 | 1 | 2 | 03/01/2024 | 03/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/27/2024 | 3/20/2025 | Y | EXP | 365 | 05/09/2024 | 06/14/2024 | 37 | 0 | 37 |  |  | 6/25/2024 | Connected |  | N
National Grid | BELLINGHAM | 191437 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W60 | 07/22/2018 | 10/01/2018 | 20 | 11 | 9 | 10/02/2018 | 10/02/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2020 | Connected |  | N
National Grid | MARLBOROUGH | 175178 | 01752 | 1073.6 |  |  | Solar |  | 05_05_311W6 | 05/03/2013 | 05/03/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2013 | 07/02/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/3/2014 |  | 12/31/2016 | N | STD | 1034 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/21/2015 | Connected |  | N
National Grid | BEVERLY | 651826 | 01915 | 7.6 |  |  | Solar |  | 05_12_51L1 | 11/04/2024 | 11/13/2024 | 5 | 1 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/04/2024 | 1/5/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/22/2025 | Connected |  | N
National Grid | LAWRENCE | 550449 | 01840 | 50 |  |  | Solar |  | 05_14_2J3 | 08/25/2023 | 09/21/2023 | 18 | 10 | 8 | 09/22/2023 | 09/22/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 08/25/2023 | 12/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 178144 | 01886 | 0 |  |  | Solar |  | 05_14_57L2 | 04/12/2018 | 04/12/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 10/22/2020 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | BILLERICA | 176311 | 01821 | 5 |  |  | Solar |  | 05_14_70L8 | 02/25/2015 | 02/25/2015 | 8 | 5 | 3 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/2/2015 | Connected |  | N
National Grid | LAWRENCE | 555249 | 01841 | 5.76 |  |  | Solar |  | 05_14_8L2 | 09/27/2023 | 11/15/2023 | 34 | 30 | 4 | 11/16/2023 | 11/16/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 634620 | 01605 | 10 |  |  | Solar |  | 05_01_24W1 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 33 | 24 | 9 | 01/24/2025 | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 4/8/2026 | N | EXP | 365 | 08/14/2025 | 08/25/2025 | 12 | 0 | 12 |  |  | 9/3/2025 | Connected |  | N
National Grid | WEBSTER | 611622 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 05/16/2024 |  | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 597641 | 01543 | 0 |  |  | Solar |  | 05_01_55W1 | 08/27/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | BLACKSTONE | 215936 | 01504 | 10 |  |  | Solar |  | 05_05_108W60 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 176833 | 01752 | 10 |  |  | Solar |  | 05_05_311W6 | 02/28/2016 | 02/28/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2016 |  | 3/5/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/19/2016 | 7/19/2016 | 7/19/2016 | Connected |  | N
National Grid | BEVERLY | 656350 | 01915 | 0 |  |  | Battery Add-On |  | 05_12_51L1 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 188 | 170 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174787 | 01840 | 100 |  |  | Solar |  | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 | 11/11/2012 | 8/11/2013 | Y | EXP | 30 | 03/07/2014 | 12/08/2014 | 187 | 0 | 187 | 4/23/2014 | 4/23/2014 | 4/24/2014 | Connected |  | N
National Grid | WESTFORD | 178697 | 01886 | 7.6 |  |  | Solar |  | 05_14_57L2 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/12/2019 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | Connected |  | N
National Grid | BILLERICA | 176509 | 01821 | 5.5 |  |  | Solar |  | 05_14_70L8 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 196 | 0 | 196 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2016 |  | 4/3/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 555821 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 09/19/2023 | 09/22/2023 | 4 | 3 | 1 | 09/25/2023 | 09/25/2023 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2023 | Connected |  | N
National Grid | WORCESTER | 639891 | 01605 | 5.76 |  |  | Solar |  | 05_01_24W1 | 09/12/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2024 | 09/12/2024 | 12/10/2025 | Y | EXP | 370 | 01/21/2025 | 10/30/2025 | 283 | 0 | 283 |  |  | 12/5/2025 | Connected |  | N
National Grid | WEBSTER | 619932 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 06/24/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 88 | 74 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 608010 | 01543 | 11.7 |  |  | Solar |  | 05_01_55W1 | 05/02/2024 | 05/13/2024 | 3 | 1 | 2 | 05/14/2024 | 05/14/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 215927 | 02019 | 3960 |  |  | Solar |  | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/04/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 202096 | 01752 | 450 |  |  | Solar |  | 05_05_311W6 | 11/30/2018 | 12/21/2018 | 15 | 11 | 4 | 12/24/2018 | 12/24/2018 | 92 | 26 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 656752 | 01915 | 7.6 |  |  | Solar |  | 05_12_51L1 | 11/25/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/24/2026 | Y | EXP | 365 | 06/11/2025 | 11/25/2025 | 168 | 0 | 168 |  |  | 12/1/2025 | Connected |  | N
National Grid | LAWRENCE | 175135 | 01840 | 150 |  |  | Solar |  | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 273553 | 01886 | 7.6 |  |  | Solar |  | 05_14_57L2 | 01/23/2020 | 02/05/2020 | 8 | 3 | 5 | 02/06/2020 | 02/06/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/23/2020 | 7/15/2021 | Y | EXP | 365 | 04/06/2021 | 04/15/2021 | 9 | 0 | 9 |  |  | 4/30/2021 | Connected |  | N
National Grid | BILLERICA | 178536 | 01821 | 15.2 |  |  | Solar |  | 05_14_70L8 | 12/07/2017 | 12/07/2017 | 15 | 0 | 15 | 01/02/2018 | 01/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 3/22/2019 | N | EXP | 443 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N
National Grid | LAWRENCE | 573304 | 01841 | 10.036 |  |  | Solar |  | 05_14_8L2 | 11/24/2023 | 11/29/2023 | 3 | 0 | 3 | 11/30/2023 | 11/30/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 640832 | 01606 | 7.6 |  |  | Solar |  | 05_01_24W1 | 09/17/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | DOUGLAS | 632100 | 01516 | 10 |  |  | Solar |  | 05_01_412L1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/11/2025 | Y | EXP | 365 | 10/11/2024 | 10/14/2024 | 4 | 0 | 4 |  |  | 12/4/2024 | Connected |  | N
National Grid | RUTLAND | 616463 | 01543 | 5.76 |  |  | Solar |  | 05_01_55W1 | 06/07/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 215920 | 02019 | 4950 |  |  | Solar |  | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/01/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 229547 | 01752 | 240 |  |  | Solar |  | 05_05_311W6 | 05/20/2019 | 06/05/2019 | 9 | 4 | 5 | 06/06/2019 | 06/06/2019 | 40 | 27 | 13 | 09/03/2019 | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 |  | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 677578 | 01915 | 3.8 |  |  | Solar |  | 05_12_51L1 | 03/12/2025 | 04/14/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/12/2025 | 6/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N
National Grid | LAWRENCE | 186700 | 01840 | 15.2 |  |  | Solar |  | 05_14_2J4 | 06/22/2018 | 06/22/2018 | 0 | 0 | 0 | 06/25/2018 | 06/25/2018 | 11 | 10 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | WESTFORD | 277368 | 01886 | 9.84 |  |  | Solar |  | 05_14_57L2 | 02/03/2020 | 02/05/2020 | 1 | 0 | 1 | 02/06/2020 | 02/06/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 | 02/03/2020 | 2/3/2021 | Y | EXP | 365 | 07/11/2020 | 07/27/2020 | 16 | 0 | 16 |  |  | 8/18/2020 | Connected |  | N
National Grid | BILLERICA | 192658 | 01821 | 10 |  |  | Solar |  | 05_14_70L8 | 08/28/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 41 | 27 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 579143 | 01841 | 10 |  |  | Solar |  | 05_14_8L2 | 01/10/2024 | 01/30/2024 | 14 | 12 | 2 | 01/31/2024 | 01/31/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 6/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N
National Grid | WORCESTER | 641542 | 01605 | 3.8 |  |  | Solar |  | 05_01_24W1 | 09/19/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | WEBSTER | 631896 | 01570 | 9.86 |  |  | Solar |  | 05_01_412L1 | 08/12/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 08/12/2024 | 11/26/2025 | Y | EXP | 365 | 02/11/2025 | 03/17/2025 | 35 | 0 | 35 |  |  | 3/21/2025 | Connected |  | N
National Grid | RUTLAND | 634556 | 01543 | 8.775 |  |  | Solar |  | 05_01_55W1 | 08/22/2024 | 09/03/2024 | 4 | 1 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BELLINGHAM | 263498 | 02019 | 7.6 |  |  | Solar |  | 05_05_108W60 | 11/19/2019 | 11/20/2019 | 0 | 0 | 0 | 11/21/2019 | 11/21/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/19/2019 | 11/19/2020 | Y | EXP | 365 | 06/04/2020 | 07/07/2020 | 33 | 0 | 33 |  |  | 7/22/2020 | Connected |  | N
National Grid | MARLBOROUGH | 296692 | 01752 | 10 |  |  | Solar |  | 05_05_311W6 | 06/16/2020 | 06/18/2020 | 1 | 0 | 1 | 06/19/2020 | 06/19/2020 | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | BEVERLY | 715101 | 01915 | 10 |  |  | Solar |  | 05_12_51L1 | 08/27/2025 | 09/17/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/27/2025 | 11/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 586766 | 01840 | 15.76 |  |  | Solar |  | 05_14_2J4 | 05/08/2024 | 06/21/2024 | 30 | 29 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 9/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | WESTFORD | 301130 | 01886 | 10 |  |  | Solar |  | 05_14_57L2 | 08/17/2020 | 08/26/2020 | 7 | 7 | 0 | 08/27/2020 | 08/27/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 08/17/2020 | 8/26/2021 | Y | EXP | 365 | 04/21/2021 | 04/30/2021 | 9 | 0 | 9 |  |  | 5/4/2021 | Connected |  | N
National Grid | TEWKSBURY | 259369 | 01876 | 3.8 |  |  | Solar |  | 05_14_70L8 | 10/22/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2020 | Connected |  | N
National Grid | LAWRENCE | 582651 | 01841 | 5.22 |  |  | Solar |  | 05_14_8L2 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/01/2024 | 3/27/2025 | Y | EXP | 365 | 04/16/2024 | 08/28/2024 | 135 | 0 | 135 |  |  | 9/19/2024 | Connected |  | N
National Grid | WORCESTER | 642848 | 01606 | 7.6 |  |  | Solar |  | 05_01_24W1 | 09/25/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 56 | 36 | 20 | 03/19/2025 | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 4/25/2025 | 09/25/2024 | 5/23/2026 | Y | EXP | 365 | 06/28/2025 | 11/13/2025 | 139 | 0 | 139 |  |  | 12/17/2025 | Connected |  | N
National Grid | WEBSTER | 646578 | 01570 | 3.8 |  |  | Solar |  | 05_01_412L1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 01/23/2025 | 03/21/2025 | 58 | 0 | 58 |  |  | 4/1/2025 | Connected |  | N
National Grid | RUTLAND | 637398 | 01543 | 5.8 |  |  | Solar |  | 05_01_55W1 | 09/03/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | BLACKSTONE | 294047 | 01504 | 15.2 |  |  | Solar |  | 05_05_108W60 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N
National Grid | MARLBOROUGH | 311656 | 01752 | 10 |  |  | Solar |  | 05_05_311W6 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 02/26/2021 | 03/12/2021 | 14 | 0 | 14 |  |  | 4/7/2021 | Connected |  | N
National Grid | BEVERLY | 667830 | 01915 | 5.7 |  |  | Solar |  | 05_12_51L2 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 652372 | 01840 | 116 |  |  | Solar |  | 05_14_2J6 | 05/08/2025 | 09/18/2025 | 91 | 82 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WESTFORD | 307057 | 01886 | 15.2 |  |  | Solar |  | 05_14_57L2 | 08/17/2020 | 08/20/2020 | 2 | 0 | 2 | 08/21/2020 | 08/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | TEWKSBURY | 300909 | 01876 | 0 |  |  | Solar |  | 05_14_70L8 | 07/14/2020 | 08/06/2020 | 17 | 17 | 0 | 08/07/2020 | 08/07/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 8/2/2023 | N | EXP | 750 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 591651 | 01844 | 0 |  |  | Solar |  | 05_14_8L2 | 06/25/2024 | 07/02/2024 | 6 | 1 | 5 | 07/02/2024 | 07/02/2024 | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | WORCESTER | 650683 | 01606 | 3.8 |  |  | Solar |  | 05_01_24W1 | 11/11/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/11/2024 | 2/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2025 | Connected |  | N
National Grid | WEBSTER | 646439 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 10/25/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/25/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 644740 | 01543 | 9.9 |  |  | Solar |  | 05_01_55W1 | 10/03/2024 | 11/14/2024 | 12 | 9 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/03/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | BLACKSTONE | 304759 | 01504 | 9.8 |  |  | Solar |  | 05_05_108W60 | 10/02/2020 | 10/15/2020 | 8 | 8 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 10/02/2020 | 10/15/2021 | Y | EXP | 365 | 03/31/2021 | 05/21/2021 | 51 | 0 | 51 |  |  | 5/27/2021 | Connected |  | N
National Grid | MARLBOROUGH | 473323 | 01752 | 120 |  |  | Solar |  | 05_05_311W6 | 11/14/2022 | 12/13/2022 | 20 | 11 | 9 | 12/14/2022 | 12/14/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 11/14/2022 | 7/24/2025 | Y | EXP | 245 | 12/04/2024 | 12/10/2024 | 7 | 0 | 7 |  |  | 2/27/2025 | Connected |  | N
National Grid | BEVERLY | 176064 | 01915 | 135 |  |  | Solar |  | 05_12_51L2 | 04/02/2015 | 04/02/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 418695 | 01840 | 57.6 |  |  | Solar |  | 05_14_2J8 | 03/18/2022 | 04/29/2022 | 29 | 19 | 10 | 05/02/2022 | 05/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 4/16/2026 | N | EXP | 184 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTFORD | 312114 | 01886 | 13.6 |  |  | Solar |  | 05_14_57L2 | 09/17/2020 | 09/24/2020 | 4 | 0 | 4 | 09/25/2020 | 09/25/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | Y
National Grid | TEWKSBURY | 362871 | 01876 | 7.83 |  |  | Solar |  | 05_14_70L8 | 07/09/2021 | 07/13/2021 | 2 | 0 | 2 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 592133 | 01841 | 10 |  |  | Solar |  | 05_14_8L2 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 685939 | 01606 | 15.2 |  |  | Solar |  | 05_01_24W1 | 04/17/2025 | 04/22/2025 | 2 | 0 | 2 | 04/23/2025 | 04/23/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 647877 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 10/28/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/28/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | RUTLAND | 655165 | 01543 | 5.76 |  |  | Solar |  | 05_01_55W1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 44 | 19 | 25 | 03/28/2025 | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/8/2026 | N | EXP | 365 | 11/11/2025 | 12/22/2025 | 42 | 0 | 42 |  |  | 12/4/2025 | Connected |  | N
National Grid | BLACKSTONE | 316764 | 01504 | 10 |  |  | Solar |  | 05_05_108W60 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 |  | Y | EXP |  | 02/09/2021 | 05/18/2021 | 98 | 0 | 98 |  |  | 6/2/2021 | Connected |  | N
National Grid | MARLBOROUGH | 588582 | 01752 | 5 |  |  | Solar |  | 05_05_311W6 | 03/11/2024 | 03/12/2024 | 1 | 0 | 1 | 03/13/2024 | 03/13/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 176091 | 01915 | 266 |  |  | Solar |  | 05_12_51L2 | 04/01/2015 | 04/01/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 681059 | 01840 | 10 |  |  | Solar |  | 05_14_2J8 | 04/04/2025 | 04/22/2025 | 3 | 0 | 3 | 05/02/2025 | 05/02/2025 | 45 | 32 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 | 04/04/2025 | 7/15/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  |  | Completion Documents |  | Y
National Grid | WESTFORD | 321224 | 01886 | 10 |  |  | Solar |  | 05_14_57L2 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 382224 | 01821 | 15.2 |  |  | Solar |  | 05_14_70L8 | 09/15/2021 | 10/14/2021 | 21 | 19 | 2 | 10/15/2021 | 10/15/2021 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 | 09/15/2021 | 5/2/2023 | Y | EXP | 365 | 04/06/2022 | 05/02/2022 | 27 | 0 | 27 |  |  | 5/20/2022 | Connected |  | N
National Grid | LAWRENCE | 595888 | 01841 | 7.6 |  |  | Solar |  | 05_14_8L2 | 03/29/2024 | 04/03/2024 | 3 | 0 | 3 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2024 |  | 5/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | WORCESTER | 660684 | 01605 | 0 |  |  | Other |  | 05_01_24W2 | 04/08/2025 | 06/17/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2025 | 07/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WEBSTER | 652003 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 11/13/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/13/2024 | 2/28/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/1/2025 | Connected |  | N
National Grid | RUTLAND | 660326 | 01543 | 7.6 |  |  | Solar |  | 05_01_55W1 | 12/12/2024 | 01/07/2025 | 8 | 6 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | BLACKSTONE | 321256 | 01504 | 7.6 |  |  | Solar |  | 05_05_108W60 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/23/2020 | 10/27/2021 | Y | EXP | 365 | 02/05/2021 | 02/12/2021 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 618845 | 01752 | 11.4 |  |  | Solar |  | 05_05_311W6 | 06/18/2024 | 07/09/2024 | 4 | 2 | 2 | 07/10/2024 | 07/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2024 | Connected |  | N
National Grid | BEVERLY | 177119 | 01915 | 390 |  |  | Solar |  | 05_12_51L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 36 | 283 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 194466 | 01840 | 480 |  |  | Solar |  | 05_14_2J8 | 08/27/2018 | 08/28/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 326885 | 01886 | 10 |  |  | Solar |  | 05_14_57L2 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | TEWKSBURY | 526597 | 01876 | 15.2 |  |  | Solar |  | 05_14_70L8 | 05/19/2023 | 05/26/2023 | 5 | 5 | 0 | 05/30/2023 | 05/30/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | LAWRENCE | 595649 | 01841 | 10 |  |  | Solar |  | 05_14_8L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 9/15/2025 | Y | EXP | 485 | 07/25/2024 | 08/08/2025 | 380 | 0 | 380 |  |  | 9/17/2025 | Connected |  | N
National Grid | WORCESTER | 718545 | 01606 | 4.93 |  |  | Solar |  | 05_01_24W2 | 09/11/2025 | 10/24/2025 | 5 | 1 | 4 | 10/27/2025 | 10/27/2025 | 46 | 29 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEBSTER | 655660 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 11/20/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/20/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | RUTLAND | 669686 | 01543 | 7.6 |  |  | Solar |  | 05_01_55W1 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 140 | 123 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 325072 | 01504 | 0 |  |  | Solar |  | 05_05_108W60 | 11/13/2020 | 12/15/2020 | 20 | 17 | 3 | 12/16/2020 | 12/16/2020 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 643293 | 01752 | 10 |  |  | Solar |  | 05_05_311W6 | 09/27/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/30/2025 | Y | EXP | 365 | 04/03/2025 | 04/09/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | BEVERLY | 337612 | 01915 | 8.4 |  |  | Solar |  | 05_12_51L2 | 02/01/2021 | 02/04/2021 | 2 | 0 | 2 | 02/05/2021 | 02/05/2021 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 | 02/01/2021 | 9/14/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 16 | 0 | 16 |  |  | 12/17/2021 | Connected |  | N
National Grid | LAWRENCE | 552093 | 01840 | 200 |  |  | Solar |  | 05_14_2J8 | 08/31/2023 | 09/28/2023 | 20 | 10 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 332968 | 01886 | 0 |  |  | Solar |  | 05_14_57L2 | 12/18/2020 | 01/04/2021 | 9 | 8 | 1 | 01/05/2021 | 01/05/2021 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/18/2020 | 1/3/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2021 | Connected |  | N
National Grid | TEWKSBURY | 529445 | 01876 | 6 |  |  | Solar |  | 05_14_70L8 | 09/06/2023 | 06/06/2023 | 3 | 2 | 1 | 09/12/2023 | 09/12/2023 | 116 | 99 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | LAWRENCE | 595986 | 01841 | 6 |  |  | Solar |  | 05_14_8L2 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 | 03/25/2024 | 5/9/2025 | Y | EXP | 365 | 07/31/2024 | 09/17/2024 | 49 | 0 | 49 |  |  | 10/30/2024 | Connected |  | N
National Grid | WORCESTER | 174591 | 01606 | 39 |  |  | Solar |  | 05_01_24W2 | 04/27/2011 | 04/27/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 8/4/2012 | N | EXP | 250 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 8/2/2012 | Connected |  | N
National Grid | WEBSTER | 663882 | 01570 | 5.76 |  |  | Solar |  | 05_01_412L1 | 01/06/2025 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | RUTLAND | 671268 | 01543 | 5.76 |  |  | Solar |  | 05_01_55W1 | 02/11/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | BLACKSTONE | 344703 | 01504 | 6.72 |  |  | Solar |  | 05_05_108W60 | 03/24/2021 | 04/02/2021 | 6 | 6 | 0 | 04/05/2021 | 04/05/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 4/1/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 662998 | 01752 | 3.8 |  |  | Solar |  | 05_05_311W6 | 12/30/2024 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 12/30/2024 | 3/11/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 11/26/2025 | Connected |  | N
National Grid | BEVERLY | 419862 | 01915 | 0 |  |  | Other |  | 05_12_51L2 | 06/14/2022 | 06/28/2022 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2022 | 07/27/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 686313 | 01840 | 15.04 |  |  | Solar |  | 05_14_2L1 | 05/11/2025 | 07/10/2025 | 39 | 38 | 1 | 07/11/2025 | 07/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 05/11/2025 | 9/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTFORD | 335891 | 01886 | 100 |  |  | Solar |  | 05_14_57L2 | 01/11/2021 | 01/25/2021 | 8 | 0 | 8 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 3/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 569114 | 01876 | 0 |  |  | Solar |  | 05_14_70L8 | 11/06/2023 | 11/30/2023 | 17 | 15 | 2 | 12/01/2023 | 12/01/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2024 | Connected |  | N
National Grid | LAWRENCE | 599574 | 01841 | 5.85 |  |  | Solar |  | 05_14_8L2 | 04/01/2024 | 04/03/2024 | 3 | 1 | 2 | 04/04/2024 | 04/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 | 04/01/2024 | 5/1/2025 | Y | EXP | 365 | 06/05/2024 | 09/18/2024 | 106 | 0 | 106 |  |  | 10/24/2024 | Connected |  | N
National Grid | WORCESTER | 174763 | 01606 | 60 |  |  | Solar |  | 05_01_24W2 | 08/23/2012 | 08/23/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 12/7/2012 | N | EXP | -5 |  |  | 0 | 0 | 0 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N
National Grid | WEBSTER | 674907 | 01570 | 10 |  |  | Solar |  | 05_01_412L1 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | RUTLAND | 679462 | 01543 | 11.52 |  |  | Solar |  | 05_01_55W1 | 03/25/2025 | 09/15/2025 | 29 | 25 | 4 | 09/16/2025 | 09/16/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | BELLINGHAM | 373157 | 02019 | 3.8 |  |  | Solar |  | 05_05_108W60 | 08/06/2021 | 08/10/2021 | 2 | 0 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 4/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2023 | Connected |  | N
National Grid | MARLBOROUGH | 670581 | 01752 | 3.8 |  |  | Solar |  | 05_05_311W6 | 02/06/2025 | 02/18/2025 | 2 | 0 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | BEVERLY | 546247 | 01915 | 9.86 |  |  | Solar |  | 05_12_51L2 | 08/06/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | LAWRENCE | 175307 | 01840 | 910 |  |  | Solar |  | 05_14_2L1 | 06/30/2014 | 06/30/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2016 | 06/30/2014 | 8/3/2021 | Y | STD | 316 | 05/21/2019 | 07/21/2021 | 406 | 4 | 402 |  |  | 8/3/2021 | Connected |  | N
National Grid | WESTFORD | 341508 | 01886 | 9.6 |  |  | Solar |  | 05_14_57L2 | 02/10/2021 | 02/16/2021 | 2 | 0 | 2 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N
National Grid | BILLERICA | 570311 | 01821 | 7.6 |  |  | Solar |  | 05_14_70L8 | 11/15/2023 | 12/07/2023 | 15 | 13 | 2 | 12/08/2023 | 12/08/2023 | 30 | 8 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 11/15/2023 | 2/20/2025 | Y | EXP | 365 | 03/19/2024 | 03/18/2024 | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | LAWRENCE | 602404 | 01841 | 3.8 |  |  | Solar |  | 05_14_8L2 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175456 | 01605 | 87 |  |  | Solar |  | 05_01_24W2 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 11/28/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 3/25/2016 | Connected |  | N
National Grid | WEBSTER | 674780 | 01570 | 7.6 |  |  | Solar |  | 05_01_412L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 376465 | 01543 | 15.2 |  |  | Solar |  | 05_05_108W60 | 08/17/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 176 | 153 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 671735 | 01504 | 3.8 |  |  | Solar |  | 05_05_311W6 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 02/12/2025 | 4/15/2026 | Y | EXP | 365 | 04/30/2025 |  | 247 | 0 | 247 |  |  | 11/25/2025 | Connected |  | N
National Grid | MARLBOROUGH | 652576 | 01752 | 5.76 |  |  | Solar |  | 05_12_51L2 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | BEVERLY | 176776 | 01915 | 390 |  |  | Solar |  | 05_14_2L1 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 02/15/2016 | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 | 11/04/2015 | 6/14/2019 | Y | EXP | 1206 | 07/11/2017 | 08/23/2017 | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | LAWRENCE | 449761 | 01840 | 7.6 |  |  | Solar |  | 05_14_57L2 | 08/09/2022 | 08/10/2022 | 1 | 0 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  | 9/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | WESTFORD | 597903 | 01886 | 16.4 |  |  | Solar |  | 05_14_70L8 | 03/19/2024 | 03/21/2024 | 2 | 0 | 2 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N
National Grid | BILLERICA | 603795 | 01821 | 7.6 |  |  | Solar |  | 05_14_8L2 | 04/13/2024 | 05/09/2024 | 3 | 2 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176042 | 01841 | 476 |  |  | Solar |  | 05_01_24W2 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 8/22/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/9/2016 | Connected |  | Y
National Grid | WORCESTER | 674712 | 01606 | 3.8 |  |  | Solar |  | 05_01_412L1 | 03/05/2025 | 03/14/2025 | 4 | 0 | 4 | 03/24/2025 | 03/24/2025 | 102 | 85 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WEBSTER | 683396 | 01570 | 20 |  |  | Solar |  | 05_01_55W1 | 04/07/2025 | 04/11/2025 | 4 | 0 | 4 | 04/14/2025 | 04/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | RUTLAND | 379282 | 01543 | 9.6 |  |  | Solar |  | 05_05_108W60 | 11/03/2021 | 12/16/2021 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/03/2021 | 7/28/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | Y
National Grid | BLACKSTONE | 672840 | 01504 | 3.8 |  |  | Solar |  | 05_05_311W6 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | MARLBOROUGH | 657811 | 01752 | 5.76 |  |  | Solar |  | 05_12_51L2 | 12/02/2024 | 12/20/2024 | 10 | 7 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | BEVERLY | 177005 | 01915 | 720 |  |  | Solar |  | 05_14_2L1 | 10/10/2016 | 10/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/15/2016 | 45 | 33 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 10/10/2016 | 10/30/2020 | Y | STD | 707 | 08/06/2019 | 10/16/2020 | 438 | 5 | 433 |  |  | 10/21/2020 | Connected |  | N
National Grid | CHELMSFORD | 373288 | 01863 | 15.2 |  |  | Solar |  | 05_14_57L2 | 09/08/2021 | 09/22/2021 | 11 | 10 | 1 | 09/23/2021 | 09/23/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 2/1/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 602386 | 01886 | 5.76 |  |  | Solar |  | 05_14_70L8 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 609010 | 01821 | 5.76 |  |  | Solar |  | 05_14_8L2 | 05/06/2024 | 05/28/2024 | 13 | 10 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 07/17/2024 | 10/25/2024 | 101 | 0 | 101 |  |  | 12/21/2024 | Connected |  | N
National Grid | LAWRENCE | 176086 | 01841 | 5 |  |  | Solar |  | 05_01_24W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 12/31/2016 | Y | EXP | 675 | 03/11/2016 | 03/31/2016 | 13 | 0 | 13 | 8/8/2016 | 8/8/2016 | 8/8/2016 | Connected |  | N
National Grid | WORCESTER | 677792 | 01606 | 10 |  |  | Solar |  | 05_01_412L1 | 03/13/2025 | 04/10/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/13/2025 | 6/10/2026 | Y | EXP | 365 | 09/05/2025 | 10/25/2025 | 51 | 0 | 51 |  |  | 12/2/2025 | Connected |  | N
National Grid | WEBSTER | 684897 | 01570 | 5.76 |  |  | Solar |  | 05_01_55W1 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 52 | 44 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 412984 | 01543 | 3.8 |  |  | Solar |  | 05_05_108W60 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | Connected |  | N
National Grid | BELLINGHAM | 678199 | 02019 | 13.36 |  |  | Solar |  | 05_05_311W6 | 03/14/2025 | 04/10/2025 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 665914 | 01752 | 18.85 |  |  | Solar |  | 05_12_51L2 | 01/15/2025 | 01/29/2025 | 7 | 2 | 5 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | BEVERLY | 178330 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L1 | 03/30/2018 | 03/30/2018 | 5 | 0 | 5 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 9/23/2020 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | CHELMSFORD | 382038 | 01863 | 19.14 |  |  | Solar |  | 05_14_57L2 | 09/14/2021 | 12/16/2021 | 3 | 0 | 3 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 625684 | 01886 | 10 |  |  | Solar |  | 05_14_70L8 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2024 | Connected |  | N
National Grid | TEWKSBURY | 609653 | 01876 | 7.6 |  |  | Solar |  | 05_14_8L2 | 05/08/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 05/08/2024 | 6/28/2025 | Y | EXP | 365 | 08/29/2024 | 01/07/2025 | 132 | 0 | 132 |  |  | 1/29/2025 | Connected |  | N
National Grid | LAWRENCE | 176204 | 01841 | 13.6 |  |  | Solar |  | 05_01_24W2 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 598 | 10/14/2016 | 10/26/2016 | 8 | 0 | 8 | 5/13/2015 | 5/13/2015 | 11/15/2016 | Connected |  | N
National Grid | WORCESTER | 680197 | 01605 | 11.5 |  |  | Solar |  | 05_01_412L1 | 04/08/2025 | 04/23/2025 | 1 | 0 | 1 | 05/13/2025 | 05/13/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/08/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N
National Grid | WEBSTER | 685863 | 01570 | 0 |  |  | Solar |  | 05_01_55W1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 420677 | 01543 | 6 |  |  | Solar |  | 05_05_108W60 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 | 04/04/2022 | 1/27/2024 | Y | EXP | 365 | 06/11/2022 | 01/26/2023 | 230 | 0 | 230 |  |  | 2/14/2023 | Connected |  | Y
National Grid | BLACKSTONE | 571788 | 01504 | 0 |  |  | Other |  | 05_05_312W1 | 01/11/2024 | 04/22/2025 | 317 | 307 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2025 | 05/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MARLBOROUGH | 669158 | 01752 | 8.125 |  |  | Solar |  | 05_12_51L2 | 01/31/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/31/2025 | 4/13/2026 | Y | EXP | 365 | 05/16/2025 | 09/03/2025 | 111 | 0 | 111 |  |  | 9/15/2025 | Connected |  | N
National Grid | BEVERLY | 178690 | 01915 | 240 |  |  | Solar |  | 05_14_2L1 | 12/20/2017 | 12/20/2017 | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 424028 | 01824 | 15.2 |  |  | Solar |  | 05_14_57L2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/14/2022 | 12/7/2024 | Y | EXP | 365 | 06/09/2023 | 12/05/2023 | 180 | 0 | 180 |  |  | 2/27/2025 | Connected |  | N
National Grid | WESTFORD | 651555 | 01886 | 7.6 |  |  | Solar |  | 05_14_70L8 | 11/01/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/01/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | BILLERICA | 611143 | 01821 | 6 |  |  | Solar |  | 05_14_8L2 | 05/15/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176552 | 01841 | 7.6 |  |  | Solar |  | 05_01_24W2 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/05/2015 | 10/13/2016 | Y | EXP | 346 | 08/03/2016 | 08/31/2016 | 20 | 0 | 20 | 9/21/2016 | 9/21/2016 | 9/21/2016 | Connected |  | N
National Grid | WORCESTER | 680170 | 01606 | 10 |  |  | Solar |  | 05_01_412L1 | 03/24/2025 | 04/22/2025 | 21 | 16 | 5 | 04/23/2025 | 04/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 694884 | 01570 | 11.4 |  |  | Solar |  | 05_01_55W1 | 06/02/2025 | 06/13/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 06/02/2025 | 9/4/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 11/24/2025 | Connected |  | N
National Grid | RUTLAND | 425396 | 01543 | 10 |  |  | Solar |  | 05_05_108W60 | 06/16/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/16/2022 | 2/2/2024 | Y | EXP | 365 | 10/12/2022 | 01/14/2023 | 95 | 0 | 95 |  |  | 5/23/2023 | Connected |  | Y
National Grid | BELLINGHAM | 660928 | 02019 | 5.76 |  |  | Solar |  | 05_05_312W1 | 12/16/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/16/2024 | 3/19/2026 | Y | EXP | 365 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 700800 | 01752 | 10 |  |  | Solar |  | 05_12_51L2 | 07/01/2025 | 08/19/2025 | 34 | 31 | 3 | 08/20/2025 | 08/20/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | BEVERLY | 209967 | 01915 | 910 |  |  | Solar |  | 05_14_2L1 | 03/04/2019 | 03/19/2019 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/20/2019 | 08/22/2019 | 101 | 35 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 431905 | 01824 | 7.6 |  |  | Solar |  | 05_14_57L2 | 07/08/2022 | 07/19/2022 | 8 | 7 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 653107 | 01886 | 2.32 |  |  | Solar |  | 05_14_70L8 | 11/14/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | BILLERICA | 613140 | 01821 | 6 |  |  | Solar |  | 05_14_8L2 | 05/23/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 10/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176696 | 01841 | 10 |  |  | Solar |  | 05_01_24W2 | 04/21/2016 | 04/21/2016 | 3 | 3 | 0 | 04/28/2016 | 04/28/2016 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 699214 | 01605 | 9.423 |  |  | Solar |  | 05_01_412L1 | 06/23/2025 | 06/25/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | WEBSTER | 702598 | 01570 | 11.5 |  |  | Solar |  | 05_01_55W1 | 07/14/2025 | 07/21/2025 | 5 | 0 | 5 | 07/22/2025 | 07/22/2025 | 64 | 55 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 469025 | 01543 | 3.8 |  |  | Solar |  | 05_05_108W60 | 10/21/2022 | 10/26/2022 | 4 | 1 | 3 | 10/27/2022 | 10/27/2022 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 739032 | 02019 | 0 |  |  | Battery Add-On |  | 05_05_312W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 697184 | 01752 | 17.6 |  |  | Solar |  | 05_12_51L3 | 06/11/2025 | 06/16/2025 | 3 | 0 | 3 | 06/17/2025 | 06/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BEVERLY | 241760 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L1 | 07/24/2019 | 07/25/2019 | 0 | 0 | 0 | 07/26/2019 | 07/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 433175 | 01879 | 10 |  |  | Solar |  | 05_14_57L2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 06/17/2022 | 3/19/2024 | Y | EXP | 365 | 03/08/2023 | 03/20/2023 | 13 | 0 | 13 |  |  | 3/27/2023 | Connected |  | Y
National Grid | WESTFORD | 657260 | 01886 | 3.8 |  |  | Solar |  | 05_14_70L8 | 11/27/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y
National Grid | TEWKSBURY | 616791 | 01876 | 5.76 |  |  | Solar |  | 05_14_8L2 | 06/10/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 12/6/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176856 | 01841 | 9 |  |  | Solar |  | 05_01_24W2 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 |  | 11/18/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/6/2016 | 5/6/2016 | 5/17/2016 | Connected |  | N
National Grid | WORCESTER | 642827 | 01605 | 4990 |  |  | Other |  | 05_01_412L2 | 11/21/2024 | 12/12/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEBSTER | 707581 | 01570 | 10 |  |  | Solar |  | 05_01_55W1 | 07/25/2025 | 09/03/2025 | 3 | 0 | 3 | 09/04/2025 | 09/04/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 478954 | 01543 | 10 |  |  | Solar |  | 05_05_108W60 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/23/2023 | 4/18/2024 | Y | EXP | 365 | 03/21/2023 | 04/19/2023 | 30 | 0 | 30 |  |  | 7/17/2023 | Connected |  | N
National Grid | BELLINGHAM | 174200 | 02019 | 260 |  |  | Solar |  | 05_05_312W1 | 03/27/2012 | 03/27/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/27/2012 | 10/1/2012 | Y | EXP | -72 | 02/06/2013 | 03/04/2013 | 13 | 0 | 13 | 3/21/2013 | 3/21/2013 | 4/1/2013 | Connected |  | N
National Grid | WESTBOROUGH | 710433 | 01581 | 18.34 |  |  | Solar |  | 05_12_51L3 | 08/07/2025 | 08/13/2025 | 4 | 0 | 4 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BEVERLY | 332924 | 01915 | 10 |  |  | Solar |  | 05_14_2L1 | 12/18/2020 | 12/22/2020 | 1 | 0 | 1 | 12/23/2020 | 12/23/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 441483 | 01863 | 7.6 |  |  | Solar |  | 05_14_57L2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 672610 | 01886 | 5.76 |  |  | Solar |  | 05_14_70L8 | 02/18/2025 | 03/17/2025 | 8 | 2 | 6 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | TEWKSBURY | 617449 | 01876 | 5.76 |  |  | Solar |  | 05_14_8L2 | 06/12/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | METHUEN | 177203 | 01844 | 379.7 |  |  | Solar |  | 05_01_24W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 670827 | 01605 | 3.8 |  |  | Solar |  | 05_01_412L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 174972 | 01570 | 4999 |  |  | Solar |  | 05_01_55W3 | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2011 | 12/20/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 09/26/2011 | 6/1/2014 | Y | STD | 590 | 03/12/2014 | 12/18/2014 | 192 | 0 | 192 | 7/9/2014 | 7/9/2014 | 7/11/2014 | Connected |  | Y
National Grid | RUTLAND | 480519 | 01543 | 0 |  |  | Solar |  | 05_05_108W60 | 11/28/2022 | 11/29/2022 | 2 | 1 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 2/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N
National Grid | BELLINGHAM | 174427 | 02019 | 600 |  |  | Solar |  | 05_05_312W1 | 11/21/2011 | 11/21/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2012 | 11/21/2011 | 10/31/2012 | Y | STD | 98 | 08/21/2012 | 10/11/2012 | 35 | 0 | 35 | 10/9/2012 | 10/9/2012 | 10/15/2012 | Connected |  | N
National Grid | WESTBOROUGH | 721115 | 01581 | 0 |  |  | Solar |  | 05_12_51L3 | 09/23/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 337901 | 01915 | 66.6 |  |  | Solar |  | 05_14_2L1 | 01/22/2021 | 02/03/2021 | 7 | 0 | 7 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | CHELMSFORD | 458118 | 01863 | 19 |  |  | Solar |  | 05_14_57L2 | 09/12/2022 | 09/12/2022 | 0 | 0 | 0 | 09/13/2022 | 09/13/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | WESTFORD | 709365 | 01886 | 15.2 |  |  | Solar |  | 05_14_70L8 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | TEWKSBURY | 617125 | 01876 | 7.6 |  |  | Solar |  | 05_14_8L2 | 06/11/2024 | 06/18/2024 | 1 | 0 | 1 | 06/20/2024 | 06/20/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LAWRENCE | 177592 | 01841 | 339.7 |  |  | Solar |  | 05_01_24W2 | 05/21/2017 | 05/21/2017 | 37 | 33 | 4 | 07/14/2017 | 07/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2017 |  | 5/27/2018 | N | EXP | 278 |  |  | 0 | 0 | 0 | 2/12/2018 | 2/12/2018 | 2/12/2018 | Connected |  | N
National Grid | WORCESTER | 670548 | 01605 | 0 |  |  | Other |  | 05_01_412L2 | 08/11/2025 | 09/15/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEBSTER | 176162 | 01570 | 1000 |  |  | Solar |  | 05_01_55W3 | 02/06/2015 | 02/06/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 | 02/06/2015 | 9/24/2017 | Y | STD | 648 | 08/11/2017 | 09/15/2017 | 24 | 0 | 24 | 9/8/2017 | 9/8/2017 | 9/29/2017 | Connected |  | N
National Grid | RUTLAND | 489055 | 01543 | 10 |  |  | Solar |  | 05_05_108W60 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 174993 | 01504 | 100 |  |  | Solar |  | 05_05_312W1 | 03/11/2013 | 03/11/2013 | 4 | 0 | 4 | 03/19/2013 | 03/19/2013 | 978 | 0 | 978 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 12/31/2016 | N | EXP | 1341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174456 | 01581 | 200 |  |  | Solar |  | 05_12_51L3 | 11/04/2011 | 11/04/2011 | 33 | 0 | 33 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2012 |  | 10/31/2012 | N | EXP | 253 |  |  | 0 | 0 | 0 | 1/28/2013 | 1/28/2013 | 2/12/2013 | Connected |  | N
National Grid | HAMILTON | 340624 | 01982 | 9.6 |  |  | Solar |  | 05_14_2L1 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 2/4/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 461886 | 01879 | 7.6 |  |  | Solar |  | 05_14_57L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 | 11/29/2022 | 6/15/2024 | Y | EXP | 365 | 06/09/2023 | 06/12/2023 | 4 | 0 | 4 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 710520 | 01886 | 18.24 |  |  | Solar |  | 05_14_70L8 | 08/07/2025 | 08/14/2025 | 4 | 1 | 3 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | Y
National Grid | BILLERICA | 619063 | 01821 | 5.76 |  |  | Solar |  | 05_14_8L2 | 06/19/2024 | 07/01/2024 | 3 | 0 | 3 | 07/02/2024 | 07/02/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | LAWRENCE | 177694 | 01841 | 5 |  |  | Solar |  | 05_01_24W2 | 03/21/2017 | 03/21/2017 | 10 | 10 | 0 | 04/04/2017 | 04/04/2017 | 211 | 0 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 |  | 3/26/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 689117 | 01605 | 15.2 |  |  | Solar |  | 05_01_412L2 | 05/05/2025 | 05/06/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 178360 | 01570 | 4300 |  |  | Solar |  | 05_01_55W3 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 491574 | 01543 | 20 |  |  | Solar |  | 05_05_108W60 | 01/11/2023 | 01/13/2023 | 3 | 2 | 1 | 01/17/2023 | 01/17/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/11/2023 | 3/2/2024 | Y | EXP | 365 | 03/21/2023 | 04/22/2023 | 33 | 0 | 33 |  |  | 6/26/2023 | Connected |  | N
National Grid | BLACKSTONE | 177043 | 01504 | 792 |  |  | Solar |  | 05_05_312W1 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 02/07/2017 | 69 | 56 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 | 10/17/2016 | 3/28/2022 | Y | STD | 1002 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174970 | 01581 | 85 |  |  | Solar |  | 05_12_51L3 | 09/10/2013 | 09/10/2013 | 7 | 0 | 7 | 09/20/2013 | 09/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 12/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 3/7/2014 | 3/7/2014 | 4/4/2014 | Connected |  | N
National Grid | BEVERLY | 346687 | 01915 | 11.31 |  |  | Solar |  | 05_14_2L1 | 03/12/2021 | 04/22/2021 | 27 | 25 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | CHELMSFORD | 479921 | 01863 | 7.6 |  |  | Solar |  | 05_14_57L2 | 01/04/2023 | 01/09/2023 | 3 | 0 | 3 | 01/10/2023 | 01/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 709192 | 01886 | 9.425 |  |  | Solar |  | 05_14_71L1 | 08/06/2025 | 10/09/2025 | 5 | 2 | 3 | 10/10/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 620656 | 01876 | 7.6 |  |  | Solar |  | 05_14_8L2 | 06/27/2024 | 07/16/2024 | 1 | 1 | 0 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/27/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LAWRENCE | 203085 | 01841 | 150 |  |  | Solar |  | 05_01_24W2 | 12/06/2018 | 01/02/2019 | 14 | 12 | 2 | 01/03/2019 | 01/03/2019 | 3 | 0 | 3 | 01/18/2019 | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 |  | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 | 5/17/2019 | 12/06/2018 | 9/25/2020 | Y | EXP | 349 | 02/14/2020 | 03/12/2020 | 27 | 0 | 27 |  |  | 9/25/2020 | Connected |  | N
National Grid | WORCESTER | 709362 | 01606 | 11.4 |  |  | Solar |  | 05_01_412L2 | 08/08/2025 | 08/19/2025 | 6 | 5 | 1 | 08/20/2025 | 08/20/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 370269 | 01570 | 2000 |  |  | Solar |  | 05_01_602W2 | 11/12/2021 | 01/21/2022 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2022 | 11/21/2022 | 209 | 201 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RUTLAND | 503144 | 01543 | 6 |  |  | Solar |  | 05_05_108W60 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/28/2023 | 5/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 177570 | 01504 | 15.2 |  |  | Solar |  | 05_05_312W1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 175113 | 01581 | 19.99 |  |  | Solar |  | 05_12_51L3 | 10/15/2013 | 10/15/2013 | 7 | 0 | 7 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 | 2/12/2014 | 2/12/2014 | 2/24/2014 | Connected |  | N
National Grid | HAMILTON | 650138 | 01982 | 4.48 |  |  | Solar |  | 05_14_2L1 | 10/28/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 540656 | 01863 | 13.92 |  |  | Solar |  | 05_14_57L2 | 07/24/2023 | 07/27/2023 | 4 | 3 | 1 | 07/28/2023 | 07/28/2023 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | WESTFORD | 715308 | 01886 | 0 |  |  | Solar |  | 05_14_71L1 | 08/28/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 621743 | 01876 | 7.6 |  |  | Solar |  | 05_14_8L2 | 07/01/2024 | 07/10/2024 | 3 | 0 | 3 | 07/11/2024 | 07/11/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N
National Grid | METHUEN | 204161 | 01844 | 426.4 |  |  | Solar |  | 05_01_24W2 | 12/18/2018 | 01/22/2019 | 22 | 17 | 5 | 01/23/2019 | 01/23/2019 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 730060 | 01605 | 20 |  |  | Solar |  | 05_01_412L2 | 10/30/2025 | 10/31/2025 | 1 | 0 | 1 | 11/03/2025 | 11/03/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 357820 | 01570 | 240 |  |  | Solar |  | 05_01_602W2 | 05/14/2021 | 06/02/2021 | 10 | 0 | 10 |  |  | 53 | 28 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RUTLAND | 508947 | 01543 | 10 |  |  | Solar |  | 05_05_108W60 | 03/20/2023 | 03/21/2023 | 1 | 0 | 1 | 03/22/2023 | 03/22/2023 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | BELLINGHAM | 191397 | 02019 | 7.6 |  |  | Solar |  | 05_05_312W1 | 07/20/2018 | 09/05/2018 | 3 | 3 | 0 | 09/06/2018 | 09/06/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 175187 | 01581 | 60 |  |  | Natural Gas |  | 05_12_51L3 | 11/14/2013 | 11/14/2013 | 6 | 0 | 6 | 11/25/2013 | 11/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2013 |  | 2/17/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 5/1/2014 | 5/1/2014 | 5/27/2014 | Connected |  | N
National Grid | HAMILTON | 664682 | 01982 | 4.18 |  |  | Solar |  | 05_14_2L1 | 01/09/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | WESTFORD | 570545 | 01886 |  |  |  | Battery Add-On |  | 05_14_57L2 | 11/10/2023 | 11/30/2023 | 14 | 12 | 2 | 12/01/2023 | 12/01/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 11/10/2023 | 2/21/2025 | Y | EXP | 365 | 04/23/2024 | 06/04/2024 | 43 | 0 | 43 |  |  | 6/7/2024 | Connected |  | N
National Grid | WESTFORD | 177528 | 01886 | 66.6 |  |  | Solar |  | 05_14_71L1 | 09/11/2017 | 09/11/2017 | 21 | 20 | 1 | 10/11/2017 | 10/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2017 |  | 6/29/2018 | N | EXP | 260 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | TEWKSBURY | 622785 | 01876 | 6 |  |  | Solar |  | 05_14_8L2 | 07/05/2024 | 07/18/2024 | 4 | 0 | 4 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/05/2024 | 8/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | LAWRENCE | 206472 | 01841 | 250 |  |  | Solar |  | 05_01_24W2 | 03/12/2019 | 03/18/2019 | 4 | 2 | 2 | 03/19/2019 | 03/19/2019 | 17 | 11 | 6 | 05/31/2019 | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 734850 | 01605 | 9.57 |  |  | Solar |  | 05_01_412L2 | 11/19/2025 | 11/20/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEBSTER | 472560 | 01570 | 30 |  |  | Solar |  | 05_01_602W2 | 05/14/2023 | 05/30/2023 | 11 | 2 | 9 |  |  | 66 | 41 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | RUTLAND | 525114 | 01543 | 0 |  |  | Solar |  | 05_05_108W60 | 05/11/2023 | 07/18/2023 | 45 | 42 | 3 | 05/01/2024 | 05/01/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 196685 | 01504 | 8.7 |  |  | Solar |  | 05_05_312W1 | 09/21/2018 | 10/24/2018 | 3 | 3 | 0 | 10/25/2018 | 10/25/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2018 | 09/21/2018 | 6/10/2019 | Y | EXP | 222 | 03/16/2019 | 03/15/2019 | 0 | 0 | 0 |  |  | 4/19/2019 | Connected |  | N
National Grid | WESTBOROUGH | 175468 | 01581 | 4.73 |  |  | Solar |  | 05_12_51L3 | 11/25/2014 | 11/25/2014 | 5 | 0 | 5 | 12/04/2014 | 12/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 11/25/2014 | 4/30/2015 | Y | EXP | 71 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 | 3/9/2015 | 3/9/2015 | 11/23/2015 | Connected |  | N
National Grid | HAMILTON | 709518 | 01982 | 11.4 |  |  | Solar |  | 05_14_2L2 | 08/05/2025 | 09/24/2025 | 34 | 24 | 10 | 09/25/2025 | 09/25/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 588461 | 01863 | 23 |  |  | Solar |  | 05_14_57L2 | 02/07/2024 | 02/14/2024 | 6 | 4 | 2 | 02/15/2024 | 02/15/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | WESTFORD | 178518 | 01886 | 10 |  |  | Solar |  | 05_14_71L1 | 04/04/2018 | 04/04/2018 | 6 | 0 | 6 | 04/13/2018 | 04/13/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 626779 | 01845 | 10 |  |  | Solar |  | 05_14_8L2 | 07/22/2024 | 09/27/2024 | 36 | 31 | 5 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 07/22/2024 | 1/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LAWRENCE | 207134 | 01841 | 240 |  |  | Solar |  | 05_01_24W2 | 01/30/2019 | 02/11/2019 | 8 | 2 | 6 | 02/12/2019 | 02/12/2019 | 39 | 20 | 19 | 08/07/2019 | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 743323 | 01606 | 10 |  |  | Solar |  | 05_01_412L2 | 01/05/2026 | 01/06/2026 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUDLEY | 536174 | 01571 | 275 |  |  | Solar |  | 05_01_602W2 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/20/2023 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GARDNER | 563891 | 01440 | 3.8 |  |  | Solar |  | 05_05_108W60 | 10/30/2023 | 12/29/2023 | 42 | 37 | 5 | 01/02/2024 | 01/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | BELLINGHAM | 200805 | 02019 | 7.6 |  |  | Solar |  | 05_05_312W1 | 11/08/2018 | 12/19/2018 | 6 | 0 | 6 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 | 11/08/2018 | 11/8/2020 | Y | EXP | 365 | 03/04/2020 | 03/25/2020 | 21 | 0 | 21 |  |  | 7/16/2020 | Connected |  | N
National Grid | WESTBOROUGH | 177285 | 01581 | 10 |  |  | Solar |  | 05_12_51L3 | 06/16/2016 | 06/16/2016 | 1 | 1 | 0 | 06/20/2016 | 06/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 | 06/16/2016 | 6/21/2017 | Y | EXP | 358 | 11/10/2016 | 01/05/2017 | 36 | 0 | 36 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N
National Grid | BEVERLY | 178453 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 | 11/29/2017 | 9/19/2019 | Y | EXP | 597 | 06/06/2018 | 06/20/2018 | 14 | 0 | 14 |  |  | 9/5/2019 | Connected |  | N
National Grid | CHELMSFORD | 604077 | 01863 | 12.35 |  |  | Solar |  | 05_14_57L2 | 04/18/2024 | 04/29/2024 | 2 | 1 | 1 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N
National Grid | WESTFORD | 184342 | 01886 | 0 |  |  | Solar |  | 05_14_71L1 | 05/18/2018 | 05/18/2018 | 1 | 0 | 1 | 05/22/2018 | 05/22/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | ANDOVER | 631949 | 01845 | 7.6 |  |  | Solar |  | 05_14_8L2 | 08/12/2024 | 08/19/2024 | 1 | 0 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 | 08/12/2024 | 9/3/2025 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | LAWRENCE | 209361 | 01841 | 72 |  |  | Solar |  | 05_01_24W2 | 02/12/2019 | 04/10/2019 | 4 | 0 | 4 | 04/11/2019 | 04/11/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174756 | 01606 | 1000 |  |  | Solar |  | 05_01_412L2 | 02/03/2014 | 02/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2014 | 02/26/2014 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2014 |  | 8/14/2016 | N | STD | 681 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 543236 | 01570 | 0 |  |  | Other |  | 05_01_602W2 | 09/07/2023 | 10/02/2023 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2023 | 11/07/2023 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GARDNER | 580770 | 01440 | 7.296 |  |  | Solar |  | 05_05_108W60 | 02/23/2024 | 03/01/2024 | 6 | 2 | 4 | 03/04/2024 | 03/04/2024 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/23/2024 | 6/17/2025 | Y | EXP | 365 | 04/30/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 11/15/2024 | Connected |  | N
National Grid | BLACKSTONE | 200739 | 01504 | 3.8 |  |  | Solar |  | 05_05_312W1 | 11/08/2018 | 01/10/2019 | 26 | 20 | 6 | 01/11/2019 | 01/11/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 5/19/2020 | Y | EXP | 488 | 01/14/2020 | 01/27/2020 | 13 | 0 | 13 |  |  | 2/6/2020 | Connected |  | N
National Grid | WESTBOROUGH | 178288 | 01581 | 7.6 |  |  | Solar |  | 05_12_51L3 | 03/28/2018 | 03/28/2018 | 7 | 0 | 7 | 04/09/2018 | 04/09/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 03/28/2018 | 7/15/2021 | Y | EXP | 317 |  |  | 0 | 0 | 0 |  |  | 6/22/2021 | Connected |  | N
National Grid | BEVERLY | 178471 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L2 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/12/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 609526 | 01863 | 11.5 |  |  | Solar |  | 05_14_57L2 | 05/08/2024 | 06/07/2024 | 3 | 0 | 3 | 06/10/2024 | 06/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | WESTFORD | 384672 | 01886 | 144 |  |  | Solar |  | 05_14_71L1 | 10/06/2021 | 12/02/2021 | 38 | 29 | 9 | 12/03/2021 | 12/03/2021 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 | 10/06/2021 | 8/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2023 | Connected |  | N
National Grid | ANDOVER | 634175 | 01845 | 5.76 |  |  | Solar |  | 05_14_8L2 | 08/22/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 08/22/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | LAWRENCE | 274013 | 01841 | 250 |  |  | Solar |  | 05_01_24W2 | 02/11/2020 | 02/14/2020 | 3 | 1 | 2 |  |  | 60 | 43 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 02/11/2020 | 6/23/2023 | Y | STD | 858 | 04/02/2022 | 06/06/2023 | 430 | 0 | 430 | 5/25/2023 | 6/7/2023 | 6/16/2023 | Connected |  | N
National Grid | WORCESTER | 175472 | 01605 | 762 |  |  | Solar |  | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 28 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 3/16/2016 | N | STD | 114 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 605595 | 01570 | 100 |  |  | Solar |  | 05_01_602W2 | 04/22/2024 | 05/08/2024 | 12 | 5 | 7 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GARDNER | 585799 | 01440 | 6 |  |  | Solar |  | 05_05_108W60 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 203444 | 01504 | 0 |  |  | Solar |  | 05_05_312W1 | 12/12/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 184467 | 01581 | 51.75 |  |  | Solar |  | 05_12_51L3 | 06/18/2018 | 06/18/2018 | 0 | 0 | 0 | 06/22/2018 | 06/22/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 10/7/2019 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | Connected |  | N
National Grid | BEVERLY | 184905 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L2 | 06/11/2018 | 06/11/2018 | 1 | 0 | 1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 616733 | 01851 | 23 |  |  | Solar |  | 05_14_57L2 | 06/10/2024 | 06/14/2024 | 4 | 3 | 1 | 06/17/2024 | 06/17/2024 | 84 | 65 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 514296 | 01886 | 10 |  |  | Solar |  | 05_14_71L1 | 04/03/2023 | 04/06/2023 | 3 | 0 | 3 | 04/07/2023 | 04/07/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 635288 | 01810 | 2.32 |  |  | Solar |  | 05_14_8L2 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/26/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | LAWRENCE | 307776 | 01841 | 9.12 |  |  | Solar |  | 05_01_24W2 | 08/31/2020 | 09/16/2020 | 11 | 11 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | WORCESTER | 175748 | 01606 | 16 |  |  | Solar |  | 05_01_412L2 | 10/30/2014 | 10/30/2014 | 6 | 4 | 2 | 11/10/2014 | 11/10/2014 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 12/30/2014 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 655034 | 01570 | 120 |  |  | Solar |  | 05_01_602W2 | 11/25/2024 | 12/20/2024 | 17 | 8 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | GARDNER | 587149 | 01440 | 7.6 |  |  | Solar |  | 05_05_108W60 | 03/26/2024 | 04/17/2024 | 15 | 13 | 2 | 04/18/2024 | 04/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 03/26/2024 | 5/3/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N
National Grid | BLACKSTONE | 209566 | 01504 | 433.3 |  |  | Solar |  | 05_05_312W1 | 04/24/2019 | 05/06/2019 | 8 | 6 | 2 | 05/30/2019 | 05/30/2019 | 0 | 0 | 0 | 07/12/2019 | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 184417 | 01581 | 24 |  |  | Solar |  | 05_12_51L3 | 06/22/2018 | 06/22/2018 | 2 | 2 | 0 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2018 |  | 11/1/2019 | N | EXP | 483 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | BEVERLY | 191228 | 01915 | 3 |  |  | Solar |  | 05_14_2L2 | 07/19/2018 | 09/13/2018 | 31 | 25 | 6 | 09/14/2018 | 09/14/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 | 07/19/2018 | 10/8/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | LOWELL | 617530 | 01851 | 15.2 |  |  | Solar |  | 05_14_57L2 | 09/18/2024 |  | 29 | 27 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 543541 | 01886 | 84.6 |  |  | Solar |  | 05_14_71L1 | 07/25/2023 | 08/29/2023 | 26 | 16 | 10 | 08/30/2023 | 08/30/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 638038 | 01810 | 7.6 |  |  | Solar |  | 05_14_8L2 | 09/05/2024 | 10/25/2024 | 22 | 21 | 1 | 10/28/2024 | 10/28/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 322315 | 01841 | 10 |  |  | Solar |  | 05_01_24W2 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | WORCESTER | 176055 | 01606 | 15.48 |  |  | Solar |  | 05_01_412L2 | 01/30/2015 | 01/30/2015 | 11 | 11 | 0 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 130 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 11/19/2015 | Connected |  | N
National Grid | WEBSTER | 653874 | 01570 | 50 |  |  | Solar |  | 05_01_602W2 | 11/15/2024 | 11/19/2024 | 2 | 0 | 2 |  |  | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | HUBBARDSTON | 587903 | 01452 | 7.83 |  |  | Solar |  | 05_05_108W60 | 02/16/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | BLACKSTONE | 209564 | 01504 | 700 |  |  | Solar |  | 05_05_312W1 | 04/24/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 189641 | 01581 | 5 |  |  | Solar |  | 05_12_51L3 | 02/26/2019 | 07/05/2018 | 5 | 0 | 5 | 03/07/2019 | 03/07/2019 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 197063 | 01982 | 7.68 |  |  | Solar |  | 05_14_2L2 | 10/03/2018 | 10/11/2018 | 3 | 3 | 0 | 10/12/2018 | 10/12/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 10/03/2018 | 5/29/2019 | Y | EXP | 225 | 02/01/2019 | 01/31/2019 | 0 | 0 | 0 |  |  | 4/16/2019 | Connected |  | N
National Grid | CHELMSFORD | 629694 | 01863 | 10 |  |  | Solar |  | 05_14_57L2 | 08/02/2024 | 08/26/2024 | 8 | 5 | 3 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/02/2024 | 9/19/2025 | Y | EXP | 365 | 10/24/2024 | 10/30/2024 | 7 | 0 | 7 |  |  | 12/27/2024 | Connected |  | N
National Grid | WESTFORD | 573060 | 01886 | 0 |  |  | Solar |  | 05_14_71L1 | 12/04/2023 | 12/12/2023 | 6 | 4 | 2 | 12/13/2023 | 12/13/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | ANDOVER | 642722 | 01810 | 5.76 |  |  | Solar |  | 05_14_8L2 | 09/25/2024 | 10/09/2024 | 2 | 0 | 2 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 351365 | 01841 | 7.6 |  |  | Solar |  | 05_01_24W2 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 10/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N
National Grid | WORCESTER | 176658 | 01605 | 6 |  |  | Solar |  | 05_01_412L2 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 4/26/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 686395 | 01570 | 3.9 |  |  | Solar |  | 05_01_602W2 | 04/21/2025 | 10/09/2025 | 2 | 0 | 2 | 10/15/2025 | 10/15/2025 | 48 | 31 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 599414 | 01440 | 7.6 |  |  | Solar |  | 05_05_108W60 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 38 | 25 | 13 | 06/11/2024 | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 8/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 209562 | 02019 | 700 |  |  | Solar |  | 05_05_312W1 | 04/25/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 306908 | 01581 | 13.6 |  |  | Solar |  | 05_12_51L3 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2020 |  | 8/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2020 | Connected |  | N
National Grid | HAMILTON | 198842 | 01982 | 3.8 |  |  | Solar |  | 05_14_2L2 | 12/06/2018 | 12/19/2018 | 8 | 0 | 8 | 12/20/2018 | 12/20/2018 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 633475 | 01851 | 8.7 |  |  | Solar |  | 05_14_57L2 | 09/20/2024 | 10/22/2024 | 9 | 5 | 4 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WESTFORD | 575824 | 01886 | 100 |  |  | Solar |  | 05_14_71L1 | 12/08/2023 | 12/22/2023 | 10 | 3 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 644598 | 01845 | 10 |  |  | Solar |  | 05_14_8L2 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/02/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | LAWRENCE | 376655 | 01841 | 9.8 |  |  | Solar |  | 05_01_24W2 | 08/31/2021 |  | 50 | 45 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176764 | 01606 | 6 |  |  | Solar |  | 05_01_412L2 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 08/04/2016 | 08/23/2016 | 13 | 0 | 13 | 4/4/2016 | 4/4/2016 | 9/15/2016 | Connected |  | N
National Grid | DUDLEY | 692468 | 01571 | 3.8 |  |  | Solar |  | 05_01_602W2 | 05/19/2025 | 07/30/2025 | 3 | 0 | 3 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/19/2025 | 9/19/2026 | Y | EXP | 365 | 12/31/2025 |  | 2 | 0 | 2 |  |  |  | Construction |  | N
National Grid | GARDNER | 600470 | 01440 | 11.02 |  |  | Solar |  | 05_05_108W60 | 05/13/2024 | 05/14/2024 | 1 | 0 | 1 | 05/15/2024 | 05/15/2024 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N
National Grid | BLACKSTONE | 228960 | 01504 | 10 |  |  | Solar |  | 05_05_312W1 | 05/17/2019 | 05/24/2019 | 4 | 0 | 4 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 309531 | 01581 | 5.8 |  |  | Solar |  | 05_12_51L3 | 09/01/2020 | 09/02/2020 | 1 | 1 | 0 | 09/03/2020 | 09/03/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2020 |  | 9/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | HAMILTON | 250967 | 01982 | 7.6 |  |  | Solar |  | 05_14_2L2 | 08/27/2019 | 08/28/2019 | 1 | 1 | 0 | 08/29/2019 | 08/29/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/27/2019 | 8/28/2020 | Y | EXP | 233 | 01/09/2020 | 03/12/2020 | 62 | 0 | 62 |  |  | 3/24/2020 | Connected |  | N
National Grid | LOWELL | 637981 | 01851 | 5.2 |  |  | Solar |  | 05_14_57L2 | 09/05/2024 | 10/01/2024 | 2 | 0 | 2 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/05/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | WESTFORD | 608290 | 01886 | 7.6 |  |  | Solar |  | 05_14_71L1 | 05/04/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 05/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 644467 | 01845 | 3.8 |  |  | Solar |  | 05_14_8L2 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | METHUEN | 410649 | 01844 | 6 |  |  | Solar |  | 05_01_24W2 | 02/07/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176851 | 01605 | 45.6 |  |  | Solar |  | 05_01_412L2 | 11/11/2015 | 11/11/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 | 11/11/2015 | 11/18/2016 | Y | EXP | 350 | 05/11/2016 | 07/13/2016 | 42 | 0 | 42 | 12/4/2015 | 12/4/2015 | 8/23/2016 | Connected |  | N
National Grid | WEBSTER | 693377 | 01570 | 11.4 |  |  | Solar |  | 05_01_602W2 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 141 | 131 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | GARDNER | 613326 | 01440 | 11.5 |  |  | Solar |  | 05_05_108W60 | 05/28/2024 | 06/11/2024 | 11 | 9 | 2 | 06/12/2024 | 06/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N
National Grid | BELLINGHAM | 240960 | 02019 | 6 |  |  | Solar |  | 05_05_312W1 | 06/26/2019 | 08/07/2019 | 7 | 7 | 0 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 06/26/2019 | 5/1/2020 | Y | EXP | 259 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 12/13/2019 | Connected |  | N
National Grid | WESTBOROUGH | 339578 | 01581 | 7.6 |  |  | Solar |  | 05_12_51L3 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | BEVERLY | 324108 | 01915 | 10 |  |  | Solar |  | 05_14_2L2 | 11/09/2020 | 12/07/2020 | 17 | 14 | 3 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 1/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | LOWELL | 651787 | 01851 | 7.6 |  |  | Solar |  | 05_14_57L2 | 11/04/2024 | 01/24/2025 | 5 | 0 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 615033 | 01886 | 7.6 |  |  | Solar |  | 05_14_71L1 | 06/03/2024 | 06/18/2024 | 5 | 0 | 5 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | ANDOVER | 648245 | 01810 | 5.76 |  |  | Solar |  | 05_14_8L2 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 | 01/15/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 2/21/2025 | 10/30/2024 | 2/26/2026 | Y | EXP | 365 | 08/20/2025 | 08/19/2025 | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | LAWRENCE | 418368 | 01841 | 9.8 |  |  | Solar |  | 05_01_24W2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/14/2022 | 9/5/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176899 | 01605 | 23.4 |  |  | Solar |  | 05_01_412L2 | 01/26/2016 | 01/26/2016 | 3 | 3 | 0 | 01/29/2016 | 01/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 |  | 1/31/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/16/2016 | 9/16/2016 | 9/16/2016 | Connected |  | N
National Grid | WEBSTER | 706227 | 01570 | 7.6 |  |  | Solar |  | 05_01_602W2 | 07/21/2025 | 07/23/2025 | 2 | 0 | 2 | 07/24/2025 | 07/24/2025 | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 620631 | 01473 | 10 |  |  | Solar |  | 05_05_108W60 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | BELLINGHAM | 287290 | 02019 | 0 |  |  | Solar |  | 05_05_312W1 | 04/09/2020 | 04/10/2020 | 0 | 0 | 0 | 04/13/2020 | 04/13/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/09/2020 | 4/9/2021 | Y | EXP | 365 | 09/05/2020 | 11/10/2020 | 66 | 0 | 66 |  |  | 2/23/2021 | Connected |  | N
National Grid | WESTBOROUGH | 342563 | 01581 | 7.68 |  |  | Solar |  | 05_12_51L3 | 02/17/2021 | 02/23/2021 | 4 | 4 | 0 | 02/24/2021 | 02/24/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | N
National Grid | HAMILTON | 394090 | 01982 | 6 |  |  | Solar |  | 05_14_2L2 | 11/29/2021 | 01/07/2022 | 11 | 10 | 1 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 662101 | 01863 | 11.5 |  |  | Solar |  | 05_14_57L2 | 12/20/2024 | 12/31/2024 | 6 | 2 | 4 | 01/02/2025 | 01/02/2025 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WESTFORD | 646857 | 01886 | 10 |  |  | Solar |  | 05_14_71L1 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 10/29/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | ANDOVER | 649543 | 01845 | 3.8 |  |  | Solar |  | 05_14_8L2 | 11/05/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | LAWRENCE | 423774 | 01841 | 67.3 |  |  | Solar |  | 05_01_24W2 | 04/20/2022 | 05/04/2022 | 10 | 1 | 9 | 05/05/2022 | 05/05/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/20/2022 | 11/8/2023 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | WORCESTER | 177152 | 01605 | 762 |  |  | Solar |  | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2015 | 11/26/2014 | 12/31/2017 | Y | STD | 766 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 | 12/1/2017 | 12/1/2017 | 12/19/2017 | Connected |  | N
National Grid | WEBSTER | 713175 | 01570 | 23 |  |  | Solar |  | 05_01_602W2 | 08/19/2025 | 08/21/2025 | 2 | 0 | 2 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 637783 | 01440 | 10 |  |  | Solar |  | 05_05_108W60 | 09/04/2024 | 09/20/2024 | 3 | 0 | 3 | 09/23/2024 | 09/23/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 289142 | 02019 | 7.6 |  |  | Solar |  | 05_05_312W1 | 04/23/2020 | 06/09/2020 | 31 | 26 | 5 | 06/10/2020 | 06/10/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | WESTBOROUGH | 354859 | 01581 | 6.38 |  |  | Solar |  | 05_12_51L3 | 04/27/2021 | 04/28/2021 | 1 | 1 | 0 | 04/29/2021 | 04/29/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  | 4/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | WENHAM | 488662 | 01984 | 22.272 |  |  | Solar |  | 05_14_2L2 | 12/29/2022 | 04/06/2023 | 68 | 59 | 9 | 04/07/2023 | 04/07/2023 | 150 | 133 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 663185 | 01851 | 5.76 |  |  | Solar |  | 05_14_57L2 | 01/02/2025 | 02/19/2025 | 13 | 9 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | WESTFORD | 661800 | 01886 | 7.6 |  |  | Solar |  | 05_14_71L1 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | ANDOVER | 652216 | 01845 | 7.6 |  |  | Solar |  | 05_14_8L2 | 11/14/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/14/2024 | 2/10/2026 | Y | EXP | 365 | 07/24/2025 | 12/01/2025 | 131 | 0 | 131 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 425538 | 01841 | 250 |  |  | Solar |  | 05_01_24W2 | 06/01/2022 | 06/15/2022 | 10 | 2 | 8 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177281 | 01605 | 1000 |  |  | Solar |  | 05_01_412L2 | 02/08/2017 | 02/17/2017 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2017 | 02/22/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2018 | 02/08/2017 | 11/12/2021 | Y | STD | 571 | 02/06/2021 | 08/13/2021 | 189 | 0 | 189 | 8/16/2021 | 9/30/2021 | 11/2/2021 | Connected |  | N
National Grid | WEBSTER | 715276 | 01570 | 10 |  |  | Solar |  | 05_01_602W2 | 08/28/2025 | 09/18/2025 | 2 | 0 | 2 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 08/28/2025 | 11/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GARDNER | 643794 | 01440 | 7.6 |  |  | Solar |  | 05_05_108W60 | 10/04/2024 | 10/18/2024 | 4 | 4 | 0 | 10/21/2024 | 10/21/2024 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | BELLINGHAM | 293153 | 02019 | 86 |  |  | Solar |  | 05_05_312W1 | 06/08/2020 | 06/24/2020 | 12 | 6 | 6 | 06/25/2020 | 06/25/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 406056 | 01581 | 0 |  |  | Battery Add-On |  | 05_12_51L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 02/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 561313 | 01982 | 7.25 |  |  | Solar |  | 05_14_2L2 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 664396 | 01851 | 7.6 |  |  | Solar |  | 05_14_57L2 | 01/08/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 666713 | 01886 | 5.76 |  |  | Solar |  | 05_14_71L1 | 01/20/2025 | 05/02/2025 | 212 | 25 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 654360 | 01845 | 7.6 |  |  | Solar |  | 05_14_8L2 | 11/14/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | METHUEN | 426710 | 01844 | 15.2 |  |  | Solar |  | 05_01_24W2 | 04/27/2022 | 04/29/2022 | 2 | 0 | 2 | 05/02/2022 | 05/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2022 | Connected |  | N
National Grid | WORCESTER | 178324 | 01605 | 2000 |  |  | Solar |  | 05_01_412L2 | 03/29/2018 | 04/09/2018 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/12/2018 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 714916 | 01570 | 12.16 |  |  | Solar |  | 05_01_602W2 | 08/26/2025 | 09/16/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/26/2025 | 12/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTMINSTER | 644592 | 01473 | 10 |  |  | Solar |  | 05_05_108W60 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/18/2025 | Y | EXP | 365 | 08/22/2025 | 09/18/2025 | 28 | 0 | 28 |  |  | 10/18/2025 | Connected |  | N
National Grid | BELLINGHAM | 299813 | 02019 | 10 |  |  | Solar |  | 05_05_312W1 | 03/03/2021 | 07/08/2020 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2021 | Connected |  | N
National Grid | WESTBOROUGH | 413470 | 01581 | 15.2 |  |  | Solar |  | 05_12_51L3 | 08/16/2022 | 02/26/2022 | 2 | 0 | 2 | 08/19/2022 | 08/19/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 566878 | 01915 | 7.6 |  |  | Solar |  | 05_14_2L2 | 11/03/2023 | 11/27/2023 | 15 | 8 | 7 | 11/28/2023 | 11/28/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/03/2023 | 2/19/2025 | Y | EXP | 365 | 07/29/2024 | 10/08/2024 | 72 | 0 | 72 |  |  | 10/17/2024 | Connected |  | N
National Grid | LOWELL | 666605 | 01851 | 17.2 |  |  | Solar |  | 05_14_57L2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | WESTFORD | 684738 | 01886 | 5.76 |  |  | Solar |  | 05_14_71L1 | 04/11/2025 | 04/29/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | ANDOVER | 654711 | 01845 | 20 |  |  | Solar |  | 05_14_8L2 | 11/20/2024 | 11/25/2024 | 3 | 0 | 3 | 11/26/2024 | 11/26/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | LAWRENCE | 436749 | 01841 | 2.32 |  |  | Solar |  | 05_01_24W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 65 | 40 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 06/17/2022 | 12/26/2024 | Y | EXP | 365 | 06/26/2024 | 07/02/2024 | 7 | 0 | 7 |  |  | 8/9/2024 | Connected |  | N
National Grid | WORCESTER | 190782 | 01604 | 23.04 |  |  | Solar |  | 05_01_412L2 | 07/16/2018 | 08/29/2018 | 31 | 0 | 31 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 743484 | 01570 | 11.52 |  |  | Solar |  | 05_01_602W2 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WESTMINSTER | 651065 | 01473 | 6.175 |  |  | Solar |  | 05_05_108W60 | 10/31/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/31/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | BLACKSTONE | 328513 | 01504 | 0 |  |  | Solar |  | 05_05_312W1 | 11/27/2020 | 12/03/2020 | 3 | 0 | 3 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 8/26/2022 | N | EXP | 560 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | WESTBOROUGH | 484468 | 01581 | 0 |  |  | Solar |  | 05_12_51L3 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 583609 | 01982 | 6.67 |  |  | Solar |  | 05_14_2L2 | 04/09/2024 | 03/06/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 71 | 59 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 667168 | 01863 | 10 |  |  | Solar |  | 05_14_57L2 | 01/22/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2025 | Connected |  | N
National Grid | WESTFORD | 719515 | 01886 | 7.6 |  |  | Solar |  | 05_14_71L3 | 09/16/2025 | 10/02/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 656005 | 01843 | 10 |  |  | Solar |  | 05_14_8L2 | 11/21/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 11/21/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 534808 | 01841 | 15.2 |  |  | Solar |  | 05_01_24W2 | 06/19/2023 | 08/01/2023 | 30 | 26 | 4 | 08/02/2023 | 08/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | WORCESTER | 190340 | 01606 | 1500 |  |  | Solar |  | 05_01_412L2 | 08/16/2018 | 08/27/2018 | 3 | 0 | 3 |  |  | 53 | 19 | 34 |  |  | 0 | 0 | 0 | 09/13/2018 | 11/12/2018 | 42 | 8 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 174177 | 01570 | 11.4 |  |  | Solar |  | 05_01_602W2 | 03/06/2012 | 03/06/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2012 |  | 6/4/2012 | N | EXP | 0 |  |  | 0 | 0 | 0 | 6/4/2012 | 6/4/2012 | 7/16/2012 | Connected |  | N
National Grid | HUBBARDSTON | 660346 | 01452 | 10 |  |  | Solar |  | 05_05_108W60 | 12/12/2024 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | BLACKSTONE | 338021 | 01504 | 80 |  |  | Solar |  | 05_05_312W1 | 01/21/2021 | 01/26/2021 | 2 | 0 | 2 | 01/27/2021 | 01/27/2021 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 | 01/21/2021 | 12/31/2024 | Y | EXP | 386 | 08/26/2024 | 08/26/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WESTBOROUGH | 485207 | 01581 | 19 |  |  | Solar |  | 05_12_51L3 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | HAMILTON | 588923 | 01982 | 7.6 |  |  | Solar |  | 05_14_2L2 | 02/28/2024 | 03/05/2024 | 4 | 0 | 4 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 667573 | 01851 | 11.5 |  |  | Solar |  | 05_14_57L2 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 91 | 69 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | WESTFORD | 721298 | 01886 | 13.36 |  |  | Solar |  | 05_14_71L3 | 09/23/2025 | 10/06/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 656577 | 01843 | 5.76 |  |  | Solar |  | 05_14_8L2 | 11/25/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/25/2024 | 1/30/2026 | Y | EXP | 365 | 09/13/2025 | 09/12/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | METHUEN | 540716 | 01844 | 0 |  |  | Solar |  | 05_01_24W2 | 07/14/2023 | 07/19/2023 | 3 | 0 | 3 | 07/20/2023 | 07/20/2023 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 196422 | 01605 | 66.6 |  |  | Solar |  | 05_01_412L2 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  | 6/30/2020 | N | EXP | 602 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 174293 | 01570 | 2000 |  |  | Solar |  | 05_01_602W2 | 12/27/2011 | 12/27/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2012 | 12/27/2011 | 10/1/2012 | Y | STD | -66 | 01/24/2014 | 02/10/2014 | 11 | 0 | 11 | 11/8/2013 | 11/8/2013 | 12/9/2013 | Connected |  | N
National Grid | HUBBARDSTON | 661870 | 01452 | 5.76 |  |  | Solar |  | 05_05_108W60 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | BELLINGHAM | 343902 | 02019 | 7.6 |  |  | Solar |  | 05_05_312W1 | 02/25/2021 | 02/26/2021 | 0 | 0 | 0 | 03/01/2021 | 03/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2022 | Connected |  | N
National Grid | WESTBOROUGH | 517501 | 01581 | 0 |  |  | Solar |  | 05_12_51L3 | 04/06/2023 | 06/02/2023 | 39 | 38 | 1 | 06/05/2023 | 06/05/2023 | 289 | 271 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 | 04/06/2023 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 11/12/2024 | 41 | 0 | 41 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 620853 | 01982 | 5.76 |  |  | Solar |  | 05_14_2L2 | 06/26/2024 | 10/11/2024 | 54 | 50 | 4 | 10/15/2024 | 10/15/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 681569 | 01851 | 15.2 |  |  | Solar |  | 05_14_57L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 04/01/2025 | 5/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | WESTFORD | 176651 | 01886 | 524 |  |  | Solar |  | 05_14_71L3 | 02/17/2016 | 02/17/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2016 | 03/08/2016 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 657157 | 01843 | 5.76 |  |  | Solar |  | 05_14_8L2 | 11/26/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | LAWRENCE | 575704 | 01841 | 14.4 |  |  | Solar |  | 05_01_24W2 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 28 | 3 | 25 | 02/07/2024 | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 5/30/2025 | N | EXP | 365 | 06/08/2024 | 08/28/2024 | 82 | 0 | 82 |  |  | 10/2/2024 | Connected |  | N
National Grid | WORCESTER | 206984 | 01605 | 3.8 |  |  | Solar |  | 05_01_412L2 | 02/10/2019 | 02/19/2019 | 5 | 0 | 5 | 02/20/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N
National Grid | WEBSTER | 174382 | 01570 | 2.58 |  |  | Solar |  | 05_01_602W2 | 05/30/2012 | 05/30/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2012 |  | 8/15/2012 | N | EXP | -26 |  |  | 0 | 0 | 0 | 9/10/2012 | 9/10/2012 | 1/22/2013 | Connected |  | N
National Grid | WESTMINSTER | 674897 | 01473 | 7.6 |  |  | Solar |  | 05_05_108W60 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | BELLINGHAM | 356524 | 02019 | 9.86 |  |  | Solar |  | 05_05_312W1 | 05/06/2021 | 05/07/2021 | 1 | 1 | 0 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | WESTBOROUGH | 592675 | 01581 | 34.5 |  |  | Solar |  | 05_12_51L3 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | HAMILTON | 644511 | 01982 | 7.6 |  |  | Solar |  | 05_14_2L2 | 10/02/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LOWELL | 680865 | 01851 | 12.92 |  |  | Solar |  | 05_14_57L2 | 03/31/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | WESTFORD | 177662 | 01886 | 249 |  |  | Solar |  | 05_14_71L3 | 11/13/2017 | 11/13/2017 | 15 | 5 | 10 | 12/06/2017 | 12/06/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 |  | 12/2/2019 | N | EXP | 711 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | ANDOVER | 665462 | 01845 | 15.76 |  |  | Solar |  | 05_14_8L2 | 01/13/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 4/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | LAWRENCE | 576161 | 01841 | 10 |  |  | Solar |  | 05_01_24W2 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 44 | 19 | 25 | 05/22/2024 | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 6/11/2025 | N | EXP | 365 | 06/27/2024 | 07/10/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 207611 | 01606 | 500 |  |  | Solar |  | 05_01_412L2 | 03/14/2019 | 04/30/2019 | 33 | 26 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2019 | 06/03/2019 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 174549 | 01570 | 2800 |  |  | Solar |  | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 | 11/03/2011 | 4/1/2014 | Y | STD | 433 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 6/23/2014 | Connected |  | N
National Grid | WESTMINSTER | 461538 | 01473 | 490 |  |  | Solar |  | 05_05_115W42 | 02/08/2023 | 06/22/2023 | 92 | 81 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 01/08/2024 | 136 | 115 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 02/08/2023 | 8/17/2026 | Y | STD | 329 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BLACKSTONE | 384615 | 01504 | 200 |  |  | Solar |  | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 28 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 648934 | 01581 | 4.56 |  |  | Solar |  | 05_12_51L3 | 10/23/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | WENHAM | 649264 | 01984 | 5.76 |  |  | Solar |  | 05_14_2L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LOWELL | 688631 | 01851 | 12.92 |  |  | Solar |  | 05_14_57L2 | 05/01/2025 | 05/16/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | WESTFORD | 378789 | 01886 | 100 |  |  | Solar |  | 05_14_71L3 | 09/03/2021 | 10/06/2021 | 22 | 12 | 10 |  |  | 35 | 4 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 09/03/2021 | 7/9/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | ANDOVER | 681899 | 01845 | 7.6 |  |  | Solar |  | 05_14_8L2 | 04/01/2025 | 05/08/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 16 | 0 | 16 | 06/13/2025 | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | LAWRENCE | 587993 | 01841 | 3.77 |  |  | Solar |  | 05_01_24W2 | 04/16/2024 | 04/19/2024 | 3 | 1 | 2 | 04/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2024 | Connected |  | N
National Grid | WORCESTER | 226260 | 01606 | 150 |  |  | Solar |  | 05_01_412L2 | 05/08/2019 | 05/21/2019 | 7 | 0 | 7 | 05/22/2019 | 05/22/2019 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 174681 | 01570 | 30 |  |  | Solar |  | 05_01_602W2 | 01/08/2014 | 01/08/2014 | 2 | 0 | 2 | 01/13/2014 | 01/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2014 | 01/08/2014 | 6/20/2014 | Y | EXP | 142 |  |  | 0 | 0 | 0 | 1/29/2014 | 1/29/2014 | 6/24/2014 | Connected |  | N
National Grid | HUBBARDSTON | 666238 | 01452 | 120 |  |  | Solar |  | 05_05_115W42 | 02/03/2025 | 03/11/2025 | 26 | 16 | 10 | 03/12/2025 | 03/12/2025 | 25 | 0 | 25 | 05/20/2025 | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 4/8/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 384619 | 01504 | 400 |  |  | Solar |  | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 657644 | 01581 | 10 |  |  | Solar |  | 05_12_51L3 | 11/29/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/29/2024 | 2/19/2026 | Y | EXP | 365 | 06/14/2025 | 09/02/2025 | 81 | 0 | 81 |  |  | 9/11/2025 | Connected |  | N
National Grid | BEVERLY | 654955 | 01915 | 3.8 |  |  | Solar |  | 05_14_2L2 | 11/18/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LOWELL | 701934 | 01851 | 19 |  |  | Solar |  | 05_14_57L2 | 07/15/2025 | 07/28/2025 | 8 | 5 | 3 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | WESTFORD | 472543 | 01886 | 15.2 |  |  | Solar |  | 05_14_71L3 | 11/22/2022 | 11/28/2022 | 3 | 0 | 3 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | ANDOVER | 683910 | 01845 | 11.52 |  |  | Solar |  | 05_14_8L2 | 04/11/2025 | 05/21/2025 | 27 | 24 | 3 | 05/22/2025 | 05/22/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 595137 | 01841 | 8.7 |  |  | Solar |  | 05_01_24W2 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N
National Grid | WORCESTER | 293823 | 01606 | 8.88 |  |  | Solar |  | 05_01_412L2 | 05/28/2020 | 06/03/2020 | 3 | 0 | 3 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | WEBSTER | 174986 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 |  | 12/31/2012 | N | STD | -23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 728667 | 01452 | 5.76 |  |  | Solar |  | 05_05_115W42 | 10/27/2025 | 10/28/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 384617 | 01504 | 400 |  |  | Solar |  | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 671935 | 01581 | 4.537 |  |  | Solar |  | 05_12_51L3 | 02/13/2025 | 03/19/2025 | 5 | 0 | 5 | 03/20/2025 | 03/20/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | BEVERLY | 671209 | 01915 | 10 |  |  | Solar |  | 05_14_2L2 | 02/10/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LOWELL | 727574 | 01851 | 15.2 |  |  | Solar |  | 05_14_57L2 | 10/19/2025 | 10/22/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | WESTFORD | 492288 | 01886 | 3.8 |  |  | Solar |  | 05_14_71L3 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 33 | 14 | 19 | 04/18/2023 | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 5/1/2023 |  | 11/29/2024 | N | EXP | 365 | 08/09/2023 | 12/28/2023 | 142 | 3 | 139 |  |  | 1/5/2024 | Connected |  | N
National Grid | ANDOVER | 714702 | 01845 | 5.76 |  |  | Solar |  | 05_14_8L2 | 08/26/2025 | 10/01/2025 | 6 | 0 | 6 | 10/02/2025 | 10/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/26/2025 | 11/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 598070 | 01841 | 7.6 |  |  | Solar |  | 05_01_24W2 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/21/2024 | 4/11/2025 | Y | EXP | 365 | 06/13/2024 | 09/11/2024 | 91 | 0 | 91 |  |  | 9/17/2024 | Connected |  | N
National Grid | WORCESTER | 317070 | 01606 | 10 |  |  | Solar |  | 05_01_412L2 | 10/19/2020 | 11/03/2020 | 10 | 8 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 4/11/2022 | N | EXP | 480 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 175020 | 01570 | 150 |  |  | Solar |  | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 342 | 0 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 6/3/2013 | N | EXP | 21 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 174581 | 01452 | 190 |  |  | Solar |  | 05_05_115W42 | 10/18/2011 | 10/18/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2011 |  | 10/31/2012 | N | EXP | 314 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/11/2012 | Connected |  | Y
National Grid | FALL RIVER | 471366 | 02724 | 9.75 |  |  | Solar |  | 05_05_312W1 | 11/09/2022 | 11/21/2022 | 8 | 3 | 5 | 11/22/2022 | 11/22/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | WESTBOROUGH | 704327 | 01581 | 15.2 |  |  | Solar |  | 05_12_51L3 | 07/11/2025 | 07/15/2025 | 2 | 0 | 2 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | HAMILTON | 680319 | 01982 | 7.6 |  |  | Solar |  | 05_14_2L2 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | CHELMSFORD | 710654 | 01863 | 0 |  |  | Battery Add-On |  | 05_14_57L3 | 08/08/2025 | 08/11/2025 | 1 | 0 | 1 | 08/12/2025 | 08/12/2025 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 578593 | 01886 | 480 |  |  | Solar |  | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 174235 | 01845 | 725 |  |  | Solar |  | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 604247 | 01844 | 3.19 |  |  | Solar |  | 05_01_24W2 | 04/19/2024 | 04/24/2024 | 3 | 0 | 3 | 04/25/2024 | 04/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 325654 | 01606 | 10 |  |  | Solar |  | 05_01_412L2 | 11/12/2020 | 01/25/2021 | 50 | 48 | 2 | 01/26/2021 | 01/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2021 | Connected |  | N
National Grid | WEBSTER | 175019 | 01570 | 350 |  |  | Solar |  | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 919 | 0 | 919 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 12/31/2016 | N | EXP | 1328 |  |  | 0 | 0 | 0 |  |  | 9/10/2013 | Connected |  | N
National Grid | HUBBARDSTON | 175817 | 01452 | 150 |  |  | Solar |  | 05_05_115W42 | 07/28/2015 | 07/28/2015 | 2 | 2 | 0 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 |  | 8/3/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/7/2016 | 9/7/2016 | 9/7/2016 | Connected |  | N
National Grid | FALL RIVER | 501473 | 02724 | 15.2 |  |  | Solar |  | 05_05_312W1 | 02/13/2023 | 02/15/2023 | 2 | 1 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | WESTBOROUGH | 535949 | 01581 | 150 |  |  | Solar |  | 05_12_51T1 | 06/22/2023 | 12/07/2023 | 115 | 106 | 9 |  |  | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | BEVERLY | 671910 | 01915 | 150 |  |  | Solar |  | 05_14_2L3 | 02/25/2025 | 03/26/2025 | 22 | 12 | 10 |  |  | 47 | 22 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LOWELL | 712195 | 01851 | 3.8 |  |  | Solar |  | 05_14_57L3 | 08/14/2025 | 09/05/2025 | 25 | 23 | 2 | 10/23/2025 | 10/23/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 08/14/2025 | 11/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTFORD | 578504 | 01886 | 400 |  |  | Solar |  | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 174234 | 01845 | 500 |  |  | Solar |  | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 626022 | 01841 | 7.6 |  |  | Solar |  | 05_01_24W2 | 07/18/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  | 9/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | WORCESTER | 440022 | 01605 | 3.77 |  |  | Solar |  | 05_01_412L2 | 07/15/2022 | 08/12/2022 | 21 | 20 | 1 | 08/15/2022 | 08/15/2022 | 63 | 44 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 11/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N
National Grid | DUDLEY | 175067 | 01571 | 675 |  |  | Solar |  | 05_01_602W2 | 03/28/2013 | 03/28/2013 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 06/03/2013 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 | 03/28/2013 | 2/3/2014 | Y | STD | 94 | 10/09/2014 | 12/10/2014 | 41 | 0 | 41 | 12/23/2014 | 12/23/2014 | 12/23/2014 | Connected |  | N
National Grid | HUBBARDSTON | 176031 | 01452 | 450 |  |  | Solar |  | 05_05_115W42 | 06/18/2015 | 06/18/2015 | 34 | 34 | 0 | 08/07/2015 | 08/07/2015 | 308 | 0 | 308 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 1/30/2017 | N | EXP | 490 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 557462 | 02724 | 7.6 |  |  | Solar |  | 05_05_312W1 | 02/23/2024 | 10/03/2023 | 7 | 5 | 2 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 3/14/2025 | Y | EXP | 365 | 04/20/2024 | 05/20/2024 | 31 | 0 | 31 |  |  | 5/22/2024 | Connected |  | N
National Grid | WESTBOROUGH | 703493 | 01581 | 11.4 |  |  | Solar |  | 05_12_51T1 | 07/08/2025 | 07/11/2025 | 3 | 0 | 3 | 07/14/2025 | 07/14/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BEVERLY | 701420 | 01915 | 5.76 |  |  | Solar |  | 05_14_2L3 | 06/26/2025 | 07/31/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 27 | 11 | 16 | 09/22/2025 | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LOWELL | 717298 | 01851 | 15.2 |  |  | Solar |  | 05_14_57L3 | 09/21/2025 | 09/25/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | WESTFORD | 583602 | 01886 | 6.38 |  |  | Solar |  | 05_14_71L3 | 02/14/2024 | 02/15/2024 | 1 | 0 | 1 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175191 | 01845 | 45 |  |  | Solar |  | 05_14_8L3 | 11/22/2013 | 11/22/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 3/26/2014 | 3/26/2014 | 4/25/2014 | Connected |  | N
National Grid | LAWRENCE | 630081 | 01841 | 7.6 |  |  | Solar |  | 05_01_24W2 | 08/05/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | WORCESTER | 446153 | 01606 | 7.6 |  |  | Solar |  | 05_01_412L2 | 09/14/2022 | 10/11/2022 | 18 | 16 | 2 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/14/2022 | 3/27/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 175102 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 01/14/2013 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 11/02/2012 | 4/1/2014 | Y | STD | 319 | 03/21/2014 | 04/29/2014 | 26 | 0 | 26 | 6/13/2014 | 6/13/2014 | 6/13/2014 | Connected |  | N
National Grid | GARDNER | 176427 | 01440 | 10 |  |  | Solar |  | 05_05_115W42 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 02/03/2016 | 1/8/2018 | Y | EXP | 672 | 08/11/2017 | 09/06/2017 | 17 | 0 | 17 | 9/27/2017 | 9/27/2017 | 9/29/2017 | Connected |  | N
National Grid | FALL RIVER | 573239 | 02724 | 500 |  |  | Solar |  | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 710223 | 01581 | 240 |  |  | Solar |  | 05_12_51T1 | 08/26/2025 | 10/13/2025 | 31 | 27 | 4 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 175901 | 01982 | 224 |  |  | Solar |  | 05_14_2L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/18/2016 | Connected |  | N
National Grid | LOWELL | 725537 | 01851 | 7.6 |  |  | Solar |  | 05_14_57L3 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TYNGSBORO | 611670 | 01879 | 3.8 |  |  | Solar |  | 05_14_71L3 | 05/16/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 05/16/2024 | 9/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y
National Grid | ANDOVER | 723449 | 01845 | 150 |  |  | Solar |  | 05_14_8T1 | 10/30/2025 | 12/08/2025 | 24 | 20 | 4 | 12/09/2025 | 12/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 639285 | 01843 | 7.6 |  |  | Solar |  | 05_01_24W2 | 09/11/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | WORCESTER | 458959 | 01606 | 3.8 |  |  | Solar |  | 05_01_412L2 | 11/02/2022 | 11/04/2022 | 3 | 1 | 2 | 11/07/2022 | 11/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 4/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | WEBSTER | 175302 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 176919 | 01440 | 6 |  |  | Solar |  | 05_05_115W42 | 05/05/2016 | 05/05/2016 | 4 | 4 | 0 | 05/12/2016 | 05/12/2016 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/11/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 573242 | 02724 | 500 |  |  | Solar |  | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 720734 | 01581 | 12.564 |  |  | Solar |  | 05_12_51T1 | 09/22/2025 | 10/24/2025 | 13 | 12 | 1 | 12/02/2025 | 12/02/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BEVERLY | 176474 | 01915 | 21.8 |  |  | Solar |  | 05_14_2L3 | 03/23/2016 | 03/23/2016 | 3 | 3 | 0 | 03/29/2016 | 03/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 3/29/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | LOWELL | 174461 | 01851 | 34.2 |  |  | Solar |  | 05_14_57L3 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | EXP | -42 |  |  | 0 | 0 | 0 | 1/10/2013 | 1/10/2013 | 1/25/2013 | Connected |  | N
National Grid | WESTFORD | 664589 | 01886 | 3.8 |  |  | Solar |  | 05_14_71L3 | 01/08/2025 | 03/19/2025 | 17 | 14 | 3 | 03/20/2025 | 03/20/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 | 01/08/2025 | 6/27/2026 | Y | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  | 12/3/2025 | Connected |  | N
National Grid | ANDOVER | 174755 | 01845 | 495 |  |  | Solar |  | 05_14_8T1 | 02/05/2014 | 02/05/2014 | 5 | 0 | 5 | 02/13/2014 | 02/13/2014 | 0 | 0 | 0 | 11/04/2014 | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2014 |  | 6/30/2014 | N | EXP | 111 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 10/2/2014 | Connected |  | N
National Grid | LAWRENCE | 640951 | 01843 | 10 |  |  | Solar |  | 05_01_24W2 | 09/17/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 25 | 0 | 25 | 02/03/2025 | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/14/2026 | N | EXP | 365 | 05/28/2025 | 06/25/2025 | 29 | 0 | 29 |  |  | 7/16/2025 | Connected |  | N
National Grid | WORCESTER | 482139 | 01605 | 0 |  |  | Battery Add-On |  | 05_01_412L2 | 12/02/2022 | 12/06/2022 | 2 | 0 | 2 | 12/07/2022 | 12/07/2022 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 175301 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 178444 | 01452 | 7.6 |  |  | Solar |  | 05_05_115W42 | 04/03/2018 | 04/03/2018 | 8 | 0 | 8 | 04/27/2018 | 04/27/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 |  | 4/9/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 11/20/2018 | Connected |  | N
National Grid | FALL RIVER | 573957 | 02724 | 0 |  |  | Battery Add-On |  | 05_05_312W1 | 11/28/2023 | 12/28/2023 | 21 | 20 | 1 | 12/29/2023 | 12/29/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | WESTBOROUGH | 724900 | 01581 | 9.5 |  |  | Solar |  | 05_12_51T1 | 10/08/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 176504 | 01930 | 150 |  |  | Solar |  | 05_14_2L3 | 02/09/2016 | 02/09/2016 | 7 | 7 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 2/15/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 12/7/2016 | 12/7/2016 | 11/23/2016 | Connected |  | N
National Grid | LOWELL | 175011 | 01854 | 235 |  |  | Solar |  | 05_14_57L3 | 08/31/2011 | 08/31/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2011 | 08/31/2011 | 11/30/2012 | Y | EXP | 338 | 01/09/2012 | 01/09/2012 | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 5/11/2012 | Connected |  | N
National Grid | WESTFORD | 691644 | 01886 | 20 |  |  | Solar |  | 05_14_71L3 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175373 | 01845 | 494 |  |  | Solar |  | 05_14_8T1 | 02/14/2014 | 02/14/2014 | 7 | 1 | 6 | 02/27/2014 | 02/27/2014 | 0 | 0 | 0 | 03/25/2014 | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/29/2014 | 02/14/2014 | 12/31/2016 | Y | EXP | 886 | 08/13/2015 | 12/23/2015 | 90 | 0 | 90 | 2/19/2015 | 2/19/2015 | 12/21/2015 | Connected |  | N
National Grid | LAWRENCE | 645210 | 01843 | 7.6 |  |  | Solar |  | 05_01_24W2 | 10/04/2024 | 11/04/2024 | 8 | 4 | 4 | 11/05/2024 | 11/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 516396 | 01605 | 12.76 |  |  | Solar |  | 05_01_412L2 | 08/17/2023 | 09/07/2023 | 15 | 14 | 1 | 09/08/2023 | 09/08/2023 | 24 | 0 | 24 | 11/22/2023 | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 2/19/2025 | N | EXP | 365 | 04/13/2024 | 05/28/2024 | 46 | 0 | 46 |  |  | 5/30/2024 | Connected |  | N
National Grid | WEBSTER | 175300 | 01570 | 4875 |  |  | Solar |  | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 6/7/2021 | Y | STD | 1373 | 10/28/2020 | 03/26/2021 | 149 | 0 | 149 |  |  | 6/4/2021 | Connected |  | N
National Grid | GARDNER | 194988 | 01440 | 7.6 |  |  | Solar |  | 05_05_115W42 | 09/04/2018 | 10/29/2018 | 19 | 19 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 591712 | 02724 | 8.96 |  |  | Solar |  | 05_05_312W1 | 02/27/2024 | 03/01/2024 | 3 | 1 | 2 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | WESTBOROUGH | 737553 | 01581 | 5.76 |  |  | Solar |  | 05_12_51T1 | 12/02/2025 | 12/03/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GLOUCESTER | 176741 | 01930 | 150 |  |  | Solar |  | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 4 | 0 | 11/06/2015 | 11/06/2015 | 424 | 56 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 9/7/2017 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175226 | 01851 | 12 |  |  | Solar |  | 05_14_57L3 | 01/06/2015 | 01/06/2015 | 8 | 4 | 4 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 6/6/2016 | Connected |  | N
National Grid | WESTFORD | 686461 | 01886 | 7.68 |  |  | Solar |  | 05_14_73L1 | 05/01/2025 | 05/14/2025 | 9 | 6 | 3 | 05/15/2025 | 05/15/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 176839 | 01845 | 50 |  |  | Solar |  | 05_14_8T1 | 04/29/2016 | 04/29/2016 | 3 | 3 | 0 | 05/04/2016 | 05/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2016 |  | 5/4/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/13/2016 | 10/13/2016 | 11/3/2016 | Connected |  | N
National Grid | ANDOVER | 652585 | 01810 | 9.074 |  |  | Solar |  | 05_01_24W2 | 11/06/2024 | 11/25/2024 | 3 | 1 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | WORCESTER | 517386 | 01605 | 3 |  |  | Solar |  | 05_01_412L2 | 05/17/2023 | 06/12/2023 | 18 | 18 | 0 | 06/13/2023 | 06/13/2023 | 20 | 0 | 20 | 08/09/2023 | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 9/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 175333 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 209761 | 01473 | 7.04 |  |  | Solar |  | 05_05_115W42 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 | 03/20/2019 | 4/10/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | FALL RIVER | 596048 | 02724 | 15.2 |  |  | Solar |  | 05_05_312W1 | 03/12/2024 | 03/18/2024 | 4 | 0 | 4 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WESTBOROUGH | 162552 | 01581 | 10 |  |  | Solar |  | 05_12_51T1 | 10/12/2017 | 10/12/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 176838 | 01915 | 150 |  |  | Solar |  | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 312 | 56 | 256 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 | 10/30/2015 | 11/7/2016 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 175693 | 01863 | 18 |  |  | Solar |  | 05_14_57L3 | 05/23/2014 | 05/23/2014 | 5 | 0 | 5 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2014 |  | 8/29/2014 | N | EXP | 58 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/13/2014 | Connected |  | N
National Grid | WESTFORD | 174466 | 01886 | 36 |  |  | Solar |  | 05_14_73L1 | 07/29/2011 | 07/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 | 1/9/2013 | Connected |  | N
National Grid | ANDOVER | 177266 | 01845 | 143 |  |  | Solar |  | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 4/7/2017 | 4/7/2017 | 3/30/2017 | Connected |  | N
National Grid | ANDOVER | 657142 | 01810 | 7.6 |  |  | Solar |  | 05_01_24W2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 11/26/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WORCESTER | 521145 | 01605 | 0 |  |  | Solar |  | 05_01_412L2 | 07/19/2023 | 07/20/2023 | 2 | 1 | 1 | 07/21/2023 | 07/21/2023 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | WEBSTER | 175332 | 01570 | 1000 |  |  | Solar |  | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 1079 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 376028 | 01473 | 3.8 |  |  | Solar |  | 05_05_115W42 | 08/25/2021 | 08/27/2021 | 2 | 0 | 2 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 | 08/25/2021 | 1/24/2023 | Y | EXP | 365 | 12/02/2021 | 01/12/2022 | 42 | 0 | 42 |  |  | 2/7/2022 | Connected |  | Y
National Grid | FALL RIVER | 614675 | 02724 | 6 |  |  | Solar |  | 05_05_312W1 | 05/31/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/31/2024 | 8/12/2025 | Y | EXP | 365 | 08/22/2024 | 09/10/2024 | 20 | 0 | 20 |  |  | 11/9/2024 | Connected |  | N
National Grid | WESTBOROUGH | 174679 | 01581 | 45 |  |  | Solar |  | 05_12_51T1 | 01/06/2014 | 01/06/2014 | 5 | 0 | 5 | 01/14/2014 | 01/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2014 |  | 3/31/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 2/21/2014 | 2/21/2014 | 4/25/2014 | Connected |  | N
National Grid | MANCHESTER | 178013 | 01944 | 150 |  |  | Solar |  | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 7/4/2018 | N | EXP | 882 |  |  | 0 | 0 | 0 | 7/18/2017 | 7/18/2017 | 7/16/2017 | Connected |  | N
National Grid | LOWELL | 177025 | 01854 | 86.4 |  |  | Solar |  | 05_14_57L3 | 03/16/2017 | 03/16/2017 | 6 | 5 | 1 | 03/24/2017 | 03/24/2017 | 229 | 0 | 229 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2017 |  | 3/21/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 174750 | 01886 | 225 |  |  | Solar |  | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 2 | 566 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2013 | 07/09/2013 | 9/30/2014 | Y | EXP | 391 | 07/23/2014 | 11/18/2015 | 329 | 0 | 329 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177265 | 01845 | 161 |  |  | Solar |  | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N
National Grid | ANDOVER | 667809 | 01810 | 480 |  |  | Solar |  | 05_01_24W2 | 09/16/2025 |  | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 520273 | 01605 | 14.79 |  |  | Solar |  | 05_01_412L2 | 04/20/2023 | 04/24/2023 | 3 | 2 | 1 | 04/25/2023 | 04/25/2023 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | WEBSTER | 175367 | 01570 | 960 |  |  | Solar |  | 05_01_602W2 | 11/17/2014 | 11/17/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/17/2014 | 3/31/2017 | Y | STD | 73 | 03/29/2017 | 03/27/2017 | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | WESTMINSTER | 387941 | 01473 | 3 |  |  | Solar |  | 05_05_115W42 | 10/21/2021 | 12/21/2021 | 9 | 4 | 5 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/21/2021 | 5/25/2024 | Y | EXP | 365 | 01/26/2023 | 05/15/2023 | 110 | 0 | 110 |  |  | 7/11/2023 | Connected |  | N
National Grid | FALL RIVER | 654529 | 02724 | 7.6 |  |  | Solar |  | 05_05_312W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | WESTBOROUGH | 175028 | 01581 | 800 |  |  | Solar |  | 05_12_51T1 | 03/20/2013 | 03/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2013 | 05/15/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2013 |  | 6/30/2014 | N | STD | 411 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/27/2013 | 12/30/2013 | Connected |  | N
National Grid | GLOUCESTER | 178705 | 01930 | 249.8 |  |  | Solar |  | 05_14_2L3 | 03/21/2018 | 03/21/2018 | 11 | 0 | 11 | 04/05/2018 | 04/05/2018 | 38 | 13 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 3/31/2021 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | LOWELL | 198756 | 01851 | 174 |  |  | Solar |  | 05_14_57L3 | 11/06/2018 | 11/27/2018 | 0 | 0 | 0 | 11/28/2018 | 11/28/2018 | 11 | 0 | 11 | 04/15/2019 | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 6/14/2019 |  | 10/15/2020 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 174749 | 01886 | 295 |  |  | Solar |  | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 16 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2013 |  | 9/1/2014 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 195724 | 01886 | 400 |  |  | Natural Gas |  | 05_14_8T1 | 02/28/2019 | 07/02/2019 | 302 | 26 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 720253 | 01810 | 3.8 |  |  | Solar |  | 05_01_24W2 | 09/18/2025 | 09/30/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 545472 | 01605 | 5.8 |  |  | Solar |  | 05_01_412L2 | 08/08/2023 | 08/28/2023 | 15 | 14 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/08/2023 | 10/11/2024 | Y | EXP | 365 | 01/16/2024 | 02/08/2024 | 24 | 0 | 24 |  |  | 2/22/2024 | Connected |  | N
National Grid | DUDLEY | 175378 | 01570 | 278.4 |  |  | Solar |  | 05_01_602W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2014 |  | 11/28/2014 | N | EXP | 121 |  |  | 0 | 0 | 0 | 10/16/2014 | 10/16/2014 | 12/31/2014 | Connected |  | N
National Grid | WESTMINSTER | 422789 | 01473 | 3.8 |  |  | Solar |  | 05_05_115W42 | 04/07/2022 | 08/04/2022 | 2 | 0 | 2 | 08/05/2022 | 08/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 660757 | 02724 | 8.45 |  |  | Solar |  | 05_05_312W1 | 12/31/2024 | 01/15/2025 | 7 | 1 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/31/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 8/14/2025 | Connected |  | N
National Grid | WESTBOROUGH | 175161 | 01581 | 75 |  |  | Solar |  | 05_12_51T1 | 07/21/2011 | 07/21/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ESSEX | 184041 | 01929 | 73.3 |  |  | Solar |  | 05_14_2L3 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/27/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 1/8/2019 | Connected |  | N
National Grid | LOWELL | 232316 | 01851 | 249 |  |  | Solar |  | 05_14_57L3 | 11/19/2019 | 01/09/2020 | 19 | 15 | 4 | 04/02/2020 | 04/02/2020 | 16 | 0 | 16 | 05/21/2020 | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 |  | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 174746 | 01886 | 225 |  |  | Solar |  | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 9/1/2014 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 690411 | 01824 | 7.6 |  |  | Solar |  | 05_01_24W3 | 05/07/2025 | 05/21/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 | 05/07/2025 | 8/18/2026 | Y | EXP | 365 | 11/07/2025 |  | 56 | 0 | 56 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 547164 | 01810 | 3.8 |  |  | Solar |  | 05_01_412L2 | 09/13/2023 | 09/20/2023 | 5 | 2 | 3 | 09/21/2023 | 09/21/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | WORCESTER | 175403 | 01606 | 960 |  |  | Solar |  | 05_01_602W2 | 11/21/2014 | 11/21/2014 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/21/2014 | 4/10/2017 | Y | STD | 83 | 02/10/2017 | 09/05/2017 | 142 | 0 | 142 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | WEBSTER | 445797 | 01570 | 6 |  |  | Solar |  | 05_05_115W42 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2022 |  | 9/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y
National Grid | WESTMINSTER | 676389 | 01473 | 5.76 |  |  | Solar |  | 05_05_312W1 | 03/07/2025 | 03/27/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 175487 | 02724 | 495 |  |  | Solar |  | 05_12_51T1 | 07/22/2014 | 07/22/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 554 | 2 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2014 |  | 1/20/2016 | N | EXP | 510 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 381753 | 01581 | 10 |  |  | Solar |  | 05_14_2L3 | 10/11/2021 | 12/07/2021 | 3 | 1 | 2 | 10/18/2021 | 10/18/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | Y
National Grid | BEVERLY | 243897 | 01915 | 0 |  |  | Solar |  | 05_14_57L3 | 07/17/2019 | 08/07/2019 | 14 | 9 | 5 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | LOWELL | 175222 | 01851 | 225 |  |  | Solar |  | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/11/2015 | 04/06/2015 | 17 | 0 | 17 | 5/13/2015 | 5/13/2015 | 6/1/2015 | Connected |  | N
National Grid | WESTFORD | 391856 | 01886 | 0 |  |  | Other |  | 05_14_8T1 | 01/04/2022 | 01/26/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 716020 | 01824 | 11.5 |  |  | Solar |  | 05_01_24W3 | 09/28/2025 | 10/06/2025 | 5 | 1 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 549203 | 01810 | 12 |  |  | Solar |  | 05_01_412L2 | 09/05/2023 | 11/14/2023 | 49 | 46 | 3 | 11/15/2023 | 11/15/2023 | 68 | 36 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175417 | 01606 | 16 |  |  | Solar |  | 05_01_602W2 | 07/10/2014 | 07/10/2014 | 7 | 0 | 7 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2014 |  | 9/30/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 8/12/2014 | 8/12/2014 | 10/14/2014 | Connected |  | N
National Grid | WEBSTER | 480673 | 01570 | 6 |  |  | Solar |  | 05_05_115W42 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | HUBBARDSTON | 419359 | 01452 | 499 |  |  | Solar |  | 05_05_312W2 | 05/26/2022 | 06/14/2022 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/15/2022 | 07/18/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 05/26/2022 | 5/14/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 175656 | 02724 | 17.6 |  |  | Solar |  | 05_12_51T1 | 05/13/2014 | 05/13/2014 | 6 | 0 | 6 | 05/22/2014 | 05/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2014 |  | 9/30/2014 | N | EXP | 99 |  |  | 0 | 0 | 0 | 7/22/2014 | 7/22/2014 | 9/2/2014 | Connected |  | N
National Grid | WESTBOROUGH | 406001 | 01581 | 0 |  |  | Battery Add-On |  | 05_14_2L3 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/25/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 242048 | 01915 | 16 |  |  | Solar |  | 05_14_57L3 | 07/09/2019 | 07/23/2019 | 9 | 9 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/11/2019 | N | EXP | 98 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | LOWELL | 175757 | 01851 | 295 |  |  | Solar |  | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/10/2015 | 04/28/2015 | 33 | 0 | 33 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | WESTFORD | 412234 | 01886 | 0 |  |  | Battery Add-On |  | 05_14_8T1 | 04/26/2022 | 05/27/2022 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/24/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 175256 | 01824 | 56 |  |  | Solar |  | 05_01_24W3 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/17/2015 | Connected |  | N
National Grid | ANDOVER | 551576 | 01810 | 4.64 |  |  | Solar |  | 05_01_412L2 | 09/19/2023 | 09/22/2023 | 3 | 0 | 3 | 09/25/2023 | 09/25/2023 | 20 | 0 | 20 | 11/13/2023 | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 |  | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/18/2025 | N | EXP | 365 | 04/13/2024 | 05/22/2024 | 40 | 0 | 40 |  |  | 6/10/2024 | Connected |  | N
National Grid | WORCESTER | 176044 | 01606 | 630 |  |  | Solar |  | 05_01_602W2 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 480438 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2023 | Connected |  | N
National Grid | GARDNER | 561576 | 01440 | 1980 |  |  | Solar |  | 05_05_312W2 | 05/15/2024 | 06/13/2024 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2024 | 07/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 175911 | 02724 | 20 |  |  | Solar |  | 05_12_51T1 | 03/11/2015 | 03/11/2015 | 11 | 8 | 3 | 03/30/2015 | 03/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 |  | 7/31/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 7/10/2015 | Connected |  | N
National Grid | WESTBOROUGH | 461779 | 01581 | 0 |  |  | Solar |  | 05_14_2L3 | 09/29/2022 | 09/30/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 1/13/2024 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | GLOUCESTER | 248827 | 01930 | 0 |  |  | Solar |  | 05_14_57L3 | 08/14/2019 | 08/19/2019 | 3 | 3 | 0 | 08/20/2019 | 08/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2019 |  | 9/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2020 | Connected |  | N
National Grid | LOWELL | 175756 | 01851 | 225 |  |  | Solar |  | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 108 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 6/2/2015 | 6/2/2015 | 7/13/2015 | Connected |  | N
National Grid | WESTFORD | 174280 | 01886 | 600 |  |  | Solar |  | 05_14_8T2 | 12/30/2011 | 12/30/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 12/30/2011 | 6/1/2012 | Y | EXP | -194 | 11/16/2012 | 02/26/2013 | 62 | 0 | 62 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N
National Grid | CHELMSFORD | 175457 | 01824 | 56 |  |  | Solar |  | 05_01_24W3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2014 |  | 11/28/2014 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 1/21/2016 | Connected |  | N
National Grid | ANDOVER | 613403 | 01810 | 6.67 |  |  | Solar |  | 05_01_412L2 | 05/28/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 7/1/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176043 | 01606 | 1000 |  |  | Solar |  | 05_01_602W2 | 08/14/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 08/14/2015 | 2/24/2020 | Y | STD | 1225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 482372 | 01570 | 3 |  |  | Solar |  | 05_05_115W42 | 12/05/2022 | 12/19/2022 | 10 | 5 | 5 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | Y
National Grid | HUBBARDSTON | 590683 | 01452 | 499 |  |  | Solar |  | 05_05_312W2 | 07/08/2024 | 08/26/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 10/03/2024 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | FALL RIVER | 176156 | 02724 | 21.4 |  |  | Solar |  | 05_12_51T1 | 02/03/2015 | 02/03/2015 | 6 | 3 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2015 | 02/03/2015 | 7/19/2016 | Y | EXP | 505 | 05/18/2016 | 10/17/2017 | 353 | 0 | 353 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Connected |  | N
National Grid | WESTBOROUGH | 505742 | 01581 | 3.8 |  |  | Solar |  | 05_14_2L3 | 03/15/2023 | 03/20/2023 | 3 | 0 | 3 | 03/21/2023 | 03/21/2023 | 22 | 1 | 21 | 04/26/2023 | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/18/2023 |  | 9/28/2024 | N | EXP | 365 | 07/29/2023 | 09/28/2023 | 62 | 0 | 62 |  |  | 10/13/2023 | Connected |  | Y
National Grid | MANCHESTER | 263166 | 01944 | 10 |  |  | Solar |  | 05_14_57L3 | 10/31/2019 | 11/01/2019 | 1 | 1 | 0 | 11/04/2019 | 11/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N
National Grid | LOWELL | 176727 | 01851 | 10 |  |  | Solar |  | 05_14_73L1 | 02/23/2016 | 02/23/2016 | 3 | 3 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/23/2016 | 8/28/2017 | Y | EXP | 511 | 07/11/2017 | 07/31/2017 | 14 | 0 | 14 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N
National Grid | TYNGSBORO | 177246 | 01879 | 1139 |  |  | Solar |  | 05_14_8T2 | 06/13/2016 | 06/13/2016 | 62 | 62 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2016 | 10/18/2016 | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2017 | 06/13/2016 | 8/6/2018 | Y | STD | 517 | 02/23/2018 | 08/03/2018 | 126 | 0 | 126 | 6/26/2018 | 7/10/2018 | 8/6/2018 | Connected |  | N
National Grid | CHELMSFORD | 175679 | 01824 | 30 |  |  | Solar |  | 05_01_24W3 | 12/18/2014 | 12/18/2014 | 6 | 1 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2015 |  | 2/28/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 6/1/2015 | Connected |  | N
National Grid | ANDOVER | 613016 | 01810 | 6 |  |  | Solar |  | 05_01_412L2 | 05/23/2024 | 06/11/2024 | 9 | 5 | 4 | 06/12/2024 | 06/12/2024 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 05/23/2024 | 1/26/2026 | Y | EXP | 365 | 09/04/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 3/26/2025 | Connected |  | N
National Grid | WORCESTER | 176306 | 01606 | 15.2 |  |  | Solar |  | 05_01_602W2 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 | 03/04/2015 | 03/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2015 |  | 7/31/2015 | N | EXP | 148 |  |  | 0 | 0 | 0 | 5/12/2017 | 5/12/2017 | 5/12/2017 | Connected |  | N
National Grid | WEBSTER | 482174 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 12/20/2022 | 12/26/2022 | 4 | 0 | 4 | 12/27/2022 | 12/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | HUBBARDSTON | 602516 | 01452 | 999 |  |  | Solar |  | 05_05_312W2 | 05/09/2024 | 08/01/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/12/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | FALL RIVER | 176185 | 02724 | 112 |  |  | Solar |  | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 | 08/28/2015 | 9/6/2016 | Y | EXP | 362 | 12/19/2016 | 02/24/2017 | 45 | 0 | 45 | 4/20/2017 | 4/20/2017 | 4/14/2017 | Connected |  | N
National Grid | WESTBOROUGH | 553845 | 01581 | 7.54 |  |  | Solar |  | 05_14_2L3 | 09/07/2023 | 12/07/2023 | 63 | 46 | 17 | 12/08/2023 | 12/08/2023 | 36 | 13 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2024 | Connected |  | N
National Grid | GLOUCESTER | 297374 | 01930 | 0 |  |  | Solar |  | 05_14_57L3 | 06/19/2020 | 06/22/2020 | 0 | 0 | 0 | 06/23/2020 | 06/23/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | LOWELL | 177572 | 01851 | 7.6 |  |  | Solar |  | 05_14_73L1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 244642 | 01879 | 200 |  |  | Solar |  | 05_14_8T2 | 07/25/2019 | 08/08/2019 | 7 | 3 | 4 | 08/09/2019 | 08/09/2019 | 15 | 3 | 12 | 10/07/2019 | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 175904 | 01824 | 10 |  |  | Solar |  | 05_01_24W3 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2015 |  | 10/6/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/13/2015 | 10/13/2015 | 1/26/2016 | Connected |  | N
National Grid | ANDOVER | 636521 | 01810 | 3.8 |  |  | Solar |  | 05_01_412L2 | 08/29/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | WORCESTER | 176398 | 01606 | 10 |  |  | Solar |  | 05_01_602W2 | 03/10/2016 | 03/10/2016 | 1 | 1 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/16/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 | 6/13/2016 | Connected |  | N
National Grid | WEBSTER | 484096 | 01570 | 10 |  |  | Solar |  | 05_05_115W42 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N
National Grid | WESTMINSTER | 174332 | 01473 | 300 |  |  | Solar |  | 05_05_312W2 | 01/18/2012 | 01/18/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2012 | 01/18/2012 | 7/1/2012 | Y | EXP | -59 | 09/25/2012 | 11/29/2012 | 29 | 0 | 29 | 1/22/2013 | 1/22/2013 | 2/6/2013 | Connected |  | N
National Grid | FALL RIVER | 176170 | 02724 | 2.75 |  |  | Solar |  | 05_12_51T1 | 04/22/2015 | 04/22/2015 | 1 | 1 | 0 | 04/24/2015 | 04/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2015 |  | 9/30/2015 | N | EXP | 142 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 9/24/2015 | Connected |  | N
National Grid | WESTBOROUGH | 553547 | 01581 | 3.8 |  |  | Solar |  | 05_14_2L3 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 297469 | 01930 | 15.2 |  |  | Solar |  | 05_14_57L3 | 06/30/2020 | 07/06/2020 | 3 | 0 | 3 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2020 | Connected |  | N
National Grid | LOWELL | 295384 | 01851 | 10 |  |  | Solar |  | 05_14_73L1 | 06/08/2020 | 06/15/2020 | 4 | 4 | 0 | 06/16/2020 | 06/16/2020 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUNSTABLE | 356820 | 01827 | 150 |  |  | Solar |  | 05_14_8T2 | 05/10/2021 | 06/07/2021 | 18 | 10 | 8 | 06/08/2021 | 06/08/2021 | 60 | 36 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 176013 | 01824 | 17.6 |  |  | Solar |  | 05_01_24W3 | 01/23/2015 | 01/23/2015 | 8 | 6 | 2 | 02/05/2015 | 02/05/2015 | 175 | 0 | 175 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 2/24/2015 | 2/24/2015 |  | Withdrawn |  | N
National Grid | LAWRENCE | 636496 | 01843 | 10 |  |  | Solar |  | 05_01_412L2 | 08/29/2024 | 10/28/2024 | 28 | 25 | 3 | 10/29/2024 | 10/29/2024 | 175 | 160 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176879 | 01606 | 266.4 |  |  | Solar |  | 05_01_602W2 | 05/04/2016 | 05/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2016 | 06/28/2016 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 05/04/2016 | 12/29/2017 | Y | STD | 373 | 05/01/2017 | 10/04/2017 | 109 | 0 | 109 | 1/11/2018 | 1/11/2018 | 12/11/2017 | Connected |  | N
National Grid | WEBSTER | 486948 | 01570 | 3 |  |  | Solar |  | 05_05_115W42 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 175072 | 01473 | 95 |  |  | Solar |  | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 5/31/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 | 4/16/2013 | Connected |  | N
National Grid | FALL RIVER | 176167 | 02724 | 150 |  |  | Solar |  | 05_12_51T1 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 |  | 9/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/19/2015 | 6/19/2015 | 11/6/2015 | Connected |  | N
National Grid | WESTBOROUGH | 606324 | 01581 | 3.77 |  |  | Solar |  | 05_14_2L3 | 04/24/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 7/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | BEVERLY | 299279 | 01915 | 10 |  |  | Solar |  | 05_14_57L3 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | LOWELL | 298402 | 01851 | 4.64 |  |  | Solar |  | 05_14_73L1 | 07/14/2020 | 07/15/2020 | 0 | 0 | 0 | 07/16/2020 | 07/16/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N
National Grid | WESTFORD | 359565 | 01886 | 466.6 |  |  | Solar |  | 05_14_8T2 | 07/09/2021 | 07/23/2021 | 9 | 3 | 6 | 07/26/2021 | 07/26/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2021 |  | 3/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2022 | Connected |  | N
National Grid | CHELMSFORD | 176730 | 01863 | 6 |  |  | Solar |  | 05_01_24W3 | 04/25/2016 | 04/25/2016 | 2 | 2 | 0 | 04/28/2016 | 04/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2016 | 04/25/2016 | 5/1/2017 | Y | EXP | 355 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | LAWRENCE | 650945 | 01843 | 3.8 |  |  | Solar |  | 05_01_412L2 | 11/12/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/12/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WORCESTER | 178594 | 01606 | 19 |  |  | Solar |  | 05_05_335W1 | 03/14/2018 | 03/14/2018 | 9 | 9 | 0 | 03/30/2018 | 03/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2018 |  | 3/20/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 500885 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 03/10/2023 | 03/20/2023 | 6 | 0 | 6 | 03/21/2023 | 03/21/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | HUBBARDSTON | 175174 | 01452 | 95 |  |  | Solar |  | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 74 | 3 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 2/28/2013 | N | EXP | -14 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176197 | 02724 | 900 |  |  | Solar |  | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 645283 | 01581 | 5.76 |  |  | Solar |  | 05_14_2L3 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 | 01/15/2025 | 02/11/2025 | 28 | 0 | 28 |  |  | 2/21/2025 | Connected |  | N
National Grid | GLOUCESTER | 329231 | 01930 | 7.6 |  |  | Solar |  | 05_14_57L3 | 12/03/2020 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 303103 | 01851 | 200 |  |  | Solar |  | 05_14_73L1 | 08/13/2020 | 01/10/2022 | 23 | 12 | 11 | 09/17/2020 | 09/17/2020 | 83 | 60 | 23 | 01/27/2021 | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 4/6/2021 | 08/13/2020 | 8/25/2025 | Y | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 430644 | 01879 | 0 |  |  | Battery Add-On |  | 05_14_8T2 | 08/23/2022 | 09/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/07/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 176780 | 01863 | 7.6 |  |  | Solar |  | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 |  | 11/10/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/25/2015 | 5/25/2016 | Connected |  | N
National Grid | LAWRENCE | 651603 | 01843 | 10 |  |  | Solar |  | 05_01_412L2 | 11/12/2024 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 11/12/2024 | 3/17/2026 | Y | EXP | 365 | 06/12/2025 | 12/01/2025 | 173 | 0 | 173 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 185872 | 01606 | 1000 |  |  | Solar |  | 05_05_335W1 | 07/19/2018 | 07/19/2018 | 15 | 14 | 1 |  |  | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 07/19/2018 | 11/23/2021 | Y | STD | 148 | 11/01/2019 | 07/02/2021 | 609 | 362 | 247 |  |  | 10/22/2021 | Connected |  | N
National Grid | WEBSTER | 504881 | 01570 | 6 |  |  | Solar |  | 05_05_115W42 | 03/09/2023 | 03/13/2023 | 2 | 0 | 2 | 03/14/2023 | 03/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2023 | 03/09/2023 | 7/13/2024 | Y | EXP | 365 | 06/20/2023 | 07/13/2023 | 24 | 0 | 24 |  |  | 8/23/2023 | Connected |  | N
National Grid | WESTMINSTER | 175204 | 01473 | 1800 |  |  | Solar |  | 05_05_312W2 | 12/06/2012 | 12/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 03/21/2013 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 176196 | 02724 | 950 |  |  | Solar |  | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 647102 | 01532 | 5.76 |  |  | Solar |  | 05_14_2L3 | 10/23/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/23/2024 | 1/3/2026 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 5/21/2025 | Connected |  | N
National Grid | GLOUCESTER | 335256 | 01930 | 250 |  |  | Solar |  | 05_14_57L3 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 354303 | 01863 | 7.6 |  |  | Solar |  | 05_14_73L1 | 04/23/2021 | 04/27/2021 | 2 | 1 | 1 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 9/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2021 | Connected |  | N
National Grid | WESTFORD | 646241 | 01886 | 480 |  |  | Solar |  | 05_14_92L1 | 03/13/2025 | 05/27/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2025 | 07/30/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | CHELMSFORD | 176779 | 01824 | 7.6 |  |  | Solar |  | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 653524 | 01843 | 5.76 |  |  | Solar |  | 05_01_412L2 | 11/15/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 3/21/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 10/2/2025 | Connected |  | N
National Grid | WORCESTER | 185870 | 01606 | 1000 |  |  | Solar |  | 05_05_335W1 | 06/07/2018 | 06/07/2018 | 732 | 0 | 732 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 529991 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 10/20/2023 | 10/24/2023 | 2 | 0 | 2 | 10/25/2023 | 10/25/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | HUBBARDSTON | 175259 | 01452 | 138 |  |  | Solar |  | 05_05_312W2 | 01/07/2015 | 01/07/2015 | 4 | 0 | 4 | 01/14/2015 | 01/14/2015 | 0 | 0 | 0 | 03/11/2015 | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 |  | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 | 11/2/2015 |  | 12/31/2016 | N | EXP | 425 |  |  | 0 | 0 | 0 | 11/2/2015 | 11/2/2015 | 6/21/2017 | Connected |  | N
National Grid | FALL RIVER | 176186 | 02724 | 112 |  |  | Solar |  | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 9/6/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 4/11/2017 | 4/11/2017 | 4/11/2017 | Connected |  | N
National Grid | WESTBOROUGH | 647024 | 01581 | 10 |  |  | Solar |  | 05_14_2L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | BEVERLY | 340473 | 01915 | 7.6 |  |  | Solar |  | 05_14_57L3 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 6/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N
National Grid | CHELMSFORD | 469528 | 01863 | 7.6 |  |  | Solar |  | 05_14_73L1 | 10/19/2022 | 10/20/2022 | 1 | 0 | 1 | 10/21/2022 | 10/21/2022 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N
National Grid | WESTFORD | 719555 | 01886 | 11.4 |  |  | Solar |  | 05_14_92L1 | 09/16/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 52 | 24 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 176980 | 01824 | 6.6 |  |  | Solar |  | 05_01_24W3 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 06/07/2017 | 07/12/2017 | 24 | 0 | 24 | 9/28/2017 | 9/28/2017 | 9/28/2017 | Connected |  | N
National Grid | LAWRENCE | 653708 | 01843 | 4950 |  |  | Other |  | 05_01_412L2 | 04/10/2025 |  | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 209959 | 01606 | 1000 |  |  | Battery Add-On |  | 05_05_335W1 | 02/25/2019 | 03/18/2019 | 15 | 6 | 9 |  |  | 139 | 125 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 594405 | 01570 | 5 |  |  | Solar |  | 05_05_115W42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/19/2024 | 4/24/2025 | Y | EXP | 365 | 05/24/2024 | 07/05/2024 | 43 | 0 | 43 |  |  | 8/1/2024 | Connected |  | N
National Grid | MENDON | 175377 | 01756 | 368 |  |  | Solar |  | 05_05_312W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 |  | 11/28/2014 | N | EXP | 122 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 12/31/2014 | Connected |  | N
National Grid | FALL RIVER | 176284 | 02724 | 126 |  |  | Solar |  | 05_12_51T1 | 05/07/2015 | 05/07/2015 | 14 | 14 | 0 | 06/01/2015 | 06/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 12/31/2016 | N | EXP | 488 |  |  | 0 | 0 | 0 | 2/12/2016 | 2/12/2016 | 3/13/2017 | Connected |  | N
National Grid | WESTBOROUGH | 650018 | 01581 | 7.6 |  |  | Solar |  | 05_14_2L3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/06/2024 | 1/3/2026 | Y | EXP | 365 | 03/11/2025 | 05/06/2025 | 57 | 0 | 57 |  |  | 5/20/2025 | Connected |  | N
National Grid | GLOUCESTER | 449402 | 01930 | 11.4 |  |  | Solar |  | 05_14_57L3 | 08/12/2022 | 08/15/2022 | 1 | 0 | 1 | 08/16/2022 | 08/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 580798 | 01851 | 9.765 |  |  | Solar |  | 05_14_73L1 | 01/23/2024 | 01/26/2024 | 4 | 1 | 3 | 01/29/2024 | 01/29/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N
National Grid | WESTFORD | 175648 | 01886 | 4.73 |  |  | Solar |  | 05_14_92L1 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/16/2015 | N | EXP | 41 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 | 12/10/2015 | Connected |  | N
National Grid | CHELMSFORD | 193768 | 01824 | 10 |  |  | Solar |  | 05_01_24W3 | 08/17/2018 | 10/12/2018 | 7 | 7 | 0 | 10/15/2018 | 10/15/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 657794 | 01843 | 20 |  |  | Solar |  | 05_01_412L2 | 12/02/2024 | 12/06/2024 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 297438 | 01606 | 7.6 |  |  | Solar |  | 05_05_335W1 | 07/01/2020 | 07/06/2020 | 2 | 0 | 2 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 07/01/2020 | 6/1/2021 | Y | EXP | 365 | 11/04/2020 | 02/12/2021 | 100 | 0 | 100 |  |  | 6/1/2021 | Connected |  | N
National Grid | WEBSTER | 608980 | 01570 | 0 |  |  | Solar |  | 05_05_115W42 | 06/17/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 16 | 5 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | MENDON | 175809 | 01756 | 741 |  |  | Solar |  | 05_05_312W2 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 07/11/2015 | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 |  | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 | 10/30/2015 | 05/18/2015 | 12/31/2016 | Y | EXP | 428 | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 | 11/30/2016 | 11/30/2016 | 6/28/2016 | Connected |  | N
National Grid | FALL RIVER | 176810 | 02724 | 22.8 |  |  | Solar |  | 05_12_51T1 | 04/27/2016 | 04/27/2016 | 1 | 1 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 5/3/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/25/2016 | 5/25/2016 | 9/15/2016 | Connected |  | N
National Grid | WESTBOROUGH | 652090 | 01581 | 5.76 |  |  | Solar |  | 05_14_2L3 | 12/03/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 374358 | 01930 | 9.86 |  |  | Solar |  | 05_14_57L3 | 08/16/2021 | 08/17/2021 | 1 | 0 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N
National Grid | CHELMSFORD | 637040 | 01863 | 17.6 |  |  | Solar |  | 05_14_73L1 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/17/2024 | 11/27/2025 | Y | EXP | 365 | 03/26/2025 | 04/16/2025 | 22 | 0 | 22 |  |  | 4/23/2025 | Connected |  | N
National Grid | WESTFORD | 177104 | 01886 | 288 |  |  | Solar |  | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 307 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | CHELMSFORD | 196491 | 01824 | 5 |  |  | Solar |  | 05_01_24W3 | 09/20/2018 | 10/24/2018 | 19 | 18 | 1 | 10/25/2018 | 10/25/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  | 10/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | BILLERICA | 667026 | 01821 | 5.76 |  |  | Solar |  | 05_01_412L2 | 01/21/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2025 | Connected |  | N
National Grid | WORCESTER | 299593 | 01606 | 1500 |  |  | Solar |  | 05_05_335W1 | 02/08/2021 | 03/17/2021 | 26 | 19 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2021 | 04/13/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 625117 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 07/16/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | MENDON | 176027 | 01756 | 475 |  |  | Solar |  | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 176960 | 02724 | 45 |  |  | Solar |  | 05_12_51T1 | 07/17/2016 | 07/17/2016 | 1 | 1 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 7/23/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 2/13/2017 | 2/13/2017 | 2/13/2017 | Connected |  | N
National Grid | WESTBOROUGH | 684613 | 01581 | 21.4 |  |  | Solar |  | 05_14_2L3 | 04/14/2025 | 04/30/2025 | 9 | 5 | 4 | 05/01/2025 | 05/01/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | GLOUCESTER | 388451 | 01930 | 9.8 |  |  | Solar |  | 05_14_57L3 | 11/05/2021 | 12/16/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/05/2021 | 7/7/2023 | Y | EXP | 365 | 06/14/2022 | 07/06/2022 | 22 | 0 | 22 |  |  | 9/9/2022 | Connected |  | N
National Grid | LOWELL | 644757 | 01851 | 17.101 |  |  | Solar |  | 05_14_73L1 | 10/03/2024 | 10/07/2024 | 2 | 0 | 2 | 10/08/2024 | 10/08/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | WESTFORD | 177103 | 01886 | 288 |  |  | Solar |  | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 320 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | CHELMSFORD | 246025 | 01824 | 6 |  |  | Solar |  | 05_01_24W3 | 08/05/2019 | 08/20/2019 | 10 | 4 | 6 | 08/21/2019 | 08/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | BILLERICA | 674700 | 01821 | 10 |  |  | Solar |  | 05_01_412L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 335851 | 01606 | 6.96 |  |  | Solar |  | 05_05_335W1 | 01/18/2021 | 01/26/2021 | 5 | 1 | 4 | 01/27/2021 | 01/27/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/18/2021 | 5/20/2022 | Y | EXP | 365 | 08/21/2021 | 09/29/2021 | 34 | 3 | 31 |  |  | 12/18/2021 | Connected |  | N
National Grid | WEBSTER | 640702 | 01570 | 5.8 |  |  | Solar |  | 05_05_115W42 | 09/17/2024 | 10/15/2024 | 5 | 2 | 3 | 10/16/2024 | 10/16/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | Y
National Grid | MENDON | 176026 | 01756 | 266 |  |  | Solar |  | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 7 | 3 | 4 | 04/09/2015 | 04/09/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/30/2015 | 8/25/2015 | Y | EXP |  | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 177027 | 02724 | 731 |  |  | Solar |  | 05_12_51T1 | 03/16/2017 | 03/16/2017 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 05/05/2017 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 03/16/2017 | 8/18/2021 | Y | STD | 1026 | 11/08/2019 | 04/22/2020 | 166 | 0 | 166 |  |  | 8/18/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 378752 | 01532 | 2999 |  |  | Solar |  | 05_14_2L4 | 02/05/2022 | 03/15/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2022 | 03/16/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 02/05/2022 | 1/19/2027 | Y | STD | 483 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GLOUCESTER | 396438 | 01930 | 7.6 |  |  | Solar |  | 05_14_57L3 | 11/18/2021 | 12/20/2021 | 22 | 19 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | LOWELL | 645633 | 01851 | 10 |  |  | Solar |  | 05_14_73L1 | 10/21/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 216947 | 01886 | 10 |  |  | Solar |  | 05_14_92L1 | 09/21/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/21/2019 | 5/28/2020 | Y | EXP | 365 | 12/27/2019 | 12/26/2019 | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | CHELMSFORD | 283927 | 01824 | 10 |  |  | Solar |  | 05_01_24W3 | 04/28/2020 | 04/29/2020 | 1 | 1 | 0 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/28/2020 | 4/28/2021 | Y | EXP | 365 | 11/07/2020 | 01/06/2021 | 60 | 0 | 60 |  |  | 1/8/2021 | Connected |  | N
National Grid | BILLERICA | 681581 | 01821 | 15.76 |  |  | Solar |  | 05_01_412L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 388023 | 01606 | 9.8 |  |  | Solar |  | 05_05_335W1 | 10/27/2021 | 11/02/2021 | 4 | 0 | 4 | 11/03/2021 | 11/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/27/2021 | 5/18/2023 | Y | EXP | 365 | 02/16/2022 | 05/18/2022 | 92 | 0 | 92 |  |  | 6/7/2022 | Connected |  | N
National Grid | WEBSTER | 644030 | 01570 | 5.28 |  |  | Solar |  | 05_05_115W42 | 10/01/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | BELLINGHAM | 176093 | 02019 | 475 |  |  | Solar |  | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 8 | 0 | 8 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 177155 | 02724 | 20 |  |  | Solar |  | 05_12_51T1 | 10/24/2016 | 10/24/2016 | 4 | 4 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2016 |  | 10/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | WESTBOROUGH | 582189 | 01581 | 100 |  |  | Solar |  | 05_14_2L4 | 01/19/2024 | 02/09/2024 | 14 | 4 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | GLOUCESTER | 402600 | 01930 | 15 |  |  | Solar |  | 05_14_57L3 | 12/31/2021 | 01/18/2022 | 10 | 6 | 4 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 7/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | LOWELL | 648564 | 01851 | 10 |  |  | Solar |  | 05_14_73L1 | 11/01/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 11/01/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | WESTFORD | 339861 | 01886 | 15.2 |  |  | Solar |  | 05_14_92L1 | 02/01/2021 | 02/04/2021 | 3 | 2 | 1 | 02/05/2021 | 02/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 4/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2021 | Connected |  | N
National Grid | WESTFORD | 368621 | 01886 | 6 |  |  | Solar |  | 05_01_24W3 | 08/19/2021 | 12/31/2021 | 4 | 2 | 2 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 690834 | 01821 | 15.2 |  |  | Solar |  | 05_01_412L2 | 05/21/2025 | 05/27/2025 | 3 | 0 | 3 | 05/28/2025 | 05/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 392259 | 01606 | 6 |  |  | Solar |  | 05_05_335W1 | 11/23/2021 | 01/07/2022 | 4 | 0 | 4 | 12/01/2021 | 12/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2021 |  | 4/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2022 | Connected |  | Y
National Grid | WEBSTER | 645420 | 01570 | 5.76 |  |  | Solar |  | 05_05_115W42 | 10/31/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | BELLINGHAM | 176785 | 02019 | 726 |  |  | Solar |  | 05_05_312W2 | 01/13/2016 | 01/13/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2016 | 01/27/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2016 | 01/13/2016 | 1/19/2017 | Y | STD | 246 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/22/2016 | 12/22/2016 | Connected |  | N
National Grid | FALL RIVER | 177559 | 02724 | 3 |  |  | Solar |  | 05_12_51T1 | 07/13/2017 | 07/13/2017 | 22 | 22 | 0 | 08/15/2017 | 08/15/2017 | 117 | 7 | 110 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/19/2018 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 174864 | 01581 | 1333 |  |  | Solar |  | 05_14_2L4 | 08/02/2012 | 08/02/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/24/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2013 | 08/02/2012 | 12/31/2012 | Y | STD | -130 | 10/25/2013 | 12/27/2013 | 42 | 0 | 42 | 12/26/2013 | 12/26/2013 | 12/27/2013 | Connected |  | N
National Grid | GLOUCESTER | 421328 | 01930 | 0 |  |  | Solar |  | 05_14_57L3 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 653596 | 01851 | 10 |  |  | Solar |  | 05_14_73L1 | 11/15/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 | 02/13/2025 | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/15/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 599440 | 01886 | 15.744 |  |  | Solar |  | 05_14_92L1 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | Y
National Grid | WESTFORD | 443258 | 01886 | 7.6 |  |  | Solar |  | 05_01_24W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/19/2022 | 2/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | BILLERICA | 708501 | 01821 | 3.8 |  |  | Solar |  | 05_01_412L2 | 08/11/2025 | 08/28/2025 | 13 | 9 | 4 | 08/29/2025 | 08/29/2025 | 45 | 28 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WORCESTER | 409458 | 01606 | 3.8 |  |  | Solar |  | 05_05_335W1 | 02/10/2022 | 02/14/2022 | 2 | 0 | 2 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/10/2022 | 11/17/2023 | Y | EXP | 365 | 08/18/2022 | 10/28/2022 | 72 | 0 | 72 |  |  | 12/5/2022 | Connected |  | N
National Grid | WEBSTER | 645390 | 01570 | 5.76 |  |  | Solar |  | 05_05_115W42 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/07/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | BELLINGHAM | 178271 | 02019 | 766.6 |  |  | Solar |  | 05_05_312W2 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/10/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2018 | 01/09/2018 | 2/26/2021 | Y | STD | 712 | 10/28/2020 | 12/14/2020 | 47 | 0 | 47 | 2/16/2021 | 2/16/2021 | 2/26/2021 | Connected |  | N
National Grid | FALL RIVER | 178070 | 02724 | 144 |  |  | Solar |  | 05_12_51T1 | 10/31/2017 | 10/31/2017 | 9 | 9 | 0 | 11/20/2017 | 11/20/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 |  | 11/6/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/27/2018 | Connected |  | N
National Grid | WESTBOROUGH | 176010 | 01581 | 64.8 |  |  | Solar |  | 05_14_2L4 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/19/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/18/2016 | Connected |  | N
National Grid | HAMILTON | 460840 | 01982 | 0 |  |  | Solar |  | 05_14_57L3 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 660285 | 01824 | 10 |  |  | Solar |  | 05_14_73L1 | 12/12/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 637006 | 01886 | 3.8 |  |  | Solar |  | 05_14_92L1 | 08/30/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 476456 | 01824 | 6 |  |  | Solar |  | 05_01_24W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | BILLERICA | 175080 | 01821 | 1000 |  |  | Natural Gas |  | 05_01_412L3 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2013 | 12/11/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2015 | 10/01/2013 | 12/31/2016 | Y | STD | 664 | 06/17/2016 | 09/01/2016 | 52 | 0 | 52 | 10/2/2013 | 10/2/2013 | 6/14/2016 | Connected |  | N
National Grid | WORCESTER | 470892 | 01606 | 9.984 |  |  | Solar |  | 05_05_335W1 | 10/28/2022 | 11/02/2022 | 3 | 0 | 3 | 11/03/2022 | 11/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | WEBSTER | 653947 | 01570 | 5.76 |  |  | Solar |  | 05_05_115W42 | 11/15/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | BELLINGHAM | 351004 | 02019 | 220 |  |  | Solar |  | 05_05_312W2 | 05/20/2021 | 07/22/2021 | 43 | 33 | 10 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 | 05/20/2021 | 11/21/2023 | Y | STD | 263 | 03/30/2023 | 04/15/2023 | 16 | 0 | 16 |  |  | 11/29/2023 | Connected |  | N
National Grid | FALL RIVER | 178074 | 02724 | 20 |  |  | Solar |  | 05_12_51T1 | 11/02/2017 | 11/02/2017 | 91 | 91 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 11/7/2018 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 176358 | 01581 | 30 |  |  | Solar |  | 05_14_2L4 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 480047 | 01930 | 15.2 |  |  | Solar |  | 05_14_57L3 | 01/13/2023 | 12/05/2022 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2023 | Connected |  | N
National Grid | CHELMSFORD | 670687 | 01863 | 7.6 |  |  | Solar |  | 05_14_73L1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | TYNGSBORO | 637131 | 01879 | 5.76 |  |  | Solar |  | 05_14_92L1 | 09/02/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 502075 | 01824 | 7.68 |  |  | Solar |  | 05_01_24W3 | 03/06/2023 | 03/08/2023 | 2 | 1 | 1 | 03/09/2023 | 03/09/2023 | 25 | 0 | 25 | 05/12/2023 | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 176487 | 01821 | 3000 |  |  | Natural Gas |  | 05_01_412L3 | 12/08/2015 | 12/10/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/11/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/23/2016 | 06/23/2016 | 21 | 0 | 21 | 11/7/2016 |  | 1/31/2019 | N | STD | 815 |  |  | 0 | 0 | 0 |  |  | 1/19/2019 | Connected |  | N
National Grid | WORCESTER | 477584 | 01606 | 6 |  |  | Solar |  | 05_05_335W1 | 12/21/2022 | 09/25/2023 | 190 | 188 | 2 | 09/26/2023 | 09/26/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2024 | Connected |  | N
National Grid | WEBSTER | 660383 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/17/2024 | 2/25/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | BELLINGHAM | 384611 | 02019 | 400 |  |  | Solar |  | 05_05_312W2 | 06/13/2022 | 08/12/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/13/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 178111 | 02724 | 15 |  |  | Solar |  | 05_12_51T1 | 11/06/2017 | 11/06/2017 | 81 | 80 | 1 | 03/23/2018 | 03/23/2018 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 11/12/2018 | N | EXP | 182 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 202054 | 01581 | 4975 |  |  | Solar |  | 05_14_2L4 | 11/27/2018 | 12/06/2018 | 157 | 2 | 155 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 485511 | 01930 | 0 |  |  | Solar |  | 05_14_57L3 | 12/14/2022 | 12/15/2022 | 1 | 0 | 1 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N
National Grid | LOWELL | 701811 | 01851 | 15.2 |  |  | Solar |  | 05_14_73L1 | 07/02/2025 | 07/28/2025 | 16 | 14 | 2 | 07/29/2025 | 07/29/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | WESTFORD | 648337 | 01886 | 10 |  |  | Solar |  | 05_14_92L1 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 93 | 71 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 576736 | 01886 | 6 |  |  | Solar |  | 05_01_24W3 | 01/03/2024 | 01/08/2024 | 3 | 1 | 2 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/03/2024 | 3/4/2025 | Y | EXP | 365 | 04/24/2024 | 09/05/2024 | 135 | 0 | 135 |  |  | 9/10/2024 | Connected |  | N
National Grid | BILLERICA | 210192 | 01821 | 4250 |  |  | Natural Gas |  | 05_01_412L3 | 06/24/2019 | 07/16/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2019 | 07/25/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 | 06/24/2019 | 9/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | WORCESTER | 478755 | 01606 | 7.6 |  |  | Solar |  | 05_05_335W1 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 |  | 7/5/2024 | N | EXP | 365 | 07/07/2023 | 07/06/2023 | 0 | 0 | 0 |  |  | 7/21/2023 | Connected |  | N
National Grid | WEBSTER | 661562 | 01570 | 3.8 |  |  | Solar |  | 05_05_115W42 | 12/18/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | BELLINGHAM | 639701 | 02019 | 333 |  |  | Solar |  | 05_05_312W3 | 09/12/2024 | 10/22/2024 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 178201 | 02724 | 0 |  |  | Solar |  | 05_12_51T1 | 02/15/2018 | 02/15/2018 | 9 | 9 | 0 | 03/08/2018 | 03/08/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/21/2019 | N | EXP | 350 |  |  | 0 | 0 | 0 |  |  | 5/7/2019 | Connected |  | N
National Grid | WESTBOROUGH | 202052 | 01581 | 4975 |  |  | Solar |  | 05_14_2L4 | 05/18/2021 |  | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 495618 | 01944 | 7.6 |  |  | Solar |  | 05_14_57L3 | 02/27/2023 | 03/06/2023 | 6 | 5 | 1 | 03/07/2023 | 03/07/2023 | 230 | 206 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 726366 | 01851 | 6.84 |  |  | Solar |  | 05_14_73L1 | 10/14/2025 | 10/23/2025 | 6 | 5 | 1 | 10/24/2025 | 10/24/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | WESTFORD | 656745 | 01886 | 8.99 |  |  | Solar |  | 05_14_92L1 | 11/25/2024 | 03/04/2025 | 11 | 7 | 4 | 03/05/2025 | 03/05/2025 | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | WESTFORD | 591330 | 01886 | 3.8 |  |  | Solar |  | 05_01_24W3 | 02/26/2024 | 03/05/2024 | 6 | 0 | 6 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/26/2024 | 4/6/2025 | Y | EXP | 365 | 07/16/2024 | 09/11/2024 | 58 | 0 | 58 |  |  | 9/20/2024 | Connected |  | N
National Grid | BILLERICA | 578994 | 01821 | 240 |  |  | Solar |  | 05_01_412L4 | 12/22/2023 | 01/09/2024 | 10 | 0 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WORCESTER | 498788 | 01606 | 15.2 |  |  | Solar |  | 05_05_335W1 | 02/02/2023 | 02/03/2023 | 1 | 0 | 1 | 02/06/2023 | 02/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 3/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | OXFORD | 663099 | 01540 | 10 |  |  | Solar |  | 05_05_115W42 | 01/02/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 01/02/2025 | 3/24/2026 | Y | EXP | 365 | 04/29/2025 | 05/15/2025 | 17 | 0 | 17 |  |  | 6/6/2025 | Connected |  | N
National Grid | MENDON | 676971 | 01756 | 750 |  |  | Solar |  | 05_05_312W3 | 04/08/2025 | 06/26/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 178526 | 02724 | 3.8 |  |  | Solar |  | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/16/2018 | 05/16/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 207472 | 01581 | 73.3 |  |  | Solar |  | 05_14_2L4 | 01/29/2019 | 01/31/2019 | 1 | 0 | 1 | 02/01/2019 | 02/01/2019 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | ESSEX | 497827 | 01929 | 15.2 |  |  | Solar |  | 05_14_57L3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 30 | 12 | 18 | 04/10/2023 | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 4/19/2023 |  | 11/29/2024 | N | EXP | 365 | 08/31/2023 | 02/27/2024 | 181 | 3 | 178 |  |  | 3/7/2024 | Connected |  | N
National Grid | LOWELL | 640463 | 01851 | 0 |  |  | Solar |  | 05_14_73L2 | 09/16/2024 | 10/31/2024 | 8 | 6 | 2 | 11/01/2024 | 11/01/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/16/2024 | 11/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Terminated |  | N
National Grid | WESTFORD | 668349 | 01886 | 11.5 |  |  | Solar |  | 05_14_92L1 | 01/28/2025 | 01/31/2025 | 3 | 0 | 3 | 02/03/2025 | 02/03/2025 | 51 | 33 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | WESTFORD | 624975 | 01886 | 3.8 |  |  | Solar |  | 05_01_24W3 | 07/15/2024 | 07/22/2024 | 1 | 0 | 1 | 07/23/2024 | 07/23/2024 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 578997 | 01821 | 140 |  |  | Solar |  | 05_01_412L4 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WORCESTER | 533315 | 01606 | 15.2 |  |  | Solar |  | 05_05_335W1 | 06/30/2023 | 07/03/2023 | 1 | 0 | 1 | 07/05/2023 | 07/05/2023 | 35 | 21 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N
National Grid | OXFORD | 700098 | 01540 | 7.6 |  |  | Solar |  | 05_05_115W44 | 06/20/2025 | 09/22/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 31 | 13 | 18 | 12/04/2025 | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BELLINGHAM | 174837 | 02019 | 30 |  |  | Solar |  | 05_05_312W3 | 09/04/2012 | 09/04/2012 | 6 | 0 | 6 | 09/13/2012 | 09/13/2012 | 433 | 0 | 433 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 |  | 12/28/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178557 | 02724 | 11.4 |  |  | Solar |  | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 175488 | 01581 | 100 |  |  | Solar |  | 05_14_31J1 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2014 |  | 10/31/2014 | N | EXP | 50 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 4/9/2015 | Connected |  | N
National Grid | GLOUCESTER | 514032 | 01930 | 0 |  |  | Solar |  | 05_14_57L3 | 03/23/2023 | 03/27/2023 | 3 | 2 | 1 | 03/28/2023 | 03/28/2023 | 252 | 25 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 726184 | 01824 | 10 |  |  | Solar |  | 05_14_73L2 | 10/20/2025 | 11/03/2025 | 9 | 6 | 3 | 11/04/2025 | 11/04/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 670946 | 01886 | 7.6 |  |  | Solar |  | 05_14_92L1 | 02/12/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/12/2025 | 4/11/2026 | Y | EXP | 365 | 06/14/2025 | 06/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | WESTFORD | 637116 | 01886 | 5.76 |  |  | Solar |  | 05_01_24W3 | 09/02/2024 | 09/12/2024 | 2 | 0 | 2 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 657806 | 01821 | 7.6 |  |  | Solar |  | 05_01_412L4 | 12/02/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 12/02/2024 | 2/6/2026 | Y | EXP | 365 | 07/30/2025 | 08/04/2025 | 6 | 0 | 6 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 550748 | 01606 | 3.8 |  |  | Solar |  | 05_05_335W1 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 08/29/2023 | 1/19/2025 | Y | EXP | 365 | 02/06/2024 | 02/09/2024 | 4 | 0 | 4 |  |  | 4/25/2024 | Connected |  | N
National Grid | OXFORD | 738197 | 01540 | 250 |  |  | Solar |  | 05_05_115W44 | 12/24/2025 |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BELLINGHAM | 175231 | 02019 | 504 |  |  | Solar |  | 05_05_312W3 | 06/10/2014 | 06/10/2014 | 7 | 3 | 4 | 06/23/2014 | 06/23/2014 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 189490 | 02724 | 10 |  |  | Solar |  | 05_12_51T1 | 10/09/2018 | 10/11/2018 | 1 | 0 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 10/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 416686 | 01532 | 100 |  |  | Solar |  | 05_14_31J1 | 04/07/2022 | 05/10/2022 | 23 | 14 | 9 | 05/11/2022 | 05/11/2022 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 534960 | 01944 | 15.2 |  |  | Solar |  | 05_14_57L3 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | CHELMSFORD | 728805 | 01824 | 13.3 |  |  | Solar |  | 05_14_73L2 | 10/23/2025 | 11/03/2025 | 6 | 2 | 4 | 11/04/2025 | 11/04/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTFORD | 688427 | 01886 | 20 |  |  | Solar |  | 05_14_92L1 | 05/02/2025 | 05/27/2025 | 16 | 14 | 2 | 05/28/2025 | 05/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 638002 | 01824 | 3.8 |  |  | Solar |  | 05_01_24W3 | 09/05/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | BILLERICA | 672839 | 01821 | 700 |  |  | Solar |  | 05_01_412L4 | 04/14/2025 | 10/10/2025 | 124 | 115 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 | 10/21/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 573727 | 01606 | 15.2 |  |  | Solar |  | 05_05_335W1 | 11/28/2023 | 12/12/2023 | 10 | 9 | 1 | 12/13/2023 | 12/13/2023 | 38 | 16 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2024 | Connected |  | N
National Grid | DUDLEY | 174492 | 01571 | 120 |  |  | Solar |  | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 3/2/2012 | N | EXP | 234 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/2/2012 | Connected |  | N
National Grid | MENDON | 175601 | 01756 | 460 |  |  | Solar |  | 05_05_312W3 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 | 10/23/2014 | 10/23/2014 | 0 | 0 | 0 | 01/27/2015 | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 3/20/2015 |  | 1/31/2015 | N | EXP | -48 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 2/4/2016 | Connected |  | N
National Grid | FALL RIVER | 195069 | 02724 | 0 |  |  | Solar |  | 05_12_51T1 | 09/05/2018 | 10/02/2018 | 10 | 4 | 6 | 10/03/2018 | 10/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | WESTBOROUGH | 603273 | 01581 | 3.8 |  |  | Solar |  | 05_14_31J3 | 04/16/2024 | 04/19/2024 | 3 | 0 | 3 | 04/22/2024 | 04/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2026 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 602139 | 01930 | 16.128 |  |  | Solar |  | 05_14_57L3 | 04/22/2024 | 04/26/2024 | 4 | 2 | 2 | 04/29/2024 | 04/29/2024 | 18 | 12 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 729822 | 01854 | 0 |  |  | Solar |  | 05_14_73L2 | 10/29/2025 | 11/12/2025 | 8 | 6 | 2 | 11/13/2025 | 11/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 727308 | 01886 | 11.4 |  |  | Solar |  | 05_14_92L1 | 10/17/2025 | 10/23/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 639629 | 01863 | 10 |  |  | Solar |  | 05_01_24W3 | 09/12/2024 | 09/20/2024 | 5 | 2 | 3 | 09/23/2024 | 09/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | BILLERICA | 677465 | 01821 | 20 |  |  | Solar |  | 05_01_412L4 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 25 | 0 | 25 | 05/27/2025 | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/21/2026 | N | EXP | 365 | 10/01/2025 |  | 93 | 0 | 93 |  |  |  | Construction |  | N
National Grid | WORCESTER | 579748 | 01606 | 10 |  |  | Solar |  | 05_05_335W1 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/15/2024 | 5/18/2025 | Y | EXP | 365 | 06/14/2024 | 07/20/2024 | 37 | 0 | 37 |  |  | 9/6/2024 | Connected |  | N
National Grid | DUDLEY | 174491 | 01571 | 82 |  |  | Solar |  | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 2/28/2012 | N | EXP | 231 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 2/28/2012 | Connected |  | N
National Grid | MENDON | 177986 | 01756 | 366.3 |  |  | Solar |  | 05_05_312W3 | 08/28/2017 | 08/28/2017 | 99 | 96 | 3 | 02/01/2018 | 02/01/2018 | 22 | 0 | 22 | 03/19/2018 | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/27/2018 |  | 9/4/2018 | N | EXP | 130 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 195777 | 02721 | 147.6 |  |  | Solar |  | 05_12_51T1 | 09/12/2018 | 09/19/2018 | 4 | 0 | 4 | 09/20/2018 | 09/20/2018 | 20 | 0 | 20 | 09/13/2019 | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 |  | 12/31/2020 | N | EXP | 172 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | WESTBOROUGH | 176476 | 01581 | 100 |  |  | Solar |  | 05_14_31J5 | 03/24/2016 | 03/24/2016 | 9 | 9 | 0 | 04/07/2016 | 04/07/2016 | 468 | 17 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/31/2018 | N | EXP | 744 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 621970 | 01930 | 11.5 |  |  | Solar |  | 05_14_57L3 | 07/02/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y
National Grid | HAVERHILL | 174304 | 01830 | 500 |  |  | Solar |  | 05_14_73L2 | 12/29/2011 | 12/29/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 511257 | 01886 | 249 |  |  | Solar |  | 05_14_92L2 | 03/16/2023 | 04/07/2023 | 16 | 6 | 10 | 04/10/2023 | 04/10/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 03/16/2023 | 6/23/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WESTFORD | 641869 | 01886 | 7.8 |  |  | Solar |  | 05_01_24W3 | 09/20/2024 | 10/03/2024 | 3 | 0 | 3 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 | 01/21/2025 | 06/10/2025 | 141 | 0 | 141 |  |  | 6/13/2025 | Connected |  | N
National Grid | BILLERICA | 693113 | 01821 | 23 |  |  | Solar |  | 05_01_412L4 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 | 05/29/2025 | 7/28/2026 | Y | EXP | 365 | 10/29/2025 |  | 65 | 0 | 65 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 590034 | 01606 | 10 |  |  | Solar |  | 05_05_335W1 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | DUDLEY | 174711 | 01571 | 485 |  |  | Solar |  | 05_05_115W44 | 06/21/2013 | 06/21/2013 | 6 | 0 | 6 | 07/02/2013 | 07/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2013 |  | 11/1/2013 | N | EXP | 113 |  |  | 0 | 0 | 0 | 12/31/2013 | 12/31/2013 | 12/31/2013 | Connected |  | Y
National Grid | MENDON | 319057 | 01756 | 249 |  |  | Solar |  | 05_05_312W3 | 10/13/2020 | 11/04/2020 | 15 | 8 | 7 | 11/18/2020 | 11/18/2020 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | FALL RIVER | 204210 | 02723 | 0 |  |  | Solar |  | 05_12_51T1 | 12/20/2018 | 01/03/2019 | 7 | 0 | 7 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 12/20/2018 | 1/3/2020 | Y | EXP | 365 | 08/23/2019 | 12/18/2019 | 117 | 0 | 117 |  |  | 7/31/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 176513 | 01532 | 99.9 |  |  | Solar |  | 05_14_31J6 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 77 | 380 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 12/6/2017 | N | EXP | 477 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ESSEX | 639845 | 01929 | 17.4 |  |  | Solar |  | 05_14_57L3 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 175635 | 01830 | 998 |  |  | Solar |  | 05_14_73L2 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 640240 | 01886 | 5.76 |  |  | Solar |  | 05_14_92L2 | 09/13/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/13/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTFORD | 657941 | 01886 | 7.6 |  |  | Solar |  | 05_01_24W3 | 12/02/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 12/02/2024 | 2/24/2026 | Y | EXP | 365 | 07/03/2025 | 07/15/2025 | 13 | 0 | 13 |  |  | 7/28/2025 | Connected |  | N
National Grid | BILLERICA | 699718 | 01821 | 10 |  |  | Solar |  | 05_01_412L4 | 06/19/2025 | 07/02/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/19/2025 | 9/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 589409 | 01606 | 6 |  |  | Solar |  | 05_05_335W1 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 11/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2024 | Connected |  | N
National Grid | DUDLEY | 175053 | 01571 | 80.25 |  |  | Solar |  | 05_05_115W44 | 08/13/2012 | 08/13/2012 | 8 | 3 | 5 | 08/24/2012 | 08/24/2012 | 276 | 0 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 409851 | 01756 | 86.4 |  |  | Solar |  | 05_05_312W3 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 | 02/04/2022 | 1/11/2023 | Y | EXP | 196 | 12/01/2022 | 12/06/2022 | 6 | 6 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | FALL RIVER | 217096 | 02721 | 0 |  |  | Solar |  | 05_12_51T1 | 04/03/2019 | 04/09/2019 | 3 | 0 | 3 | 04/10/2019 | 04/10/2019 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 650000 | 01532 | 3.8 |  |  | Solar |  | 05_14_31L9 | 10/30/2024 | 11/25/2024 | 5 | 0 | 5 | 11/26/2024 | 11/26/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 645111 | 01944 | 10 |  |  | Solar |  | 05_14_57L3 | 10/04/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176615 | 01830 | 55 |  |  | Solar |  | 05_14_73L2 | 02/15/2016 | 02/15/2016 | 48 | 48 | 0 | 04/26/2016 | 04/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2016 |  | 2/21/2017 | N | EXP | 284 |  |  | 0 | 0 | 0 | 9/14/2016 | 9/14/2016 | 9/26/2016 | Connected |  | N
National Grid | TYNGSBORO | 724655 | 01879 | 11.5 |  |  | Solar |  | 05_14_92L2 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHELMSFORD | 659022 | 01824 | 9.88 |  |  | Solar |  | 05_01_24W3 | 12/06/2024 | 01/08/2025 | 13 | 8 | 5 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | BILLERICA | 739355 | 01821 | 7.6 |  |  | Solar |  | 05_01_412L4 | 12/10/2025 | 12/11/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 592697 | 01606 | 6 |  |  | Solar |  | 05_05_335W1 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/28/2024 | 3/12/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 6/8/2024 | Connected |  | N
National Grid | DUDLEY | 175291 | 01571 | 36 |  |  | Solar |  | 05_05_115W44 | 11/06/2014 | 11/06/2014 | 5 | 2 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 2/27/2015 | N | EXP | 99 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/16/2015 | Connected |  | N
National Grid | BELLINGHAM | 552640 | 02019 | 333 |  |  | Solar |  | 05_05_312W3 | 11/21/2023 |  | 192 | 183 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 221773 | 02721 | 0 |  |  | Solar |  | 05_12_51T1 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 650670 | 01532 | 5.76 |  |  | Solar |  | 05_14_31L9 | 10/30/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 648978 | 01930 | 5.76 |  |  | Solar |  | 05_14_57L3 | 10/22/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N
National Grid | HAVERHILL | 194444 | 01830 | 7.6 |  |  | Solar |  | 05_14_73L2 | 08/26/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175361 | 01886 | 8 |  |  | Solar |  | 05_14_92L2 | 11/13/2014 | 11/13/2014 | 5 | 0 | 5 | 11/21/2014 | 11/21/2014 | 249 | 0 | 249 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 |  | 1/11/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 660119 | 01886 | 7.475 |  |  | Solar |  | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 174760 | 01821 | 497.6 |  |  | Solar |  | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/28/2017 | Y | STD | 840 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N
National Grid | WORCESTER | 610127 | 01606 | 5.76 |  |  | Solar |  | 05_05_335W1 | 05/15/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2024 | Connected |  | N
National Grid | DUDLEY | 176473 | 01571 | 72 |  |  | Solar |  | 05_05_115W44 | 03/22/2016 | 03/22/2016 | 3 | 3 | 0 | 03/28/2016 | 03/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2016 |  | 9/30/2016 | N | EXP | 143 |  |  | 0 | 0 | 0 | 9/21/2016 | 9/21/2016 | 10/4/2016 | Connected |  | N
National Grid | BELLINGHAM | 582654 | 02019 | 0 |  |  | Solar |  | 05_05_312W3 | 02/02/2024 | 03/21/2024 | 34 | 32 | 2 | 03/22/2024 | 03/22/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | FALL RIVER | 225352 | 02723 | 10 |  |  | Solar |  | 05_12_51T1 | 05/06/2019 | 05/16/2019 | 8 | 8 | 0 | 05/17/2019 | 05/17/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | Y
National Grid | NORTHBOROUGH | 653300 | 01532 | 10.88 |  |  | Solar |  | 05_14_31L9 | 11/08/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 649917 | 01930 | 10 |  |  | Solar |  | 05_14_57L3 | 10/31/2024 | 11/05/2024 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 10/31/2024 | 3/12/2026 | Y | EXP | 365 | 05/01/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 6/27/2025 | Connected |  | N
National Grid | HAVERHILL | 273784 | 01830 | 8.88 |  |  | Solar |  | 05_14_73L2 | 02/03/2020 | 02/05/2020 | 1 | 1 | 0 | 02/06/2020 | 02/06/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2020 | Connected |  | N
National Grid | TYNGSBORO | 176022 | 01879 | 3 |  |  | Solar |  | 05_14_92L2 | 03/25/2015 | 03/25/2015 | 6 | 0 | 6 | 04/03/2015 | 04/03/2015 | 464 | 0 | 464 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 8/31/2015 | N | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 660120 | 01886 | 7.475 |  |  | Solar |  | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | BILLERICA | 174759 | 01821 | 497.6 |  |  | Solar |  | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 6/30/2017 | Y | STD | 903 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 6/28/2017 | Connected |  | N
National Grid | WORCESTER | 624136 | 01606 | 0 |  |  | Solar |  | 05_05_335W1 | 07/11/2024 | 08/01/2024 | 14 | 12 | 2 | 08/02/2024 | 08/02/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | N
National Grid | DUDLEY | 387395 | 01571 | 0 |  |  | Other |  | 05_05_115W44 | 10/25/2021 | 01/04/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 718516 | 02019 | 15.2 |  |  | Solar |  | 05_05_312W4 | 09/11/2025 | 09/18/2025 | 5 | 0 | 5 | 09/19/2025 | 09/19/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 252036 | 02721 | 0 |  |  | Solar |  | 05_12_51T1 | 09/04/2019 | 09/11/2019 | 4 | 0 | 4 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 |  | 12/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 655518 | 01581 | 7.6 |  |  | Solar |  | 05_14_31L9 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 656744 | 01944 | 15.2 |  |  | Solar |  | 05_14_57L3 | 11/25/2024 | 12/18/2024 | 15 | 13 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | HAVERHILL | 297463 | 01830 | 10 |  |  | Solar |  | 05_14_73L2 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N
National Grid | TYNGSBORO | 176148 | 01879 | 172 |  |  | Solar |  | 05_14_92L2 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 9/5/2016 | N | EXP | 370 |  |  | 0 | 0 | 0 | 2/2/2016 | 2/2/2016 | 5/5/2016 | Connected |  | N
National Grid | CHELMSFORD | 668899 | 01863 | 7.6 |  |  | Solar |  | 05_01_24W3 | 02/03/2025 | 04/16/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | BILLERICA | 174758 | 01821 | 497.6 |  |  | Solar |  | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 8/31/2017 | Y | STD | 965 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 8/11/2017 | Connected |  | N
National Grid | WORCESTER | 641990 | 01606 | 3.8 |  |  | Solar |  | 05_05_335W1 | 09/20/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/20/2024 | 12/4/2025 | Y | EXP | 365 | 12/19/2024 | 01/28/2025 | 41 | 0 | 41 |  |  | 3/6/2025 | Connected |  | N
National Grid | CHARLTON | 501029 | 01507 | 100 |  |  | Solar |  | 05_05_115W44 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 174127 | 02019 | 13.97 |  |  | Solar |  | 05_05_312W4 | 04/26/2012 | 04/26/2012 | 9 | 0 | 9 | 05/14/2012 | 05/14/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2012 |  | 6/29/2012 | N | EXP | -97 |  |  | 0 | 0 | 0 | 8/29/2012 | 8/29/2012 | 10/10/2012 | Connected |  | N
National Grid | FALL RIVER | 260745 | 02721 | 5.76 |  |  | Solar |  | 05_12_51T1 | 10/18/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 | 10/18/2019 | 7/9/2020 | Y | EXP | 365 | 02/29/2020 | 02/28/2020 | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 663850 | 01532 | 14.5 |  |  | Solar |  | 05_14_31L9 | 01/08/2025 | 01/17/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MANCHESTER | 661194 | 01944 | 0 |  |  | Battery Add-On |  | 05_14_57L3 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | HAVERHILL | 317580 | 01830 | 9.28 |  |  | Solar |  | 05_14_73L2 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2021 | Connected |  | N
National Grid | WESTFORD | 176761 | 01886 | 7.6 |  |  | Solar |  | 05_14_92L2 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | CHELMSFORD | 714389 | 01863 | 5.76 |  |  | Solar |  | 05_01_24W3 | 08/25/2025 | 09/05/2025 | 7 | 2 | 5 | 09/08/2025 | 09/08/2025 | 59 | 47 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 174757 | 01821 | 448 |  |  | Solar |  | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/30/2017 | Y | STD | 842 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N
National Grid | WORCESTER | 658626 | 01606 | 3.8 |  |  | Solar |  | 05_05_335W1 | 12/05/2024 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/05/2024 | 3/10/2026 | Y | EXP | 365 | 04/15/2025 |  | 262 | 0 | 262 |  |  | 12/1/2025 | Connected |  | N
National Grid | DUDLEY | 544185 | 01571 | 18.85 |  |  | Solar |  | 05_05_115W44 | 08/04/2023 | 08/08/2023 | 2 | 0 | 2 | 08/09/2023 | 08/09/2023 | 161 | 28 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 174164 | 02019 | 10.75 |  |  | Solar |  | 05_05_312W4 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2012 |  | 6/1/2012 | N | EXP | -83 |  |  | 0 | 0 | 0 | 8/23/2012 | 8/23/2012 | 12/21/2012 | Connected |  | N
National Grid | FALL RIVER | 286147 | 02721 | 15.36 |  |  | Solar |  | 05_12_51T1 | 04/01/2020 | 04/03/2020 | 1 | 0 | 1 | 04/06/2020 | 04/06/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  | 10/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 177941 | 01851 | 120 |  |  | Solar |  | 05_14_32J1 | 06/26/2017 | 06/26/2017 | 105 | 105 | 0 |  |  | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 5/2/2019 | N | STD | 219 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 664297 | 01915 | 0 |  |  | Battery Add-On |  | 05_14_57L3 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 01/07/2025 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | HAVERHILL | 452930 | 01830 | 7.6 |  |  | Solar |  | 05_14_73L2 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2022 | 08/19/2022 | 9/30/2023 | Y | EXP | 365 | 12/06/2022 | 12/05/2022 | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N
National Grid | WESTFORD | 177216 | 01886 | 75 |  |  | Solar |  | 05_14_92L2 | 06/10/2016 | 06/10/2016 | 4 | 4 | 0 | 06/17/2016 | 06/17/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/18/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 174797 | 01863 | 100 |  |  | Solar |  | 05_01_24W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 438 | 119 | 319 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/7/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 175265 | 01821 | 15.8 |  |  | Solar |  | 05_01_412L4 | 06/16/2014 | 06/16/2014 | 6 | 0 | 6 | 06/26/2014 | 06/26/2014 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 |  | 9/1/2014 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 659458 | 01606 | 3.8 |  |  | Solar |  | 05_05_335W1 | 12/09/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 662528 | 01571 | 7.6 |  |  | Solar |  | 05_05_115W44 | 12/26/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/26/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | BELLINGHAM | 174274 | 02019 | 1000 |  |  | Solar |  | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 291501 | 02723 | 3.8 |  |  | Solar |  | 05_12_51T1 | 05/25/2020 | 05/26/2020 | 0 | 0 | 0 | 05/27/2020 | 05/27/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/25/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 176539 | 01581 | 46.8 |  |  | Solar |  | 05_14_32J5 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 9/16/2017 | N | EXP | 570 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N
National Grid | WENHAM | 678244 | 01984 | 20 |  |  | Solar |  | 05_14_57L3 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | HAVERHILL | 378620 | 01830 | 7.6 |  |  | Solar |  | 05_14_73L2 | 09/01/2021 | 09/02/2021 | 1 | 0 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2022 | Connected |  | N
National Grid | TYNGSBORO | 178502 | 01879 | 250 |  |  | Solar |  | 05_14_92L2 | 12/15/2017 | 12/15/2017 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 | 12/15/2017 | 12/20/2019 | Y | STD | 660 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | CHELMSFORD | 174964 | 01863 | 81 |  |  | Solar |  | 05_01_24W4 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2013 |  | 11/29/2013 | N | EXP | 66 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N
National Grid | BILLERICA | 175582 | 01821 | 19 |  |  | Solar |  | 05_01_412L4 | 12/14/2014 | 12/14/2014 | 6 | 4 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/28/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 | 1/7/2016 | 1/7/2016 | 1/7/2016 | Connected |  | N
National Grid | WORCESTER | 662880 | 01606 | 5.76 |  |  | Solar |  | 05_05_335W1 | 12/27/2024 | 01/13/2025 | 3 | 0 | 3 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/27/2024 | 2/26/2026 | Y | EXP | 365 | 03/15/2025 | 05/20/2025 | 67 | 0 | 67 |  |  | 7/19/2025 | Connected |  | N
National Grid | DUDLEY | 176354 | 01571 | 38 |  |  | Solar |  | 05_05_115W45 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 386 | 0 | 386 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 174273 | 02019 | 0 |  |  | Solar |  | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 292006 | 02721 | 10 |  |  | Solar |  | 05_12_51T1 | 06/09/2020 | 06/16/2020 | 5 | 5 | 0 | 06/17/2020 | 06/17/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 6/14/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 210231 | 01581 | 15.2 |  |  | Solar |  | 05_14_33L1 | 03/08/2019 | 04/03/2019 | 10 | 10 | 0 | 04/04/2019 | 04/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 7/26/2019 | N | EXP | 108 |  |  | 0 | 0 | 0 |  |  | 6/25/2019 | Connected |  | N
National Grid | GLOUCESTER | 705914 | 01930 | 15.2 |  |  | Solar |  | 05_14_57L3 | 07/22/2025 |  | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 385131 | 01830 | 7.6 |  |  | Solar |  | 05_14_73L2 | 09/28/2021 | 10/01/2021 | 4 | 3 | 1 | 10/04/2021 | 10/04/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 |  | 9/30/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 192826 | 01879 | 3.64 |  |  | Solar |  | 05_14_92L2 | 08/20/2018 | 09/13/2018 | 7 | 1 | 6 | 09/14/2018 | 09/14/2018 | 68 | 3 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 202543 | 01886 | 249.9 |  |  | Solar |  | 05_01_24W4 | 12/21/2018 | 01/10/2019 | 5 | 0 | 5 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 175747 | 01821 | 1000 |  |  | Solar |  | 05_01_412L4 | 10/30/2014 | 10/30/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 | 10/30/2014 | 9/1/2017 | Y | STD | 707 | 06/05/2017 | 08/16/2017 | 51 | 0 | 51 | 8/21/2017 | 8/21/2017 | 9/14/2017 | Connected |  | N
National Grid | WORCESTER | 666700 | 01606 | 7.6 |  |  | Solar |  | 05_05_335W1 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/20/2025 | 3/19/2026 | Y | EXP | 365 | 11/19/2025 | 11/18/2025 | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | DUDLEY | 176796 | 01571 | 216 |  |  | Solar |  | 05_05_115W45 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 | 02/25/2016 | 3/2/2017 | Y | EXP | 120 | 01/05/2017 | 01/30/2017 | 16 | 0 | 16 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | BELLINGHAM | 174272 | 02019 | 1820 |  |  | Solar |  | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 | 02/13/2012 | 04/11/2012 | 40 | 0 | 40 |  | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2013 | 11/01/2011 | 1/16/2012 | Y | STD | -409 | 10/24/2013 | 12/12/2013 | 33 | 0 | 33 | 2/12/2014 | 2/12/2014 | 4/1/2014 | Connected |  | N
National Grid | FALL RIVER | 292808 | 02721 | 0 |  |  | Battery Add-On |  | 05_12_51T1 | 05/20/2020 | 05/29/2020 | 6 | 5 | 1 | 06/01/2020 | 06/01/2020 | 112 | 53 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177356 | 01581 | 22.8 |  |  | Solar |  | 05_05_7L4 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 | 02/15/2017 | 2/21/2018 | Y | EXP | 359 | 06/28/2017 | 07/12/2017 | 9 | 0 | 9 | 9/18/2017 | 9/18/2017 | 9/21/2017 | Connected |  | N
National Grid | MANCHESTER | 705910 | 01944 | 15.2 |  |  | Solar |  | 05_14_57L3 | 08/12/2025 | 09/02/2025 | 13 | 10 | 3 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | HAVERHILL | 392677 | 01832 | 7.6 |  |  | Solar |  | 05_14_73L2 | 04/25/2022 | 06/15/2022 | 36 | 35 | 1 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/25/2022 | 8/20/2023 | Y | EXP | 365 | 12/22/2022 | 02/17/2023 | 58 | 0 | 58 |  |  | 5/11/2023 | Connected |  | N
National Grid | WESTFORD | 213493 | 01886 | 10 |  |  | Solar |  | 05_14_92L2 | 04/10/2019 | 05/29/2019 | 48 | 47 | 1 | 06/20/2019 | 06/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 04/10/2019 | 7/31/2020 | Y | EXP | 365 | 02/22/2020 | 06/03/2020 | 102 | 0 | 102 |  |  | 7/10/2020 | Connected |  | N
National Grid | WESTFORD | 396605 | 01886 | 0 |  |  | Other |  | 05_01_24W4 | 05/11/2022 | 05/27/2022 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 175872 | 01821 | 56 |  |  | Solar |  | 05_01_412L4 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 10/4/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N
National Grid | WORCESTER | 685398 | 01605 | 7.6 |  |  | Solar |  | 05_05_335W1 | 04/15/2025 | 05/19/2025 | 8 | 3 | 5 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/15/2025 | 6/11/2026 | Y | EXP | 365 | 06/25/2025 | 08/13/2025 | 50 | 0 | 50 |  |  | 8/15/2025 | Connected |  | N
National Grid | DUDLEY | 177182 | 01571 | 120 |  |  | Solar |  | 05_05_115W45 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 | 08/12/2016 | 8/17/2017 | Y | EXP | 343 | 01/05/2017 | 05/04/2017 | 82 | 0 | 82 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | BELLINGHAM | 175780 | 02019 | 866 |  |  | Solar |  | 05_05_312W4 | 07/22/2015 | 07/22/2015 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/28/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 01/05/2016 | 05/17/2016 | 91 | 10 | 81 | 6/3/2016 | 07/22/2015 | 7/27/2016 | Y | STD | 54 | 11/09/2016 | 01/25/2017 | 50 | 0 | 50 | 1/26/2017 | 1/26/2017 | 2/1/2017 | Connected |  | N
National Grid | FALL RIVER | 295399 | 02723 | 0 |  |  | Battery Add-On |  | 05_12_51T1 | 06/13/2020 | 06/22/2020 | 5 | 4 | 1 | 06/23/2020 | 06/23/2020 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 3/3/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177467 | 01581 | 192 |  |  | Solar |  | 05_05_7L4 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 21 | 6 | 15 | 05/03/2017 | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/7/2018 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | GLOUCESTER | 708703 | 01930 | 15.2 |  |  | Solar |  | 05_14_57L3 | 07/31/2025 | 08/08/2025 | 5 | 1 | 4 | 08/11/2025 | 08/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | HAVERHILL | 402422 | 01830 | 7.6 |  |  | Solar |  | 05_14_73L2 | 03/17/2022 | 03/18/2022 | 1 | 0 | 1 | 03/21/2022 | 03/21/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N
National Grid | TYNGSBORO | 214979 | 01879 | 3.8 |  |  | Solar |  | 05_14_92L2 | 03/22/2019 | 07/22/2019 | 86 | 86 | 0 | 07/23/2019 | 07/23/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/29/2019 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N
National Grid | WESTFORD | 601631 | 01886 | 3.8 |  |  | Solar |  | 05_01_24W4 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 4/25/2025 | Y | EXP | 365 | 05/24/2024 | 09/12/2024 | 112 | 0 | 112 |  |  | 9/26/2024 | Connected |  | N
National Grid | BILLERICA | 175895 | 01821 | 7.6 |  |  | Solar |  | 05_01_412L4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 358 | 09/13/2016 | 09/23/2016 | 8 | 0 | 8 | 8/18/2015 | 8/18/2015 | 9/28/2016 | Connected |  | N
National Grid | WORCESTER | 692702 | 01606 | 17.875 |  |  | Solar |  | 05_05_335W1 | 05/21/2025 | 05/23/2025 | 2 | 0 | 2 | 07/16/2025 | 07/16/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | DUDLEY | 177406 | 01571 | 7.6 |  |  | Solar |  | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 176096 | 02019 | 300 |  |  | Solar |  | 05_05_312W4 | 04/03/2015 | 04/03/2015 | 5 | 0 | 5 | 04/13/2015 | 04/13/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 |  | 2/7/2018 | N | EXP | 1024 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 298665 | 02790 | 10 |  |  | Solar |  | 05_12_51T1 | 06/26/2020 | 07/06/2020 | 6 | 1 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 6/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | WESTBOROUGH | 177466 | 01581 | 168 |  |  | Solar |  | 05_05_7L4 | 03/01/2017 | 03/01/2017 | 20 | 13 | 7 | 03/23/2017 | 03/23/2017 | 21 | 6 | 15 | 05/03/2017 | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/7/2018 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | GLOUCESTER | 717812 | 01930 | 15.66 |  |  | Solar |  | 05_14_57L3 | 09/17/2025 | 09/24/2025 | 5 | 0 | 5 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | BOXFORD | 415211 | 01921 | 7.6 |  |  | Solar |  | 05_14_73L2 | 09/29/2022 | 03/07/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | WESTFORD | 632651 | 01886 | 5.76 |  |  | Solar |  | 05_01_24W4 | 08/14/2024 | 09/10/2024 | 3 | 0 | 3 | 09/11/2024 | 09/11/2024 | 105 | 31 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175969 | 01886 | 19.75 |  |  | Solar |  | 05_01_412L4 | 08/07/2015 | 08/07/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/15/2016 | Connected |  | N
National Grid | BILLERICA | 359562 | 01821 | 480 |  |  | Solar |  | 05_05_335W2 | 06/18/2021 | 07/07/2021 | 12 | 3 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 06/18/2021 | 4/9/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WORCESTER | 177402 | 01606 | 10 |  |  | Solar |  | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/29/2016 | 7/5/2017 | Y | EXP | 352 | 05/23/2017 | 06/23/2017 | 22 | 0 | 22 | 7/17/2017 | 7/17/2017 | 7/19/2017 | Connected |  | N
National Grid | DUDLEY | 176165 | 01571 | 850 |  |  | Solar |  | 05_05_312W4 | 04/17/2015 | 04/17/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/07/2015 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 12/22/2015 | 05/11/2016 | 95 | 0 | 95 | 6/3/2016 | 04/17/2015 | 3/17/2017 | Y | STD | 287 | 10/13/2016 | 04/07/2017 | 120 | 0 | 120 | 4/26/2017 | 4/26/2017 | 4/26/2017 | Connected |  | N
National Grid | BELLINGHAM | 300315 | 02019 | 0 |  |  | Solar |  | 05_12_51T1 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | FALL RIVER | 178229 | 02723 | 15.2 |  |  | Solar |  | 05_05_7L4 | 01/03/2018 | 01/03/2018 | 38 | 32 | 6 | 03/06/2018 | 03/06/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 1/10/2019 | N | EXP | 309 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | WESTBOROUGH | 206199 | 01581 | 72 |  |  | Solar |  | 05_14_57L4 | 01/16/2019 | 01/31/2019 | 8 | 3 | 5 | 02/01/2019 | 02/01/2019 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | MANCHESTER | 424042 | 01944 | 10 |  |  | Solar |  | 05_14_73L2 | 05/05/2022 | 05/25/2022 | 14 | 14 | 0 | 05/26/2022 | 05/26/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2022 | Connected |  | N
National Grid | REHOBOTH | 384627 | 02769 | 400 |  |  | Solar |  | 05_14_92L2 | 08/11/2022 | 10/04/2022 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/28/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 733558 | 01886 | 11.4 |  |  | Solar |  | 05_01_24W5 | 11/13/2025 | 11/14/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTFORD | 176200 | 01886 | 17.6 |  |  | Solar |  | 05_01_412L4 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 |  | 12/31/2016 | N | EXP | 668 |  |  | 0 | 0 | 0 | 3/4/2015 | 3/4/2015 | 12/11/2015 | Connected |  | N
National Grid | BILLERICA | 500304 | 01821 | 3000 |  |  | Solar |  | 05_05_335W2 | 10/05/2023 | 05/16/2024 | 152 | 143 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 05/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 177448 | 01606 | 96 |  |  | Solar |  | 05_05_115W45 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 | 09/20/2016 | 09/20/2016 | 54 | 2 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 176494 | 01570 | 15.25 |  |  | Solar |  | 05_05_312W4 | 12/10/2015 | 12/10/2015 | 29 | 29 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 12/15/2016 | N | EXP | 314 |  |  | 0 | 0 | 0 | 2/18/2016 | 2/18/2016 | 2/24/2016 | Connected |  | N
National Grid | HOPEDALE | 302762 | 01747 | 10 |  |  | Solar |  | 05_12_51T1 | 07/29/2020 | 07/31/2020 | 1 | 1 | 0 | 08/03/2020 | 08/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/29/2020 | 7/30/2021 | Y | EXP | 365 | 01/21/2021 | 03/16/2021 | 54 | 0 | 54 |  |  | 5/6/2021 | Connected |  | N
National Grid | FALL RIVER | 178316 | 02723 | 7.6 |  |  | Solar |  | 05_05_7L4 | 02/26/2018 | 02/26/2018 | 3 | 3 | 0 | 03/16/2018 | 03/16/2018 | 156 | 3 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2018 |  | 3/4/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 223164 | 01581 | 99.9 |  |  | Solar |  | 05_14_57L4 | 04/29/2019 | 05/16/2019 | 12 | 8 | 4 | 05/17/2019 | 05/17/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/21/2021 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  | 3/30/2021 | Connected |  | N
National Grid | BEVERLY | 423112 | 01915 | 7.6 |  |  | Solar |  | 05_14_73L2 | 04/11/2022 | 04/12/2022 | 1 | 0 | 1 | 04/13/2022 | 04/13/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 384623 | 02769 | 400 |  |  | Solar |  | 05_14_92L2 | 08/11/2022 | 10/05/2022 | 38 | 28 | 10 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 178232 | 01886 | 43.2 |  |  | Solar |  | 05_01_24W5 | 01/05/2018 | 01/05/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2018 |  | 1/13/2019 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N
National Grid | WESTFORD | 176592 | 01886 | 10 |  |  | Solar |  | 05_01_412L4 | 10/08/2015 | 10/08/2015 | 1 | 1 | 0 | 10/13/2015 | 10/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/08/2015 | 10/14/2016 | Y | EXP | 347 | 08/31/2016 | 10/28/2016 | 40 | 0 | 40 | 11/2/2015 | 11/2/2015 | 11/2/2016 | Connected |  | N
National Grid | BILLERICA | 721649 | 01821 | 2.6 |  |  | Solar |  | 05_05_335W2 | 09/29/2025 | 10/10/2025 | 3 | 0 | 3 | 10/30/2025 | 10/30/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 178081 | 01606 | 10 |  |  | Solar |  | 05_05_115W45 | 05/08/2017 | 05/08/2017 | 6 | 6 | 0 | 05/17/2017 | 05/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 | 05/08/2017 | 5/14/2018 | Y | EXP | 361 | 10/23/2017 | 11/09/2017 | 8 | 0 | 8 | 11/9/2017 | 11/9/2017 | 11/28/2017 | Connected |  | N
National Grid | DUDLEY | 176745 | 01571 | 50.4 |  |  | Solar |  | 05_05_312W4 | 11/02/2015 | 11/02/2015 | 3 | 3 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 |  | 11/8/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 1/4/2017 | 1/4/2017 | 1/6/2017 | Connected |  | N
National Grid | MENDON | 312832 | 01756 | 10 |  |  | Solar |  | 05_12_51T1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 | 09/15/2020 | 10/14/2021 | Y | EXP | 365 | 02/05/2021 | 03/05/2021 | 28 | 0 | 28 |  |  | 3/16/2021 | Connected |  | N
National Grid | WESTPORT | 194753 | 02790 | 3060 |  |  | Solar |  | 05_05_7L4 | 08/30/2018 | 09/25/2018 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 10/23/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 08/30/2018 | 2/23/2026 | Y | STD | 442 | 06/13/2025 | 12/17/2025 | 188 | 9 | 179 |  |  | 12/30/2025 | Connected |  | N
National Grid | WESTBOROUGH | 264770 | 01581 | 9.86 |  |  | Solar |  | 05_14_57L4 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2020 | Connected |  | N
National Grid | BEVERLY | 437862 | 01915 | 7.6 |  |  | Solar |  | 05_14_73L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 204 | 184 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 448098 | 02769 | 280 |  |  | Solar |  | 05_14_92L2 | 04/13/2023 | 08/09/2023 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2023 | 09/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 226537 | 01879 | 4405 |  |  | Solar |  | 05_01_24W5 | 05/20/2019 | 05/31/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2019 | 06/27/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 678608 | 01863 | 15.925 |  |  | Solar |  | 05_07_6W1 | 03/17/2025 | 04/03/2025 | 7 | 4 | 3 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 03/17/2025 | 6/4/2026 | Y | EXP | 365 | 09/03/2025 | 11/20/2025 | 79 | 0 | 79 |  |  | 12/26/2025 | Connected |  | N
National Grid | BILLERICA | 723275 | 01821 | 11.6 |  |  | Solar |  | 05_05_335W2 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 54 | 34 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 178427 | 01606 | 42 |  |  | Solar |  | 05_05_115W45 | 01/18/2018 | 01/18/2018 | 15 | 0 | 15 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/23/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 8/15/2018 | Connected |  | N
National Grid | DUDLEY | 178005 | 01571 | 15.2 |  |  | Solar |  | 05_05_312W4 | 04/27/2017 | 04/27/2017 | 8 | 8 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2017 |  | 5/2/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 8/24/2017 | 8/24/2017 | 8/29/2017 | Connected |  | N
National Grid | MILFORD | 325210 | 01757 | 0 |  |  | Solar |  | 05_12_51T1 | 12/02/2020 | 01/04/2021 | 21 | 18 | 3 | 01/05/2021 | 01/05/2021 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 3/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2021 | Connected |  | N
National Grid | FALL RIVER | 257553 | 02721 | 8.64 |  |  | Solar |  | 05_05_7L4 | 03/17/2020 | 04/03/2020 | 12 | 8 | 4 | 04/06/2020 | 04/06/2020 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 385677 | 01581 | 3.8 |  |  | Solar |  | 05_14_57L4 | 02/07/2022 | 03/02/2022 | 17 | 16 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  | 4/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | N
National Grid | ESSEX | 442456 | 01929 | 7.6 |  |  | Solar |  | 05_14_73L2 | 07/20/2022 | 07/21/2022 | 1 | 0 | 1 | 07/22/2022 | 07/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 470694 | 02771 | 3.8 |  |  | Solar |  | 05_14_92L2 | 11/11/2022 | 11/17/2022 | 4 | 0 | 4 | 11/18/2022 | 11/18/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/11/2022 | 4/25/2024 | Y | EXP | 365 | 04/05/2023 | 04/25/2023 | 21 | 0 | 21 |  |  | 5/2/2023 | Connected |  | N
National Grid | WESTFORD | 177304 | 01886 | 650 |  |  | Solar |  | 05_07_913W17 | 11/15/2016 | 11/15/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 12/20/2016 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2017 | 11/15/2016 | 7/10/2018 | Y | STD | 441 | 10/09/2017 | 07/02/2018 | 266 | 0 | 266 |  |  | 7/9/2018 | Connected |  | N
National Grid | WESTFORD | 679356 | 01886 | 3.8 |  |  | Solar |  | 05_07_6W1 | 03/20/2025 | 07/10/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 03/20/2025 | 9/10/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | BILLERICA | 177589 | 01821 | 7.6 |  |  | Solar |  | 05_05_335W2 | 05/18/2017 | 05/18/2017 | 11 | 11 | 0 | 06/06/2017 | 06/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 | 05/18/2017 | 5/24/2018 | Y | EXP | 350 | 08/29/2017 | 10/12/2017 | 30 | 0 | 30 | 11/8/2017 | 11/8/2017 | 11/28/2017 | Connected |  | N
National Grid | WORCESTER | 192209 | 01606 | 17.6 |  |  | Solar |  | 05_05_115W45 | 07/31/2018 | 08/30/2018 | 12 | 2 | 10 | 08/31/2018 | 08/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 07/31/2018 | 10/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | DUDLEY | 178334 | 01571 | 10 |  |  | Solar |  | 05_05_312W4 | 11/15/2017 | 11/15/2017 | 70 | 59 | 11 | 03/09/2018 | 03/09/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 11/22/2018 | N | EXP | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 205636 | 01757 | 13.8 |  |  | Solar |  | 05_07_97W1 | 01/29/2019 | 01/30/2019 | 0 | 0 | 0 | 01/31/2019 | 01/31/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 | 01/29/2019 | 10/23/2020 | Y | EXP | 434 | 11/07/2019 | 01/16/2020 | 70 | 0 | 70 |  |  | 10/5/2020 | Connected |  | N
National Grid | FALL RIVER | 307102 | 02723 | 17.04 |  |  | Solar |  | 05_05_7L4 | 08/17/2020 | 08/27/2020 | 8 | 8 | 0 | 08/28/2020 | 08/28/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2021 | Connected |  | N
National Grid | WESTBOROUGH | 643818 | 01581 | 9.75 |  |  | Solar |  | 05_14_57L4 | 09/30/2024 | 10/21/2024 | 3 | 1 | 2 | 10/22/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | GLOUCESTER | 445187 | 01930 | 15.08 |  |  | Solar |  | 05_14_73L2 | 07/18/2022 | 08/03/2022 | 13 | 11 | 2 | 08/04/2022 | 08/04/2022 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 07/18/2022 | 10/1/2023 | Y | EXP | 365 | 10/19/2022 | 11/09/2022 | 22 | 0 | 22 |  |  | 11/29/2022 | Connected |  | N
National Grid | REHOBOTH | 610419 | 02769 | 23 |  |  | Solar |  | 05_14_92L2 | 05/13/2024 | 05/20/2024 | 5 | 1 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N
National Grid | WESTFORD | 178049 | 01886 | 56 |  |  | Solar |  | 05_07_913W17 | 05/05/2017 | 05/05/2017 | 43 | 42 | 1 | 07/10/2017 | 07/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2017 |  | 5/13/2018 | N | EXP | 300 |  |  | 0 | 0 | 0 | 9/8/2017 | 9/8/2017 | 10/30/2017 | Connected |  | N
National Grid | WESTFORD | 676966 | 01886 | 999.9 |  |  | Solar |  | 05_07_6W2 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 241367 | 01821 | 10 |  |  | Solar |  | 05_05_335W2 | 07/08/2019 | 07/17/2019 | 7 | 7 | 0 | 07/18/2019 | 07/18/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 | 07/08/2019 | 3/17/2020 | Y | EXP | 230 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 192619 | 01606 | 10 |  |  | Solar |  | 05_05_115W45 | 08/06/2018 | 08/30/2018 | 7 | 2 | 5 | 08/31/2018 | 08/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 08/06/2018 | 9/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | DUDLEY | 178679 | 01571 | 15.2 |  |  | Solar |  | 05_05_312W4 | 04/11/2018 | 04/11/2018 | 16 | 0 | 16 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | MILFORD | 208541 | 01757 | 10 |  |  | Solar |  | 05_07_97W1 | 02/14/2019 | 02/21/2019 | 4 | 4 | 0 | 02/22/2019 | 02/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 215 | 06/21/2019 | 08/09/2019 | 49 | 0 | 49 |  |  | 8/21/2019 | Connected |  | N
National Grid | FALL RIVER | 321328 | 02721 | 7.6 |  |  | Solar |  | 05_05_7L4 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 12/22/2022 | Y | EXP | 365 | 03/03/2022 | 03/22/2022 | 20 | 0 | 20 |  |  | 5/31/2022 | Connected |  | Y
National Grid | WESTBOROUGH | 656473 | 01581 | 8.41 |  |  | Solar |  | 05_14_57L4 | 12/06/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | BEVERLY | 445349 | 01915 | 7.6 |  |  | Solar |  | 05_14_73L2 | 07/19/2022 | 07/22/2022 | 4 | 3 | 1 | 07/25/2022 | 07/25/2022 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 637600 | 02769 | 320 |  |  | Solar |  | 05_14_92L2 | 11/01/2024 | 05/19/2025 | 131 | 121 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 208597 | 01886 | 1000 |  |  | Solar |  | 05_07_913W17 | 03/22/2019 | 04/23/2019 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/15/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 177666 | 01886 | 3.8 |  |  | Solar |  | 05_07_6W2 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 207 | 0 | 207 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/30/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 526856 | 01821 | 10 |  |  | Solar |  | 05_05_335W2 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 197978 | 01606 | 6 |  |  | Solar |  | 05_05_115W45 | 10/08/2018 | 01/03/2019 | 43 | 41 | 2 | 01/04/2019 | 01/04/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 190317 | 02188 | 3.8 |  |  | Solar |  | 05_05_312W4 | 07/10/2018 | 08/15/2018 | 9 | 2 | 7 | 08/16/2018 | 08/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 208421 | 01757 | 10 |  |  | Solar |  | 05_07_97W1 | 03/18/2019 | 03/19/2019 | 0 | 0 | 0 | 03/20/2019 | 03/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 | 03/18/2019 | 9/2/2020 | Y | EXP | 527 | 03/04/2020 | 05/12/2020 | 69 | 0 | 69 |  |  | 5/13/2020 | Connected |  | N
National Grid | FALL RIVER | 326927 | 02721 | 7.6 |  |  | Solar |  | 05_05_7L4 | 11/18/2020 | 11/19/2020 | 0 | 0 | 0 | 11/20/2020 | 11/20/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2020 | 11/18/2020 | 8/13/2022 | Y | EXP | 435 | 04/08/2021 | 04/23/2021 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 721432 | 01568 | 7.6 |  |  | Solar |  | 05_14_58L1 | 09/24/2025 | 10/03/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GLOUCESTER | 697254 | 01930 | 13.8 |  |  | Solar |  | 05_09_1109W2 | 06/16/2025 | 07/02/2025 | 1 | 0 | 1 | 07/11/2025 | 07/11/2025 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 649338 | 02771 | 7.6 |  |  | Solar |  | 05_14_92L2 | 11/04/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 1/2/2026 | Y | EXP | 365 | 03/04/2025 | 04/18/2025 | 46 | 0 | 46 |  |  | 5/2/2025 | Connected |  | N
National Grid | WESTFORD | 225530 | 01886 | 3.8 |  |  | Solar |  | 05_07_913W17 | 03/05/2020 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 199236 | 01886 | 10 |  |  | Solar |  | 05_07_6W2 | 11/13/2018 | 01/28/2019 | 49 | 45 | 4 | 01/29/2019 | 01/29/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 563998 | 01821 | 6.912 |  |  | Solar |  | 05_05_335W2 | 11/06/2023 | 11/13/2023 | 4 | 2 | 2 | 11/14/2023 | 11/14/2023 | 128 | 66 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 205831 | 02072 | 4.8 |  |  | Solar |  | 05_05_115W45 | 02/27/2019 | 03/15/2019 | 12 | 11 | 1 | 03/18/2019 | 03/18/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 02/27/2019 | 11/13/2019 | Y | EXP | 236 | 05/08/2019 | 06/06/2019 | 29 | 0 | 29 |  |  | 7/5/2019 | Connected |  | N
National Grid | WEYMOUTH | 194239 | 02188 | 15.2 |  |  | Solar |  | 05_05_312W4 | 08/22/2018 | 09/19/2018 | 19 | 19 | 0 | 09/20/2018 | 09/20/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 229376 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W1 | 03/05/2020 |  | 170 | 126 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 335356 | 02721 | 24.36 |  |  | Solar |  | 05_05_7L4 | 05/05/2021 | 05/07/2021 | 1 | 0 | 1 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | UPTON | 726691 | 01568 | 15.2 |  |  | Solar |  | 05_14_58L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 696964 | 02368 | 25 |  |  | Solar |  | 05_09_1109W2 | 06/08/2025 | 06/11/2025 | 3 | 0 | 3 | 06/12/2025 | 06/12/2025 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | Y
National Grid | REHOBOTH | 652994 | 02769 | 7.6 |  |  | Solar |  | 05_14_92L2 | 11/08/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 | 11/08/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTFORD | 412720 | 01886 | 243.3 |  |  | Solar |  | 05_07_913W17 | 02/16/2022 | 03/31/2022 | 30 | 21 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 | 02/16/2022 | 5/21/2025 | Y | STD | 560 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 205952 | 01863 | 13.6 |  |  | Solar |  | 05_07_6W2 | 02/14/2019 | 02/20/2019 | 2 | 1 | 1 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 220 | 05/16/2019 | 06/06/2019 | 21 | 0 | 21 |  |  | 8/16/2019 | Connected |  | N
National Grid | BILLERICA | 556107 | 01821 | 3.84 |  |  | Solar |  | 05_05_335W2 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 | 09/22/2023 | 11/22/2024 | Y | EXP | 365 | 03/05/2024 | 04/30/2024 | 57 | 0 | 57 |  |  | 5/1/2024 | Connected |  | N
National Grid | STOUGHTON | 304302 | 02072 | 3.8 |  |  | Solar |  | 05_05_115W45 | 08/07/2020 | 08/11/2020 | 1 | 0 | 1 | 08/12/2020 | 08/12/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 207296 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 01/28/2019 | 02/11/2019 | 9 | 0 | 9 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 01/28/2019 | 9/23/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 229007 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 10/15/2019 | 10/22/2019 | 4 | 0 | 4 | 10/23/2019 | 10/23/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 339999 | 02721 | 15.2 |  |  | Solar |  | 05_05_7L4 | 02/11/2021 | 02/23/2021 | 7 | 7 | 0 | 02/24/2021 | 02/24/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2021 | Connected |  | N
National Grid | WESTBOROUGH | 178428 | 01581 | 22.72 |  |  | Solar |  | 05_14_58L1 | 03/05/2018 | 03/05/2018 | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 3/11/2019 | N | EXP | 80 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 696836 | 02368 | 15.2 |  |  | Solar |  | 05_09_1109W2 | 06/06/2025 | 06/12/2025 | 3 | 0 | 3 | 06/13/2025 | 06/13/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | SEEKONK | 662574 | 02771 | 7.6 |  |  | Solar |  | 05_14_92L2 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 466090 | 01886 | 10 |  |  | Solar |  | 05_07_913W17 | 10/13/2022 | 10/18/2022 | 3 | 0 | 3 | 10/19/2022 | 10/19/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 11/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N
National Grid | WESTFORD | 296209 | 01886 | 12 |  |  | Solar |  | 05_07_6W2 | 06/12/2020 | 06/29/2020 | 10 | 6 | 4 | 06/30/2020 | 06/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 10/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 601386 | 01821 | 14.175 |  |  | Solar |  | 05_05_335W2 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/15/2024 | 5/6/2025 | Y | EXP | 365 | 05/18/2024 | 06/26/2024 | 40 | 0 | 40 |  |  | 7/4/2024 | Connected |  | N
National Grid | STOUGHTON | 377985 | 02072 | 6 |  |  | Solar |  | 05_05_115W45 | 09/10/2021 | 12/07/2021 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 | 09/10/2021 | 5/25/2023 | Y | EXP | 365 | 04/12/2022 | 05/18/2022 | 37 | 0 | 37 |  |  | 6/29/2022 | Connected |  | N
National Grid | WEYMOUTH | 221730 | 02191 | 0 |  |  | Solar |  | 05_05_312W4 | 06/19/2019 | 06/26/2019 | 3 | 0 | 3 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/19/2019 | 11/8/2020 | Y | EXP | 365 | 07/07/2020 | 10/10/2020 | 96 | 5 | 91 |  |  | 11/12/2020 | Connected |  | N
National Grid | MILFORD | 234729 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 08/02/2019 | 08/05/2019 | 0 | 0 | 0 | 08/06/2019 | 08/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 | 08/02/2019 | 10/2/2020 | Y | EXP | 365 | 03/28/2020 | 05/08/2020 | 41 | 0 | 41 |  |  | 7/16/2020 | Connected |  | N
National Grid | FALL RIVER | 342021 | 02721 | 18 |  |  | Solar |  | 05_05_7L4 | 02/12/2021 | 02/25/2021 | 7 | 3 | 4 | 02/26/2021 | 02/26/2021 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | WESTBOROUGH | 223575 | 01581 | 0 |  |  | Solar |  | 05_14_58L1 | 04/29/2019 | 05/07/2019 | 5 | 0 | 5 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2019 |  | 4/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2020 | Connected |  | N
National Grid | RANDOLPH | 698403 | 02368 | 10.4 |  |  | Solar |  | 05_09_1109W2 | 06/13/2025 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 668829 | 02769 | 3.9 |  |  | Solar |  | 05_14_92L2 | 02/06/2025 | 02/28/2025 | 10 | 6 | 4 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | CHELMSFORD | 501289 | 01824 | 7.6 |  |  | Solar |  | 05_07_913W17 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 158 | 133 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EGREMONT | 410224 | 01258 | 15.2 |  |  | Solar |  | 05_07_6W2 | 02/03/2022 | 04/05/2022 | 43 | 25 | 18 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 640572 | 01821 | 5.76 |  |  | Solar |  | 05_05_335W2 | 09/16/2024 | 09/27/2024 | 1 | 0 | 1 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 401114 | 02072 | 0 |  |  | Other |  | 05_05_115W45 | 01/06/2022 | 01/31/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/02/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 230666 | 02191 | 0 |  |  | Solar |  | 05_05_312W4 | 05/24/2019 | 06/18/2019 | 15 | 10 | 5 | 06/19/2019 | 06/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  | 7/19/2019 | N | EXP | 25 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | MILFORD | 244985 | 01757 | 8.82 |  |  | Solar |  | 05_07_97W1 | 08/20/2019 | 08/23/2019 | 3 | 3 | 0 | 08/26/2019 | 08/26/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/20/2019 | 4/23/2020 | Y | EXP | 225 | 10/23/2019 | 11/08/2019 | 16 | 0 | 16 |  |  | 12/18/2019 | Connected |  | N
National Grid | FALL RIVER | 342835 | 02712 | 11.4 |  |  | Solar |  | 05_05_7L4 | 02/18/2021 | 02/25/2021 | 4 | 0 | 4 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  | 11/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N
National Grid | WESTBOROUGH | 258486 | 01581 | 10 |  |  | Solar |  | 05_14_58L1 | 10/05/2019 | 10/11/2019 | 4 | 0 | 4 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N
National Grid | RANDOLPH | 710770 | 02368 | 10 |  |  | Solar |  | 05_09_1109W2 | 08/08/2025 | 08/15/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 | 08/08/2025 | 10/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | REHOBOTH | 671980 | 02769 | 10 |  |  | Solar |  | 05_14_92L2 | 02/13/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 40 | 23 | 17 | 06/05/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 7/1/2025 | 02/13/2025 | 7/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | WESTFORD | 588598 | 01886 | 0 |  |  | Solar |  | 05_07_913W17 | 02/07/2024 | 02/29/2024 | 15 | 13 | 2 | 03/01/2024 | 03/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 | 02/07/2024 | 5/21/2025 | Y | EXP | 365 | 09/05/2024 | 10/03/2024 | 29 | 0 | 29 |  |  | 10/4/2024 | Connected |  | N
National Grid | SHEFFIELD | 481330 | 01257 | 15.2 |  |  | Solar |  | 05_07_6W2 | 11/30/2022 | 12/05/2022 | 3 | 2 | 1 | 12/06/2022 | 12/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 6/9/2025 | N | EXP | 730 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 647352 | 01821 | 7.6 |  |  | Solar |  | 05_05_335W2 | 10/17/2024 | 11/07/2024 | 15 | 13 | 2 | 11/08/2024 | 11/08/2024 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/17/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | STOUGHTON | 565509 | 02072 | 5 |  |  | Solar |  | 05_05_115W45 | 11/08/2023 | 11/29/2023 | 13 | 10 | 3 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 271250 | 02191 | 400 |  |  | Solar |  | 05_05_312W4 | 01/24/2020 | 01/31/2020 | 5 | 1 | 4 |  |  | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 01/24/2020 | 3/10/2022 | Y | STD | 408 | 08/05/2021 | 08/10/2021 | 6 | 0 | 6 |  |  | 3/7/2022 | Connected |  | N
National Grid | MILFORD | 249024 | 01757 | 6 |  |  | Solar |  | 05_07_97W1 | 09/25/2019 | 10/16/2019 | 14 | 14 | 0 | 10/17/2019 | 10/17/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 9/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | WESTPORT | 355588 | 02790 | 8.7 |  |  | Solar |  | 05_05_7L4 | 05/25/2021 | 12/22/2021 | 5 | 2 | 3 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 | 05/25/2021 | 3/1/2023 | Y | EXP | 365 | 12/24/2021 | 02/24/2022 | 63 | 0 | 63 |  |  | 3/5/2022 | Connected |  | N
National Grid | UPTON | 290418 | 01568 | 10 |  |  | Solar |  | 05_14_58L1 | 05/04/2020 | 05/11/2020 | 4 | 0 | 4 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2020 | Connected |  | N
National Grid | RANDOLPH | 721721 | 02368 | 20 |  |  | Solar |  | 05_09_1109W2 | 09/24/2025 | 09/26/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | REHOBOTH | 680282 | 02769 | 10 |  |  | Solar |  | 05_14_92L2 | 03/25/2025 | 04/11/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/23/2025 | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 | 9/10/2025 | 03/25/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | WESTFORD | 666358 | 01886 | 5.76 |  |  | Solar |  | 05_07_913W17 | 01/17/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/17/2025 | 3/19/2026 | Y | EXP | 365 | 06/21/2025 | 06/20/2025 | 0 | 0 | 0 |  |  | 7/31/2025 | Connected |  | N
National Grid | EGREMONT | 489983 | 01258 | 15.2 |  |  | Solar |  | 05_07_6W2 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | BILLERICA | 668261 | 01821 | 11.5 |  |  | Solar |  | 05_05_335W2 | 02/04/2025 | 02/07/2025 | 3 | 0 | 3 | 02/10/2025 | 02/10/2025 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | STOUGHTON | 570860 | 02072 | 6 |  |  | Solar |  | 05_05_115W45 | 11/20/2023 | 12/05/2023 | 11 | 7 | 4 | 12/06/2023 | 12/06/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 11/20/2023 | 4/1/2025 | Y | EXP | 365 | 05/29/2024 | 07/25/2024 | 58 | 0 | 58 |  |  | 7/30/2024 | Connected |  | N
National Grid | WEYMOUTH | 286836 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 04/07/2020 | 04/08/2020 | 0 | 0 | 0 | 04/09/2020 | 04/09/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/7/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 276855 | 01757 | 10 |  |  | Solar |  | 05_07_97W1 | 03/06/2020 | 04/24/2020 | 36 | 35 | 1 | 04/27/2020 | 04/27/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 03/06/2020 | 3/9/2021 | Y | EXP | 365 | 07/29/2020 | 08/28/2020 | 30 | 0 | 30 |  |  | 10/7/2020 | Connected |  | N
National Grid | FALL RIVER | 372768 | 02721 | 15.2 |  |  | Solar |  | 05_05_7L4 | 07/29/2021 |  | 45 | 37 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 292702 | 01581 | 0 |  |  | Solar |  | 05_14_58L1 | 05/20/2020 | 05/22/2020 | 1 | 0 | 1 | 05/26/2020 | 05/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N
National Grid | RANDOLPH | 641155 | 02368 | 2500 |  |  | Solar |  | 05_09_1109W3 | 11/04/2024 | 01/30/2025 | 58 | 48 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2025 | 03/06/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | REHOBOTH | 706418 | 02769 | 23 |  |  | Solar |  | 05_14_92L2 | 07/29/2025 | 08/04/2025 | 4 | 0 | 4 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | WESTFORD | 684049 | 01886 | 22.8 |  |  | Solar |  | 05_07_913W17 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | Y
National Grid | SHEFFIELD | 494588 | 01257 | 9.86 |  |  | Solar |  | 05_07_6W2 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 6/22/2024 | Y | EXP | 365 | 06/09/2023 | 06/22/2023 | 14 | 0 | 14 |  |  | 7/29/2023 | Connected |  | N
National Grid | BILLERICA | 689317 | 01821 | 10 |  |  | Solar |  | 05_05_335W2 | 05/27/2025 | 06/03/2025 | 4 | 1 | 3 | 06/04/2025 | 06/04/2025 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 647595 | 02072 | 7.6 |  |  | Solar |  | 05_05_115W45 | 10/16/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 334005 | 02191 | 7.6 |  |  | Solar |  | 05_05_312W4 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 5/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2021 | Connected |  | N
National Grid | MILFORD | 323027 | 01757 | 9.8 |  |  | Solar |  | 05_07_97W1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/24/2020 | 11/23/2022 | Y | EXP | 365 | 08/18/2021 | 10/12/2021 | 54 | 3 | 51 |  |  | 12/22/2021 | Connected |  | N
National Grid | FALL RIVER | 384910 | 02724 | 9.86 |  |  | Solar |  | 05_05_7L4 | 09/28/2021 | 01/06/2022 | 9 | 7 | 2 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | UPTON | 306363 | 01568 | 0 |  |  | Battery Add-On |  | 05_14_58L1 | 08/12/2020 | 08/14/2020 | 1 | 1 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | RANDOLPH | 711945 | 02368 | 10 |  |  | Solar |  | 05_09_1109W3 | 08/13/2025 | 09/03/2025 | 5 | 0 | 5 | 09/30/2025 | 09/30/2025 | 25 | 10 | 15 | 11/20/2025 | 12/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 12/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REHOBOTH | 710015 | 02769 | 15.2 |  |  | Solar |  | 05_14_92L2 | 08/06/2025 | 08/12/2025 | 3 | 1 | 2 | 08/13/2025 | 08/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | WESTFORD | 684887 | 01886 | 9.423 |  |  | Solar |  | 05_07_913W18 | 04/14/2025 | 10/10/2025 | 6 | 4 | 2 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EGREMONT | 515717 | 01258 | 7.6 |  |  | Solar |  | 05_07_6W2 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | BILLERICA | 676136 | 01821 | 17.16 |  |  | Solar |  | 05_05_335W3 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STOUGHTON | 643993 | 02072 | 10 |  |  | Solar |  | 05_09_523L1 | 10/01/2024 | 10/10/2024 | 5 | 3 | 2 | 10/11/2024 | 10/11/2024 | 20 | 3 | 17 | 11/22/2024 | 12/29/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 12/29/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | WEYMOUTH | 449344 | 02191 | 3.8 |  |  | Solar |  | 05_05_312W4 | 08/04/2022 | 08/09/2022 | 3 | 0 | 3 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | MILFORD | 324428 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 11/30/2020 | 4/30/2022 | Y | EXP | 365 | 10/07/2021 | 10/12/2021 | 5 | 0 | 5 |  |  | 3/4/2022 | Connected |  | N
National Grid | FALL RIVER | 430893 | 02721 | 6.67 |  |  | Solar |  | 05_05_7L4 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 7/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | WESTBOROUGH | 321713 | 01581 | 16 |  |  | Solar |  | 05_14_58L1 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 4/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | RANDOLPH | 719256 | 02368 | 22.8 |  |  | Solar |  | 05_09_1109W3 | 09/15/2025 | 09/19/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | REHOBOTH | 644899 | 02769 | 16.53 |  |  | Solar |  | 05_09_909W3 | 10/03/2024 | 10/16/2024 | 8 | 6 | 2 | 10/17/2024 | 10/17/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | WESTFORD | 715057 | 01886 | 6.46 |  |  | Solar |  | 05_07_913W18 | 08/28/2025 | 09/18/2025 | 3 | 0 | 3 | 09/26/2025 | 09/26/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GREAT BARRINGTON | 520867 | 01230 | 10.15 |  |  | Solar |  | 05_07_6W2 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | BILLERICA | 710659 | 01821 | 23 |  |  | Solar |  | 05_05_335W3 | 08/12/2025 | 08/18/2025 | 4 | 0 | 4 | 08/19/2025 | 08/19/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | STOUGHTON | 666039 | 02072 | 15.2 |  |  | Solar |  | 05_09_523L1 | 01/15/2025 | 01/22/2025 | 6 | 2 | 4 | 06/23/2025 | 06/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | WEYMOUTH | 376567 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 09/01/2021 | 01/24/2022 | 98 | 92 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | MILFORD | 325702 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 12/07/2020 | 12/08/2021 | 4 | 0 | 4 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/07/2020 | 8/8/2023 | Y | EXP | 365 | 03/31/2022 | 04/25/2022 | 26 | 0 | 26 |  |  | 4/10/2023 | Connected |  | N
National Grid | FALL RIVER | 432869 | 02721 | 7.6 |  |  | Solar |  | 05_05_7L4 | 07/04/2022 | 07/06/2022 | 2 | 0 | 2 | 07/07/2022 | 07/07/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 07/04/2022 | 8/15/2024 | Y | EXP | 365 | 10/14/2022 | 12/21/2022 | 69 | 0 | 69 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 344742 | 01568 | 15.2 |  |  | Solar |  | 05_14_58L1 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 724129 | 02368 | 23.034 |  |  | Solar |  | 05_09_1109W3 | 10/07/2025 | 10/13/2025 | 3 | 1 | 2 | 10/14/2025 | 10/14/2025 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 645387 | 02769 | 10.725 |  |  | Solar |  | 05_09_909W3 | 10/08/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/08/2024 | 12/8/2025 | Y | EXP | 365 | 02/13/2025 | 02/25/2025 | 13 | 0 | 13 |  |  | 2/28/2025 | Connected |  | N
National Grid | WESTFORD | 720064 | 01886 | 38 |  |  | Solar |  | 05_07_913W18 | 09/18/2025 | 09/25/2025 | 5 | 3 | 2 | 09/26/2025 | 09/26/2025 | 65 | 39 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GREAT BARRINGTON | 649005 | 01230 | 11.4 |  |  | Solar |  | 05_07_6W2 | 10/23/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/23/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | BILLERICA | 717407 | 01821 | 11.52 |  |  | Solar |  | 05_05_335W3 | 09/08/2025 | 09/26/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOUGHTON | 670416 | 02072 | 7.6 |  |  | Solar |  | 05_09_523L1 | 02/06/2025 | 02/21/2025 | 5 | 1 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | WEYMOUTH | 394972 | 02191 | 7.6 |  |  | Solar |  | 05_05_312W4 | 02/11/2022 | 02/14/2022 | 1 | 0 | 1 | 02/15/2022 | 02/15/2022 | 102 | 90 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | MILFORD | 330177 | 01757 | 12 |  |  | Solar |  | 05_07_97W1 | 12/07/2020 | 04/01/2021 | 82 | 79 | 3 | 04/02/2021 | 04/02/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 6/8/2022 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 476815 | 02790 | 13 |  |  | Solar |  | 05_05_7L4 | 12/02/2022 | 12/07/2022 | 3 | 0 | 3 | 12/08/2022 | 12/08/2022 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 | 12/02/2022 | 8/11/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | WESTBOROUGH | 351803 | 01581 | 10 |  |  | Solar |  | 05_14_58L1 | 04/09/2021 | 04/12/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N
National Grid | RANDOLPH | 725591 | 02368 | 15.2 |  |  | Solar |  | 05_09_1109W3 | 11/19/2025 | 11/24/2025 | 3 | 0 | 3 | 11/25/2025 | 11/25/2025 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REHOBOTH | 645594 | 02769 | 10 |  |  | Solar |  | 05_09_909W3 | 10/08/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 177500 | 01886 | 6 |  |  | Solar |  | 05_07_913W18 | 03/03/2017 | 03/03/2017 | 45 | 38 | 7 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2017 | 03/03/2017 | 3/11/2018 | Y | EXP | 306 | 01/12/2018 | 02/16/2018 | 24 | 0 | 24 | 2/28/2018 | 2/28/2018 | 3/6/2018 | Connected |  | N
National Grid | EGREMONT | 662609 | 01252 | 3.77 |  |  | Solar |  | 05_07_6W2 | 12/31/2024 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | BILLERICA | 717022 | 01821 | 4.94 |  |  | Solar |  | 05_05_335W3 | 09/05/2025 | 09/24/2025 | 1 | 0 | 1 | 10/22/2025 | 10/22/2025 | 39 | 28 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOUGHTON | 687300 | 02072 | 10 |  |  | Solar |  | 05_09_523L1 | 04/24/2025 |  | 61 | 58 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 393761 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 11/05/2021 | 12/08/2021 | 2 | 0 | 2 | 11/10/2021 | 11/10/2021 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 329783 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W1 | 01/18/2021 | 01/27/2021 | 7 | 4 | 3 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 01/18/2021 | 1/27/2022 | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 9/1/2021 | Connected |  | N
National Grid | PALMER | 497589 | 01080 | 10 |  |  | Solar |  | 05_05_7L4 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/10/2023 | 6/8/2024 | Y | EXP | 365 | 05/06/2023 | 06/08/2023 | 34 | 0 | 34 |  |  | 7/18/2023 | Connected |  | N
National Grid | WESTBOROUGH | 373166 | 01581 | 15.2 |  |  | Solar |  | 05_14_58L1 | 07/30/2021 | 09/08/2021 | 27 | 25 | 2 | 09/09/2021 | 09/09/2021 | 85 | 60 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2022 |  | 1/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2022 | Connected |  | N
National Grid | RANDOLPH | 731155 | 02368 | 27.188 |  |  | Solar |  | 05_09_1109W3 | 11/07/2025 | 11/10/2025 | 1 | 0 | 1 | 11/12/2025 | 11/12/2025 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 650879 | 02769 | 23 |  |  | Solar |  | 05_09_909W3 | 10/30/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/30/2024 | 1/31/2026 | Y | EXP | 365 | 05/15/2025 | 06/16/2025 | 33 | 0 | 33 |  |  | 6/17/2025 | Connected |  | N
National Grid | WESTFORD | 246680 | 01886 | 99.9 |  |  | Solar |  | 05_07_913W18 | 08/20/2019 | 03/02/2020 | 21 | 17 | 4 | 03/03/2020 | 03/03/2020 | 170 | 100 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2021 | Connected |  | Y
National Grid | EGREMONT | 175158 | 01258 | 95 |  |  | Solar |  | 05_07_70J1 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 | 08/30/2012 | 08/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 11/1/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 6/18/2013 | Connected |  | N
National Grid | GOSHEN | 720448 | 01032 | 10 |  |  | Solar |  | 05_05_335W3 | 09/22/2025 | 10/03/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 09/22/2025 | 11/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STOUGHTON | 659910 | 02072 | 7.6 |  |  | Solar |  | 05_09_523L2 | 12/11/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 12/11/2024 | 2/13/2026 | Y | EXP | 365 | 05/16/2025 | 10/03/2025 | 141 | 0 | 141 |  |  |  | Pending Withdraw |  | Y
National Grid | WEYMOUTH | 423473 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 04/12/2022 | 04/13/2022 | 1 | 0 | 1 | 04/14/2022 | 04/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 5/27/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 336662 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 02/05/2021 | 02/12/2021 | 5 | 5 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/05/2021 | 2/11/2022 | Y | EXP | 365 | 04/17/2021 | 05/10/2021 | 23 | 0 | 23 |  |  | 5/12/2021 | Connected |  | N
National Grid | PALMER | 531460 | 01080 | 15 |  |  | Solar |  | 05_05_7L4 | 07/03/2023 | 07/05/2023 | 2 | 1 | 1 | 07/06/2023 | 07/06/2023 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2023 | Connected |  | N
National Grid | WESTBOROUGH | 406249 | 01581 | 8.7 |  |  | Solar |  | 05_14_58L1 | 01/12/2022 | 01/13/2022 | 1 | 0 | 1 | 01/14/2022 | 01/14/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 01/12/2022 | 5/21/2023 | Y | EXP | 365 | 04/22/2022 | 05/20/2022 | 29 | 0 | 29 |  |  | 8/24/2022 | Connected |  | N
National Grid | RANDOLPH | 174135 | 02368 | 12 |  |  | Solar |  | 05_09_1109W3 | 05/08/2012 | 05/08/2012 | 7 | 0 | 7 | 05/21/2012 | 05/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2012 |  | 7/10/2012 | N | EXP | -104 |  |  | 0 | 0 | 0 | 8/29/2012 | 8/29/2012 | 11/20/2012 | Connected |  | N
National Grid | SEEKONK | 659585 | 02771 | 11.2 |  |  | Solar |  | 05_09_909W3 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTFORD | 318701 | 01886 | 7.6 |  |  | Solar |  | 05_07_913W18 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 |  | Y | EXP | 365 | 03/17/2021 | 04/06/2021 | 20 | 0 | 20 |  |  | 8/15/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 713540 | 01230 | 5.76 |  |  | Solar |  | 05_07_712J1 | 08/20/2025 | 09/19/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 | 08/20/2025 | 1/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WILLIAMSBURG | 174772 | 01096 | 60 |  |  | Solar |  | 05_05_335W3 | 01/17/2013 | 01/17/2013 | 9 | 7 | 2 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2013 |  | 4/15/2013 | N | EXP | -1 |  |  | 0 | 0 | 0 | 7/29/2013 | 7/29/2013 | 8/16/2013 | Connected |  | N
National Grid | STOUGHTON | 174902 | 02072 | 1000 |  |  | Solar |  | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 | 02/15/2014 | 03/26/2014 | 25 | 0 | 25 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | WEYMOUTH | 436643 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 06/09/2022 | 06/13/2022 | 2 | 0 | 2 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2022 | Connected |  | N
National Grid | UPTON | 342575 | 01568 | 7.6 |  |  | Solar |  | 05_07_97W1 | 02/24/2021 | 03/02/2021 | 3 | 0 | 3 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 544824 | 01095 | 7.6 |  |  | Solar |  | 05_05_7L4 | 08/02/2023 | 08/07/2023 | 3 | 0 | 3 | 08/08/2023 | 08/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 08/02/2023 | 10/9/2024 | Y | EXP | 365 | 11/10/2023 | 01/05/2024 | 57 | 3 | 54 |  |  | 2/3/2024 | Connected |  | N
National Grid | WESTBOROUGH | 420189 | 01581 | 24.43 |  |  | Solar |  | 05_14_58L1 | 03/31/2022 | 04/06/2022 | 5 | 3 | 2 | 04/07/2022 | 04/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 |  | 4/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2022 | Connected |  | N
National Grid | RANDOLPH | 174186 | 02368 | 11.61 |  |  | Solar |  | 05_09_1109W3 | 10/31/2011 | 10/31/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2012 |  | 5/1/2012 | N | EXP | 41 |  |  | 0 | 0 | 0 | 5/17/2012 | 5/17/2012 | 7/16/2012 | Connected |  | N
National Grid | SEEKONK | 663177 | 02771 | 11.5 |  |  | Solar |  | 05_09_909W3 | 12/31/2024 | 01/27/2025 | 2 | 0 | 2 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 12/31/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | WESTFORD | 513459 | 01886 | 10 |  |  | Solar |  | 05_07_913W18 | 03/28/2023 | 03/29/2023 | 1 | 0 | 1 | 03/30/2023 | 03/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/28/2023 | 6/6/2024 | Y | EXP | 365 | 07/20/2023 | 08/11/2023 | 23 | 0 | 23 |  |  | 8/24/2023 | Connected |  | N
National Grid | LENOX | 715090 | 01240 | 3.8 |  |  | Solar |  | 05_07_712J1 | 08/28/2025 | 10/01/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 08/28/2025 | 12/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WILLIAMSBURG | 175586 | 01039 | 20 |  |  | Solar |  | 05_05_335W3 | 04/18/2014 | 04/18/2014 | 6 | 0 | 6 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2014 | 04/18/2014 | 6/30/2014 | Y | EXP | 45 |  |  | 0 | 0 | 0 | 5/29/2014 | 5/29/2014 | 7/14/2014 | Connected |  | N
National Grid | STOUGHTON | 174901 | 02072 | 1000 |  |  | Solar |  | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 |  |  | 0 | 0 | 0 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | WEYMOUTH | 470820 | 02191 | 15.2 |  |  | Solar |  | 05_05_312W4 | 10/24/2022 | 10/25/2022 | 1 | 0 | 1 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/24/2022 | 12/19/2023 | Y | EXP | 365 | 02/15/2023 | 04/27/2023 | 72 | 0 | 72 |  |  | 6/22/2023 | Connected |  | N
National Grid | UPTON | 366170 | 01568 | 6 |  |  | Solar |  | 05_07_97W1 | 06/25/2021 | 06/30/2021 | 4 | 2 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | Connected |  | N
National Grid | WILBRAHAM | 554638 | 01095 | 20 |  |  | Solar |  | 05_05_7L4 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 113 | 96 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2024 | Connected |  | N
National Grid | WESTBOROUGH | 421774 | 01581 | 15.2 |  |  | Solar |  | 05_14_58L1 | 05/04/2022 | 05/04/2022 | 0 | 0 | 0 | 05/05/2022 | 05/05/2022 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 05/04/2022 | 10/9/2023 | Y | EXP | 365 | 08/30/2022 | 09/24/2022 | 26 | 0 | 26 |  |  | 11/24/2022 | Connected |  | N
National Grid | RANDOLPH | 174715 | 02368 | 2000 |  |  | Solar |  | 05_09_1109W3 | 01/13/2014 | 01/13/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2014 | 02/10/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/29/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 669864 | 02769 | 10 |  |  | Solar |  | 05_09_909W3 | 02/13/2025 | 02/19/2025 | 3 | 0 | 3 | 02/20/2025 | 02/20/2025 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 02/13/2025 | 5/28/2026 | Y | EXP | 365 | 06/18/2025 | 06/30/2025 | 13 | 0 | 13 |  |  | 9/2/2025 | Connected |  | N
National Grid | CHELMSFORD | 523764 | 01824 | 10 |  |  | Solar |  | 05_07_913W18 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 | 05/17/2023 | 10/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | STOCKBRIDGE | 721528 | 01266 | 13.3 |  |  | Wind |  | 05_07_712J1 | 09/24/2025 | 10/09/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 45 | 24 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 175574 | 01062 | 490 |  |  | Solar |  | 05_05_335W3 | 12/05/2014 | 12/05/2014 | 4 | 1 | 3 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 12/05/2014 | 7/31/2015 | Y | EXP | 156 | 08/24/2015 | 11/16/2015 | 57 | 0 | 57 | 5/7/2015 | 5/7/2015 | 11/20/2015 | Connected |  | N
National Grid | STOUGHTON | 174900 | 02072 | 1000 |  |  | Solar |  | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 |  |  | 0 | 0 | 0 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | PEMBROKE | 479590 | 02359 | 7.6 |  |  | Solar |  | 05_05_312W4 | 01/05/2023 | 01/10/2023 | 3 | 0 | 3 | 01/11/2023 | 01/11/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | N
National Grid | UPTON | 392185 | 01568 | 6 |  |  | Solar |  | 05_07_97W1 | 11/18/2021 | 01/05/2022 | 3 | 0 | 3 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 2/9/2023 | Y | EXP | 365 | 01/19/2022 | 02/08/2022 | 21 | 0 | 21 |  |  | 2/12/2022 | Connected |  | N
National Grid | PALMER | 578325 | 01009 | 0 |  |  | Solar |  | 05_05_7L4 | 12/15/2023 | 12/21/2023 | 4 | 3 | 1 | 12/22/2023 | 12/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 462180 | 01581 | 13.63 |  |  | Solar |  | 05_14_58L1 | 10/10/2022 | 10/12/2022 | 2 | 0 | 2 | 10/13/2022 | 10/13/2022 | 15 | 0 | 15 | 11/08/2022 | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 1/6/2024 | N | EXP | 365 | 02/18/2023 | 05/05/2023 | 77 | 0 | 77 |  |  | 6/26/2023 | Connected |  | N
National Grid | RANDOLPH | 174895 | 02368 | 3000 |  |  | Solar |  | 05_09_1109W3 | 08/20/2013 | 08/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2013 | 10/01/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 676776 | 02769 | 20 |  |  | Solar |  | 05_09_909W3 | 03/10/2025 | 04/14/2025 | 26 | 20 | 6 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 608352 | 01886 | 10 |  |  | Solar |  | 05_07_913W18 | 05/04/2024 | 05/13/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 | 05/04/2024 | 11/13/2025 | Y | EXP | 365 | 12/26/2024 | 02/11/2025 | 48 | 0 | 48 |  |  | 2/19/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 174588 | 01266 | 30 |  |  | Solar |  | 05_07_712J1 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 8/4/2012 | N | EXP | 264 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | NORTHAMPTON | 175722 | 01053 | 16 |  |  | Solar |  | 05_05_335W3 | 12/31/2014 | 12/31/2014 | 13 | 11 | 2 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 3/1/2016 | Connected |  | N
National Grid | STOUGHTON | 175923 | 02072 | 2000 |  |  | Solar |  | 05_09_523L2 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2015 | 06/29/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/23/2016 | 04/04/2016 | 28 | 0 | 28 | 4/4/2016 | 05/29/2015 | 3/31/2018 | Y | STD | 726 | 09/26/2017 | 02/05/2018 | 83 | 0 | 83 | 3/30/2018 | 3/30/2018 | 3/30/2018 | Connected |  | N
National Grid | BROCKTON | 479439 | 02302 | 11.4 |  |  | Solar |  | 05_05_312W4 | 03/29/2023 | 12/07/2022 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2022 |  | 5/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | UPTON | 445564 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 08/01/2022 | 08/02/2022 | 1 | 0 | 1 | 08/03/2022 | 08/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 08/01/2022 | 3/1/2024 | Y | EXP | 365 | 03/02/2023 | 03/01/2023 | 0 | 0 | 0 |  |  | 3/7/2023 | Connected |  | N
National Grid | PALMER | 597739 | 01069 | 10 |  |  | Solar |  | 05_05_7L4 | 03/20/2024 | 04/18/2024 | 21 | 18 | 3 | 04/19/2024 | 04/19/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | WESTBOROUGH | 485002 | 01581 | 15.2 |  |  | Solar |  | 05_14_58L1 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 22 | 0 | 22 | 03/21/2023 | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 4/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175059 | 02368 | 18.7 |  |  | Solar |  | 05_09_1109W3 | 10/18/2012 | 10/18/2012 | 5 | 0 | 5 | 11/06/2012 | 11/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 12/17/2012 | N | EXP | -60 |  |  | 0 | 0 | 0 | 3/27/2014 | 3/27/2014 | 5/1/2013 | Connected |  | N
National Grid | REHOBOTH | 676558 | 02769 | 23 |  |  | Solar |  | 05_09_909W3 | 03/07/2025 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 645918 | 01886 | 10 |  |  | Solar |  | 05_07_913W18 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/18/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 175363 | 01230 | 5 |  |  | Solar |  | 05_07_712J1 | 11/14/2014 | 11/14/2014 | 4 | 0 | 4 | 11/21/2014 | 11/21/2014 | 442 | 0 | 442 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 |  | 1/31/2015 | N | EXP | 67 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 175805 | 01096 | 54 |  |  | Solar |  | 05_05_335W3 | 03/02/2015 | 03/02/2015 | 26 | 22 | 4 | 04/09/2015 | 04/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 8/31/2015 | N | EXP | 140 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 8/12/2015 | Connected |  | N
National Grid | STOUGHTON | 175922 | 02072 | 2000 |  |  | Solar |  | 05_09_523L2 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2015 | 06/29/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/23/2016 | 04/04/2016 | 28 | 0 | 28 | 4/4/2016 | 05/29/2015 | 3/31/2018 | Y | STD | 726 | 09/26/2017 | 02/05/2018 | 83 | 0 | 83 | 2/13/2018 | 2/13/2018 | 3/30/2018 | Connected |  | N
National Grid | BROCKTON | 489567 | 02302 | 15.2 |  |  | Solar |  | 05_05_312W4 | 01/04/2023 | 01/06/2023 | 3 | 2 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 2/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | UPTON | 466464 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 10/12/2022 | 10/13/2022 | 1 | 0 | 1 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 10/12/2022 | 6/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | PALMER | 617561 | 01069 | 6 |  |  | Solar |  | 05_05_7L4 | 06/12/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 | 06/12/2024 | 10/23/2025 | Y | EXP | 450 | 08/20/2024 | 08/19/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 491393 | 01581 | 14.592 |  |  | Solar |  | 05_14_58L1 | 01/19/2023 | 01/20/2023 | 1 | 0 | 1 | 01/23/2023 | 01/23/2023 | 274 | 112 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175099 | 02368 | 16.5 |  |  | Solar |  | 05_09_1109W3 | 10/29/2012 | 10/29/2012 | 0 | 0 | 0 | 11/19/2012 | 11/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 1/31/2013 | N | EXP | -15 |  |  | 0 | 0 | 0 | 4/29/2013 | 4/29/2013 | 4/3/2013 | Connected |  | N
National Grid | REHOBOTH | 679096 | 02769 | 10 |  |  | Solar |  | 05_09_909W3 | 03/19/2025 | 04/16/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/19/2025 | 6/5/2026 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | WESTFORD | 666514 | 01886 | 7.6 |  |  | Solar |  | 05_07_913W18 | 01/17/2025 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 175397 | 01236 | 475.2 |  |  | Solar |  | 05_07_712J1 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 | 11/24/2014 | 11/24/2014 | 242 | 4 | 238 | 07/31/2015 | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 2/15/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 176241 | 01096 | 1000 |  |  | Solar |  | 05_05_335W3 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 05/29/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 04/28/2015 | 8/31/2017 | Y | STD | 674 | 05/10/2017 | 08/22/2017 | 72 | 0 | 72 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | STOUGHTON | 176072 | 02072 | 11.4 |  |  | Solar |  | 05_09_523L2 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 119 | 0 | 119 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 501896 | 02302 | 13.975 |  |  | Solar |  | 05_05_312W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2023 | Connected |  | N
National Grid | HOPEDALE | 475958 | 01747 | 3.8 |  |  | Solar |  | 05_07_97W1 | 06/07/2023 | 11/13/2023 | 108 | 106 | 2 | 11/14/2023 | 11/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 644469 | 01069 | 7.6 |  |  | Solar |  | 05_05_7L4 | 10/02/2024 | 10/09/2024 | 3 | 0 | 3 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 506132 | 01581 | 15.2 |  |  | Solar |  | 05_14_58L1 | 03/02/2023 | 03/07/2023 | 3 | 0 | 3 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175179 | 02368 | 20 |  |  | Solar |  | 05_09_1109W3 | 05/03/2013 | 05/03/2013 | 7 | 0 | 7 | 05/15/2013 | 05/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2013 |  | 5/11/2013 | N | EXP | -51 |  |  | 0 | 0 | 0 | 7/22/2013 | 7/22/2013 | 7/25/2013 | Connected |  | N
National Grid | SEEKONK | 692583 | 02771 | 6.08 |  |  | Solar |  | 05_09_909W3 | 05/19/2025 | 06/18/2025 | 1 | 0 | 1 | 06/23/2025 | 06/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | WESTFORD | 667301 | 01886 | 15.2 |  |  | Solar |  | 05_07_913W18 | 02/03/2025 | 02/11/2025 | 7 | 4 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 176074 | 01266 | 7.6 |  |  | Solar |  | 05_07_712J1 | 08/19/2015 | 08/19/2015 | 3 | 3 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 08/19/2015 | 8/24/2016 | Y | EXP | 350 | 01/11/2016 | 02/19/2016 | 27 | 0 | 27 | 5/16/2016 | 5/16/2016 | 5/20/2016 | Connected |  | N
National Grid | NORTHAMPTON | 176240 | 01062 | 1000 |  |  | Solar |  | 05_05_335W3 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 05/29/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 04/28/2015 | 8/31/2017 | Y | STD | 674 | 05/10/2017 | 08/22/2017 | 72 | 0 | 72 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | STOUGHTON | 176501 | 02072 | 10 |  |  | Solar |  | 05_09_523L2 | 02/09/2016 | 02/09/2016 | 18 | 18 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2016 |  | 2/15/2017 | N | EXP | 296 |  |  | 0 | 0 | 0 | 4/25/2016 | 4/25/2016 | 9/28/2016 | Connected |  | N
National Grid | BROCKTON | 544251 | 02302 | 14.805 |  |  | Solar |  | 05_05_312W4 | 08/21/2023 | 09/14/2023 | 17 | 13 | 4 | 09/15/2023 | 09/15/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | MILFORD | 508496 | 01757 | 6 |  |  | Solar |  | 05_07_97W1 | 03/23/2023 | 04/12/2023 | 15 | 12 | 3 | 04/13/2023 | 04/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 | 03/23/2023 | 10/3/2024 | Y | EXP | 365 | 08/01/2023 | 10/04/2023 | 65 | 0 | 65 |  |  | 11/1/2023 | Connected |  | N
National Grid | BELCHERTOWN | 648237 | 01007 | 7.6 |  |  | Solar |  | 05_05_7L4 | 10/30/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 10/30/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | WESTBOROUGH | 515435 | 01581 | 12.6 |  |  | Solar |  | 05_14_58L1 | 03/29/2023 | 03/31/2023 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 6/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | RANDOLPH | 175341 | 02368 | 2000 |  |  | Solar |  | 05_09_1109W3 | 06/27/2014 | 06/27/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2014 | 07/09/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 | 06/27/2014 | 12/31/2016 | Y | STD | 886 | 01/04/2016 | 05/05/2016 | 84 | 0 | 84 | 5/6/2016 | 5/6/2016 | 5/6/2016 | Connected |  | N
National Grid | REHOBOTH | 701270 | 02769 | 7.6 |  |  | Solar |  | 05_09_909W3 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 8/21/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | WESTFORD | 669216 | 01886 | 8.74 |  |  | Solar |  | 05_07_913W18 | 01/31/2025 | 02/14/2025 | 6 | 1 | 5 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 176275 | 01230 | 10 |  |  | Solar |  | 05_07_712J1 | 05/01/2015 | 05/01/2015 | 70 | 70 | 0 | 08/18/2015 | 08/18/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 05/01/2015 | 2/2/2019 | Y | EXP | 1242 | 11/10/2016 | 11/22/2016 | 7 | 0 | 7 |  |  | 1/31/2019 | Connected |  | N
National Grid | NORTHAMPTON | 176819 | 01062 | 299.7 |  |  | Solar |  | 05_05_335W3 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 | 02/23/2016 | 03/25/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  | 03/25/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 | 5/17/2016 | 11/06/2015 | 4/6/2017 | Y | EXP | 324 | 10/06/2016 | 04/05/2017 | 122 | 0 | 122 | 3/21/2017 | 3/21/2017 | 5/3/2017 | Connected |  | N
National Grid | STOUGHTON | 176515 | 02072 | 5 |  |  | Solar |  | 05_09_523L2 | 10/01/2015 | 10/01/2015 | 1 | 1 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/01/2015 | 10/10/2016 | Y | EXP | 353 | 08/12/2016 | 09/13/2016 | 21 | 0 | 21 | 10/23/2015 | 10/23/2015 | 10/11/2016 | Connected |  | N
National Grid | BROCKTON | 546560 | 02302 | 0 |  |  | Solar |  | 05_05_312W4 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 12/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | MILFORD | 507261 | 01757 | 6 |  |  | Solar |  | 05_07_97W1 | 03/23/2023 | 03/28/2023 | 3 | 0 | 3 | 03/29/2023 | 03/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/23/2023 | 9/11/2024 | Y | EXP | 365 | 07/20/2023 | 09/08/2023 | 51 | 0 | 51 |  |  | 9/21/2023 | Connected |  | N
National Grid | BELCHERTOWN | 662401 | 01007 | 5.51 |  |  | Solar |  | 05_05_7L4 | 12/26/2024 | 01/29/2025 | 15 | 5 | 10 | 01/30/2025 | 01/30/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/26/2024 | 2/3/2026 | Y | EXP | 365 | 02/27/2025 | 02/26/2025 | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | WESTBOROUGH | 177950 | 01581 | 3.8 |  |  | Solar |  | 05_01_10J383 | 08/23/2017 | 08/23/2017 | 9 | 9 | 0 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2017 |  | 8/24/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | RANDOLPH | 176066 | 02368 | 499 |  |  | Solar |  | 05_09_1109W3 | 06/18/2015 | 06/18/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2015 | 07/21/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2016 |  | 6/27/2016 | N | STD | -11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 706628 | 02771 | 0 |  |  | Solar |  | 05_09_909W3 | 07/23/2025 | 07/28/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | WESTFORD | 679409 | 01886 | 11.5 |  |  | Solar |  | 05_07_913W18 | 03/20/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 176437 | 01230 | 10 |  |  | Solar |  | 05_07_712J1 | 03/16/2016 | 03/16/2016 | 3 | 3 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/16/2016 | 3/21/2017 | Y | EXP | 343 | 12/14/2016 | 01/05/2017 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/23/2017 | Connected |  | N
National Grid | WILLIAMSBURG | 176809 | 01096 | 11.4 |  |  | Solar |  | 05_05_335W3 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/3/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 176837 | 02072 | 10 |  |  | Solar |  | 05_09_523L2 | 02/29/2016 | 02/29/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/6/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 7/18/2016 | Connected |  | N
National Grid | BROCKTON | 573934 | 02302 | 15.2 |  |  | Solar |  | 05_05_312W4 | 11/28/2023 | 12/13/2023 | 11 | 8 | 3 | 12/14/2023 | 12/14/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | UPTON | 522517 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 06/01/2023 | 08/21/2023 | 55 | 55 | 0 | 08/22/2023 | 08/22/2023 | 40 | 7 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 685042 | 01007 | 22.8 |  |  | Solar |  | 05_05_7L4 | 04/14/2025 | 04/22/2025 | 5 | 0 | 5 | 04/23/2025 | 04/23/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | WESTBOROUGH | 495040 | 01581 | 3.8 |  |  | Solar |  | 05_01_10J383 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | N
National Grid | RANDOLPH | 176065 | 02368 | 499 |  |  | Solar |  | 05_09_1109W3 | 06/18/2015 | 06/18/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2015 | 07/21/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2016 |  | 6/27/2016 | N | STD | -11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 642779 | 02769 | 0 |  |  | Solar |  | 05_09_909W4 | 09/25/2024 | 11/04/2024 | 28 | 19 | 9 | 11/05/2024 | 11/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 699708 | 01886 | 5.76 |  |  | Solar |  | 05_07_913W18 | 06/24/2025 | 07/21/2025 | 7 | 3 | 4 | 09/10/2025 | 09/10/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 177178 | 01266 | 3.8 |  |  | Solar |  | 05_07_712J1 | 06/05/2016 | 06/05/2016 | 8 | 8 | 0 | 06/20/2016 | 06/20/2016 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/12/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 177172 | 01053 | 10 |  |  | Solar |  | 05_05_335W3 | 05/29/2016 | 05/29/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/29/2016 | 6/6/2017 | Y | EXP | 351 | 09/13/2016 | 09/23/2016 | 8 | 0 | 8 | 11/3/2016 | 11/3/2016 | 11/3/2016 | Connected |  | N
National Grid | STOUGHTON | 176923 | 02072 | 10.32 |  |  | Solar |  | 05_09_523L2 | 11/18/2015 | 11/18/2015 | 3 | 3 | 0 | 11/24/2015 | 11/24/2015 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 11/24/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 |  | Withdrawn |  | N
National Grid | BROCKTON | 599975 | 02302 | 11.6 |  |  | Solar |  | 05_05_312W4 | 04/04/2024 | 04/17/2024 | 8 | 4 | 4 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/04/2024 | 7/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2024 | Connected |  | N
National Grid | UPTON | 526253 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 05/26/2023 |  | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 686152 | 01007 | 24.7 |  |  | Solar |  | 05_05_7L4 | 04/18/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | WESTBOROUGH | 517558 | 01581 | 10 |  |  | Solar |  | 05_01_10J383 | 06/22/2023 | 04/26/2023 | 3 | 0 | 3 | 06/28/2023 | 06/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176151 | 02368 | 2000 |  |  | Solar |  | 05_09_1109W3 | 08/26/2015 | 08/26/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/01/2015 | 10/06/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 | 08/26/2015 | 11/2/2017 | Y | STD | 640 | 06/20/2017 | 10/31/2017 | 91 | 0 | 91 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | REHOBOTH | 714304 | 02769 | 7.6 |  |  | Solar |  | 05_09_909W4 | 08/25/2025 | 09/12/2025 | 6 | 0 | 6 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 08/25/2025 | 11/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTFORD | 701972 | 01886 | 16.32 |  |  | Solar |  | 05_07_913W47 | 06/30/2025 | 07/01/2025 | 1 | 0 | 1 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 190446 | 01236 | 15.2 |  |  | Solar |  | 05_07_712J1 | 07/11/2018 | 08/10/2018 | 8 | 0 | 8 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2018 |  | 8/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | GOSHEN | 177475 | 01032 | 225 |  |  | Solar |  | 05_05_335W3 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 | 07/07/2016 | 07/07/2016 | 0 | 0 | 0 | 09/06/2016 | 10/04/2016 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  | 10/04/2016 | 20 | 1 | 19 |  |  | 0 | 0 | 0 | 10/28/2016 |  | 2/5/2017 | N | EXP | 100 |  |  | 0 | 0 | 0 | 2/3/2017 | 2/3/2017 | 2/22/2017 | Connected |  | N
National Grid | STOUGHTON | 177944 | 02072 | 432.9 |  |  | Solar |  | 05_09_523L2 | 08/18/2017 | 10/06/2017 | 10 | 0 | 10 | 09/05/2017 | 09/05/2017 | 26 | 0 | 26 | 01/03/2018 | 01/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 01/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 4/6/2018 | 08/18/2017 | 1/31/2020 | Y | EXP | 560 |  |  | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | BROCKTON | 603992 | 02302 | 10 |  |  | Solar |  | 05_05_312W4 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 538902 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 07/10/2023 | 08/31/2023 | 35 | 34 | 1 | 09/01/2023 | 09/01/2023 | 70 | 52 | 18 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 691988 | 01007 | 15.2 |  |  | Solar |  | 05_05_7L4 | 06/02/2025 | 06/04/2025 | 2 | 1 | 1 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | WESTBOROUGH | 520774 | 01581 | 6 |  |  | Solar |  | 05_01_10J383 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 108 | 25 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176518 | 02368 | 1980 |  |  | Solar |  | 05_09_1109W3 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2015 | 11/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/01/2015 | 10/11/2016 | Y | STD | 183 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 723531 | 02769 | 10 |  |  | Solar |  | 05_09_909W4 | 10/02/2025 | 10/09/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 725705 | 01604 | 10 |  |  | Solar |  | 05_07_913W47 | 10/10/2025 | 11/24/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GREAT BARRINGTON | 194058 | 01230 | 9.92 |  |  | Solar |  | 05_07_712J1 | 08/21/2018 | 10/04/2018 | 31 | 24 | 7 | 10/11/2018 | 10/11/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 11/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | GOSHEN | 178416 | 01032 | 2450 |  |  | Solar |  | 05_05_335W3 | 11/28/2017 | 11/28/2017 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  | 4/9/2020 | N | STD | 632 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 178173 | 02072 | 3190 |  |  | Solar |  | 05_09_523L2 | 03/23/2018 | 04/06/2018 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 04/28/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 610948 | 02302 | 8.775 |  |  | Solar |  | 05_05_312W4 | 05/14/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | UPTON | 546614 | 01568 | 3.8 |  |  | Solar |  | 05_07_97W1 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 701920 | 01007 | 23 |  |  | Solar |  | 05_05_7L4 | 06/30/2025 | 07/28/2025 | 18 | 16 | 2 | 07/29/2025 | 07/29/2025 | 18 | 0 | 18 | 08/27/2025 | 09/11/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 09/11/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/6/2026 | N | EXP | 365 | 11/01/2025 | 11/19/2025 | 19 | 0 | 19 |  |  | 11/26/2025 | Connected |  | N
National Grid | WESTBOROUGH | 551311 | 01581 | 4.93 |  |  | Solar |  | 05_01_10J383 | 08/28/2023 | 08/30/2023 | 3 | 2 | 1 | 08/31/2023 | 08/31/2023 | 42 | 20 | 22 | 11/07/2023 | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 |  | 01/05/2024 | 40 | 3 | 37 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176519 | 02368 | 1920 |  |  | Solar |  | 05_09_1109W3 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2015 | 11/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/01/2015 | 8/31/2018 | Y | STD | 872 | 08/09/2016 | 01/19/2017 | 164 | 0 | 164 |  |  | 8/6/2018 | Connected |  | N
National Grid | REHOBOTH | 737787 | 02769 | 7.6 |  |  | Solar |  | 05_09_909W4 | 12/03/2025 | 12/04/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 727210 | 01604 | 7.6 |  |  | Solar |  | 05_07_913W47 | 10/16/2025 | 10/23/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GREAT BARRINGTON | 204159 | 01230 | 213.2 |  |  | Solar |  | 05_07_712J1 | 12/18/2018 | 01/24/2019 | 23 | 16 | 7 | 01/25/2019 | 01/25/2019 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 195450 | 01062 | 2450 |  |  | Solar |  | 05_05_335W3 | 11/01/2018 | 12/05/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 178640 | 02072 | 1000 |  |  | Solar |  | 05_09_523L2 | 04/09/2018 | 04/16/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/14/2018 | 43 | 27 | 16 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 625957 | 02302 | 0 |  |  | Solar |  | 05_05_312W4 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | MILFORD | 548604 | 01757 | 10 |  |  | Solar |  | 05_07_97W1 | 08/23/2023 | 08/29/2023 | 4 | 0 | 4 | 08/30/2023 | 08/30/2023 | 90 | 66 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 712964 | 01007 | 21.4 |  |  | Solar |  | 05_05_7L4 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | WESTBOROUGH | 553055 | 01581 | 10 |  |  | Solar |  | 05_01_10J383 | 09/07/2023 | 09/20/2023 | 9 | 7 | 2 | 09/21/2023 | 09/21/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176672 | 02368 | 1000 |  |  | Solar |  | 05_09_1109W3 | 10/23/2015 | 10/23/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 11/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/23/2015 | 11/16/2017 | Y | STD | 584 | 02/21/2017 | 10/31/2017 | 174 | 0 | 174 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | REHOBOTH | 742723 | 02769 | 120 |  |  | Solar |  | 05_09_909W4 | 12/31/2025 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | WORCESTER | 735275 | 01604 | 10 |  |  | Solar |  | 05_07_913W47 | 11/20/2025 | 11/21/2025 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | STOCKBRIDGE | 293251 | 01266 | 7.6 |  |  | Solar |  | 05_07_712J1 | 07/30/2020 | 09/21/2020 | 34 | 27 | 7 | 09/22/2020 | 09/22/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2020 | 07/30/2020 | 7/29/2021 | Y | EXP | 365 | 12/15/2020 | 01/08/2021 | 24 | 0 | 24 |  |  | 2/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 207419 | 01062 | 25 |  |  | Solar |  | 05_05_335W3 | 03/04/2019 | 03/05/2019 | 0 | 0 | 0 | 03/06/2019 | 03/06/2019 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2019 | 03/04/2019 | 12/17/2019 | Y | EXP | 272 |  |  | 0 | 0 | 0 |  |  | 7/3/2019 | Connected |  | N
National Grid | STOUGHTON | 178675 | 02072 | 2500 |  |  | Solar |  | 05_09_523L2 | 04/10/2018 | 04/20/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 09/06/2018 | 97 | 54 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 642208 | 02302 | 11.5 |  |  | Solar |  | 05_05_312W4 | 09/23/2024 | 10/03/2024 | 9 | 7 | 2 | 10/04/2024 | 10/04/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 10/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | MILFORD | 569520 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 11/21/2023 | 12/12/2023 | 15 | 14 | 1 | 12/13/2023 | 12/13/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | PALMER | 676722 | 01069 | 3.77 |  |  | Solar |  | 05_05_7L5 | 03/12/2025 | 03/19/2025 | 5 | 3 | 2 | 03/20/2025 | 03/20/2025 | 100 | 80 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 569102 | 01581 | 10 |  |  | Solar |  | 05_01_10J383 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178222 | 02368 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 04/13/2018 | 04/13/2018 | 24 | 0 | 24 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 10/21/2019 | N | EXP | 521 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | SEEKONK | 174670 | 02771 | 200 |  |  | Natural Gas |  | 05_09_909W4 | 06/06/2013 | 06/06/2013 | 23 | 22 | 1 | 07/12/2013 | 07/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2013 |  | 11/29/2013 | N | EXP | 121 |  |  | 0 | 0 | 0 | 11/24/2015 | 11/24/2015 | 11/24/2015 | Connected |  | N
National Grid | WORCESTER | 175615 | 01604 | 27.3 |  |  | Solar |  | 05_07_913W47 | 12/16/2014 | 12/16/2014 | 4 | 3 | 1 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2015 |  | 4/15/2015 | N | EXP | 100 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 | 7/2/2015 | Connected |  | N
National Grid | EGREMONT | 324110 | 01252 | 7.6 |  |  | Solar |  | 05_07_712J1 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/25/2020 | 1/25/2022 | Y | EXP | 365 | 08/12/2021 | 09/22/2021 | 36 | 3 | 33 |  |  | 10/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 213781 | 01062 | 0 |  |  | Solar |  | 05_05_335W3 | 03/14/2019 | 03/21/2019 | 4 | 0 | 4 | 03/22/2019 | 03/22/2019 | 143 | 140 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 11/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | STOUGHTON | 184809 | 02072 | 990 |  |  | Solar |  | 05_09_523L2 | 06/12/2018 | 06/12/2018 | 28 | 1 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 643356 | 02351 | 15.2 |  |  | Solar |  | 05_05_312W4 | 09/27/2024 | 09/30/2024 | 1 | 0 | 1 | 10/01/2024 | 10/01/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 572609 | 01568 | 6 |  |  | Solar |  | 05_07_97W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 12/07/2023 | 4/3/2025 | Y | EXP | 365 | 04/25/2024 | 06/18/2024 | 55 | 0 | 55 |  |  | 8/5/2024 | Connected |  | N
National Grid | BELCHERTOWN | 680204 | 01007 | 12.18 |  |  | Solar |  | 05_05_7L5 | 03/24/2025 | 04/17/2025 | 4 | 0 | 4 | 05/12/2025 | 05/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 03/24/2025 | 9/23/2026 | Y | EXP | 365 | 12/05/2025 |  | 28 | 0 | 28 |  |  |  | Construction |  | Y
National Grid | WESTBOROUGH | 607705 | 01581 | 3.19 |  |  | Solar |  | 05_01_10J383 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 86 | 71 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178562 | 02368 | 2500 |  |  | Solar |  | 05_09_1109W3 | 04/05/2018 | 04/05/2018 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 07/21/2018 | 64 | 48 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 175909 | 02769 | 20 |  |  | Solar |  | 05_09_909W4 | 03/10/2015 | 03/10/2015 | 4 | 0 | 4 | 03/18/2015 | 03/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2015 |  | 7/31/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 7/23/2015 | Connected |  | N
National Grid | WORCESTER | 177424 | 01604 | 7.6 |  |  | Solar |  | 05_07_913W47 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 365 |  |  | 0 | 0 | 0 | 5/2/2017 | 5/2/2017 | 5/2/2017 | Connected |  | N
National Grid | GREAT BARRINGTON | 324131 | 01230 | 5.76 |  |  | Solar |  | 05_07_712J1 | 04/07/2021 | 04/09/2021 | 1 | 0 | 1 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/8/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 212788 | 01062 | 109.9 |  |  | Solar |  | 05_05_335W3 | 03/06/2019 | 03/12/2019 | 4 | 1 | 3 | 03/13/2019 | 03/13/2019 | 6 | 0 | 6 | 04/04/2019 | 08/27/2019 | 102 | 62 | 40 |  |  | 0 | 0 | 0 |  | 08/27/2019 | 102 | 62 | 40 |  |  | 0 | 0 | 0 | 9/12/2019 | 03/06/2019 | 4/14/2021 | Y | EXP | 266 | 02/12/2020 | 08/14/2020 | 184 | 0 | 184 |  |  | 4/14/2021 | Connected |  | N
National Grid | STOUGHTON | 199150 | 02072 | 7.6 |  |  | Solar |  | 05_09_523L2 | 10/22/2018 | 10/24/2018 | 2 | 2 | 0 | 10/25/2018 | 10/25/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  | 10/7/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 8/29/2019 | Connected |  | N
National Grid | BROCKTON | 643250 | 02302 | 10 |  |  | Solar |  | 05_05_312W4 | 09/27/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 09/27/2024 | 12/12/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/22/2025 | Connected |  | N
National Grid | UPTON | 575266 | 01568 | 3.19 |  |  | Solar |  | 05_07_97W1 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 | 12/20/2023 | 2/14/2025 | Y | EXP | 365 | 05/02/2024 | 06/25/2024 | 55 | 0 | 55 |  |  | 7/10/2024 | Connected |  | N
National Grid | BELCHERTOWN | 701181 | 01007 | 23 |  |  | Solar |  | 05_05_7L5 | 06/25/2025 | 07/02/2025 | 4 | 2 | 2 | 07/03/2025 | 07/03/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 607592 | 01581 | 4.225 |  |  | Solar |  | 05_01_10J383 | 05/08/2024 | 05/31/2024 | 6 | 5 | 1 | 06/03/2024 | 06/03/2024 | 51 | 38 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | RANDOLPH | 178617 | 02368 | 11.4 |  |  | Solar |  | 05_09_1109W3 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 9/16/2020 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 176099 | 02769 | 300 |  |  | Solar |  | 05_09_909W4 | 04/10/2015 | 04/10/2015 | 3 | 3 | 0 | 04/16/2015 | 04/16/2015 | 317 | 0 | 317 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 9/11/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 322312 | 01604 | 7.6 |  |  | Solar |  | 05_07_913W47 | 10/28/2020 | 10/29/2020 | 0 | 0 | 0 | 10/30/2020 | 10/30/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 330887 | 01230 | 15.2 |  |  | Solar |  | 05_07_712J1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/4/2022 | Y | EXP | 365 | 09/03/2021 | 10/08/2021 | 36 | 0 | 36 |  |  | 12/2/2022 | Connected |  | N
National Grid | NORTHAMPTON | 212698 | 01062 | 7.6 |  |  | Solar |  | 05_05_335W3 | 11/04/2019 | 11/25/2019 | 13 | 13 | 0 | 11/26/2019 | 11/26/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2019 | 11/04/2019 | 2/18/2021 | Y | EXP | 365 | 05/16/2020 | 06/02/2020 | 17 | 0 | 17 |  |  | 10/20/2020 | Connected |  | N
National Grid | STOUGHTON | 241092 | 02072 | 10.32 |  |  | Solar |  | 05_09_523L2 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 | 07/24/2019 | 1/11/2021 | Y | EXP | 365 | 02/07/2020 | 02/06/2020 | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | BROCKTON | 650666 | 02302 | 1.74 |  |  | Solar |  | 05_05_312W4 | 10/29/2024 | 12/20/2024 | 28 | 24 | 4 | 12/23/2024 | 12/23/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | UPTON | 591148 | 01568 | 6 |  |  | Solar |  | 05_07_97W1 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/11/2024 | 6/20/2025 | Y | EXP | 365 | 05/09/2024 | 08/08/2024 | 92 | 0 | 92 |  |  | 10/22/2024 | Connected |  | N
National Grid | PALMER | 716378 | 01069 | 0 |  |  | Solar |  | 05_05_7L5 | 09/03/2025 | 09/16/2025 | 8 | 6 | 2 | 09/17/2025 | 09/17/2025 | 59 | 41 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 631126 | 01581 | 5.76 |  |  | Solar |  | 05_01_10J383 | 08/08/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178691 | 02368 | 304 |  |  | Solar |  | 05_09_1109W3 | 12/20/2017 | 12/20/2017 | 10 | 0 | 10 | 02/01/2018 | 02/01/2018 | 8 | 0 | 8 | 03/20/2018 | 04/18/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 04/18/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 6/4/2018 |  | 12/26/2018 | N | EXP | 205 |  |  | 0 | 0 | 0 |  |  | 5/31/2019 | Connected |  | N
National Grid | REHOBOTH | 176611 | 02769 | 488 |  |  | Solar |  | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 326056 | 01604 | 7.6 |  |  | Solar |  | 05_07_913W47 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 382577 | 01230 | 240 |  |  | Solar |  | 05_07_712J1 | 11/11/2021 | 12/13/2021 | 21 | 15 | 6 |  |  | 40 | 2 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 310848 | 01053 | 11.4 |  |  | Solar |  | 05_05_335W3 | 09/04/2020 | 09/10/2020 | 2 | 0 | 2 | 09/11/2020 | 09/11/2020 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 294435 | 02072 | 5 |  |  | Solar |  | 05_09_523L2 | 07/17/2020 | 07/27/2020 | 5 | 0 | 5 | 07/28/2020 | 07/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 07/17/2020 | 5/3/2021 | Y | EXP | 365 | 04/23/2021 | 05/05/2021 | 12 | 0 | 12 |  |  | 6/9/2021 | Connected |  | N
National Grid | BROCKTON | 652265 | 02302 | 11.5 |  |  | Solar |  | 05_05_312W4 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2025 | Connected |  | N
National Grid | UPTON | 594854 | 01568 | 5 |  |  | Solar |  | 05_07_97W1 | 03/16/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 | 03/16/2024 | 4/8/2025 | Y | EXP | 365 | 04/26/2024 | 05/10/2024 | 15 | 0 | 15 |  |  | 5/14/2024 | Connected |  | N
National Grid | BELCHERTOWN | 719525 | 01007 | 15.2 |  |  | Solar |  | 05_05_7L5 | 09/16/2025 | 10/16/2025 | 20 | 16 | 4 | 10/17/2025 | 10/17/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 641898 | 01581 | 5.76 |  |  | Solar |  | 05_01_10J383 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 40 | 17 | 23 | 01/30/2025 | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 03/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/06/2024 | 4/12/2026 | Y | EXP | 365 | 04/03/2025 | 07/25/2025 | 114 | 0 | 114 |  |  | 9/10/2025 | Connected |  | Y
National Grid | RANDOLPH | 197783 | 02368 | 240 |  |  | Solar |  | 05_09_1109W3 | 10/05/2018 | 11/05/2018 | 189 | 21 | 168 |  |  | 23 | 10 | 13 |  |  | 0 | 0 | 0 | 11/05/2018 | 01/05/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176610 | 02771 | 2355 |  |  | Solar |  | 05_09_909W4 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2016 | 03/11/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2016 | 02/12/2016 | 10/31/2017 | Y | STD | 419 | 08/23/2017 | 10/12/2017 | 34 | 0 | 34 | 10/26/2017 | 10/26/2017 | 11/9/2017 | Connected |  | N
National Grid | WORCESTER | 500931 | 01604 | 15.2 |  |  | Solar |  | 05_07_913W47 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | GREAT BARRINGTON | 492024 | 01230 | 6 |  |  | Solar |  | 05_07_712J1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | NORTHAMPTON | 334895 | 01062 | 3.8 |  |  | Solar |  | 05_05_335W3 | 01/05/2021 | 01/06/2021 | 1 | 1 | 0 | 01/07/2021 | 01/07/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 | 01/05/2021 | 1/5/2022 | Y | EXP | 365 | 04/21/2021 | 06/02/2021 | 42 | 0 | 42 |  |  | 6/16/2021 | Connected |  | N
National Grid | STOUGHTON | 294038 | 02072 | 9.84 |  |  | Solar |  | 05_09_523L2 | 08/05/2020 | 08/11/2020 | 3 | 0 | 3 | 08/12/2020 | 08/12/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 652105 | 02302 | 10 |  |  | Solar |  | 05_05_312W4 | 11/14/2024 | 01/08/2025 | 24 | 19 | 5 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 598614 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | PALMER | 738773 | 01009 | 15.76 |  |  | Solar |  | 05_05_7L5 | 12/08/2025 | 12/11/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 648562 | 01581 | 5.76 |  |  | Solar |  | 05_01_10J383 | 10/21/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/21/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 199441 | 02368 | 10 |  |  | Solar |  | 05_09_1109W3 | 11/08/2018 | 11/27/2018 | 8 | 3 | 5 | 11/28/2018 | 11/28/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 176633 | 02769 | 528 |  |  | Solar |  | 05_09_909W4 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 574370 | 01604 | 8.448 |  |  | Solar |  | 05_07_913W47 | 02/07/2024 | 02/12/2024 | 3 | 1 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/07/2024 | 3/1/2025 | Y | EXP | 365 | 04/16/2024 | 04/16/2024 | 1 | 0 | 1 |  |  | 6/18/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 513457 | 01230 | 0 |  |  | Solar |  | 05_07_712J1 | 03/21/2023 |  | 144 | 128 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 337021 | 01062 | 7.6 |  |  | Solar |  | 05_05_335W3 | 02/17/2021 | 05/04/2021 | 52 | 47 | 5 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 10/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | STOUGHTON | 297681 | 02072 | 3.36 |  |  | Solar |  | 05_09_523L2 | 06/22/2020 | 06/29/2020 | 4 | 0 | 4 | 06/30/2020 | 06/30/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2021 | Connected |  | N
National Grid | BROCKTON | 654499 | 02302 | 9.88 |  |  | Solar |  | 05_05_312W4 | 11/14/2024 | 12/06/2024 | 10 | 5 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | MILFORD | 608388 | 01757 | 5.76 |  |  | Solar |  | 05_07_97W1 | 05/02/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/22/2025 | Y | EXP | 365 | 10/10/2024 | 02/19/2025 | 133 | 0 | 133 |  |  | 2/28/2025 | Connected |  | N
National Grid | BELCHERTOWN | 153683 | 01007 | 15.2 |  |  | Solar |  | 05_05_7L5 | 02/02/2017 | 02/02/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/2/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 688082 | 01581 | 7.475 |  |  | Solar |  | 05_01_10J383 | 04/28/2025 | 05/13/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | Y
National Grid | RANDOLPH | 213059 | 02368 | 10 |  |  | Solar |  | 05_09_1109W3 | 04/01/2019 | 04/03/2019 | 2 | 2 | 0 | 04/04/2019 | 04/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 | 04/01/2019 | 11/5/2019 | Y | EXP | 210 | 05/22/2019 | 06/25/2019 | 34 | 0 | 34 |  |  | 8/10/2019 | Connected |  | N
National Grid | SEEKONK | 178174 | 02771 | 7.6 |  |  | Solar |  | 05_09_909W4 | 03/23/2018 | 03/23/2018 | 5 | 0 | 5 | 04/02/2018 | 04/02/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/31/2019 | N | EXP | 327 |  |  | 0 | 0 | 0 |  |  | 10/30/2019 | Connected |  | N
National Grid | WORCESTER | 631809 | 01604 | 9.6 |  |  | Solar |  | 05_07_913W47 | 08/12/2024 | 08/19/2024 | 4 | 1 | 3 | 08/20/2024 | 08/20/2024 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 559691 | 01230 | 8.19 |  |  | Solar |  | 05_07_712J1 | 10/24/2023 | 10/26/2023 | 3 | 1 | 2 | 10/27/2023 | 10/27/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 345013 | 01062 | 15.12 |  |  | Solar |  | 05_05_335W3 | 03/04/2021 | 03/08/2021 | 1 | 1 | 0 | 03/09/2021 | 03/09/2021 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/04/2021 | 3/8/2022 | Y | EXP | 365 | 04/22/2021 | 05/26/2021 | 34 | 0 | 34 |  |  | 5/28/2021 | Connected |  | Y
National Grid | STOUGHTON | 299534 | 02072 | 0 |  |  | Solar |  | 05_09_523L2 | 07/02/2020 | 08/11/2020 | 27 | 25 | 2 | 08/12/2020 | 08/12/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/02/2020 | 8/11/2021 | Y | EXP | 365 | 10/08/2020 | 10/21/2020 | 13 | 0 | 13 |  |  | 10/21/2020 | Connected |  | N
National Grid | BROCKTON | 664419 | 02302 | 11.5 |  |  | Solar |  | 05_05_312W4 | 01/08/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | MILFORD | 610295 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W1 | 05/14/2024 | 05/20/2024 | 2 | 0 | 2 | 05/21/2024 | 05/21/2024 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/14/2024 | 6/17/2025 | Y | EXP | 365 | 09/12/2024 | 10/30/2024 | 49 | 0 | 49 |  |  | 11/8/2024 | Connected |  | N
National Grid | BELCHERTOWN | 173295 | 01007 | 3.8 |  |  | Solar |  | 05_05_7L5 | 07/10/2018 | 07/19/2018 | 6 | 0 | 6 | 07/20/2018 | 07/20/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 722399 | 01581 | 13.3 |  |  | Solar |  | 05_01_11J330 | 09/26/2025 | 10/15/2025 | 1 | 0 | 1 | 10/17/2025 | 10/17/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | RANDOLPH | 218174 | 02368 | 15.37 |  |  | Solar |  | 05_09_1109W3 | 04/10/2019 | 04/12/2019 | 2 | 2 | 0 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 7/30/2019 | N | EXP | 104 |  |  | 0 | 0 | 0 |  |  | 6/24/2019 | Connected |  | N
National Grid | REHOBOTH | 178385 | 02769 | 3.8 |  |  | Solar |  | 05_09_909W4 | 01/15/2018 | 01/15/2018 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 1/21/2019 | N | EXP | 214 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 632274 | 01604 | 3.8 |  |  | Solar |  | 05_07_913W47 | 09/05/2024 | 09/09/2024 | 3 | 1 | 2 | 09/10/2024 | 09/10/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 528274 | 01230 | 6 |  |  | Solar |  | 05_07_712J1 | 05/30/2023 | 06/01/2023 | 3 | 2 | 1 | 06/02/2023 | 06/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/30/2023 | 9/28/2024 | Y | EXP | 365 | 09/06/2023 | 09/27/2023 | 22 | 0 | 22 |  |  | 10/6/2023 | Connected |  | N
National Grid | NORTHAMPTON | 387138 | 01062 | 0 |  |  | Other |  | 05_05_335W3 | 11/10/2021 | 12/28/2021 | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 11/21/2022 | 219 | 211 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 326990 | 02072 | 0 |  |  | Solar |  | 05_09_523L2 | 11/20/2020 | 12/08/2020 | 10 | 8 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 12/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2021 | Connected |  | N
National Grid | BROCKTON | 674216 | 02302 | 15.2 |  |  | Solar |  | 05_05_312W4 | 02/25/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | UPTON | 618593 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 06/17/2024 | 07/01/2024 | 6 | 4 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/17/2024 | 7/31/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | PALMER | 174188 | 01009 | 2000 |  |  | Solar |  | 05_05_7L5 | 03/14/2012 | 03/14/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 177844 | 01581 | 17.6 |  |  | Solar |  | 05_01_11J330 | 10/17/2017 | 10/17/2017 | 53 | 53 | 0 | 01/17/2018 | 01/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2018 |  | 10/24/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 222580 | 02368 | 0 |  |  | Solar |  | 05_09_1109W3 | 04/25/2019 | 05/06/2019 | 6 | 0 | 6 | 05/07/2019 | 05/07/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2019 | 04/25/2019 | 3/10/2020 | Y | EXP | 365 | 11/19/2019 | 11/18/2019 | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | REHOBOTH | 178658 | 02769 | 3564 |  |  | Solar |  | 05_09_909W4 | 02/05/2018 | 02/05/2018 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2018 | 04/11/2018 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 | 02/05/2018 | 12/31/2020 | Y | STD | 773 | 05/08/2020 | 11/18/2020 | 195 | 5 | 190 | 11/20/2020 | 12/24/2020 | 12/31/2020 | Connected |  | N
National Grid | WORCESTER | 636932 | 01604 | 10 |  |  | Solar |  | 05_07_913W47 | 08/30/2024 | 09/12/2024 | 1 | 0 | 1 | 09/13/2024 | 09/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/30/2024 | 10/9/2025 | Y | EXP | 365 | 01/28/2025 | 01/27/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 571401 | 01266 | 7.6 |  |  | Solar |  | 05_07_712J1 | 12/05/2023 | 12/08/2023 | 3 | 0 | 3 | 12/11/2023 | 12/11/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 391814 | 01062 | 1.74 |  |  | Solar |  | 05_05_335W3 | 11/09/2021 | 11/17/2021 | 5 | 4 | 1 | 11/18/2021 | 11/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 5/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | STOUGHTON | 437714 | 02072 | 10 |  |  | Solar |  | 05_09_523L2 | 07/07/2022 | 07/12/2022 | 3 | 0 | 3 | 07/13/2022 | 07/13/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 07/07/2022 | 4/6/2024 | Y | EXP | 365 | 12/22/2022 | 04/05/2023 | 105 | 0 | 105 |  |  | 4/11/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 676548 | 02333 | 10 |  |  | Solar |  | 05_05_312W4 | 03/11/2025 | 03/27/2025 | 13 | 8 | 5 | 03/28/2025 | 03/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 623636 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W1 | 07/09/2024 | 07/10/2024 | 1 | 0 | 1 | 09/23/2024 | 09/23/2024 | 26 | 9 | 17 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 12/17/2025 | N | EXP | 365 | 04/24/2025 | 08/07/2025 | 106 | 0 | 106 |  |  | 8/22/2025 | Connected |  | N
National Grid | PALMER | 174912 | 01009 | 1000 |  |  | Solar |  | 05_05_7L5 | 09/18/2012 | 09/18/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2012 | 12/26/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2013 | 09/18/2012 | 6/30/2014 | Y | STD | 181 | 05/05/2014 | 07/17/2014 | 50 | 0 | 50 | 7/2/2014 | 7/2/2014 | 7/15/2014 | Connected |  | N
National Grid | WESTBOROUGH | 646198 | 01581 | 3.8 |  |  | Solar |  | 05_01_11J330 | 10/10/2024 | 02/17/2025 | 83 | 83 | 0 | 02/18/2025 | 02/18/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 265046 | 02368 | 10 |  |  | Solar |  | 05_09_1109W3 | 11/12/2019 | 11/26/2019 | 9 | 6 | 3 | 11/27/2019 | 11/27/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/12/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2020 | Connected |  | N
National Grid | REHOBOTH | 178700 | 02769 | 4320 |  |  | Solar |  | 05_09_909W4 | 02/08/2018 | 04/09/2018 | 42 | 37 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/02/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 02/08/2018 | 12/17/2019 | Y | STD | 294 | 09/11/2019 | 11/19/2019 | 69 | 0 | 69 |  |  | 12/20/2019 | Connected |  | N
National Grid | WORCESTER | 660301 | 01604 | 7.6 |  |  | Solar |  | 05_07_913W47 | 12/12/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/12/2024 | 5/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | EGREMONT | 626740 | 01252 | 7.6 |  |  | Solar |  | 05_07_712J1 | 07/22/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 393123 | 01062 | 4990 |  |  | Other |  | 05_05_335W3 | 12/17/2021 | 01/25/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2022 | 11/22/2022 | 208 | 201 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 460033 | 02072 | 34.6 |  |  | Solar |  | 05_09_523L2 | 09/23/2022 | 11/03/2022 | 28 | 17 | 11 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 1/19/2025 | Y | STD | 450 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | Y
National Grid | BROCKTON | 681799 | 02302 | 20 |  |  | Solar |  | 05_05_312W4 | 04/02/2025 | 04/07/2025 | 3 | 0 | 3 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | UPTON | 633020 | 01568 | 10 |  |  | Solar |  | 05_07_97W1 | 08/15/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/15/2024 | 10/21/2025 | Y | EXP | 365 | 11/16/2024 | 02/04/2025 | 81 | 0 | 81 |  |  | 2/24/2025 | Connected |  | N
National Grid | BELCHERTOWN | 175170 | 01007 | 1500 |  |  | Solar |  | 05_05_7L5 | 11/15/2012 | 11/15/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2012 | 01/07/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/22/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 652361 | 01581 | 9.12 |  |  | Solar |  | 05_01_11J330 | 11/05/2024 | 11/25/2024 | 7 | 5 | 2 | 11/26/2024 | 11/26/2024 | 71 | 47 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 11/05/2024 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2025 | Connected |  | N
National Grid | RANDOLPH | 265790 | 02368 | 9.8 |  |  | Solar |  | 05_09_1109W3 | 11/25/2019 | 12/03/2019 | 4 | 0 | 4 | 12/04/2019 | 12/04/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 | 05/01/2020 | 06/26/2020 | 56 | 0 | 56 |  |  | 7/2/2020 | Connected |  | N
National Grid | REHOBOTH | 187299 | 02769 | 10 |  |  | Solar |  | 05_09_909W4 | 06/06/2018 | 06/06/2018 | 3 | 3 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 06/06/2018 | 4/17/2019 | Y | EXP | 205 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N
National Grid | WORCESTER | 666314 | 01605 | 10 |  |  | Solar |  | 05_07_913W47 | 01/17/2025 | 03/24/2025 | 9 | 5 | 4 | 03/25/2025 | 03/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 01/17/2025 | 6/12/2026 | Y | EXP | 365 | 05/22/2025 | 10/02/2025 | 134 | 0 | 134 |  |  | 12/10/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 642715 | 01266 | 4.64 |  |  | Solar |  | 05_07_712J1 | 09/25/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | NORTHAMPTON | 411189 | 01062 | 5 |  |  | Solar |  | 05_05_335W3 | 02/10/2022 | 02/22/2022 | 7 | 4 | 3 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 459650 | 02072 | 100 |  |  | Solar |  | 05_09_523L2 | 09/26/2022 | 11/07/2022 | 29 | 20 | 9 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/26/2022 | 2/13/2025 | Y | STD | 450 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | BROCKTON | 696492 | 02302 | 23 |  |  | Solar |  | 05_05_312W4 | 06/05/2025 | 06/10/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | MILFORD | 634838 | 01757 | 10 |  |  | Solar |  | 05_07_97W1 | 08/23/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | BELCHERTOWN | 175303 | 01007 | 4800 |  |  | Solar |  | 05_05_7L5 | 06/24/2014 | 06/24/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/02/2014 | 08/04/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 655535 | 01581 | 7.6 |  |  | Solar |  | 05_01_11J330 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 288929 | 02368 | 1000 |  |  | Solar |  | 05_09_1109W3 | 06/26/2020 | 07/15/2020 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2020 | 08/08/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 201270 | 02771 | 3 |  |  | Solar |  | 05_09_909W4 | 11/15/2018 | 12/19/2018 | 7 | 0 | 7 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 11/15/2018 | 1/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2019 | Connected |  | N
National Grid | WORCESTER | 672325 | 01605 | 10 |  |  | Solar |  | 05_07_913W47 | 02/17/2025 | 03/19/2025 | 1 | 0 | 1 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/17/2025 | 6/27/2026 | Y | EXP | 365 | 10/01/2025 | 10/22/2025 | 22 | 0 | 22 |  |  | 11/12/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 650146 | 01230 | 10 |  |  | Solar |  | 05_07_712J1 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 416720 | 01060 | 7.6 |  |  | Solar |  | 05_05_335W3 | 03/15/2022 | 03/17/2022 | 2 | 0 | 2 | 03/18/2022 | 03/18/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/15/2022 |  | Y | EXP | 365 | 01/07/2023 | 02/25/2023 | 50 | 0 | 50 |  |  | 3/8/2023 | Connected |  | N
National Grid | STOUGHTON | 459546 | 02072 | 150 |  |  | Solar |  | 05_09_523L2 | 09/23/2022 | 11/03/2022 | 28 | 17 | 11 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 11/28/2025 | Y | STD | 119 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | BROCKTON | 698560 | 02302 | 6.27 |  |  | Solar |  | 05_05_312W4 | 06/23/2025 | 09/15/2025 | 0 | 0 | 0 | 09/16/2025 | 09/16/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | UPTON | 637440 | 01568 | 5.76 |  |  | Solar |  | 05_07_97W1 | 09/03/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/03/2024 | 12/11/2025 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  | 12/11/2025 | Connected |  | N
National Grid | BELCHERTOWN | 175591 | 01007 | 1670 |  |  | Solar |  | 05_05_7L5 | 04/23/2014 | 04/23/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/05/2014 | 06/02/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2014 | 04/23/2014 | 12/31/2016 | Y | STD | 757 | 10/19/2015 | 02/18/2016 | 82 | 0 | 82 | 12/21/2015 | 12/21/2015 | 12/24/2015 | Connected |  | N
National Grid | WESTBOROUGH | 175077 | 01581 | 35 |  |  | Solar |  | 05_01_11J331 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 818 | 0 | 818 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2013 | 09/24/2013 | 7/31/2016 | Y | EXP | 991 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 305086 | 02368 | 0 |  |  | Solar |  | 05_09_1109W3 | 08/05/2020 | 08/17/2020 | 8 | 8 | 0 | 08/18/2020 | 08/18/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2020 | 08/05/2020 | 8/16/2021 | Y | EXP | 365 | 12/30/2020 | 01/25/2021 | 26 | 0 | 26 |  |  | 7/15/2021 | Connected |  | N
National Grid | REHOBOTH | 203430 | 02769 | 0 |  |  | Battery Add-On |  | 05_09_909W4 | 12/17/2018 | 01/19/2019 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2019 | 02/18/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 12/17/2018 | 12/31/2020 | Y | STD | 365 | 05/08/2020 | 10/21/2020 | 167 | 5 | 162 |  |  | 12/23/2020 | Connected |  | N
National Grid | WORCESTER | 672195 | 01605 | 7.6 |  |  | Solar |  | 05_07_913W47 | 02/14/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 5/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2025 | Connected |  | N
National Grid | EGREMONT | 656337 | 01252 | 3.48 |  |  | Solar |  | 05_07_712J1 | 11/22/2024 | 02/13/2025 | 11 | 8 | 3 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 11/22/2024 | 4/10/2026 | Y | EXP | 365 | 05/17/2025 | 08/08/2025 | 84 | 0 | 84 |  |  | 9/12/2025 | Connected |  | N
National Grid | NORTHAMPTON | 417539 | 01062 | 7.6 |  |  | Solar |  | 05_05_335W3 | 01/27/2023 | 03/18/2022 | 1 | 0 | 1 | 01/31/2023 | 01/31/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 01/27/2023 | 6/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2023 | Connected |  | Y
National Grid | STOUGHTON | 459446 | 02072 | 100 |  |  | Solar |  | 05_09_523L2 | 09/23/2022 | 11/14/2022 | 34 | 24 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 | 09/23/2022 | 2/5/2025 | Y | STD | 410 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | Y
National Grid | BROCKTON | 699713 | 02302 | 7.6 |  |  | Solar |  | 05_05_312W4 | 06/19/2025 | 07/02/2025 | 5 | 2 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/19/2025 | 8/18/2026 | Y | EXP | 365 | 09/13/2025 | 11/05/2025 | 54 | 0 | 54 |  |  | 1/7/2026 | Connected |  | N
National Grid | HOPEDALE | 638291 | 01747 | 5.76 |  |  | Solar |  | 05_07_97W1 | 09/06/2024 | 10/28/2024 | 27 | 25 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 | 12/12/2024 | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 | 9/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 175813 | 01009 | 40 |  |  | Solar |  | 05_05_7L5 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 10/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 6/24/2015 | 6/24/2015 | 11/23/2015 | Connected |  | N
National Grid | WESTBOROUGH | 587958 | 01581 | 825 |  |  | Natural Gas |  | 05_01_11J331 | 03/07/2024 |  | 179 | 170 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 305047 | 02368 | 0 |  |  | Solar |  | 05_09_1109W3 | 08/05/2020 | 08/17/2020 | 8 | 8 | 0 | 08/18/2020 | 08/18/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2020 |  | 8/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2020 | Connected |  | N
National Grid | REHOBOTH | 205909 | 02769 | 9.71 |  |  | Solar |  | 05_09_909W4 | 02/01/2019 | 02/13/2019 | 8 | 7 | 1 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 685308 | 01605 | 7.6 |  |  | Solar |  | 05_07_913W47 | 04/15/2025 | 05/02/2025 | 17 | 16 | 1 | 06/24/2025 | 06/24/2025 | 48 | 33 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 664339 | 01230 | 7.6 |  |  | Solar |  | 05_07_712J1 | 01/07/2025 | 01/31/2025 | 6 | 0 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | NORTHAMPTON | 427132 | 01062 | 5.376 |  |  | Solar |  | 05_05_335W3 | 04/29/2022 | 05/05/2022 | 5 | 2 | 3 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2023 | Connected |  | N
National Grid | STOUGHTON | 459286 | 02072 | 167.3 |  |  | Solar |  | 05_09_523L2 | 09/23/2022 | 11/04/2022 | 29 | 21 | 8 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 4/21/2025 | Y | STD | 500 | 11/16/2024 | 11/15/2024 | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | BROCKTON | 639754 | 02302 | 5.76 |  |  | Solar |  | 05_07_97W1 | 09/12/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 175956 | 01757 | 239.8 |  |  | Solar |  | 05_05_7L5 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 07/18/2015 | 08/14/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 08/14/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 6/30/2016 | N | EXP | 293 |  |  | 0 | 0 | 0 | 7/27/2016 | 7/27/2016 | 8/4/2016 | Connected |  | N
National Grid | PALMER | 689607 | 01069 | 5.76 |  |  | Solar |  | 05_01_11J334 | 05/05/2025 | 05/20/2025 | 3 | 0 | 3 | 06/02/2025 | 06/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 322044 | 01581 | 9.86 |  |  | Solar |  | 05_09_1109W3 | 10/27/2020 | 11/03/2020 | 4 | 2 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | RANDOLPH | 234095 | 02368 | 10 |  |  | Solar |  | 05_09_909W4 | 07/01/2019 | 07/02/2019 | 0 | 0 | 0 | 07/03/2019 | 07/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 11/15/2019 | N | EXP | 129 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | REHOBOTH | 683802 | 02769 | 4998 |  |  | Other |  | 05_07_913W67 | 10/16/2025 | 12/11/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 666538 | 01605 | 11.5 |  |  | Solar |  | 05_07_712J1 | 01/17/2025 | 02/07/2025 | 14 | 10 | 4 | 02/10/2025 | 02/10/2025 | 56 | 34 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 01/17/2025 | 9/29/2026 | Y | EXP | 365 | 10/24/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 11/15/2025 | Connected |  | Y
National Grid | STOCKBRIDGE | 438977 | 01266 | 15.2 |  |  | Solar |  | 05_05_335W3 | 06/21/2022 | 06/23/2022 | 2 | 0 | 2 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | NORTHAMPTON | 561289 | 01062 | 10 |  |  | Solar |  | 05_09_523L2 | 12/05/2023 | 12/06/2023 | 1 | 0 | 1 | 12/07/2023 | 12/07/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 711356 | 02072 | 13.12 |  |  | Solar |  | 05_05_312W4 | 08/15/2025 | 10/09/2025 | 12 | 10 | 2 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 643312 | 02333 | 3.8 |  |  | Solar |  | 05_07_97W1 | 09/27/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 09/27/2024 | 12/24/2025 | Y | EXP | 365 | 04/03/2025 | 06/02/2025 | 61 | 0 | 61 |  |  | 6/19/2025 | Connected |  | N
National Grid | HOPEDALE | 175955 | 01747 | 59.4 |  |  | Solar |  | 05_05_7L5 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 6/30/2016 | N | EXP | 388 |  |  | 0 | 0 | 0 | 6/15/2015 | 6/15/2015 | 3/18/2016 | Connected |  | N
National Grid | PALMER | 657838 | 01009 | 7.6 |  |  | Solar |  | 05_01_11J334 | 12/05/2024 | 01/22/2025 | 23 | 19 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | WESTBOROUGH | 327873 | 01581 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 11/23/2020 | 12/09/2020 | 10 | 9 | 1 | 12/10/2020 | 12/10/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 12/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | RANDOLPH | 260373 | 02368 | 8.41 |  |  | Solar |  | 05_09_909W4 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 05/16/2020 | 05/15/2020 | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | REHOBOTH | 176468 | 02769 | 6 |  |  | Solar |  | 05_07_913W67 | 03/17/2016 | 03/17/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/17/2016 | 3/23/2017 | Y | EXP | 345 | 01/25/2017 | 02/11/2017 | 13 | 0 | 13 | 3/15/2017 | 3/15/2017 | 3/17/2017 | Connected |  | N
National Grid | WORCESTER | 680819 | 01609 | 15.76 |  |  | Solar |  | 05_07_712J1 | 03/31/2025 | 04/03/2025 | 3 | 0 | 3 | 04/04/2025 | 04/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 447435 | 01230 | 15 |  |  | Solar |  | 05_05_335W3 | 09/16/2022 | 09/19/2022 | 1 | 0 | 1 | 09/20/2022 | 09/20/2022 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 09/16/2022 | 12/22/2023 | Y | EXP | 365 | 02/09/2023 | 03/08/2023 | 28 | 0 | 28 |  |  | 3/11/2023 | Connected |  | N
National Grid | NORTHAMPTON | 628785 | 01062 | 10 |  |  | Solar |  | 05_09_523L2 | 07/30/2024 | 08/14/2024 | 4 | 0 | 4 | 08/15/2024 | 08/15/2024 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | STOUGHTON | 679646 | 02072 | 0 |  |  | Other |  | 05_05_312W5 | 10/08/2025 | 11/20/2025 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 655942 | 02302 | 7.6 |  |  | Solar |  | 05_07_97W1 | 11/21/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | UPTON | 176853 | 01568 | 1000 |  |  | Solar |  | 05_05_7L5 | 11/12/2015 | 11/12/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2015 | 12/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/18/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 653116 | 01069 | 5.76 |  |  | Solar |  | 05_01_11J346 | 11/08/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WESTBOROUGH | 331061 | 01581 | 106.4 |  |  | Solar |  | 05_09_1109W3 | 12/16/2020 | 01/15/2021 | 20 | 12 | 8 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2021 | 12/16/2020 | 6/23/2023 | Y | STD | 620 |  |  | 0 | 0 | 0 |  |  | 6/23/2023 | Connected |  | N
National Grid | RANDOLPH | 265140 | 02368 | 0 |  |  | Solar |  | 05_09_909W4 | 11/24/2019 | 12/03/2019 | 5 | 0 | 5 | 12/04/2019 | 12/04/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 |  | 11/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | SEEKONK | 189720 | 02771 | 15.2 |  |  | Solar |  | 05_07_913W67 | 06/29/2018 | 06/29/2018 | 10 | 0 | 10 | 08/30/2018 | 08/30/2018 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2018 |  | 6/29/2020 | N | EXP | 500 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 370680 | 01609 | 675 |  |  | Solar |  | 05_07_75W1 | 08/12/2021 | 09/10/2021 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 08/12/2021 | 4/18/2026 | Y | STD | 518 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | GREAT BARRINGTON | 469257 | 01230 | 11.4 |  |  | Solar |  | 05_05_335W3 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 12/05/2022 | 1/13/2024 | Y | EXP | 365 | 03/01/2023 | 04/13/2023 | 44 | 0 | 44 |  |  | 5/10/2023 | Connected |  | N
National Grid | NORTHAMPTON | 648336 | 01062 | 9.92 |  |  | Solar |  | 05_09_523L2 | 10/18/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/18/2024 | 12/22/2025 | Y | EXP | 365 | 01/18/2025 | 02/11/2025 | 25 | 0 | 25 |  |  | 2/26/2025 | Connected |  | N
National Grid | STOUGHTON | 174692 | 02072 | 4000 |  |  |  |  | 05_05_312W5 | 10/26/2010 | 10/26/2010 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 657156 | 02302 | 7.6 |  |  | Solar |  | 05_07_97W1 | 11/26/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 11/26/2024 | 3/24/2026 | Y | EXP | 365 | 05/14/2025 | 11/07/2025 | 178 | 0 | 178 |  |  | 12/3/2025 | Connected |  | N
National Grid | UPTON | 176997 | 01568 | 10 |  |  | Solar |  | 05_05_7L5 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 07/19/2016 | 7/25/2017 | Y | EXP | 355 | 09/29/2016 | 10/11/2016 | 7 | 0 | 7 | 3/1/2017 | 3/1/2017 | 3/3/2017 | Connected |  | N
National Grid | PALMER | 711185 | 01069 | 7.6 |  |  | Solar |  | 05_01_11J347 | 08/11/2025 | 09/22/2025 | 2 | 0 | 2 | 10/20/2025 | 10/20/2025 | 10 | 1 | 9 | 11/13/2025 | 12/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 12/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 342184 | 01581 | 6.96 |  |  | Solar |  | 05_09_1109W3 | 02/15/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2021 | Connected |  | N
National Grid | RANDOLPH | 284382 | 02368 | 10 |  |  | Solar |  | 05_09_909W4 | 03/26/2020 | 04/08/2020 | 8 | 8 | 0 | 04/09/2020 | 04/09/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | SEEKONK | 204378 | 02771 | 13.8 |  |  | Solar |  | 05_07_913W67 | 02/26/2019 | 03/12/2019 | 9 | 9 | 0 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2019 | Connected |  | N
National Grid | WORCESTER | 347679 | 01605 | 812.5 |  |  | Solar |  | 05_07_75W1 | 04/22/2021 | 09/10/2021 | 98 | 87 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 04/22/2021 | 1/24/2026 | Y | STD | 518 | 02/01/2025 |  | 335 | 151 | 184 |  |  |  | Construction |  | N
National Grid | STOCKBRIDGE | 471899 | 01266 | 15.2 |  |  | Solar |  | 05_05_335W3 | 10/27/2022 | 10/28/2022 | 1 | 0 | 1 | 10/31/2022 | 10/31/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | NORTHAMPTON | 690691 | 01062 | 15.2 |  |  | Solar |  | 05_09_523L2 | 05/14/2025 | 05/23/2025 | 6 | 3 | 3 | 05/27/2025 | 05/27/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | STOUGHTON | 174886 | 02072 | 1500 |  |  | Solar |  | 05_05_312W5 | 02/21/2013 | 02/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2013 | 04/05/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 |  | 8/30/2013 | N | STD | 18 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 666717 | 02302 | 3.8 |  |  | Solar |  | 05_07_97W1 | 01/20/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 52 | 32 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | UPTON | 177503 | 01568 | 22.8 |  |  | Solar |  | 05_05_7L5 | 03/06/2017 | 03/06/2017 | 9 | 7 | 2 | 03/17/2017 | 03/17/2017 | 258 | 0 | 258 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/11/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 723563 | 01009 | 5.76 |  |  | Solar |  | 05_01_11J347 | 10/02/2025 | 10/09/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/02/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WESTBOROUGH | 344660 | 01581 | 10 |  |  | Solar |  | 05_09_1109W3 | 03/04/2021 | 03/22/2021 | 12 | 12 | 0 | 03/23/2021 | 03/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 6/22/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 5/11/2022 | Connected |  | N
National Grid | RANDOLPH | 287922 | 02368 | 2.4 |  |  | Solar |  | 05_09_909W4 | 05/29/2020 | 06/01/2020 | 0 | 0 | 0 | 06/02/2020 | 06/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/29/2020 | 6/1/2021 | Y | EXP | 365 | 10/08/2020 | 10/21/2020 | 13 | 0 | 13 |  |  | 11/10/2020 | Connected |  | N
National Grid | REHOBOTH | 207438 | 02769 | 3.8 |  |  | Solar |  | 05_07_913W67 | 01/29/2019 | 02/12/2019 | 9 | 0 | 9 | 02/13/2019 | 02/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | N
National Grid | WORCESTER | 429417 | 01605 | 480 |  |  | Solar |  | 05_07_75W1 | 06/06/2022 | 07/01/2022 | 18 | 12 | 6 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | GREAT BARRINGTON | 475185 | 01230 | 6.96 |  |  | Solar |  | 05_05_335W3 | 12/21/2022 | 01/03/2023 | 7 | 0 | 7 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | NORTHAMPTON | 695597 | 01062 | 11.4 |  |  | Solar |  | 05_09_523L2 | 06/02/2025 | 06/24/2025 | 15 | 12 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | STOUGHTON | 175128 | 02072 | 750 |  |  | Solar |  | 05_05_312W5 | 07/27/2011 | 07/27/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2011 | 01/23/2013 | 335 | 0 | 335 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2012 | 07/27/2011 | 12/31/2012 | Y | STD | 116 | 03/05/2013 | 04/22/2013 | 29 | 0 | 29 | 6/12/2013 | 6/12/2013 | 7/11/2013 | Connected |  | N
National Grid | BROCKTON | 684712 | 02302 | 11.5 |  |  | Solar |  | 05_07_97W1 | 04/18/2025 | 05/06/2025 | 15 | 10 | 5 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 177805 | 01568 | 496 |  |  | Solar |  | 05_05_7L5 | 10/12/2017 | 10/12/2017 | 30 | 23 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2017 | 01/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/26/2019 | N | STD | 368 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 731780 | 01007 | 10 |  |  | Solar |  | 05_01_11J347 | 11/06/2025 | 11/06/2025 | 2 | 0 | 2 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 346854 | 01581 | 4980 |  |  | Solar |  | 05_09_1109W3 | 12/15/2022 | 05/12/2023 | 101 | 93 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2023 | 11/02/2023 | 119 | 100 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 303203 | 02368 | 9.12 |  |  | Solar |  | 05_09_909W4 | 08/05/2020 | 08/11/2020 | 3 | 0 | 3 | 08/12/2020 | 08/12/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/05/2020 | 5/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | REHOBOTH | 288745 | 02769 | 6.96 |  |  | Solar |  | 05_07_913W67 | 04/21/2020 | 04/28/2020 | 5 | 5 | 0 | 04/29/2020 | 04/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 6/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174532 | 01602 | 520 |  |  | Solar |  | 05_07_75W1 | 02/18/2011 | 02/18/2011 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2011 | 05/05/2012 | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2012 |  | 10/31/2012 | N | STD | 168 |  |  | 0 | 0 | 0 | 3/6/2013 | 3/6/2013 | 3/6/2013 | Connected |  | N
National Grid | STOCKBRIDGE | 481179 | 01266 | 16 |  |  | Solar |  | 05_05_335W3 | 11/30/2022 | 12/08/2022 | 7 | 6 | 1 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | NORTHAMPTON | 698128 | 01062 | 12.54 |  |  | Solar |  | 05_09_523L2 | 06/13/2025 | 09/15/2025 | 64 | 62 | 2 | 09/16/2025 | 09/16/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 176007 | 02072 | 857.1 |  |  | Solar |  | 05_05_312W5 | 08/12/2015 | 08/12/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 42 | 15 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 684485 | 02072 | 7.6 |  |  | Solar |  | 05_07_97W1 | 04/11/2025 | 04/25/2025 | 9 | 6 | 3 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | UPTON | 177987 | 01568 | 15.2 |  |  | Solar |  | 05_05_7L5 | 08/28/2017 | 08/28/2017 | 35 | 31 | 4 | 10/20/2017 | 10/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2017 |  | 9/4/2018 | N | EXP | 319 |  |  | 0 | 0 | 0 | 12/11/2017 | 12/11/2017 | 12/19/2017 | Connected |  | N
National Grid | BELCHERTOWN | 652966 | 01007 | 8.7 |  |  | Solar |  | 05_01_11J347 | 11/21/2024 | 12/30/2024 | 6 | 1 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/21/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | WESTBOROUGH | 359175 | 01581 | 9.6 |  |  | Solar |  | 05_09_1109W3 | 05/19/2021 | 06/09/2021 | 14 | 13 | 1 | 06/10/2021 | 06/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  | 7/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2021 | Connected |  | N
National Grid | RANDOLPH | 325868 | 02368 | 15.2 |  |  | Solar |  | 05_09_909W4 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/13/2020 | 12/12/2022 | Y | EXP | 365 | 03/06/2021 | 04/06/2021 | 31 | 0 | 31 |  |  | 3/8/2022 | Connected |  | N
National Grid | REHOBOTH | 306593 | 02769 | 10 |  |  | Solar |  | 05_07_913W67 | 09/28/2020 | 10/01/2020 | 2 | 0 | 2 | 10/02/2020 | 10/02/2020 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 09/28/2020 | 9/1/2021 | Y | EXP | 365 | 03/17/2021 | 04/07/2021 | 21 | 0 | 21 |  |  | 5/13/2021 | Connected |  | N
National Grid | WORCESTER | 175513 | 01605 | 250 |  |  | Solar |  | 05_07_75W1 | 03/26/2014 | 03/26/2014 | 6 | 0 | 6 | 04/04/2014 | 04/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2014 |  | 7/31/2014 | N | EXP | 90 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 3/13/2015 | Connected |  | N
National Grid | STOCKBRIDGE | 485628 | 01266 | 7.6 |  |  | Solar |  | 05_05_335W3 | 12/27/2022 | 01/03/2023 | 4 | 0 | 4 | 01/04/2023 | 01/04/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2023 | Connected |  | N
National Grid | NORTHAMPTON | 176852 | 01062 | 60.42 |  |  | Solar |  | 05_05_312W5 | 11/11/2015 | 11/11/2015 | 1 | 1 | 0 | 11/16/2015 | 11/16/2015 | 267 | 0 | 267 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/18/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 712286 | 02072 | 3.8 |  |  | Solar |  | 05_07_97W2 | 08/14/2025 | 09/05/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 43 | 29 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | STOUGHTON | 178474 | 02072 | 636 |  |  | Solar |  | 05_05_7L5 | 03/07/2018 | 03/07/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/12/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 654510 | 01568 | 7.6 |  |  | Solar |  | 05_01_11J347 | 11/14/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 65 | 41 | 24 | 03/18/2025 | 05/14/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  | 05/14/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 360945 | 01007 | 10 |  |  | Solar |  | 05_09_1109W3 | 06/30/2021 | 01/10/2022 | 4 | 0 | 4 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 06/30/2021 | 1/11/2023 | Y | EXP | 365 | 12/23/2021 | 01/10/2022 | 19 | 0 | 19 |  |  | 1/24/2022 | Connected |  | Y
National Grid | WESTBOROUGH | 330696 | 01581 | 7.6 |  |  | Solar |  | 05_09_909W4 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/6/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 327515 | 02368 | 7.68 |  |  | Solar |  | 05_07_913W67 | 11/20/2020 | 12/15/2020 | 15 | 12 | 3 | 12/16/2020 | 12/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2021 | Connected |  | N
National Grid | REHOBOTH | 178019 | 02769 | 300 |  |  | Natural Gas |  | 05_07_75W1 | 06/29/2017 | 06/29/2017 | 8 | 6 | 2 | 07/13/2017 | 07/13/2017 | 177 | 0 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2017 |  | 7/5/2018 | N | EXP | 332 |  |  | 0 | 0 | 0 | 8/18/2017 | 8/18/2017 | 12/20/2018 | Connected |  | N
National Grid | WORCESTER | 489672 | 01605 | 0 |  |  | Solar |  | 05_05_335W3 | 01/04/2023 |  | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 676977 | 01252 | 750 |  |  | Solar |  | 05_09_523L4 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHAMPTON | 177275 | 01062 | 4500 |  |  | Solar |  | 05_05_312W5 | 02/06/2017 | 02/06/2017 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2017 | 03/02/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 715435 | 02072 | 10.15 |  |  | Solar |  | 05_07_97W2 | 08/28/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/28/2025 | 11/3/2026 | Y | EXP | 365 | 12/24/2025 | 01/06/2026 | 8 | 0 | 8 |  |  |  | Completion Documents |  | N
National Grid | AVON | 178457 | 02322 | 480 |  |  | Solar |  | 05_05_7L5 | 11/30/2017 | 11/30/2017 | 35 | 0 | 35 | 01/23/2018 | 01/23/2018 | 26 | 9 | 17 | 04/13/2018 | 06/11/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  | 06/11/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 4/15/2020 | N | EXP | 160 |  |  | 0 | 0 | 0 |  |  | 6/17/2020 | Connected |  | Y
National Grid | MILFORD | 669413 | 01757 | 7.6 |  |  | Solar |  | 05_01_11J347 | 02/03/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | BELCHERTOWN | 368959 | 01007 | 20 |  |  | Solar |  | 05_09_1109W3 | 02/16/2022 | 02/18/2022 | 2 | 0 | 2 | 02/22/2022 | 02/22/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | N
National Grid | WESTBOROUGH | 354333 | 01581 | 10 |  |  | Solar |  | 05_09_909W4 | 04/23/2021 | 04/26/2021 | 0 | 0 | 0 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | RANDOLPH | 336550 | 02368 | 7.6 |  |  | Solar |  | 05_07_913W67 | 02/19/2021 | 02/25/2021 | 3 | 0 | 3 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 | 02/19/2021 | 2/9/2023 | Y | EXP | 365 | 11/25/2021 | 01/10/2022 | 47 | 0 | 47 |  |  | 4/14/2022 | Connected |  | N
National Grid | SEEKONK | 178739 | 02771 | 249 |  |  | Solar |  | 05_07_75W1 | 04/18/2018 | 04/18/2018 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 493873 | 01605 | 10 |  |  | Solar |  | 05_05_335W3 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 | 02/14/2023 | 10/11/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | STOCKBRIDGE | 705630 | 01266 | 5.76 |  |  | Solar |  | 05_09_523L4 | 07/17/2025 | 09/15/2025 | 4 | 0 | 4 | 09/16/2025 | 09/16/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 177676 | 01062 | 56 |  |  | Solar |  | 05_05_312W5 | 07/21/2017 | 07/21/2017 | 8 | 4 | 4 | 08/03/2017 | 08/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/29/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 12/27/2017 | Connected |  | N
National Grid | STOUGHTON | 727611 | 02072 | 15.2 |  |  | Solar |  | 05_07_97W2 | 10/20/2025 | 10/24/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AVON | 178485 | 02322 | 1000 |  |  | Solar |  | 05_05_7L5 | 04/03/2018 | 04/03/2018 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2018 | 08/24/2018 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 376329 | 01568 | 7.6 |  |  | Solar |  | 05_01_11J351 | 09/21/2021 | 01/07/2022 | 51 | 50 | 1 | 12/07/2021 | 12/07/2021 | 22 | 0 | 22 | 04/05/2022 | 12/14/2023 | 422 | 0 | 422 |  |  | 0 | 0 | 0 |  | 12/14/2023 | 422 | 0 | 422 |  |  | 0 | 0 | 0 | 3/30/2022 |  | 8/20/2024 | N | EXP | 365 | 09/09/2023 | 12/14/2023 | 97 | 0 | 97 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 420606 | 01007 | 15.2 |  |  | Solar |  | 05_09_1109W3 | 03/29/2022 | 04/04/2022 | 4 | 3 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 378064 | 01581 | 3.8 |  |  | Solar |  | 05_09_909W4 | 09/09/2021 | 09/14/2021 | 3 | 0 | 3 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 347865 | 02368 | 9.8 |  |  | Solar |  | 05_07_913W67 | 04/20/2021 | 12/29/2021 | 3 | 0 | 3 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 04/20/2021 | 2/1/2023 | Y | EXP | 365 | 04/15/2022 | 10/04/2022 | 172 | 0 | 172 |  |  | 11/21/2022 | Connected |  | N
National Grid | REHOBOTH | 290740 | 02769 | 7.6 |  |  | Solar |  | 05_07_75W1 | 05/11/2020 | 05/22/2020 | 8 | 7 | 1 | 05/26/2020 | 05/26/2020 | 95 | 72 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 |  | 11/29/2021 | N | EXP | 405 |  |  | 0 | 0 | 0 |  |  | 11/19/2021 | Connected |  | N
National Grid | WORCESTER | 523162 | 01605 | 10 |  |  | Solar |  | 05_05_335W3 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/08/2023 | 8/23/2024 | Y | EXP | 365 | 08/02/2023 | 10/30/2023 | 90 | 0 | 90 |  |  | 1/9/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 735075 | 01236 | 7.6 |  |  | Solar |  | 05_09_523L4 | 11/20/2025 | 11/21/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTHAMPTON | 222837 | 01062 | 144 |  |  | Solar |  | 05_05_312W5 | 04/26/2019 | 06/14/2019 | 22 | 15 | 7 | 06/17/2019 | 06/17/2019 | 5 | 0 | 5 | 07/19/2019 | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 | 2/26/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 727914 | 02072 | 13.36 |  |  | Solar |  | 05_07_97W2 | 10/21/2025 | 10/25/2025 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | AVON | 620163 | 02322 | 5.76 |  |  | Solar |  | 05_01_11J351 | 06/24/2024 | 07/08/2024 | 2 | 0 | 2 | 07/09/2024 | 07/09/2024 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | UPTON | 428708 | 01568 | 11.4 |  |  | Solar |  | 05_09_1109W3 | 05/05/2022 | 05/09/2022 | 2 | 0 | 2 | 05/10/2022 | 05/10/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 |  | 7/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2022 | Connected |  | N
National Grid | BELCHERTOWN | 379683 | 01007 | 0 |  |  | Other |  | 05_09_909W4 | 09/02/2021 |  | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 356589 | 01581 | 9.8 |  |  | Solar |  | 05_07_913W67 | 05/05/2021 | 06/10/2021 | 1 | 0 | 1 | 06/11/2021 | 06/11/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2021 | 05/05/2021 | 12/23/2022 | Y | EXP | 365 | 11/02/2021 | 12/23/2021 | 52 | 0 | 52 |  |  | 3/25/2022 | Connected |  | N
National Grid | RANDOLPH | 591631 | 02368 | 7.6 |  |  | Solar |  | 05_07_75W1 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 02/23/2024 | 11/9/2025 | Y | EXP | 365 | 08/06/2024 | 09/17/2024 | 43 | 0 | 43 |  |  | 4/30/2025 | Connected |  | N
National Grid | REHOBOTH | 524693 | 02769 | 15.2 |  |  | Solar |  | 05_05_335W3 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/08/2023 | 12/7/2024 | Y | EXP | 365 | 09/26/2023 | 11/17/2023 | 53 | 0 | 53 |  |  | 1/16/2024 | Connected |  | N
National Grid | WORCESTER | 174243 | 01605 | 2000 |  |  | Solar |  | 05_09_523L4 | 02/21/2012 | 02/21/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 05/24/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 287647 | 01230 | 616 |  |  | Solar |  | 05_05_312W5 | 04/24/2020 | 05/06/2020 | 8 | 3 | 5 |  |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  | 8/24/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175563 | 01062 | 14.8 |  |  | Solar |  | 05_07_97W2 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 | 07/31/2014 | 10/31/2014 | Y | EXP | 59 | 10/07/2015 | 10/13/2015 | 3 | 0 | 3 | 10/26/2015 | 10/26/2015 | 10/26/2015 | Connected |  | N
National Grid | STOUGHTON | 178744 | 02072 | 726 |  |  | Solar |  | 05_05_7L5 | 05/29/2018 | 05/29/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2018 | 07/20/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2019 |  | 5/15/2020 | N | STD | 469 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 661688 | 02322 | 0 |  |  | Solar |  | 05_01_11J351 | 01/21/2025 | 02/14/2025 | 19 | 14 | 5 | 02/18/2025 | 02/18/2025 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | MILFORD | 437566 | 01757 | 15.2 |  |  | Solar |  | 05_09_1109W3 | 06/14/2022 | 06/16/2022 | 3 | 2 | 1 | 06/17/2022 | 06/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 |  | 12/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2023 | Connected |  | N
National Grid | WARE | 382307 | 01082 | 7.6 |  |  | Solar |  | 05_09_909W4 | 10/01/2021 | 01/04/2022 | 1 | 0 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 | 10/01/2021 | 1/20/2023 | Y | EXP | 365 | 01/05/2022 | 01/04/2022 | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | WESTBOROUGH | 398831 | 01581 | 9.8 |  |  | Solar |  | 05_07_913W67 | 12/20/2021 | 12/21/2021 | 1 | 0 | 1 | 12/22/2021 | 12/22/2021 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2022 | 12/20/2021 | 2/24/2024 | Y | EXP | 365 | 06/30/2022 | 02/22/2023 | 238 | 0 | 238 |  |  | 4/19/2023 | Connected |  | N
National Grid | RANDOLPH | 592939 | 02368 | 6 |  |  | Solar |  | 05_07_75W1 | 03/26/2024 | 04/03/2024 | 7 | 3 | 4 | 04/04/2024 | 04/04/2024 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/26/2024 | 5/7/2025 | Y | EXP | 365 | 06/01/2024 | 10/28/2024 | 140 | 0 | 140 |  |  | 10/19/2024 | Connected |  | N
National Grid | SEEKONK | 532580 | 02771 | 16.4 |  |  | Solar |  | 05_05_335W3 | 06/23/2023 | 06/26/2023 | 1 | 0 | 1 | 06/27/2023 | 06/27/2023 | 253 | 233 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | WORCESTER | 174292 | 01605 | 950 |  |  | Solar |  | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 163 | 322 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 287637 | 01252 | 200 |  |  | Solar |  | 05_05_312W5 | 04/13/2020 | 04/17/2020 | 3 | 0 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175584 | 01062 | 17 |  |  | Solar |  | 05_07_97W2 | 04/18/2014 | 04/18/2014 | 6 | 0 | 6 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2014 |  | 6/30/2014 | N | EXP | 60 |  |  | 0 | 0 | 0 | 6/23/2014 | 6/23/2014 | 7/10/2014 | Connected |  | N
National Grid | STOUGHTON | 187621 | 02072 | 4998 |  |  | Solar |  | 05_05_7L5 | 06/10/2018 | 06/10/2018 | 57 | 3 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2018 | 09/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 513744 | 02072 | 7.6 |  |  | Solar |  | 05_01_11J354 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 6/25/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | UPTON | 438767 | 01568 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 06/20/2022 | 06/24/2022 | 5 | 2 | 3 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | PALMER | 395501 | 01069 | 10 |  |  | Solar |  | 05_09_909W4 | 03/07/2022 | 03/08/2022 | 2 | 1 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 | 03/07/2022 | 6/13/2023 | Y | EXP | 365 | 05/19/2022 | 05/31/2022 | 13 | 0 | 13 |  |  | 8/12/2022 | Connected |  | N
National Grid | WESTBOROUGH | 417002 | 01581 | 9.84 |  |  | Solar |  | 05_07_913W67 | 03/10/2022 | 03/11/2022 | 1 | 0 | 1 | 03/14/2022 | 03/14/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 5/4/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 604070 | 02368 | 10 |  |  | Solar |  | 05_07_75W1 | 04/15/2024 | 04/24/2024 | 4 | 0 | 4 | 04/25/2024 | 04/25/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | REHOBOTH | 565699 | 02769 | 6 |  |  | Solar |  | 05_05_335W3 | 11/07/2023 | 11/16/2023 | 6 | 4 | 2 | 11/17/2023 | 11/17/2023 | 27 | 6 | 21 | 01/31/2024 | 03/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 2/16/2024 |  | 2/21/2025 | N | EXP | 365 | 05/18/2024 | 06/08/2024 | 22 | 0 | 22 |  |  | 6/18/2024 | Connected |  | N
National Grid | WORCESTER | 174291 | 01609 | 950 |  |  | Solar |  | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 483 | 0 | 483 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 293197 | 01230 | 7.6 |  |  | Solar |  | 05_05_312W5 | 05/22/2020 |  | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175767 | 01062 | 5000 |  |  | Solar |  | 05_07_97W2 | 06/12/2014 | 06/12/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/17/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 200359 | 02072 | 15.2 |  |  | Solar |  | 05_05_7L5 | 11/05/2018 | 11/08/2018 | 3 | 3 | 0 | 11/09/2018 | 11/09/2018 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 | 11/05/2018 | 10/14/2019 | Y | EXP | 256 | 05/08/2019 | 06/12/2019 | 35 | 0 | 35 |  |  | 7/20/2019 | Connected |  | N
National Grid | STOUGHTON | 538092 | 02072 | 10 |  |  | Solar |  | 05_01_11J354 | 07/05/2023 | 07/06/2023 | 2 | 1 | 1 | 07/07/2023 | 07/07/2023 | 90 | 50 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 454957 | 01568 | 9.86 |  |  | Solar |  | 05_09_1109W3 | 08/29/2022 | 09/01/2022 | 3 | 0 | 3 | 09/02/2022 | 09/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 |  | 11/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | WARE | 410687 | 01082 | 0 |  |  | Solar |  | 05_09_909W4 | 02/07/2022 | 02/23/2022 | 12 | 11 | 1 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/26/2023 | N | EXP | 390 |  |  | 0 | 0 | 0 |  |  | 3/7/2023 | Connected |  | N
National Grid | WESTBOROUGH | 432815 | 01581 | 0 |  |  | Solar |  | 05_07_913W67 | 06/09/2022 | 06/10/2022 | 1 | 0 | 1 | 06/13/2022 | 06/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 | 06/09/2022 | 10/11/2023 | Y | EXP | 365 | 09/15/2022 | 10/11/2022 | 27 | 0 | 27 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 710142 | 02368 | 15.76 |  |  | Solar |  | 05_07_75W1 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | REHOBOTH | 607126 | 02769 | 20 |  |  | Solar |  | 05_05_335W3 | 05/14/2024 | 05/28/2024 | 9 | 7 | 2 | 05/29/2024 | 05/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2024 | Connected |  | N
National Grid | WORCESTER | 174290 | 01609 | 950 |  |  | Solar |  | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 0 | 485 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 300962 | 01266 | 3.8 |  |  | Solar |  | 05_05_312W5 | 07/13/2020 | 12/14/2021 | 299 | 114 | 185 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  | 6/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175765 | 01062 | 16.01 |  |  | Solar |  | 05_07_97W2 | 06/06/2014 | 06/06/2014 | 5 | 2 | 3 | 06/16/2014 | 06/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2014 |  | 8/29/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 7/11/2014 | 7/11/2014 | 8/15/2014 | Connected |  | N
National Grid | STOUGHTON | 231935 | 02072 | 500 |  |  | Solar |  | 05_05_7L5 | 06/25/2019 | 07/29/2019 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2019 | 08/30/2019 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 560507 | 02072 | 3.8 |  |  | Solar |  | 05_01_11J354 | 10/18/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 458936 | 01568 | 0 |  |  | Solar |  | 05_09_1109W3 | 09/16/2022 | 09/21/2022 | 3 | 3 | 0 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/16/2022 | 11/1/2023 | Y | EXP | 365 | 01/28/2023 | 03/04/2023 | 36 | 0 | 36 |  |  | 4/27/2023 | Connected |  | N
National Grid | WARE | 418652 | 01082 | 15.2 |  |  | Solar |  | 05_09_909W4 | 03/18/2022 | 03/24/2022 | 5 | 4 | 1 | 03/25/2022 | 03/25/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2022 | Connected |  | N
National Grid | WESTBOROUGH | 467208 | 01581 | 5 |  |  | Solar |  | 05_07_913W67 | 11/10/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 699462 | 02368 | 7.6 |  |  | Solar |  | 05_07_75W3 | 06/18/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REHOBOTH | 609328 | 02769 | 7.6 |  |  | Solar |  | 05_05_335W3 | 05/07/2024 | 06/11/2024 | 1 | 0 | 1 | 06/12/2024 | 06/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 | 05/07/2024 | 7/15/2025 | Y | EXP | 365 | 12/11/2024 | 02/28/2025 | 80 | 0 | 80 |  |  | 3/7/2025 | Connected |  | N
National Grid | WORCESTER | 174289 | 01609 | 950 |  |  | Solar |  | 05_09_523L4 | 12/08/2011 | 12/08/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 485 | 0 | 485 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 697790 | 01230 | 3.84 |  |  | Solar |  | 05_05_312W5 | 06/19/2025 | 07/07/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 43 | 28 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | NORTHAMPTON | 176090 | 01062 | 7.6 |  |  | Solar |  | 05_07_97W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 6/30/2015 | Y | EXP | 125 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 4/20/2015 | 4/20/2015 | 11/9/2015 | Connected |  | N
National Grid | STOUGHTON | 288310 | 02072 | 0 |  |  | Other |  | 05_05_7L5 | 05/07/2020 | 08/26/2020 | 78 | 72 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 04/29/2021 | 166 | 34 | 132 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 564727 | 02072 | 8.12 |  |  | Solar |  | 05_01_11J354 | 10/25/2023 | 11/20/2023 | 17 | 15 | 2 | 11/21/2023 | 11/21/2023 | 149 | 29 | 120 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 461068 | 01747 | 30 |  |  | Solar |  | 05_09_1109W3 | 01/31/2023 | 02/08/2023 | 6 | 5 | 1 | 02/09/2023 | 02/09/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 |  | 7/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | PALMER | 458403 | 01069 | 10 |  |  | Solar |  | 05_09_909W4 | 01/30/2023 | 02/14/2023 | 11 | 9 | 2 | 02/15/2023 | 02/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 01/30/2023 | 10/25/2024 | Y | EXP | 365 | 10/10/2023 | 10/16/2023 | 7 | 0 | 7 |  |  | 11/16/2023 | Connected |  | Y
National Grid | WESTBOROUGH | 524728 | 01581 | 14.976 |  |  | Solar |  | 05_07_913W67 | 07/11/2023 | 05/23/2023 | 5 | 4 | 1 | 07/18/2023 | 07/18/2023 | 48 | 27 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  | 10/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | RANDOLPH | 735531 | 02368 | 10 |  |  | Solar |  | 05_07_75W3 | 11/21/2025 | 11/24/2025 | 2 | 0 | 2 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 611557 | 02769 | 7.6 |  |  | Solar |  | 05_05_335W3 | 05/16/2024 | 05/23/2024 | 2 | 0 | 2 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174288 | 01605 | 950 |  |  | Solar |  | 05_09_523L4 | 12/09/2011 | 12/09/2011 | 40 | 0 | 40 | 02/08/2012 | 02/08/2012 | 541 | 0 | 541 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 737612 | 01230 | 17.16 |  |  | Solar |  | 05_05_313W1 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 176247 | 01062 | 3780 |  |  | Solar |  | 05_07_97W2 | 05/01/2015 | 05/01/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 298439 | 02072 | 3.8 |  |  | Solar |  | 05_05_7L5 | 07/13/2020 | 07/14/2020 | 0 | 0 | 0 | 07/15/2020 | 07/15/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 7/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 590880 | 02072 | 1.74 |  |  | Solar |  | 05_01_11J354 | 02/23/2024 | 02/26/2024 | 1 | 0 | 1 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2024 | Connected |  | N
National Grid | UPTON | 465317 | 01568 | 10 |  |  | Solar |  | 05_09_1109W3 | 10/24/2022 | 10/26/2022 | 2 | 0 | 2 | 10/27/2022 | 10/27/2022 | 260 | 247 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 487983 | 01069 | 10 |  |  | Solar |  | 05_09_909W4 | 01/24/2023 | 01/26/2023 | 2 | 0 | 2 | 01/27/2023 | 01/27/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/24/2023 | 8/23/2024 | Y | EXP | 365 | 07/28/2023 | 07/27/2023 | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | WESTBOROUGH | 595908 | 01581 | 10 |  |  | Solar |  | 05_07_913W67 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | RANDOLPH | 175816 | 02368 | 360 |  |  | Solar |  | 05_07_75W3 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 554 | 0 | 554 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 9/6/2017 | N | EXP | 768 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 611117 | 02769 | 8.36 |  |  | Solar |  | 05_05_335W3 | 05/15/2024 | 05/21/2024 | 4 | 2 | 2 | 05/22/2024 | 05/22/2024 | 45 | 31 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | WORCESTER | 174652 | 01605 | 260 |  |  | Solar |  | 05_09_523L4 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | -40 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | Y
National Grid | GREAT BARRINGTON | 176924 | 01230 | 28 |  |  | Solar |  | 05_05_313W1 | 11/19/2015 | 11/19/2015 | 3 | 3 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/24/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 7/6/2016 | Connected |  | Y
National Grid | NORTHAMPTON | 176316 | 01062 | 3780 |  |  | Solar |  | 05_07_97W2 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 | 05/08/2015 | 11/9/2017 | Y | STD | 647 | 06/28/2017 | 10/24/2017 | 81 | 0 | 81 | 10/25/2017 | 10/25/2017 | 11/7/2017 | Connected |  | N
National Grid | STOUGHTON | 297893 | 02072 | 4500 |  |  | Other |  | 05_05_7L5 | 11/18/2020 | 01/25/2021 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2021 | 02/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 634170 | 02072 | 7.6 |  |  | Solar |  | 05_01_11J354 | 08/20/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 469401 | 01568 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 202 | 107 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 505781 | 01069 | 10.47 |  |  | Solar |  | 05_09_909W4 | 03/06/2023 | 03/08/2023 | 2 | 0 | 2 | 03/09/2023 | 03/09/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  | 4/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | WESTBOROUGH | 607609 | 01581 | 7.56 |  |  | Solar |  | 05_07_913W67 | 04/30/2024 | 05/06/2024 | 3 | 0 | 3 | 05/07/2024 | 05/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 178407 | 02368 | 498 |  |  | Solar |  | 05_07_75W3 | 04/02/2018 | 04/02/2018 | 12 | 3 | 9 |  |  | 67 | 42 | 25 | 08/20/2018 | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 |  | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 | 11/28/2018 |  | 10/1/2019 | N | STD | 307 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 654695 | 02771 | 5.76 |  |  | Solar |  | 05_05_335W3 | 12/05/2024 | 12/30/2024 | 6 | 2 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/05/2024 | 4/14/2026 | Y | EXP | 365 | 09/04/2025 | 10/16/2025 | 43 | 0 | 43 |  |  | 10/23/2025 | Connected |  | N
National Grid | WORCESTER | 175486 | 01605 | 4880 |  |  | Solar |  | 05_09_523L4 | 07/14/2014 | 07/14/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2014 | 08/19/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 01/27/2015 | 03/04/2015 | 25 | 0 | 25 | 3/12/2015 | 07/14/2014 | 6/1/2016 | Y | STD | 447 |  |  | 0 | 0 | 0 | 12/21/2015 | 12/21/2015 | 12/22/2015 | Connected |  | N
National Grid | GREAT BARRINGTON | 177320 | 01230 | 26.6 |  |  | Solar |  | 05_05_313W1 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2017 |  | 2/20/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/28/2017 | 9/28/2017 | 10/23/2017 | Connected |  | N
National Grid | NORTHAMPTON | 176580 | 01062 | 3.8 |  |  | Solar |  | 05_07_97W2 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 350 | 09/15/2016 | 10/18/2016 | 22 | 0 | 22 | 8/11/2016 | 8/11/2016 | 12/2/2016 | Connected |  | N
National Grid | STOUGHTON | 303042 | 02072 | 0 |  |  | Solar |  | 05_05_7L5 | 07/24/2020 | 07/30/2020 | 3 | 0 | 3 | 07/31/2020 | 07/31/2020 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2020 | Connected |  | N
National Grid | AVON | 636139 | 02322 | 7.6 |  |  | Solar |  | 05_01_11J354 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 31 | 24 | 7 | 11/20/2024 | 01/14/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  | 01/14/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 2/21/2026 | N | EXP | 365 | 06/26/2025 | 07/23/2025 | 28 | 0 | 28 |  |  | 8/21/2025 | Connected |  | N
National Grid | MILFORD | 471659 | 01757 | 16.34 |  |  | Solar |  | 05_09_1109W3 | 10/27/2022 | 11/07/2022 | 8 | 7 | 1 | 11/08/2022 | 11/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N
National Grid | PALMER | 528675 | 01069 | 7.6 |  |  | Solar |  | 05_09_909W4 | 05/26/2023 | 06/01/2023 | 3 | 0 | 3 | 06/02/2023 | 06/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 | 05/26/2023 | 7/6/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 8/12/2023 | Connected |  | N
National Grid | WESTBOROUGH | 617786 | 01581 | 10 |  |  | Solar |  | 05_07_913W67 | 06/13/2024 | 07/09/2024 | 2 | 0 | 2 | 07/10/2024 | 07/10/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 184781 | 02368 | 18.9 |  |  | Solar |  | 05_07_75W3 | 06/06/2018 | 06/06/2018 | 48 | 35 | 13 | 08/02/2018 | 08/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  | 8/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2019 | Connected |  | N
National Grid | SEEKONK | 663902 | 02771 | 18.2 |  |  | Solar |  | 05_05_335W3 | 01/08/2025 | 01/10/2025 | 2 | 0 | 2 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 01/08/2025 | 3/4/2026 | Y | EXP | 365 | 05/07/2025 | 05/07/2025 | 1 | 0 | 1 |  |  | 5/10/2025 | Connected |  | N
National Grid | WORCESTER | 175802 | 01605 | 4400 |  |  | Solar |  | 05_09_523L4 | 03/03/2015 | 03/03/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 03/03/2015 | 12/31/2016 | Y | STD | 446 | 09/02/2016 | 02/23/2017 | 116 | 0 | 116 |  |  | 12/30/2016 | Connected |  | N
National Grid | STOCKBRIDGE | 178346 | 01266 | 56 |  |  | Solar |  | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 29 | 19 | 10 | 02/02/2018 | 02/02/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 1/17/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | NORTHAMPTON | 176914 | 01062 | 11.4 |  |  | Solar |  | 05_07_97W2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 | 11/07/2016 | 11/26/2016 | 13 | 0 | 13 | 12/5/2016 | 12/5/2016 | 12/5/2016 | Connected |  | N
National Grid | STOUGHTON | 306988 | 02072 | 11.4 |  |  | Solar |  | 05_05_7L5 | 09/11/2020 | 09/16/2020 | 2 | 2 | 0 | 09/17/2020 | 09/17/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2020 | 09/11/2020 | 9/15/2021 | Y | EXP | 365 | 02/04/2021 | 04/07/2021 | 62 | 0 | 62 |  |  | 8/17/2021 | Connected |  | N
National Grid | AVON | 638685 | 02322 | 7.6 |  |  | Solar |  | 05_01_11J354 | 09/09/2024 | 09/20/2024 | 3 | 0 | 3 | 09/23/2024 | 09/23/2024 | 126 | 118 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 515132 | 01568 | 10 |  |  | Solar |  | 05_09_1109W3 | 03/30/2023 | 04/03/2023 | 2 | 0 | 2 | 04/04/2023 | 04/04/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | PALMER | 529594 | 01069 | 3.8 |  |  | Solar |  | 05_09_909W4 | 06/02/2023 | 06/06/2023 | 2 | 0 | 2 | 06/07/2023 | 06/07/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 645668 | 01532 | 10 |  |  | Solar |  | 05_07_913W67 | 10/25/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2025 | Connected |  | N
National Grid | RANDOLPH | 318608 | 02368 | 2.4 |  |  | Solar |  | 05_07_75W3 | 10/16/2020 | 10/22/2020 | 3 | 0 | 3 | 10/23/2020 | 10/23/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 12/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 672737 | 02769 | 15.2 |  |  | Solar |  | 05_05_335W3 | 02/20/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | WORCESTER | 176032 | 01605 | 499 |  |  | Solar |  | 05_09_523L4 | 06/19/2015 | 06/19/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/02/2015 | 07/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/19/2015 | 6/24/2016 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 178345 | 01230 | 72 |  |  | Solar |  | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 25 | 15 | 10 | 02/20/2018 | 02/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | NORTHAMPTON | 177471 | 01062 | 3.8 |  |  | Solar |  | 05_07_97W2 | 03/02/2017 | 03/02/2017 | 10 | 9 | 1 | 03/17/2017 | 03/17/2017 | 258 | 0 | 258 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/8/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 330889 | 02072 | 4946 |  |  | Solar |  | 05_05_7L5 | 02/05/2021 | 03/16/2021 | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2021 | 04/13/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 641165 | 02322 | 4.537 |  |  | Solar |  | 05_01_11J354 | 09/19/2024 | 10/08/2024 | 10 | 7 | 3 | 10/09/2024 | 10/09/2024 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/19/2024 | 11/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | MILFORD | 559483 | 01757 | 10 |  |  | Solar |  | 05_09_1109W3 | 11/10/2023 | 12/08/2023 | 19 | 18 | 1 | 12/11/2023 | 12/11/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/10/2023 | 3/25/2025 | Y | EXP | 365 | 04/23/2024 | 05/01/2024 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 547130 | 01082 | 15.2 |  |  | Solar |  | 05_09_909W4 | 08/09/2023 | 08/15/2023 | 4 | 0 | 4 | 08/16/2023 | 08/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 7/24/2025 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 652373 | 01532 | 5.76 |  |  | Solar |  | 05_07_913W67 | 11/14/2024 | 12/17/2024 | 12 | 7 | 5 | 12/18/2024 | 12/18/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 378486 | 02368 | 5.76 |  |  | Solar |  | 05_07_75W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 678931 | 02769 | 5.76 |  |  | Solar |  | 05_05_335W3 | 03/18/2025 | 04/01/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 03/18/2025 | 6/2/2026 | Y | EXP | 365 | 08/28/2025 | 10/18/2025 | 52 | 0 | 52 |  |  | 10/29/2025 | Connected |  | N
National Grid | WORCESTER | 177148 | 01605 | 4 |  |  | Solar |  | 05_09_523L4 | 08/08/2016 | 08/08/2016 | 22 | 22 | 0 | 09/12/2016 | 09/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 08/08/2016 | 8/15/2017 | Y | EXP | 330 | 04/11/2017 | 05/11/2017 | 21 | 0 | 21 | 5/15/2017 | 5/15/2017 | 5/18/2017 | Connected |  | N
National Grid | STOCKBRIDGE | 207452 | 01266 | 10 |  |  | Solar |  | 05_05_313W1 | 01/29/2019 | 02/12/2019 | 9 | 0 | 9 | 02/13/2019 | 02/13/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2019 | Connected |  | N
National Grid | NORTHAMPTON | 177961 | 01062 | 8.96 |  |  | Solar |  | 05_07_97W2 | 10/24/2017 | 10/24/2017 | 12 | 11 | 1 | 11/21/2017 | 11/21/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | STOUGHTON | 342714 | 02072 | 7.6 |  |  | Solar |  | 05_05_7L5 | 03/08/2021 | 04/14/2021 | 27 | 27 | 0 | 04/15/2021 | 04/15/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 5/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 648897 | 02322 | 3.8 |  |  | Solar |  | 05_01_11J354 | 11/18/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | UPTON | 528486 | 01568 | 14.79 |  |  | Solar |  | 05_09_1109W3 | 06/23/2023 | 07/07/2023 | 10 | 6 | 4 | 07/10/2023 | 07/10/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | PALMER | 548485 | 01069 | 6 |  |  | Solar |  | 05_09_909W4 | 08/23/2023 | 08/29/2023 | 4 | 0 | 4 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 521849 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 391865 | 02368 | 0 |  |  | Other |  | 05_07_75W3 | 01/18/2022 | 01/28/2022 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 02/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 680330 | 02771 | 10 |  |  | Solar |  | 05_05_335W3 | 03/25/2025 | 05/01/2025 | 26 | 23 | 3 | 05/02/2025 | 05/02/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 | 03/25/2025 | 7/21/2026 | Y | EXP | 365 | 09/13/2025 |  | 111 | 0 | 111 |  |  | 12/11/2025 | Connected |  | N
National Grid | WORCESTER | 177311 | 01605 | 3468 |  |  | Solar |  | 05_09_523L4 | 02/09/2017 | 02/15/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/09/2017 | 10/1/2019 | Y | STD | 666 | 12/06/2018 | 02/21/2019 | 77 | 0 | 77 |  |  | 9/17/2019 | Connected |  | N
National Grid | GREAT BARRINGTON | 224878 | 01230 | 10 |  |  | Solar |  | 05_05_313W1 | 05/28/2019 | 05/30/2019 | 1 | 0 | 1 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 |  | 6/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2019 | Connected |  | N
National Grid | NORTHAMPTON | 187799 | 01062 | 15.2 |  |  | Solar |  | 05_07_97W2 | 06/12/2018 | 06/12/2018 | 12 | 0 | 12 | 06/22/2018 | 06/22/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 366959 | 02072 | 9.8 |  |  | Solar |  | 05_05_7L5 | 07/30/2021 | 12/14/2021 | 3 | 0 | 3 | 08/05/2021 | 08/05/2021 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 653802 | 02322 | 11.5 |  |  | Solar |  | 05_01_11J354 | 11/18/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 69 | 44 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | UPTON | 544313 | 01568 | 22.8 |  |  | Solar |  | 05_09_1109W3 | 07/31/2023 | 08/01/2023 | 1 | 0 | 1 | 08/02/2023 | 08/02/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2023 | Connected |  | N
National Grid | PALMER | 552016 | 01069 | 0 |  |  | Solar |  | 05_09_909W4 | 10/05/2023 | 10/09/2023 | 2 | 0 | 2 | 10/10/2023 | 10/10/2023 | 93 | 50 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 521835 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/23/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 412236 | 02368 | 0 |  |  | Battery Add-On |  | 05_07_75W3 | 10/02/2022 | 11/15/2022 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 | 08/03/2023 | 178 | 158 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 683416 | 02769 | 10 |  |  | Solar |  | 05_05_335W3 | 04/07/2025 | 04/11/2025 | 4 | 0 | 4 | 04/14/2025 | 04/14/2025 | 64 | 49 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 | 04/07/2025 | 7/30/2026 | Y | EXP | 365 | 11/04/2025 |  | 59 | 0 | 59 |  |  | 12/11/2025 | Connected |  | N
National Grid | WORCESTER | 177604 | 01605 | 7.6 |  |  | Solar |  | 05_09_523L4 | 07/19/2017 | 07/19/2017 | 6 | 0 | 6 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/25/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 3/28/2018 | 3/28/2018 | 3/28/2018 | Connected |  | N
National Grid | GREAT BARRINGTON | 253609 | 01230 | 15.2 |  |  | Solar |  | 05_05_313W1 | 09/11/2019 | 09/16/2019 | 3 | 3 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | NORTHAMPTON | 194982 | 01062 | 7.6 |  |  | Solar |  | 05_07_97W2 | 09/04/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 09/04/2018 | 5/21/2019 | Y | EXP | 222 | 11/09/2018 | 02/27/2019 | 110 | 0 | 110 |  |  | 4/18/2019 | Connected |  | N
National Grid | STOUGHTON | 383572 | 02072 | 15.2 |  |  | Solar |  | 05_05_7L5 | 09/21/2021 | 12/09/2021 | 3 | 0 | 3 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 657179 | 02322 | 7.6 |  |  | Solar |  | 05_01_11J354 | 11/26/2024 | 12/19/2024 | 4 | 0 | 4 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | UPTON | 547421 | 01568 | 5 |  |  | Solar |  | 05_09_1109W3 | 08/10/2023 | 08/15/2023 | 4 | 3 | 1 | 08/16/2023 | 08/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2023 | Connected |  | N
National Grid | PALMER | 553933 | 01079 | 22.8 |  |  | Solar |  | 05_09_909W4 | 09/12/2023 | 09/18/2023 | 4 | 0 | 4 | 09/19/2023 | 09/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  | 11/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 521247 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 579567 | 02368 | 4.35 |  |  | Solar |  | 05_07_75W3 | 01/18/2024 | 01/19/2024 | 1 | 0 | 1 | 01/22/2024 | 01/22/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | SEEKONK | 686253 | 02771 | 11.52 |  |  | Solar |  | 05_05_335W3 | 04/18/2025 | 05/19/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177956 | 01605 | 1980 |  |  | Solar |  | 05_09_523L4 | 10/23/2017 | 10/23/2017 | 104 | 100 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 259202 | 01266 | 3.8 |  |  | Solar |  | 05_05_313W1 | 10/18/2019 | 10/22/2019 | 1 | 0 | 1 | 10/23/2019 | 10/23/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/18/2019 | 10/18/2020 | Y | EXP | 365 | 02/12/2020 | 04/02/2020 | 50 | 0 | 50 |  |  | 6/3/2020 | Connected |  | N
National Grid | NORTHAMPTON | 192557 | 01062 | 15.2 |  |  | Solar |  | 05_07_97W2 | 08/02/2018 | 08/15/2018 | 7 | 0 | 7 | 08/16/2018 | 08/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 428659 | 02072 | 0 |  |  | Other |  | 05_05_7L5 | 10/05/2022 | 01/04/2023 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2023 | 02/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 658161 | 02322 | 3.8 |  |  | Solar |  | 05_01_11J354 | 12/03/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 139 | 116 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 583485 | 01757 | 3.8 |  |  | Solar |  | 05_09_1109W3 | 03/14/2024 | 03/19/2024 | 3 | 0 | 3 | 03/20/2024 | 03/20/2024 | 2 | 0 | 2 | 04/03/2024 | 05/16/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 05/16/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | PALMER | 564752 | 01069 | 5 |  |  | Solar |  | 05_09_909W4 | 11/22/2023 | 12/07/2023 | 11 | 9 | 2 | 12/08/2023 | 12/08/2023 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/22/2023 | 3/6/2025 | Y | EXP | 365 | 03/30/2024 | 04/09/2024 | 11 | 0 | 11 |  |  | 4/11/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 521153 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 680142 | 02368 | 11.5 |  |  | Solar |  | 05_07_75W3 | 03/26/2025 | 03/31/2025 | 3 | 0 | 3 | 04/01/2025 | 04/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | REHOBOTH | 692742 | 02769 | 12.92 |  |  | Solar |  | 05_05_335W3 | 05/20/2025 | 06/02/2025 | 6 | 3 | 3 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | WORCESTER | 178136 | 01605 | 15.2 |  |  | Solar |  | 05_09_523L4 | 03/22/2018 | 03/29/2018 | 4 | 4 | 0 | 03/29/2018 | 03/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 3/28/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 12/6/2019 | Connected |  | N
National Grid | STOCKBRIDGE | 317103 | 01236 | 10 |  |  | Solar |  | 05_05_313W1 | 10/05/2020 | 10/08/2020 | 2 | 0 | 2 | 10/09/2020 | 10/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2020 | Connected |  | N
National Grid | NORTHAMPTON | 201002 | 01062 | 15.2 |  |  | Solar |  | 05_07_97W2 | 11/12/2018 | 11/16/2018 | 2 | 0 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2019 | 11/12/2018 | 7/22/2020 | Y | EXP | 365 | 01/30/2020 | 02/20/2020 | 21 | 0 | 21 |  |  | 7/14/2020 | Connected |  | N
National Grid | STOUGHTON | 443865 | 02072 | 10 |  |  | Solar |  | 05_05_7L5 | 08/04/2022 | 08/09/2022 | 4 | 3 | 1 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2022 |  | 10/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2022 | Connected |  | N
National Grid | AVON | 666118 | 02322 | 5.76 |  |  | Solar |  | 05_01_11J354 | 01/16/2025 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 589495 | 01568 | 15.66 |  |  | Solar |  | 05_09_1109W3 | 02/12/2024 | 03/08/2024 | 19 | 16 | 3 | 03/11/2024 | 03/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | PALMER | 596291 | 01069 | 0 |  |  | Solar |  | 05_09_909W4 | 03/12/2024 | 03/15/2024 | 3 | 1 | 2 | 03/18/2024 | 03/18/2024 | 54 | 54 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 521138 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 638260 | 02368 | 990 |  |  | Solar |  | 05_07_75W5 | 05/08/2025 | 07/09/2025 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SEEKONK | 699488 | 02771 | 17.6 |  |  | Solar |  | 05_05_335W3 | 07/23/2025 | 07/30/2025 | 5 | 0 | 5 | 07/31/2025 | 07/31/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | WORCESTER | 178373 | 01605 | 7.6 |  |  | Solar |  | 05_09_523L4 | 11/20/2017 | 11/20/2017 | 92 | 87 | 5 | 07/10/2018 | 07/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2018 |  | 11/26/2018 | N | EXP | 140 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EGREMONT | 343188 | 01230 | 11.4 |  |  | Solar |  | 05_05_313W1 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 121 | 73 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 223131 | 01062 | 199.8 |  |  | Solar |  | 05_07_97W2 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 07/19/2019 | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 |  | 07/30/2020 | 260 | 151 | 109 |  |  | 0 | 0 | 0 | 9/4/2020 | 04/27/2019 | 10/11/2022 | Y | EXP | 245 | 05/11/2021 | 01/04/2022 | 239 | 226 | 13 |  |  | 9/15/2022 | Connected |  | N
National Grid | STOUGHTON | 447033 | 02072 | 7.296 |  |  | Solar |  | 05_05_7L5 | 08/03/2022 | 08/05/2022 | 3 | 2 | 1 | 08/08/2022 | 08/08/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 | 08/03/2022 | 2/2/2024 | Y | EXP | 365 | 01/28/2023 | 01/27/2023 | 0 | 0 | 0 |  |  | 2/24/2023 | Connected |  | N
National Grid | AVON | 669755 | 02322 | 5.76 |  |  | Solar |  | 05_01_11J354 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 603142 | 01568 | 20 |  |  | Solar |  | 05_09_1109W3 | 04/10/2024 | 04/16/2024 | 3 | 1 | 2 | 04/17/2024 | 04/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2024 | Connected |  | N
National Grid | WARE | 600071 | 01082 | 5 |  |  | Solar |  | 05_09_909W4 | 04/02/2024 | 04/03/2024 | 1 | 0 | 1 | 04/04/2024 | 04/04/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 | 04/02/2024 | 4/23/2025 | Y | EXP | 365 | 05/24/2024 | 08/15/2024 | 84 | 0 | 84 |  |  | 9/5/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 521117 | 01532 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 174838 | 02368 | 75 |  |  | Solar |  | 05_07_75W5 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2012 | 08/28/2012 | 12/27/2012 | Y | EXP | 10 | 04/10/2013 | 04/22/2013 | 7 | 0 | 7 | 4/23/2013 | 4/23/2013 | 6/3/2013 | Connected |  | Y
National Grid | SEEKONK | 708240 | 02771 | 10 |  |  | Solar |  | 05_05_335W3 | 07/29/2025 | 09/09/2025 | 3 | 0 | 3 | 09/10/2025 | 09/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 07/29/2025 | 10/20/2026 | Y | EXP | 365 | 12/12/2025 |  | 21 | 0 | 21 |  |  | 12/13/2025 | Connected |  | N
National Grid | WORCESTER | 381762 | 01605 | 15.2 |  |  | Solar |  | 05_05_313W1 | 09/13/2021 | 10/04/2021 | 15 | 14 | 1 | 10/05/2021 | 10/05/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 1/17/2023 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | GREAT BARRINGTON | 228709 | 01230 | 7.6 |  |  | Solar |  | 05_07_97W2 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 457493 | 01062 | 10 |  |  | Solar |  | 05_05_7L5 | 10/19/2022 | 11/04/2022 | 12 | 10 | 2 | 11/07/2022 | 11/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2023 | Connected |  | N
National Grid | STOUGHTON | 669842 | 02072 | 3.8 |  |  | Solar |  | 05_01_11J357 | 02/04/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/04/2025 | 5/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | AVON | 613110 | 02322 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 05/23/2024 | 06/07/2024 | 7 | 5 | 2 | 06/10/2024 | 06/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/23/2024 | 6/26/2025 | Y | EXP | 365 | 07/26/2024 | 08/21/2024 | 27 | 0 | 27 |  |  | 8/24/2024 | Connected |  | N
National Grid | UPTON | 612200 | 01568 | 7.6 |  |  | Solar |  | 05_09_909W4 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 521110 | 01069 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 174929 | 01532 | 990 |  |  | Solar |  | 05_07_75W5 | 08/22/2013 | 08/22/2013 | 6 | 0 | 6 | 09/03/2013 | 09/03/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 08/22/2013 | 1/31/2014 | Y | EXP | 3 | 11/05/2014 | 12/18/2014 | 29 | 0 | 29 | 12/16/2014 | 12/16/2014 | 12/30/2014 | Connected |  | N
National Grid | RANDOLPH | 195290 | 02368 | 0 |  |  | Other |  | 05_05_335W4 | 12/05/2018 | 03/18/2019 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2019 | 04/24/2019 | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2019 |  | 3/14/2026 | N | STD | 63 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SEEKONK | 178491 | 02771 | 4000 |  |  | Solar |  | 05_09_523L4 | 12/01/2017 | 12/01/2017 | 41 | 40 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 02/28/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 414064 | 01605 | 15.2 |  |  | Solar |  | 05_05_313W1 | 02/24/2022 | 02/28/2022 | 3 | 2 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 230807 | 01266 | 13.6 |  |  | Solar |  | 05_07_97W2 | 06/26/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 | 06/26/2019 | 6/1/2020 | Y | EXP | 365 | 01/24/2020 | 02/05/2020 | 12 | 0 | 12 |  |  | 2/6/2020 | Connected |  | N
National Grid | NORTHAMPTON | 486773 | 01062 | 8.12 |  |  | Solar |  | 05_05_7L5 | 01/19/2023 | 02/01/2023 | 9 | 7 | 2 | 02/02/2023 | 02/02/2023 | 21 | 4 | 17 | 03/09/2023 | 03/24/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 03/24/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 10/3/2024 | N | EXP | 365 | 08/03/2023 | 10/04/2023 | 63 | 0 | 63 |  |  | 10/10/2023 | Connected |  | Y
National Grid | STOUGHTON | 737631 | 02072 | 4.56 |  |  | Solar |  | 05_01_11J357 | 12/02/2025 | 12/12/2025 | 1 | 0 | 1 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AVON | 613078 | 02322 | 999 |  |  | Solar |  | 05_09_1109W3 | 12/16/2024 | 03/05/2025 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2025 | 04/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 622038 | 01568 | 11.5 |  |  | Solar |  | 05_09_909W4 | 07/02/2024 | 07/31/2024 | 1 | 0 | 1 | 08/01/2024 | 08/01/2024 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | PALMER | 519326 | 01079 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/25/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 175391 | 01532 | 266 |  |  | Solar |  | 05_07_75W5 | 09/12/2014 | 09/12/2014 | 6 | 0 | 6 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 | 02/27/2015 | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 4/14/2015 |  | 12/31/2016 | N | EXP | 627 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 3/7/2017 | Connected |  | N
National Grid | RANDOLPH | 731683 | 02368 | 10 |  |  | Solar |  | 05_05_335W4 | 11/05/2025 | 11/05/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REHOBOTH | 192365 | 02769 | 7999 |  |  | Solar |  | 05_09_523L4 | 10/15/2018 | 11/09/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 01/08/2019 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 430956 | 01605 | 15.2 |  |  | Solar |  | 05_05_313W1 | 05/16/2022 | 05/18/2022 | 2 | 0 | 2 | 05/19/2022 | 05/19/2022 | 111 | 92 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 05/16/2022 | 7/27/2024 | Y | EXP | 365 | 02/07/2023 | 07/25/2023 | 169 | 0 | 169 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 265635 | 01230 | 4.55 |  |  | Solar |  | 05_07_97W2 | 11/21/2019 |  | 83 | 80 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 492065 | 01062 | 7.6 |  |  | Solar |  | 05_05_7L5 | 03/23/2023 | 01/24/2023 | 3 | 3 | 0 | 03/29/2023 | 03/29/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2023 |  | 5/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | STOUGHTON | 651292 | 02072 | 6.46 |  |  | Solar |  | 05_01_11J357 | 11/01/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | AVON | 616894 | 02322 | 50 |  |  | Solar |  | 05_09_1109W3 | 06/10/2024 | 06/20/2024 | 7 | 3 | 4 | 06/21/2024 | 06/21/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | UPTON | 627934 | 01568 | 10 |  |  | Solar |  | 05_09_909W4 | 09/23/2024 | 10/08/2024 | 12 | 8 | 4 | 10/09/2024 | 10/09/2024 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | WARE | 536065 | 01082 | 25 |  |  | Solar |  | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/20/2023 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/23/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 175879 | 01532 | 446.4 |  |  | Solar |  | 05_07_75W5 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 |  | 9/30/2015 | N | EXP | 182 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 3/30/2017 | Connected |  | N
National Grid | RANDOLPH | 738359 | 02368 | 11.5 |  |  | Solar |  | 05_05_335W4 | 12/05/2025 | 12/09/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 192328 | 02769 | 7.6 |  |  | Solar |  | 05_09_523L4 | 07/31/2018 | 11/07/2018 | 29 | 26 | 3 | 11/08/2018 | 11/08/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 | 07/31/2018 | 8/28/2019 | Y | EXP | 252 | 04/19/2019 | 04/18/2019 | 0 | 0 | 0 |  |  | 5/25/2019 | Connected |  | N
National Grid | WORCESTER | 492962 | 01605 | 14.5 |  |  | Solar |  | 05_05_313W1 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/01/2023 | 9/8/2024 | Y | EXP | 365 | 05/11/2023 | 09/06/2023 | 119 | 0 | 119 |  |  | 1/27/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 287352 | 01230 | 7.6 |  |  | Solar |  | 05_07_97W2 | 06/10/2020 | 06/15/2020 | 2 | 0 | 2 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/10/2020 | 6/30/2021 | Y | EXP | 365 | 01/29/2021 | 03/11/2021 | 41 | 0 | 41 |  |  | 6/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 493282 | 01062 | 50 |  |  | Solar |  | 05_05_7L5 | 03/22/2023 | 04/24/2023 | 22 | 13 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 657184 | 02072 | 5.76 |  |  | Solar |  | 05_01_11J357 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/26/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 634705 | 02322 | 11.5 |  |  | Solar |  | 05_09_1109W3 | 08/22/2024 | 09/04/2024 | 8 | 6 | 2 | 09/05/2024 | 09/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | N
National Grid | UPTON | 631183 | 01568 | 10 |  |  | Solar |  | 05_09_909W4 | 08/20/2024 | 08/21/2024 | 1 | 0 | 1 | 08/22/2024 | 08/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 174674 | 01082 | 170 |  |  | Solar |  | 05_07_913W69 | 06/03/2013 | 06/03/2013 | 9 | 2 | 7 | 06/17/2013 | 06/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2013 |  | 5/30/2014 | N | EXP | 312 |  |  | 0 | 0 | 0 | 7/30/2013 | 7/30/2013 | 6/2/2014 | Connected |  | N
National Grid | NORTHBOROUGH | 176324 | 01532 | 50 |  |  | Solar |  | 05_07_75W5 | 07/16/2015 | 07/16/2015 | 3 | 3 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 7/21/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N
National Grid | RANDOLPH | 743765 | 02368 | 60 |  |  | Solar |  | 05_05_335W4 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REHOBOTH | 214399 | 02769 | 15.2 |  |  | Solar |  | 05_09_523L4 | 03/19/2019 | 03/28/2019 | 6 | 0 | 6 | 03/29/2019 | 03/29/2019 | 66 | 38 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 557386 | 01605 | 17.4 |  |  | Solar |  | 05_05_313W1 | 09/22/2023 | 10/11/2023 | 12 | 9 | 3 | 10/12/2023 | 10/12/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 310071 | 01266 | 5 |  |  | Solar |  | 05_07_97W2 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 4/26/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 517932 | 01062 | 13.05 |  |  | Solar |  | 05_05_7L5 | 04/10/2023 | 04/13/2023 | 3 | 2 | 1 | 04/14/2023 | 04/14/2023 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 |  | 7/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | STOUGHTON | 175482 | 02072 | 47.3 |  |  | Solar |  | 05_01_12J376 | 03/21/2014 | 03/21/2014 | 5 | 1 | 4 | 04/01/2014 | 04/01/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2014 |  | 5/30/2014 | N | EXP | 51 |  |  | 0 | 0 | 0 | 4/14/2014 | 4/14/2014 | 7/11/2014 | Connected |  | N
National Grid | AVON | 644061 | 02322 | 10 |  |  | Solar |  | 05_09_1109W3 | 10/01/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 647226 | 01757 | 7.6 |  |  | Solar |  | 05_09_909W4 | 10/15/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/15/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | PALMER | 176150 | 01069 | 100 |  |  | Solar |  | 05_07_913W69 | 08/28/2015 | 08/28/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 9/5/2016 | N | EXP | 370 |  |  | 0 | 0 | 0 | 2/4/2016 | 2/4/2016 | 3/9/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 176443 | 01532 | 360 |  |  | Solar |  | 05_07_75W5 | 05/15/2016 | 05/15/2016 | 21 | 21 | 0 | 06/15/2016 | 06/15/2016 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176021 | 02368 | 820 |  |  | Natural Gas |  | 05_05_335W4 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 05/20/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 |  | 12/31/2016 | N | STD | 438 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | SEEKONK | 217150 | 02771 | 7.6 |  |  | Solar |  | 05_09_523L4 | 04/03/2019 |  | 321 | 25 | 296 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/6/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 553637 | 01605 | 160 |  |  | Solar |  | 05_05_313W1 | 09/11/2023 | 09/24/2023 | 9 | 0 | 9 | 09/25/2023 | 09/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/11/2023 | 1/5/2026 | Y | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 319113 | 01230 | 5 |  |  | Solar |  | 05_07_97W2 | 11/22/2020 | 11/24/2020 | 1 | 0 | 1 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/22/2020 |  | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 6/22/2021 | Connected |  | N
National Grid | NORTHAMPTON | 570949 | 01062 | 0 |  |  | Solar |  | 05_05_7L5 | 11/13/2023 | 11/17/2023 | 4 | 3 | 1 | 11/20/2023 | 11/20/2023 | 45 | 18 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | STOUGHTON | 651009 | 02072 | 5.76 |  |  | Solar |  | 05_01_12J376 | 11/12/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | AVON | 650232 | 02322 | 10 |  |  | Solar |  | 05_09_1109W3 | 10/28/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/28/2024 | 1/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 647872 | 01747 | 20 |  |  | Solar |  | 05_09_909W4 | 10/24/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | PALMER | 176571 | 01069 | 300 |  |  | Solar |  | 05_07_913W69 | 02/10/2016 | 02/10/2016 | 1 | 1 | 0 | 02/12/2016 | 02/12/2016 | 180 | 0 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/16/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 177908 | 01532 | 112 |  |  | Solar |  | 05_07_75W5 | 08/16/2017 | 08/16/2017 | 9 | 9 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/21/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/21/2017 | Connected |  | N
National Grid | RANDOLPH | 176865 | 02368 | 820 |  |  | Natural Gas |  | 05_05_335W4 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 05/20/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 |  | 1/27/2016 | N | STD | 99 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | REHOBOTH | 271476 | 02769 | 6.72 |  |  | Solar |  | 05_09_523L4 | 01/02/2020 | 02/24/2020 | 37 | 36 | 1 | 02/25/2020 | 02/25/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 |  | 1/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2020 | Connected |  | N
National Grid | WORCESTER | 555486 | 01605 | 240 |  |  | Solar |  | 05_05_313W1 | 09/15/2023 | 10/13/2023 | 19 | 10 | 9 | 10/16/2023 | 10/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/15/2023 | 6/17/2025 | Y | EXP | 252 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 325552 | 01230 | 7.68 |  |  | Solar |  | 05_07_97W2 | 12/28/2020 | 01/12/2021 | 9 | 9 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 12/28/2020 | 5/25/2022 | Y | EXP | 365 | 04/27/2021 | 05/19/2021 | 22 | 0 | 22 |  |  | 10/4/2021 | Connected |  | N
National Grid | NORTHAMPTON | 571548 | 01060 | 3.77 |  |  | Solar |  | 05_05_7L5 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 12/07/2023 | 1/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2024 | Connected |  | N
National Grid | STOUGHTON | 685935 | 02072 | 7.6 |  |  | Solar |  | 05_01_12J377 | 04/17/2025 | 05/08/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AVON | 650987 | 02322 | 5 |  |  | Solar |  | 05_09_1109W3 | 10/30/2024 | 11/11/2024 | 4 | 0 | 4 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | MILFORD | 652175 | 01757 | 10 |  |  | Solar |  | 05_09_909W4 | 11/11/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 117 | 99 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 177261 | 01069 | 448 |  |  | Solar |  | 05_07_913W69 | 08/18/2016 | 08/18/2016 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/27/2016 | 11/28/2016 | 41 | 38 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/1/2018 | N | STD | 360 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178077 | 01532 | 15.2 |  |  | Solar |  | 05_07_75W5 | 11/03/2017 | 11/03/2017 | 55 | 55 | 0 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 11/27/2020 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177364 | 02368 | 50 |  |  | Solar |  | 05_05_335W4 | 06/24/2016 | 06/24/2016 | 1 | 1 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2016 |  | 7/2/2017 | N | EXP | 360 |  |  | 0 | 0 | 0 | 1/20/2017 | 1/20/2017 | 1/24/2017 | Connected |  | N
National Grid | REHOBOTH | 317367 | 02769 | 187.5 |  |  | Solar |  | 05_09_523L4 | 10/07/2020 | 11/19/2020 | 28 | 24 | 4 | 11/20/2020 | 11/20/2020 | 63 | 43 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 584740 | 01605 | 9.28 |  |  | Solar |  | 05_05_313W1 | 01/23/2024 | 01/30/2024 | 6 | 5 | 1 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 332457 | 01230 | 3.8 |  |  | Solar |  | 05_07_97W2 | 01/07/2021 | 01/15/2021 | 6 | 6 | 0 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 |  | 1/14/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 572861 | 01062 | 15.2 |  |  | Solar |  | 05_05_7L5 | 11/28/2023 | 11/29/2023 | 2 | 1 | 1 | 11/30/2023 | 11/30/2023 | 42 | 17 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 | 11/28/2023 | 2/11/2025 | Y | EXP | 365 | 03/05/2024 | 04/18/2024 | 45 | 0 | 45 |  |  | 6/4/2024 | Connected |  | N
National Grid | STOUGHTON | 670626 | 02072 | 3.8 |  |  | Solar |  | 05_01_12J377 | 02/06/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | AVON | 661710 | 02322 | 11.52 |  |  | Solar |  | 05_09_1109W3 | 12/19/2024 | 01/02/2025 | 9 | 5 | 4 | 01/03/2025 | 01/03/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | MILFORD | 653490 | 01757 | 11.5 |  |  | Solar |  | 05_09_909W4 | 11/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | PALMER | 177260 | 01079 | 180 |  |  | Solar |  | 05_07_913W69 | 08/18/2016 | 08/18/2016 | 6 | 6 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2016 | 08/18/2016 | 8/24/2017 | Y | EXP | 332 | 07/18/2017 | 08/03/2017 | 12 | 0 | 12 | 9/25/2017 | 9/25/2017 | 9/25/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 187201 | 01532 | 490 |  |  | Solar |  | 05_07_75W5 | 06/18/2019 | 06/22/2019 | 3 | 0 | 3 | 06/24/2019 | 06/24/2019 | 30 | 26 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 8/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 324127 | 02368 | 10 |  |  | Solar |  | 05_05_335W4 | 11/30/2020 | 12/02/2020 | 1 | 0 | 1 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2021 | 11/30/2020 |  | Y | EXP | 365 | 05/14/2021 | 05/13/2021 | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | REHOBOTH | 322772 | 02769 | 10 |  |  | Solar |  | 05_09_523L4 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/10/2020 | 3/20/2022 | Y | EXP | 365 | 07/02/2021 | 09/10/2021 | 68 | 3 | 65 |  |  | 10/15/2021 | Connected |  | Y
National Grid | WORCESTER | 607157 | 01605 | 9.135 |  |  | Solar |  | 05_05_313W1 | 04/27/2024 | 06/24/2024 | 39 | 34 | 5 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | EGREMONT | 337718 | 01252 | 4.08 |  |  | Solar |  | 05_07_97W2 | 02/05/2021 | 04/26/2021 | 54 | 53 | 1 | 04/27/2021 | 04/27/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | NORTHAMPTON | 579230 | 01062 | 19.215 |  |  | Solar |  | 05_05_7L5 | 01/12/2024 | 01/18/2024 | 3 | 0 | 3 | 01/19/2024 | 01/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | STOUGHTON | 177106 | 02072 | 120 |  |  | Solar |  | 05_01_12J391 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2016 |  | 6/5/2017 | N | EXP | 340 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/6/2016 | Connected |  | N
National Grid | AVON | 676888 | 02322 | 23 |  |  | Solar |  | 05_09_1109W3 | 03/21/2025 | 03/25/2025 | 2 | 0 | 2 | 03/26/2025 | 03/26/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | MILFORD | 655258 | 01757 | 5.76 |  |  | Solar |  | 05_09_909W4 | 11/20/2024 | 12/20/2024 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | PALMER | 178329 | 01079 | 249 |  |  | Solar |  | 05_07_913W69 | 03/30/2018 | 03/30/2018 | 19 | 0 | 19 | 04/27/2018 | 04/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 187901 | 01532 | 240 |  |  | Solar |  | 05_07_75W5 | 06/13/2018 | 06/13/2018 | 10 | 7 | 3 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  | 2/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | RANDOLPH | 324890 | 02368 | 3.8 |  |  | Solar |  | 05_05_335W4 | 12/04/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | REHOBOTH | 348872 | 02769 | 0 |  |  | Other |  | 05_09_523L4 | 04/23/2021 | 05/09/2021 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 624536 | 01605 | 3.78 |  |  | Solar |  | 05_05_313W1 | 07/12/2024 | 07/26/2024 | 3 | 1 | 2 | 07/29/2024 | 07/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/12/2024 | 9/28/2025 | Y | EXP | 365 | 10/03/2024 | 10/24/2024 | 22 | 0 | 22 |  |  | 11/26/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 399692 | 01230 | 9.8 |  |  | Solar |  | 05_07_97W2 | 12/21/2021 | 12/22/2021 | 1 | 0 | 1 | 12/23/2021 | 12/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2022 | 12/21/2021 | 8/2/2023 | Y | EXP | 365 | 07/12/2022 | 08/01/2022 | 21 | 0 | 21 |  |  | 8/25/2022 | Connected |  | N
National Grid | NORTHAMPTON | 672543 | 01062 | 13.05 |  |  | Solar |  | 05_05_7L5 | 02/18/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | STOUGHTON | 650869 | 02072 | 5.235 |  |  | Solar |  | 05_01_13J350 | 10/30/2024 | 11/18/2024 | 6 | 2 | 4 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | AVON | 677189 | 02322 | 7.6 |  |  | Solar |  | 05_09_1109W3 | 03/11/2025 | 03/19/2025 | 7 | 3 | 4 | 03/20/2025 | 03/20/2025 | 74 | 54 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | MILFORD | 661925 | 01757 | 13.125 |  |  | Solar |  | 05_09_909W4 | 12/20/2024 | 01/06/2025 | 3 | 0 | 3 | 01/07/2025 | 01/07/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | WARE | 178612 | 01082 | 166.5 |  |  | Solar |  | 05_07_913W69 | 12/14/2017 | 12/14/2017 | 31 | 11 | 20 | 01/31/2018 | 01/31/2018 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/19/2018 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 252794 | 01532 | 7.6 |  |  | Solar |  | 05_07_75W5 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 402412 | 02368 | 0 |  |  | Battery Add-On |  | 05_05_335W4 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 11/22/2022 | 196 | 194 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 348867 | 02769 | 0 |  |  | Other |  | 05_09_523L4 | 04/23/2021 | 05/09/2021 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2021 | 06/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 645344 | 01606 | 5.76 |  |  | Solar |  | 05_05_313W1 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/07/2024 | 12/16/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/19/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 412389 | 01230 | 3 |  |  | Solar |  | 05_07_97W2 | 03/24/2022 | 03/28/2022 | 2 | 0 | 2 | 03/29/2022 | 03/29/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 681007 | 01062 | 7.6 |  |  | Solar |  | 05_05_7L5 | 03/27/2025 | 04/08/2025 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/27/2025 | 6/2/2026 | Y | EXP | 365 | 08/08/2025 | 08/14/2025 | 7 | 0 | 7 |  |  | 9/4/2025 | Connected |  | N
National Grid | STOUGHTON | 261693 | 02072 | 4900 |  |  | Natural Gas |  | 05_01_13J358 | 06/26/2020 | 07/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 08/19/2020 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 | 06/26/2020 | 11/1/2022 | Y | STD | 532 | 06/08/2022 | 10/19/2022 | 134 | 0 | 134 |  |  | 10/26/2022 | Connected |  | N
National Grid | AVON | 684139 | 02322 | 50 |  |  | Solar |  | 05_09_1109W3 | 04/09/2025 | 05/28/2025 | 32 | 22 | 10 | 05/29/2025 | 05/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | HOPEDALE | 670769 | 01747 | 23 |  |  | Solar |  | 05_09_909W4 | 02/07/2025 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | PALMER | 199038 | 01069 | 72 |  |  | Solar |  | 05_07_913W69 | 02/01/2019 | 03/15/2019 | 28 | 20 | 8 | 03/18/2019 | 03/18/2019 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 285958 | 01532 | 249 |  |  | Solar |  | 05_07_75W5 | 04/27/2020 | 05/29/2020 | 23 | 16 | 7 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 | 04/27/2020 | 1/29/2026 | Y | EXP | 253 | 12/03/2024 | 12/18/2025 | 381 | 309 | 72 |  |  | 12/26/2025 | Connected |  | N
National Grid | RANDOLPH | 521118 | 02368 | 6 |  |  | Solar |  | 05_05_335W4 | 05/03/2023 | 05/08/2023 | 3 | 0 | 3 | 05/09/2023 | 05/09/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 357047 | 02769 | 10 |  |  | Solar |  | 05_09_523L4 | 05/07/2021 | 05/19/2021 | 7 | 7 | 0 | 05/20/2021 | 05/20/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | WORCESTER | 646139 | 01605 | 5.76 |  |  | Solar |  | 05_05_313W1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/22/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/27/2025 | 42 | 0 | 42 |  |  | 3/15/2025 | Connected |  | N
National Grid | EGREMONT | 416744 | 01252 | 5.51 |  |  | Solar |  | 05_07_97W2 | 04/07/2022 | 04/11/2022 | 2 | 0 | 2 | 04/12/2022 | 04/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/07/2022 | 12/13/2023 | Y | EXP | 365 | 11/04/2022 | 12/12/2022 | 39 | 0 | 39 |  |  | 1/7/2023 | Connected |  | N
National Grid | NORTHAMPTON | 685707 | 01062 | 17.6 |  |  | Solar |  | 05_05_7L5 | 04/22/2025 | 05/02/2025 | 7 | 2 | 5 | 05/05/2025 | 05/05/2025 | 45 | 27 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | STOUGHTON | 684614 | 02072 | 15.2 |  |  | Solar |  | 05_01_13J358 | 04/12/2025 | 04/14/2025 | 1 | 0 | 1 | 04/15/2025 | 04/15/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | AVON | 697991 | 02322 | 22.8 |  |  | Solar |  | 05_09_1109W3 | 06/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 06/11/2025 | 8/12/2026 | Y | EXP | 365 | 08/26/2025 | 09/23/2025 | 29 | 0 | 29 |  |  | 10/29/2025 | Connected |  | N
National Grid | HOPEDALE | 686119 | 01747 | 10 |  |  | Solar |  | 05_09_909W4 | 04/25/2025 | 04/28/2025 | 1 | 0 | 1 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | WARE | 202031 | 01082 | 100 |  |  | Solar |  | 05_07_913W69 | 11/26/2018 | 12/05/2018 | 7 | 2 | 5 | 12/06/2018 | 12/06/2018 | 20 | 7 | 13 | 02/15/2019 | 03/25/2019 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  | 03/25/2019 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 4/19/2019 | 11/26/2018 | 10/30/2020 | Y | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 10/26/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 331898 | 01532 | 15.2 |  |  | Solar |  | 05_07_75W5 | 12/15/2020 | 12/16/2020 | 0 | 0 | 0 | 12/17/2020 | 12/17/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | RANDOLPH | 566642 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W4 | 11/15/2023 | 11/27/2023 | 7 | 0 | 7 | 11/28/2023 | 11/28/2023 | 59 | 40 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 11/15/2023 | 3/8/2025 | Y | EXP | 365 | 07/17/2024 | 08/09/2024 | 24 | 0 | 24 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 358673 | 02769 | 10 |  |  | Solar |  | 05_09_523L4 | 06/15/2021 | 12/03/2021 | 12 | 4 | 8 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 |  | 9/30/2022 | N | EXP | 365 | 09/17/2021 | 09/29/2021 | 13 | 0 | 13 |  |  | 1/19/2022 | Connected |  | Y
National Grid | WORCESTER | 651516 | 01606 | 7.6 |  |  | Solar |  | 05_05_313W1 | 11/13/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 429334 | 01230 | 15.2 |  |  | Solar |  | 05_07_97W2 | 05/09/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | NORTHAMPTON | 722765 | 01062 | 7.6 |  |  | Solar |  | 05_05_7L5 | 09/29/2025 | 10/06/2025 | 10 | 8 | 2 | 12/02/2025 | 12/02/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 503254 | 02072 | 6.09 |  |  | Solar |  | 05_01_14J367 | 03/29/2023 | 03/31/2023 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2023 | 03/29/2023 | 11/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | AVON | 707189 | 02322 | 15.2 |  |  | Solar |  | 05_09_1109W3 | 07/24/2025 | 07/30/2025 | 4 | 0 | 4 | 07/31/2025 | 07/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | MILFORD | 691058 | 01757 | 9.5 |  |  | Solar |  | 05_09_909W4 | 05/12/2025 | 06/16/2025 | 1 | 0 | 1 | 06/18/2025 | 06/18/2025 | 44 | 31 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | PALMER | 207895 | 01069 | 480 |  |  | Solar |  | 05_07_913W69 | 02/07/2019 | 02/25/2019 | 10 | 1 | 9 | 02/26/2019 | 02/26/2019 | 51 | 29 | 22 | 05/10/2019 | 06/25/2019 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  | 06/25/2019 | 32 | 3 | 29 |  |  | 0 | 0 | 0 | 6/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 467612 | 01532 | 0 |  |  | Other |  | 05_07_75W5 | 11/15/2022 | 01/23/2023 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2023 | 02/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 575857 | 02368 | 3.77 |  |  | Solar |  | 05_05_335W4 | 12/20/2023 | 12/27/2023 | 3 | 1 | 2 | 12/28/2023 | 12/28/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 428299 | 02769 | 15.2 |  |  | Solar |  | 05_09_523L4 | 05/04/2022 | 05/12/2022 | 6 | 6 | 0 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 6/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2023 | Connected |  | N
National Grid | WORCESTER | 653530 | 01606 | 10 |  |  | Solar |  | 05_05_313W1 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/18/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 438829 | 01266 | 6 |  |  | Solar |  | 05_07_97W2 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/27/2022 | 6/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | NORTHAMPTON | 724146 | 01062 | 5.76 |  |  | Solar |  | 05_05_7L5 | 10/06/2025 | 10/16/2025 | 6 | 4 | 2 | 10/17/2025 | 10/17/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | STOUGHTON | 589307 | 02072 | 7.6 |  |  | Solar |  | 05_01_14J367 | 03/01/2024 | 03/05/2024 | 2 | 0 | 2 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 03/01/2024 | 3/22/2025 | Y | EXP | 365 | 05/15/2024 | 06/26/2024 | 43 | 0 | 43 |  |  | 6/27/2024 | Connected |  | N
National Grid | AVON | 693485 | 02322 | 240 |  |  | Solar |  | 05_09_139L1 | 05/23/2025 | 07/30/2025 | 45 | 35 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILFORD | 705420 | 01747 | 5.76 |  |  | Solar |  | 05_09_909W4 | 07/16/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 213840 | 01069 | 250 |  |  | Solar |  | 05_07_913W69 | 04/08/2019 | 04/17/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2019 | 05/10/2019 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 624944 | 01532 | 7.6 |  |  | Solar |  | 05_07_75W5 | 07/15/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 600151 | 02368 | 6 |  |  | Solar |  | 05_05_335W4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 | 04/01/2024 | 4/19/2025 | Y | EXP | 365 | 07/23/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | SEEKONK | 489441 | 02771 | 3.8 |  |  | Solar |  | 05_09_523L4 | 03/09/2023 | 03/16/2023 | 5 | 0 | 5 | 03/17/2023 | 03/17/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2023 | Connected |  | N
National Grid | WORCESTER | 655152 | 01606 | 7.6 |  |  | Solar |  | 05_05_313W1 | 11/19/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 447515 | 01252 | 10 |  |  | Solar |  | 05_07_97W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2022 | Connected |  | N
National Grid | NORTHAMPTON | 197724 | 01062 | 1700 |  |  | Solar |  | 05_05_8L1 | 10/25/2018 | 11/14/2018 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 | 12/14/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 | 10/25/2018 | 5/27/2026 | Y | STD | 365 | 02/04/2023 |  | 1063 | 939 | 124 |  |  |  | Construction |  | N
National Grid | STOUGHTON | 647285 | 02072 | 3.8 |  |  | Solar |  | 05_01_14J367 | 10/21/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | AVON | 717006 | 02322 | 5.76 |  |  | Solar |  | 05_09_139L1 | 09/05/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 09/05/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MILFORD | 714408 | 01757 | 7.6 |  |  | Solar |  | 05_09_909W4 | 08/25/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | WARE | 239659 | 01082 | 250 |  |  | Solar |  | 05_07_913W69 | 06/21/2019 | 06/29/2019 | 5 | 0 | 5 | 07/01/2019 | 07/01/2019 | 16 | 3 | 13 | 08/01/2019 | 11/25/2019 | 80 | 42 | 38 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 80 | 42 | 38 |  |  | 0 | 0 | 0 | 1/6/2020 | 06/21/2019 | 1/6/2023 | Y | EXP | 662 | 02/04/2021 | 11/03/2022 | 638 | 544 | 94 |  |  | 12/5/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 634969 | 01532 | 7.6 |  |  | Solar |  | 05_07_75W5 | 08/26/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 08/26/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | RANDOLPH | 621415 | 02368 | 16 |  |  | Solar |  | 05_05_335W4 | 07/02/2024 | 07/12/2024 | 7 | 5 | 2 | 07/15/2024 | 07/15/2024 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 614250 | 02769 | 2.32 |  |  | Solar |  | 05_09_523L4 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/30/2024 | 7/1/2025 | Y | EXP | 365 | 08/01/2024 | 08/28/2024 | 28 | 0 | 28 |  |  | 9/27/2024 | Connected |  | N
National Grid | WORCESTER | 660905 | 01606 | 10 |  |  | Solar |  | 05_05_313W1 | 12/16/2024 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 468022 | 01266 | 6 |  |  | Solar |  | 05_07_97W2 | 12/05/2022 | 12/07/2022 | 2 | 0 | 2 | 12/08/2022 | 12/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 | 12/05/2022 | 4/13/2024 | Y | EXP | 365 | 04/12/2023 | 04/11/2023 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 696703 | 01062 | 5.76 |  |  | Solar |  | 05_05_8L1 | 06/25/2025 | 09/22/2025 | 54 | 51 | 3 | 09/23/2025 | 09/23/2025 | 67 | 66 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOUGHTON | 657562 | 02072 | 5.76 |  |  | Solar |  | 05_01_14J367 | 11/28/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | AVON | 738830 | 02322 | 10 |  |  | Solar |  | 05_09_139L1 | 12/08/2025 | 12/10/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 223132 | 01757 | 133.2 |  |  | Solar |  | 05_12_10C2 | 04/27/2019 | 05/21/2019 | 17 | 15 | 2 | 05/22/2019 | 05/22/2019 | 16 | 5 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 3/31/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 5/20/2021 | Connected |  | N
National Grid | PALMER | 316717 | 01069 | 12 |  |  | Solar |  | 05_07_913W69 | 10/02/2020 | 10/09/2020 | 5 | 4 | 1 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 10/02/2020 | 1/24/2022 | Y | EXP | 365 | 12/13/2020 | 12/30/2020 | 17 | 0 | 17 |  |  | 9/15/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 516245 | 01532 | 75 |  |  | Solar |  | 05_07_75W7 | 04/28/2023 | 01/06/2024 | 172 | 162 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 4/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 630854 | 02368 | 3.8 |  |  | Solar |  | 05_05_335W4 | 08/07/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 660815 | 02771 | 3.8 |  |  | Solar |  | 05_09_523L4 | 12/16/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WORCESTER | 662299 | 01606 | 0 |  |  | Solar |  | 05_05_313W1 | 01/09/2025 | 01/22/2025 | 8 | 4 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | EGREMONT | 467533 | 01252 | 7.6 |  |  | Solar |  | 05_07_97W2 | 11/16/2022 | 11/18/2022 | 2 | 0 | 2 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2022 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | NORTHAMPTON | 176350 | 01062 | 40 |  |  | Solar |  | 05_05_8L1 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 514 | 11/05/2015 | 02/03/2016 | 59 | 0 | 59 | 2/4/2016 | 2/4/2016 | 2/16/2016 | Connected |  | N
National Grid | STOUGHTON | 704048 | 02072 | 7.6 |  |  | Solar |  | 05_01_14J367 | 07/11/2025 | 07/24/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 07/11/2025 | 9/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 175021 | 02322 | 3500 |  |  | Solar |  | 05_09_139L1 | 10/08/2012 | 10/08/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 12/03/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2014 | 10/08/2012 | 6/3/2013 | Y | STD | -231 |  |  | 0 | 0 | 0 | 7/24/2015 | 7/24/2015 | 7/31/2015 | Connected |  | N
National Grid | MILFORD | 176945 | 01757 | 43.2 |  |  | Solar |  | 05_12_10J5 | 12/20/2016 | 12/20/2016 | 9 | 8 | 1 | 01/05/2017 | 01/05/2017 | 107 | 0 | 107 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2017 |  | 12/26/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 322406 | 01069 | 7.6 |  |  | Solar |  | 05_07_913W69 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 6/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 515428 | 01532 | 200 |  |  | Solar |  | 05_07_75W7 | 04/03/2023 | 04/20/2023 | 12 | 3 | 9 | 04/21/2023 | 04/21/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 4/30/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 653665 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W4 | 11/15/2024 | 04/08/2025 | 80 | 75 | 5 | 04/09/2025 | 04/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 667028 | 02769 | 20 |  |  | Solar |  | 05_09_523L4 | 02/03/2025 | 02/05/2025 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/03/2025 | 4/3/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 11/24/2025 | Connected |  | N
National Grid | WORCESTER | 668429 | 01606 | 17.225 |  |  | Solar |  | 05_05_313W1 | 02/04/2025 | 02/26/2025 | 15 | 10 | 5 | 02/27/2025 | 02/27/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | Y
National Grid | MONSON | 490321 | 01057 | 6 |  |  | Solar |  | 05_07_97W2 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/24/2023 | 9/7/2024 | Y | EXP | 365 | 08/17/2023 | 09/01/2023 | 16 | 0 | 16 |  |  | 9/18/2023 | Connected |  | N
National Grid | NORTHAMPTON | 263147 | 01062 | 2000 |  |  | Solar |  | 05_05_8L1 | 06/15/2020 | 07/17/2020 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/20/2020 | 08/11/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 175455 | 02072 | 252 |  |  | Solar |  | 05_01_14J368 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 11/28/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 3/23/2016 | Connected |  | N
National Grid | AVON | 176634 | 02322 | 527 |  |  | Solar |  | 05_09_139L1 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 174223 | 01757 | 500 |  |  |  |  | 05_12_10J6 | 02/09/2012 | 02/09/2012 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 337225 | 01082 | 250 |  |  | Solar |  | 05_07_913W69 | 02/09/2021 | 02/17/2021 | 4 | 0 | 4 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 | 04/06/2021 | 09/21/2021 | 117 | 82 | 35 |  |  | 0 | 0 | 0 |  | 09/21/2021 | 117 | 82 | 35 |  |  | 0 | 0 | 0 | 10/6/2021 | 02/09/2021 | 2/22/2024 | Y | EXP | 245 | 02/17/2022 | 08/03/2023 | 533 | 493 | 40 |  |  | 9/5/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 676560 | 01532 | 11.5 |  |  | Solar |  | 05_07_75W7 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 119 | 96 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 03/07/2025 | 9/30/2026 | Y | EXP | 365 | 11/18/2025 |  | 45 | 0 | 45 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 673496 | 02368 | 3.8 |  |  | Solar |  | 05_05_335W4 | 03/04/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 96 | 24 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | ATTLEBORO | 668004 | 02703 | 9.5 |  |  | Solar |  | 05_09_523L4 | 01/27/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | WORCESTER | 677961 | 01606 | 15.76 |  |  | Solar |  | 05_05_313W1 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | HAMPDEN | 492308 | 01036 | 6 |  |  | Solar |  | 05_07_97W2 | 01/26/2023 | 01/27/2023 | 1 | 0 | 1 | 01/30/2023 | 01/30/2023 | 263 | 25 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 285550 | 01062 | 10 |  |  | Solar |  | 05_05_8L1 | 05/06/2020 | 05/08/2020 | 1 | 0 | 1 | 05/11/2020 | 05/11/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 05/06/2020 | 5/6/2021 | Y | EXP | 365 | 09/30/2020 | 10/22/2020 | 22 | 0 | 22 |  |  | 10/28/2020 | Connected |  | N
National Grid | STOUGHTON | 407000 | 02072 | 15.37 |  |  | Solar |  | 05_01_14J368 | 03/13/2022 | 03/15/2022 | 2 | 0 | 2 | 03/16/2022 | 03/16/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2022 | Connected |  | N
National Grid | AVON | 177651 | 02322 | 2000 |  |  | Solar |  | 05_09_139L1 | 09/28/2017 | 09/28/2017 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 11/14/2017 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2017 | 09/28/2017 | 3/31/2021 | Y | STD | 1050 |  |  | 0 | 0 | 0 | 11/20/2020 | 3/8/2021 | 3/30/2021 | Connected |  | N
National Grid | MILFORD | 174222 | 01757 | 500 |  |  |  |  | 05_12_10J6 | 02/07/2012 | 02/07/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 355909 | 01079 | 480 |  |  | Solar |  | 05_07_913W69 | 06/01/2021 | 06/24/2021 | 17 | 9 | 8 | 06/25/2021 | 06/25/2021 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2021 | 06/01/2021 | 12/8/2024 | Y | EXP | 322 | 02/01/2022 | 02/13/2025 | 1108 | 720 | 388 |  |  | 10/21/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 704582 | 01532 | 480 |  |  | Solar |  | 05_07_75W7 | 10/02/2025 | 10/31/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 |  | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 682810 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W4 | 04/07/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/07/2025 | 8/1/2026 | Y | EXP | 365 | 08/08/2025 | 08/24/2025 | 17 | 0 | 17 |  |  | 11/25/2025 | Connected |  | N
National Grid | ATTLEBORO | 703736 | 02703 | 20 |  |  | Solar |  | 05_09_523L4 | 07/09/2025 | 07/24/2025 | 4 | 0 | 4 | 11/12/2025 | 11/12/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | WORCESTER | 686739 | 01606 | 7.6 |  |  | Solar |  | 05_05_313W1 | 04/23/2025 |  | 84 | 80 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 517602 | 01028 | 3.8 |  |  | Solar |  | 05_07_97W2 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 04/24/2023 | 8/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | EVERETT | 452367 | 02149 | 8.832 |  |  | Solar |  | 05_05_8L1 | 09/02/2022 | 09/07/2022 | 2 | 0 | 2 | 09/08/2022 | 09/08/2022 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 | 09/02/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2023 | Connected |  | Y
National Grid | STOUGHTON | 639399 | 02072 | 7.6 |  |  | Solar |  | 05_01_14J368 | 10/02/2024 | 02/26/2025 | 97 | 96 | 1 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | RANDOLPH | 177854 | 02368 | 250 |  |  | Solar |  | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 176188 | 01747 | 500 |  |  |  |  | 05_12_10J6 | 09/01/2015 | 09/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 09/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 432258 | 01082 | 10 |  |  | Solar |  | 05_07_913W69 | 06/02/2022 | 06/07/2022 | 3 | 0 | 3 | 06/08/2022 | 06/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176521 | 01532 | 112 |  |  | Solar |  | 05_07_75W7 | 10/05/2015 | 10/05/2015 | 2 | 2 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 | 10/05/2015 | 10/12/2016 | Y | EXP | 335 | 03/14/2016 | 04/30/2016 | 33 | 0 | 33 | 5/9/2016 | 5/9/2016 | 5/20/2016 | Connected |  | N
National Grid | RANDOLPH | 690548 | 02368 | 12.16 |  |  | Solar |  | 05_05_335W4 | 05/08/2025 | 05/21/2025 | 1 | 0 | 1 | 06/26/2025 | 06/26/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/29/2026 | N | EXP | 365 | 09/09/2025 | 10/23/2025 | 45 | 0 | 45 |  |  | 1/3/2026 | Connected |  | N
National Grid | ATTLEBORO | 442707 | 02703 | 3000 |  |  | Solar |  | 05_09_527L1 | 09/30/2022 | 10/25/2022 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 | 11/16/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 699455 | 01606 | 16.403 |  |  | Solar |  | 05_05_313W1 | 07/03/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 07/03/2025 | 8/11/2026 | Y | EXP | 365 | 10/03/2025 | 10/02/2025 | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | HAMPDEN | 519279 | 01036 | 9.984 |  |  | Solar |  | 05_07_97W2 | 06/16/2023 | 06/21/2023 | 2 | 1 | 1 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 | 06/16/2023 | 12/6/2024 | Y | EXP | 365 | 10/26/2023 | 12/04/2023 | 40 | 0 | 40 |  |  | 12/29/2023 | Connected |  | N
National Grid | EVERETT | 466729 | 02149 | 100 |  |  | Solar |  | 05_05_8L1 | 10/07/2022 | 11/10/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 12/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 175282 | 02072 | 42.57 |  |  | Solar |  | 05_01_15J392 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/5/2015 | Connected |  | N
National Grid | STOUGHTON | 177853 | 02072 | 250 |  |  | Solar |  | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 683221 | 01757 | 15.2 |  |  | Solar |  | 05_12_11J1 | 04/08/2025 | 04/10/2025 | 2 | 0 | 2 | 04/11/2025 | 04/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2025 | Connected |  | N
National Grid | PALMER | 435270 | 01069 | 0 |  |  | Solar |  | 05_07_913W69 | 06/09/2022 | 07/11/2022 | 21 | 20 | 1 | 07/12/2022 | 07/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 177482 | 01532 | 57.6 |  |  | Solar |  | 05_07_75W7 | 09/21/2016 | 09/21/2016 | 4 | 4 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2016 |  | 9/27/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 | 4/10/2017 | 4/10/2017 | 4/13/2017 | Connected |  | N
National Grid | RANDOLPH | 710894 | 02368 | 12.54 |  |  | Solar |  | 05_05_335W5 | 08/13/2025 | 08/18/2025 | 2 | 0 | 2 | 08/19/2025 | 08/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | ATTLEBORO | 465731 | 02703 | 0 |  |  | Other |  | 05_09_527L1 | 12/22/2022 | 01/10/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2023 | 02/09/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 614470 | 01606 | 240 |  |  | Solar |  | 05_05_313W2 | 06/07/2024 | 07/09/2024 | 20 | 13 | 7 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/5/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LONGMEADOW | 559566 | 01028 | 6 |  |  | Solar |  | 05_07_97W2 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/25/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/09/2024 | 57 | 0 | 57 |  |  | 6/8/2024 | Connected |  | N
National Grid | EVERETT | 480136 | 02149 | 15.2 |  |  | Solar |  | 05_05_8L1 | 11/24/2022 | 12/06/2022 | 8 | 5 | 3 | 12/07/2022 | 12/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 1/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | STOUGHTON | 405854 | 02072 | 0 |  |  | Other |  | 05_01_15J392 | 05/20/2022 | 06/09/2022 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2022 | 06/21/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 177852 | 02072 | 250 |  |  | Solar |  | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 704611 | 01757 | 480 |  |  | Solar |  | 05_12_11J13 | 10/17/2025 | 10/31/2025 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 |  | 42 | 28 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WARE | 556059 | 01082 | 0 |  |  | Solar |  | 05_07_913W69 | 09/15/2023 | 09/19/2023 | 2 | 0 | 2 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178042 | 01532 | 960 |  |  | Solar |  | 05_07_75W7 | 05/01/2017 | 05/01/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 | 07/12/2017 | 07/27/2017 | 11 | 0 | 11 | 05/22/2017 | 06/16/2017 | 18 | 4 | 14 |  | 07/27/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/27/2017 | 05/01/2017 | 7/31/2020 | Y | STD | 761 | 08/20/2019 | 06/03/2020 | 286 | 0 | 286 | 6/4/2020 | 7/27/2020 | 8/4/2020 | Connected |  | N
National Grid | RANDOLPH | 738968 | 02368 | 15.2 |  |  | Solar |  | 05_05_335W5 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 458825 | 02703 | 4980 |  |  | Solar |  | 05_09_527L1 | 10/28/2022 | 11/29/2022 | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/30/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 621987 | 01606 | 300 |  |  | Solar |  | 05_05_313W2 | 05/30/2025 | 10/15/2025 | 94 | 85 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 11/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAMPDEN | 550162 | 01036 | 10 |  |  | Solar |  | 05_07_97W2 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 08/29/2023 | 11/23/2024 | Y | EXP | 365 | 12/07/2023 | 02/17/2024 | 73 | 3 | 70 |  |  | 3/18/2024 | Connected |  | N
National Grid | EVERETT | 492352 | 02149 | 4999 |  |  | Other |  | 05_05_8L1 | 02/22/2023 | 03/08/2023 | 11 | 2 | 9 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 664954 | 02072 | 0 |  |  | Battery Add-On |  | 05_01_15J392 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | STOUGHTON | 177851 | 02072 | 250 |  |  | Solar |  | 05_09_139L1 | 04/10/2017 | 04/10/2017 | 200 | 198 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/16/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 177474 | 01747 | 7.5 |  |  | Solar |  | 05_12_11J13 | 07/06/2016 | 07/06/2016 | 26 | 26 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2016 | 07/06/2016 | 7/12/2017 | Y | EXP | 328 |  |  | 0 | 0 | 0 | 1/27/2017 | 1/27/2017 | 1/27/2017 | Connected |  | N
National Grid | PALMER | 593534 | 01069 | 8.19 |  |  | Solar |  | 05_07_913W69 | 03/18/2024 | 04/24/2024 | 26 | 23 | 3 | 04/25/2024 | 04/25/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 194829 | 01532 | 600 |  |  | Solar |  | 05_07_75W7 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/06/2018 | 59 | 7 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176052 | 02368 | 4.5 |  |  | Solar |  | 05_05_335W5 | 01/29/2015 | 01/29/2015 | 4 | 4 | 0 | 02/05/2015 | 02/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 2/24/2015 | 2/24/2015 | 9/25/2015 | Connected |  | N
National Grid | ATTLEBORO | 645502 | 02703 | 0 |  |  | Other |  | 05_09_527L1 | 03/07/2025 | 05/01/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2025 | 06/02/2025 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 664586 | 01606 | 960 |  |  | Solar |  | 05_05_313W2 | 05/19/2025 | 07/10/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2025 | 08/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MONSON | 555021 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 09/15/2023 | 09/18/2023 | 1 | 0 | 1 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 571237 | 02149 | 5 |  |  | Solar |  | 05_05_8L1 | 12/05/2023 | 02/12/2024 | 47 | 37 | 10 | 02/13/2024 | 02/13/2024 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 12/05/2023 | 3/20/2025 | Y | EXP | 365 | 08/03/2024 | 08/02/2024 | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | STOUGHTON | 441629 | 02072 | 16.82 |  |  | Solar |  | 05_01_16J1 | 07/04/2022 |  | 50 | 47 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177878 | 02072 | 250 |  |  | Solar |  | 05_09_139L1 | 10/17/2017 | 10/17/2017 | 15 | 0 | 15 | 11/09/2017 | 11/09/2017 | 19 | 0 | 19 | 02/22/2018 | 03/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 03/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/27/2018 | 10/17/2017 | 9/11/2020 | Y | EXP | 492 | 07/26/2019 | 08/03/2020 | 372 | 0 | 372 |  |  | 9/10/2020 | Connected |  | N
National Grid | HOPEDALE | 178131 | 01747 | 7.6 |  |  | Solar |  | 05_12_11J13 | 07/12/2017 | 07/12/2017 | 3 | 0 | 3 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | GRANBY | 598040 | 01033 | 7.6 |  |  | Solar |  | 05_07_913W69 | 03/22/2024 | 03/26/2024 | 2 | 0 | 2 | 03/27/2024 | 03/27/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 362507 | 01532 | 900 |  |  | Solar |  | 05_07_75W7 | 09/23/2021 | 01/31/2022 | 88 | 78 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/25/2022 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176094 | 02368 | 84 |  |  | Solar |  | 05_05_335W5 | 04/02/2015 | 04/02/2015 | 2 | 0 | 2 | 04/13/2015 | 04/13/2015 | 165 | 0 | 165 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 8/7/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 681440 | 02703 | 6.67 |  |  | Solar |  | 05_09_527L1 | 08/28/2025 | 09/17/2025 | 9 | 7 | 2 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 670266 | 01605 | 960 |  |  | Solar |  | 05_05_313W2 | 10/01/2025 | 11/23/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 12/23/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MONSON | 560567 | 01057 | 6.144 |  |  | Solar |  | 05_07_97W2 | 10/06/2023 | 10/12/2023 | 10 | 6 | 4 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2023 | 10/06/2023 | 12/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | MEDFORD | 643534 | 02155 | 7.6 |  |  | Solar |  | 05_05_8L1 | 09/27/2024 | 11/19/2024 | 6 | 3 | 3 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | STOUGHTON | 457672 | 02072 | 16.82 |  |  | Solar |  | 05_01_16J1 | 09/09/2022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 177979 | 02072 | 7.6 |  |  | Solar |  | 05_09_139L1 | 06/28/2017 | 06/28/2017 | 5 | 5 | 0 | 07/06/2017 | 07/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/3/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | MILFORD | 195807 | 01757 | 496 |  |  | Solar |  | 05_12_11J13 | 09/13/2018 | 09/21/2018 | 6 | 4 | 2 | 09/24/2018 | 09/24/2018 | 5 | 0 | 5 | 12/03/2018 | 01/17/2019 | 32 | 5 | 27 |  |  | 0 | 0 | 0 |  | 01/17/2019 | 32 | 5 | 27 |  |  | 0 | 0 | 0 | 3/28/2019 | 09/13/2018 | 10/16/2020 | Y | EXP | 551 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 648653 | 01033 | 10 |  |  | Solar |  | 05_07_913W69 | 10/21/2024 | 11/15/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 367269 | 01532 | 7.6 |  |  | Solar |  | 05_07_75W7 | 07/15/2021 | 07/30/2021 | 12 | 11 | 1 | 08/02/2021 | 08/02/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 10/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2022 | Connected |  | N
National Grid | RANDOLPH | 176171 | 02368 | 6 |  |  | Solar |  | 05_05_335W5 | 04/23/2015 | 04/23/2015 | 3 | 2 | 1 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2015 |  | 8/31/2015 | N | EXP | 124 |  |  | 0 | 0 | 0 | 6/17/2015 | 6/17/2015 | 10/26/2015 | Connected |  | N
National Grid | ATTLEBORO | 689634 | 02703 | 499 |  |  | Solar |  | 05_09_527L1 | 06/12/2025 | 07/30/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 711406 | 01605 | 5.76 |  |  | Solar |  | 05_05_313W2 | 08/13/2025 | 08/26/2025 | 11 | 7 | 4 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 | 08/13/2025 | 11/6/2026 | Y | EXP | 365 | 12/16/2025 | 12/15/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MONSON | 562983 | 01057 | 9.765 |  |  | Solar |  | 05_07_97W2 | 12/04/2023 | 12/27/2023 | 16 | 13 | 3 | 12/28/2023 | 12/28/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 12/04/2023 | 2/20/2025 | Y | EXP | 365 | 05/11/2024 | 05/14/2024 | 4 | 0 | 4 |  |  | 5/30/2024 | Connected |  | N
National Grid | MEDFORD | 645422 | 02155 | 2.03 |  |  | Solar |  | 05_05_8L1 | 10/18/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/18/2024 | 1/2/2026 | Y | EXP | 365 | 03/06/2025 | 07/18/2025 | 135 | 0 | 135 |  |  | 8/1/2025 | Connected |  | N
National Grid | STOUGHTON | 674114 | 02072 | 0 |  |  | Battery Add-On |  | 05_01_16J1 | 02/25/2025 | 03/26/2025 | 12 | 8 | 4 | 03/27/2025 | 03/27/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | STOUGHTON | 178122 | 02072 | 3480 |  |  | Solar |  | 05_09_139L1 | 05/12/2017 | 05/12/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2017 | 08/03/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2018 |  | 7/5/2019 | N | STD | 449 | 04/13/2019 | 10/15/2019 | 185 | 0 | 185 |  |  | 11/27/2019 | Connected |  | N
National Grid | MILFORD | 294723 | 01757 | 8 |  |  | Solar |  | 05_12_11J13 | 06/03/2020 | 06/29/2020 | 17 | 14 | 3 | 06/30/2020 | 06/30/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2020 | 06/03/2020 | 9/9/2021 | Y | EXP | 365 | 12/11/2020 | 02/05/2021 | 56 | 0 | 56 |  |  | 2/19/2021 | Connected |  | N
National Grid | GRANBY | 665212 | 01033 | 10 |  |  | Solar |  | 05_07_913W69 | 01/13/2025 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 430213 | 01532 | 3.8 |  |  | Solar |  | 05_07_75W7 | 05/25/2022 | 05/26/2022 | 1 | 0 | 1 | 05/27/2022 | 05/27/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 | 05/25/2022 | 6/7/2024 | Y | EXP | 365 | 12/01/2022 | 06/08/2023 | 190 | 0 | 190 |  |  | 6/14/2023 | Connected |  | N
National Grid | RANDOLPH | 176259 | 02368 | 18.06 |  |  | Solar |  | 05_05_335W5 | 09/04/2015 | 09/04/2015 | 4 | 4 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 9/12/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | ATTLEBORO | 688733 | 02703 | 22.8 |  |  | Solar |  | 05_09_527L1 | 05/07/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 737222 | 01605 | 0 |  |  | Battery Add-On |  | 05_05_313W2 | 12/01/2025 | 12/02/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MONSON | 570882 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 12/01/2023 | 1/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2024 | Connected |  | Y
National Grid | MEDFORD | 709801 | 02155 | 7.6 |  |  | Solar |  | 05_05_8L1 | 08/05/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 52 | 24 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 175762 | 02072 | 17 |  |  | Solar |  | 05_01_16J2 | 06/05/2014 | 06/05/2014 | 6 | 0 | 6 | 06/16/2014 | 06/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2014 |  | 8/29/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 7/11/2014 | 7/11/2014 | 10/9/2014 | Connected |  | N
National Grid | STOUGHTON | 178328 | 02072 | 8980 |  |  | Solar |  | 05_09_139L1 | 03/30/2018 | 03/30/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/19/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 682764 | 01757 | 7.6 |  |  | Solar |  | 05_12_11J13 | 04/03/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | GRANBY | 542075 | 01033 | 2000 |  |  | Solar |  | 05_07_915W35 | 09/29/2023 | 11/16/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 01/05/2024 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NORTHBOROUGH | 480025 | 01532 | 86 |  |  | Solar |  | 05_07_75W7 | 11/30/2022 | 12/29/2022 | 20 | 10 | 10 |  |  | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176534 | 02368 | 6 |  |  | Solar |  | 05_05_335W5 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 | 02/09/2016 | 2/15/2017 | Y | EXP | 344 | 05/11/2016 | 05/13/2016 | 2 | 0 | 2 | 5/1/2017 | 5/1/2017 | 5/5/2017 | Connected |  | N
National Grid | ATTLEBORO | 692853 | 02703 | 4980 |  |  | Solar |  | 05_09_527L1 | 06/06/2025 | 08/26/2025 | 53 | 43 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 174471 | 01602 | 285 |  |  | Solar |  | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | MONSON | 576442 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 12/08/2023 | 12/29/2023 | 15 | 12 | 3 | 01/02/2024 | 01/02/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2024 | Connected |  | N
National Grid | MEDFORD | 729560 | 02155 | 17.6 |  |  | Solar |  | 05_05_8L2 | 10/28/2025 | 11/04/2025 | 5 | 1 | 4 | 11/05/2025 | 11/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOUGHTON | 593407 | 02072 | 10 |  |  | Solar |  | 05_01_16J2 | 02/29/2024 | 03/12/2024 | 8 | 5 | 3 | 03/13/2024 | 03/13/2024 | 10 | 7 | 3 | 04/01/2024 | 04/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 04/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 4/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 178461 | 02072 | 3875 |  |  | Solar |  | 05_09_139L1 | 01/19/2018 | 01/19/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 04/20/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 | 01/19/2018 | 11/30/2022 | Y | STD | 252 | 01/14/2022 | 11/21/2022 | 312 | 0 | 312 |  |  | 11/30/2022 | Connected |  | N
National Grid | MILFORD | 553658 | 01757 | 10 |  |  | Solar |  | 05_12_11J2 | 09/11/2023 | 09/12/2023 | 1 | 0 | 1 | 09/13/2023 | 09/13/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 09/11/2023 | 10/26/2024 | Y | EXP | 365 | 02/09/2024 | 05/18/2024 | 100 | 0 | 100 |  |  | 5/21/2024 | Connected |  | N
National Grid | GRANBY | 668774 | 01033 | 0 |  |  | Solar |  | 05_07_915W35 | 01/29/2025 | 02/04/2025 | 5 | 2 | 3 | 02/05/2025 | 02/05/2025 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 500180 | 01532 | 120 |  |  | Solar |  | 05_07_75W7 | 02/13/2023 | 02/22/2023 | 6 | 0 | 6 | 02/23/2023 | 02/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 4/15/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | Y
National Grid | RANDOLPH | 177176 | 02368 | 20.2 |  |  | Solar |  | 05_05_335W5 | 06/01/2016 | 06/01/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2016 | 06/01/2016 | 6/6/2017 | Y | EXP | 335 | 10/11/2016 | 10/11/2016 | 0 | 0 | 0 | 10/21/2016 | 10/21/2016 | 10/25/2016 | Connected |  | N
National Grid | ATTLEBORO | 692847 | 02703 | 4980 |  |  | Solar |  | 05_09_527L1 | 06/12/2025 | 08/19/2025 | 45 | 37 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2025 | 09/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 174470 | 01602 | 95 |  |  | Solar |  | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/20/2012 | Connected |  | N
National Grid | MONSON | 580555 | 01057 | 4.64 |  |  | Solar |  | 05_07_97W2 | 01/12/2024 | 01/18/2024 | 3 | 0 | 3 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174346 | 02155 | 26 |  |  | Solar |  | 05_05_8L2 | 07/28/2010 | 07/28/2010 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 672266 | 02072 | 7.6 |  |  | Solar |  | 05_01_16J2 | 02/19/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/19/2025 | 4/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | STOUGHTON | 178597 | 02072 | 2500 |  |  | Solar |  | 05_09_139L1 | 04/06/2018 | 04/06/2018 | 9 | 8 | 1 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  | 9/30/2020 | N | STD | 595 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 646492 | 01757 | 7.6 |  |  | Solar |  | 05_12_11J2 | 10/11/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/11/2024 | 1/3/2026 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/17/2025 | Connected |  | N
National Grid | GRANBY | 722967 | 01033 | 20 |  |  | Solar |  | 05_07_915W35 | 09/30/2025 | 10/16/2025 | 10 | 5 | 5 | 10/17/2025 | 10/17/2025 | 51 | 24 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHBOROUGH | 516478 | 01532 | 150 |  |  | Solar |  | 05_07_75W7 | 04/07/2023 | 04/21/2023 | 9 | 0 | 9 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177435 | 02368 | 366.3 |  |  | Solar |  | 05_05_335W5 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2016 | 07/15/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 06/29/2016 | 7/5/2017 | Y | STD | 232 | 03/08/2017 | 06/30/2017 | 80 | 0 | 80 | 8/16/2017 | 8/16/2017 | 8/16/2017 | Connected |  | N
National Grid | ATTLEBORO | 716877 | 02703 | 11.02 |  |  | Solar |  | 05_09_527L1 | 09/04/2025 | 09/22/2025 | 9 | 5 | 4 | 10/09/2025 | 10/09/2025 | 37 | 18 | 19 | 12/10/2025 | 01/05/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 01/05/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 1/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 174469 | 01602 | 120 |  |  | Solar |  | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | HAMPDEN | 581836 | 01036 | 5.51 |  |  | Solar |  | 05_07_97W2 | 01/19/2024 | 01/22/2024 | 1 | 0 | 1 | 01/23/2024 | 01/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174706 | 02155 | 1500 |  |  | Solar |  | 05_05_8L2 | 06/10/2013 | 06/10/2013 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2013 | 09/03/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 174464 | 02072 | 170 |  |  | Natural Gas |  | 05_01_16J3 | 08/09/2011 | 08/09/2011 | 40 | 0 | 40 | 10/10/2011 | 10/10/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 6/29/2012 | 6/29/2012 | 1/29/2013 | Connected |  | N
National Grid | STOUGHTON | 178664 | 02072 | 3818 |  |  | Solar |  | 05_09_139L1 | 03/16/2018 | 04/16/2018 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/11/2018 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2018 | 03/16/2018 | 12/31/2024 | Y | STD | 675 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | MILFORD | 350691 | 01757 | 57.6 |  |  | Solar |  | 05_12_11J4 | 04/05/2021 | 12/20/2021 | 6 | 0 | 6 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 | 04/05/2021 | 1/2/2023 | Y | EXP | 365 | 08/06/2021 | 09/20/2021 | 24 | 3 | 21 |  |  | 1/27/2022 | Connected |  | N
National Grid | GRANBY | 156595 | 01033 | 15.2 |  |  | Solar |  | 05_07_915W35 | 08/23/2017 | 08/23/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 661275 | 01532 | 10 |  |  | Solar |  | 05_07_75W7 | 12/17/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 27 | 2 | 25 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 12/17/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | RANDOLPH | 177723 | 02368 | 33.3 |  |  | Solar |  | 05_05_335W5 | 10/03/2017 | 10/03/2017 | 3 | 0 | 3 | 10/04/2017 | 10/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 10/9/2018 | N | EXP | 307 |  |  | 0 | 0 | 0 | 2/26/2018 | 2/26/2018 | 3/6/2018 | Connected |  | N
National Grid | ATTLEBORO | 718085 | 02703 | 16 |  |  | Solar |  | 05_09_527L1 | 10/21/2025 | 10/24/2025 | 3 | 0 | 3 | 10/27/2025 | 10/27/2025 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 176385 | 01609 | 480 |  |  | Solar |  | 05_05_313W2 | 12/01/2015 | 12/01/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/18/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 8/1/2017 | N | STD | 326 |  |  | 0 | 0 | 0 | 6/21/2017 | 6/21/2017 | 7/6/2017 | Connected |  | N
National Grid | HAMPDEN | 586650 | 01036 | 8.7 |  |  | Solar |  | 05_07_97W2 | 02/07/2024 | 02/09/2024 | 2 | 0 | 2 | 02/12/2024 | 02/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/1/2025 | Y | EXP | 365 | 03/30/2024 | 04/17/2024 | 19 | 0 | 19 |  |  | 5/14/2024 | Connected |  | N
National Grid | MEDFORD | 175369 | 02155 | 648 |  |  | Solar |  | 05_05_8L2 | 02/10/2014 | 02/10/2014 | 5 | 0 | 5 | 02/19/2014 | 02/19/2014 | 0 | 0 | 0 | 04/09/2014 | 05/27/2014 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  | 05/27/2014 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 5/28/2014 | 02/10/2014 | 10/14/2014 | Y | EXP | 139 | 10/28/2014 | 11/08/2014 | 9 | 0 | 9 | 12/23/2014 | 12/23/2014 | 12/29/2014 | Connected |  | N
National Grid | NORWELL | 648172 | 02061 | 5.76 |  |  | Solar |  | 05_01_18J394 | 10/30/2024 | 03/06/2025 | 77 | 73 | 4 | 03/07/2025 | 03/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 184311 | 02368 | 7.6 |  |  | Solar |  | 05_09_139L1 | 07/15/2018 | 08/14/2018 | 21 | 0 | 21 | 08/15/2018 | 08/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 664189 | 01757 | 7.6 |  |  | Solar |  | 05_12_11J4 | 01/07/2025 | 01/27/2025 | 11 | 7 | 4 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 175929 | 01033 | 20 |  |  | Solar |  | 05_07_915W35 | 08/05/2015 | 08/05/2015 | 3 | 3 | 0 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2015 |  | 8/11/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 10/20/2015 | 10/20/2015 | 11/4/2015 | Connected |  | N
National Grid | NORTHBOROUGH | 340182 | 01532 | 100 |  |  | Solar |  | 05_07_797W1 | 02/04/2021 | 02/17/2021 | 7 | 0 | 7 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 8/12/2026 | N | EXP | 586 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 178221 | 02368 | 15.2 |  |  | Solar |  | 05_05_335W5 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 |  | 4/21/2019 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | NORTON | 729569 | 02766 | 12.76 |  |  | Solar |  | 05_09_527L1 | 10/29/2025 | 12/11/2025 | 28 | 24 | 4 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 177359 | 01609 | 10.5 |  |  | Solar |  | 05_05_313W2 | 06/21/2016 | 06/21/2016 | 3 | 3 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 344 | 11/01/2016 | 12/07/2016 | 24 | 0 | 24 | 1/17/2017 | 1/17/2017 | 1/23/2017 | Connected |  | N
National Grid | HAMPDEN | 586576 | 01036 | 7.25 |  |  | Solar |  | 05_07_97W2 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  | 10/10/2024 | Connected |  | N
National Grid | MALDEN | 175518 | 02148 | 495 |  |  | Solar |  | 05_05_8L2 | 04/01/2014 | 04/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2014 | 07/11/2014 | 61 | 32 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2016 | 04/01/2014 | 12/29/2017 | Y | STD | 652 | 03/28/2017 | 12/18/2017 | 177 | 0 | 177 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | NORWELL | 671686 | 02061 | 3.8 |  |  | Solar |  | 05_01_18J394 | 02/12/2025 | 07/28/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 199336 | 02368 | 7.6 |  |  | Solar |  | 05_09_139L1 | 11/07/2018 | 03/18/2019 | 88 | 84 | 4 | 03/19/2019 | 03/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 |  | 11/8/2019 | N | EXP | 228 |  |  | 0 | 0 | 0 |  |  | 10/11/2019 | Connected |  | N
National Grid | MILFORD | 438522 | 01757 | 50 |  |  | Solar |  | 05_12_12J3 | 07/22/2022 | 09/13/2022 | 36 | 26 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 6/9/2025 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | GRANBY | 177196 | 01033 | 46 |  |  | Solar |  | 05_07_915W35 | 11/01/2016 | 11/01/2016 | 7 | 7 | 0 | 11/10/2016 | 11/10/2016 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 11/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 729872 | 01532 | 7.6 |  |  | Solar |  | 05_07_797W1 | 10/29/2025 | 12/01/2025 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 189831 | 02368 | 10 |  |  | Solar |  | 05_05_335W5 | 07/05/2018 | 07/05/2018 | 7 | 0 | 7 | 08/21/2018 | 08/21/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 | 07/05/2018 | 8/21/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2019 | Connected |  | N
National Grid | NORTON | 732333 | 02766 | 20 |  |  | Solar |  | 05_09_527L1 | 11/12/2025 | 11/14/2025 | 2 | 0 | 2 | 11/17/2025 | 11/17/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 178636 | 01609 | 10 |  |  | Solar |  | 05_05_313W2 | 04/09/2018 | 04/09/2018 | 8 | 0 | 8 | 04/20/2018 | 04/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2018 |  | 4/15/2019 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | HAMPDEN | 587494 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 | 03/22/2024 | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 5/22/2025 | N | EXP | 365 | 06/13/2024 | 10/09/2024 | 119 | 0 | 119 |  |  | 11/7/2024 | Connected |  | N
National Grid | MALDEN | 175517 | 02148 | 495 |  |  | Solar |  | 05_05_8L2 | 04/01/2014 | 04/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2014 | 07/11/2014 | 61 | 32 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2016 | 04/01/2014 | 12/29/2017 | Y | STD | 652 | 03/28/2017 | 12/18/2017 | 177 | 0 | 177 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | NORWELL | 174124 | 02061 | 1000 |  |  |  |  | 05_01_18J394 | 04/05/2012 | 04/05/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 201377 | 02368 | 7.6 |  |  | Solar |  | 05_09_139L1 | 11/16/2018 | 12/19/2018 | 21 | 21 | 0 | 12/20/2018 | 12/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 178448 | 01757 | 33.3 |  |  | Solar |  | 05_12_12J4 | 11/29/2017 | 11/29/2017 | 4 | 4 | 0 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 11/29/2017 | 12/5/2018 | Y | EXP | 331 | 03/16/2018 | 03/16/2018 | 4 | 4 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | GRANBY | 177613 | 01033 | 15.2 |  |  | Solar |  | 05_07_915W35 | 09/22/2017 | 09/22/2017 | 24 | 24 | 0 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 9/27/2018 | N | EXP | 330 |  |  | 0 | 0 | 0 | 2/28/2018 | 2/28/2018 | 3/6/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 174862 | 01532 | 1000 |  |  | Solar |  | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 |  | 12/31/2012 | N | STD | -178 |  |  | 0 | 0 | 0 |  |  | 8/11/2015 | Withdrawn |  | N
National Grid | RANDOLPH | 196600 | 02368 | 106.6 |  |  | Solar |  | 05_05_335W5 | 09/21/2018 | 11/02/2018 | 26 | 9 | 17 | 11/05/2018 | 11/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 |  | 11/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2019 | Connected |  | N
National Grid | NORTON | 737659 | 02766 | 5.76 |  |  | Solar |  | 05_09_527L1 | 12/02/2025 | 12/03/2025 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 188768 | 01609 | 120 |  |  | Solar |  | 05_05_313W2 | 07/04/2018 | 07/04/2018 | 8 | 0 | 8 | 07/18/2018 | 07/18/2018 | 276 | 26 | 250 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 590155 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 02/23/2024 | 04/11/2024 | 34 | 25 | 9 | 04/12/2024 | 04/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 | 02/23/2024 | 5/3/2025 | Y | EXP | 365 | 10/05/2024 | 11/22/2024 | 49 | 0 | 49 |  |  | 12/3/2024 | Connected |  | N
National Grid | MEDFORD | 175536 | 02155 | 1500 |  |  | Solar |  | 05_05_8L2 | 10/02/2014 | 10/02/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2014 | 11/06/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 232530 | 02061 | 7.6 |  |  | Solar |  | 05_01_18J394 | 09/03/2019 | 09/24/2019 | 14 | 10 | 4 | 09/25/2019 | 09/25/2019 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 09/03/2019 | 10/20/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2020 | Connected |  | N
National Grid | STOUGHTON | 284615 | 02072 | 10 |  |  | Solar |  | 05_09_139L1 | 03/20/2020 | 03/31/2020 | 7 | 7 | 0 | 04/01/2020 | 04/01/2020 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 |  | 3/31/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2020 | Connected |  | N
National Grid | MILFORD | 262490 | 01757 | 0 |  |  | Solar |  | 05_12_12J5 | 10/28/2019 | 10/29/2019 | 0 | 0 | 0 | 10/30/2019 | 10/30/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | GRANBY | 203337 | 01033 | 0 |  |  | Solar |  | 05_07_915W35 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2019 | Connected |  | N
National Grid | MARLBOROUGH | 174861 | 01752 | 3000 |  |  | Solar |  | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 | 08/03/2012 | 6/1/2014 | Y | STD | 339 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 8/11/2015 | Connected |  | N
National Grid | RANDOLPH | 261005 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W5 | 10/23/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2020 | Connected |  | N
National Grid | NORTON | 741731 | 02766 | 33.853 |  |  | Solar |  | 05_09_527L1 | 12/22/2025 | 12/29/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 205688 | 01604 | 250 |  |  | Solar |  | 05_05_313W2 | 01/10/2019 | 01/16/2019 | 2 | 0 | 2 | 01/17/2019 | 01/17/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 589671 | 01036 | 9.57 |  |  | Solar |  | 05_07_97W2 | 02/27/2024 | 02/28/2024 | 1 | 0 | 1 | 02/29/2024 | 02/29/2024 | 94 | 25 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 177787 | 02148 | 3.8 |  |  | Solar |  | 05_05_8L2 | 06/01/2017 | 06/01/2017 | 3 | 3 | 0 | 06/07/2017 | 06/07/2017 | 202 | 0 | 202 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 |  | 6/7/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 265291 | 02066 | 7.6 |  |  | Solar |  | 05_01_18J394 | 12/12/2019 | 01/02/2020 | 12 | 3 | 9 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/12/2019 | 4/1/2021 | Y | EXP | 365 | 01/20/2021 | 01/22/2021 | 2 | 0 | 2 |  |  | 2/23/2021 | Connected |  | Y
National Grid | BRIDGEWATER | 333791 | 02324 | 15.2 |  |  | Solar |  | 05_09_139L1 | 12/23/2020 | 12/29/2020 | 3 | 2 | 1 | 12/30/2020 | 12/30/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/23/2020 | 6/8/2022 | Y | EXP | 365 | 04/14/2021 | 05/12/2021 | 28 | 0 | 28 |  |  | 12/14/2021 | Connected |  | N
National Grid | MILFORD | 586184 | 01757 | 25 |  |  | Solar |  | 05_12_12J5 | 01/30/2024 | 02/07/2024 | 7 | 5 | 2 | 02/08/2024 | 02/08/2024 | 10 | 0 | 10 | 02/27/2024 | 04/03/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 04/03/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | GRANBY | 438286 | 01033 | 15.2 |  |  | Solar |  | 05_07_915W35 | 06/23/2022 | 07/26/2022 | 22 | 19 | 3 | 07/27/2022 | 07/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2022 |  | 11/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | Y
National Grid | WESTBOROUGH | 175221 | 01581 | 19 |  |  | Solar |  | 05_07_797W1 | 11/03/2014 | 11/03/2014 | 7 | 4 | 3 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 5/10/2016 | Connected |  | N
National Grid | RANDOLPH | 287738 | 02368 | 8 |  |  | Solar |  | 05_05_335W5 | 04/14/2020 | 04/14/2020 | 0 | 0 | 0 | 04/15/2020 | 04/15/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2020 |  | 4/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2020 | Connected |  | N
National Grid | NORTON | 173510 | 02766 | 3.8 |  |  | Solar |  | 05_09_527L1 | 04/12/2018 | 04/12/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2019 | Connected |  | N
National Grid | WORCESTER | 306227 | 01604 | 11.4 |  |  | Solar |  | 05_05_313W2 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 8/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N
National Grid | HAMPDEN | 591319 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 03/06/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 185888 | 01915 | 9.6 |  |  | Solar |  | 05_05_8L2 | 06/08/2018 | 06/08/2018 | 25 | 14 | 11 | 07/18/2018 | 07/18/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 602751 | 02066 | 5 |  |  | Solar |  | 05_01_18J394 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 62 | 50 | 12 | 08/23/2024 | 09/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 9/30/2025 | N | EXP | 365 | 10/24/2024 | 11/12/2024 | 20 | 0 | 20 |  |  | 1/22/2025 | Connected |  | N
National Grid | BRIDGEWATER | 338188 | 02324 | 7.6 |  |  | Solar |  | 05_09_139L1 | 01/22/2021 | 01/27/2021 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/22/2021 | 9/14/2022 | Y | EXP | 365 | 09/10/2021 | 10/12/2021 | 22 | 0 | 22 |  |  | 12/15/2021 | Connected |  | Y
National Grid | MILFORD | 606036 | 01757 | 5.7 |  |  | Solar |  | 05_12_12J5 | 04/24/2024 | 05/07/2024 | 6 | 5 | 1 | 05/08/2024 | 05/08/2024 | 81 | 75 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 661282 | 01033 | 10 |  |  | Solar |  | 05_07_915W35 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/17/2024 | 2/26/2026 | Y | EXP | 365 | 07/16/2025 | 10/29/2025 | 106 | 0 | 106 |  |  | 11/13/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 176671 | 01532 | 499 |  |  | Solar |  | 05_07_797W1 | 10/22/2015 | 10/22/2015 | 2 | 2 | 0 | 10/27/2015 | 10/27/2015 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 319815 | 02368 | 9.8 |  |  | Solar |  | 05_05_335W5 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 | 1/7/2022 | Y | EXP | 365 | 03/23/2021 | 09/24/2021 | 184 | 3 | 181 |  |  | 1/3/2022 | Connected |  | Y
National Grid | NORTON | 174163 | 02766 | 11.39 |  |  | Solar |  | 05_09_527L1 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2012 |  | 6/22/2012 | N | EXP | -52 |  |  | 0 | 0 | 0 | 8/13/2012 | 8/13/2012 | 1/14/2013 | Connected |  | N
National Grid | WORCESTER | 318450 | 01604 | 15.2 |  |  | Solar |  | 05_05_313W2 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | MONSON | 595756 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 03/14/2024 | 03/15/2024 | 1 | 0 | 1 | 03/18/2024 | 03/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/14/2024 | 3/25/2025 | Y | EXP | 365 | 10/03/2024 | 11/01/2024 | 30 | 0 | 30 |  |  | 11/9/2024 | Connected |  | N
National Grid | BEVERLY | 204908 | 01915 | 16.4 |  |  | Solar |  | 05_05_8L2 | 12/28/2018 | 02/13/2019 | 31 | 28 | 3 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2019 | Connected |  | N
National Grid | NORWELL | 675673 | 02061 | 7.6 |  |  | Solar |  | 05_01_18J394 | 03/04/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | Y
National Grid | BRIDGEWATER | 340383 | 02324 | 15.36 |  |  | Solar |  | 05_09_139L1 | 02/03/2021 | 02/05/2021 | 1 | 0 | 1 | 02/08/2021 | 02/08/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 |  | 2/4/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 671333 | 01757 | 4.35 |  |  | Solar |  | 05_12_12J5 | 02/24/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | GRANBY | 667801 | 01033 | 4990 |  |  | Solar |  | 05_07_915W35 | 03/18/2025 | 04/09/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/10/2025 | 05/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 176910 | 01532 | 499 |  |  | Solar |  | 05_07_797W1 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2016 | 03/18/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2016 | 03/08/2016 | 12/15/2017 | Y | STD | 528 | 11/10/2016 | 08/09/2017 | 185 | 0 | 185 | 12/21/2016 | 12/21/2016 | 12/8/2017 | Connected |  | N
National Grid | RANDOLPH | 341876 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W5 | 03/19/2021 | 03/24/2021 | 2 | 0 | 2 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 6/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2021 | Connected |  | N
National Grid | NORTON | 174198 | 02766 | 3300 |  |  | Solar |  | 05_09_527L1 | 03/20/2012 | 03/20/2012 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 323644 | 01604 | 7.6 |  |  | Solar |  | 05_05_313W2 | 02/23/2021 | 02/24/2021 | 0 | 0 | 0 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 601570 | 01028 | 7.6 |  |  | Solar |  | 05_07_97W2 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 230608 | 01915 | 17.6 |  |  | Solar |  | 05_05_8L2 | 05/24/2019 | 06/05/2019 | 6 | 0 | 6 | 06/06/2019 | 06/06/2019 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 05/24/2019 | 7/15/2020 | Y | EXP | 365 | 11/07/2019 | 01/22/2020 | 76 | 0 | 76 |  |  | 2/12/2020 | Connected |  | N
National Grid | NORWELL | 175076 | 02061 | 100 |  |  | Solar |  | 05_01_1J363 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2013 |  | 2/1/2016 | N | EXP | 829 |  |  | 0 | 0 | 0 | 2/29/2016 | 2/29/2016 | 4/5/2016 | Connected |  | N
National Grid | BRIDGEWATER | 422881 | 02324 | 0 |  |  | Solar |  | 05_09_139L1 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  | 5/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | MILFORD | 175881 | 01757 | 40 |  |  | Solar |  | 05_12_12J6 | 03/09/2015 | 03/09/2015 | 1 | 0 | 1 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2015 |  | 8/17/2015 | N | EXP | 152 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 7/2/2015 | Connected |  | N
National Grid | GRANBY | 678529 | 01033 | 7.6 |  |  | Solar |  | 05_07_915W35 | 03/17/2025 | 03/25/2025 | 10 | 6 | 4 | 04/10/2025 | 04/10/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 186863 | 01532 | 4998 |  |  | Solar |  | 05_07_797W1 | 05/31/2018 | 05/31/2018 | 47 | 4 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2018 | 09/04/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 11/30/2020 | N | STD | 261 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 384000 | 02368 | 6 |  |  | Solar |  | 05_05_335W5 | 09/29/2021 | 12/16/2021 | 3 | 0 | 3 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 174435 | 02766 | 13.8 |  |  | Solar |  | 05_09_527L1 | 06/28/2012 | 06/28/2012 | 6 | 0 | 6 | 07/11/2012 | 07/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 06/28/2012 | 10/26/2012 | Y | EXP | -24 | 07/23/2012 | 10/18/2012 | 61 | 0 | 61 | 10/2/2012 | 10/2/2012 | 11/28/2012 | Connected |  | N
National Grid | WORCESTER | 326856 | 01604 | 8.4 |  |  | Solar |  | 05_05_313W2 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 12/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | MONSON | 607477 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 05/01/2024 | 07/15/2024 | 45 | 42 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 229911 | 01915 | 10 |  |  | Solar |  | 05_05_8L2 | 06/19/2019 | 06/26/2019 | 4 | 0 | 4 | 06/27/2019 | 06/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 424441 | 02061 | 7.6 |  |  | Solar |  | 05_01_1J363 | 05/11/2022 | 05/16/2022 | 3 | 0 | 3 | 05/17/2022 | 05/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2022 |  | 12/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2023 | Connected |  | N
National Grid | BRIDGEWATER | 456718 | 02324 | 15.2 |  |  | Solar |  | 05_09_139L1 | 09/06/2022 | 09/07/2022 | 1 | 0 | 1 | 09/08/2022 | 09/08/2022 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 | 09/06/2022 | 10/10/2023 | Y | EXP | 365 | 01/07/2023 | 01/14/2023 | 8 | 0 | 8 |  |  | 3/2/2023 | Connected |  | N
National Grid | MILFORD | 174453 | 01757 | 75 |  |  | Diesel |  | 05_12_12J7 | 07/12/2012 | 07/12/2012 | 6 | 0 | 6 | 07/24/2012 | 07/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 12/24/2012 | 12/24/2012 | 3/29/2013 | Connected |  | N
National Grid | GRANBY | 683341 | 01033 | 7.6 |  |  | Solar |  | 05_07_915W35 | 04/07/2025 | 05/02/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/07/2025 | 6/27/2026 | Y | EXP | 365 | 08/13/2025 | 09/16/2025 | 35 | 0 | 35 |  |  | 9/25/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 188766 | 01532 | 200 |  |  | Solar |  | 05_07_797W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/02/2018 | 07/02/2018 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | Connected |  | N
National Grid | RANDOLPH | 389597 | 02368 | 9.8 |  |  | Solar |  | 05_05_335W5 | 11/09/2021 | 12/13/2021 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/09/2021 | 12/22/2023 | Y | EXP | 365 | 04/09/2022 | 12/21/2022 | 257 | 0 | 257 |  |  | 2/24/2023 | Connected |  | N
National Grid | NORTON | 174676 | 02766 | 3000 |  |  | Solar |  | 05_09_527L1 | 12/30/2013 | 12/30/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2014 | 01/28/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2014 |  | 12/31/2016 | N | STD | 848 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 334003 | 01604 | 10 |  |  | Solar |  | 05_05_313W2 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2021 | Connected |  | N
National Grid | LONGMEADOW | 615043 | 01028 | 3.8 |  |  | Solar |  | 05_07_97W2 | 06/04/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/04/2024 | 8/28/2025 | Y | EXP | 365 | 09/05/2024 | 09/06/2024 | 2 | 0 | 2 |  |  | 11/6/2024 | Connected |  | N
National Grid | BEVERLY | 297939 | 01915 | 10 |  |  | Solar |  | 05_05_8L2 | 06/23/2020 | 06/29/2020 | 3 | 0 | 3 | 06/30/2020 | 06/30/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2021 | Connected |  | N
National Grid | SCITUATE | 458817 | 02066 | 0 |  |  | Solar |  | 05_01_1J363 | 09/14/2022 | 09/23/2022 | 7 | 7 | 0 | 09/26/2022 | 09/26/2022 | 124 | 37 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 462569 | 02324 | 19 |  |  | Solar |  | 05_09_139L1 | 09/26/2022 | 09/27/2022 | 2 | 1 | 1 | 09/28/2022 | 09/28/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 |  | 9/6/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 175147 | 01757 | 34.2 |  |  | Solar |  | 05_12_12J7 | 10/24/2013 | 10/24/2013 | 8 | 1 | 7 | 11/06/2013 | 11/06/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2013 |  | 12/31/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 3/24/2014 | Connected |  | N
National Grid | BELCHERTOWN | 727094 | 01007 | 0 |  |  | Battery Add-On |  | 05_07_915W36 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 316478 | 01532 | 100 |  |  | Solar |  | 05_07_797W1 | 10/02/2020 | 11/03/2020 | 20 | 14 | 6 | 11/04/2020 | 11/04/2020 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 |  | 8/19/2022 | N | EXP | 592 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | RANDOLPH | 397308 | 02368 | 5.51 |  |  | Solar |  | 05_05_335W5 | 01/28/2022 | 01/31/2022 | 1 | 0 | 1 | 02/01/2022 | 02/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 | 01/28/2022 | 11/24/2023 | Y | EXP | 365 | 08/03/2022 | 11/08/2022 | 98 | 0 | 98 |  |  | 1/9/2023 | Connected |  | N
National Grid | NORTON | 174808 | 02766 | 16 |  |  | Solar |  | 05_09_527L1 | 01/24/2013 | 01/24/2013 | 6 | 0 | 6 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2013 |  | 4/30/2013 | N | EXP | 46 |  |  | 0 | 0 | 0 | 4/10/2013 | 4/10/2013 | 5/2/2013 | Connected |  | N
National Grid | WORCESTER | 375628 | 01610 | 43.2 |  |  | Solar |  | 05_05_313W2 | 08/18/2021 | 11/20/2021 | 65 | 57 | 8 | 11/22/2021 | 11/22/2021 | 22 | 0 | 22 | 08/05/2022 | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | HAMPDEN | 618878 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 06/18/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/18/2024 | 8/6/2025 | Y | EXP | 365 | 12/12/2024 | 03/14/2025 | 93 | 0 | 93 |  |  | 4/8/2025 | Connected |  | N
National Grid | BEVERLY | 319548 | 01915 | 499 |  |  | Solar |  | 05_05_8L2 | 10/16/2020 | 12/14/2020 | 39 | 32 | 7 | 12/15/2020 | 12/15/2020 | 88 | 71 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 547657 | 02061 | 3.8 |  |  | Solar |  | 05_01_1J363 | 08/21/2023 | 08/22/2023 | 1 | 0 | 1 | 08/23/2023 | 08/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 494712 | 02324 | 240 |  |  | Solar |  | 05_09_139L1 | 01/28/2023 | 06/02/2023 | 0 | 0 | 0 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 244606 | 01757 | 146 |  |  | Solar |  | 05_12_12J7 | 07/22/2019 | 08/16/2019 | 17 | 14 | 3 |  |  | 0 | 0 | 0 | 11/01/2019 | 11/01/2019 | 1 | 1 | 0 | 08/19/2019 | 10/01/2019 | 30 | 17 | 13 |  | 11/01/2019 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 07/22/2019 | 1/18/2023 | Y | STD | 365 | 03/25/2023 | 03/24/2023 | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | GRANBY | 174512 | 01033 | 1500 |  |  | Solar |  | 05_07_915W36 | 05/23/2011 | 05/23/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 05/23/2011 | 10/31/2012 | Y | STD | -42 | 01/02/2013 | 09/12/2013 | 166 | 0 | 166 | 9/10/2013 | 9/10/2013 | 9/23/2013 | Connected |  | N
National Grid | NORTHBOROUGH | 331425 | 01532 | 3286 |  |  | Solar |  | 05_07_797W1 | 01/15/2021 | 02/16/2021 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2021 | 08/03/2021 | 117 | 93 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 | 01/15/2021 | 11/7/2024 | Y | STD | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 527637 | 02368 | 10.15 |  |  | Solar |  | 05_05_335W5 | 06/07/2023 |  | 91 | 73 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 175430 | 02766 | 499 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 504 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 380928 | 01602 | 0 |  |  | Solar |  | 05_05_313W2 | 09/27/2021 | 12/16/2021 | 2 | 0 | 2 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 620708 | 01057 | 6 |  |  | Solar |  | 05_07_97W2 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 375663 | 01915 | 240 |  |  | Solar |  | 05_05_8L2 | 08/18/2021 | 09/08/2021 | 14 | 3 | 11 |  |  | 59 | 5 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 08/18/2021 | 2/23/2024 | Y | STD | 532 | 04/14/2023 | 04/20/2023 | 7 | 0 | 7 |  |  | 5/10/2023 | Connected |  | N
National Grid | SCITUATE | 649168 | 02066 | 3.8 |  |  | Solar |  | 05_01_1J363 | 11/04/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/04/2024 | 3/2/2026 | Y | EXP | 365 | 01/23/2025 | 06/16/2025 | 145 | 0 | 145 |  |  | 8/18/2025 | Connected |  | N
National Grid | BRIDGEWATER | 498078 | 02324 | 0 |  |  | Battery Add-On |  | 05_09_139L1 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 8/3/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | MILFORD | 268435 | 01757 | 175 |  |  | Solar |  | 05_12_12J7 | 12/05/2019 | 12/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2019 | 01/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 01/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 5/18/2020 | 12/05/2019 | 1/31/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2023 | Connected |  | N
National Grid | GRANBY | 174513 | 01033 | 1500 |  |  | Solar |  | 05_07_915W36 | 05/23/2011 | 05/23/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 05/23/2011 | 10/31/2012 | Y | STD | -42 | 01/02/2013 | 09/12/2013 | 166 | 0 | 166 | 9/10/2013 | 9/10/2013 | 9/23/2013 | Connected |  | N
National Grid | WESTBOROUGH | 363047 | 01581 | 30 |  |  | Solar |  | 05_07_797W1 | 07/19/2021 | 08/04/2021 | 12 | 6 | 6 | 08/05/2021 | 08/05/2021 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 11/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | Y
National Grid | RANDOLPH | 531921 | 02368 | 6 |  |  | Solar |  | 05_05_335W5 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | NORTON | 175429 | 02766 | 499 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 3/15/2016 | Y | STD | 168 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 478391 | 01602 | 0 |  |  | Other |  | 05_05_313W2 | 12/02/2022 | 04/07/2023 | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/10/2023 | 10/26/2023 | 138 | 119 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 629620 | 01036 | 6.72 |  |  | Solar |  | 05_07_97W2 | 08/02/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 9/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BEVERLY | 375359 | 01915 | 400 |  |  | Solar |  | 05_05_8L2 | 09/10/2021 | 10/15/2021 | 24 | 16 | 8 |  |  | 54 | 21 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 09/10/2021 | 5/3/2024 | Y | STD | 532 | 02/24/2023 | 04/24/2023 | 60 | 0 | 60 |  |  | 4/16/2024 | Connected |  | N
National Grid | SCITUATE | 654216 | 02066 | 7.6 |  |  | Solar |  | 05_01_1J363 | 11/15/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 519840 | 02324 | 15.2 |  |  | Solar |  | 05_09_139L1 | 04/18/2023 | 04/24/2023 | 4 | 0 | 4 | 04/25/2023 | 04/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 |  | 6/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 446332 | 01757 | 50 |  |  | Solar |  | 05_12_12J7 | 07/22/2022 | 09/16/2022 | 39 | 29 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 6/9/2025 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | GRANBY | 174605 | 01033 | 1500 |  |  | Wind |  | 05_07_915W36 | 02/22/2010 | 02/22/2010 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2010 | 02/22/2010 | 3/29/2012 | Y | STD | 520 | 10/18/2011 | 03/15/2012 | 100 | 0 | 100 | 8/3/2012 | 8/3/2012 | 3/29/2012 | Connected |  | N
National Grid | NORTHBOROUGH | 383230 | 01532 | 3000 |  |  | Solar |  | 05_07_797W1 | 03/11/2022 | 03/25/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2022 | 05/20/2022 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 534064 | 02368 | 7.25 |  |  | Solar |  | 05_05_335W5 | 06/20/2023 | 07/03/2023 | 9 | 7 | 2 | 07/05/2023 | 07/05/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2023 | 06/20/2023 | 11/26/2024 | Y | EXP | 365 | 11/28/2023 | 11/29/2023 | 2 | 0 | 2 |  |  | 12/7/2023 | Connected |  | N
National Grid | NORTON | 175428 | 02766 | 499 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 504 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 548448 | 01602 | 10 |  |  | Solar |  | 05_05_313W2 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 |  | 10/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | MONSON | 630217 | 01057 | 3.8 |  |  | Solar |  | 05_07_97W2 | 08/05/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | BEVERLY | 414390 | 01915 | 0 |  |  | Other |  | 05_05_8L2 | 05/09/2022 | 06/21/2022 | 30 | 22 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 660183 | 02066 | 5.76 |  |  | Solar |  | 05_01_1J363 | 12/12/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 522193 | 02324 | 10 |  |  | Solar |  | 05_09_139L1 | 06/05/2023 | 06/12/2023 | 6 | 5 | 1 | 06/13/2023 | 06/13/2023 | 20 | 0 | 20 | 08/09/2023 | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/11/2023 |  | 11/1/2024 | N | EXP | 365 | 10/25/2023 | 10/30/2023 | 6 | 0 | 6 |  |  | 2/14/2024 | Connected |  | N
National Grid | MILFORD | 727434 | 01757 | 8 |  |  | Solar |  | 05_12_12J902 | 10/17/2025 | 10/23/2025 | 1 | 0 | 1 | 10/31/2025 | 10/31/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 10/17/2025 | 12/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRANBY | 177758 | 01033 | 360 |  |  | Solar |  | 05_07_915W36 | 08/02/2017 | 08/02/2017 | 48 | 48 | 0 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  | 12/1/2020 | N | STD | 874 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 390299 | 01581 | 43.2 |  |  | Solar |  | 05_07_797W1 | 10/26/2021 | 01/06/2022 | 18 | 13 | 5 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2021 |  | 6/28/2023 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | RANDOLPH | 579839 | 02368 | 1.74 |  |  | Solar |  | 05_05_335W5 | 01/17/2024 | 01/23/2024 | 4 | 0 | 4 | 01/24/2024 | 01/24/2024 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 175427 | 02766 | 392 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 571722 | 01602 | 10 |  |  | Solar |  | 05_05_313W2 | 11/21/2023 | 12/11/2023 | 14 | 11 | 3 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | MONSON | 633443 | 01057 | 9.57 |  |  | Solar |  | 05_07_97W2 | 08/22/2024 | 10/03/2024 | 26 | 24 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | BEVERLY | 650173 | 01915 | 6.09 |  |  | Solar |  | 05_05_8L2 | 10/28/2024 | 12/09/2024 | 5 | 1 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 10/28/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | SCITUATE | 720993 | 02066 | 18 |  |  | Solar |  | 05_01_1J369 | 10/06/2025 | 10/22/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BRIDGEWATER | 526470 | 02324 | 10 |  |  | Solar |  | 05_09_139L1 | 06/07/2023 | 07/05/2023 | 19 | 16 | 3 | 07/06/2023 | 07/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 |  | 9/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 738984 | 01757 | 7.6 |  |  | Solar |  | 05_12_12J902 | 12/09/2025 | 12/10/2025 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LUDLOW | 206251 | 01056 | 0 |  |  | Solar |  | 05_07_915W36 | 02/01/2019 | 02/12/2019 | 6 | 0 | 6 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 467978 | 01532 | 28.8 |  |  | Solar |  | 05_07_797W1 | 10/19/2022 | 10/21/2022 | 2 | 1 | 1 | 10/24/2022 | 10/24/2022 | 25 | 7 | 18 | 07/21/2023 | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  | 09/18/2023 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 9/21/2023 |  | 11/30/2025 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 586068 | 02368 | 0 |  |  | Battery Add-On |  | 05_05_335W5 | 01/29/2024 | 02/05/2024 | 6 | 3 | 3 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 175426 | 02766 | 280 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/29/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 574880 | 01602 | 0 |  |  | Solar |  | 05_05_313W2 | 11/30/2023 | 12/12/2023 | 9 | 6 | 3 | 12/13/2023 | 12/13/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 639713 | 01036 | 2.32 |  |  | Solar |  | 05_07_97W2 | 09/12/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | BEVERLY | 660293 | 01915 | 7.6 |  |  | Solar |  | 05_05_8L2 | 12/12/2024 | 01/08/2025 | 15 | 11 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/12/2024 | 3/11/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | SCITUATE | 742072 | 02066 | 15.2 |  |  | Solar |  | 05_01_1J369 | 12/23/2025 | 12/26/2025 | 2 | 0 | 2 | 12/29/2025 | 12/29/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 537341 | 02324 | 3.8 |  |  | Solar |  | 05_09_139L1 | 07/05/2023 | 07/19/2023 | 11 | 10 | 1 | 07/20/2023 | 07/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2023 | 07/05/2023 | 11/17/2024 | Y | EXP | 365 | 01/20/2024 | 01/19/2024 | 0 | 0 | 0 |  |  | 1/23/2024 | Connected |  | N
National Grid | MILFORD | 687004 | 01757 | 7.83 |  |  | Solar |  | 05_12_12J903 | 04/23/2025 | 05/12/2025 | 4 | 0 | 4 | 05/30/2025 | 05/30/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/23/2025 | 7/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GRANBY | 337902 | 01033 | 7.6 |  |  | Solar |  | 05_07_915W36 | 01/21/2021 | 02/09/2021 | 13 | 12 | 1 | 02/10/2021 | 02/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 11/26/2022 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 10/28/2022 | Connected |  | N
National Grid | MARLBOROUGH | 473567 | 01752 | 15.925 |  |  | Solar |  | 05_07_797W1 | 11/03/2022 | 11/07/2022 | 2 | 0 | 2 | 11/08/2022 | 11/08/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | RANDOLPH | 588787 | 02368 | 3.8 |  |  | Solar |  | 05_05_335W5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | NORTON | 175425 | 02766 | 499 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 3/15/2016 | Y | STD | 168 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 644993 | 01602 | 8.7 |  |  | Solar |  | 05_05_313W2 | 10/04/2024 | 10/24/2024 | 3 | 1 | 2 | 10/25/2024 | 10/25/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | HAMPDEN | 641021 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 10/07/2024 | 11/12/2024 | 15 | 10 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/07/2024 | 3/12/2026 | Y | EXP | 365 | 04/15/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 9/16/2025 | Connected |  | N
National Grid | BEVERLY | 695741 | 01915 | 22.8 |  |  | Solar |  | 05_05_8L2 | 06/17/2025 | 06/30/2025 | 8 | 6 | 2 | 07/01/2025 | 07/01/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | SCITUATE | 264740 | 02066 | 8.64 |  |  | Solar |  | 05_01_1J369 | 12/31/2019 | 02/19/2020 | 31 | 26 | 5 | 02/20/2020 | 02/20/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 | 12/31/2019 | 2/22/2021 | Y | EXP | 365 | 09/23/2020 | 01/25/2021 | 124 | 0 | 124 |  |  | 2/2/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 564573 | 02333 | 0 |  |  | Solar |  | 05_09_139L1 | 10/19/2023 | 10/26/2023 | 6 | 5 | 1 | 10/27/2023 | 10/27/2023 | 56 | 43 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2024 | Connected |  | N
National Grid | MILFORD | 716171 | 01757 | 3.8 |  |  | Solar |  | 05_12_12J903 | 09/10/2025 | 09/25/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 54 | 36 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 | 09/10/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GRANBY | 600721 | 01033 | 0 |  |  | Solar |  | 05_07_915W36 | 03/31/2024 | 04/02/2024 | 2 | 0 | 2 | 04/03/2024 | 04/03/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 482811 | 01532 | 10 |  |  | Solar |  | 05_07_797W1 | 12/12/2022 | 12/13/2022 | 1 | 0 | 1 | 12/14/2022 | 12/14/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | RANDOLPH | 598467 | 02368 | 12.288 |  |  | Solar |  | 05_05_335W5 | 05/01/2024 | 05/20/2024 | 2 | 0 | 2 | 05/21/2024 | 05/21/2024 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 05/01/2024 | 11/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 175424 | 02766 | 499 |  |  | Solar |  | 05_09_527L1 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2014 | 10/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 | 09/18/2014 | 2/14/2017 | Y | STD | 504 |  |  | 0 | 0 | 0 | 12/27/2016 | 12/27/2016 | 12/27/2016 | Connected |  | N
National Grid | WORCESTER | 666566 | 01602 | 3.8 |  |  | Solar |  | 05_05_313W2 | 01/17/2025 | 03/20/2025 | 10 | 6 | 4 | 03/21/2025 | 03/21/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | MONSON | 646523 | 01057 | 10 |  |  | Solar |  | 05_07_97W2 | 10/18/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | LYNN | 715379 | 01902 | 960 |  |  | Solar |  | 05_05_8L3 | 09/22/2025 | 10/06/2025 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2025 | 10/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SCITUATE | 539352 | 02066 | 6 |  |  | Solar |  | 05_01_1J369 | 02/12/2024 | 07/19/2023 | 9 | 9 | 0 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | BRIDGEWATER | 575689 | 02324 | 11.4 |  |  | Solar |  | 05_09_139L1 | 12/05/2023 | 12/06/2023 | 1 | 0 | 1 | 12/07/2023 | 12/07/2023 | 80 | 56 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2024 | Connected |  | N
National Grid | MILFORD | 730763 | 01757 | 7.6 |  |  | Solar |  | 05_12_12J903 | 11/02/2025 | 11/03/2025 | 2 | 1 | 1 | 11/14/2025 | 11/14/2025 | 33 | 17 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRANBY | 634979 | 01033 | 240 |  |  | Solar |  | 05_07_915W36 | 08/28/2024 | 01/03/2025 | 85 | 78 | 7 | 01/06/2025 | 01/06/2025 | 57 | 24 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 485014 | 01581 | 16 |  |  | Solar |  | 05_07_797W1 | 12/13/2022 | 12/27/2022 | 9 | 8 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N
National Grid | RANDOLPH | 603443 | 02368 | 5.76 |  |  | Solar |  | 05_05_335W5 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/16/2024 | 11/30/2025 | Y | EXP | 365 | 07/24/2024 | 08/28/2024 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 175588 | 02766 | 2000 |  |  | Solar |  | 05_09_527L1 | 04/21/2014 | 04/21/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2014 | 05/29/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 |  | 12/31/2016 | N | STD | 722 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 708079 | 01602 | 11.05 |  |  | Solar |  | 05_05_313W2 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | HAMPDEN | 654919 | 01036 | 11.5 |  |  | Solar |  | 05_07_97W2 | 11/19/2024 | 11/25/2024 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | LYNN | 720592 | 01902 | 15.76 |  |  | Solar |  | 05_05_8L3 | 09/19/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SCITUATE | 571562 | 02066 | 10 |  |  | Solar |  | 05_01_1J369 | 12/07/2023 | 12/12/2023 | 4 | 1 | 3 | 12/13/2023 | 12/13/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 | 12/07/2023 | 2/14/2025 | Y | EXP | 365 | 04/16/2024 | 08/28/2024 | 135 | 0 | 135 |  |  | 10/2/2024 | Connected |  | N
National Grid | BRIDGEWATER | 589118 | 02324 | 6 |  |  | Solar |  | 05_09_139L1 | 04/16/2024 | 04/17/2024 | 1 | 0 | 1 | 04/18/2024 | 04/18/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 04/16/2024 | 5/7/2025 | Y | EXP | 365 | 10/30/2024 | 10/29/2024 | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | MILFORD | 423857 | 01757 | 3 |  |  | Solar |  | 05_12_12J903 | 05/04/2022 | 06/24/2022 | 24 | 22 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 659410 | 01033 | 0 |  |  | Battery Add-On |  | 05_07_915W36 | 12/09/2024 | 12/26/2024 | 12 | 8 | 4 | 12/27/2024 | 12/27/2024 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 486457 | 01532 | 7.6 |  |  | Solar |  | 05_07_797W1 | 12/19/2022 | 01/03/2023 | 9 | 7 | 2 |  |  | 168 | 148 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 629221 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W5 | 08/02/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 175644 | 02766 | 3.23 |  |  | Solar |  | 05_09_527L1 | 12/16/2014 | 12/16/2014 | 8 | 7 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 |  | 12/31/2016 | N | EXP | 710 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 1/8/2016 | Connected |  | N
National Grid | WORCESTER | 718595 | 01602 | 9.75 |  |  | Solar |  | 05_05_313W2 | 09/11/2025 | 11/17/2025 | 19 | 17 | 2 | 11/18/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | HAMPDEN | 669810 | 01036 | 2.03 |  |  | Solar |  | 05_07_97W2 | 02/04/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | LYNN | 734928 | 01904 | 480 |  |  | Solar |  | 05_05_8L3 | 11/21/2025 | 12/18/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SCITUATE | 625582 | 02066 | 10 |  |  | Solar |  | 05_01_1J370 | 07/17/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/17/2024 | 8/20/2025 | Y | EXP | 365 | 12/05/2024 | 03/07/2025 | 93 | 0 | 93 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 620374 | 02324 | 10 |  |  | Solar |  | 05_09_139L1 | 06/25/2024 | 07/28/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 | 06/25/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | MILFORD | 472733 | 01757 | 10 |  |  | Solar |  | 05_12_12J903 | 12/07/2022 |  | 150 | 25 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 667216 | 01033 | 16.96 |  |  | Solar |  | 05_07_915W36 | 03/14/2025 | 03/20/2025 | 4 | 0 | 4 | 03/21/2025 | 03/21/2025 | 175 | 157 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 578968 | 01581 | 10 |  |  | Solar |  | 05_07_797W1 | 01/18/2024 | 01/23/2024 | 3 | 0 | 3 | 01/24/2024 | 01/24/2024 | 50 | 33 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 01/18/2024 | 5/29/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | RANDOLPH | 639115 | 02368 | 7.6 |  |  | Solar |  | 05_05_335W5 | 09/10/2024 | 10/28/2024 | 13 | 9 | 4 | 10/29/2024 | 10/29/2024 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 175908 | 02766 | 374 |  |  | Solar |  | 05_09_527L1 | 09/30/2015 | 09/30/2015 | 8 | 8 | 0 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 | 01/06/2016 | 04/08/2016 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  | 04/08/2016 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 12/14/2018 | N | EXP | 308 |  |  | 0 | 0 | 0 | 2/9/2018 | 2/9/2018 | 2/9/2018 | Connected |  | N
National Grid | WORCESTER | 553649 | 01602 | 160 |  |  | Solar |  | 05_05_313W3 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/11/2023 | 2/21/2027 | Y | EXP | 217 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | HAMPDEN | 674265 | 01036 | 11.4 |  |  | Solar |  | 05_07_97W2 | 02/26/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | LYNN | 743045 | 01902 | 17.1 |  |  | Solar |  | 05_05_8L3 | 01/02/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SCITUATE | 633683 | 02066 | 3.8 |  |  | Solar |  | 05_01_1J370 | 08/19/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BRIDGEWATER | 629307 | 02324 | 100 |  |  | Solar |  | 05_09_139L1 | 08/01/2024 |  | 58 | 49 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 591993 | 01757 | 7.6 |  |  | Solar |  | 05_12_12J903 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 668974 | 01033 | 0 |  |  | Battery Add-On |  | 05_07_915W36 | 01/30/2025 | 02/03/2025 | 2 | 0 | 2 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 592007 | 01532 | 8.99 |  |  | Solar |  | 05_07_797W1 | 02/27/2024 | 03/05/2024 | 5 | 3 | 2 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/27/2024 | 3/25/2025 | Y | EXP | 365 | 04/23/2024 | 04/23/2024 | 1 | 0 | 1 |  |  | 5/8/2024 | Connected |  | N
National Grid | RANDOLPH | 640988 | 02368 | 6 |  |  | Solar |  | 05_05_335W5 | 09/17/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 09/17/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | ATTLEBORO | 175997 | 02703 | 10 |  |  | Solar |  | 05_09_527L1 | 06/11/2015 | 06/11/2015 | 2 | 2 | 0 | 06/16/2015 | 06/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 6/17/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 | 1/12/2016 | Connected |  | N
National Grid | WORCESTER | 704593 | 01602 | 21.52 |  |  | Solar |  | 05_05_313W3 | 07/14/2025 | 07/23/2025 | 7 | 2 | 5 | 07/24/2025 | 07/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 07/14/2025 | 8/27/2026 | Y | EXP | 365 | 12/17/2025 |  | 16 | 0 | 16 |  |  |  | Construction |  | N
National Grid | HAMPDEN | 697060 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W2 | 07/10/2025 | 07/16/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 67 | 55 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175284 | 01902 | 30.96 |  |  | Solar |  | 05_05_8L3 | 09/02/2014 | 09/02/2014 | 4 | 0 | 4 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 8/20/2015 | Connected |  | N
National Grid | SCITUATE | 649792 | 02066 | 7.6 |  |  | Solar |  | 05_01_1J370 | 11/06/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/06/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | BRIDGEWATER | 634462 | 02324 | 16 |  |  | Solar |  | 05_09_139L1 | 08/21/2024 | 08/23/2024 | 3 | 1 | 2 | 08/26/2024 | 08/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N
National Grid | MILFORD | 603517 | 01757 | 10 |  |  | Solar |  | 05_12_12J903 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 20 | 0 | 20 | 06/17/2024 | 07/24/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 7/1/2024 |  | 8/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | GRANBY | 694473 | 01033 | 5.76 |  |  | Solar |  | 05_07_915W36 | 07/10/2025 | 08/15/2025 | 26 | 24 | 2 | 08/18/2025 | 08/18/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 600324 | 01532 | 12 |  |  | Solar |  | 05_07_797W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | RANDOLPH | 642723 | 02368 | 0 |  |  | Solar |  | 05_05_335W5 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 93 | 36 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 175993 | 02703 | 4.95 |  |  | Solar |  | 05_09_527L1 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 6/16/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 4/13/2016 | 4/13/2016 | 4/19/2016 | Connected |  | N
National Grid | WORCESTER | 729724 | 01602 | 12.16 |  |  | Solar |  | 05_05_313W3 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 11/06/2025 | 11/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAMPDEN | 710397 | 01036 | 10 |  |  | Solar |  | 05_07_97W2 | 08/07/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175623 | 01902 | 996 |  |  | Solar |  | 05_05_8L3 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 0 | 0 | 0 | 07/30/2014 | 09/03/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 09/03/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 1/28/2015 | 05/05/2014 | 12/31/2016 | Y | EXP | 703 | 09/17/2015 | 12/18/2015 | 63 | 0 | 63 | 12/21/2015 | 12/21/2015 | 12/21/2015 | Connected |  | N
National Grid | SCITUATE | 291231 | 02066 | 7.6 |  |  | Solar |  | 05_01_1J390 | 06/26/2020 | 07/08/2020 | 7 | 6 | 1 | 07/09/2020 | 07/09/2020 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 647319 | 02333 | 11.5 |  |  | Solar |  | 05_09_139L1 | 10/15/2024 | 11/19/2024 | 10 | 6 | 4 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/15/2024 | 3/24/2026 | Y | EXP | 365 | 05/14/2025 | 05/13/2025 | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | MILFORD | 649321 | 01757 | 12.54 |  |  | Solar |  | 05_12_12J903 | 10/24/2024 | 11/13/2024 | 14 | 11 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | BELCHERTOWN | 698491 | 01007 | 20 |  |  | Solar |  | 05_07_915W36 | 06/13/2025 | 06/26/2025 | 6 | 4 | 2 | 06/27/2025 | 06/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | WESTBOROUGH | 656387 | 01581 | 6.67 |  |  | Solar |  | 05_07_797W1 | 11/24/2024 | 12/11/2024 | 9 | 5 | 4 | 12/12/2024 | 12/12/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/24/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | RANDOLPH | 646004 | 02368 | 9.88 |  |  | Solar |  | 05_05_335W5 | 10/09/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ATTLEBORO | 176077 | 02703 | 0 |  |  | Solar |  | 05_09_527L1 | 08/20/2015 | 08/20/2015 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/29/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/30/2015 |  | 599 | 0 | 599 |  |  | 4/15/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174194 | 01602 | 22.5 |  |  | Solar |  | 05_05_313W3 | 03/19/2012 | 03/19/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2012 |  | 6/4/2012 | N | EXP | -10 |  |  | 0 | 0 | 0 | 6/12/2012 | 6/12/2012 | 7/25/2012 | Connected |  | N
National Grid | MONSON | 686545 | 01057 | 10 |  |  | Solar |  | 05_07_97W3 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 04/21/2025 | 8/7/2026 | Y | EXP | 365 | 11/26/2025 |  | 37 | 0 | 37 |  |  |  | Construction |  | N
National Grid | LYNN | 176343 | 01902 | 1000 |  |  | Solar |  | 05_05_8L3 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2015 | 03/30/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 174831 | 02066 | 2500 |  |  | Solar |  | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 11/24/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 647277 | 02324 | 7.6 |  |  | Solar |  | 05_09_139L1 | 10/15/2024 | 04/23/2025 | 11 | 8 | 3 | 05/22/2025 | 05/22/2025 | 84 | 24 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 660578 | 01757 | 5.76 |  |  | Solar |  | 05_12_12J903 | 12/13/2024 | 01/09/2025 | 5 | 0 | 5 | 01/10/2025 | 01/10/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | BELCHERTOWN | 710488 | 01007 | 0 |  |  | Battery Add-On |  | 05_07_915W36 | 10/06/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 658952 | 01532 | 8.41 |  |  | Solar |  | 05_07_797W1 | 12/06/2024 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 12/06/2024 | 5/29/2026 | Y | EXP | 365 | 07/24/2025 | 10/01/2025 | 70 | 0 | 70 |  |  | 10/16/2025 | Connected |  | N
National Grid | RANDOLPH | 646404 | 02368 | 3.8 |  |  | Solar |  | 05_05_335W5 | 10/25/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/25/2024 | 12/31/2025 | Y | EXP | 365 | 02/13/2025 | 03/18/2025 | 34 | 0 | 34 |  |  | 4/1/2025 | Connected |  | N
National Grid | NORTON | 176332 | 02766 | 7.6 |  |  | Solar |  | 05_09_527L1 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 345 | 0 | 345 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 |  | 9/21/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174179 | 01602 | 54 |  |  | Solar |  | 05_05_313W3 | 03/06/2012 | 03/06/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 8/1/2012 | N | EXP | 54 |  |  | 0 | 0 | 0 | 6/8/2012 | 6/8/2012 | 10/2/2012 | Connected |  | N
National Grid | HAMPDEN | 701953 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W3 | 07/02/2025 | 07/23/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 | 07/02/2025 | 10/6/2026 | Y | EXP | 365 | 11/08/2025 |  | 55 | 0 | 55 |  |  |  | Construction |  | N
National Grid | LYNN | 176342 | 01902 | 2000 |  |  | Solar |  | 05_05_8L3 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2015 | 03/30/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 174830 | 02066 | 500 |  |  | Solar |  | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/09/2012 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 648573 | 02324 | 5.76 |  |  | Solar |  | 05_09_139L1 | 11/01/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 692379 | 01757 | 13.36 |  |  | Solar |  | 05_12_12J904 | 05/22/2025 | 06/04/2025 | 4 | 1 | 3 | 06/25/2025 | 06/25/2025 | 28 | 13 | 15 | 08/12/2025 | 10/02/2025 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 10/02/2025 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | GRANBY | 676491 | 01033 | 24.99 |  |  | Solar |  | 05_07_915W37 | 05/06/2025 | 06/09/2025 | 23 | 20 | 3 | 06/10/2025 | 06/10/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 662678 | 01532 | 7.6 |  |  | Solar |  | 05_07_797W1 | 01/02/2025 | 01/29/2025 | 10 | 6 | 4 | 01/30/2025 | 01/30/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | RANDOLPH | 668548 | 02368 | 10 |  |  | Solar |  | 05_05_335W5 | 01/29/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2025 | Connected |  | N
National Grid | ATTLEBORO | 176449 | 02703 | 17.4 |  |  | Solar |  | 05_09_527L1 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2016 |  | 5/23/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/13/2016 | 7/13/2016 | 7/13/2016 | Connected |  | N
National Grid | WORCESTER | 174244 | 01602 | 10.32 |  |  | Solar |  | 05_05_313W3 | 02/22/2012 | 02/22/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/15/2012 | N | EXP | 14 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 7/26/2012 | Connected |  | N
National Grid | HAMPDEN | 714211 | 01036 | 5.76 |  |  | Solar |  | 05_07_97W3 | 08/22/2025 | 10/03/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 176408 | 01902 | 8.25 |  |  | Solar |  | 05_05_8L3 | 05/09/2016 | 05/09/2016 | 3 | 3 | 0 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/09/2016 | 5/16/2017 | Y | EXP | 344 | 08/04/2016 | 08/20/2016 | 12 | 0 | 12 | 10/11/2016 | 10/11/2016 | 10/11/2016 | Connected |  | N
National Grid | SCITUATE | 174859 | 02066 | 500 |  |  | Solar |  | 05_01_201W1 | 08/01/2012 | 08/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 11/24/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 653870 | 02333 | 7.6 |  |  | Solar |  | 05_09_139L1 | 11/14/2024 | 12/03/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | MILFORD | 487065 | 01757 | 19 |  |  | Solar |  | 05_12_12J904 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | BELCHERTOWN | 723924 | 01007 | 15.76 |  |  | Solar |  | 05_07_915W37 | 10/03/2025 | 10/09/2025 | 4 | 0 | 4 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 667190 | 01532 | 10 |  |  | Solar |  | 05_07_797W1 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2025 | 01/22/2025 | 3/26/2026 | Y | EXP | 365 | 05/21/2025 | 06/10/2025 | 21 | 0 | 21 |  |  | 7/22/2025 | Connected |  | N
National Grid | RANDOLPH | 678267 | 02368 | 0 |  |  | Battery Add-On |  | 05_05_335W5 | 03/14/2025 | 08/22/2025 | 111 | 109 | 2 | 08/25/2025 | 08/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2025 | Connected |  | N
National Grid | ATTLEBORO | 176653 | 02703 | 10 |  |  | Solar |  | 05_09_527L1 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/23/2016 | 02/23/2016 | 234 | 0 | 234 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2016 |  | 2/23/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 | 3/28/2016 | 3/28/2016 |  | Withdrawn |  | N
National Grid | WORCESTER | 174490 | 01602 | 1000 |  |  | Solar |  | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 715083 | 01057 | 7.6 |  |  | Solar |  | 05_07_97W3 | 08/28/2025 | 09/23/2025 | 1 | 0 | 1 | 10/02/2025 | 10/02/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 178027 | 01902 | 57.6 |  |  | Solar |  | 05_05_8L3 | 08/31/2017 | 08/31/2017 | 29 | 28 | 1 | 10/16/2017 | 10/16/2017 | 112 | 0 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 |  | 11/30/2018 | N | EXP | 410 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 175452 | 02066 | 2000 |  |  | Solar |  | 05_01_201W1 | 07/16/2014 | 07/16/2014 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 07/16/2014 | 2/1/2016 | Y | STD | 410 | 04/20/2016 | 08/10/2016 | 77 | 0 | 77 | 8/12/2016 | 8/12/2016 | 8/12/2016 | Connected |  | N
National Grid | EAST BRIDGEWATER | 696231 | 02333 | 15.2 |  |  | Solar |  | 05_09_139L1 | 06/04/2025 | 06/11/2025 | 1 | 0 | 1 | 06/12/2025 | 06/12/2025 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 503337 | 01757 | 3.8 |  |  | Solar |  | 05_12_12J904 | 02/23/2023 | 03/22/2023 | 19 | 17 | 2 | 03/23/2023 | 03/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 | 02/23/2023 | 1/23/2025 | Y | EXP | 365 | 09/06/2023 | 12/08/2023 | 94 | 0 | 94 |  |  | 2/22/2024 | Connected |  | N
National Grid | GRANBY | 174958 | 01033 | 85 |  |  | Solar |  | 05_07_915W37 | 02/28/2013 | 02/28/2013 | 3 | 0 | 3 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2013 |  | 7/31/2013 | N | EXP | 58 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/27/2013 | Connected |  | N
National Grid | NORTHBOROUGH | 174196 | 01532 | 1500 |  |  | Solar |  | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 11/1/2012 | N | STD | -111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 681982 | 02368 | 5.76 |  |  | Solar |  | 05_05_335W5 | 04/02/2025 | 04/16/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/02/2025 | 8/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | ATTLEBORO | 177036 | 02703 | 1980 |  |  | Solar |  | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 174489 | 01464 | 2000 |  |  | Solar |  | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 725687 | 01036 | 18.56 |  |  | Solar |  | 05_07_97W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 188158 | 01904 | 4482 |  |  | Solar |  | 05_05_8L3 | 06/29/2018 | 07/19/2018 | 12 | 0 | 12 |  |  | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2020 | 06/29/2018 | 11/8/2024 | Y | STD | 147 | 09/17/2022 | 06/20/2023 | 277 | 268 | 9 |  |  | 10/25/2024 | Connected |  | N
National Grid | SCITUATE | 175557 | 02066 | 996 |  |  | Solar |  | 05_01_201W1 | 07/30/2014 | 07/30/2014 | 6 | 1 | 5 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/13/2014 | 8 | 0 | 8 | 08/08/2014 | 09/10/2014 | 22 | 1 | 21 |  | 10/13/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 8/25/2015 | 07/30/2014 | 12/10/2016 | Y | STD | 473 | 07/07/2016 | 12/20/2016 | 114 | 0 | 114 | 12/7/2016 | 12/7/2016 | 12/21/2016 | Connected |  | N
National Grid | BRIDGEWATER | 704049 | 02324 | 23.04 |  |  | Solar |  | 05_09_139L1 | 07/14/2025 | 07/21/2025 | 5 | 0 | 5 | 07/22/2025 | 07/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | MILFORD | 608562 | 01757 | 10 |  |  | Solar |  | 05_12_12J904 | 05/06/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/06/2024 | 9/4/2025 | Y | EXP | 365 | 08/20/2024 | 01/17/2025 | 151 | 0 | 151 |  |  | 3/28/2025 | Connected |  | N
National Grid | GRANBY | 175771 | 01033 | 196 |  |  | Solar |  | 05_07_915W37 | 08/15/2014 | 08/15/2014 | 6 | 1 | 5 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2014 |  | 12/31/2014 | N | EXP | 106 |  |  | 0 | 0 | 0 | 12/19/2014 | 12/19/2014 | 12/19/2014 | Connected |  | N
National Grid | NORTHBOROUGH | 174480 | 01532 | 1500 |  |  | Solar |  | 05_07_797W19 | 04/19/2011 | 04/19/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2011 | 06/20/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2012 | 04/19/2011 | 10/31/2012 | Y | STD | 282 | 05/27/2013 | 07/27/2013 | 42 | 0 | 42 | 7/26/2013 | 7/26/2013 | 8/15/2013 | Connected |  | N
National Grid | HOLBROOK | 727130 | 02343 | 5.76 |  |  | Solar |  | 05_05_335W9 | 10/16/2025 | 10/24/2025 | 5 | 2 | 3 | 10/27/2025 | 10/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 10/16/2025 | 12/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 177035 | 02703 | 990 |  |  | Solar |  | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 174916 | 01464 | 760 |  |  | Solar |  | 05_05_313W3 | 02/14/2013 | 02/14/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2013 | 04/09/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 |  | 6/30/2014 | N | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | HAMPDEN | 728113 | 01036 | 10 |  |  | Solar |  | 05_07_97W3 | 10/21/2025 | 12/04/2025 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 204801 | 01902 | 20 |  |  | Solar |  | 05_05_8L3 | 12/27/2018 | 01/10/2019 | 8 | 3 | 5 | 01/11/2019 | 01/11/2019 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 2/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | COHASSET | 175925 | 02025 | 750 |  |  | Solar |  | 05_01_201W1 | 05/29/2015 | 06/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 07/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/30/2016 | 06/15/2016 | 0 | 0 | 0 | 12/5/2018 | 05/29/2015 | 12/31/2022 | Y | STD | 324 | 04/16/2022 | 06/18/2022 | 64 | 0 | 64 |  |  | 12/29/2022 | Connected |  | N
National Grid | BRIDGEWATER | 742643 | 02324 | 0 |  |  | Battery Add-On |  | 05_09_139L3 | 01/05/2026 | 01/07/2026 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 635914 | 01757 | 3.8 |  |  | Solar |  | 05_12_12J904 | 08/28/2024 | 09/05/2024 | 1 | 0 | 1 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | GRANBY | 310912 | 01033 | 6.67 |  |  | Solar |  | 05_07_915W37 | 09/15/2020 | 10/02/2020 | 13 | 13 | 0 | 10/05/2020 | 10/05/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 11/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 174898 | 01532 | 1800 |  |  | Solar |  | 05_07_797W19 | 03/20/2012 | 03/20/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2012 | 07/18/2012 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 12/3/2012 | N | STD | -79 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 174306 | 02343 | 95 |  |  | Solar |  | 05_05_335W9 | 01/06/2012 | 01/06/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2012 | 01/06/2012 | 5/7/2012 | Y | EXP | 10 | 06/06/2012 | 06/18/2012 | 8 | 0 | 8 | 7/16/2012 | 7/16/2012 | 7/24/2012 | Connected |  | N
National Grid | NORTON | 177034 | 02766 | 3960 |  |  | Solar |  | 05_09_527L1 | 07/26/2016 | 07/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2016 | 08/24/2016 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 176105 | 01464 | 20 |  |  | Solar |  | 05_05_313W3 | 06/24/2015 | 06/24/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/30/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/4/2015 | Connected |  | N
National Grid | HAMPDEN | 731036 | 01036 | 7.6 |  |  | Solar |  | 05_07_97W3 | 11/03/2025 | 11/04/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 210131 | 01902 | 13.8 |  |  | Solar |  | 05_05_8L3 | 03/04/2019 | 03/12/2019 | 5 | 0 | 5 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 | 03/04/2019 | 3/27/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2019 | Connected |  | N
National Grid | COHASSET | 176075 | 02025 | 920 |  |  | Solar |  | 05_01_201W1 | 08/18/2015 | 08/18/2015 | 7 | 7 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 | 11/06/2015 | 12/02/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 12/02/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/23/2016 | 08/18/2015 | 8/25/2016 | Y | EXP | 155 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | BRIDGEWATER | 175297 | 02324 | 499 |  |  | Solar |  | 05_09_139L3 | 01/15/2015 | 01/15/2015 | 4 | 0 | 4 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 | 01/15/2015 | 3/10/2016 | Y | EXP | 373 | 11/04/2015 | 12/23/2015 | 33 | 0 | 33 | 1/25/2016 | 1/25/2016 | 1/25/2016 | Connected |  | N
National Grid | MILFORD | 644745 | 01757 | 3.8 |  |  | Solar |  | 05_12_12J904 | 10/03/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 10/03/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 329626 | 01033 | 22.8 |  |  | Solar |  | 05_07_915W37 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 | 12/04/2020 | 12/6/2021 | Y | EXP | 365 | 02/11/2021 | 03/17/2021 | 34 | 0 | 34 |  |  | 5/19/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 176793 | 01532 | 11.4 |  |  | Solar |  | 05_07_797W19 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 238 | 0 | 238 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/1/2017 | N | EXP | 317 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y
National Grid | RANDOLPH | 176265 | 02368 | 200 |  |  | Solar |  | 05_05_335W9 | 09/09/2015 | 09/09/2015 | 3 | 3 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2015 |  | 9/14/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 4/8/2016 | Connected |  | N
National Grid | ATTLEBORO | 177166 | 02703 | 3000 |  |  | Solar |  | 05_09_527L1 | 01/25/2017 | 01/27/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2017 | 03/01/2017 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 | 01/25/2017 | 8/16/2021 | Y | STD | 21 | 06/02/2020 | 01/11/2021 | 224 | 5 | 219 | 7/22/2021 | 7/29/2021 | 7/29/2021 | Connected |  | N
National Grid | SHIRLEY | 177233 | 01464 | 156 |  |  | Solar |  | 05_05_313W3 | 11/04/2016 | 11/04/2016 | 1 | 1 | 0 | 11/08/2016 | 11/08/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 |  | 11/12/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 176628 | 01028 | 10 |  |  | Solar |  | 05_07_97W3 | 10/15/2015 | 10/15/2015 | 4 | 4 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/20/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 8/18/2016 | Connected |  | N
National Grid | LYNN | 258893 | 01904 | 0 |  |  | Solar |  | 05_05_8L3 | 10/08/2019 | 10/09/2019 | 0 | 0 | 0 | 10/10/2019 | 10/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2019 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2019 | Connected |  | N
National Grid | SCITUATE | 176239 | 02066 | 1000 |  |  | Solar |  | 05_01_201W1 | 04/27/2015 | 04/27/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 06/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 03/15/2016 | 06/24/2016 | 69 | 0 | 69 | 8/4/2016 | 04/27/2015 | 7/31/2018 | Y | STD | 726 | 11/28/2017 | 05/30/2018 | 183 | 0 | 183 | 1/9/2018 | 1/9/2018 | 6/29/2018 | Connected |  | N
National Grid | WEST BRIDGEWATER | 176704 | 02379 | 499 |  |  | Solar |  | 05_09_139L3 | 10/28/2015 | 10/28/2015 | 0 | 0 | 0 | 10/28/2015 | 10/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 10/28/2015 | 11/2/2016 | Y | EXP | 314 | 12/30/2016 | 02/14/2017 | 30 | 0 | 30 | 3/21/2017 | 3/21/2017 | 3/30/2017 | Connected |  | N
National Grid | MILFORD | 653929 | 01757 | 5.76 |  |  | Solar |  | 05_12_12J904 | 11/27/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 338336 | 01033 | 466.6 |  |  | Solar |  | 05_07_915W37 | 02/08/2021 | 02/17/2021 | 5 | 0 | 5 | 02/18/2021 | 02/18/2021 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 177635 | 01532 | 8 |  |  | Solar |  | 05_07_797W19 | 07/19/2017 | 07/19/2017 | 23 | 18 | 5 | 08/22/2017 | 08/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 | 07/19/2017 | 7/25/2018 | Y | EXP | 331 | 12/20/2017 | 12/30/2017 | 7 | 0 | 7 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N
National Grid | HOLBROOK | 176493 | 02343 | 9.75 |  |  | Solar |  | 05_05_335W9 | 12/10/2015 | 12/10/2015 | 20 | 20 | 0 | 01/11/2016 | 01/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/15/2016 | N | EXP | 331 |  |  | 0 | 0 | 0 | 3/8/2016 | 3/8/2016 | 3/8/2016 | Connected |  | N
National Grid | ATTLEBORO | 177200 | 02703 | 2.4 |  |  | Solar |  | 05_09_527L1 | 02/01/2017 | 02/01/2017 | 1 | 0 | 1 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/7/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 8/29/2017 | 8/29/2017 | 8/28/2017 | Connected |  | N
National Grid | AYER | 177390 | 01432 | 15.2 |  |  | Solar |  | 05_05_313W3 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 176652 | 01036 | 6 |  |  | Solar |  | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 | 02/17/2016 | 9/26/2019 | Y | EXP | 1274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 282466 | 01902 | 7.6 |  |  | Solar |  | 05_05_8L3 | 04/14/2020 | 04/21/2020 | 4 | 4 | 0 | 04/22/2020 | 04/22/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 04/14/2020 | 4/20/2021 | Y | EXP | 365 | 01/21/2021 | 02/08/2021 | 18 | 0 | 18 |  |  | 2/9/2021 | Connected |  | N
National Grid | SCITUATE | 176238 | 02066 | 1000 |  |  | Solar |  | 05_01_201W1 | 04/27/2015 | 04/27/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 06/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/26/2016 | 06/24/2016 | 0 | 0 | 0 | 8/4/2016 | 04/27/2015 | 7/31/2018 | Y | STD | 726 | 11/28/2017 | 05/30/2018 | 183 | 0 | 183 | 1/25/2018 | 1/25/2018 | 6/29/2018 | Connected |  | N
National Grid | WEST BRIDGEWATER | 178644 | 02379 | 1000 |  |  | Solar |  | 05_09_139L3 | 12/15/2017 | 01/05/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2018 | 02/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2018 | 12/15/2017 | 12/31/2020 | Y | STD | 687 | 04/24/2020 | 10/27/2020 | 187 | 5 | 182 | 12/9/2020 | 12/8/2020 | 12/22/2020 | Connected |  | N
National Grid | HOPEDALE | 727173 | 01747 | 15.2 |  |  | Solar |  | 05_12_12L2 | 10/16/2025 | 11/03/2025 | 11 | 7 | 4 | 11/04/2025 | 11/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRANBY | 343630 | 01033 | 499 |  |  | Solar |  | 05_07_915W37 | 05/13/2021 | 06/28/2021 | 31 | 20 | 11 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178556 | 01532 | 133.2 |  |  | Solar |  | 05_07_797W19 | 03/12/2018 | 03/12/2018 | 1 | 0 | 1 | 03/30/2018 | 03/30/2018 | 4 | 0 | 4 | 04/06/2018 | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  | 05/16/2018 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 5/30/2018 | 03/12/2018 | 1/10/2022 | Y | EXP | 611 | 02/12/2021 | 12/17/2021 | 309 | 6 | 303 |  |  | 12/30/2021 | Connected |  | N
National Grid | RANDOLPH | 177054 | 02368 | 8 |  |  | Solar |  | 05_05_335W9 | 01/12/2017 | 01/12/2017 | 18 | 17 | 1 | 02/08/2017 | 02/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2017 |  | 1/17/2018 | N | EXP | 342 |  |  | 0 | 0 | 0 | 6/1/2017 | 6/1/2017 | 6/9/2017 | Connected |  | N
National Grid | NORTON | 177258 | 02766 | 10 |  |  | Solar |  | 05_09_527L1 | 08/18/2016 | 08/18/2016 | 1 | 1 | 0 | 08/22/2016 | 08/22/2016 | 99 | 0 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2016 |  | 8/24/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 177966 | 01432 | 480 |  |  | Solar |  | 05_05_313W3 | 04/21/2017 | 04/21/2017 | 197 | 194 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 176647 | 01095 | 1260 |  |  | Solar |  | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 301078 | 01904 | 7.6 |  |  | Solar |  | 05_05_8L3 | 07/14/2020 | 07/17/2020 | 2 | 0 | 2 | 07/20/2020 | 07/20/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 176320 | 02025 | 997.6 |  |  | Solar |  | 05_01_201W1 | 05/11/2015 | 05/11/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/15/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 186355 | 02379 | 21 |  |  | Solar |  | 05_09_139L3 | 05/25/2018 | 05/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 174621 | 01747 | 190 |  |  | Solar |  | 05_12_12L2 | 04/06/2011 | 04/06/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2011 |  | 8/11/2012 | N | EXP | 380 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/18/2012 | Connected |  | Y
National Grid | GRANBY | 343627 | 01033 | 500 |  |  | Solar |  | 05_07_915W37 | 05/13/2021 | 06/28/2021 | 31 | 20 | 11 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 191685 | 01532 | 136 |  |  | Solar |  | 05_07_797W19 | 12/05/2018 | 12/12/2018 | 4 | 0 | 4 | 12/13/2018 | 12/13/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 178035 | 02343 | 20 |  |  | Solar |  | 05_05_335W9 | 10/26/2017 | 10/26/2017 | 67 | 67 | 0 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 11/1/2018 | N | EXP | 261 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 177254 | 02703 | 6 |  |  | Solar |  | 05_09_527L1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/20/2016 | 06/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/20/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 10/27/2016 | 10/27/2016 | 10/27/2016 | Connected |  | N
National Grid | SHIRLEY | 178354 | 01464 | 480 |  |  | Solar |  | 05_05_313W3 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/02/2018 | 03/02/2018 | 169 | 9 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/5/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 176646 | 01036 | 1988 |  |  | Solar |  | 05_07_97W3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/18/2016 | 03/08/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 310170 | 01902 | 10 |  |  | Solar |  | 05_05_8L3 | 10/06/2020 | 10/09/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 176319 | 02025 | 904.8 |  |  | Solar |  | 05_01_201W1 | 05/11/2015 | 05/11/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/15/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 195698 | 02379 | 0 |  |  | Solar |  | 05_09_139L3 | 06/25/2019 |  | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 174782 | 01747 | 7.31 |  |  | Solar |  | 05_12_12L2 | 07/11/2013 | 07/11/2013 | 7 | 0 | 7 | 07/23/2013 | 07/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2013 |  | 10/31/2013 | N | EXP | 97 |  |  | 0 | 0 | 0 | 11/4/2013 | 11/4/2013 | 11/4/2013 | Connected |  | N
National Grid | GRANBY | 440798 | 01033 | 9.86 |  |  | Solar |  | 05_07_915W37 | 07/19/2022 | 07/21/2022 | 2 | 0 | 2 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2022 |  | 8/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 223130 | 01532 | 133.2 |  |  | Solar |  | 05_07_797W19 | 04/27/2019 | 05/21/2019 | 16 | 13 | 3 | 05/22/2019 | 05/22/2019 | 26 | 16 | 10 | 07/26/2019 | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 |  | 09/04/2020 | 61 | 58 | 3 |  |  | 0 | 0 | 0 | 9/28/2020 |  | 1/3/2023 | N | EXP | 365 | 02/25/2021 | 12/08/2021 | 286 | 67 | 219 |  |  | 3/7/2022 | Connected |  | N
National Grid | HOLBROOK | 178508 | 02343 | 5.06 |  |  | Solar |  | 05_05_335W9 | 03/07/2018 | 03/07/2018 | 5 | 0 | 5 | 03/15/2018 | 03/15/2018 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/13/2019 | N | EXP | 306 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 177665 | 02766 | 7.6 |  |  | Solar |  | 05_09_527L1 | 05/24/2017 | 05/24/2017 | 5 | 5 | 0 | 06/02/2017 | 06/02/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2017 | 05/24/2017 | 8/31/2018 | Y | EXP | 452 | 01/30/2018 | 02/12/2018 | 9 | 0 | 9 |  |  | 6/11/2018 | Connected |  | N
National Grid | SHIRLEY | 196299 | 01464 | 236 |  |  | Solar |  | 05_05_313W3 | 11/14/2018 | 11/20/2018 | 3 | 0 | 3 | 11/21/2018 | 11/21/2018 | 18 | 2 | 16 | 06/11/2019 | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 176991 | 01036 | 3.8 |  |  | Solar |  | 05_07_97W3 | 03/13/2017 | 03/13/2017 | 9 | 7 | 2 | 03/28/2017 | 03/28/2017 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 317491 | 01902 | 50 |  |  | Solar |  | 05_05_8L3 | 10/06/2020 | 10/15/2020 | 5 | 0 | 5 | 10/16/2020 | 10/16/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2021 | Connected |  | N
National Grid | COHASSET | 177928 | 02025 | 750 |  |  | Solar |  | 05_01_201W1 | 04/18/2017 | 04/18/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2017 | 08/01/2017 | 63 | 47 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 | 04/18/2017 | 6/10/2020 | Y | STD | 709 | 12/06/2019 | 01/16/2020 | 41 | 0 | 41 |  |  | 6/16/2020 | Connected |  | N
National Grid | WEST BRIDGEWATER | 460717 | 02379 | 17.98 |  |  | Solar |  | 05_09_139L3 | 10/04/2022 | 10/10/2022 | 4 | 1 | 3 | 10/11/2022 | 10/11/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 1/13/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 174863 | 01747 | 60 |  |  | Solar |  | 05_12_12L2 | 10/18/2011 | 10/18/2011 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 7/13/2012 | Y | EXP | 127 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 7/13/2012 | Connected |  | N
National Grid | GRANBY | 461808 | 01033 | 230 |  |  | Solar |  | 05_07_915W37 | 10/14/2022 | 11/03/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2022 | 11/30/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 234850 | 01532 | 7.6 |  |  | Solar |  | 05_07_797W19 | 04/29/2020 | 06/09/2020 | 27 | 26 | 1 | 06/10/2020 | 06/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 188692 | 02368 | 499.5 |  |  | Solar |  | 05_05_335W9 | 11/17/2018 | 01/08/2019 | 33 | 25 | 8 | 01/09/2019 | 01/09/2019 | 22 | 4 | 18 | 03/01/2019 | 07/02/2019 | 87 | 53 | 34 |  |  | 0 | 0 | 0 |  | 07/02/2019 | 87 | 53 | 34 |  |  | 0 | 0 | 0 | 7/11/2019 | 11/17/2018 | 1/18/2021 | Y | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 177734 | 02766 | 10 |  |  | Solar |  | 05_09_527L1 | 03/22/2017 | 03/22/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/22/2017 | 3/27/2018 | Y | EXP | 363 |  |  | 0 | 0 | 0 | 1/5/2018 | 1/5/2018 | 1/8/2018 | Connected |  | N
National Grid | SHIRLEY | 196297 | 01464 | 496 |  |  | Solar |  | 05_05_313W3 | 11/15/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 177328 | 01095 | 15.2 |  |  | Solar |  | 05_07_97W3 | 06/20/2016 | 06/20/2016 | 2 | 2 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/26/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/17/2016 | Connected |  | N
National Grid | BEVERLY | 375559 | 01915 | 100 |  |  | Solar |  | 05_05_8L3 | 08/18/2021 | 09/08/2021 | 14 | 3 | 11 |  |  | 59 | 28 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2022 | 08/18/2021 | 3/23/2023 | Y | STD | 196 | 01/25/2023 | 04/20/2023 | 85 | 59 | 26 |  |  | 5/12/2023 | Connected |  | N
National Grid | COHASSET | 208607 | 02025 | 500 |  |  | Solar |  | 05_01_201W1 | 03/22/2019 | 04/23/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/23/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 506045 | 02301 | 10 |  |  | Solar |  | 05_09_139L3 | 03/16/2023 | 03/22/2023 | 5 | 2 | 3 | 03/23/2023 | 03/23/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/16/2023 | 6/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2023 | Connected |  | N
National Grid | HOPEDALE | 175049 | 01747 | 85 |  |  | Solar |  | 05_12_12L2 | 10/18/2011 | 10/18/2011 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 8/19/2012 | Y | EXP | 164 |  |  | 0 | 0 | 0 | 8/14/2012 | 8/14/2012 | 7/13/2012 | Connected |  | N
National Grid | GRANBY | 471856 | 01033 | 13.34 |  |  | Solar |  | 05_07_915W37 | 03/20/2023 | 01/16/2024 | 205 | 195 | 10 | 01/17/2024 | 01/17/2024 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 | 03/20/2023 | 3/26/2025 | Y | EXP | 365 | 04/19/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 10/3/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 245587 | 01532 | 7.6 |  |  | Solar |  | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 4 | 0 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/31/2019 | 12/31/2020 | Y | EXP | 365 | 09/02/2020 | 09/18/2020 | 16 | 0 | 16 |  |  | 10/17/2020 | Connected |  | N
National Grid | HOLBROOK | 273947 | 02343 | 7.6 |  |  | Solar |  | 05_05_335W9 | 01/23/2020 | 04/14/2020 | 42 | 35 | 7 | 04/15/2020 | 04/15/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 01/23/2020 | 5/4/2022 | Y | EXP | 365 | 07/31/2021 | 10/04/2021 | 63 | 3 | 60 |  |  | 12/8/2021 | Connected |  | N
National Grid | NORTON | 177779 | 02766 | 4150 |  |  | Solar |  | 05_09_527L1 | 03/30/2017 | 03/30/2017 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2017 | 05/11/2017 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 201086 | 01464 | 2460 |  |  | Solar |  | 05_05_313W3 | 02/20/2019 | 01/15/2020 | 226 | 26 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2020 | 08/19/2020 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 177626 | 01095 | 10 |  |  | Solar |  | 05_07_97W3 | 05/23/2017 | 05/23/2017 | 3 | 3 | 0 | 05/30/2017 | 05/30/2017 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/29/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 376662 | 01915 | 7.6 |  |  | Solar |  | 05_05_8L3 | 08/19/2021 | 08/26/2021 | 6 | 5 | 1 | 08/27/2021 | 08/27/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 08/19/2021 | 10/1/2022 | Y | EXP | 365 | 09/14/2021 | 09/30/2021 | 17 | 0 | 17 |  |  | 10/7/2021 | Connected |  | N
National Grid | COHASSET | 326607 | 02025 | 8 |  |  | Solar |  | 05_01_201W1 | 11/17/2020 | 11/20/2020 | 2 | 0 | 2 | 11/23/2020 | 11/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/17/2020 | 5/3/2022 | Y | EXP | 365 | 03/12/2021 | 04/12/2021 | 31 | 0 | 31 |  |  | 9/14/2021 | Connected |  | N
National Grid | BROCKTON | 682735 | 02301 | 11.4 |  |  | Solar |  | 05_09_139L3 | 04/03/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 175316 | 01747 | 6.45 |  |  | Solar |  | 05_12_12L2 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2014 |  | 11/28/2014 | N | EXP | 52 |  |  | 0 | 0 | 0 | 10/7/2014 | 10/7/2014 | 4/27/2015 | Connected |  | N
National Grid | GRANBY | 488438 | 01033 | 0 |  |  | Solar |  | 05_07_915W37 | 01/03/2023 | 01/05/2023 | 2 | 0 | 2 | 01/06/2023 | 01/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 9/30/2024 | N | EXP | 470 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 246245 | 01532 | 100 |  |  | Solar |  | 05_07_797W19 | 07/31/2019 | 08/07/2019 | 4 | 1 | 3 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 273620 | 02343 | 486.6 |  |  | Solar |  | 05_05_335W9 | 01/16/2020 | 01/24/2020 | 1 | 0 | 1 | 01/27/2020 | 01/27/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178120 | 02703 | 3960 |  |  | Solar |  | 05_09_527L1 | 05/11/2017 | 05/11/2017 | 219 | 218 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 177813 | 01464 | 7.6 |  |  | Solar |  | 05_07_97W3 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 12/15/2017 | 12/15/2017 | 12/15/2017 | Connected |  | N
National Grid | WILBRAHAM | 404485 | 01095 | 16.08 |  |  | Solar |  | 05_05_8L3 | 01/08/2022 | 01/18/2022 | 6 | 2 | 4 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 3/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | BEVERLY | 456437 | 01915 | 4.64 |  |  | Solar |  | 05_01_201W1 | 10/27/2022 | 10/31/2022 | 2 | 0 | 2 | 11/22/2022 | 11/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 683586 | 02025 | 10 |  |  | Solar |  | 05_09_139L3 | 04/08/2025 | 04/30/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175647 | 02301 | 3.66 |  |  | Solar |  | 05_12_12L2 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/16/2015 | N | EXP | 41 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/29/2015 | Connected |  | N
National Grid | MILFORD | 645050 | 01757 | 9.1 |  |  | Solar |  | 05_07_915W37 | 10/05/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | GRANBY | 254306 | 01033 | 0 |  |  | Solar |  | 05_07_797W19 | 09/17/2019 | 09/17/2019 | 0 | 0 | 0 | 09/18/2019 | 09/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 | 09/17/2019 | 6/22/2020 | Y | EXP | 365 | 12/19/2019 | 01/14/2020 | 26 | 0 | 26 |  |  | 4/3/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 282586 | 01532 | 240 |  |  | Solar |  | 05_05_335W9 | 03/05/2020 | 03/10/2020 | 2 | 0 | 2 | 03/11/2020 | 03/11/2020 | 29 | 7 | 22 | 04/22/2020 | 05/28/2020 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 05/28/2020 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 5/28/2020 |  | 12/27/2025 | N | EXP | 200 | 12/23/2020 | 11/06/2025 | 1778 | 1600 | 178 |  |  | 12/31/2025 | Connected |  | N
National Grid | RANDOLPH | 178462 | 02368 | 8300 |  |  | Solar |  | 05_09_527L1 | 01/22/2018 | 02/27/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 04/03/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 288940 | 02703 | 11.4 |  |  | Solar |  | 05_05_313W3 | 04/22/2020 | 04/30/2020 | 6 | 6 | 0 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2020 | Connected |  | N
National Grid | AYER | 178683 | 01432 | 149.4 |  |  | Solar |  | 05_07_97W3 | 12/18/2017 | 12/18/2017 | 49 | 41 | 8 | 03/12/2018 | 03/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2018 |  | 6/30/2020 | N | EXP | 285 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 426000 | 01036 | 11.89 |  |  | Solar |  | 05_05_8L3 | 06/28/2022 | 07/20/2022 | 15 | 14 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2022 | Connected |  | N
National Grid | BEVERLY | 683852 | 01915 | 16.24 |  |  | Solar |  | 05_09_139L3 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SCITUATE | 176390 | 02066 | 7.6 |  |  | Solar |  | 05_12_12L2 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/6/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 740453 | 02301 | 0 |  |  | Battery Add-On |  | 05_07_915W82 | 12/16/2025 | 12/17/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HOPEDALE | 290955 | 01747 | 57.6 |  |  | Solar |  | 05_07_797W19 | 08/03/2020 | 08/13/2020 | 7 | 3 | 4 | 08/14/2020 | 08/14/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 3/7/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 3/4/2022 | Connected |  | N
National Grid | GRANBY | 378195 | 01033 | 11.4 |  |  | Solar |  | 05_05_335W9 | 08/26/2021 | 09/20/2021 | 16 | 15 | 1 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 178677 | 01532 | 7.6 |  |  | Solar |  | 05_09_527L1 | 04/11/2018 | 04/11/2018 | 53 | 29 | 24 | 05/22/2018 | 05/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2018 |  | 4/17/2019 | N | EXP | 270 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 387185 | 02368 | 8.12 |  |  | Solar |  | 05_05_313W3 | 11/29/2021 | 01/07/2022 | 11 | 4 | 7 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 193636 | 02766 | 10 |  |  | Solar |  | 05_07_97W3 | 08/15/2018 | 10/08/2018 | 46 | 22 | 24 | 11/02/2018 | 11/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2019 | 08/15/2018 | 10/8/2020 | Y | EXP | 365 | 10/23/2019 | 11/13/2019 | 21 | 0 | 21 |  |  | 1/3/2020 | Connected |  | N
National Grid | AYER | 466376 | 01432 | 5.76 |  |  | Solar |  | 05_05_8L3 | 11/16/2022 | 11/21/2022 | 3 | 0 | 3 | 11/22/2022 | 11/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/16/2022 | 2/29/2024 | Y | EXP | 365 | 02/25/2023 | 02/27/2023 | 3 | 0 | 3 |  |  | 5/23/2023 | Connected |  | N
National Grid | WILBRAHAM | 489990 | 01095 | 11.31 |  |  | Solar |  | 05_01_201W1 | 01/06/2023 | 01/06/2023 | 0 | 0 | 0 | 01/09/2023 | 01/09/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 701116 | 01915 | 7.6 |  |  | Solar |  | 05_09_139L5 | 06/25/2025 | 07/11/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 14 | 2 | 12 | 08/20/2025 | 09/26/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 09/26/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | COHASSET | 176572 | 02025 | 68 |  |  | Solar |  | 05_12_12L2 | 02/11/2016 | 02/11/2016 | 3 | 3 | 0 | 02/17/2016 | 02/17/2016 | 162 | 0 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/16/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 177080 | 02379 | 312 |  |  | Solar |  | 05_07_915W82 | 10/18/2016 | 10/18/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/23/2017 | 59 | 43 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2018 | 10/18/2016 | 11/8/2021 | Y | STD | 225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 345964 | 01747 | 500 |  |  | Solar |  | 05_07_797W19 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 174 | 126 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 478522 | 01033 | 7.6 |  |  | Solar |  | 05_05_335W9 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2023 | Connected |  | Y
National Grid | NORTHBOROUGH | 178698 | 01532 | 4400 |  |  | Solar |  | 05_09_527L1 | 02/07/2018 | 04/02/2018 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 415225 | 02368 | 15.2 |  |  | Solar |  | 05_05_313W3 | 03/03/2022 |  | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 247656 | 02703 | 5 |  |  | Solar |  | 05_07_97W3 | 09/25/2019 | 09/30/2019 | 2 | 0 | 2 | 10/01/2019 | 10/01/2019 | 19 | 16 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2019 | 09/25/2019 | 9/25/2020 | Y | EXP | 365 | 03/04/2020 | 05/08/2020 | 65 | 0 | 65 |  |  | 6/18/2020 | Connected |  | N
National Grid | AYER | 478397 | 01432 | 15 |  |  | Solar |  | 05_05_8L3 | 01/18/2023 | 01/20/2023 | 2 | 0 | 2 | 01/23/2023 | 01/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/18/2023 | 4/18/2024 | Y | EXP | 365 | 03/29/2023 | 04/13/2023 | 16 | 0 | 16 |  |  | 10/7/2023 | Connected |  | N
National Grid | WILBRAHAM | 562170 | 01095 | 0 |  |  | Battery Add-On |  | 05_01_201W1 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 93 | 75 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 5/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | BEVERLY | 176488 | 01915 | 7.6 |  |  | Solar |  | 05_09_139L5 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/14/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/11/2016 | Connected |  | N
National Grid | SCITUATE | 177208 | 02066 | 7 |  |  | Solar |  | 05_12_12L2 | 06/06/2016 | 06/06/2016 | 3 | 3 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 06/06/2016 | 6/12/2017 | Y | EXP | 357 | 08/22/2016 | 10/07/2016 | 33 | 0 | 33 | 11/2/2016 | 11/2/2016 | 11/7/2016 | Connected |  | N
National Grid | BROCKTON | 215949 | 02301 | 0 |  |  | Solar |  | 05_07_915W82 | 03/29/2019 | 04/05/2019 | 4 | 0 | 4 | 04/08/2019 | 04/08/2019 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | MILFORD | 389732 | 01757 | 0 |  |  | Other |  | 05_07_797W19 | 11/10/2021 | 01/26/2022 | 51 | 42 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 02/02/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 544198 | 01007 | 10 |  |  | Solar |  | 05_05_335W9 | 10/17/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 178731 | 01532 | 4400 |  |  | Solar |  | 05_09_527L1 | 02/12/2018 | 04/02/2018 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 420767 | 02368 | 15.2 |  |  | Solar |  | 05_05_313W3 | 03/30/2022 | 03/31/2022 | 1 | 0 | 1 | 04/01/2022 | 04/01/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 5/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | N
National Grid | ATTLEBORO | 271946 | 02703 | 15.2 |  |  | Solar |  | 05_07_97W3 | 01/06/2020 | 01/17/2020 | 6 | 6 | 0 | 01/21/2020 | 01/21/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 1/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2020 | Connected |  | N
National Grid | AYER | 494670 | 01432 | 750 |  |  | Solar |  | 05_05_8L3 | 07/05/2023 | 10/30/2023 | 80 | 71 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 01/03/2024 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 628975 | 01036 | 9.28 |  |  | Solar |  | 05_01_201W1 | 10/15/2024 | 11/05/2024 | 8 | 4 | 4 | 11/06/2024 | 11/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/15/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | BEVERLY | 184049 | 01915 | 10.32 |  |  | Solar |  | 05_09_139L5 | 07/02/2018 | 07/02/2018 | 18 | 5 | 13 | 07/27/2018 | 07/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  |  | N | EXP | 476 |  |  | 0 | 0 | 0 |  |  | 11/22/2019 | Connected |  | N
National Grid | SCITUATE | 177385 | 02066 | 7.6 |  |  | Solar |  | 05_12_12L2 | 11/28/2016 | 11/28/2016 | 1 | 1 | 0 | 12/01/2016 | 12/01/2016 | 130 | 0 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 |  | 12/5/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 260128 | 02379 | 9.86 |  |  | Solar |  | 05_07_915W82 | 10/18/2019 | 10/27/2019 | 5 | 0 | 5 | 10/28/2019 | 10/28/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 10/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2020 | Connected |  | N
National Grid | HOPEDALE | 412220 | 01747 | 0 |  |  | Battery Add-On |  | 05_07_797W19 | 03/04/2022 | 04/28/2022 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2022 | 05/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 591098 | 01033 | 7.6 |  |  | Solar |  | 05_05_335W9 | 03/04/2024 | 03/07/2024 | 3 | 0 | 3 | 03/08/2024 | 03/08/2024 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/04/2024 | 5/10/2025 | Y | EXP | 365 | 06/13/2024 | 08/21/2024 | 70 | 0 | 70 |  |  | 11/12/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 184743 | 01532 | 630 |  |  | Solar |  | 05_09_527L1 | 07/03/2018 | 07/03/2018 | 124 | 25 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 437383 | 02368 | 15.2 |  |  | Solar |  | 05_05_313W3 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2022 | Connected |  | N
National Grid | NORTON | 318107 | 02766 | 9.57 |  |  | Solar |  | 05_07_97W3 | 10/08/2020 | 10/19/2020 | 6 | 6 | 0 | 10/20/2020 | 10/20/2020 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | Y
National Grid | AYER | 581441 | 01432 | 0 |  |  | Solar |  | 05_05_8L3 | 01/04/2024 | 01/05/2024 | 1 | 0 | 1 | 01/08/2024 | 01/08/2024 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | WILBRAHAM | 655615 | 01095 | 7.83 |  |  | Solar |  | 05_01_201W1 | 11/20/2024 | 12/04/2024 | 4 | 2 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | BEVERLY | 186850 | 01915 | 7.6 |  |  | Solar |  | 05_09_139L5 | 06/15/2018 | 06/15/2018 | 20 | 17 | 3 | 07/17/2018 | 07/17/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 178243 | 02066 | 15.04 |  |  | Solar |  | 05_12_12L2 | 02/20/2018 | 02/20/2018 | 31 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 291812 | 02301 | 11.4 |  |  | Solar |  | 05_07_915W82 | 05/13/2020 | 06/16/2020 | 22 | 17 | 5 | 06/17/2020 | 06/17/2020 | 148 | 130 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 3/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2022 | Connected |  | N
National Grid | HOPEDALE | 443983 | 01747 | 0 |  |  | Other |  | 05_07_797W19 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 605877 | 01033 | 8.41 |  |  | Solar |  | 05_05_335W9 | 04/23/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 188688 | 01532 | 456 |  |  | Solar |  | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 63 | 44 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 619299 | 02368 | 50 |  |  | Solar |  | 05_05_313W3 | 06/26/2024 | 07/24/2024 | 19 | 12 | 7 | 07/25/2024 | 07/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 11/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 318700 | 02703 | 6 |  |  | Solar |  | 05_07_97W3 | 11/23/2020 | 12/10/2020 | 11 | 9 | 2 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | SHIRLEY | 581408 | 01464 | 0 |  |  | Solar |  | 05_05_8L3 | 01/04/2024 | 01/23/2024 | 13 | 12 | 1 | 01/24/2024 | 01/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2024 | Connected |  | N
National Grid | LONGMEADOW | 665952 | 01028 | 0 |  |  | Other |  | 05_01_201W2 | 02/25/2025 | 03/28/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2025 | 04/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 188147 | 01915 | 7.6 |  |  | Solar |  | 05_09_139L5 | 06/14/2018 | 06/14/2018 | 3 | 3 | 0 | 09/14/2018 | 09/14/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 178383 | 02066 | 15.2 |  |  | Solar |  | 05_12_12L2 | 01/15/2018 | 01/15/2018 | 38 | 13 | 25 | 03/27/2018 | 03/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 |  | 1/21/2019 | N | EXP | 299 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 317813 | 02301 | 15.2 |  |  | Solar |  | 05_07_915W82 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/07/2020 | 2/27/2022 | Y | EXP | 365 | 01/14/2021 | 01/27/2021 | 13 | 0 | 13 |  |  | 12/20/2021 | Connected |  | N
National Grid | HOPEDALE | 443981 | 01747 | 0 |  |  | Other |  | 05_07_797W19 | 11/09/2022 | 01/31/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 618857 | 01033 | 15.2 |  |  | Solar |  | 05_05_335W9 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 188676 | 01532 | 470 |  |  | Solar |  | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/07/2018 | 11/08/2018 | 43 | 3 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 620202 | 02368 | 3.8 |  |  | Solar |  | 05_05_313W3 | 06/24/2024 | 08/13/2024 | 35 | 30 | 5 | 08/14/2024 | 08/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | NORTON | 333373 | 02766 | 9.36 |  |  | Solar |  | 05_07_97W3 | 01/23/2021 | 01/27/2021 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/23/2021 | 4/20/2022 | Y | EXP | 365 | 03/03/2022 | 03/07/2022 | 5 | 0 | 5 |  |  | 3/15/2022 | Connected |  | N
National Grid | AYER | 622204 | 01432 | 6.72 |  |  | Solar |  | 05_05_8L3 | 07/02/2024 | 07/05/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2024 | 07/02/2024 | 11/13/2025 | Y | EXP | 365 | 12/19/2024 | 01/16/2025 | 29 | 0 | 29 |  |  | 1/29/2025 | Connected |  | N
National Grid | LONGMEADOW | 728331 | 01028 | 8.36 |  |  | Solar |  | 05_01_201W2 | 10/22/2025 | 10/27/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 188034 | 01915 | 3.8 |  |  | Solar |  | 05_09_139L5 | 06/15/2018 | 06/15/2018 | 2 | 0 | 2 | 07/03/2018 | 07/03/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2018 | 06/15/2018 | 3/4/2020 | Y | EXP | 572 | 10/17/2019 | 10/30/2019 | 13 | 0 | 13 |  |  | 10/31/2019 | Connected |  | N
National Grid | SCITUATE | 186214 | 02066 | 9.92 |  |  | Solar |  | 05_12_12L2 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 06/25/2018 | 06/25/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  |  | N | EXP | 503 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | BROCKTON | 341765 | 02301 | 15.2 |  |  | Solar |  | 05_07_915W82 | 02/11/2021 | 03/05/2021 | 14 | 13 | 1 | 03/08/2021 | 03/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 479635 | 01757 | 8.064 |  |  | Solar |  | 05_07_797W19 | 03/07/2023 | 03/07/2023 | 0 | 0 | 0 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 668172 | 01033 | 10 |  |  | Solar |  | 05_05_335W9 | 01/27/2025 | 02/20/2025 | 1 | 0 | 1 | 02/21/2025 | 02/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 | 01/27/2025 | 4/1/2026 | Y | EXP | 365 | 09/11/2025 |  | 113 | 0 | 113 |  |  | 12/4/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 188660 | 01532 | 240 |  |  | Solar |  | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 60 | 31 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 11/08/2018 | 77 | 26 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 675814 | 02343 | 5.76 |  |  | Solar |  | 05_05_313W3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | ATTLEBORO | 336483 | 02703 | 10 |  |  | Solar |  | 05_07_97W3 | 01/12/2021 | 01/15/2021 | 2 | 0 | 2 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 625421 | 01432 | 9.86 |  |  | Solar |  | 05_05_8L3 | 07/17/2024 | 07/22/2024 | 4 | 2 | 2 | 07/23/2024 | 07/23/2024 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | Y
National Grid | LONGMEADOW | 730160 | 01028 | 11.78 |  |  | Solar |  | 05_01_201W2 | 10/30/2025 | 11/10/2025 | 6 | 4 | 2 | 11/12/2025 | 11/12/2025 | 38 | 21 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 190514 | 01915 | 9.6 |  |  | Solar |  | 05_09_139L5 | 07/11/2018 | 08/29/2018 | 10 | 0 | 10 | 08/30/2018 | 08/30/2018 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2018 | 07/11/2018 | 10/29/2019 | Y | EXP | 370 | 05/11/2019 | 05/28/2019 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 187345 | 02066 | 3.8 |  |  | Solar |  | 05_12_12L2 | 06/06/2018 | 06/06/2018 | 0 | 0 | 0 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 | 06/06/2018 | 6/24/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2019 | Connected |  | N
National Grid | WEST BRIDGEWATER | 344708 | 02379 | 7.68 |  |  | Solar |  | 05_07_915W82 | 03/02/2021 | 03/08/2021 | 3 | 0 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 494818 | 01757 | 19 |  |  | Solar |  | 05_07_797W19 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 |  | 3/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 669026 | 01432 | 0 |  |  | Battery Add-On |  | 05_05_335W9 | 02/04/2025 | 02/11/2025 | 5 | 1 | 4 | 02/12/2025 | 02/12/2025 | 59 | 36 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 188659 | 01532 | 2376 |  |  | Solar |  | 05_09_527L1 | 06/21/2018 | 06/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 11/08/2018 | 78 | 27 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 684650 | 02343 | 20 |  |  | Solar |  | 05_05_313W3 | 04/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | NORTON | 354572 | 02766 | 3.8 |  |  | Solar |  | 05_07_97W3 | 05/27/2021 | 12/11/2021 | 1 | 0 | 1 | 06/02/2021 | 06/02/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 | 05/27/2021 | 12/11/2022 | Y | EXP | 365 | 12/07/2021 | 12/09/2021 | 3 | 0 | 3 |  |  | 3/17/2022 | Connected |  | N
National Grid | AYER | 629128 | 01432 | 11.5 |  |  | Solar |  | 05_05_8L3 | 08/02/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | LONGMEADOW | 174148 | 01028 | 30 |  |  | Solar |  | 05_01_201W2 | 04/18/2012 | 04/18/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 04/18/2012 | 8/1/2012 | Y | EXP | -133 | 01/10/2013 | 02/27/2013 | 28 | 0 | 28 | 2/20/2013 | 2/20/2013 | 3/11/2013 | Connected |  | N
National Grid | BEVERLY | 218868 | 01915 | 10 |  |  | Solar |  | 05_09_139L5 | 04/11/2019 | 04/11/2019 | 0 | 0 | 0 | 04/12/2019 | 04/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 |  | 8/12/2019 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  | 7/31/2019 | Connected |  | N
National Grid | SCITUATE | 187972 | 02066 | 15.2 |  |  | Solar |  | 05_12_12L2 | 06/13/2018 | 06/13/2018 | 10 | 2 | 8 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 358914 | 02379 | 9.8 |  |  | Solar |  | 05_07_915W82 | 05/18/2021 | 05/20/2021 | 1 | 1 | 0 | 05/21/2021 | 05/21/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 5/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2021 | Connected |  | N
National Grid | HOPEDALE | 534311 | 01747 | 10 |  |  | Solar |  | 05_07_797W19 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 670686 | 01033 | 7.68 |  |  | Solar |  | 05_05_335W9 | 02/07/2025 | 03/26/2025 | 4 | 0 | 4 | 03/27/2025 | 03/27/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 695134 | 01532 | 16.34 |  |  | Solar |  | 05_05_313W3 | 06/02/2025 | 06/05/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2025 | Connected |  | N
National Grid | HOLBROOK | 534192 | 02343 | 5.76 |  |  | Solar |  | 05_07_97W3 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 22 | 0 | 22 | 08/29/2023 | 10/02/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 10/02/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 10/22/2024 | N | EXP | 365 | 12/21/2023 | 02/08/2024 | 49 | 1 | 48 |  |  | 4/15/2024 | Connected |  | N
National Grid | ATTLEBORO | 667705 | 02703 | 10 |  |  | Solar |  | 05_05_8L3 | 01/24/2025 | 02/11/2025 | 6 | 2 | 4 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | AYER | 174259 | 01432 | 217 |  |  | Solar |  | 05_01_201W2 | 02/28/2012 | 02/28/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 224421 | 01028 | 5 |  |  | Solar |  | 05_09_139L5 | 05/07/2019 | 05/15/2019 | 6 | 6 | 0 | 05/16/2019 | 05/16/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/07/2019 | 2/28/2020 | Y | EXP | 269 | 10/25/2019 | 10/30/2019 | 5 | 0 | 5 |  |  | 11/7/2019 | Connected |  | N
National Grid | BEVERLY | 188503 | 01915 | 8.32 |  |  | Solar |  | 05_12_12L2 | 07/23/2018 | 07/30/2018 | 5 | 3 | 2 | 07/31/2018 | 07/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 |  | 8/8/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | Connected |  | N
National Grid | SCITUATE | 375299 | 02066 | 21.17 |  |  | Solar |  | 05_07_915W82 | 08/11/2021 | 08/13/2021 | 3 | 2 | 1 | 08/16/2021 | 08/16/2021 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | WEST BRIDGEWATER | 546935 | 02379 | 0 |  |  | Other |  | 05_07_797W19 | 03/21/2024 | 06/12/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2024 | 07/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 684075 | 01747 | 10 |  |  | Solar |  | 05_05_335W9 | 04/09/2025 | 04/30/2025 | 3 | 0 | 3 | 05/12/2025 | 05/12/2025 | 70 | 55 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | GRANBY | 190067 | 01033 | 5000 |  |  | Solar |  | 05_09_527L1 | 07/18/2018 | 08/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/24/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 714034 | 01532 | 10.15 |  |  | Solar |  | 05_05_313W3 | 08/25/2025 | 09/02/2025 | 4 | 2 | 2 | 09/03/2025 | 09/03/2025 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | RANDOLPH | 535946 | 02368 | 5.76 |  |  | Solar |  | 05_07_97W3 | 07/05/2023 | 07/06/2023 | 2 | 1 | 1 | 07/07/2023 | 07/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 | 07/05/2023 | 8/9/2024 | Y | EXP | 365 | 10/19/2023 | 10/20/2023 | 2 | 0 | 2 |  |  | 10/23/2023 | Connected |  | N
National Grid | ATTLEBORO | 690901 | 02703 | 11.5 |  |  | Solar |  | 05_05_8L3 | 05/09/2025 | 06/18/2025 | 3 | 0 | 3 | 07/09/2025 | 07/09/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 174643 | 01451 | 90 |  |  | Solar |  | 05_01_201W2 | 12/11/2013 | 12/11/2013 | 4 | 0 | 4 | 12/18/2013 | 12/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2014 |  | 1/31/2014 | N | EXP | 24 |  |  | 0 | 0 | 0 | 1/8/2014 | 1/8/2014 | 4/7/2014 | Connected |  | N
National Grid | LONGMEADOW | 223863 | 01028 | 8.74 |  |  | Solar |  | 05_09_139L5 | 06/21/2019 | 06/28/2019 | 4 | 0 | 4 | 07/01/2019 | 07/01/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2019 |  | 6/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2020 | Connected |  | N
National Grid | BEVERLY | 189636 | 01915 | 11.4 |  |  | Solar |  | 05_12_12L2 | 06/29/2018 | 06/29/2018 | 3 | 3 | 0 | 10/10/2018 | 10/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 392732 | 02066 | 5.76 |  |  | Solar |  | 05_07_915W82 | 11/15/2021 | 01/04/2022 | 25 | 20 | 5 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/15/2021 | 5/24/2023 | Y | EXP | 365 | 04/01/2022 | 05/20/2022 | 50 | 0 | 50 |  |  | 6/30/2022 | Connected |  | N
National Grid | BROCKTON | 564779 | 02301 | 6 |  |  | Solar |  | 05_07_797W19 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | HOPEDALE | 697113 | 01747 | 250 |  |  | Solar |  | 05_05_336W1 | 07/17/2025 | 08/26/2025 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRANBY | 190691 | 01033 | 4400 |  |  | Solar |  | 05_09_527L1 | 07/16/2018 | 08/08/2018 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2018 | 10/09/2018 | 44 | 15 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 731390 | 01532 | 3.8 |  |  | Solar |  | 05_05_313W4 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 546998 | 02368 | 11.34 |  |  | Solar |  | 05_07_97W3 | 08/28/2023 | 09/05/2023 | 6 | 5 | 1 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 | 11/21/2023 | 01/05/2024 | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  | 01/05/2024 | 31 | 3 | 28 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 2/11/2025 | N | EXP | 365 | 05/02/2024 | 06/01/2024 | 31 | 0 | 31 |  |  | 6/6/2024 | Connected |  | N
National Grid | ATTLEBORO | 695236 | 02703 | 15.76 |  |  | Solar |  | 05_05_8L3 | 05/30/2025 | 06/03/2025 | 2 | 0 | 2 | 06/04/2025 | 06/04/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | HARVARD | 174833 | 01451 | 210 |  |  | Solar |  | 05_01_201W2 | 08/30/2012 | 08/30/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/12/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 272367 | 01028 | 9.89 |  |  | Solar |  | 05_09_139L5 | 05/07/2020 | 05/28/2020 | 14 | 14 | 0 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/07/2020 | 5/28/2021 | Y | EXP | 365 | 11/14/2020 | 12/10/2020 | 26 | 0 | 26 |  |  | 12/12/2020 | Connected |  | N
National Grid | BEVERLY | 194242 | 01915 | 10 |  |  | Solar |  | 05_12_12L2 | 08/22/2018 | 08/23/2018 | 7 | 6 | 1 | 09/12/2018 | 09/12/2018 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 08/22/2018 | 5/10/2019 | Y | EXP | 233 | 11/30/2018 | 04/12/2019 | 133 | 0 | 133 |  |  | 4/19/2019 | Connected |  | N
National Grid | SCITUATE | 403664 | 02066 | 0 |  |  | Solar |  | 05_07_915W82 | 12/29/2021 | 01/18/2022 | 12 | 9 | 3 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | BROCKTON | 561847 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W19 | 10/24/2023 | 10/27/2023 | 3 | 1 | 2 | 10/30/2023 | 10/30/2023 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2024 | Connected |  | N
National Grid | HOPEDALE | 720890 | 01747 | 5.76 |  |  | Solar |  | 05_05_336W1 | 09/25/2025 | 10/06/2025 | 6 | 3 | 3 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GRANBY | 193939 | 01033 | 2500 |  |  | Solar |  | 05_09_527L1 | 08/20/2018 | 09/17/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 01/26/2019 | 136 | 52 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 174586 | 01532 | 155 |  |  | Solar |  | 05_05_313W4 | 08/30/2011 | 08/30/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2011 |  | 10/31/2012 | N | EXP | 335 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | RANDOLPH | 548813 | 02368 | 10 |  |  | Solar |  | 05_07_97W3 | 08/30/2023 | 09/12/2023 | 9 | 8 | 1 | 09/13/2023 | 09/13/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 08/30/2023 | 11/5/2024 | Y | EXP | 365 | 01/04/2024 | 02/08/2024 | 36 | 0 | 36 |  |  | 2/29/2024 | Connected |  | Y
National Grid | NORTON | 704830 | 02766 | 480 |  |  | Solar |  | 05_05_8L3 | 08/28/2025 |  | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 174832 | 01451 | 260 |  |  | Solar |  | 05_01_201W2 | 08/30/2012 | 08/30/2012 | 6 | 0 | 6 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2013 | 08/30/2012 | 6/27/2014 | Y | EXP | 333 | 05/28/2014 | 07/21/2014 | 36 | 0 | 36 | 6/13/2014 | 6/13/2014 | 6/26/2014 | Connected |  | N
National Grid | LONGMEADOW | 273953 | 01028 | 3984 |  |  | Solar |  | 05_09_139L5 | 10/27/2020 | 01/12/2021 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2021 | 02/09/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 200315 | 01915 | 3.8 |  |  | Solar |  | 05_12_12L2 | 11/05/2018 | 01/28/2019 | 57 | 55 | 2 | 01/29/2019 | 01/29/2019 | 159 | 0 | 159 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 415760 | 02066 | 0 |  |  | Solar |  | 05_07_915W82 | 03/12/2022 | 03/14/2022 | 2 | 1 | 1 | 03/15/2022 | 03/15/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 5/15/2023 | N | EXP | 390 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 625688 | 02301 | 3.8 |  |  | Solar |  | 05_07_797W19 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N
National Grid | HOPEDALE | 174349 | 01747 | 60 |  |  | Solar |  | 05_05_336W1 | 07/24/2012 | 07/24/2012 | 9 | 0 | 9 | 08/06/2012 | 08/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 07/24/2012 | 11/30/2012 | Y | EXP | -12 | 02/05/2013 | 04/11/2013 | 38 | 0 | 38 | 4/22/2013 | 4/22/2013 | 4/23/2013 | Connected |  | N
National Grid | GRANBY | 192330 | 01033 | 11.4 |  |  | Solar |  | 05_09_527L1 | 07/31/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  | 9/14/2020 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 174651 | 01532 | 125 |  |  | Solar |  | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | HOLBROOK | 551665 | 02343 | 7.6 |  |  | Solar |  | 05_07_97W3 | 10/11/2023 | 10/16/2023 | 3 | 0 | 3 | 10/17/2023 | 10/17/2023 | 49 | 28 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 10/11/2023 | 1/29/2025 | Y | EXP | 365 | 04/25/2024 | 08/14/2024 | 112 | 0 | 112 |  |  | 8/23/2024 | Connected |  | N
National Grid | NORTON | 720017 | 02766 | 19 |  |  | Solar |  | 05_05_8L3 | 09/18/2025 | 10/23/2025 | 24 | 20 | 4 | 10/24/2025 | 10/24/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | HARVARD | 175365 | 01451 | 79.2 |  |  | Solar |  | 05_01_201W2 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 | 11/24/2014 | 11/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2014 |  | 4/30/2015 | N | EXP | 150 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 12/9/2015 | Connected |  | N
National Grid | LONGMEADOW | 281671 | 01028 | 9.84 |  |  | Solar |  | 05_09_139L5 | 05/20/2020 | 05/22/2020 | 1 | 0 | 1 | 05/26/2020 | 05/26/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 |  | 5/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2020 | Connected |  | N
National Grid | BEVERLY | 201091 | 01915 | 3.8 |  |  | Solar |  | 05_12_12L2 | 11/14/2018 | 12/10/2018 | 7 | 2 | 5 | 12/11/2018 | 12/11/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 491908 | 02066 | 0 |  |  | Solar |  | 05_07_915W82 | 01/12/2023 | 01/18/2023 | 4 | 1 | 3 | 01/19/2023 | 01/19/2023 | 43 | 23 | 20 | 05/03/2024 | 07/23/2024 | 56 | 9 | 47 |  |  | 0 | 0 | 0 |  | 07/23/2024 | 56 | 9 | 47 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 640558 | 02379 | 7.22 |  |  | Solar |  | 05_07_797W19 | 09/16/2024 | 10/04/2024 | 4 | 1 | 3 | 10/07/2024 | 10/07/2024 | 59 | 38 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | HOPEDALE | 174446 | 01747 | 82 |  |  | Solar |  | 05_05_336W1 | 07/10/2012 | 07/10/2012 | 6 | 0 | 6 | 07/20/2012 | 07/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | -12 |  |  | 0 | 0 | 0 | 10/3/2012 | 10/3/2012 | 12/31/2012 | Connected |  | N
National Grid | GRANBY | 197086 | 01033 | 13.8 |  |  | Solar |  | 05_09_527L1 | 09/27/2018 | 10/30/2018 | 0 | 0 | 0 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 8/30/2019 | N | EXP | 282 |  |  | 0 | 0 | 0 |  |  | 8/12/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 174650 | 01532 | 110 |  |  | Solar |  | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | Y
National Grid | RANDOLPH | 587439 | 02368 | 7.25 |  |  | Solar |  | 05_07_97W3 | 02/09/2024 | 03/07/2024 | 19 | 16 | 3 | 03/08/2024 | 03/08/2024 | 5 | 0 | 5 | 04/29/2024 | 05/02/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 05/02/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 6/1/2025 | N | EXP | 365 | 06/13/2024 | 08/30/2024 | 79 | 0 | 79 |  |  | 10/2/2024 | Connected |  | N
National Grid | ATTLEBORO | 286728 | 02703 | 0 |  |  | Solar |  | 05_05_8L4 | 04/28/2020 | 04/30/2020 | 1 | 0 | 1 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Terminated |  | N
National Grid | AYER | 175355 | 01432 | 200 |  |  | Solar |  | 05_01_201W2 | 09/05/2014 | 09/05/2014 | 7 | 0 | 7 | 09/17/2014 | 09/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2014 |  | 12/31/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 12/17/2014 | 12/17/2014 | 12/18/2014 | Connected |  | N
National Grid | LONGMEADOW | 327143 | 01028 | 11.4 |  |  | Solar |  | 05_09_139L5 | 11/19/2020 | 11/30/2020 | 5 | 1 | 4 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2020 |  | 2/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | BEVERLY | 201284 | 01915 | 180 |  |  | Solar |  | 05_12_12L2 | 11/27/2018 | 11/27/2018 | 0 | 0 | 0 | 11/28/2018 | 11/28/2018 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | SCITUATE | 521120 | 02066 | 15 |  |  | Solar |  | 05_07_915W82 | 07/27/2023 | 08/09/2023 | 9 | 7 | 2 | 08/10/2023 | 08/10/2023 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 12/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2024 | Connected |  | N
National Grid | BROCKTON | 642255 | 02301 | 5.76 |  |  | Solar |  | 05_07_797W19 | 09/23/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/23/2024 | 12/3/2025 | Y | EXP | 365 | 02/26/2025 | 05/16/2025 | 80 | 0 | 80 |  |  | 6/5/2025 | Connected |  | N
National Grid | MILFORD | 174601 | 01757 | 155 |  |  | Solar |  | 05_05_336W1 | 09/22/2011 | 09/22/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2011 |  | 4/5/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 4/5/2012 | Connected |  | N
National Grid | GRANBY | 198592 | 01033 | 5000 |  |  | Solar |  | 05_09_527L1 | 12/06/2018 | 12/22/2018 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 | 01/22/2019 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 174730 | 01532 | 100 |  |  | Solar |  | 05_05_313W4 | 08/22/2012 | 08/22/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/13/2013 | Connected |  | N
National Grid | HOLBROOK | 608653 | 02343 | 10 |  |  | Solar |  | 05_07_97W3 | 05/03/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | NORTON | 660850 | 02766 | 10 |  |  | Solar |  | 05_05_8L4 | 12/16/2024 | 01/21/2025 | 6 | 1 | 5 | 01/22/2025 | 01/22/2025 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 12/16/2024 | 4/21/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HARVARD | 176157 | 01451 | 230 |  |  | Solar |  | 05_01_201W2 | 02/04/2015 | 02/04/2015 | 3 | 1 | 2 | 02/11/2015 | 02/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 |  | 7/31/2015 | N | EXP | 150 |  |  | 0 | 0 | 0 | 7/23/2015 | 7/23/2015 | 8/6/2015 | Connected |  | N
National Grid | HAMPDEN | 335442 | 01036 | 7.875 |  |  | Solar |  | 05_09_139L5 | 01/19/2021 | 01/25/2021 | 3 | 1 | 2 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/19/2021 | 1/24/2022 | Y | EXP | 365 | 05/08/2021 | 05/25/2021 | 17 | 0 | 17 |  |  | 7/13/2021 | Connected |  | N
National Grid | BEVERLY | 203722 | 01915 | 10 |  |  | Solar |  | 05_12_12L2 | 01/01/2019 | 01/10/2019 | 6 | 0 | 6 | 01/11/2019 | 01/11/2019 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 01/01/2019 | 2/18/2020 | Y | EXP | 365 | 05/15/2019 | 05/14/2019 | 0 | 0 | 0 |  |  | 6/6/2019 | Connected |  | N
National Grid | SCITUATE | 534667 | 02066 | 50 |  |  | Solar |  | 05_07_915W82 | 06/29/2023 | 08/24/2023 | 39 | 30 | 9 | 08/25/2023 | 08/25/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  | 4/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | BROCKTON | 656078 | 02301 | 4.55 |  |  | Solar |  | 05_07_797W19 | 11/21/2024 | 12/09/2024 | 5 | 0 | 5 | 12/10/2024 | 12/10/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | MILFORD | 175145 | 01757 | 85 |  |  | Solar |  | 05_05_336W1 | 04/25/2013 | 04/25/2013 | 6 | 0 | 6 | 05/06/2013 | 05/06/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2013 |  | 7/1/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/20/2013 | Connected |  | N
National Grid | GRANBY | 201380 | 01033 | 3000 |  |  | Solar |  | 05_09_527L1 | 12/07/2018 | 01/29/2019 | 100 | 26 | 74 |  |  | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 174769 | 01532 | 110 |  |  | Solar |  | 05_05_313W4 | 08/27/2012 | 08/27/2012 | 10 | 4 | 6 | 09/13/2012 | 09/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | RANDOLPH | 608570 | 02368 | 6.93 |  |  | Solar |  | 05_07_97W3 | 05/03/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 694188 | 02703 | 7.25 |  |  | Solar |  | 05_05_8L4 | 06/05/2025 | 06/11/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 176412 | 01451 | 949.2 |  |  | Solar |  | 05_01_201W2 | 05/10/2016 | 05/10/2016 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2016 | 06/15/2016 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMPDEN | 344559 | 01036 | 6.93 |  |  | Solar |  | 05_09_139L5 | 03/26/2021 | 04/06/2021 | 7 | 7 | 0 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2021 | Connected |  | N
National Grid | BEVERLY | 223495 | 01915 | 11.4 |  |  | Solar |  | 05_12_12L2 | 04/29/2019 | 09/20/2019 | 102 | 101 | 1 | 09/23/2019 | 09/23/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 11/29/2019 | N | EXP | 63 |  |  | 0 | 0 | 0 |  |  | 10/31/2019 | Connected |  | N
National Grid | SCITUATE | 546343 | 02066 | 10.64 |  |  | Solar |  | 05_07_915W82 | 08/18/2023 | 08/28/2023 | 7 | 6 | 1 | 08/29/2023 | 08/29/2023 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | BRIDGEWATER | 673546 | 02379 | 3.8 |  |  | Solar |  | 05_07_797W19 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 175407 | 01757 | 170 |  |  | Solar |  | 05_05_336W1 | 03/04/2014 | 03/04/2014 | 6 | 0 | 6 | 03/13/2014 | 03/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2014 |  | 9/30/2014 | N | EXP | 182 |  |  | 0 | 0 | 0 | 5/13/2014 | 5/13/2014 | 10/21/2014 | Connected |  | N
National Grid | GRANBY | 201291 | 01033 | 3000 |  |  | Solar |  | 05_09_527L1 | 12/12/2018 | 02/22/2019 | 84 | 63 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/25/2019 | 03/20/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 175199 | 01752 | 125 |  |  | Solar |  | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | -115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | Y
National Grid | HOLBROOK | 622060 | 02343 | 7.6 |  |  | Solar |  | 05_07_97W3 | 07/23/2024 | 09/06/2024 | 9 | 8 | 1 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 696851 | 02766 | 11.5 |  |  | Solar |  | 05_05_8L4 | 06/06/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AYER | 176517 | 01432 | 80 |  |  | Solar |  | 05_01_201W2 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 10/11/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 12/29/2015 | 12/29/2015 | 12/29/2015 | Connected |  | N
National Grid | LONGMEADOW | 430108 | 01028 | 9.86 |  |  | Solar |  | 05_09_139L5 | 10/21/2022 | 05/20/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  | 11/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2023 | Connected |  | N
National Grid | BEVERLY | 594641 | 01915 | 23 |  |  | Solar |  | 05_07_915W82 | 03/05/2024 | 03/07/2024 | 2 | 0 | 2 | 03/08/2024 | 03/08/2024 | 27 | 23 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | SCITUATE | 692435 | 02066 | 3.8 |  |  | Solar |  | 05_07_797W19 | 05/23/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175585 | 02301 | 170 |  |  | Solar |  | 05_05_336W1 | 04/24/2014 | 04/24/2014 | 3 | 0 | 3 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 | 04/24/2014 | 10/31/2014 | Y | EXP | 171 |  |  | 0 | 0 | 0 | 5/13/2014 | 5/13/2014 | 2/17/2015 | Connected |  | N
National Grid | MILFORD | 176206 | 01757 | 15.6 |  |  | Solar |  | 05_05_313W4 | 04/24/2015 | 04/24/2015 | 6 | 6 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 8/31/2015 | N | EXP | 111 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | GRANBY | 630075 | 01033 | 3.15 |  |  | Solar |  | 05_07_97W3 | 08/05/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/05/2024 | 9/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | MARLBOROUGH | 710661 | 01752 | 11.5 |  |  | Solar |  | 05_05_8L4 | 08/08/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 176553 | 02368 | 6 |  |  | Solar |  | 05_01_201W2 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2015 |  | 10/13/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 6/3/2016 | Connected |  | N
National Grid | REHOBOTH | 460692 | 02769 | 14.79 |  |  | Solar |  | 05_09_139L5 | 10/06/2022 | 10/10/2022 | 2 | 0 | 2 | 10/11/2022 | 10/11/2022 | 52 | 37 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | HARVARD | 262763 | 01451 | 10 |  |  | Solar |  | 05_12_12L2 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/29/2019 | 10/21/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | LONGMEADOW | 601761 | 01028 | 0 |  |  | Solar |  | 05_07_915W82 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 521068 | 01915 | 495.7 |  |  | Solar |  | 05_07_797W20 | 11/02/2023 | 01/19/2024 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 02/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SCITUATE | 175785 | 02066 | 42 |  |  | Solar |  | 05_05_336W1 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 8/1/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 2/18/2016 | 2/18/2016 | 2/19/2016 | Connected |  | N
National Grid | WEST BRIDGEWATER | 219076 | 02379 | 2.88 |  |  | Solar |  | 05_09_527L1 | 07/15/2019 | 07/30/2019 | 10 | 3 | 7 | 07/31/2019 | 07/31/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 2/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 176862 | 01757 | 10 |  |  | Solar |  | 05_05_313W4 | 01/21/2016 | 01/21/2016 | 3 | 3 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 7/19/2016 | Connected |  | N
National Grid | GRANBY | 639504 | 01033 | 10 |  |  | Solar |  | 05_07_97W3 | 09/11/2024 | 12/04/2024 | 46 | 45 | 1 | 12/05/2024 | 12/05/2024 | 51 | 25 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 709735 | 01752 | 10 |  |  | Solar |  | 05_05_8L4 | 08/05/2025 | 08/25/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/05/2025 | 11/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | HOLBROOK | 176586 | 02343 | 236 |  |  | Solar |  | 05_01_201W2 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 10/19/2016 | 4/16/2017 | Y | EXP | 100 |  |  | 0 | 0 | 0 | 1/10/2017 | 1/10/2017 | 1/4/2018 | Connected |  | N
National Grid | ATTLEBORO | 486713 | 02703 | 7.83 |  |  | Solar |  | 05_09_139L5 | 12/28/2022 | 01/03/2023 | 3 | 1 | 2 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/28/2022 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | AYER | 281100 | 01434 | 7.6 |  |  | Solar |  | 05_12_12L2 | 03/04/2020 | 03/12/2020 | 6 | 6 | 0 | 03/13/2020 | 03/13/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2020 | 03/04/2020 | 3/12/2021 | Y | EXP | 365 | 09/18/2020 | 09/28/2020 | 10 | 0 | 10 |  |  | 11/4/2020 | Connected |  | N
National Grid | LONGMEADOW | 670840 | 01028 | 7.6 |  |  | Solar |  | 05_07_915W82 | 02/07/2025 | 03/17/2025 | 3 | 0 | 3 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | BEVERLY | 581189 | 01915 | 240 |  |  | Solar |  | 05_07_797W20 | 01/09/2024 | 01/16/2024 | 4 | 0 | 4 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SCITUATE | 175970 | 02066 | 56 |  |  | Solar |  | 05_05_336W1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 08/11/2015 | 8/17/2015 | Y | EXP | -8 | 12/16/2015 | 03/11/2016 | 58 | 0 | 58 | 2/9/2016 | 2/9/2016 | 3/28/2016 | Connected |  | N
National Grid | WEST BRIDGEWATER | 218290 | 02379 | 0 |  |  | Solar |  | 05_09_527L1 | 04/09/2019 | 05/13/2019 | 23 | 16 | 7 | 05/14/2019 | 05/14/2019 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2019 | Connected |  | N
National Grid | MILFORD | 177487 | 01757 | 5.2 |  |  | Solar |  | 05_05_313W4 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 |  | 10/1/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/12/2017 | Connected |  | N
National Grid | GRANBY | 643251 | 01033 | 4.8 |  |  | Solar |  | 05_07_97W3 | 09/27/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 721493 | 01752 | 10 |  |  | Solar |  | 05_05_8L4 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 10/09/2025 | 11/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | RANDOLPH | 206095 | 02368 | 10 |  |  | Solar |  | 05_01_201W2 | 02/04/2019 | 02/07/2019 | 2 | 2 | 0 | 02/08/2019 | 02/08/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 7/19/2019 | N | EXP | 140 |  |  | 0 | 0 | 0 |  |  | 7/10/2019 | Connected |  | N
National Grid | REHOBOTH | 502131 | 02769 | 0 |  |  | Solar |  | 05_09_139L5 | 02/27/2023 | 03/01/2023 | 3 | 2 | 1 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 4/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | AYER | 295936 | 01432 | 3.8 |  |  | Solar |  | 05_12_12L2 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/19/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 682654 | 01028 | 22.8 |  |  | Solar |  | 05_07_915W82 | 04/21/2025 | 05/08/2025 | 12 | 8 | 4 | 05/09/2025 | 05/09/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | BEVERLY | 676982 | 01915 | 750 |  |  | Solar |  | 05_07_797W20 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SCITUATE | 178537 | 02066 | 486 |  |  | Solar |  | 05_05_336W1 | 01/25/2018 | 01/25/2018 | 24 | 0 | 24 | 03/05/2018 | 03/05/2018 | 103 | 0 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 258757 | 02301 | 7.6 |  |  | Solar |  | 05_09_527L1 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/07/2019 | 10/7/2020 | Y | EXP | 365 | 06/02/2020 | 06/03/2020 | 1 | 0 | 1 |  |  | 7/23/2020 | Connected |  | N
National Grid | MILFORD | 186922 | 01757 | 230 |  |  | Solar |  | 05_05_313W4 | 06/01/2018 | 06/01/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  | 12/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | GRANBY | 644166 | 01033 | 10 |  |  | Solar |  | 05_07_97W3 | 10/02/2024 | 10/17/2024 | 2 | 0 | 2 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 726585 | 01752 | 0 |  |  | Solar |  | 05_05_8L4 | 11/05/2025 | 11/10/2025 | 3 | 1 | 2 | 11/12/2025 | 11/12/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HOLBROOK | 207974 | 02343 | 9.8 |  |  | Solar |  | 05_01_201W2 | 08/20/2019 | 10/30/2019 | 49 | 47 | 2 | 10/31/2019 | 10/31/2019 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 08/20/2019 | 11/18/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | REHOBOTH | 514196 | 02769 | 0 |  |  | Solar |  | 05_09_139L5 | 03/27/2023 | 03/31/2023 | 5 | 4 | 1 | 04/03/2023 | 04/03/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 324809 | 01432 | 8.64 |  |  | Solar |  | 05_12_12L2 | 12/21/2020 | 01/06/2021 | 10 | 10 | 0 | 01/07/2021 | 01/07/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/21/2020 | 1/5/2022 | Y | EXP | 365 | 07/09/2021 | 07/15/2021 | 7 | 0 | 7 |  |  | 8/5/2021 | Connected |  | N
National Grid | LONGMEADOW | 646496 | 01028 | 3.8 |  |  | Solar |  | 05_07_91W40 | 12/17/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 683042 | 01915 | 10 |  |  | Solar |  | 05_07_797W20 | 04/07/2025 | 04/30/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SCITUATE | 188185 | 02066 | 249.8 |  |  | Solar |  | 05_05_336W1 | 06/15/2018 | 06/15/2018 | 7 | 0 | 7 | 07/02/2018 | 07/02/2018 | 20 | 19 | 1 | 08/03/2018 | 11/01/2018 | 63 | 43 | 20 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 63 | 43 | 20 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 4/14/2020 | N | EXP | 510 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 291194 | 02301 | 1.92 |  |  | Solar |  | 05_09_527L1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 189709 | 01757 | 381.5 |  |  | Natural Gas |  | 05_05_313W4 | 07/03/2018 | 07/03/2018 | 32 | 23 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 5/13/2020 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | GRANBY | 646249 | 01033 | 7.6 |  |  | Solar |  | 05_07_97W3 | 10/17/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 10/17/2024 | 1/28/2026 | Y | EXP | 365 | 04/30/2025 | 06/18/2025 | 50 | 0 | 50 |  |  | 7/7/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 734048 | 01532 | 13.36 |  |  | Solar |  | 05_05_8L4 | 11/17/2025 | 11/18/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 243831 | 02368 | 6.38 |  |  | Solar |  | 05_01_201W2 | 07/31/2019 | 08/01/2019 | 0 | 0 | 0 | 08/02/2019 | 08/02/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 07/31/2019 | 11/15/2019 | Y | EXP | 94 | 09/25/2019 | 10/02/2019 | 7 | 0 | 7 |  |  | 10/25/2019 | Connected |  | N
National Grid | ATTLEBORO | 567007 | 02703 | 10 |  |  | Solar |  | 05_09_139L5 | 11/08/2023 |  | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 330235 | 01432 | 7.6 |  |  | Solar |  | 05_12_12L2 | 12/07/2020 | 02/05/2021 | 40 | 38 | 2 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 655817 | 01028 | 5.76 |  |  | Solar |  | 05_07_91W40 | 11/20/2024 | 01/15/2025 | 19 | 13 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BEVERLY | 718781 | 01915 | 12.16 |  |  | Solar |  | 05_07_797W20 | 09/12/2025 | 11/04/2025 | 1 | 0 | 1 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SCITUATE | 260025 | 02066 | 250 |  |  | Solar |  | 05_05_336W1 | 02/11/2020 | 11/04/2019 | 12 | 11 | 1 | 11/05/2019 | 11/05/2019 | 81 | 34 | 47 | 03/30/2020 | 08/05/2020 | 91 | 1 | 90 |  |  | 0 | 0 | 0 |  | 08/05/2020 | 91 | 1 | 90 |  |  | 0 | 0 | 0 | 9/2/2020 |  | 9/7/2022 | N | EXP | 365 | 08/24/2021 | 08/23/2021 | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | WEST BRIDGEWATER | 293669 | 02379 | 0 |  |  | Other |  | 05_09_527L1 | 01/05/2021 |  | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 191688 | 01757 | 133.2 |  |  | Solar |  | 05_05_313W4 | 07/24/2018 | 09/05/2018 | 26 | 17 | 9 | 09/06/2018 | 09/06/2018 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 656845 | 01033 | 5.76 |  |  | Solar |  | 05_07_97W3 | 11/26/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 736729 | 01532 | 5.76 |  |  | Solar |  | 05_05_8L4 | 11/26/2025 | 12/02/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HOLBROOK | 247186 | 02343 | 15.2 |  |  | Solar |  | 05_01_201W2 | 08/06/2019 | 08/07/2019 | 0 | 0 | 0 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 08/06/2019 | 5/1/2020 | Y | EXP | 259 | 10/29/2019 | 11/07/2019 | 9 | 0 | 9 |  |  | 1/14/2020 | Connected |  | N
National Grid | ATTLEBORO | 582369 | 02703 | 15.2 |  |  | Solar |  | 05_09_139L5 | 01/09/2024 | 01/29/2024 | 14 | 12 | 2 | 01/30/2024 | 01/30/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | AYER | 358932 | 01432 | 10 |  |  | Solar |  | 05_12_12L2 | 05/18/2021 | 05/24/2021 | 3 | 3 | 0 | 05/25/2021 | 05/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 7/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | LONGMEADOW | 699180 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 10/01/2025 | 10/13/2025 | 5 | 0 | 5 | 11/04/2025 | 11/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 735664 | 01915 | 5.76 |  |  | Solar |  | 05_07_797W20 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SCITUATE | 259098 | 02066 | 233.2 |  |  | Solar |  | 05_05_336W1 | 10/09/2019 | 10/23/2019 | 6 | 3 | 3 | 10/24/2019 | 10/24/2019 | 45 | 20 | 25 | 02/14/2020 | 04/22/2020 | 46 | 13 | 33 |  |  | 0 | 0 | 0 |  | 04/22/2020 | 46 | 13 | 33 |  |  | 0 | 0 | 0 | 6/4/2020 |  | 12/31/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 300661 | 02333 | 6.72 |  |  | Solar |  | 05_09_527L1 | 07/10/2020 | 10/22/2020 | 72 | 27 | 45 | 10/23/2020 | 10/23/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 2/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2021 | Connected |  | N
National Grid | MILFORD | 285220 | 01757 | 15.2 |  |  | Solar |  | 05_05_313W4 | 03/25/2020 | 03/30/2020 | 2 | 0 | 2 | 03/31/2020 | 03/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | GRANBY | 661823 | 01033 | 7.6 |  |  | Solar |  | 05_07_97W3 | 12/24/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/24/2024 | 4/5/2026 | Y | EXP | 365 | 05/07/2025 | 11/05/2025 | 183 | 0 | 183 |  |  | 1/6/2026 | Connected |  | Y
National Grid | NORTHBOROUGH | 742489 | 01532 | 23 |  |  | Solar |  | 05_05_8L4 | 12/29/2025 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 279637 | 02368 | 10.44 |  |  | Solar |  | 05_01_201W2 | 02/14/2020 | 03/06/2020 | 14 | 14 | 0 | 03/09/2020 | 03/09/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  | 3/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2020 | Connected |  | N
National Grid | REHOBOTH | 601540 | 02769 | 7.6 |  |  | Solar |  | 05_09_139L5 | 04/05/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 | 04/05/2024 | 5/14/2025 | Y | EXP | 365 | 08/09/2024 | 08/20/2024 | 12 | 0 | 12 |  |  | 10/4/2024 | Connected |  | N
National Grid | HARVARD | 361035 | 01451 | 3.8 |  |  | Solar |  | 05_12_12L2 | 06/11/2021 | 06/16/2021 | 3 | 0 | 3 | 06/17/2021 | 06/17/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 711584 | 01028 | 5.76 |  |  | Solar |  | 05_07_91W40 | 08/12/2025 | 10/29/2025 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BEVERLY | 177426 | 01915 | 7.6 |  |  | Solar |  | 05_07_797W20 | 02/27/2017 | 02/27/2017 | 6 | 6 | 0 | 03/08/2017 | 03/08/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 3/5/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | Connected |  | N
National Grid | SCITUATE | 390062 | 02066 | 9.8 |  |  | Solar |  | 05_05_336W1 | 11/11/2021 | 02/02/2022 | 56 | 53 | 3 | 02/03/2022 | 02/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 | 11/11/2021 | 1/2/2024 | Y | EXP | 365 | 05/25/2022 | 12/21/2022 | 211 | 0 | 211 |  |  | 1/13/2023 | Connected |  | N
National Grid | WEST BRIDGEWATER | 307066 | 02379 | 150 |  |  | Solar |  | 05_09_527L1 | 08/18/2020 | 09/16/2020 | 19 | 12 | 7 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 286585 | 01757 | 250 |  |  | Solar |  | 05_05_313W4 | 04/07/2020 | 04/11/2020 | 2 | 0 | 2 | 04/13/2020 | 04/13/2020 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2020 |  | 6/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2021 | Connected |  | N
National Grid | GRANBY | 667503 | 01033 | 8.99 |  |  | Solar |  | 05_07_97W3 | 01/28/2025 | 02/25/2025 | 8 | 4 | 4 | 02/26/2025 | 02/26/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 5/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174866 | 01752 | 2000 |  |  | Solar |  | 05_05_8L4 | 08/02/2012 | 08/02/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/15/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2013 | 08/02/2012 | 7/1/2013 | Y | STD | 42 | 10/17/2013 | 12/19/2013 | 43 | 0 | 43 | 12/16/2013 | 12/16/2013 | 12/23/2013 | Connected |  | N
National Grid | RANDOLPH | 282114 | 02368 | 66.6 |  |  | Solar |  | 05_01_201W2 | 07/21/2020 | 08/12/2020 | 15 | 9 | 6 | 08/13/2020 | 08/13/2020 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 07/21/2020 | 4/29/2022 | Y | EXP | 336 |  |  | 0 | 0 | 0 |  |  | 4/29/2022 | Connected |  | N
National Grid | ATTLEBORO | 625890 | 02703 | 9.765 |  |  | Solar |  | 05_09_139L5 | 08/14/2024 | 08/21/2024 | 6 | 3 | 3 | 10/10/2024 | 10/10/2024 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | HARVARD | 378451 | 01451 | 11.4 |  |  | Solar |  | 05_12_12L2 | 08/27/2021 | 08/31/2021 | 2 | 0 | 2 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 3/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | LONGMEADOW | 176888 | 01028 | 0 |  |  | Solar |  | 05_07_91W40 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 |  | 11/18/2016 | N | EXP | 350 |  |  | 0 | 0 | 0 | 12/4/2015 | 12/4/2015 |  | Withdrawn |  | Y
National Grid | BEVERLY | 177657 | 01915 | 1000 |  |  | Solar |  | 05_07_797W20 | 11/10/2017 | 11/10/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2017 | 01/12/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 11/19/2018 | N | STD | 159 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 408869 | 02302 | 0 |  |  | Battery Add-On |  | 05_05_336W1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 11/22/2022 | 190 | 183 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 311886 | 02379 | 8.4 |  |  | Solar |  | 05_09_527L1 | 10/20/2020 | 11/03/2020 | 1 | 0 | 1 | 11/04/2020 | 11/04/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 10/20/2020 | 6/4/2022 | Y | EXP | 365 | 06/25/2021 | 08/02/2021 | 38 | 0 | 38 |  |  | 12/20/2021 | Connected |  | N
National Grid | MILFORD | 326590 | 01757 | 11.4 |  |  | Solar |  | 05_05_313W4 | 11/17/2020 | 11/20/2020 | 2 | 0 | 2 | 11/23/2020 | 11/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/17/2020 | 9/9/2022 | Y | EXP | 365 | 06/12/2021 | 08/31/2021 | 80 | 3 | 77 |  |  | 9/13/2021 | Connected |  | N
National Grid | GRANBY | 680640 | 01033 | 10 |  |  | Solar |  | 05_07_97W3 | 03/26/2025 | 04/10/2025 | 20 | 19 | 1 | 06/02/2025 | 06/02/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 03/26/2025 | 7/9/2026 | Y | EXP | 365 | 08/29/2025 | 11/21/2025 | 85 | 0 | 85 |  |  | 11/25/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175839 | 01752 | 17.4 |  |  | Solar |  | 05_05_8L4 | 03/04/2015 | 03/04/2015 | 5 | 1 | 4 | 03/12/2015 | 03/12/2015 | 351 | 0 | 351 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 |  | 7/31/2015 | N | EXP | 140 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 283144 | 02368 | 7.6 |  |  | Solar |  | 05_01_201W2 | 03/11/2020 | 04/30/2020 | 34 | 26 | 8 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 3/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2020 | Connected |  | N
National Grid | REHOBOTH | 627240 | 02769 | 0 |  |  | Solar |  | 05_09_139L5 | 07/24/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | N
National Grid | HARVARD | 378053 | 01451 | 15.2 |  |  | Solar |  | 05_12_12L2 | 08/25/2021 | 08/26/2021 | 1 | 0 | 1 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2022 | Connected |  | N
National Grid | LONGMEADOW | 178279 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 02/23/2018 | 02/23/2018 | 5 | 5 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 9/16/2020 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 7/18/2020 | Connected |  | N
National Grid | BEVERLY | 189857 | 01915 | 999 |  |  | Solar |  | 05_07_797W20 | 07/16/2018 | 08/27/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 03/09/2020 | 186 | 4 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2019 |  | 4/29/2021 | N | STD | 658 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 571863 | 02302 | 9.86 |  |  | Solar |  | 05_05_336W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 12/07/2023 | 3/8/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 9/13/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 322287 | 02379 | 5 |  |  | Solar |  | 05_09_527L1 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2021 | Connected |  | N
National Grid | MILFORD | 346371 | 01757 | 250 |  |  | Solar |  | 05_05_313W4 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/30/2021 | 04/30/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 684881 | 01033 | 10 |  |  | Solar |  | 05_07_97W3 | 04/14/2025 | 05/08/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 14 | 0 | 14 | 06/05/2025 | 06/04/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/04/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/14/2025 | 6/16/2026 | Y | EXP | 365 | 11/04/2025 | 12/01/2025 | 28 | 0 | 28 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176040 | 01752 | 10 |  |  | Solar |  | 05_05_8L4 | 08/13/2015 | 08/13/2015 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 292576 | 02343 | 3.8 |  |  | Solar |  | 05_01_201W2 | 07/09/2020 | 07/17/2020 | 5 | 0 | 5 | 07/20/2020 | 07/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 631614 | 02769 | 5.76 |  |  | Solar |  | 05_09_139L5 | 08/09/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/09/2024 | 10/11/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/11/2025 | Connected |  | Y
National Grid | HARVARD | 378580 | 01451 | 9.8 |  |  | Solar |  | 05_12_12L2 | 08/30/2021 | 09/10/2021 | 9 | 8 | 1 | 09/13/2021 | 09/13/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 11/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2022 | Connected |  | N
National Grid | LONGMEADOW | 196383 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 09/19/2018 | 11/20/2018 | 23 | 23 | 0 | 11/21/2018 | 11/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 198658 | 01915 | 433.3 |  |  | Solar |  | 05_07_797W20 | 11/01/2018 | 11/07/2018 | 3 | 0 | 3 | 11/08/2018 | 11/08/2018 | 37 | 23 | 14 | 01/10/2019 | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  | 03/11/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 | 3/25/2019 |  | 1/2/2021 | N | EXP | 649 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 735490 | 02302 | 5.76 |  |  | Solar |  | 05_05_336W2 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 323927 | 02379 | 7.6 |  |  | Solar |  | 05_09_527L1 | 11/05/2020 | 11/24/2020 | 12 | 10 | 2 | 11/25/2020 | 11/25/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | MILFORD | 471917 | 01757 | 3.8 |  |  | Solar |  | 05_05_313W4 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 705472 | 01033 | 5.76 |  |  | Solar |  | 05_07_97W3 | 07/17/2025 | 08/01/2025 | 4 | 0 | 4 | 08/13/2025 | 08/13/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176062 | 01532 | 28.8 |  |  | Solar |  | 05_05_8L4 | 03/31/2015 | 03/31/2015 | 4 | 1 | 3 | 04/07/2015 | 04/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2015 |  | 7/31/2015 | N | EXP | 114 |  |  | 0 | 0 | 0 | 9/23/2015 | 9/23/2015 | 9/28/2015 | Connected |  | N
National Grid | RANDOLPH | 293316 | 02368 | 7.6 |  |  | Solar |  | 05_01_201W2 | 05/27/2020 | 06/03/2020 | 4 | 0 | 4 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | ATTLEBORO | 637722 | 02703 | 3000 |  |  | Solar |  | 05_09_139L5 | 02/13/2025 |  | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 382439 | 01451 | 10 |  |  | Solar |  | 05_12_12L2 | 09/17/2021 | 11/17/2021 | 42 | 40 | 2 | 11/18/2021 | 11/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 1/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | LONGMEADOW | 248607 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 08/13/2019 | 09/04/2019 | 3 | 0 | 3 | 09/05/2019 | 09/05/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 | 08/13/2019 | 9/30/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | BEVERLY | 292016 | 01915 | 7.83 |  |  | Solar |  | 05_07_797W20 | 05/27/2020 | 06/03/2020 | 4 | 0 | 4 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | BROCKTON | 174788 | 02302 | 26.5 |  |  | Solar |  | 05_05_336W2 | 06/09/2011 | 06/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2011 | 06/09/2011 | 1/23/2012 | Y | EXP | 180 | 12/29/2011 | 01/18/2012 | 12 | 0 | 12 | 8/7/2012 | 8/7/2012 | 1/23/2012 | Connected |  | N
National Grid | BRIDGEWATER | 364394 | 02333 | 19 |  |  | Solar |  | 05_09_527L1 | 06/16/2021 | 06/17/2021 | 2 | 1 | 1 | 06/18/2021 | 06/18/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2021 | Connected |  | N
National Grid | MILFORD | 483268 | 01757 | 10 |  |  | Solar |  | 05_05_313W4 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 28 | 4 | 24 | 02/06/2023 | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/25/2024 | N | EXP | 365 | 04/08/2023 | 04/26/2023 | 19 | 0 | 19 |  |  | 7/20/2023 | Connected |  | N
National Grid | GRANBY | 712872 | 01033 | 10 |  |  | Solar |  | 05_07_97W3 | 08/18/2025 | 09/11/2025 | 6 | 2 | 4 | 09/25/2025 | 09/25/2025 | 20 | 4 | 16 | 10/30/2025 | 12/09/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 12/09/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 176455 | 01532 | 7.6 |  |  | Solar |  | 05_05_8L4 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 12/08/2015 | 12/14/2016 | Y | EXP | 356 | 10/05/2016 | 10/11/2016 | 3 | 0 | 3 | 11/1/2016 | 11/1/2016 | 11/8/2016 | Connected |  | N
National Grid | RANDOLPH | 298159 | 02368 | 10 |  |  | Solar |  | 05_01_201W2 | 06/26/2020 | 07/07/2020 | 6 | 1 | 5 | 07/08/2020 | 07/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | REHOBOTH | 640515 | 02769 | 4.93 |  |  | Solar |  | 05_09_139L5 | 09/16/2024 | 11/19/2024 | 38 | 34 | 4 | 11/20/2024 | 11/20/2024 | 70 | 48 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 09/16/2024 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | AYER | 422071 | 01432 | 0 |  |  | Battery Add-On |  | 05_12_12L2 | 05/19/2022 | 08/11/2022 | 56 | 48 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 281490 | 01028 | 6 |  |  | Solar |  | 05_07_91W40 | 05/22/2020 | 05/27/2020 | 1 | 0 | 1 | 05/28/2020 | 05/28/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/22/2020 | 5/12/2022 | Y | EXP | 365 | 08/12/2021 | 08/28/2021 | 15 | 3 | 12 |  |  | 9/13/2021 | Connected |  | N
National Grid | BEVERLY | 337504 | 01915 | 150 |  |  | Solar |  | 05_07_797W20 | 01/26/2021 | 02/03/2021 | 5 | 0 | 5 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 | 04/12/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  | 07/13/2021 | 48 | 0 | 48 |  |  | 0 | 0 | 0 | 7/6/2021 | 01/26/2021 | 11/25/2022 | Y | EXP | 273 | 02/05/2022 | 07/11/2022 | 158 | 119 | 39 |  |  | 12/6/2022 | Connected |  | N
National Grid | BROCKTON | 412214 | 02302 | 0 |  |  | Battery Add-On |  | 05_05_336W2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/08/2022 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 369951 | 02379 | 996 |  |  | Solar |  | 05_09_527L1 | 08/25/2021 |  | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 521440 | 01757 | 6.175 |  |  | Solar |  | 05_05_313W4 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 78 | 57 | 21 | 10/11/2023 | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 | 03/26/2024 | 04/11/2024 | 17 | 0 | 17 |  |  | 5/3/2024 | Connected |  | N
National Grid | BELCHERTOWN | 651128 | 01007 | 10 |  |  | Solar |  | 05_07_97W4 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 60 | 36 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 11/12/2024 | 5/3/2026 | Y | EXP | 365 | 10/04/2025 |  | 90 | 21 | 69 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 176625 | 01532 | 10 |  |  | Solar |  | 05_05_8L4 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2016 |  | 4/24/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/18/2016 | 10/21/2016 | Connected |  | N
National Grid | HOLBROOK | 311609 | 02343 | 10 |  |  | Solar |  | 05_01_201W2 | 09/09/2020 | 09/10/2020 | 0 | 0 | 0 | 09/11/2020 | 09/11/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2020 |  | 9/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | REHOBOTH | 651816 | 02769 | 1.45 |  |  | Solar |  | 05_09_139L5 | 11/04/2024 | 11/25/2024 | 6 | 1 | 5 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/14/2026 | Y | EXP | 365 | 02/12/2025 | 02/15/2025 | 4 | 0 | 4 |  |  | 4/3/2025 | Connected |  | N
National Grid | HARVARD | 464712 | 01451 | 7.6 |  |  | Solar |  | 05_12_12L2 | 10/03/2022 | 10/06/2022 | 3 | 0 | 3 | 10/07/2022 | 10/07/2022 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/03/2022 | 5/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2023 | Connected |  | N
National Grid | LONGMEADOW | 315002 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/26/2020 |  | Y | EXP | 365 | 02/18/2021 | 02/24/2021 | 5 | 0 | 5 |  |  | 3/10/2021 | Connected |  | N
National Grid | BEVERLY | 378348 | 01915 | 0 |  |  | Solar |  | 05_07_797W20 | 08/26/2021 | 08/27/2021 | 1 | 0 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 3/6/2023 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 529975 | 02302 | 950 |  |  | Solar |  | 05_05_336W2 | 01/29/2024 | 05/16/2024 | 76 | 66 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 05/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 398685 | 02379 | 9.84 |  |  | Solar |  | 05_09_527L1 | 12/01/2021 | 12/02/2021 | 1 | 0 | 1 | 12/03/2021 | 12/03/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 12/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N
National Grid | MILFORD | 540566 | 01757 | 480 |  |  | Solar |  | 05_05_313W4 | 09/18/2023 | 12/06/2023 | 54 | 46 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/07/2023 | 02/21/2024 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 665647 | 01033 | 7.6 |  |  | Solar |  | 05_07_97W4 | 01/16/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/16/2025 | 6/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MARLBOROUGH | 177068 | 01752 | 15.2 |  |  | Solar |  | 05_05_8L4 | 03/21/2017 | 03/21/2017 | 7 | 6 | 1 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/26/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/26/2017 | Connected |  | N
National Grid | RANDOLPH | 329550 | 02368 | 10 |  |  | Solar |  | 05_01_201W2 | 12/10/2020 | 12/14/2020 | 1 | 0 | 1 | 12/15/2020 | 12/15/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2021 | Connected |  | N
National Grid | NORTON | 653444 | 02766 | 10 |  |  | Solar |  | 05_09_139L5 | 11/11/2024 | 12/19/2024 | 13 | 12 | 1 | 12/20/2024 | 12/20/2024 | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 11/11/2024 | 4/3/2026 | Y | EXP | 365 | 10/04/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 10/30/2025 | Connected |  | N
National Grid | AYER | 466433 | 01432 | 6 |  |  | Solar |  | 05_12_12L2 | 10/12/2022 | 10/13/2022 | 1 | 0 | 1 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 392439 | 01028 | 7.6 |  |  | Solar |  | 05_07_91W40 | 11/23/2021 | 01/03/2022 | 9 | 3 | 6 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 6/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2022 | Connected |  | N
National Grid | BEVERLY | 389737 | 01915 | 0 |  |  | Other |  | 05_07_797W20 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 529971 | 02302 | 950 |  |  | Solar |  | 05_05_336W2 | 09/21/2023 | 03/14/2024 | 119 | 109 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2024 | 05/29/2024 | 52 | 41 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 | 09/21/2023 | 1/6/2026 | Y | STD | 343 | 09/25/2025 | 12/19/2025 | 86 | 14 | 72 |  |  | 12/31/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 448872 | 02379 | 10 |  |  | Solar |  | 05_09_527L1 | 08/31/2022 | 09/01/2022 | 1 | 0 | 1 | 09/02/2022 | 09/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 10/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2022 | Connected |  | N
National Grid | MILFORD | 551451 | 01757 | 250 |  |  | Solar |  | 05_05_313W4 | 09/18/2023 | 12/26/2023 | 67 | 58 | 9 | 12/27/2023 | 12/27/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/20/2026 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | GRANBY | 725062 | 01033 | 5.76 |  |  | Solar |  | 05_07_97W4 | 10/08/2025 | 10/27/2025 | 11 | 10 | 1 | 10/28/2025 | 10/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 177099 | 01532 | 10 |  |  | Solar |  | 05_05_8L4 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/24/2016 | 5/30/2017 | Y | EXP | 358 | 08/24/2016 | 09/06/2016 | 8 | 0 | 8 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | RANDOLPH | 341611 | 02368 | 7.6 |  |  | Solar |  | 05_01_201W2 | 02/10/2021 | 02/11/2021 | 0 | 0 | 0 | 02/12/2021 | 02/12/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 |  | 2/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | REHOBOTH | 653283 | 02769 | 2.03 |  |  | Solar |  | 05_09_139L5 | 11/08/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/08/2024 | 1/22/2026 | Y | EXP | 365 | 02/13/2025 | 02/20/2025 | 8 | 0 | 8 |  |  | 3/11/2025 | Connected |  | N
National Grid | AYER | 479722 | 01432 | 6 |  |  | Solar |  | 05_12_12L2 | 12/10/2022 | 12/14/2022 | 13 | 9 | 4 | 12/30/2022 | 12/30/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2023 |  | 6/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | Y
National Grid | LONGMEADOW | 413365 | 01028 | 23.4 |  |  | Solar |  | 05_07_91W40 | 03/24/2022 |  | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 486251 | 01915 | 10 |  |  | Solar |  | 05_07_797W20 | 12/27/2022 | 01/03/2023 | 4 | 0 | 4 | 01/04/2023 | 01/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/27/2022 | 3/26/2024 | Y | EXP | 365 | 03/28/2023 | 03/27/2023 | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | BROCKTON | 581882 | 02302 | 240 |  |  | Solar |  | 05_05_336W2 | 01/19/2024 | 02/08/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 471040 | 02379 | 3.8 |  |  | Solar |  | 05_09_527L1 | 12/06/2022 | 12/09/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 | 12/06/2022 | 4/11/2024 | Y | EXP | 365 | 03/10/2023 | 04/12/2023 | 34 | 0 | 34 |  |  | 4/18/2023 | Connected |  | Y
National Grid | MILFORD | 619949 | 01757 | 11.5 |  |  | Solar |  | 05_05_313W4 | 06/24/2024 | 06/26/2024 | 4 | 0 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 | 06/24/2024 | 1/28/2026 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | GRANBY | 178045 | 01033 | 51.75 |  |  | Solar |  | 05_07_97W4 | 05/05/2017 | 05/05/2017 | 14 | 13 | 1 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 |  | 5/10/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 10/4/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 177458 | 01532 | 15.2 |  |  | Solar |  | 05_05_8L4 | 12/07/2016 | 12/07/2016 | 1 | 1 | 0 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 12/14/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/26/2017 | Connected |  | N
National Grid | RANDOLPH | 348883 | 02368 | 7.68 |  |  | Solar |  | 05_01_201W2 | 03/26/2021 | 03/29/2021 | 0 | 0 | 0 | 03/30/2021 | 03/30/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2021 | Connected |  | N
National Grid | REHOBOTH | 653585 | 02769 | 15.2 |  |  | Solar |  | 05_09_139L5 | 11/26/2024 | 11/27/2024 | 1 | 0 | 1 | 12/02/2024 | 12/02/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | HARVARD | 492383 | 01451 | 3.84 |  |  | Solar |  | 05_12_12L2 | 04/19/2023 | 04/24/2023 | 3 | 0 | 3 | 04/25/2023 | 04/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 591477 | 01028 | 15.2 |  |  | Solar |  | 05_07_797W20 | 02/20/2024 | 02/22/2024 | 2 | 0 | 2 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 693605 | 01915 | 15.2 |  |  | Solar |  | 05_05_336W3 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 35 | 22 | 13 | 08/12/2025 | 10/08/2025 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  | 10/08/2025 | 41 | 0 | 41 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/18/2026 | N | EXP | 365 | 12/30/2025 |  | 3 | 0 | 3 |  |  |  | Construction |  | Y
National Grid | BROCKTON | 501268 | 02302 | 2.03 |  |  | Solar |  | 05_09_527L1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 149 | 134 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 1/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 655214 | 02379 | 10 |  |  | Solar |  | 05_05_313W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | MILFORD | 285089 | 01757 | 7.68 |  |  | Solar |  | 05_07_97W4 | 03/25/2020 | 04/01/2020 | 4 | 0 | 4 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 | 03/25/2020 | 10/21/2021 | Y | EXP | 365 | 01/29/2021 | 03/12/2021 | 42 | 0 | 42 |  |  | 4/13/2021 | Connected |  | N
National Grid | GRANBY | 177565 | 01033 | 7.6 |  |  | Solar |  | 05_05_8L4 | 07/14/2017 | 07/14/2017 | 2 | 2 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/22/2018 | N | EXP | 367 |  |  | 0 | 0 | 0 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 397143 | 01532 | 0 |  |  | Solar |  | 05_01_201W2 | 01/10/2022 | 01/13/2022 | 3 | 2 | 1 | 01/14/2022 | 01/14/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  | 5/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | RANDOLPH | 655652 | 02368 | 5.8 |  |  | Solar |  | 05_09_139L5 | 11/20/2024 | 02/04/2025 | 15 | 10 | 5 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | REHOBOTH | 654225 | 02769 | 10 |  |  | Solar |  | 05_12_12L2 | 11/15/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/15/2024 | 2/19/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | HARVARD | 485572 | 01451 |  |  |  | Other |  | 05_07_91W40 | 01/19/2023 | 02/03/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2023 | 08/03/2023 | 124 | 105 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 625438 | 01028 | 9.86 |  |  | Solar |  | 05_07_797W20 | 07/17/2024 | 07/24/2024 | 3 | 1 | 2 | 07/25/2024 | 07/25/2024 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/17/2024 | 8/23/2025 | Y | EXP | 365 | 10/29/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 11/15/2024 | Connected |  | N
National Grid | BEVERLY | 697246 | 01915 | 11.4 |  |  | Solar |  | 05_05_336W3 | 06/09/2025 | 07/02/2025 | 11 | 6 | 5 | 08/04/2025 | 08/04/2025 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 06/09/2025 | 9/25/2026 | Y | EXP | 365 | 11/18/2025 |  | 45 | 0 | 45 |  |  |  | Construction |  | N
National Grid | BROCKTON | 522509 | 02302 | 12.18 |  |  | Solar |  | 05_09_527L1 | 05/04/2023 | 05/08/2023 | 2 | 0 | 2 | 05/09/2023 | 05/09/2023 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 674719 | 02324 | 3.8 |  |  | Solar |  | 05_05_313W4 | 02/27/2025 | 03/19/2025 | 80 | 80 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 342233 | 01757 | 10 |  |  | Solar |  | 05_07_97W4 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 | 05/04/2021 | 9/25/2022 | Y | EXP | 365 | 08/11/2021 | 09/23/2021 | 43 | 3 | 40 |  |  | 5/5/2022 | Connected |  | N
National Grid | GRANBY | 177644 | 01033 | 4268 |  |  | Solar |  | 05_05_8L4 | 09/22/2017 | 09/22/2017 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2017 | 12/14/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 | 09/22/2017 | 12/11/2020 | Y | STD | 670 | 09/24/2019 | 11/19/2020 | 422 | 5 | 417 |  |  | 12/28/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 456305 | 01532 | 10 |  |  | Solar |  | 05_01_201W2 | 09/22/2022 | 09/30/2022 | 7 | 5 | 2 | 10/03/2022 | 10/03/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2023 | Connected |  | N
National Grid | RANDOLPH | 656598 | 02368 | 10 |  |  | Solar |  | 05_09_139L5 | 11/25/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | REHOBOTH | 658638 | 02769 | 5.76 |  |  | Solar |  | 05_12_12L2 | 12/05/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 12/05/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | AYER | 493283 | 01432 | 5 |  |  | Solar |  | 05_07_91W40 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 | 02/03/2023 | 11/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | N
National Grid | LONGMEADOW | 634657 | 01028 | 9.86 |  |  | Solar |  | 05_07_797W20 | 08/22/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 08/22/2024 | 11/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | BEVERLY | 699782 | 01915 | 23 |  |  | Solar |  | 05_05_336W3 | 06/23/2025 | 07/11/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 | 06/23/2025 | 8/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 540230 | 02302 | 5 |  |  | Solar |  | 05_09_527L1 | 07/24/2023 | 07/26/2023 | 2 | 0 | 2 | 07/27/2023 | 07/27/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 07/24/2023 | 12/2/2024 | Y | EXP | 365 | 11/17/2023 | 12/14/2023 | 28 | 0 | 28 |  |  | 2/17/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 452182 | 02379 | 999 |  |  | Solar |  | 05_05_314W1 | 08/25/2022 | 10/06/2023 | 278 | 268 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 02/27/2024 | 96 | 80 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MILFORD | 351290 | 01757 | 10 |  |  | Solar |  | 05_07_97W4 | 04/23/2021 | 04/28/2021 | 2 | 0 | 2 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/23/2021 | 11/9/2022 | Y | EXP | 365 | 10/19/2021 | 10/19/2021 | 1 | 0 | 1 |  |  | 12/15/2021 | Connected |  | Y
National Grid | BELCHERTOWN | 177788 | 01007 | 7.6 |  |  | Solar |  | 05_05_8L4 | 06/02/2017 | 06/02/2017 | 13 | 13 | 0 | 06/21/2017 | 06/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2017 | 06/02/2017 | 6/7/2018 | Y | EXP | 349 | 08/24/2017 | 09/19/2017 | 17 | 0 | 17 | 9/19/2017 | 9/19/2017 | 9/27/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 472052 | 01532 | 18.816 |  |  | Solar |  | 05_01_201W2 | 10/27/2022 | 11/16/2022 | 14 | 13 | 1 | 11/17/2022 | 11/17/2022 | 27 | 15 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 | 10/27/2022 | 1/11/2024 | Y | EXP | 365 | 06/09/2023 | 08/10/2023 | 63 | 0 | 63 |  |  | 8/11/2023 | Connected |  | N
National Grid | RANDOLPH | 663991 | 02368 | 3.8 |  |  | Solar |  | 05_09_139L5 | 01/06/2025 | 02/25/2025 | 27 | 22 | 5 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | NORTON | 688843 | 02766 | 15.2 |  |  | Solar |  | 05_12_12L2 | 05/01/2025 | 05/12/2025 | 6 | 2 | 4 | 05/13/2025 | 05/13/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 05/01/2025 | 6/12/2026 | Y | EXP | 365 | 10/17/2025 | 11/24/2025 | 39 | 0 | 39 |  |  | 11/25/2025 | Connected |  | N
National Grid | AYER | 557710 | 01432 | 3.84 |  |  | Solar |  | 05_07_91W40 | 09/29/2023 | 10/02/2023 | 1 | 0 | 1 | 10/03/2023 | 10/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/29/2023 | 12/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 637313 | 01028 | 34.5 |  |  | Solar |  | 05_07_797W20 | 09/03/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 47 | 38 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | BEVERLY | 717214 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 09/10/2025 | 09/25/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | BROCKTON | 547979 | 02301 | 10 |  |  | Solar |  | 05_09_527L1 | 08/28/2023 | 08/29/2023 | 2 | 1 | 1 | 08/30/2023 | 08/30/2023 | 26 | 1 | 25 | 11/02/2023 | 12/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 12/21/2024 | N | EXP | 365 | 01/18/2024 | 01/31/2024 | 14 | 0 | 14 |  |  | 2/22/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 432400 | 02379 | 999 |  |  | Solar |  | 05_05_314W1 | 08/25/2022 | 10/24/2023 | 289 | 279 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 | 02/27/2024 | 85 | 65 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MILFORD | 413313 | 01757 | 125 |  |  | Solar |  | 05_07_97W4 | 03/14/2022 | 08/01/2022 | 96 | 87 | 9 | 08/02/2022 | 08/02/2022 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 03/14/2022 | 8/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | GRANBY | 189870 | 01033 | 10 |  |  | Solar |  | 05_05_8L4 | 07/05/2018 | 07/05/2018 | 8 | 8 | 0 | 08/14/2018 | 08/14/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 505820 | 01532 | 12.18 |  |  | Solar |  | 05_01_201W2 | 05/16/2023 | 05/18/2023 | 3 | 2 | 1 | 05/19/2023 | 05/19/2023 | 98 | 79 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2023 | Connected |  | N
National Grid | RANDOLPH | 669722 | 02368 | 10 |  |  | Solar |  | 05_09_139L5 | 02/03/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | REHOBOTH | 694351 | 02769 | 5.76 |  |  | Solar |  | 05_12_12L2 | 05/28/2025 | 11/07/2025 | 1 | 0 | 1 | 11/14/2025 | 11/14/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 548794 | 01451 | 6 |  |  | Solar |  | 05_07_91W40 | 08/25/2023 | 08/28/2023 | 1 | 0 | 1 | 08/29/2023 | 08/29/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/25/2023 | 11/24/2024 | Y | EXP | 365 | 01/30/2024 | 02/06/2024 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 647055 | 01028 | 10 |  |  | Solar |  | 05_07_797W20 | 10/24/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/24/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 739626 | 01915 | 17.6 |  |  | Solar |  | 05_05_336W3 | 12/11/2025 | 12/16/2025 | 3 | 0 | 3 | 12/17/2025 | 12/17/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 563791 | 02301 | 6 |  |  | Solar |  | 05_09_527L1 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 348940 | 02379 | 100 |  |  | Solar |  | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/11/2021 | 05/11/2021 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 576970 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W4 | 12/27/2023 | 01/02/2024 | 3 | 0 | 3 | 01/03/2024 | 01/03/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 12/27/2023 | 2/20/2025 | Y | EXP | 365 | 09/12/2024 | 11/05/2024 | 55 | 0 | 55 |  |  | 1/29/2025 | Connected |  | N
National Grid | GRANBY | 195799 | 01033 | 6 |  |  | Solar |  | 05_05_8L4 | 11/10/2018 | 11/16/2018 | 3 | 3 | 0 | 11/19/2018 | 11/19/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 | 11/10/2018 | 5/23/2019 | Y | EXP | 156 | 03/20/2019 | 03/19/2019 | 0 | 0 | 0 |  |  | 3/29/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 537240 | 01532 | 7.25 |  |  | Solar |  | 05_01_201W2 | 06/29/2023 | 07/05/2023 | 4 | 3 | 1 | 07/06/2023 | 07/06/2023 | 110 | 97 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 12/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | RANDOLPH | 687653 | 02368 | 12.6 |  |  | Solar |  | 05_09_139L5 | 04/25/2025 | 05/22/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 65 | 54 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 380771 | 02766 | 360 |  |  | Solar |  | 05_12_12L4 | 09/09/2021 | 10/11/2021 | 21 | 14 | 7 |  |  | 45 | 5 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 | 09/09/2021 | 7/7/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | AYER | 548907 | 01432 | 600 |  |  | Natural Gas |  | 05_07_91W40 | 10/03/2023 | 02/05/2024 | 82 | 73 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2024 | 02/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 654486 | 01036 | 10 |  |  | Solar |  | 05_07_797W20 | 11/18/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | BEVERLY | 175844 | 01915 | 17.6 |  |  | Solar |  | 05_05_336W3 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/22/2015 | 05/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 |  | 10/30/2015 | N | EXP | 155 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 3/28/2016 | Connected |  | N
National Grid | BROCKTON | 570155 | 02302 | 10 |  |  | Solar |  | 05_09_527L1 | 11/27/2023 | 11/28/2023 | 1 | 0 | 1 | 11/29/2023 | 11/29/2023 | 29 | 9 | 20 | 01/22/2024 | 01/24/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  | 01/24/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 2/7/2024 |  | 2/19/2025 | N | EXP | 365 | 02/28/2024 | 04/03/2024 | 36 | 0 | 36 |  |  | 4/9/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 348897 | 02379 | 150 |  |  | Solar |  | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/03/2021 | 05/03/2021 | 46 | 8 | 38 | 07/21/2021 | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 |  | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 3/14/2023 | N | EXP | 365 | 01/10/2023 | 01/10/2023 | 1 | 0 | 1 |  |  | 4/5/2023 | Connected |  | N
National Grid | MILFORD | 614076 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W4 | 05/29/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | GRANBY | 192159 | 01033 | 10 |  |  | Solar |  | 05_05_8L4 | 07/30/2018 | 09/05/2018 | 19 | 16 | 3 | 09/06/2018 | 09/06/2018 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 564591 | 01532 | 44.6 |  |  | Solar |  | 05_01_201W2 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 10/24/2023 |  | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | RANDOLPH | 702745 | 02368 | 5.76 |  |  | Solar |  | 05_09_139L5 | 07/09/2025 |  | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 674470 | 02703 | 50 |  |  | Solar |  | 05_12_12L4 | 03/03/2025 | 03/13/2025 | 8 | 4 | 4 | 03/14/2025 | 03/14/2025 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | HARVARD | 554168 | 01451 | 10 |  |  | Solar |  | 05_07_91W40 | 09/25/2023 | 09/29/2023 | 4 | 0 | 4 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/25/2023 | 11/22/2024 | Y | EXP | 365 | 01/30/2024 | 01/31/2024 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Y
National Grid | HAMPDEN | 657495 | 01036 | 11.5 |  |  | Solar |  | 05_07_797W20 | 11/27/2024 | 12/11/2024 | 9 | 7 | 2 | 12/12/2024 | 12/12/2024 | 82 | 59 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2025 | Connected |  | N
National Grid | BEVERLY | 176070 | 01915 | 3.8 |  |  | Solar |  | 05_05_336W3 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2015 |  | 6/27/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 3/22/2016 | Connected |  | N
National Grid | BROCKTON | 583851 | 02302 | 15.66 |  |  | Solar |  | 05_09_527L1 | 01/16/2024 | 01/18/2024 | 2 | 0 | 2 | 01/19/2024 | 01/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 580711 | 02379 | 150 |  |  | Solar |  | 05_05_314W1 | 01/07/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 656239 | 01568 | 5.76 |  |  | Solar |  | 05_07_97W4 | 11/22/2024 | 01/22/2025 | 22 | 18 | 4 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 11/22/2024 | 3/11/2026 | Y | EXP | 365 | 07/30/2025 | 10/24/2025 | 87 | 0 | 87 |  |  | 12/15/2025 | Connected |  | N
National Grid | GRANBY | 196777 | 01033 | 4998 |  |  | Solar |  | 05_05_8L4 | 11/06/2018 | 11/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 01/09/2019 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 567774 | 01581 | 23 |  |  | Solar |  | 05_01_201W2 | 11/01/2023 | 05/10/2024 | 131 | 128 | 3 | 05/13/2024 | 05/13/2024 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 11/01/2023 | 6/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | RANDOLPH | 714478 | 02368 | 0 |  |  | Solar |  | 05_09_139L5 | 08/27/2025 | 08/29/2025 | 2 | 0 | 2 | 09/02/2025 | 09/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | REHOBOTH | 697519 | 02769 | 24.96 |  |  | Solar |  | 05_12_12L4 | 06/26/2025 | 07/14/2025 | 10 | 8 | 2 | 07/15/2025 | 07/15/2025 | 14 | 2 | 12 | 08/11/2025 | 11/13/2025 | 66 | 24 | 42 |  |  | 0 | 0 | 0 |  | 11/13/2025 | 66 | 24 | 42 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | AYER | 583557 | 01432 | 4.35 |  |  | Solar |  | 05_07_91W40 | 02/08/2024 | 02/12/2024 | 2 | 0 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 665671 | 01028 | 0 |  |  | Solar |  | 05_07_797W20 | 01/15/2025 | 01/23/2025 | 5 | 2 | 3 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 01/15/2025 | 4/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | BEVERLY | 176556 | 01915 | 11.4 |  |  | Solar |  | 05_05_336W3 | 10/07/2015 | 10/07/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 10/13/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | BROCKTON | 595501 | 02302 | 10 |  |  | Solar |  | 05_09_527L1 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 65 | 51 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 | 03/27/2024 | 7/28/2025 | Y | EXP | 365 | 08/22/2024 | 08/29/2024 | 8 | 0 | 8 |  |  | 12/12/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 650009 | 02379 | 0 |  |  | Other |  | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 670368 | 01757 | 10 |  |  | Solar |  | 05_07_97W4 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | GRANBY | 205992 | 01033 | 7.6 |  |  | Solar |  | 05_05_8L4 | 01/15/2019 | 01/30/2019 | 9 | 0 | 9 | 01/31/2019 | 01/31/2019 | 178 | 0 | 178 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 581647 | 01581 | 7.83 |  |  | Solar |  | 05_01_201W2 | 01/09/2024 | 01/16/2024 | 5 | 1 | 4 | 01/17/2024 | 01/17/2024 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | RANDOLPH | 177777 | 02368 | 3960 |  |  | Solar |  | 05_09_501L1 | 03/28/2017 | 04/18/2017 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2017 | 05/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 03/28/2017 | 8/14/2027 | Y | STD | 1400 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 705356 | 02703 | 249 |  |  | Solar |  | 05_12_12L4 | 07/17/2025 | 08/18/2025 | 21 | 13 | 8 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | HARVARD | 609945 | 01451 | 6 |  |  | Solar |  | 05_07_91W40 | 05/09/2024 | 06/06/2024 | 2 | 0 | 2 | 06/07/2024 | 06/07/2024 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 05/09/2024 | 9/30/2025 | Y | EXP | 365 | 03/08/2025 | 04/10/2025 | 34 | 0 | 34 |  |  | 4/23/2025 | Connected |  | N
National Grid | LONGMEADOW | 671083 | 01028 | 15.2 |  |  | Solar |  | 05_07_797W20 | 02/10/2025 | 02/19/2025 | 4 | 0 | 4 | 07/18/2025 | 07/18/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 10/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | BEVERLY | 176828 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 01/18/2016 | 01/18/2016 | 5 | 5 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/24/2017 | N | EXP | 350 |  |  | 0 | 0 | 0 | 10/10/2016 | 10/10/2016 | 10/13/2016 | Connected |  | N
National Grid | BROCKTON | 598591 | 02302 | 10 |  |  | Solar |  | 05_09_527L1 | 03/27/2024 | 04/23/2024 | 19 | 16 | 3 | 04/24/2024 | 04/24/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 03/27/2024 | 7/4/2025 | Y | EXP | 365 | 08/08/2024 | 08/13/2024 | 6 | 0 | 6 |  |  | 9/18/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 650006 | 02379 | 0 |  |  | Other |  | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 737857 | 01757 | 5.76 |  |  | Solar |  | 05_07_97W5 | 12/09/2025 |  | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GRANBY | 209085 | 01033 | 3.8 |  |  | Solar |  | 05_05_8L4 | 03/12/2019 | 03/21/2019 | 6 | 0 | 6 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 593191 | 01581 | 15.2 |  |  | Solar |  | 05_01_201W2 | 02/29/2024 | 03/06/2024 | 4 | 0 | 4 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | RANDOLPH | 177639 | 02368 | 2700 |  |  | Solar |  | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 114 | 104 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 07/20/2017 | 8/14/2027 | Y | STD | 784 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 174129 | 02703 | 224 |  |  | Solar |  | 05_12_12L4 | 04/30/2012 | 04/30/2012 | 11 | 0 | 11 | 05/17/2012 | 05/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2012 |  | 9/28/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/30/2013 | 1/30/2013 | 1/8/2013 | Connected |  | N
National Grid | HARVARD | 616891 | 01451 | 3.8 |  |  | Solar |  | 05_07_91W40 | 06/10/2024 | 06/17/2024 | 1 | 0 | 1 | 06/18/2024 | 06/18/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | LONGMEADOW | 674770 | 01028 | 5.76 |  |  | Solar |  | 05_07_797W20 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | BEVERLY | 176881 | 01915 | 3.8 |  |  | Solar |  | 05_05_336W3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/10/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 602089 | 02302 | 6 |  |  | Solar |  | 05_09_527L1 | 04/11/2024 | 04/16/2024 | 2 | 0 | 2 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/11/2024 | 6/6/2025 | Y | EXP | 365 | 08/22/2024 | 08/21/2024 | 0 | 0 | 0 |  |  | 8/24/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 174569 | 02379 | 1000 |  |  | Solar |  | 05_05_314W2 | 04/17/2011 | 04/17/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2012 | 04/17/2011 | 10/31/2012 | Y | STD | 264 | 05/07/2012 | 07/23/2012 | 52 | 0 | 52 | 8/6/2012 | 8/6/2012 | 8/17/2012 | Connected |  | N
National Grid | MILFORD | 176559 | 01757 | 2052 |  |  | Solar |  | 05_07_97W5 | 10/08/2015 | 10/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2015 | 11/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/03/2016 | 08/09/2017 | 378 | 89 | 289 | 8/25/2016 |  | 10/14/2016 | N | STD | 50 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 304219 | 01033 | 6.96 |  |  | Solar |  | 05_05_8L4 | 07/30/2020 | 08/12/2020 | 8 | 8 | 0 | 08/13/2020 | 08/13/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 8/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2020 | Connected |  | N
National Grid | WESTBOROUGH | 597435 | 01581 | 23 |  |  | Solar |  | 05_01_201W2 | 03/18/2024 | 03/27/2024 | 8 | 6 | 2 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | RANDOLPH | 735375 | 02368 | 100 |  |  | Solar |  | 05_09_501L1 | 12/01/2025 |  | 22 | 17 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | ATTLEBORO | 174128 | 02703 | 224 |  |  | Solar |  | 05_12_12L4 | 04/30/2012 | 04/30/2012 | 11 | 0 | 11 | 05/17/2012 | 05/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2012 |  | 9/28/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/30/2013 | 1/30/2013 | 1/8/2013 | Connected |  | N
National Grid | HARVARD | 621865 | 01451 | 3.8 |  |  | Solar |  | 05_07_91W40 | 07/01/2024 | 07/10/2024 | 2 | 0 | 2 | 07/11/2024 | 07/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | LONGMEADOW | 688918 | 01028 | 9.425 |  |  | Solar |  | 05_07_797W20 | 05/01/2025 | 09/15/2025 | 93 | 91 | 2 | 09/16/2025 | 09/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 176974 | 01915 | 6.45 |  |  | Solar |  | 05_05_336W3 | 10/06/2016 | 10/06/2016 | 5 | 5 | 0 | 10/17/2016 | 10/17/2016 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 |  | 10/12/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 625323 | 02302 | 17.6 |  |  | Solar |  | 05_09_527L1 | 07/23/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/23/2024 | 8/19/2025 | Y | EXP | 365 | 10/02/2024 | 10/01/2024 | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | WEST BRIDGEWATER | 177081 | 02379 | 600 |  |  | Solar |  | 05_05_314W2 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/13/2017 | 53 | 46 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2017 | 10/18/2016 | 3/6/2021 | Y | STD | 1355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 176979 | 01757 | 5.2 |  |  | Solar |  | 05_07_97W5 | 12/28/2016 | 12/28/2016 | 4 | 4 | 0 | 01/05/2017 | 01/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/28/2016 | 1/3/2018 | Y | EXP | 362 | 07/24/2017 | 08/10/2017 | 13 | 0 | 13 | 9/5/2017 | 9/5/2017 | 9/7/2017 | Connected |  | N
National Grid | BELCHERTOWN | 325845 | 01007 | 15.2 |  |  | Solar |  | 05_05_8L4 | 11/13/2020 | 11/18/2020 | 2 | 0 | 2 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2021 | Connected |  | N
National Grid | WESTBOROUGH | 630200 | 01581 | 22.96 |  |  | Solar |  | 05_01_201W2 | 08/05/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 25 | 7 | 18 | 12/12/2024 | 04/28/2025 | 93 | 16 | 77 |  |  | 0 | 0 | 0 |  | 04/28/2025 | 93 | 16 | 77 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 6/11/2026 | N | EXP | 365 | 11/07/2025 | 12/22/2025 | 46 | 0 | 46 |  |  | 12/9/2025 | Connected |  | N
National Grid | RANDOLPH | 737146 | 02368 | 20 |  |  | Solar |  | 05_09_501L1 | 12/02/2025 |  | 21 | 19 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REHOBOTH | 174663 | 02769 | 50 |  |  | Solar |  | 05_12_12L4 | 12/13/2012 | 12/13/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 | 03/12/2013 | 03/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/13/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/28/2013 | Connected |  | Y
National Grid | HARVARD | 625778 | 01451 | 7.6 |  |  | Solar |  | 05_07_91W40 | 07/18/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2024 | Connected |  | N
National Grid | LONGMEADOW | 697453 | 01028 | 15.2 |  |  | Solar |  | 05_07_797W20 | 06/12/2025 | 06/25/2025 | 8 | 6 | 2 | 06/26/2025 | 06/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | BEVERLY | 177174 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 05/31/2016 | 05/31/2016 | 1 | 1 | 0 | 06/02/2016 | 06/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/31/2016 | 6/6/2017 | Y | EXP | 351 | 11/03/2016 | 12/07/2016 | 22 | 0 | 22 | 7/17/2017 | 7/17/2017 | 7/19/2017 | Connected |  | N
National Grid | BROCKTON | 630437 | 02302 | 10 |  |  | Solar |  | 05_09_527L1 | 08/06/2024 | 08/16/2024 | 1 | 0 | 1 | 08/19/2024 | 08/19/2024 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 08/06/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 177785 | 02379 | 56 |  |  | Solar |  | 05_05_314W2 | 06/01/2017 | 06/01/2017 | 4 | 3 | 1 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 |  | 6/7/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 4/2/2018 | Connected |  | N
National Grid | MILFORD | 177321 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W5 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/25/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 385414 | 01033 | 9.8 |  |  | Solar |  | 05_05_8L4 | 11/02/2021 | 12/15/2021 | 1 | 0 | 1 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 650502 | 01772 | 0 |  |  | Solar |  | 05_01_201W2 | 10/29/2024 | 10/31/2024 | 2 | 0 | 2 | 11/01/2024 | 11/01/2024 | 71 | 47 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | RANDOLPH | 175848 | 02368 | 224 |  |  | Solar |  | 05_09_501L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/25/2015 | 05/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 10/30/2015 | N | EXP | 121 |  |  | 0 | 0 | 0 | 7/1/2015 | 7/1/2015 | 12/15/2015 | Connected |  | N
National Grid | REHOBOTH | 175051 | 02769 | 190 |  |  | Solar |  | 05_12_12L4 | 10/18/2011 | 10/18/2011 | 76 | 0 | 76 | 02/09/2012 | 02/09/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2012 | 10/18/2011 | 11/30/2012 | Y | EXP | 267 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 8/23/2012 | Connected |  | Y
National Grid | AYER | 626535 | 01432 | 7.6 |  |  | Solar |  | 05_07_91W40 | 07/22/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/22/2024 | 11/22/2025 | Y | EXP | 365 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WEST BROOKFIELD | 649258 | 01585 | 499 |  |  | Solar |  | 05_07_797W23 | 02/14/2025 | 03/12/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 177982 | 01915 | 168 |  |  | Solar |  | 05_05_336W3 | 08/28/2017 | 08/28/2017 | 5 | 5 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/2/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 2/7/2018 | 2/7/2018 | 2/20/2018 | Connected |  | N
National Grid | BROCKTON | 640697 | 02302 | 15.36 |  |  | Solar |  | 05_09_527L1 | 09/17/2024 | 11/05/2024 | 34 | 30 | 4 | 11/06/2024 | 11/06/2024 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 178034 | 02333 | 92 |  |  | Solar |  | 05_05_314W2 | 10/26/2017 | 10/26/2017 | 5 | 0 | 5 | 11/13/2017 | 11/13/2017 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 |  | 11/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 189432 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W5 | 06/27/2018 | 06/27/2018 | 9 | 0 | 9 | 07/20/2018 | 07/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 06/27/2018 | 8/12/2020 | Y | EXP | 675 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 391863 | 01033 | 15.2 |  |  | Solar |  | 05_05_8L4 | 11/01/2021 | 11/09/2021 | 6 | 5 | 1 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 653155 | 01772 | 9.75 |  |  | Solar |  | 05_01_201W2 | 11/08/2024 | 12/03/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 11/08/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175847 | 02368 | 70 |  |  | Solar |  | 05_09_501L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/25/2015 | 05/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 10/30/2015 | N | EXP | 121 |  |  | 0 | 0 | 0 | 7/1/2015 | 7/1/2015 | 12/15/2015 | Connected |  | N
National Grid | ATTLEBORO | 175852 | 02703 | 1104 |  |  | Solar |  | 05_12_12L4 | 05/21/2015 | 05/21/2015 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2015 | 07/16/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 10/30/2015 | N | STD | -77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 632647 | 01451 | 4.06 |  |  | Solar |  | 05_07_91W40 | 08/14/2024 | 08/22/2024 | 3 | 0 | 3 | 08/23/2024 | 08/23/2024 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/14/2024 | 10/28/2025 | Y | EXP | 365 | 03/08/2025 | 03/19/2025 | 12 | 0 | 12 |  |  | 3/25/2025 | Connected |  | N
National Grid | WARREN | 656709 | 01585 | 4800 |  |  | Solar |  | 05_07_797W23 | 01/07/2025 | 09/15/2025 | 171 | 162 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/13/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 178390 | 01915 | 15.2 |  |  | Solar |  | 05_05_336W3 | 03/01/2018 | 03/01/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 | 03/01/2018 | 10/31/2019 | Y | EXP | 589 |  |  | 0 | 0 | 0 |  |  | 10/24/2019 | Connected |  | N
National Grid | BROCKTON | 655098 | 02302 | 5.76 |  |  | Solar |  | 05_09_527L1 | 11/19/2024 | 01/08/2025 | 12 | 7 | 5 | 01/09/2025 | 01/09/2025 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/19/2024 | 5/9/2026 | Y | EXP | 365 | 07/10/2025 | 07/23/2025 | 14 | 0 | 14 |  |  | 7/31/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 187658 | 02379 | 100 |  |  | Solar |  | 05_05_314W2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 153 | 22 | 131 | 08/15/2018 | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 194453 | 01757 | 3.8 |  |  | Solar |  | 05_07_97W5 | 09/04/2018 | 10/05/2018 | 6 | 6 | 0 | 10/08/2018 | 10/08/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 | 09/04/2018 | 3/5/2019 | Y | EXP | 147 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | GRANBY | 416885 | 01033 | 15.2 |  |  | Solar |  | 05_05_8L4 | 03/10/2022 | 03/11/2022 | 1 | 0 | 1 | 03/14/2022 | 03/14/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 3/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 656060 | 01772 | 9.423 |  |  | Solar |  | 05_01_201W2 | 11/21/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | AVON | 176295 | 02322 | 1000 |  |  | Solar |  | 05_09_501L1 | 09/09/2015 | 09/09/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/15/2015 | 10/20/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/16/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 175876 | 02769 | 50 |  |  | Solar |  | 05_12_12L4 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 8/13/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 5/13/2015 | 5/13/2015 | 7/7/2015 | Connected |  | N
National Grid | HARVARD | 639571 | 01451 | 6 |  |  | Solar |  | 05_07_91W40 | 09/12/2024 | 09/27/2024 | 7 | 6 | 1 | 09/30/2024 | 09/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/12/2024 | 12/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | WARE | 717436 | 01082 | 57 |  |  | Solar |  | 05_07_797W23 | 09/08/2025 | 09/22/2025 | 9 | 6 | 3 | 09/23/2025 | 09/23/2025 | 67 | 51 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 178449 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 11/29/2017 | 11/29/2017 | 45 | 42 | 3 | 02/06/2018 | 02/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 |  | 12/5/2018 | N | EXP | 302 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | BROCKTON | 660307 | 02302 | 17.16 |  |  | Solar |  | 05_09_527L1 | 12/12/2024 | 12/18/2024 | 4 | 1 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 229154 | 02379 | 7.6 |  |  | Solar |  | 05_05_314W2 | 05/18/2019 | 05/23/2019 | 3 | 0 | 3 | 05/24/2019 | 05/24/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 8/30/2019 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  | 8/12/2019 | Connected |  | N
National Grid | MILFORD | 195014 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W5 | 09/06/2018 | 09/24/2018 | 3 | 3 | 0 | 09/25/2018 | 09/25/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 | 09/06/2018 | 3/5/2019 | Y | EXP | 162 |  |  | 0 | 0 | 0 |  |  | 1/16/2019 | Connected |  | N
National Grid | BELCHERTOWN | 424932 | 01007 | 7.6 |  |  | Solar |  | 05_05_8L4 | 04/19/2022 |  | 86 | 69 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 671328 | 01772 | 0 |  |  | Battery Add-On |  | 05_01_201W2 | 02/11/2025 | 02/14/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | RANDOLPH | 176279 | 02368 | 75 |  |  | Solar |  | 05_09_501L1 | 05/06/2015 | 05/06/2015 | 1 | 1 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2015 |  | 10/30/2015 | N | EXP | 149 |  |  | 0 | 0 | 0 | 6/10/2015 | 6/10/2015 | 11/23/2016 | Connected |  | N
National Grid | REHOBOTH | 176984 | 02769 | 1104 |  |  | Solar |  | 05_12_12L4 | 03/07/2017 | 03/07/2017 | 229 | 225 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 641061 | 01451 | 10 |  |  | Solar |  | 05_07_91W40 | 09/17/2024 | 10/02/2024 | 9 | 6 | 3 | 10/03/2024 | 10/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 11/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 735422 | 01082 | 5.76 |  |  | Solar |  | 05_07_797W23 | 11/20/2025 | 12/12/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 178445 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 04/03/2018 | 04/03/2018 | 4 | 4 | 0 | 04/10/2018 | 04/10/2018 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/9/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 667309 | 02302 | 7.6 |  |  | Solar |  | 05_09_527L1 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 342097 | 02379 | 3.84 |  |  | Solar |  | 05_05_314W2 | 02/12/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 316225 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W5 | 11/02/2020 | 11/09/2020 | 4 | 0 | 4 | 11/10/2020 | 11/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 440304 | 01033 | 15.2 |  |  | Solar |  | 05_05_8L4 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 9/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 674076 | 01772 | 6.84 |  |  | Solar |  | 05_01_201W2 | 02/28/2025 | 03/10/2025 | 6 | 2 | 4 | 03/11/2025 | 03/11/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | RANDOLPH | 176368 | 02368 | 499 |  |  | Solar |  | 05_09_501L1 | 05/06/2016 | 05/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2016 | 06/07/2016 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/11/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178374 | 02703 | 57.5 |  |  | Solar |  | 05_12_12L4 | 11/21/2017 | 11/21/2017 | 10 | 0 | 10 | 12/08/2017 | 12/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2018 |  | 11/27/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 7/25/2018 | Connected |  | N
National Grid | AYER | 647766 | 01432 | 6.09 |  |  | Solar |  | 05_07_91W40 | 10/17/2024 | 11/12/2024 | 12 | 9 | 3 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/17/2024 | 12/31/2025 | Y | EXP | 365 | 04/15/2025 | 05/16/2025 | 32 | 0 | 32 |  |  | 5/19/2025 | Connected |  | N
National Grid | WARE | 175228 | 01082 | 17.6 |  |  | Solar |  | 05_07_797W23 | 01/06/2015 | 01/06/2015 | 9 | 4 | 5 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/17/2016 | Connected |  | N
National Grid | BEVERLY | 183593 | 01915 | 6 |  |  | Solar |  | 05_05_336W3 | 05/23/2018 | 05/23/2018 | 19 | 13 | 6 | 06/21/2018 | 06/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 692427 | 02302 | 17.6 |  |  | Solar |  | 05_09_527L1 | 05/27/2025 | 05/28/2025 | 1 | 0 | 1 | 05/29/2025 | 05/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 366728 | 02333 | 7.6 |  |  | Solar |  | 05_05_314W2 | 06/29/2021 | 08/26/2021 | 41 | 38 | 3 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 06/29/2021 | 12/2/2023 | Y | EXP | 365 | 01/06/2022 | 10/31/2022 | 299 | 0 | 299 |  |  | 1/25/2023 | Connected |  | N
National Grid | MILFORD | 466954 | 01757 | 3.77 |  |  | Solar |  | 05_07_97W5 | 02/23/2023 | 04/12/2023 | 34 | 28 | 6 | 04/13/2023 | 04/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 | 02/23/2023 | 7/23/2024 | Y | EXP | 365 | 10/21/2023 | 11/07/2023 | 18 | 0 | 18 |  |  | 11/9/2023 | Connected |  | Y
National Grid | GRANBY | 562760 | 01033 | 9.984 |  |  | Solar |  | 05_05_8L4 | 11/27/2023 | 12/21/2023 | 18 | 16 | 2 | 12/22/2023 | 12/22/2023 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 2/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 685431 | 01772 | 9.423 |  |  | Solar |  | 05_01_201W2 | 04/23/2025 | 04/30/2025 | 5 | 1 | 4 | 05/01/2025 | 05/01/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | RANDOLPH | 176472 | 02368 | 375 |  |  | Hydro |  | 05_09_501L1 | 03/21/2016 | 03/21/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2016 | 05/13/2016 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 193913 | 02766 | 112.5 |  |  | Solar |  | 05_12_12L4 | 08/21/2018 | 08/29/2018 | 6 | 5 | 1 | 08/30/2018 | 08/30/2018 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2019 |  | 11/15/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 12/17/2019 | Connected |  | N
National Grid | HARVARD | 660096 | 01451 | 7.6 |  |  | Solar |  | 05_07_91W40 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 175295 | 01082 | 21.2 |  |  | Solar |  | 05_07_797W23 | 01/14/2015 | 01/14/2015 | 4 | 1 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 | 01/14/2015 | 12/31/2016 | Y | EXP | 683 | 11/04/2016 | 11/15/2016 | 6 | 0 | 6 | 1/12/2017 | 1/12/2017 | 1/24/2017 | Connected |  | N
National Grid | BEVERLY | 188704 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 07/06/2018 | 08/10/2018 | 1 | 1 | 0 | 08/13/2018 | 08/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/06/2018 | 8/26/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2019 | Connected |  | N
National Grid | BROCKTON | 392878 | 02302 | 999 |  |  | Solar |  | 05_09_527L2 | 04/12/2022 | 06/02/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2022 | 07/07/2022 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EAST BRIDGEWATER | 375292 | 02333 | 15.2 |  |  | Solar |  | 05_05_314W2 | 08/11/2021 | 12/27/2021 | 12 | 8 | 4 | 08/30/2021 | 08/30/2021 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 |  | 1/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | MILFORD | 572536 | 01757 | 9.6 |  |  | Solar |  | 05_07_97W5 | 11/27/2023 | 12/11/2023 | 10 | 7 | 3 | 12/12/2023 | 12/12/2023 | 26 | 3 | 23 | 02/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 2/27/2024 | 11/27/2023 | 3/5/2025 | Y | EXP | 365 | 03/16/2024 | 04/19/2024 | 35 | 0 | 35 |  |  | 5/17/2024 | Connected |  | N
National Grid | GRANBY | 594903 | 01033 | 34.5 |  |  | Solar |  | 05_05_8L4 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 692599 | 01772 | 7.678 |  |  | Solar |  | 05_01_201W2 | 05/19/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177641 | 02368 | 3200 |  |  | Solar |  | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 113 | 104 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 204469 | 02769 | 20 |  |  | Solar |  | 05_12_12L4 | 02/06/2019 | 03/18/2019 | 27 | 22 | 5 | 03/19/2019 | 03/19/2019 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 9/30/2019 | N | EXP | 171 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | HARVARD | 425562 | 01451 | 999 |  |  | Solar |  | 05_07_91W41 | 08/15/2022 | 09/06/2022 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/07/2022 | 09/28/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 176549 | 01082 | 9.6 |  |  | Solar |  | 05_07_797W23 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/06/2016 | 04/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/10/2017 | Y | EXP | 356 | 11/10/2016 | 11/21/2016 | 6 | 0 | 6 | 11/28/2016 | 11/28/2016 | 11/30/2016 | Connected |  | N
National Grid | BEVERLY | 194481 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 08/28/2018 | 09/24/2018 | 8 | 8 | 0 | 09/25/2018 | 09/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 653885 | 02302 | 7.6 |  |  | Solar |  | 05_09_527L2 | 11/15/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/15/2024 | 3/8/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 375524 | 02333 | 7.6 |  |  | Solar |  | 05_05_314W2 | 08/12/2021 | 09/02/2021 | 16 | 15 | 1 | 09/03/2021 | 09/03/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | MILFORD | 579463 | 01757 | 10 |  |  | Solar |  | 05_07_97W5 | 01/10/2024 | 01/16/2024 | 3 | 0 | 3 | 01/17/2024 | 01/17/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/10/2024 | 3/6/2025 | Y | EXP | 365 | 05/24/2024 | 09/11/2024 | 111 | 0 | 111 |  |  | 9/17/2024 | Connected |  | N
National Grid | GRANBY | 632119 | 01033 | 0 |  |  | Battery Add-On |  | 05_05_8L4 | 09/03/2024 | 09/11/2024 | 6 | 4 | 2 | 09/12/2024 | 09/12/2024 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 693842 | 01772 | 10 |  |  | Solar |  | 05_01_201W2 | 05/23/2025 | 05/27/2025 | 1 | 0 | 1 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 177640 | 02368 | 2980 |  |  | Solar |  | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 113 | 104 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 243349 | 02769 | 2000 |  |  | Solar |  | 05_12_12L4 | 07/29/2019 | 09/09/2019 | 29 | 24 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2019 | 10/08/2019 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2021 | 07/29/2019 | 6/1/2023 | Y | STD | 367 | 09/28/2022 | 01/19/2023 | 114 | 0 | 114 |  |  | 5/31/2023 | Connected |  | N
National Grid | AYER | 651586 | 01432 | 5.76 |  |  | Solar |  | 05_07_91W41 | 11/13/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/13/2024 | 1/29/2026 | Y | EXP | 365 | 05/07/2025 | 06/02/2025 | 27 | 0 | 27 |  |  |  | Completion Documents |  | N
National Grid | WARE | 176822 | 01082 | 10 |  |  | Solar |  | 05_07_797W23 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 11/21/2016 | Connected |  | N
National Grid | BEVERLY | 207501 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 02/11/2019 | 02/20/2019 | 5 | 0 | 5 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/11/2019 | 7/22/2020 | Y | EXP | 365 | 11/01/2019 | 01/15/2020 | 75 | 0 | 75 |  |  | 4/22/2020 | Connected |  | N
National Grid | BROCKTON | 741953 | 02302 | 19 |  |  | Solar |  | 05_09_527L2 | 12/23/2025 |  | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BRIDGEWATER | 375895 | 02333 | 9.6 |  |  | Solar |  | 05_05_314W2 | 08/13/2021 | 09/15/2021 | 22 | 21 | 1 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 | 08/13/2021 | 5/7/2023 | Y | EXP | 365 | 04/07/2022 | 04/27/2022 | 21 | 0 | 21 |  |  | 5/27/2022 | Connected |  | N
National Grid | MILFORD | 625881 | 01757 | 5.76 |  |  | Solar |  | 05_07_97W5 | 07/18/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | GRANBY | 641921 | 01033 | 6 |  |  | Solar |  | 05_05_8L4 | 09/23/2024 | 09/30/2024 | 4 | 0 | 4 | 10/01/2024 | 10/01/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 711870 | 01772 | 6.282 |  |  | Solar |  | 05_01_201W2 | 08/13/2025 | 08/19/2025 | 4 | 0 | 4 | 08/20/2025 | 08/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | RANDOLPH | 177638 | 02368 | 4282 |  |  | Solar |  | 05_09_501L1 | 07/20/2017 | 01/11/2018 | 114 | 104 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 07/20/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 243338 | 02766 | 842 |  |  | Solar |  | 05_12_12L4 | 09/13/2019 | 10/14/2019 | 20 | 16 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/29/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 09/13/2019 | 4/26/2023 | Y | STD | 260 | 02/17/2023 | 02/16/2023 | 0 | 0 | 0 | 4/4/2023 | 4/3/2023 | 5/23/2023 | Connected |  | N
National Grid | HARVARD | 175573 | 01451 | 3720 |  |  | Solar |  | 05_07_91W41 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/12/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2015 | 10/15/2014 | 9/30/2017 | Y | STD | 843 | 06/16/2017 | 08/08/2017 | 36 | 0 | 36 | 8/9/2017 | 8/9/2017 | 8/24/2017 | Connected |  | N
National Grid | WARE | 177199 | 01082 | 3.8 |  |  | Solar |  | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/21/2017 | 8/21/2017 | 8/21/2017 | Connected |  | N
National Grid | BEVERLY | 240285 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 07/24/2019 | 07/25/2019 | 0 | 0 | 0 | 07/26/2019 | 07/26/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 10/4/2019 | N | EXP | 59 |  |  | 0 | 0 | 0 |  |  | 9/26/2019 | Connected |  | N
National Grid | BROCKTON | 174593 | 02302 | 14 |  |  | Solar |  | 05_09_527L2 | 10/28/2011 | 10/28/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 |  | 1/6/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 1/6/2012 | Connected |  | N
National Grid | BRIDGEWATER | 420913 | 02333 | 15.2 |  |  | Solar |  | 05_05_314W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 642842 | 01757 | 10 |  |  | Solar |  | 05_07_97W5 | 09/30/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 09/30/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | GRANBY | 645330 | 01033 | 7.6 |  |  | Solar |  | 05_05_8L4 | 10/07/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 10/07/2024 | 2/26/2026 | Y | EXP | 365 | 04/15/2025 | 05/20/2025 | 36 | 0 | 36 |  |  | 6/5/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 443314 | 01772 | 240 |  |  | Solar |  | 05_01_201W3 | 07/15/2022 | 07/28/2022 | 9 | 0 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | RANDOLPH | 177778 | 02368 | 8200 |  |  | Solar |  | 05_09_501L1 | 03/28/2017 | 04/18/2017 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2017 | 05/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 03/28/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 257220 | 02703 | 33.3 |  |  | Solar |  | 05_12_12L4 | 10/02/2019 | 10/17/2019 | 9 | 5 | 4 | 10/18/2019 | 10/18/2019 | 7 | 0 | 7 | 11/08/2019 | 08/18/2020 | 185 | 58 | 127 |  |  | 0 | 0 | 0 |  | 08/18/2020 | 185 | 58 | 127 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 176245 | 01451 | 5100 |  |  | Solar |  | 05_07_91W41 | 04/30/2015 | 04/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2015 | 05/08/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 177198 | 01082 | 7.6 |  |  | Solar |  | 05_07_797W23 | 02/01/2017 | 02/01/2017 | 2 | 2 | 0 | 02/03/2017 | 02/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | BEVERLY | 361359 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 06/22/2021 | 06/28/2021 | 4 | 0 | 4 | 06/29/2021 | 06/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 6/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177695 | 02302 | 11.4 |  |  | Solar |  | 05_09_527L2 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 |  | 3/26/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 430664 | 02333 | 5.04 |  |  | Solar |  | 05_05_314W2 | 06/03/2022 | 06/06/2022 | 1 | 0 | 1 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 06/03/2022 | 12/12/2023 | Y | EXP | 365 | 12/13/2022 | 01/03/2023 | 22 | 0 | 22 |  |  | 1/5/2023 | Connected |  | N
National Grid | MILFORD | 650545 | 01757 | 7.6 |  |  | Solar |  | 05_07_97W5 | 10/29/2024 | 11/07/2024 | 6 | 4 | 2 | 11/08/2024 | 11/08/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | GRANBY | 657032 | 01033 | 10 |  |  | Solar |  | 05_05_8L4 | 11/26/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 729148 | 01772 | 4995 |  |  | Other |  | 05_01_201W3 | 12/09/2025 |  | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | RANDOLPH | 177877 | 02368 | 900 |  |  | Solar |  | 05_09_501L1 | 10/17/2017 | 11/29/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 298302 | 02769 | 390 |  |  | Solar |  | 05_12_12L4 | 07/17/2020 | 10/16/2020 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 | 10/16/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 176315 | 01451 | 2610 |  |  | Solar |  | 05_07_91W41 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/04/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 | 05/08/2015 | 10/10/2017 | Y | STD | 656 | 05/05/2017 | 11/08/2017 | 124 | 0 | 124 | 11/8/2017 | 11/8/2017 | 11/15/2017 | Connected |  | N
National Grid | WARREN | 177515 | 01083 | 143.2 |  |  | Solar |  | 05_07_797W23 | 07/14/2016 | 07/14/2016 | 1 | 1 | 0 | 07/15/2016 | 07/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2016 | 07/14/2016 | 7/19/2017 | Y | EXP | 330 | 12/05/2016 | 01/05/2017 | 21 | 0 | 21 | 2/15/2017 | 2/15/2017 | 2/23/2017 | Connected |  | N
National Grid | BEVERLY | 361006 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 07/15/2021 | 07/15/2021 | 0 | 0 | 0 | 07/16/2021 | 07/16/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  | 8/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2021 | Connected |  | N
National Grid | BROCKTON | 177693 | 02302 | 7.6 |  |  | Solar |  | 05_09_527L2 | 03/21/2017 | 03/21/2017 | 5 | 5 | 0 | 03/28/2017 | 03/28/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/28/2019 | N | EXP | 729 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 643694 | 02333 | 19 |  |  | Solar |  | 05_05_314W2 | 09/30/2024 | 10/22/2024 | 16 | 14 | 2 | 10/23/2024 | 10/23/2024 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 658229 | 01757 | 5.76 |  |  | Solar |  | 05_07_97W5 | 12/03/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HADLEY | 657168 | 01075 | 5.76 |  |  | Solar |  | 05_05_8L4 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 4/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 174968 | 01772 | 27 |  |  | Solar |  | 05_01_201W3 | 09/06/2013 | 09/06/2013 | 7 | 0 | 7 | 09/18/2013 | 09/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2013 |  | 11/29/2013 | N | EXP | 38 |  |  | 0 | 0 | 0 | 11/27/2013 | 11/27/2013 | 12/27/2013 | Connected |  | N
National Grid | RANDOLPH | 177876 | 02368 | 900 |  |  | Solar |  | 05_09_501L1 | 10/17/2017 | 11/29/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 316425 | 02769 | 0 |  |  | Other |  | 05_12_12L4 | 10/07/2020 | 10/19/2020 | 6 | 0 | 6 | 10/20/2020 | 10/20/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | HARVARD | 226520 | 01451 | 4061 |  |  | Solar |  | 05_07_91W41 | 06/11/2019 | 07/02/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2019 | 07/30/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 177931 | 01585 | 7.6 |  |  | Solar |  | 05_07_797W23 | 04/20/2017 | 04/20/2017 | 7 | 7 | 0 | 05/01/2017 | 05/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 |  | 4/25/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | BEVERLY | 373774 | 01915 | 9.6 |  |  | Solar |  | 05_05_336W3 | 09/07/2021 | 01/10/2022 | 4 | 0 | 4 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 09/07/2021 | 6/2/2023 | Y | EXP | 365 | 02/01/2022 | 04/22/2022 | 81 | 0 | 81 |  |  | 6/7/2022 | Connected |  | N
National Grid | BROCKTON | 177784 | 02302 | 3.8 |  |  | Solar |  | 05_09_527L2 | 06/01/2017 | 06/01/2017 | 6 | 6 | 0 | 06/12/2017 | 06/12/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 6/7/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 674379 | 02333 | 15.356 |  |  | Solar |  | 05_05_314W2 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | MILFORD | 684073 | 01757 | 5.76 |  |  | Solar |  | 05_07_98W10 | 04/09/2025 | 08/12/2025 | 4 | 0 | 4 | 08/13/2025 | 08/13/2025 | 24 | 6 | 18 | 10/06/2025 | 10/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BELCHERTOWN | 668697 | 01033 | 10 |  |  | Solar |  | 05_05_8L4 | 01/29/2025 | 03/11/2025 | 3 | 0 | 3 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 175010 | 01772 | 1500 |  |  | Solar |  | 05_01_201W3 | 09/02/2011 | 09/02/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 |  | 11/30/2012 | N | STD | 154 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 178701 | 02368 | 5000 |  |  | Solar |  | 05_09_501L1 | 02/08/2018 | 02/08/2018 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2018 | 05/04/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 325853 | 02703 | 33.3 |  |  | Solar |  | 05_12_12L4 | 11/19/2020 | 12/05/2020 | 10 | 8 | 2 | 12/07/2020 | 12/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2021 | Connected |  | N
National Grid | HARVARD | 328433 | 01451 | 9.8 |  |  | Solar |  | 05_07_91W41 | 01/07/2021 | 01/11/2021 | 1 | 0 | 1 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 | 01/07/2021 | 6/25/2022 | Y | EXP | 365 | 06/18/2021 | 06/28/2021 | 11 | 0 | 11 |  |  | 3/29/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 178409 | 01585 | 10000 |  |  | Other |  | 05_07_797W23 | 11/22/2017 | 11/22/2017 | 89 | 82 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 430119 | 01915 | 6 |  |  | Solar |  | 05_05_336W3 | 05/23/2022 | 05/24/2022 | 1 | 0 | 1 | 05/25/2022 | 05/25/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 12/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | BROCKTON | 178133 | 02302 | 9980 |  |  | Solar |  | 05_09_527L2 | 07/12/2017 | 08/28/2017 | 32 | 32 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2017 | 09/19/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 12/21/2022 | N | STD | 1028 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 683056 | 02333 | 15.2 |  |  | Solar |  | 05_05_314W2 | 04/07/2025 | 04/10/2025 | 3 | 0 | 3 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | MILFORD | 177139 | 01757 | 7.6 |  |  | Solar |  | 05_07_98W10 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 680570 | 01033 | 15.58 |  |  | Solar |  | 05_05_8L4 | 03/26/2025 | 04/03/2025 | 7 | 3 | 4 | 04/04/2025 | 04/04/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 176175 | 01772 | 35 |  |  | Solar |  | 05_01_201W3 | 07/02/2015 | 07/02/2015 | 4 | 4 | 0 | 07/09/2015 | 07/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2015 |  | 7/7/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 12/21/2015 | Connected |  | N
National Grid | RANDOLPH | 328673 | 02368 | 0 |  |  | Solar |  | 05_09_501L1 | 12/01/2020 | 12/08/2020 | 4 | 0 | 4 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 1/12/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | Connected |  | N
National Grid | ATTLEBORO | 411748 | 02703 | 0 |  |  | Battery Add-On |  | 05_12_12L4 | 03/14/2022 | 03/28/2022 | 10 | 0 | 10 | 03/29/2022 | 03/29/2022 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 |  | 11/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | AYER | 404665 | 01432 | 0 |  |  | Solar |  | 05_07_91W41 | 01/04/2022 | 01/10/2022 | 4 | 2 | 2 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | WARREN | 178602 | 01083 | 500 |  |  | Solar |  | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2018 | 07/11/2018 | 50 | 11 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 431440 | 01915 | 7.54 |  |  | Solar |  | 05_05_336W3 | 05/19/2022 | 05/25/2022 | 3 | 2 | 1 | 05/26/2022 | 05/26/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2022 | 05/19/2022 | 12/21/2023 | Y | EXP | 365 | 10/18/2022 | 12/21/2022 | 65 | 0 | 65 |  |  | 1/11/2023 | Connected |  | N
National Grid | BRIDGEWATER | 201376 | 02333 | 10 |  |  | Solar |  | 05_09_527L2 | 11/16/2018 | 12/28/2018 | 25 | 24 | 1 | 12/31/2018 | 12/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2019 | Connected |  | N
National Grid | BRIDGEWATER | 741732 | 02333 | 7.6 |  |  | Solar |  | 05_05_314W3 | 12/22/2025 | 01/02/2026 | 6 | 5 | 1 | 01/05/2026 | 01/05/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 201105 | 01757 | 496 |  |  | Solar |  | 05_07_98W10 | 11/15/2018 | 12/06/2018 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 683213 | 01007 | 5.76 |  |  | Solar |  | 05_05_8L4 | 04/14/2025 | 04/24/2025 | 7 | 4 | 3 | 04/25/2025 | 04/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 382980 | 01772 | 3.8 |  |  | Solar |  | 05_01_201W3 | 09/19/2021 | 10/18/2021 | 20 | 19 | 1 | 10/19/2021 | 10/19/2021 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 10/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 361080 | 02368 | 9.8 |  |  | Solar |  | 05_09_501L1 | 06/01/2021 | 06/02/2021 | 0 | 0 | 0 | 06/03/2021 | 06/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2021 | 06/01/2021 | 12/17/2022 | Y | EXP | 365 | 09/11/2021 | 10/01/2021 | 21 | 0 | 21 |  |  | 8/8/2022 | Connected |  | N
National Grid | ATTLEBORO | 513872 | 02703 |  |  |  | Other |  | 05_12_12L4 | 07/13/2023 | 10/02/2023 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2023 | 11/28/2023 | 38 | 15 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 429020 | 01432 | 499 |  |  | Solar |  | 05_07_91W41 | 06/03/2022 | 07/01/2022 | 18 | 12 | 6 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 178599 | 01082 | 72 |  |  | Solar |  | 05_07_797W23 | 04/06/2018 | 04/06/2018 | 1 | 0 | 1 | 04/10/2018 | 04/10/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2018 |  | 4/14/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | BEVERLY | 521681 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 369533 | 02333 | 7.68 |  |  | Solar |  | 05_09_527L2 | 07/27/2021 | 08/03/2021 | 5 | 0 | 5 | 08/04/2021 | 08/04/2021 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 174313 | 02333 | 95 |  |  | Solar |  | 05_05_314W3 | 01/11/2012 | 01/11/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2012 |  | 5/1/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/27/2012 | 8/27/2012 | 9/10/2012 | Connected |  | Y
National Grid | MILFORD | 292050 | 01757 | 499 |  |  | Solar |  | 05_07_98W10 | 05/14/2020 | 05/29/2020 | 10 | 3 | 7 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 | 05/14/2020 | 3/29/2026 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 684218 | 01033 | 11.5 |  |  | Solar |  | 05_05_8L4 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 396935 | 01772 | 7.6 |  |  | Solar |  | 05_01_201W3 | 11/22/2021 | 01/06/2022 | 31 | 23 | 8 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 361060 | 02368 | 11.52 |  |  | Solar |  | 05_09_501L1 | 07/21/2021 | 07/22/2021 | 1 | 0 | 1 | 07/23/2021 | 07/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 590972 | 02769 | 75 |  |  | Solar |  | 05_12_12L4 | 02/19/2024 |  | 59 | 51 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 490718 | 01432 | 0 |  |  | Solar |  | 05_07_91W41 | 01/09/2023 | 01/10/2023 | 2 | 1 | 1 | 01/11/2023 | 01/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 2/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | WARE | 186356 | 01082 | 15.2 |  |  | Solar |  | 05_07_797W23 | 08/22/2018 | 10/11/2018 | 9 | 9 | 0 | 10/12/2018 | 10/12/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 08/22/2018 | 8/20/2019 | Y | EXP | 308 | 05/10/2019 | 06/05/2019 | 26 | 0 | 26 |  |  | 8/8/2019 | Connected |  | N
National Grid | BEVERLY | 556931 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 09/27/2023 | 09/28/2023 | 1 | 0 | 1 | 09/29/2023 | 09/29/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | BROCKTON | 421045 | 02302 | 10 |  |  | Solar |  | 05_09_527L2 | 03/31/2022 | 04/07/2022 | 6 | 5 | 1 | 04/08/2022 | 04/08/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 |  | 6/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | N
National Grid | BRIDGEWATER | 189184 | 02333 | 15.2 |  |  | Solar |  | 05_05_314W3 | 06/26/2018 | 06/26/2018 | 15 | 9 | 6 | 07/23/2018 | 07/23/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 368085 | 01757 | 7.6 |  |  | Solar |  | 05_07_98W10 | 07/19/2021 | 07/22/2021 | 3 | 0 | 3 | 07/23/2021 | 07/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 | 07/19/2021 | 10/30/2024 | Y | EXP | 365 | 03/01/2022 | 03/02/2022 | 2 | 0 | 2 |  |  | 11/15/2023 | Connected |  | N
National Grid | BELCHERTOWN | 687034 | 01007 | 10 |  |  | Solar |  | 05_05_8L4 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 405997 | 01772 | 0 |  |  | Battery Add-On |  | 05_01_201W3 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 05/10/2023 | 313 | 304 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 435977 | 02301 | 6 |  |  | Solar |  | 05_09_501L1 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2022 | Connected |  | N
National Grid | ATTLEBORO | 608526 | 02703 | 2.9 |  |  | Solar |  | 05_12_12L4 | 05/03/2024 | 05/28/2024 | 11 | 10 | 1 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/03/2024 | 6/24/2025 | Y | EXP | 365 | 08/20/2024 | 09/07/2024 | 19 | 0 | 19 |  |  | 9/10/2024 | Connected |  | N
National Grid | AYER | 559477 | 01432 | 7.56 |  |  | Solar |  | 05_07_91W41 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2023 | 10/27/2023 | 2/6/2025 | Y | EXP | 365 | 02/27/2024 | 04/19/2024 | 53 | 0 | 53 |  |  | 5/6/2024 | Connected |  | N
National Grid | WARE | 273621 | 01082 | 7.6 |  |  | Solar |  | 05_07_797W23 | 01/28/2020 | 02/04/2020 | 5 | 5 | 0 | 02/05/2020 | 02/05/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N
National Grid | BEVERLY | 540445 | 01915 | 6 |  |  | Solar |  | 05_05_336W3 | 07/17/2023 | 07/18/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 17 | 0 | 17 | 08/24/2023 | 09/25/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 09/25/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | BROCKTON | 488737 | 02302 | 10 |  |  | Solar |  | 05_09_527L2 | 03/16/2023 | 03/21/2023 | 3 | 1 | 2 | 03/22/2023 | 03/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2023 | 03/16/2023 | 6/25/2024 | Y | EXP | 365 | 06/09/2023 | 06/23/2023 | 15 | 0 | 15 |  |  | 6/29/2023 | Connected |  | N
National Grid | BRIDGEWATER | 202461 | 02333 | 75 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 389731 | 01757 | 0 |  |  | Other |  | 05_07_98W10 | 11/10/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 694429 | 01007 | 13.36 |  |  | Solar |  | 05_05_8L4 | 05/28/2025 | 07/15/2025 | 2 | 0 | 2 | 07/22/2025 | 07/22/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 410227 | 01772 | 3.8 |  |  | Solar |  | 05_01_201W3 | 02/03/2022 | 02/08/2022 | 4 | 3 | 1 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 505468 | 02301 | 17.6 |  |  | Solar |  | 05_09_501L1 | 03/01/2023 | 03/15/2023 | 11 | 10 | 1 | 03/16/2023 | 03/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 4/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2023 | Connected |  | N
National Grid | REHOBOTH | 621340 | 02769 | 90 |  |  | Solar |  | 05_12_12L4 | 06/28/2024 | 08/15/2024 | 33 | 24 | 9 | 08/16/2024 | 08/16/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 4/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | AYER | 544773 | 01432 | 15.2 |  |  | Solar |  | 05_07_91W41 | 07/31/2023 | 08/03/2023 | 3 | 0 | 3 | 08/04/2023 | 08/04/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 9/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N
National Grid | WARE | 300143 | 01082 | 9.8 |  |  | Solar |  | 05_07_797W23 | 09/16/2020 | 09/21/2020 | 2 | 0 | 2 | 09/22/2020 | 09/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/16/2020 | 1/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N
National Grid | BEVERLY | 552467 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 08/31/2023 | 09/05/2023 | 2 | 0 | 2 | 09/06/2023 | 09/06/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 11/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2024 | Connected |  | N
National Grid | WHITMAN | 528945 | 02382 | 15.08 |  |  | Solar |  | 05_09_527L2 | 09/25/2023 | 06/02/2023 | 5 | 2 | 3 | 10/03/2023 | 10/03/2023 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N
National Grid | BRIDGEWATER | 202201 | 02333 | 120 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 431649 | 01757 | 0 |  |  | Battery Add-On |  | 05_07_98W10 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 701732 | 01033 | 15.96 |  |  | Solar |  | 05_05_8L4 | 06/27/2025 | 07/02/2025 | 3 | 0 | 3 | 07/03/2025 | 07/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | WESTBOROUGH | 424633 | 01581 | 15.2 |  |  | Solar |  | 05_01_201W3 | 05/04/2022 | 05/12/2022 | 6 | 5 | 1 | 05/13/2022 | 05/13/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2023 | Connected |  | N
National Grid | BROCKTON | 516139 | 02301 | 20 |  |  | Solar |  | 05_09_501L1 | 03/31/2023 | 04/03/2023 | 1 | 0 | 1 | 04/04/2023 | 04/04/2023 | 132 | 113 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 644325 | 02769 | 10 |  |  | Solar |  | 05_12_12L4 | 10/02/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/02/2024 | 12/12/2025 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 606032 | 01432 | 5.76 |  |  | Solar |  | 05_07_91W41 | 04/23/2024 | 05/07/2024 | 9 | 6 | 3 | 05/08/2024 | 05/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 330658 | 01082 | 10 |  |  | Solar |  | 05_07_797W23 | 12/09/2020 | 01/07/2021 | 19 | 14 | 5 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2021 | Connected |  | N
National Grid | BEVERLY | 592714 | 01915 | 14.175 |  |  | Solar |  | 05_05_336W3 | 03/08/2024 | 03/14/2024 | 4 | 1 | 3 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 03/08/2024 | 5/31/2025 | Y | EXP | 365 | 07/02/2024 | 08/06/2024 | 36 | 0 | 36 |  |  | 8/20/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 541261 | 02333 | 0 |  |  | Battery Add-On |  | 05_09_527L2 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 98 | 77 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2025 | Connected |  | N
National Grid | BRIDGEWATER | 203268 | 02333 | 105 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 437699 | 01757 | 0 |  |  | Battery Add-On |  | 05_07_98W10 | 08/02/2022 | 08/12/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 706851 | 01007 | 15.76 |  |  | Solar |  | 05_05_8L4 | 08/06/2025 | 08/11/2025 | 3 | 0 | 3 | 08/12/2025 | 08/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | WESTBOROUGH | 437610 | 01581 | 3.8 |  |  | Solar |  | 05_01_201W3 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 | 06/14/2022 | 8/25/2023 | Y | EXP | 365 | 09/14/2022 | 09/28/2022 | 15 | 0 | 15 |  |  | 10/5/2022 | Connected |  | N
National Grid | BROCKTON | 635553 | 02301 | 5.76 |  |  | Solar |  | 05_09_501L1 | 08/26/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 08/26/2024 | 12/5/2025 | Y | EXP | 365 | 03/05/2025 | 04/30/2025 | 57 | 0 | 57 |  |  | 5/7/2025 | Connected |  | N
National Grid | REHOBOTH | 174665 | 02769 | 230 |  |  | Solar |  | 05_12_12L6 | 12/12/2012 | 12/12/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/12/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/15/2013 | Connected |  | N
National Grid | AYER | 256585 | 01432 | 7.6 |  |  | Solar |  | 05_07_91W42 | 10/17/2019 | 10/21/2019 | 2 | 1 | 1 | 10/22/2019 | 10/22/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 | 10/17/2019 | 6/9/2021 | Y | EXP | 365 | 01/14/2020 | 01/13/2020 | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | WARE | 340873 | 01082 | 15.2 |  |  | Solar |  | 05_07_797W23 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 | 02/05/2021 | 8/9/2023 | Y | EXP | 365 | 06/03/2022 | 06/28/2022 | 25 | 0 | 25 |  |  | 9/30/2022 | Connected |  | N
National Grid | BEVERLY | 603626 | 01915 | 2.32 |  |  | Solar |  | 05_05_336W3 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2024 | Connected |  | N
National Grid | BRIDGEWATER | 550526 | 02333 | 0 |  |  | Solar |  | 05_09_527L2 | 08/31/2023 | 09/12/2023 | 8 | 6 | 2 | 09/13/2023 | 09/13/2023 | 59 | 40 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 203267 | 02333 | 105 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 597159 | 01757 | 6 |  |  | Solar |  | 05_07_98W10 | 04/05/2024 | 04/23/2024 | 11 | 8 | 3 | 04/24/2024 | 04/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 728165 | 01033 | 13.36 |  |  | Solar |  | 05_05_8L4 | 10/25/2025 | 10/27/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 669239 | 01581 | 5.76 |  |  | Solar |  | 05_01_201W3 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 647481 | 02301 | 7.6 |  |  | Solar |  | 05_09_501L1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/24/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174664 | 02703 | 110 |  |  | Solar |  | 05_12_12L6 | 12/12/2012 | 12/12/2012 | 8 | 0 | 8 | 12/27/2012 | 12/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2013 | 12/12/2012 | 4/30/2013 | Y | EXP | 55 |  |  | 0 | 0 | 0 | 8/7/2013 | 8/7/2013 | 8/15/2013 | Connected |  | Y
National Grid | AYER | 371375 | 01432 | 7.6 |  |  | Solar |  | 05_07_91W42 | 08/13/2021 | 08/18/2021 | 3 | 0 | 3 | 08/19/2021 | 08/19/2021 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2021 | 08/13/2021 | 9/25/2023 | Y | EXP | 365 | 02/15/2022 | 04/25/2022 | 70 | 0 | 70 |  |  | 11/3/2022 | Connected |  | N
National Grid | WARE | 485389 | 01082 | 7.6 |  |  | Solar |  | 05_07_797W23 | 12/29/2022 | 01/03/2023 | 2 | 0 | 2 | 01/04/2023 | 01/04/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 606160 | 01915 | 3.8 |  |  | Solar |  | 05_05_336W3 | 04/23/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/23/2024 | 6/3/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 8/29/2024 | Connected |  | N
National Grid | BROCKTON | 601385 | 02302 | 6 |  |  | Solar |  | 05_09_527L2 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/15/2024 | 5/24/2025 | Y | EXP | 365 | 08/20/2024 | 10/01/2024 | 43 | 0 | 43 |  |  | 10/8/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 203266 | 02333 | 60 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 646596 | 01757 | 10 |  |  | Solar |  | 05_07_98W10 | 10/25/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/25/2024 | 12/28/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | BELCHERTOWN | 713209 | 01007 | 5.76 |  |  | Solar |  | 05_05_9L1 | 08/19/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 671932 | 01581 | 5.76 |  |  | Solar |  | 05_01_201W4 | 02/13/2025 | 06/27/2025 | 54 | 53 | 1 | 08/26/2025 | 08/26/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 | 02/13/2025 | 10/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BROCKTON | 701029 | 02301 | 5.8 |  |  | Solar |  | 05_09_501L1 | 06/25/2025 | 07/09/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/25/2025 | 8/8/2026 | Y | EXP | 365 | 10/02/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 12/2/2025 | Connected |  | N
National Grid | REHOBOTH | 177018 | 02769 | 60 |  |  | Solar |  | 05_12_12L6 | 01/09/2017 | 01/09/2017 | 4 | 4 | 0 | 01/13/2017 | 01/13/2017 | 37 | 37 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2017 |  | 8/1/2018 | N | EXP | 510 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 402619 | 01432 | 3.84 |  |  | Solar |  | 05_07_91W42 | 01/24/2022 | 02/02/2022 | 7 | 0 | 7 | 02/03/2022 | 02/03/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 |  | 3/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2022 | Connected |  | N
National Grid | WARE | 491623 | 01082 | 7.6 |  |  | Solar |  | 05_07_797W23 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | BEVERLY | 617495 | 01915 | 11.5 |  |  | Solar |  | 05_05_336W3 | 06/18/2024 | 06/21/2024 | 2 | 0 | 2 | 06/24/2024 | 06/24/2024 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 610562 | 02333 | 8.99 |  |  | Solar |  | 05_09_527L2 | 05/13/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/13/2024 | 7/8/2025 | Y | EXP | 365 | 07/26/2024 | 07/31/2024 | 6 | 0 | 6 |  |  | 8/7/2024 | Connected |  | N
National Grid | BRIDGEWATER | 203263 | 02333 | 90 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 659860 | 01757 | 7.6 |  |  | Solar |  | 05_07_98W10 | 12/11/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/11/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | GRANBY | 720985 | 01033 | 3.8 |  |  | Solar |  | 05_05_9L1 | 09/22/2025 | 11/24/2025 | 23 | 20 | 3 | 11/25/2025 | 11/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 12/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 175712 | 01581 | 5600 |  |  | Natural Gas |  | 05_01_201W4 | 10/23/2014 | 10/23/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2014 | 11/14/2014 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 10/23/2014 | 12/31/2016 | Y | STD | 614 | 07/09/2015 | 08/13/2015 | 25 | 0 | 25 | 12/2/2015 | 12/2/2015 | 12/9/2015 | Connected |  | N
National Grid | BROCKTON | 191401 | 02301 | 1371 |  |  | Solar |  | 05_09_501L2 | 01/09/2019 | 01/28/2019 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2019 | 02/20/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 177117 | 02703 | 360 |  |  | Solar |  | 05_12_12L6 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 565340 | 01432 | 10 |  |  | Solar |  | 05_07_91W42 | 11/27/2023 | 11/30/2023 | 3 | 0 | 3 | 12/01/2023 | 12/01/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/27/2023 | 2/19/2025 | Y | EXP | 365 | 04/25/2024 | 05/03/2024 | 9 | 0 | 9 |  |  | 5/13/2024 | Connected |  | N
National Grid | WARE | 563367 | 01082 | 4980 |  |  | Solar |  | 05_07_797W23 | 02/28/2024 | 04/11/2024 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2024 | 04/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 624049 | 01915 | 0 |  |  | Solar |  | 05_05_336W3 | 07/11/2024 | 07/17/2024 | 4 | 0 | 4 | 07/18/2024 | 07/18/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/11/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2024 | Connected |  | N
National Grid | BROCKTON | 661566 | 02302 | 23 |  |  | Battery Add-On |  | 05_09_527L2 | 12/18/2024 | 12/30/2024 | 8 | 5 | 3 | 12/31/2024 | 12/31/2024 | 85 | 25 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 203260 | 02333 | 60 |  |  | Solar |  | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 674682 | 01757 | 5.76 |  |  | Solar |  | 05_07_98W10 | 02/27/2025 | 05/22/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 732094 | 01007 | 10 |  |  | Solar |  | 05_05_9L1 | 11/06/2025 | 11/07/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 175959 | 01581 | 989 |  |  | Solar |  | 05_01_201W4 | 06/03/2015 | 06/03/2015 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2015 | 07/01/2015 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 03/15/2016 | 06/15/2016 | 63 | 18 | 45 | 4/18/2016 | 06/03/2015 | 6/30/2016 | Y | STD | -326 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 10/26/2017 | Connected |  | N
National Grid | BROCKTON | 191399 | 02301 | 996 |  |  | Solar |  | 05_09_501L2 | 01/04/2019 | 01/29/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 244619 | 02703 | 115.2 |  |  | Solar |  | 05_12_12L6 | 07/22/2019 | 08/21/2019 | 20 | 14 | 6 | 08/22/2019 | 08/22/2019 | 26 | 17 | 9 | 01/22/2020 | 05/05/2020 | 64 | 54 | 10 |  |  | 0 | 0 | 0 |  | 05/05/2020 | 64 | 54 | 10 |  |  | 0 | 0 | 0 | 5/27/2020 |  | 5/2/2022 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 589554 | 01432 | 9.8 |  |  | Solar |  | 05_07_91W42 | 02/21/2024 | 03/29/2024 | 27 | 24 | 3 | 04/01/2024 | 04/01/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 02/21/2024 | 12/13/2025 | Y | EXP | 365 | 06/27/2024 | 07/25/2024 | 29 | 0 | 29 |  |  | 3/17/2025 | Connected |  | N
National Grid | WARE | 572096 | 01082 | 13.05 |  |  | Solar |  | 05_07_797W23 | 01/22/2024 | 01/29/2024 | 6 | 4 | 2 | 01/30/2024 | 01/30/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 629702 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 08/02/2024 | 08/30/2024 | 12 | 7 | 5 | 09/03/2024 | 09/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 669000 | 02302 | 7.36 |  |  | Solar |  | 05_09_527L2 | 01/30/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | BRIDGEWATER | 222595 | 02333 | 432 |  |  | Solar |  | 05_05_314W3 | 04/25/2019 | 05/03/2019 | 6 | 5 | 1 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 | 04/25/2019 | 12/12/2024 | Y | STD | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 719822 | 01757 | 15.2 |  |  | Solar |  | 05_07_98W10 | 09/23/2025 | 09/29/2025 | 3 | 1 | 2 | 09/30/2025 | 09/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GRANBY | 738070 | 01033 | 3.8 |  |  | Solar |  | 05_05_9L1 | 12/04/2025 | 12/17/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 310063 | 01581 | 10 |  |  | Solar |  | 05_01_201W4 | 09/01/2020 | 09/02/2020 | 0 | 0 | 0 | 09/03/2020 | 09/03/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | BROCKTON | 178170 | 02301 | 1746 |  |  | Solar |  | 05_09_501L2 | 03/23/2018 | 04/18/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | REHOBOTH | 593565 | 02769 | 67.3 |  |  | Solar |  | 05_12_1381 | 02/29/2024 | 04/01/2024 | 23 | 13 | 10 | 04/02/2024 | 04/02/2024 | 32 | 20 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 602878 | 01432 | 4.06 |  |  | Solar |  | 05_07_91W42 | 04/09/2024 | 05/10/2024 | 3 | 2 | 1 | 05/13/2024 | 05/13/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 | 04/09/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WARE | 586841 | 01082 | 15.2 |  |  | Solar |  | 05_07_797W23 | 01/31/2024 | 02/26/2024 | 17 | 15 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N
National Grid | BEVERLY | 630813 | 01915 | 22.42 |  |  | Solar |  | 05_05_336W3 | 08/07/2024 | 08/08/2024 | 1 | 0 | 1 | 08/09/2024 | 08/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 8/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | BROCKTON | 669322 | 02302 | 0 |  |  | Battery Add-On |  | 05_09_527L2 | 01/31/2025 | 02/03/2025 | 1 | 0 | 1 | 02/04/2025 | 02/04/2025 | 61 | 46 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 452283 | 02333 | 100 |  |  | Solar |  | 05_05_314W3 | 09/01/2022 | 09/19/2022 | 11 | 2 | 9 | 09/20/2022 | 09/20/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 | 09/01/2022 | 4/15/2024 | Y | EXP | 119 | 09/15/2023 | 02/08/2024 | 146 | 145 | 1 |  |  | 4/9/2024 | Connected |  | N
National Grid | MILFORD | 441919 | 01757 | 999 |  |  | Solar |  | 05_07_98W19 | 09/07/2022 | 10/11/2022 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 | 11/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELCHERTOWN | 176386 | 01007 | 10 |  |  | Solar |  | 05_05_9L1 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2016 |  | 2/6/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | WESTBOROUGH | 317230 | 01581 | 10 |  |  | Solar |  | 05_01_201W4 | 12/18/2020 | 12/30/2020 | 6 | 0 | 6 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 368904 | 02301 | 0 |  |  | Other |  | 05_09_501L2 | 01/24/2022 | 05/02/2022 | 68 | 59 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2022 | 07/11/2022 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 587964 | 02703 | 250 |  |  | Natural Gas |  | 05_12_1383 | 03/07/2024 | 08/06/2024 | 104 | 95 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 606767 | 01432 | 5.76 |  |  | Solar |  | 05_07_91W42 | 04/25/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 6/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | WARE | 594128 | 01082 | 12.915 |  |  | Solar |  | 05_07_797W23 | 03/21/2024 | 03/27/2024 | 4 | 2 | 2 | 03/28/2024 | 03/28/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | BEVERLY | 643421 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 09/27/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 09/27/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | BROCKTON | 686247 | 02302 | 11.5 |  |  | Solar |  | 05_09_527L2 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | BRIDGEWATER | 648892 | 02333 | 10 |  |  | Solar |  | 05_05_314W3 | 11/01/2024 | 01/08/2025 | 38 | 34 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | MILFORD | 544370 | 01757 | 4999 |  |  | Solar |  | 05_07_98W19 | 08/29/2023 | 01/09/2024 | 89 | 83 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2024 | 02/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | GRANBY | 176410 | 01033 | 10 |  |  | Solar |  | 05_05_9L1 | 05/09/2016 | 05/09/2016 | 1 | 1 | 0 | 05/12/2016 | 05/12/2016 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/16/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 392812 | 01581 | 15.2 |  |  | Solar |  | 05_01_201W4 | 11/02/2021 |  | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 588156 | 02301 | 4980 |  |  | Solar |  | 05_09_501L2 | 04/12/2024 | 12/30/2024 | 176 | 166 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 12/29/2025 | 248 | 229 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 175090 | 02703 | 15 |  |  | Solar |  | 05_12_1385 | 07/29/2011 | 07/29/2011 | 322 | 65 | 257 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GROTON | 651638 | 01472 | 7.6 |  |  | Solar |  | 05_07_91W42 | 11/13/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WARE | 598158 | 01082 | 10 |  |  | Solar |  | 05_07_797W23 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | BEVERLY | 645301 | 01915 | 7.6 |  |  | Solar |  | 05_05_336W3 | 10/07/2024 | 10/30/2024 | 2 | 0 | 2 | 10/31/2024 | 10/31/2024 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | BROCKTON | 713614 | 02302 | 11.4 |  |  | Solar |  | 05_09_604W1 | 08/28/2025 | 09/23/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/28/2025 | 12/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | EAST BRIDGEWATER | 654182 | 02333 | 5.76 |  |  | Solar |  | 05_05_314W3 | 11/18/2024 | 12/20/2024 | 3 | 0 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 176978 | 01757 | 112 |  |  | Solar |  | 05_07_98W19 | 12/27/2016 | 12/27/2016 | 2 | 1 | 1 | 12/30/2016 | 12/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 |  | 1/2/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/5/2017 | 5/5/2017 | 5/5/2017 | Connected |  | N
National Grid | GRANBY | 176612 | 01033 | 250 |  |  | Solar |  | 05_05_9L1 | 02/12/2016 | 02/12/2016 | 10 | 10 | 0 | 03/01/2016 | 03/01/2016 | 0 | 0 | 0 | 08/24/2016 | 09/21/2016 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 09/21/2016 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 5/12/2017 | N | EXP | 179 |  |  | 0 | 0 | 0 | 5/2/2017 | 5/2/2017 | 5/12/2017 | Connected |  | N
National Grid | WESTBOROUGH | 477550 | 01581 | 7.83 |  |  | Solar |  | 05_01_201W4 | 01/25/2023 | 02/09/2023 | 12 | 10 | 2 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 602603 | 02301 | 11.4 |  |  | Solar |  | 05_09_501L2 | 04/08/2024 | 06/21/2024 | 38 | 36 | 2 | 07/24/2025 | 07/24/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 04/08/2024 | 11/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | ATTLEBORO | 176864 | 02703 | 26.75 |  |  | Solar |  | 05_12_1385 | 01/21/2016 | 01/21/2016 | 4 | 4 | 0 | 01/27/2016 | 01/27/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/26/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 681001 | 01432 | 4.56 |  |  | Solar |  | 05_07_91W42 | 03/27/2025 | 04/24/2025 | 3 | 0 | 3 | 04/25/2025 | 04/25/2025 | 47 | 33 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 597731 | 01082 | 10.44 |  |  | Solar |  | 05_07_797W23 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | BEVERLY | 649472 | 01915 | 10 |  |  | Solar |  | 05_05_336W3 | 11/07/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/07/2024 | 1/2/2026 | Y | EXP | 365 | 01/23/2025 | 02/13/2025 | 22 | 0 | 22 |  |  | 3/11/2025 | Connected |  | N
National Grid | BROCKTON | 174176 | 02302 | 500 |  |  | Solar |  | 05_09_604W1 | 03/04/2012 | 03/04/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 597738 | 02333 | 120 |  |  | Solar |  | 05_05_314W4 | 04/18/2024 | 05/03/2024 | 12 | 3 | 9 |  |  | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MILFORD | 176969 | 01757 | 540 |  |  | Solar |  | 05_07_98W19 | 10/04/2016 | 10/04/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2016 | 11/07/2016 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 | 10/04/2016 | 6/26/2018 | Y | STD | 446 | 12/01/2017 | 06/12/2018 | 193 | 0 | 193 | 4/5/2018 | 4/5/2018 | 6/22/2018 | Connected |  | N
National Grid | GRANBY | 177494 | 01033 | 3.8 |  |  | Solar |  | 05_05_9L1 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 |  | 12/19/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 548714 | 01581 | 7.6 |  |  | Solar |  | 05_01_201W4 | 08/28/2023 | 08/30/2023 | 2 | 0 | 2 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/28/2023 | 11/3/2024 | Y | EXP | 365 | 05/29/2024 | 06/04/2024 | 7 | 0 | 7 |  |  | 6/18/2024 | Connected |  | N
National Grid | BROCKTON | 676477 | 02301 | 249 |  |  | Solar |  | 05_09_501L2 | 03/27/2025 | 09/08/2025 | 67 | 57 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 683610 | 02703 | 20 |  |  | Solar |  | 05_12_1385 | 04/09/2025 | 04/30/2025 | 4 | 0 | 4 | 05/01/2025 | 05/01/2025 | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 692993 | 01464 | 3.8 |  |  | Solar |  | 05_07_91W42 | 05/23/2025 | 07/15/2025 | 3 | 0 | 3 | 08/04/2025 | 08/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 616189 | 01082 | 5.76 |  |  | Solar |  | 05_07_797W23 | 06/06/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 | 06/06/2024 | 8/1/2025 | Y | EXP | 365 | 09/03/2024 | 02/28/2025 | 179 | 0 | 179 |  |  | 2/28/2025 | Connected |  | N
National Grid | LYNN | 650647 | 01902 | 10 |  |  | Solar |  | 05_05_336W3 | 10/31/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2025 | Connected |  | N
National Grid | BROCKTON | 174175 | 02302 | 500 |  |  | Solar |  | 05_09_604W1 | 03/04/2012 | 03/04/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 597594 | 02333 | 120 |  |  | Solar |  | 05_05_314W4 | 03/18/2024 | 04/22/2024 | 24 | 16 | 8 |  |  | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MILFORD | 447289 | 01757 | 6 |  |  | Solar |  | 05_07_98W19 | 01/29/2024 | 08/16/2022 | 8 | 4 | 4 | 02/09/2024 | 02/09/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRANBY | 177875 | 01033 | 120 |  |  | Solar |  | 05_05_9L1 | 08/15/2017 | 08/15/2017 | 12 | 12 | 0 | 08/31/2017 | 08/31/2017 | 142 | 3 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2017 |  | 8/20/2018 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 565211 | 01581 | 0 |  |  | Solar |  | 05_01_201W4 | 10/23/2023 | 10/24/2023 | 1 | 0 | 1 | 10/25/2023 | 10/25/2023 | 50 | 29 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 2/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | BROCKTON | 676470 | 02301 | 249 |  |  | Solar |  | 05_09_501L2 | 03/26/2025 | 09/05/2025 | 60 | 50 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 529508 | 02703 | 10 |  |  | Solar |  | 05_12_1388 | 06/07/2023 |  | 46 | 35 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 701723 | 01432 | 9.5 |  |  | Solar |  | 05_07_91W42 | 06/27/2025 | 07/11/2025 | 8 | 3 | 5 | 07/31/2025 | 07/31/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/27/2025 | 9/15/2026 | Y | EXP | 365 | 10/28/2025 | 11/12/2025 | 16 | 0 | 16 |  |  | 11/12/2025 | Connected |  | N
National Grid | HARDWICK | 626085 | 01031 | 10 |  |  | Solar |  | 05_07_797W23 | 07/23/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | LYNN | 657455 | 01901 | 3.8 |  |  | Solar |  | 05_05_336W3 | 11/27/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174191 | 02302 | 1750 |  |  | Solar |  | 05_09_604W1 | 03/15/2012 | 03/15/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 702409 | 02333 | 5.76 |  |  | Solar |  | 05_05_314W4 | 07/02/2025 | 10/14/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILFORD | 571236 | 01757 | 9.984 |  |  | Solar |  | 05_07_98W19 | 11/14/2023 | 11/20/2023 | 4 | 3 | 1 | 11/21/2023 | 11/21/2023 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/14/2023 | 3/7/2025 | Y | EXP | 365 | 04/23/2024 | 05/14/2024 | 22 | 0 | 22 |  |  | 5/23/2024 | Connected |  | N
National Grid | GRANBY | 184255 | 01033 | 7.6 |  |  | Solar |  | 05_05_9L1 | 06/11/2018 | 06/11/2018 | 13 | 3 | 10 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  | 7/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | WESTBOROUGH | 662637 | 01581 | 11.5 |  |  | Solar |  | 05_01_201W4 | 12/26/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WEST BRIDGEWATER | 690066 | 02379 | 996 |  |  | Solar |  | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 535794 | 02703 | 8.8 |  |  | Solar |  | 05_12_1388 | 08/10/2023 | 08/16/2023 | 5 | 2 | 3 | 08/17/2023 | 08/17/2023 | 106 | 43 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AYER | 632735 | 01432 | 7.6 |  |  | Solar |  | 05_07_91W43 | 10/01/2024 | 04/23/2025 | 23 | 21 | 2 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 10/01/2024 | 7/2/2026 | Y | EXP | 365 | 10/01/2025 | 10/09/2025 | 9 | 0 | 9 |  |  |  | Completion Documents |  | N
National Grid | WARE | 648326 | 01082 | 3.8 |  |  | Solar |  | 05_07_797W23 | 10/21/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | LYNN | 664785 | 01901 | 11.5 |  |  | Solar |  | 05_05_336W3 | 01/09/2025 | 01/10/2025 | 1 | 0 | 1 | 01/13/2025 | 01/13/2025 | 113 | 33 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174324 | 02302 | 2000 |  |  | Solar |  | 05_09_604W1 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 | 01/13/2012 | 12/31/2012 | Y | STD | -158 |  |  | 0 | 0 | 0 | 5/28/2014 | 5/28/2014 | 5/29/2014 | Connected |  | N
National Grid | BRIDGEWATER | 724347 | 02333 | 11.4 |  |  | Solar |  | 05_05_314W4 | 10/06/2025 | 10/14/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MILFORD | 637880 | 01757 | 5.76 |  |  | Solar |  | 05_07_98W19 | 09/05/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 09/05/2024 | 1/10/2026 | Y | EXP | 365 | 12/03/2024 | 02/15/2025 | 74 | 0 | 74 |  |  | 9/11/2025 | Connected |  | N
National Grid | PETERSHAM | 189370 | 01366 | 5 |  |  | Solar |  | 05_05_9L1 | 07/05/2018 | 07/05/2018 | 6 | 0 | 6 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2018 |  | 8/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | WESTBOROUGH | 705319 | 01581 | 50 |  |  | Solar |  | 05_01_201W4 | 07/21/2025 | 08/29/2025 | 26 | 24 | 2 | 09/02/2025 | 09/02/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | Y
National Grid | BROCKTON | 690063 | 02301 | 996 |  |  | Solar |  | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 639873 | 02703 | 5.76 |  |  | Solar |  | 05_12_1389 | 09/13/2024 | 10/01/2024 | 3 | 0 | 3 | 10/02/2024 | 10/02/2024 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | AYER | 643789 | 01432 | 75 |  |  | Solar |  | 05_07_91W43 | 12/03/2024 | 02/19/2025 | 52 | 43 | 9 | 02/20/2025 | 02/20/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HARDWICK | 648691 | 01031 | 10 |  |  | Solar |  | 05_07_797W23 | 11/04/2024 | 12/04/2024 | 16 | 11 | 5 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 682310 | 01901 | 23 |  |  | Solar |  | 05_05_336W3 | 04/04/2025 | 04/11/2025 | 5 | 0 | 5 | 04/14/2025 | 04/14/2025 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174911 | 02302 | 3000 |  |  | Solar |  | 05_09_604W1 | 09/17/2012 | 09/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 174880 | 02333 | 250.8 |  |  | Solar |  | 05_05_314W4 | 02/14/2013 | 02/14/2013 | 7 | 2 | 5 | 02/27/2013 | 02/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2013 | 02/14/2013 | 10/1/2013 | Y | EXP | -7 | 11/19/2013 | 03/15/2014 | 79 | 0 | 79 | 11/20/2014 | 11/20/2014 | 12/2/2014 | Connected |  | N
National Grid | MILFORD | 641187 | 01757 | 10 |  |  | Solar |  | 05_07_98W19 | 09/27/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 245118 | 01366 | 0 |  |  | Solar |  | 05_05_9L1 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 690058 | 01581 | 996 |  |  | Solar |  | 05_09_501L2 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 205221 | 02301 | 33.3 |  |  | Solar |  | 05_12_1391 | 01/04/2019 | 01/07/2019 | 1 | 1 | 0 | 01/08/2019 | 01/08/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 1/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2021 | Connected |  | N
National Grid | ATTLEBORO | 660767 | 02703 | 6 |  |  | Solar |  | 05_07_91W43 | 12/16/2024 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 24 | 0 | 24 | 05/27/2025 | 06/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 06/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 10/15/2026 | N | EXP | 365 | 10/04/2025 | 10/09/2025 | 6 | 0 | 6 |  |  |  | Completion Documents |  | N
National Grid | AYER | 650281 | 01432 | 10 |  |  | Solar |  | 05_07_797W23 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WARE | 692666 | 01082 | 15.2 |  |  | Solar |  | 05_05_336W3 | 05/27/2025 | 06/24/2025 | 18 | 14 | 4 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | LYNN | 175234 | 01901 | 480 |  |  | Solar |  | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 740 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | BROCKTON | 176836 | 02302 | 3.75 |  |  | Solar |  | 05_05_314W4 | 02/29/2016 | 02/29/2016 | 5 | 5 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/6/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | BRIDGEWATER | 564164 | 02333 | 499 |  |  | Solar |  | 05_07_98W44 | 07/03/2024 | 03/14/2025 | 172 | 162 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2025 | 04/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 319753 | 01757 | 2.4 |  |  | Solar |  | 05_05_9L1 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 5/7/2022 | Y | EXP | 520 | 09/17/2021 | 10/15/2021 | 29 | 0 | 29 |  |  | 5/6/2022 | Connected |  | N
National Grid | PETERSHAM | 437404 | 01366 | 0 |  |  | Other |  | 05_01_207W1 | 09/26/2022 | 10/27/2022 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 11/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 697477 | 01581 | 996 |  |  | Solar |  | 05_09_501L2 | 07/07/2025 | 07/30/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 175112 | 02301 | 100 |  |  | Solar |  | 05_12_1393 | 10/09/2013 | 10/09/2013 | 8 | 2 | 6 | 10/23/2013 | 10/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2013 |  | 9/1/2014 | N | EXP | 285 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 7/25/2014 | Connected |  | N
National Grid | ATTLEBORO | 721378 | 02703 | 5.76 |  |  | Solar |  | 05_07_91W43 | 10/01/2025 | 10/08/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | AYER | 655063 | 01432 | 10 |  |  | Solar |  | 05_07_797W23 | 11/18/2024 | 12/09/2024 | 2 | 0 | 2 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/18/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | WARE | 695290 | 01082 | 5.76 |  |  | Solar |  | 05_05_336W3 | 05/30/2025 | 06/20/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | LYNN | 175233 | 01902 | 480 |  |  | Solar |  | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 740 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | BROCKTON | 176928 | 02302 | 32.4 |  |  | Solar |  | 05_05_314W4 | 11/20/2015 | 11/20/2015 | 16 | 16 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 11/25/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/11/2017 | Connected |  | N
National Grid | EAST BRIDGEWATER | 174410 | 02333 | 1750 |  |  | Solar |  | 05_07_98W44 | 06/19/2012 | 06/19/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2012 | 10/04/2012 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2013 | 06/19/2012 | 11/1/2012 | Y | STD | -112 | 01/11/2013 | 04/16/2013 | 56 | 0 | 56 | 11/20/2013 | 11/20/2013 | 12/6/2013 | Connected |  | Y
National Grid | MILFORD | 324117 | 01757 | 133.2 |  |  | Solar |  | 05_05_9L1 | 11/12/2020 | 12/08/2020 | 16 | 12 | 4 | 12/09/2020 | 12/09/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2021 |  | 11/19/2022 | N | EXP | 386 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 198460 | 01366 | 7.6 |  |  | Solar |  | 05_01_207W1 | 10/12/2018 | 11/20/2018 | 22 | 21 | 1 | 11/21/2018 | 11/21/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 697433 | 01532 | 996 |  |  | Solar |  | 05_09_501L2 | 07/07/2025 | 08/01/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2025 | 08/28/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 175379 | 02301 | 75 |  |  | Natural Gas |  | 05_12_1393 | 07/08/2014 | 07/08/2014 | 6 | 6 | 0 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2014 |  | 11/28/2014 | N | EXP | 98 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 1/5/2015 | Connected |  | Y
National Grid | ATTLEBORO | 187893 | 02703 | 11.4 |  |  | Solar |  | 05_07_91W43 | 06/25/2018 | 06/25/2018 | 3 | 0 | 3 | 07/02/2018 | 07/02/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 |  | 1/27/2020 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  | 1/3/2020 | Connected |  | N
National Grid | SHIRLEY | 677765 | 01464 | 11.5 |  |  | Solar |  | 05_07_797W23 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | HARDWICK | 699425 | 01031 | 17.4 |  |  | Solar |  | 05_05_336W3 | 06/24/2025 | 07/08/2025 | 3 | 0 | 3 | 07/09/2025 | 07/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175232 | 01902 | 480 |  |  | Solar |  | 05_09_604W1 | 06/17/2014 | 06/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/22/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 06/17/2014 | 12/31/2016 | Y | STD | 740 | 09/03/2015 | 12/02/2015 | 60 | 0 | 60 | 11/30/2015 | 11/30/2015 | 12/30/2015 | Connected |  | N
National Grid | BROCKTON | 176933 | 02301 | 72 |  |  | Solar |  | 05_05_314W4 | 01/28/2016 | 01/28/2016 | 4 | 4 | 0 | 02/03/2016 | 02/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/2/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 8/12/2016 | Connected |  | N
National Grid | EAST BRIDGEWATER | 175515 | 02333 | 250 |  |  | Solar |  | 05_07_98W44 | 03/28/2014 | 03/28/2014 | 6 | 0 | 6 | 04/08/2014 | 04/08/2014 | 548 | 3 | 545 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 |  | 12/31/2016 | N | EXP | 982 |  |  | 0 | 0 | 0 | 6/29/2015 | 6/29/2015 |  | Withdrawn |  | Y
National Grid | MILFORD | 353933 | 01757 | 200 |  |  | Solar |  | 05_05_9L1 | 07/14/2021 | 08/10/2021 | 19 | 10 | 9 | 08/11/2021 | 08/11/2021 | 27 | 3 | 24 | 12/09/2021 | 09/15/2023 | 443 | 40 | 403 |  |  | 0 | 0 | 0 |  | 09/15/2023 | 443 | 40 | 403 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 240618 | 01005 | 3.8 |  |  | Solar |  | 05_01_207W1 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 | 10/10/2019 | 7/7/2020 | Y | EXP | 365 | 02/12/2020 | 02/22/2020 | 10 | 0 | 10 |  |  | 4/21/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 697414 | 01532 | 4980 |  |  | Solar |  | 05_09_501L2 | 07/08/2025 | 07/30/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2025 | 08/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 177082 | 02301 | 750 |  |  | Solar |  | 05_12_1393 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/13/2017 | 53 | 42 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 191213 | 02760 | 0 |  |  | Solar |  | 05_07_91W43 | 08/28/2018 | 09/14/2018 | 12 | 2 | 10 | 09/17/2018 | 09/17/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 684009 | 01432 | 19.76 |  |  | Solar |  | 05_07_797W23 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | HARDWICK | 713903 | 01031 | 20 |  |  | Solar |  | 05_05_336W3 | 08/21/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | LYNN | 175451 | 01902 | 480 |  |  | Solar |  | 05_09_604W1 | 07/21/2014 | 07/21/2014 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2014 | 07/21/2014 | 12/31/2016 | Y | STD | 740 |  |  | 0 | 0 | 0 | 11/30/2015 | 11/30/2015 | 12/22/2015 | Connected |  | N
National Grid | BROCKTON | 177970 | 02301 | 414 |  |  | Solar |  | 05_05_314W4 | 04/25/2017 | 04/25/2017 | 28 | 26 | 2 | 06/06/2017 | 06/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2017 | 04/25/2017 | 5/1/2017 | Y | EXP | -73 | 09/22/2017 | 10/13/2017 | 14 | 0 | 14 | 11/27/2017 | 11/27/2017 | 11/27/2017 | Connected |  | N
National Grid | BRIDGEWATER | 175587 | 02333 | 496 |  |  | Solar |  | 05_07_98W44 | 04/28/2014 | 04/28/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2014 | 05/27/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 04/28/2014 | 9/13/2018 | Y | STD | 1070 | 02/16/2018 | 08/28/2018 | 193 | 0 | 193 |  |  | 9/7/2018 | Connected |  | N
National Grid | UPTON | 357046 | 01568 | 283.3 |  |  | Solar |  | 05_05_9L1 | 07/30/2021 | 01/27/2022 | 123 | 113 | 10 |  |  | 123 | 99 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW SALEM | 406210 | 01355 | 7.6 |  |  | Solar |  | 05_01_207W1 | 05/06/2024 | 01/17/2022 | 0 | 0 | 0 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 700559 | 01581 | 249 |  |  | Solar |  | 05_09_501L2 | 07/03/2025 | 08/08/2025 | 25 | 17 | 8 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 193190 | 02301 | 5 |  |  | Solar |  | 05_12_1394 | 08/09/2018 | 10/22/2018 | 27 | 26 | 1 | 10/23/2018 | 10/23/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 288315 | 02703 | 0 |  |  | Other |  | 05_07_91W43 | 05/07/2020 | 08/26/2020 | 77 | 70 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 04/29/2021 | 166 | 26 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AYER | 709116 | 01432 | 3.8 |  |  | Solar |  | 05_07_797W23 | 08/11/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | HARDWICK | 676974 | 01031 | 999.9 |  |  | Solar |  | 05_05_336W4 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 175580 | 01901 | 984 |  |  | Solar |  | 05_09_604W1 | 12/10/2014 | 12/10/2014 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2014 | 01/23/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 194780 | 02302 | 7.6 |  |  | Solar |  | 05_05_314W4 | 11/27/2018 | 12/05/2018 | 6 | 0 | 6 | 12/06/2018 | 12/06/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176127 | 02333 | 1656 |  |  | Solar |  | 05_07_98W44 | 02/03/2015 | 02/03/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/10/2015 | 07/06/2016 | 202 | 191 | 11 | 7/6/2016 | 02/03/2015 | 7/31/2015 | Y | STD | -341 | 12/07/2016 | 06/19/2017 | 132 | 0 | 132 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | UPTON | 356799 | 01568 | 375 |  |  | Solar |  | 05_05_9L1 | 07/14/2021 | 08/12/2021 | 21 | 11 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 | 07/14/2021 | 1/10/2024 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 412235 | 01005 | 0 |  |  | Battery Add-On |  | 05_01_207W1 | 07/22/2022 | 08/04/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2022 | 09/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 697860 | 01532 | 5000 |  |  | Solar |  | 05_09_501L2 | 09/17/2025 | 12/08/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/09/2025 | 01/02/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 340811 | 02379 | 9.8 |  |  | Solar |  | 05_12_13J2 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  | 5/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 311151 | 02703 | 10 |  |  | Solar |  | 05_07_91W43 | 10/01/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 10/01/2020 | 8/18/2022 | Y | EXP | 365 | 08/10/2021 | 10/12/2021 | 42 | 3 | 39 |  |  | 12/20/2021 | Connected |  | N
National Grid | LEOMINSTER | 719830 | 01453 | 10 |  |  | Solar |  | 05_07_797W23 | 09/18/2025 | 09/22/2025 | 2 | 0 | 2 | 09/23/2025 | 09/23/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 174659 | 01031 | 250 |  |  | Solar |  | 05_05_336W4 | 12/03/2012 | 12/03/2012 | 12 | 4 | 8 | 12/21/2012 | 12/21/2012 | 309 | 0 | 309 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 5/1/2013 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175610 | 01901 | 480 |  |  | Solar |  | 05_09_604W1 | 12/15/2014 | 12/15/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 | 01/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 208290 | 02301 | 3 |  |  | Solar |  | 05_05_314W4 | 02/13/2019 | 02/25/2019 | 6 | 1 | 5 | 02/26/2019 | 02/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | BRIDGEWATER | 176125 | 02333 | 1660 |  |  | Solar |  | 05_07_98W44 | 02/03/2015 | 02/03/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 09/10/2015 | 07/06/2016 | 202 | 191 | 11 | 7/6/2016 |  | 7/31/2015 | N | STD | -341 | 12/07/2016 | 06/19/2017 | 132 | 0 | 132 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 422661 | 01757 | 0 |  |  | Other |  | 05_05_9L1 | 08/18/2022 | 09/19/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2022 | 10/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 437434 | 01005 | 0 |  |  | Other |  | 05_01_207W1 | 09/19/2022 | 10/20/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 709806 | 01581 | 996 |  |  | Solar |  | 05_09_501L2 | 09/18/2025 | 09/29/2025 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/30/2025 | 10/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEST BRIDGEWATER | 646670 | 02379 | 7.6 |  |  | Solar |  | 05_12_13J2 | 10/25/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/25/2024 | 12/27/2025 | Y | EXP | 365 | 09/11/2025 | 09/10/2025 | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | ATTLEBORO | 315789 | 02703 | 9.8 |  |  | Solar |  | 05_07_91W43 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/03/2020 | 12/22/2024 | Y | EXP | 365 | 07/24/2021 | 07/26/2021 | 3 | 0 | 3 |  |  | 1/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 651763 | 01453 | 3.8 |  |  | Solar |  | 05_07_797W24 | 11/13/2024 | 02/19/2025 | 2 | 0 | 2 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HARDWICK | 175322 | 01031 | 301.6 |  |  | Solar |  | 05_05_336W4 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | LYNN | 176782 | 01902 | 2000 |  |  | Solar |  | 05_09_604W1 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/10/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 246090 | 02302 | 0 |  |  | Solar |  | 05_05_314W4 | 07/30/2019 | 07/31/2019 | 0 | 0 | 0 | 08/01/2019 | 08/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 176382 | 02333 | 496 |  |  | Solar |  | 05_07_98W44 | 11/25/2015 | 11/25/2015 | 3 | 3 | 0 | 12/01/2015 | 12/01/2015 | 247 | 0 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 442263 | 01757 | 11.6 |  |  | Solar |  | 05_05_9L1 | 08/03/2022 | 08/31/2022 | 21 | 20 | 1 | 09/01/2022 | 09/01/2022 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 |  | 10/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2022 | Connected |  | N
National Grid | BARRE | 477027 | 01005 | 6 |  |  | Solar |  | 05_01_207W1 | 03/07/2023 | 03/09/2023 | 2 | 1 | 1 | 03/10/2023 | 03/10/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 | 03/07/2023 | 6/8/2024 | Y | EXP | 365 | 06/09/2023 | 05/31/2023 | 64 | 0 | 64 |  |  | 8/7/2023 | Connected |  | N
National Grid | WESTBOROUGH | 724261 | 01581 | 22.8 |  |  | Solar |  | 05_09_501L2 | 10/06/2025 | 10/28/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BRIDGEWATER | 173305 | 02379 | 3.8 |  |  | Solar |  | 05_12_13J3 | 06/26/2018 | 06/26/2018 | 12 | 8 | 4 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 321262 | 02703 | 9.8 |  |  | Solar |  | 05_07_91W43 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 3/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2022 | Connected |  | N
National Grid | LEOMINSTER | 680245 | 01453 | 11.5 |  |  | Solar |  | 05_07_797W24 | 03/25/2025 | 06/16/2025 | 15 | 11 | 4 | 06/17/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARDWICK | 176441 | 01031 | 206 |  |  | Solar |  | 05_05_336W4 | 05/10/2016 | 05/10/2016 | 1 | 1 | 0 | 05/13/2016 | 05/13/2016 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/17/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176886 | 01905 | 17.25 |  |  | Solar |  | 05_09_604W1 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 286 | 0 | 286 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 |  | 11/18/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 318365 | 02301 | 10 |  |  | Solar |  | 05_05_314W4 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/09/2020 | 4/30/2021 | Y | EXP | 365 | 01/28/2021 | 02/17/2021 | 20 | 0 | 20 |  |  | 3/4/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 176718 | 02333 | 259.2 |  |  | Solar |  | 05_07_98W44 | 01/11/2016 | 01/11/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2016 | 01/27/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2016 | 01/11/2016 | 12/5/2017 | Y | STD | 495 | 10/12/2017 | 11/06/2017 | 12 | 0 | 12 | 11/2/2017 | 11/2/2017 | 12/5/2017 | Connected |  | N
National Grid | MILFORD | 453607 | 01757 | 5 |  |  | Solar |  | 05_05_9L1 | 09/12/2022 | 09/12/2022 | 0 | 0 | 0 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 | 09/12/2022 | 10/26/2023 | Y | EXP | 365 | 01/07/2023 | 01/06/2023 | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | N
National Grid | BARRE | 610626 | 01005 | 3.8 |  |  | Solar |  | 05_01_207W1 | 05/14/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/14/2024 | 12/31/2025 | Y | EXP | 365 | 05/06/2025 | 05/05/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 740154 | 01581 | 17.6 |  |  | Solar |  | 05_09_501L2 | 12/15/2025 | 12/18/2025 | 3 | 0 | 3 | 12/19/2025 | 12/19/2025 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BRIDGEWATER | 178358 | 02379 | 11.4 |  |  | Solar |  | 05_12_13J3 | 03/01/2018 | 03/01/2018 | 10 | 0 | 10 | 03/16/2018 | 03/16/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 |  | 3/23/2020 | N | EXP | 683 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | ATTLEBORO | 348390 | 02703 | 7.6 |  |  | Solar |  | 05_07_91W43 | 04/22/2021 | 04/28/2021 | 3 | 0 | 3 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 703140 | 01453 | 400 |  |  | Solar |  | 05_07_797W24 | 07/26/2025 | 09/03/2025 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/04/2025 | 09/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 176734 | 01082 | 206 |  |  | Solar |  | 05_05_336W4 | 04/26/2016 | 04/26/2016 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177809 | 01902 | 50 |  |  | Solar |  | 05_09_604W1 | 10/12/2017 | 10/12/2017 | 10 | 0 | 10 | 10/27/2017 | 10/27/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 10/18/2018 | N | EXP | 255 |  |  | 0 | 0 | 0 |  |  | 8/27/2018 | Connected |  | N
National Grid | BROCKTON | 343155 | 02301 | 0 |  |  | Solar |  | 05_05_314W4 | 02/19/2021 | 02/24/2021 | 3 | 2 | 1 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/24/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 176992 | 02333 | 7.6 |  |  | Solar |  | 05_07_98W44 | 03/15/2017 | 03/15/2017 | 9 | 7 | 2 | 03/28/2017 | 03/28/2017 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2017 |  | 3/20/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 471193 | 01757 | 120 |  |  | Solar |  | 05_05_9L1 | 11/01/2022 | 11/10/2022 | 8 | 1 | 7 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 661867 | 01005 | 3.8 |  |  | Solar |  | 05_01_207W1 | 12/19/2024 |  | 79 | 75 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 174162 | 01581 | 276.8 |  |  | Solar |  | 05_09_501L2 | 04/23/2012 | 04/23/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/25/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 09/10/2013 | 10/22/2013 | 29 | 0 | 29 | 12/31/2013 | 04/23/2012 |  | Y | STD | 365 | 06/29/2015 | 07/29/2015 | 21 | 0 | 21 | 7/29/2015 | 7/29/2015 | 7/31/2015 | Connected |  | N
National Grid | WEST BRIDGEWATER | 188535 | 02379 | 3.8 |  |  | Solar |  | 05_12_13J3 | 06/19/2018 | 06/19/2018 | 1 | 0 | 1 | 06/22/2018 | 06/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2018 |  | 9/22/2021 | N | EXP | 600 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | ATTLEBORO | 355333 | 02703 | 480 |  |  | Natural Gas |  | 05_07_91W43 | 06/14/2021 | 09/14/2021 | 64 | 52 | 12 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 724039 | 01453 | 15.2 |  |  | Solar |  | 05_07_797W24 | 10/07/2025 | 11/04/2025 | 19 | 17 | 2 | 11/05/2025 | 11/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 10/07/2025 | 1/6/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WARE | 177077 | 01082 | 206 |  |  | Solar |  | 05_05_336W4 | 05/10/2016 | 05/10/2016 | 1 | 0 | 1 | 05/13/2016 | 05/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 | 05/10/2016 | 12/30/2016 | Y | EXP | 137 | 11/10/2016 | 12/28/2016 | 31 | 0 | 31 | 12/28/2016 | 12/28/2016 | 1/10/2017 | Connected |  | N
National Grid | SAUGUS | 178292 | 01906 | 14.2 |  |  | Solar |  | 05_09_604W1 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 | 05/23/2018 | 05/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 11/19/2018 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 415123 | 02301 | 15.2 |  |  | Solar |  | 05_05_314W4 | 03/02/2022 | 03/03/2022 | 1 | 0 | 1 | 03/04/2022 | 03/04/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 178509 | 02333 | 60 |  |  | Solar |  | 05_07_98W44 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/19/2018 | 03/19/2018 | 55 | 41 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2018 |  | 3/13/2019 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 5/30/2019 | Connected |  | N
National Grid | MILFORD | 485614 | 01757 | 15.2 |  |  | Solar |  | 05_05_9L1 | 12/15/2022 | 12/27/2022 | 7 | 4 | 3 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2023 | Connected |  | N
National Grid | BARRE | 652757 | 01005 | 17.6 |  |  | Solar |  | 05_01_207W2 | 11/14/2024 | 11/19/2024 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 46 | 26 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTBOROUGH | 174161 | 01581 | 1825.6 |  |  | Solar |  | 05_09_501L2 | 04/20/2012 | 04/20/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 06/25/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 09/10/2013 | 10/22/2013 | 29 | 0 | 29 | 12/31/2013 | 04/20/2012 | 12/31/2014 | Y | STD | 365 | 06/29/2015 | 07/29/2015 | 21 | 0 | 21 | 7/29/2015 | 7/29/2015 | 7/31/2015 | Connected |  | N
National Grid | WEST BRIDGEWATER | 199773 | 02379 | 7.6 |  |  | Solar |  | 05_12_13J3 | 10/30/2018 | 11/08/2018 | 6 | 0 | 6 | 11/09/2018 | 11/09/2018 | 75 | 60 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 450999 | 02703 | 3.8 |  |  | Solar |  | 05_07_91W43 | 09/15/2022 | 09/19/2022 | 2 | 0 | 2 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/15/2022 | 3/31/2024 | Y | EXP | 365 | 03/29/2023 | 03/31/2023 | 3 | 0 | 3 |  |  | 4/28/2023 | Connected |  | N
National Grid | LEOMINSTER | 174858 | 01453 | 10 |  |  | Solar |  | 05_07_797W24 | 08/08/2013 | 08/08/2013 | 6 | 0 | 6 | 08/19/2013 | 08/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2013 |  | 12/31/2016 | N | EXP | 1219 |  |  | 0 | 0 | 0 | 3/16/2015 | 3/16/2015 | 2/9/2017 | Connected |  | N
National Grid | HARDWICK | 177935 | 01031 | 34.2 |  |  | Solar |  | 05_05_336W4 | 06/20/2017 | 06/20/2017 | 143 | 143 | 0 | 01/24/2018 | 01/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2018 |  | 6/25/2018 | N | EXP | 152 |  |  | 0 | 0 | 0 |  |  | 4/27/2018 | Connected |  | N
National Grid | SAUGUS | 178434 | 01906 | 636 |  |  | Solar |  | 05_09_604W1 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 472757 | 02301 | 11.31 |  |  | Solar |  | 05_05_314W4 | 11/11/2022 | 11/18/2022 | 6 | 2 | 4 | 11/21/2022 | 11/21/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/11/2022 | 4/24/2024 | Y | EXP | 365 | 02/07/2023 | 04/25/2023 | 78 | 0 | 78 |  |  | 12/1/2023 | Connected |  | N
National Grid | HANSON | 188061 | 02341 | 1400 |  |  | Solar |  | 05_07_98W44 | 06/14/2018 | 06/14/2018 | 10 | 9 | 1 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 06/14/2018 | 11/29/2022 | Y | STD | 29 | 06/05/2021 | 09/23/2021 | 111 | 3 | 108 |  |  | 10/18/2022 | Connected |  | N
National Grid | MILFORD | 556357 | 01757 | 199.8 |  |  | Solar |  | 05_05_9L1 | 01/08/2024 | 06/11/2024 | 107 | 97 | 10 |  |  | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 | 01/08/2024 | 1/5/2026 | Y | STD | 224 | 05/09/2025 | 05/14/2025 | 6 | 0 | 6 |  |  | 12/10/2025 | Connected |  | N
National Grid | BARRE | 651785 | 01005 | 3.8 |  |  | Solar |  | 05_01_207W2 | 01/02/2025 | 02/12/2025 | 25 | 22 | 3 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHBOROUGH | 175216 | 01532 | 480 |  |  | Solar |  | 05_09_501L2 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/18/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 05/10/2016 | 06/27/2016 | 32 | 0 | 32 | 12/21/2015 | 11/03/2014 | 3/31/2017 | Y | STD | 466 | 10/10/2016 | 03/23/2017 | 111 | 0 | 111 | 3/27/2017 | 3/27/2017 | 4/3/2017 | Connected |  | N
National Grid | WEST BRIDGEWATER | 209880 | 02379 | 7.6 |  |  | Solar |  | 05_12_13J3 | 02/28/2019 | 03/11/2019 | 6 | 0 | 6 | 03/12/2019 | 03/12/2019 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 381633 | 02703 | 5 |  |  | Solar |  | 05_07_91W43 | 10/04/2021 | 12/16/2021 | 26 | 16 | 10 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/04/2021 | 4/14/2023 | Y | EXP | 365 | 02/22/2022 | 04/14/2022 | 51 | 0 | 51 |  |  | 5/13/2022 | Connected |  | N
National Grid | LEOMINSTER | 175261 | 01453 | 22.8 |  |  | Solar |  | 05_07_797W24 | 01/09/2015 | 01/09/2015 | 5 | 2 | 3 | 01/19/2015 | 01/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2015 |  | 5/31/2015 | N | EXP | 89 |  |  | 0 | 0 | 0 | 3/3/2015 | 3/3/2015 | 8/28/2015 | Connected |  | N
National Grid | HARDWICK | 273779 | 01037 | 60 |  |  | Solar |  | 05_05_336W4 | 01/23/2020 | 02/06/2020 | 9 | 5 | 4 | 02/07/2020 | 02/07/2020 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2020 |  | 6/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 178746 | 01906 | 990 |  |  | Solar |  | 05_09_604W1 | 08/02/2018 | 08/10/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2018 | 09/05/2018 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 495314 | 02302 | 11.136 |  |  | Solar |  | 05_05_314W4 | 04/10/2023 | 05/02/2023 | 15 | 13 | 2 | 05/03/2023 | 05/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 7/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | PEMBROKE | 204836 | 02359 | 300 |  |  | Solar |  | 05_07_98W44 | 12/27/2018 | 01/10/2019 | 9 | 5 | 4 | 01/11/2019 | 01/11/2019 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2019 |  | 9/3/2023 | N | EXP | 448 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 645348 | 01757 | 5.76 |  |  | Solar |  | 05_05_9L1 | 10/07/2024 | 11/12/2024 | 11 | 7 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/31/2025 | Y | EXP | 365 | 02/13/2025 | 02/19/2025 | 7 | 0 | 7 |  |  | 2/26/2025 | Connected |  | N
National Grid | BARRE | 724260 | 01005 | 12.47 |  |  | Solar |  | 05_01_207W2 | 10/08/2025 | 12/01/2025 | 3 | 1 | 2 | 12/18/2025 | 12/18/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 175215 | 01581 | 480 |  |  | Solar |  | 05_09_501L2 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/18/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 05/10/2016 | 06/27/2016 | 32 | 0 | 32 | 12/21/2015 | 11/03/2014 | 3/31/2017 | Y | STD | 466 | 10/28/2016 | 03/23/2017 | 98 | 0 | 98 | 3/27/2017 | 3/27/2017 | 4/3/2017 | Connected |  | N
National Grid | BROCKTON | 231877 | 02301 | 3.8 |  |  | Solar |  | 05_12_13J3 | 08/15/2019 | 08/26/2019 | 6 | 1 | 5 | 08/27/2019 | 08/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2019 |  | 8/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | ATTLEBORO | 409189 | 02703 | 4.8 |  |  | Solar |  | 05_07_91W43 | 02/11/2022 | 02/22/2022 | 6 | 0 | 6 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 3/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2022 | Connected |  | N
National Grid | LEOMINSTER | 175305 | 01453 | 16 |  |  | Solar |  | 05_07_797W24 | 06/25/2014 | 06/25/2014 | 19 | 13 | 6 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2014 |  | 9/30/2014 | N | EXP | 47 |  |  | 0 | 0 | 0 | 9/3/2014 | 9/3/2014 | 11/14/2014 | Connected |  | N
National Grid | WARE | 340729 | 01082 | 466.6 |  |  | Solar |  | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 10 | 0 | 10 |  |  | 93 | 66 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 02/19/2021 | 7/29/2025 | Y | STD | 308 | 01/28/2025 | 03/03/2025 | 35 | 0 | 35 |  |  | 7/3/2025 | Connected |  | N
National Grid | SAUGUS | 235906 | 01906 | 17.28 |  |  | Solar |  | 05_09_604W1 | 06/12/2019 | 06/21/2019 | 6 | 2 | 4 | 06/27/2019 | 06/27/2019 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  | 7/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2019 | Connected |  | N
National Grid | BROCKTON | 544895 | 02301 | 15.2 |  |  | Solar |  | 05_05_314W4 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | HANSON | 389735 | 02341 | 0 |  |  | Other |  | 05_07_98W44 | 11/10/2021 | 01/04/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 645296 | 01757 | 10 |  |  | Solar |  | 05_05_9L1 | 10/07/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/07/2024 | 12/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | PETERSHAM | 176161 | 01366 | 11 |  |  | Solar |  | 05_01_207W2 | 02/05/2015 | 02/05/2015 | 4 | 1 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 6/24/2016 | N | EXP | 483 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 3/18/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 175476 | 01532 | 1000 |  |  | Solar |  | 05_09_501L2 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 3/1/2017 | N | STD | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 256490 | 02379 | 10 |  |  | Solar |  | 05_12_13J3 | 10/04/2019 | 10/19/2019 | 9 | 9 | 0 | 10/21/2019 | 10/21/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 | 10/04/2019 | 10/4/2020 | Y | EXP | 365 | 04/08/2020 | 05/15/2020 | 37 | 0 | 37 |  |  | 5/28/2020 | Connected |  | Y
National Grid | ATTLEBORO | 418384 | 02703 | 16.24 |  |  | Solar |  | 05_07_91W43 | 03/18/2022 | 03/28/2022 | 6 | 5 | 1 | 03/29/2022 | 03/29/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 11/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | LEOMINSTER | 175616 | 01453 | 23.4 |  |  | Solar |  | 05_07_797W24 | 12/16/2014 | 12/16/2014 | 8 | 7 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 | 12/16/2014 | 12/31/2016 | Y | EXP | 710 | 11/02/2015 | 11/10/2015 | 6 | 0 | 6 | 1/22/2015 | 1/22/2015 | 6/17/2016 | Connected |  | Y
National Grid | HARDWICK | 340727 | 01031 | 466.6 |  |  | Solar |  | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 |  |  | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 291503 | 01906 | 20 |  |  | Solar |  | 05_09_604W1 | 05/18/2020 | 06/02/2020 | 9 | 9 | 0 | 06/03/2020 | 06/03/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/18/2020 | 5/4/2022 | Y | EXP | 400 | 03/13/2021 | 03/24/2021 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 548633 | 02302 | 5.985 |  |  | Solar |  | 05_05_314W4 | 08/22/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2024 | Connected |  | N
National Grid | HALIFAX | 401391 | 02338 | 9.8 |  |  | Solar |  | 05_07_98W44 | 03/02/2022 | 03/08/2022 | 4 | 2 | 2 | 03/09/2022 | 03/09/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/02/2022 | 7/27/2023 | Y | EXP | 365 | 07/13/2022 | 07/21/2022 | 9 | 0 | 9 |  |  | 1/31/2023 | Connected |  | N
National Grid | MILFORD | 649789 | 01757 | 8.7 |  |  | Solar |  | 05_05_9L1 | 10/25/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 178351 | 01366 | 5 |  |  | Solar |  | 05_01_207W2 | 01/12/2018 | 01/12/2018 | 9 | 9 | 0 | 03/27/2018 | 03/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 | 01/12/2018 | 5/17/2019 | Y | EXP | 415 |  |  | 0 | 0 | 0 |  |  | 5/9/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 175475 | 01532 | 1000 |  |  | Solar |  | 05_09_501L2 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 3/1/2017 | N | STD | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 668811 | 02301 | 7.6 |  |  | Solar |  | 05_12_13J3 | 02/05/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 438914 | 02703 | 6 |  |  | Solar |  | 05_07_91W43 | 07/05/2022 | 08/11/2022 | 27 | 24 | 3 | 08/12/2022 | 08/12/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 07/05/2022 | 5/22/2024 | Y | EXP | 365 | 05/13/2023 | 05/19/2023 | 7 | 0 | 7 |  |  | 7/24/2023 | Connected |  | N
National Grid | LEOMINSTER | 175940 | 01453 | 19 |  |  | Solar |  | 05_07_797W24 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 556 | 0 | 556 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 343062 | 01031 | 233.2 |  |  | Solar |  | 05_05_336W4 | 02/19/2021 | 03/05/2021 | 10 | 0 | 10 |  |  | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 02/19/2021 | 6/6/2025 | Y | STD | 308 | 04/03/2025 | 04/21/2025 | 19 | 0 | 19 |  |  | 7/16/2025 | Connected |  | N
National Grid | SAUGUS | 298629 | 01906 | 9.36 |  |  | Solar |  | 05_09_604W1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 553642 | 02302 | 120 |  |  | Solar |  | 05_05_314W4 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 09/11/2023 | 10/14/2025 | Y | EXP | 217 | 01/30/2025 | 01/20/2025 | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | HALIFAX | 552189 | 02338 | 4.095 |  |  | Solar |  | 05_07_98W44 | 08/31/2023 | 09/05/2023 | 2 | 0 | 2 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2023 | Connected |  | N
National Grid | MILFORD | 657139 | 01757 | 5.76 |  |  | Solar |  | 05_05_9L1 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 178704 | 01366 | 10 |  |  | Solar |  | 05_01_207W2 | 03/20/2018 | 03/20/2018 | 22 | 20 | 2 | 09/24/2018 | 09/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 3/26/2019 | N | EXP | 182 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 176023 | 01532 | 180 |  |  | Solar |  | 05_09_501L2 | 03/25/2015 | 03/25/2015 | 7 | 4 | 3 | 04/06/2015 | 04/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 8/31/2015 | N | EXP | 147 |  |  | 0 | 0 | 0 | 7/10/2017 | 7/10/2017 | 7/31/2017 | Connected |  | N
National Grid | WEST BRIDGEWATER | 697587 | 02379 | 6.84 |  |  | Solar |  | 05_12_16J1 | 06/17/2025 | 07/01/2025 | 7 | 5 | 2 | 07/17/2025 | 07/17/2025 | 59 | 46 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 492594 | 02703 | 6 |  |  | Solar |  | 05_07_91W43 | 02/01/2023 | 02/03/2023 | 2 | 0 | 2 | 02/06/2023 | 02/06/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175952 | 01453 | 17.6 |  |  | Solar |  | 05_07_797W24 | 03/19/2015 | 03/19/2015 | 10 | 9 | 1 | 04/03/2015 | 04/03/2015 | 454 | 0 | 454 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 7/17/2015 | N | EXP | 102 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 |  | Withdrawn |  | N
National Grid | HARDWICK | 391850 | 01037 | 0 |  |  | Other |  | 05_05_336W4 | 12/16/2021 | 01/05/2022 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 11/22/2022 | 221 | 213 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 330336 | 01906 | 7.6 |  |  | Solar |  | 05_09_604W1 | 01/18/2021 | 01/28/2021 | 8 | 5 | 3 | 01/29/2021 | 01/29/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/18/2021 | 1/27/2022 | Y | EXP | 365 | 04/21/2021 | 05/12/2021 | 21 | 0 | 21 |  |  | 5/13/2021 | Connected |  | N
National Grid | BROCKTON | 567577 | 02302 | 240 |  |  | Solar |  | 05_05_314W4 | 10/31/2023 |  | 97 | 27 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 627633 | 02333 | 10.725 |  |  | Solar |  | 05_07_98W44 | 07/30/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 07/30/2024 | 9/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2024 | Connected |  | N
National Grid | MILFORD | 672006 | 01757 | 5.76 |  |  | Solar |  | 05_05_9L1 | 02/13/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 187189 | 01366 | 200 |  |  | Solar |  | 05_01_207W2 | 07/02/2018 | 07/02/2018 | 15 | 1 | 14 | 07/26/2018 | 07/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 |  | 12/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 176205 | 01532 | 495 |  |  | Solar |  | 05_09_501L2 | 04/24/2015 | 04/24/2015 | 6 | 6 | 0 | 05/05/2015 | 05/05/2015 | 246 | 0 | 246 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 426175 | 02302 | 7.6 |  |  | Solar |  | 05_12_16J1 | 04/25/2022 | 04/25/2022 | 0 | 0 | 0 | 04/26/2022 | 04/26/2022 | 70 | 52 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 540461 | 02703 | 10 |  |  | Solar |  | 05_07_91W43 | 07/17/2023 | 07/18/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 | 07/17/2023 | 9/16/2024 | Y | EXP | 365 | 10/28/2023 | 11/14/2023 | 18 | 0 | 18 |  |  | 1/26/2024 | Connected |  | N
National Grid | LEOMINSTER | 177047 | 01453 | 876 |  |  | Solar |  | 05_07_797W24 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/20/2017 | 58 | 43 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 | 10/17/2016 | 12/15/2021 | Y | STD | 741 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 401110 | 01037 | 0 |  |  | Other |  | 05_05_336W4 | 01/05/2022 | 02/04/2022 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 11/22/2022 | 199 | 199 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 370720 | 01906 | 7.68 |  |  | Solar |  | 05_09_604W1 | 07/19/2021 | 07/21/2021 | 3 | 2 | 1 | 07/22/2021 | 07/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2021 | 07/19/2021 | 5/7/2023 | Y | EXP | 365 | 12/02/2021 | 04/29/2022 | 149 | 0 | 149 |  |  | 5/16/2022 | Connected |  | N
National Grid | BROCKTON | 593596 | 02302 | 6.282 |  |  | Solar |  | 05_05_314W4 | 03/08/2024 | 03/13/2024 | 3 | 0 | 3 | 03/14/2024 | 03/14/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | BRIDGEWATER | 683588 | 02333 | 6 |  |  | Solar |  | 05_07_98W44 | 04/08/2025 | 04/28/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 04/08/2025 | 7/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | MILFORD | 711687 | 01757 | 19.893 |  |  | Solar |  | 05_05_9L1 | 08/25/2025 | 09/05/2025 | 8 | 3 | 5 | 09/08/2025 | 09/08/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 196330 | 01366 | 7.6 |  |  | Solar |  | 05_01_207W2 | 11/29/2018 | 12/19/2018 | 13 | 6 | 7 | 12/20/2018 | 12/20/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 11/29/2018 | 1/27/2021 | Y | EXP | 365 | 05/26/2021 | 06/24/2021 | 29 | 0 | 29 |  |  | 10/12/2021 | Connected |  | Y
National Grid | NORTHBOROUGH | 176263 | 01532 | 20 |  |  | Solar |  | 05_09_501L2 | 09/08/2015 | 09/08/2015 | 4 | 4 | 0 | 09/14/2015 | 09/14/2015 | 338 | 0 | 338 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 9/13/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 4/11/2016 | 4/11/2016 |  | Withdrawn |  | Y
National Grid | WEST BRIDGEWATER | 532542 | 02379 | 5 |  |  | Solar |  | 05_12_16J1 | 06/29/2023 | 07/06/2023 | 5 | 4 | 1 | 07/07/2023 | 07/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/29/2023 | 10/25/2024 | Y | EXP | 365 | 06/22/2024 | 07/09/2024 | 18 | 0 | 18 |  |  | 7/22/2024 | Connected |  | N
National Grid | ATTLEBORO | 564420 | 02703 | 9.765 |  |  | Solar |  | 05_07_91W43 | 01/24/2024 | 01/25/2024 | 2 | 1 | 1 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/24/2024 | 3/8/2025 | Y | EXP | 365 | 04/10/2024 | 05/08/2024 | 29 | 0 | 29 |  |  | 5/9/2024 | Connected |  | N
National Grid | LEOMINSTER | 177302 | 01453 | 532.8 |  |  | Solar |  | 05_07_797W24 | 11/15/2016 | 11/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 03/06/2017 | 74 | 59 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 12/1/2018 | N | STD | 270 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 422048 | 01037 | 0 |  |  | Battery Add-On |  | 05_05_336W4 | 07/28/2022 | 08/10/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 436738 | 01906 | 1.74 |  |  | Solar |  | 05_09_604W1 | 07/01/2022 | 07/12/2022 | 6 | 3 | 3 | 07/13/2022 | 07/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 | 07/01/2022 | 8/8/2024 | Y | EXP | 365 | 03/07/2023 | 08/02/2023 | 149 | 0 | 149 |  |  | 7/17/2024 | Connected |  | N
National Grid | BROCKTON | 621808 | 02302 | 11.5 |  |  | Solar |  | 05_05_314W4 | 07/01/2024 | 08/19/2024 | 9 | 4 | 5 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | HALIFAX | 707304 | 02338 | 7.6 |  |  | Solar |  | 05_07_98W46 | 07/24/2025 | 08/25/2025 | 4 | 0 | 4 | 08/26/2025 | 08/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 174134 | 01757 | 36 |  |  | Solar |  | 05_05_9L2 | 05/04/2012 | 05/04/2012 | 9 | 0 | 9 | 05/21/2012 | 05/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2012 |  | 5/19/2012 | N | EXP | -104 |  |  | 0 | 0 | 0 | 8/31/2012 | 8/31/2012 | 10/24/2012 | Connected |  | N
National Grid | BARRE | 198844 | 01005 | 10 |  |  | Solar |  | 05_01_207W2 | 11/08/2018 | 11/20/2018 | 5 | 0 | 5 | 11/21/2018 | 11/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 176561 | 01532 | 250 |  |  | Solar |  | 05_09_501L2 | 12/18/2015 | 12/22/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 01/22/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/25/2016 | 59 | 0 | 59 | 1/15/2019 | 12/18/2015 |  | Y | STD | 259 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 188941 | 02379 | 499.5 |  |  | Solar |  | 05_12_16J2 | 09/17/2018 | 09/21/2018 | 3 | 0 | 3 | 09/24/2018 | 09/24/2018 | 165 | 1 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 562243 | 02703 | 6 |  |  | Solar |  | 05_07_91W43 | 10/25/2023 |  | 81 | 25 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 183820 | 01453 | 0 |  |  | Solar |  | 05_07_797W24 | 05/25/2018 | 05/25/2018 | 5 | 0 | 5 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 522693 | 01037 | 100 |  |  | Solar |  | 05_05_336W4 | 04/29/2023 | 01/06/2024 | 171 | 162 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 466768 | 01906 | 3.8 |  |  | Solar |  | 05_09_604W1 | 10/17/2022 | 10/18/2022 | 1 | 0 | 1 | 10/19/2022 | 10/19/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2022 |  | 11/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2022 | Connected |  | N
National Grid | BROCKTON | 657569 | 02301 | 5.76 |  |  | Solar |  | 05_05_314W4 | 11/28/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/28/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | HALIFAX | 731035 | 02338 | 11.5 |  |  | Solar |  | 05_07_98W46 | 11/03/2025 | 11/25/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 175394 | 01757 | 131 |  |  | Solar |  | 05_05_9L2 | 09/16/2014 | 09/16/2014 | 7 | 0 | 7 | 09/26/2014 | 09/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2014 |  | 12/31/2014 | N | EXP | 82 |  |  | 0 | 0 | 0 | 1/15/2015 | 1/15/2015 | 2/5/2015 | Connected |  | N
National Grid | PETERSHAM | 204913 | 01366 | 3.8 |  |  | Solar |  | 05_01_207W2 | 01/30/2019 | 02/12/2019 | 8 | 0 | 8 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 176560 | 01532 | 972 |  |  | Solar |  | 05_09_501L2 | 12/17/2015 | 12/18/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2015 | 01/15/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/25/2016 | 5 | 0 | 5 | 2/4/2019 | 12/17/2015 | 10/9/2020 | Y | STD | 441 | 02/28/2020 | 04/01/2020 | 33 | 0 | 33 |  |  | 10/8/2020 | Connected |  | N
National Grid | WEST BRIDGEWATER | 188939 | 02379 | 499.5 |  |  | Solar |  | 05_12_16J2 | 09/19/2018 | 09/21/2018 | 1 | 0 | 1 | 09/24/2018 | 09/24/2018 | 165 | 1 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 568122 | 02703 | 22.8 |  |  | Solar |  | 05_07_91W43 | 11/22/2023 | 12/18/2023 | 17 | 14 | 3 | 12/19/2023 | 12/19/2023 | 288 | 263 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 290756 | 01453 | 7.68 |  |  | Solar |  | 05_07_797W24 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2022 | Connected |  | N
National Grid | HARDWICK | 698208 | 01037 | 150 |  |  | Solar |  | 05_05_336W4 | 07/07/2025 |  | 56 | 49 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 498809 | 02148 | 7.6 |  |  | Solar |  | 05_09_604W1 | 02/21/2023 | 02/23/2023 | 2 | 0 | 2 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/21/2023 | 7/5/2024 | Y | EXP | 365 | 08/16/2023 | 11/01/2023 | 78 | 0 | 78 |  |  | 11/23/2023 | Connected |  | N
National Grid | BROCKTON | 663565 | 02302 | 10 |  |  | Solar |  | 05_05_314W4 | 01/03/2025 | 01/29/2025 | 12 | 8 | 4 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 174197 | 02333 | 2000 |  |  | Solar |  | 05_07_98W46 | 03/20/2012 | 03/20/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2012 | 09/04/2012 | 96 | 0 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2013 | 03/20/2012 | 6/1/2014 | Y | STD | 319 | 06/05/2014 | 07/11/2014 | 24 | 0 | 24 | 7/25/2014 | 7/25/2014 | 7/31/2014 | Connected |  | N
National Grid | MILFORD | 175655 | 01757 | 684 |  |  | Solar |  | 05_05_9L2 | 05/09/2014 | 05/09/2014 | 8 | 0 | 8 | 05/22/2014 | 05/22/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/28/2015 | 05/09/2014 | 12/31/2016 | Y | EXP | 703 | 05/04/2016 | 08/23/2016 | 76 | 0 | 76 | 8/31/2016 | 8/31/2016 | 8/31/2016 | Connected |  | N
National Grid | PETERSHAM | 205332 | 01366 | 9.6 |  |  | Solar |  | 05_01_207W2 | 01/07/2019 | 02/05/2019 | 10 | 1 | 9 | 02/06/2019 | 02/06/2019 | 301 | 0 | 301 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 01/07/2019 | 7/22/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 177024 | 01581 | 15.2 |  |  | Solar |  | 05_09_501L2 | 03/16/2017 | 03/16/2017 | 8 | 7 | 1 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/21/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 9/19/2017 | 9/19/2017 | 9/19/2017 | Connected |  | N
National Grid | WEST BRIDGEWATER | 689238 | 02379 | 120 |  |  | Solar |  | 05_12_16J4 | 10/17/2025 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | ATTLEBORO | 571413 | 02703 | 75 |  |  | Solar |  | 05_07_91W43 | 11/22/2023 |  | 110 | 26 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 299346 | 01453 | 10 |  |  | Solar |  | 05_07_797W24 | 07/01/2020 | 07/08/2020 | 4 | 0 | 4 | 07/09/2020 | 07/09/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 175467 | 01031 | 7.6 |  |  | Solar |  | 05_05_341W1 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 565348 | 02148 | 1999.2 |  |  | Solar |  | 05_09_604W1 | 10/30/2023 | 01/30/2024 | 61 | 53 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2024 | 02/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 6/3/2025 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | BROCKTON | 695567 | 02302 | 15.2 |  |  | Solar |  | 05_05_314W4 | 06/04/2025 | 06/11/2025 | 4 | 1 | 3 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | HANSON | 175118 | 02341 | 50 |  |  | Solar |  | 05_07_98W46 | 10/18/2013 | 10/18/2013 | 5 | 0 | 5 | 10/28/2013 | 10/28/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2013 |  | 12/31/2013 | N | EXP | 42 |  |  | 0 | 0 | 0 | 1/27/2014 | 1/27/2014 | 2/6/2014 | Connected |  | N
National Grid | MILFORD | 175657 | 01757 | 60 |  |  | Solar |  | 05_05_9L2 | 05/13/2014 | 05/13/2014 | 7 | 0 | 7 | 05/23/2014 | 05/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2014 | 05/13/2014 | 9/30/2014 | Y | EXP | 106 | 11/05/2014 | 11/20/2014 | 10 | 0 | 10 | 12/12/2014 | 12/12/2014 | 12/16/2014 | Connected |  | N
National Grid | BARRE | 317534 | 01005 | 50 |  |  | Solar |  | 05_01_207W2 | 10/06/2020 | 10/15/2020 | 5 | 0 | 5 | 10/16/2020 | 10/16/2020 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 177674 | 01532 | 4980 |  |  | Solar |  | 05_09_501L2 | 07/20/2017 | 08/11/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2017 | 09/06/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 12/31/2019 | N | STD | 588 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BRIDGEWATER | 707537 | 02379 | 11.5 |  |  | Solar |  | 05_12_16J4 | 07/25/2025 | 09/03/2025 | 3 | 0 | 3 | 09/17/2025 | 09/17/2025 | 20 | 4 | 16 | 10/30/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | ATTLEBORO | 576220 | 02703 | 2.32 |  |  | Solar |  | 05_07_91W43 | 12/20/2023 | 12/22/2023 | 1 | 1 | 0 | 12/26/2023 | 12/26/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 326952 | 01453 | 9.36 |  |  | Solar |  | 05_07_797W24 | 12/09/2020 | 01/08/2021 | 20 | 15 | 5 | 01/11/2021 | 01/11/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 1/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | HARDWICK | 175894 | 01037 | 6 |  |  | Solar |  | 05_05_341W1 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/10/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 12/3/2015 | Connected |  | N
National Grid | MALDEN | 599337 | 02148 | 14.8 |  |  | Solar |  | 05_09_604W1 | 04/17/2024 | 04/22/2024 | 4 | 1 | 3 | 04/23/2024 | 04/23/2024 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/17/2024 | 6/10/2025 | Y | EXP | 365 | 09/27/2024 | 10/29/2024 | 33 | 0 | 33 |  |  | 10/31/2024 | Connected |  | N
National Grid | BROCKTON | 175947 | 02302 | 336 |  |  | Solar |  | 05_05_314W5 | 03/17/2015 | 03/17/2015 | 2 | 1 | 1 | 03/20/2015 | 03/20/2015 | 410 | 13 | 397 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2015 |  | 8/17/2015 | N | EXP | 101 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 175950 | 02341 | 2166 |  |  | Solar |  | 05_07_98W46 | 03/16/2015 | 03/16/2015 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/27/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 | 03/16/2015 | 8/31/2017 | Y | STD | 575 | 03/06/2017 | 08/15/2017 | 113 | 0 | 113 | 8/16/2017 | 8/16/2017 | 9/6/2017 | Connected |  | N
National Grid | MILFORD | 175957 | 01757 | 997 |  |  | Solar |  | 05_05_9L2 | 06/02/2015 | 06/02/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2015 | 07/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 | 06/02/2015 | 6/30/2016 | Y | STD | 209 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 331470 | 01366 | 3.36 |  |  | Solar |  | 05_01_207W2 | 02/13/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 177782 | 01532 | 1320 |  |  | Solar |  | 05_09_501L2 | 05/31/2017 | 06/21/2017 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2017 | 07/11/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2017 | 05/31/2017 | 12/16/2021 | Y | STD | 63 | 11/27/2019 | 03/03/2021 | 463 | 6 | 457 | 11/17/2021 | 12/6/2021 | 12/10/2021 | Connected |  | N
National Grid | BROCKTON | 175889 | 02301 | 56 |  |  | Solar |  | 05_12_16J4 | 05/27/2015 | 05/27/2015 | 1 | 1 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2015 |  | 10/30/2015 | N | EXP | 129 |  |  | 0 | 0 | 0 | 6/30/2015 | 6/30/2015 | 1/25/2016 | Connected |  | N
National Grid | ATTLEBORO | 578958 | 02703 | 7.6 |  |  | Solar |  | 05_07_91W43 | 01/31/2024 | 02/01/2024 | 1 | 0 | 1 | 02/02/2024 | 02/02/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | LEOMINSTER | 339190 | 01453 | 57.2 |  |  | Solar |  | 05_07_797W24 | 03/30/2021 | 12/09/2021 | 34 | 24 | 10 | 06/03/2021 | 06/03/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | WARE | 177163 | 01082 | 3.8 |  |  | Solar |  | 05_05_341W1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 | 01/24/2017 | 1/29/2018 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 9/21/2017 | 9/21/2017 | 9/21/2017 | Connected |  | N
National Grid | LYNN | 643807 | 01905 | 10 |  |  | Solar |  | 05_09_604W1 | 10/08/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/08/2024 | 2/10/2026 | Y | EXP | 365 | 05/16/2025 | 09/23/2025 | 131 | 0 | 131 |  |  | 10/7/2025 | Connected |  | N
National Grid | BROCKTON | 176866 | 02301 | 1232 |  |  | Solar |  | 05_05_314W5 | 01/22/2016 | 01/22/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2016 | 02/17/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/27/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 176348 | 02338 | 225 |  |  | Solar |  | 05_07_98W46 | 02/26/2015 | 02/26/2015 | 5 | 0 | 5 | 03/09/2015 | 03/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2015 |  | 9/30/2015 | N | EXP | 184 |  |  | 0 | 0 | 0 | 4/1/2016 | 4/1/2016 | 4/1/2016 | Connected |  | N
National Grid | MILFORD | 177007 | 01757 | 997 |  |  | Solar |  | 05_05_9L2 | 10/13/2016 | 10/13/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 11/01/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/18/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PETERSHAM | 340616 | 01366 | 57.6 |  |  | Solar |  | 05_01_207W2 | 03/30/2021 | 12/09/2021 | 9 | 0 | 9 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 6/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2021 | Connected |  | N
National Grid | WESTBOROUGH | 177768 | 01581 | 5000 |  |  | Solar |  | 05_09_501L2 | 10/06/2017 | 01/31/2018 | 77 | 70 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2018 | 02/22/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176667 | 02301 | 268.8 |  |  | Solar |  | 05_12_16J4 | 10/20/2015 | 10/20/2015 | 2 | 2 | 0 | 10/23/2015 | 10/23/2015 | 332 | 26 | 306 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2016 |  | 10/26/2016 | N | EXP | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 580600 | 02703 | 9.765 |  |  | Solar |  | 05_07_91W43 | 01/23/2024 | 01/24/2024 | 1 | 0 | 1 | 01/25/2024 | 01/25/2024 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 01/23/2024 | 3/4/2025 | Y | EXP | 365 | 03/26/2024 | 04/22/2024 | 28 | 0 | 28 |  |  | 4/26/2024 | Connected |  | N
National Grid | LEOMINSTER | 439549 | 01453 | 0 |  |  | Solar |  | 05_07_797W24 | 07/06/2022 | 07/08/2022 | 3 | 2 | 1 | 07/11/2022 | 07/11/2022 | 54 | 34 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 11/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | WARE | 177340 | 01082 | 480 |  |  | Solar |  | 05_05_341W1 | 11/11/2016 | 11/11/2016 | 4 | 4 | 0 | 11/28/2016 | 11/28/2016 | 205 | 14 | 191 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/26/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 665912 | 02148 | 7.6 |  |  | Solar |  | 05_09_604W1 | 01/15/2025 | 01/30/2025 | 2 | 0 | 2 | 01/31/2025 | 01/31/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 196392 | 02301 | 496 |  |  | Solar |  | 05_05_314W5 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 73 | 51 | 22 |  |  | 0 | 0 | 0 | 10/02/2018 | 02/26/2019 | 97 | 57 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 176676 | 02341 | 5 |  |  | Solar |  | 05_07_98W46 | 01/04/2016 | 01/04/2016 | 1 | 1 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 01/04/2016 | 1/10/2017 | Y | EXP | 347 | 04/23/2017 | 05/05/2017 | 9 | 0 | 9 | 5/8/2017 | 5/8/2017 | 5/10/2017 | Connected |  | N
National Grid | MILFORD | 177239 | 01757 | 1080 |  |  | Solar |  | 05_05_9L2 | 02/03/2017 | 03/07/2017 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2017 | 05/15/2017 | 50 | 37 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 | 02/03/2017 | 4/2/2023 | Y | STD | 20 | 10/11/2021 | 03/01/2022 | 142 | 4 | 138 |  |  | 3/31/2023 | Connected |  | N
National Grid | BARRE | 350603 | 01005 | 9.86 |  |  | Solar |  | 05_01_207W2 | 04/02/2021 | 04/22/2021 | 13 | 13 | 0 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 177973 | 01532 | 1500 |  |  | Solar |  | 05_09_501L2 | 06/27/2017 | 06/27/2017 | 152 | 151 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 178608 | 02356 | 15.2 |  |  | Solar |  | 05_12_16J4 | 12/12/2017 | 12/12/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 3/22/2019 | N | EXP | 443 |  |  | 0 | 0 | 0 |  |  | 6/6/2019 | Connected |  | N
National Grid | ATTLEBORO | 590937 | 02703 | 10 |  |  | Solar |  | 05_07_91W43 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 463055 | 01453 | 2550 |  |  | Solar |  | 05_07_797W24 | 11/03/2022 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177968 | 01082 | 10 |  |  | Solar |  | 05_05_341W1 | 04/24/2017 | 04/24/2017 | 26 | 26 | 0 | 05/31/2017 | 05/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 04/24/2017 | 4/29/2018 | Y | EXP | 332 | 08/29/2017 | 09/08/2017 | 7 | 0 | 7 | 10/24/2017 | 10/24/2017 | 10/24/2017 | Connected |  | N
National Grid | MALDEN | 666716 | 02148 | 13.3 |  |  | Solar |  | 05_09_604W1 | 01/20/2025 | 02/03/2025 | 5 | 1 | 4 | 02/04/2025 | 02/04/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/20/2025 | 3/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | BROCKTON | 201712 | 02301 | 7.6 |  |  | Solar |  | 05_05_314W5 | 11/20/2018 | 12/14/2018 | 4 | 0 | 4 | 12/17/2018 | 12/17/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2019 | 11/20/2018 | 4/14/2020 | Y | EXP | 467 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 1/14/2020 | Connected |  | N
National Grid | HALIFAX | 177764 | 02338 | 9.92 |  |  | Solar |  | 05_07_98W46 | 10/05/2017 | 10/05/2017 | 25 | 25 | 0 | 11/21/2017 | 11/21/2017 | 92 | 0 | 92 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/11/2018 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | FRANKLIN | 177427 | 02038 | 997 |  |  | Solar |  | 05_05_9L2 | 02/28/2017 | 02/28/2017 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2017 | 03/24/2017 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 369937 | 01005 | 28.8 |  |  | Solar |  | 05_01_207W2 | 08/09/2021 | 01/05/2022 | 1 | 0 | 1 | 08/11/2021 | 08/11/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 177997 | 01532 | 1610 |  |  | Solar |  | 05_09_501L2 | 10/25/2017 | 10/25/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2018 | 02/14/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 188285 | 02356 | 6 |  |  | Solar |  | 05_12_16J4 | 08/29/2018 | 06/15/2018 | 41 | 30 | 11 | 09/26/2018 | 09/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 10/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2019 | Connected |  | N
National Grid | ATTLEBORO | 591245 | 02703 | 3.78 |  |  | Solar |  | 05_07_91W43 | 03/06/2024 | 03/11/2024 | 3 | 0 | 3 | 03/12/2024 | 03/12/2024 | 4 | 1 | 3 | 04/08/2024 | 05/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 05/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 5/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 490153 | 01453 | 20 |  |  | Solar |  | 05_07_797W24 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | N
National Grid | HARDWICK | 266941 | 01037 | 10 |  |  | Solar |  | 05_05_341W1 | 11/22/2019 | 01/28/2020 | 45 | 44 | 1 | 01/29/2020 | 01/29/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2020 | Connected |  | N
National Grid | MALDEN | 674451 | 02148 | 8.64 |  |  | Solar |  | 05_09_604W1 | 02/26/2025 | 03/14/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2026 | Connected |  | N
National Grid | BROCKTON | 205806 | 02302 | 7.6 |  |  | Solar |  | 05_05_314W5 | 04/15/2019 | 06/12/2019 | 39 | 32 | 7 | 06/13/2019 | 06/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 04/15/2019 | 3/6/2020 | Y | EXP | 262 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | EAST BRIDGEWATER | 178505 | 02333 | 9.92 |  |  | Solar |  | 05_07_98W46 | 01/24/2018 | 01/24/2018 | 20 | 10 | 10 | 02/23/2018 | 02/23/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2018 | 01/24/2018 | 10/31/2019 | Y | EXP | 577 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | FRANKLIN | 178090 | 02038 | 100 |  |  | Solar |  | 05_05_9L2 | 07/07/2017 | 07/07/2017 | 32 | 32 | 0 | 08/22/2017 | 08/22/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2017 |  | 7/12/2018 | N | EXP | 317 |  |  | 0 | 0 | 0 |  |  | 8/21/2018 | Connected |  | N
National Grid | ATHOL | 390483 | 01331 | 4.8 |  |  | Solar |  | 05_01_207W2 | 11/09/2021 | 01/10/2022 | 4 | 2 | 2 | 11/17/2021 | 11/17/2021 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/09/2021 | 9/21/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2023 | Connected |  | N
National Grid | WESTBOROUGH | 177996 | 01582 | 1610 |  |  | Solar |  | 05_09_501L2 | 10/25/2017 | 10/25/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2018 | 02/14/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 546731 | 02356 | 25 |  |  | Solar |  | 05_12_16J4 | 10/27/2023 | 11/07/2023 | 8 | 5 | 3 | 11/08/2023 | 11/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | ATTLEBORO | 607506 | 02703 | 3.8 |  |  | Solar |  | 05_07_91W43 | 04/29/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 499293 | 01453 | 19 |  |  | Solar |  | 05_07_797W24 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 6/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | WARE | 656447 | 01082 | 23 |  |  | Battery Add-On |  | 05_05_341W1 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | MALDEN | 681343 | 02148 | 11.4 |  |  | Solar |  | 05_09_604W1 | 05/14/2025 | 05/20/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | BROCKTON | 650005 | 02301 | 0 |  |  | Other |  | 05_05_317W1 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 110 | 92 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HANSON | 234807 | 02341 | 10 |  |  | Solar |  | 05_07_98W46 | 07/30/2019 | 07/31/2019 | 0 | 0 | 0 | 08/01/2019 | 08/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/30/2019 | 7/19/2023 | Y | EXP | 365 | 01/12/2021 | 01/25/2021 | 13 | 0 | 13 |  |  | 1/7/2023 | Connected |  | N
National Grid | FRANKLIN | 433514 | 02038 | 10 |  |  | Solar |  | 05_05_9L2 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/22/2022 | 1/7/2024 | Y | EXP | 365 | 01/07/2023 | 01/06/2023 | 0 | 0 | 0 |  |  | 2/3/2023 | Connected |  | N
National Grid | PETERSHAM | 475067 | 01366 | 5.22 |  |  | Solar |  | 05_01_207W2 | 02/13/2023 | 02/17/2023 | 5 | 3 | 2 | 02/21/2023 | 02/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/13/2023 | 11/15/2024 | Y | EXP | 365 | 12/14/2023 | 12/22/2023 | 9 | 3 | 6 |  |  | 12/29/2023 | Connected |  | N
National Grid | WESTBOROUGH | 178030 | 01582 | 4998 |  |  | Solar |  | 05_09_501L2 | 09/01/2017 | 09/01/2017 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2017 | 10/12/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 546706 | 02356 | 25 |  |  | Solar |  | 05_12_16J4 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/10/2023 | 11/10/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | ATTLEBORO | 631090 | 02703 | 5.76 |  |  | Solar |  | 05_07_91W43 | 08/08/2024 | 09/10/2024 | 18 | 16 | 2 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 516332 | 01453 | 10 |  |  | Solar |  | 05_07_797W24 | 06/09/2023 | 07/12/2023 | 22 | 21 | 1 | 07/13/2023 | 07/13/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/09/2023 | 8/16/2024 | Y | EXP | 365 | 09/13/2023 | 09/13/2023 | 1 | 0 | 1 |  |  | 9/18/2023 | Connected |  | N
National Grid | HARDWICK | 678310 | 01031 | 10 |  |  | Solar |  | 05_05_341W1 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | MALDEN | 696615 | 02148 | 23.725 |  |  | Solar |  | 05_09_604W1 | 06/20/2025 | 06/25/2025 | 3 | 1 | 2 | 06/26/2025 | 06/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175356 | 02302 | 1200 |  |  | Bio Gas |  | 05_05_317W1 | 09/05/2014 | 09/05/2014 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2014 | 10/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2014 |  | 12/31/2016 | N | STD | 738 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/22/2015 | 12/22/2015 | Connected |  | N
National Grid | HANSON | 251819 | 02341 | 7.6 |  |  | Solar |  | 05_07_98W46 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/14/2019 | 3/29/2021 | Y | EXP | 365 | 08/10/2021 | 08/10/2021 | 0 | 0 | 0 |  |  | 2/7/2022 | Connected |  | N
National Grid | FRANKLIN | 456501 | 02038 | 19.14 |  |  | Solar |  | 05_05_9L2 | 09/03/2022 | 09/07/2022 | 3 | 2 | 1 | 09/08/2022 | 09/08/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 11/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | PETERSHAM | 484968 | 01366 | 8.99 |  |  | Solar |  | 05_01_207W2 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 12/15/2022 | 10/25/2024 | Y | EXP | 365 | 07/18/2023 | 10/20/2023 | 95 | 0 | 95 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 178050 | 01582 | 6740 |  |  | Solar |  | 05_09_501L2 | 06/29/2017 | 08/09/2017 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2017 | 09/01/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2018 |  | 7/5/2018 | N | STD | -54 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 546570 | 02301 | 25 |  |  | Solar |  | 05_12_16J4 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 |  | 12/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | ATTLEBORO | 632654 | 02703 | 7.6 |  |  | Solar |  | 05_07_91W43 | 08/14/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 518671 | 01453 | 9.86 |  |  | Solar |  | 05_07_797W24 | 05/01/2023 | 05/09/2023 | 6 | 5 | 1 | 05/10/2023 | 05/10/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N
National Grid | HARDWICK | 715096 | 01037 | 23 |  |  | Solar |  | 05_05_341W1 | 08/28/2025 | 09/03/2025 | 3 | 1 | 2 | 09/04/2025 | 09/04/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | MALDEN | 712329 | 02148 | 8.376 |  |  | Solar |  | 05_09_604W1 | 08/21/2025 | 09/11/2025 | 2 | 0 | 2 | 09/16/2025 | 09/16/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 | 08/21/2025 | 10/16/2026 | Y | EXP | 365 | 11/21/2025 | 11/25/2025 | 5 | 0 | 5 |  |  | 12/2/2025 | Connected |  | N
National Grid | BROCKTON | 176480 | 02301 | 75 |  |  | Solar |  | 05_05_317W1 | 05/19/2016 | 05/19/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 |  | 5/31/2019 | N | EXP | 1029 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | HANSON | 293451 | 02341 | 1.92 |  |  | Solar |  | 05_07_98W46 | 06/01/2020 | 06/04/2020 | 2 | 0 | 2 | 06/05/2020 | 06/05/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 598260 | 02038 | 10 |  |  | Solar |  | 05_05_9L2 | 03/29/2024 | 04/16/2024 | 12 | 10 | 2 | 04/17/2024 | 04/17/2024 | 10 | 6 | 4 | 05/14/2024 | 06/26/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 06/26/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 514450 | 01005 | 7.6 |  |  | Solar |  | 05_01_207W2 | 04/06/2023 | 04/17/2023 | 7 | 5 | 2 | 04/18/2023 | 04/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 | 04/06/2023 | 7/26/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2024 | Connected |  | N
National Grid | WESTBOROUGH | 178059 | 01581 | 3000 |  |  | Solar |  | 05_09_501L2 | 09/01/2017 | 09/22/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2017 | 10/17/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2018 | 09/01/2017 | 7/8/2021 | Y | STD | 839 | 05/29/2020 | 03/29/2021 | 304 | 88 | 216 |  |  | 7/8/2021 | Connected |  | N
National Grid | BROCKTON | 646234 | 02301 | 10 |  |  | Solar |  | 05_12_16J4 | 10/15/2024 | 10/16/2024 | 1 | 0 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 10/15/2024 | 2/5/2026 | Y | EXP | 365 | 04/16/2025 | 08/18/2025 | 125 | 0 | 125 |  |  | 10/3/2025 | Connected |  | N
National Grid | ATTLEBORO | 640968 | 02703 | 5 |  |  | Solar |  | 05_07_91W43 | 09/19/2024 | 10/17/2024 | 13 | 11 | 2 | 10/18/2024 | 10/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 601957 | 01453 | 10 |  |  | Solar |  | 05_07_797W24 | 04/11/2024 | 04/12/2024 | 1 | 0 | 1 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 04/11/2024 | 5/16/2025 | Y | EXP | 365 | 05/23/2024 | 07/15/2024 | 54 | 0 | 54 |  |  | 10/16/2024 | Connected |  | N
National Grid | HARDWICK | 738905 | 01037 | 0 |  |  | Battery Add-On |  | 05_05_341W2 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MALDEN | 714578 | 02148 | 24.32 |  |  | Solar |  | 05_09_604W1 | 08/25/2025 | 08/28/2025 | 2 | 0 | 2 | 08/29/2025 | 08/29/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176631 | 02301 | 75 |  |  | Solar |  | 05_05_317W1 | 10/16/2015 | 10/16/2015 | 3 | 3 | 0 | 10/23/2015 | 10/23/2015 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 308244 | 02338 | 1.92 |  |  | Solar |  | 05_07_98W46 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 609619 | 02038 | 12.6 |  |  | Solar |  | 05_05_9L2 | 05/09/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 7/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2024 | Connected |  | N
National Grid | PETERSHAM | 523383 | 01366 | 6 |  |  | Solar |  | 05_01_207W2 | 05/12/2023 | 05/16/2023 | 2 | 0 | 2 | 05/17/2023 | 05/17/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 | 05/12/2023 | 7/23/2024 | Y | EXP | 365 | 09/21/2023 | 10/24/2023 | 34 | 0 | 34 |  |  | 11/9/2023 | Connected |  | N
National Grid | WESTBOROUGH | 178396 | 01581 | 19.2 |  |  | Solar |  | 05_09_501L2 | 03/04/2018 | 03/04/2018 | 1 | 1 | 0 | 03/20/2018 | 03/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2018 |  | 3/11/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 7/27/2018 | Connected |  | N
National Grid | BROCKTON | 530618 | 02301 | 0 |  |  | Solar |  | 05_12_16J5 | 06/01/2023 | 06/02/2023 | 1 | 0 | 1 | 06/05/2023 | 06/05/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | ATTLEBORO | 647475 | 02703 | 7.6 |  |  | Solar |  | 05_07_91W43 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | LEOMINSTER | 646911 | 01453 | 7.6 |  |  | Solar |  | 05_07_797W24 | 10/24/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | HARDWICK | 174314 | 01037 | 20.5 |  |  | Solar |  | 05_05_341W2 | 01/16/2012 | 01/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 467839 | 02148 | 1900 |  |  | Solar |  | 05_09_604W2 | 02/27/2023 | 05/09/2023 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2023 | 06/27/2023 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 176857 | 02301 | 75 |  |  | Solar |  | 05_05_317W1 | 01/19/2016 | 01/19/2016 | 0 | 0 | 0 | 01/19/2016 | 01/19/2016 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 325302 | 02338 | 7.6 |  |  | Solar |  | 05_07_98W46 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  | 5/23/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 647209 | 02038 | 7.6 |  |  | Solar |  | 05_05_9L2 | 10/15/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 101 | 75 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 532600 | 01366 | 6 |  |  | Solar |  | 05_01_207W2 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 178619 | 01772 | 7.6 |  |  | Solar |  | 05_09_501L2 | 01/31/2018 | 03/07/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 | 01/31/2018 | 6/17/2019 | Y | EXP | 466 | 03/07/2019 | 03/06/2019 | 0 | 0 | 0 |  |  | 5/17/2019 | Connected |  | N
National Grid | BROCKTON | 658179 | 02301 | 5.76 |  |  | Solar |  | 05_12_16J5 | 12/04/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/04/2024 | 2/20/2026 | Y | EXP | 365 | 04/15/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 5/19/2025 | Connected |  | N
National Grid | ATTLEBORO | 650602 | 02703 | 5.2 |  |  | Solar |  | 05_07_91W43 | 11/04/2024 | 11/19/2024 | 5 | 1 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/04/2024 | 1/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 651648 | 01453 | 7.6 |  |  | Solar |  | 05_07_797W24 | 11/04/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/04/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 175726 | 01082 | 140 |  |  | Solar |  | 05_05_341W2 | 05/30/2014 | 05/30/2014 | 14 | 9 | 5 | 06/23/2014 | 06/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 | 05/30/2014 | 10/15/2014 | Y | EXP | 85 | 10/16/2014 | 12/04/2014 | 33 | 0 | 33 | 7/16/2014 | 7/16/2014 | 12/30/2014 | Connected |  | N
National Grid | MALDEN | 702660 | 02148 | 13.8 |  |  | Solar |  | 05_09_604W2 | 07/03/2025 | 08/26/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 62 | 50 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BROCKTON | 177517 | 02302 | 75 |  |  | Solar |  | 05_05_317W1 | 06/23/2016 | 06/23/2016 | 5 | 0 | 5 | 06/30/2016 | 06/30/2016 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 333382 | 02341 | 9.6 |  |  | Solar |  | 05_07_98W46 | 05/06/2021 | 05/06/2021 | 0 | 0 | 0 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2021 |  | 7/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2022 | Connected |  | N
National Grid | FRANKLIN | 657108 | 02038 | 5.76 |  |  | Solar |  | 05_05_9L2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/26/2024 | 2/11/2026 | Y | EXP | 365 | 03/04/2025 | 04/17/2025 | 45 | 0 | 45 |  |  | 5/16/2025 | Connected |  | N
National Grid | PETERSHAM | 546090 | 01366 | 26 |  |  | Solar |  | 05_01_207W2 | 08/04/2023 | 08/08/2023 | 2 | 0 | 2 | 08/09/2023 | 08/09/2023 | 214 | 29 | 185 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 178606 | 01752 | 10 |  |  | Solar |  | 05_09_501L2 | 12/12/2017 | 12/13/2017 | 77 | 61 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 676531 | 02301 | 3.8 |  |  | Solar |  | 05_12_16J5 | 03/07/2025 | 03/26/2025 | 1 | 0 | 1 | 04/04/2025 | 04/04/2025 | 136 | 125 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 650743 | 02703 | 6 |  |  | Solar |  | 05_07_91W43 | 10/30/2024 | 11/18/2024 | 4 | 0 | 4 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 654121 | 01453 | 5.7 |  |  | Solar |  | 05_07_797W24 | 11/18/2024 | 12/12/2024 | 6 | 2 | 4 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/18/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | BARRE | 393614 | 01005 | 15.2 |  |  | Solar |  | 05_05_341W2 | 11/05/2021 | 11/09/2021 | 2 | 0 | 2 | 11/10/2021 | 11/10/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 723717 | 02148 | 15.96 |  |  | Solar |  | 05_09_604W2 | 10/02/2025 | 10/08/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 178234 | 02301 | 1200 |  |  | Landfill Gas |  | 05_05_317W1 | 01/08/2018 | 01/08/2018 | 36 | 3 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2018 | 04/13/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/13/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 342718 | 02341 | 10 |  |  | Solar |  | 05_07_98W46 | 05/27/2021 | 06/03/2021 | 3 | 0 | 3 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 662700 | 02038 | 10 |  |  | Solar |  | 05_05_9L2 | 12/26/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/26/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | PETERSHAM | 551656 | 01366 | 3.8 |  |  | Solar |  | 05_01_207W2 | 08/30/2023 | 09/01/2023 | 2 | 0 | 2 | 09/05/2023 | 09/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/30/2023 | 11/10/2024 | Y | EXP | 365 | 02/22/2024 | 03/13/2024 | 21 | 0 | 21 |  |  | 4/18/2024 | Connected |  | N
National Grid | MARLBOROUGH | 188725 | 01752 | 15.2 |  |  | Solar |  | 05_09_501L2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  | 9/20/2019 | N | EXP | 308 |  |  | 0 | 0 | 0 |  |  | 9/3/2019 | Connected |  | N
National Grid | BROCKTON | 175037 | 02301 | 300 |  |  | Solar |  | 05_12_16J6 | 09/20/2013 | 09/20/2013 | 12 | 5 | 7 | 10/09/2013 | 10/09/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2013 |  | 12/31/2013 | N | EXP | 64 |  |  | 0 | 0 | 0 | 12/23/2013 | 12/23/2013 | 12/27/2013 | Connected |  | N
National Grid | ATTLEBORO | 654702 | 02703 | 5.76 |  |  | Solar |  | 05_07_91W43 | 11/19/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | LEOMINSTER | 693651 | 01453 | 17.6 |  |  | Solar |  | 05_07_797W24 | 06/02/2025 | 06/06/2025 | 4 | 0 | 4 | 06/09/2025 | 06/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Connected |  | N
National Grid | WARE | 423130 | 01082 | 7.6 |  |  | Solar |  | 05_05_341W2 | 04/11/2022 | 05/27/2022 | 34 | 33 | 1 | 05/31/2022 | 05/31/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2022 | Connected |  | N
National Grid | MALDEN | 729932 | 02148 | 13.36 |  |  | Solar |  | 05_09_604W2 | 11/14/2025 | 11/17/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 178387 | 02301 | 10 |  |  | Solar |  | 05_05_317W1 | 01/16/2018 | 01/16/2018 | 16 | 0 | 16 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/22/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 6/1/2018 | Connected |  | N
National Grid | HANSON | 352007 | 02341 | 10 |  |  | Solar |  | 05_07_98W46 | 04/29/2021 | 05/06/2021 | 4 | 0 | 4 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 1/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2021 | Connected |  | N
National Grid | FRANKLIN | 670414 | 02038 | 30.6 |  |  | Solar |  | 05_05_9L2 | 02/06/2025 | 03/05/2025 | 19 | 16 | 3 | 03/06/2025 | 03/06/2025 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PETERSHAM | 565145 | 01366 | 6.3 |  |  | Solar |  | 05_01_207W2 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 12/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | MARLBOROUGH | 191405 | 01752 | 1746 |  |  | Solar |  | 05_09_501L2 | 12/14/2018 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 223160 | 02301 | 133.2 |  |  | Solar |  | 05_12_16J6 | 04/29/2019 | 05/16/2019 | 12 | 7 | 5 | 05/17/2019 | 05/17/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 |  | 6/21/2021 | N | EXP | 720 |  |  | 0 | 0 | 0 |  |  | 5/27/2021 | Connected |  | N
National Grid | ATTLEBORO | 657585 | 02703 | 5.76 |  |  | Solar |  | 05_07_91W43 | 11/29/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 31 | 9 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 479187 | 01453 | 4990 |  |  | Solar |  | 05_07_797W29 | 05/30/2023 | 07/13/2023 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2023 | 08/17/2023 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 476346 | 01082 | 0 |  |  | Other |  | 05_05_341W2 | 02/21/2023 |  | 99 | 56 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 734018 | 02148 | 11.5 |  |  | Solar |  | 05_09_604W2 | 11/14/2025 | 11/18/2025 | 2 | 0 | 2 | 11/19/2025 | 11/19/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 193382 | 02301 | 3.8 |  |  | Solar |  | 05_05_317W1 | 08/14/2018 | 08/31/2018 | 2 | 2 | 0 | 09/04/2018 | 09/04/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 378903 | 02341 | 9.8 |  |  | Solar |  | 05_07_98W46 | 09/15/2021 | 09/16/2021 | 1 | 0 | 1 | 09/17/2021 | 09/17/2021 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 |  | 9/16/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 687241 | 02038 | 7.25 |  |  | Solar |  | 05_05_9L2 | 05/02/2025 | 05/20/2025 | 2 | 0 | 2 | 06/03/2025 | 06/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | BARRE | 573630 | 01005 | 10 |  |  | Solar |  | 05_01_207W2 | 12/12/2023 | 12/19/2023 | 5 | 1 | 4 | 12/20/2023 | 12/20/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 | 12/12/2023 | 2/12/2025 | Y | EXP | 365 | 05/11/2024 | 06/05/2024 | 26 | 0 | 26 |  |  | 6/15/2024 | Connected |  | N
National Grid | MARLBOROUGH | 191403 | 01752 | 2200 |  |  | Solar |  | 05_09_501L2 | 12/14/2018 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/25/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 291626 | 02301 | 24.36 |  |  | Solar |  | 05_12_16J6 | 05/12/2020 | 05/14/2020 | 1 | 0 | 1 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 |  | 5/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2020 | Connected |  | N
National Grid | ATTLEBORO | 662984 | 02703 | 10 |  |  | Solar |  | 05_07_91W43 | 12/30/2024 | 01/27/2025 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | LEOMINSTER | 681042 | 01453 | 1826 |  |  | Solar |  | 05_07_797W29 | 04/07/2025 | 04/25/2025 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2025 | 06/06/2025 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 507457 | 01082 | 8.448 |  |  | Solar |  | 05_05_341W2 | 03/16/2023 | 04/25/2023 | 28 | 27 | 1 | 04/26/2023 | 04/26/2023 | 105 | 82 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  | 10/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2023 | Connected |  | N
National Grid | MALDEN | 733815 | 02148 | 0 |  |  | Battery Add-On |  | 05_09_604W2 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 421420 | 02301 | 0 |  |  | Solar |  | 05_05_317W1 | 12/07/2022 | 12/19/2022 | 8 | 7 | 1 | 12/20/2022 | 12/20/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2023 | Connected |  | N
National Grid | HANSON | 381609 | 02341 | 9.8 |  |  | Solar |  | 05_07_98W46 | 09/23/2021 | 12/29/2021 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 09/23/2021 |  | Y | EXP |  | 04/23/2022 | 04/25/2022 | 3 | 0 | 3 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 700980 | 02038 | 7.6 |  |  | Solar |  | 05_05_9L2 | 06/25/2025 | 07/10/2025 | 2 | 0 | 2 | 07/18/2025 | 07/18/2025 | 13 | 0 | 13 | 08/22/2025 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 06/25/2025 | 9/10/2026 | Y | EXP | 365 | 11/04/2025 | 11/24/2025 | 21 | 0 | 21 |  |  | 12/5/2025 | Connected |  | N
National Grid | OAKHAM | 576114 | 01068 | 34.5 |  |  | Solar |  | 05_01_207W2 | 12/06/2023 | 02/01/2024 | 38 | 26 | 12 | 02/02/2024 | 02/02/2024 | 144 | 25 | 119 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 197527 | 01752 | 4998 |  |  | Solar |  | 05_09_501L2 | 11/13/2018 | 11/30/2018 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 12/28/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 669885 | 02301 | 7.54 |  |  | Solar |  | 05_12_16J6 | 02/06/2025 | 03/18/2025 | 12 | 7 | 5 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | ATTLEBORO | 672475 | 02703 | 3.8 |  |  | Solar |  | 05_07_91W43 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 568963 | 01453 | 0 |  |  | Battery Add-On |  | 05_05_341W2 | 11/06/2023 | 12/07/2023 | 21 | 19 | 2 | 12/08/2023 | 12/08/2023 | 87 | 59 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | WARE | 735466 | 01082 | 11.4 |  |  | Solar |  | 05_09_604W2 | 11/21/2025 | 12/04/2025 | 7 | 6 | 1 | 12/05/2025 | 12/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MALDEN | 610366 | 02148 | 10.15 |  |  | Solar |  | 05_05_317W1 | 05/20/2024 | 06/24/2024 | 5 | 2 | 3 | 06/25/2024 | 06/25/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 10/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2024 | Connected |  | N
National Grid | BROCKTON | 386273 | 02301 | 15.2 |  |  | Solar |  | 05_07_98W46 | 04/05/2022 | 04/20/2022 | 11 | 10 | 1 | 04/21/2022 | 04/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  | 5/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2022 | Connected |  | N
National Grid | HANSON | 718105 | 02341 | 11.4 |  |  | Solar |  | 05_05_9L3 | 09/10/2025 | 09/26/2025 | 2 | 0 | 2 | 10/27/2025 | 10/27/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FRANKLIN | 592388 | 02038 | 7.6 |  |  | Solar |  | 05_01_207W2 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/11/2024 | 4/24/2025 | Y | EXP | 365 | 05/30/2024 | 06/04/2024 | 6 | 0 | 6 |  |  | 6/11/2024 | Connected |  | N
National Grid | OAKHAM | 200896 | 01068 | 4998 |  |  | Solar |  | 05_09_501L2 | 11/12/2018 | 11/30/2018 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 12/29/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 732515 | 01752 | 7.678 |  |  | Solar |  | 05_12_16W1 | 11/09/2025 | 12/02/2025 | 14 | 10 | 4 | 12/03/2025 | 12/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 673026 | 02301 | 7.6 |  |  | Solar |  | 05_07_91W43 | 02/24/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/24/2025 | 4/24/2026 | Y | EXP | 365 | 07/15/2025 | 10/22/2025 | 100 | 0 | 100 |  |  | 12/16/2025 | Connected |  | N
National Grid | ATTLEBORO | 712520 | 02703 | 0 |  |  | Battery Add-On |  | 05_07_797W29 | 08/15/2025 | 08/19/2025 | 2 | 0 | 2 | 08/20/2025 | 08/20/2025 | 53 | 33 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 178770 | 01453 | 10 |  |  | Solar |  | 05_05_3422W1 | 10/02/2012 | 10/02/2012 | 6 | 0 | 6 | 10/12/2012 | 10/12/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/5/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 174442 | 01082 | 1000 |  |  | Solar |  | 05_09_604W2 | 07/03/2012 | 07/03/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2012 | 08/22/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 660358 | 02148 | 16.8 |  |  | Solar |  | 05_05_317W1 | 01/22/2025 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/22/2025 | 3/14/2026 | Y | EXP | 365 | 12/05/2025 | 12/04/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | BROCKTON | 402370 | 02301 | 9.8 |  |  | Solar |  | 05_07_98W46 | 12/23/2021 | 12/29/2021 | 4 | 0 | 4 | 12/30/2021 | 12/30/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 12/23/2021 | 4/12/2023 | Y | EXP | 365 | 03/19/2022 | 04/11/2022 | 24 | 0 | 24 |  |  | 8/9/2022 | Connected |  | N
National Grid | HALIFAX | 202263 | 02338 | 7.6 |  |  | Solar |  | 05_05_9L3 | 12/19/2018 | 01/03/2019 | 8 | 1 | 7 | 01/28/2019 | 01/28/2019 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 593162 | 02038 | 3.77 |  |  | Solar |  | 05_01_207W2 | 03/03/2024 | 03/06/2024 | 3 | 0 | 3 | 03/07/2024 | 03/07/2024 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 | 03/03/2024 | 4/25/2025 | Y | EXP | 365 | 07/10/2024 | 07/16/2024 | 7 | 0 | 7 |  |  | 8/6/2024 | Connected |  | N
National Grid | BARRE | 200895 | 01005 | 1660 |  |  | Solar |  | 05_09_501L2 | 11/12/2018 | 11/30/2018 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/30/2019 | 56 | 21 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 188457 | 01772 | 9.92 |  |  | Solar |  | 05_12_16W1 | 06/18/2018 | 06/18/2018 | 21 | 21 | 0 | 08/22/2018 | 08/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 11/15/2019 | N | EXP | 450 |  |  | 0 | 0 | 0 |  |  | 10/6/2019 | Connected |  | N
National Grid | BROCKTON | 696136 | 02301 | 11.52 |  |  | Solar |  | 05_07_91W43 | 06/05/2025 | 06/10/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 716184 | 02703 | 8 |  |  | Solar |  | 05_07_797W29 | 09/02/2025 |  | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LEOMINSTER | 178769 | 01453 | 12 |  |  | Solar |  | 05_05_3422W1 | 09/18/2012 | 09/18/2012 | 7 | 0 | 7 | 09/28/2012 | 09/28/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2013 |  | 11/20/2012 | N | EXP | -55 |  |  | 0 | 0 | 0 | 1/14/2013 | 1/14/2013 | 4/1/2013 | Connected |  | N
National Grid | HARDWICK | 174611 | 01082 | 1000 |  |  | Solar |  | 05_09_604W2 | 10/28/2010 | 10/28/2010 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2011 |  | 8/8/2012 | N | STD | 335 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 8/3/2012 | Connected |  | N
National Grid | MALDEN | 174312 | 02148 | 333 |  |  | Solar |  | 05_05_317W2 | 12/21/2011 | 12/21/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 03/26/2012 | 0 | 0 | 0 | 4/2/2012 |  | 6/8/2012 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/12/2012 | 9/12/2012 | 9/17/2012 | Connected |  | N
National Grid | BROCKTON | 436238 | 02302 | 10 |  |  | Solar |  | 05_07_98W46 | 06/14/2022 | 06/15/2022 | 2 | 1 | 1 | 06/16/2022 | 06/16/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2022 | Connected |  | N
National Grid | HANSON | 205771 | 02341 | 10 |  |  | Solar |  | 05_05_9L3 | 02/13/2019 | 03/05/2019 | 12 | 12 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 | 02/13/2019 | 3/13/2020 | Y | EXP | 365 | 11/15/2019 | 01/08/2020 | 48 | 0 | 48 |  |  | 1/17/2020 | Connected |  | N
National Grid | FRANKLIN | 605055 | 02038 | 3.8 |  |  | Solar |  | 05_01_207W2 | 04/18/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/18/2024 | 5/29/2025 | Y | EXP | 365 | 08/23/2024 | 09/16/2024 | 25 | 0 | 25 |  |  | 9/20/2024 | Connected |  | N
National Grid | OAKHAM | 205168 | 01068 | 3500 |  |  | Solar |  | 05_09_501L2 | 03/19/2019 | 04/23/2019 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/18/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 199644 | 01581 | 11.4 |  |  | Solar |  | 05_12_16W1 | 12/03/2018 | 12/17/2018 | 9 | 0 | 9 | 12/18/2018 | 12/18/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 | 12/03/2018 | 12/3/2020 | Y | EXP | 365 | 01/29/2020 | 02/05/2020 | 7 | 0 | 7 |  |  | 4/15/2020 | Connected |  | N
National Grid | BROCKTON | 702055 | 02301 | 5.76 |  |  | Solar |  | 05_07_91W43 | 07/08/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 174821 | 02703 | 180 |  |  | Solar |  | 05_07_797W29 | 08/02/2013 | 08/02/2013 | 7 | 0 | 7 | 08/14/2013 | 08/14/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2013 | 08/02/2013 | 11/1/2014 | Y | EXP | 432 |  |  | 0 | 0 | 0 | 2/13/2015 | 2/13/2015 | 2/13/2015 | Connected |  | N
National Grid | LEOMINSTER | 178768 | 01453 | 11 |  |  | Solar |  | 05_05_3422W1 | 02/15/2013 | 02/15/2013 | 5 | 0 | 5 | 02/28/2013 | 02/28/2013 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2013 |  | 12/31/2016 | N | EXP | 1354 |  |  | 0 | 0 | 0 | 4/17/2013 | 4/17/2013 | 1/1/2014 | Connected |  | N
National Grid | WARE | 174609 | 01082 | 1000 |  |  | Solar |  | 05_09_604W2 | 10/19/2010 | 10/19/2010 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2011 | 10/19/2010 | 3/2/2012 | Y | STD | 176 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/2/2012 | Connected |  | N
National Grid | MALDEN | 175038 | 02148 | 100 |  |  | Solar |  | 05_05_317W2 | 09/22/2013 | 09/22/2013 | 7 | 0 | 7 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 |  | 12/31/2013 | N | EXP | 60 |  |  | 0 | 0 | 0 | 11/8/2013 | 11/8/2013 | 1/8/2014 | Connected |  | N
National Grid | BROCKTON | 457764 | 02301 | 0 |  |  | Solar |  | 05_07_98W46 | 09/16/2022 | 09/19/2022 | 0 | 0 | 0 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 222415 | 02333 | 5 |  |  | Solar |  | 05_05_9L3 | 05/02/2019 | 05/09/2019 | 3 | 3 | 0 | 05/10/2019 | 05/10/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2019 | 05/02/2019 | 11/15/2019 | Y | EXP | 169 |  |  | 0 | 0 | 0 |  |  | 10/9/2019 | Connected |  | N
National Grid | FRANKLIN | 629800 | 02038 | 5.76 |  |  | Solar |  | 05_01_207W2 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 | 08/02/2024 | 10/2/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | OAKHAM | 225183 | 01068 | 0 |  |  | Solar |  | 05_09_501L2 | 05/03/2019 | 05/08/2019 | 2 | 0 | 2 | 05/09/2019 | 05/09/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 207669 | 01772 | 10 |  |  | Solar |  | 05_12_16W1 | 02/01/2019 | 02/22/2019 | 2 | 1 | 1 | 02/25/2019 | 02/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2019 |  | 11/15/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | BROCKTON | 672350 | 02301 | 7.54 |  |  | Solar |  | 05_07_91W46 | 02/17/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 88 | 67 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 02/17/2025 | 7/25/2026 | Y | EXP | 365 | 10/02/2025 | 11/18/2025 | 48 | 0 | 48 |  |  |  | Completion Documents |  | Y
National Grid | ATTLEBORO | 175280 | 02703 | 42.57 |  |  | Solar |  | 05_07_797W29 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/4/2015 | Connected |  | N
National Grid | LEOMINSTER | 178760 | 01453 | 300 |  |  | Solar |  | 05_05_3422W1 | 12/22/2011 | 12/22/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 174680 | 01082 | 19.99 |  |  | Solar |  | 05_09_604W2 | 01/06/2014 | 01/06/2014 | 5 | 0 | 5 | 01/14/2014 | 01/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2014 | 01/06/2014 | 3/31/2014 | Y | EXP | 52 | 01/22/2015 | 04/08/2014 | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 7/8/2014 | Connected |  | N
National Grid | MALDEN | 189707 | 02148 | 472.5 |  |  | Natural Gas |  | 05_05_317W2 | 07/03/2018 | 07/03/2018 | 33 | 24 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 12/31/2019 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | BROCKTON | 465211 | 02301 | 15.2 |  |  | Solar |  | 05_07_98W46 | 10/02/2022 | 10/10/2022 | 6 | 3 | 3 | 10/11/2022 | 10/11/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2022 | 10/02/2022 | 8/1/2024 | Y | EXP | 500 | 06/09/2023 | 04/16/2024 | 313 | 3 | 310 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 299443 | 02333 | 7.44 |  |  | Solar |  | 05_05_9L3 | 07/02/2020 | 07/08/2020 | 3 | 1 | 2 | 07/09/2020 | 07/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 | 07/02/2020 | 7/5/2021 | Y | EXP | 365 | 10/06/2020 | 10/26/2020 | 20 | 0 | 20 |  |  | 11/4/2020 | Connected |  | N
National Grid | FRANKLIN | 632334 | 02038 | 7.6 |  |  | Solar |  | 05_01_207W2 | 08/21/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 | 08/21/2024 | 9/16/2025 | Y | EXP | 365 | 01/09/2025 | 01/08/2025 | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | OAKHAM | 288610 | 01068 | 3.8 |  |  | Solar |  | 05_09_501L2 | 05/28/2020 |  | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 291578 | 01581 | 7.6 |  |  | Solar |  | 05_12_16W1 | 05/20/2020 | 05/27/2020 | 3 | 0 | 3 | 05/28/2020 | 05/28/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/20/2020 | 9/9/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2021 | Connected |  | N
National Grid | BROCKTON | 711480 | 02301 | 20 |  |  | Solar |  | 05_07_91W46 | 08/19/2025 | 08/28/2025 | 6 | 2 | 4 | 08/29/2025 | 08/29/2025 | 41 | 22 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 177803 | 02703 | 499.5 |  |  | Solar |  | 05_07_797W29 | 10/11/2017 | 10/11/2017 | 103 | 96 | 7 | 03/23/2018 | 03/23/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 | 10/11/2017 | 2/12/2021 | Y | EXP | 573 | 07/19/2019 | 08/04/2020 | 382 | 0 | 382 |  |  | 2/9/2021 | Connected |  | N
National Grid | LEOMINSTER | 178803 | 01453 | 15.2 |  |  | Solar |  | 05_05_3422W1 | 02/01/2018 | 02/01/2018 | 32 | 0 | 32 | 04/26/2018 | 04/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 |  | 2/7/2019 | N | EXP | 287 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | HARDWICK | 174818 | 01037 | 749 |  |  | Solar |  | 05_09_604W2 | 07/29/2013 | 07/29/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2013 | 11/18/2013 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 549586 | 02148 | 200 |  |  | Solar |  | 05_05_317W2 | 09/25/2023 | 03/07/2024 | 111 | 102 | 9 | 03/08/2024 | 03/08/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 5/27/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | BROCKTON | 495450 | 02301 | 3.8 |  |  | Solar |  | 05_07_98W46 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 335835 | 02382 | 9.12 |  |  | Solar |  | 05_05_9L3 | 04/15/2021 | 05/14/2021 | 20 | 20 | 0 | 05/17/2021 | 05/17/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid |  | 635778 | 02093 | 6 |  |  | Solar |  | 05_01_207W2 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/27/2024 | 1/7/2026 | Y | EXP | 365 | 02/12/2025 | 03/03/2025 | 20 | 0 | 20 |  |  | 3/18/2025 | Connected |  | N
National Grid | BARRE | 291680 | 01005 | 0 |  |  | Other |  | 05_09_501L2 | 08/31/2020 | 09/16/2020 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2020 | 10/08/2020 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 346151 | 01772 | 19.893 |  |  | Solar |  | 05_12_16W1 | 03/10/2021 | 03/17/2021 | 4 | 4 | 0 | 03/18/2021 | 03/18/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 |  | 3/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2021 | Connected |  | N
National Grid | BROCKTON | 175465 | 02301 | 490 |  |  | Solar |  | 05_07_91W46 | 09/24/2014 | 09/24/2014 | 7 | 0 | 7 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2014 |  | 1/30/2015 | N | EXP | 93 |  |  | 0 | 0 | 0 | 2/17/2016 | 2/17/2016 | 2/17/2016 | Connected |  | N
National Grid | ATTLEBORO | 177856 | 02703 | 3.8 |  |  | Solar |  | 05_07_797W29 | 04/11/2017 | 04/11/2017 | 3 | 2 | 1 | 04/14/2017 | 04/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2017 | 04/11/2017 | 4/16/2018 | Y | EXP | 362 | 06/28/2017 | 07/17/2017 | 12 | 0 | 12 | 10/16/2017 | 10/16/2017 | 10/16/2017 | Connected |  | N
National Grid | LEOMINSTER | 178793 | 01453 | 133.2 |  |  | Solar |  | 05_05_3422W1 | 02/23/2017 | 02/23/2017 | 2 | 0 | 2 | 02/27/2017 | 02/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 |  | 2/28/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/16/2017 | Connected |  | N
National Grid | HARDWICK | 175058 | 01037 | 2000 |  |  | Solar |  | 05_09_604W2 | 10/17/2012 | 10/17/2012 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 02/04/2013 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 625569 | 02148 | 499 |  |  | Solar |  | 05_05_317W2 | 09/25/2024 |  | 73 | 66 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 500083 | 02302 | 0 |  |  | Solar |  | 05_07_98W46 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 124 | 102 | 22 | 12/06/2023 | 01/17/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 356770 | 02333 | 300 |  |  | Solar |  | 05_05_9L3 | 07/14/2021 | 08/10/2021 | 19 | 9 | 10 |  |  | 48 | 20 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2022 | 07/14/2021 | 10/19/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 639505 | 02093 | 3.8 |  |  | Solar |  | 05_01_207W2 | 09/11/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 09/11/2024 | 12/18/2025 | Y | EXP | 365 | 01/30/2025 | 02/12/2025 | 14 | 0 | 14 |  |  | 2/20/2025 | Connected |  | N
National Grid | BARRE | 315000 | 01005 | 5 |  |  | Solar |  | 05_09_501L2 | 10/06/2020 |  | 70 | 48 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 362215 | 01752 | 7.6 |  |  | Solar |  | 05_12_16W1 | 07/19/2021 | 12/29/2021 | 1 | 0 | 1 | 07/21/2021 | 07/21/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 | 07/19/2021 | 1/28/2023 | Y | EXP | 365 | 01/29/2022 | 01/28/2022 | 0 | 0 | 0 |  |  | 3/16/2022 | Connected |  | N
National Grid | BROCKTON | 184909 | 02301 | 125 |  |  | Natural Gas |  | 05_07_91W46 | 06/21/2018 | 06/21/2018 | 15 | 12 | 3 | 07/20/2018 | 07/20/2018 | 39 | 17 | 22 | 10/12/2018 | 11/21/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 |  | 11/21/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 6/7/2019 | N | EXP | 183 |  |  | 0 | 0 | 0 |  |  | 7/17/2019 | Connected |  | N
National Grid | ATTLEBORO | 177855 | 02703 | 3.8 |  |  | Solar |  | 05_07_797W29 | 04/11/2017 | 04/11/2017 | 3 | 3 | 0 | 04/14/2017 | 04/14/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2017 | 04/11/2017 | 7/30/2020 | Y | EXP | 942 | 06/28/2017 | 07/17/2017 | 12 | 0 | 12 |  |  | 6/1/2020 | Connected |  | N
National Grid | LEOMINSTER | 178792 | 01453 | 28.8 |  |  | Solar |  | 05_05_3422W1 | 02/23/2017 | 02/23/2017 | 2 | 0 | 2 | 02/27/2017 | 02/27/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 176071 | 01082 | 10 |  |  | Solar |  | 05_09_604W2 | 06/19/2015 | 06/19/2015 | 12 | 12 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 6/28/2016 | N | EXP | 336 |  |  | 0 | 0 | 0 | 7/28/2015 | 7/28/2015 | 6/30/2016 | Connected |  | N
National Grid | SAUGUS | 650004 | 01906 | 0 |  |  | Other |  | 05_05_317W3 | 05/02/2025 | 07/11/2025 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 12/18/2025 | 109 | 92 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 520042 | 02301 | 7.83 |  |  | Solar |  | 05_07_98W46 | 04/27/2023 | 05/15/2023 | 12 | 9 | 3 | 05/16/2023 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 7/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | BRIDGEWATER | 398708 | 02333 | 7.6 |  |  | Solar |  | 05_05_9L3 | 12/02/2021 | 12/07/2021 | 3 | 0 | 3 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 2/22/2023 | N | EXP | 405 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 645900 | 02093 | 7.6 |  |  | Solar |  | 05_01_207W2 | 10/09/2024 | 10/24/2024 | 9 | 6 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | BARRE | 318585 | 01005 | 0 |  |  | Other |  | 05_09_501L2 | 11/06/2020 |  | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 389679 | 01752 | 8.027 |  |  | Solar |  | 05_12_16W1 | 10/25/2021 | 01/03/2022 | 3 | 3 | 0 | 10/27/2021 | 10/27/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/25/2021 | 12/29/2022 | Y | EXP | 365 | 01/13/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 8/23/2022 | Connected |  | N
National Grid | BROCKTON | 199415 | 02301 | 430 |  |  | Solar |  | 05_07_91W46 | 10/25/2018 | 11/13/2018 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 12/27/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178510 | 02703 | 6 |  |  | Solar |  | 05_07_797W29 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/15/2018 | 03/15/2018 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/08/2018 | 3/13/2019 | Y | EXP | 306 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | LEOMINSTER | 178785 | 01453 | 480 |  |  | Solar |  | 05_05_3422W1 | 08/18/2015 | 08/18/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 268 | 0 | 268 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 176349 | 01082 | 2000 |  |  | Solar |  | 05_09_604W2 | 02/25/2015 | 03/09/2015 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 12/22/2016 | 02/17/2017 | 38 | 11 | 27 | 3/30/2017 | 02/25/2015 | 4/21/2021 | Y | STD | 1250 | 01/11/2020 | 02/12/2021 | 397 | 180 | 217 |  |  | 4/20/2021 | Connected |  | N
National Grid | SAUGUS | 177488 | 01906 | 7.6 |  |  | Solar |  | 05_05_317W3 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 361 | 08/22/2017 | 09/12/2017 | 14 | 0 | 14 | 9/25/2017 | 9/25/2017 | 9/28/2017 | Connected |  | N
National Grid | BROCKTON | 534910 | 02302 | 5.76 |  |  | Solar |  | 05_07_98W46 | 06/22/2023 | 06/26/2023 | 2 | 0 | 2 | 06/27/2023 | 06/27/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2023 | 06/22/2023 | 10/22/2024 | Y | EXP | 365 | 10/04/2023 | 10/20/2023 | 17 | 0 | 17 |  |  | 10/26/2023 | Connected |  | N
National Grid | WHITMAN | 418617 | 02382 | 0 |  |  | Battery Add-On |  | 05_05_9L3 | 03/21/2022 | 04/05/2022 | 11 | 10 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 648296 | 02038 | 10 |  |  | Solar |  | 05_01_207W2 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | OAKHAM | 327466 | 01068 | 6.24 |  |  | Solar |  | 05_09_501L2 | 12/01/2020 | 01/05/2021 | 22 | 18 | 4 | 01/06/2021 | 01/06/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 1/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2021 | Connected |  | N
National Grid | MARLBOROUGH | 422479 | 01752 | 9.57 |  |  | Solar |  | 05_12_16W1 | 04/20/2022 | 04/21/2022 | 1 | 0 | 1 | 04/22/2022 | 04/22/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2022 | 04/20/2022 | 10/20/2023 | Y | EXP | 365 | 09/14/2022 | 10/14/2022 | 31 | 0 | 31 |  |  | 2/15/2023 | Connected |  | N
National Grid | BROCKTON | 204748 | 02301 | 1380 |  |  | Solar |  | 05_07_91W46 | 12/27/2018 | 01/16/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2019 | 02/28/2019 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 | 12/27/2018 | 3/10/2025 | Y | STD | 860 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ATTLEBORO | 194877 | 02703 | 3.8 |  |  | Solar |  | 05_07_797W29 | 08/31/2018 | 10/01/2018 | 4 | 4 | 0 | 10/02/2018 | 10/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2018 |  | 10/18/2019 | N | EXP | 380 |  |  | 0 | 0 | 0 |  |  | 9/9/2019 | Connected |  | N
National Grid | LEOMINSTER | 185160 | 01453 | 10.56 |  |  | Solar |  | 05_05_3422W1 | 06/08/2018 | 06/08/2018 | 18 | 7 | 11 | 06/13/2018 | 06/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2018 | Connected |  | N
National Grid | WARE | 176715 | 01082 | 16.4 |  |  | Solar |  | 05_09_604W2 | 01/08/2016 | 01/08/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/27/2017 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 289768 | 02148 | 166.6 |  |  | Solar |  | 05_05_317W3 | 06/10/2020 | 07/06/2020 | 18 | 13 | 5 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 7/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2021 | Connected |  | N
National Grid | BROCKTON | 554912 | 02302 | 5 |  |  | Solar |  | 05_07_98W46 | 09/15/2023 | 10/24/2023 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 444120 | 02333 | 9.86 |  |  | Solar |  | 05_05_9L3 | 09/09/2022 | 09/13/2022 | 2 | 0 | 2 | 09/14/2022 | 09/14/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 10/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | N
National Grid |  | 649022 | 02093 | 3.8 |  |  | Solar |  | 05_01_207W2 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 329493 | 01535 | 0 |  |  | Battery Add-On |  | 05_09_501L2 | 12/15/2020 | 01/11/2021 | 17 | 13 | 4 | 01/12/2021 | 01/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 | 12/15/2020 | 5/23/2022 | Y | EXP | 365 | 05/07/2021 | 05/18/2021 | 11 | 0 | 11 |  |  | 11/3/2021 | Connected |  | N
National Grid | MARLBOROUGH | 468441 | 01752 | 7.6 |  |  | Solar |  | 05_12_16W1 | 10/21/2022 | 10/26/2022 | 3 | 0 | 3 | 10/27/2022 | 10/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/21/2022 | 7/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2023 | Connected |  | N
National Grid | BROCKTON | 213914 | 02301 | 100 |  |  | Solar |  | 05_07_91W46 | 03/14/2019 | 03/19/2019 | 2 | 0 | 2 | 03/20/2019 | 03/20/2019 | 7 | 0 | 7 | 04/05/2019 | 06/03/2019 | 41 | 15 | 26 |  |  | 0 | 0 | 0 |  | 06/03/2019 | 41 | 15 | 26 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 194734 | 02703 | 10 |  |  | Solar |  | 05_07_797W29 | 11/19/2018 | 10/23/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 | 11/19/2018 | 3/27/2020 | Y | EXP | 472 | 11/15/2019 | 12/12/2019 | 27 | 0 | 27 |  |  | 12/12/2019 | Connected |  | N
National Grid | LEOMINSTER | 185621 | 01453 | 996 |  |  | Solar |  | 05_05_3422W1 | 05/24/2018 | 05/24/2018 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2018 | 08/02/2018 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 05/24/2018 | 3/24/2023 | Y | STD | 575 | 10/23/2021 | 01/27/2023 | 461 | 4 | 457 |  |  | 3/14/2023 | Connected |  | N
National Grid | WARE | 176993 | 01082 | 16 |  |  | Solar |  | 05_09_604W2 | 03/15/2017 | 03/15/2017 | 10 | 10 | 0 | 03/31/2017 | 03/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 |  | 3/20/2018 | N | EXP | 350 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | SAUGUS | 324464 | 01906 | 16 |  |  | Solar |  | 05_05_317W3 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 587972 | 02302 | 6.67 |  |  | Solar |  | 05_07_98W46 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 30 | 23 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 604389 | 02333 | 10 |  |  | Solar |  | 05_05_9L3 | 04/16/2024 | 04/24/2024 | 1 | 0 | 1 | 04/25/2024 | 04/25/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid |  | 649640 | 02093 | 3.8 |  |  | Solar |  | 05_01_207W2 | 11/06/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/06/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | OAKHAM | 339048 | 01068 | 5 |  |  | Solar |  | 05_09_501L2 | 02/05/2021 | 04/14/2021 | 48 | 48 | 0 | 04/15/2021 | 04/15/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 471967 | 01752 | 3.8 |  |  | Solar |  | 05_12_16W1 | 12/13/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2023 | Connected |  | N
National Grid | BROCKTON | 330313 | 02301 | 7.6 |  |  | Solar |  | 05_07_91W46 | 12/21/2020 | 12/22/2020 | 0 | 0 | 0 | 12/23/2020 | 12/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 | 12/21/2020 |  | Y | EXP | 365 | 04/20/2021 | 04/19/2021 | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | ATTLEBORO | 193184 | 02703 | 780 |  |  | Solar |  | 05_07_797W29 | 09/11/2018 | 09/25/2018 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 11/06/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 | 09/11/2018 | 11/10/2021 | Y | STD | 484 | 06/11/2021 | 09/27/2021 | 90 | 3 | 87 | 10/1/2021 | 9/30/2021 | 10/7/2021 | Connected |  | N
National Grid | LEOMINSTER | 188212 | 01453 | 172.8 |  |  | Solar |  | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 19 | 2 | 17 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177180 | 01082 | 12.75 |  |  | Solar |  | 05_09_604W2 | 06/06/2016 | 06/06/2016 | 3 | 3 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/12/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 10/4/2016 | 10/4/2016 | 10/6/2016 | Connected |  | N
National Grid | SAUGUS | 422790 | 01906 | 17.6 |  |  | Solar |  | 05_05_317W3 | 04/08/2022 | 05/05/2022 | 19 | 17 | 2 | 05/06/2022 | 05/06/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/08/2022 | 3/8/2024 | Y | EXP | 365 | 08/11/2022 | 01/11/2023 | 154 | 0 | 154 |  |  | 8/23/2023 | Connected |  | N
National Grid | BROCKTON | 587841 | 02302 | 0 |  |  | Solar |  | 05_07_98W46 | 02/14/2024 | 03/01/2024 | 12 | 10 | 2 | 03/04/2024 | 03/04/2024 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 4/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | BRIDGEWATER | 615713 | 02333 | 9.8 |  |  | Solar |  | 05_05_9L3 | 06/05/2024 | 07/15/2024 | 24 | 18 | 6 | 07/16/2024 | 07/16/2024 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 654350 | 02093 | 6.175 |  |  | Solar |  | 05_01_207W2 | 11/14/2024 | 12/17/2024 | 12 | 7 | 5 | 12/18/2024 | 12/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 434992 | 01535 | 8.99 |  |  | Solar |  | 05_09_501L2 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 537674 | 01772 | 7.6 |  |  | Solar |  | 05_12_16W1 | 02/16/2024 | 07/07/2023 | 4 | 0 | 4 | 02/26/2024 | 02/26/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 | 02/16/2024 | 3/13/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 6/9/2024 | Connected |  | N
National Grid | BROCKTON | 331606 | 02301 | 200 |  |  | Solar |  | 05_07_91W46 | 02/02/2021 | 02/17/2021 | 9 | 0 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 211156 | 02703 | 210 |  |  | Natural Gas |  | 05_07_797W29 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 13 | 4 | 9 | 12/30/2019 | 04/01/2020 | 65 | 46 | 19 |  |  | 0 | 0 | 0 |  | 04/01/2020 | 65 | 46 | 19 |  |  | 0 | 0 | 0 | 4/1/2020 |  | 9/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2020 | Connected |  | N
National Grid | LEOMINSTER | 188150 | 01453 | 172.8 |  |  | Solar |  | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 18 | 1 | 17 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 177331 | 01031 | 990 |  |  | Solar |  | 05_09_604W2 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2016 | 12/15/2016 | 73 | 57 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 439477 | 01906 | 7.6 |  |  | Solar |  | 05_05_317W3 | 07/28/2022 | 08/01/2022 | 2 | 0 | 2 | 08/02/2022 | 08/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 07/28/2022 | 1/5/2024 | Y | EXP | 365 | 10/11/2022 | 01/24/2023 | 106 | 0 | 106 |  |  | 1/14/2023 | Connected |  | N
National Grid | BROCKTON | 604595 | 02302 | 7.6 |  |  | Solar |  | 05_07_98W46 | 04/17/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 04/17/2024 | 7/30/2025 | Y | EXP | 365 | 08/02/2024 | 10/01/2024 | 61 | 0 | 61 |  |  | 4/10/2025 | Connected |  | N
National Grid | WHITMAN | 617491 | 02382 | 7.6 |  |  | Solar |  | 05_05_9L3 | 06/14/2024 | 07/02/2024 | 8 | 3 | 5 | 07/03/2024 | 07/03/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 661571 | 02762 | 5.76 |  |  | Solar |  | 05_01_207W2 | 12/18/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 12/18/2024 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | OAKHAM | 491099 | 01068 | 11.02 |  |  | Solar |  | 05_09_501L2 | 01/26/2023 | 02/24/2023 | 21 | 20 | 1 | 02/27/2023 | 02/27/2023 | 72 | 49 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 551251 | 01772 | 3.8 |  |  | Solar |  | 05_12_16W1 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 09/01/2023 | 10/19/2024 | Y | EXP | 365 | 02/09/2024 | 02/26/2024 | 18 | 0 | 18 |  |  | 3/4/2024 | Connected |  | N
National Grid | BROCKTON | 527992 | 02301 | 20.01 |  |  | Solar |  | 05_07_91W46 | 05/20/2023 | 07/12/2023 | 35 | 33 | 2 | 07/13/2023 | 07/13/2023 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | ATTLEBORO | 260147 | 02703 | 0 |  |  | Solar |  | 05_07_797W29 | 10/15/2019 | 10/16/2019 | 0 | 0 | 0 | 10/17/2019 | 10/17/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 10/14/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2020 | Connected |  | N
National Grid | LEOMINSTER | 188144 | 01453 | 345.6 |  |  | Solar |  | 05_05_3422W1 | 06/15/2018 | 06/15/2018 | 11 | 11 | 0 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 177421 | 01037 | 17.6 |  |  | Solar |  | 05_09_604W2 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 231 | 0 | 231 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 12/11/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 456585 | 01906 | 10 |  |  | Solar |  | 05_05_317W3 | 09/05/2022 | 09/06/2022 | 1 | 0 | 1 | 09/07/2022 | 09/07/2022 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | BROCKTON | 610691 | 02302 | 0 |  |  | Solar |  | 05_07_98W46 | 05/13/2024 | 05/21/2024 | 6 | 3 | 3 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/13/2024 | 6/14/2025 | Y | EXP | 365 | 08/21/2024 | 10/02/2024 | 43 | 0 | 43 |  |  | 12/10/2024 | Connected |  | N
National Grid | BRIDGEWATER | 643142 | 02333 | 10 |  |  | Solar |  | 05_05_9L3 | 09/26/2024 | 11/15/2024 | 18 | 16 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 09/26/2024 | 1/17/2026 | Y | EXP | 365 | 02/19/2025 | 02/18/2025 | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid |  | 661778 | 02093 | 10 |  |  | Solar |  | 05_01_207W2 | 12/19/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | OAKHAM | 519111 | 01068 | 7.6 |  |  | Solar |  | 05_09_501L2 | 04/28/2023 | 05/08/2023 | 6 | 4 | 2 | 05/09/2023 | 05/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 555760 | 01772 | 2.9 |  |  | Solar |  | 05_12_16W1 | 10/11/2023 | 10/23/2023 | 8 | 4 | 4 | 10/24/2023 | 10/24/2023 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | BROCKTON | 622917 | 02301 | 6 |  |  | Solar |  | 05_07_91W46 | 07/05/2024 | 08/01/2024 | 11 | 10 | 1 | 08/02/2024 | 08/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | ATTLEBORO | 306629 | 02703 | 3.8 |  |  | Solar |  | 05_07_797W29 | 09/14/2020 | 10/02/2020 | 14 | 14 | 0 | 10/05/2020 | 10/05/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 | 09/14/2020 | 11/5/2021 | Y | EXP | 365 | 02/18/2021 | 04/07/2021 | 48 | 0 | 48 |  |  | 4/13/2021 | Connected |  | N
National Grid | LEOMINSTER | 188139 | 01453 | 259.2 |  |  | Solar |  | 05_05_3422W1 | 06/14/2018 | 06/14/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 178336 | 01082 | 1000 |  |  | Solar |  | 05_09_604W2 | 11/17/2017 | 11/17/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2017 | 12/27/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 511745 | 01906 | 15.2 |  |  | Solar |  | 05_05_317W3 | 03/16/2023 | 03/17/2023 | 1 | 0 | 1 | 03/20/2023 | 03/20/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 | 03/16/2023 | 4/27/2024 | Y | EXP | 365 | 05/06/2023 | 12/06/2023 | 215 | 0 | 215 |  |  | 12/14/2023 | Connected |  | N
National Grid | BROCKTON | 620821 | 02302 | 5 |  |  | Solar |  | 05_07_98W46 | 06/28/2024 | 07/10/2024 | 6 | 5 | 1 | 07/11/2024 | 07/11/2024 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 06/28/2024 | 8/30/2025 | Y | EXP | 365 | 09/10/2024 | 11/20/2024 | 72 | 0 | 72 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 645897 | 02333 | 15.2 |  |  | Solar |  | 05_05_9L3 | 10/11/2024 | 10/21/2024 | 5 | 4 | 1 | 10/22/2024 | 10/22/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | FRANKLIN | 663213 | 02038 | 7.6 |  |  | Solar |  | 05_01_207W2 | 12/31/2024 | 01/03/2025 | 13 | 9 | 4 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 12/31/2024 | 4/4/2026 | Y | EXP | 365 | 09/30/2025 | 10/13/2025 | 14 | 0 | 14 |  |  | 10/17/2025 | Connected |  | N
National Grid | OAKHAM | 544083 | 01068 | 7.6 |  |  | Solar |  | 05_09_501L2 | 08/18/2023 | 08/22/2023 | 2 | 0 | 2 | 08/23/2023 | 08/23/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 578271 | 01772 | 11.4 |  |  | Solar |  | 05_12_16W1 | 12/21/2023 | 12/29/2023 | 5 | 0 | 5 | 01/02/2024 | 01/02/2024 | 20 | 0 | 20 | 04/11/2024 | 02/12/2025 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 76 | 0 | 76 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/30/2025 | N | EXP | 365 | 08/31/2024 | 09/20/2024 | 21 | 0 | 21 |  |  | 12/18/2024 | Connected |  | N
National Grid | BROCKTON | 650518 | 02301 | 7.6 |  |  | Solar |  | 05_07_91W46 | 11/11/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/11/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | ATTLEBORO | 328155 | 02703 | 10 |  |  | Solar |  | 05_07_797W29 | 01/08/2021 | 01/12/2021 | 1 | 0 | 1 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/08/2021 |  | Y | EXP | 365 | 07/20/2021 | 08/17/2021 | 25 | 0 | 25 |  |  | 9/2/2021 | Connected |  | N
National Grid | LEOMINSTER | 188306 | 01453 | 259.2 |  |  | Solar |  | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 11 | 11 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 186270 | 01082 | 4998 |  |  | Solar |  | 05_09_604W2 | 05/29/2018 | 05/29/2018 | 50 | 49 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 10/12/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 507198 | 01906 | 19.72 |  |  | Solar |  | 05_05_317W3 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 4/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | BROCKTON | 621695 | 02302 | 10 |  |  | Solar |  | 05_07_98W46 | 07/01/2024 | 08/07/2024 | 24 | 21 | 3 | 08/08/2024 | 08/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 07/01/2024 | 11/7/2025 | Y | EXP | 365 | 12/18/2024 | 02/22/2025 | 67 | 0 | 67 |  |  | 7/16/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 647336 | 02333 | 0 |  |  | Solar |  | 05_05_9L3 | 12/12/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/12/2024 | 2/4/2026 | Y | EXP | 365 | 03/18/2025 | 04/07/2025 | 21 | 0 | 21 |  |  |  | Withdrawn |  | N
National Grid |  | 665465 | 02093 | 10 |  |  | Solar |  | 05_01_207W2 | 01/13/2025 | 03/12/2025 | 17 | 13 | 4 | 03/13/2025 | 03/13/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 573208 | 01068 | 7.6 |  |  | Solar |  | 05_09_501L2 | 12/12/2023 | 12/13/2023 | 1 | 0 | 1 | 12/14/2023 | 12/14/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 | 12/12/2023 | 3/8/2025 | Y | EXP | 365 | 06/13/2024 | 07/08/2024 | 26 | 0 | 26 |  |  | 7/9/2024 | Connected |  | Y
National Grid | SOUTHBOROUGH | 594652 | 01772 | 7.6 |  |  | Solar |  | 05_12_16W1 | 03/08/2024 | 03/12/2024 | 2 | 0 | 2 | 03/13/2024 | 03/13/2024 | 7 | 0 | 7 | 04/08/2024 | 07/16/2024 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  | 07/16/2024 | 67 | 0 | 67 |  |  | 0 | 0 | 0 | 6/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 653234 | 02301 | 3.8 |  |  | Solar |  | 05_07_91W46 | 11/08/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 345490 | 02703 | 500 |  |  | Solar |  | 05_07_797W29 | 04/07/2021 | 04/23/2021 | 11 | 0 | 11 |  |  | 107 | 82 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 188304 | 01453 | 302.4 |  |  | Solar |  | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 13 | 13 | 0 |  |  | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 198424 | 01082 | 2000 |  |  | Battery Add-On |  | 05_09_604W2 | 12/06/2018 | 01/19/2019 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2019 | 03/13/2019 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 554254 | 02151 | 0 |  |  | Solar |  | 05_05_317W3 | 09/08/2023 | 09/12/2023 | 2 | 0 | 2 | 09/13/2023 | 09/13/2023 | 29 | 7 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 09/08/2023 | 12/7/2024 | Y | EXP | 365 | 11/21/2023 | 11/21/2023 | 1 | 0 | 1 |  |  | 2/12/2024 | Connected |  | N
National Grid | BROCKTON | 637460 | 02382 | 7.6 |  |  | Solar |  | 05_07_98W46 | 09/03/2024 | 09/17/2024 | 1 | 0 | 1 | 09/18/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | WHITMAN | 685298 | 02382 | 16.34 |  |  | Solar |  | 05_05_9L3 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid |  | 668536 | 02093 | 7.6 |  |  | Solar |  | 05_01_207W2 | 01/29/2025 | 02/25/2025 | 4 | 0 | 4 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 576642 | 01535 | 7.6 |  |  | Solar |  | 05_09_501L2 | 01/08/2024 | 01/16/2024 | 6 | 3 | 3 | 01/17/2024 | 01/17/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 595219 | 01772 | 5 |  |  | Solar |  | 05_12_16W1 | 03/26/2024 | 03/28/2024 | 2 | 0 | 2 | 03/29/2024 | 03/29/2024 | 31 | 25 | 6 | 06/21/2024 | 07/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/19/2025 | N | EXP | 365 | 08/03/2024 | 11/12/2024 | 102 | 0 | 102 |  |  | 11/13/2024 | Connected |  | N
National Grid | BROCKTON | 653207 | 02301 | 3.8 |  |  | Solar |  | 05_07_91W46 | 11/08/2024 | 11/27/2024 | 4 | 0 | 4 | 12/02/2024 | 12/02/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 394890 | 02703 | 996 |  |  | Solar |  | 05_07_797W29 | 01/29/2022 | 03/01/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2022 | 03/02/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 188303 | 01453 | 172.8 |  |  | Solar |  | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 6 | 5 | 1 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 363219 | 01082 | 6 |  |  | Solar |  | 05_09_604W2 | 06/25/2021 | 06/30/2021 | 4 | 2 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 9/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2022 | Connected |  | N
National Grid | SAUGUS | 645386 | 01906 | 10 |  |  | Solar |  | 05_05_317W3 | 10/18/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/18/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/19/2025 | 34 | 0 | 34 |  |  | 4/22/2025 | Connected |  | N
National Grid | BROCKTON | 639218 | 02302 | 5.76 |  |  | Solar |  | 05_07_98W46 | 09/10/2024 | 09/24/2024 | 3 | 0 | 3 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | EAST BRIDGEWATER | 697764 | 02339 | 15.2 |  |  | Solar |  | 05_05_9L3 | 06/11/2025 | 06/16/2025 | 3 | 0 | 3 | 06/17/2025 | 06/17/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 06/11/2025 | 8/14/2026 | Y | EXP | 365 | 10/02/2025 | 10/01/2025 | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid |  | 670824 | 02093 | 3.9 |  |  | Solar |  | 05_01_207W2 | 02/07/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 585404 | 01535 | 11.4 |  |  | Solar |  | 05_09_501L2 | 01/26/2024 | 03/27/2024 | 42 | 41 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 01/26/2024 | 4/4/2025 | Y | EXP | 365 | 07/03/2024 | 07/05/2024 | 3 | 0 | 3 |  |  | 7/8/2024 | Connected |  | Y
National Grid | SOUTHBOROUGH | 629646 | 01772 | 5.76 |  |  | Solar |  | 05_12_16W1 | 08/02/2024 | 08/21/2024 | 5 | 0 | 5 | 08/22/2024 | 08/22/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2024 | Connected |  | N
National Grid | BROCKTON | 658949 | 02301 | 3.8 |  |  | Solar |  | 05_07_91W46 | 12/09/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 | 02/07/2025 | 03/18/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 03/18/2025 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 460265 | 02703 | 15.2 |  |  | Solar |  | 05_07_797W29 | 09/20/2022 |  | 78 | 57 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 188301 | 01453 | 302.4 |  |  | Solar |  | 05_05_3422W1 | 06/18/2018 | 06/18/2018 | 10 | 10 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 539539 | 01082 | 0 |  |  | Battery Add-On |  | 05_09_604W2 | 07/13/2023 | 07/17/2023 | 2 | 0 | 2 | 07/18/2023 | 07/18/2023 | 129 | 104 | 25 | 02/16/2024 | 02/15/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/15/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 07/13/2023 | 3/21/2025 | Y | EXP | 365 | 05/29/2024 | 12/18/2024 | 204 | 0 | 204 |  |  | 8/12/2024 | Connected |  | N
National Grid | SAUGUS | 649999 | 01906 | 16.72 |  |  | Solar |  | 05_05_317W3 | 10/25/2024 | 10/30/2024 | 3 | 0 | 3 | 10/31/2024 | 10/31/2024 | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | BROCKTON | 640647 | 02302 | 7.6 |  |  | Solar |  | 05_07_98W46 | 09/18/2024 | 10/03/2024 | 3 | 0 | 3 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 701607 | 02382 | 0 |  |  | Battery Add-On |  | 05_05_9L3 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid |  | 670642 | 02093 | 10 |  |  | Solar |  | 05_01_207W2 | 02/06/2025 | 04/11/2025 | 28 | 25 | 3 | 04/14/2025 | 04/14/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 595171 | 01068 | 7.6 |  |  | Solar |  | 05_09_501L2 | 03/13/2024 | 04/03/2024 | 16 | 12 | 4 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 635855 | 01772 | 4.93 |  |  | Solar |  | 05_12_16W1 | 08/28/2024 | 09/17/2024 | 10 | 7 | 3 | 09/18/2024 | 09/18/2024 | 8 | 0 | 8 | 12/13/2024 | 12/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 12/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/25/2026 | N | EXP | 365 | 03/18/2025 | 05/07/2025 | 51 | 12 | 39 |  |  | 4/29/2025 | Connected |  | N
National Grid | BROCKTON | 174594 | 02301 | 36.4 |  |  | Solar |  | 05_07_91W47 | 10/20/2011 | 10/20/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2012 |  | 3/2/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 3/2/2012 | Connected |  | N
National Grid | ATTLEBORO | 494260 | 02703 | 10 |  |  | Solar |  | 05_07_797W29 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  | 5/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N
National Grid | LEOMINSTER | 193188 | 01453 | 1500 |  |  | Solar |  | 05_05_3422W1 | 08/30/2018 | 10/17/2018 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 11/15/2018 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 611134 | 01082 | 9.88 |  |  | Solar |  | 05_09_604W2 | 05/15/2024 | 05/17/2024 | 2 | 1 | 1 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 177389 | 01906 | 15.2 |  |  | Solar |  | 05_05_317W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/8/2017 | 6/8/2017 | 6/13/2017 | Connected |  | N
National Grid | BROCKTON | 642925 | 02302 | 6.67 |  |  | Solar |  | 05_07_98W46 | 09/25/2024 | 11/01/2024 | 18 | 13 | 5 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 09/25/2024 | 12/2/2025 | Y | EXP | 365 | 02/26/2025 | 03/26/2025 | 29 | 0 | 29 |  |  | 3/31/2025 | Connected |  | N
National Grid | BRIDGEWATER | 265289 | 02333 | 600 |  |  | Natural Gas |  | 05_05_9L4 | 12/02/2020 | 01/05/2021 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/24/2021 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 | 12/02/2020 | 4/26/2026 | Y | STD | 609 | 06/15/2024 |  | 566 | 358 | 208 |  |  |  | Construction |  | N
National Grid |  | 599874 | 02093 | 10 |  |  | Solar |  | 05_09_501L2 | 05/29/2024 | 05/31/2024 | 2 | 1 | 1 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/29/2024 | 7/1/2025 | Y | EXP | 365 | 08/01/2024 | 07/31/2024 | 0 | 0 | 0 |  |  | 9/13/2024 | Connected |  | N
National Grid | OAKHAM | 644192 | 01068 | 7.6 |  |  | Solar |  | 05_12_16W1 | 10/01/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 25 | 0 | 25 | 01/22/2025 | 03/07/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/07/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2025 | Connected |  | Y
National Grid | SOUTHBOROUGH | 175275 | 01772 | 42.57 |  |  | Solar |  | 05_07_91W47 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 70 |  |  | 0 | 0 | 0 | 9/19/2014 | 9/19/2014 | 4/30/2015 | Connected |  | N
National Grid | BROCKTON | 517489 | 02301 | 5.22 |  |  | Solar |  | 05_07_797W29 | 11/01/2023 | 04/17/2023 | 20 | 19 | 1 | 12/01/2023 | 12/01/2023 | 74 | 51 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | ATTLEBORO | 223811 | 02703 | 0 |  |  | Solar |  | 05_05_3422W1 | 04/30/2019 | 05/01/2019 | 0 | 0 | 0 | 05/02/2019 | 05/02/2019 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2019 |  | 7/8/2019 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 7/1/2019 | Connected |  | N
National Grid | LEOMINSTER | 614764 | 01453 | 5 |  |  | Solar |  | 05_09_604W2 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 49 | 41 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2024 | Connected |  | N
National Grid | WARE | 255931 | 01082 | 10 |  |  | Solar |  | 05_05_317W4 | 09/23/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 |  | 9/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | SAUGUS | 644508 | 01906 | 7.6 |  |  | Solar |  | 05_07_98W46 | 10/03/2024 | 10/17/2024 | 3 | 0 | 3 | 10/18/2024 | 10/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/03/2024 | 12/18/2025 | Y | EXP | 365 | 04/24/2025 | 05/29/2025 | 36 | 0 | 36 |  |  | 6/27/2025 | Connected |  | N
National Grid | BROCKTON | 358156 | 02302 | 875 |  |  | Solar |  | 05_05_9L4 | 07/26/2021 | 11/04/2021 | 71 | 61 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2021 | 02/03/2022 | 62 | 15 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EAST BRIDGEWATER | 671919 | 02333 | 10 |  |  | Solar |  | 05_01_207W2 | 02/13/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid |  | 602802 | 02093 | 6 |  |  | Solar |  | 05_09_501L2 | 04/13/2024 | 04/15/2024 | 0 | 0 | 0 | 04/16/2024 | 04/16/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N
National Grid | OAKHAM | 645489 | 01068 | 6.175 |  |  | Solar |  | 05_12_16W1 | 10/07/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | Y
National Grid | SOUTHBOROUGH | 176108 | 01772 | 476 |  |  | Solar |  | 05_07_91W47 | 06/26/2015 | 06/26/2015 | 2 | 2 | 0 | 06/30/2015 | 06/30/2015 | 451 | 0 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 | 06/26/2015 | 7/1/2016 | Y | EXP | 330 |  |  | 0 | 0 | 0 | 8/6/2015 | 8/6/2015 |  | Withdrawn |  | N
National Grid | BROCKTON | 527426 | 02301 | 6.96 |  |  | Solar |  | 05_07_797W29 | 05/18/2023 | 05/22/2023 | 2 | 0 | 2 | 05/23/2023 | 05/23/2023 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2023 | Connected |  | N
National Grid | ATTLEBORO | 243834 | 02703 | 0 |  |  | Solar |  | 05_05_3422W1 | 07/16/2019 | 07/23/2019 | 4 | 0 | 4 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | LEOMINSTER | 631321 | 01453 | 7.6 |  |  | Solar |  | 05_09_604W2 | 08/08/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/08/2024 | 9/25/2025 | Y | EXP | 365 | 11/15/2024 | 06/23/2025 | 221 | 0 | 221 |  |  | 6/28/2025 | Connected |  | N
National Grid | WARE | 299834 | 01082 | 10 |  |  | Solar |  | 05_05_317W4 | 07/06/2020 | 07/29/2020 | 16 | 14 | 2 | 07/30/2020 | 07/30/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 10/16/2021 | N | EXP | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 650253 | 02148 | 10 |  |  | Solar |  | 05_07_98W46 | 11/07/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 741152 | 02302 | 9.12 |  |  | Solar |  | 05_05_9L4 | 12/18/2025 | 12/19/2025 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | EAST BRIDGEWATER | 695112 | 02333 | 15.58 |  |  | Solar |  | 05_01_207W2 | 06/11/2025 | 06/18/2025 | 3 | 0 | 3 | 09/12/2025 | 09/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | Y
National Grid |  | 602792 | 02093 | 3 |  |  | Solar |  | 05_09_501L2 | 04/26/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/26/2024 | 6/3/2025 | Y | EXP | 365 | 08/17/2024 | 09/10/2024 | 25 | 0 | 25 |  |  | 11/22/2024 | Connected |  | N
National Grid | NEW BRAINTREE | 646803 | 01531 | 5.8 |  |  | Solar |  | 05_12_16W1 | 10/14/2024 | 10/22/2024 | 4 | 0 | 4 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/14/2024 | 11/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 177267 | 01772 | 10 |  |  | Solar |  | 05_07_91W47 | 11/08/2016 | 11/08/2016 | 1 | 1 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2016 |  | 11/14/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 10/10/2017 | 10/10/2017 | 10/10/2017 | Connected |  | N
National Grid | BROCKTON | 528895 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W29 | 06/21/2023 | 06/22/2023 | 1 | 0 | 1 | 06/23/2023 | 06/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 10/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2023 | Connected |  | N
National Grid | ATTLEBORO | 295996 | 02703 | 5 |  |  | Solar |  | 05_05_3422W1 | 06/12/2020 | 06/16/2020 | 1 | 0 | 1 | 06/17/2020 | 06/17/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2020 | 06/12/2020 | 6/14/2021 | Y | EXP | 365 | 12/04/2020 | 01/19/2021 | 46 | 0 | 46 |  |  | 5/19/2021 | Connected |  | N
National Grid | LEOMINSTER | 634131 | 01453 | 7.475 |  |  | Solar |  | 05_09_604W2 | 08/23/2024 | 10/14/2024 | 15 | 11 | 4 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 08/23/2024 | 11/18/2025 | Y | EXP | 365 | 12/31/2024 | 01/21/2025 | 22 | 0 | 22 |  |  | 1/24/2025 | Connected |  | N
National Grid | WARE | 428460 | 01082 | 7.6 |  |  | Solar |  | 05_05_317W4 | 05/04/2022 | 05/12/2022 | 7 | 6 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | SAUGUS | 651868 | 01906 | 10 |  |  | Solar |  | 05_07_98W46 | 11/13/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | BROCKTON | 174147 | 02302 | 9.99 |  |  | Solar |  | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 14 | 0 | 14 | 05/03/2012 | 05/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | -200 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | WHITMAN | 499837 | 02382 | 240 |  |  | Solar |  | 05_01_207W3 | 02/20/2023 | 03/24/2023 | 24 | 14 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid |  | 611141 | 02093 | 9.28 |  |  | Solar |  | 05_09_501L2 | 05/15/2024 | 06/21/2024 | 18 | 17 | 1 | 06/24/2024 | 06/24/2024 | 81 | 37 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 649182 | 01068 | 10 |  |  | Solar |  | 05_12_16W1 | 10/23/2024 | 12/03/2024 | 21 | 19 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 204844 | 01772 | 180 |  |  | Solar |  | 05_07_91W47 | 12/28/2018 | 01/09/2019 | 7 | 4 | 3 | 01/10/2019 | 01/10/2019 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 3/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 528712 | 02301 | 3.84 |  |  | Solar |  | 05_07_797W29 | 05/30/2023 | 06/16/2023 | 14 | 13 | 1 | 06/20/2023 | 06/20/2023 | 39 | 18 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2023 | 05/30/2023 | 4/28/2025 | Y | EXP | 365 | 03/19/2024 | 05/14/2024 | 57 | 0 | 57 |  |  | 12/24/2024 | Connected |  | N
National Grid | ATTLEBORO | 318964 | 02703 | 19.25 |  |  | Solar |  | 05_05_3422W1 | 10/13/2020 | 10/14/2020 | 1 | 1 | 0 | 10/15/2020 | 10/15/2020 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | LEOMINSTER | 642285 | 01453 | 15.2 |  |  | Solar |  | 05_09_604W2 | 09/23/2024 | 09/25/2024 | 2 | 0 | 2 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 |  | 11/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | WARE | 497172 | 01082 | 15.356 |  |  | Solar |  | 05_05_317W4 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 10/31/2024 | Y | EXP | 365 | 06/14/2023 | 11/01/2023 | 141 | 0 | 141 |  |  | 11/11/2023 | Connected |  | N
National Grid | SAUGUS | 660550 | 01906 | 5.76 |  |  | Solar |  | 05_07_98W46 | 12/13/2024 | 12/19/2024 | 4 | 0 | 4 | 02/11/2025 | 02/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | Y
National Grid | BROCKTON | 174146 | 02302 | 9.99 |  |  | Solar |  | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 14 | 0 | 14 | 05/03/2012 | 05/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | -200 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | HANSON | 620051 | 02341 | 9000 |  |  | Solar |  | 05_01_207W3 | 08/12/2024 | 11/20/2024 | 69 | 60 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2024 | 06/30/2025 | 149 | 130 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid |  | 637293 | 02093 | 15.2 |  |  | Solar |  | 05_09_501L2 | 09/11/2024 | 09/19/2024 | 7 | 5 | 2 | 09/20/2024 | 09/20/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | OAKHAM | 654913 | 01068 | 3.8 |  |  | Solar |  | 05_12_16W1 | 11/19/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 284129 | 01772 | 999 |  |  | Solar |  | 05_07_91W47 | 03/23/2020 | 04/10/2020 | 14 | 9 | 5 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 03/23/2020 | 9/27/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 531257 | 02301 | 14.4 |  |  | Solar |  | 05_07_797W29 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 |  | 8/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | ATTLEBORO | 326235 | 02703 | 9.8 |  |  | Solar |  | 05_05_3422W1 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/22/2020 | 3/8/2022 | Y | EXP | 365 | 09/04/2021 | 10/12/2021 | 13 | 0 | 13 |  |  | 2/3/2022 | Connected |  | N
National Grid | LEOMINSTER | 658509 | 01453 | 5.76 |  |  | Solar |  | 05_09_604W2 | 12/04/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | WARE | 625861 | 01082 | 15.2 |  |  | Solar |  | 05_05_317W4 | 07/18/2024 | 07/24/2024 | 5 | 3 | 2 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | SAUGUS | 679036 | 01906 | 11.4 |  |  | Solar |  | 05_07_98W46 | 03/19/2025 | 05/14/2025 | 11 | 7 | 4 | 05/15/2025 | 05/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 03/19/2025 | 6/9/2026 | Y | EXP | 365 | 09/24/2025 | 10/09/2025 | 16 | 0 | 16 |  |  | 10/14/2025 | Connected |  | N
National Grid | BROCKTON | 174145 | 02302 | 9.99 |  |  | Solar |  | 05_05_9L4 | 04/10/2012 | 04/10/2012 | 13 | 0 | 13 | 05/02/2012 | 05/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2012 | 04/10/2012 | 6/1/2012 | Y | EXP | -200 | 01/21/2013 | 02/25/2013 | 19 | 0 | 19 | 3/4/2013 | 3/4/2013 | 3/15/2013 | Connected |  | N
National Grid | EAST BRIDGEWATER | 714915 | 02333 | 6.08 |  |  | Solar |  | 05_01_207W3 | 08/26/2025 | 10/22/2025 | 14 | 11 | 3 | 10/23/2025 | 10/23/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid |  | 643780 | 02093 | 10 |  |  | Solar |  | 05_09_501L2 | 10/01/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 10/01/2024 | 1/2/2026 | Y | EXP | 365 | 02/13/2025 | 02/12/2025 | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 659125 | 01535 | 10 |  |  | Solar |  | 05_12_16W1 | 12/10/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 334165 | 01772 | 9.8 |  |  | Solar |  | 05_07_91W47 | 01/11/2021 |  | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 546743 | 02301 | 10 |  |  | Solar |  | 05_07_797W29 | 08/21/2023 | 08/22/2023 | 1 | 0 | 1 | 08/23/2023 | 08/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2023 |  | 10/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2023 | Connected |  | N
National Grid | ATTLEBORO | 330825 | 02703 | 11.52 |  |  | Solar |  | 05_05_3422W1 | 12/10/2020 | 01/28/2021 | 31 | 26 | 5 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  | 1/28/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 664799 | 01453 | 6.38 |  |  | Solar |  | 05_09_604W2 | 01/09/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 660095 | 01094 | 23 |  |  | Solar |  | 05_05_317W4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | SAUGUS | 740038 | 01906 |  |  |  | Battery Add-On |  | 05_07_98W48 | 12/12/2025 | 12/18/2025 | 4 | 0 | 4 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 175606 | 02302 | 644 |  |  | Solar |  | 05_05_9L4 | 10/21/2014 | 10/21/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/25/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 174258 | 02333 | 111 |  |  | Solar |  | 05_01_207W3 | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/6/2012 | N | EXP | -128 |  |  | 0 | 0 | 0 | 8/16/2012 | 8/16/2012 | 3/2/2013 | Connected |  | N
National Grid |  | 656486 | 02093 | 10 |  |  | Solar |  | 05_09_501L2 | 11/26/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 634128 | 01005 | 6.38 |  |  | Solar |  | 05_12_16W2 | 08/21/2024 | 10/01/2024 | 24 | 21 | 3 | 10/02/2024 | 10/02/2024 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 08/21/2024 | 6/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SOUTHBOROUGH | 392417 | 01772 | 6 |  |  | Solar |  | 05_07_91W47 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 566962 | 02301 | 3.84 |  |  | Solar |  | 05_07_797W29 | 10/27/2023 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | ATTLEBORO | 387717 | 02703 | 2000 |  |  | Solar |  | 05_05_3422W1 | 10/27/2021 | 12/16/2021 | 35 | 25 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 664958 | 01453 | 15.2 |  |  | Solar |  | 05_09_604W2 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/10/2025 | 3/18/2026 | Y | EXP | 365 | 09/03/2025 | 09/02/2025 | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | WARE | 454160 | 01082 | 133.2 |  |  | Solar |  | 05_05_317W6 | 10/06/2022 | 01/24/2023 | 72 | 62 | 10 | 01/25/2023 | 01/25/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 10/06/2022 | 7/16/2026 | Y | EXP | 245 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 174210 | 02151 | 100 |  |  | Solar |  | 05_07_98W48 | 02/01/2012 | 02/01/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 2/18/2012 | N | EXP | -298 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 175718 | 02382 | 475 |  |  | Solar |  | 05_05_9L4 | 12/30/2014 | 12/30/2014 | 6 | 1 | 5 | 01/08/2015 | 01/08/2015 | 140 | 0 | 140 | 03/03/2015 | 08/03/2015 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  | 08/03/2015 | 104 | 0 | 104 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175337 | 02333 | 100 |  |  | Solar |  | 05_01_207W3 | 01/19/2015 | 01/19/2015 | 4 | 1 | 3 | 01/26/2015 | 01/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2015 |  | 6/30/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 2/12/2015 | 2/12/2015 | 6/11/2015 | Connected |  | N
National Grid |  | 667431 | 02093 | 7.6 |  |  | Solar |  | 05_09_501L2 | 01/27/2025 | 02/18/2025 | 8 | 3 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 | 01/27/2025 | 3/25/2026 | Y | EXP | 365 | 05/02/2025 | 05/08/2025 | 7 | 0 | 7 |  |  | 12/18/2025 | Connected |  | N
National Grid | BARRE | 659695 | 01005 | 11.4 |  |  | Solar |  | 05_12_16W2 | 12/10/2024 | 01/03/2025 | 14 | 10 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/10/2024 | 4/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | SOUTHBOROUGH | 541611 | 01772 | 90 |  |  | Solar |  | 05_07_91W47 | 08/07/2023 | 10/05/2023 | 43 | 33 | 10 |  |  | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 597629 | 02301 | 10 |  |  | Solar |  | 05_07_797W29 | 05/07/2024 | 06/07/2024 | 23 | 22 | 1 | 06/10/2024 | 06/10/2024 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 405839 | 02703 | 0 |  |  | Battery Add-On |  | 05_05_3422W1 | 01/23/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/04/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 668996 | 01453 | 5.76 |  |  | Solar |  | 05_09_604W2 | 01/30/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/30/2025 | 3/28/2026 | Y | EXP | 365 | 06/14/2025 |  | 202 | 0 | 202 |  |  | 11/25/2025 | Connected |  | N
National Grid | WARE | 347804 | 01082 | 216 |  |  | Solar |  | 05_05_317W6 | 03/19/2021 | 04/05/2021 | 9 | 0 | 9 | 04/06/2021 | 04/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2021 |  | 6/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | REVERE | 177165 | 02151 | 99.9 |  |  | Solar |  | 05_07_98W48 | 01/24/2017 | 01/24/2017 | 14 | 12 | 2 | 02/14/2017 | 02/14/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 1/30/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 9/12/2018 | Connected |  | N
National Grid | BROCKTON | 176321 | 02302 | 140 |  |  | Solar |  | 05_05_9L4 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 478 | 03/28/2016 | 05/16/2016 | 34 | 0 | 34 | 7/11/2016 | 7/11/2016 | 7/14/2016 | Connected |  | N
National Grid | WHITMAN | 176599 | 02382 | 75 |  |  | Solar |  | 05_01_207W3 | 12/29/2015 | 12/29/2015 | 0 | 0 | 0 | 12/30/2015 | 12/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2016 |  | 1/4/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/15/2016 | 11/15/2016 | Connected |  | N
National Grid |  | 674945 | 02093 | 15.7 |  |  | Solar |  | 05_09_501L2 | 03/03/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 | 03/03/2025 | 6/5/2026 | Y | EXP | 365 | 07/25/2025 | 10/02/2025 | 70 | 0 | 70 |  |  | 10/6/2025 | Connected |  | N
National Grid | BARRE | 742326 | 01005 | 3.8 |  |  | Solar |  | 05_12_16W2 | 12/26/2025 | 12/30/2025 | 2 | 0 | 2 | 12/31/2025 | 12/31/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 545337 | 01772 | 7.56 |  |  | Solar |  | 05_07_91W47 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 11/2/2024 | Y | EXP | 365 | 12/02/2023 | 01/19/2024 | 49 | 3 | 46 |  |  | 1/25/2024 | Connected |  | N
National Grid | BROCKTON | 603730 | 02301 | 16.128 |  |  | Solar |  | 05_07_797W29 | 04/17/2024 | 07/18/2024 | 32 | 29 | 3 | 07/19/2024 | 07/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 9/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | ATTLEBORO | 515278 | 02703 | 8.99 |  |  | Solar |  | 05_05_3422W1 | 05/25/2023 | 05/26/2023 | 1 | 0 | 1 | 05/30/2023 | 05/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | LEOMINSTER | 685631 | 01453 | 5.76 |  |  | Solar |  | 05_09_604W2 | 04/16/2025 | 05/05/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 | 04/16/2025 | 6/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | WARE | 348992 | 01082 | 100 |  |  | Solar |  | 05_05_317W6 | 03/26/2021 | 05/03/2021 | 24 | 15 | 9 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 6/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177287 | 01906 | 240 |  |  | Solar |  | 05_07_98W48 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/17/2016 | 07/21/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 |  | 2/22/2017 | N | STD | 105 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/15/2016 | 3/6/2017 | Connected |  | N
National Grid | BROCKTON | 177560 | 02302 | 594 |  |  | Solar |  | 05_05_9L4 | 07/13/2017 | 07/13/2017 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2017 | 09/06/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 176930 | 02333 | 360 |  |  | Solar |  | 05_01_207W3 | 01/27/2016 | 01/27/2016 | 2 | 2 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 | 01/27/2016 | 4/14/2017 | Y | EXP | 350 | 12/08/2016 | 03/21/2017 | 69 | 0 | 69 | 4/7/2017 | 4/7/2017 | 4/12/2017 | Connected |  | N
National Grid |  | 678319 | 02093 | 7.6 |  |  | Solar |  | 05_09_501L2 | 03/26/2025 | 04/22/2025 | 19 | 15 | 4 | 04/23/2025 | 04/23/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OAKHAM | 177868 | 01068 | 3.8 |  |  | Solar |  | 05_12_16W2 | 08/09/2017 | 08/09/2017 | 4 | 4 | 0 | 08/16/2017 | 08/16/2017 | 116 | 0 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/15/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 566719 | 01772 | 7.6 |  |  | Solar |  | 05_07_91W47 | 11/09/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N
National Grid | BROCKTON | 634802 | 02301 | 10 |  |  | Solar |  | 05_07_797W29 | 08/22/2024 | 09/17/2024 | 11 | 9 | 2 | 09/18/2024 | 09/18/2024 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 | 08/22/2024 | 12/18/2025 | Y | EXP | 365 | 12/19/2024 | 01/10/2025 | 23 | 0 | 23 |  |  | 3/15/2025 | Connected |  | N
National Grid | ATTLEBORO | 601598 | 02703 | 0 |  |  | Other |  | 05_05_3422W1 | 04/25/2024 | 07/18/2024 | 56 | 48 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2024 | 08/12/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 700297 | 01453 | 120 |  |  | Hydro |  | 05_09_604W2 | 07/22/2025 | 07/25/2025 | 3 | 2 | 1 | 07/28/2025 | 07/28/2025 | 28 | 17 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | WARE | 494891 | 01082 | 24.94 |  |  | Solar |  | 05_05_317W6 | 02/15/2023 | 03/20/2023 | 23 | 22 | 1 | 03/21/2023 | 03/21/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | SAUGUS | 192458 | 01906 | 710 |  |  | Solar |  | 05_07_98W48 | 09/14/2018 | 10/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 12/03/2018 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 |  | 5/18/2021 | N | STD | 601 |  |  | 0 | 0 | 0 |  |  | 5/12/2021 | Connected |  | N
National Grid | WHITMAN | 184801 | 02382 | 990 |  |  | Solar |  | 05_05_9L4 | 07/09/2018 | 06/12/2018 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/22/2018 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2019 |  | 1/2/2021 | N | STD | 589 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 177185 | 02382 | 225 |  |  | Solar |  | 05_01_207W3 | 08/12/2016 | 08/12/2016 | 2 | 2 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2016 |  | 11/20/2017 | N | EXP | 433 |  |  | 0 | 0 | 0 | 9/13/2017 | 9/13/2017 | 9/13/2017 | Connected |  | N
National Grid |  | 687185 | 02093 | 15.2 |  |  | Solar |  | 05_09_501L2 | 04/24/2025 | 04/29/2025 | 3 | 0 | 3 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 | 04/24/2025 | 6/15/2026 | Y | EXP | 365 | 06/18/2025 | 09/06/2025 | 81 | 0 | 81 |  |  | 9/23/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 340353 | 01535 | 7.6 |  |  | Solar |  | 05_12_16W2 | 02/03/2021 | 02/11/2021 | 5 | 3 | 2 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/23/2023 | N | EXP | 700 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 654977 | 01772 | 3.8 |  |  | Solar |  | 05_07_91W47 | 11/19/2024 | 01/03/2025 | 10 | 7 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 11/19/2024 | 3/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | BROCKTON | 646690 | 02301 | 5.76 |  |  | Solar |  | 05_07_797W29 | 10/25/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/25/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | ATTLEBORO | 609575 | 02703 | 10 |  |  | Solar |  | 05_05_3422W1 | 05/08/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/08/2024 | 12/31/2025 | Y | EXP | 365 | 07/23/2024 | 09/03/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 336793 | 01453 | 0 |  |  | Solar |  | 05_09_604W3 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/02/2021 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 597028 | 01082 | 46.5 |  |  | Solar |  | 05_05_317W6 | 03/22/2024 | 05/17/2024 | 26 | 19 | 7 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N
National Grid | EVERETT | 389742 | 02149 | 0 |  |  | Other |  | 05_07_98W48 | 11/10/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 200411 | 02382 | 492 |  |  | Solar |  | 05_05_9L4 | 11/19/2018 | 12/19/2018 | 11 | 5 | 6 |  |  | 32 | 17 | 15 | 04/02/2019 | 05/02/2019 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 05/02/2019 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/19/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 178359 | 02333 | 17.28 |  |  | Solar |  | 05_01_207W3 | 03/01/2018 | 03/01/2018 | 10 | 0 | 10 | 04/27/2018 | 04/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 3/7/2019 | N | EXP | 234 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 699285 | 02093 | 15.58 |  |  | Solar |  | 05_09_501L2 | 06/17/2025 | 06/20/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 77 | 25 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OAKHAM | 354177 | 01068 | 16.82 |  |  | Solar |  | 05_12_16W2 | 04/22/2021 | 04/23/2021 | 0 | 0 | 0 | 04/26/2021 | 04/26/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2021 | Connected |  | Y
National Grid | MARLBOROUGH | 659627 | 01752 | 6.175 |  |  | Solar |  | 05_07_91W47 | 12/10/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | EASTON | 670573 | 02375 | 10 |  |  | Solar |  | 05_07_797W29 | 02/06/2025 | 03/10/2025 | 14 | 11 | 3 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | ATTLEBORO | 616598 | 02703 | 0 |  |  | Solar |  | 05_05_3422W1 | 06/14/2024 | 07/22/2024 | 24 | 22 | 2 | 07/23/2024 | 07/23/2024 | 30 | 22 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2024 | Connected |  | N
National Grid | LEOMINSTER | 319692 | 01453 | 250 |  |  | Solar |  | 05_09_604W3 | 10/20/2020 | 12/07/2020 | 31 | 25 | 6 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | WARE | 430828 | 01082 | 237.5 |  |  | Solar |  | 05_05_317W7 | 05/25/2022 | 06/24/2022 | 20 | 14 | 6 | 06/27/2022 | 06/27/2022 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 | 05/25/2022 | 4/8/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EVERETT | 391844 | 02149 | 0 |  |  | Other |  | 05_07_98W48 | 11/11/2021 | 01/04/2022 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 325226 | 02382 | 10 |  |  | Solar |  | 05_05_9L4 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/11/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 185527 | 02333 | 4950 |  |  | Solar |  | 05_01_207W3 | 05/21/2018 | 06/19/2018 | 6 | 0 | 6 |  |  | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 05/21/2018 | 4/30/2021 | Y | STD | 726 |  |  | 0 | 0 | 0 |  |  | 4/7/2021 | Connected |  | N
National Grid |  | 699771 | 02093 | 6 |  |  | Solar |  | 05_09_501L2 | 07/09/2025 | 07/22/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 07/09/2025 | 8/18/2026 | Y | EXP | 365 | 10/02/2025 |  | 92 | 0 | 92 |  |  | 12/11/2025 | Connected |  | N
National Grid | OAKHAM | 415927 | 01068 | 3.8 |  |  | Solar |  | 05_12_16W2 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/14/2022 | 4/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | MARLBOROUGH | 487773 | 01752 | 1680 |  |  | Solar |  | 05_07_91W48 | 02/28/2023 | 03/14/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2023 | 04/11/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EASTON | 697510 | 02375 | 14.06 |  |  | Solar |  | 05_07_797W29 | 06/10/2025 | 06/26/2025 | 4 | 0 | 4 | 07/31/2025 | 07/31/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | ATTLEBORO | 616100 | 02703 | 3.8 |  |  | Solar |  | 05_05_3422W1 | 06/06/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 60 | 46 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 1/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | LEOMINSTER | 309808 | 01453 | 960 |  |  | Solar |  | 05_09_604W3 | 08/17/2021 | 01/18/2022 | 104 | 96 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2022 | 11/21/2022 | 212 | 205 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 175489 | 01082 | 16.8 |  |  | Solar |  | 05_05_317W7 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2014 |  | 10/31/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 9/8/2014 | 9/8/2014 | 12/11/2015 | Connected |  | Y
National Grid | EVERETT | 430304 | 02149 | 100 |  |  | Solar |  | 05_07_98W48 | 05/27/2022 | 08/18/2022 | 56 | 49 | 7 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 | 05/27/2022 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | WHITMAN | 331536 | 02382 | 7.6 |  |  | Solar |  | 05_05_9L4 | 01/07/2021 | 01/12/2021 | 2 | 0 | 2 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 195313 | 02333 | 995 |  |  | Solar |  | 05_01_207W3 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 |  |  | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid |  | 707554 | 02093 | 11.52 |  |  | Solar |  | 05_09_501L2 | 07/25/2025 | 09/08/2025 | 5 | 0 | 5 | 09/09/2025 | 09/09/2025 | 58 | 44 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 418839 | 01535 | 11.5 |  |  | Solar |  | 05_12_16W2 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 | 02/14/2023 | 7/16/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 671662 | 01752 | 8.99 |  |  | Solar |  | 05_07_91W48 | 02/12/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 02/12/2025 | 10/1/2026 | Y | EXP | 365 | 12/12/2025 |  | 21 | 0 | 21 |  |  |  | Construction |  | N
National Grid | EASTON | 644742 | 02375 | 1996 |  |  | Solar |  | 05_07_797W42 | 10/03/2024 |  | 68 | 25 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | ATTLEBORO | 637593 | 02703 | 0 |  |  | Solar |  | 05_05_3422W1 | 09/04/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 433961 | 01453 | 996 |  |  | Other |  | 05_09_604W3 | 08/18/2022 | 10/03/2022 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2022 | 10/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 714695 | 01031 | 7.6 |  |  | Solar |  | 05_05_317W8 | 08/26/2025 | 09/16/2025 | 5 | 2 | 3 | 11/25/2025 | 11/25/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EVERETT | 598992 | 02149 | 25 |  |  | Solar |  | 05_07_98W48 | 03/22/2024 | 04/09/2024 | 12 | 9 | 3 | 04/10/2024 | 04/10/2024 | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 357632 | 02382 | 283.2 |  |  | Solar |  | 05_05_9L4 | 07/14/2021 | 10/01/2021 | 56 | 46 | 10 |  |  | 32 | 4 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 203373 | 02333 | 19.52 |  |  | Solar |  | 05_01_207W3 | 12/10/2018 | 12/31/2018 | 13 | 5 | 8 | 01/02/2019 | 01/02/2019 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid |  | 327667 | 02093 | 0 |  |  | Other |  | 05_09_503L1 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BARRE | 502664 | 01005 | 6 |  |  | Solar |  | 05_12_16W2 | 02/22/2023 | 02/24/2023 | 2 | 0 | 2 | 02/27/2023 | 02/27/2023 | 179 | 160 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 693870 | 01752 | 7.6 |  |  | Solar |  | 05_07_91W48 | 09/12/2025 | 09/29/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 36 | 20 | 16 | 01/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | EASTON | 693546 | 02375 | 15.2 |  |  | Solar |  | 05_07_797W42 | 05/28/2025 | 06/03/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 664060 | 02703 | 5.76 |  |  | Solar |  | 05_05_3422W1 | 01/10/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | LEOMINSTER | 531613 | 01453 | 4999 |  |  | Other |  | 05_09_604W3 | 06/29/2023 | 07/26/2023 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2023 | 08/29/2023 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARDWICK | 717150 | 01037 | 12.92 |  |  | Solar |  | 05_05_317W8 | 09/05/2025 | 09/23/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EVERETT | 660345 | 02149 | 120 |  |  | Solar |  | 05_07_98W48 | 12/24/2024 | 01/10/2025 | 11 | 3 | 8 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 357619 | 02382 | 466.6 |  |  | Solar |  | 05_05_9L4 | 07/14/2021 | 08/11/2021 | 20 | 10 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 330998 | 02382 | 10 |  |  | Solar |  | 05_01_207W3 | 12/10/2020 | 12/14/2020 | 1 | 0 | 1 | 12/15/2020 | 12/15/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 327663 | 02093 | 0 |  |  | Other |  | 05_09_503L1 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 570390 | 01531 | 11.4 |  |  | Solar |  | 05_12_16W2 | 11/09/2023 | 11/16/2023 | 2 | 0 | 2 | 08/20/2024 | 08/20/2024 | 52 | 45 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 717839 | 01752 | 21.66 |  |  | Solar |  | 05_07_91W48 | 09/25/2025 | 10/20/2025 | 16 | 12 | 4 | 10/21/2025 | 10/21/2025 | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EASTON | 733746 | 02375 | 12.54 |  |  | Solar |  | 05_07_797W42 | 11/13/2025 | 11/14/2025 | 1 | 0 | 1 | 11/17/2025 | 11/17/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 683812 | 02703 | 13.12 |  |  | Solar |  | 05_05_3422W1 | 04/08/2025 | 05/06/2025 | 0 | 0 | 0 | 05/07/2025 | 05/07/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/08/2025 | 7/7/2026 | Y | EXP | 365 | 10/07/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 11/3/2025 | Connected |  | N
National Grid | LEOMINSTER | 570272 | 01453 | 1500 |  |  | Solar |  | 05_09_604W3 | 12/05/2023 | 02/28/2024 | 57 | 48 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/29/2024 | 02/29/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 12/05/2023 | 4/7/2026 | Y | STD | 112 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WARE | 728722 | 01082 | 11.5 |  |  | Solar |  | 05_05_317W8 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EVERETT | 670860 | 02149 | 7.6 |  |  | Solar |  | 05_07_98W49 | 02/07/2025 | 03/14/2025 | 5 | 0 | 5 | 03/25/2025 | 03/25/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 02/07/2025 | 5/5/2026 | Y | EXP | 365 | 05/16/2025 | 07/31/2025 | 77 | 0 | 77 |  |  |  | Completion Documents |  | N
National Grid | WHITMAN | 357402 | 02382 | 300 |  |  | Solar |  | 05_05_9L4 | 07/14/2021 | 08/11/2021 | 20 | 10 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 | 07/14/2021 | 1/6/2024 | Y | STD | 306 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 348269 | 02382 | 400 |  |  | Solar |  | 05_01_207W3 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 421650 | 02093 | 240 |  |  | Solar |  | 05_09_503L1 | 05/26/2022 | 06/14/2022 | 12 | 5 | 7 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 580198 | 01531 | 7.25 |  |  | Solar |  | 05_12_16W2 | 01/09/2024 |  | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174784 | 01752 | 180 |  |  | Solar |  | 05_07_91W48 | 07/17/2013 | 07/17/2013 | 5 | 0 | 5 | 07/25/2013 | 07/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2013 | 07/17/2013 | 7/30/2014 | Y | EXP | 355 | 04/23/2014 | 06/26/2014 | 44 | 0 | 44 | 7/17/2014 | 7/17/2014 | 7/23/2014 | Connected |  | N
National Grid | EASTON | 174559 | 02375 | 2000 |  |  | Solar |  | 05_07_797W42 | 09/02/2011 | 09/02/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/09/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2012 | 09/02/2011 | 10/31/2012 | Y | STD | -9 | 04/01/2013 | 05/28/2013 | 39 | 0 | 39 | 5/9/2013 | 5/9/2013 | 6/7/2013 | Connected |  | N
National Grid | ATTLEBORO | 699705 | 02703 | 15.2 |  |  | Solar |  | 05_05_3422W1 | 06/19/2025 | 06/30/2025 | 6 | 2 | 4 | 07/01/2025 | 07/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LANCASTER | 660297 | 01523 | 225 |  |  | Solar |  | 05_09_604W3 | 12/12/2024 | 01/14/2025 | 22 | 12 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 176029 | 01082 | 23.75 |  |  | Solar |  | 05_05_317W8 | 06/16/2015 | 06/16/2015 | 22 | 22 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 6/22/2016 | N | EXP | 330 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | EVERETT | 686134 | 02149 | 5.76 |  |  | Solar |  | 05_07_98W49 | 04/18/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/18/2025 | 6/24/2026 | Y | EXP | 365 | 07/30/2025 | 08/28/2025 | 30 | 0 | 30 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 357809 | 02301 | 499.5 |  |  | Solar |  | 05_05_9L4 | 07/30/2021 | 11/11/2021 | 71 | 60 | 11 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 426071 | 02341 | 15.2 |  |  | Solar |  | 05_01_207W3 | 04/26/2022 | 04/27/2022 | 1 | 0 | 1 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 | 04/26/2022 | 10/20/2023 | Y | EXP | 365 | 09/30/2022 | 10/18/2022 | 19 | 0 | 19 |  |  | 5/4/2023 | Connected |  | Y
National Grid |  | 634442 | 02093 | 4980 |  |  | Solar |  | 05_09_503L1 | 12/04/2024 | 01/09/2025 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2025 | 02/10/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 586800 | 01531 | 6.38 |  |  | Solar |  | 05_12_16W2 | 02/19/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175498 | 01752 | 990 |  |  | Solar |  | 05_07_91W48 | 09/26/2014 | 09/26/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 175092 | 02375 | 12 |  |  | Solar |  | 05_07_797W42 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 | 11/06/2012 | 11/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2013 |  | 1/15/2013 | N | EXP | -3 |  |  | 0 | 0 | 0 | 2/3/2014 | 2/3/2014 | 2/10/2014 | Connected |  | N
National Grid | ATTLEBORO | 655156 | 02703 | 7.22 |  |  | Solar |  | 05_05_3422W2 | 11/19/2024 | 12/04/2024 | 3 | 0 | 3 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 666567 | 01453 | 4980 |  |  | Solar |  | 05_09_604W3 | 02/07/2025 | 03/07/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 04/29/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 343536 | 01082 | 100 |  |  | Solar |  | 05_05_317W8 | 02/26/2021 | 03/15/2021 | 10 | 0 | 10 | 03/16/2021 | 03/16/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2022 | Connected |  | N
National Grid | EVERETT | 175497 | 02149 | 1889 |  |  | Solar |  | 05_07_98W49 | 09/26/2014 | 09/26/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 10/31/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 370328 | 02302 | 480 |  |  | Solar |  | 05_05_9L4 | 11/16/2021 | 12/14/2021 | 19 | 11 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 11/16/2021 | 12/16/2025 | Y | STD | 306 | 09/08/2023 | 12/09/2025 | 822 | 582 | 240 |  |  | 12/24/2025 | Connected |  | N
National Grid | BRIDGEWATER | 435106 | 02333 | 0 |  |  | Other |  | 05_01_207W3 | 07/01/2022 | 10/24/2022 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 654380 | 02093 | 10 |  |  | Solar |  | 05_09_503L1 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 4/3/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BARRE | 600537 | 01005 | 7.6 |  |  | Solar |  | 05_12_16W2 | 04/16/2024 | 06/04/2024 | 34 | 30 | 4 | 06/05/2024 | 06/05/2024 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 04/16/2024 | 11/30/2025 | Y | EXP | 365 | 03/04/2025 | 10/13/2025 | 224 | 0 | 224 |  |  | 10/22/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177759 | 01752 | 648 |  |  | Solar |  | 05_07_91W48 | 08/02/2017 | 08/02/2017 | 69 | 69 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/01/2017 | 12/18/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 08/02/2017 | 2/1/2020 | Y | STD | 523 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 176134 | 02375 | 1000 |  |  | Solar |  | 05_07_797W42 | 04/16/2015 | 04/16/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/17/2015 | 05/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 703901 | 02703 | 0 |  |  | Solar |  | 05_05_3422W2 | 07/10/2025 | 07/21/2025 | 7 | 4 | 3 | 07/22/2025 | 07/22/2025 | 98 | 82 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 690051 | 01453 | 996 |  |  | Solar |  | 05_09_604W3 | 06/03/2025 | 07/14/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PALMER | 625321 | 01069 | 0 |  |  | Other |  | 05_05_318W1 | 01/16/2025 | 05/01/2025 | 72 | 63 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2025 | 05/30/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EVERETT | 196581 | 02149 | 3.8 |  |  | Solar |  | 05_07_98W49 | 09/20/2018 | 10/12/2018 | 5 | 5 | 0 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 9/9/2019 | Connected |  | N
National Grid | BROCKTON | 374717 | 02302 | 11.4 |  |  | Solar |  | 05_05_9L4 | 08/09/2021 |  | 33 | 26 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 439256 | 02333 | 4.64 |  |  | Solar |  | 05_01_207W3 | 06/26/2022 | 07/21/2022 | 18 | 17 | 1 | 07/22/2022 | 07/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 06/26/2022 | 8/19/2023 | Y | EXP | 365 | 09/21/2022 | 10/11/2022 | 21 | 0 | 21 |  |  | 5/5/2023 | Connected |  | N
National Grid |  | 723341 | 02093 | 15.2 |  |  | Solar |  | 05_09_503L1 | 10/01/2025 | 10/07/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BARRE | 620312 | 01005 | 10 |  |  | Solar |  | 05_12_16W2 | 06/25/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/25/2024 | 8/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177826 | 01752 | 60 |  |  | Solar |  | 05_07_91W48 | 06/08/2017 | 06/08/2017 | 3 | 3 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2017 |  | 6/13/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/25/2017 | 8/25/2017 | 9/8/2017 | Connected |  | N
National Grid | EASTON | 176312 | 02375 | 5.16 |  |  | Solar |  | 05_07_797W42 | 02/25/2015 | 02/25/2015 | 9 | 6 | 3 | 03/11/2015 | 03/11/2015 | 439 | 0 | 439 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 12/31/2016 | N | EXP | 655 |  |  | 0 | 0 | 0 | 3/17/2015 | 3/17/2015 |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 188280 | 02703 | 259.2 |  |  | Solar |  | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 690043 | 01453 | 996 |  |  | Solar |  | 05_09_604W3 | 06/03/2025 | 07/17/2025 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2025 | 08/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PALMER | 174933 | 01069 | 371.2 |  |  | Solar |  | 05_05_318W1 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2014 | 08/29/2013 | 10/30/2014 | Y | EXP | 290 | 04/02/2015 | 04/10/2015 | 6 | 0 | 6 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | EVERETT | 357829 | 02149 | 9.8 |  |  | Solar |  | 05_07_98W49 | 07/15/2021 | 07/16/2021 | 1 | 1 | 0 | 07/19/2021 | 07/19/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 7/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 374279 | 02302 | 7.6 |  |  | Solar |  | 05_05_9L4 | 08/05/2021 | 08/17/2021 | 9 | 8 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 8/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 519207 | 02333 | 10 |  |  | Solar |  | 05_01_207W3 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 05/03/2023 | 6/15/2024 | Y | EXP | 365 | 08/26/2023 | 10/19/2023 | 55 | 0 | 55 |  |  | 10/28/2023 | Connected |  | N
National Grid |  | 175380 | 02093 | 499 |  |  | Solar |  | 05_09_503L1 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2014 | 08/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 | 07/09/2014 | 1/15/2016 | Y | STD | 309 | 08/03/2016 | 10/11/2016 | 47 | 0 | 47 | 3/17/2017 | 3/17/2017 | 10/17/2016 | Connected |  | N
National Grid | BARRE | 641458 | 01005 | 7.98 |  |  | Solar |  | 05_12_16W2 | 09/19/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/19/2024 | 11/13/2025 | Y | EXP | 365 | 02/28/2025 | 02/27/2025 | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | MARLBOROUGH | 244132 | 01752 | 999 |  |  | Solar |  | 05_07_91W48 | 09/17/2019 | 10/04/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2019 | 01/15/2020 | 68 | 49 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2021 | 09/17/2019 | 2/24/2023 | Y | STD | 400 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176544 | 02301 | 10 |  |  | Solar |  | 05_07_797W42 | 03/31/2016 | 03/31/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/6/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 10/3/2016 | Connected |  | N
National Grid | ATTLEBORO | 188239 | 02703 | 259.2 |  |  | Solar |  | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 11 | 11 | 0 |  |  | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 689991 | 01453 | 4980 |  |  | Solar |  | 05_09_604W3 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PALMER | 177383 | 01069 | 366.3 |  |  | Solar |  | 05_05_318W1 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/4/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 6/22/2017 | 6/22/2017 | 6/27/2017 | Connected |  | N
National Grid | EVERETT | 413113 | 02149 | 6 |  |  | Solar |  | 05_07_98W49 | 02/25/2022 | 03/01/2022 | 2 | 0 | 2 | 03/02/2022 | 03/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 02/25/2022 | 5/3/2023 | Y | EXP | 365 | 04/07/2022 | 05/02/2022 | 26 | 0 | 26 |  |  | 5/6/2022 | Connected |  | N
National Grid | BROCKTON | 384112 | 02301 | 10 |  |  | Solar |  | 05_05_9L4 | 10/14/2021 | 12/23/2021 | 4 | 2 | 2 | 10/21/2021 | 10/21/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 1/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | BRIDGEWATER | 543114 | 02333 | 7.6 |  |  | Solar |  | 05_01_207W3 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2023 |  | 9/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid |  | 175916 | 02093 | 252 |  |  | Solar |  | 05_09_503L1 | 03/12/2015 | 03/12/2015 | 8 | 6 | 2 | 03/26/2015 | 03/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 |  | 8/12/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 4/10/2015 | 4/10/2015 | 11/19/2015 | Connected |  | N
National Grid | NEW BRAINTREE | 676976 | 01531 | 999.9 |  |  | Solar |  | 05_12_16W3 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 246170 | 01752 | 10 |  |  | Solar |  | 05_07_91W48 | 09/12/2019 | 11/12/2019 | 40 | 40 | 0 | 11/13/2019 | 11/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2019 | 09/12/2019 | 9/12/2020 | Y | EXP | 365 | 02/14/2020 | 03/02/2020 | 17 | 0 | 17 |  |  | 8/11/2020 | Connected |  | N
National Grid | BROCKTON | 176989 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W42 | 03/10/2017 | 03/10/2017 | 5 | 3 | 2 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/10/2017 | 3/15/2018 | Y | EXP | 359 | 08/22/2017 | 08/31/2017 | 7 | 0 | 7 | 1/29/2018 | 1/29/2018 | 2/7/2018 | Connected |  | N
National Grid | ATTLEBORO | 188233 | 02703 | 302.4 |  |  | Solar |  | 05_05_3422W2 | 06/15/2018 | 06/15/2018 | 10 | 10 | 0 |  |  | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 730587 | 01453 | 11.5 |  |  | Solar |  | 05_09_604W3 | 10/31/2025 | 11/13/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PALMER | 178048 | 01069 | 750 |  |  | Solar |  | 05_05_318W1 | 05/05/2017 | 05/05/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 01/16/2018 | 10/25/2019 | 449 | 20 | 429 | 12/21/2018 | 05/05/2017 | 2/19/2021 | Y | STD | 500 | 01/04/2020 | 12/16/2020 | 347 | 5 | 342 |  |  | 2/12/2021 | Connected |  | N
National Grid | EVERETT | 597382 | 02149 | 6 |  |  | Solar |  | 05_07_98W49 | 03/29/2024 | 04/03/2024 | 3 | 0 | 3 | 04/04/2024 | 04/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/29/2024 | 5/15/2025 | Y | EXP | 365 | 07/23/2024 | 08/09/2024 | 18 | 0 | 18 |  |  | 1/10/2025 | Connected |  | N
National Grid | BROCKTON | 421701 | 02301 | 15.2 |  |  | Solar |  | 05_05_9L4 | 06/15/2022 | 06/24/2022 | 6 | 4 | 2 | 06/27/2022 | 06/27/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 10/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2023 | Connected |  | N
National Grid | BRIDGEWATER | 568532 | 02333 | 6.96 |  |  | Solar |  | 05_01_207W3 | 11/15/2023 | 11/21/2023 | 5 | 3 | 2 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/15/2023 | 6/30/2025 | Y | EXP | 365 | 01/30/2024 | 02/16/2024 | 18 | 0 | 18 |  |  |  | Withdrawn |  | Y
National Grid |  | 176892 | 02093 | 2000 |  |  | Solar |  | 05_09_503L1 | 11/16/2015 | 11/16/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 | 12/21/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/21/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 705094 | 01005 | 300 |  |  | Solar |  | 05_12_16W3 | 08/18/2025 | 11/10/2025 | 57 | 51 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 01/05/2026 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 451320 | 01752 | 3.8 |  |  | Solar |  | 05_07_91W48 | 08/26/2022 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 186427 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W42 | 05/25/2018 | 05/25/2018 | 24 | 19 | 5 | 06/15/2018 | 06/15/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 188112 | 02703 | 302.4 |  |  | Solar |  | 05_05_3422W2 | 06/14/2018 | 06/14/2018 | 10 | 10 | 0 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 174381 | 01453 | 1000 |  |  | Solar |  | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 178327 | 01069 | 1300 |  |  | Solar |  | 05_05_318W1 | 03/30/2018 | 03/30/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 06/18/2018 | 54 | 32 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 606381 | 02149 | 7.6 |  |  | Solar |  | 05_07_98W49 | 04/24/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 427776 | 02302 | 8.064 |  |  | Solar |  | 05_05_9L4 | 05/05/2022 | 05/16/2022 | 8 | 7 | 1 | 05/17/2022 | 05/17/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 | 05/05/2022 | 9/6/2023 | Y | EXP | 365 | 08/06/2022 | 09/03/2022 | 29 | 0 | 29 |  |  | 1/10/2023 | Connected |  | N
National Grid | BRIDGEWATER | 605468 | 02324 | 11.4 |  |  | Solar |  | 05_01_207W3 | 04/24/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 177313 | 02093 | 4290 |  |  | Solar |  | 05_09_503L1 | 02/10/2017 | 02/22/2017 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2017 | 02/23/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2018 | 02/10/2017 | 8/21/2020 | Y | STD | 526 | 07/16/2019 | 10/15/2019 | 91 | 0 | 91 |  |  | 8/20/2020 | Connected |  | N
National Grid | BARRE | 176460 | 01005 | 56 |  |  | Solar |  | 05_12_16W3 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/13/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/22/2016 | Connected |  | N
National Grid | MARLBOROUGH | 475340 | 01752 | 250 |  |  | Solar |  | 05_07_91W48 | 10/31/2023 |  | 92 | 27 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 195864 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W42 | 11/02/2018 | 11/14/2018 | 6 | 0 | 6 | 11/15/2018 | 11/15/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  | 11/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2020 | Connected |  | N
National Grid | ATTLEBORO | 188300 | 02703 | 259.2 |  |  | Solar |  | 05_05_3422W2 | 06/18/2018 | 06/18/2018 | 11 | 11 | 0 |  |  | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 174380 | 01453 | 1000 |  |  | Solar |  | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 482180 | 01069 | 2550 |  |  | Solar |  | 05_05_318W3 | 07/06/2023 | 10/25/2023 | 78 | 68 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 | 11/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | EVERETT | 609927 | 02149 | 10 |  |  | Solar |  | 05_07_98W49 | 05/17/2024 |  | 41 | 40 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 431477 | 02302 | 5.8 |  |  | Solar |  | 05_05_9L4 | 06/03/2022 | 06/06/2022 | 1 | 0 | 1 | 06/07/2022 | 06/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | BRIDGEWATER | 620474 | 02333 | 3.8 |  |  | Solar |  | 05_01_207W3 | 06/25/2024 | 07/19/2024 | 5 | 4 | 1 | 07/22/2024 | 07/22/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/25/2024 | 10/4/2025 | Y | EXP | 365 | 12/20/2024 | 01/15/2025 | 27 | 0 | 27 |  |  | 2/4/2025 | Connected |  | N
National Grid |  | 177678 | 02093 | 72 |  |  | Solar |  | 05_09_503L1 | 07/21/2017 | 08/04/2017 | 9 | 6 | 3 | 08/04/2017 | 08/04/2017 | 161 | 0 | 161 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/29/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 178582 | 01005 | 37.8 |  |  | Solar |  | 05_12_16W3 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/6/2019 | N | EXP | 280 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | Connected |  | N
National Grid | MARLBOROUGH | 476961 | 01752 | 10 |  |  | Solar |  | 05_07_91W48 | 01/26/2023 | 01/30/2023 | 2 | 0 | 2 | 01/31/2023 | 01/31/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 | 01/26/2023 | 6/23/2024 | Y | EXP | 365 | 06/22/2023 | 06/21/2023 | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | BROCKTON | 192138 | 02301 | 4975 |  |  | Solar |  | 05_07_797W42 | 09/20/2018 | 10/01/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/08/2018 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 217708 | 02703 | 25 |  |  | Solar |  | 05_05_3422W2 | 04/24/2019 | 05/06/2019 | 7 | 0 | 7 | 05/07/2019 | 05/07/2019 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  | 5/6/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2019 | Connected |  | N
National Grid | LEOMINSTER | 174379 | 01453 | 3000 |  |  | Solar |  | 05_09_604W3 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 09/18/2012 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2015 |  | 2/13/2013 | N | STD | -751 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 619605 | 01069 | 4980 |  |  | Solar |  | 05_05_318W3 | 07/17/2024 | 08/21/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2024 | 08/29/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | EVERETT | 619247 | 02149 | 8.7 |  |  | Solar |  | 05_07_98W49 | 06/20/2024 | 06/28/2024 | 4 | 0 | 4 | 07/01/2024 | 07/01/2024 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2024 | Connected |  | N
National Grid | BROCKTON | 559140 | 02302 | 0 |  |  | Battery Add-On |  | 05_05_9L4 | 09/28/2023 | 10/02/2023 | 2 | 0 | 2 | 10/03/2023 | 10/03/2023 | 104 | 84 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 644944 | 02333 | 3.8 |  |  | Solar |  | 05_01_207W3 | 10/03/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/03/2024 | 3/20/2026 | Y | EXP | 365 | 02/28/2025 |  | 307 | 90 | 217 |  |  | 12/3/2025 | Connected |  | N
National Grid |  | 177765 | 02093 | 3014 |  |  | Solar |  | 05_09_503L1 | 10/05/2017 | 10/05/2017 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2017 | 11/27/2017 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/11/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 215396 | 01005 | 5 |  |  | Solar |  | 05_12_16W3 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 04/02/2019 | 2/17/2020 | Y | EXP | 365 | 01/30/2020 | 01/29/2020 | 0 | 0 | 0 |  |  | 2/19/2020 | Connected |  | N
National Grid | MARLBOROUGH | 558519 | 01752 | 5.67 |  |  | Solar |  | 05_07_91W48 | 09/26/2023 | 10/06/2023 | 8 | 5 | 3 | 05/29/2024 | 05/29/2024 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 09/26/2023 | 10/26/2025 | Y | EXP | 365 | 12/19/2024 | 03/31/2025 | 102 | 0 | 102 |  |  | 5/29/2025 | Connected |  | N
National Grid | BROCKTON | 191425 | 02301 | 10 |  |  | Solar |  | 05_07_797W42 | 08/01/2018 | 09/18/2018 | 24 | 13 | 11 | 09/19/2018 | 09/19/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 08/01/2018 | 9/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2019 | Connected |  | N
National Grid | ATTLEBORO | 249752 | 02703 | 3.8 |  |  | Solar |  | 05_05_3422W2 | 08/20/2019 | 09/09/2019 | 12 | 6 | 6 | 09/10/2019 | 09/10/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 |  | 8/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | LEOMINSTER | 174656 | 01453 | 800 |  |  | Solar |  | 05_09_604W3 | 04/11/2011 | 04/11/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 299 |  |  | 0 | 0 | 0 | 12/3/2012 | 12/3/2012 | 12/4/2012 | Connected |  | N
National Grid | PALMER | 709064 | 01069 | 5.76 |  |  | Solar |  | 05_05_318W3 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 80 | 60 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 639502 | 01906 | 10 |  |  | Solar |  | 05_07_98W49 | 10/10/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/10/2024 | 2/4/2026 | Y | EXP | 365 | 04/18/2025 | 06/05/2025 | 49 | 0 | 49 |  |  | 6/11/2025 | Connected |  | N
National Grid | BROCKTON | 560385 | 02302 | 18.85 |  |  | Solar |  | 05_05_9L4 | 06/14/2024 |  | 79 | 55 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 652489 | 02333 | 0 |  |  | Solar |  | 05_01_207W3 | 11/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid |  | 178051 | 02093 | 4950 |  |  | Solar |  | 05_09_503L1 | 06/29/2017 | 08/10/2017 | 28 | 27 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2017 | 08/31/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 | 06/29/2017 | 10/8/2020 | Y | STD | 643 | 08/06/2019 | 10/16/2019 | 71 | 0 | 71 | 7/30/2020 | 8/20/2020 | 10/7/2020 | Connected |  | N
National Grid | NORTH BROOKFIELD | 217215 | 01535 | 3 |  |  | Solar |  | 05_12_16W3 | 04/09/2019 | 04/17/2019 | 5 | 0 | 5 | 04/18/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2019 | 04/09/2019 | 4/2/2020 | Y | EXP | 365 | 02/19/2020 | 02/26/2020 | 7 | 0 | 7 |  |  | 3/12/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 536961 | 01532 | 10 |  |  | Solar |  | 05_07_91W48 | 06/27/2023 | 07/10/2023 | 2 | 0 | 2 | 07/11/2023 | 07/11/2023 | 77 | 59 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 06/27/2023 | 12/6/2024 | Y | EXP | 365 | 02/02/2024 | 02/12/2024 | 11 | 0 | 11 |  |  | 6/26/2024 | Connected |  | N
National Grid | BROCKTON | 201018 | 02301 | 7.6 |  |  | Solar |  | 05_07_797W42 | 11/12/2018 | 11/16/2018 | 3 | 1 | 2 | 11/19/2018 | 11/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/29/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | ATTLEBORO | 319784 | 02703 | 15 |  |  | Solar |  | 05_05_3422W2 | 11/10/2020 | 11/17/2020 | 4 | 2 | 2 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | LEOMINSTER | 174689 | 01453 | 800 |  |  | Solar |  | 05_09_604W3 | 04/11/2011 | 04/11/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 299 | 07/17/2012 | 12/12/2012 | 87 | 0 | 87 | 12/3/2012 | 12/3/2012 | 12/4/2012 | Connected |  | N
National Grid | PALMER | 712988 | 01069 | 19.1 |  |  | Solar |  | 05_05_318W3 | 10/01/2025 | 10/27/2025 | 16 | 14 | 2 | 10/28/2025 | 10/28/2025 | 42 | 26 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MALDEN | 692715 | 02148 | 4.537 |  |  | Solar |  | 05_07_98W49 | 05/21/2025 | 06/12/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 64 | 52 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 538767 | 02301 | 15.2 |  |  | Solar |  | 05_05_9L4 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 54 | 26 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 653697 | 02333 | 7.6 |  |  | Solar |  | 05_01_207W3 | 11/15/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/15/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid |  | 178061 | 02093 | 2640 |  |  | Solar |  | 05_09_503L1 | 09/01/2017 | 09/26/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2017 | 11/07/2017 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 9/14/2020 | N | STD | 689 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 218392 | 01531 | 5 |  |  | Solar |  | 05_12_16W3 | 04/18/2019 | 04/26/2019 | 6 | 5 | 1 | 04/29/2019 | 04/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/18/2019 | 4/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | MARLBOROUGH | 550852 | 01752 | 8.99 |  |  | Solar |  | 05_07_91W48 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 206156 | 02301 | 3.8 |  |  | Solar |  | 05_07_797W42 | 04/17/2019 | 06/18/2019 | 42 | 40 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 341243 | 02703 | 0 |  |  | Solar |  | 05_05_3422W2 | 02/09/2021 | 02/10/2021 | 0 | 0 | 0 | 02/11/2021 | 02/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2021 |  | 7/13/2022 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 6/27/2022 | Connected |  | N
National Grid | LEOMINSTER | 175003 | 01453 | 4000 |  |  | Solar |  | 05_09_604W3 | 09/16/2013 | 09/16/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2013 | 10/25/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 |  | 8/29/2014 | N | STD | -48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 742068 | 01069 | 45.6 |  |  | Solar |  | 05_05_318W3 | 12/31/2025 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MALDEN | 632686 | 02148 | 0 |  |  | Solar |  | 05_07_99W32 | 08/14/2024 | 10/07/2024 | 28 | 24 | 4 | 10/08/2024 | 10/08/2024 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Terminated |  | N
National Grid | BROCKTON | 543889 | 02301 | 3 |  |  | Solar |  | 05_05_9L4 | 07/26/2023 | 08/04/2023 | 7 | 5 | 2 | 08/07/2023 | 08/07/2023 | 47 | 29 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 11/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 676801 | 02333 | 7.6 |  |  | Solar |  | 05_01_207W3 | 03/10/2025 | 04/28/2025 | 18 | 14 | 4 | 04/29/2025 | 04/29/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid |  | 178238 | 02093 | 6 |  |  | Solar |  | 05_09_503L1 | 02/20/2018 | 02/20/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2018 |  | 2/25/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 8/7/2018 | Connected |  | Y
National Grid | NEW BRAINTREE | 233774 | 01531 | 3.8 |  |  | Solar |  | 05_12_16W3 | 06/19/2019 | 07/09/2019 | 13 | 13 | 0 | 07/10/2019 | 07/10/2019 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2019 |  | 6/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 554752 | 01532 | 6 |  |  | Solar |  | 05_07_91W48 | 10/04/2023 | 10/10/2023 | 3 | 0 | 3 | 10/11/2023 | 10/11/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2024 | Connected |  | N
National Grid | BROCKTON | 210891 | 02301 | 10 |  |  | Solar |  | 05_07_797W42 | 02/21/2019 | 03/05/2019 | 7 | 0 | 7 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2019 | Connected |  | N
National Grid | ATTLEBORO | 383113 | 02703 | 13800 |  |  | Other |  | 05_05_3422W2 | 11/11/2021 | 12/30/2021 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2021 | 01/19/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175016 | 01453 | 1500 |  |  | Solar |  | 05_09_604W3 | 09/16/2011 | 09/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2011 | 12/12/2011 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2013 | 09/16/2011 | 11/30/2012 | Y | STD | -189 |  |  | 0 | 0 | 0 | 4/11/2014 | 4/11/2014 | 4/28/2014 | Connected |  | N
National Grid | PALMER | 174857 | 01069 | 750 |  |  | Solar |  | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | MALDEN | 175890 | 02148 | 56 |  |  | Solar |  | 05_07_99W32 | 05/27/2015 | 05/27/2015 | 1 | 1 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 10/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 12/15/2015 | Connected |  | N
National Grid | BROCKTON | 549717 | 02301 | 11.4 |  |  | Solar |  | 05_05_9L4 | 08/24/2023 | 09/13/2023 | 14 | 13 | 1 | 09/14/2023 | 09/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 08/24/2023 | 11/22/2024 | Y | EXP | 365 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 |  |  | 6/18/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 686521 | 02333 | 5.76 |  |  | Solar |  | 05_01_207W3 | 04/21/2025 | 05/14/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 178758 | 02093 | 1000 |  |  | Solar |  | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 306220 | 01531 | 10 |  |  | Solar |  | 05_12_16W3 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | BERLIN | 554224 | 01503 | 6 |  |  | Solar |  | 05_07_91W48 | 09/26/2023 | 10/03/2023 | 5 | 0 | 5 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 | 09/26/2023 | 1/31/2025 | Y | EXP | 365 | 02/27/2024 | 03/18/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 290149 | 02301 | 996 |  |  | Solar |  | 05_07_797W42 | 05/18/2020 | 06/23/2020 | 24 | 17 | 7 |  |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 405831 | 02703 | 0 |  |  | Battery Add-On |  | 05_05_3422W2 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 02/04/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175218 | 01453 | 750 |  |  | Solar |  | 05_09_604W3 | 11/03/2014 | 11/03/2014 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 | 12/19/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 174856 | 01069 | 750 |  |  | Solar |  | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | SAUGUS | 177255 | 01906 | 35 |  |  | Solar |  | 05_07_99W32 | 08/17/2016 | 08/17/2016 | 282 | 282 | 0 | 10/03/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2017 |  | 2/28/2018 | N | EXP | 147 |  |  | 0 | 0 | 0 | 1/22/2018 | 1/22/2018 | 1/19/2018 | Connected |  | N
National Grid | BROCKTON | 552428 | 02301 | 6 |  |  | Solar |  | 05_05_9L4 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2024 | Connected |  | N
National Grid | BRIDGEWATER | 405711 | 02333 | 0 |  |  | Other |  | 05_01_207W4 | 02/23/2022 | 04/01/2022 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 02/23/2022 |  | Y | STD | 1160 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid |  | 178757 | 02093 | 1000 |  |  | Solar |  | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 405846 | 01005 | 0 |  |  | Battery Add-On |  | 05_12_16W3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 562420 | 01503 | 3.8 |  |  | Solar |  | 05_07_91W48 | 10/24/2023 | 10/26/2023 | 2 | 1 | 1 | 10/27/2023 | 10/27/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 10/24/2023 | 12/7/2024 | Y | EXP | 365 | 05/07/2024 | 05/15/2024 | 9 | 0 | 9 |  |  | 5/22/2024 | Connected |  | N
National Grid | BROCKTON | 353508 | 02301 | 498 |  |  | Solar |  | 05_07_797W42 | 06/23/2021 | 09/08/2021 | 53 | 44 | 9 |  |  | 60 | 17 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 408895 | 02703 | 9.6 |  |  | Solar |  | 05_05_3422W2 | 03/22/2022 | 03/28/2022 | 4 | 0 | 4 | 03/29/2022 | 03/29/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 | 03/22/2022 | 9/14/2023 | Y | EXP | 365 | 08/25/2022 | 09/08/2022 | 15 | 0 | 15 |  |  | 1/6/2023 | Connected |  | N
National Grid | LEOMINSTER | 175238 | 01453 | 480 |  |  | Solar |  | 05_09_604W3 | 08/20/2014 | 08/20/2014 | 7 | 0 | 7 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 | 10/21/2014 | 11/24/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 11/24/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 12/24/2014 | 08/20/2014 | 11/15/2015 | Y | EXP | 326 | 09/08/2015 | 11/12/2015 | 45 | 0 | 45 | 11/6/2015 | 11/6/2015 | 11/16/2015 | Connected |  | N
National Grid | PALMER | 174855 | 01069 | 750 |  |  | Solar |  | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | SAUGUS | 177306 | 01906 | 936 |  |  | Solar |  | 05_07_99W32 | 11/16/2016 | 11/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/01/2017 | 12/18/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2018 | 11/16/2016 | 8/11/2021 | Y | STD | 197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 564312 | 02302 | 15.2 |  |  | Solar |  | 05_05_9L4 | 10/18/2023 | 10/20/2023 | 2 | 0 | 2 | 10/23/2023 | 10/23/2023 | 80 | 64 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | BRIDGEWATER | 439851 | 02333 | 2341 |  |  | Solar |  | 05_01_207W4 | 08/12/2022 | 11/16/2022 | 64 | 54 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 12/13/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid |  | 178756 | 02093 | 2550 |  |  | Solar |  | 05_09_503L1 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2012 | 05/16/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2014 | 12/27/2011 | 4/30/2016 | Y | STD | 605 | 10/13/2016 | 03/20/2017 | 106 | 0 | 106 | 7/13/2017 | 7/13/2017 | 3/31/2017 | Connected |  | N
National Grid | BARRE | 434702 | 01005 | 0 |  |  | Other |  | 05_12_16W3 | 07/12/2022 | 07/12/2022 | 67 | 58 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2023 | 02/24/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 626242 | 01740 | 5.76 |  |  | Solar |  | 05_07_91W48 | 07/19/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/19/2024 | 9/16/2025 | Y | EXP | 365 | 12/11/2024 | 01/29/2025 | 50 | 0 | 50 |  |  | 2/10/2025 | Connected |  | N
National Grid | BROCKTON | 358173 | 02301 | 9.6 |  |  | Solar |  | 05_07_797W42 | 05/14/2021 | 05/19/2021 | 3 | 3 | 0 | 05/20/2021 | 05/20/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 |  | 1/11/2023 | N | EXP | 534 |  |  | 0 | 0 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | ATTLEBORO | 606714 | 02703 | 15.3 |  |  | Solar |  | 05_05_3422W2 | 04/25/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | LEOMINSTER | 175304 | 01453 | 499 |  |  | Solar |  | 05_09_604W3 | 06/25/2014 | 06/25/2014 | 6 | 0 | 6 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2014 | 06/25/2014 | 11/18/2016 | Y | EXP | 826 | 12/02/2016 | 03/29/2017 | 79 | 0 | 79 | 4/12/2017 | 4/12/2017 | 4/12/2017 | Connected |  | N
National Grid | PALMER | 174894 | 01069 | 666 |  |  | Solar |  | 05_05_318W3 | 08/20/2013 | 08/20/2013 | 52 | 43 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2013 | 09/16/2014 | 213 | 0 | 213 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 177326 | 01906 | 828 |  |  | Solar |  | 05_07_99W32 | 06/20/2016 | 06/20/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/24/2016 | 08/03/2016 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 583657 | 02301 | 8.12 |  |  | Solar |  | 05_05_9L4 | 02/06/2024 | 02/20/2024 | 10 | 7 | 3 | 02/21/2024 | 02/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N
National Grid | BRIDGEWATER | 657558 | 02333 | 10 |  |  | Solar |  | 05_01_207W4 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 |  | 204 | 0 | 204 |  |  |  | Completion Documents |  | N
National Grid |  | 195621 | 02093 | 4885 |  |  | Solar |  | 05_09_503L1 | 10/17/2018 | 11/06/2018 | 10 | 0 | 10 |  |  | 30 | 28 | 2 |  |  | 0 | 0 | 0 | 11/07/2018 | 12/15/2018 | 30 | 28 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARDWICK | 635533 | 01037 | 6 |  |  | Solar |  | 05_07_91W48 | 08/26/2024 | 08/30/2024 | 2 | 0 | 2 | 09/03/2024 | 09/03/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BERLIN | 473695 | 01053 | 6 |  |  | Solar |  | 05_07_797W42 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 02/17/2023 | 9/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | WEYMOUTH | 317765 | 02190 | 200 |  |  | Solar |  | 05_05_3422W3 | 10/22/2020 | 11/24/2020 | 22 | 15 | 7 | 11/25/2020 | 11/25/2020 | 173 | 69 | 104 | 05/11/2021 | 12/28/2023 | 659 | 33 | 626 |  |  | 0 | 0 | 0 |  | 12/28/2023 | 659 | 33 | 626 |  |  | 0 | 0 | 0 | 1/31/2024 |  | 4/2/2026 | N | EXP | 231 | 03/29/2025 |  | 279 | 224 | 55 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 175688 | 02703 | 480 |  |  | Solar |  | 05_09_604W3 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 10/6/2014 | 05/22/2014 | 11/13/2015 | Y | EXP | 403 | 10/06/2015 | 10/21/2015 | 10 | 0 | 10 | 11/5/2015 | 11/5/2015 | 11/16/2015 | Connected |  | N
National Grid | LEOMINSTER | 174960 | 01453 | 750 |  |  | Solar |  | 05_05_318W3 | 03/01/2013 | 03/01/2013 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2013 | 04/18/2013 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 03/01/2013 | 6/30/2014 | Y | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/30/2014 | Connected |  | N
National Grid | PALMER | 178091 | 01069 | 3.8 |  |  | Solar |  | 05_07_99W32 | 07/07/2017 | 07/07/2017 | 7 | 6 | 1 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/15/2018 | N | EXP | 360 |  |  | 0 | 0 | 0 | 1/5/2018 | 1/5/2018 | 1/5/2018 | Connected |  | N
National Grid | SAUGUS | 613496 | 01906 | 5.8 |  |  | Solar |  | 05_05_9L4 | 06/05/2024 | 06/11/2024 | 4 | 3 | 1 | 06/12/2024 | 06/12/2024 | 35 | 21 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 725213 | 02301 | 100 |  |  | Solar |  | 05_01_207W4 | 10/08/2025 | 10/29/2025 | 14 | 7 | 7 |  |  | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BRIDGEWATER | 197020 | 02333 | 3840 |  |  | Solar |  | 05_09_503L1 | 09/27/2018 | 10/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 11/28/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid |  | 437637 | 02093 | 350 |  |  | Solar |  | 05_12_16W3 | 09/01/2022 | 09/23/2022 | 15 | 5 | 10 |  |  | 68 | 47 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 09/01/2022 | 8/3/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 646456 | 01005 | 3.8 |  |  | Solar |  | 05_07_91W48 | 10/29/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 515597 | 01503 | 10 |  |  | Solar |  | 05_07_797W42 | 04/04/2023 | 04/21/2023 | 13 | 12 | 1 | 04/24/2023 | 04/24/2023 | 158 | 137 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | ABINGTON | 660617 | 02351 | 10 |  |  | Solar |  | 05_05_3422W3 | 12/13/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ATTLEBORO | 175779 | 02703 | 40 |  |  | Solar |  | 05_09_604W3 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2015 | 07/21/2015 | 8/27/2017 | Y | EXP | 745 | 04/27/2017 | 05/11/2017 | 10 | 0 | 10 | 8/13/2015 | 8/13/2015 | 6/19/2017 | Connected |  | N
National Grid | LEOMINSTER | 177688 | 01453 | 4950 |  |  | Solar |  | 05_05_318W3 | 10/03/2017 | 10/24/2017 | 15 | 12 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/27/2017 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 10/03/2017 | 8/5/2021 | Y | STD | 1006 | 03/14/2021 | 07/30/2021 | 138 | 0 | 138 | 6/18/2021 | 7/30/2021 | 7/30/2021 | Connected |  | N
National Grid | PALMER | 194141 | 01069 | 660 |  |  | Solar |  | 05_07_99W32 | 10/09/2018 | 10/30/2018 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2018 | 11/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 628004 | 02148 | 18.85 |  |  | Solar |  | 05_05_9L4 | 08/01/2024 | 08/22/2024 | 12 | 10 | 2 | 08/23/2024 | 08/23/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174277 | 02301 | 25.6 |  |  | Solar |  | 05_01_207W4 | 12/14/2011 | 12/14/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 03/13/2012 | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 03/14/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 4/14/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 4/2/2012 | 4/2/2012 | 4/24/2012 | Connected |  | N
National Grid | EAST BRIDGEWATER | 201424 | 02333 | 4290 |  |  | Solar |  | 05_09_503L1 | 12/07/2018 | 01/09/2019 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2019 | 02/06/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid |  | 576689 | 02093 | 0 |  |  | Battery Add-On |  | 05_12_16W3 | 12/08/2023 | 12/19/2023 | 7 | 6 | 1 | 12/20/2023 | 12/20/2023 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | NEW BRAINTREE | 646825 | 01531 | 6.38 |  |  | Solar |  | 05_07_91W48 | 10/14/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | BERLIN | 536248 | 01503 | 15.2 |  |  | Solar |  | 05_07_797W42 | 06/26/2023 | 06/27/2023 | 2 | 1 | 1 | 06/28/2023 | 06/28/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2023 | Connected |  | N
National Grid | WEYMOUTH | 676978 | 02190 | 750 |  |  | Solar |  | 05_05_3422W3 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 175954 | 02703 | 990 |  |  | Solar |  | 05_09_604W3 | 03/12/2015 | 03/12/2015 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/24/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 184729 | 01453 | 16.64 |  |  | Solar |  | 05_05_318W3 | 05/07/2018 | 05/07/2018 | 9 | 0 | 9 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 205175 | 01069 | 0 |  |  | Solar |  | 05_07_99W32 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/22/2019 | 01/22/2019 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | MALDEN | 627851 | 02148 | 5.76 |  |  | Solar |  | 05_05_9L4 | 07/25/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2024 | Connected |  | N
National Grid | BROCKTON | 245424 | 02301 | 0 |  |  | Solar |  | 05_01_207W4 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | EAST BRIDGEWATER | 329775 | 02333 | 15.2 |  |  | Solar |  | 05_09_503L1 | 12/04/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 673208 | 02093 | 500 |  |  | Solar |  | 05_12_16W4 | 05/27/2025 | 06/26/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BARRE | 652303 | 01005 | 7.6 |  |  | Solar |  | 05_07_91W48 | 11/14/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | BERLIN | 567311 | 01503 | 10 |  |  | Solar |  | 05_07_797W42 | 11/16/2023 | 11/17/2023 | 1 | 0 | 1 | 11/20/2023 | 11/20/2023 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 | 11/16/2023 | 1/18/2025 | Y | EXP | 365 | 03/29/2024 | 04/30/2024 | 33 | 0 | 33 |  |  | 5/3/2024 | Connected |  | N
National Grid | WEYMOUTH | 742850 | 02188 | 19 |  |  | Solar |  | 05_05_3422W3 | 01/02/2026 | 01/05/2026 | 0 | 0 | 0 | 01/06/2026 | 01/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 175951 | 02703 | 990 |  |  | Solar |  | 05_09_604W3 | 03/12/2015 | 03/12/2015 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/24/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 195130 | 01453 | 479.904 |  |  | Solar |  | 05_05_318W3 | 09/06/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2018 |  | 5/31/2020 | N | EXP | 389 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | PALMER | 223586 | 01069 | 100 |  |  | Solar |  | 05_07_99W32 | 04/29/2019 | 05/21/2019 | 16 | 14 | 2 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 | 07/17/2019 | 08/20/2020 | 277 | 240 | 37 |  |  | 0 | 0 | 0 |  | 08/20/2020 | 277 | 240 | 37 |  |  | 0 | 0 | 0 | 9/9/2020 |  | 6/23/2022 | N | EXP | 365 | 03/02/2021 | 06/10/2021 | 100 | 0 | 100 |  |  | 12/27/2021 | Connected |  | N
National Grid | SAUGUS | 634091 | 01906 | 5.76 |  |  | Solar |  | 05_05_9L4 | 08/20/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 377022 | 02302 | 250 |  |  | Solar |  | 05_01_207W4 | 01/21/2022 | 02/01/2022 | 7 | 1 | 6 |  |  | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 342869 | 02333 | 10 |  |  | Solar |  | 05_09_503L1 | 03/19/2021 | 03/26/2021 | 4 | 1 | 3 | 03/29/2021 | 03/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 729210 | 02093 | 200 |  |  | Solar |  | 05_12_16W4 | 10/30/2025 | 12/04/2025 | 22 | 16 | 6 | 12/05/2025 | 12/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEW BRAINTREE | 658143 | 01531 | 7.6 |  |  | Solar |  | 05_07_91W48 | 12/03/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/03/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 598236 | 01532 | 10 |  |  | Solar |  | 05_07_797W42 | 04/15/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2024 | Connected |  | N
National Grid | WEYMOUTH | 178763 | 02188 | 142 |  |  | Solar |  | 05_05_3422W3 | 04/14/2011 | 04/14/2011 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | -42 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 9/7/2012 | Connected |  | N
National Grid | ATTLEBORO | 176322 | 02703 | 15.2 |  |  | Solar |  | 05_09_604W3 | 07/14/2015 | 07/14/2015 | 8 | 8 | 0 | 07/27/2015 | 07/27/2015 | 313 | 0 | 313 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2015 |  | 7/20/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 202568 | 01453 | 15.2 |  |  | Solar |  | 05_05_318W3 | 12/10/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 | 12/10/2018 | 9/23/2021 | Y | EXP | 365 | 04/07/2021 | 04/14/2021 | 7 | 0 | 7 |  |  | 4/23/2021 | Connected |  | N
National Grid | PALMER | 248006 | 01069 | 7.6 |  |  | Solar |  | 05_07_99W32 | 10/01/2019 | 10/03/2019 | 1 | 0 | 1 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 10/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 637461 | 01906 | 10 |  |  | Solar |  | 05_05_9L4 | 09/04/2024 | 09/16/2024 | 1 | 0 | 1 | 09/17/2024 | 09/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 429394 | 02301 | 0 |  |  | Other |  | 05_01_207W4 | 09/16/2022 | 10/21/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 | 11/09/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 390310 | 02302 | 15.2 |  |  | Solar |  | 05_09_503L1 | 11/01/2021 | 11/03/2021 | 2 | 0 | 2 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 11/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 175479 | 02035 | 240.8 |  |  | Solar |  | 05_12_16W4 | 03/13/2014 | 03/13/2014 | 10 | 5 | 5 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2014 | 03/13/2014 | 8/29/2014 | Y | EXP | 128 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 | 12/12/2014 | 12/12/2014 | 1/2/2015 | Connected |  | N
National Grid | NORTH BROOKFIELD | 662628 | 01535 | 7.475 |  |  | Solar |  | 05_07_91W48 | 12/26/2024 | 02/26/2025 | 36 | 25 | 11 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 600629 | 01503 | 9.8 |  |  | Solar |  | 05_07_797W42 | 04/12/2024 | 05/20/2024 | 0 | 0 | 0 | 07/16/2024 | 07/16/2024 | 145 | 45 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 178762 | 02190 | 102.6 |  |  | Solar |  | 05_05_3422W3 | 08/29/2011 | 08/29/2011 | 181 | 0 | 181 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2013 | 08/29/2011 | 6/23/2012 | Y | EXP | -229 | 10/11/2012 | 12/19/2012 | 32 | 0 | 32 | 2/7/2013 | 2/7/2013 | 3/12/2013 | Connected |  | N
National Grid | ATTLEBORO | 176411 | 02703 | 34.2 |  |  | Solar |  | 05_09_604W3 | 05/10/2016 | 05/10/2016 | 2 | 2 | 0 | 05/13/2016 | 05/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/10/2016 | 5/16/2017 | Y | EXP | 344 | 02/27/2017 | 03/22/2017 | 17 | 0 | 17 | 3/23/2017 | 3/23/2017 | 3/29/2017 | Connected |  | N
National Grid | LEOMINSTER | 202205 | 01453 | 20 |  |  | Solar |  | 05_05_318W3 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 279479 | 01069 | 7.6 |  |  | Solar |  | 05_07_99W32 | 02/13/2020 | 02/18/2020 | 1 | 0 | 1 | 02/19/2020 | 02/19/2020 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2020 | Connected |  | N
National Grid | MALDEN | 641014 | 02148 | 7.6 |  |  | Solar |  | 05_05_9L4 | 09/17/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 437417 | 02302 | 0 |  |  | Other |  | 05_01_207W4 | 09/26/2022 | 10/26/2022 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/17/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 440288 | 02302 | 18.85 |  |  | Solar |  | 05_09_503L1 | 06/27/2022 | 06/30/2022 | 4 | 1 | 3 | 09/09/2022 | 09/09/2022 | 14 | 14 | 0 | 10/05/2022 | 11/09/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/09/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 3/5/2024 | N | EXP | 365 | 01/07/2023 | 03/06/2023 | 59 | 0 | 59 |  |  | 3/9/2023 | Connected |  | N
National Grid | PLAINVILLE | 175930 | 02762 | 10 |  |  | Solar |  | 05_12_16W4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 360 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 8/2/2016 | Connected |  | N
National Grid | NEW BRAINTREE | 669861 | 01531 | 3.8 |  |  | Solar |  | 05_07_91W48 | 02/10/2025 | 03/14/2025 | 12 | 10 | 2 | 03/17/2025 | 03/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 6/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | Y
National Grid | BERLIN | 680697 | 01503 | 10 |  |  | Solar |  | 05_07_797W42 | 03/26/2025 | 04/04/2025 | 2 | 0 | 2 | 04/14/2025 | 04/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 03/26/2025 | 6/2/2026 | Y | EXP | 365 | 09/13/2025 | 09/12/2025 | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | ABINGTON | 178784 | 02351 | 1000 |  |  | Solar |  | 05_05_3422W3 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 03/31/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176783 | 02703 | 2000 |  |  | Solar |  | 05_09_604W3 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 241787 | 01453 | 9.28 |  |  | Solar |  | 05_05_318W3 | 09/30/2019 | 10/07/2019 | 4 | 1 | 3 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2020 | Connected |  | N
National Grid | PALMER | 303572 | 01069 | 8 |  |  | Solar |  | 05_07_99W32 | 07/28/2020 | 07/31/2020 | 3 | 3 | 0 | 08/03/2020 | 08/03/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 643239 | 02148 | 3.8 |  |  | Solar |  | 05_05_9L4 | 09/26/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 09/26/2024 | 3/21/2026 | Y | EXP | 365 | 02/22/2025 | 02/21/2025 | 0 | 0 | 0 |  |  | 4/24/2025 | Connected |  | N
National Grid | BROCKTON | 445310 | 02301 | 100 |  |  | Solar |  | 05_01_207W4 | 07/26/2022 | 08/29/2022 | 24 | 15 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EAST BRIDGEWATER | 465144 | 02333 | 50 |  |  | Solar |  | 05_09_503L1 | 10/03/2022 | 10/28/2022 | 19 | 9 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 176915 | 02762 | 14.19 |  |  | Solar |  | 05_12_16W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 348 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 11/15/2016 | Connected |  | N
National Grid | BARRE | 685885 | 01005 | 7.6 |  |  | Solar |  | 05_07_91W48 | 04/17/2025 | 04/25/2025 | 5 | 1 | 4 | 04/28/2025 | 04/28/2025 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 | 04/17/2025 | 7/11/2026 | Y | EXP | 365 | 11/18/2025 |  | 45 | 0 | 45 |  |  | 12/19/2025 | Connected |  | N
National Grid | BERLIN | 176388 | 01503 | 3.8 |  |  | Solar |  | 05_07_8W1 | 01/29/2016 | 01/29/2016 | 3 | 3 | 0 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 2/6/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/1/2016 | 12/1/2016 | 12/5/2016 | Connected |  | N
National Grid | WEYMOUTH | 178783 | 02190 | 1000 |  |  | Solar |  | 05_05_3422W3 | 01/23/2015 | 01/23/2015 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 03/31/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176812 | 02703 | 1000 |  |  | Solar |  | 05_09_604W3 | 11/05/2015 | 11/05/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/10/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 346401 | 01453 | 250 |  |  | Solar |  | 05_05_318W3 | 04/07/2021 | 04/23/2021 | 11 | 0 | 11 |  |  | 171 | 98 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 04/07/2021 | 7/20/2024 | Y | STD | 437 | 08/16/2023 | 10/27/2023 | 73 | 0 | 73 |  |  | 5/22/2024 | Connected |  | N
National Grid | PALMER | 319983 | 01069 | 35 |  |  | Natural Gas |  | 05_07_99W32 | 10/20/2020 |  | 308 | 116 | 192 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 648652 | 02148 | 10 |  |  | Solar |  | 05_05_9L4 | 10/21/2024 | 11/06/2024 | 7 | 4 | 3 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 | 01/07/2025 | 01/06/2025 | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | BROCKTON | 485045 | 02302 | 0 |  |  | Other |  | 05_01_207W4 | 02/27/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2023 | 03/24/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 540050 | 02302 | 0 |  |  | Solar |  | 05_09_503L1 | 07/13/2023 | 07/14/2023 | 1 | 0 | 1 | 07/17/2023 | 07/17/2023 | 135 | 115 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 2/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | PLAINVILLE | 177140 | 02762 | 6 |  |  | Solar |  | 05_12_16W4 | 05/27/2016 | 05/27/2016 | 9 | 9 | 0 | 06/14/2016 | 06/14/2016 | 153 | 0 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 |  | 6/6/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 687718 | 01005 | 10.64 |  |  | Solar |  | 05_07_91W48 | 04/29/2025 | 05/30/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUDSON | 177454 | 01749 | 7.6 |  |  | Solar |  | 05_07_8W1 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 277 | 0 | 277 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 |  | 2/14/2018 | N | EXP | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 178772 | 02190 | 300 |  |  | Solar |  | 05_05_3422W3 | 08/16/2012 | 08/16/2012 | 5 | 1 | 4 | 08/24/2012 | 08/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 |  | 11/27/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 1/3/2013 | 1/3/2013 | 1/17/2013 | Connected |  | N
National Grid | ATTLEBORO | 177092 | 02703 | 40.25 |  |  | Solar |  | 05_09_604W3 | 01/19/2017 | 01/19/2017 | 0 | 0 | 0 | 01/19/2017 | 01/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2017 |  | 1/24/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | LEOMINSTER | 355955 | 01453 | 7.83 |  |  | Solar |  | 05_05_318W3 | 05/03/2021 | 05/06/2021 | 3 | 1 | 2 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N
National Grid | PALMER | 319549 | 01069 | 7.6 |  |  | Solar |  | 05_07_99W32 | 11/17/2020 | 11/23/2020 | 3 | 0 | 3 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 651200 | 02151 | 5 |  |  | Solar |  | 05_05_9L4 | 11/01/2024 | 12/20/2024 | 15 | 12 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | BROCKTON | 579807 | 02302 | 6.38 |  |  | Solar |  | 05_01_207W4 | 02/13/2024 | 03/27/2024 | 30 | 27 | 3 | 03/28/2024 | 03/28/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | BRIDGEWATER | 555915 | 02333 | 10 |  |  | Solar |  | 05_09_503L1 | 10/23/2023 | 10/24/2023 | 1 | 0 | 1 | 10/25/2023 | 10/25/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 10/23/2023 | 1/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | PLAINVILLE | 177358 | 02762 | 7.6 |  |  | Solar |  | 05_12_16W4 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/10/2017 | 10/10/2017 | 8/31/2017 | Connected |  | N
National Grid | BARRE | 536401 | 01005 | 100 |  |  | Solar |  | 05_07_91W49 | 07/18/2023 | 09/06/2023 | 35 | 27 | 8 |  |  | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 07/18/2023 | 8/27/2026 | Y | STD | 280 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BERLIN | 198035 | 01503 | 9 |  |  | Solar |  | 05_07_8W1 | 10/16/2018 | 12/27/2018 | 10 | 10 | 0 | 12/28/2018 | 12/28/2018 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 10/16/2018 | 10/22/2019 | Y | EXP | 279 | 04/24/2019 | 05/31/2019 | 37 | 0 | 37 |  |  | 8/1/2019 | Connected |  | N
National Grid | WEYMOUTH | 178791 | 02190 | 86.6 |  |  | Solar |  | 05_05_3422W3 | 02/03/2017 | 02/03/2017 | 2 | 2 | 0 | 02/07/2017 | 02/07/2017 | 199 | 66 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2017 |  | 2/8/2018 | N | EXP | 254 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 177323 | 02703 | 7.6 |  |  | Solar |  | 05_09_604W3 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/26/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/6/2016 | 10/6/2016 | 10/6/2016 | Connected |  | N
National Grid | LEOMINSTER | 366496 | 01453 | 8.7 |  |  | Solar |  | 05_05_318W3 | 09/07/2021 | 09/13/2021 | 4 | 0 | 4 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 09/07/2021 | 12/21/2023 | Y | EXP | 365 | 04/13/2022 | 12/21/2022 | 253 | 0 | 253 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 329977 | 01069 | 10 |  |  | Solar |  | 05_07_99W32 | 12/07/2020 | 12/10/2020 | 2 | 0 | 2 | 12/11/2020 | 12/11/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | REVERE | 652294 | 02151 | 5.76 |  |  | Solar |  | 05_05_9L4 | 11/06/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 37 | 22 | 15 | 01/27/2025 | 02/11/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/28/2026 | N | EXP | 365 | 03/12/2025 | 04/14/2025 | 34 | 0 | 34 |  |  | 4/21/2025 | Connected |  | N
National Grid | BROCKTON | 587583 | 02302 | 7.25 |  |  | Solar |  | 05_01_207W4 | 02/13/2024 | 03/06/2024 | 15 | 12 | 3 | 03/07/2024 | 03/07/2024 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 | 02/13/2024 | 4/4/2025 | Y | EXP | 365 | 06/28/2024 | 08/07/2024 | 41 | 0 | 41 |  |  | 8/16/2024 | Connected |  | N
National Grid | BROCKTON | 579915 | 02302 | 7.6 |  |  | Solar |  | 05_09_503L1 | 01/18/2024 | 01/23/2024 | 3 | 0 | 3 | 01/24/2024 | 01/24/2024 | 71 | 56 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 189147 | 02035 | 10 |  |  | Solar |  | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 6 | 1 | 5 | 09/14/2018 | 09/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 10/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2018 | Connected |  | N
National Grid | NEW BRAINTREE | 643766 | 01531 | 15.2 |  |  | Solar |  | 05_07_91W49 | 12/03/2024 | 12/05/2024 | 3 | 2 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BERLIN | 428516 | 01503 | 7.6 |  |  | Solar |  | 05_07_8W1 | 05/05/2022 | 05/26/2022 | 15 | 14 | 1 | 05/27/2022 | 05/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 178786 | 02190 | 19.4 |  |  | Solar |  | 05_05_3422W3 | 04/27/2015 | 04/27/2015 | 0 | 0 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2015 |  | 9/30/2015 | N | EXP | 153 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 7/1/2016 | Connected |  | N
National Grid | ATTLEBORO | 177316 | 02703 | 1000 |  |  | Solar |  | 05_09_604W3 | 02/10/2017 | 02/15/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 02/10/2017 | 12/21/2024 | Y | STD | 1050 | 02/08/2023 | 03/07/2023 | 28 | 0 | 28 |  |  | 12/23/2024 | Connected |  | N
National Grid | LEOMINSTER | 372931 | 01453 | 7.6 |  |  | Solar |  | 05_05_318W3 | 08/31/2021 | 09/08/2021 | 4 | 4 | 0 | 09/09/2021 | 09/09/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 5/14/2023 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 341855 | 01069 | 7.6 |  |  | Solar |  | 05_07_99W32 | 02/11/2021 | 02/17/2021 | 2 | 0 | 2 | 02/18/2021 | 02/18/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2021 | Connected |  | N
National Grid | REVERE | 655290 | 02151 | 10 |  |  | Solar |  | 05_05_9L4 | 11/19/2024 | 12/11/2024 | 5 | 3 | 2 | 12/12/2024 | 12/12/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/19/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BROCKTON | 590751 | 02301 | 10 |  |  | Solar |  | 05_01_207W4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/22/2024 | 3/23/2025 | Y | EXP | 365 | 05/18/2024 | 05/30/2024 | 13 | 0 | 13 |  |  | 6/21/2024 | Connected |  | N
National Grid | BROCKTON | 588858 | 02302 | 7.6 |  |  | Solar |  | 05_09_503L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 03/18/2024 | 4/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 189054 | 02762 | 10 |  |  | Solar |  | 05_12_16W4 | 06/26/2018 | 06/26/2018 | 3 | 1 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/26/2018 | 6/26/2020 | Y | EXP | 650 | 05/07/2020 | 05/18/2020 | 9 | 0 | 9 |  |  | 6/3/2020 | Connected |  | N
National Grid | NORTH BROOKFIELD | 651307 | 01535 | 5.76 |  |  | Solar |  | 05_07_91W49 | 11/12/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 456387 | 01740 | 7.6 |  |  | Solar |  | 05_07_8W1 | 11/28/2022 | 12/01/2022 | 3 | 2 | 1 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 | 11/28/2022 | 6/10/2024 | Y | EXP | 365 | 05/12/2023 | 06/09/2023 | 29 | 0 | 29 |  |  | 6/23/2023 | Connected |  | N
National Grid | WEYMOUTH | 212066 | 02190 | 17.6 |  |  | Solar |  | 05_05_3422W3 | 03/04/2019 | 03/14/2019 | 7 | 7 | 0 | 03/15/2019 | 03/15/2019 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  | 4/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 177315 | 02703 | 1800 |  |  | Solar |  | 05_09_604W3 | 02/10/2017 | 03/10/2017 | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 03/24/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 | 02/10/2017 | 12/9/2024 | Y | STD | 1050 | 09/13/2024 | 09/12/2024 | 0 | 0 | 0 |  |  | 12/23/2024 | Connected |  | N
National Grid | LEOMINSTER | 384559 | 01453 | 7.6 |  |  | Solar |  | 05_05_318W3 | 09/27/2021 | 09/28/2021 | 1 | 0 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2022 | Connected |  | N
National Grid | PALMER | 416071 | 01069 | 15.2 |  |  | Solar |  | 05_07_99W32 | 03/07/2022 | 03/08/2022 | 1 | 0 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 5/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2023 | Connected |  | N
National Grid | REVERE | 671376 | 02151 | 18.85 |  |  | Solar |  | 05_05_9L4 | 02/20/2025 | 04/23/2025 | 43 | 25 | 18 | 04/24/2025 | 04/24/2025 | 102 | 25 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 598939 | 02302 | 5 |  |  | Solar |  | 05_01_207W4 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 624145 | 02190 | 4.55 |  |  | Solar |  | 05_09_503L1 | 07/24/2024 | 09/20/2024 | 3 | 1 | 2 | 09/23/2024 | 09/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 07/24/2024 | 11/11/2025 | Y | EXP | 365 | 06/10/2025 | 08/04/2025 | 56 | 0 | 56 |  |  | 8/21/2025 | Connected |  | N
National Grid | PLAINVILLE | 195285 | 02762 | 10 |  |  | Solar |  | 05_12_16W4 | 10/16/2018 | 11/15/2018 | 14 | 9 | 5 | 11/16/2018 | 11/16/2018 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 10/16/2018 | 12/27/2019 | Y | EXP | 365 | 07/09/2019 | 07/15/2019 | 6 | 0 | 6 |  |  | 8/20/2019 | Connected |  | N
National Grid | BARRE | 656536 | 01005 | 6.96 |  |  | Solar |  | 05_07_91W49 | 11/26/2024 | 03/10/2025 | 29 | 25 | 4 | 03/11/2025 | 03/11/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BERLIN | 520468 | 01503 | 0 |  |  | Solar |  | 05_07_8W1 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | WEYMOUTH | 259189 | 02190 | 12 |  |  | Solar |  | 05_05_3422W3 | 10/28/2019 | 11/04/2019 | 4 | 0 | 4 | 11/05/2019 | 11/05/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 |  | 10/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2020 | Connected |  | N
National Grid | ATTLEBORO | 177314 | 02703 | 1650 |  |  | Solar |  | 05_09_604W3 | 02/10/2017 | 02/15/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/10/2017 | 12/8/2023 | Y | STD | 803 | 08/04/2022 | 01/31/2023 | 181 | 0 | 181 | 2/1/2023 | 10/26/2023 | 11/21/2023 | Connected |  | N
National Grid | LEOMINSTER | 388680 | 01453 | 9.86 |  |  | Solar |  | 05_05_318W3 | 10/14/2021 | 10/19/2021 | 3 | 3 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 1/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | PALMER | 525126 | 01069 | 7.6 |  |  | Solar |  | 05_07_99W32 | 06/27/2023 | 08/03/2023 | 27 | 25 | 2 | 08/04/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 9/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2023 | Connected |  | N
National Grid | REVERE | 673851 | 02151 | 3.19 |  |  | Solar |  | 05_05_9L4 | 02/24/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 02/24/2025 | 7/24/2026 | Y | EXP | 365 | 08/02/2025 | 08/14/2025 | 13 | 0 | 13 |  |  | 9/4/2025 | Connected |  | N
National Grid | BROCKTON | 651575 | 02302 | 5.76 |  |  | Solar |  | 05_01_207W4 | 11/04/2024 | 11/26/2024 | 5 | 0 | 5 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 632606 | 02190 | 11.5 |  |  | Solar |  | 05_09_503L1 | 08/27/2024 | 08/28/2024 | 1 | 0 | 1 | 08/29/2024 | 08/29/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/27/2024 | 9/26/2025 | Y | EXP | 365 | 10/29/2024 | 11/07/2024 | 10 | 0 | 10 |  |  | 5/1/2025 | Connected |  | N
National Grid | FOXBOROUGH | 195873 | 02035 | 10 |  |  | Solar |  | 05_12_16W4 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 708868 | 01005 | 0 |  |  | Battery Add-On |  | 05_07_91W49 | 07/31/2025 | 08/04/2025 | 2 | 0 | 2 | 08/05/2025 | 08/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 07/31/2025 | 9/16/2026 | Y | EXP | 365 | 10/31/2025 | 11/28/2025 | 29 | 0 | 29 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 579417 | 01740 | 16 |  |  | Solar |  | 05_07_8W1 | 12/26/2023 | 12/28/2023 | 2 | 0 | 2 | 12/29/2023 | 12/29/2023 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 291839 | 02190 | 10 |  |  | Solar |  | 05_05_3422W3 | 05/14/2020 | 06/02/2020 | 11 | 7 | 4 | 06/03/2020 | 06/03/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | ATTLEBORO | 177354 | 02703 | 499 |  |  | Solar |  | 05_09_604W3 | 02/15/2017 | 04/26/2017 | 47 | 47 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2017 | 04/26/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 |  | 2/26/2021 | N | STD | 995 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 418047 | 01453 | 15.2 |  |  | Solar |  | 05_05_318W3 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 559009 | 01069 | 15.2 |  |  | Solar |  | 05_07_99W32 | 09/28/2023 | 10/03/2023 | 3 | 0 | 3 | 10/04/2023 | 10/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | REVERE | 669674 | 02151 | 0 |  |  | Other |  | 05_05_9L5 | 07/22/2025 | 08/26/2025 | 24 | 13 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 11/01/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 647261 | 02301 | 10 |  |  | Solar |  | 05_09_503L1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N
National Grid | WEYMOUTH | 203604 | 02190 | 3.8 |  |  | Solar |  | 05_12_16W4 | 01/24/2019 | 01/30/2019 | 4 | 4 | 0 | 01/31/2019 | 01/31/2019 | 228 | 0 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 714619 | 02035 | 7.6 |  |  | Solar |  | 05_07_91W49 | 08/26/2025 | 09/16/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BARRE | 642780 | 01005 | 7.6 |  |  | Solar |  | 05_07_8W1 | 09/25/2024 | 10/17/2024 | 1 | 0 | 1 | 10/18/2024 | 10/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/25/2024 | 12/20/2025 | Y | EXP | 365 | 05/30/2025 | 08/19/2025 | 82 | 0 | 82 |  |  | 8/22/2025 | Connected |  | N
National Grid | BOLTON | 347002 | 01740 | 999 |  |  | Solar |  | 05_05_3422W3 | 04/29/2021 | 05/16/2021 | 11 | 3 | 8 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 177428 | 02190 | 997 |  |  | Solar |  | 05_09_604W3 | 02/28/2017 | 04/07/2017 | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2017 | 04/26/2017 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 02/28/2017 | 5/3/2023 | Y | STD | 541 | 11/18/2022 | 04/18/2023 | 153 | 43 | 110 |  |  | 4/26/2023 | Connected |  | Y
National Grid | ATTLEBORO | 429894 | 02703 | 15.2 |  |  | Solar |  | 05_05_318W3 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | LEOMINSTER | 552899 | 01453 | 7.6 |  |  | Solar |  | 05_07_99W32 | 09/01/2023 | 09/07/2023 | 3 | 0 | 3 | 09/08/2023 | 09/08/2023 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 721787 | 01069 | 3.8 |  |  | Solar |  | 05_05_9L5 | 09/29/2025 | 10/03/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 653516 | 02151 | 10.075 |  |  | Solar |  | 05_01_207W4 | 11/20/2024 | 03/04/2025 | 13 | 9 | 4 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 11/20/2024 | 4/14/2026 | Y | EXP | 365 | 09/20/2025 | 09/23/2025 | 4 | 0 | 4 |  |  | 10/8/2025 | Connected |  | N
National Grid | BROCKTON | 685358 | 02301 | 4980 |  |  | Solar |  | 05_09_503L1 | 06/03/2025 | 07/09/2025 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 223563 | 02190 | 106.6 |  |  | Solar |  | 05_12_16W4 | 04/29/2019 | 05/16/2019 | 12 | 7 | 5 | 05/17/2019 | 05/17/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2019 | 04/29/2019 | 8/6/2021 | Y | EXP | 720 | 11/04/2020 | 04/07/2021 | 154 | 0 | 154 |  |  | 8/5/2021 | Connected |  | N
National Grid | FOXBOROUGH | 731422 | 02035 | 8.74 |  |  | Solar |  | 05_07_91W49 | 11/04/2025 | 11/05/2025 | 6 | 3 | 3 | 11/19/2025 | 11/19/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | NEW BRAINTREE | 657360 | 01531 | 3.8 |  |  | Solar |  | 05_07_8W1 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | BOLTON | 380603 | 01740 | 9.6 |  |  | Solar |  | 05_05_3422W3 | 09/22/2021 | 09/23/2021 | 2 | 1 | 1 | 09/24/2021 | 09/24/2021 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 11/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2021 | Connected |  | N
National Grid | WEYMOUTH | 177436 | 02190 | 10 |  |  | Solar |  | 05_09_604W3 | 06/30/2016 | 06/30/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/30/2016 | 7/6/2017 | Y | EXP | 353 | 10/12/2016 | 10/12/2016 | 0 | 0 | 0 | 11/21/2016 | 11/21/2016 | 11/21/2016 | Connected |  | N
National Grid | ATTLEBORO | 434493 | 02703 | 15.2 |  |  | Solar |  | 05_05_318W3 | 06/01/2022 | 06/03/2022 | 2 | 0 | 2 | 06/06/2022 | 06/06/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2023 | Connected |  | N
National Grid | LEOMINSTER | 552140 | 01453 | 0 |  |  | Solar |  | 05_07_99W32 | 08/30/2023 | 10/03/2023 | 24 | 23 | 1 | 10/04/2023 | 10/04/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | PALMER | 733030 | 01069 | 25.38 |  |  | Solar |  | 05_05_9L5 | 11/11/2025 | 11/12/2025 | 1 | 0 | 1 | 11/13/2025 | 11/13/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 684320 | 02151 | 7.6 |  |  | Solar |  | 05_01_207W4 | 04/10/2025 | 05/13/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 9/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | BROCKTON | 680003 | 02301 | 4980 |  |  | Solar |  | 05_09_503L2 | 05/06/2025 | 06/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEYMOUTH | 257961 | 02190 | 5 |  |  | Solar |  | 05_12_16W4 | 11/13/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2019 | 11/13/2019 | 11/13/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/22/2020 | Connected |  | N
National Grid | PLAINVILLE | 738165 | 02762 | 19.38 |  |  | Solar |  | 05_07_91W49 | 12/04/2025 |  | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NEW BRAINTREE | 677102 | 01531 | 40 |  |  | Solar |  | 05_07_910W25 | 03/24/2025 | 03/27/2025 | 3 | 0 | 3 | 03/28/2025 | 03/28/2025 | 24 | 6 | 18 | 05/12/2025 | 05/20/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/20/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/17/2026 | N | EXP | 365 | 07/30/2025 | 09/30/2025 | 63 | 0 | 63 |  |  |  | Completion Documents |  | Y
National Grid | BOLTON | 396690 | 01740 | 15.2 |  |  | Solar |  | 05_05_3422W3 | 11/19/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2021 |  | 1/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | WEYMOUTH | 177724 | 02190 | 4800 |  |  | Solar |  | 05_09_604W3 | 10/04/2017 | 10/18/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2017 | 11/08/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 | 6/14/2018 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 462578 | 02703 | 60 |  |  | Solar |  | 05_05_318W3 | 10/06/2022 | 11/07/2022 | 22 | 12 | 10 | 11/08/2022 | 11/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 10/06/2022 | 6/25/2024 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | LEOMINSTER | 568632 | 01453 | 7.6 |  |  | Solar |  | 05_07_99W32 | 11/03/2023 | 02/01/2024 | 59 | 55 | 4 | 02/02/2024 | 02/02/2024 | 21 | 10 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | PALMER | 174239 | 01069 | 500 |  |  | Solar |  | 05_05_9L5 | 02/17/2012 | 02/17/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 645834 | 02151 | 4950 |  |  | Other |  | 05_01_207W6 | 01/29/2025 | 04/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 696490 | 02301 | 24.7 |  |  | Solar |  | 05_09_503L2 | 06/05/2025 | 06/25/2025 | 12 | 9 | 3 | 06/26/2025 | 06/26/2025 | 56 | 41 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 263607 | 02190 | 10 |  |  | Solar |  | 05_12_16W4 | 11/12/2019 | 11/20/2019 | 6 | 6 | 0 | 11/21/2019 | 11/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 737460 | 02035 | 0 |  |  | Battery Add-On |  | 05_07_91W49 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEW BRAINTREE | 727211 | 01531 | 11.5 |  |  | Solar |  | 05_07_910W25 | 10/16/2025 | 10/24/2025 | 5 | 3 | 2 | 10/27/2025 | 10/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BERLIN | 400659 | 01503 | 19.72 |  |  | Solar |  | 05_05_3422W3 | 02/16/2022 | 03/09/2022 | 14 | 13 | 1 | 03/10/2022 | 03/10/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2022 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | WEYMOUTH | 178305 | 02190 | 1855 |  |  | Solar |  | 05_09_604W3 | 01/09/2018 | 03/09/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 478862 | 02703 | 16.82 |  |  | Solar |  | 05_05_318W3 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | N
National Grid | LEOMINSTER | 577766 | 01453 | 0 |  |  | Other |  | 05_07_99W32 | 12/21/2023 | 02/21/2024 | 41 | 32 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 175148 | 01069 | 50 |  |  | Solar |  | 05_05_9L5 | 10/25/2013 | 10/25/2013 | 6 | 0 | 6 | 11/04/2013 | 11/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2013 |  | 12/31/2013 | N | EXP | 48 |  |  | 0 | 0 | 0 | 1/24/2014 | 1/24/2014 | 1/24/2014 | Connected |  | N
National Grid | REVERE | 722918 | 02151 | 3.8 |  |  | Solar |  | 05_01_207W6 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 175162 | 02301 | 3000 |  |  | Solar |  | 05_09_503L2 | 07/18/2011 | 07/18/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2011 | 09/30/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2012 | 07/18/2011 | 12/31/2012 | Y | STD | 194 | 01/09/2014 | 10/07/2014 | 185 | 0 | 185 | 8/25/2014 | 8/25/2014 | 8/25/2014 | Connected |  | N
National Grid | WEYMOUTH | 341284 | 02190 | 5 |  |  | Solar |  | 05_12_16W4 | 02/12/2021 | 02/17/2021 | 1 | 0 | 1 | 02/18/2021 | 02/18/2021 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 | 02/12/2021 | 5/3/2022 | Y | EXP | 365 | 06/16/2021 | 07/26/2021 | 41 | 0 | 41 |  |  | 1/13/2022 | Connected |  | N
National Grid | FOXBOROUGH | 736855 | 02035 | 7.6 |  |  | Solar |  | 05_07_91W49 | 12/22/2025 | 12/26/2025 | 0 | 0 | 0 | 01/07/2026 | 01/07/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEW BRAINTREE | 728034 | 01531 | 15 |  |  | Solar |  | 05_07_910W25 | 10/21/2025 | 10/27/2025 | 4 | 0 | 4 | 10/28/2025 | 10/28/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BERLIN | 405128 | 01503 | 100 |  |  | Solar |  | 05_05_3422W3 | 01/06/2022 |  | 207 | 200 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 193356 | 02190 | 4998 |  |  | Solar |  | 05_09_604W3 | 10/01/2018 | 10/15/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 12/20/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 482613 | 02771 | 0 |  |  | Solar |  | 05_05_318W3 | 12/13/2022 | 01/03/2023 | 13 | 8 | 5 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2024 | Connected |  | N
National Grid | LEOMINSTER | 606662 | 01453 | 23 |  |  | Solar |  | 05_07_99W32 | 04/25/2024 | 04/29/2024 | 2 | 0 | 2 | 04/30/2024 | 04/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 175210 | 01069 | 285 |  |  | Solar |  | 05_05_9L5 | 12/05/2012 | 12/05/2012 | 6 | 0 | 6 | 12/17/2012 | 12/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2013 | 12/05/2012 | 5/15/2013 | Y | EXP | 90 | 06/07/2013 | 07/31/2013 | 36 | 0 | 36 | 2/15/2013 | 2/15/2013 | 9/23/2013 | Connected |  | N
National Grid | REVERE | 729074 | 02151 | 7.6 |  |  | Solar |  | 05_01_207W6 | 11/04/2025 | 11/07/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROCKTON | 175738 | 02301 | 4280 |  |  | Solar |  | 05_09_503L2 | 08/11/2014 | 08/11/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2014 | 09/23/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 08/11/2014 | 12/31/2017 | Y | STD | 1005 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 346961 | 02190 | 7.6 |  |  | Solar |  | 05_12_16W4 | 03/30/2021 | 03/31/2021 | 0 | 0 | 0 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/16/2022 | Connected |  | N
National Grid |  | 740616 | 02093 | 13.68 |  |  | Solar |  | 05_07_91W49 | 12/16/2025 | 12/17/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEW BRAINTREE | 736328 | 01531 | 25.7 |  |  | Solar |  | 05_07_910W25 | 11/25/2025 | 12/08/2025 | 8 | 5 | 3 | 12/09/2025 | 12/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BERLIN | 433335 | 01503 | 300 |  |  | Solar |  | 05_05_3422W3 | 07/12/2022 | 12/22/2022 | 111 | 101 | 10 |  |  | 209 | 185 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 297453 | 02190 | 420 |  |  | Solar |  | 05_09_604W3 | 07/28/2020 | 09/28/2020 | 43 | 36 | 7 | 09/29/2020 | 09/29/2020 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 484982 | 02771 | 7.6 |  |  | Solar |  | 05_05_318W3 | 01/04/2023 | 01/05/2023 | 1 | 0 | 1 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | Y
National Grid | LEOMINSTER | 633824 | 01453 | 15.2 |  |  | Solar |  | 05_07_99W32 | 08/19/2024 | 09/09/2024 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | PALMER | 175554 | 01069 | 750 |  |  | Solar |  | 05_05_9L5 | 04/16/2014 | 04/16/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 06/17/2014 | 07/31/2014 | 30 | 0 | 30 | 04/25/2014 | 05/22/2014 | 19 | 0 | 19 |  | 07/31/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 10/27/2014 |  | 12/31/2014 | N | STD | 65 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 4/3/2015 | Connected |  | N
National Grid | REVERE | 175882 | 02151 | 984 |  |  | Solar |  | 05_01_207W6 | 05/21/2015 | 05/21/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2015 | 06/25/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2016 | 05/21/2015 | 10/31/2017 | Y | STD | 487 | 09/14/2017 | 01/05/2018 | 71 | 0 | 71 | 12/28/2017 | 12/28/2017 | 1/4/2018 | Connected |  | N
National Grid | BROCKTON | 175838 | 02301 | 2000 |  |  | Solar |  | 05_09_503L2 | 03/04/2015 | 03/04/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2015 | 04/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2015 | 03/04/2015 | 8/14/2017 | Y | STD | 671 | 03/08/2017 | 07/21/2017 | 94 | 0 | 94 | 8/18/2017 | 8/18/2017 | 8/18/2017 | Connected |  | N
National Grid | WEYMOUTH | 408870 | 02190 | 0 |  |  | Battery Add-On |  | 05_12_16W4 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/04/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 175743 | 02762 | 684 |  |  | Solar |  | 05_07_91W49 | 10/28/2014 | 10/28/2014 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2014 | 12/05/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/18/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW BRAINTREE | 738354 | 01531 | 5.76 |  |  | Solar |  | 05_07_910W25 | 12/05/2025 | 12/10/2025 | 3 | 0 | 3 | 12/11/2025 | 12/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BERLIN | 493072 | 01503 | 0 |  |  | Other |  | 05_05_3422W3 | 05/01/2023 | 06/29/2023 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 12/07/2023 | 110 | 96 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 385046 | 02190 | 2660 |  |  | Solar |  | 05_09_604W3 | 10/26/2021 | 01/11/2022 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/12/2022 | 11/21/2022 | 216 | 211 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 488595 | 02769 | 15.95 |  |  | Solar |  | 05_05_318W3 | 01/11/2023 | 01/27/2023 | 12 | 11 | 1 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 4/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2023 | Connected |  | N
National Grid | LEOMINSTER | 664153 | 01453 | 10.4 |  |  | Solar |  | 05_07_99W32 | 01/07/2025 | 01/16/2025 | 3 | 1 | 2 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/07/2025 | 3/10/2026 | Y | EXP | 365 | 05/10/2025 | 06/20/2025 | 42 | 0 | 42 |  |  | 6/28/2025 | Connected |  | Y
National Grid | MONSON | 175800 | 01057 | 990 |  |  | Solar |  | 05_05_9L5 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176471 | 02151 | 7.6 |  |  | Solar |  | 05_01_207W6 | 03/20/2016 | 03/20/2016 | 3 | 3 | 0 | 03/24/2016 | 03/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/20/2016 | 3/26/2017 | Y | EXP | 348 | 11/08/2016 | 11/29/2016 | 13 | 0 | 13 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | BROCKTON | 176457 | 02301 | 7.6 |  |  | Solar |  | 05_09_503L2 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 |  | 12/14/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 6/10/2016 | 6/10/2016 | 6/21/2016 | Connected |  | N
National Grid | PEMBROKE | 534356 | 02359 | 3.8 |  |  | Solar |  | 05_12_16W4 | 06/26/2023 | 06/28/2023 | 2 | 0 | 2 | 06/29/2023 | 06/29/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 176620 | 02035 | 10 |  |  | Solar |  | 05_07_91W49 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 07/18/2016 | 07/25/2016 | 5 | 0 | 5 | 1/23/2017 | 1/23/2017 | 3/9/2017 | Connected |  | N
National Grid | NEW BRAINTREE | 740489 | 01531 | 7.6 |  |  | Solar |  | 05_07_910W25 | 12/16/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BERLIN | 495226 | 01503 | 15.2 |  |  | Solar |  | 05_05_3422W3 | 01/26/2023 | 04/14/2023 | 55 | 55 | 0 | 04/18/2023 | 04/18/2023 | 78 | 57 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2024 | Connected |  | N
National Grid | WEYMOUTH | 454366 | 02190 | 10 |  |  | Solar |  | 05_09_604W3 | 09/06/2022 | 09/12/2022 | 4 | 1 | 3 | 09/13/2022 | 09/13/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 9/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2023 | Connected |  | N
National Grid | SEEKONK | 502268 | 02771 | 7.6 |  |  | Solar |  | 05_05_318W3 | 03/09/2023 | 03/31/2023 | 17 | 16 | 1 | 04/03/2023 | 04/03/2023 | 66 | 46 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | LEOMINSTER | 684372 | 01453 | 10 |  |  | Solar |  | 05_07_99W32 | 04/10/2025 | 05/12/2025 | 4 | 0 | 4 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | WALES | 175883 | 01081 | 150 |  |  | Solar |  | 05_05_9L5 | 05/22/2015 | 05/22/2015 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 06/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 | 05/22/2015 | 10/30/2016 | Y | STD | 334 | 08/11/2016 | 10/19/2016 | 47 | 0 | 47 | 10/31/2016 | 10/31/2016 | 11/8/2016 | Connected |  | N
National Grid | REVERE | 176557 | 02151 | 6 |  |  | Solar |  | 05_01_207W6 | 10/07/2015 | 10/07/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 10/13/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/31/2016 | 3/31/2016 | 4/6/2016 | Connected |  | N
National Grid | BROCKTON | 176601 | 02301 | 2000 |  |  | Solar |  | 05_09_503L2 | 12/29/2015 | 01/05/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/15/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 06/24/2016 | 09/27/2016 | 65 | 12 | 53 | 9/30/2016 | 12/29/2015 | 2/28/2019 | Y | STD | 881 | 09/19/2018 | 11/09/2018 | 51 | 0 | 51 |  |  | 2/28/2019 | Connected |  | N
National Grid | PEMBROKE | 535671 | 02359 | 5 |  |  | Solar |  | 05_12_16W4 | 01/02/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 309629 | 02762 | 7.6 |  |  | Solar |  | 05_07_91W49 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/29/2020 | 1/24/2022 | Y | EXP | 365 | 08/21/2021 | 08/30/2021 | 3 | 0 | 3 |  |  | 10/19/2021 | Connected |  | N
National Grid | NORTH BROOKFIELD | 175854 | 01535 | 10 |  |  | Solar |  | 05_07_910W25 | 08/03/2015 | 08/03/2015 | 3 | 3 | 0 | 08/07/2015 | 08/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/9/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 12/18/2015 | Connected |  | N
National Grid | BERLIN | 601533 | 01503 | 7.6 |  |  | Solar |  | 05_05_3422W3 | 04/04/2024 | 04/17/2024 | 9 | 5 | 4 | 04/18/2024 | 04/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2024 | Connected |  | N
National Grid | ABINGTON | 479620 | 02351 | 10 |  |  | Solar |  | 05_09_604W3 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 63 | 38 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 554413 | 02703 | 0 |  |  | Battery Add-On |  | 05_05_318W3 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 81 | 60 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | LEOMINSTER | 706368 | 01453 | 8.725 |  |  | Solar |  | 05_07_99W32 | 07/22/2025 | 07/25/2025 | 3 | 0 | 3 | 07/28/2025 | 07/28/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | MONSON | 177549 | 01057 | 7.6 |  |  | Solar |  | 05_05_9L5 | 05/15/2017 | 05/15/2017 | 6 | 5 | 1 | 05/24/2017 | 05/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2017 |  | 5/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | REVERE | 176657 | 02151 | 3.8 |  |  | Solar |  | 05_01_207W6 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 4/26/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176850 | 02301 | 972 |  |  | Solar |  | 05_09_503L2 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/11/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 550822 | 02359 | 3.8 |  |  | Solar |  | 05_12_16W4 | 08/28/2023 | 09/01/2023 | 4 | 2 | 2 | 09/05/2023 | 09/05/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 311832 | 02762 | 10.32 |  |  | Solar |  | 05_07_91W49 | 10/23/2020 | 10/26/2020 | 0 | 0 | 0 | 10/27/2020 | 10/27/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/23/2020 | 7/26/2023 | Y | EXP | 900 | 12/18/2020 | 01/26/2021 | 39 | 0 | 39 |  |  |  | Withdrawn |  | Y
National Grid | NEW BRAINTREE | 176147 | 01531 | 2400 |  |  | Solar |  | 05_07_910W25 | 08/24/2015 | 08/24/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/28/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 03/23/2016 | 03/23/2016 | 0 | 0 | 0 | 5/11/2016 | 08/24/2015 | 12/18/2017 | Y | STD | 586 | 08/03/2017 | 12/18/2017 | 88 | 0 | 88 | 12/5/2017 | 12/5/2017 | 12/18/2017 | Connected |  | N
National Grid | BERLIN | 637353 | 01503 | 11.5 |  |  | Solar |  | 05_05_3422W3 | 09/03/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | WEYMOUTH | 480402 | 02190 | 7.6 |  |  | Solar |  | 05_09_604W3 | 11/28/2022 | 12/05/2022 | 6 | 5 | 1 | 12/06/2022 | 12/06/2022 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 566220 | 02703 | 7.6 |  |  | Solar |  | 05_05_318W3 | 10/25/2023 | 10/26/2023 | 1 | 0 | 1 | 10/27/2023 | 10/27/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | LEOMINSTER | 456001 | 01453 | 200 |  |  | Solar |  | 05_07_99W61 | 09/02/2022 | 09/19/2022 | 10 | 0 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  | 5/26/2026 | N | STD | 147 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MONSON | 177769 | 01057 | 10 |  |  | Solar |  | 05_05_9L5 | 10/09/2017 | 10/09/2017 | 14 | 14 | 0 | 10/31/2017 | 10/31/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/15/2018 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 176656 | 02151 | 10 |  |  | Solar |  | 05_01_207W6 | 04/20/2016 | 04/20/2016 | 1 | 1 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 | 04/20/2016 | 4/25/2017 | Y | EXP | 357 | 08/30/2016 | 09/09/2016 | 7 | 0 | 7 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | BROCKTON | 178214 | 02301 | 4980 |  |  | Solar |  | 05_09_503L2 | 03/23/2018 | 03/23/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2018 | 05/04/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 581875 | 02359 | 100 |  |  | Solar |  | 05_12_16W4 | 01/19/2024 | 02/08/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 313208 | 02762 | 7.6 |  |  | Solar |  | 05_07_91W49 | 10/01/2020 | 10/06/2020 | 2 | 0 | 2 | 10/07/2020 | 10/07/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 | 10/01/2020 | 5/20/2024 | Y | EXP | 365 | 01/08/2021 | 01/21/2021 | 13 | 0 | 13 |  |  | 8/7/2023 | Connected |  | N
National Grid | NORTH BROOKFIELD | 178143 | 01535 | 4998 |  |  | Solar |  | 05_07_910W25 | 03/23/2018 | 03/30/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/25/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 | 03/23/2018 | 6/2/2020 | Y | STD | 635 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 644099 | 01503 | 7.6 |  |  | Solar |  | 05_05_3422W3 | 10/01/2024 | 11/12/2024 | 14 | 12 | 2 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 492334 | 02351 | 2000 |  |  | Solar |  | 05_09_604W3 | 03/08/2023 | 03/22/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2023 | 05/16/2023 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 612829 | 02703 | 10 |  |  | Solar |  | 05_05_318W3 | 05/22/2024 | 05/24/2024 | 3 | 2 | 1 | 05/28/2024 | 05/28/2024 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | LEOMINSTER | 689730 | 01453 | 6.96 |  |  | Solar |  | 05_07_99W61 | 05/05/2025 | 07/11/2025 | 3 | 0 | 3 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MONSON | 177791 | 01057 | 612 |  |  | Solar |  | 05_05_9L5 | 08/02/2017 | 08/02/2017 | 126 | 126 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/8/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176795 | 02151 | 10 |  |  | Solar |  | 05_01_207W6 | 02/25/2016 | 02/25/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2016 | 02/25/2016 | 3/1/2017 | Y | EXP | 328 | 07/18/2016 | 08/01/2016 | 10 | 0 | 10 | 4/7/2016 | 4/7/2016 | 8/3/2016 | Connected |  | N
National Grid | BROCKTON | 184321 | 02301 | 11.4 |  |  | Solar |  | 05_09_503L2 | 07/15/2018 | 08/09/2018 | 18 | 0 | 18 | 08/10/2018 | 08/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 600326 | 02359 | 6 |  |  | Solar |  | 05_12_16W4 | 04/05/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 377483 | 02093 | 10 |  |  | Solar |  | 05_07_91W49 | 08/26/2021 | 08/31/2021 | 4 | 1 | 3 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 | 08/26/2021 | 5/5/2023 | Y | EXP | 365 | 03/09/2022 | 03/31/2022 | 23 | 0 | 23 |  |  | 11/22/2022 | Connected |  | Y
National Grid | BARRE | 178167 | 01005 | 11.4 |  |  | Solar |  | 05_07_910W25 | 02/14/2018 | 02/14/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 2/20/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | BOLTON | 651087 | 01740 | 5.76 |  |  | Solar |  | 05_05_3422W3 | 11/12/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/12/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | Y
National Grid | WEYMOUTH | 669890 | 02190 | 5.76 |  |  | Solar |  | 05_09_604W3 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | REHOBOTH | 637222 | 02769 | 6.08 |  |  | Solar |  | 05_05_318W3 | 09/03/2024 | 09/16/2024 | 3 | 1 | 2 | 09/17/2024 | 09/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 10/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | LEOMINSTER | 707767 | 01453 | 13.8 |  |  | Solar |  | 05_07_99W61 | 07/30/2025 | 08/06/2025 | 4 | 0 | 4 | 08/07/2025 | 08/07/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | MONSON | 177821 | 01057 | 300 |  |  | Natural Gas |  | 05_05_9L5 | 06/05/2017 | 06/05/2017 | 6 | 6 | 0 | 06/15/2017 | 06/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2017 |  | 2/28/2018 | N | EXP | 233 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 3/29/2018 | Connected |  | N
National Grid | REVERE | 177137 | 02151 | 7.6 |  |  | Solar |  | 05_01_207W6 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 | 05/27/2016 | 6/5/2017 | Y | EXP | 356 | 11/01/2016 | 11/14/2016 | 8 | 0 | 8 | 12/7/2016 | 12/7/2016 | 12/12/2016 | Connected |  | N
National Grid | BROCKTON | 185765 | 02301 | 4990 |  |  | Solar |  | 05_09_503L2 | 05/25/2018 | 05/25/2018 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 612100 | 02359 | 7.6 |  |  | Solar |  | 05_12_16W4 | 05/21/2024 | 06/03/2024 | 2 | 0 | 2 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | FOXBOROUGH | 438769 | 02035 | 0 |  |  | Solar |  | 05_07_91W49 | 06/20/2022 | 06/21/2022 | 1 | 0 | 1 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 06/20/2022 | 5/3/2024 | Y | EXP | 365 | 04/13/2023 | 05/03/2023 | 21 | 0 | 21 |  |  | 5/24/2023 | Connected |  | N
National Grid | NEW BRAINTREE | 178285 | 01531 | 3200 |  |  | Solar |  | 05_07_910W25 | 03/29/2018 | 03/29/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 04/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 | 03/29/2018 | 12/30/2022 | Y | STD | 532 | 12/15/2021 | 07/25/2022 | 223 | 141 | 82 |  |  | 12/28/2022 | Connected |  | N
National Grid | BERLIN | 660959 | 01503 | 10 |  |  | Solar |  | 05_05_3422W3 | 12/16/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/16/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WEYMOUTH | 670324 | 02190 | 17.225 |  |  | Solar |  | 05_09_604W3 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 640073 | 02771 | 0 |  |  | Battery Add-On |  | 05_05_318W3 | 09/13/2024 | 09/17/2024 | 2 | 0 | 2 | 09/18/2024 | 09/18/2024 | 14 | 6 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 708790 | 01453 | 240 |  |  | Solar |  | 05_07_99W61 | 08/05/2025 | 09/16/2025 | 28 | 18 | 10 |  |  | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MONSON | 178187 | 01057 | 15.2 |  |  | Solar |  | 05_05_9L5 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/21/2019 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | REVERE | 177219 | 02151 | 36 |  |  | Solar |  | 05_01_207W6 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2016 |  | 1/21/2018 | N | EXP | 486 |  |  | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | BROCKTON | 185764 | 02301 | 4990 |  |  | Solar |  | 05_09_503L2 | 06/18/2018 | 06/18/2018 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/23/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 613303 | 02359 | 34.6 |  |  | Solar |  | 05_12_16W4 | 06/05/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | FOXBOROUGH | 487499 | 02035 | 15.2 |  |  | Solar |  | 05_07_91W49 | 12/27/2022 | 01/03/2023 | 4 | 2 | 2 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 5/23/2024 | N | EXP | 390 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW BRAINTREE | 249662 | 01531 | 3200 |  |  | Solar |  | 05_07_910W25 | 09/05/2019 | 11/19/2019 | 48 | 46 | 2 |  |  | 2 | 2 | 0 |  |  | 0 | 0 | 0 | 11/20/2019 | 05/07/2020 | 116 | 94 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 669146 | 01503 | 10 |  |  | Solar |  | 05_05_3422W3 | 01/31/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | WEYMOUTH | 694159 | 02190 | 20 |  |  | Solar |  | 05_09_604W3 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 | 05/29/2025 | 7/11/2026 | Y | EXP | 365 | 11/14/2025 |  | 49 | 0 | 49 |  |  | 12/27/2025 | Connected |  | N
National Grid | SEEKONK | 682747 | 02771 | 15.2 |  |  | Solar |  | 05_05_318W3 | 04/04/2025 | 04/10/2025 | 4 | 0 | 4 | 04/11/2025 | 04/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 04/04/2025 | 5/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 177379 | 01453 | 1000 |  |  | Solar |  | 05_07_99W61 | 11/23/2016 | 11/23/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/3/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 178321 | 01057 | 612 |  |  | Solar |  | 05_05_9L5 | 08/02/2017 | 08/02/2017 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/29/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178182 | 02151 | 3.8 |  |  | Solar |  | 05_01_207W6 | 04/13/2018 | 04/13/2018 | 7 | 0 | 7 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2018 |  | 4/21/2019 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 190886 | 02301 | 3.8 |  |  | Solar |  | 05_09_503L2 | 07/17/2018 | 12/20/2018 | 8 | 0 | 8 | 10/04/2018 | 10/04/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 643354 | 02359 | 10 |  |  | Solar |  | 05_12_16W4 | 09/27/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 486521 | 02762 | 7.6 |  |  | Solar |  | 05_07_91W49 | 01/03/2023 | 01/27/2023 | 17 | 15 | 2 | 01/30/2023 | 01/30/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | NORTH BROOKFIELD | 303299 | 01535 | 0 |  |  | Solar |  | 05_07_910W25 | 07/27/2020 | 07/28/2020 | 0 | 0 | 0 | 07/29/2020 | 07/29/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 8/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 710748 | 01740 | 20 |  |  | Solar |  | 05_05_3422W3 | 08/21/2025 | 08/22/2025 | 1 | 0 | 1 | 08/25/2025 | 08/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | ROCKLAND | 699206 | 02370 | 11.4 |  |  | Solar |  | 05_09_604W3 | 06/19/2025 | 07/08/2025 | 13 | 12 | 1 | 07/31/2025 | 07/31/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 685270 | 02771 | 15.2 |  |  | Solar |  | 05_05_318W3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 196387 | 01453 | 100 |  |  | Solar |  | 05_07_99W61 | 09/19/2018 | 10/05/2018 | 7 | 0 | 7 | 10/08/2018 | 10/08/2018 | 25 | 4 | 21 | 11/29/2018 | 12/19/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 12/19/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 1/24/2019 | 09/19/2018 | 6/1/2020 | Y | EXP | 494 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 292469 | 01057 | 0 |  |  | Solar |  | 05_05_9L5 | 05/20/2020 | 12/23/2021 | 2 | 0 | 2 | 05/27/2020 | 05/27/2020 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 | 05/20/2020 | 10/12/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178446 | 02151 | 7.6 |  |  | Solar |  | 05_01_207W6 | 04/03/2018 | 04/03/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2018 |  | 4/9/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2018 | Connected |  | N
National Grid | BROCKTON | 194853 | 02301 | 10 |  |  | Solar |  | 05_09_503L2 | 09/16/2018 | 10/29/2018 | 13 | 13 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 643781 | 02359 | 10 |  |  | Solar |  | 05_12_16W4 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/01/2024 | 1/6/2026 | Y | EXP | 365 | 07/30/2025 | 10/29/2025 | 92 | 0 | 92 |  |  | 12/3/2025 | Connected |  | N
National Grid | PLAINVILLE | 489910 | 02762 | 10 |  |  | Solar |  | 05_07_91W49 | 04/25/2023 | 05/22/2023 | 20 | 19 | 1 | 05/23/2023 | 05/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 04/25/2023 | 8/1/2025 | Y | EXP | 365 | 10/18/2023 | 11/03/2023 | 17 | 0 | 17 |  |  | 10/15/2024 | Connected |  | N
National Grid | NEW BRAINTREE | 365824 | 01531 | 7.6 |  |  | Solar |  | 05_07_910W25 | 06/24/2021 | 01/06/2022 | 2 | 0 | 2 | 06/29/2021 | 06/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  | 7/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2022 | Connected |  | N
National Grid | BERLIN | 686036 | 01503 | 7.6 |  |  | Solar |  | 05_05_3422W4 | 04/18/2025 | 05/06/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 | 04/18/2025 | 7/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | ROCKLAND | 334194 | 02370 | 0 |  |  | Other |  | 05_09_604W4 | 04/06/2021 | 04/30/2021 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 723459 | 02703 | 3.8 |  |  | Solar |  | 05_05_318W3 | 10/02/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | LEOMINSTER | 218741 | 01453 | 7.6 |  |  | Solar |  | 05_07_99W61 | 04/10/2019 | 04/22/2019 | 7 | 0 | 7 | 04/23/2019 | 04/23/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 372331 | 01057 | 11.02 |  |  | Solar |  | 05_05_9L5 | 08/04/2021 | 08/09/2021 | 10 | 6 | 4 | 08/19/2021 | 08/19/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 10/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 187836 | 02151 | 9.84 |  |  | Solar |  | 05_01_207W6 | 06/13/2018 | 06/12/2018 | 10 | 5 | 5 | 06/28/2018 | 06/28/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 | 06/13/2018 | 8/30/2019 | Y | EXP | 394 | 03/09/2019 | 03/08/2019 | 0 | 0 | 0 |  |  | 8/10/2019 | Connected |  | N
National Grid | BROCKTON | 204943 | 02301 | 7.6 |  |  | Solar |  | 05_09_503L2 | 02/06/2019 | 02/15/2019 | 6 | 0 | 6 | 02/19/2019 | 02/19/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/06/2019 | 9/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2020 | Connected |  | N
National Grid | PEMBROKE | 673809 | 02359 | 5.76 |  |  | Solar |  | 05_12_16W4 | 02/24/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 511260 | 02762 | 7.6 |  |  | Solar |  | 05_07_91W49 | 03/28/2023 |  | 215 | 209 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 373135 | 01005 | 498 |  |  | Solar |  | 05_07_910W25 | 09/08/2021 | 10/13/2021 | 24 | 16 | 8 |  |  | 37 | 25 | 12 |  |  | 0 | 0 | 0 | 10/14/2021 | 10/15/2021 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 178747 | 01503 | 500 |  |  | Solar |  | 05_05_3422W4 | 12/14/2011 | 12/14/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2012 | 12/14/2011 | 6/8/2012 | Y | STD | -102 | 01/16/2013 | 02/24/2013 | 22 | 0 | 22 | 2/22/2013 | 2/22/2013 | 3/5/2013 | Connected |  | N
National Grid | ROCKLAND | 667804 | 02370 | 996 |  |  | Solar |  | 05_09_604W4 | 02/20/2025 | 03/25/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2025 | 04/24/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ATTLEBORO | 661572 | 02703 | 11.5 |  |  | Solar |  | 05_05_318W5 | 12/23/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 392758 | 01453 | 100 |  |  | Solar |  | 05_07_99W61 | 11/05/2021 | 12/02/2021 | 17 | 9 | 8 | 12/03/2021 | 12/03/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2022 |  | 6/27/2024 | N | EXP | 90 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | MONSON | 392829 | 01057 | 10 |  |  | Solar |  | 05_05_9L5 | 12/09/2021 | 01/07/2022 | 5 | 1 | 4 | 12/17/2021 | 12/17/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 12/09/2021 | 5/9/2023 | Y | EXP | 365 | 05/03/2022 | 05/06/2022 | 4 | 0 | 4 |  |  | 6/8/2022 | Connected |  | N
National Grid | REVERE | 189869 | 02151 | 4999 |  |  | Solar |  | 05_01_207W6 | 09/10/2018 | 09/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2018 | 11/19/2018 | 46 | 20 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 9/30/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 211308 | 02301 | 15 |  |  | Solar |  | 05_09_503L2 | 03/12/2019 | 03/15/2019 | 2 | 1 | 1 | 03/18/2019 | 03/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 03/12/2019 | 11/22/2019 | Y | EXP | 245 | 08/06/2019 | 08/14/2019 | 8 | 0 | 8 |  |  | 8/21/2019 | Connected |  | N
National Grid | PEMBROKE | 655553 | 02359 | 3.8 |  |  | Solar |  | 05_12_16W5 | 11/20/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | PLAINVILLE | 515507 | 02762 | 12.16 |  |  | Solar |  | 05_07_91W49 | 04/18/2024 | 05/01/2024 | 10 | 8 | 2 | 05/02/2024 | 05/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 391653 | 01535 | 7.6 |  |  | Solar |  | 05_07_910W25 | 11/02/2021 | 12/21/2021 | 6 | 0 | 6 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/02/2021 | 4/7/2023 | Y | EXP | 365 | 03/16/2022 | 04/04/2022 | 20 | 0 | 20 |  |  | 4/29/2022 | Connected |  | N
National Grid | BERLIN | 178761 | 01503 | 625 |  |  | Natural Gas |  | 05_05_3422W4 | 01/05/2012 | 01/05/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2012 |  | 2/18/2012 | N | STD | -213 |  |  | 0 | 0 | 0 | 12/18/2012 | 12/18/2012 | 12/19/2012 | Connected |  | Y
National Grid | ROCKLAND | 669274 | 02370 | 4316 |  |  | Solar |  | 05_09_604W4 | 02/21/2025 | 03/17/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2025 | 04/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SEEKONK | 716128 | 02771 | 11.4 |  |  | Solar |  | 05_05_320W1 | 09/02/2025 | 10/02/2025 | 20 | 16 | 4 | 11/04/2025 | 11/04/2025 | 39 | 19 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 396029 | 01453 | 6 |  |  | Solar |  | 05_07_99W61 | 12/07/2021 | 01/07/2022 | 22 | 20 | 2 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 12/07/2021 | 11/20/2023 | Y | EXP | 365 | 06/15/2022 | 10/11/2022 | 118 | 0 | 118 |  |  | 6/1/2023 | Connected |  | N
National Grid | MONSON | 403290 | 01057 | 250 |  |  | Solar |  | 05_05_9L5 | 01/19/2022 | 01/28/2022 | 7 | 1 | 6 | 01/31/2022 | 01/31/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2022 | 01/19/2022 | 5/13/2024 | Y | EXP | 386 | 04/15/2024 | 04/14/2024 | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | REVERE | 241465 | 02151 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 8/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 325183 | 02301 | 7.6 |  |  | Solar |  | 05_09_503L2 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | PEMBROKE | 677613 | 02359 | 250 |  |  | Solar |  | 05_12_16W5 | 06/13/2025 | 07/07/2025 | 14 | 5 | 9 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 06/13/2025 | 5/27/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 522930 | 02035 | 6.38 |  |  | Solar |  | 05_07_91W49 | 05/18/2023 | 06/14/2023 | 18 | 17 | 1 | 06/15/2023 | 06/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 393258 | 01535 | 15.2 |  |  | Solar |  | 05_07_910W25 | 11/05/2021 | 01/05/2022 | 32 | 26 | 6 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | N
National Grid | BERLIN | 178755 | 01503 | 500 |  |  | Solar |  | 05_05_3422W4 | 12/14/2011 | 12/14/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/22/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 715130 | 02370 | 5.76 |  |  | Solar |  | 05_09_604W4 | 08/27/2025 | 09/23/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ATTLEBORO | 726974 | 02703 | 15.2 |  |  | Solar |  | 05_05_320W1 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 419309 | 01453 | 240 |  |  | Solar |  | 05_07_99W61 | 05/26/2022 | 07/17/2022 | 33 | 26 | 7 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 411356 | 01057 | 4999.2 |  |  | Battery Add-On |  | 05_05_9L5 | 05/11/2022 | 07/07/2022 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2022 | 08/04/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 241464 | 02151 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 340846 | 02302 | 9.8 |  |  | Solar |  | 05_09_503L2 | 03/30/2021 | 04/06/2021 | 4 | 0 | 4 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 | 03/30/2021 | 6/7/2023 | Y | EXP | 365 | 09/11/2021 | 11/16/2021 | 67 | 4 | 63 |  |  | 6/8/2023 | Connected |  | Y
National Grid | PEMBROKE | 692294 | 02359 | 3.839 |  |  | Solar |  | 05_12_16W5 | 05/16/2025 | 06/05/2025 | 1 | 0 | 1 | 06/10/2025 | 06/10/2025 | 97 | 85 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 05/16/2025 | 11/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 559160 | 02035 | 7.875 |  |  | Solar |  | 05_07_91W49 | 10/12/2023 | 10/16/2023 | 3 | 1 | 2 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 431674 | 01535 | 0 |  |  | Battery Add-On |  | 05_07_910W25 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BERLIN | 208008 | 01503 | 7.6 |  |  | Solar |  | 05_05_3422W4 | 02/04/2019 | 02/07/2019 | 3 | 3 | 0 | 02/08/2019 | 02/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N
National Grid | ROCKLAND | 740862 | 02370 | 5.76 |  |  | Solar |  | 05_09_604W4 | 12/17/2025 | 12/22/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SEEKONK | 728545 | 02771 | 0 |  |  | Battery Add-On |  | 05_05_320W1 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 | 10/23/2025 | 12/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 668646 | 01453 | 15.2 |  |  | Solar |  | 05_07_99W61 | 01/29/2025 | 02/07/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | MONSON | 506779 | 01057 | 11.02 |  |  | Solar |  | 05_05_9L5 | 03/17/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 150 | 130 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | REVERE | 241463 | 02151 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 397572 | 02301 | 9.45 |  |  | Solar |  | 05_09_503L2 | 11/30/2021 | 12/14/2021 | 10 | 9 | 1 | 12/15/2021 | 12/15/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  | 2/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2022 | Connected |  | Y
National Grid | PEMBROKE | 730134 | 02359 | 10 |  |  | Solar |  | 05_12_16W5 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid |  | 543562 | 02093 | 10 |  |  | Solar |  | 05_07_91W49 | 07/28/2023 | 08/01/2023 | 2 | 0 | 2 | 08/02/2023 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 439708 | 01005 | 15.2 |  |  | Solar |  | 05_07_910W25 | 06/23/2022 | 06/27/2022 | 2 | 0 | 2 | 06/28/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2022 | Connected |  | N
National Grid | BOLTON | 279731 | 01740 | 0 |  |  | Solar |  | 05_05_3422W4 | 02/18/2020 | 02/26/2020 | 6 | 6 | 0 | 02/27/2020 | 02/27/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2020 |  | 3/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 174209 | 02370 | 500 |  |  | Solar |  | 05_09_604W4 | 02/27/2012 | 02/27/2012 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 733037 | 02771 | 15.2 |  |  | Solar |  | 05_05_320W1 | 11/11/2025 | 11/19/2025 | 5 | 2 | 3 | 11/20/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 424099 | 01453 | 187.5 |  |  | Solar |  | 05_07_99W62 | 06/02/2022 | 06/24/2022 | 15 | 9 | 6 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 06/02/2022 | 1/27/2026 | Y | STD | 280 | 09/23/2025 |  | 100 | 46 | 54 |  |  |  | Construction |  | Y
National Grid | MONSON | 579428 | 01057 | 6.09 |  |  | Solar |  | 05_05_9L5 | 12/26/2023 | 01/02/2024 | 4 | 0 | 4 | 01/03/2024 | 01/03/2024 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 | 12/26/2023 | 2/26/2025 | Y | EXP | 365 | 06/04/2024 | 07/09/2024 | 36 | 0 | 36 |  |  | 7/17/2024 | Connected |  | N
National Grid | REVERE | 241462 | 02151 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 409183 | 02301 | 0 |  |  | Solar |  | 05_09_503L2 | 01/28/2022 | 02/25/2022 | 20 | 19 | 1 | 02/28/2022 | 02/28/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 4/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2022 | Connected |  | N
National Grid | PEMBROKE | 176347 | 02359 | 140 |  |  | Solar |  | 05_12_16W5 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 | 03/09/2015 | 03/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/30/2015 | N | EXP | 191 |  |  | 0 | 0 | 0 | 3/25/2015 | 3/25/2015 | 11/18/2015 | Connected |  | N
National Grid |  | 543423 | 02093 | 3.8 |  |  | Solar |  | 05_07_91W49 | 07/27/2023 | 07/31/2023 | 2 | 0 | 2 | 08/01/2023 | 08/01/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | BARRE | 464697 | 01005 | 9.984 |  |  | Solar |  | 05_07_910W25 | 09/30/2022 | 10/25/2022 | 16 | 16 | 0 | 10/26/2022 | 10/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 374918 | 01532 | 468 |  |  | Solar |  | 05_05_3422W4 | 10/19/2021 | 11/24/2021 | 25 | 15 | 10 | 11/25/2021 | 11/25/2021 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | ROCKLAND | 174323 | 02370 | 1000 |  |  | Solar |  | 05_09_604W4 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 736897 | 02771 | 11.52 |  |  | Solar |  | 05_05_320W1 | 11/28/2025 | 12/01/2025 | 1 | 0 | 1 | 12/02/2025 | 12/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 672406 | 01453 | 15.2 |  |  | Solar |  | 05_07_99W62 | 02/26/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WALES | 603824 | 01081 | 15.2 |  |  | Solar |  | 05_05_9L5 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 241461 | 02149 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 419511 | 02301 | 15.2 |  |  | Solar |  | 05_09_503L2 | 03/23/2022 | 03/29/2022 | 5 | 4 | 1 | 03/30/2022 | 03/30/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 |  | 5/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | PEMBROKE | 176784 | 02359 | 432 |  |  | Solar |  | 05_12_16W5 | 01/13/2016 | 01/13/2016 | 9 | 9 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 |  | 7/1/2017 | N | EXP | 249 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 6/30/2017 | Connected |  | N
National Grid |  | 543283 | 02093 | 3.8 |  |  | Solar |  | 05_07_91W49 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2023 | 07/27/2023 | 10/15/2024 | Y | EXP | 365 | 03/15/2024 | 05/20/2024 | 67 | 0 | 67 |  |  | 6/10/2024 | Connected |  | N
National Grid | BARRE | 553060 | 01005 | 10 |  |  | Solar |  | 05_07_910W25 | 10/02/2023 | 10/05/2023 | 3 | 0 | 3 | 10/06/2023 | 10/06/2023 | 91 | 74 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 10/02/2023 | 2/26/2025 | Y | EXP | 365 | 03/14/2024 | 04/26/2024 | 44 | 0 | 44 |  |  | 7/10/2024 | Connected |  | N
National Grid | NORTHBRIDGE | 385688 | 01534 | 15.2 |  |  | Solar |  | 05_05_3422W4 | 09/30/2021 | 10/01/2021 | 1 | 0 | 1 | 10/04/2021 | 10/04/2021 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2022 | Connected |  | N
National Grid | ROCKLAND | 174603 | 02370 | 15 |  |  | Solar |  | 05_09_604W4 | 09/07/2011 | 09/07/2011 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/19/2012 | N | EXP | 48 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/19/2012 | Connected |  | N
National Grid | ATTLEBORO | 174792 | 02703 | 225 |  |  | Solar |  | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/16/2012 | N | EXP | 185 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/16/2012 | Connected |  | N
National Grid | LEOMINSTER | 738840 | 01453 | 17.6 |  |  | Solar |  | 05_07_99W62 | 12/10/2025 | 12/30/2025 | 13 | 12 | 1 | 12/31/2025 | 12/31/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MONSON | 619110 | 01057 | 6.84 |  |  | Solar |  | 05_05_9L5 | 06/19/2024 | 07/03/2024 | 4 | 2 | 2 | 07/05/2024 | 07/05/2024 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | MALDEN | 241466 | 02148 | 22.8 |  |  | Solar |  | 05_01_207W6 | 07/01/2019 | 07/10/2019 | 5 | 0 | 5 | 07/11/2019 | 07/11/2019 | 14 | 9 | 5 | 08/07/2019 | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  | 09/09/2019 | 22 | 6 | 16 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 7/31/2020 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  | 9/1/2020 | Connected |  | N
National Grid | BROCKTON | 425011 | 02301 | 10 |  |  | Solar |  | 05_09_503L2 | 05/23/2022 | 05/25/2022 | 2 | 1 | 1 | 05/26/2022 | 05/26/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 7/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | Y
National Grid | PEMBROKE | 323866 | 02359 | 6 |  |  | Solar |  | 05_12_16W5 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/23/2020 | 6/16/2022 | Y | EXP | 365 | 10/15/2021 | 12/07/2021 | 54 | 4 | 50 |  |  | 12/13/2021 | Connected |  | Y
National Grid |  | 551871 | 02093 | 6 |  |  | Solar |  | 05_07_91W49 | 09/19/2023 | 10/03/2023 | 11 | 8 | 3 | 10/04/2023 | 10/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2024 | Connected |  | N
National Grid | BARRE | 645357 | 01005 | 10 |  |  | Solar |  | 05_07_910W25 | 10/07/2024 | 10/18/2024 | 2 | 0 | 2 | 10/21/2024 | 10/21/2024 | 22 | 0 | 22 | 01/10/2025 | 02/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 02/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 2/19/2025 | 10/07/2024 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | WHITINSVILLE | 393455 | 01588 | 10 |  |  | Solar |  | 05_05_3422W4 | 02/12/2023 | 01/14/2022 | 2 | 1 | 1 | 02/14/2023 | 02/14/2023 | 26 | 3 | 23 | 04/06/2023 | 05/08/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 05/08/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 1/14/2022 |  | 8/2/2024 | N | EXP | 365 | 07/13/2023 | 07/26/2023 | 14 | 0 | 14 |  |  | 8/30/2023 | Connected |  | N
National Grid | ROCKLAND | 175217 | 02370 | 480 |  |  | Solar |  | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 | 11/17/2014 | 11/17/2014 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 174791 | 02703 | 120 |  |  | Solar |  | 05_05_320W1 | 06/20/2011 | 06/20/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2011 |  | 3/12/2012 | N | EXP | 181 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | LEOMINSTER | 177595 | 01453 | 323 |  |  | Solar |  | 05_07_99W62 | 07/17/2017 | 07/17/2017 | 10 | 10 | 0 | 07/31/2017 | 07/31/2017 | 165 | 3 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 7/22/2018 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  | 6/12/2018 | Connected |  | N
National Grid | MONSON | 632018 | 01057 | 5.12 |  |  | Solar |  | 05_05_9L5 | 08/16/2024 | 08/20/2024 | 2 | 1 | 1 | 08/21/2024 | 08/21/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 294443 | 02149 | 15.2 |  |  | Solar |  | 05_01_207W6 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 73 | 55 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 06/02/2020 | 6/4/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 4/29/2021 | Connected |  | N
National Grid | BROCKTON | 530542 | 02301 | 3.8 |  |  | Solar |  | 05_09_503L2 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  | 9/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | PEMBROKE | 326220 | 02359 | 7.6 |  |  | Solar |  | 05_12_16W5 | 11/25/2020 | 12/01/2020 | 2 | 0 | 2 | 12/02/2020 | 12/02/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 11/25/2020 | 9/13/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid |  | 552507 | 02093 | 5.985 |  |  | Solar |  | 05_07_91W49 | 09/11/2023 | 09/12/2023 | 2 | 1 | 1 | 09/13/2023 | 09/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 646996 | 01005 | 5.7 |  |  | Solar |  | 05_07_910W25 | 10/14/2024 | 11/01/2024 | 4 | 0 | 4 | 11/04/2024 | 11/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/14/2024 | 2/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | UPTON | 397405 | 01568 | 5.76 |  |  | Solar |  | 05_05_3422W4 | 11/23/2021 | 12/15/2021 | 5 | 4 | 1 | 12/16/2021 | 12/16/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  | 7/23/2023 | N | EXP | 550 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKLAND | 175214 | 02370 | 960 |  |  | Solar |  | 05_09_604W4 | 11/03/2014 | 11/03/2014 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2014 | 12/08/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 03/18/2017 | 02/14/2017 | 0 | 0 | 0 | 5/9/2017 | 11/03/2014 | 9/27/2018 | Y | STD | 506 |  |  | 0 | 0 | 0 |  |  | 9/17/2018 | Connected |  | N
National Grid | SEEKONK | 175581 | 02771 | 13.6 |  |  | Solar |  | 05_05_320W1 | 12/12/2014 | 12/12/2014 | 38 | 38 | 0 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2015 |  | 4/30/2015 | N | EXP | 78 |  |  | 0 | 0 | 0 | 2/5/2016 | 2/5/2016 | 2/5/2016 | Connected |  | N
National Grid | LEOMINSTER | 345576 | 01453 | 9.6 |  |  | Solar |  | 05_07_99W62 | 03/08/2021 | 03/10/2021 | 1 | 0 | 1 | 03/11/2021 | 03/11/2021 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | WALES | 646163 | 01081 | 6 |  |  | Solar |  | 05_05_9L5 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/04/2024 | 12/04/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | EVERETT | 295621 | 02149 | 9.8 |  |  | Solar |  | 05_01_207W6 | 07/30/2020 | 08/03/2020 | 1 | 0 | 1 | 08/04/2020 | 08/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/30/2020 | 8/2/2021 | Y | EXP | 365 | 05/04/2021 | 05/05/2021 | 1 | 0 | 1 |  |  | 5/24/2021 | Connected |  | N
National Grid | BROCKTON | 554489 | 02301 | 3.8 |  |  | Solar |  | 05_09_503L2 | 09/12/2023 | 09/13/2023 | 1 | 0 | 1 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/12/2023 | 11/11/2024 | Y | EXP | 365 | 12/27/2023 | 01/18/2024 | 23 | 0 | 23 |  |  | 3/8/2024 | Connected |  | N
National Grid | PEMBROKE | 419637 | 02359 | 85 |  |  | Solar |  | 05_12_16W5 | 04/13/2022 | 07/26/2022 | 70 | 62 | 8 | 07/27/2022 | 07/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 | 04/13/2022 | 1/18/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2023 | Connected |  | N
National Grid |  | 555644 | 02093 | 5 |  |  | Solar |  | 05_07_91W49 | 10/11/2023 | 10/16/2023 | 3 | 0 | 3 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 |  | 12/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | HUBBARDSTON | 651669 | 01452 | 9.92 |  |  | Solar |  | 05_07_910W25 | 11/01/2024 | 12/02/2024 | 5 | 0 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | NORTHBRIDGE | 446350 | 01534 | 6.96 |  |  | Solar |  | 05_05_3422W4 | 08/01/2022 | 08/04/2022 | 3 | 0 | 3 | 08/05/2022 | 08/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 08/01/2022 | 2/3/2024 | Y | EXP | 365 | 10/27/2022 | 02/01/2023 | 98 | 0 | 98 |  |  | 2/14/2023 | Connected |  | N
National Grid | ABINGTON | 175544 | 02351 | 1000 |  |  | Solar |  | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | SEEKONK | 175862 | 02771 | 5 |  |  | Solar |  | 05_05_320W1 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/10/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 5/5/2016 | Connected |  | N
National Grid | LEOMINSTER | 412225 | 01453 | 0 |  |  | Battery Add-On |  | 05_07_99W62 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 657113 | 01057 | 6.96 |  |  | Solar |  | 05_05_9L5 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/26/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | MALDEN | 326200 | 02148 | 11.4 |  |  | Solar |  | 05_01_207W6 | 11/19/2020 | 11/25/2020 | 4 | 2 | 2 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/24/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | BROCKTON | 648797 | 02302 | 5.76 |  |  | Solar |  | 05_09_503L2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 642291 | 02359 | 11.4 |  |  | Solar |  | 05_12_16W5 | 09/25/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 566403 | 02093 | 6 |  |  | Solar |  | 05_07_91W49 | 11/16/2023 | 11/27/2023 | 6 | 0 | 6 | 11/28/2023 | 11/28/2023 | 89 | 68 | 21 | 05/01/2024 | 06/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 06/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 652723 | 01452 | 2000 |  |  | Other |  | 05_07_910W25 | 05/07/2025 | 06/17/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2025 | 07/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 453555 | 01534 | 0 |  |  | Battery Add-On |  | 05_05_3422W4 | 10/17/2022 | 10/27/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 11/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 175543 | 02351 | 557 |  |  | Solar |  | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2015 | N | STD |  | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 175949 | 02771 | 15.2 |  |  | Solar |  | 05_05_320W1 | 03/13/2015 | 03/13/2015 | 7 | 4 | 3 | 03/26/2015 | 03/26/2015 | 468 | 0 | 468 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 4/14/2015 | 4/14/2015 |  | Withdrawn |  | N
National Grid | LEOMINSTER | 553916 | 01453 | 10 |  |  | Solar |  | 05_07_99W62 | 04/03/2024 | 09/15/2023 | 3 | 0 | 3 | 04/09/2024 | 04/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 673203 | 01057 | 17.28 |  |  | Solar |  | 05_05_9L5 | 02/25/2025 | 03/03/2025 | 5 | 1 | 4 | 03/04/2025 | 03/04/2025 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | MALDEN | 325515 | 02148 | 7.6 |  |  | Solar |  | 05_01_207W6 | 11/30/2020 | 12/08/2020 | 5 | 0 | 5 | 12/09/2020 | 12/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 11/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 655987 | 02301 | 7.6 |  |  | Solar |  | 05_09_503L2 | 11/21/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | PEMBROKE | 588206 | 02359 | 6 |  |  | Solar |  | 05_12_16W6 | 05/06/2024 | 09/17/2024 | 52 | 50 | 2 | 09/18/2024 | 09/18/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2024 | 05/06/2024 | 1/24/2026 | Y | EXP | 425 | 03/27/2025 | 07/11/2025 | 107 | 0 | 107 |  |  |  | Completion Documents |  | Y
National Grid |  | 561903 | 02093 | 15.2 |  |  | Solar |  | 05_07_91W49 | 10/10/2023 | 10/20/2023 | 8 | 6 | 2 | 10/23/2023 | 10/23/2023 | 28 | 16 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 676202 | 01005 | 4990 |  |  | Solar |  | 05_07_910W25 | 04/29/2025 | 05/27/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2025 | 07/02/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 566683 | 01588 | 46 |  |  | Solar |  | 05_05_3422W4 | 10/27/2023 | 11/13/2023 | 10 | 8 | 2 | 11/14/2023 | 11/14/2023 | 95 | 79 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | ABINGTON | 175542 | 02351 | 540 |  |  | Solar |  | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | SEEKONK | 176133 | 02771 | 10 |  |  | Solar |  | 05_05_320W1 | 04/15/2015 | 04/15/2015 | 1 | 1 | 0 | 04/17/2015 | 04/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 04/15/2015 | 12/31/2016 | Y | EXP | 614 | 02/19/2016 | 02/29/2016 | 6 | 0 | 6 | 4/27/2015 | 4/27/2015 | 8/8/2016 | Connected |  | N
National Grid | LEOMINSTER | 577753 | 01453 | 0 |  |  | Other |  | 05_07_99W62 | 01/04/2024 | 02/21/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2024 | 02/28/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 678782 | 01057 | 5.76 |  |  | Solar |  | 05_05_9L5 | 03/19/2025 | 03/26/2025 | 5 | 0 | 5 | 03/27/2025 | 03/27/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 401899 | 02148 | 6 |  |  | Solar |  | 05_01_207W6 | 01/26/2022 | 01/27/2022 | 0 | 0 | 0 | 01/28/2022 | 01/28/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | BROCKTON | 661116 | 02301 | 11.5 |  |  | Solar |  | 05_09_503L2 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | Y
National Grid | PEMBROKE | 726424 | 02359 | 3.8 |  |  | Solar |  | 05_12_16W6 | 10/14/2025 | 11/17/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid |  | 568459 | 02093 | 15.2 |  |  | Solar |  | 05_07_91W49 | 11/22/2023 | 12/18/2023 | 17 | 14 | 3 | 12/19/2023 | 12/19/2023 | 83 | 28 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 684020 | 01005 | 22.8 |  |  | Solar |  | 05_07_910W25 | 04/12/2025 | 04/16/2025 | 3 | 0 | 3 | 04/17/2025 | 04/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | WHITINSVILLE | 659602 | 01588 | 480 |  |  | Solar |  | 05_05_3424W1 | 05/20/2025 | 07/29/2025 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2025 | 09/25/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ABINGTON | 175541 | 02351 | 380 |  |  | Solar |  | 05_09_604W4 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 | 12/22/2015 | 12/05/2014 | 3/31/2018 | Y | STD | 830 | 01/03/2018 | 02/20/2018 | 32 | 0 | 32 | 2/21/2018 | 2/21/2018 | 3/6/2018 | Connected |  | N
National Grid | ATTLEBORO | 176293 | 02703 | 7.6 |  |  | Solar |  | 05_05_320W1 | 07/10/2015 | 07/10/2015 | 15 | 15 | 0 | 08/03/2015 | 08/03/2015 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/18/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 655138 | 01453 | 3.8 |  |  | Solar |  | 05_07_99W62 | 11/19/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | MONSON | 681353 | 01057 | 15.2 |  |  | Solar |  | 05_05_9L5 | 03/28/2025 | 04/02/2025 | 3 | 0 | 3 | 04/03/2025 | 04/03/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | MALDEN | 409760 | 02148 | 12 |  |  | Solar |  | 05_01_207W6 | 05/12/2022 | 05/17/2022 | 3 | 1 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | BROCKTON | 667744 | 02301 | 7.6 |  |  | Solar |  | 05_09_503L2 | 01/24/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | PEMBROKE | 174267 | 02359 | 75 |  |  | Solar |  | 05_12_16W6 | 01/03/2012 | 01/03/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 4/2/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid |  | 568062 | 02093 | 6 |  |  | Solar |  | 05_07_91W49 | 11/16/2023 |  | 73 | 27 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BARRE | 701465 | 01005 | 5.76 |  |  | Solar |  | 05_07_910W25 | 06/26/2025 | 07/30/2025 | 3 | 0 | 3 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/26/2025 | 10/1/2026 | Y | EXP | 365 | 11/05/2025 | 11/28/2025 | 24 | 0 | 24 |  |  | 12/4/2025 | Connected |  | N
National Grid | UPTON | 178751 | 01568 | 125 |  |  | Solar |  | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 | 03/30/2012 | 03/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 2 |  |  | 0 | 0 | 0 | 12/13/2012 | 12/13/2012 | 12/19/2012 | Connected |  | N
National Grid | ABINGTON | 175752 | 02351 | 480 |  |  | Solar |  | 05_09_604W4 | 10/31/2014 | 10/31/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 176431 | 02703 | 6 |  |  | Solar |  | 05_05_320W1 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 11/1/2016 | Connected |  | N
National Grid | LEOMINSTER | 656847 | 01453 | 5.76 |  |  | Solar |  | 05_07_99W62 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | MONSON | 704378 | 01057 | 34.2 |  |  | Solar |  | 05_05_9L5 | 08/14/2025 | 08/21/2025 | 4 | 3 | 1 | 08/22/2025 | 08/22/2025 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | EVERETT | 416852 | 02149 | 9.86 |  |  | Solar |  | 05_01_207W6 | 03/11/2022 | 04/04/2022 | 16 | 13 | 3 | 04/05/2022 | 04/05/2022 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/11/2022 | 7/26/2023 | Y | EXP | 365 | 06/30/2022 | 07/20/2022 | 21 | 0 | 21 |  |  | 8/24/2022 | Connected |  | Y
National Grid | BROCKTON | 671245 | 02301 | 10 |  |  | Solar |  | 05_09_503L2 | 02/10/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 177687 | 02359 | 6.54 |  |  | Solar |  | 05_12_16W6 | 09/29/2017 | 09/29/2017 | 5 | 5 | 0 | 10/06/2017 | 10/06/2017 | 80 | 12 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/7/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid |  | 570456 | 02093 | 0 |  |  | Solar |  | 05_07_91W49 | 11/10/2023 | 11/16/2023 | 5 | 3 | 2 | 11/17/2023 | 11/17/2023 | 104 | 91 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | BARRE | 391839 | 01005 | 0 |  |  | Other |  | 05_07_910W26 | 11/11/2021 | 01/05/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 03/02/2022 | 38 | 4 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 178750 | 01568 | 495 |  |  | Solar |  | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 | 03/30/2012 | 03/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 2 |  |  | 0 | 0 | 0 | 12/19/2012 | 12/19/2012 | 12/19/2012 | Connected |  | N
National Grid | ABINGTON | 175977 | 02351 | 760 |  |  | Solar |  | 05_09_604W4 | 05/07/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2016 | 08/11/2016 | 50 | 0 | 50 | 12/9/2015 | 05/07/2015 | 6/30/2016 | Y | STD | 204 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 176467 | 02771 | 27 |  |  | Solar |  | 05_05_320W1 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/13/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 12/5/2016 | Connected |  | N
National Grid | LEOMINSTER | 424573 | 01453 | 480 |  |  | Solar |  | 05_07_99W63 | 06/03/2022 | 07/13/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2022 | 08/09/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 4/30/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MONSON | 702226 | 01057 | 11.4 |  |  | Solar |  | 05_05_9L6 | 07/02/2025 | 07/09/2025 | 2 | 0 | 2 | 12/16/2025 | 12/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | EVERETT | 427452 | 02149 | 19 |  |  | Solar |  | 05_01_207W6 | 05/03/2022 | 06/28/2022 | 38 | 35 | 3 | 06/29/2022 | 06/29/2022 | 343 | 325 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 683451 | 02301 | 3.8 |  |  | Solar |  | 05_09_503L2 | 04/15/2025 |  | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 177718 | 02359 | 3.8 |  |  | Solar |  | 05_12_16W6 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 121 | 0 | 121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 577152 | 02035 | 8.7 |  |  | Solar |  | 05_07_91W49 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 12/27/2023 | 4/20/2025 | Y | EXP | 365 | 06/27/2024 | 07/17/2024 | 21 | 0 | 21 |  |  | 9/11/2024 | Connected |  | N
National Grid | BARRE | 676968 | 01005 | 750 |  |  | Solar |  | 05_07_910W51 | 04/11/2025 | 06/27/2025 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBRIDGE | 178749 | 01534 | 75 |  |  | Solar |  | 05_05_3424W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/1/2012 | N | EXP | -164 |  |  | 0 | 0 | 0 | 12/19/2012 | 12/19/2012 | 12/19/2012 | Connected |  | N
National Grid | ABINGTON | 175975 | 02351 | 990 |  |  | Solar |  | 05_09_604W4 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 176739 | 02771 | 3 |  |  | Solar |  | 05_05_320W1 | 10/29/2015 | 10/29/2015 | 2 | 2 | 0 | 11/04/2015 | 11/04/2015 | 275 | 0 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/7/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/17/2015 | 11/17/2015 |  | Withdrawn |  | N
National Grid | LEOMINSTER | 581885 | 01453 | 100 |  |  | Solar |  | 05_07_99W63 | 02/22/2024 | 03/06/2024 | 9 | 0 | 9 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MONSON | 177097 | 01057 | 5 |  |  | Solar |  | 05_05_9L6 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/24/2016 | 5/30/2017 | Y | EXP | 358 | 11/03/2016 | 11/14/2016 | 6 | 0 | 6 | 1/5/2017 | 1/5/2017 | 1/5/2017 | Connected |  | N
National Grid | MELROSE | 471046 | 02176 | 6 |  |  | Solar |  | 05_01_207W6 | 11/20/2023 | 11/01/2022 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 | 11/20/2023 | 2/20/2025 | Y | EXP | 365 | 05/03/2024 | 05/29/2024 | 27 | 0 | 27 |  |  | 7/6/2024 | Connected |  | N
National Grid | BROCKTON | 699724 | 02301 | 19 |  |  | Solar |  | 05_09_503L2 | 06/19/2025 | 06/23/2025 | 2 | 0 | 2 | 06/24/2025 | 06/24/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | PEMBROKE | 177754 | 02359 | 6 |  |  | Solar |  | 05_12_16W6 | 07/31/2017 | 07/31/2017 | 8 | 8 | 0 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/6/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/12/2018 | Connected |  | Y
National Grid |  | 578264 | 02093 | 10 |  |  | Solar |  | 05_07_91W49 | 02/14/2024 | 02/16/2024 | 2 | 0 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 675216 | 01005 | 0 |  |  | Other |  | 05_07_910W51 | 06/25/2025 | 08/26/2025 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBRIDGE | 178766 | 01534 | 375 |  |  | Solar |  | 05_05_3424W1 | 07/27/2012 | 07/27/2012 | 242 | 233 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 177057 | 02351 | 4900.5 |  |  | Solar |  | 05_09_604W4 | 01/16/2017 | 01/19/2017 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/03/2017 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 | 01/16/2017 | 9/24/2021 | Y | STD | 996 | 02/28/2019 | 10/27/2020 | 608 | 5 | 603 | 6/4/2021 | 9/23/2021 | 9/24/2021 | Connected |  | N
National Grid | SEEKONK | 176840 | 02771 | 7 |  |  | Solar |  | 05_05_320W1 | 05/02/2016 | 05/02/2016 | 5 | 5 | 0 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 | 05/02/2016 | 5/7/2017 | Y | EXP | 347 | 08/01/2016 | 10/19/2016 | 55 | 0 | 55 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | LEOMINSTER | 693329 | 01453 | 200 |  |  | Solar |  | 05_07_99W63 | 05/29/2025 | 08/25/2025 | 58 | 48 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MONSON | 178043 | 01057 | 1382 |  |  | Solar |  | 05_05_9L6 | 05/03/2017 | 05/03/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2017 | 05/30/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2017 |  | 2/15/2019 | N | STD | 443 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 487948 | 02148 | 10 |  |  | Solar |  | 05_01_207W6 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 9/19/2024 | Y | EXP | 365 | 10/18/2023 | 11/14/2023 | 28 | 0 | 28 |  |  | 1/31/2024 | Connected |  | Y
National Grid | BROCKTON | 174449 | 02301 | 1000 |  |  | Solar |  | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 178263 | 02359 | 16.32 |  |  | Solar |  | 05_12_16W6 | 04/17/2018 | 04/17/2018 | 3 | 3 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 340 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 584131 | 02035 | 10 |  |  | Solar |  | 05_07_91W49 | 01/24/2024 | 03/05/2024 | 28 | 26 | 2 | 03/06/2024 | 03/06/2024 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 | 01/24/2024 | 4/15/2025 | Y | EXP | 365 | 05/15/2024 | 05/17/2024 | 3 | 0 | 3 |  |  | 6/12/2024 | Connected |  | N
National Grid | BARRE | 175661 | 01005 | 70 |  |  | Solar |  | 05_07_910W51 | 05/23/2014 | 05/23/2014 | 5 | 2 | 3 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2014 |  | 8/29/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 11/19/2014 | Connected |  | N
National Grid | NORTHBRIDGE | 178776 | 01534 | 255 |  |  | Solar |  | 05_05_3424W1 | 04/02/2014 | 04/02/2014 | 5 | 0 | 5 | 04/11/2014 | 04/11/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 | 04/02/2014 | 6/30/2014 | Y | EXP | 67 |  |  | 0 | 0 | 0 | 8/13/2015 | 8/13/2015 | 8/13/2015 | Connected |  | N
National Grid | ABINGTON | 177955 | 02351 | 3300 |  |  | Solar |  | 05_09_604W4 | 10/23/2017 | 12/21/2017 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/02/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 10/31/2018 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 177348 | 02771 | 7.6 |  |  | Solar |  | 05_05_320W1 | 11/23/2016 | 11/23/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 |  | 11/28/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 177849 | 01453 | 166.5 |  |  | Solar |  | 05_07_99W63 | 04/06/2017 | 04/06/2017 | 7 | 7 | 0 | 04/19/2017 | 04/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 04/06/2017 | 4/12/2018 | Y | EXP | 324 | 05/24/2017 | 06/21/2017 | 19 | 0 | 19 | 12/15/2017 | 12/15/2017 | 12/21/2017 | Connected |  | N
National Grid | MONSON | 203529 | 01057 | 3.8 |  |  | Solar |  | 05_05_9L6 | 01/30/2019 | 02/12/2019 | 8 | 0 | 8 | 02/13/2019 | 02/13/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 491121 | 02176 | 9.86 |  |  | Solar |  | 05_01_207W6 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 | 02/02/2023 | 5/31/2024 | Y | EXP | 365 | 06/01/2023 | 05/31/2023 | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | BROCKTON | 174448 | 02301 | 1000 |  |  | Solar |  | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 185547 | 02359 | 17.85 |  |  | Solar |  | 05_12_16W6 | 05/16/2018 | 05/16/2018 | 35 | 25 | 10 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FOXBOROUGH | 586610 | 02035 | 7.6 |  |  | Solar |  | 05_07_91W49 | 02/09/2024 | 03/05/2024 | 16 | 13 | 3 | 03/06/2024 | 03/06/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 | 02/09/2024 | 4/11/2025 | Y | EXP | 365 | 08/27/2024 | 10/03/2024 | 38 | 0 | 38 |  |  | 1/16/2025 | Connected |  | N
National Grid | BARRE | 175884 | 01005 | 15.2 |  |  | Solar |  | 05_07_910W51 | 05/20/2015 | 05/20/2015 | 1 | 1 | 0 | 05/27/2015 | 05/27/2015 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 10/30/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 178775 | 01568 | 170 |  |  | Solar |  | 05_05_3424W1 | 08/27/2014 | 08/27/2014 | 7 | 0 | 7 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2014 |  | 11/28/2014 | N | EXP | 57 |  |  | 0 | 0 | 0 | 1/2/2015 | 1/2/2015 | 2/22/2016 | Connected |  | N
National Grid | ABINGTON | 178496 | 02351 | 10 |  |  | Solar |  | 05_09_604W4 | 12/04/2017 | 02/12/2018 | 46 | 46 | 0 | 02/12/2018 | 02/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 |  | 12/10/2018 | N | EXP | 301 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 177890 | 02771 | 15.2 |  |  | Solar |  | 05_05_320W1 | 04/12/2017 | 04/12/2017 | 4 | 3 | 1 | 04/20/2017 | 04/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2017 |  | 4/18/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/29/2017 | 8/29/2017 | 9/5/2017 | Connected |  | N
National Grid | LEOMINSTER | 178160 | 01453 | 230 |  |  | Solar |  | 05_07_99W63 | 12/26/2017 | 12/26/2017 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2018 | 01/30/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/26/2017 | 7/10/2019 | Y | STD | 384 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 205070 | 01057 | 0 |  |  | Solar |  | 05_05_9L6 | 01/03/2019 | 01/11/2019 | 5 | 0 | 5 | 01/14/2019 | 01/14/2019 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  | 3/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | MELROSE | 556880 | 02176 | 9.86 |  |  | Solar |  | 05_01_207W6 | 10/18/2023 | 11/08/2023 | 16 | 14 | 2 | 11/09/2023 | 11/09/2023 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174447 | 02301 | 1000 |  |  | Solar |  | 05_09_503L4 | 07/11/2012 | 07/11/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/24/2012 | 10/16/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 237449 | 02339 | 7.6 |  |  | Solar |  | 05_12_16W6 | 07/15/2019 | 08/06/2019 | 16 | 16 | 0 | 08/07/2019 | 08/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 | 07/15/2019 | 3/10/2020 | Y | EXP | 365 | 10/11/2019 | 01/07/2020 | 88 | 0 | 88 |  |  | 1/12/2020 | Connected |  | N
National Grid | FOXBOROUGH | 588333 | 02035 | 6.96 |  |  | Solar |  | 05_07_91W49 | 02/14/2024 | 02/20/2024 | 3 | 0 | 3 | 02/21/2024 | 02/21/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BARRE | 176278 | 01005 | 98 |  |  | Solar |  | 05_07_910W51 | 05/05/2015 | 05/05/2015 | 1 | 1 | 0 | 05/08/2015 | 05/08/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 | 05/05/2015 | 10/30/2015 | Y | EXP | 170 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITINSVILLE | 178799 | 01588 | 432.9 |  |  | Solar |  | 05_05_3424W1 | 02/16/2018 | 02/16/2018 | 0 | 0 | 0 |  |  | 33 | 8 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2018 | 02/16/2018 | 9/11/2020 | Y | STD | 417 | 01/10/2020 | 05/08/2020 | 119 | 0 | 119 |  |  | 9/3/2020 | Connected |  | N
National Grid | ROCKLAND | 189429 | 02370 | 3000 |  |  | Solar |  | 05_09_604W4 | 06/28/2018 | 06/28/2018 | 7 | 7 | 0 |  |  | 10 | 6 | 4 |  |  | 0 | 0 | 0 | 07/25/2018 | 09/13/2018 | 36 | 9 | 27 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178493 | 02703 | 4980 |  |  | Solar |  | 05_05_320W1 | 12/01/2017 | 12/01/2017 | 45 | 43 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2018 | 03/26/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2018 | 12/01/2017 | 3/31/2021 | Y | STD | 434 | 01/14/2021 | 03/31/2021 | 76 | 0 | 76 |  |  | 3/31/2021 | Connected |  | N
National Grid | LEOMINSTER | 178648 | 01453 | 244 |  |  | Solar |  | 05_07_99W63 | 12/15/2017 | 12/15/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/02/2018 | 01/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 | 12/15/2017 | 8/6/2021 | Y | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N