## Sheet1
DG Interconnection Tracking and Reporting
Utility Timelines
Reporting Period: |  |  |  | from |  |  | 2009-01-01 |  | to
Date Filed:
Force Majeure Reporting | [6 empty] | Start Date |  | End Date | Explanation
Enter Dates (inclusive) of Force Majeure Events with "Clock" Stoppage |  |  |  | Force Majuere events listed in Holidays worksheet
* added Complex
|  |  |  | Total Workdays (calculated) |  |  | 0 |  | #VALUE!
[7 empty] | 0 |  | 0
Application and Site Information | [9 empty] | Application Receipt |  |  |  |  | Screen Review |  |  |  |  | Supplemental Review |  |  |  |  | Standard Process Initial Review |  |  |  |  | Impact Study |  |  |  |  | Detailed Study |  |  |  |  | IA and Pre-Construction Information | [5 empty] | Construction |  |  |  |  | Witness Test |  | Authorization and Misc Information |  |  |  | Group Study Info
Company Name | City/Town | Facility ID (if any) | ZIP Code | Design Capacity (Nameplate) (kW) | Export Capacity (kW) | Import Capacity (kW) | Fuel Type (Solar, Wind, etc) | Battery Energy Storage System (BESS) | Circuit Name | Date Application Received | Date Application Deemed Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Review of Screens Begun | Date Review of Screens Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Supplemental Review Begun | Date Supplemental Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Standard Process Initial Review Begun | Date Standard Process Initial Review Complete | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Impact Study Begun | Date Impact Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Detailed Study Begun | Date Detailed Study Sent | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Interconnection Agreement Sent | Date ISA and Payment Received | Estimated In-Service Date (listed on App.) | System Modification Required | Expedited/Standard / Complex Project | Construction Commitment Date | Date Construction Begun | Date Construction Completed | Total Time Lapsed (Workdays) calculated value | Customer Time Lapsed (Workdays) enter workdays of "clock" stoppage by Customer | Utility Time Lapsed (Workdays) enter workdays without "clock" stoppage | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | NOTES | Comm/Indus/Res/Muni | Net Metered? (Y/N) | Group Study | Group Study Designation
Fitchburg | Lunenburg | 11955 | 1462 | 8.4 | 8.4 | 0 | Solar + Energy Storage | Yes | F30W31 | 2025-12-01 | 2026-01-06 | 24 | 22 | 2 | 2026-01-06 | 2026-01-12 | 4 | 0 | 4 | [20 empty] | 2026-01-12 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12010 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-30 | 2026-01-08 | 6 | 5 | 1 | 2026-01-08 | 2026-01-12 | 2 | 0 | 2 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 12023 | 1462 | 20 | 20 | N/A | Solar | No | F31W37 | 2026-01-07 | 2026-01-08 | 1 | 0 | 1 | 2026-01-08 | 2026-01-13 | 3 | 0 | 3 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Fitchburg | 12030 | 1420 | 240 | 240 | N/A | Solar | No | F35W36 | 2026-01-15 | [33 empty] | Expedited | [9 empty] | Application Received | Comm | Y
Fitchburg | Fitchburg | 12025 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F31W34 | 2026-01-28 | [33 empty] | Expedited | [9 empty] | Application Received | Res | Y
Fitchburg | Fitchburg | 12026 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F31W34 | 2026-01-05 | 2026-01-07 | 2 | 1 | 1 | 2026-01-07 | 2026-01-12 | 3 | 0 | 3 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 12032 | 1474 | 15.2 | 15.2 | N/A | Solar | No | F39W18 | 2026-01-06 | [33 empty] | Expedited | [9 empty] | Application Received | Res | Y
Fitchburg | Fitchburg | 12035 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F50W51 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-15 | 2 | 0 | 2 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12037 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F11W11 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-14 | 1 | 0 | 1 | [20 empty] | 2026-01-20 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 12042 | 1420 | 15.2 | 15.2 | N/A | Solar | No | F25W27 | 2026-01-15 | 2026-01-23 | 6 | 5 | 1 | 2026-01-23 | 2026-01-26 | 3 | 0 | 3 | [23 empty] | NO | Expedited | [9 empty] | Review Analysis and Approval Letter | Res | Y
Fitchburg | Fitchburg | 12044 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F25W27 | 2026-01-09 | 2026-01-13 | 2 | 0 | 2 | 2026-01-13 | 2026-01-14 | 1 | 0 | 1 | [20 empty] | 2026-01-16 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12059 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W40 | 2026-01-19 | 2026-01-21 | 2 | 0 | 2 | 2026-01-21 | 2026-01-23 | 2 | 0 | 2 | [20 empty] | 2026-02-02 |  |  | YES | Expedited | [9 empty] | Review Analysis and Approval Letter | Res | Y
Fitchburg | Ashby | 12068 | 1431 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W19 | 2026-01-28 | 2026-01-29 | 1 | 0 | 1 | 2026-01-29 | 2026-01-30 | 1 | 0 | 1 | [23 empty] | YES | Expedited | [9 empty] | Prepare Estimate | Res | Y
Fitchburg | Townsend | 11931 | 1469 | 7.6 | 7.6 | N/A | Solar | No | F39W18 | 2025-11-12 | 2025-12-02 | 12 | 9 | 3 | 2025-12-04 | 2025-12-04 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [8 empty] | 2025-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 11913 | 1420 | 20 | 20 | N/A | Solar | No | F50W51 | 2025-11-14 | 2025-12-09 | 15 | 8 | 7 | 12/11/205 | 2025-12-12 | 1 | 0 | 1 | [20 empty] | 2025-12-15 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Fitchburg | 11940 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F50W55 | 2025-11-24 | 2025-12-01 | 2 | 0 | 2 | 2025-12-01 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11992 | 1462 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F30W30 | 2025-12-19 | 2025-12-23 | 2 | 0 | 2 | 2025-12-23 | 2025-12-29 | 3 | 0 | 3 | [23 empty] | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11991 | 1420 | 13.7 | 13.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-12-16 | 2025-12-17 | 1 | 0 | 1 | 2025-12-17 | 2025-12-18 | 1 | 0 | 1 | [20 empty] | 2025-12-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11984 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F01W04 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2026-01-08 |  |  | YES | Expedited | [9 empty] | Waiting for Mods Fee | Res | Y
Fitchburg | Fitchburg | 11983 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2026-01-08 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11975 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-26 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11968 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-26 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11952 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F50W55 | 2025-12-02 | 2025-12-04 | 2 | 0 | 2 | 2025-12-04 | 2025-12-09 | 3 | 2 | 1 | [20 empty] | 2025-12-15 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11939 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-24 | 2025-12-01 | 3 | 0 | 3 | 2025-12-01 | 2025-12-03 | 2 | 0 | 2 | [20 empty] | 2025-12-11 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11937 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-11-24 | 2025-12-04 | 6 | 4 | 2 | 2025-12-04 | 2025-12-05 | 1 | 0 | 1 | [20 empty] | 2025-12-11 | 2026-01-22 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 12002 | 1462 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F31W37 | 2025-12-19 | 2025-12-29 | 5 | 3 | 2 | 2025-12-29 | 2025-12-31 | 2 | 1 | 1 | [20 empty] | 2026-01-12 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 12011 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F20W22 | 2025-12-30 | 2025-12-30 | 1 | 0 | 1 | 2025-12-30 | 2026-01-05 | 3 | 0 | 3 | [20 empty] | 2026-01-12 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11891 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-11-21 | 2025-12-03 | 6 | 4 | 2 | 2025-12-03 | 2025-12-03 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11903 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F22W1 | 2025-11-14 | 2025-12-02 | 10 | 8 | 2 | 2025-12-02 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11941 | 1420 | 15.7 | 15.7 | N/A | Solar | No | F40W40 | 2025-11-24 | 2025-12-02 | 4 | 1 | 3 | 2025-12-02 | 2025-12-03 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11943 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-24 | 2025-12-01 | 3 | 0 | 3 | 2025-12-01 | 2025-12-02 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11946 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-11-24 | 2025-12-03 | 5 | 2 | 3 | 2025-12-03 | 2025-12-04 | 1 | 0 | 1 | [20 empty] | 2025-12-04 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11960 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F50W51 | 2025-12-09 | 2025-12-12 | 3 | 0 | 3 | 2025-12-12 | 2025-12-16 | 2 | 0 | 2 | [20 empty] | 2025-12-17 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11967 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-12-09 | 2025-12-15 | 4 | 3 | 1 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2025-12-17 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11997 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F20W22 | 2025-12-19 | 2025-12-29 | 5 | 3 | 2 | 2025-12-31 | 2025-12-31 | 1 | 0 | 1 | [20 empty] | 2025-12-31 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11982 | 1474 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F39W18 | 2025-12-16 | 2025-12-29 | 8 | 7 | 1 | 2025-12-29 | 2025-12-30 | 1 | 0 | 1 | [20 empty] | 2025-12-31 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 12009 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-12-30 | 2025-12-31 | 1 | 0 | 1 | 2025-12-31 | 2026-01-05 | 3 | 0 | 3 | [20 empty] | 2026-01-05 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11962 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W11 | 2025-12-09 | 2025-12-15 | 4 | 1 | 3 | 2025-12-15 | 2025-12-16 | 1 | 0 | 1 | [20 empty] | 2026-01-16 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Lunenburg | 11872 | 1462 | 21.3 | 21.3 | 0 | Solar + Energy Storage | Yes | F31W38 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-18 | 2025-11-25 | 6 | 5 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11873 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F50W51 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11888 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-03 | 2025-11-17 | 10 | 9 | 1 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11909 | 1462 | 13.8 | 15 | 0 | Solar + Energy Storage | Yes | F31W37 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-25 | 1 | 0 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11912 | 1420 | 21.4 | 21.4 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-25 | 1 | 0 | 1 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11862 | 1420 | 11.5 | 11.5 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-10-17 | 2025-11-06 | 15 | 10 | 5 | 2025-11-06 | 2025-11-13 | 5 | 2 | 3 | [20 empty] | 2025-11-18 |  |  | NO | Expedited | [8 empty] | 2026-01-21 | In Operation | Res | Y
Fitchburg | Townsend | 11870 | 1474 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W18 | 2025-10-27 | 2025-11-14 | 14 | 8 | 6 | 2025-11-14 | 2025-11-25 | 8 | 4 | 4 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Ashby | 11876 | 1431 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F39W19 | 2025-10-27 | 2025-11-17 | 15 | 9 | 6 | 2025-11-17 | 2025-11-19 | 2 | 0 | 2 | [20 empty] | 2025-11-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11887 | 1462 | 23 | 23 | 0 | Solar + Energy Storage | Yes | F30W30 | 2025-11-17 | 2025-11-26 | 8 | 7 | 1 | 2025-11-26 | 2025-11-26 | 1 | 0 | 1 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11916 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F25W28 | 2025-11-14 | 2025-11-25 | 8 | 6 | 2 | 2025-11-25 | 2025-11-26 | 1 | 0 | 1 | [20 empty] | 2025-12-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11855 | 1462 | 10 | 0 | 0 | Energy Storage | Yes | F30W30 | 2025-10-13 | 2025-10-29 | 12 | 8 | 4 | 2025-10-29 | 2025-11-07 | 8 | 1 | 7 | [20 empty] | 2025-11-12 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11847 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W12 | 2025-10-08 | 2025-10-24 | 12 | 4 | 8 | 2025-10-24 | 2025-11-19 | 18 | 16 | 2 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11843 | 1420 | 3.8 |  |  | Solar + Energy Storage |  | F25W28 | 2025-10-07 | 2025-10-23 | 12 | 5 | 7 | 2025-10-23 | [28 empty] | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11834 | 1420 | 17.6 | 17.6 | 0 | Solar + Energy Storage | Yes | F11W12 | 2025-10-01 | 2025-10-09 | 7 | 4 | 3 | 2025-10-09 | 2025-11-19 | 28 | 21 | 7 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Ashby | 11833 | 1431 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F39W19 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-20 | 27 | 25 | 2 | [20 empty] | 2025-12-02 | 2025-12-29 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11832 | 1420 | 15.7 | 15.7 | 0 | Solar + Energy Storage | Yes | F40W42 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-11-21 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11831 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F01W04 | 2025-10-01 | 2025-10-13 | 8 | 4 | 4 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-11-21 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11829 | 1420 | 100 | 100 | N/A | Solar | No | F11W11 | 2025-09-30 | 2025-10-27 | 19 | 16 | 3 | 2025-10-27 | 2025-11-26 | 22 | 18 | 4 | [23 empty] | YES | Expedited | [9 empty] | Create ISA | Res | Y
Fitchburg | Fitchburg | 11828 | 1420 | 100 | 100 | N/A | Solar | No | F40W39 | 2025-09-30 | 2025-10-24 | 18 | 15 | 3 | 2025-10-24 | 2025-11-26 | 23 | 18 | 5 | [23 empty] | YES | Expedited | [9 empty] | Create ISA | Res | Y
Fitchburg | Fitchburg | 11822 | 1420 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F40W38 | 2025-09-29 | 2025-10-13 | 10 | 5 | 5 | 2025-10-13 | 2025-11-19 | 26 | 22 | 4 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11815 | 1420 | 12.2 | 12.2 | 0 | Solar + Energy Storage | Yes | F40W40 | 2025-09-24 | 2025-10-16 | 16 | 9 | 7 | 2025-10-16 | 2025-11-07 | 17 | 12 | 5 | [20 empty] | 2025-11-12 |  |  | NO | Expedited | [8 empty] | 2026-01-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 11813 | 1420 | 20 | 20 | 0 | Solar + Energy Storage | Yes | F35W36 | 2025-09-23 | 2025-10-16 | 17 | 13 | 4 | 2025-10-16 | 2025-11-19 | 24 | 17 | 7 | [20 empty] | 2025-12-01 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11811 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-23 | 2025-10-14 | 15 | 6 | 9 | 2025-10-14 | [28 empty] | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11803 | 1420 | 15.2 |  |  | Solar |  | F31W34 | 2025-09-22 | 2025-10-01 | 8 | 7 | 1 | 2025-10-01 | 2025-10-02 | 2 | 0 | 2 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11790 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F40W40 | 2025-09-17 | 2025-09-24 | 7 | 6 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11787 | 1462 | 11.5 |  |  | Solar + Energy Storage |  | F30W30 | 2025-09-23 | 2025-10-01 | 11 | 10 | 1 | 2025-10-01 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [8 empty] | 2026-01-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 11783 | 1462 | 20 |  |  | Solar |  | F30W30 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [8 empty] | 2026-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 11780 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-16 | 2025-09-24 | 8 | 7 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11773 | 1420 | 17.6 |  |  | Solar + Energy Storage |  | F40W42 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11772 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F25W27 | 2025-09-12 | 2025-09-24 | 10 | 9 | 1 | 2025-09-24 | 2025-09-30 | 5 | 0 | 5 | [20 empty] | 2025-10-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11759 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | F40W40 | 2025-09-10 | 2025-09-30 | 15 | 10 | 5 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11752 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F22W1 | 2025-09-08 | 2025-10-01 | 18 | 12 | 3 | 2025-10-01 | 2025-10-02 | 1 | 0 | 1 | [20 empty] | 2025-10-13 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11742 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F22W1 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-29 | 4 | 0 | 4 | [20 empty] | 2025-09-29 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11739 | 1462 | 13.8 | 13.8 | 0 | Solar + Energy Storage | Yes | F30W31 | 2025-09-02 | 2025-10-01 | 22 | 16 | 6 | 2025-10-01 | 2025-11-20 | 35 | 31 | 4 | [20 empty] | 2025-12-02 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 11738 | 1474 | 15.7 |  |  | Solar + Energy Storage |  | F39W18 | 2025-09-02 | 2025-09-30 | 21 | 15 | 6 | 2025-09-30 | 2025-10-01 | 1 | 0 | 1 | [20 empty] | 2025-10-01 |  |  | NO | Expedited | [8 empty] | 2025-12-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 11737 | 1420 | 23.8 | 8 | 0 | Solar + Energy Storage | Yes | F01W02 | 2025-09-02 | 2025-09-24 | 17 | 16 | 1 | 2025-09-24 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-10-01 |  |  | No | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11728 | 1420 | 17.6 |  |  | Solar + Energy Storage |  | F11W12 | 2025-08-28 | 2025-09-03 | 4 | 3 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-08 |  |  | NO | Expedited | [8 empty] | 2025-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 11726 | 1420 | 250.8 | 250.8 | N/A | Solar | No | F50W55 | 2025-08-27 | 2025-09-30 | 24 | 14 | 10 | 2025-09-30 | 2025-10-30 | 22 | 0 | 22 | [23 empty] | YES | Expedited | [9 empty] | Supplemental Review | Comm | N
Fitchburg | Fitchburg | 11727 | 1420 | 180.4 | 180.4 | N/A | Solar | No | F50W55 | 2025-08-27 | 2025-10-02 | 26 | 11 | 15 | 2025-10-03 | 2025-10-30 | 19 | 0 | 19 | [23 empty] | YES | Expedited | [9 empty] | Supplemental Review | Comm | N
Fitchburg | Fitchburg | 11722 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | F40W42 | 2025-08-26 | 2025-09-23 | 20 | 16 | 4 | 2025-09-23 | 2025-10-06 | 10 | 7 | 3 | [20 empty] | 2025-10-14 |  |  | YES | Expedited | [9 empty] | Waiting for ISA Signature | Res | Y
Fitchburg | Fitchburg | 11713 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | F22W1 | 2025-08-21 | 2025-09-03 | 9 | 8 | 1 | 2025-09-03 | 2025-09-04 | 2 | 0 | 2 | [20 empty] | 2025-09-23 |  |  | Yes | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11709 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | 25W27 | 2025-08-20 | 2025-08-28 | 8 | 5 | 3 | 2025-08-28 | 2025-08-29 | 1 | 0 | 1 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [8 empty] | 2025-12-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 11700 | 1462 | 17.6 | 17.6 | N/A | Solar | No | 30W31 | 2025-08-18 | 2025-08-28 | 9 | 7 | 2 | 2025-08-28 | 2025-09-04 | 5 | 0 | 5 | [20 empty] | 2025-09-12 | 2025-11-12 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11691 | 1420 | 13.8 |  |  | Solar + Energy Storage |  | F40W40 | 2025-08-27 | 2025-09-23 | 19 | 10 | 9 | 2025-09-23 | 2025-09-25 | 2 | 0 | 2 | [20 empty] | 2025-09-28 |  |  | NO | Expedited | [8 empty] | 2026-01-07 | In Operation | Res | Y
Fitchburg | Townsend | 11677 | 1474 | 15.7 | 12 | 0 | Solar + Energy Storage | Yes | 39W18 | 2025-08-11 | 2025-08-25 | 11 | 7 | 4 | 2025-08-25 | 2025-08-29 | 5 | 2 | 3 | [20 empty] | 2025-09-07 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11676 | 1420 | 13.7 |  |  | Solar + Energy Storage |  | 25W28 | 2025-08-11 | 2025-08-21 | 9 | 2 | 7 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-07 |  |  | NO | Expedited | [8 empty] | 2025-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 11675 | 1420 | 15.7 |  |  | Solar + Energy Storage |  | 11W12 | 2025-08-11 | 2025-08-21 | 10 | 7 | 3 | 2025-08-21 | 2025-08-29 | 7 | 2 | 5 | [20 empty] | 2025-09-08 |  |  | Yes | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11674 | 1462 | 17.6 |  |  | Solar + Energy Storage |  | 31W37 | 2025-08-11 | 2025-08-20 | 8 | 7 | 1 | 2025-08-20 | 2025-08-27 | 6 | 0 | 6 | [20 empty] | 2025-08-27 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11663 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 40W42 | 2025-08-06 | 2025-08-14 | 16 | 10 | 6 | 2025-08-14 | 2025-08-15 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [8 empty] | 2026-01-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 11658 | 1420 | 13.7 |  |  | Solar |  | F25W28 | 2025-08-11 | 2025-09-11 | 24 | 20 | 4 | 2025-09-11 | 2025-09-12 | 1 | 0 | 1 | [20 empty] | 2025-09-22 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11605 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | 31W34 | 2025-07-16 | 2025-07-29 | 10 | 6 | 4 | 2025-08-11 | 2025-08-11 | 0 | 0 | 0 | [20 empty] | 2025-08-14 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11600 | 1420 | 33.1 |  |  | Solar |  | 20W22 | 2025-07-15 | 2025-07-25 | 9 | 7 | 2 | 2025-07-25 | 2025-07-28 | 3 | 0 | 3 | [20 empty] | 2025-07-29 |  |  | NO | Expedited | [8 empty] | 2025-08-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 11578 | 1420 | 16.2 |  |  | Solar |  | 25W27 | 2025-07-09 | 2025-07-22 | 10 | 7 | 3 | 2025-07-22 | 2025-07-25 | 4 | 0 | 4 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11571 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 11W11 | 2025-07-08 | 2025-08-14 | 13 | 9 | 4 | 2025-08-14 | 2025-08-14 | 1 | 0 | 1 | [20 empty] | 2025-08-20 |  |  | NO | Expedited | [8 empty] | 2026-01-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 11554 | 1462 | 17.4 |  |  | Solar |  | 30W30 | 2025-06-27 | 2025-07-23 | 18 | 16 | 2 | 2025-07-23 | 2025-07-24 | 1 | 0 | 1 | [20 empty] | 2025-07-25 |  |  | NO | Expedited | [8 empty] | 2025-12-15 | In Operation | Res | Y
Fitchburg | Ashby | 11539 | 1431 | 990 |  |  | Solar |  | 39W19 | 2025-06-24 | 2025-07-29 | 25 | 22 | 3 | [10 empty] | 2025-07-29 | 2025-08-01 | 3 | 0 | 3 | [14 empty] | Standard | [9 empty] | Cancelled | Comm | N
Fitchburg | Fitchburg | 11527 | 1420 | 996 |  |  | Solar + Energy Storage |  | 40W40 | 2025-06-23 | 2025-06-30 | 5 | 4 | 1 | [10 empty] | 2025-06-30 | 2025-07-09 | 7 | 0 | 7 | [14 empty] | Standard | [9 empty] | On Hold | Comm | N
Fitchburg | West Townsend | 11518 | 1474 | 24.576 |  |  | Solar |  | 39W18 | 2025-07-01 | 2025-07-07 | 3 | 0 | 3 | 2025-07-07 | 2025-07-08 | 1 | 0 | 1 | [20 empty] | 2025-07-16 | 2025-08-18 |  | YES | Expedited | [8 empty] | 2025-12-26 | In Operation | Res | Y
Fitchburg | Ashby | 11517 | 1431 | 20 |  |  | Solar |  | 39W19 | 2025-06-23 | 2025-07-08 | 10 | 6 | 4 | 2025-07-08 | 2025-07-09 | 1 | 0 | 1 | [20 empty] | 2025-07-09 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11513 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 50W56 | 2025-06-13 | 2025-06-24 | 10 | 3 | 7 | 2025-06-24 | 2025-06-26 | 3 | 0 | 3 | [20 empty] | 2025-07-03 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 11496 | 1431 | 23 | 23 | 10 | Solar + Energy Storage | Yes | 40W40 | 2025-06-09 | 2025-06-25 | 15 | 9 | 6 | 2025-06-25 | 2025-07-21 | 18 | 17 | 1 | [20 empty] | 2025-07-21 |  |  | NO | Expedited | [8 empty] | 2026-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 11481 | 1420 | 11.5 |  |  | Solar + Energy Storage |  | 40W40 | 2025-06-02 | 2025-06-16 | 10 | 9 | 1 | 2025-06-16 | 2025-07-07 | 14 | 4 | 10 | [20 empty] | 2025-07-07 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11474 | 1469 | 498 |  |  | Solar |  | 39W18 | 2025-05-29 | 2025-06-05 | 5 | 2 | 3 | [10 empty] | 2025-06-06 | 2025-06-17 | 7 | 0 | 7 | 2025-09-26 | 2026-01-07 | 69 | 0 | 69 | [9 empty] | Standard | [9 empty] | Create ISA | Comm | N
Fitchburg | Lunenburg | 11447 | 1462 | 11.4 |  |  | Solar |  | 31W37 | 2025-05-20 | 2025-06-05 | 22 | 12 | 10 | 2025-06-05 | 2025-06-11 | 5 | 0 | 5 | [20 empty] | 2025-06-14 |  |  | NO | Expedited | [8 empty] | 2025-07-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 11439 | 1462 | 15.2 |  |  | Solar |  | 30W30 | 2025-05-16 | 2025-05-30 | 10 | 8 | 2 | 2025-05-30 | 2025-06-03 | 3 | 0 | 3 | [20 empty] | 2025-06-10 | 2025-08-05 |  | YES | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 11437 | 1420 | 15.4 | 15.4 | N/A | Solar | No | 50W56 | 2025-06-03 | 2025-06-05 | 2 | 1 | 1 | 2025-06-05 | 2025-06-11 | 4 | 0 | 4 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [8 empty] | 2025-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 11351 | 1420 | 49.7 |  |  | Solar |  | 22W1 | 2025-04-18 | 2025-05-12 | 20 | 17 | 3 | 2025-05-12 | 2025-05-13 | 1 | 0 | 1 | [20 empty] | 2025-06-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11344 | 1469 | 11.5 |  |  | Solar + Energy Storage |  | 15W17 | 2025-04-17 | 2025-04-28 | 8 | 7 | 1 | 2025-04-28 | 2025-04-30 | 3 | 0 | 3 | [20 empty] | 2025-05-13 |  |  | NO | Expedited | [8 empty] | 2025-08-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 11336 | 1462 | 11.5 |  |  | Solar + Energy Storage |  | 31W37 | 2025-04-15 | 2025-04-28 | 10 | 5 | 5 | 2025-05-01 | 2025-05-02 | 3 | 0 | 3 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [8 empty] | 2025-10-30 | In Operation | Res | Y
Fitchburg | Townsend | 11328 | 1469 | 10 |  |  | Solar + Energy Storage |  | 39W18 | 2025-04-30 | 2025-05-01 | 1 | 0 | 1 | 2025-05-01 | 2025-05-05 | 4 | 0 | 4 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [8 empty] | 2025-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 11249 | 1420 | 15.2 |  |  | Solar |  | 20W22 | 2025-04-15 | 2025-04-25 | 9 | 4 | 5 | 2025-04-25 | 2025-04-28 | 2 | 0 | 2 | [20 empty] | 2025-04-01 |  |  | NO | Expedited | [8 empty] | 2025-07-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 11240 | 1462 | 38 |  |  | Solar |  | 30W30 | 2025-03-17 | 2025-04-08 | 17 | 5 | 12 | 2025-04-21 | 2025-04-21 | 1 | 0 | 1 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [8 empty] | 2026-01-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 11230 | 1462 | 9 |  |  | Solar + Energy Storage |  | 31W37 | 2025-04-15 | 2025-05-05 | 15 | 8 | 7 | 2025-05-05 | 2025-05-09 | 5 | 0 | 5 | [20 empty] | 2025-05-02 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Lunenburg | 11228 | 1462 | 999 | 999 | 0 | Solar + Energy Storage | Yes | 30W30 | 2025-03-12 | 2025-03-26 | 11 | 10 | 1 | [10 empty] | 2025-03-27 | 2025-03-31 | 3 | 0 | 3 | 2025-07-18 | 2025-10-17 | 64 | 0 | 64 | [9 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N
Fitchburg | Fitchburg | 11216 | 1420 | 15.2 |  |  | Solar |  | 50W55 | 2025-03-10 | 2025-04-17 | 29 | 26 | 3 | 2025-04-17 | 2025-04-28 | 8 | 0 | 8 | [20 empty] | 2025-04-30 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Townsend | 11190 | 1469 | 15.84 |  |  | Solar |  | 15W16 | 2025-03-01 | 2025-03-27 | 19 | 0 | 19 | 2025-03-27 | 2025-03-29 | 1 | 0 | 1 | [20 empty] | 2025-04-16 |  |  | No | Expedited | [8 empty] | 2025-10-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 11176 | 1420 | 4999 | 4999 | 4999 | Energy Storage | Yes | 40W39 | 2025-02-28 | 2025-03-13 | 10 | 9 | 1 | [10 empty] | 2025-03-15 | 2025-03-25 | 7 | 0 | 7 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Fitchburg | 11167 | 1420 | 15.2 |  |  | Solar |  | 01W04 | 2025-03-06 | 2025-03-26 | 14 |  | 14 | 2025-03-27 | 2025-03-31 | 3 |  | 3 | [20 empty] | 2025-04-02 |  |  | NO | Expedited | [8 empty] | 2025-05-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 11163 | 1420 | 9.5 |  |  | Solar |  | 11W11 | 2025-02-20 | 2025-03-10 | 13 | 12 | 1 | 2025-03-11 | 2025-03-11 | 1 | 0 | 1 | [20 empty] | 2025-03-14 |  |  | NO | Expedited | [8 empty] | 2025-07-31 | In Operation | Res | Y
Fitchburg | Ashby | 11154 | 1431 | 20 |  |  | Solar |  | 39W19 | 2025-02-17 | 2025-03-04 | 12 | 11 | 1 | 2025-03-10 | 2025-03-11 | 2 | 0 | 2 | [20 empty] | 2025-03-31 | 2025-05-19 |  | YES | Expedited | [8 empty] | 2025-08-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 11150 | 1462 | 20 |  |  | Solar |  | 30W30 | 2025-02-14 | 2025-03-03 | 12 | 11 | 1 | 2025-03-04 | 2025-03-04 | 1 | 0 | 1 | [20 empty] | 2025-04-16 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 11144 | 1420 | 4000 | 4000 | 4000 | Energy Storage | Yes | 40W39 | 2025-04-22 | 2025-05-14 | 17 | 10 | 7 | [10 empty] | 2025-05-15 | 2025-05-16 | 2 | 0 | 2 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Townsend | 11113 | 1469 | 15.2 |  |  | Solar |  | 15W17 | 2025-02-03 | 2025-02-19 | 13 | 12 | 1 | 2025-02-19 | 2025-02-20 | 2 | 0 | 2 | [20 empty] | 2025-02-26 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Res | Y
Fitchburg | Fitchburg | 11059 | 1420 | 34.6 |  |  | Solar |  | 20W22 | 2025-01-08 | 2025-01-23 | 12 | 9 | 3 | 2025-01-24 | 2025-01-24 | 1 | 0 | 1 | [20 empty] | 2025-01-29 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 11032 | 1462 | 30.72 | 0 | 15.36 | Energy Storage | Yes | 31W38 | 2024-12-26 | 2025-02-10 | 33 | 32 | 1 | 2025-02-18 | 2025-03-13 | 18 | 6 | 12 | [20 empty] | 2025-03-28 | 2025-05-06 |  | YES | Expedited | [9 empty] | Pending COC & Photos | Res | N
Fitchburg | Fitchburg | 10973 | 1420 | 4998 | 4998 | 4998 | Energy Storage | Yes | 40W39 | 2025-04-04 | 2025-04-21 | 11 | 6 | 5 | [10 empty] | 2025-04-30 | 2025-05-02 | 2 | 0 | 2 | 2025-09-22 | [13 empty] | Standard | [9 empty] | Impact Study in Process | Comm | N | Summer Street Substation Group | Study In Process - Preliminary Assesment Stage
Fitchburg | Fitchburg | 10966 | 1420 | 16.13 |  |  | Solar |  | 22W1 | 2024-12-04 | 2024-12-24 | 15 | 14 | 1 | 2025-01-06 | 2025-01-07 | 2 |  | 2 | [20 empty] | 2025-01-17 |  |  | NO | Expedited | [8 empty] | 2025-03-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 10960 | 1420 | 5.76 |  |  | Solar + Energy Storage |  | 01W02 | 2024-12-02 | 2024-12-06 | 5 | 0 | 5 | 2024-12-19 | 2024-12-19 | 1 | 0 | 1 | [20 empty] | 2025-01-02 |  |  | NO | Expedited | [8 empty] | 2025-06-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 10943 | 1420 | 7.72 |  |  | Solar |  | 35W36 | 2024-11-26 | 2024-12-23 | 19 | 14 | 5 | 2024-12-24 | 2025-01-07 | 10 |  | 10 | [20 empty] | 2025-01-28 |  |  | NO | Expedited | [8 empty] | 2025-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 10833 | 1462 | 15.2 |  |  | Solar + Energy Storage |  | 31W37 | 2024-10-28 | 2024-11-21 | 18 | 17 | 1 | 2024-11-22 | 2024-11-26 | 3 |  | 3 | [20 empty] | 2024-12-13 |  |  | NO | Expedited | [8 empty] | 2025-03-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 10724 | 1462 | 10 |  |  | Solar |  | 30W31 | 2024-09-30 | 2024-10-17 | 13 | 4 | 9 | 2024-10-18 | 2024-10-18 | 1 |  | 1 | [20 empty] | 2024-10-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 10673 | 1431 | 34.5 | 0 | 0 | Energy Storage | Yes | 39W19 | 2024-09-17 | 2024-10-23 | 26 | 17 | 9 | 2024-10-24 | 2024-10-25 | 2 | 0 | 2 | [20 empty] | 2024-10-30 |  |  | NO | Expedited | [8 empty] | 2025-06-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 10586 | 1420 | 40 |  |  | Solar |  | 40W39 | 2024-08-28 | 2024-11-05 | 48 | 44 | 4 | 2024-11-06 | 2024-11-07 | 2 | 0 | 2 | [20 empty] | 2024-11-17 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | N
Fitchburg | Fitchburg | 10579 | 1420 | 120 |  |  | Solar |  | 40W39 | 2024-08-27 | 2024-11-06 | 50 | 49 | 1 | 2024-11-13 | 2024-11-14 | 2 |  | 2 | [20 empty] | 2024-12-04 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 10556 | 1462 | 10 |  |  | Solar + Energy Storage |  | 30W31 | 2024-08-22 | 2024-09-17 | 18 | 9 | 9 | 2024-09-18 | 2024-09-18 | 1 |  | 1 | [20 empty] | 2024-09-27 |  |  | NO | Expedited | [8 empty] | 2025-02-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 10460 | 1462 | 33.75 |  |  | Solar + Energy Storage |  | 30W30 | 2024-07-19 | 2024-09-27 | 50 | 47 | 3 | 2024-09-27 | 2024-09-30 | 2 |  | 2 | [20 empty] | 2024-10-17 |  |  | NO | Expedited | [8 empty] | 2025-03-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 10421 | 1420 | 15.51 |  |  | Solar |  | 01W04 | 2024-07-09 | 2024-08-01 | 18 | 16 | 2 | 2024-08-01 | 2024-08-01 | 1 |  | 1 | [20 empty] | 2024-08-12 |  |  | NO | Expedited | [8 empty] | 2024-12-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 10273 | 1420 | 9.8 |  |  | Solar + Energy Storage |  | 25W27 | 2024-05-28 | 2024-07-01 | 25 | 20 | 5 | 2024-07-02 | 2024-07-08 | 4 |  | 4 | [20 empty] | 2024-07-31 |  |  | NO | Expedited | [8 empty] | 2024-12-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 10188 | 1420 | 250 |  |  | Solar |  | 22W1 | 2024-05-07 | 2024-05-13 | 5 | 0 | 5 | 2024-05-14 | 2024-07-30 | 54 | 0 | 54 | [20 empty] | 2024-09-02 | 2025-02-26 |  | YES | Expedited | [9 empty] | Perform Mods | Res | N
Fitchburg | Townsend | 10182 | 1474 | 8.832 |  |  | Solar + Energy Storage |  | 39W18 | 2024-05-06 | 2024-05-20 | 11 | 10 | 1 | 2024-05-21 | 2024-05-21 | 1 |  | 1 | [20 empty] | 2024-05-28 |  |  | NO | Expedited | [8 empty] | 2025-02-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 10133 | 1462 | 11.5 | 6 | 0 | Solar + Energy Storage | Yes | 30W30 | 2024-04-19 | 2024-06-06 | 34 | 32 | 2 | [5 empty] | 2024-07-11 | 2024-07-12 | 2 | 0 | 2 | [15 empty] | 2024-07-26 |  |  | NO | Expedited | [8 empty] | 2025-11-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 10102 | 1420 | 66 |  |  | Solar |  | 31W34 | 2024-04-11 | 2024-04-30 | 13 | 5 | 8 | 2024-05-06 | 2024-06-03 | 20 | 17 | 3 | [20 empty] | 2024-06-24 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | N
Fitchburg | Fitchburg | 10090 | 1420 | 120 |  |  | Solar |  | 50W55 | 2024-04-08 | 2024-05-06 | 20 | 10 | 10 | 2024-05-07 | 2024-05-08 | 2 |  | 2 | [20 empty] | 2024-05-28 |  |  | NO | Expedited | [8 empty] | 2025-05-07 | In Operation | Res | N
Fitchburg | Ashby | 10089 | 1431 | 14.83 |  |  | Solar + Energy Storage |  | 39W19 | 2024-04-08 | 2024-04-18 | 8 | 6 | 2 | 2024-04-19 | 2024-04-19 | 1 |  | 1 | [20 empty] | 2024-05-03 |  |  | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 10055 | 1420 | 80 |  |  | Solar |  | 50W56 | 2024-03-28 | 2024-04-11 | 11 | 7 | 4 | 2024-04-12 | 2024-04-17 | 3 | 0 | 3 | [20 empty] | 2024-04-22 |  |  | NO | Expedited | [8 empty] | 2025-07-23 | In Operation | Comm | Y
Fitchburg | Townsend | 9985 | 1474 | 10 | 10 | 0 | Solar + Energy Storage | Yes | 39W18 | 2024-03-11 | 2024-03-25 | 11 | 10 | 1 | 2024-03-26 | 2024-03-26 | 1 |  | 1 | [20 empty] | 2024-04-02 |  |  | NO | Expedited | [8 empty] | 2024-07-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 9883 | 1420 | 16.13 |  |  | Solar |  | 22W1 | 2024-02-13 | 2024-04-18 | 46 | 39 | 7 | 2024-04-19 | 2024-04-19 | 1 |  | 1 | [20 empty] | 2024-04-25 |  |  | NO | Expedited | [9 empty] | Cancelled
Fitchburg | Lunenburg | 9793 | 1462 | 16.89 |  |  | Solar |  | 30W30 | 2024-01-19 | 2024-02-06 | 13 | 6 | 7 | 2024-02-07 | 2024-02-08 | 2 |  | 2 | [20 empty] | 2024-03-06 | 2024-03-18 |  | YES | Expedited | [8 empty] | 2025-03-18 | In Operation | Res | Y
Fitchburg | Townsend | 9697 | 1469 | 0 |  |  | Energy Storage |  | 15W16 | 2023-12-19 | 2024-02-19 | 41 | 37 | 4 | 2024-02-20 | 2024-04-08 | 35 | 30 | 5 | [20 empty] | 2024-04-11 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 9661 | 1469 | 14.8 |  |  | Solar + Energy Storage |  | 39W18 | 2023-12-07 | 2024-01-28 | 34 | 25 | 9 | 2024-01-29 | 2024-01-29 | 1 |  | 1 | [20 empty] | 2024-02-13 |  |  | NO | Expedited | [8 empty] | 2024-05-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 9582 | 1462 | 6.48 |  |  | Solar + Energy Storage |  | 30W31 | 2023-11-20 | 2024-05-15 | 122 | 120 | 2 | 2024-05-16 | 2024-06-06 | 15 |  | 15 | [20 empty] | 2024-06-24 |  |  | NO | Expedited | [8 empty] | 2024-07-19 | In Operation | Res | Y
Fitchburg | Townsend | 9572 | 1474 | 6 | 6 | 0 | Solar + Energy Storage | Yes | 39W18 | 2023-11-17 | 2023-12-19 | 22 | 16 | 6 | 2023-12-20 | 2023-12-22 | 3 |  | 3 | [20 empty] | 2024-01-04 |  |  | NO | Expedited | [8 empty] | 2024-08-05 | In Operation | Res | Y
Fitchburg | Townsend | 9547 | 1469 | 14.8 |  |  | Solar + Energy Storage |  | 15W16 | 2023-11-13 | 2023-12-14 | 23 | 8 | 15 | 2023-12-15 | 2023-12-18 | 2 |  | 2 | [20 empty] | 2023-12-21 |  |  | NO | Expedited | [8 empty] | 2024-04-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 9480 | 1462 | 15.744 |  |  | Solar |  | 31W38 | 2023-11-02 | 2023-11-14 | 9 | 7 | 2 | 2023-11-15 | 2023-11-15 | 1 |  | 1 | [20 empty] | 2023-11-16 |  |  | NO | Expedited | [8 empty] | 2024-01-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 9438 | 1420 | 18 |  |  | Solar |  | 20W22 | 2023-10-26 | 2023-12-14 | 35 | 28 | 7 | 2023-12-15 | 2023-12-15 | 1 |  | 1 | [20 empty] | 2024-01-10 | 2024-01-30 |  | YES | Expedited | [8 empty] | 2024-04-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 9124 | 1462 | 7.6 |  |  | Solar + Energy Storage |  | 30W30 | 2023-09-25 | 2023-10-31 | 26 | 3 | 23 | 2023-11-01 | 2023-11-03 | 3 | 1 | 2 | [20 empty] | 2023-11-13 |  |  | NO | Expedited | [8 empty] | 2024-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 9097 | 1420 | 43.2 |  |  | Solar |  | 11W11 | 2023-09-08 | 2023-09-26 | 13 | 12 | 1 | 2023-09-27 | 2024-04-12 | 137 | 136 | 1 | [20 empty] | 2024-04-15 |  |  | NO | Expedited | [8 empty] | 2025-08-13 | In Operation | Comm | N
Fitchburg | Lunenburg | 9057 | 1462 | 6.27 |  |  | Solar + Energy Storage |  | 31W37 | 2023-08-30 | 2023-09-19 | 14 | 13 | 1 | 2023-09-20 | 2023-09-27 | 6 |  | 6 | [20 empty] | 2023-10-09 |  |  | NO | Expedited | [8 empty] | 2023-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 7795 | 1420 | 16 |  |  | Solar |  | 20W22 | 2023-07-19 | 2023-08-21 | 24 | 24 | 1 | 2023-08-21 | 2023-08-21 | 1 |  | 1 | [20 empty] | 2023-09-01 |  |  | NO | Expedited | [8 empty] | 2024-05-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 7752 | 1462 | 7.45 | 7.45 | 0 | Solar + Energy Storage | Yes | 30W30 | 2023-08-18 | 2023-09-20 | 23 | 21 | 2 | 2023-09-21 | 2023-09-27 | 5 |  | 5 | [20 empty] | 2023-10-09 |  |  | NO | Expedited | [8 empty] | 2024-03-29 | In Operation | Res | Y
Fitchburg | Townsend | 7702 | 1469 | 3.8 |  |  | Solar + Energy Storage |  | 39W18 | 2023-09-06 | 2023-09-11 | 4 | 3 | 1 | 2023-09-15 | 2023-09-18 | 2 |  | 2 | [20 empty] | 2023-10-03 |  |  |  | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 7521 | 1469 | 180 |  |  | Solar |  | 15W17 | 2023-05-26 | 2023-06-07 | 8 | 7 | 1 | 2023-06-08 | 2023-06-09 | 2 |  | 2 | [20 empty] | 2023-06-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 7519 | 1469 | 100 |  |  | Solar |  | 15W17 | 2023-05-26 | 2023-05-31 | 3 | 3 | 1 | 2023-06-01 | 2023-06-02 | 2 | 0 | 2 | [20 empty] | 2023-06-07 |  |  | NO | Expedited | [9 empty] | Pending COC & Photos | Comm | N
Fitchburg | Fitchburg | 7410 | 1420 | 5 |  |  | Solar |  | 11H10 | 2023-05-08 | 2023-05-26 | 15 | 11 | 4 | 2023-05-30 | 2023-05-30 | 1 |  | 1 | [20 empty] | 2023-06-07 | 2023-07-25 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 7401 | 1420 | 7.5 | 7.5 | 0 | Solar + Energy Storage | Yes | 25W27 | 2023-07-05 | 2023-07-07 | 3 | 2 | 1 | 2023-07-07 | 2023-07-10 | 2 |  | 2 | [20 empty] | 2023-07-17 |  |  | NO | Expedited | [8 empty] | 2024-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 7320 | 1462 | 12.3 |  |  | Solar + Energy Storage |  | 30W31 | 2023-08-10 | 2023-08-17 | 6 | 5 | 1 | 2023-08-18 | 2023-08-21 | 2 |  | 2 | [20 empty] | 2023-09-01 |  |  | NO | Expedited | [8 empty] | 2023-10-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 7278 | 1462 | 15.9 |  |  | Solar |  | 30W30 | 2023-04-14 | 2023-05-12 | 20 | 19 | 1 | 2023-05-13 | 2023-05-19 | 5 |  | 5 | [20 empty] | 2023-05-24 |  |  | NO | Expedited | [8 empty] | 2023-07-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 7194 | 1420 | 4999 |  |  | Solar |  | 25W27 | 2023-03-22 | 2023-03-30 | 7 | 5 | 2 | [10 empty] | 2023-04-01 | 2023-04-18 | 11 |  |  | 2023-06-30 | 2023-11-08 | 91 |  | 91 | [5 empty] | 2024-08-01 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 7182 | 1420 | 15.6 |  |  | Solar |  | 11W11 | 2023-03-21 | 2023-04-13 | 18 | 15 | 3 | 2023-04-14 | 2023-04-24 | 6 |  | 6 | [20 empty] | 2023-05-03 | 2023-09-06 |  | YES | Expedited | [8 empty] | 2023-09-19 | In Operation | Res | Y
Fitchburg | Ashby | 7029 | 1431 | 7.965 |  |  | Solar + Energy Storage |  | 39W19 | 2023-02-08 | 2023-03-08 | 20 | 19 | 1 | 2023-03-09 | 2023-03-09 | 1 |  | 1 | [20 empty] | 2023-03-14 |  |  | NO | Expedited | [8 empty] | 2023-10-31 | In Operation | Res | Y
Fitchburg | Townsend | 6969 | 1469 | 3.8 |  |  | Solar + Energy Storage |  | 15W16 | 2023-01-24 | 2023-03-08 | 29 | 29 | 1 | 2023-03-08 | 2023-03-15 | 4 |  | 4 | [20 empty] | 2023-03-20 |  |  | NO | Expedited | [8 empty] | 2023-03-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 6751 | 1420 | 4999.2 | 4999.2 | 4999.2 | Energy Storage | Yes | 50W55 | 2022-11-17 | 2022-11-29 | 8 | 7 | 1 | [10 empty] | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 2023-02-18 | 2024-08-19 | 374 | 196 | 178 | [5 empty] | 2024-10-25 |  |  | YES | Standard | [9 empty] | Waiting for Mods Fee | Comm | N
Fitchburg | Lunenburg | 6664 | 1462 | 12 |  |  | Solar + Energy Storage |  | 30W30 | 2022-11-02 | 2022-11-08 | 5 | 3 | 2 | 2022-11-09 | 2022-11-17 | 6 | 5 | 1 | [20 empty] | 2022-11-21 |  |  | NO | Expedited | [8 empty] | 2023-06-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 6561 | 1462 | 19 |  |  | Solar |  | 30W30 | 2022-10-07 | 2022-11-07 | 21 | 20 | 1 | 2022-11-08 | 2022-11-08 | 1 |  | 1 | [20 empty] | 2022-11-08 |  |  | NO | Expedited | [8 empty] | 2022-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 6550 | 1462 | 4999 | 4999 | 749.85 | Energy Storage | Yes | 30W30 | 2022-10-06 | 2022-10-20 | 10 | 9 | 1 | [10 empty] | 2022-10-22 | 2022-11-10 | 14 | 0 | 14 | 2023-02-18 | 2024-07-03 | 342 | 75 | 267 | [5 empty] | 2024-10-25 | 2025-10-03 |  | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 6544 | 1420 | 80 |  |  | Solar |  | 50W56 | 2022-10-05 | 2022-10-19 | 10 | 5 | 5 | 2022-10-20 | 2022-10-24 | 3 |  | 3 | [20 empty] | 2022-11-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 6370 | 1431 | 7.6 |  |  | Solar + Energy Storage |  | 39W19 | 2022-08-25 | 2022-09-19 | 17 | 3 | 14 | 2022-09-19 | 2023-01-30 | 85 | 81 | 4 | [20 empty] | 2023-02-02 |  |  | NO | Expedited | [8 empty] | 2023-10-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 6367 | 1462 | 16.128 |  |  | Solar |  | 30W31 | 2022-08-24 | 2022-09-02 | 8 | 3 | 5 | 2022-09-05 | 2022-09-15 | 8 |  | 8 | [20 empty] | 2022-09-21 |  |  | NO | Expedited | [8 empty] | 2023-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 6265 | 1420 | 490 |  |  | Solar |  | 35W36 | 2022-08-02 | 2022-08-16 | 11 | 10 | 1 | 2022-08-17 | 2022-09-13 | 19 | 0 | 19 | 2022-10-13 | 2022-12-09 | 40 | 8 | 32 | [15 empty] | 2022-12-27 | 2024-02-05 |  | YES | Expedited | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 6247 | 1420 | 7.5 |  |  | Solar |  | 01W02 | 2022-07-28 | 2022-08-19 | 17 | 16 | 1 | 2022-08-19 | 2022-08-22 | 2 |  | 2 | [20 empty] | 2022-08-25 |  |  | NO | Expedited | [8 empty] | 2023-01-04 | Not in Service | Res | Y
Fitchburg | Lunenburg | 6224 | 1462 | 4 |  |  | Solar |  | 30W30 | 2022-07-22 | 2022-07-29 | 6 | 5 | 1 | 2022-08-01 | 2022-08-02 | 2 |  | 2 | [20 empty] | 2022-08-03 |  |  | NO | Expedited | [8 empty] | 2022-09-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 6187 | 1420 | 10.03 |  |  | Solar + Energy Storage |  | 35W36 | 2022-07-15 | 2022-09-21 | 48 | 47 | 1 | 2022-09-22 | 2022-09-28 | 5 |  | 5 | [20 empty] | 2022-09-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 6129 | 1420 | 84.6 |  |  | Solar |  | 22W1 | 2022-06-30 | 2022-07-26 | 18 | 16 | 2 | 2022-07-27 | 2022-08-03 | 6 |  | 6 | [20 empty] | 2022-08-11 |  |  | NO | Expedited | [8 empty] | 2023-12-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 6065 | 1462 | 7.6 |  |  | Solar + Energy Storage |  | 31W38 | 2022-06-15 | 2022-09-13 | 63 | 59 | 4 | 2022-09-14 | 2022-12-23 | 69 |  | 69 | [20 empty] | 2022-12-27 |  |  | NO | Expedited | [8 empty] | 2024-01-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 6010 | 1462 | 10 |  |  | Solar |  | 30W31 | 2022-06-02 | 2022-06-07 | 4 | 3 | 1 | 2022-06-08 | 2022-06-08 | 1 |  | 1 | [20 empty] | 2022-06-13 |  |  | NO | Expedited | [8 empty] | 2022-08-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5982 | 1420 | 4.5 |  |  | Solar + Energy Storage |  | 20W22 | 2022-05-26 | 2022-06-15 | 14 | 12 | 2 | 2022-06-15 | 2022-06-29 | 11 | 10 | 1 | [20 empty] | 2022-08-22 |  |  | NO | Expedited | [8 empty] | 2022-09-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 5916 | 1420 | 3.8 |  |  | Solar |  | 11H10 | 2022-05-12 | 2022-05-18 | 5 | 4 | 1 | 2022-05-19 | 2022-05-19 | 1 |  | 1 | [20 empty] | 2022-05-20 |  |  | NO | Expedited | [8 empty] | 2022-07-25 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5914 | 1420 | 2.95 |  |  | Solar |  | 11W12 | 2022-05-12 | 2022-05-18 | 5 | 3 | 2 | 2022-05-19 | 2022-05-19 | 1 |  | 1 | [20 empty] | 2022-05-20 |  |  | NO | Expedited | [8 empty] | 2023-02-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5855 | 1420 | 6 |  |  | Solar |  | 11W12 | 2022-04-29 | 2022-05-05 | 5 | 3 | 2 | 2022-05-05 | 2022-05-05 | 1 |  | 1 | [20 empty] | 2022-05-09 |  |  | NO | Expedited | [8 empty] | 2022-07-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5850 | 1420 | 5.31 |  |  | Solar |  | 11H11 | 2022-04-28 | 2022-05-05 | 6 | 4 | 2 | 2022-05-05 | 2022-05-05 | 1 |  | 1 | [20 empty] | 2022-05-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5817 | 1420 | 10 |  |  | Solar |  | 11W11 | 2022-04-20 | 2022-04-25 | 4 | 2 | 2 | 2022-04-26 | 2022-04-27 | 2 |  | 2 | [20 empty] | 2022-04-29 |  |  | NO | Expedited | [8 empty] | 2022-07-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 5786 | 1420 | 6 |  |  | Solar |  | 11W11 | 2022-04-13 | 2022-04-25 | 8 | 5 | 3 | 2022-04-26 | 2022-04-27 | 2 |  | 2 | [20 empty] | 2022-04-29 |  |  | NO | Expedited | [8 empty] | 2022-07-06 | In Operation | Res | Y
Fitchburg | Ashby | 5781 | 1431 | 10 |  |  | Solar |  | 39W19 | 2022-04-12 | 2022-05-16 | 24 | 20 | 4 | 2022-05-17 | 2022-05-23 | 5 |  | 5 | [20 empty] | 2022-05-25 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5766 | 1420 | 6 |  |  | Solar |  | 40W42 | 2022-04-12 | 2022-04-15 | 4 | 1 | 3 | 2022-04-15 | 2022-04-15 | 1 |  | 1 | [20 empty] | 2022-04-21 |  |  | NO | Expedited | [8 empty] | 2022-06-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5758 | 1420 | 14.16 |  |  | Solar |  | 40W42 | 2022-04-11 | 2022-06-06 | 39 | 34 | 5 | 2022-06-07 | 2022-06-08 | 2 |  | 2 | [20 empty] | 2022-06-14 |  |  | NO | Expedited | [8 empty] | 2023-05-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 5726 | 1420 | 3800 |  |  | Solar |  | 11H10 | 2022-04-04 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5681 | 1469 | 10 |  |  | Solar |  | 15W17 | 2022-03-17 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5680 | 1420 | 8 |  |  | Solar |  | 40W42 | 2022-03-17 | 2022-03-21 | 3 | 3 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-04-25 |  |  | NO | Expedited | [8 empty] | 2022-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5679 | 1420 | 3.8 |  |  | Solar |  | 11W11 | 2022-03-17 | 2022-03-21 | 3 | 3 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-03-28 |  |  | NO | Expedited | [8 empty] | 2022-06-22 | In Operation | Res | Y
Fitchburg | Ashby | 5674 | 1431 | 10 |  |  | Solar |  | 39W19 | 2022-03-16 | 2022-03-21 | 4 | 4 | 1 | 2022-03-22 | 2022-03-22 | 1 |  | 1 | [20 empty] | 2022-04-25 |  |  | NO | Expedited | [8 empty] | 2022-05-26 | In Operation | Res | Y
Fitchburg | Townsend | 5647 | 1469 | 7.6 |  |  | Solar + Energy Storage |  | 15W16 | 2022-03-01 | 2022-04-13 | 32 | 25 | 7 | 2022-04-13 | 2022-04-14 | 2 |  | 2 | [20 empty] | 2022-04-21 | 2022-05-11 |  | YES | Expedited | [8 empty] | 2022-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 5639 | 1420 | 307.52 |  |  | Solar |  | 0 | 2022-02-28 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5616 | 1420 | 6 |  |  | Solar |  | 40W42 | 2022-02-22 | 2022-03-01 | 6 | 6 | 1 | 2022-03-02 | 2022-03-02 | 1 |  | 1 | [20 empty] | 2022-03-07 |  |  | NO | Expedited | [8 empty] | 2022-09-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 5604 | 1462 | 7.6 |  |  | Solar + Energy Storage |  | 30W30 | 2022-02-17 | 2022-03-11 | 16 | 16 | 1 | 2022-03-11 | 2022-03-24 | 10 | 9 | 1 | [20 empty] | 2022-03-28 | 2022-04-12 |  | YES | Expedited | [8 empty] | 2022-04-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5583 | 1420 | 6 |  |  | Solar |  | 40W42 | 2022-02-10 | 2022-02-16 | 5 | 4 | 1 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-22 |  |  | NO | Expedited | [8 empty] | 2022-05-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5582 | 1420 | 3.8 |  |  | Solar |  | 11W11 | 2022-02-10 | 2022-02-16 | 5 | 4 | 1 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 5574 | 1420 | 3.8 |  |  | Solar |  | 11W11 | 2022-02-09 | 2022-02-11 | 3 | 2 | 1 | 2022-02-14 | 2022-02-14 | 1 |  | 1 | [20 empty] | 2022-02-17 |  |  | NO | Expedited | [8 empty] | 2022-06-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 5573 | 1420 | 3.8 |  |  | Solar |  | 40W42 | 2022-02-09 | 2022-02-14 | 4 | 2 | 2 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5572 | 1420 | 3.8 |  |  | Solar |  | 11W11 | 2022-02-09 | 2022-02-24 | 11 | 8 | 3 | 2022-02-24 | 2022-02-24 | 1 |  | 1 | [20 empty] | 2022-03-17 |  |  | NO | Expedited | [8 empty] | 2022-06-24 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5547 | 1420 | 150 |  |  | Solar |  | 50W51 | 2022-02-01 | 2022-02-09 | 7 | 2 | 5 | 2022-02-10 | 2022-05-19 | 69 | 63 | 6 | [20 empty] | 2022-05-25 | 2023-09-25 | 2026-01-05 | YES | Expedited | [9 empty] | Perform Mods | Comm | N
Fitchburg | Fitchburg | 5525 | 1420 | 6 |  |  | Solar |  | 11W11 | 2022-01-24 | 2022-02-03 | 9 | 7 | 2 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2022-06-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5523 | 1420 | 5 |  |  | Solar |  | 11H11 | 2022-01-24 | 2022-02-03 | 9 | 7 | 2 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5521 | 1469 | 8.56 | 8.56 | 5.7 | Solar + Energy Storage | Yes | 39W18 | 2022-01-24 | 2022-03-01 | 26 | 24 | 2 | 2022-03-01 | 2022-03-02 | 2 |  | 2 | [20 empty] | 2022-03-07 |  |  | NO | Expedited | [8 empty] | 2022-05-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5516 | 1420 | 302.87 |  |  | Solar |  | 0 | 2022-01-21 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5492 | 1420 | 3.8 |  |  | Solar |  | 11W12 | 2022-01-06 | 2022-01-19 | 9 | 8 | 1 | 2022-01-20 | 2022-01-24 | 3 |  | 3 | [20 empty] | 2022-01-27 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 5486 | 1462 | 11.4 |  |  | Solar + Energy Storage |  | 30W30 | 2022-01-05 | 2022-02-11 | 27 | 25 | 2 | 2022-02-14 | 2022-02-21 | 5 |  | 5 | [20 empty] | 2022-03-02 | 2022-03-09 |  | YES | Expedited | [8 empty] | 2022-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5457 | 1420 | 6.5 |  |  | Solar |  | 35W36 | 2021-12-22 | 2022-02-03 | 31 | 27 | 4 | 2022-02-04 | 2022-02-07 | 2 |  | 2 | [20 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2023-04-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5453 | 1420 | 6 |  |  | Solar |  | 11H10 | 2021-12-21 | 2022-01-10 | 15 | 10 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5452 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-12-21 | 2022-01-10 | 15 | 10 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-07-11 | In Operation | Res | Y
Fitchburg | Ashby | 5449 | 1431 | 9.8 |  |  | Solar |  | 39W19 | 2021-12-20 | 2022-01-10 | 16 | 11 | 5 | 2022-01-11 | 2022-01-11 | 1 |  | 1 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-06-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5442 | 1420 | 100 |  |  | Solar |  | 50W56 | 2021-12-17 | 2022-01-04 | 13 | 10 | 3 | 2022-01-04 | 2022-05-19 | 95 | 94 | 1 | [20 empty] | 2022-05-25 | 2023-02-27 | 2026-01-05 | YES | Expedited | [8 empty] | 2025-12-16 | In Operation | Comm | N
Fitchburg | Fitchburg | 5441 | 1420 | 250 |  |  | Solar |  | 0 | 2021-12-17 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5438 | 1420 | 100 |  |  | Solar |  | 50W51 | 2021-12-15 | 2022-01-24 | 28 | 23 | 5 | 2022-01-25 | 2022-05-19 | 81 | 62 | 19 | [20 empty] | 2022-05-25 | 2023-09-25 | 2026-12-01 | YES | Expedited | [8 empty] | 2025-12-16 | In Operation | Comm | N
Fitchburg | Fitchburg | 5420 | 1420 | 6 |  |  | Solar |  | 25W27 | 2021-12-09 | 2021-12-14 | 4 | 3 | 1 | 2021-12-15 | 2021-12-15 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5416 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2021-12-08 | 2022-02-11 | 47 | 46 | 1 | 2022-02-14 | 2022-02-14 | 1 |  | 1 | [20 empty] | 2022-03-02 |  |  | NO | Expedited | [8 empty] | 2022-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5415 | 1420 | 6 |  |  | Solar |  | 40W42 | 2021-12-08 | 2022-02-16 | 50 | 47 | 3 | 2022-02-17 | 2022-02-17 | 1 |  | 1 | [20 empty] | 2022-02-24 |  |  | NO | Expedited | [8 empty] | 2022-05-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 5413 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-12-08 | 2021-12-13 | 4 | 3 | 1 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 | 2022-01-05 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5412 | 1431 | 10 |  |  | Solar |  | 0 | 2021-12-08 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5409 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-12-07 | 2021-12-13 | 5 | 3 | 2 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [8 empty] | 2022-03-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 5408 | 1420 | 6 |  |  | Solar |  | 40W42 | 2021-12-07 | 2021-12-14 | 6 | 5 | 1 | 2021-12-15 | 2021-12-15 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 5405 | 1462 | 11.4 |  |  | Solar |  | 31W38 | 2021-12-07 | 2021-12-17 | 9 | 8 | 1 | 2021-12-20 | 2021-12-21 | 2 |  | 2 | [20 empty] | 2021-12-30 | 2022-01-25 |  | YES | Expedited | [8 empty] | 2022-02-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 5395 | 1420 | 230 |  |  | Solar |  | 22W1 | 2021-12-03 | 2021-12-22 | 14 | 13 | 1 | 2021-12-23 | 2022-01-11 | 14 |  | 14 | 2022-01-26 | 2022-01-28 | 3 |  | 3 | [15 empty] | 2022-02-03 | 2022-03-01 |  | YES | Expedited | [8 empty] | 2023-07-17 | In Operation | Res | Y
Fitchburg | Townsend | 5388 | 1469 | 9.44 |  |  | Solar |  | 15W16 | 2021-12-02 | 2021-12-08 | 5 | 4 | 1 | 2021-12-09 | 2021-12-14 | 4 |  | 4 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5378 | 1469 | 2.88 |  |  | Solar |  | 15W16 | 2021-11-29 | 2021-12-07 | 7 | 1 | 6 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5358 | 1420 | 9.92 |  |  | Solar + Energy Storage |  | 0 | 2021-11-19 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5350 | 1420 | 8 |  |  | Solar |  | 25W27 | 2021-11-17 | 2021-12-07 | 14 | 5 | 9 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5343 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2021-11-16 | 2021-12-07 | 15 | 5 | 10 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5320 | 1420 | 9.8 |  |  | Solar |  | 11W11 | 2021-11-23 | 2021-11-29 | 4 | 3 | 1 | 2021-11-29 | 2021-11-29 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [8 empty] | 2022-06-09 | In Operation | Res | Y
Fitchburg | Ashby | 5318 | 1431 | 8.1 |  |  | Energy Storage |  | 39W19 | 2021-11-11 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5308 | 1420 | 5.02 |  |  | Solar |  | 25W27 | 2021-11-09 | 2021-12-20 | 28 | 27 | 1 | 2021-12-21 | 2021-12-21 | 1 |  | 1 | [20 empty] | 2021-12-23 |  |  | NO | Expedited | [8 empty] | 2023-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5293 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-11-04 | 2021-11-09 | 4 | 3 | 1 | 2021-11-10 | 2021-12-15 | 24 | 23 | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-03-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 5290 | 1420 | 6 |  |  | Solar |  | 25W28 | 2021-11-04 | 2021-12-09 | 24 | 5 | 19 | 2021-12-10 | 2021-12-10 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5289 | 1469 | 6 |  |  | Solar |  | 39W18 | 2021-11-04 | 2021-12-07 | 22 | 3 | 19 | 2021-12-08 | 2021-12-09 | 2 |  | 2 | [20 empty] | 2021-12-16 | 2022-03-01 |  | YES | Expedited | [8 empty] | 2022-03-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5288 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2021-11-03 | 2021-12-27 | 37 | 32 | 5 | 2021-12-28 | [24 empty] | 2022-01-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5287 | 1469 | 5 |  |  | Solar |  | 15W16 | 2021-11-09 | 2021-11-19 | 8 | 7 | 1 | 2021-11-19 | 2021-11-22 | 2 |  | 2 | [20 empty] | 2021-11-30 |  |  | NO | Expedited | [8 empty] | 2022-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5286 | 1420 | 9.8 |  |  | Solar |  | 11W11 | 2021-11-03 | 2021-12-12 | 26 | 6 | 20 | 2021-12-13 | 2022-01-06 | 19 |  | 19 | [20 empty] | 2022-01-20 | 2022-04-12 |  | YES | Expedited | [8 empty] | 2022-09-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5283 | 1420 | 7.08 |  |  | Solar |  | 11W11 | 2021-11-03 | 2021-12-08 | 24 | 4 | 20 | 2021-12-09 | 2021-12-09 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-04-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5278 | 1420 | 6 |  |  | Solar |  | 25W27 | 2021-11-01 | 2021-11-24 | 17 | 16 | 1 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-02-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 5276 | 1420 | 9.8 |  |  | Solar |  | 11W11 | 2021-11-01 | 2021-11-22 | 15 | 12 | 3 | 2021-11-22 | 2021-11-22 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 5271 | 1462 | 10 |  |  | Solar |  | 30W31 | 2021-10-28 | 2021-11-15 | 12 | 7 | 5 | 2021-11-18 | 2022-01-11 | 38 |  | 38 | [20 empty] | 2022-01-14 |  |  | NO | Expedited | [8 empty] | 2022-02-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 5270 | 1420 | 3.8 |  |  | Solar |  | 25W28 | 2021-10-27 | 2021-11-08 | 9 | 5 | 4 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5269 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-10-27 | 2021-11-04 | 7 | 6 | 1 | 2021-11-05 | 2021-11-05 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5268 | 1420 | 3.8 |  |  | Solar |  | 40W42 | 2021-01-03 | 2021-11-18 | 222 | 221 | 1 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 5267 | 1474 | 3.8 |  |  | Solar |  | 39W18 | 2021-11-18 | 2021-12-01 | 9 | 8 | 1 | 2021-12-01 | 2021-12-01 | 1 |  | 1 | [20 empty] | 2021-12-09 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5257 | 1420 | 8.5 |  |  | Solar |  | 40W42 | 2021-10-26 | 2021-11-24 | 21 | 5 | 16 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-06 |  |  | NO | Expedited | [8 empty] | 2022-03-07 | In Operation | Res | Y
Fitchburg | Ashby | 5249 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-10-21 | 2021-11-23 | 23 | 7 | 16 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5244 | 1420 | 9.8 |  |  | Solar |  | 25W28 | 2021-10-20 | 2021-12-13 | 37 | 34 | 3 | 2021-12-14 | 2021-12-15 | 2 |  | 2 | [20 empty] | 2021-12-17 |  |  | NO | Expedited | [8 empty] | 2022-05-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5240 | 1420 | 5.9 |  |  | Solar |  | 31W37 | 2021-10-18 | 2022-01-03 | 54 | 50 | 4 | 2022-01-04 | 2022-01-04 | 1 |  | 1 | [20 empty] | 2022-01-10 |  |  | NO | Expedited | [8 empty] | 2022-02-15 | In Operation | Res | Y
Fitchburg | Townsend | 5232 | 1469 | 10.03 |  |  | Solar |  | 15W16 | 2021-10-26 | 2021-11-17 | 16 | 1 | 15 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [8 empty] | 2012-12-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5221 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2021-10-13 | 2021-10-26 | 10 | 6 | 4 | 2021-10-27 | 2021-10-27 | 1 |  | 1 | [20 empty] | 2021-10-28 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5216 | 1420 | 123 |  |  | Solar |  | 0 | 2021-10-12 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 5215 | 1420 | 8.8 |  |  | Solar |  | 20W22 | 2021-10-18 | 2021-10-27 | 8 | 6 | 2 | 2021-10-28 | 2021-11-15 | 12 |  | 12 | [20 empty] | 2021-11-18 |  |  | NO | Expedited | [8 empty] | 2022-08-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 5213 | 1462 | 10.03 |  |  | Solar |  | 30W31 | 2021-10-11 | 2021-10-14 | 3 | 2 | 1 | 2021-10-19 | 2021-10-20 | 2 |  | 2 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5212 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2021-10-28 | 2021-11-17 | 14 | 13 | 1 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [8 empty] | 2021-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5209 | 1420 | 4 |  |  | Solar |  | 25W27 | 2021-10-08 | 2021-11-14 | 24 | 7 | 17 | 2021-11-15 | 2021-11-15 | 1 |  | 1 | [20 empty] | 2021-11-16 |  |  | NO | Expedited | [8 empty] | 2022-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5203 | 1420 | 7998 |  |  | Energy Storage |  | 40W42 | 2021-10-05 | 2021-10-18 | 9 | 8 | 1 | [10 empty] | 2021-10-20 | [17 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Ashby | 5201 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-10-05 | 2021-10-19 | 10 | 9 | 1 | 2021-10-20 | 2021-10-20 | 1 |  | 1 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5199 | 1469 | 8 |  |  | Solar |  | 39W18 | 2021-10-04 | 2021-11-16 | 30 | 6 | 24 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5193 | 1420 | 8 |  |  | Solar |  | 50W51 | 2021-10-01 | 2021-10-28 | 19 | 5 | 14 | 2021-10-29 | 2021-11-02 | 3 |  | 3 | [20 empty] | 2021-11-04 |  |  | NO | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5192 | 1420 | 6 |  |  | Solar |  | 01W02 | 2021-10-01 | 2021-11-16 | 31 | 7 | 24 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-18 |  |  | NO | Expedited | [8 empty] | 2021-12-09 | In Operation | Res | Y
Fitchburg | Townsend | 5180 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2021-09-28 | 2021-10-18 | 14 | 13 | 1 | 2021-10-19 | 2021-11-15 | 19 |  | 19 | [20 empty] | 2021-11-17 | 2021-11-23 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5169 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2021-09-22 | 2021-09-27 | 4 |  | 4 | 2021-09-28 | 2021-09-29 | 2 |  | 2 | [20 empty] | 2021-09-30 | 2021-10-18 |  | YES | Expedited | [8 empty] | 2021-01-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 5168 | 1420 | 7.6 |  |  | Solar |  | 50W56 | 2021-09-22 | 2021-10-08 | 13 | 12 | 1 | 2021-10-11 | 2021-10-13 | 2 |  | 2 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5167 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-09-22 | 2021-10-07 | 12 | 11 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2022-01-12 | In Operation | Res | Y
Fitchburg | Ashby | 5164 | 1431 | 6 |  |  | Solar |  | 39W19 | 2021-09-21 | 2021-10-07 | 13 | 12 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2021-11-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5155 | 1420 | 6 |  |  | Solar |  | 40W42 | 2021-09-17 | 2021-10-07 | 15 | 14 | 1 | 2021-10-08 | 2021-10-13 | 3 |  | 3 | [20 empty] | 2021-10-18 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 5145 | 1462 | 9.8 |  |  | Solar |  | 31W38 | 2021-09-15 | 2021-10-18 | 23 | 19 | 4 | 2021-10-19 | 2021-10-20 | 2 |  | 2 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5144 | 1420 | 6 |  |  | Solar |  | 50W51 | 2021-09-15 | 2021-11-23 | 48 | 5 | 43 | 2021-11-24 | 2021-11-24 | 1 |  | 1 | [20 empty] | 2021-12-07 | 2021-12-14 |  | YES | Expedited | [8 empty] | 2022-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 5135 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2021-09-22 | 2021-09-22 | 1 |  | 1 | 2021-09-23 | 2021-09-23 | 1 |  | 1 | [20 empty] | 2021-09-24 | 2021-10-01 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5133 | 1420 | 9.15 |  |  | Solar |  | 20W22 | 2021-09-13 | 2021-09-14 | 2 |  | 2 | 2021-09-15 | 2021-09-22 | 6 |  | 6 | [20 empty] | 2021-09-24 |  |  | NO | Expedited | [8 empty] | 2021-12-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 5126 | 1420 | 5 |  |  | Solar |  | 11W11 | 2021-09-21 | 2021-10-25 | 24 |  | 24 | 2021-10-26 | 2021-10-26 | 1 |  | 1 | [20 empty] | 2021-10-28 | 2021-11-23 |  | YES | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 5118 | 1462 | 9 |  |  | Solar + Energy Storage |  | 30W31 | 2021-10-20 | 2021-11-04 | 12 | 4 | 8 | 2021-11-05 | 2022-02-08 | [23 empty] | 2022-02-15 |  |  | NO | Expedited | [8 empty] | 2023-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 5114 | 1420 | 9.735 |  |  | Solar |  | 01W02 | 2021-09-03 | 2021-09-08 | 3 |  | 3 | 2021-09-09 | 2021-09-09 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2021-10-27 |  | YES | Expedited | [8 empty] | 2022-03-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 5112 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2021-09-01 | 2021-10-19 | 33 | 29 | 4 | 2021-10-20 | 2021-10-20 | 1 |  | 1 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [8 empty] | 2022-01-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5111 | 1420 | 6 |  |  | Solar |  | 25W28 | 2021-09-01 | 2021-09-15 | 10 | 5 | 5 | 2021-09-16 | 2021-09-20 | 3 |  | 3 | [20 empty] | 2021-09-24 |  |  | NO | Expedited | [8 empty] | 2021-12-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5105 | 1420 | 3.8 |  |  | Solar |  | 20W22 | 2021-08-31 | 2021-09-27 | 19 | 7 | 12 | 2021-09-28 | 2021-09-29 | 2 |  | 2 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5104 | 1420 | 4 |  |  | Solar |  | 01W04 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 |  |  | NO | Expedited | [8 empty] | 2022-04-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 5103 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2021-12-09 |  | YES | Expedited | [8 empty] | 2021-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 5102 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2021-08-31 | 2021-09-16 | 12 |  | 12 | 2021-09-17 | 2021-10-13 | 18 |  | 18 | [20 empty] | 2021-10-18 | 2022-03-22 |  | YES | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5101 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-08-30 | 2021-09-16 | 13 | 8 | 5 | 2021-09-17 | 2021-09-17 | 1 |  | 1 | [20 empty] | 2021-09-23 | 2022-02-01 |  | YES | Expedited | [8 empty] | 2021-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 5097 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-08-30 | 2021-09-23 | 18 |  | 18 | 2021-09-24 | 2021-09-28 | 3 |  | 3 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [8 empty] | 2022-02-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 5096 | 1462 | 7.25 |  |  | Solar |  | 31W37 | 2021-10-22 | 2021-10-27 | 4 |  | 4 | 2021-11-17 | 2021-11-18 | 2 |  | 2 | [20 empty] | 2021-11-19 | 2021-12-06 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 5095 | 1462 | 10.29 |  |  | Solar |  | 31W37 | 2021-08-29 | 2021-09-30 | 23 | 3 | 20 | 2021-10-01 | 2021-10-01 | 1 |  | 1 | [20 empty] | 2021-10-01 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5088 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2021-08-25 | 2021-08-30 | 4 |  | 4 | 2021-08-31 | 2021-09-09 | 7 |  | 7 | [20 empty] | 2021-09-09 |  |  | NO | Expedited | [8 empty] | 2021-12-09 | Cancelled | Res | Y
Fitchburg | Fitchburg | 5082 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-08-30 | 2021-11-08 | 49 | 10 | 39 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-12-16 |  |  | NO | Expedited | [8 empty] | 2022-10-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 5077 | 1420 | 7.6 |  |  | Solar |  | 11W12 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5076 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5075 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-08-19 | 2021-08-27 | 7 | 4 | 3 | 2021-08-27 | 2021-08-30 | 2 |  | 2 | [20 empty] | 2021-09-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5073 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-08-19 | 2021-09-13 | 17 | 6 | 11 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-17 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 5072 | 1420 | 10.03 |  |  | Solar |  | 31W37 | 2021-08-19 | 2021-09-01 | 10 | 6 | 4 | 2021-09-02 | 2021-09-02 | 1 |  | 1 | [20 empty] | 2021-09-02 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 5065 | 1420 | 8.3 |  |  | Solar |  | 11W11 | 2021-08-18 | 2021-11-30 | 71 | 66 | 5 | 2021-12-01 | 2021-12-01 | 1 |  | 1 | [20 empty] | 2021-12-07 |  |  | NO | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 5064 | 1420 | 9.8 |  |  | Solar |  | 50W51 | 2021-08-18 | 2021-10-06 | 35 |  | 35 | 2021-10-07 | 2021-10-19 | 8 |  | 8 | [20 empty] | 2021-10-26 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 5056 | 1469 | 10 |  |  | Solar |  | 15W16 | 2021-08-16 | 2021-09-01 | 13 | 9 | 4 | 2021-09-02 | 2021-09-02 | 1 |  | 1 | [20 empty] | 2021-09-02 | 2021-10-12 |  | YES | Expedited | [8 empty] | 2021-11-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 5049 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-08-09 | 2021-08-19 | 9 | 5 | 4 | 2021-08-20 | 2021-08-23 | 2 |  | 2 | [20 empty] | 2021-09-30 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 5046 | 1431 | 6 |  |  | Solar |  | 39W19 | 2021-08-09 | 2021-08-17 | 7 | 5 | 2 | 2021-08-18 | 2021-08-18 | 1 |  | 1 | [20 empty] | 2021-08-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5045 | 1420 | 6 |  |  | Solar |  | 25W27 | 2021-08-09 | 2021-08-17 | 7 | 5 | 2 | 2021-08-18 | 2021-08-18 | 1 |  | 1 | [20 empty] | 2021-08-25 | 2022-04-08 |  | YES | Expedited | [8 empty] | 2022-04-12 | Cancelled | Res | Y
Fitchburg | Lunenburg | 5040 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2021-08-31 | 2021-09-14 | 10 |  | 10 | 2021-09-14 | 2021-09-14 | 1 |  | 1 | [20 empty] | 2021-09-21 | 2021-09-27 |  | YES | Expedited | [8 empty] | 2022-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 5038 | 1462 | 10.03 |  |  | Solar |  | 30W30 | 2021-08-06 | 2021-08-13 | 6 | 1 | 5 | 2021-08-14 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 | 2022-04-13 |  | YES | Expedited | [8 empty] | 2022-08-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 5037 | 1420 | 6 |  |  | Solar |  | 25W28 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-06-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 5036 | 1420 | 6 |  |  | Solar |  | 01W02 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 5035 | 1420 | 9.8 |  |  | Solar |  | 01W02 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 | 2022-03-25 |  | YES | Expedited | [8 empty] | 2021-04-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 5034 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-01-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 5033 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-08-06 | 2021-08-14 | 6 | 1 | 5 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-02-07 | In Operation | Res | Y
Fitchburg | Ashby | 5030 | 1431 | 5 |  |  | Solar |  | 39W19 | 2021-08-05 | 2021-08-11 | 5 | 2 | 3 | 2021-08-12 | 2021-08-23 | 8 |  | 8 | [20 empty] | 2021-08-25 |  |  | NO | Expedited | [8 empty] | 2021-11-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5029 | 1420 | 4.5 |  |  | Solar |  | 01W01 | 2021-08-05 | 2021-08-12 | 6 | 2 | 4 | 2021-08-13 | 2021-08-16 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5028 | 1420 | 2.75 |  |  | Solar |  | 01W04 | 2021-08-05 | 2021-08-14 | 7 | 4 | 3 | 2021-08-15 | 2021-08-16 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2022-08-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 5018 | 1420 | 5.75 |  |  | Solar |  | 35W36 | 2021-08-02 | 2021-11-04 | 67 |  | 67 | 2021-11-05 | 2021-11-05 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5017 | 1420 | 5.5 |  |  | Solar |  | 31W37 | 2021-10-27 | 2021-11-08 | 9 |  | 9 | 2021-11-09 | 2021-11-09 | 1 |  | 1 | [20 empty] | 2021-11-10 |  |  | NO | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 5011 | 1420 | 10.4 |  |  | Solar |  | 11W11 | 2021-07-29 | 2021-08-11 | 10 | 8 | 2 | 2021-08-12 | 2021-08-17 | 4 | 1 | 3 | [20 empty] | 2021-08-23 |  |  | NO | Expedited | [8 empty] | 2021-11-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 5007 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-09 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5006 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-09 | 5 |  | 5 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 5005 | 1420 | 9.8 |  |  | Solar |  | 11W12 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2022-04-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 5004 | 1420 | 3.8 |  |  | Solar |  | 11W12 | 2021-07-28 | 2021-08-03 | 5 | 4 | 1 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2022-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 5003 | 1420 | 3.8 |  |  | Solar |  | 01W02 | 2021-07-28 | 2021-08-02 | 4 | 2 | 2 | 2021-08-26 | 2021-09-01 | 5 |  | 5 | [20 empty] | 2021-09-02 |  |  | NO | Expedited | [8 empty] | 2021-12-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4998 | 1420 | 10 |  |  | Solar |  | 50W51 | 2021-07-27 | 2021-08-04 | 7 | 3 | 4 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4996 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2021-07-27 | 2021-08-02 | 5 | 3 | 2 | 2021-08-03 | 2021-08-04 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4994 | 1420 | 3.8 |  |  | Solar |  | 40W42 | 2021-07-27 | 2021-10-28 | 66 |  | 66 | 2021-10-29 | 2021-11-02 | 3 |  | 3 | [20 empty] | 2021-11-04 |  |  | NO | Expedited | [8 empty] | 2022-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4993 | 1420 | 7.68 |  |  | Solar + Energy Storage |  | 01W04 | 2021-07-27 | 2021-12-27 | 106 | 104 | 2 | 2021-12-28 | 2021-12-28 | 1 |  | 1 | [20 empty] | 2022-01-07 |  |  | NO | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Townsend | 4992 | 1469 | 3.8 |  |  | Solar |  | 39W18 | 2021-07-27 | 2021-08-04 | 7 | 5 | 2 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 | 2021-08-27 |  | YES | Expedited | [8 empty] | 2021-11-22 | In Operation | Res | Y
Fitchburg | Ashby | 4991 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2021-07-27 | 2021-07-29 | 3 | 2 | 1 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-02 | 2021-08-06 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4982 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2021-07-22 | 2021-07-29 | 6 | 5 | 1 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4981 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2021-07-22 | 2021-07-29 | 6 | 4 | 2 | 2021-07-29 | 2021-07-29 | 1 |  | 1 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2022-09-12 | In Operation | Res | Y
Fitchburg | Townsend | 4969 | 1469 | 10 |  |  | Solar |  | 30W31 | 2021-07-16 | 2021-07-27 | 8 | 7 | 1 | 2021-07-28 | 2021-07-28 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Ashby | 4965 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-07-16 | 2021-07-21 | 4 | 3 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 |  |  | NO | Expedited | [8 empty] | 2022-03-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 4960 | 1420 | 5 |  |  | Solar |  | 25W28 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-02 |  | YES | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4959 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-02 |  | YES | Expedited | [8 empty] | 2021-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4958 | 1420 | 10 |  |  | Solar |  | 25W28 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 | 2021-08-26 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4957 | 1420 | 7.25 |  |  | Solar |  | 01W02 | 2021-07-15 | 2021-07-21 | 5 | 4 | 1 | 2021-07-22 | 2021-07-22 | 1 |  | 1 | [20 empty] | 2021-07-28 |  |  | NO | Expedited | [8 empty] | 2021-10-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4953 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2021-07-13 | 2021-07-29 | 13 | 11 | 2 | 2021-07-30 | 2021-07-30 | 1 |  | 1 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4939 | 1420 | 9.8 |  |  | Solar |  | 11H10 | 2021-07-08 | 2021-08-09 | 23 |  | 23 | 2021-08-10 | 2021-08-23 | 10 |  | 10 | [20 empty] | 2021-08-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4938 | 1474 | 10 |  |  | Solar |  | 39W18 | 2021-07-08 | 2021-07-13 | 4 | 3 | 1 | 2021-07-13 | 2021-07-14 | 2 |  | 2 | [20 empty] | 2021-07-20 | 2021-07-22 |  | YES | Expedited | [8 empty] | 2022-01-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4937 | 1462 | 8.85 |  |  | Solar |  | 30W30 | 2021-07-08 | 2021-07-13 | 4 | 3 | 1 | 2021-07-13 | 2021-07-14 | 2 |  | 2 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [8 empty] | 2021-08-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4929 | 1420 | 10 |  |  | Solar |  | 11W11 | 2021-07-01 | 2021-07-28 | 20 | 18 | 2 | 2021-07-28 | 2021-07-28 | 1 |  | 1 | [20 empty] | 2021-08-02 |  |  | NO | Expedited | [8 empty] | 2021-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4918 | 1420 | 8.8 |  |  | Solar |  | 40W42 | 2021-06-29 | 2021-07-08 | 8 | 6 | 2 | 2021-07-09 | 2021-07-09 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4909 | 1420 | 7.6 |  |  | Solar |  | 25W28 | 2021-06-25 | 2021-07-02 | 6 | 3 | 3 | 2021-07-02 | 2021-07-02 | 1 |  | 1 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2021-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4905 | 1420 | 9.8 |  |  | Solar |  | 20W22 | 2021-06-23 | 2021-07-08 | 12 | 10 | 2 | 2021-07-09 | 2021-07-09 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-11-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4903 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2021-06-23 | 2021-07-01 | 7 | 4 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4902 | 1420 | 5.5 |  |  | Solar |  | 25W27 | 2021-06-23 | 2021-07-02 | 8 | 4 | 4 | 2021-07-02 | 2021-07-02 | 1 |  | 1 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4901 | 1420 | 7.5 |  |  | Solar |  | 25W27 | 2021-06-23 | 2021-07-20 | 20 | 17 | 3 | 2021-07-21 | 2021-07-21 | 1 |  | 1 | [20 empty] | 2021-07-26 |  |  | NO | Expedited | [8 empty] | 2022-03-03 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4899 | 1420 | 6 |  |  | Solar |  | 25W27 | 2021-06-23 | 2021-07-01 | 7 | 4 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-10-29 | In Operation | Res | Y
Fitchburg | West Townsend | 4898 | 1474 | 7.6 |  |  | Solar |  | 39W18 | 2021-06-22 | 2021-06-30 | 7 | 3 | 4 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-10-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4897 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2021-06-22 | 2021-07-01 | 8 | 5 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4896 | 1462 | 5.75 |  |  | Solar |  | 30W31 | 2021-06-22 | 2021-08-04 | 32 |  | 32 | 2021-08-04 | 2021-08-05 | 2 |  | 2 | [20 empty] | 2021-08-15 |  |  | NO | Expedited | [8 empty] | 2022-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4891 | 1420 | 10 |  |  | Solar |  | 11W12 | 2021-06-18 | 2021-06-30 | 9 | 7 | 2 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2021-09-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 4889 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2021-06-18 | 2021-07-01 | 10 | 8 | 2 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-08-11 |  |  | NO | Expedited | [8 empty] | 2021-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4888 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-06-18 | 2021-07-01 | 10 | 7 | 3 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4887 | 1474 | 10 |  |  | Solar |  | 39W18 | 2021-06-18 | 2021-06-24 | 5 | 4 | 1 | 2021-06-24 | 2021-06-25 | 2 |  | 2 | [20 empty] | 2021-07-06 | 2021-08-03 |  | YES | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4885 | 1420 | 6 |  |  | Solar |  | 11H10 | 2021-06-17 | 2021-06-29 | 9 | 6 | 3 | 2021-06-30 | 2021-06-30 | 1 |  | 1 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4884 | 1469 | 10 |  |  | Solar |  | 39W18 | 2021-06-17 | 2021-06-22 | 4 | 3 | 1 | 2021-06-21 | 2021-06-23 | 3 |  | 3 | [20 empty] | 2021-07-06 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-12-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 4879 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2021-06-11 | 2021-06-18 | 6 | 4 | 2 | 2021-06-18 | 2021-06-21 | 2 |  | 2 | [20 empty] | 2021-06-24 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4875 | 1462 | 5 |  |  | Solar |  | 30W30 | 2021-06-11 | 2021-06-21 | 7 | 6 | 1 | 2021-06-21 | 2021-06-22 | 2 |  | 2 | [20 empty] | 2021-07-14 |  |  | NO | Expedited | [8 empty] | 2021-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4872 | 1420 | 7.6 |  |  | Solar |  | 25W28 | 2021-06-09 | 2021-06-17 | 7 | 6 | 1 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Townsend | 4871 | 1469 | 8.85 |  |  | Solar |  | 15W17 | 2021-06-09 | 2021-06-16 | 6 | 3 | 3 | 2021-06-16 | 2021-06-16 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4870 | 1420 | 3.8 |  |  | Solar |  | 40W42 | 2021-06-09 | 2021-06-17 | 7 | 4 | 3 | 2021-06-18 | 2021-06-22 | 3 |  | 3 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4867 | 1420 | 10 |  |  | Solar |  | 25W28 | 2021-06-08 | 2021-08-11 | 47 |  | 47 | 2021-08-12 | 2021-08-16 | 3 |  | 3 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4866 | 1420 | 10 |  |  | Solar |  | 01W04 | 2021-06-08 | 2021-06-29 | 16 | 13 | 3 | 2021-06-30 | 2021-06-30 | 1 |  | 1 | [20 empty] | 2021-07-15 | 2021-10-12 |  | YES | Expedited | [8 empty] | 2022-04-07 | In Operation | Res | Y
Fitchburg | Townsend | 4865 | 1469 | 10 |  |  | Solar |  | 15W16 | 2021-06-08 | 2021-06-22 | 11 | 10 | 1 | 2021-06-22 | 2021-06-23 | 2 |  | 2 | [20 empty] | 2021-07-15 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-09-16 | In Operation | Res | Y
Fitchburg | Townsend | 4864 | 1474 | 6 |  |  | Solar |  | 39W18 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-18 | 2021-06-18 | 1 |  | 1 | [20 empty] | 2021-06-24 |  |  | NO | Expedited | [8 empty] | 2022-01-10 | In Operation | Res | Y
Fitchburg | Ashby | 4863 | 1431 | 10 |  |  | Solar |  | 39W19 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [8 empty] | 2021-07-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4862 | 1420 | 6 |  |  | Solar |  | 50W51 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-15 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4860 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2021-06-07 | 2021-06-17 | 9 | 6 | 3 | 2021-06-17 | 2021-06-17 | 1 |  | 1 | [20 empty] | 2021-07-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4851 | 1420 | 10 |  |  | Solar |  | 20W22 | 2021-06-03 | 2021-07-30 | 42 | 40 | 2 | 2021-07-30 | 2021-08-02 | 2 |  | 2 | [20 empty] | 2021-08-20 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4843 | 1420 | 1.77 |  |  | Solar |  | 01W04 | 2021-06-01 | 2021-06-07 | 5 | 4 | 1 | 2021-06-08 | 2021-06-08 | 1 |  | 1 | [20 empty] | 2021-06-14 | 2021-06-17 |  | YES | Expedited | [8 empty] | 2022-01-21 | In Operation | Res | Y
Fitchburg | Townsend | 4842 | 1469 | 10 |  |  | Solar |  | 15W16 | 2021-06-01 | 2021-06-10 | 8 | 2 | 6 | 2021-06-11 | 2021-06-11 | 1 |  | 1 | [20 empty] | 2021-06-21 | 2021-10-19 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 4840 | 1462 | 10 |  |  | Solar |  | 30W30 | 2021-06-01 | 2021-06-16 | 12 | 8 | 4 | 2021-06-16 | 2021-06-17 | 2 |  | 2 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Townsend | 4839 | 1469 | 2.65 |  |  | Solar |  | 39W18 | 2021-06-01 | 2021-06-07 | 5 | 4 | 1 | 2021-06-08 | 2021-06-08 | 1 |  | 1 | [20 empty] | 2021-06-14 |  |  | NO | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Townsend | 4832 | 1474 | 7.6 |  |  | Solar |  | 39W18 | 2021-05-27 | 2021-06-30 | 24 | 22 | 2 | 2021-06-30 | 2021-07-01 | 2 |  | 2 | [20 empty] | 2021-07-13 |  |  | NO | Expedited | [8 empty] | 2022-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 4819 | 1420 | 5.25 |  |  | Solar |  | 31W37 | 2021-05-21 | 2021-06-17 | 19 | 7 | 12 | 2021-06-18 | 2021-06-18 | 1 |  | 1 | [20 empty] | 2021-06-23 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Westminster | 4811 | 0 | 18000 |  |  | Wood |  | K-Line | [33 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4808 | 1420 | 10 |  |  | Solar |  | 0 | 2021-05-18 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 4806 | 1462 | 9.75 |  |  | Solar |  | 30W30 | 2021-05-18 | 2021-06-22 | 25 | 24 | 1 | 2021-06-22 | 2021-06-23 | 2 |  | 2 | [20 empty] | 2021-06-29 |  |  | NO | Expedited | [8 empty] | 2021-10-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4804 | 1420 | 7.6 |  |  | Solar |  | 20W22 | 2021-05-17 | 2021-05-26 | 8 | 5 | 3 | 2021-05-27 | 2021-06-01 | 3 |  | 3 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4803 | 1420 | 3.8 |  |  | Solar |  | 40W40 | 2021-05-17 | 2021-05-27 | 9 | 6 | 3 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-10 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4801 | 1420 | 9.15 |  |  | Solar |  | 40W40 | 2021-05-14 | 2021-05-19 | 4 | 2 | 2 | 2021-05-20 | 2021-05-20 | 1 |  | 1 | [20 empty] | 2021-06-02 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4800 | 1420 | 8.42 |  |  | Solar |  | 40W40 | 2021-05-14 | 2021-05-27 | 10 | 6 | 4 | 2021-05-28 | 2021-06-03 | 4 |  | 4 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4799 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-05-14 | 2021-05-28 | 11 | 7 | 4 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2022-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4798 | 1420 | 9.8 |  |  | Solar |  | 25W27 | 2021-05-14 | 2021-05-28 | 11 | 9 | 2 | 2021-05-28 | 2021-06-01 | 2 |  | 2 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [8 empty] | 2021-09-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4797 | 1462 | 6 |  |  | Solar |  | 31W38 | 2021-05-14 | 2021-05-27 | 10 | 9 | 1 | 2021-05-28 | 2021-06-03 | 4 |  | 4 | [20 empty] | 2021-06-07 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4794 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2021-05-13 | 2021-06-18 | 26 | 25 | 1 | 2021-06-18 | 2021-06-21 | 2 |  | 2 | [20 empty] | 2021-06-24 | 2021-10-19 |  | YES | Expedited | [8 empty] | 2021-12-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4793 | 1420 | 9.8 |  |  | Solar |  | 01W04 | 2021-05-13 | 2021-05-21 | 7 | 4 | 3 | 2021-05-21 | 2021-05-24 | 2 |  | 2 | [20 empty] | 2021-06-02 |  |  | NO | Expedited | [8 empty] | 2022-04-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4788 | 1420 | 6 |  |  | Solar |  | 11W11 | 2021-05-11 | 2021-07-01 | 37 | 35 | 2 | 2021-07-01 | 2021-07-02 | 2 |  | 2 | [20 empty] | 2021-07-13 | 2021-07-20 |  | YES | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4787 | 1420 | 6 |  |  | Solar |  | 25W28 | 2021-05-11 | 2021-05-13 | 3 | 1 | 2 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 | 2021-06-01 |  | YES | Expedited | [8 empty] | 2021-12-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4780 | 1420 | 9.8 |  |  | Solar |  | 50W51 | 2021-05-07 | 2021-05-13 | 5 | 4 | 1 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4779 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2021-05-07 | 2021-05-21 | 11 | 7 | 4 | 2021-05-21 | 2021-05-25 | 3 |  | 3 | [20 empty] | 2021-06-02 | 2021-06-10 |  | YES | Expedited | [8 empty] | 2021-08-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 4778 | 1420 | 9.8 |  |  | Solar |  | 25W27 | 2021-05-06 | 2021-05-13 | 6 | 5 | 1 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4777 | 1420 | 5 |  |  | Solar |  | 01W04 | 2021-05-06 | 2021-05-13 | 6 | 4 | 2 | 2021-05-14 | 2021-05-17 | 2 |  | 2 | [20 empty] | 2021-05-25 | 2021-09-21 |  | YES | Expedited | [8 empty] | 2021-12-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4776 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-05-06 | 2021-05-17 | 8 | 7 | 1 | 2021-05-18 | 2021-05-18 | 1 |  | 1 | [20 empty] | 2021-05-27 |  |  | NO | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4771 | 1420 | 6 |  |  | Solar |  | 50W51 | 2021-05-05 | 2021-05-12 | 6 | 5 | 1 | 2021-05-13 | 2021-05-17 | 3 |  | 3 | [20 empty] | 2021-05-25 |  |  | NO | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4764 | 1462 | 9.8 |  |  | Solar |  | 31W38 | 2021-05-03 | 2021-05-04 | 2 |  | 2 | 2021-05-05 | 2021-05-18 | 10 |  | 10 | [20 empty] | 2021-05-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4761 | 1420 | 12.095 |  |  | Solar |  | 31W37 | 2021-05-03 | 2021-05-24 | 16 | 13 | 3 | 2021-05-25 | 2021-05-26 | 2 |  | 2 | [20 empty] | 2021-06-02 |  |  | NO | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 4759 | 1462 | 10 |  |  | Solar |  | 30W30 | 2021-04-30 | 2021-05-03 | 2 |  | 2 | 2021-05-04 | 2021-05-04 | 1 |  | 1 | [20 empty] | 2021-05-12 | 2021-05-17 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4758 | 1420 | 5 |  |  | Solar |  | 01W04 | 2021-04-30 | 2021-06-10 | 29 | 27 | 2 | 2021-06-11 | 2021-06-14 | 2 |  | 2 | [20 empty] | 2021-06-21 | 2021-02-04 |  | YES | Expedited | [8 empty] | 2022-06-01 | In Operation | Res | Y
Fitchburg | Ashby | 4751 | 1431 | 10 |  |  | Solar |  | 39W19 | 2021-04-28 | 2021-04-30 | 3 | 2 | 1 | 2021-04-30 | 2021-05-03 | 2 |  | 2 | [20 empty] | 2021-05-11 |  |  | NO | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Ashby | 4747 | 1431 | 9.8 |  |  | Solar |  | 39W19 | 2021-04-26 | 2021-05-04 | 7 | 6 | 1 | 2021-05-05 | 2021-05-05 | 1 |  | 1 | [20 empty] | 2021-05-13 | 2021-05-17 |  | YES | Expedited | [8 empty] | 2021-06-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4744 | 1462 | 10 |  |  | Solar |  | 30W30 | 2021-04-23 | 2021-04-27 | 3 | 2 | 1 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2022-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4743 | 1420 | 9.8 |  |  | Solar |  | 01W04 | 2021-04-23 | 2021-04-28 | 4 | 3 | 1 | 2021-04-29 | 2021-04-29 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4740 | 1420 | 7.6 |  |  | Solar |  | 20W22 | 2021-04-22 | 2021-04-28 | 5 | 3 | 2 | 2021-04-29 | 2021-04-29 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2022-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 4735 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2021-04-21 | 2021-04-27 | 5 | 2 | 3 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2021-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4734 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2021-04-21 | 2021-04-27 | 5 | 3 | 2 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2022-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4733 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2021-04-21 | 2021-04-27 | 5 | 3 | 2 | 2021-04-28 | 2021-04-28 | 1 |  | 1 | [20 empty] | 2021-05-04 |  |  | NO | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4731 | 1420 | 5.31 |  |  | Solar |  | 25W27 | 2021-04-20 | 2021-04-27 | 6 | 3 | 3 | 2021-04-28 | [24 empty] | 2021-05-14 | 2021-07-16 |  | YES | Expedited | [8 empty] | 2021-09-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 4730 | 1420 | 3.8 |  |  | Solar |  | 0 | 2021-04-20 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4729 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2021-04-20 | 2021-04-26 | 5 | 2 | 3 | 2021-04-27 | 2021-04-27 | 1 |  | 1 | [20 empty] | 2021-05-04 | 2021-05-18 |  | YES | Expedited | [8 empty] | 2021-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4727 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2021-04-19 | 2021-04-23 | 4 | 3 | 1 | 2021-04-26 | 2021-04-26 | 1 |  | 1 | [20 empty] | 2021-04-28 |  |  | NO | Expedited | [8 empty] | 2021-10-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4726 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2021-04-19 | 2021-04-23 | 4 | 3 | 1 | 2021-04-26 | 2021-04-26 | 1 |  | 1 | [20 empty] | 2021-04-28 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4722 | 1462 | 9 |  |  | Solar |  | 30W31 | 2021-04-16 | 2021-06-23 | 47 | 46 | 1 | 2021-06-23 | 2021-06-24 | 2 |  | 2 | [20 empty] | 2021-06-29 | 2021-07-02 |  | YES | Expedited | [8 empty] | 2021-08-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 4721 | 1420 | 7.6 |  |  | Solar |  | 20W22 | 2021-04-16 | 2021-04-19 | 1 | 1 | 0 | 2021-04-20 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-21 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4720 | 1420 | 8.26 |  |  | Solar |  | 35W36 | 2021-04-15 | 2021-05-26 | 29 | 27 | 2 | 2021-05-27 | 2021-06-03 | 5 |  | 5 | [20 empty] | 2021-06-07 | 2021-07-07 |  | YES | Expedited | [8 empty] | 2021-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4719 | 1420 | 5 |  |  | Solar |  | 25W28 | 2021-04-15 | 2021-04-19 | 2 | 1 | 1 | 2021-04-20 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-26 | 2021-05-12 |  | YES | Expedited | [8 empty] | 2021-07-01 | In Operation | Res | Y
Fitchburg | Townsend | 4714 | 1474 | 9.8 |  |  | Solar |  | 39W18 | 2021-04-14 | 2021-06-03 | 35 | 33 | 2 | 2021-06-04 | 2021-06-07 | 2 |  | 2 | [20 empty] | 2021-06-10 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4713 | 1431 | 10 |  |  | Solar + Energy Storage |  | 39W19 | 2021-04-13 | 2021-05-24 | 29 | 26 | 3 | 2021-05-25 | 2021-05-27 | 3 |  | 3 | [20 empty] | 2021-06-02 | 2021-07-23 |  | YES | Expedited | [8 empty] | 2021-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4706 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2021-04-07 | 2021-04-21 | 10 | 8 | 2 | 2021-04-22 | 2021-04-22 | 1 |  | 1 | [20 empty] | 2021-04-29 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-06-01 | Cancelled | Res | Y
Fitchburg | Lunenburg | 4705 | 1462 | 6 |  |  | Solar |  | 31W37 | 2021-04-07 | 2021-04-21 | 10 | 9 | 1 | 2021-04-22 | 2021-04-22 | 1 |  | 1 | [20 empty] | 2021-04-27 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 4693 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2021-04-01 | 2021-04-12 | 8 | 5 | 3 | 2021-04-13 | 2021-04-21 | 6 |  | 6 | [20 empty] | 2021-04-26 |  |  | NO | Expedited | [8 empty] | 2021-10-26 | In Operation | Res | Y
Fitchburg | Ashby | 4692 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2021-04-01 | 2021-04-20 | 13 | 5 | 8 | 2021-04-21 | 2021-04-21 | 1 |  | 1 | [20 empty] | 2021-04-27 |  |  | NO | Expedited | [8 empty] | 2021-11-03 | In Operation | Res | Y
Fitchburg | Townsend | 4691 | 1469 | 10.03 |  |  | Solar |  | 39W18 | 2021-03-31 | 2021-04-08 | 7 | 4 | 3 | 2021-04-09 | 2021-04-09 | 1 |  | 1 | [20 empty] | 2021-04-19 |  |  | NO | Expedited | [8 empty] | 2021-07-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 4689 | 1420 | 9.735 |  |  | Solar |  | 40W40 | 2021-03-31 | 2021-04-29 | 21 | 21 | 0 | 2021-04-30 | 2021-05-13 | [23 empty] | 2021-05-19 | 2021-06-08 |  | YES | Expedited | [8 empty] | 2021-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4687 | 1420 | 6 |  |  | Solar |  | 25W28 | 2021-03-30 | 2021-04-12 | 10 | 8 | 2 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-04-26 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4686 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2021-03-30 | 2021-04-12 | 10 | 8 | 2 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-08-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 4685 | 1420 | 8 |  |  | Solar |  | 11H11 | 2021-03-29 | 2021-04-06 | 7 | 6 | 1 | 2021-04-07 | 2021-04-21 | 10 |  | 10 | [20 empty] | 2021-04-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4677 | 1462 | 3.8 |  |  | Solar |  | 31W37 | 2021-03-26 | 2021-04-08 | 10 | 9 | 1 | 2021-04-09 | 2021-04-09 | 1 |  | 1 | [20 empty] | 2021-04-19 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4675 | 1420 | 2000 |  |  | Solar + Energy Storage |  | 40W39 | 2021-03-26 | 2021-04-07 | 9 | 4 | 5 | [10 empty] | 2021-04-09 | 2021-04-20 | 7 |  | 8 | 2021-07-02 | [12 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4667 | 1420 | 3.8 |  |  | Solar |  | 01W02 | 2021-03-22 | 2021-03-29 | 6 | 3 | 3 | 2021-03-30 | 2021-03-31 | 2 |  | 2 | [20 empty] | 2021-04-06 |  |  | NO | Expedited | [8 empty] | 2021-08-17 | In Operation | Res | Y
Fitchburg | Ashby | 4661 | 1431 | 8.5 |  |  | Solar |  | 39W19 | 2021-03-19 | 2021-04-01 | 10 | 9 | 1 | 2021-04-01 | 2021-04-02 | 2 |  | 2 | [20 empty] | 2021-04-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4660 | 1431 | 5.5 |  |  | Solar |  | 39W19 | 2021-03-19 | 2021-04-16 | 21 | 9 | 12 | 2021-04-19 | 2021-04-20 | 1 |  | 1 | [20 empty] | 2021-04-26 | 2021-06-01 |  | YES | Expedited | [8 empty] | 2021-06-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4659 | 1420 | 8.26 |  |  | Solar |  | 25W27 | 2021-03-19 | 2021-04-01 | 10 | 9 | 1 | 2021-04-01 | 2021-04-02 | 2 |  | 2 | [20 empty] | 2021-04-08 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4657 | 1420 | 8 |  |  | Solar |  | 01W04 | 2021-03-18 | 2021-04-02 | 12 | 10 | 2 | 2021-04-05 | 2021-04-07 | 3 |  | 3 | [20 empty] | 2021-04-14 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-12-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4656 | 1462 | 4.5 |  |  | Solar |  | 31W38 | 2021-03-18 | 2021-03-26 | 7 | 5 | 2 | 2021-03-26 | 2021-03-29 | 2 |  | 2 | [20 empty] | 2021-04-02 |  |  | NO | Expedited | [8 empty] | 2021-06-03 | In Operation | Res | Y
Fitchburg | Townsend | 4651 | 1469 | 19 |  |  | Solar |  | 15W16 | 2021-03-16 | 2021-04-12 | 20 | 15 | 5 | 2021-04-13 | 2021-04-15 | 3 |  | 3 | [20 empty] | 2021-04-19 | 2022-03-22 |  | YES | Expedited | [8 empty] | 2022-05-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4646 | 1462 | 7.5 |  |  | Solar |  | 30W30 | 2021-03-13 | 2021-03-24 | 8 | 6 | 2 | 2021-03-24 | 2021-03-25 | 2 |  | 2 | [20 empty] | 2021-03-30 | 2021-04-12 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4645 | 1420 | 7.965 |  |  | Solar + Energy Storage |  | 20W22 | 2021-03-12 | 2021-04-02 | 16 | 7 | 9 | 2021-04-05 | 2021-04-07 | 3 |  | 3 | [20 empty] | 2021-04-14 | 2021-04-26 |  | YES | Expedited | [8 empty] | 2021-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 4644 | 1462 | 19.6 |  |  | Solar |  | 0 | 2021-03-12 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4640 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2021-03-10 | 2021-04-12 | 24 | 23 | 1 | 2021-04-13 | 2021-04-13 | 1 |  | 1 | [20 empty] | 2021-04-19 | 2021-06-14 |  | YES | Expedited | [8 empty] | 2021-07-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 4637 | 1420 | 6 |  |  | Solar |  | 31W37 | 2021-03-06 | 2021-03-16 | 7 | 3 | 4 | 2021-03-17 | 2021-03-22 | 4 |  | 4 | [20 empty] | 2021-05-06 | 2021-05-14 |  | YES | Expedited | [8 empty] | 2021-09-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 4626 | 1420 | 16 |  |  | Solar |  | 22W1 | 2021-02-26 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4623 | 1420 | 6 |  |  | Solar |  | 50W51 | 2021-02-25 | 2021-03-01 | 3 | 2 | 1 | 2021-03-02 | 2021-03-03 | 2 |  | 2 | [20 empty] | 2021-03-12 | 2021-04-16 |  | YES | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4622 | 1420 | 10 |  |  | Solar |  | 01W01 | 2021-02-25 | 2021-03-01 | 3 | 2 | 1 | 2021-03-02 | 2021-03-04 | 3 |  | 3 | [20 empty] | 2021-03-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4619 | 1462 | 6.49 |  |  | Solar |  | 30W30 | 2021-02-22 | 2021-03-09 | 12 | 11 | 1 | 2021-03-10 | 2021-03-10 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-03-31 |  | YES | Expedited | [8 empty] | 2021-04-16 | In Operation | Res | Y
Fitchburg | Ashby | 4614 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-02-18 | 2021-03-09 | 14 | 13 | 1 | 2021-03-10 | 2021-03-10 | 1 |  | 1 | [20 empty] | 2021-03-17 |  |  | NO | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 4612 | 1420 | 4.75 |  |  | Solar |  | 50W51 | 2021-02-18 | 2021-02-24 | 5 | 4 | 1 | 2021-02-24 | 2021-02-25 | 2 |  | 2 | [20 empty] | 2021-03-09 | 2021-03-12 |  | YES | Expedited | [8 empty] | 2021-05-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4608 | 1420 | 8.96 |  |  | Solar |  | 20W22 | 2021-02-16 | 2021-02-22 | 5 | 4 | 1 | 2021-02-22 | 2021-02-22 | 1 |  | 1 | [20 empty] | 2021-02-26 | 2021-07-12 |  | YES | Expedited | [8 empty] | 2021-08-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 4606 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2021-02-12 | 2021-03-30 | 32 | 32 | 0 | 2021-03-30 | 2021-03-31 | 2 |  | 2 | [20 empty] | 2021-04-06 | 2021-05-17 |  | YES | Expedited | [8 empty] | 2022-01-25 | In Operation | Res | Y
Fitchburg | Ashby | 4604 | 1431 | 7.965 |  |  | Solar |  | 39W19 | 2021-02-12 | 2021-02-19 | 5 | 5 | 0 | 2021-02-19 | 2021-02-22 | 2 |  | 2 | [20 empty] | 2021-02-26 | 2021-03-01 |  | YES | Expedited | [8 empty] | 2021-05-19 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4603 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2021-02-11 | 2021-02-18 | 5 | 4 | 1 | 2021-02-19 | 2021-02-22 | 2 |  | 2 | [20 empty] | 2021-02-26 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 4601 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2021-02-11 | 2021-03-02 | 13 | 13 | 0 | 2021-03-03 | 2021-03-04 | 2 |  | 2 | [20 empty] | 2021-04-26 | 2021-05-11 |  | YES | Expedited | [8 empty] | 2021-09-03 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4600 | 1420 | 5 |  |  | Solar |  | 20W22 | 2021-02-10 | 2021-03-02 | 14 | 14 | 0 | 2021-03-03 | 2021-03-05 | 3 |  | 3 | [20 empty] | 2021-03-12 | 2021-03-30 |  | YES | Expedited | [8 empty] | 2021-07-06 | In Operation | Res | Y
Fitchburg | Townsend | 4589 | 1474 | 10 |  |  | Solar |  | 39W18 | 2021-02-05 | 2021-02-17 | 8 | 8 | 0 | 2021-02-17 | 2021-02-17 | 1 |  | 1 | [20 empty] | 2021-02-18 | 2021-02-26 |  | YES | Expedited | [8 empty] | 2021-05-03 | In Operation | Res | Y
Fitchburg | Ashby | 4588 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2021-02-05 | 2021-02-17 | 8 | 8 | 0 | 2021-02-18 | 2021-02-23 | 4 |  | 4 | [20 empty] | 2021-02-26 | 2021-03-23 |  | YES | Expedited | [8 empty] | 2021-06-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4586 | 1420 | 6 |  |  | Solar |  | 31W37 | 2021-02-02 | 2021-03-18 | 32 | 30 | 2 | 2021-03-19 | 2021-03-22 | 2 |  | 2 | [20 empty] | 2021-03-26 | 2021-04-01 |  | YES | Expedited | [8 empty] | 2021-09-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4574 | 1462 | 7.68 |  |  | Solar |  | 30W30 | 2021-01-27 | 2021-02-25 | 21 | 21 | 0 | 2021-03-08 | 2021-03-08 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-06-15 | In Operation | Res | Y
Fitchburg | Townsend | 4572 | 1469 | 10 |  |  | Solar |  | 15W16 | 2021-01-26 | 2021-02-17 | 16 | 15 | 1 | 2021-02-17 | 2021-02-17 | 1 |  | 1 | [20 empty] | 2021-02-24 | 2021-03-10 |  | YES | Expedited | [8 empty] | 2021-04-19 | In Operation | Res | Y
Fitchburg | Townsend | 4571 | 1474 | 9.75 |  |  | Solar |  | 39W18 | 2021-01-26 | 2021-02-16 | 15 | 14 | 1 | 2021-02-17 | 2021-03-22 | 24 | 23 | 1 | [20 empty] | 2021-03-26 | 2021-04-05 |  | YES | Expedited | [8 empty] | 2021-05-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 4570 | 1420 | 9.75 |  |  | Solar |  | 01W04 | 2021-01-26 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4568 | 1420 | 2738 |  |  | Solar + Energy Storage |  | 25W27 | 2021-01-21 | 2021-02-02 | 9 | 8 | 1 | [10 empty] | 2021-02-04 | 2021-03-16 | 28 |  | 27 | 2021-04-29 | 2021-09-02 | 90 | 21 | 69 | [5 empty] | 2021-11-17 |  |  | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 4564 | 1420 | 6 |  |  | Solar |  | 01W04 | 2021-01-21 | 2021-02-16 | 18 | 17 | 1 | 2021-02-16 | 2021-02-17 | 2 |  | 2 | [20 empty] | 2021-02-18 | 2021-04-12 |  | YES | Expedited | [8 empty] | 2021-04-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4554 | 1420 | 10 |  |  | Solar |  | 01W04 | 2021-01-06 | 2021-01-20 | 10 | 9 | 1 | 2021-01-20 | 2021-01-20 | 1 |  | 1 | [20 empty] | 2021-01-25 | 2021-02-10 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4552 | 1462 | 6.5 |  |  | Solar |  | 30W31 | 2021-01-06 | 2021-02-04 | 21 | 21 | 0 | 2021-02-04 | 2021-02-04 | 1 |  | 1 | [20 empty] | 2021-02-12 | 2021-02-23 |  | YES | Expedited | [8 empty] | 2021-04-22 | In Operation | Res | Y
Fitchburg | Townsend | 4551 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2021-01-05 | 2021-01-29 | 18 | 16 | 2 | 2021-02-01 | 2021-02-02 | 2 |  | 2 | [20 empty] | 2021-02-08 | 2021-02-15 |  | YES | Expedited | [8 empty] | 2021-08-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 4548 | 1462 | 9.735 |  |  | Solar |  | 30W30 | 2020-12-31 | 2021-01-20 | 13 | 12 | 1 | 2021-01-20 | 2021-01-21 | 2 |  | 2 | [20 empty] | 2021-02-01 | 2021-02-19 |  | YES | Expedited | [8 empty] | 2021-04-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 4544 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-12-30 | 2021-01-18 | 12 | 7 | 5 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-22 | 2021-04-15 |  | YES | Expedited | [8 empty] | 2021-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 4543 | 1462 | 8.96 |  |  | Solar |  | 31W37 | 2020-12-30 | 2021-01-19 | 13 | 10 | 3 | 2021-01-19 | 2021-01-19 | 1 |  | 1 | [20 empty] | 2021-01-22 | 2021-04-09 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 4542 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-12-30 | 2021-01-18 | 12 | 12 | 0 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-21 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-08-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4540 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2020-12-29 | 2021-01-07 | 7 | 6 | 1 | 2021-01-07 | 2021-01-08 | 2 |  | 2 | [20 empty] | 2021-01-21 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4535 | 1420 | 3 |  |  | Solar |  | 01W04 | 2020-12-24 | 2021-01-21 | 18 | 18 | 0 | 2021-01-22 | 2021-01-22 | 1 |  | 1 | [20 empty] | 2021-02-01 | 2021-02-04 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4533 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2020-12-23 | 2021-01-18 | 16 | 6 | 10 | 2021-01-18 | 2021-01-19 | 1 |  | 1 | [20 empty] | 2021-01-22 | 2021-01-27 |  | YES | Expedited | [8 empty] | 2021-10-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 4531 | 1420 | 9.75 |  |  | Solar |  | 31W37 | 2020-12-22 | 2021-02-04 | 30 | 30 | 0 | 2021-02-04 | 2021-02-04 | 1 |  | 1 | [20 empty] | 2021-02-12 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 4526 | 1431 | 10 |  |  | Solar |  | 39W19 | 2020-12-18 | 2021-01-18 | 19 | 16 | 3 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-21 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-03-25 | In Operation | Res | Y
Fitchburg | Ashby | 4519 | 1431 | 6 |  |  | Solar |  | 39W19 | 2020-12-17 | 2020-12-21 | 3 |  | 3 | 2020-12-22 | 2020-12-29 | 5 |  | 5 | [20 empty] | 2021-01-18 | 2021-02-11 |  | YES | Expedited | [8 empty] | 2021-03-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 4518 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-12-15 | 2021-02-26 | 50 | 41 | 9 | 2021-02-26 | 2021-02-26 | 1 |  | 1 | [20 empty] | 2021-03-09 | 2021-12-09 |  | YES | Expedited | [8 empty] | 2021-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 4510 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2020-12-11 | 2020-12-21 | 7 | 5 | 2 | 2020-12-22 | 2020-12-29 | 5 |  | 5 | [20 empty] | 2021-01-05 | 2021-01-08 |  | YES | Expedited | [8 empty] | 2021-07-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 4501 | 1420 | 10 |  |  | Solar |  | 30W31 | 2020-12-08 | 2020-12-09 | 2 | 1 | 1 | 2020-12-10 | 2020-12-10 | 1 |  | 1 | [20 empty] | 2021-01-21 | 2021-02-04 |  | YES | Expedited | [8 empty] | 2021-03-26 | Cancelled | Res | Y
Fitchburg | Fitchburg | 4499 | 1420 | 500 |  |  | Solar |  | 50W56 | 2020-12-07 | 2021-02-15 | 47 | 47 | 1 | [10 empty] | 2021-02-18 | 2021-03-11 | 16 |  | 16 | 2021-08-13 | 2023-05-25 | 439 | 368 | 71 | [5 empty] | 2023-08-01 | 2024-04-25 | 2026-06-20 | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Lunenburg | 4496 | 1462 | 7.6 |  |  | Solar |  | 0 | 2020-12-07 | [32 empty] | NO | Simplified | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4493 | 1469 | 6.75 |  |  | Solar |  | 15W16 | 2020-12-03 | 2020-12-14 | 8 | 6 | 2 | 2020-12-14 | 2020-12-15 | 2 |  | 2 | [20 empty] | 2020-12-22 | 2021-03-08 |  | YES | Expedited | [8 empty] | 2021-03-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4491 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2020-12-02 | 2021-01-06 | 24 | 23 | 1 | 2021-01-06 | 2021-01-07 | 2 |  | 2 | [20 empty] | 2021-02-01 | 2021-02-12 |  | YES | Expedited | [8 empty] | 2022-02-09 | In Operation | Res | Y
Fitchburg | Ashby | 4480 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2020-11-25 | 2020-12-01 | 4 | 3 | 1 | 2020-12-02 | 2020-12-07 | 0 |  | 0 | [20 empty] | 2020-12-14 | 2020-12-18 | 2020-12-12 | YES | Expedited | [8 empty] | 2021-05-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 4478 | 1462 | 8.5 |  |  | Solar |  | 30W31 | 2020-11-24 | 2021-01-27 | 43 | 40 | 3 | 2021-01-27 | 2021-01-27 | 0 |  | 0 | [20 empty] | 2021-02-08 | 2021-03-05 |  | YES | Expedited | [8 empty] | 2021-03-17 | In Operation | Res | Y
Fitchburg | Townsend | 4476 | 1469 | 3.8 |  |  | Solar |  | 15W16 | 2020-11-24 | 2021-01-29 | 45 | 41 | 4 | 2021-01-29 | 2021-02-01 | 0 |  | 0 | [20 empty] | 2021-02-08 | 2021-04-06 |  | YES | Expedited | [8 empty] | 2021-08-13 | In Operation | Res | Y
Fitchburg | Townsend | 4474 | 1469 | 9.8 |  |  | Solar |  | 15W16 | 2020-11-23 | 2021-01-25 | 42 | 42 | 0 | 2021-01-26 | 2021-01-26 | 0 |  | 0 | [20 empty] | 2021-02-02 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4466 | 1462 | 8.84 |  |  | Solar |  | 31W38 | 2020-11-19 | 2020-12-28 | 26 | 25 | 1 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-06 | 2021-04-19 |  | YES | Expedited | [8 empty] | 2021-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4464 | 1420 | 2738 | 2738 | 0 | Solar + Energy Storage | Yes | 20W22 | 2020-11-18 | 2020-11-30 | 8 | 3 | 5 | [10 empty] | 2020-12-02 | 2020-12-09 | 6 |  | 5 | 2021-02-02 | 2021-06-22 | 98 | 16 | 82 | [5 empty] | 2021-08-25 | 2022-11-28 | 2020-12-03 | YES | Standard | [9 empty] | Perform Mods | Comm | N
Fitchburg | Townsend | 4446 | 1469 | 7.5 |  |  | Solar |  | 15W16 | 2020-11-10 | 2020-11-20 | 8 | 6 | 2 | 2020-11-21 | 2020-11-23 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-23 | 2020-11-02 | YES | Expedited | [8 empty] | 2021-01-09 | In Operation | Res | Y
Fitchburg | Townsend | 4442 | 1469 | 5 |  |  | Solar |  | 15W16 | 2020-11-07 | 2021-01-11 | 42 | 41 | 1 | 2021-01-12 | 2021-01-19 | 5 |  | 5 | [20 empty] | 2021-01-22 | 2021-03-25 |  | YES | Expedited | [8 empty] | 2021-04-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4435 | 1462 | 10 |  |  | Solar |  | 30W31 | 2020-10-30 | 2020-11-24 | 17 | 16 | 1 | 2020-11-25 | 2020-11-25 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-09 |  | YES | Expedited | [8 empty] | 2021-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 4432 | 1462 | 4 |  |  | Solar |  | 31W37 | 2020-10-27 | 2021-01-18 | 55 | 51 | 4 | 2021-01-18 | 2021-01-18 | 0 |  | 0 | [20 empty] | 2021-01-22 | 2021-02-16 | 2020-08-31 | YES | Expedited | [8 empty] | 2021-05-25 | In Operation | Res | Y
Fitchburg | Townsend | 4425 | 1469 | 10 |  |  | Solar |  | 39W18 | 2020-10-26 | 2020-11-05 | 9 | 8 | 1 | 2020-11-06 | 2020-12-07 | 20 |  | 20 | [20 empty] | 2020-12-14 | 2020-12-18 | 2020-11-19 | YES | Expedited | [8 empty] | 2021-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 4424 | 1462 | 10 |  |  | Solar |  | 31W37 | 2020-10-24 | [31 empty] | 2020-11-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4423 | 1462 | 10 |  |  | Solar |  | 30W30 | 2020-10-24 | 2021-01-12 | 53 | 41 | 12 | 2021-01-13 | 2021-01-19 | 4 |  | 4 | [20 empty] | 2021-01-22 | 2021-02-03 | 2020-11-24 | YES | Expedited | [8 empty] | 2021-06-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 4422 | 1462 | 8 |  |  | Solar |  | 30W30 | 2020-10-23 | [31 empty] | 2020-10-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4421 | 1469 | 10 |  |  | Solar |  | 39W18 | 2020-10-23 | 2020-12-28 | 44 | 40 | 4 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-18 |  | 2020-11-23 | NO | Expedited | [8 empty] | 2021-11-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 4420 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2020-10-23 | [31 empty] | 2020-11-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4419 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-10-23 | [31 empty] | 2020-11-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4418 | 1420 | 5 |  |  | Solar |  | 20W22 | 2020-10-23 | 2020-11-24 | 22 | 21 | 1 | 2020-11-25 | 2020-11-25 | 1 |  | 1 | [20 empty] | 2020-12-03 | 2020-12-09 |  | YES | Expedited | [8 empty] | 2020-12-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 4414 | 1462 | 10 |  |  | Solar |  | 31W37 | 2020-10-21 | 2020-12-28 | 46 | 44 | 2 | 2020-12-29 | 2020-12-29 | 1 |  | 1 | [20 empty] | 2021-01-06 | 2021-02-03 | 2020-10-12 | YES | Expedited | [8 empty] | 2021-07-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 4410 | 1462 | 10 |  |  | Solar |  | 30W31 | 2020-10-20 | 2020-10-28 | 7 | 5 | 2 | 2020-10-28 | 2020-10-29 | 2 |  | 2 | [20 empty] | 2020-11-10 | 2020-11-17 | 2020-10-26 | YES | Expedited | [8 empty] | 2021-04-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 4409 | 1462 | 9.75 |  |  | Solar |  | 31W38 | 2020-10-19 | 2020-10-27 | 7 | 6 | 1 | 2020-10-28 | 2020-10-28 | 1 |  | 1 | [20 empty] | 2020-11-10 | 2021-02-03 | 2020-09-19 | YES | Expedited | [8 empty] | 2021-02-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4408 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2020-10-19 | 2020-10-23 | 5 | 4 | 1 | 2020-10-23 | 2020-10-26 | 2 |  | 2 | [20 empty] | 2020-10-29 | 2020-11-03 | 2020-11-09 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4404 | 1420 | 7.6 |  |  | Solar + Energy Storage |  | 40W40 | 2020-10-16 | [32 empty] | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 4388 | 1469 | 10 |  |  | Solar |  | 15W17 | 2020-10-08 | 2020-10-28 | 14 | 13 | 1 | 2020-10-28 | 2020-10-29 | 2 |  | 2 | [20 empty] | 2020-11-10 | 2020-11-17 |  | YES | Expedited | [8 empty] | 2021-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4387 | 1420 | 5 |  |  | Solar |  | 22W1 | 2020-10-07 | 2020-11-16 | 27 | 23 | 4 | 2020-11-17 | 2020-11-25 | 7 | 6 | 1 | [20 empty] | 2020-12-03 | 2021-01-26 |  | YES | Expedited | [8 empty] | 2021-04-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 4378 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2020-09-30 | 2020-10-06 | 5 | 3 | 2 | 2020-10-07 | 2020-10-07 | 1 |  | 1 | [20 empty] | 2020-10-15 |  | 2020-09-20 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4376 | 1420 | 9.75 |  |  | Solar |  | 01W04 | 2020-09-30 | 2020-10-13 | 9 | 7 | 2 | 2020-10-13 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2021-02-23 | 2020-10-16 | YES | Expedited | [8 empty] | 2021-03-09 | In Operation | Res | Y
Fitchburg | Townsend | 4375 | 1474 | 7.5 |  |  | Solar |  | 39W18 | 2020-09-30 | 2020-10-27 | 19 | 18 | 1 | 2020-10-28 | 2020-10-28 | 1 |  | 1 | [20 empty] | 2020-11-10 | 2020-12-14 | 2020-10-05 | YES | Expedited | [8 empty] | 2020-12-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 4374 | 1462 | 10 |  |  | Solar |  | 31W38 | 2020-09-28 | 2020-10-14 | 12 | 7 | 5 | 2020-10-15 | 2020-10-15 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-12-18 |  | YES | Expedited | [8 empty] | 2021-01-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 4371 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-09-25 | 2020-10-05 | 7 | 5 | 2 | 2020-10-05 | 2020-10-06 | 2 |  | 2 | [20 empty] | 2020-10-15 | 2020-10-22 | 2020-10-11 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4361 | 1474 | 5.5 |  |  | Solar |  | 39W18 | 2020-09-22 | 2020-10-01 | 8 | 7 | 1 | 2020-10-01 | 2020-10-02 | 2 |  | 2 | [20 empty] | 2020-10-23 | 2020-11-06 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4352 | 1462 | 8 |  |  | Solar |  | 30W31 | 2020-09-15 | 2020-11-16 | 43 | 40 | 3 | 2020-11-17 | 2020-11-17 | 1 |  | 1 | [20 empty] | 2020-11-30 | 2021-01-06 | 2020-09-26 | YES | Expedited | [8 empty] | 2021-01-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 4351 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-09-15 | 2020-09-23 | 7 | 4 | 3 | 2020-09-23 | 2020-09-23 | 1 |  | 1 | [20 empty] | 2020-10-20 |  | 2020-11-07 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4350 | 1462 | 15.2 |  |  | Solar + Energy Storage |  | 30W31 | 2020-09-14 | 2020-09-30 | 13 | 12 | 1 | 2020-10-01 | 2021-02-10 | [23 empty] | 2021-02-16 | 2021-02-25 |  | YES | Expedited | [8 empty] | 2021-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 4347 | 1420 | 16 |  |  | Solar |  | 40W40 | 2020-09-14 | 2020-09-23 | 8 | 7 | 1 | 2020-09-23 | 2020-09-24 | 2 |  | 2 | [20 empty] | 2020-10-05 |  | 2020-09-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4346 | 1469 | 9.75 |  |  | Solar |  | 39W18 | 2020-09-11 | 2020-09-15 | 3 | 2 | 1 | 2020-09-16 | 2020-09-18 | 3 |  | 3 | [20 empty] | 2020-10-05 | 2021-02-19 | 2020-09-16 | YES | Expedited | [8 empty] | 2021-04-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 4339 | 1464 | 2 |  |  | Solar |  | 30W30 | 2020-09-08 | 2020-10-12 | 24 | 22 | 2 | 2020-10-12 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-10-28 | 2020-09-17 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4338 | 1420 | 2.95 |  |  | Solar |  | 31W37 | 2020-09-08 | 2020-09-17 | 8 | 7 | 1 | 2020-09-18 | 2020-09-18 | 1 |  | 1 | [20 empty] | 2020-09-25 | 2021-02-03 | 2020-09-18 | YES | Expedited | [8 empty] | 2021-02-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 4329 | 1462 | 10.15 |  |  | Solar |  | 30W31 | 2020-09-02 | 2020-09-10 | 6 | 5 | 1 | 2020-09-11 | 2020-09-15 | 3 |  | 3 | [20 empty] | 2020-09-17 |  | 2020-09-19 | NO | Expedited | [8 empty] | 2020-11-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4327 | 1420 | 7.68 | 7.68 | 0 | Solar + Energy Storage | Yes | 01W04 | 2020-09-02 | 2020-10-30 | 41 | 39 | 2 | 2020-11-02 | 2020-11-03 | 2 |  | 2 | [20 empty] | 2020-11-17 | 2020-12-10 | 2020-09-20 | YES | Expedited | [8 empty] | 2021-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 4325 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2020-08-31 | 2020-09-11 | 9 | 8 | 1 | 2020-09-14 | 2020-09-16 | 3 |  | 3 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-09-21 | YES | Expedited | [8 empty] | 2021-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 4324 | 1462 | 10 |  |  | Solar |  | 30W30 | 2020-08-31 | 2020-09-14 | 10 | 9 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-18 | 2020-09-25 | 2020-10-27 | YES | Expedited | [8 empty] | 2020-12-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 4323 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-08-31 | 2020-09-14 | 10 | 9 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-25 | 2020-10-12 | 2020-09-24 | YES | Expedited | [8 empty] | 2021-01-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 4320 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2020-08-28 | 2020-09-14 | 11 | 10 | 1 | 2020-09-15 | 2020-09-16 | 2 |  | 2 | [20 empty] | 2020-09-25 | 2020-10-09 | 2020-09-01 | YES | Expedited | [8 empty] | 2021-06-22 | In Operation | Res | Y
Fitchburg | Townsend | 4316 | 1469 | 6.75 |  |  | Solar |  | 15W16 | 2020-08-27 | 2020-09-10 | 10 | 8 | 2 | 2020-09-11 | 2020-09-16 | 4 |  | 4 | [20 empty] | 2020-09-17 | 2020-09-21 | 2020-09-10 | YES | Expedited | [8 empty] | 2020-10-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4312 | 1420 | 7.95 |  |  | Solar |  | 35W36 | 2020-08-26 | 2020-08-27 | 2 |  | 2 | 2020-08-28 | 2020-09-01 | 3 |  | 3 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-08-26 | YES | Expedited | [8 empty] | 2021-12-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 4309 | 1420 | 7.5 |  |  | Solar |  | 01W04 | 2020-08-25 | 2020-08-31 | 5 | 4 | 1 | 2020-09-01 | 2020-09-02 | 2 |  | 2 | [20 empty] | 2020-09-02 |  | 2020-06-21 | NO | Expedited | [8 empty] | 2021-10-15 | In Operation | Res | Y
Fitchburg | Ashby | 4308 | 1431 | 9.5 |  |  | Solar |  | 39W19 | 2020-08-25 | 2020-08-31 | 5 | 4 | 1 | 2020-08-31 | 2020-09-01 | 2 |  | 2 | [20 empty] | 2020-09-02 | 2020-10-26 | 2020-06-29 | YES | Expedited | [8 empty] | 2020-10-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4307 | 1420 | 4999 |  |  | Solar + Energy Storage |  | 40W38 | 2020-08-25 | 2020-09-23 | 21 | 19 | 2 | [10 empty] | 2020-10-06 | 2020-10-22 | 12 |  | 12 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 4301 | 1420 | 6.75 |  |  | Solar |  | 31W37 | 2020-08-21 | 2020-08-28 | 6 | 5 | 1 | 2020-08-31 | 2020-09-01 | 2 |  | 2 | [20 empty] | 2020-09-02 | 2020-12-23 | 2020-09-25 | YES | Expedited | [8 empty] | 2021-02-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 4291 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2020-08-14 | 2020-09-04 | 16 | 14 | 2 | 2020-09-07 | 2020-09-15 | 6 |  | 6 | [20 empty] | 2020-09-17 | 2020-09-25 | 2020-10-05 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4284 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2020-08-12 | 2020-08-20 | 7 | 3 | 4 | 2020-08-21 | 2020-08-25 | 3 |  | 3 | [20 empty] | 2020-08-31 | 2020-09-09 | 2020-09-30 | YES | Expedited | [8 empty] | 2020-12-29 | In Operation | Res | Y
Fitchburg | Ashby | 4279 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2020-08-11 | [31 empty] | 2020-10-13 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 4273 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2020-08-06 | 2020-08-13 | 6 | 5 | 1 | 2020-08-13 | 2020-08-14 | 2 |  | 2 | [20 empty] | 2020-08-31 | 2020-09-09 | 2020-09-01 | YES | Expedited | [8 empty] | 2020-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 4267 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2020-08-05 | 2020-08-06 | 2 |  | 2 | 2020-08-07 | 2020-08-11 | 3 |  | 3 | [20 empty] | 2020-08-12 | 2020-08-17 | 2020-10-06 | YES | Expedited | [8 empty] | 2020-12-08 | In Operation | Res | Y
Fitchburg | Ashby | 4257 | 1431 | 6 |  |  | Solar |  | 39W19 | 2020-08-10 | 2020-08-11 | 2 |  | 2 | 2020-08-11 | 2020-08-11 | 1 |  | 1 | [20 empty] | 2020-08-24 | 2020-09-09 | 2020-08-10 | YES | Expedited | [8 empty] | 2020-10-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 4254 | 1420 | 12.15 |  |  | Solar |  | 35W36 | 2020-07-30 | 2020-09-30 | 44 | 40 | 4 | 2020-10-01 | 2020-10-07 | 5 |  | 5 | [20 empty] | 2020-10-29 | 2021-03-02 | 2020-09-30 | YES | Expedited | [8 empty] | 2021-03-11 | In Operation | Res | Y
Fitchburg | Townsend | 4241 | 1469 | 10 |  |  | Solar |  | 15W16 | 2020-07-21 | 2020-10-13 | 59 | 55 | 4 | 2020-10-13 | 2020-10-13 | 1 |  | 1 | [20 empty] | 2020-10-20 | 2020-10-21 | 2020-09-01 | YES | Expedited | [8 empty] | 2020-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4237 | 1420 | 2999 |  |  | Solar + Energy Storage |  | 25W28 | 2020-07-20 | 2020-08-10 | 16 | 8 | 8 | [10 empty] | 2020-08-14 | 2020-08-28 | 11 |  | 11 | 2020-09-18 | [12 empty] | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 4228 | 1462 | 24.4 |  |  | Solar + Energy Storage |  | 30W31 | 2020-07-10 | 2020-07-20 | 7 | 5 | 2 | 2020-08-13 | 2020-09-24 | [23 empty] | 2020-10-16 | 2021-02-09 | 2020-09-10 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4213 | 1420 | 245 |  |  | Solar + Energy Storage |  | 20H22 | 2020-06-29 | 2020-07-10 | 10 | 2 | 8 | [5 empty] | 2020-10-14 | 2020-11-16 | 23 |  | 23 | [17 empty] | 2020-09-15 | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 4204 | 1469 | 8 |  |  | Solar |  | 39W18 | 2020-06-15 | 2020-06-18 | 4 | 1 | 3 | 2020-06-19 | 2020-06-23 | 3 |  | 3 | [20 empty] | 2020-07-09 | 2020-07-20 | 2020-07-02 | YES | Expedited | [8 empty] | 2020-08-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 4192 | 1420 | 86.4 |  |  | Solar |  | 22W1 | 2020-06-24 | 2020-07-01 | 6 | 3 | 3 | 2020-07-02 | 2020-08-13 | 31 |  | 31 | [20 empty] | 2020-08-31 | 2020-09-11 | 2020-09-07 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 4178 | 1469 | 5.9 |  |  | Solar |  | 15W16 | 2020-05-26 | 2020-06-23 | 21 | 19 | 2 | 2018-06-24 | 2018-06-25 | 1 |  | 1 | [20 empty] | 2020-06-30 | 2020-07-06 | 2020-07-19 | YES | Expedited | [8 empty] | 2020-09-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 4176 | 1462 | 7 |  |  | Solar |  | 31W38 | 2020-05-28 | 2020-06-10 | 10 | 6 | 4 | 2020-06-11 | 2020-06-15 | 3 |  | 3 | [20 empty] | 2020-06-18 | 2020-06-22 | 2020-06-23 | YES | Expedited | [8 empty] | 2020-11-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4163 | 1462 | 10 |  |  | Solar |  | 31W37 | 2020-05-18 | 2020-05-21 | 4 | 2 | 2 | 2020-05-22 | 2020-05-26 | 2 |  | 2 | [20 empty] | 2020-05-28 | 2020-06-15 |  | YES | Expedited | [8 empty] | 2020-10-07 | In Operation | Res | Y
Fitchburg | Townsend | 4160 | 1474 | 10 |  |  | Solar |  | 39W19 | 2020-05-11 | 2020-05-15 | 5 | 2 | 3 | 2020-05-18 | 2020-05-18 | 1 |  | 1 | [20 empty] | 2020-05-27 | 2020-07-07 | 2020-07-10 | YES | Expedited | [8 empty] | 2020-08-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 4147 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2020-04-30 | 2020-07-02 | 45 | 34 | 11 | 2020-07-06 | 2020-07-09 | 4 |  | 4 | [20 empty] | 2020-07-16 | 2020-07-29 | 2020-06-30 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 4128 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2020-04-13 | 2020-04-20 | 5 | 4 | 1 | 2020-04-21 | 2020-04-21 | 1 |  | 1 | [20 empty] | 2020-05-07 | 2020-09-03 | 2020-06-13 | YES | Expedited | [8 empty] | 2020-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 4127 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2020-04-13 | 2020-04-21 | 6 | 4 | 2 | 2020-04-22 | 2020-04-23 | 2 |  | 2 | [20 empty] | 2020-05-15 | 2020-06-25 | 2020-06-13 | YES | Expedited | [8 empty] | 2020-07-13 | In Operation | Res | Y
Fitchburg | Ashby | 4122 | 1431 | 9.765 |  |  | Solar |  | 39W19 | 2020-04-09 | 2020-05-28 | 34 | 21 | 13 | 2020-06-03 | 2020-06-17 | 11 | 6 | 5 | [20 empty] | 2020-06-18 | 2020-07-20 |  | YES | Expedited | [8 empty] | 2020-08-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 4121 | 1462 | 5 |  |  | Solar |  | 30W30 | 2020-04-08 | 2020-05-15 | 27 | 22 | 5 | 2020-05-18 | 2020-05-18 | 1 |  | 1 | [20 empty] | 2020-07-17 | 2020-07-22 |  | YES | Expedited | [8 empty] | 2020-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 4118 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 | 2020-08-05 | 2020-06-03 | YES | Expedited | [8 empty] | 2020-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4117 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 |  | 2020-06-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4116 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2020-04-03 | 2020-04-09 | 5 | 3 | 2 | 2020-04-10 | 2020-04-13 | 2 |  | 2 | [20 empty] | 2020-04-23 |  | 2020-06-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 4115 | 1462 | 10 |  |  | Solar |  | 30W30 | 2020-04-03 | 2020-04-13 | 7 | 4 | 3 | 2020-04-13 | 2020-04-13 | 1 |  | 1 | [20 empty] | 2020-04-23 | 2020-09-25 | 2020-06-03 | YES | Expedited | [8 empty] | 2020-09-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 4113 | 1462 | 6.785 |  |  | Solar |  | 30W31 | 2020-04-03 | 2020-04-14 | 8 | 5 | 3 | 2020-04-15 | 2020-04-16 | 2 |  | 2 | [20 empty] | 2020-05-27 | 2020-07-20 |  | YES | Expedited | [8 empty] | 2020-08-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 4099 | 1420 | 4394 | 4394 | 0 | Solar + Energy Storage | Yes | 25W28 | 2020-03-13 | 2020-04-08 | 19 | 17 | 2 | [10 empty] | 2020-05-19 | 2020-05-19 | 0 |  | 0 | 2020-05-19 | 2020-09-10 | 81 | 1 | 80 | [5 empty] | 2020-11-06 | 2021-10-19 | 2019-10-01 | YES | Standard | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-09-12 | In Operation | Comm | N
Fitchburg | Fitchburg | 4092 | 1420 | 5.5 |  |  | Solar |  | 31W37 | 2020-03-13 | 2020-03-17 | 3 | 2 | 1 | 2020-03-18 | 2020-03-19 | 2 |  | 2 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-05-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 4091 | 1420 | 4.25 |  |  | Solar |  | 01W04 | 2020-03-13 | 2020-03-17 | 3 | 2 | 1 | 2020-03-18 | 2020-03-19 | 2 |  | 2 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-07-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 4089 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2020-03-11 | 2020-03-18 | 6 | 3 | 3 | 2020-03-19 | 2020-03-19 | 1 |  | 1 | [20 empty] | 2020-04-06 | 2020-08-12 | 2020-06-11 | YES | Expedited | [8 empty] | 2020-08-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 4069 | 1420 | 8.75 |  |  | Solar |  | 31W37 | 2020-03-07 | 2020-03-13 | 5 | 3 | 2 | 2020-03-16 | 2020-03-19 | 4 |  | 4 | [20 empty] | 2020-04-06 | 2020-04-27 | 2020-03-31 | YES | Expedited | [8 empty] | 2020-05-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 4051 | 1462 | 6 |  |  | Solar |  | 30W30 | 2020-02-24 | 2020-03-04 | 8 | 5 | 3 | 2020-03-06 | 2020-03-10 | 3 |  | 3 | [20 empty] | 2020-04-07 | 2020-04-20 | 2020-04-20 | YES | Expedited | [8 empty] | 2020-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 4044 | 1462 | 9.9 |  |  | Solar |  | 31W38 | 2020-02-13 | 2020-04-30 | 54 | 53 | 1 | 2020-05-01 | 2020-06-01 | 21 |  | 21 | [20 empty] | 2020-06-18 | 2020-11-24 | 2020-04-13 | YES | Expedited | [8 empty] | 2021-04-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 4043 | 1420 | 4.25 |  |  | Solar |  | 31W37 | 2020-02-18 | 2020-02-19 | 2 |  | 2 | 2020-02-20 | 2020-03-11 | 15 |  | 15 | [20 empty] | 2020-04-01 | 2020-04-13 | 2020-02-29 | YES | Expedited | [8 empty] | 2020-06-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 4038 | 1462 | 9.8 |  |  | Solar |  | 30W30 | 2020-02-12 | 2020-02-13 | 2 |  | 2 | 2020-02-14 | 2020-02-17 | 1 |  | 1 | [20 empty] | 2020-02-25 | 2020-03-12 | 2020-03-09 | YES | Expedited | [8 empty] | 2020-06-24 | In Operation | Res | Y
Fitchburg | Townsend | 4027 | 1469 | 5 |  |  | Solar |  | 15W17 | 2020-01-30 | 2020-02-04 | 4 |  | 4 | 2020-02-05 | 2020-02-10 | 4 |  | 4 | [20 empty] | 2020-02-13 | 2020-02-14 | 2020-02-29 | YES | Expedited | [8 empty] | 2020-03-31 | In Operation | Res | Y
Fitchburg | Ashby | 4022 | 1431 | 10 |  |  | Solar |  | 39W19 | 2020-01-23 | 2020-02-10 | 13 | 11 | 2 | 2020-02-11 | 2020-02-18 | 5 |  | 5 | [20 empty] | 2020-02-25 | 2020-03-10 | 2020-04-01 | YES | Expedited | [8 empty] | 2020-12-04 | In Operation | Res | Y
Fitchburg | Townsend | 4021 | 1469 | 10 |  |  | Solar |  | 39W18 | 2020-01-21 | 2020-01-23 | 3 |  | 3 | 2020-01-27 | 2020-01-28 | 2 |  | 2 | [20 empty] | 2020-02-03 | 2020-02-05 |  | YES | Expedited | [8 empty] | 2020-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 4017 | 1462 | 7.67 |  |  | Solar |  | 31W38 | 2020-01-20 | 2020-02-07 | 14 | 11 | 3 | 2020-02-10 | 2020-02-17 | 5 |  | 5 | [20 empty] | 2020-02-25 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 4013 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2020-01-23 | 2020-01-24 | 2 |  | 2 | 2020-01-27 | 2020-01-31 | 5 |  | 5 | [20 empty] | 2020-02-03 | 2020-02-07 |  | YES | Expedited | [8 empty] | 2020-06-05 | In Operation | Res | Y
Fitchburg | Ashby | 4005 | 1431 | 10 |  |  | Solar |  | 39W19 | 2019-12-24 | 2019-12-27 | 3 |  | 3 | 2019-12-30 | 2020-01-07 | 6 |  | 6 | [20 empty] | 2020-01-14 | 2020-01-16 | 2020-01-20 | YES | Expedited | [8 empty] | 2020-02-19 | In Operation | Res | Y
Fitchburg | Townsend | 3998 | 1474 | 5.76 |  |  | Solar |  | 39W18 | 2019-12-11 | 2019-12-18 | 6 | 3 | 3 | 2019-12-19 | 2019-12-24 | 4 |  | 4 | [20 empty] | 2020-01-07 | 2020-01-13 | 2020-02-11 | YES | Expedited | [8 empty] | 2020-06-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3993 | 1462 | 7.08 |  |  | Solar |  | 39W18 | 2019-12-26 | 2019-12-27 | 2 |  | 2 | 2019-12-30 | 2019-12-31 | 2 |  | 2 | [20 empty] | 2020-01-07 | 2020-02-04 |  | YES | Expedited | [8 empty] | 2020-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 3989 | 1469 | 10 |  |  | Solar |  | 39W18 | 2019-12-09 | 2019-12-09 | 1 |  | 1 | 2019-12-10 | 2019-12-12 | 3 |  | 3 | [20 empty] | 2019-12-17 | 2020-02-04 | 2020-01-03 | YES | Expedited | [8 empty] | 2020-03-04 | In Operation | Res | Y
Fitchburg | Ashby | 3988 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2019-12-09 | 2019-12-09 | 1 |  | 1 | 2019-12-10 | 2019-12-12 | 3 |  | 3 | [20 empty] | 2019-12-17 | 2019-12-27 |  | YES | Expedited | [8 empty] | 2020-04-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3987 | 1462 | 10 |  |  | Solar |  | 31W37 | [33 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3974 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2019-12-23 | 2020-01-21 | 19 | 19 | 0 | 2020-01-22 | 2020-01-23 | 2 |  | 2 | [20 empty] | 2020-01-28 | 2020-01-31 |  | YES | Expedited | [8 empty] | 2020-11-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3971 | 1420 | 10 |  |  | Solar |  | 35W36 | 2019-11-25 | 2019-11-26 | 2 |  | 2 | 2019-11-27 | 2019-12-04 | 6 |  | 6 | [20 empty] | 2020-01-14 | 2020-01-22 |  | YES | Expedited | [8 empty] | 2020-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 3956 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2019-11-13 | 2019-11-13 | 1 |  | 1 | 2019-11-14 | 2019-11-25 | 7 |  | 7 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3945 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2019-12-10 | 2019-12-11 | 2 |  | 2 | 2019-12-11 | 2019-12-11 | 1 |  | 1 | 2020-01-24 | 2020-02-10 | 12 |  | 12 | [15 empty] | 2020-02-13 | 2020-02-20 |  | YES | Expedited | [8 empty] | 2020-10-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3944 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2019-11-06 | 2019-11-07 | 2 |  | 2 | 2019-11-08 | 2019-11-13 | 3 |  | 3 | [20 empty] | 2019-11-19 | 2019-11-27 |  | YES | Expedited | [8 empty] | 2021-01-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3943 | 1462 | 5 |  |  | Solar |  | 31W38 | 2019-11-05 | 2019-11-07 | 3 |  | 3 | 2019-11-08 | 2019-11-13 | 3 |  | 3 | [20 empty] | 2019-11-19 | 2019-11-26 |  | YES | Expedited | [8 empty] | 2020-05-12 | In Operation | Res | Y
Fitchburg | Townsend | 3941 | 1469 | 6 |  |  | Solar |  | 15W17 | 2019-11-19 | 2019-11-26 | 5 |  | 5 | 2019-11-27 | 2019-12-04 | 6 |  | 6 | [20 empty] | 2020-01-28 | 2020-02-06 |  | YES | Expedited | [8 empty] | 2020-03-03 | In Operation | Res | Y
Fitchburg | Townsend | 3931 | 1474 | 7.6 |  |  | Solar |  | 39W18 | 2019-10-22 | 2019-10-22 | 1 |  | 1 | 2019-10-23 | 2019-10-29 | 5 |  | 5 | [20 empty] | 2019-11-01 | 2019-11-21 | 2019-12-19 | YES | Expedited | [8 empty] | 2020-07-08 | In Operation | Res | Y
Fitchburg | Townsend | 3927 | 1474 | 3.8 |  |  | Solar |  | 39W19 | 2019-11-05 | 2019-12-11 | 25 | 20 | 5 | 2019-12-12 | 2019-12-12 | 1 |  | 1 | [20 empty] | 2019-12-17 | 2020-01-10 |  | YES | Expedited | [8 empty] | 2020-02-20 | Cancelled | Res | Y
Fitchburg | Townsend | 3923 | 1469 | 6 |  |  | Solar |  | 39W18 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-12-10 | 2019-11-15 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3922 | 1474 | 10 |  |  | Solar |  | 39W18 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-05 | 2019-11-15 | YES | Expedited | [8 empty] | 2019-01-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3920 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-13 | 2019-11-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3915 | 1431 | 10 |  |  | Solar |  | 39W19 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-12 |  | YES | Expedited | [8 empty] | 2019-12-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3914 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2019-10-29 | 2019-11-12 | 10 | 6 | 4 | 2019-11-13 | 2019-11-25 | 8 |  | 8 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [8 empty] | 2020-06-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3913 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2019-10-16 | 2019-10-17 | 2 |  | 2 | 2019-10-18 | 2019-10-18 | 1 |  | 1 | [20 empty] | 2019-11-01 | 2019-11-13 |  | YES | Expedited | [8 empty] | 2020-08-18 | Cancelled | Res | Y
Fitchburg | Ashby | 3909 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-10-10 | 2019-10-14 | 3 |  | 3 | 2019-10-15 | 2019-10-21 | 5 |  | 5 | [20 empty] | 2019-12-10 | 2019-12-16 |  | YES | Expedited | [8 empty] | 2020-05-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 3896 | 1462 | 10 |  |  | Solar |  | 30W31 | 2019-09-24 | 2019-09-30 | 5 |  | 5 | 2019-09-30 | 2019-09-30 | 1 |  | 1 | [20 empty] | 2019-10-08 | 2019-10-16 | 2019-11-08 | YES | Expedited | [8 empty] | 2019-12-09 | In Operation | Res | Y
Fitchburg | Ashby | 3891 | 1431 | 4.75 |  |  | Solar |  | 39W19 | 2019-10-03 | 2019-10-04 | 2 |  | 2 | 2019-10-14 | 2019-10-15 | 2 |  | 2 | [20 empty] | 2019-10-18 | 2019-11-12 |  | YES | Expedited | [8 empty] | 2019-12-20 | In Operation |  | Y
Fitchburg | Lunenburg | 3889 | 1462 | 10.03 |  |  | Solar |  | 30W30 | 2019-09-20 | 2019-09-20 | 1 |  | 1 | 2019-09-23 | 2019-09-24 | 2 |  | 2 | [20 empty] | 2019-09-30 | 2019-10-04 | 2019-10-31 | YES | Expedited | [8 empty] | 2019-12-20 | In Operation | Res | Y
Fitchburg | Townsend | 3881 | 1474 | 7.6 |  |  | Solar |  | 39W18 | 2019-10-04 | 2019-10-11 | 5 |  | 5 | 2019-10-14 | 2019-10-14 | 1 |  | 1 | [20 empty] | 2019-10-18 | 2019-11-21 |  | YES | Expedited | [8 empty] | 2020-03-24 | In Operation |  | Y
Fitchburg | Fitchburg | 3871 | 1420 | 17.6 |  |  | Solar |  | 50W55 | 2019-09-04 | 2021-02-24 |  |  |  | 2021-02-24 | 2021-02-25 | 2 |  | 2 | [20 empty] | 2021-03-09 | 2021-03-18 | 2019-04-28 | YES | Expedited | [8 empty] | 2022-01-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 3870 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2019-09-11 | 2019-09-13 | 3 |  | 3 | 2019-09-13 | 2019-09-16 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-09-25 | 2019-10-29 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3869 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2019-09-23 | 2019-09-24 | 2 |  | 2 | [27 empty] | 2019-09-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3868 | 1462 | 11.4 |  |  | Solar |  | 30W31 | 2019-09-03 | 2019-09-05 | 2 |  | 2 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-13 | 2019-09-24 |  | YES | Expedited | [8 empty] | 2019-11-19 | In Operation | Res | Y
Fitchburg | Townsend | 3865 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2019-09-04 | 2019-09-05 | 2 |  | 2 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-12 | 2019-09-16 | YES | Expedited | [8 empty] | 2019-10-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 3863 | 1462 | 10 |  |  | Solar |  | 31W37 | 2019-09-06 | 2019-09-10 | 3 |  | 3 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-10-15 | 2019-10-29 | YES | Expedited | [8 empty] | 2020-04-24 | In Operation | Res | Y
Fitchburg | Ashby | 3858 | 1431 | 3.52 |  |  | Solar |  | 39W19 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | 2019-09-05 | 2019-09-05 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-16 | 2019-06-30 | YES | Expedited | [8 empty] | 2020-04-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 3855 | 1462 | 9.75 |  |  | Solar |  | 30W30 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | 2019-08-28 | 2019-08-28 | 1 |  | 1 | [20 empty] | 2019-09-04 | 2019-09-12 |  | YES | Expedited | [8 empty] | 2019-10-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3847 | 1420 | 10 |  |  | Solar |  | 01W04 | 2019-08-16 | 2019-08-21 | 4 |  | 4 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | [20 empty] | 2019-08-29 | 2019-08-30 |  | YES | Expedited | [8 empty] | 2020-01-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 3833 | 1462 | 4.5 |  |  | Solar |  | 30W30 | 2019-08-13 | 2019-08-14 | 2 |  | 2 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-09-20 |  | YES | Expedited | [8 empty] | 2019-10-22 | In Operation | Res | Y
Fitchburg | Ashby | 3829 | 1431 | 3.5 |  |  | Solar |  | 39W19 | 2019-08-27 | 2019-08-27 | 1 |  | 1 | 2019-08-28 | 2019-08-28 | 1 |  | 1 | [20 empty] | 2019-09-09 | 2019-11-25 | 2019-08-25 | YES | Expedited | [8 empty] | 2020-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 3823 | 1462 | 1000 |  |  | Solar + Energy Storage |  | 31W37 | 2019-07-31 | 2019-08-06 | 5 |  | 5 | [10 empty] | 2019-08-08 | 2019-08-30 | 17 |  | 17 | [14 empty] | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 3820 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2019-09-09 | 2019-09-10 | 2 |  | 2 | 2019-09-11 | 2019-09-12 | 2 |  | 2 | [20 empty] | 2019-09-19 | 2019-10-03 |  | YES | Expedited | [8 empty] | 2019-12-24 | In Operation |  | Y
Fitchburg | Lunenburg | 3807 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2019-07-31 | 2019-08-01 | 2 |  | 2 | 2019-08-06 | 2019-08-06 | 1 |  | 1 | [20 empty] | 2019-08-15 | 2019-08-29 | 2019-07-10 | YES | Expedited | [8 empty] | 2019-12-09 | In Operation | Res | Y
Fitchburg | Townsend | 3804 | 1469 | 1000 |  |  | Solar + Energy Storage |  | 39W18 | 2019-07-19 | 2019-07-23 | 3 |  | 3 | [10 empty] | 2019-07-25 | 2019-08-30 | 27 |  | 27 | 2019-09-17 | 2020-03-13 | 122 | 19 | 103 | [5 empty] | 2020-10-30 |  | 2019-07-14 |  | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 3796 | 1474 | 10 |  |  | Solar |  | 39W18 | 2019-08-08 | 2019-08-12 | 3 |  | 3 | 2019-08-13 | 2019-08-14 | 2 |  | 2 | [20 empty] | 2019-08-15 | 2019-09-24 |  | YES | Expedited | [8 empty] | 2019-11-21 | In Operation |  | Y
Fitchburg | Lunenburg | 3795 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2019-07-22 | 2019-07-22 | 1 |  | 1 | 2019-07-23 | 2019-07-23 | 1 |  | 1 | [20 empty] | 2019-08-02 | 2019-08-15 | 2019-07-16 | YES | Expedited | [8 empty] | 2019-08-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 3794 | 1420 | 6 |  |  | Solar |  | 31W37 | 2019-07-18 | 2019-07-18 | 1 |  | 1 | 2019-07-19 | 2019-07-19 | 1 |  | 1 | [20 empty] | 2019-07-24 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3786 | 1420 | 6 |  |  | Solar |  | 25W27 | 2019-07-16 | 2021-03-08 |  |  |  | 2021-03-08 | 2021-03-08 | 1 |  | 1 | [20 empty] | 2021-03-15 | 2021-03-25 |  | YES | Expedited | [8 empty] | 2021-05-25 | In Operation |  | Y
Fitchburg | Townsend | 3785 | 1474 | 10 |  |  | Solar |  | 39W18 | 2019-07-17 | 2019-07-18 | 2 |  | 2 | 2019-07-19 | 2019-07-19 | 1 |  | 1 | [20 empty] | 2019-07-24 | 2019-07-29 |  | YES | Expedited | [8 empty] | 2019-08-16 | In Operation | Res | Y
Fitchburg | Townsend | 3770 | 1474 | 10 |  |  | Solar |  | 39W18 | 2019-07-02 | 2019-07-08 | 4 |  | 4 | 2019-07-09 | 2019-07-11 | 3 |  | 3 | [20 empty] | 2019-07-18 | 2019-08-28 |  | YES | Expedited | [8 empty] | 2019-11-25 | In Operation | Res | Y
Fitchburg | Townsend | 3768 | 1469 | 9.6 |  |  | Solar |  | 15W17 | 2019-07-01 | 2019-07-08 | 5 |  | 5 | 2019-07-09 | 2019-07-11 | 3 |  | 3 | [20 empty] | 2019-07-18 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3765 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2019-06-26 | [33 empty] | Expedited | [9 empty] | Cancelled |  | Y
Fitchburg | Lunenburg | 3751 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2019-06-21 | 2019-06-24 | 2 |  | 2 | 2019-06-25 | 2019-06-27 | 3 |  | 3 | [20 empty] | 2019-07-08 | 2019-07-10 | 2019-07-22 | YES | Expedited | [8 empty] | 2020-12-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 3750 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2019-06-24 | 2019-06-25 | 2 |  | 2 | 2019-06-26 | 2019-06-27 | 2 |  | 2 | [20 empty] | 2019-07-08 | 2019-11-20 | 2019-08-18 | YES | Expedited | [8 empty] | 2019-12-12 | In Operation | Res | Y
Fitchburg | Ashby | 3739 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2019-07-02 | 2019-07-09 | 5 |  | 5 | 2019-07-10 | 2019-07-10 | 1 |  | 1 | [20 empty] | 2019-07-18 | 2019-07-26 |  | YES | Expedited | [8 empty] | 2019-08-07 | In Operation |  | Y
Fitchburg | Townsend | 3738 | 1474 | 7.6 |  |  | Solar |  | 39W18 | 2019-06-12 | 2019-06-13 | 2 |  | 2 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-07-22 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 3722 | 1420 | 7.6 |  |  | Solar |  | 40W42 | 2019-06-10 | 2019-06-11 | 2 |  | 2 | 2020-04-04 | 2020-04-13 | 6 |  | 6 | [20 empty] | 2020-04-13 | 2020-04-20 | 2019-07-31 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3720 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-06-04 | 2019-06-04 | 1 |  | 1 | 2019-06-04 | 2019-06-04 | 1 |  | 1 | [20 empty] | 2019-06-14 | 2019-06-11 | 2019-03-21 | YES | Expedited | [8 empty] | 2019-06-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3718 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2019-06-17 | 2019-06-18 | 1 |  | 1 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-07-01 | 2019-07-10 | YES | Expedited | [8 empty] | 2019-08-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3714 | 1462 | 10.62 |  |  | Solar |  | 30W31 | 2019-05-31 | 2019-06-03 | 2 |  | 2 | 2019-06-04 | 2019-06-05 | 2 |  | 2 | [20 empty] | 2019-06-10 | 2019-06-17 | 2019-08-02 | YES | Expedited | [8 empty] | 2019-08-13 | In Operation |  | Y
Fitchburg | Fitchburg | 3712 | 1420 | 9.86 |  |  | Solar |  | 01W04 | 2019-06-03 | 2019-06-04 | 2 |  | 2 | 2019-06-05 | 2019-06-05 | 1 |  | 1 | [20 empty] | 2019-06-10 | 2019-06-17 |  | YES | Expedited | [8 empty] | 2019-07-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3700 | 1462 | 20 |  |  | Solar |  | 31W38 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | 2019-05-22 | 2019-06-21 | 21 | 12 | 9 | [20 empty] | 2019-06-25 | 2019-07-02 |  | YES | Expedited | [8 empty] | 2019-10-11 | In Operation |  | Y
Fitchburg | Ashby | 3698 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-06-18 | 2019-06-18 | 1 |  | 1 | 2019-06-19 | 2019-06-21 | 3 |  | 3 | [20 empty] | 2019-06-25 | 2019-08-27 |  | YES | Expedited | [8 empty] | 2019-10-25 | In Operation | Res | Y
Fitchburg | Townsend | 3696 | 1469 | 8.26 |  |  | Solar |  | 39W18 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | 2019-05-30 | 2019-06-05 | 5 |  | 5 | [20 empty] | 2019-06-10 | 2019-06-18 |  | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Ashby | 3687 | 1431 | 6 |  |  | Solar |  | 39W19 | 2019-05-07 | 2019-05-09 | 3 |  | 3 | 2019-05-10 | 2019-05-21 | 8 |  | 8 | [20 empty] | 2019-05-22 | 2019-06-03 |  | YES | Expedited | [8 empty] | 2019-08-06 | In Operation |  | Y
Fitchburg | Ashby | 3685 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-05-07 | 2019-05-10 | 4 |  | 4 | 2019-05-13 | 2019-05-29 | 12 |  | 12 | [20 empty] | 2019-06-04 | 2019-06-19 | 2019-05-27 | YES | Expedited | [8 empty] | 2019-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3684 | 1462 | 9.95 |  |  | Solar |  | 30W31 | 2019-05-14 | 2019-05-14 | 1 |  | 1 | 2019-05-15 | 2019-05-21 | 5 |  | 5 | [20 empty] | 2019-05-22 | 2019-06-06 |  | YES | Expedited | [8 empty] | 2019-11-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3682 | 1420 | 8.64 |  |  | Solar |  | 25W27 | 2019-05-14 | 2019-05-17 | 4 |  | 4 | 2019-07-11 | 2019-07-11 | 1 |  | 1 | [20 empty] | 2019-07-18 | 2019-11-12 | 2019-06-04 | YES | Expedited | [8 empty] | 2020-02-10 | In Operation | Res | Y
Fitchburg | Ashby | 3681 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-05-14 | 2019-05-17 | 4 |  | 4 | 2019-05-20 | 2019-05-21 | 2 |  | 2 | [22 empty] | 2019-03-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3667 | 1420 | 10 |  |  | Solar |  | 25W28 | 2019-05-10 | 2019-05-16 | 5 |  | 5 | 2021-03-02 | 2021-03-05 | 4 |  | 4 | [20 empty] | 2021-03-15 |  | 2019-05-10 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3665 | 1420 | 7.6 |  |  | Solar |  | 25W28 | 2019-04-26 | 2019-04-29 | 2 |  | 2 | 2019-04-30 | 2019-05-21 | 16 |  | 16 | [20 empty] | 2019-05-22 | 2019-05-30 | 2019-05-26 | YES | Expedited | [8 empty] | 2019-08-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3664 | 1462 | 6 |  |  | Solar |  | 31W38 | 2019-04-29 | 2019-04-30 | 2 |  | 2 | 2019-05-01 | 2019-05-08 | 6 |  | 6 | [20 empty] | 2019-05-15 | 2019-05-20 | 2019-05-26 | YES | Expedited | [8 empty] | 2019-07-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3663 | 1462 | 5 |  |  | Solar |  | 31W37 | 2019-04-29 | 2019-05-08 | 8 | 5 | 3 | 2019-05-09 | 2019-05-15 | 5 |  | 5 | [20 empty] | 2019-05-22 | 2019-05-30 |  | YES | Expedited | [8 empty] | 2019-06-17 | In Operation |  | Y
Fitchburg | Lunenburg | 3649 | 1462 | 9.1 |  |  | Solar |  | 30W31 | 2019-04-26 | 2019-04-29 | 2 |  | 2 | 2019-04-30 | 2019-05-21 | 16 | 5 | 11 | [20 empty] | 2019-05-22 | 2019-06-24 | 2019-05-30 | YES | Expedited | [8 empty] | 2019-07-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3646 | 1462 | 9.145 |  |  | Solar |  | 30W31 | 2019-04-20 | 2019-04-22 | 1 |  | 1 | 2019-04-23 | 2019-04-24 | 2 |  | 2 | [20 empty] | 2019-05-22 | 2019-05-30 | 2019-05-30 | YES | Expedited | [8 empty] | 2019-08-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3645 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2019-04-25 | 2019-04-29 | 3 |  | 3 | 2019-04-30 | 2019-05-08 | 7 |  | 7 | [20 empty] | 2019-05-15 | 2019-06-24 | 2019-05-17 | YES | Expedited | [8 empty] | 2019-10-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3643 | 1420 | 3 |  |  | Solar |  | 25W27 | 2019-04-18 | 2019-04-19 | 2 |  | 2 | [27 empty] | 2019-05-17 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3624 | 1469 | 5 |  |  | Solar |  | 39W18 | 2019-04-30 | 2019-04-30 | 1 |  | 1 | 2019-05-01 | 2019-05-06 | 4 |  | 4 | [20 empty] | 2019-06-26 | 2019-07-09 | 2019-05-03 | YES | Expedited | [8 empty] | 2019-09-03 | In Operation | Res | Y
Fitchburg | Townsend | 3616 | 1474 | 7.38 |  |  | Solar |  | 39W18 | 2019-04-12 | 2019-04-12 | 1 |  | 1 | 2019-04-15 | 2019-04-16 | 1 |  | 1 | [20 empty] | 2019-04-18 | 2019-04-23 |  | YES | Expedited | [8 empty] | 2020-12-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 3583 | 1462 | 6 |  |  | Solar |  | 30W30 | 2019-03-14 | 2019-03-15 | 2 |  | 2 | 2019-03-16 | 2019-03-28 | 9 |  | 9 | [20 empty] | 2019-04-02 | 2019-05-06 | 2019-04-13 | YES | Expedited | [8 empty] | 2019-09-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 3580 | 1420 | 5 |  |  | Solar |  | 01W04 | 2019-03-13 | 2019-03-15 | 3 |  | 3 | 2019-03-16 | 2019-03-25 | 6 |  | 6 | [20 empty] | 2019-03-27 | 2019-04-02 | 2019-03-20 | YES | Expedited | [8 empty] | 2019-05-23 | In Operation | Res | Y
Fitchburg | Ashby | 3574 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-03-05 | 2019-03-05 | 1 |  | 1 | 2019-03-06 | 2019-03-13 | 6 |  | 6 | [20 empty] | 2019-03-15 | 2019-03-20 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-04-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3573 | 1420 | 0 |  |  | Solar + Energy Storage |  | 35W36 | 2019-03-01 | 2019-03-01 | 1 |  | 1 | [10 empty] | 2019-03-05 | 2019-03-05 | 1 |  | 1 | 2019-05-22 | 2019-11-12 | 119 | 49 | 70 | [5 empty] | 2020-01-02 | 2020-12-21 | 2019-07-01 | YES | Standard | [8 empty] | 2024-04-26 | Cancelled | Comm
Fitchburg | Ashby | 3570 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-02-28 | 2019-03-01 | 2 |  | 2 | 2019-03-07 | 2019-03-13 | 5 |  | 5 | [20 empty] | 2019-03-15 | 2019-06-28 | 2019-03-19 | YES | Expedited | [8 empty] | 2019-07-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 3565 | 1420 | 6 |  |  | Solar |  | 25W27 | 2019-02-27 | 2019-02-28 | 2 |  | 2 | 2019-03-01 | 2019-03-04 | 2 |  | 2 | [20 empty] | 2019-03-14 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3562 | 1462 | 10 |  |  | Solar |  | 30W31 | 2019-02-28 | 2019-02-28 | 1 |  | 1 | 2019-03-07 | 2019-03-13 | 5 |  | 5 | [20 empty] | 2019-03-15 | 2019-07-02 | 2019-03-19 | YES | Expedited | [8 empty] | 2019-08-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3561 | 1420 | 11.4 |  |  | Solar |  | 35W36 | 2019-02-22 | 2019-02-25 | 1 |  | 1 | 2019-02-26 | 2019-03-04 | 4 |  | 4 | [20 empty] | 2019-03-12 | 2019-03-20 | 2019-05-01 | YES | Expedited | [8 empty] | 2019-05-16 | In Operation | Res | Y
Fitchburg | Ashby | 3560 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2019-02-28 | 2019-03-01 | 2 |  | 2 | 2019-03-01 | 2019-03-04 | 2 |  | 2 | [20 empty] | 2019-03-13 | 2019-04-01 | 2019-03-21 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3551 | 1462 | 6 |  |  | Solar |  | 30W31 | 2019-02-21 | 2019-02-21 | 1 |  | 1 | 2019-02-22 | 2019-02-28 | 3 |  | 3 | [20 empty] | 2019-03-12 | 2019-03-27 | 2019-03-02 | YES | Expedited | [8 empty] | 2019-05-13 | In Operation | Res | Y
Fitchburg | Townsend | 3542 | 1474 | 10 |  |  | Solar |  | 39W18 | 2019-02-05 | 2019-02-05 | 1 |  | 1 | 2019-02-06 | 2019-02-14 | 7 |  | 7 | [20 empty] | 2019-02-21 | 2019-02-26 | 2019-02-18 | YES | Expedited | [8 empty] | 2019-04-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 3535 | 1420 | 9.8 |  |  | Solar |  | 35W36 | 2019-02-01 | 2019-02-01 | 1 |  | 1 | 2019-02-04 | 2019-02-04 | 1 |  | 1 | [20 empty] | 2019-02-15 | 2019-03-01 | 2019-03-28 | YES | Expedited | [8 empty] | 2020-02-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3531 | 1420 | 8.5 |  |  | Solar |  | 50W51 | 2019-02-06 | 2019-02-06 | 1 |  | 1 | 2019-02-07 | 2019-05-08 | 61 | 60 | 1 | [20 empty] | 2020-12-09 |  | 2019-03-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3518 | 1420 | 6.4 |  |  | Solar |  | 31W37 | 2019-01-18 | 2019-02-01 | 11 | 6 | 5 | 2019-02-04 | 2019-02-04 | 1 |  | 1 | [20 empty] | 2019-02-15 | 2019-03-25 |  | YES | Expedited | [8 empty] | 2018-03-27 | In Operation |  | Y
Fitchburg | Lunenburg | 3517 | 1462 | 6 |  |  | Solar |  | 30W31 | 2019-01-17 | 2019-01-17 | 1 |  | 1 | 2019-01-17 | 2019-01-21 | 3 |  | 3 | [20 empty] | 2019-01-24 | 2019-02-11 |  | YES | Expedited | [8 empty] | 2019-05-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 3514 | 1420 | 7.6 |  |  | Solar |  | 20H22 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-21 | 3 |  | 3 | [20 empty] | 2019-04-10 |  | 2019-02-16 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3507 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-17 | 1 |  | 1 | [20 empty] | 2019-01-22 |  | 2019-03-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3506 | 1469 | 10 |  |  | Solar |  | 39W18 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-17 | 1 |  | 1 | [20 empty] | 2019-01-22 | 2019-08-29 | 2019-03-09 | YES | Expedited | [8 empty] | 2019-08-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3505 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | 2019-01-16 | 2019-01-16 | 0 |  | 0 | [20 empty] | 2019-01-22 |  | 2019-03-09 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3501 | 1420 | 7.6 |  |  | Solar |  | 25W28 | 2019-01-14 | 2019-01-14 | 1 |  | 1 | 2019-01-15 | 2019-01-15 | 1 |  | 1 | [20 empty] | 2019-01-22 | 2019-02-12 | 2019-02-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3498 | 1469 | 5 |  |  | Solar |  | 39W18 | 2019-01-04 | 2019-01-04 | 1 |  | 1 | 2019-01-07 | 2019-01-07 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2019-02-13 |  | YES | Expedited | [8 empty] | 2019-03-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 3493 | 1462 | 3.8 |  |  | Solar |  | 30W30 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-09 | 2019-08-02 | 2019-02-28 | YES | Expedited | [8 empty] | 2019-08-09 | In Operation | Res | Y
Fitchburg | Townsend | 3492 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-10 | 2019-01-24 | 2018-01-27 | YES | Expedited | [8 empty] | 2019-03-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 3490 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2019-01-02 | 2019-01-02 | 1 |  | 1 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-09 | 2019-04-25 | 2019-02-21 | YES | Expedited | [8 empty] | 2019-08-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 3489 | 1462 | 10 |  |  | Solar |  | 30W30 | 2018-12-26 | 2018-12-27 | 2 |  | 2 | 2018-12-28 | 2019-01-03 | 4 |  | 4 | [20 empty] | 2019-01-09 |  | 2019-02-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3486 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2019-01-02 | 2019-01-03 | 2 |  | 2 | 2019-01-03 | 2019-01-03 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2019-02-06 | 2018-01-14 | YES | Expedited | [8 empty] | 2019-10-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 3485 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2018-12-20 | 2018-12-20 | 1 |  | 1 | 2018-12-21 | 2019-01-09 | 12 |  | 12 | 2018-03-29 | 2019-05-08 | 277 |  | 277 | [15 empty] | 2020-12-09 |  | 2019-02-19 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 3481 | 1469 | 5 |  |  | Solar |  | 39W18 | 2018-12-26 | 2018-12-27 | 2 |  | 2 | 2018-12-28 | 2019-01-02 | 3 |  | 3 | [20 empty] | 2019-01-09 | 2019-02-28 | 2019-01-18 | YES | Expedited | [8 empty] | 2019-03-22 | In Operation | Res | Y
Fitchburg | Ashby | 3478 | 1431 | 10 |  |  | Solar |  | 39W19 | 2018-12-19 | 2018-12-19 | 1 |  | 1 | 2018-12-21 | 2019-01-09 | 12 |  | 12 | [20 empty] | 2019-01-11 | 2019-02-13 |  | YES | Expedited | [8 empty] | 2019-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 3470 | 1462 | 5.5 |  |  | Solar |  | 30W31 | 2018-12-17 | 2018-12-17 | 1 |  | 1 | 2018-12-18 | 2018-12-21 | 4 |  | 4 | [20 empty] | 2018-12-28 | 2019-03-05 | 2019-01-14 | YES | Expedited | [8 empty] | 2019-03-15 | In Operation | Res | Y
Fitchburg | Townsend | 3469 | 1469 | 7.67 |  |  | Solar |  | 39W18 | 2018-12-17 | 2018-12-18 | 2 |  | 2 | 2018-12-19 | 2018-12-21 | 3 |  | 3 | [20 empty] | 2018-12-28 | 2019-01-14 | 2019-02-05 | YES | Expedited | [8 empty] | 2019-06-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3464 | 1420 | 8.36 |  |  | Solar |  | 20W22 | 2018-12-10 | 2018-12-17 | 6 | 1 | 5 | 2018-12-18 | 2019-01-09 | 15 |  | 15 | 2019-03-11 | 2019-04-09 | 22 |  | 22 | [15 empty] | 2020-09-29 | 2020-11-03 | 2019-01-07 | YES | Expedited | [8 empty] | 2020-11-09 | In Operation | Res | Y
Fitchburg | Townsend | 3462 | 1469 | 10.75 |  |  | Solar |  | 15W17 | 2018-12-10 | 2019-01-09 | 21 | 18 | 3 | 2019-01-09 | 2019-01-09 | 1 |  | 1 | [20 empty] | 2019-01-11 | 2020-04-27 | 2018-01-20 | YES | Expedited | [8 empty] | 2021-01-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 3457 | 1420 | 7 |  |  | Solar |  | 50W51 | 2018-12-20 | 2018-12-21 | 2 |  | 2 | 2018-12-21 | 2019-01-09 | 12 | 1 | 11 | 2019-04-10 | 2019-05-08 | 20 |  | 20 | [15 empty] | 2020-12-15 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3444 | 1420 | 10 |  |  | Solar |  | 50W51 | 2018-11-14 | 2018-12-06 | 16 | 12 | 4 | 2018-12-07 | 2019-01-09 | 22 | 20 | 2 | 2019-03-29 | 2019-05-08 | 28 |  | 28 | [15 empty] | 2019-05-08 |  | 2018-01-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3440 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2018-11-12 | 2018-12-06 | 18 | 14 | 4 | 2018-12-07 | 2019-01-09 | 22 | 16 | 6 | 2019-03-29 | 2019-05-08 | 28 |  | 28 | [15 empty] | 2019-05-08 |  | 2018-01-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3438 | 1420 | 9.86 |  |  | Solar |  | 20W22 | 2018-11-07 | 2018-11-14 | 6 | 2 | 4 | 2018-11-20 | 2019-01-04 | 31 | 24 | 7 | 2019-03-11 | 2019-04-09 | 22 |  | 22 | [15 empty] | 2020-09-29 | 2020-10-02 |  | YES | Expedited | [8 empty] | 2020-11-20 | In Operation | Res | Y
Fitchburg | Townsend | 3437 | 1474 | 10 |  |  | Solar |  | 39W18 | 2018-11-08 | 2018-11-13 | 4 | 1 | 3 | 2018-11-14 | 2018-12-10 | 18 | 15 | 3 | [20 empty] | 2018-12-26 | 2019-06-26 | 2018-12-10 | YES | Expedited | [8 empty] | 2019-07-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 3436 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2018-11-08 | 2018-11-13 | 4 | 1 | 3 | 2018-11-14 | 2018-12-06 | 16 | 11 | 5 | [20 empty] | 2018-12-10 | 2019-01-18 | 2018-12-10 | YES | Expedited | [8 empty] | 2019-01-22 | In Operation | Res | Y
Fitchburg | Townsend | 3432 | 1469 | 5 |  |  | Solar |  | 39W18 | 2018-11-01 | 2018-11-14 | 10 | 5 | 5 | 2018-11-15 | 2018-12-10 | 17 | 14 | 3 | [20 empty] | 2018-12-10 |  | 2018-12-01 | NO | Expedited | [8 empty] | 2019-02-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3426 | 1420 | 6 |  |  | Solar |  | 20W22 | 2018-10-31 | 2018-11-02 | 3 |  | 3 | 2018-11-05 | 2018-11-19 | 11 | 9 | 2 | [20 empty] | 2018-11-29 | 2018-11-03 | 2018-12-31 | YES | Expedited | [8 empty] | 2019-01-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3424 | 1462 | 10 |  |  | Solar |  | 31W37 | 2018-10-29 | 2018-11-01 | 4 |  | 4 | 2018-11-02 | 2018-12-10 | 26 | 11 | 15 | [20 empty] | 2018-12-19 | 2019-01-22 | 2018-11-08 | YES | Expedited | [8 empty] | 2019-01-25 | In Operation | Res | Y
Fitchburg | Townsend | 3423 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2018-10-25 | 2018-10-26 | 2 |  | 2 | 2018-10-30 | 2018-12-06 | 27 | 12 | 15 | [20 empty] | 2018-12-10 | 2019-01-14 | 2018-11-25 | YES | Expedited | [8 empty] | 2019-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 3410 | 1420 | 10 |  |  | Solar |  | 50W51 | 2018-10-15 | 2018-10-22 | 6 | 3 | 3 | 2018-10-22 | 2018-11-26 | 25 | 17 | 8 | [20 empty] | 2018-11-27 |  | 2018-11-20 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3409 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2018-10-12 | 2018-10-12 | 1 |  | 1 | 2018-10-15 | 2018-10-15 | 1 |  | 1 | [20 empty] | 2018-11-27 | 2018-12-05 | 2018-11-18 | YES | Expedited | [8 empty] | 2019-01-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3400 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2018-10-04 | 2018-10-08 | 2 |  | 2 | 2018-10-09 | 2018-10-09 | 1 |  | 1 | [20 empty] | 2018-10-12 |  | 2018-10-31 | NO | Expedited | [8 empty] | 2019-01-11 | In Operation | Res | Y
Fitchburg | Townsend | 3399 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2018-10-03 | 2018-10-15 | 8 | 6 | 2 | 2018-10-15 | 2018-10-16 | 2 |  | 2 | [20 empty] | 2018-10-30 |  | 2018-10-30 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Ashby | 3387 | 1431 | 6 |  |  | Solar |  | 39W19 | 2018-10-01 | 2018-10-01 | 1 |  | 1 | 2018-10-02 | 2018-10-04 | 3 |  | 3 | [20 empty] | 2018-10-11 |  | 2018-10-24 | NO | Expedited | [8 empty] | 2018-11-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 3384 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-09-27 | 2018-10-01 | 3 |  | 3 | 2018-10-02 | 2018-10-03 | 2 |  | 2 | [20 empty] | 2018-10-19 | 2019-10-15 | 2018-11-24 | YES | Expedited | [8 empty] | 2019-10-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3378 | 1462 | 7.6 |  |  | Solar |  | 31W34 | 2018-09-27 | 2018-10-01 | 3 |  | 3 | 2018-10-02 | 2018-10-04 | 3 |  | 3 | [20 empty] | 2018-10-11 | 2021-02-26 | 2018-11-19 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3375 | 1462 | 10.95 |  |  | Solar |  | 31W37 | 2018-09-24 | 2018-09-25 | 2 |  | 2 | 2018-09-25 | 2018-09-26 | 2 |  | 2 | 2019-01-07 | 2019-02-01 | 19 |  | 19 | [15 empty] | 2019-02-15 | 2019-04-01 |  | YES | Expedited | [8 empty] | 2019-05-09 | In Operation | Res | Y
Fitchburg | Ashby | 3369 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2018-09-10 | 2018-09-25 | 12 | 6 | 6 | 2018-09-25 | 2018-09-25 | 1 |  | 1 | [20 empty] | 2018-09-28 | 2018-12-05 |  | YES | Expedited | [8 empty] | 2018-12-18 | In Operation | Res | Y
Fitchburg | Ashby | 3367 | 1431 | 8.12 |  |  | Solar |  | 39W19 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | 2018-09-10 | 2018-09-17 | 6 |  | 6 | [20 empty] | 2018-09-24 |  |  | NO | Expedited | [8 empty] | 2018-11-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3363 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2018-08-30 | 2018-09-10 | 7 | 3 | 4 | 2018-09-10 | 2018-09-17 | 6 |  | 6 | [20 empty] | 2018-09-24 | 2019-09-23 | 2018-10-30 | YES | Expedited | [8 empty] | 2019-10-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3361 | 1469 | 6 |  |  | Solar |  | 30W31 | 2018-10-01 | 2018-10-01 | 1 |  | 1 | 2018-10-03 | 2018-10-03 | 1 |  | 1 | [20 empty] | 2018-10-19 | 2019-01-24 | 2018-09-30 | YES | Expedited | [8 empty] | 2019-02-01 | In Operation | Res | Y
Fitchburg | Ashby | 3358 | 1431 | 7.68 |  |  | Solar |  | 39W19 | 2018-08-29 | 2018-09-06 | 6 | 2 | 4 | 2018-09-05 | 2018-09-10 | 4 |  | 4 | [20 empty] | 2021-09-07 | 2021-09-29 | 2018-09-07 | YES | Expedited | [8 empty] | 2021-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3353 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2018-08-24 | 2018-08-31 | 6 | 4 | 2 | 2018-09-03 | 2018-09-05 | 2 |  | 2 | [20 empty] | 2018-09-12 |  | 2018-09-21 | NO | Expedited | [8 empty] | 2018-10-24 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3350 | 1462 | 10 |  |  | Solar |  | 31W38 | 2018-08-21 | 2018-08-28 | 6 | 3 | 3 | 2018-08-28 | 2018-08-28 | 1 |  | 1 | [20 empty] | 2018-08-31 | 2019-05-13 | 2018-09-18 | YES | Expedited | [8 empty] | 2019-07-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3346 | 1462 | 10.6 |  |  | Solar |  | 31W38 | 2018-08-17 | 2018-09-07 | 15 | 12 | 3 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | [20 empty] | 2018-09-12 | 2019-02-05 | 2018-09-18 | YES | Expedited | [8 empty] | 2018-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3345 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2018-08-14 | 2018-08-16 | 3 |  | 3 | 2018-08-29 | 2018-08-29 | 1 |  | 1 | [20 empty] | 2018-08-31 | 2019-03-01 | 2018-10-13 | YES | Expedited | [8 empty] | 2019-04-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3344 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2018-08-13 | 2018-08-15 | 3 |  | 3 | 2018-08-16 | 2018-08-29 | 10 | 8 | 2 | [20 empty] | 2018-08-31 |  | 2018-10-11 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3341 | 1462 | 10 |  |  | Solar |  | 31W38 | 2018-08-08 | 2018-09-10 | 23 | 18 | 5 | 2018-09-11 | 2018-09-17 | 5 |  | 5 | [20 empty] | 2018-09-24 | 2019-07-01 | 2018-10-08 | YES | Expedited | [8 empty] | 2019-08-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 3340 | 1420 | 6 |  |  | Solar |  | 01W04 | 2018-08-07 | 2018-08-15 | 7 |  | 7 | 2018-08-20 | 2018-08-21 | 2 | 1 | 1 | [20 empty] | 2018-09-13 |  | 2018-09-15 | NO | Expedited | [8 empty] | 2018-10-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3336 | 1462 | 6.6 |  |  | Solar |  | 30W31 | 2018-09-24 | 2018-09-25 | 2 |  | 2 | 2018-09-25 | 2018-09-25 | 1 |  | 1 | [20 empty] | 2018-10-01 | 2019-02-27 | 2018-09-08 | YES | Expedited | [8 empty] | 2019-03-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 3335 | 1420 | 5 |  |  | Solar |  | 01W04 | 2018-08-06 | 2018-08-10 | 5 |  | 5 | 2018-09-07 | 2018-09-10 | 2 |  | 2 | [20 empty] | 2018-09-12 | 2019-02-06 | 2018-09-08 | YES | Expedited | [8 empty] | 2018-12-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3333 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-08-01 | 2018-08-14 | 10 | 4 | 6 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-09-06 | NO | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3329 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-07-31 | 2018-08-14 | 11 | 8 | 3 | 2018-09-21 | 2018-09-21 | 1 |  | 1 | [20 empty] | 2018-09-24 | 2019-09-23 |  | YES | Expedited | [8 empty] | 2020-04-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3325 | 1420 | 10 |  |  | Solar |  | 01W04 | 2018-07-26 | 2018-07-30 | 3 |  | 3 | 2018-10-09 | 2018-10-09 | 1 |  | 1 | [20 empty] | 2018-10-11 | 2019-04-26 | 2018-10-28 | YES | Expedited | [8 empty] | 2019-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3320 | 1420 | 10 |  |  | Solar |  | 01W04 | 2018-07-25 | 2018-07-30 | 4 |  | 4 | 2018-08-06 | 2018-08-06 | 1 |  | 1 | [20 empty] | 2018-08-07 |  | 2018-09-01 | NO | Expedited | [8 empty] | 2018-09-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3318 | 1420 | 8.36 |  |  | Solar |  | 25W27 | 2018-07-25 | 2018-07-30 | 4 |  | 4 | 2018-08-21 | 2018-08-21 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-08-26 | NO | Expedited | [8 empty] | 2018-10-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3316 | 1462 | 999 | 999 | 0 | Solar + Energy Storage | Yes | 31W38 | 2018-08-27 | 2018-09-06 | 8 |  | 8 | [5 empty] | 2018-09-27 | 2018-11-28 | 43 |  | 43 | [5 empty] | 2018-12-20 | 2019-04-23 | 82 |  | 82 | [5 empty] | 2019-05-23 | 2020-05-18 |  | YES | Standard | [8 empty] | 2021-12-28 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3315 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-07-21 | 2018-08-06 | 11 | 3 | 8 | 2018-08-07 | 2018-08-10 | 4 |  | 4 | [20 empty] | 2018-08-14 | 2019-03-25 | 2018-09-20 | YES | Expedited | [8 empty] | 2019-07-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 3314 | 1420 | 6.4 |  |  | Solar |  | 50W51 | 2018-07-21 | 2018-07-30 | 6 | 1 | 5 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  | 2018-08-10 | NO | Expedited | [8 empty] | 2018-11-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3309 | 1462 | 8.7 |  |  | Solar |  | 30W30 | 2018-07-18 | 2018-08-14 | 20 | 10 | 10 | 2018-08-15 | 2018-08-15 | 1 |  | 1 | [20 empty] | 2018-08-23 |  |  | NO | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3304 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2018-07-13 | 2018-07-18 | 4 |  | 4 | 2018-08-10 | 2018-08-10 | 1 |  | 1 | [20 empty] | 2018-08-14 | 2019-11-22 | 2018-09-13 | YES | Expedited | [8 empty] | 2020-04-30 | Cancelled | Res | Y
Fitchburg | Fitchburg | 3301 | 1420 | 7.68 |  |  | Solar |  | 35W36 | 2018-07-12 | 2018-07-16 | 3 |  | 3 | 2018-07-18 | 2018-07-19 | 2 |  | 2 | [20 empty] | 2018-07-26 |  | 2018-08-20 | NO | Expedited | [8 empty] | 2018-09-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3299 | 1420 | 3 |  |  | Solar |  | 20W22 | 2018-07-16 | 2018-07-20 | 5 | 1 | 4 | 2018-08-02 | 2018-08-06 | 3 |  | 3 | [20 empty] | 2018-08-07 |  | 2018-08-10 | NO | Expedited | [8 empty] | 2018-08-31 | In Operation | Res | Y
Fitchburg | Ashby | 3298 | 1431 | 5.22 |  |  | Solar |  | 39W19 | 2018-07-10 | 2018-07-24 | 11 | 9 | 2 | 2018-07-24 | 2018-07-25 | 2 |  | 2 | [20 empty] | 2018-08-03 |  | 2018-06-02 | NO | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 3294 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-07-06 | 2018-08-16 | 30 | 27 | 3 | 2018-08-16 | 2018-08-21 | 4 |  | 4 | [20 empty] | 2018-08-23 | 2019-01-29 | 2018-08-08 | YES | Expedited | [8 empty] | 2019-04-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 3293 | 1462 | 12 |  |  | Solar |  | 30W30 | 2018-07-06 | 2018-08-17 | 31 | 28 | 3 | 2018-08-17 | 2018-08-21 | 3 |  | 3 | [20 empty] | 2018-08-23 |  |  |  | Expedited | [8 empty] | 2018-09-24 | In Operation |  | Y
Fitchburg | Lunenburg | 3290 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2018-06-28 | 2018-07-10 | 8 | 2 | 6 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  | 2018-08-28 | NO | Expedited | [8 empty] | 2018-11-08 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3289 | 1462 | 10.95 |  |  | Solar |  | 31W38 | 2018-06-26 | 2018-07-03 | 6 | 4 | 2 | 2018-07-03 | 2018-07-05 | 2 |  | 2 | [20 empty] | 2018-07-10 |  | 2018-07-24 | YES | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 3285 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-06-26 | 2018-07-10 | 10 | 5 | 5 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  | 2018-08-25 | NO | Expedited | [8 empty] | 2018-11-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 3283 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2018-06-25 | 2018-06-29 | 5 |  | 5 | 2018-07-11 | 2018-08-08 | 21 |  | 21 | [20 empty] | 2018-08-14 |  |  | NO | Expedited | [8 empty] | 2018-10-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 3282 | 1420 | 5 |  |  | Solar |  | 20W22 | 2018-06-25 | 2018-07-02 | 6 | 1 | 5 | 2018-08-23 | 2018-08-28 | 4 |  | 4 | [20 empty] | 2018-08-30 |  |  | NO | Expedited | [8 empty] | 2018-09-05 | In Operation | Res | Y
Fitchburg | Townsend | 3279 | 1474 | 30 |  |  | Solar |  | 39W18 | 2018-06-21 | 2018-07-05 | 10 | 1 | 9 | 2018-07-06 | 2018-07-06 | 1 |  | 1 | [20 empty] | 2018-07-31 | 2018-08-06 | 2018-06-28 | YES | Expedited | [8 empty] | 2018-11-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 3278 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2018-06-20 | 2018-07-13 | 17 | 12 | 5 | 2018-07-13 | 2018-07-17 | 3 |  | 3 | [20 empty] | 2018-07-24 |  |  | YES | Expedited | [8 empty] | 2018-11-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3276 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-06-20 | 2018-07-26 | 26 | 21 | 5 | 2018-07-27 | 2018-07-30 | 2 |  | 2 | [20 empty] | 2018-08-03 |  | 2018-08-19 | NO | Expedited | [8 empty] | 2018-08-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 3275 | 1462 | 3.3 |  |  | Solar |  | 30W30 | 2018-06-19 | 2018-07-02 | 10 | 8 | 2 | 2018-07-02 | 2018-07-05 | 3 |  | 3 | [20 empty] | 2018-07-10 |  | 2018-08-27 | YES | Expedited | [8 empty] | 2018-08-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3273 | 1420 | 9.4 |  |  | Solar |  | 31W37 | 2018-06-18 | 2018-06-22 | 5 |  | 5 | 2018-07-02 | 2018-07-03 | 2 |  | 2 | [20 empty] | 2018-07-06 | 2019-02-12 |  | YES | Expedited | [8 empty] | 2018-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3271 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2018-06-15 | 2018-07-06 | 15 | 12 | 3 | 2018-07-10 | 2018-07-11 | 2 |  | 2 | [20 empty] | 2018-07-13 |  |  | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3270 | 1462 | 9.84 |  |  | Solar |  | 31W37 | 2018-06-18 | 2018-07-20 | 24 | 21 | 3 | 2018-07-24 | 2018-07-25 | 2 |  | 2 | [20 empty] | 2018-08-03 |  |  | NO | Expedited | [8 empty] | 2018-10-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 3269 | 1420 | 10 |  |  | Solar |  | 50W51 | 2018-06-15 | 2018-06-19 | 3 |  | 3 | 2018-06-20 | 2018-06-22 | 3 |  | 3 | [20 empty] | 2018-06-26 |  | 2018-07-30 | NO | Expedited | [8 empty] | 2018-10-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3266 | 1420 | 4885 |  |  | Solar + Energy Storage |  | 25W28 | 2018-09-11 | 2018-10-02 | 16 | 15 | 1 | [10 empty] | 2018-10-13 | 2018-10-24 | 8 |  | 8 | 2018-11-30 | 2019-05-16 | 113 |  | 113 | [5 empty] | 2019-05-23 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 3264 | 1420 | 5 |  |  | Solar |  | 01W04 | 2018-06-12 | 2018-06-26 | 11 | 5 | 6 | 2018-07-09 | 2018-07-11 | 3 |  | 3 | [20 empty] | 2018-07-13 |  |  | NO | Expedited | [8 empty] | 2018-09-04 | In Operation |  | Y
Fitchburg | Lunenburg | 3262 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-06-08 | 2018-06-19 | 8 | 6 | 2 | 2018-06-19 | 2018-06-22 | 4 |  | 4 | [20 empty] | 2018-06-26 | 2020-05-22 | 2018-08-08 | YES | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3261 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-06-07 | 2018-07-17 | 28 | 24 | 4 | 2018-07-18 | 2018-07-19 | 2 |  | 2 | [20 empty] | 2018-07-26 |  | 2018-08-06 | NO | Expedited | [8 empty] | 2018-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3259 | 1462 | 5 |  |  | Solar |  | 30W31 | 2018-06-07 | 2018-06-27 | 15 | 12 | 3 | 2018-06-27 | 2018-07-05 | 6 |  | 6 | [20 empty] | 2018-07-10 |  | 2018-07-08 | NO | Expedited | [8 empty] | 2018-09-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 3258 | 1462 | 10.95 |  |  | Solar |  | 31W38 | 2018-06-06 | 2018-06-28 | 17 | 13 | 4 | 2018-06-28 | 2018-07-03 | 4 |  | 4 | [20 empty] | 2018-07-09 |  | 2018-08-04 | NO | Expedited | [8 empty] | 2018-09-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3256 | 1462 | 13.6 |  |  | Solar |  | 31W37 | 2018-06-05 | 2018-06-13 | 7 | 6 | 1 | 2018-06-13 | 2018-06-13 | 1 |  | 1 | [20 empty] | 2018-06-21 |  | 2018-08-05 | NO | Expedited | [8 empty] | 2018-08-22 | In Operation | Res | Y
Fitchburg | Ashby | 3251 | 1431 | 3.8 |  |  | Solar |  | 39W19 | 2018-06-01 | 2018-06-11 | 7 | 6 | 1 | 2018-06-11 | 2018-06-11 | 1 |  | 1 | [20 empty] | 2018-06-13 |  | 2018-08-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3249 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2018-06-01 | 2018-06-29 | 21 | 12 | 9 | 2018-06-29 | 2018-07-05 | 4 |  | 4 | [20 empty] | 2018-07-10 |  | 2018-07-02 | NO | Expedited | [8 empty] | 2018-09-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3247 | 1462 | 6 |  |  | Solar |  | 30W30 | 2018-05-31 | 2018-06-14 | 11 | 9 | 2 | 2018-06-14 | 2018-06-15 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-30 | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3246 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2018-05-30 | 2018-06-05 | 5 |  | 5 | 2018-06-06 | 2018-06-11 | 4 |  | 4 | [20 empty] | 2018-06-13 |  |  | NO | Expedited | [8 empty] | 2018-08-03 | In Operation | Res | Y
Fitchburg | Townsend | 3238 | 1469 | 10.95 |  |  | Solar |  | 39W18 | 2018-05-23 | 2018-05-29 | 4 |  | 4 | 2018-06-01 | 2018-06-04 | 2 |  | 2 | [20 empty] | 2018-06-08 |  | 2018-06-20 | NO | Expedited | [8 empty] | 2018-08-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3234 | 1420 | 9.8 |  |  | Solar |  | 31W37 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-05-25 | 2018-05-29 | 2 |  | 2 | [20 empty] | 2018-05-31 |  | 2018-07-17 | NO | Expedited | [8 empty] | 2018-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3233 | 1420 | 10.95 |  |  | Solar |  | 35W36 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-19 | NO | Expedited | [8 empty] | 2018-08-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 3232 | 1420 | 9.3 |  |  | Solar |  | 50W51 | 2018-05-17 | 2018-05-22 | 4 |  | 4 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-21 |  | 2018-06-19 | NO | Expedited | [8 empty] | 2018-08-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3230 | 1420 | 10.95 |  |  | Solar |  | 35W36 | 2018-04-23 | 2018-05-21 | 21 |  | 21 | 2018-06-01 | 2018-06-04 | 2 |  | 2 | [20 empty] | 2018-06-08 | 2019-07-24 |  | YES | Expedited | [8 empty] | 2019-09-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 3229 | 1462 | 12.6 |  |  | Solar |  | 31W34 | 2018-05-15 | 2018-06-08 | 18 | 10 | 8 | 2018-06-08 | 2018-06-11 | 2 |  | 2 | [20 empty] | 2018-06-13 |  | 2018-07-15 | NO | Expedited | [8 empty] | 2018-09-12 | In Operation | Res | Y
Fitchburg | Townsend | 3223 | 1469 | 9 |  |  | Solar |  | 39W18 | 2018-05-09 | 2018-05-21 | 9 | 5 | 4 | 2018-07-25 | 2018-07-25 | 1 |  | 1 | [20 empty] | 2018-08-03 |  |  | NO | Expedited | [8 empty] | 2018-09-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3222 | 1420 | 5 |  |  | Solar |  | 20W22 | 2018-05-09 | 2018-05-14 | 4 | 1 | 3 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  |  | NO | Expedited | [8 empty] | 2018-07-25 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3219 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-05-09 | 2018-05-14 | 4 | 2 | 2 | 2018-05-16 | 2018-05-21 | 4 |  | 4 | [20 empty] | 2018-05-22 |  | 2018-06-30 | NO | Expedited | [8 empty] | 2018-07-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3218 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2018-05-09 | 2018-06-13 | 25 | 22 | 3 | 2018-06-13 | 2018-06-13 | 1 |  | 1 | [20 empty] | 2018-06-21 |  | 2018-07-08 | NO | Expedited | [8 empty] | 2018-08-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 3213 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2018-05-04 | 2018-06-08 | 25 | 20 | 5 | 2018-06-08 | 2018-06-11 | 2 |  | 2 | [20 empty] | 2018-06-13 |  | 2018-07-04 | NO | Expedited | [8 empty] | 2018-10-24 | In Operation | Res | Y
Fitchburg | Fitchburg | 3212 | 1420 | 200 |  |  | Solar |  | 11H11 | 2018-06-07 | 2018-07-05 | 20 | 11 | 9 | 2018-07-05 | 2018-07-05 | 1 |  | 1 | 2018-08-11 | 2018-09-18 | 26 |  | 26 | [15 empty] | 2018-09-24 |  |  |  | Expedited | [9 empty] | Cancelled
Fitchburg | Lunenburg | 3211 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2018-05-21 | 2018-05-21 | 1 |  | 1 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  | 2018-06-18 | NO | Expedited | [8 empty] | 2018-07-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 3208 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2018-05-01 | 2018-05-29 | 20 | 19 | 1 | 2018-05-29 | 2018-05-30 | 2 |  | 2 | [20 empty] | 2018-05-31 |  | 2018-05-29 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3205 | 1420 | 3.8 |  |  | Solar |  | 20W22 | 2018-04-26 | 2018-05-01 | 4 |  | 4 | 2018-05-21 | 2018-05-22 | 2 |  | 2 | [20 empty] | 2018-05-24 |  | 2018-05-23 | NO | Expedited | [8 empty] | 2018-08-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3204 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2018-04-26 | 2018-05-01 | 4 |  | 4 | 2018-05-15 | 2018-05-21 | 5 |  | 5 | [20 empty] | 2018-05-22 |  | 2018-06-24 | NO | Expedited | [8 empty] | 2018-10-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3198 | 1420 | 10.95 |  |  | Solar |  | 25W27 | 2018-04-25 | 2018-05-22 | 20 | 15 | 5 | 2018-06-11 | 2018-06-12 | 2 |  | 2 | [20 empty] | 2018-06-26 | 2018-07-23 | 2018-05-24 | YES | Expedited | [8 empty] | 2018-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 3197 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2018-04-25 | 2018-05-04 | 8 | 3 | 5 | 2018-05-04 | 2018-05-07 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-24 | NO | Expedited | [8 empty] | 2018-06-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3195 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-04-14 | 2018-04-30 | 10 | 2 | 8 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-23 |  |  | YES | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3193 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2018-04-19 | 2018-04-27 | 7 | 5 | 2 | 2018-04-27 | 2018-04-30 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-06-11 | NO | Expedited | [8 empty] | 2018-07-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 3190 | 1462 | 5 |  |  | Solar |  | 31W38 | 2018-04-17 | 2018-04-30 | 10 | 8 | 2 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-14 |  | 2018-05-18 | NO | Expedited | [8 empty] | 2018-11-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3189 | 1420 | 10.95 |  |  | Solar |  | 35W36 | 2018-04-16 | 2018-04-25 | 7 | 5 | 2 | 2018-05-15 | 2018-05-21 | 5 |  | 5 | [20 empty] | 2018-05-22 |  | 2018-06-28 | NO | Expedited | [8 empty] | 2018-08-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 3188 | 1462 | 8.36 |  |  | Solar |  | 30W31 | 2018-04-11 | 2018-04-27 | 12 | 8 | 4 | 2018-04-27 | 2018-04-30 | 2 |  | 2 | [20 empty] | 2018-05-04 |  | 2018-05-13 | NO | Expedited | [8 empty] | 2018-07-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3187 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2018-04-11 | 2018-04-16 | 3 |  | 3 | 2018-04-23 | 2018-04-23 | 1 |  | 1 | [20 empty] | 2018-05-03 |  | 2018-06-01 | NO | Expedited | [8 empty] | 2018-09-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3183 | 1462 | 5 |  |  | Solar |  | 31W38 | 2018-04-10 | 2018-04-30 | 14 | 12 | 2 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-09 | NO | Expedited | [8 empty] | 2018-09-11 | Cancelled | Res | Y
Fitchburg | Fitchburg | 3182 | 1420 | 8.36 |  |  | Solar |  | 35W36 | 2018-04-09 | 2018-04-20 | 9 | 6 | 3 | 2018-04-30 | 2018-05-01 | 2 |  | 2 | [20 empty] | 2018-05-10 |  | 2018-05-11 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3180 | 1462 | 12 |  |  | Solar |  | 31W38 | 2017-11-14 | 2018-04-17 | 102 | 93 | 9 | 2018-04-20 | 2018-04-20 | 1 |  | 1 | [20 empty] | 2018-04-23 |  | 2018-01-14 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 3179 | 1420 | 70.8 |  |  | Solar |  | 31W37 | 2018-06-01 | 2018-06-28 | 20 |  | 20 | 2018-06-29 | 2018-08-31 | 45 | 1 | 44 | [20 empty] | 2018-10-03 | 2019-05-14 |  | YES | Expedited | [8 empty] | 2022-05-04 | In Operation |  | Y
Fitchburg | Townsend | 3175 | 1453 | 750 |  |  | Solar |  | 39W18 | 2018-04-06 | 2018-04-07 | 1 |  | 1 | 2018-04-07 | 2018-04-16 | 5 |  | 5 | 2018-05-04 | 2018-07-11 | 47 |  | 47 | [15 empty] | 2018-07-11 | 2019-06-03 |  | YES | Expedited | [6 empty] | 2021-03-26 | 2021-03-26 | 2021-04-14 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3174 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-03-30 | 2018-05-10 | 29 | 28 | 1 | 2018-05-10 | 2018-06-12 | 23 | 19 | 4 | [20 empty] | 2018-06-21 |  | 2018-05-30 | NO | Expedited | [8 empty] | 2018-07-10 | Cancelled | Res | Y
Fitchburg | West Townsend | 3173 | 1474 | 5 |  |  | Solar |  | 39W18 | 2018-03-29 | 2018-04-04 | 5 |  | 5 | 2018-04-09 | 2018-04-17 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-07-15 | YES | Expedited | [8 empty] | 2018-08-13 | In Operation | Res | Y
Fitchburg | Ashby | 3171 | 1431 | 10.95 |  |  | Solar |  | 39W19 | 2018-03-29 | 2018-04-27 | 21 | 20 | 1 | 2018-04-27 | 2018-04-27 | 1 |  | 1 | [20 empty] | 2018-05-04 |  | 2018-05-28 | NO | Expedited | [8 empty] | 2018-07-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 3170 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-03-29 | 2018-04-06 | 7 | 5 | 2 | 2018-04-06 | 2018-04-06 | 1 |  | 1 | [20 empty] | 2018-04-23 |  | 2018-05-28 | NO | Expedited | [8 empty] | 2018-07-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 3163 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2018-03-21 | 2018-04-04 | 11 | 10 | 1 | 2018-04-04 | 2018-04-16 | 8 |  | 8 | [20 empty] | 2018-04-23 |  | 2018-05-21 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3162 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2018-03-15 | 2018-03-19 | 3 |  | 3 | 2018-03-26 | 2018-04-24 | 21 |  | 21 | [20 empty] | 2018-05-02 |  | 2018-06-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3158 | 1462 | 10 |  |  | Solar |  | 31W37 | 2018-03-13 | 2018-03-29 | 13 | 11 | 2 | 2018-03-29 | 2018-04-16 | 12 |  | 12 | [20 empty] | 2018-04-23 |  | 2018-04-15 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3157 | 1420 | 3.8 |  |  | Solar |  | 50W51 | 2018-03-08 | 2018-03-14 | 3 |  | 3 | [25 empty] | 2018-03-26 |  | 2018-05-02 | NO | Expedited | [8 empty] | 2018-04-13 | Cancelled | Res | Y
Fitchburg | Lunenburg | 3156 | 1462 | 12 |  |  | Solar |  | 30W31 | 2018-03-08 | 2018-03-15 | 4 |  | 4 | 2018-03-15 | 2018-03-22 | 6 |  | 6 | [20 empty] | 2018-03-29 |  | 2018-04-08 | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3155 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2018-03-08 | 2018-04-06 | 20 | 19 | 1 | 2018-04-06 | 2018-04-16 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-05-08 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 3154 | 1462 | 17.01 |  |  | Solar |  | 30W31 | 2018-03-07 | 2018-04-17 | 26 | 20 | 6 | 2018-04-17 | 2018-04-18 | 2 |  | 2 | [20 empty] | 2018-05-04 |  | 2018-04-09 | NO | Expedited | [8 empty] | 2018-08-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 3149 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2018-02-07 | 2018-03-13 | 21 | 10 | 11 | 2018-03-16 | 2018-03-16 | 1 |  | 1 | [20 empty] | 2018-03-19 |  | 2018-02-01 | NO | Expedited | [8 empty] | 2018-05-25 | In Operation | Res | Y
Fitchburg | Lunenburg | 3148 | 1469 | 3200 |  |  | Solar |  | 30W31 | 2018-03-01 | 2018-04-01 | 19 | 18 | 1 | [5 empty] | 2018-06-22 | 2018-07-23 | 21 |  | 21 | [15 empty] | 2018-08-06 |  |  | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 3146 | 1462 | 5 |  |  | Solar |  | 30W31 | 2018-02-28 | 2018-03-05 | 4 |  | 4 | 2018-03-12 | 2018-03-15 | 4 |  | 4 | [20 empty] | 2018-03-19 |  | 2018-03-09 | NO | Expedited | [8 empty] | 2018-05-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3138 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2018-02-20 | 2018-02-23 | 3 |  | 3 | 2018-03-01 | 2018-03-15 | 8 |  | 8 | [20 empty] | 2018-03-16 |  | 2018-04-20 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3130 | 1420 | 6 |  |  | Solar |  | 01W04 | 2018-02-09 | 2018-03-09 | 17 | 16 | 1 | 2018-04-06 | 2018-04-16 | 6 |  | 6 | [20 empty] | 2018-04-23 |  | 2018-03-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3129 | 1462 | 12 |  |  | Solar |  | 30W30 | 2018-01-06 | 2018-02-16 | 29 | 25 | 4 | 2018-02-16 | 2018-02-19 | 2 |  | 2 | [20 empty] | 2018-02-23 |  | 2018-03-04 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3123 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2018-01-29 | 2018-03-14 | 29 | 28 | 1 | 2018-03-14 | 2018-04-10 | 20 |  | 20 | [20 empty] | 2018-04-23 |  | 2018-03-29 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3121 | 1431 | 10.95 |  |  | Solar |  | 39W19 | 2018-01-29 | 2018-02-06 | 7 | 5 | 2 | 2018-02-06 | 2018-02-20 | 10 |  | 10 | [20 empty] | 2018-02-23 |  |  | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Ashby | 3113 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2018-01-24 | 2018-02-12 | 14 | 11 | 3 | 2018-02-12 | 2018-02-20 | 6 |  | 6 | [20 empty] | 2018-02-23 |  | 2018-02-12 | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 3112 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2018-01-19 | 2018-01-26 | 6 |  | 6 | 2018-02-09 | 2018-02-19 | 7 |  | 7 | [20 empty] | 2018-02-23 |  | 2018-02-22 | NO | Expedited | [8 empty] | 2018-06-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3111 | 1462 | 6 |  |  | Solar |  | 30W30 | 2018-01-24 | 2018-02-21 | 20 | 10 | 10 | 2018-02-21 | 2018-02-23 | 3 |  | 3 | [20 empty] | 2018-02-23 |  | 2018-02-23 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3110 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2018-01-17 | 2018-01-24 | 6 |  | 6 | 2018-01-24 | 2018-01-29 | 4 |  | 4 | [20 empty] | 2018-01-29 |  | 2018-02-24 | NO | Expedited | [8 empty] | 2018-05-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3105 | 1462 | 15.3 |  |  | Solar |  | 30W31 | 2018-01-15 | 2018-01-22 | 5 |  | 5 | 2018-01-22 | 2018-02-20 | 21 | 2 | 19 | [20 empty] | 2018-02-20 |  | 2018-03-15 | YES | Expedited | [8 empty] | 2018-03-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 3102 | 1462 | 11.4 |  |  | Solar |  | 30W31 | 2018-01-12 | 2018-01-22 | 6 | 3 | 3 | 2018-01-22 | 2018-02-19 | 21 | 2 | 19 | [20 empty] | 2018-02-19 |  | 2018-03-12 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 3100 | 1420 | 3.8 |  |  | Solar |  | 50W51 | 2018-01-12 | 2018-01-22 | 6 |  | 6 | 2018-02-01 | 2018-02-13 | 9 |  | 9 | [22 empty] | 2018-03-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3090 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2018-01-08 | 2018-02-09 | 24 | 20 | 4 | 2018-02-09 | 2018-02-19 | 7 |  | 7 | [20 empty] | 2018-02-23 |  | 2018-02-05 | NO | Expedited | [8 empty] | 2018-04-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 3079 | 1420 | 3.8 |  |  | Solar |  | 50W51 | 2018-01-02 | 2018-01-09 | 6 |  | 6 | 2018-01-11 | 2018-01-16 | 3 |  | 3 | [20 empty] | 2018-01-22 |  |  | NO | Expedited | [8 empty] | 2018-03-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 3078 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2018-01-02 | 2018-01-15 | 10 | 3 | 7 | 2018-01-19 | 2018-01-26 | 6 |  | 6 | [20 empty] | 2018-02-01 |  | 02/29/2018 | NO | Expedited | [8 empty] | 2018-05-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 3076 | 1420 | 6.6 |  |  | Solar |  | 20W22 | 2017-12-28 | 2018-01-09 | 8 |  | 8 | 2018-01-29 | 2018-02-02 | 5 |  | 5 | [20 empty] | 2018-02-02 |  | 2018-02-19 | NO | Expedited | [8 empty] | 2018-03-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3075 | 1420 | 21.6 |  |  | Solar |  | 31W37 | 2017-12-28 | 2018-01-18 | 14 |  | 14 | 2018-01-18 | 2018-02-08 | 16 |  | 16 | [20 empty] | 2018-02-08 |  | 02/29/2018 | NO | Expedited | [8 empty] | 2018-06-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3074 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2017-12-28 | 2018-01-09 | 8 |  | 8 | 2018-01-24 | 2018-01-26 | 3 |  | 3 | [20 empty] | 2018-02-01 |  | 2018-02-05 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3072 | 1462 | 3000 |  |  | Solar |  | 0 | 2018-02-09 | 2018-04-05 | 36 |  | 36 | [28 empty] | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 3071 | 1420 | 8.36 |  |  | Solar |  | 31W37 | 2017-12-27 | 2018-01-05 | 7 |  | 7 | 2018-02-01 | 2018-02-13 | 9 |  | 9 | [20 empty] | 2018-02-19 |  | 2018-01-29 | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 3069 | 1462 | 10.95 |  |  | Solar |  | 31W37 | 2017-12-21 | 2018-01-08 | 11 | 1 | 10 | 2018-01-12 | 2018-01-16 | 2 |  | 2 | [20 empty] | 2018-01-22 |  | 2018-01-20 | YES | Expedited | [8 empty] | 2018-04-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3066 | 1420 | 5.52 |  |  | Solar |  | 20W22 | 2017-12-20 | 2018-01-05 | 11 | 1 | 10 | 2018-01-11 | 2018-01-16 | 3 |  | 3 | [20 empty] | 2018-01-18 |  |  | NO | Expedited | [8 empty] | 2018-04-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 3065 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2017-12-15 | 2018-01-03 | 12 |  | 12 | 2018-01-08 | 2018-01-15 | 6 |  | 6 | [20 empty] | 2018-01-25 |  | 2018-02-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3062 | 1462 | 240 |  |  | Solar |  | 31W38 | 2017-12-14 | 2018-01-10 | 18 | 5 | 13 | 2018-01-10 | 2018-01-24 | 10 |  | 10 | 2018-01-30 | 2018-02-26 | 19 |  | 19 | [15 empty] | 2018-02-28 | 2019-04-16 | 2017-05-01 | YES | Expedited | [8 empty] | 2019-08-12 | In Operation | Res | Y
Fitchburg | Townsend | 3060 | 1474 | 5 |  |  | Solar |  | 39W18 | 2017-12-14 | 2017-12-22 | 7 | 1 | 6 | 2018-01-02 | 2018-01-05 | 4 |  | 4 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-03-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 3059 | 1420 | 4400 |  |  | Solar |  | 25W28 | 2017-12-01 | 2017-12-18 | 12 |  | 12 | [10 empty] | 2017-12-19 | 2018-01-17 | 19 |  | 19 | 2018-02-09 | 2018-07-06 | 99 | 40 | 59 | [5 empty] | 2018-07-24 |  | 2018-09-14 | YES | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Townsend | 3057 | 1469 | 6.96 |  |  | Solar |  | 15W16 | 2017-12-11 | 2018-01-05 | 18 | 9 | 9 | 2018-01-16 | 2018-01-30 | 10 |  | 10 | [20 empty] | 2018-02-01 |  |  | YES | Expedited | [8 empty] | 2018-04-02 | In Operation | Res | Y
Fitchburg | Townsend | 3056 | 1469 | 10.95 |  |  | Solar |  | 15W17 | 2017-12-11 | 2017-12-19 | 7 |  | 7 | 2018-02-06 | 2018-02-09 | 4 |  | 4 | [20 empty] | 2018-02-12 |  | 2018-01-01 | NO | Expedited | [8 empty] | 2018-03-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 3054 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-12-12 | 2017-12-19 | 6 |  | 6 | 2018-01-08 | 2018-01-15 | 6 |  | 6 | [20 empty] | 2018-01-23 |  | 2018-01-30 | NO | Expedited | [8 empty] | 2018-04-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 3053 | 1420 | 6 |  |  | Solar |  | 01W02 | 2017-12-11 | 2017-12-14 | 4 |  | 4 | 2018-01-04 | 2018-01-05 | 2 |  | 2 | [20 empty] | 2018-01-08 |  | 2018-01-11 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3052 | 1420 | 5 |  |  | Solar |  | 20W22 | 2017-12-07 | 2017-12-13 | 5 |  | 5 | 2018-01-26 | 2018-01-26 | 1 |  | 1 | [20 empty] | 2018-01-29 |  |  | NO | Expedited | [8 empty] | 2018-05-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 3049 | 1420 | 8.12 |  |  | Solar |  | 50W51 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-08 |  | 2017-01-30 | NO | Expedited | [8 empty] | 2018-05-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 3048 | 1420 | 3.8 |  |  | Solar |  | 20W22 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2018-01-03 | 2018-01-03 | 1 |  | 1 | [20 empty] | 2018-01-05 |  |  | NO | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 3047 | 1462 | 6 |  |  | Solar |  | 30W30 | 2017-12-06 | 2017-12-11 | 4 |  | 4 | 2018-01-03 | 2018-01-05 | 3 |  | 3 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3046 | 1420 | 8.35 |  |  | Solar |  | 50W51 | 2017-12-05 | 2017-12-07 | 3 |  | 3 | 2017-12-20 | 2018-01-03 | 9 |  | 9 | [20 empty] | 2018-01-08 |  |  | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3045 | 1420 | 300 |  |  | Gas |  | 50W55 | 2017-12-18 | 2018-01-03 | 11 | 3 | 8 | [10 empty] | 2018-01-04 | 2018-01-31 | 19 |  | 19 | 2018-04-16 | 2018-07-26 | 71 | 9 | 62 | [5 empty] | 2019-01-16 |  | 2017-03-15 | NO | Standard | [8 empty] | 2019-05-16 | In Operation | Comm | Y
Fitchburg | Lunenburg | 3042 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2017-12-01 | 2017-12-05 | 3 |  | 3 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-05 |  | 2018-01-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3041 | 1462 | 10.95 |  |  | Solar |  | 31W38 | 2017-12-01 | 2017-12-05 | 3 |  | 3 | 2018-01-02 | 2018-01-03 | 2 |  | 2 | [20 empty] | 2018-01-05 |  | 2018-01-02 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3038 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2017-11-30 | 2017-12-06 | 5 | 1 | 4 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-08 |  | 2018-01-29 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 3037 | 1420 | 5 |  |  | Solar |  | 01W04 | 2017-11-28 | 2017-11-30 | 3 |  | 3 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-05 |  | 2018-02-14 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3035 | 1420 | 6 |  |  | Solar |  | 01W04 | 2017-11-22 | 2017-11-28 | 4 |  | 4 | 2018-01-02 | 2018-01-05 | 4 |  | 4 | [20 empty] | 2018-01-08 |  | 2017-12-24 | NO | Expedited | [8 empty] | 2018-03-05 | In Operation | Res | Y
Fitchburg | Ashby | 3034 | 1431 | 6 |  |  | Solar |  | 39W19 | 2017-11-20 | 2017-11-27 | 5 |  | 5 | 2018-01-11 | 2018-01-15 | 3 |  | 3 | [20 empty] | 2018-01-29 |  | 2017-12-18 | YES | Expedited | [8 empty] | 2018-05-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 3028 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-11-15 | 2017-11-22 | 6 |  | 6 | 2018-01-12 | 2018-01-15 | 2 |  | 2 | [20 empty] | 2018-01-23 |  | 2018-01-14 | NO | Expedited | [8 empty] | 2018-04-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 3026 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2017-11-14 | 2017-11-22 | 7 |  | 7 | 2017-12-05 | 2017-12-19 | 11 |  | 11 | [20 empty] | 2017-12-22 |  |  | NO | Expedited | [8 empty] | 2018-05-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3025 | 1420 | 5 |  |  | Solar |  | 40W40 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2018-01-22 | 2018-01-25 | 4 |  | 4 | [20 empty] | 2018-01-25 |  | 2018-01-23 | NO | Expedited | [8 empty] | 2018-04-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 3024 | 1420 | 10.95 |  |  | Solar |  | 25W27 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2017-12-18 | 2018-01-03 | 11 |  | 11 | [20 empty] | 2018-01-11 |  | 2018-01-13 | YES | Expedited | [8 empty] | 2018-03-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 3023 | 1420 | 10 |  |  | Solar |  | 31W37 | 2017-11-13 | 2017-11-21 | 7 |  | 7 | 2018-01-02 | 2018-01-03 | 2 |  | 2 | [20 empty] | 2018-01-05 |  | 2017-12-16 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Townsend | 3022 | 1469 | 10.95 |  |  | Solar |  | 15W16 | 2017-11-10 | 2017-11-21 | 8 |  | 8 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-11 |  | 2017-12-27 | NO | Expedited | [8 empty] | 2018-01-22 | In Operation | Res | Y
Fitchburg | Ashby | 3019 | 1431 | 10.95 |  |  | Solar |  | 39W19 | 2017-11-09 | 2017-11-16 | 6 | 5 | 1 | 2017-11-29 | 2017-12-04 | 4 |  | 4 | [20 empty] | 2017-12-05 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-04-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 3018 | 1420 | 6 |  |  | Solar |  | 11W11 | 2017-11-08 | 2017-11-13 | 4 |  | 4 | 2018-03-02 | 2018-03-12 | 4 |  | 4 | [20 empty] | 2017-11-28 |  | 2017-12-11 | YES | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 3016 | 1420 | 5.12 |  |  | Solar |  | 31W37 | 2017-11-07 | 2017-11-08 | 2 |  | 2 | 2017-12-19 | 2018-01-03 | 10 |  | 10 | [20 empty] | 2018-01-08 |  | 2017-12-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 3014 | 1431 | 9.2 |  |  | Solar |  | 39W19 | 2017-11-06 | 2017-11-09 | 4 |  | 4 | 2017-12-01 | 2017-12-19 | 13 |  | 13 | [20 empty] | 2017-12-22 |  |  | YES | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 3013 | 1420 | 7.6 |  |  | Solar |  | 01W04 | 2017-11-06 | 2017-11-08 | 3 |  | 3 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-07 |  | 2017-12-04 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 3012 | 1462 | 7.6 |  |  | Solar |  | 39W18 | 2017-11-06 | 2017-11-08 | 3 |  | 3 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 3010 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2017-11-02 | 2017-11-07 | 4 |  | 4 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2018-01-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 3009 | 1420 | 5 |  |  | Solar |  | 01W04 | 2017-11-02 | 2017-11-07 | 4 |  | 4 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-07 |  | 2017-12-04 | NO | Expedited | [8 empty] | 2018-03-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3008 | 1420 | 3.8 |  |  | Solar |  | 40W40 | 2017-11-02 | 2017-11-08 | 5 |  | 5 | 2017-12-12 | 2017-12-19 | 6 |  | 6 | [20 empty] | 2017-12-22 |  | 2017-12-17 | NO | Expedited | [8 empty] | 2018-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 3007 | 1420 | 10.9 |  |  | Solar |  | 01W04 | 2017-11-03 | 2017-11-08 | 4 | 1 | 3 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 | 2021-03-26 |  | YES | Expedited | [8 empty] | 2021-05-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 3006 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2017-11-01 | 2017-11-06 | 4 | 1 | 3 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2018-01-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 3005 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-11-01 | 2017-11-06 | 4 |  | 4 | 2017-11-27 | 2017-12-08 | 10 |  | 10 | [20 empty] | 2017-12-08 |  | 2017-12-03 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 3003 | 1462 | 9.52 |  |  | Solar |  | 30W30 | 2017-11-01 | 2017-11-07 | 5 |  | 5 | 2018-01-02 | 2018-01-08 | 5 |  | 5 | [20 empty] | 2018-01-08 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 3002 | 1462 | 9.8 |  |  | Solar |  | 30W31 | 2017-10-31 | 2017-11-03 | 3 |  | 3 | 2017-11-14 | 2017-11-28 | 10 |  | 10 | [20 empty] | 2017-11-28 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-03-05 | In Operation | Res | Y
Fitchburg | Ashby | 3001 | 1431 | 9 |  |  | Solar |  | 39W19 | 2017-10-30 | 2017-11-03 | 4 |  | 4 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 3000 | 1462 | 10 |  |  | Solar |  | 31W37 | 2017-10-30 | 2017-11-03 | 4 |  | 4 | 2017-12-20 | 2018-01-03 | 9 |  | 9 | [20 empty] | 2018-01-05 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2999 | 1420 | 7.6 |  |  | Solar |  | 20W22 | 2017-10-27 | 2017-12-11 | 30 | 25 | 5 | 2018-01-04 | 2018-01-08 | 3 |  | 3 | [20 empty] | 2018-01-08 |  | 2017-11-29 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2997 | 1420 | 10.95 |  |  | Solar |  | 20W22 | 2017-10-26 | 2017-11-08 | 9 | 1 | 8 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  |  | NO | Expedited | [8 empty] | 2018-04-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2996 | 1462 | 5 |  |  | Solar |  | 30W31 | 2017-10-26 | 2017-11-03 | 6 |  | 6 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2995 | 1431 | 9.6 |  |  | Solar |  | 39W19 | 2017-10-24 | 2017-11-03 | 8 |  | 8 | 2017-11-20 | 2017-12-01 | 9 |  | 9 | [20 empty] | 2017-12-08 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Townsend | 2992 | 1469 | 10.95 |  |  | Solar |  | 15W16 | 2017-10-25 | 2017-11-01 | 5 | 1 | 4 | 2017-11-20 | 2017-11-28 | 6 |  | 6 | [20 empty] | 2017-12-01 |  | 2017-11-27 | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2990 | 1420 | 10.95 |  |  | Solar |  | 50W56 | 2017-10-30 | 2017-11-06 | 5 | 4 | 1 | 2017-12-07 | 2017-12-19 | 9 |  | 9 | [20 empty] | 2017-12-22 |  | 2017-11-09 | NO | Expedited | [8 empty] | 2018-02-16 | In Operation | Res | Y
Fitchburg | Townsend | 2989 | 1474 | 5.2 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-10-30 | 6 |  | 6 | 2017-11-16 | 2017-12-01 | 11 |  | 11 | [20 empty] | 2017-12-08 |  | 2018-01-17 | NO | Expedited | [8 empty] | 2018-02-05 | In Operation | Res | Y
Fitchburg | Townsend | 2986 | 1469 | 6.7 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-13 | 2017-11-27 | 10 |  | 10 | [20 empty] | 2017-11-27 |  | 2017-11-10 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2985 | 1462 | 6.6 |  |  | Solar |  | 30W30 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-16 | 2017-11-28 | 8 |  | 8 | [20 empty] | 2017-12-01 |  | 2018-01-07 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2984 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2017-10-23 | 2017-10-27 | 5 |  | 5 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-08 |  | 2017-12-19 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Ashby | 2983 | 1431 | 120.8 |  |  | Solar |  | 39W19 | 2017-10-23 | 2017-11-07 | 11 |  | 11 | 2017-11-07 | 2017-11-27 | 14 |  | 14 | [20 empty] | 2017-11-27 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2981 | 1420 | 59.4 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2980 | 1420 | 5.4 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2979 | 1420 | 59.4 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2978 | 1420 | 400 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 2977 | 1420 | 59.4 |  |  | Solar |  | 39W18 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2976 | 1469 | 59.4 |  |  | Solar |  | 15W17 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [14 empty] | 0 | [12 empty] | 2018-03-01 | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2974 | 1431 | 8.64 |  |  | Solar |  | 39W19 | 2017-10-19 | 2017-10-25 | 5 | 2 | 3 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2017-11-16 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Townsend | 2973 | 1469 | 6 |  |  | Solar |  | 15W16 | 2017-10-19 | 2017-10-23 | 3 |  | 3 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-27 |  | 2018-01-07 | NO | Expedited | [8 empty] | 2018-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 2972 | 1431 | 7.6 |  |  | Solar |  | 35W36 | 2017-10-19 | 2017-10-23 | 3 |  | 3 | 2017-11-16 | 2017-12-01 | 11 |  | 11 | [20 empty] | 2017-12-08 |  | 2017-12-18 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2971 | 1420 | 6 |  |  | Solar |  | 25W27 | 2017-10-17 | 2017-10-26 | 8 | 2 | 6 | 2017-11-13 | 2017-12-01 | 14 |  | 14 | [20 empty] | 2017-12-08 |  | 2017-11-16 | NO | Expedited | [8 empty] | 2018-04-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 2969 | 1462 | 5 |  |  | Solar |  | 30W31 | 2017-10-17 | 2017-10-26 | 8 | 3 | 5 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2968 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2017-10-16 | 2017-10-25 | 8 | 1 | 7 | 2017-11-15 | 2017-11-28 | 9 |  | 9 | [20 empty] | 2017-12-01 |  | 2017-12-21 | NO | Expedited | [8 empty] | 2018-02-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2966 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2017-10-13 | 2017-10-20 | 6 |  | 6 | 2017-11-08 | 2017-11-20 | 9 |  | 9 | [20 empty] | 2017-11-30 |  | 2017-12-12 | NO | Expedited | [8 empty] | 2018-04-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2965 | 1420 | 10.95 |  |  | Solar |  | 25W27 | 2017-10-12 | 2017-10-20 | 7 | 1 | 6 | 2017-11-17 | 2017-12-01 | 10 |  | 10 | [20 empty] | 2017-12-07 |  | 2017-11-01 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Townsend | 2964 | 1469 | 9.8 |  |  | Solar |  | 15W16 | 2017-10-11 | 2017-10-24 | 10 | 1 | 9 | 2017-11-07 | 2017-11-20 | 10 |  | 10 | [20 empty] | 2017-11-27 |  | 2017-11-11 | NO | Expedited | [8 empty] | 2018-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2963 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-10-09 | 2017-10-12 | 3 |  | 3 | 2017-11-02 | 2017-11-20 | 13 |  | 13 | [20 empty] | 2017-11-30 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2017-12-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2962 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2017-10-09 | 2017-10-19 | 8 | 4 | 4 | 2017-11-08 | 2017-11-21 | 10 |  | 10 | [20 empty] | 2017-11-22 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-03-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2961 | 1462 | 12 |  |  | Solar |  | 30W30 | 2017-10-09 | 2017-10-16 | 5 | 2 | 3 | 2018-01-05 | 2018-01-05 | 1 |  | 1 | [20 empty] | 2018-01-05 |  | 2017-12-06 | YES | Expedited | [8 empty] | 2018-03-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2960 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-10-06 | 2017-10-17 | 7 | 2 | 5 | 2017-11-16 | 2017-11-28 | 8 |  | 8 | [20 empty] | 2017-12-08 |  | 2017-12-15 | NO | Expedited | [8 empty] | 2018-07-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2959 | 1420 | 6 |  |  | Solar |  | 20W22 | 2017-10-05 | 2017-10-19 | 10 | 5 | 5 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2018-03-10 | NO | Expedited | [8 empty] | 2018-01-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2958 | 1420 | 6 |  |  | Solar |  | 50W51 | 2017-10-05 | 2017-10-20 | 11 | 5 | 6 | 2017-11-06 | 2017-11-21 | 12 |  | 12 | [20 empty] | 2017-11-22 |  | 2017-11-23 | NO | Expedited | [8 empty] | 2017-12-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2957 | 1420 | 6 |  |  | Solar |  | 40W42 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-25 | 2017-11-20 | 18 |  | 18 | [20 empty] | 2017-11-22 |  |  | NO | Expedited | [8 empty] | 2018-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2956 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2017-10-03 | 2017-10-19 | 12 | 11 | 1 | 2017-10-27 | 2017-11-13 | 11 |  | 11 | [20 empty] | 2017-11-14 |  | 2017-12-02 | NO | Expedited | [8 empty] | 2018-05-08 | In Operation | Res | Y
Fitchburg | Ashby | 2955 | 1431 | 5 |  |  | Solar |  | 39W19 | 2017-10-03 | 2017-10-16 | 9 | 5 | 4 | 2017-10-30 | 2017-11-20 | 15 |  | 15 | [20 empty] | 2017-11-27 |  | 2017-11-06 | YES | Expedited | [8 empty] | 2018-01-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2954 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-15 |  | 2017-12-02 | NO | Expedited | [8 empty] | 2018-03-12 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2953 | 1462 | 12 |  |  | Solar |  | 30W31 | 2017-10-04 | 2017-10-10 | 4 |  | 4 | 2017-10-27 | 2017-11-17 | 15 |  | 15 | [20 empty] | 2017-11-17 |  | 2017-12-02 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 2951 | 1420 | 6 |  |  | Solar |  | 20W22 | 2017-09-27 | 2017-10-10 | 9 |  | 9 | 2017-10-26 | 2017-11-20 | 17 |  | 17 | [20 empty] | 2017-11-22 |  | 2017-11-28 | NO | Expedited | [8 empty] | 2017-12-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 2949 | 1462 | 6.72 |  |  | Solar |  | 31W37 | 2017-09-27 | 2017-10-03 | 5 |  | 5 | 2017-10-27 | 2017-11-14 | 12 |  | 12 | [20 empty] | 2017-11-14 |  |  | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | West Townsend | 2948 | 1474 | 10 |  |  | Solar |  | 39W18 | 2017-09-27 | 2017-10-03 | 5 |  | 5 | 2017-10-26 | 2017-11-27 | 21 |  | 21 | [20 empty] | 2017-11-27 |  | 2017-09-22 | NO | Expedited | [8 empty] | 2018-02-15 | In Operation | Res | Y
Fitchburg | Townsend | 2947 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2017-09-28 | 2017-10-03 | 4 |  | 4 | 2017-10-20 | 2017-11-06 | 11 |  | 11 | [20 empty] | 2017-11-06 |  | 2017-10-19 | NO | Expedited | [8 empty] | 2017-12-28 | In Operation | Res | Y
Fitchburg | Townsend | 2946 | 1469 | 6 |  |  | Solar |  | 15W16 | 2017-09-28 | 2017-10-03 | 4 |  | 4 | 2017-11-03 | 2017-11-20 | 12 |  | 12 | [20 empty] | 2017-11-27 |  | 2017-10-30 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2945 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-16 |  | 2017-11-25 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Townsend | 2944 | 1469 | 3.8 |  |  | Solar |  | 39W18 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-10-23 | 2017-11-15 | 17 |  | 17 | [20 empty] | 2017-11-15 |  | 2017-11-25 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2943 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2017-09-26 | 2017-10-03 | 6 |  | 6 | 2017-11-15 | 2017-11-15 | 1 |  | 1 | [20 empty] | 2017-11-16 |  | 2017-11-25 | NO | Expedited | [8 empty] | 2018-01-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 2939 | 1420 | 7.6 |  |  | Solar |  | 20W22 | 2017-09-25 | 2017-10-03 | 7 |  | 7 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-14 |  | 2017-10-23 | YES | Expedited | [8 empty] | 2018-08-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2938 | 1420 | 6.6 |  |  | Solar |  | 40W39 | 2017-09-25 | 2017-10-03 | 7 |  | 7 | 2017-11-02 | 2017-11-21 | 14 |  | 14 | [20 empty] | 2017-11-22 |  | 2017-10-25 | NO | Expedited | [8 empty] | 2018-04-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 2936 | 1420 | 4.4 |  |  | Solar |  | 01W04 | 2017-09-25 | 2017-10-02 | 6 |  | 6 | 2017-11-02 | 2017-11-21 | 14 |  | 14 | [20 empty] | 2017-11-22 |  | 2017-10-25 | NO | Expedited | [8 empty] | 2018-02-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2935 | 1420 | 3.8 |  |  | Solar |  | 31W37 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-27 | 2017-11-13 | 11 |  | 11 | [20 empty] | 2017-11-14 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Ashby | 2934 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-27 | 2017-12-28 | 42 |  | 42 | [20 empty] | 2018-01-02 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2018-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2932 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2017-09-20 | 2017-09-29 | 8 |  | 8 | 2017-10-20 | 2017-11-01 | 8 |  | 8 | [20 empty] | 2017-11-06 |  |  | NO | Expedited | [8 empty] | 2018-07-11 | In Operation | Res | Y
Fitchburg | Lunenburg | 2931 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2017-09-19 | 2017-09-29 | 9 |  | 9 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [20 empty] | 2017-11-17 |  | 2017-11-19 | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2930 | 1462 | 12 |  |  | Solar |  | 30W30 | 2017-09-18 | 2017-09-25 | 6 |  | 6 | 2017-10-23 | 2017-11-14 | 16 |  | 16 | [20 empty] | 2017-11-17 |  | 2017-11-15 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2929 | 1462 | 12 |  |  | Solar |  | 31W38 | 2017-09-18 | 2017-09-25 | 6 |  | 6 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-11-16 |  | 2017-09-15 | YES | Expedited | [8 empty] | 2018-03-23 | In Operation | Res | Y
Fitchburg | Lunenburg | 2928 | 1462 | 9 |  |  | Solar |  | 31W37 | 2017-09-15 | 2017-09-25 | 7 |  | 7 | 2017-10-26 | 2017-11-21 | 18 |  | 18 | [20 empty] | 2017-11-22 |  | 2017-08-22 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2925 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2017-09-14 | 2017-09-25 | 8 |  | 8 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-11-14 |  | 2017-11-11 | NO | Expedited | [8 empty] | 2018-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2924 | 1420 | 10.4 |  |  | Solar |  | 11W11 | 2017-09-11 | 2017-09-29 | 15 |  | 15 | 2017-10-31 | 2017-12-28 | 40 |  | 40 | [20 empty] | 2018-01-02 |  | 2017-11-13 | NO | Expedited | [8 empty] | 2018-03-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2921 | 1462 | 15 |  |  | Solar |  | 30W31 | 2017-09-11 | 2017-10-10 | 21 | 7 | 14 | 2017-10-23 | 2017-11-17 | 19 |  | 19 | [20 empty] | 2017-11-17 |  | 2017-11-15 | NO | Expedited | [8 empty] | 2018-01-15 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2920 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-09-07 | 2017-10-11 | 24 | 7 | 17 | 2017-11-13 | 2017-11-20 | 6 |  | 6 | [20 empty] | 2017-11-30 |  | 2017-12-22 | NO | Expedited | [8 empty] | 2018-01-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2917 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2017-09-01 | 2017-10-05 | 24 | 5 | 19 | 2017-10-20 | 2017-11-01 | 8 |  | 8 | [20 empty] | 2017-11-06 |  | 2017-10-28 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2914 | 1420 | 7.6 |  |  | Solar |  | 01W02 | 2017-09-01 | 2017-09-25 | 16 |  | 16 | 2017-10-23 | 2017-11-13 | 15 |  | 15 | [20 empty] | 2017-12-07 |  | 2017-11-01 | YES | Expedited | [8 empty] | 2018-08-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2904 | 1420 | 5 |  |  | Solar |  | 01W04 | 2017-08-30 | 2017-09-22 | 17 |  | 17 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2901 | 1420 | 8.35 |  |  | Solar |  | 11W11 | 2017-08-29 | 2017-09-27 | 21 |  | 21 | 2017-10-23 | 2017-11-20 | 20 |  | 20 | [20 empty] | 2017-11-30 |  | 2017-10-29 | YES | Expedited | [8 empty] | 2018-03-27 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2892 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-08-28 | 2017-09-15 | 14 | 1 | 13 | 2017-10-13 | 2017-11-07 | 17 |  | 17 | [20 empty] | 2017-11-07 |  | 2017-10-02 | NO | Expedited | [8 empty] | 2018-02-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2888 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2017-08-28 | 2017-09-20 | 17 |  | 17 | 2017-10-16 | 2017-11-01 | 12 |  | 12 | [20 empty] | 2017-11-15 |  | 2017-10-13 | NO | Expedited | [8 empty] | 2017-11-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 2884 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-08-24 | 2017-09-15 | 16 | 3 | 13 | 2017-10-17 | 2017-11-13 | 19 |  | 19 | [20 empty] | 2017-11-13 |  | 2017-09-20 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2882 | 1420 | 10.95 |  |  | Solar |  | 01W02 | 2017-08-23 | 2017-09-15 | 17 | 2 | 15 | 2017-10-16 | 2017-11-13 | 20 |  | 20 | [20 empty] | 2017-11-13 |  |  | NO | Expedited | [8 empty] | 2018-01-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2879 | 1420 | 3.8 |  |  | Solar |  | 35W36 | 2017-08-22 | 2017-09-15 | 18 | 15 | 3 | 2017-09-30 | 2017-10-25 | 17 |  | 17 | [20 empty] | 2017-10-25 |  | 2017-10-21 | NO | Expedited | [8 empty] | 2018-02-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2878 | 1462 | 6 |  |  | Solar |  | 30W30 | 2017-08-21 | 2017-09-19 | 21 | 19 | 2 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  | 2017-09-25 | NO | Expedited | [8 empty] | 2017-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2876 | 1420 | 3.8 |  |  | Solar |  | 01W02 | 2017-08-21 | 2017-09-15 | 19 |  | 19 | 2017-09-30 | 2017-11-03 | 23 |  | 23 | [20 empty] | 2017-11-03 |  | 2017-10-21 | YES | Expedited | [8 empty] | 2018-07-06 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2875 | 1420 | 5 |  |  | Solar |  | 11W11 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | 2017-10-10 | 2017-10-25 | 12 |  | 12 | [20 empty] | 2017-10-25 |  |  | NO | Expedited | [8 empty] | 2018-01-24 | In Operation | Res | Y
Fitchburg | Townsend | 2874 | 1469 | 7.6 |  |  | Solar |  | 15W16 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | 2017-10-13 | 2017-11-06 | 16 |  | 16 | [20 empty] | 2017-11-09 |  | 2017-10-19 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2872 | 1420 | 5.22 |  |  | Solar |  | 01W04 | 2017-08-17 | 2017-09-08 | 16 |  | 16 | [27 empty] | 2017-09-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2871 | 1431 | 1.8 |  |  | Solar |  | 39W19 | 2017-08-16 | 2017-09-19 | 24 | 7 | 17 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  |  | NO | Expedited | [8 empty] | 2017-11-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2869 | 1420 | 8.35 |  |  | Solar |  | 25W27 | 2017-08-17 | 2017-09-07 | 15 |  | 15 | 2017-09-29 | 2017-10-25 | 18 |  | 18 | [20 empty] | 2017-10-25 |  | 2017-10-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2868 | 1474 | 9.28 |  |  | Solar |  | 39W18 | 2017-08-16 | 2017-09-05 | 14 | 3 | 11 | 2017-09-29 | 2017-10-26 | 19 |  | 19 | [20 empty] | 2017-10-26 |  | 2017-10-20 | NO | Expedited | [8 empty] | 2018-01-29 | In Operation | Res | Y
Fitchburg | Townsend | 2867 | 1469 | 10.95 |  |  | Solar |  | 15W16 | 2017-08-16 | 2017-09-05 | 14 |  | 14 | 2017-09-29 | 2017-10-26 | 19 |  | 19 | [20 empty] | 2017-10-26 |  | 2017-09-16 | NO | Expedited | [8 empty] | 2017-12-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2865 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-08-15 | 2017-08-23 | 7 |  | 7 | 2017-09-15 | 2017-10-26 | 29 |  | 29 | [20 empty] | 2017-10-26 |  | 2017-08-17 | NO | Expedited | [8 empty] | 2017-12-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2864 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-08-14 | 2017-09-22 | 29 | 1 | 28 | 2017-10-12 | 2017-10-26 | 11 |  | 11 | [20 empty] | 2017-10-26 |  | 2017-08-28 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2855 | 1420 | 10.95 |  |  | Solar |  | 50W51 | 2017-08-10 | 2017-08-17 | 6 |  | 6 | 2017-09-14 | 2017-09-29 | 12 |  | 12 | [20 empty] | 2017-10-05 |  | 2017-10-10 | NO | Expedited | [8 empty] | 2017-11-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2853 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2017-08-14 | 2017-08-17 | 4 |  | 4 | 2017-09-14 | 2017-09-29 | 12 |  | 12 | [20 empty] | 2017-10-11 |  | 2017-10-11 | NO | Expedited | [8 empty] | 2018-02-15 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2852 | 1420 | 5 |  |  | Solar |  | 20W22 | 2017-08-11 | 2017-09-25 | 31 | 25 | 6 | 2017-10-27 | 2017-11-22 | 18 | 3 | 15 | [20 empty] | 2017-11-22 |  | 2017-08-20 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2849 | 1462 | 5.45 |  |  | Solar |  | 30W31 | 2017-08-08 | 2017-08-11 | 4 |  | 4 | 2017-09-25 | 2017-10-24 | 21 |  | 21 | [20 empty] | 2017-11-01 |  | 2017-09-08 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2847 | 1469 | 9 |  |  | Solar |  | 15W16 | 2017-08-08 | 2017-08-11 | 4 |  | 4 | 2017-09-11 | 2017-09-29 | 15 |  | 15 | [20 empty] | 2017-10-12 |  | 2017-10-10 | NO | Expedited | [8 empty] | 2017-11-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2846 | 1462 | 7.6 |  |  | Solar |  | 31W37 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-07 | NO | Expedited | [8 empty] | 2018-01-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2845 | 1420 | 7.6 |  |  | Solar |  | 11W11 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-04 | NO | Expedited | [8 empty] | 2018-04-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2844 | 1462 | 12 |  |  | Solar |  | 30W30 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-28 | 19 |  | 19 | [20 empty] | 2017-09-28 |  | 2017-10-04 | NO | Expedited | [8 empty] | 2017-11-09 | In Operation | Res | Y
Fitchburg | Townsend | 2843 | 1469 | 8.35 |  |  | Solar |  | 15W16 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-08-30 | 2017-09-15 | 12 |  | 12 | [20 empty] | 2017-10-12 |  | 2017-10-03 | YES | Expedited | [8 empty] | 2018-04-04 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2842 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-15 | 10 |  | 10 | [20 empty] | 2017-10-12 |  | 2017-10-03 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2841 | 1462 | 12 |  |  | Solar |  | 31W38 | 2017-08-07 | 2017-08-10 | 4 |  | 4 | 2017-09-01 | 2017-09-15 | 10 |  | 10 | [20 empty] | 2017-10-04 |  | 2017-10-03 | YES | Expedited | [8 empty] | 2018-03-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2837 | 1420 | 1860 |  |  | Solar |  | 31W37 | 2018-01-11 | 2018-03-19 | 43 | 43 | 0 | [10 empty] | 2018-04-17 | 2018-05-13 | 19 |  | 19 | 2018-08-03 | 2019-03-28 | 161 | 29 | 132 | [7 empty] | 2018-10-01 | NO | Standard | [9 empty] | Cancelled | Comm
Fitchburg | Lunenburg | 2828 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-08-01 | 2017-08-14 | 10 |  | 10 | 2017-09-13 | 2017-09-28 | 12 |  | 12 | [20 empty] | 2017-10-12 |  | 2017-09-27 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2815 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-06-30 | 2017-08-02 | 23 |  | 23 | 2017-08-09 | 2017-08-31 | 17 |  | 17 | [20 empty] | 2017-08-31 |  | 2017-08-29 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2808 | 1462 | 10.95 |  |  | Solar |  | 31W37 | 2017-07-31 | 2017-08-03 | 4 | 1 | 3 | 2017-08-17 | 2017-09-15 | 21 |  | 21 | [20 empty] | 2017-09-19 |  | 09/31/2017 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2807 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2017-07-27 | 2017-08-03 | 6 | 2 | 4 | 2017-09-06 | 2017-09-28 | 17 |  | 17 | [20 empty] | 2017-10-10 |  | 2017-08-27 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2803 | 1462 | 7.68 |  |  | Solar |  | 30W30 | 2017-07-25 | 2017-08-01 | 6 |  | 6 | 2017-08-17 | 2017-09-15 | 21 |  | 21 | [20 empty] | 2017-09-19 |  | 2017-07-25 | NO | Expedited | [8 empty] | 2017-12-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2802 | 1420 | 3 |  |  | Solar |  | 01W02 | 2017-07-24 | 2017-07-26 | 3 | 1 | 2 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2797 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2017-07-21 | 2017-07-25 | 3 |  | 3 | 2017-08-03 | 2017-08-23 | 15 |  | 15 | [20 empty] | 2017-08-31 |  |  | NO | Expedited | [8 empty] | 2018-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2794 | 1420 | 10 |  |  | Solar |  | 35W36 | 2017-07-20 | 2017-07-28 | 7 | 3 | 4 | 2017-08-17 | 2017-09-18 | 22 |  | 22 | [20 empty] | 2017-09-19 |  | 2017-10-07 | NO | Expedited | [8 empty] | 2017-11-07 | In Operation | Res | Y
Fitchburg | Townsend | 2793 | 1469 | 8.35 |  |  | Solar |  | 39W18 | 2017-07-20 | 2017-07-27 | 6 | 2 | 4 | 2017-08-10 | 2017-09-07 | 20 |  | 20 | [20 empty] | 2017-09-07 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-10-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2792 | 1420 | 5 |  |  | Solar |  | 25W27 | 2017-07-19 | 2017-07-21 | 3 |  | 3 | 2017-08-01 | 2017-08-23 | 17 |  | 17 | [20 empty] | 2017-08-28 |  |  | NO | Expedited | [8 empty] | 2018-03-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2791 | 1420 | 3.8 |  |  | Solar |  | 40W42 | 2017-07-19 | 2017-07-21 | 3 |  | 3 | 2017-08-04 | 2017-08-23 | 14 |  | 14 | [20 empty] | 2017-08-28 |  |  | NO | Expedited | [8 empty] | 2017-11-08 | In Operation | Res | Y
Fitchburg | West Townsend | 2790 | 1474 | 8.35 |  |  | Solar |  | 39W18 | 2017-07-19 | 2017-07-27 | 7 | 5 | 2 | 2017-08-24 | 2017-09-24 | 21 |  | 21 | [20 empty] | 2017-09-21 |  | 2017-08-02 | YES | Expedited | [8 empty] | 2017-11-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2788 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2017-07-17 | 2017-07-19 | 3 |  | 3 | 2017-08-02 | 2017-09-15 | 32 |  | 32 | [20 empty] | 2017-09-15 |  | 2017-09-14 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2785 | 1469 | 8.35 |  |  | Solar |  | 39W18 | 2017-07-14 | 2017-08-03 | 15 | 9 | 6 | 2017-08-18 | 2017-09-15 | 20 |  | 20 | [20 empty] | 2017-09-19 |  | 2017-08-13 | NO | Expedited | [8 empty] | 2017-10-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2784 | 1420 | 3 |  |  | Solar |  | 25W27 | 2017-07-14 | 2017-07-19 | 4 |  | 4 | 2017-08-09 | 2017-09-15 | 27 |  | 27 | [20 empty] | 2017-10-04 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2783 | 1420 | 10.1 |  |  | Solar |  | 25W27 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-08-24 | 2017-09-15 | 16 |  | 16 | [20 empty] | 2017-09-21 |  | 2017-09-13 | NO | Expedited | [8 empty] | 2018-04-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2781 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-07-27 | 2017-08-23 | 20 |  | 20 | [20 empty] | 2017-08-28 |  | 2017-09-13 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Townsend | 2780 | 1474 | 8.35 |  |  | Solar |  | 39W18 | 2017-07-14 | 2017-07-14 | 1 |  | 1 | 2017-07-27 | 2017-08-23 | 20 |  | 20 | [20 empty] | 2017-08-28 |  | 2017-09-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2779 | 1420 | 3.8 |  |  | Solar |  | 25W27 | 2017-07-13 | 2017-07-14 | 2 |  | 2 | 2017-08-03 | 2017-08-23 | 15 |  | 15 | [20 empty] | 2017-08-31 |  |  | NO | Expedited | [8 empty] | 2018-01-04 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2774 | 1420 | 7.6 |  |  | Solar |  | 50W51 | 2017-10-17 | 2017-10-18 | 2 |  | 2 | 2017-08-21 | 2017-09-18 | 20 |  | 20 | [20 empty] | 2017-10-19 |  | 2017-08-07 | NO | Expedited | [8 empty] | 2017-10-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2773 | 1462 | 7.6 |  |  | Solar |  | 30W31 | 2017-07-10 | 2017-07-11 | 2 |  | 2 | 2017-11-27 | 2017-12-04 | 6 |  | 6 | [20 empty] | 2017-12-07 |  | 2017-09-10 | NO | Expedited | [8 empty] | 2018-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2772 | 1420 | 8.35 |  |  | Solar |  | 25W27 | 2017-06-30 | 2017-07-05 | 3 |  | 3 | 2017-08-10 | 2017-09-06 | 19 |  | 19 | [20 empty] | 2017-09-06 |  |  | NO | Expedited | [8 empty] | 2018-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2771 | 1420 | 10.05 |  |  | Solar |  | 31W37 | 2017-06-30 | 2017-07-07 | 5 |  | 5 | 2017-07-25 | 2017-08-23 | 22 |  | 22 | [20 empty] | 2017-08-29 |  | 2017-08-30 | NO | Expedited | [8 empty] | 2017-10-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2770 | 1462 | 10 |  |  | Solar |  | 30W31 | 2017-06-27 | 2017-06-30 | 4 |  | 4 | 2017-07-14 | 2017-08-22 | 28 |  | 28 | [20 empty] | 2017-08-23 |  |  | NO | Expedited | [8 empty] | 2017-10-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2769 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-06-27 | 2017-07-05 | 6 |  | 6 | 2017-07-17 | 2017-08-23 | 28 |  | 28 | [20 empty] | 2017-08-24 |  | 2017-07-24 | NO | Expedited | [8 empty] | 2017-12-21 | In Operation | Res | Y
Fitchburg | Townsend | 2768 | 1469 | 10.95 |  |  | Solar |  | 15w16 | 2017-06-27 | 2017-06-30 | 4 |  | 4 | 2017-08-04 | 2017-08-24 | 15 |  | 15 | [20 empty] | 2017-08-31 |  | 2017-07-07 | NO | Expedited | [8 empty] | 2017-11-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2762 | 1420 | 6 |  |  | Solar |  | 01W04 | 2017-06-26 | 2017-06-28 | 3 |  | 3 | 2017-08-04 | 2017-08-24 | 15 |  | 15 | [20 empty] | 2017-08-31 |  | 2017-07-28 | NO | Expedited | [8 empty] | 2017-11-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2755 | 1420 | 3 |  |  | Solar |  | 01W04 | 2017-06-23 | 2017-07-10 | 11 | 8 | 3 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2753 | 1420 | 4.15 |  |  | Solar |  | 20W22 | 2017-06-21 | 2017-06-27 | 5 |  | 5 | 2017-07-13 | 2017-08-22 | 29 |  | 29 | [20 empty] | 2017-08-22 |  | 2017-08-21 | NO | Expedited | [8 empty] | 2017-10-17 | In Operation | Res | Y
Fitchburg | Townsend | 2752 | 1469 | 6.6 |  |  | Solar |  | 15W16 | 2017-06-21 | 2017-06-26 | 4 |  | 4 | 2017-08-18 | [24 empty] | 2017-08-18 |  | 2017-08-21 | NO | Expedited | [8 empty] | 2017-09-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2751 | 1420 | 4.6 |  |  | Solar |  | 25W27 | 2017-06-19 | 2017-06-26 | 6 |  | 6 | 2017-07-13 | 2017-08-22 | 29 |  | 29 | [20 empty] | 2017-08-23 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-12-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2747 | 1462 | 9.9 |  |  | Solar |  | 31W38 | 2017-06-15 | 2017-06-20 | 4 |  | 4 | 2017-07-18 | 2017-09-13 | 41 |  | 41 | [20 empty] | 2017-08-31 |  | 2017-08-13 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 2746 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-06-13 | 2017-06-20 | 6 |  | 6 | 2017-07-06 | 2017-09-07 | 45 |  | 45 | [20 empty] | 2017-09-07 |  | 2017-08-14 | NO | Expedited | [8 empty] | 2018-01-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2744 | 1420 | 159.9 |  |  | Solar |  | 01W04 | 2017-06-23 | 2017-06-27 | 3 |  | 3 | 2017-07-06 | 2017-08-02 | 20 |  | 20 | [20 empty] | 2017-08-02 |  | 2017-10-01 | YES | Expedited | [8 empty] | 2018-03-06 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2743 | 1462 | 4.15 |  |  | Solar |  | 30W31 | 2017-06-08 | 2017-07-10 | 22 | 17 | 5 | 2017-08-22 | 2017-09-15 | 18 |  | 18 | [20 empty] | 2017-09-19 |  | 2017-08-19 | NO | Expedited | [8 empty] | 2017-11-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 2742 | 1420 | 8.35 |  |  | Solar |  | 31W37 | 2017-06-08 | 2017-06-13 | 4 |  | 4 | 2017-06-27 | 2017-08-17 | 37 |  | 37 | [20 empty] | 2017-08-18 |  | 2017-08-07 | NO | Expedited | [8 empty] | 2017-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2739 | 1420 | 8.35 |  |  | Solar |  | 01W02 | 2017-06-06 | 2017-06-12 | 5 |  | 5 | 2017-06-27 | 2017-08-17 | 37 |  | 37 | [20 empty] | 2017-08-18 |  | 2017-08-06 | NO | Expedited | [8 empty] | 2017-09-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2729 | 1462 | 7.68 |  |  | Solar |  | 30W30 | 2017-06-01 | 2017-06-05 | 3 |  | 3 | 2017-07-13 | 2017-08-17 | 26 |  | 26 | [20 empty] | 2017-08-18 |  | 2017-09-11 | NO | Expedited | [8 empty] | 2017-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 2723 | 1469 | 997.7 |  |  | Solar |  | 39W18 | 2017-05-24 | 2017-06-23 | 22 | 10 | 12 | [10 empty] | 2017-06-24 | 2017-08-05 | 29 |  | 29 | 2017-08-19 | 2017-12-22 | 86 |  | 86 | 2018-05-04 | 2018-06-26 | 37 |  | 37 | 2018-07-11 | 2019-06-13 | 2018-01-30 | YES | Standard | [6 empty] | 2020-07-10 | 2020-07-10 | 2020-10-07 | In Operation | Comm | Y
Fitchburg | Townsend | 2720 | 1469 | 8.35 |  |  | Solar |  | 15W16 | 2017-05-23 | 2017-06-01 | 7 | 5 | 2 | 2017-06-23 | 2017-08-02 | 28 | 5 | 23 | [20 empty] | 2017-08-02 |  |  | NO | Expedited | [8 empty] | 2017-08-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2714 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-05-17 | 2017-05-22 | 4 |  | 4 | 2017-07-17 | 2017-08-31 | 34 |  | 34 | [20 empty] | 2017-08-31 |  | 2017-04-14 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Ashby | 2712 | 1431 | 10.95 |  |  | Solar |  | 39W19 | 2017-05-17 | 2017-05-22 | 4 |  | 4 | 2017-06-08 | 2017-06-21 | 10 |  | 10 | [20 empty] | 2017-06-27 |  | 2017-07-01 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Townsend | 2709 | 1469 | 8.35 |  |  | Solar |  | 15W16 | 2017-05-15 | 2017-05-19 | 5 | 1 | 4 | 2017-07-17 | 2017-08-18 | 25 |  | 25 | [20 empty] | 2017-08-18 |  | 2017-06-09 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 2708 | 1462 | 5.45 |  |  | Solar |  | 30W30 | 2017-05-15 | 2017-05-17 | 3 |  | 3 | 2017-05-30 | 2017-06-26 | 20 |  | 20 | [20 empty] | 2017-06-26 |  |  | NO | Expedited | [8 empty] | 2017-08-14 | In Operation | Res | Y
Fitchburg | Townsend | 2704 | 1469 | 8.35 |  |  | Solar |  | 39W18 | 2017-05-12 | 2017-05-16 | 3 |  | 3 | 2017-05-30 | 2017-06-20 | 16 |  | 16 | [20 empty] | 2017-06-27 |  | 2017-07-10 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2695 | 1420 | 168 |  |  | Solar |  | 40W40 | 2017-05-03 | 2017-06-12 | 28 | 13 | 15 | 2017-06-12 | 2017-07-31 | 35 |  | 35 | [20 empty] | 2017-07-31 |  | 2017-08-02 | NO | Expedited | [8 empty] | 2017-12-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2692 | 1462 | 10 |  |  | Solar |  | 30W30 | 2017-05-02 | 2017-05-04 | 3 |  | 3 | 2017-06-02 | 2017-06-27 | 18 |  | 18 | [20 empty] | 2017-06-27 |  | 2017-05-24 | NO | Expedited | [8 empty] | 2017-12-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2691 | 1462 | 4.95 |  |  | Solar |  | 31W38 | 2017-05-02 | 2017-05-03 | 2 |  | 2 | 2017-05-23 | 2017-06-12 | 14 |  | 14 | [20 empty] | 2017-06-12 |  | 2017-07-01 | NO | Expedited | [8 empty] | 2017-07-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2690 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-05-02 | 2017-05-03 | 2 |  | 2 | 2017-06-19 | 2017-06-21 | 3 |  | 3 | [20 empty] | 2017-06-27 |  | 2017-07-01 | YES | Expedited | [8 empty] | 2017-09-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2688 | 1462 | 9.92 |  |  | Solar |  | 30W31 | 2017-05-01 | 2017-05-03 | 3 |  | 3 | 2017-05-15 | 2017-06-20 | 26 |  | 26 | [20 empty] | 2017-06-26 |  | 2017-06-30 | NO | Expedited | [8 empty] | 2017-09-12 | In Operation | Res | Y
Fitchburg | Lunenburg | 2684 | 1462 | 10.13 |  |  | Solar |  | 30W30 | 2017-04-28 | 2017-05-01 | 2 |  | 2 | [28 empty] | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2682 | 1431 | 5.76 |  |  | Solar |  | 39W19 | 2017-04-26 | 2017-04-27 | 2 |  | 2 | 2017-05-11 | 2017-06-20 | 28 |  | 28 | [20 empty] | 2017-06-26 |  | 2017-06-01 | NO | Expedited | [8 empty] | 2017-08-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 2681 | 1462 | 10 |  |  | Solar |  | 30W30 | 2017-04-26 | 2017-04-27 | 2 |  | 2 | 2017-05-12 | [26 empty] | 2017-06-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2673 | 1420 | 10 |  |  | Solar |  | 31W37 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-09 | 2017-06-20 | 30 | 7 | 23 | [22 empty] | 2017-05-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2672 | 1462 | 9.92 |  |  | Solar |  | 30W31 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-08 | 2017-06-20 | 31 |  | 31 | [20 empty] | 2017-06-23 |  | 06/31/2017 | NO | Expedited | [8 empty] | 2017-08-01 | In Operation | Res | Y
Fitchburg | Townsend | 2671 | 1469 | 6 |  |  | Solar |  | 30W31 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-12 | 2017-06-20 | 27 |  | 27 | [20 empty] | 2017-06-26 |  | 2017-06-18 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2670 | 1420 | 8.75 |  |  | Solar |  | 01W02 | 2017-04-19 | 2017-04-24 | 4 |  | 4 | 2017-05-11 | 2017-06-20 | 28 |  | 28 | [20 empty] | 2017-06-23 |  | 2017-06-03 | NO | Expedited | [8 empty] | 2017-08-08 | In Operation | Res | Y
Fitchburg | Townsend | 2667 | 1469 | 8.35 |  |  | Solar |  | 15W16 | 2017-04-18 | 2017-04-24 | 5 | 2 | 3 | 2017-05-05 | 2017-06-19 | 31 |  | 31 | [20 empty] | 2017-06-20 |  | 2017-05-12 | NO | Expedited | [8 empty] | 2017-07-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2666 | 1462 | 3.8 |  |  | Solar |  | 30W30 | 2017-04-18 | 2017-04-20 | 3 |  | 3 | 2017-05-02 | 2017-06-20 | 35 |  | 35 | [20 empty] | 2017-06-23 |  | 2017-06-18 | NO | Expedited | [8 empty] | 2017-07-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2665 | 1420 | 6 |  |  | Solar |  | 01W02 | 2017-04-18 | 2017-04-19 | 2 |  | 2 | 2017-05-26 | 2017-06-20 | 17 |  | 17 | [20 empty] | 2017-06-26 |  | 2017-05-17 | NO | Expedited | [8 empty] | 2017-08-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2664 | 1420 | 7.45 |  |  | Solar |  | 50W51 | 2017-04-17 | 2017-04-19 | 2 |  | 2 | 2017-05-01 | 2017-06-15 | 33 |  | 33 | [20 empty] | 2017-06-16 |  | 2017-12-27 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Townsend | 2663 | 1469 | 12.15 |  |  | Solar |  | 15W16 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | 2017-05-02 | 2017-06-15 | 32 |  | 32 | [20 empty] | 2017-06-16 |  | 2017-06-14 | NO | Expedited | [8 empty] | 2017-09-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2662 | 1420 | 12 |  |  | Solar |  | 20W22 | 2017-04-14 | 2017-04-19 | 3 | 1 | 2 | 2017-05-02 | 2017-06-15 | 32 |  | 32 | [20 empty] | 2017-06-16 |  | 2017-06-13 | NO | Expedited | [8 empty] | 2017-09-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2661 | 1420 | 4 |  |  | Solar |  | 31W37 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | 2017-05-01 | 2017-06-05 | 25 |  | 25 | [20 empty] | 2017-06-12 |  | 2017-06-14 | NO | Expedited | [8 empty] | 2017-08-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2660 | 1462 | 9.6 |  |  | Solar |  | 31w37 | 2017-04-14 | 2017-04-19 | 3 |  | 3 | [27 empty] | 2016-06-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2659 | 1420 | 8.35 |  |  | Solar |  | 25W27 | 2017-04-14 | 2017-04-18 | 2 |  | 2 | 2017-04-27 | 2017-06-05 | 27 |  | 27 | [20 empty] | 2017-06-05 |  | 2017-05-26 | NO | Expedited | [8 empty] | 2017-07-05 | In Operation | Res | Y
Fitchburg | Townsend | 2656 | 1474 | 14.75 |  |  | Solar |  | 39W18 | 2017-04-12 | 2017-04-13 | 2 |  | 2 | 2017-04-20 | 2017-06-16 | 41 |  | 41 | [20 empty] | 2017-06-16 |  | 2017-06-11 | YES | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2654 | 1420 | 8.75 |  |  | Solar |  | 25W27 | 2017-04-10 | 2017-04-13 | 4 |  | 4 | 2017-04-26 | 2017-06-20 | 39 |  | 39 | [20 empty] | 2017-06-20 |  | 2017-06-10 | NO | Expedited | [8 empty] | 2017-09-06 | In Operation | Res | Y
Fitchburg | Townsend | 2653 | 1474 | 8.35 |  |  | Solar |  | 39W18 | 2017-04-06 | 2017-04-10 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-22 | In Operation | Res | Y
Fitchburg | Townsend | 2651 | 1469 | 12.5 |  |  | Solar |  | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-25 | 26 |  | 26 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Townsend | 2650 | 1469 | 8.35 |  |  | Solar |  | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Townsend | 2649 | 1469 | 8.35 |  |  | Solar |  | 15W17 | 2017-04-05 | 2017-04-07 | 3 |  | 3 | 2017-04-20 | 2017-05-25 | 26 |  | 26 | [20 empty] | 2017-05-30 |  | 2017-06-05 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2647 | 1420 | 6.4 |  |  | Solar |  | 01W04 | 2017-04-03 | 2017-04-05 | 3 |  | 3 | [27 empty] | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2644 | 1469 | 12.15 |  |  | Solar |  | 39W18 | 2017-04-03 | 2017-04-05 | 3 |  | 3 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-02 | NO | Expedited | [8 empty] | 2018-03-21 | In Operation | Res | Y
Fitchburg | Townsend | 2643 | 1469 | 15 |  |  | Solar |  | 15W16 | 2017-04-26 | 2017-06-05 | 28 |  | 28 | 2017-06-30 | 2017-08-18 | 35 |  | 35 | [20 empty] | 2017-08-18 |  | 2017-08-01 | NO | Expedited | [8 empty] | 2017-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 2642 | 1469 | 7.95 |  |  | Solar |  | 15W16 | 2017-03-27 | 2017-05-17 | 37 | 32 | 5 | 2017-05-26 | 2017-06-19 | 16 |  | 16 | [20 empty] | 2017-06-21 |  | 2017-06-28 | NO | Expedited | [8 empty] | 2018-03-16 | In Operation | Res | Y
Fitchburg | Townsend | 2640 | 1469 | 7.6 |  |  | Solar |  | 39W18 | 2017-03-31 | 2017-04-04 | 3 |  | 3 | 2017-04-26 | 2017-06-20 | 39 |  | 39 | [20 empty] | 2017-06-20 |  | 2017-05-27 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 2639 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-03-30 | 2017-04-04 | 4 |  | 4 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2638 | 1420 | 8.35 |  |  | Solar |  | 31W37 | 2017-03-30 | 2017-04-04 | 4 |  | 4 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-06-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2636 | 1420 | 396 |  |  | Solar |  | 50W51 | 2017-05-26 | 2017-06-30 | 25 |  | 25 | 2017-06-30 | 2017-08-04 | 25 |  | 25 | 2017-08-14 | 2017-09-15 | 24 |  | 24 | [15 empty] | 2017-09-15 |  | 2017-07-15 | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Ashby | 2635 | 1431 | 4.15 |  |  | Solar |  | 39W19 | 2017-03-29 | 2017-04-04 | 5 | 3 | 2 | 2017-04-13 | 2017-05-30 | 32 |  | 32 | [20 empty] | 2017-05-30 |  | 2017-06-28 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2634 | 1469 | 10.95 |  |  | Solar |  | 15W16 | 2017-03-28 | 2017-05-02 | 25 |  | 25 | 2017-05-15 | 2017-06-19 | 25 |  | 25 | [20 empty] | 2017-06-20 |  | 2017-05-01 | NO | Expedited | [8 empty] | 2017-10-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2632 | 1420 | 10.95 |  |  | Solar |  | 11W11 | 2017-03-27 | 2017-03-31 | 5 |  | 5 | 2017-04-28 | 2017-06-02 | 25 |  | 25 | [20 empty] | 2017-06-16 |  |  | YES | Expedited | [8 empty] | 2017-11-08 | Not In Service | Res | Y
Fitchburg | Ashby | 2631 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2017-03-29 | 2017-04-11 | 10 |  | 10 | 2017-04-20 | 2017-05-30 | 28 |  | 28 | [20 empty] | 2017-05-30 |  | 2017-04-27 | NO | Expedited | [8 empty] | 2017-07-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2628 | 1420 | 3.8 |  |  | Solar |  | 01W04 | 2017-03-24 | 2017-03-29 | 4 |  | 4 | 2017-04-05 | 2017-05-05 | 22 |  | 22 | [20 empty] | 2017-05-05 |  | 2017-06-24 | NO | Expedited | [8 empty] | 2017-08-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 2627 | 1420 | 12 |  |  | Solar |  | 01W04 | 2017-03-23 | 2017-03-27 | 3 |  | 3 | 2017-04-05 | 2017-05-05 | 22 |  | 22 | [20 empty] | 2017-05-05 |  | 2017-05-22 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2625 | 1420 | 10.95 |  |  | Solar |  | 01W04 | 2017-03-23 | 2017-03-29 | 5 |  | 5 | 2017-04-13 | 2017-05-08 | 17 |  | 17 | [20 empty] | 2017-05-08 |  |  | NO | Expedited | [8 empty] | 2017-07-06 | In Operation | Res | Y
Fitchburg | Ashby | 2623 | 1431 | 7.6 |  |  | Solar |  | 39W19 | 2017-03-22 | 2017-03-30 | 7 |  | 7 | 2017-04-17 | 2017-05-30 | 30 |  | 30 | [20 empty] | 2017-05-30 |  | 2017-05-22 | NO | Expedited | [8 empty] | 2017-08-28 | In Operation | Res | Y
Fitchburg | Lunenburg | 2618 | 1462 | 6 |  |  | Solar |  | 30W30 | 2017-03-21 | 2017-03-27 | 5 |  | 5 | 2017-04-21 | 2017-05-30 | 27 |  | 27 | [20 empty] | 2017-05-30 |  | 2017-05-01 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2614 | 1420 | 3.8 |  |  | Solar |  | 20W22 | 2017-03-15 | 2017-03-21 | 4 |  | 4 | 2017-04-05 | 2017-05-04 | 21 |  | 21 | [20 empty] | 2017-05-05 |  | 2017-06-06 | NO | Expedited | [8 empty] | 2017-07-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2613 | 1462 | 10 |  |  | Solar |  | 31W37 | 2017-03-14 | 2017-03-29 | 11 | 4 | 7 | 2017-04-17 | 2017-05-30 | 30 |  | 30 | [20 empty] | 2017-05-30 |  | 2017-04-04 | NO | Expedited | [8 empty] | 2017-06-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2612 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-03-14 | 2017-03-27 | 9 |  | 9 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-04-15 | NO | Expedited | [8 empty] | 2017-06-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2611 | 1462 | 7.2 |  |  | Solar |  | 30W30 | 2017-03-13 | 2017-03-17 | 4 |  | 4 | 2017-05-11 | 2017-06-27 | 33 |  | 33 | [20 empty] | 2017-06-27 |  | 2017-05-13 | NO | Expedited | [8 empty] | 2017-09-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2610 | 1420 | 9 |  |  | Solar |  | 01W02 | 2017-03-13 | 2017-03-17 | 4 |  | 4 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-05-13 | NO | Expedited | [8 empty] | 2017-06-06 | In Operation | Res | Y
Fitchburg | Townsend | 2608 | 1469 | 10.95 |  |  | Solar |  | 39W18 | 2017-03-10 | 2017-03-15 | 4 |  | 4 | 2017-03-22 | 2017-05-01 | 28 |  | 28 | [20 empty] | 2017-05-05 |  | 2017-04-19 | NO | Expedited | [8 empty] | 2017-06-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2606 | 1462 | 5.45 |  |  | Solar |  | 30W31 | 2017-03-09 | 2017-03-10 | 2 |  | 2 | 2017-04-07 | 2017-05-04 | 19 |  | 19 | [20 empty] | 2017-05-08 |  |  | NO | Expedited | [8 empty] | 2017-06-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2605 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-03-09 | 2017-04-10 | 22 | 14 | 8 | 2017-04-19 | 2017-05-25 | 27 |  | 27 | [20 empty] | 2017-05-30 |  | 2017-04-19 | NO | Expedited | [8 empty] | 2017-09-18 | In Operation | Res | Y
Fitchburg | Ashby | 2604 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2017-03-07 | 2017-03-10 | 4 |  | 4 | 2017-03-24 | 2017-05-04 | 29 |  | 29 | [20 empty] | 2017-05-05 |  | 2017-05-08 | NO | Expedited | [8 empty] | 2017-08-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 2601 | 1420 | 9 |  |  | Solar |  | 01W04 | 2017-03-03 | 2017-03-08 | 4 |  | 4 | 2017-03-16 | 2017-04-26 | 28 |  | 28 | [20 empty] | 2017-04-28 |  | 2017-05-02 | NO | Expedited | [8 empty] | 2017-06-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2600 | 1420 | 3204 |  |  | Solar |  | 31W37 | 2017-04-03 | 2017-05-12 | 29 |  | 29 | [10 empty] | 2018-05-13 | 2018-05-13 | 0 |  | 0 | 2017-05-17 | 2017-09-08 | 80 |  | 80 | [5 empty] | 2017-10-28 | 2019-07-29 | 2018-06-01 | YES | Standard | [6 empty] | 2020-12-21 | 2020-12-21 | 2020-12-22 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2591 | 1462 | 23.04 |  |  | Solar |  | 31W38 | 2017-03-17 | 2017-04-03 | 11 |  | 11 | 2017-04-04 | 2017-04-13 | 8 |  | 8 | [20 empty] | 2017-11-22 |  | 2017-04-01 | NO | Expedited | [8 empty] | 2017-12-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2586 | 1420 | 8.35 |  |  | Solar |  | 20W22 | 2017-02-13 | 2017-02-20 | 5 |  | 5 | 2017-02-27 | 2017-03-30 | 22 |  | 22 | [20 empty] | 2017-08-11 |  | 2017-09-08 | YES | Expedited | [8 empty] | 2017-09-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2585 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2017-02-15 | 2017-02-17 | 3 |  | 3 | [27 empty] | 2017-04-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2584 | 1420 | 5.76 |  |  | Solar |  | 35W36 | 2017-02-23 | 2017-04-27 | 43 | 35 | 8 | 2017-06-19 | 2017-07-10 | 15 |  | 15 | [20 empty] | 2017-07-10 |  | 2017-01-20 | NO | Expedited | [8 empty] | 2017-08-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2580 | 1420 | 5 |  |  | Solar |  | 01W02 | 2017-02-14 | 2017-02-16 | 3 |  | 3 | 2017-03-20 | 2017-04-28 | 29 |  | 29 | [20 empty] | 2017-04-28 |  | 2017-03-17 | NO | Expedited | [8 empty] | 2017-06-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2577 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-02-14 | 2017-02-15 | 2 |  | 2 | 2017-03-15 | 2017-04-26 | 29 |  | 29 | [20 empty] | 2017-04-27 |  | 2017-04-14 | NO | Expedited | [8 empty] | 2017-07-14 | In Operation | Res | Y
Fitchburg | Townsend | 2575 | 1469 | 8.35 |  |  | Solar |  | 30W31 | 2017-02-13 | 2017-02-15 | 3 |  | 3 | 2017-03-15 | 2017-04-26 | 29 |  | 29 | [20 empty] | 2017-04-27 |  | 2017-04-10 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2570 | 1420 | 3.6 |  |  | Solar |  | 50W51 | 2017-02-10 | 2017-02-14 | 3 |  | 3 | 2017-03-23 | 2017-05-02 | 28 |  | 28 | [20 empty] | 2017-05-05 |  | 2017-04-10 | NO | Expedited | [8 empty] | 2017-07-13 | Cancelled | Res | Y
Fitchburg | Townsend | 2564 | 1469 | 7.6 |  |  | Solar |  | 15W16 | 2017-02-06 | 2017-02-08 | 3 |  | 3 | [25 empty] | 2017-03-31 |  |  |  | Expedited | [8 empty] | 2017-05-03 | In Operation |  | Y
Fitchburg | Fitchburg | 2562 | 1420 | 4.15 |  |  | Solar |  | 31W37 | 2017-01-31 | 2017-02-06 | 5 |  | 5 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-03-31 |  | 2017-03-31 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2561 | 1420 | 10.95 |  |  | Solar |  | 31W37 | 2017-02-03 | 2017-02-06 | 2 |  | 2 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-04-05 |  | 2017-08-09 | YES | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2559 | 1462 | 3.8 |  |  | Solar |  | 30W30 | 2017-01-31 | 2017-02-03 | 4 |  | 4 | 2017-03-09 | 2017-04-26 | 33 |  | 33 | [20 empty] | 2017-04-27 |  | 2017-03-31 | NO | Expedited | [8 empty] | 2017-05-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2558 | 1462 | 5.2 |  |  | Solar |  | 31W37 | 2017-01-31 | 2017-02-03 | 4 |  | 4 | 2017-02-27 | 2017-03-28 | 20 |  | 20 | [20 empty] | 2017-03-31 |  | 2017-03-31 | NO | Expedited | [8 empty] | 2017-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2556 | 1462 | 10.96 |  |  | Solar |  | 30W30 | 2017-01-30 | 2017-02-02 | 4 |  | 4 | 2017-04-06 | 2017-05-04 | 20 |  | 20 | [20 empty] | 2017-05-05 |  | 2017-03-30 | NO | Expedited | [8 empty] | 2017-07-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2554 | 1462 | 21.3 |  |  | Solar |  | 30W30 | 2017-01-25 | 2017-03-01 | 24 | 15 | 9 | 2017-04-21 | 2017-05-16 | 18 |  | 18 | [22 empty] | 2016-12-29 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2553 | 1462 | 4.15 |  |  | Solar |  | 31W37 | 2017-01-25 | 2017-02-02 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-24 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2552 | 1642 | 4.15 |  |  | Solar |  | 31W38 | 2017-01-25 | 2017-02-03 | 8 |  | 8 | 2018-03-28 | 2018-04-05 | 7 |  | 7 | [20 empty] | 2018-04-09 |  | 2017-03-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2551 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2017-01-25 | 2017-02-03 | 8 |  | 8 | 2017-02-27 | 2017-03-29 | 21 |  | 21 | [20 empty] | 2017-04-12 |  | 2017-03-24 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2550 | 1420 | 8.35 |  |  | Solar |  | 35W36 | 2017-01-25 | 2017-02-02 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-24 | NO | Expedited | [8 empty] | 2017-07-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2545 | 1420 | 10.95 |  |  | Solar |  | 20W22 | 2017-01-23 | 2017-02-02 | 9 |  | 9 | 2017-02-27 | 2017-04-13 | 32 |  | 32 | [20 empty] | 2017-04-18 |  | 2017-08-09 | YES | Expedited | [8 empty] | 2017-09-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2542 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-01-17 | 2017-02-02 | 13 |  | 13 | 2017-02-27 | 2017-03-30 | 22 |  | 22 | [20 empty] | 2017-04-03 |  | 2017-03-17 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Ashby | 2541 | 1431 | 6 |  |  | Solar |  | 39W19 | 2017-01-18 | 2017-01-31 | 10 |  | 10 | 2017-02-06 | 2017-03-06 | 18 |  | 18 | [20 empty] | 2017-03-13 |  | 2017-01-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2540 | 1462 | 10 |  |  | Solar |  | 30W30 | 2017-01-12 | 2017-01-23 | 7 |  | 7 | 2017-01-27 | 2017-03-09 | 27 |  | 27 | [20 empty] | 2017-03-30 |  | 2017-06-30 | YES | Expedited | [8 empty] | 2017-08-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2539 | 1462 | 17 |  |  | Solar |  | 30W31 | 2017-01-18 | 2017-01-19 | 2 |  | 2 | 2017-01-19 | 2017-03-02 | 28 |  | 28 | [20 empty] | 2017-03-06 |  |  | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 2538 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2017-01-11 | 2017-01-20 | 7 |  | 7 | 2017-01-30 | 2017-03-06 | 23 |  | 23 | [20 empty] | 2017-03-13 |  | 2017-03-11 | NO | Expedited | [8 empty] | 2017-05-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 2534 | 1420 | 8.35 |  |  | Solar |  | 20W22 | 2017-01-06 | 2017-01-17 | 7 |  | 7 | 2017-03-24 | 2017-07-10 | 74 |  | 74 | [20 empty] | 2017-07-10 |  | 2017-03-06 | NO | Expedited | [8 empty] | 2017-09-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2533 | 1462 | 4.15 |  |  | Solar |  | 30W31 | 2017-01-06 | 2017-01-17 | 7 |  | 7 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-13 |  | 2017-03-06 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2529 | 1462 | 5.2 |  |  | Solar |  | 30W31 | 2017-01-04 | 2017-01-13 | 8 |  | 8 | 2017-01-30 | 2017-02-21 | 15 |  | 15 | [20 empty] | 2017-02-22 |  | 2017-03-04 | NO | Expedited | [8 empty] | 2017-05-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2527 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2016-12-30 | 2017-01-10 | 8 |  | 8 | 2017-02-02 | 2017-03-06 | 20 |  | 20 | [20 empty] | 2017-03-06 |  | 2017-01-06 | NO | Expedited | [8 empty] | 2017-03-24 | In Operation | Res | Y
Fitchburg | Lunenburg | 2526 | 1462 | 6 |  |  | Solar |  | 30W30 | 2016-12-29 | 2017-01-11 | 10 | 2 | 8 | 2017-01-23 | 2017-02-24 | 23 |  | 23 | [20 empty] | 2017-03-01 |  | 2017-01-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2525 | 1462 | 6.6 |  |  | Solar |  | 30W30 | 2016-12-23 | 2017-01-06 | 11 |  | 11 | 2017-01-31 | 2017-02-21 | 14 |  | 14 | [20 empty] | 2017-02-22 |  | 2017-02-22 | NO | Expedited | [8 empty] | 2017-06-12 | In Operation | Res | Y
Fitchburg | Ashby | 2523 | 1431 | 7.5 |  |  | Solar |  | 39W19 | 2016-12-21 | 2017-01-05 | 12 |  | 12 | 2017-01-18 | 2017-02-07 | 15 |  | 15 | [20 empty] | 2017-02-10 |  | 2016-12-13 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2522 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2016-12-21 | 2017-01-10 | 15 |  | 15 | 2017-01-19 | 2017-02-21 | 22 |  | 22 | [20 empty] | 2017-02-22 |  | 2017-01-30 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2521 | 1462 | 7.36 |  |  | Solar |  | 30W30 | 2016-12-20 | 2017-01-09 | 15 |  | 15 | 2017-01-25 | 2017-02-27 | 22 |  | 22 | [20 empty] | 2017-03-06 |  | 2017-02-01 | NO | Expedited | [8 empty] | 2017-05-11 | In Operation | Res | Y
Fitchburg | Townsend | 2517 | 1469 | 296 |  |  | Solar |  | 15W16 | 2017-10-27 | 2017-11-07 | 7 |  | 7 | 2017-11-07 | 2017-12-06 | 21 |  | 21 | [20 empty] | 2017-12-06 |  | 2017-12-01 | NO | Expedited | [8 empty] | 2018-07-05 | In Operation | Res | Y
Fitchburg | Ashby | 2512 | 1431 | 5 |  |  | Solar |  | 39W19 | 2016-12-15 | 2017-01-04 | 15 |  | 15 | 2017-01-18 | 2017-02-13 | 18 |  | 18 | [20 empty] | 2017-02-14 |  | 2016-12-27 | NO | Expedited | [8 empty] | 2017-04-25 | In Operation | Res | Y
Fitchburg | Ashby | 2509 | 1431 | 4.15 |  |  | Solar |  | 39W19 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-11 | 2017-02-07 | 19 |  | 19 | [20 empty] | 2017-02-10 |  | 2017-02-14 | NO | Expedited | [8 empty] | 2017-05-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2508 | 1420 | 4.15 |  |  | Solar |  | 31W37 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-16 | 2017-02-07 | 16 |  | 16 | [20 empty] | 2017-02-10 |  | 2017-02-14 | NO | Expedited | [8 empty] | 2017-06-16 | In Operation | Res | Y
Fitchburg | Fitchburg | 2507 | 1420 | 6 |  |  | Solar |  | 01W02 | 2016-12-14 | 2017-01-04 | 16 |  | 16 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-02-14 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2505 | 1431 | 4.15 |  |  | Solar |  | 39W19 | 2016-12-13 | 2017-01-04 | 17 |  | 17 | 2017-01-31 | 2017-02-13 | 9 |  | 9 | [20 empty] | 2017-02-14 |  | 2017-02-13 | NO | Expedited | [8 empty] | 2017-06-12 | In Operation | Res | Y
Fitchburg | Townsend | 2502 | 1469 | 8.3 |  |  | Solar |  | 15W16 | 2016-12-07 | 2016-12-30 | 18 |  | 18 | 2017-01-23 | 2017-02-17 | 19 |  | 19 | [20 empty] | 2017-02-17 |  | 2017-02-07 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2501 | 1469 | 5.2 |  |  | Solar |  | 15W16 | 2016-12-06 | 2016-12-27 | 16 |  | 16 | 2017-01-23 | 2017-02-17 | 19 |  | 19 | [20 empty] | 2017-02-17 |  | 2017-02-06 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2496 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2016-12-02 | 2016-12-20 | 13 | 8 | 5 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-09-28 | NO | Expedited | [8 empty] | 2017-08-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2494 | 1462 | 4.15 |  |  | Solar |  | 30W30 | 2016-12-01 | 2016-12-20 | 14 |  | 14 | 2017-01-09 | 2017-01-30 | 15 |  | 15 | [20 empty] | 2017-01-31 |  | 2016-12-23 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Townsend | 2492 | 1469 | 8.35 |  |  | Solar |  | 15W16 | 2016-12-01 | 2016-12-20 | 14 |  | 14 | 2017-01-09 | 2017-02-03 | 19 |  | 19 | [20 empty] | 2017-02-09 |  | 2017-01-30 | NO | Expedited | [8 empty] | 2017-04-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2488 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2016-11-30 | 2016-12-13 | 10 |  | 10 | 2017-01-12 | 2017-02-03 | 16 |  | 16 | [20 empty] | 2017-02-06 |  | 2017-01-29 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Res | Y
Fitchburg | Ashby | 2486 | 1431 | 7.25 |  |  | Solar |  | 35W36 | 2016-11-28 | 2016-12-12 | 11 |  | 11 | 2016-12-20 | 2016-12-27 | 6 |  | 6 | [20 empty] | 2016-12-27 |  | 2017-01-27 | NO | Expedited | [8 empty] | 2017-01-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2484 | 1420 | 4.95 |  |  | Solar |  | 40W40 | 2016-11-28 | 2016-12-12 | 11 |  | 11 | 2017-01-03 | 2017-02-02 | 22 |  | 22 | [20 empty] | 2017-02-07 |  | 2016-11-08 | YES | Expedited | [8 empty] | 2017-03-20 | In Operation | Res | Y
Fitchburg | Lunenburg | 2482 | 1462 | 3.8 |  |  | Solar |  | 30W31 | 2016-11-22 | 2016-12-08 | 12 | 3 | 9 | 2016-12-16 | 2017-01-06 | 16 |  | 16 | [20 empty] | 2017-01-09 |  | 2017-01-22 | NO | Expedited | [8 empty] | 2017-11-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2480 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2016-11-22 | 2016-12-08 | 12 |  | 12 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2017-01-22 | NO | Expedited | [8 empty] | 2017-07-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2479 | 1462 | 5.4 |  |  | Solar |  | 30W31 | 2016-11-22 | 2016-12-09 | 13 | 3 | 10 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-03-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2477 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2016-11-21 | 2016-12-06 | 11 | 2 | 9 | 2017-02-13 | 2017-03-06 | 14 |  | 14 | [20 empty] | 2017-03-14 |  | 2017-07-23 | YES | Expedited | [8 empty] | 2017-07-10 | In Operation | Res | Y
Fitchburg | Townsend | 2476 | 1469 | 4.15 |  |  | Solar |  | 30W31 | 2016-11-21 | 2016-12-06 | 11 |  | 11 | 2017-01-20 | 2017-01-20 | 1 |  | 1 | [20 empty] | 2017-01-24 |  | 2017-01-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2475 | 1431 | 10 |  |  | Solar |  | 39W19 | 2016-11-21 | 2016-12-07 | 12 |  | 12 | 2016-12-21 | 2017-01-17 | 19 |  | 19 | [20 empty] | 2017-01-23 |  |  |  | Expedited | [9 empty] | Cancelled |  | Y
Fitchburg | Townsend | 2474 | 1469 | 8.3 |  |  | Solar |  | 15W16 | 2016-11-21 | 2016-12-06 | 11 |  | 11 | 2016-12-16 | 2017-01-09 | 17 |  | 17 | [20 empty] | 2017-01-11 |  | 2017-01-18 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2473 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2016-11-18 | 2016-11-22 | 3 |  | 3 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2017-01-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2472 | 1469 | 3.8 |  |  | Solar |  | 15W17 | 2016-11-18 | 2016-11-22 | 3 |  | 3 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-18 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2468 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2016-11-16 | 2016-11-22 | 5 |  | 5 | 2016-12-20 | 2017-01-20 | 23 |  | 23 | [20 empty] | 2017-01-23 |  | 2017-01-16 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2467 | 1462 | 5.45 |  |  | Solar |  | 30W31 | 2016-11-16 | 2016-11-22 | 5 |  | 5 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-27 |  | 2017-01-15 | YES | Expedited | [8 empty] | 2017-06-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 2466 | 1462 | 4.8 |  |  | Solar |  | 30W30 | 2016-11-16 | 2016-12-06 | 14 | 5 | 9 | 2017-01-03 | 2017-01-30 | 19 |  | 19 | [20 empty] | 2017-01-31 |  | 2016-12-23 | NO | Expedited | [8 empty] | 2017-03-02 | In Operation | Res | Y
Fitchburg | Lunenburg | 2464 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2016-11-15 | 2016-11-22 | 6 |  | 6 | 2017-01-11 | 2017-02-03 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2017-01-15 | NO | Expedited | [8 empty] | 2017-10-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2463 | 1420 | 8.35 |  |  | Solar |  | 40W40 | 2016-11-15 | 2016-11-17 | 3 |  | 3 | 2017-01-11 | 2017-02-02 | 16 | 2 | 14 | [20 empty] | 2017-02-07 |  | 2017-01-14 | NO | Expedited | [8 empty] | 2017-06-08 | In Operation | Res | Y
Fitchburg | Ashby | 2462 | 1431 | 10 |  |  | Solar |  | 39W19 | 2016-11-15 | 2016-11-29 | 10 |  | 10 | 2017-01-27 | 2017-02-14 | 12 |  | 12 | [20 empty] | 2017-02-14 |  | 2017-01-15 | NO | Expedited | [8 empty] | 2018-05-10 | In Operation | Res | Y
Fitchburg | Ashby | 2459 | 1431 | 10 |  |  | Solar |  | 39W19 | 2016-11-14 | 2016-12-02 | 14 | 4 | 10 | 2016-12-16 | 2016-12-29 | 10 |  | 10 | [20 empty] | 2016-12-29 |  |  | NO | Expedited | [8 empty] | 2017-06-05 | In Operation | Res | Y
Fitchburg | Ashby | 2458 | 1431 | 2.75 |  |  | Solar |  | 39W19 | 2016-11-10 | 2016-12-05 | 16 | 10 | 6 | 2016-12-16 | 2016-12-28 | 9 |  | 9 | [20 empty] | 2016-12-28 |  |  | NO | Expedited | [8 empty] | 2017-01-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2455 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2016-11-10 | 2016-11-18 | 6 |  | 6 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-24 |  | 2017-01-09 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2454 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2016-11-08 | 2016-11-18 | 8 |  | 8 | 2017-01-03 | 2017-01-30 | 19 |  | 19 | [20 empty] | 2017-01-31 |  | 2017-01-08 | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2453 | 1420 | 5.4 |  |  | Solar |  | 01W02 | 2016-11-08 | 2016-11-18 | 8 |  | 8 | 2016-12-05 | 2016-12-21 | 13 |  | 13 | [20 empty] | 2016-12-27 |  | 2017-01-08 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2452 | 1420 | 4.15 |  |  | Solar |  | 11H10 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2017-01-11 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2451 | 1462 | 7.6 |  |  | Solar |  | 30W30 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-22 | 2017-01-20 | 21 |  | 21 | [20 empty] | 2017-01-23 |  | 2017-01-07 | NO | Expedited | [8 empty] | 2017-03-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2450 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2016-11-07 | 2016-11-18 | 9 |  | 9 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2016-12-27 |  | 2017-01-07 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2449 | 1420 | 8.35 |  |  | Solar |  | 25W27 | 2016-11-03 | 2016-11-10 | 6 |  | 6 | 2016-12-15 | 2016-12-15 | 1 |  | 1 | [20 empty] | 2016-12-15 |  | 2017-01-02 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2447 | 1462 | 12 |  |  | Solar |  | 30W31 | 2016-11-04 | 2016-11-17 | 9 |  | 9 | 2017-01-16 | 2017-01-20 | 4 |  | 4 | [20 empty] | 2017-02-10 |  | 2017-01-04 | NO | Expedited | [8 empty] | 2017-04-14 | In Operation | Res | Y
Fitchburg | Lunenburg | 2446 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2016-11-04 | 2016-11-17 | 9 |  | 9 | 2017-01-16 | 2017-01-17 | 1 |  | 1 | [20 empty] | 2017-02-10 |  | 2017-01-03 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2445 | 1420 | 7.6 |  |  | Solar |  | 01W02 | 2016-11-03 | 2016-11-17 | 10 |  | 10 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-24 |  | 2017-01-03 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2444 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2017-03-20 | 2017-03-20 | 1 |  | 1 | 2017-04-06 | 2017-05-05 | 21 |  | 21 | [20 empty] | 2017-05-05 |  | 2017-01-02 | NO | Expedited | [8 empty] | 2017-05-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2442 | 1420 | 7.6 |  |  | Solar |  | 35W36 | 2016-11-01 | 2016-11-17 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-31 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2441 | 1462 | 5.45 |  |  | Solar |  | 30W31 | 2016-10-31 | 2016-11-14 | 10 |  | 10 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-31 | NO | Expedited | [8 empty] | 2017-05-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2440 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2016-10-28 | 2016-11-14 | 11 |  | 11 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-28 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2439 | 1420 | 10.95 |  |  | Solar |  | 25W27 | 2016-10-27 | 2016-11-22 | 18 | 5 | 13 | 2016-12-08 | 2016-12-21 | 10 |  | 10 | [20 empty] | 2016-12-27 |  | 2016-12-27 | NO | Expedited | [8 empty] | 2017-02-09 | In Operation | Res | Y
Fitchburg | Lunenburg | 2438 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2016-10-27 | 2016-11-16 | 14 | 4 | 10 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2436 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2016-10-27 | 2016-11-14 | 12 |  | 12 | 2016-12-09 | 2016-12-21 | 9 |  | 9 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Townsend | 2435 | 1469 | 12.55 |  |  | Solar |  | 39W18 | 2016-10-27 | 2016-11-15 | 13 |  | 13 | 2017-01-26 | 2017-01-28 | 2 |  | 2 | [20 empty] | 2017-01-28 |  | 2016-12-26 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2434 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2016-10-26 | 2016-11-14 | 13 |  | 13 | 2016-12-20 | 2016-12-22 | 3 |  | 3 | [20 empty] | 2016-12-27 |  | 2016-12-26 | NO | Expedited | [8 empty] | 2017-02-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2433 | 1420 | 6 |  |  | Solar |  | 11W11 | 2016-10-26 | 2016-11-10 | 12 |  | 12 | 2016-12-15 | 2016-12-17 | 2 |  | 2 | [20 empty] | 2016-12-17 |  |  | YES | Expedited | [8 empty] | 2017-03-07 | In Operation | Res | Y
Fitchburg | Townsend | 2432 | 1474 | 4.15 |  |  | Solar |  | 39W18 | 2016-10-26 | 2016-11-10 | 12 |  | 12 | 2016-11-28 | 2016-12-22 | 19 |  | 19 | [20 empty] | 2016-12-27 |  | 2016-12-25 | NO | Expedited | [8 empty] | 2017-03-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2431 | 1462 | 10.95 |  |  | Solar |  | 31W38 | 2016-10-25 | 2016-11-10 | 13 |  | 13 | 2016-12-20 | 2017-01-12 | 18 |  | 18 | [20 empty] | 2017-01-16 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 2429 | 1469 | 10 |  |  | Solar |  | 15W16 | 2016-10-25 | 2016-11-10 | 13 |  | 13 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-12-29 | In Operation | Res | Y
Fitchburg | Townsend | 2428 | 1469 | 5.45 |  |  | Solar |  | 39W18 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2427 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2016-12-27 | 2017-01-20 | 18 |  | 18 | [20 empty] | 2017-01-25 |  | 2016-12-24 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2426 | 1420 | 7.6 |  |  | Solar |  | 31W37 | 2016-10-25 | 2016-11-09 | 12 |  | 12 | 2017-01-12 | 2017-02-06 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2016-12-24 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2425 | 1462 | 8.25 |  |  | Solar |  | 30W31 | 2016-10-24 | 2016-11-15 | 16 | 6 | 10 | 2016-12-14 | 2016-12-22 | 7 |  | 7 | [20 empty] | 2016-12-27 |  | 2016-01-11 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2424 | 1420 | 3.5 |  |  | Solar |  | 20H22 | 2016-10-24 | 2016-11-09 | 13 |  | 13 | 2016-12-05 | 2016-12-20 | 12 |  | 12 | [20 empty] | 2016-12-27 |  | 2016-12-31 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2420 | 1462 | 9 |  |  | Solar |  | 30W30 | 2016-10-21 | 2016-11-09 | 14 |  | 14 | 2016-12-22 | 2017-01-23 | 22 |  | 22 | [20 empty] | 2017-01-23 |  | 2016-12-20 | NO | Expedited | [8 empty] | 2017-03-03 | In Operation | Res | Y
Fitchburg | Lunenburg | 2418 | 1462 | 10.95 |  |  | Solar |  | 30W30 | 2016-10-21 | 2016-11-07 | 12 |  | 12 | 2016-12-22 | 2017-01-24 | 23 |  | 23 | [20 empty] | 2017-01-24 |  | 2016-12-20 | NO | Expedited | [8 empty] | 2017-03-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2416 | 1420 | 4.75 |  |  | Solar |  | 11H10 | 2016-10-20 | 2016-11-03 | 11 |  | 11 | 2016-12-05 | 2016-12-22 | 14 |  | 14 | [20 empty] | 2017-01-11 |  | 2016-12-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2414 | 1462 | 8.35 |  |  | Solar |  | 30W31 | 2016-10-19 | 2016-11-02 | 11 |  | 11 | 2016-12-16 | 2016-12-29 | 10 |  | 10 | [20 empty] | 2016-12-29 |  | 2016-12-15 | NO | Expedited | [8 empty] | 2017-03-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2413 | 1420 | 4.73 |  |  | Solar |  | 01W04 | 2016-10-17 | 2016-10-28 | 10 |  | 10 | 2016-11-29 | 2016-12-21 | 17 |  | 17 | [20 empty] | 2016-12-22 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-04-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 2412 | 1420 | 7.88 |  |  | Solar |  | 35W36 | 2016-10-17 | 2016-11-15 | 21 |  | 21 | 2016-11-22 | 2016-12-22 | 22 |  | 22 | [20 empty] | 2016-12-22 |  | 2016-12-17 | NO | Expedited | [8 empty] | 2017-03-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2409 | 1420 | 5.45 |  |  | Solar |  | 35W36 | 2016-10-13 | 2016-10-27 | 11 | 6 | 5 | 2016-12-09 | 2016-12-22 | 10 |  | 10 | [20 empty] | 2017-01-09 |  |  | NO | Expedited | [8 empty] | 2017-06-07 | In Operation | Res | Y
Fitchburg | Lunenburg | 2408 | 1462 | 8 |  |  | Solar |  | 31W37 | 2016-10-12 | 2016-10-27 | 12 |  | 12 | 2016-11-17 | 2016-11-29 | 8 |  | 8 | [20 empty] | 2016-11-30 |  | 2016-11-01 | NO | Expedited | [8 empty] | 2017-01-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 2407 | 1420 | 6.6 |  |  | Solar |  | 25W27 | 2016-10-11 | 2016-10-26 | 12 | 10 | 2 | 2017-02-03 | 2017-02-07 | 3 |  | 3 | [20 empty] | 2017-02-09 |  | 2016-12-11 | NO | Expedited | [8 empty] | 2017-03-28 | In Operation | Res | Y
Fitchburg | Ashby | 2405 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2016-10-10 | 2016-10-26 | 12 |  | 12 | 2016-11-28 | 2016-12-28 | 23 |  | 23 | [20 empty] | 2016-12-28 |  | 2016-12-10 | NO | Expedited | [8 empty] | 2017-03-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2404 | 1420 | 5.45 |  |  | Solar |  | 31W37 | 2016-10-07 | 2016-10-25 | 12 |  | 12 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-11-01 | NO | Expedited | [8 empty] | 2017-01-26 | In Operation | Res | Y
Fitchburg | Lunenburg | 2402 | 1462 | 9 |  |  | Solar |  | 30W31 | 2016-10-07 | 2016-10-25 | 12 |  | 12 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-12-06 | NO | Expedited | [8 empty] | 2017-03-23 | In Operation | Res | Y
Fitchburg | Townsend | 2401 | 1469 | 5.45 |  |  | Solar |  | 39W18 | 2016-10-06 | 2016-10-25 | 13 |  | 13 | 2016-11-14 | 2016-11-29 | 11 |  | 11 | [20 empty] | 2016-11-30 |  | 2016-11-30 | NO | Expedited | [8 empty] | 2017-03-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 2397 | 1420 | 5.2 |  |  | Solar |  | 31W37 | 2016-10-05 | 2016-10-25 | 14 | 7 | 7 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-12-04 | NO | Expedited | [8 empty] | 2017-01-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2396 | 1462 | 5.45 |  |  | Solar |  | 30W31 | 2016-10-04 | 2016-10-25 | 15 | 6 | 9 | 2017-01-12 | 2017-02-06 | 17 |  | 17 | [20 empty] | 2017-02-06 |  | 2016-12-04 | NO | Expedited | [8 empty] | 2017-05-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2395 | 1420 | 6.24 |  |  | Solar |  | 25W27 | 2016-10-04 | 2016-10-26 | 16 | 4 | 12 | 2016-12-12 | 2016-12-22 | 9 |  | 9 | [20 empty] | 2016-10-27 |  | 2016-06-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2394 | 1462 | 9 |  |  | Solar |  | 30W31 | 2016-10-04 | 2016-10-24 | 14 | 3 | 11 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-06 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-03-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2393 | 1462 | 5.2 |  |  | Solar |  | 30W30 | 2016-10-04 | 2016-10-24 | 14 | 6 | 8 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-02 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2391 | 1420 | 4.15 |  |  | Solar |  | 20W22 | 2016-10-04 | 2016-10-20 | 12 |  | 12 | 2016-11-04 | 2016-11-29 | 16 |  | 16 | [20 empty] | 2016-11-30 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-04-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2388 | 1462 | 10 |  |  | Solar |  | 30W31 | 2016-10-03 | 2016-10-20 | 13 |  | 13 | 2016-11-03 | 2016-11-03 | 1 |  | 1 | [20 empty] | 2016-11-07 |  | 2016-12-03 | NO | Expedited | [8 empty] | 2017-02-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2387 | 1462 | 3.8 |  |  | Solar |  | 31W38 | 2016-09-29 | 2016-10-20 | 15 |  | 15 | 2016-11-17 | 2016-12-01 | 10 |  | 10 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-02-08 | In Operation | Res | Y
Fitchburg | Fitchburg | 2386 | 1420 | 3.8 |  |  | Solar |  | 40W40 | 2016-09-29 | 2016-10-20 | 15 |  | 15 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-01-06 | In Operation | Res | Y
Fitchburg | Fitchburg | 2385 | 1420 | 4000 | 4000 | 0 | Solar + Energy Storage | Yes | 35W36 | 2017-02-16 | 2017-03-03 | 10 |  | 10 | [10 empty] | 2017-03-04 | 2017-04-01 | 19 | 11 | 8 | 2017-05-22 | 2017-09-08 | 77 | 35 | 42 | 2018-02-20 | 2018-03-13 | 12 |  | 12 | 2018-05-07 | 2018-11-28 | 2017-12-01 | YES | Standard | [6 empty] | 2020-03-17 | 2020-03-17 | 2020-03-18 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2381 | 1420 | 5.45 |  |  | Solar |  | 31W37 | 2016-09-29 | 2016-10-19 | 14 | 3 | 11 | 2016-11-17 | 2016-11-30 | 9 |  | 9 | [20 empty] | 2016-12-02 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2017-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2380 | 1420 | 8.96 |  |  | Solar |  | 31W37 | 2016-09-29 | 2016-10-19 | 14 | 3 | 11 | 2016-11-14 | 2016-11-29 | 11 |  | 11 | [20 empty] | 2016-11-30 |  | 2016-11-29 | NO | Expedited | [8 empty] | 2016-12-21 | In Operation | Res | Y
Fitchburg | Ashby | 2379 | 1431 | 5.45 |  |  | Solar |  | 39W19 | 2016-09-28 | 2016-10-18 | 14 |  | 14 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-04 |  | 2016-10-15 | NO | Expedited | [8 empty] | 2016-12-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2378 | 1469 | 7.68 |  |  | Solar |  | 30W30 | 2016-09-29 | 2016-10-11 | 8 | 6 | 2 | 2016-10-28 | 2016-11-01 | 3 |  | 3 | [20 empty] | 2016-11-01 |  | 2016-09-01 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2377 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2016-09-30 | 2016-10-18 | 12 | 4 | 8 | 2016-10-31 | 2016-11-08 | 7 |  | 7 | [20 empty] | 2016-11-09 |  | 2016-11-28 | NO | Expedited | [8 empty] | 2017-12-06 | In Operation | Res | Y
Fitchburg | Lunenburg | 2375 | 1462 | 8.35 |  |  | Solar |  | 30W30 | 2016-09-27 | 2016-10-17 | 14 | 4 | 10 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-07 |  | 2016-11-27 | NO | Expedited | [6 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 2369 | 1420 | 9.45 |  |  | Solar |  | 35W36 | 2016-09-22 | 2016-11-16 | 38 | 24 | 14 | 2016-12-05 | 2016-12-21 | 13 | 6 | 7 | [20 empty] | 2016-12-27 |  |  | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2368 | 1420 | 10.95 |  |  | Solar |  | 20H22 | 2016-09-22 | 2016-10-12 | 14 |  | 14 | [27 empty] | 2016-09-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2367 | 1431 | 15 |  |  | Solar |  | 39W19 | 2016-09-22 | 2016-10-06 | 11 | 2 | 9 | 2016-10-24 | 2016-11-03 | 9 |  | 9 | [20 empty] | 2016-11-04 |  |  | NO | Expedited | [8 empty] | 2016-11-10 | In Operation | Res | Y
Fitchburg | Lunenburg | 2364 | 1462 | 9 |  |  | Solar |  | 30W31 | 2016-09-21 | 2016-10-10 | 13 |  | 13 | [27 empty] | 2016-11-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2362 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2016-09-20 | 2016-10-10 | 14 |  | 14 | 2016-10-31 | 2016-11-03 | 4 |  | 4 | [20 empty] | 2016-11-04 |  | 2016-09-27 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2361 | 1469 | 6.6 |  |  | Solar |  | 15W17 | 2016-09-19 | 2016-10-10 | 15 |  | 15 | 2016-11-18 | 2016-12-21 | 23 |  | 23 | [20 empty] | 2016-12-22 |  | 2016-11-19 | NO | Expedited | [8 empty] | 2017-02-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2359 | 1462 | 10.95 |  |  | Solar |  | 30W31 | 2016-09-19 | 2016-10-11 | 16 |  | 16 | 2016-11-22 | 2016-12-21 | 21 |  | 21 | [20 empty] | 2016-12-22 |  | 2016-11-17 | NO | Expedited | [8 empty] | 2017-09-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2357 | 1462 | 10.95 |  |  | Solar |  | 31W37 | 2016-09-19 | 2016-10-06 | 14 | 1 | 13 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-12-21 | NO | Expedited | [8 empty] | 2017-02-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2355 | 1420 | 3.8 |  |  | Solar |  | 01W02 | 2016-09-16 | 2016-10-05 | 14 |  | 14 | 2016-12-19 | 2016-12-22 | 4 |  | 4 | [20 empty] | 2016-12-27 |  | 2017-06-08 | NO | Expedited | [8 empty] | 2017-02-17 | In Operation | Res | Y
Fitchburg | Lunenburg | 2353 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-11-03 | 2016-11-08 | 4 |  | 4 | [20 empty] | 2016-11-09 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-28 | In Operation | Res | Y
Fitchburg | Ashby | 2352 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-10-18 | 2016-10-25 | 6 |  | 6 | [20 empty] | 2016-10-25 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2351 | 1420 | 8.35 |  |  | Solar |  | 25W27 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | 2016-10-18 | 2016-10-20 | 3 |  | 3 | [20 empty] | 2016-10-25 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2017-03-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2350 | 1462 | 5.8 |  |  | Solar |  | 30W30 | 2016-09-15 | 2016-10-03 | 13 |  | 13 | 2016-10-28 | 2016-10-28 | 1 |  | 1 | [20 empty] | 2016-11-01 |  | 2016-11-15 | NO | Expedited | [8 empty] | 2016-12-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 2348 | 1462 | 6.6 |  |  | Solar |  | 30W30 | 2016-09-13 | 2016-09-29 | 13 |  | 13 | 2016-11-08 | 2016-12-28 | 35 |  | 35 | [20 empty] | 2016-12-28 |  | 2016-11-13 | NO | Expedited | [8 empty] | 2017-03-27 | In Operation | Res | Y
Fitchburg | Lunenburg | 2346 | 1462 | 7.6 |  |  | Solar |  | 31W38 | 2016-09-12 | 2016-09-29 | 14 |  | 14 | [27 empty] | 2016-11-12 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2340 | 1431 | 12.75 |  |  | Solar |  | 39W19 | 2016-09-07 | 2016-09-21 | 11 |  | 11 | 2016-10-18 | 2016-10-19 | 2 |  | 2 | [20 empty] | 2016-10-21 |  |  | YES | Expedited | 2016-11-29 | 2016-11-16 | 2016-11-16 | 1 |  | 1 | 2017-04-07 | 2017-04-07 | 2017-04-11 | In Operation |  | Y
Fitchburg | Ashby | 2338 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2016-09-06 | 2016-09-21 | 12 | 2 | 10 | 2016-10-12 | 2016-10-12 | 1 |  | 1 | [20 empty] | 2016-10-20 |  | 2016-10-01 | NO | Expedited | [8 empty] | 2016-11-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 2337 | 1420 | 6.6 |  |  | Solar |  | 20W22 | 2016-09-06 | 2016-09-15 | 8 | 4 | 4 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-11-09 | NO | Expedited | [8 empty] | 2017-02-10 | In Operation | Res | Y
Fitchburg | Ashby | 2330 | 1431 | 6 |  |  | Solar |  | 39W19 | 2016-09-01 | 2016-09-16 | 11 | 1 | 10 | 2016-10-17 | 2016-10-19 | 3 |  | 3 | [20 empty] | 2016-10-20 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-11-17 | Cancelled | Res | Y
Fitchburg | Lunenburg | 2321 | 1462 | 9 |  |  | Solar |  | 30W31 | 2016-08-29 | 2016-09-13 | 11 |  | 11 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-10-29 | NO | Expedited | [8 empty] | 2017-02-13 | In Operation | Res | Y
Fitchburg | Lunenburg | 2320 | 1462 | 12 |  |  | Solar |  | 30W31 | 2016-08-29 | 2016-09-13 | 11 |  | 11 | 2016-10-05 | 2016-10-12 | 5 |  | 5 | [20 empty] | 2016-10-18 |  | 2016-11-01 | YES | Expedited | [8 empty] | 2016-12-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 2319 | 1469 | 4.15 |  |  | Solar |  | 30W31 | 2016-08-26 | 2016-09-13 | 12 |  | 12 | 2016-11-22 | 2016-12-01 | 7 |  | 7 | [20 empty] | 2016-12-06 |  | 2016-10-26 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2317 | 1462 | 5 |  |  | Solar |  | 30W31 | 2016-08-26 | 2016-09-12 | 11 |  | 11 | [25 empty] | 2016-09-22 |  | 2016-10-26 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2316 | 1469 | 6 |  |  | Solar |  | 39W18 | 2016-08-25 | 2016-09-12 | 12 | 4 | 8 | 2016-09-26 | 2016-09-30 | 5 |  | 5 | [20 empty] | 2016-10-07 |  | 2016-10-17 | NO | Expedited | [8 empty] | 2016-11-01 | In Operation | Res | Y
Fitchburg | Townsend | 2315 | 1469 | 5.25 |  |  | Solar |  | 15W16 | 2016-08-25 | 2016-09-07 | 9 |  | 9 | 2016-09-19 | 2016-10-07 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-09-28 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2313 | 1420 | 6.6 |  |  | Solar |  | 01W04 | 2016-08-24 | 2016-09-02 | 8 |  | 8 | 2016-11-28 | 2016-12-21 | 18 |  | 18 | [20 empty] | 2016-12-22 |  | 2016-10-23 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2301 | 1462 | 5.2 |  |  | Solar |  | 31W37 | 2016-08-18 | 2016-08-31 | 10 |  | 10 | 2016-09-19 | 2016-10-07 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-10-17 | NO | Expedited | [8 empty] | 2016-11-16 | In Operation | Res | Y
Fitchburg | Townsend | 2292 | 1469 | 4.95 |  |  | Solar |  | 15W16 | 2016-08-12 | 2016-08-29 | 12 |  | 12 | 2016-09-09 | 2016-09-29 | 15 |  | 15 | [20 empty] | 2016-10-07 |  | 2016-10-12 | NO | Expedited | [8 empty] | 2016-12-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 2289 | 1420 | 7.6 |  |  | Solar |  | 25W27 | 2016-08-11 | 2016-08-25 | 11 |  | 11 | 2016-09-16 | 2016-09-30 | 11 |  | 11 | [20 empty] | 2016-10-07 |  | 2016-05-19 | NO | Expedited | [8 empty] | 2016-11-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 2284 | 1462 | 8 |  |  | Solar |  | 30W30 | 2016-08-09 | 2016-08-23 | 11 | 2 | 9 | 2016-09-27 | 2016-10-07 | 9 |  | 9 | [20 empty] | 2016-10-07 |  |  | NO | Expedited | [8 empty] | 2017-05-26 | In Operation | Res | Y
Fitchburg | Fitchburg | 2283 | 1420 | 6.67 |  |  | Solar |  | 31W37 | 2016-08-08 | 2016-08-24 | 13 | 1 | 12 | 2016-09-23 | 2016-10-07 | 11 |  | 11 | [20 empty] | 2016-10-07 |  | 2016-08-17 | NO | Expedited | [8 empty] | 2016-11-19 | In Operation | Res | Y
Fitchburg | Fitchburg | 2282 | 1420 | 4 |  |  | Solar |  | 01W02 | 2016-08-09 | 2016-08-23 | 11 |  | 11 | 2016-09-06 | 2016-09-28 | 17 |  | 17 | [20 empty] | 2016-10-05 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-10-26 | In Operation | Res | Y
Fitchburg | Ashby | 2281 | 1431 | 8.35 |  |  | Solar |  | 39W19 | 2016-08-05 | 2016-08-23 | 13 | 1 | 12 | 2016-09-15 | 2016-09-30 | 12 |  | 12 | [20 empty] | 2016-10-07 |  |  | NO | Expedited | [8 empty] | 2016-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2280 | 1420 | 7.6 |  |  | Solar |  | 40W40 | 2016-08-05 | 2016-08-22 | 12 |  | 12 | 2016-09-12 | 2016-10-11 | 21 |  | 21 | [20 empty] | 2016-10-18 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-12-14 | In Operation | Res | Y
Fitchburg | Fitchburg | 2278 | 1420 | 4.25 |  |  | Solar |  | 20W22 | 2016-08-03 | 2016-08-22 | 14 |  | 14 | 2016-09-13 | 2016-10-05 | 17 |  | 17 | [20 empty] | 2016-10-12 |  | 2016-09-08 | YES | Expedited |  | 2016-12-15 | 2016-12-15 | 1 |  | 1 |  |  | 2016-12-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2274 | 1462 | 8.35 |  |  | Solar |  | 31W38 | 2016-08-02 | 2016-08-16 | 11 |  | 11 | 2016-09-12 | 2016-09-30 | 15 |  | 15 | [20 empty] | 2016-09-30 |  | 2016-10-05 | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2273 | 1420 | 4.15 |  |  | Solar |  | 20H22 | 2016-08-01 | 2016-08-11 | 9 |  | 9 | 2016-08-19 | 2016-09-26 | 26 |  | 26 | [20 empty] | 2016-09-26 |  | 2016-10-01 | YES | Expedited |  | 2016-12-15 | 2016-12-15 | 1 |  | 1 |  |  |  | Cancelled | Res | Y
Fitchburg | Lunenburg | 2268 | 1462 | 32 |  |  | Solar |  | 30W31 | 2016-07-29 | 2016-08-16 | 13 |  | 13 | 2016-08-17 | 2016-09-20 | 24 | 15 | 9 | [20 empty] | 2016-09-29 |  | 2016-10-01 | YES | Expedited | [6 empty] | 2017-02-21 | 2017-02-21 | 2017-02-21 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2267 | 1462 | 262 |  |  | Solar |  | 30W31 | 2016-08-15 | 2016-08-17 | 3 |  | 3 | 2016-08-18 | 2016-09-21 | 24 | 20 | 4 | [20 empty] | 2016-10-13 |  | 2016-10-01 | YES | Expedited | [8 empty] | 2017-06-01 | In Operation | Comm | Y
Fitchburg | Lunenburg | 2263 | 1462 | 8 |  |  | Solar |  | 30W31 | 2016-07-25 | 2016-08-04 | 9 |  | 9 | 2016-09-20 | 2016-09-20 | 1 |  | 1 | [20 empty] | 2016-09-22 |  | 2016-10-01 | NO | Expedited | [8 empty] | 2017-09-19 | In Operation | Res | Y
Fitchburg | Lunenburg | 2260 | 1462 | 10.95 |  |  | Solar |  | 31W37 | 2016-07-22 | 2016-08-04 | 10 |  | 10 | 2016-09-14 | 2016-09-29 | 12 |  | 12 | [20 empty] | 2016-10-07 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 2259 | 1420 | 2.7 |  |  | Solar |  | 31W34 | 2016-07-21 | 2016-08-04 | 11 |  | 11 | 2016-08-26 | 2016-09-15 | 14 |  | 14 | [20 empty] | 2016-08-26 |  | 2016-09-22 | NO | Expedited | [8 empty] | 2016-08-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 2256 | 1420 | 5.4 |  |  | Solar |  | 01W02 | 2016-07-19 | 2016-08-02 | 11 |  | 11 | 2016-08-22 | 2016-09-15 | 18 |  | 18 | [20 empty] | 2016-09-21 |  | 2016-09-19 | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2255 | 1420 | 4.15 |  |  | Solar |  | 20H22 | 2016-07-19 | 2016-08-01 | 10 |  | 10 | 2016-08-19 | 2016-09-13 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-09-19 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Ashby | 2253 | 1431 | 5.45 |  |  | Solar |  | 39W19 | 2016-07-19 | 2016-08-03 | 12 | 2 | 10 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  |  | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2251 | 1420 | 8.35 |  |  | Solar |  | 11H10 | 2016-07-19 | 2016-07-29 | 9 |  | 9 | [27 empty] | 2016-09-18 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2244 | 1420 | 17.2 |  |  | Solar |  | 20H22 | 2016-08-24 | 2016-08-31 | 6 |  | 6 | [25 empty] | 2016-09-27 |  |  | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 2240 | 1469 | 10.95 |  |  | Solar |  | 15W16 | 2016-07-11 | 2016-07-25 | 11 |  | 11 | 2016-08-15 | 2016-09-15 | 23 |  | 23 | [20 empty] | 2016-09-08 |  | 2016-09-11 | NO | Expedited | [8 empty] | 2016-11-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2239 | 1420 | 4.15 |  |  | Solar |  | 31W34 | 2016-07-11 | 2016-07-25 | 11 | 5 | 6 | 2016-08-05 | 2016-08-05 | 1 |  | 1 | [20 empty] | 2016-08-26 |  | 2016-09-11 | NO | Expedited | [8 empty] | 2017-02-10 | In Operation | Res | Y
Fitchburg | Fitchburg | 2237 | 1420 | 9 |  |  | Solar |  | 01W02 | 2016-07-11 | 2016-07-25 | 11 |  | 11 | 2016-09-30 | 2016-09-30 | 1 |  | 1 | [20 empty] | 2016-10-07 |  | 2016-08-31 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 2230 | 1420 | 7.25 |  |  | Solar |  | 25W27 | 2016-07-06 | 2016-07-19 | 10 |  | 10 | 2016-08-09 | 2016-08-25 | 13 |  | 13 | [20 empty] | 2016-09-01 |  | 2016-08-08 | NO | Expedited | [7 empty] | 2016-10-26 | 2016-10-28 | Cancelled | Res | Y
Fitchburg | Fitchburg | 2229 | 1420 | 8.88 |  |  | Solar |  | 35W36 | 2016-07-05 | 2016-07-15 | 9 |  | 9 | 2016-08-08 | 2016-08-22 | 11 |  | 11 | [20 empty] | 2016-08-26 |  | 2016-09-05 | NO | Expedited | [8 empty] | 2016-11-04 | In Operation | Res | Y
Fitchburg | Lunenburg | 2228 | 1462 | 4.15 |  |  | Solar |  | 30W30 | 2016-07-05 | 2016-07-15 | 9 |  | 9 | 2016-08-08 | 2016-08-19 | 10 |  | 10 | [20 empty] | 2016-08-22 |  |  | NO | Expedited | [8 empty] | 2016-11-03 | In Operation | Res | Y
Fitchburg | Fitchburg | 2225 | 1420 | 4.15 |  |  | Solar |  | 31W37 | 2016-07-01 | 2016-07-15 | 10 |  | 10 | 2016-08-08 | 2016-08-23 | 12 |  | 12 | [20 empty] | 2016-08-26 |  | 2016-09-01 | NO | Expedited | [8 empty] | 2016-11-15 | In Operation | Res | Y
Fitchburg | Lunenburg | 2219 | 1462 | 6.76 |  |  | Solar |  | 31W38 | 2016-06-30 | 2016-07-13 | 9 | 2 | 7 | 2016-07-19 | 2016-08-19 | 24 |  | 24 | [20 empty] | 2016-08-18 |  |  | NO | Expedited | [8 empty] | 2016-09-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2215 | 1420 | 4.15 |  |  | Solar |  | 35W36 | 2016-06-28 | 2016-07-12 | 10 |  | 10 | 2016-07-22 | 2016-08-05 | 11 |  | 11 | [20 empty] | 2016-08-05 |  | 2016-08-27 | NO | Expedited | [8 empty] | 2016-10-13 | In Operation | Res | Y
Fitchburg | Fitchburg | 2210 | 1420 | 7.25 |  |  | Solar |  | 31W37 | 2016-06-27 | 2016-07-11 | 10 |  | 10 | 2016-07-26 | 2016-08-19 | 19 |  | 19 | [20 empty] | 2016-08-22 |  | 2016-07-30 | NO | Expedited | [8 empty] | 2016-09-09 | In Operation | Res | Y
Fitchburg | Townsend | 2205 | 1469 | 5.75 |  |  | Solar |  | 15W17 | 2016-06-23 | 2016-07-07 | 10 |  | 10 | 2016-07-22 | 2016-08-25 | 25 |  | 25 | [20 empty] | 2016-09-01 |  | 2016-07-26 | NO | Expedited | [8 empty] | 2016-11-01 | In Operation | Res | Y
Fitchburg | Lunenburg | 2199 | 1462 | 239 |  |  | Solar |  | 30W30 | 2016-07-25 | 2016-08-05 | 10 |  | 10 | 2016-08-05 | 2016-09-26 | 36 |  | 36 | [20 empty] | 2016-09-26 |  |  | YES | Expedited | [6 empty] | 2017-01-06 | 2017-01-06 | 2017-01-06 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2195 | 1420 | 5 |  |  | Solar |  | 40W40 | 2016-06-20 | 2016-07-01 | 10 |  | 10 | 2016-09-16 | 2016-10-18 | 22 |  | 22 | [20 empty] | 2016-10-01 |  | 2016-07-31 | NO | Expedited | [8 empty] | 2016-12-12 | In Operation | Res | Y
Fitchburg | Fitchburg | 2193 | 1420 | 84 |  |  | Solar |  | 50W56 | 2016-06-20 | 2016-07-01 | 10 |  | 10 | 2016-07-17 | 2016-07-29 | 10 |  | 10 | [20 empty] | 2016-08-02 |  | 2016-07-20 | NO | Expedited | [8 empty] | 2016-12-22 | In Operation | Res | Y
Fitchburg | Fitchburg | 2192 | 1420 | 8.35 |  |  | Solar |  | 01W02 | 2016-06-16 | 2016-07-01 | 11 | 8 | 3 | 2016-08-15 | 2016-08-29 | 11 |  | 11 | [20 empty] | 2016-09-01 |  | 2017-03-26 | NO | Expedited | [8 empty] | 2016-11-18 | In Operation | Res | Y
Fitchburg | Lunenburg | 2188 | 1462 | 18.15 |  |  | Solar |  | 31W38 | 2016-06-16 | 2016-06-30 | 10 |  | 10 | 2016-07-19 | 2016-08-17 | 22 |  | 22 | [20 empty] | 2016-08-18 |  | 2016-08-15 | NO | Expedited | [8 empty] | 2017-01-27 | In Operation | Res | Y
Fitchburg | Fitchburg | 2185 | 1420 | 4.15 |  |  | Solar |  | 35W36 | 2016-06-15 | 2016-06-23 | 6 |  | 6 | 2016-07-19 | 2016-08-05 | 14 |  | 14 | [20 empty] | 2016-08-05 |  | 2016-08-15 | NO | Expedited | [8 empty] | 2016-10-12 | In Operation | Res | Y
Fitchburg | Townsend | 2183 | 1469 | 6.72 |  |  | Solar |  | 15W16 | 2016-06-15 | 2016-06-22 | 5 |  | 5 | 2016-07-19 | 2016-08-05 | 14 |  | 14 | [20 empty] | 2016-08-05 |  | 2016-08-20 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2182 | 1462 | 9.92 |  |  | Solar |  | 31W37 | 2016-06-15 | 2016-06-22 | 5 | 2 | 3 | 2016-07-22 | 2016-08-19 | 21 |  | 21 | [20 empty] | 2016-08-22 |  | 2016-10-31 | NO | Expedited | [8 empty] | 2016-11-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2179 | 1420 | 195 |  |  | Solar |  | 25W27 | 2016-06-13 | 2016-08-24 | 51 | 47 | 4 | 2016-08-25 | 2016-09-19 | 17 |  | 17 | [20 empty] | 2016-09-22 |  | 2016-09-01 | YES | Expedited | 2016-11-08 | 2016-11-10 | 2016-11-10 | 1 |  | 1 | 2017-02-17 | 2017-02-23 | 2017-02-23 | In Operation | Res | Y
Fitchburg | Fitchburg | 2178 | 1420 | 288 |  |  | Solar |  | 01W04 | 2016-06-13 | 2016-06-23 | 8 |  | 8 | 2016-06-24 | 2016-07-26 | 22 |  | 22 | [20 empty] | 2016-07-28 |  | 2016-09-01 | YES | Expedited | [8 empty] | 2017-06-19 | In Operation | Res | Y
Fitchburg | Ashby | 2177 | 1431 | 5.45 |  |  | Solar |  | 35W36 | 2016-06-13 | 2016-06-17 | 4 |  | 4 | 2016-08-05 | 2016-08-05 | 1 |  | 1 | [20 empty] | 2016-08-09 |  | 2016-08-13 | YES | Expedited | [8 empty] | 2016-11-07 | In Operation | Res | Y
Fitchburg | Fitchburg | 2175 | 1420 | 5.75 |  |  | Solar |  | 01W02 | 2016-06-10 | 2016-06-16 | 5 |  | 5 | 2016-07-05 | 2016-08-03 | 22 |  | 22 | [20 empty] | 2016-08-08 |  | 2016-07-14 | NO | Expedited | [8 empty] | 2016-09-20 | In Operation | Res | Y
Fitchburg | Fitchburg | 2174 | 1420 | 6 |  |  | Solar |  | 20W22 | 2016-06-10 | 2016-06-16 | 5 |  | 5 | [25 empty] | 2016-09-09 |  |  | YES | Expedited | [8 empty] | 2016-09-29 | In Operation | Res | Y
Fitchburg | Fitchburg | 2173 | 1420 | 3.3 |  |  | Solar |  | 31W34 | 2016-06-09 | 2016-06-16 | 6 | 1 | 5 | 2016-07-30 | 2016-08-05 | 5 |  | 5 | [20 empty] | 2016-08-05 |  | 2016-08-01 | NO | Expedited | [8 empty] | 2016-11-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 2170 | 1420 | 4.15 |  |  | Solar |  | 31W34 | 2016-06-07 | 2016-06-15 | 7 |  | 7 | 2016-07-06 | 2016-07-06 | 1 |  | 1 | [20 empty] | 2016-08-05 |  | 2016-08-07 | NO | Expedited | [8 empty] | 2016-11-16 | Cancelled | Res | Y
Fitchburg | Townsend | 2168 | 1469 | 7 |  |  | Solar |  | 15W16 | 2016-06-06 | 2016-06-13 | 6 |  | 6 | 2016-06-27 | 2016-07-28 | 23 |  | 23 | [20 empty] | 2016-07-28 |  | 2016-07-12 | NO | Expedited | [8 empty] | 2016-08-25 | In Operation | Comm | Y
Fitchburg | Townsend | 2167 | 1469 | 10.5 |  |  | Solar |  | 15W16 | 2016-05-25 | 2016-06-09 | 12 | 1 | 11 | 2016-06-24 | 2016-06-24 | 1 |  | 1 | [20 empty] | 2016-07-28 |  | 2016-07-27 | NO | Expedited | [8 empty] | 2016-08-25 | In Operation | Res | Y
Fitchburg | Fitchburg | 2165 | 1420 | 7.5 |  |  | Solar |  | 20W22 | 2016-06-03 | 2016-07-06 | 22 | 6 | 16 | 2016-08-05 | 2016-08-23 | 13 |  | 13 | [20 empty] | 2016-08-25 |  | 2016-08-03 | YES | Expedited | [8 empty] | 2016-11-15 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2160 | 1420 | 5 |  |  | Solar |  | 40W40 | 2016-05-31 | 2016-08-25 | 61 | 55 | 6 | 2016-09-10 | 2016-09-29 | 14 |  | 14 | [20 empty] | 2016-09-29 |  | 2016-08-01 | NO | Expedited | [8 empty] | 2016-11-21 | In Operation | Res | Y
Fitchburg | Ashby | 2157 | 1431 | 10 |  |  | Solar |  | 39W19 | 2016-05-27 | 2016-06-09 | 10 |  | 10 | 2016-06-22 | 2016-06-22 | 1 |  | 1 | [20 empty] | 2016-06-22 |  |  | NO | Expedited | [8 empty] | 2016-11-10 | In Operation | Res | Y
Fitchburg | Ashby | 2148 | 1431 | 6.25 |  |  | Solar |  | 39W19 | 2016-05-24 | 2016-08-11 | 56 | 42 | 14 | 2016-08-22 | 2016-09-06 | 11 |  | 11 | [20 empty] | 2016-09-09 |  |  | NO | Expedited | [8 empty] | 2016-11-17 | In Operation | Res | Y
Fitchburg | Fitchburg | 2147 | 1420 | 3.5 |  |  | Solar |  | 31W34 | 2016-05-24 | 2016-06-06 | 10 |  | 10 | 2016-06-27 | 2016-07-28 | 23 |  | 23 | [20 empty] | 2016-07-28 |  | 2016-06-14 | NO | Expedited | [8 empty] | 2016-08-05 | In Operation | Res | Y
Fitchburg | Lunenburg | 2129 | 1462 | 12 |  |  | Solar |  | 31W37 | 2016-05-13 | 2016-06-01 | 13 |  | 13 | 2016-06-28 | 2016-07-28 | 22 |  | 22 | [20 empty] | 2016-07-28 |  | 2016-07-12 | NO | Expedited | [8 empty] | 2016-11-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2128 | 1420 | 3.5 |  |  | Solar |  | 35W36 | 2016-05-13 | 2016-06-01 | 13 |  | 13 | 2016-06-27 | 2018-06-27 | 497 |  | 497 | [20 empty] | 2016-07-28 |  | 2016-06-15 | NO | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Lunenburg | 2110 | 1462 | 5.5 |  |  | Solar |  | 31W37 | 2016-05-04 | 2016-06-02 | 21 |  | 21 | 2016-06-27 | 2016-06-27 | 1 |  | 1 | [20 empty] | 2016-07-28 |  | 2016-06-01 | NO | Expedited | [8 empty] | 2016-12-08 | In Operation | Res | Y
Fitchburg | Lunenburg | 2109 | 1462 | 4990 |  |  | Solar |  | 31W37 | 2017-02-16 | 2017-03-03 | 10 |  | 10 | [10 empty] | 2017-03-05 | 2017-03-31 | 19 | 3 | 16 | 2017-05-22 | 2017-09-08 | 77 | 32 | 45 | [5 empty] | 2017-10-28 | 2019-02-18 | 2017-12-01 | YES | Standard | [6 empty] | 2020-11-19 | 2020-11-19 | 2020-12-22 | In Operation | Comm | Y
Fitchburg | Fitchburg | 2103 | 1420 | 4.15 |  |  | Solar |  | 31W37 | 2016-05-03 | 2016-05-20 | 14 |  | 14 | 2016-06-26 | 2016-07-29 | 24 |  | 24 | [20 empty] | 2016-07-29 |  | 2016-07-02 | NO | Expedited | [8 empty] | 2016-11-09 | In Operation | Res | Y
Fitchburg | Fitchburg | 2098 | 1420 | 6 |  |  | Solar |  | 25W27 | 2016-04-28 | 2016-06-08 | 29 |  | 29 | 2016-06-29 | 2016-07-28 | 21 |  | 21 | [20 empty] | 2016-07-28 |  | 2016-06-27 | NO | Expedited | [8 empty] | 2017-03-08 | In Operation | Comm | Y
Fitchburg | Ashby | 2061 | 1431 | 8 |  |  | Solar |  | 39W19 | 2016-04-12 | 2016-07-28 | 74 | 52 | 22 | 2016-08-19 | 2018-09-14 | 514 |  | 514 | [20 empty] | 2016-09-16 |  |  | NO | Expedited | [8 empty] | 2016-12-02 | In Operation | Res | Y
Fitchburg | Fitchburg | 2032 | 1420 | 22.5 |  |  | Solar |  | 11W11 | 2016-04-05 | 2016-04-08 | 4 |  | 4 | 2016-04-09 | 2016-04-12 | 2 |  | 2 | [20 empty] | 2016-04-13 |  |  | YES | Expedited | [6 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | In Operation | Res | Y
Fitchburg | Ashby | 2007 | 1431 | 3.25 |  |  | Solar |  | 39W19 | 2016-03-22 | 2016-08-16 | 102 |  | 102 | 2016-08-20 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-09-05 | NO | Expedited | [8 empty] | 2016-11-16 | In Operation | Res | Y
Fitchburg | Ashby | 2000 | 1431 | 8.75 |  |  | Solar |  | 39W19 | 2016-03-24 | 2016-08-10 | 96 |  | 96 | 2016-08-22 | 2016-09-14 | 17 |  | 17 | [20 empty] | 2016-09-16 |  | 2016-08-31 | YES | Expedited | [8 empty] | 2016-10-11 | In Operation | Res | Y
Fitchburg | Townsend | 1984 | 1469 | 10 |  |  | Solar |  | 15W16 | 2016-03-14 | 2016-03-17 | 3 |  | 3 | 2016-12-09 | 2016-12-27 | 13 |  | 13 | [20 empty] | 2016-03-18 |  | 2016-12-25 | NO | Expedited | [8 empty] | 2017-09-18 | In Operation | Res | Y
Fitchburg | Ashby | 1961 | 1431 | 2 |  |  | Solar |  | 39W19 | 2016-08-22 | 2016-08-24 | 3 | 96 | -93 | 2016-08-23 | 2016-09-07 | 11 | 6 | 5 | [20 empty] | 2016-09-09 |  |  | NO | Expedited | [6 empty] | 2016-11-22 | 2016-11-22 | 2016-11-23 | Cancelled | Res | Y
Fitchburg | Townsend | 1938 | 1469 | 20.5 |  |  | Solar |  | 15W16 | 2016-03-01 | 2016-03-09 | 7 |  | 7 | 2016-03-10 | 2016-03-15 | 4 |  | 4 | [20 empty] | 2016-03-18 |  | 2016-03-29 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Fitchburg | 1665 | 1420 | 200 |  |  | Solar |  | 50W56 | 2015-12-16 | 2015-12-29 | 9 |  | 9 | 2015-12-30 | 2016-01-26 | 18 |  | 18 | [20 empty] | 2016-01-26 |  | 2016-02-15 | YES | Expedited | [6 empty] | 2016-06-21 | 2016-07-05 | 2016-07-05 | In Operation | Res | Y
Fitchburg | Fitchburg | 1540 | 1420 | 488 |  |  | Solar |  | 50W56 | 2015-11-16 | 2016-02-23 | 67 |  | 67 | [25 empty] | 2016-04-06 |  | 2016-01-05 | YES | Standard | [8 empty] | 2017-06-08 | In Operation |  | Y
Fitchburg | Townsend | 1531 | 1453 | 750 |  |  | Solar |  | 39W18 | 2016-05-02 | 2017-01-04 | 171 | 42 | 129 | [25 empty] | 2017-06-08 |  | 2017-09-01 | YES | Standard | [9 empty] | Cancelled | comm
Fitchburg | Fitchburg | 1464 | 1420 | 151.2 |  |  | Solar |  | 01W02 | 2016-03-18 | 2016-04-12 | 18 | 2 | 16 | [14 empty] | 0 | 2016-05-04 | 2016-07-20 | 53 |  | 53 | [5 empty] | 2016-07-22 |  |  | NO | Standard | [8 empty] | 2017-11-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 1320 | 1462 | 20.35 |  |  | Solar |  | 39W18 | 2015-09-18 | 2015-10-07 | 14 | 3 | 11 | 2015-10-07 | 2015-10-29 | 16 |  | 16 | [20 empty] | 2015-12-03 |  |  | NO | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 1314 | 1462 | 21 |  |  | Solar |  | 31W38 | 2015-10-09 | 2015-10-22 | 9 |  | 9 | [25 empty] | 2015-11-17 |  | 2015-11-01 | NO | Expedited | [8 empty] | 2016-02-01 | In Operation | Res | Y
Fitchburg | Townsend | 1239 | 1469 | 360 |  |  | Solar |  | 39W18 | 2016-03-21 | 2016-05-16 | 40 |  | 40 | 2016-05-16 | 2016-05-18 | 3 |  | 3 | [22 empty] | 06/31/2016 | NO | Expedited | [9 empty] | Cancelled | Comm | Y
Fitchburg | Fitchburg | 1235 | 1420 | 19.3 |  |  | Solar |  | 40W40 | 2015-08-13 | 2015-08-31 | 13 |  | 13 | [15 empty] | 2015-10-02 | 2015-10-08 | 5 |  | 5 | [5 empty] | 2015-10-02 |  | 2015-10-13 | NO | Expedited | [8 empty] | 2016-03-21 | In Operation | Res | Y
Fitchburg | Ashby | 1219 | 1431 | 18 |  |  | Solar |  | 39W19 | 2015-08-19 | 2015-09-03 | 12 |  | 12 | 2015-09-04 | 2015-09-23 | 13 |  | 13 | [20 empty] | 2015-09-30 |  | 2015-10-13 | YES | Expedited |  | 2015-12-01 | 2015-12-01 | 1 |  | 1 | 2016-04-20 | 2016-04-20 | 2016-04-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 1218 | 1420 | 42 |  |  | Solar |  | 40W39 | 2015-08-14 | 2015-09-03 | 15 |  | 15 | [15 empty] | 2015-09-30 | 2015-10-09 | 8 |  | 8 | [5 empty] | 2015-10-14 |  | 2015-10-01 | NO | Expedited | [6 empty] | 2015-12-21 | 2015-12-21 | 2015-12-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 1206 | 1420 | 45 |  |  | Solar |  | 40W40 | 2015-08-19 | 2015-09-03 | 12 |  | 12 | 2015-09-04 | 2015-09-23 | 13 |  | 13 | [20 empty] | 2015-09-30 |  | 2015-11-30 | YES | Expedited |  | 2015-11-02 | 2015-12-04 | 23 |  | 23 | 2015-12-30 | 2015-12-30 | 2015-12-30 | In Operation | Res | Y
Fitchburg | Fitchburg | 1192 | 1420 | 16.95 |  |  | Solar |  | 25W27 | 2015-08-13 | 2015-08-28 | 12 |  | 12 | 2018-08-29 | 2018-08-29 | 1 |  | 1 | [10 empty] | 2015-10-02 | 2015-11-24 | 36 |  | 36 | [5 empty] | 2015-10-02 |  |  | YES | Expedited | [8 empty] | 2016-03-01 | In Operation | Res | Y
Fitchburg | Fitchburg | 1191 | 1420 | 720 |  |  | Solar |  | 31W37 | 2015-08-05 | 2015-10-08 | 46 | 27 | 19 | 2015-10-08 | 2015-10-08 | 1 |  | 1 | [22 empty] | 2015-10-31 | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 1126 | 1420 | 500 |  |  | Solar |  | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1125 | 1420 | 500 |  |  | Solar |  | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1124 | 1420 | 500 |  |  | Solar |  | 50W56 | 2016-01-21 | 2016-03-31 | 49 |  | 49 | [14 empty] | 0 | [13 empty] | NO | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 1123 | 1420 | 500 |  |  | Solar |  | 50W56 | 2016-01-21 | 2016-03-31 | 49 | 29 | 20 | 2016-03-31 | 2016-05-05 | 25 |  | 25 | [10 empty] | 2016-04-15 | 2016-05-31 | 31 |  | 31 | [7 empty] | 2016-09-14 | NO | Expedited | [9 empty] | Cancelled | Comm | Y
Fitchburg | Ashby | 964 | 1431 | 414 |  |  | Solar |  | 39W19 | 2015-05-11 | 2015-06-24 | 31 | 22 | 9 | 2015-06-24 | 2015-07-23 | 22 |  | 22 | [22 empty] | 2015-08-01 | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 952 | 1420 | 400 |  |  | Solar |  | 01W01 | 2015-05-12 | 2015-05-21 | 8 |  | 8 | [14 empty] | 0 | 2015-05-26 | 2015-06-05 | 9 |  | 9 | [5 empty] | 2015-12-04 |  | 2015-09-15 | NO | Standard | [8 empty] | 2015-12-30 | In Operation | Res | Y
Fitchburg | Lunenburg | 932 | 1462 | 15.2 |  |  | Solar |  | 31W38 | 2015-04-20 | 2015-05-06 | 12 | 2 | 10 | [5 empty] | 2015-05-19 | 2015-06-15 | 19 |  | 19 | [5 empty] | 2015-06-15 | 2015-06-23 | 6 |  | 6 | [5 empty] | 2015-06-15 |  | 2015-06-30 | NO | Expedited | [8 empty] | 2015-09-11 | In Operation | Res | Y
Fitchburg | Fitchburg | 895 | 1420 | 4608 |  |  | Solar |  | 20H22 | 2015-03-26 | 2015-04-09 | 11 |  | 11 | 2015-04-09 | 2015-04-09 | 1 |  | 1 | [22 empty] | 2015-08-01 | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 894 | 1420 | 480 |  |  | Solar |  | 20H22 | 2015-03-26 | 2015-04-09 | 11 |  | 11 | 2015-04-09 | 2015-04-24 | 11 |  | 11 | [10 empty] | 2015-06-04 | 2015-08-28 | 61 |  | 61 | [8 empty] | YES | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 850 | 1420 | 984 |  |  | Solar |  | 35W36 | 2015-02-06 | 2015-03-17 | 26 | 19 | 7 | [10 empty] | 2015-03-19 | 2015-04-15 | 20 |  | 20 | 2015-05-21 | 2015-10-02 | 94 |  | 94 | 2016-02-22 | 2016-04-28 | 47 |  | 47 | 2016-06-03 | 2017-06-14 |  | YES | Standard |  | 2017-06-15 | 2018-06-04 | 239 | 120 | 119 | 2018-06-07 | 2018-06-07 | 2018-07-18 | In Operation | Comm | Y
Fitchburg | Fitchburg | 849 | 1420 | 864 |  |  | Solar |  | 35W36 | 2015-02-06 | 2015-03-01 | 15 | 15 | 0 | [10 empty] | 2015-03-08 | 2015-04-15 | 27 |  | 27 | 2015-05-21 | 2015-10-02 | 94 |  | 94 | 2016-02-22 | 2016-04-28 | 47 |  | 47 | 2016-06-03 | 2017-06-14 |  | YES | Standard |  | 2017-06-15 | 2018-06-04 | 239 | 120 | 119 | 2018-06-07 | 2018-06-07 | 2018-07-18 | In Operation | Comm | Y
Fitchburg | Lunenburg | 843 | 1462 | 2000 |  |  | Solar |  | 30W30 | 2015-03-19 | 2015-04-20 | 22 | 6 | 16 | 2015-04-20 | 2015-04-28 | 6 |  | 6 | [23 empty] | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Ashby | 841 | 1431 | 997.6 |  |  | Solar |  | 39W19 | 2015-01-27 | 2015-03-16 | 34 | 25 | 9 | 2015-03-16 | 2015-04-14 | 21 |  | 21 | [22 empty] | 2015-08-01 | NO | Expedited | [9 empty] | Cancelled | Comm
Fitchburg | Fitchburg | 808 | 1420 | 540 |  |  | Solar |  | 40W40 | 2015-05-11 | 2015-05-26 | 11 |  | 11 | [10 empty] | 2015-06-16 | 2015-07-13 | 19 | 4 | 15 | 2015-07-27 | 2015-10-06 | 51 |  | 51 | 2015-11-25 | 2016-01-08 | 30 |  | 30 | 2016-02-08 |  | 2015-09-01 | NO | Standard | [8 empty] | 2017-02-22 | In Operation | Res | Y
Fitchburg | Lunenburg | 755 | 1462 | 170 |  |  | Solar |  | 31W37 | 2014-12-05 | 2014-12-17 | 9 |  | 9 | [5 empty] | 2015-02-12 | 2015-03-05 | 15 |  | 15 | [5 empty] | 2015-04-09 | 2015-05-12 | 23 |  | 23 | [5 empty] | 2015-03-31 |  | 2015-03-30 | NO | Standard | [6 empty] | 2015-12-04 | 2015-12-04 | 2015-12-04 | In Operation | Res | Y
Fitchburg | Fitchburg | 750 | 1420 | 72 |  |  | Solar |  | 40W40 | 2014-12-03 | 2014-12-05 | 3 |  | 3 | 2014-12-05 | 2014-12-10 | 4 |  | 4 | [20 empty] | 2014-12-12 |  | 2015-01-31 | YES | Expedited | [6 empty] | 2015-03-11 | 2015-03-11 | 2015-03-11 | In Operation | Res | Y
Fitchburg | Ashby | 501 | 1431 | 1848 |  |  | Solar |  | 39W19 | 2014-12-15 | 2015-04-13 | 81 | 79 | 2 | [10 empty] | 2015-04-15 | 2015-04-22 | 5 |  | 5 | 2015-05-01 | 2015-09-04 | 89 | 5 | 84 | 2015-12-22 | 2016-02-08 | 32 |  | 32 | 2015-10-28 |  | 2015-06-01 | YES | Standard | 2017-11-08 | 2017-03-15 | 2017-10-04 | 141 |  | 141 |  |  | 2017-12-06 | In Operation | Comm | Y
Fitchburg | Townsend | 452 | 1420 | 17 |  |  | Solar |  | 15W16 | 2014-05-22 | 2014-06-23 | 21 | 10 | 11 | [14 empty] | 0 | [10 empty] | 2014-06-23 |  | 2014-07-19 | NO | Standard | [6 empty] | 2014-12-18 | 2014-12-18 | 2014-12-29 | In Operation | Res | Y
Fitchburg | Lunenburg | 413 | 1462 | 72 |  |  | Solar |  | 30W30 | 2014-04-17 | 2014-04-24 | 5 | 1 | 4 | 2014-04-25 | 2014-05-19 | 17 |  | 17 | [20 empty] | 2014-05-20 |  | 2014-06-01 | YES | Expedited | [9 empty] | Cancelled | Res | Y
Fitchburg | Townsend | 395 | 1469 | 36.765 |  |  | Solar |  | 15W16 | 2014-02-03 | 2014-02-07 | 5 |  | 5 | [14 empty] | 0 | 2014-04-30 | 2014-05-05 | 4 |  | 4 | [5 empty] | 2014-05-06 |  | 2014-02-17 | NO | Standard | [8 empty] | 2014-06-16 | In Operation | Res | Y
Fitchburg | Lunenburg | 374 | 1462 | 72 |  |  | Solar |  | 30W30 | 2013-10-28 | 2013-11-01 | 5 |  | 5 | 2013-11-05 | 2013-12-02 | 18 |  | 18 | [20 empty] | 2013-12-10 |  | 2014-06-01 | YES | Expedited | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 268 | 1462 | 300 |  |  | Solar |  | 31W37 | 2012-08-21 | 2012-09-03 | 9 |  | 9 | [14 empty] | 0 | [10 empty] | 2012-11-05 |  | 2012-11-01 | NO | Standard | [6 empty] | 2012-12-28 | 2012-12-28 | 2012-12-28 | In Operation | Res | Y
Fitchburg | Fitchburg | 258 | 1420 | 71.4 |  |  | Gas |  | 22W1 | 2012-07-13 | 2012-08-13 | 22 |  | 22 | [5 empty] | 2012-12-10 | 2013-03-04 | 57 |  | 57 |  |  |  |  | 0 | [10 empty] | 2013-04-11 |  | 2012-05-02 | NO | Standard | [8 empty] | 2014-10-21 | In Operation | Res | Y
Fitchburg | Fitchburg | 238 | 1420 | 155 |  |  | Solar |  | 40W42 | 2012-05-17 | 2012-08-08 | 58 | 48 | 10 | [5 empty] | 2012-10-01 | 2012-11-26 | 39 |  | 39 |  |  |  |  | 0 | [10 empty] | 2012-11-26 |  | 2012-08-01 | NO | Standard | [6 empty] | 2013-01-08 | 2013-01-11 | 2013-01-11 | In Operation | Res | Y
Fitchburg | West Townsend | 230 | 1474 | 10 |  |  | Solar |  | 39W18 | 2012-04-11 | 2012-04-19 | 6 |  | 6 | [14 empty] | 0 | [10 empty] | 2012-05-22 |  | 2012-07-30 | NO | Standard | [6 empty] | 2012-07-18 | 2012-07-18 | 2012-07-18 | In Operation | Res | Y
Fitchburg | Fitchburg | 206 | 1420 | 675 |  |  | Solar |  | 40W39 | 2012-03-29 | 2012-04-13 | 12 |  | 12 | [10 empty] | 2012-04-15 | 2012-04-27 | 9 |  | 9 | [5 empty] | 2012-05-08 | 2012-07-24 | 54 |  | 54 | 2012-10-25 |  | 2012-06-01 | YES | Standard |  | 2012-11-20 | 2013-05-31 | 132 |  | 132 | 2013-05-31 | 2013-05-31 | 2013-05-31 | In Operation | Res | Y
Fitchburg | Fitchburg | 186 | 1420 | 190 |  |  | Solar |  | 22W1 | 2011-10-21 | 2011-11-01 | 8 |  | 8 | [14 empty] | 0 | [10 empty] | 2012-01-17 |  | 2011-12-01 | NO | Standard | [8 empty] | 2012-02-15 | In Operation | Res | Y
Fitchburg | Fitchburg | 179 | 1420 | 2000 |  |  | Solar |  | 35W36 | 2011-08-26 | 2011-10-11 | 33 |  | 33 | [14 empty] | 0 | 2011-11-09 | 2012-11-01 | 250 | 210 | 40 | [7 empty] | 2012-07-01 | YES | Standard | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 178 | 1462 | 1000 |  |  | Solar |  | 31W38 | 2011-08-26 | 2011-09-26 | 22 |  | 22 | [10 empty] | 2011-10-12 | 2011-10-30 | 13 |  | 13 | 2011-11-09 | 2012-11-01 | 250 | 210 | 40 | [5 empty] | 2012-10-04 |  | 2012-07-01 | YES | Standard | [8 empty] | 2014-07-31 | In Operation | Res | Y
Fitchburg | Lunenburg | 174 | 1462 | 2500 |  |  | Solar |  | 0 | 2011-07-28 | 2011-08-17 | 15 |  | 15 | [10 empty] | 2011-08-02 | 2011-10-18 | 56 | 28 | 28 | 2012-01-11 | 2012-05-02 | 78 | 9 | 69 | [7 empty] | 2012-03-01 | YES | Standard | [9 empty] | Cancelled | Res
Fitchburg | Lunenburg | 173 | 1462 | 2500 |  |  | Solar |  | 30W31 | 2011-07-28 | 2011-08-17 | 15 |  | 15 | [10 empty] | 2011-08-02 | 2011-10-18 | 56 |  | 56 | 2012-01-11 | 2012-05-02 | 78 |  | 78 | [5 empty] | 2013-06-28 |  | 2013-06-28 | YES | Standard | [6 empty] | 2014-07-21 | 2014-07-21 | 2014-07-21 | In Operation | Res | Y
Fitchburg | Lunenburg | 169 | 1852 | 1500 |  |  | Solar |  | 40W40 | 2011-07-28 | 2011-08-10 | 10 |  | 10 | [5 empty] | 2011-09-16 | 2011-10-13 | 20 |  | 20 |  |  |  |  | 0 | 2011-10-25 | 2012-01-22 | 63 | 45 | 18 | [7 empty] | 2011-12-31 | YES | Standard | [9 empty] | Cancelled | Res | Y
Fitchburg | Fitchburg | 139 | 1420 | 1800 |  |  | Gas |  | 40W38 | 2011-02-10 | 2011-04-19 | 49 | 41 | 8 | [14 empty] | 0 | 2011-06-01 | 2011-10-28 | 108 | 88 | 20 | [5 empty] | 2011-11-01 |  |  | YES | Standard | [8 empty] | 2012-04-13 | Not In Service | Res