{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["MASTER COPY","WMDG List","Sheet1","Holiday"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":2,"defined_names":4,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"MASTER COPY","index":0,"n_rows":6163,"n_cols":177,"rows_kept":562,"cut":true,"hidden":true,"merged":[[0,176,2,176],[0,127,0,131],[0,132,0,138],[1,29,2,29],[3,132,3,138],[3,172,3,173],[3,127,3,131],[2,59,2,62],[0,13,2,13]],"bounds":{"rows_first":250,"rows_last":62,"rows_between":250,"halvings":3}}
[1,2,null,null,null,null,null,null,null,null,null,null,null,"New Net Mtr # from C2 NOT Listed starting 11/1/2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"****************",null,null,null,null,null,null,null,null,null,null,null,1,null,null,null,null,null,null,null,null,null,2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"**OPERATE",null,null,null,null,"= Closed / Do Not Use",null,null,null,"= Pending Closure / Do Not Use",null,null,"= Closed / Do Not Use",null,null,3,null,null,4,"= Pending Closure / Do Not Use",null,null,null,"= Closed / Do Not Use",null,null,"= Pending Closure / Do Not Use",null,null,"= Closed / Do Not Use",null,null,6,null,null,null,null,null,null,null,7,null,null,null,null,null,null,null,null,null,null,null,null,null,"***MUST be filled in for DRTS***",null,null,null,null,"***MUST be filled in for DRTS***",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Stopped tracking as of 11/10/2015"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Public = Class 2 or 3 ONLY, Private excl. Simp.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"10 Days","DATE**",null,null,null,null,"= Pending Closure / Do Not Use",null,null,null,"= Active",null,null,null,null,null,null,null,null,null,"= Active",null,null,null,null,null,5,"= Active"]
[null,null,"DOER",null,null,null,null,"DOER",null,null,"rvisd",null,null,null,null,null,null,null,null,"DOER",null,"DOER","DOER",null,"DOER",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"DOER","WMECO","DOER",null,"DOER","WMECO","WMECO","DOER","WMECO","DOER","WMECO","WMECO","WMECO","WMECO","WMECO","WMECO","WMECO","DOER","DOER","DOER","for SQ reporting as of 5/1/2014",null,null,null,"DOER","WMECO",null,"3rd Party","Landowner",null,null,"DOER",null,"WMECO","DOER","WMECO","WMECO","DOER",null,"= Active",null,null,null,"WMECO","WMECO","WMECO","WMECO","DOER","DOER","DOER","DOER","DOER","DOER","WMECO","WMECO","WMECO","WMECO","DOER","DOER","DOER","WMECO","WMECO","WMECO","WMECO","DOER","DOER","DOER","WMECO","WMECO","WMECO","WMECO","DOER","DOER","DOER","DOER","WMECO","DOER","DOER","WMECO","DOER"]
["2016-02-03T12:29:30.580",null,"Expedited / Standard Process","for SQ Reporting",null,"Project Status",null,"Facility ID",null,null," 4-13-12 EIA Report","BA#","SA#","Meter #","Site #",null,null,null,null,"City/Town",null,"Zip Code","Company Name",null,"Circuit Name",null,null,null,null,"Proposed Net Meter 3% minus Simp vs 3%",null,"As of 2/16/11",null,"*** See Note in Cell A1",null,null,null,null,"EIA Report","Design Capacity","Internal Use ONLY          Design Capacity","Fuel Type","internal","Date Application Received","Internal Use ONLY as of 4/10/2013","Internal Use ONLY as of 4/10/2013","Date Application Deemed Complete","Internal Use ONLY as of 4/11/2013","Customer Time Lapsed (Workdays)","Simplified","Simplified","Customer Time Lapsed (Workdays)","Simplified Plus 5 as of 8/21/2013","Simplified Plus 5","Simplified Plus 5","Customer Time Lapsed (Workdays)","New DOER","New DOER ","Customer Time Lapsed (Workdays)","IA Phase","IA Phase","IA Phase","Timeline Verification","Date Interconnection Agreement Sent","For Internal Use ONLY as of 1/1/2011","As of 8/25/09","3rd Party needed","Landowner needed","as of 8/11/10","As of 8/25/09","System Modifications Required",null,"As of 8/21/2013","Authorization to Interconnect","For Internal Use ONLY as of 8/21/2013","Customer Time Lapsed (Workdays)","Customer's Estimated In-Service Date",null,"internal","internal","internal","internal","internal","internal","internal","internal","New DOER","New DOER ","Customer Time Lapsed (Workdays)","New DOER","New DOER ","Customer Time Lapsed (Workdays)","internal","internal","internal","internal","New DOER ","New DOER ","Customer Time Lapsed (Workdays)","internal","internal","internal","internal","New DOER ","New DOER ","Customer Time Lapsed (Workdays)","internal","internal","internal","internal","New DOER ","New DOER ","New DOER ","Customer Time Lapsed (Workdays)","internal","New DOER ","New DOER ","internal","NOTES",null,null,null,null,null,null,"Method of",null,"Electric Customer Contact Info from Exhibit H section 6.1",null,null,null,null,"Interconnecting Customer Contact Info from Section 17.1 of the IA Agreement.",null,null,null,null,null,null,"Meter Reporting",null,null,null,null,null,null,null,null,null,null,null,null,null,"Planning & Ordering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April 1st QF Report","Mike Hall - columns added for FERC review",null,"EIA-861","Have Application"]
["2016-02-03T12:29:30.580","3rd Party Owner NAME","Requires Monthly Report to DOER \"SIMP\" \"EXP\" \"STD\" \"COMP\" \"ISO\" \"OTHER\"","Negotiated Timeline, Early ISA, Group","WMECO DG Project Manager","In Process / Completed / Cancelled / Removed / Withdrawn / Cust Hold","Date Cancelled / Removed / Withdrawn Cust Hold","WMECO Tracking ID","STORMS      Work Request Number","Elect. Rate","Residential / Commercial / Industrial","C2 Billing Account #","C2 Service Account #","Meter Numbers","Site ID","Street #","Street                                                          This is the SERVICE ADDRESS from C2","Unit Type","Unit Value","Town","State","ZIP","Company Name","Substation","Circuit *","For Bill O'Hara     PTF","For Bill O'Hara    non-PTF","Prime Mover","Description","private 3% / public 3% per Mike to Cindy as of Nov 14","Has CADMUS Approval","Host Customer = Municipality or Governmental entity (DPU)","Date Schedule Z Received","1%","For Solar = Aggregate Capacity for 1% = 80% of DC-STC (KW)","For Solar = DC-STC (KW)","Compensation for Net Metering","Send sales payment info form to Craig Holmes","Total AC (KW)","Design Capacity (kW)  AC","Capacity (kW)  AC   insurance req'd","Fuel Type","Year application received","Date Appl Rcvd - as of 8/28/2013 appl rcvd after 4pm is next day","Date 3 Day Ack Sent","Number of Business Days for 3 day Acknowledgement","Date Application Complete","Number of Business Days for 10 day \"Date Appl Complete\"","Number workdays \"clock\" stoppage 10 day \"Cust for Ap Compl\" ","SIMP Date \"15 day\" Review of Screens Begun","SIMP Date \"15 day\" Review of Screens Completed","Number workdays \"clock\" stoppage by Cust \"Screen Review\""," \"SIMP\" or \"SIMP5\"","Date \"5 day\" Start SVC type / New Svc Review Begun","Date \"5 day\" Start SVC type / New Svc Review Complete","Number workdays \"clock\" stoppage by Cust \"Service Review\"","EXP Date \"25 day\" Review of Screens Begun","EXP Date \"25 day\" Review of Screens Completed","Number workdays \"clock\" stoppage by Cust \"Screen Review\"  ","Date IA Begun","Date IA Sent","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer","Date Timeline Verification Email Sent","Date Agreement Sent \"Approval to Install\"","Number of Business Days for Application \"Approval to Install\".","IA on File (date received)","3rd Party doc - on File (date rcvd)","Landowner doc - on File (date rcvd)","Insurance Required Min Amount","Insurance - Valid through ","Requires Monthly Report to DOER \"Yes\" or \"No\" or \"TBD\"","SOG Required for Dispatch?","Date \"10 days\" Certificate of Completion Received","In-Service Date (On-Line) \"Approval to Operate\"","Number of Business Days for Application \"Approval to Operate\".","Number workdays \"clock\" stop by Cust \"Compl Docs\"","Estimated In-Service Date","Transfer of Owner Form Required (enter date received)","DG Work Order #","Application Fee Dollars Received","DG Work Order Actuals","Balance on CLOSED DG work order","WMECO - Work Order # for Supplemental Review","WMECO - $ Estimate for Supplemental Review","WMECO - $ Actuals for Supplemental Review","WMECO - Date WMECO executed Supplemental Review Agreement","Date \"20 Days\" Supplemental Review Begun","Date \"20 Days\" Supplemental Review Complete","Number workdays of \"clock\" stoppage by Customer   ","Date \"20 Day\" Standard Process Initial Review Begun","Date \"20 Day\"  Standard Process Initial Review Complete","Number workdays of \"clock\" stoppage by Customer    ","WMECO - Work Order # for Impact Study","WMECO - $ Estimate for Impact Study","WMECO - $ Actuals for Impact Study","WMECO - Date WMECO executed Impact Study Agreement","Date \"55 Days\" Impact Study Begun","Date \"55 Days\"  Impact Study Sent","Number workdays of \"clock\" stoppage by Customer     ","WMECO - Work Order # for Detailed Study","WMECO - $ Estimate for Detailed Study","WMECO - $ Actuals for Detailed Study","WMECO - Date WMECO executed Detailed Study Agreement","Date Detailed \"30 Days\" Study Begun","Date \"30 Days\"  Detailed Study Sent","Number workdays of \"clock\" stoppage by Customer      ","WMECO - Total $ for Upgrade Estimate","WMECO - Construction Estimate","WMECO - CIAC Estimate","WMECO - $ Actuals for Construction without CIAC","Construction Commitment Date (negotiated)","Date Construction Begun (negotiated)","Date Construction Completed (negotiated)","Number workdays of \"clock\" stoppage by Customer       ","WITNESS TEST Work Order #","Date Witness Test Scheduled (part of 10 Day Completion)","Date Witness Test Completed (part of 10 Day Completion)","WMECO - $ Actuals for Witness Test","Requires Monthly Report to DOER","In Service Year","Send protection review reminder letter (1 yr notice from due date in column K)","Protection review required every 6 yrs from in-service date","Certified Relay Test Results RECEIVED DATE","Certified Relay Test Results APPROVED by Protection YES / NO","Yearly O&M maint billing Per IA","Delivery","Comments","Electric Customer Contact Name","Electric Customer Mailing Address","Electric Customer Mailing Town","Electric Customer Mailing State","Electric Customer Mailing Zip","Name","Street","Town","State","Zip","Phone","Fax","Y if include on monthly report to meter departments","Estimated Meter Need Date","Estimated Meter Install Date","Meter Engineering Review","Primary Meter Request Form Sent","CT/PT Ordered","Current Transformers","Voltage Transformers","Meter Ordered","Meter Voltage","Meter Type","Meter Phone Number","Company, CCC, Construction Work Order Number, Activity","Work Request","Y if include on monthly report to Dave Thomas / planners and Frank Vancini","Likelyhood of Being Built","Impact Study Status","Work Order written?","Long Lead Time Materials ordered?","Technician","Estimated Construction Start","Estimated Construction End","Estimated Generation ISD","Construction Description","Construction Dollars (does not include CIAC)","S/S, EM, Test","OH","UG","Trees","Meters","Project Status","ISO Notify 1 - 5 MW / ISO APP 5 + MW","QF - for yearly DPU 220 CMR reporting","FERC Jurisdic- tional ?","IA on File - for FERC Review   2-25-11","FERC Report Com/Ind & Sync & <1 MW","if *****, may not be in service","Date Meter requested"]
["Robert Mazer",null,"OTHER",null,null,"Completed",null,"6A1-2003",null,"R1","R","54952202059","170541000","888508262","303942004","100","Larkspur Dr",null,null,"Amherst","MA","01002","WMECO",{"$f":"LEFT(Y6,3)","v":"17K"},"17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-04-27",2.1120000000000001,{"$f":"AJ6*0.8","v":2.1120000000000001},2.64,"Class 1 (Solar / Wind)",null,2.4,2.4,2.4,"Solar",2003,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2003-08-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2003,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["John J. Czajkowski",null,null,null,null,"Completed",null,"6A2-2004",null,"R1","R","54290702042","433841003","888243692","893652003","133","Mount Warner Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",2.08,{"$f":"AJ7*0.8","v":2.08},2.6,"Class 1 (Solar / Wind)",null,2.1,2.1,2.1,"Solar",2004,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2004-06-04",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2004,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Christina Clarke",null,null,null,null,"Completed",null,"6A3-2004",null,"R1","R","54356602011","073741002","888508362","553552000","329","Pine St",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-30",1.8,{"$f":"AJ8*0.8","v":0},null,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2004,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2004-06-04",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2004,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Open Fields Foundation Inc",null,null,null,null,"Completed",null,"6A4-2004",null,"R1","R","54265171017","343621008","890471312","171712000","593","South Pleasant St",null,null,"Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","No Cap",null,null,"2010-01-25",2.1,{"$f":"AJ9*0.8","v":0},null,"Class 1 (Solar / Wind)",null,2.1,2.1,2.1,"Solar",2004,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2004-11-04",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2004,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Andrew Bellak",null,null,null,null,"Completed",null,"6A5-2004",null,"R1","R","54525091021","533731002","890662482","063732001","216","Lincoln Ave",null,null,"Amherst","MA","01002","WMECO","17K","17K4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-03",2.2999999999999998,{"$f":"AJ10*0.8","v":0},null,"Class 1 (Solar / Wind)",null,2.2999999999999998,2.2999999999999998,2.2999999999999998,"Solar",2004,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2005-06-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"removed - approved",null,null,"N.R.","N (4MW sync)","removed"]
["UMASS - Steam Plant",null,null,null,null,"Removed",null,"6A6-2004",null,"T2",null,"54548734086","372092009","058883271","634105006","360","Campus Center Way - Umass Campus",null,null,"Amherst","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","Steam Turbine","cogeneration facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,4000,4000,"Coal",2004,"n.r.","n.r.",null,"n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,"N/A",null,"2005-12-01",null,null,null,"no","WDGCG402",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005 - removed",null,null,null,null,null,"no export","removed 2008",null,null,null,null,null,"Ray Jackson","360 Campus Center Way","Amherst","MA","01002","413-545-0605","413-545-1450",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Robert Lynch","Riverland Farm - Scott Reed",null,null,null,"Completed",null,"6A6-2005",null,"G0","C","54352434088","310882009","891141102","582594005","195","River Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-03-12",2.85,null,null,"Class 1 (Solar / Wind)",null,2.85,2.85,2.85,"Solar",2005,"2005-08-24",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-09-06",null,"n/a","??",null,0,"n/a",null,null,null,"2006-04-13",null,null,null,"2008-02-26",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering","now Robert Lynch on electric account but Scott Reed still owns the place",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Neil Immerman",null,null,null,null,"Completed",null,"6A7-2005",null,"R1","R","54399861020","994521001","890834942","536512001","37","Hillcrest Pl",null,null,"Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-30",2.7360000000000002,{"$f":"AJ13*0.8","v":2.7360000000000002},3.42,"Class 1 (Solar / Wind)",null,3.42,3.42,3.42,"Solar",2005,"2005-09-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-09-19",null,"n/a",null,null,0,"n/a",null,null,null,"2005-10-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled"]
["Indian River Hydro",null,"STD",null,null,"Cancelled",null,"6A7H-2005",null,null,null,null,null,null,null,null,"Station Rd",null,null,"Russell","MA","01071","WMECO","19J","19J1","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,"300 + 400","Hydro",2005,"2005-08-02",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,"N/A",null,null,null,null,null,"no","WDGHY501",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - generator","cancelled per customer request",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Y","N (9MW sync)"]
["UMASS - Central Heating Plant (See 6A54-2008)","UMBA",null,null,null,"Completed",null,"6A8-2005",null,"T2",null,"54548734086","013092007","058883131","634105006","200","Mullins Way - Umass Campus",null,null,"Hadley","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","Gas Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,null,9000,9000,"Natural Gas/Fuel Oil",2007,"04/11/2007 *",null,null,"2007-10-31",{"$f":"IF(AU15=0,NETWORKDAYS(AR15,$A$4),NETWORKDAYS(AR15,AU15))","v":{"$error":"#VALUE!"}},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-10-31",null,"Yes","2007-10-31",null,"$5M / $5M","2015-04-01",null,"Yes",null,"2009-01-29",null,null,null,"no","WDGCG502",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"n/a - will not export (export during 1st testing phase only)","* original application dated 2005, revised application dated 4/11/07.   **yes - received insurance 04/25/08 - sent Con an email - contact correct - tariff n.r.",null,null,null,null,null,"Umass Building Authority           Attn:  David MacKenzie - Executive Director","333 South Street,   4th Floor","Shrewsbury","MA","01545",7744557250,7744557255,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved",null,null,"new SGIA - Y","cancelled 400 + 400 = Yes","cancelled","Y"]
["Woronoco Hydro LLC",null,"STD",null,null,"Cancelled",null,"6A8H-2005",null,"G0",null,"54904534005","939882006","036020261","625694008",null,"Bridge St",null,null,"Woronoco (Russell)","MA","01071","WMECO","19J","19J2","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,null,"1900 + 400 + 400","Hydro",2005,"2005-07-29",null,null,"2005-08-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-10-19",null,"Cancelled - Yes",null,null,"n/a","n/a",null,"N/A - done 5/12/2010",null,"2007-04-09",null,null,null,"no","WDGHY502",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - generator selling energy","was market participant  (cancld - replaced w/ new SGIA - 2007)  disconnect switch on pole   (replaced by ISO-2011-2 and cancld with new SGIA 1/6/2012)",null,null,null,null,null,"Attn:  Peter Clark","823 Bay Rd,   PO Box 149","Hamilton","MA","01936","978-468-3999","978-468-1210",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Gabor Lukacs",null,null,null,null,"Completed",null,"6A9-2005",null,"R1","R","54962191003","374731004","890690812","306632009","44","Beston St",null,null,"Amherst","MA","01002","WMECO","17K","17K4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-29",0.84,{"$f":"AJ17*0.8","v":0.84000000000000008},1.05,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2005,"2005-09-12",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-09-19",null,"n/a",null,null,0,"n/a",null,null,null,"2005-11-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Brookfield Farm (Biodynamic Farmland Conservation Inc) (see 6A173-2011 addition)",null,null,null,null,"Completed",null,"6A10-2005",null,"G0","C","54548791094","096241005","890645322","987542007","24","Hulst Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap",null,null,"see 6A173-2011",3.024,{"$f":"AJ18*0.8","v":3.024},3.78,"Class 1 (Solar / Wind)",null,null,3.78,3.78,"Solar",2005,"2005-10-04",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-10-14",null,"n/a",null,null,0,"n/a",null,null,null,"2005-10-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering","installed and inspected prior to approval given to install",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled"]
["Jef Sharp",null,null,null,null,"Cancelled",null,"6A10A-2005",null,null,null,null,null,null,null,"233B","Stanley St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,2,"Solar",2005,"2005-09-19",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-09-19",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cancelled per customer request",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","removed"]
["UMASS - Knowles Engineering Bldg",null,null,null,null,"Removed",null,"6A11-2005",null,"T2",null,"54548734086","372092009","058883271","634105006","151","Holdsworth Way",null,null,"Amherst","MA","01003","WMECO","18G","18G1 & 18G2"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"N/A",null,null,7.5,7.5,"Solar",2005,"2005-11-12",null,null,"n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-11-14",null,"n/a",null,null,"n/a","n/a",null,null,null,"2005-12-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005 - removed",null,null,null,null,null,"no export","removed 12/20/10 - NO EXPORT of PV - would be Class 1 (solar/wind)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Kristin Neville",null,"SIMP",null,null,"Completed",null,"6A12-2006",null,"R1","R","54436502041","364641002","890835012","230352002","18","Tucker Rd",null,null,"Huntington","MA","01050","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-02-04",1.52,{"$f":"AJ21*0.8","v":1.52},1.9,"Class 1 (Solar / Wind)",null,2,2,2,"Solar",2006,"2006-01-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-01-05",null,"n/a",null,null,0,"n/a",null,null,null,"2006-03-23",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Tawnya Tiskus",null,"SIMP",null,null,"Completed",null,"6A13-2006",null,"R1","R","54199391046","148931007","890835432","642042003","94","West St",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-05-02",1.8240000000000001,1.8239999999999998,2.2799999999999998,"Class 1 (Solar / Wind)",null,2.5,2.5,2.5,"Solar",2006,"2006-01-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-01-05",null,"n/a",null,null,0,"n/a",null,null,null,"2006-05-11",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Kuhn Riddle Architects",null,null,null,null,"Completed",null,"6A14-2006",null,"G0","C","54526434055","171982006","891141252","802694003","28","Amity St","Suite","2A","Amherst","MA","01002","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2009-12-28",4.2560000000000002,4.2560000000000002,5.32,"Class 1 (Solar / Wind)",null,5.32,5.32,5.32,"Solar",2006,"2006-01-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-02-16",null,"n/a",null,null,0,"n/a",null,null,null,"2006-10-31",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering","lock box with key near entrance for access to building and disconnect switch, 1 phase inverter on three phase service fed from 3 phase bank",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Jeffrey Sharp",null,null,null,null,"Completed",null,"6A15-2006",null,"R1","R","54785334053","126782004","890835302","143394004","276","Strong St",null,null,"Amherst","MA","01002","WMECO","17K","17K7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-03",1.8240000000000001,1.8239999999999998,2.2799999999999998,"Class 1 (Solar / Wind)",null,2,2,2,"Solar",2006,"2006-01-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-01-06",null,"n/a",null,null,0,"n/a",null,null,null,"2006-09-21",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Aaron Hayden",null,"SIMP",null,null,"Completed",null,"6A16-2006",null,"R1","R","54273091090","011831001","890835252","543732008","1491","South East St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-08",3.3,0,null,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2006,"2006-01-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-01-26",null,"n/a",null,null,0,"n/a",null,null,null,"2006-12-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Richard & Jane Wilkie",null,null,null,null,"Completed",null,"6A17-2006",null,"R1","R","54998034052","909682003","890807642","570094004","1660","South East St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",2.5,0,null,"Class 1 (Solar / Wind)",null,2.5,2.5,2.5,"Solar",2006,"2006-01-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-01-26",null,"n/a",null,null,0,"n/a",null,null,null,"2006-01-26",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Marvin Davenport",null,null,null,null,"Completed",null,"6A18-2006",null,"R1","R","54403502065","624741006","890835232","533252004","7","The Jog",null,null,"West Hatfield","MA","01039","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",2.5,0,null,"Class 1 (Solar / Wind)",null,2.5,2.5,2.5,"Solar",2006,"2006-02-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-03-06",null,"n/a",null,null,0,"n/a",null,null,null,"2006-07-21",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Thomas Ewing",null,null,null,null,"Completed",null,"6A19-2006",null,"R1","R","54622534063","145882004","891114132","790794005","46","Number Six Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-16",4.4800000000000004,4.4799999999999995,5.6,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2006,"2006-04-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-04-25",null,"n/a",null,null,0,"n/a",null,null,null,"2007-01-31",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Thomas Hartman (see 6A177-2011 addition)",null,null,null,null,"Completed",null,"6A20-2006",null,"R1","R","54452661010","287321001","890835412","699112000","4","Amherst Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",1.8240000000000001,1.8239999999999998,2.2799999999999998,"Class 1 (Solar / Wind)",null,null,2,2,"Solar",2006,"2006-04-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-04-25",null,"n/a",null,null,0,"n/a",null,null,null,"2006-05-24",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Joan Milan & David King (see 6A1154-2015)",null,null,null,null,"Completed",null,"6A22A-2006",null,"R1","R","54624481073","127331004","890835462","630132006","24","Sheerman Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-26",3.68,0,null,"Class 1 (Solar / Wind)",null,null,3.68,3.68,"Solar",2006,"2006-07-17",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-07-17",null,"n/a",null,null,0,"n/a",null,null,null,"2006-09-29",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled"]
["Richard Chedester",null,"SIMP",null,null,"Cancelled",null,"6A23-2006",null,"R1","R","54550481063","983303000","891711362","806822004","260","Haydenville Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Wind Turbine","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,1,"Wind",2006,"2006-04-25",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-05-16",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cancelled per customer request",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Y","500 = Yes"]
["Amherst College",null,"STD",null,null,"Completed",null,"6A24-2006",null,"T2",null,"54421791013","036141004","041503131 + 041502911","467342009",null,"College St",null,null,"Amherst","MA","01002","WMECO","17K","17K4, (17K5 N.O.)"," ","non-PTF","Gas Turbine & Steam Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,1750,1750,"1250 + 500","Natural Gas / Diesel",2006,"2006-05-11",null,null,"2007-08-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-09-25",null,"Yes",null,null,"$2M / $5M","2015-07-01",null,"Yes - written",null,"2007-12-04",null,null,null,"no","WDGCG601",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"no export",null,null,null,null,null,null,"Attn:  Aaron Hayden","Amherst College Physical Plant  PO Box 5000  (6 East Drive)","Amherst","MA","01002-5000",4135422644,4135425789,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled"]
["Nina Weyl",null,"SIMP",null,null,"Cancelled",null,"6A25-2006",null,"R1","R","54157481003","714621004","887899012","559032006","101","High St",null,null,"Amherst","MA","01002","WMECO","17K","17K3"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,3.45,"Solar",2006,"2006-05-15",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-05-15",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","(Cancelled per cust request)  5/11/07 found out from solar installer that customer cancelled project",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Kent Faerber",null,"SIMP",null,null,"Completed",null,"6A26-2006",null,"R1","R","54653534008","072882009","890835572","743594009","481","Station Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",2.88,{"$f":"AJ34*0.8","v":2.8800000000000003},3.6,"Class 1 (Solar / Wind)",null,3.6,3.6,3.6,"Solar",2006,"2006-05-15",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-05-15",null,"n/a",null,null,0,"n/a",null,null,null,"2006-10-13",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Joshua Goldstein (was Andra Rose)",null,"SIMP",null,null,"Removed","2015-10-02","6A27-2006",null,"R1","R","54585027006","928741007","890835652","615552009","16","Poets Corner Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-02",3.45,0,null,"Class 1 (Solar / Wind)",null,3.45,3.45,3.45,"Solar",2006,"2006-06-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-06-28",null,"n/a",null,null,0,"n/a",null,null,null,"2006-11-30",null,null,null,"2015-05-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006 - replaced",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Christopher Smith (Hatfield Printing & Publishing)",null,null,null,null,"Completed",null,"6A28-2006",null,"R1","R","54631791001","399041002","890326842","736652008","19","Prospect St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-29",14.4,14.4,18,"Class 1 (Solar / Wind)",null,18,18,18,"Solar",2006,"2006-07-31",null,null,"2006-08-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-08-04",null,"n/a - has IA under old rules",null,null,0,"n/a",null,null,null,"2006-08-25",null,null,null,"no","WDGSL602",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering","can open C/O's on pole. (3) 6 kW, single phase inverters on 3 ph service.  Per CADMUS - 3 ph system - NO CAP.",null,null,null,null,null,"Christopher Smith","19 Prospect St","Hatfield","MA","01038","413-247-5362",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Ellen & Robert Meeropol (see 6A539-2014)",null,null,null,null,"Completed",null,"6A30-2006",null,"R1","R","54501302061","128441002","890834872","662152005","79","Plain St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-12",2.5,0,null,"Class 1 (Solar / Wind)",null,null,2.5,2.5,"Solar",2006,"2006-09-05",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-09-12",null,"n/a",null,null,0,"n/a",null,null,null,"2006-12-26",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Roger Webb (see 6A295-2012 addition)",null,null,null,null,"Completed",null,"6A31-2006",null,"R1","R","54164734006","025982007","891113962","251994008","293","Potwine Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",2.88,2.8800000000000003,3.6,"Class 1 (Solar / Wind)",null,null,4,4,"Solar",2006,"2006-09-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-09-25",null,"n/a",null,null,0,"n/a",null,null,null,"2007-03-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering","new construction",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Lee Edwards",null,null,null,null,"Completed",null,"6A32-2006",null,"R3","R","54355791039","169141000","891140442","877242002","5","Wildwood Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-07",4.1280000000000001,4.1280000000000001,5.16,"Class 1 (Solar / Wind)",null,5.16,5.16,5.16,"Solar",2006,"2006-10-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-10-20",null,"n/a",null,null,0,"n/a",null,null,null,"2006-12-31",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Food Bank of Western Massachusetts",null,null,null,null,"Completed",null,"6A33-2006",null,"G0","C","54405734039","697982000","891169972","414894001","97","North Hatfield Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2010-04-04",24.192,24.192,30.24,"Class 1 (Solar / Wind)",null,25.623000000000001,25.623000000000001,25.623000000000001,"Solar",2006,"2006-11-09",null,null,"2006-11-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-01-22",null,"Yes",null,null,0,"n/a",null,null,null,"2007-01-22",null,null,null,"no","WDGSL603",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering","external switch",null,null,null,null,null,"Asa deRoode","97 North Hatfield Rd","Hatfield","MA","01038","413-247-9738","413-247-9577",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Daniel & Patricia Campbell",null,null,null,null,"Completed",null,"6A34-2006",null,"R1","R","54338861016","351521007","891140852","364412000","96","Prospect St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-31",4.3,0,null,"Class 1 (Solar / Wind)",null,4.3,4.3,4.3,"Solar",2006,"2006-11-01",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-11-13",null,"n/a",null,null,0,"n/a",null,null,null,"2006-12-18",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Stiebel Eltron Inc",null,null,null,null,"Completed",null,"6A35-2006",null,"G0","C","54177502069","806641004","891169992","883452005","17","West St",null,null,"West Hatfield","MA","01088","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2011-03-07",4.5,0,null,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2006,"2006-11-17",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-11-21",null,"n/a - has IA under old rules",null,null,0,"n/a",null,null,null,"2007-03-29",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering","can open C/O's on pole, two single phase inverters on three phase service",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Flora Chamlin (see 6A237-2011 additon)",null,null,null,null,"Completed",null,"6A36-2006",null,"R1","R","54040271033","093621004","891140452","750812001","35","Westbrook Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"see 6A237-2011",2.7360000000000002,2.7360000000000002,3.42,"Class 1 (Solar / Wind)",null,null,4,4,"Solar",2006,"2006-11-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-11-28",null,"n/a",null,null,0,"n/a",null,null,null,"2007-03-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Rolf Nelson",null,null,null,null,"Completed",null,"6A37-2006",null,"R1","R","54029602075","464841006","891140562","216552005","40","Hop Brook Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-03-16",3.84,3.84,4.8,"Class 1 (Solar / Wind)",null,4.8,4.8,4.8,"Solar",2006,"2006-12-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-12-21",null,"n/a",null,null,0,"n/a",null,null,null,"2007-04-03",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Lisa Gawle",null,null,null,null,"Completed",null,"6A38-2007",null,"R1","R","54442334082","469782003","891146852","536494007","36","Holly Circle",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-28",3.63,0,null,"Class 1 (Solar / Wind)",null,3.63,3.63,3.63,"Solar",2007,"2007-01-02",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-01-02",null,"n/a",null,null,0,"n/a",null,null,null,"2007-01-02",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Annettte Wysocki (was Fred Cheyette)",null,null,null,null,"Completed",null,"6A39-2007",null,"R1","R","54451637086","041303008","891408202","044232004","119","Shutesbury Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-02",3.6480000000000001,3.6479999999999997,4.5599999999999996,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2007,"2007-07-16",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-07-16",null,"n/a",null,null,0,"n/a",null,null,null,"2007-12-07",null,null,null,"2015-12-02",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["David Arnold & Elizabeth Harvey (see 6A557-2014",null,null,null,null,"Completed",null,"6A40-2007",null,"R1","R","54562602011","480741002","891378122","108452000","35","Hop Brook Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",2.8,2.8000000000000003,3.5,"Class 1 (Solar / Wind)",null,null,4,4,"Solar",2007,"2007-08-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-08-28",null,"n/a",null,null,0,"n/a",null,null,null,"2007-10-05",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Tom Baker",null,"SIMP",null,null,"Completed",null,"6A41-2007",null,"R1","R","54530502046","416641007","891146722","967352003","137","Shutesbury Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-18",3.36,3.3600000000000003,4.2,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2007,"2007-08-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-08-28",null,"n/a",null,null,0,"n/a",null,null,null,"2007-10-22",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["William Obear",null,"SIMP",null,null,"Completed",null,"6A42-2007",null,"R1","R","54742791007","232141008","891378322","010342008","134","Webber Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",3.74,0,null,"Class 1 (Solar / Wind)",null,3.74,3.74,3.74,"Solar",2007,"2007-09-25",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-09-26",null,"n/a",null,null,0,"n/a",null,null,null,"2007-10-05",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Daniel Giat",null,"SIMP",null,null,"Completed",null,"6A43-2007",null,"R1","R","54593961071","726421002","891146662","240612006","98","Arnold Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-08",5,0,null,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2007,"2007-10-22",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-10-22",null,"n/a",null,null,0,"n/a",null,null,null,"2008-01-07",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Robert Fydenkevez",null,"SIMP",null,null,"Completed",null,"6A44-2007",null,"R1","R","54191491000","568931001","891378522","340042008","120","Christian Ln",null,null,"Whately","MA","01373","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-15",2.88,2.8800000000000003,3.6,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2007,"2007-11-06",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2007-11-06",null,"n/a",null,null,0,"n/a",null,null,null,"2008-04-30",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled - new application submitted"]
["Constance & Herbert Futter (new 6A48-2008)",null,null,null,null,"Cancelled",null,"6A45-2007",null,"R1","R","54772271003","683621004","891408292","490812008","7","Claverick Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,9.8000000000000007,"Solar",2007,"2007-12-13",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Kosmo Solar specified a 3 phase inverter for a single phase service.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Bruce Coldham (was Colham & Hartman Architects LLC)",null,null,null,null,"Completed",null,"6A46-2008",null,"R1","R","54277706073","632741000","891806182","760552001","155","Pine St",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-06-18",3.08,{"$f":"AJ53*0.8","v":3.08},3.85,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2008,"2008-01-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-01-15",null,"n/a",null,null,0,"n/a",null,null,null,"2008-03-05",null,null,null,"2012-06-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering","Single phase svc and gen.  Under 10 kW. NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Richard Seelig",null,null,null,null,"Completed",null,"6A47-2008",null,"R1","R","54354702003","473741004","891408072","165552009","39","Buffam Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-17",0.99199999999999999,{"$f":"AJ54*0.8","v":0.99199999999999999},1.24,"Class 1 (Solar / Wind)",null,1.24,1.24,1.24,"Solar",2008,"2008-01-23",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-01-23",null,"n/a",null,null,0,"n/a",null,null,null,"2008-03-11",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Patricia Lomeli ( was Constance & Herbert Futter)",null,null,null,null,"Completed",null,"6A48-2008",null,"R1","R","54372886036","683621004","891408292","490812008","7","Claverick Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-16",9.8000000000000007,{"$f":"AJ55*0.8","v":0},null,"Class 1 (Solar / Wind)",null,9.8000000000000007,9.8000000000000007,9.8000000000000007,"Solar",2008,"2008-02-15",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-02-19",null,"n/a",null,null,0,"n/a",null,null,null,"2008-03-13",null,null,null,"2014-06-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering","Solar Wrights (Kosmo Solar's new name) started installation prior to WMECO receiving application.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled - new application submitted"]
["Paul Newlin (new 6A52-2008)",null,null,null,null,"Cancelled",null,"6A49-2008",null,"R3","R","54782725055","672621008","891408282","690812008","148","Conway Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,3.7,"Solar",2008,"2008-02-20",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-02-21",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","5/1/08 installer said customer cancelled this project",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Natalia Bouyea (was Timothy Chilson)",null,null,null,null,"Completed",null,"6A50-2008",null,"R1","R","54653327098","052321004","891408332","235312006","19","Keddy St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"MIMO - needed",3,null,null,"N/A because no Schedule Z on file",null,3,3,3,"Solar",2008,"2008-02-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-02-26",null,"n/a",null,null,0,"n/a",null,null,null,"2008-05-14",null,null,null,"MIMO - needed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Jonathan Child (was Elizabeth Rosenberg) (see 6A166-2011 addition)",null,null,null,null,"Completed",null,"6A51-2008",null,"R1","R","54404976011","664753006","891408342","443332000","135","East St",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"see 6A166-2011",2.96,{"$f":"AJ58*0.8","v":2.9600000000000004},3.7,"Class 1 (Solar / Wind)",null,null,4,4,"Solar",2008,"2008-03-12",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-03-12",null,null,null,null,0,"n/a",null,null,null,"2008-09-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled - new application submitted"]
["Paul Newlin (new 6A60-2008)",null,null,null,null,"Cancelled",null,"6A52-2008",null,"R3","R","54782725055","672621008","891408282","690812008","148","Conway Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,3.7,"Solar",2008,"2008-04-04",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-04-04",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","6/16/08 installer changing inverters/solar panels, cancelled this project",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Kathryn Perry",null,null,null,null,"Completed",null,"6A53-2008",null,"R2","R","54985734078","737982009","891479552","352005006","24","Stanley St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-03",2.5,{"$f":"AJ60*0.8","v":0},null,"Class 1 (Solar / Wind)",null,2.5,2.5,2.5,"Solar",2008,"2008-04-08",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-04-08",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-14",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Y","N (4MW sync)",null,"2008-04-08"]
["UMASS 4 MW - 4 MW at CHP w/UMBA 9 MW",null,"STD",null,null,"Completed",null,"6A54-2008",null,"T2",null,"54548734086","013092007","004100100","634105006","200","Mullins Way - Umass Campus",null,null,"Hadley","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","Gas Turbine & Steam Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,null,4000,"4,000 kW add (13,000 kW total)","Natural Gas/Fuel Oil",2008,"2008-01-31",null,null,"2009-09-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-29",null,"Yes",null,null,"see 6A104-2009 combined insurance","see 6A104-2009",null,"Yes",null,"2009-04-16",null,null,null,"no","WDGCG801",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"no export",null,null,null,null,null,null,"Attn:  Raymond Jackson - Assist. Dir Utilities","Physical Plant                         360 Campus Center Way","Amherst","MA","01003-9248","413-545-0605",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"n/a"]
["Janie Morose (was Ann Latham)",null,null,null,null,"Completed",null,"6A55-2008",null,"R1","R","54661517029","885263008","891479562","272452005","65","Edwards Rd",null,null,"Westhampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-03",3.456,{"$f":"AJ62*0.8","v":3.4560000000000004},4.32,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2008,"2008-04-24",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-04-25",null,"n/a",null,null,0,"n/a",null,null,null,"2008-06-10",null,null,null,"2015-06-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Sarah Rossmassler",null,null,null,null,"Completed",null,"6A56-2008",null,"R1","R","54432091098","668731009","891479822","412732008","100","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-26",1.056,{"$f":"AJ63*0.8","v":1.056},1.32,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2008,"2008-05-12",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-05-13",null,"n/a",null,null,0,"n/a",null,null,null,"2008-06-10",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - needed",null,null,"N.R.","N","cancelled"]
["Indian River Hydro",null,"STD",null,null,"Cancelled",null,"6A56H-2008",null,null,null,null,null,null,null,null,"Station Rd",null,null,"Russell","MA","01071","WMECO","19J","19J1","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,"700 + 700 not MA tariff","Hydro",2008,"2008-05-12",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,null,null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - generator","cancld -cust needs to file with Russell or ISO  [Not MA tariff (19J1)]",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Stanley Brown",null,null,null,null,"Completed",null,"6A57-2008",null,"R1","R","54678602012","343841003","891408362","016552000","14","Wampanoag Dr",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",5.0999999999999996,{"$f":"AJ65*0.8","v":0},null,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2008,"2008-05-19",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-05-20",null,"n/a",null,null,0,"n/a",null,null,null,"2008-07-08",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["John & Elizabeth Finn",null,null,null,null,"Completed",null,"6A58-2008",null,"R3","R","54626181002","865231003","891480322","581622009","34","Carriage Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-06-20",3.84,3.84,4.8,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2008,"2008-06-02",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-06-02",null,"n/a",null,null,0,"n/a",null,null,null,"2008-07-21",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Daniel Regish",null,null,null,null,"Completed",null,"6A59-2008",null,"R3","R","54194771051","418921002","891480222","011222004","16","Newton Ln",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-05-03",5,0,null,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2008,"2008-06-10",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-06-10",null,"n/a",null,null,0,"n/a",null,null,null,"2008-07-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Paul Newlin",null,null,null,null,"Completed",null,"6A60-2008",null,"R3","R","54782725055","672621008","891408282","690812008","148","Conway Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-29",3.85,0,null,"Class 1 (Solar / Wind)",null,3.85,3.85,3.85,"Solar",2008,"2008-06-16",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-06-17",null,"n/a",null,null,0,"n/a",null,null,null,"2008-06-24",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Ashlee Cancio-Bello (was Pioneer Valley Habitat for Humanity)",null,null,null,null,"Completed",null,"6A61-2008",null,"R1","R","54704494038","474292003","891758452","472405008","18","Stanley St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-01",2.016,2.016,2.52,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2008,"2008-06-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-06-26",null,"n/a",null,null,0,"n/a",null,null,null,"2008-11-17",null,null,null,"2010-04-06",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-07-30"]
["Larry Kuttner",null,null,null,null,"Completed",null,"6A62-2008",null,"R1","R","54959791096","955241007","891759612","388542007","37","Laurel Mt Rd",null,null,"Whately","MA","01093","WMECO",{"$f":"LEFT(Y70,3)","v":"18G"},"18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-25",2.8,0,null,"Class 1 (Solar / Wind)",null,2.8,2.8,2.8,"Solar",2008,"2008-07-16",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-07-16",null,"n/a",null,null,0,"n/a",null,null,null,"2008-11-04",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-09"]
["Nancy Talanian",null,null,null,null,"Completed",null,"6A63-2008",null,"R1","R","54241481035","817431006","891728902","706032001","19","Poplar Hill Rd",null,null,"Whately","MA","01039","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-28",2.88,2.8800000000000003,3.6,"Class 1 (Solar / Wind)",null,3,3,3,"Solar",2008,"2008-08-13",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-08-14",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-06",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering","50 kVA xfr on 2B/6 feeds 17, 17R, 19 & 28 Poplar Hill and 176 Conway Rd per field check",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-08-14"]
["Noble View Camp (Appalachian Mountain Club)",null,null,null,null,"Completed",null,"6A64-2008",null,"G0","C","54605434018","265782002","891256632","883305009","635","South Quarter Rd",null,null,"Russell","MA","01097","WMECO","19J","19J2","PTF"," ","Photovoltaic","Inverter","Private",null,null,"2010-02-12",8.2080000000000002,8.2080000000000002,10.26,"Class 1 (Solar / Wind)",null,12,10,10,"Solar",2008,"2008-08-14",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-08-14",null,"n/a",null,null,0,"n/a",null,null,null,"2010-02-05",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","Actual size is 12 kW AC (2 x 6).  12 > 10, on single phase svc.  PRIVATE.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-08-14"]
["Marcy A Sala",null,null,null,null,"Completed",null,"6A65-2008",null,"R1","R","54608402020","287641001","891759372","799352001","161","Pine St","Unit  ","E","Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-03",3.2,0,null,"Class 1 (Solar / Wind)",null,3.2,3.2,3.2,"Solar",2008,"2008-08-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-08-22",null,"n/a",null,null,0,"n/a",null,null,null,"2008-12-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-08-22"]
["Steven R Dunn",null,null,null,null,"Completed",null,"6A66-2008",null,"R1","R","54119402022","849641003","891759642","021452001","161","Pine St","Unit  ","A","Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-25",2.9,0,null,"Class 1 (Solar / Wind)",null,2.9,2.9,2.9,"Solar",2008,"2008-08-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-08-22",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-16",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-08-22"]
["Kay Klippel",null,null,null,null,"Completed",null,"6A67-2008",null,"R1","R","54037381050","792431001","891729292","143032003","95","Haydenville Rd",null,null,"Whately","MA","01039","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-18",4.3680000000000003,4.3680000000000003,5.46,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2008,"2008-08-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-02",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-05",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-02"]
["David Kastor",null,null,null,null,"Completed",null,"6A68-2008",null,"R1","R","54787502004","229641005","891759512","273352009","161","Pine St","Unit  ","D","Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-16",3.3,0,null,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2008,"2008-09-10",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-11",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-16",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-10"]
["Peter & Kate Lamdin",null,null,null,null,"Completed",null,"6A69-2008",null,"R1","R","54219861093","098421004","891758532","232612007","24","Cook Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-21",3.36,0,null,"Class 1 (Solar / Wind)",null,3.36,3.36,3.36,"Solar",2008,"2008-09-08",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-09",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-07",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-08"]
["David Mastroianni",null,null,null,null,"Completed",null,"6A70-2008",null,"R3","R","54121661094","417321005","891805592","130312008","39","Tracy Circle",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-03",3.84,3.84,4.8,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2008,"2008-09-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-10",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-09",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-09"]
["Nicholas Jones",null,null,null,null,"Completed",null,"6A71-2008",null,"R1","R","54145481081","005331002","891806842","278032006","175","Chestnut Plain Rd","Floor",1,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",3.36,3.3600000000000003,4.2,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2008,"2008-09-22",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-23",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-06",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-23"]
["Greg Howe (was Phil Smith)",null,null,null,null,"Completed",null,"6A72-2008",null,"R1","R","54878275023","708331004","891759822","349032001","9","Briggs St","Floor",1,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"MIMO - needed",5,0,null,"N/A because no Schedule Z on file",null,5,5,5,"Solar",2008,"2008-09-23",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-23",null,"n/a",null,null,0,"n/a",null,null,null,"2008-10-27",null,null,null,"MIMO - needed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-23"]
["Mark Gelotte",null,null,null,null,"Completed",null,"6A73-2008",null,"R1","R","54362391054","429931005","891758032","441832004","70","Elm St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",3.024,3.024,3.78,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2008,"2008-10-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-10-09",null,"n/a",null,null,0,"n/a",null,null,null,"2009-01-09",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-10-09"]
["Hampshire College - Liebling Center",null,null,null,null,"Completed",null,"6A74-2008",null,"T2","C","54917561086","538221007","000010940","082212006","893","West St",null,null,"Amherst","MA","01002","WMECO","19B","19B16","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"no export",0,null,null,"No Export",null,5.4,5.4,5.4,"Solar",2008,"2008-12-11",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-12-11",null,"n/a",null,null,0,"n/a",null,null,null,"2009-04-14",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"n/a - not expected to export",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"n/a"]
["Rebecca Jones",null,null,null,null,"Completed",null,"6A75-2008",null,"R1","R","54419381025","707431006","891808212","084922000","185","Chestnut Plain Rd",null,null,"Whately","MA","01093","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-28",3.9,{"$f":"AJ83*0.8","v":0},null,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2008,"2008-12-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-12-19",null,"n/a",null,null,0,"n/a",null,null,null,"2009-05-04",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-12-19"]
["James David Marley",null,null,null,null,"Completed",null,"6A76-2008",null,"G2","C","54411002033","811113005","891725642","660742001","100","University Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2009-12-09",65.52,65.52000000000001,81.900000000000006,"Class 2","now net metered 06/08/2009",82,82,82,"Solar",2008,"2008-12-23",null,null,"2009-02-13",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-02-17",null,"Yes",null,null,"$500K / $500K","2014-07-23",null,"No",null,"2009-06-08",null,null,"2009-05-01","no","WDGSL805",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,"c/o Diversified Construction","100 University Drive","Amherst","MA","01002",4135492900,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-02-18"]
["John Knox",null,"SIMP",null,null,"Completed",null,"6A77-2009",null,"R1","R","54485781017","628531008","891759652","496332000","8","Searle Rd",null,null,"Huntington","MA","01050","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-12",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-03-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-03-09",null,"n/a",null,null,0,"n/a",null,null,null,"2009-04-28",null,null,"06/2009","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-03-09"]
["Eric Decker",null,"SIMP",null,null,"Completed",null,"6A78-2009",null,"R1","R","54967771064","705031005","891806402","484322005","18","Russell St",null,null,"Sunderland","MA","01375","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-28",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-04-07",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-04-07",null,"n/a",null,null,0,"n/a",null,null,null,"2009-06-11",null,null,"2009-06-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-04-07"]
["Peter Acker",null,"SIMP",null,null,"Completed",null,"6A79-2009",null,"R1","R","54990602096","106741007","890690682","938552008","138","Harkness Rd","Lot",5,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-26",3.28,0,null,"Class 1 (Solar / Wind)",null,3.28,3.28,3.28,"Solar",2009,"2009-05-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-05-26",null,"n/a",null,null,0,"n/a",null,null,null,"2009-07-30",null,null,"2009-07-08","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-05-26"]
["Allen Eccleston",null,null,null,null,"Completed",null,"6AF79-2008",null,"R1","R","54347502064","753741005","891407842","263452005","231","Bay Rd",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-29",2.52,2.52,3.15,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2008,"2008-06-19",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-06-19",null,"n/a",null,null,0,"n/a",null,null,null,"2008-07-30",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2008,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["R. Brooke Thomas (see 6A549-2014)",null,"SIMP",null,null,"Completed",null,"6A80-2009",null,"R1","R","54203481031","495331002","891758782","340922002","39","Long Hill Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",2.52,2.52,3.15,"Class 1 (Solar / Wind)",null,null,3.15,3.15,"Solar",2009,"2009-06-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-06-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-10-28",null,null,"2009-09-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-06-29"]
["Hitchcock Center Inc",null,"SIMP",null,null,"Completed",null,"6A81-2009",null,"G0","C","54574591012","992703001","891880592","851142000","525","South Pleasant St",null,null,"Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-25",0.57599999999999996,0.57599999999999996,0.72,"Class 1 (Solar / Wind)",null,0.72,0.72,0.72,"Solar",2009,"2009-06-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-06-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-09-15",null,null,"2009-07-06","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering","< 10 kW single phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-06-29"]
["New England Environmental, Inc.",null,"EXP",null,"Cindy","Completed",null,"6A82-2009",null,"G0","C","54473884047","903003006","891220802","890835002","15","Research Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2009-12-15",31.2,31.200000000000003,39,"Class 1 (Solar / Wind)",null,39,39,39,"Solar",2009,"2009-06-29",null,null,"2009-07-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-30",null,"Yes",null,null,0,"n/a","No",null,null,"2009-08-10",null,null,"08/2009","no","WDGSL902",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,357.29,"On line. New construction.",2009,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  Michael J. Marcus","15 Research Drive","Amherst","MA","01002",4132560202,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-30"]
["Michael April",null,"SIMP",null,null,"Completed",null,"6A83-2009",null,"R1","R","54947402053","271641004","891807702","591252004","120","Pulpit Hill Rd","Unit  ",1,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-27",2.7,0,null,"Class 1 (Solar / Wind)",null,2.7,2.7,2.7,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-30",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-14",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-30"]
["William Lyons Whitten",null,"SIMP",null,null,"Completed",null,"6A84-2009",null,"R1","R","54747402055","633741006","891864802","491252004","120","Pulpit Hill Rd","Unit  ",7,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-13",3.7,0,null,"Class 1 (Solar / Wind)",null,3.7,3.7,3.7,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-28",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-14",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-28"]
["Jerry Koch-Gonzalez",null,"SIMP",null,null,"Completed",null,"6A85-2009",null,"R1","R","54681502068","337641009","891863972","286352005","120","Pulpit Hill Rd","Unit  ",8,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-03-25",3.5,0,null,"Class 1 (Solar / Wind)",null,3.5,3.5,3.5,"Solar",2009,"2009-08-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-08-04",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-24",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-08-04"]
["Louis R Conover",null,"SIMP",null,null,"Completed",null,"6A86-2009",null,"R1","R","54728402090","918641001","891806102","691452008","120","Pulpit Hill Rd","Unit  ",9,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-10-10",4,0,null,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-14",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-29"]
["Amy Freed",null,"SIMP",null,null,"Completed",null,"6A87-2009",null,"R1","R","54200502011","021641002","891864782","024352009","120","Pulpit Hill Rd","Unit  ",19,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-04",2.8,0,null,"Class 1 (Solar / Wind)",null,2.8,2.8,2.8,"Solar",2009,"2009-08-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-08-04",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-20",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-08-04"]
["Diane Wiley",null,"SIMP",null,null,"Completed",null,"6A88-2009",null,"R1","R","54137502084","769641005","891864972","627452007","120","Pulpit Hill Rd","Unit  ",21,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-08",2.4,0,null,"Class 1 (Solar / Wind)",null,2.4,2.4,2.4,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-09-11",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-29"]
["Jana Lussier (was Robin Luberoff)",null,"SIMP",null,null,"Completed",null,"6A89-2009",null,"R1","R","54673606075","147641009","891863952","802452008","120","Pulpit Hill Rd","Unit  ",26,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-05-14",2.8,0,null,"Class 1 (Solar / Wind)",null,2.8,2.8,2.8,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-24",null,null,"2009-08-03","2012-05-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-29"]
["Karen Kowles",null,"SIMP",null,null,"Completed",null,"6A90-2009",null,"R2","R","54638402099","146641000","891807032","702452008","120","Pulpit Hill Rd","Unit  ",27,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-11",1.8,0,null,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2009,"2009-07-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-08-24",null,null,"2009-08-03","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled","2009-07-29"]
["Roger Bird",null,"EXP",null,"Cindy","Cancelled",null,"6A91-2009",null,null,null,null,null,null,null,"88","Shutesbury Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,13.8,13.8,13.8,"Solar",2009,"2009-07-28",null,null,"2009-09-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-09-17",null,"Yes",null,null,"n/a","n/a","Yes",null,null,null,null,null,"08/2009 or 09/2009","canc","WDGSL905",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1117.57,989,128.57,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Cust changed design, reapplied.","Cancelled","n/a","n/a",null,null,null,"net metering","cancelled per customer request 2/5/10",null,null,null,null,null,"Roger Bird","88 Shutesbury Road","Leverett","MA","01054",4135494959,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled"]
["Robert McGovern",null,"SIMP",null,null,"Cancelled",null,"6A92-2009",null,"R3","R","54658391073","672931004","885605122","454042006","53","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,5.04,"Solar",2009,"2009-08-11",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-08-14",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,"09/31/09","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Cancld 10-30-09 Michelle by phone",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-08-14"]
["Francis P Lepine","Sun Run","SIMP",null,null,"Completed",null,"6A93-2009",null,"R1","R","54507961068","594521009","887295652","076512005","14","Garfield Ave ",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",4.51,{"$f":"AJ102*0.8","v":0},null,"Class 1 (Solar / Wind)",null,4.51,4.51,4.51,"Solar",2009,"2009-08-20",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-08-21",null,"n/a","yes",null,0,"n/a",null,null,null,"2009-12-03",null,null,"2009-09-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-08-21"]
["Kirk Birrell",null,"SIMP",null,null,"Completed",null,"6A94-2009",null,"R1","R","54932702038","101841009","887901922","998452002","15","Montgomery Rd",null,null,"Huntington","MA","01050","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-04-06",5,{"$f":"AJ103*0.8","v":0},null,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2009,"2009-09-28",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-09-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-11-16",null,null,"2009-10-12","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-09-29"]
["James Harvey (see 6A456-2013)",null,"SIMP",null,null,"Completed",null,"6A95-2009",null,"R1","R","54293602025","094841006","883791542","390652001","293","River Dr",null,null,"Hadley","MA","01035","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-15",3.2,{"$f":"AJ104*0.8","v":3.2},4,"Class 1 (Solar / Wind)",null,null,3.9,3.9,"Solar",2009,"2009-09-29",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-09-29",null,"n/a",null,null,0,"n/a",null,null,null,"2009-12-04",null,null,"2009-11-20","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-09-29"]
[" Kim Mcgovern","Sun Run","SIMP",null,null,"Completed",null,"6A96-2009",null,"R3","R","54658391073","672931004","891864372","454042006","53","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-09",4.032,{"$f":"AJ105*0.8","v":4.032},5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-10-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-11-10",null,"n/a","yes",null,0,"n/a",null,null,null,"2010-01-05",null,null,"2009-11-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-11-10"]
["Gary O'Connor","Sun Run","SIMP",null,null,"Completed",null,"6A97-2009",null,"R1","R","54303602015","563841006","891759172","781552009","131","Former Rd",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-07",4.032,{"$f":"AJ106*0.8","v":4.032},5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-10-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-10-21",null,"n/a","2009-11-13",null,0,"n/a",null,null,null,"2009-12-09",null,null,"2009-11-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-10-29"]
["Alicia Hackerson",null,"SIMP",null,null,"Completed",null,"6A98-2009",null,"R3","R","54414102095","071541006","883963762","242052008","35","Church St",null,null,"Huntington","MA","01050","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-03-12",2.0499999999999998,null,null,"Class 1 (Solar / Wind)",null,2.0499999999999998,2.0499999999999998,2.0499999999999998,"Solar",2009,"2009-09-16",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-10-27",null,"n/a",null,null,0,"n/a",null,null,null,"2010-03-08",null,null,"2009-09-14","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-10-27"]
["James & Martha Hanner","Sun Run","SIMP",null,null,"Completed",null,"6A99-2009",null,"R1","R","54118002088","197341009","883910622","013942007","18","Alyssum Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-23",3.9,{"$f":"AJ108*0.8","v":0},null,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2009,"2009-10-27",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-10-28",null,"n/a","2009-12-23",null,0,"n/a",null,null,null,"2010-02-12",null,null,"2009-12-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["That's a Plenty Farm",null,"SIMP",null,null,"Completed",null,"6A100-2009",null,"G0","C","54905125084","548703002","891742742","439585008","36","Honey Pot Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-04-13",1.44,{"$f":"AJ109*0.8","v":1.4400000000000002},1.8,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2009,"2009-10-01",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-11-13",null,"n/a",null,null,0,"n/a",null,null,null,"2010-04-30",null,null,"2009-12-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","new construction. < 10 kW single phase.  NO CAP.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-04-14"]
["Patrick Zephyr","Sun Run","SIMP",null,null,"Completed",null,"6A101-2009",null,"R1","R","54026602094","062841005","891865202","845652008","281","North Valley Rd","Lot",7,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-05",4.032,{"$f":"AJ110*0.8","v":4.032},5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-11-19",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-11-24",null,"n/a","yes",null,0,"n/a",null,null,null,"2010-02-10",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-11-25"]
["Saloma Furlong",null,"SIMP",null,null,"Completed",null,"6A102-2009",null,"R1","R","54166574061","451821004","891697552","761912004","6","School St",null,null,"Sunderland","MA","01375","WMECO","18G","18G3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-18",2.3919999999999999,{"$f":"AJ111*0.8","v":2.3920000000000003},2.99,"Class 1 (Solar / Wind)",null,2.9,2.9,2.9,"Solar",2009,"2009-12-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-12-24",null,"n/a",null,null,0,"n/a",null,null,null,"2010-01-12",null,null,"2009-12-18","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-12-24"]
["Paul Tourville (was Daniel Dmuchovsky)","(was Sun Run)","SIMP",null,null,"Completed",null,"6A103-2009",null,"R1","R","54568047088","830031004","891865812","758322003","97","Main Rd",null,null,"Westhampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-02-08",4.032,{"$f":"AJ112*0.8","v":4.032},5.04,"Class 1 (Solar / Wind)",null,5.04,5.04,5.04,"Solar",2009,"2009-12-22",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-12-31",null,"n/a","yes",null,0,"n/a",null,null,null,"2010-04-07",null,null,"2010-01-22","2016-02-08",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Y",null,null,"2009-12-31"]
["UMASS 2 MW Turbine addition to 4 MW & UMBA 9 MW","UMBA","STD",null,"Cindy","Completed",null,"6A104-2009",null,"T2",null,"54548734086","013092007","004100100","634105006","200","Mullins Way - Umass Campus",null,null,"Hadley","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","Steam Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,15000,2000,"2,000 kW add (15,000 kW total)","Natural Gas/Fuel Oil",2009,"2009-12-30",null,null,"2010-02-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-02-22",null,"Yes","yes",null,"Combined amount          $5M / $5M","2015-05-01","Yes","Yes",null,"2011-03-01",null,null,"09/2010",null,"WDGCG001",2500,9697.58,{"$f":"CC113-CB113","v":7197.58},null,null,null,null,null,null,null,null,null,null,"WDGCG00A",55000,41166.57,"2010-04-02","2010-07-19",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2512.5500000000002,"On line.",2011,"needed","needed",null,null,"??","no export","This project has a Transmission Study work order = WDCGT001",null,null,null,null,null,"Attn:  Raymond Jackson - Assist. Dir Utilities","Physical Plant                         360 Campus Center Way","Amherst","MA","01003-9248","413-545-0605",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Amherst Housing (Town of Amherst)",null,"SIMP",null,null,"Completed",null,"6A105-2010",null,"G2","C","54361961022","376521003","889037782","927412000","33","Kellogg Ave","Ste",81,"Amherst","MA","01002","WMECO","17K","17K4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-10",13.2,{"$f":"AJ114*0.8","v":13.200000000000001},16.5,"Class 1 (Solar / Wind)",null,15,15,15,"Solar",2010,"2010-01-13",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-01-18",null,"n/a",null,null,0,"n/a",null,null,null,"2010-03-29",null,null,"2010-01-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","(Attn Donna Ceabteee) - Town of Amherst. < 25 kW three phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-01-18"]
["Peter K. Hepler",null,"SIMP",null,null,"Completed",null,"6A106-2010",null,"R1","R","54514661040","667321001","888825452","087212003","6","Quarry Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-01-02",4.4160000000000004,4.4159999999999995,5.52,"Class 1 (Solar / Wind)",null,5.52,5.52,5.52,"Solar",2010,"2010-02-05",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-02-08",null,"n/a",null,null,0,"n/a",null,null,null,"2010-05-14",null,null,"2010-05-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-02-08"]
["Roger Bird",null,"EXP",null,"Cindy","Completed",null,"6A107-2010",null,"R1","R","54477025043","734303000","890985332","223855004","88","Shutesbury Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2010-02-08",8.7360000000000007,8.7360000000000007,10.92,"Class 1 (Solar / Wind)",null,{"$f":"9.995+3.8","v":13.794999999999998},{"$f":"9.995+3.8","v":13.794999999999998},{"$f":"9.995+3.8","v":13.794999999999998},"Solar",2010,"2010-02-05",null,null,"2010-02-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-02-12",null,"Yes",null,null,0,"n/a","Yes",null,null,"2010-02-18",null,null,"2010-02-01","no","WDGSL005",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1117.57,989,128.57,null,null,null,null,null,null,null,null,291.57,"On line. New construction.",2010,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Roger Bird","88 Shutesbury Road","Leverett","MA","01054",4135494959,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-02-10"]
["Janice Lamberg (was Pioneer Valley Habitat for Humanity)",null,"SIMP",null,null,"Completed",null,"6A108-2010",null,"R1","R","54249535055","128703009","891805522","926285006","14","Stanley St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-01-13",2.2400000000000002,2.2399999999999998,2.8,"Class 1 (Solar / Wind)",null,2.8,2.8,2.8,"Solar",2010,"2010-02-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-03-01",null,"n/a",null,null,0,"n/a",null,null,null,"2010-03-12",null,null,"2010-03-01","2011-01-13",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-03-01"]
["Mary Methot",null,"SIMP",null,null,"Completed",null,"6A109-2010",null,"R1","R","54465794071","904141000","890690702","764242005","135","Packardville Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-04-21",4.048,4.048,5.0599999999999996,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-03-05",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-03-26",null,"n/a",null,null,0,"n/a",null,null,null,"2010-05-07",null,null,"2010-04-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-03-26"]
["Sara Ross",null,"EXP",null,"Cindy","Completed",null,"6A110-2010",null,"R1","R","54427481080","528621009","892150822","067812007","82","Cottage St",null,null,"Amherst","MA","01002","WMECO","17K","17K3"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2013-03-18",9.9359999999999999,9.9359999999999999,12.42,"Class 1 (Solar / Wind)",null,14.7,14.7,14.7,"Solar",2010,"2010-04-01",null,null,"2010-04-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-05-18",null,"Yes",null,null,0,"n/a","Yes",null,null,"2010-06-23",null,null,"5/2010","no","WDGSL006",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,6500,5200,1300,null,null,null,null,null,null,null,null,207.96,"On line. New construction.",2010,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Sara Ross","82 Cottage Street","Amherst","MA","01002",4135495690,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-05-20"]
["Charles Emmons",null,"SIMP",null,null,"Completed",null,"6A111-2010",null,"R1","R","54338102056","358441007","892151302","038842004","457","Montague Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-04-06",5.2080000000000002,5.2080000000000002,6.51,"Class 1 (Solar / Wind)",null,6.51,6.51,6.51,"Solar",2010,"2010-04-06",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-04-09",null,"n/a",null,null,0,"n/a",null,null,null,"2010-06-23",null,null,"2010-07-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-04-09"]
["Bob Saul (new 6A115-2010)","Sun Run","SIMP",null,null,"Cancelled",null,"6A111A-2010",null,"R1","R","54772502076","645641007","883786412","912452006","321","East Hadley Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K1"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.8,"Solar",2010,"2010-04-08",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a","needed",null,0,"n/a",null,null,null,null,null,null,"2010-04-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Fisher Home, Inc.",null,"SIMP",null,null,"Completed",null,"6A112-2010",null,"G0","C","54690271077","783621008","892000502","743612004","1165","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-18",4.16,{"$f":"AJ122*0.8","v":4.16},5.2,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-05-14",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-05-18",null,"n/a",null,null,0,"n/a",null,null,null,"2010-06-18",null,null,"2010-05-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","< 10 kW single phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-05-18"]
["Andrew Cowles",null,"SIMP",null,null,"Completed",null,"6A113-2010",null,"G0","C","54970402053","696541004","892000542","909252003","1178","South East St",null,null,"Amherst","MA","01003","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-05-12",3.52,3.5200000000000005,4.4000000000000004,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2010,"2010-05-12",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-05-17",null,"n/a",null,null,0,"n/a",null,null,null,"2010-07-01",null,null,"2010-06-11","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-05-17"]
["Lisa Rutledge (was Don Muccino)",null,"SIMP",null,null,"Completed",null,"6A114-2010",null,"R1","R","54378146039","446931007","892150952","227932005","17","Pleasant View Dr",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-04-18",4.1280000000000001,4.1280000000000001,5.16,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-05-06","2010-05-07",{"$f":"IF(AS124=0,NETWORKDAYS(AR124,$A$4),NETWORKDAYS(AR124,AS124))","v":2},"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-05-17",null,"n/a",null,null,0,"n/a",null,null,null,"2010-06-14",null,null,"2010-05-30","2013-04-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-05-17"]
["Bob Saul","Sun Run","SIMP",null,null,"Completed",null,"6A115-2010",null,"R1","R","54772502076","645641007","891866522","912452006","321","East Hadley Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-05-26",5.76,5.7600000000000007,7.2,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2010,"2010-05-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-04",null,"n/a","2010-06-21",null,0,"n/a",null,null,null,"2010-11-16",null,null,"2010-06-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-07"]
["Jeannette Wicks-Lim","Sun Run","SIMP",null,null,"Completed",null,"6A116-2010",null,"R1","R","54211571062","463503006","891866862","240665004","865","Belchertown Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-05-26",4.08,4.08,5.0999999999999996,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-05-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-17",null,"n/a","2010-07-01",null,0,"n/a",null,null,null,"2010-10-08",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-18"]
["Vicky Pillard",null,"SIMP",null,null,"Completed",null,"6A117-2010",null,"R1","R","54568402093","702641004","891866612","240665004","120","Pulpit Hill Rd","Unit  ",16,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-07",3.024,3.024,3.78,"Class 1 (Solar / Wind)",null,3.3260000000000001,3.3260000000000001,3.3260000000000001,"Solar",2010,"2010-06-07",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-09",null,"n/a",null,null,0,"n/a",null,null,null,"2010-08-13",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-09"]
["Charles Bodhi",null,"SIMP",null,null,"Completed",null,"6A118-2010",null,"R1","R","54696502087","192641008","891866272","942252004","120","Pulpit Hill Rd","Unit  ",24,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-07",2.952,2.952,3.69,"Class 1 (Solar / Wind)",null,3.2469999999999999,3.2469999999999999,3.2469999999999999,"Solar",2010,"2010-06-07",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-14",null,"n/a",null,null,0,"n/a",null,null,null,"2010-08-13",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-14"]
["Mary Kraus",null,"SIMP",null,null,"Completed",null,"6A119-2010",null,"R1","R","54448402099","746641000","891866532","796452007","120","Pulpit Hill Rd","Unit  ",14,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-07",4.7039999999999997,4.7039999999999997,5.88,"Class 1 (Solar / Wind)",null,5.1740000000000004,5.1740000000000004,5.1740000000000004,"Solar",2010,"2010-06-07",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-09",null,"n/a",null,null,0,"n/a",null,null,null,"2010-09-17",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-09"]
["Nancy Bair",null,"SIMP",null,null,"Completed",null,"6A120-2010",null,"R1","R","54786502088","437641009","891866662","176452007","120","Pulpit Hill Rd","Unit  ",5,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-07",2.2959999999999998,2.2960000000000003,2.87,"Class 1 (Solar / Wind)",null,2.5249999999999999,2.5249999999999999,2.5249999999999999,"Solar",2010,"2010-06-07",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-09",null,"n/a",null,null,0,"n/a",null,null,null,"2010-09-17",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-06-09"]
["Navjiwan Fuller (new 6A126-2010)",null,"SIMP",null,null,"Cancelled",null,"6A121-2010",null,"R1","R","54268502010","125741001","988423062","745452009","189","Long Plain Rd",null,null,"Leverett","MA","01054","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.9000000000000004,"Solar",2010,"2010-06-11",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-07-14",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-06-24","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cancld - diff inverter new appl submitted see 6A126-2010",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-07-14"]
["Peter Jessop",null,"SIMP",null,null,"Completed",null,"6A122-2010",null,"R1","R","54327502084","659641005","891866292","717452007","120","Pulpit Hill Rd","Unit  ",15,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-15",3.024,{"$f":"AJ132*0.8","v":3.024},3.78,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2010,"2010-06-15",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-07-01",null,"n/a",null,null,0,"n/a",null,null,null,"2010-08-13",null,null,"2010-06-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-07-01"]
["Dirgha Gurung (was William Allan)",null,"SIMP",null,null,"Completed",null,"6A123-2010",null,"R3","R","54196207070","804031009","891866872","696322003","85","Rocky Hill Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-02-04",4.048,4.048,5.0599999999999996,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2010,"2010-06-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-24",null,"n/a",null,null,0,"n/a",null,null,null,"2010-08-26",null,null,"2010-08-10","2015-02-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-25"]
["Al Haskins",null,"SIMP",null,null,"Completed",null,"6A124-2010",null,"R1","R","54255202095","809541006","891866762","705152008","163","Russell St",null,null,"Sunderland","MA","01375","WMECO",{"$f":"LEFT(Y134,3)","v":"18G"},"18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-21",4.5119999999999996,4.5119999999999996,5.64,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2010,"2010-06-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-22",null,"n/a",null,null,0,"n/a",null,null,null,"2010-10-13",null,null,"2010-09-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-22"]
["Richard Strong","Sun Run","SIMP",null,null,"Completed",null,"6A125-2010",null,"R1","R","54773991096","263341007","891867122","808642008","166","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-07-13",4.7039999999999997,4.7039999999999997,5.88,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2010,"2010-07-13",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-07-14",null,"n/a","2010-07-22",null,0,"n/a",null,null,null,"2010-11-16",null,null,"2010-08-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-07-14"]
["Navjiwan Fuller",null,"SIMP",null,null,"Completed",null,"6A126-2010",null,"R1","R","54268502010","125741001","891867092","745452009","189","Long Plain Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-06-24",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2010,"2010-07-21",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-07-21",null,"n/a",null,null,0,"n/a",null,null,null,"2010-07-30",null,null,"2010-07-24","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-07-14"]
["Mark & Elisabeth Hamin","Sun Run","SIMP",null,null,"Completed",null,"6A127-2010",null,"R1","R","54319002010","983441001","891863902","369842009","75","State St",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-07-26",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-07-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-07-28",null,"n/a","2010-08-11",null,0,"n/a",null,null,null,"2011-01-18",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-07-30"]
["MR Banas Ins Agency Inc. (new 6A129-2010)",null,"SIMP",null,null,"Cancelled",null,"6A128-2010",null,"G0",null,"54048091045","055831006","891545732","202732003","63","Main St",null,null,"Easthampton","MA","01027","WMECO","19B","19B6","PTF"," ","Wind Turbine","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,6,"Wind",2010,"2010-07-29",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-08-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled"]
["MR Banas Insurance Agency Inc.","Urban Power","SIMP",null,null,"Cancelled",null,"6A129-2010",null,"G0",null,"54048091045","055831006","891545732","202732003","63","Main St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Wind Turbine","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,6,"Wind",2010,"2010-08-03",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a","needed",null,0,"n/a",null,null,null,null,null,null,"2010-08-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","project cancelled  ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted"]
["Simple Gifts Farm (new 6A133-2010)",null,"SIMP",null,null,"Cancelled",null,"6A130-2010",null,null,null,null,null,null,null,"1089","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,8.1,"Solar",2010,"2010-08-03",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-08-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Wesley Brown",null,"SIMP",null,null,"Completed",null,"6A131-2010",null,"R1","R","54101961068","322521009","891867242","780512005","117","Plain Rd West",null,null,"South Deerfield","MA","01373","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-08-09",7.1760000000000002,{"$f":"AJ141*0.8","v":7.176000000000001},8.9700000000000006,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2010,"2010-08-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-08-12",null,"n/a",null,null,0,"n/a",null,null,null,"2010-11-16",null,null,"2010-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-08-13"]
["Brian Towles (new 6A139-2010)",null,"SIMP",null,null,"Cancelled",null,"6A132-2010",null,"R1","R","54584871008","154031009","891867162","313322009","73","Phelps St",null,null,"Easthampton","MA","01027","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,3.9,"Solar",2010,"2010-08-10",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-08-12",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-10-21","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","(cancld - changed inverter see 6A139-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-08-13"]
["Jeremy Barker-Plotkin (new 6A135-2010)",null,"SIMP",null,null,"Cancelled",null,"6A133-2010",null,"G0",null,"54607891017","505241008","889943762","023542009","1089","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,8.1,"Solar",2010,"2010-08-05",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-08-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","(cancld - new appl submitted w/dif inverter see ID 6A135-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Cultivating Solutions, LLC",null,"EXP",null,"Carla","Completed",null,"6A134-2010",null,"G0","C","54270545064","445103001","891880612","626945007","17","Lawrence Plain Rd",null,"Barn","Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2014-09-12",27.456,{"$f":"AJ144*0.8","v":27.456000000000003},34.32,"Class 1 (Solar / Wind)",null,30.3,30.3,30.3,"Solar",2010,"2010-08-20",null,null,"2010-09-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-09-21",null,"Yes",null,null,0,"n/a","Yes",null,null,"2010-11-10",null,null,"2010-09-20",null,"WDGSL014",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2548.91,2055.5700000000002,493.34,null,null,null,null,null,null,null,null,27.93,"On line.",2010,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  Michael Docter","113 Bay Road","Hadley","MA","01035",4133877140,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-11-05"]
["Jeremy Barker-Plotkin (new 6A142-2010)",null,"SIMP",null,null,"Cancelled",null,"6A135-2010",null,"G0",null,"54607891017","505241008","889943762","023542009","1089","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,9.9949999999999992,"Solar",2010,"2010-08-27",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-09-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","(cancld - new appl submitted w/diff inverter see 6A142-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Hampshire College - Longsworth Arts",null,"EXP",null,"Erik","Completed",null,"6A136-2010",null,"T2","C","54917561086","538221007","064632791 + 078004591","082212006","893","West St",null,null,"Amherst","MA","01002","WMECO","19B","19B16","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"no export",0,null,null,"No Export",null,39.6,39.6,39.6,"Solar",2010,"2010-08-30",null,null,"2010-09-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-10-01",null,"Yes",null,null,0,"n/a","No",null,null,"2010-10-15",null,null,"2010-09-01","no","WDGSL016",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line.",2010,"needed","needed",null,null,null,"n/a - not expected to export",null,null,null,null,null,null,"Trustees of Hampshire College   Attn:  Larry Archer","893 West St","Amherst","MA","01002",4135595767,4135595662,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-09-22"]
["Alan Sax",null,"SIMP",null,null,"Completed",null,"6A137-2010",null,"R1","R","54508402021","840641002","892149012","699352001","161","Pine St","Apt","F","Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-04-10",4.5359999999999996,{"$f":"AJ147*0.8","v":4.5360000000000005},5.67,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2010,"2010-09-13",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-09-20",null,"n/a",null,null,0,"n/a",null,null,null,"2011-01-05",null,null,"2010-12-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-09-20"]
["Carolyn & Kyle Cave",null,"EXP",null,"Cindy","Completed",null,"6A138-2010",null,"R1","R","54145771010","659613005","890985372","126926001","18","Kennedy Dr",null,null,"Hadley","MA","01035","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2015-01-20",17.303999999999998,{"$f":"AJ148*0.8","v":17.303999999999998},21.63,"Class 1 (Solar / Wind)",null,25.5,25.5,25.5,"Solar",2010,"2010-09-21",null,null,"2010-10-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-11-30",null,"Yes",null,null,0,"n/a","Yes",null,null,"2011-02-23",null,null,"2010-11-01",null,"WDGSL019",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3000,2650,350,null,null,null,null,null,null,null,null,65.64,"On line. New construction.",2011,"??","??",null,null,null,"net metering","new construction",null,null,null,null,null,"Carolyn Cave","18 Kennedy Drive","Hadley","MA","01035",4135490321,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-12-01"]
["Brian Towles (new 6A148-2010)",null,"SIMP",null,null,"Cancelled",null,"6A139-2010",null,"R1","R","54584871008","154031009","891867162","313322009","73","Phelps St",null,null,"Easthampton","MA","10583","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.18,"Solar",2010,"2010-10-27",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-11-03",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-01-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Customer applied, changed inverters, cancelled was application 6A132-2010",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-08-13"]
["Mapleline Farm (new 6A141-2010)",null,"SIMP",null,null,"Cancelled",null,"6A140-2010",null,"G0",null,"54260534029","891982000","890475492","105694000","71","Comins Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,11.4,"Solar",2010,"2010-11-05",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,"n/a","n/a",null,null,null,null,null,null,"2011-02-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","(cancld - submitted appl with different name see ID 6A141-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["John Kokoski",null,"SIMP",null,null,"Completed",null,"6A141-2010",null,"G0","C","54260534029","891982000","891873012","105694000","71","Comins Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-11-09",7.7439999999999998,{"$f":"AJ151*0.8","v":7.7439999999999998},9.68,"Class 1 (Solar / Wind)",null,11.4,11.4,11.4,"Solar",2010,"2010-11-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-11-29",null,null,null,null,0,"n/a",null,null,null,"2011-02-15",null,null,"2011-02-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","< 25 kW three phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-11-29"]
["Jeremy Barker-Plotkin (new 6A143-2010)",null,"SIMP",null,null,"Cancelled",null,"6A142-2010",null,"G0",null,"54607891017","505241008","892243822","023542009","1089","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,12,"Solar",2010,"2010-11-12",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,"n/a","n/a",null,null,null,null,null,null,"2010-11-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cancld - new appl submitted w/diff inverter see 6A143-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Jeremy Barker-Plotkin",null,"SIMP",null,null,"Completed",null,"6A143-2010",null,"G0","C","54607891017","505241008","892243822","023542009","1089","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-09-24",7.84,{"$f":"AJ153*0.8","v":7.8400000000000007},9.8000000000000007,"Class 1 (Solar / Wind)",null,11.4,11.4,11.4,"Solar",2010,"2010-11-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-11-19",null,null,null,null,0,"n/a",null,null,null,"2010-11-23",null,null,"2010-11-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","< 25 kW three phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Seren Derin","Sun Run","SIMP",null,null,"Completed",null,"6A144-2010",null,"R1","R","54254991060","154341001","892149412","651642005","22","Alyssum Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-11-22",3.68,{"$f":"AJ154*0.8","v":3.6799999999999997},4.5999999999999996,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2010,"2010-11-22",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-12-01",null,"n/a","2010-12-08",null,0,"n/a",null,null,null,"2011-05-20",null,null,"2010-02-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-12-01"]
["Albert Larose",null,"SIMP",null,null,"Completed",null,"6A145-2010",null,"R1","R","54882571060","810921001","892149712","290122005","17","Pomeroy St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-12-01",4.0490000000000004,{"$f":"AJ155*0.8","v":4.0488},5.0609999999999999,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2010,"2010-11-22",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-12-02",null,null,null,null,0,"n/a",null,null,null,"2011-01-27",null,null,"2010-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-12-02"]
["Brian Dillon (new 6A150-2011)",null,"SIMP",null,null,"Cancelled",null,"6A146-2010",null,"R1","R","54927471052","830921003","892149842","315912004","22","Pomeroy St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.7,"Solar",2010,"2010-11-22",null,null,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-12-02",null,"n/a",null,null,0,"n/a",null,null,null,null,null,null,"2010-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cancld - new appl submitted w/ diff inverter see 6A150-2011",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-12-02"]
["Robert Tinker",null,"SIMP",null,null,"Completed",null,"6A147-2010",null,"R3","R","54684002025","555441006","892149872","541842000","126","Shutesbury Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-11-29",4.1360000000000001,{"$f":"AJ157*0.8","v":4.1360000000000001},5.17,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2010,"2010-11-29",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-12-03",null,null,null,null,0,"n/a",null,null,null,"2011-04-12",null,null,"2010-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-12-03"]
["Brian Towles ",null,"SIMP",null,null,"Completed",null,"6A148-2010",null,"R1","R","54584871008","154031009","891867162","313322009","73","Phelps St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-11-03",3.1680000000000001,{"$f":"AJ158*0.8","v":3.1680000000000001},3.96,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2010,"2010-11-29",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-12-08",null,null,null,null,0,"n/a",null,null,null,"2010-12-28",null,null,"2010-12-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2010-08-13"]
["Barstow's Longview Farm (new 6A156-2011)",null,"STD",null,"Cindy","Cancelled",null,"6A149-2011",null,"G0",null,null,null,null,null,"14","Barstow Ln",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Reciprocating Engines","cogeneration facility","n/a",null,null,"n/a",null,null,null,"N/A",null,450,450,450,"Biogas",2011,"2011-01-04","2011-01-04",{"$f":"IF(AS159=0,NETWORKDAYS(AR159,$A$4),NETWORKDAYS(AR159,AS159))","v":1},null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,"n/a","n/a","Yes",null,null,null,null,null,"2011-07-01",null,"WDGCG101","see 6A156-2011",null,null,null,null,null,null,null,null,null,null,null,null,"WDCGA101",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Cust name and design changed. Reapplied.","Cancelled","n/a","n/a",null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Brian Dillon",null,"SIMP",null,null,"Completed",null,"6A150-2011",null,"R1","R","54927471052","830921003","892149842","315912004","22","Pomeroy St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-12-01",4.0490000000000004,{"$f":"AJ160*0.8","v":4.0488},5.0609999999999999,"Class 1 (Solar / Wind)",null,5.4,5.4,5.4,"Solar",2011,"2011-01-18","2011-01-19",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-01-21",{"$f":"IF(BL160=0,NETWORKDAYS(AR160,$A$4),NETWORKDAYS(AR160,BL160))","v":4},null,null,null,0,"n/a",null,null,null,"2011-01-27",null,null,"2010-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Y",null,null,"n/a"]
["City of Easthampton (Landfill)","GLC - (MA) Easthampton, LLC","STD",null,"Erik","Completed",null,"6A151-2011",null,"G0","C","54995506078","076923008","000003648","768027003","155","Oliver St",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","Public",null,"Municipality","2013-12-09",1762.904,1762.9040000000002,2203.63,"Class 2",null,2000,2000,2000,"Solar",2011,"2011-01-27","2011-01-27",1,"2011-03-16",{"$f":"IF(AU161=0,NETWORKDAYS(AR161,$A$4),NETWORKDAYS(AR161,AU161))","v":35},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-21",192,"2011-11-01","2011-11-07",null,"$2M / $5M","2015-04-01","Yes","yes",null,"2012-06-01",null,null,"2011-11-19",null,"WDGSL102",2500,11033.75,{"$f":"CC161-CB161","v":8533.75},null,null,null,null,null,null,null,null,null,null,"WDSLA102",40000,32276.76,"2011-03-10","2011-03-21","2011-06-29",null,"WDSLD102",35000,34890.22,"2011-06-24","2011-07-06",null,null,577500,550000,27500,418266.66,null,null,null,null,null,null,null,1527.24,"On line. Int Cust worked with Verizon to get phone lines. Third party owned. Stand alone generation. New construction.",2012,"needed","needed",null,null,"??","net metering","Also has Transfer Tip WO# WDSTT102.  Online prior to DTT being activated.  Subject to temporary SOG.","Attn:  Office of the Mayor","50 Payson Avenue","Easthampton","MA","01027","GLC - (MA) Easthampton, LLC  c/o Accretive Solutions Attn: Jason Tai","2500 Venture Oaks Way, Suite 390","Sacramento","CA","95833",null,null,"C","2012-02-06","installed","Complete","Yes","Yes",null,null,null,"23 KV","ION 8600","413-527-2831","4D 621 6A120511 DXO",1821109,"C","Constructed","completed by RLC","yes","yes","Matt Fuller","Fall 2011","2012-04-30","2012-05-01","Replace armless brackets with fiberglass arms, new primary metered service with DSCADA recloser, another recloser, DTT ",550000,"x","x",null,null,"x","Complete",null,"Y",null,"Y"]
["Phyllis Keenan (was Pioneer Valley Habitat For Humanity)",null,"SIMP",null,null,"Completed",null,"6A152-2011",null,"R1","R","54112975008","138813008","892152232","316646006","10","Stanley St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-12",2.3519999999999999,2.3519999999999999,2.94,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2011,"2011-02-04","2011-02-07",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-02-15",8,null,null,null,0,"n/a",null,null,null,"2011-03-28",null,null,"2011-03-01","2011-10-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","new construction",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-03-17"]
["John A Knybel","Sun Run","SIMP",null,null,"Completed",null,"6A153-2011",null,"R1","R","54333502052","613741003","892151852","268252004","17","Fort Hill Rd",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-02-18",7.1040000000000001,7.104000000000001,8.8800000000000008,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2011,"2011-02-18","2011-02-18",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-02-22",3,null,"2011-03-01",null,0,"n/a",null,null,null,"2011-04-01",null,null,"2011-04-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-02-22"]
["Marcia Hendrick",null,"SIMP",null,null,"Completed",null,"6A154-2011",null,"R1","R","54418781068","492631009","892152072","203432005","8","Old Main Rd",null,null,"Montgomery","MA","01085","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-02-22",5.016,5.016,6.27,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2011,"2011-02-22","2011-02-22",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-03-07",10,null,null,null,0,"n/a",null,null,null,"2011-04-28",null,null,"2011-03-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-03-07"]
["John McCarran  see WMECO Pilot 5",null,"SIMP",null,null,"Completed",null,"6A155-2011",null,"R1","R","54469081061","726131002","888508182","264622005","42","Carriage Ln",null,null,"Amherst","MA","01301","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-02-22",6.48,6.48,8.1,"Class 1 (Solar / Wind)",null,8.34,7.8,"7.8 kW add (8.34 kW total)","Solar",2011,"2011-02-22","2011-02-23",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-03-07",10,null,null,null,0,"n/a",null,null,null,"2011-05-05",null,null,"2011-03-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","n/a"]
["AGreen Energy, LLC (new 6A209-2011)",null,"STD",null,"Erik","Cancelled","2011-09-21","6A156-2011",null,null,null,null,null,null,null,"14","Barstow Ln",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Reciprocating Engines","cogeneration facility","n/a",null,null,"n/a",null,null,null,"N/A",null,450,450,450,"Biogas",2011,"2011-02-23","2011-02-23",1,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","needed",null,null,"n/a","n/a","Yes",null,null,null,null,null,"2011-07-01",null,"WDGCG101",1350,null,null,null,null,null,null,null,null,null,null,null,null,"WDCGA101",null,254.23,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Cust submitted new application for larger unit.","Cancelled","n/a","n/a",null,null,null,"net metering","new construction",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted"]
["EH Home Ownership, LLC (new 6A158-2011) ",null,"SIMP",null,null,"Cancelled",null,"6A157-2011",null,null,null,null,null,null,null,"3","River Valley Way",null,null,"Easthampton","MA","01024","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,7,"Solar",2011,"2011-02-24","2011-02-24",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2011-02-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","cancelled - new application submitted"]
["Northampton Cooperative Action Association (new 6AF160-2010)",null,"EXP",null,"Cindy","Cancelled",null,"6AF157-2010",null,"G0",null,"54505171025","803721006","891538792","433712009","353","Long Plain Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,20,20,20,"Solar",2010,"2010-04-21",null,null,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,"n/a","n/a","TBD",null,null,null,null,null,"7/2010",null,"WDGSL008",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Cust changed design, reapplied. ","Cancelled","n/a","n/a",null,null,null,"net metering","cancld 6/1/10 changed inverters (new 6AF160-2010)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Gyuri Kepes (was EH Home Ownership, LLC)","RePower Partners","SIMP",null,null,"Completed",null,"6A158-2011",null,"R1","R","54632026027","258713008","892152092","478736001","3","River Valley Way",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-04-01",6.048,{"$f":"AJ169*0.8","v":6.048},7.56,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2011,"2011-02-28","2011-03-01",{"$f":"IF(AS169=0,NETWORKDAYS(AR169,$A$4),NETWORKDAYS(AR169,AS169))","v":2},"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-03-08",{"$f":"IF(BL169=0,NETWORKDAYS(AR169,$A$4),NETWORKDAYS(AR169,BL169))","v":7},null,"2011-03-14",null,0,"n/a",null,null,null,"2011-03-21",null,null,"2011-03-07","12/18/2012 Exhibit G",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","1, 3, 5, 8 River Valley fed from 50 kVA xfr pad 335/2P",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-03-08"]
["Hatfield Market (new 6A160-2011)",null,"SIMP",null,null,"Cancelled",null,"6A159-2011",null,null,null,null,null,null,null,"72","School St",null,null,"Hatfield","MA","01038","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,5,"Solar",2011,"2011-03-08","2011-03-09",{"$f":"IF(AS170=0,NETWORKDAYS(AR170,$A$4),NETWORKDAYS(AR170,AS170))","v":2},"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,0,"n/a",null,null,null,null,null,null,"2011-05-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted"]
["Hatfield Properties and Storage (new 6A175-2011)",null,"SIMP",null,null,"Cancelled",null,"6A160-2011",null,"G0",null,"54836391060","847931009","889145312","897932005","72","School St",null,null,"Hatfield","MA","01038","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,2.66,"Solar",2011,"2011-03-15","2011-03-15",{"$f":"IF(AS171=0,NETWORKDAYS(AR171,$A$4),NETWORKDAYS(AR171,AS171))","v":1},"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-03-29",{"$f":"IF(BL171=0,NETWORKDAYS(AR171,$A$4),NETWORKDAYS(AR171,BL171))","v":11},"n/a",null,null,0,"n/a",null,null,null,null,null,null,"2011-05-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2011-03-29"]
["Northampton Cooperative Auction Association, Inc.",null,"EXP",null,"Cindy","Completed",null,"6AF160-2010",null,"G0","C","54505171025","803721006","891880442","433712009","353","Long Plain Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2010-05-14",14.784000000000001,{"$f":"AJ172*0.8","v":14.784000000000001},18.48,"Class 1 (Solar / Wind)",null,15.6,15.6,15.6,"Solar",2010,"2010-06-01",null,null,"2010-06-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-06-28",null,"2010-07-06",null,null,0,"n/a","Yes",null,null,"2010-07-09",null,null,"7/2010",null,"WDGSL008",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1587.04,1269.6300000000001,317.41000000000003,null,null,null,null,null,null,null,null,152.63999999999999,"On line.",2010,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  Kim Reardon","PO Box 203","So. Deerfield","MA","01373",4136284784,4136283872,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-06-17"]
["Lori Shollenberger","Sun Run","SIMP",null,null,"Completed",null,"6A161-2011",null,"R1","R","54178855094","524813001","892341932","297146007","14","Johnson Ave",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-05-13",3.9359999999999999,{"$f":"AJ173*0.8","v":3.9359999999999999},4.92,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-03-21","2011-03-22",{"$f":"IF(AS173=0,NETWORKDAYS(AR173,$A$4),NETWORKDAYS(AR173,AS173))","v":2},"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-04-13",{"$f":"IF(BL173=0,NETWORKDAYS(AR173,$A$4),NETWORKDAYS(AR173,BL173))","v":18},null,"2011-04-26",null,0,"n/a",null,null,null,"2011-05-20",null,null,"2011-05-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-04-13"]
["Ray Mann",null,"SIMP",null,null,"Completed",null,"6A162-2011",null,"R1","R","54997535083","182213007","892152302","144606006","982","East Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-03-22",6.6239999999999997,{"$f":"AJ174*0.8","v":6.6239999999999997},8.2799999999999994,"Class 1 (Solar / Wind)",null,7.56,7.5,7.56,"Solar",2011,"2011-03-22","2011-03-22",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-04-04",{"$f":"IF(BL174=0,NETWORKDAYS(AR174,$A$4),NETWORKDAYS(AR174,BL174))","v":10},null,null,null,0,"n/a",null,null,null,"2011-09-15",null,null,"2011-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-04-04"]
["Andrew Starkweather (see 6A245-2011)",null,"SIMP",null,null,"Completed",null,"6A163-2011",null,"R1","R","54971715008","243703008","892341942","807975008","18","Hannabrooke Dr",null,null,"Leverett","MA","01054","WMECO","21C","21C7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-03-23",2.016,{"$f":"AJ175*0.8","v":2.016},2.52,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2011,"2011-03-23","2011-03-25",3,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-04-12",{"$f":"IF(BL175=0,NETWORKDAYS(AR175,$A$4),NETWORKDAYS(AR175,BL175))","v":15},null,null,null,0,"n/a",null,null,null,"2011-04-28",null,null,"2010-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-04-12"]
["John S. Lane & Son (new 6A168-2011)",null,"STD",null,"Erik","Cancelled","2011-05-17","6A164-2011",null,null,null,null,null,null,null,"931","Pochassic Rd",null,null,"Westfield","MA","01085","WMECO","19J","19J2","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,250,250,250,"Solar",2011,"2011-04-07","2011-04-08",2,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","n/a",null,null,"n/a","n/a","TBD",null,null,null,null,null,"2011-07-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Wrong application submitted. 3rd party info incorrect. Cust submited new application.","Cancelled","n/a","n/a",null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Raymond Babb","Sun Run","SIMP",null,null,"Completed",null,"6A165-2011",null,"R1","R","54724615091","542703008","892342082","975975006","81","North Maple St",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-04-26",4.9119999999999999,{"$f":"AJ177*0.8","v":4.9119999999999999},6.14,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2011,"2011-04-26","2011-04-26",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-05-11",{"$f":"IF(BL177=0,NETWORKDAYS(AR177,$A$4),NETWORKDAYS(AR177,BL177))","v":12},null,"2011-05-19",null,0,"n/a",null,null,null,"2011-06-09",null,null,"2011-05-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-05-11"]
["Jonathan Child (was Elizabeth Rosenberg) (addition to 6A51-2008)",null,"SIMP",null,null,"Completed",null,"6A166-2011",null,"R1","R","54404976011","664753006","891408342","443332000","135","East St",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-04-22",4.6079999999999997,4.6079999999999997,5.76,"Class 1 (Solar / Wind)",null,10,6,"  6 kW add (10 kW total)","Solar",2011,"2011-04-28","2011-04-28",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-05-12",{"$f":"IF(BL178=0,NETWORKDAYS(AR178,$A$4),NETWORKDAYS(AR178,BL178))","v":11},null,null,null,0,"n/a",null,null,null,"2011-06-13",null,null,"2011-05-01","2014-04-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Michael Zeoli","Sun Run","SIMP",null,null,"Completed",null,"6A167-2011",null,"R1","R","54044602043","911741004","892151312","635552003","48","Claybrook Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-05-02",6.048,6.048,7.56,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2011,"2011-05-02","2011-05-02",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-05-09",{"$f":"IF(BL179=0,NETWORKDAYS(AR179,$A$4),NETWORKDAYS(AR179,BL179))","v":6},null,"2011-05-19",null,0,"n/a",null,null,null,"2011-05-24",null,null,"2011-05-13",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"needed ?",null,null,"Future",null,"cancelled","2011-05-09"]
["John S. Lane & Son","Echo Sierra Two, LLC)","STD",null,"Erik","Cancelled","2013-02-06","6A168-2011",null,"G0",null,"54348571001","952821002","891611912","319122006","931","Pochassic Rd",null,null,"Westfield","MA","01085","WMECO","19J","19J2","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,898.56000000000006,1123.2,"N/A",null,1000,1000,"250 kW or 1000 kW","Solar",2011,"2011-05-17","not sure","not sure","2011-07-20",{"$f":"IF(AU180=0,NETWORKDAYS(AR180,$A$4),NETWORKDAYS(AR180,AU180))","v":47},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","needed","needed",null,"cancld","cancld","Yes","Yes",null,null,null,null,"2011-09-30",null,"WDGSL109",2500,1995.84,{"$f":"CC180-CB180","v":-504.16000000000008},null,null,null,null,null,null,null,null,null,null,"WDSLA109",null,195.97,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Int Cust. Third party owned. Essentially stand alone generation. New construction. Application has two options 250 kW or 1,000 kW. Highest option listed in Design Capacity.","Cancelled","needed","needed",null,null,null,"net metering","Cancelled per customer request",null,null,null,null,null,null,null,null,null,null,null,null,"N","cancelled by customer","N/A","cancelled","No",null,null,null,null,"23 KV or secondary",null,"future","future","future","N","Very Low","on hold per cust, TRC","no","no","Jack Szpila","TBD","TBD","TBD","TBD - new 23 kV primary metered service or secondary service upgrade",null,null,null,null,null,null,"on hold per customer",null,"Y",null,"Y"]
["Nat Larson",null,"SIMP",null,null,"Completed",null,"6A169-2011",null,"R1","R","54381702034","162841005","892342402","228452002","35","Summerfield Rd","Lot",31,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-05-18",5.2640000000000002,5.2640000000000002,6.58,"Class 1 (Solar / Wind)",null,5.32,5.32,5.32,"Solar",2011,"2011-05-18","2011-05-18",{"$f":"IF(AS181=0,NETWORKDAYS(AR181,$A$4),NETWORKDAYS(AR181,AS181))","v":1},"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-06-01",{"$f":"IF(BL181=0,NETWORKDAYS(AR181,$A$4),NETWORKDAYS(AR181,BL181))","v":11},null,null,null,0,"n/a",null,null,null,"2011-06-20",null,null,"2011-05-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"Future",null,null,"2011-06-01"]
["Franklin County Sheriff's Office","Whately Solar LLC","STD",null,"Carla","Completed",null,"6A170-2011",null,"G0","C","54067895078","670823005","000003668","833017007","228","State Rd ",null,null,"Whately","MA","01373","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","Public",null,"Other Governmental Entity","2011-07-13",1440,1440,1800,"Class 2",null,1500,1500,1500,"Solar",2011,"2011-05-19","2011-05-19",1,"2011-07-21",{"$f":"IF(AU182=0,NETWORKDAYS(AR182,$A$4),NETWORKDAYS(AR182,AU182))","v":46},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-04-03",{"$f":"IF(BL182=0,NETWORKDAYS(AR182,$A$4),NETWORKDAYS(AR182,BL182))","v":229},"2012-04-17","2012-04-13",null,"$2M / $5M","2015-05-11","Yes","Yes",null,"2013-03-11",null,null,"2011-09-01",null,"WDGSL110",2500,4166.0200000000004,{"$f":"CC182-CB182","v":1666.0200000000004},null,null,null,null,null,null,null,null,null,null,"WDSLA110",37975,33620.410000000003,"2011-07-01","2011-07-08","2011-12-28",null,"WDSLD110",43000,21030.76,"2011-12-13","2011-12-21",null,null,335610,297000,38610,167474.99,null,null,null,null,null,"2013-01-29","2013-02-01",661.66,"On line. Third party owned. Stand alone generation. New construction.",2013,"needed","needed",null,null,null,"net metering",null,"Attn:  Paul Gervais","160 Elm Street","Greenfield",1301,"MA","Whately Solar, LLC    Attn:  Brian Morrissey","88 Black Falcon Avenue,  Suite 342","Boston","MA","02210",6179510405,null,"C","2012-03-05","2012-10-15","Complete","meter installed","yes",null,"8400 : 120",null,"13.8 KV","ION 8600","413-665-7686","DWN12009, \n4D 621 6A120475 DXO","WR1806730\n1721266, 120V 228 State Rd= 2092542, 120V 0 Christian Ln = 2092554","C","Constructed","completed by RLC","yes","yes, 1 recloser, 2 controls","Dave Silloway","2012-09-01","2012-10-15","on line","new 13.8 kV primary metered service with DSCADA recloser and recloser control replacement, DTT",297000,"x","x",null,null,"x","120 V services for DTT installed and phone lines installed.  DTT needs to be commissioned ASAP.",null,"Y",null,"Y",null,null,"Y"]
["Andrea Cooper (was Melanie DeSilva)","Sun Run","SIMP",null,null,"Completed",null,"6A171-2011",null,"R1","R","54264756057","137641009","892342342","740452001","161","Pine St","Apt","C","Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-09-12",2.3679999999999999,2.3679999999999999,2.96,"Class 1 (Solar / Wind)",null,2.9,2.9,2.9,"Solar",2011,"2011-05-31","2011-05-31",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-06-07",{"$f":"IF(BL183=0,NETWORKDAYS(AR183,$A$4),NETWORKDAYS(AR183,BL183))","v":6},null,"2013-09-12",null,0,"n/a",null,null,null,"2011-07-29",null,null,"2011-07-17","2013-09-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-06-07"]
["Jeffery Thelen (new  6A182-2011)",null,"SIMP",null,null,"Cancelled",null,"6A172-2011",null,"R1","R","54619302011","304541002","868271492","396152000","14","Grand Oak Farm Rd",null,null,"Hadley","MA","01035","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.9000000000000004,"Solar",2011,"2011-05-31","2011-05-31",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,null,null,"2011-07-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Biodynamic Farmland Conservation Inc.  (addition to 6A10-2005)",null,"SIMP",null,null,"Completed",null,"6A173-2011",null,"G0","C","54548791094","096241005","890645322","987542007","24","Hulst Rd",null,null,"Amherst","MA","01004","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-06-20",3.52,{"$f":"AJ185*0.8","v":3.5200000000000005},4.4000000000000004,"Class 1 (Solar / Wind)",null,8.7799999999999994,5,"5 kW add (8.78 kW total)","Solar",2011,"2011-06-06","2011-06-07",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-06-28",{"$f":"IF(BL185=0,NETWORKDAYS(AR185,$A$4),NETWORKDAYS(AR185,BL185))","v":17},null,null,null,0,"n/a",null,null,null,"2011-07-08",null,null,"2011-07-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","< 10 kW single phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Robert Libon","Sun Run","SIMP",null,null,"Completed",null,"6A174-2011",null,"R1","R","54795102078","443441009","892342582","043942005","32","Laurel Mt Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-06-14",4.2640000000000002,4.2640000000000002,5.33,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-06-14","2011-06-14",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-06",17,null,"2011-07-14",null,0,"n/a",null,null,null,"2011-07-18",null,null,"2011-07-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","On same XFR as 37 Laurel Mt Rd 6A62-2008",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-07-06"]
["William Skorupski, Jr (was Hatfield Properties & Storage)",null,"SIMP",null,null,"Completed",null,"6A175-2011",null,"G0","C","54030947071","923931008","892244052","897932005","72","School St","Floor",1,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"MIMO - needed",2.6320000000000001,2.6320000000000001,3.29,"Class 1 (Solar / Wind)",null,2.66,2.66,2.66,"Solar",2011,"2011-06-21","2011-06-21",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-06-27",5,null,null,null,0,"n/a",null,null,null,"2011-07-08",null,null,"2011-06-20","MIMO - needed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","three phase system with microinverters, < 25 kW.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-06-29"]
["Miles Morrissey","Sun Run","SIMP",null,null,"Completed",null,"6A176-2011",null,"R1","R","54927961045","759521006","892342672","658512003","39","Taft Ave",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-06-29",4.5919999999999996,4.5920000000000005,5.74,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2011,"2011-06-29","2011-06-29",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-06",6,null,"2011-07-14",null,0,"n/a",null,null,null,"2011-07-14",null,null,"2011-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-07-06"]
["Thomas Hartman (addition to 6A20-2006)",null,"SIMP",null,null,"Completed",null,"6A177-2011",null,"R1","R","54452661010","287321001","890835412","699112000","4","Amherst Rd",null,null,"Pelham","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-07-06",2.2080000000000002,2.2079999999999997,2.76,"Class 1 (Solar / Wind)",null,4.5199999999999996,2.52,"2.52 kW add (4.52 kW total)","Solar",2011,"2011-07-06","2011-07-06",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-13",6,null,null,null,0,"n/a",null,null,null,"2011-08-12",null,null,"2011-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Kathleen Lugosch",null,"SIMP",null,null,"Completed",null,"6A178-2011",null,"R1","R","54366402097","231641008","891140462","664452007","15","Hawks View Rd",null,null,"Shutesbury","MA","01072","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-07-08",7.68,7.68,9.6,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-07-08","2011-07-11",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-21",10,null,null,null,0,"n/a",null,null,null,"2011-09-28",null,null,"2011-08-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-07-21"]
["Warren Goldstein","Sun Run","SIMP",null,null,"Completed",null,"6A179-2011",null,"G0","C","54177745080","173992001","890684212","320735001","165B","West St","Unit  ","Owners","Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-07-13",6.8879999999999999,6.8879999999999999,8.61,"Class 1 (Solar / Wind)",null,8,8,8,"Solar",2011,"2011-07-13","2011-07-13",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-06",40,null,"2011-09-16",null,0,"n/a",null,null,null,"2011-09-27",null,null,"2011-09-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-09-06"]
["Ronald Howey (new 6A186-2011)","Sun Run","SIMP",null,null,"Cancelled",null,"6A180-2011",null,"R1","R","54796691095","864241006","883998242","525342008","90","Russell St",null,null,"Sunderland","MA","01375","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,4.9000000000000004,"Solar",2011,"2011-07-13","2011-07-13",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,0,"n/a",null,null,null,null,null,null,"2011-09-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Allen Banas","Sun Run","SIMP",null,null,"Completed",null,"6A181-2011",null,"R1","R","54699391033","904931004","890835612","317832002","32","Broad St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-07-13",4.2,{"$f":"AJ193*0.8","v":4.2},5.25,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-07-13","2011-07-13",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-18",{"$f":"IF(BL193=0,NETWORKDAYS(AR193,$A$4),NETWORKDAYS(AR193,BL193))","v":4},null,"2011-07-27",null,0,"n/a",null,null,null,"2011-09-13",null,null,"2011-09-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-07-18"]
["Jeffery Thelen",null,"SIMP",null,null,"Completed",null,"6A182-2011",null,"R1","R","54619302011","304541002","892342362","396152000","14","Grand Oak Farm Rd",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-06-02",4.6079999999999997,4.6079999999999997,5.76,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2011,"2011-07-14","2011-07-15",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-21",{"$f":"IF(BL194=0,NETWORKDAYS(AR194,$A$4),NETWORKDAYS(AR194,BL194))","v":6},null,null,null,0,"n/a",null,null,null,"2011-08-26",null,null,"2011-08-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Atkins Fruit Bowl",null,"EXP",null,"Carla","Completed",null,"6A183-2011",null,"G2","C","54416181089","076723008","891794962","133722006","1151","West St",null,null,"Amherst","MA","01002","WMECO","19B","19B16","PTF"," ","Photovoltaic","Inverter","Private",null,null,"2011-08-30",36.799999999999997,36.800000000000004,46,"Class 1 (Solar / Wind)",null,60,60,60,"Solar",2011,"2011-07-28","2011-07-28",1,"2011-09-22",{"$f":"IF(AU195=0,NETWORKDAYS(AR195,$A$4),NETWORKDAYS(AR195,AU195))","v":41},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-17",{"$f":"IF(BL195=0,NETWORKDAYS(AR195,$A$4),NETWORKDAYS(AR195,BL195))","v":58},"2011-10-17",null,null,0,"n/a","No","No",null,"2011-11-18",null,null,"2011-11-01",null,"WDGSL114",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line.",2011,"n/a","n/a",null,null,"n/a","net metering",null,null,null,null,null,null,"Atikins fruit Bowl","1150 West Street","Amherst","MA","01002","(413) 253-9528","(413) 256-3117",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"N/N "]
["Barry Elbaum",null,"SIMP",null,null,"Completed",null,"6A184-2011",null,"R1","R","54461661043","760321004","892342842","375212003","25","Prospect St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-01",4,4,5,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-08-01","2011-08-02",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-12",{"$f":"IF(BL196=0,NETWORKDAYS(AR196,$A$4),NETWORKDAYS(AR196,BL196))","v":10},null,null,null,0,"n/a",null,null,null,"2011-09-02",null,null,"2011-08-19",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-08-12"]
["Mark Monska (new 6A187-2011)",null,"SIMP",null,null,"Cancelled",null,"6A185-2011",null,null,null,null,null,null,null,"42","Clapp St",null,null,"Easthampton","MA","01027","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a",null,null,"n/a",null,3.6799999999999997,4.5999999999999996,"N/A",null,null,null,4,"Solar",2011,"2011-08-01","2011-08-02",2,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,null,null,"2011-09-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Barbara Howey","Sun Run","SIMP",null,null,"Completed",null,"6A186-2011",null,"R1","R","54796691095","864241006","892342822","525342008","90","Russell St",null,null,"Sunderland","MA","01375","WMECO",{"$f":"LEFT(Y198,3)","v":"18G"},"18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-08",6.12,6.120000000000001,7.65,"Class 1 (Solar / Wind)",null,7.4,7.4,7.4,"Solar",2011,"2011-08-08","2011-08-08",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-18",{"$f":"IF(BL198=0,NETWORKDAYS(AR198,$A$4),NETWORKDAYS(AR198,BL198))","v":9},null,"2011-08-31",null,0,"n/a",null,null,null,"2011-09-15",null,null,"2011-09-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-08-18"]
["Mark Monska (new 6A203-2011)",null,"SIMP",null,null,"Cancelled",null,"6A187-2011",null,"R1","R","54227502036","659641007","887311282","578252002","42","Clapp St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,3.6799999999999997,4.5999999999999996,"N/A",null,null,null,4,"Solar",2011,"2011-08-09","2011-08-09",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-10",2,null,null,null,0,"n/a",null,null,null,null,null,null,"2011-09-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-08-10"]
["Kazutaka Hirata",null,"SIMP",null,null,"Completed",null,"6A188-2011",null,"R3","R","54941594038","690641006","892340802","458152008","37","Jenks St","Lot",15,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-12",5.3360000000000003,5.3360000000000003,6.67,"Class 1 (Solar / Wind)",null,6.02,6.02,6.02,"Solar",2011,"2011-08-12","2011-08-12",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-09",21,null,null,null,0,"n/a",null,null,null,"2011-11-23",null,null,"2011-09-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-09"]
["Harold Green",null,"SIMP",null,null,"Completed",null,"6A189-2011",null,"R1","R","54444091029","796731000","892340912","612632000","48","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-15",5.6,5.6000000000000005,7,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2011,"2011-08-15","2011-08-15",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-20",27,null,null,null,0,"n/a",null,null,null,"2011-10-20",null,null,"2011-08-26",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-20"]
["John Hornik",null,"SIMP",null,null,"Completed",null,"6A190-2011",null,"R3","R","54538991001","335241002","892343052","036542009","59","Carriage Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-16",7.68,7.68,9.6,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-08-16","2011-08-16",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-18",3,null,null,null,0,"n/a",null,null,null,"2011-09-26",null,null,"2011-09-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled","2011-08-18"]
["David Biddle","Sun Run","SIMP",null,null,"Cancelled",null,"6A191-2011",null,"R1","R","54970602058","317741009","766674423","855552003","96","Bridge St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,8,10,"N/A",null,null,null,10,"Solar",2011,"2011-08-19","2011-08-19",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-23",3,null,"needed",null,0,"n/a",null,null,null,null,null,null,"2011-09-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","project cancelled",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-08-23"]
["William Simmons II","Sun Run","SIMP",null,null,"Completed",null,"6A192-2011",null,"R1","R","54993602051","972741002","892340782","423452004","172","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-19",4,4,5,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-08-19","2011-08-19",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-08-25",5,null,"2011-09-16",null,0,"n/a",null,null,null,"2011-11-22",null,null,"2011-11-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"cancelled","2011-08-25"]
["Marge Frank","Sun Run","SIMP",null,null,"Cancelled",null,"6A193-2011",null,"R1","R","54602691057","922141008","884886492","430142004","6","Winterberry Ln",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,4.8000000000000007,6,"N/A",null,null,null,5.3,"Solar",2011,"2011-08-22","2011-08-22",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-02",10,null,"2011-10-06",null,0,"n/a",null,null,null,null,null,null,"2011-09-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","project cancelled",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-02"]
["Ingrid Flory","Sun Run","SIMP",null,null,"Completed",null,"6A194-2011",null,"R1","R","54660481052","535431003","892340852","739822004","45","Briggs St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-29",4.8,4.8000000000000007,6,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2011,"2011-08-29","2011-08-29",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-07",8,null,"2011-09-14",null,0,"n/a",null,null,null,"2011-11-14",null,null,"2011-10-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-09-07"]
["Melba & David Jensen (new 6A202-2011)",null,"SIMP",null,null,"Cancelled",null,"6A195-2011",null,"R1","R","54133905042","539492002","891204392","173125004","4","Plainville Rd",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,2.8120000000000003,3.5150000000000001,"N/A",null,null,null,3.61,"Solar",2011,"2011-09-01","2011-09-01",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,null,null,"2011-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Lynne Edwards",null,"EXP",null,"Erik","Completed",null,"6A196-2011",null,"G0","C","54624395026","439823009","892241792","055317000","27","Middle St","Lot","Solar Field","Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"04/02/2012 & 6/13/2012",79.2,79.2,99,"Class 2",null,95,95,95,"Solar",2011,"2011-09-01","2011-09-01",1,"2011-10-25",{"$f":"IF(AU208=0,NETWORKDAYS(AR208,$A$4),NETWORKDAYS(AR208,AU208))","v":39},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-30",{"$f":"IF(BL208=0,NETWORKDAYS(AR208,$A$4),NETWORKDAYS(AR208,BL208))","v":65},"2011-12-06",null,null,"$500K / $500K","2014-10-01","Yes","No",null,"2012-03-30",null,null,"2011-11-01",null,"WDGSL117",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line. Stand alone generation. New construction.",2012,"n/a","n/a",null,null,null,"net metering",null,null,null,null,null,null,null,"PO Box 78","Hadley","MA","01035",4135859897,4135859897,null,null,null,null,null,null,null,null,null,null,null,"413-586-0810",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Carol Lewis",null,"SIMP",null,null,"Completed",null,"6A197-2011",null,"R1","R","54516171022","541721003","892340732","055317000","21","Ward St",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-02",1.84,1.8399999999999999,2.2999999999999998,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2011,"2011-09-02","2011-09-02",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-08",5,null,null,null,0,"n/a",null,null,null,"2011-10-21",null,null,"2011-10-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-08"]
["Matthew Dusseault (was Robert Eckert)","Sun Run","SIMP",null,null,"Completed",null,"6A198-2011",null,"R1","R","54416876019","896092004","893239222","348005000","71","Gilbert Rd",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-03",7.84,7.8400000000000007,9.8000000000000007,"Class 1 (Solar / Wind)",null,10,10,10,"Solar",2011,"2011-09-02","2011-09-02",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-12",7,null,"2011-09-16",null,0,"n/a",null,null,null,"2011-09-29",null,null,"2011-09-23","2014-04-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-12"]
["Daniel Burbine",null,"SIMP",null,null,"Completed",null,"6A199-2011",null,"R1","R","54792961070","542392000","892341112","845905003","1178","North Pleasant St",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-06",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2011,"2011-09-06","2011-09-07",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-23",14,null,null,null,0,"n/a",null,null,null,"2012-02-01",null,null,"2011-09-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-09-23"]
["Francis Flavin (new 6A218-2011)","Sun Run","SIMP",null,null,"Cancelled",null,"6A200-2011",null,"R3","R","54317391043","123931004","884397692","379932003","10","Plantation Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,5.6000000000000005,7,"N/A",null,null,null,6,"Solar",2011,"2011-09-07","2011-09-07",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-21",11,null,"2011-09-26",null,0,"n/a",null,null,null,null,null,null,"2011-10-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-21"]
["Jeffrey Brouillard","Sun Run","SIMP",null,null,"Completed",null,"6A201-2011",null,"R1","R","54808602098","981841009","892342712","512752007","210","Brickyard Rd","Lot",1,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-08",6.4,6.4,8,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2011,"2011-09-08","2011-09-09",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-14",5,null,"2011-09-20",null,0,"n/a",null,null,null,"2011-09-29",null,null,"2011-10-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-14"]
["Melba & David Jensen (was 6A195-2011)",null,"SIMP",null,null,"Completed",null,"6A202-2011",null,"R1","R","54133905042","539492002","892342902","173125004","4","Plainville Rd",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-01",2.6659999999999999,2.6664000000000003,3.3330000000000002,"Class 1 (Solar / Wind)",null,4.085,4.085,4.085,"Solar",2011,"2011-09-08","2011-09-09",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-14",5,null,null,null,0,"n/a",null,null,null,"2011-12-02",null,null,"10/2011",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-14"]
["Mark Monska",null,"SIMP",null,null,"Completed",null,"6A203-2011",null,"R1","R","54227502036","659641007","892343012","578252002","42","Clapp St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-08-01",3.68,3.6799999999999997,4.5999999999999996,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2011,"2011-09-12","2011-09-12",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-21",8,null,null,null,0,"n/a",null,null,null,"2011-09-29",null,null,"2011-09-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-09-21"]
["Beth Walker","Sun Edison","SIMP",null,null,"Completed",null,"6A204-2011",null,"R1","R","54748602034","630841005","892341002","404452002","50","Kingman Rd",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-30",7.02,7.0200000000000005,8.7750000000000004,"Class 1 (Solar / Wind)",null,8.3849999999999998,8.3849999999999998,8.3849999999999998,"Solar",2011,"2011-09-13","2011-09-14",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-09-29",13,null,"2011-10-06",null,0,"n/a",null,null,null,"2011-11-22",null,null,"2011-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-09-29"]
["Ocean Air Aviation, LLC (new 6A241-2011)",null,"SIMP",null,null,"Cancelled",null,"6A205-2011",null,"G0",null,"54941015026","557331008","890630912","851922002","180","Pleasant St",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Wind Turbine","Inverter","n/a",null,null,"n/a",null,null,null,"N/A",null,null,null,3.3,"Wind",2011,"2011-09-16","2011-09-16",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"??",null,"n/a","n/a",null,null,null,null,null,null,"2011-09-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","cust submitted EXP Application",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted"]
["Paul Petcen (new 6A219-2011)","Sun Run","SIMP",null,null,"Cancelled",null,"6A206-2011",null,"R1","R","54632391058","507931009","885770272","219932003","65","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,{"$f":"AJ218*0.8","v":5.6000000000000005},7,"N/A",null,null,null,6,"Solar",2011,"2011-09-20","2011-09-20",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-04",{"$f":"IF(BL218=0,NETWORKDAYS(AR218,$A$4),NETWORKDAYS(AR218,BL218))","v":11},null,"2011-10-17",null,0,"n/a",null,null,null,null,null,null,"2011-10-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-10-04"]
["Frank Motyka, Jr. (new 6A216-2011)","Sun Run","SIMP",null,null,"Cancelled",null,"6A207-2011",null,"R1","R","54172691073","928041004","885003542","076242006","53","Plain Rd  ",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,{"$f":"AJ219*0.8","v":4.8000000000000007},6,"N/A",null,null,null,5.3,"Solar",2011,"2011-09-20","2011-09-20",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,0,"n/a",null,null,null,null,null,null,"2011-11-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Richard & Jean Gilbert","Sun Run","SIMP",null,null,"Completed",null,"6A208-2011",null,"R1","R","54496691031","100141002","892342982","200342001","45","Plain Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-20",8,{"$f":"AJ220*0.8","v":8},10,"Class 1 (Solar / Wind)",null,10,10,10,"Solar",2011,"2011-09-20","2011-09-20",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-06",{"$f":"IF(BL220=0,NETWORKDAYS(AR220,$A$4),NETWORKDAYS(AR220,BL220))","v":13},null,"2011-10-17",null,0,"n/a",null,null,null,"2011-12-21",null,null,"2011-11-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FUTURE",null,null,"2011-10-06"]
["BGreen Energy, LLC",null,"STD",null,"Erik","Completed",null,"6A209-2011",null,"G0","C","54335966081","307743003","891801472","167148008","14","Barstow Ln",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Reciprocating Engines","generator","Private","yes",null,"2014-02-18",300,null,null,"Class 2",null,300,300,"225, 300 or 600","Biogas",2011,"2011-09-21","not sure","not sure","2013-10-18",{"$f":"IF(AU221=0,NETWORKDAYS(AR221,$A$4),NETWORKDAYS(AR221,AU221))","v":543},null,null,null,null,null,null,null,null,"2013-10-21",null,null,null,null,null,null,"2013-12-19",{"$f":"IF(BL221=0,NETWORKDAYS(AR221,$A$4),NETWORKDAYS(AR221,BL221))","v":587},"2013-12-20",null,null,"$1M / $1M","2015-05-15","Yes","Yes",null,"2013-12-31",{"$f":"IF(BV221=0,NETWORKDAYS(BU221,$A$4),NETWORKDAYS(BU221,BV221))","v":29742},null,"2012-04-01",null,"WDGCG104",1800,null,null,"WDCGS104",4500,3013.91,"2013-11-21",null,null,null,null,null,null,"WDCGA104",null,null,null,null,null,null,null,null,null,null,null,null,null,178944.6,155811,23133.599999999999,94621.14,null,null,null,null,null,null,null,1220.6300000000001,"Online",2013,"needed","needed",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  William Jorgenson","26 Union Park,  Apt 3","Boston","MA","02118","617-510-5245",8573627442,"F","Future","TBD","future request",null,null,null,null,null,"13.8 kV or secondary",null,"future","future","future","F","Low","on hold per cust","no","no","Dave Silloway","TBD","TBD","TBD","TBD - new 1200 Amp 480 V service with 750 KVA transformer or 13.8 kV primary metered service",null,null,null,null,null,null,"on hold per customer",null,"Y"]
["Mauro Giavalisco (was Mauro Calzetti) (also 6A592-2014)",null,"SIMP",null,null,"Completed",null,"6A210-2011",null,"R1","R","54899502025","012841006","892341292","755552001","170","East Leverett Rd","Lot",3,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-11-08",0.60799999999999998,{"$f":"AJ222*0.8","v":0.6080000000000001},0.76,"Class 1 (Solar / Wind)",null,0.76,0.76,0.76,"Solar",2011,"2011-09-26","2011-09-26",{"$f":"IF(AS222=0,NETWORKDAYS(AR222,$A$4),NETWORKDAYS(AR222,AS222))","v":1},"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-09",{"$f":"IF(BL222=0,NETWORKDAYS(AR222,$A$4),NETWORKDAYS(AR222,BL222))","v":55},null,null,null,0,"n/a",null,null,null,"2012-06-08",null,null,"2011-10-25","2013-11-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled","2012-12-09"]
["Margaret Solis","Sun Run","SIMP",null,null,"Cancelled",null,"6A211-2011",null,"R1","R","54912365053","009321001","891567392","711112004","15","Torrey St",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,8,10,"N/A",null,null,null,10,"Solar",2011,"2011-09-28","2011-09-28",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,0,"n/a",null,null,null,null,null,null,"2011-11-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Cancelled per customer request",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Sheryl Derderian","Sun Run","SIMP",null,null,"Completed",null,"6A212-2011",null,"R3","R","54699591095","340241006","892341322","367242008","26","King St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-29",4,4,5,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-09-29","2011-09-29",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-14",{"$f":"IF(BL224=0,NETWORKDAYS(AR224,$A$4),NETWORKDAYS(AR224,BL224))","v":12},null,"2011-11-29",null,0,"n/a",null,null,null,"2011-12-16",null,null,"2011-12-02",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-10-14"]
["Ann Bronner",null,"SIMP",null,null,"Completed",null,"6A213-2011",null,"R1","R","54755402021","858541002","892341222","407352001","198","Rocky Hill Rd",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-09-30",2.96,2.9600000000000004,3.7,"Class 1 (Solar / Wind)",null,4.3,4.3,4.3,"Solar",2011,"2011-09-30","2011-09-30",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-14",11,null,null,null,0,"n/a",null,null,null,"2011-12-09",null,null,"2011-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-10-14"]
["Edward Chang",null,"SIMP",null,null,"Completed",null,"6A214-2011",null,"R1","R","54992602060","337741001","892341422","351552005","6","Arbor Way",null,null,"Amherst","MA","01002","WMECO","17K","17K7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-05",6.9119999999999999,6.9120000000000008,8.64,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-10-05","2011-10-05",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-09",26,null,null,null,0,"n/a",null,null,null,"2011-11-23",null,null,"2011-10-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-11-09"]
["Samantha Mjenzi",null,"SIMP",null,null,"Completed",null,"6A215-2011",null,"R3","R","54510774094","245821000","892341452","775022009","23","Pomeroy St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-12",4.4000000000000004,4.4000000000000004,5.5,"Class 1 (Solar / Wind)",null,5.0999999999999996,5.0999999999999996,5.0999999999999996,"Solar",2011,"2011-10-12","2011-10-12",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-25",10,null,null,null,0,"n/a",null,null,null,"2011-12-02",null,null,"2011-10-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","#17, #22 & #23 Pomeroy all fed from secondary from xfr 219/4",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-10-25"]
["Frank Motyka, Jr.","Sun Run","SIMP",null,null,"Completed",null,"6A216-2011",null,"R1","R","54172691073","928041004","892341232","076242006","53","Plain Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-17",4.5599999999999996,4.5600000000000005,5.7,"Class 1 (Solar / Wind)",null,4.9000000000000004,4.9000000000000004,4.9000000000000004,"Solar",2011,"2011-10-17","2011-10-18",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-10-26",8,null,"2011-11-07",null,0,"n/a",null,null,null,"2011-12-21",null,null,"2011-11-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-10-26"]
["Joanne Despres",null,"SIMP",null,null,"Completed",null,"6A217-2011",null,"R1","R","54858381056","601431007","892922482","237822004","33","Rocky Hill Rd","Floor",1,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-12-30",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2011,"2011-10-24","2011-10-25",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-01-13",60,null,null,null,0,"n/a",null,null,null,"2012-02-03",null,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2012-01-13"]
["Francis Flavin","Sun Run","SIMP",null,null,"Completed",null,"6A218-2011",null,"R3","R","54317391043","123931004","892340922","237822004","10","Plantation Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-25",5.6,5.6000000000000005,7,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2011,"2011-10-25","2011-10-25",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-16",17,null,"2011-11-21",null,0,"n/a",null,null,null,"2011-11-23",null,null,"2011-10-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Paul Petcen","Sun Run","SIMP",null,null,"Completed",null,"6A219-2011",null,"R1","R","54632391058","507931009","892341142","219932003","65","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-25",5.6,5.6000000000000005,7,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2011,"2011-10-25","2011-10-25",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-17",18,null,"2011-11-22",null,0,"n/a",null,null,null,"2011-11-29",null,null,"2011-10-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["John Gerber","Solar City","SIMP",null,null,"Completed",null,"6A220-2011",null,"R1","R","54218381010","056513000","892919542","685922000","123","Harlow Dr",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-10-26",1.6919999999999999,1.6920000000000002,2.1150000000000002,"Class 1 (Solar / Wind)",null,2,2,2,"Solar",2011,"2011-10-26","2011-10-26",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-23",21,null,"2011-12-05",null,0,"n/a",null,null,null,"2012-01-26",null,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-11-23"]
["Bruce Penniman",null,"SIMP",null,null,"Completed",null,"6A221-2011",null,"R1","R","54560102055","499441006","892921892","700842004","50","South Mt Holyoke Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-12-01",5.0759999999999996,5.0760000000000005,6.3449999999999998,"Class 1 (Solar / Wind)",null,5.8049999999999997,5.8049999999999997,5.8049999999999997,"Solar",2011,"2011-11-07","2011-11-07",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-01",19,null,null,null,0,"n/a",null,null,null,"2012-01-13",null,null,"2011-11-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-01"]
["Richard Abbott","Sun Run","SIMP",null,null,"Completed",null,"6A222-2011",null,"R1","R","54422491001","251931002","892919552","764932009","66","Elm St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-07",3.6,3.6,4.5,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2011,"2011-11-07","2011-11-08",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-18",10,null,"2011-11-30",null,0,"n/a",null,null,null,"2011-12-21",null,null,"2011-11-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering","Per field check, 25 kVA xfr on 11/31 feeds #62, 64, 66, 69, 71A, 71B, 73, 75, 77 and 77A Elm St.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2011-11-18"]
["Patterson Farm LLC",null,"SIMP",null,null,"Completed",null,"6A223-2011",null,"G0","C","54399205087","992303004","892000402","962165005","159","Montague Rd","Unit  ","Sugar Hse","Sunderland","MA","01375","WMECO","18G","18G3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-07",7.36,7.3599999999999994,9.1999999999999993,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-11-07","2011-11-08",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-01",19,null,null,null,0,"n/a",null,null,null,"2012-05-08",null,null,"2011-12-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering","< 10 kW single phase. NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Andrew Logan",null,"SIMP",null,null,"Completed",null,"6A224-2011",null,"R1","R","54087955084","213613003","892922192","127426009","11","Moody Field Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-07",5.5679999999999996,5.5680000000000005,6.96,"Class 1 (Solar / Wind)",null,6.2350000000000003,6.2350000000000003,6.2350000000000003,"Solar",2011,"2011-11-07","2011-11-09",3,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-01-31",62,null,null,null,0,"n/a",null,null,null,"2012-03-06",null,null,"2011-11-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2012-01-31"]
["Pro Pel Plastech (new 6A239-2011)",null,"EXP",null,"Carla","Cancelled",null,"6A225-2011",null,"G2",null,null,null,null,null,"378","Long Plain Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,209.66399999999999,262.08,"N/A",null,260,260,259.97000000000003,"Solar",2011,"2011-11-07","2011-11-09",3,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","needed",null,null,"n/a","n/a","TBD","N/A",null,null,null,null,"2012-03-16",null,"WDGSL123",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled by Cust. Cust changed design, submitted new application.","Cancelled","n/a","n/a",null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Robert Wagner",null,"SIMP",null,null,"Completed",null,"6A226-2011",null,"R1","R","54150691095","190241006","892921902","728242008","221","Linseed Rd",null,null,"West Hatfield","MA","01088","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-08",5.76,5.7600000000000007,7.2,"Class 1 (Solar / Wind)",null,6.45,6.45,6.45,"Solar",2011,"2011-11-08","2011-11-09",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-30",{"$f":"IF(BL238=0,NETWORKDAYS(AR238,$A$4),NETWORKDAYS(AR238,BL238))","v":17},null,null,null,0,"n/a",null,null,null,"2012-01-19",null,null,"2011-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-11-30"]
["Carol Walker","Sun Run","SIMP",null,null,"Completed",null,"6A227-2011",null,"R3","R","54722491081","081931002","892921732","087042007","28","King St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-09",3,3,3.75,"Class 1 (Solar / Wind)",null,3.9,3.9,3.9,"Solar",2011,"2011-11-09","2011-11-10",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-28",14,null,"2011-12-07",null,0,"n/a",null,null,null,"2012-01-09",null,null,"2011-12-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-11-28"]
["Thomas Zuzgo",null,"EXP",null,"Erik","Completed",null,"6A228-2011",null,"G0","C","54284771052","537031003","890684312","101222004","351","River Dr",null,null,"Hadley","MA","01035","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2011-11-18",14.784000000000001,14.784000000000001,18.48,"Class 1 (Solar / Wind)",null,17.995000000000001,17.995000000000001,17.995000000000001,"Solar",2011,"2011-11-09","2011-11-10",2,"2011-12-20",{"$f":"IF(AU240=0,NETWORKDAYS(AR240,$A$4),NETWORKDAYS(AR240,AU240))","v":30},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-21",31,"2011-12-29",null,null,0,"n/a","No",null,null,"2012-01-19",null,null,"2011-11-28",null,"WDGSL124",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line.",2012,"??","??",null,null,null,"net metering",null,null,null,null,null,null,null,"351 River Drive","Hadley","MA","01035",4135395708,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y"]
["Amy Petcen","Sun Run","SIMP",null,null,"Completed",null,"6A229-2011",null,"R1","R","54778091074","770831005","892341582","895732006","8","Sunset Ave",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-15",2.4,2.4000000000000004,3,"Class 1 (Solar / Wind)",null,2.9,2.99,2.9,"Solar",2011,"2011-11-15","2011-11-15",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-02",14,null,"2011-12-12",null,0,"n/a",null,null,null,"2011-12-29",null,null,"2011-12-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-12-02"]
["John Merz (new 6A257-2012","Sun Run","SIMP",null,null,"Cancelled",null,"6A230-2011",null,"R1","R","54370002032","307341003","884363422","983542002","37","Chestnut St",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,5.6000000000000005,7,"N/A",null,null,null,6,"Solar",2011,"2011-11-15","2011-11-15",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-02",14,null,"2011-12-12",null,0,"n/a",null,null,null,null,null,null,"2012-01-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-02"]
["Hopkins Academy - Town of Hadley","Hyperion Systems","SIMP",null,null,"Completed",null,"6A231-2011",null,"G2","C","54052181047","618131008","892580812","827722007","131","Russell St",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-18",1.472,1.4720000000000002,1.84,"Class 1 (Solar / Wind)",null,1.72,1.72,1.72,"Solar",2011,"2011-11-18","2011-11-18",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-21",24,null,"2012-01-03",null,0,"n/a",null,null,null,"2012-01-13",null,null,"2011-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering","< 25 kW three phase system, w/ single phase inverters. NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-21"]
["Nessim Watson",null,"SIMP",null,null,"Completed",null,"6A232-2011",null,"R2","R","54278691043","533141004","892921882","796142002","257","Long Plain Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"03/21/2014  and  6/16/2014",4,4,5,"Class 1 (Solar / Wind)",null,5.3,5.3,5.3,"Solar",2011,"2011-11-18","2011-11-18",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-06",13,null,null,null,0,"n/a",null,null,null,"2012-01-27",null,null,"2011-12-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-06"]
["Amber Helems","Sun Run","SIMP",null,null,"Completed",null,"6A233-2011",null,"R3","R","54469265086","369931005","892341182","425932009","67","Old Stage Rd",null,null,"West Hatfield","MA","01088","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-22",2.4,2.4000000000000004,3,"Class 1 (Solar / Wind)",null,2.9,2.9,2.9,"Solar",2011,"2011-11-22","2011-11-23",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-15",18,null,"2012-01-03",null,0,"n/a",null,null,null,"2012-02-03",null,null,"2012-02-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-15"]
["Pamela Raymond","Sun Run","SIMP",null,null,"Completed",null,"6A234-2011",null,"R2","R","54130991052","983341003","892341552","733642003","44","Plain Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-27",8,8,10,"Class 1 (Solar / Wind)",null,9.1999999999999993,9.1999999999999993,9.1999999999999993,"Solar",2011,"2011-11-28","2011-11-29",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-12",11,null,"2011-12-19",null,0,"n/a",null,null,null,"2012-02-15",null,null,"2012-01-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2011-12-12"]
["Michael Beeltje","Sun Run","SIMP",null,null,"Completed",null,"6A235-2011",null,"R1","R","54322791088","747141009","892341312","366342007","102","Russell St",null,null,"Sunderland","MA","01375","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-28",7.2,7.2,9,"Class 1 (Solar / Wind)",null,10,10,10,"Solar",2011,"2011-11-28","2011-11-29",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-12",11,null,"2012-02-13",null,0,"n/a",null,null,null,"2012-02-17",null,null,"2011-12-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted","2011-12-12"]
["Garrett Deane (new 6A258-2012)","Sun Run","SIMP",null,null,"Cancelled",null,"6A236-2011",null,"R1","R","54821502036","425641007","883997842","102252002","17","Grybko Cross Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,6.4,8,"N/A",null,null,null,7,"Solar",2011,"2011-12-02","2011-12-02",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-20",13,null,"2012-01-04",null,0,"n/a",null,null,null,null,null,null,"2012-01-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2011-12-20"]
["Flora Chamlin (addition to 6A36-2006)",null,"SIMP",null,null,"Completed",null,"6A237-2011",null,"R3","R","54040271033","093621004","891140452","750812001","35","Westbrook Rd",null,null,"Whately","MA","01093","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-12-05",4.6079999999999997,4.6079999999999997,5.76,"Class 1 (Solar / Wind)",null,10,6,"6.0 kW add (10 kW total)","Solar",2011,"2011-12-05","2011-12-06",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-01-06",25,null,null,null,0,"n/a",null,null,null,"2012-02-23",null,null,"2011-12-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Michael Morrissey",null,"SIMP",null,null,"Completed",null,"6A238-2011",null,"R1","R","54884202094","044541005","892341652","429152007","34","Thomas Rd",null,null,"Montgomery","MA","01085","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-12-16",6.3360000000000003,6.3360000000000003,7.92,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-12-16","2011-12-16",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-21",4,null,null,null,0,"n/a",null,null,null,"2012-05-09",null,null,"2012-01-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2011-12-21"]
["Garrett Deane","Sun Run","SIMP",null,null,"Completed",null,"6A258-2012",null,"R1","R","54821502036","425641007","892341812","102252002","17","Grybko Cross Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-01-18",6.4,6.4,8,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2012,"2012-01-18","2012-01-19",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-02-09",{"$f":"IF(BL268=0,NETWORKDAYS(AR268,$A$4),NETWORKDAYS(AR268,BL268))","v":17},null,"2012-02-24",null,0,"n/a",null,null,null,"2012-03-01",null,null,"2012-01-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - new application submitted"]
["Michael McGrath",null,"SIMP",null,null,"Completed",null,"6A269-2012",null,"R1","R","54761491083","272931004","892922882","617042007","69","Main St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-02-23",7,7,8.75,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2012,"2012-02-23","2012-02-23",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-03-09",12,null,null,null,0,"n/a",null,null,null,"2012-03-30",null,null,"2012-03-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-03-09"]
["Erin Guzowski","PV Home PPA1, LLC","SIMP",null,null,"Completed",null,"6A306-2012",null,"R1","R","54765402094","647641005","892921442","188352008","67","Bridge St",null,null,"Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-05-09",6.24,6.24,7.8,"Class 1 (Solar / Wind)",null,8,8,8,"Solar",2012,"2012-05-09","2012-05-09",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-06-08",23,null,"2012-06-20",null,0,"n/a",null,null,null,"2012-07-05",null,null,"2012-05-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Richard Pitcher (was Christa McCauley)",null,"SIMP",null,null,"Completed",null,"6A326-2012",null,"R1","R","54839337011","391631007","893073892","956432001","4","Louise Ave",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-24",6.5279999999999996,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,7.31,7.31,7.31,"Solar",2012,"2012-06-26","2012-06-26",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-07-09",10,null,null,null,0,"n/a",null,null,null,"2012-10-03",null,null,null,"2015-12-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - new application submitted","2012-07-09"]
["C & F Farms, Inc. (was Chester Szawlowski)",null,"EXP",null,"Carla","Completed",null,"6A339-2012",null,"G0","C","54658646088","675433005","058884091","276694003","107","Main St","Bldg","Lower","Hatfield","MA","01038","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2013-06-21",149.6,149.6,187,"Class 2",null,175,175,175,"Solar",2012,"2012-07-27","2012-07-30",2,"2012-08-31",{"$f":"IF(AU349=0,NETWORKDAYS(AR349,$A$4),NETWORKDAYS(AR349,AU349))","v":26},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-10-09",53,"2012-10-12",null,null,"$1M / $1M","2014-06-28","No",null,null,"2012-12-01",null,null,"not supplied","2013-06-20","WDGSL273",525,2253.9699999999998,{"$f":"CC349-CB349","v":1728.9699999999998},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-11-29","2012-12-03",68.22,"On line.",2012,"n/a","n'a",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  Shelley Szawlowski","103 Main Street","Hatfield","MA","01038",4132479240,4132473270,null,null,null,null,null,null,null,null,null,null,null,null,"N/A ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-10-03"]
["John Tobiason",null,"SIMP",null,null,"Completed",null,"6A371-2012",null,"R1","R","54084391093","004931004","893149442","633042008","350","Potwine Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-13",7.8479999999999999,7.8480000000000008,9.81,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2012,"2012-10-19","2012-10-19",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-11-28",29,null,null,null,0,"n/a",null,null,null,"2012-12-19",null,null,"early 12/2012",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Blue Wave Capital, LLC","??","STD",null,"Carla","Cancelled","2013-09-04","6A382-2012",null,null,null,"new service",null,null,null,"100","Venture Way","Parcel","3A / 4B","Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,663.04,828.8,"N/A",null,760,760,"750 or 760","Solar",2012,"2012-11-21","2012-11-27",5,"2012-11-29",{"$f":"IF(AU392=0,NETWORKDAYS(AR392,$A$4),NETWORKDAYS(AR392,AU392))","v":7},2,null,null,null,null,null,null,null,"2012-11-30","2013-01-31",0,null,null,null,null,null,"canc","needed","??",null,null,"cancld","Yes","?",null,null,null,null,"2013-12-15",null,"WDGSL297",2280,1348.03,{"$f":"CC392-CB392","v":-931.97},null,null,null,null,null,null,null,"2013-01-31","2013-01-31",0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Stand alone generation. New construction. May be third party owned. Scoping meeting held.   Project on hold (2/14/13), customer needs to submit option because of inverter change.  Purge letter sent to Int Cust 5/20/13. Rcvd new option 5/28/13 from customer. Need to perform initial review of new option.  New project size 10 kW larger than original. Design 750 kW or 760 kW. Highest design listed. 8/20/13 call with deigner - Customer sending new option. Customer sent e-mail 8/29/13 that this project has been cancelled.","Cancelled","??","??",null,null,null,"net metering","Cancelled by Interconnecting customer.",null,null,null,null,null,null,null,null,null,null,null,null,"N","Third Quarter 2013","Third Quarter 2013","future request",null,null,null,null,null,"13.8 KV or secondary",null,"future","future",null,"N","Medium","will be needed","no","no","TBD","TBD","TBD","Fourth Quarter 2013","Fourth Quarter 2013",null,null,null,null,null,null,"New application.",null,"Y"]
["Michelle Chandler","SolarCity Corp","SIMP",null,null,"Completed",null,"6A404-2013",null,"R2","R","54744502063","653641004","893071822","499352005","326","West Pomeroy Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-02-05",3.2639999999999998,3.2640000000000002,4.08,"Class 1 (Solar / Wind)",null,3.8,3.8,3.8,"Solar",2013,"2013-02-05","2013-02-05",{"$f":"IF(AS414=0,NETWORKDAYS(AR414,$A$4),NETWORKDAYS(AR414,AS414))","v":1},"n.r.","n/a",null,null,null,null,null,null,null,null,"n.r.","n.r",null,null,null,null,null,"2013-03-18",30,null,"2013-05-10",null,0,"n/a",null,null,null,"2013-06-11",null,null,"2013-06-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,"cancelled","2013-03-18"]
["John Skorupski","Sun Run","SIMP",null,null,"Completed",null,"6A439-2013",null,"R1","R","54976302000","745541001","893148402","439052009","119","Oliver St",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-05-23",6.4,6.4,8,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2013,"2013-05-23","2013-05-23",1,"2013-06-05",{"$f":"IF(AU449=0,NETWORKDAYS(AR449,$A$4),NETWORKDAYS(AR449,AU449))","v":10},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-06-06",{"$f":"IF(BL449=0,NETWORKDAYS(AR449,$A$4),NETWORKDAYS(AR449,BL449))","v":11},null,"2013-06-12",null,0,"n/a",null,null,"2013-08-23","2013-09-23",{"$f":"IF(BV449=0,NETWORKDAYS(BU449,$A$4),NETWORKDAYS(BU449,BV449))","v":22},5,"2013-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-06-06"]
["Paul Bourke",null,"SIMP",null,null,"Completed",null,"6A461-2013",null,"R1","R","54806991071","675241002","893240572","666642006","77","Long Hill Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-07-17",7.36,7.3599999999999994,9.1999999999999993,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2013,"2013-07-17","2013-07-17",1,"2013-07-31",11,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-07-31",{"$f":"IF(BL471=0,NETWORKDAYS(AR471,$A$4),NETWORKDAYS(AR471,BL471))","v":11},null,null,null,0,"n/a",null,null,"2013-08-28","2013-08-30",{"$f":"IF(BV471=0,NETWORKDAYS(BU471,$A$4),NETWORKDAYS(BU471,BV471))","v":3},null,"2013-08-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-07-31"]
["Christopher Raker",null,"SIMP",null,null,"Completed",null,"6A484-2013",null,"R2","R","54352302095","333641006","893568622","142252008","46","Jenks St",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-10-04",5.76,5.7600000000000007,7.2,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2013,"2013-10-04","2013-10-04",1,"2013-10-31",20,12,"2013-10-29","2013-10-30",0,null,null,null,null,null,null,null,null,null,null,null,"2013-10-31",20,null,null,null,0,"n/a",null,null,"2013-12-02","2013-12-12",9,0,"2013-11-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-10-31"]
["Jeremy M Barker-Plotkin",null,"SIMP",null,"Erik","Completed",null,"6A518-2013","2270080","R1","R","54719834046","759092007","866668982","594005002","241","Pine St","Lot","A","Amherst","MA","01007","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-12-12",5.52,5.5200000000000005,6.9,"Class 1 (Solar / Wind)",null,7,7,7,"Solar",2013,"2013-12-12","2013-12-18",5,"2014-01-09",21,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-01-09",21,null,null,null,0,null,null,null,"2014-03-06","2014-03-13",6,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-01-09"]
["Chester Papineau",null,"SIMP",null,"Erik","Completed",null,"6A526-2014","2274720","R1","R","54810505065","738192007","891625522","079205009","107","White Loaf Rd",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-01-15",3.44,3.44,4.3,"Class 1 (Solar / Wind)",null,4.3,4.3,4.3,"Solar",2014,"2014-01-15","2014-01-17",3,"2014-03-14",43,37,"2014-03-14","2014-03-14",0,null,null,null,null,null,null,null,null,null,null,"2014-05-27","2014-03-14",43,null,null,null,0,"n/a",null,null,"2014-03-21","2014-03-25",3,0,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-03-14"]
["John Lapaire",null,"SIMP",null,"Erik","Completed",null,"6A563-2014","2311912","R1","R","54208502039","199641000","889305422","569252002","112","North Maple St",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-04-11",3.18,3.18,3.9750000000000001,"Class 1 (Solar / Wind)",null,3.75,3.75,3.75,"Solar",2014,"2014-04-11","2014-04-14",2,"2014-05-28",34,26,"2014-05-29","2014-06-03",0,null,null,null,null,null,null,null,null,null,null,"2014-07-14","2014-06-03",38,null,null,null,0,"n/a",null,null,"2014-07-14","2014-07-21",6,0,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-05-29"]
["Jeannette Tokarz",null,"SIMP",null,"Carla","Completed",null,"6A583-2014","2324957","R1","R","54680874096","733541004","881772182","172252003","36","Woodlot Rd","Lot",20,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-05-08",4.1760000000000002,4.1760000000000002,5.22,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2014,"2014-05-08","2014-05-08",1,"2014-05-12",3,0,"2014-05-15","2014-05-15",0,null,null,null,null,null,null,null,null,null,null,"2014-06-16","2014-05-15",6,null,null,null,0,"n/a",null,null,"2014-08-06","2014-08-18",9,3,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-05-12"]
["Gordon Thorne",null,"SIMP",null,"Carla","Completed",null,"6A597-2014","2331600","R3","R","54371202029","229441000","868754072","339942000","599","South Pleasant St","Duplex","Front","Amherst","MA","01002","WMECO","17K","17K6"," ","non-PTF","Photovoltaic","Inverter","Private","yes",null,"2014-05-21",10.987,10.987200000000001,13.734,"Class 1 (Solar / Wind)",null,14.35,14.35,14.35,"Solar",2014,"2014-05-21","2014-05-21",1,"2014-06-06",13,0,"2014-06-06","2014-06-06",0,null,null,null,null,null,null,null,null,null,null,"2014-06-14","2014-06-06",13,null,null,null,0,"n/a",null,null,"2014-06-23","2014-07-08",12,0,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-06-06"]
["Richard Weinberg",null,"SIMP",null,"Carla","Completed",null,"6A631-2014","2345487","R1","R","54407402056","946641007","894052742","141252004","555","Market Hill Rd",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-17",6.24,6.24,7.8,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2014,"2014-06-17","2014-06-18",2,"2014-07-02",12,0,"2014-07-09","2014-07-09",0,null,null,null,null,null,null,null,null,null,null,"2014-08-26","2014-07-09",17,null,null,null,0,"n/a",null,null,"2014-09-23","2014-09-26",4,0,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-07-09"]
["Shirley Griffin",null,"SIMP",null,"Erik","Completed",null,"6A648-2014","2349389","R1","R","54081476095","571831003","894060652","839632005","20","Beston St",null,null,"Amherst","MA","01002","WMECO","17K","17K4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-23",5.5200000000000005,5.5200000000000005,6.9,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2014,"2014-06-23","2014-06-23",1,"2014-07-03",9,0,"2014-07-07","2014-07-21",0,null,null,null,null,null,null,null,null,null,null,"2014-08-26","2014-07-21",21,null,null,null,0,"n/a",null,null,"2014-10-27","2014-11-04",7,0,"2014-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-07-16"]
["Richard Hill","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A676-2014","2361417","R1","R","54222702037","895741008","894063582","578452002","2","Kingsberry Way",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-07-15",6.9359999999999999,6.9359999999999999,8.67,"Class 1 (Solar / Wind)",null,7.65,7.65,7.65,"Solar",2014,"2014-07-15","2014-07-15",1,"2014-07-25",9,0,"2014-07-28","2014-08-26",2,null,null,null,null,null,null,null,null,null,null,"2014-09-25","2014-08-26",31,null,"2014-09-22",null,0,"n/a",null,null,"2014-11-06","2014-11-13",6,0,"2014-09-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-08-25"]
["Edward Armstrong",null,"SIMP",null,"Erik","Cancelled","2014-08-04","6A705-2014","2369637","R1","R","54303302012","668541003","868271802","670152000","114","South Maple St",null,null,"Hadley","MA","01035","WMECO","19B","19B15","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,{"$f":"AJ715*0.8","v":7.9680000000000009},9.9600000000000009,"N/A",null,9,9,9,"Solar",2014,"2014-07-30","2014-08-01",3,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,"canc",null,"2014-08-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled"]
["Anthony J Stonina II","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A710-2014","2373213","R1","R","54914602057","254741008","894063602","943452004","18","Clark Ln",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-01",4.8960000000000008,4.8960000000000008,6.12,"Class 1 (Solar / Wind)",null,5.4,5.4,5.4,"Solar",2014,"2014-08-01","2014-08-05",3,"2014-08-05",3,0,null,null,null,"SIMP5","2014-08-06","2014-09-18",0,null,null,null,null,null,null,"2014-10-08","2014-09-18",35,null,"2014-10-22",null,0,"n/a",null,null,"2014-11-06","2014-11-13",6,0,"2014-09-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-09-17"]
["Catherine Helgoe","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A744-2014","2379124","R1","R","54652602004","942741005","894199542","709352009","8","High Meadow Rd",null,null,"Hadley","MA","01035","WMECO","17K","17K5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-08",4.6960000000000006,4.6960000000000006,5.87,"Class 1 (Solar / Wind)",null,5.1749999999999998,5.1749999999999998,5.1749999999999998,"Solar",2014,"2014-08-08","2014-08-11",2,"2014-09-19",31,0,"2014-09-22","2014-10-03",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2014-10-03",41,null,"2014-10-22",null,0,"n/a",null,null,"2015-04-10","2015-04-22",9,0,"2014-10-08",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-02"]
["Heidi Popham",null,"SIMP",null,"Erik","Completed",null,"6A770-2014","2383334","R1","R","54499646024","391841009","894063942 ","736652001","148","Northwest Rd",null,null,"Westhampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-15",4.6639999999999997,4.6640000000000006,5.83,"Class 1 (Solar / Wind)",null,5.5,5.5,5.5,"Solar",2014,"2014-08-15","2014-08-15",1,"2014-10-23",50,0,"2014-10-24","2014-10-24",0,null,null,null,null,null,null,null,null,null,null,"2015-01-29","2014-10-24",51,null,null,null,0,"n/a",null,null,"2014-11-18","2014-11-20",3,0,"2014-08-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-24"]
["Maureen Manning",null,"SIMP",null,"Erik","Completed",null,"6A789-2014","2385956","R3","R","54146081054","283231005","894062412","829422004","167","Shays St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-26",3.3280000000000003,3.3280000000000003,4.16,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2014,"2014-08-26","2014-08-26",1,"2014-09-26",24,0,"2014-09-29","2014-10-21",0,null,null,null,null,null,null,null,null,null,null,"2015-01-29","2014-10-21",41,null,null,null,0,"n/a",null,null,"2015-01-20","2015-02-05",13,0,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-21"]
["Edward Westhead",null,"SIMP",null,"Erik","Completed",null,"6A803-2014","2389425","R3","R","54978081024","183231005","891759922","339622001","20","Cortland Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-02",7.9040000000000008,7.9040000000000008,9.8800000000000008,"Class 1 (Solar / Wind)",null,9.5,9.5,9.5,"Solar",2014,"2014-09-02","2014-09-02",1,"2014-10-10",29,0,"2014-10-14","2014-10-22",0,null,null,null,null,null,null,null,null,null,null,"2015-01-29","2014-10-22",37,null,null,null,0,"n/a",null,null,"2015-03-27","2015-04-10",11,5,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-22"]
["Erin Pope",null,"SIMP",null,"Erik","Completed",null,"6A846-2014","2398479","R1","R","54935155028","242682007","889330812","125094002","15","Valley Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-17",5.1840000000000002,5.1840000000000011,6.48,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2014,"2014-09-17","2014-09-17",1,"2014-10-10",18,0,"2014-10-14","2014-10-28",0,null,null,null,null,null,null,null,null,null,null,"2015-02-10","2014-10-28",30,null,null,null,0,"n/a",null,null,"2014-10-28","2014-11-10",10,2,"2014-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-28"]
["Daniel Thouin",null,"SIMP",null,"Erik","Completed",null,"6A869-2014","2408248","R1","R","54914502018","680741009","894062422","946352000","137","Tob Rd",null,null,"Westhampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-02",6.7319999999999993,6.7319999999999993,8.4149999999999991,"Class 1 (Solar / Wind)",null,7.4249999999999998,7.4249999999999998,7.4249999999999998,"Solar",2014,"2014-10-02","2014-10-02",1,"2014-10-17",12,0,"2014-10-20","2014-11-13",0,null,null,null,null,null,null,null,null,null,null,"2015-02-10","2014-11-13",31,null,null,null,0,"n/a",null,null,"2015-01-08","2015-01-20",9,5,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-13"]
["Kevin Jones",null,"SIMP",null,"Erik","Completed",null,"6A893-2014","2419038","R1","R","54711791095","727241006","894192772","215442008","21","East Hadley Rd",null,null,"Hadley","MA","01035","WMECO",{"$f":"LEFT(Y902,3)","v":"19B"},"19B15","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-22",4.3760000000000003,4.3760000000000003,5.47,"Class 1 (Solar / Wind)",null,4.95,4.95,4.95,"Solar",2014,"2014-10-22","2014-10-22",1,"2014-11-07",13,0,"2014-11-10","2014-11-25",0,null,null,null,null,null,null,null,null,null,null,"2015-02-11","2014-11-25",25,null,null,null,0,"n/a",null,null,"2015-03-20","2015-06-12",61,52,"2014-11-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-25"]
["Gerald Aubrye","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A903-2014","2420089","R1","R","54607991031","627241002","894199442","700542002","7","Golden Dr",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-24",5.1040000000000001,5.1040000000000001,6.38,"Class 1 (Solar / Wind)",null,5.625,5.625,5.625,"Solar",2014,"2014-10-24","2014-10-24",1,"2014-11-14",16,0,"2014-11-17","2014-12-02",0,null,null,null,null,null,null,null,null,null,null,"2015-01-20","2014-12-02",28,null,"2015-02-23",null,0,"n/a",null,null,"2015-04-09","2015-04-16",6,0,"2014-12-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-02"]
["Mark Hemeon Heyer",null,"SIMP",null,"Erik","Completed",null,"6A926-2014","2430030","R1","R","54150602001","592641002","894161682","686352009","125","Cherry Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-11-05",3.84,3.84,4.8,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2014,"2014-11-05","2014-11-05",1,"2014-11-24",14,0,"2014-11-25","2014-12-09",0,null,null,null,null,null,null,null,null,null,null,"2015-02-13","2014-12-09",25,null,null,null,0,"n/a",null,null,"2014-12-15","2014-12-24",8,6,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-12-09"]
["Harry Vandoloski",null,"SIMP",null,"Erik","Completed",null,"6A960-2014","2444523","R1","R","54297471047","111821008","868207622","475912002","20","Middle St","Floor",1,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-02",6.5720000000000001,6.5720000000000001,8.2149999999999999,"Class 1 (Solar / Wind)",null,7.4249999999999998,7.4249999999999998,7.4249999999999998,"Solar",2014,"2014-12-02","2014-12-02",1,"2014-12-12",9,0,"2014-12-15","2014-12-16",0,null,null,null,null,null,null,null,null,null,null,"2015-02-18","2014-12-16",11,null,null,null,0,"n/a",null,null,"2015-09-11","2015-11-03",38,31,"2015-01-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-12-16"]
["Nancy Speas","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A982-2014","2452800","R1","R","54296602014","352841005","886697422","504552000","4","Poets Corner Rd","Lot",2,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-16",6.5279999999999996,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2014,"2014-12-16","2014-12-16",1,"2014-12-18",3,0,"2014-12-19","2015-01-08",0,null,null,null,null,null,null,null,null,null,null,"2015-07-07","2015-01-08",18,null,"2016-01-07",null,0,"n/a",null,null,"2015-10-15","2016-01-15",67,56,"2015-02-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-01-07"]
["Paul Spinale","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-01-26","6A991-2014","2457129","R1","R","54983602020","199741001","883785602","980652001","358","South Silver Ln","Lot",3,"Sunderland","MA","01375","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-22",null,4.2880000000000003,5.36,"Class 1 (Solar / Wind)",null,4.7249999999999996,4.7249999999999996,4.7249999999999996,"Solar",2014,"2014-12-22","2014-12-22",1,"2015-01-05",11,0,"2015-01-06","2015-01-22",0,null,null,null,null,null,null,null,null,null,null,"2015-07-07","2015-01-22",24,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-02-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-01-21"]
["Nina Weyl","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6A1017-2015","2472788","R1","R","54053481073","856331004","894523872","559032006","101","High St",null,null,"Amherst","MA","01002","WMECO","17K","17K3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-14",1.8360000000000001,1.8360000000000001,2.2949999999999999,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-01-14","2015-01-14",1,"2015-01-16",3,0,"2015-01-20","2015-02-23",2,null,null,null,null,null,null,null,null,null,null,"2015-06-09","2015-02-23",29,null,"2015-09-08",null,0,"n/a",null,null,"2015-07-23","2015-09-18",42,32,"2015-03-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-02-11"]
["Robert Poudrier",null,"SIMP",null,"Erik","Completed",null,"6A1057-2015","2485660","R1","R","54311691091","089041002","888676282","688242008","12","Evans Ave",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-02-17",4.4880000000000004,4.4880000000000004,5.61,"Class 1 (Solar / Wind)",null,4.95,4.95,4.95,"Solar",2015,"2015-02-17","2015-02-17",1,"2015-05-15",64,61,"2015-05-18","2015-05-28",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-28",73,null,null,null,0,"n/a",null,null,"2015-12-02","2016-01-08",28,16,"2015-03-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-28"]
["Mary Shaughan","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A1074-2015","2494193","R3","R","54698381019","530431000","887904892","276922000","52","Blackberry Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-10",3.0640000000000001,3.0640000000000001,3.83,"Class 1 (Solar / Wind)",null,3.375,3.375,3.375,"Solar",2015,"2015-03-10","2015-03-10",1,"2015-03-17",6,0,"2015-03-18","2015-04-09",0,null,null,null,null,null,null,null,null,null,null,"2015-07-09","2015-04-09",23,null,"2015-09-02",null,0,"n/a",null,null,"2015-09-02","2015-10-22",37,25,"2015-05-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-04-09"]
["Alison Boland",null,"SIMP",null,"Erik","Completed",null,"6A1096-2015","2505953","R1","R","54089345003","560903006","894192362","701185002","2","Whispering Meadow Ln",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-01",5.088000000000001,5.088000000000001,6.36,"Class 1 (Solar / Wind)",null,5.4,5.4,5.4,"Solar",2015,"2015-04-01","2015-04-01",1,"2015-05-06",26,0,"2015-05-06","2015-05-06",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-06",26,null,null,null,0,"n/a",null,null,"2015-05-28","2015-06-23",19,13,"Jan 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-06"]
["Sugurd Nilsen",null,"SIMP",null,"Erik","Completed",null,"6A1114-2015","2513240","R1","R","54230684060","372541005","894527702","547052005","27","Teaberry Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-15",3.7440000000000002,3.7439999999999998,4.68,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2015,"2015-04-15","2015-04-15",1,"2015-05-12",20,0,"2015-05-13","2015-05-18",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-18",24,null,null,null,0,"n/a",null,null,"2015-07-24","2015-08-07",11,9,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-18"]
["Lynda Faye","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6A1153-2015","2520885","R1","R","54406781039","98831000","889239992","966232002","232","East Pleasant St",null,null,"Amherst","MA","01002","WMECO","17K","17K4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-30",5.7119999999999997,5.7119999999999997,7.14,"Class 1 (Solar / Wind)",null,6.3,6.3,6.3,"Solar",2015,"2015-04-30","2015-04-30",1,"2015-05-27",20,0,"2015-05-28","2015-06-05",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-05",27,null,"2015-10-07",null,0,"n/a",null,null,"2015-08-19","2015-10-27",50,34,"2015-06-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-08"]
["Robert Wall",null,"SIMP",null,"Erik","Completed",null,"6A1155-2015","2522817","G0","C","54124602012","430841003","891350472","953552009","93","Carrington Rd",null,null,"Montgomery","MA","01085","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-01",5.8240000000000007,5.8240000000000007,7.28,"Class 1 (Solar / Wind)",null,6.7080000000000002,6.7080000000000002,6.7080000000000002,"Solar",2015,"2015-05-01","2015-05-04",2,"2015-05-27",19,0,"2015-05-28","2015-06-11",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-11",30,null,null,null,0,"n/a",null,null,"2015-06-12","2015-07-09",20,5,"2015-01-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-11"]
["Jody Kasper",null,"SIMP",null,"Erik","Completed",null,"6A1187-2015","2532216","R1","R","54645796087","416353007","892892512","889888005","15","River Valley Way",null,null,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-20",6.96,6.96,8.6999999999999993,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-05-20","2015-05-21",2,"2015-06-04",12,0,"2015-06-05","2015-07-09",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-09",37,null,null,null,0,"n/a",null,null,"2015-08-31","2015-10-01",24,0,"2015-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-09"]
["Dennis O'Brien","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6A1209-2015","2536313","R1","R","54732602073","547641004","865642502","5/3552006","3","Sophie Cir",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-29",5.4080000000000004,5.4080000000000004,6.76,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-05-29","2015-06-01",2,"2015-06-15",12,0,"2015-06-16","2015-07-10",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-10",31,null,"2015-10-03",null,0,"n/a",null,null,"2015-08-17","2015-10-16",45,33,"2015-07-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-13"]
["Mattias Larsson",null,"SIMP",null,"Erik","Completed",null,"6A1236-2015","2544058","R1","R","54171502008","682641009","881317162","424252009","14","Howard Hepburn Dr",null,null,"Sunderland","MA","01375","WMECO","18G","18G8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-08",3.96,3.9600000000000004,4.95,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2015,"2015-06-08","2015-06-09",2,"2015-07-09",24,5,"2015-07-10","2015-07-22",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-22",33,null,null,null,0,"n/a",null,null,"2015-09-21","2015-10-22",24,15,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-22"]
["Terry Bartus","Vivint Solar Developer, LLC","SIMP",null,"Erik","In Process",null,"6A1267-2015","2552860","R3","R","54532881083","492341001","884868342","927542009","66","Straits Rd",null,null,"Hatfield","MA","01038","WMECO","18G","18G6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-19",null,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2015,"2015-06-19","2015-06-23",3,"2015-07-17",21,0,"2015-07-20","2015-08-03",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04",33,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-05"]
["David Miller","NRG Home Solar","SIMP",null,"Erik","Cancelled","2015-07-27","6A1278-2015","2553539","R1","R","54753725043","979931009","883665132","529832002","6","Campus View Rd",null,null,"Montgomery","MA","01085","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-22",null,9.1840000000000011,11.48,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2015,"2015-06-22","2015-06-26",5,null,163,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,163,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Daniel Clapp","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-07-16","6A1301-2015","2557866","R1","R","54223481045","208431006","887904882","015032003","40","Blackberry Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-07",null,5.2,6.5,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2015,"2015-07-07","2015-07-07",1,null,152,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,152,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-09-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Thomas Keenan",null,"SIMP",null,"Erik","Completed",null,"6A1323-2015","2560609","R1","R","54018716001","704641004","885708792","138252002","20","Strong Rd","Lot",6,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-14",7.8,7.8000000000000007,9.75,"Class 1 (Solar / Wind)",null,8.7750000000000004,8.7750000000000004,8.7750000000000004,"Solar",2015,"2015-07-14","2015-07-14",1,"2015-08-07",19,0,"2015-08-07","2015-08-19",8,null,null,null,null,null,null,null,null,null,null,null,"2015-08-20",28,null,null,null,0,"n/a",null,null,"2015-09-11","2015-10-22",30,21,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-20"]
["Berry Plastics","ECA Solar LLC","EXP",null,"Carla","In Process",null,"6A1343-2015","2568525","G2","C","54627702038","014841009","039962841","464552002","44","Oneil St",null,null,"Easthampton","MA","01027","WMECO","15A","15A2","PTF"," ","Photovoltaic","Inverter",null,null,null,"??",null,0,0,null,null,null,1980,null,"Solar",2015,"2015-07-30","2015-07-31",2,"2015-12-09",95,26,null,null,null,null,null,null,null,"2015-12-10",null,null,null,null,null,null,null,135,null,"needed",null,"??","??",null,null,null,null,30288,null,"2016-05-28",null,"6A521057",7500,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"??",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Q3 2016",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Q3 2016",null,"Q4 2016"]
["Ricardo Gomez",null,"SIMP",null,"Carla","Completed",null,"6A1380-2015","2580359","R1","R","54484371042","860821003","867179302","393912003","17","Harvey Johnson Dr",null,null,"Agawam","MA","01001","WMECO","16C","16C16","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-17",4.7519999999999998,4.7520000000000007,5.94,"Class 1 (Solar / Wind)",null,5.5,5.5,5.5,"Solar",2015,"2015-08-17","2015-08-17",1,"2015-10-07",38,1,"2015-10-08","2015-10-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15",44,null,null,null,0,"n/a",null,null,"2015-11-20","2015-12-01",8,0,"Nov 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-17"]
["Steven Gaspari","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6A1400-2015","2587775","R3","R","54549391043","244931004","885739322","102042003","17","Lynn Dr",null,null,"Southampton","MA","01073","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-24",null,6.048,7.56,"Class 1 (Solar / Wind)",null,6.75,6.75,6.75,"Solar",2015,"2015-08-24","2015-08-25",2,"2015-10-14",38,0,"2015-10-15","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",40,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-10-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-23"]
["Catherine Schwartz","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6A1414-2015","2591313","R1","R","54673502001","977541002","892453092","078252009","16","Torrey St","Lot",1,"Easthampton","MA","01027","WMECO","15A","15A3","PTF"," ","Photovoltaic","Inverter","Private","needed",null,"2015-09-03",null,8.7360000000000007,10.92,"Class 1 (Solar / Wind)",null,12,12,12,"Solar",2015,"2015-09-03","2015-09-03",1,"2015-10-15",31,0,"2015-10-15","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",32,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-11-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-23"]
["Ronald Gregoire",null,"SIMP",null,"Carla","In Process",null,"6A1457-2015","2610267","R1","R","54902991033","794241004","887511972","054442002","25","Sterling Dr",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-09-30",null,7.9920000000000009,9.99,"Class 1 (Solar / Wind)",null,10.15,10.15,10.15,"Solar",2015,"2015-09-30","2015-10-01",2,"2015-10-19",14,0,"2015-10-19","2015-12-08",18,null,null,null,null,null,null,null,null,null,null,null,"2015-12-09",51,null,null,null,0,"n/a",null,null,null,null,30288,null,"2015-10-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["William Degowin","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6A1482-2015","2613948","R3","R","54403791072","131241003","881091942","633442006","1731","South East St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-15",null,6.5560000000000009,8.1950000000000003,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2015,"2015-10-15","2015-10-15",1,"2015-11-23",28,0,"2015-11-23","2015-11-23",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-24",29,null,"needed",null,0,"n/a",null,null,null,null,{"$f":"IF(BV1489=0,NETWORKDAYS(BU1489,$A$4),NETWORKDAYS(BU1489,BV1489))","v":30288},null,"2015-11-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Robert Nomakeo","Vivint Solar Developer, LLC","SIMP",null,"Carla","Completed",null,"6A1493-2015","2614278","R3","R","54275771095","569031006","886577922","311422008","62","Phelps St",null,null,"Easthampton","MA","01027","WMECO","15A","15A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-16",4.16,{"$f":"AJ1500*0.8","v":4.16},5.2,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-10-16","2015-10-20",3,"2015-11-24",28,0,"2015-11-24","2015-11-24",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-24",28,null,"2015-12-16",null,0,"n/a",null,null,"2015-12-16","2015-12-29",10,4,"2015-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Robert Lowry",null,"SIMP",null,"Carla","In Process",null,"6A1522-2015","2629466","R1","R","54338547086","225663009","894591742","348479001","1739","South East St",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","Private","needed",null,"2015-11-04",null,12.420000000000002,15.525,"Class 1 (Solar / Wind)",null,14.35,14.35,14.35,"Solar",2015,"2015-11-04","2015-11-04",1,"2015-12-03",22,0,"2015-12-04","2015-12-11",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-14",29,null,null,null,0,"n/a",null,null,null,null,30288,null,"Nov 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["John P Regish","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6A1550-2015","2640625","R1","R","54694102070","363441001","868448852","812942005","22","West St",null,null,"Hadley","MA","01035","WMECO","18G","18G4"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-20",null,8.5120000000000005,10.64,"Class 1 (Solar / Wind)",null,9.5,9.5,9.5,"Solar",2015,"2015-11-20","2015-11-20",1,"2015-12-10",15,0,"2015-12-10","2016-01-13",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-13",39,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"12/28/2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Claire A Day",null,"SIMP",null,"Carla","In Process",null,"6A1555-2015","2640698","R3","R","54997596069","957621000","894551002","680812005","8","Gross Ln",null,null,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-20",null,6.6239999999999997,8.2799999999999994,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-11-20","2015-11-20",1,"2015-12-11",16,1,"2015-12-11","2015-12-11",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-14",17,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"February 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Jonathan Ward-Miller",null,"SIMP",null,"Carla","In Process",null,"6A1595-2015","2649704","R1","R","54237884093","559541004","868738252","810352009","33","Tamarack Dr",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter",null,null,null,"2015-12-16",null,9.7200000000000006,12.15,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2015,"2015-12-16","2015-12-17",2,null,36,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,36,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"02/17/2021",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Susan E Mcintosh","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6A1606-2015","2661942","R1","R","54444206015","807531002","883962862","637432001","78","Country Rd",null,null,"Huntington","MA","01050","WMECO","19J","19J1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-24",null,1.8719999999999999,2.34,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-12-24","2015-12-28",3,"2016-01-06",10,0,"2016-01-06","2016-01-06",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-07",11,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"02/23/2016",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Helen L Sekulski","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6A1645-2016","2675082","R1","R","54519471049","084721006","866445022","435612004","64","Clark St ","Floor",1,"Easthampton","MA","01027","WMECO","15A","15A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-01-25",null,6.120000000000001,7.65,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2016,"2016-01-25","2016-01-25",1,"2016-02-01",6,0,"2016-02-01","2016-02-01",0,null,null,null,null,null,null,null,null,null,null,null,"2016-02-02",7,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["IGS Solar",null,"EXP",null,"Carla","In Process",null,"6A1652-2016","2677284",null,null,null,null,null,null,"267","River Rd",null,null,"Whately","MA","01093","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter",null,null,null,null,null,0,0,null,null,null,null,null,"Solar",2016,"2016-01-29","2016-01-29",1,null,4,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,null,null,null,"??","??",null,null,null,null,30288,null,"Summer 2016",null,"6A620158"]
["Conte Community School - City of Pittsfield School Dept.",null,null,null,null,"Completed",null,"6B4-2005",null,"G2","C","54761781079","045531000","890326812","263332005",null,"West Union St",null,null,"Pittsfield","MA","01201","WMECO","30B","30B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-01",7.2,{"$f":"AJ1684*0.8","v":7.2},9,"Class 1 (Solar / Wind)",null,9,9,9,"Solar",2005,"2005-01-26",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.",null,"n/a",null,null,0,"n/a",null,null,null,"2005-06-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering","13 kW three phase inverter.  < 25 kW three phase.  NO CAP",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Lynn A Webster",null,null,null,null,"Completed",null,"6B33-2008",null,"R1","R","54402781009","663531000","891805482","277232009","84","Cummings Ave",null,null,"Pittsfield","MA","01201","WMECO","30B","30B3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-01",2.2400000000000002,2.2399999999999998,2.8,"Class 1 (Solar / Wind)",null,3,3,3,"Solar",2008,"2008-10-03",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-10-03",null,"n/a",null,null,0,"n/a",null,null,null,"2009-02-23",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-10-03"]
["Savoy Wind Project - Newpath Energy - Chevron",null,"STD",null,"Carla","Cancelled",null,"6B44-2009",null,null,null,null,null,null,null,null,"Adams Rd",null,null,"Savoy","MA","01256","WMECO","18C","18C1","PTF"," ","Wind Turbine","wind farm","n/a",null,null,"n/a",null,null,null,"N/A",null,10000,10000,"8000 or 10000","Wind",2009,"2009-06-26",null,null,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc","needed",null,null,"cancld","cancld","Yes","Yes",null,null,null,null,"2010-07-01",null,"WDGWN902",2500,1817.74,{"$f":"CC1726-CB1726","v":-682.26},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Was on hold by Cust. Cancelled. Cust can't confirm design. Need design for Impact Study. Stand alone generation. New construction. Application has two options 8,000 kW or 10,000 kW. Highest option listed in Design Capacity.","Cancelled","needed","needed",null,null,null,"n/a - generator selling energy","project cancelled by WMECO due to no action taken by customer and no communication in over 2 years.  (new construction)",null,null,null,null,null,null,null,null,null,null,null,null,"N","cancelled by customer","TBD","future request",null,null,null,null,null,"23 kV",null,"future","future","future","N","Very Low","on hold per cust","no","no","TBD","TBD","TBD","TBD","TBD - new 23 kV primary metered service with DSCADA recloser and line extension, expect DTT",null,null,null,null,null,null,"On hold per customer.","needed","N",null,"FUTURE","Yes","Cancelled","no"]
["Anthony Jamula",null,"SIMP",null,null,"Completed",null,"6B67-2010",null,"R1","R","54286861083","782421004","892150432","222512007","670","Crane Ave",null,null,"Pittsfield","MA","01201","WMECO","15E","15E2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-11-01",2.3759999999999999,2.3760000000000003,2.97,"Class 1 (Solar / Wind)",null,2.97,2.97,2.97,"Solar",2010,"2010-02-25",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-02-25",null,"n/a",null,null,0,"n/a",null,null,null,"2010-11-09",null,null,"2010-04-01","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-03-01"]
["ALNASCO",null,"EXP",null,"Carla","Completed",null,"6B111-2011",null,"G2","C","54860016005","264233003","058883941","810452005","703","West Housatonic St",null,null,"Pittsfield","MA","01201","WMECO","30B","30B4","PTF"," ","Photovoltaic","Inverter","Private",null,null,"2011-09-14",263.92,263.92,329.9,"Class 2",null,300,300,300,"Solar",2011,"2011-09-02","2011-09-02",1,"2011-10-05",{"$f":"IF(AU1794=0,NETWORKDAYS(AR1794,$A$4),NETWORKDAYS(AR1794,AU1794))","v":24},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-02-07",113,"2012-02-29",null,null,"$1M / $1M","2014-12-13","No",null,null,"2012-06-01",null,null,"2011-10-01",null,"WDGSL118",900,4062.65,{"$f":"CC1794-CB1794","v":3162.65},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,70.3,"On line. Cust changed their switchgear. Service upgrade.",2012,"??","??",null,null,null,"net metering","This was Steel Realty",null,null,null,null,null,"ALNASCO\nAttn:  Seth Nash","703 West Housatonic Street","Pittsfield","MA","01201","(413) 442-1600 ext 333",4134969169,null,null,null,null,null,null,null,null,null,null,null," 413-448-6022 ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Mary Dockray Miller",null,"SIMP",null,null,"Completed",null,"6B123-2011",null,"R1","R","54243861044","458421005","892341742","423312002","22","Boat Ln",null,null,"Richmond","MA","01254","WMECO","30B","30B2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-12-07",5.0960000000000001,5.0960000000000001,6.37,"Class 1 (Solar / Wind)",null,5.59,5.59,5.59,"Solar",2011,"2011-12-07","2011-12-08",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-20",{"$f":"IF(BL1806=0,NETWORKDAYS(AR1806,$A$4),NETWORKDAYS(AR1806,BL1806))","v":10},null,null,null,0,"n/a",null,null,null,"2012-03-07",null,null,"2011-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2011-12-20"]
["Lee Farm (system #1) - Town of Lee renamed Lee Recreation Area","Broadway Electrical, Inc.","STD",null,"Carla","Withdrawn","2014-06-27","6B145-2012",null,"new svc","C",null,null,null,null,"415","Stockbridge Rd",null,null,"Lee","MA","01238","WMECO","16B","16B5","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,704.35200000000009,880.44,"N/A",null,750,750,"1000 or 750","Solar",2012,"2012-03-21","2012-03-22",2,"2013-03-27","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-06-26","canc","2013-07-01","??",null,"$1M / $1M","2014-12-31","Yes","Yes",null,null,"canc",null,"2012-05-01",null,"WDGSL238",2500,1689.99,-810.01,null,null,null,null,null,null,null,null,null,null,"See 6B144-2012",null,null,null,"2013-01-09","2013-07-08",24,"WDSLD238",51000,8054.25,"2013-05-24","2013-06-04","2013-06-07",0,727994,627581,100413,null,null,null,null,null,null,null,null,null,"Impact Study required joint with 6B144-2012. Int Cust changed inverters 021413, revised study, waited for updated project info . Detailed Study required. Third party owned. Stand alone generation. New construction. Application has two options 1,000 kW or 750 kW. Customer's current design option listed in Design Capacity. Received signed Detail Study agreement 052413, waiting for first check.  Plus/minus 10% sent to cust 6/7/13. Sent Exhibit G & H for signature 6/28/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13.  Per conf call with  Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps.  Until these are provided, we will not prepare another tentative construction schedule.\nInterconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time.\nIt is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response.  Withdrawn 6/27/14. Int Customer owes WMECO money.","withdrawn","??","??",null,null,null,"net metering",null,"Town of Lee\nAttn: Robert Nason","32 Main Street","Lee","MA",1238,"Broadway Electrical, Inc.\nAttn: Jonathan Wienslaw","295 Freeport Street","Boston","MA","02210","617-822-8831","617-288-4169","N","Fourth Quarter 2013","Second Quarter 2014","2013-06-03","2013-05-30",null,null,null,null,"23 KV","ION 8600","future","project # WD00036 \n4D 617 6B320369  DXO  \nsubstation DWN32013 ADDS0 \nWR# 2145742\n\n",2142560,"N","High","complete","yes","ordered - 2 reclosers, 3 controls","Ray Galaska","2013-11-01","2013-12-15","2014-01-10","New 23 kV primary metered service with DSCADA recloser, phone DTT",627581,"X","X",null,null,"X","Status = 50, hours = 387. Deadline for upgrade estimate monies 8/30/13 for construction times to be valid.",null,"Y",null,null,null,"withdrawn"]
["Darren Ovitsky",null,"SIMP",null,null,"Completed",null,"6B167-2012",null,"R1","R","54336906003","058531005","893074022","486232000","149","Narragansett Ave",null,null,"Lanesboro","MA","01237","WMECO","15E","15E2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-06-18",2.0680000000000001,2.0680000000000001,2.585,"Class 1 (Solar / Wind)",null,2.3650000000000002,2.3650000000000002,2.3650000000000002,"Solar",2012,"2012-06-18","2012-06-18",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-07-10",{"$f":"IF(BL1850=0,NETWORKDAYS(AR1850,$A$4),NETWORKDAYS(AR1850,BL1850))","v":17},null,null,null,0,"n/a",null,null,null,"2012-08-21",null,null,"2012-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-07-10"]
["Renee & Donald Far","Astrum Solar","SIMP",null,null,"Completed",null,"6B188-2012",null,"R1","R","54920991098","642341009","893073632","469642007","65","Golden Hill Rd",null,null,"Lenoxdale","MA","01242","WMECO","17G","17G3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-09-13",4.2,4.2,5.25,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2012,"2012-09-13","2012-09-13",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-10-03",{"$f":"IF(BL1871=0,NETWORKDAYS(AR1871,$A$4),NETWORKDAYS(AR1871,BL1871))","v":15},null,"2012-10-17",null,0,"n/a",null,null,null,"2012-12-03",null,null,"2012-10-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-10-03"]
["Seth Nash (new 6B257-2013)","??","SIMP",null,null,"Cancelled",null,"6B224-2012",null,"G0",null,"54719402091","371641002","890063302","977452007","103","Hawthorne Ave",null,null,"Pittsfield","MA","01201","WMECO","30B","30B4","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,19.584000000000003,24.48,"N/A",null,null,null,21.93,"Solar",2012,"2012-10-23","2012-10-24",2,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"??",null,0,"n/a",null,null,null,null,null,null,"2012-11-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - new application submitted"]
["Kimberly Dean","SolarCity Corp","SIMP",null,null,"Completed",null,"6B245-2012",null,"R1","R","54727071011","876521002","893148752","352612000","137","Jones Ave",null,null,"Pittsfield","MA","01201","WMECO","30B","30B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-12-19",3.0720000000000001,3.0720000000000001,3.84,"Class 1 (Solar / Wind)",null,3,3,3,"Solar",2012,"2012-12-19","2012-12-20",2,"n.r.","n/a",null,null,null,null,null,null,null,null,"n.r.","n.r.",null,null,null,null,null,"2013-02-07",37,null,"2013-03-28",null,0,"n/a",null,null,"2013-08-07","2013-08-09",{"$f":"IF(BV1928=0,NETWORKDAYS(BU1928,$A$4),NETWORKDAYS(BU1928,BV1928))","v":3},null,"2/30/2012",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2013-02-07"]
["George Valli","Kilowatt Systems, LLC","SIMP",null,null,"Completed",null,"6B256-2013",null,"R1","R","54577005044","685831002","893072292","515732002","123","Lucia Dr",null,null,"Pittsfield","MA","01201","WMECO","30B","30B2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-01-22",6.4720000000000004,6.4720000000000004,8.09,"Class 1 (Solar / Wind)",null,7.0949999999999998,7.0949999999999998,7.0949999999999998,"Solar",2013,"2013-01-22","2013-01-22",1,"n.r.","n/a",null,null,null,null,null,null,null,null,"n.r.","n.r.",null,null,null,null,null,"2013-03-13",37,null,"2013-03-18",null,0,"n/a",null,null,null,"2013-04-16",null,null,"2013-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2013-03-13"]
["Thomas Renton Jr. (was 6B202-2012)","Astrum Solar","SIMP",null,null,"Completed",null,"6B278-2013",null,"R1","R","54796326031","900353005","893151002","503612000","163","Cheshire Rd",null,null,"Pittsfield","MA","01201","WMECO","19A","19A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-11-08",4.2,{"$f":"AJ1963*0.8","v":4.2},5.25,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2013,"2013-05-07","2013-05-07",1,"2013-05-20",10,0,"2013-05-21","2013-05-21",0,null,null,null,null,null,null,null,null,null,null,null,"2013-05-22",{"$f":"IF(BL1963=0,NETWORKDAYS(AR1963,$A$4),NETWORKDAYS(AR1963,BL1963))","v":12},null,"2013-10-28",null,0,"n/a",null,null,"2013-01-14","2013-12-05",{"$f":"IF(BV1963=0,NETWORKDAYS(BU1963,$A$4),NETWORKDAYS(BU1963,BV1963))","v":234},22,"2013-07-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-01-14"]
["Brian Smith",null,"SIMP",null,"Erik","Completed",null,"6B308-2013","2270171","R1","R","54604771006","317921007","890987412","089222008","694","Peru Rd",null,null,"Hinsdale","MA","01235","WMECO","18C","18C2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-10-07",3.6,3.6,4.5,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2013,"2013-09-18","2013-09-18",1,"2013-10-03",12,3,"2014-10-04","2014-10-04",0,null,null,null,null,null,null,null,null,null,null,null,"2013-10-04",13,null,null,null,0,"n/a",null,null,"2014-01-28","2014-02-21",19,16,"2013-10-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-10-04"]
["Janet Kalas",null,"SIMP",null,"Erik","Completed",null,"6B335-2013","2270177","R1","R","54252481007","923331008","89356475","235922008","255","Prospect St",null,null,"Lee","MA","01238","WMECO","16B","16B5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-01",3.6120000000000001,3.6120000000000001,4.5149999999999997,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2013,"2013-11-04","2013-11-06",3,"2014-01-14",52,24,"2014-01-16","2014-01-16",0,null,null,null,null,null,null,null,null,null,null,null,"2014-01-16",54,null,null,null,0,null,null,null,"2014-04-02","2014-04-10",7,4,"2014-02-19",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-01-16"]
["Guidewire, Inc. (see 6B398-2014)","Jon Macht","SIMP",null,"Erik","Cancelled","2014-05-22","6B365-2014","2274723","R1","R","54347981011","489631002","987993932","179532009","114","Balance Rock Rd","Apt","Rear","Lanesboro","MA","01237","WMECO","30B","30B5","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,9.0400000000000009,11.3,"N/A",null,9,9,9,"Solar",2014,"2014-01-15","2014-01-17",3,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,0,"n/a",null,null,null,null,"canc",null,"2014-06-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - new application submitted"]
["Robert Newton",null,"EXP",null,"Erik","Cancelled","2014-04-22","6B369-2014","2283574","R3","R","54004661005","627321006","890677982","717112009","375","Stockbridge Rd",null,null,"Lee","MA","01238","WMECO","16B","16B5","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,14.200000000000001,17.75,"n/a",null,15.265000000000001,15.265000000000001,15.265000000000001,"Solar",2014,"2014-02-05","2014-02-05",1,"2014-02-19",11,6,null,null,null,null,null,null,null,"2014-02-20",null,25,null,null,null,null,null,"canc",null,null,null,null,null,null,null,null,null,"canc",null,"2014-03-28",null,"6B420099",300,442.18,{"$f":"CC2054-CB2054","v":142.18},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Application Complete.  Screening email sent 2/25.  WMECO needs information. Customer cancelled project.","Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - new application submitted"]
["Roma Bernstein","SolarCity Corp","SIMP",null,"Erik","Cancelled","2014-04-30","6B391-2014","2309349","R1","R","54344381041","250331002","979964352","010922003","65","Harding St",null,null,"Pittsfield","MA","01201","WMECO","30B","30B3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-04-08",null,2.4000000000000004,3,"Class 1 (Solar / Wind)",null,3.65,3.65,3.65,"Solar",2014,"2014-04-08","2014-04-08",1,"2014-04-21",10,0,"2014-04-22","2014-04-29",0,null,null,null,null,null,null,null,null,null,null,"2015-03-31","2014-04-29","canc",null,"needed",null,0,"n/a",null,null,null,null,"canc",null,"2014-06-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled"]
["Kelley Khoury Cady",null,"SIMP",null,"Erik","Cancelled","2014-10-27","6B430-2014","2394849","R1","R","54786681049","716421007","960524942","575212004","21","Ann Dr",null,null,"Pittsfield","MA","01201","WMECO","19A","19A1","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,8,10,"n/a",null,10,10,10,"Solar",2014,"2014-09-11","2014-09-11",1,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,"canc",null,"2014-08-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled"]
["Alfred Soohoo","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B448-2014","2420077","R1","R","54727561086","848221007","894171050","354212007","41","Imperial Ave",null,null,"Pittsfield","MA","01201","WMECO","19A","19A2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-24",4.08,4.08,5.0999999999999996,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2014,"2014-10-24","2014-10-24",1,"2014-11-14",16,6,"2014-11-17","2014-12-02",0,null,null,null,null,null,null,null,null,null,null,"2015-02-10","2014-12-02",28,null,"2015-04-14",null,0,"n/a",null,null,"2015-04-03","2015-04-21",13,1,"2014-10-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-02"]
["Terence Chiaretto","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B471-2014","2454975","R1","R","54899991053","162341004","894198902","786842003","134","Oak Hill Rd",null,null,"Pittsfield","MA","01201","WMECO","15E","15E2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-16",4.8960000000000008,4.8960000000000008,6.12,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2014,"2014-12-16","2014-12-16",1,"2015-01-05",15,0,"2015-01-06","2015-01-08",0,null,null,null,null,null,null,null,null,null,null,"2015-06-09","2015-01-08",18,null,"2015-05-18",null,0,"n/a",null,null,"2015-05-18","2015-06-12",20,0,"2015-02-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-01-07"]
["Charles Frambach, Jr.","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B505-2015","2515691","R1","R","54062471073","257721004","894715662","50622006","4","Pinehurst Ave","Floor",1,"Pittsfield","MA","01201","WMECO","30B","30B5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-17",3.2639999999999998,3.2640000000000002,4.08,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-04-17","2015-04-17",1,"2015-06-04",35,15,"2015-06-05","2015-06-05",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-05",36,null,"2015-06-17",null,0,"n/a",null,null,"2015-06-04","2015-10-05",88,26,"2015-06-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-08"]
["David Young","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B527-2015","2528806","G0","C",null,null,null,null,"1179","South Washington State Rd",null,null,"Washington","MA","01223","WMECO","19J","19J3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-11",3.7440000000000002,3.7439999999999998,4.68,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-05-11","2015-05-12",2,"2015-06-01",16,8,"2015-06-02","2015-07-15",9,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15",48,null,"2015-12-15",null,0,"n/a",null,null,"2015-09-17","2015-12-29",74,60,"2015-07-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15"]
["David Hinckley","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B552-2015","2540799","R1","R","54505455022","074821003","894526362","184912009","35","Newton Ave",null,null,"Pittsfield","MA","01201","WMECO","30B","30B5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-03",7.6959999999999997,7.6959999999999997,9.6199999999999992,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-06-03","2015-06-04",2,"2015-06-26",18,0,"2015-06-29","2015-07-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15",31,null,"2015-08-27",null,0,"n/a",null,null,"2015-08-17","2015-10-01",34,8,"2015-08-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15"]
["Charles Lane","NRG Home Solar","SIMP",null,"Erik","In Process",null,"6B561-2015","2550412","R3","R","54677081002","250231003","866234992","623522009","376","Summit Hill Rd",null,null,"Washington","MA","01223","WMECO","18C","18C2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-11",null,5.152000000000001,6.44,"Class 1 (Solar / Wind)",null,5.75,5.75,5.75,"Solar",2015,"2015-06-11","2015-06-11",1,"2015-07-07",19,0,"2015-07-08","2015-07-24",7,null,null,null,null,null,null,null,null,null,null,null,"2015-07-24",32,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-24"]
["Donald Mattie, Sr.","Sunnova Energy Corp","SIMP",null,"Erik","Completed",null,"6B593-2015","2554992","R1","R","54346125065","404741004","881626332","356452002","405","Colebrook River Rd",null,null,"Tolland","MA","01034","WMECO","19J","19J4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-02",4.992,4.9920000000000009,6.24,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-07-02","2015-07-02",1,"2015-07-31",22,0,"2015-08-03","2015-08-21",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-24",38,null,"2015-12-11",null,0,"n/a",null,null,"2015-12-11","2016-02-02",38,31,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-25"]
["Barbara Seddon","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6B618-2015","2564768","R1","R","54307981019","343731000","980023812","985532000","27","Dewey Ave","Floor",1,"Pittsfield","MA","01201","WMECO","30B","30B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-27",3.536,3.536,4.42,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-07-27","2015-07-27",1,"2015-09-08",32,8,"2015-09-09","2015-09-28",0,null,null,null,null,null,null,null,null,null,null,null,"2015-09-29",47,null,"2015-12-29",null,0,"n/a",null,null,"2015-11-23","2015-12-31",29,24,"2015-08-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-09-29"]
["Prem Management LLC",null,"EXP",null,"Carla","In Process",null,"6B640-2014","2574156","G0","C","54664817046","964953003","890585382","66829007","1032","South St",null,null,"Pittsfield","MA","01201","WMECO","30B","30B2","PTF"," ","Photovoltaic","Inverter","private","needed",null,null,null,51.204000000000001,64.004999999999995,"Class 1 (Solar / Wind)",null,54,54,54,"Solar",2015,"2015-08-12","2015-08-13",2,"2015-09-23",31,5,null,null,null,null,null,null,null,"2015-09-24","2015-12-29",47,"2015-12-30","2015-12-30",0,null,"2015-12-30",101,null,null,null,"??","??",null,null,null,null,30288,null,"2015-07-01",null,"6B520604",300,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"??"]
["Ashley Stump","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6B658-2015","2588730","R2","R","54849071055","840721006","884380342","266512004","31","Garfield Ave",null,null,"Pittsfield","MA","01201","WMECO","19A","19A7","PTF"," ","Photovoltaic","Inverter","private","needed",null,"2015-08-28",null,11.856000000000002,14.82,"Class 1 (Solar / Wind)",null,14.25,14.25,14.25,"Solar",2015,"2015-08-28","2015-09-01",3,"2015-10-15",35,0,"2015-10-15","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",36,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-10-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-22"]
["CG Hinsdale Energy Development, LLC","??","STD","neg, GRP","Carla","In Process",null,"6B674-2015","2586673",null,null,null,null,null,null,"30","Frank Schnopp Rd",null,null,"Hinsdale","MA","01235","WMECO","18C","18C2","PTF"," ","Photovoltaic","Inverter","private","needed",null,null,null,0,0,null,null,1000,1000,"995, 995, 995, 1000, 1000, 1000","Solar",2015,"2015-09-08","2015-09-08",1,"2015-11-16",50,27,null,null,null,null,null,null,null,"2015-11-17",null,null,null,null,null,null,null,107,null,"??",null,"??","??",null,null,null,null,30288,null,"8/15/2016",null,"6B520701",4500,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2016-01-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Q3 2016",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Q3 2016",null,"Q4 2016"]
["Schuyler Goodrich","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6B715-2015","2610391","R3","R","54350781084","566531005","892294362","528332006","76","Birch Grove Rd",null,null,"Hancock","MA","01237","WMECO","30B","30B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-02",null,6.6560000000000006,8.32,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-10-02","2015-10-05",2,"2015-10-19",12,0,"2015-10-19","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",12,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-22"]
["Jeffrey Thompson","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6B731-2015","2614037","R1","R","54336664065","465292009","891681882","266805003","113","Otis Stage Rd",null,null,"Blandford","MA","01008","WMECO","19J","19J2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-10-13",null,8.32,10.4,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-10-13","2015-10-13",1,"2015-11-13",24,0,"2015-11-13","2015-11-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-17",26,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Donna Whalen","Sunnova Energy Corp","SIMP",null,"Carla","In Process",null,"6B753-2015","2618486","R1","R","54134091073","781731004","893175682","461732006","11","Hollow Rd",null,null,"Lanesboro","MA","01224","WMECO","19A","19A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-10-27",null,9.1519999999999992,11.44,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-10-27","2015-10-28",2,"2015-12-04",29,4,"2015-12-07","2015-12-11",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-14",35,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Donald Atwater","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6B780-2015","2632735","R1","R","54553202094","773541005","977698512","792152008","78","Elaine Ave",null,null,"Dalton","MA","01226","WMECO","19A","19A2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-12",null,4.3680000000000003,5.46,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-11-12","2015-11-12",1,"2015-12-07",18,0,"2015-12-07","2015-12-07",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-09",20,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Mark Lausier","SolarCity Corp","SIMP",null,"Carla"," In Process",null,"6B810-2015","2644441","R1","R","54740381058","056331009","893452972","362722004","21","Fairfield St",null,null,"Pittsfield","MA","01201","WMECO","30B","30B3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,null,null,5.6159999999999997,7.02,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-12-07","2015-12-07",1,"2015-12-21",11,0,"2015-12-21","2015-12-21",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-22",12,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-06",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Brian C Uliasz","Sunnova Energy Corp","SIMP",null,"Carla","In Process",null,"6B813-2015","2646165","R1","R","54785407024","170421002","977728422","085312000","600","Crane Ave",null,null,"Pittsfield","MA","01201","WMECO","15E","15E2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-12-09",null,8.32,10.4,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-12-09","2015-12-10",2,"2015-12-23",11,0,"2016-01-05","2016-01-05",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-05",20,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Katherine Wright","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6B844-2015","2661963","R1","R","54506274018","953621000","891163082","286512004","40","Herie Ave",null,null,"Pittsfield","MA","01201","WMECO","19A","19A7","PTF"," ","Photovoltaic","Inverter",null,null,null,"2015-12-24",null,3.3280000000000003,4.16,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2015,"2015-12-24","2015-12-28",3,null,30,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["William O'Brien",null,"SIMP",null,"Carla","In Process",null,"6B866-2016","2670367","R1","R","54389702002","574841003","881697082","500752008","148","Town Hill Rd",null,null,"Sandisfield","MA","01255","WMECO","19J","19J4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-01-14",null,6.36,7.95,"Class 1 (Solar / Wind)",null,6.75,6.75,6.75,"Solar",2016,"2016-01-14","2016-01-14",1,"2016-01-19",4,0,"2016-01-19","2016-01-19",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-22",7,null,null,null,0,"n/a",null,null,null,null,30288,null,"2016-01-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Stacey A. Lennard (was & Stephen Saxenian)",null,"OTHER",null,null,"Completed",null,"6F6-2003",null,"R1","R","54782781090","023631001","888508392","705432008","79","Teawaddlle Hill Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-09-22",0.88880000000000003,0.88880000000000003,1.111,"Class 1 (Solar / Wind)",null,0.999,0.999,0.999,"Solar",2003,"n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2003-12-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2003,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["Mauricia Alvarez (was Sherrill Hogen & Carl Doerner)",null,null,null,null,"Completed",null,"6F24-2005",null,"R1","R","54290786094","478741003","890835142","848552008","137","South Shirkshire Rd",null,null,"Conway","MA","01341","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"MIMO - needed",0,0,null,"Class 1 (Solar / Wind)",null,1.8,1.8,1.8,"Solar",2005,"2005-08-25",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2005-09-06",null,"n/a",null,null,0,"n/a",null,null,null,"2006-01-31",null,null,null,"2014-10-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2006,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N"]
["John Ward",null,null,null,null,"Removed",null,"6F35-2006",null,"R1","R","54392771093","797921004","890835442","918322008","4","Grove St",null,null,"Gill","MA","01354","WMECO","21C","21C1","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"N/A",null,null,1.2,1.2,"Solar",2006,"2006-10-05",null,null,"n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006-10-06",null,"n/a",null,null,"n/a","n/a",null,null,null,"2006-10-23",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2006 - removed",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","removed"]
["Phurbu Wangdu  (was Rural Dev)",null,null,null,null,"Completed",null,"6F66-2008",null,"R1","R","54887091080","076653003","891865142","896988002","32","Solar Way",null,null,"Greenfield","MA","01301","WMECO","22B","22B3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-06-08",2.4300000000000002,0,null,"Class 1 (Solar / Wind)",null,2.4300000000000002,2.4300000000000002,2.4300000000000002,"Solar",2008,"2008-02-19",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-02-20",null,"n/a",null,null,0,"n/a",null,null,null,"2010-01-28",null,null,null,"2010-05-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2010,null,null,null,null,null,"net metering","new construction",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-11-25"]
["Benjamin Welcome ( was Laurence & Tammy Stearns)",null,null,null,null,"Completed",null,"6F91-2008",null,"R1","R","54239996044","043341007","891759432","550742006","1158A","Millers Falls Rd",null,null,"Northfield","MA","01360","WMECO","21B","21B8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-29",2.9,{"$f":"AJ2677*0.8","v":0},null,"Class 1 (Solar / Wind)",null,2.9,2.9,2.9,"Solar",2008,"2008-09-09",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-09-09",null,"n/a",null,null,0,"n/a",null,null,null,"2009-02-13",null,null,null,"2014-09-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-09-09"]
["Albert G. LaValley  (wind see 6F100S-2008)",null,null,null,null,"Completed",null,"6F100W-2008",null,"R1","R","54391481074","332431005","891808382","191032006","556","Huckle Hill Rd",null,null,"Bernardston ","MA","01337","WMECO","21B","21B8"," ","non-PTF","Wind Turbine","Inverter","No Cap","n/a",null,"see 6F100S-2008",1,null,null,"Class 1 (Solar / Wind)",null,1,1,1,"Wind",2008,"2008-12-18",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2008-12-22",null,"n/a",null,null,0,"n/a",null,null,null,"2009-06-17",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2008-12-22"]
["Kim Reardon",null,"SIMP",null,null,"Completed",null,"6F134-2009",null,"R1","R","54960402048","100641009","891863932","936252001","1231","West Rd",null,null,"Ashfield","MA","01330","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-02-10",9.3000000000000007,0,null,"Class 1 (Solar / Wind)",null,9.3000000000000007,9.3000000000000007,9.3000000000000007,"Solar",2009,"2009-07-16",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-07-17",null,"n/a",null,null,0,"n/a",null,null,null,"2009-10-09",null,null,"2009-09-15","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-07-17"]
["Biscuit Hill Farm",null,"EXP",null,"Cindy","Completed",null,"6F155-2010",null,"R1","R","54780502084","284641005","890835352","655352006","55","Shelburne Center Rd",null,null,"Shelburne","MA","01370","WMECO","22B","22B6","PTF"," ","Photovoltaic","Inverter","Private",null,null,"2010-04-23",15.624000000000001,15.624000000000002,19.53,"Class 1 (Solar / Wind)",null,24.2,24.2,24.2,"Solar",2010,"2010-04-06",null,null,"2010-04-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-04-27",null,"Yes",null,null,0,"n/a","Yes",null,null,"2010-05-21",null,null,"5/2010","no","WDGSL007",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line.",2010,"n/a","n/a",null,null,null,"net metering",null,null,null,null,null,null,"Attn:  Beth Manning","55 Shelburne Center Road","Shelburne Falls","MA","01370",4136259967,4136250019,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2010-04-28"]
["Michael Archer","Sun Run","SIMP",null,null,"Completed",null,"6F181-2010",null,"R1","R","54835602012","721841003","891867282","735552009","80","Pickett Ln",null,null,"Greenfield","MA","01301","WMECO","22B","22B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-09-15",5.5439999999999996,{"$f":"AJ2766*0.8","v":5.5440000000000005},6.93,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2010,"2010-09-15",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2010-09-24",null,"n/a","2010-10-04",null,0,"n/a",null,null,null,"2011-01-26",null,null,"2010-09-30","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2010-09-24"]
["Walton Congdon",null,"SIMP",null,null,"Completed",null,"6F214-2011",null,"R1","R","54708391073","152931004","892341902","793042006","16","Warwick Rd",null,null,"Northfield","MA","01360","WMECO","33P","33P1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-04-18",1.44,1.4400000000000002,1.8,"Class 1 (Solar / Wind)",null,1.52,1.52,1.52,"Solar",2011,"2011-04-05","2011-04-05",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-04-20",12,null,null,null,0,"n/a",null,null,null,"2011-05-20",null,null,"2011-05-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-04-20"]
["John Hoffman (was Gloria Easton)",null,"SIMP",null,null,"Completed",null,"6F237-2011",null,"R1","R","54083666081","985141005","893565202","092242005","452","Colrain Shelburne Rd",null,null,"Shelburne Falls","MA","01370","WMECO","29R","29R2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-12-20",8.24,8.24,10.3,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2011,"2011-07-06","2011-07-06",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-07-11",{"$f":"IF(BL2823=0,NETWORKDAYS(AR2823,$A$4),NETWORKDAYS(AR2823,BL2823))","v":4},null,null,null,0,"n/a",null,null,null,"2011-08-09",null,null,"2011-07-19","2013-12-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2011,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-07-11"]
["Christian Elwell",null,"EXP",null,"Erik","Completed",null,"6F248-2011",null,"G0","C","54373791052","535241003","890684422","797242004","888","Shelburne Falls Rd",null,null,"Conway","MA","01341","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","Private",null,null,"2011-08-12",19.968,19.968000000000004,24.96,"Class 1 (Solar / Wind)",null,22.8,22.8,22.8,"Solar",2011,"2011-08-12","2011-08-12",1,"2011-10-26",{"$f":"IF(AU2834=0,NETWORKDAYS(AR2834,$A$4),NETWORKDAYS(AR2834,AU2834))","v":54},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-11-17",70,"2011-11-23",null,null,0,"n/a","Yes",null,null,"2012-02-27",null,null,"2011-09-10",null,"WDGSL115",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line.",2012,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Christian Elwell","888 Shelburne Falls Road","Conway","MA","01341",4133694066,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Tim & Lise Coppinger",null,"SIMP",null,null,"Completed",null,"6F278-2011",null,"R3","R","54820481075","765431006","892341342","872922005","151","North Leverett Rd","Apt","B","Leverett","MA","01054","WMECO",{"$f":"LEFT(Y2864,3)","v":"21C"},"21C7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2011-11-16",4.6079999999999997,4.6079999999999997,5.76,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2011,"2011-11-16","2011-11-17",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-12-15",22,null,null,null,0,"n/a",null,null,null,"2012-01-09",null,null,"2011-11-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-12-15"]
["Mark Shapiro",null,"SIMP",null,null,"Completed",null,"6F294-2012",null,"R1","R","54251961058","754521009","892922402","939312004","42","Conwell Rd",null,null,"Worthington","MA","01098","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-10-15",6,6,7.5,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2012,"2012-01-09","2012-01-10",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-03-19",51,null,null,null,0,"n/a",null,null,null,"2013-01-17",null,null,"2012-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-03-19"]
["Bruce Thomas",null,"SIMP",null,null,"Withdrawn","2013-07-12","6F312-2012",null,"R1","R","54497502047","237641008","883388822","462352002","75","Boyden Rd",null,null,"Conway","MA","01341","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,4.8960000000000008,6.12,"N/A",null,6,null,6,"Solar",2012,"2012-04-02","2012-04-03",2,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-07-11",73,null,null,null,0,"n/a",null,null,null,null,null,null,"2012-05-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"withdrawn",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,"withdrawn","2012-07-11"]
["Dena Willmore",null,"SIMP",null,null,"Completed",null,"6F351-2012",null,"R1","R","54880891072","175241003","893152642","383442005",null,"Maynard Hill Rd","Lot ","Barn","Buckland","MA","01338","WMECO","29R","29R1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-08-14",7.68,7.68,9.6,"Class 1 (Solar / Wind)",null,9.8000000000000007,9.8000000000000007,9.8000000000000007,"Solar",2012,"2012-08-14","2012-08-15",2,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-10-24",52,null,null,null,0,"n/a",null,null,null,"2012-12-03",null,null,"9/31/12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1997504,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-11-19"]
["Sarah Pick",null,"SIMP",null,null,"Completed",null,"6F373-2012",null,"R1","R","54165471061","008721002","893151732","148812004","25","Union St ",null,null,"Montague","MA","01351","WMECO","21C","21C7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-09-20",2.7440000000000002,2.7440000000000002,3.43,"Class 1 (Solar / Wind)",null,3.01,3.01,3.01,"Solar",2012,"2012-09-20","2012-09-20",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-10-09",14,null,null,null,0,"n/a",null,null,null,"2012-11-21",null,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2012-10-09"]
["Conor Power (addition to 6F138-2009)",null,"SIMP",null,null,"Completed",null,"6F401-2012",null,"R1","R","54271502023","383641004","891864222","134452001","181","Meadow Rd",null,null,"Montague","MA","01351","WMECO","21C","21C7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-10-12",1.764,1.7640000000000002,2.2050000000000001,"Class 1 (Solar / Wind)",null,9.3000000000000007,3.3,"3.3 kw add (9.3 kW total)","Solar",2012,"2012-11-19","2012-11-20",2,"n.r.","n/a",null,null,null,null,null,null,null,null,"n.r.","n.r.",null,null,null,null,null,"2013-01-16",43,null,null,null,0,"n/a",null,null,"2013-08-26","2013-08-30",{"$f":"IF(BV2986=0,NETWORKDAYS(BU2986,$A$4),NETWORKDAYS(BU2986,BV2986))","v":5},null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"n/a see 6F138-2009"]
["Janice Frey",null,"SIMP",null,null,"Completed",null,"6F407-2012",null,"R1","R","54882171028","666621009","893151522","918612000","10","Old Sunderland Rd",null,null,"Montague","MA","01351","WMECO",{"$f":"LEFT(Y2992,3)","v":"21C"},"21C7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-12-07",4.08,4.08,5.0999999999999996,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2012,"2012-12-07","2012-12-13",5,"n.r.","n/a",null,null,null,null,null,null,null,null,"n.r.","n.r.",null,null,null,null,null,"2013-01-22",33,null,null,null,0,"n/a",null,null,null,"2013-06-03",null,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2013-01-22"]
["Harland Hoisington (new 6F535-2014)",null,"SIMP",null,null,"Cancelled","2014-01-23","6F434-2013",null,"R1","R","54191134022","912782003","883521502","876194000","571B","Millers Falls Rd",null,null,"Northfield","MA","01360","WMECO","21B","21B8"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",null,0.22857142857142856,0.2857142857142857,"N/A",null,9.8000000000000007,null,9.8000000000000007,"Solar",2013,"2013-02-07","2013-02-07",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-03-21","canc",null,null,null,0,"n/a",null,null,"2014-01-10",null,null,null,"2013-03-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,"cancelled - new application submitted","2013-03-21"]
["Jack Hayden",null,"SIMP",null,null,"Completed",null,"6F464-2013",null,"R1","R","54380661066","734321009","893245502","413112002","131","Charlemont Rd",null,null,"Buckland","MA","01338","WMECO","29R","29R1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-06-20",7.9960000000000004,7.9959999999999996,9.9949999999999992,"Class 1 (Solar / Wind)",null,9.9949999999999992,9.9949999999999992,9.9949999999999992,"Solar",2013,"2013-06-13","2013-06-17",3,"2013-06-26",10,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-06-27",11,null,null,null,0,"n/a",null,null,"2013-09-23","2013-09-27",5,null,"2013-08-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-06-27"]
["Annie Chappell",null,"SIMP",null,null,"Completed",null,"6F486-2013",null,"R1","R","54926091034","430831005","892343022","244532002","25","Glen Rd",null,null,"Northfield","MA","01360","WMECO","33P","33P1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-15",3.68,3.6799999999999997,4.5999999999999996,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2013,"2013-09-03","2013-09-03",1,"2013-09-16",{"$f":"IF(AU3071=0,NETWORKDAYS(AR3071,$A$4),NETWORKDAYS(AR3071,AU3071))","v":10},0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-09-17",{"$f":"IF(BL3071=0,NETWORKDAYS(AR3071,$A$4),NETWORKDAYS(AR3071,BL3071))","v":11},null,null,null,0,"n/a",null,null,"2013-09-26","2013-10-01",{"$f":"IF(BV3071=0,NETWORKDAYS(BU3071,$A$4),NETWORKDAYS(BU3071,BV3071))","v":4},null,"2013-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-09-17"]
["Thomas Liimatainen",null,"SIMP",null,"Carla","Completed",null,"6F499-2013",null,"R1","R","54400402012","442641003","884363082","250252009","44","Curtis Rd",null,null,"Chesterfield","MA","01012","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2013-10-16",1.6,1.6,2,"Class 1 (Solar / Wind)",null,1.9039999999999999,1.9039999999999999,1.9039999999999999,"Solar",2013,"2013-10-16","2013-10-16",1,"2013-11-07",17,3,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-11-07",17,null,null,null,0,"n/a",null,null,"2013-12-19","2013-12-31",9,0,"2013-10-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-11-07"]
["Franklin Land Trust",null,"SIMP",null,"Erik","Completed",null,"6F544-2014","2290733","R1","R","54838446086","356621007","976745163","199712001","5","Mechanic St",null,null,"Shelburne Falls","MA","01370","WMECO","29R","29R1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-03-10",7.4880000000000004,7.4879999999999995,9.36,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2014,"2014-02-26","2014-02-26",1,"2014-03-12",11,1,"2014-03-12","2014-03-12",0,null,null,null,null,null,null,null,null,null,null,"2014-05-27","2014-03-12",11,null,null,null,0,"n/a",null,null,"2014-06-18","2014-06-30",9,0,"2014-03-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-03-12"]
["Ronald Weaver","SolarCity Corp","SIMP",null,"Carla","Completed",null,"6F565-2014","2330637","R1","R","54634471064","005821005","894192052","717812004","32","Rockland Rd",null,null,"Greenfield","MA","01301","WMECO","21C","21C1","PTF"," ","Photovoltaic","Inverter","Private","na per CADMUS",null,"2014-05-19",8.4,8.4,10.5,"Class 1 (Solar / Wind)",null,10.9,10.9,10.9,"Solar",2014,"2014-05-19","2014-05-19",1,"2014-06-02",11,2,"2014-06-04","2014-06-04",0,null,null,null,null,null,null,null,null,null,null,"2014-06-14","2014-06-04",{"$f":"IF(BL3149=0,NETWORKDAYS(AR3149,$A$4),NETWORKDAYS(AR3149,BL3149))","v":13},null,"2015-05-11",null,0,"n/a",null,null,"2015-05-11","2015-06-26",{"$f":"IF(BV3149=0,NETWORKDAYS(BU3149,$A$4),NETWORKDAYS(BU3149,BV3149))","v":35},0,"2014-07-19",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-06-04"]
["Irene Clancy",null,"SIMP",null,"Erik","Completed",null,"6F578-2014","2348176","R1","R","54445835051","199041000","894062352 ","906142009","5","Meadowwood Dr",null,null,"South Deerfield","MA","01373","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-23",2.86,2.8600000000000003,3.5750000000000002,"Class 1 (Solar / Wind)",null,3.25,3.25,3.25,"Solar",2014,"2014-06-23","2014-06-23",1,"2014-07-03",9,0,"2014-07-07","2014-07-21",0,null,null,null,null,null,null,null,null,null,null,"2014-08-26","2014-07-21",21,null,null,null,0,"n/a",null,null,"2014-10-24","2014-11-04",8,0,"2014-08-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-07-15"]
["Alan R Ballou","Vivint Solar Developer, LLC","SIMP",null,"Carla","Completed",null,"6F600-2014","2372871","R1","R","54752481077","375331008","894063152","152032006","3","King Philip Ave",null,null,"South Deerfield","MA","01373","WMECO",{"$f":"LEFT(Y3184,3)","v":"18G"},"18G3"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-01",6.9359999999999999,6.9359999999999999,8.67,"Class 1 (Solar / Wind)",null,7.65,7.65,7.65,"Solar",2014,"2014-08-01","2014-08-04",2,"2014-09-19",36,1,"2014-09-19","2014-09-19",1,null,null,null,null,null,null,null,null,null,null,"2014-10-08","2014-09-19",36,null,"2014-11-05",null,0,"n/a",null,null,"2014-11-04","2014-11-24",15,6,"2014-09-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-09-19"]
["George Mount","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2014-10-20","6F622-2014","2382289","R1","R","54941402042","102641003","866399932","145252003","31","Lee Rd",null,null,"South Deerfield","MA","01373","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"2014-08-12",null,6.9359999999999999,8.67,"Class 1 (Solar / Wind)",null,7.65,7.65,7.65,"Solar",2014,"2014-08-12","2014-08-13",2,"2014-09-26",34,0,"2014-09-29","2014-10-15",0,null,null,null,null,null,null,null,null,null,null,"2015-01-16","2014-10-15",47,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2014-10-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled","2014-10-15"]
["Julia Freedgood",null,"SIMP",null,"Erik","Completed",null,"6F657-2014","2401857","R1","R","54445481070","544431001","893565572","024032005","26","South St",null,null,"Chesterfield","MA","01012","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-22",4,4,5,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2014,"2014-09-22","2014-09-22",1,"2014-10-10",15,0,"2014-10-14","2014-10-31",0,null,null,null,null,null,null,null,null,null,null,"2015-02-12","2014-10-31",30,null,null,null,0,"n/a",null,null,"2014-12-11","2014-12-31",15,6,"2014-11-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-30"]
["Sally Wright",null,"SIMP",null,"Erik","Completed",null,"6F663-2014","2406079","R1","R","54013171012","256821003","894063642","911912002","254","High St",null,null,"Greenfield","MA","01301","WMECO","21C","21C4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-30",6.6239999999999997,6.6239999999999997,8.2799999999999994,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2014,"2014-09-30","2014-09-30",1,"2014-10-17",14,0,"2014-10-20","2014-11-05",0,null,null,null,null,null,null,null,null,null,null,"2015-02-12","2014-11-05",27,null,null,null,0,"n/a",null,null,"2014-11-07","2014-11-18",8,2,"October 2014",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-05"]
["George Mount",null,"SIMP",null,"Erik","Completed",null,"6F692-2014","2423580","R1","R","54941402042","102641003","894199492","145252003","31","Lee Rd",null,null,"South Deerfield","MA","01373","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-30",7.0400000000000009,7.0400000000000009,8.8000000000000007,"Class 1 (Solar / Wind)",null,8,8,8,"Solar",2014,"2014-10-30","2014-10-30",1,"2014-11-21",17,0,"2014-11-21","2014-12-03",0,null,null,null,null,null,null,null,null,null,null,"2015-02-18","2014-12-03",25,null,null,null,0,"n/a",null,null,"2015-04-16","2015-04-28",9,0,"Q1 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-03"]
["Shannon Ketch",null,"SIMP",null,"Erik","Completed",null,"6F714-2014","2444516","R1","R","54205275035","656031006","885729142","961322005","39","K St",null,null,"Turners Falls","MA","01376","WMECO","21C","21C5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-01",5.1760000000000002,5.1760000000000002,6.47,"Class 1 (Solar / Wind)",null,5.85,5.85,5.85,"Solar",2014,"2014-12-01","2014-12-01",1,"2014-12-12",10,0,"2014-12-15","2014-12-16",0,null,null,null,null,null,null,null,null,null,null,"2015-02-18","2014-12-16",12,null,null,null,0,"n/a",null,null,"2015-10-16","2015-10-29",10,7,"2015-01-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-12-16"]
["Patty McConnell",null,"SIMP",null,"Erik","Completed",null,"6F745-2015","2466000","R1","R","54179681093","827443000","988026242","997822000","21","Bald Mountain Rd",null,null,"Bernardston ","MA","01337","WMECO","21B","21B8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-05",5.7960000000000003,5.7960000000000003,7.2450000000000001,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-01-05","2015-01-05",1,"2015-01-12",6,0,"2015-01-13","2015-02-04",0,null,null,null,null,null,null,null,null,null,null,"2015-07-28","2015-02-04",23,null,null,null,0,"n/a",null,null,"2015-02-05","2015-02-20",12,0,"2015-01-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-02-04"]
["Wendy Swan","SolarCity Corp","SIMP",null,"Erik","In Process",null,"6F771-2015","2476430","R1","R","54027391077","302931008","881754502","082042006","57","Baptist Corner Rd",null,null,"Ashfield","MA","01330","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-21",null,1.6320000000000001,2.04,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-01-21","2015-01-21",1,"2015-03-23",44,36,"2015-03-24","2015-03-26",0,null,null,null,null,null,null,null,null,null,null,"2015-06-09","2015-03-26",47,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-03-26"]
["Nancy Finn",null,"SIMP",null,"Erik","Completed",null,"6F787-2015","2483206","R2","R","54365481001","804331002","888190282","648922008","609","Mohawk Trl",null,null,"Shelburne Falls","MA","01370","WMECO","22B","22B5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-02-09",8.16,8.16,10.199999999999999,"Class 1 (Solar / Wind)",null,9,9,9,"Solar",2015,"2015-02-09","2015-02-09",1,"2015-03-11",{"$f":"IF(AU3369=0,NETWORKDAYS(AR3369,$A$4),NETWORKDAYS(AR3369,AU3369))","v":23},13,"2015-03-12","2015-03-16",0,null,null,null,null,null,null,null,null,null,null,"2015-09-16","2015-03-16",26,null,null,null,0,"n/a",null,null,"2015-11-25","2015-12-09",11,5,"2015-03-13",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-03-16"]
["Mary Praus",null,"SIMP",null,"Erik","Completed",null,"6F806-2015","2489851","R1","R","54627945074","687531007","894192832","994432007","254","Davis St",null,null,"Greenfield","MA","01301","WMECO","22B","22B2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-02-27",2.0960000000000001,2.0960000000000001,2.62,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-02-27","2015-02-27",1,"2015-03-30",22,9,"2015-03-31","2015-05-06",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-06",49,null,null,null,0,"n/a",null,null,"2015-05-20","2015-06-12",18,4,"April 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-06"]
["Andrew Rothschild",null,"SIMP",null,"Erik","Completed",null,"6F828-2015","2498938","R1","R","54690471016","582821007","894165932","285912000","32","Lillian St",null,null,"Greenfield","MA","01301","WMECO","21C","21C1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-19",5.04,5.04,6.3,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-03-19","2015-03-19",1,"2015-03-24",4,0,"2015-03-25","2015-04-17",0,null,null,null,null,null,null,null,null,null,null,null,"2015-04-17",22,null,null,null,0,"n/a",null,null,"2015-05-01","2015-05-15",11,1,"2015-04-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-04-17"]
["Wynne Busby",null,"SIMP",null,"Erik","Completed",null,"6F852-2015","2510335","R1","R","54000602045","349741006","894199702","529452003","26","Potash Hill Rd",null,null,"Cummington","MA","01026","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-08",3.1392000000000002,3.1392000000000002,3.9239999999999999,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-04-08","2015-04-08",1,"2015-05-12",25,0,"2015-05-13","2015-05-13",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-13",26,null,null,null,0,"n/a",null,null,"2015-06-12","2015-07-02",15,3,"May 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-13"]
["Joseph Charron III","NRG","SIMP",null,"Erik","Cancelled","2016-01-15","6F885-2015","2520415","R1","R","54094366077","935321001","867711732","823212003","186","Plain Rd",null,null,"Greenfield","MA","01301","WMECO","22B","22B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-29",null,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2015,"2015-04-29","2015-04-29",1,"2015-05-27",21,0,"2015-05-28","2015-06-03",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-03",26,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-06-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-03"]
["Anne Schuyler","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6F909-2015","2530185","R1","R","54985066000","669341006","894706832","286642003","95","Amherst Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-05-18",8.1120000000000001,8.1120000000000001,10.14,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-05-18","2015-05-19",2,"2015-06-04",14,0,"2015-06-05","2015-07-06",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-06",36,null,"2015-08-27",null,0,"n/a",null,null,"2015-08-21","2015-10-01",30,4,"2015-07-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-06"]
["Andrea Beaudoin",null,"SIMP",null,"Erik","In Process",null,"6F942-2015","2544033","R1","R","54394855068","446031003","884503312","790322009","3014","Shelburne Falls Rd",null,null,"Conway","MA","01341","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-08",null,4,5,"Class 1 (Solar / Wind)",null,5,5,5,"Solar",2015,"2015-06-08","2015-06-09",2,"2015-07-23",34,2,"2015-07-24","2015-07-30",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-30",39,null,null,null,0,"n/a",null,null,null,null,30288,null,"2015-06-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-30"]
["Raymond Stonntag","NRG Home Solar","SIMP",null,"Erik","Cancelled","2016-01-15","6F964-2015","2551790","R3","R","54961391018","926931009","883921012","333932009","139","Main St",null,null,"Shelburne Falls","MA","01370","WMECO","29R","29R1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-16",null,6.944,8.68,"Class 1 (Solar / Wind)",null,7.75,7.75,7.75,"Solar",2015,"2015-06-16","2015-06-18",3,"2015-07-13",20,0,"2015-07-14","2015-08-03",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04",36,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04"]
["Patricia Zywna","NRG Home Solar","SIMP",null,"Erik","Completed",null,"6F974-2015","2552777","R1","R","54444771026","212031007","868204192","717222000","74","Mountain Rd",null,null,"Gill","MA","01354","WMECO","21C","21C5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-16",6.12,6.120000000000001,7.65,"Class 1 (Solar / Wind)",null,7.5,7.5,7.5,"Solar",2015,"2015-06-18","2015-06-23",{"$f":"IF(AS3556=0,NETWORKDAYS(AR3556,$A$4),NETWORKDAYS(AR3556,AS3556))","v":4},"2015-07-14",19,0,"2015-07-15","2015-08-03",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04",34,null,"2015-12-08",null,0,"n/a",null,null,"2015-12-07","2015-12-18",10,7,"2015-07-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04"]
["Joseph Shutta","Vivint Solar Developer, LLC","SIMP",null,"Erik","In Process",null,"6F998-2015","2556363","R1","R","54976781070","614031005","890467261","008322008","117","Hillcrest Dr",null,null,"Bernardston ","MA","01337","WMECO","21C","21C1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-07",null,3.9520000000000004,4.9400000000000004,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-07-07","2015-07-07",1,"2015-08-05",22,2,"2015-08-06","2015-08-21",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-24",35,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-09-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-25"]
["Margaret Allard",null,"SIMP",null,"Erik","Completed",null,"6F1031-2015","2573614","R1","R","54043781095","537631006","884371912","570532007","11","Damon Pond Rd",null,null,"Chesterfield","MA","01012","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-29",6.28,6.28,7.85,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-07-29","2015-07-29",1,"2015-08-28",23,0,"2015-08-31","2015-09-29",0,null,null,null,null,null,null,null,null,null,null,null,"2015-09-30",46,null,null,null,0,"n/a",null,null,"2015-12-03","2015-12-09",5,0,"Dec 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-09-30"]
["David Kulp",null,"SIMP",null,"Carla","In Process",null,"6F1055-2015","2585094","R3","R","54588791012","496241003","882261732","025442009","183","Phillips Rd",null,null,"Ashfield","MA","01330","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-18",null,5.28,6.6,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-08-18","2015-08-19",2,"2015-10-15",43,2,"2015-10-15","2015-10-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15",43,null,null,null,0,"n/a",null,null,null,null,30288,null,"2015-08-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-17"]
["Christine Hoffman","NRG Home Solar","SIMP",null,"Carla","Cancelled","2015-11-17","6F1077-2015","2588628","R1","R","54231602053","071741004","868725242","799352004","602","Federal St",null,null,"Montague","MA","01351","WMECO","21C","21C7","PTF"," ","Photovoltaic","Inverter",null,null,null,"2015-08-26",null,8.0640000000000001,10.08,"Class 1 (Solar / Wind)",null,9,9,9,"Solar",2015,"2015-08-26","2015-08-27",2,null,116,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,116,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-10-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Steven Morgan",null,"SIMP",null,"Carla","In Process",null,"6F1096-2015","2595143","R1","R","54364002006","364341007","885716932","803642009","16","Lawton Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-08",null,6.3520000000000003,7.94,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-09-08","2015-09-08",1,"2015-10-15",28,0,"2015-10-15","2015-10-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15",28,null,null,null,0,"n/a",null,null,null,null,30288,null,"Dec 2015",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-17"]
["John Riggan",null,"SIMP",null,"Carla","In Process",null,"6F1111-2015","2599913","R1","R","54208471078","705821009","884503522","854022005","19","South St",null,null,"Buckland","MA","01338","WMECO","22B","22B5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-14",null,5.3000000000000007,6.625,"Class 1 (Solar / Wind)",null,5.625,5.625,5.625,"Solar",2015,"2015-09-14","2015-09-15",2,"2015-10-19",26,23,"2015-10-19","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",26,null,null,null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-20"]
["Evan Johnson / Kathryn Ewald",null,"SIMP",null,"Carla","Completed",null,"6F1153-2015","2610473","R1","R","54037591062","752141003","866521772","760042004","88","Harvey Rd",null,null,"Worthington","MA","01098","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-05",2.448,2.4480000000000004,3.06,"Class 1 (Solar / Wind)",null,3.016,3.016,3.016,"Solar",2015,"2015-10-05","2015-10-05",1,"2015-10-19",11,0,"2015-10-19","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",11,null,null,null,0,"n/a",null,null,"2015-11-13","2015-12-03",15,8,"2015-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-22"]
["Stephen Schulze",null,"SIMP",null,"Carla","Completed",null,"6F1156-2015","2610513","R1","R","54458171022","662721003","866311792","434812001","401","Huntington Rd",null,null,"Worthington","MA","01098","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-09",4.2839999999999998,4.2840000000000007,5.3550000000000004,"Class 1 (Solar / Wind)",null,5.25,5.25,5.25,"Solar",2015,"2015-10-06","2015-10-06",1,"2015-10-19",10,0,"2015-10-19","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",10,null,null,null,0,"n/a",null,null,"2015-11-17","2015-12-11",19,15,"2015-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-22"]
["Ronald Croteau","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6F1186-2015","2614458","R1","R","54075702035","019841006","887495572","068652001","62","Fargo St",null,null,"Greenfield","MA","01301","WMECO","21C","21C1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-23",null,3.476,4.3449999999999998,"Class 1 (Solar / Wind)",null,4.25,4.25,{"$f":"17*0.25","v":4.25},"Solar",2015,"2015-10-23","2015-10-23",1,"2015-11-25",24,0,"2015-11-25","2015-11-25",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-25",24,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-11-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Manfred Gabriel",null,"SIMP",null,"Carla","Completed",null,"6F1213-2015","2629453","R1","R","54288591043","847041004","868716672","620242003","62","Briar Hill Rd",null,null,"Ashfield","MA","01330","WMECO","38A","38A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-04",5.04,5.04,6.3,"Class 1 (Solar / Wind)",null,5.25,5.25,5.25,"Solar",2015,"2015-11-04","2015-11-04",1,"2015-12-02",21,0,"2015-12-02","2015-12-11",2,null,null,null,null,null,null,null,null,null,null,null,"2015-12-14",29,null,null,null,0,"n/a",null,null,"2016-01-25","2016-01-28",4,1,"2016-01-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering"]
["Sarah Z Westbrook","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6F1247-2015","2640566","R1","R","54408434033","986241004","885625562","486642006","38","Captain Lathrop Dr",null,null,"South Deerfield","MA","01373","WMECO","22B","22B1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-11-20",null,9.1519999999999992,11.44,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-11-20","2015-11-20",1,"2015-12-10",15,0,"2015-12-10","2015-12-10",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-14",17,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Francis Murphy","Oneroof Energy","SIMP",null,"Carla","In Process",null,"6F1251-2015","2641206","R1","R","54449081041","755131002","887926992","205622006","145","Upper Rd",null,null,"Deerfield","MA","01342","WMECO","22B","22B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-25",null,4.3164000000000007,5.3955000000000002,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-11-25","2015-11-30",4,"2015-12-15",15,0,"2015-12-15","2015-12-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-17",17,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Carl W Kingsley III",null,"SIMP",null,"Carla","In Process",null,"6F1292-2015","2661909","R1","R","54882781065","305141008","867058442","816442007","707","Country Club Rd",null,null,"Greenfield","MA","01301","WMECO","22B","22B7","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-23",null,4,5,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-12-23","2015-12-24",2,"2016-01-08",13,0,"2016-01-08","2016-01-08",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-08",13,null,null,null,0,"n/a",null,null,null,null,30288,null,"2016-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Joseph R Charron III","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6F1309-2016","2667747","R1","R","54094366077","935321001","867711732","823212003","186","Plain Rd",null,null,"Greenfield","MA","01301","WMECO","22B","22B7","PTF"," ","Photovoltaic","Inverter",null,null,null,"2016-01-05",null,6.24,7.8,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2016,"2016-01-05","2016-01-05",1,"2016-01-15",9,1,"2016-01-15","2016-01-15",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-15",9,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-03-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Kevin W Gamache","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6F1327-2016","2674189","R1","R","54248502023","219641004","865612192","543552001","23","Riverview Dr",null,null,"Northfield","MA","01360","WMECO","21B","21B8"," ","non-PTF","Photovoltaic","Inverter",null,null,null,"2016-01-22",null,14.144,17.68,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2016,"2016-01-22","2016-01-22",1,null,9,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,9,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-03-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Matthew G Slowinski",null,"SIMP",null,"Carla","In Process",null,"6F1349-2016","2682232","RGO","R","54777865007","586441002","893726912","154152001","13","Bennett Dr",null,null,"Colrain","MA","01340","WMECO","29R","29R2","PTF"," ","Photovoltaic","Inverter",null,null,null,"2016-02-08",null,2,2.5,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2016,"2016-02-08","2016-02-08",1,null,-4,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,-4,null,null,null,0,"n/a",null,null,null,null,30288,null,"2016-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["MMWECO Stony Brook Energy",null,"SIMP",null,null,"Completed",null,"6S20-2009",null,"G2","C","54287591093","909041004","891725392","130342007",null,"Westover Ind Air Park",null,null,"Ludlow","MA","01056","WMECO","27A","27A5","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"no export",0,null,9.6,"No Export",null,9.6,9.6,9.6,"Solar",2009,"2009-02-25",null,null,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2009-02-27",null,"n/a",null,null,0,"n/a",null,null,null,"2009-06-09",null,null,"2009-05-04","no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2009,null,null,null,null,null,"n/a - not expected to export",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y","N",null,"2009-02-27"]
["Gandara Mental Health Center","Here Comes The Sun, LLC","EXP",null,"Erik","Completed",null,"6S52-2010",null,"G0","C","54875591059","490141000","891970242","643042004","147","Norman St",null,null,"West Springfield","MA","01089","WMECO","16C","16C14","PTF"," ","Photovoltaic","Inverter","Private",null,null,"2010-12-17",35.880000000000003,35.880000000000003,44.85,"Class 1 (Solar / Wind)",null,50,50,50,"Solar",2010,"2010-12-07",null,null,"2011-01-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2011-03-02",null,"2011-03-11","2011-03-21",null,0,"n/a","No",null,null,"2011-03-29",null,null,"2011-02-01",null,"WDGSL021",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"On line. Third party owned.",2011,"??","??",null,null,null,"net metering",null,null,null,null,null,null,"Here Comes The Sun LLC       Attn:  Jerry Belair","1 Bridge Street","Newton","MA","02458","617-965-2200  ext 178   cell = 401-450-1263",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2011-03-11"]
["Paige Scyocurka","Green Earth Energy Corp","SIMP",null,null,"Cancelled",null,"6S77-2011",null,"R1",null,"54674102090","957441001","890376302","703052008","208","Shaker Rd",null,null,"Longmeadow","MA","01106","WMECO","22H","22H11","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,19.600000000000001,24.5,"N/A",null,null,null,22.8,"Solar",2011,"2011-12-01","2011-12-01",1,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,0,"n/a",null,null,null,null,null,null,"2012-01-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Cancelled per cust request.  New app to be submitted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"Cancelled","2011-12-21"]
["Mary Collins (was Brian Kivel)","Brian Kivel - Landlord","SIMP",null,null,"Completed",null,"6S86-2011",null,"R1","R","54961717048","406621006","892922392","800712008","6","South Park Pl","Floor",1,"Longmeadow","MA","01106","WMECO","22H","22H17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-17",4.032,4.032,5.04,"Class 1 (Solar / Wind)",null,4.5149999999999997,4.5149999999999997,4.5149999999999997,"Solar",2011,"2011-12-30","2012-01-03",3,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-01-24",18,null,null,null,0,"n/a",null,null,null,"2012-02-09",null,null,"2011-12-30","2015-02-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering","Fed from xfr 86/5 which is mislabeled 58/6 on mapping as of 1/23/2012.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Y",null,null,"2012-01-24"]
["Andrew Bristol (replaced WMECO Pilot3)",null,"SIMP",null,null,"Completed",null,"6S107-2012",null,"R1","R","54138971023","541131004","888508012","368522001","80","Margaret Ln",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-04-03",8,8,10,"Class 1 (Solar / Wind)",null,10,10,10,"Solar",2012,"2012-04-03","2012-04-03",1,"n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2012-06-26",61,null,null,null,0,"n/a",null,null,null,"2012-10-10",null,null,"2012-05-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2800,2535.73,264.27,2637.32,null,null,null,null,null,null,null,null,null,2012,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"WO 6S221614",1945720,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Kathy Kelly",null,"SIMP",null,null,"Cancelled",null,"6S141-2012",null,"R1","R","54956761076","111421007","984094942","363412006","25","Kipling St",null,null,"Springfield","MA","01118","WMECO","20A","20A32","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,6.1560000000000006,7.6950000000000003,"N/A",null,null,null,null,"Solar",2012,"2012-09-10","2012-09-11",2,"n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,null,null,0,"n/a",null,null,null,null,null,null,"2012-12-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled"]
["June Robbins","Sun Run, Inc.","SIMP",null,null,"Completed",null,"6S164-2013",null,"R1","R","54477661078","347321009","893071292","206312003","233","Island Pond Rd",null,null,"Springfield","MA","01118","WMECO","20A","20A22","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-03-15",3.4,3.4000000000000004,4.25,"Class 1 (Solar / Wind)",null,4,4,4,"Solar",2013,"2013-03-15","2013-03-15",1,"2013-04-26",{"$f":"IF(AU4100=0,NETWORKDAYS(AR4100,$A$4),NETWORKDAYS(AR4100,AU4100))","v":31},null,null,null,null,null,null,null,null,"n.r.","n.r.",null,null,null,null,null,"2013-04-26",31,null,"2013-06-03",null,0,"n/a",null,null,null,"2013-06-11",null,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,null,null,null,"2013-04-26"]
["Joanna Harlow","Sun Run","SIMP",null,null,"Completed",null,"6S198-2013",null,"R1","R","54623981032","903731003","893241062","871432002","256","Norman St",null,null,"West Springfield","MA","01089","WMECO","16C","16C14","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-07-15",5.2,5.2,6.5,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2013,"2013-07-15","2013-07-16",2,"2013-07-29",11,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-07-29",11,null,"2013-09-17",null,0,"n/a",null,null,"2013-09-17","2013-09-20",4,null,"2013-08-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2013,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-07-29"]
["Peter Briancesco",null,"SIMP",null,"Erik","Completed",null,"6S221-2013",null,"R3","R","54513991042","892341003","881487852","181642003","35","High Meadow Rd",null,null,"Feeding Hills","MA","01030","WMECO","16C","16C17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2013-11-13",6.4,6.4,8,"Class 1 (Solar / Wind)",null,8,8,8,"Solar",2013,"2013-11-13","2013-11-13",1,"2014-01-03",38,12,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-01-06",39,null,null,null,0,null,null,null,"2014-01-08","2014-01-17",8,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-01-06"]
["Beth Ann Sarnelli","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S243-2014","2283439","R1","R","54226491066","562041007","893566422","607042005","77","Newton Rd",null,null,"Springfield","MA","01118","WMECO","20A","20A32","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-02-04",3.7240000000000002,3.7240000000000002,4.6550000000000002,"Class 1 (Solar / Wind)",null,3.8,3.8,3.8,"Solar",2014,"2014-02-04","2014-02-05",2,"2014-02-11",6,0,"2014-02-26","2014-02-26",0,null,null,null,null,null,null,null,null,null,null,"2014-05-23","2014-02-26",17,null,"2014-03-03",null,0,"n/a",null,null,"2014-03-10","2014-03-18",{"$f":"IF(BV4179=0,NETWORKDAYS(BU4179,$A$4),NETWORKDAYS(BU4179,BV4179))","v":7},0,"2014-03-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-02-26"]
["Gloria Caballer-Arce","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S263-2014","2307651","R1","R","54529181083","436231005","894055902","749722007","23","Brandon Ave",null,null,"Springfield","MA","01119","WMECO","20A","20A33","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-04-02",3.4000000000000004,3.4000000000000004,4.25,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2014,"2014-04-02","2014-04-02",1,"2014-04-17",12,9,"2014-04-17","2014-04-17",0,null,null,null,null,null,null,null,null,null,null,"2014-06-04","2014-04-17",12,null,"2014-11-07",null,0,"n/a",null,null,"2014-11-25","2014-12-03",7,135,"2014-05-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-04-17"]
["David Groncki",null,"SIMP",null,"Erik","Completed",null,"6S277-2014","2318869","R1","R","54346125081","274721004","881746262","239712004","37","Dale St",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-04-25",4.968,4.968,6.21,"Class 1 (Solar / Wind)",null,5.1749999999999998,5.1749999999999998,5.1749999999999998,"Solar",2014,"2014-04-25","2014-04-25",1,"2014-05-06",8,0,"2014-05-07","2014-07-15",31,null,null,null,null,null,null,null,null,null,null,"2014-08-26","2014-07-15",58,null,null,null,0,"n/a",null,null,"2014-07-23","2014-08-01",8,0,"2014-05-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-07-08"]
["Daniel Paquette","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S304-2014","2340384","R1","R","54050935097","329703004","894055442 ","512185004","46","Burlington Dr",null,null,"Agawam","MA","01001","WMECO","30A","30A6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-06-09",6.5279999999999996,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,7.2,7.2,7.2,"Solar",2014,"2014-06-09","2014-06-09",1,"2014-06-25",13,11,"2014-06-26","2014-08-21",35,null,null,null,null,null,null,null,null,null,null,"2014-09-24","2014-08-21",54,null,"2014-08-28",null,0,"n/a",null,null,"2014-09-25","2014-11-04",29,20,"2014-08-06",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-08-18"]
["Macy's Corporate Services Inc","SunConnect MA3, LLC","EXP",null,"Carla","Cancelled","2014-06-30","6S334-2014","2347757","T2",null,"54814995007","355531005","891763812","738232005","1685","Boston Rd",null,null,"Springfield","MA","01129","WMECO",{"$f":"LEFT(Y4270,3)","v":"20A"},"20A35","PTF"," ","Photovoltaic","Inverter","n/a","n/a",null,"n/a",null,292.072,365.09,"n/a",null,278.39999999999998,278.39999999999998,278.39999999999998,"Solar",2014,"2014-06-23","2014-06-23",1,null,"canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"canc",null,"needed",null,"cancld","cancld",null,null,null,null,"canc",null,"2014-10-31",null,"6S421353",0,56.91,{"$f":"CC4270-CB4270","v":56.91},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Project cancelled by customer.","Cancelled",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled"]
["Jamilette Reyes","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2016-01-08","6S356-2014","2361041","R2","R","54180825051","273841001","887987652","118552000","265","Gresham St",null,null,"Springfield","MA","01119","WMECO","20A","20A33","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-07-15",null,3.88,4.8499999999999996,"Class 1 (Solar / Wind)",null,4.2750000000000004,4.2750000000000004,4.2750000000000004,"Solar",2014,"2014-07-15","2014-07-15",1,"2014-07-25",9,0,"2014-07-28","2014-08-19",0,null,null,null,null,null,null,null,null,null,null,"2014-09-22","2014-08-19",26,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2014-09-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-08-19"]
["Michelle L Longey","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S385-2014","2373258","R1","R","54725761027","019321008","894063852","151312000","66","Squassick Rd",null,null,"West Springfield","MA","01089","WMECO","21N","21N4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-01",5.9200000000000008,5.9200000000000008,7.4,"Class 1 (Solar / Wind)",null,6.5250000000000004,6.5250000000000004,6.5250000000000004,"Solar",2014,"2014-08-01","2014-08-05",3,"2014-08-05",3,0,"2014-08-06","2014-09-12",0,null,null,null,null,null,null,null,null,null,null,"2014-10-08","2014-09-12",31,null,"2015-03-27",null,0,"n/a",null,null,"2015-03-27","2015-04-08",9,0,"2014-09-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-09-12"]
["Joseph Kozaczka","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S390-2014","2374112","R1","R","54732591094","031141005","894155932","339142008","492","Miller St",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","Private","yes",null,"2014-08-04",9.1840000000000011,9.1840000000000011,11.48,"Class 1 (Solar / Wind)",null,10.125,10.125,10.125,"Solar",2014,"2014-08-04","2014-08-05",2,"2014-09-16",32,0,null,null,null,"SIMP5","2014-09-17","2014-09-19",2,null,null,null,null,null,null,"2014-10-08","2014-09-19",35,null,"2014-12-16",null,0,"n/a",null,null,"2014-12-16","2015-01-09",19,14,"2014-10-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-09-18"]
["Lori Pajer","Vivint Solar Developer, LLC","SIMP",null,"Carla","Completed",null,"6S426-2014","2379883","R1","R","54139781041","286531002","868408052","684432003","11","Gargon Ter",null,null,"Southwick","MA","01077","WMECO","29A","29A1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-12",3.2639999999999998,3.2640000000000002,4.08,"Class 1 (Solar / Wind)",null,3.6,3.6,3.6,"Solar",2014,"2014-08-12","2014-08-13",2,"2014-09-19",29,0,"2014-09-20","2014-10-10",0,null,null,null,null,null,null,null,null,null,null,"2015-01-16","2014-10-10",44,null,"2015-09-15",null,0,"n/a",null,null,"2015-04-28","2015-10-19",125,96,"2014-10-11",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-10"]
["Nancy Tyburski","SolarCity Corp","SIMP",null,"Erik","Cancelled","2015-12-31","6S447-2014","2383360","R1","R","54324291087","381831008","892185752","969832007","1488","Parker St",null,null,"Springfield","MA","01129","WMECO","20A","20A34","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-18",null,6.5280000000000005,8.16,"Class 1 (Solar / Wind)",null,8.3000000000000007,8.3000000000000007,8.3000000000000007,"Solar",2014,"2014-08-18","2014-08-19",2,"2014-09-26",{"$f":"IF(AU4383=0,NETWORKDAYS(AR4383,$A$4),NETWORKDAYS(AR4383,AU4383))","v":30},2,"2014-09-29","2014-10-16",0,null,null,null,null,null,null,null,null,null,null,"2015-01-16","2014-10-16",{"$f":"IF(BL4383=0,NETWORKDAYS(AR4383,$A$4),NETWORKDAYS(AR4383,BL4383))","v":44},null,"needed",null,0,"n/a",null,null,null,null,{"$f":"IF(BV4383=0,NETWORKDAYS(BU4383,$A$4),NETWORKDAYS(BU4383,BV4383))","v":30288},null,"2014-09-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-16"]
["Arthur Pelkey","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S469-2014","2386838","R1","R","54138761069","622421000","894063542","738312005","57","Squassick Rd",null,null,"West Springfield","MA","01089","WMECO","21N","21N4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-08-28",5.3040000000000003,5.3040000000000003,6.63,"Class 1 (Solar / Wind)",null,5.85,5.85,5.85,"Solar",2014,"2014-08-28","2014-08-28",1,"2014-09-26",22,0,"2014-09-29","2014-10-22",0,null,null,null,null,null,null,null,null,null,null,"2015-01-16","2014-10-22",40,null,"2014-11-24",null,0,"n/a",null,null,"2015-04-21","2015-06-12",39,0,"2014-10-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-22"]
["Richard Giordano, Sr","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S491-2014","2391327","R3","R","54142691062","585141003","894160033","752242005","84","Cambridge St",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-05",2.4480000000000004,2.4480000000000004,3.06,"Class 1 (Solar / Wind)",null,2.7,2.7,2.7,"Solar",2014,"2014-09-05","2014-09-05",1,"2014-10-10",26,0,"2014-10-14","2014-10-24",0,null,null,null,null,null,null,null,null,null,null,"2015-01-16","2014-10-24",36,null,"2015-03-19",null,0,"n/a",null,null,"2015-03-27","2015-04-08",9,0,"2014-11-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-23"]
["Matthew Preston","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2016-01-07","6S526-2014","2402719","R1","R","54505291021","339431000","988194532","615032002","3","Ogden St",null,null,"Indian Orchard","MA","01151","WMECO",{"$f":"LEFT(Y4462,3)","v":"05J"},"05J17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-09-23",null,2.04,2.5499999999999998,"Class 1 (Solar / Wind)",null,2.25,2.25,2.25,"Solar",2014,"2014-09-23","2014-09-23",1,"2014-10-17",19,0,"2014-10-20","2014-10-31",0,null,null,null,null,null,null,null,null,null,null,"2015-01-20","2014-10-31",29,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2014-11-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-10-31"]
["David Myers","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S548-2014","2409134","R1","R","54293691044","866141005","894532512","475242003","96","Americo St",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-03",4.28,4.28,5.35,"Class 1 (Solar / Wind)",null,4.7249999999999996,4.7249999999999996,4.7249999999999996,"Solar",2014,"2014-10-03","2014-10-03",1,"2014-10-17",11,0,"2014-10-20","2014-11-13",0,null,null,null,null,null,null,null,null,null,null,"2015-01-20","2014-11-13",30,null,"needed",null,0,"n/a",null,null,"2015-07-07","2015-09-14",50,10,"2014-11-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-13"]
["Maria Doughty","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S560-2014","2411086","R1","R","54557371069","096721000","894161912","829712004","7","Karen Dr",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-06",5.1040000000000001,5.1040000000000001,6.38,"Class 1 (Solar / Wind)",null,5.625,5.625,5.625,"Solar",2014,"2014-10-06","2014-10-06",1,"2014-10-24",15,0,"2014-10-27","2014-11-17",0,null,null,null,null,null,null,null,null,null,null,"2015-01-20","2014-11-17",31,null,"2014-12-17",null,0,"n/a",null,null,"2015-04-15","2015-04-28",10,0,"2014-11-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-17"]
["Andrey Antropov",null,"SIMP",null,"Erik","Completed",null,"6S583-2014","2414695","R1","R","54729876003","384541000","894160412","029152001","4","Nicholson Hill Rd",null,null,"Southwick","MA","01077","WMECO","29A","29A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-10",4.056,4.056,5.07,"Class 1 (Solar / Wind)",null,4.9400000000000004,4.9400000000000004,4.9400000000000004,"Solar",2014,"2014-10-10","2014-10-14",3,"2014-10-24",11,0,"2014-10-27","2014-11-19",0,null,null,null,null,null,null,null,null,null,null,"2015-02-13","2014-11-19",29,null,null,null,0,"n/a",null,null,"2014-12-11","2014-12-18",6,4,"2014-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2014,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-11-19"]
["Jerry Sibilia Jr","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S614-2014","2418463","R1","R","54775502008","165641009","868695402","211352009","64","Zachary Ln","Lot",11,"Agawam","MA","01001","WMECO","30A","30A2"," ","non-PTF","Photovoltaic","Inverter","Private","yes",null,"2014-10-22",11.423999999999999,11.423999999999999,14.28,"Class 1 (Solar / Wind)",null,12,12,12,"Solar",2014,"2014-10-22","2014-10-22",1,"2014-11-26",26,5,"2014-11-28","2014-12-30",20,null,null,null,null,null,null,null,null,null,null,"2015-02-10","2014-12-30",50,null,"2015-10-07",null,0,"n/a",null,null,"2015-06-05","2015-10-19",97,85,"2014-12-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-31"]
["Steve Plummer","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S640-2014","2423576","R1","R","54689691061","692141002","894159992","350342005","50","Fordham Ave",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-10-29",4.08,4.08,5.0999999999999996,"Class 1 (Solar / Wind)",null,4.5,4.5,4.5,"Solar",2014,"2014-10-29","2014-10-29",1,"2014-11-21",18,0,"2014-11-24","2014-12-03",0,null,null,null,null,null,null,null,null,null,null,"2015-02-13","2014-12-03",26,null,"2015-03-19",null,0,"n/a",null,null,"2015-04-01","2015-04-10",8,0,"2015-01-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-03"]
["Domenic Battista","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S647-2014","2427293","R1","R","54142502004","805641005","868589222","315252009","118","Galaska Dr",null,null,"West Springfield","MA","01089","WMECO","21N","21N9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-11-03",8.16,8.16,10.199999999999999,"Class 1 (Solar / Wind)",null,9.3000000000000007,9.3000000000000007,9.3000000000000007,"Solar",2014,"2014-11-03","2014-11-04",2,"2014-11-24",16,0,"2014-11-25","2014-12-04",0,null,null,null,null,null,null,null,null,null,null,"2015-02-13","2014-12-04",24,null,"needed",null,0,"n/a",null,null,"2015-01-21","2015-02-27",28,10,"2015-01-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"*****","2014-12-04"]
["Kearsarge Energy LLC",null,"EXP",null,"Carla","Cancelled","2014-11-26","6S674-2014","2435599",null,null,null,null,null,null,"85","Tilley St",null,null,"Ludlow","MA","01056","WMECO","",null,{"$error":"#N/A"},{"$error":"#N/A"},"Photovoltaic","Inverter","n/a","n/a",null,"2014-11-14",null,518.5,648.125,"Class 2",null,null,499,499,"Solar",2014,"2014-11-14","2014-11-14",1,null,319,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,319,null,null,null,"cancld","cancld",null,null,null,null,null,null,"Summer 2015",null,"6S422283",2245.5,83.01,{"$f":"CC4609-CB4609","v":-2162.4899999999998},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","Interconnecting Customer Cancelled 11/26/14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled"]
["Scott Curry","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-12-30","6S696-2014","2445863","R1","R","54333371094","830821005","987905602","938912008","32","Miller St",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-04",null,4.4880000000000004,5.61,"Class 1 (Solar / Wind)",null,4.95,4.95,4.95,"Solar",2014,"2014-12-04","2014-12-04",1,"2014-12-12",7,0,"2014-12-15","2014-12-17",0,null,null,null,null,null,null,null,null,null,null,"2015-02-13","2014-12-17",10,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-01-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2014-12-17"]
["Joseph Parisi","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S736-2014","2457125","R3","R","54399661016","629321007","894532802","176212000","103","Chesterfield Ave",null,null,"Springfield","MA","01118","WMECO","20A","20A32","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-22",5.5120000000000005,5.5120000000000005,6.89,"Class 1 (Solar / Wind)",null,6.0750000000000002,6.0750000000000002,6.0750000000000002,"Solar",2014,"2014-12-22","2014-12-22",1,"2015-01-05",11,0,"2015-01-06","2015-01-22",0,null,null,null,null,null,null,null,null,null,null,null,"2015-01-22",24,null,"2015-05-07",null,0,"n/a",null,null,"2015-05-07","2015-06-09",24,0,"2015-02-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-01-21"]
["Charles Dupre","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S753-2014","2462413","R3","R","54129791000","151241001","885204532","256342009","169","Country Rd",null,null,"Agawam","MA","01001","WMECO","30A","30A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2014-12-31",6.9359999999999999,6.9359999999999999,8.67,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2014,"2014-12-31","2015-01-02",3,"2015-01-12",9,0,"2015-01-13","2015-01-30",0,null,null,null,null,null,null,null,null,null,null,"2015-06-09","2015-01-30",23,null,"needed",null,0,"n/a",null,null,"2015-05-11","2015-07-30",59,40,"2015-02-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-01-30"]
["Robert Wager","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-06-17","6S769-2015","2467850","R1","R","54340502095","015741006","865659812","344452008","170","Reservoir Rd",null,null,"Ludlow","MA","01056","WMECO","19S","19S2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-09",null,5.5120000000000005,6.89,"Class 1 (Solar / Wind)",null,6.0750000000000002,6.0750000000000002,6.0750000000000002,"Solar",2015,"2015-01-09","2015-01-09",1,"2015-01-13",3,0,"2015-01-14","2015-02-06",0,null,null,null,null,null,null,null,null,null,null,null,"2015-02-06",21,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-03-08",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-02-06"]
["Regina Tillery Jenkins","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S798-2015","2475023","R1","R","54628334021","813782002","894063552","636594001","1","Pearson Dr","Lot",26,"Springfield","MA","01119","WMECO","20A","20A33","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-20",7.5519999999999996,7.5519999999999996,9.44,"Class 1 (Solar / Wind)",null,8.3249999999999993,8.3249999999999993,8.3249999999999993,"Solar",2015,"2015-01-20","2015-01-20",1,"2015-01-23",4,0,"2015-01-26","2015-02-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-02-19",23,null,"2015-03-09",null,0,"n/a",null,null,"2015-03-25","2015-05-06",31,0,"2015-03-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-02-19"]
["Kyle Rodriguez",null,"SIMP",null,"Erik","Completed",null,"6S809-2015","2477930","R1","R","54026506063","904531006","894063500","683132005","43","Geneva St",null,null,"Indian Orchard","MA","01151","WMECO","05J","05J17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-01-23",2.8559999999999999,2.8559999999999999,3.57,"Class 1 (Solar / Wind)",null,3.15,3.15,3.15,"Solar",2015,"2015-01-23","2015-01-23",1,"2015-01-29",5,0,"2015-01-30","2015-02-23",0,null,null,null,null,null,null,null,null,null,null,"2015-09-11","2015-02-23",22,null,null,null,0,"n/a",null,null,"2015-04-21","2015-05-15",19,0,"2015-02-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-02-23"]
["Ronald Hendrix",null,"SIMP",null,"Erik","Completed",null,"6S834-2015","2483484","R1","R","54206402034","573641005","883502612","583152002","1186","River Rd",null,null,"Agawam","MA","01001","WMECO","16C","16C16","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-02-10",8.16,8.16,10.199999999999999,"Class 1 (Solar / Wind)",null,9,9,9,"Solar",2015,"2015-02-10","2015-02-10",1,"2015-02-24",11,0,"2015-02-25","2015-03-12",0,null,null,null,null,null,null,null,null,null,null,null,"2015-03-12",23,null,null,null,0,"n/a",null,null,"2015-10-02","2015-10-13",8,4,"2015-02-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-03-12"]
["Rudolph Ruggeri",null,"SIMP",null,"Erik","In Process",null,"6S866-2015","2491169","R1","R","54988661047","873321008","988331972","042312003","77","Bellwood Rd",null,null,"Springfield","MA","01119","WMECO","20A","20A35","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-03",null,4.9280000000000008,6.16,"Class 1 (Solar / Wind)",null,5.5,5.5,5.5,"Solar",2015,"2015-03-03","2015-03-03",1,"2015-03-18",12,0,"2015-03-19","2015-04-02",0,null,null,null,null,null,null,null,null,null,null,null,"2015-04-02",23,null,null,null,0,"n/a",null,null,null,null,30288,null,"2015-04-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-04-02"]
["Ruben Davis III","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-06-17","6S891-2015","2499905","R1","R","54862281060","541331001","887719712","226722005","37","Bulat Dr",null,null,"Springfield","MA","01129","WMECO","20A","20A35","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-23",null,7.3440000000000003,9.18,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-03-23","2015-03-23",1,"2015-03-24",2,0,"2015-03-25","2015-04-22",0,null,null,null,null,null,null,null,null,null,null,null,"2015-04-22",23,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-05-19",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-04-22"]
["Gary Montano","NRG","SIMP",null,"Erik","Cancelled","2015-05-13","6S911-2015","2503479","R1","R","54827691056","168141007","883509112","021242004","77","Valley View Cir",null,null,"West Springfield","MA","01089","WMECO",{"$f":"LEFT(Y4846,3)","v":"21N"},"21N4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-03-24",null,8.7720000000000002,10.965,"Class 1 (Solar / Wind)",null,9.6750000000000007,9.6750000000000007,9.6750000000000007,"Solar",2015,"2015-03-24","2015-03-25",2,"2015-04-27",25,0,"2015-04-27","2015-04-27",0,null,null,null,null,null,null,null,null,null,null,"2015-06-08","2015-04-27",25,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-05-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-04-27"]
["Frederick Asta Ferrero",null,"SIMP",null,"Erik","Cancelled","2015-09-10","6S945-2015","2510318","R3","R","54925791055","469241006","883769182","849242004","116","Massachusetts Ave",null,null,"Ludlow","MA","01056","WMECO","19S","19S3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-07",null,6.7840000000000007,8.48,"Class 1 (Solar / Wind)",null,7.2,7.27,7.2,"Solar",2015,"2015-04-07","2015-04-07",1,"2015-05-12",26,0,"2015-05-12","2015-05-12",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-12",26,null,null,null,0,"n/a",null,null,null,null,30288,null,"Dec 2014",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-12"]
["Jesus Garcia","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S956-2015","2515677","R2","R","54374302099","847541000","893139752","074252008","103","Eastern Ave",null,null,"Springfield","MA","01109","WMECO","21S","21S11","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-16",3.32,3.3200000000000003,4.1500000000000004,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-04-16","2015-04-17",2,"2015-05-13",20,0,"2015-05-14","2015-05-20",0,null,null,null,null,null,null,null,null,null,null,null,"2015-05-20",25,null,"2015-09-18",null,0,"n/a",null,null,"2015-06-23","2015-10-19",85,61,"2015-06-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-05-20"]
["R. Stephen Cook, Jr.",null,"SIMP",null,"Erik","Completed",null,"6S979-2015","2517823","R1","R","54660881095","314741007","866239672","457352002","631","Main Rd",null,null,"Granville","MA","01034","WMECO","29A","29A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-04-21",7.992,7.9920000000000009,9.99,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-04-21","2015-04-22",2,"2015-05-15",19,0,"2015-05-18","2015-06-15",13,null,null,null,null,null,null,null,null,null,null,null,"2015-06-15",{"$f":"IF(BL4914=0,NETWORKDAYS(AR4914,$A$4),NETWORKDAYS(AR4914,BL4914))","v":40},null,null,null,0,"n/a",null,null,"2015-09-17","2015-10-19",23,4,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-15"]
["Rosura Claudio","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-07-22","6S1013-2015","2522824","R2","R","54539271098","516721009","892420232","554912008","161","Eastern Ave",null,null,"Springfield","MA","01109","WMECO","21S","21S11","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-01",null,2.8559999999999999,3.57,"Class 1 (Solar / Wind)",null,3.15,3.15,3.15,"Solar",2015,"2015-05-01","2015-05-04",{"$f":"IF(AS4948=0,NETWORKDAYS(AR4948,$A$4),NETWORKDAYS(AR4948,AS4948))","v":2},"2015-06-17",34,4,"2015-06-18","2015-06-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-19",36,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-06-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-19"]
["Susan Hoynoski","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S1024-2015","2522901","R3","R","54567681085","468531006","884435152","327332007","213","Suffield St",null,null,"Agawam","MA","01001","WMECO","16C","16C16","PTF"," ","Photovoltaic","Inverter","Private","yes",null,"2015-05-04",13.26,13.26,16.574999999999999,"Class 1 (Solar / Wind)",null,14.35,14.35,14.35,"Solar",2015,"2015-05-04","2015-05-04",1,"2015-05-28",19,0,"2015-05-29","2015-06-14",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-14",30,null,"2015-10-08",null,0,"n/a",null,null,"2015-07-10","2015-10-27",78,63,"2015-07-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-14"]
["Clara Tereso","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-12-10","6S1046-2015","2526373","R1","R","54126602044","820841005","881808002","993452002","205","Colonial Dr",null,null,"Ludlow","MA","01056","WMECO","19S","19S3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-08",null,4.8960000000000008,6.12,"Class 1 (Solar / Wind)",null,5.4,5.4,5.4,"Solar",2015,"2015-05-08","2015-05-08",1,"2015-06-01",17,0,"2015-06-02","2015-06-23",0,null,null,null,null,null,null,null,null,null,null,null,"2015-06-23",33,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-06-24"]
["Eric Preston","Vivint Solar Developer, LLC","SIMP",null,"Erik","In Process",null,"6S1081-2015","2531709","R1","R","54126425024","955741009","866463812","862552003","103","Frederick St","Lot","C1","West Springfield","MA","01089","WMECO","21N","21N6","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-19",null,7.7519999999999998,9.69,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-05-19","2015-05-19",1,"2015-06-04",13,0,"2015-06-05","2015-07-08",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-08",37,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-09"]
["Charlotte Marks","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1103-2015","2533920","R1","R","54882491020","653041001","988282712","700142001","70","Whittum Ave",null,null,"Springfield","MA","01118","WMECO",{"$f":"LEFT(Y5038,3)","v":"20A"},"20A32","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-05-27",3.2639999999999998,3.2640000000000002,4.08,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-05-27","2015-05-27",1,"2015-06-11",12,0,"2015-06-12","2015-07-09",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-09",32,null,"2015-11-04",null,0,"n/a",null,null,"2015-11-04","2015-11-18",11,6,"2015-07-27",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-09"]
["Scott Trahan","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S1135-2015","2540789","R3","R","54525071023","857521004","881806052","510712001","35","South West St",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-03",6.9359999999999999,6.9359999999999999,8.67,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-06-03","2015-06-04",2,"2015-06-30",20,2,"2015-07-01","2015-07-22",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-22",36,null,"2015-10-06",null,0,"n/a",null,null,"2015-10-02","2015-10-23",16,2,"2015-08-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-22"]
["Henry Dobosz","SolarCity Corp","SIMP",null,"Erik","In Process",null,"6S1137-2015","2540795","R1","R","54101884088","779031008","881099782","274522003","159","Burbank Rd",null,null,"Longmeadow","MA","01106","WMECO","22H","22H12","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-03",null,6.032,7.54,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-06-03","2015-06-04",2,"2015-06-30",20,2,"2015-07-01","2015-07-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15",31,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-08-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-15"]
["Francis Keefe","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1168-2015","2551632","R1","R","54256191016","595831007","988101632","014732000","93","Druid Hill Rd",null,null,"Springfield","MA","01129","WMECO","20A","20A34","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-12",4.992,4.9920000000000009,6.24,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-06-12","2015-06-16",3,"2015-07-21",28,10,"2015-07-22","2015-07-30",0,null,null,null,null,null,null,null,null,null,null,null,"2015-07-30",35,null,"2015-09-02",null,0,"n/a",null,null,"2015-08-17","2015-10-22",49,12,"2015-08-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-07-30"]
["Stacy Wieners","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1194-2015","2552725","R4","R","54769794066","123721008","894709402","601022006","67","Debra Ln",null,null,"Agawam","MA","01001","WMECO","30A","30A5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-17",6.12,6.120000000000001,7.65,"Class 1 (Solar / Wind)",null,6.75,6.75,6.75,"Solar",2015,"2015-06-17","2015-06-19",3,"2015-07-21",25,1,"2015-07-22","2015-08-07",5,null,null,null,null,null,null,null,null,null,null,null,"2015-08-10",39,null,"2015-08-25",null,0,"n/a",null,null,"2015-08-24","2015-09-30",28,1,"2015-08-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-11"]
["Knolly Farrell","NRG Home Solar","SIMP",null,"Erik","Cancelled","2015-08-04","6S1216-2015","2553506","R3","R","54612202051","455441002","988679242","062942004","23","Lakevilla Ave",null,null,"Springfield","MA","01109","WMECO","20A","20A22","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-22",null,4.1696,5.2119999999999997,"Class 1 (Solar / Wind)",null,4.7249999999999996,4.7249999999999996,7.7249999999999996,"Solar",2015,"2015-06-22","2015-06-23",2,"2015-07-24",25,0,"2015-07-27","2015-08-04",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04",32,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-29",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-04"]
["Patricia Ross","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1233-2015","2554202","R1","R","54726764020","975521007","891713342","828612006","135","Aldrew Ter",null,null,"Springfield","MA","01119","WMECO","20A","20A14","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-06-24",4.2880000000000003,4.2880000000000003,5.36,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-06-24","2015-06-26",3,"2015-08-07",33,0,"2015-08-07","2015-08-10",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-10",34,null,"2015-10-05",null,0,"n/a",null,null,"2015-09-24","2015-10-22",21,7,"2015-08-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-10"]
["Ana Rodriguez","Vivint Solar Developer, LLC","SIMP",null,"Erik","Cancelled","2015-11-25","6S1273-2015","2554993","R2","R","54846661015","682421006","981252002","083212000","111","Stockman St",null,null,"Springfield","MA","01104","WMECO","05J","05J9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-03",null,3.7439999999999998,4.68,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-07-03","2015-07-07",3,null,154,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,154,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Edward Hamel","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1298-2015","2558420","R1","R","54936591031","203041002","883813702","702042002","400","Poplar St",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-09",2.9119999999999999,2.9120000000000004,3.64,"Class 1 (Solar / Wind)",null,3.15,3.15,3.15,"Solar",2015,"2015-07-09","2015-07-09",1,"2015-08-05",20,0,"2015-08-06","2015-08-21",0,null,null,null,null,null,null,null,null,null,null,null,"2015-08-24",33,null,"2015-10-05",null,0,"n/a",null,null,"2015-09-22","2015-10-23",24,9,"2015-09-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-08-25"]
["Roger Landry","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S1307-2015","2559142","R3","R","54191681022","895531003","885067012","791232000","32","Wrenwood Ln",null,null,"Agawam","MA","01001","WMECO","30A","30A1"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-13",2.496,2.4960000000000004,3.12,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-07-13","2015-07-14",2,"2015-08-06",19,0,"2015-08-07","2015-09-21",15,null,null,null,null,null,null,null,null,null,null,null,"2015-09-22",52,null,"2016-01-13",null,0,"n/a",null,null,"2015-10-23","2016-01-26",68,54,"2015-08-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-09-22"]
["Thomas Labonte","Vivint Solar Developer, LLC","SIMP",null,"Erik","Completed",null,"6S1329-2015","2560625","R1","R","54186191078","443831009","988136102","543832006","26","Boyd St",null,null,"Springfield","MA","01108","WMECO","22H","22H15","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-07-14",4.5759999999999996,4.5759999999999996,5.72,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-07-14","2015-07-16",3,"2015-08-11",21,0,"2015-08-12","2015-09-03",0,null,null,null,null,null,null,null,null,null,null,null,"2015-09-04",39,null,"2015-10-05",null,0,"n/a",null,null,"2015-09-28","2015-10-23",20,5,"2015-09-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-09-04"]
["John Buldrini","SolarCity Corp","SIMP",null,"Erik","Completed",null,"6S1355-2015","2564542","R3","R","54597571009","456821000","868011352","247022009","210","Mort Vining Rd",null,null,"Southwick","MA","01077","WMECO","29A","29A5","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-07-21",8.32,8.32,10.4,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-07-21","2015-07-21",1,"2015-08-21",24,0,"2015-08-24","2015-09-10",0,null,null,null,null,null,null,null,null,null,null,null,"2015-09-10",38,null,"2015-12-29",null,0,"n/a",null,null,"2015-10-21","2015-12-31",52,46,"2015-09-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-09-10"]
["Dr Cyril Shea, Jr.","SolarCity Corp","SIMP",null,"Erik","In Process",null,"6S1386-2015","2577343","R1","R","54931402077","053541008","882119122","337252006","116","Forest Ridge Rd",null,null,"West Springfield","MA","01089","WMECO","21N","21N4","PTF"," ","Photovoltaic","Inverter","Private","needed",null,"2015-07-31",null,12.48,15.6,"Class 1 (Solar / Wind)",null,12,12,12,"Solar",2015,"2015-07-31","2015-08-03",2,"2015-08-31",22,0,"2015-09-01","2015-10-06",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-07",49,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-07-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-07"]
["Joseph Lapointe",null,"SIMP",null,"Carla","Completed",null,"6S1396-2015","2577614","R1","R","54978446094","763331000","883818252","698822001","45","Glenwood St",null,null,"Ludlow","MA","01056","WMECO","27A","27A4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-04",2.9120000000000004,2.9120000000000004,3.64,"Class 1 (Solar / Wind)",null,3.15,3.15,3.15,"Solar",2015,"2015-08-04","2015-08-06",3,"2015-09-18",34,12,"2015-09-21","2015-10-01",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-02",44,null,null,null,0,"n/a",null,null,"2015-10-19","2015-10-29",9,1,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-02"]
["Robert Deyo","NRG Home Solar","SIMP",null,"Carla","Completed",null,"6S1420-2015","2580988","R1","R","54110102076","788341007","868379612","534942006","342","Barry St",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-10",4.9720000000000004,4.9720000000000004,6.2149999999999999,"Class 1 (Solar / Wind)",null,6.625,5.625,5.625,"Solar",2015,"2015-08-10","2015-08-11",2,"2015-10-13",47,0,"2015-10-14","2015-10-14",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-14",48,null,"2015-11-10",null,0,"n/a",null,null,"2015-11-02","2015-11-25",18,6,"2015-09-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15"]
["Richard Hickling, Jr.","SolarCity Corp","SIMP",null,"Carla","Completed",null,"6S1442-2015","2584951","R1","R","54138602065","106841006","885667282","378552005","33","Tanglewood Dr","Lot",8,"Springfield","MA","01129","WMECO","20A","20A14","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-08-17",7.9039999999999999,7.9040000000000008,9.8800000000000008,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-08-17","2015-08-19",3,"2015-10-14",43,0,"2015-10-15","2015-10-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15",44,null,"2015-10-20",null,0,"n/a",null,null,"2015-10-30","2015-12-18",36,27,"2015-10-17",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15"]
["Michael Commins","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6S1477-2015","2587771","R1","R","54202306023","046921003","979895122","846222006","23","Russell St",null,null,"Springfield","MA","01104","WMECO","05J","05J12","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-24",null,3.2520000000000007,4.0650000000000004,"Class 1 (Solar / Wind)",null,4.05,4.05,4.05,"Solar",2015,"2015-08-24","2015-08-25",2,"2015-10-15",39,0,"2015-10-15","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",40,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-10-04",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-26"]
["Robin Waterman",null,"SIMP",null,"Carla","Completed",null,"6S1499-2015","2588816","R3","R","54108071069","239521000","883950772","896612005","46","Orlando St",null,null,"Feeding Hills","MA","01030","WMECO","30A","30A6"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-08-31",{"$f":"AI5434","v":3.8759999999999999},3.8759999999999999,4.8449999999999998,"Class 1 (Solar / Wind)",null,4.25,4.25,4.25,"Solar",2015,"2015-08-31","2015-09-01",2,"2015-10-15",34,0,"2015-10-15","2015-10-15",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-15",34,null,null,null,0,"n/a",null,null,"2015-10-27","2015-11-25",22,1,"2015-11-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2015,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-17"]
["Brian Barci","Vivint Solar Developer, LLC","SIMP",null,"Carla","Completed",null,"6S1518-2015","2590589","R1","R","54012981049","718631000","866761902","275532003","179","Woodmont St",null,null,"West Springfield","MA","01089","WMECO","21N","21N9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-02",5.8239999999999998,5.8240000000000007,7.28,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-09-02","2015-09-03",2,"2015-10-15",32,0,"2015-10-15","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",33,null,"2016-01-15",null,0,"n/a",null,null,"2015-11-30","2016-01-26",42,32,"2015-11-02",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-10-31"]
["Teresa Kurowska","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1556-2015","2599873","R1","R","54306295098","889223005","892657012","917176000","418","Kent Rd",null,null,"Springfield","MA","01129","WMECO","20A","20A35","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-14",null,4.16,5.2,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-09-14","2015-09-14",1,"2015-10-16",{"$f":"IF(AU5491=0,NETWORKDAYS(AR5491,$A$4),NETWORKDAYS(AR5491,AU5491))","v":25},0,"2015-10-16","2015-10-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-16",25,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-11-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-11-03"]
["Daniel Santana","Sunnova Energy Corp","SIMP",null,"Carla","Completed",null,"6S1578-2015","2603981","R1","R","54769475070","144841001","889289922","767652003","15","Jimmy Ct","Lot",8,"Springfield","MA","01104","WMECO","05J","05J10","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-09-18",8.7360000000000007,8.7360000000000007,10.92,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-09-18","2015-09-21",2,"2015-11-17",43,20,"2015-11-17","2015-11-17",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-18",44,null,"2016-01-19",null,0,"n/a",null,null,"2015-12-09","2016-01-27",36,26,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2016,null,null,null,null,null,"net metering"]
["Melissa Murray","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1583-2015","2604022","R2","R","54006171052","351421008","885584612","464312000","636","Fuller St",null,null,"Ludlow","MA","01056","WMECO","19S","19S3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-21",null,2.08,2.6,"Class 1 (Solar / Wind)",null,2.25,2.25,2.25,"Solar",2015,"2015-09-21","2015-09-21",1,"2015-10-16",20,0,"2015-10-16","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",21,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-11-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-11-03"]
["Maria Otero","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1612-2015","2604533","R1","R","54069102036","255441007","893665382","456842002","345","Parkerview St",null,null,"Springfield","MA","01129","WMECO","20A","20A35","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-09-28",null,7.0720000000000001,8.84,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-09-28","2015-09-29",2,"2015-10-16",15,0,"2015-10-16","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",16,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-11-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-11-03"]
["Michelle Hunt","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1640-2015","2610603","R1","R","54851981092","864731003","868921042","271632008","40","Meadowbrook Rd",null,null,"Agawam","MA","01001","WMECO","30A","30A5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-05",null,4.16,5.2,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-10-05","2015-10-05",1,"2015-10-19",11,0,"2015-10-19","2015-10-19",0,null,null,null,null,null,null,null,null,null,null,null,"2015-10-19",11,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-05",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2015-11-04"]
["Karen Blair","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1669-2015","2615994","R1","R","54812391084","982931005","884967052","886932007","44","Portland St",null,null,"Feeding Hills","MA","01030","WMECO","16C","16C17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-14",null,7.0720000000000001,8.84,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-10-14","2015-10-14",1,"2015-11-17",25,0,"2015-11-17","2015-11-17",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-18",26,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-14",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Theresa Zheleznyakov","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1691-2015","2614272","R1","R","54444071096","710621007","882141182","730712008","307","Green Hill Rd",null,null,"Longmeadow","MA","01106","WMECO","22H","22H11","PTF"," ","Photovoltaic","Inverter","Private","needed",null,"2015-10-20",null,10.608000000000001,13.26,"Class 1 (Solar / Wind)",null,12,12,12,"Solar",2015,"2015-10-20","2015-10-20",1,"2015-11-24",26,0,"2015-11-24","2015-11-24",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-24",26,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Momoh Kamara",null,"SIMP",null,"Carla","In Process",null,"6S1705-2015","2614420","R1","R","54553871021","660003005","888554782","665145005","230","Draper St",null,null,"Springfield","MA","01108","WMECO","22H","22H15","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-22",null,5.4080000000000004,6.76,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-10-22","2015-10-22",1,"2015-11-16",18,0,"2015-11-16","2015-11-16",0,null,null,null,null,null,null,null,null,null,null,null,"2015-11-17",19,null,null,null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Brian Longey","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1725-2015","2618553","R1","R","54797281011","258231002","881955652","307722000","470","North Westfield St",null,null,"Feeding Hills","MA","01030","WMECO","16C","16C17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-10-28",null,6.24,7.8,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-10-28","2015-10-28",1,"2015-12-01",25,0,"2015-12-01","2015-12-01",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-01",25,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Kenneth A Kubik","NRG Home Solar","SIMP",null,"Carla","In Process",null,"6S1762-2015","2630006","R1","R","54930681093","078431004","881966112","872332008","63","Pleasant St",null,null,"Feeding Hills","MA","01030","WMECO","16C","16C17","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-09",null,5.6159999999999997,7.02,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-11-09","2015-11-09",1,"2015-12-04",20,0,"2015-12-04","2015-12-04",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-08",22,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Paul Page","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1770-2015","2632737","R1","R","54358675015","952141009","868637052","144142000","235","James St",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-12",null,6.8640000000000008,8.58,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-11-12","2015-11-12",1,"2015-12-07",18,0,"2015-12-07","2015-12-07",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-09",20,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-01-09",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Ronald Gaudette","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S1808-2015","2635709","R1","R","54544861032","881099732","881099732","480312002","29","Pomeroy St",null,null,"Agawam","MA","01001","WMECO",{"$f":"LEFT(Y5739,3)","v":"16C"},"16C16","PTF"," ","Photovoltaic","Inverter",null,null,null,"2015-11-17",null,{"$f":"AJ5739*0.8","v":5.2},6.5,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2015,"2015-11-17","2015-11-19",3,null,{"$f":"IF(AU5739=0,NETWORKDAYS(AR5739,$A$4),NETWORKDAYS(AR5739,AU5739))","v":57},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(BL5739=0,NETWORKDAYS(AR5739,$A$4),NETWORKDAYS(AR5739,BL5739))","v":57},null,"needed",null,0,"n/a",null,null,null,null,{"$f":"IF(BV5739=0,NETWORKDAYS(BU5739,$A$4),NETWORKDAYS(BU5739,BV5739))","v":30288},null,"2016-01-16"]
["Robert Dickson","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1827-2015","2640782","R1","R","54079502001","722641002","884922842","795352009","22","Trinity Dr",null,null,"West Springfield","MA","01089","WMECO","21N","21N9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-11-23",null,4.5759999999999996,5.72,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2015,"2015-11-23","2015-11-23",1,"2015-12-14",16,0,"2015-12-14","2015-12-14",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-15",17,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2015-12-23",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Gail Kennedy","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1861-2015","2644161","R1","R","54292661097","512321008","988880182","802312008","71","Judith S",null,null,"Springfield","MA","01118","WMECO","20A","20A22","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-03",null,2.4960000000000004,3.12,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-12-03","2015-12-03",1,"2015-12-31",21,7,"2016-01-04","2016-01-20",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-20",35,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Mark R Grenier","Sunnova Energy Corp","SIMP",null,"Carla","In Process",null,"6S1884-2015","2646231","R1","R","54073602039","773741000","892085592","317352002","133","Wedgewood Dr",null,null,"Ludlow","MA","01056","WMECO","19S","19S3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-10",null,6.6560000000000006,8.32,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-12-10","2015-12-10",1,"2015-12-24",11,0,"2015-12-28","2015-12-28",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-28",13,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"not supplied",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Matthew R Lillibridge","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1906-2015","2648964","R1","R","54409227014","340621006","988238772","287512005","162","Hartford Ter",null,null,"Springfield","MA","01118","WMECO","20A","20A32","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-15",null,2.9120000000000004,3.64,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Solar",2015,"2015-12-15","2015-12-15",1,"2015-12-29",11,0,"2015-12-29","2015-12-29",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-30",12,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-01-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Joseph N Werner","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1917-2015","2649146","R1","R","54470861071","108321002",867084912,"807412006","34","Fox St",null,null,"West Springfield","MA","01089","WMECO","21N","21N9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-16",null,7.9040000000000008,9.8800000000000008,"Class 1 (Solar / Wind)",null,8.35,8.35,8.35,"Solar",2015,"2015-12-16","2015-12-16",1,"2015-12-28",9,0,"2015-12-29","2015-12-29",0,null,null,null,null,null,null,null,null,null,null,null,"2015-12-30",11,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Vernon L. Johnson Jr","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1949-2015","2664018","R1","R","54999566011","381621001",988884842,"106612003","38","Inglewood Ave",null,null,"Springfield","MA","01119","WMECO","20A","20A34","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-23",null,5.8240000000000007,7.28,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2015,"2015-12-23","2015-12-23",1,"2016-01-07",12,0,"2016-01-07","2016-01-07",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-07",12,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-22",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Lorraine B Woods","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1974-2015","2665366","R1","R","54899971071","088031002","893984242","340622006","93","Tatham Hill Rd",null,null,"West Springfield","MA","01089","WMECO","21N","21N4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2015-12-29",null,3.3280000000000003,4.16,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2015,"2015-12-29","2015-12-29",1,"2016-01-12",11,0,"2016-01-12","2016-01-12",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-12",11,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-02-28",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Sarah J Peczka","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S1982-2015","2665450","R1","R","54024316010","916341003","121814443","553642005","15","Old Coach Cir","Lot",41,"Springfield","MA","01056","WMECO","19S","19S3","PTF"," ","Photovoltaic","Inverter","No Cap","n/a per cadmus",null,"2015-12-29",null,9.36,11.7,"Class 1 (Solar / Wind)",null,10.95,10.95,10.95,"Solar",2015,"2015-12-29","2015-12-30",2,"2016-01-12",11,0,"2016-01-12","2016-01-12",0,null,null,null,null,null,null,null,null,null,null,null,"2016-01-12",11,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-06-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Robert G Smith","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S2019-2016","2667924","R1","R","54312302011","830541002","867921112","589052000","100","Waverly Rd","lot",13,"Ludlow","MA","01056","WMECO","19S","19S2","PTF"," ","Photovoltaic","Inverter",null,null,null,"2016-01-08",null,10.192,12.74,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2016,"2016-01-08","2016-01-08",1,null,19,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,19,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-03-08",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Ron Hudon","Vivint Solar Developer, LLC","SIMP",null,"Carla","In Process",null,"6S2030-2016","2669600","R1","R","54086844040","203931005","867077232","224832009","119","Howard St","apt"," Left","Ludlow","MA","01056","WMECO","27A","27A6","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-01-12",null,3.7439999999999998,4.68,"Class 1 (Solar / Wind)",null,4.1500000000000004,4.1500000000000004,4.1500000000000004,"Solar",2016,"2016-01-12","2016-01-12",1,"2016-01-19",6,0,"2016-01-19","2016-01-22",3,null,null,null,null,null,null,null,null,null,null,null,"2016-01-25",10,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Eurico Ferreira","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S2072-2016","2675077","R1","R","54144596061","397321004",964352092,"535212002","325","Gillette Ave",null,null,"Springfield","MA","01118","WMECO","20A","20A32","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-01-25",null,4.8960000000000008,6.12,"Class 1 (Solar / Wind)",null,6,6,6,"Solar",2016,"2016-01-25","2016-01-25",1,"2016-02-01",6,0,"2016-02-01","2016-02-01",0,null,null,null,null,null,null,null,null,null,null,null,"2016-02-02",7,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-03-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Elnora Smith","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S2076-2016","2675671","R1","R","54619191083","888731004",988422182,"945832007","224","Hartwick St",null,null,"Springfield","MA","01108","WMECO","22H","22H16","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2016-01-26",null,4.7840000000000007,5.98,"Class 1 (Solar / Wind)",null,5.45,5.45,5.45,"Solar",2016,"2016-01-26","2016-01-26",1,"2016-02-04",8,0,"2016-02-04","2016-02-04",0,null,null,null,null,null,null,null,null,null,null,null,"2016-02-04",8,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"2016-03-25",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Wayne Day","SolarCity Corp","SIMP",null,"Carla","In Process",null,"6S2105-2016","2680377","R1","R","54698402013","221641004","881107352","630352000","59","Nora Ln",null,null,"Ludlow","MA","01056","WMECO","27A","27A4","PTF"," ","Photovoltaic","Inverter",null,null,null,"2016-02-04",null,9.5680000000000014,11.96,"Class 1 (Solar / Wind)",null,null,null,null,"Solar",2016,"2016-02-04","2016-02-04",1,null,-2,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,-2,null,"needed",null,0,"n/a",null,null,null,null,30288,null,"04/3/2016",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"net metering"]
["Jiminy Peak Mountain Resort, Inc.- NGRID customer",null,"OTHER",null,"Cindy","Completed",null,"NGRID-2006-1",null,null,null,"NGRID","NGRID","NGRID",null,"37","Corey Rd",null,null,"Hancock","MA","01237","NGRID","15E","15E1 - NGRID","PTF"," ","Wind Turbine","wind turbine","n/a",null,null,"n/a",0,null,null,"N/A",null,1500,1500,1500,"Wind","2006 NGRID","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a","n/a = NGRID",null,null,"n/a = NGRID","n/a",null,"Yes - written",null,"2007-08-07",null,null,null,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2007,null,null,null,null,null,"n/a - NGRID - will export with limits in IA","witness test maybe 7/24/07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"NGRID - approved","NGRID",null,"N.R."]
["Peter Derrico",null,"OTHER",null,null,"Completed",null,"19Solar Avenue II",null,"R1","R",54814791059,"422241000",888508322,548242004,"340","Long Plain Rd",null,null,"Leverett","MA","01054","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-16",1,0,null,"Class 1 (Solar / Wind)",null,1,1,1,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2005-05-01",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2005,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Andrew Bristol",null,"OTHER",null,null,"Removed",null,"WMECO Pilot3",null,"R1","R","54138971023","541131004","888508012","368522001","80","Margaret Ln",null,null,"Ludlow","MA","01056","WMECO","19S","19S1","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"N/A",null,null,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,"2001-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2001 - removed",null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"WMECO?","N","removed"]
["James Cusimano",null,"OTHER",null,null,"Completed",null,"WMECO Pilot4",null,"R1","R","54523181089","569131000","888508202","363722007","67","Foundry Village Rd",null,null,"Colrain","MA","01340","WMECO","29R","29R2","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-13",0.54,{"$f":"AJ6103*0.8","v":0},null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2000-12-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2000,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["John McCarran (see 6A155-2011 addition)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot5",null,"R1","R","54469081061","726131002","888508182","264622005","42","Carriage Ln",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"see 6A155-2011",0.48,{"$f":"AJ6104*0.8","v":0.48},0.6,"Class 1 (Solar / Wind)",null,null,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-05-21",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Howard M. Meister (was Rick Lafontaine)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot6",null,"R1","R","54641181060","755231001","888508172","356622005","132","Stage Rd",null,null,"Cummington","MA","01026","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2012-04-26",0.54,null,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2004-06-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2004,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Gisele Zuchara",null,"OTHER",null,null,"Completed",null,"WMECO Pilot7",null,"R3","R","54865281000","699231001","888508082","250722009","207","Mallowhill Rd",null,null,"Springfield","MA","01101","WMECO","20A","20A23","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-15",0.54,{"$f":"AJ6106*0.8","v":0},null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-05-16",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Woolman Hill Inc., The Red House",null,"OTHER",null,null,"Completed",null,"WMECO Pilot8",null,"R1","R","54961481033","836331004","888508312","619822002","107","Keets Rd",null,null,"Deerfield","MA","01342","WMECO","22B","22B4","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-11",1.08,0,null,"Class 1 (Solar / Wind)",null,1.08,1.08,1.08,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-11-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Jean Schwartz / John Coull",null,"OTHER",null,null,"Completed",null,"WMECO Pilot9",null,"R1","R","54009381013","227331004","888508042","050032009","20","Sheerman Ln",null,null,"Amherst","MA","01002","WMECO","18G","18G7"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-04",0.54,0,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-06-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Ann Gail Hult (was Angeline Bregianes)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot10",null,"R1","R","54035291087","342831008","888508062","360932007","167","Woodcrest Rd",null,null,"Springfield","MA","01101","WMECO","20A","20A34","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-11",0.54,0,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2000-12-08",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2000,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Jane & Stephan Smith",null,"OTHER",null,null,"Completed",null,"WMECO Pilot11",null,"R1","R","54899391007","041931008","888508342","391932009","15","Oakman St",null,null,"Turners Falls","MA","01376","WMECO","29H","29H1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-01-18",0.54,0,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-12-07",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Luis Negron",null,"OTHER",null,null,"Completed",null,"WMECO Pilot12",null,"R1","R","54808491062","546041003","888508352","891932004","390","Newhouse St",null,null,"Springfield","MA","01101","WMECO","20A","20A21","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2009-12-28",0.54,0,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2000-12-18",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2000,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Clifford Smart (was Sharon Rust)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot13",null,"R1","R","54893065045","313141009","888508372","460242005","50","Buffington Hill Rd",null,null,"Worthington","MA","01098","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-03-10",0.5,0,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-11-21",null,null,null,"2011-03-10",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Deborah Stelzer (was Ralph Shapiro / Carolyn Charette)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot14",null,"R1","R","54566002069","678341000","888508122","017842005","82","Country View St","Lot ",7,"West Springfield","MA","01089","WMECO","21N","21N9","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2012-06-08",0.54,null,null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-11-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Daniel Dee (was Jonathan Bete)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot15",null,"R1","R","54258402015","852741006","888507982","089252000","499","Old Farm Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K8"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-21",0.54,{"$f":"AJ6114*0.8","v":0},null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2000-12-06",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2000,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Arnold Krugman (was Paul Redstone) ?",null,"OTHER",null,null,"Cancelled",null,"WMECO Pilot16",null,"R1","R","54781402029","948641007","885840212","084252004","82","Claybrook Rd",null,null,"Sunderland","MA","01375","WMECO","18G","18G3"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",{"$f":"AI6115","v":0},null,null,"N/A",null,null,null,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.",null,"n/a",null,null,0,"n/a",null,null,null,"12/11/2001 ???",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","field checked April 9, 2010, no PV, cancelled",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","Cancelled"]
["William B. Tobey (new appl 6A348-2012)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot17",null,"R1","R","54260602040","194741001","888508102","500552003","318","Harkness Rd",null,null,"Amherst","MA","01002","WMECO","17K","17K2"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"2011-02-16",0.54,{"$f":"AJ6116*0.8","v":0},null,"Class 1 (Solar / Wind)",null,null,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-11-20",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Maria Koziol Guerra (was Delbert C. Glover)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot18",null,"R1","R","54674996095","306741005","888508002","218552007","25","Cole Rd",null,null,"West Hatfield","MA","01088","WMECO","18G","18G5"," ","non-PTF","Photovoltaic","Inverter","No Cap","n/a",null,"MIMO - Needed",0,{"$f":"AJ6117*0.8","v":0},null,"N/A because no Schedule Z on file",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-10-05",null,null,null,"2014-12-15",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Sadao Yagi   (Louise Palmer)",null,"OTHER",null,null,"Completed",null,"WMECO Pilot19",null,"R3","R","54366602084","076741005","888243712","356552006","20","Mallery Rd","Lot",1,"New Ashford","MA","01237","WMECO","15E","15E1","PTF"," ","Photovoltaic","Inverter","No Cap","n/a",null,"2010-03-01",0.54,{"$f":"AJ6118*0.8","v":0},null,"Class 1 (Solar / Wind)",null,0.54,0.54,0.54,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"2001-11-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2001,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"WMECO?","N"]
["Solutia - (West Sub)",null,"OTHER",null,"Cindy","Completed",null,"Historic 1",null,"PR-T2",null,"54170561013","??","??","682805002","730","Worcester St",null,null,"Springfield","MA","01151","WMECO","27A","27A11 & 27A12","PTF"," ","Steam Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,5685,5685,5685,"Coal","n/a","n.r.","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"needed",null,null,"$5M / $5M","needed",null,"Yes",null,"1984-05-01",null,null,"historic",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Historic generator.",1984,"needed","needed",null,null,"??","no export","historic generator received information 2010 for review, ISO aware of generator per Paul Sousa",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved","Y",null,"??"]
["Crane & Company (Byron - Weston Mill) Historic CHP ",null,"OTHER",null,"Carla","Completed",null,"Historic 2",null,null,"I","54999461098","049221009","000010690","444212007","800","Main St",null,null,"Dalton","MA","01226","WMECO","19A","19A6 or 19A2 & 19A3","PTF"," ","Steam Turbine","generator","n/a",null,null,"no export",0,null,null,"No Export",null,220.7,220.7,220.7,"Natural Gas",2011,"2011-06-20","n.r.","n/a","2011-07-18",{"$f":"IF(AU6120=0,NETWORKDAYS(AR6120,$A$4),NETWORKDAYS(AR6120,AU6120))","v":21},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-04-30",{"$f":"IF(BL6120=0,NETWORKDAYS(AR6120,$A$4),NETWORKDAYS(AR6120,BL6120))","v":487},"2013-05-10",null,null,"Combined amt $1M / $1M","see 6B106-2011",null,null,"2013-09-25","2013-10-03",null,23,"historic",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Historic generator. Impact Study in progress. Historic CHP, reviewing with new application. May not export. This generator was restudied with the Pioneer Mill CHP and the new hydro. Was previosly out of service in 2012. On line 10/3/13.",1989,"needed","needed",null,null,"??","no export","historic generator received information 2011 for review",null,null,null,null,null,"Crane & Co, Inc.\nAttn: James Noles","30 South Street","Dalton","MA","01226","413-684-6319","413-684-1789","N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Future",null,null,"n/a"]
["Southworth historic cogen",null,"OTHER",null,"Cindy","In Process",null,"Historic 3",null,"PR-T2","I","54870106085","222923009","890472272","637112001","36","Canal Rd",null,null,"Turners Falls","MA","01376","WMECO","21C","21C6","PTF"," ","Steam Turbine","cogeneration unit","n/a",null,null,"no export",0,null,null,"No Export",null,null,null,229,"Diesel",2012,"2012-01-10","not sure","not sure",null,{"$f":"IF(AU6121=0,NETWORKDAYS(AR6121,$A$4),NETWORKDAYS(AR6121,AU6121))","v":1062},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-03-27",{"$f":"IF(BL6121=0,NETWORKDAYS(AR6121,$A$4),NETWORKDAYS(AR6121,BL6121))","v":317},"needed",null,null,"see 6F295-2012","needed",null,null,null,null,{"$f":"IF(BV6121=0,NETWORKDAYS(BU6121,$A$4),NETWORKDAYS(BU6121,BV6121))","v":30288},null,"historic",null,"see 6F295-2012","see 6F295-2012",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Historic generator. Impact Study in progress. Will not export. Review with new hydro.","historic","needed","needed",null,null,null,"no export","historic generator",null,null,null,null,null,null,null,null,null,null,null,null,"F",null,null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"Future",null,"*****"]
["Yankee Environmental Systems",null,"OTHER",null,"Cindy","Completed",null,"Historic 4",null,"G0","C","54483402020","184641001","893322402","303352001","101","Industrial Blvd",null,null,"Turners Falls","MA","01376","WMECO","21C","21C3","PTF"," ","Wind Turbine","Inverter","Private",null,null,"2013-03-13",10,null,null,"Class 1 (Solar / Wind)",null,10,10,10,"Wind",2013,"2013-03-13","2013-03-13",{"$f":"IF(AS6122=0,NETWORKDAYS(AR6122,$A$4),NETWORKDAYS(AR6122,AS6122))","v":1},"2013-03-27",{"$f":"IF(AU6122=0,NETWORKDAYS(AR6122,$A$4),NETWORKDAYS(AR6122,AU6122))","v":11},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2013-03-28","n/a","2013-04-16",null,null,0,"n/a",null,null,null,"2001",null,null,"historic",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Historic generator.",2001,null,null,null,null,null,"net metering","historic generator on line in 2001, received info in 2013 for review, mismatch 1 phase inverter on service",null,null,null,null,null,"Attn:  Mark Beaubien","101 Industrial Boulevard","Turners Falls","MA","01376",4138630200,4138630255,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y"]
["Gardners Falls Hydro Electric Facility",null,"OTHER",null,"Cindy","In Process",null,"Historic 5",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"WMECO","22B","22B5 & 22B6","PTF"," ","Hydro","hydro generator","n/a",null,null,null,null,null,null,"Market Participant",null,2580,2580,"1300. 940, 940, 400","Hydro",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"6F420451",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Q4 2015"]
["Interland Real Estate, LLC","Ocean Air Aviation","OTHER",null,"Erik","In Process",null,"Historic 6",null,null,null,null,null,null,null,"180","Pleasant St",null,null,"Easthampton","MA","01027","WMECO","15A","15A ","PTF"," ","Wind Turbine","Inverter","No Cap","n/a",null,null,null,null,null,"Class 1 (Solar / Wind)",null,3.3,3.3,3.3,"Wind",2014,"2014-11-14","n/a","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"needed",null,null,null,null,null,null,null,null,null,null,"needed"]
["NESEA (new 6F360-2012)",null,"OTHER",null,null,"Completed",null,"?",null,"G0","C","54666861018","551521009","890092332","095412009",null,"Miles St",null,null,"Greenfield","MA","01301","WMECO","28W","28W4","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"no export",0,null,null,"No Export",null,null,1,1,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a",null,null,0,"n/a",null,null,null,"1999-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1999,null,null,null,null,null,"n/a - not expected to export",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??","N"]
["Robert Jensen (was Kamal Souccar) ?",null,"OTHER",null,null,"Cancelled",null,"?",null,"R1","R","54712502020","970741001","891626102","284452001","21","Dodwells Rd",null,null,"Cummington","MA","01026","WMECO","18K","18K2"," ","non-PTF","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"N/A",null,null,null,0.5,"Solar","n/a","n.r.","n.r.","n/a","n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.",null,"n/a",null,null,0,"n/a",null,null,null,"10/30/2001 ???",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"net metering","field checked April 9, 2010, no PV, cancelled",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","Cancelled"]
["Turners Falls Hydro LLC (owned by Swift River Hydro), was Strathmore Paper",null,"OTHER",null,null,"Completed",null,"-",null,"G0","C","54413561044","563321006","078004411","234012002",null,"Canal St",null,null,"Turners Falls","MA","01376","WMECO","21C","21C6","PTF"," ","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"Market Participant",null,950,950,950,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ISO - ?",null,null,"??","Yes"]
["Crane & Company (gen @ Byron Weston Mill) DO NOT USE THIS LINE",null,"OTHER",null,null,"Completed",null,"?",null,"T2","I","54999461098","49221009","064631981 + 064631831","444212007","800","Main St (Housatonic St= el act, Main St(Rt 8)= gen)??",null,null,"Dalton","MA","01226","WMECO","19A","19A6 via cust owned 29M11 (was 18C1) ","PTF"," ","Gas Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,420,420,420,"Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1999-05-01",null,null,"historic",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1999,null,null,null,null,null,"n/a - not expected to export","Application under review.  Waiting for updated drawing from customer.   steam, customer has not been able to export (gen trips off) but we don't know if they have reverse power relays",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??"]
["Esleeck Mfg Co Inc - bought by Southworth Paper",null,"OTHER",null,null,"Removed",null,"-",null,"PR-T2",null,"54495561037","??","??","637112001","36","Canal Rd",null,null,"Turners Falls","MA","01376","WMECO","21C","21C6","PTF"," ","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"N/A",null,null,380,380,"Hydro","n/a","n.r.","n.r.","n/a","n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"???",null,null,"n/a","n/a",null,null,null,"unknown",null,null,"historic",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown - OOS","needed","needed",null,null,"??","no export","historic generator  O.O.S. 2005",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"??",null,"removed"]
["Recorder Publishing Co",null,"OTHER",null,null,"Completed",null,"?",null,"S1","C","54440481034","512431005","047589081","141922009","14","Hope St",null,null,"Greenfield","MA",null,"WMECO","22B","22B2","PTF"," ","unknown","Unknown","n/a",null,null,"n/a",0,null,null,"Unknown",null,null,null,"???","unknown","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"?",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"??"]
["Mead Westvaco - Willow St South Lee",null,"OTHER",null,null,"Removed",null,"-",null,"T2",null,"54026691071","698041002","035773381","404242005","1085","Pleasant St",null,null,"Lee","MA","01260","WMECO","16B","16B3","PTF"," ","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"N/A",null,null,100,100,"Hydro","n/a","n.r.","n.r.","n/a","n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown - OOS",null,null,null,null,null,"n/a - not expected to export","(O.O.S. 2005) removed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","Yes","removed"]
["Linden Towers",null,"OTHER",null,null,"Removed",null,"-",null,null,null,"54973691066","644141007","890449352","067042004","310","Stafford St",null,null,"Springfield","MA","01104","WMECO","21S","21S3","PTF"," ","unknown","cogeneration unit","n/a",null,null,"n/a",0,null,null,"N/A",null,null,65,65,"Natural Gas","n/a","n.r.","n.r.","n/a","n.r.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,"1993-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"1993 - removed",null,null,null,null,null,"n/a - not expected to export","(replaced spring 2007)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","removed"]
["Chicopee Falls Hydro Electric Ltd  - Swift River Hydro",null,"OTHER",null,null,"Completed",null,"-",null,"G0",null,"54726002009","427341001+ 984341000","890302322 + 937852370","731742008",null,"North Main St",null,null,"Chicopee Falls","MA",null,"WMECO","18L","18L11","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,2500,2500,"1250 + 1250","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"?",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ISO - ?",null,null,"??","N"]
["Ashley Reservoir - City of Pittsfield",null,"OTHER",null,null,"Completed",null,"-",null,"G2","C","54926002031","052341002","891606632","649842001",null,"Washington Mt Rd",null,null,"Washington","MA","01223","WMECO","19A","19A1","PTF"," ","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"Power Purchase Schedule - Craig Holmes","Craig pays Ashley for hydro",225,225,225,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1987-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1987,null,null,null,null,null,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??"]
["Littleville Power Co (near Texon) may be owned by Consolidated Hydro Inc. - Crescent Dam - (new ISO-2009)",null,"OTHER",null,null,"Cancelled",null,"-",null,"G0",null,"54770502045","603741006","846039912","193252002",null,"Route 20",null,null,"Russell","MA","01071","WMECO","19J","19J1","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,null,1000,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","canc","Cancelled - Yes",null,null,"cancld","cancld",null,"N/A - written",null,"01/26/1994 ???",null,null,null,"no",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled","see ISO-2009","see ISO-2009",null,null,"no","n/a - generator selling energy","Cancelled 1994 -- Customer submitted a new application to increase output from 1MW to 1.667 MW.",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ISO - approved",null,"FERC","new SGIA - Y",null,"cancelled - new application submitted"]
["Glendale Hydro - NGRID customer - Littleville Power Company","CHI Power Marketing","OTHER",null,null,"Completed",null,"ISO-2014",null,null,null,"NGRID","NGRID","NGRID",null,null,"Glendale Rd",null,null,"Stockbridge","MA",null,"NGRID","16B","16B - via NGRID's 1102W1","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"N/A",null,1392,1392,"200 + 298 + 298 + 298 + 298","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a = NGRID",null,null,"n/a = NGRID","n/a",null,"?",null,"unknown",null,null,null,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - NGRID - exports - selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"NGRID","FERC","N.R."]
["Chestnut Knoll at Glen Meadow",null,"OTHER",null,null,"Completed",null,"-",null,"G2","C","54132602004","232741005","041502851","619452006","24","Tabor Crossing",null,null,"Longmeadow","MA","01106","WMECO","22H","22H17","PTF"," ","Gas Turbine","cogeneration unit","n/a",null,null,"n/a",0,null,null,"Unknown",null,75,75,75,"Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"2000-03-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2000,null,null,null,null,null,"n/a - not expected to export",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??","N"]
["Town of Lee Board of Public Works (Lee Water Treatment) - (new IA)",null,"OTHER",null,null,"Cancelled",null,"-",null,"G0",null,"54545502056","332741007","889148422","758452003","310","Reservoir Rd",null,null,"Lee","MA","01238","WMECO","17G","17G3","PTF"," ","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"N/A",null,null,null,85,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","canc","n/a",null,null,"n/a","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - not expected to export","(cancelled - Original 1998) gen used by customer,  cancelled 2011 - new ap - original 05/1998",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"cancelled - new application submitted"]
["Red Bridge (owned by Con Ed)",null,"OTHER",null,null,"Completed",null,"-",null,"G0",null,"54549602084","898741005","036089281","260652006",null,"East St",null,null,"Ludlow","MA",null,null,"25J","25J1 (WMECO's 27A15)","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,3600,3600,"3600 ?","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Putts Bridge (owned by Con Ed)",null,"OTHER",null,null,"Completed",null,"-",null,"G0",null,"54103602025","634841006","036089031","110552000",null,"Center St",null,null,"Ludlow","MA",null,null,"24Y","24Y1 (WMECO's 27A15)","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,3200,3200,"3200 ?","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Indian Orchard (owned by Con Ed)",null,"OTHER",null,null,"Completed",null,"-",null,"G2",null,"54242602050","049741001","040411941","108552003",null,"Front St",null,null,"Indian Orchard","MA",null,"WMECO","27A","27A10","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,3700,3700,"3700 ?","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Dwight Hydro (owned by Con Ed)",null,"OTHER",null,null,"Completed",null,"-",null,"G0","C","54692702004","060841005","040411911","171652008",null,"Front St",null,null,"Chicopee","MA",null,"WMECO","21N","21N8 (21N7A ?)","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,1200,1200,"1200 ?","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Robert Cole ???",null,"OTHER",null,null,"Completed",null,"?",null,null,"NA",null,null,null,null,null,"Shelburne Falls Rd",null,null,"Conway","MA","01341","WMECO","38A","38A1"," ","non-PTF","Hydro","hydro generator","n/a",null,null,"n/a",0,null,null,"Unknown",null,6,6,6,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1983-01-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1983,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??"]
["Black Swan Inn",null,"OTHER",null,null,"Completed",null,"?",null,null,"C",null,null,null,null,null,"Laurel St",null,null,"Lee","MA","01238","WMECO","16B","16B5","PTF"," ","Gas Turbine","cogeneration unit","n/a",null,null,"n/a",0,null,null,"Unknown",null,10.5,10.5,10.5,"Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1987-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1987,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??"]
["Cobble Mountain (owned by City of Springfield), operated by HG&E",null,"OTHER",null,null,"Completed",null,"-",null,"T2","NA","54549761088","142421009","891776132","483412006",null,"Cobble Mountain Rd",null,null,"Westfield","MA",null,"Springfield","Cit","City of Spfld's 69 KV line that ties in to Pochassic S/S ",{"$error":"#N/A"},{"$error":"#N/A"},"Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,33,33,"13+7+13","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,null,"??"]
["Crown Plaza Hotel (also known as Berkshire Common Corp ?)",null,"OTHER",null,null,"Completed",null,"-",null,null,"C","54993381052 ?","921431003 ?","001069790 ?","483922003 ?","38 ?","North St ",null,null,"Pittsfield","MA","01201","WMECO","30B","30B2 & 30B4","PTF"," ","Gas Turbine","cogeneration facility","n/a",null,null,"n/a",0,null,null,"Unknown",null,120,120,"60 + 60","Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1985-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1985,null,null,null,null,null,"n/a - not expected to export","induction machines",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??","N"]
["ECO - Springfield (Bondi's Island, Springfield Resource Recovery) - Springfield Refuse - (new IA)",null,"OTHER",null,null,"Cancelled",null,"-",null,null,null,null,null,null,null,"188","M St",null,null,"Agawam","MA","01001","WMECO","08C","08C22"," ","non-PTF","Trash","cogeneration facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,null,7500,"Trash","n/a","n.r.","n.r.","n/a","n.r.","canc",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","canc","n/a",null,null,"n/a","n/a",null,"N/A",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - generator selling energy","(cancelled - Original unknown) cancelled 2010 - new ap - original unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"cancelled - approved",null,null,"new SGIA - Y",null,"cancelled - new application submitted"]
["Gardner Falls Hydro (owned by Con Ed), was WMECO",null,"OTHER",null,null,"Completed",null,"-",null,null,null,null,null,null,null,null,"Gardner Falls Rd",null,null,"Shelburne Falls","MA",null,"WMECO","22B","22B5 & 22B6","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,3580,3580,"3580 ?","Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Hampshire College (2 - 60KW units)",null,"OTHER",null,null,"Completed",null,"-",null,null,"C",null,null,null,null,null,"West Bay Rd",null,null,"Amherst","MA","01002","WMECO","19B","19B15 & 19B16","PTF"," ","Gas Turbine","cogeneration facility","n/a",null,null,"no export",0,null,null,"No Export",null,120,120,"60 + 60","Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1984-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1984,null,null,null,null,null,"n/a - not expected to export",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??","N"]
["Jeff Frechette",null,"OTHER",null,null,"Removed",null,"-",null,null,null,null,null,null,null,null,"Lake Damon Rd",null,null,"Chesterfield","MA","01012","WMECO","18K","18K2"," ","non-PTF","Wind Turbine","wind turbine","n/a",null,null,"n/a",0,null,null,"N/A",null,null,10,10,"Wind","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,"1990-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"1990 - removed",null,null,null,null,null,"net metering","(removed by customer)  2/25/08 Bill Robertson called, wants to buy Jeff's turbine which was removed, wanted DG application info",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.","N","removed"]
["Pittsfield YMCA",null,"OTHER",null,null,"Completed",null,"?",null,null,"C",null,null,null,null,"292","North St",null,null,"Pittsfield","MA","01201","WMECO","31L","31L1","PTF"," ","Gas Turbine","cogeneration unit","n/a",null,null,"n/a",0,null,null,"Unknown",null,60,60,60,"Natural Gas","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,"1993-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1993,null,null,null,null,null,"net metering",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Y",null,"??","N"]
["Turners Falls No. 1 Station owned by First Light Hydro Generating Company, was NGS, was WMECO",null,"OTHER",null,null,"Completed",null,"-",null,null,null,null,null,null,null,"16","Canal Rd",null,null,"Montague","MA",null,"WMECO","21C","21C6","PTF"," ","Hydro","hydro generating facility","n/a",null,null,"n/a",0,null,null,"Market Participant",null,6300,6300,6300,"Hydro","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"1904 ???",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy","agreement dated 7/24/06",null,null,null,null,null,"Alan Dunlea","20 Church St, 16th Floor","Hartford","CT","06103",8608956914,8608956978,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["UMASS - Steam Plant",null,"OTHER",null,null,"Removed",null,"-",null,"T2",null,null,null,null,null,"360","Campus Center Way - Umass Campus",null,null,"Amherst","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","unknown","cogeneration facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,1500,1500,"Coal","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,"N/A",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown - removed",null,null,null,null,null,"no export","(removed by customer winter 2005/2006)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,null,"N.R.",null,"removed"]
["UMASS - Steam Plant",null,"OTHER",null,null,"Removed",null,"-",null,"T2",null,null,null,null,null,"360","Campus Center Way - Umass Campus",null,null,"Amherst","MA","01002","WMECO","18G","18G1 & 18G2"," ","non-PTF","unknown","cogeneration facility","n/a",null,null,"n/a",0,null,null,"N/A",null,null,500,500,"Coal","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n/a",null,null,"n/a","n/a",null,null,null,"unknown approx 1950",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown - removed",null,null,null,null,null,"no export","(removed by customer winter 2008/2009)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"N.R.",null,"removed"]
["?? unknown wind on circuit print",null,"OTHER",null,null,"Unknown",null,"?",null,null,null,null,null,null,null,null,"Putney Rd",null,null,"Leverett","MA",null,"WMECO","18G","18G6"," ","non-PTF","Wind Turbine","wind turbine","n/a",null,null,"n/a",null,null,null,"Unknown",null,null,null,"???","Wind","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,null,null,null,{"$f":"IF(BV6155=0,NETWORKDAYS(BU6155,$A$4),NETWORKDAYS(BU6155,BV6155))","v":30288},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"?",null,null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"??",null,"*****"]
["Doreen Jet  19A-10U - owned by NAEA",null,"OTHER",null,null,"Completed",null,"-",null,null,null,null,null,null,null,null,null,null,null,"Pittsfield","MA",null,"WMECO","19A","19A S/S - 19A9 ","PTF"," ","unknown","jet","n/a",null,null,"n/a",0,null,null,"Market Participant",null,18000,18000,18000,"unknown","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Woodland Road  17G-10U - owned by NAEA",null,"OTHER",null,null,"Completed",null,"-",null,null,null,null,null,null,null,null,null,null,null,"Lee","MA",null,"WMECO","17G","17G S/S","PTF"," ","unknown","jet","n/a",null,null,"n/a",0,null,null,"Market Participant",null,22000,22000,22000,"unknown","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["West Springfield 10U - \"8C-10U  = Not NU\"",null,"OTHER",null,null,"Completed",null,"-",null,null,null,null,null,null,null,null,"Agawam Ave",null,null,"West Springfield","MA","01089","WMECO","08C","13.8KV at West Springfield 8C bus"," ","non-PTF","unknown","jet","n/a",null,null,"n/a",0,null,null,"Market Participant",null,22000,22000,22000,"unknown","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["Con Edison Energy Unit 1 - West Springfield GT1  - \"8C-1U  = Not NU\"",null,"OTHER",null,null,"Completed",null,"-",null,null,null,"n/a","n/a",null,null,null,"Agawam Ave",null,null,"West Springfield","MA","01089","WMECO","08C","13.8KV at West Springfield 8C bus"," ","non-PTF","unknown","generator","n/a",null,null,"n/a",0,null,null,"Market Participant",null,60500,60500,60500,"unknown","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","???",null,null,"??","??",null,"Yes",null,"unknown",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"unknown",null,null,null,null,null,"n/a - generator selling energy",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"?",null,"FERC","??"]
["WMECO - Silver Lake Blvd, Pittsfield PV",null,"OTHER",null,"Bill Blanchard","Completed",null,"WMECO Solar 1",null,"G0","C","54430555086","760713004","000002758","952436008","75","Silver Lake Blvd",null,null,"Pittsfield","MA","01201","WMECO",{"$f":"LEFT(Y6160,3)","v":"30B"},"30B4 N.C. / 30B1 N.O.","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"Market Participant",null,1473,1473,1473,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a = WMECO",null,null,"n/a = WMECO","n/a",null,"Yes",null,"2010-11-03",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"3 - 500 kW inverters, aggregate approved AC size approved at 1.5 MW",2010,null,null,null,null,null,"n/a - generator selling energy","WMECO Solar = application and all work handled by Bill Blanchard",null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved",null,"FERC","??"]
["WMECO - Cottage Street, Springfield PV",null,"OTHER",null,"Bill Blanchard","Completed",null,"WMECO Solar 2",null,"G0","C","54403186000",null,null,null,"285","Cottage St",null,null,"Springfield","MA","01104","WMECO",{"$f":"LEFT(Y6161,3)","v":"05J"},"05J13A","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"Market Participant",null,3193,3193,3193,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a = WMECO",null,null,"n/a = WMECO","n/a",null,"Yes",null,"2014-04-24",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"6 - 500 kW and 1 - 250 kW inverters, aggregate approved AC size rated at 3.2 MW",2014,null,null,null,null,null,"n/a - generator selling energy","WMECO Solar = application and all work handled by Bill Blanchard",null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved",null,"FERC","??"]
["WMECO - Goodwin Street, Indian Orchard PV",null,"OTHER",null,"Bill Blanchard","Completed",null,"WMECO Solar 3",null,"G0","C","54991295031",null,null,null,"225","Goodwin St",null,null,"Springfield","MA","01151","WMECO",{"$f":"LEFT(Y6162,3)","v":"27A"},"27A13","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",0,null,null,"Market Participant",null,1891,1891,1891,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a = WMECO",null,null,"n/a = WMECO","n/a",null,"Yes",null,"2011-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"4 - 500 kW inverters, aggregate approved AC size rated at 1.9 MW",2011,null,null,null,null,null,"n/a - generator selling energy","WMECO Solar = application and all work handled by Bill Blanchard",null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"approved",null,"FERC","??"]
["WMECO - Delta Hills, Springfield PV",null,"OTHER",null,"Bill Blanchard","Cancelled","2014-05-19","WMECO Solar 4",null,null,null,null,null,null,null,null,"off Robin Cir",null,null,"Springfield","MA",null,"WMECO",{"$f":"LEFT(Y6163,3)","v":"05J"},"05J11","PTF"," ","Photovoltaic","Inverter","n/a",null,null,"n/a",null,null,null,"Market Participant",null,1500,null,1500,"Solar","n/a","n.r.","n.r.","n/a","n.r.","n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"n.r.","n/a","n/a = WMECO",null,null,"n/a = WMECO","n/a",null,"Yes",null,null,{"$f":"IF(BV6163=0,NETWORKDAYS(BU6163,$A$4),NETWORKDAYS(BU6163,BV6163))","v":30288},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cancelled",null,null,null,null,null,"n/a - generator selling energy","WMECO Solar = application and all work handled by Bill Blanchard",null,null,null,null,null,null,null,null,null,null,null,null,"N",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FERC","??",null,"cancelled"]

{"sheet":"WMDG List","index":1,"n_rows":1679,"n_cols":58,"rows_kept":1679,"cut":false,"hidden":false,"merged":[]}
[null,"Company Name","City/Town","Facility ID (if any)","ZIP Code","Design Capacity (kW)","Fuel Type (Solar, Wind, etc)","Circuit Name","Date Application Received","Date Application  Deemed Complete","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Review of Screens Study Begun","Date Review of Screens Study Completed","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer  ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Supplemental Review Begun","Date Supplemental Review Complete ","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer   ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Standard Process Initial Review Begun ","Date Standard Process Initial Review  Complete ","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer    ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Impact Study Begun","Date Impact Study Sent","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer     ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Detailed Study Begun","Date Detailed Study Sent","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer      ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Interconnection Agreement Sent","Date ISA & Payment Received","Estimated In-Service Date","System Modification Required","Expedited/ Standard / Complex Project","Construction Timeline Commitment (Workdays)","Date Construction Begun","Date Construction Completed","Total Time Lapsed (Workdays) calculated value","Customer Time Lapsed (Workdays) enter workdays of \"clock\" stoppage by Customer       ","Utility Time Lapsed (Workdays) enter workdays  without \"clock\" stoppage","Date Witness Test Scheduled","Date Witness Test Completed","Authorization to Interconnect","NOTES","Impact_Group_Study_Name","Group_Name","ASO_Group_Name","Limiting Export Max Size kW","Substation_Name"]
[null,"WMECO","Springfield","6S21-2009","01105",75,"Solar","8C14","2009-03-30","2009-04-13",{"$f":"NETWORKDAYS(I2,J2,MALegalHolidays)","v":11},null,{"$f":"IF(K2>0,K2-L2,\" \")","v":11},null,null,null,null,{"$f":"IF(P2>0,P2-Q2,\" \")","v":" "},null,null,null,null,{"$f":"IF(U2>0,U2-V2,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z2>0,Z2-AA2,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE2>0,AE2-AF2,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ2>0,AJ2-AK2,\" \")","v":" "},"2009-04-24",null,"07/2009","No","EXP",null,null,null,null,null,{"$f":"IF(AU2>0,AU2-AV2,\" \")","v":" "},null,null,"2009-07-23","on line"]
[null,"WMECO","Savoy","6B44-2009","01256",10000,"Wind","18C1","2009-06-26",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2010-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Was on hold by Cust. Cancelled. Cust can't confirm design. Need design for Impact Study. Stand alone generation. New construction. Application has two options 8,000 kW or 10,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Amherst","6A82-2009","01002",39,"Solar","17K2","2009-06-29","2009-07-24",{"$f":"NETWORKDAYS(I4,J4,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2009-07-30",null,"08/2009","No","EXP",null,null,null,null,null," ",null,null,"2009-08-10","On line. New construction."]
[null,"WMECO","Leverett","6A91-2009","01054",13.8,"Solar","18G7","2009-07-28","2009-09-14",{"$f":"NETWORKDAYS(I5,J5,MALegalHolidays)","v":35},null,35,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2009-09-17",null,"08/2009 or 09/2009","Yes","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust changed design, reapplied."]
[null,"WMECO","Pittsfield","6B46-2009","01201",86,"Solar","15E3","2009-07-29","2009-09-29",{"$f":"NETWORKDAYS(I6,J6,MALegalHolidays)","v":45},null,45,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2009-09-30",null,"11/2009","No","EXP",null,null,null,null,null," ",null,null,"2010-01-14","on line"]
[null,"WMECO","Pittsfield","6B47-2009","01201",95,"Solar","19A5","2009-07-29","2009-09-15",{"$f":"NETWORKDAYS(I7,J7,MALegalHolidays)","v":35},null,35,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2009-09-16",null,"11/2009","No","EXP",null,null,null,null,null," ",null,null,"2009-11-10","on line"]
[null,"WMECO","Lee","6B55-2009","01238",125,"Solar","16B5","2009-11-05",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2009-11-15","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application not complete and incorrect, reapplied."]
[null,"WMECO","Springfield","6S34-2009","01104",50,"Solar","5J13","2009-11-13",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2009-11-15","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application not complete. Cust changed size, reapplied."]
[null,"WMECO","Pittsfield","6B59-2009","01201",126.9,"Solar","19A2","2009-12-01",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2009-12-31","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application not complete, reapplied. "]
[null,"WMECO","Springfield","6S35-2009","01105",30,"Solar","8C26","2009-12-01","2009-12-30",{"$f":"NETWORKDAYS(I11,J11,MALegalHolidays)","v":22},null,22,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-01-11",null,"2009-12-30","No","EXP",null,null,null,null,null," ",null,null,"2010-02-12","On line. Third party owned."]
[null,"WMECO","Lee","6B60-2009","01238",125,"Solar","16B5","2009-12-09","2009-12-16",{"$f":"NETWORKDAYS(I12,J12,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2009-12-24",null,"2009-12-31","No","EXP",null,null,null,null,null," ",null,null,"2009-12-30","on line"]
[null,"WMECO","Springfield","6S36-2009","01111",87,"Solar","5J14","2009-12-24","2010-01-29",{"$f":"NETWORKDAYS(I13,J13,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-02-08",null,"2010-03-26","No","EXP",null,null,null,null,null," ",null,null,"2010-08-11","On line. Will not export."]
[null,"WMECO","Hancock","6B62-2009","01237",81.2,"Solar","30B7","2009-12-28",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2009-12-31","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application not correct, reapplied. "]
[null,"WMECO","Springfield","6S37-2009","01104",95,"Solar","5J14","2009-12-28",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Wrong application, not complete, reapplied."]
[null,"WMECO","Hadley","6A104-2009","01002",2000,"Natural Gas / Fuel Oil","18G1 & 18G2","2009-12-30","2010-02-17",{"$f":"NETWORKDAYS(I16,J16,MALegalHolidays)","v":36},null,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-07-19",null,{"$f":"NETWORKDAYS(AC16,AD16,MALegalHolidays)","v":-28841},null," ",null,null,null,null," ","2011-02-22",null,"09/2010","Yes","STD",null,null,null,null,null," ",null,null,"2011-03-01","On line.  Removed."]
[null,"WMECO","Springfield","6S38-2010","01104",38.07,"Solar","5J13","2010-01-05","2010-01-29",{"$f":"NETWORKDAYS(I17,J17,MALegalHolidays)","v":19},null,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-02-02",null,"2010-01-15","No","EXP",null,null,null,null,null," ",null,null,"2010-02-19","on line"]
[null,"WMECO","Hancock","6B63-2010","01237",81.2,"Solar","30B7","2010-01-12","2010-02-08",{"$f":"NETWORKDAYS(I18,J18,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-02-19",null,"2009-12-31","No","EXP",null,null,null,null,null," ",null,null,"2010-03-09","On line. Third party owned."]
[null,"WMECO","Pittsfield","6B64-2010","01201",126.91,"Solar","19A2","2010-01-12","2010-01-28",{"$f":"NETWORKDAYS(I19,J19,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-02-09",null,"2009-12-31","No","EXP",null,null,null,null,null," ",null,null,"2010-02-25","On line. Third party owned."]
[null,"WMECO","Springfield","6S39-2010","01104",95,"Solar","5J14","2010-02-03","2010-03-05",{"$f":"NETWORKDAYS(I20,J20,MALegalHolidays)","v":23},null,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-04-05",null,"2010-03-15","No","EXP",null,null,null,null,null," ",null,null,"2010-10-13","On line. Third party owned."]
[null,"WMECO","Leverett","6A107-2010","01054",{"$f":"9.995+3.8","v":13.794999999999998},"Solar","18G7","2010-02-05","2010-02-11",{"$f":"NETWORKDAYS(I21,J21,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-02-12",null,"2010-02-01","Yes","EXP",null,null,null,null,null," ",null,null,"2010-02-18","On line. New construction."]
[null,"WMECO","Amherst","6A110-2010","01002",14.7,"Solar","17K3","2010-04-01","2010-04-12",{"$f":"NETWORKDAYS(I22,J22,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-05-18",null,"5/2010","Yes","EXP",null,null,null,null,null," ",null,null,"2010-06-23","On line. New construction."]
[null,"WMECO","Shelburne","6F155-2010","01370",24.2,"Solar","22B5","2010-04-06","2010-04-22",{"$f":"NETWORKDAYS(I23,J23,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-04-27",null,"5/2010","Yes","EXP",null,null,null,null,null," ",null,null,"2010-05-21","on line"]
[null,"WMECO","Whately","6AF157-2010","01093",20,"Solar","18G8","2010-04-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"7/2010","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust changed design, reapplied. "]
[null,"WMECO","Northfield","6F158-2010","01360",65.400000000000006,"Solar","21B8","2010-04-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust will not make changes to existing system."]
[null,"WMECO","Whately","6AF160-2010","01093",15.6,"Solar","18G8","2010-06-01","2010-06-18",{"$f":"NETWORKDAYS(I26,J26,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-06-28",null,"7/2010","Yes","EXP",null,null,null,null,null," ",null,null,"2010-07-09","on line"]
[null,"WMECO","Pittsfield","6B71-2010","01201",36,"Solar","30B4","2010-06-01","2010-08-23",{"$f":"NETWORKDAYS(I27,J27,MALegalHolidays)","v":60},null,60,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-10-04",null,"2010-09-13","No","EXP",null,null,null,null,null," ",null,null,"2010-12-22","On line. New construction service."]
[null,"WMECO","Greenfield","6F161-2010","01301",2000,"Solar","22B3","2010-06-03","2011-01-05",{"$f":"NETWORKDAYS(I28,J28,MALegalHolidays)","v":155},null,155,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-07-20","2011-01-28",{"$f":"NETWORKDAYS(AC28,AD28,MALegalHolidays)","v":139},null,139,null,null,null,null," ","2011-01-28",null,"2011-03-04","Yes","STD",null,null,null,null,null," ",null,null,"2012-06-20","On line. Draft Impact Study sent to cust 10/8/11. They changed inverters & design so study was redone. Third party owned. Stand alone generation. New constr."]
[null,"WMECO","Pittsfield","6B72-2010","01201",1800,"Solar","30B3","2010-06-11",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"11/2010","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application not correct, reapplied. "]
[null,"WMECO","Pittsfield","6B74-2010","01201",1800,"Solar","30B3 N.C. / 30B2 N.O. *","2010-06-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"11/2010","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust changed design, reapplied. "]
[null,"WMECO","Pittsfield","6B75-2010","01201",62,"Hydro","19A7","2010-07-01","2011-02-14",{"$f":"NETWORKDAYS(I31,J31,MALegalHolidays)","v":163},null,163,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-09-30",null,{"$f":"NETWORKDAYS(AC31,AD31,MALegalHolidays)","v":-28894},null," ",null,null,null,null," ","2011-04-07",null,"2010-11-15","No","STD",null,null,null,null,null," ",null,null,"2011-06-16","On line. New construction service."]
[null,"WMECO","Pittsfield","6B77-2010","01201",1500,"Solar","30B3 ","2010-07-30","2011-02-02",{"$f":"NETWORKDAYS(I32,J32,MALegalHolidays)","v":134},null,134,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-08-20",null,{"$f":"NETWORKDAYS(AC32,AD32,MALegalHolidays)","v":-28865},null," ",null,null,null,null," ","2011-03-24",null,"2010-12-10","Yes","STD",null,null,null,null,null," ",null,"2012-02-01","2012-02-01","On line. Stand alone generation. New construction."]
[null,"WMECO","Greenfield","6F171-2010","01301",50,"Solar","22B7","2010-08-03","2011-01-11",{"$f":"NETWORKDAYS(I33,J33,MALegalHolidays)","v":116},null,116,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-01-12",null,"2010-10-20","No","EXP",null,null,null,null,null," ",null,null,"2011-02-10","On line. Customer upgraded service."]
[null,"WMECO","Springfield","6S46-2010","01118",26.4,"Solar","22H16","2010-08-03","2010-09-18",{"$f":"NETWORKDAYS(I34,J34,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-10-20",null,"2010-09-01","No","EXP",null,null,null,null,null," ",null,null,"2010-11-03","On line. New construction."]
[null,"WMECO","Hadley","6A134-2010","01035",30.3,"Solar","17K5","2010-08-20","2010-09-03",{"$f":"NETWORKDAYS(I35,J35,MALegalHolidays)","v":11},null,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-09-21",null,"2010-09-20","Yes","EXP",null,null,null,null,null," ",null,null,"2010-11-10","on line"]
[null,"WMECO","Amherst","6A136-2010","01002",39.6,"Solar","19B15","2010-08-30","2010-09-10",{"$f":"NETWORKDAYS(I36,J36,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-10-01",null,"2010-09-01","No","EXP",null,null,null,null,null," ",null,null,"2010-10-15","on line"]
[null,"WMECO","Deerfield","6F175-2010","01343",50,"Solar","22B3","2010-08-30","2010-09-10",{"$f":"NETWORKDAYS(I37,J37,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-10-26",null,"2010-09-01","No","EXP",null,null,null,null,null," ",null,null,"2010-12-17","on line"]
[null,"WMECO","Lee","6B78S-2010","01238",30,"Solar","17G3","2010-09-17","2011-03-01",{"$f":"NETWORKDAYS(I38,J38,MALegalHolidays)","v":118},null,118,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-06-01",null,"2010-10-01","Yes","EXP",null,null,null,null,null," ",null,null,"2011-12-01","On line. Cust has historic hydro."]
[null,"WMECO","Hadley","6A138-2010","01035",25.5,"Solar","18G5","2010-09-21","2010-10-22",{"$f":"NETWORKDAYS(I39,J39,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2010-11-30",null,"2010-11-01","Yes","EXP",null,null,null,null,null," ",null,null,"2011-02-23","On line. New construction."]
[null,"WMECO","Ashfield","6F192-2010","01330",41.384999999999998,"Solar","38A1","2010-12-03","2011-01-28",{"$f":"NETWORKDAYS(I40,J40,MALegalHolidays)","v":41},null,41,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-01-28",null,"2010-01-01","Yes","EXP",null,null,null,null,null," ",null,null,"2011-04-19","On line. Cust installed new service. Verizon pole set area."]
[null,"WMECO","West Springfield","6S52-2010","01089",50,"Solar","16C14","2010-12-07","2011-01-25",{"$f":"NETWORKDAYS(I41,J41,MALegalHolidays)","v":36},null,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-03-02",null,"2011-02-01","No","EXP",null,null,null,null,null," ",null,null,"2011-03-29","On line. Third party owned."]
[null,"WMECO","Pittsfield","6B82-2010","01201",195,"Digester Gas","30B3","2010-12-09","2011-08-18",{"$f":"NETWORKDAYS(I42,J42,MALegalHolidays)","v":181},null,181,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-09-27",null,"2011-01-01","No","STD",null,null,null,null,null," ",null,null,"2012-02-10","On line. Will not export."]
[null,"WMECO","Pittsfield","6B86-2010","01201",387.2,"Solar","30B7","2010-12-15","2011-06-17",{"$f":"NETWORKDAYS(I43,J43,MALegalHolidays)","v":133},null,133,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-06-17",null,"2011-01-01","No","EXP",null,null,null,null,null," ",null,null,"2011-07-27","on line"]
[null,"WMECO","Hadley","6A149-2011","01035",450,"Biogas","19B15","2011-01-04",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust name and design changed. Reapplied."]
[null,"WMECO","Greenfield","6F194-2011","01301",83,"Solar","22B7","2011-01-04","2011-07-08",{"$f":"NETWORKDAYS(I45,J45,MALegalHolidays)","v":134},null,134,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-12-13",null,"2011-03-01","No","EXP",null,null,null,null,null," ",null,null,"2012-02-06","On line. Cust installed phone line to meter."]
[null,"WMECO","Deerfield","6F195-2011","01342",450,"Biogas","22B1","2011-01-04",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-06-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust name and design change, reapplied."]
[null,"WMECO","Easthampton","6A151-2011","01027",2000,"Solar","15A3","2011-01-27","2011-03-16",{"$f":"NETWORKDAYS(I47,J47,MALegalHolidays)","v":35},null,35,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-03-21","2011-06-29",{"$f":"NETWORKDAYS(AC47,AD47,MALegalHolidays)","v":73},null,73,"2011-07-06",null,{"$f":"NETWORKDAYS(AH47,AI47,MALegalHolidays)","v":-29093},null," ","2011-10-21",null,"2011-11-19","Yes","STD",null,null,null,null,null," ",null,null,"2012-06-01","On line. Int Cust worked with Verizon to get phone lines. Third party owned. Stand alone generation. New construction."]
[null,"WMECO","Hadley","6A156-2011","01035",450,"Biogas","19B15","2011-02-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust submitted new application for larger unit."]
[null,"WMECO","Pittsfield","6B92-2011","01201",2000,"Solar","19A3","2011-02-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-05-26",null,{"$f":"NETWORKDAYS(AC49,AD49,MALegalHolidays)","v":-29064},null," ",null,null,null,null," ",null,null,"2011-12-15","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Third party owned. Stand alone generation. New construction. "]
[null,"WMECO","Deerfield","6F201-2011","01373",450,"Biogas","22B1","2011-02-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust submitted new application for larger unit."]
[null,"WMECO","Sandisfield","6B93-2011","01255",14,"Solar","19J4","2011-03-03","2011-03-28",{"$f":"NETWORKDAYS(I51,J51,MALegalHolidays)","v":18},null,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-04-27",null,"2011-06-01","No","EXP",null,null,null,null,null," ",null,null,"2011-12-05","on line"]
[null,"WMECO","Greenfield","6F203-2011","01301",100,"Solar","22B4","2011-03-04","2011-12-07",{"$f":"NETWORKDAYS(I52,J52,MALegalHolidays)","v":199},null,199,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-03-26",null,"2011-07-01","No","EXP",null,null,null,null,null," ",null,null,"2012-05-07","On line. New construction service."]
[null,"WMECO","Springfield","6S56-2011","01107",120.4,"Solar","21S7","2011-03-17","2012-01-06",{"$f":"NETWORKDAYS(I53,J53,MALegalHolidays)","v":211},null,211,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-01-30",null,"2011-05-01","No","STD",null,null,null,null,null," ",null,null,"2012-03-12","on line"]
[null,"WMECO","Westfield","6A164-2011","01085",250,"Solar","19J2","2011-04-07",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-07-31","TBD","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Wrong application submitted. 3rd party info incorrect. Cust submited new application."]
[null,"WMECO","Northfield","6F215-2011","01360",2000,"Solar","21B8","2011-04-07","2011-08-18",{"$f":"NETWORKDAYS(I55,J55,MALegalHolidays)","v":96},null,96,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-07-13","2011-12-13",{"$f":"NETWORKDAYS(AC55,AD55,MALegalHolidays)","v":110},null,110,"2011-11-28",null,{"$f":"NETWORKDAYS(AH55,AI55,MALegalHolidays)","v":-29196},null," ","2012-02-07",null,"2011-08-01","Yes","STD",null,null,null,null,null," ",null,null,"2012-03-30","On line. Third party owned. Essentially stand alone generation."]
[null,"WMECO","Agawam","6S57-2011","01001",1500,"Solar","30A6","2011-04-19","2011-05-26",{"$f":"NETWORKDAYS(I56,J56,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-06-09","2011-10-21",{"$f":"NETWORKDAYS(AC56,AD56,MALegalHolidays)","v":97},null,97,"2011-11-14",null,{"$f":"NETWORKDAYS(AH56,AI56,MALegalHolidays)","v":-29186},null," ","2012-04-27",null,"2011-09-01","Yes","STD",null,null,null,null,null," ","2013-03-11","2013-03-13","2013-03-13","On line. Communication work with Verizon in progress. Third party owned. Stand alone generation. New construction."]
[null,"WMECO","Westfield","6A168-2011","01085",1000,"Solar","19J2","2011-05-17","2011-07-20",{"$f":"NETWORKDAYS(I57,J57,MALegalHolidays)","v":47},null,47,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-09-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Third party owned. Essentially stand alone generation. New construction. Application has two options 250 kW or 1,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Whately","6A170-2011","01373",1500,"Solar","18G8","2011-05-19","2011-07-21",{"$f":"NETWORKDAYS(I58,J58,MALegalHolidays)","v":46},null,{"$f":"IF(K58>0,K58-L58,\" \")","v":46},null,null,null,null,{"$f":"IF(P58>0,P58-Q58,\" \")","v":" "},null,null,null,null,{"$f":"IF(U58>0,U58-V58,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z58>0,Z58-AA58,\" \")","v":" "},"2011-07-08","2011-12-28",{"$f":"NETWORKDAYS(AC58,AD58,MALegalHolidays)","v":124},null,{"$f":"IF(AE58>0,AE58-AF58,\" \")","v":124},"2011-12-21",null,{"$f":"NETWORKDAYS(AH58,AI58,MALegalHolidays)","v":-29213},null,{"$f":"IF(AJ58>0,AJ58-AK58,\" \")","v":" "},"2012-04-03",null,"2011-09-01","Yes","STD",null,null,null,null,null,{"$f":"IF(AU58>0,AU58-AV58,\" \")","v":" "},"2013-01-29","2013-02-01","2013-03-11","On line. Third party owned. Stand alone generation. New construction."]
[null,"WMECO","Greenfield","6F230-2011","01301",34.200000000000003,"Solar","22B4","2011-06-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust submitted new application."]
[null,"WMECO","Dalton","6B105-2011","01226",224,"Steam","19A6","2011-06-20","2012-01-11",{"$f":"NETWORKDAYS(I60,J60,MALegalHolidays)","v":147},null,147,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-10-20",null,{"$f":"NETWORKDAYS(AC60,AD60,MALegalHolidays)","v":-29169},null," ",null,null,null,null," ","2012-01-11",null,"2011-11-11","No","STD",null,null,null,null,null," ",null,null,"2012-01-24","On line. Will not export."]
[null,"WMECO","Dalton","6B106-2011","01226",250,"Hydro","19A6","2011-06-20","2012-05-29",{"$f":"NETWORKDAYS(I61,J61,MALegalHolidays)","v":242},null,242,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-07-16","2012-12-19",{"$f":"NETWORKDAYS(AC61,AD61,MALegalHolidays)","v":108},null,108,null,null,null,null," ","2013-04-30",null,"2012-04-01","Yes","STD",null,null,null,null,null," ","2013-09-27","2013-10-03","2013-10-03","on line 10/3/13"]
[null,"WMECO","Greenfield","6F235-2011","01301",34.200000000000003,"Solar","22B4","2011-06-24","2011-07-15",{"$f":"NETWORKDAYS(I62,J62,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-07-20",null,"2011-07-21","No","EXP",null,null,null,null,null," ",null,null,"2011-08-05","on line"]
[null,"WMECO","Agawam","6S60-2011","01001",1500,"Solar","16C16","2011-07-07","2011-08-03",{"$f":"NETWORKDAYS(I63,J63,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-09-01","2011-12-29",{"$f":"NETWORKDAYS(AC63,AD63,MALegalHolidays)","v":86},null,86,"2011-12-21",null,{"$f":"NETWORKDAYS(AH63,AI63,MALegalHolidays)","v":-29213},null," ","2012-04-13",null,"2011-12-01","Yes","STD",null,null,null,null,null," ","2013-02-06","2013-02-22","2013-03-11","On line. Communication work with Verizon in progress. Third party owned. Stand alone generation. New construction. On line."]
[null,"WMECO","Chesterfield","6F243-2011","01012",12,"Solar","18K3","2011-07-25","2011-08-22",{"$f":"NETWORKDAYS(I64,J64,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-08-23",null,"2011-08-01","No","EXP",null,null,null,null,null," ",null,null,"2011-09-15","on line"]
[null,"WMECO","Amherst","6A183-2011","01002",60,"Solar","19B16","2011-07-28","2011-09-22",{"$f":"NETWORKDAYS(I65,J65,MALegalHolidays)","v":41},null,41,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-10-17",null,"2011-11-01","No","EXP",null,null,null,null,null," ",null,null,"2011-11-18","on line"]
[null,"WMECO","Conway","6F248-2011","01341",22.8,"Solar","38A1","2011-08-12","2011-10-26",{"$f":"NETWORKDAYS(I66,J66,MALegalHolidays)","v":54},null,54,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-11-17",null,"2011-09-10","Yes","EXP",null,null,null,null,null," ",null,null,"2012-02-27","on line"]
[null,"WMECO","Whately","6F251-2011","01373",100,"Solar","18G8","2011-08-18","2011-10-13",{"$f":"NETWORKDAYS(I67,J67,MALegalHolidays)","v":41},null,41,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-10-18",null,"not supplied","No","EXP",null,null,null,null,null," ",null,null,"2011-12-28","On line. New construction service."]
[null,"WMECO","Hadley","6A196-2011","01035",95,"Solar","18G4","2011-09-01","2011-10-25",{"$f":"NETWORKDAYS(I68,J68,MALegalHolidays)","v":39},null,39,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-11-30",null,"2011-11-01","Yes","EXP",null,null,null,null,null," ",null,null,"2012-03-30","On line. Stand alone generation. New construction."]
[null,"WMECO","Pittsfield","6B111-2011","01201",300,"Solar","30B4","2011-09-02","2011-10-05",{"$f":"NETWORKDAYS(I69,J69,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-02-07",null,"2011-10-01","No","EXP",null,null,null,null,null," ",null,null,"2012-06-01","On line. Cust changed their switchgear. Service upgrade."]
[null,"WMECO","Springfield","6S68-2011","01111",208,"Solar","5J14","2011-09-12","2011-11-17",{"$f":"NETWORKDAYS(I70,J70,MALegalHolidays)","v":49},null,49,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-11-30",null,"2011-10-15","No","EXP",null,null,null,null,null," ",null,null,"2012-01-24","On line. Will not export."]
[null,"WMECO","Deerfield","6F264-2011","01342",30,"Solar","22B7","2011-09-16","2011-10-19",{"$f":"NETWORKDAYS(I71,J71,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-11-07",null,"2011-10-31","No","EXP",null,null,null,null,null," ",null,null,"2012-02-03","on line"]
[null,"WMECO","Hadley","6A209-2011","01035",300,"Biogas","19B15","2011-09-21","2013-10-18",{"$f":"NETWORKDAYS(I72,J72,MALegalHolidays)","v":522},null,522,"2013-10-21",null,{"$f":"NETWORKDAYS(N72,O72,MALegalHolidays)","v":-29670},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-12-19",null,"2012-04-01","Yes","STD",null,null,null,null,null," ",null,null,"2013-12-31","on line"]
[null,"WMECO","Deerfield","6F265-2011","01372",600,"Biogas","22B1","2011-09-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-04-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Sent purge letter 5/20/13. Cust submitted new option 6/17/13. Gen-set nampeplate and application fee required. Stand alone generation. New construction. Design option 600 kW or 300 kW.  Highest design listed. Reviewed new option for completeness.  App not complete. Cust cancelled 9/10/13."]
[null,"WMECO","Lee","6B116-2011","01238",295,"Solar","16B5","2011-10-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q2 2012","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Submitted new application."]
[null,"WMECO","Colrain","6F274-2011","01340",15.36,"Solar","29R2","2011-10-24","2012-01-12",{"$f":"NETWORKDAYS(I75,J75,MALegalHolidays)","v":58},null,58,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-02-07",null,"2011-11-30","Yes","EXP",null,null,null,null,null," ",null,null,"2012-05-23","On line. Essentially stand alone generation."]
[null,"WMECO","Whately","6A225-2011","01093",260,"Solar","18G8","2011-11-07",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-03-16","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust changed design, submitted new application."]
[null,"WMECO","Hadley","6A228-2011","01035",17.995000000000001,"Solar","18G5","2011-11-09","2011-12-20",{"$f":"NETWORKDAYS(I77,J77,MALegalHolidays)","v":30},null,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2011-12-21",null,"2011-11-28","No","EXP",null,null,null,null,null," ",null,null,"2012-01-19","on line"]
[null,"WMECO","Pittsfield","6B117-2011","01201",100,"Solar","30B3","2011-11-09","2012-01-18",{"$f":"NETWORKDAYS(I78,J78,MALegalHolidays)","v":49},null,49,null,null,null,null," ","2011-12-12",null,{"$f":"NETWORKDAYS(S78,T78,MALegalHolidays)","v":-29206},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-03-02",null,"2011-12-15","Yes","EXP",null,null,null,null,null," ",null,null,"2012-05-03","On line. Generation significantly larger than load."]
[null,"WMECO","Springfield","6S74-2011","01104",60,"Solar","21S7","2011-11-15","2012-04-10",{"$f":"NETWORKDAYS(I79,J79,MALegalHolidays)","v":103},null,103,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-04-10",null,"2012-03-01","No","EXP",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. Waiting for Cust to return IA and completion documents to schedule Witness Test. Withdrawn"]
[null,"WMECO","Springfield","6S75-2011","01104",95,"Solar","21S7","2011-11-15","2012-04-09",{"$f":"NETWORKDAYS(I80,J80,MALegalHolidays)","v":102},null,102,"2011-12-20",null,{"$f":"NETWORKDAYS(N80,O80,MALegalHolidays)","v":-29212},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-04-19",null,"2012-03-01","No","EXP",null,null,null,null,null," ","2014-04-30","2014-05-05","2014-05-05","Waiting for Cust to return IA and completion documents to schedule Witness Test. Have heard nothing from cust as of 8/21/13. Waiting for Customer.  Received most of the completion docs from Interconnecting Customer, waiting for revised drawing with inverter settings  Received revised drawing, need inverter setting sheet, Int Customer will provide during Witness Test.  Witness Test performed, Witness Test passed, Int Customer is on line."]
[null,"WMECO","Dalton","6B120-2011","01226",13,"Solar","19A2","2011-11-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2011-12-22","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Application is incomplete and incorrect. Cust changed design and reapplied."]
[null,"WMECO","Buckland","6F286-2011","01338",57,"Solar","22B5","2011-12-07","2012-02-22",{"$f":"NETWORKDAYS(I82,J82,MALegalHolidays)","v":53},null,53,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-03-12",null,"2012-01-01","Yes","EXP",null,null,null,null,null," ",null,null,"2012-05-01","On line. Third party owned."]
[null,"WMECO","Greenfield","6F290-2011","01301",14.7,"Solar","21C4","2011-12-14","2012-01-26",{"$f":"NETWORKDAYS(I83,J83,MALegalHolidays)","v":30},null,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-02-08",null,"2012-01-01","No","EXP",null,null,null,null,null," ",null,null,"2012-03-19","on line"]
[null,"WMECO","Whately","6A239-2011","01093",260,"Solar","18G8","2011-12-16","2012-04-13",{"$f":"NETWORKDAYS(I84,J84,MALegalHolidays)","v":83},null,83,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-04-19",null,"2012-03-16","No","EXP",null,null,null,null,null," ",null,null,"2012-05-01","on line"]
[null,"WMECO","Easthampton","6A241-2011","01027",3.3,"Wind","15A5","2011-12-22","2012-01-04",{"$f":"NETWORKDAYS(I85,J85,MALegalHolidays)","v":9},null,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-01-12",null,"not supplied","No","EXP",null,null,null,null,null," ",null,null,"2012-02-13","On line. Third party owned. Single phase system on three phase service."]
[null,"WMECO","Hadley","6A242-2011","01035",2000,"Solar","18G4","2011-12-27","2012-02-16",{"$f":"NETWORKDAYS(I86,J86,MALegalHolidays)","v":36},null,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-04-02","2013-07-09",{"$f":"NETWORKDAYS(AC86,AD86,MALegalHolidays)","v":316},0,316,"2013-05-03","2013-09-12",{"$f":"NETWORKDAYS(AH86,AI86,MALegalHolidays)","v":91},51,40,"2013-10-04",null,"2012-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust cancelled project. Int Cust changed inverters and name, (Impact Study 3/12/12 & IS Option 1 10/17/12) new Impact Study approved for option. ISO-NE notification approved. Third party owned. Stand alone generation. New construction.  Detailed Study agreement and check returned to WMECO. Project in Detailed Study mode. Site visit  6/5/13 w/ cust, tech and Verizon, cust needs to decide where to interconnect on property, clock stopped for Detailed Study 6/5/13. Cust asked for an extenstion. Second site visit (8/19/13) interconnection poles laid out work order writing to commence.  Work orders written need to put together estimate to include in IA.  Draft IAs sent out for review 9/12/13, Customer wants breakdown of IA system upgrades. Cust sent comments on draft Exhibit G. waiting for comments on Draft Exhibit H.  Sent IAs for signature. Waiting for signed agreements and money.  Construction of  project may be delayed due to a required Cultural Review at project site. Recvd signed Exhibits G & H, waiting for monies & insurance to schedule construction. "]
[null,"WMECO","Whately","6A247-2012","01093",1000,"Solar","18G8","2012-01-04",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust submitted new application. Stand alone generation. New construction."]
[null,"WMECO","Whately","6A250-2012","01039",1000,"Solar","18G8","2012-01-04",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Cust submitted new application. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6BA253-2012","01008",1000,"Solar","19J2","2012-01-10",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-09-18","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust cancelled project. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6BA254-2012","01008",1000,"Solar","19J2","2012-01-10",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-09-18","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust cancelled project. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Turners Falls","6F295-2012","01376",370,"Hydro","21C6","2012-01-10","2012-03-05",{"$f":"NETWORKDAYS(I91,J91,MALegalHolidays)","v":38},null,38,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-03-20",null,{"$f":"NETWORKDAYS(AC91,AD91,MALegalHolidays)","v":-29274},null," ",null,null,null,null," ","2013-03-27",null,"not supplied","No","STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Tolland","6B125-2012","01634",3500,"Solar","19J4","2012-01-25","2013-01-31",{"$f":"NETWORKDAYS(I92,J92,MALegalHolidays)","v":255},0,255,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-18","2013-06-07",{"$f":"NETWORKDAYS(AC92,AD92,MALegalHolidays)","v":243},0,243,"2013-07-31","2013-09-06",{"$f":"NETWORKDAYS(AH92,AI92,MALegalHolidays)","v":27},null,27,"2013-09-06",null,"2012-09-25","Yes","COMP",null,null,null,null,null," ","2014-09-25","2014-10-03","2014-10-03","Early ISA 6/7/13. Impact Study joint with 6B126-2012 and 6B127-2012. (6/5/12) Int Cust submitted new option, new study will continue when agreement executed (1/25/13). ISO-NE notification submitted and approved. Detailed Study required. Stand alone generation. New construction. Application has two options 2,000 kW or 3,500 kW. Selected option listed in Design Capacity. Customer requested early ISA. Detailed Study has not started yet. Early ISA exhibit G & H sent to cust for signature 6/7/13, rcvd signed Early Exhibit G from Int Cust 6/28/13, waiting for signed Early Exhibit H from Host Cst.  rcvd detailed Study check 7/31/13.  sent e-mail to cust to set up site visit. Site visit 8/8/13 work orders are being written. sent IA to Customer and Interconnecting Customer 9/6/13. Rcvd signed Exhibit H 9/18/13 Waiting for signed Exhibit G and payment for system upgrades. Payment for upgrades received.  Easement for interconnection service has not been completed, waiting for the lawyers to finalize.  The line recloser controls and tranfer trip equpment have been installed.   ION meter has been installed.   DTT is commissioned.  waiting for revised completion info from Customer.  Rcvd revised info, Witness Test scheduled, Witness test passed, Aproval to Operate sent to Interconnecting Customer and Customer, Project is on line."]
[null,"WMECO","Tolland","6B126-2012","01634",1000,"Solar","19J4","2012-01-25",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-18",null,{"$f":"NETWORKDAYS(AC93,AD93,MALegalHolidays)","v":-29336},null," ",null,null,null,null," ",null,null,"2012-09-25","Yes","STD",null,null,null,null,null," ",null,null,null,"Int cust cancelled 6/12/13. Impact Study joint with 6B126-2012 and 6B127-2012. On hold by Cust. ISO-NE notification and Detailed Study required if project proceeds. Stand alone generation. New construction."]
[null,"WMECO","Tolland","6B127-2012","01634",1000,"Solar","19J4","2012-01-25",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-18",null,{"$f":"NETWORKDAYS(AC94,AD94,MALegalHolidays)","v":-29336},null," ",null,null,null,null," ",null,null,"2012-09-25","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust cancelled 6/12/13. Impact Study joint with 6B126-2012 and 6B127-2012. On hold by Cust. ISO-NE notification and Detailed Study required if project proceeds. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Tolland","6B128-2012","01634",1000,"Solar","19J4","2012-01-25",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-09-25","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust after Scoping Meeting. Stand alone generation. New construction."]
[null,"WMECO","West Springfield","6S90-2012","01089",110,"Solar","21N5","2012-02-01","2012-03-02",{"$f":"NETWORKDAYS(I96,J96,MALegalHolidays)","v":22},null,22,null,null,null,null," ","2012-02-29",null,{"$f":"NETWORKDAYS(S96,T96,MALegalHolidays)","v":-29260},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-24",null,"not supplied","No","EXP",null,null,null,null,null," ",null,null,"2012-07-12","On Line. Cust upgraded service."]
[null,"WMECO","Pittsfield","6B130-2012","01201",2000,"Solar","15E2","2012-02-02",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-02","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust after being on hold by Cust. Impact Study Agreement sent to Cust for joint study with 6B131-2012 who did not execute it. Stand alone generation. New construction."]
[null,"WMECO","Pittsfield","6B131-2012","01201",3000,"Solar","15E2","2012-02-02",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-02","Yes","STD",null,null,null,null,null," ",null,null,null,"Talked with Customer  9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status. Cust submitted 3 MW option 4/24/13 for separate Impact Study. Impact Study Agreement sent to Cust for joint study with 6B130-2012 who did not execute it. Stand alone generation. New construction. Application has options 500 kW or 750 kW or 1,000 kW or 3,000. Current 3 MW option listed in Design Capacity. withdrawn"]
[null,"WMECO","Ludlow","6S91-2012","01056",3000,"Solar","19S3","2012-02-03",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-09-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust who submitted new applications. Stand alone generation. New construction."]
[null,"WMECO","Hatfield","6A262-2012","01038",45.6,"Solar","18G5","2012-02-06","2012-04-11",{"$f":"NETWORKDAYS(I100,J100,MALegalHolidays)","v":47},null,47,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-02",null,"not supplied","Yes","EXP",null,null,null,null,null," ","2012-08-24","2012-08-28","2012-08-28","on line"]
[null,"WMECO","Shutesbury","6A263-2012","01072",11.4,"Solar","18G7","2012-02-07","2012-05-01",{"$f":"NETWORKDAYS(I101,J101,MALegalHolidays)","v":59},null,59,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-25",null,"2/2012","No","EXP",null,null,null,null,null," ",null,null,"2012-06-13","on line"]
[null,"WMECO","Deerfield","6F303-2012","01342",22.8,"Solar","22B4","2012-02-07","2012-05-07",{"$f":"NETWORKDAYS(I102,J102,MALegalHolidays)","v":63},null,63,null,null,null,null," ","2012-04-17",null,{"$f":"NETWORKDAYS(S102,T102,MALegalHolidays)","v":-29293},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-10",null,"2012-04-01","Yes","EXP",null,null,null,null,null," ",null,null,"2012-09-12","on line"]
[null,"WMECO","Southampton","6A266-2012","01073",11.18,"Solar","15A1","2012-02-17","2012-04-04",{"$f":"NETWORKDAYS(I103,J103,MALegalHolidays)","v":33},null,33,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-18",null,"2012-04-25","No","EXP",null,null,null,null,null," ",null,null,"2012-08-06","on line"]
[null,"WMECO","Whately","6A267-2012","01373",2000,"Solar","18G8","2012-02-17","2012-04-10",{"$f":"NETWORKDAYS(I104,J104,MALegalHolidays)","v":37},null,37,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-17","2012-11-07",{"$f":"NETWORKDAYS(AC104,AD104,MALegalHolidays)","v":121},0,121,"2012-09-12","2013-01-22",{"$f":"NETWORKDAYS(AH104,AI104,MALegalHolidays)","v":88},0,88,"2013-02-26",null,"2012-09-01","Yes","STD",null,null,null,null,null," ","2014-06-09","2014-06-16","2014-06-25","Int Cust changed their name. Now 3rd party owned. ISO-NE notification approved. Stand alone generation. New construction. Application has three options 1,000 kW or 1,500 kW or 2,000 kW. Option selected listed in Design Capacity.  Waiting for Customer to return signed IA. Cust Exhibit G rcvd 3/6/13. Purge letter sent to Int Cust 5/20/13. Sent new tariff  IA form sent to cust & Int Cust for signature 6/6/13. Rcvd new tariff IA from Int Cust 6/11/13. Need payments to schedule construction. Call w/ Cust ISD by early December providing all upgrade monies & insurance recvd by WMECO by 9/3/13.  System upgrade monies received, construction scheduled.  Construction of interconnection service completed, Customer is energized for testing purposes only, Communication to primary meter  is required before ION meter set can be scheduled.  POTS line to primary meter delayed by Verizon, WMECO investigated using alternate mode of communicatio, after testing device provided by Customer, the device does not communicate with the ION meter, need Verizon POTS line in service before ION meter is installed. Completion docs have been received and reviewed.  ION meter has been set. Witness Test scheduled.  Witness Test passed.  Approval to operate given.  Solar facility is on line."]
[null,"WMECO","Blandford","6B133-2012","01008",2000,"Solar","19J4","2012-02-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust, had been on hold by Cust. Impact Study Agreement for joint study with 6B135-2012 and 6B136-2012 sent to Cust not executed. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6B134-2012","01008",1000,"Solar","19J4","2012-02-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Not included in joint Impact Study with associated applications. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6B135-2012","01008",1000,"Solar","19J4","2012-02-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust, had been on hold by Cust. Impact Study Agreement for joint study with 6B133-2012 and 6B136-2012 sent to Cust not executed. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6B136-2012","01008",4000,"Solar","19J4","2012-02-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Talked with Customer  9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status.  Cust submitted 3 MW and 4 MW options 4/24/13 for separate Impact Study. Impact Study Agreement for joint study with 6B133-2012 and 6B135-2012 sent to Cust not executed. Stand alone generation. New construction. Application has options 1,000 kW or 3,000 kW or 4,000 kW. Highest option listed in Design Capacity. withdrawn"]
[null,"WMECO","Blandford","6B137-2012","01008",1000,"Solar","19J4","2012-02-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Not included in joint Impact Study with associated applications. Stand alone generation. New construction."]
[null,"WMECO","Ludlow","6S96-2012","01056",2000,"Solar","27A5","2012-02-23","2012-06-29",{"$f":"NETWORKDAYS(I110,J110,MALegalHolidays)","v":90},null,90,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-02","2012-10-22",{"$f":"NETWORKDAYS(AC110,AD110,MALegalHolidays)","v":56},null,56,"2012-12-26","2013-03-08",{"$f":"NETWORKDAYS(AH110,AI110,MALegalHolidays)","v":50},0,50,"2013-03-14",null,"2012-09-30","Yes","STD","2013-07-31",null,"2013-07-30",null,null," ","2013-08-02","2013-08-07","2013-08-26","Scoping Mtg. Held.  IA executed.  Impact Study Complete.  Detailed Study Complete. Line construction complete.  System is online under Temporary SOG while DTT/substation issue dealt with.  Temporary SOG is valid only until transfer trip is commissioned. "]
[null,"WMECO","Ludlow","6S97-2012","01056",1000,"Solar","19S3","2012-02-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-09-30","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Proceeding with one application at this site. Third party owned. Stand alone generation. New construction."]
[null,"WMECO","Hatfield","6A271-2012","01038",2000,"Solar","18G6","2012-02-24","2012-07-19",{"$f":"NETWORKDAYS(I112,J112,MALegalHolidays)","v":102},null,102,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-04-30","2012-11-01",{"$f":"NETWORKDAYS(AC112,AD112,MALegalHolidays)","v":130},0,130,"2012-10-10","2012-10-17",{"$f":"NETWORKDAYS(AH112,AI112,MALegalHolidays)","v":6},0,6,"2013-02-13",null,"2012-11-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust trying to find Cust and make this 3rd party owned. ISO-NE notification approved. Stand alone generation. New construction. Sent IA to Jen for signature to send to cust for signature 6/10/13. Developer sent letter 6/30/13 requesting temp suspension due to court case.  Developer sent in first part of system upgrade monies, They have 120 days to send in the remainder of the monies. withdrawn"]
[null,"WMECO","Pittsfield","6B139-2012","01201",2000,"Solar","30B2","2012-02-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-11-06","Yes","STD",null,null,null,null,null," ",null,null,null,"Talked with Customer  9/16/13 re: status of project moving forward, Customer will talk with investors, WMECO to send e-mail with request to Customer of project status. Cust decided to move forward with separate Impact Study. Impact Study will no longer be joint with 6B140-2012. Stand alone generation. New construction. withdrawn"]
[null,"WMECO","Pittsfield","6B140-2012","01201",1000,"Solar","30B2","2012-02-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-11-06","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust, had been on hold by Cust. Impact Study will no longer be joint with 6B139-2012. Stand alone generation. New construction. Application has three options 500 kW or 750 kW or 1,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Agawam","6S98-2012","01001",2000,"Solar","30A6","2012-02-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-11-06","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Stand alone generation. New construction."]
[null,"WMECO","Agawam","6S99-2012","01001",2000,"Solar","30A6","2012-02-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-11-06","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Stand alone generation. New construction. Application has three options 1,000 kW or 1,500 kW or 2,000 kW. Highest option listed in Design Capacity."]
[null,"WMECO","Easthampton","6A273-2012","01027",11,"Solar","15A5","2012-03-01",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-03-20","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Submitted new Simplified Application."]
[null,"WMECO","Lee","6B141-2012","01238",295,"Solar","16B5","2012-03-01","2012-06-11",{"$f":"NETWORKDAYS(I118,J118,MALegalHolidays)","v":71},null,71,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-14",null,"Q2 2012","No","EXP",null,null,null,null,null," ",null,null,"2012-08-10","On line. Third party owned."]
[null,"WMECO","Easthampton","6A275-2012","01027",26.4,"Solar","15A3","2012-03-02","2012-05-11",{"$f":"NETWORKDAYS(I119,J119,MALegalHolidays)","v":50},null,50,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-09-12",null,"2012-04-15","No","EXP",null,null,null,null,null," ",null,null,"2012-10-04","On line. New construction service."]
[null,"WMECO","Hadley","6A277-2012","01035",1000,"Solar","17K1","2012-03-12",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust. Stand alone generation. New construction."]
[null,"WMECO","Hadley","6A278-2012","01035",2500,"Solar","17K1","2012-03-12","2012-07-18",{"$f":"NETWORKDAYS(I121,J121,MALegalHolidays)","v":90},null,90,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-29","2013-06-07",{"$f":"NETWORKDAYS(AC121,AD121,MALegalHolidays)","v":192},0,192,"2013-05-31","2013-07-23",{"$f":"NETWORKDAYS(AH121,AI121,MALegalHolidays)","v":36},18,18,"2013-07-30",null,"2012-10-12","Yes","STD",null,null,null,null,null," ","2014-06-09","2014-06-16","2014-07-02","(impact study 8/7/12) Cust decided on new option. New Impact Study (3/4/13) required. Stand alone generation. New construction. Application has two options 1,500 kW or 2,500 kW. Highest option listed in Design Capacity. Sent Detailed Study to Customer, rcvd signed detailed study agrement 5/16/13, waiting for first check.  Check rcvd for Detailed Study 6/5/13. Site visit to design service 6/18/13.  Customer needs to decide where to interconnect service.  Cust decided on new intconnect point and sent new site plan 7/5/13.  Tech to write work order. Work orders completed 7/19/13, sent cust %10 est for circuit upgrades 7/23/13.   Rcvd Scheule Z for Town of Ashfield, Project is third party owned as of 7/23/13, waiting for revised app with Town of Ashfield info. Rcvd revised Sched Z 7/23/13, rcvd revised app 7/24/13.  Sent draft IAs for signature 7/30/13.  Received signd IA. Call w/ Cust ISD by 11/18/13 providing all upgrade monies & insurance recvd by WMECO by 8/5/13. System upgrade monies received, construction scheduled.  Construction of interconnection service is compelted, Customer is energized for testing purposes only,  Communication to primary meter  is required before ION meter set can be scheduled.  Completion docs have been received and reviewed.  ION meter has been set. Witness Test scheduled.  Witness Test passed. Waiting on Verizon to finish the two FDDA lines.  Verizon finished FDDA lines, tranfer trip finished and commissioned and in service.  Project is on line."]
[null,"WMECO","Longmeadow","6S102-2012","01106",45.6,"Solar","22H11","2012-03-14","2012-05-03",{"$f":"NETWORKDAYS(I122,J122,MALegalHolidays)","v":36},null,{"$f":"IF(K122>0,K122-L122,\" \")","v":36},null,null,null,null,{"$f":"IF(P122>0,P122-Q122,\" \")","v":" "},null,null,null,null,{"$f":"IF(U122>0,U122-V122,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z122>0,Z122-AA122,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE122>0,AE122-AF122,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ122>0,AJ122-AK122,\" \")","v":" "},"2012-06-11",null,"2012-07-01","No","EXP",null,null,null,null,null,{"$f":"IF(AU122>0,AU122-AV122,\" \")","v":" "},null,null,"2012-08-15","On line. Third party owned."]
[null,"WMECO","Lenoxdale","6B142-2012","01242",780,"Solar","17G3","2012-03-19","2013-03-27",{"$f":"NETWORKDAYS(I123,J123,MALegalHolidays)","v":256},null,256,null,null,null,0," ",null,null,null,null," ",null,null,null,null," ","2012-12-17","2013-07-08",{"$f":"NETWORKDAYS(AC123,AD123,MALegalHolidays)","v":138},29,109,"2013-05-10","2013-06-07",{"$f":"NETWORKDAYS(AH123,AI123,MALegalHolidays)","v":20},0,20,"2013-06-03",null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust changed inverters and size on 021413, almost done w/ report continued w/ original study for final report, cust submitted new option 021913 revised study, waited for updated project info. Detailed Study required. Signed Detailed Study Agreement and check rcvd.  Third party owned. Stand alone generation or Cust to upgrade their service. Application has three options 1,000 kW or 885 kW or 780 kW. Customer's current design option listed in Design Capacity. Sent plus/minus 10% and draft IA to Int cust 5/29/13. Sent Exhibit G & H for signatures 6/6/13.   Rvcd signed Exhibit H 6/22/13. Sent phone line specs to customer 6/26/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received.  Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13.  Per conf call with  Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps.  Until these are provided, we will not prepare another tentative construction schedule. withdrawn\nInterconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time.\nIt is the understanding of both Interconnection Customer and WMECO  that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response.  Withdrawn 6/27/14. Int Cust owes WMECO money."]
[null,"WMECO","Lee","6B143-2012","01238",500,"Solar","17G7","2012-03-19","2013-03-27",{"$f":"NETWORKDAYS(I124,J124,MALegalHolidays)","v":256},null,256,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-09","2013-07-08",{"$f":"NETWORKDAYS(AC124,AD124,MALegalHolidays)","v":123},29,94,"2013-05-10","2013-06-07",{"$f":"NETWORKDAYS(AH124,AI124,MALegalHolidays)","v":20},0,20,"2013-06-03",null,"2012-05-12","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust changed inverters,021413 almost done w/ report continued w/ original study for final report, cust submitted new option 021913, revised study, waited for updated project info. Detailed Study required.  Signed detailed Study Agreement and check rcvd.  Third party owned. Stand alone generation. New construction. Sent plus/minus 10% and draft IA to Int cust. Sent Exhibit G & H for signatures 6/6/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates.  Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13.  Per conf call with  Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps.  Until these are provided, we will not prepare another tentative construction schedule. withdrawn\nInterconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time.\nIt is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response.  Withdrawn 6/27/14. Int Cust owes WMECO money."]
[null,"WMECO","Lee","6B144-2012","01238",750,"Solar","16B5","2012-03-19","2013-03-27",{"$f":"NETWORKDAYS(I125,J125,MALegalHolidays)","v":256},null,256,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-09","2013-07-08",{"$f":"NETWORKDAYS(AC125,AD125,MALegalHolidays)","v":123},24,99,"2013-06-04","2013-06-07",{"$f":"NETWORKDAYS(AH125,AI125,MALegalHolidays)","v":4},0,4,"2013-06-26",null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Impact Study joint with 6B145-2012. Int Cust changed inverters, 021413, revised study, waited for updated project info. Detailed Study required. Third party owned. May be new construction service. Application has two options 1,000 kW or 750 kW. Customer's current design option listed in Design Capacity. Received signed Detail Study agreement 052413, waiting for first check.  Plus/minus 10% sent to cust 6/7/13. Sent Exhibit G & H for signature 6/28/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13.  Per conf call with  Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps.  Until these are provided, we will not prepare another tentative construction schedule. withdrawn\nInterconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time.\nIt is the understanding of both Interconnection Customer and WMECO  that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response.  Withdrawn 6/27/14. Int Cust owes WMECO money."]
[null,"WMECO","Lee","6B145-2012","01238",750,"Solar","16B5","2012-03-21","2013-03-27",{"$f":"NETWORKDAYS(I126,J126,MALegalHolidays)","v":254},null,254,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-09","2013-07-08",{"$f":"NETWORKDAYS(AC126,AD126,MALegalHolidays)","v":123},24,99,"2013-06-04","2013-06-07",{"$f":"NETWORKDAYS(AH126,AI126,MALegalHolidays)","v":4},0,4,"2013-06-26",null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Impact Study required joint with 6B144-2012. Int Cust changed inverters 021413, revised study, waited for updated project info . Detailed Study required. Third party owned. Stand alone generation. New construction. Application has two options 1,000 kW or 750 kW. Customer's current design option listed in Design Capacity. Received signed Detail Study agreement 052413, waiting for first check.  Plus/minus 10% sent to cust 6/7/13. Sent Exhibit G & H for signature 6/28/13. Conf call w/ customer 7/29/13 to discuss ISD dates and requirements for those dates. Liability insurance received. Exhibit H from Town of Lee received. Sent two revised construction schedules, waiting for Customer to send in system upgrade monies by 8/30/13.  Per conf call with  Interconnecting Customer on 9/9/13, If the checks and new in service dates are provided before or during our next conference call which is scheduled for 9/23/13, we will be able to discuss the next steps.  Until these are provided, we will not prepare another tentative construction schedule. withdrawn\nInterconnection Customer stated that the ball is in their court and that WMECO will not be held responsible for any delay for construction at this time.\nIt is the understanding of both Interconnection Customer and WMECO that completed construction for this project is not anticipated in 2013. Int Customer in liquidation. Sent notice letter, no response.  Withdrawn 6/27/14. Int Customer owes WMECO money."]
[null,"WMECO","Lee","6B146-2012","01238",1000,"Solar","16B5","2012-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction."]
[null,"WMECO","Lee","6B147-2012","01238",1000,"Solar","16B5","2012-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction."]
[null,"WMECO","Lee","6B148-2012","01238",1000,"Solar","16B5","2012-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction."]
[null,"WMECO","Lee","6B149-2012","01238",1000,"Solar","16B5","2012-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction."]
[null,"WMECO","Lee","6B150-2012","01238",1000,"Solar","16B5","2012-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Int Cust. Will be third party owned. Stand alone generation. New construction."]
[null,"WMECO","Amherst","6A286-2012","01002",3750,"Solar","17K2","2012-03-22",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. On hold by Int Cust. Held Scoping Meeting. Impact Study required. Int Cust may submit option(s). Third party owned. Stand alone generation. New construction. Withdrawn"]
[null,"WMECO","Whately","6A287-2012","01373",1000,"Solar","18G8","2012-03-22",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Cancelled by Cust who submitted new application. Stand alone generation. New construction."]
[null,"WMECO","Middlefield","6B156-2012","01243",12.04,"Solar","18C2","2012-03-29","2012-06-18",{"$f":"NETWORKDAYS(I134,J134,MALegalHolidays)","v":56},null,56,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-07-17",null,"2012-04-24","No","EXP",null,null,null,null,null," ",null,"2012-09-13","2012-09-13","on line"]
[null,"WMECO","Whately","6A289-2012","01373",1000,"Solar","18G8","2012-04-03",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-01-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. On hold by Int Cust. Held Scoping Meeting. Impact Study required. Int Cust deciding if will move forward. Third party owned. Stand alone generation. New construction."]
[null,"WMECO","Hatfield","6A290-2012","01038",44.4,"Solar","18G5","2012-04-06","2012-06-08",{"$f":"NETWORKDAYS(I136,J136,MALegalHolidays)","v":44},null,44,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-06-29",null,"2012-04-30","No","EXP",null,null,null,null,null," ",null,null,"2012-07-27","on line"]
[null,"WMECO","Hadley","6A291-2012","01035",1000,"Solar","17K1","2012-04-06","2012-06-29",{"$f":"NETWORKDAYS(I137,J137,MALegalHolidays)","v":59},null,59,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-29",null,{"$f":"NETWORKDAYS(AC137,AD137,MALegalHolidays)","v":-29387},null," ",null,null,null,null," ",null,null,"2012-10-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Int Cust cancelled project, had been on hold. Joint Impact Study with 6A278-2012 in progress but on hold by Int Cust. Stand alone generation. New construction."]
[null,"WMECO","Blandford","6B159-2012","01008",125,"Solar","19J4","2012-04-09",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-25","Yes","STD",null,null,null,null,null," ",null,null,null,"Impact Study estimate sent to customer. Cust submitted two options. On hold by Cust. Third party owned. Either new construction or cust to upgrade service. Third party owned. Application has three options 50 kW or 100 kW or 125 kW. Highest option listed in Design Capacity. cancelled"]
[null,"WMECO","Hatfield","6A294-2012","01088",67.5,"Solar","18G5","2012-04-10","2012-10-09",{"$f":"NETWORKDAYS(I139,J139,MALegalHolidays)","v":126},null,126,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-10-10",null,"2012-10-31","No","EXP",null,null,null,null,null," ",null,null,"2012-11-13","On line. Third party owned. Will not export. "]
[null,"WMECO","Chesterfield","6F316-2012","01012",60,"Solar","18K3","2012-04-11","2012-05-18",{"$f":"NETWORKDAYS(I140,J140,MALegalHolidays)","v":27},null,27,null,null,null,null," ","2012-07-12",null,{"$f":"NETWORKDAYS(S140,T140,MALegalHolidays)","v":-29353},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-05-31",null,"2012-05-01","No","EXP",null,null,null,null,null," ",null,null,"2012-09-25","on line"]
[null,"WMECO","Turners Falls","6F319-2012","01376",8.6,"Solar","21C2","2012-04-23","2012-07-18",{"$f":"NETWORKDAYS(I141,J141,MALegalHolidays)","v":61},null,61,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-07-25",null,"2012-04-30","No","EXP",null,null,null,null,null," ",null,null,"2012-09-18","On line. Two phase system on three phase service."]
[null,"WMECO","Cummington","6F322-2012","01026",12.255000000000001,"Solar","18K3","2012-05-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-05-25","TBD","EXP",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. Held Scoping Meeting. Waiting for info."]
[null,"WMECO","Hadley","6A312-2012","01035",95,"Solar","17K6","2012-05-17","2012-07-05",{"$f":"NETWORKDAYS(I143,J143,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-09-25",null,"2012-07-13","No","EXP",null,null,null,null,null," ","2012-12-27","2012-12-28","2012-12-28","on line"]
[null,"WMECO","West Springfield","6S112-2012","01089",333,"Solar","21N8 ","2012-05-18","2012-08-15",{"$f":"NETWORKDAYS(I144,J144,MALegalHolidays)","v":62},null,62,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-17",null,"2012-10-29","No","EXP",null,null,null,null,null," ",null,null,null,"Int Cust delayed construction to 2013. Need completion documents to schedule Witness Test. Third party owned. Have heard nothing from cust as of 8/21/13. Waiting for Customer.  Custoemr may be cancelling this project. Cancelled"]
[null,"WMECO","Turners Falls","6F325-2012","01376",500,"Solar","21C3","2012-05-29",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-11-01","Yes","EXP",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. Impact Study Agreement out for signature. Need signed agreement and check for initial payment. Third party owned. Stand alone generation. New construction. Withdrawn"]
[null,"WMECO","Easthampton","6A316-2012","01027",298,"Solar","15A3","2012-05-30","2013-08-27",{"$f":"NETWORKDAYS(I146,J146,MALegalHolidays)","v":311},null,311,"2013-08-28","2013-12-10",{"$f":"NETWORKDAYS(N146,O146,MALegalHolidays)","v":70},58,12,"2013-12-10",null,{"$f":"NETWORKDAYS(S146,T146,MALegalHolidays)","v":-29703},52," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-08-10",null,"EXP",null,null,null,null,null," ",null,null,null,"New option (option 2) submitted. Application Complete.  In Supplemental Review. Held Meeting.  Application cancelled per Interconnecting Customer 4/28/14"]
[null,"WMECO","Easthampton","6A317-2012","01027",120,"Solar","15A2","2012-05-30","2013-08-06",{"$f":"NETWORKDAYS(I147,J147,MALegalHolidays)","v":296},297,-1,"2013-08-07","2013-09-11",{"$f":"NETWORKDAYS(N147,O147,MALegalHolidays)","v":25},5,20,"2014-04-29","2014-05-20",{"$f":"NETWORKDAYS(S147,T147,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-07-31",null,"2012-08-10","TBD","EXP",null,null,null,null,null," ","2015-06-26","2015-06-26","2015-07-10","New option (option 2) submitted. Application Complete.  Supplemental Review complete.  Received signed Exhibit H. Received signed Exhibit G.  Received CoC.  Compliance docs received.  Witness Test performed.  Online"]
[null,"WMECO","Deerfield","6F328-2012","01342",19.989999999999998,"Solar","22B1","2012-06-04","2012-08-14",{"$f":"NETWORKDAYS(I148,J148,MALegalHolidays)","v":51},null,51,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-29",null,"2012-09-01","No","EXP",null,null,null,null,null," ","2012-11-01","2012-11-07","2012-11-08","on line"]
[null,"WMECO","Springfield","6S115-2012","01104",500,"Solar","5J15","2012-06-04","2012-10-18",{"$f":"NETWORKDAYS(I149,J149,MALegalHolidays)","v":96},null,96,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-02-21",null,"Q4 2012","No","EXP",null,null,null,null,null," ","2013-05-20","2013-05-21","2013-05-30","Third party owned. On line."]
[null,"WMECO","Hatfield","6A320-2012","01038",1000,"Solar","18G6","2012-06-08",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-06-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping Meeting. On hold by Int Cust. See 6A321-2012 and 6A322-2012. Stand alone generation. New construction."]
[null,"WMECO","Hatfield","6A321-2012","01038",1000,"Solar","18G6","2012-06-08",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-06-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping meeting. Was on hold by Int Cust. See 6A320-2012 and 6A322-2012. Stand alone generation. New construction."]
[null,"WMECO","Hatfield","6A322-2012","01038",1000,"Solar","18G6","2012-06-08",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-06-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Sent purge letter 5/20/13. Int cust cancelled 6/12/13. Held Scoping Meeting. On hold by Int Cust. See 6A320-2012 and 6A321-2012. Stand alone generation. New construction."]
[null,"WMECO","Hinsdale","6B169-2012","01235",23.995000000000001,"Solar","18C2","2012-06-27","2012-08-03",{"$f":"NETWORKDAYS(I153,J153,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-08-10",null,"2012-08-01","Yes","EXP",null,null,null,null,null," ",null,"2012-09-28","2012-09-28","on line"]
[null,"WMECO","Shelburne Falls","6F338-2012","01370",82,"Solar","29R1","2012-06-28","2012-10-07",{"$f":"NETWORKDAYS(I154,J154,MALegalHolidays)","v":70},null,70,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-10-22",null,"2012-09-01","No","EXP",null,null,null,null,null," ","2012-11-28","2012-12-05","2012-12-06","on line"]
[null,"WMECO","Easthampton","6A332-2012","01027",14,"Solar","15A5","2012-07-13","2012-11-02",{"$f":"NETWORKDAYS(I155,J155,MALegalHolidays)","v":79},null,79,"2012-11-05","2012-11-16",{"$f":"NETWORKDAYS(N155,O155,MALegalHolidays)","v":9},0,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-20",null,"2012-09-01","No","EXP",null,null,null,null,null," ","2012-12-14","2012-12-20","2012-12-20","on line"]
[null,"WMECO","Springfield","6S123-2012","01104",142,"Solar","5J9","2012-07-16","2012-10-23",{"$f":"NETWORKDAYS(I156,J156,MALegalHolidays)","v":70},null,70,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-03-13",null,"not supplied","No","EXP",null,null,null,null,null," ","2012-04-10","2013-04-11","2013-04-23","On line. Third party owned. "]
[null,"WMECO","Springfield","6S124-2012","01104",266,"Solar","5J18","2012-07-16","2012-08-30",{"$f":"NETWORKDAYS(I157,J157,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-16",null,"2012-10-30","No","EXP",null,null,null,null,null," ","2013-05-30","2013-05-31","2013-05-31","New construction service. On line"]
[null,"WMECO","Southwick","6S126-2012","01077",1500,"Solar","29A1","2012-07-17","2012-10-18",{"$f":"NETWORKDAYS(I158,J158,MALegalHolidays)","v":66},65,1,null,null,null,null," ",null,null,null,null," ","2012-10-19","2013-03-05",{"$f":"NETWORKDAYS(X158,Y158,MALegalHolidays)","v":91},89,2,"2013-04-16","2013-09-20",{"$f":"NETWORKDAYS(AC158,AD158,MALegalHolidays)","v":110},0,110,"2014-03-31","2014-08-20",{"$f":"NETWORKDAYS(AH158,AI158,MALegalHolidays)","v":99},99,0,"2013-12-16",null,"Q4 2012","Yes","STD",null,null,null,null,null," ",null,null,null,"Impact Study in progress. Cust to submit info. Third party owned. Stand alone generation. New construction. Sent ISO docs to Customer.  Waiting for Customer to sned ISO docs.  Waiting for final Impact Study report from vendor. Received final report from vendor, sent report to customer 9/20/13. Detailed Stduy Agreement sent to customer.  Talked to Carter Wilde-Widling on 11/26/13, the Customer is waiting for the SREC II program results in order to mmove forward with the project.  It will not be on line before June 2014 and they may change their design to offset customer load. Received signed Detailed Study Agreement 12/9/13 as well as  request for an extension for the Detailed Study phase as the Customer cannot move forward until MA SREC-II is in place.  Extension has lapsed, Customer is moving forward with the detailed Study, proposed dates for site visit, Customer is not ready, will notify WMECO when ready, project is on Customer hold. Held site visit, after site visit Customer informed WMECO PM that the adjoining resident objected to overhead poles, PM got information on pad mounted metering, however WMECO does not use padmounted recloser.  The Customer informed WMECO that the overhead equipment is no longer an issue. The technician is writing the work order.  Work order has been written, Customer has Early ISA from December 2013, sent new Exhibit G & H dated August 20, 2014, Exhibit G included plu/minus 10% and construction schedule.  Customer wants to send construction monies ASAP.  Waiting for Customer to send system Modifications monies.  Verizon has not yet set poles. cancelled"]
[null,"WMECO","Amherst","6A336-2012","01002",11.4,"Solar","19B16","2012-07-24","2012-09-28",{"$f":"NETWORKDAYS(I159,J159,MALegalHolidays)","v":48},null,48,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-10-11",null,"2012-08-01","No","EXP",null,null,null,null,null," ","2012-11-15","2012-11-16","2012-11-16","on line"]
[null,"WMECO","Hatfield","6A339-2012","01038",175,"Solar","18G5","2012-07-27","2012-08-31",{"$f":"NETWORKDAYS(I160,J160,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-10-09",null,"not supplied","No","EXP",null,null,null,null,null," ","2012-11-29","2012-12-03","2012-12-01","on line"]
[null,"WMECO","Amherst","6A341-2012","01002",34.200000000000003,"Solar","17K2","2012-07-30","2012-11-29",{"$f":"NETWORKDAYS(I161,J161,MALegalHolidays)","v":84},null,84,"2012-11-30","2012-12-04",{"$f":"NETWORKDAYS(N161,O161,MALegalHolidays)","v":3},0,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-12-05",null,"2012-09-12","No","EXP",null,null,null,null,null," ","2012-12-27","2012-12-28","2012-12-31","on line"]
[null,"WMECO","Amherst","6A343-2012","01027",57,"Solar","17K8","2012-07-31","2012-12-10",{"$f":"NETWORKDAYS(I162,J162,MALegalHolidays)","v":90},null,90,"2012-12-11","2013-01-08",{"$f":"NETWORKDAYS(N162,O162,MALegalHolidays)","v":19},0,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-10",null,"2012-09-01","No","EXP",null,null,null,null,null," ","2013-02-26","2013-02-28","2013-02-28","on line"]
[null,"WMECO","Amherst","6A344-2012","01002",29.984999999999999,"Solar","17K7","2012-08-01","2012-10-03",{"$f":"NETWORKDAYS(I163,J163,MALegalHolidays)","v":45},null,45,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-20",null,"not supplied","No","EXP",null,null,null,null,null," ","2012-12-18","2012-12-19","2012-12-19","on line"]
[null,"WMECO","Greenfield","6F354-2012","01301",135,"Solar","21C1","2012-08-17","2012-10-29",{"$f":"NETWORKDAYS(I164,J164,MALegalHolidays)","v":50},null,50,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-20",null,"not supplied","No","EXP",null,null,null,null,null," ","2012-12-10","2012-12-12","2012-12-12","on line"]
[null,"WMECO","Gill","6F355-2012","01354",1250,"Diesel","21B8","2012-08-20","2012-09-12",{"$f":"NETWORKDAYS(I165,J165,MALegalHolidays)","v":17},null,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-12-14","2013-08-21",{"$f":"NETWORKDAYS(AC165,AD165,MALegalHolidays)","v":171},17,154,null,null,null,null," ","2013-12-12",null,"2012-11-25","TBD","STD",null,null,null,null,null," ","2017-08-10","2017-05-19","2017-08-21","Protection review in progress. Will not export. Closed transition emergency generator. ISO notification not required. Waiting for Customer.  No longer waiting for customer, need protection review of information that customer sent. Review finished need to send IA.  Waiting for information from Customer. Received signed Exhibit G & H.  Waiting for relay test results from Customer."]
[null,"WMECO","Springfield","6S136-2012","01119",333,"Solar","20A33","2012-08-20","2012-10-05",{"$f":"NETWORKDAYS(I166,J166,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-12-21",null,"2012-11-01","No","EXP",null,null,null,null,null," ","2012-12-27","2012-12-31","2012-12-31","On line. Third party owned."]
[null,"WMECO","Tolland","6B180-2012","01034",136.80000000000001,"Solar","19J4","2012-08-22",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2013-01-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Purge letter sent 5/20/13. Withdrawn 7/8/13 due to no response. Waiting for Cust to submit info. New Construction. "]
[null,"WMECO","Amherst","6A347-2012","01002",14,"Solar","17K8","2012-08-24","2012-11-26",{"$f":"NETWORKDAYS(I168,J168,MALegalHolidays)","v":62},null,62,"2012-11-27","2012-11-29",{"$f":"NETWORKDAYS(N168,O168,MALegalHolidays)","v":3},0,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-30",null,"2012-12-01","Yes","EXP",null,"2012-12-06","2012-12-06",{"$f":"NETWORKDAYS(AS168,AT168,MALegalHolidays)","v":1},0,1,"2012-12-14","2012-12-17","2012-12-17","on line"]
[null,"WMECO","Leyden ","6F358-2012","01337",38,"Solar","22B7","2012-08-28","2012-09-07",{"$f":"NETWORKDAYS(I169,J169,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-06",null,"2012-12-01","Yes","EXP",null,null,null,null,null," ","2013-05-17","2013-05-22","2013-05-22","on line"]
[null,"WMECO","Easthampton","6A349-2012","01027",83,"Solar","15A2","2012-08-29","2012-09-26",{"$f":"NETWORKDAYS(I170,J170,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-16",null,"2012-11-12","No","EXP",null,null,null,null,null," ","2013-03-29","2013-04-02","2013-04-02","On line. New construction service."]
[null,"WMECO","Greenfield","6F360-2012","01301",3.4,"Solar","28WNW_1","2012-08-29","2012-09-20",{"$f":"NETWORKDAYS(I171,J171,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-15",null,"2012-09-30","No","STD",null,null,null,null,null," ","2013-04-22","2013-04-23","2013-04-23","on line"]
[null,"WMECO","Hancock","6B183-2012","01237",6000,"Solar","30B7","2012-09-05",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q3 2013","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Int Cust submitted new option. Third party owned. Stand alone generation. New Construction. Applicationm has two options 1,500 kW or 6,000 kW. Highest option listed in Design Capacity. withdrawn"]
[null,"WMECO","Hancock","6B184-2012","01237",1500,"Solar","30B7","2012-09-05",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q3 2013","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Third party owned. Stand alone generation. New Construction. Project hold per Int Cust due to net metering laws. Submitted option to related project. Withdrawn"]
[null,"WMECO","Hancock","6B185-2012","01237",1500,"Solar","30B7","2012-09-05",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q3 2013","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust sent purge letter 5/20/13. 7/2/13 Cust said will continue. Third party owned. Stand alone generation. New Construction. Project hold per Int Cust due to net metering laws. Submitted option to related project. withdrawn"]
[null,"WMECO","Deerfield","6F368-2012","01342",34.83,"Solar","22B1","2012-09-06","2012-11-09",{"$f":"NETWORKDAYS(I175,J175,MALegalHolidays)","v":46},null,46,"2012-11-12","2012-11-19",{"$f":"NETWORKDAYS(N175,O175,MALegalHolidays)","v":5},0,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-26",null,"not supplied","No","EXP",null,null,null,null,null," ","2012-12-14","2013-01-03","2013-01-03","on line"]
[null,"WMECO","Russell","6A357-2012","01071",125,"Solar","19J2","2012-09-17","2012-10-04",{"$f":"NETWORKDAYS(I176,J176,MALegalHolidays)","v":14},2,12,"2012-11-05","2012-11-06",{"$f":"NETWORKDAYS(N176,O176,MALegalHolidays)","v":2},0,2,null,null,null,null," ",null,null,null,null," ","2013-03-18","2013-09-03",{"$f":"NETWORKDAYS(AC176,AD176,MALegalHolidays)","v":117},0,117,"2013-09-18","2013-10-10",{"$f":"NETWORKDAYS(AH176,AI176,MALegalHolidays)","v":17},0,17,"2013-12-10",null,"2012-11-08","Yes","STD",null,null,null,null,null," ",null,null,null,"Cust decided on own Impact Study instead of joint study, study in progress. Stand alone generation. New construction. First site visit 6/25/13, second site visit to design new service 7/1/13.  Sent prices for two options for upgrades/new service 7/24/13-waiting for customer to contact WMECO with their decision on how to move forward with project. conf cal w/ Paradise 8/21/13 customer needs to decide on option. Customer decided upon a primary metered service. Sent out Detailed Study Agreement for signature 9/3/13. Customer sent signed agreement and first check 9/18/13, work order writing underway.  Customer is still deciding on option for interconnection service.  Sent Draft IA for review 10/18/13.  Sent IA for signature. Customer cancelled project."]
[null,"WMECO","Middlefield","6B190-2012","01243",10.965,"Solar","18C2","2012-09-24","2012-10-17",{"$f":"NETWORKDAYS(I177,J177,MALegalHolidays)","v":17},0,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-01-24",null,"2012-11-24","No","EXP",null,null,null,null,null," ","2013-06-18","2013-06-20","2013-06-20"," On Line 6/20/13."]
[null,"WMECO","Westhampton","6A363-2012","01027",12.9,"Solar","15A3","2012-10-01","2012-10-01",{"$f":"NETWORKDAYS(I178,J178,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2012-11-27",null,"2012-09-28","No","EXP",null,null,null,null,null," ","2012-12-26","2012-12-31","2012-12-31","on line"]
[null,"WMECO","Pittsfield","6B194-2012","01201",23.22,"Solar","30B4","2012-10-02","2012-11-15",{"$f":"NETWORKDAYS(I179,J179,MALegalHolidays)","v":31},null,31,"2012-11-16",null,{"$f":"NETWORKDAYS(N179,O179,MALegalHolidays)","v":-29441},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-11",null,"not supplied","No","EXP",null,null,null,null,null," ","2013-05-02","2013-05-03","2013-05-03","Was third party owned. Single phase inverters on three phase service. On line."]
[null,"WMECO","Pittsfield","6B195-2012","01201",18.059999999999999,"Solar","30B4","2012-10-02","2012-11-13",{"$f":"NETWORKDAYS(I180,J180,MALegalHolidays)","v":29},null,29,"2012-11-14",null,{"$f":"NETWORKDAYS(N180,O180,MALegalHolidays)","v":-29439},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-11",null,"not supplied","No","EXP",null,null,null,null,null," ","2013-05-02","2013-05-03","2013-05-03","Was third party owned. On line."]
[null,"WMECO","Ludlow","6S144-2012","01056",600,"Diesel","27A4","2012-10-19","2012-11-15",{"$f":"NETWORKDAYS(I181,J181,MALegalHolidays)","v":19},0,19,"2012-11-27","2013-06-21",{"$f":"NETWORKDAYS(N181,O181,MALegalHolidays)","v":142},40,102,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-07-03",null,"2012-11-12","No","EXP",null,null,null,null,null," ","2013-07-29","2013-07-30","2013-08-01","May not export. Closed transition emergency generator. Generator to be interconnected with Big Y service,  cust on line 7/30/13. On line 8/7/13."]
[null,"WMECO","Pittsfield","6B225-2012","01201",23.22,"Solar","30BNW_1","2012-10-23","2012-11-07",{"$f":"NETWORKDAYS(I182,J182,MALegalHolidays)","v":12},null,12,"2012-11-08",null,{"$f":"NETWORKDAYS(N182,O182,MALegalHolidays)","v":-29436},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-03-21",null,"not supplied","No","EXP",null,null,null,null,null," ","2013-04-01","2013-04-05","2013-04-05","On line. Single phase inverters on three phase service."]
[null,"WMECO","Pittsfield","6B234-2012","01201",19.78,"Solar","30B7","2012-11-16","2013-02-21",{"$f":"NETWORKDAYS(I183,J183,MALegalHolidays)","v":64},28,36,"2013-02-22","2013-02-22",{"$f":"NETWORKDAYS(N183,O183,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-08",null,"2013-01-21","No","EXP",null,null,null,null,null," ","2014-03-03","2014-03-05","2014-03-05","on line"]
[null,"WMECO","Hadley","6A381-2012","01035",760,"Solar","17K5","2012-11-21","2013-07-30",{"$f":"NETWORKDAYS(I184,J184,MALegalHolidays)","v":170},2,168,"2012-11-30","2013-09-10",{"$f":"NETWORKDAYS(N184,O184,MALegalHolidays)","v":194},153,41,null,null,null,null," ","2013-01-31","2013-01-31",{"$f":"NETWORKDAYS(X184,Y184,MALegalHolidays)","v":1},0,1,"2013-10-08","2013-11-25",{"$f":"NETWORKDAYS(AC184,AD184,MALegalHolidays)","v":33},2,31,null,null,null,null," ",null,null,"2013-12-15","Yes","STD",null,null,null,null,null," ",null,null,null,"Stand alone generation. New construction. May be third party owned. Scoping meeting held.  Project on hold (2/14/13), customer needs to submit option because of inverter change.  Purge letter sent to Int Cust 5/20/13. Rcvd new option 5/28/13 from customer. Need to perform initial review of new option. New project size 10 kW larger than original. Design 750 kW or 760 kW. Highest design listed. 8/20/13 call with designer - Customer sending new option.  Recieved new option, need to make project smaller due to wetlands. Customer informed WMECO that they would move forward with the 760 kW project on 9/4/13.  Waiting for Customer to revise drawings.  Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades.  Waiting for customer to submit correct site plan and one line. Sent Impact Study agreement for signature 9/26/13. Still waiting for revised project information. Received updated info. Received Impact Study agreement and first check. Sent Impact Study Report and Detailed Study Agreement to Customer. Sents Early ISA to Customer for signature and received signed early ISA from Customer 12/19/13. Detailed Study was sent out for signature, Customer has not returned signed agreement. Project cancelled by Interconnecting Customer."]
[null,"WMECO","Hadley","6A382-2012","01035",760,"Solar","17K5","2012-11-21","2012-11-29",{"$f":"NETWORKDAYS(I185,J185,MALegalHolidays)","v":5},2,3,"2012-11-30","2013-01-31",{"$f":"NETWORKDAYS(N185,O185,MALegalHolidays)","v":42},0,42,null,null,null,null," ","2013-01-31","2013-01-31",{"$f":"NETWORKDAYS(X185,Y185,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,"2013-12-15","Yes","STD",null,null,null,null,null," ",null,null,null,"Stand alone generation. New construction. May be third party owned. Scoping meeting held.   Project on hold (2/14/13), customer needs to submit option because of inverter change.  Purge letter sent to Int Cust 5/20/13. Rcvd new option 5/28/13 from customer. Need to perform initial review of new option.  New project size 10 kW larger than original. Design 750 kW or 760 kW. Highest design listed. 8/20/13 call with deigner - Customer sending new option. Customer sent e-mail 8/29/13 that this project has been cancelled."]
[null,"WMECO","Lanesborough","6B236-2012","01237",20.2,"Solar","15E1","2012-11-21","2012-12-03",{"$f":"NETWORKDAYS(I186,J186,MALegalHolidays)","v":7},0,{"$f":"IF(K186>0,K186-L186,\" \")","v":7},"2012-11-22","2012-11-22",{"$f":"NETWORKDAYS(N186,O186,MALegalHolidays)","v":0},0,{"$f":"IF(P186>0,P186-Q186,\" \")","v":" "},null,null,null,null,{"$f":"IF(U186>0,U186-V186,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z186>0,Z186-AA186,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE186>0,AE186-AF186,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ186>0,AJ186-AK186,\" \")","v":" "},null,null,"2013-02-07","TBD","EXP",null,null,null,null,null,{"$f":"IF(AU186>0,AU186-AV186,\" \")","v":" "},null,null,null,"Cancelled. New application submitted"]
[null,"WMECO","Springfield","6S149-2012","01105",5000,"Natural Gas / Diesel","08C21, 08C23, 21S3","2012-11-26",null,null,208," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2012-10-15","TBD","STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B238-2012","01201",45.795000000000002,"Solar","30B4","2012-11-27","2012-12-03",{"$f":"NETWORKDAYS(I188,J188,MALegalHolidays)","v":5},null,5,"2012-12-04","2013-06-27",{"$f":"NETWORKDAYS(N188,O188,MALegalHolidays)","v":141},46,95,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-08-19",null,"2012-11-30","TBD","EXP",null,null,null,null,null," ","2013-09-29","2013-09-30","2013-09-30","Customer is on line 9/30/13."]
[null,"WMECO","Southampton","6A384-2012","01073",600,"Diesel","15A1","2012-12-04","2012-12-07",{"$f":"NETWORKDAYS(I189,J189,MALegalHolidays)","v":4},0,4,"2013-06-10","2013-06-21",{"$f":"NETWORKDAYS(N189,O189,MALegalHolidays)","v":9},8,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-07-03",null,"2012-12-31","TBD","EXP",null,null,null,null,null," ","2013-07-29","2013-07-30","2013-07-30","Will not export. Closed transition emergency generator. Generator to be interconnected with Big Y service,  Customer on line, 7/30/13."]
[null,"WMECO","Pittsfield","6B240-2012","01201",11.4,"Solar","30B3","2012-12-05","2013-03-13",{"$f":"NETWORKDAYS(I190,J190,MALegalHolidays)","v":67},33,34,"2013-03-14","2013-04-08",{"$f":"NETWORKDAYS(N190,O190,MALegalHolidays)","v":18},0,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-09",null,"2013-01-21","TBD","EXP",null,null,null,null,null," ",null,null,null,"Cancelled. New application submitted"]
[null,"WMECO","Montague","6F410-2012","01351",11.4,"Solar","21C7","2012-12-13","2013-02-12",{"$f":"NETWORKDAYS(I191,J191,MALegalHolidays)","v":41},null,41,"2013-02-12","2013-02-12",{"$f":"NETWORKDAYS(N191,O191,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-03-19",null,"2013-02-01","No","EXP",null,null,null,null,null," ","2013-04-30","2013-05-03","2013-05-03","on line"]
[null,"WMECO","Amherst","6A385-2012","01002",19.350000000000001,"Solar","17K2","2012-12-17","2013-02-05",{"$f":"NETWORKDAYS(I192,J192,MALegalHolidays)","v":34},null,34,"2013-02-05","2013-02-12",{"$f":"NETWORKDAYS(N192,O192,MALegalHolidays)","v":6},0,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-02-14",null,"not supplied","No","EXP",null,null,null,null,null," ","2013-03-29","2013-04-01","2013-04-01","Cust made change to service. On line."]
[null,"WMECO","Springfield","6S154-2012","01111",5000,"Diesel","5J14","2012-12-17","2013-04-19",{"$f":"NETWORKDAYS(I193,J193,MALegalHolidays)","v":85},0,85,"2013-05-13","2013-10-28",{"$f":"NETWORKDAYS(N193,O193,MALegalHolidays)","v":116},45,71,null,null,null,null," ","2013-04-22","2013-04-22",{"$f":"NETWORKDAYS(X193,Y193,MALegalHolidays)","v":1},0,1,"2013-10-28","2013-11-13",{"$f":"NETWORKDAYS(AC193,AD193,MALegalHolidays)","v":12},0,12,null,null,null,null," ","2014-01-09",null,"not supplied","TBD","STD",null,null,null,null,null," ","2014-11-13","2014-11-30","2014-12-01","Closed transition generator. Will export 250 kW for 10 seconds via reverse power relay.  Initial review done. Waiting for cutomer to send revised drawings. Protection review done, need revised info from Customer. Revised info sent is O.K.  Sent Draft IA to Customer for review.  Sent revised Draft IA for review 11/18/13. Exhibit G for signature sent  to Customer 1/9/14.  Waiting on Customer for relay test results and final doucumentation to peform a Witness Test.  Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14.  Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14.    Witness Test performed.  Generators on line."]
[null,"WMECO","Amherst","6A387-2012","01059",3000,"Solar","18G7","2012-12-26",null,null,148," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2013-07-01","Yes","STD",null,null,null,null,null," ",null,null,null,"Stand alone generation. New construction. Third party owned. Held Scoping meeting.  Interconnecint Customer may submit options. Need updated drawings and options to continue. Withdrawn"]
[null,"WMECO","Richmond","6B254-2013","01254",11.2,"Solar","30B7","2013-01-08","2013-02-20",{"$f":"NETWORKDAYS(I195,J195,MALegalHolidays)","v":30},2,28,"2013-02-21","2013-03-11",{"$f":"NETWORKDAYS(N195,O195,MALegalHolidays)","v":13},0,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-03-14",null,"2013-03-13","No","EXP",null,null,null,null,null," ",null,null,null,"Cancelled. New Simplified application submitted."]
[null,"WMECO","West Springfield","6S155-2013","01089",16.984999999999999,"Solar","21N9","2013-01-10","2013-03-06",{"$f":"NETWORKDAYS(I196,J196,MALegalHolidays)","v":38},1,37,"2013-03-07","2013-03-07",{"$f":"NETWORKDAYS(N196,O196,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-01",null,"2013-01-01","No","EXP",null,null,null,null,null," ","2013-05-08","2013-05-09","2013-05-09","on line"]
[null,"WMECO","Pittsfield","6B257-2013","01201",21.93,"Solar","30B4","2013-01-16","2013-01-23",{"$f":"NETWORKDAYS(I197,J197,MALegalHolidays)","v":5},0,5,"2013-01-24","2013-01-24",{"$f":"NETWORKDAYS(N197,O197,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-07-08",null,"not supplied","TBD","EXP",null,null,null,null,null," ","2013-10-09","2013-10-10","2013-10-10"," on line 10/10/13."]
[null,"WMECO","Bernardston ","6F432-2013","01337",31.39,"Solar","21B8","2013-02-01","2013-03-18",{"$f":"NETWORKDAYS(I198,J198,MALegalHolidays)","v":31},4,27,"2013-03-19","2013-04-03",{"$f":"NETWORKDAYS(N198,O198,MALegalHolidays)","v":12},5,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-04-08",null,"2013-05-01","Yes","EXP",null,null,null,null,null," ","2013-05-31","2013-06-05","2013-06-05","on line"]
[null,"WMECO","Hadley","6A405-2013","01035",833,"Solar","18G4","2013-02-11","2013-06-19",{"$f":"NETWORKDAYS(I199,J199,MALegalHolidays)","v":89},26,63,"2013-07-09","2013-07-12",{"$f":"NETWORKDAYS(N199,O199,MALegalHolidays)","v":4},0,4,null,null,null,null," ","2013-07-12","2013-07-12",{"$f":"NETWORKDAYS(X199,Y199,MALegalHolidays)","v":1},0,1,"2013-10-07","2013-11-25",{"$f":"NETWORKDAYS(AC199,AD199,MALegalHolidays)","v":34},0,34,null,null,null,null," ","2013-12-23",null,"2013-12-15","Yes","STD",null,null,null,null,null," ",null,null,null,"Stand alone generation. New construction. May be third party owned. Will not be third party owned per Customer.  Waiting for Customer to revise drawings.  Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades. Waiting for Customer to supply revised info. Interconnecting Customer wants Impact Study to study 833, 500 and 333 kW projects or other size that will not require significant upgrades for other than the interconnection service.  If  Impact Study determines project size other than the original submitted inverters, the Interconneting Customer will need to submit new application package and fee and the DG process starts over. Sent Joint Impact Study to Interconnecting Customer 10/2/13 for 6A405-2013 & 6A415-2013 total cost $33,000. Received Impact Study agreement and first check. Sent Impact Study Report and Detailed Study Agreement to Customer.  Sent Early ISA to Customer for signature 12/23/13, recieved signed Early ISA from Customer 12/28/13.  Detailed Study agreement was sent out for signature, Customer has not returned signed agreement.  Customer wanted to interconnect this and the 6A415-2013 project at one interconnection point, WMECO sent them an estimate for this design, the Customer has not decided whether to go with one interconnection point or to only build the 6A415-2013 project.  Customer had an extension for the Detailed Syudy phase.  Extension expired, WMECO DG sent e-mail to Customer that this project is withdrawn for the interconnection queue."]
[null,"WMECO","Hadley","6A408-2013","01035",2730,"Solar","17K1","2013-02-14","2013-03-29",{"$f":"NETWORKDAYS(I200,J200,MALegalHolidays)","v":31},1,30,"2013-04-01",null,{"$f":"NETWORKDAYS(N200,O200,MALegalHolidays)","v":-29531},93," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2013-10-13","Yes","STD",null,null,null,null,null," ",null,null,null,"Sent email to schedule Scoping Mtg. Stand alone generation. New construction. May be third party owned. Held Scoping meeting.  Need decsision from Interconnecting Customer on how they will move forward. Cancelled"]
[null,"WMECO","Sunderland","6A411-2013","01375",300,"Solar","18G3","2013-02-27","2013-04-03",{"$f":"NETWORKDAYS(I201,J201,MALegalHolidays)","v":26},18,8,"2013-04-04","2013-09-11",{"$f":"NETWORKDAYS(N201,O201,MALegalHolidays)","v":110},84,26,"2013-09-20","2013-10-11",{"$f":"NETWORKDAYS(S201,T201,MALegalHolidays)","v":16},0,16,null," ",null,null," ",null,null,null,null," ",null,null,null,null," ","2013-12-05",null,"2013-06-01","Yes","EXP",null,null,null,null,null," ",null,null,null,"New option (option 2) submitted.  Received incremental application fee 8/13/13.  Supplemental Review completed.  Agreement's out for signature.  Interconnecting Customer in liquidation.  On hold while Customer seeks new developer. Notice sent to all parties, no response. Application withdrawn 6/27/14."]
[null,"WMECO","Sunderland","6A412-2013","01375",349.5,"Solar","18G3","2013-02-27","2013-04-01",{"$f":"NETWORKDAYS(I202,J202,MALegalHolidays)","v":24},16,8,"2013-04-02","2013-09-11",{"$f":"NETWORKDAYS(N202,O202,MALegalHolidays)","v":112},85,27,"2013-10-15","2013-11-12",{"$f":"NETWORKDAYS(S202,T202,MALegalHolidays)","v":20},0,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-12-05",null,"2013-06-01","Yes","STD",null,null,null,null,null," ",null,null,null,"New option (option 2) submitted for smaller size.  Application was on hold due to delay in application 6A411-2013.  Applications are on the same circuit.  Supplemental Review completed.  Agreement's out for signature.  Interconnecting Customer in liquidation.  On hold while Customer seeks new developer. Notice sent to all parties, no response. Application withdrawn 6/27/14."]
[null,"WMECO","Pittsfield","6B265-2013","01201",9.89,"Solar","30BNW_1","2013-03-14","2013-03-28",{"$f":"NETWORKDAYS(I203,J203,MALegalHolidays)","v":11},0,11,"2013-03-29","2013-07-02",{"$f":"NETWORKDAYS(N203,O203,MALegalHolidays)","v":65},8,57,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-08-01",null,"2013-05-09","TBD","STD",null,null,null,null,null," ",null,null,"2013-10-25","Received Comletion Documents.  Need updated Witness Test Procedure to schedule Witness Test."]
[null,"WMECO","Hadley","6A415-2013","01035",833,"Solar","18G4","2013-03-18","2013-06-18",{"$f":"NETWORKDAYS(I204,J204,MALegalHolidays)","v":64},21,43,"2013-07-11","2013-07-12",{"$f":"NETWORKDAYS(N204,O204,MALegalHolidays)","v":2},0,2,null,null,null,null," ","2013-07-12","2013-07-12",{"$f":"NETWORKDAYS(X204,Y204,MALegalHolidays)","v":1},0,1,"2013-10-07","2013-11-25",{"$f":"NETWORKDAYS(AC204,AD204,MALegalHolidays)","v":34},0,34,"2014-03-04","2014-04-14",{"$f":"NETWORKDAYS(AH204,AI204,MALegalHolidays)","v":29},3,26,"2014-05-07",null,"2013-10-15","Yes","STD","2014-09-15","2014-09-15",null,{"$f":"NETWORKDAYS(AS204,AT204,MALegalHolidays)","v":-29892},null," ","2014-10-21","2014-10-30","2014-10-30","May be third party owned.  Will not be third party owned per Customer.  Waiting for Customer to revise drawings.  Customer wants the Impact Study to inform them of the size project that can be installed without significant system upgrades.Waiting for Customer to supply revised info. Interconnecting Customer wants Impact Study to study 833, 500 and 333 kW projects or other size that will not require significant upgrades for other than the interconnection service.  If  Impact Study determines project size other than the original submitted inverters, the Interconneting Customer will need to submit new application package and fee and the DG process starts over. Sent Joint Impact Study to Interconnecting Customer 10/2/13 for 6A405-2013 & 6A415-2013 total cost $33,000. Received Impact Study agreement and first check.  Sent Impact Study Report and Detailed Study Agreement to Customer. Sent Early ISA to Customer for signature 12/23/13, recieved signed Early ISA from Customer 12/28/13.  Detailed Study agreement was sent out for signature, Customer has not returned signed agreement.  Customer wanted to interconnect this and the 6A405-2013 project at one interconnection point, WMECO sent them an estimate for this design, the Customer has not decided whether to go with one interconnection point or to only build this 6A415-2013 project.  The Customer has signed the Detailed Study Agreement and sent in all monies to write work orders and design DTT for the Huntington Rd project only as originally submitted.  Work orders have been written, need to give Customer Exhibit G with plus/minus 10%. Customer changed the name from BueWave Capital to BWC Origination Huntington Road, LLC.  Sent out Draft IA for review, Customer sent it back with name change.  Talked with Customer they are not going to change the name.  Need revised insurance certificate with BWC Origination name.  Sent out IA for signature.  Revised insurance certificate received.  Verizon scheduled to set poles.  WMECO technician has to go out and restake pole locates for interconnection service because they were knocked down.  Construction of interconnection service has started.  Interconnection service finished, transfer trip FDDA lines need to be installed by Verizon, Customer did not order the FDDA lines until early October, FDDA lines installed, transfer trip commissioned, Witness Test scheduled.  Customer is on line."]
[null,"WMECO","West Springfield","6S165-2013","01089",79.8,"Solar","21N5","2013-03-18","2013-04-25",{"$f":"NETWORKDAYS(I205,J205,MALegalHolidays)","v":28},22,6,"2013-04-26",null,{"$f":"NETWORKDAYS(N205,O205,MALegalHolidays)","v":-29549},38," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-08-06",null,"2013-04-25","TBD","EXP",null,null,null,null,null," ","2013-11-13","2013-12-10","2013-12-10","on line"]
[null,"WMECO","Hadley","6A418-2013","01035",57.405000000000001,"Solar","17K5","2013-04-09","2013-06-12",{"$f":"NETWORKDAYS(I206,J206,MALegalHolidays)","v":45},37,8,"2013-06-13","2013-08-06",{"$f":"NETWORKDAYS(N206,O206,MALegalHolidays)","v":37},28,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-08-09",null,"2013-07-22","TBD","EXP",null,null,null,null,null," ","2013-11-13","2013-12-12","2013-12-31","IA on file.  Completed successful Witness Test.  Changes were made to the design.  Need updated documents before Approval to Operate."]
[null,"WMECO","Greenfield","6F447-2013","01301",300,"Solar","21C1","2013-04-09","2013-05-07",{"$f":"NETWORKDAYS(I207,J207,MALegalHolidays)","v":20},null,20,"2013-05-08","2013-05-23",{"$f":"NETWORKDAYS(N207,O207,MALegalHolidays)","v":12},null,12,"2013-06-03","2013-06-26",{"$f":"NETWORKDAYS(S207,T207,MALegalHolidays)","v":17},0,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-07-15",null,"not supplied","TBD","EXP",null,null,null,null,null," ",null,null,null,"App complete.  Scoping Mtg. held.  Supplemental Review complete.  Received Signed IA. Need Completion Documents. **** I.C. cancelled *****"]
[null,"WMECO","Amherst","6A419-2013","01002",100,"Solar","18G4","2013-04-16","2013-04-30",{"$f":"NETWORKDAYS(I208,J208,MALegalHolidays)","v":11},null,11,"2013-05-01","2013-06-06",{"$f":"NETWORKDAYS(N208,O208,MALegalHolidays)","v":26},2,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-06-06",null,"2013-05-01","TBD","EXP",null,null,null,null,null," ","2013-10-15","2013-10-22","2013-10-22","Scheduled witness Test on 10/15/13. Performed Witness Test on 10/18/13, the inverter failed on start up.  Needs to schedule an addtional Witness Test.   Witness test dates = 10/18/2013 & 10/22/2013"]
[null,"WMECO","Otis","6B269-2013","01253",1800,"Wind","19J6","2013-04-19","2013-05-02",{"$f":"NETWORKDAYS(I209,J209,MALegalHolidays)","v":10},0,10,null,null,null,null," ",null,null,null,null," ","2013-05-03","2014-02-18",{"$f":"NETWORKDAYS(X209,Y209,MALegalHolidays)","v":196},166,30,"2014-04-10","2014-07-01",{"$f":"NETWORKDAYS(AC209,AD209,MALegalHolidays)","v":56},3,53,null,null,null,null," ",null,null,"2013-11-13","Yes","COMP",null,null,null,null,null," ",null,null,null,"Scoping Mtg held.  Need info from Interconnecting Customer. Off hold.  Additional option information received.  Impact Study Agreement out for siganture 3/5. Signed agreement and payment received 4/9.  Impact Study report sent.  Detaled Study agreement sent.  Interconnecting Customer inidiated ADR.  Clock is stopped unitl ADR process completed. cancelled"]
[null,"WMECO","Peru","6B277-2013","01235",16500,"Wind","18C2","2013-05-06","2013-05-23",{"$f":"NETWORKDAYS(I210,J210,MALegalHolidays)","v":14},2,12,null,null,null,null," ",null,null,null,null," ","2013-05-24","2013-09-06",{"$f":"NETWORKDAYS(X210,Y210,MALegalHolidays)","v":72},47,25,null,null,null,29," ",null,null,null,null," ",null,null,"not supplied","Yes","COMP",null,null,null,null,null," ",null,null,null,"Application complete.  Held Scoping Mtg.  Interconnecting Customer submitted additional options.  Impact Study Agreemet out for Signature.  Interconnecting Customer timelines expired on execution of Impact Study Agrement.  Application withdrawn per the Tariff procedure."]
[null,"WMECO","Lanesborough","6B280-2013","01237",20.21,"Solar","15E1","2013-05-13","2013-11-12",{"$f":"NETWORKDAYS(I211,J211,MALegalHolidays)","v":126},120,6,"2013-10-29","2013-10-29",{"$f":"NETWORKDAYS(N211,O211,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-11-12",null,"2013-07-10","TBD","EXP",null,null,null,null,null," ","2014-03-28","2014-04-01","2014-04-01","new application. Have not heard from Customer as of 8/21/13. Waiting for service upgrades to be done. Devloper called 9/17/13 project is moving forward, Customer needs to sign lease for solar facility. Sent Drat Exhibit G & H.  Rcvd stamped one line.  Rcvd initial payment for system modifications. Sent Exhibit G & H for signature.  Received signed Exhibit G.  Rcvd Exhibit H. The initial check for system modifications was returned to Int Customer (outdated check becuase of project delay). On hold in November. Rcvd new check for system modifications in February.  System modification completed, completion docs recvd, Witness Test performed, On line."]
[null,"WMECO","Amherst","6A449-2013","01002",19.989999999999998,"Solar","17K7","2013-06-26","2013-07-03",{"$f":"NETWORKDAYS(I212,J212,MALegalHolidays)","v":6},0,6,"2013-07-05","2013-09-05",{"$f":"NETWORKDAYS(N212,O212,MALegalHolidays)","v":44},21,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-10-07",null,"2013-09-01","TBD","EXP",null,null,null,null,null," ","2013-10-28","2013-10-29","2013-11-18","Held site visit.  WMECO sent customer estimate for construction required for option 2 (customer has two options, 19.99 kW and 21.395 kW).  As of 9/5/2013 Interconnecting Customer is moving forward with 19.99 kW option.  Received IA.  System Online"]
[null,"WMECO","Southwick","6S195-2013","01077",40,"Hydro","29A5","2013-07-09","2013-07-30",{"$f":"NETWORKDAYS(I213,J213,MALegalHolidays)","v":16},8,8,"2013-07-31",null,{"$f":"NETWORKDAYS(N213,O213,MALegalHolidays)","v":-29614},17," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2013-11-01",null,"EXP",null,null,null,null,null," ",null,null,null,"Application complete. Held Scoping Meeting.  Interconnecting Customer may cancel application and resubmit new design.  Interconnecting Customer requested an extension. Cancelled"]
[null,"WMECO","Conway","6F473-2013","01341",19.989999999999998,"Solar","38A1","2013-07-15","2013-07-24",{"$f":"NETWORKDAYS(I214,J214,MALegalHolidays)","v":8},0,8,"2013-07-25","2013-09-19",{"$f":"NETWORKDAYS(N214,O214,MALegalHolidays)","v":40},9,31,"2013-09-26","2013-11-04",{"$f":"NETWORKDAYS(S214,T214,MALegalHolidays)","v":27},0,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-11-15",null,"2013-08-01",null,"EXP",null,null,null,null,null," ","2013-12-10","2013-12-13","2013-12-20","Application Complete.  Supplemental Review Complete.  Construction Complete.  Online."]
[null,"WMECO","Southwick","6S200-2013","01077",3340,"Solar","29A1","2013-07-18","2013-08-07",{"$f":"NETWORKDAYS(I215,J215,MALegalHolidays)","v":15},9,6,null,null,null,null," ",null,null,null,null," ","2013-08-08","2013-10-15",{"$f":"NETWORKDAYS(X215,Y215,MALegalHolidays)","v":47},27,20,"2013-12-13","2014-05-01",{"$f":"NETWORKDAYS(AC215,AD215,MALegalHolidays)","v":94},0,94,"2014-05-05","2014-11-05",{"$f":"NETWORKDAYS(AH215,AI215,MALegalHolidays)","v":128},12,116,"2014-05-01",null,"2014-08-01",null,"STD",null,"2015-03-09","2015-03-20",{"$f":"NETWORKDAYS(AS215,AT215,MALegalHolidays)","v":9},null,9,"2015-03-09","2015-03-30","2015-03-30","App not complete.  Need Information from Interconnecting Customer. Conf call with Customer 9/24/13, Customer needs to decide whether to move forward with existing aproject or cancel and resubmit different size project. Customer informed WMECO on 9/26/13 that the project size will be decreased to 3340 kW (two 1670 kW inverters).  They will send send early next week as an option 1 to the original project. Customer sent Option1 app package for 3340 kW on 10/2/13. Sent Impact Study Agreement to Customer.  Impact Study complete, Iso notification complete.  Project was sold to another developer, names were changed on agreements.  Developer sent in all system modification monies, Construction will start January 2015.  Insurance cert received, sent revised attachment 3 for system upgrades due to this project moving forward prior to the Customer in the interconnection queue, recevied initialed attachment 3 and check for addional modifications.  Project is on hold due to a prject ahead of this ion the DG queue.  Substation construction scheduled for February, line constructio scheudled for March, Witness Test scheduled for end of March.  Revised application and schedule Z submitted with the Town of West Springfield info, project is now third party owned.  Electric account was established. Received completion docs.  Some revisions required, Received revised Completion docs, Completion docs reviewed - O.K. Project requires Land Owner agreement.  Interconnection service and substation work and transfer trip completed and comissioned. Rcvd signed Exhbit H and landowner agreement.  Witness Test performed, Project on line."]
[null,"WMECO","Richmond","6B301-2013","01254",18,"Solar","30B7","2013-08-28","2013-10-07",{"$f":"NETWORKDAYS(I216,J216,MALegalHolidays)","v":28},20,8,"2013-10-08","2013-11-20",{"$f":"NETWORKDAYS(N216,O216,MALegalHolidays)","v":30},19,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-11-20",null,"2013-09-01",null,"EXP",null,null,null,null,null," ","2013-12-13","2013-12-18","2013-12-31","on line"]
[null,"WMECO","Springfield","6S208-2013","01129",333,"Solar","20A35","2013-08-29","2013-09-20",{"$f":"NETWORKDAYS(I217,J217,MALegalHolidays)","v":16},12,4,"2013-10-31","2013-10-31",{"$f":"NETWORKDAYS(N217,O217,MALegalHolidays)","v":1},0,1,"2013-12-02","2014-01-06",{"$f":"NETWORKDAYS(S217,T217,MALegalHolidays)","v":24},0,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-02-06",null,"2014-06-30","TBD","EXP",null,null,null,null,null," ",null,null,null,"Application not complete.  Information requested.  Customer sent revised application for third party on 11/20/13.  Suplemental review finished.  Drfat Exhibit G & H sent out for review.  Sent out Exhibit G & H for signature. Received signed Exhibit G & H.  Solar facility will not be built until 2nd or 3rd quarter 2014 per Interconnecting Customer.  Customer wants to change inverters, sent them an e-mail informing them that they have a signed agreement and cannot change inverters at this time.  They will need to submit a new application with fee and new technical information. cancelled"]
[null,"WMECO","Pittsfield","6B316-2013","01201",600,"Diesel","30B4","2013-10-01","2013-11-05",{"$f":"NETWORKDAYS(I218,J218,MALegalHolidays)","v":25},13,12,"2013-11-05","2014-01-13",{"$f":"NETWORKDAYS(N218,O218,MALegalHolidays)","v":45},45,0,"2014-01-17","2014-04-11",{"$f":"NETWORKDAYS(S218,T218,MALegalHolidays)","v":58},44,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-05-20",null,"2013-10-24",null,"EXP",null,null,null,null,null," ",null,null,"2018-04-25","App complete, supplemental review started, waiting for revised info on watch dog timer, timer is integral part of transfer switch, Protection informed us that timer needs to be in addition to the transfer swtch and cannot be integral.  Customer sent revised drawing with additional discreet watch dog timer.  Protection sent final comments.  Drawings and design O.K.  Sent Draft IA to Customer for review. Sent e-mail 2nd request to review Draft Exhibit G. Recvd comments, made changes, sent Executable Exhibit G to Customer.  Rceived signed Exhibit G from Customer.  Waiting to schedule Witness Test."]
[null,"WMECO","Southwick","6S217-2013","01077",40,"Hydro","29A2","2013-10-21","2013-11-05",{"$f":"NETWORKDAYS(I219,J219,MALegalHolidays)","v":12},1,11,"2013-11-06","2013-12-04",{"$f":"NETWORKDAYS(N219,O219,MALegalHolidays)","v":18},2,16,"2013-12-09","2014-01-30",{"$f":"NETWORKDAYS(S219,T219,MALegalHolidays)","v":36},20,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-02-06",null,"2014-03-28",null,"EXP",null,null,null,null,null," ","2015-11-16","2015-11-30","2015-11-30","Supplemental Review Comnplete.  Executed IA received.  Received relay test results.  Ned Witness Test procedure and to schedule Witness Test with I.C."]
[null,"WMECO","Greenfield","6F508-2013","01301",29.984999999999999,"Solar","22B2","2013-10-25","2013-11-05",{"$f":"NETWORKDAYS(I220,J220,MALegalHolidays)","v":8},0,8,"2013-11-05","2013-11-05",{"$f":"NETWORKDAYS(N220,O220,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-01-03",null,"ASAP",null,"EXP",null,null,null,null,null," ","2014-04-14","2014-04-15","2014-04-15","Sent app complete info, initial review done, sent DRAFT Exhibit G for signature, ordered Net meter. Exhibig G received.  Received completion docs, scheduled DG meter set.  Confirmed meter set.Scheduled Witness Test. Witness test successful, Customer on line,"]
[null,"WMECO","Hadley","6A496-2013","01305",1950,"Solar","17K1","2013-10-28","2014-01-17",{"$f":"NETWORKDAYS(I221,J221,MALegalHolidays)","v":55},10,45,null,null,null,null," ",null,null,null,null," ","2014-01-21","2014-03-10",{"$f":"NETWORKDAYS(X221,Y221,MALegalHolidays)","v":34},21,13,"2014-04-09","2014-06-30",{"$f":"NETWORKDAYS(AC221,AD221,MALegalHolidays)","v":56},0,56,"2014-12-09","2015-05-27",{"$f":"NETWORKDAYS(AH221,AI221,MALegalHolidays)","v":115},97,18,"2015-07-21",null,null,null,"STD",null,null,null,null,null," ",null,"2016-10-20","2016-10-25","App Complete.  Scoping Meeting Held.  Need Impact Study Agreement.  Impact Study Agreement out for signature on 3/12.  Executed Agreement received 3/12, payment received 4/8.  In Impact Study.  Impact Study results meeting held. I.C. reviewed alternate DTT scheme.   I.C. requested Detailed Study payment plan.  Received signed Exhibit F and payment.  Site visit held.   Interconnecting Customer reviewed and approved Exhibit G language.  On hold for ISO RC.  Project was not included on 4/21 meeting agenda despite being submitted correclty before the deadline for that meeting.  ISO review complete.  Need clarification on ABB/Power One inverters."]
[null,"WMECO","Greenfield","6F513-2013","01301",16,"Solar","22B7","2013-10-29","2013-11-05",{"$f":"NETWORKDAYS(I222,J222,MALegalHolidays)","v":6},3,3,"2013-11-07","2013-11-12",{"$f":"NETWORKDAYS(N222,O222,MALegalHolidays)","v":3},0,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2013-11-18",null,"2013-11-10",null,"EXP",null,null,null,null,null," ","2013-12-18","2013-12-23","2014-01-17","Sent app complete info, initial review done, sent DRAFT Exhibits G & H, ordered Net meter.  Witness Test passed, Need Mass ACA Reservied.  Recevd Mass ACA Reserved Approval to operate sent to Customer. On Line."]
[null,"WMECO","Dalton","6B345-2013","01226",1650,"Solar","19A2 or 19A3","2013-12-03","2014-02-28",{"$f":"NETWORKDAYS(I223,J223,MALegalHolidays)","v":60},57,3,null,null,null,null," ",null,null,null,null," ","2014-03-03","2014-04-10",{"$f":"NETWORKDAYS(X223,Y223,MALegalHolidays)","v":28},22,6,"2014-05-12",null,{"$f":"NETWORKDAYS(AC223,AD223,MALegalHolidays)","v":-29806},11," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"Options received.  Application Complete.  Scoping meeting held.  In Impact Study.  \"Preliminary\" report shared (for the purpose of potential alternate DTT solution).  Call held with I.C.  Cancelled by I.C."]
[null,"WMECO","Pittsfield","6B359-2014","01201",16.5,"Solar","30B7","2014-01-06","2014-02-12",{"$f":"NETWORKDAYS(I224,J224,MALegalHolidays)","v":27},15,12,"2014-02-12","2014-02-12",{"$f":"NETWORKDAYS(N224,O224,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-02-18",null,"2014-02-04",null,"EXP",null,null,null,null,null," ","2014-04-17","2014-04-18","2014-04-18","need additional info from Customer.  Rcvd additional info.  Sent out Draft Exhibit G for review.  Sent out Exhibit G for signature.  Rcvd comp docs, need additional info.  Rcvd additional info.  Ordered meter set. Scheduled Witness Test. On line."]
[null,"WMECO","Dalton","6B364-2014","01226",1250,"Solar","19A2 or 19A3","2014-01-14","2014-02-28",{"$f":"NETWORKDAYS(I225,J225,MALegalHolidays)","v":32},16,16,null,null,null,null," ",null,null,null,null," ","2014-03-03","2014-04-10",{"$f":"NETWORKDAYS(X225,Y225,MALegalHolidays)","v":28},22,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"Options received.  Application Complete.  Scoping meeting held.  Impact Study agreement and payment received.  Queued behind 6B345-2013. Cancelled by I.C."]
[null,"WMECO","West Springfield","6S240-2014","01089",1950,"Solar","16C12","2014-01-17","2014-03-12",{"$f":"NETWORKDAYS(I226,J226,MALegalHolidays)","v":37},22,15,null,null,null,null," ",null,null,null,null," ","2014-03-13","2014-06-12",{"$f":"NETWORKDAYS(X226,Y226,MALegalHolidays)","v":63},56,7,"2014-07-18","2014-12-05",{"$f":"NETWORKDAYS(AC226,AD226,MALegalHolidays)","v":97},90,7,"2015-04-21","2015-11-20",{"$f":"NETWORKDAYS(AH226,AI226,MALegalHolidays)","v":148},70,78,"2015-11-30",null,"2014-10-01",null,"COMP",null,null,null,null,null," ","2017-03-14","2017-03-22","2017-03-30","Application Complete.  Screening email sent. In Impact Study.  Impact Study time frame was extended to 100 business days per mutual agreement.  Received Detailed Study Agreement.  Received payment. I.C. requested early ISA. In D.S. but on hold.  Need updated drawings from I.C. Need ISO RC.  Site visit held.  Need to straigten out issues with property lines."]
[null,"WMECO","Springfield","6S244-2014","01111",4000,"Diesel","5J14","2014-02-04","2014-02-24",{"$f":"NETWORKDAYS(I227,J227,MALegalHolidays)","v":14},13,1,"2014-02-25","2014-03-19",{"$f":"NETWORKDAYS(N227,O227,MALegalHolidays)","v":16},0,16,"2014-04-22","2014-05-12",{"$f":"NETWORKDAYS(S227,T227,MALegalHolidays)","v":15},10,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-07-02",null,"2014-06-01",null,"EXP",null,null,null,null,null," ","2014-11-13","2014-11-30","2014-12-01","Application complete, Initial review done.  Supplemental review started.  Need revised one line with neutral grnding resistors.  Sent protection comments to Customer, need revised 32R setting, received revised info, sent to Protection to review. Sent out Draft IA for comment.   Sent out IA for signature.  Received signed agreement.  Need insurance cert to include these two generators, sent e-mail to Customer.   Waiting on Customer for relay test results and final doucumentation to peform a Witness Test.  Witness Test originally scheduled for 11/23/14 but Customer rescheduled for 11/30/14.  Witness Test performed.  Generaotrs on line."]
[null,"WMECO","Lee","6B369-2014","01238",15.265000000000001,"Solar","16B5","2014-02-05","2014-02-19",{"$f":"NETWORKDAYS(I228,J228,MALegalHolidays)","v":10},6,4,"2014-02-20",null,{"$f":"NETWORKDAYS(N228,O228,MALegalHolidays)","v":-29751},25," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-03-28",null,"EXP",null,null,null,null,null," ",null,null,null,"Application Complete.  Screening email sent 2/25.  WMECO needs information. Customer cancelled project."]
[null,"WMECO","Lee","6B370-2014","01238",17.324999999999999,"Solar","16B5","2014-02-05","2014-02-25",{"$f":"NETWORKDAYS(I229,J229,MALegalHolidays)","v":14},10,4,"2014-02-26","2014-06-23",{"$f":"NETWORKDAYS(N229,O229,MALegalHolidays)","v":80},71,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-08-05",null,"2014-01-24",null,"EXP",null,null,null,null,null," ","2016-02-10","2016-02-16","2016-02-16","Application Complete.  Screening email sent 3/12.  WMECO needs information.  Construction required.  Site visit held and estimate provided.  IA fully executed."]
[null,"WMECO","Conway","6F542-2014","01341",16.125,"Solar","38A1","2014-02-24","2014-04-10",{"$f":"NETWORKDAYS(I230,J230,MALegalHolidays)","v":33},25,8,"2014-04-11","2014-04-15",{"$f":"NETWORKDAYS(N230,O230,MALegalHolidays)","v":3},1,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-04-15",null,"2014-03-21",null,"EXP",null,null,null,null,null," ","2014-04-22","2014-04-24","2014-04-24","on line"]
[null,"WMECO","Amherst","6A540-2014","01002",24,"Solar","17K6","2014-02-28","2014-03-12",{"$f":"NETWORKDAYS(I231,J231,MALegalHolidays)","v":9},8,1,"2014-03-13","2014-05-01",{"$f":"NETWORKDAYS(N231,O231,MALegalHolidays)","v":34},14,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-05-07",null,"2014-04-01",null,"EXP",null,null,null,null,null," ","2014-05-30","2014-06-04","2014-06-04","Existing system on property moved to PPS comensation.  Online"]
[null,"WMECO","Lee","6B383-2014","01238",19.8,"Solar","16B5","2014-03-03","2014-03-19",{"$f":"NETWORKDAYS(I232,J232,MALegalHolidays)","v":12},7,5,"2014-03-20","2014-05-20",{"$f":"NETWORKDAYS(N232,O232,MALegalHolidays)","v":43},6,37,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-06-10",null,"2014-04-15",null,"EXP",null,null,null,null,null," ","2014-09-12","2014-09-15","2014-09-30","On line 9/30/14"]
[null,"WMECO","West Hatfield","6A543-2014","01088",500,"Solar","18G5","2014-03-06",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-06-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Longmeadow","6S254-2014","01106",12,"Solar","22H12","2014-03-11",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-05-30",null,"EXP",null,null,null,null,null," ",null,null,null,"Project cancelled by applicant."]
[null,"WMECO","Whately","6A564-2014","01093",22.8,"Solar","18G6","2014-04-14","2014-04-23",{"$f":"NETWORKDAYS(I235,J235,MALegalHolidays)","v":7},0,7,"2014-05-05","2014-05-21",{"$f":"NETWORKDAYS(N235,O235,MALegalHolidays)","v":13},7,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-05-21",null,"2014-05-01",null,"EXP",null,null,null,null,null," ","2014-08-05","2014-08-06","2014-08-06","Reveiwed project, needed ac solar disconnect location reviewed by meter supervisor. Location O.K., Sent out Draft Exhibit G for review. Need revised one line with text for combiner panel \"only generation circutis\" recevied revised one line. Need Int Customer name and address on 1-line, received revised one line, Sent out Exhibit G for siganture.  Received signed Exhibit G from Customer.  Witness test performed, Customer on line."]
[null,"WMECO","Springfield","6S312-2014","01119",336,"Solar","20A33","2014-06-11","2014-07-03",{"$f":"NETWORKDAYS(I236,J236,MALegalHolidays)","v":16},6,10,"2014-07-07","2015-01-20",{"$f":"NETWORKDAYS(N236,O236,MALegalHolidays)","v":135},134,1,"2015-01-21","2015-02-11",{"$f":"NETWORKDAYS(S236,T236,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-27",null,"2014-11-17",null,"EXP",null,null,null,null,null," ",null,null,null,"Application is complete, started Initial  Review, sent out comments to Custoemr, One line drawing needs revision before the Supplemental Review can be performed.  It is difficult to reach the Custoerm by phone in Florida as the phone lines are frequently busy and I cannot get through. waiting for stamped revised one line. Sent Supplemental Review for signature, Int Cust will send stamped drawing ASAP.  WMECO rcvd siganed agreement and check, Interconnecting Customer requested an extension to get WMECO information.  WMECO granted the extension as part of the initial review stage, expires 1/20/15.  Supplemental Review under way.  Supplemenatl Review Report sent to Interconnecitng Customer and Customer.  IStarted IAs, info required, Rvcd partial info, Rcvd completed info, IAs sent out for signature.  Withdrawn after no contact from applicants and none of the contact information is valid. withdrawn"]
[null,"WMECO","Pittsfield","6B409-2014","01201",266,"Solar","15E2","2014-06-23","2014-07-22",{"$f":"NETWORKDAYS(I237,J237,MALegalHolidays)","v":21},18,3,"2014-07-23","2015-05-06",{"$f":"NETWORKDAYS(N237,O237,MALegalHolidays)","v":196},192,4,"2015-05-21","2015-06-17",{"$f":"NETWORKDAYS(S237,T237,MALegalHolidays)","v":18},0,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-08-14",null,"2014-08-25",null,"EXP",null,null,null,null,null," ","2015-12-17","2016-04-21","2016-04-21","app not complete need inverter cut sheet, rcvd cut sheet, Application complete, started initial review, sent out comments info required, held scoping meeting 7/30 sent out minutes, drawings need to be revised, waiting for revised application that includes the information of the two historical diesel generators and the one line to include the relay settings of the two diesel generators.  Sent the Supplemental Review agreements to the Customer, have not received the signed agreement nor check.  Still have not rcvd application with diesel generator information nor 1-line with diesel generator settings.  Sent e-mail that they have 10 days to send info. Rcvd revised app and 1-line with diesel gen info.  Need to review. started Supplemental Review, info required from Customer, rcvd info finsihed Supplemental review, sent results to Customer.  Watch dog timers required for each existing diesel generator.  Conf call with Customer to explain existing gen issues.  Revised drawing showing watch Dog timers required for IA to be sent out.  W D Timers required to be installed prior to sched Witness Test. Witness Test performed for solar facility, Solar Customer is on line. Customer required to install Watch Dog Time for the two closed transition diesel generators.  Witness test scheduled for Watch Dog timer.  Witness test failed.  A second Witness test is scheduled for the Watch Dog timer, Witness test  successful.  Diesel generators are on line."]
[null,"WMECO","Springfield","6S334-2014","01129",278.39999999999998,"Solar","20A35","2014-06-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-10-31",null,"EXP",null,null,null,null,null," ",null,null,null,"Project cancelled by customer."]
[null,"WMECO","Windsor","6B413-2014","01270",24,"Solar","18C1","2014-07-10","2014-07-22",{"$f":"NETWORKDAYS(I239,J239,MALegalHolidays)","v":9},2,7,"2014-08-21","2014-09-03",{"$f":"NETWORKDAYS(N239,O239,MALegalHolidays)","v":9},8,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-09-05",null,"2014-11-01",null,"EXP",null,null,null,null,null," ","2014-12-09","2014-12-16","2014-12-16","app not complete, need app fee, app fee received, app complete, initial review started need revised one line & site plan.  Received revised info. Approval to install.  Received completion docs, need inspaector requirement in WR.  Inspector requirement completed.  Scheduled meter set. Witness Test scheduled, Witness Test performed, successful, Customer is on line. "]
[null,"WMECO","Russell","6A681-2014","01071",49,"Solar","19J2","2014-07-16","2014-09-05",{"$f":"NETWORKDAYS(I240,J240,MALegalHolidays)","v":37},30,7,"2014-09-12","2014-12-03",{"$f":"NETWORKDAYS(N240,O240,MALegalHolidays)","v":56},50,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-12-16",null,"2014-09-26",null,"EXP",null,null,null,null,null," ","2015-10-02","2015-10-06","2015-10-06","Application complete, Initial review done, comments sent to Customer, project requires system modifications, Customer recvd WR #, technician needs to make site visit.  Technician is writing up work order for system upgrades.  Technician finished writing system mod work order.  Exhibit G to be written and sent to Customer.  Project on Customer Hold due to Customer land  permitting issues.  WMECO has notification that the Customer would like to procedd with the 49 kW project, sent DRAFT Exhibit G to Customer for review.  Sent Exhibit G for signature.  Still need system modification upgrade monies.  Rcvd system modification monies, scheduled modifications.  Modifications completed.  Waiting for system to be installed. rcvd some comp docs, need inverter setting sheets, rvcd setting sheets, scheduled Wit Test, performed wit test, costomer on line."]
[null,"WMECO","Hadley","6A682-2014","01035",24.98,"Solar","18G4","2014-07-16","2014-08-26",{"$f":"NETWORKDAYS(I241,J241,MALegalHolidays)","v":30},26,4,"2014-08-27","2014-09-04",{"$f":"NETWORKDAYS(N241,O241,MALegalHolidays)","v":6},2,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-09-04",null,"not supplied",null,"EXP",null,null,null,null,null," ","2014-12-22","2014-12-22","2014-12-22","app complete, initial review, site address incorrect, insytaller send town assessor records, Customer Care changed site address in WMECO records, new one line requested/received, sent out IA for signature, rcvd signed IA, rcvd wit test docs, schd wit test, Customer on line."]
[null,"WMECO","Greenfield","6F594-2014","01301",600,"Diesel","22B7","2014-07-24","2014-08-26",{"$f":"NETWORKDAYS(I242,J242,MALegalHolidays)","v":24},23,1,"2014-08-26","2014-12-03",{"$f":"NETWORKDAYS(N242,O242,MALegalHolidays)","v":68},54,14,"2014-12-03","2014-12-29",{"$f":"NETWORKDAYS(S242,T242,MALegalHolidays)","v":18},0,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-01-07",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2018-04-25","Application not complete, Application Complete Checklist is required.  Application complete, Supplemental Review required, Supplemental review started, Supplemental Review complete, need to send Exhibit G, sent out Exhibit G for signature.  Rcvd signed Exhibit G and insurance cert.  "]
[null,"WMECO","Springfield","6S386-2014","01103",42,"Solar","8CNW_1","2014-08-04","2014-08-25",{"$f":"NETWORKDAYS(I243,J243,MALegalHolidays)","v":16},15,1,"2014-08-26","2014-09-29",{"$f":"NETWORKDAYS(N243,O243,MALegalHolidays)","v":24},22,2,null,null,null,17," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-08-01",null,"STD",null,null,null,null,null," ",null,null,null,"Application not complete, Application Complete Checklist is required, recvd app complete checklist, initial review sent ot Customer, waiting for required info., Customer is located on the area network. Cancelled"]
[null,"WMECO","West Springfield","6S468-2014","01089",200,"Solar","16C12","2014-08-25",null,null,165," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-08-01",null,"EXP",null,null,null,null,null," ",null,null,null,"The Customer names on the application do not match the WMECO electric accounts.  The Installer is checking with the Customer regarding this issue.  The meter department field checked the electric service at the site so that comments can be sent to the installer on how to revise the one line drawing.  sent an e-mail to the installer asking if the project is moving forward, have gotten no reply.  Interconnecting Customer requested an extension, expires 2/5/15.   Received drawings prior to expiration of extension.  Reviewed for completeness, app not complete.  Project withdrawn, sent e-mail to installer and customer. withdrawn"]
[null,"WMECO","Pittsfield","6B427-2014","01201",30.25,"Solar","30B4","2014-08-26","2014-09-18",{"$f":"NETWORKDAYS(I245,J245,MALegalHolidays)","v":17},14,3,"2014-09-19","2014-09-22",{"$f":"NETWORKDAYS(N245,O245,MALegalHolidays)","v":2},1,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-09-22",null,"2014-12-01",null,"EXP",null,null,null,null,null," ","2015-01-29","2015-02-04","2015-02-04","Application received, initial  review performed, three phase service with single phase inverters, need phase loss relay,  meter ordered, revised drawing required, approval to install. Have not rcvd the signed agreement for the Interconnecting Customer.   Rvdc signed agreement.  Rcvd completion docs, need revised witness test procedure.  Rcvd revised witness Test procedure, scheduled Witness Test.  Performed Witness Test.  Customer on line."]
[null,"WMECO","Chesterfield","6F652-2014","01012",22,"Solar","18K3","2014-09-15","2014-10-15",{"$f":"NETWORKDAYS(I246,J246,MALegalHolidays)","v":22},20,2,"2014-10-16","2014-11-05",{"$f":"NETWORKDAYS(N246,O246,MALegalHolidays)","v":15},8,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-11-12",null,"Q4 2014",null,"EXP",null,null,null,null,null," ","2015-01-21","2015-01-26","2015-01-26","Application complete, started initial review, made site visit to check tranformer, sent e-mail to installer asking for revised print to show subpanel in small horse barn and that the Customer is requesting a site visit.  Resent e-mail to installer that the Custmer wants a site visit.  Customer changed DC-STC number.  Sent out Draft IA, waiting for stamped one line to send IA out for signature.  In the interest of time the Exhibit G was sent to the Customer without the stamped one line, which will be sent at a later date.  stamped 1-line rcvd, inspector requirement completed, waiting for completion docs to schedule Witness Test.  Rcvd  COC and pictures, need Witness Test procedure.  Rcvd Witness Test procedure, scheduled Witness Test, performed Witness Test. Customer is on line."]
[null,"WMECO","Pittsfield","6B436-2014","01201",499,"Solar","30B2","2014-09-25","2014-10-09",{"$f":"NETWORKDAYS(I247,J247,MALegalHolidays)","v":11},5,6,"2014-10-09","2014-10-15",{"$f":"NETWORKDAYS(N247,O247,MALegalHolidays)","v":4},3,1,"2014-10-16","2014-11-07",{"$f":"NETWORKDAYS(S247,T247,MALegalHolidays)","v":17},0,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-12-02",null,"2014-12-14",null,"EXP","2014-12-27","2014-12-30","2014-12-30",{"$f":"NETWORKDAYS(AS247,AT247,MALegalHolidays)","v":1},null,1,"2014-12-26","2014-12-31","2015-01-12","Application receved, application reviewed for Completeness - info required, Rcvd info, sent initial review to Customer, need Supplemental review, Customer asking WMECO to send Supplemental Review Agreement. Rcvd signed agreement and check.  WMECO internal conf call held.  Sent installer & Customer e-mail, info is required from them for the supplemental review.  Supplemental Review is underway.  The Supplemental Review report was sent to the Interconnecting Customer and Customer.  The Interconnecting Customer requested a name /entity for the project.   Info on how to process the name change was sent to the Int Cust.  Int Cust is required to take out a work request for system modifications but has not yet done this.  The project is on Customer Hold until the name change paper work is finalized and a work requist number is provided.  Work request was submitted, site visit was performed, work order was written, cost estimate was sent, Draft Exhibit G and H were sent for review, Executable Exhibit G and H were sent.  Signed Exhibit G was recevied by WMECO, system modifications are scheduled contingent upon Interconnecting Customer work to be completed. rcvd system modification monies, construction work scheduled, rcvd inspector requirement completion, construction work completed, witness Test scheduled, Witness Test performed,  need inverter setting sheets and cap allocation. Cap allocation recvd.  Rcvd inverter settting sheets, need PE stamped revised drawing with the correct inverter settings.  The Interconnecting Customer cannot get the drawing stamped until 1/19/15, they were given approval to operate on 1/12/15 but they have until 1/20/15 to send the PE stamped drawing.  In all of the confusion of this project the CoC and the inspector sign off was not recieved for the solar project prior to being given approval to operate.  An e-mail was sent to the Int Customer asking for these two items to be completed.  CoC was rcvd, still need electrical inspector sign off in WR."]
[null,"WMECO","Springfield","6S530-2014","01109",44.55,"Solar","5JNW_1","2014-09-29",null,null,14," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2014-11-01",null,"STD",null,null,null,null,null," ",null,null,null,"Application not complete.  Customer is located on the area network.  Customer cancelled instead of moving forward with a study."]
[null,"WMECO","Springfield","6S531-2014","01109",44.55,"Solar","5J9","2014-09-29","2014-10-28",{"$f":"NETWORKDAYS(I249,J249,MALegalHolidays)","v":21},20,1,"2014-10-29","2014-11-18",{"$f":"NETWORKDAYS(N249,O249,MALegalHolidays)","v":14},3,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-11-24",null,"2014-11-01",null,"EXP",null,null,null,null,null," ",null,null,"2015-02-18","Application received, need info for application complete, recevied info, application complete.  Reviewed project, sent Draft Exhibit G and H for review, sent Exhibit G and H for signature.  Rcvd signed agreements, rcvd inspector sign off, waiting for completion docs to schedule Witness Test."]
[null,"WMECO","Indian Orchard","6S532-2014","01151",180,"Solar","27A13","2014-09-29","2014-10-14",{"$f":"NETWORKDAYS(I250,J250,MALegalHolidays)","v":11},10,{"$f":"IF(K250>0,K250-L250,\" \")","v":1},"2014-10-15","2014-11-26",{"$f":"NETWORKDAYS(N250,O250,MALegalHolidays)","v":30},9,{"$f":"IF(P250>0,P250-Q250,\" \")","v":21},null,null,null,null,{"$f":"IF(U250>0,U250-V250,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z250>0,Z250-AA250,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE250>0,AE250-AF250,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ250>0,AJ250-AK250,\" \")","v":" "},"2014-12-05",null,"2014-11-30",null,"EXP",null,null,null,null,null,{"$f":"IF(AU250>0,AU250-AV250,\" \")","v":" "},"2015-08-28","2015-09-02","2015-09-02","App complete.  Agreements out for signature. Signed Agreements recevd.  Witness Test performed. Comp docs rcvd.  Project is on line."]
[null,"WMECO","Easthampton","6A880-2014","01027",98,"Solar","15A2","2014-10-06","2014-11-26",{"$f":"NETWORKDAYS(I251,J251,MALegalHolidays)","v":36},34,2,"2014-11-28","2015-02-19",{"$f":"NETWORKDAYS(N251,O251,MALegalHolidays)","v":56},35,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-04-15",null,"2014-12-01",null,"EXP",null,null,null,null,null," ","2016-03-03","2016-03-10","2016-03-10","App complete.  Screen Review email sent.  Draft IA out for review. Signed Exhibt G and H received, new service required, customer on line"]
[null,"WMECO","Pittsfield","6B446-2014","01201",234,"Solar","19A5","2014-10-15","2014-10-28",{"$f":"NETWORKDAYS(I252,J252,MALegalHolidays)","v":10},3,7,"2014-10-29","2014-12-10",{"$f":"NETWORKDAYS(N252,O252,MALegalHolidays)","v":29},13,16,"2014-12-11","2016-02-19",{"$f":"NETWORKDAYS(S252,T252,MALegalHolidays)","v":298},262,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-22",null,"2014-12-31",null,"EXP",null,null,null,null,null," ","2016-03-17","2016-03-23","2016-03-23","application complete.  Sent initial review to Customer. Sent Supplemental Agreement for signature.  Rcvd signed agreement and payment.  Review is started. Supplemenatl Review finished, project requires Direct Transfer Trip.  Customer requests a conference call with protection engineer.  Customer Hold.  Conference call was conducted, the project manager will get back to WMECO whether project will move forward.  Interconnecting Customer wants estimates for PLC and phone transfer trip.  Need time for other departments to give estimates. Sent estimate to Interconnecting Customer.  Customer deceided to ove forward with no export.  New drawing requried, Rcvd new drawing, sned to protection dept for review.  Customer requested conf call re: comments on drawings, will send three line drawing re: relay connections. received completion docs, scheduled Witness Test.  Witness Test successful, Customer on line."]
[null,"WMECO","Pittsfield","6B447-2014","01201",168,"Solar","30B2","2014-10-24","2014-10-29",{"$f":"NETWORKDAYS(I253,J253,MALegalHolidays)","v":4},0,4,"2014-10-30","2014-11-18",{"$f":"NETWORKDAYS(N253,O253,MALegalHolidays)","v":13},12,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2014-12-09",null,"2014-12-12",null,"EXP",null,null,null,null,null," ","2015-01-21","2015-01-22","2015-01-22","application complete.  Sent initial Review to Customer. Ordered meter,  Meter engineering had questions regarding where solar was interconnecting. Needed revised drawing and explanation of service configuration.  Meter supervisor perormed site visit and verified service configuration. Rcvd revised drawing. Sent Exhibit G and H for signature.  Rcvd IA docs, waiting for completion docs, rcvd and reviewed comp docs, scheduled Witness Test, Performed Witness Test.  Customer on line."]
[null,"WMECO","Amherst","6A919-2014","01002",57.75,"Solar","17K8","2014-11-05","2014-11-25",{"$f":"NETWORKDAYS(I254,J254,MALegalHolidays)","v":14},6,8,"2014-11-26","2015-03-02",{"$f":"NETWORKDAYS(N254,O254,MALegalHolidays)","v":64},33,31,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-04",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-06-12","2015-06-15","2015-06-15","app complete. Needs site visit.  Site visit with meter supervisor and installer, may need to discuss system modifications prior to initial review. Cust putting solar on two buildings but tying both in to one service.  The meter supervisor is requireing that the meters be moved outside as the installer is making a change to the service.  Customer Hold. The installer will change where the solar will be interconnected.  A site visit is required to verify from which transformer the new POI is fed. transformer info was received, Time frame for approval to install was negotiated with installer. Installer is required to send revised application, one line and site plan.  Rcvd revised info, sent out Exhibit G for signature. Rcvd signed agreement. Rcvd comp docs, need revised wit test procedure and fist page of Sched Z.  Rcvd info Witness Test scheduled.  Witness Test performed, Customer is on line."]
[null,"WMECO","Hatfield","6A935-2014","01038",3300,"Solar","18G5","2014-11-13","2015-03-04",{"$f":"NETWORKDAYS(I255,J255,MALegalHolidays)","v":75},69,6,null,null,null,null," ",null,null,null,null," ","2015-03-05","2015-06-06",{"$f":"NETWORKDAYS(X255,Y255,MALegalHolidays)","v":64},61,3,"2015-05-29","2015-11-05",{"$f":"NETWORKDAYS(AC255,AD255,MALegalHolidays)","v":111},12,99,"2016-04-12",null,{"$f":"NETWORKDAYS(AH255,AI255,MALegalHolidays)","v":-30286},null," ",null,null,"2015-10-01",null,"COMP",null,null,null,null,null," ",null,null,null,"App rcvd, review for completeness, app not complete, Int Customer asked for an extension. Int Customer requested conference call.  Customer requested Impact Study estimates, application still not complete.  Info rcvd, application complete, sent out initial review to Customer.  Scoping meeting required.  Scoping meeting held, info required, property may be more than one parcel. Project may become third party owned.  On Customer hold. Proprties are required to be legally combined. Impact Study started.  IC requested 30 days for tech reasons in DS.  Sold, new applicant cancelled project."]
[null,"WMECO","Ludlow","6S672-2014","01056",998,"Solar","19S3","2014-11-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2015",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S673-2014","01056",499,"Solar","19S3","2014-11-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2015",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S674-2014","01056",499,"Solar","19S3","2014-11-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2015",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S689-2014","01104",150,"Solar","21S7","2014-11-25","2015-07-30",{"$f":"NETWORKDAYS(I259,J259,MALegalHolidays)","v":168},163,5,"2015-07-31","2016-05-05",{"$f":"NETWORKDAYS(N259,O259,MALegalHolidays)","v":195},31,164,null,null,null,null," ",null,null,null,null," ","2016-05-06","2016-09-26",{"$f":"NETWORKDAYS(AC259,AD259,MALegalHolidays)","v":102},46,56,null,null,null,null," ","2016-09-26",null,"12/2014",null,"STD",null,null,null,null,null," ","2017-08-24","2017-08-25","2017-08-25","Application received, review for completeness, app not complete, info required sent e-mail. Rcvd info, initial review sent out to customer, held scoping meeting. Negotiated timeline, customer submitted smaller 150 kW option, 10 days for Impact Study stage, other negotiations to determine creative solution for interconnection. No system modifications required.  New service was installed.  Service swith gear was delivered as 120/208 instead of 480/277.  Inverters were purchased and installed as 120/208. Output of inverters did not change. Witness test performed, project is on line."]
[null,"WMECO","Otis","6B458-2014","01029",1500,"Wind","19J6","2014-12-01","2014-12-17",{"$f":"NETWORKDAYS(I260,J260,MALegalHolidays)","v":13},12,1,null,null,null,null," ",null,null,null,null," ","2014-12-18","2015-03-26",{"$f":"NETWORKDAYS(X260,Y260,MALegalHolidays)","v":66},63,3,"03/27/2015 & 7/15/2016","07/23/2015 & 10/5/2016",{"$f":"NETWORKDAYS(AC260,AD260,MALegalHolidays)","v":{"$error":"#VALUE!"}},17,{"$error":"#VALUE!"},"2016-02-23",null,{"$f":"NETWORKDAYS(AH260,AI260,MALegalHolidays)","v":-30251},144," ","2015-07-27",null,"2015-06-01",null,"COMP",null,null,null,null,null," ",null,null,"2018-03-09","Received new App.  App fee waived.  Application is Complete with one design option.  Impact Study Agreement out for signature.  I.S. Agreement and  payment received.  In Impact Study.  On Customer stop from 7/23/15 to 2/22/16.  I.C. verified they CAN get the origianl turbine. Another Impact Study started 7/18/16 due to design issue.  New ISA issued 10/5/16 for new design option 2."]
[null,"WMECO","Otis","6B459-2014","01253",960,"Solar","19J4","2014-12-02","2015-01-19",{"$f":"NETWORKDAYS(I261,J261,MALegalHolidays)","v":32},27,5,"2015-01-20","2015-06-15",{"$f":"NETWORKDAYS(N261,O261,MALegalHolidays)","v":101},44,57,null,null,null,null," ",null,null,null,null," ","2015-08-03","2016-01-04",{"$f":"NETWORKDAYS(AC261,AD261,MALegalHolidays)","v":106},41,65,null,null,null,null," ","2016-02-04",null,"2015-08-01",null,"COMP",null,null,null,null,null," ",null,null,null,"app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete. Sent out initial review, scoping meeting held, info required. Rcvd partial info.  Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels.  Project on Customer Hold. Customer sent e-mail, two projects cannot be installed on the one parcel, they will cancel one project and submit a new project on another project for another parcel.  Had multiple calls with Customer, Customer will move forward with the two projects oin the one parcel and get an exception form the DPU for Net metering purposes. Sent out Group Impact Study agreement for both projects 6B459-2015 and 6B463-2014.  Rcvd signed agreement and personal check for study, certified check required. Project on hold until certified check rcvd.  Rcvd cert check, Impact study in process. Impact Study report sent to Customer. Detailed Study agreement sent out for signature. Withdrawn after agreement not executed, applicant does not have money."]
[null,"WMECO","Sunderland","6A962-2014","01375",22.8,"Solar","18G3","2014-12-03","2014-12-30",{"$f":"NETWORKDAYS(I262,J262,MALegalHolidays)","v":19},9,10,"2014-12-31","2015-02-27",{"$f":"NETWORKDAYS(N262,O262,MALegalHolidays)","v":40},36,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-06",null,"2015-02-01",null,"EXP",null,null,null,null,null," ","2015-04-15","2015-04-16","2015-04-16","app complete, sent e-mail, need initial review, sent out initial review need revised drawing due to line side tap.  Rcvd info.  Need tofield check transformer, may be more than 20 kW of generation on shared secondaries, same property, two single phase services.  Field check performed , this Customer has one service fed from a pad mounted tranformer.  Sent out Exhibit G for signature.  Rcvd signed IA.  Rcvd revised one line, sent as attachment 1, ordered net meter. Rcvd completion docs, scheduled meter set and Witness Test.  Witness Test performed, successful, Customer is on line"]
[null,"WMECO","Pittsfield","6B462-2014","01201",3300,"Solar","15E2","2014-12-08","2014-12-15",{"$f":"NETWORKDAYS(I263,J263,MALegalHolidays)","v":6},2,4,null,null,null,null," ",null,null,null,null," ","2014-12-16","2015-02-17",{"$f":"NETWORKDAYS(X263,Y263,MALegalHolidays)","v":42},26,16,"2015-03-16","2015-08-24",{"$f":"NETWORKDAYS(AC263,AD263,MALegalHolidays)","v":111},33,78,"2015-08-11","2015-10-22",{"$f":"NETWORKDAYS(AH263,AI263,MALegalHolidays)","v":51},30,21,"2015-10-23",null,"2015-08-27",null,"COMP",null,null,null,null,null," ",null,null,"2017-04-13","app complete, sent e-mail, needs initial review, sent out initial review, info required. Held scoping meeting, info received.  Requested estimates for Impact Study, rcvd estimates, sent out Impact Study Agreement, Waiting for signed agreement and check.  Rcvd signed agremment and check, sent info to vendor to start study.  Impact Stduy check returned for insufficiant funds.  Impact Study on hold. Int Customer replaced  check with certified check, Impact Study restarted.  Conf call with Int Cust. on DG process again.  They are searching for Host Customer.  DTT estimate requested from line and S/S. Impact Study Report sent out to Customer with plus/minus 25% system modification costs. Held call with customer, revided report. Negotiated timeline. Detailed Study agreement and ISO notification form sent out to Customer. Recevied first payment for the Detailed Study.  Site visit performed, Int Customer required to take out WR # to move forward with writing WO."]
[null,"WMECO","Otis","6B463-2014","01253",960,"Solar","19J4","2014-12-08","2015-01-19",{"$f":"NETWORKDAYS(I264,J264,MALegalHolidays)","v":28},24,4,"2015-01-20","2015-06-15",{"$f":"NETWORKDAYS(N264,O264,MALegalHolidays)","v":101},44,57,null,null,null,null," ",null,null,null,null," ","2015-08-03","2016-01-04",{"$f":"NETWORKDAYS(AC264,AD264,MALegalHolidays)","v":106},41,65,null,null,null,null," ","2016-02-04",null,"2015-08-01",null,"COMP",null,null,null,null,null," ",null,null,null,"app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete.   Sent out initial review,  scoping meeting held, info required. Rcvd partial info.  Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels.  Project on Customer Hold.  app rcvd, need check, rcvd check, review for completeness, need info, rcvd info app complete. Sent out initial review, scoping meeting held, info required. Rcvd partial info.  Talked with the Town of Otis Administrator, the propertiy is not divided into 2 parcels.  Project on Customer Hold. Customer sent e-mail, two projects cannot be installed on the one parcel, they will cancel one project and submit a new project on another project for another parcel.  Had multiple calls with Customer, Customer will move forward with the two projects oin the one parcel and get an exception form the DPU for Net metering purposes. Sent out Group Impact Study agreement for both projects 6B459-2015 and 6B463-2014.  Impact Study report sent to Customer. Detailed Study agreement sent out for signature. Withdrawn after agreement not executed, applicant does not have money."]
[null,"WMECO","Longmeadow","6S708-2014","01106",16.350000000000001,"Solar","22H12","2014-12-09","2014-12-15",{"$f":"NETWORKDAYS(I265,J265,MALegalHolidays)","v":5},0,5,"2014-12-16","2015-01-23",{"$f":"NETWORKDAYS(N265,O265,MALegalHolidays)","v":26},11,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-02-03",null,"2015-02-09",null,"EXP",null,null,null,null,null," ",null,null,null,"app complete, sent e-mail, needs initial review, initial reviewe performed revised drawing required.  Rcvd drawing, info for agreements required,  sent out Exhibit H and Exhibit G for signature. Cancelled by IC."]
[null,"WMECO","Greenfield","6F724-2014","01301",48,"Solar","21C1","2014-12-12","2014-12-30",{"$f":"NETWORKDAYS(I266,J266,MALegalHolidays)","v":12},10,2,"2014-12-31","2015-03-09",{"$f":"NETWORKDAYS(N266,O266,MALegalHolidays)","v":46},38,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-25",null,"2015-02-15",null,"EXP",null,null,null,null,null," ","2015-06-04","2015-06-08","2015-06-08","Addition to existing system.  Application is Complete with one design option.  Screen Review sent.  Need updated info from I.C.  Have executed IA.  Have Comp. Docs.  Witness Test Successful.  Online 6/8."]
[null,"WMECO","Deerfield","6F725-2014","01342",4500,"Solar","22B4","2014-12-12","2015-01-29",{"$f":"NETWORKDAYS(I267,J267,MALegalHolidays)","v":32},23,9,null,null,null,null," ",null,null,null,null," ","2015-01-30","2015-03-17",{"$f":"NETWORKDAYS(X267,Y267,MALegalHolidays)","v":31},16,15,"2015-03-18","2015-11-30",{"$f":"NETWORKDAYS(AC267,AD267,MALegalHolidays)","v":176},38,138,"2016-03-18",null,{"$f":"NETWORKDAYS(AH267,AI267,MALegalHolidays)","v":-30269},null," ","2015-12-07",null,"Q3/4 2015",null,"COMP",null,null,null,null,null," ","2017-10-11","2017-10-18","2017-12-08","Review for completeness, app not complete, need UL certs for inverters.  Rcvd cert for the 1000 NX need cert for the 1000 NX.  Invetigated information that Customer sent for the 500NX inverter and was able to determine that the 500NX is certified for UL1741, Application is complete, needs initial review. Sent out initial review comments, held scoping meeting, info required.  Rcvd info, requested Impact Study estimate, Rcvd estimate, sent out Impact Study agreement.  Rcdv signed Impact Study agreement and check.  Sent info to vendor to start study.  Requested estimate for DTT. Issue with high voltage at PCC, snt volt reg info to Asset Mangment, sent out report to Customer. Sent Detailed Study Agreement for signature. Sent early ISA and landowner agreement for signature"]
[null,"WMECO","Greenfield","6F736-2014","01301",24,"Solar","21C4","2014-12-26","2015-01-22",{"$f":"NETWORKDAYS(I268,J268,MALegalHolidays)","v":18},13,5,"2015-01-23","2015-03-12",{"$f":"NETWORKDAYS(N268,O268,MALegalHolidays)","v":34},23,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Feb 2015",null,"EXP",null,null,null,null,null," ",null,null,null,"App reviewed for completness, App complete. Initial review performed, site address on electric account does not match town records. Installer submitted smaller project due to the required upgrades. This project is cancelled"]
[null,"WMECO","Springfield","6S764-2015","01108",37.799999999999997,"Solar","22H16","2015-01-06","2015-01-30",{"$f":"NETWORKDAYS(I269,J269,MALegalHolidays)","v":18},17,1,"2015-02-02","2015-03-06",{"$f":"NETWORKDAYS(N269,O269,MALegalHolidays)","v":24},15,9,"2015-03-09","2015-04-03",{"$f":"NETWORKDAYS(S269,T269,MALegalHolidays)","v":19},1,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-04-20",null,"2015-01-22",null,"EXP",null,null,null,null,null," ","2015-08-10","2015-08-12","2015-08-13","App complete.  Screening email sent.  Need information from I.C. and Supplemental Review completed.  Signed Exhibit G received. Comp docs rcvd, Wit test perfomed, need RESERVED STATUS for Cap Allocation.  Cap Allocation rcvd, project on line."]
[null,"WMECO","Pittsfield","6B474-2015","01201",36,"Solar","15E3","2015-01-07","2015-02-11",{"$f":"NETWORKDAYS(I270,J270,MALegalHolidays)","v":25},9,16,"2015-02-12","2015-04-08",{"$f":"NETWORKDAYS(N270,O270,MALegalHolidays)","v":38},37,1,"2015-04-28","2015-05-18",{"$f":"NETWORKDAYS(S270,T270,MALegalHolidays)","v":15},14,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-07-08",null,"2015-08-01",null,"EXP",null,null,null,null,null," ","2015-11-10","2015-11-13","2015-11-13","Application received, app acknowledged, need check, app not complete, info required, app complete, initial review, info required, held scoping meeting, drawing needs to be revised, sent to meter engineering for their review and comment.  Project requires supplemental review due to distance of tranformers from proposed solar facility i.e.generation may cause high voltage in area, Jon made a complaint to DPU. Suppleeemental agreement was sent for his signature. Conference call with Jon and Cindy.  Jon sent stamped drawing will send signed supplemental review agreement and check.  Rcvd signed agreement and check, Supp Rev schedueld. Supp Rev completed, system mods required. sent e-mail to Customer with choices and high level costs. Cusotmer does not agree with high level costs.  Customer took out request for one of the choices.  He will have a site visit with with tech.  Technician met with the customer for a site visit.  The technicain wrote up the job for the system modiicaiton cost estimate.  The Exhibit G and Exhibit H were sent our for signature.  The Net meter was ordered. system modifications were completed. Completion docs were received, net meter was set.  Electric Customer changed, new account number, new Exhibit H and Exhibit G required. Wtness Test scheduled, sent out revised IAs, Witness test performed, IAs rcvd. Customer on line."]
[null,"WMECO","Deerfield","6F749-2015","01342",40,"Solar","22B1","2015-01-07","2015-02-04",{"$f":"NETWORKDAYS(I271,J271,MALegalHolidays)","v":20},15,5,"2015-02-05","2015-09-18",{"$f":"NETWORKDAYS(N271,O271,MALegalHolidays)","v":155},111,44,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-09-18",null,"2015-02-01",null,"EXP",null,null,null,null,null," ","2015-11-05","2015-11-12","2016-02-03","App reviewed for complteness, not complete. Rcvd info, application complete. Initial Review sent to customer.  Scoping meeting held, service required to be uipgraded due to safety hazard at meter socket.  Revised one line required."]
[null,"WMECO","Hadley","6A1005-2015","01035",253,"Solar","17K6","2015-01-09","2015-01-23",{"$f":"NETWORKDAYS(I272,J272,MALegalHolidays)","v":10},5,5,"2015-01-26","2015-03-02",{"$f":"NETWORKDAYS(N272,O272,MALegalHolidays)","v":25},15,10,"2015-03-05","2015-03-27",{"$f":"NETWORKDAYS(S272,T272,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-04-03",null,"2015-05-05",null,"EXP",null,null,null,null,null," ","2015-06-24","2015-07-01","2015-07-23","App Rcvd, app fee check rcvd, Application reviewed for completeness, app not complete.  Rcvd info, app complete, needs initial review.  Sent out initial review, info required from Int Customer.  Supplemental review required.  Info required, rcvd info,  sent out supplemental Review for signture. Supplemental Review finished, sent out report to Customer.  Started Exhibit G and Exhibit H, sent out for signature.  Cell based Net meter is scheduled to be set.  Meter is set.  Waiting for insigned IAs and completion docs.  Recvd compl docs and insurance cert - o.k. Witness Test scheduled.  Witness Test performed and was successful.  The Customer is required to stay off line until they have CADMUS cap allocation Reserved status.  Interconnecting Customer and Customer have been notified numerous times of this issue.  Reserved status has been received, Customer is on line."]
[null,"WMECO","Lanesborough","6B479-2015","01237",368,"Solar","15E2","2015-01-21","2015-02-04",{"$f":"NETWORKDAYS(I273,J273,MALegalHolidays)","v":11},6,5,"2015-02-05","2015-03-03",{"$f":"NETWORKDAYS(N273,O273,MALegalHolidays)","v":18},12,6,"2015-03-04","2017-01-08",{"$f":"NETWORKDAYS(S273,T273,MALegalHolidays)","v":473},435,38,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-01-10",null,"2015-05-05",null,"EXP",null,null,null,null,null," ",null,null,"2017-12-22","App rcvd, need app fee check, rcvd check, reviewed for copleteness, app not complete, rcvd info, app complete.  Sent out initial review, review by meter supervisor is required.  info required.   Supplemental review required.   Rcvd info, Sent out Supplemental Review Agreement for signture.  Rcvd signed agreement, review started, review report sent ot Customer.  Project requires DTT.  High level Estimates for DTT required for Customer. Negotiated timeline, 5 extra days."]
[null,"WMECO","Becket","6B481-2015","01223",24,"Solar","16B1","2015-01-23","2015-01-26",{"$f":"NETWORKDAYS(I274,J274,MALegalHolidays)","v":2},1,1,"2015-01-27","2015-03-06",{"$f":"NETWORKDAYS(N274,O274,MALegalHolidays)","v":28},16,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-10",null,"Spring 2015",null,"EXP",null,null,null,null,null," ","2015-10-05","2015-10-07","2015-10-09","App rcvd, need check for application fee, need projetc check list, rcvd check, review for completeness, app not complete inverter cut sheet required. Rcvd info, app complete, Sent out IA for signature."]
[null,"WMECO","Whately","6A1047-2015","01093",20,"Solar","18G8","2015-02-02","2015-02-19",{"$f":"NETWORKDAYS(I275,J275,MALegalHolidays)","v":13},5,8,"2015-02-19","2015-02-20",{"$f":"NETWORKDAYS(N275,O275,MALegalHolidays)","v":2},0,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-02-20",null,"Q1 2015",null,"EXP",null,null,null,null,null," ","2015-07-03","2015-07-07","2015-07-07","App rcvd, app fee required, rcvd app fee, review for completeness, app not complete info required, rcvd infor app complete.  Initial review sent out.  Started IA, sent out IA for signature, Rcvd revised Schedule Z. Rcvd comp docs, rvwd comp docs, need revised CoC with building designation per the electric account address.  Rcvd revised CoC, Wit test procedure, scheduled Witness Test, Witness Test successful, project on line. "]
[null,"WMECO","Hatfield","6A1053-2015","01038",1890,"Solar","18G6","2015-02-09","2015-05-15",{"$f":"NETWORKDAYS(I276,J276,MALegalHolidays)","v":67},65,2,"2015-05-18","2015-10-29",{"$f":"NETWORKDAYS(N276,O276,MALegalHolidays)","v":114},76,38,null,null,null,null," ",null,null,null,null," ","2015-10-30","2016-02-12",{"$f":"NETWORKDAYS(AC276,AD276,MALegalHolidays)","v":73},2,71,"2016-03-07",null,{"$f":"NETWORKDAYS(AH276,AI276,MALegalHolidays)","v":-30260},null," ","2016-02-12",null,"Sept 2015",null,"COMP",null,null,null,null,null," ","2017-07-03","2017-07-10","2017-09-07","Application received, review for completeness, app not complete."]
[null,"WMECO","Whately","6A1062-2015","01093",19.3,"Solar","18G6","2015-02-19","2015-04-22",{"$f":"NETWORKDAYS(I277,J277,MALegalHolidays)","v":43},41,2,"2015-04-23","2015-07-10",{"$f":"NETWORKDAYS(N277,O277,MALegalHolidays)","v":54},47,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-07-10",null,"2015-04-06",null,"EXP",null,null,null,null,null," ","2016-01-29","2016-02-02","2016-02-02","Application received, review for completeness, app not complete.  Rcvd revised information app complete, Initial review performed, info required"]
[null,"WMECO","Becket","6B483-2015","01223",17.5,"Solar","19J6","2015-02-23","2015-04-16",{"$f":"NETWORKDAYS(I278,J278,MALegalHolidays)","v":38},18,20,"2015-04-17","2015-04-30",{"$f":"NETWORKDAYS(N278,O278,MALegalHolidays)","v":9},8,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-05-18",null,"2015-05-15",null,"EXP",null,null,null,null,null," ",null,null,"2015-11-04","App rcvd, need check for application fee, need projetc check list, rcvd check, other inor required, rcvd info, technical review of application.  The solar facility is shown being located on adjoining parcel.  Customer owns both parcels, he will legally combine them.  Started IA, talked with Mrs. Haber, address listed on application and electric account are incorrect, sent an e-mail to Customer to call Customer Service to change street number.   sent out ISA, ordered meter. Rvcd comp docs, set meter, customer asked that wit test be waived as we did not sched wit test within 10 days of recving comp docs, Wit test waived. project on line. "]
[null,"WMECO","South Deerfield","6F801-2015","01342",500,"Biogas","22B1","2015-02-24","2015-04-15",{"$f":"NETWORKDAYS(I279,J279,MALegalHolidays)","v":36},34,2,"2015-04-16","2015-05-22",{"$f":"NETWORKDAYS(N279,O279,MALegalHolidays)","v":26},16,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-12-01",null,"STD",null,null,null,null,null," ",null,null,null,"Application received.  Check for fee received.  App Complete.  Sent Screen Review email.  Need Supplemental Review.  Scoping call held.  Interconnecting Customer elected to go to Impact Study.  Impact Sutdy out for signature on 6/1.  Have not received agreement or payment yet. withdrawn"]
[null,"WMECO","Deerfield","6F802-2015","01373",18,"Solar","18G3","2015-02-24","2015-03-05",{"$f":"NETWORKDAYS(I280,J280,MALegalHolidays)","v":8},0,8,"2015-03-06","2015-03-13",{"$f":"NETWORKDAYS(N280,O280,MALegalHolidays)","v":6},4,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-03-24",null,"March 2015",null,"EXP",null,null,null,null,null," ","2015-05-19","2015-05-21","2015-05-21","Application rcvd, rvw for completeness. Info required,  info received same day, app complete.  Initial Review started. New service under construction.  New service finished.  IA sent out for signature.  New service, new electrci account was set up.  Rcvd coc, not O.K. rcvd revised CoC , need revised one ine drawing to send to meter engineering, rcvd cap reserved status and remaining comp docs, witness test performed, project in line."]
[null,"WMECO","Greenfield","6F815-2015","01301",56,"Solar","21C1","2015-03-05","2015-03-31",{"$f":"NETWORKDAYS(I281,J281,MALegalHolidays)","v":18},15,3,"2015-04-01","2015-04-13",{"$f":"NETWORKDAYS(N281,O281,MALegalHolidays)","v":9},2,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-04-15",null,"2015-05-01",null,"EXP",null,null,null,null,null," ","2017-04-19","2017-04-20","2017-04-20","Application received, need app fee, check rcvd, review for app complete, app complete, initial review started, talked with installer revised one line and site plan required. Info recvd, IA sent for signature"]
[null,"WMECO","Lee","6B490-2015","01238",1904,"Solar","17G7","2015-03-12","2015-03-20",{"$f":"NETWORKDAYS(I282,J282,MALegalHolidays)","v":6},2,4,null,null,null,null," ",null,null,null,null," ","2015-03-23","2015-04-30",{"$f":"NETWORKDAYS(X282,Y282,MALegalHolidays)","v":28},23,5,"2015-05-15","2015-08-12",{"$f":"NETWORKDAYS(AC282,AD282,MALegalHolidays)","v":61},3,58,"2015-08-20",null,{"$f":"NETWORKDAYS(AH282,AI282,MALegalHolidays)","v":-30123},null," ","2015-08-27",null,"2015-09-30",null,"STD",null,null,null,null,null," ","2017-03-28","2015-04-11","2017-04-11","App rcvd, need check for application fee,  rcvd check revw for completeness, app not complete info required, rcvd info, app complete, intial review sent out, info required, sent out dates for scoping meeting.  Held scoping meeting, Int Cust wanted to send in options.  Rcvd two options both for a smaller project each with different inverters.initial review of options started. Comments sent out, info required, rcvd info, need to rvw. Started Impact Study.  Impact Study Report and Detailed Study agreement sent to Customer.  Rcvd signed agreement and check.  Need to schedule site visit."]
[null,"WMECO","Pittsfield","6B497-2015","01201",2340,"Solar","19A3","2015-03-24","2015-03-31",{"$f":"NETWORKDAYS(I283,J283,MALegalHolidays)","v":6},2,4,null,null,null,null," ",null,null,null,null," ","2015-04-01","2015-06-04",{"$f":"NETWORKDAYS(X283,Y283,MALegalHolidays)","v":45},30,15,"2015-06-05","2015-11-06",{"$f":"NETWORKDAYS(AC283,AD283,MALegalHolidays)","v":107},0,107,"2015-11-24","2016-09-21",{"$f":"NETWORKDAYS(AH283,AI283,MALegalHolidays)","v":215},0,215,"2015-11-09",null,"Fall 2015",null,"COMP",null,null,null,null,null," ","2017-01-18","2017-01-20","2017-01-31","Application received, reviewed for completeness, infor required, talked with project contact on phone regarding transmission access permission study required.  Contacted Transmission real estate that a solar facility is proposing to install/cross the ROW. Application complete, Initial Review sent ot Interconnecting Customer, scoping meeting set up.  held site visit with installer, lect customer, transmission ROW.  Civil plans required for transmission ROW review, fee and agreement required for review.  Solar facility can be installed as long as equipment is located outside of ROW.  Rcvd signed T and Impact Study agreements and checks.  Impact Study in process. Detailed Study in process.  Work orders written, equipment long led.  equipment received.  Substation work started.  Substation work finished, Plc line work finished.  witness Test scheduled.  witness Test performed.  Need updated Schedule Z with correct allocation info. Schedule Z received with correct info.  project given approval to operate."]
[null,"WMECO","Greenfield","6F836-2015","01301",19.3,"Solar","21C4","2015-03-27","2015-04-20",{"$f":"NETWORKDAYS(I284,J284,MALegalHolidays)","v":16},8,8,"2015-04-21","2015-04-21",{"$f":"NETWORKDAYS(N284,O284,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-04-22",null,"2015-04-01",null,"EXP",null,null,null,null,null," ","2015-05-15","2015-05-19","2015-05-19","App recvd, app fee required. Rcvd app fee, rvw for completeness, app not complete, address required to be changed to correct address as reflected on asessor's map.  Address changed, app complete.  Initial review revised 1-line drawing required. Rcvd revised 1-line.  IA sent out for signature. Rcvd CoC and pics, need signed Ex G wit test procedure and cap allocation.  Received required comp docs, scheduled wit test, project on line."]
[null,"WMECO","Granville","6S941-2015","01034",24.99,"Solar","29A5","2015-04-06","2015-04-16",{"$f":"NETWORKDAYS(I285,J285,MALegalHolidays)","v":9},6,3,"2015-04-16","2015-04-16",{"$f":"NETWORKDAYS(N285,O285,MALegalHolidays)","v":1},0,1,"2015-04-21","2015-05-06",{"$f":"NETWORKDAYS(S285,T285,MALegalHolidays)","v":12},0,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-05-07",null,"2015-06-01",null,"EXP",null,null,null,null,null," ","2015-07-30","2015-07-31","2015-07-31","Application received, need app fee, received check for app fee, reviewed for completeness, app not complete, info required.  Rcvd info, sent out initial review, system mods required, sned out Supp Rev to write WO, sent out IA with est for syst Mods.  Rcvd executed IA. Customer wants to remove OH service and install UG service.  All work will be scheduled for same day.  Construtciot and service work fininshed. Scheduled Witness Test.  Performed Witness Test, Customer is on line."]
[null,"WMECO","Sunderland","6A1124-2015","01375",44,"Solar","18G3","2015-04-17","2015-05-12",{"$f":"NETWORKDAYS(I286,J286,MALegalHolidays)","v":17},11,6,"2015-05-13","2015-06-18",{"$f":"NETWORKDAYS(N286,O286,MALegalHolidays)","v":25},0,25,"2015-06-22","2015-06-30",{"$f":"NETWORKDAYS(S286,T286,MALegalHolidays)","v":7},0,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-06-30",null,"July 2015",null,"EXP",null,null,"2015-09-25",null,null," ","2015-09-24","2015-09-30","2015-09-30","App received.  Rvw for app cmplt. Info required. Rcvd info app cmplt. Negotiated time line for tech.  Supp Review rquired.  Sent out agreement to Customer.  Rcvd signed agrmnt and check, started review.  solar facility was installed prior to approval to install.  Supplemental Review performed, system modifications required, sent out early IA for signature. Rvcd signed IA.  Rvcd comp docs, electrician required to take out electrical permit for service upgrade.  CT rated service. Customer will upgrade service. Customer issue OH service VS UG service.  UG service installed, service complete.  Net meter set.  Witnest scheduled. performed, Customer on line."]
[null,"WMECO","Northfield","6F857-2015","01360",56,"Solar","21B8","2015-04-17","2015-05-12",{"$f":"NETWORKDAYS(I287,J287,MALegalHolidays)","v":17},6,11,"2015-05-13","2015-05-27",{"$f":"NETWORKDAYS(N287,O287,MALegalHolidays)","v":10},0,10,"2015-06-17","2015-07-20",{"$f":"NETWORKDAYS(S287,T287,MALegalHolidays)","v":22},17,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-07-31",null,"7/2015",null,"EXP",null,null,null,null,null," ","2016-02-02","2016-02-03","2016-02-03","App rcvd. Need app fee. Rcvd app fee, rvw for compltness, app complete.  Tech rvw new service requied D transformers required to be as close as possibe to inveters re: volt rise at Customer.  Supp Rev to determinte syste mod costs.  Sent out agreement, rcvd agrmnt waiting for check, rcvd check. Tech held site meeting with installer and customer.  Tech wrote eatimate for OH and UG service.  Installer/Customer requested UG service, sent out IA to include UG service estimate.  Work required OH primary extension onto Customer's property.  "]
[null,"WMECO","Southwick","6S959-2015","01077",1316,"Solar","29A5","2015-04-17","2015-04-22",{"$f":"NETWORKDAYS(I288,J288,MALegalHolidays)","v":3},0,3,"2015-04-23","2015-09-21",{"$f":"NETWORKDAYS(N288,O288,MALegalHolidays)","v":104},93,11,null,null,null,null," ",null,null,null,null," ","2015-09-22","2015-12-11",{"$f":"NETWORKDAYS(AC288,AD288,MALegalHolidays)","v":56},0,56,"2016-01-11",null,{"$f":"NETWORKDAYS(AH288,AI288,MALegalHolidays)","v":-30220},null," ","2016-01-26",null,"2015-12-01",null,"COMP",null,null,null,null,null," ",null,"2016-12-06","2016-12-14","App rcvd, app fee check required, rcvd app fee, reviewed for completeness app complete.  Facility to be interconnected on a separate parcel that Big Y owns.  Properties required to be legally combined.  Customer proposes to install new sw gear with solar facility behind the Customer meter.  There is a nonprimary Net meter available for this size project.  Eversoure not sure how to interconnect due to project size requiring DTT.  Conf call with Customer re: proejct staus update.  Conf call with Eversource attorney, exception from DPU required for combining properties.  Initial review sent to Customer."]
[null,"WMECO","Shelburne Falls","6F872-2015","01370",39.6,"Solar","22B5","2015-04-23",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hatfield","6A1145-2015","01038",18.5,"Solar","18G6","2015-04-27","2015-06-02",{"$f":"NETWORKDAYS(I290,J290,MALegalHolidays)","v":26},20,6,"2015-06-03","2015-07-02",{"$f":"NETWORKDAYS(N290,O290,MALegalHolidays)","v":21},4,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-07-10",null,"June 2015",null,"EXP",null,null,null,null,null," ","2015-08-11","2015-08-17","2015-08-17","App and app fee recvd., Info required, review for completeness, info required, rcvd info , app complete.  Initial review sent out to Customer, revised one line and site plan required."]
[null,"WMECO","South Deerfield","6F881-2015","01373",16.7,"Solar","22B1","2015-04-27","2015-05-18",{"$f":"NETWORKDAYS(I291,J291,MALegalHolidays)","v":16},13,3,"2015-05-19","2015-05-27",{"$f":"NETWORKDAYS(N291,O291,MALegalHolidays)","v":6},3,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-05-29",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-02-02","2016-02-03","2016-02-03"]
[null,"WMECO","Amherst","6A1148-2015","01002",54,"Solar","19B16","2015-04-29","2015-07-16",{"$f":"NETWORKDAYS(I292,J292,MALegalHolidays)","v":54},40,14,"2015-07-17","2015-11-18",{"$f":"NETWORKDAYS(N292,O292,MALegalHolidays)","v":86},18,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-11-18",null,"July 2015",null,"EXP",null,null,null,null,null," ","2016-09-01","2016-09-07","2016-09-07"]
[null,"WMECO","Ashfield","6F890-2015","01330",1995,"Biogas","38A1","2015-05-01","2015-11-02",{"$f":"NETWORKDAYS(I293,J293,MALegalHolidays)","v":127},63,64,"2015-11-03","2016-02-17",{"$f":"NETWORKDAYS(N293,O293,MALegalHolidays)","v":74},30,44,null,null,null,null," ",null,null,null,null," ","2016-02-18","2016-08-15",{"$f":"NETWORKDAYS(AC293,AD293,MALegalHolidays)","v":128},54,74,"2016-08-16","2017-10-05",{"$f":"NETWORKDAYS(AH293,AI293,MALegalHolidays)","v":298},34,264,"2017-10-10",null,"2016-01-01",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Richmond","6B516-2015","01254",18,"Solar","30B2","2015-05-04","2015-08-10",{"$f":"NETWORKDAYS(I294,J294,MALegalHolidays)","v":68},55,13,"2015-08-11","2015-10-14",{"$f":"NETWORKDAYS(N294,O294,MALegalHolidays)","v":45},5,40,"2015-10-15","2016-01-29",{"$f":"NETWORKDAYS(S294,T294,MALegalHolidays)","v":74},44,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-02",null,"2015-06-01",null,"EXP",null,null,null,null,null," ","2016-09-21","2016-09-26","2016-10-18"]
[null,"WMECO","Pittsfield","6B521-2015","01201",499,"Solar","30B5","2015-05-08","2015-06-01",{"$f":"NETWORKDAYS(I295,J295,MALegalHolidays)","v":16},8,8,"2015-06-02","2015-12-30",{"$f":"NETWORKDAYS(N295,O295,MALegalHolidays)","v":145},44,101,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-04-19",{"$f":"NETWORKDAYS(AC295,AD295,MALegalHolidays)","v":79},26,53,"2016-06-13",null,{"$f":"NETWORKDAYS(AH295,AI295,MALegalHolidays)","v":-30330},null," ","2016-05-09",null,"2015-06-30",null,"STD",null,null,null,null,null," ",null,null,"2018-10-30","App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer. Started Ex G, Customer needs to decide on which Option to build.  Customer decided on Option1, Ex G and Ex I sent out for signature.  Need site plan to complete Detailed Study, extra 20 business days for Detailed Study."]
[null,"WMECO","Pittsfield","6B522-2015","01201",499,"Solar","30B5","2015-05-08","2015-06-10",{"$f":"NETWORKDAYS(I296,J296,MALegalHolidays)","v":23},8,15,"2015-06-11","2015-12-30",{"$f":"NETWORKDAYS(N296,O296,MALegalHolidays)","v":138},27,111,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-04-19",{"$f":"NETWORKDAYS(AC296,AD296,MALegalHolidays)","v":79},26,53,"2016-06-13",null,{"$f":"NETWORKDAYS(AH296,AI296,MALegalHolidays)","v":-30330},null," ","2016-05-09",null,"2015-06-30",null,"STD",null,null,null,null,null," ",null,null,"2018-10-30","App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer.  Started Ex G, Customer needs to decide on which Option to build.  Customer decided on Option1, Ex G and Ex I sent out for signature. Need site plan to complete Detailed Study, extra 20 business days for Detailed Study."]
[null,"WMECO","Pittsfield","6B523-2015","01201",499,"Solar","30B5","2015-05-08","2015-06-10",{"$f":"NETWORKDAYS(I297,J297,MALegalHolidays)","v":23},8,15,"2015-06-11","2015-12-30",{"$f":"NETWORKDAYS(N297,O297,MALegalHolidays)","v":138},32,106,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-04-19",{"$f":"NETWORKDAYS(AC297,AD297,MALegalHolidays)","v":79},26,53,"2016-06-13",null,{"$f":"NETWORKDAYS(AH297,AI297,MALegalHolidays)","v":-30330},null," ","2016-05-09",null,"2015-06-30",null,"STD",null,null,null,null,null," ",null,null,"2018-10-30","App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer.  Started Ex G, Customer needs to decide on which Option to build.  Customer decided on Option1, Ex G and Ex I sent out for signature.  Need site plan to complete Detailed Study, extra 20 business days for Detailed Study."]
[null,"WMECO","Pittsfield","6B525-2015","01201",499,"Solar","30B5","2015-05-08","2015-06-10",{"$f":"NETWORKDAYS(I298,J298,MALegalHolidays)","v":23},8,15,"2015-06-11","2015-12-30",{"$f":"NETWORKDAYS(N298,O298,MALegalHolidays)","v":138},27,111,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-04-19",{"$f":"NETWORKDAYS(AC298,AD298,MALegalHolidays)","v":79},26,53,"2016-06-13",null,{"$f":"NETWORKDAYS(AH298,AI298,MALegalHolidays)","v":-30330},null," ","2016-05-09",null,"2015-06-30",null,"STD",null,null,null,null,null," ",null,null,"2018-10-30","App rcvd, need app fee, rcvd fee. Rvw for completeness, app complete, sent out initial review. Sent out group impact study agreement, need signed agreement and check, missed dealine for signed agreement and check, will be withdrawn if not received, signed agreement and check received, Impact study started, Impact Study report sent to customer.  Started Ex G, Customer needs to decide on which Option to build.  Customer decided on Option1, Ex G and Ex I sent out for signature.  Need site plan to complete Detailed Study, extra 20 business days for Detailed Study."]
[null,"WMECO","West Springfield","6S1051-2015","01089",180,"Solar","16C12","2015-05-08","2015-06-25",{"$f":"NETWORKDAYS(I299,J299,MALegalHolidays)","v":33},20,13,"2015-06-26",null,{"$f":"NETWORKDAYS(N299,O299,MALegalHolidays)","v":-30085},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-11-15",null,"EXP",null,null,null,null,null," ",null,null,null,"App received.  On hold for 6S240-2014, cancelled"]
[null,"WMECO","Hadley","6A1169-2015","01035",140,"Solar","18G5","2015-05-12","2015-06-11",{"$f":"NETWORKDAYS(I300,J300,MALegalHolidays)","v":22},10,12,"2015-06-12","2015-11-16",{"$f":"NETWORKDAYS(N300,O300,MALegalHolidays)","v":107},105,2,null,null,null,null," ",null,null,null,null," ","2015-11-16","2016-02-11",{"$f":"NETWORKDAYS(AC300,AD300,MALegalHolidays)","v":62},5,57,null,null,null,null," ","2016-02-12",null,"2015-08-01",null,"STD",null,null,null,null,null," ",null,null,"2016-09-27","application received, app fee received, need whole amount, remaining amount received. Review for completeness, info required, info received, App complete.  On Hold for RES America Impact Study for 110 days, Initial review performed, Impact Study performed, Impact Study report sent out, included design in study.  Early IA sent out."]
[null,"WMECO","Pittsfield","6B529-2015","01201",499,"Solar","30B5","2015-05-12","2015-07-06",{"$f":"NETWORKDAYS(I301,J301,MALegalHolidays)","v":37},10,27,"2015-07-07","2015-12-30",{"$f":"NETWORKDAYS(N301,O301,MALegalHolidays)","v":122},32,90,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-04-19",{"$f":"NETWORKDAYS(AC301,AD301,MALegalHolidays)","v":79},26,53,"2016-06-13",null,{"$f":"NETWORKDAYS(AH301,AI301,MALegalHolidays)","v":-30330},null," ","2016-05-09",null,"2015-06-30",null,"COMP",null,null,null,null,null," ",null,null,"2019-10-24","on line"]
[null,"WMECO","Ludlow","6S1070-2015","01056",1095.8,"Solar","19S2","2015-05-15","2015-07-30",{"$f":"NETWORKDAYS(I302,J302,MALegalHolidays)","v":52},51,1,"2015-07-31","2016-02-18",{"$f":"NETWORKDAYS(N302,O302,MALegalHolidays)","v":140},43,97,null,null,null,null," ",null,null,null,null," ","2016-02-19","2016-05-11",{"$f":"NETWORKDAYS(AC302,AD302,MALegalHolidays)","v":59},0,59,"2016-06-09",null,{"$f":"NETWORKDAYS(AH302,AI302,MALegalHolidays)","v":-30328},null," ","2016-05-11",null,"2016-04-01",null,"STD",null,null,null,null,null," ",null,null,"2018-01-03","Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out.  Application sold."]
[null,"WMECO","Ludlow","6S1071-2015","01056",1095.8,"Solar","19S2","2015-05-15","2015-07-30",{"$f":"NETWORKDAYS(I303,J303,MALegalHolidays)","v":52},51,1,"2015-07-31","2016-02-18",{"$f":"NETWORKDAYS(N303,O303,MALegalHolidays)","v":140},43,97,null,null,null,null," ",null,null,null,null," ","2016-02-19","2016-05-11",{"$f":"NETWORKDAYS(AC303,AD303,MALegalHolidays)","v":59},0,59,"2016-06-09",null,{"$f":"NETWORKDAYS(AH303,AI303,MALegalHolidays)","v":-30328},null," ","2016-05-11",null,"2016-04-01",null,"COMP",null,null,null,null,null," ",null,null,"2017-12-21","Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out.  Application sold."]
[null,"WMECO","Shelburne Falls","6F914-2015","01370",25,"Solar","29R2","2015-05-19","2015-07-10",{"$f":"NETWORKDAYS(I304,J304,MALegalHolidays)","v":36},16,20,"2015-07-13","2015-07-14",{"$f":"NETWORKDAYS(N304,O304,MALegalHolidays)","v":2},0,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-07-16",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-08-24","2015-08-25","2015-08-25","app rcvd, cust submited option2 app complete, tech rvw done, IA sent out for signature, signed IA rcvd, scheduled wit test, performed Wit test, project on line."]
[null,"WMECO","Pittsfield","6B537-2015","01201",499,"Solar","30B7","2015-05-20","2015-06-15",{"$f":"NETWORKDAYS(I305,J305,MALegalHolidays)","v":18},3,15,"2015-06-16","2015-10-20",{"$f":"NETWORKDAYS(N305,O305,MALegalHolidays)","v":87},30,57,null,null,null,null," ",null,null,null,null," ","2015-10-21","2016-03-30",{"$f":"NETWORKDAYS(AC305,AD305,MALegalHolidays)","v":113},0,113,"2016-04-14",null,{"$f":"NETWORKDAYS(AH305,AI305,MALegalHolidays)","v":-30288},null," ","2016-04-25",null,"2015-10-01",null,"STD",null,null,null,null,null," ",null,null,"2018-02-09","Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB.  Talked with Customer, they resent file, app complete, initial review sent out.  Will require group Impact Study with project 6B553-2015. Held scoping meeting. Sent out Impact Study agrmnt for signature.  Impact Study Report and Detailed Study Agreement sent out to Customer.  Received payment for Detailed Study, held internal site visit. "]
[null,"WMECO","Pittsfield","6B538-2015","01201",499,"Solar","30B7","2015-05-20","2015-06-15",{"$f":"NETWORKDAYS(I306,J306,MALegalHolidays)","v":18},3,15,"2015-06-16","2015-10-20",{"$f":"NETWORKDAYS(N306,O306,MALegalHolidays)","v":87},29,58,null,null,null,null," ",null,null,null,null," ","2015-10-21","2016-03-30",{"$f":"NETWORKDAYS(AC306,AD306,MALegalHolidays)","v":113},0,113,"2016-04-14",null,{"$f":"NETWORKDAYS(AH306,AI306,MALegalHolidays)","v":-30288},null," ","2016-04-25",null,"2015-10-01",null,"STD",null,null,null,null,null," ",null,null,"2018-02-09","Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB.  Talked with Customer, they resent file, app complete, initial review sent out.Will require group Impact Study with project 6B553-2015. Held scoping meeting.  Sent out Impact Study agrmnt for signature.   Impact Study Report and Detailed Study Agreement sent out to Customer.  Received payment for Detailed Study, held internal site visit. "]
[null,"WMECO","Pittsfield","6B539-2015","01201",499,"Solar","30B7","2015-05-20","2015-06-15",{"$f":"NETWORKDAYS(I307,J307,MALegalHolidays)","v":18},3,15,"2015-06-16","2015-10-20",{"$f":"NETWORKDAYS(N307,O307,MALegalHolidays)","v":87},29,58,null,null,null,null," ",null,null,null,null," ","2015-10-21","2016-03-30",{"$f":"NETWORKDAYS(AC307,AD307,MALegalHolidays)","v":113},0,113,"2016-04-14",null,{"$f":"NETWORKDAYS(AH307,AI307,MALegalHolidays)","v":-30288},null," ","2016-04-25",null,"2015-10-01",null,"STD",null,null,null,null,null," ",null,null,"2018-02-09","Rcvd app and app fee, started rvw for completeness, did not rcv all attachements as file was greater than 10 MB.  Talked with Customer, they resent file, app complete, initial review sent out.  Will require group Impact Study with project 6B553-2015. Held scoping meeting.  Sent out Impact Study agrmnt for signature.   Impact Study Report and Detailed Study Agreement sent out to Customer.  Received payment for Detailed Study, held internal site visit. "]
[null,"WMECO","Greenfield","6F915-2015","01301",480,"Solar","21C1","2015-05-21","2015-07-09",{"$f":"NETWORKDAYS(I308,J308,MALegalHolidays)","v":33},7,26,"2015-07-10","2016-01-07",{"$f":"NETWORKDAYS(N308,O308,MALegalHolidays)","v":125},43,82,null,null,null,null," ",null,null,null,null," ","2016-01-08","2016-05-13",{"$f":"NETWORKDAYS(AC308,AD308,MALegalHolidays)","v":91},29,62,null,null,null,null," ",null,null,"2015-07-01",null,"STD",null,null,null,null,null," ",null,null,null,"app and fee rcvd. App cplt, initial rvw sent to customer. Scoping meeting scheduled.  Work Order to be written for load service and solar using one transformer. Cancelled by applicant"]
[null,"WMECO","Cummington","6F917-2015","01026",499,"Solar","18K3","2015-05-21","2015-07-30",{"$f":"NETWORKDAYS(I309,J309,MALegalHolidays)","v":48},47,1,"2015-07-31","2015-12-30",{"$f":"NETWORKDAYS(N309,O309,MALegalHolidays)","v":104},33,71,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-09-09",{"$f":"NETWORKDAYS(AC309,AD309,MALegalHolidays)","v":182},59,123,"2016-09-12",null,{"$f":"NETWORKDAYS(AH309,AI309,MALegalHolidays)","v":-30395},null," ","2016-09-26",null,"Oct 2015",null,"COMP",null,null,null,null,null," ",null,null,"2018-08-09","Impact Study Report and Detailed Study agreement sent to interconnecting Customer.  Applicant send revised ap with Landowner info 9/26/16.  Two applicants cancelled 1/20/17, Detailed Study and system mod costs need to be recalculated.  January 2017 change is assignment"]
[null,"WMECO","Ludlow","6S1096-2015","01056",1095.8,"Solar","19S2","2015-05-21","2015-06-24",{"$f":"NETWORKDAYS(I310,J310,MALegalHolidays)","v":23},17,6,"2015-06-25","2016-02-18",{"$f":"NETWORKDAYS(N310,O310,MALegalHolidays)","v":165},43,122,null,null,null,null," ",null,null,null,null," ","2016-02-19","2016-05-11",{"$f":"NETWORKDAYS(AC310,AD310,MALegalHolidays)","v":59},0,59,"2016-06-09",null,{"$f":"NETWORKDAYS(AH310,AI310,MALegalHolidays)","v":-30328},null," ","2016-05-11",null,"2016-04-01",null,"STD",null,null,null,null,null," ",null,null,"2018-01-03","Negotiated timeline with IC due to new option submitted after deemed complete. Part of group. Fourth applicant cancelled so new Detailed Study Agreements sent out. Application sold.  "]
[null,"WMECO","Amherst","6A1199-2015","01002",2002,"Solar","19B16","2015-05-22","2015-07-20",{"$f":"NETWORKDAYS(I311,J311,MALegalHolidays)","v":39},14,25,"2015-07-21","2015-11-04",{"$f":"NETWORKDAYS(N311,O311,MALegalHolidays)","v":75},53,22,null,null,null,null," ",null,null,null,null," ","2015-11-05","2016-03-03",{"$f":"NETWORKDAYS(AC311,AD311,MALegalHolidays)","v":83},13,70,"2016-05-17",null,{"$f":"NETWORKDAYS(AH311,AI311,MALegalHolidays)","v":-30311},null," ","2016-03-04",null,"2015-12-31",null,"COMP",null,null,null,null,null," ","2017-05-08","2017-05-11","2017-05-12","Application and check received.  Review for completeness, info required, rcvd info, itinitial review sent out.  The one line drawings that were sent to vendor with requested revisions also had a project size change that was not brought to the attention of Eversource Energy until reviewing the Draft Impact Study Report.  Impact Study report was sent to Customer.  Early ISA was sent out for signature."]
[null,"WMECO","Amherst","6A1200-2015","01002",1728,"Solar","19B16","2015-05-22","2015-07-20",{"$f":"NETWORKDAYS(I312,J312,MALegalHolidays)","v":39},14,25,"2015-07-21","2015-11-04",{"$f":"NETWORKDAYS(N312,O312,MALegalHolidays)","v":75},53,22,null,null,null,null," ",null,null,null,null," ","2015-11-05","2016-03-03",{"$f":"NETWORKDAYS(AC312,AD312,MALegalHolidays)","v":83},13,70,"2016-05-17",null,{"$f":"NETWORKDAYS(AH312,AI312,MALegalHolidays)","v":-30311},null," ","2016-03-04",null,"2015-12-31",null,"COMP",null,null,null,null,null," ","2017-11-22","2017-11-28","2017-12-27","Application and check received.  Review for completeness, info required, rcvd info, itinitial review sent out.  The one line drawings that were sent to vendor with requested revisions also had a project size change that was not brought to the attention of Eversource Energy until reviewing the Draft Impact Study Report.  Impact Study report was sent to Customer.  Early ISA was sent out for signature."]
[null,"WMECO","Cummington","6F920-2015","01026",840,"Solar","18K3","2015-05-22","2015-07-30",{"$f":"NETWORKDAYS(I313,J313,MALegalHolidays)","v":47},46,1,"2015-07-31","2015-12-30",{"$f":"NETWORKDAYS(N313,O313,MALegalHolidays)","v":104},33,71,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-06-15",{"$f":"NETWORKDAYS(AC313,AD313,MALegalHolidays)","v":120},0,120,null,null,null,null," ",null,null,"Oct 2015",null,"STD",null,null,null,null,null," ",null,null,null,"Impact Study Report and Detailed Study agreement sent to interconnecting Customer 6F920-2015 is cancelled by customer"]
[null,"WMECO","Deerfield","6F921-2015","01342",19.3,"Solar","22B7","2015-05-26","2015-07-06",{"$f":"NETWORKDAYS(I314,J314,MALegalHolidays)","v":28},4,{"$f":"IF(K314>0,K314-L314,\" \")","v":24},"2015-07-07","2015-07-22",{"$f":"NETWORKDAYS(N314,O314,MALegalHolidays)","v":12},1,{"$f":"IF(P314>0,P314-Q314,\" \")","v":11},null,null,null,null,{"$f":"IF(U314>0,U314-V314,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z314>0,Z314-AA314,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE314>0,AE314-AF314,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ314>0,AJ314-AK314,\" \")","v":" "},"2015-08-14",null,"Aug 2015",null,"EXP",null,null,null,null,null,{"$f":"IF(AU314>0,AU314-AV314,\" \")","v":" "},"2016-02-04","2016-02-08","2016-02-08","app rcvd, app complete, tech rvw, IA sent out for signature, signed IA rcvd. Need RESERVED status and comp docs."]
[null,"WMECO","Amherst","6A1211-2015","01002",192,"Solar","18G1, 18G2","2015-05-29","2015-07-06",{"$f":"NETWORKDAYS(I315,J315,MALegalHolidays)","v":25},9,16,"2015-07-07","2015-10-08",{"$f":"NETWORKDAYS(N315,O315,MALegalHolidays)","v":67},37,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-10-23",null,"2015-09-01",null,"EXP",null,null,null,null,null," ","2016-02-11","2016-02-18","2016-02-18","Removed."]
[null,"WMECO","Plainfield","6F926-2015","01070",331,"Solar","18K3","2015-05-29","2015-07-30",{"$f":"NETWORKDAYS(I316,J316,MALegalHolidays)","v":43},6,37,"2015-07-31","2015-11-05",{"$f":"NETWORKDAYS(N316,O316,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-12-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Plainfield","6F927-2015","01070",499,"Solar","18K3","2015-05-29","2015-07-30",{"$f":"NETWORKDAYS(I317,J317,MALegalHolidays)","v":43},6,37,"2015-07-31","2015-11-05",{"$f":"NETWORKDAYS(N317,O317,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-12-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A1217-2015","01002",15,"Solar","17K8","2015-06-01","2015-07-06",{"$f":"NETWORKDAYS(I318,J318,MALegalHolidays)","v":24},1,23,"2015-07-07","2015-07-23",{"$f":"NETWORKDAYS(N318,O318,MALegalHolidays)","v":13},1,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-08-14",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-09-01","2015-09-11","2015-09-11","app rcvd, need info, app complete, sent out initial review.  Sentout IA for signature, rcvd signed IA, rcvd comp docs. Scheduled Wit test, performed Wit test. Project on line."]
[null,"WMECO","Turners Falls","6F939-2015","01376",1774,"Solar","21C3","2015-06-05","2015-10-05",{"$f":"NETWORKDAYS(I319,J319,MALegalHolidays)","v":84},1,83,"2015-10-06",null,{"$f":"NETWORKDAYS(N319,O319,MALegalHolidays)","v":-30155},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-11-01",null,"EXP",null,null,null,null,null," ",null,null,null,"Customer did proceed with study, created group when new applications were received.  Application withdrawn after missed deadlines and no response."]
[null,"WMECO","Pittsfield","6B553-2015","01201",1480,"Solar","30B7","2015-06-08","2015-07-22",{"$f":"NETWORKDAYS(I320,J320,MALegalHolidays)","v":31},17,14,"2015-07-23","2015-10-20",{"$f":"NETWORKDAYS(N320,O320,MALegalHolidays)","v":62},29,33,null,null,null,null," ",null,null,null,null," ","2015-10-21","2016-03-30",{"$f":"NETWORKDAYS(AC320,AD320,MALegalHolidays)","v":113},0,113,"2016-04-14",null,{"$f":"NETWORKDAYS(AH320,AI320,MALegalHolidays)","v":-30288},null," ","2016-04-25",null,"2015-07-30",null,"COMP",null,null,null,null,null," ",null,null,"2017-12-21","App rcvd, need app fee, check rcvd, app complete, Initial rvw.  Will require group study with 6B553-2015.  Held scoping meeting, property on which solar to be installed not owned by Int Cust nor host Cust, has different address from that on the application.  Installer to submit revised application for the 220 Cloverdale St property that will replace the 1505 West St applicaiton.  Sent out Impact Study agrmnt for signature.   Impact Study Report and Detailed Study Agreement sent out to Customer.   Received payment for Detailed Study,"]
[null,"WMECO","Pittsfield","6B554-2015","01201",497,"Solar","30B2","2015-06-08","2015-09-08",{"$f":"NETWORKDAYS(I321,J321,MALegalHolidays)","v":64},44,20,"2015-09-09",null,{"$f":"NETWORKDAYS(N321,O321,MALegalHolidays)","v":-30136},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-07-30",null,"STD",null,null,null,null,null," ",null,null,null,"Group. Cancelled by applicant, incentives changed."]
[null,"WMECO","Pittsfield","6B555-2015","01201",497,"Solar","30B2","2015-06-08","2015-09-08",{"$f":"NETWORKDAYS(I322,J322,MALegalHolidays)","v":64},44,20,"2015-09-09",null,{"$f":"NETWORKDAYS(N322,O322,MALegalHolidays)","v":-30136},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"1901-12-30",null,"STD",null,null,null,null,null," ",null,null,null,"Group. Cancelled by applicant, incentives changed."]
[null,"WMECO","Shelburne Falls","6F953-2015","01370",40,"Solar","22B5","2015-06-10","2015-07-17",{"$f":"NETWORKDAYS(I323,J323,MALegalHolidays)","v":26},9,17,"2015-07-20","2015-08-10",{"$f":"NETWORKDAYS(N323,O323,MALegalHolidays)","v":16},15,1,"2015-08-20","2015-10-05",{"$f":"NETWORKDAYS(S323,T323,MALegalHolidays)","v":32},22,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-10-07",null,"2015-08-01",null,"EXP",null,null,null,null,null," ","2015-12-23","2015-12-30","2015-12-30","app rvcd, need app fee, rcvd app fee, app complete, initial review, need infor rcvd info, need Supplemental Review sent out agreement.  Rcvd agreement, supp Rev started."]
[null,"WMECO","Easthampton","6A1251-2015","01027",244,"Solar","15A3","2015-06-15","2015-09-28",{"$f":"NETWORKDAYS(I324,J324,MALegalHolidays)","v":73},12,61,"2015-09-29",null,{"$f":"NETWORKDAYS(N324,O324,MALegalHolidays)","v":-30150},117," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-07-31",null,"STD",null,null,null,null,null," ",null,null,null,"IC sent new option, not sure what they will build, did not execute study, will now be parr of a group, cancelled by applicant"]
[null,"WMECO","Whately","6A1252-2015","01093",496,"Solar","18G8","2015-06-15","2015-07-17",{"$f":"NETWORKDAYS(I325,J325,MALegalHolidays)","v":23},18,5,"2015-07-20","2015-11-02",{"$f":"NETWORKDAYS(N325,O325,MALegalHolidays)","v":74},21,53,null,null,null,null," ",null,null,null,null," ","2015-11-03","2016-01-27",{"$f":"NETWORKDAYS(AC325,AD325,MALegalHolidays)","v":59},3,56,"2016-03-09",null,{"$f":"NETWORKDAYS(AH325,AI325,MALegalHolidays)","v":-30262},0," ","2016-02-04",null,"not supplied",null,"STD",null,null,null,null,null," ","2017-02-28","2017-03-01","2017-03-02"]
[null,"WMECO","Springfield","6S1174-2015","01104",150,"Solar","5J13","2015-06-15","2015-09-08",{"$f":"NETWORKDAYS(I326,J326,MALegalHolidays)","v":59},40,19,"2015-09-09","2016-06-01",{"$f":"NETWORKDAYS(N326,O326,MALegalHolidays)","v":187},95,92,null,null,null,null," ",null,null,null,null," ","2016-06-02","2016-08-23",{"$f":"NETWORKDAYS(AC326,AD326,MALegalHolidays)","v":59},0,59,"2016-09-14",null,{"$f":"NETWORKDAYS(AH326,AI326,MALegalHolidays)","v":-30397},null," ","2016-09-14",null,"2015-07-31",null,"STD",null,null,null,null,null," ","2017-10-05","2017-10-11","2017-10-26","Applicant not sure if they will proceed, requested extension."]
[null,"WMECO","Springfield","6S1175-2015","01104",284,"Solar","5J13","2015-06-15","2015-09-08",{"$f":"NETWORKDAYS(I327,J327,MALegalHolidays)","v":59},40,19,"2015-09-09","2016-06-01",{"$f":"NETWORKDAYS(N327,O327,MALegalHolidays)","v":187},95,92,null,null,null,null," ",null,null,null,null," ","2016-06-02","2016-08-23",{"$f":"NETWORKDAYS(AC327,AD327,MALegalHolidays)","v":59},0,59,"2016-09-14",null,{"$f":"NETWORKDAYS(AH327,AI327,MALegalHolidays)","v":-30397},null," ","2016-09-14",null,"1901-12-31",null,"STD",null,null,null,null,null," ","2018-01-17","2018-01-24","2018-01-30","Applicant not sure if they will proceed., sent 10 day notice of missed deadline."]
[null,"WMECO","Pittsfield","6B569-2015","01201",408,"Solar","19A8","2015-06-18","2015-09-29",{"$f":"NETWORKDAYS(I328,J328,MALegalHolidays)","v":72},25,47,"2015-09-30",null,{"$f":"NETWORKDAYS(N328,O328,MALegalHolidays)","v":-30151},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-07-31",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by Interconnecting Customer."]
[null,"WMECO","Becket","6B571-2015","01223",10,"Solar","19J6","2015-06-18","2015-07-22",{"$f":"NETWORKDAYS(I329,J329,MALegalHolidays)","v":24},23,1,"2015-07-23","2015-08-20",{"$f":"NETWORKDAYS(N329,O329,MALegalHolidays)","v":21},2,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-08-20",null,"08-2015",null,"EXP",null,null,null,null,null," ","2016-01-25","2016-01-25","2016-01-25"]
[null,"WMECO","Shelburne","6F969-2015","01370",16.7,"Solar","22B6","2015-06-18","2015-07-30",{"$f":"NETWORKDAYS(I330,J330,MALegalHolidays)","v":30},13,17,"2015-07-31",null,{"$f":"NETWORKDAYS(N330,O330,MALegalHolidays)","v":-30109},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Chesterfield","6F970-2015","01012",499,"Solar","18K3","2015-06-18","2015-10-06",{"$f":"NETWORKDAYS(I331,J331,MALegalHolidays)","v":77},1,76,"2015-10-07","2015-12-30",{"$f":"NETWORKDAYS(N331,O331,MALegalHolidays)","v":57},33,24,null,null,null,null," ",null,null,null,null," ","2015-12-31",null,{"$f":"NETWORKDAYS(AC331,AD331,MALegalHolidays)","v":-30213},null," ",null,null,null,null," ",null,null,"2015-10-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Chesterfield","6F971-2015","01012",499,"Solar","18K3","2015-06-18","2015-09-29",{"$f":"NETWORKDAYS(I332,J332,MALegalHolidays)","v":72},1,71,"2015-09-30","2015-12-30",{"$f":"NETWORKDAYS(N332,O332,MALegalHolidays)","v":62},33,29,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-09-09",{"$f":"NETWORKDAYS(AC332,AD332,MALegalHolidays)","v":182},59,123,"2016-09-12",null,{"$f":"NETWORKDAYS(AH332,AI332,MALegalHolidays)","v":-30395},null," ","2016-09-26",null,"2015-10-30",null,"COMP",null,null,null,null,null," ",null,null,null,"Impact Study Report and Detailed Study agreement sent to interconnecting Customer.  On 9/23/16 applicant submitted revisd app with Landowner info. Cancelled by applicant."]
[null,"WMECO","Chesterfield","6F972-2015","01012",499,"Solar","18K3","2015-06-18","2015-09-29",{"$f":"NETWORKDAYS(I333,J333,MALegalHolidays)","v":72},1,71,"2015-09-30","2015-12-30",{"$f":"NETWORKDAYS(N333,O333,MALegalHolidays)","v":62},33,29,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-09-09",{"$f":"NETWORKDAYS(AC333,AD333,MALegalHolidays)","v":182},59,123,"2016-09-12",null,{"$f":"NETWORKDAYS(AH333,AI333,MALegalHolidays)","v":-30395},null," ","2016-09-26",null,"2015-10-30",null,"COMP",null,null,null,null,null," ",null,null,null,"Impact Study Report and Detailed Study agreement sent to interconnecting Customer.  On 9/23/16 applicant submitted revisd app with Landowner info. Cancelled by applicant."]
[null,"WMECO","Easthampton","6A1270-2015","01027",27,"Solar","15A3","2015-06-19","2015-08-10",{"$f":"NETWORKDAYS(I334,J334,MALegalHolidays)","v":36},23,13,"2015-08-11","2015-11-10",{"$f":"NETWORKDAYS(N334,O334,MALegalHolidays)","v":64},0,64,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-11-10",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-12-15","2015-12-17","2015-12-18"]
[null,"WMECO","Blandford","6B572-2015","01008",499,"Solar","19J2","2015-06-19","2015-09-28",{"$f":"NETWORKDAYS(I335,J335,MALegalHolidays)","v":70},4,66,"2015-09-29",null,{"$f":"NETWORKDAYS(N335,O335,MALegalHolidays)","v":-30150},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Winter 2015",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by Interconnecting Customer."]
[null,"WMECO","Pittsfield","6B579-2015","01201",170,"Solar","30B2","2015-06-23","2015-09-08",{"$f":"NETWORKDAYS(I336,J336,MALegalHolidays)","v":54},34,20,"2015-09-09",null,{"$f":"NETWORKDAYS(N336,O336,MALegalHolidays)","v":-30136},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-07-31",null,"EXP",null,null,null,null,null," ",null,null,null,"was behind  apps in a group study, nwanted new service, customer cancelled service WR#, sent 10 day notice, no response, withdrawn"]
[null,"WMECO","Greenfield","6F980-2015","01301",450,"Diesel","21C4","2015-06-23","2015-09-29",{"$f":"NETWORKDAYS(I337,J337,MALegalHolidays)","v":69},17,52,"2015-09-30","2016-02-23",{"$f":"NETWORKDAYS(N337,O337,MALegalHolidays)","v":101},18,83,"2016-02-23","2016-10-05",{"$f":"NETWORKDAYS(S337,T337,MALegalHolidays)","v":162},5,157,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-10-06",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-12-07","2016-12-18","2016-12-19"]
[null,"WMECO","Plainfield","6F986-2015","01070",392,"Solar","18K3","2015-06-29","2015-09-29",{"$f":"NETWORKDAYS(I338,J338,MALegalHolidays)","v":65},0,65,"2015-09-30","2015-11-05",{"$f":"NETWORKDAYS(N338,O338,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-10-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Plainfield","6F987-2015","01070",499,"Solar","18K3","2015-06-29","2015-09-29",{"$f":"NETWORKDAYS(I339,J339,MALegalHolidays)","v":65},0,65,"2015-09-30","2015-11-05",{"$f":"NETWORKDAYS(N339,O339,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-10-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Sunderland","6A1298-2015","01375",242,"Solar","18G3","2015-07-02","2015-12-21",{"$f":"NETWORKDAYS(I340,J340,MALegalHolidays)","v":118},30,88,"2015-12-22","2016-01-28",{"$f":"NETWORKDAYS(N340,O340,MALegalHolidays)","v":27},9,18,null,null,null,null," ",null,null,null,null," ","2016-01-28","2016-04-28",{"$f":"NETWORKDAYS(AC340,AD340,MALegalHolidays)","v":66},0,66,null,null,null,null," ","2016-05-03",null,"winter 2015",null,"STD",null,null,null,null,null," ","2016-12-27","2016-12-28","2016-12-30","part of group, not sure what size to install, submitted options, other applicant cancelled"]
[null,"WMECO","Sunderland","6A1309-2015","01375",160,"Solar","18G3","2015-07-10","2015-12-21",{"$f":"NETWORKDAYS(I341,J341,MALegalHolidays)","v":113},25,88,"2015-12-22","2016-01-28",{"$f":"NETWORKDAYS(N341,O341,MALegalHolidays)","v":27},9,18,null,null,null,null," ",null,null,null,null," ","2016-01-28","2016-04-28",{"$f":"NETWORKDAYS(AC341,AD341,MALegalHolidays)","v":66},0,66,null,null,null,null," ",null,null,"winter 2015",null,"STD",null,null,null,null,null," ",null,null,null,"part of group, not sure what size to install, submitted options, cancelled by Int Cust"]
[null,"WMECO","Conway","6F1012-2015","01341",19.8,"Solar","38A1","2015-07-14","2015-08-07",{"$f":"NETWORKDAYS(I342,J342,MALegalHolidays)","v":19},6,13,"2015-08-10","2015-11-03",{"$f":"NETWORKDAYS(N342,O342,MALegalHolidays)","v":60},11,49,"2015-11-12","2015-11-30",{"$f":"NETWORKDAYS(S342,T342,MALegalHolidays)","v":12},0,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-07",null,"2015-09-01",null,"EXP",null,null,null,null,null," ","2016-03-04","2016-03-08","2016-03-08"]
[null,"WMECO","Easthampton","6A1329-2015","01027",20.5,"Solar","15A5","2015-07-15","2015-08-10",{"$f":"NETWORKDAYS(I343,J343,MALegalHolidays)","v":19},18,1,"2015-08-11","2015-10-15",{"$f":"NETWORKDAYS(N343,O343,MALegalHolidays)","v":46},0,46,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-11-10",null,"2015-10-05",null,"EXP",null,null,null,null,null," ","2015-12-18","2015-12-22","2015-12-22"]
[null,"WMECO","Bernardston ","6F1028-2015","01337",36,"Solar","21C1","2015-07-27","2015-09-23",{"$f":"NETWORKDAYS(I344,J344,MALegalHolidays)","v":42},5,37,"2015-09-24","2015-10-13",{"$f":"NETWORKDAYS(N344,O344,MALegalHolidays)","v":13},3,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-10-13",null,"Sept 2015",null,"EXP",null,null,null,null,null," ","2015-12-15","2015-12-17","2015-12-18"]
[null,"WMECO","Easthampton","6A1343-2015","01027",1980,"Solar","15A2","2015-07-30","2015-12-09",{"$f":"NETWORKDAYS(I345,J345,MALegalHolidays)","v":91},26,65,"2015-12-10",null,{"$f":"NETWORKDAYS(N345,O345,MALegalHolidays)","v":-30199},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-28",null,"STD",null,null,null,null,null," ",null,null,null,"Int Customer send Impact Study Agreement.  Sent 10 day notice because they did not execute agreement.  Int Cust cancelled their application.  "]
[null,"WMECO","Pittsfield","6B624-2015","01201",995,"Solar","30B7","2015-07-31","2015-08-06",{"$f":"NETWORKDAYS(I346,J346,MALegalHolidays)","v":5},3,2,"2015-08-07",null,{"$f":"NETWORKDAYS(N346,O346,MALegalHolidays)","v":-30114},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"10/1/2015",null,"STD",null,null,null,null,null," ",null,null,null,"Rcvd app and app fee, started rvw for completeness, app complete. Will require group Impact Study with project 6B553-2015. Held scoping meeting.  Sent out Impact Study agrmnt for signature. Cancelled"]
[null,"WMECO","Pittsfield","6B625-2015","01201",870,"Solar","30B3","2015-08-03","2015-10-06",{"$f":"NETWORKDAYS(I347,J347,MALegalHolidays)","v":46},13,33,"2015-10-07","2016-05-02",{"$f":"NETWORKDAYS(N347,O347,MALegalHolidays)","v":145},92,53,null,null,null,null," ",null,null,null,null," ","2016-05-03","2016-07-19",{"$f":"NETWORKDAYS(AC347,AD347,MALegalHolidays)","v":56},32,24,null,null,null,null," ",null,null,"12/1/2015",null,"STD",null,null,null,null,null," ",null,null,null,"Was in group. Group changed. New agreement sent out.  Cancelled by applicant."]
[null,"WMECO","West Springfield","6S1388-2015","01089",30,"Solar","21N6","2015-08-03","2015-09-23",{"$f":"NETWORKDAYS(I348,J348,MALegalHolidays)","v":37},19,18,"2015-09-24","2015-11-10",{"$f":"NETWORKDAYS(N348,O348,MALegalHolidays)","v":33},9,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-11-16",null,"Q3 2015",null,"EXP",null,null,null,null,null," ","2016-02-11","2016-02-17","2016-02-17"]
[null,"WMECO","Whately","6A1350-2015","01093",1115,"Solar","18G8","2015-08-04","2015-11-20",{"$f":"NETWORKDAYS(I349,J349,MALegalHolidays)","v":76},11,65,"2015-11-23","2016-04-28",{"$f":"NETWORKDAYS(N349,O349,MALegalHolidays)","v":112},51,61,null,null,null,null," ",null,null,null,null," ","2016-04-29","2016-08-31",{"$f":"NETWORKDAYS(AC349,AD349,MALegalHolidays)","v":89},1,88,"2016-10-31",null,{"$f":"NETWORKDAYS(AH349,AI349,MALegalHolidays)","v":-30430},null," ","2016-10-03",null,"2/28/16",null,"STD",null,null,null,null,null," ",null,null,"2020-10-01","on line"]
[null,"WMECO","Hinsdale","6B635-2015","01235",1484,"Solar","18C2","2015-08-11",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hadley","6A1366-2015","01035",32,"Solar","17K5","2015-08-12","2015-10-22",{"$f":"NETWORKDAYS(I351,J351,MALegalHolidays)","v":50},39,11,"2015-10-23","2015-11-03",{"$f":"NETWORKDAYS(N351,O351,MALegalHolidays)","v":8},0,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-11-10",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-01-27","2016-01-29","2016-01-29","App rcvd, need app fee check, rcvd check, reviewed for copleteness, app complete.  Sent out initial review.  Sent out Appl to Install.  Rcvd Comp Docs.  Sch Witness Test.  Performed Witness Test.  Cust Online."]
[null,"WMECO","Pittsfield","6B640-2015","01201",54,"Solar","30B2","2015-08-12","2015-09-23",{"$f":"NETWORKDAYS(I352,J352,MALegalHolidays)","v":30},5,25,"2015-09-24","2015-12-29",{"$f":"NETWORKDAYS(N352,O352,MALegalHolidays)","v":65},47,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-30",null,"2015-07-01",null,"EXP",null,null,null,null,null," ","2016-05-13","2016-05-13","2016-05-13"]
[null,"WMECO","Springfield","6S1435-2015","01104",140,"Solar","5J16","2015-08-13","2015-09-24",{"$f":"NETWORKDAYS(I353,J353,MALegalHolidays)","v":30},5,25,"2015-09-25","2016-02-05",{"$f":"NETWORKDAYS(N353,O353,MALegalHolidays)","v":92},19,73,null,null,null,null," ",null,null,null,null," ","2016-02-08","2016-05-05",{"$f":"NETWORKDAYS(AC353,AD353,MALegalHolidays)","v":64},0,64,"2016-10-06",null,{"$f":"NETWORKDAYS(AH353,AI353,MALegalHolidays)","v":-30413},null," ","2016-05-05",null,"2015-10-23",null,"STD",null,null,null,null,null," ","2017-09-20","2017-09-26","2017-10-06","Revised early ISA sent 9/12/16., with new Detailed Study Agreement."]
[null,"WMECO","Sandisfield","6B641-2015","01255",21.91,"Solar","19J4","2015-08-14","2015-09-24",{"$f":"NETWORKDAYS(I354,J354,MALegalHolidays)","v":29},27,2,"2015-09-25",null,{"$f":"NETWORKDAYS(N354,O354,MALegalHolidays)","v":-30148},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-10-13",null,"EXP",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Pittsfield","6B655-2015","01201",1.8,"Solar","30B7","2015-08-14","2015-09-23",{"$f":"NETWORKDAYS(I355,J355,MALegalHolidays)","v":28},21,7,"2015-09-23","2016-04-08",{"$f":"NETWORKDAYS(N355,O355,MALegalHolidays)","v":139},105,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-11",null,"09302015",null,"EXP",null,null,null,null,null," ","2017-05-16","2017-05-30","2017-05-30","small educational facility for students, addition"]
[null,"WMECO","Hatfield","6A1390-2015","01066",584,"Solar","18G6","2015-08-20","2015-11-17",{"$f":"NETWORKDAYS(I356,J356,MALegalHolidays)","v":61},4,57,"2015-11-18","2016-02-16",{"$f":"NETWORKDAYS(N356,O356,MALegalHolidays)","v":63},28,35,null,null,null,null," ",null,null,null,null," ","2016-02-17",null,{"$f":"NETWORKDAYS(AC356,AD356,MALegalHolidays)","v":-30247},null," ",null,null,null,null," ",null,null,"2015-05-01",null,"STD",null,null,null,null,null," ",null,null,null,"Project cancelled by Int Cust 3/24/16, said customer changed their mind."]
[null,"WMECO","Sandisfield","6B651-2015","01255",16.399999999999999,"Solar","19J4","2015-08-21","2015-10-27",{"$f":"NETWORKDAYS(I357,J357,MALegalHolidays)","v":46},41,5,"2015-10-28","2015-11-04",{"$f":"NETWORKDAYS(N357,O357,MALegalHolidays)","v":6},0,6,"2015-12-02","2015-12-03",{"$f":"NETWORKDAYS(S357,T357,MALegalHolidays)","v":2},0,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-04",null,"Sept 2015",null,"EXP",null,null,null,null,null," ","2015-12-22","2015-12-24","2015-12-24"]
[null,"WMECO","Plainfield","6F1072-2015","01070",1050,"Solar","18K3","2015-08-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-06-28",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Southwick","6S1476-2015","01077",18.399999999999999,"Solar","29A5","2015-08-24","2015-10-02",{"$f":"NETWORKDAYS(I359,J359,MALegalHolidays)","v":29},12,17,"2015-10-05","2016-03-24",{"$f":"NETWORKDAYS(N359,O359,MALegalHolidays)","v":120},95,25,"2016-03-25",null,{"$f":"NETWORKDAYS(S359,T359,MALegalHolidays)","v":-30274},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-10-24",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Feeding Hills","6S1481-2015","01030",17.25,"Solar","16C17","2015-08-25","2015-10-22",{"$f":"NETWORKDAYS(I360,J360,MALegalHolidays)","v":41},30,11,"2015-10-23","2015-10-28",{"$f":"NETWORKDAYS(N360,O360,MALegalHolidays)","v":4},0,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-10-30",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-12-11","2015-12-14","2015-12-14"]
[null,"WMECO","West Hatfield","6A1403-2015","01088",22.5,"Solar","18G5","2015-08-28","2015-10-22",{"$f":"NETWORKDAYS(I361,J361,MALegalHolidays)","v":38},27,11,"2015-10-22","2015-10-28",{"$f":"NETWORKDAYS(N361,O361,MALegalHolidays)","v":5},2,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-10-30",null,"not supplied",null,"EXP",null,null,null,null,null," ","2015-12-15","2015-12-16","2015-12-16"]
[null,"WMECO","Dalton","6B667-2015","01226",25,"Solar","18C1","2015-09-02","2015-11-05",{"$f":"NETWORKDAYS(I362,J362,MALegalHolidays)","v":45},33,12,"2015-11-06","2016-01-06",{"$f":"NETWORKDAYS(N362,O362,MALegalHolidays)","v":41},22,19,"2016-01-07","2016-01-13",{"$f":"NETWORKDAYS(S362,T362,MALegalHolidays)","v":5},2,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-01-13",null,"2015-09-25",null,"EXP",null,null,null,null,null," ","2016-06-27","2016-06-29","2016-06-29"]
[null,"WMECO","Easthampton","6A1411-2015","01027",2100,"Solar","15A5","2015-09-03",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-08-15",null,"EXP",null,null,null,null,null," ",null,null,null,"Applicant did not respond to requests for information.  Sent 10 day notice and tried calling.  Application withdrawn after two notices."]
[null,"WMECO","Feeding Hills","6S1520-2015","01030",5440,"Solar","30A6","2015-09-03",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-08-15",null,"EXP",null,null,null,null,null," ",null,null,null,"Applicant did not respond to requests for information.  Sent 10 day notice and tried calling.  Application withdrawn after two notices."]
[null,"WMECO","Pittsfield","6B670-2015","01201",1380,"Solar","30B7","2015-09-04","2015-09-17",{"$f":"NETWORKDAYS(I365,J365,MALegalHolidays)","v":9},2,7,"2015-09-17","2015-10-20",{"$f":"NETWORKDAYS(N365,O365,MALegalHolidays)","v":23},22,1,null,null,null,null," ",null,null,null,null," ","2015-10-21","2016-03-30",{"$f":"NETWORKDAYS(AC365,AD365,MALegalHolidays)","v":113},0,113,"2016-04-14",null,{"$f":"NETWORKDAYS(AH365,AI365,MALegalHolidays)","v":-30288},null," ","2016-04-25",null,"July 2016",null,"STD",null,null,null,null,null," ",null,null,"2018-04-17","Rcvd app and app fee, started rvw for completeness, app complete. Will require group Impact Study with project 6B553-2015.   Sent out Impact Study agrmnt for signature.   Impact Study Report and Detailed Study Agreement sent out to Customer.   Received payment for Detailed Study, 2 options"]
[null,"WMECO","Springfield","6S1550-2015","01109",1980,"Solar","5J18","2015-09-04",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-05-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Southampton","6A1417-2015","01073",2000,"Solar","15A1","2015-09-08","2015-11-09",{"$f":"NETWORKDAYS(I367,J367,MALegalHolidays)","v":44},35,9,"2015-11-10","2016-02-05",{"$f":"NETWORKDAYS(N367,O367,MALegalHolidays)","v":61},14,47,null,null,null,null," ",null,null,null,null," ","2016-02-05","2016-07-19",{"$f":"NETWORKDAYS(AC367,AD367,MALegalHolidays)","v":118},54,64,"2016-07-20","2017-04-21",{"$f":"NETWORKDAYS(AH367,AI367,MALegalHolidays)","v":198},145,53,"2017-04-28",null,"2016-08-15",null,"COMP",null,null,null,null,null," ",null,null,"2019-02-20","customer requested extension, application sold"]
[null,"WMECO","Savoy","6B673-2015","01256",2000,"Solar","18C1","2015-09-08","2015-11-09",{"$f":"NETWORKDAYS(I368,J368,MALegalHolidays)","v":44},17,27,"2015-11-10","2016-02-11",{"$f":"NETWORKDAYS(N368,O368,MALegalHolidays)","v":65},20,45,null,null,null,null," ",null,null,null,null," ","2016-02-12","2016-07-15",{"$f":"NETWORKDAYS(AC368,AD368,MALegalHolidays)","v":111},50,61,"2016-07-18","2017-04-20",{"$f":"NETWORKDAYS(AH368,AI368,MALegalHolidays)","v":199},145,54,"2017-05-10",null,"8/15/2016",null,"COMP",null,null,null,null,null," ",null,null,"2018-12-19","customer requested extension10 day extension, negotiated timeline, customer selected 2000 kW size to move forward with oin 7/19/16, Customer changed proprty lines, interconnection point changed from Griffin Hill Rd to Windsor Rd.  Application sold."]
[null,"WMECO","Hinsdale","6B674-2015","01235",1000,"Solar","18C2","2015-09-08","2015-11-16",{"$f":"NETWORKDAYS(I369,J369,MALegalHolidays)","v":48},27,21,"2015-11-17",null,{"$f":"NETWORKDAYS(N369,O369,MALegalHolidays)","v":-30183},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"8/15/2016",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated timeline, 20 days, customer submitted new options after complete. In group, group changed.  IC cancelled project 5/17/16."]
[null,"WMECO","Greenfield","6F1098-2015","01301",2000,"Solar","21C1","2015-09-08","2015-11-13",{"$f":"NETWORKDAYS(I370,J370,MALegalHolidays)","v":47},36,11,"2015-11-16","2016-01-07",{"$f":"NETWORKDAYS(N370,O370,MALegalHolidays)","v":37},22,15,null,null,null,null," ",null,null,null,null," ","2016-01-08","2016-05-13",{"$f":"NETWORKDAYS(AC370,AD370,MALegalHolidays)","v":91},29,62,"2016-10-31",null,{"$f":"NETWORKDAYS(AH370,AI370,MALegalHolidays)","v":-30430},null," ","2017-05-22",null,"2016-08-15",null,"COMP",null,null,null,null,null," ",null,null,"2019-01-25","In group with another applicant 6F915 who dropped out after Impact Study was sent (7/21/16). Stop dates in Impact Study due to decision needed from other applicant. Negotiated timeline for Impact Study at applicants request, another 20 days. Application sold."]
[null,"WMECO","Otis","6B685-2015","01253",76.650000000000006,"Solar","19J4","2015-09-14","2015-10-22",{"$f":"NETWORKDAYS(I371,J371,MALegalHolidays)","v":28},20,8,"2015-10-23","2015-11-09",{"$f":"NETWORKDAYS(N371,O371,MALegalHolidays)","v":12},0,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-10-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hinsdale","6B689-2015","01235",2000,"Solar","18C2","2015-09-15","2015-11-16",{"$f":"NETWORKDAYS(I372,J372,MALegalHolidays)","v":43},27,16,"2015-11-17","2016-08-30",{"$f":"NETWORKDAYS(N372,O372,MALegalHolidays)","v":204},152,52,null,null,null,null," ",null,null,null,null," ","2016-08-31","2017-03-08",{"$f":"NETWORKDAYS(AC372,AD372,MALegalHolidays)","v":136},40,96,"2017-03-09",null,{"$f":"NETWORKDAYS(AH372,AI372,MALegalHolidays)","v":-30523},null," ","2017-04-12",null,"2016-08-15",null,"STD",null,null,null,null,null," ",null,null,"2018-12-19","Negotiated timeline, 10 days and 15 days, customer submitted new options after complete. In group, group changed. 5/17/16 group changed again, no longer in group. Application sold."]
[null,"WMECO","Springfield","6S1577-2015","01119",16.7,"Solar","20A12","2015-09-18","2015-11-20",{"$f":"NETWORKDAYS(I373,J373,MALegalHolidays)","v":44},18,26,"2015-11-23","2015-12-21",{"$f":"NETWORKDAYS(N373,O373,MALegalHolidays)","v":20},17,3,"2015-12-22","2016-01-14",{"$f":"NETWORKDAYS(S373,T373,MALegalHolidays)","v":17},0,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-01-25",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-04-21","2016-04-27","2016-04-27"]
[null,"WMECO","Springfield","6S1588-2015","01107",5300,"Natural Gas","21S8","2015-09-22","2015-12-01",{"$f":"NETWORKDAYS(I374,J374,MALegalHolidays)","v":48},10,38,"2015-12-02","2016-02-22",{"$f":"NETWORKDAYS(N374,O374,MALegalHolidays)","v":58},18,40,"2016-02-23","2016-04-27",{"$f":"NETWORKDAYS(S374,T374,MALegalHolidays)","v":47},11,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-29",null,"June 2017",null,"EXP",null,null,null,null,null," ",null,null,"2018-04-06"]
[null,"WMECO","Southampton","6A1443-2015","01073",49.55,"Solar","15A1","2015-09-23","2015-11-03",{"$f":"NETWORKDAYS(I375,J375,MALegalHolidays)","v":29},20,9,"2015-11-04","2015-12-24",{"$f":"NETWORKDAYS(N375,O375,MALegalHolidays)","v":35},22,13,"2015-12-28","2016-02-29",{"$f":"NETWORKDAYS(S375,T375,MALegalHolidays)","v":46},3,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-03-01",null,"2015-10-12",null,"EXP",null,null,null,null,null," ","2016-09-09","2016-09-14","2016-09-14"]
[null,"WMECO","Lenox ","6B702-2015","01201",448,"Solar","17G3","2015-09-23","2015-11-02",{"$f":"NETWORKDAYS(I376,J376,MALegalHolidays)","v":28},3,25,"2015-11-03","2015-12-23",{"$f":"NETWORKDAYS(N376,O376,MALegalHolidays)","v":35},25,10,null,null,null,null," ",null,null,null,null," ","2015-12-24","2016-02-11",{"$f":"NETWORKDAYS(AC376,AD376,MALegalHolidays)","v":35},4,31,"2016-02-18",null,{"$f":"NETWORKDAYS(AH376,AI376,MALegalHolidays)","v":-30248},null," ","2016-02-11",null,"2016-03-31",null,"STD",null,null,null,null,null," ",null,null,"2017-04-12"]
[null,"WMECO","Southwick","6S1590-2015","01077",500,"Solar","29A5","2015-09-23","2015-12-01",{"$f":"NETWORKDAYS(I377,J377,MALegalHolidays)","v":47},7,40,"2015-12-02","2016-03-18",{"$f":"NETWORKDAYS(N377,O377,MALegalHolidays)","v":77},42,35,null,null,null,null," ",null,null,null,null," ","2016-03-21","2016-08-22",{"$f":"NETWORKDAYS(AC377,AD377,MALegalHolidays)","v":111},0,111,null,null,null,null," ","2016-08-22",null,"12/1/2015",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Gill","6F1134-2015","01354",1992,"Solar","21B8","2015-09-24","2015-11-04",{"$f":"NETWORKDAYS(I378,J378,MALegalHolidays)","v":29},3,{"$f":"IF(K378>0,K378-L378,\" \")","v":26},"2015-11-05","2016-02-18",{"$f":"NETWORKDAYS(N378,O378,MALegalHolidays)","v":73},9,{"$f":"IF(P378>0,P378-Q378,\" \")","v":64},null,null,null,null,{"$f":"IF(U378>0,U378-V378,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z378>0,Z378-AA378,\" \")","v":" "},"2016-02-19","2016-04-27",{"$f":"NETWORKDAYS(AC378,AD378,MALegalHolidays)","v":49},9,{"$f":"IF(AE378>0,AE378-AF378,\" \")","v":40},"2016-05-06",null,{"$f":"NETWORKDAYS(AH378,AI378,MALegalHolidays)","v":-30304},null,{"$f":"IF(AJ378>0,AJ378-AK378,\" \")","v":" "},"2016-04-27",null,"2016-03-01",null,"COMP",null,null,null,null,null,{"$f":"IF(AU378>0,AU378-AV378,\" \")","v":" "},"2017-12-29","2017-12-05","2018-01-18","App and fee rcvd and acknowledged. Review for app complete, need UL cert, app complete, sent out initial review, sent out Impact Study agreement, rcvd, signed Impact tudy Agreement, received check for Imapact study, Impact Study started, Impact Study report and Detailed Study agreement sent to Customer. sent Approval to Install to customer.  held site visit, Customer needs to take out a request for service."]
[null,"WMECO","Greenfield","6F1135-2015","01301",43.8,"Solar","22B7","2015-09-25","2015-10-08",{"$f":"NETWORKDAYS(I379,J379,MALegalHolidays)","v":10},5,5,"2015-10-09","2016-02-04",{"$f":"NETWORKDAYS(N379,O379,MALegalHolidays)","v":81},50,31,"2016-02-04","2016-02-17",{"$f":"NETWORKDAYS(S379,T379,MALegalHolidays)","v":10},1,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-17",null,"Jan 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"notice sent to applicant to execute ISA, withdrawn after applicant did not pay for system modifications and fully execute ISA"]
[null,"WMECO","Southwick","6S1604-2015","01077",2000,"Solar","29A5","2015-09-25","2015-12-04",{"$f":"NETWORKDAYS(I380,J380,MALegalHolidays)","v":48},26,22,"2015-12-07",null,{"$f":"NETWORKDAYS(N380,O380,MALegalHolidays)","v":-30196},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"8/15/2016",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","West Springfield","6S1610-2015","01089",112,"Solar","21N5","2015-09-28","2015-12-17",{"$f":"NETWORKDAYS(I381,J381,MALegalHolidays)","v":56},49,7,"2015-12-18",null,{"$f":"NETWORKDAYS(N381,O381,MALegalHolidays)","v":-30205},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 31",null,"EXP",null,null,null,null,null," ",null,null,null,"Withdrawn after no response to calls and emails."]
[null,"WMECO","Plainfield","6F1149-2016","01070",499,"Solar","18K3","2015-10-02","2015-10-22",{"$f":"NETWORKDAYS(I382,J382,MALegalHolidays)","v":14},5,9,"2015-10-23","2015-11-05",{"$f":"NETWORKDAYS(N382,O382,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Plainfield","6F1150-2015","01070",1990,"Solar","18K3","2015-10-05","2015-10-07",{"$f":"NETWORKDAYS(I383,J383,MALegalHolidays)","v":3},0,3,"2015-10-08","2015-12-30",{"$f":"NETWORKDAYS(N383,O383,MALegalHolidays)","v":56},33,23,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-09-09",{"$f":"NETWORKDAYS(AC383,AD383,MALegalHolidays)","v":182},59,123,"2016-09-12",null,{"$f":"NETWORKDAYS(AH383,AI383,MALegalHolidays)","v":-30395},null," ",null,null,"2016-04-30",null,"STD",null,null,null,null,null," ",null,null,null,"Impact Study Report and Detailed Study agreement sent to interconnecting Customer, customer granted 10 day extension, negotiated timeline 10 days, cancelled"]
[null,"WMECO","Plainfield","6F1151-2015","01070",1990,"Solar","18K3","2015-10-05","2015-10-07",{"$f":"NETWORKDAYS(I384,J384,MALegalHolidays)","v":3},0,3,"2015-10-08","2015-12-30",{"$f":"NETWORKDAYS(N384,O384,MALegalHolidays)","v":56},33,23,null,null,null,null," ",null,null,null,null," ","2015-12-31","2016-09-09",{"$f":"NETWORKDAYS(AC384,AD384,MALegalHolidays)","v":182},59,123,"2016-09-12",null,{"$f":"NETWORKDAYS(AH384,AI384,MALegalHolidays)","v":-30395},null," ","2016-12-22",null,"2016-04-30",null,"COMP",null,null,null,null,null," ",null,null,"2019-02-15","Impact Study Report and Detailed Study agreement sent to interconnecting Customer.  An applicant dropped out of the group so the Impact Study was reevaluated.  Two applicants cancelled 1/20/17, Detailed Study and system mod costs need to be recalculated."]
[null,"WMECO","Amherst","6A1467-2015","01002",15.3,"Solar","17K2","2015-10-06","2015-11-23",{"$f":"NETWORKDAYS(I385,J385,MALegalHolidays)","v":33},5,28,"2015-11-24","2016-03-02",{"$f":"NETWORKDAYS(N385,O385,MALegalHolidays)","v":70},52,18,"2016-03-03",null,{"$f":"NETWORKDAYS(S385,T385,MALegalHolidays)","v":-30258},9," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-12-05",null,"EXP",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Hatfield","6A1468-2015","01038",900,"Solar","18G5","2015-10-06","2016-01-13",{"$f":"NETWORKDAYS(I386,J386,MALegalHolidays)","v":68},24,44,"2016-01-14",null,{"$f":"NETWORKDAYS(N386,O386,MALegalHolidays)","v":-30223},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-11-30",null,"STD",null,null,null,null,null," ",null,null,null,"On hold behind 6A935-2014. In group with 6A1528-2015.  Cancelled by applicant."]
[null,"WMECO","Springfield","6S1673-2015","01102",1000,"Diesel","21S7  21S3 ","2015-10-09","2016-02-23",{"$f":"NETWORKDAYS(I387,J387,MALegalHolidays)","v":94},51,43,"2016-02-24","2016-04-04",{"$f":"NETWORKDAYS(N387,O387,MALegalHolidays)","v":29},17,12,"2016-04-05","2016-04-12",{"$f":"NETWORKDAYS(S387,T387,MALegalHolidays)","v":6},0,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-13",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Whately","6A1481-2015","01093",2000,"Solar","18G8","2015-10-15","2015-12-11",{"$f":"NETWORKDAYS(I388,J388,MALegalHolidays)","v":40},5,35,"2015-12-14",null,{"$f":"NETWORKDAYS(N388,O388,MALegalHolidays)","v":-30201},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Springfield","6S1680-2015","01128",600,"Diesel","20A34","2015-10-15","2016-01-20",{"$f":"NETWORKDAYS(I389,J389,MALegalHolidays)","v":67},11,56,"2016-01-21","2016-04-14",{"$f":"NETWORKDAYS(N389,O389,MALegalHolidays)","v":61},49,12,"2016-04-15","2016-09-08",{"$f":"NETWORKDAYS(S389,T389,MALegalHolidays)","v":105},10,95,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-09-09",null,null,null,"EXP",null,null,null,null,null," ",null,null,"2018-04-25"]
[null,"WMECO","Agawam","6S1687-2015","01001",999,"Solar","30A3","2015-10-19","2015-12-07",{"$f":"NETWORKDAYS(I390,J390,MALegalHolidays)","v":34},2,32,"2015-12-08",null,{"$f":"NETWORKDAYS(N390,O390,MALegalHolidays)","v":-30197},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Agawam","6S1697-2015","01001",500,"Solar","16C16","2015-10-21","2015-12-22",{"$f":"NETWORKDAYS(I391,J391,MALegalHolidays)","v":43},41,2,"2015-12-23","2016-04-22",{"$f":"NETWORKDAYS(N391,O391,MALegalHolidays)","v":87},40,47,null,null,null,null," ",null,null,null,null," ","2016-04-25","2016-08-15",{"$f":"NETWORKDAYS(AC391,AD391,MALegalHolidays)","v":81},0,81,null,null,null,null," ",null,null,"2016-08-11",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant, never executed Detailed Study Agreement"]
[null,"WMECO","Ludlow","6S1698-2015","01056",311,"Solar","19S2","2015-10-21","2015-12-02",{"$f":"NETWORKDAYS(I392,J392,MALegalHolidays)","v":29},5,24,"2015-12-03","2016-02-18",{"$f":"NETWORKDAYS(N392,O392,MALegalHolidays)","v":55},43,12,null,null,null,null," ",null,null,null,null," ","2016-02-19","2016-05-11",{"$f":"NETWORKDAYS(AC392,AD392,MALegalHolidays)","v":59},0,59,null,null,null,null," ","2016-05-11",null,"2016-08-11",null,"STD",null,null,null,null,null," ",null,null,null,"part of group, negotiated timeline due to timing ot submitted option, cancelled by applicant"]
[null,"WMECO","Agawam","6S1699-2015","01001",500,"Solar","16C16","2015-10-21","2016-01-20",{"$f":"NETWORKDAYS(I393,J393,MALegalHolidays)","v":63},1,62,"2016-01-21","2016-04-22",{"$f":"NETWORKDAYS(N393,O393,MALegalHolidays)","v":67},40,27,null,null,null,null," ",null,null,null,null," ","2016-04-25","2016-08-15",{"$f":"NETWORKDAYS(AC393,AD393,MALegalHolidays)","v":81},0,81,null,null,null,null," ",null,null,"2016-08-11",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant, never executed Detailed Study Agreement"]
[null,"WMECO","Ludlow","6S1797-2015","01056",16.7,"Solar","19S1","2015-10-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-11-20",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Buckland","6F1201-2015","01338",16.7,"Solar","38A1","2015-10-28","2015-11-30",{"$f":"NETWORKDAYS(I395,J395,MALegalHolidays)","v":22},18,4,"2015-12-01","2015-12-15",{"$f":"NETWORKDAYS(N395,O395,MALegalHolidays)","v":11},5,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-15",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-03-07","2016-03-09","2016-03-09"]
[null,"WMECO","Montague","6F1203-2015","01351",408,"Solar","21C3","2015-10-28","2016-01-27",{"$f":"NETWORKDAYS(I396,J396,MALegalHolidays)","v":63},3,60,"2016-01-28","2016-06-10",{"$f":"NETWORKDAYS(N396,O396,MALegalHolidays)","v":97},35,62,null,null,null,null," ",null,null,null,null," ","2016-06-13","2016-08-24",{"$f":"NETWORKDAYS(AC396,AD396,MALegalHolidays)","v":53},null,53,null,null,null,null," ",null,null,"June 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Part of group study. One applicant cancelled their project so group changed.  Applicant cancelled this project."]
[null,"WMECO","Springfield","6S1730-2015","01108",299.16000000000003,"Solar","22H17","2015-10-29","2016-03-08",{"$f":"NETWORKDAYS(I397,J397,MALegalHolidays)","v":91},28,63,"2016-03-09",null,{"$f":"NETWORKDAYS(N397,O397,MALegalHolidays)","v":-30262},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-03-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Montague","6F1208-2015","01351",1992,"Solar","21C3","2015-10-30","2016-01-27",{"$f":"NETWORKDAYS(I398,J398,MALegalHolidays)","v":61},1,60,"2016-01-28","2016-06-10",{"$f":"NETWORKDAYS(N398,O398,MALegalHolidays)","v":97},35,62,null,null,null,null," ",null,null,null,null," ","2016-06-13","2016-08-24",{"$f":"NETWORKDAYS(AC398,AD398,MALegalHolidays)","v":53},0,53,null,null,null,null," ",null,null,"June 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Part of group study. One applicant cancelled their project so group changed.  Applicant cancelled this project."]
[null,"WMECO","Montague","6F1209-2015","01351",4176,"Solar","21C2","2015-10-30","2016-02-16",{"$f":"NETWORKDAYS(I399,J399,MALegalHolidays)","v":75},11,64,"2016-02-17","2016-06-10",{"$f":"NETWORKDAYS(N399,O399,MALegalHolidays)","v":83},35,48,null,null,null,null," ",null,null,null,null," ","2016-06-13","2016-08-24",{"$f":"NETWORKDAYS(AC399,AD399,MALegalHolidays)","v":53},0,53,"2016-11-08",null,{"$f":"NETWORKDAYS(AH399,AI399,MALegalHolidays)","v":-30436},null," ","2016-09-23",null,"June 2016",null,"COMP",null,null,null,null,null," ",null,null,"2018-09-24","Part of group study. One applicant cancelled their project so group changed. Customer submitted new option. Negotiated 10 days for review.  Other two applicants cancelled their projects after the group Impact Study. Projetc to be 3rd party owned as of April 2017"]
[null,"WMECO","Ashfield","6F1210-2015","01330",45.6,"Solar","38A1","2015-11-02","2015-11-19",{"$f":"NETWORKDAYS(I400,J400,MALegalHolidays)","v":13},7,6,"2015-11-20","2016-01-19",{"$f":"NETWORKDAYS(N400,O400,MALegalHolidays)","v":41},17,24,"2016-01-20","2016-01-29",{"$f":"NETWORKDAYS(S400,T400,MALegalHolidays)","v":8},0,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-03",null,"Nov 2015",null,"EXP",null,null,null,null,null," ","2016-05-26","2016-05-27","2016-05-27"]
[null,"WMECO","Longmeadow","6S1804-2015","01106",18,"Solar","22H17","2015-11-03","2015-12-15",{"$f":"NETWORKDAYS(I401,J401,MALegalHolidays)","v":29},12,17,"2015-12-15","2015-12-17",{"$f":"NETWORKDAYS(N401,O401,MALegalHolidays)","v":3},2,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-17",null,"2015-12-26",null,"EXP",null,null,null,null,null," ","2016-06-20","2016-06-27","2016-06-27"]
[null,"WMECO","Southwick","6S1756-2015","01077",478,"Solar","29A5","2015-11-06","2016-01-20",{"$f":"NETWORKDAYS(I402,J402,MALegalHolidays)","v":51},21,30,"2016-01-20","2016-03-18",{"$f":"NETWORKDAYS(N402,O402,MALegalHolidays)","v":43},40,3,null,null,null,null," ",null,null,null,null," ","2016-03-21","2016-08-22",{"$f":"NETWORKDAYS(AC402,AD402,MALegalHolidays)","v":111},0,111,null,null,null,null," ","2016-08-22",null,"2016-02-03",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","West Hatfield","6A1528-2015","01088",292,"Solar","18G5","2015-11-09","2015-12-22",{"$f":"NETWORKDAYS(I403,J403,MALegalHolidays)","v":30},12,18,"2015-12-23",null,{"$f":"NETWORKDAYS(N403,O403,MALegalHolidays)","v":-30208},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2015-03-15",null,"STD",null,null,null,null,null," ",null,null,null,"On hold behind 6A935-2014.  In group with 6A1468-2015.  Applicant cancelled."]
[null,"WMECO","Plainfield","6F1233-2015","01070",22.8,"Solar","18K3","2015-11-10","2015-11-23",{"$f":"NETWORKDAYS(I404,J404,MALegalHolidays)","v":9},4,5,"2015-11-24","2015-12-15",{"$f":"NETWORKDAYS(N404,O404,MALegalHolidays)","v":15},4,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2015-12-15",null,"Nov 2015",null,"EXP",null,null,null,null,null," ","2016-04-01","2016-04-05","2016-04-05"]
[null,"WMECO","Otis","6B789-2015","01253",2000,"Solar","19J4","2015-11-13","2016-02-02",{"$f":"NETWORKDAYS(I405,J405,MALegalHolidays)","v":56},7,49,"2016-02-03",null,{"$f":"NETWORKDAYS(N405,O405,MALegalHolidays)","v":-30237},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-07-15",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn after no response to email notices and voice mails"]
[null,"WMECO","Feeding Hills","6S1795-2015","01030",15.3,"Solar","16C17","2015-11-13","2015-12-04",{"$f":"NETWORKDAYS(I406,J406,MALegalHolidays)","v":15},8,7,"2015-12-07","2015-12-10",{"$f":"NETWORKDAYS(N406,O406,MALegalHolidays)","v":4},0,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-01-08",null,"2016-01-13",null,"EXP",null,null,null,null,null," ","2016-03-23","2016-04-11","2016-04-11"]
[null,"WMECO","South Deerfield","6F1241-2015","01373",1992,"Solar","18G3","2015-11-16","2015-12-14",{"$f":"NETWORKDAYS(I407,J407,MALegalHolidays)","v":20},1,19,"2015-12-15",null,{"$f":"NETWORKDAYS(N407,O407,MALegalHolidays)","v":-30202},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","South Deerfield","6F1242-2015","01373",1992,"Solar","18G3","2015-11-16","2015-12-14",{"$f":"NETWORKDAYS(I408,J408,MALegalHolidays)","v":20},1,19,"2015-12-15",null,{"$f":"NETWORKDAYS(N408,O408,MALegalHolidays)","v":-30202},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Springfield","6S1796-2015","01104",1985,"Solar","5J18","2015-11-16","2015-12-21",{"$f":"NETWORKDAYS(I409,J409,MALegalHolidays)","v":25},1,24,"2015-12-22","2016-02-23",{"$f":"NETWORKDAYS(N409,O409,MALegalHolidays)","v":45},17,28,null,null,null,null," ",null,null,null,null," ","2016-02-24","2016-05-02",{"$f":"NETWORKDAYS(AC409,AD409,MALegalHolidays)","v":49},0,49,"2016-05-12",null,{"$f":"NETWORKDAYS(AH409,AI409,MALegalHolidays)","v":-30308},7," ","2016-05-02",null,"2016-05-31",null,"STD",null,null,null,null,null," ","2017-06-19","2017-06-26","2017-06-26"]
[null,"WMECO","Hadley","6A1553-2015","01035",570,"Biogas","19B15","2015-11-20","2016-02-24",{"$f":"NETWORKDAYS(I410,J410,MALegalHolidays)","v":67},63,4,"2016-02-25","2016-04-20",{"$f":"NETWORKDAYS(N410,O410,MALegalHolidays)","v":40},36,4,null,null,null,null," ",null,null,null,null," ","2016-04-21","2016-07-11",{"$f":"NETWORKDAYS(AC410,AD410,MALegalHolidays)","v":58},45,13,"2016-08-22",null,{"$f":"NETWORKDAYS(AH410,AI410,MALegalHolidays)","v":-30380},null," ","2016-08-17",null,"4/30/2016",null,"STD",null,null,null,null,null," ","2017-06-30","2017-07-13","2017-07-13","On hold behind a group impact study through 4/19/16."]
[null,"WMECO","Whately","6A1560-2015","01093",504,"Solar","18G8","2015-11-24","2015-12-16",{"$f":"NETWORKDAYS(I411,J411,MALegalHolidays)","v":16},3,13,"2015-12-17","2016-04-28",{"$f":"NETWORKDAYS(N411,O411,MALegalHolidays)","v":95},51,44,null,null,null,null," ",null,null,null,null," ","2016-04-29","2016-08-31",{"$f":"NETWORKDAYS(AC411,AD411,MALegalHolidays)","v":89},null,89,null,null,null,null," ",null,null,"March 2016",null,"STD",null,null,null,null,null," ",null,null,null,"Group changed, new study agreement sent out. Application cancelled by applicant."]
[null,"WMECO","Pittsfield","6B807-2015","01201",72,"Solar","19A7","2015-12-01","2016-01-06",{"$f":"NETWORKDAYS(I412,J412,MALegalHolidays)","v":26},5,21,"2016-01-07","2016-02-10",{"$f":"NETWORKDAYS(N412,O412,MALegalHolidays)","v":25},11,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-10",null,"1st qtr 2016",null,"EXP",null,null,null,null,null," ","2016-05-20","2016-05-24","2016-05-24"]
[null,"WMECO","Whately","6A1570-2015","01093",2000,"Solar","18G8","2015-12-02","2015-12-11",{"$f":"NETWORKDAYS(I413,J413,MALegalHolidays)","v":8},0,8,"2015-12-14","2016-04-28",{"$f":"NETWORKDAYS(N413,O413,MALegalHolidays)","v":98},51,47,null,null,null,null," ",null,null,null,null," ","2016-04-29","2016-08-31",{"$f":"NETWORKDAYS(AC413,AD413,MALegalHolidays)","v":89},7,82,"2016-10-31",null,{"$f":"NETWORKDAYS(AH413,AI413,MALegalHolidays)","v":-30430},null," ","2016-10-03",null,"Sept 2016",null,"STD",null,null,null,null,null," ",null,null,"2019-12-20","on line"]
[null,"WMECO","Lee","6B809-2015","01238",2000,"Solar","16B5","2015-12-03","2016-02-11",{"$f":"NETWORKDAYS(I414,J414,MALegalHolidays)","v":50},9,41,"2016-02-12","2016-04-04",{"$f":"NETWORKDAYS(N414,O414,MALegalHolidays)","v":37},12,25,null,null,null,null," ",null,null,null,null," ","2016-04-05","2016-08-05",{"$f":"NETWORKDAYS(AC414,AD414,MALegalHolidays)","v":89},73,16,null,null,null,null," ",null,null,"2016-08-01",null,"STD",null,null,null,null,null," ",null,null,null,"IC requested 55 day extension in I.S., extension granted, study increases by 18 days in length.  Impact Study report sent out.  Cust ext - need to send out Detailed Study agreement, waiting for information.  Application withdrawn after applicant did not move forward."]
[null,"WMECO","South Deerfield","6F1262-2015","01373",452,"Solar","15E1","2015-12-04","2016-02-02",{"$f":"NETWORKDAYS(I415,J415,MALegalHolidays)","v":42},2,40,"2016-02-03",null,{"$f":"NETWORKDAYS(N415,O415,MALegalHolidays)","v":-30237},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-03-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by IC, had sent notice that they missed deadline to execute Impact Study Agreement"]
[null,"WMECO","Easthampton","6A1578-2015","01027",496,"Solar","15A2","2015-12-09","2016-01-28",{"$f":"NETWORKDAYS(I416,J416,MALegalHolidays)","v":36},25,11,"2016-01-29","2016-06-03",{"$f":"NETWORKDAYS(N416,O416,MALegalHolidays)","v":91},49,42,null,null,null,null," ",null,null,null,null," ","2016-06-06","2016-09-23",{"$f":"NETWORKDAYS(AC416,AD416,MALegalHolidays)","v":80},0,80,null,null,null,null," ","2016-09-23",null,"June 2016",null,"COMP",null,null,null,null,null," ",null,null,null,"Group changed, first applicant dropped out, another project was added.  Sent Detailed Study Agreement, reminder to execute agreement, sent 10 day notice.  No response from applicant, called them and they thought they would cancel their application.  No response so withdrew application."]
[null,"WMECO","Indian Orchard","6S1915-2015","01151",1931.4,"Solar","27A12","2015-12-15","2016-02-10",{"$f":"NETWORKDAYS(I417,J417,MALegalHolidays)","v":41},18,23,"2016-02-11","2016-03-17",{"$f":"NETWORKDAYS(N417,O417,MALegalHolidays)","v":26},12,14,null,null,null,null," ",null,null,null,null," ","2016-03-18","2016-08-08",{"$f":"NETWORKDAYS(AC417,AD417,MALegalHolidays)","v":102},17,85,null,null,null,null," ","2016-08-12",null,"2015-08-01",null,"STD",null,null,null,null,null," ","2017-02-10","2017-02-16","2017-02-16","applicant submitted a third option, revised study, had to do a second Witness Test"]
[null,"WMECO","Hadley","6A1588-2015","01035",1995.4,"Solar","17K6","2015-12-16","2016-04-15",{"$f":"NETWORKDAYS(I418,J418,MALegalHolidays)","v":87},42,45,"2016-04-19","2016-08-12",{"$f":"NETWORKDAYS(N418,O418,MALegalHolidays)","v":84},51,33,null,null,null,null," ",null,null,null,null," ","2016-08-15","2016-12-01",{"$f":"NETWORKDAYS(AC418,AD418,MALegalHolidays)","v":79},0,79,"2017-01-05",null,{"$f":"NETWORKDAYS(AH418,AI418,MALegalHolidays)","v":-30478},null," ","2017-04-14",null,"Sept 2016",null,"COMP",null,null,null,null,null," ",null,null,"2020-01-16","on line"]
[null,"WMECO","Hadley","6A1589-2015","01035",1995.4,"Solar","17K1","2015-12-16","2016-04-15",{"$f":"NETWORKDAYS(I419,J419,MALegalHolidays)","v":87},42,45,"2016-04-19","2016-08-12",{"$f":"NETWORKDAYS(N419,O419,MALegalHolidays)","v":84},51,33,null,null,null,null," ",null,null,null,null," ","2016-08-15","2017-01-27",{"$f":"NETWORKDAYS(AC419,AD419,MALegalHolidays)","v":120},24,96,"2017-02-21",null,{"$f":"NETWORKDAYS(AH419,AI419,MALegalHolidays)","v":-30511},null," ","2017-04-14",null,"Sept 2016",null,"COMP",null,null,null,null,null," ",null,null,"2020-01-16","on line"]
[null,"WMECO","Amherst","6A1599-2015","01002",19.3,"Solar","17K8","2015-12-16","2016-01-21",{"$f":"NETWORKDAYS(I420,J420,MALegalHolidays)","v":26},13,13,"2016-01-21","2016-02-08",{"$f":"NETWORKDAYS(N420,O420,MALegalHolidays)","v":13},9,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-08",null,"02/16/2016",null,"EXP",null,null,null,null,null," ","2016-11-30","2016-12-01","2016-12-01"]
[null,"WMECO","Hinsdale","6B826-2015","01235",1988,"Solar","18C2","2015-12-16","2016-02-23",{"$f":"NETWORKDAYS(I421,J421,MALegalHolidays)","v":49},16,33,"2016-02-24","2016-06-10",{"$f":"NETWORKDAYS(N421,O421,MALegalHolidays)","v":78},37,41,null,null,null,null," ",null,null,null,null," ","2016-06-13","2016-08-10",{"$f":"NETWORKDAYS(AC421,AD421,MALegalHolidays)","v":43},0,43,"2016-09-09",null,{"$f":"NETWORKDAYS(AH421,AI421,MALegalHolidays)","v":-30394},null," ","2016-08-19",null,"2015-09-01",null,"STD",null,null,null,null,null," ","2017-11-17","2017-11-20","2017-11-21","Negotiated timeline, 20 days for review, customer submitted second option after already deemed complete. In group, group changed, second study agreement sent out. 5/17/16 group changed again. JEversource field checked the installed equipment prior to the Witness Test.  Customer performed his own Witness Test and sent certified info."]
[null,"WMECO","Amherst","6A1600-2015","01006",16.7,"Solar","18G7","2015-12-18","2016-01-07",{"$f":"NETWORKDAYS(I422,J422,MALegalHolidays)","v":14},8,6,"2016-01-08","2016-02-10",{"$f":"NETWORKDAYS(N422,O422,MALegalHolidays)","v":24},21,3,"2016-02-11","2016-02-28",{"$f":"NETWORKDAYS(S422,T422,MALegalHolidays)","v":12},0,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-29",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by customer"]
[null,"WMECO","Feeding Hills","6S1953-2015","01030",16.399999999999999,"Solar","16C17","2015-12-23","2016-01-06",{"$f":"NETWORKDAYS(I423,J423,MALegalHolidays)","v":10},1,9,"2016-01-06","2016-01-06",{"$f":"NETWORKDAYS(N423,O423,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-01",null,"2016-02-16",null,"EXP",null,null,null,null,null," ","2016-08-15","2016-08-23","2016-08-23"]
[null,"WMECO","Middlefield","6F1294-2015","01243",32.85,"Solar","18C2","2015-12-24","2016-01-19",{"$f":"NETWORKDAYS(I424,J424,MALegalHolidays)","v":18},7,11,"2016-01-19","2016-07-15",{"$f":"NETWORKDAYS(N424,O424,MALegalHolidays)","v":129},98,31,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-07-15",null,"2015-12-31",null,"EXP",null,null,null,null,null," ","2016-09-07","2016-09-13","2016-09-13"]
[null,"WMECO","Amherst","6A1612-2015","01003",154,"Solar","18G2","2015-12-28","2016-01-12",{"$f":"NETWORKDAYS(I425,J425,MALegalHolidays)","v":12},6,6,"2016-01-13","2016-03-02",{"$f":"NETWORKDAYS(N425,O425,MALegalHolidays)","v":36},33,3,"2016-03-03","2016-04-21",{"$f":"NETWORKDAYS(S425,T425,MALegalHolidays)","v":36},2,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-22",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by customer"]
[null,"WMECO","Springfield","6S1979-2015","01129",343,"Solar","20A23","2015-12-28","2016-01-28",{"$f":"NETWORKDAYS(I426,J426,MALegalHolidays)","v":24},20,4,"2016-01-29",null,{"$f":"NETWORKDAYS(N426,O426,MALegalHolidays)","v":-30234},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn after sending 10 day notice that Impact Study was not executed.  Called IC who said they were not sure if or when the customer would decide to install generation."]
[null,"WMECO","Feeding Hills","6S1978-2015","01030",20.925000000000001,"Solar","16C17","2015-12-29","2016-01-20",{"$f":"NETWORKDAYS(I427,J427,MALegalHolidays)","v":17},9,8,"2016-01-21","2016-02-17",{"$f":"NETWORKDAYS(N427,O427,MALegalHolidays)","v":20},17,3,"2016-02-18",null,{"$f":"NETWORKDAYS(S427,T427,MALegalHolidays)","v":-30248},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B851-2016","01201",1000,"Solar","30B7","2016-01-04","2016-04-14",{"$f":"NETWORKDAYS(I428,J428,MALegalHolidays)","v":74},38,36,"2016-04-15","2016-05-16",{"$f":"NETWORKDAYS(N428,O428,MALegalHolidays)","v":22},13,9,null,null,null,null," ",null,null,null,null," ","2016-05-17","2016-08-10",{"$f":"NETWORKDAYS(AC428,AD428,MALegalHolidays)","v":62},0,62,"2016-08-31",null,{"$f":"NETWORKDAYS(AH428,AI428,MALegalHolidays)","v":-30387},null," ","2016-08-15",null,"not supplied",null,"STD",null,null,null,null,null," ",null,null,"2017-11-20","Was on hold behind first group study on circuit."]
[null,"WMECO","Hancock","6B852-2016","01237",2000,"Solar","30B7","2016-01-04","2016-04-14",{"$f":"NETWORKDAYS(I429,J429,MALegalHolidays)","v":74},38,36,"2016-04-15","2016-05-16",{"$f":"NETWORKDAYS(N429,O429,MALegalHolidays)","v":22},13,9,null,null,null,null," ",null,null,null,null," ","2016-05-17","2016-08-10",{"$f":"NETWORKDAYS(AC429,AD429,MALegalHolidays)","v":62},0,62,"2016-08-31",null,{"$f":"NETWORKDAYS(AH429,AI429,MALegalHolidays)","v":-30387},null," ","2016-08-15",null,"not supplied",null,"STD",null,null,null,null,null," ",null,null,"2017-11-20","Was on hold behind first group study on circuit."]
[null,"WMECO","Hancock","6B853-2016","01201",2000,"Solar","30B7","2016-01-04","2016-04-14",{"$f":"NETWORKDAYS(I430,J430,MALegalHolidays)","v":74},38,36,"2016-04-15","2016-05-16",{"$f":"NETWORKDAYS(N430,O430,MALegalHolidays)","v":22},13,9,null,null,null,null," ",null,null,null,null," ","2016-05-17","2016-08-10",{"$f":"NETWORKDAYS(AC430,AD430,MALegalHolidays)","v":62},0,62,"2016-08-31",null,{"$f":"NETWORKDAYS(AH430,AI430,MALegalHolidays)","v":-30387},null," ","2016-08-15",null,"not supplied",null,"STD",null,null,null,null,null," ",null,null,"2017-11-20","Was on hold behind first group study on circuit."]
[null,"WMECO","Southwick","6S1998-2016","01077",16.7,"Solar","29A5","2016-01-05","2016-01-08",{"$f":"NETWORKDAYS(I431,J431,MALegalHolidays)","v":4},2,2,"2016-01-08",null,{"$f":"NETWORKDAYS(N431,O431,MALegalHolidays)","v":-30219},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-03-04",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn after multiple requsts for response"]
[null,"WMECO","Amherst","6A1621-2016","01002",17,"Solar","19B16","2016-01-07","2016-01-22",{"$f":"NETWORKDAYS(I432,J432,MALegalHolidays)","v":12},6,6,"2016-01-23","2016-02-09",{"$f":"NETWORKDAYS(N432,O432,MALegalHolidays)","v":12},0,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-10",null,"2016-05-01",null,"EXP",null,null,null,null,null," ","2016-06-23","2016-06-27","2016-06-27"]
[null,"WMECO","Amherst","6A1622-2016","01002",27,"Solar","17K5","2016-01-07","2016-03-02",{"$f":"NETWORKDAYS(I433,J433,MALegalHolidays)","v":40},19,21,"2016-03-02","2016-06-13",{"$f":"NETWORKDAYS(N433,O433,MALegalHolidays)","v":74},63,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-06-16",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-09-08","2016-09-21","2016-09-21"]
[null,"WMECO","West Springfield","6S2018-2016","01089",24,"Solar","21N9","2016-01-08","2016-01-14",{"$f":"NETWORKDAYS(I434,J434,MALegalHolidays)","v":5},1,4,"2016-01-14","2016-04-04",{"$f":"NETWORKDAYS(N434,O434,MALegalHolidays)","v":58},54,4,"2016-04-05","2016-07-19",{"$f":"NETWORKDAYS(S434,T434,MALegalHolidays)","v":76},0,76,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-08-04",null,"2016-03-07",null,"EXP",null,null,null,null,null," ","2017-01-04","2017-01-06","2017-01-06"]
[null,"WMECO","Whately","6A1625-2016","01093",16.7,"Solar","18G8","2016-01-12","2016-01-20",{"$f":"NETWORKDAYS(I435,J435,MALegalHolidays)","v":7},1,6,"2016-01-20","2016-02-09",{"$f":"NETWORKDAYS(N435,O435,MALegalHolidays)","v":15},9,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-11",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by customer"]
[null,"WMECO","Dalton","6B864-2016","01226",495.28,"Solar","19A3","2016-01-12","2016-07-01",{"$f":"NETWORKDAYS(I436,J436,MALegalHolidays)","v":124},92,32,"2016-07-05",null,{"$f":"NETWORKDAYS(N436,O436,MALegalHolidays)","v":-30346},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-09-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Springfield","6S2043-2016","01109",16.7,"Solar","20A32","2016-01-19","2016-02-09",{"$f":"NETWORKDAYS(I437,J437,MALegalHolidays)","v":16},7,9,"2016-02-09","2016-02-29",{"$f":"NETWORKDAYS(N437,O437,MALegalHolidays)","v":15},10,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-03-18",null,"2016-02-02",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Springfield","6S2044-2016","01118",14.35,"Solar","20A32","2016-01-19",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-02-02",null,"EXP",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Longmeadow","6S2053-2016","01106",16.7,"Solar","22H12","2016-01-19","2016-02-09",{"$f":"NETWORKDAYS(I439,J439,MALegalHolidays)","v":16},7,9,"2016-02-09","2016-02-17",{"$f":"NETWORKDAYS(N439,O439,MALegalHolidays)","v":7},5,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-19",null,"2016-02-04",null,"EXP",null,null,null,null,null," ","2016-04-21","2016-04-25","2016-04-25"]
[null,"WMECO","Amherst","6A1637-2016","01002",99,"Solar","19B15","2016-01-20","2016-01-27",{"$f":"NETWORKDAYS(I440,J440,MALegalHolidays)","v":6},4,2,"2016-01-28","2016-02-23",{"$f":"NETWORKDAYS(N440,O440,MALegalHolidays)","v":19},0,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-23",null,"Feb 2016",null,"EXP",null,null,null,null,null," ","2016-06-15","2016-06-16","2016-06-16"]
[null,"WMECO","Agawam","6S2068-2016","01001",45,"Solar","16C16","2016-01-22","2016-02-11",{"$f":"NETWORKDAYS(I441,J441,MALegalHolidays)","v":15},9,6,"2016-02-11","2016-02-18",{"$f":"NETWORKDAYS(N441,O441,MALegalHolidays)","v":6},3,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-02-22",null,"2016-03-15",null,"EXP",null,null,null,null,null," ",null,null,"2016-09-20","on line"]
[null,"WMECO","Whately","6A1647-2016","01093",1992,"Solar","18G8","2016-01-27","2016-02-04",{"$f":"NETWORKDAYS(I442,J442,MALegalHolidays)","v":7},1,{"$f":"IF(K442>0,K442-L442,\" \")","v":6},"2016-02-05",null,{"$f":"NETWORKDAYS(N442,O442,MALegalHolidays)","v":-30239},null,{"$f":"IF(P442>0,P442-Q442,\" \")","v":" "},null,null,null,null,{"$f":"IF(U442>0,U442-V442,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z442>0,Z442-AA442,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE442>0,AE442-AF442,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ442>0,AJ442-AK442,\" \")","v":" "},null,null,"Summer 2016",null,"STD",null,null,null,null,null,{"$f":"IF(AU442>0,AU442-AV442,\" \")","v":" "},null,null,null,"Cancelled by Interconnecting Customer because SREC program ended."]
[null,"WMECO","Whately","6A1652-2016","01093",1548,"Solar","18G8","2016-01-29",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Springfield","6S2094-2016","01104",140,"Solar","5J11","2016-02-02","2017-02-13",{"$f":"NETWORKDAYS(I444,J444,MALegalHolidays)","v":270},223,47,"2017-02-14",null,{"$f":"NETWORKDAYS(N444,O444,MALegalHolidays)","v":-30506},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"3/16",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Agawam","6S2095-2016","01001",250,"Solar","30A6","2016-02-02","2016-09-08",{"$f":"NETWORKDAYS(I445,J445,MALegalHolidays)","v":158},149,9,"2016-09-09","2017-01-27",{"$f":"NETWORKDAYS(N445,O445,MALegalHolidays)","v":101},88,13,"2017-01-30","2017-03-01",{"$f":"NETWORKDAYS(S445,T445,MALegalHolidays)","v":23},0,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"3/16",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pittsfield","6B887-2016","01201",625.79999999999995,"Solar","30B7","2016-02-03","2016-03-08",{"$f":"NETWORKDAYS(I446,J446,MALegalHolidays)","v":25},9,16,"2016-03-09","2016-05-16",{"$f":"NETWORKDAYS(N446,O446,MALegalHolidays)","v":49},13,36,null,null,null,null," ",null,null,null,null," ","2016-05-17","2016-08-10",{"$f":"NETWORKDAYS(AC446,AD446,MALegalHolidays)","v":62},0,62,"2016-08-31",null,{"$f":"NETWORKDAYS(AH446,AI446,MALegalHolidays)","v":-30387},null," ","2016-08-16",null,"2016-04-01",null,"STD",null,null,null,null,null," ","2017-11-28","2017-12-01","2017-12-18","Was on hold behind first group study on circuit."]
[null,"WMECO","Westhampton","6A1661-2016","01027",566.1,"Solar","15A3","2016-02-04","2016-04-05",{"$f":"NETWORKDAYS(I447,J447,MALegalHolidays)","v":44},21,23,"2016-04-06","2016-07-22",{"$f":"NETWORKDAYS(N447,O447,MALegalHolidays)","v":78},71,7,null,null,null,null," ",null,null,null,null," ","2016-07-25","2016-10-07",{"$f":"NETWORKDAYS(AC447,AD447,MALegalHolidays)","v":55},null,55,null,null,null,null," ",null,null,"2016-04-01",null,"STD",null,null,null,null,null," ",null,null,null,"On hold behind 6A1251, formed froup with 6A1251, 6A1251 cancelled so removed from group.  Cancelled by applicant.  Had two 10 day extensions..  "]
[null,"WMECO","Whately","6A1662-2016","01093",8.35,"Solar","18G6","2016-02-04","2016-04-11",{"$f":"NETWORKDAYS(I448,J448,MALegalHolidays)","v":48},44,4,"2016-04-11","2016-05-04",{"$f":"NETWORKDAYS(N448,O448,MALegalHolidays)","v":18},16,2,"2016-05-05",null,{"$f":"NETWORKDAYS(S448,T448,MALegalHolidays)","v":-30303},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-03",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pittsfield","6B896-2016","01201",390,"Solar","19A7","2016-02-10","2016-05-03",{"$f":"NETWORKDAYS(I449,J449,MALegalHolidays)","v":60},23,37,"2016-05-04",null,{"$f":"NETWORKDAYS(N449,O449,MALegalHolidays)","v":-30302},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant 7/13/16, decided not to proceed, never executed group study agreement"]
[null,"WMECO","Amherst","6A1697-2015","01002",22.7,"Solar","18G7","2016-02-22","2016-03-10",{"$f":"NETWORKDAYS(I450,J450,MALegalHolidays)","v":14},10,4,"2016-03-10",null,{"$f":"NETWORKDAYS(N450,O450,MALegalHolidays)","v":-30263},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-03-15",null,"EXP",null,null,null,null,null," ",null,null,null,"Sent Supplemental Review 3/10/16.  Int Cust/Cust did not submit executed agreement or respond to notices.  Withdrawn after no response."]
[null,"WMECO","Sunderland","6A1704-2016","01375",288,"Solar","18G3","2016-02-23","2016-05-04",{"$f":"NETWORKDAYS(I451,J451,MALegalHolidays)","v":52},44,8,"2016-05-05",null,{"$f":"NETWORKDAYS(N451,O451,MALegalHolidays)","v":-30303},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by customer"]
[null,"WMECO","Sunderland","6A1708-2016","01375",22.5,"Solar","18G8","2016-02-23","2016-04-13",{"$f":"NETWORKDAYS(I452,J452,MALegalHolidays)","v":37},6,31,"2016-04-13","2016-04-14",{"$f":"NETWORKDAYS(N452,O452,MALegalHolidays)","v":2},1,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-15",null,"not supplied",null,"EXP",null,null,null,null,null," ","2016-06-08","2016-06-09","2016-06-09"]
[null,"WMECO","South Deerfield","6F1389-2016","01373",1000,"Biogas","22B1","2016-02-25","2016-04-13",{"$f":"NETWORKDAYS(I453,J453,MALegalHolidays)","v":35},12,23,"2016-04-14","2016-07-01",{"$f":"NETWORKDAYS(N453,O453,MALegalHolidays)","v":57},20,37,null,null,null,null," ",null,null,null,null," ","2016-07-05","2016-10-06",{"$f":"NETWORKDAYS(AC453,AD453,MALegalHolidays)","v":68},0,68,"2016-10-19",null,{"$f":"NETWORKDAYS(AH453,AI453,MALegalHolidays)","v":-30422},null," ","2016-10-12",null,"6/20/16",null,"COMP",null,null,null,null,null," ","2017-12-06","2017-12-11","2017-12-11","applicant submitted design change after complete, negotiated timeline to re do steps, second Impact Study Agreement sent"]
[null,"WMECO","Otis","6B923-2016","01253",40.75,"Solar","19J4","2016-03-01",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-02",null,"EXP",null,null,null,null,null," ",null,null,null,"Application withdrawn after calls and email notices that application was not complete and deadlines were missed."]
[null,"WMECO","Hadley","6A1736-2016","01035",16.399999999999999,"Solar","18G4","2016-03-03","2016-03-10",{"$f":"NETWORKDAYS(I455,J455,MALegalHolidays)","v":6},2,4,"2016-03-10",null,{"$f":"NETWORKDAYS(N455,O455,MALegalHolidays)","v":-30263},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-03",null,"EXP",null,null,null,null,null," ",null,null,null,"Cancelled by applicant"]
[null,"WMECO","Buckland","6F1417-2016","01338",25.425000000000001,"Solar","38A1","2016-03-04","2016-06-27",{"$f":"NETWORKDAYS(I456,J456,MALegalHolidays)","v":82},74,8,"2016-06-27",null,{"$f":"NETWORKDAYS(N456,O456,MALegalHolidays)","v":-30340},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-15",null,"EXP",null,null,null,null,null," ",null,null,null,"Application withdrawn after no response to multiple requests for status and Supplemental Review Agreement was not executed."]
[null,"WMECO","Agawam","6S2185-2016","01001",22.95,"Solar","16C17","2016-03-04","2016-03-21",{"$f":"NETWORKDAYS(I457,J457,MALegalHolidays)","v":12},3,9,"2016-03-21","2016-03-28",{"$f":"NETWORKDAYS(N457,O457,MALegalHolidays)","v":6},5,1,"2016-03-29",null,{"$f":"NETWORKDAYS(S457,T457,MALegalHolidays)","v":-30276},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-29",null,"EXP",null,null,null,null,null," ",null,null,null,"installer cancelled application due to changs in SREC program"]
[null,"WMECO","Amherst","6A1743-2016","01002",19.75,"Solar","18G4","2016-03-07","2016-03-14",{"$f":"NETWORKDAYS(I458,J458,MALegalHolidays)","v":6},5,1,"2016-03-15",null,{"$f":"NETWORKDAYS(N458,O458,MALegalHolidays)","v":-30266},15," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q2 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Agawam","6S2199-2016","01001",22.95,"Solar","16C17","2016-03-08",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-30",null,"EXP",null,null,null,null,null," ",null,null,null,"installer cancelled application due to changs in SREC program"]
[null,"WMECO","Easthampton","6A1754-2016","01027",180,"Solar","15A2","2016-03-09","2016-04-15",{"$f":"NETWORKDAYS(I460,J460,MALegalHolidays)","v":28},0,28,"2016-04-19","2016-06-03",{"$f":"NETWORKDAYS(N460,O460,MALegalHolidays)","v":34},25,9,null,null,null,null," ",null,null,null,null," ","2016-06-06","2016-09-23",{"$f":"NETWORKDAYS(AC460,AD460,MALegalHolidays)","v":80},0,80,null,null,null,null," ","2016-09-23",null,"5/2016",null,"STD",null,null,null,null,null," ","2017-03-28","2017-04-04","2017-04-04","application added to group, group changed, this app does not need Detailed Study"]
[null,"WMECO","Amherst","6A1755-2016","01002",60,"Solar","17K4","2016-03-09","2016-04-06",{"$f":"NETWORKDAYS(I461,J461,MALegalHolidays)","v":21},11,10,"2016-04-06","2016-04-12",{"$f":"NETWORKDAYS(N461,O461,MALegalHolidays)","v":5},2,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-04-13",null,"May 2016",null,"EXP",null,null,null,null,null," ","2016-10-04","2016-10-06","2016-10-06"]
[null,"WMECO","Hadley","6A1766-2016","01035",84,"Solar","18G5","2016-03-11","2016-03-21",{"$f":"NETWORKDAYS(I462,J462,MALegalHolidays)","v":7},0,7,"2016-03-21","2016-06-20",{"$f":"NETWORKDAYS(N462,O462,MALegalHolidays)","v":66},62,4,"2016-06-21","2016-07-18",{"$f":"NETWORKDAYS(S462,T462,MALegalHolidays)","v":20},0,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-07-19",null,"3/2016",null,"EXP",null,null,null,null,null," ","2017-03-21","2017-03-22","2017-03-22"]
[null,"WMECO","Southampton","6A1767-2016","01073",23.45,"Solar","15A1","2016-03-11","2016-04-11",{"$f":"NETWORKDAYS(I463,J463,MALegalHolidays)","v":22},17,5,"2016-04-11",null,{"$f":"NETWORKDAYS(N463,O463,MALegalHolidays)","v":-30285},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"5/10/16",null,"EXP",null,null,null,null,null," ",null,null,null,"customer cancelled their application"]
[null,"WMECO","Deerfield","6F1439-2016","01342",75,"Solar","22B3","2016-03-11","2016-08-10",{"$f":"NETWORKDAYS(I464,J464,MALegalHolidays)","v":109},90,19,"2016-08-10","2016-11-30",{"$f":"NETWORKDAYS(N464,O464,MALegalHolidays)","v":81},68,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-12-05",null,"5/2016",null,"EXP",null,null,null,null,null," ","2017-12-12","2017-12-13","2018-04-23","applicant submitted new option 2, negotiated timeline 10 extra days.  Witness test performed.  Customer requested that project not be given approval to Operate until the tranfer of ownership was completed.  "]
[null,"WMECO","Turners Falls","6F1440-2016","01376",19.3,"Solar","21C6","2016-03-14","2016-03-25",{"$f":"NETWORKDAYS(I465,J465,MALegalHolidays)","v":10},8,2,"2016-03-25","2016-03-31",{"$f":"NETWORKDAYS(N465,O465,MALegalHolidays)","v":5},4,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-03-31",null,"2015-11-09",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Hancock","6B939-2016","01237",42.25,"Solar","30B7","2016-03-17",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-16",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Deerfield","6F1449-2016","01342",64,"Solar","22B3","2016-03-17","2016-06-27",{"$f":"NETWORKDAYS(I467,J467,MALegalHolidays)","v":73},56,17,"2016-06-28","2016-08-11",{"$f":"NETWORKDAYS(N467,O467,MALegalHolidays)","v":33},26,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-08-11",null,"6/2016",null,"EXP",null,null,null,null,null," ","2017-09-22","2017-10-04","2018-04-25","negotiated extra time to review second option, 5 extra days. Customer requested that the project not be given approval to operate until the tranfer of onwership is completed"]
[null,"WMECO","Springfield","6S2233-2016","01105",16.95,"Solar","21S11","2016-03-17","2016-07-26",{"$f":"NETWORKDAYS(I468,J468,MALegalHolidays)","v":94},80,14,"2016-07-26","2016-09-16",{"$f":"NETWORKDAYS(N468,O468,MALegalHolidays)","v":39},37,2,"2016-09-19",null,{"$f":"NETWORKDAYS(S468,T468,MALegalHolidays)","v":-30400},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-16",null,"EXP",null,null,null,null,null," ",null,null,null,"two different 15 day extensions granted, requested information from applicant, no responses so withdrew application after no response to 10 day notice "]
[null,"WMECO","Cheshire","6B947-2016","01225",16.7,"Solar","19A5","2016-03-18","2016-03-30",{"$f":"NETWORKDAYS(I469,J469,MALegalHolidays)","v":9},7,2,"2016-03-30",null,{"$f":"NETWORKDAYS(N469,O469,MALegalHolidays)","v":-30277},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-03",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn due to no response to emails or phone calls to IC and installer"]
[null,"WMECO","Southwick","6S2236-2016","01077",21.9,"Solar","29A5","2016-03-22","2016-04-07",{"$f":"NETWORKDAYS(I470,J470,MALegalHolidays)","v":13},12,1,"2016-04-07","2016-04-28",{"$f":"NETWORKDAYS(N470,O470,MALegalHolidays)","v":16},14,2,"2016-04-29","2016-05-20",{"$f":"NETWORKDAYS(S470,T470,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-05-26",null,"2016-06-17",null,"EXP",null,null,null,null,null," ","2017-03-06","2017-03-09","2017-03-09"]
[null,"WMECO","Springfield","6S2248-2016","01109",72,"Solar","5J15","2016-03-24","2016-04-05",{"$f":"NETWORKDAYS(I471,J471,MALegalHolidays)","v":9},7,2,"2016-04-05","2016-05-30",{"$f":"NETWORKDAYS(N471,O471,MALegalHolidays)","v":40},30,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-06-01",null,"July 2015",null,"EXP",null,null,null,null,null," ","2017-03-31","2017-04-05","2017-04-05"]
[null,"WMECO","West Springfield","6S2264-2016","01089",16.399999999999999,"Solar","21N4","2016-03-29","2016-04-07",{"$f":"NETWORKDAYS(I472,J472,MALegalHolidays)","v":8},7,1,"2016-04-07",null,{"$f":"NETWORKDAYS(N472,O472,MALegalHolidays)","v":-30283},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"Applicant requested an extension 5/19/16, extension granted to 6/10/16.  No response from calls and emails so withdrawn."]
[null,"WMECO","Lanesborough","6B960-2016","01201",21.9,"Solar","15E2","2016-04-05","2016-05-03",{"$f":"NETWORKDAYS(I473,J473,MALegalHolidays)","v":21},18,3,"2016-05-03","2016-07-12",{"$f":"NETWORKDAYS(N473,O473,MALegalHolidays)","v":51},39,12,"2016-07-13",null,{"$f":"NETWORKDAYS(S473,T473,MALegalHolidays)","v":-30352},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-04-23",null,"EXP",null,null,null,null,null," ",null,null,null,"applicant requested an extension, 5 days, cancelled by applicant"]
[null,"WMECO","Lanesborough","6B973-2016","01237",16.399999999999999,"Solar","15E1","2016-04-11","2016-04-19",{"$f":"NETWORKDAYS(I474,J474,MALegalHolidays)","v":7},5,2,"2016-04-19","2016-05-09",{"$f":"NETWORKDAYS(N474,O474,MALegalHolidays)","v":15},14,1,"2016-05-10","2016-05-10",{"$f":"NETWORKDAYS(S474,T474,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-05-16",null,"2016-05-04",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Agawam","6S2294-2016","01001",45.9,"Solar","16C17","2016-04-11","2016-05-03",{"$f":"NETWORKDAYS(I475,J475,MALegalHolidays)","v":17},13,4,"2016-05-03","2016-05-11",{"$f":"NETWORKDAYS(N475,O475,MALegalHolidays)","v":7},6,1,"2016-05-12","2016-05-18",{"$f":"NETWORKDAYS(S475,T475,MALegalHolidays)","v":5},0,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-05-27",null,"2016-05-28",null,"EXP",null,null,null,null,null," ",null,null,"2016-07-27"]
[null,"WMECO","Agawam","6S2295-2016","01001",46.8,"Solar","16C18","2016-04-11","2016-05-03",{"$f":"NETWORKDAYS(I476,J476,MALegalHolidays)","v":17},14,3,"2016-05-03","2016-05-03",{"$f":"NETWORKDAYS(N476,O476,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-05-05",null,"2016-05-28",null,"EXP",null,null,null,null,null," ","2016-08-09","2016-08-11","2016-08-11"]
[null,"WMECO","Montague","6F1484-2016","01351",18,"Solar","21C7","2016-04-12","2016-04-25",{"$f":"NETWORKDAYS(I477,J477,MALegalHolidays)","v":10},8,2,"2016-04-25",null,{"$f":"NETWORKDAYS(N477,O477,MALegalHolidays)","v":-30295},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"July 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Montague","6F1485-2016","01351",56.35,"Solar","21C7","2016-04-12","2016-04-25",{"$f":"NETWORKDAYS(I478,J478,MALegalHolidays)","v":10},8,2,"2016-04-25","2016-05-20",{"$f":"NETWORKDAYS(N478,O478,MALegalHolidays)","v":20},18,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-05-26",null,"July 2016",null,"EXP",null,null,null,null,null," ","2017-01-18","2017-01-26","2017-01-26","failed first Witness Test, rescheduled nd passed second WT"]
[null,"WMECO","Southwick","6S2301-2016","01077",2000,"Solar","29A3","2016-04-13","2016-06-01",{"$f":"NETWORKDAYS(I479,J479,MALegalHolidays)","v":36},23,13,"2016-06-02","2017-05-03",{"$f":"NETWORKDAYS(N479,O479,MALegalHolidays)","v":240},217,23,null,null,null,null," ",null,null,null,null," ","2017-05-04","2017-09-19",{"$f":"NETWORKDAYS(AC479,AD479,MALegalHolidays)","v":99},15,84,"2017-10-28",null,{"$f":"NETWORKDAYS(AH479,AI479,MALegalHolidays)","v":-30689},null," ","2017-10-05",null,"Spring 2017",null,"COMP",null,null,null,null,null," ",null,null,"2018-12-20","on line"]
[null,"WMECO","Southwick","6S2303-2016","01077",2000,"Solar","29A3","2016-04-13","2016-06-01",{"$f":"NETWORKDAYS(I480,J480,MALegalHolidays)","v":36},23,13,"2016-06-02","2017-05-03",{"$f":"NETWORKDAYS(N480,O480,MALegalHolidays)","v":240},217,23,null,null,null,null," ",null,null,null,null," ","2017-05-04","2017-09-19",{"$f":"NETWORKDAYS(AC480,AD480,MALegalHolidays)","v":99},15,84,"2017-10-28",null,{"$f":"NETWORKDAYS(AH480,AI480,MALegalHolidays)","v":-30689},null," ","2017-10-05",null,"Spring 2017",null,"STD",null,null,null,null,null," ",null,null,"2018-12-20","on line"]
[null,"WMECO","West Springfield","6S2305-2016","01089",12,"Solar","21N6","2016-04-14","2016-04-20",{"$f":"NETWORKDAYS(I481,J481,MALegalHolidays)","v":5},3,2,"2016-04-20",null,{"$f":"NETWORKDAYS(N481,O481,MALegalHolidays)","v":-30292},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-08-07",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Ludlow","6S2314-2016","01056",16.7,"Solar","19S3","2016-04-18","2016-05-09",{"$f":"NETWORKDAYS(I482,J482,MALegalHolidays)","v":16},14,2,"2016-05-09",null,{"$f":"NETWORKDAYS(N482,O482,MALegalHolidays)","v":-30305},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-06-18",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn after no response to calls and emails and missed timelines"]
[null,"WMECO","Ludlow","6S2347-2016","01056",12,"Solar","19S1","2016-04-28",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-25",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B996-2016","01201",1476,"Solar","30B7","2016-05-02","2016-05-24",{"$f":"NETWORKDAYS(I484,J484,MALegalHolidays)","v":17},6,11,"2016-05-25",null,{"$f":"NETWORKDAYS(N484,O484,MALegalHolidays)","v":-30317},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-11-01",null,"STD",null,null,null,null,null," ",null,null,null,"Application on hold behind behind a group study on 30B7 circuit.  Negotiated 10 days extra.  Customer also requested 10 day extension.  Applicant did not execute Impact Study Agreement.  Applicant cancelled  application."]
[null,"WMECO","Southwick","6S2367-2016","01077",16.7,"Solar","29A5","2016-05-04","2016-05-16",{"$f":"NETWORKDAYS(I485,J485,MALegalHolidays)","v":9},8,1,"2016-05-16","2016-06-15",{"$f":"NETWORKDAYS(N485,O485,MALegalHolidays)","v":23},21,2,"2016-06-16","2016-06-22",{"$f":"NETWORKDAYS(S485,T485,MALegalHolidays)","v":5},0,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-06-23",null,"2016-03-04",null,"EXP",null,null,null,null,null," ","2016-11-08","2016-11-14","2016-11-14"]
[null,"WMECO","Springfield","6S2368-2016","01119",152,"Solar","27A7","2016-05-04","2016-05-16",{"$f":"NETWORKDAYS(I486,J486,MALegalHolidays)","v":9},1,8,"2016-05-17","2016-07-07",{"$f":"NETWORKDAYS(N486,O486,MALegalHolidays)","v":38},18,20,"2016-07-08","2016-08-02",{"$f":"NETWORKDAYS(S486,T486,MALegalHolidays)","v":18},0,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-08-09",null,"Aug 2016",null,"EXP",null,null,null,null,null," ","2017-02-07","2017-02-10","2017-02-10"]
[null,"WMECO","Hancock","6B1002-2016","01237",42.25,"Solar","30B7","2016-05-05","2016-09-15",{"$f":"NETWORKDAYS(I487,J487,MALegalHolidays)","v":96},77,19,"2016-09-15"," ",{"$f":"NETWORKDAYS(N487,O487,MALegalHolidays)","v":{"$error":"#VALUE!"}},42,{"$error":"#VALUE!"},null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-16",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Dalton","6B1014-2016","01226",16.149999999999999,"Solar","18C1","2016-05-10","2016-05-19",{"$f":"NETWORKDAYS(I488,J488,MALegalHolidays)","v":8},3,5,"2016-05-19","2016-06-09",{"$f":"NETWORKDAYS(N488,O488,MALegalHolidays)","v":16},14,2,"2016-06-10","2016-07-13",{"$f":"NETWORKDAYS(S488,T488,MALegalHolidays)","v":24},0,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-07-14",null,"2016-07-03",null,"EXP",null,null,null,null,null," ","2016-12-07","2016-12-13","2016-12-13"]
[null,"WMECO","Montague","6F1500-2016","01351",36,"Solar","21C7","2016-05-10","2016-06-15",{"$f":"NETWORKDAYS(I489,J489,MALegalHolidays)","v":27},22,5,"2016-06-15","2016-07-11",{"$f":"NETWORKDAYS(N489,O489,MALegalHolidays)","v":19},16,3,"2016-07-12","2016-09-26",{"$f":"NETWORKDAYS(S489,T489,MALegalHolidays)","v":55},17,38,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-09-29",null,"2016-08-01",null,"EXP",null,null,null,null,null," ","2017-06-09","2017-06-21","2017-11-10"]
[null,"WMECO","Plainfield","6F1513-2016","01070",17.5,"Solar","18K3","2016-05-25",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lee","6B1034-2016","01238",36,"Solar","16B5","2016-05-26","2016-08-05",{"$f":"NETWORKDAYS(I491,J491,MALegalHolidays)","v":52},48,4,"2016-08-05","2016-08-29",{"$f":"NETWORKDAYS(N491,O491,MALegalHolidays)","v":17},7,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-08-30",null,"Not supplied",null,"EXP",null,null,null,null,null," ","2017-01-17","2017-01-19","2017-01-20"]
[null,"WMECO","Turners Falls","6F1515-2016","01376",1160,"Solar","21C8","2016-05-27","2016-06-28",{"$f":"NETWORKDAYS(I492,J492,MALegalHolidays)","v":23},15,8,"2016-06-29","2016-07-22",{"$f":"NETWORKDAYS(N492,O492,MALegalHolidays)","v":18},6,12,null,null,null,null," ",null,null,null,null," ","2016-07-25","2016-10-06",{"$f":"NETWORKDAYS(AC492,AD492,MALegalHolidays)","v":54},0,54,null,null,null,null," ",null,null,"2016-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated 20 extra days.  Applicant not sure if they will proceed.  Withdrawn after notices and no response."]
[null,"WMECO","Southwick","6S2463-2016","01077",15.75,"Solar","29A5","2016-05-31","2016-06-23",{"$f":"NETWORKDAYS(I493,J493,MALegalHolidays)","v":18},14,4,"2016-06-23","2016-07-07",{"$f":"NETWORKDAYS(N493,O493,MALegalHolidays)","v":11},9,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-07-14",null,"2016-06-15",null,"EXP",null,null,null,null,null," ","2016-11-28","2016-11-29","2016-11-29"]
[null,"WMECO","Pittsfield","6B1040-2016","01201",60,"Solar","30B7","2016-06-01","2016-07-20",{"$f":"NETWORKDAYS(I494,J494,MALegalHolidays)","v":36},32,4,"2016-07-20","2016-11-02",{"$f":"NETWORKDAYS(N494,O494,MALegalHolidays)","v":76},48,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-11-02",null,"Sept 2016",null,"EXP",null,null,null,null,null," ","2017-04-04","2017-04-06","2017-04-06","Sent Supplemental Review Agreement.  Applicant submitted new Option 2. Negotiated 10 extra days to review new option."]
[null,"WMECO","Pittsfield","6B1047-2016","01201",166.5,"Solar","30B3","2016-06-08","2016-06-30",{"$f":"NETWORKDAYS(I495,J495,MALegalHolidays)","v":17},14,3,"2016-06-30","2016-07-19",{"$f":"NETWORKDAYS(N495,O495,MALegalHolidays)","v":14},12,2,"2016-07-19","2018-07-13",{"$f":"NETWORKDAYS(S495,T495,MALegalHolidays)","v":519},236,283,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-07-17",null,"Oct 2016",null,"STD",null,null,null,null,null," ","2018-08-30","2018-08-31","2018-09-04","Sent Impact Study, sent 10 day withdrawal notice, negotiated timeline, 10 days, sent another Impact Study, sent withdrawal notice "]
[null,"WMECO","Amherst","6A1948-2016","01002",86.995000000000005,"Solar","18G4","2016-06-10","2016-06-21",{"$f":"NETWORKDAYS(I496,J496,MALegalHolidays)","v":8},5,3,"2016-06-21",null,{"$f":"NETWORKDAYS(N496,O496,MALegalHolidays)","v":-30336},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Sept 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Lee","6B1052-2016","01238",3328,"Natural Gas","16B3","2016-06-10","2016-07-12",{"$f":"NETWORKDAYS(I497,J497,MALegalHolidays)","v":23},6,17,"2016-07-13","2016-09-21",{"$f":"NETWORKDAYS(N497,O497,MALegalHolidays)","v":51},37,14,null,null,null,null," ",null,null,null,null," ","2016-09-22","2017-03-13",{"$f":"NETWORKDAYS(AC497,AD497,MALegalHolidays)","v":123},78,45,null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1053-2016","01201",460,"Solar","19A5","2016-06-10","2017-01-11",{"$f":"NETWORKDAYS(I498,J498,MALegalHolidays)","v":154},137,17,"2017-01-12","2017-03-10",{"$f":"NETWORKDAYS(N498,O498,MALegalHolidays)","v":42},38,4,null,null,null,null," ",null,null,null,null," ","2017-03-13","2017-05-18",{"$f":"NETWORKDAYS(AC498,AD498,MALegalHolidays)","v":49},0,49,null,null,null,null," ",null,null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"Negotiated timeline - 10 days to Impact Study.  Notice sent, withdrawn after applicant did not execute Detailed Study Agreement."]
[null,"WMECO","Southampton","6A1949-2016","01073",18,"Solar","15A1","2016-06-13","2016-07-12",{"$f":"NETWORKDAYS(I499,J499,MALegalHolidays)","v":22},15,7,"2016-07-13","2016-09-06",{"$f":"NETWORKDAYS(N499,O499,MALegalHolidays)","v":40},37,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-09-13",null,"8/12",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pelham","6A1953-2016","01002",19.3,"Solar","17K2","2016-06-15","2016-07-28",{"$f":"NETWORKDAYS(I500,J500,MALegalHolidays)","v":32},26,6,"2016-07-28","2016-08-23",{"$f":"NETWORKDAYS(N500,O500,MALegalHolidays)","v":19},18,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-08-29",null,"2016-08-14",null,"EXP",null,null,null,null,null," ","2017-03-02","2017-03-07","2017-03-07"]
[null,"WMECO","West Springfield","6S2516-2016","01089",16.399999999999999,"Solar","21N4","2016-06-22","2016-07-18",{"$f":"NETWORKDAYS(I501,J501,MALegalHolidays)","v":19},12,7,"2016-07-18","2016-09-02",{"$f":"NETWORKDAYS(N501,O501,MALegalHolidays)","v":35},34,1,"2016-09-06",null,{"$f":"NETWORKDAYS(S501,T501,MALegalHolidays)","v":-30391},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Southampton","6A1971-2016","01073",21.9,"Solar","15A1","2016-06-23","2016-06-29",{"$f":"NETWORKDAYS(I502,J502,MALegalHolidays)","v":5},2,3,"2016-06-29","2016-07-19",{"$f":"NETWORKDAYS(N502,O502,MALegalHolidays)","v":15},13,2,"2016-07-20",null,{"$f":"NETWORKDAYS(S502,T502,MALegalHolidays)","v":-30357},2," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-07-04",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","West Springfield","6S2539-2016","01089",16.399999999999999,"Solar","21N4","2016-06-29",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Ludlow","6S2573-2016","01056",396,"Solar","27A5","2016-07-11","2016-08-09",{"$f":"NETWORKDAYS(I504,J504,MALegalHolidays)","v":22},19,3,"2016-08-12",null,{"$f":"NETWORKDAYS(N504,O504,MALegalHolidays)","v":-30374},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"New option submitted 9/29/16.  Cancelled by applicants."]
[null,"WMECO","Southampton","6A2007-2016","01073",23.4,"Solar","15A1","2016-07-26",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-05-26",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled "]
[null,"WMECO","Otis","6B1113-2016","01253",67.599999999999994,"Solar","19J4","2016-07-26","2016-09-23",{"$f":"NETWORKDAYS(I506,J506,MALegalHolidays)","v":44},38,{"$f":"IF(K506>0,K506-L506,\" \")","v":6},"2016-09-26","2016-10-07",{"$f":"NETWORKDAYS(N506,O506,MALegalHolidays)","v":10},8,{"$f":"IF(P506>0,P506-Q506,\" \")","v":2},"2016-10-11",null,{"$f":"NETWORKDAYS(S506,T506,MALegalHolidays)","v":-30416},null,{"$f":"IF(U506>0,U506-V506,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z506>0,Z506-AA506,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE506>0,AE506-AF506,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ506>0,AJ506-AK506,\" \")","v":" "},null,null,"Not supplied",null,"EXP",null,null,null,null,null,{"$f":"IF(AU506>0,AU506-AV506,\" \")","v":" "},null,null,null,"negotiated timeline, 35 extra days for new option, withdrawn after application did not move forward"]
[null,"WMECO","Pittsfield","6B1127-2016","01201",1476,"Solar","30B7","2016-08-04","2016-08-31",{"$f":"NETWORKDAYS(I507,J507,MALegalHolidays)","v":20},15,5,"2016-09-01",null,{"$f":"NETWORKDAYS(N507,O507,MALegalHolidays)","v":-30388},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-11-01",null,"EXP",null,null,null,null,null," ",null,null,null,"Applicant granted 10 day extension.  Applicant did not execute Supplemental Review Agreement.  Applicant cancelled application."]
[null,"WMECO","Bernardston","6F1588-2016","01337",42,"Solar","21C1","2016-08-08","2016-08-15",{"$f":"NETWORKDAYS(I508,J508,MALegalHolidays)","v":6},5,1,"2016-08-15",null,{"$f":"NETWORKDAYS(N508,O508,MALegalHolidays)","v":-30375},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2016",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Greenfield","6F1590-2016","01301",50,"Solar","21C1","2016-08-08",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"August  ",null,"EXP",null,null,null,null,null," ",null,null,null,"two or three options, not complete, withdrawn after missed deadlines"]
[null,"WMECO","Hadley","6A2032-2016","01035",25,"Solar","18G6","2016-08-12","2016-09-13",{"$f":"NETWORKDAYS(I510,J510,MALegalHolidays)","v":23},12,11,"2016-08-31",null,{"$f":"NETWORKDAYS(N510,O510,MALegalHolidays)","v":-30387},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-10-28",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1134-2016","01201",16.75,"Solar","19A1","2016-08-12","2016-09-27",{"$f":"NETWORKDAYS(I511,J511,MALegalHolidays)","v":33},13,20,"2016-09-28","2016-09-28",{"$f":"NETWORKDAYS(N511,O511,MALegalHolidays)","v":1},0,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-09-29",null,"2016-08-15",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Amherst","6A2045-2016","01002",86.995000000000005,"Solar","18G4","2016-08-17","2016-09-27",{"$f":"NETWORKDAYS(I512,J512,MALegalHolidays)","v":30},18,12,"2016-09-28","2016-11-03",{"$f":"NETWORKDAYS(N512,O512,MALegalHolidays)","v":27},11,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-11-03",null,"Sept 2016",null,"EXP",null,null,null,null,null," ","2017-03-15","2017-03-21","2017-03-21"]
[null,"WMECO","Pittsfield","6B1139-2016","01201",240,"Solar","19A7","2016-08-17","2016-09-01",{"$f":"NETWORKDAYS(I513,J513,MALegalHolidays)","v":12},10,2,"2016-09-02",null,{"$f":"NETWORKDAYS(N513,O513,MALegalHolidays)","v":-30389},44," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-11-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant, not ready to move forward"]
[null,"WMECO","Springfield","6S2702-2016","01104",420,"Solar","5J15","2016-08-18","2016-09-14",{"$f":"NETWORKDAYS(I514,J514,MALegalHolidays)","v":20},14,6,"2016-09-15",null,{"$f":"NETWORKDAYS(N514,O514,MALegalHolidays)","v":-30398},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-12-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S2703-2016","01104",300,"Solar","5J15","2016-08-18","2016-09-14",{"$f":"NETWORKDAYS(I515,J515,MALegalHolidays)","v":20},14,6,"2016-09-15",null,{"$f":"NETWORKDAYS(N515,O515,MALegalHolidays)","v":-30398},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-12-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S2720-2016","01104",796,"Solar","5J13","2016-08-23","2016-09-13",{"$f":"NETWORKDAYS(I516,J516,MALegalHolidays)","v":16},9,7,"2016-09-14","2016-11-29",{"$f":"NETWORKDAYS(N516,O516,MALegalHolidays)","v":55},32,23,null,null,null,null," ",null,null,null,null," ","2016-11-30","2017-01-27",{"$f":"NETWORKDAYS(AC516,AD516,MALegalHolidays)","v":43},0,43,"2017-03-30",null,{"$f":"NETWORKDAYS(AH516,AI516,MALegalHolidays)","v":-30538},null," ","2017-03-21",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Westhampton","6A2060-2016","01027",16.7,"Solar","15A3","2016-08-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-10-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant, submitted Simplified app"]
[null,"WMECO","Ludlow","6S2770-2016","01056",16.7,"Solar","19S3","2016-09-13","2016-10-24",{"$f":"NETWORKDAYS(I518,J518,MALegalHolidays)","v":30},19,11,"2016-10-24",null,{"$f":"NETWORKDAYS(N518,O518,MALegalHolidays)","v":-30425},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-06-18",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Hadley","6A2086-2016","01035",399.6,"Solar","18G5","2016-09-14","2016-09-27",{"$f":"NETWORKDAYS(I519,J519,MALegalHolidays)","v":10},5,5,"2016-09-28","2016-11-10",{"$f":"NETWORKDAYS(N519,O519,MALegalHolidays)","v":32},19,13,null,null,null,null," ",null,null,null,null," ","2016-11-14","2017-04-19",{"$f":"NETWORKDAYS(AC519,AD519,MALegalHolidays)","v":113},56,57,"2017-04-20","2017-08-10",{"$f":"NETWORKDAYS(AH519,AI519,MALegalHolidays)","v":81},21,60,"2017-08-23",null,"Nov 2016",null,"STD",null,null,null,null,null," ",null,null,"2019-06-20","on line"]
[null,"WMECO","Worthington","6F1646-2016","01098",13.5,"Solar","18K3","2016-09-15",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-11-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Middlefield","6F1675-2016","01243",41.5,"Solar","18C2","2016-10-03","2016-10-17",{"$f":"NETWORKDAYS(I521,J521,MALegalHolidays)","v":11},8,3,"2016-10-17","2016-11-07",{"$f":"NETWORKDAYS(N521,O521,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-11-07",null,"2016-12-01",null,"EXP",null,null,null,null,null," ","2017-06-01","2017-06-05","2017-06-06","addition to existing facility"]
[null,"WMECO","Northfield","6F1684-2016","01360",21.9,"Solar","21B8","2016-10-06","2016-11-23",{"$f":"NETWORKDAYS(I522,J522,MALegalHolidays)","v":35},32,3,"2016-11-25",null,{"$f":"NETWORKDAYS(N522,O522,MALegalHolidays)","v":-30449},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-01-01",null,"EXP",null,null,null,null,null," ",null,null,null,"Cancelled by applicant, did not want to pay for Supplemental Review."]
[null,"WMECO","Worthington","6F1694-2016","01098",13.5,"Solar","18K3","2016-10-11",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2016-12-15",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant, should have submitted a Simplified Application"]
[null,"WMECO","Springfield","6S2863-2016","01109",16.7,"Solar","20A32","2016-10-11","2016-12-05",{"$f":"NETWORKDAYS(I524,J524,MALegalHolidays)","v":40},33,7,"2016-12-05","2016-12-12",{"$f":"NETWORKDAYS(N524,O524,MALegalHolidays)","v":6},1,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-12-12",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2017-02-21"]
[null,"WMECO","Greenfield","6F1707-2016","01301",1200,"Solar","21C1","2016-10-18","2016-10-31",{"$f":"NETWORKDAYS(I525,J525,MALegalHolidays)","v":10},7,3,"2016-11-01","2016-11-17",{"$f":"NETWORKDAYS(N525,O525,MALegalHolidays)","v":13},10,3,null,null,null,null," ",null,null,null,null," ","2016-11-18","2017-01-27",{"$f":"NETWORKDAYS(AC525,AD525,MALegalHolidays)","v":51},0,51,"2017-02-21",null,{"$f":"NETWORKDAYS(AH525,AI525,MALegalHolidays)","v":-30511},null," ","2017-03-10",null,"2017-09-21",null,"COMP",null,null,null,null,null," ",null,null,"2021-12-23","on line"]
[null,"WMECO","Pittsfield","6B1240-2016","01201",1320,"Solar","15E3","2016-10-25","2016-11-23",{"$f":"NETWORKDAYS(I526,J526,MALegalHolidays)","v":22},9,13,"2016-11-25",null,{"$f":"NETWORKDAYS(N526,O526,MALegalHolidays)","v":-30449},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"May 2017",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated timeline for technical information concerning export or no-export, 15 extra days.  Withdrawn with customer's agreement after not proceeding with project."]
[null,"WMECO","Springfield","6S2924-2016","01104",37.799999999999997,"Solar","5J15","2016-10-26","2016-11-01",{"$f":"NETWORKDAYS(I527,J527,MALegalHolidays)","v":5},3,2,"2016-11-01","2016-12-07",{"$f":"NETWORKDAYS(N527,O527,MALegalHolidays)","v":27},18,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-12-07",null,"2016-12-05",null,"EXP",null,null,null,null,null," ","2017-05-24","2017-05-26","2017-05-26","applicant submitted new option 2"]
[null,"WMECO","Amherst","6A2150-2016","01002",19.8,"Solar","18G4","2016-10-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"11/30/2016",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S2929-2016","01104",252,"Solar","21S6","2016-10-27","2016-11-08",{"$f":"NETWORKDAYS(I529,J529,MALegalHolidays)","v":9},6,3,"2016-11-09","2016-12-05",{"$f":"NETWORKDAYS(N529,O529,MALegalHolidays)","v":19},15,4,"2016-12-06","2016-12-29",{"$f":"NETWORKDAYS(S529,T529,MALegalHolidays)","v":18},6,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-03-15",null,"May 2016",null,"EXP",null,null,null,null,null," ","2017-11-15","2017-12-07","2017-12-07"]
[null,"WMECO","Dalton","6B1258-2016","01226",27.5,"Solar","18C1","2016-11-03","2016-12-13",{"$f":"NETWORKDAYS(I530,J530,MALegalHolidays)","v":29},25,4,"2016-12-13","2017-01-20",{"$f":"NETWORKDAYS(N530,O530,MALegalHolidays)","v":29},3,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-01-24",null,"Q4 2016",null,"EXP",null,null,null,null,null," ","2016-09-22","2016-09-27","2017-09-27"]
[null,"WMECO","Springfield","6S2985-2016","01118",149.9,"Solar","20A22","2016-11-14","2016-12-01",{"$f":"NETWORKDAYS(I531,J531,MALegalHolidays)","v":14},10,4,"2016-12-01","2016-12-07",{"$f":"NETWORKDAYS(N531,O531,MALegalHolidays)","v":5},2,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-12-07",null,"1/4/2017",null,"EXP",null,null,null,null,null," ","2018-01-08","2018-01-11","2018-01-11"]
[null,"WMECO","Becket","6B1277-2016","01223",4950,"Solar","19J6","2016-11-15","2016-12-19",{"$f":"NETWORKDAYS(I532,J532,MALegalHolidays)","v":25},21,4,"2016-12-19",null,{"$f":"NETWORKDAYS(N532,O532,MALegalHolidays)","v":-30465},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-10-18",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated 10 extra business days for technical review.  Customer sent Impact Study Agreement, had two extensions, withdrawn after missing deadlines."]
[null,"WMECO","Becket","6B1278-2016","01223",4950,"Solar","16B1","2016-11-15","2016-12-01",{"$f":"NETWORKDAYS(I533,J533,MALegalHolidays)","v":13},9,4,"2016-12-02","2017-01-25",{"$f":"NETWORKDAYS(N533,O533,MALegalHolidays)","v":39},29,10,null,null,null,null," ",null,null,null,null," ","2017-01-26","2017-03-30",{"$f":"NETWORKDAYS(AC533,AD533,MALegalHolidays)","v":46},0,46,"2017-04-20",null,{"$f":"NETWORKDAYS(AH533,AI533,MALegalHolidays)","v":-30553},null," ","2017-04-19",null,"2017-10-18",null,"COMP",null,null,null,null,null," ",null,null,"2018-11-15","on line"]
[null,"WMECO","Lee","6B1279-2016","01238",1860,"Solar","16B1","2016-11-15","2017-01-23",{"$f":"NETWORKDAYS(I534,J534,MALegalHolidays)","v":50},39,11,"2017-01-24","2017-03-22",{"$f":"NETWORKDAYS(N534,O534,MALegalHolidays)","v":42},3,39,null,null,null,null," ",null,null,null,null," ","2017-03-23","2017-07-24",{"$f":"NETWORKDAYS(AC534,AD534,MALegalHolidays)","v":88},17,71,"2017-07-25","2017-11-03",{"$f":"NETWORKDAYS(AH534,AI534,MALegalHolidays)","v":74},0,74,"2017-11-03",null,"Sept 2017",null,"STD",null,null,null,null,null," ",null,null,"2018-08-24","applicant submitted second option, requires T ROW study, negotiated timeline due to complicated ROW interconnection, 10 days initial review, 10 days Impact Study."]
[null,"WMECO","Lanesborough","6B1280-2016","01237",4491,"Solar","15E1","2016-11-15","2017-02-13",{"$f":"NETWORKDAYS(I535,J535,MALegalHolidays)","v":65},58,7,"2017-02-14","2017-03-22",{"$f":"NETWORKDAYS(N535,O535,MALegalHolidays)","v":27},21,6,null,null,null,null," ",null,null,null,null," ","2017-03-23",null,{"$f":"NETWORKDAYS(AC535,AD535,MALegalHolidays)","v":-30533},null," ",null,null,null,null," ",null,null,"Sept 2017",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated timeline - 20 days, cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1281-2016","01201",1500,"Solar","15E2","2016-11-15","2017-01-23",{"$f":"NETWORKDAYS(I536,J536,MALegalHolidays)","v":50},39,11,"2017-01-04",null,{"$f":"NETWORKDAYS(N536,O536,MALegalHolidays)","v":-30477},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Sept 2017",null,"STD",null,null,null,null,null," ",null,null,null,"applicant submitted options, cancelled"]
[null,"WMECO","Montague","6F1738-2016","01351",4080,"Solar","21C8","2016-11-15","2017-02-17",{"$f":"NETWORKDAYS(I537,J537,MALegalHolidays)","v":69},64,5,"2017-02-21","2017-03-22",{"$f":"NETWORKDAYS(N537,O537,MALegalHolidays)","v":22},16,6,null,null,null,null," ",null,null,null,null," ","2017-03-23","2017-07-28",{"$f":"NETWORKDAYS(AC537,AD537,MALegalHolidays)","v":92},16,76,"2017-07-31","2017-10-02",{"$f":"NETWORKDAYS(AH537,AI537,MALegalHolidays)","v":46},0,46,"2017-10-19",null,"Sept 2017",null,"COMP",null,null,null,null,null," ",null,null,"2018-10-12","second option submitted, Negotiated timeline - 15 days"]
[null,"WMECO","Ludlow","6S2989-2016","01056",1860,"Solar","19S1","2016-11-15","2017-01-23",{"$f":"NETWORKDAYS(I538,J538,MALegalHolidays)","v":50},39,11,"2017-01-24","2017-03-02",{"$f":"NETWORKDAYS(N538,O538,MALegalHolidays)","v":28},21,7,null,null,null,null," ",null,null,null,null," ","2017-03-03","2017-06-12",{"$f":"NETWORKDAYS(AC538,AD538,MALegalHolidays)","v":72},20,52,"2017-06-13","2017-10-03",{"$f":"NETWORKDAYS(AH538,AI538,MALegalHolidays)","v":81},0,81,"2017-10-17",null,"Sept 2017",null,"COMP",null,null,null,null,null," ",null,null,"2018-08-29","applicant submitted second option, requires T ROW study"]
[null,"WMECO","Agawam","6S2990-2016","01030",4140,"Solar","30A6","2016-11-15","2017-01-23",{"$f":"NETWORKDAYS(I539,J539,MALegalHolidays)","v":50},42,8,"2017-01-24","2017-03-02",{"$f":"NETWORKDAYS(N539,O539,MALegalHolidays)","v":28},13,15,null,null,null,null," ",null,null,null,null," ","2017-03-03","2017-05-12",{"$f":"NETWORKDAYS(AC539,AD539,MALegalHolidays)","v":51},0,51,null,null,null,null," ",null,null,"Sept 2017",null,"COMP",null,null,null,null,null," ",null,null,null,"applicant submitted second option, cancelled by applicant"]
[null,"WMECO","Agawam","6S2996-2016","01001",95.4,"Solar","16C16","2016-11-15","2016-12-05",{"$f":"NETWORKDAYS(I540,J540,MALegalHolidays)","v":15},11,4,"2016-12-05","2016-12-15",{"$f":"NETWORKDAYS(N540,O540,MALegalHolidays)","v":9},6,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2016-12-15",null,"12/23/2016",null,"EXP",null,null,null,null,null," ","2017-07-10","2017-07-12","2017-07-18"]
[null,"WMECO","Pittsfield","6B1282-2016","01201",1590,"Solar","30B7","2016-11-16","2016-12-01",{"$f":"NETWORKDAYS(I541,J541,MALegalHolidays)","v":12},6,6,"2016-12-02","2016-12-19",{"$f":"NETWORKDAYS(N541,O541,MALegalHolidays)","v":12},4,8,"2016-12-20","2017-02-08",{"$f":"NETWORKDAYS(S541,T541,MALegalHolidays)","v":37},15,22,null,null,null,null," ","2017-02-09","2017-04-11",{"$f":"NETWORKDAYS(AC541,AD541,MALegalHolidays)","v":44},0,44,"2017-04-21",null,{"$f":"NETWORKDAYS(AH541,AI541,MALegalHolidays)","v":-30554},null," ","2017-04-26",null,"12/2016",null,"STD",null,null,null,null,null," ",null,"2018-08-10","2018-09-10","applicant submitted options"]
[null,"WMECO","Hadley","6A2172-2016","01035",1630,"Solar","19B15","2016-11-21","2017-01-23",{"$f":"NETWORKDAYS(I542,J542,MALegalHolidays)","v":46},35,11,"2017-01-24","2017-03-02",{"$f":"NETWORKDAYS(N542,O542,MALegalHolidays)","v":28},21,7,null,null,null,null," ",null,null,null,null," ","2017-03-03","2017-05-19",{"$f":"NETWORKDAYS(AC542,AD542,MALegalHolidays)","v":56},0,56,null,null,null,null," ",null,null,"2017-09-28",null,"STD",null,null,null,null,null," ",null,null,null,"applicant submitted second option, cancelled by applicant"]
[null,"WMECO","Lee","6B1290-2016","01238",999,"Solar","16B1","2016-11-21","2016-12-01",{"$f":"NETWORKDAYS(I543,J543,MALegalHolidays)","v":9},7,2,"2016-12-02",null,{"$f":"NETWORKDAYS(N543,O543,MALegalHolidays)","v":-30454},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"5/1/2017",null,"STD",null,null,null,null,null," ",null,null,null,"applicant submitted two options, negotiated 10 days, applicant cancelled application"]
[null,"WMECO","Agawam","6S3021-2016","01030",849.7,"Solar","30A6","2016-11-21","2017-02-28",{"$f":"NETWORKDAYS(I544,J544,MALegalHolidays)","v":72},65,7,"2017-03-01","2017-03-22",{"$f":"NETWORKDAYS(N544,O544,MALegalHolidays)","v":16},10,6,null,null,null,null," ",null,null,null,null," ","2017-03-23",null,{"$f":"NETWORKDAYS(AC544,AD544,MALegalHolidays)","v":-30533},24," ",null,null,null,null," ",null,null,"9/28/2017",null,"STD",null,null,null,null,null," ",null,null,null,"applicant submitted a smaller option to proceed with, on hold behind another application 6S2990-2016, cancelled by applicant"]
[null,"WMECO","Montague","6A2182-2016","01351",450,"Solar","21C8","2016-11-22","2017-01-03",{"$f":"NETWORKDAYS(I545,J545,MALegalHolidays)","v":31},27,4,"2017-01-04","2017-04-05",{"$f":"NETWORKDAYS(N545,O545,MALegalHolidays)","v":66},60,6,null,null,null,null," ",null,null,null,null," ","2017-04-06","2018-02-23",{"$f":"NETWORKDAYS(AC545,AD545,MALegalHolidays)","v":232},179,53,null,null,null,null," ","2018-02-28",null,"Dec 2016",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S3052-2016","01118",266.39999999999998,"Solar","20A32","2016-12-02","2017-04-03",{"$f":"NETWORKDAYS(I546,J546,MALegalHolidays)","v":87},81,6,"2017-04-04",null,{"$f":"NETWORKDAYS(N546,O546,MALegalHolidays)","v":-30541},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-06-30",null,"EXP",null,null,null,null,null," ",null,null,null,"three options, cancelled by applicant, not sure what they will install"]
[null,"WMECO","Agawam","6S3100-2016","01001",129.6,"Solar","30A2","2016-12-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-01-28",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Springfield","6S3147-2017","01103",1023.24,"Solar","08C31, 08C32","2017-01-03","2017-02-14",{"$f":"NETWORKDAYS(I548,J548,MALegalHolidays)","v":31},23,8,"2017-02-15",null,{"$f":"NETWORKDAYS(N548,O548,MALegalHolidays)","v":-30507},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-10-15",null,"EXP",null,null,null,null,null," ",null,null,null,"negotiated 20 days for option, cancelled by applicant"]
[null,"WMECO","Granville","6S3151-2017","01034",475,"Biogas","29A5","2017-01-03","2017-02-16",{"$f":"NETWORKDAYS(I549,J549,MALegalHolidays)","v":33},28,5,"2017-02-17","2017-04-27",{"$f":"NETWORKDAYS(N549,O549,MALegalHolidays)","v":50},46,4,null,null,null,null," ",null,null,null,null," ","2017-04-28","2017-07-20",{"$f":"NETWORKDAYS(AC549,AD549,MALegalHolidays)","v":60},11,49,"2017-07-21","2017-10-03",{"$f":"NETWORKDAYS(AH549,AI549,MALegalHolidays)","v":53},0,53,"2017-10-19",null,"2017-10-30",null,"STD",null,null,null,null,null," ",null,null,"2019-05-16","on line"]
[null,"WMECO","Hatfield","6A2232-2017","01088",334.42,"Solar","18G5","2017-01-09","2017-03-20",{"$f":"NETWORKDAYS(I550,J550,MALegalHolidays)","v":51},46,5,"2017-03-21",null,{"$f":"NETWORKDAYS(N550,O550,MALegalHolidays)","v":-30531},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"9/1/2017",null,"STD",null,null,null,null,null," ",null,null,null,"existing non export solar will be removed and replaced by new project, cancelled by applicant "]
[null,"WMECO","Pittsfield","6B1329-2017","01201",725,"Natural Gas","30B1","2017-01-10","2017-02-13",{"$f":"NETWORKDAYS(I551,J551,MALegalHolidays)","v":25},22,3,"2017-02-14","2017-04-21",{"$f":"NETWORKDAYS(N551,O551,MALegalHolidays)","v":49},36,13,"2017-04-24","2017-07-13",{"$f":"NETWORKDAYS(S551,T551,MALegalHolidays)","v":59},40,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-07-24",null,"11/1/2017",null,"EXP",null,null,null,null,null," ","2018-05-14","2018-05-23","2018-06-07"]
[null,"WMECO","Erving","6F1795-2017","01344",210,"Solar","21B9","2017-01-11","2017-03-15",{"$f":"NETWORKDAYS(I552,J552,MALegalHolidays)","v":46},40,6,"2017-03-16",null,{"$f":"NETWORKDAYS(N552,O552,MALegalHolidays)","v":-30528},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-08-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Chicopee","6S3180-2017","01013",2535,"Solar","21N7","2017-01-18","2017-02-14",{"$f":"NETWORKDAYS(I553,J553,MALegalHolidays)","v":20},8,12,"2017-02-15","2017-03-09",{"$f":"NETWORKDAYS(N553,O553,MALegalHolidays)","v":17},12,5,null,null,null,null," ",null,null,null,null," ","2017-03-10","2017-06-15",{"$f":"NETWORKDAYS(AC553,AD553,MALegalHolidays)","v":70},3,67,null,null,null,null," ","2017-06-30",null,"2017-08-31",null,"STD",null,null,null,null,null," ",null,null,null,"rcvd application, need check, rcvd check, rvw for app complete, requested info, rcvd info app complete, starteted initi revw, init revw sent out customer, customer requested two options, started Impact Study agreement, sent impact study agreement to customer.  Draft report sent ot engineering for review.  Negotiated 20 days to develope new DTT for this type of circuit.  Withdrawn, applicant did not execute Detailed Study."]
[null,"WMECO","Springfield","6S3184-2017","01103",6250,"Diesel","8C31","2017-01-19","2017-02-17",{"$f":"NETWORKDAYS(I554,J554,MALegalHolidays)","v":22},12,10,"2017-02-21","2017-05-08",{"$f":"NETWORKDAYS(N554,O554,MALegalHolidays)","v":55},18,37,null,null,null,null," ",null,null,null,null," ","2017-05-09","2017-08-04",{"$f":"NETWORKDAYS(AC554,AD554,MALegalHolidays)","v":64},55,9,null,null,null,null," ","2017-08-24",null,"Not supplied",null,"STD",null,null,null,null,null," ","2017-09-15","2017-09-18","2017-09-25","Negotiated 10 extra days for option and for customer to make decisions. 2 design options, applicant going with only 2 emergency generators on this app"]
[null,"WMECO","Greenfield","6F1810-2017","01301",250,"Solar","22B7","2017-01-24","2017-03-01",{"$f":"NETWORKDAYS(I555,J555,MALegalHolidays)","v":27},12,15,"2017-03-01",null,{"$f":"NETWORKDAYS(N555,O555,MALegalHolidays)","v":-30517},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-05-01",null,"EXP",null,null,null,null,null," ",null,null,null,"Was on hold behind prior app on same circuit.  Negotiated timeline - IC granted 25 day extension to initial review and 30 days for technical information required. Cancelled by applicant"]
[null,"WMECO","Greenfield","6F1809-2017","01301",294,"Solar","22B7","2017-01-25","2017-03-01",{"$f":"NETWORKDAYS(I556,J556,MALegalHolidays)","v":26},12,14,"2017-03-01",null,{"$f":"NETWORKDAYS(N556,O556,MALegalHolidays)","v":-30517},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-05-01",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn after the applicants did not move forward"]
[null,"WMECO","Savoy","6B1350-2017","01256",7500,"Wind","18C1","2017-02-01","2017-02-23",{"$f":"NETWORKDAYS(I557,J557,MALegalHolidays)","v":17},12,5,"2017-02-24","2017-03-28",{"$f":"NETWORKDAYS(N557,O557,MALegalHolidays)","v":23},15,8,null,null,null,null," ",null,null,null,null," ","2017-03-29","2018-02-22",{"$f":"NETWORKDAYS(AC557,AD557,MALegalHolidays)","v":237},106,131,"2018-02-23",null,{"$f":"NETWORKDAYS(AH557,AI557,MALegalHolidays)","v":-30774},null," ",null,null,"Sept 2018",null,"COMP",null,null,null,null,null," ",null,null,null,"Applicant submitted 2 options.  Negotiated timeline - 20 days Impact Study.  Submitted another option.  Customer submitted another option.  Customer requested another extension, granted 42 days.  Cancelled by applicant."]
[null,"WMECO","Agawam","6S3221-2017","01001",1252,"Solar","30A3","2017-02-06","2017-02-22",{"$f":"NETWORKDAYS(I558,J558,MALegalHolidays)","v":13},4,9,"2017-02-23","2017-06-12",{"$f":"NETWORKDAYS(N558,O558,MALegalHolidays)","v":78},52,26,null,null,null,null," ",null,null,null,null," ","2017-06-13",null,{"$f":"NETWORKDAYS(AC558,AD558,MALegalHolidays)","v":-30591},null," ","2017-08-17",null,{"$f":"NETWORKDAYS(AH558,AI558,MALegalHolidays)","v":-30638},null," ",null,null,"May 2017",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated timeline, 10 extra days for submittal and review of new drawing/option.  Cancelled by applicant."]
[null,"WMECO","Agawam","6S3222-2017","01001",167,"Solar","30A3","2017-02-06","2017-02-22",{"$f":"NETWORKDAYS(I559,J559,MALegalHolidays)","v":13},4,9,"2017-02-23",null,{"$f":"NETWORKDAYS(N559,O559,MALegalHolidays)","v":-30513},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"May 2017",null,"EXP",null,null,null,null,null," ",null,null,null,"Negotiated timeline for option, 10 extra days, on hold behind another app on same circuit, submitted an option, negotiated 7 extra days, applicant cancelled"]
[null,"WMECO","Agawam","6S3223-2017","01001",72,"Solar","30A3","2017-02-06","2017-02-22",{"$f":"NETWORKDAYS(I560,J560,MALegalHolidays)","v":13},4,9,"2017-02-23",null,{"$f":"NETWORKDAYS(N560,O560,MALegalHolidays)","v":-30513},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"May 2017",null,"EXP",null,null,null,null,null," ",null,null,null,"Negotiated timeline, 20 extra days for submittal of new options, need information.  On hold behind another app on same circuit.  Applicant cancelled."]
[null,"WMECO","Springfield","6S3230-2017","01103",16.2,"Solar","8CNW_1","2017-02-08","2017-03-16",{"$f":"NETWORKDAYS(I561,J561,MALegalHolidays)","v":27},19,8,"2017-03-17","2017-04-13",{"$f":"NETWORKDAYS(N561,O561,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-04-10",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A2263-2017","01002",3120,"Solar","18G4","2017-02-09","2017-02-15",{"$f":"NETWORKDAYS(I562,J562,MALegalHolidays)","v":5},4,1,"2017-02-16","2017-05-04",{"$f":"NETWORKDAYS(N562,O562,MALegalHolidays)","v":56},44,12,null,null,null,null," ",null,null,null,null," ","2017-05-05","2017-08-04",{"$f":"NETWORKDAYS(AC562,AD562,MALegalHolidays)","v":66},15,51,"2017-08-07",null,{"$f":"NETWORKDAYS(AH562,AI562,MALegalHolidays)","v":-30630},null," ","2017-08-23",null,"2017-12-01",null,"STD",null,null,null,null,null," ",null,null,"2019-12-20","on line"]
[null,"WMECO","Worthington","6A2274-2017","01098",5000,"Solar","18K3","2017-02-13","2017-03-01",{"$f":"NETWORKDAYS(I563,J563,MALegalHolidays)","v":13},10,3,"2017-03-02",null,{"$f":"NETWORKDAYS(N563,O563,MALegalHolidays)","v":-30518},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-01-15",null,"STD",null,null,null,null,null," ",null,null,null,"Negotiated 15 days at request of applicant.  Withdrawn after missed deadlines and applicant did not execute Impact Study Agreement."]
[null,"WMECO","Blandford","6B1362-2017","01008",1000,"Solar","19J2","2017-02-13","2017-02-27",{"$f":"NETWORKDAYS(I564,J564,MALegalHolidays)","v":11},7,4,"2017-02-28","2017-04-14",{"$f":"NETWORKDAYS(N564,O564,MALegalHolidays)","v":34},20,14,null,null,null,null," ",null,null,null,null," ","2017-04-17","2017-08-08",{"$f":"NETWORKDAYS(AC564,AD564,MALegalHolidays)","v":82},38,44,"2017-08-09","2017-11-17",{"$f":"NETWORKDAYS(AH564,AI564,MALegalHolidays)","v":73},4,69,"2017-11-17",null,"Dec 2017",null,"STD",null,null,null,null,null," ",null,null,"2019-11-15","on line"]
[null,"WMECO","Hinsdale","6B1363-2017","01235",5000,"Solar","18C2","2017-02-13","2017-03-16",{"$f":"NETWORKDAYS(I565,J565,MALegalHolidays)","v":24},21,3,"2017-03-17",null,{"$f":"NETWORKDAYS(N565,O565,MALegalHolidays)","v":-30529},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Dec 2017",null,"STD",null,null,null,null,null," ",null,null,null,"three options, withdrawn after 10 day extension, notices and decision by applicant to have application withdrawn"]
[null,"WMECO","Pittsfield","6B1365-2017","01201",499.5,"Solar","30B5","2017-02-15","2017-03-29",{"$f":"NETWORKDAYS(I566,J566,MALegalHolidays)","v":31},20,11,"2017-03-30",null,{"$f":"NETWORKDAYS(N566,O566,MALegalHolidays)","v":-30538},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Dalton","6B1366-2017","01226",499.5,"Solar","19A3","2017-02-15","2017-03-29",{"$f":"NETWORKDAYS(I567,J567,MALegalHolidays)","v":31},20,11,"2017-03-30","2017-05-05",{"$f":"NETWORKDAYS(N567,O567,MALegalHolidays)","v":27},22,5,null,null,null,null," ",null,null,null,null," ","2017-05-08","2017-08-14",{"$f":"NETWORKDAYS(AC567,AD567,MALegalHolidays)","v":71},26,45,"2017-08-24",null,{"$f":"NETWORKDAYS(AH567,AI567,MALegalHolidays)","v":-30643},null," ","2017-08-14",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2018-12-28"]
[null,"WMECO","Cummington","6A2290-2017","01026",10.95,"Solar","18K3","2017-02-23","2017-03-06",{"$f":"NETWORKDAYS(I568,J568,MALegalHolidays)","v":8},4,4,"2017-03-06","2017-04-28",{"$f":"NETWORKDAYS(N568,O568,MALegalHolidays)","v":40},24,16,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-04-28",null,"2017-05-15",null,"EXP",null,null,null,null,null," ","2017-06-26","2017-06-30","2017-06-30"]
[null,"WMECO","Pittsfield","6B1375-2017","01201",1160,"Solar","15E2","2017-02-27","2017-03-08",{"$f":"NETWORKDAYS(I569,J569,MALegalHolidays)","v":8},6,2,"2017-03-08","2017-03-22",{"$f":"NETWORKDAYS(N569,O569,MALegalHolidays)","v":11},8,3,null,null,null,null," ",null,null,null,null," ","2017-03-23","2017-07-28",{"$f":"NETWORKDAYS(AC569,AD569,MALegalHolidays)","v":92},16,76,"2017-07-31","2017-09-29",{"$f":"NETWORKDAYS(AH569,AI569,MALegalHolidays)","v":45},9,36,"2017-10-06",null,"2017-09-01",null,"STD",null,null,null,null,null," ",null,null,"2018-08-17","Negotiated timeline - 20 days"]
[null,"WMECO","Lanesborough","6B1377-2017","01237",1998,"Solar","15E1","2017-02-28","2017-04-11",{"$f":"NETWORKDAYS(I570,J570,MALegalHolidays)","v":31},28,{"$f":"IF(K570>0,K570-L570,\" \")","v":3},"2017-04-12",null,{"$f":"NETWORKDAYS(N570,O570,MALegalHolidays)","v":-30547},9,{"$f":"IF(P570>0,P570-Q570,\" \")","v":" "},null,null,null,null,{"$f":"IF(U570>0,U570-V570,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z570>0,Z570-AA570,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE570>0,AE570-AF570,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ570>0,AJ570-AK570,\" \")","v":" "},null,null,"Not supplied",null,"STD",null,null,null,null,null,{"$f":"IF(AU570>0,AU570-AV570,\" \")","v":" "},null,null,null,"application on hold behind another application intil the first Impact Study is completed, app now moving forward, cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1378-2017","01201",27.44,"Solar","19A7","2017-02-28","2017-03-29",{"$f":"NETWORKDAYS(I571,J571,MALegalHolidays)","v":22},21,1,"2017-03-29","2017-04-20",{"$f":"NETWORKDAYS(N571,O571,MALegalHolidays)","v":17},15,2,"2017-04-21","2017-07-14",{"$f":"NETWORKDAYS(S571,T571,MALegalHolidays)","v":61},0,61,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-07-14",null,"Aug 2017",null,"EXP",null,null,null,null,null," ","3821/18","2018-03-21","2018-03-23"]
[null,"WMECO","Greenfield","6A2305-2017","01337",995,"Biogas","22B7","2017-03-06","2017-03-20",{"$f":"NETWORKDAYS(I572,J572,MALegalHolidays)","v":11},9,2,"2017-03-21",null,{"$f":"NETWORKDAYS(N572,O572,MALegalHolidays)","v":-30531},30," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"Sent 10 day notice for missed deadline, application cancelled by application"]
[null,"WMECO","Worthington","6A2316-2017","01098",21.9,"Solar","18K3","2017-03-09","2017-03-30",{"$f":"NETWORKDAYS(I573,J573,MALegalHolidays)","v":16},14,2,"2017-03-30",null,{"$f":"NETWORKDAYS(N573,O573,MALegalHolidays)","v":-30538},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-06-15",null,"EXP",null,null,null,null,null," ",null,null,null,"Applicant sent Supplemental Review, sent 10 day notice to move forward or withdraw, applicant decided not to proceed, withdrawn at applicant's request."]
[null,"WMECO","Lanesborough","6B1399-2017","01237",1998,"Solar","15E1","2017-03-20",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn 4/24/17, applicant said this was a duplicate of another application 6B1377-2017"]
[null,"WMECO","Gill","6A2364-2017","01354",4998.3999999999996,"Solar","21C5","2017-03-29","2017-04-17",{"$f":"NETWORKDAYS(I575,J575,MALegalHolidays)","v":14},7,7,"2017-04-18","2017-07-24",{"$f":"NETWORKDAYS(N575,O575,MALegalHolidays)","v":70},29,41,null,null,null,null," ",null,null,null,null," ","2017-07-25","2017-12-18",{"$f":"NETWORKDAYS(AC575,AD575,MALegalHolidays)","v":105},18,87,null,null,null,null," ",null,null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"Negotiated timeline 25 days to review 3 options, 20 days for review, Complex 20 extra days for Impact Study, applicant must pick option to proceed to Detailed Study with.  Cancelled by applicant."]
[null,"WMECO","Longmeadow","6S3353-2017","01106",86.4,"Solar","22H15","2017-04-07",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"5/7",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Amherst","6A2398-2017","01059",996,"Solar","18G7","2017-04-12","2017-06-16",{"$f":"NETWORKDAYS(I577,J577,MALegalHolidays)","v":48},41,7,"2017-06-19",null,{"$f":"NETWORKDAYS(N577,O577,MALegalHolidays)","v":-30595},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"on hold behind other apps on circuit, negotiated 10 days to tech review, cancelled by applicant"]
[null,"WMECO","Amherst","6A2399-2017","01059",4980,"Battery","18G7","2017-04-12","2017-06-16",{"$f":"NETWORKDAYS(I578,J578,MALegalHolidays)","v":48},41,7,"2017-06-19","2017-08-08",{"$f":"NETWORKDAYS(N578,O578,MALegalHolidays)","v":37},28,9,null,null,null,null," ",null,null,null,null," ","2017-08-09","2017-10-17",{"$f":"NETWORKDAYS(AC578,AD578,MALegalHolidays)","v":50},0,50,"2017-12-15",null,{"$f":"NETWORKDAYS(AH578,AI578,MALegalHolidays)","v":-30724},null," ","2017-10-30",null,"2017-12-31",null,"STD",null,null,null,null,null," ",null,null,"2019-07-30","on line"]
[null,"WMECO","Amherst","6A2400-2017","01059",996,"Solar","18G7","2017-04-12","2017-06-16",{"$f":"NETWORKDAYS(I579,J579,MALegalHolidays)","v":48},41,7,"2017-06-19",null,{"$f":"NETWORKDAYS(N579,O579,MALegalHolidays)","v":-30595},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"on hold behind other apps on circuit, negotiated 10 days to tech review, cancelled by applicant"]
[null,"WMECO","West Springfield","6S3370-2017","01089",300,"Natural Gas","21N5","2017-04-13","2017-07-20",{"$f":"NETWORKDAYS(I580,J580,MALegalHolidays)","v":71},67,4,"2017-07-21","2017-10-10",{"$f":"NETWORKDAYS(N580,O580,MALegalHolidays)","v":58},49,9,null,null,null,null," ",null,null,null,null," ","2017-10-11","2017-11-10",{"$f":"NETWORKDAYS(AC580,AD580,MALegalHolidays)","v":23},0,23,null,null,null,null," ",null,null,"2/2018",null,"COMP",null,null,null,null,null," ",null,null,null,"negitiated 20 days for review, 2 designs, cancelled by applicant"]
[null,"WMECO","Springfield","6S3392-2017","01118",165,"Solar","20A32","2017-04-21","2017-05-01",{"$f":"NETWORKDAYS(I581,J581,MALegalHolidays)","v":7},5,2,"2017-05-01","2017-05-08",{"$f":"NETWORKDAYS(N581,O581,MALegalHolidays)","v":6},3,3,"2017-05-09","2017-08-31",{"$f":"NETWORKDAYS(S581,T581,MALegalHolidays)","v":83},43,40,null,null,null,null," ","2017-09-01","2017-11-28",{"$f":"NETWORKDAYS(AC581,AD581,MALegalHolidays)","v":63},7,56,null,null,null,null," ","2017-11-28",null,"2017-06-30",null,"STD",null,null,null,null,null," ",null,null,null,"three options, negotiated an extra 25 days for Supp Review, cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1444-2017","01201",240,"Solar","15E2","2017-04-25","2017-05-15",{"$f":"NETWORKDAYS(I582,J582,MALegalHolidays)","v":15},13,2,"2017-05-16","2017-06-23",{"$f":"NETWORKDAYS(N582,O582,MALegalHolidays)","v":29},3,26,null,"2017-07-06",null,null," ",null,null,null,null," ","2017-06-23","2017-10-04",{"$f":"NETWORKDAYS(AC582,AD582,MALegalHolidays)","v":74},64,10,"2017-10-05","2017-12-21",{"$f":"NETWORKDAYS(AH582,AI582,MALegalHolidays)","v":56},0,56,"2017-12-21",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hatfield","6A2448-2017","01038",15.36,"Solar","18G6","2017-05-01","2017-05-12",{"$f":"NETWORKDAYS(I583,J583,MALegalHolidays)","v":10},7,3,"2017-05-12",null,{"$f":"NETWORKDAYS(N583,O583,MALegalHolidays)","v":-30569},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-05-29",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Lanesborough","6B1446-2017","01237",2597.4,"Solar","15E2","2017-05-04","2017-05-18",{"$f":"NETWORKDAYS(I584,J584,MALegalHolidays)","v":11},2,9,"2017-05-19",null,{"$f":"NETWORKDAYS(N584,O584,MALegalHolidays)","v":-30574},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"application on hold behind an earlier application, application cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1447-2017","01201",1998,"Solar","19A4","2017-05-05","2017-05-18",{"$f":"NETWORKDAYS(I585,J585,MALegalHolidays)","v":10},3,7,"2017-05-19","2017-06-02",{"$f":"NETWORKDAYS(N585,O585,MALegalHolidays)","v":11},6,5,null,null,null,null," ",null,null,null,null," ","2017-06-05","2017-08-23",{"$f":"NETWORKDAYS(AC585,AD585,MALegalHolidays)","v":58},4,54,"2017-08-24",null,{"$f":"NETWORKDAYS(AH585,AI585,MALegalHolidays)","v":-30643},null," ","2017-08-30",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2018-12-21"]
[null,"WMECO","Blandford","6B1451-2017","01008",4700,"Solar","19J4","2017-05-08","2017-08-18",{"$f":"NETWORKDAYS(I586,J586,MALegalHolidays)","v":75},60,15,"2017-08-21","2017-09-14",{"$f":"NETWORKDAYS(N586,O586,MALegalHolidays)","v":19},11,8,null,null,null,null," ",null,null,null,null," ","2017-09-15","2017-12-04",{"$f":"NETWORKDAYS(AC586,AD586,MALegalHolidays)","v":57},10,47,"2017-12-19",null,{"$f":"NETWORKDAYS(AH586,AI586,MALegalHolidays)","v":-30726},null," ","2017-12-04",null,"2018-09-01",null,"COMP",null,null,null,null,null," ",null,null,"2020-06-30","on line"]
[null,"WMECO","Springfield","6S3435-2017","01104",1440,"Solar","5J11","2017-05-08","2017-06-01",{"$f":"NETWORKDAYS(I587,J587,MALegalHolidays)","v":19},9,10,"2017-06-02","2017-07-19",{"$f":"NETWORKDAYS(N587,O587,MALegalHolidays)","v":34},30,4,null,null,null,null," ",null,null,null,null," ","2017-07-20","2017-11-02",{"$f":"NETWORKDAYS(AC587,AD587,MALegalHolidays)","v":76},17,59,"2017-11-10",null,{"$f":"NETWORKDAYS(AH587,AI587,MALegalHolidays)","v":-30699},null," ","2017-12-11",null,"Nov 2017",null,"COMP",null,null,null,null,null," ",null,null,"2018-10-17","two options, negotisated an extra 25 days"]
[null,"WMECO","Pittsfield","6B1454-2017","01201",1556,"Solar","30B5","2017-05-11","2017-06-19",{"$f":"NETWORKDAYS(I588,J588,MALegalHolidays)","v":28},21,7,"2017-06-20",null,{"$f":"NETWORKDAYS(N588,O588,MALegalHolidays)","v":-30596},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-01-01",null,"STD",null,null,null,null,null," ",null,null,null,"three options, negotiated 10 days to initial review, Impact Study Agreement not executed, cancelled at applicant's request"]
[null,"WMECO","Cummington","6A2489-2017","01026",480,"Solar","18K3","2017-05-12","2017-06-06",{"$f":"NETWORKDAYS(I589,J589,MALegalHolidays)","v":18},13,5,"2017-06-07","2017-07-17",{"$f":"NETWORKDAYS(N589,O589,MALegalHolidays)","v":29},22,7,null,null,null,null," ",null,null,null,null," ","2017-07-18","2017-09-28",{"$f":"NETWORKDAYS(AC589,AD589,MALegalHolidays)","v":53},0,53,null,null,null,null," ",null,null,"2018-02-15",null,"COMP",null,null,null,null,null," ",null,null,null,"2 options, cancelled by applicant"]
[null,"WMECO","Cummington","6A2491-2017","01026",240,"Solar","18K3","2017-05-12","2017-06-06",{"$f":"NETWORKDAYS(I590,J590,MALegalHolidays)","v":18},13,5,"2017-06-07",null,{"$f":"NETWORKDAYS(N590,O590,MALegalHolidays)","v":-30587},111," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-02-15",null,"STD",null,null,null,null,null," ",null,null,null,"on hold behind another app in queue, sent 10 day notice, withdrawn after missed deadlines"]
[null,"WMECO","Shelburne","6A2495-2017","01370",60,"Solar","29R2","2017-05-17","2017-05-25",{"$f":"NETWORKDAYS(I591,J591,MALegalHolidays)","v":7},2,5,"2017-05-25","2017-06-05",{"$f":"NETWORKDAYS(N591,O591,MALegalHolidays)","v":8},5,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-06-09",null,"Not supplied",null,"EXP",null,null,null,null,null," ","2018-01-31","2018-02-02","2018-02-02"]
[null,"WMECO","Easthampton","6A2529-2017","01027",1095.8,"Solar","15A5","2017-05-25","2017-08-17",{"$f":"NETWORKDAYS(I592,J592,MALegalHolidays)","v":61},51,10,"2017-08-18","2017-10-27",{"$f":"NETWORKDAYS(N592,O592,MALegalHolidays)","v":51},37,14,null,null,null,null," ",null,null,null,null," ","2017-10-30","2018-03-15",{"$f":"NETWORKDAYS(AC592,AD592,MALegalHolidays)","v":99},21,78,"2018-03-16","2018-06-26",{"$f":"NETWORKDAYS(AH592,AI592,MALegalHolidays)","v":73},11,62,"2018-06-29",null,"2018-04-15",null,"COMP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Deerfield","6A2524-2017","01342",72,"Solar","22B1","2017-05-30","2017-06-08",{"$f":"NETWORKDAYS(I593,J593,MALegalHolidays)","v":8},5,3,"2017-06-09","2017-06-22",{"$f":"NETWORKDAYS(N593,O593,MALegalHolidays)","v":10},2,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-06-22",null,"2017",null,"EXP",null,null,null,null,null," ","2017-12-26","2017-12-17","2018-01-12"]
[null,"WMECO","Dalton","6B1482-2017","01226",4980,"Solar","29M1","2017-06-02","2017-06-15",{"$f":"NETWORKDAYS(I594,J594,MALegalHolidays)","v":10},6,4,"2017-06-16",null,{"$f":"NETWORKDAYS(N594,O594,MALegalHolidays)","v":-30594},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2017",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Lanesborough","6B1483-2017","01237",4980,"Solar","15E2","2017-06-02","2017-06-15",{"$f":"NETWORKDAYS(I595,J595,MALegalHolidays)","v":10},6,4,"2017-06-16",null,{"$f":"NETWORKDAYS(N595,O595,MALegalHolidays)","v":-30594},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2017",null,"STD",null,null,null,null,null," ",null,null,null,"negotiated 10 days initial review, cancelled by applicant"]
[null,"WMECO","Southwick","6S3507-2017","01077",4980,"Solar","29A1","2017-06-02","2017-06-15",{"$f":"NETWORKDAYS(I596,J596,MALegalHolidays)","v":10},6,4,"2017-06-16","2017-09-01",{"$f":"NETWORKDAYS(N596,O596,MALegalHolidays)","v":56},48,8,null,null,null,null," ",null,null,null,null," ","2017-09-05","2017-10-20",{"$f":"NETWORKDAYS(AC596,AD596,MALegalHolidays)","v":34},0,34,"2017-10-31",null,{"$f":"NETWORKDAYS(AH596,AI596,MALegalHolidays)","v":-30691},null," ","2017-10-30",null,"1905-07-09",null,"STD",null,null,null,null,null," ",null,null,"2019-02-01"]
[null,"WMECO","Greenfield","6A2544-2017","01301",380,"Solar","22B2","2017-06-06","2017-06-20",{"$f":"NETWORKDAYS(I597,J597,MALegalHolidays)","v":11},4,7,"2017-06-21","2017-09-25",{"$f":"NETWORKDAYS(N597,O597,MALegalHolidays)","v":69},30,39,"2017-09-26","2017-12-28",{"$f":"NETWORKDAYS(S597,T597,MALegalHolidays)","v":68},41,27,null,null,null,null," ","2017-12-29","2018-02-02",{"$f":"NETWORKDAYS(AC597,AD597,MALegalHolidays)","v":26},8,18,null,null,null,null," ","2018-02-07",null,"10-17",null,"STD",null,null,null,null,null," ",null,"2018-04-27","2018-04-30","negotiated, 15 days, 2 options"]
[null,"WMECO","Hatfield","6A2545-2017","01038",380,"Biogas","18G6","2017-06-06","2017-06-30",{"$f":"NETWORKDAYS(I598,J598,MALegalHolidays)","v":19},10,9,"2017-07-03","2017-07-27",{"$f":"NETWORKDAYS(N598,O598,MALegalHolidays)","v":19},8,11,null,null,null,null," ",null,null,null,null," ","2017-07-28","2017-11-03",{"$f":"NETWORKDAYS(AC598,AD598,MALegalHolidays)","v":71},1,70,"2018-01-19",null,{"$f":"NETWORKDAYS(AH598,AI598,MALegalHolidays)","v":-30749},null," ","2017-11-10",null,"6/2018",null,"STD",null,null,null,null,null," ",null,null,"2019-05-21","on line"]
[null,"WMECO","Springfield","6S3522-2017","01151",3500,"Solar","27A13","2017-06-09","2017-09-22",{"$f":"NETWORKDAYS(I599,J599,MALegalHolidays)","v":76},35,41,"2017-09-25","2017-12-06",{"$f":"NETWORKDAYS(N599,O599,MALegalHolidays)","v":53},45,8,null,null,null,null," ",null,null,null,null," ","2017-12-07","2018-03-19",{"$f":"NETWORKDAYS(AC599,AD599,MALegalHolidays)","v":73},10,63,"2018-04-03",null,{"$f":"NETWORKDAYS(AH599,AI599,MALegalHolidays)","v":-30801},null," ","2018-04-10",null,"2018-06-07",null,"STD",null,null,null,null,null," ",null,null,"2019-12-27","on line"]
[null,"WMECO","Springfield","6S3523-2017","01151",2000,"Solar","27A13","2017-06-09","2017-09-22",{"$f":"NETWORKDAYS(I600,J600,MALegalHolidays)","v":76},33,43,"2017-09-25","2018-02-13",{"$f":"NETWORKDAYS(N600,O600,MALegalHolidays)","v":102},92,10,null,null,null,null," ",null,null,null,null," ","2018-02-14","2018-09-04",{"$f":"NETWORKDAYS(AC600,AD600,MALegalHolidays)","v":145},null,145,null,null,null,null," ","2018-08-15",null,"2018-06-07",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Longmeadow","6S3529-2017","01106",16,"Solar","22H12","2017-06-12","2017-06-22",{"$f":"NETWORKDAYS(I601,J601,MALegalHolidays)","v":9},3,6,"2017-06-22","2017-06-26",{"$f":"NETWORKDAYS(N601,O601,MALegalHolidays)","v":3},0,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-06-30",null,"2017-07-15",null,"EXP",null,null,null,null,null," ",null,null,"2017-11-08"]
[null,"WMECO","Pittsfield","6B1488-2017","01201",33.299999999999997,"Solar","30B5","2017-06-14","2017-07-13",{"$f":"NETWORKDAYS(I602,J602,MALegalHolidays)","v":22},13,9,"2017-07-13","2017-08-25",{"$f":"NETWORKDAYS(N602,O602,MALegalHolidays)","v":32},15,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-09-17",null,"2017-08-01",null,"EXP",null,null,null,null,null," ",null,null,"2023-08-04","on line"]
[null,"WMECO","Sunderland","6A2588-2017","01375",1084,"Solar","18G3","2017-06-15","2017-06-27",{"$f":"NETWORKDAYS(I603,J603,MALegalHolidays)","v":9},1,8,"2017-06-28","2017-08-24",{"$f":"NETWORKDAYS(N603,O603,MALegalHolidays)","v":42},30,12,null,null,null,null," ",null,null,null,null," ","2017-08-24","2017-10-19",{"$f":"NETWORKDAYS(AC603,AD603,MALegalHolidays)","v":41},0,41,"2017-11-10",null,{"$f":"NETWORKDAYS(AH603,AI603,MALegalHolidays)","v":-30699},null," ","2017-10-30",null,"DEC 2017",null,"STD",null,null,null,null,null," ",null,null,"2018-09-21"]
[null,"WMECO","Pittsfield","6B1490-2017","01201",499.5,"Solar","30B1","2017-06-15","2017-07-05",{"$f":"NETWORKDAYS(I604,J604,MALegalHolidays)","v":15},3,12,"2017-07-06",null,{"$f":"NETWORKDAYS(N604,O604,MALegalHolidays)","v":-30608},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"sent Impact Study Agreement to applicant, sent 10 day notice, applicant cancelled"]
[null,"WMECO","Pittsfield","6B1491-2017","01201",765.9,"Solar","30B1","2017-06-15","2017-07-03",{"$f":"NETWORKDAYS(I605,J605,MALegalHolidays)","v":13},3,10,"2017-07-05","2017-12-18",{"$f":"NETWORKDAYS(N605,O605,MALegalHolidays)","v":119},93,26,null,null,null,null," ",null,null,null,null," ","2017-12-19","2018-03-21",{"$f":"NETWORKDAYS(AC605,AD605,MALegalHolidays)","v":67},null,67,null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S3543-2017","01001",4989.8,"Solar","30A3","2017-06-15","2017-06-28",{"$f":"NETWORKDAYS(I606,J606,MALegalHolidays)","v":10},6,4,"2017-06-29",null,{"$f":"NETWORKDAYS(N606,O606,MALegalHolidays)","v":-30603},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Fall 2018",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Agawam","6S3544-2017","01001",4990,"Solar","30A3","2017-06-15","2017-06-30",{"$f":"NETWORKDAYS(I607,J607,MALegalHolidays)","v":12},6,6,"2017-07-03","2017-08-01",{"$f":"NETWORKDAYS(N607,O607,MALegalHolidays)","v":22},14,8,null,null,null,null," ",null,null,null,null," ","2017-08-02","2017-12-14",{"$f":"NETWORKDAYS(AC607,AD607,MALegalHolidays)","v":97},36,61,"2017-12-15","2018-03-15",{"$f":"NETWORKDAYS(AH607,AI607,MALegalHolidays)","v":65},12,53,"2018-03-16",null,"Fall 2018",null,"STD",null,null,null,null,null," ",null,null,"2020-12-11","on line"]
[null,"WMECO","Springfield","6S3549-2017","01104",4000,"Solar","5J18","2017-06-15","2017-06-27",{"$f":"NETWORKDAYS(I608,J608,MALegalHolidays)","v":9},1,8,"2017-06-28","2017-08-23",{"$f":"NETWORKDAYS(N608,O608,MALegalHolidays)","v":41},32,9,null,null,null,null," ",null,null,null,null," ","2017-08-24","2017-11-28",{"$f":"NETWORKDAYS(AC608,AD608,MALegalHolidays)","v":69},0,69,"2017-12-06",null,{"$f":"NETWORKDAYS(AH608,AI608,MALegalHolidays)","v":-30717},null," ","2017-12-05",null,"DEC 2017",null,"COMP",null,null,null,null,null," ",null,null,"2019-02-01","Negotiated 10 days for complicated system mods in Impact Study"]
[null,"WMECO","Amherst","6A2594-2017","01002",3875,"Solar","17K8","2017-06-19","2017-06-29",{"$f":"NETWORKDAYS(I609,J609,MALegalHolidays)","v":9},7,2,"2017-06-30","2017-08-29",{"$f":"NETWORKDAYS(N609,O609,MALegalHolidays)","v":43},31,12,null,null,null,null," ",null,null,null,null," ","2017-08-30","2017-11-01",{"$f":"NETWORKDAYS(AC609,AD609,MALegalHolidays)","v":46},null,46,null,null,null,null," ","2017-12-05",null,"7/18",null,"COMP",null,null,null,null,null," ",null,null,null,"in impact study"]
[null,"WMECO","Hinsdale","6B1495-2017","01235",999,"Solar","18C2","2017-06-19","2017-07-05",{"$f":"NETWORKDAYS(I610,J610,MALegalHolidays)","v":13},5,8,"2017-07-06","2017-08-18",{"$f":"NETWORKDAYS(N610,O610,MALegalHolidays)","v":32},23,9,null,null,null,null," ",null,null,null,null," ","2017-08-21","2017-10-24",{"$f":"NETWORKDAYS(AC610,AD610,MALegalHolidays)","v":47},0,47,"2017-11-29",null,{"$f":"NETWORKDAYS(AH610,AI610,MALegalHolidays)","v":-30712},null," ","2017-11-02",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2019-10-30","on line"]
[null,"WMECO","Feeding Hills","6S3555-2017","01030",18.88,"Solar","16C17","2017-06-19","2017-07-07",{"$f":"NETWORKDAYS(I611,J611,MALegalHolidays)","v":15},6,9,"2017-07-07",null,{"$f":"NETWORKDAYS(N611,O611,MALegalHolidays)","v":-30609},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-07-20",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn after applicant did not execute Supplemental Review Agreement "]
[null,"WMECO","Lanesborough","6B1497-2017","01237",499.5,"Solar","15E1","2017-06-21","2017-07-07",{"$f":"NETWORKDAYS(I612,J612,MALegalHolidays)","v":13},6,7,"2017-07-10","2017-10-04",{"$f":"NETWORKDAYS(N612,O612,MALegalHolidays)","v":63},55,8,null,null,null,null," ",null,null,null,null," ","2017-10-05","2017-12-14",{"$f":"NETWORKDAYS(AC612,AD612,MALegalHolidays)","v":51},0,51,"2018-01-26",null,{"$f":"NETWORKDAYS(AH612,AI612,MALegalHolidays)","v":-30754},null," ","2017-12-18",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2019-07-25","on line"]
[null,"WMECO","Southwick","6S3566-2017","01077",2000,"Solar","29A1","2017-06-21","2017-08-07",{"$f":"NETWORKDAYS(I613,J613,MALegalHolidays)","v":34},16,18,"2017-08-08",null,{"$f":"NETWORKDAYS(N613,O613,MALegalHolidays)","v":-30631},37," ",null,null,null,null," ",null,null,null,null," ",null,null,null,11," ",null,null,null,null," ",null,null,"Sept 2017",null,"STD",null,null,null,null,null," ",null,null,null,"10 day notice sent, negotiated timeline, second option, on hold behind another application, withdrawn due to missed deadlines"]
[null,"WMECO","Easthampton","6A2609-2017","01027",32.85,"Solar","15A5","2017-06-22","2017-06-28",{"$f":"NETWORKDAYS(I614,J614,MALegalHolidays)","v":5},0,5,"2017-06-28","2017-08-10",{"$f":"NETWORKDAYS(N614,O614,MALegalHolidays)","v":32},31,1,"2017-08-11","2017-08-25",{"$f":"NETWORKDAYS(S614,T614,MALegalHolidays)","v":11},0,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-08-28",null,"2017",null,"EXP",null,null,null,null,null," ","2018-08-30","2018-08-31","2018-08-31"]
[null,"WMECO","Agawam","6S3582-2017","01001",2330,"Solar","30A4","2017-06-29","2017-11-30",{"$f":"NETWORKDAYS(I615,J615,MALegalHolidays)","v":111},99,12,"2017-12-01",null,{"$f":"NETWORKDAYS(N615,O615,MALegalHolidays)","v":-30714},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S3583-2017","01001",5555,"Solar","30A4","2017-06-29","2017-12-14",{"$f":"NETWORKDAYS(I616,J616,MALegalHolidays)","v":121},112,9,"2017-12-14","2017-12-14",{"$f":"NETWORKDAYS(N616,O616,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S3584-2017","01001",5500,"Solar","30A4","2017-06-29","2017-11-30",{"$f":"NETWORKDAYS(I617,J617,MALegalHolidays)","v":111},99,12,"2017-12-01",null,{"$f":"NETWORKDAYS(N617,O617,MALegalHolidays)","v":-30714},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S3585-2017","01001",2330,"Solar","30A4","2017-06-29",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Blandford","6B1522-2017","01008",4920,"Solar","19J2","2017-07-17","2017-07-20",{"$f":"NETWORKDAYS(I619,J619,MALegalHolidays)","v":4},1,3,"2017-07-21","2017-11-10",{"$f":"NETWORKDAYS(N619,O619,MALegalHolidays)","v":81},31,50,null,null,null,null," ",null,null,null,null," ","2017-11-13","2018-03-13",{"$f":"NETWORKDAYS(AC619,AD619,MALegalHolidays)","v":87},7,80,"2018-06-29",null,{"$f":"NETWORKDAYS(AH619,AI619,MALegalHolidays)","v":-30864},null," ","2018-05-07",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,"2019-12-27","on line"]
[null,"WMECO","Hatfield","6A2693-2017","01038",3600,"Solar","18G5","2017-07-24","2017-07-27",{"$f":"NETWORKDAYS(I620,J620,MALegalHolidays)","v":4},0,4,"2017-07-27","2017-09-27",{"$f":"NETWORKDAYS(N620,O620,MALegalHolidays)","v":45},20,25,null,null,null,null," ",null,null,null,null," ","2017-09-28","2017-11-16",{"$f":"NETWORKDAYS(AC620,AD620,MALegalHolidays)","v":36},0,36,"2017-11-28",null,{"$f":"NETWORKDAYS(AH620,AI620,MALegalHolidays)","v":-30711},null," ","2017-11-27",null,"Nov 2017",null,"COMP",null,null,null,null,null," ",null,null,"2018-11-02","on line"]
[null,"WMECO","Amherst","6A2698-2017","01002",98.5,"Solar","18G4","2017-07-26","2017-09-22",{"$f":"NETWORKDAYS(I621,J621,MALegalHolidays)","v":43},33,10,"2017-09-25","2017-10-20",{"$f":"NETWORKDAYS(N621,O621,MALegalHolidays)","v":20},8,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-10-27",null,"2017",null,"EXP",null,null,null,null,null," ",null,null,"2018-03-30","on line"]
[null,"WMECO","Pittsfield","6B1539-2017","01201",4980,"Solar","15E2","2017-07-28","2017-09-11",{"$f":"NETWORKDAYS(I622,J622,MALegalHolidays)","v":32},22,10,"2017-09-12",null,{"$f":"NETWORKDAYS(N622,O622,MALegalHolidays)","v":-30656},44," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"two options, negotiated 20 extra days, withdrawn, applicant did not execute Impact Study agreement"]
[null,"WMECO","Deerfield","6A2710-2017","01342",2200,"Solar","22B4","2017-07-31","2017-08-09",{"$f":"NETWORKDAYS(I623,J623,MALegalHolidays)","v":8},1,7,"2017-08-10","2017-08-28",{"$f":"NETWORKDAYS(N623,O623,MALegalHolidays)","v":13},6,7,null,null,null,null," ",null,null,null,null," ","2017-08-29","2018-02-26",{"$f":"NETWORKDAYS(AC623,AD623,MALegalHolidays)","v":130},11,119,null,null,null,null," ","2018-06-20",null,"2018-03-02",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Easthampton","6A2718-2017","01027",2200,"Solar","15A2","2017-08-02","2017-08-28",{"$f":"NETWORKDAYS(I624,J624,MALegalHolidays)","v":19},15,4,"2017-08-28","2017-09-22",{"$f":"NETWORKDAYS(N624,O624,MALegalHolidays)","v":20},18,2,null,null,null,null," ",null,null,null,null," ","2017-09-25","2017-12-07",{"$f":"NETWORKDAYS(AC624,AD624,MALegalHolidays)","v":54},17,37,"2017-12-08","2018-03-23",{"$f":"NETWORKDAYS(AH624,AI624,MALegalHolidays)","v":76},21,55,"2018-04-02",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A2774-2017","01002",233.1,"Solar","17K8","2017-08-16","2017-08-25",{"$f":"NETWORKDAYS(I625,J625,MALegalHolidays)","v":8},3,5,"2017-08-28",null,{"$f":"NETWORKDAYS(N625,O625,MALegalHolidays)","v":-30645},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Amherst","6A2776-2017","01002",233.1,"Solar","17K2","2017-08-16","2017-08-25",{"$f":"NETWORKDAYS(I626,J626,MALegalHolidays)","v":8},3,5,"2017-08-28","2017-09-28",{"$f":"NETWORKDAYS(N626,O626,MALegalHolidays)","v":24},20,4,null,null,null,null," ",null,null,null,null," ","2017-09-29","2017-10-31",{"$f":"NETWORKDAYS(AC626,AD626,MALegalHolidays)","v":23},0,23,null,null,null,null," ",null,null,"2017",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Lee","6B1571-2017","01238",4993,"Solar","16B1","2017-08-24","2017-09-26",{"$f":"NETWORKDAYS(I627,J627,MALegalHolidays)","v":24},15,9,"2017-09-27","2018-06-20",{"$f":"NETWORKDAYS(N627,O627,MALegalHolidays)","v":191},62,129,null,null,null,null," ",null,null,null,null," ","2018-06-21","2018-11-05",{"$f":"NETWORKDAYS(AC627,AD627,MALegalHolidays)","v":98},null,98,null,null,null,null," ","2018-11-09",null,null,null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","West Springfield","6S3712-2017","01089",20,"Solar","21N4","2017-08-24","2017-09-19",{"$f":"NETWORKDAYS(I628,J628,MALegalHolidays)","v":19},4,15,"2017-09-20","2017-10-16",{"$f":"NETWORKDAYS(N628,O628,MALegalHolidays)","v":19},0,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-10-16",null,"2017",null,"EXP",null,null,null,null,null," ","2017-12-18","2017-12-21","2017-12-28","on line"]
[null,"WMECO","Greenfield","6A2815-2017","01301",7190,"Solar","21C1","2017-08-29","2017-09-21",{"$f":"NETWORKDAYS(I629,J629,MALegalHolidays)","v":18},4,14,"2017-09-22",null,{"$f":"NETWORKDAYS(N629,O629,MALegalHolidays)","v":-30664},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-18",null,"STD",null,null,null,null,null," ",null,null,null,"sent 10 day notice - cancelled by applicant"]
[null,"WMECO","Erving","6A2826-2017","01344",990,"Solar","21B8","2017-09-01","2017-10-12",{"$f":"NETWORKDAYS(I630,J630,MALegalHolidays)","v":30},20,10,"2017-10-13","2018-02-09",{"$f":"NETWORKDAYS(N630,O630,MALegalHolidays)","v":86},47,39,null,null,null,null," ",null,null,null,null," ","2018-02-09","2018-07-19",{"$f":"NETWORKDAYS(AC630,AD630,MALegalHolidays)","v":115},32,83,"2018-07-20",null,{"$f":"NETWORKDAYS(AH630,AI630,MALegalHolidays)","v":-30879},null," ","2018-08-15",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,"2020-09-11","on line"]
[null,"WMECO","Springfield","6S3764-2017","01105",72,"Solar","5J16","2017-09-08","2017-09-21",{"$f":"NETWORKDAYS(I631,J631,MALegalHolidays)","v":10},7,3,"2017-09-22","2017-12-07",{"$f":"NETWORKDAYS(N631,O631,MALegalHolidays)","v":55},33,22,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-12-08",null,"11/17",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Cummington","6A2837-2017","01026",999,"Solar","18K3","2017-09-11","2017-10-12",{"$f":"NETWORKDAYS(I632,J632,MALegalHolidays)","v":24},16,8,"2017-10-13",null,{"$f":"NETWORKDAYS(N632,O632,MALegalHolidays)","v":-30679},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Fall 2018",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Leverett","6A2858-2017","01054",366.3,"Solar","18G7","2017-09-14","2017-09-27",{"$f":"NETWORKDAYS(I633,J633,MALegalHolidays)","v":10},9,1,"2017-09-28","2017-11-02",{"$f":"NETWORKDAYS(N633,O633,MALegalHolidays)","v":26},7,19,null,null,null,null," ",null,null,null,null," ","2017-11-03","2018-01-23",{"$f":"NETWORKDAYS(AC633,AD633,MALegalHolidays)","v":58},0,58,null,null,null,null," ","2018-02-01",null,"2018-01-20",null,"STD",null,null,null,null,null," ",null,null,"2019-02-14","on line"]
[null,"WMECO","Springfield","6S3788-2017","01105",57.6,"Solar","8C26","2017-09-19","2017-09-28",{"$f":"NETWORKDAYS(I634,J634,MALegalHolidays)","v":8},7,{"$f":"IF(K634>0,K634-L634,\" \")","v":1},"2017-09-29","2018-01-22",{"$f":"NETWORKDAYS(N634,O634,MALegalHolidays)","v":82},53,{"$f":"IF(P634>0,P634-Q634,\" \")","v":29},null,null,null,null,{"$f":"IF(U634>0,U634-V634,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z634>0,Z634-AA634,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE634>0,AE634-AF634,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ634>0,AJ634-AK634,\" \")","v":" "},"2018-01-22",null,"2018-10-26",null,"EXP",null,null,null,null,null,{"$f":"IF(AU634>0,AU634-AV634,\" \")","v":" "},null,null,"2019-04-26","on line"]
[null,"WMECO","Springfield","6S3797-2017","01103",450,"Natural Gas","8C31","2017-09-20","2017-11-06",{"$f":"NETWORKDAYS(I635,J635,MALegalHolidays)","v":34},24,10,"2017-11-07","2017-12-05",{"$f":"NETWORKDAYS(N635,O635,MALegalHolidays)","v":21},6,15,"2017-12-06","2018-02-26",{"$f":"NETWORKDAYS(S635,T635,MALegalHolidays)","v":59},40,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-03-06",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A2885-2017","01002",2000,"Diesel","17K4, (17K5 N.O.)","2017-09-21","2017-10-18",{"$f":"NETWORKDAYS(I636,J636,MALegalHolidays)","v":20},13,7,"2017-10-19","2018-02-28",{"$f":"NETWORKDAYS(N636,O636,MALegalHolidays)","v":95},26,69,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-10",null,"Sept 2018",null,"EXP",null,null,null,null,null," ",null,null,"2018-11-20","on line"]
[null,"WMECO","South Deerfield","6A2888-2017","01373",57.5,"Solar","22B1","2017-09-22","2017-10-05",{"$f":"NETWORKDAYS(I637,J637,MALegalHolidays)","v":10},5,5,"2017-10-06","2017-11-07",{"$f":"NETWORKDAYS(N637,O637,MALegalHolidays)","v":23},21,2,"2017-11-08","2017-11-14",{"$f":"NETWORKDAYS(S637,T637,MALegalHolidays)","v":5},0,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-11-28",null,"Nov 2017",null,"EXP",null,null,null,null,null," ",null,null,"2018-04-20","on line"]
[null,"WMECO","South Deerfield","6A2889-2017","01373",57,"Solar","22B1","2017-09-22",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2017",null,"EXP",null,null,null,null,null," ",null,null,null,"3 phase facility, cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1612-2017","01201",22.8,"Solar","30B3","2017-09-22","2017-10-10",{"$f":"NETWORKDAYS(I639,J639,MALegalHolidays)","v":13},9,4,"2017-10-11",null,{"$f":"NETWORKDAYS(N639,O639,MALegalHolidays)","v":-30677},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"12/17",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Otis","6B1616-2017","01253",24,"Solar","19J4","2017-09-26","2017-10-04",{"$f":"NETWORKDAYS(I640,J640,MALegalHolidays)","v":7},5,2,"2017-10-05","2018-09-24",{"$f":"NETWORKDAYS(N640,O640,MALegalHolidays)","v":253},null,253,"2018-09-25","2018-10-23",{"$f":"NETWORKDAYS(S640,T640,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-10-23",null,"2017-11-22",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Southwick","6S3810-2017","01077",4980,"Solar","29A5","2017-09-27","2017-09-29",{"$f":"NETWORKDAYS(I641,J641,MALegalHolidays)","v":3},0,3,"2017-10-02",null,{"$f":"NETWORKDAYS(N641,O641,MALegalHolidays)","v":-30670},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"negotiated 10 days, cancelled by applicant"]
[null,"WMECO","Easthampton","6A2904-2017","01027",2460,"Solar","15A2","2017-09-28","2017-09-29",{"$f":"NETWORKDAYS(I642,J642,MALegalHolidays)","v":2},0,2,"2017-10-02","2017-11-21",{"$f":"NETWORKDAYS(N642,O642,MALegalHolidays)","v":37},10,27,null,null,null,null," ",null,null,null,null," ","2017-11-22","2018-02-09",{"$f":"NETWORKDAYS(AC642,AD642,MALegalHolidays)","v":58},0,58,"2018-02-12",null,{"$f":"NETWORKDAYS(AH642,AI642,MALegalHolidays)","v":-30765},null," ","2018-02-20",null,"Q4 2018",null,"STD",null,null,null,null,null," ",null,null,"2020-09-22","on line"]
[null,"WMECO","Shelburne Falls","6A2914-2017","01370",60,"Solar","22B5","2017-09-28","2017-10-17",{"$f":"NETWORKDAYS(I643,J643,MALegalHolidays)","v":14},11,3,"2017-10-18","2017-10-27",{"$f":"NETWORKDAYS(N643,O643,MALegalHolidays)","v":8},4,4,"2017-10-27","2017-12-06",{"$f":"NETWORKDAYS(S643,T643,MALegalHolidays)","v":29},3,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2017-12-14",null,"Nov 2017",null,"EXP",null,null,null,null,null," ","2018-05-15","2018-05-17","2018-05-17","on line"]
[null,"WMECO","Shelburne Falls","6A2915-2017","01370",50,"Solar","22B5","2017-09-28","2017-10-17",{"$f":"NETWORKDAYS(I644,J644,MALegalHolidays)","v":14},11,3,"2017-10-18",null,{"$f":"NETWORKDAYS(N644,O644,MALegalHolidays)","v":-30682},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2017",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Dalton","6B1618-2017","01226",9.2799999999999994,"Solar","19A2","2017-09-28",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2017-12-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Hinsdale","6B1620-2017","01235",3000,"Solar","18C2","2017-09-28","2017-10-04",{"$f":"NETWORKDAYS(I646,J646,MALegalHolidays)","v":5},2,3,"2017-10-05","2017-10-24",{"$f":"NETWORKDAYS(N646,O646,MALegalHolidays)","v":14},4,10,null,null,null,null," ",null,null,null,null," ","2017-10-25","2018-02-27",{"$f":"NETWORKDAYS(AC646,AD646,MALegalHolidays)","v":90},0,90,"2018-02-28",null,{"$f":"NETWORKDAYS(AH646,AI646,MALegalHolidays)","v":-30777},null," ","2018-02-27",null,"12.18",null,"STD",null,null,null,null,null," ",null,null,"2021-10-15","on line"]
[null,"WMECO","Otis","6B1625-2017","01253",24,"Solar","19J4","2017-09-29","2017-10-04",{"$f":"NETWORKDAYS(I647,J647,MALegalHolidays)","v":4},2,2,"2017-10-05","2018-09-24",{"$f":"NETWORKDAYS(N647,O647,MALegalHolidays)","v":253},null,253,"2018-09-25","2018-10-23",{"$f":"NETWORKDAYS(S647,T647,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-10-23",null,"Nov 22",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-10","on line"]
[null,"WMECO","Hinsdale","6B1626-2017","01235",2200,"Solar","18C2","2017-09-29","2017-10-05",{"$f":"NETWORKDAYS(I648,J648,MALegalHolidays)","v":5},3,2,"2017-10-06",null,{"$f":"NETWORKDAYS(N648,O648,MALegalHolidays)","v":-30674},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-31",null,"STD",null,null,null,null,null," ",null,null,null,"sent 10 day notice, negotiated 20 days, withdrawn after applicant did not execute Impact Study, withdrawn"]
[null,"WMECO","West Springfield","6S3822-2017","01089",46.8,"Solar","16C15","2017-10-02","2017-11-10",{"$f":"NETWORKDAYS(I649,J649,MALegalHolidays)","v":30},26,4,"2017-11-13","2018-01-26",{"$f":"NETWORKDAYS(N649,O649,MALegalHolidays)","v":55},40,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-01-26",null,"2017-11-01",null,"EXP",null,null,null,null,null," ","2018-04-02","2018-04-10","2018-04-13","on line"]
[null,"WMECO","Russell","6A2932-2017","01071",2988,"Solar","19J2","2017-10-04","2017-10-17",{"$f":"NETWORKDAYS(I650,J650,MALegalHolidays)","v":10},8,2,"2017-10-18","2017-11-27",{"$f":"NETWORKDAYS(N650,O650,MALegalHolidays)","v":29},3,26,null,null,null,null," ",null,null,null,null," ","2017-11-28","2018-05-24",{"$f":"NETWORKDAYS(AC650,AD650,MALegalHolidays)","v":128},60,68,"2018-06-06",null,{"$f":"NETWORKDAYS(AH650,AI650,MALegalHolidays)","v":-30847},null," ","2018-06-01",null,"2019",null,"COMP",null,null,null,null,null," ",null,null,"2020-10-26","on line"]
[null,"WMECO","Tolland","6B1628-2017","01034",4980,"Solar","19J4","2017-10-04","2017-10-17",{"$f":"NETWORKDAYS(I651,J651,MALegalHolidays)","v":10},7,3,"2017-10-18","2017-12-11",{"$f":"NETWORKDAYS(N651,O651,MALegalHolidays)","v":39},16,23,null,null,null,null," ",null,null,null,null," ","2017-12-12","2018-02-20",{"$f":"NETWORKDAYS(AC651,AD651,MALegalHolidays)","v":51},0,51,"2018-03-01",null,{"$f":"NETWORKDAYS(AH651,AI651,MALegalHolidays)","v":-30778},null," ","2018-02-27",null,"2019",null,"COMP",null,null,null,null,null," ",null,null,"2020-12-28","on line"]
[null,"WMECO","Pittsfield","6B1632-2017","01201",4987,"Solar","15E2","2017-10-06","2017-10-17",{"$f":"NETWORKDAYS(I652,J652,MALegalHolidays)","v":8},4,4,"2017-10-18",null,{"$f":"NETWORKDAYS(N652,O652,MALegalHolidays)","v":-30682},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Summer 2018",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Montague","6A2951-2017","01349",800,"Solar","21C2","2017-10-11","2017-12-15",{"$f":"NETWORKDAYS(I653,J653,MALegalHolidays)","v":48},45,3,"2017-12-18","2018-02-21",{"$f":"NETWORKDAYS(N653,O653,MALegalHolidays)","v":48},28,20,null,null,null,null," ",null,null,null,null," ","2018-02-22","2018-05-08",{"$f":"NETWORKDAYS(AC653,AD653,MALegalHolidays)","v":54},22,32,"2018-05-09",null,{"$f":"NETWORKDAYS(AH653,AI653,MALegalHolidays)","v":-30827},null," ","2018-07-19",null,"6/31/2018",null,"STD",null,null,null,null,null," ",null,null,"2020-12-31","on line"]
[null,"WMECO","Windsor","6B1641-2017","01270",999,"Solar","18C1","2017-10-12","2017-11-16",{"$f":"NETWORKDAYS(I654,J654,MALegalHolidays)","v":26},19,7,"2017-11-17","2017-12-27",{"$f":"NETWORKDAYS(N654,O654,MALegalHolidays)","v":29},24,5,null,null,null,null," ",null,null,null,null," ","2017-12-28","2018-04-27",{"$f":"NETWORKDAYS(AC654,AD654,MALegalHolidays)","v":87},42,45,null,null,null,null," ","2018-10-26",null,"Fall 2018",null,"STD",null,null,null,null,null," ",null,null,"2020-12-29","on line"]
[null,"WMECO","Springfield","6S3848-2017","01119",600,"Diesel","20A14","2017-10-12","2017-11-06",{"$f":"NETWORKDAYS(I655,J655,MALegalHolidays)","v":18},13,5,"2017-11-07","2018-01-23",{"$f":"NETWORKDAYS(N655,O655,MALegalHolidays)","v":56},35,21,"2018-01-24","2018-04-02",{"$f":"NETWORKDAYS(S655,T655,MALegalHolidays)","v":49},41,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-18",null,"2017-12-15",null,"EXP",null,null,null,null,null," ","2018-04-25","2018-06-07","2018-06-07","on line"]
[null,"WMECO","Springfield","6S3870-2017","01103",1140,"Solar","8C31","2017-10-18","2017-11-06",{"$f":"NETWORKDAYS(I656,J656,MALegalHolidays)","v":14},12,2,"2017-11-07","2018-04-20",{"$f":"NETWORKDAYS(N656,O656,MALegalHolidays)","v":119},71,48,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-26",null,"2018-11-30",null,"EXP",null,null,null,null,null," ",null,null,"2020-07-22","behind two other apps"]
[null,"WMECO","Turners Falls","6A2995-2017","01349",996,"Solar","21C2","2017-10-30","2017-11-16",{"$f":"NETWORKDAYS(I657,J657,MALegalHolidays)","v":14},8,6,"2017-11-17","2018-01-08",{"$f":"NETWORKDAYS(N657,O657,MALegalHolidays)","v":37},26,11,null,null,null,null," ",null,null,null,null," ","2018-01-05","2018-06-11",{"$f":"NETWORKDAYS(AC657,AD657,MALegalHolidays)","v":112},94,18,null,null,null,null," ","2018-09-20",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2019-12-24","on line"]
[null,"WMECO","Westhampton","6A3031-2017","01027",4980,"Solar","15A3","2017-11-13","2017-12-15",{"$f":"NETWORKDAYS(I658,J658,MALegalHolidays)","v":25},22,3,"2017-12-18","2018-01-08",{"$f":"NETWORKDAYS(N658,O658,MALegalHolidays)","v":16},2,14,null,null,null,null," ",null,null,null,null," ","2018-01-09","2018-04-02",{"$f":"NETWORKDAYS(AC658,AD658,MALegalHolidays)","v":60},11,49,"2018-04-05",null,{"$f":"NETWORKDAYS(AH658,AI658,MALegalHolidays)","v":-30803},null," ","2018-04-13",null,"2019",null,"COMP",null,null,null,null,null," ",null,null,"2022-01-26","on line"]
[null,"WMECO","Agawam","6S3940-2017","01001",366.3,"Solar","16C16","2017-11-20","2017-12-15",{"$f":"NETWORKDAYS(I659,J659,MALegalHolidays)","v":20},17,3,"2017-12-18","2018-02-28",{"$f":"NETWORKDAYS(N659,O659,MALegalHolidays)","v":53},44,9,"2018-03-01","2018-03-14",{"$f":"NETWORKDAYS(S659,T659,MALegalHolidays)","v":10},8,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-03-29",null,"Not supplied",null,"EXP",null,null,null,null,null," ","2018-10-03","2018-10-03","2018-10-05","on line"]
[null,"WMECO","Lanesborough","6B1701-2017","01237",4536,"Solar","15E2","2017-11-21","2017-12-22",{"$f":"NETWORKDAYS(I660,J660,MALegalHolidays)","v":24},16,8,"2017-12-22","2018-03-12",{"$f":"NETWORKDAYS(N660,O660,MALegalHolidays)","v":57},36,21,null,null,null,null," ",null,null,null,null," ","2018-03-13","2018-06-15",{"$f":"NETWORKDAYS(AC660,AD660,MALegalHolidays)","v":69},4,65,"2018-07-26",null,{"$f":"NETWORKDAYS(AH660,AI660,MALegalHolidays)","v":-30883},null," ","2018-06-28",null,"asap",null,"COMP",null,null,null,null,null," ",null,null,"2022-12-09","on line"]
[null,"WMECO","Lanesborough","6B1702-2017","01237",3600,"Solar","15E1","2017-11-21","2017-12-22",{"$f":"NETWORKDAYS(I661,J661,MALegalHolidays)","v":24},16,8,"2017-12-22","2018-03-12",{"$f":"NETWORKDAYS(N661,O661,MALegalHolidays)","v":57},51,6,null,null,null,null," ",null,null,null,null," ","2018-03-13","2018-06-15",{"$f":"NETWORKDAYS(AC661,AD661,MALegalHolidays)","v":69},4,65,"2018-07-18",null,{"$f":"NETWORKDAYS(AH661,AI661,MALegalHolidays)","v":-30877},null," ","2018-06-28",null,"asap",null,"STD",null,null,null,null,null," ",null,null,"2022-12-09","on line"]
[null,"WMECO","Hadley","6A3069-2017","01035",2990,"Solar","18G5","2017-11-27","2017-12-18",{"$f":"NETWORKDAYS(I662,J662,MALegalHolidays)","v":16},13,3,"2017-12-19",null,{"$f":"NETWORKDAYS(N662,O662,MALegalHolidays)","v":-30726},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Hadley","6A3073-2017","01035",2000,"Solar","18G5","2017-11-27","2017-12-18",{"$f":"NETWORKDAYS(I663,J663,MALegalHolidays)","v":16},13,3,"2017-12-19",null,{"$f":"NETWORKDAYS(N663,O663,MALegalHolidays)","v":-30726},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Windsor","6B1708-2017","01027",2573,"Solar","18C1","2017-11-27","2017-12-15",{"$f":"NETWORKDAYS(I664,J664,MALegalHolidays)","v":15},13,2,"2017-12-15",null,{"$f":"NETWORKDAYS(N664,O664,MALegalHolidays)","v":-30724},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019",null,"EXP",null,null,null,null,null," ",null,null,null,"on hold behind another application, cancelled by applicant"]
[null,"WMECO","Montague","6A3081-2017","01376",3770,"Solar","21C2","2017-11-29","2018-02-28",{"$f":"NETWORKDAYS(I665,J665,MALegalHolidays)","v":66},37,29,"2018-03-01","2018-06-11",{"$f":"NETWORKDAYS(N665,O665,MALegalHolidays)","v":73},63,10,null,null,null,null," ",null,null,null,null," ","2018-06-12","2018-10-31",{"$f":"NETWORKDAYS(AC665,AD665,MALegalHolidays)","v":102},null,102,null,null,null,null," ","2018-10-29",null,"August 2018",null,"STD",null,null,null,null,null," ",null,null,"2021-11-23","on line"]
[null,"WMECO","Worthington","6A3090-2017","01098",8300,"Solar","18K3","2017-12-01","2017-12-18",{"$f":"NETWORKDAYS(I666,J666,MALegalHolidays)","v":12},9,3,"2017-12-19",null,{"$f":"NETWORKDAYS(N666,O666,MALegalHolidays)","v":-30726},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Greenfield","6A3094-2017","01301",1000,"Solar","22B7","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I667,J667,MALegalHolidays)","v":14},11,3,"2017-12-22","2018-05-03",{"$f":"NETWORKDAYS(N667,O667,MALegalHolidays)","v":95},70,25,null,null,null,null," ",null,null,null,null," ","2018-05-04","2018-09-17",{"$f":"NETWORKDAYS(AC667,AD667,MALegalHolidays)","v":97},null,97,null,null,null,null," ","2018-11-20",null,"2018-03-01",null,"COMP",null,null,null,null,null," ",null,null,null,"sent 10 day notice for missed deadline for executing Impact Study Agreement, 2 options, negotiated 20 days"]
[null,"WMECO","Chesterfield","6A3095-2017","01012",500,"Solar","18K3","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I668,J668,MALegalHolidays)","v":14},11,3,"2017-12-22",null,{"$f":"NETWORKDAYS(N668,O668,MALegalHolidays)","v":-30729},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Greenfield","6A3096-2017","01301",500,"Solar","22B7","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I669,J669,MALegalHolidays)","v":14},11,3,"2017-12-22",null,{"$f":"NETWORKDAYS(N669,O669,MALegalHolidays)","v":-30729},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Northfield","6A3097-2017","01360",1000,"Solar","21B8","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I670,J670,MALegalHolidays)","v":14},11,3,"2017-12-22","2018-05-03",{"$f":"NETWORKDAYS(N670,O670,MALegalHolidays)","v":95},65,30,null,null,null,null," ",null,null,null,null," ","2018-05-04","2018-10-19",{"$f":"NETWORKDAYS(AC670,AD670,MALegalHolidays)","v":121},null,121,null,null,null,null," ","2018-11-20",null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Northfield","6A3098-2017","01360",500,"Solar","21B8","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I671,J671,MALegalHolidays)","v":14},11,3,"2017-12-22",null,{"$f":"NETWORKDAYS(N671,O671,MALegalHolidays)","v":-30729},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Northfield","6A3099-2017","01360",500,"Solar","21B8","2017-12-04","2017-12-21",{"$f":"NETWORKDAYS(I672,J672,MALegalHolidays)","v":14},11,3,"2017-12-22",null,{"$f":"NETWORKDAYS(N672,O672,MALegalHolidays)","v":-30729},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1724-2017","01201",1380,"Solar","30B5","2017-12-05","2018-01-16",{"$f":"NETWORKDAYS(I673,J673,MALegalHolidays)","v":31},23,8,"2018-01-17","2018-02-28",{"$f":"NETWORKDAYS(N673,O673,MALegalHolidays)","v":31},24,7,null,null,null,null," ",null,null,null,null," ","2018-03-01","2018-07-16",{"$f":"NETWORKDAYS(AC673,AD673,MALegalHolidays)","v":98},40,58,"2018-07-17",null,{"$f":"NETWORKDAYS(AH673,AI673,MALegalHolidays)","v":-30876},null," ","2018-07-16",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2020-12-30","on line"]
[null,"WMECO","Ludlow","6S3969-2017","01056",3969,"Solar","27A5","2017-12-05","2018-02-08",{"$f":"NETWORKDAYS(I674,J674,MALegalHolidays)","v":48},30,18,"2018-02-09","2018-04-27",{"$f":"NETWORKDAYS(N674,O674,MALegalHolidays)","v":56},29,27,null,null,null,null," ",null,null,null,null," ","2018-04-30","2018-10-15",{"$f":"NETWORKDAYS(AC674,AD674,MALegalHolidays)","v":121},null,121,null,null,null,null," ","2018-10-27",null,"2018",null,"COMP",null,null,null,null,null," ",null,null,"2021-01-29","on line"]
[null,"WMECO","Lanesborough","6B1728-2017","01237",3000,"Solar","15E1","2017-12-07",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Greenfield","6A3130-2017","01301",4500,"Solar","21C1","2017-12-14","2017-12-27",{"$f":"NETWORKDAYS(I676,J676,MALegalHolidays)","v":10},2,8,"2017-12-28","2018-02-14",{"$f":"NETWORKDAYS(N676,O676,MALegalHolidays)","v":35},7,28,null,null,null,null," ",null,null,null,null," ","2018-02-15","2018-07-25",{"$f":"NETWORKDAYS(AC676,AD676,MALegalHolidays)","v":115},42,73,"2018-07-26",null,{"$f":"NETWORKDAYS(AH676,AI676,MALegalHolidays)","v":-30883},null," ","2020-03-23",null,"2018-12-21",null,"STD",null,null,null,null,null," ",null,null,"2024-07-23","in construction phase"]
[null,"WMECO","Lanesborough","6B1736-2017","01237",4536,"Solar","15E1","2017-12-14","2017-12-22",{"$f":"NETWORKDAYS(I677,J677,MALegalHolidays)","v":7},0,7,"2017-12-22","2018-05-31",{"$f":"NETWORKDAYS(N677,O677,MALegalHolidays)","v":115},106,9,null,null,null,null," ",null,null,null,null," ","2018-06-01","2018-08-27",{"$f":"NETWORKDAYS(AC677,AD677,MALegalHolidays)","v":62},null,62,null,null,null,null," ","2018-09-25",null,"ASAP",null,"STD",null,null,null,null,null," ",null,null,"2022-12-09","on line"]
[null,"WMECO","Lanesborough","6B1737-2017","01237",3000,"Solar","15E1","2017-12-14","2017-12-15",{"$f":"NETWORKDAYS(I678,J678,MALegalHolidays)","v":2},0,2,"2017-12-18","2018-01-16",{"$f":"NETWORKDAYS(N678,O678,MALegalHolidays)","v":22},11,11,null,null,null,null," ",null,null,null,null," ","2018-09-20","2018-10-16",{"$f":"NETWORKDAYS(AC678,AD678,MALegalHolidays)","v":19},null,19,null,null,null,null," ","2019-05-21",null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Easthampton","6A3136-2017","01027",4998,"Solar","15A3","2017-12-15","2018-01-02",{"$f":"NETWORKDAYS(I679,J679,MALegalHolidays)","v":13},5,8,"2018-01-03","2018-06-05",{"$f":"NETWORKDAYS(N679,O679,MALegalHolidays)","v":110},97,13,null,null,null,null," ",null,null,null,null," ","2018-06-06","2018-10-22",{"$f":"NETWORKDAYS(AC679,AD679,MALegalHolidays)","v":99},null,99,null,null,null,null," ","2018-10-18",null,"2019-01-14",null,"COMP",null,null,null,null,null," ",null,null,"2022-11-30","on line"]
[null,"WMECO","Pittsfield","6B1741-2017","01201",5000,"Solar","30B2","2017-12-18","2017-12-27",{"$f":"NETWORKDAYS(I680,J680,MALegalHolidays)","v":8},1,7,"2017-12-28","2018-02-28",{"$f":"NETWORKDAYS(N680,O680,MALegalHolidays)","v":45},12,33,null,null,null,null," ",null,null,null,null," ","2018-03-01","2018-09-24",{"$f":"NETWORKDAYS(AC680,AD680,MALegalHolidays)","v":148},null,148,null,null,null,null," ","2018-10-05",null,"2019-01-14",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","West Springfield","6S4000-2017","01089",180,"Solar","16C12","2017-12-18","2018-02-02",{"$f":"NETWORKDAYS(I681,J681,MALegalHolidays)","v":35},6,29,"2018-02-05","2018-03-12",{"$f":"NETWORKDAYS(N681,O681,MALegalHolidays)","v":26},7,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-03-15",null,"2018-03-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Conway","6A3138-2017","01341",2178,"Solar","22B1","2017-12-19","2018-01-10",{"$f":"NETWORKDAYS(I682,J682,MALegalHolidays)","v":17},13,4,"2018-01-11",null,{"$f":"NETWORKDAYS(N682,O682,MALegalHolidays)","v":-30743},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Dec 2018",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4010-2017","01118",99.9,"Solar","20A32","2017-12-20","2018-01-10",{"$f":"NETWORKDAYS(I683,J683,MALegalHolidays)","v":16},9,7,"2018-01-11","2018-02-09",{"$f":"NETWORKDAYS(N683,O683,MALegalHolidays)","v":22},2,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-02-09",null,"2018-05-01",null,"EXP",null,null,null,null,null," ",null,null,"2019-10-03","on line"]
[null,"WMECO","Southwick","6S4042-2018","01077",9950,"Solar","29A1","2018-01-03","2018-02-08",{"$f":"NETWORKDAYS(I684,J684,MALegalHolidays)","v":27},21,6,"2018-02-09",null,{"$f":"NETWORKDAYS(N684,O684,MALegalHolidays)","v":-30764},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-10",null,"STD",null,null,null,null,null," ",null,null,null,"multiple options, negotiated 15 days"]
[null,"WMECO","Hatfield","6A3180-2018","01038",500,"Solar","18G5","2018-01-08","2018-01-31",{"$f":"NETWORKDAYS(I685,J685,MALegalHolidays)","v":18},1,17,"2018-02-01",null,{"$f":"NETWORKDAYS(N685,O685,MALegalHolidays)","v":-30758},11," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-04-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Becket","6B1756-2018","01223",33.299999999999997,"Solar","19J6","2018-01-12","2018-01-22",{"$f":"NETWORKDAYS(I686,J686,MALegalHolidays)","v":7},4,3,"2018-01-23","2018-02-28",{"$f":"NETWORKDAYS(N686,O686,MALegalHolidays)","v":27},0,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-02-02",null,"2018-05-01",null,"EXP",null,null,null,null,null," ","2018-07-11","2018-07-17","2018-07-18","on line"]
[null,"WMECO","Deerfield","6A3216-2018","01373",500,"Solar","22B3","2018-01-16","2018-01-31",{"$f":"NETWORKDAYS(I687,J687,MALegalHolidays)","v":12},5,7,"2018-02-01","2018-03-13",{"$f":"NETWORKDAYS(N687,O687,MALegalHolidays)","v":29},22,7,null,null,null,null," ",null,null,null,null," ","2018-03-14","2018-04-30",{"$f":"NETWORKDAYS(AC687,AD687,MALegalHolidays)","v":34},2,32,null,null,null,null," ",null,null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Blandford","6B1761-2018","01008",4450,"Solar","19J6","2018-01-17","2018-01-29",{"$f":"NETWORKDAYS(I688,J688,MALegalHolidays)","v":9},1,8,"2018-01-30",null,{"$f":"NETWORKDAYS(N688,O688,MALegalHolidays)","v":-30756},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Erving ","6A3219-2018","01344",4980,"Solar","21C8","2018-01-18","2018-01-31",{"$f":"NETWORKDAYS(I689,J689,MALegalHolidays)","v":10},1,9,"2018-02-01","2018-05-03",{"$f":"NETWORKDAYS(N689,O689,MALegalHolidays)","v":66},43,23,null,null,null,null," ",null,null,null,null," ","2018-05-04","2018-08-03",{"$f":"NETWORKDAYS(AC689,AD689,MALegalHolidays)","v":66},8,58,null,null,null,null," ","2018-08-10",null,"Summer 2018",null,"COMP",null,null,null,null,null," ",null,null,"2022-11-25","on line"]
[null,"WMECO","Deerfield","6A3221-2018","01373",1000,"Solar","22B3","2018-01-18","2018-01-30",{"$f":"NETWORKDAYS(I690,J690,MALegalHolidays)","v":9},3,6,"2018-01-31","2018-02-06",{"$f":"NETWORKDAYS(N690,O690,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Peru","6B1762-2018","01235",3320,"Solar","18C2","2018-01-18","2018-01-30",{"$f":"NETWORKDAYS(I691,J691,MALegalHolidays)","v":9},2,7,"2018-01-31","2018-03-09",{"$f":"NETWORKDAYS(N691,O691,MALegalHolidays)","v":28},21,7,null,null,null,null," ",null,null,null,null," ","2018-03-12","2018-05-11",{"$f":"NETWORKDAYS(AC691,AD691,MALegalHolidays)","v":45},0,45,"2018-05-16",null,{"$f":"NETWORKDAYS(AH691,AI691,MALegalHolidays)","v":-30832},null," ","2018-05-18",null,"Q4 2018",null,"STD",null,null,null,null,null," ",null,null,"2020-11-18","on line"]
[null,"WMECO","Northfield","6A3238-2018","01360",5000,"Solar","21B8","2018-01-30","2018-02-21",{"$f":"NETWORKDAYS(I692,J692,MALegalHolidays)","v":17},7,10,"2018-02-22","2018-10-26",{"$f":"NETWORKDAYS(N692,O692,MALegalHolidays)","v":177},165,12,null,null,null,null," ",null,null,null,null," ","2018-10-29",null,{"$f":"NETWORKDAYS(AC692,AD692,MALegalHolidays)","v":-30950},null," ",null,null,null,null," ","2018-11-30",null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Windsor","6B1777-2018","01270",20,"Solar","18C1","2018-01-31","2018-02-08",{"$f":"NETWORKDAYS(I693,J693,MALegalHolidays)","v":7},5,2,"2018-02-09","2018-04-17",{"$f":"NETWORKDAYS(N693,O693,MALegalHolidays)","v":48},24,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-17",null,"2018-03-15",null,"EXP",null,null,null,null,null," ","2018-06-12","2018-06-15","2018-06-18","on line"]
[null,"WMECO","Leverett","6A3271-2018","01054",3120,"Solar","18G7","2018-02-09","2018-02-21",{"$f":"NETWORKDAYS(I694,J694,MALegalHolidays)","v":9},6,3,"2018-02-22","2018-04-04",{"$f":"NETWORKDAYS(N694,O694,MALegalHolidays)","v":30},28,2,null,null,null,null," ",null,null,null,null," ","2018-04-05","2018-05-24",{"$f":"NETWORKDAYS(AC694,AD694,MALegalHolidays)","v":36},0,36,null,null,null,null," ","2018-06-28",null,"2018-12-01",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1787-2018","01201",2574,"Solar","30B2","2018-02-09","2018-03-05",{"$f":"NETWORKDAYS(I695,J695,MALegalHolidays)","v":17},4,13,"2018-03-06","2018-03-14",{"$f":"NETWORKDAYS(N695,O695,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ","2019-04-05","2019-11-22",{"$f":"NETWORKDAYS(AC695,AD695,MALegalHolidays)","v":166},null,166,null,null,null,null," ","2020-03-23",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A3277-2018","01360",3575,"Solar","21B8","2018-02-12","2018-03-09",{"$f":"NETWORKDAYS(I696,J696,MALegalHolidays)","v":20},12,8,"2018-03-12","2018-03-19",{"$f":"NETWORKDAYS(N696,O696,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Whately","6A3279-2018","01093",5225,"Solar","18G8","2018-02-12","2018-02-22",{"$f":"NETWORKDAYS(I697,J697,MALegalHolidays)","v":9},0,9,"2018-02-23","2018-05-10",{"$f":"NETWORKDAYS(N697,O697,MALegalHolidays)","v":55},46,9,null,null,null,null," ",null,null,null,null," ","2018-05-11","2018-10-11",{"$f":"NETWORKDAYS(AC697,AD697,MALegalHolidays)","v":110},null,110,null,null,null,null," ",null,null,"2018-08-30",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A3280-2018","01337",1410,"Solar","21C1","2018-02-12","2018-02-22",{"$f":"NETWORKDAYS(I698,J698,MALegalHolidays)","v":9},0,{"$f":"IF(K698>0,K698-L698,\" \")","v":9},"2018-02-23","2018-05-11",{"$f":"NETWORKDAYS(N698,O698,MALegalHolidays)","v":56},48,{"$f":"IF(P698>0,P698-Q698,\" \")","v":8},null,null,null,null,{"$f":"IF(U698>0,U698-V698,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z698>0,Z698-AA698,\" \")","v":" "},"2018-05-14","2018-11-14",{"$f":"NETWORKDAYS(AC698,AD698,MALegalHolidays)","v":133},null,{"$f":"IF(AE698>0,AE698-AF698,\" \")","v":133},null,null,null,null,{"$f":"IF(AJ698>0,AJ698-AK698,\" \")","v":" "},"2018-11-28",null,"2018-08-30",null,"STD",null,null,null,null,null,{"$f":"IF(AU698>0,AU698-AV698,\" \")","v":" "},null,null,"2022-10-31","completed"]
[null,"WMECO","Westhampton","6A3288-2018","01027",22.8,"Solar","15A3","2018-02-14","2018-02-22",{"$f":"NETWORKDAYS(I699,J699,MALegalHolidays)","v":7},4,3,"2018-02-23","2018-03-05",{"$f":"NETWORKDAYS(N699,O699,MALegalHolidays)","v":7},3,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-03-07",null,"2018-03-15",null,"EXP",null,null,null,null,null," ","2018-05-30","2018-06-13","2018-06-13","on line"]
[null,"WMECO","Whately","6A3295-2018","01093",1000,"Solar","18G8","2018-02-16","2018-02-22",{"$f":"NETWORKDAYS(I700,J700,MALegalHolidays)","v":5},3,2,"2018-02-23","2018-07-31",{"$f":"NETWORKDAYS(N700,O700,MALegalHolidays)","v":113},105,8,null,null,null,null," ",null,null,null,null," ","2018-08-01","2018-11-18",{"$f":"NETWORKDAYS(AC700,AD700,MALegalHolidays)","v":78},null,78,null,null,null,null," ",null,null,"2018-12-31",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Blandford","6B1793-2018","01008",4998,"Solar","19J4","2018-02-16","2018-02-22",{"$f":"NETWORKDAYS(I701,J701,MALegalHolidays)","v":5},2,3,"2018-02-23","2018-03-08",{"$f":"NETWORKDAYS(N701,O701,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn after missed deadlines, applicant does not want to proceed"]
[null,"WMECO","West Springfield","6S4145-2018","01089",19.3,"Solar","16C14","2018-02-16","2018-02-22",{"$f":"NETWORKDAYS(I702,J702,MALegalHolidays)","v":5},2,3,"2018-02-23","2018-03-06",{"$f":"NETWORKDAYS(N702,O702,MALegalHolidays)","v":8},4,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-03-07",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S4152-2018","01056",4998,"Solar","19S3","2018-02-16","2018-02-22",{"$f":"NETWORKDAYS(I703,J703,MALegalHolidays)","v":5},2,3,"2018-02-23","2018-06-20",{"$f":"NETWORKDAYS(N703,O703,MALegalHolidays)","v":84},67,17,null,null,null,null," ",null,null,null,null," ","2018-06-21","2018-10-02",{"$f":"NETWORKDAYS(AC703,AD703,MALegalHolidays)","v":74},null,74,null,null,null,null," ","2018-11-12",null,"2019-10-01",null,"COMP",null,null,null,null,null," ",null,null,"2022-12-16","on line"]
[null,"WMECO","Ludlow","6S4153-2018","01056",5000,"Solar","19S3","2018-02-16","2018-02-22",{"$f":"NETWORKDAYS(I704,J704,MALegalHolidays)","v":5},2,3,"2018-02-23",null,{"$f":"NETWORKDAYS(N704,O704,MALegalHolidays)","v":-30774},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Whately","6A3297-2018","01373",1925,"Solar","18G8","2018-02-20","2018-03-09",{"$f":"NETWORKDAYS(I705,J705,MALegalHolidays)","v":14},9,5,"2018-03-12","2018-03-15",{"$f":"NETWORKDAYS(N705,O705,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Cheshire","6B1794-2018","01225",1650,"Solar","19A5","2018-02-20","2018-03-05",{"$f":"NETWORKDAYS(I706,J706,MALegalHolidays)","v":10},7,3,"2018-03-06",null,{"$f":"NETWORKDAYS(N706,O706,MALegalHolidays)","v":-30781},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-30",null,"STD",null,null,null,null,null," ",null,null,null,"2 options, negotiated 10 days, cancelled by applicant"]
[null,"WMECO","Hinsdale","6B1795-2018","01235",2200,"Solar","18C2","2018-02-22","2018-03-14",{"$f":"NETWORKDAYS(I707,J707,MALegalHolidays)","v":15},11,4,"2018-03-15",null,{"$f":"NETWORKDAYS(N707,O707,MALegalHolidays)","v":-30788},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-31",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn after missed deadlines, applicant does not want to proceed"]
[null,"WMECO","Bernardston","6A3302-2018","01337",4160,"Solar","21C1","2018-02-23","2018-03-14",{"$f":"NETWORKDAYS(I708,J708,MALegalHolidays)","v":14},10,4,"2018-03-15","2018-03-16",{"$f":"NETWORKDAYS(N708,O708,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-03-01",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B1798-2018","01201",3250,"Solar","30B5","2018-02-26","2018-03-28",{"$f":"NETWORKDAYS(I709,J709,MALegalHolidays)","v":23},19,4,"2018-03-29","2018-05-14",{"$f":"NETWORKDAYS(N709,O709,MALegalHolidays)","v":33},17,16,null,null,null,null," ",null,null,null,null," ","2018-05-15","2018-10-23",{"$f":"NETWORKDAYS(AC709,AD709,MALegalHolidays)","v":116},37,79,null,null,null,null," ","2018-11-23",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southwick","6S4177-2018","01077",248,"Solar","29A1","2018-02-28","2018-03-29",{"$f":"NETWORKDAYS(I710,J710,MALegalHolidays)","v":22},19,3,"2018-04-02","2018-04-23",{"$f":"NETWORKDAYS(N710,O710,MALegalHolidays)","v":16},4,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-23",null,"5/2018",null,"EXP",null,null,null,null,null," ","2018-10-02","2018-10-02","2018-10-02","on line"]
[null,"WMECO","Amherst","6A3310-2018","01002",32.950000000000003,"Solar","17K3","2018-03-01",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"March 2018",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Amherst","6A3312-2018","01002",99.9,"Solar","17K4, (17K5 N.O.)","2018-03-02","2018-03-14",{"$f":"NETWORKDAYS(I712,J712,MALegalHolidays)","v":9},8,1,"2018-03-15","2018-08-06",{"$f":"NETWORKDAYS(N712,O712,MALegalHolidays)","v":103},48,55,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-08-06",null,"2018-06-01",null,"EXP",null,null,null,null,null," ",null,null,"2019-01-10","on line"]
[null,"WMECO","Shelburne Falls","6A3316-2018","01370",900,"Solar","22B5","2018-03-05","2018-06-20",{"$f":"NETWORKDAYS(I713,J713,MALegalHolidays)","v":78},72,6,"2018-06-21","2018-06-21",{"$f":"NETWORKDAYS(N713,O713,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ","2018-10-09","2019-03-13",{"$f":"NETWORKDAYS(AC713,AD713,MALegalHolidays)","v":112},null,112,null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Huntington","6A3317-2018","01050",900,"Solar","19J5","2018-03-05","2018-06-20",{"$f":"NETWORKDAYS(I714,J714,MALegalHolidays)","v":78},72,6,"2018-06-21","2018-06-26",{"$f":"NETWORKDAYS(N714,O714,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Westhampton","6A3322-2018","01027",2500,"Solar","15A3","2018-03-06","2018-04-18",{"$f":"NETWORKDAYS(I715,J715,MALegalHolidays)","v":32},23,9,"2018-04-19","2018-10-19",{"$f":"NETWORKDAYS(N715,O715,MALegalHolidays)","v":132},126,6,null,null,null,null," ",null,null,null,null," ","2018-10-19","2018-12-18",{"$f":"NETWORKDAYS(AC715,AD715,MALegalHolidays)","v":43},null,43,null,null,null,null," ","2019-01-27",null,"2019-04-30",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4201-2018","01118",15.68,"Solar","20A32","2018-03-13",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-04-05",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Russell","6A3340-2018","01070",495,"Solar","19J5","2018-03-14","2018-06-13",{"$f":"NETWORKDAYS(I717,J717,MALegalHolidays)","v":66},55,11,"2018-06-14","2018-06-22",{"$f":"NETWORKDAYS(N717,O717,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-04-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","South Deerfield","6A3341-2018","01373",2000,"Solar","18G8","2018-03-15","2018-03-28",{"$f":"NETWORKDAYS(I718,J718,MALegalHolidays)","v":10},4,6,"2018-03-29",null,{"$f":"NETWORKDAYS(N718,O718,MALegalHolidays)","v":-30798},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Conway","6A3350-2018","01341",4400,"Solar","38A1","2018-03-16","2018-04-18",{"$f":"NETWORKDAYS(I719,J719,MALegalHolidays)","v":24},17,7,"2018-04-19","2018-05-11",{"$f":"NETWORKDAYS(N719,O719,MALegalHolidays)","v":17},11,6,null,null,null,null," ",null,null,null,null," ","2018-05-14","2018-09-25",{"$f":"NETWORKDAYS(AC719,AD719,MALegalHolidays)","v":97},null,97,null,null,null,null," ","2019-02-22",null,"2018-12-01",null,"COMP",null,null,null,null,null," ",null,null,"2021-07-28","on line"]
[null,"WMECO","Pittsfield","6B1811-2018","01201",4890,"Solar","30B5","2018-03-16","2018-04-06",{"$f":"NETWORKDAYS(I720,J720,MALegalHolidays)","v":16},9,7,"2018-04-09","2018-08-03",{"$f":"NETWORKDAYS(N720,O720,MALegalHolidays)","v":85},17,68,null,null,null,null," ",null,null,null,null," ","2018-08-06","2018-11-16",{"$f":"NETWORKDAYS(AC720,AD720,MALegalHolidays)","v":75},null,75,null,null,null,null," ",null,null,"2018-12-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1817-2018","01201",187,"Solar","30B5","2018-03-21","2018-04-03",{"$f":"NETWORKDAYS(I721,J721,MALegalHolidays)","v":10},3,7,"2018-04-04","2018-04-27",{"$f":"NETWORKDAYS(N721,O721,MALegalHolidays)","v":18},15,3,"2018-04-30","2018-07-20",{"$f":"NETWORKDAYS(S721,T721,MALegalHolidays)","v":60},22,38,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-09-17",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2019-07-30","on line"]
[null,"WMECO","Pittsfield","6B1818-2018","01201",191,"Solar","30B4","2018-03-21","2018-04-03",{"$f":"NETWORKDAYS(I722,J722,MALegalHolidays)","v":10},3,7,"2018-04-04","2018-04-13",{"$f":"NETWORKDAYS(N722,O722,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1819-2018","01201",249,"Solar","30B7","2018-03-21","2018-04-04",{"$f":"NETWORKDAYS(I723,J723,MALegalHolidays)","v":11},5,6,"2018-04-05","2018-05-24",{"$f":"NETWORKDAYS(N723,O723,MALegalHolidays)","v":36},22,14,"2018-05-25","2018-09-17",{"$f":"NETWORKDAYS(S723,T723,MALegalHolidays)","v":82},null,82,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-10-18",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2020-04-14","on line"]
[null,"WMECO","Dalton","6B1825-2018","01226",4400,"Solar","18C1","2018-03-21","2018-04-19",{"$f":"NETWORKDAYS(I724,J724,MALegalHolidays)","v":22},18,4,"2018-04-20","2018-08-03",{"$f":"NETWORKDAYS(N724,O724,MALegalHolidays)","v":76},48,28,null,null,null,null," ",null,null,null,null," ","2018-08-06","2018-11-29",{"$f":"NETWORKDAYS(AC724,AD724,MALegalHolidays)","v":84},null,84,null,null,null,null," ","2018-11-30",null,"2018-12-01",null,"STD",null,null,null,null,null," ",null,null,"2021-05-25","on line"]
[null,"WMECO","Springfield","6S4229-2018","01119",14.4,"Solar","20A35","2018-03-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-04-16",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Pittsfield","6B1824-2018","01201",480,"Solar","30B5","2018-03-22","2018-04-03",{"$f":"NETWORKDAYS(I726,J726,MALegalHolidays)","v":9},2,7,"2018-04-04","2021-04-23",{"$f":"NETWORKDAYS(N726,O726,MALegalHolidays)","v":798},null,798,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Richmond","6B1826-2018","01254",97.75,"Solar","30B7","2018-03-22","2018-03-29",{"$f":"NETWORKDAYS(I727,J727,MALegalHolidays)","v":6},1,5,"2018-04-02","2018-04-20",{"$f":"NETWORKDAYS(N727,O727,MALegalHolidays)","v":15},6,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-04-20",null,"6/2018",null,"EXP",null,null,null,null,null," ",null,null,"2019-08-28","on line"]
[null,"WMECO","Pittsfield","6B1831-2018","01201",350,"Solar","19A5","2018-03-26","2018-07-03",{"$f":"NETWORKDAYS(I728,J728,MALegalHolidays)","v":72},60,12,"2018-07-05","2019-07-01",{"$f":"NETWORKDAYS(N728,O728,MALegalHolidays)","v":258},null,258,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Granville","6S4247-2018","01034",4455,"Solar","29A5","2018-03-27","2018-04-11",{"$f":"NETWORKDAYS(I729,J729,MALegalHolidays)","v":12},4,8,"2018-04-12","2018-06-11",{"$f":"NETWORKDAYS(N729,O729,MALegalHolidays)","v":43},32,11,null,null,null,null," ",null,null,null,null," ","2018-06-12","2018-10-29",{"$f":"NETWORKDAYS(AC729,AD729,MALegalHolidays)","v":100},null,100,null,null,null,null," ","2018-11-06",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,"2022-05-31","on line"]
[null,"WMECO","Granville","6S4248-2018","01034",996,"Solar","29A5","2018-03-27","2018-04-11",{"$f":"NETWORKDAYS(I730,J730,MALegalHolidays)","v":12},4,8,"2018-04-12","2018-10-29",{"$f":"NETWORKDAYS(N730,O730,MALegalHolidays)","v":143},null,143,null,null,null,null," ",null,null,null,null," ","2018-10-29","2019-02-14",{"$f":"NETWORKDAYS(AC730,AD730,MALegalHolidays)","v":79},null,79,null,null,null,null," ","2019-04-19",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pelham","6A3370-2018","01543",4890,"Solar","17K2","2018-03-28","2019-02-05",{"$f":"NETWORKDAYS(I731,J731,MALegalHolidays)","v":225},null,225,"2019-02-05","2019-03-22",{"$f":"NETWORKDAYS(N731,O731,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ","2019-10-16","2020-01-07",{"$f":"NETWORKDAYS(AC731,AD731,MALegalHolidays)","v":60},null,60,null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Plainfield","6A3396-2018","01070",4998,"Solar","18K3","2018-04-06","2018-07-05",{"$f":"NETWORKDAYS(I732,J732,MALegalHolidays)","v":65},60,5,"2018-07-06","2018-07-30",{"$f":"NETWORKDAYS(N732,O732,MALegalHolidays)","v":17},null,17,null,null,null,null," ",null,null,null,null," ","2019-01-18","2019-04-25",{"$f":"NETWORKDAYS(AC732,AD732,MALegalHolidays)","v":70},null,70,null,null,null,null," ",null,null,"2019-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hinsdale","6B1847-2018","01235",4998,"Solar","18C2","2018-04-09","2018-05-07",{"$f":"NETWORKDAYS(I733,J733,MALegalHolidays)","v":21},15,6,"2018-05-08",null,{"$f":"NETWORKDAYS(N733,O733,MALegalHolidays)","v":-30826},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-10-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4298-2018","01104",500,"Solar","21S6","2018-04-09","2018-05-02",{"$f":"NETWORKDAYS(I734,J734,MALegalHolidays)","v":18},14,4,"2018-05-03","2018-05-15",{"$f":"NETWORKDAYS(N734,O734,MALegalHolidays)","v":9},7,2,"2018-05-17","2018-06-07",{"$f":"NETWORKDAYS(S734,T734,MALegalHolidays)","v":16},null,16,null,null,null,null," ","2018-05-16",null,{"$f":"NETWORKDAYS(AC734,AD734,MALegalHolidays)","v":-30832},null," ",null,null,null,null," ","2018-11-26",null,"2018-06-15",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S4299-2018","01001",576.6,"Solar","16C16","2018-04-09","2018-05-02",{"$f":"NETWORKDAYS(I735,J735,MALegalHolidays)","v":18},14,4,"2018-05-03","2018-05-15",{"$f":"NETWORKDAYS(N735,O735,MALegalHolidays)","v":9},7,2,null,null,null,null," ",null,null,null,null," ","2018-05-16","2018-09-29",{"$f":"NETWORKDAYS(AC735,AD735,MALegalHolidays)","v":98},null,98,null,null,null,null," ",null,null,"2018-06-15",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Otis","6B1854-2018","01253",1375,"Solar","19J4","2018-04-16","2018-05-07",{"$f":"NETWORKDAYS(I736,J736,MALegalHolidays)","v":16},5,11,"2018-05-08","2018-05-10",{"$f":"NETWORKDAYS(N736,O736,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"April 2019",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Northfield","6A3441-2018","01360",4988,"Solar","21B8","2018-04-23","2018-05-14",{"$f":"NETWORKDAYS(I737,J737,MALegalHolidays)","v":16},6,10,"2019-02-06",null,{"$f":"NETWORKDAYS(N737,O737,MALegalHolidays)","v":-31022},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Lanesborough","6B1868-2018","01237",15.12,"Solar","15E2","2018-04-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-05-21",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Springfield","6S4359-2018","01129",12.32,"Solar","20A34","2018-04-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-05-29",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4367-2018","01104",800,"Solar","5J15","2018-05-01","2018-06-05",{"$f":"NETWORKDAYS(I740,J740,MALegalHolidays)","v":26},17,9,"2018-06-06","2018-07-18",{"$f":"NETWORKDAYS(N740,O740,MALegalHolidays)","v":31},null,31,null,null,null,null," ",null,null,null,null," ","2018-09-26","2018-11-19",{"$f":"NETWORKDAYS(AC740,AD740,MALegalHolidays)","v":39},null,39,null,null,null,null," ","2018-11-21",null,"2018-08-31",null,"STD",null,null,null,null,null," ",null,null,"2022-08-16","on line"]
[null,"WMECO","Gill ","6A3473-2018","01354",132,"Solar","21B8","2018-05-07","2018-06-11",{"$f":"NETWORKDAYS(I741,J741,MALegalHolidays)","v":26},20,6,"2018-06-12","2018-06-19",{"$f":"NETWORKDAYS(N741,O741,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Gill ","6A3474-2018","01354",2310,"Solar","21B8","2018-05-08","2018-05-29",{"$f":"NETWORKDAYS(I742,J742,MALegalHolidays)","v":16},9,7,"2018-05-30","2018-05-31",{"$f":"NETWORKDAYS(N742,O742,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Plainfield","6A3478-2018","01070",990,"Solar","18K3","2018-05-09","2018-06-20",{"$f":"NETWORKDAYS(I743,J743,MALegalHolidays)","v":31},22,9,"2018-06-21","2018-07-02",{"$f":"NETWORKDAYS(N743,O743,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Shelburne","6A3480-2018","01050",900,"Solar","29R2","2018-05-09","2018-06-21",{"$f":"NETWORKDAYS(I744,J744,MALegalHolidays)","v":32},23,9,"2018-06-22","2018-08-01",{"$f":"NETWORKDAYS(N744,O744,MALegalHolidays)","v":29},null,29,null,null,null,null," ",null,null,null,null," ","2018-12-04","2019-05-17",{"$f":"NETWORKDAYS(AC744,AD744,MALegalHolidays)","v":119},null,119,null,null,null,null," ","2019-06-26",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Lanesborough","6B1875-2018","01237",990,"Solar","15E2","2018-05-09","2018-06-20",{"$f":"NETWORKDAYS(I745,J745,MALegalHolidays)","v":31},22,9,"2018-06-21","2018-07-05",{"$f":"NETWORKDAYS(N745,O745,MALegalHolidays)","v":11},null,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Granville","6S4395-2018","01034",990,"Solar","29A5","2018-05-09","2018-06-20",{"$f":"NETWORKDAYS(I746,J746,MALegalHolidays)","v":31},22,9,"2018-06-21","2018-07-02",{"$f":"NETWORKDAYS(N746,O746,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Windsor","6B1876-2018","01270",990,"Solar","18C1","2018-05-10","2018-06-20",{"$f":"NETWORKDAYS(I747,J747,MALegalHolidays)","v":30},21,9,"2018-06-21","2018-07-23",{"$f":"NETWORKDAYS(N747,O747,MALegalHolidays)","v":23},null,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hatfield","6A3483-2018","01038",249.8,"Solar","18G5","2018-05-14","2018-06-06",{"$f":"NETWORKDAYS(I748,J748,MALegalHolidays)","v":18},5,13,"2018-06-07","2018-08-15",{"$f":"NETWORKDAYS(N748,O748,MALegalHolidays)","v":50},null,50,null,null,null,null," ",null,null,null,null," ","2018-12-02","2018-12-03",{"$f":"NETWORKDAYS(AC748,AD748,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,"2018-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hadley","6A3484-2018","01035",499.9,"Solar","17K5","2018-05-14","2018-06-06",{"$f":"NETWORKDAYS(I749,J749,MALegalHolidays)","v":18},6,12,"2018-06-07","2018-08-06",{"$f":"NETWORKDAYS(N749,O749,MALegalHolidays)","v":43},null,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4407-2018","01107",240,"Solar","21S6","2018-05-14","2018-05-31",{"$f":"NETWORKDAYS(I750,J750,MALegalHolidays)","v":14},5,9,"2018-06-01","2018-06-14",{"$f":"NETWORKDAYS(N750,O750,MALegalHolidays)","v":10},8,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-06-28",null,"2018-08-17",null,"EXP",null,null,null,null,null," ",null,null,"2019-12-12","on line"]
[null,"WMECO","Springfield","6S4409-2018","01104",199.8,"Solar","5J13","2018-05-14","2018-06-13",{"$f":"NETWORKDAYS(I751,J751,MALegalHolidays)","v":23},14,9,"2018-06-14","2018-10-23",{"$f":"NETWORKDAYS(N751,O751,MALegalHolidays)","v":94},null,94,"2018-10-24",null,{"$f":"NETWORKDAYS(S751,T751,MALegalHolidays)","v":-30947},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-27",null,"2018-09-01",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-04","on line"]
[null,"WMECO","Conway","6A3492-2018","01341",900,"Solar","38A1","2018-05-15","2018-06-20",{"$f":"NETWORKDAYS(I752,J752,MALegalHolidays)","v":27},21,6,"2018-06-21","2018-07-06",{"$f":"NETWORKDAYS(N752,O752,MALegalHolidays)","v":12},null,12,null,null,null,null," ",null,null,null,null," ","2018-12-04","2019-05-17",{"$f":"NETWORKDAYS(AC752,AD752,MALegalHolidays)","v":119},null,119,null,null,null,null," ","2019-06-13",null,"Not supplied",null,"COMP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Worthington","6A3493-2018","01098",990,"Solar","18K3","2018-05-15","2018-06-20",{"$f":"NETWORKDAYS(I753,J753,MALegalHolidays)","v":27},21,6,"2018-06-21","2018-07-06",{"$f":"NETWORKDAYS(N753,O753,MALegalHolidays)","v":12},null,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B1881-2018","01201",250,"Solar","15E2","2018-05-15","2018-09-21",{"$f":"NETWORKDAYS(I754,J754,MALegalHolidays)","v":94},0,94,"2018-09-21","2018-11-19",{"$f":"NETWORKDAYS(N754,O754,MALegalHolidays)","v":42},null,42,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-26",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1882-2018","01201",250,"Solar","15E2","2018-05-15","2018-09-21",{"$f":"NETWORKDAYS(I755,J755,MALegalHolidays)","v":94},0,94,"2018-09-21","2018-11-19",{"$f":"NETWORKDAYS(N755,O755,MALegalHolidays)","v":42},null,42,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-26",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Shelburne","6A3497-2018","01370",990,"Solar","22B5","2018-05-16","2018-06-20",{"$f":"NETWORKDAYS(I756,J756,MALegalHolidays)","v":26},21,5,"2018-06-21","2019-03-29",{"$f":"NETWORKDAYS(N756,O756,MALegalHolidays)","v":202},null,202,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Worthington","6A3498-2018","01098",990,"Solar","18K3","2018-05-16","2018-06-20",{"$f":"NETWORKDAYS(I757,J757,MALegalHolidays)","v":26},21,5,"2018-06-21","2018-07-27",{"$f":"NETWORKDAYS(N757,O757,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Lee","6B1887-2018","01238",480,"Solar","16B1","2018-05-17","2018-09-19",{"$f":"NETWORKDAYS(I758,J758,MALegalHolidays)","v":90},0,90,"2018-09-19","2018-11-05",{"$f":"NETWORKDAYS(N758,O758,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ","2018-11-14",null,{"$f":"NETWORKDAYS(AC758,AD758,MALegalHolidays)","v":-30962},null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4424-2018","01119",19.2,"Solar","20A33","2018-05-17","2018-11-08",{"$f":"NETWORKDAYS(I759,J759,MALegalHolidays)","v":126},null,126,"2018-11-08",null,{"$f":"NETWORKDAYS(N759,O759,MALegalHolidays)","v":-30958},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-07-17",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Ashfield","6A3509-2018","01330",4980,"Solar","38A1","2018-05-21","2018-06-21",{"$f":"NETWORKDAYS(I760,J760,MALegalHolidays)","v":24},19,5,"2018-06-22","2018-07-31",{"$f":"NETWORKDAYS(N760,O760,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Huntington","6A3510-2018","01050",4980,"Solar","19J5","2018-05-21","2018-06-21",{"$f":"NETWORKDAYS(I761,J761,MALegalHolidays)","v":24},19,5,"2018-06-22","2018-07-31",{"$f":"NETWORKDAYS(N761,O761,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Deerfield","6A3512-2018","01342",2000,"Solar","22B3","2018-05-22","2018-06-05",{"$f":"NETWORKDAYS(I762,J762,MALegalHolidays)","v":11},9,{"$f":"IF(K762>0,K762-L762,\" \")","v":2},"2018-06-06","2018-07-16",{"$f":"NETWORKDAYS(N762,O762,MALegalHolidays)","v":29},17,{"$f":"IF(P762>0,P762-Q762,\" \")","v":12},null,null,null,null,{"$f":"IF(U762>0,U762-V762,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z762>0,Z762-AA762,\" \")","v":" "},"2018-07-17","2018-11-02",{"$f":"NETWORKDAYS(AC762,AD762,MALegalHolidays)","v":79},null,{"$f":"IF(AE762>0,AE762-AF762,\" \")","v":79},null,null,null,null,{"$f":"IF(AJ762>0,AJ762-AK762,\" \")","v":" "},"2018-11-29",null,"2019-01-31",null,"COMP",null,null,null,null,null,{"$f":"IF(AU762>0,AU762-AV762,\" \")","v":" "},null,null,"2022-09-20","on line"]
[null,"WMECO","Granville","6S4443-2018","01034",4980,"Solar","29A5","2018-05-23","2018-06-21",{"$f":"NETWORKDAYS(I763,J763,MALegalHolidays)","v":22},17,5,"2018-06-22","2018-07-30",{"$f":"NETWORKDAYS(N763,O763,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Deerfield","6A3523-2018","01342",72,"Solar","22B1","2018-05-24","2018-06-20",{"$f":"NETWORKDAYS(I764,J764,MALegalHolidays)","v":20},13,7,"2018-06-21","2018-07-16",{"$f":"NETWORKDAYS(N764,O764,MALegalHolidays)","v":18},null,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-08-30",null,"2018-09-01",null,"EXP",null,null,null,null,null," ",null,null,"2019-10-02","on line"]
[null,"WMECO","Springfield","6S4457-2018","01104",975,"Solar","5J9","2018-05-25","2018-06-11",{"$f":"NETWORKDAYS(I765,J765,MALegalHolidays)","v":12},8,4,"2018-06-12","2018-09-20",{"$f":"NETWORKDAYS(N765,O765,MALegalHolidays)","v":73},null,73,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-02-01",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4459-2018","01129",333.3,"Solar","20A23","2018-05-25","2018-06-20",{"$f":"NETWORKDAYS(I766,J766,MALegalHolidays)","v":19},5,14,"2018-06-21","2018-06-22",{"$f":"NETWORKDAYS(N766,O766,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-07",null,"2018-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southampton","6A3534-2018","01073",5000,"Solar","15A1","2018-05-30","2018-08-02",{"$f":"NETWORKDAYS(I767,J767,MALegalHolidays)","v":47},39,8,"2018-08-03","2018-09-11",{"$f":"NETWORKDAYS(N767,O767,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-11-01",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B1906-2018","01201",2656,"Solar","30B2","2018-05-30","2018-07-31",{"$f":"NETWORKDAYS(I768,J768,MALegalHolidays)","v":45},34,11,"2018-08-01","2020-03-18",{"$f":"NETWORKDAYS(N768,O768,MALegalHolidays)","v":426},null,426,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Blandford","6B1907-2018","01008",4980,"Solar","19J2","2018-05-30","2018-09-12",{"$f":"NETWORKDAYS(I769,J769,MALegalHolidays)","v":76},49,27,"2018-09-13",null,{"$f":"NETWORKDAYS(N769,O769,MALegalHolidays)","v":-30918},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Springfield","6S4467-2018","01104",210,"Solar","21S7","2018-05-31","2018-06-27",{"$f":"NETWORKDAYS(I770,J770,MALegalHolidays)","v":20},3,17,"2018-06-28","2018-08-08",{"$f":"NETWORKDAYS(N770,O770,MALegalHolidays)","v":30},null,30,"2018-11-13","2018-11-20",{"$f":"NETWORKDAYS(S770,T770,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-21",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Granville","6S4468-2018","01034",594,"Solar","29A5","2018-05-31","2018-06-25",{"$f":"NETWORKDAYS(I771,J771,MALegalHolidays)","v":18},14,4,"2018-06-26","2018-07-31",{"$f":"NETWORKDAYS(N771,O771,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Granville","6S4469-2018","01034",1992,"Solar","29A5","2018-05-31","2018-07-31",{"$f":"NETWORKDAYS(I772,J772,MALegalHolidays)","v":44},33,11,"2018-08-01","2018-08-20",{"$f":"NETWORKDAYS(N772,O772,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Gill ","6A3550-2018","01344",2000,"Solar","21C5","2018-06-05","2018-06-28",{"$f":"NETWORKDAYS(I773,J773,MALegalHolidays)","v":18},14,4,"2018-06-29","2018-08-01",{"$f":"NETWORKDAYS(N773,O773,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Westhampton","6A3553-2018","01027",27,"Solar","15A3","2018-06-07","2018-06-20",{"$f":"NETWORKDAYS(I774,J774,MALegalHolidays)","v":10},2,8,"2018-06-21",null,{"$f":"NETWORKDAYS(N774,O774,MALegalHolidays)","v":-30858},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Springfield","6S4501-2018","01104",999,"Solar","5J13","2018-06-07","2018-07-12",{"$f":"NETWORKDAYS(I775,J775,MALegalHolidays)","v":26},17,9,"2018-07-13","2018-08-24",{"$f":"NETWORKDAYS(N775,O775,MALegalHolidays)","v":31},null,31,null,null,null,null," ",null,null,null,null," ","2018-12-31","2019-05-16",{"$f":"NETWORKDAYS(AC775,AD775,MALegalHolidays)","v":99},null,99,null,null,null,null," ","2019-12-20",null,"Not supplied",null,"STD",null,null,null,null,null," ",null,null,"2024-07-23","in construction phase"]
[null,"WMECO","Amherst","6A3567-2018","01002",433.3,"Solar","17K8","2018-06-12","2018-06-20",{"$f":"NETWORKDAYS(I776,J776,MALegalHolidays)","v":7},0,7,"2018-06-21","2018-09-18",{"$f":"NETWORKDAYS(N776,O776,MALegalHolidays)","v":64},null,64,"2018-09-19","2018-11-02",{"$f":"NETWORKDAYS(S776,T776,MALegalHolidays)","v":33},null,33,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-15",null,"2018",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4517-2018","01105",2500,"Diesel","8CNW_1","2018-06-14","2019-02-05",{"$f":"NETWORKDAYS(I777,J777,MALegalHolidays)","v":169},158,11,"2019-02-05","2020-01-14",{"$f":"NETWORKDAYS(N777,O777,MALegalHolidays)","v":246},null,246,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-14",null,"2012",null,"EXP",null,null,null,null,null," ",null,null,null,"in Construction phase"]
[null,"WMECO","Hadley","6A3587-2018","01035",133.19999999999999,"Solar","17K5","2018-06-20","2018-08-01",{"$f":"NETWORKDAYS(I778,J778,MALegalHolidays)","v":31},24,7,"2018-08-02","2018-09-05",{"$f":"NETWORKDAYS(N778,O778,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-12-07",null,"September 2018",null,"EXP",null,null,null,null,null," ",null,null,"2019-04-25","on line"]
[null,"WMECO","Lee","6B1926-2018","01238",2000,"Solar","17G3","2018-06-20","2018-07-16",{"$f":"NETWORKDAYS(I779,J779,MALegalHolidays)","v":19},6,13,"2018-07-17","2018-08-27",{"$f":"NETWORKDAYS(N779,O779,MALegalHolidays)","v":30},null,30,null,null,null,null," ",null,null,null,null," ","2018-11-23","2019-12-10",{"$f":"NETWORKDAYS(AC779,AD779,MALegalHolidays)","v":273},null,273,null,null,null,null," ","2020-03-24",null,"2019-01-20",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A3593-2018","01002",2000,"Battery","18G7","2018-06-22","2019-01-17",{"$f":"NETWORKDAYS(I780,J780,MALegalHolidays)","v":150},null,150,"2019-01-17","2019-05-31",{"$f":"NETWORKDAYS(N780,O780,MALegalHolidays)","v":97},null,97,null,null,null,null," ",null,null,null,null," ","2019-06-10","2019-07-31",{"$f":"NETWORKDAYS(AC780,AD780,MALegalHolidays)","v":38},null,38,null,null,null,null," ","2019-09-04",null,"2018-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Blandford","6B1932-2018","01008",4450,"Solar","19J2","2018-06-26","2018-08-01",{"$f":"NETWORKDAYS(I781,J781,MALegalHolidays)","v":27},13,14,"2018-08-02","2018-10-10",{"$f":"NETWORKDAYS(N781,O781,MALegalHolidays)","v":50},null,50,null,null,null,null," ",null,null,null,null," ","2019-02-07","2019-07-19",{"$f":"NETWORKDAYS(AC781,AD781,MALegalHolidays)","v":117},null,117,null,null,null,null," ","2019-08-05",null,"2019-09-30",null,"COMP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Longmeadow","6S4578-2018","01106",600,"Diesel","22H12","2018-06-28",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2022-10-26","on line"]
[null,"WMECO","Pittsfield","6B1937-2018","01201",1850,"Solar","30B3","2018-06-29","2018-08-01",{"$f":"NETWORKDAYS(I783,J783,MALegalHolidays)","v":24},19,5,"2018-08-02",null,{"$f":"NETWORKDAYS(N783,O783,MALegalHolidays)","v":-30888},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1938-2018","01201",4998,"Solar","30B3","2018-06-29","2018-08-01",{"$f":"NETWORKDAYS(I784,J784,MALegalHolidays)","v":24},18,6,"2018-08-02","2018-08-29",{"$f":"NETWORKDAYS(N784,O784,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-12-31",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Colrain","6A3610-2018","01340",3300,"Solar","29R2","2018-07-03","2018-07-17",{"$f":"NETWORKDAYS(I785,J785,MALegalHolidays)","v":11},4,7,"2018-07-18","2018-08-15",{"$f":"NETWORKDAYS(N785,O785,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2019-08-13",null,{"$f":"NETWORKDAYS(AC785,AD785,MALegalHolidays)","v":-31156},null," ",null,null,null,null," ",null,null,"2019",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Granville","6S4596-2018","01034",40,"Solar","29A5","2018-07-03","2018-07-24",{"$f":"NETWORKDAYS(I786,J786,MALegalHolidays)","v":16},6,10,"2018-07-25","2018-10-22",{"$f":"NETWORKDAYS(N786,O786,MALegalHolidays)","v":64},null,64,"2018-10-22",null,{"$f":"NETWORKDAYS(S786,T786,MALegalHolidays)","v":-30945},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-29",null,"2018-08-15",null,"EXP",null,null,null,null,null," ",null,null,"2020-11-24","on line"]
[null,"WMECO","Greenfield","6A3611-2018","01301",4998,"Solar","22B7","2018-07-05","2018-07-24",{"$f":"NETWORKDAYS(I787,J787,MALegalHolidays)","v":14},7,7,"2018-07-25",null,{"$f":"NETWORKDAYS(N787,O787,MALegalHolidays)","v":-30882},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q2 2019",null,"STD",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hatfield","6A3612-2018","01373",4998,"Solar","18G6","2018-07-05","2018-07-24",{"$f":"NETWORKDAYS(I788,J788,MALegalHolidays)","v":14},8,6,"2018-07-25","2018-08-28",{"$f":"NETWORKDAYS(N788,O788,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ","2018-11-20","2019-04-16",{"$f":"NETWORKDAYS(AC788,AD788,MALegalHolidays)","v":106},null,106,null,null,null,null," ","2019-05-15",null,"Q2 2019",null,"COMP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Bernardston","6A3615-2018","01337",180,"Solar","21C1","2018-07-05","2018-08-01",{"$f":"NETWORKDAYS(I789,J789,MALegalHolidays)","v":20},17,3,"2018-08-02","2018-09-05",{"$f":"NETWORKDAYS(N789,O789,MALegalHolidays)","v":25},null,25,null,"2019-10-09",null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-10-09",null,"2018-12-15",null,"EXP",null,null,null,null,null," ",null,null,"2020-04-22","on line"]
[null,"WMECO","Tolland","6B1941-2018","01034",4998,"Solar","19J4","2018-07-05","2018-07-24",{"$f":"NETWORKDAYS(I790,J790,MALegalHolidays)","v":14},8,6,"2018-07-25","2018-08-15",{"$f":"NETWORKDAYS(N790,O790,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ","2019-05-07",null,{"$f":"NETWORKDAYS(AC790,AD790,MALegalHolidays)","v":-31086},null," ",null,null,null,null," ",null,null,"Q2 2019",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S4610-2018","01056",14.08,"Solar","19S1","2018-07-06",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-08-02",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled, will submit Simplified application"]
[null,"WMECO","Hadley","6A3626-2018","01035",2500,"Solar","17K5","2018-07-11","2018-10-01",{"$f":"NETWORKDAYS(I792,J792,MALegalHolidays)","v":59},null,59,"2018-09-28","2019-04-18",{"$f":"NETWORKDAYS(N792,O792,MALegalHolidays)","v":145},null,145,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-15",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hadley","6A3627-2018","01035",2500,"Solar","17K5","2018-07-11","2018-10-01",{"$f":"NETWORKDAYS(I793,J793,MALegalHolidays)","v":59},null,59,"2018-10-02","2018-10-31",{"$f":"NETWORKDAYS(N793,O793,MALegalHolidays)","v":22},null,22,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-15",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Russell","6A3631-2018","01071",13.688000000000001,"Solar","19J2","2018-07-11",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-05-28",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Feeding Hills","6S4648-2018","01030",15.36,"Solar","16C17","2018-07-13","2018-10-18",{"$f":"NETWORKDAYS(I795,J795,MALegalHolidays)","v":70},31,39,"2018-10-18","2019-01-17",{"$f":"NETWORKDAYS(N795,O795,MALegalHolidays)","v":66},null,66,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-28",null,"2018-09-10",null,"EXP",null,null,null,null,null," ",null,null,"2019-07-19","on line"]
[null,"WMECO","Gill ","6A3641-2018","01354",4950,"Solar","21C5","2018-07-17","2018-08-02",{"$f":"NETWORKDAYS(I796,J796,MALegalHolidays)","v":13},0,13,"2018-08-03","2018-09-10",{"$f":"NETWORKDAYS(N796,O796,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-02-25",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4645-2018","01108",37.6,"Solar","22H16","2018-07-17","2018-07-31",{"$f":"NETWORKDAYS(I797,J797,MALegalHolidays)","v":11},2,9,"2018-08-01","2018-09-04",{"$f":"NETWORKDAYS(N797,O797,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-26",null,"2018-08-10",null,"EXP",null,null,null,null,null," ",null,null,"2019-05-03","on line"]
[null,"WMECO","Springfield","6S4646-2018","01108",37.9,"Solar","22H16","2018-07-17","2018-07-31",{"$f":"NETWORKDAYS(I798,J798,MALegalHolidays)","v":11},2,9,"2018-08-01","2018-09-04",{"$f":"NETWORKDAYS(N798,O798,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-20",null,"2018-08-10",null,"EXP",null,null,null,null,null," ",null,null,"2019-05-03","on line"]
[null,"WMECO","Russell","6A3655-2018","01071",13.928000000000001,"Solar","19J2","2018-07-24",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-09-24",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lanesborough","6B1959-2018","01237",4890,"Solar","15E1","2018-07-24","2018-08-31",{"$f":"NETWORKDAYS(I800,J800,MALegalHolidays)","v":29},11,18,"2018-09-04","2019-04-01",{"$f":"NETWORKDAYS(N800,O800,MALegalHolidays)","v":150},null,150,null,null,null,null," ",null,null,null,null," ","2019-05-30","2022-06-13",{"$f":"NETWORKDAYS(AC800,AD800,MALegalHolidays)","v":793},null,793,null,null,null,null," ",null,null,"Spring 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S4675-2018","01001",4890,"Solar","30A3","2018-07-24","2018-08-13",{"$f":"NETWORKDAYS(I801,J801,MALegalHolidays)","v":15},13,2,"2018-08-14","2019-03-29",{"$f":"NETWORKDAYS(N801,O801,MALegalHolidays)","v":164},null,164,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2019",null,"STD",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southwick","6S4685-2018","01077",1000,"Battery","29A3","2018-07-24","2019-01-29",{"$f":"NETWORKDAYS(I802,J802,MALegalHolidays)","v":136},null,136,"2019-01-29","2019-05-07",{"$f":"NETWORKDAYS(N802,O802,MALegalHolidays)","v":71},null,71,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southwick","6S4686-2018","01077",1000,"Battery","29A3","2018-07-24","2019-01-29",{"$f":"NETWORKDAYS(I803,J803,MALegalHolidays)","v":136},null,136,"2019-01-29","2019-05-07",{"$f":"NETWORKDAYS(N803,O803,MALegalHolidays)","v":71},null,71,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Longmeadow","6S4747-2018","01106",27,"Solar","22H11","2018-08-10","2018-09-26",{"$f":"NETWORKDAYS(I804,J804,MALegalHolidays)","v":34},0,34,"2018-09-27",null,{"$f":"NETWORKDAYS(N804,O804,MALegalHolidays)","v":-30928},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-11-08",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4748-2018","01104",209.8,"Solar","5J14","2018-08-10",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-11-06",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled by applicant"]
[null,"WMECO","Longmeadow","6S4750-2018","01106",27,"Solar","22H11","2018-08-10","2018-09-21",{"$f":"NETWORKDAYS(I806,J806,MALegalHolidays)","v":31},0,31,"2018-10-12","2018-11-21",{"$f":"NETWORKDAYS(N806,O806,MALegalHolidays)","v":29},null,29,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-25",null,"2018-11-08",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4751-2018","01104",209.8,"Solar","5J14","2018-08-10","2018-10-12",{"$f":"NETWORKDAYS(I807,J807,MALegalHolidays)","v":46},0,46,"2018-10-12","2018-11-20",{"$f":"NETWORKDAYS(N807,O807,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-11-06",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S4753-2018","01001",286.39999999999998,"Solar","30A3","2018-08-10","2018-10-01",{"$f":"NETWORKDAYS(I808,J808,MALegalHolidays)","v":37},0,37,"2018-10-01","2018-11-20",{"$f":"NETWORKDAYS(N808,O808,MALegalHolidays)","v":37},null,37,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-25",null,"2018-11-06",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Longmeadow","6S4754-2018","01106",66.599999999999994,"Solar","22H12","2018-08-10","2018-10-03",{"$f":"NETWORKDAYS(I809,J809,MALegalHolidays)","v":39},0,39,"2018-10-03","2018-11-26",{"$f":"NETWORKDAYS(N809,O809,MALegalHolidays)","v":39},null,39,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-26",null,"2018-11-06",null,"EXP",null,null,null,null,null," ",null,null,"2020-04-01","on line"]
[null,"WMECO","Northfield","6A3710-2018","01360",4950,"Solar","21B8","2018-08-14","2018-09-12",{"$f":"NETWORKDAYS(I810,J810,MALegalHolidays)","v":22},1,21,"2018-09-13","2019-08-16",{"$f":"NETWORKDAYS(N810,O810,MALegalHolidays)","v":242},null,242,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-02-15",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4780-2018","01106",163.30000000000001,"Solar","22H16","2018-08-16","2018-10-12",{"$f":"NETWORKDAYS(I811,J811,MALegalHolidays)","v":42},0,42,"2018-10-12","2018-11-26",{"$f":"NETWORKDAYS(N811,O811,MALegalHolidays)","v":32},null,32,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2018-11-26",null,"2018-11-12",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Russell","6A3737-2018","01071",4998,"Solar","19J2","2018-08-21","2018-10-29",{"$f":"NETWORKDAYS(I812,J812,MALegalHolidays)","v":50},null,50,"2018-10-30","2019-04-01",{"$f":"NETWORKDAYS(N812,O812,MALegalHolidays)","v":110},null,110,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q4 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Erving ","6A3738-2018","01344",4494.3999999999996,"Solar","21B9","2018-08-21","2019-01-03",{"$f":"NETWORKDAYS(I813,J813,MALegalHolidays)","v":98},null,98,"2019-01-03","2019-03-28",{"$f":"NETWORKDAYS(N813,O813,MALegalHolidays)","v":61},null,61,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q4 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Otis","6B1993-2018","01253",4998,"Solar","19J4","2018-08-21","2018-12-11",{"$f":"NETWORKDAYS(I814,J814,MALegalHolidays)","v":81},71,10,"2018-12-11","2019-04-01",{"$f":"NETWORKDAYS(N814,O814,MALegalHolidays)","v":80},null,80,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q4 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lee","6B1994-2018","01238",120,"Solar","17G3","2018-08-23","2018-10-09",{"$f":"NETWORKDAYS(I815,J815,MALegalHolidays)","v":34},0,34,"2018-10-10","2019-01-15",{"$f":"NETWORKDAYS(N815,O815,MALegalHolidays)","v":70},null,70,"2019-03-26","2019-04-30",{"$f":"NETWORKDAYS(S815,T815,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-13",null,"2018-12-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B1997-2018","01201",253.1,"Solar","30B2","2018-08-27","2018-09-20",{"$f":"NETWORKDAYS(I816,J816,MALegalHolidays)","v":19},0,19,"2018-09-20","2018-12-12",{"$f":"NETWORKDAYS(N816,O816,MALegalHolidays)","v":60},null,60,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-25",null,"2018-11-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Feeding Hills","6S4816-2018","01030",250,"Solar","16C17","2018-08-28","2018-10-24",{"$f":"NETWORKDAYS(I817,J817,MALegalHolidays)","v":42},0,42,"2018-10-25","2018-12-12",{"$f":"NETWORKDAYS(N817,O817,MALegalHolidays)","v":35},null,35,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"11/31/18",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B2002-2018","01201",1450,"Solar","19A5","2018-08-29","2018-11-28",{"$f":"NETWORKDAYS(I818,J818,MALegalHolidays)","v":66},0,66,"2018-11-28","2019-03-05",{"$f":"NETWORKDAYS(N818,O818,MALegalHolidays)","v":70},null,70,null,null,null,null," ",null,null,null,null," ","2019-05-21","2019-08-19",{"$f":"NETWORKDAYS(AC818,AD818,MALegalHolidays)","v":65},null,65,null,null,null,null," ","2019-08-19",null,"2018-09-01",null,"STD",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Chesterfield","6A3750-2018","01026",3500,"Solar","18K3","2018-08-30","2018-09-25",{"$f":"NETWORKDAYS(I819,J819,MALegalHolidays)","v":19},0,19,"2018-09-26",null,{"$f":"NETWORKDAYS(N819,O819,MALegalHolidays)","v":-30927},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"3/15/2019",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Ludlow","6S4833-2018","01056",2772,"Solar","19S1","2018-08-31","2018-11-28",{"$f":"NETWORKDAYS(I820,J820,MALegalHolidays)","v":64},0,64,"2018-11-28",null,{"$f":"NETWORKDAYS(N820,O820,MALegalHolidays)","v":-30972},null," ",null,null,null,null," ",null,null,null,null," ","2019-07-25","2020-03-09",{"$f":"NETWORKDAYS(AC820,AD820,MALegalHolidays)","v":163},null,163,null,null,null,null," ","2020-03-25",null,"2019-04-01",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Sandisfield","6B2011-2018","01255",400,"Solar","19J4","2018-09-06","2018-09-21",{"$f":"NETWORKDAYS(I821,J821,MALegalHolidays)","v":12},0,12,"2018-09-24","2018-11-25",{"$f":"NETWORKDAYS(N821,O821,MALegalHolidays)","v":45},null,45,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-08-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S4841-2018","01104",450,"Solar","5J9","2018-09-06","2018-11-29",{"$f":"NETWORKDAYS(I822,J822,MALegalHolidays)","v":61},0,61,"2018-11-29","2018-12-12",{"$f":"NETWORKDAYS(N822,O822,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ","2018-12-18","2018-12-19",{"$f":"NETWORKDAYS(AC822,AD822,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,"2018-12-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Agawam","6S4842-2018","01001",580,"Solar","16C16","2018-09-10","2018-10-09",{"$f":"NETWORKDAYS(I823,J823,MALegalHolidays)","v":22},0,22,"2018-10-10","2020-08-06",{"$f":"NETWORKDAYS(N823,O823,MALegalHolidays)","v":477},null,477,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-29",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Ashfield","6A3767-2018","01330",4450,"Solar","38A1","2018-09-11","2018-11-30",{"$f":"NETWORKDAYS(I824,J824,MALegalHolidays)","v":59},0,59,"2018-12-03","2019-02-22",{"$f":"NETWORKDAYS(N824,O824,MALegalHolidays)","v":60},null,60,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"10/1/2019",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Longmeadow","6S4890-2018","01106",16.239999999999998,"Solar","22H12","2018-09-19","2018-10-24",{"$f":"NETWORKDAYS(I825,J825,MALegalHolidays)","v":26},0,26,"2018-10-25","2018-11-21",{"$f":"NETWORKDAYS(N825,O825,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-23",null,"2018-09-21",null,"EXP",null,null,null,null,null," ",null,null,"2018-11-26","on line"]
[null,"WMECO","Agawam","6S4959-2018","01001",366.3,"Solar","30A3","2018-10-05","2018-10-30",{"$f":"NETWORKDAYS(I826,J826,MALegalHolidays)","v":18},null,{"$f":"IF(K826>0,K826-L826,\" \")","v":18},"2018-10-31","2019-01-17",{"$f":"NETWORKDAYS(N826,O826,MALegalHolidays)","v":57},null,{"$f":"IF(P826>0,P826-Q826,\" \")","v":57},null,null,null,null,{"$f":"IF(U826>0,U826-V826,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z826>0,Z826-AA826,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE826>0,AE826-AF826,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ826>0,AJ826-AK826,\" \")","v":" "},"2019-01-30",null,"2018-11-26",null,"EXP",null,null,null,null,null,{"$f":"IF(AU826>0,AU826-AV826,\" \")","v":" "},null,null,null,"withdrawn"]
[null,"WMECO","Russell","6A3820-2018","01071",5000,"Solar","19J2","2018-10-08","2018-12-19",{"$f":"NETWORKDAYS(I827,J827,MALegalHolidays)","v":53},null,53,"2018-12-19","2019-05-07",{"$f":"NETWORKDAYS(N827,O827,MALegalHolidays)","v":100},null,100,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B2036-2018","01201",1000,"Solar","30B3 ","2018-10-12","2019-01-14",{"$f":"NETWORKDAYS(I828,J828,MALegalHolidays)","v":67},null,67,"2019-01-14","2019-02-04",{"$f":"NETWORKDAYS(N828,O828,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ","2019-12-09","2020-03-13",{"$f":"NETWORKDAYS(AC828,AD828,MALegalHolidays)","v":70},null,70,null,null,null,null," ","2020-04-28",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A3840-2018","01002",250,"Solar","19B16","2018-10-15","2018-11-06",{"$f":"NETWORKDAYS(I829,J829,MALegalHolidays)","v":17},null,17,"2018-11-06","2019-01-10",{"$f":"NETWORKDAYS(N829,O829,MALegalHolidays)","v":48},null,48,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A3841-2018","01002",1000,"Solar","19B16","2018-10-15","2018-11-20",{"$f":"NETWORKDAYS(I830,J830,MALegalHolidays)","v":27},null,27,"2018-11-20","2019-01-28",{"$f":"NETWORKDAYS(N830,O830,MALegalHolidays)","v":50},null,50,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Southwick","6S4998-2018","01077",18872,"Solar","29A5","2018-10-18",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Southwick","6S5004-2018","01077",150,"Solar","29A5","2018-10-22","2018-10-24",{"$f":"NETWORKDAYS(I832,J832,MALegalHolidays)","v":3},0,3,"2018-10-25","2019-01-11",{"$f":"NETWORKDAYS(N832,O832,MALegalHolidays)","v":57},null,57,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-15",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S5005-2018","01108",99.9,"Solar","21S12","2018-10-22","2018-10-25",{"$f":"NETWORKDAYS(I833,J833,MALegalHolidays)","v":4},0,4,"2018-10-26",null,{"$f":"NETWORKDAYS(N833,O833,MALegalHolidays)","v":-30949},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-01-15",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Blandford","6B2044-2018","01008",18872,"Solar","19J2","2018-10-23","2019-01-14",{"$f":"NETWORKDAYS(I834,J834,MALegalHolidays)","v":60},null,60,"2019-01-14","2019-02-13",{"$f":"NETWORKDAYS(N834,O834,MALegalHolidays)","v":23},null,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southwick","6S5010-2018","01077",4400,"Solar","29A5","2018-10-23","2019-02-07",{"$f":"NETWORKDAYS(I835,J835,MALegalHolidays)","v":78},null,78,"2019-02-07","2019-03-28",{"$f":"NETWORKDAYS(N835,O835,MALegalHolidays)","v":36},null,36,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Whately","6A3861-2018","01373",4885,"Solar","18G6","2018-10-26","2019-01-14",{"$f":"NETWORKDAYS(I836,J836,MALegalHolidays)","v":57},null,57,"2019-01-14","2019-04-17",{"$f":"NETWORKDAYS(N836,O836,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Whately","6A3868-2018","01373",999,"Solar","18G8","2018-10-30","2019-01-17",{"$f":"NETWORKDAYS(I837,J837,MALegalHolidays)","v":58},50,8,"2019-01-17","2019-03-29",{"$f":"NETWORKDAYS(N837,O837,MALegalHolidays)","v":52},null,52,null,null,null,null," ",null,null,null,null," ",null,"2023-11-09",null,null," ",null,null,null,null," ","2023-11-10",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"ISA issued 11/10/2023"]
[null,"WMECO","Ludlow","6S5036-2018","01056",5550,"Solar","19S1","2018-10-30","2019-01-17",{"$f":"NETWORKDAYS(I838,J838,MALegalHolidays)","v":58},null,58,"2019-01-17","2019-03-22",{"$f":"NETWORKDAYS(N838,O838,MALegalHolidays)","v":47},null,47,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A3871-2018","01002",36.496000000000002,"Solar","17K4","2018-11-01","2018-11-05",{"$f":"NETWORKDAYS(I839,J839,MALegalHolidays)","v":3},null,3,"2018-11-05","2019-01-29",{"$f":"NETWORKDAYS(N839,O839,MALegalHolidays)","v":62},null,62,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southampton","6A3880-2018","01073",3180,"solar","15A1","2018-11-02","2019-01-30",{"$f":"NETWORKDAYS(I840,J840,MALegalHolidays)","v":64},null,64,"2019-01-30","2019-03-29",{"$f":"NETWORKDAYS(N840,O840,MALegalHolidays)","v":43},null,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Shelburne Falls","6A3884-2018","01370",250,"Solar","29R2","2018-11-05","2018-12-06",{"$f":"NETWORKDAYS(I841,J841,MALegalHolidays)","v":24},null,24,"2018-12-06","2018-12-19",{"$f":"NETWORKDAYS(N841,O841,MALegalHolidays)","v":10},null,10,"2019-10-25","2019-11-22",{"$f":"NETWORKDAYS(S841,T841,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-11-26",null,null,null,"EXP",null,null,null,null,null," ",null,null,"2022-07-21","on line"]
[null,"WMECO","Ludlow","6S5054-2018","01056",4400,"Solar","19S3","2018-11-05","2018-12-06",{"$f":"NETWORKDAYS(I842,J842,MALegalHolidays)","v":24},null,24,"2018-12-06","2019-01-03",{"$f":"NETWORKDAYS(N842,O842,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2019-03-05","2019-07-25",{"$f":"NETWORKDAYS(AC842,AD842,MALegalHolidays)","v":103},null,103,null,null,null,null," ","2020-03-25",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hinsdale","6A3888-2018","01235",39600,"Solar","18C2","2018-11-08","2019-01-15",{"$f":"NETWORKDAYS(I843,J843,MALegalHolidays)","v":49},null,49,"2019-01-15","2019-03-22",{"$f":"NETWORKDAYS(N843,O843,MALegalHolidays)","v":49},null,49,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hinsdale","6A3889-2018","01235",14400,"Solar","18C2","2018-11-08","2019-01-15",{"$f":"NETWORKDAYS(I844,J844,MALegalHolidays)","v":49},null,49,"2019-01-15",null,{"$f":"NETWORKDAYS(N844,O844,MALegalHolidays)","v":-31006},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Pittsfield","6B2053-2018","01201",4347.6499999999996,"Solar","15E2","2018-11-08","2019-01-15",{"$f":"NETWORKDAYS(I845,J845,MALegalHolidays)","v":49},null,49,"2019-01-15","2019-02-13",{"$f":"NETWORKDAYS(N845,O845,MALegalHolidays)","v":22},null,22,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q4 2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A3896-2018","01360",2104,"Solar","21B8","2018-11-13","2019-03-19",{"$f":"NETWORKDAYS(I846,J846,MALegalHolidays)","v":91},null,91,"2019-03-19","2019-03-28",{"$f":"NETWORKDAYS(N846,O846,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Hadley","6A3901-2018","01035",518.4,"Solar","17K5","2018-11-15","2018-12-06",{"$f":"NETWORKDAYS(I847,J847,MALegalHolidays)","v":16},null,16,"2018-12-06","2018-12-26",{"$f":"NETWORKDAYS(N847,O847,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A3916-2018","01002",3000,"Battery","18G4","2018-11-19","2019-02-04",{"$f":"NETWORKDAYS(I848,J848,MALegalHolidays)","v":56},null,56,"2019-02-04","2019-05-08",{"$f":"NETWORKDAYS(N848,O848,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ","2019-07-22","2019-10-25",{"$f":"NETWORKDAYS(AC848,AD848,MALegalHolidays)","v":70},null,70,null,null,null,null," ","2020-03-26",null,"4/5/2019",null,"EXP",null,null,null,null,null," ",null,null,"2024-01-09","on line"]
[null,"WMECO","Springfield","6S5117-2018","01103",32.83,"Solar","8CNW_1","2018-11-20","2019-01-18",{"$f":"NETWORKDAYS(I849,J849,MALegalHolidays)","v":44},null,44,"2019-01-18","2019-04-10",{"$f":"NETWORKDAYS(N849,O849,MALegalHolidays)","v":59},null,59,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S5103-2018","01104",532.79999999999995,"Solar","5J9","2018-11-21","2018-11-26",{"$f":"NETWORKDAYS(I850,J850,MALegalHolidays)","v":4},null,4,"2018-11-26","2019-01-17",{"$f":"NETWORKDAYS(N850,O850,MALegalHolidays)","v":39},null,39,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Nov 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B2062-2018","01201",463.01,"Solar","19A5","2018-11-26","2019-01-24",{"$f":"NETWORKDAYS(I851,J851,MALegalHolidays)","v":44},null,44,"2019-01-24",null,{"$f":"NETWORKDAYS(N851,O851,MALegalHolidays)","v":-31013},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-04-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Deerfield","6A3912-2018","01373",15.78,"Solar","22B1","2018-11-28","2018-12-03",{"$f":"NETWORKDAYS(I852,J852,MALegalHolidays)","v":4},null,4,"2018-12-03","2018-12-24",{"$f":"NETWORKDAYS(N852,O852,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ","2018-12-03",null,{"$f":"NETWORKDAYS(AC852,AD852,MALegalHolidays)","v":-30975},null," ",null,null,null,null," ","2019-03-08",null,"12/2018",null,"EXP",null,null,null,null,null," ",null,null,"2019-07-17","on line"]
[null,"WMECO","Agawam","6S5118-2018","01001",4950,"Solar","16C16","2018-11-30","2019-01-15",{"$f":"NETWORKDAYS(I853,J853,MALegalHolidays)","v":33},null,33,"2019-01-28","2019-03-28",{"$f":"NETWORKDAYS(N853,O853,MALegalHolidays)","v":44},null,44,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2018-12-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A3920-2018","01002",2500,"Solar","17K2","2018-12-04","2019-01-24",{"$f":"NETWORKDAYS(I854,J854,MALegalHolidays)","v":38},null,38,"2019-01-24","2019-03-22",{"$f":"NETWORKDAYS(N854,O854,MALegalHolidays)","v":42},null,42,null,null,null,null," ",null,null,null,null," ","2019-04-24","2019-11-27",{"$f":"NETWORKDAYS(AC854,AD854,MALegalHolidays)","v":156},null,156,null,null,null,null," ","2020-03-27",null,"10/1/2019",null,"EXP",null,null,null,null,null," ",null,null,"2022-08-23","on line"]
[null,"WMECO","Lanesborough","6B2072-2018","01237",4540,"Solar","15E1","2018-12-11","2019-01-15",{"$f":"NETWORKDAYS(I855,J855,MALegalHolidays)","v":26},null,26,"2019-01-15","2019-03-22",{"$f":"NETWORKDAYS(N855,O855,MALegalHolidays)","v":49},null,49,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Fall 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S5140-2018","01109",24,"Solar","5J17","2018-12-11","2019-01-17",{"$f":"NETWORKDAYS(I856,J856,MALegalHolidays)","v":28},null,28,"2019-01-17","2019-04-02",{"$f":"NETWORKDAYS(N856,O856,MALegalHolidays)","v":54},null,54,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-03-18",null,null,null,"EXP",null,null,null,null,null," ",null,null,"2019-07-16","on line"]
[null,"WMECO","Greenfield","6A3934-2018","01301",41.47,"Solar","22B2","2018-12-14","2019-01-31",{"$f":"NETWORKDAYS(I857,J857,MALegalHolidays)","v":35},null,35,"2019-01-31","2019-03-22",{"$f":"NETWORKDAYS(N857,O857,MALegalHolidays)","v":37},null,37,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-28",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Greenfield","6A3935-2018","01301",96,"Solar","21C4","2018-12-14","2019-01-23",{"$f":"NETWORKDAYS(I858,J858,MALegalHolidays)","v":29},null,29,"2019-01-23","2019-03-22",{"$f":"NETWORKDAYS(N858,O858,MALegalHolidays)","v":43},null,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-28",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Greenfield","6A3936-2018","01301",101.38,"Solar","22B3 ","2018-12-14","2019-02-07",{"$f":"NETWORKDAYS(I859,J859,MALegalHolidays)","v":40},null,40,"2019-02-07","2019-03-22",{"$f":"NETWORKDAYS(N859,O859,MALegalHolidays)","v":32},null,32,"2019-06-19",null,{"$f":"NETWORKDAYS(S859,T859,MALegalHolidays)","v":-31117},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-12-04",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Greenfield","6A3937-2018","01301",36,"Solar","22B2","2018-12-14","2019-01-23",{"$f":"NETWORKDAYS(I860,J860,MALegalHolidays)","v":29},null,29,"2019-01-23","2019-03-22",{"$f":"NETWORKDAYS(N860,O860,MALegalHolidays)","v":43},null,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-06-06",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Greenfield","6A3938-2018","01301",88.13,"Solar","21C4","2018-12-14","2019-01-24",{"$f":"NETWORKDAYS(I861,J861,MALegalHolidays)","v":30},null,30,"2019-01-24","2019-03-22",{"$f":"NETWORKDAYS(N861,O861,MALegalHolidays)","v":42},null,42,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-06-06",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Greenfield","6A3939-2018","01301",194,"Solar","21C4","2018-12-14","2019-01-24",{"$f":"NETWORKDAYS(I862,J862,MALegalHolidays)","v":30},null,30,"2019-01-24","2019-04-02",{"$f":"NETWORKDAYS(N862,O862,MALegalHolidays)","v":49},null,49,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-28",null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A3949-2018","01002",3182.2240000000002,"Solar","18G7","2018-12-19",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","West Springfield","6S5163-2018","01089",228,"Solar","16C15","2018-12-20","2019-01-03",{"$f":"NETWORKDAYS(I864,J864,MALegalHolidays)","v":11},null,11,"2019-01-03","2019-01-17",{"$f":"NETWORKDAYS(N864,O864,MALegalHolidays)","v":11},null,11,null,null,null,null," ",null,null,null,null," ","2019-01-03",null,{"$f":"NETWORKDAYS(AC864,AD864,MALegalHolidays)","v":-30998},null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Ashfield","6A3958-2018","01330",4998,"Solar","38A1","2018-12-24","2019-02-04",{"$f":"NETWORKDAYS(I865,J865,MALegalHolidays)","v":31},null,31,"2019-02-04","2019-03-28",{"$f":"NETWORKDAYS(N865,O865,MALegalHolidays)","v":39},null,39,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hadley","6A4077-2019","01035",1000,"Battery","17K6","2019-01-03","2019-05-06",{"$f":"NETWORKDAYS(I866,J866,MALegalHolidays)","v":88},null,88,"2019-05-06","2019-05-22",{"$f":"NETWORKDAYS(N866,O866,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ","2019-07-22","2019-10-25",{"$f":"NETWORKDAYS(AC866,AD866,MALegalHolidays)","v":70},null,70,null,null,null,null," ","2019-12-18",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2024-05-09","in construction phase"]
[null,"WMECO","Hadley","6A4078-2019","01035",1000,"Battery","17K1","2019-01-03","2019-05-06",{"$f":"NETWORKDAYS(I867,J867,MALegalHolidays)","v":88},null,88,"2019-05-06","2019-05-22",{"$f":"NETWORKDAYS(N867,O867,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ","2019-07-22","2019-10-25",{"$f":"NETWORKDAYS(AC867,AD867,MALegalHolidays)","v":70},null,70,null,null,null,null," ","2019-12-18",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2024-03-26","on line"]
[null,"WMECO","Plainfield","6A3984-2019","01070",1000,"Battery","18K3","2019-01-22","2019-02-07",{"$f":"NETWORKDAYS(I868,J868,MALegalHolidays)","v":13},null,13,"2019-02-07","2019-03-22",{"$f":"NETWORKDAYS(N868,O868,MALegalHolidays)","v":32},null,32,null,null,null,null," ",null,null,null,null," ","2019-07-22","2019-10-16",{"$f":"NETWORKDAYS(AC868,AD868,MALegalHolidays)","v":63},null,63,null,null,null,null," ","2020-03-27",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2024-01-24","on line"]
[null,"WMECO","Hatfied","6A4031-2019","01038",232,"Solar","18G5","2019-02-14","2019-03-19",{"$f":"NETWORKDAYS(I869,J869,MALegalHolidays)","v":24},null,24,"2019-03-19","2019-04-02",{"$f":"NETWORKDAYS(N869,O869,MALegalHolidays)","v":11},null,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-05-24",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2022-07-21","on line"]
[null,"WMECO","Leyden","6A4033-2019","01301",4980,"Solar","22B7","2019-02-14","2019-02-22",{"$f":"NETWORKDAYS(I870,J870,MALegalHolidays)","v":7},null,7,"2019-02-22","2019-04-18",{"$f":"NETWORKDAYS(N870,O870,MALegalHolidays)","v":40},null,40,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Colrain","6A4034-2019","01340",1980,"Solar","29R2","2019-02-14","2019-02-22",{"$f":"NETWORKDAYS(I871,J871,MALegalHolidays)","v":7},null,7,"2019-02-22","2019-03-19",{"$f":"NETWORKDAYS(N871,O871,MALegalHolidays)","v":18},null,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A4045-2019","01360",3000,"Solar","21B8","2019-02-20","2019-04-01",{"$f":"NETWORKDAYS(I872,J872,MALegalHolidays)","v":29},27,2,"2019-04-01","2019-04-18",{"$f":"NETWORKDAYS(N872,O872,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ","2020-08-04","2022-12-14",{"$f":"NETWORKDAYS(AC872,AD872,MALegalHolidays)","v":617},null,617,null,null,null,null," ","2023-02-27",null,"2020-01-29",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold - construction extension"]
[null,"WMECO","Northfield","6A4048-2019","01360",2000,"Solar","21B8","2019-02-20","2019-05-06",{"$f":"NETWORKDAYS(I873,J873,MALegalHolidays)","v":54},47,7,"2019-05-06","2019-06-07",{"$f":"NETWORKDAYS(N873,O873,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ","2020-08-04","2022-12-14",{"$f":"NETWORKDAYS(AC873,AD873,MALegalHolidays)","v":617},null,617,null,null,null,null," ","2023-02-27",null,"2020-01-29",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold - construction extension"]
[null,"WMECO","Northfield","6A4049-2019","01360",1000,"Solar","21B8","2019-02-20","2019-05-06",{"$f":"NETWORKDAYS(I874,J874,MALegalHolidays)","v":54},42,12,"2019-05-06","2019-05-22",{"$f":"NETWORKDAYS(N874,O874,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ","2020-08-04","2022-12-14",{"$f":"NETWORKDAYS(AC874,AD874,MALegalHolidays)","v":617},null,617,null,null,null,null," ","2023-02-27",null,"2020-01-29",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold - construction extension"]
[null,"WMECO","Ashfield","6A4068-2019","01330",4950,"Solar",null,"2019-03-06","2019-05-08",{"$f":"NETWORKDAYS(I875,J875,MALegalHolidays)","v":46},null,46,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"4/4/2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S5364-2019","01056",212,"Solar","27A5","2019-03-13","2019-05-14",{"$f":"NETWORKDAYS(I876,J876,MALegalHolidays)","v":45},null,45,"2019-05-14","2019-06-28",{"$f":"NETWORKDAYS(N876,O876,MALegalHolidays)","v":34},null,34,"2020-04-15","2020-09-16",{"$f":"NETWORKDAYS(S876,T876,MALegalHolidays)","v":111},null,111,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-09-16",null,"2019-11-01",null,"Exp",null,null,null,null,null," ",null,null,"2023-07-10","on line"]
[null,"WMECO","Whately","6A4126-2019","01093",1000,"Battery","18G8","2019-03-18","2019-04-22",{"$f":"NETWORKDAYS(I877,J877,MALegalHolidays)","v":26},null,26,"2019-04-22","2019-05-08",{"$f":"NETWORKDAYS(N877,O877,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,"2020-01-16",null,null," ",null,null,null,null," ","2020-03-23",null,"3/1/2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S5370-2019","01056",136,"Solar","19S3","2019-03-19","2019-04-30",{"$f":"NETWORKDAYS(I878,J878,MALegalHolidays)","v":31},null,31,"2019-04-30","2019-05-13",{"$f":"NETWORKDAYS(N878,O878,MALegalHolidays)","v":10},null,10,"2019-06-04","2019-07-30",{"$f":"NETWORKDAYS(S878,T878,MALegalHolidays)","v":41},null,41,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-10-22",null,"Q3 2019",null,"Exp",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Agawam","6S5376-2019","01001",15.08,"Solar","30A5","2019-03-19",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-03-03",null,"Exp",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Deerfield","6A4093-2019","01342",72,"Solar","22B1","2019-03-25","2019-05-07",{"$f":"NETWORKDAYS(I880,J880,MALegalHolidays)","v":32},null,32,"2019-05-07","2019-09-05",{"$f":"NETWORKDAYS(N880,O880,MALegalHolidays)","v":88},null,88,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-09-26",null,"5/2019",null,"EXP",null,null,null,null,null," ",null,null,"2020-04-21","on line"]
[null,"WMECO","Springfield","6S5394-2019","01104",80,"Solar","5J16","2019-03-27","2019-04-03",{"$f":"NETWORKDAYS(I881,J881,MALegalHolidays)","v":6},null,6,"2019-04-03","2019-04-11",{"$f":"NETWORKDAYS(N881,O881,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"ASAP",null,"Exp",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Northfield","6A4098-2019","01360",1000,"Solar","21B8","2019-03-29",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S5405-2019","01001",4990,"Solar","30A3","2019-04-03","2019-05-06",{"$f":"NETWORKDAYS(I883,J883,MALegalHolidays)","v":24},null,24,"2019-05-06","2019-05-23",{"$f":"NETWORKDAYS(N883,O883,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,"2019-06-24",null,null," ",null,null,null,null," ",null,null,"Summer 2019",null,"Exp",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Deerfield","6A4131-2019","01342",25.3,"Solar","22B7","2019-04-17","2019-05-07",{"$f":"NETWORKDAYS(I884,J884,MALegalHolidays)","v":15},null,15,"2019-05-07","2019-06-03",{"$f":"NETWORKDAYS(N884,O884,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-08-15",null,"6/12/2019",null,"EXP",null,null,null,null,null," ",null,null,"2019-12-11","on line"]
[null,"WMECO","Lanesborough","6B2129-2019","01237",3960,"Solar","15E1","2019-04-17","2019-05-07",{"$f":"NETWORKDAYS(I885,J885,MALegalHolidays)","v":15},null,15,"2019-05-07","2019-05-23",{"$f":"NETWORKDAYS(N885,O885,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lanesborough","6B2130-2019","01237",4990,"Solar","15E2","2019-04-17","2019-05-07",{"$f":"NETWORKDAYS(I886,J886,MALegalHolidays)","v":15},null,15,"2019-05-07","2019-05-23",{"$f":"NETWORKDAYS(N886,O886,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lanesborough","6B2131-2019","01237",4990,"Solar","15E1","2019-04-17","2019-05-06",{"$f":"NETWORKDAYS(I887,J887,MALegalHolidays)","v":14},null,14,"2019-05-06","2019-05-22",{"$f":"NETWORKDAYS(N887,O887,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Spring 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S5434-2019","01229",200,"Solar","27A13","2019-04-17","2019-05-08",{"$f":"NETWORKDAYS(I888,J888,MALegalHolidays)","v":16},null,16,"2019-05-08","2019-05-23",{"$f":"NETWORKDAYS(N888,O888,MALegalHolidays)","v":12},null,12,"2019-09-25","2020-06-23",{"$f":"NETWORKDAYS(S888,T888,MALegalHolidays)","v":195},null,195,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-06-23",null,"2020-03-24",null,"Exp",null,null,null,null,null," ",null,null,"2022-09-21","on line"]
[null,"WMECO","Colrain","6A4169-2019","01340",25,"Solar","29R2","2019-05-07","2019-06-12",{"$f":"NETWORKDAYS(I889,J889,MALegalHolidays)","v":27},null,27,"2019-06-12","2019-06-18",{"$f":"NETWORKDAYS(N889,O889,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"7/30/2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Colrain","6A4199-2019","01340",25,"Solar","29R2","2019-05-07","2019-06-12",{"$f":"NETWORKDAYS(I890,J890,MALegalHolidays)","v":27},null,{"$f":"IF(K890>0,K890-L890,\" \")","v":27},"2019-06-12","2019-06-18",{"$f":"NETWORKDAYS(N890,O890,MALegalHolidays)","v":5},null,{"$f":"IF(P890>0,P890-Q890,\" \")","v":5},null,null,null,null,{"$f":"IF(U890>0,U890-V890,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z890>0,Z890-AA890,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE890>0,AE890-AF890,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ890>0,AJ890-AK890,\" \")","v":" "},null,null,"2019-07-30",null,"EXP",null,null,null,null,null,{"$f":"IF(AU890>0,AU890-AV890,\" \")","v":" "},null,null,null,"cancelled"]
[null,"WMECO","Colrain","6A4200-2019","01340",25,"Solar","29R2","2019-05-07","2019-06-12",{"$f":"NETWORKDAYS(I891,J891,MALegalHolidays)","v":27},null,27,"2019-06-12","2019-06-25",{"$f":"NETWORKDAYS(N891,O891,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Colrain","6A4201-2019","01340",25,"Solar","29R2","2019-05-07","2019-06-12",{"$f":"NETWORKDAYS(I892,J892,MALegalHolidays)","v":27},null,27,"2019-06-12","2019-06-25",{"$f":"NETWORKDAYS(N892,O892,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-07-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A4175-2019","01002",3778,"Solar","18G7","2019-05-13",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-09-11",null,"Oct 2019",null,"EXP",null,null,null,null,null," ",null,null,"2019-07-30","transmission / ISO"]
[null,"WMECO","Tolland","6B2161-2019","01034",5000,"Solar","19J4","2019-06-11","2019-06-20",{"$f":"NETWORKDAYS(I894,J894,MALegalHolidays)","v":8},6,2,"2019-06-20","2019-06-21",{"$f":"NETWORKDAYS(N894,O894,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q4 2020",null,"EXP",null,null,null,null,null," ",null,null,null,"Plainfield / Blandford Group Study"]
[null,"WMECO","Whately","6A4237-2019","01093",1000,"Solar","18G8","2019-06-13","2019-06-20",{"$f":"NETWORKDAYS(I895,J895,MALegalHolidays)","v":6},null,6,"2019-06-20","2019-06-26",{"$f":"NETWORKDAYS(N895,O895,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2020-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S5606-2019","01001",4975,"Solar","30A1","2019-06-14","2019-06-20",{"$f":"NETWORKDAYS(I896,J896,MALegalHolidays)","v":5},null,5,"2019-06-20","2019-06-24",{"$f":"NETWORKDAYS(N896,O896,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ","2019-12-02","2020-02-19",{"$f":"NETWORKDAYS(AC896,AD896,MALegalHolidays)","v":58},null,58,null,null,null,null," ","2020-04-03",null,"2018-12-14",null,"Exp",null,null,null,null,null," ",null,null,"2021-12-16","on line"]
[null,"WMECO","Westhampton","6A4242-2019","01027",34,"Solar","15A3","2019-06-17","2019-09-11",{"$f":"NETWORKDAYS(I897,J897,MALegalHolidays)","v":63},null,63,"2019-09-11","2019-09-12",{"$f":"NETWORKDAYS(N897,O897,MALegalHolidays)","v":2},null,2,"2019-10-17","2020-02-05",{"$f":"NETWORKDAYS(S897,T897,MALegalHolidays)","v":80},null,80,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-01-12",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2023-08-17","on line"]
[null,"WMECO","Greenfield","6A4259-2019","01301",20,"Solar","21C4","2019-06-21","2019-08-27",{"$f":"NETWORKDAYS(I898,J898,MALegalHolidays)","v":48},null,48,"2019-08-27","2019-10-11",{"$f":"NETWORKDAYS(N898,O898,MALegalHolidays)","v":34},null,34,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-03-03",null,"2019-08-15",null,"EXP",null,null,null,null,null," ",null,null,"2020-10-16","on line"]
[null,"WMECO","Turners Falls","6A4261-2019","01376",460,"Solar","21C2","2019-06-25","2019-06-26",{"$f":"NETWORKDAYS(I899,J899,MALegalHolidays)","v":2},null,2,"2019-06-26","2019-07-01",{"$f":"NETWORKDAYS(N899,O899,MALegalHolidays)","v":4},null,4,"2019-09-10","2019-10-22",{"$f":"NETWORKDAYS(S899,T899,MALegalHolidays)","v":31},null,31,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-10-24",null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Huntington","6A4268-2019","01050",21.54,"Solar","19J5","2019-06-25","2019-09-09",{"$f":"NETWORKDAYS(I900,J900,MALegalHolidays)","v":55},null,55,"2019-09-09","2019-08-14",{"$f":"NETWORKDAYS(N900,O900,MALegalHolidays)","v":-19},null," ","2019-09-12","2019-10-25",{"$f":"NETWORKDAYS(S900,T900,MALegalHolidays)","v":32},null,32,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-10-30",null,"Fall 2019",null,"EXP",null,null,null,null,null," ",null,null,"2020-08-20","on line"]
[null,"WMECO","Springfield","6S5635-2019","01102",1875,"Diesel","5J13","2019-07-02","2019-09-09",{"$f":"NETWORKDAYS(I901,J901,MALegalHolidays)","v":50},null,50,"2019-09-09","2019-12-11",{"$f":"NETWORKDAYS(N901,O901,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-08-11",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-15","on line"]
[null,"WMECO","Ashfield","6A4287-2019","01330",25,"Solar","22B5","2019-07-09","2019-07-10",{"$f":"NETWORKDAYS(I902,J902,MALegalHolidays)","v":2},null,2,"2019-07-10",null,{"$f":"NETWORKDAYS(N902,O902,MALegalHolidays)","v":-31132},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Shelburne","6A4288-2019","01370",25,"Solar","38A1","2019-07-09","2019-07-10",{"$f":"NETWORKDAYS(I903,J903,MALegalHolidays)","v":2},null,2,"2019-07-10","2019-08-06",{"$f":"NETWORKDAYS(N903,O903,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","West Springfield","6S5659-2019","01089",233.3,"Solar","21N5","2019-07-12","2019-07-18",{"$f":"NETWORKDAYS(I904,J904,MALegalHolidays)","v":5},null,5,"2019-07-18","2019-07-29",{"$f":"NETWORKDAYS(N904,O904,MALegalHolidays)","v":8},null,8,"2020-02-19",null,{"$f":"NETWORKDAYS(S904,T904,MALegalHolidays)","v":-31292},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-07-01",null,"2019-12-31",null,"Exp",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pelham","6A4306-2019","01002","2200/3300/4400","Solar","17K2","2019-07-15","2019-09-26",{"$f":"NETWORKDAYS(I905,J905,MALegalHolidays)","v":54},52,2,"2019-09-26","2019-09-30",{"$f":"NETWORKDAYS(N905,O905,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ","2020-12-08","2022-06-29",{"$f":"NETWORKDAYS(AC905,AD905,MALegalHolidays)","v":407},null,407,null,null,null,null," ",null,null,"1/1/21",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Amherst","6A4309-2019","01002",4400,"Solar","17K7","2019-07-15","2019-09-26",{"$f":"NETWORKDAYS(I906,J906,MALegalHolidays)","v":54},51,3,"2019-09-26","2019-09-30",{"$f":"NETWORKDAYS(N906,O906,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ","2020-12-08","2022-05-13",{"$f":"NETWORKDAYS(AC906,AD906,MALegalHolidays)","v":374},null,374,null,null,null,null," ","2023-01-20",null,"2021-01-21",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Easthampton","6A4329-2019","01027",1000,"Solar","15A3","2019-07-19","2019-07-31",{"$f":"NETWORKDAYS(I907,J907,MALegalHolidays)","v":9},9,0,"2019-07-31","2019-08-21",{"$f":"NETWORKDAYS(N907,O907,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ","2021-03-01",null,{"$f":"NETWORKDAYS(AC907,AD907,MALegalHolidays)","v":-31560},null," ",null,null,null,null," ",null,null,"2020-07-10",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","South Deerfield","6A4414-2019","01773",25,"Solar","22B3","2019-08-28","2019-09-03",{"$f":"NETWORKDAYS(I908,J908,MALegalHolidays)","v":5},null,5,"2019-09-03","2019-09-03",{"$f":"NETWORKDAYS(N908,O908,MALegalHolidays)","v":1},null,1,"2019-09-24",null,{"$f":"NETWORKDAYS(S908,T908,MALegalHolidays)","v":-31186},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"","","EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Gill","6A4433-2019","01354",17.600000000000001,"Solar","21C5","2019-09-03","2019-09-06",{"$f":"NETWORKDAYS(I909,J909,MALegalHolidays)","v":4},null,4,"2019-09-06","2019-10-10",{"$f":"NETWORKDAYS(N909,O909,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-12-03",null,"2019-10-15",null,"EXP",null,null,null,null,null," ",null,null,"2020-03-31","on line"]
[null,"WMECO","Lanesborough","6B2239-2019","01237",34.200000000000003,"Solar","15E1","2019-09-03","2019-10-02",{"$f":"NETWORKDAYS(I910,J910,MALegalHolidays)","v":22},null,22,"2019-10-02","2019-10-10",{"$f":"NETWORKDAYS(N910,O910,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-12-30",null,"Nov 2019",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Greenfield","6A4430-2019","01301",25,"Solar","22B4","2019-09-05","2019-09-13",{"$f":"NETWORKDAYS(I911,J911,MALegalHolidays)","v":7},null,7,"2019-09-13","2019-09-17",{"$f":"NETWORKDAYS(N911,O911,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-11-13",null,"Nov 2019",null,"EXP",null,null,null,null,null," ",null,null,"2020-02-07","on line"]
[null,"WMECO","Windsor","6B2245-2019","01270",6,"Solar","18C1","2019-09-05","2019-10-30",{"$f":"NETWORKDAYS(I912,J912,MALegalHolidays)","v":40},null,40,"2019-10-31","2019-10-31",{"$f":"NETWORKDAYS(N912,O912,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Springfield","6S5825-2019","01128",72,"Battery","20A21","2019-09-12","2019-10-07",{"$f":"NETWORKDAYS(I913,J913,MALegalHolidays)","v":18},null,18,"2019-10-07","2019-10-15",{"$f":"NETWORKDAYS(N913,O913,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-03-30",null,"2019-12-30",null,"Exp",null,null,null,null,null," ",null,null,"2020-08-27","on line"]
[null,"WMECO","Northfield","6A4475-2019","01360",25,"Solar","21B8","2019-09-20","2019-10-01",{"$f":"NETWORKDAYS(I914,J914,MALegalHolidays)","v":8},null,8,"2019-10-01","2019-10-08",{"$f":"NETWORKDAYS(N914,O914,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2019-11-30",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Blandford","6B2269-2019","01008",4998,"Solar","19J2","2019-10-01","2019-10-07",{"$f":"NETWORKDAYS(I915,J915,MALegalHolidays)","v":5},3,2,"2019-10-07","2019-10-16",{"$f":"NETWORKDAYS(N915,O915,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Indian Orchard","6S5881-2019","01151",6780,"Solar","27A11","2019-10-01","2019-10-01",{"$f":"NETWORKDAYS(I916,J916,MALegalHolidays)","v":1},null,1,"2019-10-01","2020-01-09",{"$f":"NETWORKDAYS(N916,O916,MALegalHolidays)","v":73},null,73,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2020-04-17",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Ludlow","6S5908-2019","01056",3.8,"Solar","27A4","2019-10-09","2019-10-28",{"$f":"NETWORKDAYS(I917,J917,MALegalHolidays)","v":14},null,14,"2019-10-29","2019-11-01",{"$f":"NETWORKDAYS(N917,O917,MALegalHolidays)","v":4},null,4,"2020-05-19","2020-05-20",{"$f":"NETWORKDAYS(S917,T917,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-21",null,"2019-11-08",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-15","on line"]
[null,"WMECO","Amherst","6A4520-2019","01002",20,"Solar","17K8","2019-10-10","2019-10-15",{"$f":"NETWORKDAYS(I918,J918,MALegalHolidays)","v":4},null,4,"2019-10-15","2019-10-21",{"$f":"NETWORKDAYS(N918,O918,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-11-06",null,"Dec 2019",null,"EXP",null,null,null,null,null," ",null,null,"2020-02-13","on line"]
[null,"WMECO","Greenfield","6A4584-2019","01301",220,"Solar","21C1","2019-11-06","2019-11-12",{"$f":"NETWORKDAYS(I919,J919,MALegalHolidays)","v":5},null,5,"2019-11-13","2019-11-21",{"$f":"NETWORKDAYS(N919,O919,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-12-04",null,"5/2020",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-30","on line"]
[null,"WMECO","Greenfield","6A4585-2019","01301",220,"Solar","21C1","2019-11-06","2019-11-12",{"$f":"NETWORKDAYS(I920,J920,MALegalHolidays)","v":5},null,5,"2019-11-13","2019-11-21",{"$f":"NETWORKDAYS(N920,O920,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2019-12-04",null,"5/2020",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-30","on line"]
[null,"WMECO","Deerfield","6A4600-2019","01373",2250,"Solar","22B1","2019-11-14","2019-11-20",{"$f":"NETWORKDAYS(I921,J921,MALegalHolidays)","v":5},3,2,"2019-11-20","2019-12-02",{"$f":"NETWORKDAYS(N921,O921,MALegalHolidays)","v":9},null,9,null,null,null,null," ",null,null,null,null," ","2021-02-26","2023-11-07",{"$f":"NETWORKDAYS(AC921,AD921,MALegalHolidays)","v":703},null,703,null,null,null,null," ","2023-11-10",null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"ISA issued 11/10/2023"]
[null,"WMECO","Pelham","6A4622-2019","01002",17.600000000000001,"Solar","17K2","2019-11-21","2020-01-30",{"$f":"NETWORKDAYS(I922,J922,MALegalHolidays)","v":51},null,51,"2020-01-30","2020-02-04",{"$f":"NETWORKDAYS(N922,O922,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-03-30",null,"2019-12-17",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-14","on line"]
[null,"WMECO","Tyringham","6B2332-2019","01264",26.25,"Solar","16B1","2019-11-27","2019-12-17",{"$f":"NETWORKDAYS(I923,J923,MALegalHolidays)","v":15},null,15,"2019-12-17","2020-01-22",{"$f":"NETWORKDAYS(N923,O923,MALegalHolidays)","v":27},null,27,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Greenfield","6A4674-2019","01301",23.4,"Solar","22B7","2019-12-31","2020-01-10",{"$f":"NETWORKDAYS(I924,J924,MALegalHolidays)","v":9},null,9,"2020-01-13","2020-01-31",{"$f":"NETWORKDAYS(N924,O924,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-03-24",null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Russell","6A4686-2020","01071",2750,"Solar","19J2","2020-01-13","2020-01-15",{"$f":"NETWORKDAYS(I925,J925,MALegalHolidays)","v":3},2,1,"2020-01-16","2020-02-10",{"$f":"NETWORKDAYS(N925,O925,MALegalHolidays)","v":18},null,18,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-09-30",null,"EXP",null,null,null,null,null," ",null,null,null,"Plainfield / Blandford Group Study"]
[null,"WMECO","Greenfield","6A4689-2020","01301",23.4,"Solar","28WNW_1","2020-01-13","2020-01-28",{"$f":"NETWORKDAYS(I926,J926,MALegalHolidays)","v":12},null,12,"2020-01-28","2020-01-30",{"$f":"NETWORKDAYS(N926,O926,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-06-01",null,"2020-03-15",null,"EXP",null,null,null,null,null," ",null,null,"2020-10-08","on line"]
[null,"WMECO","Windsor","6B2367-2020","01270",6,"Solar","18C1","2020-01-16","2020-02-28",{"$f":"NETWORKDAYS(I927,J927,MALegalHolidays)","v":32},null,32,"2020-02-28","2020-03-05",{"$f":"NETWORKDAYS(N927,O927,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-03-13",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2021-01-08","on line"]
[null,"WMECO","Chesterfield","6A4702-2020","01012",17,"Solar","18K3","2020-01-22","2020-01-24",{"$f":"NETWORKDAYS(I928,J928,MALegalHolidays)","v":3},null,3,"2020-01-28","2020-01-28",{"$f":"NETWORKDAYS(N928,O928,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"March 2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Shelburne","6A4735-2020","01370",240,"Solar","29R2","2020-02-19","2020-02-26",{"$f":"NETWORKDAYS(I929,J929,MALegalHolidays)","v":6},null,6,"2020-02-27","2020-03-09",{"$f":"NETWORKDAYS(N929,O929,MALegalHolidays)","v":8},null,8,"2020-04-07","2020-07-09",{"$f":"NETWORKDAYS(S929,T929,MALegalHolidays)","v":68},null,68,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-07-09",null,"Nov 2020",null,"EXP",null,null,null,null,null," ",null,null,"2024-10-07","customer hold"]
[null,"WMECO","Conway","6A4737-2020","01341",17.600000000000001,"Solar","38A1","2020-02-19","2020-02-28",{"$f":"NETWORKDAYS(I930,J930,MALegalHolidays)","v":8},null,8,"2020-02-28","2020-03-05",{"$f":"NETWORKDAYS(N930,O930,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-04-07",null,"2020-04-21",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-22","on line"]
[null,"WMECO","Easthampton","6A4739-2020","01027",133,"Solar","15A3","2020-02-21","2020-02-28",{"$f":"NETWORKDAYS(I931,J931,MALegalHolidays)","v":6},null,6,"2020-02-28","2020-03-13",{"$f":"NETWORKDAYS(N931,O931,MALegalHolidays)","v":11},null,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-08-27",null,"Nov 2020",null,"EXP",null,null,null,null,null," ",null,null,"2023-09-05","on line"]
[null,"WMECO","Greenfield","6A4743-2020","01301",498,"Solar","22B7","2020-02-25","2020-03-09",{"$f":"NETWORKDAYS(I932,J932,MALegalHolidays)","v":10},10,0,"2020-03-09","2020-03-17",{"$f":"NETWORKDAYS(N932,O932,MALegalHolidays)","v":7},null,7,"2020-09-15","2020-10-30",{"$f":"NETWORKDAYS(S932,T932,MALegalHolidays)","v":34},null,34,null,null,null,null," ","2021-01-09","2022-11-14",{"$f":"NETWORKDAYS(AC932,AD932,MALegalHolidays)","v":481},109,372,null,null,null,null," ","2023-01-12",null,2020,null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Easthampton","6A4745-2020","01027",500,"Solar","15A3","2020-02-26","2020-02-28",{"$f":"NETWORKDAYS(I933,J933,MALegalHolidays)","v":3},null,3,"2020-02-28","2020-03-17",{"$f":"NETWORKDAYS(N933,O933,MALegalHolidays)","v":13},null,13,"2020-06-08","2020-08-17",{"$f":"NETWORKDAYS(S933,T933,MALegalHolidays)","v":51},null,51,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-08-18",null,"Nov 2020",null,"EXP",null,null,null,null,null," ",null,null,"2023-12-15","on line"]
[null,"WMECO","Haldle","6A4756-2020","01035",18,"Solar","18G5","2020-02-27",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A4755-2020","01360",2000,"Solar","21B8","2020-03-02","2020-06-24",{"$f":"NETWORKDAYS(I935,J935,MALegalHolidays)","v":83},80,3,"2020-06-25","2020-07-23",{"$f":"NETWORKDAYS(N935,O935,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2020-11-06","2022-12-14",{"$f":"NETWORKDAYS(AC935,AD935,MALegalHolidays)","v":549},null,549,null,null,null,null," ","2023-02-27",null,"2021-01-29",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold - construction extension"]
[null,"WMECO","Shelburne Falls","6A4759-2020","01370",60,"Solar","29R2","2020-03-03","2020-03-09",{"$f":"NETWORKDAYS(I936,J936,MALegalHolidays)","v":5},null,5,"2020-03-09","2020-03-12",{"$f":"NETWORKDAYS(N936,O936,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-27",null,"Nov 2020",null,"EXP",null,null,null,null,null," ",null,null,"2021-01-20","on line"]
[null,"WMECO","Erving ","6A4764-2020","01344",43.2,"Solar","21B8","2020-03-09","2020-03-11",{"$f":"NETWORKDAYS(I937,J937,MALegalHolidays)","v":3},null,3,"2020-03-12","2020-03-31",{"$f":"NETWORKDAYS(N937,O937,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-04",null,"2020-02-27",null,"EXP",null,null,null,null,null," ",null,null,"2020-12-01","on line"]
[null,"WMECO","Amherst","6A4781-2020","01002",17,"Solar","17K2","2020-03-17","2020-04-02",{"$f":"NETWORKDAYS(I938,J938,MALegalHolidays)","v":13},null,13,"2020-04-02","2020-04-06",{"$f":"NETWORKDAYS(N938,O938,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-28",null,"2020-04-25",null,"EXP",null,null,null,null,null," ",null,null,"2020-10-15","on line"]
[null,"WMECO","Springfield","6S6248-2020","01105",292,"Solar","21S4","2020-03-18","2020-04-21",{"$f":"NETWORKDAYS(I939,J939,MALegalHolidays)","v":25},null,25,"2020-04-21","2020-04-27",{"$f":"NETWORKDAYS(N939,O939,MALegalHolidays)","v":5},null,5,"2021-01-19","2021-02-04",{"$f":"NETWORKDAYS(S939,T939,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-01",null,"Nov 2020",null,"EXP",null,null,null,null,null," ",null,null,"2024-05-07","on line"]
[null,"WMECO","Bernardston","6A4815-2020","01337",996,"Solar","21B8","2020-04-06","2020-11-03",{"$f":"NETWORKDAYS(I940,J940,MALegalHolidays)","v":152},0,152,"2020-11-04","2020-11-09",{"$f":"NETWORKDAYS(N940,O940,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"July 2021",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Hatfield","6A4825-2020","01038",2750,"Solar","18G6","2020-04-13","2020-04-15",{"$f":"NETWORKDAYS(I941,J941,MALegalHolidays)","v":3},2,1,"2020-04-16","2020-04-22",{"$f":"NETWORKDAYS(N941,O941,MALegalHolidays)","v":5},null,5,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-09-30",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Huntington","6A4832-2020","01050",20,"Solar","19J5","2020-04-17","2020-04-27",{"$f":"NETWORKDAYS(I942,J942,MALegalHolidays)","v":7},null,7,"2020-04-28","2020-05-01",{"$f":"NETWORKDAYS(N942,O942,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-12",null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,"2020-09-11","on line"]
[null,"WMECO","South Deerfield","6A4834-2020","01373",10,"Battery","22B1","2020-04-20","2020-04-27",{"$f":"NETWORKDAYS(I943,J943,MALegalHolidays)","v":6},null,6,"2020-04-28","2020-05-05",{"$f":"NETWORKDAYS(N943,O943,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-05-15",null,"asap",null,"EXP",null,null,null,null,null," ",null,null,"2021-03-10","on line"]
[null,"WMECO","Northfield","6A4835-2020","01360",2250,"Solar","21B8","2020-04-20","2020-06-24",{"$f":"NETWORKDAYS(I944,J944,MALegalHolidays)","v":48},45,3,"2020-06-25","2020-07-23",{"$f":"NETWORKDAYS(N944,O944,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2020-11-06",null,{"$f":"NETWORKDAYS(AC944,AD944,MALegalHolidays)","v":-31479},null," ",null,null,null,null," ",null,null,"2021-05-13",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Northfield","6A4838-2020","01360",2000,"Solar","21B8","2020-04-22","2020-06-24",{"$f":"NETWORKDAYS(I945,J945,MALegalHolidays)","v":46},43,3,"2020-06-25","2020-07-23",{"$f":"NETWORKDAYS(N945,O945,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2020-11-06",null,{"$f":"NETWORKDAYS(AC945,AD945,MALegalHolidays)","v":-31479},null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A4839-2020","01360",2000,"Solar","21B8","2020-04-23","2020-06-25",{"$f":"NETWORKDAYS(I946,J946,MALegalHolidays)","v":46},44,2,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N946,O946,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ","2020-11-06",null,{"$f":"NETWORKDAYS(AC946,AD946,MALegalHolidays)","v":-31479},null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Plainfield","6A4840-2020","01070",3300,"Solar","18K3","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I947,J947,MALegalHolidays)","v":47},null,47,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N947,O947,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Plainfield","6A4841-2020","01070",3000,"Solar","18K3","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I948,J948,MALegalHolidays)","v":47},null,47,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N948,O948,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A4842-2020","01337",2000,"Solar","21C1","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I949,J949,MALegalHolidays)","v":47},44,3,"2020-06-26","2020-08-06",{"$f":"NETWORKDAYS(N949,O949,MALegalHolidays)","v":30},null,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Bernardston","6A4843-2020","01337",2000,"Solar","21C1","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I950,J950,MALegalHolidays)","v":47},44,3,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N950,O950,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A4844-2020","01337",2000,"Solar","21C1","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I951,J951,MALegalHolidays)","v":47},44,3,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N951,O951,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A4845-2020","01337",1570,"Solar","21C1","2020-04-23","2020-06-26",{"$f":"NETWORKDAYS(I952,J952,MALegalHolidays)","v":47},44,3,"2020-06-26","2020-07-29",{"$f":"NETWORKDAYS(N952,O952,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Becket","6B2431-2020","01223",3640,"Solar","19J6","2020-04-23","2020-06-25",{"$f":"NETWORKDAYS(I953,J953,MALegalHolidays)","v":46},44,2,"2020-06-26","2020-07-23",{"$f":"NETWORKDAYS(N953,O953,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-05-23",null,"Exp",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Becket","6B2432-2020","01223",7860,"Solar","19J6","2020-04-23","2020-06-25",{"$f":"NETWORKDAYS(I954,J954,MALegalHolidays)","v":46},44,{"$f":"IF(K954>0,K954-L954,\" \")","v":2},"2020-06-26","2020-07-23",{"$f":"NETWORKDAYS(N954,O954,MALegalHolidays)","v":20},null,{"$f":"IF(P954>0,P954-Q954,\" \")","v":20},null,null,null,null,{"$f":"IF(U954>0,U954-V954,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z954>0,Z954-AA954,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE954>0,AE954-AF954,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ954>0,AJ954-AK954,\" \")","v":" "},null,null,"2021-05-23",null,"Exp",null,null,null,null,null,{"$f":"IF(AU954>0,AU954-AV954,\" \")","v":" "},null,null,null,"in system impact study queue"]
[null,"WMECO","Dalton","6B2451-2020","01226",16,"Solar","19A1","2020-05-05",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2020-06-29",null,"Exp",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Tolland","6B2464-2020","01034",30.36,"Solar","19J4","2020-05-21",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Amherst","6A4896-2020","01002",10,"Battery","17K4","2020-06-05","2020-07-14",{"$f":"NETWORKDAYS(I957,J957,MALegalHolidays)","v":28},null,28,"2020-07-15","2020-08-19",{"$f":"NETWORKDAYS(N957,O957,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-09-28",null,"July 2020",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-22","on line"]
[null,"WMECO","Tolland","6B2480-2020","01034",30.36,"Solar","19J4","2020-06-09","2020-08-18",{"$f":"NETWORKDAYS(I958,J958,MALegalHolidays)","v":51},49,2,"2020-08-19","2020-09-03",{"$f":"NETWORKDAYS(N958,O958,MALegalHolidays)","v":12},null,12,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-10-21",null,"2020-08-09",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-16","on line"]
[null,"WMECO","Springfield","6S6361-2020","01104",1669,"Solar","5J13","2020-06-11","2020-06-25",{"$f":"NETWORKDAYS(I959,J959,MALegalHolidays)","v":11},11,0,"2020-06-26","2020-07-30",{"$f":"NETWORKDAYS(N959,O959,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ","2020-12-04","2022-09-09",{"$f":"NETWORKDAYS(AC959,AD959,MALegalHolidays)","v":461},null,461,null,null,null,null," ","2022-09-19",null,"2020-10-01",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Lee","6B2503-2020","01238",4000,"Solar","16B1","2020-06-15","2020-07-09",{"$f":"NETWORKDAYS(I960,J960,MALegalHolidays)","v":19},null,19,"2020-07-10","2020-10-15",{"$f":"NETWORKDAYS(N960,O960,MALegalHolidays)","v":70},null,70,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-04-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A4913-2020","01337",4500,"Solar","21C1","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I961,J961,MALegalHolidays)","v":13},12,1,"2020-07-13","2020-08-14",{"$f":"NETWORKDAYS(N961,O961,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Greenfield","6A4914-2020","01301",1300,"Solar","21C1","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I962,J962,MALegalHolidays)","v":13},12,1,"2020-07-13","2020-08-14",{"$f":"NETWORKDAYS(N962,O962,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ","2020-12-08","2022-12-30",{"$f":"NETWORKDAYS(AC962,AD962,MALegalHolidays)","v":539},18,521,null,null,null,null," ","2023-01-12",null,"2021-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Granville","6S6392-2020","01034",6750,"Solar","29A5","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I963,J963,MALegalHolidays)","v":13},12,1,"2020-07-13","2020-07-23",{"$f":"NETWORKDAYS(N963,O963,MALegalHolidays)","v":9},null,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Granville","6S6393-2020","01034",2250,"Solar","29A5","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I964,J964,MALegalHolidays)","v":13},12,1,"2020-07-13","2020-07-23",{"$f":"NETWORKDAYS(N964,O964,MALegalHolidays)","v":9},null,9,null,null,null,null," ",null,null,null,null," ","2022-07-15","2023-02-27",{"$f":"NETWORKDAYS(AC964,AD964,MALegalHolidays)","v":162},13,149,null,null,null,null," ","2023-03-07",null,"2021-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Granville","6S6394-2020","01034",2250,"Solar","29A5","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I965,J965,MALegalHolidays)","v":13},12,1,"2020-07-13","2020-09-25",{"$f":"NETWORKDAYS(N965,O965,MALegalHolidays)","v":55},null,55,null,null,null,null," ",null,null,null,null," ","2022-07-15","2023-02-27",{"$f":"NETWORKDAYS(AC965,AD965,MALegalHolidays)","v":162},13,149,null,null,null,null," ","2023-03-07",null,"2021-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Granville","6S6395-2020","01034",2250,"Solar","29A5","2020-06-24","2020-07-10",{"$f":"NETWORKDAYS(I966,J966,MALegalHolidays)","v":13},13,0,"2020-07-13","2020-10-05",{"$f":"NETWORKDAYS(N966,O966,MALegalHolidays)","v":61},null,61,null,null,null,null," ",null,null,null,null," ","2022-07-15","2023-02-27",{"$f":"NETWORKDAYS(AC966,AD966,MALegalHolidays)","v":162},13,149,null,null,null,null," ","2023-03-07",null,"2020-07-18",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Dalton","6B2502-2020","01226",499,"Solar","19A3","2020-07-06","2020-08-05",{"$f":"NETWORKDAYS(I967,J967,MALegalHolidays)","v":23},22,1,"2020-08-05","2020-08-14",{"$f":"NETWORKDAYS(N967,O967,MALegalHolidays)","v":8},34,-26,null,null,null,0," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-12",null,"Dec 2020",null,"EXP",null,null,null,null,null," ",null,null,"2023-12-29","on line"]
[null,"WMECO","Feeding Hills","6S6432-2020","01030",10,"Battery","30A1","2020-07-13","2020-08-31",{"$f":"NETWORKDAYS(I968,J968,MALegalHolidays)","v":36},null,36,null,"2020-09-23",null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-10-02",null,"summer 2020",null,"EXP",null,null,null,null,null," ",null,null,"2023-03-15","on line"]
[null,"WMECO","Agawam","6S6455-2020","01001",50,"Solar","30A3","2020-07-22","2020-10-23",{"$f":"NETWORKDAYS(I969,J969,MALegalHolidays)","v":68},null,68,"2020-10-26","2020-11-19",{"$f":"NETWORKDAYS(N969,O969,MALegalHolidays)","v":19},null,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-12-16",null,"2020-09-21",null,"EXP",null,null,null,null,null," ",null,null,"2021-05-20","on line"]
[null,"WMECO","Tyringham","6B2524-2020","01264",9.6,"Battery","16B1","2020-07-24","2020-08-31",{"$f":"NETWORKDAYS(I970,J970,MALegalHolidays)","v":27},null,27,"2020-08-31","2020-09-09",{"$f":"NETWORKDAYS(N970,O970,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-10-15",null,"Summer 2020",null,"EXP",null,null,null,null,null," ",null,null,"2022-08-03","on line"]
[null,"WMECO","Hatfield","6A4961-2020","01038",20,"Solar","18G6","2020-07-28","2020-09-09",{"$f":"NETWORKDAYS(I971,J971,MALegalHolidays)","v":32},null,32,"2020-09-09","2020-09-18",{"$f":"NETWORKDAYS(N971,O971,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-10-05",null,"Autumn",null,"EXP",null,null,null,null,null," ",null,null,"2021-02-10","on line"]
[null,"WMECO","Deerfield","6A4968-2020","01342",900,"Solar","22B1","2020-08-04","2020-09-09",{"$f":"NETWORKDAYS(I972,J972,MALegalHolidays)","v":27},24,3,"2020-09-09","2020-09-28",{"$f":"NETWORKDAYS(N972,O972,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"April 2021",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Granville","6S6539-2020","01034",436,"Biogas","29A5","2020-08-17","2020-09-16",{"$f":"NETWORKDAYS(I973,J973,MALegalHolidays)","v":23},20,3,"2020-09-16","2020-10-21",{"$f":"NETWORKDAYS(N973,O973,MALegalHolidays)","v":26},null,26,"2020-11-23","2021-01-25",{"$f":"NETWORKDAYS(S973,T973,MALegalHolidays)","v":46},null,46,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-01-15",null,"EXP",null,null,null,null,null," ",null,null,null,"in impact study"]
[null,"WMECO","Springfield","6S6574-2020","01103",30,"Diesel","8C24","2020-08-28","2020-09-22",{"$f":"NETWORKDAYS(I974,J974,MALegalHolidays)","v":18},15,3,"2020-09-23","2020-10-27",{"$f":"NETWORKDAYS(N974,O974,MALegalHolidays)","v":25},21,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-11",null,"Dec 2020",null,"EXP",null,null,null,null,null," ",null,null,"2021-06-23","on line"]
[null,"WMECO","Springfield","6S6575-2020","01103",75,"Diesel","8C24","2020-08-28","2020-09-09",{"$f":"NETWORKDAYS(I975,J975,MALegalHolidays)","v":9},6,3,"2020-09-10","2020-10-28",{"$f":"NETWORKDAYS(N975,O975,MALegalHolidays)","v":35},null,35,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Dec 2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S6576-2020","01103",35,"Diesel","8C23","2020-08-28","2020-09-23",{"$f":"NETWORKDAYS(I976,J976,MALegalHolidays)","v":19},16,3,"2020-09-24","2020-10-27",{"$f":"NETWORKDAYS(N976,O976,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Dec 2020",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Shelburne","6A5004-2020","01370",499,"Solar","22B5","2020-09-03","2020-10-20",{"$f":"NETWORKDAYS(I977,J977,MALegalHolidays)","v":34},30,4,"2020-10-21","2020-11-03",{"$f":"NETWORKDAYS(N977,O977,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-07",null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"ISA Issued - Waiting on Constr Payment"]
[null,"WMECO","Hadley","6A5016-2020","01035",5000,"Solar","18G4","2020-09-09","2020-09-09",{"$f":"NETWORKDAYS(I978,J978,MALegalHolidays)","v":1},0,1,"2020-09-09","2020-09-18",{"$f":"NETWORKDAYS(N978,O978,MALegalHolidays)","v":8},null,8,null,null,null,null," ",null,null,null,null," ","2021-04-21","2022-10-19",{"$f":"NETWORKDAYS(AC978,AD978,MALegalHolidays)","v":391},49,342,null,null,null,null," ","2023-01-12",null,"2020-12-15",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Amherst","6A5034-2020","01002",14.64,"Solar","17K2","2020-09-17","2020-11-19",{"$f":"NETWORKDAYS(I979,J979,MALegalHolidays)","v":46},null,46,"2020-11-20","2020-11-25",{"$f":"NETWORKDAYS(N979,O979,MALegalHolidays)","v":4},null,4,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2020-11-25",null,"2020-11-17",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Granville","6S6623-2020","01034",15.36,"Solar","29A5","2020-09-17","2021-09-03",{"$f":"NETWORKDAYS(I980,J980,MALegalHolidays)","v":252},237,15,"2021-09-03","2021-09-27",{"$f":"NETWORKDAYS(N980,O980,MALegalHolidays)","v":17},0,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-10-01",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2023-04-18","on line"]
[null,"WMECO","Pittsfield","6B2615-2020","01201",2490,"Solar","30B3","2020-09-25","2020-10-20",{"$f":"NETWORKDAYS(I981,J981,MALegalHolidays)","v":18},11,7,"2020-10-21","2020-11-09",{"$f":"NETWORKDAYS(N981,O981,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ","2021-02-22","2022-01-20",{"$f":"NETWORKDAYS(AC981,AD981,MALegalHolidays)","v":239},17,222,null,null,null,null," ","2023-01-13",null,"2021-10-01",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Pittsfield","6B2616-2020","01201",996,"Solar","30B3","2020-09-25","2020-10-20",{"$f":"NETWORKDAYS(I982,J982,MALegalHolidays)","v":18},11,7,"2020-10-21","2020-10-23",{"$f":"NETWORKDAYS(N982,O982,MALegalHolidays)","v":3},null,3,null,null,null,null," ",null,null,null,null," ","2021-02-22","2022-01-20",{"$f":"NETWORKDAYS(AC982,AD982,MALegalHolidays)","v":239},17,222,null,null,null,null," ","2022-09-09",null,"2021-10-01",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Amherst","6A5066-2020","01002",20,"Solar","17K2","2020-10-06","2020-11-02",{"$f":"NETWORKDAYS(I983,J983,MALegalHolidays)","v":20},15,5,"2020-11-03","2020-11-03",{"$f":"NETWORKDAYS(N983,O983,MALegalHolidays)","v":1},null,1,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-06-03",null,"2020-11-01",null,"Exp",null,null,null,null,null," ",null,null,"2022-05-26","on line"]
[null,"WMECO","Ludlow","6S6730-2020","01056",990,"Solar","19S1","2020-10-19","2020-11-02",{"$f":"NETWORKDAYS(I984,J984,MALegalHolidays)","v":11},7,4,"2020-11-03","2021-01-05",{"$f":"NETWORKDAYS(N984,O984,MALegalHolidays)","v":46},null,46,null,null,null,null," ",null,null,null,null," ","2021-05-11","2022-10-07",{"$f":"NETWORKDAYS(AC984,AD984,MALegalHolidays)","v":369},22,347,null,null,null,null," ","2022-11-09",null,"2022-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Longmeadow","6S6731-2020","01106",20,"Solar","22H12","2020-10-20","2020-11-03",{"$f":"NETWORKDAYS(I985,J985,MALegalHolidays)","v":11},8,3,"2020-11-04","2020-11-24",{"$f":"NETWORKDAYS(N985,O985,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-06-15",null,"2020-12-20",null,"EXP",null,null,null,null,null," ",null,null,"2023-04-12","on line"]
[null,"WMECO","Greenfield","6A5099-2020","01301",4990,"Battery","21C1","2020-10-27","2020-11-05",{"$f":"NETWORKDAYS(I986,J986,MALegalHolidays)","v":8},null,8,"2020-11-06","2020-11-09",{"$f":"NETWORKDAYS(N986,O986,MALegalHolidays)","v":2},null,2,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-11-20",null,"Exp",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Springfield","6S6762-2020","01109",130.9,"Solar","5J17","2020-10-27","2020-11-09",{"$f":"NETWORKDAYS(I987,J987,MALegalHolidays)","v":10},4,6,"2020-11-10","2020-12-21",{"$f":"NETWORKDAYS(N987,O987,MALegalHolidays)","v":30},0,30,"2021-01-15","2021-02-17",{"$f":"NETWORKDAYS(S987,T987,MALegalHolidays)","v":24},15,9,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-02",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","West Springfield","6S6770-2020","01089",20,"Solar","21N4","2020-10-30","2020-12-08",{"$f":"NETWORKDAYS(I988,J988,MALegalHolidays)","v":28},23,5,"2020-12-09","2021-04-05",{"$f":"NETWORKDAYS(N988,O988,MALegalHolidays)","v":84},0,84,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-04-05",null,"2020-11-03",null,"EXP",null,null,null,null,null," ",null,null,"2022-02-25","on line"]
[null,"WMECO","Greenfield","6A5102-2020","01301",4990,"Solar","22B3","2020-11-05","2020-11-12",{"$f":"NETWORKDAYS(I989,J989,MALegalHolidays)","v":6},0,6,"2020-11-12","2020-11-19",{"$f":"NETWORKDAYS(N989,O989,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ","2021-05-13",null,{"$f":"NETWORKDAYS(AC989,AD989,MALegalHolidays)","v":-31613},null," ",null,null,null,null," ",null,null,"2022-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S6773-2020","01104",25,"Solar","5J16","2020-11-05","2020-11-23",{"$f":"NETWORKDAYS(I990,J990,MALegalHolidays)","v":13},null,13,"2020-11-24","2021-01-22",{"$f":"NETWORKDAYS(N990,O990,MALegalHolidays)","v":44},null,44,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-01-25",null,"2021-01-31",null,"EXP",null,null,null,null,null," ",null,null,"2023-01-24","on line"]
[null,"WMECO","Plainfield","6A5104-2020","01070",10,"Battery","18K3","2020-11-09","2020-11-23",{"$f":"NETWORKDAYS(I991,J991,MALegalHolidays)","v":11},null,11,"2020-11-24","2020-12-29",{"$f":"NETWORKDAYS(N991,O991,MALegalHolidays)","v":26},null,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-01-20",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2022-05-16","on line"]
[null,"WMECO","Pittsfield","6B2658-2020","01201",2495,"Battery",null,"2020-11-12",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-11-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Windsor","6B2659-2020","01270",2495,"Battery",null,"2020-11-12",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-11-20",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S6772-2020","01001",15.2,"Solar","16C17","2020-11-12","2020-11-16",{"$f":"NETWORKDAYS(I994,J994,MALegalHolidays)","v":3},null,3,"2020-11-16","2020-12-03",{"$f":"NETWORKDAYS(N994,O994,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-01",null,"2021-01-11",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-03","on line"]
[null,"WMECO","Southwick","6S6774-2020","01077",10,"Solar","29A5","2020-11-13","2021-02-16",{"$f":"NETWORKDAYS(I995,J995,MALegalHolidays)","v":68},null,68,"2021-02-16","2021-03-05",{"$f":"NETWORKDAYS(N995,O995,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-05",null,"2021-01-13",null,"EXP",null,null,null,null,null," ",null,null,"2021-11-08","on line"]
[null,"WMECO","Lee","6B2660-2020","01240",3625,"Solar","16B5","2020-11-16","2020-11-23",{"$f":"NETWORKDAYS(I996,J996,MALegalHolidays)","v":6},2,4,"2020-11-23","2020-11-30",{"$f":"NETWORKDAYS(N996,O996,MALegalHolidays)","v":6},null,6,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Q 4 2021",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A5103-2020","01002",2840,"Solar",null,"2020-11-18",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Easthampton","6A5105-2020","01029",125,"Solar","15A2","2020-11-24","2020-12-09",{"$f":"NETWORKDAYS(I998,J998,MALegalHolidays)","v":12},null,12,"2020-12-10","2021-02-08",{"$f":"NETWORKDAYS(N998,O998,MALegalHolidays)","v":43},null,43,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-08",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2023-06-28","on line"]
[null,"WMECO","Amherst","6A5106-2020","01002",20,"Solar","19B16","2020-12-03","2021-01-19",{"$f":"NETWORKDAYS(I999,J999,MALegalHolidays)","v":34},28,6,"2021-01-19","2021-04-05",{"$f":"NETWORKDAYS(N999,O999,MALegalHolidays)","v":55},0,55,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-04-05",null,"2021-01-24",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-02","on line"]
[null,"WMECO","Deerfield","6A5118-2020","01342",17.600000000000001,"Solar","22B1","2020-12-10","2021-01-19",{"$f":"NETWORKDAYS(I1000,J1000,MALegalHolidays)","v":29},null,29,"2021-01-19","2021-02-19",{"$f":"NETWORKDAYS(N1000,O1000,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-24",null,"2021-02-07",null,"EXP",null,null,null,null,null," ",null,null,"2022-01-11","on line"]
[null,"WMECO","Amherst","6A5119-2020","01002",20,"Solar","17K5","2020-12-10","2021-01-19",{"$f":"NETWORKDAYS(I1001,J1001,MALegalHolidays)","v":29},null,29,"2021-01-19","2021-02-19",{"$f":"NETWORKDAYS(N1001,O1001,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-24",null,"2021-02-10",null,"EXP",null,null,null,null,null," ",null,null,"2022-01-03","on line"]
[null,"WMECO","South Deerfield","6A5107-2020","01373",4980,"Solar",null,"2020-12-14",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Not Supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Westhampton","6A5111-2020","01027",22.8,"Solar","15A3","2020-12-16","2021-02-01",{"$f":"NETWORKDAYS(I1003,J1003,MALegalHolidays)","v":34},26,8,"2021-02-01","2021-03-10",{"$f":"NETWORKDAYS(N1003,O1003,MALegalHolidays)","v":28},0,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-16",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2021-10-19","on line"]
[null,"WMECO","Ludlow","6S6775-2020","01056",133.19999999999999,"Solar","27A6","2020-12-16","2020-12-24",{"$f":"NETWORKDAYS(I1004,J1004,MALegalHolidays)","v":7},null,7,"2020-12-24","2021-02-05",{"$f":"NETWORKDAYS(N1004,O1004,MALegalHolidays)","v":32},null,32,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-05",null,"2021-04-01",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Montague","6A5108-2020","01376",4500,"Battery","21C2","2020-12-17","2020-12-22",{"$f":"NETWORKDAYS(I1005,J1005,MALegalHolidays)","v":4},null,4,"2020-12-22","2021-01-11",{"$f":"NETWORKDAYS(N1005,O1005,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Montague","6A5109-2020","01376",4500,"Battery","21C2","2020-12-17","2020-12-22",{"$f":"NETWORKDAYS(I1006,J1006,MALegalHolidays)","v":4},null,4,"2020-12-22","2021-01-11",{"$f":"NETWORKDAYS(N1006,O1006,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A5110-2020","01360",4500,"Battery","21B8","2020-12-17","2020-12-22",{"$f":"NETWORKDAYS(I1007,J1007,MALegalHolidays)","v":4},null,4,"2020-12-22","2021-01-11",{"$f":"NETWORKDAYS(N1007,O1007,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Worthington","6A5112-2020","01098",1990,"Solar","18K3","2020-12-22","2020-12-24",{"$f":"NETWORKDAYS(I1008,J1008,MALegalHolidays)","v":3},null,3,"2020-12-24","2021-01-11",{"$f":"NETWORKDAYS(N1008,O1008,MALegalHolidays)","v":13},null,13,null,null,null,null," ",null,null,null,null," ","2021-04-20",null,{"$f":"NETWORKDAYS(AC1008,AD1008,MALegalHolidays)","v":-31596},null," ",null,null,null,null," ",null,null,"2022-01-16",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Feeding Hills","6S6776-2020","01030",7.6,"Solar","16C17","2020-12-22","2021-01-21",{"$f":"NETWORKDAYS(I1009,J1009,MALegalHolidays)","v":23},null,23,"2021-01-21","2021-02-16",{"$f":"NETWORKDAYS(N1009,O1009,MALegalHolidays)","v":19},0,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-16",null,"2020-12-21",null,"EXP",null,null,null,null,null," ",null,null,"2021-07-19","on line"]
[null,"WMECO","Shelburne","6A5113-2020","01370",10,"Solar","22B5","2020-12-23","2021-01-05",{"$f":"NETWORKDAYS(I1010,J1010,MALegalHolidays)","v":10},null,10,"2021-01-05","2021-02-16",{"$f":"NETWORKDAYS(N1010,O1010,MALegalHolidays)","v":31},null,31,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-02-16",null,"May",null,"EXP",null,null,null,null,null," ",null,null,"2021-12-20","on line"]
[null,"WMECO","Feeding Hills","6S6777-2020","01030",17.600000000000001,"Solar","16C17","2020-12-23","2021-03-04",{"$f":"NETWORKDAYS(I1011,J1011,MALegalHolidays)","v":52},null,52,"2021-03-04","2021-03-12",{"$f":"NETWORKDAYS(N1011,O1011,MALegalHolidays)","v":7},0,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-19",null,"2021-02-22",null,"EXP",null,null,null,null,null," ",null,null,"2021-07-19","on line"]
[null,"WMECO","Cummington","6A5114-2020","01026",4990,"Battery","18K3","2020-12-28","2021-01-14",{"$f":"NETWORKDAYS(I1012,J1012,MALegalHolidays)","v":14},null,14,"2021-01-14","2021-01-27",{"$f":"NETWORKDAYS(N1012,O1012,MALegalHolidays)","v":10},null,10,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-22",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Amherst","6A5115-2020","01002",4990,"Battery","18G3","2020-12-28","2021-01-11",{"$f":"NETWORKDAYS(I1013,J1013,MALegalHolidays)","v":11},null,11,"2021-01-11","2021-01-29",{"$f":"NETWORKDAYS(N1013,O1013,MALegalHolidays)","v":15},null,15,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-22",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hinsdale","6B2662-2020","01235",2495,"Battery","18C2","2020-12-28","2021-01-14",{"$f":"NETWORKDAYS(I1014,J1014,MALegalHolidays)","v":14},null,14,"2021-01-14","2021-02-10",{"$f":"NETWORKDAYS(N1014,O1014,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-18",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hinsdale","6B2663-2020","01235",2495,"Battery","18C2","2020-12-28","2021-01-14",{"$f":"NETWORKDAYS(I1015,J1015,MALegalHolidays)","v":14},null,14,"2021-01-14","2021-02-10",{"$f":"NETWORKDAYS(N1015,O1015,MALegalHolidays)","v":20},null,20,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-18",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Otis","6B2664-2020","01253",4990,"Battery","19J4","2020-12-28","2021-01-11",{"$f":"NETWORKDAYS(I1016,J1016,MALegalHolidays)","v":11},null,11,"2021-01-11","2021-02-02",{"$f":"NETWORKDAYS(N1016,O1016,MALegalHolidays)","v":17},null,17,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-18",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Bernardston","6A5116-2020","01337",4990,"Battery","21C1","2020-12-29","2021-01-19",{"$f":"NETWORKDAYS(I1017,J1017,MALegalHolidays)","v":16},null,16,"2021-01-19","2021-01-27",{"$f":"NETWORKDAYS(N1017,O1017,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S6778-2020","01119",4.8,"Solar","20A33","2020-12-29",null,null,null,{"$f":"IF(K1018>0,K1018-L1018,\" \")","v":" "},null,null,null,null,{"$f":"IF(P1018>0,P1018-Q1018,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1018>0,U1018-V1018,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1018>0,Z1018-AA1018,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1018>0,AE1018-AF1018,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1018>0,AJ1018-AK1018,\" \")","v":" "},null,null,"2021-01-01",null,"EXP",null,null,null,null,null,{"$f":"IF(AU1018>0,AU1018-AV1018,\" \")","v":" "},null,null,null,"withdrawn"]
[null,"WMECO","Ludlow","6S6779-2020","01056",5000,"Battery",null,"2020-12-29","2021-01-19",{"$f":"NETWORKDAYS(I1019,J1019,MALegalHolidays)","v":16},null,16,"2021-01-19","2021-02-19",{"$f":"NETWORKDAYS(N1019,O1019,MALegalHolidays)","v":24},null,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-01-14",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Easthampton","6A5120-2021","01027",120,"Solar","15A2","2021-01-08","2021-01-19",{"$f":"NETWORKDAYS(I1020,J1020,MALegalHolidays)","v":8},null,8,"2021-01-19","2021-02-22",{"$f":"NETWORKDAYS(N1020,O1020,MALegalHolidays)","v":25},null,25,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-01",null,"2021-06-01",null,"Exp",null,null,null,null,null," ",null,null,"2021-09-29","on line"]
[null,"WMECO","Easthampton","6A5121-2021","01027",16.86,"Battery","15A5","2021-01-08","2021-02-01",{"$f":"NETWORKDAYS(I1021,J1021,MALegalHolidays)","v":17},null,17,"2021-02-01","2021-03-12",{"$f":"NETWORKDAYS(N1021,O1021,MALegalHolidays)","v":30},null,30,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-10",null,"March 2021",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Windsor","6A5117-2021","01270",10,"Battery","18K3","2021-01-11","2021-02-01",{"$f":"NETWORKDAYS(I1022,J1022,MALegalHolidays)","v":16},null,16,"2021-02-01","2021-03-10",{"$f":"NETWORKDAYS(N1022,O1022,MALegalHolidays)","v":28},null,28,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-11",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Lanesborough","6B2665-2021","01224",4990,"Solar","19A5","2021-01-14","2021-02-22",{"$f":"NETWORKDAYS(I1023,J1023,MALegalHolidays)","v":28},null,28,"2021-02-22","2021-03-15",{"$f":"NETWORKDAYS(N1023,O1023,MALegalHolidays)","v":16},null,16,null,null,null,null," ",null,null,null,null," ","2021-05-20",null,{"$f":"NETWORKDAYS(AC1023,AD1023,MALegalHolidays)","v":-31618},null," ",null,null,null,null," ",null,null,"ASAP",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Westfield","6S6780-2021","01085",2000,"Hydro","18F1","2021-01-19","2021-02-01",{"$f":"NETWORKDAYS(I1024,J1024,MALegalHolidays)","v":10},4,6,"2021-02-01","2021-04-26",{"$f":"NETWORKDAYS(N1024,O1024,MALegalHolidays)","v":61},0,61,null,null,null,0," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2023-12-01",null,"EXP",null,null,null,null,null," ",null,null,null,"withdrawn"]
[null,"WMECO","Becket","6B2666-2021","01223",10,"Solar","19J6","2021-01-21","2021-02-22",{"$f":"NETWORKDAYS(I1025,J1025,MALegalHolidays)","v":23},null,23,"2021-02-22","2021-03-24",{"$f":"NETWORKDAYS(N1025,O1025,MALegalHolidays)","v":23},null,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-25",null,"Spring 2021",null,"EXP",null,null,null,null,null," ",null,null,"2022-10-05","on line"]
[null,"WMECO","Ludlow","6S6781-2021","01056",990,"Solar","19S1","2021-01-26","2021-02-02",{"$f":"NETWORKDAYS(I1026,J1026,MALegalHolidays)","v":6},null,6,"2021-02-02","2021-02-19",{"$f":"NETWORKDAYS(N1026,O1026,MALegalHolidays)","v":14},null,14,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-07-01",null,"EXP",null,null,null,null,null," ",null,null,null,"in impact study"]
[null,"WMECO","Easthampton","6A5123-2021","01027",450,"Solar","15A2","2021-01-29","2021-02-22",{"$f":"NETWORKDAYS(I1027,J1027,MALegalHolidays)","v":17},4,13,"2021-02-22","2021-03-15",{"$f":"NETWORKDAYS(N1027,O1027,MALegalHolidays)","v":16},0,16,null,null,null,null," ",null,null,null,null," ","2021-12-01","2022-06-14",{"$f":"NETWORKDAYS(AC1027,AD1027,MALegalHolidays)","v":140},8,132,null,null,null,null," ","2022-08-08",null,"2021-09-01",null,"Exp",null,null,null,null,null," ",null,null,"2023-12-19","on line"]
[null,"WMECO","Amherst","6A5122-2021","01002",25,"Solar","18G7","2021-02-01","2021-02-22",{"$f":"NETWORKDAYS(I1028,J1028,MALegalHolidays)","v":16},null,16,"2021-02-22","2021-03-24",{"$f":"NETWORKDAYS(N1028,O1028,MALegalHolidays)","v":23},null,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-26",null,"not supplied",null,"Exp",null,null,null,null,null," ",null,null,"2022-05-26","on line"]
[null,"WMECO","Dalton","6B2667-2021","01226",25,"Solar","19A2","2021-02-03","2021-02-22",{"$f":"NETWORKDAYS(I1029,J1029,MALegalHolidays)","v":14},null,14,"2021-02-22","2021-04-05",{"$f":"NETWORKDAYS(N1029,O1029,MALegalHolidays)","v":31},0,31,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-12",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Southwick","6S6782-2021","01077",4600,"Solar","29A1","2021-02-10","2021-02-22",{"$f":"NETWORKDAYS(I1030,J1030,MALegalHolidays)","v":9},null,9,"2021-02-22","2021-03-22",{"$f":"NETWORKDAYS(N1030,O1030,MALegalHolidays)","v":21},null,21,null,null,null,null," ",null,null,null,null," ","2021-09-21","2022-11-29",{"$f":"NETWORKDAYS(AC1030,AD1030,MALegalHolidays)","v":311},null,311,null,null,null,null," ","2022-12-08",null,"2021-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Dalton","6B2669-2021","01226",2660,"Solar","18C1","2021-02-15","2021-02-22",{"$f":"NETWORKDAYS(I1031,J1031,MALegalHolidays)","v":6},3,3,"2021-02-22","2021-03-04",{"$f":"NETWORKDAYS(N1031,O1031,MALegalHolidays)","v":9},null,9,null,null,null,null," ",null,null,null,null," ","2021-05-19","2022-08-23",{"$f":"NETWORKDAYS(AC1031,AD1031,MALegalHolidays)","v":330},38,292,null,null,null,null," ","2023-01-11",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,null,"in construction phase"]
[null,"WMECO","Pittsfield","6B2668-2021","01201",86.4,"Solar","30B7","2021-02-16","2021-03-25",{"$f":"NETWORKDAYS(I1032,J1032,MALegalHolidays)","v":28},27,1,"2021-03-25","2021-04-26",{"$f":"NETWORKDAYS(N1032,O1032,MALegalHolidays)","v":23},0,23,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-13",null,"2021-06-15",null,"EXP",null,null,null,null,null," ",null,null,"2022-06-30","on line"]
[null,"WMECO","Hadley","6A5124-2021","01035",20,"Battery","17K5","2021-02-18","2021-03-03",{"$f":"NETWORKDAYS(I1033,J1033,MALegalHolidays)","v":10},9,1,"2021-03-03","2021-04-05",{"$f":"NETWORKDAYS(N1033,O1033,MALegalHolidays)","v":24},0,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-04-05",null,"March 2021",null,"Exp",null,null,null,null,null," ",null,null,"2022-04-15","on line"]
[null,"WMECO","Springfield","6S6783-2021","01119",4.8,"Solar","20A33","2021-02-18","2021-02-22",{"$f":"NETWORKDAYS(I1034,J1034,MALegalHolidays)","v":3},2,1,"2021-02-22","2021-03-08",{"$f":"NETWORKDAYS(N1034,O1034,MALegalHolidays)","v":11},0,11,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-03-11",null,"2021-01-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Blandford","6B2670-2021","01008",1000,"Solar","19J2","2021-02-26","2021-03-25",{"$f":"NETWORKDAYS(I1035,J1035,MALegalHolidays)","v":20},19,1,"2021-03-25","2021-04-23",{"$f":"NETWORKDAYS(N1035,O1035,MALegalHolidays)","v":22},6,16,null,null,null,0," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Jan 2022",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hatfield","6A5125-2021","01038",250,"Biogas","18G6","2021-03-01","2021-05-19",{"$f":"NETWORKDAYS(I1036,J1036,MALegalHolidays)","v":58},56,2,"2021-05-19","2021-06-14",{"$f":"NETWORKDAYS(N1036,O1036,MALegalHolidays)","v":19},0,19,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2021-08-30",null,"Exp",null,null,null,null,null," ",null,null,null,"in system impact study queue"]
[null,"WMECO","Easthampton","6A5126-2021","01027",17.600000000000001,"Solar","15A5","2021-03-09","2021-03-29",{"$f":"NETWORKDAYS(I1037,J1037,MALegalHolidays)","v":15},6,9,"2021-03-29","2021-05-03",{"$f":"NETWORKDAYS(N1037,O1037,MALegalHolidays)","v":26},2,24,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-26",null,"not supplied",null,"Exp",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S6784-2021","01001",360,"Solar","30A2","2021-03-09","2021-03-25",{"$f":"NETWORKDAYS(I1038,J1038,MALegalHolidays)","v":13},4,9,"2021-03-25","2021-04-22",{"$f":"NETWORKDAYS(N1038,O1038,MALegalHolidays)","v":21},0,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-22",null,"2021-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Agawam","6S6785-2021","01001",499.9,"Solar","30A2","2021-03-09","2021-03-25",{"$f":"NETWORKDAYS(I1039,J1039,MALegalHolidays)","v":13},4,9,"2021-03-25","2021-04-29",{"$f":"NETWORKDAYS(N1039,O1039,MALegalHolidays)","v":26},0,26,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-22",null,"2021-12-31",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Pittsfield","6B2671-2021","01201",166.6,"Solar","30B4","2021-03-12","2021-03-29",{"$f":"NETWORKDAYS(I1040,J1040,MALegalHolidays)","v":12},9,3,"2021-03-29","2021-04-26",{"$f":"NETWORKDAYS(N1040,O1040,MALegalHolidays)","v":21},0,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-13",null,"2021-09-01",null,"EXP",null,null,null,null,null," ",null,null,null,"customer hold"]
[null,"WMECO","Lanesborough","6B2672-2021","01237",16,"Solar","15E1","2021-03-16","2021-03-29",{"$f":"NETWORKDAYS(I1041,J1041,MALegalHolidays)","v":10},6,4,"2021-03-29","2021-04-26",{"$f":"NETWORKDAYS(N1041,O1041,MALegalHolidays)","v":21},0,21,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-13",null,"not supplied",null,"EXP",null,null,null,null,null," ",null,null,"2022-05-13","on line"]
[null,"WMECO","Springfield","6S6786-2021","01128",500,"Solar",null,"2021-03-18",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"Oct 2021",null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Springfield","6S6787-2021","01129",500,"Solar",null,"2021-03-18",null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"EXP",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Northfield","6A5127-2021","01360",1500,"Solar","21B8","2021-03-26","2021-04-09",{"$f":"NETWORKDAYS(I1044,J1044,MALegalHolidays)","v":11},0,11,"2021-04-09","2021-04-19",{"$f":"NETWORKDAYS(N1044,O1044,MALegalHolidays)","v":7},null,7,null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,"2022-04-24",null,"Exp",null,null,null,null,null," ",null,null,null,"cancelled"]
[null,"WMECO","Hadley","ESMAEX-00037","01035",25,"Solar & Battery","18G4","2021-04-08","2021-05-03",{"$f":"NETWORKDAYS(I1045,J1045,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1045,O1045,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-06",null,null,null,null,null,null,null,null,null," ",null,null,"2022-02-11","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Southwick","ESMAEX-00043","01077",8.6999999999999993,"Solar & Battery","29A1","2021-04-14","2021-05-18",{"$f":"NETWORKDAYS(I1046,J1046,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1046,O1046,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-06-07",null,null,null,null,null,null,null,null,null," ",null,null,"2021-12-16","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Indian Orchard","ESMAEX-00045","01151",2040,"Solar",null,"2021-05-28","2021-06-21",{"$f":"NETWORKDAYS(I1047,J1047,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1047,O1047,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-06",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-26","Online",null,null,"2023 ASO Batch 1"]
[null,"WMECO","West Springfield","ESMAEX-00061","01089",21.4,"Solar & Battery","21N9","2021-04-19","2021-05-18",{"$f":"NETWORKDAYS(I1048,J1048,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1048,O1048,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-05-24",null,null,null,null,null,null,null,null,null," ",null,null,"2022-01-18","Online",null,null,null,11.4,"21N PIPER"]
[null,"WMECO","Ludlow","ESMAEX-00069","01056",19.8,"Solar","27A6","2021-04-22","2021-05-18",{"$f":"NETWORKDAYS(I1049,J1049,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1049,O1049,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-06-21",null,null,null,null,null,null,null,null,null," ",null,null,"2021-11-02","Online",null,null,null,9.8000000000000007,"27A ORCHARD"]
[null,"WMECO","Amherst","ESMAEX-00170","01002",66.599999999999994,"Solar","17K4","2022-02-11","2021-06-21",{"$f":"NETWORKDAYS(I1050,J1050,MALegalHolidays)","v":-170},null," ",null,null,{"$f":"NETWORKDAYS(N1050,O1050,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-02-11",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-11","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Huntington","ESMAEX-00294","01050",20,"Solar","19J5","2021-08-11","2021-08-23",{"$f":"NETWORKDAYS(I1051,J1051,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1051,O1051,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-09-21",null,null,null,null,null,null,null,null,null," ",null,null,"2022-06-28","Online"]
[null,"WMECO","Chicopee","ESMAEX-00185","01013",4999,"Battery","21N7","2021-06-15","2024-10-23",{"$f":"NETWORKDAYS(I1052,J1052,MALegalHolidays)","v":877},null,877,null,null,{"$f":"NETWORKDAYS(N1052,O1052,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-03-27",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,null,"2023 ASO Batch 1",4999,"21N PIPER"]
[null,"WMECO","Greenfield","ESMAEX-00134","01301",15,"Solar","22B7","2021-05-18","2021-06-01",{"$f":"NETWORKDAYS(I1053,J1053,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1053,O1053,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-14",null,null,null,null,null,null,null,null,null," ",null,null,"2021-10-26","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","New Ashford","ESMAEX-00146","01237",10,"Solar & Battery","15E1","2021-05-24","2021-06-21",{"$f":"NETWORKDAYS(I1054,J1054,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1054,O1054,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-06-24",null,null,null,null,null,null,null,null,null," ",null,null,"2022-10-03","Online"]
[null,"WMECO","Huntington","ESMAEX-00150","01050",18,"Solar & Battery","19J5","2021-05-26","2021-06-21",{"$f":"NETWORKDAYS(I1055,J1055,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1055,O1055,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-08-03",null,null,null,null,null,null,null,null,null," ",null,null,"2021-11-15","Online",null,null,null,7.68]
[null,"WMECO","Colrain","ESMAEX-00162","01340",22.8,"Solar","29R2","2021-06-02","2021-06-21",{"$f":"NETWORKDAYS(I1056,J1056,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1056,O1056,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-02",null,null,null,null,null,null,null,null,null," ",null,null,"2021-12-02","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Springfield","ESMAEX-00165","01109",7.5,"Solar","5J17","2021-06-03","2021-06-21",{"$f":"NETWORKDAYS(I1057,J1057,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1057,O1057,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-12",null,null,null,null,null,null,null,null,null," ",null,null,"2021-12-10","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Hadley","ESMAEX-00177","01035",375,"Solar","18G5","2021-06-09","2021-06-21",{"$f":"NETWORKDAYS(I1058,J1058,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1058,O1058,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-19",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-14","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Agawam","ESMAEX-00366","01001",17.600000000000001,"Solar & Battery","16C16","2021-08-27","2021-09-30",{"$f":"NETWORKDAYS(I1059,J1059,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1059,O1059,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-10-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-05-13","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Agawam","ESMAEX-00187","01001",22,"Solar","16C16","2021-06-15","2021-07-16",{"$f":"NETWORKDAYS(I1060,J1060,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1060,O1060,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-07-20",null,null,null,null,null,null,null,null,null," ",null,null,"2021-10-13","Online",null,null,null,12,"16C AGAWAM"]
[null,"WMECO","Hadley","ESMAEX-00212","01035",10.44,"Solar","19B15","2021-06-25","2021-07-16",{"$f":"NETWORKDAYS(I1061,J1061,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1061,O1061,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-08-03",null,null,null,null,null,null,null,null,null," ",null,null,"2021-10-26","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Pittsfield","ESMAEX-00205","01201",60,"Internal Combustion Engine","30B2","2021-06-23","2021-07-16",{"$f":"NETWORKDAYS(I1062,J1062,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1062,O1062,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-12-21",null,null,null,null,null,null,null,null,null," ",null,null,"2025-07-28","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Southampton","ESMAEX-00220","01073",996,"Solar & Battery","15A1","2021-10-20","2021-10-26",{"$f":"NETWORKDAYS(I1063,J1063,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1063,O1063,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-02",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,2000,"15A GUNN"]
[null,"WMECO","Greenfield","ESMAEX-00256","01301",100.8,"Solar","21C1","2021-07-21","2021-08-06",{"$f":"NETWORKDAYS(I1064,J1064,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1064,O1064,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-08-25",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-14","Online",null,null,null,null,"21C MONTAGUE"]
[null,"WMECO","Tyringham","ESMAEX-00233","01264",22.8,"Solar","16B1","2021-07-12","2021-08-23",{"$f":"NETWORKDAYS(I1065,J1065,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1065,O1065,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-17",null,null,null,null,null,null,null,null,null," ",null,null,"2022-04-11","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Westhampton","ESMAEX-00728","01027",30,"Battery","15A3","2022-01-13","2022-01-26",{"$f":"NETWORKDAYS(I1066,J1066,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1066,O1066,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-28",null,null,null,null,null,null,null,null,null," ",null,null,"2022-07-27","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Feeding Hills","ESMAEX-00242","01030",8,"Solar","30A1","2021-07-16","2021-08-06",{"$f":"NETWORKDAYS(I1067,J1067,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1067,O1067,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-08-09",null,null,null,null,null,null,null,null,null," ",null,null,"2021-10-07","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Springfield","ESMAEX-00290","01103",150,"Internal Combustion Engine","8C24","2022-01-20","2022-02-10",{"$f":"NETWORKDAYS(I1068,J1068,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1068,O1068,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-18",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-22","Online",null,null,null,0,"8C WEST SPRINGFIELD"]
[null,"WMECO","Easthampton","ESMAEX-00295","01027",9.8000000000000007,"Solar","15A1","2021-08-10","2021-10-12",{"$f":"NETWORKDAYS(I1069,J1069,MALegalHolidays)","v":46},null,46,null,null,{"$f":"NETWORKDAYS(N1069,O1069,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-10-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-01-31","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Springfield","ESMAEX-00296","01129",17.600000000000001,"Solar","20A23","2021-08-10","2021-10-21",{"$f":"NETWORKDAYS(I1070,J1070,MALegalHolidays)","v":53},null,53,null,null,{"$f":"NETWORKDAYS(N1070,O1070,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-01",null,null,null,null,null,null,null,null,null," ",null,null,"2022-05-10","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Springfield","ESMAEX-00332","01105",60,"Internal Combustion Engine","21S5","2021-08-19","2021-10-22",{"$f":"NETWORKDAYS(I1071,J1071,MALegalHolidays)","v":47},null,47,null,null,{"$f":"NETWORKDAYS(N1071,O1071,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-01",null,null,null,null,null,null,null,null,null," ",null,null,"2022-05-06","Online",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Hadley","ESMAEX-00369","01035",45.6,"Solar","18G4","2021-08-30","2021-08-30",{"$f":"NETWORKDAYS(I1072,J1072,MALegalHolidays)","v":1},null,1,null,null,{"$f":"NETWORKDAYS(N1072,O1072,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-05",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-24","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-00383","01109",17.5,"Battery","5J17","2021-09-03","2021-10-26",{"$f":"NETWORKDAYS(I1073,J1073,MALegalHolidays)","v":38},null,38,null,null,{"$f":"NETWORKDAYS(N1073,O1073,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-02",null,null,null,null,null,null,null,null,null," ",null,null,"2021-12-01","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Springfield","ESMAEX-00370","01109",15.8,"Solar","20A31","2021-08-30","2021-09-20",{"$f":"NETWORKDAYS(I1074,J1074,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1074,O1074,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-09-28",null,null,null,null,null,null,null,null,null," ",null,null,"2022-01-27","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Southwick","ESMAEX-00401","01077",18,"Solar","29A1","2021-09-10","2021-09-28",{"$f":"NETWORKDAYS(I1075,J1075,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1075,O1075,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-09-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-02-07","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Ludlow","ESMAEX-00475","01056",1992,"Solar & Battery","27A5","2021-10-06","2021-10-12",{"$f":"NETWORKDAYS(I1076,J1076,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1076,O1076,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-17",null,null,null,null,null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,"2023 ASO Batch 1",null,"27A ORCHARD"]
[null,"WMECO","West Springfield","ESMAEX-00456","01089",16.225000000000001,"Solar","21N9","2021-09-29","2021-10-26",{"$f":"NETWORKDAYS(I1077,J1077,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1077,O1077,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-11","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Westhampton","ESMAEX-00459","01027",9.7349999999999994,"Solar & Battery","15A3","2021-09-30","2021-10-12",{"$f":"NETWORKDAYS(I1078,J1078,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1078,O1078,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-30",null,null,null,null,null,null,null,null,null," ",null,null,"2022-05-24","Online",null,null,null,null,"GUNN"]
[null,"WMECO","Longmeadow","ESMAEX-00471","01106",15.2,"Solar","22H11","2021-10-04","2021-11-08",{"$f":"NETWORKDAYS(I1079,J1079,MALegalHolidays)","v":26},null,26,null,null,{"$f":"NETWORKDAYS(N1079,O1079,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-29",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Springfield","ESMAEX-00491","01107",3000,"Internal Combustion Engine","21S8","2021-10-12","2021-11-09",{"$f":"NETWORKDAYS(I1080,J1080,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1080,O1080,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-11",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-07","Online",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Sunderland","ESMAEX-00483","01375",60,"Solar","18G3","2021-10-08","2021-10-26",{"$f":"NETWORKDAYS(I1081,J1081,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1081,O1081,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-30",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-07","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-00501","01104",108,"Solar","5J9","2021-10-14","2021-10-26",{"$f":"NETWORKDAYS(I1082,J1082,MALegalHolidays)","v":9},null,{"$f":"IF(K1082>0,K1082-L1082,\" \")","v":9},null,null,{"$f":"NETWORKDAYS(N1082,O1082,MALegalHolidays)","v":0},null,{"$f":"IF(P1082>0,P1082-Q1082,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1082>0,U1082-V1082,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1082>0,Z1082-AA1082,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1082>0,AE1082-AF1082,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1082>0,AJ1082-AK1082,\" \")","v":" "},"2022-06-06",null,null,null,null,null,null,null,null,null,{"$f":"IF(AU1082>0,AU1082-AV1082,\" \")","v":" "},null,null,"2023-08-31","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Bernardston","ESMAEX-00657","01337",2200,"Solar & Battery","21B8","2021-12-13","2021-12-14",{"$f":"NETWORKDAYS(I1083,J1083,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1083,O1083,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague","2023 ASO Batch 1",null,"21B FRENCH KING"]
[null,"WMECO","Colrain","ESMAEX-00550","01340",10,"Battery","29R2","2021-10-27","2021-11-08",{"$f":"NETWORKDAYS(I1084,J1084,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1084,O1084,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-12-01",null,null,null,null,null,null,null,null,null," ",null,null,"2023-03-07","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Hinsdale","ESMAEX-00541","01235",20,"Solar","18C2","2021-10-25","2021-11-08",{"$f":"NETWORKDAYS(I1085,J1085,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1085,O1085,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2021-11-30",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-14","Online",null,null,null,null,"BERKSHIRE"]
[null,"WMECO","Agawam","ESMAEX-00578","01001",4990,"Battery","30A6","2022-01-12","2022-01-20",{"$f":"NETWORKDAYS(I1086,J1086,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1086,O1086,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-05",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,"2023 ASO Batch 1",null,"30A SILVER"]
[null,"WMECO","Chicopee","ESMAEX-00750","01013",4100,"Fuel Cell","21N7","2022-01-21","2022-02-10",{"$f":"NETWORKDAYS(I1087,J1087,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1087,O1087,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-07",null,null,null,null,null,null,null,null,null," ",null,null,"2026-01-29","Permission to Operate",null,null,"2023 ASO Batch 1",null,"21N PIPER"]
[null,"WMECO","Hinsdale","ESMAEX-00608","01235",19.52,"Solar","18C2","2021-11-19","2021-12-12",{"$f":"NETWORKDAYS(I1088,J1088,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1088,O1088,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-10",null,null,null,null,null,null,null,null,null," ",null,null,"2022-03-29","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Dalton","ESMAEX-00846","01226",42.6,"Solar",null,"2022-02-22","2022-03-07",{"$f":"NETWORKDAYS(I1089,J1089,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1089,O1089,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-10",null,null,null,null,null,null,null,null,null," ",null,null,"2022-08-02","Online"]
[null,"WMECO","Springfield","ESMAEX-00618","01128",9.92,"Solar & Battery","20A34","2021-11-23","2021-12-08",{"$f":"NETWORKDAYS(I1090,J1090,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1090,O1090,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-11",null,null,null,null,null,null,null,null,null," ",null,null,"2022-03-22","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Montague","ESMAEX-00653","01351",5,"Battery","21C2","2021-12-10","2021-12-16",{"$f":"NETWORKDAYS(I1091,J1091,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1091,O1091,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-18",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-23","Online",null,"Gill-Montague",null,14,"21C MONTAGUE"]
[null,"WMECO","Southwick","ESMAEX-00695","01077",3984,"Solar","29A3","2022-01-31","2022-02-10",{"$f":"NETWORKDAYS(I1092,J1092,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1092,O1092,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick","2023 ASO Batch 1",null,"29A SOUTHWICK"]
[null,"WMECO","Buckland","ESMAEX-00739","01338",24,"Solar","38A1","2022-01-19","2022-01-28",{"$f":"NETWORKDAYS(I1093,J1093,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1093,O1093,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-31",null,null,null,null,null,null,null,null,null," ",null,null,"2023-03-02","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Erving","ESMAEX-00810","01344",2600,"Battery","21C8","2022-02-04","2022-02-28",{"$f":"NETWORKDAYS(I1094,J1094,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1094,O1094,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study",null,null,"2023 ASO Batch 1",null,"21C MONTAGUE"]
[null,"WMECO","Huntington","ESMAEX-01101","01050",4250,"Solar & Battery","19J5","2022-05-12","2022-05-26",{"$f":"NETWORKDAYS(I1095,J1095,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1095,O1095,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",null,"19J BLANDFORD"]
[null,"WMECO","Lee","ESMAEX-00749","01238",9.49,"Solar & Battery","16B5","2022-01-21","2022-01-24",{"$f":"NETWORKDAYS(I1096,J1096,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1096,O1096,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-03-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-03","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Northfield","ESMAEX-00836","01360",40,"Battery",null,"2022-02-16","2022-03-10",{"$f":"NETWORKDAYS(I1097,J1097,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1097,O1097,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-03-15",null,null,null,null,null,null,null,null,null," ",null,null,"2022-07-01","Online"]
[null,"WMECO","Whately","ESMAEX-00756","01093",6.4,"Battery","18G6","2022-01-25","2022-01-28",{"$f":"NETWORKDAYS(I1098,J1098,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1098,O1098,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-01-28",null,null,null,null,null,null,null,null,null," ",null,null,"2022-06-15","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-00823","01105",46.4,"Solar","21S4","2022-02-09","2022-02-18",{"$f":"NETWORKDAYS(I1099,J1099,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1099,O1099,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-01",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-10","Online",null,null,null,null,"CLINTON"]
[null,"WMECO","Longmeadow","ESMAEX-00766","01106",7.09,"Solar & Battery","22H11","2022-01-29","2022-02-22",{"$f":"NETWORKDAYS(I1100,J1100,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1100,O1100,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-03-09",null,null,null,null,null,null,null,null,null," ",null,null,"2022-04-21","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Springfield","ESMAEX-00777","01118",4999.2,"Battery","20A21","2023-01-18","2023-02-17",{"$f":"NETWORKDAYS(I1101,J1101,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1101,O1101,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Exhibit E Agreement",null,null,null,4.9997999999999996,"20A BRECKWOOD"]
[null,"WMECO","Lee","ESMAEX-00806","01238",7.6,"Solar & Battery","16B5","2022-02-03","2022-04-06",{"$f":"NETWORKDAYS(I1102,J1102,MALegalHolidays)","v":45},null,45,null,null,{"$f":"NETWORKDAYS(N1102,O1102,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-12",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-08","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Pittsfield","ESMAEX-00914","01201",440,"Solar","19A3","2022-04-07","2022-04-19",{"$f":"NETWORKDAYS(I1103,J1103,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1103,O1103,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-06",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-12","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Lee","ESMAEX-00855","01238",19.8,"Solar & Battery","16B1","2022-02-24","2022-03-02",{"$f":"NETWORKDAYS(I1104,J1104,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1104,O1104,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-09","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Pittsfield","ESMAEX-00854","01201",15.2,"Solar & Battery","30B7","2022-02-24","2022-04-06",{"$f":"NETWORKDAYS(I1105,J1105,MALegalHolidays)","v":30},null,30,null,null,{"$f":"NETWORKDAYS(N1105,O1105,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-12",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-14","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","West Springfield","ESMAEX-00868","01089",5,"Battery","21N4","2022-03-01","2022-03-29",{"$f":"NETWORKDAYS(I1106,J1106,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1106,O1106,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-01","Online",null,null,null,14,"21N PIPER"]
[null,"WMECO","Feeding Hills","ESMAEX-00898","01030",15.2,"Solar","30A6","2022-03-11","2022-03-17",{"$f":"NETWORKDAYS(I1107,J1107,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1107,O1107,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-03-22",null,null,null,null,null,null,null,null,null," ",null,null,"2022-12-21","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Springfield","ESMAEX-00942","01108",13.6,"Solar","22H16","2022-03-17","2022-03-28",{"$f":"NETWORKDAYS(I1108,J1108,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1108,O1108,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2022-10-17","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Ludlow","ESMAEX-00910","01056",9.8000000000000007,"Solar","27A5","2022-03-11","2022-03-17",{"$f":"NETWORKDAYS(I1109,J1109,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1109,O1109,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-19","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Agawam","ESMAEX-00944","01001",149.1,"Solar","30A3","2022-03-18","2022-03-28",{"$f":"NETWORKDAYS(I1110,J1110,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1110,O1110,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-15",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-12","Online",null,null,null,null,"SILVER"]
[null,"WMECO","Southwick","ESMAEX-00933","01077",15.2,"Solar","29A5","2022-03-16","2022-04-12",{"$f":"NETWORKDAYS(I1111,J1111,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1111,O1111,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-26",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-05","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Pittsfield","ESMAEX-00941","01201",10,"Solar","30B7","2022-03-17","2022-04-07",{"$f":"NETWORKDAYS(I1112,J1112,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1112,O1112,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-04-21",null,null,null,null,null,null,null,null,null," ",null,null,"2022-08-05","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Springfield","ESMAEX-00957","01095",240,"Solar","20A35","2022-05-10","2022-06-09",{"$f":"NETWORKDAYS(I1113,J1113,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1113,O1113,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-11",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Southwick","ESMAEX-00958","01077",240,"Solar","29A5","2022-05-10","2022-06-09",{"$f":"NETWORKDAYS(I1114,J1114,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1114,O1114,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-20",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-30","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Montague","ESMAEX-00988","01376",11000,"Battery","21C6","2023-01-20","2023-01-23",{"$f":"NETWORKDAYS(I1115,J1115,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1115,O1115,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague","2023 ASO Batch 1",4990,"21C MONTAGUE"]
[null,"WMECO","Granville","ESMAEX-01120","01034",15.2,"Solar & Battery","29A5","2022-04-27","2022-05-09",{"$f":"NETWORKDAYS(I1116,J1116,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1116,O1116,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-10",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-14","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Dalton","ESMAEX-01075","01226",20,"Solar","18C1","2022-04-12","2022-04-26",{"$f":"NETWORKDAYS(I1117,J1117,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1117,O1117,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-08-08","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Northfield","ESMAEX-01087","01360",10,"Battery","21B8","2022-04-16","2022-05-16",{"$f":"NETWORKDAYS(I1118,J1118,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1118,O1118,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-16",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-23","Online",null,"Gill-Montague",null,null,"21B FRENCH KING"]
[null,"WMECO","Huntington","ESMAEX-01102","01050",4999,"Solar","19J5","2022-05-12","2022-05-26",{"$f":"NETWORKDAYS(I1119,J1119,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1119,O1119,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",null,"19J BLANDFORD"]
[null,"WMECO","Lanesborough","ESMAEX-01110","01237",3.54,"Solar & Battery","15E1","2022-04-25","2022-05-04",{"$f":"NETWORKDAYS(I1120,J1120,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1120,O1120,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-14","Online"]
[null,"WMECO","Ludlow","ESMAEX-01134",10709,490,"Solar","27A5","2022-06-14","2022-06-16",{"$f":"NETWORKDAYS(I1121,J1121,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1121,O1121,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-12",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Westhampton","ESMAEX-01141","01027",3.8,"Solar & Battery","15A3","2022-05-03","2022-05-18",{"$f":"NETWORKDAYS(I1122,J1122,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1122,O1122,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-25",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-24","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","West Springfield","ESMAEX-01146","01089",3.8,"Solar & Battery","21N4","2022-05-04","2022-05-18",{"$f":"NETWORKDAYS(I1123,J1123,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1123,O1123,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-24",null,null,null,null,null,null,null,null,null," ",null,null,"2023-03-09","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Springfield","ESMAEX-01148","01104",400,"Solar & Battery","5J9","2022-06-14","2022-06-30",{"$f":"NETWORKDAYS(I1124,J1124,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1124,O1124,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-14",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Greenfield","ESMAEX-01159","01301",996,"Solar & Battery","22B7","2022-10-10","2022-10-21",{"$f":"NETWORKDAYS(I1125,J1125,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1125,O1125,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-01-28",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,996,"22B CUMBERLAND"]
[null,"WMECO","Agawam","ESMAEX-01547","01001",117.3,"Solar","30A2","2022-09-06","2022-09-13",{"$f":"NETWORKDAYS(I1126,J1126,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1126,O1126,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-09-13",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-06","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Longmeadow","ESMAEX-01165","01106",10,"Solar & Battery","22H17","2022-05-10","2022-05-18",{"$f":"NETWORKDAYS(I1127,J1127,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1127,O1127,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-05-20",null,null,null,null,null,null,null,null,null," ",null,null,"2022-08-22","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Plainfield","ESMAEX-01166","01070",4980,"Solar & Battery","18K3","2023-03-24","2023-05-05",{"$f":"NETWORKDAYS(I1128,J1128,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1128,O1128,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,4980,"18K PLAINFIELD"]
[null,"WMECO","Westhampton","ESMAEX-01182","01027",15.2,"Solar & Battery","15A3","2022-05-16","2022-06-09",{"$f":"NETWORKDAYS(I1129,J1129,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1129,O1129,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-06-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-22","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Springfield","ESMAEX-01230","01109",791.5,"Solar & Battery","21S4","2022-07-28","2022-08-04",{"$f":"NETWORKDAYS(I1130,J1130,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1130,O1130,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-11-20",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Bernardston","ESMAEX-01240","01337",15.2,"Solar","21C5","2022-06-01","2022-06-16",{"$f":"NETWORKDAYS(I1131,J1131,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1131,O1131,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-07",null,null,null,null,null,null,null,null,null," ",null,null,"2025-04-07","Online",null,"Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","West Springfield","ESMAEX-01249","01089",10,"Battery","21N4","2022-06-02","2022-06-09",{"$f":"NETWORKDAYS(I1132,J1132,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1132,O1132,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-11",null,null,null,null,null,null,null,null,null," ",null,null,"2023-07-05","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Springfield","ESMAEX-01251","01103",990,"Solar & Battery","5J13","2023-08-02","2023-08-11",{"$f":"NETWORKDAYS(I1133,J1133,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1133,O1133,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Springfield","ESMAEX-01257","01129",6,"Solar","20A14","2022-06-06","2022-06-16",{"$f":"NETWORKDAYS(I1134,J1134,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1134,O1134,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-06-17",null,null,null,null,null,null,null,null,null," ",null,null,"2022-09-19","Online",null,null,null,6,"20A BRECKWOOD"]
[null,"WMECO","Amherst","ESMAEX-01410","01002",50,"Solar","17K5","2022-07-25","2022-08-04",{"$f":"NETWORKDAYS(I1135,J1135,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1135,O1135,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-09-14",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-04","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Easthampton","ESMAEX-01308","01027",10,"Solar","15A1","2022-06-17","2022-06-30",{"$f":"NETWORKDAYS(I1136,J1136,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1136,O1136,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-26",null,null,null,null,null,null,null,null,null," ",null,null,"2022-10-12","Online",null,null,null,10,"15A GUNN"]
[null,"WMECO","Feeding Hills","ESMAEX-01317","01030",15.2,"Solar","30A6","2022-06-22","2022-06-30",{"$f":"NETWORKDAYS(I1137,J1137,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1137,O1137,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-13","Online",null,null,null,16,"30A SILVER"]
[null,"WMECO","Easthampton","ESMAEX-01326","01027",17.600000000000001,"Battery","15A3","2022-06-27","2022-07-01",{"$f":"NETWORKDAYS(I1138,J1138,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1138,O1138,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-07-26",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-02","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Whately","ESMAEX-01352","01093",10,"Battery","18G8","2022-07-07","2022-07-29",{"$f":"NETWORKDAYS(I1139,J1139,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1139,O1139,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-08-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-02-02","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Greenfield","ESMAEX-01376","01301",15.2,"Solar","22B7","2022-07-13","2022-08-04",{"$f":"NETWORKDAYS(I1140,J1140,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1140,O1140,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-08-23",null,null,null,null,null,null,null,null,null," ",null,null,"2022-11-22","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Lanesborough","ESMAEX-01480","01224",17.600000000000001,"Solar & Battery","19A5","2022-08-17","2022-09-07",{"$f":"NETWORKDAYS(I1141,J1141,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1141,O1141,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-09-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-07","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Southampton","ESMAEX-01350","01073",17.68,"Solar & Battery","15A1","2022-07-06","2022-08-04",{"$f":"NETWORKDAYS(I1142,J1142,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1142,O1142,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-08-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-05","Online",null,null,null,7.68,"15A GUNN"]
[null,"WMECO","Springfield","ESMAEX-01356","01107",2000,"Battery","21S10","2022-10-18","2022-12-05",{"$f":"NETWORKDAYS(I1143,J1143,MALegalHolidays)","v":35},null,35,null,null,{"$f":"NETWORKDAYS(N1143,O1143,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-26",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-08","Online",null,null,"2023 ASO Batch 1",0,"21S CLINTON"]
[null,"WMECO","Springfield","ESMAEX-01384","01109",1833.3,"Solar & Battery","20A33","2023-01-13","2023-02-02",{"$f":"NETWORKDAYS(I1144,J1144,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1144,O1144,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-17",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,"2023 ASO Batch 1",null,"20A BRECKWOOD"]
[null,"WMECO","Longmeadow","ESMAEX-01501","01106",15.2,"Solar & Battery","22H11","2022-08-23","2022-09-23",{"$f":"NETWORKDAYS(I1145,J1145,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1145,O1145,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Cheshire","ESMAEX-01421","01225",3800,"Solar & Battery","19A5","2022-08-15","2022-09-07",{"$f":"NETWORKDAYS(I1146,J1146,MALegalHolidays)","v":18},null,{"$f":"IF(K1146>0,K1146-L1146,\" \")","v":18},null,null,{"$f":"NETWORKDAYS(N1146,O1146,MALegalHolidays)","v":0},null,{"$f":"IF(P1146>0,P1146-Q1146,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1146>0,U1146-V1146,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1146>0,Z1146-AA1146,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1146>0,AE1146-AF1146,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1146>0,AJ1146-AK1146,\" \")","v":" "},"2024-12-13",null,null,null,null,null,null,null,null,null,{"$f":"IF(AU1146>0,AU1146-AV1146,\" \")","v":" "},null,null,null,"Compliances Documents",null,null,"2023 ASO Batch 1",3800,"19A DOREEN"]
[null,"WMECO","Southwick","ESMAEX-01444","01077",15.2,"Solar & Battery",null,"2022-08-08","2022-08-24",{"$f":"NETWORKDAYS(I1147,J1147,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1147,O1147,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-08-24",null,null,null,null,null,null,null,null,null," ",null,null,"2023-01-31","Online"]
[null,"WMECO","Granville","ESMAEX-01439","01034",3000,"Solar & Battery","29A5","2022-09-07","2022-09-13",{"$f":"NETWORKDAYS(I1148,J1148,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1148,O1148,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick","2023 ASO Batch 1",3000,"29A SOUTHWICK"]
[null,"WMECO","Amherst","ESMAEX-01445","01002",69.2,"Solar","17K4","2022-08-08","2022-08-16",{"$f":"NETWORKDAYS(I1149,J1149,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1149,O1149,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-09-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-14","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Ludlow","ESMAEX-01447","01056",20,"Solar",null,"2022-08-08","2022-12-16",{"$f":"NETWORKDAYS(I1150,J1150,MALegalHolidays)","v":95},null,95,null,null,{"$f":"NETWORKDAYS(N1150,O1150,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-01","Online"]
[null,"WMECO","Springfield","ESMAEX-01448","01109",1033.0999999999999,"Solar & Battery","20A14","2023-01-17","2023-02-02",{"$f":"NETWORKDAYS(I1151,J1151,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1151,O1151,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-19",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,"2023 ASO Batch 1",null,"20A BRECKWOOD"]
[null,"WMECO","Savoy","ESMAEX-02010","01256",15.2,"Solar & Battery","18K4","2023-01-12","2023-01-23",{"$f":"NETWORKDAYS(I1152,J1152,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1152,O1152,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-12","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Blandford","ESMAEX-01479","01008",4998,"Solar & Battery","19J5","2022-12-20","2022-12-29",{"$f":"NETWORKDAYS(I1153,J1153,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1153,O1153,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",4998,"19J BLANDFORD"]
[null,"WMECO","Pittsfield","ESMAEX-01489","01201",240,"Solar",null,"2023-01-12","2022-09-07",{"$f":"NETWORKDAYS(I1154,J1154,MALegalHolidays)","v":-92},null," ",null,null,{"$f":"NETWORKDAYS(N1154,O1154,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-01","Online"]
[null,"WMECO","Springfield","ESMAEX-01502","01108",3,"Solar & Battery","22H15","2022-08-23","2022-09-07",{"$f":"NETWORKDAYS(I1155,J1155,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1155,O1155,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-06",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-12","Online",null,null,null,14,"22H FRANCONIA"]
[null,"WMECO","Otis","ESMAEX-01512","01253",20,"Solar","19J4","2022-08-25","2022-09-07",{"$f":"NETWORKDAYS(I1156,J1156,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1156,O1156,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-12",null,null,null,null,null,null,null,null,null," ",null,null,"2026-01-21","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Shelburne Falls","ESMAEX-01514","01370",20,"Solar","22B5","2022-08-25","2022-09-15",{"$f":"NETWORKDAYS(I1157,J1157,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1157,O1157,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-25",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-22","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Hadley","ESMAEX-01515","01035",15.6,"Solar & Battery","18G5","2022-08-26","2022-09-07",{"$f":"NETWORKDAYS(I1158,J1158,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1158,O1158,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-04",null,null,null,null,null,null,null,null,null," ",null,null,"2023-02-08","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Amherst","ESMAEX-01522","01002",4990,"Battery","18G6","2022-08-29","2022-09-14",{"$f":"NETWORKDAYS(I1159,J1159,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1159,O1159,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study",null,null,null,4990,"18G PODICK"]
[null,"WMECO","Agawam","ESMAEX-01527","01001",960,"Solar","30A3","2022-09-19","2022-09-23",{"$f":"NETWORKDAYS(I1160,J1160,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1160,O1160,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-08",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-14","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Hatfield","ESMAEX-01533","01038",20,"Solar","18G6","2022-09-01","2022-09-13",{"$f":"NETWORKDAYS(I1161,J1161,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1161,O1161,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-04",null,null,null,null,null,null,null,null,null," ",null,null,"2022-12-21","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Sunderland","ESMAEX-01539","01375",10,"Solar & Battery","18G8","2022-09-02","2022-09-21",{"$f":"NETWORKDAYS(I1162,J1162,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1162,O1162,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-05",null,null,null,null,null,null,null,null,null," ",null,null,"2023-03-06","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-01563","01109",60,"Solar","20A33","2022-09-11","2022-09-23",{"$f":"NETWORKDAYS(I1163,J1163,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1163,O1163,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-22",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Southwick","ESMAEX-01581","01077",4999,"Battery","29A3","2023-03-20","2023-04-19",{"$f":"NETWORKDAYS(I1164,J1164,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1164,O1164,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Southwick","ESMAEX-01582","01077",6700,"Solar & Battery","29A3","2023-03-20","2023-03-22",{"$f":"NETWORKDAYS(I1165,J1165,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1165,O1165,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Amherst","ESMAEX-01586","01002",3830,"Solar & Battery","17K8","2022-09-14","2022-09-15",{"$f":"NETWORKDAYS(I1166,J1166,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1166,O1166,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-11",null,null,null,null,null,null,null,null,null," ",null,null,"2026-01-29","Online",null,null,null,3830,"17K AMHERST"]
[null,"WMECO","Lanesborough","ESMAEX-01590","01237",16.399999999999999,"Solar","15E1","2022-09-14","2022-09-23",{"$f":"NETWORKDAYS(I1167,J1167,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1167,O1167,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-09-27",null,null,null,null,null,null,null,null,null," ",null,null,"2023-07-06","Online",null,null,null,null,"PARTRIDGE"]
[null,"WMECO","Buckland","ESMAEX-01594","01338",250,"Solar","29R1","2022-10-07","2022-10-13",{"$f":"NETWORKDAYS(I1168,J1168,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1168,O1168,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-02",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-02","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Worthington","ESMAEX-01622","01098",3000,"Solar & Battery","18K3","2023-05-10","2023-05-24",{"$f":"NETWORKDAYS(I1169,J1169,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1169,O1169,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,3000,"18K PLAINFIELD"]
[null,"WMECO","Blandford","ESMAEX-01635","01008",2000,"Solar","19J2","2022-11-29","2022-12-05",{"$f":"NETWORKDAYS(I1170,J1170,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1170,O1170,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",2000,"19J BLANDFORD"]
[null,"WMECO","Cummington","ESMAEX-01631","01026",5,"Solar","18C1","2022-09-26","2022-10-05",{"$f":"NETWORKDAYS(I1171,J1171,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1171,O1171,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-02-24","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Hatfield","ESMAEX-01733","01038",7.6,"Solar & Battery","18G5","2022-10-27","2023-01-11",{"$f":"NETWORKDAYS(I1172,J1172,MALegalHolidays)","v":55},null,55,null,null,{"$f":"NETWORKDAYS(N1172,O1172,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-18",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-15","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Longmeadow","ESMAEX-01682","01106",10.752000000000001,"Solar & Battery","22H11","2022-10-13","2022-11-21",{"$f":"NETWORKDAYS(I1173,J1173,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1173,O1173,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-15",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-27","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Richmond","ESMAEX-01647","01254",22.8,"Solar & Battery","30B7","2022-09-30","2022-12-01",{"$f":"NETWORKDAYS(I1174,J1174,MALegalHolidays)","v":45},null,45,null,null,{"$f":"NETWORKDAYS(N1174,O1174,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-07",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-11","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Springfield","ESMAEX-01645","01109",12.6,"Solar & Battery","5J17","2022-09-29","2022-10-21",{"$f":"NETWORKDAYS(I1175,J1175,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1175,O1175,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-21",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-21","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Amherst","ESMAEX-01862","01002",60,"Solar","17K6","2022-11-29","2022-12-05",{"$f":"NETWORKDAYS(I1176,J1176,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1176,O1176,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-07",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-05","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Becket","ESMAEX-01852","01223",2490,"Solar","19J6","2022-11-28","2022-12-05",{"$f":"NETWORKDAYS(I1177,J1177,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1177,O1177,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",null,"19J BLANDFORD"]
[null,"WMECO","Ashfield","ESMAEX-01748","01330",10,"Solar","38A1","2022-11-01","2022-11-16",{"$f":"NETWORKDAYS(I1178,J1178,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1178,O1178,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-25","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Whately","ESMAEX-01677","01093",400,"Solar","18G8","2023-02-16","2023-02-24",{"$f":"NETWORKDAYS(I1179,J1179,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1179,O1179,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-10",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Southwick","ESMAEX-01715","01077",10,"Solar & Battery","29A5","2022-10-25","2022-10-28",{"$f":"NETWORKDAYS(I1180,J1180,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1180,O1180,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-10-31",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-06","Online",null,"Southwick",null,7,"29A SOUTHWICK"]
[null,"WMECO","Ludlow","ESMAEX-01813","01056",17.600000000000001,"Solar & Battery","19S1","2022-11-15","2023-01-23",{"$f":"NETWORKDAYS(I1181,J1181,MALegalHolidays)","v":50},null,50,null,null,{"$f":"NETWORKDAYS(N1181,O1181,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-31",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-30","Online",null,null,null,17.600000000000001,"19S LUDLOW"]
[null,"WMECO","West Springfield","ESMAEX-01719","01089",225,"Solar","21N5","2022-10-25","2022-11-07",{"$f":"NETWORKDAYS(I1182,J1182,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1182,O1182,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-24","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Granville","ESMAEX-01695","01034",17.100000000000001,"Solar","29A5","2022-10-19","2022-10-28",{"$f":"NETWORKDAYS(I1183,J1183,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1183,O1183,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-20","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Lanesborough","ESMAEX-01708","01237",3800,"Solar & Battery","30B5","2023-01-10","2024-07-29",{"$f":"NETWORKDAYS(I1184,J1184,MALegalHolidays)","v":405},null,405,null,null,{"$f":"NETWORKDAYS(N1184,O1184,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-05",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,2800,"30B OSWALD"]
[null,"WMECO","Conway","ESMAEX-01702","01341",12.6,"Solar","38A1","2022-10-21","2022-11-07",{"$f":"NETWORKDAYS(I1185,J1185,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1185,O1185,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-12",null,null,null,null,null,null,null,null,null," ",null,null,"2023-02-09","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Blandford","ESMAEX-01704","01008",4998,"Solar & Battery","19J2","2022-12-20","2022-12-29",{"$f":"NETWORKDAYS(I1186,J1186,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1186,O1186,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford","2023 ASO Batch 1",4998,"19J BLANDFORD"]
[null,"WMECO","Easthampton","ESMAEX-01713","01027",15.2,"Solar & Battery","15A2","2022-10-25","2022-11-07",{"$f":"NETWORKDAYS(I1187,J1187,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1187,O1187,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-12",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-13","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Amherst","ESMAEX-01764","01002",10,"Battery","17K8","2022-11-03","2022-12-07",{"$f":"NETWORKDAYS(I1188,J1188,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1188,O1188,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-18",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-07","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Southwick","ESMAEX-01830","01077",15.93,"Solar","29A1","2022-11-17","2022-12-05",{"$f":"NETWORKDAYS(I1189,J1189,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1189,O1189,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-05",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-29","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Southwick","ESMAEX-01769","01077",10,"Solar & Battery","29A5","2022-11-04","2022-11-16",{"$f":"NETWORKDAYS(I1190,J1190,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1190,O1190,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-16",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-06","Online",null,"Southwick",null,7,"29A SOUTHWICK"]
[null,"WMECO","Hadley","ESMAEX-01754","01035",10,"Solar","18G4","2022-11-02","2022-11-16",{"$f":"NETWORKDAYS(I1191,J1191,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1191,O1191,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-14",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-06","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Washington","ESMAEX-01766","01223",5,"Solar & Battery","19J6","2022-11-04","2022-11-16",{"$f":"NETWORKDAYS(I1192,J1192,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1192,O1192,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-18",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-12","Online"]
[null,"WMECO","Bernardston","ESMAEX-01755","01337",4700,"Solar & Battery","21C1","2023-09-21","2023-09-29",{"$f":"NETWORKDAYS(I1193,J1193,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1193,O1193,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague",null,4700,"21C MONTAGUE"]
[null,"WMECO","Feeding Hills","ESMAEX-01802","01030",10,"Solar","30A1","2022-11-11","2022-11-16",{"$f":"NETWORKDAYS(I1194,J1194,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1194,O1194,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-11-21",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-07","Online",null,null,null,7,"30A SILVER"]
[null,"WMECO","Ludlow","ESMAEX-01826","01056",14.7,"Solar","27A5","2022-11-17","2022-12-21",{"$f":"NETWORKDAYS(I1195,J1195,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1195,O1195,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2022-12-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-04-06","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Conway","ESMAEX-01828","01341",3984,"Solar & Battery","22B1","2023-01-25","2023-02-01",{"$f":"NETWORKDAYS(I1196,J1196,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1196,O1196,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,4200,"22B CUMBERLAND"]
[null,"WMECO","Whately","ESMAEX-01872","01093",20,"Solar","18G6","2022-11-30","2022-12-05",{"$f":"NETWORKDAYS(I1197,J1197,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1197,O1197,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-25",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-12","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-01869","01118",15.2,"Solar & Battery","20A32","2022-11-29","2022-12-14",{"$f":"NETWORKDAYS(I1198,J1198,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1198,O1198,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-01-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-04","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Whately","ESMAEX-02067","01093",5,"Battery","18G8","2023-01-25","2023-02-21",{"$f":"NETWORKDAYS(I1199,J1199,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1199,O1199,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-17","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Otis","ESMAEX-02145","01253",15.2,"Solar & Battery","19J4","2023-02-09","2023-02-24",{"$f":"NETWORKDAYS(I1200,J1200,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1200,O1200,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-23","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Ashfield","ESMAEX-02059","01330",20,"Solar","38A1","2023-01-23","2023-02-01",{"$f":"NETWORKDAYS(I1201,J1201,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1201,O1201,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-20",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-12","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Whately","ESMAEX-01991","01093",15.2,"Solar","18G6","2023-01-10","2023-01-23",{"$f":"NETWORKDAYS(I1202,J1202,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1202,O1202,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-15",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-08","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Ludlow","ESMAEX-01968","01056",240,"Solar",null,"2023-01-05","2023-02-01",{"$f":"NETWORKDAYS(I1203,J1203,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1203,O1203,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-03",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Longmeadow","ESMAEX-02008","01106",20,"Solar","22H13","2023-01-12","2023-02-01",{"$f":"NETWORKDAYS(I1204,J1204,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1204,O1204,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-15",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-23","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Feeding Hills","ESMAEX-02090","01030",10.62,"Solar & Battery","30A1","2023-01-30","2023-03-31",{"$f":"NETWORKDAYS(I1205,J1205,MALegalHolidays)","v":45},null,45,null,null,{"$f":"NETWORKDAYS(N1205,O1205,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-04-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-04","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Amherst","ESMAEX-02073","01002",15.2,"Solar","18G7","2023-01-25","2023-02-08",{"$f":"NETWORKDAYS(I1206,J1206,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1206,O1206,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-09",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-05","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Feeding Hills","ESMAEX-02040","01030",15.2,"Solar","16C17","2023-01-19","2023-02-01",{"$f":"NETWORKDAYS(I1207,J1207,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1207,O1207,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-04","Online",null,null,null,17.399999999999999,"16C AGAWAM"]
[null,"WMECO","Deerfield","ESMAEX-02052","01342",480,"Solar","22B3","2023-02-17","2023-03-03",{"$f":"NETWORKDAYS(I1208,J1208,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1208,O1208,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-03",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Longmeadow","ESMAEX-02128","01106",10,"Battery","22H13","2023-02-06","2023-02-24",{"$f":"NETWORKDAYS(I1209,J1209,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1209,O1209,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-01",null,null,null,null,null,null,null,null,null," ",null,null,"2024-01-25","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Agawam","ESMAEX-02138","01030",15.2,"Solar & Battery","16C17","2023-02-07","2023-02-17",{"$f":"NETWORKDAYS(I1210,J1210,MALegalHolidays)","v":9},null,{"$f":"IF(K1210>0,K1210-L1210,\" \")","v":9},null,null,{"$f":"NETWORKDAYS(N1210,O1210,MALegalHolidays)","v":0},null,{"$f":"IF(P1210>0,P1210-Q1210,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1210>0,U1210-V1210,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1210>0,Z1210-AA1210,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1210>0,AE1210-AF1210,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1210>0,AJ1210-AK1210,\" \")","v":" "},"2023-02-17",null,null,null,null,null,null,null,null,null,{"$f":"IF(AU1210>0,AU1210-AV1210,\" \")","v":" "},null,null,"2023-09-07","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Feeding Hills","ESMAEX-02074","01030",15.2,"Solar","30A1","2023-01-26","2023-02-08",{"$f":"NETWORKDAYS(I1211,J1211,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1211,O1211,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-08",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-11","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Longmeadow","ESMAEX-02093","01106",20.56,"Solar & Battery","22H13","2023-01-31","2023-02-10",{"$f":"NETWORKDAYS(I1212,J1212,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1212,O1212,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-15",null,null,null,null,null,null,null,null,null," ",null,null,"2023-07-07","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Pelham","ESMAEX-02103","01002",13.26,"Solar & Battery","17K2","2023-02-02","2023-03-31",{"$f":"NETWORKDAYS(I1213,J1213,MALegalHolidays)","v":42},null,42,null,null,{"$f":"NETWORKDAYS(N1213,O1213,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-04-13",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-07","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Colrain","ESMAEX-02141","01340",18.239999999999998,"Solar & Battery","29R2","2023-02-08","2023-02-14",{"$f":"NETWORKDAYS(I1214,J1214,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1214,O1214,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-02-27",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-08","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Agawam","ESMAEX-02252","01001",15.2,"Solar","30A5","2023-03-09","2023-03-22",{"$f":"NETWORKDAYS(I1215,J1215,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1215,O1215,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-14","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Springfield","ESMAEX-02230","01108",15.2,"Solar","22H15","2023-03-03","2023-03-08",{"$f":"NETWORKDAYS(I1216,J1216,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1216,O1216,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-24",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-23","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Longmeadow","ESMAEX-02189","01106",15.2,"Solar & Battery","22H13","2023-02-22","2023-03-03",{"$f":"NETWORKDAYS(I1217,J1217,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1217,O1217,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-17","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Southampton","ESMAEX-02171","01073",4980,"Solar & Battery","15A1","2023-03-27","2023-06-02",{"$f":"NETWORKDAYS(I1218,J1218,MALegalHolidays)","v":50},null,50,null,null,{"$f":"NETWORKDAYS(N1218,O1218,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Transmission",null,null,null,4980,"15A GUNN"]
[null,"WMECO","Lanesborough","ESMAEX-02210","01237",7.6,"Solar & Battery","15E1","2023-02-28","2023-03-03",{"$f":"NETWORKDAYS(I1219,J1219,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1219,O1219,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-21","Online",null,null,null,14]
[null,"WMECO","West Hatfield","ESMAEX-02405","01088",125,"Solar","18G5","2023-04-21","2023-04-28",{"$f":"NETWORKDAYS(I1220,J1220,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1220,O1220,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-31",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-23","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Blandford","ESMAEX-02238","01008",17.399999999999999,"Solar","29A5","2023-03-06","2023-03-17",{"$f":"NETWORKDAYS(I1221,J1221,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1221,O1221,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-17",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-23","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Lee","ESMAEX-02279","01238",20.736000000000001,"Solar","16B5","2023-03-17","2023-03-31",{"$f":"NETWORKDAYS(I1222,J1222,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1222,O1222,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-08","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Longmeadow","ESMAEX-02289","01106",15.2,"Solar & Battery","22H12","2023-03-21","2023-03-31",{"$f":"NETWORKDAYS(I1223,J1223,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1223,O1223,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-04-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-08","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Pittsfield","ESMAEX-02258","01201",12.98,"Solar","19A7","2023-03-10","2023-03-22",{"$f":"NETWORKDAYS(I1224,J1224,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1224,O1224,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-07-20","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Amherst","ESMAEX-02259","01002",84.671999999999997,"Solar",null,"2023-03-10","2024-03-27",{"$f":"NETWORKDAYS(I1225,J1225,MALegalHolidays)","v":274},null,274,null,null,{"$f":"NETWORKDAYS(N1225,O1225,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-07",null,null,null,null,null,null,null,null,null," ",null,null,"2025-05-09","Online"]
[null,"WMECO","Springfield","ESMAEX-02264","01108",8.26,"Solar & Battery","21S12","2023-03-14","2023-03-20",{"$f":"NETWORKDAYS(I1226,J1226,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1226,O1226,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-03-21",null,null,null,null,null,null,null,null,null," ",null,null,"2023-05-03","Online",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Hadley","ESMAEX-02288","01035",17.600000000000001,"Solar","18G4","2023-03-20","2023-03-31",{"$f":"NETWORKDAYS(I1227,J1227,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1227,O1227,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-12",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-10","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Richmond","ESMAEX-02312","01254",15.2,"Solar & Battery","30B2","2023-03-27","2023-04-26",{"$f":"NETWORKDAYS(I1228,J1228,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1228,O1228,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-26","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Bernardston","ESMAEX-02295","01337",15.2,"Solar",null,"2023-03-22","2023-05-17",{"$f":"NETWORKDAYS(I1229,J1229,MALegalHolidays)","v":41},null,41,null,null,{"$f":"NETWORKDAYS(N1229,O1229,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-27",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-21","Online"]
[null,"WMECO","Cummington","ESMAEX-02311","01026",10,"Solar & Battery","18C1","2023-03-27","2023-05-01",{"$f":"NETWORKDAYS(I1230,J1230,MALegalHolidays)","v":26},null,26,null,null,{"$f":"NETWORKDAYS(N1230,O1230,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-06",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-04","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Southwick","ESMAEX-02314","01077",2000,"Solar","29A5","2023-07-27","2023-08-02",{"$f":"NETWORKDAYS(I1231,J1231,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1231,O1231,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick",null,2000,"29A SOUTHWICK"]
[null,"WMECO","Becket","ESMAEX-02317","01223",9.3000000000000007,"Solar","19J6","2023-03-28","2023-04-07",{"$f":"NETWORKDAYS(I1232,J1232,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1232,O1232,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-03","Online"]
[null,"WMECO","Springfield","ESMAEX-02322","01109",999,"Solar & Battery","20A21","2023-05-09","2023-06-09",{"$f":"NETWORKDAYS(I1233,J1233,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1233,O1233,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-18",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Amherst","ESMAEX-02326","01002",10,"Solar","19B16","2023-03-30","2023-04-12",{"$f":"NETWORKDAYS(I1234,J1234,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1234,O1234,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-16",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-21","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Pittsfield","ESMAEX-02362","01201",60,"Solar","19A7","2023-04-10","2023-04-26",{"$f":"NETWORKDAYS(I1235,J1235,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1235,O1235,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-02",null,null,null,null,null,null,null,null,null," ",null,null,"2024-01-18","Online",null,null,null,null,"DOREEN"]
[null,"WMECO","Hadley","ESMAEX-02350","01035",15.2,"Solar","19B15","2023-04-06","2023-04-26",{"$f":"NETWORKDAYS(I1236,J1236,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1236,O1236,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-26",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-09","Online",null,null,null,15.2,"19B MIDWAY"]
[null,"WMECO","Southampton","ESMAEX-02348","01073",6,"Solar","15A1","2023-04-05","2023-04-26",{"$f":"NETWORKDAYS(I1237,J1237,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1237,O1237,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-26",null,null,null,null,null,null,null,null,null," ",null,null,"2023-06-26","Online",null,null,null,6,"15A GUNN"]
[null,"WMECO","Southampton","ESMAEX-02396","01073",6,"Solar","15A3","2023-04-20","2023-05-05",{"$f":"NETWORKDAYS(I1238,J1238,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1238,O1238,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-31",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-31","Online",null,null,null,6,"15A GUNN"]
[null,"WMECO","Peru","ESMAEX-02361","01235",10,"Battery",null,"2023-04-10","2023-05-17",{"$f":"NETWORKDAYS(I1239,J1239,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1239,O1239,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-26",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-07","Online"]
[null,"WMECO","Longmeadow","ESMAEX-02370","01106",15.2,"Solar & Battery","22H17","2023-04-11","2023-04-26",{"$f":"NETWORKDAYS(I1240,J1240,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1240,O1240,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-04-28",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-21","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Richmond","ESMAEX-02475","01254",50,"Solar","30B7","2023-05-15","2023-05-24",{"$f":"NETWORKDAYS(I1241,J1241,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1241,O1241,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-27",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-31","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Greenfield","ESMAEX-02459","01301",25,"Solar","22B7","2023-05-08","2023-05-12",{"$f":"NETWORKDAYS(I1242,J1242,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1242,O1242,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-23",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-27","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Springfield","ESMAEX-02394","01105",100,"Solar","5J16","2023-04-19","2023-06-08",{"$f":"NETWORKDAYS(I1243,J1243,MALegalHolidays)","v":37},null,37,null,null,{"$f":"NETWORKDAYS(N1243,O1243,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-08",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-29","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Otis","ESMAEX-02390","01253",20,"Solar","19J4","2023-04-19","2023-05-15",{"$f":"NETWORKDAYS(I1244,J1244,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1244,O1244,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-26",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-09","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Southwick","ESMAEX-02540","01077",16.52,"Solar","29A5","2023-05-30","2023-07-07",{"$f":"NETWORKDAYS(I1245,J1245,MALegalHolidays)","v":29},null,29,null,null,{"$f":"NETWORKDAYS(N1245,O1245,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-07",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-23","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Southampton","ESMAEX-02541","01073",15.2,"Solar & Battery","15A1","2023-05-31","2023-06-16",{"$f":"NETWORKDAYS(I1246,J1246,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1246,O1246,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-03","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Worthington","ESMAEX-02438","01098",2000,"Solar & Battery","18K3","2023-05-26","2023-06-02",{"$f":"NETWORKDAYS(I1247,J1247,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1247,O1247,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,2000,"18K PLAINFIELD"]
[null,"WMECO","Longmeadow","ESMAEX-02482","01106",21,"Solar","22H11","2023-05-16","2023-05-31",{"$f":"NETWORKDAYS(I1248,J1248,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1248,O1248,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-31",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-12","Online",null,null,null,null,"FRANCONIA"]
[null,"WMECO","Amherst","ESMAEX-02471","01002",7.8,"Solar & Battery","17K2","2023-05-11","2023-05-17",{"$f":"NETWORKDAYS(I1249,J1249,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1249,O1249,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-21","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Southampton","ESMAEX-02462","01073",10,"Solar","15A3","2023-05-08","2023-05-17",{"$f":"NETWORKDAYS(I1250,J1250,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1250,O1250,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-05","Online",null,null,null,10,"15A GUNN"]
[null,"WMECO","Longmeadow","ESMAEX-02470","01106",15.2,"Solar & Battery","22H13","2023-05-10","2023-05-24",{"$f":"NETWORKDAYS(I1251,J1251,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1251,O1251,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-05-25",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Sunderland","ESMAEX-02492","01375",25,"Solar","18G8","2023-05-18","2023-05-24",{"$f":"NETWORKDAYS(I1252,J1252,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1252,O1252,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-02",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-02","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Montague","ESMAEX-02511","01376",4000,"Battery","21C5","2023-05-23","2023-06-06",{"$f":"NETWORKDAYS(I1253,J1253,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1253,O1253,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague",null,4000,"21C MONTAGUE"]
[null,"WMECO","Amherst","ESMAEX-02473","01002",15.2,"Solar & Battery","19B16","2023-05-11","2023-07-06",{"$f":"NETWORKDAYS(I1254,J1254,MALegalHolidays)","v":41},null,41,null,null,{"$f":"NETWORKDAYS(N1254,O1254,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-13",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-17","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Feeding Hills","ESMAEX-02493","01030",15.2,"Solar","30A6","2023-05-18","2023-06-02",{"$f":"NETWORKDAYS(I1255,J1255,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1255,O1255,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-05",null,null,null,null,null,null,null,null,null," ",null,null,"2023-08-10","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Worthington","ESMAEX-02520","01098",23.6,"Solar & Battery","18C2","2023-05-25","2023-06-09",{"$f":"NETWORKDAYS(I1256,J1256,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1256,O1256,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-22",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-17","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Becket","ESMAEX-02484","01223",15.2,"Solar & Battery","19J6","2023-05-16","2023-05-24",{"$f":"NETWORKDAYS(I1257,J1257,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1257,O1257,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-27",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-09","Online"]
[null,"WMECO","Deerfield","ESMAEX-02485","01342",15.2,"Solar & Battery","22B1","2023-05-16","2023-06-06",{"$f":"NETWORKDAYS(I1258,J1258,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1258,O1258,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-06",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-12","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Becket","ESMAEX-02501","01223",4999,"Solar & Battery","16B1","2023-05-22","2023-05-31",{"$f":"NETWORKDAYS(I1259,J1259,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1259,O1259,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-04",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,4999,"16B PLEASANT"]
[null,"WMECO","Southwick","ESMAEX-02529","01077",15.2,"Solar","29A1","2023-05-26","2023-06-19",{"$f":"NETWORKDAYS(I1260,J1260,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1260,O1260,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-06-19",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-30","Online",null,null,null,null,"29A SOUTHWICK"]
[null,"WMECO","Springfield","ESMAEX-02508","01109",14,"Battery","5J14","2023-05-22","2023-07-31",{"$f":"NETWORKDAYS(I1261,J1261,MALegalHolidays)","v":51},null,51,null,null,{"$f":"NETWORKDAYS(N1261,O1261,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-10",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-15","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Blandford","ESMAEX-02512","01008",2656,"Solar & Battery","19J2","2023-07-05","2023-07-13",{"$f":"NETWORKDAYS(I1262,J1262,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1262,O1262,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford",null,2490,"19J BLANDFORD"]
[null,"WMECO","Sunderland","ESMAEX-02515","01375",15.2,"Solar & Battery","18G3","2023-05-24","2023-06-09",{"$f":"NETWORKDAYS(I1263,J1263,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1263,O1263,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-07",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-23","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Montague","ESMAEX-02552","01376",4999,"Battery","21C2","2023-07-20","2023-08-03",{"$f":"NETWORKDAYS(I1264,J1264,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1264,O1264,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","Feeding Hills","ESMAEX-02604","01030",15.2,"Solar","16C17","2023-06-22","2023-07-07",{"$f":"NETWORKDAYS(I1265,J1265,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1265,O1265,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-07",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-17","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","West Hatfield","ESMAEX-02557","01088",15.2,"Solar","18G5","2023-06-06","2023-06-27",{"$f":"NETWORKDAYS(I1266,J1266,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1266,O1266,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-01-05","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Russell","ESMAEX-02599","01071",5,"Battery","19J2","2023-06-21","2023-07-07",{"$f":"NETWORKDAYS(I1267,J1267,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1267,O1267,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-07","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Agawam","ESMAEX-02606","01001",996,"Solar","30A3","2023-08-15","2023-08-17",{"$f":"NETWORKDAYS(I1268,J1268,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1268,O1268,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"30A SILVER"]
[null,"WMECO","Hinsdale","ESMAEX-02613","01235",19,"Solar","18C2","2023-06-23","2023-07-06",{"$f":"NETWORKDAYS(I1269,J1269,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1269,O1269,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-02",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-12","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","South Deerfield","ESMAEX-02623","01373",20,"Solar","22B3","2023-06-27","2023-07-06",{"$f":"NETWORKDAYS(I1270,J1270,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1270,O1270,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-14",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-18","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Springfield","ESMAEX-02625","01104",6,"Solar","5J15","2023-06-27","2023-07-06",{"$f":"NETWORKDAYS(I1271,J1271,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1271,O1271,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-07-07",null,null,null,null,null,null,null,null,null," ",null,null,"2023-09-26","Online",null,null,null,6,"5J EAST SPRINGFIELD"]
[null,"WMECO","Tolland","ESMAEX-02715","01034",6,"Solar & Battery","19J4","2023-07-26","2023-08-03",{"$f":"NETWORKDAYS(I1272,J1272,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1272,O1272,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-24",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-25","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Amherst","ESMAEX-02641","01002",18.047999999999998,"Solar","17K8","2023-07-06","2023-08-30",{"$f":"NETWORKDAYS(I1273,J1273,MALegalHolidays)","v":40},null,40,null,null,{"$f":"NETWORKDAYS(N1273,O1273,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-03",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-13","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Lee","ESMAEX-02695","01238",110,"Solar",null,"2023-07-20","2023-08-01",{"$f":"NETWORKDAYS(I1274,J1274,MALegalHolidays)","v":9},null,{"$f":"IF(K1274>0,K1274-L1274,\" \")","v":9},null,null,{"$f":"NETWORKDAYS(N1274,O1274,MALegalHolidays)","v":0},null,{"$f":"IF(P1274>0,P1274-Q1274,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1274>0,U1274-V1274,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1274>0,Z1274-AA1274,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1274>0,AE1274-AF1274,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1274>0,AJ1274-AK1274,\" \")","v":" "},"2023-08-02",null,null,null,null,null,null,null,null,null,{"$f":"IF(AU1274>0,AU1274-AV1274,\" \")","v":" "},null,null,"2024-06-20","Permission to Operate"]
[null,"WMECO","Southwick","ESMAEX-02662","01077",4998,"Solar & Battery","29A1","2023-08-08","2023-08-09",{"$f":"NETWORKDAYS(I1275,J1275,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1275,O1275,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study ",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Middlefield","ESMAEX-02696","01243",17.28,"Solar","18C2","2023-07-21","2023-08-08",{"$f":"NETWORKDAYS(I1276,J1276,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1276,O1276,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-08",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-22","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Pittsfield","ESMAEX-02692","01201",22.8,"Solar & Battery","30B4","2023-07-19","2023-08-03",{"$f":"NETWORKDAYS(I1277,J1277,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1277,O1277,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-06",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-04","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Springfield","ESMAEX-02764","01104",15.2,"Solar","5J10","2023-08-07","2023-08-11",{"$f":"NETWORKDAYS(I1278,J1278,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1278,O1278,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-28",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-23","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Easthampton","ESMAEX-02682","01027",15.2,"Solar & Battery","15A5","2023-07-18","2023-12-15",{"$f":"NETWORKDAYS(I1279,J1279,MALegalHolidays)","v":109},null,109,null,null,{"$f":"NETWORKDAYS(N1279,O1279,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-29",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-15","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Leverett","ESMAEX-02685","01054",15.2,"Solar & Battery","21C7","2023-07-18","2023-09-06",{"$f":"NETWORKDAYS(I1280,J1280,MALegalHolidays)","v":37},null,37,null,null,{"$f":"NETWORKDAYS(N1280,O1280,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-25",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-18","Online",null,"Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","West Springfield","ESMAEX-02702","01089",11.21,"Solar & Battery","21N4","2023-07-21","2023-08-07",{"$f":"NETWORKDAYS(I1281,J1281,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1281,O1281,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-07",null,null,null,null,null,null,null,null,null," ",null,null,"2023-10-12","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Middlefield","ESMAEX-02742","01243",10,"Battery","18C2","2023-08-01","2023-09-05",{"$f":"NETWORKDAYS(I1282,J1282,MALegalHolidays)","v":26},null,26,null,null,{"$f":"NETWORKDAYS(N1282,O1282,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-02",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-01","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Southampton","ESMAEX-02710","01073",15.2,"Solar & Battery",null,"2023-07-25","2023-08-03",{"$f":"NETWORKDAYS(I1283,J1283,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1283,O1283,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-02","Online"]
[null,"WMECO","Amherst","ESMAEX-02721","01002",20,"Solar","17K2","2023-07-28","2023-08-11",{"$f":"NETWORKDAYS(I1284,J1284,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1284,O1284,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-22",null,null,null,null,null,null,null,null,null," ",null,null,"2023-11-13","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Pittsfield","ESMAEX-02741","01201",120,"Solar","30B4","2023-10-19","2023-11-06",{"$f":"NETWORKDAYS(I1285,J1285,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1285,O1285,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-14","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Leverett","ESMAEX-02743","01054",15.2,"Solar & Battery","18G7","2023-08-01","2023-08-15",{"$f":"NETWORKDAYS(I1286,J1286,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1286,O1286,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-18",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-01","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Richmond","ESMAEX-02753","01254",24.4,"Solar","30B7","2023-08-04","2023-08-11",{"$f":"NETWORKDAYS(I1287,J1287,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1287,O1287,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-15",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-09","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Agawam","ESMAEX-02765","01001",200,"Solar","16C16","2023-08-29","2023-08-11",{"$f":"NETWORKDAYS(I1288,J1288,MALegalHolidays)","v":-13},null," ",null,null,{"$f":"NETWORKDAYS(N1288,O1288,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-02",null,null,null,null,null,null,null,null,null," ",null,null,"2025-11-24","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Easthampton","ESMAEX-02766","01027",10,"Solar","15A3","2023-08-07","2023-08-11",{"$f":"NETWORKDAYS(I1289,J1289,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1289,O1289,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2023-12-18","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Becket","ESMAEX-02759","01223",13.12,"Solar & Battery","19J6","2023-08-04","2023-08-30",{"$f":"NETWORKDAYS(I1290,J1290,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1290,O1290,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-02",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-02","Online"]
[null,"WMECO","Southampton","ESMAEX-02782","01073",15.2,"Solar & Battery","15A1","2023-08-09","2023-08-17",{"$f":"NETWORKDAYS(I1291,J1291,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1291,O1291,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-09-18",null,null,null,null,null,null,null,null,null," ",null,null,"2024-01-03","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Hinsdale","ESMAEX-02797","01235",4950,"Solar & Battery","18C2","2023-12-07","2023-12-12",{"$f":"NETWORKDAYS(I1292,J1292,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1292,O1292,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Berkshire","Berkshire",null,null,"18C BERKSHIRE"]
[null,"WMECO","Plainfield","ESMAEX-02897","01070",5,"Solar & Battery","18K4","2023-09-07","2023-09-13",{"$f":"NETWORKDAYS(I1293,J1293,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1293,O1293,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-18",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-07","Online",null,"Dalton-Hinsdale",null,null,"18K PLAINFIELD"]
[null,"WMECO","Plainfield","ESMAEX-02846","01075",4980,"Solar & Battery","18K3","2023-09-28","2023-11-06",{"$f":"NETWORKDAYS(I1294,J1294,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1294,O1294,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,4980,"18K PLAINFIELD"]
[null,"WMECO","Lanesborough","ESMAEX-02849","01237",4980,"Solar & Battery","15E1","2023-09-28","2023-11-06",{"$f":"NETWORKDAYS(I1295,J1295,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1295,O1295,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"15E PARTRIDGE"]
[null,"WMECO","Agawam","ESMAEX-02855","01001",16,"Solar","30A3","2023-08-23","2023-08-30",{"$f":"NETWORKDAYS(I1296,J1296,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1296,O1296,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-08-31",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-01","Online",null,null,null,16,"SILVER"]
[null,"WMECO","Indian Orchard","ESMAEX-02866","01151",6,"Solar","27A13","2023-08-25","2023-08-30",{"$f":"NETWORKDAYS(I1297,J1297,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1297,O1297,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-03",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-18","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Northfield","ESMAEX-03085","01360",10,"Solar","21B8","2023-10-25","2023-11-06",{"$f":"NETWORKDAYS(I1298,J1298,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1298,O1298,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-04",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-14","Online",null,"Gill-Montague",null,null,"21B FRENCH KING"]
[null,"WMECO","Russell","ESMAEX-02942","01071",25,"Solar","19J2","2023-09-21","2023-10-04",{"$f":"NETWORKDAYS(I1299,J1299,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1299,O1299,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-29","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Easthampton","ESMAEX-02907","01027",21.25,"Solar & Battery","15A2","2023-09-11","2023-09-19",{"$f":"NETWORKDAYS(I1300,J1300,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1300,O1300,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-01",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-11","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Dalton","ESMAEX-02940","01226",22.8,"Solar","19A2","2023-09-21","2023-10-12",{"$f":"NETWORKDAYS(I1301,J1301,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1301,O1301,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-20","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Springfield","ESMAEX-02924","01108",10,"Battery","22H15","2023-09-15","2023-10-12",{"$f":"NETWORKDAYS(I1302,J1302,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1302,O1302,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-21","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Tyringham","ESMAEX-02990","01264",15.2,"Solar & Battery",null,"2023-09-29","2023-10-05",{"$f":"NETWORKDAYS(I1303,J1303,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1303,O1303,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-02","Online"]
[null,"WMECO","Dalton","ESMAEX-03002","01226",15.2,"Solar","18C1","2023-10-02","2023-10-12",{"$f":"NETWORKDAYS(I1304,J1304,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1304,O1304,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-19","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Richmond","ESMAEX-03008","01254",15.2,"Solar","30B2","2023-10-03","2023-10-12",{"$f":"NETWORKDAYS(I1305,J1305,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1305,O1305,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-10-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-04-16","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Hatfield","ESMAEX-03011","01038",1992,"Solar & Battery","18G6","2023-11-22","2023-11-29",{"$f":"NETWORKDAYS(I1306,J1306,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1306,O1306,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study",null,null,null,null,"18G PODICK"]
[null,"WMECO","Ludlow","ESMAEX-03039","01056",20,"Solar","19S3","2023-10-12","2023-11-06",{"$f":"NETWORKDAYS(I1307,J1307,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1307,O1307,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-06",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-13","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Pittsfield","ESMAEX-03068","01201",30,"Solar","30B2","2023-10-19","2024-09-16",{"$f":"NETWORKDAYS(I1308,J1308,MALegalHolidays)","v":238},null,238,null,null,{"$f":"NETWORKDAYS(N1308,O1308,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-08",null,null,null,null,null,null,null,null,null," ",null,null,"2025-11-20","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Springfield","ESMAEX-03047","01107",6,"Solar","21S6","2023-10-13","2023-10-25",{"$f":"NETWORKDAYS(I1309,J1309,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1309,O1309,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-06",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-07","Online",null,null,null,6,"21S CLINTON"]
[null,"WMECO","Ludlow","ESMAEX-03087","01056",17.28,"Solar","19S1","2023-10-25","2023-11-06",{"$f":"NETWORKDAYS(I1310,J1310,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1310,O1310,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-09",null,null,null,null,null,null,null,null,null," ",null,null,"2024-02-08","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Hadley","ESMAEX-03121","01035",16,"Solar & Battery","19B15","2023-11-06","2023-12-07",{"$f":"NETWORKDAYS(I1311,J1311,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1311,O1311,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-29",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-05","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Dalton","ESMAEX-03120","01226",15.2,"Solar & Battery",null,"2023-11-06","2023-11-16",{"$f":"NETWORKDAYS(I1312,J1312,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1312,O1312,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-11-22",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-21","Online"]
[null,"WMECO","Agawam","ESMAEX-03118","01001",14.79,"Solar","30A1","2023-11-03","2023-11-16",{"$f":"NETWORKDAYS(I1313,J1313,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1313,O1313,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-08",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-20","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Amherst","ESMAEX-03125","01002",15,"Battery",null,"2023-11-07","2024-02-27",{"$f":"NETWORKDAYS(I1314,J1314,MALegalHolidays)","v":81},null,81,null,null,{"$f":"NETWORKDAYS(N1314,O1314,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-22","Online"]
[null,"WMECO","Springfield","ESMAEX-03156","01118",7.6,"Solar & Battery","20A32","2023-11-15","2023-11-20",{"$f":"NETWORKDAYS(I1315,J1315,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1315,O1315,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-03-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-22","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Hatfield","ESMAEX-03241","01088",20,"Solar & Battery","18G5","2023-12-06","2023-12-28",{"$f":"NETWORKDAYS(I1316,J1316,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1316,O1316,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-01",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-11","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Westhampton","ESMAEX-03179","01027",15.2,"Solar","15A3","2023-11-20","2023-11-29",{"$f":"NETWORKDAYS(I1317,J1317,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1317,O1317,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-12","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Tolland","ESMAEX-03176","01034",2988,"Solar & Battery","19J4","2023-11-20","2023-12-01",{"$f":"NETWORKDAYS(I1318,J1318,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1318,O1318,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,"Blandford",null,2988,"19J BLANDFORD"]
[null,"WMECO","Easthampton","ESMAEX-03184","01027",100,"Solar","15A2","2023-11-21","2023-11-22",{"$f":"NETWORKDAYS(I1319,J1319,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1319,O1319,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-08",null,null,null,null,null,null,null,null,null," ",null,null,"2024-01-24","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Plainfield","ESMAEX-03192","01070",3820,"Solar & Battery","18K3","2023-11-22","2023-11-29",{"$f":"NETWORKDAYS(I1320,J1320,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1320,O1320,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,"Plainfield",null,3820,"18K PLAINFIELD"]
[null,"WMECO","Hadley","ESMAEX-03228","01035",499,"Solar","18G6","2024-02-08","2024-02-22",{"$f":"NETWORKDAYS(I1321,J1321,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1321,O1321,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-24",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,499,"18G PODICK"]
[null,"WMECO","Hadley","ESMAEX-03229","01035",499,"Solar","18G5","2024-02-08","2024-02-22",{"$f":"NETWORKDAYS(I1322,J1322,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1322,O1322,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-02",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,499,"18G PODICK"]
[null,"WMECO","Whately","ESMAEX-03396","01093",84.6,"Solar & Battery","18G8","2024-01-30","2024-02-22",{"$f":"NETWORKDAYS(I1323,J1323,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1323,O1323,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-16",null,null,null,null,null,null,null,null,null," ",null,null,null,"Meter Review Rejected - Customer Action",null,null,null,null,"18G PODICK"]
[null,"WMECO","Easthampton","ESMAEX-03234","01027",15.2,"Solar","15A3","2023-12-06","2023-12-22",{"$f":"NETWORKDAYS(I1324,J1324,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1324,O1324,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2023-12-29",null,null,null,null,null,null,null,null,null," ",null,null,"2024-06-18","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Easthampton","ESMAEX-03323","01027",15.36,"Solar & Battery","15A3","2024-01-03","2024-01-17",{"$f":"NETWORKDAYS(I1325,J1325,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1325,O1325,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-07-16","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Ashfield","ESMAEX-03516","01330",10,"Solar & Battery","38A1","2024-03-08","2024-03-19",{"$f":"NETWORKDAYS(I1326,J1326,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1326,O1326,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-26",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-06","Online",null,null,null,10,"38A ASHFIELD"]
[null,"WMECO","Richmond","ESMAEX-03326","01254",15.36,"Solar & Battery","30B2","2024-01-03","2024-01-17",{"$f":"NETWORKDAYS(I1327,J1327,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1327,O1327,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-25","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Hadley","ESMAEX-03306","01035",10,"Solar","18G4","2023-12-21","2024-01-04",{"$f":"NETWORKDAYS(I1328,J1328,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1328,O1328,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-07-23","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Ludlow","ESMAEX-03290","01056",7.6,"Battery","27A4","2023-12-19","2024-01-17",{"$f":"NETWORKDAYS(I1329,J1329,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1329,O1329,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-15",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-19","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Easthampton","ESMAEX-03304","01027",18,"Solar","15A5","2023-12-21","2023-12-28",{"$f":"NETWORKDAYS(I1330,J1330,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1330,O1330,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-19","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Easthampton","ESMAEX-03309","01027",22.8,"Solar","15A2","2023-12-21","2023-12-28",{"$f":"NETWORKDAYS(I1331,J1331,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1331,O1331,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-15","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Longmeadow","ESMAEX-03380","01106",15.2,"Solar & Battery",null,"2024-01-24","2024-02-01",{"$f":"NETWORKDAYS(I1332,J1332,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1332,O1332,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-26",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-28","Online"]
[null,"WMECO","Buckland","ESMAEX-03311","01338",37.5,"Solar","22B5","2023-12-22","2024-01-09",{"$f":"NETWORKDAYS(I1333,J1333,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1333,O1333,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-03-13",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-21","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","West Springfield","ESMAEX-03327","01089",15.2,"Solar","16C11","2024-01-03","2024-01-19",{"$f":"NETWORKDAYS(I1334,J1334,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1334,O1334,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-24",null,null,null,null,null,null,null,null,null," ",null,null,"2024-03-05","Online",null,null,null,15.2,"16C AGAWAM"]
[null,"WMECO","Westhampton","ESMAEX-03330","01027",15.2,"Solar & Battery","15A3","2024-01-04","2024-01-17",{"$f":"NETWORKDAYS(I1335,J1335,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1335,O1335,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-29","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Amherst","ESMAEX-03343","01002",16.5,"Solar","18G4","2024-01-09","2024-01-17",{"$f":"NETWORKDAYS(I1336,J1336,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1336,O1336,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-01-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-07-16","Online",null,null,null,15.95,"18G PODICK"]
[null,"WMECO","Conway","ESMAEX-03473","01341",20,"Battery","38A1","2024-02-22","2024-02-28",{"$f":"NETWORKDAYS(I1337,J1337,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1337,O1337,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-30","Online",null,null,null,10,"38A ASHFIELD"]
[null,"WMECO","Greenfield","ESMAEX-03367","01301",999,"Solar & Battery","22B2","2025-04-25","2025-05-08",{"$f":"NETWORKDAYS(I1338,J1338,MALegalHolidays)","v":10},null,{"$f":"IF(K1338>0,K1338-L1338,\" \")","v":10},null,null,{"$f":"NETWORKDAYS(N1338,O1338,MALegalHolidays)","v":0},null,{"$f":"IF(P1338>0,P1338-Q1338,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1338>0,U1338-V1338,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1338>0,Z1338-AA1338,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1338>0,AE1338-AF1338,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1338>0,AJ1338-AK1338,\" \")","v":" "},null,null,null,null,"Expedited",null,null,null,null,null,{"$f":"IF(AU1338>0,AU1338-AV1338,\" \")","v":" "},null,null,null,"Technical Review",null,null,null,999,"22B CUMBERLAND"]
[null,"WMECO","Westhampton","ESMAEX-03638","01027",17.600000000000001,"Solar","15A3","2024-04-08","2024-04-18",{"$f":"NETWORKDAYS(I1339,J1339,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1339,O1339,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-28",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-16","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Greenfield","ESMAEX-03857","01301",30,"Solar","22B4","2024-06-24","2024-07-25",{"$f":"NETWORKDAYS(I1340,J1340,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1340,O1340,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-03",null,null,null,null,null,null,null,null,null," ",null,null,"2025-03-20","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Hancock","ESMAEX-04296","01237",2000,"Solar","30B7","2024-11-22","2025-01-30",{"$f":"NETWORKDAYS(I1341,J1341,MALegalHolidays)","v":50},null,50,null,null,{"$f":"NETWORKDAYS(N1341,O1341,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-16",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,2000,"30B OSWALD"]
[null,"WMECO","Tolland","ESMAEX-03388","01034",9.9,"Solar & Battery","19J4","2024-01-26","2024-02-09",{"$f":"NETWORKDAYS(I1342,J1342,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1342,O1342,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-13",null,null,null,null,null,null,null,null,null," ",null,null,"2024-05-20","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Hancock","ESMAEX-04297","01237",2000,"Solar","30B7","2024-11-22","2025-01-30",{"$f":"NETWORKDAYS(I1343,J1343,MALegalHolidays)","v":50},null,50,null,null,{"$f":"NETWORKDAYS(N1343,O1343,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-16",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,2000,"30B OSWALD"]
[null,"WMECO","Pittsfield","ESMAEX-04298","01201",1000,"Solar","30B7","2024-11-22","2025-01-22",{"$f":"NETWORKDAYS(I1344,J1344,MALegalHolidays)","v":44},null,44,null,null,{"$f":"NETWORKDAYS(N1344,O1344,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-16",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,1000,"30B OSWALD"]
[null,"WMECO","South Deerfield","ESMAEX-03438","01373",10,"Battery","18G3","2024-02-14","2024-03-18",{"$f":"NETWORKDAYS(I1345,J1345,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1345,O1345,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-17","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Hadley","ESMAEX-03394","01035",15.2,"Solar","17K5","2024-01-29","2024-02-01",{"$f":"NETWORKDAYS(I1346,J1346,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1346,O1346,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-03-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-13","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Springfield","ESMAEX-03437","01118",5,"Solar & Battery","20A21","2024-02-14","2024-02-22",{"$f":"NETWORKDAYS(I1347,J1347,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1347,O1347,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-02-26",null,null,null,null,null,null,null,null,null," ",null,null,"2024-07-16","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Plainfield","ESMAEX-03434","01070",24,"Solar","18C1","2024-02-13","2024-04-23",{"$f":"NETWORKDAYS(I1348,J1348,MALegalHolidays)","v":51},null,51,null,null,{"$f":"NETWORKDAYS(N1348,O1348,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-04",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-06","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Turners Falls","ESMAEX-03587","01376",40,"Solar","21C6","2024-03-28","2024-05-09",{"$f":"NETWORKDAYS(I1349,J1349,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1349,O1349,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-11",null,null,null,null,null,null,null,null,null," ",null,null,"2025-12-10","Online",null,"Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","Agawam","ESMAEX-03455","01001",1500,"Solar","30A3","2024-05-06","2024-06-06",{"$f":"NETWORKDAYS(I1350,J1350,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1350,O1350,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliance Documents",null,null,null,null,"30A SILVER"]
[null,"WMECO","West Springfield","ESMAEX-03502","01089",250,"Solar","21N8","2024-03-01","2024-04-03",{"$f":"NETWORKDAYS(I1351,J1351,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1351,O1351,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-06-24",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-05","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Springfield","ESMAEX-03541","01103",700,"Fuel Cell","8C13","2024-03-19","2024-04-03",{"$f":"NETWORKDAYS(I1352,J1352,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1352,O1352,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-03",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"8C WEST SPRINGFIELD"]
[null,"WMECO","Erving","ESMAEX-03495","01360",4980,"Solar & Battery","21B8","2024-02-29","2024-03-18",{"$f":"NETWORKDAYS(I1353,J1353,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1353,O1353,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Whatley-Deerfield","Gill-Montague",null,4980,"21B FRENCH KING"]
[null,"WMECO","Worthington","ESMAEX-03482","01098",15.2,"Solar","18C2","2024-02-27","2024-03-06",{"$f":"NETWORKDAYS(I1354,J1354,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1354,O1354,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-24","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Lenox Dale","ESMAEX-03488","01242",13.6,"Solar & Battery","17G3","2024-02-28","2024-03-06",{"$f":"NETWORKDAYS(I1355,J1355,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1355,O1355,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-03-06",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-31","Online",null,null,null,null,"17G WOODLAND RD"]
[null,"WMECO","Worthington","ESMAEX-03492","01098",20,"Solar","18C2","2024-02-29","2024-03-06",{"$f":"NETWORKDAYS(I1356,J1356,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1356,O1356,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-04","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Springfield","ESMAEX-03550","01104",32.83,"Solar","5J13","2024-03-19","2024-05-13",{"$f":"NETWORKDAYS(I1357,J1357,MALegalHolidays)","v":40},null,40,null,null,{"$f":"NETWORKDAYS(N1357,O1357,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-22",null,null,null,null,null,null,null,null,null," ",null,null,"2026-02-13","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Otis","ESMAEX-03531","01253",70,"Solar","19J4","2024-03-12","2024-04-01",{"$f":"NETWORKDAYS(I1358,J1358,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1358,O1358,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-24",null,null,null,null,null,null,null,null,null," ",null,null,null,"Construction Stage",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Lee","ESMAEX-03528","01238",10,"Solar & Battery","16B5","2024-03-11","2024-03-21",{"$f":"NETWORKDAYS(I1359,J1359,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1359,O1359,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-25",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-09","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Turners Falls","ESMAEX-03511","01376",990,"Battery","21C8","2024-07-24","2024-09-16",{"$f":"NETWORKDAYS(I1360,J1360,MALegalHolidays)","v":39},null,39,null,null,{"$f":"NETWORKDAYS(N1360,O1360,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-25",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,"Gill-Montague",null,990,"21C MONTAGUE"]
[null,"WMECO","Hadley","ESMAEX-03526","01035",498,"Solar","18G4","2024-06-11","2024-06-21",{"$f":"NETWORKDAYS(I1361,J1361,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1361,O1361,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"18G PODICK"]
[null,"WMECO","Worthington","ESMAEX-03537","01098",16.8,"Solar","18C2","2024-03-14","2024-03-21",{"$f":"NETWORKDAYS(I1362,J1362,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1362,O1362,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-05",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-29","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Easthampton","ESMAEX-03563","01027",15.2,"Solar & Battery","15A5","2024-03-21","2024-03-27",{"$f":"NETWORKDAYS(I1363,J1363,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1363,O1363,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-01",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-08","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Southwick","ESMAEX-04793","01077",10,"Solar & Battery","29A1","2025-04-15","2025-04-29",{"$f":"NETWORKDAYS(I1364,J1364,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1364,O1364,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,"Southwick",null,8.74,"29A SOUTHWICK"]
[null,"WMECO","Middlefield","ESMAEX-03579","01243",10,"Solar & Battery","18C2","2024-03-26","2024-04-03",{"$f":"NETWORKDAYS(I1365,J1365,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1365,O1365,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-31",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-24","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Peru","ESMAEX-03573","01235",4999.8,"Solar & Battery","18C2","2024-03-25","2024-05-15",{"$f":"NETWORKDAYS(I1366,J1366,MALegalHolidays)","v":38},null,38,null,null,{"$f":"NETWORKDAYS(N1366,O1366,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Berkshire","Berkshire",null,4999.8,"18C BERKSHIRE"]
[null,"WMECO","Easthampton","ESMAEX-03576","01027",15.2,"Solar","15A2","2024-03-26","2024-04-03",{"$f":"NETWORKDAYS(I1367,J1367,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1367,O1367,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-15",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-12","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","West Springfield","ESMAEX-03620","01089",50,"Solar",null,"2024-04-03","2024-05-15",{"$f":"NETWORKDAYS(I1368,J1368,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1368,O1368,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-28",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-22","Online"]
[null,"WMECO","Deerfield","ESMAEX-03581","01342",46,"Solar & Battery","22B4","2024-03-27","2024-04-12",{"$f":"NETWORKDAYS(I1369,J1369,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1369,O1369,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-21",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-28","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Springfield","ESMAEX-03600","01118",15.2,"Solar","20A32","2024-04-01","2024-04-12",{"$f":"NETWORKDAYS(I1370,J1370,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1370,O1370,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-11-28",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-26","Online",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Amherst","ESMAEX-03626","01002",20,"Solar","18G3","2024-04-03","2024-06-05",{"$f":"NETWORKDAYS(I1371,J1371,MALegalHolidays)","v":46},null,46,null,null,{"$f":"NETWORKDAYS(N1371,O1371,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-07","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-03681","01108",10,"Battery","22H16","2024-04-18","2024-04-24",{"$f":"NETWORKDAYS(I1372,J1372,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1372,O1372,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-04-26",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-25","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Amherst","ESMAEX-03648","01002",15.2,"Solar","18G7","2024-04-09","2024-05-21",{"$f":"NETWORKDAYS(I1373,J1373,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1373,O1373,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-13","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Lanesborough","ESMAEX-03699","01237",9.9,"Solar & Battery","15E1","2024-04-22","2024-05-13",{"$f":"NETWORKDAYS(I1374,J1374,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1374,O1374,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-10",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-17","Online",null,null,null,9.75]
[null,"WMECO","Ludlow","ESMAEX-03662","01056",3.8,"Solar","27A4","2024-04-12","2024-05-28",{"$f":"NETWORKDAYS(I1375,J1375,MALegalHolidays)","v":33},null,33,null,null,{"$f":"NETWORKDAYS(N1375,O1375,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-16","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Pittsfield","ESMAEX-03669","01201",7.6,"Solar","19A1","2024-04-15","2024-06-06",{"$f":"NETWORKDAYS(I1376,J1376,MALegalHolidays)","v":39},null,39,null,null,{"$f":"NETWORKDAYS(N1376,O1376,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-17","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Savoy","ESMAEX-03695","01256",10,"Battery","18K4","2024-04-22","2024-05-14",{"$f":"NETWORKDAYS(I1377,J1377,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1377,O1377,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-05-22",null,null,null,null,null,null,null,null,null," ",null,null,"2024-08-28","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Amherst","ESMAEX-03769","01002",100,"Solar","17K7","2024-05-15","2024-05-22",{"$f":"NETWORKDAYS(I1378,J1378,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1378,O1378,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-05",null,null,null,null,null,null,null,null,null," ",null,null,"2025-12-08","Permission to Operate",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Lee","ESMAEX-03737","01238",100,"Solar","16B5","2024-05-07","2024-05-28",{"$f":"NETWORKDAYS(I1379,J1379,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1379,O1379,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-30",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Shutesbury","ESMAEX-03732","01072",11.5,"Solar & Battery","18G7","2024-05-03","2024-05-14",{"$f":"NETWORKDAYS(I1380,J1380,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1380,O1380,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-06-18",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-07","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Ludlow","ESMAEX-03727","01056",15.2,"Solar",null,"2024-05-02","2024-05-31",{"$f":"NETWORKDAYS(I1381,J1381,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1381,O1381,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-17",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-17","Online"]
[null,"WMECO","Sunderland","ESMAEX-03718","01375",10,"Solar","18G6","2024-04-30","2024-06-06",{"$f":"NETWORKDAYS(I1382,J1382,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1382,O1382,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-30",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-14","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-03739","01108",240,"Solar","22H17","2024-05-08","2024-05-16",{"$f":"NETWORKDAYS(I1383,J1383,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1383,O1383,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-26",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Hatfield","ESMAEX-03738","01038",15,"Solar","18G6","2024-05-08","2024-05-21",{"$f":"NETWORKDAYS(I1384,J1384,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1384,O1384,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-02","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Agawam","ESMAEX-03748","01001",9,"Solar","30A5","2024-05-10","2024-07-09",{"$f":"NETWORKDAYS(I1385,J1385,MALegalHolidays)","v":43},null,43,null,null,{"$f":"NETWORKDAYS(N1385,O1385,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-12",null,null,null,null,null,null,null,null,null," ",null,null,"2024-09-03","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Hinsdale","ESMAEX-03822","01235",4999.8,"Solar & Battery","18C2","2024-06-10","2024-06-21",{"$f":"NETWORKDAYS(I1386,J1386,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1386,O1386,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study","Berkshire","Berkshire",null,4999.8,"18C BERKSHIRE"]
[null,"WMECO","Springfield","ESMAEX-03751","01108",15.2,"Solar","21S11","2024-05-10","2024-05-30",{"$f":"NETWORKDAYS(I1387,J1387,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1387,O1387,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-06-15",null,null,null,null,null,null,null,null,null," ",null,null,"2024-10-30","Online",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Sunderland","ESMAEX-03764","01375",20,"Solar","18G6","2024-05-14","2024-06-06",{"$f":"NETWORKDAYS(I1388,J1388,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1388,O1388,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-23",null,null,null,null,null,null,null,null,null," ",null,null,"2025-04-07","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-03772","01107",20,"Solar","21S10","2024-05-15","2024-06-21",{"$f":"NETWORKDAYS(I1389,J1389,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1389,O1389,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-01-10",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-12","Online",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Turners Falls","ESMAEX-03804","01376",600,"Internal Combustion Engine","21C2","2024-05-30","2024-06-21",{"$f":"NETWORKDAYS(I1390,J1390,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1390,O1390,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-09",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,"Gill-Montague",null,0,"21C MONTAGUE"]
[null,"WMECO","Montgomery","ESMAEX-03811","01085",15.2,"Solar","19J5","2024-06-04","2024-07-01",{"$f":"NETWORKDAYS(I1391,J1391,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1391,O1391,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-20","Online",null,"Blandford"]
[null,"WMECO","Bernardston","ESMAEX-03897","01337",240,"Solar","21B8","2024-07-12","2024-07-22",{"$f":"NETWORKDAYS(I1392,J1392,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1392,O1392,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-03",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Gill-Montague",null,null,"21B FRENCH KING"]
[null,"WMECO","Greenfield","ESMAEX-03928","01301",240,"Solar","22B7","2024-07-26","2024-08-06",{"$f":"NETWORKDAYS(I1393,J1393,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1393,O1393,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-10",null,null,null,null,null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Hatfield","ESMAEX-03820","01038",750,"Solar","18G5","2024-10-24","2024-11-01",{"$f":"NETWORKDAYS(I1394,J1394,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1394,O1394,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Sunderland","ESMAEX-03843","01375",20,"Solar","18G3","2024-06-14","2024-08-05",{"$f":"NETWORKDAYS(I1395,J1395,MALegalHolidays)","v":37},null,37,null,null,{"$f":"NETWORKDAYS(N1395,O1395,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-30",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-12","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Leyden","ESMAEX-03827","01337",10,"Solar","22B7","2024-06-12","2024-07-08",{"$f":"NETWORKDAYS(I1396,J1396,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1396,O1396,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-07",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-02","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Colrain","ESMAEX-03862","01340",20,"Solar & Battery","29R2","2024-06-25","2024-07-23",{"$f":"NETWORKDAYS(I1397,J1397,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1397,O1397,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-28",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-02","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","South Deerfield","ESMAEX-03855","01373",15.2,"Solar","22B1","2024-06-24","2024-07-05",{"$f":"NETWORKDAYS(I1398,J1398,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1398,O1398,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-08",null,null,null,null,null,null,null,null,null," ",null,null,"2024-11-26","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","West Springfield","ESMAEX-03872","01089",20,"Solar","21N9","2024-06-29","2024-07-23",{"$f":"NETWORKDAYS(I1399,J1399,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1399,O1399,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-07-29",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-13","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Ludlow","ESMAEX-03876","01056",23,"Solar & Battery","19S3","2024-07-01","2024-07-09",{"$f":"NETWORKDAYS(I1400,J1400,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1400,O1400,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-29",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-14","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Amherst","ESMAEX-03880","01002",23,"Solar","19B16","2024-07-02","2024-08-07",{"$f":"NETWORKDAYS(I1401,J1401,MALegalHolidays)","v":27},null,27,null,null,{"$f":"NETWORKDAYS(N1401,O1401,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-30",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-24","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","East Otis","ESMAEX-03888","01029",20,"Solar","19J4","2024-07-10","2024-08-06",{"$f":"NETWORKDAYS(I1402,J1402,MALegalHolidays)","v":20},null,{"$f":"IF(K1402>0,K1402-L1402,\" \")","v":20},null,null,{"$f":"NETWORKDAYS(N1402,O1402,MALegalHolidays)","v":0},null,{"$f":"IF(P1402>0,P1402-Q1402,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1402>0,U1402-V1402,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1402>0,Z1402-AA1402,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1402>0,AE1402-AF1402,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1402>0,AJ1402-AK1402,\" \")","v":" "},"2024-10-06",null,null,null,null,null,null,null,null,null,{"$f":"IF(AU1402>0,AU1402-AV1402,\" \")","v":" "},null,null,"2025-01-10","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Pittsfield","ESMAEX-03925","01201",3500,"Solar & Battery","15E2","2024-07-25","2024-08-06",{"$f":"NETWORKDAYS(I1403,J1403,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1403,O1403,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,null,"Impact Study",null,null,null,null,"15E PARTRIDGE"]
[null,"WMECO","Lee","ESMAEX-03914","01238",4999,"Other","16B5","2025-02-04","2025-02-11",{"$f":"NETWORKDAYS(I1404,J1404,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1404,O1404,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Standard",null,null,null,null,null," ",null,null,null,"Exhibit E Agreement",null,null,null,4999,"16B PLEASANT"]
[null,"WMECO","Huntington","ESMAEX-03924","01050",23,"Solar & Battery","19J5","2024-07-25","2024-08-20",{"$f":"NETWORKDAYS(I1405,J1405,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1405,O1405,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-13","Online"]
[null,"WMECO","Feeding Hills","ESMAEX-03937","01030",15.2,"Solar","30A6","2024-07-30","2024-09-13",{"$f":"NETWORKDAYS(I1406,J1406,MALegalHolidays)","v":34},null,34,null,null,{"$f":"NETWORKDAYS(N1406,O1406,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-16",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-06","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Tyringham","ESMAEX-03966","01264",23,"Solar","16B1","2024-08-14","2024-08-28",{"$f":"NETWORKDAYS(I1407,J1407,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1407,O1407,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-08-30",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-14","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Pittsfield","ESMAEX-03954","01201",180,"Solar","30B2","2024-09-06","2024-11-08",{"$f":"NETWORKDAYS(I1408,J1408,MALegalHolidays)","v":46},null,46,null,null,{"$f":"NETWORKDAYS(N1408,O1408,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-19",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Longmeadow","ESMAEX-03961","01106",15.36,"Solar","22H13","2024-08-12","2024-08-14",{"$f":"NETWORKDAYS(I1409,J1409,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1409,O1409,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-16",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Lee","ESMAEX-03957","01238",15.2,"Solar","16B5","2024-08-09","2024-09-11",{"$f":"NETWORKDAYS(I1410,J1410,MALegalHolidays)","v":24},null,24,null,null,{"$f":"NETWORKDAYS(N1410,O1410,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-06",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-12","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Montague","ESMAEX-03967","01351",20,"Battery","21C7","2024-08-14","2024-09-11",{"$f":"NETWORKDAYS(I1411,J1411,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1411,O1411,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-16",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-30","Online",null,"Gill-Montague",null,10,"21C MONTAGUE"]
[null,"WMECO","West Hatfield","ESMAEX-03989","01088",9.57,"Solar","18G5","2024-08-22","2024-08-29",{"$f":"NETWORKDAYS(I1412,J1412,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1412,O1412,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-23",null,null,null,null,null,null,null,null,null," ",null,null,"2024-12-13","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Whately","ESMAEX-03978","01093",23,"Solar & Battery","18G8","2024-08-18","2024-08-28",{"$f":"NETWORKDAYS(I1413,J1413,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1413,O1413,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-25",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,23,"18G PODICK"]
[null,"WMECO","Otis","ESMAEX-03984","01253",5000,"Solar & Battery","19J4","2024-09-09","2024-09-13",{"$f":"NETWORKDAYS(I1414,J1414,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1414,O1414,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Lanesborough","ESMAEX-04002","01237",16.899999999999999,"Battery","15E1","2024-08-27","2024-09-16",{"$f":"NETWORKDAYS(I1415,J1415,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1415,O1415,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-09-17",null,null,null,null,null,null,null,null,null," ",null,null,null,"Permission to Operate",null,null,null,6.9]
[null,"WMECO","Southampton","ESMAEX-04025","01073",23,"Solar & Battery","15A3","2024-09-04","2024-09-26",{"$f":"NETWORKDAYS(I1416,J1416,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1416,O1416,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-29",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-24","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Amherst","ESMAEX-04054","01002",30,"Solar","18G7","2024-09-12","2024-09-20",{"$f":"NETWORKDAYS(I1417,J1417,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1417,O1417,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-29",null,null,null,null,null,null,null,null,null," ",null,null,"2025-01-24","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Hadley","ESMAEX-04039","01035",999,"Solar","17K5","2024-11-19","2025-01-28",{"$f":"NETWORKDAYS(I1418,J1418,MALegalHolidays)","v":51},null,51,null,null,{"$f":"NETWORKDAYS(N1418,O1418,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,999,"17K AMHERST"]
[null,"WMECO","Hadley","ESMAEX-04202","01035",625,"Solar","17K5","2024-10-24","2024-11-18",{"$f":"NETWORKDAYS(I1419,J1419,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1419,O1419,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-26",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Lee","ESMAEX-04068","01238",15.2,"Solar",null,"2024-09-18","2024-10-22",{"$f":"NETWORKDAYS(I1420,J1420,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1420,O1420,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-10-24",null,null,null,null,null,null,null,null,null," ",null,null,"2025-04-07","Online"]
[null,"WMECO","Hadley","ESMAEX-04056","01035",240,"Solar","17K1","2024-09-13","2024-09-19",{"$f":"NETWORKDAYS(I1421,J1421,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1421,O1421,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-03",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Southwick","ESMAEX-04115","01077",7.6,"Solar","29A1","2024-09-26","2024-10-17",{"$f":"NETWORKDAYS(I1422,J1422,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1422,O1422,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-28",null,null,null,null,null,null,null,null,null," ",null,null,"2025-07-17","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Southampton","ESMAEX-04155","01073",15.2,"Solar","15A1","2024-10-08","2024-10-28",{"$f":"NETWORKDAYS(I1423,J1423,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1423,O1423,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-03",null,null,null,null,null,null,null,null,null," ",null,null,"2025-03-12","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","North Hatfield","ESMAEX-04157","01066",17.16,"Solar","18G6","2024-10-09","2024-10-18",{"$f":"NETWORKDAYS(I1424,J1424,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1424,O1424,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-12-09",null,null,null,null,null,null,null,null,null," ",null,null,"2025-04-08","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Dalton","ESMAEX-04162","01226",2988,"Solar & Battery","18C1","2024-11-01","2024-11-18",{"$f":"NETWORKDAYS(I1425,J1425,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1425,O1425,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,"Berkshire",null,null,"18C BERKSHIRE"]
[null,"WMECO","Southampton","ESMAEX-04166","01073",3000,"Solar & Battery","15A1","2024-11-06","2024-11-18",{"$f":"NETWORKDAYS(I1426,J1426,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1426,O1426,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Transmission",null,null,null,null,"15A GUNN"]
[null,"WMECO","Ludlow","ESMAEX-04200","01056",7.6,"Solar","19S3","2024-10-22","2024-11-08",{"$f":"NETWORKDAYS(I1427,J1427,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1427,O1427,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-11-18",null,null,null,null,null,null,null,null,null," ",null,null,"2025-03-25","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Richmond","ESMAEX-04237","01254",10,"Solar & Battery","30B7","2024-11-04","2024-11-12",{"$f":"NETWORKDAYS(I1428,J1428,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1428,O1428,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-02",null,null,null,null,null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Easthampton","ESMAEX-04203","01027",11.5,"Battery","15A2","2024-10-24",null,{"$f":"NETWORKDAYS(I1429,J1429,MALegalHolidays)","v":-32513},null," ",null,null,{"$f":"NETWORKDAYS(N1429,O1429,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-13","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Southwick","ESMAEX-04231","01077",15,"Battery","29A5","2024-11-01","2024-11-19",{"$f":"NETWORKDAYS(I1430,J1430,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1430,O1430,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-03",null,null,null,null,null,null,null,null,null," ",null,null,"2025-07-18","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Dalton","ESMAEX-04224","01226",24,"Solar","19A2","2024-10-29","2024-11-06",{"$f":"NETWORKDAYS(I1431,J1431,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1431,O1431,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2024-11-06",null,null,null,null,null,null,null,null,null," ",null,null,"2025-02-27","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Hinsdale","ESMAEX-04230","01235",13.8,"Solar","18C2","2024-11-01","2025-01-08",{"$f":"NETWORKDAYS(I1432,J1432,MALegalHolidays)","v":49},null,49,null,null,{"$f":"NETWORKDAYS(N1432,O1432,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-06",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Southwick","ESMAEX-04274","01077",11.5,"Battery","29A5","2024-11-13",null,{"$f":"NETWORKDAYS(I1433,J1433,MALegalHolidays)","v":-32527},null," ",null,null,{"$f":"NETWORKDAYS(N1433,O1433,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-27",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-13","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Amherst","ESMAEX-04280","01002",300,"Solar","17K5","2025-02-14","2025-02-24",{"$f":"NETWORKDAYS(I1434,J1434,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1434,O1434,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-09",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Hadley","ESMAEX-04356","01035",22.8,"Solar","19B15","2024-12-10","2025-01-24",{"$f":"NETWORKDAYS(I1435,J1435,MALegalHolidays)","v":34},null,34,null,null,{"$f":"NETWORKDAYS(N1435,O1435,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-05",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Hadley","ESMAEX-04357","01035",22.8,"Solar","19B15","2024-12-10","2025-01-24",{"$f":"NETWORKDAYS(I1436,J1436,MALegalHolidays)","v":34},null,34,null,null,{"$f":"NETWORKDAYS(N1436,O1436,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-10",null,null,null,null,null,null,null,null,null," ",null,null,null,"Meter",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","West Springfield","ESMAEX-04335","01089",11.5,"Battery","16C11","2024-12-05","2025-01-24",{"$f":"NETWORKDAYS(I1437,J1437,MALegalHolidays)","v":37},null,37,null,null,{"$f":"NETWORKDAYS(N1437,O1437,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-06",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Blandford","ESMAEX-04291","01008",1999,"Solar & Battery","19J2","2024-11-21","2024-12-05",{"$f":"NETWORKDAYS(I1438,J1438,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1438,O1438,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Impact Study",null,"Blandford",null,1999,"19J BLANDFORD"]
[null,"WMECO","Pittsfield","ESMAEX-04288","01201",46,"Solar & Battery",null,"2024-11-20","2024-11-26",{"$f":"NETWORKDAYS(I1439,J1439,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1439,O1439,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-02",null,null,null,null,null,null,null,null,null," ",null,null,"2025-07-16","Online"]
[null,"WMECO","West Springfield","ESMAEX-04318","01089",22.77,"Solar","21N9","2024-12-03","2024-12-18",{"$f":"NETWORKDAYS(I1440,J1440,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1440,O1440,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-14",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-17","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Feeding Hills","ESMAEX-04359","01030",15.2,"Solar","30A1","2024-12-11","2025-01-15",{"$f":"NETWORKDAYS(I1441,J1441,MALegalHolidays)","v":26},null,26,null,null,{"$f":"NETWORKDAYS(N1441,O1441,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-18",null,null,null,null,null,null,null,null,null," ",null,null,"2025-10-20","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Deerfield","ESMAEX-04370","01342",4999,"Solar & Battery","22B7","2024-12-13",null,{"$f":"NETWORKDAYS(I1442,J1442,MALegalHolidays)","v":-32549},null," ",null,null,{"$f":"NETWORKDAYS(N1442,O1442,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Erving","ESMAEX-04365","01344",200,"Solar","21C8","2024-12-17","2025-01-28",{"$f":"NETWORKDAYS(I1443,J1443,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1443,O1443,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,"Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","Amherst","ESMAEX-04361","01002",15.2,"Solar","19B16","2024-12-11","2025-01-15",{"$f":"NETWORKDAYS(I1444,J1444,MALegalHolidays)","v":26},null,26,null,null,{"$f":"NETWORKDAYS(N1444,O1444,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-07",null,null,null,null,null,null,null,null,null," ",null,null,"2025-04-29","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Hadley","ESMAEX-04385","01035",67.3,"Solar","18G4","2024-12-16","2025-01-21",{"$f":"NETWORKDAYS(I1445,J1445,MALegalHolidays)","v":27},null,27,null,null,{"$f":"NETWORKDAYS(N1445,O1445,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-12",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-29","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","West Springfield","ESMAEX-04467","01089",240,"Solar","21N5","2025-06-17","2025-06-30",{"$f":"NETWORKDAYS(I1446,J1446,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1446,O1446,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"21N PIPER"]
[null,"WMECO","Westhampton","ESMAEX-04403","01027",15.2,"Solar","15A3","2024-12-23","2025-01-22",{"$f":"NETWORKDAYS(I1447,J1447,MALegalHolidays)","v":23},null,23,null,null,{"$f":"NETWORKDAYS(N1447,O1447,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-12",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-17","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Springfield","ESMAEX-04412","01109",400,"Solar","5J18","2025-04-15","2025-05-02",{"$f":"NETWORKDAYS(I1448,J1448,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1448,O1448,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Pittsfield","ESMAEX-04476","01201",120,"Solar","30B2","2025-01-29","2025-02-11",{"$f":"NETWORKDAYS(I1449,J1449,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1449,O1449,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-05",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Whately","ESMAEX-04431","01093",11.4,"Solar","18G8","2025-01-14","2025-01-30",{"$f":"NETWORKDAYS(I1450,J1450,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1450,O1450,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-12",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-16","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Easthampton","ESMAEX-04459","01027",15.2,"Solar","15A5","2025-01-22","2025-02-07",{"$f":"NETWORKDAYS(I1451,J1451,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1451,O1451,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-17",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-18","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Hadley","ESMAEX-04586","01035",15.2,"Battery","18G4","2025-03-04","2025-03-10",{"$f":"NETWORKDAYS(I1452,J1452,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1452,O1452,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-06-13","Online",null,null,null,13.8,"18G PODICK"]
[null,"WMECO","Pittsfield","ESMAEX-04470","01201",120,"Solar","30B2","2025-01-28","2025-02-11",{"$f":"NETWORKDAYS(I1453,J1453,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1453,O1453,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-19",null,null,null,null,null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Chesterfield","ESMAEX-04473","01012",30,"Solar & Battery","19J5","2025-01-29","2025-02-26",{"$f":"NETWORKDAYS(I1454,J1454,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1454,O1454,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-05",null,null,null,null,null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Westhampton","ESMAEX-04474","01027",15.2,"Solar","15A3","2025-01-29","2025-02-25",{"$f":"NETWORKDAYS(I1455,J1455,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1455,O1455,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-21",null,null,null,null,null,null,null,null,null," ",null,null,"2025-06-17","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Conway","ESMAEX-04480","01341",18.48,"Solar","38A1","2025-02-13","2025-02-26",{"$f":"NETWORKDAYS(I1456,J1456,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1456,O1456,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-26",null,null,null,null,null,null,null,null,null," ",null,null,"2026-02-03","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Lee","ESMAEX-04484","01238",51.9,"Solar","16B5","2025-02-04","2025-02-19",{"$f":"NETWORKDAYS(I1457,J1457,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1457,O1457,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-02-21",null,null,null,null,null,null,null,null,null," ",null,null,"2025-10-03","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Hatfield","ESMAEX-04498","01038",9,"Solar","18G5","2025-02-07","2025-03-21",{"$f":"NETWORKDAYS(I1458,J1458,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1458,O1458,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,null,null,null,null,null,null," ",null,null,"2025-10-09","Online",null,null,null,9,"18G PODICK"]
[null,"WMECO","Leyden","ESMAEX-04516","01301",23,"Solar & Battery","22B7","2025-02-24","2025-03-10",{"$f":"NETWORKDAYS(I1459,J1459,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1459,O1459,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-29",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-10","Online",null,null,null,15,"22B CUMBERLAND"]
[null,"WMECO","Westhampton","ESMAEX-04497","01027",10.56,"Solar","15A3","2025-02-07","2025-02-20",{"$f":"NETWORKDAYS(I1460,J1460,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1460,O1460,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-31",null,null,null,null,null,null,null,null,null," ",null,null,"2025-07-17","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Hadley","ESMAEX-04495","01035",450,"Solar","18G5","2025-03-10","2025-04-16",{"$f":"NETWORKDAYS(I1461,J1461,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1461,O1461,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Hinsdale","ESMAEX-04505","01235",4999,"Solar & Battery","18C2","2025-02-10","2025-04-07",{"$f":"NETWORKDAYS(I1462,J1462,MALegalHolidays)","v":41},null,41,null,null,{"$f":"NETWORKDAYS(N1462,O1462,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Impact Study",null,"Berkshire",null,4999,"18C BERKSHIRE"]
[null,"WMECO","Ludlow","ESMAEX-04504","01056",5.76,"Solar","19S3","2025-02-10","2025-03-03",{"$f":"NETWORKDAYS(I1463,J1463,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1463,O1463,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-15",null,null,null,null,null,null,null,null,null," ",null,null,"2026-01-21","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Amherst","ESMAEX-04513","01002",15.744,"Solar","17K8","2025-02-12","2025-02-25",{"$f":"NETWORKDAYS(I1464,J1464,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1464,O1464,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-21",null,null,null,null,null,null,null,null,null," ",null,null,"2025-10-08","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Conway","ESMAEX-04521","01341",11.5,"Solar & Battery","38A1","2025-02-14","2025-03-24",{"$f":"NETWORKDAYS(I1465,J1465,MALegalHolidays)","v":27},null,27,null,null,{"$f":"NETWORKDAYS(N1465,O1465,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-30",null,null,null,null,null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Amherst","ESMAEX-04554","01002",704,"Solar","17K2","2026-01-14","2026-01-26",{"$f":"NETWORKDAYS(I1466,J1466,MALegalHolidays)","v":9},null,{"$f":"IF(K1466>0,K1466-L1466,\" \")","v":9},null,null,{"$f":"NETWORKDAYS(N1466,O1466,MALegalHolidays)","v":0},null,{"$f":"IF(P1466>0,P1466-Q1466,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1466>0,U1466-V1466,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1466>0,Z1466-AA1466,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1466>0,AE1466-AF1466,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1466>0,AJ1466-AK1466,\" \")","v":" "},null,null,null,null,"Expedited",null,null,null,null,null,{"$f":"IF(AU1466>0,AU1466-AV1466,\" \")","v":" "},null,null,null,"Technical Review",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Greenfield","ESMAEX-04532","01301",999.45,"Solar & Battery","22B3","2025-03-27","2025-04-11",{"$f":"NETWORKDAYS(I1467,J1467,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1467,O1467,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,999.45,"22B CUMBERLAND"]
[null,"WMECO","Southampton","ESMAEX-04542","01073",20,"Solar","15A1","2025-02-19","2025-03-10",{"$f":"NETWORKDAYS(I1468,J1468,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1468,O1468,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,null,null,null,null,null,null," ",null,null,"2025-08-26","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Southampton","ESMAEX-04557","01073",10,"Solar","15A1","2025-02-21","2025-03-10",{"$f":"NETWORKDAYS(I1469,J1469,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1469,O1469,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,null,null,null,null,null,null," ",null,null,"2025-09-18","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Leverett","ESMAEX-04568","01054",11.4,"Solar","18G7","2025-02-25","2025-03-03",{"$f":"NETWORKDAYS(I1470,J1470,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1470,O1470,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-21",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-08-29","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Pittsfield","ESMAEX-04562","01201",21.4,"Solar","15E2","2025-03-03","2025-03-17",{"$f":"NETWORKDAYS(I1471,J1471,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1471,O1471,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-06-17","Online"]
[null,"WMECO","Amherst","ESMAEX-04600","01002",7.6,"Solar","18G7","2025-03-06","2025-03-17",{"$f":"NETWORKDAYS(I1472,J1472,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1472,O1472,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-06-17","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","West Springfield","ESMAEX-04628","01089",50,"Solar","21N5","2025-03-14","2025-04-02",{"$f":"NETWORKDAYS(I1473,J1473,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1473,O1473,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-08","Online",null,null,null,null,"21N PIPER"]
[null,"WMECO","Pittsfield","ESMAEX-04566","01201",4350,"Other","15E2","2025-07-22","2025-08-13",{"$f":"NETWORKDAYS(I1474,J1474,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1474,O1474,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,4350,"15E PARTRIDGE"]
[null,"WMECO","Ludlow","ESMAEX-04570","01056",8.36,"Solar & Battery","19S2","2025-02-26","2025-03-10",{"$f":"NETWORKDAYS(I1475,J1475,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1475,O1475,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-08-26","Online",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Hadley","ESMAEX-04573","01035",11.5,"Solar & Battery","18G4","2025-02-26","2025-03-10",{"$f":"NETWORKDAYS(I1476,J1476,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1476,O1476,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-14",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-04578","01109",400,"Solar","5J18","2025-04-15","2025-05-02",{"$f":"NETWORKDAYS(I1477,J1477,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1477,O1477,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Pittsfield","ESMAEX-04602","01201",9.6,"Solar","30B5","2025-03-05","2025-03-21",{"$f":"NETWORKDAYS(I1478,J1478,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1478,O1478,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-01",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-07-17","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Longmeadow","ESMAEX-04617","01106",5.76,"Solar","22H11","2025-03-11","2025-03-17",{"$f":"NETWORKDAYS(I1479,J1479,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1479,O1479,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-03-27",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-06-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Hadley","ESMAEX-04633","01035",15.2,"Solar","19B15","2025-03-14","2025-03-25",{"$f":"NETWORKDAYS(I1480,J1480,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1480,O1480,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-08-05","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Springfield","ESMAEX-04651","01129",990,"Solar","27A7","2025-04-11","2025-04-24",{"$f":"NETWORKDAYS(I1481,J1481,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1481,O1481,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Hadley","ESMAEX-04657","01035",990,"Solar","17K5","2025-04-11","2025-04-24",{"$f":"NETWORKDAYS(I1482,J1482,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1482,O1482,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Longmeadow","ESMAEX-04661","01106",240,"Solar","22H12","2025-04-11","2025-04-24",{"$f":"NETWORKDAYS(I1483,J1483,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1483,O1483,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Savoy","ESMAEX-04663","01256",5.76,"Solar","18K4","2025-03-19","2025-04-09",{"$f":"NETWORKDAYS(I1484,J1484,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1484,O1484,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-15","Online",null,"Dalton-Hinsdale",null,null,"18C BERKSHIRE"]
[null,"WMECO","Easthampton","ESMAEX-04670","01027",17.600000000000001,"Solar & Battery","15A1","2025-03-19","2025-04-29",{"$f":"NETWORKDAYS(I1485,J1485,MALegalHolidays)","v":30},null,30,null,null,{"$f":"NETWORKDAYS(N1485,O1485,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-20",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-27","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","New Ashford","ESMAEX-04682","01237",9.3000000000000007,"Solar","15E1","2025-03-24","2025-03-31",{"$f":"NETWORKDAYS(I1486,J1486,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1486,O1486,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-04-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-12","Online",null,"Partridge",null,null,"15E PARTRIDGE"]
[null,"WMECO","Hadley","ESMAEX-04703","01035",22.8,"Solar","18G5","2025-03-28","2025-04-15",{"$f":"NETWORKDAYS(I1487,J1487,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1487,O1487,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-15",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-29","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Deerfield","ESMAEX-04917","01342",95,"Solar","22B1","2025-05-14","2025-07-01",{"$f":"NETWORKDAYS(I1488,J1488,MALegalHolidays)","v":35},null,35,null,null,{"$f":"NETWORKDAYS(N1488,O1488,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-01",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-04","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Leverett","ESMAEX-04764","01054",13.8,"Solar","18G7","2025-04-08","2025-04-15",{"$f":"NETWORKDAYS(I1489,J1489,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1489,O1489,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-18","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Southampton","ESMAEX-04748","01073",996,"Solar","15A1","2025-04-07","2025-04-24",{"$f":"NETWORKDAYS(I1490,J1490,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1490,O1490,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"15A GUNN"]
[null,"WMECO","South Deerfield","ESMAEX-04749","01373",15.2,"Solar","22B1","2025-04-07","2025-04-15",{"$f":"NETWORKDAYS(I1491,J1491,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1491,O1491,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-03","Online",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Buckland","ESMAEX-04755","01370",498,"Solar","38A1","2025-04-23","2025-05-08",{"$f":"NETWORKDAYS(I1492,J1492,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1492,O1492,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Springfield","ESMAEX-05060","01105",161,"Solar","21S12","2025-06-13","2025-07-02",{"$f":"NETWORKDAYS(I1493,J1493,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1493,O1493,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Sunderland","ESMAEX-04767","01375",7.6,"Solar","18G6","2025-04-08","2025-04-15",{"$f":"NETWORKDAYS(I1494,J1494,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1494,O1494,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-19",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-07-30","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Southwick","ESMAEX-04769","01077",20,"Solar","29A5","2025-04-08","2025-04-15",{"$f":"NETWORKDAYS(I1495,J1495,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1495,O1495,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Northfield","ESMAEX-04863","01360",11.5,"Solar & Battery","21B8","2025-05-01","2025-05-14",{"$f":"NETWORKDAYS(I1496,J1496,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1496,O1496,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-02","Online",null,"Gill-Montague",null,10,"21B FRENCH KING"]
[null,"WMECO","Hinsdale","ESMAEX-04784","01235",4999,"Solar & Battery","18C2","2025-04-10","2025-04-24",{"$f":"NETWORKDAYS(I1497,J1497,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1497,O1497,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"On Hold",null,"Berkshire",null,4999,"18C BERKSHIRE"]
[null,"WMECO","Lee","ESMAEX-04791","01238",23,"Solar & Battery","16B5","2025-04-14","2025-04-23",{"$f":"NETWORKDAYS(I1498,J1498,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1498,O1498,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-07-28","Online",null,null,null,8,"16B PLEASANT"]
[null,"WMECO","Easthampton","ESMAEX-04803","01027",11.5,"Other","15A2","2025-04-17","2025-04-30",{"$f":"NETWORKDAYS(I1499,J1499,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1499,O1499,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-21",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-05","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Feeding Hills","ESMAEX-04833","01030",4.22,"Solar & Battery","16C17","2025-05-01","2025-05-12",{"$f":"NETWORKDAYS(I1500,J1500,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1500,O1500,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-07","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Springfield","ESMAEX-04814","01105",99.9,"Solar",null,"2025-04-18","2025-06-30",{"$f":"NETWORKDAYS(I1501,J1501,MALegalHolidays)","v":52},null,52,null,null,{"$f":"NETWORKDAYS(N1501,O1501,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-24",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,100]
[null,"WMECO","West Springfield","ESMAEX-04815","01089",161,"Solar","21N5","2025-04-18","2025-07-02",{"$f":"NETWORKDAYS(I1502,J1502,MALegalHolidays)","v":54},null,54,null,null,{"$f":"NETWORKDAYS(N1502,O1502,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,161,"21N PIPER"]
[null,"WMECO","Lanesborough","ESMAEX-04806","01237",5.76,"Solar","30B5","2025-04-17","2025-05-01",{"$f":"NETWORKDAYS(I1503,J1503,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1503,O1503,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-08","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Whately","ESMAEX-04816","01093",498,"Solar","18G8","2025-05-12","2025-06-01",{"$f":"NETWORKDAYS(I1504,J1504,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1504,O1504,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Granville","ESMAEX-04868","01034",7.6,"Solar","29A5","2025-05-02","2025-05-20",{"$f":"NETWORKDAYS(I1505,J1505,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1505,O1505,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-06-20","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Agawam","ESMAEX-04834","01001",15.18,"Solar","30A1","2025-04-25","2025-05-14",{"$f":"NETWORKDAYS(I1506,J1506,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1506,O1506,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-05-21",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-07-22","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Otis","ESMAEX-04873","01253",16.2,"Solar","19J4","2025-05-05","2025-06-11",{"$f":"NETWORKDAYS(I1507,J1507,MALegalHolidays)","v":28},null,28,null,null,{"$f":"NETWORKDAYS(N1507,O1507,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-24",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Hadley","ESMAEX-05100","01035",20,"Solar","18G4","2025-06-24","2025-07-07",{"$f":"NETWORKDAYS(I1508,J1508,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1508,O1508,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-21","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Cummington","ESMAEX-04865","01026",24.42,"Solar","18C1","2025-05-01","2025-05-14",{"$f":"NETWORKDAYS(I1509,J1509,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1509,O1509,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-04","Online",null,"Plainfield",null,null,"18C BERKSHIRE"]
[null,"WMECO","Leverett","ESMAEX-04895","01054",15.2,"Solar","18G7","2025-05-09","2025-05-22",{"$f":"NETWORKDAYS(I1510,J1510,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1510,O1510,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-29","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","South Deerfield","ESMAEX-04957","01373",250,"Solar","22B3","2025-05-20","2025-06-01",{"$f":"NETWORKDAYS(I1511,J1511,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1511,O1511,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Amherst","ESMAEX-04900","01002",10,"Solar","19B16","2025-05-12","2025-05-22",{"$f":"NETWORKDAYS(I1512,J1512,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1512,O1512,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Meter",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Ashfield","ESMAEX-04941","01330",10,"Solar","38A1","2025-05-16","2025-06-02",{"$f":"NETWORKDAYS(I1513,J1513,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1513,O1513,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-25",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","West Springfield","ESMAEX-05066","01089",80,"Solar",null,"2025-06-16","2025-11-11",{"$f":"NETWORKDAYS(I1514,J1514,MALegalHolidays)","v":107},null,107,null,null,{"$f":"NETWORKDAYS(N1514,O1514,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement "]
[null,"WMECO","Longmeadow","ESMAEX-04880","01106",15.2,"Solar","22H12","2025-05-06","2025-05-30",{"$f":"NETWORKDAYS(I1515,J1515,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1515,O1515,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-03",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-10","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Amherst","ESMAEX-04891","01002",10,"Solar","19B16","2025-05-09","2025-05-22",{"$f":"NETWORKDAYS(I1516,J1516,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1516,O1516,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-27",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-18","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Otis","ESMAEX-04888","01253",20,"Solar","19J4","2025-05-06","2025-06-23",{"$f":"NETWORKDAYS(I1517,J1517,MALegalHolidays)","v":35},null,35,null,null,{"$f":"NETWORKDAYS(N1517,O1517,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-25",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-21","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Greenfield","ESMAEX-04959","01301",22.8,"Solar","22B4","2025-05-20","2025-06-10",{"$f":"NETWORKDAYS(I1518,J1518,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1518,O1518,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Conway","ESMAEX-04906","01341",15,"Solar & Battery","38A1","2025-05-13","2025-05-21",{"$f":"NETWORKDAYS(I1519,J1519,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1519,O1519,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-16",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-07","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Bernardston","ESMAEX-04910","01337",15.2,"Solar","21C1","2025-05-13","2025-06-10",{"$f":"NETWORKDAYS(I1520,J1520,MALegalHolidays)","v":21},null,21,null,null,{"$f":"NETWORKDAYS(N1520,O1520,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-14","Online",null,"Gill-Montague",null,null,"21C MONTAGUE"]
[null,"WMECO","Pittsfield","ESMAEX-04946","01201",15.18,"Solar","19A1","2025-05-18","2025-06-01",{"$f":"NETWORKDAYS(I1521,J1521,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1521,O1521,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-07-25","Online",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Hadley","ESMAEX-04936","01035",499,"Other","17K5","2025-08-01","2025-08-13",{"$f":"NETWORKDAYS(I1522,J1522,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1522,O1522,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,499,"17K AMHERST"]
[null,"WMECO","Ashfield","ESMAEX-04962","01330",50,"Solar","38A1","2025-05-20","2025-07-17",{"$f":"NETWORKDAYS(I1523,J1523,MALegalHolidays)","v":43},null,43,null,null,{"$f":"NETWORKDAYS(N1523,O1523,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-08",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Ashfield","ESMAEX-04963","01330",120,"Solar","38A1","2025-05-20","2025-07-17",{"$f":"NETWORKDAYS(I1524,J1524,MALegalHolidays)","v":43},null,43,null,null,{"$f":"NETWORKDAYS(N1524,O1524,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Huntington","ESMAEX-05030","01050",10,"Solar","19J5","2025-06-09","2025-06-26",{"$f":"NETWORKDAYS(I1525,J1525,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1525,O1525,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-28","Online"]
[null,"WMECO","West Springfield","ESMAEX-04964","01089",15.2,"Solar","16C11","2025-05-21","2025-06-04",{"$f":"NETWORKDAYS(I1526,J1526,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1526,O1526,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-24","Online",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Lee","ESMAEX-04965","01238",7.6,"Solar","16B5","2025-05-21","2025-06-10",{"$f":"NETWORKDAYS(I1527,J1527,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1527,O1527,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-16",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-18","Online",null,null,null,null,"16B PLEASANT"]
[null,"WMECO","Southampton","ESMAEX-04983","01073",19,"Solar","15A1","2025-05-27","2025-06-05",{"$f":"NETWORKDAYS(I1528,J1528,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1528,O1528,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-26",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-07","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Granville","ESMAEX-05010","01034",498,"Solar","29A5","2025-06-26","2025-07-11",{"$f":"NETWORKDAYS(I1529,J1529,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1529,O1529,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Feeding Hills","ESMAEX-05012","01030",5.76,"Solar","30A6","2025-06-04","2025-07-10",{"$f":"NETWORKDAYS(I1530,J1530,MALegalHolidays)","v":27},null,{"$f":"IF(K1530>0,K1530-L1530,\" \")","v":27},null,null,{"$f":"NETWORKDAYS(N1530,O1530,MALegalHolidays)","v":0},null,{"$f":"IF(P1530>0,P1530-Q1530,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1530>0,U1530-V1530,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1530>0,Z1530-AA1530,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1530>0,AE1530-AF1530,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1530>0,AJ1530-AK1530,\" \")","v":" "},"2025-07-30",null,null,null,"Expedited",null,null,null,null,null,{"$f":"IF(AU1530>0,AU1530-AV1530,\" \")","v":" "},null,null,"2025-10-31","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Pittsfield","ESMAEX-05016","01201",5.76,"Solar","30B5","2025-06-05","2025-06-23",{"$f":"NETWORKDAYS(I1531,J1531,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1531,O1531,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Southwick","ESMAEX-05043","01077",15.76,"Solar","29A1","2025-06-10","2025-06-24",{"$f":"NETWORKDAYS(I1532,J1532,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1532,O1532,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-06-27",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-11","Online",null,"Southwick",null,null,"29A SOUTHWICK"]
[null,"WMECO","Springfield","ESMAEX-05072","01104",250,"Solar","5J9","2025-06-19","2025-06-30",{"$f":"NETWORKDAYS(I1533,J1533,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1533,O1533,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-15","Online",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Easthampton","ESMAEX-05056","01027",7.6,"Solar","15A1","2025-06-13","2025-06-25",{"$f":"NETWORKDAYS(I1534,J1534,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1534,O1534,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-12","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Montgomery","ESMAEX-05069","01085",20,"Solar","19J5","2025-06-16","2025-07-01",{"$f":"NETWORKDAYS(I1535,J1535,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1535,O1535,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Hatfield","ESMAEX-05096","01038",10,"Solar","18G5","2025-06-20","2025-07-03",{"$f":"NETWORKDAYS(I1536,J1536,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1536,O1536,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-18","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Hadley","ESMAEX-05106","01035",999,"Solar","18G4","2025-09-26","2026-02-18",{"$f":"NETWORKDAYS(I1537,J1537,MALegalHolidays)","v":104},null,104,null,null,{"$f":"NETWORKDAYS(N1537,O1537,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Standard",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,999,"18G PODICK"]
[null,"WMECO","Ludlow","ESMAEX-05166","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1538,J1538,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1538,O1538,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05168","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1539,J1539,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1539,O1539,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05169","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1540,J1540,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1540,O1540,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05170","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1541,J1541,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1541,O1541,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-27","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05171","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1542,J1542,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1542,O1542,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Permission to Operate",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05172","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1543,J1543,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1543,O1543,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Ludlow","ESMAEX-05173","01056",22.8,"Solar","27A4","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1544,J1544,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1544,O1544,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Online",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Hadley","ESMAEX-05102","01035",499,"Solar","19B15","2025-07-21","2025-08-13",{"$f":"NETWORKDAYS(I1545,J1545,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1545,O1545,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Pittsfield","ESMAEX-05107","01201",11.5,"Solar & Battery","30B7","2025-06-23","2025-07-10",{"$f":"NETWORKDAYS(I1546,J1546,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1546,O1546,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-31",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-21","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Westhampton","ESMAEX-05132","01027",50,"Solar",null,"2025-06-26","2025-07-16",{"$f":"NETWORKDAYS(I1547,J1547,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1547,O1547,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Lanesborough","ESMAEX-05162","01237",6.9,"Solar","15E1","2025-07-07","2025-07-21",{"$f":"NETWORKDAYS(I1548,J1548,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1548,O1548,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-22",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-25","Permission to Operate"]
[null,"WMECO","Conway","ESMAEX-05133","01341",28.33,"Solar","38A1","2025-06-26","2025-08-22",{"$f":"NETWORKDAYS(I1549,J1549,MALegalHolidays)","v":42},null,42,null,null,{"$f":"NETWORKDAYS(N1549,O1549,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-17","Online",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Longmeadow","ESMAEX-05136","01106",22.8,"Solar","22H13","2025-06-27","2025-07-07",{"$f":"NETWORKDAYS(I1550,J1550,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1550,O1550,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-12","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","West Springfield","ESMAEX-05140","01089",7.6,"Solar","16C11","2025-06-27","2025-07-18",{"$f":"NETWORKDAYS(I1551,J1551,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1551,O1551,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-08","Permission to Operate",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Colrain","ESMAEX-05161","01340",15.2,"Solar","29R2","2025-07-07","2025-07-18",{"$f":"NETWORKDAYS(I1552,J1552,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1552,O1552,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-25",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-10-10","Online",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Hadley","ESMAEX-05179","01035",7.6,"Solar","17K5","2025-07-08","2025-07-14",{"$f":"NETWORKDAYS(I1553,J1553,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1553,O1553,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-14","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Southwick","ESMAEX-05197","01077",3340,"Solar","29A1","2025-09-24","2025-10-15",{"$f":"NETWORKDAYS(I1554,J1554,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1554,O1554,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"29A SOUTHWICK"]
[null,"WMECO","Turners Falls","ESMAEX-05407","01376",480,"Solar","21C2","2025-09-02","2025-09-29",{"$f":"NETWORKDAYS(I1555,J1555,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1555,O1555,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"21C MONTAGUE"]
[null,"WMECO","Russell","ESMAEX-05189","01071",15.2,"Solar","19J2","2025-07-10","2025-07-14",{"$f":"NETWORKDAYS(I1556,J1556,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1556,O1556,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Pittsfield","ESMAEX-05194","01201",10.89,"Solar","30B7","2025-07-11","2025-07-24",{"$f":"NETWORKDAYS(I1557,J1557,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1557,O1557,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-12","Online",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Huntington","ESMAEX-05195","01050",20.736000000000001,"Solar","19J5","2025-07-11","2025-07-22",{"$f":"NETWORKDAYS(I1558,J1558,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1558,O1558,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-20","Online"]
[null,"WMECO","Amherst","ESMAEX-05190","01002",5.76,"Solar","17K1","2025-07-10","2025-07-22",{"$f":"NETWORKDAYS(I1559,J1559,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1559,O1559,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Pittsfield","ESMAEX-05198","01201",400,"Solar","19A8","2025-08-08","2025-08-22",{"$f":"NETWORKDAYS(I1560,J1560,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1560,O1560,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Agawam","ESMAEX-05206","01001",7.6,"Solar","30A3","2025-07-15","2025-07-24",{"$f":"NETWORKDAYS(I1561,J1561,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1561,O1561,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-10","Online",null,null,null,null,"30A SILVER"]
[null,"WMECO","Pelham","ESMAEX-05282","01002",37.299999999999997,"Solar","17K2","2025-08-05","2025-09-08",{"$f":"NETWORKDAYS(I1562,J1562,MALegalHolidays)","v":25},null,25,null,null,{"$f":"NETWORKDAYS(N1562,O1562,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-13","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Hadley","ESMAEX-05235","01035",5.76,"Solar","18G4","2025-07-28","2025-07-29",{"$f":"NETWORKDAYS(I1563,J1563,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1563,O1563,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-19","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","South Deerfield","ESMAEX-05214","01373",19,"Solar","22B3","2025-07-18","2025-07-18",{"$f":"NETWORKDAYS(I1564,J1564,MALegalHolidays)","v":1},null,1,null,null,{"$f":"NETWORKDAYS(N1564,O1564,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-07-21",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-09-05","Online",null,null,null,19,"22B CUMBERLAND"]
[null,"WMECO","Amherst","ESMAEX-05221","01002",19.032,"Solar","18G7","2025-07-22","2025-07-29",{"$f":"NETWORKDAYS(I1565,J1565,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1565,O1565,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-14",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-11-20","Online",null,null,null,null,"18G PODICK"]
[null,"WMECO","Granville","ESMAEX-05260","01034",11.5,"Other","29A5","2025-07-31","2025-08-25",{"$f":"NETWORKDAYS(I1566,J1566,MALegalHolidays)","v":18},null,18,null,null,{"$f":"NETWORKDAYS(N1566,O1566,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-18",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,0,"29A SOUTHWICK"]
[null,"WMECO","Feeding Hills","ESMAEX-05243","01030",7.6,"Solar","16C17","2025-07-29","2025-07-31",{"$f":"NETWORKDAYS(I1567,J1567,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1567,O1567,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Hadley","ESMAEX-05251","01035",7.6,"Solar","19B15","2025-07-29","2025-08-04",{"$f":"NETWORKDAYS(I1568,J1568,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1568,O1568,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-08-14",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-27","Online",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Ludlow","ESMAEX-05272","01056",4988,"Solar & Battery","19S3","2025-08-04","2025-08-22",{"$f":"NETWORKDAYS(I1569,J1569,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1569,O1569,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-18",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,4988,"19S LUDLOW"]
[null,"WMECO","Amherst","ESMAEX-05291","01002",15.2,"Solar","17K8","2025-08-07","2025-08-20",{"$f":"NETWORKDAYS(I1570,J1570,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1570,O1570,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-01","Online",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Worthington","ESMAEX-05332","01098",7.6,"Solar & Battery","18C2","2025-08-18","2025-08-26",{"$f":"NETWORKDAYS(I1571,J1571,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1571,O1571,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-26",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-27","Online",null,null,null,null,"18C BERKSHIRE"]
[null,"WMECO","Plainfield","ESMAEX-05280","01070",4950,"Other","18K3","2025-10-02","2025-10-21",{"$f":"NETWORKDAYS(I1572,J1572,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1572,O1572,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"18K PLAINFIELD"]
[null,"WMECO","Greenfield","ESMAEX-05511","01301",67.3,"Solar","22B8","2025-09-29","2025-10-08",{"$f":"NETWORKDAYS(I1573,J1573,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1573,O1573,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Southampton","ESMAEX-05297","01073",11.4,"Solar","15A1","2025-08-08","2025-09-04",{"$f":"NETWORKDAYS(I1574,J1574,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1574,O1574,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-01",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-09","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Whately","ESMAEX-05315","01093",250,"Solar","18G8","2025-10-08","2025-10-21",{"$f":"NETWORKDAYS(I1575,J1575,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1575,O1575,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"18G PODICK"]
[null,"WMECO","Otis","ESMAEX-05411","01253",25,"Solar","19J4","2025-09-02","2025-09-16",{"$f":"NETWORKDAYS(I1576,J1576,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1576,O1576,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-08",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,"Blandford",null,20,"19J BLANDFORD"]
[null,"WMECO","West Springfield","ESMAEX-05357","01089",5.3760000000000003,"Battery","16C11","2025-08-22","2025-09-18",{"$f":"NETWORKDAYS(I1577,J1577,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1577,O1577,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-09-29",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"16C AGAWAM"]
[null,"WMECO",0,"ESMAEX-05340","01301",240,"Solar","22B7","2025-08-27","2025-09-12",{"$f":"NETWORKDAYS(I1578,J1578,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1578,O1578,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Springfield","ESMAEX-05510","01105",50,"Solar","8C15","2025-09-29","2025-10-07",{"$f":"NETWORKDAYS(I1579,J1579,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1579,O1579,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"8C WEST SPRINGFIELD"]
[null,"WMECO","Pittsfield","ESMAEX-05361","01201",15.2,"Solar","19A7","2025-08-25","2025-08-26",{"$f":"NETWORKDAYS(I1580,J1580,MALegalHolidays)","v":2},null,2,null,null,{"$f":"NETWORKDAYS(N1580,O1580,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Chicopee","ESMAEX-05362","01013",960,"Solar","21N7","2025-10-31","2025-11-11",{"$f":"NETWORKDAYS(I1581,J1581,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1581,O1581,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Standard",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"21N PIPER"]
[null,"WMECO","Agawam","ESMAEX-05364","01001",480,"Solar","30A3","2025-10-03","2025-10-15",{"$f":"NETWORKDAYS(I1582,J1582,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1582,O1582,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30A SILVER"]
[null,"WMECO","Bernardston","ESMAEX-05375","01337",499,"Solar","21C1","2025-09-22","2025-10-21",{"$f":"NETWORKDAYS(I1583,J1583,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1583,O1583,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"21C MONTAGUE"]
[null,"WMECO","Sunderland","ESMAEX-05409","01375",11.5,"Other","18G6","2025-09-02","2025-09-16",{"$f":"NETWORKDAYS(I1584,J1584,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1584,O1584,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-09",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,20,"18G PODICK"]
[null,"WMECO","Greenfield","ESMAEX-05464","01301",150,"Solar","22B6","2025-09-16","2025-11-11",{"$f":"NETWORKDAYS(I1585,J1585,MALegalHolidays)","v":41},null,41,null,null,{"$f":"NETWORKDAYS(N1585,O1585,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Middlefield","ESMAEX-05454","01243",22.8,"Solar","18C2","2025-09-15","2025-09-22",{"$f":"NETWORKDAYS(I1586,J1586,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1586,O1586,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-03","Online",null,null,null,null,"18C BERKSHIRE"]
[null,"WMECO","Easthampton","ESMAEX-05559","01027",50,"Solar","15A3","2025-10-09","2025-10-21",{"$f":"NETWORKDAYS(I1587,J1587,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1587,O1587,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"15A GUNN"]
[null,"WMECO","Longmeadow","ESMAEX-05468","01106",15.2,"Solar","22H18","2025-09-17","2025-09-29",{"$f":"NETWORKDAYS(I1588,J1588,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1588,O1588,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-20",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-09","Online",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Pittsfield","ESMAEX-05474","01201",480,"Solar","15E2","2025-10-15","2025-10-24",{"$f":"NETWORKDAYS(I1589,J1589,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1589,O1589,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-10",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"15E PARTRIDGE"]
[null,"WMECO","Southwick","ESMAEX-05487","01077",450,"Solar","29A1","2025-10-24","2025-11-11",{"$f":"NETWORKDAYS(I1590,J1590,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1590,O1590,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"29A SOUTHWICK"]
[null,"WMECO","Lanesborough","ESMAEX-05493","01237",23,"Other","30B5","2025-09-22","2025-10-21",{"$f":"NETWORKDAYS(I1591,J1591,MALegalHolidays)","v":22},null,22,null,null,{"$f":"NETWORKDAYS(N1591,O1591,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"30B OSWALD"]
[null,"WMECO","West Springfield","ESMAEX-05513","01089",30,"Solar",null,"2025-09-25","2025-10-16",{"$f":"NETWORKDAYS(I1592,J1592,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1592,O1592,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement "]
[null,"WMECO","Southwick","ESMAEX-05501","01077",160,"Solar","29A1","2025-09-23","2025-10-08",{"$f":"NETWORKDAYS(I1593,J1593,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1593,O1593,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"29A SOUTHWICK"]
[null,"WMECO","Easthampton","ESMAEX-05523","01027",11.5,"Solar & Battery","15A1","2025-09-29","2025-10-07",{"$f":"NETWORKDAYS(I1594,J1594,MALegalHolidays)","v":7},null,{"$f":"IF(K1594>0,K1594-L1594,\" \")","v":7},null,null,{"$f":"NETWORKDAYS(N1594,O1594,MALegalHolidays)","v":0},null,{"$f":"IF(P1594>0,P1594-Q1594,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1594>0,U1594-V1594,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1594>0,Z1594-AA1594,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1594>0,AE1594-AF1594,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1594>0,AJ1594-AK1594,\" \")","v":" "},"2025-11-07",null,null,null,"Expedited",null,null,null,null,null,{"$f":"IF(AU1594>0,AU1594-AV1594,\" \")","v":" "},null,null,null,"Compliances Documents",null,null,null,null,"15A GUNN"]
[null,"WMECO","Lanesborough","ESMAEX-05508","01237",6,"Solar","15E1","2025-09-24","2025-10-14",{"$f":"NETWORKDAYS(I1595,J1595,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1595,O1595,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage"]
[null,"WMECO","Easthampton","ESMAEX-05524","01027",11.5,"Solar & Battery","15A5","2025-09-29","2025-10-02",{"$f":"NETWORKDAYS(I1596,J1596,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1596,O1596,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-01-27","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Hatfield","ESMAEX-05525","01038",19.8,"Solar",null,"2025-09-29","2025-10-07",{"$f":"NETWORKDAYS(I1597,J1597,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1597,O1597,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-10-15",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2025-12-31","Online"]
[null,"WMECO","Ludlow","ESMAEX-05526","01056",360,"Solar","27A5","2025-11-11","2025-11-21",{"$f":"NETWORKDAYS(I1598,J1598,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1598,O1598,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Amherst","ESMAEX-05535","01002",240,"Other","17K3","2025-10-02","2025-10-15",{"$f":"NETWORKDAYS(I1599,J1599,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1599,O1599,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Lee","ESMAEX-05536","01238",250,"Solar","16B5","2025-10-03","2025-10-14",{"$f":"NETWORKDAYS(I1600,J1600,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1600,O1600,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,249,"16B PLEASANT"]
[null,"WMECO","Agawam","ESMAEX-05539","01001",70,"Solar","30A3","2025-10-03","2025-10-15",{"$f":"NETWORKDAYS(I1601,J1601,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1601,O1601,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"30A SILVER"]
[null,"WMECO","Pelham","ESMAEX-05613","01002",18.666,"Solar","17K2","2025-10-23","2025-11-13",{"$f":"NETWORKDAYS(I1602,J1602,MALegalHolidays)","v":16},null,16,null,null,{"$f":"NETWORKDAYS(N1602,O1602,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Becket","ESMAEX-05552","01223",4999,"Solar","16B1","2025-10-06","2025-10-24",{"$f":"NETWORKDAYS(I1603,J1603,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1603,O1603,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,4999,"16B PLEASANT"]
[null,"WMECO","Otis","ESMAEX-05624","01253",34.520000000000003,"Solar & Battery","19J4","2025-10-23","2025-11-05",{"$f":"NETWORKDAYS(I1604,J1604,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1604,O1604,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-27",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Review",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Feeding Hills","ESMAEX-05769","01030",17.48,"Solar","30A1","2025-11-24","2025-12-01",{"$f":"NETWORKDAYS(I1605,J1605,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1605,O1605,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Meter",null,null,null,null,"30A SILVER"]
[null,"WMECO","South Deerfield","ESMAEX-05590","01373",17.16,"Solar","18G3","2025-10-15","2025-10-22",{"$f":"NETWORKDAYS(I1606,J1606,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1606,O1606,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-17",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"18G PODICK"]
[null,"WMECO","Southampton","ESMAEX-05731","01073",2988,"Solar & Battery","15A1","2025-11-11","2025-11-17",{"$f":"NETWORKDAYS(I1607,J1607,MALegalHolidays)","v":5},null,5,null,null,{"$f":"NETWORKDAYS(N1607,O1607,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"15A GUNN"]
[null,"WMECO","Greenfield","ESMAEX-05596","01301",50,"Solar",null,"2025-10-16","2025-10-28",{"$f":"NETWORKDAYS(I1608,J1608,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1608,O1608,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-11-07",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Deerfield","ESMAEX-05662","01342",80,"Solar","22B3","2025-10-31","2025-11-17",{"$f":"NETWORKDAYS(I1609,J1609,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1609,O1609,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Pittsfield","ESMAEX-05603","01201",15.2,"Solar","19A1","2025-10-20","2025-10-31",{"$f":"NETWORKDAYS(I1610,J1610,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1610,O1610,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-23",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"19A DOREEN"]
[null,"WMECO","Turners Falls","ESMAEX-05623","01376",4950,"Other","21C2","2026-01-21","2026-02-05",{"$f":"NETWORKDAYS(I1611,J1611,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1611,O1611,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,4950,"21C MONTAGUE"]
[null,"WMECO","Pittsfield","ESMAEX-05629","01201",5.76,"Solar","30B1","2025-10-24","2025-10-28",{"$f":"NETWORKDAYS(I1612,J1612,MALegalHolidays)","v":3},null,3,null,null,{"$f":"NETWORKDAYS(N1612,O1612,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30B OSWALD"]
[null,"WMECO",0,"ESMAEX-05636","02137",499,"Solar","15E2","2025-11-19","2025-12-03",{"$f":"NETWORKDAYS(I1613,J1613,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1613,O1613,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,499,"15E PARTRIDGE"]
[null,"WMECO","Sandisfield","ESMAEX-05694","01255",7.59,"Solar & Battery","19J4","2025-11-04","2025-11-12",{"$f":"NETWORKDAYS(I1614,J1614,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1614,O1614,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-24","Online",null,"Blandford",null,null,"19J BLANDFORD"]
[null,"WMECO","Westhampton","ESMAEX-05689","01770",499,"Solar","15A3","2025-11-03","2025-11-12",{"$f":"NETWORKDAYS(I1615,J1615,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1615,O1615,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"15A GUNN"]
[null,"WMECO","Greenfield","ESMAEX-05737","01301",17.16,"Solar","22B2","2025-11-12","2025-12-30",{"$f":"NETWORKDAYS(I1616,J1616,MALegalHolidays)","v":35},null,35,null,null,{"$f":"NETWORKDAYS(N1616,O1616,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-22",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Pittsfield","ESMAEX-05699","01201",11.5,"Other","30B3","2025-11-05","2025-12-02",{"$f":"NETWORKDAYS(I1617,J1617,MALegalHolidays)","v":20},null,20,null,null,{"$f":"NETWORKDAYS(N1617,O1617,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Springfield","ESMAEX-05711","01105",15.2,"Solar & Battery","21S4","2025-11-07","2025-11-20",{"$f":"NETWORKDAYS(I1618,J1618,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1618,O1618,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,20,"21S CLINTON"]
[null,"WMECO","Springfield","ESMAEX-05724","01104",10,"Solar","5J16","2025-11-10","2025-11-13",{"$f":"NETWORKDAYS(I1619,J1619,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1619,O1619,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"5J EAST SPRINGFIELD"]
[null,"WMECO","Amherst","ESMAEX-05823","01002",999,"Solar",null,"2025-12-10",null,{"$f":"NETWORKDAYS(I1620,J1620,MALegalHolidays)","v":-32807},null," ",null,null,{"$f":"NETWORKDAYS(N1620,O1620,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review"]
[null,"WMECO","Hadley","ESMAEX-05721","01035",250,"Solar","17K1","2025-12-04","2025-12-17",{"$f":"NETWORKDAYS(I1621,J1621,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1621,O1621,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Hadley","ESMAEX-05722","01035",999,"Solar","17K1","2025-12-04","2025-12-17",{"$f":"NETWORKDAYS(I1622,J1622,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1622,O1622,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,999,"17K AMHERST"]
[null,"WMECO","Easthampton","ESMAEX-05734","01027",5.7,"Solar","15A5","2025-11-11","2025-12-01",{"$f":"NETWORKDAYS(I1623,J1623,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1623,O1623,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"15A GUNN"]
[null,"WMECO","Easthampton","ESMAEX-05740","01027",15.2,"Solar","15A5","2025-11-13","2025-12-01",{"$f":"NETWORKDAYS(I1624,J1624,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1624,O1624,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2025-12-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,"2026-02-24","Online",null,null,null,null,"15A GUNN"]
[null,"WMECO","Pittsfield","ESMAEX-05745","01201",3.8,"Solar & Battery","15E2","2025-11-17","2025-12-03",{"$f":"NETWORKDAYS(I1625,J1625,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1625,O1625,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Lanesborough","ESMAEX-05849","01237",13.36,"Solar & Battery","15E1","2025-12-18","2026-01-09",{"$f":"NETWORKDAYS(I1626,J1626,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1626,O1626,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Ashfield","ESMAEX-05754","01330",499,"Solar","38A1","2025-11-18","2025-12-03",{"$f":"NETWORKDAYS(I1627,J1627,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1627,O1627,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Longmeadow","ESMAEX-05758","01106",7.2,"Solar","22H11","2025-11-19","2025-12-01",{"$f":"NETWORKDAYS(I1628,J1628,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1628,O1628,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Pittsfield","ESMAEX-05761","01201",3.8,"Solar & Battery","30B7","2025-11-19","2025-12-03",{"$f":"NETWORKDAYS(I1629,J1629,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1629,O1629,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-03-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30B OSWALD"]
[null,"WMECO","West Springfield","ESMAEX-05785","01089",140,"Solar","21N9","2025-12-02","2025-12-05",{"$f":"NETWORKDAYS(I1630,J1630,MALegalHolidays)","v":4},null,4,null,null,{"$f":"NETWORKDAYS(N1630,O1630,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"21N PIPER"]
[null,"WMECO","Hinsdale","ESMAEX-05763","01235",15.2,"Solar","18C2","2025-11-20","2026-03-03",{"$f":"NETWORKDAYS(I1631,J1631,MALegalHolidays)","v":74},null,74,null,null,{"$f":"NETWORKDAYS(N1631,O1631,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"18C BERKSHIRE"]
[null,"WMECO","Hadley","ESMAEX-05820","01035",999,"Solar","19B15","2026-01-29","2026-02-18",{"$f":"NETWORKDAYS(I1632,J1632,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1632,O1632,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Standard",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Pelham","ESMAEX-05789","01002",16,"Other","17K2","2025-12-02","2026-03-09",{"$f":"NETWORKDAYS(I1633,J1633,MALegalHolidays)","v":70},null,70,null,null,{"$f":"NETWORKDAYS(N1633,O1633,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Springfield","ESMAEX-05780","01108",5.76,"Solar & Battery","22H15","2025-11-29","2025-12-11",{"$f":"NETWORKDAYS(I1634,J1634,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1634,O1634,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO",0,"ESMAEX-05787","01001",4998,"Other","30A3","2025-12-02","2026-01-29",{"$f":"NETWORKDAYS(I1635,J1635,MALegalHolidays)","v":43},null,43,null,null,{"$f":"NETWORKDAYS(N1635,O1635,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Complex",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"30A SILVER"]
[null,"WMECO","Springfield","ESMAEX-05784","01128",15.2,"Solar","20A21","2025-12-01","2025-12-09",{"$f":"NETWORKDAYS(I1636,J1636,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1636,O1636,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-02",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Construction Stage",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Deerfield","ESMAEX-05790","01342",12,"Solar & Battery","22B7","2025-12-03","2025-12-16",{"$f":"NETWORKDAYS(I1637,J1637,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1637,O1637,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-22",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,17.5,"22B CUMBERLAND"]
[null,"WMECO","Springfield","ESMAEX-05824","01107",11.5,"Solar & Battery","21S6","2025-12-10","2025-12-23",{"$f":"NETWORKDAYS(I1638,J1638,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1638,O1638,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-13",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Peru","ESMAEX-05803","01235",9.8819999999999997,"Solar & Battery","18C2","2025-12-05","2025-12-16",{"$f":"NETWORKDAYS(I1639,J1639,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1639,O1639,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"18C BERKSHIRE"]
[null,"WMECO","Springfield","ESMAEX-05808","01128",966,"Solar","20A34","2026-01-09","2026-01-22",{"$f":"NETWORKDAYS(I1640,J1640,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1640,O1640,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Agawam","ESMAEX-05810","01001",480,"Solar","30A3","2026-01-20","2026-01-29",{"$f":"NETWORKDAYS(I1641,J1641,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1641,O1641,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"30A SILVER"]
[null,"WMECO","South Deerfield","ESMAEX-05818","01373",5.76,"Solar","18G6","2025-12-09","2026-01-21",{"$f":"NETWORKDAYS(I1642,J1642,MALegalHolidays)","v":32},null,32,null,null,{"$f":"NETWORKDAYS(N1642,O1642,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-05821","01109",11.5,"Solar & Battery","20A32","2025-12-10","2026-01-05",{"$f":"NETWORKDAYS(I1643,J1643,MALegalHolidays)","v":19},null,19,null,null,{"$f":"NETWORKDAYS(N1643,O1643,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"20A BRECKWOOD"]
[null,"WMECO","Feeding Hills","ESMAEX-05822","01030",11.5,"Solar & Battery","30A1","2025-12-10","2025-12-23",{"$f":"NETWORKDAYS(I1644,J1644,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1644,O1644,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"30A SILVER"]
[null,"WMECO","West Springfield","ESMAEX-05888","01089",3.8,"Solar & Battery",null,"2025-12-29","2026-01-14",{"$f":"NETWORKDAYS(I1645,J1645,MALegalHolidays)","v":13},null,13,null,null,{"$f":"NETWORKDAYS(N1645,O1645,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,13]
[null,"WMECO","West Springfield","ESMAEX-05842","01089",16.512,"Solar","21N4","2025-12-16","2026-01-05",{"$f":"NETWORKDAYS(I1646,J1646,MALegalHolidays)","v":15},null,15,null,null,{"$f":"NETWORKDAYS(N1646,O1646,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"21N PIPER"]
[null,"WMECO","New Ashford","ESMAEX-05840","01237",20,"Solar","1.50E+02","2025-12-15","2026-01-26",{"$f":"NETWORKDAYS(I1647,J1647,MALegalHolidays)","v":31},null,31,null,null,{"$f":"NETWORKDAYS(N1647,O1647,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-30",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"15E PARTRIDGE"]
[null,"WMECO","Ludlow","ESMAEX-05832","01056",15.2,"Solar","19S1","2025-12-11","2025-12-23",{"$f":"NETWORKDAYS(I1648,J1648,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1648,O1648,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-06",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"19S LUDLOW"]
[null,"WMECO","Northfield","ESMAEX-05833","01360",22.96,"Solar","21B8","2025-12-12",null,{"$f":"NETWORKDAYS(I1649,J1649,MALegalHolidays)","v":-32809},null," ",null,null,{"$f":"NETWORKDAYS(N1649,O1649,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"21B FRENCH KING"]
[null,"WMECO","Pelham","ESMAEX-05845","01002",9.984,"Solar","17K2","2025-12-17","2025-12-30",{"$f":"NETWORKDAYS(I1650,J1650,MALegalHolidays)","v":10},null,10,null,null,{"$f":"NETWORKDAYS(N1650,O1650,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-01-28",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Colrain","ESMAEX-05878","01340",249,"Solar","29R2","2025-12-23","2026-01-07",{"$f":"NETWORKDAYS(I1651,J1651,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1651,O1651,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Colrain","ESMAEX-05879","01340",249,"Solar","29R2","2025-12-23","2026-01-07",{"$f":"NETWORKDAYS(I1652,J1652,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1652,O1652,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"29R SHELBURNE"]
[null,"WMECO","Westhampton","ESMAEX-05900","01027",75,"Solar","15A3","2026-01-05","2026-01-22",{"$f":"NETWORKDAYS(I1653,J1653,MALegalHolidays)","v":14},null,14,null,null,{"$f":"NETWORKDAYS(N1653,O1653,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-18",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,null,"15A GUNN"]
[null,"WMECO","Conway","ESMAEX-05906","01341",15.2,"Solar","38A1","2026-01-06","2026-01-14",{"$f":"NETWORKDAYS(I1654,J1654,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1654,O1654,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"38A ASHFIELD"]
[null,"WMECO","Hadley","ESMAEX-05909","01035",23,"Solar & Battery","19B15","2026-01-07","2026-01-21",{"$f":"NETWORKDAYS(I1655,J1655,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1655,O1655,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"19B MIDWAY"]
[null,"WMECO","Leyden","ESMAEX-05917","01337",7.6,"Solar","22B7","2026-01-09","2026-01-21",{"$f":"NETWORKDAYS(I1656,J1656,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1656,O1656,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-11",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"22B CUMBERLAND"]
[null,"WMECO","Amherst","ESMAEX-05943","01002",80,"Solar","17K5","2026-01-16","2026-01-27",{"$f":"NETWORKDAYS(I1657,J1657,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1657,O1657,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-05",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"ISA Agreement ",null,null,null,-100,"17K AMHERST"]
[null,"WMECO","Springfield","ESMAEX-05920","01104",5.76,"Solar & Battery","5J12","2026-01-12","2026-01-22",{"$f":"NETWORKDAYS(I1658,J1658,MALegalHolidays)","v":9},null,{"$f":"IF(K1658>0,K1658-L1658,\" \")","v":9},null,null,{"$f":"NETWORKDAYS(N1658,O1658,MALegalHolidays)","v":0},null,{"$f":"IF(P1658>0,P1658-Q1658,\" \")","v":" "},null,null,null,null,{"$f":"IF(U1658>0,U1658-V1658,\" \")","v":" "},null,null,null,null,{"$f":"IF(Z1658>0,Z1658-AA1658,\" \")","v":" "},null,null,null,null,{"$f":"IF(AE1658>0,AE1658-AF1658,\" \")","v":" "},null,null,null,null,{"$f":"IF(AJ1658>0,AJ1658-AK1658,\" \")","v":" "},"2026-02-03",null,null,null,"Expedited",null,null,null,null,null,{"$f":"IF(AU1658>0,AU1658-AV1658,\" \")","v":" "},null,null,null,"Compliances Documents",null,null,null,10,"5J EAST SPRINGFIELD"]
[null,"WMECO","Greenfield","ESMAEX-05954","01301",22.8,"Solar",null,"2026-01-22","2026-02-02",{"$f":"NETWORKDAYS(I1659,J1659,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1659,O1659,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-12",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents"]
[null,"WMECO","Amherst","ESMAEX-05946","01002",15.2,"Solar","17K8","2026-01-20","2026-01-28",{"$f":"NETWORKDAYS(I1660,J1660,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1660,O1660,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ","2026-02-04",null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Compliances Documents",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Ludlow","ESMAEX-05948","01056",15.2,"Solar","27A6","2026-01-20","2026-01-27",{"$f":"NETWORKDAYS(I1661,J1661,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1661,O1661,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"27A ORCHARD"]
[null,"WMECO","Huntington","ESMAEX-05951","01050",18.43,"Solar","19J5","2026-01-20","2026-02-04",{"$f":"NETWORKDAYS(I1662,J1662,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1662,O1662,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review"]
[null,"WMECO","Richmond","ESMAEX-05959","01254",7.6,"Solar","30B2","2026-01-23",null,{"$f":"NETWORKDAYS(I1663,J1663,MALegalHolidays)","v":-32839},null," ",null,null,{"$f":"NETWORKDAYS(N1663,O1663,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"30B OSWALD"]
[null,"WMECO","Savoy","ESMAEX-05961","01256",15.2,"Solar","18K4","2026-01-26","2026-02-02",{"$f":"NETWORKDAYS(I1664,J1664,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1664,O1664,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review"]
[null,"WMECO","Pittsfield","ESMAEX-05965","01201",30,"Solar & Battery","30B5","2026-01-27",null,{"$f":"NETWORKDAYS(I1665,J1665,MALegalHolidays)","v":-32841},null," ",null,null,{"$f":"NETWORKDAYS(N1665,O1665,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,20,"30B OSWALD"]
[null,"WMECO","Bernardston","ESMAEX-05975","01337",22.8,"Solar","21C1","2026-02-02","2026-02-09",{"$f":"NETWORKDAYS(I1666,J1666,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1666,O1666,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"21C MONTAGUE"]
[null,"WMECO","Springfield","ESMAEX-05970","01128",23,"Solar & Battery","20A34","2026-01-28","2026-02-19",{"$f":"NETWORKDAYS(I1667,J1667,MALegalHolidays)","v":17},null,17,null,null,{"$f":"NETWORKDAYS(N1667,O1667,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,15,"20A BRECKWOOD"]
[null,"WMECO","Sunderland","ESMAEX-05988","01375",5.76,"Solar","18G6","2026-02-04","2026-02-12",{"$f":"NETWORKDAYS(I1668,J1668,MALegalHolidays)","v":7},null,7,null,null,{"$f":"NETWORKDAYS(N1668,O1668,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"18G PODICK"]
[null,"WMECO","Springfield","ESMAEX-05993","01108",23.42,"Solar","21S5","2026-02-06","2026-02-13",{"$f":"NETWORKDAYS(I1669,J1669,MALegalHolidays)","v":6},null,6,null,null,{"$f":"NETWORKDAYS(N1669,O1669,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Supplemental Designer",null,null,null,null,"21S CLINTON"]
[null,"WMECO","Longmeadow","ESMAEX-05999","01106",10,"Solar","22H17","2026-02-10","2026-02-20",{"$f":"NETWORKDAYS(I1670,J1670,MALegalHolidays)","v":9},null,9,null,null,{"$f":"NETWORKDAYS(N1670,O1670,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"22H FRANCONIA"]
[null,"WMECO","Millers Falls","ESMAEX-06000","01349",7.6,"Solar","21C8","2026-02-10",null,{"$f":"NETWORKDAYS(I1671,J1671,MALegalHolidays)","v":-32851},null," ",null,null,{"$f":"NETWORKDAYS(N1671,O1671,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,null,"21C MONTAGUE"]
[null,"WMECO","Agawam","ESMAEX-06008","01001",100,"Solar","30A1","2026-02-11",null,{"$f":"NETWORKDAYS(I1672,J1672,MALegalHolidays)","v":-32852},null," ",null,null,{"$f":"NETWORKDAYS(N1672,O1672,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,null,"30A SILVER"]
[null,"WMECO","Agawam","ESMAEX-06011","01001",100,"Solar","16C16","2026-02-13","2026-02-27",{"$f":"NETWORKDAYS(I1673,J1673,MALegalHolidays)","v":11},null,11,null,null,{"$f":"NETWORKDAYS(N1673,O1673,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Agawam","ESMAEX-06018","01001",150,"Solar","16C18","2026-02-18","2026-02-27",{"$f":"NETWORKDAYS(I1674,J1674,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1674,O1674,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"16C AGAWAM"]
[null,"WMECO","Amherst","ESMAEX-06022","01002",19.96,"Solar","17K8","2026-02-19","2026-03-02",{"$f":"NETWORKDAYS(I1675,J1675,MALegalHolidays)","v":8},null,8,null,null,{"$f":"NETWORKDAYS(N1675,O1675,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"17K AMHERST"]
[null,"WMECO","Agawam","ESMAEX-06025","01001",150,"Solar","30A4","2026-02-20","2026-03-09",{"$f":"NETWORKDAYS(I1676,J1676,MALegalHolidays)","v":12},null,12,null,null,{"$f":"NETWORKDAYS(N1676,O1676,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Technical Review",null,null,null,null,"30A SILVER"]
[null,"WMECO","Amherst","ESMAEX-06041","01002",11.5,"Solar & Battery","17K8","2026-02-25",null,{"$f":"NETWORKDAYS(I1677,J1677,MALegalHolidays)","v":-32862},null," ",null,null,{"$f":"NETWORKDAYS(N1677,O1677,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,6.6,"17K AMHERST"]
[null,"WMECO","Bernardston","ESMAEX-06043","01337",30,"Solar & Battery","21B8","2026-02-25",null,{"$f":"NETWORKDAYS(I1678,J1678,MALegalHolidays)","v":-32862},null," ",null,null,{"$f":"NETWORKDAYS(N1678,O1678,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"On Hold",null,null,null,15,"21B FRENCH KING"]
[null,"WMECO","Middlefield","ESMAEX-06047","01243",23,"Solar & Battery","UNLINKED","2026-02-26",null,{"$f":"NETWORKDAYS(I1679,J1679,MALegalHolidays)","v":-32863},null," ",null,null,{"$f":"NETWORKDAYS(N1679,O1679,MALegalHolidays)","v":0},null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null," ",null,null,null,null,"Expedited",null,null,null,null,null," ",null,null,null,"Application Review",null,null,null,10]

{"sheet":"Sheet1","index":2,"n_rows":95,"n_cols":2,"rows_kept":95,"cut":false,"hidden":false,"merged":[]}
["DOER Status","Raw Data Enterprise Report Status"]
["Online","Application Completed/Closed"]
["Application Review"," Awaiting Work Order Number"]
["Application Review","Eversource Waiting For Payment"]
["Application Review","Incomplete Application  Customer Action Required"]
["Application Review","Awaiting App Fee and/or Further Info"]
["Application Review","Awaiting Fee"]
["Technical Review","Eversource Initiated Technical Review"]
["Technical Review","Eversource Technical Review Completed"]
["Technical Review","Initiate Additional Technical Review"]
["Technical Review","Additional Technical Details Required - Customer Action Required"]
["Technical Review","Additional Details Required for CR - Customer Action Required"]
["Technical Review","Eversource Review Schedule Z"]
["Technical Review","Eversource QF - Schedule Z Review"]
["Technical Review","Eversource Initiate Detailed Study"]
["Technical Review","Additional Technical Review Completed"]
["Technical Review","Initiate Application Additional Review"]
["Engineering Review","Awaiting Response and/or Cost Estimates from Eng"]
["Engineering Review","Eng Stage: Awaiting Customer's Response/Docs"]
["Engineering Review","Engineering Review Stage"]
["Engineering Review","Engineering Screen Review"]
["Engineering Review","Engineering Screen Review Desn1 Stage"]
["Engineering Review","Eng Screen Review: Awaiting Customer's Response/Docs"]
["Impact Study","Eng.  Impact Study"]
["Impact Study","Eng Impct Stdy:Awaiting Customers Response/Doc"]
["Impact Study","Awaiting Impact Study WO"]
["Impact Study","Awaiting Impact Study Fee & Agreement"]
["Impact Study","Impact Study Stage"]
["Impact Study","Impact Study Started"]
["Impact Study","Awaiting Maximo WO"]
["Impact Study","Impact Study Hold"]
["ISA Agreement ","ISA Received/Signed"]
["ISA Agreement ","ISA sent"]
["ISA Agreement ","Awaiting ISA Receipt/Approval"]
["ISA Agreement ","Amended ISA Agreement - Customer Action Required"]
["ISA Agreement ","Customer ISA eSignature Completed"]
["ISA Agreement ","Amended ISA Agreement  Customer Action Required"]
["ISA Agreement ","Missing Agreement Sign  Customer Action Required"]
["ISA Agreement ","Eversource Sent ISA Agreement - Customer Action Required"]
["ISA Agreement ","Customer Accepted ISA Agreement"]
["Withdrawn","Application Withdrawn"]
["Design Stage","Design Approval"]
["Construction Stage","Eversource Initiated Construction"]
["Meter","Eversource Initiate Meter Installation"]
["Meter","Meter Review"]
["Meter","Wiring Issues"]
["Permission to Operate","Ready for PTO"]
["Permission to Operate","Permission to Operate"]
["Permission to Operate","Final Close Out Documents - Customer Action Required"]
["Compliances Documents","Submit Compliances Documents"]
["Compliances Documents","Missing Documents - Customer Action Required"]
["Compliances Documents","Awaiting Completion Docs"]
["Compliances Documents","Awaiting Completion Docs and NSTARwork completion"]
["Compliances Documents","Missing Documents - Customer Action Required"]
["Compliances Documents","Missing Agreement Sign - Customer Action Required"]
["Compliances Documents","Incomplete Application - Customer Action Required"]
["Compliances Documents","Initiated Eversource Document Verification"]
["Compliances Documents","Waiting for Customer's Response / Revised Docs"]
["Witness Test","Witness Test Awaiting Cust Response/Doc"]
["Customer Cost","Customer Cost"]
["Cust Docs","Cust Docs"]
["Decommissioned","Decommissioned"]
["Detailed Study Stage","Detailed Study Stage"]
["Exhibit E Agreement","Exhibit E Agreement - Customer Action Required"]
["Field Com","Field Com"]
["Cluster Study","hold  cluster"]
["In Queue","In Queue"]
["Rights & Rights/Customer Cost","Same as the status"]
["Study","Waiting for the Study of a Nearby System"]
["In Queue",""]
["Compliances Documents","Missing Schedule Z Details - Customer Action Required"]
["On Hold","On Hold"]
["Compliances Documents","Request Customer Care For Additional Details"]
["ISA Agreement ","Request ISA - Customer Action Required"]
["Compliances Documents","Supplemental Review Completed"]
["Meter","Wiring Issue - Customer Action Required"]
["Compliance Documents","Request Project Changes - Customer Action Required"]
["Application Review","Eversource Perform Initial Review"]
["Technical Review","Post ISA Technical Review"]
["Technical Review","Upload Technical Documents Customer Action Required"]
["Compliance Documents","Upload Technical Documents (Impact Study)– Customer Action Required"]
["Impact Study","Impact Study Review"]
["ISA Agreement ","Permission To Install/ISA Approval"]
["Impact Study ","Impact Study Completed"]
["Cancelled","Cancelled"]
["On Hold","CIP On Hold"]
["ISA Agreement ","Awaiting Supplemental WO"]
["Application Review","Customer Exhibit D eSignature Completed"]
["Application Review","Eversource Waiting for Supp Review Check"]
["Application Review","Exhibit D Agreement Customer Action Required"]
["Impact Study","Impact Study Approval"]
["Meter Review Rejected - Customer Action","Meter Review Rejected - Customer Action Required"]
["Supplemental Designer","Supplemental Designer Review"]
["Transmission","Transmission Study"]
["Supplemental Review","Supplemental Review Started"]

{"sheet":"Holiday","index":3,"n_rows":71,"n_cols":3,"rows_kept":71,"cut":false,"hidden":false,"merged":[[1,1,1,2],[2,1,2,2]]}
[]
[null,"Holiday List 2012-2014"]
[null,"(official Massachusetts Legal Holidays - Sec of State Office)"]
[null,"And WMECO Holidays"]
[null,"New Year’s Day","2012-01-02"]
[null,"Martin Luther King Jr. Birthday","2012-01-16"]
[null,"Washington’s Birthday","2012-02-20"]
[null,"Evacuation Day","2012-03-17"]
[null,"Patriots' Day","2012-04-16"]
[null,"Memorial Day ","2012-05-28"]
[null,"Bunker Hill Day","2012-06-17"]
[null,"Independence Day ","2012-07-04"]
[null,"Labor Day ","2012-09-03"]
[null,"Columbus Day","2012-10-08"]
[null,"Veterans’ Day","2012-11-12"]
[null,"Thanksgiving Day","2012-11-22"]
[null,"Day after Thanksgiving Day WMECO","2012-11-23"]
[null,"Christmas Day","2012-12-25"]
[null,"New Year’s Day","2013-01-01"]
[null,"Martin Luther King Jr. Birthday","2013-01-21"]
[null,"Washington’s Birthday","2013-02-18"]
[null,"Evacuation Day","2013-03-17"]
[null,"Patriots' Day","2013-04-15"]
[null,"Memorial Day ","2013-05-27"]
[null,"Bunker Hill Day","2013-06-17"]
[null,"Independence Day ","2013-07-04"]
[null,"Labor Day ","2013-09-02"]
[null,"Columbus Day","2013-10-14"]
[null,"Veterans’ Day","2013-11-11"]
[null,"Thanksgiving Day","2013-11-28"]
[null,"Day after Thanksgiving Day WMECO","2013-11-29"]
[null,"Christmas Day","2013-12-25"]
[null,"New Year’s Day","2014-01-01"]
[null,"Martin Luther King Jr. Birthday","2014-01-20"]
[null,"Washington’s Birthday","2014-02-17"]
[null,"Evacuation Day","2014-03-17"]
[null,"Patriots' Day","2014-04-21"]
[null,"Memorial Day ","2014-05-26"]
[null,"Bunker Hill Day","2014-06-17"]
[null,"Independence Day ","2014-07-04"]
[null,"Labor Day ","2014-09-01"]
[null,"Columbus Day","2014-10-13"]
[null,"Veterans’ Day","2014-11-11"]
[null,"Thanksgiving Day","2014-11-27"]
[null,"Christmas Day","2014-12-25"]
[null,"New Year’s Day","2015-01-01"]
[null,"Martin Luther King Jr. Birthday","2015-01-19"]
[null,"Washington’s Birthday","2015-02-16"]
[null,"Evacuation Day","2015-03-17"]
[null,"Patriots' Day","2015-04-20"]
[null,"Memorial Day ","2015-05-25"]
[null,"Bunker Hill Day","2015-06-17"]
[null,"Independence Day ","2015-07-03"]
[null,"Labor Day ","2015-09-07"]
[null,"Columbus Day","2015-10-12"]
[null,"Veterans’ Day","2015-11-11"]
[null,"Thanksgiving Day","2015-11-26"]
[null,"Christmas Day","2015-12-25"]
[null,"New Year’s Day","2016-01-01"]
[null,"Martin Luther King Jr. Birthday","2016-01-18"]
[null,"Washington’s Birthday","2016-02-15"]
[null,"Evacuation Day","2016-03-17"]
[null,"Patriots' Day","2016-04-18"]
[null,"Memorial Day ","2016-05-30"]
[null,"Bunker Hill Day","2016-06-17"]
[null,"Independence Day ","2016-07-04"]
[null,"Labor Day ","2016-09-05"]
[null,"Columbus Day","2016-10-10"]
[null,"Veterans’ Day","2016-11-11"]
[null,"Thanksgiving Day","2016-11-24"]
[null,"Christmas Day","2016-12-26"]