## DOER
Company Name | City/Town | Facility ID | Zip Code | Design Capacity (kW) | Fuel Type | Circuit Name | Date Application Received | Date Application Deemed Complete | Application Receipt Total Time Lapsed (Workdays) | Application Receipt Customer Time Lapsed (Workdays) | Application Receipt Utility Time Lapsed (Workdays) | Date of Screen Study Began | Date of Screen Study Completed | Screen Review Total Time Lapsed (Workdays) | Screen Review Customer Time Lapsed (Workdays) | Screen Review Utility Time Lapsed (Workdays) | Date Supplemental Review Began | Date Supplemental Review Complete | Supplemental Review Total Time Lapsed (Workdays) | Supplemental Review Customer Time Lapsed (Workdays) | Supplemental Review Utility Time Lapsed (Workdays) | Date Standard Process Initial Review Began | Date Standard Process Initial Review Complete | Standard Process Total Time Lapsed (Workdays) | Standard Process Customer Time Lapsed (Workdays) | Standard Process Utility Time Lapsed (Workdays) | Date Impact Study Begun | Date Impact Study Sent | Impact Study Total Time Lapsed (Workdays) | Impact Study Customer Time Lapsed (Workdays) | Impact Study Utility Time Lapsed (Workdays) | Date Detailed Study Began | Date Detailed Study Sent | Detailed Study Total Time Lapsed (Workdays) | Detailed Study Customer Time Lapsed (Workdays) | Detailed Study Utility Time Lapsed (Workdays) | Date Interconnection Agreement Sent | Date ISA & Payment Received | Estimated In-Service Date | System Modification Required | Expedited/Standard/Complex Project | Construction Timeline Commitment (Workdays) | Date Construction Began | Date Construction Completed | Construction Total Time Lapsed (Workdays) | Construction Customer Time Lapsed (Workdays) | Construction Utility Time Lapsed (Workdays) | Date Witness Test Scheduled | Date Witness Test Completed | Authorization to Interconnect | Status | Private/Gov't | Net Metered? (Y/N) | Date of Info Request (NGrid Missing) | Group Study | Group Study Designation | Impact_Group_Study_Name | ASO_Group_Name | Limiting Export Max Size kW | Substation_Name
National Grid | ATHOL | 195816 | 01331 | 4200 | Solar | 05_09_705W4 | 09/14/2018 | 10/05/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2018 | 11/08/2018 | 62 | 14 | 48 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | WENHAM | 252036 | 01984 | 0 | Solar | 05_12_51T1 | 09/04/2019 | 09/11/2019 | 4 | 0 | 4 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 |  | 12/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Scoping Meeting
National Grid | LOWELL | 505742 | 01851 | 3.8 | Solar | 05_14_2L3 | 03/15/2023 | 03/20/2023 | 3 | 0 | 3 | 03/21/2023 | 03/21/2023 | 22 | 1 | 21 | 04/26/2023 | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/18/2023 |  | 9/28/2024 | N | EXP | 365 | 07/29/2023 | 09/28/2023 | 62 | 0 | 62 |  |  | 10/13/2023 | Connected |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 485511 | 01886 | 0 | Solar | 05_14_57L3 | 12/14/2022 | 12/15/2022 | 1 | 0 | 1 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | ANDOVER | 492288 | 01845 | 3.8 | Solar | 05_14_71L3 | 01/24/2023 | 01/27/2023 | 3 | 0 | 3 | 01/30/2023 | 01/30/2023 | 33 | 14 | 19 | 04/18/2023 | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 05/16/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 5/1/2023 |  | 11/29/2024 | N | EXP | 365 | 08/09/2023 | 12/28/2023 | 142 | 3 | 139 |  |  | 1/5/2024 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | LAWRENCE | 649543 | 01841 | 3.8 | Solar | 05_14_8L2 | 11/05/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | WORCESTER | 641542 | 01606 | 3.8 | Solar | 05_01_24W1 | 09/19/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | WEBSTER | 371739 | 01570 | 15.2 | Solar | 05_01_412L1 | 07/23/2021 | 07/26/2021 | 2 | 1 | 1 | 07/27/2021 | 07/27/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2022 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | RUTLAND | 175371 | 01543 | 46.08 | Solar | 05_01_55W1 | 02/14/2014 | 02/14/2014 | 5 | 0 | 5 | 02/25/2014 | 02/25/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2014 | 02/14/2014 | 8/29/2014 | Y | EXP | 57 | 01/06/2015 | 01/06/2015 | 0 | 0 | 0 | 3/2/2015 | 3/2/2015 | 3/5/2015 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | FALL RIVER | 591268 | 02723 | 6 | Solar | 05_05_106W82 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | PETERSHAM | 195814 | 01366 | 3000 | Solar | 05_09_705W4 | 09/14/2018 | 10/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 11/08/2018 | 65 | 35 | 30 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | GLOUCESTER | 260745 | 01930 | 5.76 | Solar | 05_12_51T1 | 10/18/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 | 10/18/2019 | 7/9/2020 | Y | EXP | 365 | 02/29/2020 | 02/28/2020 | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | CHELMSFORD | 553547 | 01863 | 3.8 | Solar | 05_14_2L3 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | WESTFORD | 495618 | 01886 | 7.6 | Solar | 05_14_57L3 | 02/27/2023 | 03/06/2023 | 6 | 5 | 1 | 03/07/2023 | 03/07/2023 | 230 | 206 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | ANDOVER | 578593 | 01845 | 480 | Solar | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Ayer-Clinton | Closed
National Grid | LAWRENCE | 652216 | 01841 | 7.6 | Solar | 05_14_8L2 | 11/14/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/14/2024 | 2/10/2026 | Y | EXP | 365 | 07/24/2025 | 12/01/2025 | 131 | 0 | 131 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 642848 | 01605 | 7.6 | Solar | 05_01_24W1 | 09/25/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 56 | 36 | 20 | 03/19/2025 | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 03/19/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 4/25/2025 | 09/25/2024 | 5/23/2026 | Y | EXP | 365 | 06/28/2025 | 11/13/2025 | 139 | 0 | 139 |  |  | 12/17/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WEBSTER | 379708 | 01570 | 9.8 | Solar | 05_01_412L1 | 09/15/2021 | 12/20/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 4/26/2023 | Y | EXP | 365 | 03/31/2022 | 04/26/2022 | 27 | 0 | 27 |  |  | 5/24/2022 | Connected |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | RUTLAND | 175471 | 01543 | 4.75 | Solar | 05_01_55W1 | 12/01/2014 | 12/01/2014 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2014 | 01/02/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2015 |  | 4/30/2015 | N | STD | 118 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/10/2015 | Connected |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | FALL RIVER | 635301 | 02723 | 5.76 | Solar | 05_05_106W82 | 08/26/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/26/2024 | 10/21/2025 | Y | EXP | 365 | 12/21/2024 | 01/18/2025 | 29 | 0 | 29 |  |  | 1/28/2025 | Connected |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | AMESBURY | 704904 | 01913 | 50 | Solar | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | MANCHESTER | 286147 | 01944 | 15.36 | Solar | 05_12_51T1 | 04/01/2020 | 04/03/2020 | 1 | 0 | 1 | 04/06/2020 | 04/06/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  | 10/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Time Frame Suspension
National Grid | LOWELL | 553845 | 01851 | 7.54 | Solar | 05_14_2L3 | 09/07/2023 | 12/07/2023 | 63 | 46 | 17 | 12/08/2023 | 12/08/2023 | 36 | 13 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2024 | Connected |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | WESTFORD | 497827 | 01886 | 15.2 | Solar | 05_14_57L3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 30 | 12 | 18 | 04/10/2023 | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 05/15/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 4/19/2023 |  | 11/29/2024 | N | EXP | 365 | 08/31/2023 | 02/27/2024 | 181 | 3 | 178 |  |  | 3/7/2024 | Connected |  | N |  | Gardner-Winchendon | Time Frame Suspension
National Grid | ANDOVER | 578504 | 01845 | 400 | Solar | 05_14_71L3 | 01/12/2024 | 02/08/2024 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2024 | 02/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Time Frame Suspension
National Grid | METHUEN | 654360 | 01844 | 7.6 | Solar | 05_14_8L2 | 11/14/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WORCESTER | 650683 | 01606 | 3.8 | Solar | 05_01_24W1 | 11/11/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/11/2024 | 2/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | DOUGLAS | 473685 | 01516 | 11.02 | Solar | 05_01_412L1 | 11/17/2022 | 12/20/2022 | 22 | 20 | 2 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | RUTLAND | 175638 | 01543 | 15.8 | Solar | 05_01_55W1 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2014 |  | 2/6/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 5/27/2016 | Connected |  | N |  | MPL-East | Closed
National Grid | FALL RIVER | 639123 | 02723 | 0 | Solar | 05_05_106W82 | 09/10/2024 | 10/02/2024 | 10 | 5 | 5 | 10/03/2024 | 10/03/2024 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N |  | MPL-East | Closed
National Grid | AMESBURY | 704916 | 01913 | 50 | Solar | 05_14_5J14 | 08/21/2025 | 08/25/2025 | 2 | 0 | 2 | 08/26/2025 | 08/26/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | MPL-East | Closed
National Grid | GLOUCESTER | 291501 | 01930 | 3.8 | Solar | 05_12_51T1 | 05/25/2020 | 05/26/2020 | 0 | 0 | 0 | 05/27/2020 | 05/27/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/25/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | Closed
National Grid | CHELMSFORD | 606324 | 01863 | 3.77 | Solar | 05_14_2L3 | 04/24/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 7/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N |  | MPL-East | Closed
National Grid | WESTFORD | 514032 | 01886 | 0 | Solar | 05_14_57L3 | 03/23/2023 | 03/27/2023 | 3 | 2 | 1 | 03/28/2023 | 03/28/2023 | 252 | 25 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | Closed
National Grid | ANDOVER | 583602 | 01845 | 6.38 | Solar | 05_14_71L3 | 02/14/2024 | 02/15/2024 | 1 | 0 | 1 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Closed
National Grid | LAWRENCE | 654711 | 01841 | 20 | Solar | 05_14_8L2 | 11/20/2024 | 11/25/2024 | 3 | 0 | 3 | 11/26/2024 | 11/26/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N |  | MPL-East | Closed
National Grid | WORCESTER | 685939 | 01606 | 15.2 | Solar | 05_01_24W1 | 04/17/2025 | 04/22/2025 | 2 | 0 | 2 | 04/23/2025 | 04/23/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Closed
National Grid | WEBSTER | 490569 | 01570 | 5.235 | Solar | 05_01_412L1 | 03/06/2024 |  | 108 | 94 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | RUTLAND | 175720 | 01543 | 499 | Solar | 05_01_55W1 | 12/31/2014 | 12/31/2014 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/15/2015 | 02/12/2015 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | FALL RIVER | 655843 | 02723 | 4.35 | Solar | 05_05_106W82 | 12/20/2024 | 01/09/2025 | 4 | 2 | 2 | 01/10/2025 | 01/10/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension - Group Member Withdraw
National Grid | AMESBURY | 175401 | 01913 | 17 | Solar | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 15 | 0 | 12/15/2014 | 12/15/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | GLOUCESTER | 292006 | 01930 | 10 | Solar | 05_12_51T1 | 06/09/2020 | 06/16/2020 | 5 | 5 | 0 | 06/17/2020 | 06/17/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 6/14/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | Time Frame Suspension
National Grid | LOWELL | 645283 | 01851 | 5.76 | Solar | 05_14_2L3 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 | 01/15/2025 | 02/11/2025 | 28 | 0 | 28 |  |  | 2/21/2025 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | WESTFORD | 534960 | 01886 | 15.2 | Solar | 05_14_57L3 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | ANDOVER | 611670 | 01845 | 3.8 | Solar | 05_14_71L3 | 05/16/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 05/16/2024 | 9/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y |  | Spencer-Rutland | Time Frame Suspension
National Grid | LAWRENCE | 656005 | 01841 | 10 | Solar | 05_14_8L2 | 11/21/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 11/21/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | WORCESTER | 660684 | 01606 | 0 | Other | 05_01_24W2 | 04/08/2025 | 06/17/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/18/2025 | 07/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | WEBSTER | 519952 | 01570 | 11.4 | Solar | 05_01_412L1 | 04/19/2023 | 04/26/2023 | 6 | 5 | 1 |  |  | 70 | 51 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | RUTLAND | 175828 | 01543 | 10 | Solar | 05_01_55W1 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/27/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/4/2016 | 4/4/2016 | 4/8/2016 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | FALL RIVER | 666670 | 02723 | 10 | Solar | 05_05_106W82 | 01/20/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 9/7/2026 | Y | EXP | 365 | 06/13/2025 | 08/15/2025 | 64 | 0 | 64 |  |  | 2/6/2026 | Connected |  | Y |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | AMESBURY | 175681 | 01913 | 17 | Solar | 05_14_5J14 | 11/19/2014 | 11/19/2014 | 15 | 0 | 15 | 12/15/2014 | 12/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2015 |  | 1/31/2015 | N | EXP | 24 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/29/2015 | Connected |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | MANCHESTER | 292808 | 01944 | 0 | Battery Add-On | 05_12_51T1 | 05/20/2020 | 05/29/2020 | 6 | 5 | 1 | 06/01/2020 | 06/01/2020 | 112 | 53 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | CHELMSFORD | 647102 | 01863 | 5.76 | Solar | 05_14_2L3 | 10/23/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/23/2024 | 1/3/2026 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 5/21/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | TYNGSBORO | 602139 | 01879 | 16.128 | Solar | 05_14_57L3 | 04/22/2024 | 04/26/2024 | 4 | 2 | 2 | 04/29/2024 | 04/29/2024 | 18 | 12 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | ANDOVER | 664589 | 01845 | 3.8 | Solar | 05_14_71L3 | 01/08/2025 | 03/19/2025 | 17 | 14 | 3 | 03/20/2025 | 03/20/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 | 01/08/2025 | 6/27/2026 | Y | EXP | 365 | 10/01/2025 | 12/02/2025 | 63 | 0 | 63 |  |  | 12/3/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | LAWRENCE | 656577 | 01841 | 5.76 | Solar | 05_14_8L2 | 11/25/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/25/2024 | 1/30/2026 | Y | EXP | 365 | 09/13/2025 | 09/12/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | WORCESTER | 745145 | 01606 | 8.36 | Solar | 05_01_24W2 | 01/13/2026 | 01/23/2026 | 5 | 2 | 3 | 02/11/2026 | 02/11/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | WEBSTER | 535445 | 01570 | 3 | Solar | 05_01_412L1 | 06/21/2023 | 06/26/2023 | 3 | 1 | 2 | 06/27/2023 | 06/27/2023 | 463 | 444 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension - Group Member Withdraw
National Grid | RUTLAND | 175887 | 01543 | 7.6 | Solar | 05_01_55W1 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 9/22/2015 | 9/22/2015 | 10/2/2015 | Connected |  | N |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | FALL RIVER | 677978 | 02723 | 3.42 | Solar | 05_05_106W82 | 03/14/2025 | 04/08/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Time Frame Suspension - Group Member Withdraw
National Grid | AMESBURY | 339779 | 01913 | 133.2 | Solar | 05_14_5J14 | 02/12/2021 | 03/04/2021 | 12 | 3 | 9 | 03/05/2021 | 03/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Time Frame Suspension
National Grid | BEVERLY | 295399 | 01915 | 0 | Battery Add-On | 05_12_51T1 | 06/13/2020 | 06/22/2020 | 5 | 4 | 1 | 06/23/2020 | 06/23/2020 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 3/3/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Closed
National Grid | LOWELL | 647024 | 01851 | 10 | Solar | 05_14_2L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N |  | Hopedale-West | Closed
National Grid | WESTFORD | 621970 | 01886 | 11.5 | Solar | 05_14_57L3 | 07/02/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y |  | Hopedale-West | Closed
National Grid | ANDOVER | 691644 | 01845 | 20 | Solar | 05_14_71L3 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Closed
National Grid | LAWRENCE | 657157 | 01841 | 5.76 | Solar | 05_14_8L2 | 11/26/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N |  | Hopedale-West | Closed - Construction Hold
National Grid | WORCESTER | 746118 | 01606 | 11.5 | Solar | 05_01_24W2 | 01/19/2026 | 01/22/2026 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N |  | Hopedale-West | Closed
National Grid | WEBSTER | 555700 | 01570 | 10 | Solar | 05_01_412L1 | 09/18/2023 | 09/19/2023 | 1 | 0 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2024 | Connected |  | N |  | Hopedale-West | Closed
National Grid | RUTLAND | 176009 | 01543 | 2230 | Solar | 05_01_55W1 | 08/13/2015 | 08/18/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 | 08/13/2015 | 9/19/2019 | Y | STD | 846 | 11/09/2018 | 01/31/2019 | 83 | 0 | 83 | 6/7/2019 | 6/19/2019 | 8/28/2019 | Connected |  | N |  | Hopedale-West | Closed
National Grid | FALL RIVER | 707962 | 02723 | 6.46 | Solar | 05_05_106W82 | 07/28/2025 | 08/13/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N |  | Hopedale-West | Closed
National Grid | AMESBURY | 425281 | 01913 | 133.2 | Solar | 05_14_5J14 | 04/20/2022 | 05/04/2022 | 10 | 0 | 10 |  |  | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Closed
National Grid | BEVERLY | 298665 | 01915 | 10 | Solar | 05_12_51T1 | 06/26/2020 | 07/06/2020 | 6 | 1 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 6/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N |  | Hopedale-West | Closed - Construction Hold
National Grid | LOWELL | 650018 | 01851 | 7.6 | Solar | 05_14_2L3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/06/2024 | 1/3/2026 | Y | EXP | 365 | 03/11/2025 | 05/06/2025 | 57 | 0 | 57 |  |  | 5/20/2025 | Connected |  | N |  | Shutesbury | Closed
National Grid | TYNGSBORO | 639845 | 01879 | 17.4 | Solar | 05_14_57L3 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Shutesbury | Closed
National Grid | WESTFORD | 686461 | 01886 | 7.68 | Solar | 05_14_73L1 | 05/01/2025 | 05/14/2025 | 9 | 6 | 3 | 05/15/2025 | 05/15/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Shutesbury | Closed
National Grid | LAWRENCE | 665462 | 01841 | 15.76 | Solar | 05_14_8L2 | 01/13/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 4/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N |  | Shutesbury | Closed
National Grid | WORCESTER | 746119 | 01606 | 11.5 | Solar | 05_01_24W2 | 01/19/2026 | 01/22/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Shutesbury | Closed
National Grid | DOUGLAS | 562803 | 01516 | 23 | Solar | 05_01_412L1 | 10/13/2023 | 10/30/2023 | 12 | 11 | 1 | 10/31/2023 | 10/31/2023 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | RUTLAND | 176053 | 01543 | 22.58 | Solar | 05_01_55W1 | 01/29/2015 | 01/29/2015 | 5 | 4 | 1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 3/10/2015 | 3/10/2015 | 6/10/2015 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | BELLINGHAM | 177384 | 02019 | 12 | Solar | 05_05_108W51 | 11/28/2016 | 11/28/2016 | 2 | 2 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2016 |  | 12/4/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/19/2017 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | AMESBURY | 673138 | 01913 | 30 | Solar | 05_14_5J14 | 05/12/2025 | 05/14/2025 | 2 | 0 | 2 | 05/15/2025 | 05/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | ESSEX | 300315 | 01929 | 0 | Solar | 05_12_51T1 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | LOWELL | 652090 | 01851 | 5.76 | Solar | 05_14_2L3 | 12/03/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed
National Grid | TYNGSBORO | 645111 | 01879 | 10 | Solar | 05_14_57L3 | 10/04/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 174466 | 01824 | 36 | Solar | 05_14_73L1 | 07/29/2011 | 07/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 | 1/9/2013 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | METHUEN | 681899 | 01844 | 7.6 | Solar | 05_14_8L2 | 04/01/2025 | 05/08/2025 | 1 | 0 | 1 | 05/09/2025 | 05/09/2025 | 16 | 0 | 16 | 06/13/2025 | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 174591 | 01606 | 39 | Solar | 05_01_24W2 | 04/27/2011 | 04/27/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 8/4/2012 | N | EXP | 25 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 8/2/2012 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | WEBSTER | 576129 | 01570 | 11.4 | Solar | 05_01_412L1 | 01/22/2024 | 02/21/2024 | 21 | 19 | 2 | 02/22/2024 | 02/22/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 01/22/2024 | 6/1/2025 | Y | EXP | 365 | 05/11/2024 | 08/16/2024 | 98 | 0 | 98 |  |  | 10/24/2024 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | RUTLAND | 176118 | 01543 | 6 | Solar | 05_01_55W1 | 08/21/2015 | 08/21/2015 | 13 | 13 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2015 |  | 8/30/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 4/14/2016 | 4/14/2016 | 4/25/2016 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | BELLINGHAM | 177504 | 02019 | 10 | Solar | 05_05_108W51 | 03/06/2017 | 03/06/2017 | 9 | 7 | 2 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/11/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/30/2017 | 8/30/2017 | 9/6/2017 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | GLOUCESTER | 689590 | 01930 | 0 | Battery Add-On | 05_12_24J10 | 05/05/2025 | 06/02/2025 | 19 | 15 | 4 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | MPL-East | Scoping Meeting
National Grid | GLOUCESTER | 302762 | 01930 | 10 | Solar | 05_12_51T1 | 07/29/2020 | 07/31/2020 | 1 | 1 | 0 | 08/03/2020 | 08/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/29/2020 | 7/30/2021 | Y | EXP | 365 | 01/21/2021 | 03/16/2021 | 54 | 0 | 54 |  |  | 5/6/2021 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | LOWELL | 684613 | 01851 | 21.4 | Solar | 05_14_2L3 | 04/14/2025 | 04/30/2025 | 9 | 5 | 4 | 05/01/2025 | 05/01/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WESTFORD | 648978 | 01886 | 5.76 | Solar | 05_14_57L3 | 10/22/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | CHELMSFORD | 174750 | 01824 | 225 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 2 | 566 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2013 | 07/09/2013 | 9/30/2014 | Y | EXP | 391 | 07/23/2014 | 11/18/2015 | 329 | 0 | 329 |  |  |  | Withdrawn |  | N |  | MPL-Northwest | Study Complete
National Grid | LAWRENCE | 683910 | 01841 | 11.52 | Solar | 05_14_8L2 | 04/11/2025 | 05/21/2025 | 27 | 24 | 3 | 05/22/2025 | 05/22/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-Northwest | Study Complete
National Grid | WORCESTER | 174763 | 01606 | 60 | Solar | 05_01_24W2 | 08/23/2012 | 08/23/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 12/7/2012 | N | EXP | 5 |  |  | 0 | 0 | 0 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WEBSTER | 604870 | 01570 | 10 | Solar | 05_01_412L1 | 04/18/2024 | 04/30/2024 | 4 | 0 | 4 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/18/2024 | 5/16/2025 | Y | EXP | 365 | 08/15/2024 | 08/14/2024 | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | RUTLAND | 176129 | 01543 | 4.3 | Solar | 05_01_55W1 | 04/13/2015 | 04/13/2015 | 3 | 2 | 1 | 04/16/2015 | 04/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 8/31/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 8/26/2015 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | BELLINGHAM | 177664 | 02019 | 15.2 | Solar | 05_05_108W51 | 05/24/2017 | 05/24/2017 | 2 | 2 | 0 | 05/30/2017 | 05/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 | 12/15/2017 | 12/15/2017 | 12/27/2017 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | GLOUCESTER | 731829 | 01930 | 16.24 | Solar | 05_12_24J10 | 12/04/2025 | 02/06/2026 | 42 | 25 | 17 | 02/09/2026 | 02/09/2026 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BEVERLY | 312832 | 01915 | 10 | Solar | 05_12_51T1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 | 09/15/2020 | 10/14/2021 | Y | EXP | 365 | 02/05/2021 | 03/05/2021 | 28 | 0 | 28 |  |  | 3/16/2021 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | CHELMSFORD | 378752 | 01824 | 2999 | Solar | 05_14_2L4 | 02/05/2022 | 03/15/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2022 | 03/16/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 02/05/2022 | 1/26/2027 | Y | STD | 483 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 649917 | 01886 | 10 | Solar | 05_14_57L3 | 10/31/2024 | 11/05/2024 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 10/31/2024 | 3/12/2026 | Y | EXP | 365 | 05/01/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 6/27/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | CHELMSFORD | 174749 | 01824 | 295 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 16 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2013 |  | 9/1/2014 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-Northwest | Study Complete
National Grid | LAWRENCE | 714702 | 01841 | 5.76 | Solar | 05_14_8L2 | 08/26/2025 | 10/01/2025 | 6 | 0 | 6 | 10/02/2025 | 10/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/26/2025 | 11/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 175456 | 01605 | 87 | Solar | 05_01_24W2 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 11/28/2014 | N | EXP | 53 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 3/25/2016 | Connected |  | N |  | Hopedale-West | Time Frame Suspension - Construction Hold
National Grid | DOUGLAS | 608295 | 01516 | 23 | Solar | 05_01_412L1 | 05/02/2024 | 05/16/2024 | 10 | 8 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | RUTLAND | 176264 | 01543 | 380 | Landfill Gas | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2015 | 10/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/14/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BELLINGHAM | 402732 | 02019 | 3.48 | Solar | 05_05_108W51 | 01/28/2022 | 02/07/2022 | 6 | 3 | 3 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 9/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | GLOUCESTER | 175642 | 01930 | 17 | Solar | 05_12_24J10 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 2/6/2015 | N | EXP | 88 |  |  | 0 | 0 | 0 | 6/9/2016 | 6/9/2016 | 6/14/2016 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | GLOUCESTER | 325210 | 01930 | 0 | Solar | 05_12_51T1 | 12/02/2020 | 01/04/2021 | 21 | 18 | 3 | 01/05/2021 | 01/05/2021 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 3/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2021 | Connected |  | N |  | Hopedale-West | Time Frame Suspension - Construction Hold
National Grid | CHELMSFORD | 582189 | 01863 | 100 | Solar | 05_14_2L4 | 01/19/2024 | 02/09/2024 | 15 | 4 | 11 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | MPL-East | Scoping Meeting
National Grid | TYNGSBORO | 656744 | 01879 | 15.2 | Solar | 05_14_57L3 | 11/25/2024 | 12/18/2024 | 15 | 13 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 174746 | 01824 | 225 | Solar | 05_14_73L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 9/1/2014 | N | EXP | 378 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | LAWRENCE | 723961 | 01841 | 9.56 | Solar | 05_14_8L2 | 10/03/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N |  | Hopedale-West | Closed - Construction Hold
National Grid | WORCESTER | 176042 | 01606 | 476 | Solar | 05_01_24W2 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 8/22/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/6/2015 | 10/6/2015 | 6/9/2016 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 611622 | 01570 | 10 | Solar | 05_01_412L1 | 05/16/2024 |  | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Millbury-Grafton | Closed
National Grid | RUTLAND | 176262 | 01543 | 10 | Solar | 05_01_55W1 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | BELLINGHAM | 551974 | 02019 | 10 | Solar | 05_05_108W51 | 09/11/2023 | 09/18/2023 | 5 | 0 | 5 | 09/19/2023 | 09/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 | 09/11/2023 | 12/31/2024 | Y | EXP | 365 | 04/25/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 6/12/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | GLOUCESTER | 176689 | 01930 | 10 | Solar | 05_12_24J10 | 02/19/2016 | 02/19/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/16/2016 | 8/16/2016 | 8/16/2016 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | BEVERLY | 327199 | 01915 | 10 | Solar | 05_12_51T1 | 11/19/2020 | 11/25/2020 | 3 | 0 | 3 | 11/27/2020 | 11/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/19/2020 | 4/26/2022 | Y | EXP | 365 | 04/09/2021 | 04/20/2021 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | LOWELL | 174864 | 01851 | 1333 | Solar | 05_14_2L4 | 08/02/2012 | 08/02/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/14/2012 | 10/24/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2013 | 08/02/2012 | 12/31/2012 | Y | STD | 13 | 10/25/2013 | 12/27/2013 | 42 | 0 | 42 | 12/26/2013 | 12/26/2013 | 12/27/2013 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | TYNGSBORO | 661194 | 01879 | 0 | Battery Add-On | 05_14_57L3 | 12/17/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 175222 | 01824 | 225 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 18 | 03/11/2015 | 04/06/2015 | 17 | 0 | 17 | 5/13/2015 | 5/13/2015 | 6/1/2015 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | LAWRENCE | 726834 | 01841 | 11.52 | Solar | 05_14_8L2 | 10/23/2025 |  | 78 | 77 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | WORCESTER | 176086 | 01605 | 5 | Solar | 05_01_24W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 12/31/2016 | Y | EXP | 675 | 03/11/2016 | 03/31/2016 | 13 | 0 | 13 | 8/8/2016 | 8/8/2016 | 8/8/2016 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WEBSTER | 619932 | 01570 | 10 | Solar | 05_01_412L1 | 06/24/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 88 | 74 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Millbury-Grafton | Closed
National Grid | RUTLAND | 176290 | 01543 | 22.8 | Solar | 05_01_55W1 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 | 07/10/2015 | 7/18/2016 | Y | EXP | 354 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 1/19/2017 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | BELLINGHAM | 564861 | 02019 | 10 | Solar | 05_05_108W51 | 11/10/2023 | 11/14/2023 | 2 | 0 | 2 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 11/10/2023 | 1/22/2025 | Y | EXP | 365 | 03/07/2024 | 04/20/2024 | 45 | 0 | 45 |  |  | 5/16/2024 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | GLOUCESTER | 183953 | 01930 | 6.44 | Solar | 05_12_24J10 | 05/09/2018 | 05/09/2018 | 8 | 0 | 8 | 05/22/2018 | 05/22/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2018 |  | 6/24/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | BEVERLY | 354200 | 01915 | 250 | Solar | 05_12_51T1 | 05/07/2021 | 05/26/2021 | 13 | 8 | 5 | 05/27/2021 | 05/27/2021 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2021 |  | 10/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | LOWELL | 176010 | 01851 | 64.8 | Solar | 05_14_2L4 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/19/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 5/13/2016 | 5/13/2016 | 5/18/2016 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 664297 | 01886 | 0 | Battery Add-On | 05_14_57L3 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 01/07/2025 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | CHELMSFORD | 175757 | 01824 | 295 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/10/2015 | 04/28/2015 | 33 | 0 | 33 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | LAWRENCE | 174235 | 01843 | 725 | Solar | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 176204 | 01605 | 13.6 | Solar | 05_01_24W2 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 598 | 10/14/2016 | 10/26/2016 | 8 | 0 | 8 | 5/13/2015 | 5/13/2015 | 11/15/2016 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 631896 | 01570 | 9.86 | Solar | 05_01_412L1 | 08/12/2024 | 09/27/2024 | 4 | 0 | 4 | 09/30/2024 | 09/30/2024 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 08/12/2024 | 11/26/2025 | Y | EXP | 365 | 02/11/2025 | 03/17/2025 | 35 | 0 | 35 |  |  | 3/21/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | RUTLAND | 176356 | 01543 | 5 | Solar | 05_01_55W1 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 | 10/1/2015 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BELLINGHAM | 658856 | 02019 | 3.8 | Solar | 05_05_108W51 | 12/05/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 3/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | GLOUCESTER | 325646 | 01930 | 10 | Solar | 05_12_24J11 | 11/12/2020 | 01/27/2021 | 49 | 47 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | MANCHESTER | 365294 | 01944 | 9.86 | Solar | 05_12_51T1 | 06/23/2021 | 07/16/2021 | 17 | 14 | 3 | 07/19/2021 | 07/19/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2021 |  | 9/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2021 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | LOWELL | 176358 | 01851 | 30 | Solar | 05_14_2L4 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | TYNGSBORO | 678244 | 01879 | 20 | Solar | 05_14_57L3 | 03/19/2025 | 03/24/2025 | 3 | 0 | 3 | 03/25/2025 | 03/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 175756 | 01824 | 225 | Solar | 05_14_73L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 18 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 6/2/2015 | 6/2/2015 | 7/13/2015 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | LAWRENCE | 174234 | 01843 | 500 | Solar | 05_14_8L3 | 02/02/2012 | 02/02/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2012 | 09/24/2012 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | WORCESTER | 176552 | 01605 | 7.6 | Solar | 05_01_24W2 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/05/2015 | 10/13/2016 | Y | EXP | 346 | 08/03/2016 | 08/31/2016 | 20 | 0 | 20 | 9/21/2016 | 9/21/2016 | 9/21/2016 | Connected |  | N |  | Hopedale-West | Closed - Construction Hold
National Grid | WEBSTER | 632100 | 01570 | 10 | Solar | 05_01_412L1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/11/2025 | Y | EXP | 365 | 10/11/2024 | 10/14/2024 | 4 | 0 | 4 |  |  | 12/4/2024 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 176383 | 01543 | 28 | Solar | 05_01_55W1 | 11/25/2015 | 11/25/2015 | 8 | 8 | 0 | 12/08/2015 | 12/08/2015 | 511 | 72 | 439 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2016 |  | 6/29/2018 | N | EXP | 815 |  |  | 0 | 0 | 0 |  |  | 8/30/2018 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BELLINGHAM | 670566 | 02019 | 7.6 | Solar | 05_05_108W51 | 02/06/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | GLOUCESTER | 677404 | 01930 | 8.36 | Solar | 05_12_24J11 | 03/12/2025 | 03/26/2025 | 10 | 6 | 4 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BEVERLY | 376945 | 01915 | 6.96 | Solar | 05_12_51T1 | 08/19/2021 | 01/04/2022 | 2 | 0 | 2 | 08/24/2021 | 08/24/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2022 | Connected |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | CHELMSFORD | 202054 | 01824 | 4975 | Solar | 05_14_2L4 | 11/27/2018 | 12/06/2018 | 157 | 2 | 155 |  |  | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Shutesbury | Closed
National Grid | WESTFORD | 705914 | 01886 | 15.2 | Solar | 05_14_57L3 | 07/22/2025 |  | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | CHELMSFORD | 176727 | 01863 | 10 | Solar | 05_14_73L1 | 02/23/2016 | 02/23/2016 | 3 | 3 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/23/2016 | 8/28/2017 | Y | EXP | 511 | 07/11/2017 | 07/31/2017 | 14 | 0 | 14 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | LAWRENCE | 175191 | 01843 | 45 | Solar | 05_14_8L3 | 11/22/2013 | 11/22/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 5 |  |  | 0 | 0 | 0 | 3/26/2014 | 3/26/2014 | 4/25/2014 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 176696 | 01605 | 10 | Solar | 05_01_24W2 | 04/21/2016 | 04/21/2016 | 3 | 3 | 0 | 04/28/2016 | 04/28/2016 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | WEBSTER | 646439 | 01570 | 10 | Solar | 05_01_412L1 | 10/25/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/25/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-North | Closed
National Grid | RUTLAND | 176511 | 01543 | 10 | Solar | 05_01_55W1 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/31/2016 | 8/31/2016 | 8/31/2016 | Connected |  | N |  | Brockton-North | Closed
National Grid | BELLINGHAM | 745830 | 02019 |  | Battery Add-On | 05_05_108W60 | 01/16/2026 | 01/20/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Brockton-North | Closed
National Grid | GLOUCESTER | 691429 | 01930 | 14.79 | Solar | 05_12_24J11 | 05/14/2025 | 05/29/2025 | 9 | 3 | 6 | 05/30/2025 | 05/30/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 05/14/2025 | 7/14/2026 | Y | EXP | 365 | 09/26/2025 | 11/18/2025 | 54 | 0 | 54 |  |  | 11/21/2025 | Connected |  | N |  | Brockton-North | Closed
National Grid | BEVERLY | 382216 | 01915 | 9.772 | Solar | 05_12_51T1 | 09/15/2021 | 09/20/2021 | 4 | 3 | 1 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2022 | Connected |  | N |  | Scituate | Closed
National Grid | CHELMSFORD | 202052 | 01824 | 4975 | Solar | 05_14_2L4 | 05/18/2021 |  | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Scituate | Closed
National Grid | WESTFORD | 705910 | 01886 | 15.2 | Solar | 05_14_57L3 | 08/12/2025 | 09/02/2025 | 13 | 10 | 3 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N |  | Brockton-South | Closed
National Grid | CHELMSFORD | 177572 | 01863 | 7.6 | Solar | 05_14_73L1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 105 | 0 | 105 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-South | Closed
National Grid | ANDOVER | 723449 | 01810 | 150 | Solar | 05_14_8T1 | 10/30/2025 | 12/08/2025 | 25 | 22 | 3 | 12/09/2025 | 12/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Brockton-South | Closed
National Grid | WORCESTER | 176856 | 01605 | 9 | Solar | 05_01_24W2 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2015 |  | 11/18/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/6/2016 | 5/6/2016 | 5/17/2016 | Connected |  | N |  | Brockton-South | Closed
National Grid | WEBSTER | 646578 | 01570 | 3.8 | Solar | 05_01_412L1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 01/23/2025 | 03/21/2025 | 58 | 0 | 58 |  |  | 4/1/2025 | Connected |  | N |  | Brockton-South | Closed
National Grid | RUTLAND | 176609 | 01543 | 616 | Solar | 05_01_55W1 | 02/12/2016 | 02/12/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Closed
National Grid | BELLINGHAM | 751142 | 02019 | 15.76 | Solar | 05_05_108W60 | 02/20/2026 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Hopedale-East | Closed
National Grid | GLOUCESTER | 177146 | 01930 | 25 | Solar | 05_12_24J2 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 | 08/09/2016 | 08/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 8/14/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N |  | Hopedale-East | Closed
National Grid | MANCHESTER | 392637 | 01944 | 0 | Other | 05_12_51T1 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Marlborough | Closed
National Grid | LOWELL | 207472 | 01854 | 73.3 | Solar | 05_14_2L4 | 01/29/2019 | 01/31/2019 | 1 | 0 | 1 | 02/01/2019 | 02/01/2019 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N |  | Marlborough | Closed
National Grid | WESTFORD | 708703 | 01886 | 15.2 | Solar | 05_14_57L3 | 07/31/2025 | 08/08/2025 | 5 | 1 | 4 | 08/11/2025 | 08/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N |  | Fall River-South | Closed
National Grid | CHELMSFORD | 295384 | 01824 | 10 | Solar | 05_14_73L1 | 06/08/2020 | 06/15/2020 | 4 | 4 | 0 | 06/16/2020 | 06/16/2020 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-South | Closed
National Grid | ANDOVER | 174755 | 01810 | 495 | Solar | 05_14_8T1 | 02/05/2014 | 02/05/2014 | 5 | 0 | 5 | 02/13/2014 | 02/13/2014 | 0 | 0 | 0 | 11/04/2014 | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2014 |  | 6/30/2014 | N | EXP | 111 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 10/2/2014 | Connected |  | N |  | Fall River-South | Closed
National Grid | WORCESTER | 177203 | 01606 | 379.7 | Solar | 05_01_24W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-South | Closed
National Grid | WEBSTER | 647877 | 01570 | 7.6 | Solar | 05_01_412L1 | 10/28/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/28/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N |  | Bridgewater | Closed
National Grid | RUTLAND | 176629 | 01543 | 6 | Solar | 05_01_55W1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2015 |  | 10/21/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 4/29/2016 | Connected |  | N |  | Bridgewater | Closed
National Grid | BELLINGHAM | 171881 | 02019 | 10 | Solar | 05_05_108W60 | 07/01/2018 | 07/01/2018 | 5 | 5 | 0 | 07/11/2018 | 07/11/2018 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Attleboro | Closed
National Grid | GLOUCESTER | 396049 | 01930 | 0 | Other | 05_12_24J2 | 01/04/2022 | 01/19/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/01/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Attleboro | Closed
National Grid | MANCHESTER | 394507 | 01944 | 360 | Solar | 05_12_51T1 | 12/17/2021 | 02/02/2022 | 32 | 24 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Attleboro | Closed - Conditional Approval Hold
National Grid | HAVERHILL | 175488 | 01830 | 100 | Solar | 05_14_31J1 | 07/23/2014 | 07/23/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2014 |  | 10/31/2014 | N | EXP | 5 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 4/9/2015 | Connected |  | N |  | Hanover | Closed
National Grid | TYNGSBORO | 717812 | 01879 | 15.66 | Solar | 05_14_57L3 | 09/17/2025 | 09/24/2025 | 5 | 0 | 5 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N |  | Hanover | Closed
National Grid | CHELMSFORD | 298402 | 01824 | 4.64 | Solar | 05_14_73L1 | 07/14/2020 | 07/15/2020 | 0 | 0 | 0 | 07/16/2020 | 07/16/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N |  | Hanover | Closed
National Grid | ANDOVER | 175373 | 01810 | 494 | Solar | 05_14_8T1 | 02/14/2014 | 02/14/2014 | 7 | 1 | 6 | 02/27/2014 | 02/27/2014 | 0 | 0 | 0 | 03/25/2014 | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/29/2014 | 02/14/2014 | 12/31/2016 | Y | EXP | 886 | 08/13/2015 | 12/23/2015 | 90 | 0 | 90 | 2/19/2015 | 2/19/2015 | 12/21/2015 | Connected |  | N |  | Hanover | Closed
National Grid | WORCESTER | 177592 | 01605 | 339.7 | Solar | 05_01_24W2 | 05/21/2017 | 05/21/2017 | 37 | 33 | 4 | 07/14/2017 | 07/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2017 |  | 5/27/2018 | N | EXP | 278 |  |  | 0 | 0 | 0 | 2/12/2018 | 2/12/2018 | 2/12/2018 | Connected |  | N |  | Hanover | Closed
National Grid | WEBSTER | 652003 | 01570 | 7.6 | Solar | 05_01_412L1 | 11/13/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/13/2024 | 2/28/2026 | Y | EXP | 365 | 06/12/2025 | 11/21/2025 | 163 | 0 | 163 |  |  | 12/1/2025 | Connected |  | N |  | Hanover | Closed
National Grid | RUTLAND | 176698 | 01543 | 380 | Bio Gas | 05_01_55W1 | 04/25/2016 | 05/16/2016 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2016 | 07/06/2016 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2016 | 04/25/2016 | 7/5/2022 | Y | STD | 7 | 03/09/2019 | 09/26/2019 | 202 | 107 | 95 |  |  | 3/16/2022 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BLACKSTONE | 175746 | 01504 | 20 | Solar | 05_05_108W60 | 10/29/2014 | 10/29/2014 | 5 | 3 | 2 | 11/10/2014 | 11/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 1/15/2015 | N | EXP | 64 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 3/3/2015 | Connected |  | N |  | Hopedale-East | Closed
National Grid | GLOUCESTER | 615112 | 01930 | 6 | Solar | 05_12_24J2 | 06/05/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/05/2024 | 8/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2024 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BEVERLY | 393606 | 01915 | 10 | Solar | 05_12_51T1 | 11/19/2021 | 11/23/2021 | 3 | 1 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | HAVERHILL | 416686 | 01830 | 100 | Solar | 05_14_31J1 | 04/07/2022 | 05/10/2022 | 23 | 14 | 9 | 05/11/2022 | 05/11/2022 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 717298 | 01886 | 15.2 | Solar | 05_14_57L3 | 09/21/2025 | 09/25/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | Y |  | Spencer-Rutland | Scoping Meeting
National Grid | CHELMSFORD | 303103 | 01824 | 200 | Solar | 05_14_73L1 | 08/13/2020 | 01/10/2022 | 23 | 12 | 11 | 09/17/2020 | 09/17/2020 | 83 | 60 | 23 | 01/27/2021 | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  | 03/22/2021 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 4/6/2021 | 08/13/2020 | 8/25/2025 | Y | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Scoping Meeting
National Grid | ANDOVER | 176839 | 01810 | 50 | Solar | 05_14_8T1 | 04/29/2016 | 04/29/2016 | 3 | 3 | 0 | 05/04/2016 | 05/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2016 |  | 5/4/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/13/2016 | 10/13/2016 | 11/3/2016 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 177694 | 01605 | 5 | Solar | 05_01_24W2 | 03/21/2017 | 03/21/2017 | 10 | 10 | 0 | 04/04/2017 | 04/04/2017 | 211 | 0 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2017 |  | 3/26/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Closed
National Grid | WEBSTER | 655660 | 01570 | 7.6 | Solar | 05_01_412L1 | 11/20/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/20/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N |  | Somerset | Closed
National Grid | RUTLAND | 176872 | 01543 | 10 | Solar | 05_01_55W1 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 3/7/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/2/2016 | 8/2/2016 | 8/8/2016 | Connected |  | N |  | Somerset | Closed
National Grid | BLACKSTONE | 175939 | 01504 | 7.6 | Solar | 05_05_108W60 | 01/21/2015 | 01/21/2015 | 23 | 22 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 5/31/2015 | N | EXP | 83 |  |  | 0 | 0 | 0 | 3/13/2015 | 3/13/2015 | 12/7/2015 | Connected |  | N |  | Hopedale-West | Time Frame Suspension - Design Hold
National Grid | GLOUCESTER | 664113 | 01930 | 5.76 | Solar | 05_12_24J2 | 01/07/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | Scoping Meeting
National Grid | MANCHESTER | 400010 | 01944 | 8.027 | Solar | 05_12_51T1 | 12/08/2021 | 01/05/2022 | 19 | 17 | 2 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2022 | Connected |  | N |  | Hopedale-East | Closed
National Grid | HAVERHILL | 603273 | 01830 | 3.8 | Solar | 05_14_31J3 | 04/16/2024 | 04/19/2024 | 3 | 0 | 3 | 04/22/2024 | 04/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2026 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Millbury-Grafton | Closed
National Grid | WESTFORD | 725537 | 01886 | 7.6 | Solar | 05_14_57L3 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | N |  | Marlborough | Closed
National Grid | CHELMSFORD | 354303 | 01824 | 7.6 | Solar | 05_14_73L1 | 04/23/2021 | 04/27/2021 | 2 | 1 | 1 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 9/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2021 | Connected |  | N |  | Brockton-North | Closed
National Grid | ANDOVER | 177266 | 01810 | 143 | Solar | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 4/7/2017 | 4/7/2017 | 3/30/2017 | Connected |  | N |  | Brockton-North | Closed
National Grid | WORCESTER | 203085 | 01606 | 150 | Solar | 05_01_24W2 | 12/06/2018 | 01/02/2019 | 14 | 12 | 2 | 01/03/2019 | 01/03/2019 | 3 | 0 | 3 | 01/18/2019 | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 |  | 04/30/2019 | 70 | 4 | 66 |  |  | 0 | 0 | 0 | 5/17/2019 | 12/06/2018 | 9/25/2020 | Y | EXP | 349 | 02/14/2020 | 03/12/2020 | 27 | 0 | 27 |  |  | 9/25/2020 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 663882 | 01570 | 5.76 | Solar | 05_01_412L1 | 01/06/2025 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N |  | Fall River-South | Closed
National Grid | RUTLAND | 177130 | 01543 | 7.25 | Solar | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 10 | 9 | 1 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 1/28/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BLACKSTONE | 176333 | 01504 | 6 | Solar | 05_05_108W60 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2015 | 09/15/2015 | 9/21/2016 | Y | EXP | 348 | 10/18/2016 | 10/27/2016 | 7 | 0 | 7 | 12/13/2016 | 12/13/2016 | 12/16/2016 | Connected |  | N |  | Hopedale-East | Closed
National Grid | GLOUCESTER | 672436 | 01930 | 5.76 | Solar | 05_12_24J2 | 02/17/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Awaiting Initial Payments for Common System Modifications
National Grid | MANCHESTER | 425303 | 01944 | 15.2 | Solar | 05_12_51T1 | 04/20/2022 | 05/11/2022 | 15 | 14 | 1 | 05/12/2022 | 05/12/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | HAVERHILL | 176476 | 01830 | 100 | Solar | 05_14_31J5 | 03/24/2016 | 03/24/2016 | 9 | 9 | 0 | 04/07/2016 | 04/07/2016 | 468 | 17 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2016 |  | 5/31/2018 | N | EXP | 744 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 747662 | 01886 | 150 | Solar | 05_14_57L4 | 02/24/2026 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N |  | Bridgewater | Closed
National Grid | CHELMSFORD | 469528 | 01824 | 7.6 | Solar | 05_14_73L1 | 10/19/2022 | 10/20/2022 | 1 | 0 | 1 | 10/21/2022 | 10/21/2022 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N |  | Methuen | Closed
National Grid | ANDOVER | 177265 | 01810 | 161 | Solar | 05_14_8T1 | 11/08/2016 | 11/08/2016 | 12 | 12 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 11/13/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N |  | Methuen | Closed
National Grid | WORCESTER | 204161 | 01606 | 426.4 | Solar | 05_01_24W2 | 12/18/2018 | 01/22/2019 | 22 | 17 | 5 | 01/23/2019 | 01/23/2019 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-North | Closed
National Grid | WEBSTER | 674712 | 01570 | 3.8 | Solar | 05_01_412L1 | 03/05/2025 | 03/14/2025 | 4 | 0 | 4 | 03/24/2025 | 03/24/2025 | 102 | 85 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N |  | Fall River-South | Closed
National Grid | RUTLAND | 177129 | 01543 |  |  | 05_01_55W1 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/28/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Closed
National Grid | BELLINGHAM | 176355 | 02019 | 6 | Solar | 05_05_108W60 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2015 | 05/14/2015 | 12/31/2016 | Y | EXP | 578 | 11/19/2015 | 12/15/2015 | 17 | 0 | 17 | 3/22/2016 | 3/22/2016 | 3/28/2016 | Connected |  | N |  | Hopedale-East | Closed
National Grid | GLOUCESTER | 177120 | 01930 | 420 | Solar | 05_12_24J8 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 44 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Closed
National Grid | GLOUCESTER | 426149 | 01930 | 7.6 | Solar | 05_12_51T1 | 06/13/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | HAVERHILL | 176513 | 01830 | 99.9 | Solar | 05_14_31J6 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 77 | 380 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 12/6/2017 | N | EXP | 477 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Worcester North - Dont Use | Closed
National Grid | WESTFORD | 206199 | 01886 | 72 | Solar | 05_14_57L4 | 01/16/2019 | 01/31/2019 | 8 | 3 | 5 | 02/01/2019 | 02/01/2019 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N |  | Worcester North - Dont Use | Closed
National Grid | CHELMSFORD | 580798 | 01824 | 9.765 | Solar | 05_14_73L1 | 01/23/2024 | 01/26/2024 | 4 | 1 | 3 | 01/29/2024 | 01/29/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N |  | Worcester North/South | Closed
National Grid | ANDOVER | 195724 | 01810 | 400 | Natural Gas | 05_14_8T1 | 02/28/2019 | 07/02/2019 | 302 | 26 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Somerset | Closed
National Grid | WORCESTER | 206472 | 01605 | 250 | Solar | 05_01_24W2 | 03/12/2019 | 03/18/2019 | 4 | 2 | 2 | 03/19/2019 | 03/19/2019 | 17 | 11 | 6 | 05/31/2019 | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  | 10/25/2019 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Cape Ann | Closed
National Grid | WEBSTER | 674907 | 01570 | 10 | Solar | 05_01_412L1 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N |  | Cape Ann | Closed
National Grid | RUTLAND | 177173 | 01543 | 5.59 | Solar | 05_01_55W1 | 05/31/2016 | 05/31/2016 | 17 | 17 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2016 |  | 6/6/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N |  | Cape Ann | Closed
National Grid | BLACKSTONE | 176365 | 01504 | 3.8 | Solar | 05_05_108W60 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 |  | 3/15/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Cape Ann | Closed
National Grid | LYNN | 728080 | 01904 | 11.5 | Solar | 05_12_24W1 | 10/28/2025 | 11/03/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Cape Ann | Closed
National Grid | BEVERLY | 426053 | 01915 | 22.272 | Solar | 05_12_51T1 | 04/25/2022 | 06/07/2022 | 30 | 26 | 4 | 06/08/2022 | 06/08/2022 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N |  | Cape Ann | Closed
National Grid | HAVERHILL | 650000 | 01830 | 3.8 | Solar | 05_14_31L9 | 10/30/2024 | 11/25/2024 | 5 | 0 | 5 | 11/26/2024 | 11/26/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Cape Ann | Closed
National Grid | WESTFORD | 223164 | 01886 | 99.9 | Solar | 05_14_57L4 | 04/29/2019 | 05/16/2019 | 12 | 8 | 4 | 05/17/2019 | 05/17/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/21/2021 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  | 3/30/2021 | Connected |  | N |  | Methuen/Haverhill | Closed - Pending
National Grid | WESTFORD | 637040 | 01886 | 17.6 | Solar | 05_14_73L1 | 09/17/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/17/2024 | 11/27/2025 | Y | EXP | 365 | 03/26/2025 | 04/16/2025 | 22 | 0 | 22 |  |  | 4/23/2025 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | ANDOVER | 207134 | 01810 | 240 | Solar | 05_01_24W2 | 01/30/2019 | 02/11/2019 | 8 | 2 | 6 | 02/12/2019 | 02/12/2019 | 39 | 20 | 19 | 08/07/2019 | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 09/04/2019 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | WORCESTER | 674780 | 01606 | 7.6 | Solar | 05_01_412L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | WEBSTER | 177420 | 01570 | 5 | Solar | 05_01_55W1 | 12/05/2016 | 12/05/2016 | 2 | 2 | 0 | 12/08/2016 | 12/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2016 |  | 12/11/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/7/2017 | 3/7/2017 | 3/7/2017 | Connected |  | N |  | Billerica | Closed
National Grid | RUTLAND | 176417 | 01543 | 10 | Solar | 05_05_108W60 | 12/02/2015 | 12/02/2015 | 3 | 3 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/8/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/15/2015 | 12/15/2015 | 6/6/2016 | Connected |  | N |  | North Andover | Closed
National Grid | BELLINGHAM | 175225 | 02019 | 11.25 | Solar | 05_12_24W1 | 01/06/2015 | 01/06/2015 | 10 | 7 | 3 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 7/6/2015 | Connected |  | N |  | North Andover | Closed
National Grid | LYNN | 432837 | 01904 | 220 | Solar | 05_12_51T1 | 06/23/2022 | 07/29/2022 | 25 | 15 | 10 |  |  | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 06/23/2022 | 10/31/2024 | Y | STD | 29 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N |  | North Andover | Closed
National Grid | MANCHESTER | 650670 | 01944 | 5.76 | Solar | 05_14_31L9 | 10/30/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | North Andover | Closed
National Grid | HAVERHILL | 264770 | 01830 | 9.86 | Solar | 05_14_57L4 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2020 | Connected |  | N |  | North Andover | Closed
National Grid | WESTFORD | 644757 | 01886 | 17.101 | Solar | 05_14_73L1 | 10/03/2024 | 10/07/2024 | 2 | 0 | 2 | 10/08/2024 | 10/08/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N |  | Tewksbury | Closed
National Grid | WESTFORD | 391856 | 01886 | 0 | Other | 05_14_8T1 | 01/04/2022 | 01/26/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Tewksbury | Closed
National Grid | ANDOVER | 209361 | 01810 | 72 | Solar | 05_01_24W2 | 02/12/2019 | 04/10/2019 | 4 | 0 | 4 | 04/11/2019 | 04/11/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Beverly | Closed
National Grid | WORCESTER | 677792 | 01606 | 10 | Solar | 05_01_412L1 | 03/13/2025 | 04/10/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 03/13/2025 | 6/10/2026 | Y | EXP | 365 | 09/05/2025 | 10/25/2025 | 51 | 0 | 51 |  |  | 12/2/2025 | Connected |  | N |  | Beverly | Closed
National Grid | WEBSTER | 178189 | 01570 | 296 | Solar | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 10 | 0 | 10 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 | 10/25/2018 | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/05/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/7/2018 |  | 2/3/2020 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N |  | Adams-Deerfield | Closed
National Grid | RUTLAND | 176794 | 01543 | 7.6 | Solar | 05_05_108W60 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 329 | 06/28/2016 | 09/15/2016 | 55 | 0 | 55 | 4/6/2016 | 4/6/2016 | 11/18/2016 | Connected |  | N |  | Adams-Deerfield | Closed
National Grid | BELLINGHAM | 175968 | 02019 | 6 | Solar | 05_12_24W1 | 08/06/2015 | 08/06/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Leominster | Closed
National Grid | LYNN | 431218 | 01904 | 10 | Solar | 05_12_51T1 | 05/17/2022 | 05/18/2022 | 1 | 0 | 1 | 05/19/2022 | 05/19/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N |  | Leominster | Closed
National Grid | GLOUCESTER | 653300 | 01930 | 10.88 | Solar | 05_14_31L9 | 11/08/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-Southwest | Closed
National Grid | HAVERHILL | 385677 | 01830 | 3.8 | Solar | 05_14_57L4 | 02/07/2022 | 03/02/2022 | 17 | 16 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  | 4/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | N |  | MPL-Southwest | Closed
National Grid | WESTFORD | 645633 | 01886 | 10 | Solar | 05_14_73L1 | 10/21/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Northampton | Closed
National Grid | CHELMSFORD | 412234 | 01824 | 0 | Battery Add-On | 05_14_8T1 | 04/26/2022 | 05/27/2022 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/24/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-North | Closed
National Grid | ANDOVER | 274013 | 01810 | 250 | Solar | 05_01_24W2 | 02/11/2020 | 02/14/2020 | 3 | 1 | 2 |  |  | 60 | 43 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 02/11/2020 | 6/23/2023 | Y | STD | 858 | 04/02/2022 | 06/06/2023 | 430 | 0 | 430 | 5/25/2023 | 6/7/2023 | 6/16/2023 | Connected |  | N |  | Brockton-North | Closed
National Grid | WORCESTER | 680197 | 01605 | 11.5 | Solar | 05_01_412L1 | 04/08/2025 | 04/23/2025 | 1 | 0 | 1 | 05/13/2025 | 05/13/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/08/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N |  | Hopedale-East | Closed
National Grid | WEBSTER | 178188 | 01570 | 294 | Solar | 05_01_55W1 | 12/28/2017 | 12/28/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 2/3/2020 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N |  | Hopedale-East | Closed
National Grid | RUTLAND | 176831 | 01543 | 6 | Solar | 05_05_108W60 | 02/25/2016 | 02/25/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/5/2017 | N | EXP | 327 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 2/22/2017 | Connected |  | N |  | Hopedale-East | Closed
National Grid | BELLINGHAM | 176777 | 02019 | 8.5 | Solar | 05_12_24W1 | 11/04/2015 | 11/04/2015 | 3 | 3 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 11/9/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 1/10/2017 | Connected |  | N |  | Marlborough | Closed
National Grid | LYNN | 456681 | 01904 | 15.2 | Solar | 05_12_51T1 | 09/06/2022 | 09/07/2022 | 1 | 0 | 1 | 09/08/2022 | 09/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2023 | Connected |  | N |  | Brockton-South | Closed
National Grid | GLOUCESTER | 655518 | 01930 | 7.6 | Solar | 05_14_31L9 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Chelmsford/Westford | Closed
National Grid | HAVERHILL | 643818 | 01830 | 9.75 | Solar | 05_14_57L4 | 09/30/2024 | 10/21/2024 | 3 | 1 | 2 | 10/22/2024 | 10/22/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | WESTFORD | 648564 | 01886 | 10 | Solar | 05_14_73L1 | 11/01/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 11/01/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | CHELMSFORD | 174280 | 01824 | 600 | Solar | 05_14_8T2 | 12/30/2011 | 12/30/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 12/30/2011 | 6/1/2012 | Y | EXP | 194 | 11/16/2012 | 02/26/2013 | 62 | 0 | 62 | 12/17/2012 | 12/17/2012 | 12/31/2012 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | LAWRENCE | 307776 | 01843 | 9.12 | Solar | 05_01_24W2 | 08/31/2020 | 09/16/2020 | 11 | 11 | 0 | 09/17/2020 | 09/17/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | WORCESTER | 680170 | 01606 | 10 | Solar | 05_01_412L1 | 03/24/2025 | 04/22/2025 | 21 | 16 | 5 | 04/23/2025 | 04/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Closed
National Grid | WEBSTER | 178233 | 01570 | 133.2 | Solar | 05_01_55W1 | 01/07/2018 | 01/07/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2018 |  | 4/16/2021 | N | EXP | 49 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N |  | Billerica | Closed
National Grid | RUTLAND | 177051 | 01543 | 7.6 | Solar | 05_05_108W60 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2017 | 01/11/2017 | 1/18/2018 | Y | EXP | 364 | 03/08/2017 | 03/01/2017 | 0 | 0 | 0 | 6/19/2017 | 6/19/2017 | 6/22/2017 | Connected |  | N |  | North Andover | Closed
National Grid | BELLINGHAM | 177282 | 02019 | 10 | Solar | 05_12_24W1 | 06/14/2016 | 06/14/2016 | 1 | 1 | 0 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N |  | North Andover | Closed
National Grid | LYNN | 456466 | 01904 | 0 | Solar | 05_12_51T1 | 09/26/2022 | 09/30/2022 | 4 | 3 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Bridgewater | Closed
National Grid | BEVERLY | 663850 | 01915 | 14.5 | Solar | 05_14_31L9 | 01/08/2025 | 01/17/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N |  | Marlborough | Closed
National Grid | HAVERHILL | 656473 | 01830 | 8.41 | Solar | 05_14_57L4 | 12/06/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WESTFORD | 653596 | 01886 | 10 | Solar | 05_14_73L1 | 11/15/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 | 02/13/2025 | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/12/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/15/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen | Closed
National Grid | WESTFORD | 177246 | 01886 | 1139 | Solar | 05_14_8T2 | 06/13/2016 | 06/13/2016 | 62 | 62 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2016 | 10/18/2016 | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2017 | 06/13/2016 | 8/6/2018 | Y | STD | 517 | 02/23/2018 | 08/03/2018 | 126 | 0 | 126 | 6/26/2018 | 7/10/2018 | 8/6/2018 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | LAWRENCE | 322315 | 01843 | 10 | Solar | 05_01_24W2 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N |  | Beverly | Closed
National Grid | WORCESTER | 699214 | 01605 | 9.423 | Solar | 05_01_412L1 | 06/23/2025 | 06/25/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | WEBSTER | 178262 | 01570 | 7.6 | Solar | 05_01_55W1 | 04/17/2018 | 04/17/2018 | 19 | 0 | 19 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 4/23/2019 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Closed
National Grid | RUTLAND | 177115 | 01543 | 10 | Solar | 05_05_108W60 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 | 08/05/2016 | 8/14/2017 | Y | EXP | 364 | 12/05/2016 | 01/16/2017 | 28 | 0 | 28 | 3/16/2017 | 3/16/2017 | 3/20/2017 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BELLINGHAM | 177814 | 02019 | 3.8 | Solar | 05_12_24W1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 219 | 0 | 219 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/5/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Worcester North/South | Closed - Completion Documents Hold
National Grid | LYNN | 456448 | 01904 | 22.8 | Solar | 05_12_51T1 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 | 11/18/2022 | 7/16/2024 | Y | EXP | 55 | 04/05/2023 | 06/12/2023 | 69 | 0 | 69 |  |  | 5/20/2024 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | MANCHESTER | 177941 | 01944 | 120 | Solar | 05_14_32J1 | 06/26/2017 | 06/26/2017 | 105 | 105 | 0 |  |  | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 5/2/2019 | N | STD | 219 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Bridgewater | Closed
National Grid | HAVERHILL | 721432 | 01832 | 7.6 | Solar | 05_14_58L1 | 09/24/2025 | 10/03/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 09/24/2025 | 12/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N |  | Hanover | Closed
National Grid | CHELMSFORD | 660285 | 01824 | 10 | Solar | 05_14_73L1 | 12/12/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Closed
National Grid | WESTFORD | 244642 | 01886 | 200 | Solar | 05_14_8T2 | 07/25/2019 | 08/08/2019 | 7 | 3 | 4 | 08/09/2019 | 08/09/2019 | 15 | 3 | 12 | 10/07/2019 | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 11/18/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Closed
National Grid | LAWRENCE | 351365 | 01843 | 7.6 | Solar | 05_01_24W2 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 10/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N |  | Tewksbury | Closed
National Grid | WORCESTER | 642827 | 01605 | 4990 | Other | 05_01_412L2 | 11/21/2024 | 12/12/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | Ayer-Clinton | Closed
National Grid | WEBSTER | 178361 | 01570 | 3000 | Solar | 05_01_55W1 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Closed
National Grid | RUTLAND | 177305 | 01543 | 50.4 | Solar | 05_05_108W60 | 11/15/2016 | 11/15/2016 | 10 | 10 | 0 | 11/30/2016 | 11/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2016 |  | 11/21/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/17/2017 | Connected |  | N |  | Hanover | Closed
National Grid | BELLINGHAM | 177896 | 02019 | 7.6 | Solar | 05_12_24W1 | 06/15/2017 | 06/15/2017 | 9 | 9 | 0 | 06/28/2017 | 06/28/2017 | 150 | 0 | 150 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2017 |  | 6/20/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-North | Closed
National Grid | LYNN | 480578 | 01904 | 0 | Solar | 05_12_51T1 | 11/28/2022 | 11/29/2022 | 1 | 0 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2023 | Connected |  | N |  | Bridgewater | Closed
National Grid | BEVERLY | 176539 | 01915 | 46.8 | Solar | 05_14_32J5 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 9/16/2017 | N | EXP | 57 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N |  | Chelmsford/Westford | Closed - Design Hold
National Grid | HAVERHILL | 726691 | 01830 | 15.2 | Solar | 05_14_58L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Hopedale-East | Closed
National Grid | WESTFORD | 670687 | 01886 | 7.6 | Solar | 05_14_73L1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N |  | Brockton-North | Closed
National Grid | WESTFORD | 356820 | 01886 | 150 | Solar | 05_14_8T2 | 05/10/2021 | 06/07/2021 | 18 | 10 | 8 | 06/08/2021 | 06/08/2021 | 60 | 36 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Somerset | Closed
National Grid | LAWRENCE | 376655 | 01843 | 9.8 | Solar | 05_01_24W2 | 08/31/2021 |  | 50 | 45 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Bridgewater | Closed
National Grid | WORCESTER | 670827 | 01605 | 3.8 | Solar | 05_01_412L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Worcester North - Dont Use | Closed - Completion Documents Hold
National Grid | WEBSTER | 178532 | 01570 | 7.6 | Solar | 05_01_55W1 | 12/05/2017 | 12/05/2017 | 83 | 82 | 1 | 06/06/2018 | 06/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  | 12/10/2018 | N | EXP | 188 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | RUTLAND | 177521 | 01543 | 7.6 | Solar | 05_05_108W60 | 09/29/2016 | 09/29/2016 | 3 | 3 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 | 09/29/2016 | 10/4/2017 | Y | EXP | 364 | 01/03/2017 | 01/16/2017 | 9 | 0 | 9 | 2/16/2017 | 2/16/2017 | 2/22/2017 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | BELLINGHAM | 201447 | 02019 | 7.6 | Solar | 05_12_24W1 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 | 12/12/2018 | 4/14/2021 | Y | EXP | 365 | 11/03/2020 | 02/08/2021 | 97 | 0 | 97 |  |  | 3/17/2021 | Connected |  | Y |  | Methuen/Haverhill | Closed
National Grid | LYNN | 486700 | 01904 | 0 | Solar | 05_12_51T1 | 12/21/2022 | 12/27/2022 | 4 | 3 | 1 | 12/28/2022 | 12/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | BEVERLY | 210231 | 01965 | 15.2 | Solar | 05_14_33L1 | 03/08/2019 | 04/03/2019 | 10 | 10 | 0 | 04/04/2019 | 04/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 7/26/2019 | N | EXP | 18 |  |  | 0 | 0 | 0 |  |  | 6/25/2019 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension - Group Member Withdraw
National Grid | BOXFORD | 178428 | 01921 | 22.72 | Solar | 05_14_58L1 | 03/05/2018 | 03/05/2018 | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 3/11/2019 | N | EXP | 8 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-North | Closed
National Grid | WESTFORD | 701811 | 01886 | 15.2 | Solar | 05_14_73L1 | 07/02/2025 | 07/28/2025 | 16 | 14 | 2 | 07/29/2025 | 07/29/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N |  | Leominster | Closed
National Grid | WESTFORD | 359565 | 01886 | 466.6 | Solar | 05_14_8T2 | 07/09/2021 | 07/23/2021 | 9 | 3 | 6 | 07/26/2021 | 07/26/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2021 |  | 3/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2022 | Connected |  | N |  | Tewksbury | Closed
National Grid | LAWRENCE | 410649 | 01843 | 6 | Solar | 05_01_24W2 | 02/07/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Closed
National Grid | WORCESTER | 670548 | 01605 | 0 | Other | 05_01_412L2 | 08/11/2025 | 09/15/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | Billerica | Closed
National Grid | WEBSTER | 177602 | 01570 | 7.04 | Solar | 05_05_108W60 | 07/19/2017 | 07/19/2017 | 7 | 6 | 1 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/24/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 9/29/2017 | 9/29/2017 | 10/3/2017 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | RUTLAND | 223585 | 01543 | 7.6 | Solar | 05_12_24W1 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 | 06/05/2019 | 6/3/2020 | Y | EXP | 365 | 12/05/2019 | 12/16/2019 | 11 | 0 | 11 |  |  | 3/13/2020 | Connected |  | N |  | Worcester North/South | Closed - Completion Documents Hold
National Grid | BLACKSTONE | 495086 | 01504 | 0 | Solar | 05_12_51T1 | 01/27/2023 | 03/16/2023 | 33 | 32 | 1 | 03/17/2023 | 03/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 7/23/2024 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Closed
National Grid | LYNN | 267108 | 01904 | 0 | Battery Add-On | 05_14_33L1 | 11/25/2019 | 01/02/2020 | 23 | 17 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 4/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2020 | Connected |  | N |  | Hopedale-East | Closed
National Grid | MANCHESTER | 223575 | 01944 | 0 | Solar | 05_14_58L1 | 04/29/2019 | 05/07/2019 | 5 | 0 | 5 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2019 |  | 4/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2020 | Connected |  | N |  | Tewksbury | Closed
National Grid | TOPSFIELD | 726366 | 01983 | 6.84 | Solar | 05_14_73L1 | 10/14/2025 | 10/23/2025 | 6 | 5 | 1 | 10/24/2025 | 10/24/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N |  | Fall River-South | Closed
National Grid | WESTFORD | 430644 | 01886 | 0 | Battery Add-On | 05_14_8T2 | 08/23/2022 | 09/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/07/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-North | Closed
National Grid | CHELMSFORD | 418368 | 01824 | 9.8 | Solar | 05_01_24W2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/14/2022 | 9/5/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Closed
National Grid | LAWRENCE | 689117 | 01843 | 15.2 | Solar | 05_01_412L2 | 05/05/2025 | 05/06/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Fall River-North | Closed - Completion Documents Hold
National Grid | WORCESTER | 178535 | 01605 | 7.6 | Solar | 05_01_55W1 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 | 12/07/2017 | 3/22/2019 | Y | EXP | 441 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N |  | North Andover | Closed
National Grid | WEBSTER | 177667 | 01570 | 10 | Solar | 05_05_108W60 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/24/2017 | 5/30/2018 | Y | EXP | 363 | 10/02/2017 | 11/30/2017 | 35 | 0 | 35 | 12/20/2017 | 12/20/2017 | 1/5/2018 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed - Completion Documents Hold
National Grid | RUTLAND | 277587 | 01543 | 10 | Solar | 05_12_24W1 | 03/04/2020 | 03/16/2020 | 7 | 3 | 4 | 03/17/2020 | 03/17/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 | 03/04/2020 | 12/21/2022 | Y | EXP | 365 | 12/10/2020 | 03/11/2021 | 91 | 0 | 91 |  |  | 9/22/2022 | Connected |  | N |  | Somerset | Closed
National Grid | BLACKSTONE | 496638 | 01504 | 7.6 | Solar | 05_12_51T1 | 02/24/2023 | 02/28/2023 | 2 | 0 | 2 | 03/01/2023 | 03/01/2023 | 167 | 127 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2023 | Connected |  | N |  | Somerset | Closed
National Grid | LYNN | 283459 | 01904 | 10 | Solar | 05_14_33L1 | 03/12/2020 | 03/19/2020 | 5 | 5 | 0 | 03/20/2020 | 03/20/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2020 | Connected |  | N |  | Hanover | Closed
National Grid | BEVERLY | 258486 | 01915 | 10 | Solar | 05_14_58L1 | 10/05/2019 | 10/11/2019 | 4 | 0 | 4 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N |  | Hopedale-East | Closed
National Grid | BOXFORD | 640463 | 01921 | 0 | Solar | 05_14_73L2 | 09/16/2024 | 10/31/2024 | 8 | 6 | 2 | 11/01/2024 | 11/01/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/16/2024 | 11/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Terminated |  | N |  | Hopedale-East | Closed - Construction Hold
National Grid | WESTFORD | 646241 | 01886 | 480 | Solar | 05_14_92L1 | 03/13/2025 | 05/27/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2025 | 07/30/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N |  | Ayer-Clinton | Closed
National Grid | CHELMSFORD | 423774 | 01863 | 67.3 | Solar | 05_01_24W2 | 04/20/2022 | 05/04/2022 | 10 | 1 | 9 | 05/05/2022 | 05/05/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/20/2022 | 11/8/2023 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | BILLERICA | 709362 | 01821 | 11.4 | Solar | 05_01_412L2 | 08/08/2025 | 08/19/2025 | 6 | 5 | 1 | 08/20/2025 | 08/20/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 178563 | 01604 | 2500 | Solar | 05_01_55W1 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/20/2018 | 68 | 52 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Attleboro | Closed
National Grid | DUDLEY | 177874 | 01571 | 3600 | Solar | 05_05_108W60 | 08/14/2017 | 08/14/2017 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2017 | 09/25/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2018 | 08/14/2017 | 9/26/2022 | Y | STD | 55 | 01/22/2022 | 06/01/2022 | 131 | 0 | 131 |  |  | 8/3/2022 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | RUTLAND | 515479 | 01543 | 3.8 | Solar | 05_12_24W1 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N |  | Hanover | Closed
National Grid | BLACKSTONE | 514443 | 01504 | 0 | Solar | 05_12_51T1 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 72 | 54 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-North | Closed
National Grid | LYNN | 294246 | 01904 | 0 | Solar | 05_14_33L1 | 06/01/2020 | 06/02/2020 | 0 | 0 | 0 | 06/03/2020 | 06/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2021 | Connected |  | N |  | Beverly | Closed
National Grid | MANCHESTER | 290418 | 01944 | 10 | Solar | 05_14_58L1 | 05/04/2020 | 05/11/2020 | 4 | 0 | 4 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2020 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BOXFORD | 726184 | 01921 | 10 | Solar | 05_14_73L2 | 10/20/2025 | 11/03/2025 | 9 | 6 | 3 | 11/04/2025 | 11/04/2025 | 83 | 25 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Worcester North/South | Closed
National Grid | WESTFORD | 175648 | 01886 | 4.73 | Solar | 05_14_92L1 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/16/2015 | N | EXP | 41 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 | 12/10/2015 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | WESTFORD | 425538 | 01886 | 250 | Solar | 05_01_24W2 | 06/01/2022 | 06/15/2022 | 10 | 2 | 8 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Bridgewater | Closed
National Grid | BILLERICA | 730060 | 01821 | 20 | Solar | 05_01_412L2 | 10/30/2025 | 10/31/2025 | 1 | 0 | 1 | 11/03/2025 | 11/03/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Worcester North/South | Closed
National Grid | WORCESTER | 185992 | 01606 | 8.4 | Solar | 05_01_55W1 | 07/17/2018 | 08/14/2018 | 19 | 0 | 19 | 08/15/2018 | 08/15/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  | 9/25/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | Connected |  | N |  | North Andover | Closed
National Grid | WEBSTER | 177909 | 01570 | 11.4 | Solar | 05_05_108W60 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/16/2017 | 8/21/2018 | Y | EXP | 348 | 01/18/2018 | 02/14/2018 | 19 | 0 | 19 | 2/27/2018 | 2/27/2018 | 3/6/2018 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 560141 | 01543 | 6 | Solar | 05_12_24W1 | 10/19/2023 | 11/13/2023 | 17 | 15 | 2 | 11/14/2023 | 11/14/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | BLACKSTONE | 516409 | 01504 | 15.007 | Solar | 05_12_51T1 | 04/14/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | LYNN | 306879 | 01904 | 20 | Solar | 05_14_33L1 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 | 08/14/2020 | 8/17/2021 | Y | EXP | 365 | 02/05/2021 | 02/04/2021 | 0 | 0 | 0 |  |  | 2/9/2021 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | GLOUCESTER | 292702 | 01930 | 0 | Solar | 05_14_58L1 | 05/20/2020 | 05/22/2020 | 1 | 0 | 1 | 05/26/2020 | 05/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N |  | Attleboro | Closed
National Grid | BOXFORD | 729822 | 01921 | 0 | Solar | 05_14_73L2 | 10/29/2025 | 11/12/2025 | 8 | 6 | 2 | 11/13/2025 | 11/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Worcester North/South | Closed
National Grid | WESTFORD | 177104 | 01886 | 288 | Solar | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 37 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N |  | Worcester North/South | Closed
National Grid | CHELMSFORD | 426710 | 01824 | 15.2 | Solar | 05_01_24W2 | 04/27/2022 | 04/29/2022 | 2 | 0 | 2 | 05/02/2022 | 05/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 8/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2022 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BILLERICA | 734850 | 01821 | 9.57 | Solar | 05_01_412L2 | 11/19/2025 | 11/20/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 | 11/19/2025 | 1/23/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Methuen/Haverhill | Closed
National Grid | WORCESTER | 190717 | 01605 | 10 | Solar | 05_01_55W1 | 07/13/2018 | 10/23/2018 | 30 | 24 | 6 | 10/24/2018 | 10/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 07/13/2018 | 8/28/2019 | Y | EXP | 32 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 5/23/2019 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | WEBSTER | 178247 | 01570 | 4990 | Solar | 05_05_108W60 | 03/27/2018 | 03/27/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | RUTLAND | 565880 | 01543 | 10 | Solar | 05_12_24W1 | 11/03/2023 | 11/07/2023 | 2 | 0 | 2 | 11/08/2023 | 11/08/2023 | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 11/03/2023 | 4/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N |  | Attleboro | Closed
National Grid | BLACKSTONE | 554842 | 01504 | 10 | Solar | 05_12_51T1 | 09/12/2023 | 09/14/2023 | 2 | 0 | 2 | 09/15/2023 | 09/15/2023 | 134 | 51 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed - Pending Customer Decision
National Grid | LYNN | 463152 | 01904 | 7.6 | Solar | 05_14_33L1 | 12/07/2022 | 12/08/2022 | 1 | 0 | 1 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 12/07/2022 | 5/29/2024 | Y | EXP | 365 | 03/28/2023 | 05/30/2023 | 64 | 0 | 64 |  |  | 6/2/2023 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | BEVERLY | 306363 | 01915 | 0 | Battery Add-On | 05_14_58L1 | 08/12/2020 | 08/14/2020 | 1 | 1 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | TOPSFIELD | 174304 | 01983 | 500 | Solar | 05_14_73L2 | 12/29/2011 | 12/29/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Tewksbury | Closed
National Grid | WESTFORD | 177103 | 01886 | 288 | Solar | 05_14_92L1 | 05/27/2016 | 05/27/2016 | 3 | 3 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 05/27/2016 | 7/5/2017 | Y | EXP | 32 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N |  | Worcester North/South | Closed
National Grid | WESTFORD | 436749 | 01886 | 2.32 | Solar | 05_01_24W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 65 | 40 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 06/17/2022 | 12/26/2024 | Y | EXP | 365 | 06/26/2024 | 07/02/2024 | 7 | 0 | 7 |  |  | 8/9/2024 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | BILLERICA | 743323 | 01821 | 10 | Solar | 05_01_412L2 | 01/05/2026 | 01/06/2026 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 195060 | 01605 | 10 | Solar | 05_01_55W1 | 09/04/2018 | 10/12/2018 | 11 | 10 | 1 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Closed
National Grid | WEBSTER | 178519 | 01570 | 7.6 | Solar | 05_05_108W60 | 04/04/2018 | 04/04/2018 | 14 | 0 | 14 | 05/17/2018 | 05/17/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/04/2018 | 11/30/2019 | Y | EXP | 541 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | RUTLAND | 573665 | 01543 | 7.6 | Solar | 05_12_24W1 | 12/11/2023 | 12/12/2023 | 1 | 0 | 1 | 12/13/2023 | 12/13/2023 | 64 | 40 | 24 | 05/03/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | BELLINGHAM | 567996 | 02019 | 10 | Solar | 05_12_51T1 | 11/15/2023 | 11/27/2023 | 7 | 0 | 7 | 11/28/2023 | 11/28/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | Time Frame Suspension
National Grid | LYNN | 462041 | 01904 | 14.79 | Solar | 05_14_33L1 | 11/17/2022 | 11/23/2022 | 4 | 1 | 3 | 11/25/2022 | 11/25/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2023 | Connected |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | ESSEX | 321713 | 01929 | 16 | Solar | 05_14_58L1 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 4/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N |  | Northampton | Closed
National Grid | BOXFORD | 175635 | 01921 | 998 | Solar | 05_14_73L2 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-South | Closed - Design Hold
National Grid | WESTFORD | 216947 | 01886 | 10 | Solar | 05_14_92L1 | 09/21/2019 | 09/25/2019 | 2 | 2 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/21/2019 | 5/28/2020 | Y | EXP | 365 | 12/27/2019 | 12/26/2019 | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | WESTFORD | 534808 | 01886 | 15.2 | Solar | 05_01_24W2 | 06/19/2023 | 08/01/2023 | 30 | 26 | 4 | 08/02/2023 | 08/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N |  | Billerica | Closed
National Grid | BILLERICA | 745414 | 01821 | 5.76 | Solar | 05_01_412L2 | 01/14/2026 | 01/20/2026 | 7 | 4 | 3 | 02/03/2026 | 02/03/2026 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N |  | Spencer-Rutland | Time Frame Suspension
National Grid | WORCESTER | 197026 | 01606 | 8.4 | Solar | 05_01_55W1 | 09/26/2018 | 11/08/2018 | 27 | 17 | 10 | 11/09/2018 | 11/09/2018 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 | 09/26/2018 | 12/23/2019 | Y | EXP | 365 | 06/18/2019 | 06/17/2019 | 0 | 0 | 0 |  |  | 8/1/2019 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | WEBSTER | 178665 | 01570 | 4200 | Solar | 05_05_108W60 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/17/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2018 | 03/16/2018 | 8/5/2022 | Y | STD | 55 | 02/09/2022 | 07/06/2022 | 146 | 0 | 146 |  |  | 7/19/2022 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | RUTLAND | 586866 | 01543 | 7.6 | Solar | 05_12_24W1 | 03/08/2024 | 03/11/2024 | 1 | 0 | 1 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/08/2024 | 4/24/2025 | Y | EXP | 365 | 05/11/2024 | 07/06/2024 | 57 | 0 | 57 |  |  | 7/13/2024 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | BLACKSTONE | 575964 | 01504 | 8.99 | Solar | 05_12_51T1 | 12/05/2023 | 12/11/2023 | 4 | 3 | 1 | 12/12/2023 | 12/12/2023 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | LYNN | 479868 | 01904 | 22.8 | Solar | 05_14_33L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-Northwest | Study Complete
National Grid | GLOUCESTER | 344742 | 01930 | 15.2 | Solar | 05_14_58L1 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | BOXFORD | 176615 | 01921 | 55 | Solar | 05_14_73L2 | 02/15/2016 | 02/15/2016 | 48 | 48 | 0 | 04/26/2016 | 04/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2016 |  | 2/21/2017 | N | EXP | 284 |  |  | 0 | 0 | 0 | 9/14/2016 | 9/14/2016 | 9/26/2016 | Connected |  | N |  | Beverly | Closed
National Grid | WESTFORD | 339861 | 01886 | 15.2 | Solar | 05_14_92L1 | 02/01/2021 | 02/04/2021 | 3 | 2 | 1 | 02/05/2021 | 02/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 4/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2021 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed - Completion Documents Hold
National Grid | CHELMSFORD | 540716 | 01863 | 0 | Solar | 05_01_24W2 | 07/14/2023 | 07/19/2023 | 3 | 0 | 3 | 07/20/2023 | 07/20/2023 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BILLERICA | 748720 | 01821 | 11.4 | Solar | 05_01_412L2 | 02/02/2026 | 02/03/2026 | 2 | 0 | 2 | 02/13/2026 | 02/13/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | WORCESTER | 199337 | 01606 | 4998 | Solar | 05_01_55W1 | 11/19/2018 | 12/05/2018 | 9 | 0 | 9 |  |  | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension - Completion Documents Hold
National Grid | WEBSTER | 185770 | 01570 | 11.4 | Solar | 05_05_108W60 | 05/18/2018 | 05/18/2018 | 5 | 0 | 5 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 | 05/18/2018 |  | Y | EXP | 466 | 07/11/2019 | 07/10/2019 | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | RUTLAND | 592974 | 01543 | 10.73 | Solar | 05_12_24W1 | 03/06/2024 | 03/21/2024 | 12 | 8 | 4 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N |  | Attleboro | Closed
National Grid | BELLINGHAM | 590822 | 02019 | 8.7 | Solar | 05_12_51T1 | 03/01/2024 | 03/08/2024 | 5 | 3 | 2 | 03/11/2024 | 03/11/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 03/01/2024 | 4/21/2025 | Y | EXP | 365 | 05/16/2024 | 10/02/2024 | 140 | 1 | 139 |  |  | 8/14/2024 | Connected |  | N |  | Leominster | Closed
National Grid | LYNN | 500918 | 01904 | 22.8 | Solar | 05_14_33L1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Billerica | Closed
National Grid | ESSEX | 351803 | 01929 | 10 | Solar | 05_14_58L1 | 04/09/2021 | 04/12/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N |  | Billerica | Closed
National Grid | BOXFORD | 194444 | 01921 | 7.6 | Solar | 05_14_73L2 | 08/26/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 599440 | 01886 | 15.744 | Solar | 05_14_92L1 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | Y |  | North Andover | Closed
National Grid | CHELMSFORD | 575704 | 01863 | 14.4 | Solar | 05_01_24W2 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 28 | 3 | 25 | 02/07/2024 | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 03/18/2024 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 5/30/2025 | N | EXP | 365 | 06/08/2024 | 08/28/2024 | 82 | 0 | 82 |  |  | 10/2/2024 | Connected |  | N |  | Scituate | Closed
National Grid | BILLERICA | 174756 | 01821 | 1000 | Solar | 05_01_412L2 | 02/03/2014 | 02/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2014 | 02/26/2014 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2014 |  | 8/14/2016 | N | STD | 681 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Somerset | Closed
National Grid | WORCESTER | 199325 | 01606 | 4998 | Solar | 05_01_55W1 | 11/19/2018 | 11/28/2018 | 4 | 0 | 4 |  |  | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/07/2020 | 63 | 3 | 60 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Cape Ann | Closed - Study Hold
National Grid | WEBSTER | 191437 | 01570 | 7.6 | Solar | 05_05_108W60 | 07/22/2018 | 10/01/2018 | 20 | 11 | 9 | 10/02/2018 | 10/02/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2018 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2020 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 606154 | 01543 | 7.6 | Solar | 05_12_24W1 | 04/23/2024 | 05/07/2024 | 3 | 0 | 3 | 05/08/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | BELLINGHAM | 610191 | 02019 | 5.76 | Solar | 05_12_51T1 | 05/14/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Common System Modifications Design In Progress - In Progress
National Grid | LYNN | 590429 | 01904 | 23 | Solar | 05_14_33L1 | 02/15/2024 | 02/22/2024 | 4 | 0 | 4 | 02/23/2024 | 02/23/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Closed
National Grid | MANCHESTER | 373166 | 01944 | 15.2 | Solar | 05_14_58L1 | 07/30/2021 | 09/08/2021 | 27 | 25 | 2 | 09/09/2021 | 09/09/2021 | 85 | 60 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2022 |  | 1/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2022 | Connected |  | N |  | Leominster | Closed
National Grid | TOPSFIELD | 273784 | 01983 | 8.88 | Solar | 05_14_73L2 | 02/03/2020 | 02/05/2020 | 1 | 1 | 0 | 02/06/2020 | 02/06/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2020 | Connected |  | N |  | Fall River-North | Closed
National Grid | CHELMSFORD | 637131 | 01824 | 5.76 | Solar | 05_14_92L1 | 09/02/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Closed
National Grid | CHELMSFORD | 576161 | 01863 | 10 | Solar | 05_01_24W2 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 44 | 19 | 25 | 05/22/2024 | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 6/11/2025 | N | EXP | 365 | 06/27/2024 | 07/10/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y |  | Millbury-Grafton | Closed
National Grid | BILLERICA | 175472 | 01821 | 762 | Solar | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 28 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 3/16/2016 | N | STD | 114 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 |  |  |  | Withdrawn |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 208913 | 01606 | 7.6 | Solar | 05_01_55W1 | 02/08/2019 | 02/20/2019 | 6 | 0 | 6 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 02/08/2019 | 7/22/2020 | Y | EXP | 365 | 10/05/2019 | 12/02/2019 | 58 | 0 | 58 |  |  | 2/28/2020 | Connected |  | N |  | Leominster | Closed
National Grid | WEBSTER | 215936 | 01570 | 10 | Solar | 05_05_108W60 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Closed - Study Hold
National Grid | RUTLAND | 610904 | 01543 | 10 | Solar | 05_12_24W1 | 05/14/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/14/2024 | 8/7/2025 | Y | EXP | 365 | 09/27/2024 | 01/09/2025 | 105 | 0 | 105 |  |  | 1/14/2025 | Connected |  | N |  | Billerica | Closed
National Grid | BELLINGHAM | 613784 | 02019 | 21.125 | Solar | 05_12_51T1 | 06/11/2024 | 06/14/2024 | 4 | 1 | 3 | 06/17/2024 | 06/17/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 9/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N |  | Leominster | Closed
National Grid | LYNN | 620928 | 01904 | 23 | Solar | 05_14_33L1 | 06/27/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/27/2024 | 7/25/2025 | Y | EXP | 365 | 10/04/2024 | 11/14/2024 | 42 | 0 | 42 |  |  | 10/8/2024 | Connected |  | N |  | Amesbury Newburyport | Closed
National Grid | BEVERLY | 406249 | 01915 | 8.7 | Solar | 05_14_58L1 | 01/12/2022 | 01/13/2022 | 1 | 0 | 1 | 01/14/2022 | 01/14/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 | 01/12/2022 | 5/21/2023 | Y | EXP | 365 | 04/22/2022 | 05/20/2022 | 29 | 0 | 29 |  |  | 8/24/2022 | Connected |  | N |  | Leominster | Closed
National Grid | TOPSFIELD | 297463 | 01983 | 10 | Solar | 05_14_73L2 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N |  | Cape Ann | Closed
National Grid | WESTFORD | 637006 | 01886 | 3.8 | Solar | 05_14_92L1 | 08/30/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Beverly | Closed
National Grid | CHELMSFORD | 587993 | 01863 | 3.77 | Solar | 05_01_24W2 | 04/16/2024 | 04/19/2024 | 3 | 1 | 2 | 04/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2024 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | BILLERICA | 175748 | 01821 | 16 | Solar | 05_01_412L2 | 10/30/2014 | 10/30/2014 | 6 | 4 | 2 | 11/10/2014 | 11/10/2014 | 251 | 0 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 12/30/2014 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | WORCESTER | 210006 | 01606 | 7.6 | Solar | 05_01_55W1 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension - Study Hold
National Grid | DUDLEY | 215927 | 01571 | 3960 | Solar | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/04/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | RUTLAND | 615444 | 01543 | 10.15 | Solar | 05_12_24W1 | 06/04/2024 | 06/14/2024 | 5 | 4 | 1 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N |  | Millbury-Grafton | Closed - Study Hold
National Grid | BLACKSTONE | 644032 | 01504 | 10 | Solar | 05_12_51T1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | LYNN | 624766 | 01904 | 9.86 | Solar | 05_14_33L1 | 07/15/2024 | 08/28/2024 | 3 | 1 | 2 | 08/29/2024 | 08/29/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 07/15/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | Y |  | Scituate | Closed
National Grid | MANCHESTER | 420189 | 01944 | 24.43 | Solar | 05_14_58L1 | 03/31/2022 | 04/06/2022 | 5 | 3 | 2 | 04/07/2022 | 04/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 |  | 4/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed - Study Hold
National Grid | TOPSFIELD | 317580 | 01983 | 9.28 | Solar | 05_14_73L2 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2021 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | WESTFORD | 648337 | 01886 | 10 | Solar | 05_14_92L1 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 93 | 71 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Bridgewater | Notice Period
National Grid | WESTFORD | 595137 | 01886 | 8.7 | Solar | 05_01_24W2 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | BILLERICA | 176055 | 01821 | 15.48 | Solar | 05_01_412L2 | 01/30/2015 | 01/30/2015 | 11 | 11 | 0 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 13 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 11/19/2015 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WORCESTER | 245447 | 01605 | 10 | Solar | 05_01_55W1 | 07/25/2019 | 07/30/2019 | 2 | 0 | 2 | 07/31/2019 | 07/31/2019 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 8/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 215920 | 01570 | 4950 | Solar | 05_05_108W60 | 04/24/2019 | 05/09/2019 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/01/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Closed - Pending Customer Decision
National Grid | RUTLAND | 625257 | 01543 | 5 | Solar | 05_12_24W1 | 07/18/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 9/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2025 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | BLACKSTONE | 653896 | 01504 | 7.6 | Solar | 05_12_51T1 | 11/15/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N |  | Leominster | Closed - Start Study
National Grid | LYNN | 630827 | 01904 | 4.64 | Solar | 05_14_33L1 | 08/07/2024 | 08/13/2024 | 7 | 3 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 08/07/2024 | 1/3/2026 | Y | EXP | 365 | 01/23/2025 | 01/30/2025 | 8 | 0 | 8 |  |  | 2/5/2025 | Connected |  | N |  | Leominster | Closed - Study Hold
National Grid | BEVERLY | 421774 | 01915 | 15.2 | Solar | 05_14_58L1 | 05/04/2022 | 05/04/2022 | 0 | 0 | 0 | 05/05/2022 | 05/05/2022 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 05/04/2022 | 10/9/2023 | Y | EXP | 365 | 08/30/2022 | 09/24/2022 | 26 | 0 | 26 |  |  | 11/24/2022 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | TOPSFIELD | 452930 | 01983 | 7.6 | Solar | 05_14_73L2 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2022 | 08/19/2022 | 9/30/2023 | Y | EXP | 365 | 12/06/2022 | 12/05/2022 | 0 | 0 | 0 |  |  | 3/17/2023 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | WESTFORD | 656745 | 01886 | 8.99 | Solar | 05_14_92L1 | 11/25/2024 | 03/04/2025 | 11 | 7 | 4 | 03/05/2025 | 03/05/2025 | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | WESTFORD | 598070 | 01886 | 7.6 | Solar | 05_01_24W2 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/21/2024 | 4/11/2025 | Y | EXP | 365 | 06/13/2024 | 09/11/2024 | 91 | 0 | 91 |  |  | 9/17/2024 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | BILLERICA | 176658 | 01821 | 6 | Solar | 05_01_412L2 | 04/19/2016 | 04/19/2016 | 13 | 13 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 4/26/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-Northwest | Closed
National Grid | WORCESTER | 282553 | 01606 | 4950 | Other | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 263498 | 01570 | 7.6 | Solar | 05_05_108W60 | 11/19/2019 | 11/20/2019 | 0 | 0 | 0 | 11/21/2019 | 11/21/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/19/2019 | 11/19/2020 | Y | EXP | 365 | 06/04/2020 | 07/07/2020 | 33 | 0 | 33 |  |  | 7/22/2020 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | RUTLAND | 630212 | 01543 | 7.6 | Solar | 05_12_24W1 | 08/05/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BLACKSTONE | 657144 | 01504 | 7.6 | Solar | 05_12_51T1 | 11/26/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y |  | Worcester North/South | Closed
National Grid | LYNN | 649671 | 01904 | 7.6 | Solar | 05_14_33L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-North | Closed - Completion Documents Hold
National Grid | BEVERLY | 462180 | 01915 | 13.63 | Solar | 05_14_58L1 | 10/10/2022 | 10/12/2022 | 2 | 0 | 2 | 10/13/2022 | 10/13/2022 | 15 | 0 | 15 | 11/08/2022 | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 12/13/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 1/6/2024 | N | EXP | 365 | 02/18/2023 | 05/05/2023 | 77 | 0 | 77 |  |  | 6/26/2023 | Connected |  | N |  | Amesbury Newburyport | Closed
National Grid | TOPSFIELD | 378620 | 01983 | 7.6 | Solar | 05_14_73L2 | 09/01/2021 | 09/02/2021 | 1 | 0 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2022 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress - In Progress
National Grid | WESTFORD | 668349 | 01886 | 11.5 | Solar | 05_14_92L1 | 01/28/2025 | 01/31/2025 | 3 | 0 | 3 | 02/03/2025 | 02/03/2025 | 51 | 33 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WESTFORD | 604247 | 01886 | 3.19 | Solar | 05_01_24W2 | 04/19/2024 | 04/24/2024 | 3 | 0 | 3 | 04/25/2024 | 04/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Closed
National Grid | BILLERICA | 176764 | 01821 | 6 | Solar | 05_01_412L2 | 02/24/2016 | 02/24/2016 | 5 | 5 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 08/04/2016 | 08/23/2016 | 13 | 0 | 13 | 4/4/2016 | 4/4/2016 | 9/15/2016 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WORCESTER | 284371 | 01606 | 4950 | Other | 05_01_55W1 | 04/07/2020 | 04/24/2020 | 12 | 9 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Millbury-Grafton | Closed
National Grid | WEBSTER | 294047 | 01570 | 15.2 | Solar | 05_05_108W60 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | RUTLAND | 645964 | 01543 | 7.6 | Solar | 05_12_24W1 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/7/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/28/2025 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | BLACKSTONE | 678570 | 01504 | 150 | Solar | 05_12_51T1 | 03/19/2025 | 04/30/2025 | 30 | 20 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Closed
National Grid | LYNN | 680660 | 01904 | 15.2 | Solar | 05_14_33L1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed
National Grid | MANCHESTER | 485002 | 01944 | 15.2 | Solar | 05_14_58L1 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 22 | 0 | 22 | 03/21/2023 | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 04/27/2023 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 4/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed - Construction Hold
National Grid | BOXFORD | 385131 | 01921 | 7.6 | Solar | 05_14_73L2 | 09/28/2021 | 10/01/2021 | 4 | 3 | 1 | 10/04/2021 | 10/04/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2021 |  | 9/30/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed
National Grid | WESTFORD | 670946 | 01886 | 7.6 | Solar | 05_14_92L1 | 02/12/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/12/2025 | 4/11/2026 | Y | EXP | 365 | 06/14/2025 | 06/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N |  | Scituate | Closed
National Grid | WESTFORD | 626022 | 01886 | 7.6 | Solar | 05_01_24W2 | 07/18/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 |  | 9/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N |  | Fall River-North | Closed
National Grid | BILLERICA | 176851 | 01821 | 45.6 | Solar | 05_01_412L2 | 11/11/2015 | 11/11/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 | 11/11/2015 | 11/18/2016 | Y | EXP | 35 | 05/11/2016 | 07/13/2016 | 42 | 0 | 42 | 12/4/2015 | 12/4/2015 | 8/23/2016 | Connected |  | N |  | Brockton-North | 160 Day Study - Construction Hold
National Grid | WORCESTER | 294525 | 01605 | 10 | Solar | 05_01_55W1 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2020 | 06/06/2020 | 10/7/2021 | Y | EXP | 365 | 04/07/2021 | 04/15/2021 | 8 | 0 | 8 |  |  | 8/14/2021 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | WEBSTER | 304759 | 01570 | 9.8 | Solar | 05_05_108W60 | 10/02/2020 | 10/15/2020 | 8 | 8 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 10/02/2020 | 10/15/2021 | Y | EXP | 365 | 03/31/2021 | 05/21/2021 | 51 | 0 | 51 |  |  | 5/27/2021 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | RUTLAND | 660596 | 01543 | 2.03 | Solar | 05_12_24W1 | 12/13/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Closed
National Grid | BLACKSTONE | 683594 | 01504 | 10 | Solar | 05_12_51T1 | 04/08/2025 | 05/19/2025 | 3 | 0 | 3 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/08/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | Y |  | Brockton-North | 160 Day Study
National Grid | LYNN | 701737 | 01904 | 17.6 | Solar | 05_14_33L1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N |  | Scituate | Closed
National Grid | ESSEX | 491393 | 01929 | 14.592 | Solar | 05_14_58L1 | 01/19/2023 | 01/20/2023 | 1 | 0 | 1 | 01/23/2023 | 01/23/2023 | 274 | 112 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Attleboro | Time Frame Suspension
National Grid | BOXFORD | 392677 | 01921 | 7.6 | Solar | 05_14_73L2 | 04/25/2022 | 06/15/2022 | 36 | 35 | 1 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 | 04/25/2022 | 8/20/2023 | Y | EXP | 365 | 12/22/2022 | 02/17/2023 | 58 | 0 | 58 |  |  | 5/11/2023 | Connected |  | N |  | Tewksbury | Closed
National Grid | WESTFORD | 688427 | 01886 | 20 | Solar | 05_14_92L1 | 05/02/2025 | 05/27/2025 | 16 | 14 | 2 | 05/28/2025 | 05/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Closed
National Grid | WESTFORD | 630081 | 01886 | 7.6 | Solar | 05_01_24W2 | 08/05/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N |  | Walpole/Foxboro | Closed - Design Hold
National Grid | BILLERICA | 176899 | 01821 | 23.4 | Solar | 05_01_412L2 | 01/26/2016 | 01/26/2016 | 3 | 3 | 0 | 01/29/2016 | 01/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 |  | 1/31/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/16/2016 | 9/16/2016 | 9/16/2016 | Connected |  | N |  | Walpole/Foxboro | Closed - Construction Hold
National Grid | WORCESTER | 309418 | 01605 | 10 | Solar | 05_01_55W1 | 08/27/2020 | 08/28/2020 | 1 | 1 | 0 | 08/31/2020 | 08/31/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2020 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | WEBSTER | 316764 | 01570 | 10 | Solar | 05_05_108W60 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 |  | Y | EXP |  | 02/09/2021 | 05/18/2021 | 98 | 0 | 98 |  |  | 6/2/2021 | Connected |  | N |  | Somerset | Closed
National Grid | RUTLAND | 668006 | 01543 | 5.76 | Solar | 05_12_24W1 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/27/2025 | 4/11/2026 | Y | EXP | 365 | 07/03/2025 | 07/02/2025 | 0 | 0 | 0 |  |  | 8/18/2025 | Connected |  | N |  | Somerset | Closed
National Grid | BLACKSTONE | 692067 | 01504 | 13.3 | Solar | 05_12_51T1 | 05/15/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 05/15/2025 | 8/14/2026 | Y | EXP | 365 | 10/17/2025 | 11/21/2025 | 36 | 0 | 36 |  |  | 11/26/2025 | Connected |  | N |  | Somerset | Closed
National Grid | LYNN | 720945 | 01904 | 23 | Solar | 05_14_33L1 | 09/22/2025 | 09/24/2025 | 2 | 0 | 2 | 09/25/2025 | 09/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Somerset | Closed
National Grid | GLOUCESTER | 506132 | 01930 | 15.2 | Solar | 05_14_58L1 | 03/02/2023 | 03/07/2023 | 3 | 0 | 3 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Closed
National Grid | TOPSFIELD | 402422 | 01983 | 7.6 | Solar | 05_14_73L2 | 03/17/2022 | 03/18/2022 | 1 | 0 | 1 | 03/21/2022 | 03/21/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N |  | Dracut | Closed
National Grid | WESTFORD | 719555 | 01886 | 11.4 | Solar | 05_14_92L1 | 09/16/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 84 | 25 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Dracut | Closed
National Grid | WESTFORD | 639285 | 01886 | 7.6 | Solar | 05_01_24W2 | 09/11/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N |  | Beverly | Closed
National Grid | BILLERICA | 177152 | 01821 | 762 | Solar | 05_01_412L2 | 11/26/2014 | 11/26/2014 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2015 | 02/04/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2015 | 11/26/2014 | 12/31/2017 | Y | STD | 766 | 08/11/2017 | 09/09/2017 | 20 | 0 | 20 | 12/1/2017 | 12/1/2017 | 12/19/2017 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WORCESTER | 312260 | 01605 | 5.52 | Solar | 05_01_55W1 | 09/29/2020 | 12/03/2020 | 43 | 40 | 3 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 | 09/29/2020 | 12/24/2022 | Y | EXP | 55 | 01/28/2021 | 02/25/2021 | 28 | 0 | 28 |  |  | 12/8/2022 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 321256 | 01570 | 7.6 | Solar | 05_05_108W60 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/23/2020 | 10/27/2021 | Y | EXP | 365 | 02/05/2021 | 02/12/2021 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y |  | Fall River-North | Closed
National Grid | RUTLAND | 679840 | 01543 | 3.8 | Solar | 05_12_24W1 | 04/10/2025 | 06/06/2025 | 12 | 9 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | BELLINGHAM | 698492 | 02019 | 11.4 | Solar | 05_12_51T1 | 06/13/2025 | 06/30/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | LYNN | 724078 | 01904 | 16 | Solar | 05_14_33L1 | 10/04/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | BEVERLY | 515435 | 01915 | 12.6 | Solar | 05_14_58L1 | 03/29/2023 | 03/31/2023 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 6/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress - In Progress
National Grid | TOPSFIELD | 415211 | 01983 | 7.6 | Solar | 05_14_73L2 | 09/29/2022 | 03/07/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N |  | Scituate | Closed
National Grid | WESTFORD | 727308 | 01886 | 11.4 | Solar | 05_14_92L1 | 10/17/2025 | 10/23/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Cape Ann | Closed - Study Hold
National Grid | CHELMSFORD | 640951 | 01863 | 10 | Solar | 05_01_24W2 | 09/17/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 25 | 0 | 25 | 02/03/2025 | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/14/2026 | N | EXP | 365 | 05/28/2025 | 06/25/2025 | 29 | 0 | 29 |  |  | 7/16/2025 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | BILLERICA | 177281 | 01821 | 1000 | Solar | 05_01_412L2 | 02/08/2017 | 02/17/2017 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2017 | 02/22/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2018 | 02/08/2017 | 11/12/2021 | Y | STD | 571 | 02/06/2021 | 08/13/2021 | 189 | 0 | 189 | 8/16/2021 | 9/30/2021 | 11/2/2021 | Connected |  | N |  | Leominster | Closed
National Grid | WORCESTER | 318655 | 01605 | 0 | Other | 05_01_55W1 | 12/04/2020 | 01/05/2021 | 20 | 16 | 4 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 01/06/2021 | 02/09/2021 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 325072 | 01570 | 0 | Solar | 05_05_108W60 | 11/13/2020 | 12/15/2020 | 20 | 17 | 3 | 12/16/2020 | 12/16/2020 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Ayer-Clinton | Closed - Awaiting Payment
National Grid | RUTLAND | 684334 | 01543 | 10 | Solar | 05_12_24W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/10/2025 | 6/12/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/27/2025 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BLACKSTONE | 704375 | 01504 | 24.7 | Solar | 05_12_51T1 | 07/14/2025 | 07/30/2025 | 10 | 8 | 2 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | LYNN | 731440 | 01904 | 11 | Solar | 05_14_33L2 | 11/05/2025 | 11/05/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Walpole/Foxboro | Closed - Design Hold
National Grid | BEVERLY | 541791 | 01915 | 15.2 | Solar | 05_14_58L1 | 07/18/2023 | 07/24/2023 | 4 | 2 | 2 | 07/25/2023 | 07/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2023 | 07/18/2023 | 1/24/2025 | Y | EXP | 365 | 03/29/2024 | 06/05/2024 | 69 | 0 | 69 |  |  | 6/15/2024 | Connected |  | N |  | Somerset | Closed
National Grid | BOXFORD | 423112 | 01921 | 7.6 | Solar | 05_14_73L2 | 04/11/2022 | 04/12/2022 | 1 | 0 | 1 | 04/13/2022 | 04/13/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed - Pending Customer Decision
National Grid | WESTFORD | 511257 | 01886 | 249 | Solar | 05_14_92L2 | 03/16/2023 | 04/07/2023 | 16 | 6 | 10 | 04/10/2023 | 04/10/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 03/16/2023 | 7/22/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N |  | Millbury-Grafton | Closed
National Grid | WESTFORD | 645210 | 01886 | 7.6 | Solar | 05_01_24W2 | 10/04/2024 | 11/04/2024 | 8 | 4 | 4 | 11/05/2024 | 11/05/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | BILLERICA | 178324 | 01821 | 2000 | Solar | 05_01_412L2 | 03/29/2018 | 04/09/2018 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2018 | 05/12/2018 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | Scoping Meeting
National Grid | WORCESTER | 452194 | 01605 | 6.09 | Solar | 05_01_55W1 | 10/27/2022 | 11/22/2022 | 17 | 15 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2022 | 10/27/2022 | 6/14/2024 | Y | EXP | 365 | 06/06/2023 | 06/14/2023 | 9 | 0 | 9 |  |  | 7/12/2023 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WEBSTER | 344703 | 01570 | 6.72 | Solar | 05_05_108W60 | 03/24/2021 | 04/02/2021 | 6 | 6 | 0 | 04/05/2021 | 04/05/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 4/1/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | RUTLAND | 703102 | 01543 | 15.2 | Solar | 05_12_24W1 | 07/07/2025 | 07/11/2025 | 38 | 38 | 0 | 08/29/2025 | 08/29/2025 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | BLACKSTONE | 711434 | 01504 | 11.5 | Solar | 05_12_51T1 | 08/12/2025 | 08/15/2025 | 3 | 0 | 3 | 08/18/2025 | 08/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N |  | Brockton-North | 160 Day Study - Completion Documents Hold
National Grid | LYNN | 177680 | 01904 | 45.6 | Solar | 05_14_33L2 | 07/25/2017 | 07/25/2017 | 35 | 33 | 2 | 09/13/2017 | 09/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2017 |  | 7/30/2018 | N | EXP | 32 |  |  | 0 | 0 | 0 | 2/13/2018 | 2/13/2018 | 2/13/2018 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | ESSEX | 547989 | 01929 | 15.2 | Solar | 05_14_58L1 | 08/14/2023 | 08/15/2023 | 2 | 1 | 1 | 08/16/2023 | 08/16/2023 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2024 | Connected |  | N |  | Cape Ann | Closed
National Grid | BOXFORD | 424042 | 01921 | 10 | Solar | 05_14_73L2 | 05/05/2022 | 05/25/2022 | 14 | 14 | 0 | 05/26/2022 | 05/26/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2022 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | WESTFORD | 724655 | 01886 | 11.5 | Solar | 05_14_92L2 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | WESTFORD | 652585 | 01886 | 9.074 | Solar | 05_01_24W2 | 11/06/2024 | 11/25/2024 | 3 | 1 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | BILLERICA | 190782 | 01821 | 23.04 | Solar | 05_01_412L2 | 07/16/2018 | 08/29/2018 | 31 | 0 | 31 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-South | Closed
National Grid | WORCESTER | 367324 | 01605 | 11.025 | Solar | 05_01_55W1 | 07/25/2021 | 09/03/2021 | 30 | 30 | 0 | 09/07/2021 | 09/07/2021 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 373157 | 01570 | 3.8 | Solar | 05_05_108W60 | 08/06/2021 | 08/10/2021 | 2 | 0 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 |  | 4/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2023 | Connected |  | N |  | Billerica | Closed - Design Hold
National Grid | RUTLAND | 741965 | 01543 | 15.2 | Solar | 05_12_24W2 | 12/23/2025 | 12/24/2025 | 1 | 0 | 1 | 01/22/2026 | 01/22/2026 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | North Andover | Closed - Construction Hold
National Grid | BELLINGHAM | 713829 | 02019 | 17.6 | Solar | 05_12_51T1 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N |  | Scituate | Closed
National Grid | LYNN | 178574 | 01904 | 11.4 | Solar | 05_14_33L2 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 7/15/2020 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 3/23/2020 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | MANCHESTER | 549217 | 01944 | 7.6 | Solar | 05_14_58L1 | 08/17/2023 | 08/21/2023 | 2 | 1 | 1 | 08/22/2023 | 08/22/2023 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | TOPSFIELD | 437862 | 01983 | 7.6 | Solar | 05_14_73L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 204 | 184 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 175361 | 01886 | 8 | Solar | 05_14_92L2 | 11/13/2014 | 11/13/2014 | 5 | 0 | 5 | 11/21/2014 | 11/21/2014 | 249 | 0 | 249 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 |  | 1/11/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | WESTFORD | 657142 | 01886 | 7.6 | Solar | 05_01_24W2 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 11/26/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N |  | Worcester North/South | Closed
National Grid | BILLERICA | 190340 | 01821 | 1500 | Solar | 05_01_412L2 | 08/16/2018 | 08/27/2018 | 3 | 0 | 3 |  |  | 53 | 19 | 34 |  |  | 0 | 0 | 0 | 09/13/2018 | 11/12/2018 | 42 | 8 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Worcester North/South | Closed
National Grid | WORCESTER | 368515 | 01606 | 4300 | Solar | 05_01_55W1 | 08/10/2021 | 09/07/2021 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2021 | 10/05/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Attleboro | Closed
National Grid | WEBSTER | 376465 | 01570 | 15.2 | Solar | 05_05_108W60 | 08/17/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 176 | 153 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Attleboro | Closed
National Grid | RUTLAND | 753974 | 01543 |  | Battery Add-On | 05_12_24W2 | 03/02/2026 | 03/04/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Worcester North/South | Closed
National Grid | BLACKSTONE | 724900 | 01504 | 9.5 | Solar | 05_12_51T1 | 10/08/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2026 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications - Completion Documents Hold
National Grid | LYNN | 348454 | 01904 | 10 | Solar | 05_14_33L2 | 04/14/2021 | 04/14/2021 | 0 | 0 | 0 | 04/15/2021 | 04/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 | 04/14/2021 | 4/14/2022 | Y | EXP | 365 | 07/14/2021 | 07/13/2021 | 0 | 0 | 0 |  |  | 9/2/2021 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | MANCHESTER | 555011 | 01944 | 9.57 | Solar | 05_14_58L1 | 09/25/2023 | 09/28/2023 | 4 | 1 | 3 | 09/29/2023 | 09/29/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications - Pending Customer Decision
National Grid | TOPSFIELD | 442456 | 01983 | 7.6 | Solar | 05_14_73L2 | 07/20/2022 | 07/21/2022 | 1 | 0 | 1 | 07/22/2022 | 07/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 176022 | 01886 | 3 | Solar | 05_14_92L2 | 03/25/2015 | 03/25/2015 | 6 | 0 | 6 | 04/03/2015 | 04/03/2015 | 464 | 0 | 464 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2015 |  | 8/31/2015 | N | EXP | 147 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-North | 160 Day Study
National Grid | WESTFORD | 667809 | 01886 | 480 | Solar | 05_01_24W2 | 09/16/2025 |  | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | BILLERICA | 196422 | 01821 | 66.6 | Solar | 05_01_412L2 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  | 6/30/2020 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WORCESTER | 378372 | 01606 | 5.52 | Solar | 05_01_55W1 | 10/11/2021 | 10/19/2021 | 6 | 6 | 0 | 10/20/2021 | 10/20/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/11/2021 | 10/21/2023 | Y | EXP | 555 | 02/01/2022 | 02/14/2022 | 14 | 0 | 14 |  |  | 8/23/2023 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WEBSTER | 379282 | 01570 | 9.6 | Solar | 05_05_108W60 | 11/03/2021 | 12/16/2021 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/03/2021 | 7/28/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | Y |  | Millbury-Grafton | Closed
National Grid | RUTLAND | 176935 | 01543 | 6 | Solar | 05_12_24W2 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 01/29/2016 | 2/6/2017 | Y | EXP | 336 |  |  | 0 | 0 | 0 | 9/19/2016 | 9/19/2016 | 9/19/2016 | Connected |  | N |  | Billerica | Closed
National Grid | BELLINGHAM | 732153 | 02019 | 23 | Solar | 05_12_51T1 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N |  | Worcester North/South | Closed
National Grid | LYNN | 499234 | 01904 | 15 | Solar | 05_14_33L2 | 02/07/2023 | 02/21/2023 | 10 | 9 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2023 | Connected |  | N |  | Brockton-South | Closed
National Grid | BEVERLY | 637421 | 01915 | 5.525 | Solar | 05_14_58L1 | 09/04/2024 | 09/24/2024 | 8 | 4 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N |  | Attleboro | Closed - Construction Hold
National Grid | BOXFORD | 445349 | 01921 | 7.6 | Solar | 05_14_73L2 | 07/19/2022 | 07/22/2022 | 4 | 3 | 1 | 07/25/2022 | 07/25/2022 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Northampton | Closed
National Grid | WESTFORD | 176148 | 01886 | 172 | Solar | 05_14_92L2 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 9/5/2016 | N | EXP | 37 |  |  | 0 | 0 | 0 | 2/2/2016 | 2/2/2016 | 5/5/2016 | Connected |  | N |  | Northampton | Closed - Design Hold
National Grid | WESTFORD | 718545 | 01886 | 4.93 | Solar | 05_01_24W2 | 09/11/2025 | 10/24/2025 | 5 | 1 | 4 | 10/27/2025 | 10/27/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Northampton | Closed
National Grid | BILLERICA | 206984 | 01821 | 3.8 | Solar | 05_01_412L2 | 02/10/2019 | 02/19/2019 | 5 | 0 | 5 | 02/20/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 390938 | 01605 | 10 | Solar | 05_01_55W1 | 11/08/2021 | 12/13/2021 | 3 | 1 | 2 | 11/12/2021 | 11/12/2021 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/08/2021 |  | Y | EXP | 365 | 03/08/2022 | 04/11/2022 | 35 | 0 | 35 |  |  | 4/19/2022 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 412984 | 01570 | 3.8 | Solar | 05_05_108W60 | 02/17/2022 | 02/23/2022 | 3 | 0 | 3 | 02/24/2022 | 02/24/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | RUTLAND | 195033 | 01543 | 22.8 | Solar | 05_12_24W2 | 09/04/2018 | 10/17/2018 | 10 | 10 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BELLINGHAM | 445040 | 02019 | 250 | Solar | 05_12_51T2 | 08/08/2022 | 08/31/2022 | 17 | 7 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | LYNN | 566735 | 01904 | 34.2 | Solar | 05_14_33L2 | 02/28/2024 | 07/12/2024 | 93 | 90 | 3 | 07/15/2024 | 07/15/2024 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N |  | Ayer-Clinton | Closed - Completion Documents Hold
National Grid | HAMILTON | 427890 | 01982 | 875 | Solar | 05_14_58L2 | 08/25/2022 | 12/13/2022 | 74 | 64 | 10 |  |  | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | BOXFORD | 445187 | 01921 | 15.08 | Solar | 05_14_73L2 | 07/18/2022 | 08/03/2022 | 13 | 11 | 2 | 08/04/2022 | 08/04/2022 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 | 07/18/2022 | 10/1/2023 | Y | EXP | 365 | 10/19/2022 | 11/09/2022 | 22 | 0 | 22 |  |  | 11/29/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 176761 | 01824 | 7.6 | Solar | 05_14_92L2 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | CHELMSFORD | 720253 | 01863 | 3.8 | Solar | 05_01_24W2 | 09/18/2025 | 09/30/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | BILLERICA | 207611 | 01821 | 500 | Solar | 05_01_412L2 | 03/14/2019 | 04/30/2019 | 33 | 26 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2019 | 06/03/2019 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | Closed - Internal Review
National Grid | WORCESTER | 417891 | 01606 | 6.528 | Solar | 05_01_55W1 | 04/29/2022 | 04/29/2022 | 0 | 0 | 0 | 05/02/2022 | 05/02/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2022 |  | 5/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed - Internal Review
National Grid | WEBSTER | 420677 | 01570 | 6 | Solar | 05_05_108W60 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 | 04/04/2022 | 1/27/2024 | Y | EXP | 365 | 06/11/2022 | 01/26/2023 | 230 | 0 | 230 |  |  | 2/14/2023 | Connected |  | Y |  | Spencer-Rutland | Scoping Meeting
National Grid | RUTLAND | 251755 | 01543 | 10 | Solar | 05_12_24W2 | 10/17/2019 | 10/21/2019 | 1 | 0 | 1 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/17/2019 | 10/17/2020 | Y | EXP | 365 | 02/25/2020 | 04/13/2020 | 48 | 0 | 48 |  |  | 4/29/2020 | Connected |  | N |  | Leominster | Closed
National Grid | BELLINGHAM | 515409 | 02019 | 34.6 | Solar | 05_12_51T2 | 05/24/2023 | 07/14/2023 | 34 | 24 | 10 | 07/17/2023 | 07/17/2023 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 | 05/24/2023 | 7/2/2026 | Y | EXP | 22 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | LYNN | 667060 | 01904 | 23 | Solar | 05_14_33L2 | 01/21/2025 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Closed
National Grid | HAMILTON | 744151 | 01982 | 11.52 | Solar | 05_14_58L2 | 01/09/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Leominster | Closed
National Grid | BOXFORD | 473412 | 01921 | 15.2 | Solar | 05_14_73L2 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/01/2022 | 12/19/2023 | Y | EXP | 365 | 01/28/2023 | 02/15/2023 | 19 | 0 | 19 |  |  | 6/13/2023 | Connected |  | N |  | Leominster | Closed
National Grid | CHELMSFORD | 177216 | 01824 | 75 | Solar | 05_14_92L2 | 06/10/2016 | 06/10/2016 | 4 | 4 | 0 | 06/17/2016 | 06/17/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/18/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WESTFORD | 751295 | 01886 | 11.5 | Solar | 05_01_24W2 | 02/16/2026 | 02/18/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BILLERICA | 226260 | 01821 | 150 | Solar | 05_01_412L2 | 05/08/2019 | 05/21/2019 | 7 | 0 | 7 | 05/22/2019 | 05/22/2019 | 21 | 9 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 504707 | 01606 | 10 | Solar | 05_01_55W1 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Billerica | Closed
National Grid | WEBSTER | 425396 | 01570 | 10 | Solar | 05_05_108W60 | 06/16/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/16/2022 | 2/2/2024 | Y | EXP | 365 | 10/12/2022 | 01/14/2023 | 95 | 0 | 95 |  |  | 5/23/2023 | Connected |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | RUTLAND | 309907 | 01543 | 7.6 | Solar | 05_12_24W2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | BELLINGHAM | 653313 | 02019 | 240 | Solar | 05_12_51T2 | 11/13/2024 | 12/10/2024 | 18 | 8 | 10 |  |  | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N |  | Millbury-Grafton | Closed
National Grid | LYNN | 670708 | 01904 | 10 | Solar | 05_14_33L2 | 02/07/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WENHAM | 174602 | 01984 | 95 | Solar | 05_14_58L2 | 09/20/2011 | 09/20/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2011 |  | 1/20/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 1/20/2012 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | TOPSFIELD | 642436 | 01983 | 10 | Solar | 05_14_73L2 | 09/29/2024 | 10/17/2024 | 5 | 2 | 3 | 10/18/2024 | 10/18/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 09/29/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WESTFORD | 178502 | 01886 | 250 | Solar | 05_14_92L2 | 12/15/2017 | 12/15/2017 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 | 12/15/2017 | 12/20/2019 | Y | STD | 66 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N |  | Brockton-South | Closed
National Grid | CHELMSFORD | 690411 | 01863 | 7.6 | Solar | 05_01_24W3 | 05/07/2025 | 05/21/2025 | 4 | 0 | 4 | 06/10/2025 | 06/10/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 | 05/07/2025 | 8/18/2026 | Y | EXP | 365 | 11/07/2025 |  | 120 | 0 | 120 |  |  |  | Completion Documents |  | N |  | Brockton-South | Closed
National Grid | BILLERICA | 293823 | 01821 | 8.88 | Solar | 05_01_412L2 | 05/28/2020 | 06/03/2020 | 3 | 0 | 3 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N |  | North Andover | Closed
National Grid | WORCESTER | 506739 | 01606 | 6.96 | Solar | 05_01_55W1 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 5/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N |  | MPL-Northwest | Study Complete
National Grid | DUDLEY | 469025 | 01571 | 3.8 | Solar | 05_05_108W60 | 10/21/2022 | 10/26/2022 | 4 | 1 | 3 | 10/27/2022 | 10/27/2022 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-North | 160 Day Study
National Grid | RUTLAND | 362370 | 01543 | 10 | Solar | 05_12_24W2 | 06/09/2021 | 06/15/2021 | 4 | 3 | 1 | 06/16/2021 | 06/16/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 | 06/09/2021 | 10/12/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 24 | 0 | 24 |  |  | 10/18/2021 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress - In Progress
National Grid | BLACKSTONE | 714498 | 01504 | 20 | Solar | 05_12_51T2 | 08/25/2025 | 09/03/2025 | 6 | 1 | 5 | 09/04/2025 | 09/04/2025 | 39 | 26 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/25/2025 | 11/18/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N |  | Methuen/Haverhill | Closed
National Grid | LYNN | 686801 | 01904 | 11.78 | Solar | 05_14_33L2 | 04/22/2025 | 07/25/2025 | 37 | 24 | 13 | 07/28/2025 | 07/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Cape Ann | Closed - Conditional Approval Hold
National Grid | HAMILTON | 175285 | 01982 | 30 | Solar | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 5 | 1 | 4 | 11/14/2014 | 11/14/2014 | 147 | 4 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 1/30/2015 | Y | EXP | 5 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N |  | Beverly | Closed
National Grid | BOXFORD | 648149 | 01921 | 23 | Solar | 05_14_73L2 | 10/18/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Somerset | Closed
National Grid | CHELMSFORD | 192826 | 01824 | 3.64 | Solar | 05_14_92L2 | 08/20/2018 | 09/13/2018 | 7 | 1 | 6 | 09/14/2018 | 09/14/2018 | 68 | 3 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-South | Closed
National Grid | CHELMSFORD | 716020 | 01824 | 11.5 | Solar | 05_01_24W3 | 09/28/2025 | 10/06/2025 | 5 | 1 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Leominster | Closed
National Grid | BILLERICA | 317070 | 01821 | 10 | Solar | 05_01_412L2 | 10/19/2020 | 11/03/2020 | 10 | 8 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 4/11/2022 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WORCESTER | 505628 | 01606 | 7.83 | Solar | 05_01_55W1 | 03/03/2023 | 03/07/2023 | 2 | 0 | 2 | 03/08/2023 | 03/08/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 03/03/2023 | 8/1/2024 | Y | EXP | 365 | 10/04/2023 | 10/16/2023 | 13 | 0 | 13 |  |  | 10/30/2023 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 478954 | 01570 | 10 | Solar | 05_05_108W60 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/23/2023 | 4/18/2024 | Y | EXP | 365 | 03/21/2023 | 04/19/2023 | 30 | 0 | 30 |  |  | 7/17/2023 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | RUTLAND | 367457 | 01543 | 7.6 | Solar | 05_12_24W2 | 07/09/2021 | 07/12/2021 | 1 | 0 | 1 | 07/13/2021 | 07/13/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/09/2021 | 8/16/2022 | Y | EXP | 365 | 01/13/2022 | 03/31/2022 | 78 | 0 | 78 |  |  | 4/11/2022 | Connected |  | N |  | Cape Ann | Closed
National Grid | BLACKSTONE | 724733 | 01504 | 0 | Solar | 05_12_51T2 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Cape Ann | Closed - Sent to Customer
National Grid | LYNN | 697072 | 01904 | 20.16 | Solar | 05_14_33L2 | 06/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N |  | Fall River-South | Closed
National Grid | HAMILTON | 175898 | 01982 | 476 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-South | Closed
National Grid | BOXFORD | 650207 | 01921 | 12.16 | Solar | 05_14_73L2 | 10/28/2024 | 11/26/2024 | 9 | 6 | 3 | 11/27/2024 | 11/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications - Completion Documents Hold
National Grid | CHELMSFORD | 213493 | 01824 | 10 | Solar | 05_14_92L2 | 04/10/2019 | 05/29/2019 | 48 | 47 | 1 | 06/20/2019 | 06/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 04/10/2019 | 7/31/2020 | Y | EXP | 365 | 02/22/2020 | 06/03/2020 | 102 | 0 | 102 |  |  | 7/10/2020 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | CHELMSFORD | 175256 | 01863 | 56 | Solar | 05_01_24W3 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/17/2015 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BILLERICA | 325654 | 01821 | 10 | Solar | 05_01_412L2 | 11/12/2020 | 01/25/2021 | 50 | 48 | 2 | 01/26/2021 | 01/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2021 | Connected |  | N |  | Beverly | Closed
National Grid | WORCESTER | 526469 | 01606 | 9.86 | Solar | 05_01_55W1 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 58 | 38 | 20 | 09/26/2023 | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  | 11/20/2023 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 3/4/2025 | N | EXP | 365 | 04/19/2024 | 05/14/2024 | 26 | 0 | 26 |  |  | 6/6/2024 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 480519 | 01570 | 0 | Solar | 05_05_108W60 | 11/28/2022 | 11/29/2022 | 2 | 1 | 1 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 2/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N |  | North Andover | Closed - Construction Hold
National Grid | RUTLAND | 438823 | 01543 | 7.6 | Solar | 05_12_24W2 | 08/18/2022 | 08/23/2022 | 4 | 3 | 1 | 08/24/2022 | 08/24/2022 | 47 | 28 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Chelmsford/Westford | Closed
National Grid | BLACKSTONE | 729870 | 01504 | 9.28 | Solar | 05_12_51T2 | 11/02/2025 | 11/18/2025 | 10 | 5 | 5 | 11/19/2025 | 11/19/2025 | 73 | 59 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Brockton-North | 160 Day Study
National Grid | LYNN | 177297 | 01904 | 16 | Solar | 05_14_34M1 | 08/26/2016 | 08/26/2016 | 7 | 7 | 0 | 09/08/2016 | 09/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/3/2017 | N | EXP | 359 |  |  | 0 | 0 | 0 | 11/21/2016 | 11/21/2016 | 11/23/2016 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | ESSEX | 175897 | 01929 | 1988 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BYFIELD | 657626 | 01922 | 3.8 | Solar | 05_14_73L2 | 11/29/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | CHELMSFORD | 214979 | 01824 | 3.8 | Solar | 05_14_92L2 | 03/22/2019 | 07/22/2019 | 86 | 86 | 0 | 07/23/2019 | 07/23/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/29/2019 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  | 11/13/2019 | Connected |  | N |  | Scituate | Closed
National Grid | WESTFORD | 175457 | 01886 | 56 | Solar | 05_01_24W3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2014 |  | 11/28/2014 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 1/21/2016 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BILLERICA | 440022 | 01821 | 3.77 | Solar | 05_01_412L2 | 07/15/2022 | 08/12/2022 | 21 | 20 | 1 | 08/15/2022 | 08/15/2022 | 63 | 44 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 |  | 11/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N |  | Cape Ann | Closed
National Grid | WORCESTER | 534007 | 01606 | 6 | Solar | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 2 | 0 | 2 | 07/03/2023 | 07/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Worcester North/South | Closed
National Grid | WEBSTER | 489055 | 01570 | 10 | Solar | 05_05_108W60 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Attleboro | Time Frame Suspension
National Grid | RUTLAND | 552287 | 01543 | 10 | Solar | 05_12_24W2 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2023 | 10/11/2023 | 2/14/2025 | Y | EXP | 365 | 04/11/2024 | 04/29/2024 | 19 | 0 | 19 |  |  | 5/5/2024 | Connected |  | N |  | Dracut | Closed - Construction Hold
National Grid | BELLINGHAM | 746712 | 02019 | 0 | Battery Add-On | 05_12_51T2 | 01/21/2026 | 01/27/2026 | 4 | 0 | 4 | 01/28/2026 | 01/28/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Leominster | Closed
National Grid | LYNN | 277157 | 01904 | 0 | Battery Add-On | 05_14_34M1 | 01/30/2020 | 01/31/2020 | 1 | 1 | 0 | 02/03/2020 | 02/03/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2020 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | BEVERLY | 175896 | 01915 | 476 | Solar | 05_14_58L2 | 07/31/2015 | 07/31/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2015 | 09/03/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Leominster | Closed
National Grid | NEWBURY | 658155 | 01985 | 0 | Battery Add-On | 05_14_73L2 | 12/03/2024 | 12/05/2024 | 2 | 0 | 2 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 12/03/2024 | 3/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | CHELMSFORD | 175679 | 01824 | 30 | Solar | 05_01_24W3 | 12/18/2014 | 12/18/2014 | 6 | 1 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2015 |  | 2/28/2015 | N | EXP | 51 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 6/1/2015 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WESTFORD | 446153 | 01886 | 7.6 | Solar | 05_01_412L2 | 09/14/2022 | 10/11/2022 | 18 | 16 | 2 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/14/2022 | 3/27/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | BILLERICA | 536354 | 01821 | 5 | Solar | 05_01_55W1 | 06/28/2023 | 06/30/2023 | 3 | 1 | 2 | 07/03/2023 | 07/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 | 06/28/2023 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 491574 | 01606 | 20 | Solar | 05_05_108W60 | 01/11/2023 | 01/13/2023 | 3 | 2 | 1 | 01/17/2023 | 01/17/2023 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/11/2023 | 3/2/2024 | Y | EXP | 365 | 03/21/2023 | 04/22/2023 | 33 | 0 | 33 |  |  | 6/26/2023 | Connected |  | N |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | WEBSTER | 567702 | 01570 | 5 | Solar | 05_12_24W2 | 02/26/2024 | 03/12/2024 | 11 | 6 | 5 | 03/13/2024 | 03/13/2024 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2024 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 169987 | 01543 | 10 | Solar | 05_12_51T2 | 07/09/2018 | 07/24/2018 | 11 | 8 | 3 | 07/25/2018 | 07/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 07/09/2018 | 10/1/2019 | Y | EXP | 432 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N |  | Leominster | Closed
National Grid | BLACKSTONE | 418217 | 01504 | 9.772 | Solar | 05_14_34M1 | 05/11/2022 | 05/12/2022 | 1 | 0 | 1 | 05/13/2022 | 05/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2022 | 05/11/2022 | 8/23/2023 | Y | EXP | 365 | 10/06/2022 | 11/03/2022 | 29 | 0 | 29 |  |  | 11/10/2022 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | LYNN | 176030 | 01904 | 30 | Solar | 05_14_58L2 | 11/05/2014 | 11/05/2014 | 3 | 0 | 3 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 11/05/2014 | 9/30/2015 | Y | EXP | 293 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 3/6/2015 | Connected |  | N |  | Scituate | Closed
National Grid | ESSEX | 664749 | 01929 | 5.7 | Solar | 05_14_73L2 | 01/09/2025 | 02/06/2025 | 13 | 8 | 5 | 02/07/2025 | 02/07/2025 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N |  | North Andover | Closed
National Grid | NEWBURY | 384627 | 01985 | 400 | Solar | 05_14_92L2 | 08/11/2022 | 10/04/2022 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/28/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | CHELMSFORD | 175904 | 01824 | 10 | Solar | 05_01_24W3 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2015 |  | 10/6/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 10/13/2015 | 10/13/2015 | 1/26/2016 | Connected |  | N |  | Brockton-South | Closed - Pending Customer Decision
National Grid | WESTFORD | 458959 | 01886 | 3.8 | Solar | 05_01_412L2 | 11/02/2022 | 11/04/2022 | 3 | 1 | 2 | 11/07/2022 | 11/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  | 4/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 561632 | 01821 | 7.6 | Solar | 05_01_55W1 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 10/13/2023 | 5/4/2025 | Y | EXP | 365 | 10/02/2024 | 10/10/2024 | 9 | 0 | 9 |  |  | 10/24/2024 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | WORCESTER | 503144 | 01606 | 6 | Solar | 05_05_108W60 | 03/28/2023 | 03/30/2023 | 2 | 0 | 2 | 03/31/2023 | 03/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/28/2023 | 5/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | Notice Period - Completion Documents Hold
National Grid | WEBSTER | 588113 | 01570 | 10 | Solar | 05_12_24W2 | 02/12/2024 | 02/22/2024 | 7 | 4 | 3 | 02/23/2024 | 02/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/12/2024 | 4/4/2025 | Y | EXP | 365 | 05/17/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 6/25/2024 | Connected |  | N |  | Marlborough | Notice Period - Conditional Approval Hold
National Grid | RUTLAND | 174123 | 01543 | 128.25 | Solar | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | Notice Period - Conditional Approval Hold
National Grid | BELLINGHAM | 605342 | 02019 | 10 | Solar | 05_14_34M1 | 06/05/2024 | 06/11/2024 | 1 | 0 | 1 | 06/12/2024 | 06/12/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 | 06/05/2024 | 7/19/2025 | Y | EXP | 365 | 10/12/2024 | 10/28/2024 | 17 | 0 | 17 |  |  | 11/14/2024 | Connected |  | N |  | Marlborough | Notice Period - Completion Documents Hold
National Grid | LYNN | 176726 | 01904 | 179 | Solar | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2016 | 03/22/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2016 |  | 2/28/2017 | N | STD | 21 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | HAMILTON | 683559 | 01982 | 23 | Solar | 05_14_73L2 | 04/09/2025 | 04/11/2025 | 0 | 0 | 0 | 04/11/2025 | 04/11/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | NEWBURY | 384623 | 01985 | 400 | Solar | 05_14_92L2 | 08/11/2022 | 10/05/2022 | 38 | 28 | 10 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | WESTFORD | 176013 | 01886 | 17.6 | Solar | 05_01_24W3 | 01/23/2015 | 01/23/2015 | 8 | 6 | 2 | 02/05/2015 | 02/05/2015 | 175 | 0 | 175 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 2/24/2015 | 2/24/2015 |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | CHELMSFORD | 482139 | 01824 | 0 | Battery Add-On | 05_01_412L2 | 12/02/2022 | 12/06/2022 | 2 | 0 | 2 | 12/07/2022 | 12/07/2022 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BILLERICA | 569867 | 01821 | 10 | Solar | 05_01_55W1 | 12/05/2023 | 12/07/2023 | 3 | 2 | 1 | 12/08/2023 | 12/08/2023 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N |  | Marlborough | Notice Period
National Grid | WORCESTER | 508947 | 01606 | 10 | Solar | 05_05_108W60 | 03/20/2023 | 03/21/2023 | 1 | 0 | 1 | 03/22/2023 | 03/22/2023 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N |  | Marlborough | Notice Period
National Grid | WEBSTER | 599697 | 01570 | 10 | Solar | 05_12_24W2 | 04/12/2024 | 04/15/2024 | 0 | 0 | 0 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/12/2024 | 6/14/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 9/12/2024 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 174122 | 01543 | 250 | Solar | 05_12_51T2 | 04/04/2012 | 04/04/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/15/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | Notice Period
National Grid | BLACKSTONE | 641381 | 01504 | 10 | Solar | 05_14_34M1 | 09/18/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 09/18/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | LYNN | 176756 | 01904 | 20.86 | Solar | 05_14_58L2 | 02/23/2016 | 02/23/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 3/1/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/1/2016 | 11/1/2016 | 11/1/2016 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 719098 | 01982 | 11.5 | Battery Add-On | 05_14_73L2 | 09/16/2025 | 09/24/2025 | 5 | 3 | 2 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | 160 Day Study - Completion Documents Hold
National Grid | BYFIELD | 448098 | 01922 | 280 | Solar | 05_14_92L2 | 04/13/2023 | 08/09/2023 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2023 | 09/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | North Andover | Closed - UTC Meter Hold
National Grid | CHELMSFORD | 176730 | 01824 | 6 | Solar | 05_01_24W3 | 04/25/2016 | 04/25/2016 | 2 | 2 | 0 | 04/28/2016 | 04/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2016 | 04/25/2016 | 5/1/2017 | Y | EXP | 355 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | WESTFORD | 517386 | 01886 | 3 | Solar | 05_01_412L2 | 05/17/2023 | 06/12/2023 | 18 | 18 | 0 | 06/13/2023 | 06/13/2023 | 20 | 0 | 20 | 08/09/2023 | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 09/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 9/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | Notice Period
National Grid | BILLERICA | 578149 | 01821 | 2.32 | Solar | 05_01_55W1 | 01/08/2024 | 01/10/2024 | 1 | 1 | 0 | 01/11/2024 | 01/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WORCESTER | 525114 | 01606 | 0 | Solar | 05_05_108W60 | 05/11/2023 | 07/18/2023 | 45 | 42 | 3 | 05/01/2024 | 05/01/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-North | Closed
National Grid | DUDLEY | 599918 | 01570 | 6 | Solar | 05_12_24W2 | 04/09/2024 | 04/16/2024 | 5 | 1 | 4 | 04/17/2024 | 04/17/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 7/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | 160 Day Study - Ordered
National Grid | RUTLAND | 174411 | 01543 | 14 | Solar | 05_12_51T2 | 06/22/2012 | 06/22/2012 | 10 | 0 | 10 | 07/09/2012 | 07/09/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 9/6/2012 | N | EXP | 96 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/11/2012 | Connected |  | N |  | Hopedale-East | 160 Day Study
National Grid | BLACKSTONE | 454032 | 01504 | 21.75 | Solar | 05_14_36J2 | 09/01/2022 | 09/08/2022 | 4 | 4 | 0 | 09/09/2022 | 09/09/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | LYNN | 177190 | 01904 | 323 | Solar | 05_14_58L2 | 08/21/2015 | 08/21/2015 | 4 | 0 | 4 | 08/27/2015 | 08/27/2015 | 0 | 0 | 0 | 11/05/2015 | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 |  | 01/06/2016 | 40 | 12 | 28 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 8/1/2017 | Y | EXP | 539 | 06/15/2017 | 09/06/2017 | 57 | 0 | 57 | 8/30/2017 | 8/30/2017 | 9/7/2017 | Connected |  | N |  | Marlborough | Notice Period
National Grid | WENHAM | 728805 | 01984 | 10.7 | Solar | 05_14_73L2 | 10/23/2025 | 11/03/2025 | 6 | 2 | 4 | 11/04/2025 | 11/04/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2026 | Connected |  | N |  | Marlborough | Notice Period
National Grid | NEWBURY | 470694 | 01950 | 3.8 | Solar | 05_14_92L2 | 11/11/2022 | 11/17/2022 | 4 | 0 | 4 | 11/18/2022 | 11/18/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/11/2022 | 4/25/2024 | Y | EXP | 365 | 04/05/2023 | 04/25/2023 | 21 | 0 | 21 |  |  | 5/2/2023 | Connected |  | N |  | Hopedale-East | 160 Day Study
National Grid | WESTFORD | 176780 | 01886 | 7.6 | Solar | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 |  | 11/10/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 11/25/2015 | 11/25/2015 | 5/25/2016 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | WESTFORD | 516396 | 01886 | 12.76 | Solar | 05_01_412L2 | 08/17/2023 | 09/07/2023 | 15 | 14 | 1 | 09/08/2023 | 09/08/2023 | 24 | 0 | 24 | 11/22/2023 | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/22/2024 |  | 2/19/2025 | N | EXP | 365 | 04/13/2024 | 05/28/2024 | 46 | 0 | 46 |  |  | 5/30/2024 | Connected |  | N |  | Millbury-Grafton | Closed - Internal Review
National Grid | BILLERICA | 584251 | 01821 | 3.8 | Solar | 05_01_55W1 | 02/01/2024 | 02/05/2024 | 2 | 0 | 2 | 02/06/2024 | 02/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | WORCESTER | 563891 | 01606 | 3.8 | Solar | 05_05_108W60 | 10/30/2023 | 12/29/2023 | 42 | 37 | 5 | 01/02/2024 | 01/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | WEBSTER | 602977 | 01570 | 3.8 | Solar | 05_12_24W2 | 04/23/2024 | 04/26/2024 | 3 | 0 | 3 | 04/29/2024 | 04/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | RUTLAND | 175123 | 01543 | 18 | Solar | 05_12_51T2 | 08/16/2012 | 08/16/2012 | 5 | 0 | 5 | 08/24/2012 | 08/24/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/16/2012 | 11/30/2012 | Y | EXP | 12 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 4/2/2013 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | BLACKSTONE | 451338 | 01504 | 67.3 | Solar | 05_14_36J6 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 | 09/20/2022 | 09/20/2022 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | LYNN | 178313 | 01904 | 875 | Solar | 05_14_58L2 | 02/26/2018 | 02/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 04/06/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 02/26/2018 | 4/4/2022 | Y | STD | 1 | 04/20/2021 | 10/12/2021 | 175 | 3 | 172 |  |  | 3/28/2022 | Connected |  | N |  | Chelmsford/Westford | Closed - Construction Hold
National Grid | ESSEX | 457510 | 01929 | 100 | Solar | 05_14_74L1 | 10/10/2022 | 01/04/2023 | 58 | 48 | 10 | 01/05/2023 | 01/05/2023 | 23 | 0 | 23 | 07/10/2025 | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  | 08/28/2025 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 9/5/2025 | 10/10/2022 | 1/15/2027 | Y | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N |  | Beverly | Closed
National Grid | NEWBURY | 610419 | 01950 | 23 | Solar | 05_14_92L2 | 05/13/2024 | 05/20/2024 | 5 | 1 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2024 | Connected |  | N |  | Millbury-Grafton | Closed - Awaiting Payment
National Grid | CHELMSFORD | 176779 | 01824 | 7.6 | Solar | 05_01_24W3 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | 160 Day Study
National Grid | METHUEN | 520273 | 01844 | 14.79 | Solar | 05_01_412L2 | 04/20/2023 | 04/24/2023 | 3 | 2 | 1 | 04/25/2023 | 04/25/2023 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | BILLERICA | 591901 | 01821 | 6 | Solar | 05_01_55W1 | 02/27/2024 | 02/29/2024 | 3 | 1 | 2 | 03/01/2024 | 03/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/27/2024 | 3/20/2025 | Y | EXP | 365 | 05/09/2024 | 06/14/2024 | 37 | 0 | 37 |  |  | 6/25/2024 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WORCESTER | 580770 | 01606 | 7.296 | Solar | 05_05_108W60 | 02/23/2024 | 03/01/2024 | 6 | 2 | 4 | 03/04/2024 | 03/04/2024 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/23/2024 | 6/17/2025 | Y | EXP | 365 | 04/30/2024 | 05/08/2024 | 9 | 0 | 9 |  |  | 11/15/2024 | Connected |  | N |  | Methuen/Haverhill | Closed - Construction Hold
National Grid | WEBSTER | 605616 | 01570 | 3.8 | Solar | 05_12_24W2 | 04/22/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 04/22/2024 | 6/24/2025 | Y | EXP | 365 | 09/07/2024 | 11/01/2024 | 56 | 0 | 56 |  |  | 11/15/2024 | Connected |  | N |  | Marlborough | Notice Period
National Grid | RUTLAND | 175750 | 01543 | 17.2 | Solar | 05_12_51T2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2014 |  | 3/31/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 1/12/2015 | 1/12/2015 | 9/17/2015 | Connected |  | N |  | Marlborough | Notice Period
National Grid | BLACKSTONE | 728333 | 01504 | 23 | Solar | 05_14_36L1 | 10/22/2025 | 10/27/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Marlborough | Notice Period - Completion Documents Hold
National Grid | LYNN | 378906 | 01904 | 11.4 | Solar | 05_14_58L2 | 08/30/2021 | 10/07/2021 | 27 | 26 | 1 | 10/08/2021 | 10/08/2021 | 81 | 58 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  | 5/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2022 | Connected |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 444190 | 01982 | 499 | Solar | 05_14_74L1 | 09/26/2022 | 10/31/2022 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/02/2022 | 12/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 637600 | 01950 | 320 | Solar | 05_14_92L2 | 11/01/2024 | 05/19/2025 | 131 | 121 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2025 | 06/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Billerica | Pending
National Grid | CHELMSFORD | 176980 | 01824 | 6.6 | Solar | 05_01_24W3 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 06/07/2017 | 07/12/2017 | 24 | 0 | 24 | 9/28/2017 | 9/28/2017 | 9/28/2017 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | METHUEN | 521145 | 01844 | 0 | Solar | 05_01_412L2 | 07/19/2023 | 07/20/2023 | 2 | 1 | 1 | 07/21/2023 | 07/21/2023 | 151 | 130 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2024 | Connected |  | N |  | Fall River-North | Closed
National Grid | BILLERICA | 597641 | 01821 | 0 | Solar | 05_01_55W1 | 08/27/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N |  | Fall River-North | Closed - Completion Documents Hold
National Grid | WORCESTER | 585799 | 01606 | 6 | Solar | 05_05_108W60 | 02/07/2024 | 02/14/2024 | 5 | 0 | 5 | 02/15/2024 | 02/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-North | Closed
National Grid | WEBSTER | 632460 | 01570 | 7.6 | Solar | 05_12_24W2 | 08/15/2024 | 08/23/2024 | 1 | 0 | 1 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Fall River-North | Closed
National Grid | RUTLAND | 175937 | 01543 | 750 | Solar | 05_12_51T2 | 01/20/2015 | 01/20/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2015 | 02/25/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Fall River-North | Closed
National Grid | BELLINGHAM | 744809 | 02019 | 5.76 | Solar | 05_14_36L1 | 02/04/2026 | 02/05/2026 | 1 | 0 | 1 | 02/06/2026 | 02/06/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Fall River-North | Closed - Completion Documents Hold
National Grid | LYNN | 410741 | 01904 | 6 | Solar | 05_14_58L2 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/21/2022 | 2/15/2024 | Y | EXP | 365 | 01/28/2023 | 02/14/2023 | 18 | 0 | 18 |  |  | 3/10/2023 | Connected |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | GLOUCESTER | 660642 | 01930 | 5.76 | Solar | 05_14_74L1 | 12/13/2024 | 01/30/2025 | 27 | 25 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 12/13/2024 | 4/10/2026 | Y | EXP | 365 | 05/07/2025 | 12/22/2025 | 230 | 0 | 230 |  |  |  | Completion Documents |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 640240 | 01950 | 5.76 | Solar | 05_14_92L2 | 09/13/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/13/2024 | 11/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | CHELMSFORD | 193768 | 01824 | 10 | Solar | 05_01_24W3 | 08/17/2018 | 10/12/2018 | 7 | 7 | 0 | 10/15/2018 | 10/15/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Tewksbury | Closed
National Grid | METHUEN | 545472 | 01844 | 5.8 | Solar | 05_01_412L2 | 08/08/2023 | 08/28/2023 | 15 | 14 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/08/2023 | 10/11/2024 | Y | EXP | 365 | 01/16/2024 | 02/08/2024 | 24 | 0 | 24 |  |  | 2/22/2024 | Connected |  | N |  | Tewksbury | Closed - Awaiting Payment
National Grid | BILLERICA | 608010 | 01821 | 11.7 | Solar | 05_01_55W1 | 05/02/2024 | 05/13/2024 | 3 | 1 | 2 | 05/14/2024 | 05/14/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Tewksbury | Closed - Completion Documents Hold
National Grid | WORCESTER | 587149 | 01606 | 7.6 | Solar | 05_05_108W60 | 03/26/2024 | 04/17/2024 | 15 | 13 | 2 | 04/18/2024 | 04/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 03/26/2024 | 5/3/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 10/3/2024 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | WEBSTER | 634313 | 01570 | 8.125 | Solar | 05_12_24W2 | 08/21/2024 | 09/17/2024 | 10 | 6 | 4 | 09/18/2024 | 09/18/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 | 08/21/2024 | 10/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | RUTLAND | 176160 | 01543 | 17.4 | Solar | 05_12_51T2 | 02/05/2015 | 02/05/2015 | 4 | 1 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 6/30/2015 | N | EXP | 137 |  |  | 0 | 0 | 0 | 3/6/2015 | 3/6/2015 | 9/25/2015 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | BLACKSTONE | 749885 | 01504 | 150 | Solar | 05_14_36L1 | 02/13/2026 |  | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N |  | Ayer-Clinton | Extended Group Study Opt-In
National Grid | LYNN | 576775 | 01904 | 23 | Solar | 05_14_58L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 03/05/2024 | 03/05/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N |  | Leominster | Group Window
National Grid | BEVERLY | 733696 | 01915 | 3.8 | Solar | 05_14_74L1 | 11/13/2025 | 11/14/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Leominster | Group Window
National Grid | NEWBURY | 649338 | 01950 | 7.6 | Solar | 05_14_92L2 | 11/04/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 1/2/2026 | Y | EXP | 365 | 03/04/2025 | 04/18/2025 | 46 | 0 | 46 |  |  | 5/2/2025 | Connected |  | N |  | Leominster | Group Window
National Grid | CHELMSFORD | 196491 | 01824 | 5 | Solar | 05_01_24W3 | 09/20/2018 | 10/24/2018 | 19 | 18 | 1 | 10/25/2018 | 10/25/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  | 10/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | Connected |  | N |  | Leominster | Group Window
National Grid | METHUEN | 547164 | 01844 | 3.8 | Solar | 05_01_412L2 | 09/13/2023 | 09/20/2023 | 5 | 2 | 3 | 09/21/2023 | 09/21/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 616463 | 01821 | 5.76 | Solar | 05_01_55W1 | 06/07/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 587903 | 01606 | 7.83 | Solar | 05_05_108W60 | 02/16/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 666059 | 01570 | 10 | Solar | 05_12_24W2 | 01/15/2025 | 02/24/2025 | 5 | 1 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 | 01/15/2025 | 5/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | RUTLAND | 177044 | 01543 | 630 | Solar | 05_12_51T2 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BELLINGHAM | 175095 | 02019 | 12 | Solar | 05_14_36L1 | 10/23/2012 | 10/23/2012 | 2 | 0 | 2 | 11/19/2012 | 11/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2013 |  | 1/31/2013 | N | EXP | 6 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 3/14/2013 | Connected |  | N |  | Methuen/Haverhill | Closed - Construction Hold
National Grid | LYNN | 579860 | 01904 | 7.875 | Solar | 05_14_58L2 | 01/18/2024 | 02/01/2024 | 11 | 9 | 2 | 02/02/2024 | 02/02/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/18/2024 | 2/26/2025 | Y | EXP | 365 | 03/20/2024 | 04/09/2024 | 21 | 0 | 21 |  |  | 4/12/2024 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | HAMILTON | 734937 | 01982 | 11.5 | Solar | 05_14_74L1 | 11/19/2025 | 12/01/2025 | 12 | 8 | 4 | 01/07/2026 | 01/07/2026 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Methuen/Haverhill | Closed
National Grid | NEWBURY | 652994 | 01950 | 7.6 | Solar | 05_14_92L2 | 11/08/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 | 11/08/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | CHELMSFORD | 246025 | 01824 | 6 | Solar | 05_01_24W3 | 08/05/2019 | 08/20/2019 | 10 | 4 | 6 | 08/21/2019 | 08/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | METHUEN | 549203 | 01844 | 12 | Solar | 05_01_412L2 | 09/05/2023 | 11/14/2023 | 49 | 46 | 3 | 11/15/2023 | 11/15/2023 | 68 | 36 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Methuen/Haverhill | Closed
National Grid | BILLERICA | 634556 | 01821 | 8.775 | Solar | 05_01_55W1 | 08/22/2024 | 09/03/2024 | 4 | 1 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | WORCESTER | 599414 | 01606 | 7.6 | Solar | 05_05_108W60 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 38 | 25 | 13 | 06/11/2024 | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  | 09/11/2024 | 64 | 0 | 64 |  |  | 0 | 0 | 0 | 8/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed - Construction Hold
National Grid | WEBSTER | 701422 | 01570 | 7.6 | Solar | 05_12_24W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N |  | Methuen/Haverhill | Closed - Internal Review
National Grid | RUTLAND | 177335 | 01543 | 186.5 | Solar | 05_12_51T2 | 08/31/2016 | 08/31/2016 | 2 | 2 | 0 | 09/02/2016 | 09/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 9/5/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | BELLINGHAM | 218135 | 02019 | 18.85 | Solar | 05_14_36L1 | 04/09/2019 | 04/12/2019 | 3 | 3 | 0 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 8/20/2019 | N | EXP | 125 |  |  | 0 | 0 | 0 |  |  | 8/15/2019 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | LYNN | 636327 | 01904 | 5 | Solar | 05_14_58L2 | 08/29/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | HAMILTON | 738754 | 01982 | 7.6 | Solar | 05_14_74L1 | 12/08/2025 | 12/22/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Cape Ann | Closed - Study Hold
National Grid | NEWBURY | 662574 | 01950 | 7.6 | Solar | 05_14_92L2 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Cape Ann | Closed - Sent to Customer
National Grid | WESTFORD | 283927 | 01886 | 10 | Solar | 05_01_24W3 | 04/28/2020 | 04/29/2020 | 1 | 1 | 0 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/28/2020 | 4/28/2021 | Y | EXP | 365 | 11/07/2020 | 01/06/2021 | 60 | 0 | 60 |  |  | 1/8/2021 | Connected |  | N |  | Cape Ann | Closed - Study Hold
National Grid | METHUEN | 551576 | 01844 | 4.64 | Solar | 05_01_412L2 | 09/19/2023 | 09/22/2023 | 3 | 0 | 3 | 09/25/2023 | 09/25/2023 | 20 | 0 | 20 | 11/13/2023 | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 |  | 03/15/2024 | 58 | 41 | 17 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/18/2025 | N | EXP | 365 | 04/13/2024 | 05/22/2024 | 40 | 0 | 40 |  |  | 6/10/2024 | Connected |  | N |  | Cape Ann | Closed - Conditional Approval Hold
National Grid | BILLERICA | 637398 | 01821 | 5.8 | Solar | 05_01_55W1 | 09/03/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N |  | Cape Ann | Closed
National Grid | WORCESTER | 600470 | 01606 | 11.02 | Solar | 05_05_108W60 | 05/13/2024 | 05/14/2024 | 1 | 0 | 1 | 05/15/2024 | 05/15/2024 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N |  | Cape Ann | Closed
National Grid | WEBSTER | 174925 | 01570 | 1000 | Solar | 05_12_25W1 | 02/25/2013 | 02/25/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/09/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Cape Ann | Closed - Study Hold
National Grid | RUTLAND | 177600 | 01543 | 28.75 | Solar | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/15/2017 | 09/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2017 |  | 7/24/2018 | N | EXP | 312 |  |  | 0 | 0 | 0 | 3/16/2018 | 3/16/2018 | 4/25/2018 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | BELLINGHAM | 258094 | 02019 | 3.8 | Solar | 05_14_36L1 | 10/10/2019 | 10/21/2019 | 5 | 0 | 5 | 10/22/2019 | 10/22/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 10/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Millbury-Grafton | Closed - Completion Documents Hold
National Grid | SAUGUS | 695649 | 01906 | 5.76 | Solar | 05_14_58L2 | 06/09/2025 | 06/12/2025 | 3 | 0 | 3 | 06/13/2025 | 06/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | ESSEX | 744891 | 01929 | 19.38 | Solar | 05_14_74L1 | 01/13/2026 | 01/21/2026 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 668829 | 01950 | 3.9 | Solar | 05_14_92L2 | 02/06/2025 | 02/28/2025 | 10 | 6 | 4 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 368621 | 01886 | 6 | Solar | 05_01_24W3 | 08/19/2021 | 12/31/2021 | 4 | 2 | 2 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed - Completion Documents Hold
National Grid | HAVERHILL | 613016 | 01832 | 6 | Solar | 05_01_412L2 | 05/23/2024 | 06/11/2024 | 9 | 5 | 4 | 06/12/2024 | 06/12/2024 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 05/23/2024 | 1/26/2026 | Y | EXP | 365 | 09/04/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 3/26/2025 | Connected |  | N |  | Cape Ann | Closed - Study Hold
National Grid | BILLERICA | 644740 | 01821 | 9.9 | Solar | 05_01_55W1 | 10/03/2024 | 11/14/2024 | 12 | 9 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/03/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y |  | Brockton-North | 160 Day Study
National Grid | WORCESTER | 613326 | 01606 | 11.5 | Solar | 05_05_108W60 | 05/28/2024 | 06/11/2024 | 11 | 9 | 2 | 06/12/2024 | 06/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WEBSTER | 175253 | 01570 | 8.82 | Solar | 05_12_25W1 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 9/4/2015 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | RUTLAND | 177599 | 01543 | 28.75 | Solar | 05_12_51T2 | 07/19/2017 | 07/19/2017 | 40 | 31 | 9 | 09/14/2017 | 09/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 7/24/2018 | N | EXP | 313 |  |  | 0 | 0 | 0 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | BELLINGHAM | 432857 | 02019 | 0 | Solar | 05_14_36L1 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 7/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2023 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | SAUGUS | 710905 | 01906 | 4.93 | Solar | 05_14_58L2 | 08/10/2025 | 09/17/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | ESSEX | 753410 | 01929 | 20 | Solar | 05_14_74L1 | 03/03/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N |  | Brockton-North | 160 Day Study
National Grid | NEWBURY | 671980 | 01950 | 10 | Solar | 05_14_92L2 | 02/13/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 40 | 23 | 17 | 06/05/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 7/1/2025 | 02/13/2025 | 7/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | CHELMSFORD | 443258 | 01824 | 7.6 | Solar | 05_01_24W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/19/2022 | 2/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | HAVERHILL | 613403 | 01832 | 6.67 | Solar | 05_01_412L2 | 05/28/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 7/1/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-North | 160 Day Study
National Grid | BILLERICA | 655165 | 01821 | 5.76 | Solar | 05_01_55W1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 44 | 19 | 25 | 03/28/2025 | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  | 06/12/2025 | 53 | 0 | 53 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/8/2026 | N | EXP | 365 | 11/11/2025 | 12/22/2025 | 42 | 0 | 42 |  |  | 12/4/2025 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WORCESTER | 620631 | 01606 | 10 | Solar | 05_05_108W60 | 06/26/2024 | 07/11/2024 | 1 | 0 | 1 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N |  | Scituate | Closed
National Grid | WEBSTER | 176097 | 01570 | 1296 | Solar | 05_12_25W1 | 04/06/2015 | 04/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2015 | 05/11/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 | 04/06/2015 | 9/29/2017 | Y | STD | 541 |  |  | 0 | 0 | 0 | 9/7/2017 | 9/7/2017 | 9/8/2017 | Connected |  | N |  | Scituate | Closed
National Grid | RUTLAND | 178038 | 01543 | 17.6 | Solar | 05_12_51T2 | 10/27/2017 | 10/27/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 3/30/2019 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Scituate | Closed
National Grid | BELLINGHAM | 438236 | 02019 | 15.2 | Solar | 05_14_36L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2022 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | SAUGUS | 613783 | 01906 | 0 | Battery Add-On | 05_14_58L3 | 05/28/2024 | 06/20/2024 | 16 | 13 | 3 | 06/21/2024 | 06/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Terminated |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | ESSEX | 174576 | 01929 | 1000 | Solar | 05_14_74L1 | 04/01/2011 | 04/01/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 06/22/2011 | 08/20/2012 | 289 | 0 | 289 | 05/04/2011 | 06/15/2011 | 29 | 0 | 29 |  | 08/20/2012 | 289 | 0 | 289 |  |  | 0 | 0 | 0 | 10/11/2012 | 04/01/2011 | 10/31/2012 | Y | STD | 2 | 05/14/2013 | 09/16/2013 | 85 | 0 | 85 | 7/9/2013 | 7/9/2013 | 7/25/2013 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | NEWBURY | 680282 | 01950 | 10 | Solar | 05_14_92L2 | 03/25/2025 | 04/11/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/23/2025 | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  | 09/08/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 | 9/10/2025 | 03/25/2025 | 9/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WESTFORD | 476456 | 01886 | 6 | Solar | 05_01_24W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | METHUEN | 636521 | 01844 | 3.8 | Solar | 05_01_412L2 | 08/29/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N |  | Brockton-South | Closed
National Grid | BILLERICA | 660326 | 01821 | 7.6 | Solar | 05_01_55W1 | 12/12/2024 | 01/07/2025 | 8 | 6 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 637783 | 01606 | 10 | Solar | 05_05_108W60 | 09/04/2024 | 09/20/2024 | 3 | 0 | 3 | 09/23/2024 | 09/23/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 176438 | 01570 | 10 | Solar | 05_12_25W1 | 03/16/2016 | 03/16/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/22/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 7/29/2016 | 7/29/2016 | 7/29/2016 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | RUTLAND | 205162 | 01543 | 0 | Solar | 05_12_51T2 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 7/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BLACKSTONE | 463499 | 01504 | 15.2 | Solar | 05_14_36L1 | 09/27/2022 | 10/04/2022 | 6 | 5 | 1 | 10/05/2022 | 10/05/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 |  | 1/10/2024 | N | EXP | 43 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 698097 | 01906 | 9.5 | Solar | 05_14_58L3 | 06/12/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 72 | 47 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 175052 | 01982 | 2000 | Solar | 05_14_74L1 | 07/20/2011 | 07/20/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2011 | 09/13/2011 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2012 | 07/20/2011 | 6/30/2014 | Y | STD | 74 | 04/01/2014 | 06/18/2014 | 53 | 0 | 53 | 6/25/2014 | 6/25/2014 | 6/23/2014 | Connected |  | N |  | Brockton-South | Closed - Awaiting Payment
National Grid | NEWBURY | 706418 | 01950 | 23 | Solar | 05_14_92L2 | 07/29/2025 | 08/04/2025 | 4 | 0 | 4 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N |  | Brockton-South | Closed
National Grid | WESTFORD | 502075 | 01886 | 7.68 | Solar | 05_01_24W3 | 03/06/2023 | 03/08/2023 | 2 | 1 | 1 | 03/09/2023 | 03/09/2023 | 25 | 0 | 25 | 05/12/2023 | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 6/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | 160 Day Study
National Grid | METHUEN | 636496 | 01844 | 10 | Solar | 05_01_412L2 | 08/29/2024 | 10/28/2024 | 28 | 25 | 3 | 10/29/2024 | 10/29/2024 | 175 | 160 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | Scoping Meeting
National Grid | BILLERICA | 669686 | 01821 | 7.6 | Solar | 05_01_55W1 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 140 | 123 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Construction Hold
National Grid | WORCESTER | 640399 | 01606 | 0 | Battery Add-On | 05_05_108W60 | 09/16/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 171 | 136 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 176712 | 01570 | 8.75 | Solar | 05_12_25W1 | 01/07/2016 | 01/07/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 1/13/2017 | N | EXP | 36 |  |  | 0 | 0 | 0 | 2/22/2016 | 2/22/2016 | 2/25/2016 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | RUTLAND | 238751 | 01543 | 10 | Solar | 05_12_51T2 | 06/19/2019 | 06/20/2019 | 0 | 0 | 0 | 06/21/2019 | 06/21/2019 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  | 9/6/2019 | N | EXP | 67 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N |  | Billerica | Closed
National Grid | BELLINGHAM | 555470 | 02019 | 7.54 | Solar | 05_14_36L1 | 09/14/2023 | 09/18/2023 | 3 | 1 | 2 | 09/19/2023 | 09/19/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 10/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N |  | Cape Ann | Closed - Design Hold
National Grid | SAUGUS | 710780 | 01906 | 67.3 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Attleboro | Time Frame Suspension
National Grid | ESSEX | 176057 | 01929 | 996 | Solar | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 | 03/27/2015 | 8/1/2015 | Y | STD | 132 | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 | 11/16/2017 | 11/16/2017 | 11/16/2017 | Connected |  | N |  | Dracut | Closed
National Grid | NEWBURY | 710015 | 01950 | 15.2 | Solar | 05_14_92L2 | 08/06/2025 | 08/12/2025 | 3 | 1 | 2 | 08/13/2025 | 08/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | WESTFORD | 576736 | 01886 | 6 | Solar | 05_01_24W3 | 01/03/2024 | 01/08/2024 | 3 | 1 | 2 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/03/2024 | 3/4/2025 | Y | EXP | 365 | 04/24/2024 | 09/05/2024 | 135 | 0 | 135 |  |  | 9/10/2024 | Connected |  | N |  | Methuen/Haverhill | Closed - Internal Review
National Grid | HAVERHILL | 650945 | 01832 | 3.8 | Solar | 05_01_412L2 | 11/12/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/12/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | BILLERICA | 671566 | 01821 | 10 | Solar | 05_01_55W1 | 02/11/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/11/2025 | 5/25/2026 | Y | EXP | 365 | 08/28/2025 | 12/01/2025 | 96 | 0 | 96 |  |  | 1/16/2026 | Connected |  | N |  | Dracut | Closed
National Grid | WORCESTER | 643794 | 01606 | 7.6 | Solar | 05_05_108W60 | 10/04/2024 | 10/18/2024 | 4 | 4 | 0 | 10/21/2024 | 10/21/2024 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WEBSTER | 176708 | 01570 | 10 | Solar | 05_12_25W1 | 10/27/2015 | 10/27/2015 | 1 | 1 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 10/27/2015 | 11/3/2016 | Y | EXP | 344 | 09/21/2016 | 10/11/2016 | 13 | 0 | 13 | 11/25/2015 | 11/25/2015 | 10/26/2016 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | RUTLAND | 242810 | 01543 | 7.6 | Solar | 05_12_51T2 | 07/16/2019 | 07/17/2019 | 0 | 0 | 0 | 07/18/2019 | 07/18/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2019 |  | 7/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N |  | Billerica | Closed
National Grid | BLACKSTONE | 578652 | 01504 | 11.4 | Solar | 05_14_36L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/27/2023 | 2/27/2025 | Y | EXP | 365 | 03/16/2024 | 04/10/2024 | 26 | 0 | 26 |  |  | 4/16/2024 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 710796 | 01906 | 200 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | ESSEX | 176056 | 01929 | 980 | Solar | 05_14_74L1 | 03/27/2015 | 03/27/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  | 08/22/2017 | 01/31/2018 | 104 | 0 | 104 |  |  |  | Withdrawn |  | N |  | Worcester North/South | Closed
National Grid | NEWBURY | 177716 | 01950 | 112 | Solar | 05_14_92L3 | 07/26/2017 | 07/26/2017 | 6 | 6 | 0 | 08/04/2017 | 08/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WESTFORD | 591330 | 01886 | 3.8 | Solar | 05_01_24W3 | 02/26/2024 | 03/05/2024 | 6 | 0 | 6 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/26/2024 | 4/6/2025 | Y | EXP | 365 | 07/16/2024 | 09/11/2024 | 58 | 0 | 58 |  |  | 9/20/2024 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | HAVERHILL | 651603 | 01832 | 10 | Solar | 05_01_412L2 | 11/12/2024 | 01/28/2025 | 5 | 0 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 11/12/2024 | 3/17/2026 | Y | EXP | 365 | 06/12/2025 | 12/01/2025 | 173 | 0 | 173 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | BILLERICA | 671268 | 01821 | 5.76 | Solar | 05_01_55W1 | 02/11/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WORCESTER | 644592 | 01606 | 10 | Solar | 05_05_108W60 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/18/2025 | Y | EXP | 365 | 08/22/2025 | 09/18/2025 | 28 | 0 | 28 |  |  | 10/18/2025 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | WEBSTER | 176752 | 01570 | 34.2 | Solar | 05_12_25W1 | 01/12/2016 | 01/12/2016 | 8 | 8 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/12/2016 | 1/18/2017 | Y | EXP | 344 | 05/27/2016 | 06/03/2016 | 4 | 0 | 4 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | RUTLAND | 260576 | 01543 | 13.6 | Solar | 05_12_51T2 | 10/17/2019 | 10/24/2019 | 5 | 3 | 2 | 10/25/2019 | 10/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2020 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | BELLINGHAM | 628681 | 02019 | 19 | Solar | 05_14_36L1 | 07/30/2024 | 08/01/2024 | 2 | 0 | 2 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | SAUGUS | 710791 | 01906 | 240 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | HAMILTON | 176913 | 01936 | 7.6 | Solar | 05_14_74L1 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | Time Frame Suspension
National Grid | NEWBURY | 644567 | 01950 | 10 | Solar | 05_14_92L3 | 10/02/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WESTFORD | 624975 | 01886 | 3.8 | Solar | 05_01_24W3 | 07/15/2024 | 07/22/2024 | 1 | 0 | 1 | 07/23/2024 | 07/23/2024 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | METHUEN | 653708 | 01844 | 4950 | Other | 05_01_412L2 | 04/10/2025 |  | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Beverly | Closed
National Grid | BILLERICA | 679462 | 01821 | 11.52 | Solar | 05_01_55W1 | 03/25/2025 | 09/15/2025 | 29 | 25 | 4 | 09/16/2025 | 09/16/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | WORCESTER | 651065 | 01606 | 6.175 | Solar | 05_05_108W60 | 10/31/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/31/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N |  | Tewksbury | Closed
National Grid | WEBSTER | 176963 | 01570 | 15.2 | Solar | 05_12_25W1 | 07/18/2016 | 07/18/2016 | 0 | 0 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/18/2016 | 10/12/2018 | Y | EXP | 88 | 01/18/2018 | 03/05/2018 | 30 | 0 | 30 |  |  | 9/26/2018 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | RUTLAND | 283128 | 01543 | 8.7 | Solar | 05_12_51T2 | 03/10/2020 | 03/11/2020 | 0 | 0 | 0 | 03/12/2020 | 03/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 3/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BELLINGHAM | 629011 | 02019 | 23 | Solar | 05_14_36L1 | 07/31/2024 | 08/05/2024 | 6 | 5 | 1 | 09/27/2024 | 09/27/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/31/2024 | 11/21/2025 | Y | EXP | 365 | 01/11/2025 | 02/24/2025 | 45 | 0 | 45 |  |  | 3/5/2025 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | SAUGUS | 710790 | 01906 | 240 | Solar | 05_14_58L3 | 09/19/2025 | 01/06/2026 | 72 | 64 | 8 | 01/07/2026 | 01/07/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | WENHAM | 176972 | 01984 | 7.6 | Solar | 05_14_74L1 | 10/05/2016 | 10/05/2016 | 2 | 2 | 0 | 10/10/2016 | 10/10/2016 | 91 | 0 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/11/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Brockton-South | Common System Modifications Design In Progress - Design Hold
National Grid | NEWBURY | 646579 | 01950 | 10 | Solar | 05_14_92L3 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Closed - Pending Customer Decision
National Grid | WESTFORD | 637116 | 01886 | 5.76 | Solar | 05_01_24W3 | 09/02/2024 | 09/12/2024 | 2 | 0 | 2 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | METHUEN | 653524 | 01844 | 5.76 | Solar | 05_01_412L2 | 11/15/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 3/21/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 10/2/2025 | Connected |  | N |  | Chelmsford/Westford | Closed - Construction Hold
National Grid | BILLERICA | 683396 | 01821 | 20 | Solar | 05_01_55W1 | 04/07/2025 | 04/11/2025 | 4 | 0 | 4 | 04/14/2025 | 04/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | WORCESTER | 660346 | 01606 | 10 | Solar | 05_05_108W60 | 12/12/2024 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WEBSTER | 185047 | 01570 | 13.6 | Solar | 05_12_25W1 | 07/09/2018 | 07/18/2018 | 7 | 3 | 4 | 07/19/2018 | 07/19/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  | 7/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | RUTLAND | 293270 | 01543 | 0 | Battery Add-On | 05_12_51T2 | 05/27/2020 | 06/08/2020 | 7 | 7 | 0 | 06/09/2020 | 06/09/2020 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 05/27/2020 | 4/9/2022 | Y | EXP | 365 | 03/10/2021 | 04/05/2021 | 26 | 0 | 26 |  |  |  | Withdrawn |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | BLACKSTONE | 656931 | 01504 | 0 | Battery Add-On | 05_14_36L1 | 11/26/2024 | 12/23/2024 | 6 | 1 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N |  | North Andover | Closed
National Grid | SAUGUS | 725182 | 01906 | 15.2 | Solar | 05_14_58L3 | 10/09/2025 | 10/20/2025 | 5 | 0 | 5 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Chelmsford/Westford | Closed
National Grid | ESSEX | 177164 | 01929 | 7.6 | Solar | 05_14_74L1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 88 | 0 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Beverly | Closed
National Grid | NEWBURY | 648246 | 01950 | 10 | Solar | 05_14_92L3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/18/2024 | 1/1/2026 | Y | EXP | 365 | 03/15/2025 | 03/24/2025 | 10 | 0 | 10 |  |  | 3/27/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | WESTFORD | 638002 | 01886 | 3.8 | Solar | 05_01_24W3 | 09/05/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | METHUEN | 657794 | 01844 | 20 | Solar | 05_01_412L2 | 12/02/2024 | 12/06/2024 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Bridgewater | Notice Period
National Grid | BILLERICA | 684897 | 01821 | 5.76 | Solar | 05_01_55W1 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 52 | 44 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | North Andover | Closed
National Grid | WORCESTER | 661870 | 01606 | 5.76 | Solar | 05_05_108W60 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | WEBSTER | 219604 | 01570 | 7.6 | Solar | 05_12_25W1 | 04/12/2019 | 10/02/2019 | 119 | 114 | 5 | 10/03/2019 | 10/03/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 9/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | RUTLAND | 293961 | 01543 | 15.08 | Solar | 05_12_51T2 | 05/29/2020 | 06/04/2020 | 3 | 0 | 3 | 06/05/2020 | 06/05/2020 | 92 | 82 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2021 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | BLACKSTONE | 659827 | 01504 | 3.8 | Solar | 05_14_36L1 | 12/11/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Common System Modifications Design In Progress
National Grid | SAUGUS | 729434 | 01906 | 5.76 | Solar | 05_14_58L3 | 10/27/2025 | 10/29/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | WENHAM | 177621 | 01984 | 15.2 | Solar | 05_14_74L1 | 11/09/2017 | 11/09/2017 | 11 | 10 | 1 | 11/29/2017 | 11/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 11/15/2018 | N | EXP | 52 |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | NEWBURY | 670042 | 01950 | 10 | Solar | 05_14_92L3 | 02/11/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N |  | MPL-Northwest | Closed
National Grid | WESTFORD | 639629 | 01886 | 10 | Solar | 05_01_24W3 | 09/12/2024 | 09/20/2024 | 5 | 2 | 3 | 09/23/2024 | 09/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N |  | Chelmsford/Westford | Closed - Construction Hold
National Grid | METHUEN | 667026 | 01844 | 5.76 | Solar | 05_01_412L2 | 01/21/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2025 | Connected |  | N |  | Beverly | Closed
National Grid | BILLERICA | 685863 | 01821 | 0 | Solar | 05_01_55W1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WORCESTER | 674897 | 01606 | 7.6 | Solar | 05_05_108W60 | 03/13/2025 | 03/18/2025 | 3 | 0 | 3 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Completion Documents Hold
National Grid | WEBSTER | 234682 | 01570 | 3.8 | Solar | 05_12_25W1 | 07/24/2019 | 08/30/2019 | 27 | 26 | 1 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 |  | 12/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | RUTLAND | 301864 | 01543 | 7.6 | Solar | 05_12_51T2 | 08/14/2020 | 08/18/2020 | 1 | 0 | 1 | 08/19/2020 | 08/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 | 08/14/2020 | 2/5/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2021 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | BLACKSTONE | 665116 | 01504 | 10 | Solar | 05_14_36L1 | 01/10/2025 | 01/14/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | SAUGUS | 174768 | 01906 | 75 | Solar | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | 139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N |  | Brockton-North | 160 Day Study
National Grid | HAMILTON | 177732 | 01982 | 8.32 | Solar | 05_14_74L1 | 03/22/2017 | 03/22/2017 | 27 | 27 | 0 | 05/01/2017 | 05/01/2017 | 126 | 0 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/27/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed
National Grid | NEWBURY | 197046 | 01950 | 2500 | Natural Gas | 05_14_92L4 | 10/04/2019 | 11/07/2019 | 23 | 19 | 4 |  |  | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 10/04/2019 | 4/14/2026 | Y | STD | 855 | 10/28/2020 | 09/23/2021 | 134 | 0 | 134 |  |  |  | Completion Documents |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WESTFORD | 641869 | 01886 | 7.8 | Solar | 05_01_24W3 | 09/20/2024 | 10/03/2024 | 3 | 0 | 3 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 | 01/21/2025 | 06/10/2025 | 141 | 0 | 141 |  |  | 6/13/2025 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | METHUEN | 674700 | 01844 | 10 | Solar | 05_01_412L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | BILLERICA | 694884 | 01821 | 11.4 | Solar | 05_01_55W1 | 06/02/2025 | 06/13/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 06/02/2025 | 9/4/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/24/2025 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WORCESTER | 461538 | 01606 | 490 | Solar | 05_05_115W42 | 02/08/2023 | 06/22/2023 | 92 | 81 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 01/08/2024 | 136 | 115 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 02/08/2023 | 11/28/2026 | Y | STD | 329 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | WEBSTER | 276489 | 01570 | 400 | Solar | 05_12_25W1 | 04/09/2020 | 04/22/2020 | 7 | 2 | 5 |  |  | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2020 | 04/09/2020 | 5/13/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | RUTLAND | 330933 | 01543 | 5 | Solar | 05_12_51T2 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/13/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2021 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 667873 | 02724 | 10.15 | Solar | 05_14_36L1 | 01/26/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 174767 | 01906 | 100 | Solar | 05_14_58L3 | 08/24/2012 | 08/24/2012 | 8 | 0 | 8 | 09/06/2012 | 09/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 12/14/2012 | N | EXP | 139 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/10/2013 | Connected |  | N |  | Ayer-Clinton | Closed
National Grid | ESSEX | 178372 | 01929 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N |  | Dracut | Closed
National Grid | NEWBURY | 174891 | 01950 | 990 | Solar | 05_14_92L4 | 08/14/2013 | 08/14/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/22/2013 | 11/22/2013 | 22 | 0 | 22 | 08/23/2013 | 10/01/2013 | 26 | 0 | 26 |  | 11/22/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/2/2013 |  | 12/31/2013 | N | STD | 29 |  |  | 0 | 0 | 0 | 12/28/2013 | 12/28/2013 | 12/31/2013 | Connected |  | N |  | Attleboro | Time Frame Suspension
National Grid | WESTFORD | 657941 | 01886 | 7.6 | Solar | 05_01_24W3 | 12/02/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 12/02/2024 | 2/24/2026 | Y | EXP | 365 | 07/03/2025 | 07/15/2025 | 13 | 0 | 13 |  |  | 7/28/2025 | Connected |  | N |  | Chelmsford/Westford | Closed - Awaiting Payment
National Grid | METHUEN | 681581 | 01844 | 15.76 | Solar | 05_01_412L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-Northwest | Closed
National Grid | BILLERICA | 702598 | 01821 | 11.5 | Solar | 05_01_55W1 | 07/14/2025 | 07/21/2025 | 5 | 0 | 5 | 07/22/2025 | 07/22/2025 | 64 | 55 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Cape Ann | Closed - Study Hold
National Grid | WORCESTER | 666238 | 01606 | 120 | Solar | 05_05_115W42 | 02/03/2025 | 03/11/2025 | 26 | 16 | 10 | 03/12/2025 | 03/12/2025 | 25 | 0 | 25 | 05/20/2025 | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  | 05/29/2025 | 7 | 4 | 3 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/12/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | North Andover | Closed
National Grid | WEBSTER | 374165 | 01570 | 9.98 | Solar | 05_12_25W1 | 11/05/2021 |  | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed
National Grid | RUTLAND | 330460 | 01543 | 9.8 | Solar | 05_12_51T2 | 01/21/2021 | 12/07/2021 | 1 | 0 | 1 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/21/2021 | 4/9/2023 | Y | EXP | 365 | 07/31/2021 | 08/26/2021 | 26 | 1 | 25 |  |  | 7/20/2022 | Connected |  | N |  | Methuen/Haverhill | Closed
National Grid | FALL RIVER | 669838 | 02724 | 6.84 | Solar | 05_14_36L1 | 02/04/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | SAUGUS | 174796 | 01906 | 13 | Solar | 05_14_58L3 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2012 |  | 11/30/2012 | N | EXP | 1 |  |  | 0 | 0 | 0 | 2/7/2013 | 2/7/2013 | 2/21/2013 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | HAMILTON | 178371 | 01982 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 2/15/2019 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  | 5/24/2019 | Connected |  | N |  | Dracut | Closed
National Grid | NEWBURY | 201405 | 01950 | 15.2 | Solar | 05_14_92L4 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/16/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Common System Modifications Design In Progress - In Progress
National Grid | WESTFORD | 659022 | 01886 | 9.88 | Solar | 05_01_24W3 | 12/06/2024 | 01/08/2025 | 13 | 8 | 5 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N |  | Brockton-North | 160 Day Study - Completion Documents Hold
National Grid | METHUEN | 690834 | 01844 | 15.2 | Solar | 05_01_412L2 | 05/21/2025 | 05/27/2025 | 3 | 0 | 3 | 05/28/2025 | 05/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Beverly | Closed
National Grid | BILLERICA | 707581 | 01821 | 10 | Solar | 05_01_55W1 | 07/25/2025 | 09/03/2025 | 3 | 0 | 3 | 09/04/2025 | 09/04/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | WORCESTER | 728667 | 01606 | 5.76 | Solar | 05_05_115W42 | 10/27/2025 | 10/28/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WEBSTER | 410526 | 01570 | 0 | Solar | 05_12_25W1 | 02/04/2022 | 02/08/2022 | 2 | 1 | 1 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | Closed
National Grid | RUTLAND | 333234 | 01543 | 7.6 | Solar | 05_12_51T2 | 01/27/2021 | 12/08/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | Closed
National Grid | FALL RIVER | 710902 | 02724 | 15.2 | Solar | 05_14_36L1 | 08/10/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | MELROSE | 177122 | 02176 | 0 | Solar | 05_14_58L3 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 02/03/2017 | 70 | 58 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Scoping Meeting
National Grid | HAMILTON | 178370 | 01982 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 44 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 11/26/2018 | N | EXP | 3 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N |  | Chelmsford/Westford | Closed
National Grid | NEWBURY | 372447 | 01950 | 9.8 | Solar | 05_14_92L4 | 08/05/2021 | 12/10/2021 | 2 | 1 | 1 | 08/09/2021 | 08/09/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2022 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress - Start Study
National Grid | WESTFORD | 660119 | 01886 | 7.475 | Solar | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | METHUEN | 708501 | 01844 | 3.8 | Solar | 05_01_412L2 | 08/11/2025 | 08/28/2025 | 13 | 9 | 4 | 08/29/2025 | 08/29/2025 | 45 | 28 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | BILLERICA | 727815 | 01821 | 5.76 | Solar | 05_01_55W1 | 10/20/2025 | 11/14/2025 | 17 | 15 | 2 | 11/17/2025 | 11/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WORCESTER | 174581 | 01606 | 190 | Solar | 05_05_115W42 | 10/18/2011 | 10/18/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2011 |  | 10/31/2012 | N | EXP | 314 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/11/2012 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | WEBSTER | 537105 | 01570 | 10 | Solar | 05_12_25W1 | 08/01/2023 | 08/07/2023 | 4 | 0 | 4 | 08/08/2023 | 08/08/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 | 08/01/2023 | 11/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | RUTLAND | 341902 | 01543 | 15.2 | Solar | 05_12_51T2 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N |  | Hanover | Awaiting Initial Payments for Common System Modifications
National Grid | FALL RIVER | 549712 | 02724 | 4998 | Other | 05_14_36L2 | 10/25/2023 | 11/16/2023 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 02/16/2024 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N |  | Adams-Deerfield | Closed
National Grid | SAUGUS | 202799 | 01906 | 10 | Solar | 05_14_58L3 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 2/6/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N |  | Brockton-South | Common System Modifications Design In Progress
National Grid | ESSEX | 178369 | 01929 | 20 | Solar | 05_14_74L1 | 11/20/2017 | 11/20/2017 | 44 | 8 | 36 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 3/22/2019 | N | EXP | 416 |  |  | 0 | 0 | 0 |  |  | 3/23/2019 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications - Awaiting Full Payment
National Grid | NEWBURY | 465206 | 01950 | 15.2 | Solar | 05_14_92L4 | 10/02/2022 | 10/05/2022 | 4 | 3 | 1 | 10/06/2022 | 10/06/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2023 | Connected |  | N |  | North Andover | Closed
National Grid | WESTFORD | 660120 | 01886 | 7.475 | Solar | 05_01_24W3 | 12/12/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N |  | North Andover | Closed
National Grid | METHUEN | 175080 | 01844 | 1000 | Natural Gas | 05_01_412L3 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2013 | 12/11/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2015 | 10/01/2013 | 12/31/2016 | Y | STD | 664 | 06/17/2016 | 09/01/2016 | 52 | 0 | 52 | 10/2/2013 | 10/2/2013 | 6/14/2016 | Connected |  | N |  | North Andover | Closed
National Grid | BILLERICA | 174972 | 01821 | 4999 | Solar | 05_01_55W3 | 09/26/2011 | 09/26/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2011 | 12/20/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2012 | 09/26/2011 | 6/1/2014 | Y | STD | 59 | 03/12/2014 | 12/18/2014 | 192 | 0 | 192 | 7/9/2014 | 7/9/2014 | 7/11/2014 | Connected |  | N |  | North Andover | Closed
National Grid | WORCESTER | 175817 | 01606 | 150 | Solar | 05_05_115W42 | 07/28/2015 | 07/28/2015 | 2 | 2 | 0 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 |  | 8/3/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/7/2016 | 9/7/2016 | 9/7/2016 | Connected |  | N |  | North Andover | Closed
National Grid | OXFORD | 578612 | 01540 | 8.7 | Solar | 05_12_25W1 | 01/08/2024 | 01/11/2024 | 3 | 0 | 3 | 01/12/2024 | 01/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Tewksbury | Closed - Awaiting Payment
National Grid | RUTLAND | 347745 | 01543 | 10 | Solar | 05_12_51T2 | 04/15/2021 | 05/05/2021 | 13 | 12 | 1 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | FALL RIVER | 704769 | 02724 | 210 | Solar | 05_14_36L2 | 07/14/2025 | 08/07/2025 | 18 | 8 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | SAUGUS | 247730 | 01906 | 10 | Solar | 05_14_58L3 | 08/12/2019 | 08/13/2019 | 0 | 0 | 0 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 8/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N |  | Fall River-North | Closed - Completion Documents Hold
National Grid | HAMILTON | 178489 | 01982 | 7 | Solar | 05_14_74L1 | 11/30/2017 | 11/30/2017 | 0 | 0 | 0 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/6/2018 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N |  | Billerica | Closed - Construction Hold
National Grid | NEWBURY | 705471 | 01950 | 13.36 | Solar | 05_14_92L4 | 07/21/2025 | 08/21/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 54 | 39 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Chelmsford/Westford | Closed
National Grid | WESTFORD | 668899 | 01886 | 7.6 | Solar | 05_01_24W3 | 02/03/2025 | 04/16/2025 | 1 | 0 | 1 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N |  | Bridgewater | Notice Period - Pending Customer Decision
National Grid | METHUEN | 176487 | 01844 | 3000 | Natural Gas | 05_01_412L3 | 12/08/2015 | 12/10/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/11/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/23/2016 | 06/23/2016 | 21 | 0 | 21 | 11/7/2016 |  | 1/31/2019 | N | STD | 815 |  |  | 0 | 0 | 0 |  |  | 1/19/2019 | Connected |  | N |  | Hopedale-West | Time Frame Suspension
National Grid | BILLERICA | 176162 | 01821 | 1000 | Solar | 05_01_55W3 | 02/06/2015 | 02/06/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 | 02/06/2015 | 9/24/2017 | Y | STD | 648 | 08/11/2017 | 09/15/2017 | 24 | 0 | 24 | 9/8/2017 | 9/8/2017 | 9/29/2017 | Connected |  | N |  | Tewksbury | Closed - Completion Documents Hold
National Grid | WORCESTER | 176031 | 01606 | 450 | Solar | 05_05_115W42 | 06/18/2015 | 06/18/2015 | 34 | 34 | 0 | 08/07/2015 | 08/07/2015 | 308 | 0 | 308 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 1/30/2017 | N | EXP | 49 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Methuen/Haverhill | Closed - Completion Documents Hold
National Grid | OXFORD | 647190 | 01540 | 6 | Solar | 05_12_25W1 | 10/15/2024 | 10/18/2024 | 1 | 0 | 1 | 10/21/2024 | 10/21/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2024 | Connected |  | N |  | Chelmsford/Westford | Closed - Pending Customer Decision
National Grid | RUTLAND | 368281 | 01543 | 7.6 | Solar | 05_12_51T2 | 07/23/2021 | 01/07/2022 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 07/23/2021 | 1/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2022 | Connected |  | N |  | Hopedale-East | Awaiting Full Payments for Common System Modifications
National Grid | FALL RIVER | 729925 | 02724 | 34.6 | Solar | 05_14_36L2 | 11/06/2025 | 11/20/2025 | 9 | 7 | 2 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | SAUGUS | 263958 | 01906 | 0 | Solar | 05_14_58L3 | 11/05/2019 | 11/05/2019 | 0 | 0 | 0 | 11/06/2019 | 11/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N |  | Marlborough | Notice Period
National Grid | ESSEX | 178539 | 01929 | 7.6 | Solar | 05_14_74L1 | 01/26/2018 | 01/26/2018 | 9 | 1 | 8 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 | 01/26/2018 | 1/31/2019 | Y | EXP | 356 | 06/12/2018 | 06/21/2018 | 9 | 0 | 9 |  |  | 8/20/2018 | Connected |  | N |  | Chelmsford/Westford | Closed - Awaiting Payment
National Grid | NEWBURY | 702356 | 01950 | 20 | Solar | 05_14_92L6 | 07/02/2025 | 08/04/2025 | 13 | 11 | 2 | 08/05/2025 | 08/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y |  | Millbury-Grafton | Closed
National Grid | WESTFORD | 714389 | 01886 | 5.76 | Solar | 05_01_24W3 | 08/25/2025 | 09/05/2025 | 7 | 2 | 5 | 09/08/2025 | 09/08/2025 | 59 | 47 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Tewksbury | Closed - Awaiting Payment
National Grid | METHUEN | 210192 | 01844 | 4250 | Natural Gas | 05_01_412L3 | 06/24/2019 | 07/16/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2019 | 07/25/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 | 06/24/2019 | 9/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N |  | Ayer-Clinton | Closed - Pending Customer Decision
National Grid | BILLERICA | 178360 | 01821 | 4300 | Solar | 05_01_55W3 | 03/30/2018 | 03/30/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2018 | 05/21/2018 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Leominster | Closed
National Grid | WORCESTER | 176427 | 01606 | 10 | Solar | 05_05_115W42 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 | 02/03/2016 | 1/8/2018 | Y | EXP | 672 | 08/11/2017 | 09/06/2017 | 17 | 0 | 17 | 9/27/2017 | 9/27/2017 | 9/29/2017 | Connected |  | N |  | Bridgewater | Notice Period
National Grid | OXFORD | 656366 | 01540 | 10 | Solar | 05_12_25W1 | 11/22/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Lowell | 125 Day Study
National Grid | RUTLAND | 369753 | 01543 | 8.376 | Solar | 05_12_51T2 | 08/17/2021 | 08/27/2021 | 9 | 8 | 1 | 08/30/2021 | 08/30/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2021 |  | 11/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2022 | Connected |  | N |  | Lowell | 125 Day Study
National Grid | FALL RIVER | 737803 | 02724 | 11.5 | Solar | 05_14_36L2 | 12/03/2025 | 12/05/2025 | 2 | 0 | 2 | 01/05/2026 | 01/05/2026 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N |  | Lowell | 125 Day Study
National Grid | SAUGUS | 353145 | 01906 | 5.8 | Solar | 05_14_58L3 | 04/16/2021 | 05/10/2021 | 15 | 13 | 2 | 05/11/2021 | 05/11/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N |  | Lowell | 125 Day Study
National Grid | BEVERLY | 186105 | 01915 | 15.2 | Solar | 05_14_74L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Scituate | Closed
National Grid | NEWBURY | 710907 | 01950 | 15.68 | Solar | 05_14_92L6 | 09/10/2025 | 09/22/2025 | 7 | 4 | 3 | 09/23/2025 | 09/23/2025 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y |  | Scituate | Closed
National Grid | WESTFORD | 174797 | 01886 | 100 | Solar | 05_01_24W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 438 | 119 | 319 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/7/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | METHUEN | 578994 | 01844 | 240 | Solar | 05_01_412L4 | 12/22/2023 | 01/09/2024 | 10 | 0 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | BILLERICA | 357820 | 01821 | 240 | Solar | 05_01_602W2 | 05/14/2021 | 06/02/2021 | 10 | 0 | 10 |  |  | 53 | 28 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 176919 | 01605 | 6 | Solar | 05_05_115W42 | 05/05/2016 | 05/05/2016 | 4 | 4 | 0 | 05/12/2016 | 05/12/2016 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/11/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | DUDLEY | 665766 | 01571 | 7.6 | Solar | 05_12_25W1 | 01/15/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/15/2025 | 3/21/2026 | Y | EXP | 365 | 10/28/2025 | 10/29/2025 | 2 | 0 | 2 |  |  |  | Withdrawn |  | Y |  | Brockton-South | Closed
National Grid | GARDNER | 372473 | 01440 | 6.96 | Solar | 05_12_51T2 | 07/28/2021 | 07/29/2021 | 1 | 0 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2021 | Connected |  | N |  | Brockton-South | Closed
National Grid | FALL RIVER | 742426 | 02724 | 50 | Solar | 05_14_36L2 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 369368 | 01906 | 7.6 | Solar | 05_14_58L3 | 07/13/2021 | 08/24/2021 | 30 | 26 | 4 | 08/25/2021 | 08/25/2021 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2022 | Connected |  | N |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | BEVERLY | 187541 | 01915 | 11.4 | Solar | 05_14_74L1 | 06/08/2018 | 06/08/2018 | 10 | 0 | 10 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 6/8/2020 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 752916 | 01950 | 11.4 | Solar | 05_14_92L6 | 02/24/2026 | 02/27/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 174964 | 01886 | 81 | Solar | 05_01_24W4 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2013 |  | 11/29/2013 | N | EXP | 66 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | METHUEN | 578997 | 01844 | 140 | Solar | 05_01_412L4 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Chelmsford/Westford | Group Member Confirmation - Pending Customer Decision
National Grid | BILLERICA | 472560 | 01821 | 30 | Solar | 05_01_602W2 | 05/14/2023 | 05/30/2023 | 11 | 2 | 9 |  |  | 66 | 41 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 178444 | 01606 | 7.6 | Solar | 05_05_115W42 | 04/03/2018 | 04/03/2018 | 8 | 0 | 8 | 04/27/2018 | 04/27/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 |  | 4/9/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 11/20/2018 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | DUDLEY | 673544 | 01571 | 10 | Solar | 05_12_25W1 | 02/21/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/21/2025 | 6/7/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  | 1/5/2026 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | GARDNER | 396471 | 01440 | 0 | Other | 05_12_51T2 | 01/04/2022 | 01/28/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 03/02/2022 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Millbury-Grafton | Closed - QC and Revisions
National Grid | FALL RIVER | 745432 | 02724 | 21.28 | Solar | 05_14_36L2 | 02/27/2026 |  | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N |  | Millbury-Grafton | Closed
National Grid | SAUGUS | 401105 | 01906 | 0 | Other | 05_14_58L3 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 02/10/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Millbury-Grafton | Closed - Start Study
National Grid | ESSEX | 205269 | 01929 | 1500 | Solar | 05_14_74L1 | 01/04/2019 | 02/08/2019 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/11/2019 | 03/06/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Leominster | Group Window
National Grid | NEWBURY | 174140 | 01950 | 82.3 | Solar | 05_14_92L6 | 04/11/2012 | 04/11/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 7/6/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 12/27/2012 | Connected |  | N |  | Leominster | Group Window
National Grid | WESTFORD | 202543 | 01886 | 249.9 | Solar | 05_01_24W4 | 12/21/2018 | 01/10/2019 | 5 | 0 | 5 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hanover | Time Frame Suspension
National Grid | METHUEN | 657806 | 01844 | 7.6 | Solar | 05_01_412L4 | 12/02/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 12/02/2024 | 3/13/2026 | Y | EXP | 4 | 07/30/2025 | 08/04/2025 | 6 | 0 | 6 |  |  |  | Completion Documents |  | N |  | Hanover | Time Frame Suspension
National Grid | BILLERICA | 536174 | 01821 | 275 | Solar | 05_01_602W2 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/20/2023 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 194988 | 01606 | 7.6 | Solar | 05_05_115W42 | 09/04/2018 | 10/29/2018 | 19 | 19 | 0 | 10/30/2018 | 10/30/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 686943 | 01571 | 3.8 | Solar | 05_12_25W1 | 04/22/2025 | 05/08/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | GARDNER | 401039 | 01440 | 15.2 | Solar | 05_12_51T2 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 174790 | 02724 | 1020 | Diesel | 05_14_36L2 | 06/16/2011 | 06/16/2011 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 5/2/2012 | N | STD | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 5/2/2012 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | SAUGUS | 402235 | 01906 | 0 | Solar | 05_14_58L3 | 12/20/2021 | 12/21/2021 | 1 | 0 | 1 | 12/22/2021 | 12/22/2021 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 | 12/20/2021 | 4/11/2023 | Y | EXP | 365 | 03/09/2022 | 04/11/2022 | 34 | 0 | 34 |  |  | 5/12/2022 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | HAMILTON | 208621 | 01982 | 900 | Solar | 05_14_74L1 | 03/27/2019 | 04/20/2019 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2019 | 05/17/2019 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 175938 | 01950 | 16 | Solar | 05_14_92L6 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 6/15/2016 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WESTFORD | 396605 | 01886 | 0 | Other | 05_01_24W4 | 05/11/2022 | 05/27/2022 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/22/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | METHUEN | 672839 | 01844 | 700 | Solar | 05_01_412L4 | 04/14/2025 | 10/10/2025 | 124 | 115 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 | 10/21/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | MPL-East | Scoping Meeting
National Grid | BILLERICA | 543236 | 01821 | 0 | Other | 05_01_602W2 | 09/07/2023 | 10/02/2023 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2023 | 11/07/2023 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N |  | Hopedale-East | 160 Day Study
National Grid | WORCESTER | 209761 | 01606 | 7.04 | Solar | 05_05_115W42 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 | 03/20/2019 | 4/10/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N |  | Cape Ann | Pending
National Grid | DUDLEY | 716298 | 01571 | 0 | Battery Add-On | 05_12_25W1 | 09/03/2025 | 10/17/2025 | 3 | 0 | 3 | 10/20/2025 | 10/20/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | HUBBARDSTON | 421351 | 01452 | 0 | Solar | 05_12_51T2 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Group Member Confirmation
National Grid | FALL RIVER | 174865 | 02724 | 30 | Solar | 05_14_36L2 | 04/08/2011 | 04/08/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 04/08/2011 | 5/2/2012 | Y | EXP |  | 02/21/2012 | 03/13/2012 | 15 | 0 | 15 | 8/9/2012 | 8/9/2012 | 5/2/2012 | Connected |  | N |  | Leominster | Group Window
National Grid | SAUGUS | 401888 | 01906 | 15.2 | Solar | 05_14_58L3 | 12/17/2021 | 12/23/2021 | 5 | 3 | 2 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Lowell | On Hold Behind Preceding Group Study
National Grid | ESSEX | 208566 | 01929 | 3.8 | Solar | 05_14_74L1 | 02/18/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Lowell | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 176225 | 01950 | 7.6 | Solar | 05_14_92L6 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 05/06/2016 | 09/02/2016 | 82 | 0 | 82 | 9/23/2015 | 9/23/2015 | 9/13/2016 | Connected |  | N |  | Hanover | Time Frame Suspension
National Grid | WESTFORD | 601631 | 01886 | 3.8 | Solar | 05_01_24W4 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 4/25/2025 | Y | EXP | 365 | 05/24/2024 | 09/12/2024 | 112 | 0 | 112 |  |  | 9/26/2024 | Connected |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | METHUEN | 677465 | 01844 | 20 | Solar | 05_01_412L4 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 25 | 0 | 25 | 05/27/2025 | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 43 | 0 | 43 |  |  | 0 | 0 | 0 | 8/4/2025 |  | 8/21/2026 | N | EXP | 365 | 10/01/2025 |  | 157 | 0 | 157 |  |  |  | Construction |  | N |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 605595 | 01821 | 100 | Solar | 05_01_602W2 | 04/22/2024 | 05/08/2024 | 12 | 5 | 7 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Hopedale-East | 160 Day Study
National Grid | WORCESTER | 376028 | 01606 | 3.8 | Solar | 05_05_115W42 | 08/25/2021 | 08/27/2021 | 2 | 0 | 2 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 | 08/25/2021 | 1/24/2023 | Y | EXP | 365 | 12/02/2021 | 01/12/2022 | 42 | 0 | 42 |  |  | 2/7/2022 | Connected |  | Y |  | Chelmsford/Westford | Group Member Confirmation - Awaiting Other Group Members
National Grid | DUDLEY | 726138 | 01571 | 17.2 | Solar | 05_12_25W2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | GARDNER | 433980 | 01440 | 7.6 | Solar | 05_12_51T2 | 06/14/2022 | 06/15/2022 | 2 | 1 | 1 | 06/16/2022 | 06/16/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2023 | Connected |  | N |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 175714 | 02724 | 64 | Solar | 05_14_36L2 | 12/24/2014 | 12/24/2014 | 7 | 4 | 3 | 01/06/2015 | 01/06/2015 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 12/31/2016 | N | EXP | 683 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 |  | Withdrawn |  | N |  | Chelmsford/Westford | Group Member Confirmation - Pending Customer Decision
National Grid | MELROSE | 427118 | 02176 | 15.2 | Solar | 05_14_58L3 | 04/28/2022 | 06/09/2022 | 29 | 29 | 0 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 04/28/2022 | 1/30/2024 | Y | EXP | 365 | 01/07/2023 | 01/30/2023 | 24 | 0 | 24 |  |  | 4/27/2023 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 277815 | 01982 | 7.6 | Solar | 05_14_74L1 | 03/03/2020 | 03/09/2020 | 3 | 0 | 3 | 03/10/2020 | 03/10/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2020 | 03/03/2020 |  | Y | EXP | 365 | 02/06/2021 | 02/12/2021 | 6 | 0 | 6 |  |  | 4/27/2021 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | NEWBURY | 176469 | 01950 | 10 | Solar | 05_14_92L6 | 03/17/2016 | 03/17/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/17/2016 | 3/23/2017 | Y | EXP | 345 | 06/21/2016 | 07/29/2016 | 27 | 0 | 27 | 9/20/2016 | 9/20/2016 | 9/23/2016 | Connected |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | WESTFORD | 632651 | 01886 | 5.76 | Solar | 05_01_24W4 | 08/14/2024 | 09/10/2024 | 3 | 0 | 3 | 09/11/2024 | 09/11/2024 | 105 | 31 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | METHUEN | 699718 | 01844 | 10 | Solar | 05_01_412L4 | 06/19/2025 | 07/02/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/19/2025 | 9/5/2026 | Y | EXP | 365 | 02/13/2026 |  | 22 | 0 | 22 |  |  |  | Construction |  | N |  | Barre-Athol | Scoping Meeting
National Grid | BILLERICA | 655034 | 01821 | 120 | Solar | 05_01_602W2 | 11/25/2024 | 12/20/2024 | 17 | 8 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 387941 | 01606 | 3 | Solar | 05_05_115W42 | 10/21/2021 | 12/21/2021 | 9 | 4 | 5 | 11/04/2021 | 11/04/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/21/2021 | 5/25/2024 | Y | EXP | 365 | 01/26/2023 | 05/15/2023 | 110 | 0 | 110 |  |  | 7/11/2023 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 174932 | 01571 | 278.4 | Solar | 05_12_25W2 | 08/29/2013 | 08/29/2013 | 7 | 0 | 7 | 09/11/2013 | 09/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 | 08/29/2013 | 10/31/2014 | Y | EXP | 378 | 12/19/2014 | 02/12/2015 | 36 | 0 | 36 | 4/1/2015 | 4/1/2015 | 4/6/2015 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | GARDNER | 433829 | 01440 | 5.76 | Solar | 05_12_51T2 | 06/07/2022 | 06/15/2022 | 6 | 5 | 1 | 06/16/2022 | 06/16/2022 | 74 | 42 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | FALL RIVER | 177069 | 02724 | 150 | Solar | 05_14_36L2 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 07/29/2016 | 07/29/2016 | 315 | 26 | 289 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/29/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Barre-Athol | Scoping Meeting
National Grid | SAUGUS | 534351 | 01906 | 15.2 | Solar | 05_14_58L3 | 06/15/2023 | 06/27/2023 | 7 | 5 | 2 | 06/28/2023 | 06/28/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N |  | Leominster | Group Window
National Grid | ESSEX | 283578 | 01929 | 9.57 | Solar | 05_14_74L1 | 06/17/2020 | 06/19/2020 | 1 | 0 | 1 | 06/22/2020 | 06/22/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/17/2020 | 6/17/2021 | Y | EXP | 365 | 02/10/2021 | 04/09/2021 | 58 | 0 | 58 |  |  | 4/13/2021 | Connected |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 199034 | 01950 | 7.6 | Solar | 05_14_92L6 | 10/19/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | WESTFORD | 178232 | 01886 | 43.2 | Solar | 05_01_24W5 | 01/05/2018 | 01/05/2018 | 0 | 0 | 0 | 01/25/2018 | 01/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2018 |  | 1/13/2019 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | METHUEN | 734536 | 01844 | 5.76 | Solar | 05_01_412L4 | 11/18/2025 | 11/19/2025 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 653874 | 01821 | 50 | Solar | 05_01_602W2 | 11/15/2024 | 11/19/2024 | 2 | 0 | 2 |  |  | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 422789 | 01606 | 3.8 | Solar | 05_05_115W42 | 04/07/2022 | 08/04/2022 | 2 | 0 | 2 | 08/05/2022 | 08/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 178186 | 01571 | 15.2 | Solar | 05_12_25W2 | 04/13/2018 | 04/13/2018 | 6 | 0 | 6 | 04/25/2018 | 04/25/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | GARDNER | 448083 | 01440 | 7.6 | Solar | 05_12_51T2 | 08/17/2022 | 08/22/2022 | 17 | 9 | 8 | 08/23/2022 | 08/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2023 | Connected |  | N |  | Millbury-Grafton | Closed
National Grid | FALL RIVER | 177596 | 02724 | 180 | Solar | 05_14_36L2 | 07/18/2017 | 07/18/2017 | 73 | 69 | 4 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2018 | 07/18/2017 | 8/31/2021 | Y | STD | 533 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | Scoping Meeting
National Grid | SAUGUS | 554429 | 01906 | 0 | Battery Add-On | 05_14_58L3 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | Scoping Meeting
National Grid | BEVERLY | 321316 | 01915 | 7.6 | Solar | 05_14_74L1 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | NEWBURY | 221173 | 01950 |  | Solar | 05_14_92L6 | 04/19/2019 |  | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | 160 Day Study
National Grid | WESTFORD | 226537 | 01886 | 4405 | Solar | 05_01_24W5 | 05/20/2019 | 05/31/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2019 | 06/27/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Hopedale-East | 160 Day Study
National Grid | METHUEN | 739355 | 01844 | 7.6 | Solar | 05_01_412L4 | 12/10/2025 | 12/11/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 | 12/10/2025 | 2/9/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N |  | Hopedale-East | 160 Day Study
National Grid | BILLERICA | 706227 | 01821 | 7.6 | Solar | 05_01_602W2 | 07/21/2025 | 07/23/2025 | 2 | 0 | 2 | 07/24/2025 | 07/24/2025 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 445797 | 01606 | 6 | Solar | 05_05_115W42 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2022 |  | 9/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | CHARLTON | 178740 | 01507 | 15.2 | Solar | 05_12_25W2 | 04/18/2018 | 04/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/24/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTMINSTER | 457042 | 01473 | 15.2 | Solar | 05_12_51T2 | 09/07/2022 | 09/08/2022 | 1 | 0 | 1 | 09/09/2022 | 09/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2022 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 177863 | 02724 | 990 | Solar | 05_14_36L2 | 06/13/2017 | 06/13/2017 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2017 | 07/31/2017 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 | 06/13/2017 | 3/15/2024 | Y | STD | 753 | 05/29/2020 | 03/31/2021 | 306 | 5 | 301 |  |  |  | Withdrawn |  | N |  | MPL-East | Scoping Meeting
National Grid | SAUGUS | 650740 | 01906 | 8.376 | Solar | 05_14_58L3 | 10/30/2024 | 12/02/2024 | 10 | 5 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 10/30/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | HAMILTON | 323842 | 01982 | 9.8 | Solar | 05_14_74L1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Millbury-Grafton | Group Window
National Grid | NEWBURY | 230013 | 01950 | 15.2 | Solar | 05_14_92L6 | 05/21/2019 | 05/28/2019 | 3 | 1 | 2 | 05/29/2019 | 05/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 05/21/2019 | 11/1/2019 | Y | EXP | 147 | 07/25/2019 | 10/02/2019 | 69 | 0 | 69 |  |  | 10/8/2019 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 309000 | 01886 | 7.6 | Solar | 05_01_24W5 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | METHUEN | 174759 | 01844 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 6/30/2017 | Y | STD | 93 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 6/28/2017 | Connected |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 713175 | 01821 | 23 | Solar | 05_01_602W2 | 08/19/2025 | 08/21/2025 | 2 | 0 | 2 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 480673 | 01606 | 6 | Solar | 05_05_115W42 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | DUDLEY | 327874 | 01571 | 7.6 | Solar | 05_12_25W2 | 11/23/2020 | 11/25/2020 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 | 11/23/2020 | 9/10/2022 | Y | EXP | 365 | 04/22/2021 | 08/10/2021 | 110 | 0 | 110 |  |  | 9/24/2021 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | WESTMINSTER | 459143 | 01473 | 15.2 | Solar | 05_12_51T2 | 09/15/2022 | 09/19/2022 | 2 | 0 | 2 | 09/20/2022 | 09/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | N |  | Hanover | Time Frame Suspension
National Grid | FALL RIVER | 177940 | 02724 | 125 | Solar | 05_14_36L2 | 06/22/2017 | 06/22/2017 | 0 | 0 | 0 | 02/12/2018 | 02/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 06/22/2017 | 12/31/2019 | Y | EXP | 675 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N |  | Hanover | Time Frame Suspension
National Grid | MELROSE | 657428 | 02176 | 7.6 | Solar | 05_14_58L3 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | ESSEX | 334306 | 01929 | 7.6 | Solar | 05_14_74L1 | 01/13/2021 | 01/29/2021 | 11 | 11 | 0 | 02/01/2021 | 02/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 | 01/13/2021 | 9/29/2022 | Y | EXP | 365 | 09/11/2021 | 09/24/2021 | 14 | 0 | 14 |  |  | 3/3/2022 | Connected |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | NEWBURY | 354556 | 01950 | 10 | Solar | 05_14_92L6 | 04/26/2021 | 05/04/2021 | 5 | 5 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2021 | Connected |  | N |  | Hanover | Time Frame Suspension
National Grid | WESTFORD | 396684 | 01886 | 0 | Other | 05_01_24W5 | 04/28/2022 | 05/19/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Group Member Confirmation
National Grid | METHUEN | 174758 | 01844 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 8/31/2017 | Y | STD | 965 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 8/11/2017 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | BILLERICA | 715276 | 01821 | 10 | Solar | 05_01_602W2 | 08/28/2025 | 09/18/2025 | 2 | 0 | 2 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 08/28/2025 | 11/4/2026 | Y | EXP | 365 | 01/15/2026 |  | 51 | 0 | 51 |  |  |  | Construction |  | N |  | MPL-East | Scoping Meeting
National Grid | WORCESTER | 480438 | 01606 | 3.8 | Solar | 05_05_115W42 | 11/29/2022 | 12/06/2022 | 5 | 0 | 5 | 12/07/2022 | 12/07/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2023 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | DUDLEY | 475161 | 01571 | 15.2 | Solar | 05_12_25W2 | 11/07/2022 | 11/08/2022 | 2 | 1 | 1 | 11/09/2022 | 11/09/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Barre-Athol | Scoping Meeting
National Grid | HUBBARDSTON | 476277 | 01452 | 0 | Solar | 05_12_51T2 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/15/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 187091 | 02724 | 86.4 | Solar | 05_14_36L2 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  | 7/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | Connected |  | N |  | MPL-Northwest | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 663371 | 01906 | 17.6 | Solar | 05_14_58L3 | 01/02/2025 | 01/06/2025 | 3 | 1 | 2 | 01/07/2025 | 01/07/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 01/02/2025 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 338817 | 01982 | 937.5 | Solar | 05_14_74L1 | 05/17/2021 | 08/04/2021 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2021 | 09/08/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 367329 | 01950 | 7.6 | Solar | 05_14_92L6 | 07/20/2021 | 07/21/2021 | 0 | 0 | 0 | 07/22/2021 | 07/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2021 | 07/20/2021 | 5/20/2023 | Y | EXP | 365 | 01/18/2022 | 05/20/2022 | 123 | 0 | 123 |  |  | 6/8/2022 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTFORD | 415781 | 01886 | 8.41 | Solar | 05_01_24W5 | 07/11/2022 |  | 30 | 27 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | Scoping Meeting
National Grid | METHUEN | 174757 | 01844 | 448 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/30/2017 | Y | STD | 842 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | BILLERICA | 714916 | 01821 | 12.16 | Solar | 05_01_602W2 | 08/26/2025 | 09/16/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/26/2025 | 12/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 482372 | 01606 | 3 | Solar | 05_05_115W42 | 12/05/2022 | 12/19/2022 | 10 | 5 | 5 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 5/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | Y |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 608064 | 01571 | 0 | Battery Add-On | 05_12_25W2 | 05/09/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 05/09/2024 | 6/20/2025 | Y | EXP | 365 | 07/31/2024 | 12/05/2024 | 127 | 0 | 127 |  |  | 12/11/2024 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | HUBBARDSTON | 477583 | 01452 | 9.57 | Solar | 05_12_51T2 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  | 1/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N |  | Gardner-Winchendon | Scoping Meeting
National Grid | FALL RIVER | 210060 | 02724 | 7.6 | Solar | 05_14_36L2 | 03/19/2019 |  | 142 | 26 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Group Window
National Grid | MELROSE | 551107 | 02176 | 240 | Solar | 05_14_59L1 | 01/05/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2024 | 02/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y |  | Hopedale-East | 160 Day Study
National Grid | ESSEX | 340566 | 01929 | 6 | Solar | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 638125 | 01950 | 10 | Solar | 05_14_92L6 | 09/05/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 440578 | 01810 | 8.41 | Solar | 05_01_24W5 | 07/20/2022 | 08/03/2022 | 11 | 8 | 3 | 08/04/2022 | 08/04/2022 | 28 | 7 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 07/20/2022 | 6/8/2024 | Y | EXP | 365 | 05/24/2023 | 06/08/2023 | 16 | 0 | 16 |  |  | 6/30/2023 | Connected |  | Y |  | Bridgewater | On Hold Behind Preceding Group Study
National Grid | METHUEN | 174760 | 01844 | 497.6 | Solar | 05_01_412L4 | 02/06/2014 | 02/06/2014 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2014 | 03/18/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2015 | 02/06/2014 | 4/28/2017 | Y | STD | 84 | 12/16/2016 | 06/06/2017 | 116 | 0 | 116 | 7/14/2017 | 7/14/2017 | 4/18/2017 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 743484 | 01821 | 11.52 | Solar | 05_01_602W2 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | WORCESTER | 482174 | 01606 | 3.8 | Solar | 05_05_115W42 | 12/20/2022 | 12/26/2022 | 4 | 0 | 4 | 12/27/2022 | 12/27/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | DUDLEY | 625229 | 01571 | 15.2 | Solar | 05_12_25W2 | 07/18/2024 | 07/25/2024 | 5 | 3 | 2 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | WESTMINSTER | 483824 | 01473 | 0 | Solar | 05_12_51T2 | 12/08/2022 | 12/15/2022 | 6 | 4 | 2 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N |  | Millbury-Grafton | Group Window
National Grid | FALL RIVER | 243484 | 02724 | 53 | Solar | 05_14_36L2 | 07/15/2019 | 07/30/2019 | 11 | 3 | 8 | 07/31/2019 | 07/31/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | SAUGUS | 174889 | 01906 | 20 | Solar | 05_14_59L1 | 08/13/2013 | 08/13/2013 | 7 | 0 | 7 | 08/23/2013 | 08/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2013 |  | 9/25/2013 | N | EXP | 9 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 2/10/2014 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | ESSEX | 346362 | 01929 | 7.6 | Solar | 05_14_74L1 | 03/26/2021 | 03/31/2021 | 2 | 0 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/26/2021 | 10/19/2022 | Y | EXP | 365 | 09/29/2021 | 10/29/2021 | 31 | 4 | 27 |  |  | 11/30/2021 | Connected |  | Y |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 643835 | 01950 | 7.6 | Solar | 05_14_92L6 | 10/01/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y |  | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 552074 | 01810 | 5.985 | Solar | 05_01_24W5 | 10/25/2023 | 12/08/2023 | 30 | 25 | 5 | 12/11/2023 | 12/11/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 10/25/2023 | 3/15/2025 | Y | EXP | 365 | 05/15/2024 | 07/03/2024 | 50 | 0 | 50 |  |  | 8/13/2024 | Connected |  | N |  | Barre-Athol | On Hold Behind Preceding Group Study
National Grid | METHUEN | 175265 | 01844 | 15.8 | Solar | 05_01_412L4 | 06/16/2014 | 06/16/2014 | 6 | 0 | 6 | 06/26/2014 | 06/26/2014 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2014 |  | 9/1/2014 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | BILLERICA | 746247 | 01821 | 11.5 | Solar | 05_01_602W2 | 01/19/2026 | 01/27/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 484096 | 01606 | 10 | Solar | 05_05_115W42 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 1/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2023 | Connected |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 628432 | 01571 | 23 | Solar | 05_12_25W2 | 07/29/2024 | 07/31/2024 | 2 | 0 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | GARDNER | 485658 | 01440 | 7.6 | Solar | 05_12_51T2 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 63 | 40 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 259475 | 02724 | 53 | Solar | 05_14_36L2 | 10/25/2019 | 11/18/2019 | 15 | 13 | 2 | 11/19/2019 | 11/19/2019 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2020 | Connected |  | N |  | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | MELROSE | 174979 | 02176 | 950 | Solar | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | ESSEX | 364103 | 01929 | 4.08 | Solar | 05_14_74L1 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Leominster | Group Window
National Grid | NEWBURY | 645912 | 01950 | 7.6 | Solar | 05_14_92L6 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/18/2024 | 1/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N |  | Attleboro | On Hold Behind Preceding Group Study
National Grid | TEWKSBURY | 554530 | 01876 | 3.8 | Solar | 05_01_24W5 | 09/12/2023 | 09/18/2023 | 4 | 0 | 4 | 09/19/2023 | 09/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N |  | Hanover | Time Frame Suspension - Awaiting Additional Study Payments
National Grid | METHUEN | 175582 | 01844 | 19 | Solar | 05_01_412L4 | 12/14/2014 | 12/14/2014 | 6 | 4 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2015 |  | 2/28/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 | 1/7/2016 | 1/7/2016 | 1/7/2016 | Connected |  | N |  | Hopedale-East | 160 Day Study
National Grid | BILLERICA | 174177 | 01821 | 11.4 | Solar | 05_01_602W2 | 03/06/2012 | 03/06/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2012 |  | 6/4/2012 | N | EXP |  |  |  | 0 | 0 | 0 | 6/4/2012 | 6/4/2012 | 7/16/2012 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 486948 | 01606 | 3 | Solar | 05_05_115W42 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Chelmsford/Westford | Group Member Confirmation
National Grid | DUDLEY | 644449 | 01571 | 3.8 | Solar | 05_12_25W2 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | Chelmsford/Westford | Group Member Confirmation
National Grid | WESTMINSTER | 501092 | 01473 | 5.76 | Solar | 05_12_51T2 | 03/30/2023 | 04/03/2023 | 2 | 0 | 2 | 04/04/2023 | 04/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/30/2023 | 5/21/2024 | Y | EXP | 365 | 07/20/2023 | 07/24/2023 | 5 | 0 | 5 |  |  | 8/1/2023 | Connected |  | Y |  | Chelmsford/Westford | Group Member Confirmation
National Grid | FALL RIVER | 270895 | 02724 | 10 | Solar | 05_14_36L2 | 12/31/2019 | 01/10/2020 | 6 | 0 | 6 | 01/13/2020 | 01/13/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N |  | Chelmsford/Westford | Group Member Confirmation - Pending Customer Decision
National Grid | MELROSE | 174978 | 02176 | 950 | Solar | 05_14_59L1 | 09/13/2011 | 09/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/13/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N |  | Leominster | Group Window
National Grid | ESSEX | 395653 | 01929 | 6 | Solar | 05_14_74L1 | 12/06/2021 | 01/07/2022 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 12/06/2021 | 6/28/2023 | Y | EXP | 365 | 05/24/2022 | 06/28/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 646409 | 01950 | 5.76 | Solar | 05_14_92L6 | 10/25/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/25/2024 | 1/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N |  | Leominster | Group Window
National Grid | TEWKSBURY | 587312 | 01876 | 7.6 | Solar | 05_01_24W5 | 02/03/2024 | 02/05/2024 | 1 | 0 | 1 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/03/2024 | 2/22/2025 | Y | EXP | 365 | 05/04/2024 | 08/15/2024 | 104 | 0 | 104 |  |  | 10/25/2024 | Connected |  | N |  | Millbury-Grafton | Group Window
National Grid | METHUEN | 175747 | 01844 | 1000 | Solar | 05_01_412L4 | 10/30/2014 | 10/30/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/08/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 | 10/30/2014 | 9/1/2017 | Y | STD | 77 | 06/05/2017 | 08/16/2017 | 51 | 0 | 51 | 8/21/2017 | 8/21/2017 | 9/14/2017 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | BILLERICA | 174293 | 01821 | 2000 | Solar | 05_01_602W2 | 12/27/2011 | 12/27/2011 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2012 | 12/27/2011 | 10/1/2012 | Y | STD | 66 | 01/24/2014 | 02/10/2014 | 11 | 0 | 11 | 11/8/2013 | 11/8/2013 | 12/9/2013 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WORCESTER | 500885 | 01606 | 3.8 | Solar | 05_05_115W42 | 03/10/2023 | 03/20/2023 | 6 | 0 | 6 | 03/21/2023 | 03/21/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | DUDLEY | 646179 | 01571 | 7.6 | Solar | 05_12_25W2 | 10/18/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/18/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | HUBBARDSTON | 524266 | 01452 | 9.28 | Solar | 05_12_51T2 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 324647 | 02724 | 15.2 | Solar | 05_14_36L2 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2021 | Connected |  | N |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | MELROSE | 175015 | 02176 | 950 | Solar | 05_14_59L1 | 08/29/2011 | 08/29/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/19/2011 | 11/03/2011 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 08/29/2011 | 11/30/2012 | Y | STD | 12 | 04/11/2013 | 12/14/2013 | 169 | 0 | 169 | 12/13/2013 | 12/13/2013 | 12/13/2013 | Connected |  | N |  | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 409865 | 01982 | 6.67 | Solar | 05_14_74L1 | 03/24/2022 | 04/06/2022 | 10 | 9 | 1 | 04/07/2022 | 04/07/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2022 | 03/24/2022 | 7/8/2023 | Y | EXP | 365 | 06/08/2022 | 06/28/2022 | 21 | 0 | 21 |  |  | 8/1/2022 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | NEWBURY | 653778 | 01951 | 10 | Solar | 05_14_92L6 | 11/18/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/18/2024 | 3/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | ANDOVER | 615561 | 01810 | 3.8 | Solar | 05_01_24W5 | 06/04/2024 | 06/27/2024 | 12 | 11 | 1 | 06/28/2024 | 06/28/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Adams-Deerfield | Closed
National Grid | METHUEN | 175872 | 01844 | 56 | Solar | 05_01_412L4 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 10/4/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | BILLERICA | 174382 | 01821 | 2.58 | Solar | 05_01_602W2 | 05/30/2012 | 05/30/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2012 |  | 8/15/2012 | N | EXP | 26 |  |  | 0 | 0 | 0 | 9/10/2012 | 9/10/2012 | 1/22/2013 | Connected |  | N |  | Ayer-Clinton | Extended Group Study Opt-In - Pending Customer Decision
National Grid | WORCESTER | 504881 | 01606 | 6 | Solar | 05_05_115W42 | 03/09/2023 | 03/13/2023 | 2 | 0 | 2 | 03/14/2023 | 03/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2023 | 03/09/2023 | 7/13/2024 | Y | EXP | 365 | 06/20/2023 | 07/13/2023 | 24 | 0 | 24 |  |  | 8/23/2023 | Connected |  | N |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | WEBSTER | 650631 | 01570 | 7.6 | Solar | 05_12_25W2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/29/2024 | 1/7/2026 | Y | EXP | 365 | 04/15/2025 | 09/09/2025 | 148 | 0 | 148 |  |  |  | Withdrawn |  | Y |  | Leominster | Group Window
National Grid | HUBBARDSTON | 526797 | 01452 | 15.2 | Solar | 05_12_51T2 | 05/16/2023 | 05/18/2023 | 2 | 0 | 2 | 05/19/2023 | 05/19/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N |  | Brockton-North | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 354525 | 02724 | 100 | Solar | 05_14_36L2 | 05/27/2021 | 07/02/2021 | 24 | 14 | 10 | 07/06/2021 | 07/06/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 4/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | MELROSE | 175240 | 02176 | 15.2 | Solar | 05_14_59L1 | 08/21/2014 | 08/21/2014 | 7 | 0 | 7 | 09/03/2014 | 09/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 12/8/2014 | Connected |  | N |  | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | HAMILTON | 474114 | 01982 | 10 | Solar | 05_14_74L1 | 12/20/2022 | 12/21/2022 | 1 | 0 | 1 | 12/22/2022 | 12/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/20/2022 | 4/19/2024 | Y | EXP | 365 | 03/14/2023 | 04/19/2023 | 37 | 0 | 37 |  |  | 5/15/2023 | Connected |  | N |  | Gardner-Winchendon | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 654416 | 01950 | 5 | Solar | 05_14_92L6 | 11/14/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/14/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N |  | Hopedale-West | On Hold Behind Preceding Group Study
National Grid | ANDOVER | 643869 | 01810 | 10 | Solar | 05_01_24W5 | 10/04/2024 | 10/17/2024 | 4 | 0 | 4 | 10/18/2024 | 10/18/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/04/2024 | 12/9/2025 | Y | EXP | 365 | 02/13/2025 | 03/21/2025 | 37 | 0 | 37 |  |  | 4/16/2025 | Connected |  | N |  | MPL-East | On Hold Behind Preceding Group Study
National Grid | METHUEN | 175895 | 01844 | 7.6 | Solar | 05_01_412L4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 358 | 09/13/2016 | 09/23/2016 | 8 | 0 | 8 | 8/18/2015 | 8/18/2015 | 9/28/2016 | Connected |  | N |  | Spencer-Rutland | Scoping Meeting
National Grid | BILLERICA | 174549 | 01821 | 2800 | Solar | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 | 11/03/2011 | 4/1/2014 | Y | STD | 433 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 6/23/2014 | Connected |  | N |  | Barre-Athol | Scoping Meeting
National Grid | WORCESTER | 529991 | 01606 | 3.8 | Solar | 05_05_115W42 | 10/20/2023 | 10/24/2023 | 2 | 0 | 2 | 10/25/2023 | 10/25/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N |  | MPL-East | Scoping Meeting
National Grid | DUDLEY | 651937 | 01571 | 6.84 | Solar | 05_12_25W2 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | Y |  | Marlborough | On Hold Behind Preceding Group Study
National Grid | HUBBARDSTON | 566169 | 01452 | 0 | Solar | 05_12_51T2 | 10/25/2023 | 11/02/2023 | 6 | 3 | 3 | 11/03/2023 | 11/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2023 |  | 12/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N |  | Hopedale-East | On Hold Behind Preceding Group Study
National Grid | FALL RIVER | 668934 | 02724 | 0 | Battery Add-On | 05_14_36L2 | 01/30/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Webster-Southbridge-Charlton | On Hold Behind Preceding Group Study
National Grid | MELROSE | 177624 | 02176 | 15.2 | Solar | 05_14_59L1 | 11/09/2017 | 11/09/2017 | 1 | 0 | 1 | 12/05/2017 | 12/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N |  | Millbury-Grafton | Group Window
National Grid | ESSEX | 492624 | 01929 | 17.45 | Solar | 05_14_74L1 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/16/2023 | 6/14/2024 | Y | EXP | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y |  | Spencer-Rutland | On Hold Behind Preceding Group Study
National Grid | NEWBURY | 655710 | 01950 | 3.8 | Solar | 05_14_92L6 | 11/20/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 11/20/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | ANDOVER | 665488 | 01810 | 3.8 | Solar | 05_01_24W5 | 01/14/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175969 | 01844 | 19.75 | Solar | 05_01_412L4 | 08/07/2015 | 08/07/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/17/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/15/2016 | Connected |  | N
National Grid | BILLERICA | 174681 | 01821 | 30 | Solar | 05_01_602W2 | 01/08/2014 | 01/08/2014 | 2 | 0 | 2 | 01/13/2014 | 01/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2014 | 01/08/2014 | 6/20/2014 | Y | EXP | 142 |  |  | 0 | 0 | 0 | 1/29/2014 | 1/29/2014 | 6/24/2014 | Connected |  | N
National Grid | WORCESTER | 594405 | 01606 | 5 | Solar | 05_05_115W42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/19/2024 | 4/24/2025 | Y | EXP | 365 | 05/24/2024 | 07/05/2024 | 43 | 0 | 43 |  |  | 8/1/2024 | Connected |  | N
National Grid | DUDLEY | 662178 | 01571 | 12.92 | Solar | 05_12_25W2 | 12/23/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2025 | Connected |  | N
National Grid | HUBBARDSTON | 562855 | 01452 | 16.065 | Solar | 05_12_51T2 | 10/17/2023 | 10/31/2023 | 10 | 7 | 3 | 11/01/2023 | 11/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N
National Grid | FALL RIVER | 701387 | 02724 | 17.6 | Solar | 05_14_36L2 | 07/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | SAUGUS | 247404 | 01906 | 0 | Solar | 05_14_59L1 | 08/07/2019 | 08/07/2019 | 0 | 0 | 0 | 08/08/2019 | 08/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 10/11/2019 | N | EXP | 57 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | HAMILTON | 515458 | 01982 | 12.6 | Solar | 05_14_74L1 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 | 04/24/2023 | 11/5/2024 | Y | EXP | 365 | 09/12/2023 | 10/24/2023 | 43 | 0 | 43 |  |  | 11/18/2023 | Connected |  | N
National Grid | NEWBURY | 656812 | 01950 | 5.76 | Solar | 05_14_92L6 | 11/25/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/25/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | ANDOVER | 672053 | 01810 | 5.76 | Solar | 05_01_24W5 | 02/13/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | METHUEN | 176200 | 01844 | 17.6 | Solar | 05_01_412L4 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 | 02/19/2015 | 02/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 |  | 12/31/2016 | N | EXP | 668 |  |  | 0 | 0 | 0 | 3/4/2015 | 3/4/2015 | 12/11/2015 | Connected |  | N
National Grid | BILLERICA | 174986 | 01821 | 1000 | Solar | 05_01_602W2 | 11/03/2011 | 11/03/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 02/16/2012 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2013 |  | 12/31/2012 | N | STD | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 608980 | 01606 | 0 | Solar | 05_05_115W42 | 06/17/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 16 | 5 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | DUDLEY | 672929 | 01571 | 7.6 | Solar | 05_12_25W2 | 02/19/2025 | 03/24/2025 | 5 | 0 | 5 | 03/25/2025 | 03/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | HUBBARDSTON | 574209 | 01452 | 490 | Solar | 05_12_51T2 | 12/15/2023 | 01/09/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2024 | 03/11/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 710220 | 02724 | 26.6 | Solar | 05_14_36L2 | 08/06/2025 | 08/28/2025 | 16 | 14 | 2 | 08/29/2025 | 08/29/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | SAUGUS | 272817 | 01906 | 0 | Solar | 05_14_59L1 | 01/10/2020 | 01/21/2020 | 5 | 0 | 5 | 01/22/2020 | 01/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 1/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | HAMILTON | 558385 | 01982 | 990 | Solar | 05_14_74L1 | 12/04/2023 |  | 181 | 172 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 656807 | 01951 | 7.6 | Solar | 05_14_92L6 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | ANDOVER | 673375 | 01810 | 999 | Solar | 05_01_26W1 | 11/07/2025 | 01/15/2026 | 44 | 35 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2026 | 02/09/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 176592 | 01844 | 10 | Solar | 05_01_412L4 | 10/08/2015 | 10/08/2015 | 1 | 1 | 0 | 10/13/2015 | 10/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2015 | 10/08/2015 | 10/14/2016 | Y | EXP | 347 | 08/31/2016 | 10/28/2016 | 40 | 0 | 40 | 11/2/2015 | 11/2/2015 | 11/2/2016 | Connected |  | N
National Grid | BILLERICA | 175019 | 01821 | 350 | Solar | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 919 | 0 | 919 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 12/31/2016 | N | EXP | 1328 |  |  | 0 | 0 | 0 |  |  | 9/10/2013 | Connected |  | N
National Grid | AUBURN | 625117 | 01501 | 3.8 | Solar | 05_05_115W42 | 07/16/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | DUDLEY | 673521 | 01571 | 5.76 | Solar | 05_12_25W2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 625514 | 01440 | 0 | Battery Add-On | 05_12_51T2 | 07/17/2024 | 10/11/2024 | 60 | 50 | 10 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | FALL RIVER | 558936 | 02724 | 240 | Solar | 05_14_3J4 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/29/2023 | 6/12/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SAUGUS | 279685 | 01906 | 10 | Solar | 05_14_59L1 | 02/24/2020 | 02/25/2020 | 0 | 0 | 0 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2020 |  | 2/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2020 | Connected |  | N
National Grid | HAMILTON | 658010 | 01982 | 7.6 | Solar | 05_14_92L6 | 12/03/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 12/03/2024 | 8/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 729908 | 01852 | 5.76 | Solar | 05_01_26W1 | 10/29/2025 | 12/01/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 176931 | 01810 | 22.8 | Solar | 05_01_412L4 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 | 01/28/2016 | 01/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 4/2/2017 | N | EXP | 422 |  |  | 0 | 0 | 0 | 11/7/2016 | 11/7/2016 | 11/17/2016 | Connected |  | N
National Grid | METHUEN | 175020 | 01844 | 150 | Solar | 05_01_602W2 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 342 | 0 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2013 |  | 6/3/2013 | N | EXP | 21 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 640702 | 01821 | 5.8 | Solar | 05_05_115W42 | 09/17/2024 | 10/15/2024 | 5 | 2 | 3 | 10/16/2024 | 10/16/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | Y
National Grid | AUBURN | 681135 | 01501 | 17.1 | Solar | 05_12_25W2 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | DUDLEY | 641444 | 01571 | 8.775 | Solar | 05_12_51T2 | 09/19/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 | 10/22/2024 | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 10/25/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 10/30/2024 |  | 11/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 735290 | 01440 | 17.6 | Solar | 05_14_3J4 | 11/24/2025 | 12/01/2025 | 4 | 0 | 4 | 12/02/2025 | 12/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 301740 | 02724 | 15.2 | Solar | 05_14_59L1 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 |  | 5/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2021 | Connected |  | N
National Grid | MELROSE | 559307 | 02176 | 240 | Solar | 05_14_74L1 | 11/17/2023 | 12/08/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 11/17/2023 | 4/17/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ESSEX | 662600 | 01929 | 7.6 | Solar | 05_14_92L6 | 12/26/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | LOWELL | 739680 | 01852 | 10 | Solar | 05_01_26W1 | 12/11/2025 | 12/15/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ANDOVER | 176959 | 01810 | 9 | Solar | 05_01_412L4 | 07/16/2016 | 07/16/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 07/16/2016 | 7/23/2017 | Y | EXP | 362 | 03/24/2017 | 05/04/2017 | 28 | 0 | 28 | 6/27/2017 | 6/27/2017 | 6/27/2017 | Connected |  | N
National Grid | METHUEN | 175067 | 01844 | 675 | Solar | 05_01_602W2 | 03/28/2013 | 03/28/2013 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2013 | 06/03/2013 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2013 | 03/28/2013 | 2/3/2014 | Y | STD | 94 | 10/09/2014 | 12/10/2014 | 41 | 0 | 41 | 12/23/2014 | 12/23/2014 | 12/23/2014 | Connected |  | N
National Grid | BILLERICA | 644030 | 01821 | 5.28 | Solar | 05_05_115W42 | 10/01/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | AUBURN | 685291 | 01501 | 15.2 | Solar | 05_12_25W2 | 04/21/2025 | 05/12/2025 | 14 | 10 | 4 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | DUDLEY | 643245 | 01571 | 7.6 | Solar | 05_12_51T2 | 09/26/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 38 | 15 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 1/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | HUBBARDSTON | 397015 | 01452 | 200 | Solar | 05_14_3J4 | 11/24/2021 | 12/06/2021 | 7 | 0 | 7 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  | 6/2/2023 | N | STD | 65 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N
National Grid | FALL RIVER | 306442 | 02724 | 0 | Solar | 05_14_59L1 | 08/12/2020 | 09/14/2020 | 21 | 21 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/12/2020 | 9/14/2021 | Y | EXP | 365 | 01/05/2021 | 01/19/2021 | 14 | 0 | 14 |  |  | 3/2/2021 | Connected |  | N
National Grid | MELROSE | 559191 | 02176 | 240 | Solar | 05_14_74L1 | 11/03/2023 | 11/21/2023 | 12 | 0 | 12 | 11/22/2023 | 11/22/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 11/03/2023 | 4/16/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ESSEX | 663221 | 01929 | 7.6 | Solar | 05_14_92L6 | 12/31/2024 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LOWELL | 742988 | 01852 | 5.76 | Solar | 05_01_26W1 | 01/02/2026 | 01/05/2026 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 176996 | 01810 | 3.8 | Solar | 05_01_412L4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175102 | 01844 | 1000 | Solar | 05_01_602W2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 01/14/2013 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 11/02/2012 | 4/1/2014 | Y | STD | 319 | 03/21/2014 | 04/29/2014 | 26 | 0 | 26 | 6/13/2014 | 6/13/2014 | 6/13/2014 | Connected |  | N
National Grid | BILLERICA | 645420 | 01821 | 5.76 | Solar | 05_05_115W42 | 10/31/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | AUBURN | 689325 | 01501 | 20 | Solar | 05_12_25W2 | 05/06/2025 | 05/16/2025 | 7 | 2 | 5 | 05/19/2025 | 05/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | DUDLEY | 644917 | 01571 | 6 | Solar | 05_12_51T2 | 10/07/2024 | 10/28/2024 | 10 | 6 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/07/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | GARDNER | 174366 | 01440 | 45.6 | Solar | 05_14_3J40 | 05/21/2012 | 05/21/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2012 |  | 8/1/2012 | N | EXP | 2 |  |  | 0 | 0 | 0 | 10/1/2012 | 10/1/2012 | 10/19/2012 | Connected |  | N
National Grid | FALL RIVER | 308036 | 02724 | 0 | Battery Add-On | 05_14_59L1 | 09/30/2020 | 10/16/2020 | 11 | 9 | 2 | 10/19/2020 | 10/19/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 4/15/2022 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N
National Grid | SAUGUS | 539516 | 01906 | 10 | Solar | 05_14_74L1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 714061 | 01982 | 7.6 | Solar | 05_14_92L6 | 08/29/2025 | 10/23/2025 | 5 | 0 | 5 | 11/04/2025 | 11/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 175987 | 01810 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177938 | 01810 | 96 | Solar | 05_01_412L4 | 06/26/2017 | 06/26/2017 | 28 | 27 | 1 | 08/07/2017 | 08/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2017 |  | 7/2/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N
National Grid | METHUEN | 175302 | 01844 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 179 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 645390 | 01821 | 5.76 | Solar | 05_05_115W42 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/07/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | AUBURN | 174478 | 01501 | 164 | Solar | 05_12_25W3 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 6/27/2012 | Connected |  | N
National Grid | DUDLEY | 652283 | 01571 | 10 | Solar | 05_12_51T2 | 11/14/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 174644 | 01473 | 18 | Solar | 05_14_3J40 | 12/17/2013 | 12/17/2013 | 5 | 0 | 5 | 12/27/2013 | 12/27/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2014 |  | 2/28/2014 | N | EXP | 57 |  |  | 0 | 0 | 0 | 1/13/2014 | 1/13/2014 | 4/25/2014 | Connected |  | N
National Grid | FALL RIVER | 309991 | 02724 | 9.6 | Solar | 05_14_59L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2021 | Connected |  | N
National Grid | SAUGUS | 551550 | 01906 | 12 | Solar | 05_14_74L1 | 09/05/2023 |  | 110 | 53 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 686883 | 01982 | 12 | Solar | 05_14_9J1 | 04/30/2025 | 07/21/2025 | 54 | 50 | 4 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 175986 | 01810 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178095 | 01810 | 7.6 | Solar | 05_01_412L4 | 07/10/2017 | 07/19/2017 | 7 | 6 | 1 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/15/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | Connected |  | N
National Grid | METHUEN | 175301 | 01844 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 179 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 653947 | 01824 | 5.76 | Solar | 05_05_115W42 | 11/15/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | AUBURN | 177207 | 01501 | 259.8 | Solar | 05_12_25W3 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 652513 | 01571 | 13.05 | Solar | 05_12_51T2 | 11/13/2024 | 12/05/2024 | 1 | 0 | 1 | 12/06/2024 | 12/06/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WESTMINSTER | 479312 | 01473 | 15.2 | Solar | 05_14_3J41 | 11/21/2022 | 11/23/2022 | 2 | 0 | 2 | 11/25/2022 | 11/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | FALL RIVER | 397084 | 02724 | 1375 | Solar | 05_14_59L1 | 03/15/2022 | 02/08/2023 | 57 | 48 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2022 | 06/30/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 552256 | 01906 | 0 | Solar | 05_14_74L1 | 08/30/2023 | 09/08/2023 | 6 | 4 | 2 | 09/11/2023 | 09/11/2023 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 175760 | 01982 | 75 | Solar | 05_14_9J1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 04/28/2015 | 35 | 0 | 35 | 6/2/2015 | 6/2/2015 | 6/2/2015 | Connected |  | N
National Grid | ANDOVER | 175985 | 01810 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/30/2015 | N | STD | 412 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 178192 | 01876 | 3630 | Solar | 05_01_412L4 | 01/02/2018 | 02/23/2018 | 35 | 9 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 04/02/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2020 | 01/02/2018 | 6/28/2024 | Y | STD | 45 | 07/07/2023 | 09/21/2023 | 77 | 0 | 77 |  |  | 6/10/2024 | Connected |  | N
National Grid | METHUEN | 175300 | 01844 | 4875 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 6/7/2021 | Y | STD | 1373 | 10/28/2020 | 03/26/2021 | 149 | 0 | 149 |  |  | 6/4/2021 | Connected |  | N
National Grid | CHELMSFORD | 660383 | 01824 | 3.8 | Solar | 05_05_115W42 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/17/2024 | 2/25/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | AUBURN | 178123 | 01501 | 300 | Natural Gas | 05_12_25W3 | 05/12/2017 | 05/12/2017 | 22 | 19 | 3 | 06/14/2017 | 06/14/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2017 |  | 9/7/2018 | N | EXP | 423 |  |  | 0 | 0 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | DUDLEY | 669106 | 01571 | 10 | Solar | 05_12_51T2 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | WESTMINSTER | 577657 | 01473 | 23 | Solar | 05_14_3J44 | 12/13/2023 | 12/18/2023 | 3 | 2 | 1 | 12/19/2023 | 12/19/2023 | 83 | 28 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 408840 | 02724 | 0 | Battery Add-On | 05_14_59L1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 03/02/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 551686 | 01906 | 6.38 | Solar | 05_14_74L1 | 08/29/2023 | 08/31/2023 | 2 | 0 | 2 | 09/01/2023 | 09/01/2023 | 25 | 0 | 25 | 10/13/2023 | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 10/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 418712 | 01915 | 6 | Solar | 05_14_9J1 | 07/26/2022 | 07/28/2022 | 2 | 0 | 2 | 07/29/2022 | 07/29/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/26/2022 | 5/10/2024 | Y | EXP | 365 | 02/22/2023 | 05/10/2023 | 78 | 0 | 78 |  |  | 5/23/2023 | Connected |  | Y
National Grid | ANDOVER | 175984 | 01810 | 1000 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 9/21/2015 | N | STD | 421 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178264 | 01810 | 1250 | Solar | 05_01_412L4 | 04/18/2018 | 04/30/2018 | 8 | 8 | 0 |  |  | 39 | 14 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 | 04/18/2018 | 4/14/2025 | Y | STD | 485 | 08/20/2024 | 02/13/2025 | 178 | 178 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | METHUEN | 175333 | 01844 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 |  | 10/16/2019 | N | STD | 179 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 661562 | 01824 | 3.8 | Solar | 05_05_115W42 | 12/18/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | AUBURN | 204173 | 01540 | 259.8 | Solar | 05_12_25W3 | 12/18/2018 | 01/17/2019 | 19 | 12 | 7 | 01/18/2019 | 01/18/2019 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 678202 | 01571 | 5.76 | Solar | 05_12_51T2 | 03/17/2025 | 03/24/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 03/17/2025 | 5/29/2026 | Y | EXP | 365 | 08/19/2025 | 11/05/2025 | 79 | 0 | 79 |  |  | 11/14/2025 | Connected |  | Y
National Grid | WESTMINSTER | 646072 | 01473 | 7.6 | Solar | 05_14_3J44 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 10/10/2024 | 1/14/2026 | Y | EXP | 365 | 03/27/2025 | 05/07/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 412219 | 02724 | 0 | Battery Add-On | 05_14_59L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 571764 | 01906 | 240 | Solar | 05_14_74L1 | 11/17/2023 | 12/06/2023 | 12 | 3 | 9 | 12/07/2023 | 12/07/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 11/17/2023 | 7/10/2026 | Y | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 432583 | 01915 | 15.2 | Solar | 05_14_9J1 | 05/23/2022 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175983 | 01810 | 4875 | Solar | 05_01_26W1 | 03/20/2015 | 03/30/2015 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2015 | 04/27/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 03/20/2015 | 5/25/2022 | Y | STD | 61 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N
National Grid | ANDOVER | 178355 | 01810 | 2990 | Solar | 05_01_412L4 | 02/28/2018 | 02/28/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2018 | 06/15/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175332 | 01844 | 1000 | Solar | 05_01_602W2 | 01/17/2015 | 03/03/2015 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/02/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2016 | 01/17/2015 | 10/16/2019 | Y | STD | 179 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 663099 | 01824 | 10 | Solar | 05_05_115W42 | 01/02/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 01/02/2025 | 3/24/2026 | Y | EXP | 365 | 04/29/2025 | 05/15/2025 | 17 | 0 | 17 |  |  | 6/6/2025 | Connected |  | N
National Grid | AUBURN | 253386 | 01501 | 262.5 | Natural Gas | 05_12_25W3 | 09/24/2019 | 11/04/2019 | 27 | 24 | 3 | 11/05/2019 | 11/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 689316 | 01571 | 15.2 | Solar | 05_12_51T2 | 05/02/2025 | 05/22/2025 | 14 | 11 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | WESTMINSTER | 662149 | 01473 | 5.76 | Solar | 05_14_3J45 | 12/23/2024 | 01/15/2025 | 1 | 0 | 1 | 01/14/2025 | 01/14/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 12/23/2024 | 2/26/2026 | Y | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 457561 | 02724 | 9.6 | Solar | 05_14_59L1 | 09/09/2022 | 09/27/2022 | 13 | 12 | 1 | 09/28/2022 | 09/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y
National Grid | SAUGUS | 591226 | 01906 | 6 | Solar | 05_14_74L1 | 08/22/2024 | 08/27/2024 | 3 | 0 | 3 | 08/28/2024 | 08/28/2024 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAMILTON | 437921 | 01982 | 15.2 | Solar | 05_14_9J1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | ANDOVER | 176341 | 01810 | 8.6 | Solar | 05_01_26W1 | 02/25/2015 | 02/25/2015 | 9 | 6 | 3 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/18/2016 | 03/14/2016 | 17 | 0 | 17 | 3/17/2015 | 3/17/2015 | 5/5/2016 | Connected |  | N
National Grid | ANDOVER | 178442 | 01810 | 9 | Solar | 05_01_412L4 | 04/02/2018 | 04/10/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 | 04/02/2018 | 5/6/2019 | Y | EXP | 333 | 03/30/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 5/2/2019 | Connected |  | N
National Grid | METHUEN | 175367 | 01844 | 960 | Solar | 05_01_602W2 | 11/17/2014 | 11/17/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/17/2014 | 3/31/2017 | Y | STD | 73 | 03/29/2017 | 03/27/2017 | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | CHELMSFORD | 700098 | 01824 | 9.5 | Solar | 05_05_115W44 | 06/20/2025 | 09/22/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 31 | 13 | 18 | 12/04/2025 | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/03/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 302630 | 01501 | 262.5 | Natural Gas | 05_12_25W3 | 08/05/2020 | 09/30/2020 | 39 | 28 | 11 | 10/01/2020 | 10/01/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2020 |  | 2/21/2022 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | N
National Grid | DUDLEY | 691103 | 01571 | 15.2 | Solar | 05_12_51T2 | 06/02/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | HUBBARDSTON | 488581 | 01452 | 300 | Solar | 05_14_3J5 | 02/24/2023 |  | 302 | 204 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 501458 | 02721 | 15.2 | Solar | 05_14_59L1 | 02/13/2023 | 02/14/2023 | 1 | 0 | 1 | 02/15/2023 | 02/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 593838 | 01906 | 15.2 | Solar | 05_14_74L1 | 03/01/2024 | 04/15/2024 | 28 | 25 | 3 | 04/16/2024 | 04/16/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N
National Grid | HAMILTON | 176716 | 01982 | 10 | Solar | 05_14_9J3 | 01/11/2016 | 01/11/2016 | 1 | 1 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/17/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/7/2016 | 3/7/2016 | 8/11/2016 | Connected |  | N
National Grid | LOWELL | 177031 | 01852 | 3.8 | Solar | 05_01_26W1 | 03/20/2017 | 03/20/2017 | 6 | 5 | 1 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 |  | 3/25/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | ANDOVER | 195056 | 01810 | 7.6 | Solar | 05_01_412L4 | 09/04/2018 | 10/26/2018 | 21 | 21 | 0 | 10/29/2018 | 10/29/2018 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 09/04/2018 | 11/8/2019 | Y | EXP | 359 | 07/11/2019 | 09/16/2019 | 67 | 0 | 67 |  |  | 10/9/2019 | Connected |  | N
National Grid | METHUEN | 175378 | 01844 | 278.4 | Solar | 05_01_602W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2014 |  | 11/28/2014 | N | EXP | 121 |  |  | 0 | 0 | 0 | 10/16/2014 | 10/16/2014 | 12/31/2014 | Connected |  | N
National Grid | CHELMSFORD | 174492 | 01824 | 120 | Solar | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 3/2/2012 | N | EXP | 234 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/2/2012 | Connected |  | N
National Grid | AUBURN | 357487 | 01501 | 240 | Solar | 05_12_25W3 | 05/14/2021 | 06/23/2021 | 26 | 16 | 10 | 06/24/2021 | 06/24/2021 | 343 | 319 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 700744 | 01571 | 0 | Solar | 05_12_51T2 | 06/24/2025 | 06/30/2025 | 4 | 0 | 4 | 07/01/2025 | 07/01/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 8/15/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 11/21/2025 | Connected |  | N
National Grid | GARDNER | 707495 | 01440 | 10 | Solar | 05_14_3J7 | 07/25/2025 | 09/12/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 | 07/25/2025 | 10/24/2026 | Y | EXP | 365 | 12/18/2025 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 504001 | 02721 | 0 | Solar | 05_14_59L1 | 02/24/2023 | 02/27/2023 | 1 | 0 | 1 | 02/28/2023 | 02/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2023 | 02/24/2023 | 7/27/2024 | Y | EXP | 365 | 08/29/2023 | 10/04/2023 | 37 | 0 | 37 |  |  | 11/20/2023 | Connected |  | N
National Grid | SAUGUS | 596597 | 01906 | 6 | Solar | 05_14_74L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/18/2024 | 4/29/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/7/2024 | Connected |  | N
National Grid | HAMILTON | 178384 | 01982 | 3.8 | Solar | 05_14_9J3 | 01/15/2018 | 01/15/2018 | 32 | 3 | 29 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 1/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177489 | 01852 | 288 | Solar | 05_01_26W1 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 |  | 10/1/2017 | N | EXP | 313 |  |  | 0 | 0 | 0 | 6/14/2017 | 6/14/2017 | 6/14/2017 | Connected |  | N
National Grid | ANDOVER | 268311 | 01810 | 10 | Solar | 05_01_412L4 | 01/17/2020 | 02/10/2020 | 1 | 1 | 0 | 02/11/2020 | 02/11/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  | 2/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175403 | 01844 | 960 | Solar | 05_01_602W2 | 11/21/2014 | 11/21/2014 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/13/2016 | 09/19/2016 | 87 | 0 | 87 | 1/17/2017 | 11/21/2014 | 4/10/2017 | Y | STD | 83 | 02/10/2017 | 09/05/2017 | 142 | 0 | 142 | 4/21/2017 | 4/21/2017 | 5/5/2017 | Connected |  | N
National Grid | CHELMSFORD | 174491 | 01824 | 82 | Solar | 05_05_115W44 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2011 |  | 2/28/2012 | N | EXP | 231 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 2/28/2012 | Connected |  | N
National Grid | AUBURN | 419316 | 01501 | 240 | Solar | 05_12_25W3 | 05/26/2022 | 06/27/2022 | 20 | 14 | 6 | 06/28/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | DUDLEY | 708571 | 01571 | 9.86 | Solar | 05_12_51T2 | 07/30/2025 | 09/15/2025 | 32 | 29 | 3 | 09/16/2025 | 09/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | HUBBARDSTON | 647340 | 01452 | 8.12 | Solar | 05_14_3J7 | 10/21/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | FALL RIVER | 512029 | 02721 | 15.2 | Solar | 05_14_59L1 | 03/16/2023 | 03/20/2023 | 2 | 0 | 2 | 03/21/2023 | 03/21/2023 | 59 | 39 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2024 | Connected |  | N
National Grid | SAUGUS | 597545 | 01906 | 7.6 | Solar | 05_14_74L1 | 03/21/2024 | 04/30/2024 | 28 | 25 | 3 | 05/01/2024 | 05/01/2024 | 10 | 3 | 7 | 05/17/2024 | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WENHAM | 249645 | 01984 | 3.8 | Solar | 05_14_9J3 | 08/30/2019 | 09/04/2019 | 1 | 0 | 1 | 09/05/2019 | 09/05/2019 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 08/30/2019 | 10/13/2021 | Y | EXP | 365 | 08/04/2020 | 08/21/2020 | 17 | 0 | 17 |  |  | 11/18/2020 | Connected |  | N
National Grid | LOWELL | 177645 | 01852 | 10 | Solar | 05_01_26W1 | 09/25/2017 | 11/13/2017 | 27 | 27 | 0 | 11/13/2017 | 11/13/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/1/2018 | N | EXP | 321 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | ANDOVER | 299874 | 01810 | 9.36 | Solar | 05_01_412L4 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | METHUEN | 175417 | 01844 | 16 | Solar | 05_01_602W2 | 07/10/2014 | 07/10/2014 | 7 | 0 | 7 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2014 |  | 9/30/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 8/12/2014 | 8/12/2014 | 10/14/2014 | Connected |  | N
National Grid | CHELMSFORD | 174711 | 01824 | 485 | Solar | 05_05_115W44 | 06/21/2013 | 06/21/2013 | 6 | 0 | 6 | 07/02/2013 | 07/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2013 |  | 11/1/2013 | N | EXP | 113 |  |  | 0 | 0 | 0 | 12/31/2013 | 12/31/2013 | 12/31/2013 | Connected |  | N
National Grid | AUBURN | 476349 | 01501 | 240 | Solar | 05_12_25W3 | 02/23/2023 | 08/22/2023 | 36 | 26 | 10 | 08/23/2023 | 08/23/2023 | 179 | 93 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 714207 | 01571 | 15.04 | Solar | 05_12_51T2 | 08/22/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | HUBBARDSTON | 647453 | 01452 | 6.67 | Solar | 05_14_3J7 | 10/16/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 541519 | 02723 | 9.57 | Solar | 05_14_59L1 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 11/22/2024 | Y | EXP | 365 | 03/26/2024 | 07/23/2024 | 120 | 0 | 120 |  |  | 7/25/2024 | Connected |  | N
National Grid | SAUGUS | 600465 | 01906 | 10 | Solar | 05_14_74L1 | 04/04/2024 | 04/16/2024 | 8 | 7 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 5/25/2025 | Y | EXP | 365 | 08/01/2024 | 01/02/2025 | 155 | 0 | 155 |  |  | 4/1/2025 | Connected |  | N
National Grid | BEVERLY | 393377 | 01915 | 9.772 | Solar | 05_14_9J3 | 11/04/2021 | 11/16/2021 | 8 | 5 | 3 | 11/17/2021 | 11/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y
National Grid | LOWELL | 178467 | 01852 | 299.7 | Solar | 05_01_26W1 | 01/23/2018 | 02/22/2018 | 2 | 2 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 2/28/2020 | N | EXP | 518 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N
National Grid | ANDOVER | 320511 | 01810 | 9.8 | Solar | 05_01_412L4 | 11/04/2020 | 11/09/2020 | 2 | 0 | 2 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2020 |  | 1/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176044 | 01844 | 630 | Solar | 05_01_602W2 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 175053 | 01824 | 80.25 | Solar | 05_05_115W44 | 08/13/2012 | 08/13/2012 | 8 | 3 | 5 | 08/24/2012 | 08/24/2012 | 276 | 0 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 488519 | 01501 | 480 | Solar | 05_12_25W3 | 02/24/2023 | 06/28/2023 | 85 | 74 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 703588 | 01571 | 0 | Solar | 05_12_51T3 | 07/08/2025 | 07/14/2025 | 3 | 1 | 2 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 648266 | 01473 | 5.76 | Solar | 05_14_3J7 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/8/2026 | Y | EXP | 365 | 03/04/2025 | 05/14/2025 | 72 | 0 | 72 |  |  | 5/23/2025 | Connected |  | N
National Grid | FALL RIVER | 564915 | 02721 | 0 | Solar | 05_14_59L1 | 10/20/2023 | 10/23/2023 | 1 | 0 | 1 | 10/24/2023 | 10/24/2023 | 90 | 78 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 10/20/2023 | 3/20/2025 | Y | EXP | 365 | 07/06/2024 | 09/03/2024 | 60 | 0 | 60 |  |  | 9/10/2024 | Connected |  | N
National Grid | SAUGUS | 605469 | 01906 | 11.4 | Solar | 05_14_74L1 | 04/23/2024 | 04/30/2024 | 2 | 0 | 2 | 05/01/2024 | 05/01/2024 | 12 | 5 | 7 | 06/03/2024 | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 6/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 719817 | 01966 | 3.8 | Solar | 05_12_5C3 | 09/17/2025 | 11/04/2025 | 4 | 0 | 4 | 11/05/2025 | 11/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 194297 | 01852 | 250 | Solar | 05_01_26W1 | 08/24/2018 | 08/28/2018 | 1 | 0 | 1 | 08/29/2018 | 08/29/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 375104 | 01810 | 9.8 | Solar | 05_01_412L4 | 09/28/2021 | 12/16/2021 | 4 | 0 | 4 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2022 | Connected |  | N
National Grid | METHUEN | 176043 | 01844 | 1000 | Solar | 05_01_602W2 | 08/14/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2015 | 09/15/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 08/14/2015 | 2/24/2020 | Y | STD | 1225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 175291 | 02148 | 36 | Solar | 05_05_115W44 | 11/06/2014 | 11/06/2014 | 5 | 2 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 2/27/2015 | N | EXP | 99 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/16/2015 | Connected |  | N
National Grid | AUBURN | 657521 | 01501 | 7.6 | Solar | 05_12_25W4 | 11/27/2024 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DUDLEY | 738933 | 01571 | 10 | Solar | 05_12_51T3 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 653837 | 01473 | 3.8 | Solar | 05_14_3J7 | 11/13/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | FALL RIVER | 608981 | 02721 | 23 | Battery Add-On | 05_14_59L1 | 05/06/2024 | 05/07/2024 | 1 | 0 | 1 | 05/08/2024 | 05/08/2024 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | MELROSE | 609378 | 02176 | 5.76 | Solar | 05_14_74L1 | 05/07/2024 | 05/14/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | GLOUCESTER | 176869 | 01930 | 10 | Solar | 05_12_5C3 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 |  | 3/7/2017 | N | EXP | 323 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 |  | Withdrawn |  | Y
National Grid | LOWELL | 205077 | 01852 | 7.6 | Solar | 05_01_26W1 | 02/07/2019 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 391345 | 01810 | 7.6 | Solar | 05_01_412L4 | 11/11/2021 | 12/28/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 11/11/2021 | 8/26/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | METHUEN | 176306 | 01844 | 15.2 | Solar | 05_01_602W2 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 | 03/04/2015 | 03/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2015 |  | 7/31/2015 | N | EXP | 148 |  |  | 0 | 0 | 0 | 5/12/2017 | 5/12/2017 | 5/12/2017 | Connected |  | N
National Grid | MALDEN | 176473 | 02148 | 72 | Solar | 05_05_115W44 | 03/22/2016 | 03/22/2016 | 3 | 3 | 0 | 03/28/2016 | 03/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2016 |  | 9/30/2016 | N | EXP | 143 |  |  | 0 | 0 | 0 | 9/21/2016 | 9/21/2016 | 10/4/2016 | Connected |  | N
National Grid | AUBURN | 728422 | 01501 | 5.44 | Solar | 05_12_25W4 | 10/22/2025 | 10/27/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/22/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | DUDLEY | 175636 | 01571 | 45 | Solar | 05_12_51T3 | 10/19/2014 | 10/19/2014 | 6 | 2 | 4 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 1/15/2015 | 1/15/2015 | 2/13/2015 | Connected |  | N
National Grid | HUBBARDSTON | 662094 | 01452 | 6.46 | Solar | 05_14_3J7 | 12/20/2024 | 03/17/2025 | 53 | 49 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 627752 | 02721 | 23.725 | Solar | 05_14_59L1 | 08/23/2024 | 08/27/2024 | 2 | 0 | 2 | 08/28/2024 | 08/28/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | MELROSE | 610663 | 02176 | 10 | Solar | 05_14_74L1 | 05/14/2024 | 05/29/2024 | 1 | 0 | 1 | 05/30/2024 | 05/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 05/14/2024 | 12/31/2025 | Y | EXP | 365 | 08/28/2025 | 11/21/2025 | 86 | 0 | 86 |  |  | 11/24/2025 | Connected |  | N
National Grid | GLOUCESTER | 177760 | 01930 | 468 | Solar | 05_12_5C3 | 08/02/2017 | 08/02/2017 | 95 | 95 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2017 | 01/25/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 208525 | 01852 | 2340 | Solar | 05_01_26W1 | 02/13/2019 |  | 176 | 51 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 440471 | 01810 | 15.2 | Solar | 05_01_412L4 | 06/27/2022 | 06/30/2022 | 3 | 0 | 3 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176398 | 01844 | 10 | Solar | 05_01_602W2 | 03/10/2016 | 03/10/2016 | 1 | 1 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2016 |  | 3/16/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 | 6/13/2016 | Connected |  | N
National Grid | MALDEN | 387395 | 02148 | 0 | Other | 05_05_115W44 | 10/25/2021 | 01/04/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 176158 | 01501 | 15.2 | Solar | 05_12_25W4 | 01/29/2015 | 01/29/2015 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 175788 | 01571 | 200 | Solar | 05_12_51T3 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 | 09/18/2015 | 09/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/17/2015 | 9/23/2016 | Y | EXP | 366 |  |  | 0 | 0 | 0 | 4/15/2016 | 4/15/2016 | 5/3/2016 | Connected |  | N
National Grid | WESTMINSTER | 666688 | 01473 | 3.8 | Solar | 05_14_3J7 | 01/20/2025 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | FALL RIVER | 631986 | 02723 | 0 | Solar | 05_14_59L1 | 08/12/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 101 | 77 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | MELROSE | 611903 | 02176 | 7.6 | Solar | 05_14_74L1 | 07/04/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 563209 | 01930 | 10 | Solar | 05_12_5C3 | 12/06/2023 | 03/07/2024 | 52 | 50 | 2 | 03/08/2024 | 03/08/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 |  | 5/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | LOWELL | 223683 | 01852 | 10 | Solar | 05_01_26W1 | 04/30/2019 | 05/07/2019 | 4 | 0 | 4 | 05/08/2019 | 05/08/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2019 | 04/30/2019 | 8/16/2022 | Y | EXP | 11 | 09/23/2020 | 11/18/2020 | 56 | 0 | 56 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 443970 | 01810 | 0 | Other | 05_01_412L4 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176879 | 01844 | 266.4 | Solar | 05_01_602W2 | 05/04/2016 | 05/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2016 | 06/28/2016 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 05/04/2016 | 12/29/2017 | Y | STD | 373 | 05/01/2017 | 10/04/2017 | 109 | 0 | 109 | 1/11/2018 | 1/11/2018 | 12/11/2017 | Connected |  | N
National Grid | MALDEN | 501029 | 02148 | 100 | Solar | 05_05_115W44 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 177407 | 01501 | 56 | Solar | 05_12_25W4 | 09/09/2016 | 09/09/2016 | 17 | 17 | 0 | 10/04/2016 | 10/04/2016 | 60 | 60 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 7/31/2018 | N | EXP | 573 |  |  | 0 | 0 | 0 |  |  | 12/12/2018 | Connected |  | N
National Grid | WEBSTER | 176028 | 01570 | 30.25 | Solar | 05_12_51T3 | 06/16/2015 | 06/16/2015 | 4 | 4 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/21/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | HUBBARDSTON | 669223 | 01452 | 6 | Solar | 05_14_3J7 | 01/31/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 662547 | 02721 | 7.6 | Solar | 05_14_59L1 | 01/02/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | MELROSE | 617697 | 02176 | 10 | Solar | 05_14_74L1 | 06/13/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 32 | 21 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 683574 | 01930 | 16.53 | Solar | 05_12_5C3 | 04/08/2025 | 04/14/2025 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | LOWELL | 247021 | 01852 | 10 | Solar | 05_01_26W1 | 08/19/2019 | 08/26/2019 | 4 | 3 | 1 | 08/27/2019 | 08/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2019 |  | 11/25/2019 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  | 10/23/2019 | Connected |  | N
National Grid | TEWKSBURY | 445324 | 01876 | 7.6 | Solar | 05_01_412L4 | 09/27/2022 | 10/12/2022 | 10 | 7 | 3 | 10/13/2022 | 10/13/2022 | 18 | 0 | 18 | 11/29/2022 | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  | 04/24/2023 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 5/15/2023 |  | 10/25/2024 | N | EXP | 365 | 04/10/2024 | 06/13/2024 | 65 | 0 | 65 |  |  | 7/8/2024 | Connected |  | N
National Grid | METHUEN | 176901 | 01844 | 6 | Solar | 05_01_602W2 | 01/27/2016 | 01/27/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/1/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 4/11/2016 | Connected |  | N
National Grid | MALDEN | 544185 | 02148 | 18.85 | Solar | 05_05_115W44 | 08/04/2023 | 08/08/2023 | 2 | 0 | 2 | 08/09/2023 | 08/09/2023 | 161 | 28 | 133 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 191843 | 01501 | 50 | Solar | 05_12_25W4 | 08/21/2018 | 09/17/2018 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2019 |  | 11/29/2019 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | DUDLEY | 176270 | 01571 | 17.42 | Solar | 05_12_51T3 | 02/18/2015 | 02/18/2015 | 4 | 0 | 4 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/30/2015 | Connected |  | N
National Grid | WESTMINSTER | 700371 | 01473 | 11.02 | Solar | 05_14_3J7 | 06/23/2025 | 08/13/2025 | 5 | 3 | 2 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 664232 | 02721 | 0 | Battery Add-On | 05_14_59L1 | 01/07/2025 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 619049 | 02176 | 3.8 | Solar | 05_14_74L1 | 06/19/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 67 | 52 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 06/19/2024 | 1/1/2026 | Y | EXP | 365 | 12/11/2024 | 04/04/2025 | 115 | 26 | 89 |  |  | 8/29/2025 | Connected |  | N
National Grid | GLOUCESTER | 745544 | 01930 | 11.4 | Solar | 05_12_67J1 | 01/15/2026 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LOWELL | 248514 | 01852 | 10 | Solar | 05_01_26W1 | 09/04/2019 | 09/05/2019 | 0 | 0 | 0 | 09/06/2019 | 09/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 09/04/2019 | 5/11/2020 | Y | EXP | 237 | 12/21/2019 | 01/24/2020 | 34 | 0 | 34 |  |  | 2/10/2020 | Connected |  | N
National Grid | ANDOVER | 484394 | 01810 | 7.6 | Solar | 05_01_412L4 | 12/09/2022 | 12/14/2022 | 3 | 1 | 2 | 12/15/2022 | 12/15/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 177318 | 01844 | 2000 | Solar | 05_01_602W2 | 02/14/2017 | 02/14/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2017 | 03/27/2017 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/20/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 662528 | 02155 | 7.6 | Solar | 05_05_115W44 | 12/26/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/26/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | AUBURN | 206824 | 01501 | 0 | Solar | 05_12_25W4 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | DUDLEY | 176530 | 01571 | 108 | Solar | 05_12_51T3 | 12/16/2015 | 12/16/2015 | 0 | 0 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/22/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | HUBBARDSTON | 557014 | 01452 | 200 | Solar | 05_14_3L2 | 09/21/2023 | 10/06/2023 | 11 | 2 | 9 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/21/2023 | 7/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | FALL RIVER | 678283 | 02723 | 5.76 | Solar | 05_14_59L1 | 03/19/2025 | 03/28/2025 | 8 | 3 | 5 | 03/31/2025 | 03/31/2025 | 116 | 94 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 630260 | 02176 | 10 | Solar | 05_14_74L1 | 08/05/2024 | 08/21/2024 | 9 | 6 | 3 | 08/22/2024 | 08/22/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/05/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | GLOUCESTER | 331636 | 01930 | 10 | Solar | 05_12_67J1 | 01/08/2021 | 01/12/2021 | 2 | 2 | 0 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/08/2021 | 1/11/2022 | Y | EXP | 365 | 03/25/2021 | 06/24/2021 | 91 | 0 | 91 |  |  | 6/30/2021 | Connected |  | N
National Grid | LOWELL | 338558 | 01852 | 7.6 | Solar | 05_01_26W1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/12/2021 | 1/20/2023 | Y | EXP | 365 | 12/15/2021 | 01/19/2022 | 36 | 0 | 36 |  |  | 1/25/2022 | Connected |  | N
National Grid | TEWKSBURY | 517480 | 01876 | 14.79 | Solar | 05_01_412L4 | 04/06/2023 | 04/10/2023 | 2 | 0 | 2 | 04/11/2023 | 04/11/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 178021 | 01844 | 900 | Solar | 05_01_602W2 | 08/29/2017 | 08/29/2017 | 8 | 8 | 0 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/5/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 176354 | 02155 | 38 | Solar | 05_05_115W45 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/18/2015 | 05/18/2015 | 386 | 0 | 386 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 447514 | 01501 | 15.66 | Solar | 05_12_25W4 | 08/25/2022 | 09/13/2022 | 13 | 12 | 1 | 09/14/2022 | 09/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2022 |  | 10/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2023 | Connected |  | N
National Grid | DUDLEY | 177374 | 01571 | 345 | Solar | 05_12_51T3 | 09/08/2016 | 09/08/2016 | 2 | 2 | 0 | 09/12/2016 | 09/12/2016 | 361 | 2 | 359 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 6/29/2018 | N | EXP | 64 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 674259 | 01452 | 220 | Solar | 05_14_3L2 | 02/28/2025 | 03/14/2025 | 10 | 0 | 10 | 03/17/2025 | 03/17/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 | 02/28/2025 | 4/13/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WESTPORT | 681004 | 02790 | 13.8 | Solar | 05_14_59L1 | 03/28/2025 | 04/09/2025 | 3 | 0 | 3 | 04/17/2025 | 04/17/2025 | 22 | 0 | 22 | 06/17/2025 | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 07/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 7/28/2025 | 03/28/2025 | 7/31/2026 | Y | EXP | 365 | 11/14/2025 | 11/21/2025 | 8 | 0 | 8 |  |  | 11/24/2025 | Connected |  | N
National Grid | MELROSE | 631163 | 02176 | 10 | Solar | 05_14_74L1 | 08/08/2024 | 08/20/2024 | 4 | 0 | 4 | 08/21/2024 | 08/21/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/08/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | GLOUCESTER | 331978 | 01930 | 7.6 | Solar | 05_12_67J1 | 12/16/2020 | 01/08/2021 | 15 | 12 | 3 | 01/11/2021 | 01/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N
National Grid | LOWELL | 438906 | 01852 | 9.86 | Solar | 05_01_26W1 | 07/22/2022 | 07/26/2022 | 2 | 2 | 0 | 07/27/2022 | 07/27/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 | 07/22/2022 | 9/1/2023 | Y | EXP | 365 | 10/20/2022 | 03/08/2023 | 140 | 0 | 140 |  |  | 3/9/2023 | Connected |  | N
National Grid | TEWKSBURY | 516711 | 01876 | 9.28 | Solar | 05_01_412L4 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/29/2023 | 12/7/2024 | Y | EXP | 365 | 03/01/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 5/2/2024 | Connected |  | N
National Grid | METHUEN | 178134 | 01844 | 15.2 | Solar | 05_01_602W2 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | MEDFORD | 176796 | 02155 | 216 | Solar | 05_05_115W45 | 02/25/2016 | 02/25/2016 | 1 | 1 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 | 02/25/2016 | 3/2/2017 | Y | EXP | 12 | 01/05/2017 | 01/30/2017 | 16 | 0 | 16 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | AUBURN | 475633 | 01501 | 50 | Solar | 05_12_25W4 | 11/10/2022 | 11/23/2022 | 8 | 0 | 8 | 11/25/2022 | 11/25/2022 | 44 | 24 | 20 | 02/02/2023 | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/22/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 11/29/2024 | N | EXP | 365 | 10/21/2023 | 12/05/2023 | 46 | 0 | 46 |  |  | 8/23/2024 | Connected |  | N
National Grid | DUDLEY | 177959 | 01571 | 20 | Solar | 05_12_51T3 | 10/24/2017 | 10/24/2017 | 2 | 0 | 2 | 11/06/2017 | 11/06/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/31/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | WESTMINSTER | 734040 | 01473 | 18.24 | Solar | 05_14_3L2 | 11/14/2025 | 11/20/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 53 | 35 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 681911 | 02723 | 15.2 | Solar | 05_14_59L1 | 04/01/2025 | 04/10/2025 | 8 | 3 | 5 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | MELROSE | 632110 | 02176 | 10 | Solar | 05_14_74L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/21/2024 | 10/29/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | GLOUCESTER | 502077 | 01930 | 15.744 | Solar | 05_12_67J1 | 03/06/2023 | 03/14/2023 | 6 | 5 | 1 | 03/15/2023 | 03/15/2023 | 30 | 5 | 25 | 05/12/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 6/22/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N
National Grid | LOWELL | 478360 | 01852 | 13.34 | Solar | 05_01_26W1 | 12/07/2022 | 12/14/2022 | 5 | 2 | 3 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N
National Grid | ANDOVER | 556681 | 01810 | 10 | Solar | 05_01_412L4 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 09/25/2023 | 12/20/2024 | Y | EXP | 365 | 03/06/2024 | 04/17/2024 | 43 | 0 | 43 |  |  | 5/22/2024 | Connected |  | N
National Grid | METHUEN | 178224 | 01844 | 2375 | Solar | 05_01_602W2 | 04/16/2018 | 04/16/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 177182 | 02155 | 120 | Solar | 05_05_115W45 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 | 08/12/2016 | 8/17/2017 | Y | EXP | 343 | 01/05/2017 | 05/04/2017 | 82 | 0 | 82 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | AUBURN | 491299 | 01505 | 6.48 | Solar | 05_12_25W4 | 01/20/2023 | 01/24/2023 | 2 | 0 | 2 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 | 03/28/2023 | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  | 06/27/2023 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2023 | Connected |  | N
National Grid | DUDLEY | 186691 | 01571 | 6 | Solar | 05_12_51T3 | 06/15/2018 | 06/15/2018 | 9 | 5 | 4 | 06/29/2018 | 06/29/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 5/30/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/16/2018 | Connected |  | N
National Grid | HUBBARDSTON | 424685 | 01452 | 6.09 | Solar | 05_14_3L2 | 05/13/2022 | 05/16/2022 | 1 | 0 | 1 | 05/17/2022 | 05/17/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 05/13/2022 | 8/19/2024 | Y | EXP | 365 | 04/16/2023 | 05/03/2023 | 18 | 0 | 18 |  |  | 10/12/2023 | Connected |  | N
National Grid | FALL RIVER | 686755 | 02723 | 19.14 | Solar | 05_14_59L1 | 04/22/2025 | 04/29/2025 | 5 | 0 | 5 | 04/30/2025 | 04/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | MELROSE | 644612 | 02176 | 10 | Solar | 05_14_74L1 | 10/02/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 52 | 34 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 10/02/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | GLOUCESTER | 555081 | 01930 | 10 | Solar | 05_12_67J1 | 09/15/2023 | 09/19/2023 | 3 | 2 | 1 | 09/20/2023 | 09/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2023 | 09/15/2023 | 10/26/2024 | Y | EXP | 365 | 02/16/2024 | 05/21/2024 | 96 | 0 | 96 |  |  | 8/3/2024 | Connected |  | N
National Grid | TEWKSBURY | 480883 | 01876 | 0 | Solar | 05_01_26W1 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 558380 | 01810 | 15.2 | Solar | 05_01_412L4 | 10/02/2023 | 10/23/2023 | 15 | 14 | 1 | 10/24/2023 | 10/24/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2024 | Connected |  | N
National Grid | METHUEN | 178326 | 01844 | 5000 | Solar | 05_01_602W2 | 03/26/2018 | 03/26/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/04/2018 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 177406 | 02155 | 7.6 | Solar | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 536960 | 01501 | 10 | Solar | 05_12_25W4 | 07/10/2023 | 07/11/2023 | 1 | 0 | 1 | 07/12/2023 | 07/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 396042 | 01571 | 0 | Other | 05_12_51T3 | 01/04/2022 | 02/04/2022 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 03/02/2022 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 583375 | 01452 | 10 | Solar | 05_14_3L2 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 57 | 45 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 01/26/2024 | 6/3/2025 | Y | EXP | 365 | 09/14/2024 | 11/04/2024 | 52 | 0 | 52 |  |  | 11/18/2024 | Connected |  | N
National Grid | WESTPORT | 709203 | 02790 | 22.8 | Solar | 05_14_59L1 | 08/03/2025 | 08/21/2025 | 13 | 10 | 3 | 08/22/2025 | 08/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | MELROSE | 645335 | 02176 | 3.8 | Solar | 05_14_74L1 | 10/07/2024 | 12/04/2024 | 25 | 20 | 5 | 12/05/2024 | 12/05/2024 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/07/2024 | 2/25/2026 | Y | EXP | 365 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | GLOUCESTER | 628731 | 01930 | 11.5 | Solar | 05_12_67J1 | 07/30/2024 | 09/20/2024 | 49 | 44 | 5 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | LOWELL | 514516 | 01852 | 14.79 | Solar | 05_01_26W1 | 04/07/2023 | 04/20/2023 | 8 | 7 | 1 | 04/21/2023 | 04/21/2023 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2023 |  | 9/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | ANDOVER | 527634 | 01810 | 6 | Solar | 05_01_412L4 | 10/24/2023 | 05/25/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 65 | 42 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | METHUEN | 178567 | 01844 | 4950 | Solar | 05_01_602W2 | 12/07/2017 | 01/08/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/07/2018 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 177402 | 02148 | 10 | Solar | 05_05_115W45 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 | 06/29/2016 | 7/5/2017 | Y | EXP | 352 | 05/23/2017 | 06/23/2017 | 22 | 0 | 22 | 7/17/2017 | 7/17/2017 | 7/19/2017 | Connected |  | N
National Grid | AUBURN | 613279 | 01501 | 6.825 | Solar | 05_12_25W4 | 05/28/2024 | 06/12/2024 | 1 | 0 | 1 | 06/13/2024 | 06/13/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 | 05/28/2024 | 7/19/2025 | Y | EXP | 365 | 09/19/2024 | 10/28/2024 | 40 | 0 | 40 |  |  | 5/14/2025 | Connected |  | N
National Grid | DUDLEY | 419846 | 01571 | 0 | Other | 05_12_51T3 | 06/14/2022 | 07/19/2022 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/20/2022 | 08/08/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 641313 | 01440 | 7.6 | Solar | 05_14_3L2 | 09/18/2024 | 10/07/2024 | 4 | 0 | 4 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/18/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176542 | 02721 | 10 | Solar | 05_14_59L3 | 03/30/2016 | 03/30/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 646267 | 02176 | 10 | Solar | 05_14_74L1 | 10/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/21/2024 | 1/19/2026 | Y | EXP | 365 | 03/04/2025 | 03/03/2025 | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | GLOUCESTER | 637387 | 01930 | 6.4 | Solar | 05_12_67J1 | 09/03/2024 | 09/06/2024 | 6 | 2 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2025 | Connected |  | N
National Grid | LOWELL | 518028 | 01852 | 6 | Solar | 05_01_26W1 | 09/22/2023 | 09/25/2023 | 2 | 1 | 1 | 09/26/2023 | 09/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | TEWKSBURY | 547469 | 01876 | 6 | Solar | 05_01_412L4 | 08/23/2023 | 08/28/2023 | 3 | 1 | 2 | 08/29/2023 | 08/29/2023 | 53 | 26 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 206349 | 01844 | 2340 | Solar | 05_01_602W2 | 02/06/2019 |  | 140 | 26 | 114 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 177448 | 02155 | 96 | Solar | 05_05_115W45 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 | 09/20/2016 | 09/20/2016 | 54 | 2 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 640889 | 01501 | 9 | Solar | 05_12_25W4 | 09/18/2024 | 11/01/2024 | 17 | 11 | 6 | 11/04/2024 | 11/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | DUDLEY | 496619 | 01571 | 110 | Solar | 05_12_51T3 | 02/21/2023 | 04/21/2023 | 41 | 31 | 10 |  |  | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 647155 | 01473 | 6 | Solar | 05_14_3L2 | 10/24/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2025 | Connected |  | N
National Grid | FALL RIVER | 176927 | 02723 | 7.6 | Solar | 05_14_59L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/25/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/19/2016 | 5/19/2016 | 5/23/2016 | Connected |  | N
National Grid | MELROSE | 647971 | 02176 | 7.6 | Solar | 05_14_74L1 | 10/17/2024 | 01/22/2025 | 3 | 0 | 3 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 10/17/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | GLOUCESTER | 688261 | 01930 | 5.76 | Solar | 05_12_67J1 | 05/01/2025 |  | 65 | 63 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 523508 | 01852 | 3 | Solar | 05_01_26W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/05/2023 | 6/21/2024 | Y | EXP | 365 | 08/19/2023 | 09/29/2023 | 42 | 0 | 42 |  |  | 10/10/2023 | Connected |  | N
National Grid | TEWKSBURY | 552482 | 01876 | 10 | Solar | 05_01_412L4 | 09/13/2023 | 09/19/2023 | 4 | 2 | 2 | 09/20/2023 | 09/20/2023 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | METHUEN | 282891 | 01844 | 4950 | Other | 05_01_602W2 | 03/19/2020 | 03/27/2020 | 5 | 1 | 4 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/29/2020 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178081 | 02155 | 10 | Solar | 05_05_115W45 | 05/08/2017 | 05/08/2017 | 6 | 6 | 0 | 05/17/2017 | 05/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 | 05/08/2017 | 5/14/2018 | Y | EXP | 361 | 10/23/2017 | 11/09/2017 | 8 | 0 | 8 | 11/9/2017 | 11/9/2017 | 11/28/2017 | Connected |  | N
National Grid | AUBURN | 645195 | 01501 | 7.6 | Solar | 05_12_25W4 | 10/25/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 572797 | 01571 | 7.6 | Solar | 05_12_51T3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/12/2024 | 3/24/2025 | Y | EXP | 365 | 08/01/2024 | 09/25/2024 | 56 | 0 | 56 |  |  | 10/29/2024 | Connected |  | N
National Grid | HUBBARDSTON | 649912 | 01565 | 3.8 | Solar | 05_14_3L2 | 11/06/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/06/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | FALL RIVER | 177144 | 02721 | 10 | Solar | 05_14_59L3 | 05/29/2016 | 05/29/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 164 | 0 | 164 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 648935 | 02176 | 5.76 | Solar | 05_14_74L1 | 11/04/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 | 03/15/2025 | 03/25/2025 | 11 | 0 | 11 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 730479 | 01930 | 3.8 | Solar | 05_12_67J1 | 10/30/2025 | 11/05/2025 | 4 | 0 | 4 | 11/06/2025 | 11/06/2025 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2026 | Connected |  | N
National Grid | LOWELL | 568871 | 01852 | 10 | Solar | 05_01_26W1 | 11/14/2023 | 11/16/2023 | 2 | 0 | 2 | 11/17/2023 | 11/17/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 552358 | 01876 | 6 | Solar | 05_01_412L4 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 | 09/01/2023 | 10/27/2024 | Y | EXP | 365 | 01/27/2024 | 04/03/2024 | 68 | 0 | 68 |  |  | 4/16/2024 | Connected |  | N
National Grid | METHUEN | 287828 | 01844 | 0 | Other | 05_01_602W2 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/09/2020 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178427 | 02155 | 42 | Solar | 05_05_115W45 | 01/18/2018 | 01/18/2018 | 15 | 0 | 15 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/23/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  | 8/15/2018 | Connected |  | N
National Grid | AUBURN | 647977 | 01501 | 6.67 | Solar | 05_12_25W4 | 10/17/2024 | 11/26/2024 | 6 | 1 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | DUDLEY | 615411 | 01571 | 25 | Solar | 05_12_51T3 | 06/10/2024 | 11/07/2024 | 104 | 95 | 9 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | HUBBARDSTON | 651647 | 01452 | 7.6 | Solar | 05_14_3L2 | 11/13/2024 | 12/08/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/13/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | FALL RIVER | 177325 | 02721 | 6 | Solar | 05_14_59L3 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/22/2016 | 06/22/2016 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2016 |  | 6/26/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 650926 | 02176 | 10 | Solar | 05_14_74L1 | 11/12/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | ROCKPORT | 721153 | 01966 | 100 | Solar | 05_01_HT56B | 02/22/2026 |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LOWELL | 569888 | 01852 | 10 | Solar | 05_01_26W1 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/20/2023 | 1/25/2025 | Y | EXP | 365 | 03/16/2024 | 06/18/2024 | 95 | 0 | 95 |  |  | 7/1/2024 | Connected |  | N
National Grid | TEWKSBURY | 572497 | 01876 | 7.25 | Solar | 05_01_412L4 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 31 | 6 | 25 | 02/09/2024 | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 03/12/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/7/2025 | N | EXP | 365 | 03/08/2024 | 04/19/2024 | 43 | 0 | 43 |  |  | 5/30/2024 | Connected |  | N
National Grid | METHUEN | 290747 | 01844 | 0 | Other | 05_01_602W2 | 08/31/2020 | 09/16/2020 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/17/2020 | 10/08/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 192209 | 01604 | 17.6 | Solar | 05_05_115W45 | 07/31/2018 | 08/30/2018 | 12 | 2 | 10 | 08/31/2018 | 08/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 07/31/2018 | 10/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | AUBURN | 648629 | 01501 | 7.6 | Solar | 05_12_25W4 | 10/22/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/22/2024 | 3/7/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | DUDLEY | 700819 | 01571 | 15.76 | Solar | 05_12_51T3 | 07/02/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 07/02/2025 | 8/4/2026 | Y | EXP | 365 | 11/04/2025 | 11/18/2025 | 15 | 0 | 15 |  |  | 12/8/2025 | Connected |  | N
National Grid | WESTMINSTER | 661000 | 01473 | 8.74 | Solar | 05_14_3L2 | 12/18/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/18/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | FALL RIVER | 177655 | 02721 | 2838 | Solar | 05_14_59L3 | 11/09/2017 | 11/09/2017 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/30/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 11/09/2017 | 4/10/2022 | Y | STD | 266 | 11/17/2021 | 01/13/2022 | 57 | 0 | 57 |  |  | 2/18/2022 | Connected |  | N
National Grid | MELROSE | 650870 | 02176 | 10 | Solar | 05_14_74L1 | 11/11/2024 | 12/18/2024 | 1 | 0 | 1 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/11/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | GLOUCESTER | 578624 | 01930 | 200 | Solar | 05_01_HT56B | 02/06/2024 | 01/17/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 581921 | 01852 | 6.38 | Solar | 05_01_26W1 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | TEWKSBURY | 573922 | 01876 | 10 | Solar | 05_01_412L4 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/07/2023 | 12/07/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/01/2023 | 4/14/2025 | Y | EXP | 365 | 05/02/2024 | 08/23/2024 | 114 | 0 | 114 |  |  | 11/24/2024 | Connected |  | N
National Grid | METHUEN | 291986 | 01844 | 5.76 | Solar | 05_01_602W2 | 05/14/2020 | 05/15/2020 | 0 | 0 | 0 | 05/18/2020 | 05/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | WORCESTER | 192619 | 01604 | 10 | Solar | 05_05_115W45 | 08/06/2018 | 08/30/2018 | 7 | 2 | 5 | 08/31/2018 | 08/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 | 08/06/2018 | 9/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | AUBURN | 665306 | 01501 | 5.76 | Solar | 05_12_25W4 | 01/13/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 6/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | DUDLEY | 703384 | 01571 | 90 | Solar | 05_12_51T3 | 07/10/2025 | 08/07/2025 | 20 | 11 | 9 | 08/08/2025 | 08/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 666669 | 01440 | 7.6 | Solar | 05_14_3L2 | 01/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/20/2025 | 4/14/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 12/4/2025 | Connected |  | N
National Grid | FALL RIVER | 178219 | 02721 | 7.6 | Solar | 05_14_59L3 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 651514 | 02176 | 5.76 | Solar | 05_14_74L1 | 11/21/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 680413 | 01930 | 7.6 | Solar | 05_01_216W4 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 | 04/07/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 599053 | 01852 | 15.2 | Solar | 05_01_26W1 | 04/18/2024 | 06/21/2024 | 45 | 43 | 2 | 06/24/2024 | 06/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 04/18/2024 | 7/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 574933 | 01876 | 499 | Solar | 05_01_412L4 | 01/19/2024 |  | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 294861 | 01844 | 0 | Other | 05_01_602W2 | 09/09/2020 | 09/22/2020 | 8 | 1 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 197978 | 01523 | 6 | Solar | 05_05_115W45 | 10/08/2018 | 01/03/2019 | 43 | 41 | 2 | 01/04/2019 | 01/04/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 665545 | 01501 | 7.6 | Solar | 05_12_25W4 | 01/14/2025 | 01/30/2025 | 3 | 0 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | DUDLEY | 628375 | 01571 | 34.5 | Battery Add-On | 05_12_52J2 | 07/29/2024 | 08/01/2024 | 3 | 0 | 3 | 08/02/2024 | 08/02/2024 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | HUBBARDSTON | 679992 | 01452 | 11.52 | Solar | 05_14_3L2 | 03/24/2025 | 04/11/2025 | 10 | 6 | 4 | 04/30/2025 | 04/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178637 | 02721 | 7.6 | Solar | 05_14_59L3 | 04/09/2018 | 04/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 655742 | 02176 | 3.8 | Solar | 05_14_74L1 | 11/20/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | GLOUCESTER | 721352 | 01930 | 9.074 | Solar | 05_01_216W4 | 09/27/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/27/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LOWELL | 664182 | 01852 | 3.8 | Solar | 05_01_26W1 | 01/07/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 587291 | 01876 | 4.93 | Solar | 05_01_412L4 | 02/13/2024 | 02/15/2024 | 2 | 0 | 2 | 02/16/2024 | 02/16/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 319090 | 01844 | 15.2 | Solar | 05_01_602W2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 03/02/2021 | 03/19/2021 | 17 | 0 | 17 |  |  | 7/15/2021 | Connected |  | N
National Grid | LANCASTER | 205831 | 01523 | 4.8 | Solar | 05_05_115W45 | 02/27/2019 | 03/15/2019 | 12 | 11 | 1 | 03/18/2019 | 03/18/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 02/27/2019 | 11/13/2019 | Y | EXP | 236 | 05/08/2019 | 06/06/2019 | 29 | 0 | 29 |  |  | 7/5/2019 | Connected |  | N
National Grid | AUBURN | 671938 | 01501 | 9.88 | Solar | 05_12_25W4 | 02/13/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | DUDLEY | 657154 | 01571 | 3.8 | Solar | 05_12_52L1 | 11/26/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HUBBARDSTON | 707901 | 01452 | 3.8 | Solar | 05_14_3L2 | 07/28/2025 | 08/29/2025 | 5 | 0 | 5 | 09/02/2025 | 09/02/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 183612 | 02712 | 7.6 | Solar | 05_14_59L3 | 04/23/2018 | 04/23/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2019 | Connected |  | N
National Grid | MELROSE | 657618 | 02176 | 10 | Solar | 05_14_74L1 | 11/29/2024 | 01/10/2025 | 2 | 0 | 2 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 11/29/2024 | 3/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | GLOUCESTER | 725215 | 01930 | 60 | Solar | 05_01_216W4 | 10/09/2025 | 10/29/2025 | 13 | 6 | 7 |  |  | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 696569 | 01852 | 15.96 | Solar | 05_01_26W1 | 06/05/2025 | 06/09/2025 | 2 | 0 | 2 | 06/10/2025 | 06/10/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | TEWKSBURY | 595397 | 01876 | 7.296 | Solar | 05_01_412L4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/01/2024 | 7/2/2025 | Y | EXP | 365 | 08/01/2024 | 08/19/2024 | 19 | 0 | 19 |  |  | 8/22/2024 | Connected |  | N
National Grid | METHUEN | 326400 | 01844 | 84 | Solar | 05_01_602W2 | 11/17/2020 | 02/18/2021 | 62 | 54 | 8 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 02/19/2021 | 02/23/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 304302 | 01523 | 3.8 | Solar | 05_05_115W45 | 08/07/2020 | 08/11/2020 | 1 | 0 | 1 | 08/12/2020 | 08/12/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 694846 | 01501 | 11.4 | Solar | 05_12_25W4 | 06/12/2025 | 06/20/2025 | 4 | 0 | 4 | 06/23/2025 | 06/23/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | DUDLEY | 691723 | 01571 | 11.5 | Solar | 05_12_52L1 | 06/12/2025 | 07/22/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HUBBARDSTON | 710001 | 01452 | 5.933 | Solar | 05_14_3L2 | 08/06/2025 | 08/26/2025 | 3 | 0 | 3 | 09/03/2025 | 09/03/2025 | 62 | 47 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 189478 | 02790 | 7.6 | Solar | 05_14_59L3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 | 07/02/2018 | 07/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 663020 | 02176 | 5.76 | Solar | 05_14_74L1 | 12/30/2024 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 | 12/30/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | GLOUCESTER | 174206 | 01930 | 2450 | Solar | 05_01_216W4 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 |  | 1/1/2013 | N | STD | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 710851 | 01852 | 5.76 | Solar | 05_01_26W1 | 08/08/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | TEWKSBURY | 605221 | 01876 | 7.6 | Solar | 05_01_412L4 | 04/23/2024 | 05/14/2024 | 12 | 10 | 2 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | METHUEN | 342936 | 01844 | 7.68 | Solar | 05_01_602W2 | 03/02/2021 | 03/08/2021 | 4 | 4 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | Y
National Grid | BOLTON | 377985 | 01740 | 6 | Solar | 05_05_115W45 | 09/10/2021 | 12/07/2021 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 | 09/10/2021 | 5/25/2023 | Y | EXP | 365 | 04/12/2022 | 05/18/2022 | 37 | 0 | 37 |  |  | 6/29/2022 | Connected |  | N
National Grid | AUBURN | 699634 | 01501 | 7.678 | Solar | 05_12_25W4 | 06/18/2025 | 07/02/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | DUDLEY | 724732 | 01571 | 19.2 | Solar | 05_12_52L1 | 10/13/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | GARDNER | 642855 | 01440 | 120 | Solar | 05_14_3L4 | 09/30/2024 | 01/30/2025 | 81 | 73 | 8 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 09/30/2024 | 2/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FALL RIVER | 321076 | 02721 | 6.38 | Solar | 05_14_59L3 | 10/22/2020 | 10/23/2020 | 1 | 1 | 0 | 10/26/2020 | 10/26/2020 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 | 10/22/2020 | 10/22/2021 | Y | EXP | 365 | 03/19/2021 | 03/18/2021 | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | MELROSE | 667339 | 02176 | 5.76 | Solar | 05_14_74L1 | 01/23/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/23/2025 | 3/28/2026 | Y | EXP | 365 | 06/18/2025 | 12/22/2025 | 188 | 0 | 188 |  |  | 12/4/2025 | Connected |  | N
National Grid | GLOUCESTER | 176510 | 01930 | 10 | Solar | 05_01_216W4 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 4/3/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/11/2016 | Connected |  | N
National Grid | LOWELL | 716350 | 01852 | 11.517 | Solar | 05_01_26W1 | 09/03/2025 | 09/29/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2026 | Connected |  | N
National Grid | TEWKSBURY | 606033 | 01876 | 10 | Solar | 05_01_412L4 | 04/26/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 6/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | METHUEN | 342428 | 01844 | 9.6 | Solar | 05_01_602W2 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2021 | Connected |  | N
National Grid | CLINTON | 401114 | 01510 | 0 | Other | 05_05_115W45 | 01/06/2022 | 01/31/2022 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/02/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 658099 | 01501 | 3.8 | Solar | 05_12_25W5 | 12/03/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 740577 | 01571 | 11.52 | Solar | 05_12_52L1 | 12/19/2025 | 12/26/2025 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTMINSTER | 659689 | 01473 | 7.6 | Solar | 05_14_3L4 | 12/10/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 349329 | 02724 | 3.8 | Solar | 05_14_59L3 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N
National Grid | MELROSE | 668089 | 02176 | 3.8 | Solar | 05_14_74L1 | 01/27/2025 | 02/18/2025 | 1 | 0 | 1 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | GLOUCESTER | 176516 | 01930 | 10 | Solar | 05_01_216W4 | 10/02/2015 | 10/02/2015 | 0 | 0 | 0 | 10/05/2015 | 10/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 12/29/2015 | 12/29/2015 | 1/12/2016 | Connected |  | N
National Grid | LOWELL | 719926 | 01852 | 11.5 | Solar | 05_01_26W1 | 09/17/2025 | 09/30/2025 | 5 | 3 | 2 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 | 09/17/2025 | 1/7/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | TEWKSBURY | 660754 | 01876 | 10 | Solar | 05_01_412L4 | 12/16/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 155 | 137 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 346682 | 01844 | 22.8 | Solar | 05_01_602W2 | 03/18/2021 | 04/01/2021 | 10 | 10 | 0 | 04/02/2021 | 04/02/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/18/2021 | 4/1/2022 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 565509 | 01523 | 5 | Solar | 05_05_115W45 | 11/08/2023 | 11/29/2023 | 13 | 10 | 3 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 707442 | 01501 | 7.6 | Solar | 05_12_25W5 | 07/25/2025 | 08/13/2025 | 4 | 0 | 4 | 09/16/2025 | 09/16/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 753100 | 01571 | 22.8 | Solar | 05_12_52L1 | 02/25/2026 | 02/27/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HUBBARDSTON | 679179 | 01452 | 250 | Solar | 05_14_3L4 | 04/14/2025 | 05/19/2025 | 24 | 14 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | FALL RIVER | 396310 | 02721 | 0 | Other | 05_14_59L3 | 02/17/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/05/2022 | 04/05/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 668858 | 02176 | 10 | Solar | 05_14_74L1 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | GLOUCESTER | 186590 | 01930 | 15.2 | Solar | 05_01_216W4 | 05/29/2018 | 05/29/2018 | 8 | 0 | 8 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | LOWELL | 728456 | 01852 | 10 | Solar | 05_01_26W1 | 10/22/2025 | 10/26/2025 | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 664981 | 01876 | 10 | Solar | 05_01_412L4 | 01/10/2025 | 01/28/2025 | 7 | 2 | 5 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 01/10/2025 | 7/12/2026 | Y | EXP | 365 | 06/12/2025 | 07/08/2025 | 27 | 0 | 27 |  |  | 10/28/2025 | Connected |  | N
National Grid | METHUEN | 351897 | 01844 | 3.8 | Solar | 05_01_602W2 | 05/10/2021 | 05/14/2021 | 3 | 0 | 3 | 05/17/2021 | 05/17/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 570860 | 01561 | 6 | Solar | 05_05_115W45 | 11/20/2023 | 12/05/2023 | 11 | 7 | 4 | 12/06/2023 | 12/06/2023 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 11/20/2023 | 4/1/2025 | Y | EXP | 365 | 05/29/2024 | 07/25/2024 | 58 | 0 | 58 |  |  | 7/30/2024 | Connected |  | N
National Grid | AUBURN | 175387 | 01501 | 90 | Solar | 05_12_25W5 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/15/2014 | N | EXP | 68 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 1/15/2015 | Connected |  | N
National Grid | DUDLEY | 175870 | 01571 | 25 | Solar | 05_12_52L1 | 09/25/2015 | 09/25/2015 | 1 | 1 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2015 |  | 10/3/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 1/29/2016 | 1/29/2016 | 2/3/2016 | Connected |  | N
National Grid | GARDNER | 727228 | 01440 | 7.6 | Solar | 05_14_3L4 | 10/16/2025 | 01/22/2026 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 525204 | 02721 | 4.41 | Solar | 05_14_59L3 | 05/16/2023 | 05/17/2023 | 1 | 0 | 1 | 05/18/2023 | 05/18/2023 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2023 |  | 8/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | MELROSE | 673277 | 02176 | 23 | Solar | 05_14_74L1 | 02/20/2025 | 06/05/2025 | 72 | 38 | 34 | 06/06/2025 | 06/06/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | GLOUCESTER | 430312 | 01930 | 0 | Other | 05_01_216W4 | 01/04/2023 | 01/19/2023 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 587625 | 01852 | 200 | Solar | 05_01_26W2 | 03/14/2024 | 07/10/2025 | 328 | 322 | 6 |  |  | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | TEWKSBURY | 669061 | 01876 | 11.5 | Solar | 05_01_412L4 | 02/04/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/04/2025 | 4/14/2026 | Y | EXP | 365 | 05/06/2025 | 07/11/2025 | 67 | 0 | 67 |  |  | 7/30/2025 | Connected |  | N
National Grid | METHUEN | 452437 | 01844 | 8.12 | Solar | 05_01_602W2 | 10/04/2022 | 10/28/2022 | 18 | 14 | 4 | 10/31/2022 | 10/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 10/04/2022 | 5/4/2024 | Y | EXP | 365 | 04/20/2023 | 05/03/2023 | 14 | 0 | 14 |  |  | 5/12/2023 | Connected |  | N
National Grid | LANCASTER | 647595 | 01523 | 7.6 | Solar | 05_05_115W45 | 10/16/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 176038 | 01501 | 10 | Solar | 05_12_25W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 6/22/2016 | 6/22/2016 | 8/5/2016 | Connected |  | N
National Grid | DUDLEY | 177815 | 01571 | 15.2 | Solar | 05_12_52L1 | 03/31/2017 | 03/31/2017 | 7 | 4 | 3 | 04/11/2017 | 04/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2017 | 03/31/2017 | 8/10/2018 | Y | EXP | 485 | 01/24/2018 | 02/23/2018 | 21 | 0 | 21 |  |  | 7/30/2018 | Connected |  | N
National Grid | HUBBARDSTON | 748135 | 01452 | 3.8 | Solar | 05_14_3L4 | 01/29/2026 | 02/03/2026 | 3 | 0 | 3 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTPORT | 585728 | 02790 | 0 | Solar | 05_14_59L3 | 01/26/2024 | 02/01/2024 | 5 | 3 | 2 | 02/02/2024 | 02/02/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 679348 | 02176 | 7.6 | Solar | 05_14_74L1 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 438016 | 01930 | 10 | Solar | 05_01_216W4 | 07/18/2022 | 07/20/2022 | 2 | 0 | 2 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/18/2022 | 8/25/2023 | Y | EXP | 365 | 10/11/2022 | 12/21/2022 | 72 | 0 | 72 |  |  | 1/10/2023 | Connected |  | N
National Grid | LOWELL | 641473 | 01852 | 125 | Solar | 05_01_26W2 | 09/19/2024 | 10/29/2024 | 27 | 18 | 9 | 10/30/2024 | 10/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 5/13/2026 | N | EXP | 12 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 685553 | 01876 | 11.4 | Solar | 05_01_412L4 | 04/16/2025 | 04/24/2025 | 5 | 0 | 5 | 04/25/2025 | 04/25/2025 | 98 | 90 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | HAVERHILL | 438280 | 01832 | 15.2 | Solar | 05_01_602W2 | 03/12/2024 | 07/04/2022 | 15 | 13 | 2 | 04/02/2024 | 04/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N
National Grid | LANCASTER | 661519 | 01523 | 3.2 | Solar | 05_05_115W45 | 12/18/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/18/2024 | 4/21/2026 | Y | EXP | 365 | 05/10/2025 | 05/09/2025 | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | AUBURN | 178553 | 01501 | 120 | Solar | 05_12_25W5 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 11/14/2019 | N | EXP | 393 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | DUDLEY | 274362 | 01571 | 4.32 | Solar | 05_12_52L1 | 02/12/2020 | 02/26/2020 | 8 | 8 | 0 | 02/27/2020 | 02/27/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 02/12/2020 | 2/26/2021 | Y | EXP | 365 | 07/23/2020 | 09/15/2020 | 55 | 5 | 50 |  |  | 9/16/2020 | Connected |  | N
National Grid | GARDNER | 387537 | 01440 | 18.148 | Solar | 05_14_3L4 | 10/12/2021 | 01/07/2022 | 6 | 0 | 6 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | FALL RIVER | 606299 | 02721 | 7.6 | Solar | 05_14_59L3 | 04/24/2024 | 05/03/2024 | 5 | 0 | 5 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 07/24/2024 | 02/26/2025 | 218 | 0 | 218 |  |  | 3/7/2025 | Connected |  | N
National Grid | MELROSE | 682711 | 02176 | 5.76 | Solar | 05_14_74L1 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | GLOUCESTER | 481067 | 01930 | 6.38 | Solar | 05_01_216W4 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/15/2022 | 5/16/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | LOWELL | 649613 | 01852 | 200 | Solar | 05_01_26W2 | 05/06/2025 | 07/25/2025 | 55 | 45 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | TEWKSBURY | 693374 | 01876 | 12.54 | Solar | 05_01_412L4 | 05/28/2025 |  | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 473103 | 01844 | 14.79 | Solar | 05_01_602W2 | 11/03/2022 |  | 171 | 72 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 667660 | 01523 | 7.6 | Solar | 05_05_115W45 | 01/24/2025 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | AUBURN | 195099 | 01501 | 7.6 | Solar | 05_12_25W5 | 09/05/2018 | 09/26/2018 | 3 | 3 | 0 | 09/27/2018 | 09/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 303344 | 01571 | 15.2 | Solar | 05_12_52L1 | 07/27/2020 | 08/28/2020 | 24 | 24 | 0 | 08/31/2020 | 08/31/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 4/11/2022 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 2/10/2022 | Connected |  | N
National Grid | GARDNER | 422062 | 01440 | 0 | Battery Add-On | 05_14_3L4 | 10/05/2022 | 06/22/2023 | 176 | 166 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 07/18/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 612327 | 02724 | 7.6 | Solar | 05_14_59L3 | 05/20/2024 | 06/03/2024 | 3 | 0 | 3 | 06/04/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 | 05/20/2024 | 7/25/2025 | Y | EXP | 365 | 08/29/2024 | 10/23/2024 | 56 | 0 | 56 |  |  | 12/4/2024 | Connected |  | N
National Grid | MELROSE | 689896 | 02176 | 11.5 | Solar | 05_14_74L1 | 05/06/2025 | 05/08/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 506925 | 01930 | 8.7 | Solar | 05_01_216W4 | 05/25/2023 | 06/05/2023 | 6 | 4 | 2 | 06/06/2023 | 06/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/25/2023 | 8/12/2024 | Y | EXP | 365 | 05/07/2024 | 05/14/2024 | 8 | 0 | 8 |  |  | 5/15/2024 | Connected |  | N
National Grid | LOWELL | 742221 | 01852 | 15.76 | Solar | 05_01_26W2 | 12/25/2025 | 12/31/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 693113 | 01876 | 23 | Solar | 05_01_412L4 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 | 05/29/2025 | 7/28/2026 | Y | EXP | 365 | 10/29/2025 | 01/20/2026 | 84 | 0 | 84 |  |  | 1/9/2026 | Connected |  | N
National Grid | METHUEN | 487740 | 01844 | 9.86 | Solar | 05_01_602W2 | 01/05/2023 | 01/09/2023 | 2 | 0 | 2 | 01/10/2023 | 01/10/2023 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 671676 | 01523 | 7.6 | Solar | 05_05_115W45 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/12/2025 | 4/9/2026 | Y | EXP | 365 | 05/02/2025 | 06/06/2025 | 36 | 0 | 36 |  |  | 6/23/2025 | Connected |  | N
National Grid | AUBURN | 192454 | 01501 | 10 | Solar | 05_12_25W5 | 08/02/2018 | 08/11/2018 | 2 | 2 | 0 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | Connected |  | N
National Grid | DUDLEY | 371202 | 01571 | 7.6 | Solar | 05_12_52L1 | 08/03/2021 | 08/18/2021 | 12 | 11 | 1 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2021 | Connected |  | N
National Grid | WESTMINSTER | 500890 | 01473 | 100 | Solar | 05_14_3L4 | 02/24/2023 | 04/07/2023 | 30 | 21 | 9 | 04/10/2023 | 04/10/2023 | 43 | 18 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 | 02/24/2023 | 1/27/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 642192 | 02721 | 0 | Battery Add-On | 05_14_59L3 | 09/27/2024 | 10/02/2024 | 3 | 0 | 3 | 10/03/2024 | 10/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | MELROSE | 700558 | 02176 | 15.2 | Solar | 05_14_74L1 | 06/23/2025 | 07/25/2025 | 22 | 17 | 5 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | ROCKPORT | 640010 | 01966 | 3.77 | Solar | 05_01_216W4 | 09/13/2024 | 09/25/2024 | 5 | 2 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 09/13/2024 | 12/2/2025 | Y | EXP | 365 | 04/15/2025 | 11/09/2025 | 209 | 0 | 209 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 744507 | 01852 | 5.76 | Solar | 05_01_26W2 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TEWKSBURY | 697368 | 01876 | 15.58 | Solar | 05_01_412L4 | 06/10/2025 | 06/24/2025 | 9 | 6 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2025 | Connected |  | N
National Grid | HAVERHILL | 493004 | 01832 | 15.95 | Solar | 05_01_602W2 | 01/17/2023 | 02/08/2023 | 16 | 15 | 1 | 02/09/2023 | 02/09/2023 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 01/17/2023 | 7/26/2024 | Y | EXP | 365 | 08/15/2023 | 09/22/2023 | 39 | 0 | 39 |  |  | 10/3/2023 | Connected |  | N
National Grid | CLINTON | 687395 | 01510 | 498 | Solar | 05_05_115W45 | 05/16/2025 | 07/08/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2025 | 08/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 222080 | 01501 | 7.6 | Solar | 05_12_25W5 | 06/05/2019 | 06/06/2019 | 0 | 0 | 0 | 06/07/2019 | 06/07/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 | 06/05/2019 | 9/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | DUDLEY | 375231 | 01571 | 11.4 | Solar | 05_12_52L1 | 08/11/2021 | 08/31/2021 | 14 | 13 | 1 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2021 | 08/11/2021 | 2/14/2023 | Y | EXP | 365 | 01/06/2022 | 02/14/2022 | 40 | 0 | 40 |  |  | 4/19/2022 | Connected |  | Y
National Grid | WESTMINSTER | 556411 | 01473 | 250 | Solar | 05_14_3L4 | 12/01/2023 | 12/26/2023 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 647522 | 02790 | 7.6 | Solar | 05_14_59L3 | 10/22/2024 | 11/19/2024 | 7 | 5 | 2 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 713543 | 02176 | 7.6 | Solar | 05_14_74L1 | 08/20/2025 | 09/10/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 60 | 47 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKPORT | 650594 | 01966 | 10 | Solar | 05_01_216W4 | 11/11/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/11/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | LOWELL | 174587 | 01852 | 22.8 | Solar | 05_01_26W2 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 6/28/2012 | N | EXP | 227 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 6/28/2012 | Connected |  | N
National Grid | TEWKSBURY | 725829 | 01876 | 7.6 | Solar | 05_01_412L4 | 10/10/2025 | 10/24/2025 | 8 | 2 | 6 | 10/27/2025 | 10/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | METHUEN | 511164 | 01844 | 9.57 | Solar | 05_01_602W2 | 03/15/2023 | 04/21/2023 | 26 | 25 | 1 | 04/24/2023 | 04/24/2023 | 90 | 73 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | LANCASTER | 663198 | 01523 | 999.9 | Solar | 05_05_115W52 | 02/06/2025 | 04/24/2025 | 53 | 44 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/22/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 269791 | 01501 | 3 | Solar | 05_12_25W5 | 12/20/2019 | 01/02/2020 | 6 | 0 | 6 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | DUDLEY | 380590 | 01571 | 7.6 | Solar | 05_12_52L1 | 11/16/2021 | 12/20/2021 | 23 | 22 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 551159 | 01452 | 6 | Solar | 05_14_3L4 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | FALL RIVER | 648085 | 02721 | 3 | Solar | 05_14_59L3 | 10/18/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | MELROSE | 720467 | 02176 | 15.2 | Solar | 05_14_74L1 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | GLOUCESTER | 670659 | 01930 | 13.3 | Solar | 05_01_216W4 | 02/08/2025 | 02/18/2025 | 6 | 1 | 5 | 02/19/2025 | 02/19/2025 | 56 | 35 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/08/2025 | 5/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 175624 | 01852 | 684 | Solar | 05_01_26W2 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 0 | 0 | 0 | 07/30/2014 | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  | 08/29/2014 | 22 | 4 | 18 |  |  | 0 | 0 | 0 | 10/2/2014 | 05/05/2014 | 12/31/2015 | Y | EXP | 455 | 08/25/2015 | 11/23/2015 | 61 | 0 | 61 | 11/18/2015 | 11/18/2015 | 12/16/2015 | Connected |  | N
National Grid | TEWKSBURY | 704897 | 01876 | 15.2 | Solar | 05_01_412L5 | 07/15/2025 | 08/07/2025 | 17 | 12 | 5 | 08/08/2025 | 08/08/2025 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 523055 | 01832 | 7.6 | Solar | 05_01_602W2 | 05/15/2023 | 05/15/2023 | 0 | 0 | 0 | 05/16/2023 | 05/16/2023 | 195 | 34 | 161 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 683283 | 01523 | 3.8 | Solar | 05_05_115W52 | 04/07/2025 | 04/24/2025 | 3 | 0 | 3 | 05/07/2025 | 05/07/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 04/07/2025 | 6/24/2026 | Y | EXP | 365 | 07/09/2025 | 08/29/2025 | 52 | 0 | 52 |  |  |  | Completion Documents |  | Y
National Grid | MILLBURY | 294223 | 01527 | 0 | Solar | 05_12_25W5 | 06/01/2020 | 06/04/2020 | 3 | 3 | 0 | 06/05/2020 | 06/05/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2020 | Connected |  | N
National Grid | DUDLEY | 412422 | 01571 | 15.2 | Solar | 05_12_52L1 | 02/23/2022 | 02/24/2022 | 2 | 1 | 1 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | WESTMINSTER | 595183 | 01473 | 3.8 | Solar | 05_14_3L4 | 03/13/2024 | 03/14/2024 | 1 | 0 | 1 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 03/13/2024 | 4/1/2025 | Y | EXP | 365 | 05/07/2024 | 08/08/2024 | 94 | 0 | 94 |  |  | 9/16/2024 | Connected |  | N
National Grid | FALL RIVER | 651393 | 02721 | 3.8 | Solar | 05_14_59L3 | 11/22/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MELROSE | 727180 | 02176 | 5.76 | Solar | 05_14_74L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 685367 | 01930 | 16.34 | Solar | 05_01_216W4 | 04/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | LOWELL | 175849 | 01852 | 1000 | Solar | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 02/10/2017 | 06/30/2016 | 0 | 0 | 0 | 8/3/2016 |  | 9/30/2017 | N | STD | 423 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 739666 | 01876 | 15.2 | Solar | 05_01_412L5 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 553543 | 01844 | 6 | Solar | 05_01_602W2 | 09/22/2023 | 09/26/2023 | 2 | 0 | 2 | 09/27/2023 | 09/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/22/2023 | 12/2/2024 | Y | EXP | 365 | 05/03/2024 | 05/18/2024 | 16 | 0 | 16 |  |  | 5/23/2024 | Connected |  | N
National Grid | LANCASTER | 692739 | 01523 | 20 | Solar | 05_05_115W52 | 05/19/2025 | 05/21/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 52 | 43 | 9 | 11/04/2025 |  | 83 | 66 | 17 |  |  | 0 | 0 | 0 |  |  | 83 | 66 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | Y
National Grid | MILLBURY | 334088 | 01527 | 10 | Solar | 05_12_25W5 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | DUDLEY | 485413 | 01571 | 7.6 | Solar | 05_12_52L1 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 12/31/2024 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 601232 | 01452 | 6 | Solar | 05_14_3L4 | 04/08/2024 | 04/10/2024 | 2 | 0 | 2 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 653564 | 02720 | 5.76 | Solar | 05_14_59L3 | 11/15/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/15/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | MELROSE | 665501 | 02176 | 999 | Solar | 05_14_74L2 | 01/29/2025 | 02/24/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/25/2025 | 03/25/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | GLOUCESTER | 686227 | 01930 | 10 | Solar | 05_01_216W4 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177238 | 01852 | 186.6 | Solar | 05_01_26W2 | 02/03/2017 | 02/03/2017 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 176210 | 01876 | 5 | Solar | 05_01_412L5 | 04/27/2015 | 04/27/2015 | 0 | 0 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2015 |  | 9/30/2015 | N | EXP | 153 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 3/29/2016 | Connected |  | N
National Grid | METHUEN | 561273 | 01844 | 6.38 | Solar | 05_01_602W2 | 11/14/2023 | 01/10/2024 | 39 | 31 | 8 | 01/11/2024 | 01/11/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 711421 | 01510 | 11.4 | Solar | 05_05_115W52 | 09/09/2025 | 10/01/2025 | 15 | 9 | 6 | 10/02/2025 | 10/02/2025 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 376077 | 01501 | 15.2 | Solar | 05_12_25W5 | 09/06/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 9/13/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 488780 | 01571 | 15.2 | Solar | 05_12_52L1 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 641328 | 01452 | 6 | Solar | 05_14_3L4 | 09/20/2024 | 09/30/2024 | 4 | 0 | 4 | 10/01/2024 | 10/01/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/20/2024 | 11/20/2025 | Y | EXP | 365 | 02/19/2025 | 03/12/2025 | 22 | 0 | 22 |  |  | 3/19/2025 | Connected |  | Y
National Grid | WESTPORT | 659218 | 02790 | 9.6 | Solar | 05_14_59L3 | 12/09/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/09/2024 | 4/14/2026 | Y | EXP | 365 | 05/23/2025 | 05/22/2025 | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | MELROSE | 688247 | 02176 | 100 | Solar | 05_14_74L2 | 10/17/2025 |  | 94 | 25 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GLOUCESTER | 696423 | 01930 | 10 | Solar | 05_01_216W4 | 06/09/2025 | 06/18/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | LOWELL | 177496 | 01852 | 15.2 | Solar | 05_01_26W2 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2016 |  | 12/19/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N
National Grid | TEWKSBURY | 177367 | 01876 | 528 | Solar | 05_01_412L5 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2016 | 08/23/2016 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/3/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 566632 | 01844 | 2000 | Solar | 05_01_602W2 | 11/01/2023 |  | 95 | 55 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 714265 | 01510 | 2000 | Solar | 05_05_115W52 | 09/09/2025 | 10/02/2025 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2025 | 10/17/2025 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | AUBURN | 410315 | 01501 | 8.99 | Solar | 05_12_25W5 | 02/03/2022 | 02/04/2022 | 1 | 0 | 1 | 02/07/2022 | 02/07/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | WEBSTER | 570135 | 01570 | 15.2 | Solar | 05_12_52L1 | 11/09/2023 | 11/27/2023 | 11 | 9 | 2 | 11/28/2023 | 11/28/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | Y
National Grid | HUBBARDSTON | 646620 | 01452 | 5.76 | Solar | 05_14_3L4 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 12/20/2025 | Y | EXP | 365 | 03/04/2025 | 03/24/2025 | 21 | 0 | 21 |  |  | 3/27/2025 | Connected |  | N
National Grid | WESTPORT | 661819 | 02790 | 7.6 | Solar | 05_14_59L3 | 12/19/2024 | 01/14/2025 | 3 | 0 | 3 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | MELROSE | 722959 | 02176 | 3.8 | Solar | 05_14_74L2 | 10/01/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 | 10/01/2025 | 12/17/2026 | Y | EXP | 365 | 02/11/2026 |  | 24 | 0 | 24 |  |  |  | Construction |  | N
National Grid | GLOUCESTER | 546068 | 01930 | 500 | Solar | 05_01_216W5 | 09/07/2023 | 10/12/2023 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/03/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 177735 | 01852 | 1000 | Solar | 05_01_26W2 | 05/20/2015 | 05/20/2015 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2015 | 07/08/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 05/12/2016 | 06/30/2016 | 33 | 0 | 33 | 8/3/2016 | 05/20/2015 | 9/21/2018 | Y | STD | 779 |  |  | 0 | 0 | 0 |  |  | 9/10/2018 | Connected |  | N
National Grid | TEWKSBURY | 178735 | 01876 | 3.8 | Solar | 05_01_412L5 | 02/12/2018 | 03/15/2018 | 12 | 0 | 12 | 03/15/2018 | 03/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 | 02/12/2018 | 11/21/2019 | Y | EXP | 615 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | METHUEN | 565997 | 01844 | 10 | Solar | 05_01_602W2 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 11/07/2023 | 1/10/2025 | Y | EXP | 365 | 03/23/2024 | 04/22/2024 | 31 | 0 | 31 |  |  | 4/30/2024 | Connected |  | N
National Grid | CLINTON | 731372 | 01510 | 11.4 | Solar | 05_05_115W52 | 11/06/2025 | 11/14/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 35 | 23 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILLBURY | 437932 | 01527 | 9.984 | Solar | 05_12_25W5 | 06/15/2022 | 06/24/2022 | 3 | 1 | 2 | 06/30/2022 | 06/30/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | WEBSTER | 574937 | 01570 | 23 | Solar | 05_12_52L1 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 114 | 90 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | WESTMINSTER | 652013 | 01473 | 15.2 | Solar | 05_14_3L4 | 11/04/2024 | 11/25/2024 | 14 | 10 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WESTPORT | 664658 | 02790 | 6.84 | Solar | 05_14_59L3 | 01/09/2025 | 01/31/2025 | 7 | 2 | 5 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 4/10/2026 | Y | EXP | 365 | 06/07/2025 | 06/06/2025 | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | MELROSE | 734586 | 02176 | 11.5 | Solar | 05_14_74L2 | 11/18/2025 | 11/19/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 | 11/18/2025 | 2/4/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GLOUCESTER | 174377 | 01930 | 1000 | Solar | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2013 | N | STD |  | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178054 | 01852 | 10 | Solar | 05_01_26W2 | 07/05/2017 | 07/05/2017 | 25 | 25 | 0 | 08/10/2017 | 08/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 7/11/2018 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  | 5/25/2018 | Connected |  | N
National Grid | TEWKSBURY | 187735 | 01876 | 466.6 | Solar | 05_01_412L5 | 06/28/2018 | 06/28/2018 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2018 | 08/14/2018 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 569809 | 01844 | 0 | Solar | 05_01_602W2 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2024 |  | 9/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2024 | Connected |  | N
National Grid | CLINTON | 741857 | 01510 | 11.4 | Solar | 05_05_115W52 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 43 | 28 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 530600 | 01501 | 0 | Solar | 05_12_25W5 | 10/09/2023 | 06/13/2023 | 5 | 4 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 11/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | DUDLEY | 581847 | 01571 | 0 | Solar | 05_12_52L1 | 01/08/2024 | 02/07/2024 | 22 | 19 | 3 | 02/08/2024 | 02/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 652158 | 01452 | 3.8 | Solar | 05_14_3L4 | 11/05/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 668537 | 02790 | 5.76 | Solar | 05_14_59L3 | 01/29/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 176004 | 02176 | 7.6 | Solar | 05_14_74L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2015 |  | 8/19/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 1/25/2017 | 1/25/2017 | 1/25/2017 | Connected |  | N
National Grid | GLOUCESTER | 174376 | 01930 | 1954 | Solar | 05_01_216W5 | 05/29/2012 | 05/29/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2012 | 08/17/2012 | 47 | 0 | 47 |  |  | 0 | 0 | 0 | 03/26/2014 | 03/26/2014 | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 8/31/2017 | Y | STD | 1631 | 11/02/2017 | 08/10/2017 | 0 | 0 | 0 | 6/27/2017 | 6/27/2017 | 9/29/2017 | Connected |  | N
National Grid | LOWELL | 178522 | 01852 | 2297.7 | Solar | 05_01_26W2 | 04/04/2018 | 04/05/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 201618 | 01876 | 10 | Solar | 05_01_412L5 | 11/19/2018 | 01/03/2019 | 3 | 0 | 3 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 11/19/2018 | 1/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2021 | Connected |  | N
National Grid | METHUEN | 570427 | 01844 | 10 | Solar | 05_01_602W2 | 11/21/2023 | 11/30/2023 | 7 | 4 | 3 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 748169 | 01510 | 11.4 | Solar | 05_05_115W52 | 01/29/2026 | 02/03/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AUBURN | 545446 | 01501 | 6 | Solar | 05_12_25W5 | 08/08/2023 | 08/11/2023 | 3 | 0 | 3 | 08/14/2023 | 08/14/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 9/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2023 | Connected |  | N
National Grid | WEBSTER | 593568 | 01570 | 0 | Solar | 05_12_52L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | WESTMINSTER | 652366 | 01473 | 3.8 | Solar | 05_14_3L4 | 11/14/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/14/2024 | 1/23/2026 | Y | EXP | 365 | 03/11/2025 | 03/24/2025 | 14 | 0 | 14 |  |  | 5/3/2025 | Connected |  | N
National Grid | WESTPORT | 671372 | 02790 | 10 | Solar | 05_14_59L3 | 02/11/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | MELROSE | 177002 | 02176 | 195 | Solar | 05_14_74L2 | 07/21/2016 | 07/21/2016 | 0 | 0 | 0 | 07/22/2016 | 07/22/2016 | 389 | 6 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2016 |  | 2/28/2018 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 177492 | 01930 | 7.6 | Solar | 05_01_216W5 | 12/13/2016 | 12/13/2016 | 6 | 6 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 |  | 12/18/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N
National Grid | LOWELL | 194034 | 01852 | 150 | Solar | 05_01_26W2 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 203677 | 01876 | 9.57 | Solar | 05_01_412L5 | 12/31/2018 | 01/11/2019 | 7 | 1 | 6 | 01/18/2019 | 01/18/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  | 2/12/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2019 | Connected |  | N
National Grid | METHUEN | 579357 | 01844 | 5.22 | Solar | 05_01_602W2 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/26/2024 | 3/19/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | CLINTON | 748001 | 01510 | 15.2 | Solar | 05_05_115W52 | 01/28/2026 | 02/02/2026 | 3 | 0 | 3 | 02/03/2026 | 02/03/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 560633 | 01501 | 9.57 | Solar | 05_12_25W5 | 10/04/2023 | 10/05/2023 | 2 | 1 | 1 | 10/06/2023 | 10/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2024 | Connected |  | N
National Grid | DUDLEY | 635534 | 01571 | 5.76 | Solar | 05_12_52L1 | 09/04/2024 | 09/06/2024 | 3 | 1 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | HUBBARDSTON | 653437 | 01452 | 5.76 | Solar | 05_14_3L4 | 11/18/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 55 | 33 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 684665 | 02790 | 23 | Solar | 05_14_59L3 | 04/11/2025 | 05/01/2025 | 13 | 10 | 3 | 05/02/2025 | 05/02/2025 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | MELROSE | 177887 | 02176 | 300 | Natural Gas | 05_14_74L2 | 04/11/2017 | 04/11/2017 | 40 | 40 | 0 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 4/17/2018 | N | EXP | 284 |  |  | 0 | 0 | 0 | 4/5/2018 | 4/5/2018 | 4/5/2018 | Connected |  | N
National Grid | GLOUCESTER | 178289 | 01930 | 11.4 | Solar | 05_01_216W5 | 03/28/2018 | 03/28/2018 | 7 | 7 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/3/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 204134 | 01852 | 333 | Solar | 05_01_26W2 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 208138 | 01876 | 10 | Solar | 05_01_412L5 | 02/19/2019 | 02/19/2019 | 0 | 0 | 0 | 02/20/2019 | 02/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/19/2019 | 11/5/2019 | Y | EXP | 257 | 09/17/2019 | 09/18/2019 | 1 | 0 | 1 |  |  | 9/23/2019 | Connected |  | N
National Grid | METHUEN | 599345 | 01844 | 0 | Solar | 05_01_602W2 | 03/26/2024 | 04/26/2024 | 22 | 20 | 2 | 04/29/2024 | 04/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2024 | Connected |  | N
National Grid | CLINTON | 748790 | 01510 | 11.4 | Solar | 05_05_115W52 | 02/03/2026 | 02/04/2026 | 4 | 0 | 4 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AUBURN | 603372 | 01501 | 7.54 | Solar | 05_12_25W5 | 04/19/2024 | 05/07/2024 | 13 | 11 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | DUDLEY | 640394 | 01571 | 3 | Solar | 05_12_52L1 | 09/24/2024 | 11/26/2024 | 28 | 27 | 1 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 09/24/2024 | 3/24/2026 | Y | EXP | 365 | 04/24/2025 | 08/06/2025 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 653277 | 01473 | 7.6 | Solar | 05_14_3L4 | 11/14/2024 | 01/16/2025 | 31 | 25 | 6 | 01/17/2025 | 01/17/2025 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 710883 | 02790 | 9.92 | Solar | 05_14_59L3 | 08/09/2025 | 08/14/2025 | 4 | 0 | 4 | 08/15/2025 | 08/15/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | MELROSE | 177993 | 02176 | 15.2 | Solar | 05_14_74L2 | 10/24/2017 | 10/24/2017 | 14 | 14 | 0 | 11/27/2017 | 11/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/1/2018 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | GLOUCESTER | 178323 | 01930 | 249.8 | Solar | 05_01_216W5 | 03/29/2018 | 03/29/2018 | 9 | 0 | 9 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  | 12/31/2020 | N | EXP | 373 |  |  | 0 | 0 | 0 |  |  | 2/19/2021 | Connected |  | N
National Grid | LOWELL | 312600 | 01852 | 10 | Solar | 05_01_26W2 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | TEWKSBURY | 207488 | 01876 | 10 | Solar | 05_01_412L5 | 01/30/2019 | 02/04/2019 | 3 | 3 | 0 | 02/05/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 | 01/30/2019 | 11/25/2019 | Y | EXP | 292 | 05/25/2019 | 07/12/2019 | 48 | 0 | 48 |  |  | 9/10/2019 | Connected |  | N
National Grid | METHUEN | 625690 | 01844 | 6 | Solar | 05_01_602W2 | 07/19/2024 | 08/05/2024 | 5 | 3 | 2 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 9/11/2025 | Y | EXP | 365 | 10/10/2024 | 10/31/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 175769 | 01510 | 4800 | Solar | 05_05_115W52 | 06/10/2014 | 06/10/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2014 | 07/21/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 12/31/2016 | N | STD | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 623061 | 01501 | 6 | Solar | 05_12_25W5 | 07/08/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 643700 | 01571 | 5.76 | Solar | 05_12_52L1 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 01/06/2025 | 02/11/2025 | 36 | 0 | 36 |  |  | 2/28/2025 | Connected |  | N
National Grid | GARDNER | 654034 | 01440 | 5.76 | Solar | 05_14_3L4 | 11/13/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | WESTPORT | 178363 | 02790 | 4920 | Solar | 05_14_59L4 | 03/30/2018 | 03/30/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 04/18/2019 | 260 | 9 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MELROSE | 184808 | 02176 | 25.2 | Solar | 05_14_74L2 | 05/08/2018 | 05/08/2018 | 6 | 0 | 6 | 05/17/2018 | 05/17/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 256639 | 01930 | 7.6 | Solar | 05_01_216W5 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/14/2019 | 10/21/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2021 | Connected |  | N
National Grid | LOWELL | 339198 | 01852 | 9.8 | Solar | 05_01_26W2 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 315053 | 01810 | 50 | Solar | 05_01_412L5 | 09/25/2020 | 10/06/2020 | 6 | 1 | 5 | 10/07/2020 | 10/07/2020 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | METHUEN | 626147 | 01844 | 6 | Solar | 05_01_602W2 | 07/22/2024 | 08/19/2024 | 7 | 5 | 2 | 08/20/2024 | 08/20/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | CLINTON | 175819 | 01510 | 2000 | Solar | 05_05_115W52 | 07/30/2015 | 07/30/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2015 | 09/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 07/30/2015 | 7/15/2017 | Y | STD | 333 | 03/01/2017 | 06/23/2017 | 80 | 0 | 80 | 6/27/2017 | 6/27/2017 | 7/31/2017 | Connected |  | N
National Grid | AUBURN | 644273 | 01501 | 5.76 | Solar | 05_12_25W5 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | WEBSTER | 645714 | 01570 | 10 | Solar | 05_12_52L1 | 10/10/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | WESTMINSTER | 657027 | 01473 | 7.6 | Solar | 05_14_3L4 | 11/26/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | WESTPORT | 175357 | 02790 | 30 | Solar | 05_14_59L5 | 09/08/2014 | 09/08/2014 | 17 | 14 | 3 | 10/02/2014 | 10/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/30/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 10/6/2014 | 10/6/2014 | 8/20/2015 | Connected |  | N
National Grid | MELROSE | 222991 | 02176 | 153.3 | Solar | 05_14_74L2 | 04/26/2019 | 05/16/2019 | 14 | 9 | 5 | 05/17/2019 | 05/17/2019 | 18 | 4 | 14 | 08/13/2019 | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  | 09/18/2019 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP | 734 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 497623 | 01930 | 18.27 | Solar | 05_01_216W5 | 02/01/2023 | 02/03/2023 | 3 | 2 | 1 | 02/06/2023 | 02/06/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 | 02/01/2023 | 3/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 344165 | 01852 | 2000 | Solar | 05_01_26W2 | 07/28/2021 | 08/23/2021 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2021 | 11/23/2021 | 79 | 59 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 329818 | 01876 | 15.2 | Solar | 05_01_412L5 | 12/05/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 4/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2022 | Connected |  | N
National Grid | METHUEN | 644276 | 01844 | 5.76 | Solar | 05_01_602W2 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | CLINTON | 176227 | 01510 | 10 | Solar | 05_05_115W52 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/01/2015 | 9/12/2016 | Y | EXP | 355 | 01/21/2016 | 01/28/2016 | 5 | 0 | 5 | 9/23/2015 | 9/23/2015 | 5/5/2016 | Connected |  | N
National Grid | MILLBURY | 652699 | 01527 | 5.76 | Solar | 05_12_25W5 | 11/07/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/07/2024 | 2/14/2026 | Y | EXP | 365 | 07/02/2025 | 10/11/2025 | 102 | 0 | 102 |  |  | 11/14/2025 | Connected |  | N
National Grid | DUDLEY | 656918 | 01571 | 6.282 | Solar | 05_12_52L1 | 11/27/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | GARDNER | 658318 | 01440 | 3.8 | Solar | 05_14_3L4 | 12/04/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | WESTPORT | 175492 | 02790 | 1800 | Solar | 05_14_59L5 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/03/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 | 07/25/2014 | 3/1/2016 | Y | STD | 354 | 10/28/2015 | 07/13/2017 | 424 | 0 | 424 | 5/24/2017 | 5/24/2017 | 6/26/2017 | Connected |  | N
National Grid | MELROSE | 327655 | 02176 | 7.6 | Solar | 05_14_74L2 | 12/08/2020 | 12/09/2020 | 0 | 0 | 0 | 12/10/2020 | 12/10/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 12/08/2020 |  | Y | EXP | 365 | 05/05/2021 | 06/18/2021 | 44 | 0 | 44 |  |  | 8/24/2021 | Connected |  | N
National Grid | GLOUCESTER | 521794 | 01930 | 13 | Solar | 05_01_216W5 | 04/28/2023 | 05/08/2023 | 7 | 5 | 2 | 05/09/2023 | 05/09/2023 | 65 | 47 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 9/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2023 | Connected |  | N
National Grid | LOWELL | 358733 | 01852 | 133.2 | Solar | 05_01_26W2 | 09/03/2021 | 05/12/2022 | 172 | 162 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/25/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | ANDOVER | 332213 | 01810 | 7.6 | Solar | 05_01_412L5 | 01/12/2021 | 01/15/2021 | 2 | 0 | 2 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/12/2021 | 3/8/2022 | Y | EXP | 365 | 09/23/2021 | 01/19/2022 | 119 | 4 | 115 |  |  | 2/5/2022 | Connected |  | N
National Grid | METHUEN | 656989 | 01844 | 7.6 | Solar | 05_01_602W2 | 11/26/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | CLINTON | 176902 | 01510 | 750 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N
National Grid | MILLBURY | 684394 | 01527 | 7.6 | Solar | 05_12_25W5 | 04/10/2025 | 05/30/2025 | 1 | 0 | 1 | 06/02/2025 | 06/02/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 662099 | 01570 | 3.8 | Solar | 05_12_52L1 | 12/20/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | GARDNER | 661851 | 01440 | 3.8 | Solar | 05_14_3L4 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 175822 | 02790 | 120 | Solar | 05_14_59L5 | 08/03/2015 | 08/03/2015 | 10 | 10 | 0 | 08/17/2015 | 08/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 |  | 2/15/2016 | N | EXP | 116 |  |  | 0 | 0 | 0 | 2/11/2016 | 2/11/2016 | 2/17/2016 | Connected |  | N
National Grid | MELROSE | 348265 | 02176 | 499.9 | Solar | 05_14_74L2 | 06/10/2021 |  | 315 | 315 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 641059 | 01930 | 5 | Solar | 05_01_216W5 | 09/19/2024 | 10/15/2024 | 3 | 0 | 3 | 10/16/2024 | 10/16/2024 | 57 | 40 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 09/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | LOWELL | 432998 | 01852 | 100 | Solar | 05_01_26W2 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 346007 | 01876 | 7.6 | Solar | 05_01_412L5 | 03/19/2021 | 03/22/2021 | 0 | 0 | 0 | 03/23/2021 | 03/23/2021 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 664441 | 01844 | 0 | Solar | 05_01_602W2 | 01/08/2025 | 02/17/2025 | 7 | 2 | 5 | 02/18/2025 | 02/18/2025 | 15 | 0 | 15 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2025 | Connected |  | N
National Grid | CLINTON | 176895 | 01510 | 1500 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/6/2018 | Y | STD | 842 |  |  | 0 | 0 | 0 |  |  | 12/3/2018 | Connected |  | N
National Grid | AUBURN | 704751 | 01501 | 15.2 | Solar | 05_12_26L1 | 07/14/2025 | 07/15/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DUDLEY | 668880 | 01571 | 3.8 | Solar | 05_12_52L1 | 02/03/2025 | 03/11/2025 | 14 | 9 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/03/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 11/24/2025 | 28 | 0 | 28 |  |  | 12/10/2025 | Connected |  | N
National Grid | HUBBARDSTON | 663246 | 01452 | 3.8 | Solar | 05_14_3L4 | 01/10/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | WESTPORT | 176048 | 02790 | 300 | Solar | 05_14_59L5 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 348029 | 01983 | 7.6 | Solar | 05_14_74L2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 05/04/2021 | 2/28/2023 | Y | EXP | 365 | 11/25/2021 | 01/24/2022 | 61 | 0 | 61 |  |  | 3/9/2022 | Connected |  | N
National Grid | GLOUCESTER | 649301 | 01930 | 5.76 | Solar | 05_01_216W5 | 11/05/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 11/05/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 455849 | 01852 | 299.7 | Solar | 05_01_26W2 | 05/05/2023 |  | 120 | 112 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 442567 | 01876 | 15.2 | Solar | 05_01_412L5 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2022 | Connected |  | N
National Grid | METHUEN | 666513 | 01844 | 23 | Solar | 05_01_602W2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 176894 | 01510 | 4000.002 | Solar | 05_05_115W52 | 01/22/2016 | 01/22/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2016 | 03/18/2016 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 | 01/22/2016 | 12/5/2018 | Y | STD | 841 | 05/05/2018 | 10/03/2018 | 151 | 0 | 151 |  |  | 11/30/2018 | Connected |  | N
National Grid | AUBURN | 711334 | 01501 | 11.5 | Battery Add-On | 05_12_26L1 | 08/12/2025 | 08/18/2025 | 4 | 0 | 4 | 08/19/2025 | 08/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 715316 | 01571 | 20 | Solar | 05_12_52L1 | 08/28/2025 | 09/05/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | WESTMINSTER | 674880 | 01473 | 9.86 | Solar | 05_14_3L4 | 02/28/2025 | 03/12/2025 | 2 | 1 | 1 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/28/2025 | 5/29/2026 | Y | EXP | 365 | 09/17/2025 | 09/16/2025 | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | WESTPORT | 176478 | 02790 | 133.2 | Solar | 05_14_59L5 | 05/18/2016 | 05/18/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 428 | 0 | 428 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 |  | 2/28/2018 | N | EXP | 617 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 361148 | 01983 | 7.6 | Solar | 05_14_74L2 | 07/04/2021 | 07/07/2021 | 2 | 0 | 2 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/04/2021 | 3/10/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2022 | Connected |  | Y
National Grid | GLOUCESTER | 654500 | 01930 | 10 | Solar | 05_01_216W5 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LOWELL | 513820 | 01852 | 0 | Other | 05_01_26W2 | 07/11/2023 | 08/25/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 11/28/2023 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 477663 | 01876 | 15.2 | Solar | 05_01_412L5 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2023 | Connected |  | N
National Grid | METHUEN | 686395 | 01844 | 3.9 | Solar | 05_01_602W2 | 04/21/2025 | 10/09/2025 | 2 | 0 | 2 | 10/15/2025 | 10/15/2025 | 55 | 38 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | CLINTON | 176922 | 01510 | 996 | Solar | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N
National Grid | AUBURN | 745104 | 01501 | 6.84 | Solar | 05_12_26L1 | 02/05/2026 | 02/09/2026 | 2 | 0 | 2 | 02/10/2026 | 02/10/2026 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUDLEY | 644938 | 01571 | 4.225 | Solar | 05_12_5C2 | 10/03/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/03/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTMINSTER | 647611 | 01473 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 405741 | 02720 | 0 | Battery Add-On | 05_14_59L5 | 01/23/2022 | 01/31/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 03/02/2022 | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 365469 | 01983 | 7.6 | Solar | 05_14_74L2 | 07/13/2021 | 07/16/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 | 07/13/2021 | 8/16/2024 | Y | EXP | 365 | 01/18/2022 | 02/22/2022 | 36 | 0 | 36 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 656839 | 02148 | 5.76 | Solar | 05_01_216W5 | 11/25/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 522113 | 01852 | 15.08 | Solar | 05_01_26W2 | 11/29/2023 | 05/05/2023 | 7 | 6 | 1 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | TEWKSBURY | 483367 | 01876 | 7.6 | Solar | 05_01_412L5 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 89 | 65 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y
National Grid | METHUEN | 692468 | 01844 | 3.8 | Solar | 05_01_602W2 | 05/19/2025 | 07/30/2025 | 3 | 0 | 3 | 07/31/2025 | 07/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/19/2025 | 9/19/2026 | Y | EXP | 365 | 12/31/2025 | 01/30/2026 | 31 | 0 | 31 |  |  | 2/5/2026 | Connected |  | N
National Grid | CLINTON | 176921 | 01510 | 996 | Solar | 05_05_115W52 | 11/12/2015 | 11/12/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 12/14/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 | 11/12/2015 | 12/30/2017 | Y | STD | 522 | 04/14/2017 | 12/27/2017 | 170 | 0 | 170 | 12/29/2017 | 12/29/2017 | 12/30/2017 | Connected |  | N
National Grid | AUBURN | 175550 | 01501 | 33.3 | Solar | 05_12_26L1 | 04/11/2014 | 04/11/2014 | 6 | 0 | 6 | 04/23/2014 | 04/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 8/29/2014 | N | EXP | 18 |  |  | 0 | 0 | 0 | 6/17/2014 | 6/17/2014 | 9/2/2014 | Connected |  | N
National Grid | DUDLEY | 174340 | 01571 | 50 | Solar | 05_12_5C5 | 12/13/2011 | 12/13/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2012 |  | 3/30/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 7/18/2012 | Connected |  | N
National Grid | GARDNER | 647609 | 01440 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 586370 | 02720 | 2890 | Battery Add-On | 05_14_59L5 | 02/01/2024 |  | 264 | 254 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 392129 | 01983 | 7.6 | Solar | 05_14_74L2 | 10/29/2021 | 11/09/2021 | 5 | 5 | 0 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2023 | Connected |  | N
National Grid | MALDEN | 668947 | 02148 | 5 | Solar | 05_01_216W5 | 01/30/2025 | 04/25/2025 | 14 | 11 | 3 | 04/28/2025 | 04/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 | 01/30/2025 | 7/3/2026 | Y | EXP | 365 | 09/05/2025 | 09/04/2025 | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | LOWELL | 524124 | 01852 | 8.41 | Solar | 05_01_26W2 | 05/16/2023 | 05/30/2023 | 9 | 8 | 1 | 05/31/2023 | 05/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 489902 | 01810 | 15.2 | Solar | 05_01_412L5 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | METHUEN | 692073 | 01844 | 10 | Solar | 05_01_602W2 | 06/02/2025 | 06/16/2025 | 2 | 0 | 2 | 07/09/2025 | 07/09/2025 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | CLINTON | 176941 | 01510 | 7.6 | Solar | 05_05_115W52 | 12/19/2016 | 12/19/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 | 12/19/2016 | 2/28/2018 | Y | EXP | 421 | 09/15/2017 | 12/11/2017 | 53 | 0 | 53 | 2/20/2018 | 2/20/2018 | 3/6/2018 | Connected |  | N
National Grid | AUBURN | 177483 | 01501 | 19 | Solar | 05_12_26L1 | 09/22/2016 | 09/22/2016 | 2 | 2 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2016 |  | 10/13/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 9/26/2017 | 9/26/2017 | 9/26/2017 | Connected |  | N
National Grid | DUDLEY | 185756 | 01571 | 150 | Solar | 05_12_5J10 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/31/2018 | 05/31/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2018 |  | 12/2/2019 | N | EXP | 536 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | GARDNER | 647617 | 01440 | 0 | Hydro | 05_14_3L5 | 02/04/2025 | 03/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2025 | 03/31/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | FALL RIVER | 587585 | 02721 | 23 | Solar | 05_14_59L5 | 02/02/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 405990 | 01983 | 0 | Battery Add-On | 05_14_74L2 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/14/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 686255 | 02148 | 15.76 | Solar | 05_01_216W5 | 04/18/2025 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 557228 | 01852 | 12.18 | Solar | 05_01_26W2 | 09/21/2023 | 09/21/2023 | 0 | 0 | 0 | 09/22/2023 | 09/22/2023 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N
National Grid | ANDOVER | 517520 | 01810 | 10 | Solar | 05_01_412L5 | 08/22/2023 | 04/15/2023 | 5 | 4 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2023 | 08/22/2023 | 10/23/2024 | Y | EXP | 365 | 03/13/2024 | 03/22/2024 | 10 | 0 | 10 |  |  | 3/25/2024 | Connected |  | N
National Grid | METHUEN | 693699 | 01844 | 3.8 | Solar | 05_01_602W2 | 05/27/2025 | 07/03/2025 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | CLINTON | 176947 | 01510 | 11.4 | Solar | 05_05_115W52 | 03/06/2017 | 03/06/2017 | 8 | 7 | 1 | 03/17/2017 | 03/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 |  | 1/21/2020 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 1/11/2020 | Connected |  | N
National Grid | AUBURN | 178107 | 01501 | 103.5 | Solar | 05_12_26L1 | 11/03/2017 | 11/03/2017 | 41 | 41 | 0 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 9/16/2019 | N | EXP | 616 |  |  | 0 | 0 | 0 |  |  | 9/23/2019 | Connected |  | N
National Grid | DUDLEY | 587973 | 01571 | 550 | Natural Gas | 05_12_5J9 | 02/28/2024 | 08/06/2024 | 110 | 101 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2024 | 08/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 175719 | 01452 | 120.9 | Solar | 05_14_3L5 | 12/29/2014 | 12/29/2014 | 8 | 6 | 2 | 01/12/2015 | 01/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/29/2014 | 5/31/2015 | Y | EXP | 117 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 11/25/2015 | Connected |  | N
National Grid | WESTPORT | 609316 | 02790 | 23 | Solar | 05_14_59L5 | 05/07/2024 | 05/17/2024 | 9 | 7 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 414167 | 01983 | 10 | Solar | 05_14_74L2 | 03/22/2022 |  | 328 | 156 | 172 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 693561 | 02148 | 11.5 | Solar | 05_01_216W5 | 05/22/2025 | 06/04/2025 | 2 | 0 | 2 | 06/11/2025 | 06/11/2025 | 48 | 34 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 | 05/22/2025 | 9/2/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 12/3/2025 | Connected |  | N
National Grid | LOWELL | 569868 | 01852 | 10 | Solar | 05_01_26W2 | 12/06/2023 | 12/14/2023 | 6 | 3 | 3 | 12/15/2023 | 12/15/2023 | 41 | 19 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 523805 | 01810 | 6.67 | Solar | 05_01_412L5 | 05/08/2023 | 05/12/2023 | 4 | 2 | 2 | 05/15/2023 | 05/15/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/08/2023 | 7/12/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N
National Grid | METHUEN | 693377 | 01844 | 11.4 | Solar | 05_01_602W2 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 141 | 131 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CLINTON | 177142 | 01510 | 6 | Solar | 05_05_115W52 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2016 | 05/27/2016 | 6/6/2017 | Y | EXP | 35 | 09/01/2016 | 09/12/2016 | 6 | 0 | 6 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N
National Grid | AUBURN | 191835 | 01501 | 22.8 | Solar | 05_12_26L1 | 07/25/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 47 | 36 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 12/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2019 | Connected |  | N
National Grid | DUDLEY | 667538 | 01571 | 7.6 | Solar | 05_12_64J1 | 01/31/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 120 | 104 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 177150 | 01440 | 7.56 | Solar | 05_14_3L5 | 08/10/2016 | 08/10/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 | 08/10/2016 | 8/16/2017 | Y | EXP | 362 | 12/14/2016 | 01/06/2017 | 15 | 0 | 15 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | WESTPORT | 645946 | 02790 | 10 | Solar | 05_14_59L5 | 10/10/2024 | 10/28/2024 | 12 | 10 | 2 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | TOPSFIELD | 529105 | 01983 | 3.8 | Solar | 05_14_74L2 | 06/21/2023 | 06/26/2023 | 3 | 0 | 3 | 06/27/2023 | 06/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 659631 | 02155 | 27.55 | Solar | 05_01_216W6 | 12/16/2024 | 01/28/2025 | 28 | 26 | 2 | 01/29/2025 | 01/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | LOWELL | 572356 | 01852 | 7.6 | Solar | 05_01_26W2 | 01/09/2024 | 01/24/2024 | 11 | 7 | 4 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/09/2024 | 4/17/2025 | Y | EXP | 365 | 05/22/2024 | 09/07/2024 | 109 | 0 | 109 |  |  | 9/17/2024 | Connected |  | N
National Grid | TEWKSBURY | 535016 | 01876 | 15.2 | Solar | 05_01_412L5 | 06/19/2023 | 06/26/2023 | 5 | 2 | 3 | 06/27/2023 | 06/27/2023 | 75 | 61 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | METHUEN | 318674 | 01844 | 0 | Other | 05_01_602W3 | 04/06/2021 | 04/30/2021 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOLTON | 177134 | 01740 | 15.2 | Solar | 05_05_115W52 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 11/17/2017 | Connected |  | N
National Grid | AUBURN | 203602 | 01501 | 10 | Solar | 05_12_26L1 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 242 | 19 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 | 12/18/2018 | 3/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2020 | Connected |  | N
National Grid | DUDLEY | 561812 | 01571 | 6.3 | Solar | 05_12_64J1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 |  | 2/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | WESTMINSTER | 370918 | 01473 | 100 | Solar | 05_14_3L5 | 08/16/2021 | 09/10/2021 | 18 | 8 | 10 | 09/13/2021 | 09/13/2021 | 66 | 13 | 53 | 12/30/2021 | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 01/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/3/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2022 | Connected |  | N
National Grid | WESTPORT | 667034 | 02790 | 10 | Solar | 05_14_59L5 | 02/03/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 571180 | 01983 | 10 | Solar | 05_14_74L2 | 12/08/2023 | 12/13/2023 | 3 | 1 | 2 | 12/14/2023 | 12/14/2023 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 724889 | 02155 |  | Battery Add-On | 05_01_216W6 | 10/15/2025 | 10/24/2025 | 6 | 2 | 4 | 10/27/2025 | 10/27/2025 | 48 | 33 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 587534 | 01852 | 200 | Solar | 05_01_26W2 | 03/14/2024 |  | 56 | 50 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 548244 | 01876 | 6 | Solar | 05_01_412L5 | 08/23/2023 | 08/24/2023 | 1 | 0 | 1 | 08/25/2023 | 08/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 12/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | METHUEN | 487745 | 01844 | 2000 | Solar | 05_01_602W3 | 01/27/2023 | 02/22/2023 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2023 | 03/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BOLTON | 177294 | 01740 | 17.6 | Solar | 05_05_115W52 | 08/24/2016 | 08/24/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/3/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 208665 | 01501 | 15 | Solar | 05_12_26L1 | 02/06/2019 | 02/12/2019 | 3 | 0 | 3 | 02/13/2019 | 02/13/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 562644 | 01571 | 2.52 | Solar | 05_12_64J1 | 12/13/2023 | 12/20/2023 | 5 | 3 | 2 | 12/21/2023 | 12/21/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 |  | 2/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2024 | Connected |  | N
National Grid | WESTMINSTER | 642148 | 01473 | 3.84 | Solar | 05_14_3L5 | 09/23/2024 | 09/27/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 | 09/23/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WESTPORT | 724788 | 02790 | 5.76 | Solar | 05_14_59L5 | 10/08/2025 | 10/22/2025 | 9 | 8 | 1 | 10/23/2025 | 10/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | N
National Grid | TOPSFIELD | 646050 | 01983 | 6 | Solar | 05_14_74L2 | 10/09/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/09/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | MEDFORD | 750991 | 02155 | 10 | Solar | 05_01_216W6 | 02/20/2026 | 02/26/2026 | 4 | 0 | 4 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 588475 | 01852 | 125 | Solar | 05_01_26W2 | 04/17/2024 |  | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 551716 | 01876 | 15.2 | Solar | 05_01_412L5 | 09/05/2023 | 09/07/2023 | 3 | 1 | 2 | 09/08/2023 | 09/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 |  | 11/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2023 | Connected |  | N
National Grid | METHUEN | 661234 | 01844 | 5000 | Solar | 05_01_602W3 | 04/28/2025 | 11/21/2025 | 142 | 132 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 01/06/2026 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CLINTON | 178128 | 01510 | 7.6 | Solar | 05_05_115W52 | 07/11/2017 | 07/11/2017 | 5 | 5 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 10/23/2017 | 10/23/2017 | 10/23/2017 | Connected |  | N
National Grid | AUBURN | 208186 | 01501 | 10 | Solar | 05_12_26L1 | 02/13/2019 | 02/19/2019 | 3 | 3 | 0 | 02/20/2019 | 02/20/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 | 02/13/2019 | 10/30/2019 | Y | EXP | 236 | 06/28/2019 | 07/24/2019 | 26 | 0 | 26 |  |  | 7/27/2019 | Connected |  | N
National Grid | DUDLEY | 637288 | 01571 | 6.98 | Solar | 05_12_64J1 | 09/03/2024 | 12/19/2024 | 29 | 23 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 09/03/2024 | 2/10/2026 | Y | EXP | 365 | 05/07/2025 | 08/06/2025 | 92 | 0 | 92 |  |  | 8/15/2025 | Connected |  | N
National Grid | WESTMINSTER | 656613 | 01473 | 7.6 | Solar | 05_14_3L5 | 11/25/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | WESTPORT | 724647 | 02790 | 0 | Solar | 05_14_59L6 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TOPSFIELD | 648151 | 01983 | 5.76 | Solar | 05_14_74L2 | 10/30/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174686 | 02155 | 5.3 | Solar | 05_01_216W6 | 01/24/2011 | 01/24/2011 | 8 | 0 | 8 | 02/04/2011 | 02/04/2011 | 451 | 0 | 451 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 608555 | 01852 | 10 | Solar | 05_01_26W2 | 05/03/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 565284 | 01810 | 6 | Solar | 05_01_412L5 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/01/2023 | 1/1/2025 | Y | EXP | 365 | 05/02/2024 | 06/06/2024 | 36 | 0 | 36 |  |  | 6/13/2024 | Connected |  | N
National Grid | METHUEN | 725531 | 01844 | 50 | Solar | 05_01_602W3 | 10/22/2025 | 12/30/2025 | 46 | 36 | 10 | 12/31/2025 | 12/31/2025 | 45 | 31 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HARVARD | 178175 | 01451 | 15.2 | Solar | 05_05_115W52 | 03/23/2018 | 03/23/2018 | 2 | 1 | 1 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 3/31/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 10/2/2018 | Connected |  | N
National Grid | AUBURN | 214988 | 01501 | 20.8 | Solar | 05_12_26L1 | 03/22/2019 | 03/28/2019 | 3 | 0 | 3 | 03/29/2019 | 03/29/2019 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 4/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | WEBSTER | 357707 | 01570 | 66.6 | Solar | 05_12_64J2 | 05/17/2021 | 05/11/2022 | 248 | 244 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 05/17/2021 | 7/11/2024 | Y | EXP | 9 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | WESTMINSTER | 658847 | 01473 | 3.8 | Solar | 05_14_3L5 | 12/05/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 730098 | 02790 | 10 | Solar | 05_14_59L6 | 10/29/2025 | 10/30/2025 | 4 | 0 | 4 | 12/10/2025 | 12/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TOPSFIELD | 658199 | 01983 | 5.76 | Solar | 05_14_74L2 | 12/04/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | MEDFORD | 174815 | 02155 | 995 | Solar | 05_01_216W6 | 07/31/2013 | 07/31/2013 | 7 | 0 | 7 | 08/12/2013 | 08/12/2013 | 0 | 0 | 0 | 01/14/2014 | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 03/05/2014 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 3/14/2014 |  | 12/31/2013 | N | EXP | 73 |  |  | 0 | 0 | 0 | 12/24/2014 | 12/24/2014 | 12/30/2014 | Connected |  | N
National Grid | LOWELL | 658756 | 01852 | 7.6 | Solar | 05_01_26W2 | 12/05/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/05/2024 | 2/13/2026 | Y | EXP | 365 | 05/22/2025 | 05/21/2025 | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | ANDOVER | 564963 | 01810 | 6 | Solar | 05_01_412L5 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 46 | 21 | 25 | 04/01/2024 | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 05/13/2024 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/23/2025 | N | EXP | 365 | 07/25/2024 | 12/19/2024 | 148 | 0 | 148 |  |  | 12/31/2024 | Connected |  | N
National Grid | METHUEN | 731396 | 01844 | 9.5 | Solar | 05_01_602W3 | 11/06/2025 | 11/10/2025 | 2 | 0 | 2 | 11/12/2025 | 11/12/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 11/06/2025 | 1/30/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BOLTON | 178687 | 01740 | 3500 | Solar | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/5/2018 | Y | STD | 261 | 08/03/2018 | 10/09/2018 | 67 | 0 | 67 |  |  | 11/27/2018 | Connected |  | N
National Grid | AUBURN | 243633 | 01501 | 9.84 | Solar | 05_12_26L1 | 07/19/2019 | 07/26/2019 | 5 | 5 | 0 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 11/11/2019 | N | EXP | 96 |  |  | 0 | 0 | 0 |  |  | 10/16/2019 | Connected |  | N
National Grid | DUDLEY | 661943 | 01571 | 5.76 | Solar | 05_12_64J3 | 12/20/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | WESTMINSTER | 660925 | 01473 | 7.6 | Solar | 05_14_3L5 | 12/16/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/16/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 12/02/2025 | 174 | 0 | 174 |  |  | 12/15/2025 | Connected |  | N
National Grid | WESTPORT | 738704 | 02790 | 22.8 | Solar | 05_14_59L6 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | TOPSFIELD | 668418 | 01983 | 3.8 | Solar | 05_14_74L2 | 01/28/2025 | 03/18/2025 | 25 | 20 | 5 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 | 01/28/2025 | 4/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 175571 | 02155 | 6 | Solar | 05_01_216W6 | 10/10/2014 | 10/10/2014 | 10 | 7 | 3 | 10/28/2014 | 10/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 | 10/10/2014 | 4/22/2015 | Y | EXP | 153 | 03/11/2015 | 03/16/2015 | 3 | 0 | 3 | 3/12/2015 | 3/12/2015 | 6/1/2015 | Connected |  | N
National Grid | LOWELL | 696813 | 01852 | 15.2 | Solar | 05_01_26W2 | 06/10/2025 | 06/17/2025 | 5 | 0 | 5 | 06/18/2025 | 06/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | ANDOVER | 577506 | 01810 | 7.6 | Solar | 05_01_412L5 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | METHUEN | 739400 | 01844 | 7.6 | Solar | 05_01_602W3 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 178686 | 01451 | 1500 | Solar | 05_05_115W52 | 12/19/2017 | 01/22/2016 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 | 12/19/2017 | 12/6/2018 | Y | STD | 262 | 08/03/2018 | 02/20/2020 | 566 | 0 | 566 |  |  | 12/6/2018 | Connected |  | N
National Grid | AUBURN | 243526 | 01501 | 4000 | Solar | 05_12_26L1 | 08/15/2019 | 09/12/2019 | 19 | 11 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2019 | 10/07/2019 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 664919 | 01571 | 10 | Solar | 05_12_64J3 | 01/10/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 668859 | 01473 | 6 | Solar | 05_14_3L5 | 01/30/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 749645 | 02790 | 20.9 | Solar | 05_14_59L6 | 02/12/2026 |  | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | TOPSFIELD | 685217 | 01983 | 10 | Solar | 05_14_74L2 | 04/15/2025 | 05/13/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/15/2025 | 7/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | SOMERVILLE | 177884 | 02145 | 38 | Solar | 05_01_216W6 | 10/19/2017 | 10/19/2017 | 10 | 10 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 10/25/2018 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 690816 | 01852 | 499 | Other | 05_01_26W3 | 07/11/2025 | 08/29/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 10/15/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | ANDOVER | 585721 | 01810 | 8.12 | Solar | 05_01_412L5 | 02/19/2024 | 04/18/2024 | 43 | 40 | 3 | 04/19/2024 | 04/19/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 | 02/19/2024 | 6/21/2025 | Y | EXP | 365 | 07/03/2024 | 07/02/2024 | 0 | 0 | 0 |  |  | 7/16/2024 | Connected |  | N
National Grid | METHUEN | 174307 | 01844 | 500 | Solar | 05_01_602W3 | 01/10/2012 | 01/10/2012 | 23 | 0 | 23 | 02/13/2012 | 02/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2012 |  | 7/1/2012 | N | EXP | 8 |  |  | 0 | 0 | 0 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N
National Grid | CLINTON | 178798 | 01510 | 6 | Solar | 05_05_115W52 | 02/14/2018 | 02/14/2018 | 18 | 0 | 18 | 03/28/2018 | 03/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2018 |  | 2/19/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 393102 | 01501 | 11.4 | Solar | 05_12_26L1 | 11/03/2021 | 11/04/2021 | 1 | 0 | 1 | 11/05/2021 | 11/05/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | DUDLEY | 223134 | 01571 | 106 | Solar | 05_12_64J5 | 04/27/2019 | 05/21/2019 | 16 | 11 | 5 | 05/22/2019 | 05/22/2019 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 |  | 6/21/2021 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | WESTMINSTER | 671248 | 01473 | 5.76 | Solar | 05_14_43L2 | 02/10/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 70 | 52 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTPORT | 175499 | 02790 | 29.455 | Solar | 05_14_59L6 | 09/26/2014 | 09/26/2014 | 6 | 0 | 6 | 10/07/2014 | 10/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 | 09/26/2014 | 12/31/2016 | Y | EXP | 641 | 10/22/2015 | 02/01/2016 | 67 | 0 | 67 | 5/17/2016 | 5/17/2016 | 6/2/2016 | Connected |  | N
National Grid | TOPSFIELD | 637381 | 01983 | 7.6 | Solar | 05_14_74L3 | 09/03/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/03/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 188838 | 02155 | 1560 | Solar | 05_01_216W6 | 07/16/2018 | 07/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/20/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 704637 | 01844 | 480 | Solar | 05_01_26W3 | 10/29/2025 | 11/10/2025 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ANDOVER | 592892 | 01810 | 6 | Solar | 05_01_412L5 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/21/2024 | 7/26/2025 | Y | EXP | 365 | 06/28/2024 | 07/02/2024 | 5 | 0 | 5 |  |  | 11/14/2024 | Connected |  | N
National Grid | METHUEN | 175778 | 01844 | 480 | Solar | 05_01_602W3 | 08/20/2014 | 08/20/2014 | 7 | 0 | 7 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 | 10/21/2014 | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/26/2014 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 12/31/2014 | 08/20/2014 | 9/1/2015 | Y | EXP | 244 | 09/18/2015 | 11/03/2015 | 31 | 0 | 31 | 10/23/2015 | 10/23/2015 | 11/16/2015 | Connected |  | N
National Grid | BOLTON | 186693 | 01740 | 3300 | Solar | 05_05_115W52 | 08/07/2018 | 09/21/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 11/01/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 495464 | 01501 | 16.53 | Solar | 05_12_26L1 | 01/27/2023 | 02/03/2023 | 5 | 2 | 3 | 02/06/2023 | 02/06/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 3/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2023 | Connected |  | N
National Grid | DUDLEY | 394755 | 01571 | 0 | Solar | 05_12_64J5 | 12/16/2021 | 01/05/2022 | 13 | 10 | 3 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2022 |  | 3/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | WESTMINSTER | 710789 | 01473 | 10 | Solar | 05_14_43L2 | 08/08/2025 | 10/20/2025 | 4 | 0 | 4 | 10/21/2025 | 10/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 | 08/08/2025 | 12/17/2026 | Y | EXP | 365 | 01/28/2026 |  | 38 | 0 | 38 |  |  |  | Construction |  | N
National Grid | WESTPORT | 177121 | 02790 | 540 | Solar | 05_14_59L6 | 10/19/2016 | 10/19/2016 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 02/03/2017 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 656139 | 01983 | 6.175 | Solar | 05_14_74L3 | 11/28/2024 | 03/17/2025 | 28 | 26 | 2 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 196197 | 02155 | 15.2 | Solar | 05_01_216W6 | 09/25/2018 | 10/04/2018 | 12 | 11 | 1 | 10/11/2018 | 10/11/2018 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | HAVERHILL | 176827 | 01832 | 10 | Solar | 05_01_26W3 | 01/18/2016 | 01/18/2016 | 5 | 5 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 1/30/2017 | N | EXP | 32 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 609568 | 01810 | 3.8 | Solar | 05_01_412L5 | 05/08/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/08/2024 | 6/14/2025 | Y | EXP | 365 | 09/19/2024 | 09/30/2024 | 12 | 0 | 12 |  |  | 11/5/2024 | Connected |  | N
National Grid | LAWRENCE | 176816 | 01841 | 2200 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 191028 | 01740 | 233.1 | Solar | 05_05_115W52 | 08/27/2018 | 09/10/2018 | 8 | 1 | 7 | 09/11/2018 | 09/11/2018 | 63 | 30 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 569963 | 01501 | 2500 | Solar | 05_12_26L1 | 06/07/2024 |  | 277 | 267 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUDLEY | 177360 | 01571 | 43.2 | Solar | 05_12_67J3 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/28/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/23/2017 | 5/23/2017 | 5/23/2017 | Connected |  | N
National Grid | WESTMINSTER | 747031 | 01473 | 11.2 | Solar | 05_14_43L2 | 01/23/2026 | 01/30/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 177730 | 02722 | 20 | Solar | 05_14_59L6 | 10/05/2017 | 10/05/2017 | 0 | 0 | 0 | 02/13/2018 | 02/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 10/10/2018 | N | EXP | 239 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | TOPSFIELD | 668860 | 01983 | 10 | Solar | 05_14_74L3 | 01/30/2025 | 03/28/2025 | 6 | 1 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MELROSE | 212493 | 02176 | 0 | Solar | 05_01_216W6 | 03/05/2019 | 03/12/2019 | 4 | 0 | 4 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 03/05/2019 | 3/6/2020 | Y | EXP | 365 | 09/05/2019 | 09/11/2019 | 6 | 0 | 6 |  |  | 2/4/2020 | Connected |  | N
National Grid | HAVERHILL | 177912 | 01832 | 9 | Solar | 05_01_26W3 | 08/17/2017 | 08/17/2017 | 8 | 2 | 6 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/22/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 613091 | 01810 | 9.56 | Solar | 05_01_412L5 | 05/23/2024 | 06/04/2024 | 3 | 0 | 3 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/23/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/21/2024 | 50 | 0 | 50 |  |  | 1/29/2025 | Connected |  | N
National Grid | METHUEN | 176815 | 01844 | 2200 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 12/28/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 196024 | 01451 | 7.6 | Solar | 05_05_115W52 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 609102 | 01501 | 15.2 | Solar | 05_12_26L1 | 05/06/2024 | 05/08/2024 | 2 | 0 | 2 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 10/01/2024 | 01/02/2025 | 94 | 0 | 94 |  |  | 1/13/2025 | Connected |  | N
National Grid | DUDLEY | 327303 | 01571 | 43.2 | Solar | 05_12_67J3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  | 3/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 178362 | 01473 | 3.8 | Solar | 05_14_43L2 | 03/30/2018 | 03/30/2018 | 5 | 5 | 0 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 4/7/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 243231 | 02790 | 10 | Solar | 05_14_59L6 | 08/15/2019 | 08/21/2019 | 3 | 0 | 3 | 08/22/2019 | 08/22/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/15/2019 | 8/15/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | TOPSFIELD | 692028 | 01983 | 7.6 | Solar | 05_14_74L3 | 05/26/2025 | 06/16/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MELROSE | 243391 | 02176 | 0 | Solar | 05_01_216W6 | 07/17/2019 | 07/18/2019 | 0 | 0 | 0 | 07/19/2019 | 07/19/2019 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 | 07/17/2019 | 3/4/2020 | Y | EXP | 211 | 11/14/2019 | 11/26/2019 | 12 | 0 | 12 |  |  | 1/28/2020 | Connected |  | N
National Grid | METHUEN | 178217 | 01844 | 3.8 | Solar | 05_01_26W3 | 04/13/2018 | 04/13/2018 | 9 | 0 | 9 | 07/16/2018 | 07/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 4/21/2019 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 677277 | 01810 | 7.6 | Solar | 05_01_412L5 | 03/11/2025 | 03/25/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | METHUEN | 176813 | 01844 | 2000 | Solar | 05_01_602W3 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/07/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 199068 | 01740 | 10 | Solar | 05_05_115W52 | 10/21/2018 | 11/08/2018 | 12 | 6 | 6 | 11/09/2018 | 11/09/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | AUBURN | 611833 | 01501 | 6.38 | Solar | 05_12_26L1 | 05/20/2024 | 05/29/2024 | 2 | 1 | 1 | 05/30/2024 | 05/30/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/20/2024 | 9/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | Y
National Grid | WEBSTER | 349034 | 01570 | 9.8 | Solar | 05_12_67J4 | 04/15/2021 | 04/19/2021 | 1 | 0 | 1 | 04/20/2021 | 04/20/2021 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 11/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2021 | Connected |  | N
National Grid | WESTMINSTER | 178551 | 01473 | 9 | Solar | 05_14_43L2 | 03/09/2018 | 03/09/2018 | 18 | 18 | 0 | 04/12/2018 | 04/12/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/18/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 257906 | 02790 | 11.4 | Solar | 05_14_59L6 | 10/02/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2020 | Connected |  | N
National Grid | TOPSFIELD | 709517 | 01983 | 5.76 | Solar | 05_14_74L3 | 08/04/2025 | 08/28/2025 | 2 | 0 | 2 | 08/29/2025 | 08/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MALDEN | 248297 | 02148 | 0 | Solar | 05_01_216W6 | 08/12/2019 | 08/21/2019 | 7 | 7 | 0 | 08/22/2019 | 08/22/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2019 |  | 11/22/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 10/22/2019 | Connected |  | N
National Grid | METHUEN | 178678 | 01844 | 7.6 | Solar | 05_01_26W3 | 04/11/2018 | 04/11/2018 | 29 | 28 | 1 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/17/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 678787 | 01810 | 11.52 | Solar | 05_01_412L5 | 03/18/2025 | 04/01/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 03/18/2025 | 7/11/2026 | Y | EXP | 365 | 09/17/2025 | 10/10/2025 | 24 | 0 | 24 |  |  | 10/22/2025 | Connected |  | N
National Grid | METHUEN | 176848 | 01844 | 480 | Solar | 05_01_602W3 | 11/09/2015 | 11/09/2015 | 1 | 1 | 0 | 11/10/2015 | 11/10/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 204363 | 01740 | 0 | Solar | 05_05_115W52 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | OXFORD | 649651 | 01540 | 9.28 | Solar | 05_12_26L1 | 10/25/2024 | 11/12/2024 | 8 | 3 | 5 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/25/2024 | 1/21/2026 | Y | EXP | 365 | 02/18/2025 | 03/03/2025 | 14 | 0 | 14 |  |  | 3/11/2025 | Connected |  | N
National Grid | DUDLEY | 468598 | 01571 | 6 | Solar | 05_12_67J4 | 10/21/2022 | 10/28/2022 | 5 | 2 | 3 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 178603 | 01473 | 3.8 | Solar | 05_14_43L2 | 04/09/2018 | 04/09/2018 | 13 | 0 | 13 | 04/27/2018 | 04/27/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2018 | 04/09/2018 | 11/29/2019 | Y | EXP | 568 | 09/12/2019 | 10/15/2019 | 33 | 0 | 33 |  |  | 10/23/2019 | Connected |  | N
National Grid | WESTPORT | 306710 | 02790 | 133.2 | Solar | 05_14_59L6 | 08/18/2020 | 10/05/2020 | 33 | 28 | 5 | 10/06/2020 | 10/06/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 1/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 738712 | 01983 | 10 | Solar | 05_14_74L3 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 12/08/2025 | 2/12/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MALDEN | 251196 | 02148 | 7.6 | Solar | 05_01_216W6 | 08/28/2019 | 10/14/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 08/28/2019 | 10/8/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | METHUEN | 189789 | 01844 | 15.2 | Solar | 05_01_26W3 | 07/02/2018 | 07/02/2018 | 5 | 4 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 731941 | 01810 | 13.36 | Solar | 05_01_412L5 | 11/06/2025 | 11/24/2025 | 11 | 8 | 3 | 11/25/2025 | 11/25/2025 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 184587 | 01844 | 3000 | Solar | 05_01_602W3 | 06/04/2018 | 06/04/2018 | 11 | 0 | 11 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 06/20/2018 | 07/11/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CLINTON | 257375 | 01510 | 10 | Solar | 05_05_115W52 | 10/14/2019 | 10/21/2019 | 5 | 5 | 0 | 10/22/2019 | 10/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 10/14/2019 | 7/7/2020 | Y | EXP | 365 | 12/20/2019 | 02/19/2020 | 61 | 0 | 61 |  |  | 2/20/2020 | Connected |  | N
National Grid | AUBURN | 657173 | 01501 | 10 | Solar | 05_12_26L1 | 11/26/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/26/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | DUDLEY | 649994 | 01571 | 3.8 | Solar | 05_12_67J4 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WESTMINSTER | 194175 | 01473 | 65 | Solar | 05_14_43L2 | 08/23/2018 | 10/16/2018 | 35 | 0 | 35 | 10/17/2018 | 10/17/2018 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 309079 | 02790 | 3.8 | Solar | 05_14_59L6 | 08/26/2020 | 09/15/2020 | 13 | 13 | 0 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2021 | Connected |  | N
National Grid | TOPSFIELD | 751572 | 01983 | 7.6 | Solar | 05_14_74L3 | 02/17/2026 | 02/23/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MALDEN | 263665 | 02148 | 0 | Solar | 05_01_216W6 | 11/04/2019 | 11/08/2019 | 3 | 0 | 3 | 11/12/2019 | 11/12/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 | 11/04/2019 | 11/4/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | METHUEN | 189536 | 01844 | 17.6 | Solar | 05_01_26W3 | 06/28/2018 | 06/28/2018 | 13 | 11 | 2 | 07/19/2018 | 07/19/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  | 8/23/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2019 | Connected |  | N
National Grid | ANDOVER | 635538 | 01810 | 0 | Other | 05_01_412L6 | 11/08/2024 | 12/12/2024 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 01/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 189902 | 01841 | 950 | Solar | 05_01_602W3 | 07/25/2018 | 09/17/2018 | 101 | 12 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 12/19/2018 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 280942 | 01740 | 3.8 | Solar | 05_05_115W52 | 03/02/2020 | 03/11/2020 | 7 | 3 | 4 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2020 | 03/02/2020 | 2/26/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2020 | Connected |  | N
National Grid | AUBURN | 659886 | 01501 | 9.57 | Solar | 05_12_26L1 | 12/11/2024 | 12/24/2024 | 9 | 5 | 4 | 12/26/2024 | 12/26/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | WEBSTER | 685446 | 01570 | 3.84 | Solar | 05_12_67J4 | 04/16/2025 | 05/23/2025 | 3 | 1 | 2 | 05/27/2025 | 05/27/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/16/2025 | 6/16/2026 | Y | EXP | 365 | 10/01/2025 | 11/21/2025 | 52 | 0 | 52 |  |  | 11/25/2025 | Connected |  | N
National Grid | WESTMINSTER | 305828 | 01473 | 9.6 | Solar | 05_14_43L2 | 08/10/2020 | 09/15/2020 | 25 | 23 | 2 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | FALL RIVER | 360062 | 02721 | 130 | Natural Gas | 05_14_59L6 | 06/09/2021 | 07/20/2021 | 28 | 18 | 10 |  |  | 54 | 29 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 | 06/09/2021 | 8/20/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | TOPSFIELD | 174308 | 01983 | 190 | Solar | 05_14_74L3 | 12/09/2011 | 12/09/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2012 | 12/09/2011 | 2/1/2012 | Y | EXP | 41 | 05/08/2012 | 05/09/2012 | 1 | 0 | 1 | 5/11/2012 | 5/11/2012 | 5/23/2012 | Connected |  | N
National Grid | MALDEN | 289076 | 02148 | 7.68 | Solar | 05_01_216W6 | 04/23/2020 | 04/27/2020 | 1 | 0 | 1 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/23/2020 | 8/18/2022 | Y | EXP | 759 | 12/02/2020 | 12/11/2020 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 194766 | 01832 | 650 | Solar | 05_01_26W3 | 09/19/2018 | 10/16/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/20/2018 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 718416 | 01810 | 0 | Other | 05_01_412L6 | 10/27/2025 | 01/15/2026 | 54 | 48 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/16/2026 | 02/09/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 201267 | 01844 | 996 | Solar | 05_01_602W3 | 01/11/2019 | 02/11/2019 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2019 | 03/18/2019 | 24 | 18 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 301536 | 01451 | 3.8 | Solar | 05_05_115W52 | 07/16/2020 | 07/22/2020 | 3 | 0 | 3 | 07/23/2020 | 07/23/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 676798 | 01501 | 22.8 | Solar | 05_12_26L1 | 03/11/2025 | 03/14/2025 | 3 | 0 | 3 | 03/17/2025 | 03/17/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | WEBSTER | 241200 | 01570 | 7.6 | Solar | 05_12_6J2 | 07/03/2019 | 07/10/2019 | 3 | 0 | 3 | 07/11/2019 | 07/11/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/03/2019 | 8/3/2020 | Y | EXP | 365 | 05/20/2020 | 06/17/2020 | 28 | 0 | 28 |  |  | 7/21/2020 | Connected |  | N
National Grid | WESTMINSTER | 364023 | 01473 | 9.8 | Solar | 05_14_43L2 | 06/28/2021 | 12/15/2021 | 1 | 0 | 1 | 06/30/2021 | 06/30/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 | 06/28/2021 | 12/26/2023 | Y | EXP | 365 | 01/18/2022 | 07/26/2022 | 189 | 0 | 189 |  |  | 8/3/2023 | Connected |  | N
National Grid | WESTPORT | 398978 | 02790 | 11.4 | Solar | 05_14_59L6 | 01/04/2022 | 01/07/2022 | 3 | 0 | 3 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | TOPSFIELD | 176470 | 01983 | 252 | Solar | 05_14_74L3 | 03/20/2016 | 03/20/2016 | 13 | 13 | 0 | 04/07/2016 | 04/07/2016 | 383 | 0 | 383 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 12/31/2017 | N | EXP | 611 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 293500 | 01905 | 200 | Solar | 05_01_216W6 | 05/27/2020 | 06/16/2020 | 14 | 12 | 2 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 196917 | 01832 | 9.2 | Solar | 05_01_26W3 | 09/25/2018 | 10/11/2018 | 10 | 9 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2018 | 09/25/2018 | 3/8/2019 | Y | EXP | 147 | 12/25/2018 | 01/08/2019 | 14 | 0 | 14 |  |  | 3/4/2019 | Connected |  | N
National Grid | ANDOVER | 176664 | 01810 | 660 | Solar | 05_01_412L6 | 10/20/2015 | 10/20/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 10/25/2016 | N | STD | 237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 321925 | 01844 | 7.6 | Solar | 05_01_602W3 | 10/27/2020 | 10/28/2020 | 0 | 0 | 0 | 10/29/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/19/2022 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | HARVARD | 320315 | 01451 | 15.6 | Solar | 05_05_115W52 | 10/20/2020 | 01/27/2021 | 66 | 59 | 7 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 10/20/2020 | 7/16/2022 | Y | EXP | 365 | 04/03/2021 | 05/17/2021 | 44 | 0 | 44 |  |  | 10/26/2021 | Connected |  | N
National Grid | OXFORD | 693020 | 01540 | 31.04 | Solar | 05_12_26L1 | 05/29/2025 | 06/03/2025 | 3 | 0 | 3 | 06/04/2025 | 06/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | WEBSTER | 342995 | 01570 | 7.6 | Solar | 05_12_6J2 | 03/02/2021 |  | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 378895 | 01473 | 6 | Solar | 05_14_43L2 | 09/16/2021 | 12/21/2021 | 3 | 0 | 3 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2022 | Connected |  | Y
National Grid | WESTPORT | 405190 | 02790 | 0 | Battery Add-On | 05_14_59L6 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TOPSFIELD | 176680 | 01983 | 6 | Solar | 05_14_74L3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/11/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 4/18/2016 | 4/18/2016 | 5/24/2016 | Connected |  | N
National Grid | LYNN | 295570 | 01905 | 0 | Solar | 05_01_216W6 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 | 10/26/2020 | 10/25/2022 | Y | EXP | 365 | 04/07/2021 | 04/28/2021 | 21 | 0 | 21 |  |  | 7/27/2022 | Connected |  | N
National Grid | HAVERHILL | 197089 | 01832 | 3.8 | Solar | 05_01_26W3 | 09/27/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | ANDOVER | 176663 | 01810 | 1000 | Solar | 05_01_412L6 | 10/20/2015 | 10/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 | 10/20/2015 | 6/10/2021 | Y | STD | 316 | 10/03/2020 | 02/26/2021 | 146 | 0 | 146 |  |  | 6/8/2021 | Connected |  | N
National Grid | METHUEN | 345465 | 01844 | 500 | Solar | 05_01_602W3 | 04/07/2021 |  | 314 | 158 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 450178 | 01740 | 10 | Solar | 05_05_115W52 | 08/26/2022 | 09/22/2022 | 18 | 15 | 3 | 09/23/2022 | 09/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 08/26/2022 | 2/8/2024 | Y | EXP | 365 | 01/07/2023 | 02/07/2023 | 32 | 0 | 32 |  |  | 3/23/2023 | Connected |  | N
National Grid | AUBURN | 717527 | 01501 | 18.85 | Solar | 05_12_26L1 | 09/08/2025 | 09/18/2025 | 6 | 2 | 4 | 09/19/2025 | 09/19/2025 | 86 | 70 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 613313 | 01570 | 5 | Solar | 05_12_6J2 | 05/28/2024 | 06/18/2024 | 3 | 1 | 2 | 06/20/2024 | 06/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | WESTMINSTER | 396668 | 01473 | 0 | Other | 05_14_43L2 | 01/04/2022 | 01/14/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 414820 | 02790 | 7.6 | Solar | 05_14_59L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TOPSFIELD | 176823 | 01983 | 6 | Solar | 05_14_74L3 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/20/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/25/2016 | Connected |  | N
National Grid | LYNN | 298017 | 01905 | 10 | Solar | 05_01_216W6 | 06/24/2020 | 06/29/2020 | 2 | 0 | 2 | 06/30/2020 | 06/30/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2020 | Connected |  | N
National Grid | METHUEN | 258441 | 01844 | 10 | Solar | 05_01_26W3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/17/2019 | 3/4/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | ANDOVER | 201422 | 01810 | 500 | Solar | 05_01_412L6 | 12/07/2018 | 01/05/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2019 | 02/05/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 556865 | 01844 | 4998 | Solar | 05_01_602W3 | 07/02/2024 |  | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HARVARD | 380699 | 01451 | 480 | Solar | 05_05_115W52 | 10/29/2021 | 12/15/2021 | 30 | 20 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 714746 | 01501 | 0 | Solar | 05_12_28L2 | 08/28/2025 | 09/10/2025 | 8 | 4 | 4 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 630759 | 01570 | 10 | Solar | 05_12_6J2 | 08/07/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 400900 | 01473 | 16.53 | Solar | 05_14_43L2 | 02/01/2022 | 02/03/2022 | 2 | 0 | 2 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 6/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2023 | Connected |  | N
National Grid | FALL RIVER | 486898 | 02723 | 16 | Solar | 05_14_59L6 | 01/11/2023 | 01/24/2023 | 9 | 8 | 1 | 01/25/2023 | 01/25/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | GLOUCESTER | 176884 | 01930 | 7.6 | Solar | 05_14_74L3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 311915 | 01905 | 14.5 | Solar | 05_01_216W6 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 286480 | 01844 | 7.6 | Solar | 05_01_26W3 | 05/26/2020 | 06/03/2020 | 5 | 0 | 5 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 311549 | 01810 | 250 | Hydro | 05_01_412L6 | 02/22/2022 | 05/27/2022 | 67 | 59 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2022 | 06/21/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 | 02/22/2022 | 12/31/2024 | Y | STD | 36 | 10/01/2024 | 10/31/2024 | 31 | 0 | 31 |  |  | 1/9/2025 | Connected |  | N
National Grid | METHUEN | 608973 | 01844 | 10 | Solar | 05_01_602W3 | 05/06/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 454988 | 01740 | 6.96 | Solar | 05_05_115W52 | 11/16/2022 | 01/03/2023 | 29 | 25 | 4 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2023 | 11/16/2022 | 6/25/2024 | Y | EXP | 365 | 03/29/2023 | 05/03/2023 | 36 | 0 | 36 |  |  | 7/20/2023 | Connected |  | N
National Grid | AUBURN | 725607 | 01501 | 0 | Solar | 05_12_28L2 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEBSTER | 657888 | 01570 | 7.6 | Solar | 05_12_6J2 | 12/02/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 406366 | 01473 | 470 | Solar | 05_14_43L2 | 01/28/2022 | 05/02/2022 | 64 | 54 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2023 | 01/28/2022 | 8/27/2024 | Y | STD | 29 |  |  | 0 | 0 | 0 |  |  | 7/5/2024 | Connected |  | N
National Grid | WESTPORT | 499224 | 02790 | 15.08 | Solar | 05_14_59L6 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | Y
National Grid | GLOUCESTER | 176943 | 01930 | 5.75 | Solar | 05_14_74L3 | 12/12/2016 | 12/12/2016 | 1 | 1 | 0 | 12/21/2016 | 12/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/12/2016 | 12/25/2017 | Y | EXP | 368 | 06/20/2017 | 07/05/2017 | 10 | 0 | 10 | 9/21/2017 | 9/21/2017 | 9/21/2017 | Connected |  | N
National Grid | LYNN | 336027 | 01905 | 200 | Solar | 05_01_216W6 | 01/11/2021 | 12/07/2021 | 9 | 1 | 8 | 02/03/2021 | 02/03/2021 | 74 | 51 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2021 |  | 7/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | HAVERHILL | 337541 | 01832 | 9.8 | Solar | 05_01_26W3 | 01/19/2021 | 01/25/2021 | 3 | 0 | 3 | 01/26/2021 | 01/26/2021 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 3/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2021 | Connected |  | N
National Grid | ANDOVER | 455151 | 01810 | 100 | Solar | 05_01_412L6 | 11/15/2022 |  | 237 | 229 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 650633 | 01841 | 3.77 | Solar | 05_01_602W3 | 10/29/2024 | 11/06/2024 | 3 | 0 | 3 | 11/07/2024 | 11/07/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 465035 | 01451 | 4.06 | Solar | 05_05_115W52 | 09/30/2022 | 10/20/2022 | 13 | 12 | 1 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2023 | Connected |  | N
National Grid | AUBURN | 750287 | 01501 | 3.8 | Solar | 05_12_28L2 | 02/10/2026 | 02/11/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEBSTER | 701479 | 01570 | 6.72 | Solar | 05_12_6J2 | 06/28/2025 | 07/14/2025 | 5 | 0 | 5 | 07/28/2025 | 07/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/28/2025 | 9/10/2026 | Y | EXP | 365 | 11/14/2025 | 12/15/2025 | 32 | 0 | 32 |  |  | 1/20/2026 | Connected |  | N
National Grid | WESTMINSTER | 425587 | 01473 | 498 | Solar | 05_14_43L2 | 08/31/2022 | 09/20/2022 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2022 | 10/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTPORT | 530104 | 02790 | 9.86 | Solar | 05_14_59L6 | 06/17/2023 | 06/20/2023 | 13 | 8 | 5 | 06/21/2023 | 06/21/2023 | 21 | 0 | 21 | 08/09/2023 | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 09/12/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 10/10/2024 | N | EXP | 365 | 10/06/2023 | 10/05/2023 | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | Y
National Grid | GLOUCESTER | 176936 | 01930 | 7.6 | Solar | 05_14_74L3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/6/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/4/2016 | 8/4/2016 | 8/8/2016 | Connected |  | N
National Grid | LYNN | 356319 | 01905 | 9.28 | Solar | 05_01_216W6 | 05/05/2021 | 05/11/2021 | 4 | 4 | 0 | 05/12/2021 | 05/12/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | HAVERHILL | 450660 | 01832 | 19 | Solar | 05_01_26W3 | 08/10/2022 | 09/12/2022 | 22 | 22 | 0 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 | 12/07/2022 | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 |  | 03/20/2023 | 70 | 0 | 70 |  |  | 0 | 0 | 0 | 3/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 605768 | 01810 | 6 | Solar | 05_01_412L6 | 04/24/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 5/20/2025 | Y | EXP | 365 | 09/06/2024 | 10/11/2024 | 36 | 0 | 36 |  |  | 10/18/2024 | Connected |  | N
National Grid | METHUEN | 652673 | 01844 | 4.06 | Solar | 05_01_602W3 | 11/06/2024 | 12/02/2024 | 8 | 4 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 473743 | 01740 | 10 | Solar | 05_05_115W52 | 12/20/2022 | 12/27/2022 | 4 | 2 | 2 | 12/28/2022 | 12/28/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 | 12/20/2022 | 4/6/2024 | Y | EXP | 365 | 04/22/2023 | 05/25/2023 | 34 | 0 | 34 |  |  | 6/1/2023 | Connected |  | N
National Grid | AUBURN | 176498 | 01501 | 22.8 | Solar | 05_12_28L2 | 02/09/2016 | 02/09/2016 | 1 | 1 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2016 |  | 2/15/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/19/2016 | 2/19/2016 | 10/24/2016 | Connected |  | N
National Grid | WEBSTER | 712486 | 01570 | 10.47 | Solar | 05_12_6J2 | 08/22/2025 | 08/26/2025 | 2 | 0 | 2 | 08/27/2025 | 08/27/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | WESTMINSTER | 433206 | 01473 | 10 | Solar | 05_14_43L2 | 06/07/2022 | 06/09/2022 | 2 | 0 | 2 | 06/10/2022 | 06/10/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 | 06/07/2022 | 10/20/2023 | Y | EXP | 365 | 09/28/2022 | 10/19/2022 | 22 | 0 | 22 |  |  | 11/17/2022 | Connected |  | N
National Grid | WESTPORT | 555740 | 02790 | 10 | Solar | 05_14_59L6 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 21 | 0 | 21 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/2/2025 | N | EXP | 365 | 05/04/2024 | 01/30/2025 | 272 | 0 | 272 |  |  | 3/6/2025 | Connected |  | N
National Grid | MANCHESTER | 177053 | 01944 | 7.6 | Solar | 05_14_74L3 | 01/11/2017 | 01/11/2017 | 4 | 3 | 1 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2017 |  | 1/16/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | LYNN | 366741 | 01905 | 7.6 | Solar | 05_01_216W6 | 06/29/2021 | 06/30/2021 | 1 | 0 | 1 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 10/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2022 | Connected |  | N
National Grid | METHUEN | 404298 | 01844 | 6 | Solar | 05_01_26W3 | 01/13/2022 | 01/18/2022 | 2 | 0 | 2 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/13/2022 | 7/13/2023 | Y | EXP | 365 | 05/27/2022 | 06/13/2022 | 18 | 0 | 18 |  |  | 7/26/2022 | Connected |  | Y
National Grid | ANDOVER | 633327 | 01810 | 5 | Solar | 05_01_412L6 | 08/19/2024 | 09/03/2024 | 2 | 1 | 1 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/19/2024 | 11/6/2025 | Y | EXP | 365 | 11/19/2024 | 02/28/2025 | 102 | 0 | 102 |  |  | 3/27/2025 | Connected |  | N
National Grid | METHUEN | 656529 | 01844 | 7.98 | Solar | 05_01_602W3 | 11/24/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/24/2024 | 3/26/2026 | Y | EXP | 365 | 06/11/2025 | 11/21/2025 | 164 | 0 | 164 |  |  | 2/11/2026 | Connected |  | Y
National Grid | BOLTON | 523454 | 01740 | 10 | Solar | 05_05_115W52 | 06/05/2023 | 06/12/2023 | 5 | 4 | 1 | 06/13/2023 | 06/13/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 06/05/2023 | 7/16/2024 | Y | EXP | 365 | 08/16/2023 | 10/11/2023 | 57 | 0 | 57 |  |  | 10/16/2023 | Connected |  | N
National Grid | AUBURN | 176791 | 01501 | 7.6 | Solar | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/20/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 8/2/2016 | Connected |  | N
National Grid | WEBSTER | 715339 | 01570 | 2.7 | Solar | 05_12_6J2 | 08/29/2025 | 09/19/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 443275 | 01473 | 15.2 | Solar | 05_14_43L2 | 07/11/2022 | 07/13/2022 | 2 | 0 | 2 | 07/14/2022 | 07/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | WESTPORT | 554641 | 02790 | 15 | Solar | 05_14_59L6 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | GLOUCESTER | 178183 | 01930 | 7.6 | Solar | 05_14_74L3 | 04/13/2018 | 04/13/2018 | 21 | 21 | 0 | 05/02/2018 | 05/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 367483 | 01905 | 0 | Solar | 05_01_216W6 | 07/02/2021 | 07/06/2021 | 1 | 0 | 1 | 07/07/2021 | 07/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2022 | Connected |  | N
National Grid | HAVERHILL | 403477 | 01832 | 9.57 | Solar | 05_01_26W3 | 08/01/2022 | 01/13/2022 | 21 | 21 | 0 | 08/31/2022 | 08/31/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2023 | Connected |  | N
National Grid | ANDOVER | 644967 | 01810 | 10 | Solar | 05_01_412L6 | 10/04/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/04/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | METHUEN | 614910 | 01844 | 4000 | Solar | 05_01_607W1 | 09/25/2024 | 10/30/2024 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 12/02/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HARVARD | 560606 | 01451 | 15.08 | Solar | 05_05_115W52 | 10/05/2023 | 10/09/2023 | 2 | 0 | 2 | 10/10/2023 | 10/10/2023 | 63 | 41 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 3/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | MILLBURY | 176789 | 01527 | 7.6 | Solar | 05_12_28L2 | 01/14/2016 | 01/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/20/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 226580 | 01570 | 1950 | Natural Gas | 05_12_72L1 | 07/25/2019 | 10/29/2019 | 65 | 58 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 | 01/31/2020 | 63 | 31 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2021 | 07/25/2019 | 8/14/2026 | Y | STD | 161 | 10/09/2024 |  | 514 | 514 | 0 |  |  |  | Construction |  | Y
National Grid | GARDNER | 562970 | 01440 | 10 | Solar | 05_14_43L2 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 34 | 12 | 22 | 02/13/2024 | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 03/11/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 | 05/22/2024 | 01/31/2025 | 267 | 0 | 267 |  |  | 1/31/2025 | Connected |  | N
National Grid | WESTPORT | 568051 | 02790 | 0 | Solar | 05_14_59L6 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2024 | Connected |  | N
National Grid | GLOUCESTER | 193240 | 01930 | 6 | Solar | 05_14_74L3 | 08/10/2018 | 11/30/2018 | 42 | 34 | 8 | 12/03/2018 | 12/03/2018 | 21 | 10 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 8/10/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 374977 | 01915 | 11.4 | Solar | 05_01_216W6 | 08/10/2021 | 09/07/2021 | 19 | 18 | 1 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2022 | Connected |  | N
National Grid | HAVERHILL | 430569 | 01832 | 11.02 | Solar | 05_01_26W3 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 11/16/2023 | Y | EXP | 365 | 10/12/2022 | 11/14/2022 | 34 | 0 | 34 |  |  | 12/7/2022 | Connected |  | Y
National Grid | ANDOVER | 661555 | 01810 | 5.76 | Solar | 05_01_412L6 | 12/18/2024 | 01/09/2025 | 5 | 0 | 5 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 05/15/2025 | 05/14/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 673050 | 01841 | 5.76 | Solar | 05_01_607W1 | 02/20/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BOLTON | 583847 | 01740 | 480 | Solar | 05_05_115W52 | 02/22/2024 | 05/22/2024 | 63 | 53 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 178625 | 01501 | 11.4 | Solar | 05_12_28L2 | 03/15/2018 | 03/15/2018 | 14 | 0 | 14 | 04/05/2018 | 04/05/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2018 |  | 3/21/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 9/6/2019 | Connected |  | N
National Grid | WEBSTER | 724946 | 01570 | 1000 | Solar | 05_12_72L1 | 12/08/2025 |  | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | GARDNER | 622796 | 01440 | 7.6 | Solar | 05_14_43L2 | 07/05/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 07/05/2024 | 11/24/2025 | Y | EXP | 365 | 09/19/2024 | 12/02/2024 | 75 | 0 | 75 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 594025 | 02723 | 10 | Solar | 05_14_59L6 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 221314 | 01930 | 7.6 | Solar | 05_14_74L3 | 04/19/2019 | 06/05/2019 | 0 | 0 | 0 | 06/06/2019 | 06/06/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2019 | 04/19/2019 | 7/16/2020 | Y | EXP | 365 | 03/04/2020 | 05/21/2020 | 78 | 0 | 78 |  |  | 6/5/2020 | Connected |  | N
National Grid | BEVERLY | 376566 | 01915 | 7.6 | Solar | 05_01_216W6 | 11/04/2021 | 12/06/2021 | 21 | 18 | 3 | 12/07/2021 | 12/07/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2022 | Connected |  | N
National Grid | METHUEN | 433265 | 01844 | 150 | Solar | 05_01_26W3 | 06/01/2022 | 06/30/2022 | 20 | 12 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 672975 | 01810 | 17.6 | Solar | 05_01_412L6 | 03/03/2025 | 03/14/2025 | 10 | 5 | 5 | 03/17/2025 | 03/17/2025 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/03/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | LAWRENCE | 704606 | 01841 | 3.8 | Solar | 05_01_607W1 | 07/14/2025 | 09/11/2025 | 5 | 1 | 4 | 09/12/2025 | 09/12/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 07/14/2025 | 10/20/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BOLTON | 598026 | 01740 | 2.9 | Solar | 05_05_115W52 | 04/11/2024 | 05/01/2024 | 13 | 10 | 3 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/11/2024 | 5/20/2025 | Y | EXP | 365 | 07/03/2024 | 08/08/2024 | 37 | 0 | 37 |  |  | 9/28/2024 | Connected |  | N
National Grid | AUBURN | 203910 | 01501 | 0 | Solar | 05_12_28L2 | 12/18/2018 | 12/31/2018 | 7 | 0 | 7 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 1/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | WEBSTER | 177522 | 01570 | 24 | Solar | 05_12_72L1 | 02/11/2016 | 02/11/2016 | 3 | 0 | 3 | 02/17/2016 | 02/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 10/4/2017 | N | EXP | 595 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 10/5/2016 | Connected |  | N
National Grid | GARDNER | 632056 | 01440 | 7.6 | Solar | 05_14_43L2 | 08/13/2024 | 09/24/2024 | 8 | 3 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 08/13/2024 | 12/31/2025 | Y | EXP | 365 | 01/25/2025 | 09/12/2025 | 231 | 0 | 231 |  |  | 11/7/2025 | Connected |  | N
National Grid | FALL RIVER | 607739 | 02721 |  | Battery Add-On | 05_14_59L6 | 04/30/2024 | 05/03/2024 | 3 | 0 | 3 | 05/06/2024 | 05/06/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | MANCHESTER | 215214 | 01944 | 7.6 | Solar | 05_14_74L3 | 04/17/2019 | 04/24/2019 | 4 | 0 | 4 | 04/25/2019 | 04/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 04/17/2019 | 9/17/2020 | Y | EXP | 365 | 03/04/2020 | 03/19/2020 | 15 | 0 | 15 |  |  | 7/10/2020 | Connected |  | N
National Grid | BEVERLY | 379354 | 01915 | 0 | Solar | 05_01_216W6 | 09/01/2021 | 09/13/2021 | 7 | 7 | 0 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2021 | Connected |  | N
National Grid | HAVERHILL | 476717 | 01832 | 160 | Solar | 05_01_26W3 | 12/13/2022 | 02/20/2023 | 45 | 38 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 12/13/2022 | 3/9/2025 | Y | STD | 133 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ANDOVER | 680767 | 01810 | 3.8 | Solar | 05_01_412L6 | 03/26/2025 | 04/16/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 739577 | 01841 | 7.6 | Solar | 05_01_607W1 | 12/11/2025 | 12/12/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 601783 | 01740 | 0 | Solar | 05_05_115W52 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 203625 | 01501 | 3.8 | Solar | 05_12_28L2 | 12/27/2018 | 01/04/2019 | 4 | 0 | 4 | 01/07/2019 | 01/07/2019 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 177914 | 01570 | 365 | Natural Gas | 05_12_72L1 | 10/20/2017 | 10/20/2017 | 55 | 0 | 55 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  | 6/28/2019 | N | STD | 252 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | GARDNER | 637795 | 01440 | 10 | Solar | 05_14_43L2 | 09/04/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/04/2024 | 11/2/2025 | Y | EXP | 365 | 12/19/2024 | 03/15/2025 | 86 | 0 | 86 |  |  | 3/22/2025 | Connected |  | N
National Grid | WESTPORT | 652980 | 02790 | 5.76 | Solar | 05_14_59L6 | 11/14/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | GLOUCESTER | 255172 | 01930 | 7.6 | Solar | 05_14_74L3 | 09/27/2019 | 10/02/2019 | 2 | 1 | 1 | 10/03/2019 | 10/03/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2019 | 09/27/2019 | 9/27/2020 | Y | EXP | 365 | 02/12/2020 | 03/12/2020 | 29 | 0 | 29 |  |  | 6/16/2020 | Connected |  | N
National Grid | BEVERLY | 395135 | 01915 | 250 | Solar | 05_01_216W6 | 12/14/2021 | 01/03/2022 | 14 | 8 | 6 |  |  | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 520551 | 01844 | 0 | Solar | 05_01_26W3 | 04/20/2023 | 04/27/2023 | 5 | 3 | 2 | 04/28/2023 | 04/28/2023 | 231 | 210 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 687053 | 01810 | 3.8 | Solar | 05_01_412L6 | 04/23/2025 | 07/09/2025 | 52 | 48 | 4 | 07/10/2025 | 07/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | METHUEN | 174398 | 01844 | 1000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/26/2012 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 603266 | 01740 | 4.06 | Solar | 05_05_115W52 | 04/11/2024 | 05/10/2024 | 8 | 3 | 5 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 8/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | AUBURN | 293839 | 01501 | 10 | Solar | 05_12_28L2 | 05/28/2020 | 06/15/2020 | 12 | 12 | 0 | 06/16/2020 | 06/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2020 | Connected |  | N
National Grid | WEBSTER | 178031 | 01570 | 5.2 | Solar | 05_12_72L1 | 10/25/2017 | 10/25/2017 | 24 | 24 | 0 | 12/11/2017 | 12/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 10/25/2017 | 10/15/2019 | Y | EXP | 673 | 08/08/2018 | 10/05/2018 | 58 | 0 | 58 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 647179 | 01440 | 5.12 | Solar | 05_14_43L2 | 10/15/2024 | 10/25/2024 | 4 | 1 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 10/15/2024 | 12/12/2025 | Y | EXP | 365 | 02/14/2025 | 04/28/2025 | 74 | 0 | 74 |  |  | 4/30/2025 | Connected |  | N
National Grid | FALL RIVER | 679799 | 02721 | 3.8 | Solar | 05_14_59L6 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 261505 | 01930 | 0 | Solar | 05_14_74L3 | 10/22/2019 | 10/27/2019 | 3 | 0 | 3 | 10/28/2019 | 10/28/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 | 10/22/2019 | 11/15/2020 | Y | EXP | 365 | 04/25/2020 | 07/06/2020 | 72 | 0 | 72 |  |  | 2/8/2021 | Connected |  | N
National Grid | BEVERLY | 404028 | 01915 | 12.86 | Solar | 05_01_216W6 | 12/29/2021 | 01/03/2022 | 3 | 0 | 3 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2022 | Connected |  | N
National Grid | HAVERHILL | 520407 | 01832 | 15 | Solar | 05_01_26W3 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 8/18/2025 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 466552 | 01810 | 250 | Solar | 05_01_413L1 | 10/21/2022 | 11/07/2022 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2022 | 12/05/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 174397 | 01841 | 1000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 647197 | 01740 | 7.6 | Solar | 05_05_115W52 | 10/17/2024 | 10/29/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 12/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | AUBURN | 359131 | 01501 | 5.22 | Solar | 05_12_28L2 | 05/19/2021 | 06/07/2021 | 12 | 11 | 1 | 06/08/2021 | 06/08/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 178181 | 01550 | 3.8 | Solar | 05_12_72L1 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/02/2018 | 05/02/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/18/2019 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 647458 | 01440 | 7.6 | Solar | 05_14_43L2 | 10/22/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/22/2024 | 3/27/2026 | Y | EXP | 365 | 04/08/2025 | 12/22/2025 | 259 | 12 | 247 |  |  | 2/10/2026 | Connected |  | N
National Grid | FALL RIVER | 712505 | 02720 | 6.08 | Solar | 05_14_59L6 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | MANCHESTER | 270454 | 01944 | 7.6 | Solar | 05_14_74L3 | 12/26/2019 | 01/06/2020 | 5 | 0 | 5 | 01/07/2020 | 01/07/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2020 | 12/26/2019 | 12/26/2020 | Y | EXP | 365 | 09/23/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 10/27/2020 | Connected |  | N
National Grid | BEVERLY | 407694 | 01915 | 10 | Solar | 05_01_216W6 | 01/20/2022 | 01/24/2022 | 3 | 1 | 2 | 01/25/2022 | 01/25/2022 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 | 01/20/2022 | 8/31/2023 | Y | EXP | 365 | 05/07/2022 | 08/25/2022 | 108 | 0 | 108 |  |  | 9/1/2022 | Connected |  | N
National Grid | HAVERHILL | 544706 | 01832 | 10 | Solar | 05_01_26W3 | 08/08/2023 | 08/10/2023 | 2 | 0 | 2 | 08/11/2023 | 08/11/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2023 | 08/08/2023 | 10/10/2024 | Y | EXP | 365 | 03/05/2024 | 03/04/2024 | 0 | 0 | 0 |  |  | 3/26/2024 | Connected |  | N
National Grid | ANDOVER | 643826 | 01810 | 5.76 | Solar | 05_01_413L1 | 09/30/2024 | 10/11/2024 | 5 | 1 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 7/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 174396 | 01844 | 2000 | Solar | 05_01_607W1 | 06/14/2012 | 06/14/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2012 | 09/24/2012 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2013 | 06/14/2012 | 2/11/2014 | Y | STD | 27 | 11/27/2013 | 04/25/2014 | 100 | 0 | 100 | 5/6/2014 | 5/6/2014 | 5/23/2014 | Connected |  | N
National Grid | BOLTON | 677831 | 01740 | 5.76 | Solar | 05_05_115W52 | 03/13/2025 | 03/25/2025 | 8 | 4 | 4 | 03/26/2025 | 03/26/2025 | 56 | 38 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 03/13/2025 | 6/30/2026 | Y | EXP | 365 | 08/23/2025 | 10/01/2025 | 40 | 0 | 40 |  |  | 10/13/2025 | Connected |  | N
National Grid | AUBURN | 453090 | 01501 | 8.7 | Solar | 05_12_28L2 | 09/26/2022 | 09/29/2022 | 3 | 2 | 1 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2022 |  | 12/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 178590 | 01550 | 3.2 | Solar | 05_12_72L1 | 03/14/2018 | 03/14/2018 | 0 | 0 | 0 | 04/24/2018 | 04/24/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/20/2019 | N | EXP | 313 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 649032 | 01440 | 13.975 | Solar | 05_14_43L2 | 10/22/2024 | 11/05/2024 | 10 | 7 | 3 | 11/06/2024 | 11/06/2024 | 61 | 25 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WESTPORT | 607813 | 02790 | 175 | Solar | 05_14_5J11 | 05/01/2024 | 07/25/2024 | 58 | 52 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2024 | 08/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GLOUCESTER | 298830 | 01930 | 7.6 | Solar | 05_14_74L3 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 435624 | 01915 | 15.2 | Solar | 05_01_216W6 | 06/06/2022 | 06/24/2022 | 13 | 11 | 2 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | METHUEN | 553735 | 01844 | 6.912 | Solar | 05_01_26W3 | 09/25/2023 | 10/12/2023 | 12 | 5 | 7 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/25/2023 | 2/25/2025 | Y | EXP | 365 | 05/16/2024 | 06/11/2024 | 27 | 0 | 27 |  |  | 6/20/2024 | Connected |  | N
National Grid | AMESBURY | 661362 | 01913 | 5.76 | Solar | 05_01_413L1 | 12/18/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 174707 | 01841 | 60 | Natural Gas | 05_01_607W1 | 06/17/2013 | 06/17/2013 | 13 | 5 | 8 | 07/08/2013 | 07/08/2013 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2013 |  | 12/1/2017 | N | EXP | 1592 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 680103 | 01740 | 7.6 | Solar | 05_05_115W52 | 03/24/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 373988 | 01501 | 9.86 | Solar | 05_12_28L2 | 08/04/2021 | 08/09/2021 | 4 | 2 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 196655 | 01550 | 3.8 | Solar | 05_12_72L1 | 09/21/2018 | 10/16/2018 | 5 | 5 | 0 | 10/17/2018 | 10/17/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 650321 | 01440 | 10 | Solar | 05_14_43L2 | 11/07/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | FALL RIVER | 174139 | 02721 | 22.8 | Solar | 05_14_5J11 | 04/10/2012 | 04/10/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2012 |  | 6/1/2012 | N | EXP | 6 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 11/19/2012 | Connected |  | N
National Grid | MANCHESTER | 312794 | 01944 | 3.84 | Solar | 05_14_74L3 | 10/27/2020 |  | 61 | 26 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 515975 | 01915 | 7.6 | Solar | 05_01_216W6 | 05/09/2023 | 08/16/2023 | 68 | 66 | 2 | 08/17/2023 | 08/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2023 | Connected |  | N
National Grid | METHUEN | 570140 | 01844 | 13.325 | Solar | 05_01_26W3 | 12/04/2023 | 12/07/2023 | 3 | 0 | 3 | 12/08/2023 | 12/08/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/04/2023 | 3/12/2025 | Y | EXP | 365 | 04/16/2024 | 07/12/2024 | 88 | 0 | 88 |  |  | 7/22/2024 | Connected |  | N
National Grid | AMESBURY | 739089 | 01913 | 20 | Solar | 05_01_413L1 | 12/10/2025 | 12/15/2025 | 3 | 0 | 3 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | METHUEN | 175258 | 01844 | 42 | Solar | 05_01_607W1 | 01/08/2015 | 01/08/2015 | 4 | 2 | 2 | 01/15/2015 | 01/15/2015 | 425 | 0 | 425 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 |  | Withdrawn |  | N
National Grid | CLINTON | 685905 | 01510 | 7.6 | Solar | 05_05_115W52 | 04/17/2025 | 07/08/2025 | 9 | 7 | 2 | 07/24/2025 | 07/24/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2026 | Connected |  | N
National Grid | AUBURN | 397029 | 01501 | 20 | Solar | 05_12_28L2 | 12/09/2021 | 12/20/2021 | 8 | 6 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 1/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 468924 | 01550 | 10 | Solar | 05_12_72L1 | 11/01/2022 | 11/02/2022 | 1 | 0 | 1 | 11/03/2022 | 11/03/2022 | 60 | 42 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 | 11/01/2022 | 7/2/2024 | Y | EXP | 365 | 04/22/2023 | 06/30/2023 | 70 | 0 | 70 |  |  | 8/9/2023 | Connected |  | N
National Grid | GARDNER | 652375 | 01440 | 5.76 | Solar | 05_14_43L2 | 12/04/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/04/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | WESTPORT | 176451 | 02790 | 52.8 | Solar | 05_14_5J11 | 12/08/2015 | 12/08/2015 | 7 | 7 | 0 | 12/17/2015 | 12/17/2015 | 122 | 0 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 318214 | 01930 | 6.38 | Solar | 05_14_74L3 | 10/09/2020 | 10/12/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | BEVERLY | 543308 | 01915 | 15 | Solar | 05_01_216W6 | 07/24/2023 | 07/25/2023 | 1 | 0 | 1 | 07/26/2023 | 07/26/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | HAVERHILL | 588492 | 01832 | 9.135 | Solar | 05_01_26W3 | 02/23/2024 | 03/01/2024 | 5 | 1 | 4 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 4/18/2025 | Y | EXP | 365 | 05/02/2024 | 07/15/2024 | 75 | 0 | 75 |  |  | 8/23/2024 | Connected |  | N
National Grid | AMESBURY | 745492 | 01913 | 7.6 | Solar | 05_01_413L1 | 01/15/2026 | 01/30/2026 | 5 | 2 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 176116 | 01844 | 7.6 | Solar | 05_01_607W1 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/29/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 3/18/2016 | Connected |  | N
National Grid | BOLTON | 694610 | 01740 | 15.96 | Solar | 05_05_115W52 | 06/23/2025 | 07/28/2025 | 23 | 22 | 1 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | AUBURN | 422580 | 01501 | 0 | Solar | 05_12_28L2 | 04/08/2022 | 04/21/2022 | 9 | 8 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 |  | 5/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 516020 | 01550 | 5 | Solar | 05_12_72L1 | 04/26/2023 | 05/26/2023 | 22 | 21 | 1 | 05/30/2023 | 05/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/26/2023 | 8/18/2024 | Y | EXP | 365 | 10/25/2023 | 10/25/2023 | 1 | 0 | 1 |  |  | 11/17/2023 | Connected |  | N
National Grid | GARDNER | 652297 | 01440 | 5.76 | Solar | 05_14_43L2 | 11/14/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTPORT | 177462 | 02790 | 43.2 | Solar | 05_14_5J11 | 12/12/2016 | 12/12/2016 | 7 | 7 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/17/2017 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/23/2017 | Connected |  | N
National Grid | MANCHESTER | 401100 | 01944 | 0 | Other | 05_14_74L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 568830 | 01915 | 15.435 | Solar | 05_01_216W6 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  | 5/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2024 | Connected |  | N
National Grid | HAVERHILL | 614949 | 01832 | 10 | Solar | 05_01_26W3 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 | 06/04/2024 | 7/25/2025 | Y | EXP | 365 | 09/18/2024 | 10/21/2024 | 34 | 0 | 34 |  |  | 10/24/2024 | Connected |  | N
National Grid | AMESBURY | 751787 | 01913 | 11.52 | Solar | 05_01_413L1 | 02/18/2026 | 02/24/2026 | 4 | 1 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 176507 | 01844 | 6 | Solar | 05_01_607W1 | 03/24/2016 | 03/24/2016 | 36 | 36 | 0 | 05/17/2016 | 05/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 03/24/2016 | 3/30/2017 | Y | EXP | 297 | 07/28/2016 | 09/23/2016 | 40 | 0 | 40 | 11/8/2016 | 11/8/2016 | 11/10/2016 | Connected |  | N
National Grid | BOLTON | 700073 | 01740 | 17.6 | Solar | 05_05_115W52 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | OXFORD | 430870 | 01540 | 15.2 | Solar | 05_12_28L2 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 07/12/2022 | 07/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 12/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 565683 | 01550 | 3.8 | Solar | 05_12_72L1 | 10/24/2023 | 11/14/2023 | 3 | 1 | 2 | 11/15/2023 | 11/15/2023 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 656096 | 01440 | 3.8 | Solar | 05_14_43L2 | 11/21/2024 | 12/04/2024 | 4 | 0 | 4 | 12/05/2024 | 12/05/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/21/2024 | 3/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | WESTPORT | 195497 | 02790 | 7.6 | Solar | 05_14_5J11 | 09/10/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2018 | 09/10/2018 | 10/30/2020 | Y | EXP | 4 | 02/14/2020 | 02/18/2020 | 4 | 0 | 4 |  |  | 5/4/2020 | Connected |  | N
National Grid | GLOUCESTER | 461031 | 01930 | 6 | Solar | 05_14_74L3 | 09/28/2022 | 10/06/2022 | 6 | 3 | 3 | 10/07/2022 | 10/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 12/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | BEVERLY | 570119 | 01915 | 9.45 | Solar | 05_01_216W6 | 01/31/2024 | 02/06/2024 | 4 | 1 | 3 | 02/07/2024 | 02/07/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 01/31/2024 | 4/26/2025 | Y | EXP | 365 | 07/10/2024 | 07/16/2024 | 7 | 0 | 7 |  |  | 7/26/2024 | Connected |  | N
National Grid | METHUEN | 647810 | 01844 | 10 | Solar | 05_01_26W3 | 10/18/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/18/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | AMESBURY | 175324 | 01913 | 262.8 | Solar | 05_01_413L1 | 11/07/2014 | 11/07/2014 | 6 | 0 | 6 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 3/31/2015 | N | EXP | 15 |  |  | 0 | 0 | 0 | 10/20/2015 | 10/20/2015 | 10/21/2015 | Connected |  | N
National Grid | METHUEN | 177059 | 01844 | 900 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 720034 | 01740 | 11.4 | Solar | 05_05_115W52 | 09/18/2025 | 10/03/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | OXFORD | 596850 | 01540 | 3.77 | Solar | 05_12_72L1 | 03/19/2024 | 03/21/2024 | 2 | 1 | 1 | 03/22/2024 | 03/22/2024 | 8 | 6 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 660296 | 01550 | 15.2 | Solar | 05_14_43L2 | 12/19/2024 | 01/08/2025 | 13 | 9 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/19/2024 | 3/21/2026 | Y | EXP | 365 | 07/02/2025 | 07/24/2025 | 22 | 0 | 22 |  |  | 8/21/2025 | Connected |  | N
National Grid | WINCHENDON | 191148 | 01475 | 6.96 | Solar | 05_14_5J11 | 07/19/2018 | 07/31/2018 | 0 | 0 | 0 | 08/01/2018 | 08/01/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 7/31/2019 | N | EXP | 39 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | Connected |  | N
National Grid | WESTPORT | 460980 | 02790 | 3.8 | Solar | 05_14_74L3 | 09/29/2022 | 10/10/2022 | 7 | 3 | 4 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 09/29/2022 | 7/19/2024 | Y | EXP | 39 | 01/24/2023 | 02/01/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 574056 | 01930 | 0 | Battery Add-On | 05_01_216W6 | 11/28/2023 | 01/02/2024 | 23 | 17 | 6 | 01/03/2024 | 01/03/2024 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | BEVERLY | 650772 | 01915 | 10 | Solar | 05_01_26W3 | 10/30/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | METHUEN | 176176 | 01844 | 1000 | Solar | 05_01_413L1 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2015 | 07/02/2015 | 7/11/2016 | Y | STD | 21 | 08/04/2017 | 09/20/2017 | 32 | 0 | 32 | 10/16/2017 | 10/16/2017 | 10/13/2015 | Connected |  | N
National Grid | AMESBURY | 177058 | 01913 | 4500 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/09/2017 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 742764 | 01844 | 5.76 | Solar | 05_05_115W53 | 12/30/2025 | 12/31/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 | 12/30/2025 | 2/11/2027 | Y | EXP | 365 | 03/04/2026 |  | 3 | 0 | 3 |  |  |  | Construction |  | N
National Grid | BOLTON | 558123 | 01740 | 3.8 | Solar | 05_12_28L2 | 09/25/2023 | 10/03/2023 | 6 | 0 | 6 | 10/04/2023 | 10/04/2023 | 52 | 30 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | AUBURN | 641368 | 01501 | 10 | Solar | 05_12_72L1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 11/20/2025 | Y | EXP | 365 | 01/29/2025 | 02/06/2025 | 9 | 0 | 9 |  |  | 2/25/2025 | Connected |  | Y
National Grid | SOUTHBRIDGE | 670504 | 01550 | 7.54 | Solar | 05_14_43L2 | 02/06/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 451807 | 01475 | 10 | Solar | 05_14_5J11 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/20/2022 | 11/23/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2023 | Connected |  | N
National Grid | FALL RIVER | 468024 | 02721 | 10 | Solar | 05_14_74L3 | 10/20/2022 | 10/24/2022 | 2 | 0 | 2 | 10/25/2022 | 10/25/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | GLOUCESTER | 582430 | 01930 | 15.2 | Solar | 05_01_216W6 | 01/09/2024 | 01/11/2024 | 2 | 0 | 2 | 01/12/2024 | 01/12/2024 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 4/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | BEVERLY | 674775 | 01915 | 5.76 | Solar | 05_01_26W3 | 02/27/2025 | 03/18/2025 | 2 | 0 | 2 | 03/19/2025 | 03/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 | 02/27/2025 | 4/18/2026 | Y | EXP | 365 | 10/28/2025 | 10/27/2025 | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | HAVERHILL | 177030 | 01832 | 224 | Solar | 05_01_413L1 | 03/19/2017 | 03/19/2017 | 69 | 68 | 1 | 06/27/2017 | 06/27/2017 | 0 | 0 | 0 | 12/07/2017 | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 |  | 01/04/2018 | 106 | 0 | 106 |  |  | 0 | 0 | 0 | 9/14/2017 |  | 3/30/2018 | N | EXP | 197 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/14/2018 | Connected |  | N
National Grid | AMESBURY | 177090 | 01913 | 4500 | Solar | 05_01_607W1 | 01/17/2017 | 01/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2017 | 02/10/2017 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 177926 | 01841 | 7.6 | Solar | 05_05_115W53 | 04/18/2017 | 04/18/2017 | 4 | 4 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/23/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/26/2017 | 10/26/2017 | 10/26/2017 | Connected |  | N
National Grid | BOLTON | 555498 | 01740 | 23.8 | Solar | 05_12_28L2 | 09/14/2023 | 10/25/2023 | 28 | 23 | 5 | 10/26/2023 | 10/26/2023 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | MILLBURY | 351267 | 01527 | 100 | Solar | 05_12_79J1 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 683783 | 01550 | 0 | Battery Add-On | 05_14_43L2 | 04/08/2025 | 04/21/2025 | 8 | 4 | 4 | 04/22/2025 | 04/22/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | WINCHENDON | 727510 | 01475 | 11.5 | Solar | 05_14_5J11 | 10/23/2025 | 10/27/2025 | 2 | 0 | 2 | 10/28/2025 | 10/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | FALL RIVER | 475239 | 02721 | 7.6 | Solar | 05_14_74L3 | 12/07/2022 | 12/11/2022 | 3 | 0 | 3 | 12/12/2022 | 12/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | GLOUCESTER | 582976 | 01930 | 8.775 | Solar | 05_01_216W6 | 01/29/2024 | 02/08/2024 | 9 | 8 | 1 | 02/09/2024 | 02/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | NAHANT | 683563 | 01908 | 13.8 | Solar | 05_01_26W3 | 04/16/2025 | 08/29/2025 | 29 | 24 | 5 | 09/02/2025 | 09/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 04/16/2025 | 10/20/2026 | Y | EXP | 365 | 02/04/2026 | 02/11/2026 | 8 | 0 | 8 |  |  | 2/13/2026 | Connected |  | N
National Grid | HAVERHILL | 178353 | 01832 | 5 | Solar | 05_01_413L1 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/06/2018 | 03/06/2018 | 239 | 0 | 239 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 3/5/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/12/2018 | Connected |  | N
National Grid | AMESBURY | 177393 | 01913 | 4950 | Solar | 05_01_607W1 | 02/17/2017 | 02/27/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2017 | 03/14/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 02/17/2017 | 12/31/2020 | Y | STD | 838 | 12/12/2019 | 12/31/2020 | 385 | 5 | 380 | 12/30/2020 | 12/31/2020 | 12/31/2019 | Connected |  | N
National Grid | LAWRENCE | 178132 | 01841 | 3.8 | Solar | 05_05_115W53 | 07/12/2017 | 07/12/2017 | 4 | 4 | 0 | 07/19/2017 | 07/19/2017 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/18/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 560873 | 01740 | 23 | Solar | 05_12_28L2 | 10/05/2023 | 10/06/2023 | 1 | 0 | 1 | 10/10/2023 | 10/10/2023 | 112 | 91 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2024 | Connected |  | N
National Grid | AUBURN | 387711 | 01501 | 15.2 | Solar | 05_12_79J1 | 10/11/2021 | 10/13/2021 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 2/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 714209 | 01550 | 15.2 | Solar | 05_14_43L2 | 08/24/2025 | 09/17/2025 | 16 | 15 | 1 | 09/18/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2026 | Connected |  | N
National Grid | GARDNER | 616963 | 01440 | 6 | Solar | 05_14_5J12 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2024 | Connected |  | N
National Grid | FALL RIVER | 505172 | 02721 | 6 | Solar | 05_14_74L3 | 03/09/2023 | 03/16/2023 | 5 | 0 | 5 | 03/17/2023 | 03/17/2023 | 23 | 0 | 23 | 04/27/2023 | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MANCHESTER | 588321 | 01944 | 6.282 | Solar | 05_01_216W6 | 03/05/2024 | 03/27/2024 | 17 | 16 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | NAHANT | 707156 | 01908 | 11.31 | Solar | 05_01_26W3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | HAVERHILL | 184817 | 01832 | 478 | Solar | 05_01_413L1 | 01/04/2019 | 01/08/2019 | 1 | 0 | 1 |  |  | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177538 | 01913 | 4990 | Solar | 05_01_607W1 | 11/06/2017 | 12/15/2017 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2017 | 01/10/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 178394 | 01841 | 2470 | Solar | 05_05_115W53 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/12/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 586229 | 01740 | 6 | Solar | 05_12_28L2 | 02/05/2024 | 02/07/2024 | 2 | 0 | 2 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/05/2024 | 3/18/2025 | Y | EXP | 365 | 05/08/2024 | 05/20/2024 | 13 | 0 | 13 |  |  | 7/19/2024 | Connected |  | N
National Grid | AUBURN | 490037 | 01501 | 4.06 | Solar | 05_12_79J1 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 4/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 724254 | 01550 | 11.4 | Solar | 05_14_43L2 | 10/06/2025 | 12/18/2025 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 201623 | 01440 | 7.6 | Solar | 05_14_5J13 | 11/19/2018 |  | 197 | 26 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 516649 | 02721 | 10 | Solar | 05_14_74L3 | 05/19/2023 | 05/22/2023 | 2 | 1 | 1 | 05/23/2023 | 05/23/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 05/19/2023 | 8/16/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 2/28/2024 | Connected |  | N
National Grid | GLOUCESTER | 598176 | 01930 | 11.5 | Solar | 05_01_216W6 | 03/20/2024 | 04/11/2024 | 16 | 13 | 3 | 04/12/2024 | 04/12/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NAHANT | 711413 | 01908 | 15.2 | Solar | 05_01_26W3 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 08/12/2025 | 10/10/2026 | Y | EXP | 365 | 02/03/2026 | 02/05/2026 | 3 | 0 | 3 |  |  | 3/4/2026 | Connected |  | N
National Grid | HAVERHILL | 193984 | 01832 | 72 | Solar | 05_01_413L1 | 10/23/2018 | 10/25/2018 | 178 | 28 | 150 | 12/14/2018 | 12/14/2018 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177882 | 01913 | 3300 | Solar | 05_01_607W1 | 10/18/2017 | 12/21/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 12/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  | 10/24/2018 | N | STD | 43 | 10/10/2018 | 03/01/2019 | 142 | 0 | 142 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 193337 | 01841 | 290 | Solar | 05_05_115W53 | 08/13/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 26 | 5 | 21 | 12/07/2018 | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  | 01/24/2019 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 624869 | 01740 | 6.825 | Solar | 05_12_28L2 | 07/15/2024 | 03/25/2025 | 4 | 1 | 3 | 03/26/2025 | 03/26/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | AUBURN | 711878 | 01501 | 17.6 | Solar | 05_12_79J1 | 08/15/2025 | 08/21/2025 | 4 | 0 | 4 | 08/22/2025 | 08/22/2025 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 704923 | 01550 | 200 | Solar | 05_14_43L3 | 07/15/2025 | 09/10/2025 | 40 | 31 | 9 | 09/11/2025 | 09/11/2025 | 52 | 33 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WINCHENDON | 203345 | 01475 | 13.8 | Solar | 05_14_5J13 | 12/21/2018 | 01/25/2019 | 22 | 22 | 0 | 01/25/2019 | 01/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 | 12/21/2018 | 3/26/2020 | Y | EXP | 422 | 10/18/2019 | 02/21/2020 | 126 | 0 | 126 |  |  | 2/25/2020 | Connected |  | N
National Grid | FALL RIVER | 539231 | 02721 | 5.76 | Solar | 05_14_74L3 | 07/11/2023 | 07/12/2023 | 1 | 0 | 1 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  | 11/13/2024 | N | EXP | 365 | 04/17/2024 | 05/28/2024 | 42 | 0 | 42 |  |  | 6/10/2024 | Connected |  | N
National Grid | MANCHESTER | 609347 | 01944 | 100 | Solar | 05_01_216W6 | 05/29/2024 | 08/20/2024 | 57 | 48 | 9 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 05/29/2024 | 11/16/2025 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2025 | Connected |  | N
National Grid | NAHANT | 722655 | 01908 | 10 | Solar | 05_01_26W4 | 09/29/2025 | 10/02/2025 | 3 | 0 | 3 | 10/03/2025 | 10/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | HAVERHILL | 196406 | 01835 | 66.6 | Solar | 05_01_413L1 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 5/1/2020 | N | EXP | 379 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177919 | 01913 | 3300 | Solar | 05_01_607W1 | 10/23/2017 | 10/23/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 |  | 100 | 0 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 193334 | 01844 | 119.9 | Solar | 05_05_115W53 | 08/13/2018 | 10/22/2018 | 6 | 1 | 5 | 10/23/2018 | 10/23/2018 | 45 | 29 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 650150 | 01740 | 23 | Solar | 05_12_28L2 | 10/28/2024 | 11/20/2024 | 4 | 0 | 4 | 04/15/2025 | 04/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | AUBURN | 392553 | 01501 | 13.96 | Solar | 05_12_79J2 | 11/22/2021 | 01/06/2022 | 10 | 6 | 4 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 | 11/22/2021 | 7/27/2023 | Y | EXP | 365 | 04/28/2022 | 06/02/2022 | 36 | 0 | 36 |  |  | 8/9/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 750989 | 01550 | 15.96 | Solar | 05_14_43L3 | 02/12/2026 | 02/18/2026 | 3 | 0 | 3 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 290419 | 01440 | 10 | Solar | 05_14_5J13 | 05/04/2020 | 05/06/2020 | 2 | 2 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2020 | Connected |  | N
National Grid | FALL RIVER | 544120 | 02721 | 5.04 | Solar | 05_14_74L3 | 09/05/2023 | 09/06/2023 | 1 | 0 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 | 10/24/2023 | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 11/27/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 11/29/2024 | N | EXP | 365 | 02/01/2024 | 04/19/2024 | 79 | 0 | 79 |  |  | 5/6/2024 | Connected |  | N
National Grid | MANCHESTER | 638189 | 01944 | 10 | Solar | 05_01_216W6 | 09/06/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 09/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | NAHANT | 347070 | 01908 | 26 | Solar | 05_01_27W1 | 03/31/2022 | 04/11/2022 | 7 | 0 | 7 | 04/12/2022 | 04/12/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/16/2026 | N | EXP | 1 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 293474 | 01835 | 7.92 | Solar | 05_01_413L1 | 06/17/2020 | 07/09/2020 | 16 | 12 | 4 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2021 | Connected |  | N
National Grid | AMESBURY | 177998 | 01913 | 660 | Solar | 05_01_607W1 | 10/25/2017 | 01/05/2018 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/19/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 193191 | 01844 | 199.9 | Solar | 05_05_115W53 | 08/13/2018 | 10/15/2018 | 21 | 17 | 4 | 10/16/2018 | 10/16/2018 | 23 | 0 | 23 | 12/07/2018 | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  | 01/24/2019 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 651396 | 01740 | 9.86 | Solar | 05_12_28L2 | 11/01/2024 | 12/02/2024 | 5 | 0 | 5 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/01/2024 | 3/14/2026 | Y | EXP | 365 | 06/12/2025 | 06/12/2025 | 1 | 0 | 1 |  |  | 6/20/2025 | Connected |  | N
National Grid | WORCESTER | 398056 | 01604 | 15.2 | Solar | 05_12_79J2 | 11/29/2021 | 12/08/2021 | 7 | 6 | 1 | 12/09/2021 | 12/09/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  | 5/1/2023 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 176543 | 01550 | 476 | Solar | 05_14_43L3 | 03/30/2016 | 03/30/2016 | 4 | 4 | 0 | 04/07/2016 | 04/07/2016 | 457 | 0 | 457 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 10/31/2017 | N | EXP | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 525541 | 01475 | 15 | Solar | 05_14_5J13 | 05/10/2023 | 05/12/2023 | 2 | 0 | 2 | 05/15/2023 | 05/15/2023 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | Y
National Grid | FALL RIVER | 544833 | 02721 | 10 | Solar | 05_14_74L3 | 08/16/2023 | 08/21/2023 | 3 | 0 | 3 | 08/22/2023 | 08/22/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 9/24/2024 | Y | EXP | 365 | 03/26/2024 | 04/23/2024 | 29 | 0 | 29 |  |  | 6/1/2024 | Connected |  | N
National Grid | MANCHESTER | 645214 | 01944 | 6.175 | Solar | 05_01_216W6 | 10/08/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NAHANT | 665454 | 01908 | 60 | Solar | 05_01_27W1 | 02/10/2025 | 03/26/2025 | 31 | 22 | 9 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/13/2026 | N | EXP | 12 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 419438 | 01835 | 7.6 | Solar | 05_01_413L1 | 03/23/2022 | 05/05/2022 | 31 | 30 | 1 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N
National Grid | AMESBURY | 178113 | 01913 | 4990 | Solar | 05_01_607W1 | 11/06/2017 | 12/12/2017 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/10/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 206944 | 01844 | 420 | Solar | 05_05_115W53 | 01/24/2019 | 02/07/2019 | 8 | 6 | 2 | 02/08/2019 | 02/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2020 | Connected |  | N
National Grid | BOLTON | 659984 | 01740 | 11.7 | Solar | 05_12_28L2 | 12/11/2024 | 03/26/2025 | 4 | 1 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | WORCESTER | 404987 | 01604 | 15.356 | Solar | 05_12_79J2 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2022 | 01/05/2022 | 6/9/2023 | Y | EXP | 365 | 04/28/2022 | 06/08/2022 | 42 | 0 | 42 |  |  | 6/15/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 177341 | 01550 | 750 | Solar | 05_14_43L3 | 11/18/2016 | 11/18/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 | 12/28/2016 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 625454 | 01440 | 10 | Solar | 05_14_5J13 | 07/17/2024 | 07/29/2024 | 0 | 0 | 0 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/17/2024 | 10/8/2025 | Y | EXP | 365 | 11/13/2024 | 01/13/2025 | 62 | 0 | 62 |  |  | 1/30/2025 | Connected |  | N
National Grid | FALL RIVER | 547080 | 02721 | 6 | Solar | 05_14_74L3 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2023 | 08/16/2023 | 11/14/2024 | Y | EXP | 365 | 01/24/2024 | 01/31/2024 | 8 | 0 | 8 |  |  | 3/18/2024 | Connected |  | N
National Grid | MANCHESTER | 655285 | 01944 | 7.6 | Solar | 05_01_216W6 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | NAHANT | 723925 | 01908 | 7.6 | Solar | 05_01_27W1 | 10/03/2025 | 12/09/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 482280 | 01835 | 18.816 | Solar | 05_01_413L1 | 01/03/2023 | 01/25/2023 | 15 | 14 | 1 | 01/26/2023 | 01/26/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 3/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | AMESBURY | 178530 | 01913 | 1250 | Solar | 05_01_607W1 | 12/04/2017 | 12/04/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/01/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 210964 | 01841 | 7.6 | Solar | 05_05_115W53 | 03/17/2019 | 03/19/2019 | 1 | 1 | 0 | 03/20/2019 | 03/20/2019 | 113 | 25 | 88 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 664791 | 01740 | 4.64 | Solar | 05_12_28L2 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | WORCESTER | 422671 | 01604 | 15.2 | Solar | 05_12_79J2 | 04/07/2022 | 04/08/2022 | 1 | 0 | 1 | 04/11/2022 | 04/11/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 | 04/07/2022 | 6/6/2024 | Y | EXP | 365 | 05/18/2023 | 06/07/2023 | 21 | 0 | 21 |  |  | 7/10/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 177479 | 01550 | 75.6 | Solar | 05_14_43L3 | 07/06/2016 | 07/06/2016 | 35 | 35 | 0 | 08/26/2016 | 08/26/2016 | 244 | 55 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 |  | 8/31/2017 | N | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 177256 | 01475 | 43.2 | Solar | 05_14_5J15 | 08/17/2016 | 08/17/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 8/22/2017 | N | EXP | 321 |  |  | 0 | 0 | 0 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | FALL RIVER | 551612 | 02721 | 6.09 | Solar | 05_14_74L3 | 09/05/2023 | 09/25/2023 | 15 | 14 | 1 | 09/26/2023 | 09/26/2023 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2023 | 09/05/2023 | 2/9/2025 | Y | EXP | 365 | 01/31/2024 | 03/22/2024 | 52 | 0 | 52 |  |  | 6/13/2024 | Connected |  | N
National Grid | GLOUCESTER | 657684 | 01930 | 10 | Solar | 05_01_216W6 | 12/02/2024 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NAHANT | 735996 | 01908 | 5.76 | Solar | 05_01_27W1 | 11/24/2025 | 12/22/2025 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HAVERHILL | 573990 | 01832 | 6 | Solar | 05_01_413L1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 178646 | 01913 | 4980 | Solar | 05_01_607W1 | 12/15/2017 | 09/07/2018 | 75 | 51 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2018 | 05/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 214093 | 01844 | 7.36 | Solar | 05_05_115W53 | 05/17/2019 | 05/30/2019 | 7 | 1 | 6 | 05/31/2019 | 05/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 | 05/17/2019 | 6/16/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | BOLTON | 676411 | 01740 | 15.2 | Solar | 05_12_28L2 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 538674 | 01604 | 15.2 | Solar | 05_12_79J2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 201984 | 01550 | 3.8 | Solar | 05_14_43L3 | 11/26/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 299817 | 01475 | 7.6 | Solar | 05_14_5J15 | 02/04/2021 | 02/08/2021 | 1 | 0 | 1 | 02/09/2021 | 02/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 560972 | 02721 | 7.6 | Solar | 05_14_74L3 | 10/05/2023 | 05/07/2024 | 2 | 0 | 2 | 05/08/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 10/05/2023 | 6/12/2025 | Y | EXP | 365 | 07/31/2024 | 09/30/2024 | 62 | 0 | 62 |  |  | 10/17/2024 | Connected |  | N
National Grid | GLOUCESTER | 678256 | 01930 | 17.6 | Solar | 05_01_216W6 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 | 03/21/2025 | 5/2/2026 | Y | EXP | 365 | 07/04/2025 | 11/17/2025 | 137 | 0 | 137 |  |  | 12/4/2025 | Connected |  | N
National Grid | NAHANT | 739521 | 01908 | 5.76 | Solar | 05_01_27W1 | 12/11/2025 | 02/06/2026 | 7 | 5 | 2 | 02/09/2026 | 02/09/2026 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 579815 | 01835 | 7.25 | Solar | 05_01_413L1 | 01/05/2024 | 01/12/2024 | 5 | 3 | 2 | 01/16/2024 | 01/16/2024 | 170 | 25 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 278494 | 01913 | 5 | Solar | 05_05_115W53 | 03/04/2020 | 03/18/2020 | 10 | 7 | 3 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2020 | 03/04/2020 |  | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/25/2020 | Connected |  | N
National Grid | LAWRENCE | 683914 | 01841 | 11.05 | Solar | 05_12_28L2 | 04/09/2025 | 05/07/2025 | 6 | 3 | 3 | 05/08/2025 | 05/08/2025 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | BOLTON | 612259 | 01740 | 15.2 | Solar | 05_12_79J2 | 05/20/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | WORCESTER | 322749 | 01604 | 7.6 | Solar | 05_14_43L3 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2020 | 11/12/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 6/29/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 307055 | 01550 | 7.6 | Solar | 05_14_5J15 | 08/28/2020 | 08/31/2020 | 0 | 0 | 0 | 09/01/2020 | 09/01/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 | 08/28/2020 | 8/30/2021 | Y | EXP | 365 | 12/19/2020 | 01/21/2021 | 33 | 0 | 33 |  |  | 5/25/2021 | Connected |  | N
National Grid | WINCHENDON | 567261 | 01475 | 5 | Solar | 05_14_74L3 | 03/28/2024 | 12/26/2023 | 12 | 9 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 5/23/2025 | Y | EXP | 365 | 06/05/2024 | 08/20/2024 | 77 | 0 | 77 |  |  | 10/11/2024 | Connected |  | N
National Grid | FALL RIVER | 699612 | 02721 | 15.2 | Solar | 05_01_216W6 | 06/25/2025 | 06/30/2025 | 10 | 7 | 3 | 07/14/2025 | 07/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2025 | Connected |  | N
National Grid | MANCHESTER | 174418 | 01944 | 110 | Solar | 05_01_27W1 | 10/20/2011 | 10/20/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2011 | 10/20/2011 | 5/4/2012 | Y | EXP | 137 | 03/12/2012 | 04/12/2012 | 22 | 0 | 22 | 1/25/2013 | 1/25/2013 | 5/4/2012 | Connected |  | N
National Grid | NAHANT | 585346 | 01908 | 8.12 | Solar | 05_01_413L1 | 03/15/2024 | 03/20/2024 | 3 | 0 | 3 | 03/21/2024 | 03/21/2024 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 03/15/2024 | 4/23/2025 | Y | EXP | 365 | 07/17/2024 | 08/13/2024 | 28 | 0 | 28 |  |  | 8/31/2024 | Connected |  | N
National Grid | HAVERHILL | 195209 | 01835 | 8290 | Solar | 05_01_607W1 | 10/22/2018 | 10/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/06/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 281069 | 01913 | 5 | Solar | 05_05_115W53 | 04/06/2020 | 04/20/2020 | 9 | 9 | 0 | 04/21/2020 | 04/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/06/2020 | 4/19/2021 | Y | EXP | 365 | 07/03/2020 | 07/31/2020 | 28 | 0 | 28 |  |  | 8/12/2020 | Connected |  | Y
National Grid | LAWRENCE | 691827 | 01841 | 23.8 | Solar | 05_12_28L2 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | HARVARD | 710901 | 01451 | 9.6 | Solar | 05_12_79J2 | 08/20/2025 | 09/15/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | WORCESTER | 342609 | 01604 | 5 | Solar | 05_14_43L3 | 03/04/2021 | 03/09/2021 | 2 | 0 | 2 | 03/10/2021 | 03/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/04/2021 | 10/5/2022 | Y | EXP | 365 | 09/11/2021 | 09/21/2021 | 6 | 0 | 6 |  |  | 9/29/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 533655 | 01550 | 10 | Solar | 05_14_5J16 | 06/20/2023 | 06/28/2023 | 6 | 4 | 2 | 06/29/2023 | 06/29/2023 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 06/20/2023 | 9/28/2024 | Y | EXP | 365 | 01/04/2024 | 01/18/2024 | 15 | 0 | 15 |  |  | 1/29/2024 | Connected |  | N
National Grid | GARDNER | 580225 | 01440 | 5.8 | Solar | 05_14_74L3 | 01/11/2024 | 01/22/2024 | 7 | 6 | 1 | 01/23/2024 | 01/23/2024 | 88 | 71 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 01/11/2024 | 6/4/2025 | Y | EXP | 365 | 09/19/2024 | 11/06/2024 | 49 | 0 | 49 |  |  | 11/19/2024 | Connected |  | N
National Grid | FALL RIVER | 706361 | 02721 | 10 | Solar | 05_01_216W6 | 07/22/2025 | 08/06/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | GLOUCESTER | 175075 | 01930 | 75 | Solar | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2013 |  | 11/10/2016 | N | EXP | 1122 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/15/2016 | Connected |  | N
National Grid | NAHANT | 657508 | 01908 | 9.88 | Solar | 05_01_413L1 | 11/27/2024 | 12/29/2024 | 12 | 8 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 261017 | 01835 | 10 | Solar | 05_01_607W1 | 11/20/2019 | 11/26/2019 | 3 | 0 | 3 | 11/27/2019 | 11/27/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 280777 | 01913 | 3.8 | Solar | 05_05_115W53 | 03/10/2020 | 03/18/2020 | 5 | 0 | 5 | 03/19/2020 | 03/19/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 713834 | 01841 | 15.2 | Solar | 05_12_28L2 | 08/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 08/21/2025 | 10/24/2026 | Y | EXP | 365 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 |  |  | 12/13/2025 | Connected |  | N
National Grid | BOLTON | 639120 | 01740 | 7.36 | Solar | 05_12_7J1 | 09/10/2024 | 10/02/2024 | 4 | 0 | 4 | 10/03/2024 | 10/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | WORCESTER | 412233 | 01604 | 0 | Battery Add-On | 05_14_43L3 | 05/28/2022 | 08/09/2022 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/10/2022 | 09/07/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 501981 | 01550 | 11.02 | Solar | 05_14_5J40 | 02/14/2023 | 03/21/2023 | 25 | 23 | 2 | 03/22/2023 | 03/22/2023 | 129 | 109 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | GARDNER | 586831 | 01440 | 7.83 | Solar | 05_14_74L3 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 7/24/2025 | Y | EXP | 465 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | FALL RIVER | 714691 | 02721 | 25 | Solar | 05_01_216W6 | 08/28/2025 | 09/09/2025 | 6 | 4 | 2 | 09/10/2025 | 09/10/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | MANCHESTER | 175074 | 01944 | 100 | Solar | 05_01_27W1 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2013 |  | 12/5/2016 | N | EXP | 1119 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/6/2016 | Connected |  | N
National Grid | REVERE | 663621 | 02151 | 10 | Solar | 05_01_413L1 | 01/03/2025 | 01/17/2025 | 6 | 0 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | HAVERHILL | 355755 | 01835 | 10 | Solar | 05_01_607W1 | 06/07/2021 | 06/15/2021 | 6 | 0 | 6 | 06/16/2021 | 06/16/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 317453 | 01844 | 50 | Solar | 05_05_115W53 | 10/06/2020 | 11/03/2020 | 18 | 13 | 5 | 11/04/2020 | 11/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | LAWRENCE | 700420 | 01841 | 7.6 | Solar | 05_12_29W1 | 07/01/2025 | 07/15/2025 | 3 | 0 | 3 | 07/24/2025 | 07/24/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 07/01/2025 | 12/8/2026 | Y | EXP | 365 | 11/14/2025 | 11/14/2025 | 1 | 0 | 1 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 743642 | 01740 | 3.8 | Solar | 05_12_7J2 | 01/06/2026 | 01/08/2026 | 1 | 0 | 1 | 01/22/2026 | 01/22/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 498937 | 01604 | 5.04 | Solar | 05_14_43L3 | 02/28/2023 | 03/07/2023 | 5 | 3 | 2 | 03/08/2023 | 03/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 02/28/2023 | 11/29/2024 | Y | EXP | 365 | 06/09/2023 | 02/03/2024 | 240 | 3 | 237 |  |  | 2/6/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 534198 | 01550 | 6.912 | Solar | 05_14_5J40 | 03/20/2024 | 04/15/2024 | 18 | 15 | 3 | 04/16/2024 | 04/16/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 597076 | 01440 | 8.12 | Solar | 05_14_74L3 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 720645 | 02721 | 11.78 | Solar | 05_01_216W6 | 09/21/2025 | 09/26/2025 | 5 | 0 | 5 | 09/29/2025 | 09/29/2025 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LYNN | 189268 | 01905 | 15.2 | Solar | 05_01_27W1 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 06/26/2018 | 10/13/2019 | Y | EXP | 5 | 05/02/2020 | 05/01/2020 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 663838 | 02151 | 3.8 | Solar | 05_01_413L1 | 01/06/2025 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 450860 | 01835 | 5 | Solar | 05_01_607W1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 | 10/11/2022 | 9/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2023 | Connected |  | N
National Grid | METHUEN | 391147 | 01844 | 10 | Solar | 05_05_115W53 | 11/03/2021 | 01/10/2022 | 5 | 0 | 5 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/03/2021 | 5/3/2023 | Y | EXP | 365 | 03/11/2022 | 04/29/2022 | 50 | 0 | 50 |  |  | 7/9/2022 | Connected |  | N
National Grid | METHUEN | 703718 | 01844 | 6.72 | Solar | 05_12_29W1 | 07/09/2025 | 07/29/2025 | 9 | 3 | 6 | 09/30/2025 | 09/30/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 07/09/2025 | 12/5/2026 | Y | EXP | 365 | 01/22/2026 |  | 44 | 0 | 44 |  |  |  | Construction |  | N
National Grid | HARVARD | 234799 | 01451 | 10 | Solar | 05_12_7J2 | 07/19/2019 | 07/30/2019 | 6 | 0 | 6 | 07/31/2019 | 07/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 |  | 12/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | WORCESTER | 529552 | 01604 | 10 | Solar | 05_14_43L3 | 05/26/2023 | 06/05/2023 | 5 | 1 | 4 | 06/06/2023 | 06/06/2023 | 238 | 218 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 7/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 534674 | 01550 | 7.6 | Solar | 05_14_5J40 | 06/28/2023 | 07/05/2023 | 5 | 4 | 1 | 07/06/2023 | 07/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | GARDNER | 607376 | 01440 | 7.6 | Solar | 05_14_74L3 | 04/30/2024 | 05/06/2024 | 1 | 0 | 1 | 05/07/2024 | 05/07/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/30/2024 | 6/4/2025 | Y | EXP | 365 | 07/31/2024 | 10/01/2024 | 63 | 0 | 63 |  |  | 10/8/2024 | Connected |  | N
National Grid | FALL RIVER | 736348 | 02721 | 7.6 | Solar | 05_01_216W6 | 11/25/2025 | 12/10/2025 | 10 | 7 | 3 | 12/11/2025 | 12/11/2025 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 197109 | 01905 | 7.6 | Solar | 05_01_27W1 | 09/27/2018 | 10/18/2018 | 4 | 3 | 1 | 10/19/2018 | 10/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 8/30/2019 | N | EXP | 247 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | REVERE | 673133 | 02151 | 10 | Solar | 05_01_413L1 | 02/21/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 02/21/2025 | 4/11/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | HAVERHILL | 372586 | 01835 | 9.8 | Solar | 05_01_607W1 | 08/04/2021 | 08/05/2021 | 1 | 0 | 1 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/04/2021 | 11/24/2022 | Y | EXP | 365 | 10/15/2021 | 11/23/2021 | 40 | 4 | 36 |  |  | 12/1/2021 | Connected |  | Y
National Grid | METHUEN | 440461 | 01844 | 250 | Solar | 05_05_115W53 | 07/25/2022 | 08/10/2022 | 12 | 2 | 10 | 08/11/2022 | 08/11/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 07/25/2022 | 10/22/2025 | Y | EXP | 133 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 717420 | 01844 | 5.76 | Solar | 05_12_29W1 | 09/10/2025 | 10/03/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 | 09/10/2025 | 11/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HARVARD | 553820 | 01451 | 8.725 | Solar | 05_12_7J2 | 11/22/2023 | 12/29/2023 | 25 | 20 | 5 | 01/02/2024 | 01/02/2024 | 179 | 25 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 637884 | 01607 | 5.76 | Solar | 05_14_43L3 | 10/24/2024 | 11/01/2024 | 5 | 1 | 4 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/24/2024 | 3/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 574631 | 01550 | 6.38 | Solar | 05_14_5J40 | 01/23/2024 | 01/29/2024 | 4 | 0 | 4 | 01/30/2024 | 01/30/2024 | 79 | 54 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 | 01/23/2024 | 6/3/2025 | Y | EXP | 365 | 10/15/2024 | 01/03/2025 | 81 | 0 | 81 |  |  | 1/24/2025 | Connected |  | Y
National Grid | GARDNER | 619623 | 01440 | 6 | Solar | 05_14_74L3 | 06/21/2024 | 07/02/2024 | 3 | 0 | 3 | 07/03/2024 | 07/03/2024 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178695 | 02721 | 500 | Solar | 05_01_219W1 | 02/06/2018 | 02/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 06/21/2018 | 07/19/2018 | 19 | 0 | 19 | 03/05/2018 | 04/11/2018 | 28 | 8 | 20 |  | 07/19/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/25/2018 |  | 11/1/2019 | N | STD | 464 |  |  | 0 | 0 | 0 |  |  | 12/23/2019 | Connected |  | N
National Grid | LYNN | 201073 | 01904 | 396 | Solar | 05_01_27W1 | 11/15/2018 | 11/21/2018 | 4 | 2 | 2 | 11/26/2018 | 11/26/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 686535 | 02151 | 20 | Solar | 05_01_413L1 | 04/23/2025 | 04/29/2025 | 4 | 0 | 4 | 04/30/2025 | 04/30/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 389904 | 01835 | 9.57 | Solar | 05_01_607W1 | 10/26/2021 | 12/16/2021 | 2 | 2 | 0 | 10/29/2021 | 10/29/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 | 10/26/2021 | 5/26/2023 | Y | EXP | 365 | 04/27/2022 | 05/04/2022 | 8 | 0 | 8 |  |  | 6/29/2022 | Connected |  | N
National Grid | METHUEN | 492560 | 01844 | 7.6 | Solar | 05_05_115W53 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 | 02/01/2023 | 7/1/2024 | Y | EXP | 365 | 07/13/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 11/21/2023 | Connected |  | N
National Grid | LAWRENCE | 721288 | 01841 | 7.6 | Solar | 05_12_29W1 | 09/23/2025 | 10/21/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEOMINSTER | 583707 | 01453 | 7.6 | Solar | 05_12_7J2 | 01/29/2024 | 02/02/2024 | 5 | 4 | 1 | 02/05/2024 | 02/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/29/2024 | 3/17/2025 | Y | EXP | 365 | 05/09/2024 | 05/20/2024 | 12 | 0 | 12 |  |  | 8/20/2024 | Connected |  | N
National Grid | WORCESTER | 654621 | 01604 | 10 | Solar | 05_14_43L3 | 11/15/2024 | 12/17/2024 | 8 | 4 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/15/2024 | 3/18/2026 | Y | EXP | 365 | 04/22/2025 | 04/30/2025 | 9 | 0 | 9 |  |  | 4/5/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 596274 | 01550 | 5 | Solar | 05_14_5J40 | 04/01/2024 | 05/08/2024 | 26 | 23 | 3 | 05/09/2024 | 05/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 | 04/01/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 09/25/2024 | 72 | 0 | 72 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 627966 | 01440 | 5.22 | Solar | 05_14_74L3 | 07/26/2024 | 09/05/2024 | 19 | 18 | 1 | 09/06/2024 | 09/06/2024 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 340774 | 02721 | 25.52 | Solar | 05_01_219W1 | 02/09/2021 | 04/19/2021 | 47 | 46 | 1 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2021 | Connected |  | N
National Grid | LYNN | 206484 | 01905 | 480 | Solar | 05_01_27W1 | 03/13/2019 | 04/27/2019 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2019 | 05/23/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 03/13/2019 | 6/30/2023 | Y | STD | 644 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | REVERE | 688107 | 02151 | 15.2 | Solar | 05_01_413L1 | 04/28/2025 | 04/30/2025 | 2 | 0 | 2 | 05/01/2025 | 05/01/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 389245 | 01835 | 3.84 | Solar | 05_01_607W1 | 12/15/2021 | 01/07/2022 | 2 | 0 | 2 | 12/20/2021 | 12/20/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 501441 | 01844 | 14.79 | Solar | 05_05_115W53 | 06/13/2023 | 02/23/2023 | 13 | 9 | 4 | 07/05/2023 | 07/05/2023 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 744859 | 01841 | 3.8 | Solar | 05_12_29W1 | 01/15/2026 | 01/20/2026 | 8 | 4 | 4 | 02/05/2026 | 02/05/2026 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 638789 | 01453 | 3.8 | Solar | 05_12_7J2 | 09/09/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | WORCESTER | 655934 | 01604 | 5.76 | Solar | 05_14_43L3 | 11/21/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 597978 | 01550 | 3.8 | Solar | 05_14_5J40 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/18/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 636179 | 01440 | 10 | Solar | 05_14_74L3 | 08/28/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | FALL RIVER | 427478 | 02721 | 0 | Other | 05_01_219W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/14/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 260892 | 01905 | 6 | Solar | 05_01_27W1 | 11/01/2019 | 01/02/2020 | 40 | 38 | 2 | 01/03/2020 | 01/03/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/01/2019 | 9/3/2021 | Y | EXP | 365 | 05/06/2021 | 06/10/2021 | 35 | 0 | 35 |  |  | 8/10/2021 | Connected |  | N
National Grid | REVERE | 695187 | 02151 | 15.2 | Solar | 05_01_413L1 | 06/13/2025 | 06/24/2025 | 5 | 2 | 3 | 06/25/2025 | 06/25/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | HAVERHILL | 395576 | 01835 | 20.355 | Solar | 05_01_607W1 | 11/17/2021 | 12/22/2021 | 2 | 0 | 2 | 11/19/2021 | 11/19/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 2/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | METHUEN | 519921 | 01844 | 6 | Solar | 05_05_115W53 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 747398 | 01844 | 7.6 | Solar | 05_12_29W1 | 01/26/2026 | 02/02/2026 | 10 | 7 | 3 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 638214 | 01453 | 19.76 | Solar | 05_12_7J2 | 09/06/2024 | 09/11/2024 | 3 | 1 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | N
National Grid | WORCESTER | 657060 | 01604 | 10 | Solar | 05_14_43L3 | 11/26/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 651593 | 01550 | 3.8 | Solar | 05_14_5J40 | 11/12/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/12/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 636115 | 01440 | 6 | Solar | 05_14_74L3 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 701156 | 02721 | 6 | Solar | 05_01_219W1 | 06/25/2025 | 07/23/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 9/25/2026 | Y | EXP | 365 | 09/20/2025 | 09/19/2025 | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | LYNN | 336430 | 01904 | 6 | Solar | 05_01_27W1 | 01/15/2021 | 01/25/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2021 | Connected |  | N
National Grid | REVERE | 197148 | 02151 | 996 | Solar | 05_01_413L2 | 10/04/2018 | 11/02/2018 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2018 | 12/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2020 | 10/04/2018 | 3/7/2026 | Y | STD | 476 | 12/23/2025 |  | 74 | 0 | 74 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 524121 | 01835 | 14.5 | Solar | 05_01_607W1 | 05/04/2023 | 06/07/2023 | 24 | 22 | 2 | 06/08/2023 | 06/08/2023 | 64 | 44 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | Y
National Grid | METHUEN | 546881 | 01844 | 10 | Solar | 05_05_115W53 | 09/05/2023 | 08/15/2023 | 4 | 0 | 4 | 09/12/2023 | 09/12/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | LAWRENCE | 176207 | 01841 | 11.4 | Solar | 05_12_29W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/30/2015 | 04/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 08/29/2016 | 09/30/2016 | 23 | 0 | 23 | 9/12/2016 | 9/12/2016 | 9/12/2016 | Connected |  | N
National Grid | LEOMINSTER | 643463 | 01453 | 21.4 | Solar | 05_12_7J2 | 10/22/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/22/2024 | 12/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | WORCESTER | 657119 | 01604 | 5.76 | Solar | 05_14_43L3 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 656760 | 01550 | 10 | Solar | 05_14_5J40 | 12/03/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 636493 | 01440 | 5.22 | Solar | 05_14_74L3 | 08/29/2024 | 12/12/2024 | 21 | 19 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 682588 | 02721 | 11.866 | Solar | 05_01_219W2 | 04/10/2025 | 06/26/2025 | 7 | 3 | 4 | 07/15/2025 | 07/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | LYNN | 396408 | 01904 | 9.772 | Solar | 05_01_27W1 | 11/22/2021 | 12/22/2021 | 6 | 3 | 3 | 12/02/2021 | 12/02/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 5/31/2023 | N | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 6/6/2023 | Connected |  | N
National Grid | REVERE | 419334 | 02151 | 240 | Solar | 05_01_413L2 | 05/26/2022 | 06/13/2022 | 11 | 6 | 5 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 05/26/2022 | 6/26/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 558965 | 01835 | 11.5 | Solar | 05_01_607W1 | 01/11/2024 | 03/04/2024 | 35 | 31 | 4 | 03/05/2024 | 03/05/2024 | 24 | 22 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 01/11/2024 | 4/19/2025 | Y | EXP | 365 | 05/11/2024 | 05/15/2024 | 5 | 0 | 5 |  |  | 8/9/2024 | Connected |  | N
National Grid | METHUEN | 575780 | 01844 | 9.765 | Solar | 05_05_115W53 | 12/11/2023 | 12/14/2023 | 3 | 0 | 3 | 12/15/2023 | 12/15/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/11/2023 | 2/25/2025 | Y | EXP | 365 | 07/02/2024 | 08/02/2024 | 32 | 0 | 32 |  |  | 8/20/2024 | Connected |  | N
National Grid | LAWRENCE | 176763 | 01841 | 6 | Solar | 05_12_29W1 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 5/1/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 4/28/2016 | 4/28/2016 |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 682939 | 01453 | 3.8 | Solar | 05_12_7J2 | 04/04/2025 | 05/05/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/04/2025 | 6/12/2026 | Y | EXP | 365 | 09/11/2025 | 12/01/2025 | 82 | 0 | 82 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 658163 | 01604 | 7.6 | Solar | 05_14_43L3 | 12/03/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/03/2024 | 2/21/2026 | Y | EXP | 365 | 02/20/2025 | 03/19/2025 | 28 | 14 | 14 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 677063 | 01566 | 100 | Solar | 05_14_5J40 | 03/31/2025 | 05/06/2025 | 25 | 16 | 9 | 05/07/2025 | 05/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 |  | 3/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Connected |  | N
National Grid | GARDNER | 639000 | 01440 | 9.28 | Solar | 05_14_74L3 | 09/10/2024 | 10/08/2024 | 11 | 10 | 1 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 715054 | 02721 | 7.6 | Solar | 05_01_219W2 | 09/10/2025 | 09/16/2025 | 4 | 0 | 4 | 09/17/2025 | 09/17/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 467875 | 01905 | 6 | Solar | 05_01_27W1 | 11/28/2022 |  | 239 | 65 | 174 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 406202 | 02151 | 249 | Solar | 05_01_413L2 | 01/14/2022 | 03/03/2022 | 32 | 24 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 01/14/2022 | 5/11/2026 | Y | STD | 224 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 533436 | 01835 | 0 | Battery Add-On | 05_01_607W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 90 | 25 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 577963 | 01844 | 10 | Solar | 05_05_115W53 | 12/18/2023 | 01/02/2024 | 8 | 6 | 2 | 01/03/2024 | 01/03/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/18/2023 | 2/6/2025 | Y | EXP | 365 | 03/26/2024 | 03/25/2024 | 0 | 0 | 0 |  |  | 4/23/2024 | Connected |  | N
National Grid | LAWRENCE | 177003 | 01841 | 6.6 | Solar | 05_12_29W1 | 10/07/2016 | 10/07/2016 | 1 | 1 | 0 | 10/11/2016 | 10/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/07/2016 | 3/30/2018 | Y | EXP | 529 | 10/09/2017 | 10/11/2017 | 1 | 0 | 1 | 2/12/2018 | 2/12/2018 | 3/23/2018 | Connected |  | N
National Grid | LEOMINSTER | 178628 | 01453 | 3.8 | Solar | 05_12_7J3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/21/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 661220 | 01604 | 10 | Solar | 05_14_43L3 | 12/17/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | STURBRIDGE | 692129 | 01566 | 11.52 | Solar | 05_14_5J41 | 05/29/2025 | 08/08/2025 | 1 | 0 | 1 | 08/18/2025 | 08/18/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | GARDNER | 639679 | 01440 | 5.856 | Solar | 05_14_74L3 | 09/12/2024 | 10/04/2024 | 8 | 2 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/12/2024 | 11/14/2025 | Y | EXP | 365 | 01/30/2025 | 04/24/2025 | 85 | 0 | 85 |  |  | 4/28/2025 | Connected |  | N
National Grid | FALL RIVER | 717728 | 02721 | 3.8 | Solar | 05_01_219W2 | 09/09/2025 | 09/23/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 09/09/2025 | 12/1/2026 | Y | EXP | 365 | 02/19/2026 |  | 16 | 0 | 16 |  |  |  | Construction |  | N
National Grid | LYNN | 556062 | 01904 | 7.6 | Solar | 05_01_27W1 | 03/15/2024 | 09/22/2023 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | REVERE | 431376 | 02151 | 500 | Solar | 05_01_413L2 | 06/06/2022 | 06/22/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/06/2022 | 1/27/2027 | Y | STD | 397 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HAVERHILL | 555974 | 01835 | 10 | Solar | 05_01_607W1 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 | 09/26/2023 | 11/18/2024 | Y | EXP | 365 | 01/18/2024 | 01/23/2024 | 6 | 0 | 6 |  |  | 2/26/2024 | Connected |  | N
National Grid | METHUEN | 617210 | 01844 | 7.6 | Solar | 05_05_115W53 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/11/2024 | 8/7/2025 | Y | EXP | 365 | 09/25/2024 | 10/16/2024 | 22 | 0 | 22 |  |  | 10/29/2024 | Connected |  | N
National Grid | LAWRENCE | 177253 | 01841 | 3.8 | Solar | 05_12_29W1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 06/14/2016 | 6/20/2017 | Y | EXP | 358 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | LEOMINSTER | 407783 | 01453 | 3.84 | Solar | 05_12_7J3 | 02/21/2022 | 02/22/2022 | 1 | 0 | 1 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 662220 | 01604 | 5.76 | Solar | 05_14_43L3 | 12/23/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 742521 | 01566 | 150 | Solar | 05_14_5J41 | 12/31/2025 | 02/04/2026 | 22 | 13 | 9 | 02/05/2026 | 02/05/2026 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 643551 | 01440 | 10 | Solar | 05_14_74L3 | 09/27/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | FALL RIVER | 733103 | 02721 | 10 | Solar | 05_01_219W2 | 11/12/2025 | 12/26/2025 | 2 | 0 | 2 | 12/29/2025 | 12/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 573451 | 01904 | 5.51 | Solar | 05_01_27W1 | 12/12/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | REVERE | 708984 | 02151 | 0 | Other | 05_01_413L2 | 10/08/2025 | 11/20/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAVERHILL | 564080 | 01835 | 0 | Battery Add-On | 05_01_607W1 | 10/19/2023 |  | 222 | 222 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 634387 | 01844 | 10 | Solar | 05_05_115W53 | 08/21/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2024 | 08/21/2024 | 10/28/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | LAWRENCE | 204587 | 01841 | 3.8 | Solar | 05_12_29W1 | 01/07/2019 | 01/18/2019 | 8 | 0 | 8 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/07/2019 | 9/16/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2021 | Connected |  | N
National Grid | LEOMINSTER | 210788 | 01453 | 7.6 | Solar | 05_12_7J4 | 03/04/2019 | 03/05/2019 | 0 | 0 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/04/2019 | 7/21/2020 | Y | EXP | 365 | 02/25/2020 | 03/19/2020 | 23 | 0 | 23 |  |  | 5/26/2020 | Connected |  | N
National Grid | WORCESTER | 662119 | 01604 | 3.8 | Solar | 05_14_43L3 | 12/21/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | STURBRIDGE | 176466 | 01566 | 408 | Solar | 05_14_5J41 | 02/05/2016 | 02/05/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 646410 | 01440 | 11.4 | Solar | 05_14_74L3 | 10/17/2024 | 11/12/2024 | 14 | 11 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 2/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | FALL RIVER | 746248 | 02721 | 5.76 | Solar | 05_01_219W2 | 01/20/2026 | 01/22/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 596342 | 01904 | 0 | Solar | 05_01_27W1 | 03/28/2024 | 04/01/2024 | 7 | 3 | 4 | 04/09/2024 | 04/09/2024 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2024 | Connected |  | N
National Grid | REVERE | 737365 | 02151 | 7.6 | Solar | 05_01_413L2 | 12/02/2025 | 12/03/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 593301 | 01835 | 7.6 | Solar | 05_01_607W1 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/06/2024 | 4/1/2025 | Y | EXP | 365 | 07/25/2024 | 07/29/2024 | 5 | 0 | 5 |  |  | 8/20/2024 | Connected |  | N
National Grid | METHUEN | 640654 | 01844 | 7.6 | Solar | 05_05_115W53 | 09/18/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 2/18/2025 | Connected |  | N
National Grid | METHUEN | 205264 | 01844 | 7.6 | Solar | 05_12_29W1 | 02/04/2019 | 02/07/2019 | 3 | 3 | 0 | 02/08/2019 | 02/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 184583 | 01453 | 15.2 | Solar | 05_12_7J6 | 07/15/2018 | 07/18/2018 | 1 | 0 | 1 | 07/19/2018 | 07/19/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2019 | Connected |  | N
National Grid | WORCESTER | 494666 | 01604 | 360 | Solar | 05_14_43L4 | 07/11/2023 | 09/01/2023 | 39 | 30 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2023 | 10/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOUTHBRIDGE | 418542 | 01550 | 7.6 | Solar | 05_14_5J41 | 03/21/2022 | 03/25/2022 | 4 | 0 | 4 | 03/28/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/21/2022 | 5/27/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | N
National Grid | GARDNER | 649008 | 01440 | 10 | Solar | 05_14_74L3 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | FALL RIVER | 745876 | 02721 | 11.5 | Battery Add-On | 05_01_219W2 | 01/16/2026 | 01/22/2026 | 3 | 0 | 3 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 600309 | 01904 | 5 | Solar | 05_01_27W1 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 741674 | 02151 | 11.5 | Solar | 05_01_413L2 | 12/22/2025 | 12/29/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 593486 | 01844 | 7.6 | Solar | 05_01_607W1 | 03/18/2024 | 03/21/2024 | 3 | 0 | 3 | 03/22/2024 | 03/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/18/2024 | 5/9/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | METHUEN | 644253 | 01844 | 7.6 | Solar | 05_05_115W53 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LAWRENCE | 207594 | 01841 | 6 | Solar | 05_12_29W1 | 02/05/2019 | 02/13/2019 | 6 | 6 | 0 | 02/14/2019 | 02/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/05/2019 | 2/5/2020 | Y | EXP | 349 | 09/25/2019 | 11/19/2019 | 55 | 0 | 55 |  |  | 12/3/2019 | Connected |  | N
National Grid | LEOMINSTER | 309830 | 01453 | 10 | Solar | 05_12_7J6 | 09/23/2020 |  | 62 | 54 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 672915 | 01604 | 10 | Solar | 05_14_43L4 | 02/19/2025 | 04/08/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOUTHBRIDGE | 456175 | 01550 | 5 | Solar | 05_14_5J41 | 10/11/2022 | 10/24/2022 | 10 | 9 | 1 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/11/2022 | 1/6/2024 | Y | EXP | 365 | 03/15/2023 | 03/31/2023 | 17 | 0 | 17 |  |  | 4/3/2023 | Connected |  | N
National Grid | GARDNER | 650775 | 01440 | 10 | Solar | 05_14_74L3 | 11/11/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 174697 | 02721 | 2000 | Solar | 05_01_219W2 | 12/31/2012 | 12/31/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2013 | 03/20/2013 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2014 | 12/31/2012 | 1/31/2014 | Y | STD | 67 | 12/26/2014 | 04/14/2015 | 73 | 0 | 73 | 4/9/2015 | 4/9/2015 | 4/9/2015 | Connected |  | N
National Grid | LYNN | 600630 | 01905 | 6 | Solar | 05_01_27W1 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 174118 | 02151 | 1725 | Solar | 05_01_413L2 | 03/15/2012 | 03/15/2012 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 605406 | 01844 | 3.8 | Solar | 05_01_607W1 | 04/19/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 647339 | 01844 | 10 | Solar | 05_05_115W53 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/15/2024 | 11/27/2025 | Y | EXP | 365 | 01/07/2025 | 01/06/2025 | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | Y
National Grid | METHUEN | 252203 | 01844 | 11.4 | Solar | 05_12_29W1 | 10/01/2019 | 11/06/2019 | 25 | 25 | 0 | 11/07/2019 | 11/07/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/01/2019 | 12/7/2020 | Y | EXP | 365 | 08/05/2020 | 11/16/2020 | 104 | 5 | 99 |  |  | 11/24/2020 | Connected |  | N
National Grid | LEOMINSTER | 330995 | 01453 | 10 | Solar | 05_12_7J6 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 678808 | 01604 | 5.76 | Solar | 05_14_43L4 | 03/18/2025 | 09/04/2025 | 7 | 2 | 5 | 09/19/2025 | 09/19/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 | 03/18/2025 | 11/3/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | SOUTHBRIDGE | 592556 | 01550 | 3.8 | Solar | 05_14_5J41 | 03/01/2024 | 04/18/2024 | 33 | 32 | 1 | 04/19/2024 | 04/19/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | GARDNER | 657165 | 01440 | 5.76 | Solar | 05_14_74L3 | 11/26/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/26/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 175935 | 02721 | 10 | Solar | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 2 | 2 | 08/12/2015 | 08/12/2015 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | N
National Grid | LYNN | 604510 | 01904 | 5.76 | Solar | 05_01_27W1 | 04/17/2024 | 05/01/2024 | 5 | 0 | 5 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/17/2024 | 6/7/2025 | Y | EXP | 365 | 08/16/2024 | 10/29/2024 | 75 | 0 | 75 |  |  | 11/12/2024 | Connected |  | N
National Grid | REVERE | 175101 | 02151 | 2000 | Solar | 05_01_413L2 | 10/25/2012 | 10/25/2012 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 12/31/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/13/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 642870 | 01844 | 7.83 | Solar | 05_01_607W1 | 09/25/2024 | 11/05/2024 | 13 | 8 | 5 | 11/06/2024 | 11/06/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/25/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | METHUEN | 651440 | 01844 | 4.35 | Solar | 05_05_115W53 | 11/01/2024 | 12/09/2024 | 8 | 4 | 4 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/01/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | LAWRENCE | 307291 | 01841 | 6.72 | Solar | 05_12_29W1 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 10/20/2020 | 9/25/2022 | Y | EXP | 365 | 09/09/2021 | 09/23/2021 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 333059 | 01453 | 7.6 | Solar | 05_12_7J6 | 03/08/2021 | 03/10/2021 | 1 | 0 | 1 | 03/11/2021 | 03/11/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/5/2022 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 709253 | 01604 | 10 | Solar | 05_14_43L4 | 08/04/2025 | 09/02/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 08/04/2025 | 11/3/2026 | Y | EXP | 365 | 12/18/2025 |  | 79 | 0 | 79 |  |  |  | Construction |  | N
National Grid | STURBRIDGE | 606739 | 01566 | 10 | Solar | 05_14_5J41 | 04/25/2024 | 05/03/2024 | 1 | 0 | 1 | 05/06/2024 | 05/06/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 04/25/2024 | 5/30/2025 | Y | EXP | 365 | 07/31/2024 | 09/28/2024 | 60 | 0 | 60 |  |  | 10/12/2024 | Connected |  | N
National Grid | GARDNER | 657183 | 01440 | 5.76 | Solar | 05_14_74L3 | 11/26/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176076 | 02721 | 10 | Solar | 05_01_219W2 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/20/2015 | 08/20/2015 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/25/2016 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 605299 | 01905 | 3.8 | Solar | 05_01_27W1 | 04/19/2024 | 04/26/2024 | 4 | 0 | 4 | 04/29/2024 | 04/29/2024 | 57 | 47 | 10 | 08/05/2024 | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 31 | 0 | 31 |  |  | 0 | 0 | 0 | 9/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 175596 | 02151 | 480 | Solar | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 | 08/12/2014 | 08/12/2014 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/15/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 651317 | 01841 | 3.8 | Solar | 05_01_607W1 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | METHUEN | 654700 | 01844 | 3.8 | Solar | 05_05_115W53 | 11/19/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/19/2024 | 3/18/2026 | Y | EXP | 365 | 04/02/2025 | 04/18/2025 | 17 | 0 | 17 |  |  | 5/3/2025 | Connected |  | N
National Grid | LAWRENCE | 311321 | 01844 | 6.48 | Solar | 05_12_29W1 | 10/12/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 60 | 41 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2021 | Connected |  | N
National Grid | LEOMINSTER | 471831 | 01453 | 15.2 | Solar | 05_12_7J6 | 10/27/2022 | 10/28/2022 | 1 | 0 | 1 | 10/31/2022 | 10/31/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2023 | Connected |  | N
National Grid | WORCESTER | 715619 | 01604 | 13.12 | Solar | 05_14_43L4 | 08/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STURBRIDGE | 607882 | 01566 | 5.04 | Solar | 05_14_5J41 | 05/01/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 05/01/2024 | 4/22/2026 | Y | EXP | 365 | 05/16/2025 | 09/15/2025 | 123 | 0 | 123 |  |  | 10/17/2025 | Connected |  | N
National Grid | GARDNER | 657640 | 01440 | 9.1 | Solar | 05_14_74L3 | 12/11/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | FALL RIVER | 176257 | 02721 | 252 | Solar | 05_01_219W2 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 | 09/07/2015 | 09/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2015 | 09/03/2015 | 9/12/2016 | Y | EXP | 354 | 06/22/2016 | 08/30/2016 | 48 | 0 | 48 | 9/24/2015 | 9/24/2015 | 10/7/2016 | Connected |  | N
National Grid | LYNN | 610041 | 01904 | 7.6 | Solar | 05_01_27W1 | 05/09/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 59 | 45 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 175595 | 02151 | 996 | Solar | 05_01_413L2 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 09/09/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/01/2014 | 4/1/2016 | Y | STD | 34 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | LAWRENCE | 651319 | 01841 | 5.76 | Solar | 05_01_607W1 | 11/12/2024 | 01/13/2025 | 22 | 17 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/12/2024 | 3/14/2026 | Y | EXP | 365 | 06/11/2025 | 10/04/2025 | 116 | 0 | 116 |  |  | 11/24/2025 | Connected |  | N
National Grid | METHUEN | 660461 | 01844 | 4.64 | Solar | 05_05_115W53 | 12/13/2024 | 01/30/2025 | 28 | 25 | 3 | 01/31/2025 | 01/31/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 313176 | 01841 | 7.6 | Solar | 05_12_29W1 | 11/02/2020 | 11/03/2020 | 0 | 0 | 0 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 11/02/2020 | 11/2/2021 | Y | EXP | 365 | 03/25/2021 | 08/16/2021 | 144 | 0 | 144 |  |  | 9/7/2021 | Connected |  | N
National Grid | LEOMINSTER | 567022 | 01453 | 6.96 | Solar | 05_12_7J6 | 11/15/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2024 | Connected |  | N
National Grid | WORCESTER | 732219 | 01604 | 7.6 | Solar | 05_14_43L4 | 11/07/2025 | 11/20/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STURBRIDGE | 617581 | 01566 | 3.8 | Solar | 05_14_5J41 | 06/12/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/12/2024 | 7/19/2025 | Y | EXP | 365 | 11/13/2024 | 11/26/2024 | 14 | 0 | 14 |  |  | 12/6/2024 | Connected |  | N
National Grid | GARDNER | 663368 | 01440 | 8.96 | Solar | 05_14_74L3 | 01/02/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | FALL RIVER | 176439 | 02721 | 10 | Solar | 05_01_219W2 | 08/06/2015 | 08/06/2015 | 4 | 0 | 4 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 3/17/2016 | 3/17/2016 | 7/19/2016 | Connected |  | N
National Grid | LYNN | 610657 | 01905 | 3.8 | Solar | 05_01_27W1 | 05/14/2024 | 05/21/2024 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 175664 | 02151 | 996 | Solar | 05_01_413L2 | 08/11/2014 | 08/11/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/09/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 | 08/11/2014 | 3/15/2016 | Y | STD | 323 | 05/24/2016 | 06/28/2016 | 23 | 0 | 23 | 6/27/2016 | 6/27/2016 | 6/30/2016 | Connected |  | N
National Grid | METHUEN | 659940 | 01844 | 7.6 | Solar | 05_01_607W1 | 12/11/2024 | 12/18/2024 | 2 | 0 | 2 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/11/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | METHUEN | 661398 | 01844 | 3.8 | Solar | 05_05_115W53 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 362142 | 01841 | 7.6 | Solar | 05_12_29W1 | 07/01/2021 | 01/06/2022 | 6 | 0 | 6 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 | 07/01/2021 | 8/21/2024 | Y | EXP | 365 | 03/22/2022 | 08/18/2023 | 515 | 0 | 515 |  |  | 9/8/2023 | Connected |  | N
National Grid | LEOMINSTER | 562600 | 01453 | 6 | Solar | 05_12_7J6 | 10/16/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 87 | 69 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 735576 | 01604 |  | Solar | 05_14_43L4 | 11/21/2025 | 11/24/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STURBRIDGE | 618583 | 01566 | 10 | Solar | 05_14_5J41 | 06/17/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 665241 | 01440 | 15.2 | Solar | 05_14_74L3 | 01/16/2025 | 01/31/2025 | 10 | 4 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/16/2025 | 3/18/2026 | Y | EXP | 365 | 08/09/2025 | 08/18/2025 | 10 | 0 | 10 |  |  | 8/26/2025 | Connected |  | N
National Grid | FALL RIVER | 176738 | 02721 | 900 | Solar | 05_01_219W2 | 10/29/2015 | 10/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 12/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/4/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 612619 | 01905 | 5 | Solar | 05_01_27W1 | 05/29/2024 | 06/13/2024 | 1 | 0 | 1 | 06/14/2024 | 06/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2024 | Connected |  | N
National Grid | REVERE | 176660 | 02151 | 1440 | Solar | 05_01_413L2 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 670136 | 01844 | 5.76 | Solar | 05_01_607W1 | 02/05/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | METHUEN | 663847 | 01844 | 3.8 | Solar | 05_05_115W53 | 01/06/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 380798 | 01844 | 5 | Solar | 05_12_29W1 | 09/10/2021 | 09/24/2021 | 1 | 0 | 1 | 09/27/2021 | 09/27/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/10/2021 | 2/27/2023 | Y | EXP | 365 | 01/13/2022 | 02/24/2022 | 43 | 0 | 43 |  |  | 3/3/2022 | Connected |  | N
National Grid | LEOMINSTER | 599877 | 01453 | 6 | Solar | 05_12_7J6 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/15/2024 | 4/25/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/19/2025 | Connected |  | Y
National Grid | WORCESTER | 742927 | 01604 | 0 | Other | 05_14_43L4 | 02/24/2026 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SOUTHBRIDGE | 625945 | 01550 | 15.2 | Solar | 05_14_5J41 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/18/2024 | 12/9/2025 | Y | EXP | 365 | 01/25/2025 | 03/04/2025 | 39 | 0 | 39 |  |  | 6/21/2025 | Connected |  | N
National Grid | GARDNER | 669715 | 01440 | 7.6 | Solar | 05_14_74L3 | 02/03/2025 | 03/12/2025 | 20 | 16 | 4 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | FALL RIVER | 176747 | 02721 | 3 | Solar | 05_01_219W2 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 4/2/2017 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 614361 | 01905 | 3.8 | Solar | 05_01_27W1 | 05/30/2024 | 06/10/2024 | 3 | 0 | 3 | 06/11/2024 | 06/11/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 177438 | 02151 | 260 | Solar | 05_01_413L2 | 07/01/2016 | 07/01/2016 | 2 | 2 | 0 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 07/01/2016 | 10/6/2017 | Y | EXP | 382 | 07/17/2017 | 09/27/2017 | 51 | 0 | 51 | 9/29/2017 | 9/29/2017 | 9/29/2017 | Connected |  | N
National Grid | METHUEN | 686443 | 01844 | 15.2 | Solar | 05_01_607W1 | 04/21/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 669664 | 01844 | 5.76 | Solar | 05_05_115W53 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 02/03/2025 | 4/7/2026 | Y | EXP | 365 | 04/29/2025 | 06/24/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 379716 | 01841 | 9.8 | Solar | 05_12_29W1 | 09/23/2021 | 12/16/2021 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 602832 | 01453 | 6 | Solar | 05_12_7J6 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174281 | 01604 | 55 | Solar | 05_14_43L4 | 12/31/2011 | 12/31/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 03/07/2012 | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/02/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 | 12/31/2011 | 1/24/2012 | Y | EXP | 85 | 05/14/2012 | 05/18/2012 | 4 | 0 | 4 | 6/15/2012 | 6/15/2012 | 7/3/2012 | Connected |  | N
National Grid | SOUTHBRIDGE | 637475 | 01550 | 7.6 | Solar | 05_14_5J41 | 09/09/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 09/09/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | GARDNER | 670532 | 01440 | 3.8 | Solar | 05_14_74L3 | 02/06/2025 | 03/25/2025 | 25 | 20 | 5 | 03/26/2025 | 03/26/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/06/2025 | 5/20/2026 | Y | EXP | 365 | 06/24/2025 | 07/28/2025 | 35 | 0 | 35 |  |  | 8/1/2025 | Connected |  | N
National Grid | FALL RIVER | 177417 | 02721 | 7.6 | Solar | 05_01_219W2 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 | 12/01/2016 | 12/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2016 | 11/29/2016 | 12/6/2017 | Y | EXP | 365 | 07/25/2017 | 09/26/2017 | 44 | 0 | 44 | 10/23/2017 | 10/23/2017 | 10/20/2017 | Connected |  | N
National Grid | LYNN | 615988 | 01904 | 5.76 | Solar | 05_01_27W1 | 06/06/2024 | 06/14/2024 | 0 | 0 | 0 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 | 06/06/2024 | 7/5/2025 | Y | EXP | 365 | 10/03/2024 | 11/07/2024 | 36 | 0 | 36 |  |  | 12/19/2024 | Connected |  | N
National Grid | REVERE | 178286 | 02151 | 5 | Solar | 05_01_413L2 | 03/28/2018 | 03/28/2018 | 6 | 0 | 6 | 04/06/2018 | 04/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/28/2018 | 4/3/2019 | Y | EXP | 336 |  |  | 0 | 0 | 0 |  |  | 3/26/2019 | Connected |  | N
National Grid | METHUEN | 657316 | 01844 | 160 | Solar | 05_01_607W2 | 12/03/2024 | 12/20/2024 | 14 | 9 | 5 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | METHUEN | 673224 | 01844 | 7.6 | Solar | 05_05_115W53 | 02/25/2025 | 03/14/2025 | 13 | 9 | 4 | 03/17/2025 | 03/17/2025 | 126 | 25 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 407981 | 01841 | 7.6 | Solar | 05_12_29W1 | 02/15/2022 | 02/16/2022 | 1 | 0 | 1 | 02/17/2022 | 02/17/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/15/2022 | 11/2/2023 | Y | EXP | 365 | 06/03/2022 | 06/10/2022 | 8 | 0 | 8 |  |  | 11/9/2022 | Connected |  | N
National Grid | LEOMINSTER | 189881 | 01453 | 3.8 | Solar | 05_12_7J7 | 07/03/2018 | 07/03/2018 | 5 | 0 | 5 | 10/31/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177608 | 01604 | 42 | Solar | 05_14_43L4 | 09/20/2017 | 09/20/2017 | 12 | 11 | 1 | 10/09/2017 | 10/09/2017 | 1 | 0 | 1 | 02/09/2018 | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/26/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  | 7/16/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 646096 | 01550 | 11.02 | Solar | 05_14_5J41 | 10/22/2024 | 11/26/2024 | 11 | 7 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 10/22/2024 | 2/5/2026 | Y | EXP | 365 | 04/15/2025 | 07/11/2025 | 88 | 0 | 88 |  |  | 7/18/2025 | Connected |  | N
National Grid | GARDNER | 676986 | 01440 | 3.8 | Solar | 05_14_74L3 | 03/10/2025 | 03/22/2025 | 1 | 0 | 1 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 03/10/2025 | 5/13/2026 | Y | EXP | 365 | 10/01/2025 | 12/02/2025 | 63 | 0 | 63 |  |  | 12/18/2025 | Connected |  | N
National Grid | FALL RIVER | 178627 | 02721 | 7.6 | Solar | 05_01_219W2 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/21/2019 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 622781 | 01904 | 9.8 | Solar | 05_01_27W1 | 07/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | REVERE | 178281 | 02151 | 7.6 | Solar | 05_01_413L2 | 02/23/2018 | 02/23/2018 | 4 | 4 | 0 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2018 |  | 3/3/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | LAWRENCE | 708125 | 01841 | 15.58 | Solar | 05_01_607W2 | 07/29/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 673848 | 01844 | 4.93 | Solar | 05_05_115W53 | 02/24/2025 | 03/27/2025 | 4 | 2 | 2 | 03/28/2025 | 03/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/24/2025 | 8/29/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 10/10/2025 | Connected |  | N
National Grid | METHUEN | 420646 | 01844 | 10 | Solar | 05_12_29W1 | 03/31/2022 | 04/25/2022 | 16 | 13 | 3 | 04/26/2022 | 04/26/2022 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | LEOMINSTER | 225696 | 01453 | 7.6 | Solar | 05_12_7J7 | 06/12/2019 | 06/18/2019 | 3 | 0 | 3 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/12/2019 | 4/23/2021 | Y | EXP | 365 | 10/03/2020 | 11/18/2020 | 46 | 0 | 46 |  |  | 1/8/2021 | Connected |  | N
National Grid | WORCESTER | 186476 | 01604 | 15.04 | Solar | 05_14_43L4 | 06/04/2018 | 06/04/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2018 | Connected |  | N
National Grid | STURBRIDGE | 662588 | 01566 | 10 | Solar | 05_14_5J41 | 01/03/2025 | 01/21/2025 | 5 | 2 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 681130 | 01440 | 3.8 | Solar | 05_14_74L3 | 03/27/2025 | 04/16/2025 | 4 | 0 | 4 | 08/11/2025 | 08/11/2025 | 85 | 64 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2026 | Connected |  | N
National Grid | FALL RIVER | 200671 | 02721 | 7.6 | Solar | 05_01_219W2 | 11/07/2018 | 12/17/2018 | 21 | 13 | 8 | 12/18/2018 | 12/18/2018 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 625256 | 01905 | 3.8 | Solar | 05_01_27W1 | 07/16/2024 | 07/29/2024 | 3 | 0 | 3 | 07/30/2024 | 07/30/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 12/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | REVERE | 191126 | 02151 | 3.8 | Solar | 05_01_413L2 | 07/19/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174639 | 01844 | 60 | Solar | 05_01_607W2 | 05/23/2013 | 05/23/2013 | 7 | 0 | 7 | 06/05/2013 | 06/05/2013 | 1121 | 0 | 1121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2013 |  | 10/14/2020 | N | EXP | 1745 |  |  | 0 | 0 | 0 | 3/3/2015 | 3/3/2015 | 10/14/2020 | Connected |  | N
National Grid | METHUEN | 684035 | 01844 | 7.6 | Solar | 05_05_115W53 | 04/14/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 542019 | 01841 | 3.8 | Solar | 05_12_29W1 | 07/26/2023 | 07/27/2023 | 1 | 0 | 1 | 07/28/2023 | 07/28/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/26/2023 | 8/24/2024 | Y | EXP | 365 | 10/20/2023 | 11/03/2023 | 15 | 0 | 15 |  |  | 11/15/2023 | Connected |  | N
National Grid | LEOMINSTER | 659647 | 01453 | 5.76 | Solar | 05_12_7J7 | 12/10/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 193103 | 01604 | 650 | Solar | 05_14_43L4 | 08/22/2018 | 10/25/2018 | 45 | 3 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 | 01/31/2019 | 62 | 26 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 688562 | 01566 | 5.76 | Solar | 05_14_5J41 | 04/30/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | GARDNER | 682830 | 01440 | 8.027 | Solar | 05_14_74L3 | 04/04/2025 | 05/12/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | FALL RIVER | 211055 | 02721 | 50 | Solar | 05_01_219W2 | 02/22/2019 | 03/11/2019 | 10 | 7 | 3 | 03/12/2019 | 03/12/2019 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 625053 | 01904 | 3.8 | Solar | 05_01_27W1 | 07/16/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/16/2024 | 8/6/2025 | Y | EXP | 365 | 08/29/2024 | 08/28/2024 | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | REVERE | 199144 | 02151 | 11.4 | Solar | 05_01_413L2 | 10/22/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 178322 | 01844 | 2510 | Solar | 05_01_607W2 | 03/29/2018 | 04/03/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/25/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 687844 | 01844 | 10.24 | Solar | 05_05_115W53 | 04/28/2025 | 05/28/2025 | 2 | 0 | 2 | 05/29/2025 | 05/29/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 | 04/28/2025 | 7/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | LAWRENCE | 552539 | 01841 | 3.8 | Solar | 05_12_29W1 | 09/20/2023 | 09/22/2023 | 3 | 2 | 1 | 09/25/2023 | 09/25/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/4/2024 | Connected |  | N
National Grid | LEOMINSTER | 725831 | 01453 | 5.76 | Solar | 05_12_7J901 | 10/10/2025 | 12/10/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 219512 | 01604 | 10 | Solar | 05_14_43L4 | 11/14/2019 | 11/20/2019 | 3 | 2 | 1 | 11/21/2019 | 11/21/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 |  | 7/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | STURBRIDGE | 178227 | 01566 | 7.6 | Solar | 05_14_5J42 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 |  | 1/10/2019 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 684455 | 01452 | 10 | Solar | 05_14_74L3 | 04/10/2025 | 05/02/2025 | 15 | 12 | 3 | 05/05/2025 | 05/05/2025 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/10/2025 | 8/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | FALL RIVER | 283064 | 02721 | 7.6 | Solar | 05_01_219W2 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 8/11/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 11 | 0 | 11 |  |  | 2/25/2022 | Connected |  | N
National Grid | LYNN | 625527 | 01904 | 5 | Solar | 05_01_27W1 | 07/18/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 204532 | 01905 | 7.6 | Solar | 05_01_413L2 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 01/10/2019 | 8/19/2020 | Y | EXP | 365 | 06/24/2020 | 06/30/2020 | 6 | 0 | 6 |  |  | 7/30/2020 | Connected |  | N
National Grid | LAWRENCE | 192422 | 01841 | 100 | Solar | 05_01_607W2 | 08/01/2018 | 08/20/2018 | 11 | 0 | 11 | 08/21/2018 | 08/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 1/7/2020 | N | EXP | 475 | 11/13/2019 | 11/12/2019 | 0 | 0 | 0 |  |  | 1/7/2020 | Connected |  | N
National Grid | METHUEN | 696536 | 01844 | 7.6 | Solar | 05_05_115W54 | 06/05/2025 | 06/17/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | METHUEN | 554746 | 01844 | 10 | Solar | 05_12_29W1 | 09/25/2023 | 09/29/2023 | 4 | 0 | 4 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/25/2023 | 12/10/2024 | Y | EXP | 365 | 02/09/2024 | 05/01/2024 | 83 | 0 | 83 |  |  | 8/4/2024 | Connected |  | N
National Grid | LEOMINSTER | 176380 | 01453 | 1520 | Solar | 05_12_7J901 | 11/23/2015 | 11/23/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2015 | 12/18/2015 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 11/29/2016 | N | STD | 251 |  |  | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/12/2016 | Connected |  | N
National Grid | WORCESTER | 326326 | 01604 | 7.6 | Solar | 05_14_43L4 | 01/08/2021 | 01/11/2021 | 0 | 0 | 0 | 01/12/2021 | 01/12/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2021 | 01/08/2021 |  | Y | EXP | 365 | 05/25/2021 | 06/18/2021 | 24 | 0 | 24 |  |  | 8/27/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 178338 | 01550 | 5 | Solar | 05_14_5J42 | 11/17/2017 | 11/17/2017 | 48 | 47 | 1 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 11/25/2018 | N | EXP | 298 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 735225 | 01440 | 15.76 | Solar | 05_14_74L3 | 11/20/2025 | 11/26/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | FALL RIVER | 285851 | 02724 | 6 | Solar | 05_01_219W2 | 04/22/2020 | 04/27/2020 | 3 | 1 | 2 | 04/28/2020 | 04/28/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 | 04/22/2020 | 4/28/2022 | Y | EXP | 365 | 05/07/2021 | 06/23/2021 | 47 | 0 | 47 |  |  | 9/24/2021 | Connected |  | N
National Grid | LYNN | 632259 | 01905 | 10 | Solar | 05_01_27W1 | 08/20/2024 | 08/23/2024 | 3 | 0 | 3 | 08/26/2024 | 08/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/20/2024 | 9/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 225333 | 01905 | 10 | Solar | 05_01_413L2 | 05/07/2019 | 07/19/2019 | 54 | 53 | 1 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 482643 | 01844 | 17.4 | Solar | 05_01_607W2 | 02/06/2023 | 03/24/2023 | 33 | 32 | 1 | 03/27/2023 | 03/27/2023 | 72 | 52 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 418915 | 01844 | 15.2 | Solar | 05_05_115W54 | 03/21/2022 | 03/25/2022 | 4 | 3 | 1 | 03/28/2022 | 03/28/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 566137 | 01841 | 6 | Solar | 05_12_29W1 | 11/06/2023 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 280354 | 01453 | 7.6 | Solar | 05_12_7J901 | 03/04/2020 | 06/02/2020 | 63 | 62 | 1 | 06/03/2020 | 06/03/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 | 03/04/2020 | 6/2/2021 | Y | EXP | 365 | 12/11/2020 | 03/16/2021 | 95 | 0 | 95 |  |  | 3/19/2021 | Connected |  | N
National Grid | WORCESTER | 347618 | 01604 | 6.09 | Solar | 05_14_43L4 | 04/15/2021 | 04/22/2021 | 3 | 1 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 320041 | 01566 | 9.8 | Solar | 05_14_5J42 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/30/2020 | 9/3/2022 | Y | EXP | 365 | 08/19/2021 | 10/12/2021 | 40 | 3 | 37 |  |  | 6/2/2022 | Connected |  | N
National Grid | GARDNER | 556519 | 01440 | 340 | Natural Gas | 05_14_74L4 | 02/20/2024 | 07/03/2025 | 341 | 331 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2025 | 08/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | FALL RIVER | 341966 | 02721 | 3.8 | Solar | 05_01_219W2 | 02/22/2021 | 02/23/2021 | 0 | 0 | 0 | 02/24/2021 | 02/24/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  | 2/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 634251 | 01904 | 3.8 | Solar | 05_01_27W1 | 08/21/2024 | 09/18/2024 | 15 | 13 | 2 | 09/19/2024 | 09/19/2024 | 83 | 66 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LYNN | 260850 | 01905 | 10 | Solar | 05_01_413L2 | 10/28/2019 | 10/31/2019 | 3 | 3 | 0 | 11/01/2019 | 11/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/28/2019 | 10/28/2020 | Y | EXP | 365 | 02/19/2020 | 03/03/2020 | 13 | 0 | 13 |  |  | 3/6/2020 | Connected |  | N
National Grid | METHUEN | 620468 | 01844 | 3.8 | Solar | 05_01_607W2 | 06/25/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | METHUEN | 439740 | 01844 | 15.2 | Solar | 05_05_115W54 | 06/23/2022 |  | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 563069 | 01841 | 2.9 | Solar | 05_12_29W1 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 77 | 61 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | LEOMINSTER | 603654 | 01453 | 3.8 | Solar | 05_12_7J901 | 04/15/2024 | 04/23/2024 | 7 | 3 | 4 | 04/24/2024 | 04/24/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 04/15/2024 | 5/16/2025 | Y | EXP | 365 | 08/29/2024 | 12/05/2024 | 99 | 0 | 99 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 349417 | 01604 | 9.8 | Solar | 05_14_43L4 | 05/13/2021 | 05/21/2021 | 5 | 0 | 5 | 05/24/2021 | 05/24/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | STURBRIDGE | 558417 | 01566 | 10 | Solar | 05_14_5J42 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 11/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | GARDNER | 672131 | 01440 | 180 | Solar | 05_14_74L4 | 04/04/2025 |  | 228 | 32 | 196 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | Y
National Grid | FALL RIVER | 352779 | 02721 | 5.76 | Solar | 05_01_219W2 | 05/04/2021 | 05/05/2021 | 0 | 0 | 0 | 05/06/2021 | 05/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2021 | Connected |  | N
National Grid | LYNN | 636951 | 01905 | 3.8 | Solar | 05_01_27W1 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 313745 | 01905 | 10 | Solar | 05_01_413L2 | 10/07/2020 | 10/27/2020 | 13 | 12 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | LAWRENCE | 312828 | 01841 | 762 | Solar | 05_01_607W3 | 04/29/2021 | 10/03/2021 | 108 | 98 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/04/2021 | 12/04/2021 | 42 | 4 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 | 04/29/2021 | 2/12/2026 | Y | STD | 2 | 01/01/2026 | 12/31/2025 | 0 | 0 | 0 |  |  | 12/31/2025 | Witness Test |  | N
National Grid | METHUEN | 649641 | 01844 | 6.72 | Solar | 05_05_115W54 | 10/25/2024 | 11/15/2024 | 12 | 7 | 5 | 11/18/2024 | 11/18/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | LAWRENCE | 572266 | 01840 | 7.6 | Solar | 05_12_29W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/07/2023 | 1/31/2025 | Y | EXP | 365 | 04/17/2024 | 06/17/2024 | 62 | 0 | 62 |  |  | 7/4/2024 | Connected |  | N
National Grid | LEOMINSTER | 657216 | 01453 | 2.9 | Solar | 05_12_7J901 | 11/27/2024 | 02/25/2025 | 6 | 3 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | WORCESTER | 373213 | 01604 | 10 | Solar | 05_14_43L4 | 09/10/2021 | 01/06/2022 | 3 | 0 | 3 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 | 09/10/2021 | 7/27/2023 | Y | EXP | 365 | 06/09/2022 | 06/08/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 533962 | 01550 | 10 | Solar | 05_14_5J42 | 07/06/2023 | 07/13/2023 | 6 | 5 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2023 | 07/06/2023 | 9/2/2024 | Y | EXP | 365 | 02/17/2024 | 02/16/2024 | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | GARDNER | 677996 | 01440 | 15.2 | Solar | 05_14_74L4 | 03/17/2025 | 03/24/2025 | 5 | 1 | 4 | 03/25/2025 | 03/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 451693 | 02721 | 6 | Solar | 05_01_219W2 | 08/25/2022 | 08/30/2022 | 3 | 0 | 3 | 08/31/2022 | 08/31/2022 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 636882 | 01905 | 10 | Solar | 05_01_27W1 | 08/30/2024 | 09/11/2024 | 1 | 0 | 1 | 09/12/2024 | 09/12/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 335828 | 01905 | 0 | Other | 05_01_413L2 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175152 | 01844 | 750 | Solar | 05_01_607W3 | 11/01/2013 | 11/20/2013 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 01/02/2014 |  | 1053 | 203 | 850 | 11/20/2013 | 01/02/2014 | 28 | 28 | 0 |  |  | 1053 | 203 | 850 |  |  | 0 | 0 | 0 | 9/11/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 671800 | 01844 | 3.8 | Solar | 05_05_115W54 | 02/12/2025 | 03/11/2025 | 7 | 2 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | LAWRENCE | 572647 | 01841 | 5.8 | Solar | 05_12_29W1 | 11/27/2023 | 11/30/2023 | 3 | 2 | 1 | 12/01/2023 | 12/01/2023 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | LEOMINSTER | 657861 | 01453 | 5.76 | Solar | 05_12_7J901 | 12/05/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | WORCESTER | 378603 | 01604 | 9.8 | Solar | 05_14_43L4 | 09/10/2021 | 01/03/2022 | 3 | 2 | 1 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 534971 | 01550 | 7.6 | Solar | 05_14_5J42 | 07/06/2023 | 07/25/2023 | 14 | 13 | 1 | 07/26/2023 | 07/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 | 07/06/2023 | 9/20/2024 | Y | EXP | 365 | 01/24/2024 | 02/14/2024 | 22 | 0 | 22 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 697435 | 01440 | 15.2 | Solar | 05_14_74L4 | 06/10/2025 | 06/24/2025 | 8 | 0 | 8 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 367884 | 02724 | 10 | Solar | 05_01_219W2 | 07/13/2021 | 12/20/2021 | 3 | 0 | 3 | 07/19/2021 | 07/19/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 | 07/13/2021 | 8/8/2023 | Y | EXP | 365 | 05/03/2022 | 05/17/2022 | 15 | 0 | 15 |  |  | 8/17/2022 | Connected |  | Y
National Grid | LYNN | 654101 | 01905 | 11.89 | Solar | 05_01_27W1 | 11/25/2024 | 01/14/2025 | 19 | 17 | 2 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | Y
National Grid | LYNN | 418074 | 01905 | 15.2 | Solar | 05_01_413L2 | 03/16/2022 | 03/18/2022 | 3 | 2 | 1 | 03/21/2022 | 03/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | METHUEN | 178561 | 01844 | 1666 | Solar | 05_01_607W3 | 04/05/2018 | 04/05/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 10/26/2018 | 137 | 70 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 741858 | 01844 | 7.6 | Solar | 05_05_115W55 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LAWRENCE | 583921 | 01841 | 5.22 | Solar | 05_12_29W1 | 02/12/2024 | 02/20/2024 | 5 | 2 | 3 | 02/21/2024 | 02/21/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | LEOMINSTER | 691255 | 01453 | 3.8 | Solar | 05_12_7J901 | 05/13/2025 | 05/23/2025 | 1 | 0 | 1 | 06/16/2025 | 06/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 | 05/13/2025 | 7/15/2026 | Y | EXP | 365 | 10/01/2025 | 11/18/2025 | 49 | 0 | 49 |  |  | 12/15/2025 | Connected |  | N
National Grid | WORCESTER | 381715 | 01604 | 11.04 | Solar | 05_14_43L4 | 09/16/2021 | 09/20/2021 | 2 | 0 | 2 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 596892 | 01566 | 5 | Solar | 05_14_5J42 | 03/19/2024 | 03/25/2024 | 4 | 0 | 4 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/19/2024 | 8/29/2025 | Y | EXP | 45 | 10/03/2024 | 10/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 712563 | 01475 | 15.2 | Solar | 05_14_74L4 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 104 | 77 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | FALL RIVER | 420950 | 02724 | 8.99 | Solar | 05_01_219W2 | 04/06/2022 | 04/21/2022 | 11 | 10 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 656846 | 01904 | 6 | Solar | 05_01_27W1 | 11/26/2024 | 03/20/2025 | 21 | 16 | 5 | 02/24/2025 | 02/24/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/26/2024 | 4/14/2026 | Y | EXP | 365 | 06/24/2025 | 07/16/2025 | 23 | 0 | 23 |  |  | 7/22/2025 | Connected |  | N
National Grid | LYNN | 471227 | 01905 | 7.6 | Solar | 05_01_413L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 155 | 21 | 134 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 200441 | 01844 | 4998 | Solar | 05_01_607W3 | 11/15/2018 | 11/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 | 01/25/2019 | 57 | 20 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175360 | 01844 | 20 | Solar | 05_05_115W55 | 11/12/2014 | 11/12/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 587528 | 01841 | 7.6 | Solar | 05_12_29W1 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 177808 | 01453 | 7.6 | Solar | 05_12_7J903 | 10/12/2017 | 10/12/2017 | 8 | 0 | 8 | 10/25/2017 | 10/25/2017 | 86 | 0 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2017 |  | 10/18/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 390053 | 01604 | 7.6 | Solar | 05_14_43L4 | 10/26/2021 | 11/02/2021 | 5 | 0 | 5 | 11/03/2021 | 11/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/26/2021 | 2/7/2023 | Y | EXP | 365 | 01/19/2022 | 02/07/2022 | 20 | 0 | 20 |  |  | 2/15/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 639677 | 01550 | 7.6 | Solar | 05_14_5J42 | 09/12/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/12/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WINCHENDON | 727868 | 01475 | 7.6 | Solar | 05_14_74L4 | 10/20/2025 | 10/23/2025 | 3 | 0 | 3 | 10/24/2025 | 10/24/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 437201 | 02724 | 5.76 | Solar | 05_01_219W2 | 07/18/2022 | 07/19/2022 | 1 | 0 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/18/2022 | 2/1/2024 | Y | EXP | 365 | 01/07/2023 | 02/01/2023 | 26 | 0 | 26 |  |  | 5/8/2023 | Connected |  | N
National Grid | LYNN | 658492 | 01904 | 7.6 | Solar | 05_01_27W1 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | SAUGUS | 471147 | 01906 | 10 | Solar | 05_01_413L2 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 8/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2023 | Connected |  | N
National Grid | METHUEN | 282444 | 01844 | 831 | Natural Gas | 05_01_607W3 | 05/20/2020 | 07/06/2020 | 31 | 25 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 177153 | 01844 | 60 | Solar | 05_05_115W55 | 08/12/2016 | 08/12/2016 | 1 | 1 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/17/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/12/2016 | 12/14/2016 | Connected |  | N
National Grid | METHUEN | 588428 | 01844 | 3.8 | Solar | 05_12_29W1 | 02/21/2024 | 04/17/2024 | 28 | 25 | 3 | 04/18/2024 | 04/18/2024 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | LEOMINSTER | 178676 | 01453 | 7.6 | Solar | 05_12_7J903 | 04/10/2018 | 04/10/2018 | 0 | 0 | 0 | 04/30/2018 | 04/30/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 1/8/2020 | N | EXP | 614 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 395186 | 01604 | 6 | Solar | 05_14_43L4 | 11/18/2021 | 01/06/2022 | 2 | 0 | 2 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 6/16/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2022 | Connected |  | Y
National Grid | SOUTHBRIDGE | 644236 | 01550 | 5.76 | Solar | 05_14_5J42 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | GARDNER | 174279 | 01440 | 491 | Solar | 05_14_74L4 | 12/13/2011 | 12/13/2011 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2012 | 12/13/2011 | 3/1/2012 | Y | EXP | 62 | 06/06/2012 | 07/16/2012 | 26 | 0 | 26 | 6/26/2012 | 6/26/2012 | 7/2/2012 | Connected |  | N
National Grid | FALL RIVER | 440596 | 02724 | 10 | Solar | 05_01_219W2 | 07/14/2022 | 07/15/2022 | 2 | 1 | 1 | 07/18/2022 | 07/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 661842 | 01904 | 3.8 | Solar | 05_01_27W1 | 01/06/2025 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/06/2025 | 4/28/2026 | Y | EXP | 365 | 06/14/2025 | 02/03/2026 | 235 | 6 | 229 |  |  | 3/2/2026 | Connected |  | N
National Grid | SAUGUS | 478408 | 01906 | 8.7 | Solar | 05_01_413L2 | 01/20/2023 | 01/23/2023 | 1 | 0 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | METHUEN | 439984 | 01844 | 9.86 | Solar | 05_01_607W3 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 549206 | 01844 | 25 | Solar | 05_05_115W55 | 09/12/2023 | 09/16/2023 | 4 | 2 | 2 | 09/18/2023 | 09/18/2023 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | LAWRENCE | 590460 | 01840 | 5 | Solar | 05_12_29W1 | 03/01/2024 | 05/28/2024 | 16 | 16 | 0 | 05/29/2024 | 05/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | LEOMINSTER | 194313 | 01453 | 7.6 | Solar | 05_12_7J903 | 09/19/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 09/19/2018 | 10/12/2020 | Y | EXP | 45 | 05/02/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 2/7/2020 | Connected |  | N
National Grid | WORCESTER | 401101 | 01604 | 0 | Other | 05_14_43L4 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/02/2022 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 655097 | 01550 | 10 | Solar | 05_14_5J42 | 11/21/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/21/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | GARDNER | 174828 | 01440 | 100 | Solar | 05_14_74L4 | 08/15/2011 | 08/15/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2011 | 08/15/2011 | 3/6/2012 | Y | EXP | 81 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 3/6/2012 | Connected |  | N
National Grid | FALL RIVER | 513551 | 02724 | 0 | Solar | 05_01_219W2 | 03/21/2023 | 03/22/2023 | 1 | 0 | 1 | 03/23/2023 | 03/23/2023 | 54 | 33 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 662937 | 01904 | 7.6 | Solar | 05_01_27W1 | 12/30/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2025 | Connected |  | N
National Grid | SAUGUS | 480272 | 01906 | 7.6 | Solar | 05_01_413L2 | 12/07/2022 | 01/12/2023 | 25 | 22 | 3 | 01/13/2023 | 01/13/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 | 12/07/2022 | 8/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | METHUEN | 641030 | 01844 | 9.86 | Solar | 05_01_607W3 | 09/17/2024 | 11/05/2024 | 11 | 9 | 2 | 11/06/2024 | 11/06/2024 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2024 | Connected |  | N
National Grid | METHUEN | 550284 | 01844 | 10 | Solar | 05_05_115W55 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 | 08/25/2023 | 11/29/2024 | Y | EXP | 365 | 01/10/2024 | 02/28/2024 | 50 | 0 | 50 |  |  | 5/30/2024 | Connected |  | N
National Grid | LAWRENCE | 596319 | 01840 | 3.8 | Solar | 05_12_29W1 | 03/20/2024 | 03/25/2024 | 3 | 0 | 3 | 03/26/2024 | 03/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 03/20/2024 | 5/29/2025 | Y | EXP | 365 | 10/17/2024 | 02/12/2025 | 68 | 0 | 68 |  |  | 12/31/2024 | Connected |  | N
National Grid | LEOMINSTER | 199443 | 01453 | 3.8 | Solar | 05_12_7J903 | 11/02/2018 | 11/29/2018 | 7 | 0 | 7 | 11/30/2018 | 11/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 1/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | WORCESTER | 435737 | 01604 | 15.2 | Solar | 05_14_43L4 | 06/06/2022 | 06/16/2022 | 9 | 8 | 1 | 06/17/2022 | 06/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 660963 | 01550 | 7.6 | Solar | 05_14_5J42 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 175933 | 01440 | 7.6 | Solar | 05_14_74L4 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 362 | 0 | 362 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 |  | 8/15/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 |  | Withdrawn |  | Y
National Grid | FALL RIVER | 527887 | 02724 | 6 | Solar | 05_01_219W2 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 668077 | 01905 | 3.8 | Solar | 05_01_27W1 | 01/27/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SAUGUS | 520785 | 01906 | 10 | Solar | 05_01_413L2 | 05/12/2023 | 05/16/2023 | 2 | 0 | 2 | 05/17/2023 | 05/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/12/2023 | 6/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2024 | Connected |  | N
National Grid | METHUEN | 644604 | 01844 | 10 | Solar | 05_01_607W3 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/02/2024 | 12/24/2025 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 582671 | 01844 | 1.74 | Solar | 05_05_115W55 | 01/26/2024 | 01/30/2024 | 2 | 0 | 2 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | METHUEN | 600626 | 01844 | 3.8 | Solar | 05_12_29W1 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 214350 | 01453 | 3.8 | Solar | 05_12_7J903 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 470911 | 01604 | 10 | Solar | 05_14_43L4 | 11/17/2022 |  | 162 | 50 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 728326 | 01566 | 5.76 | Solar | 05_14_5J42 | 11/17/2025 | 11/20/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 176269 | 01475 | 17.6 | Solar | 05_14_74L4 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/13/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 7/25/2016 | Connected |  | N
National Grid | FALL RIVER | 571393 | 02724 | 10 | Solar | 05_01_219W2 | 11/24/2023 | 12/11/2023 | 12 | 11 | 1 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 679786 | 01905 | 3.8 | Solar | 05_01_27W1 | 03/21/2025 | 06/03/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 44 | 32 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 521609 | 01906 | 7.6 | Solar | 05_01_413L2 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 656728 | 01841 | 5.76 | Solar | 05_01_607W3 | 11/25/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | METHUEN | 627842 | 01844 | 3.8 | Solar | 05_05_115W55 | 07/25/2024 | 08/05/2024 | 6 | 5 | 1 | 08/06/2024 | 08/06/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 07/25/2024 | 9/11/2025 | Y | EXP | 365 | 09/25/2024 | 10/11/2024 | 17 | 0 | 17 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 605243 | 01844 | 6.96 | Solar | 05_12_29W1 | 04/19/2024 | 06/11/2024 | 22 | 20 | 2 | 06/12/2024 | 06/12/2024 | 155 | 25 | 130 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 501622 | 01453 | 7.6 | Solar | 05_12_7J903 | 05/01/2023 | 05/04/2023 | 3 | 1 | 2 | 05/05/2023 | 05/05/2023 | 23 | 0 | 23 | 06/14/2023 | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  | 09/18/2023 | 66 | 0 | 66 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/27/2024 | N | EXP | 365 | 12/07/2023 | 12/06/2023 | 0 | 0 | 0 |  |  | 1/12/2024 | Connected |  | N
National Grid | WORCESTER | 479994 | 01604 | 7.6 | Solar | 05_14_43L4 | 12/19/2022 | 12/26/2022 | 5 | 0 | 5 | 12/27/2022 | 12/27/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 729809 | 01550 | 10 | Solar | 05_14_5J43 | 10/28/2025 | 10/29/2025 | 18 | 15 | 3 | 12/09/2025 | 12/09/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 | 10/28/2025 | 2/24/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GARDNER | 176665 | 01440 | 17.25 | Solar | 05_14_74L4 | 10/19/2015 | 10/19/2015 | 7 | 7 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 |  | 10/26/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/9/2016 | 8/9/2016 | 8/9/2016 | Connected |  | N
National Grid | FALL RIVER | 604880 | 02724 | 5.76 | Solar | 05_01_219W2 | 04/18/2024 | 05/21/2024 | 19 | 14 | 5 | 05/22/2024 | 05/22/2024 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/18/2024 | 7/25/2025 | Y | EXP | 365 | 09/04/2024 | 09/12/2024 | 9 | 0 | 9 |  |  | 12/12/2024 | Connected |  | N
National Grid | LYNN | 701051 | 01905 | 3.8 | Solar | 05_01_27W1 | 06/25/2025 | 07/10/2025 | 4 | 0 | 4 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 | 06/25/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | SAUGUS | 545544 | 01906 | 15.2 | Solar | 05_01_413L2 | 08/02/2023 | 08/09/2023 | 6 | 5 | 1 | 08/10/2023 | 08/10/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 08/02/2023 | 1/31/2025 | Y | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | METHUEN | 659120 | 01844 | 0 | Battery Add-On | 05_01_607W3 | 12/06/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 630792 | 01844 | 5.76 | Solar | 05_05_115W55 | 08/07/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/07/2024 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 10/07/2024 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 607470 | 01844 | 7.6 | Solar | 05_12_29W1 | 04/30/2024 | 05/10/2024 | 1 | 0 | 1 | 05/13/2024 | 05/13/2024 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 04/30/2024 | 12/31/2025 | Y | EXP | 365 | 02/19/2025 | 10/03/2025 | 227 | 0 | 227 |  |  | 10/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 519264 | 01453 | 3.8 | Solar | 05_12_7J903 | 05/03/2023 | 05/08/2023 | 3 | 0 | 3 | 05/09/2023 | 05/09/2023 | 21 | 0 | 21 | 06/14/2023 | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  | 09/15/2023 | 65 | 0 | 65 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/22/2024 | N | EXP | 365 | 01/03/2024 | 01/09/2024 | 7 | 0 | 7 |  |  | 1/13/2024 | Connected |  | N
National Grid | WORCESTER | 486205 | 01604 | 7.6 | Solar | 05_14_43L4 | 12/27/2022 | 12/29/2022 | 2 | 0 | 2 | 12/30/2022 | 12/30/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 515931 | 01550 | 3.8 | Solar | 05_14_5J43 | 04/07/2023 |  | 149 | 148 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 194731 | 01440 | 10 | Solar | 05_14_74L4 | 08/31/2018 | 09/18/2018 | 4 | 4 | 0 | 09/19/2018 | 09/19/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 | 08/31/2018 | 5/21/2019 | Y | EXP | 238 | 03/09/2019 | 04/09/2019 | 31 | 0 | 31 |  |  | 4/16/2019 | Connected |  | N
National Grid | FALL RIVER | 621331 | 02724 | 9.45 | Solar | 05_01_219W2 | 07/03/2024 | 07/05/2024 | 7 | 5 | 2 | 10/03/2024 | 10/03/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2024 | 07/03/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LYNN | 710806 | 01904 | 7.22 | Solar | 05_01_27W1 | 08/29/2025 | 10/13/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 568896 | 01906 | 6 | Solar | 05_01_413L2 | 01/08/2024 | 01/23/2024 | 11 | 9 | 2 | 01/24/2024 | 01/24/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/08/2024 | 5/24/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | METHUEN | 673971 | 01844 | 11.5 | Solar | 05_01_607W3 | 02/27/2025 | 03/10/2025 | 7 | 4 | 3 | 03/11/2025 | 03/11/2025 | 108 | 85 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 633673 | 01844 | 9.88 | Solar | 05_05_115W55 | 08/19/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 26 | 11 | 15 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 12/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 613294 | 01844 | 3.8 | Solar | 05_12_29W1 | 05/31/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 562325 | 01453 | 3.8 | Solar | 05_12_7J903 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2024 | Connected |  | N
National Grid | WORCESTER | 489999 | 01604 | 10 | Solar | 05_14_43L4 | 02/10/2023 |  | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 588136 | 01550 | 7.6 | Solar | 05_14_5J43 | 04/05/2024 | 04/17/2024 | 7 | 4 | 3 | 04/18/2024 | 04/18/2024 | 91 | 79 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 200801 | 01440 | 7.6 | Solar | 05_14_74L4 | 11/08/2018 | 12/31/2018 | 2 | 2 | 0 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 3/10/2020 | Y | EXP | 418 | 09/05/2019 | 09/26/2019 | 21 | 0 | 21 |  |  | 10/9/2019 | Connected |  | N
National Grid | FALL RIVER | 639575 | 02724 | 10 | Solar | 05_01_219W2 | 09/12/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/12/2024 | 12/3/2025 | Y | EXP | 365 | 12/19/2024 | 01/07/2025 | 20 | 0 | 20 |  |  | 1/17/2025 | Connected |  | N
National Grid | LYNN | 177653 | 01905 | 464 | Solar | 05_01_27W2 | 09/29/2017 | 09/29/2017 | 14 | 8 | 6 | 10/20/2017 | 10/20/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 601302 | 01906 | 10 | Solar | 05_01_413L2 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/04/2024 | 4/22/2025 | Y | EXP | 365 | 05/11/2024 | 06/04/2024 | 25 | 0 | 25 |  |  | 11/14/2024 | Connected |  | N
National Grid | METHUEN | 674436 | 01844 | 3.8 | Solar | 05_01_607W3 | 02/26/2025 | 04/25/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 02/26/2025 | 7/31/2026 | Y | EXP | 365 | 08/07/2025 | 10/24/2025 | 79 | 0 | 79 |  |  | 1/16/2026 | Connected |  | N
National Grid | METHUEN | 657557 | 01844 | 6 | Solar | 05_05_115W55 | 11/28/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | METHUEN | 619178 | 01844 | 5 | Solar | 05_12_29W1 | 06/19/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 | 06/19/2024 | 7/30/2025 | Y | EXP | 365 | 09/06/2024 | 12/19/2024 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 587947 | 01453 | 3.8 | Solar | 05_12_7J903 | 02/10/2024 | 02/12/2024 | 1 | 0 | 1 | 02/13/2024 | 02/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 2/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | WORCESTER | 491242 | 01605 | 7.83 | Solar | 05_14_43L4 | 01/20/2023 | 01/25/2023 | 3 | 1 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/20/2023 | 8/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 608023 | 01550 | 3.8 | Solar | 05_14_5J43 | 05/02/2024 | 05/09/2024 | 1 | 0 | 1 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 | 05/02/2024 | 8/3/2025 | Y | EXP | 365 | 09/19/2024 | 10/29/2024 | 41 | 0 | 41 |  |  | 1/17/2025 | Connected |  | N
National Grid | GARDNER | 215445 | 01440 | 10 | Solar | 05_14_74L4 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 644853 | 02724 | 10 | Solar | 05_01_219W2 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/03/2024 | 12/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | LYNN | 193702 | 01904 | 832.5 | Solar | 05_01_27W2 | 09/18/2018 | 10/31/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 04/01/2019 | 101 | 82 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 09/18/2018 | 4/25/2024 | Y | STD | 1142 | 05/18/2023 | 04/22/2024 | 339 | 144 | 195 |  |  | 4/15/2024 | Connected |  | N
National Grid | SAUGUS | 602467 | 01906 | 9.88 | Solar | 05_01_413L2 | 04/12/2024 | 04/18/2024 | 3 | 0 | 3 | 04/19/2024 | 04/19/2024 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | METHUEN | 459174 | 01844 | 240 | Solar | 05_01_607W4 | 09/23/2022 | 10/17/2022 | 16 | 8 | 8 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | METHUEN | 682467 | 01844 | 6.08 | Solar | 05_05_115W55 | 04/04/2025 | 04/28/2025 | 15 | 10 | 5 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | METHUEN | 628547 | 01844 | 7.6 | Solar | 05_12_29W1 | 09/17/2024 | 11/25/2024 | 26 | 25 | 1 | 11/26/2024 | 11/26/2024 | 61 | 41 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 09/17/2024 | 4/10/2026 | Y | EXP | 365 | 07/24/2025 | 11/18/2025 | 118 | 0 | 118 |  |  | 12/1/2025 | Connected |  | N
National Grid | LEOMINSTER | 174990 | 01453 | 75 | Diesel | 05_12_7W1 | 03/06/2013 | 03/06/2013 | 5 | 0 | 5 | 03/18/2013 | 03/18/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2013 |  | 6/28/2013 | N | EXP | 7 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/17/2013 | Connected |  | N
National Grid | WORCESTER | 512389 | 01605 | 9.86 | Solar | 05_14_43L4 | 05/10/2023 | 05/15/2023 | 3 | 0 | 3 | 05/16/2023 | 05/16/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 616382 | 01566 | 3.8 | Solar | 05_14_5J43 | 06/07/2024 | 06/28/2024 | 1 | 0 | 1 | 07/01/2024 | 07/01/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 | 06/07/2024 | 8/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | GARDNER | 268864 | 01440 | 10 | Solar | 05_14_74L4 | 12/17/2019 | 12/20/2019 | 2 | 0 | 2 | 12/23/2019 | 12/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 | 12/17/2019 | 12/17/2020 | Y | EXP | 365 | 07/16/2020 | 08/19/2020 | 34 | 0 | 34 |  |  | 10/28/2020 | Connected |  | N
National Grid | FALL RIVER | 647479 | 02724 | 5.76 | Solar | 05_01_219W2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/29/2024 | 1/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | LYNN | 197375 | 01905 | 10 | Solar | 05_01_27W2 | 10/08/2018 | 10/29/2018 | 13 | 13 | 0 | 10/30/2018 | 10/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 609343 | 02151 | 3.8 | Solar | 05_01_413L2 | 05/07/2024 | 05/14/2024 | 5 | 0 | 5 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 10/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | METHUEN | 722236 | 01844 | 10 | Solar | 05_01_607W4 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 689895 | 01844 | 7.6 | Solar | 05_05_115W55 | 05/06/2025 | 06/26/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/06/2025 | 10/10/2026 | Y | EXP | 365 | 01/06/2026 | 01/05/2026 | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | METHUEN | 632467 | 01844 | 3.8 | Solar | 05_12_29W1 | 08/15/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/15/2024 | 9/10/2025 | Y | EXP | 365 | 10/30/2024 | 04/14/2025 | 167 | 0 | 167 |  |  | 5/6/2025 | Connected |  | N
National Grid | LEOMINSTER | 177794 | 01453 | 7.6 | Solar | 05_12_7W1 | 08/02/2017 | 08/02/2017 | 4 | 0 | 4 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 |  | 8/8/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  | 8/1/2018 | Connected |  | N
National Grid | WORCESTER | 521781 | 01605 | 11.04 | Solar | 05_14_43L4 | 04/27/2023 |  | 136 | 135 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 625674 | 01550 | 7.6 | Solar | 05_14_5J43 | 07/17/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | GARDNER | 273564 | 01440 | 360 | Natural Gas | 05_14_74L4 | 05/12/2020 | 06/04/2020 | 16 | 10 | 6 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 647432 | 02724 | 3.8 | Solar | 05_01_219W2 | 10/30/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | LYNN | 495536 | 01904 | 11.4 | Solar | 05_01_27W2 | 02/04/2023 | 02/06/2023 | 26 | 25 | 1 | 03/14/2023 | 03/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | N
National Grid | REVERE | 618333 | 02151 | 10 | Solar | 05_01_413L2 | 01/17/2025 | 02/05/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | METHUEN | 747256 | 01844 | 0 | Battery Add-On | 05_01_607W4 | 01/23/2026 | 01/27/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 27 | 16 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 721391 | 01844 | 11.5 | Solar | 05_05_115W55 | 09/23/2025 | 10/08/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 641041 | 01841 | 7.6 | Solar | 05_12_29W1 | 11/08/2024 | 03/12/2025 | 10 | 7 | 3 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LEOMINSTER | 394618 | 01453 | 28.8 | Solar | 05_12_7W1 | 01/13/2022 | 01/26/2022 | 9 | 7 | 2 | 01/27/2022 | 01/27/2022 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  | 3/18/2024 | N | EXP | 7 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | WORCESTER | 524638 | 01605 | 6 | Solar | 05_14_43L4 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 177329 | 01566 | 120 | Solar | 05_14_5J44 | 06/21/2016 | 06/21/2016 | 2 | 2 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 32 | 02/15/2017 | 02/28/2017 | 8 | 0 | 8 | 4/19/2017 | 4/19/2017 | 4/19/2017 | Connected |  | N
National Grid | GARDNER | 281460 | 01440 | 10 | Solar | 05_14_74L4 | 03/11/2020 | 03/23/2020 | 0 | 0 | 0 | 03/24/2020 | 03/24/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/11/2020 | 3/22/2021 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | FALL RIVER | 648304 | 02724 | 10 | Solar | 05_01_219W2 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/21/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | LYNN | 500916 | 01905 | 100 | Solar | 05_01_27W2 | 02/24/2023 | 04/07/2023 | 31 | 21 | 10 | 04/10/2023 | 04/10/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 624915 | 02151 | 7.6 | Solar | 05_01_413L2 | 07/15/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 750045 | 01844 | 500 | Solar | 05_01_607W4 | 03/03/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | METHUEN | 562342 | 01844 | 4990 | Solar | 05_05_11W81 | 12/05/2023 | 01/19/2024 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2024 | 03/28/2024 | 48 | 30 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 12/05/2023 | 11/2/2026 | Y | STD | 46 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | METHUEN | 642538 | 01844 | 7.54 | Solar | 05_12_29W1 | 09/24/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 616872 | 01453 | 7.6 | Solar | 05_12_7W1 | 06/11/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | WORCESTER | 527935 | 01605 | 10 | Solar | 05_14_43L4 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 258970 | 01566 | 10 | Solar | 05_14_5J44 | 10/24/2019 | 10/25/2019 | 0 | 0 | 0 | 10/28/2019 | 10/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 10/24/2019 | 10/24/2020 | Y | EXP | 365 | 02/27/2020 | 03/03/2020 | 5 | 0 | 5 |  |  | 3/4/2020 | Connected |  | N
National Grid | GARDNER | 590983 | 01440 | 6 | Solar | 05_14_74L4 | 03/11/2024 | 03/13/2024 | 2 | 0 | 2 | 03/14/2024 | 03/14/2024 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 03/11/2024 | 7/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | SWANSEA | 655579 | 02777 | 3.8 | Solar | 05_01_219W2 | 11/20/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | LYNN | 648354 | 01904 | 3.8 | Solar | 05_01_27W2 | 10/30/2024 | 05/05/2025 | 3 | 1 | 2 | 05/06/2025 | 05/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 641629 | 02151 | 10 | Solar | 05_01_413L2 | 10/02/2024 | 10/23/2024 | 7 | 4 | 3 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/02/2024 | 1/3/2026 | Y | EXP | 365 | 06/11/2025 | 07/30/2025 | 50 | 0 | 50 |  |  | 10/7/2025 | Connected |  | N
National Grid | METHUEN | 174498 | 01844 | 3300 | Wind | 05_01_607W4 | 06/10/2010 | 06/10/2010 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 06/10/2010 | 10/31/2012 | Y | STD | 42 |  |  | 0 | 0 | 0 | 4/12/2013 | 4/12/2013 | 4/4/2013 | Connected |  | N
National Grid | METHUEN | 693170 | 01844 | 5.76 | Solar | 05_05_11W81 | 06/02/2025 | 07/15/2025 | 7 | 4 | 3 | 08/06/2025 | 08/06/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 643215 | 01844 | 10 | Solar | 05_12_29W1 | 09/26/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/26/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LEOMINSTER | 648905 | 01453 | 7.68 | Solar | 05_12_7W1 | 10/22/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | WORCESTER | 527661 | 01605 | 10 | Solar | 05_14_43L4 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 290050 | 01550 | 7.6 | Solar | 05_14_5J44 | 05/05/2020 |  | 48 | 48 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 593130 | 01440 | 10 | Solar | 05_14_74L4 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/03/2024 | 5/31/2025 | Y | EXP | 365 | 07/16/2024 | 11/18/2024 | 126 | 0 | 126 |  |  | 12/21/2024 | Connected |  | N
National Grid | SWANSEA | 659724 | 02777 | 2.32 | Solar | 05_01_219W2 | 12/10/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LYNN | 666140 | 01904 | 5.76 | Solar | 05_01_27W2 | 01/16/2025 | 02/04/2025 | 8 | 4 | 4 | 02/05/2025 | 02/05/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 647245 | 02151 | 5.76 | Solar | 05_01_413L2 | 10/15/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/15/2024 | 12/23/2025 | Y | EXP | 365 | 08/22/2025 | 08/28/2025 | 7 | 0 | 7 |  |  | 9/15/2025 | Connected |  | N
National Grid | METHUEN | 176405 | 01844 | 1500 | Wind | 05_01_607W4 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/06/2016 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 730560 | 01844 | 23 | Solar | 05_05_11W81 | 10/31/2025 | 11/04/2025 | 2 | 0 | 2 | 11/05/2025 | 11/05/2025 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 1/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 652674 | 01844 | 7.6 | Solar | 05_12_29W1 | 11/06/2024 | 12/04/2024 | 10 | 5 | 5 | 12/05/2024 | 12/05/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/06/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | N
National Grid | LEOMINSTER | 666990 | 01453 | 3.2 | Solar | 05_12_7W1 | 01/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/21/2025 | 5/16/2026 | Y | EXP | 365 | 08/08/2025 | 11/21/2025 | 106 | 0 | 106 |  |  | 12/1/2025 | Connected |  | N
National Grid | WORCESTER | 534617 | 01605 | 11.31 | Solar | 05_14_43L4 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/27/2023 | 10/31/2024 | Y | EXP | 365 | 12/06/2023 | 12/12/2023 | 7 | 0 | 7 |  |  | 1/12/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 304996 | 01550 | 7.6 | Solar | 05_14_5J44 | 08/04/2020 | 08/06/2020 | 1 | 0 | 1 | 08/07/2020 | 08/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 621133 | 01440 | 15.2 | Solar | 05_14_74L4 | 06/29/2024 | 07/11/2024 | 8 | 6 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 660535 | 02777 | 10 | Solar | 05_01_219W2 | 12/13/2024 | 01/08/2025 | 1 | 0 | 1 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 670172 | 01904 | 10 | Solar | 05_01_27W2 | 02/05/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | REVERE | 648427 | 02151 | 3.8 | Solar | 05_01_413L2 | 11/07/2024 | 11/21/2024 | 4 | 0 | 4 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 11/07/2024 | 2/18/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | METHUEN | 176399 | 01844 | 7.6 | Solar | 05_01_607W4 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2016 | 03/10/2016 | 3/19/2017 | Y | EXP | 328 | 07/18/2016 | 08/11/2016 | 18 | 0 | 18 | 4/25/2016 | 4/25/2016 | 9/8/2016 | Connected |  | N
National Grid | METHUEN | 174269 | 01844 | 300 | Solar | 05_05_11W81 | 12/19/2011 | 12/19/2011 | 30 | 0 | 30 | 02/02/2012 | 02/02/2012 | 486 | 0 | 486 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2012 |  | 6/1/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 653618 | 01841 | 4.56 | Solar | 05_12_29W1 | 11/12/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 683414 | 01453 | 14.95 | Solar | 05_12_7W1 | 04/23/2025 | 05/23/2025 | 4 | 0 | 4 | 06/12/2025 | 06/12/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 553269 | 01605 | 6 | Solar | 05_14_43L4 | 09/15/2023 | 09/28/2023 | 9 | 7 | 2 | 09/29/2023 | 09/29/2023 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 426328 | 01550 | 5.51 | Solar | 05_14_5J44 | 05/11/2022 | 05/24/2022 | 10 | 7 | 3 | 05/25/2022 | 05/25/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 |  | 7/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2022 | Connected |  | N
National Grid | GARDNER | 624281 | 01440 | 10 | Solar | 05_14_74L4 | 07/15/2024 | 07/23/2024 | 1 | 0 | 1 | 07/24/2024 | 07/24/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 663860 | 02777 | 3.8 | Solar | 05_01_219W2 | 01/06/2025 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 01/06/2025 | 3/17/2026 | Y | EXP | 365 | 04/30/2025 | 10/24/2025 | 178 | 0 | 178 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 685699 | 01904 | 5.76 | Solar | 05_01_27W2 | 04/28/2025 | 05/13/2025 | 7 | 2 | 5 | 06/12/2025 | 06/12/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | REVERE | 655030 | 02151 | 8.99 | Solar | 05_01_413L2 | 11/18/2024 | 03/10/2025 | 26 | 25 | 1 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | LAWRENCE | 176568 | 01841 | 7.6 | Solar | 05_01_607W4 | 12/23/2015 | 12/23/2015 | 20 | 20 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 12/23/2015 | 12/29/2016 | Y | EXP | 31 | 07/18/2016 | 08/16/2016 | 21 | 0 | 21 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | METHUEN | 174873 | 01844 | 2000 | Solar | 05_05_11W81 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 11/27/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 655690 | 01844 | 6 | Solar | 05_12_29W1 | 11/20/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | LEOMINSTER | 744816 | 01453 | 5.76 | Solar | 05_12_7W2 | 01/14/2026 | 01/20/2026 | 7 | 5 | 2 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 564231 | 01605 | 7.6 | Solar | 05_14_43L4 | 11/08/2023 | 11/17/2023 | 6 | 3 | 3 | 11/20/2023 | 11/20/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 671959 | 01550 | 11.52 | Solar | 05_14_5J44 | 02/13/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | GARDNER | 626258 | 01440 | 10 | Solar | 05_14_74L4 | 07/19/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/19/2024 | 8/26/2025 | Y | EXP | 365 | 11/26/2024 | 03/25/2025 | 120 | 0 | 120 |  |  | 4/7/2025 | Connected |  | N
National Grid | SWANSEA | 670221 | 02777 | 39.9 | Solar | 05_01_219W2 | 03/18/2025 | 03/27/2025 | 7 | 4 | 3 | 03/28/2025 | 03/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | LYNN | 174467 | 01904 | 250 | Natural Gas | 05_01_27W3 | 07/20/2011 | 07/20/2011 | 43 | 0 | 43 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 |  | 12/31/2016 | N | EXP | 1852 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 658103 | 02151 | 7.6 | Solar | 05_01_413L2 | 12/03/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 177006 | 01844 | 10 | Solar | 05_01_607W4 | 10/11/2016 | 10/13/2016 | 1 | 1 | 0 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2016 | 10/11/2016 | 9/30/2019 | Y | EXP | 178 | 05/05/2017 | 05/05/2017 | 39 | 0 | 39 | 3/13/2018 | 3/13/2018 | 9/13/2019 | Connected |  | N
National Grid | METHUEN | 174930 | 01844 | 50 | Solar | 05_05_11W81 | 08/26/2013 | 08/26/2013 | 11 | 4 | 7 | 09/13/2013 | 09/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2013 |  | 12/31/2013 | N | EXP | 96 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 | 12/12/2013 | Connected |  | N
National Grid | METHUEN | 688867 | 01844 | 11.4 | Solar | 05_12_29W1 | 05/01/2025 | 06/18/2025 | 13 | 8 | 5 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/01/2025 | 7/28/2026 | Y | EXP | 365 | 08/21/2025 | 10/29/2025 | 70 | 0 | 70 |  |  | 11/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 744515 | 01453 | 7.6 | Solar | 05_12_7W2 | 01/14/2026 | 01/15/2026 | 19 | 16 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 578821 | 01604 | 7.6 | Solar | 05_14_43L4 | 07/15/2024 | 01/08/2024 | 6 | 1 | 5 | 07/24/2024 | 07/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 193954 | 01550 | 357 | Hydro | 05_14_5J45 | 08/31/2018 | 09/27/2018 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2019 |  | 2/26/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  | 2/12/2021 | Connected |  | N
National Grid | GARDNER | 640113 | 01440 | 10 | Solar | 05_14_74L4 | 09/13/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 693924 | 02777 | 6.96 | Solar | 05_01_219W2 | 05/23/2025 | 06/03/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2025 | Connected |  | N
National Grid | LYNN | 198897 | 01904 | 3000 | Natural Gas | 05_01_27W3 | 07/11/2019 | 08/30/2019 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2019 | 10/14/2019 | 29 | 21 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 658241 | 02151 | 5.76 | Solar | 05_01_413L2 | 12/03/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | LAWRENCE | 177832 | 01841 | 900 | Solar | 05_01_607W4 | 08/08/2017 | 08/08/2017 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2017 | 09/26/2017 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 | 08/08/2017 | 10/8/2021 | Y | STD | 555 | 01/07/2021 | 09/21/2021 | 258 | 80 | 178 | 9/22/2021 | 9/30/2021 | 10/7/2021 | Connected |  | N
National Grid | METHUEN | 175116 | 01844 | 25 | Solar | 05_05_11W81 | 10/16/2013 | 10/16/2013 | 6 | 0 | 6 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2013 |  | 9/1/2014 | N | EXP | 299 |  |  | 0 | 0 | 0 | 5/27/2014 | 5/27/2014 | 7/3/2014 | Connected |  | N
National Grid | METHUEN | 691976 | 01844 | 5.12 | Solar | 05_12_29W1 | 05/15/2025 | 06/18/2025 | 5 | 1 | 4 | 07/03/2025 | 07/03/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 05/15/2025 | 10/10/2026 | Y | EXP | 365 | 10/07/2025 | 10/17/2025 | 11 | 0 | 11 |  |  | 11/25/2025 | Connected |  | N
National Grid | LEOMINSTER | 745715 | 01453 | 15.76 | Solar | 05_12_7W2 | 01/20/2026 | 01/27/2026 | 5 | 0 | 5 | 01/28/2026 | 01/28/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 585644 | 01602 | 9.28 | Solar | 05_14_43L4 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 3/6/2025 | Y | EXP | 365 | 07/16/2024 | 11/04/2024 | 112 | 0 | 112 |  |  | 11/9/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 178560 | 01550 | 432.9 | Solar | 05_14_60L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 44 | 19 | 25 | 07/02/2018 | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  | 10/09/2018 | 69 | 0 | 69 |  |  | 0 | 0 | 0 | 4/12/2019 | 04/05/2018 | 8/7/2026 | Y | STD | 154 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTMINSTER | 640945 | 01473 | 7.6 | Solar | 05_14_74L4 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 696159 | 02777 | 5.76 | Solar | 05_01_219W2 | 06/11/2025 | 06/26/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2026 | Connected |  | N
National Grid | LYNN | 378510 | 01904 | 3000 | Natural Gas | 05_01_27W3 | 04/12/2022 | 05/16/2022 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2022 | 06/15/2022 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 04/12/2022 | 2/10/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | REVERE | 659732 | 02151 | 7.6 | Solar | 05_01_413L2 | 12/10/2024 | 01/01/2025 | 5 | 0 | 5 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/10/2024 | 2/20/2026 | Y | EXP | 365 | 04/30/2025 | 08/04/2025 | 97 | 0 | 97 |  |  | 9/8/2025 | Connected |  | N
National Grid | METHUEN | 193550 | 01844 | 250 | Solar | 05_01_607W4 | 08/15/2018 | 08/27/2018 | 6 | 0 | 6 | 08/28/2018 | 08/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 175934 | 01951 | 8.6 | Solar | 05_05_11W81 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/15/2016 | N | EXP | 349 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/16/2016 | Connected |  | N
National Grid | LAWRENCE | 742453 | 01841 | 17.16 | Solar | 05_12_29W1 | 12/29/2025 | 12/31/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176039 | 01453 | 2.58 | Solar | 05_12_7W2 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/19/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 5/12/2016 | 5/12/2016 | 6/27/2016 | Connected |  | N
National Grid | WORCESTER | 589208 | 01602 | 7.6 | Solar | 05_14_43L4 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/23/2024 | 4/23/2025 | Y | EXP | 365 | 07/16/2024 | 09/20/2024 | 67 | 0 | 67 |  |  | 10/23/2024 | Connected |  | N
National Grid | STURBRIDGE | 555669 | 01566 | 0 | Solar | 05_14_60L1 | 09/14/2023 | 09/19/2023 | 4 | 3 | 1 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/14/2026 | N | EXP | 195 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GARDNER | 642225 | 01440 | 10 | Solar | 05_14_74L4 | 09/23/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 98 | 78 | 20 | 03/31/2025 | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 04/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/23/2024 | 5/28/2026 | Y | EXP | 365 | 06/28/2025 | 12/22/2025 | 178 | 0 | 178 |  |  | 12/15/2025 | Connected |  | N
National Grid | SWANSEA | 701355 | 02777 | 11.5 | Solar | 05_01_219W2 | 06/27/2025 | 07/08/2025 | 6 | 3 | 3 | 07/09/2025 | 07/09/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | LYNN | 676963 | 01904 | 960 | Solar | 05_01_27W4 | 04/10/2025 | 06/10/2025 | 41 | 32 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 659432 | 02151 | 7.68 | Solar | 05_01_413L2 | 12/10/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 195651 | 01844 | 5 | Solar | 05_01_607W4 | 09/11/2018 | 10/24/2018 | 15 | 15 | 0 | 10/25/2018 | 10/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/11/2018 | 4/26/2019 | Y | EXP | 176 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | NEWBURY | 176169 | 01951 | 476 | Solar | 05_05_11W81 | 04/17/2015 | 04/17/2015 | 1 | 1 | 0 | 04/22/2015 | 04/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2015 | 04/17/2015 | 12/31/2016 | Y | EXP | 582 | 08/30/2016 | 12/12/2016 | 70 | 0 | 70 | 5/29/2015 | 5/29/2015 | 12/13/2016 | Connected |  | N
National Grid | METHUEN | 731709 | 01844 | 3.8 | Solar | 05_12_29W1 | 11/05/2025 | 11/19/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 176339 | 01453 | 3.8 | Solar | 05_12_7W2 | 09/17/2015 | 09/17/2015 | 5 | 5 | 0 | 09/24/2015 | 09/24/2015 | 330 | 0 | 330 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 |  | 9/22/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 591270 | 01605 | 6 | Solar | 05_14_43L4 | 02/23/2024 | 02/26/2024 | 1 | 0 | 1 | 02/27/2024 | 02/27/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 02/23/2024 | 3/27/2025 | Y | EXP | 365 | 05/30/2024 | 07/17/2024 | 49 | 0 | 49 |  |  | 7/19/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 703373 | 01550 | 2.9 | Solar | 05_14_60L1 | 07/08/2025 | 07/10/2025 | 2 | 0 | 2 | 07/11/2025 | 07/11/2025 | 163 | 150 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 657516 | 01440 | 7.6 | Solar | 05_14_74L4 | 11/27/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/7/2026 | N | EXP | 365 | 03/11/2025 | 03/25/2025 | 15 | 0 | 15 |  |  | 5/22/2025 | Connected |  | N
National Grid | SWANSEA | 729072 | 02777 | 11.5 | Solar | 05_01_219W2 | 11/04/2025 | 11/10/2025 | 4 | 0 | 4 | 11/12/2025 | 11/12/2025 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 679785 | 01905 | 117.3 | Solar | 05_01_27W4 | 09/03/2025 | 10/03/2025 | 22 | 14 | 8 | 10/06/2025 | 10/06/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 673435 | 02151 | 5.76 | Solar | 05_01_413L2 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | METHUEN | 192916 | 01844 | 2040 | Solar | 05_01_607W4 | 10/25/2018 |  | 232 | 26 | 206 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 176583 | 01951 | 7.6 | Solar | 05_05_11W81 | 04/07/2016 | 04/07/2016 | 4 | 4 | 0 | 04/13/2016 | 04/13/2016 | 199 | 0 | 199 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/12/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 605829 | 01844 | 484.6 | Solar | 05_12_29W2 | 05/13/2024 | 07/02/2024 | 34 | 26 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2024 | 07/16/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 4/19/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LEOMINSTER | 176788 | 01453 | 11.4 | Solar | 05_12_7W2 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 01/14/2016 | 10/31/2017 | Y | EXP | 616 | 09/18/2017 | 11/14/2017 | 34 | 0 | 34 | 4/28/2017 | 4/28/2017 | 11/16/2017 | Connected |  | N
National Grid | WORCESTER | 595995 | 01605 | 7.6 | Solar | 05_14_43L4 | 04/05/2024 | 04/15/2024 | 6 | 2 | 4 | 04/16/2024 | 04/16/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/05/2024 | 4/25/2025 | Y | EXP | 365 | 06/05/2024 | 06/21/2024 | 17 | 0 | 17 |  |  | 7/18/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 752120 | 01550 | 11.5 | Solar | 05_14_60L1 | 02/23/2026 | 02/26/2026 | 3 | 0 | 3 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GARDNER | 661078 | 01440 | 5 | Solar | 05_14_74L4 | 12/17/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 749323 | 02777 | 0 | Battery Add-On | 05_01_219W2 | 02/04/2026 | 02/10/2026 | 4 | 0 | 4 | 02/11/2026 | 02/11/2026 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 706238 | 01970 | 200 | Solar | 05_01_27W4 | 08/11/2025 | 09/18/2025 | 27 | 17 | 10 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 677981 | 02151 | 10 | Solar | 05_01_413L2 | 03/13/2025 | 09/15/2025 | 118 | 25 | 93 | 09/16/2025 | 09/16/2025 | 53 | 52 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 371045 | 01844 | 7.6 | Solar | 05_01_607W4 | 08/03/2021 | 12/30/2021 | 1 | 0 | 1 | 08/05/2021 | 08/05/2021 | 53 | 29 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 11/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | NEWBURY | 176748 | 01951 | 5 | Solar | 05_05_11W81 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 9/1/2016 | Connected |  | N
National Grid | LAWRENCE | 605827 | 01841 | 250 | Solar | 05_12_29W2 | 05/13/2024 | 07/15/2024 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2024 | 07/16/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 05/13/2024 | 4/19/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LEOMINSTER | 177141 | 01453 | 10 | Solar | 05_12_7W2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 162 | 0 | 162 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/6/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 595579 | 01605 | 7.6 | Solar | 05_14_43L4 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 03/13/2024 | 4/17/2025 | Y | EXP | 365 | 04/16/2024 | 09/03/2024 | 141 | 0 | 141 |  |  | 9/26/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 175109 | 01550 | 1992 | Solar | 05_14_60L1 | 04/22/2013 | 04/22/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2013 | 06/24/2013 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2014 | 04/22/2013 | 12/31/2016 | Y | STD | 943 | 01/03/2017 | 04/18/2017 | 72 | 0 | 72 |  |  | 5/4/2017 | Connected |  | N
National Grid | GARDNER | 665950 | 01440 | 0 | Solar | 05_14_74L4 | 01/15/2025 | 01/16/2025 | 1 | 0 | 1 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/15/2025 | 6/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SWANSEA | 435107 | 02777 | 0 | Other | 05_01_219W3 | 07/05/2022 | 10/20/2022 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/08/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SALEM | 716552 | 01970 | 67.3 | Solar | 05_01_27W4 | 09/23/2025 | 10/20/2025 | 17 | 8 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 688350 | 02151 | 10 | Solar | 05_01_413L2 | 04/29/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/29/2025 | 8/4/2026 | Y | EXP | 365 | 11/07/2025 | 12/18/2025 | 42 | 0 | 42 |  |  | 12/3/2025 | Connected |  | N
National Grid | LAWRENCE | 407933 | 01841 | 6 | Solar | 05_01_607W4 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/04/2022 | 4/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | NEWBURY | 177167 | 01951 | 2.75 | Solar | 05_05_11W81 | 01/25/2017 | 01/25/2017 | 80 | 78 | 2 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 | 01/25/2017 | 1/31/2018 | Y | EXP | 253 | 07/18/2017 | 07/24/2017 | 4 | 0 | 4 | 11/3/2017 | 11/3/2017 | 11/3/2017 | Connected |  | N
National Grid | METHUEN | 697403 | 01844 | 12.92 | Solar | 05_12_29W2 | 06/10/2025 | 09/18/2025 | 7 | 2 | 5 | 10/03/2025 | 10/03/2025 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | LEOMINSTER | 177738 | 01453 | 6 | Solar | 05_12_7W2 | 03/24/2017 | 03/24/2017 | 4 | 4 | 0 | 03/31/2017 | 03/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/24/2017 | 8/10/2018 | Y | EXP | 493 | 10/24/2017 | 11/29/2017 | 19 | 0 | 19 |  |  | 8/29/2018 | Connected |  | N
National Grid | WORCESTER | 597509 | 01605 | 13.325 | Solar | 05_14_43L4 | 04/03/2024 | 04/17/2024 | 9 | 6 | 3 | 04/18/2024 | 04/18/2024 | 37 | 32 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 175203 | 01550 | 3000 | Solar | 05_14_60L1 | 11/30/2012 | 11/30/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2012 | 01/14/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 668181 | 01440 | 7.6 | Solar | 05_14_74L4 | 01/27/2025 | 02/17/2025 | 15 | 14 | 1 | 02/18/2025 | 02/18/2025 | 51 | 30 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 174600 | 02777 | 225 | Solar | 05_01_219W3 | 10/03/2011 | 10/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2011 | 10/03/2011 | 3/1/2012 | Y | EXP | 87 | 02/16/2012 | 02/24/2012 | 5 | 0 | 5 | 8/9/2012 | 8/9/2012 | 3/1/2012 | Connected |  | N
National Grid | SALEM | 716453 | 01970 | 100 | Solar | 05_01_27W4 | 09/23/2025 | 10/14/2025 | 14 | 5 | 9 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 705879 | 02151 | 10 | Solar | 05_01_413L2 | 07/18/2025 | 08/04/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 07/18/2025 | 9/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | LAWRENCE | 437898 | 01841 | 10 | Solar | 05_01_607W4 | 06/28/2022 |  | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 177423 | 01951 | 1260 | Solar | 05_05_11W81 | 12/06/2016 | 12/06/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 01/12/2017 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2017 |  | 6/11/2020 | N | STD | 152 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 177353 | 01844 | 3.8 | Solar | 05_12_29W2 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 | 02/15/2017 | 7/17/2019 | Y | EXP | 87 | 05/24/2018 | 05/24/2018 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 178212 | 01453 | 3.8 | Solar | 05_12_7W2 | 03/23/2018 | 03/23/2018 | 9 | 0 | 9 | 05/14/2018 | 05/14/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 | 03/23/2018 | 7/31/2019 | Y | EXP | 48 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 597079 | 01605 | 2.32 | Solar | 05_14_43L4 | 03/22/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 176968 | 01550 | 20 | Solar | 05_14_60L1 | 10/04/2016 | 10/04/2016 | 2 | 2 | 0 | 10/06/2016 | 10/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 |  | 10/9/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/31/2017 | 8/31/2017 | 8/31/2017 | Connected |  | N
National Grid | GARDNER | 679170 | 01440 | 10 | Solar | 05_14_74L4 | 03/19/2025 | 05/22/2025 | 4 | 0 | 4 | 05/23/2025 | 05/23/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176977 | 02777 | 35 | Solar | 05_01_219W3 | 12/27/2016 | 12/27/2016 | 4 | 3 | 1 | 01/03/2017 | 01/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2017 |  | 1/2/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 3/30/2017 | Connected |  | N
National Grid | SALEM | 740379 | 01970 | 5.76 | Solar | 05_01_27W4 | 12/15/2025 | 01/20/2026 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 674825 | 02151 | 7.6 | Solar | 05_01_413L3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 527513 | 01841 | 10 | Solar | 05_01_607W4 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 177710 | 01950 | 7.6 | Solar | 05_05_11W81 | 05/30/2017 | 05/30/2017 | 7 | 7 | 0 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 | 05/30/2017 | 6/4/2018 | Y | EXP | 36 | 09/28/2017 | 10/13/2017 | 10 | 0 | 10 | 10/25/2017 | 10/25/2017 | 10/30/2017 | Connected |  | N
National Grid | METHUEN | 196948 | 01844 | 8.64 | Solar | 05_12_29W2 | 09/25/2018 | 10/17/2018 | 13 | 7 | 6 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 178452 | 01453 | 10 | Solar | 05_12_7W2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 11/29/2017 | 11/25/2019 | Y | EXP | 64 | 01/08/2019 | 04/19/2019 | 101 | 0 | 101 |  |  | 11/6/2019 | Connected |  | N
National Grid | WORCESTER | 602477 | 01605 | 11.4 | Solar | 05_14_43L4 | 04/17/2024 | 06/25/2024 | 47 | 47 | 0 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 | 04/17/2024 | 8/12/2025 | Y | EXP | 365 | 10/03/2024 | 11/26/2024 | 55 | 0 | 55 |  |  | 12/18/2024 | Connected |  | N
National Grid | DUDLEY | 178071 | 01571 | 15.2 | Solar | 05_14_60L1 | 10/31/2017 | 10/31/2017 | 0 | 0 | 0 | 11/06/2017 | 11/06/2017 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 11/6/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 681572 | 01473 | 0 | Solar | 05_14_74L4 | 04/02/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 193664 | 02777 | 7.6 | Solar | 05_01_219W3 | 08/15/2018 | 09/05/2018 | 4 | 4 | 0 | 09/06/2018 | 09/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 747555 | 01970 | 15.2 | Solar | 05_01_27W4 | 01/29/2026 | 02/02/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 680048 | 02151 | 10 | Solar | 05_01_413L3 | 03/26/2025 | 04/30/2025 | 24 | 22 | 2 | 05/01/2025 | 05/01/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 600531 | 01844 | 7.6 | Solar | 05_01_607W4 | 04/04/2024 | 04/10/2024 | 4 | 0 | 4 | 04/11/2024 | 04/11/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/04/2024 | 6/4/2025 | Y | EXP | 365 | 08/21/2024 | 09/09/2024 | 20 | 0 | 20 |  |  | 9/14/2024 | Connected |  | N
National Grid | NEWBURY | 177751 | 01951 | 5.2 | Solar | 05_05_11W81 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2017 | 07/27/2017 | 8/1/2018 | Y | EXP | 348 | 08/24/2017 | 09/09/2017 | 11 | 0 | 11 | 11/27/2017 | 11/27/2017 | 12/1/2017 | Connected |  | N
National Grid | METHUEN | 208985 | 01844 | 7.6 | Solar | 05_12_29W2 | 03/15/2019 | 03/18/2019 | 1 | 1 | 0 | 03/19/2019 | 03/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/15/2019 | 2/21/2020 | Y | EXP | 337 | 08/16/2019 | 10/02/2019 | 47 | 0 | 47 |  |  | 10/31/2019 | Connected |  | N
National Grid | LEOMINSTER | 184518 | 01453 | 10 | Solar | 05_12_7W2 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 6/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2018 | Connected |  | N
National Grid | WORCESTER | 610901 | 01605 | 10 | Solar | 05_14_43L4 | 05/31/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 178240 | 01550 | 10 | Solar | 05_14_60L1 | 02/20/2018 | 02/20/2018 | 6 | 6 | 0 | 02/28/2018 | 02/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2018 |  | 2/25/2019 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 10/17/2018 | Connected |  | N
National Grid | GARDNER | 685925 | 01440 | 11.52 | Solar | 05_14_74L4 | 04/17/2025 | 07/21/2025 | 7 | 2 | 5 | 07/22/2025 | 07/22/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 322879 | 02777 | 43.2 | Solar | 05_01_219W3 | 11/02/2020 | 11/13/2020 | 7 | 0 | 7 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 4/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2021 | Connected |  | N
National Grid | SALEM | 174500 | 01970 | 300 | Natural Gas | 05_01_27W4 | 11/17/2009 | 11/17/2009 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2010 |  | 10/31/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 9/18/2012 | 9/18/2012 | 7/7/2010 | Connected |  | N
National Grid | REVERE | 685196 | 02151 | 10 | Solar | 05_01_413L3 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 601448 | 01844 | 3.8 | Solar | 05_01_607W4 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | NEWBURY | 178549 | 01951 | 5 | Solar | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 22 | 0 | 22 | 04/27/2018 | 04/27/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 3/18/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  | 10/29/2018 | Connected |  | N
National Grid | LAWRENCE | 216823 | 01841 | 3.8 | Solar | 05_12_29W2 | 04/02/2019 | 04/23/2019 | 14 | 10 | 4 | 04/24/2019 | 04/24/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | LEOMINSTER | 195384 | 01453 | 499.9 | Solar | 05_12_7W2 | 09/12/2018 | 09/21/2018 | 5 | 0 | 5 | 09/24/2018 | 09/24/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 12/31/2020 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | WORCESTER | 629865 | 01605 | 6 | Solar | 05_14_43L4 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 01/09/2025 | 01/08/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 178380 | 01507 | 20 | Solar | 05_14_60L1 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 04/10/2018 | 04/10/2018 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2018 |  | 1/20/2019 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GARDNER | 688618 | 01440 | 3.8 | Solar | 05_14_74L4 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 09/25/2025 | 12/01/2025 | 68 | 0 | 68 |  |  | 12/3/2025 | Connected |  | N
National Grid | SWANSEA | 520020 | 02777 | 250 | Solar | 05_01_219W4 | 05/09/2023 | 07/25/2023 | 53 | 43 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SALEM | 174641 | 01970 | 82.8 | Solar | 05_01_27W4 | 12/04/2013 | 12/04/2013 | 5 | 0 | 5 | 12/11/2013 | 12/11/2013 | 941 | 6 | 935 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/04/2013 | 12/31/2016 | Y | EXP | 11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 701578 | 02151 | 4980 | Solar | 05_01_413L3 | 12/24/2025 | 02/03/2026 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2026 | 02/25/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 660589 | 01844 | 10 | Solar | 05_01_607W4 | 12/13/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/13/2024 | 2/21/2026 | Y | EXP | 365 | 05/08/2025 | 10/11/2025 | 157 | 0 | 157 |  |  | 11/21/2025 | Connected |  | N
National Grid | NEWBURY | 178548 | 01951 | 6 | Solar | 05_05_11W81 | 03/09/2018 | 03/09/2018 | 24 | 24 | 0 | 04/27/2018 | 04/27/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2018 |  | 3/18/2019 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | LAWRENCE | 230204 | 01841 | 0 | Solar | 05_12_29W2 | 05/22/2019 | 05/30/2019 | 4 | 0 | 4 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2019 | Connected |  | N
National Grid | LEOMINSTER | 192939 | 01453 | 7.6 | Solar | 05_12_7W2 | 08/08/2018 | 09/04/2018 | 12 | 0 | 12 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 631324 | 01605 | 10 | Solar | 05_14_43L4 | 08/08/2024 | 08/21/2024 | 5 | 0 | 5 | 08/22/2024 | 08/22/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 10/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 190362 | 01550 | 15.2 | Solar | 05_14_60L1 | 07/25/2018 | 08/28/2018 | 23 | 23 | 0 | 08/29/2018 | 08/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 |  | 9/6/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2019 | Connected |  | N
National Grid | GARDNER | 703871 | 01440 | 17.16 | Solar | 05_14_74L5 | 07/09/2025 | 07/31/2025 | 12 | 8 | 4 | 12/24/2025 | 12/24/2025 | 30 | 12 | 18 | 03/05/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 7/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | SWANSEA | 667799 | 02777 | 450 | Solar | 05_01_219W4 | 03/14/2025 | 04/28/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2025 | 05/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | SALEM | 175270 | 01970 | 336 | Solar | 05_01_27W4 | 06/16/2014 | 06/16/2014 | 7 | 0 | 7 | 06/27/2014 | 06/27/2014 | 687 | 32 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2014 |  | 11/28/2014 | N | EXP | 77 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 703963 | 02151 | 475 | Solar | 05_01_413L3 | 08/11/2025 | 09/17/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2025 | 10/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | METHUEN | 678299 | 01844 | 5.76 | Solar | 05_01_607W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 76 | 60 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 178609 | 01951 | 6 | Solar | 05_05_11W81 | 12/13/2017 | 12/13/2017 | 49 | 35 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 12/18/2018 | N | EXP | 295 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | METHUEN | 228309 | 01844 | 10 | Solar | 05_12_29W2 | 05/15/2019 | 05/22/2019 | 4 | 3 | 1 | 05/23/2019 | 05/23/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 |  | 7/30/2019 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | LEOMINSTER | 197019 | 01453 | 7.6 | Solar | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 633402 | 01605 | 5 | Solar | 05_14_43L4 | 08/19/2024 | 10/04/2024 | 31 | 25 | 6 | 10/07/2024 | 10/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 296240 | 01550 | 3.8 | Solar | 05_14_60L1 | 07/03/2020 | 07/08/2020 | 2 | 0 | 2 | 07/09/2020 | 07/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GARDNER | 748180 | 01440 | 16.72 | Solar | 05_14_74L5 | 02/02/2026 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 671681 | 02777 | 0 | Other | 05_01_219W4 | 01/08/2026 |  | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALEM | 176705 | 01970 | 6 | Solar | 05_01_27W4 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 368 | 0 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 358 | 05/19/2016 | 06/01/2016 | 8 | 0 | 8 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 711116 | 02151 | 150 | Solar | 05_01_413L3 | 08/11/2025 | 09/08/2025 | 19 | 9 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 699431 | 01841 | 18.48 | Solar | 05_01_607W4 | 07/02/2025 | 07/24/2025 | 14 | 10 | 4 | 07/25/2025 | 07/25/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | NEWBURY | 199525 | 01951 | 1000 | Solar | 05_05_11W81 | 10/26/2018 | 11/16/2018 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2018 | 12/18/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 278977 | 01832 | 9.36 | Solar | 05_12_29W2 | 03/05/2020 | 03/11/2020 | 3 | 0 | 3 | 03/12/2020 | 03/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 197013 | 01453 | 3 | Solar | 05_12_7W2 | 09/27/2018 | 10/17/2018 | 3 | 3 | 0 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 09/27/2018 | 5/20/2019 | Y | EXP | 213 | 02/12/2019 | 04/11/2019 | 58 | 0 | 58 |  |  | 4/27/2019 | Connected |  | N
National Grid | WORCESTER | 636570 | 01605 | 5.76 | Solar | 05_14_43L4 | 08/29/2024 | 09/23/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 08/29/2024 | 10/30/2025 | Y | EXP | 365 | 12/19/2024 | 03/03/2025 | 75 | 0 | 75 |  |  | 3/12/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 316180 | 01550 | 6 | Solar | 05_14_60L1 | 10/15/2020 | 10/20/2020 | 2 | 0 | 2 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/15/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2021 | Connected |  | N
National Grid | GARDNER | 751928 | 01440 | 11.5 | Solar | 05_14_74L5 | 02/18/2026 | 02/24/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SWANSEA | 678562 | 02777 | 420 | Solar | 05_01_219W4 | 06/18/2025 | 10/29/2025 | 91 | 82 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 11/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SALEM | 177829 | 01970 | 7.6 | Solar | 05_01_27W4 | 08/04/2017 | 08/04/2017 | 4 | 0 | 4 | 08/11/2017 | 08/11/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/12/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | REVERE | 741865 | 02151 | 5.76 | Solar | 05_01_413L3 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 707825 | 01844 | 18.81 | Solar | 05_01_607W4 | 07/28/2025 | 08/01/2025 | 4 | 0 | 4 | 08/04/2025 | 08/04/2025 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 315459 | 01951 | 998 | Solar | 05_05_11W81 | 02/22/2021 | 04/30/2021 | 48 | 39 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2021 | 06/15/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 286474 | 01844 | 3.8 | Solar | 05_12_29W2 | 04/17/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 | 04/17/2020 | 10/21/2021 | Y | EXP | 365 | 04/13/2021 | 05/03/2021 | 20 | 0 | 20 |  |  | 9/3/2021 | Connected |  | N
National Grid | LEOMINSTER | 196955 | 01453 | 3.8 | Solar | 05_12_7W2 | 11/26/2018 | 02/04/2019 | 49 | 44 | 5 | 02/05/2019 | 02/05/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 11/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 637943 | 01605 | 6.98 | Solar | 05_14_43L4 | 09/05/2024 | 10/16/2024 | 4 | 0 | 4 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/05/2024 | 11/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 344862 | 01550 | 7.6 | Solar | 05_14_60L1 | 03/03/2021 | 03/04/2021 | 0 | 0 | 0 | 03/05/2021 | 03/05/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2022 | Connected |  | N
National Grid | GARDNER | 177322 | 01440 | 7.6 | Solar | 05_14_74L5 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/3/2016 | 11/3/2016 | 11/7/2016 | Connected |  | N
National Grid | SWANSEA | 739118 | 02777 | 15.2 | Solar | 05_01_219W4 | 12/11/2025 | 12/22/2025 | 6 | 4 | 2 | 12/23/2025 | 12/23/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 178284 | 01970 | 684 | Solar | 05_01_27W4 | 03/28/2018 | 03/28/2018 | 17 | 11 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/2/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 742664 | 02151 | 11.4 | Solar | 05_01_413L3 | 12/30/2025 | 01/02/2026 | 2 | 0 | 2 | 01/05/2026 | 01/05/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 385049 | 01841 | 4920 | Solar | 05_01_609W1 | 10/29/2021 | 12/02/2021 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEWBURY | 349385 | 01951 | 7.6 | Solar | 05_05_11W81 | 04/05/2021 | 04/14/2021 | 6 | 0 | 6 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2021 | Connected |  | N
National Grid | METHUEN | 583402 | 01844 | 10 | Solar | 05_12_29W2 | 01/19/2024 | 02/13/2024 | 18 | 16 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/19/2024 | 3/1/2025 | Y | EXP | 365 | 05/15/2024 | 05/28/2024 | 14 | 0 | 14 |  |  | 5/31/2024 | Connected |  | N
National Grid | LEOMINSTER | 198416 | 01453 | 3.8 | Solar | 05_12_7W2 | 11/09/2018 | 11/20/2018 | 5 | 0 | 5 | 11/21/2018 | 11/21/2018 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 11/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2020 | Connected |  | N
National Grid | WORCESTER | 643784 | 01605 | 13.12 | Solar | 05_14_43L4 | 09/30/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 349237 | 01550 | 0 | Solar | 05_14_60L1 | 04/08/2021 | 04/27/2021 | 12 | 12 | 0 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 8/24/2022 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 177355 | 01473 | 7.6 | Solar | 05_14_74L5 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 |  | 2/21/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | SWANSEA | 175288 | 02777 | 225 | Solar | 05_01_219W4 | 11/06/2014 | 11/06/2014 | 5 | 0 | 5 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2014 |  | 4/1/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 12/19/2014 | 12/19/2014 | 10/22/2015 | Connected |  | N
National Grid | SALEM | 357062 | 01970 | 7.6 | Solar | 05_01_27W4 | 05/26/2021 | 06/03/2021 | 4 | 0 | 4 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 749054 | 02151 | 19.12 | Solar | 05_01_413L3 | 02/03/2026 |  | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 617857 | 01841 | 4999 | Solar | 05_01_609W1 | 08/14/2024 | 11/14/2024 | 65 | 55 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 05/09/2025 | 119 | 98 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEWBURY | 443975 | 01951 | 0 | Other | 05_05_11W81 | 11/09/2022 | 01/31/2023 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2023 | 03/02/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 632118 | 01832 | 10 | Solar | 05_12_29W2 | 08/23/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | LEOMINSTER | 198866 | 01453 | 7.6 | Solar | 05_12_7W2 | 10/19/2018 | 11/05/2018 | 7 | 1 | 6 | 11/06/2018 | 11/06/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 | 10/19/2018 | 1/27/2020 | Y | EXP | 365 | 06/05/2019 | 06/22/2019 | 17 | 0 | 17 |  |  | 1/16/2020 | Connected |  | N
National Grid | WORCESTER | 644259 | 01605 | 3.8 | Solar | 05_14_43L4 | 10/01/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 367210 | 01571 | 7.6 | Solar | 05_14_60L1 | 07/01/2021 | 11/01/2021 | 84 | 63 | 21 | 11/02/2021 | 11/02/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 |  | 10/31/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 177904 | 01452 | 20 | Solar | 05_14_74L5 | 08/15/2017 | 08/15/2017 | 15 | 15 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 8/20/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/14/2017 | Connected |  | N
National Grid | SWANSEA | 175419 | 02777 | 30 | Solar | 05_01_219W4 | 07/11/2014 | 07/11/2014 | 6 | 0 | 6 | 07/22/2014 | 07/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 11/28/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 7/29/2014 | 7/29/2014 | 12/18/2014 | Connected |  | N
National Grid | SALEM | 442781 | 01970 | 10 | Solar | 05_01_27W4 | 07/14/2022 | 07/18/2022 | 2 | 0 | 2 | 07/19/2022 | 07/19/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/14/2022 | 8/25/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 175014 | 02151 | 1500 | Solar | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 2 | 03/04/2014 | 03/07/2014 | 3 | 0 | 3 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | METHUEN | 708824 | 01844 | 7.6 | Solar | 05_01_609W1 | 09/08/2025 | 09/23/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/08/2025 | 11/7/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NEWBURY | 489747 | 01951 | 10 | Solar | 05_05_11W81 | 01/09/2023 | 01/11/2023 | 2 | 0 | 2 | 01/12/2023 | 01/12/2023 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 | 01/09/2023 | 5/3/2024 | Y | EXP | 365 | 04/11/2023 | 05/02/2023 | 22 | 0 | 22 |  |  | 6/21/2023 | Connected |  | Y
National Grid | METHUEN | 636021 | 01844 | 4.93 | Solar | 05_12_29W2 | 08/28/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2024 | Connected |  | N
National Grid | LEOMINSTER | 200168 | 01453 | 3.8 | Solar | 05_12_7W2 | 11/05/2018 | 11/20/2018 | 3 | 3 | 0 | 11/21/2018 | 11/21/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | WORCESTER | 645461 | 01605 | 7.54 | Solar | 05_14_43L4 | 10/11/2024 | 10/21/2024 | 2 | 0 | 2 | 10/22/2024 | 10/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 |  | 11/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 421113 | 01550 | 0 | Solar | 05_14_60L1 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  | 4/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | WESTMINSTER | 178343 | 01473 | 500 | Solar | 05_14_74L5 | 01/10/2018 | 01/10/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 | 05/10/2018 | 11/16/2018 | 133 | 109 | 24 | 03/12/2018 | 04/09/2018 | 15 | 0 | 15 |  | 11/16/2018 | 133 | 109 | 24 |  |  | 0 | 0 | 0 | 12/20/2018 |  | 11/15/2019 | N | STD | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 175892 | 02777 | 5 | Solar | 05_01_219W4 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 | 08/04/2015 | 8/10/2016 | Y | EXP | 357 | 05/24/2016 | 06/22/2016 | 19 | 0 | 19 | 8/19/2015 | 8/19/2015 | 8/29/2016 | Connected |  | N
National Grid | SALEM | 459363 | 01970 | 3.8 | Solar | 05_01_27W4 | 01/05/2023 |  | 213 | 213 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 175013 | 02151 | 1500 | Solar | 05_01_413L3 | 07/29/2011 | 07/29/2011 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 12/02/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 | 03/16/2012 | 04/23/2012 | 24 | 0 | 24 | 12/12/2012 | 07/29/2011 | 1/1/2013 | Y | STD | 2 |  |  | 0 | 0 | 0 | 4/24/2013 | 4/24/2013 | 4/24/2013 | Connected |  | N
National Grid | METHUEN | 716246 | 01844 | 3.8 | Solar | 05_01_609W1 | 09/03/2025 | 09/22/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 533802 | 01951 | 2400 | Solar | 05_05_11W81 | 07/24/2023 | 09/08/2023 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 09/18/2023 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 647623 | 01832 | 3.8 | Solar | 05_12_29W2 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | LEOMINSTER | 200027 | 01453 | 10 | Solar | 05_12_7W2 | 11/01/2018 | 11/21/2018 | 2 | 1 | 1 | 11/26/2018 | 11/26/2018 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/01/2018 | 7/17/2020 | Y | EXP | 365 | 07/26/2019 | 07/31/2019 | 5 | 0 | 5 |  |  | 7/13/2020 | Connected |  | N
National Grid | WORCESTER | 649010 | 01605 | 10 | Solar | 05_14_43L4 | 11/18/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 508264 | 01550 | 9.57 | Solar | 05_14_60L1 | 03/28/2023 | 03/30/2023 | 2 | 1 | 1 | 03/31/2023 | 03/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 5/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | WESTMINSTER | 193466 | 01473 | 15.2 | Solar | 05_14_74L5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 184325 | 02777 | 7.6 | Solar | 05_01_219W4 | 05/24/2018 | 05/24/2018 | 21 | 20 | 1 | 06/21/2018 | 06/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 582263 | 01970 | 10.44 | Solar | 05_01_27W4 | 01/09/2024 | 01/11/2024 | 3 | 1 | 2 | 01/12/2024 | 01/12/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | REVERE | 175096 | 02151 | 500 | Solar | 05_01_413L3 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 | 11/19/2012 | 11/19/2012 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 744618 | 01841 | 11.5 | Battery Add-On | 05_01_609W1 | 01/15/2026 | 01/21/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NEWBURY | 564941 | 01532 | 10 | Solar | 05_05_11W81 | 11/03/2023 | 12/12/2023 | 26 | 23 | 3 | 12/13/2023 | 12/13/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/03/2023 | 5/2/2025 | Y | EXP | 365 | 04/19/2024 | 05/17/2024 | 29 | 0 | 29 |  |  | 7/19/2024 | Connected |  | N
National Grid | HAVERHILL | 648716 | 01832 | 5.76 | Solar | 05_12_29W2 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | LEOMINSTER | 200644 | 01453 | 10 | Solar | 05_12_7W2 | 11/08/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 649801 | 01605 | 5.2 | Solar | 05_14_43L4 | 10/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/30/2024 | 1/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 520810 | 01550 | 0 | Other | 05_14_60L1 | 06/02/2023 | 06/22/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2023 | 08/14/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 296655 | 01452 | 7.6 | Solar | 05_14_74L5 | 06/18/2020 | 06/23/2020 | 2 | 0 | 2 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 194293 | 02777 | 250 | Solar | 05_01_219W4 | 08/24/2018 | 09/04/2018 | 3 | 0 | 3 | 09/05/2018 | 09/05/2018 | 304 | 56 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 623960 | 01970 | 3.8 | Solar | 05_01_27W4 | 07/10/2024 | 07/26/2024 | 2 | 0 | 2 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/10/2024 | 8/14/2025 | Y | EXP | 365 | 09/19/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 11/26/2024 | Connected |  | N
National Grid | REVERE | 175249 | 02151 | 1000 | Solar | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/12/2018 | 6/20/2018 | 7/26/2018 | Connected |  | N
National Grid | METHUEN | 747380 | 01844 | 21.638 | Solar | 05_01_609W1 | 01/28/2026 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 562469 | 01922 | 5 | Solar | 05_05_11W81 | 11/06/2023 | 11/28/2023 | 14 | 12 | 2 | 11/29/2023 | 11/29/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 672412 | 01832 | 5.76 | Solar | 05_12_29W2 | 02/17/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | Y
National Grid | LEOMINSTER | 203133 | 01453 | 7.6 | Solar | 05_12_7W2 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 651165 | 01605 | 6.825 | Solar | 05_14_43L4 | 10/31/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/31/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | DUDLEY | 603110 | 01571 | 46 | Solar | 05_14_60L1 | 04/10/2024 | 05/29/2024 | 27 | 25 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | HUBBARDSTON | 357875 | 01452 | 9.8 | Solar | 05_14_74L5 | 05/25/2021 | 05/26/2021 | 0 | 0 | 0 | 05/27/2021 | 05/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2021 |  | 8/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2022 | Connected |  | N
National Grid | SWANSEA | 245798 | 02777 | 7.6 | Solar | 05_01_219W4 | 10/09/2019 | 10/15/2019 | 2 | 0 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 09/16/2020 | 09/21/2020 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 623801 | 01970 | 5.76 | Solar | 05_01_27W4 | 07/10/2024 | 08/02/2024 | 4 | 3 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | REVERE | 175248 | 02151 | 1000 | Solar | 05_01_413L3 | 11/04/2014 | 11/04/2014 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 11/04/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 |  |  | 7/26/2018 | Connected |  | N
National Grid | METHUEN | 749034 | 01844 | 7.6 | Solar | 05_01_609W1 | 02/03/2026 | 02/06/2026 | 3 | 0 | 3 | 02/09/2026 | 02/09/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 569149 | 01950 | 15 | Solar | 05_05_11W81 | 11/06/2023 | 11/17/2023 | 9 | 6 | 3 | 11/20/2023 | 11/20/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 1/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2024 | Connected |  | N
National Grid | METHUEN | 725929 | 01844 | 5.76 | Solar | 05_12_29W2 | 10/13/2025 | 10/20/2025 | 7 | 5 | 2 | 11/10/2025 | 11/10/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 204942 | 01453 | 3.8 | Solar | 05_12_7W2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 142 | 0 | 142 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 652499 | 01605 | 9.5 | Solar | 05_14_43L4 | 11/06/2024 | 11/26/2024 | 4 | 1 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DUDLEY | 613820 | 01571 | 5.22 | Solar | 05_14_60L1 | 05/28/2024 | 06/04/2024 | 1 | 0 | 1 | 06/05/2024 | 06/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 375924 | 01452 | 9.8 | Solar | 05_14_74L5 | 08/26/2021 | 12/07/2021 | 3 | 0 | 3 | 09/01/2021 | 09/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2022 | Connected |  | N
National Grid | SWANSEA | 377934 | 02777 | 700 | Natural Gas | 05_01_219W4 | 03/10/2022 | 05/26/2022 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2022 | 11/18/2022 | 120 | 101 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 633504 | 01970 | 5 | Solar | 05_01_27W4 | 08/19/2024 | 08/22/2024 | 2 | 1 | 1 | 08/23/2024 | 08/23/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/19/2024 | 10/6/2025 | Y | EXP | 365 | 12/07/2024 | 04/24/2025 | 139 | 0 | 139 |  |  | 5/14/2025 | Connected |  | N
National Grid | REVERE | 175245 | 02151 | 1000 | Solar | 05_01_413L3 | 08/28/2014 | 08/28/2014 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/07/2014 | 21 | 21 | 0 |  |  | 0 | 0 | 0 | 01/20/2017 | 02/17/2017 | 20 | 0 | 20 | 7/11/2017 | 08/28/2014 | 7/31/2018 | Y | STD | 385 | 12/27/2017 | 05/08/2018 | 132 | 0 | 132 | 6/11/2018 | 6/20/2018 | 7/18/2018 | Connected |  | N
National Grid | METHUEN | 174268 | 01844 | 300 | Solar | 05_01_609W1 | 12/26/2011 | 12/26/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 632418 | 01950 | 10 | Solar | 05_05_11W81 | 08/13/2024 | 08/16/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 29 | 5 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 08/13/2024 | 3/4/2026 | Y | EXP | 365 | 03/27/2025 | 04/17/2025 | 22 | 0 | 22 |  |  | 4/22/2025 | Connected |  | N
National Grid | HAVERHILL | 736817 | 01832 |  | Battery Add-On | 05_12_29W3 | 12/03/2025 | 12/04/2025 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 234798 | 01453 | 7.6 | Solar | 05_12_7W2 | 07/10/2019 | 07/18/2019 | 5 | 0 | 5 | 07/19/2019 | 07/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 7/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | WORCESTER | 657188 | 01605 | 15.2 | Solar | 05_14_43L4 | 11/26/2024 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | DUDLEY | 624569 | 01571 | 10 | Solar | 05_14_60L1 | 07/26/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/25/2025 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | WESTMINSTER | 401112 | 01473 | 0 | Other | 05_14_74L5 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 427472 | 02777 | 0 | Other | 05_01_219W4 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 643734 | 01905 | 7.6 | Solar | 05_01_27W4 | 10/01/2024 | 11/18/2024 | 18 | 13 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | REVERE | 175794 | 02151 | 1000 | Solar | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174322 | 01844 | 1125 | Solar | 05_01_609W1 | 01/13/2012 | 01/13/2012 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2012 | 05/23/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/8/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 654991 | 01951 | 3.8 | Solar | 05_05_11W81 | 11/19/2024 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | HAVERHILL | 176276 | 01832 | 79 | Solar | 05_12_29W3 | 05/04/2015 | 05/04/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 |  | Withdrawn |  | N
National Grid | LEOMINSTER | 301272 | 01453 | 7.6 | Solar | 05_12_7W2 | 08/03/2020 | 08/05/2020 | 1 | 0 | 1 | 08/06/2020 | 08/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 |  | 8/4/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 660661 | 01605 | 7.6 | Solar | 05_14_43L4 | 12/14/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 627652 | 01550 | 5.76 | Solar | 05_14_60L1 | 07/25/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 9/4/2025 | Y | EXP | 365 | 10/11/2024 | 10/11/2024 | 1 | 0 | 1 |  |  | 11/4/2024 | Connected |  | N
National Grid | HUBBARDSTON | 565286 | 01452 | 11.97 | Solar | 05_14_74L5 | 01/05/2024 | 01/08/2024 | 1 | 0 | 1 | 01/09/2024 | 01/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 | 01/05/2024 | 2/14/2025 | Y | EXP | 365 | 06/28/2024 | 07/01/2024 | 4 | 0 | 4 |  |  | 8/16/2024 | Connected |  | N
National Grid | SWANSEA | 429601 | 02777 | 15.2 | Solar | 05_01_219W4 | 05/11/2022 | 05/16/2022 | 4 | 3 | 1 | 05/17/2022 | 05/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | LYNN | 647137 | 01905 | 3.8 | Solar | 05_01_27W4 | 10/23/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | REVERE | 175793 | 02151 | 760 | Solar | 05_01_413L3 | 09/16/2015 | 09/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2015 | 10/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/26/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174685 | 01844 | 7.6 | Solar | 05_01_609W1 | 03/09/2011 | 03/09/2011 | 423 | 60 | 363 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 655862 | 01951 | 10 | Solar | 05_05_11W81 | 11/21/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | METHUEN | 176604 | 01844 | 4.25 | Solar | 05_12_29W3 | 12/30/2015 | 12/30/2015 | 3 | 3 | 0 | 01/05/2016 | 01/05/2016 | 270 | 0 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/4/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 311805 | 01453 | 7.6 | Solar | 05_12_7W2 | 09/29/2020 | 10/02/2020 | 2 | 0 | 2 | 10/05/2020 | 10/05/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 661675 | 01605 | 10 | Solar | 05_14_43L4 | 12/20/2024 | 01/22/2025 | 5 | 1 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/20/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 629796 | 01550 | 3.8 | Solar | 05_14_60L1 | 08/19/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 08/19/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | WESTMINSTER | 569971 | 01473 | 16.53 | Solar | 05_14_74L5 | 11/08/2023 | 11/21/2023 | 8 | 5 | 3 | 11/22/2023 | 11/22/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 439536 | 02777 | 18.56 | Solar | 05_01_219W4 | 06/23/2022 | 07/12/2022 | 12 | 10 | 2 | 07/13/2022 | 07/13/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2022 | Connected |  | Y
National Grid | LYNN | 680013 | 01905 | 15.76 | Solar | 05_01_27W4 | 03/24/2025 | 03/26/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | REVERE | 175874 | 02151 | 25 | Solar | 05_01_413L3 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 382 | 0 | 382 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 12/31/2016 | N | EXP | 655 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174973 | 01844 | 91.2 | Solar | 05_01_609W1 | 09/26/2011 | 09/26/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 666526 | 01951 | 7.6 | Solar | 05_05_11W81 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/05/2025 | 4/23/2026 | Y | EXP | 365 | 05/29/2025 | 08/01/2025 | 65 | 0 | 65 |  |  | 8/11/2025 | Connected |  | N
National Grid | METHUEN | 177962 | 01844 | 3.8 | Solar | 05_12_29W3 | 10/24/2017 | 10/24/2017 | 15 | 14 | 1 | 11/27/2017 | 11/27/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 10/31/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 318712 | 01453 | 7.6 | Solar | 05_12_7W2 | 10/27/2020 | 11/02/2020 | 3 | 0 | 3 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 662855 | 01605 | 7.6 | Solar | 05_14_43L4 | 12/27/2024 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 642862 | 01550 | 7.6 | Solar | 05_14_60L1 | 09/26/2024 | 09/30/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 642704 | 01473 | 10 | Solar | 05_14_74L5 | 09/25/2024 | 10/02/2024 | 5 | 0 | 5 | 10/03/2024 | 10/03/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/25/2024 | 12/3/2025 | Y | EXP | 365 | 03/15/2025 | 03/17/2025 | 3 | 0 | 3 |  |  | 5/22/2025 | Connected |  | N
National Grid | SWANSEA | 492026 | 02777 | 450 | Solar | 05_01_219W4 | 03/17/2023 |  | 246 | 236 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 678914 | 01905 | 3.8 | Solar | 05_01_27W5 | 03/18/2025 | 03/26/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 03/18/2025 | 6/16/2026 | Y | EXP | 365 | 08/05/2025 | 09/30/2025 | 57 | 0 | 57 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 175996 | 02151 | 18.75 | Solar | 05_01_413L3 | 06/11/2015 | 06/11/2015 | 6 | 6 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/17/2016 | N | EXP | 352 |  |  | 0 | 0 | 0 | 11/6/2015 | 11/6/2015 | 11/6/2015 | Connected |  | N
National Grid | METHUEN | 175523 | 01844 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | NEWBURY | 671235 | 01951 | 3.8 | Solar | 05_05_11W81 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | METHUEN | 189736 | 01844 | 7.6 | Solar | 05_12_29W3 | 07/02/2018 | 07/02/2018 | 2 | 0 | 2 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/02/2018 | 11/15/2019 | Y | EXP | 463 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | LEOMINSTER | 462753 | 01453 | 7.6 | Solar | 05_12_7W2 | 10/06/2022 | 10/12/2022 | 4 | 1 | 3 | 10/13/2022 | 10/13/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 669208 | 01604 | 3.8 | Solar | 05_14_43L4 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 | 02/03/2025 | 4/12/2026 | Y | EXP | 365 | 05/15/2025 | 11/03/2025 | 172 | 3 | 169 |  |  | 7/29/2025 | Connected |  | N
National Grid | CHARLTON | 645437 | 01507 | 23 | Solar | 05_14_60L1 | 10/07/2024 | 10/16/2024 | 5 | 3 | 2 | 10/17/2024 | 10/17/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WESTMINSTER | 643144 | 01473 | 5.76 | Solar | 05_14_74L5 | 09/26/2024 | 11/09/2024 | 13 | 11 | 2 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 | 12/31/2024 | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/30/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 09/26/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | SWANSEA | 652365 | 02777 | 10 | Solar | 05_01_219W4 | 11/14/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 689732 | 01905 | 5.76 | Solar | 05_01_27W5 | 05/05/2025 | 05/16/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | REVERE | 176639 | 02151 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | METHUEN | 175522 | 01844 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 2/13/2018 | 2/13/2018 | 3/19/2018 | Connected |  | N
National Grid | NEWBURY | 700720 | 01951 | 15.2 | Solar | 05_05_11W81 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 220688 | 01832 | 3 | Solar | 05_12_29W3 | 04/24/2019 | 04/29/2019 | 4 | 4 | 0 | 04/30/2019 | 04/30/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 503442 | 01453 | 10 | Solar | 05_12_7W2 | 03/19/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 25 | 0 | 25 | 05/08/2023 | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 06/14/2023 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/31/2024 | N | EXP | 365 | 08/01/2023 | 07/31/2023 | 0 | 0 | 0 |  |  | 8/8/2023 | Connected |  | Y
National Grid | WORCESTER | 672120 | 01604 | 7.6 | Solar | 05_14_43L4 | 02/14/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 651238 | 01550 | 17.6 | Solar | 05_14_60L1 | 11/04/2024 | 01/15/2025 | 40 | 36 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/4/2026 | Y | EXP | 365 | 08/26/2025 | 09/03/2025 | 9 | 0 | 9 |  |  | 9/23/2025 | Connected |  | N
National Grid | WESTMINSTER | 648578 | 01473 | 3.8 | Solar | 05_14_74L5 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | SWANSEA | 679496 | 02777 | 5.76 | Solar | 05_01_219W4 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 706568 | 01904 | 15.76 | Solar | 05_01_27W5 | 07/23/2025 | 07/29/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 176638 | 02151 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | METHUEN | 175521 | 01844 | 499 | Solar | 05_01_609W1 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2014 | 09/04/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 | 07/25/2014 | 3/31/2018 | Y | STD | 974 | 05/09/2017 | 03/19/2018 | 198 | 0 | 198 | 12/5/2017 | 12/5/2017 | 3/19/2018 | Connected |  | N
National Grid | NEWBURY | 707625 | 01951 | 11.4 | Solar | 05_05_11W81 | 07/27/2025 | 08/21/2025 | 18 | 15 | 3 | 08/22/2025 | 08/22/2025 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 | 07/27/2025 | 10/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | HAVERHILL | 242778 | 01832 | 3.8 | Solar | 05_12_29W3 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 516902 | 01453 | 6.38 | Solar | 05_12_7W2 | 08/07/2023 |  | 84 | 26 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 673315 | 01604 | 10 | Solar | 05_14_43L4 | 02/20/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 652089 | 01550 | 2.9 | Solar | 05_14_60L1 | 11/06/2024 | 01/22/2025 | 5 | 3 | 2 | 01/23/2025 | 01/23/2025 | 70 | 25 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 650791 | 01473 | 10 | Solar | 05_14_74L5 | 10/31/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 738314 | 02777 | 17.86 | Solar | 05_01_219W4 | 12/08/2025 | 12/10/2025 | 2 | 0 | 2 | 12/11/2025 | 12/11/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 711138 | 01905 | 8 | Solar | 05_01_27W5 | 08/18/2025 | 09/05/2025 | 17 | 13 | 4 | 10/03/2025 | 10/03/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/18/2025 | 12/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 176637 | 02151 | 1000 | Solar | 05_01_413L3 | 12/29/2015 | 12/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/14/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2016 | 12/29/2015 | 1/9/2017 | Y | STD | 245 | 09/11/2017 | 11/07/2017 | 35 | 0 | 35 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | METHUEN | 175773 | 01844 | 480 | Solar | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 175614 | 01951 | 0 | Solar | 05_05_11W82 | 12/16/2014 | 12/16/2014 | 4 | 2 | 2 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2015 | 12/16/2014 | 4/30/2015 | Y | EXP | 97 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Terminated |  | N
National Grid | METHUEN | 255456 | 01844 | 7.6 | Solar | 05_12_29W3 | 10/07/2019 | 10/08/2019 | 0 | 0 | 0 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2019 |  | 10/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | Connected |  | N
National Grid | LEOMINSTER | 530131 | 01453 | 8.12 | Solar | 05_12_7W2 | 07/12/2023 | 08/02/2023 | 16 | 15 | 1 | 08/03/2023 | 08/03/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 677373 | 01604 | 5.76 | Solar | 05_14_43L4 | 03/12/2025 | 03/26/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 655001 | 01550 | 5.2 | Solar | 05_14_60L1 | 11/19/2024 | 12/09/2024 | 6 | 3 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | HUBBARDSTON | 650671 | 01452 | 10 | Solar | 05_14_74L5 | 11/04/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | SOMERSET | 495510 | 02726 | 1600 | Solar | 05_01_219W5 | 04/16/2023 | 06/29/2023 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/26/2023 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 731667 | 01905 | 7.6 | Solar | 05_01_27W5 | 11/12/2025 | 01/26/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 176768 | 02151 | 1872 | Solar | 05_01_413L3 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 05/31/2016 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/7/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175772 | 01841 | 480 | Solar | 05_01_609W1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 562551 | 01951 | 3125 | Solar | 05_05_11W82 | 02/20/2024 | 07/22/2024 | 105 | 96 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2024 | 09/04/2024 | 31 | 18 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 02/20/2024 | 4/14/2027 | Y | STD | 42 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | HAVERHILL | 286083 | 01832 | 3.8 | Solar | 05_12_29W3 | 05/08/2020 | 05/27/2020 | 12 | 12 | 0 | 05/28/2020 | 05/28/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 05/08/2020 | 5/26/2021 | Y | EXP | 365 | 12/05/2020 | 01/06/2021 | 32 | 0 | 32 |  |  | 1/7/2021 | Connected |  | N
National Grid | LEOMINSTER | 591484 | 01453 | 3.8 | Solar | 05_12_7W2 | 02/27/2024 | 04/11/2024 | 30 | 25 | 5 | 04/12/2024 | 04/12/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 678663 | 01604 | 15.96 | Solar | 05_14_43L4 | 03/18/2025 | 04/07/2025 | 14 | 9 | 5 | 04/08/2025 | 04/08/2025 | 33 | 19 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 655842 | 01550 | 3.8 | Solar | 05_14_60L1 | 11/20/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/20/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | HUBBARDSTON | 651903 | 01452 | 5.76 | Solar | 05_14_74L5 | 11/25/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 176008 | 02777 | 6 | Solar | 05_01_219W5 | 08/13/2015 | 08/13/2015 | 2 | 2 | 0 | 08/18/2015 | 08/18/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 735538 | 01904 | 10 | Solar | 05_01_27W5 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 177748 | 02151 | 1500 | Solar | 05_01_413L3 | 05/26/2017 | 06/09/2017 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/07/2017 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2018 | 05/26/2017 | 10/31/2020 | Y | STD | 1174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175836 | 01841 | 990 | Solar | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 639826 | 01951 | 240 | Solar | 05_05_11W82 | 04/02/2025 | 04/29/2025 | 18 | 9 | 9 | 04/30/2025 | 04/30/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 7/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 310786 | 01844 | 7.68 | Solar | 05_12_29W3 | 10/19/2020 | 10/20/2020 | 1 | 1 | 0 | 10/21/2020 | 10/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 | 10/19/2020 | 4/21/2022 | Y | EXP | 365 | 01/20/2021 | 03/12/2021 | 51 | 0 | 51 |  |  | 10/14/2021 | Connected |  | N
National Grid | LEOMINSTER | 684928 | 01453 | 7.6 | Solar | 05_14_43L4 | 04/14/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/14/2025 | 7/8/2026 | Y | EXP | 365 | 09/25/2025 | 10/30/2025 | 36 | 0 | 36 |  |  | 11/7/2025 | Connected |  | N
National Grid | WORCESTER | 659314 | 01604 | 7.6 | Solar | 05_14_60L1 | 12/09/2024 | 01/03/2025 | 16 | 11 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 657128 | 01550 | 7.6 | Solar | 05_14_74L5 | 11/26/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | HUBBARDSTON | 176033 | 01452 | 6.45 | Solar | 05_01_219W5 | 06/19/2015 | 06/19/2015 | 2 | 2 | 0 | 06/23/2015 | 06/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 6/24/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 4/7/2016 | 4/7/2016 | 4/13/2016 | Connected |  | N
National Grid | SOMERSET | 746935 | 02726 | 11.4 | Solar | 05_01_27W5 | 01/22/2026 | 01/28/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 | 01/22/2026 | 2/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LYNN | 178534 | 01904 | 3744 | Solar | 05_01_413L3 | 12/05/2017 | 12/05/2017 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 | 12/05/2017 | 12/31/2020 | Y | STD | 784 | 06/12/2020 | 11/23/2020 | 165 | 5 | 160 | 12/14/2020 | 12/22/2020 | 12/31/2020 | Connected |  | N
National Grid | REVERE | 175834 | 02151 | 990 | Solar | 05_01_609W1 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 725092 | 01844 | 7.6 | Solar | 05_05_11W82 | 10/08/2025 | 10/30/2025 | 3 | 0 | 3 | 12/10/2025 | 12/10/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 378521 | 01951 | 5.76 | Solar | 05_12_29W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2021 |  | 11/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | METHUEN | 600033 | 01844 | 10 | Solar | 05_12_7W2 | 03/29/2024 | 04/15/2024 | 11 | 8 | 3 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/29/2024 | 5/14/2025 | Y | EXP | 365 | 07/31/2024 | 08/30/2024 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 684767 | 01453 | 11.4 | Solar | 05_14_43L4 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 8/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | WORCESTER | 705439 | 01604 | 5.85 | Solar | 05_14_60L1 | 07/21/2025 | 08/06/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 665424 | 01550 | 3.8 | Solar | 05_14_74L5 | 01/13/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/13/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HUBBARDSTON | 176908 | 01452 | 231 | Solar | 05_01_219W5 | 03/07/2016 | 03/07/2016 | 4 | 4 | 0 | 03/11/2016 | 03/11/2016 | 425 | 14 | 411 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2016 |  | 3/12/2017 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 750555 | 02726 | 3.8 | Solar | 05_01_27W5 | 02/11/2026 | 02/17/2026 | 1 | 0 | 1 | 02/26/2026 | 02/26/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 194187 | 01905 | 333 | Solar | 05_01_413L3 | 08/23/2018 | 08/23/2018 | 0 | 0 | 0 | 08/24/2018 | 08/24/2018 | 20 | 19 | 1 | 11/15/2018 | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  | 03/11/2019 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176313 | 02151 | 96 | Solar | 05_01_609W1 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 | 05/11/2015 | 05/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2015 |  | 10/30/2015 | N | EXP | 17 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/10/2016 | Connected |  | N
National Grid | LAWRENCE | 172587 | 01841 | 3.8 | Solar | 05_05_11W82 | 05/22/2018 | 05/22/2018 | 11 | 2 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 | 05/22/2018 | 7/12/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2019 | Connected |  | N
National Grid | NEWBURY | 488328 | 01950 | 6 | Solar | 05_12_29W3 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 | 01/10/2023 | 6/13/2024 | Y | EXP | 365 | 06/09/2023 | 06/09/2023 | 1 | 0 | 1 |  |  | 7/11/2023 | Connected |  | N
National Grid | HAVERHILL | 604225 | 01832 | 3.48 | Solar | 05_12_7W2 | 04/16/2024 |  | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 685249 | 01453 | 7.6 | Solar | 05_14_43L4 | 04/15/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 694244 | 01604 | 22.8 | Solar | 05_14_60L2 | 05/27/2025 | 06/16/2025 | 13 | 11 | 2 | 06/17/2025 | 06/17/2025 | 19 | 0 | 19 | 07/24/2025 | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 08/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 672317 | 01550 | 10 | Solar | 05_14_74L5 | 02/16/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | HUBBARDSTON | 176925 | 01452 | 500 | Solar | 05_01_219W5 | 11/20/2015 | 11/20/2015 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/06/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 | 8/2/2016 | 11/20/2015 | 4/27/2018 | Y | STD | 633 | 10/23/2017 | 03/02/2018 | 83 | 0 | 83 | 4/11/2018 | 4/11/2018 | 4/27/2018 | Connected |  | N
National Grid | SOMERSET | 753948 | 02726 | 16.403 | Solar | 05_01_27W5 | 03/02/2026 |  | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LYNN | 241223 | 01904 | 400 | Solar | 05_01_413L3 | 04/14/2020 | 05/11/2020 | 17 | 11 | 6 |  |  | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176505 | 02151 | 540 | Solar | 05_01_609W1 | 03/24/2016 | 03/29/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2016 | 05/26/2016 | 41 | 37 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 03/24/2016 | 12/31/2018 | Y | STD | 746 | 12/12/2018 | 01/02/2019 | 21 | 0 | 21 |  |  | 12/31/2018 | Connected |  | N
National Grid | METHUEN | 176184 | 01844 | 1143 | Solar | 05_05_11W82 | 08/28/2015 | 08/28/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 12/17/2015 | 71 | 37 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2016 | 08/28/2015 | 9/6/2016 | Y | STD | 138 | 08/11/2016 | 11/07/2016 | 60 | 0 | 60 | 6/27/2017 | 6/27/2017 | 5/17/2017 | Connected |  | N
National Grid | BYFIELD | 573455 | 01922 | 5.8 | Solar | 05_12_29W3 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 | 12/20/2023 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 11/18/2025 | 435 | 0 | 435 |  |  | 11/25/2025 | Connected |  | N
National Grid | HAVERHILL | 613662 | 01832 | 11.4 | Solar | 05_12_7W2 | 05/29/2024 | 06/11/2024 | 6 | 4 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 | 05/29/2024 | 8/6/2025 | Y | EXP | 365 | 08/21/2024 | 10/03/2024 | 44 | 0 | 44 |  |  | 2/8/2025 | Connected |  | N
National Grid | LEOMINSTER | 704124 | 01453 | 7.6 | Solar | 05_14_43L4 | 07/10/2025 | 07/25/2025 | 3 | 0 | 3 | 08/06/2025 | 08/06/2025 | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176109 | 01604 | 47.1 | Solar | 05_14_60L2 | 06/26/2015 | 06/26/2015 | 2 | 2 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 |  | 7/1/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/22/2015 | 7/22/2015 | 11/3/2015 | Connected |  | N
National Grid | SOUTHBRIDGE | 679744 | 01550 | 13.8 | Solar | 05_14_74L5 | 03/21/2025 | 04/01/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2025 | 03/21/2025 | 5/30/2026 | Y | EXP | 365 | 06/13/2025 | 08/22/2025 | 71 | 0 | 71 |  |  | 9/12/2025 | Connected |  | N
National Grid | WESTMINSTER | 177974 | 01473 | 6 | Solar | 05_01_219W5 | 06/27/2017 | 06/27/2017 | 37 | 36 | 1 | 08/18/2017 | 08/18/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/2/2018 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176244 | 02726 | 96 | Solar | 05_01_27W5 | 04/30/2015 | 04/30/2015 | 1 | 1 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 10/30/2015 | N | EXP | 171 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 12/2/2016 | Connected |  | N
National Grid | LYNN | 273618 | 01904 | 5000 | Other | 05_01_413L3 | 03/03/2020 | 03/17/2020 | 10 | 7 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176744 | 02151 | 2000 | Solar | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 176875 | 01844 | 7.6 | Solar | 05_05_11W82 | 03/02/2016 | 03/02/2016 | 30 | 30 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 03/02/2016 | 3/7/2017 | Y | EXP | 315 | 09/06/2016 | 09/21/2016 | 11 | 0 | 11 | 11/4/2016 | 11/4/2016 | 11/9/2016 | Connected |  | N
National Grid | NEWBURY | 574706 | 01951 | 3.8 | Solar | 05_12_29W3 | 12/01/2023 | 12/06/2023 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | HAVERHILL | 616866 | 01832 | 3 | Solar | 05_12_7W2 | 06/10/2024 |  | 18 | 16 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 725772 | 01453 | 15.2 | Solar | 05_14_43L4 | 10/10/2025 | 10/27/2025 | 9 | 6 | 3 | 10/28/2025 | 10/28/2025 | 53 | 41 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177160 | 01604 | 32 | Solar | 05_14_60L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2016 |  | 11/2/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/21/2017 | 3/21/2017 | 3/21/2017 | Connected |  | N
National Grid | SOUTHBRIDGE | 706445 | 01550 | 7.6 | Solar | 05_14_74L5 | 07/22/2025 | 08/28/2025 | 1 | 0 | 1 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | HUBBARDSTON | 178765 | 01452 | 495 | Solar | 05_01_219W5 | 07/29/2013 | 07/29/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2013 | 03/03/2014 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2014 |  | 1/31/2014 | N | STD | 41 |  |  | 0 | 0 | 0 | 7/14/2014 | 7/14/2014 | 7/24/2014 | Connected |  | N
National Grid | SOMERSET | 209675 | 02726 | 7.6 | Solar | 05_01_27W5 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 02/21/2019 | 10/10/2019 | Y | EXP | 223 | 05/30/2019 | 07/15/2019 | 46 | 0 | 46 |  |  | 8/27/2019 | Connected |  | N
National Grid | LYNN | 282071 | 01904 | 4950 | Other | 05_01_413L3 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/10/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 176743 | 02151 | 2200 | Solar | 05_01_609W1 | 11/02/2015 | 11/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/04/2015 | 12/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 178007 | 01841 | 15 | Solar | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2017 |  | 5/3/2018 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/7/2017 | Connected |  | N
National Grid | BYFIELD | 585391 | 01922 | 2.03 | Solar | 05_12_29W3 | 01/29/2024 | 01/30/2024 | 1 | 0 | 1 | 01/31/2024 | 01/31/2024 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 623418 | 01844 | 4.64 | Solar | 05_12_7W2 | 07/09/2024 | 07/31/2024 | 11 | 8 | 3 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 728924 | 01453 | 5.76 | Solar | 05_14_43L4 | 10/24/2025 | 10/27/2025 | 10 | 8 | 2 | 12/09/2025 | 12/09/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | WORCESTER | 270193 | 01604 | 10 | Solar | 05_14_60L2 | 01/06/2020 | 01/07/2020 | 0 | 0 | 0 | 01/08/2020 | 01/08/2020 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 1/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 7/9/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 712554 | 01550 | 17.6 | Solar | 05_14_74L5 | 08/25/2025 | 08/26/2025 | 1 | 0 | 1 | 08/27/2025 | 08/27/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | HUBBARDSTON | 186058 | 01452 | 4600 | Solar | 05_01_219W5 | 06/28/2018 | 06/28/2018 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 6/28/2021 | N | STD | 613 | 12/04/2020 | 06/10/2021 | 188 | 0 | 188 |  |  | 6/21/2021 | Connected |  | N
National Grid | SWANSEA | 210574 | 02777 | 10 | Solar | 05_01_27W5 | 03/14/2019 | 03/15/2019 | 0 | 0 | 0 | 03/18/2019 | 03/18/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 | 03/14/2019 | 11/19/2019 | Y | EXP | 243 | 05/21/2019 | 05/29/2019 | 8 | 0 | 8 |  |  | 6/19/2019 | Connected |  | N
National Grid | LYNN | 300622 | 01905 | 0 | Other | 05_01_413L3 | 09/22/2020 | 10/01/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2020 | 10/29/2020 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 177289 | 02151 | 174 | Hydro | 05_01_609W1 | 06/17/2016 | 07/06/2016 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2016 | 09/06/2016 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/17/2016 | 9/25/2020 | Y | STD | 1176 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | METHUEN | 178006 | 01844 | 20 | Solar | 05_05_11W82 | 04/28/2017 | 04/28/2017 | 10 | 10 | 0 | 05/12/2017 | 05/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2017 |  | 5/3/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/8/2017 | Connected |  | N
National Grid | BYFIELD | 588850 | 01922 | 5 | Solar | 05_12_29W3 | 02/23/2024 | 03/06/2024 | 9 | 8 | 1 | 03/07/2024 | 03/07/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 6/24/2025 | Y | EXP | 365 | 07/25/2024 | 10/30/2024 | 98 | 0 | 98 |  |  | 11/14/2024 | Connected |  | N
National Grid | METHUEN | 632337 | 01844 | 6 | Solar | 05_12_7W2 | 08/13/2024 | 08/30/2024 | 2 | 0 | 2 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | LANCASTER | 547085 | 01523 | 50 | Solar | 05_14_43L6 | 11/14/2023 | 02/07/2024 | 57 | 47 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 1/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 291579 | 01604 | 10 | Solar | 05_14_60L2 | 06/15/2020 | 06/18/2020 | 3 | 2 | 1 | 06/19/2020 | 06/19/2020 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 6/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 590405 | 01550 | 25 | Solar | 05_14_74L6 | 02/15/2024 | 06/24/2024 | 87 | 86 | 1 | 06/25/2024 | 06/25/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/1/2026 | N | EXP | 7 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTMINSTER | 373151 | 01473 | 7.6 | Solar | 05_01_219W5 | 08/18/2021 | 08/31/2021 | 8 | 3 | 5 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 243356 | 02777 | 3.8 | Solar | 05_01_27W5 | 07/24/2019 | 07/29/2019 | 2 | 0 | 2 | 07/30/2019 | 07/30/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2019 | 07/24/2019 | 7/23/2020 | Y | EXP | 365 | 04/17/2020 | 06/09/2020 | 53 | 0 | 53 |  |  | 6/25/2020 | Connected |  | N
National Grid | LYNN | 307951 | 01905 | 9.6 | Solar | 05_01_413L3 | 08/20/2020 | 08/21/2020 | 0 | 0 | 0 | 08/24/2020 | 08/24/2020 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2020 | 08/20/2020 | 11/2/2021 | Y | EXP | 365 | 03/11/2021 | 03/15/2021 | 4 | 0 | 4 |  |  | 4/12/2021 | Connected |  | N
National Grid | REVERE | 177715 | 02151 | 4686 | Solar | 05_01_609W1 | 07/26/2017 | 10/06/2017 | 51 | 51 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2017 | 10/25/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 07/26/2017 | 10/31/2022 | Y | STD | 273 | 08/26/2022 | 10/12/2022 | 48 | 0 | 48 | 10/13/2022 | 11/4/2022 | 11/18/2022 | Connected |  | N
National Grid | HAVERHILL | 263922 | 01832 | 8.7 | Solar | 05_05_11W82 | 11/15/2019 | 11/18/2019 | 0 | 0 | 0 | 11/19/2019 | 11/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2019 | 11/15/2019 | 7/22/2020 | Y | EXP | 365 | 01/10/2020 | 02/26/2020 | 46 | 0 | 46 |  |  | 2/27/2020 | Connected |  | N
National Grid | BYFIELD | 595104 | 01922 | 3.8 | Solar | 05_12_29W3 | 04/09/2024 | 04/10/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/09/2024 | 5/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | LAWRENCE | 642706 | 01840 | 5.76 | Solar | 05_12_7W2 | 09/25/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 68 | 44 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | LEOMINSTER | 744884 | 01453 | 15.2 | Solar | 05_14_43L6 | 01/12/2026 | 02/10/2026 | 19 | 15 | 4 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 347069 | 01604 | 8.7 | Solar | 05_14_60L2 | 04/19/2021 | 04/22/2021 | 2 | 0 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 7/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | DUDLEY | 605450 | 01571 | 11.4 | Solar | 05_14_74L6 | 04/24/2024 | 07/19/2024 | 39 | 39 | 0 | 07/22/2024 | 07/22/2024 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 04/24/2024 | 10/10/2025 | Y | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTMINSTER | 438321 | 01473 | 5.22 | Solar | 05_01_219W5 | 06/21/2022 | 06/23/2022 | 2 | 1 | 1 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/21/2022 | 4/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | SWANSEA | 369971 | 02777 | 7.6 | Solar | 05_01_27W5 | 07/15/2021 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 318399 | 01905 | 19.2 | Solar | 05_01_413L3 | 10/09/2020 |  | 40 | 39 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 178022 | 02151 | 500 | Solar | 05_01_609W1 | 08/29/2017 | 09/13/2017 | 8 | 8 | 0 |  |  | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 271016 | 01832 | 999 | Solar | 05_05_11W82 | 01/06/2020 | 01/17/2020 | 9 | 7 | 2 |  |  | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BYFIELD | 602833 | 01922 | 3.8 | Solar | 05_12_29W3 | 04/10/2024 | 04/11/2024 | 1 | 0 | 1 | 04/12/2024 | 04/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 04/10/2024 | 5/18/2025 | Y | EXP | 365 | 08/22/2024 | 02/12/2025 | 175 | 0 | 175 |  |  | 3/20/2025 | Connected |  | N
National Grid | METHUEN | 643644 | 01844 | 2.61 | Solar | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 176497 | 01453 | 34.2 | Solar | 05_14_43L6 | 02/07/2016 | 02/07/2016 | 5 | 5 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 | 02/07/2016 | 2/13/2017 | Y | EXP | 348 | 06/28/2016 | 07/05/2016 | 4 | 0 | 4 | 4/11/2016 | 4/11/2016 | 8/11/2016 | Connected |  | N
National Grid | WORCESTER | 378339 | 01604 | 11.4 | Solar | 05_14_60L2 | 08/26/2021 | 09/21/2021 | 17 | 16 | 1 | 09/22/2021 | 09/22/2021 | 62 | 39 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 1/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2022 | Connected |  | N
National Grid | DUDLEY | 719923 | 01571 | 5.76 | Solar | 05_14_74L6 | 09/22/2025 | 10/06/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 09/22/2025 | 12/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HUBBARDSTON | 472241 | 01452 | 6.38 | Solar | 05_01_219W5 | 11/17/2022 | 01/30/2023 | 47 | 46 | 1 | 01/31/2023 | 01/31/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  | 5/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2023 | Connected |  | N
National Grid | SOMERSET | 398037 | 02726 | 3.8 | Solar | 05_01_27W5 | 12/17/2021 | 01/07/2022 | 2 | 0 | 2 | 12/22/2021 | 12/22/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2022 | Connected |  | N
National Grid | LYNN | 324361 | 01904 | 0 | Solar | 05_01_413L3 | 11/06/2020 | 12/18/2020 | 28 | 27 | 1 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 11/06/2020 | 12/17/2021 | Y | EXP | 365 | 05/20/2021 | 06/25/2021 | 36 | 0 | 36 |  |  | 6/29/2021 | Connected |  | N
National Grid | REVERE | 178110 | 02151 | 8730 | Solar | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 412047 | 01832 | 0 | Other | 05_05_11W82 | 03/30/2022 | 04/21/2022 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2022 | 04/21/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 616805 | 01922 | 2.9 | Solar | 05_12_29W3 | 06/10/2024 |  | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 643619 | 01844 | 8.99 | Solar | 05_12_7W2 | 09/30/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/30/2024 | 12/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | LEOMINSTER | 176496 | 01453 | 17.6 | Solar | 05_14_43L6 | 02/05/2016 | 02/05/2016 | 8 | 8 | 0 | 02/19/2016 | 02/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2016 |  | 2/13/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/20/2016 | 9/20/2016 | 9/20/2016 | Connected |  | N
National Grid | WORCESTER | 443818 | 01604 | 50 | Solar | 05_14_60L2 | 07/15/2022 | 07/29/2022 | 10 | 0 | 10 | 08/01/2022 | 08/01/2022 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 |  | 2/23/2024 | N | EXP | 275 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 177324 | 01550 | 10 | Solar | 05_14_74L6 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 | 06/21/2016 | 06/21/2016 | 156 | 0 | 156 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2016 |  | 6/26/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 505826 | 01452 | 6 | Solar | 05_01_219W5 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 462891 | 02777 | 480 | Solar | 05_01_27W5 | 01/20/2023 | 04/10/2023 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 335832 | 01905 | 0 | Other | 05_01_413L3 | 04/07/2021 | 04/30/2021 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178109 | 02151 | 3396 | Solar | 05_01_609W1 | 11/06/2017 | 12/11/2017 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2017 | 01/09/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 416604 | 01832 | 250 | Solar | 05_05_11W82 | 04/04/2022 | 04/11/2022 | 5 | 0 | 5 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/04/2022 | 3/25/2025 | Y | STD | 455 |  |  | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | BYFIELD | 622079 | 01922 | 10 | Solar | 05_12_29W3 | 07/02/2024 | 07/18/2024 | 9 | 8 | 1 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/02/2024 | 8/7/2025 | Y | EXP | 365 | 10/04/2024 | 02/20/2025 | 140 | 0 | 140 |  |  | 3/3/2025 | Connected |  | N
National Grid | METHUEN | 656953 | 01844 | 7.6 | Solar | 05_12_7W2 | 11/26/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/26/2024 | 2/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LEOMINSTER | 176538 | 01453 | 34.2 | Solar | 05_14_43L6 | 02/10/2016 | 02/10/2016 | 5 | 5 | 0 | 02/19/2016 | 02/19/2016 | 434 | 0 | 434 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 11/20/2017 | N | EXP | 628 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 488659 | 01527 | 10.752 | Solar | 05_14_60L2 | 02/08/2023 | 02/09/2023 | 2 | 1 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 177643 | 01550 | 10 | Solar | 05_14_74L6 | 07/20/2017 | 07/20/2017 | 5 | 0 | 5 | 07/28/2017 | 07/28/2017 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2017 |  | 7/26/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 540185 | 01452 | 4.35 | Solar | 05_01_219W5 | 08/31/2023 | 09/01/2023 | 1 | 0 | 1 | 09/05/2023 | 09/05/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/31/2023 | 10/13/2024 | Y | EXP | 365 | 01/18/2024 | 02/07/2024 | 21 | 0 | 21 |  |  | 2/7/2024 | Connected |  | N
National Grid | SOMERSET | 469690 | 02726 | 9.84 | Solar | 05_01_27W5 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/11/2022 | 9/13/2024 | Y | EXP | 365 | 07/20/2023 | 09/14/2023 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 399464 | 01902 | 2625 | Solar | 05_01_413L3 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 178332 | 02151 | 1875 | Solar | 05_01_609W1 | 11/16/2017 | 02/23/2018 | 65 | 53 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/27/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 424766 | 01832 | 7.6 | Solar | 05_05_11W82 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2022 | Connected |  | Y
National Grid | BYFIELD | 630545 | 01922 | 3.8 | Solar | 05_12_29W3 | 08/09/2024 | 08/21/2024 | 3 | 0 | 3 | 08/22/2024 | 08/22/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | METHUEN | 660061 | 01844 | 10 | Solar | 05_12_7W2 | 12/20/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | LEOMINSTER | 193994 | 01453 | 540 | Solar | 05_14_43L6 | 09/18/2018 | 10/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 643637 | 01604 | 10 | Solar | 05_14_60L2 | 09/30/2024 | 10/29/2024 | 1 | 0 | 1 | 10/30/2024 | 10/30/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/30/2024 | 12/10/2025 | Y | EXP | 365 | 02/12/2025 | 02/26/2025 | 15 | 0 | 15 |  |  | 3/7/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 178226 | 01550 | 11.4 | Solar | 05_14_74L6 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 01/03/2018 | 1/10/2019 | Y | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 12/12/2019 | Connected |  | N
National Grid | WESTMINSTER | 546565 | 01473 | 7.6 | Solar | 05_01_219W5 | 08/08/2023 |  | 120 | 120 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 526849 | 02726 | 9.57 | Solar | 05_01_27W5 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 18 | 0 | 18 | 06/28/2023 | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 08/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 7/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 424618 | 01904 | 7.54 | Solar | 05_01_413L3 | 05/04/2022 | 05/09/2022 | 4 | 1 | 3 | 05/10/2022 | 05/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 | 05/04/2022 | 1/10/2024 | Y | EXP | 365 | 12/28/2022 | 01/10/2023 | 14 | 0 | 14 |  |  | 1/13/2023 | Connected |  | N
National Grid | REVERE | 217237 | 02151 | 10 | Solar | 05_01_609W1 | 04/03/2019 | 04/04/2019 | 0 | 0 | 0 | 04/05/2019 | 04/05/2019 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 |  | 6/28/2019 | N | EXP | 74 |  |  | 0 | 0 | 0 |  |  | 6/5/2019 | Connected |  | N
National Grid | HAVERHILL | 429706 | 01835 | 240 | Solar | 05_05_11W82 | 06/01/2022 | 06/30/2022 | 20 | 15 | 5 | 07/01/2022 | 07/01/2022 | 524 | 500 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BYFIELD | 631549 | 01922 | 7.6 | Solar | 05_12_29W3 | 08/09/2024 | 09/12/2024 | 5 | 4 | 1 | 09/13/2024 | 09/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LAWRENCE | 662068 | 01841 | 11.5 | Solar | 05_12_7W2 | 12/20/2024 | 12/30/2024 | 6 | 2 | 4 | 12/31/2024 | 12/31/2024 | 39 | 16 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 193993 | 01453 | 650 | Solar | 05_14_43L6 | 09/12/2018 | 10/02/2018 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2018 | 01/31/2019 | 80 | 0 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 646226 | 01604 | 5.76 | Solar | 05_14_60L2 | 10/21/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/24/2025 | Y | EXP | 365 | 02/26/2025 | 02/25/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 178524 | 01550 | 10 | Solar | 05_14_74L6 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/18/2018 | 05/18/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2018 |  | 4/10/2019 | N | EXP | 316 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 554393 | 01473 | 12.285 | Solar | 05_01_219W5 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | SOMERSET | 562649 | 02726 | 7.6 | Solar | 05_01_27W5 | 10/24/2023 | 10/25/2023 | 1 | 0 | 1 | 10/26/2023 | 10/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/24/2023 | 11/29/2024 | Y | EXP | 365 | 02/23/2024 | 03/26/2024 | 33 | 0 | 33 |  |  | 4/12/2024 | Connected |  | N
National Grid | LYNN | 447179 | 01905 | 7.6 | Solar | 05_01_413L3 | 08/31/2022 | 10/14/2022 | 30 | 30 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2022 | 08/31/2022 | 2/15/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 10/20/2023 | Connected |  | N
National Grid | REVERE | 257644 | 02151 | 0 | Battery Add-On | 05_01_609W1 | 10/07/2019 | 11/06/2019 | 0 | 0 | 0 | 11/07/2019 | 11/07/2019 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 10/07/2019 | 6/24/2020 | Y | EXP | 365 | 01/03/2020 | 01/09/2020 | 6 | 0 | 6 |  |  | 3/4/2020 | Connected |  | N
National Grid | HAVERHILL | 443979 | 01835 | 0 | Other | 05_05_11W82 | 01/30/2023 | 02/15/2023 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BYFIELD | 633685 | 01922 | 10 | Solar | 05_12_29W3 | 08/19/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | Y
National Grid | LAWRENCE | 669313 | 01841 | 1.625 | Solar | 05_12_7W2 | 02/10/2025 | 03/19/2025 | 2 | 0 | 2 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 313668 | 01453 | 6 | Solar | 05_14_43L6 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2020 |  | 9/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 681996 | 01604 | 22.8 | Solar | 05_14_60L2 | 04/01/2025 | 04/23/2025 | 15 | 12 | 3 | 04/24/2025 | 04/24/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 178591 | 01550 | 3.8 | Solar | 05_14_74L6 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 3/20/2019 | N | EXP | 32 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 642791 | 01473 | 15.2 | Solar | 05_01_219W5 | 03/11/2025 | 03/27/2025 | 12 | 8 | 4 | 03/28/2025 | 03/28/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | SOMERSET | 581603 | 02726 | 10 | Solar | 05_01_27W5 | 01/19/2024 | 01/23/2024 | 2 | 0 | 2 | 01/24/2024 | 01/24/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2024 | Connected |  | N
National Grid | LYNN | 457748 | 01905 | 0 | Other | 05_01_413L3 | 11/23/2022 | 12/21/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2022 | 01/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 257344 | 02151 | 9.765 | Solar | 05_01_609W1 | 12/09/2019 | 12/11/2019 | 2 | 2 | 0 | 12/12/2019 | 12/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 12/09/2019 | 12/9/2020 | Y | EXP | 365 | 05/29/2020 | 06/15/2020 | 17 | 0 | 17 |  |  | 9/22/2020 | Connected |  | N
National Grid | HAVERHILL | 468426 | 01832 | 10 | Solar | 05_05_11W82 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | BYFIELD | 655348 | 01922 | 6.72 | Solar | 05_12_29W3 | 11/19/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | LAWRENCE | 669803 | 01841 | 3.8 | Solar | 05_12_7W2 | 02/04/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | LEOMINSTER | 375768 | 01453 | 7.6 | Solar | 05_14_43L6 | 08/13/2021 | 08/30/2021 | 12 | 11 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 725530 | 01604 | 23 | Solar | 05_14_60L2 | 10/09/2025 | 10/17/2025 | 5 | 3 | 2 | 10/20/2025 | 10/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | SOUTHBRIDGE | 215537 | 01550 | 10 | Solar | 05_14_74L6 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 | 04/02/2019 | 2/5/2020 | Y | EXP | 296 | 11/06/2019 | 11/22/2019 | 16 | 0 | 16 |  |  | 11/26/2019 | Connected |  | N
National Grid | HUBBARDSTON | 651521 | 01452 | 10 | Solar | 05_01_219W5 | 11/13/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | SOMERSET | 628532 | 02726 | 5.76 | Solar | 05_01_27W5 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/29/2024 | 8/23/2025 | Y | EXP | 365 | 03/06/2025 | 06/06/2025 | 93 | 0 | 93 |  |  | 8/19/2025 | Connected |  | N
National Grid | LYNN | 471682 | 01905 | 3.8 | Solar | 05_01_413L3 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 12/05/2022 | 3/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | REVERE | 283891 | 02151 | 0 | Battery Add-On | 05_01_609W1 | 03/30/2020 | 04/06/2020 | 5 | 5 | 0 | 04/07/2020 | 04/07/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2020 | Connected |  | N
National Grid | HAVERHILL | 475488 | 01832 | 15.08 | Solar | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BYFIELD | 660896 | 01922 | 3.8 | Solar | 05_12_29W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | LAWRENCE | 673349 | 01841 | 3.8 | Solar | 05_12_7W2 | 02/21/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 416288 | 01453 | 7.6 | Solar | 05_14_43L6 | 12/20/2022 | 01/05/2023 | 10 | 10 | 0 | 01/06/2023 | 01/06/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | N
National Grid | WORCESTER | 426194 | 01604 | 460 | Solar | 05_14_60L3 | 05/18/2022 | 07/14/2022 | 38 | 31 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 05/18/2022 | 5/1/2026 | Y | STD | 5 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DUDLEY | 261851 | 01571 | 7.6 | Solar | 05_14_74L6 | 11/05/2019 | 01/08/2020 | 40 | 33 | 7 | 01/09/2020 | 01/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/05/2019 | 1/15/2021 | Y | EXP | 365 | 07/07/2020 | 07/10/2020 | 3 | 0 | 3 |  |  | 1/11/2021 | Connected |  | N
National Grid | HUBBARDSTON | 655465 | 01452 | 7.6 | Solar | 05_01_219W5 | 11/20/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 635563 | 02726 | 10 | Solar | 05_01_27W5 | 08/26/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 08/26/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 10/01/2025 | 112 | 0 | 112 |  |  | 10/28/2025 | Connected |  | N
National Grid | LYNN | 585545 | 01905 | 498 | Solar | 05_01_413L3 | 02/14/2024 | 05/01/2024 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2024 | 05/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 289990 | 02151 | 4950 | Other | 05_01_609W1 | 05/16/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 475485 | 01832 | 15.08 | Solar | 05_05_11W82 | 11/08/2022 | 11/14/2022 | 3 | 2 | 1 | 11/15/2022 | 11/15/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 660840 | 01950 | 5.76 | Solar | 05_12_29W3 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 683296 | 01841 | 5.76 | Solar | 05_12_7W2 | 04/07/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/07/2025 | 8/1/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/2/2025 | Connected |  | N
National Grid | LEOMINSTER | 418171 | 01453 | 149.9 | Solar | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/8/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/8/2023 | Connected |  | N
National Grid | WORCESTER | 475737 | 01604 | 100 | Solar | 05_14_60L3 | 12/15/2022 | 01/18/2023 | 21 | 12 | 9 | 01/19/2023 | 01/19/2023 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 | 12/15/2022 | 10/7/2026 | Y | EXP | 326 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBRIDGE | 289216 | 01550 | 7.6 | Solar | 05_14_74L6 | 05/21/2020 | 05/27/2020 | 2 | 0 | 2 | 05/28/2020 | 05/28/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/21/2020 | 9/17/2021 | Y | EXP | 365 | 01/20/2021 | 01/28/2021 | 8 | 0 | 8 |  |  | 7/16/2021 | Connected |  | N
National Grid | HUBBARDSTON | 680944 | 01452 | 20 | Solar | 05_01_219W5 | 03/27/2025 | 04/14/2025 | 12 | 8 | 4 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 639402 | 02726 | 7.6 | Solar | 05_01_27W5 | 09/11/2024 | 09/24/2024 | 3 | 0 | 3 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | LYNN | 611319 | 01904 | 20 | Solar | 05_01_413L3 | 05/23/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | REVERE | 291210 | 02151 | 0 | Other | 05_01_609W1 | 08/31/2020 | 09/23/2020 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2020 | 10/16/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 510632 | 01832 | 30 | Solar | 05_05_11W82 | 05/14/2023 | 05/30/2023 | 11 | 2 | 9 | 05/31/2023 | 05/31/2023 | 66 | 42 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2023 |  | 11/29/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/6/2025 | Connected |  | N
National Grid | NEWBURY | 662949 | 01950 | 3.8 | Solar | 05_12_29W3 | 12/30/2024 | 01/13/2025 | 4 | 0 | 4 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 701317 | 01841 | 10.24 | Solar | 05_12_7W2 | 06/26/2025 | 07/11/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LEOMINSTER | 418169 | 01453 | 133.2 | Solar | 05_14_43L6 | 03/17/2022 | 04/11/2022 | 17 | 11 | 6 |  |  | 37 | 12 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | WORCESTER | 510521 | 01604 | 480 | Solar | 05_14_60L3 | 08/01/2023 | 09/08/2023 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2023 | 12/11/2023 | 63 | 45 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 08/01/2023 | 10/8/2027 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SOUTHBRIDGE | 334597 | 01550 | 7.6 | Solar | 05_14_74L6 | 01/13/2021 | 02/05/2021 | 16 | 16 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/13/2021 | 9/2/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | HUBBARDSTON | 683085 | 01452 | 7.6 | Solar | 05_01_219W5 | 04/04/2025 | 05/08/2025 | 24 | 22 | 2 | 05/09/2025 | 05/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 644294 | 02726 | 3.8 | Solar | 05_01_27W5 | 10/02/2024 | 11/07/2024 | 13 | 11 | 2 | 11/08/2024 | 11/08/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | LYNN | 615697 | 01905 | 20 | Solar | 05_01_413L3 | 06/05/2024 | 06/14/2024 | 7 | 5 | 2 | 06/17/2024 | 06/17/2024 | 61 | 50 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 299584 | 02151 | 7.68 | Solar | 05_01_609W1 | 07/02/2020 | 07/08/2020 | 3 | 0 | 3 | 07/09/2020 | 07/09/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2020 |  | 7/6/2022 | N | EXP | 629 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 616104 | 01832 | 250 | Solar | 05_05_11W82 | 08/08/2024 | 02/05/2025 | 120 | 110 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2025 | 03/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 664528 | 01950 | 7.6 | Solar | 05_12_29W3 | 01/09/2025 | 02/26/2025 | 4 | 1 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 704708 | 01844 | 3.8 | Solar | 05_12_7W2 | 07/14/2025 | 07/29/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 73 | 59 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 418150 | 01453 | 149.9 | Solar | 05_14_43L6 | 03/17/2022 | 03/28/2022 | 7 | 0 | 7 |  |  | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 03/17/2022 | 12/12/2023 | Y | STD | 165 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | WORCESTER | 176280 | 01604 | 42 | Solar | 05_14_60L3 | 05/06/2015 | 05/06/2015 | 0 | 0 | 0 | 05/07/2015 | 05/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 | 05/06/2015 | 10/30/2015 | Y | EXP | 161 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 5/13/2016 | Connected |  | N
National Grid | CHARLTON | 501293 | 01507 | 6 | Solar | 05_14_74L6 | 04/13/2023 |  | 202 | 198 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 747732 | 01473 | 20 | Solar | 05_01_219W5 | 01/27/2026 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2026 | Connected |  | Y
National Grid | SOMERSET | 644817 | 02726 | 5.76 | Solar | 05_01_27W5 | 10/03/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | LYNN | 648192 | 01904 | 3.8 | Solar | 05_01_413L3 | 10/30/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | REVERE | 299242 | 02151 | 0 | Solar | 05_01_609W1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 630480 | 01832 | 7.83 | Solar | 05_05_11W82 | 08/06/2024 | 09/09/2024 | 17 | 13 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/06/2024 | 10/28/2025 | Y | EXP | 365 | 11/13/2024 | 12/05/2024 | 23 | 0 | 23 |  |  | 2/8/2025 | Connected |  | N
National Grid | NEWBURY | 701959 | 01950 | 3.8 | Solar | 05_12_29W4 | 06/30/2025 | 09/23/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 87 | 74 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 742271 | 01841 | 18.88 | Solar | 05_12_7W3 | 02/18/2026 | 02/25/2026 | 1 | 0 | 1 | 02/26/2026 | 02/26/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 532437 | 01453 | 6 | Solar | 05_14_43L6 | 06/14/2023 | 06/16/2023 | 2 | 0 | 2 | 06/20/2023 | 06/20/2023 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177073 | 01604 | 36 | Solar | 05_14_60L3 | 08/03/2016 | 08/03/2016 | 1 | 0 | 1 | 08/05/2016 | 08/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 8/9/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/27/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 516167 | 01550 | 6 | Solar | 05_14_74L6 | 06/20/2023 | 06/22/2023 | 3 | 1 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 9/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 725691 | 01473 | 5.76 | Solar | 05_01_219W6 | 10/10/2025 | 11/07/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 57 | 38 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 647364 | 02726 | 7.6 | Solar | 05_01_27W5 | 10/30/2024 | 11/21/2024 | 2 | 0 | 2 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 649017 | 01904 | 7.6 | Solar | 05_01_413L3 | 11/04/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/04/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | REVERE | 311144 | 02151 | 9.6 | Solar | 05_01_609W1 | 09/07/2020 | 09/08/2020 | 0 | 0 | 0 | 09/09/2020 | 09/09/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/07/2020 | 9/7/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2021 | Connected |  | N
National Grid | HAVERHILL | 633722 | 01835 | 7.6 | Solar | 05_05_11W82 | 08/19/2024 | 12/30/2024 | 18 | 13 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 08/19/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | NEWBURY | 706810 | 01950 | 11.5 | Solar | 05_12_29W4 | 08/25/2025 | 09/02/2025 | 5 | 0 | 5 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 395249 | 01841 | 34.6 | Solar | 05_12_7W3 | 02/17/2022 | 03/22/2022 | 22 | 20 | 2 | 03/23/2022 | 03/23/2022 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 |  | 3/31/2024 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 3/25/2024 | Connected |  | N
National Grid | LEOMINSTER | 550928 | 01453 | 7.6 | Solar | 05_14_43L6 | 10/11/2023 | 10/12/2023 | 1 | 0 | 1 | 10/13/2023 | 10/13/2023 | 18 | 0 | 18 | 12/12/2023 | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 |  | 01/25/2024 | 30 | 3 | 27 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177456 | 01604 | 594 | Solar | 05_14_60L3 | 12/07/2016 | 12/07/2016 | 40 | 25 | 15 | 02/06/2017 | 02/06/2017 | 0 | 0 | 0 | 05/22/2017 | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2017 |  | 12/12/2017 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/11/2017 | 10/11/2017 | 10/17/2017 | Connected |  | N
National Grid | DUDLEY | 558017 | 01571 | 7.6 | Solar | 05_14_74L6 | 10/04/2023 | 10/09/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/04/2023 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2024 | Connected |  | N
National Grid | WESTMINSTER | 744345 | 01473 | 23 | Solar | 05_01_219W6 | 01/09/2026 | 01/13/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 35 | 24 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 647973 | 02726 | 7.6 | Solar | 05_01_27W5 | 10/28/2024 | 12/12/2024 | 23 | 20 | 3 | 12/13/2024 | 12/13/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 649412 | 01907 | 3.8 | Solar | 05_01_413L3 | 11/05/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 343989 | 02151 | 7.6 | Solar | 05_01_609W1 | 02/25/2021 | 03/01/2021 | 1 | 0 | 1 | 03/02/2021 | 03/02/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 662986 | 01835 | 8.36 | Solar | 05_05_11W82 | 12/30/2024 | 02/11/2025 | 5 | 2 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/30/2024 | 4/7/2026 | Y | EXP | 365 | 04/16/2025 | 05/20/2025 | 35 | 0 | 35 |  |  | 6/3/2025 | Connected |  | N
National Grid | NEWBURY | 749412 | 01950 | 5.76 | Solar | 05_12_29W4 | 02/04/2026 | 02/09/2026 | 4 | 0 | 4 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 464788 | 01841 | 8.99 | Solar | 05_12_7W3 | 11/15/2022 | 11/18/2022 | 3 | 0 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  | 12/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | LEOMINSTER | 593129 | 01453 | 7.6 | Solar | 05_14_43L6 | 03/16/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 6 | 1 | 5 | 04/16/2024 | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 05/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 5/15/2024 |  | 6/22/2025 | N | EXP | 365 | 07/10/2024 | 08/30/2024 | 52 | 0 | 52 |  |  | 10/12/2024 | Connected |  | N
National Grid | WORCESTER | 216789 | 01604 | 55 | Solar | 05_14_60L3 | 04/02/2019 | 04/11/2019 | 6 | 5 | 1 | 04/12/2019 | 04/12/2019 | 3 | 0 | 3 | 05/23/2019 | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 06/20/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 7/12/2019 |  | 7/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 552870 | 01507 | 10 | Solar | 05_14_74L6 | 11/06/2023 | 11/15/2023 | 6 | 4 | 2 | 11/16/2023 | 11/16/2023 | 48 | 41 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 11/06/2023 | 4/17/2025 | Y | EXP | 365 | 07/31/2024 | 10/23/2024 | 85 | 0 | 85 |  |  | 11/13/2024 | Connected |  | N
National Grid | WESTMINSTER | 176432 | 01473 | 1965 | Natural Gas | 05_01_219W6 | 03/14/2016 | 03/14/2016 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2016 | 06/23/2016 | 56 | 38 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2017 | 03/14/2016 | 6/30/2019 | Y | STD | 832 | 10/11/2017 | 04/04/2018 | 103 | 0 | 103 | 1/5/2018 | 1/5/2018 | 8/8/2018 | Connected |  | N
National Grid | SOMERSET | 660823 | 02726 | 5.76 | Solar | 05_01_27W5 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/16/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | Y
National Grid | SALEM | 655973 | 01970 | 0 | Battery Add-On | 05_01_413L3 | 11/21/2024 | 11/25/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 58 | 33 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 11/21/2024 | 3/14/2026 | Y | EXP | 365 | 07/26/2025 | 07/29/2025 | 4 | 0 | 4 |  |  | 11/24/2025 | Connected |  | N
National Grid | REVERE | 402697 | 02151 | 0 | Solar | 05_01_609W1 | 12/21/2021 | 01/10/2022 | 13 | 12 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 3/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | HAVERHILL | 679803 | 01832 | 7.6 | Solar | 05_05_11W82 | 03/21/2025 | 04/03/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 | 03/21/2025 | 6/2/2026 | Y | EXP | 365 | 07/24/2025 | 07/24/2025 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 752028 | 01950 | 20 | Solar | 05_12_29W4 | 02/19/2026 | 02/20/2026 | 1 | 0 | 1 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 565408 | 01841 | 25 | Solar | 05_12_7W3 | 11/03/2023 | 01/31/2024 | 59 | 55 | 4 | 02/01/2024 | 02/01/2024 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 605419 | 01453 | 7.6 | Solar | 05_14_43L6 | 04/22/2024 | 05/01/2024 | 8 | 7 | 1 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/22/2024 | 5/23/2025 | Y | EXP | 365 | 08/22/2024 | 03/04/2025 | 195 | 0 | 195 |  |  | 3/6/2025 | Connected |  | N
National Grid | WORCESTER | 276671 | 01604 | 400 | Solar | 05_14_60L3 | 05/29/2020 | 07/09/2020 | 29 | 23 | 6 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 562808 | 01507 | 6 | Solar | 05_14_74L6 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 | 11/01/2023 | 12/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | HUBBARDSTON | 196233 | 01452 | 7.6 | Solar | 05_01_219W6 | 09/18/2018 | 08/09/2019 | 147 | 145 | 2 | 08/12/2019 | 08/12/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2021 | Connected |  | N
National Grid | SOMERSET | 667511 | 02726 | 11.4 | Solar | 05_01_27W5 | 02/04/2025 | 03/11/2025 | 16 | 12 | 4 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | LYNN | 669716 | 01904 | 0 | Other | 05_01_413L3 | 03/07/2025 | 03/31/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 426230 | 02151 | 7.6 | Solar | 05_01_609W1 | 06/01/2022 | 06/06/2022 | 4 | 2 | 2 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2022 | Connected |  | N
National Grid | HAVERHILL | 613222 | 01835 | 3320 | Solar | 05_05_11W83 | 07/11/2024 | 07/30/2024 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NEWBURY | 175227 | 01950 | 7.6 | Solar | 05_12_29W4 | 01/06/2015 | 01/06/2015 | 4 | 0 | 4 | 01/13/2015 | 01/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 | 01/06/2015 | 12/31/2016 | Y | EXP | 687 | 11/16/2015 | 12/29/2015 | 29 | 0 | 29 | 4/16/2015 | 4/16/2015 | 6/14/2016 | Connected |  | N
National Grid | LAWRENCE | 587779 | 01841 | 7.6 | Solar | 05_12_7W3 | 02/05/2024 | 02/13/2024 | 6 | 0 | 6 | 02/14/2024 | 02/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2024 | Connected |  | N
National Grid | LEOMINSTER | 608805 | 01453 | 7.6 | Solar | 05_14_43L6 | 05/04/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 349427 | 01604 | 9.8 | Solar | 05_14_60L3 | 04/21/2021 | 04/26/2021 | 2 | 0 | 2 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 578472 | 01550 | 2.03 | Solar | 05_14_74L6 | 01/02/2024 | 01/05/2024 | 3 | 0 | 3 | 01/08/2024 | 01/08/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  | 2/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2024 | Connected |  | N
National Grid | WESTMINSTER | 193270 | 01473 | 3.8 | Solar | 05_01_219W6 | 08/11/2018 | 09/24/2018 | 3 | 3 | 0 | 09/25/2018 | 09/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 680717 | 02777 | 7.6 | Solar | 05_01_27W5 | 03/26/2025 | 04/11/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 699104 | 01904 | 13.8 | Solar | 05_01_413L3 | 06/24/2025 | 07/22/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/24/2025 | 8/26/2026 | Y | EXP | 365 | 11/14/2025 | 02/13/2026 | 92 | 0 | 92 |  |  | 11/26/2025 | Connected |  | N
National Grid | REVERE | 472538 | 02151 | 7.6 | Solar | 05_01_609W1 | 11/18/2022 | 11/23/2022 | 3 | 0 | 3 | 11/25/2022 | 11/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/18/2022 | 3/2/2024 | Y | EXP | 365 | 02/23/2023 | 03/02/2023 | 8 | 0 | 8 |  |  | 6/24/2023 | Connected |  | N
National Grid | HAVERHILL | 747624 | 01832 | 13.36 | Solar | 05_05_11W83 | 01/27/2026 | 01/30/2026 | 3 | 0 | 3 | 02/02/2026 | 02/02/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEWBURY | 175298 | 01950 | 5 | Solar | 05_12_29W4 | 01/15/2015 | 01/15/2015 | 43 | 43 | 0 | 03/24/2015 | 03/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 5/31/2015 | N | EXP | 65 |  |  | 0 | 0 | 0 | 1/8/2016 | 1/8/2016 | 1/8/2016 | Connected |  | N
National Grid | LAWRENCE | 636110 | 01841 | 8.12 | Solar | 05_12_7W3 | 08/28/2024 | 09/10/2024 | 1 | 0 | 1 | 09/11/2024 | 09/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | LEOMINSTER | 619180 | 01453 | 10 | Solar | 05_14_43L6 | 06/19/2024 | 07/10/2024 | 5 | 1 | 4 | 07/11/2024 | 07/11/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | WORCESTER | 396682 | 01604 | 0 | Other | 05_14_60L3 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/03/2022 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 580061 | 01550 | 10 | Solar | 05_14_74L6 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | WESTMINSTER | 199248 | 01473 | 7.6 | Solar | 05_01_219W6 | 11/08/2018 | 12/03/2018 | 13 | 10 | 3 | 12/04/2018 | 12/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 681379 | 02777 | 15.2 | Solar | 05_01_27W5 | 03/28/2025 | 04/01/2025 | 2 | 0 | 2 | 04/02/2025 | 04/02/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 321753 | 01904 | 0 | Other | 05_01_413L4 | 04/13/2021 | 04/30/2021 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2021 | 06/01/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 542295 | 02151 | 0 | Other | 05_01_609W1 | 08/28/2023 | 09/12/2023 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2023 | 10/11/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174178 | 01832 | 20 | Solar | 05_05_11W83 | 03/05/2012 | 03/05/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2012 |  | 5/16/2012 | N | EXP | 2 |  |  | 0 | 0 | 0 | 6/5/2012 | 6/5/2012 | 8/2/2012 | Connected |  | N
National Grid | NEWBURY | 175646 | 01950 | 5.16 | Solar | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 10/21/2015 | Connected |  | N
National Grid | LAWRENCE | 636904 | 01841 | 5 | Solar | 05_12_7W3 | 08/30/2024 | 10/11/2024 | 4 | 2 | 2 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 620785 | 01453 | 7.6 | Solar | 05_14_43L6 | 06/26/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 10/19/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 521128 | 01604 | 0 | Other | 05_14_60L3 | 08/11/2023 | 08/28/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 02/09/2024 | 112 | 93 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 603429 | 01507 | 10 | Solar | 05_14_74L6 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 | 04/17/2024 | 6/24/2025 | Y | EXP | 365 | 10/23/2024 | 12/02/2024 | 41 | 0 | 41 |  |  | 12/6/2024 | Connected |  | N
National Grid | WESTMINSTER | 230771 | 01473 | 7.6 | Solar | 05_01_219W6 | 06/18/2019 | 06/24/2019 | 3 | 0 | 3 | 06/25/2019 | 06/25/2019 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 684979 | 02777 | 15.2 | Solar | 05_01_27W5 | 04/14/2025 | 04/23/2025 | 4 | 1 | 3 | 04/24/2025 | 04/24/2025 | 35 | 22 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | SALEM | 684764 | 01970 | 11.4 | Solar | 05_01_413L4 | 06/09/2025 | 07/25/2025 | 10 | 7 | 3 | 08/20/2025 | 08/20/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | REVERE | 552766 | 02151 | 0 | Solar | 05_01_609W1 | 09/01/2023 | 09/05/2023 | 1 | 0 | 1 | 09/06/2023 | 09/06/2023 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176000 | 01832 | 10 | Solar | 05_05_11W83 | 06/11/2015 | 06/11/2015 | 0 | 0 | 0 | 06/16/2015 | 06/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 6/21/2016 | N | EXP | 34 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/28/2016 | Connected |  | N
National Grid | NEWBURY | 175645 | 01922 | 5.16 | Solar | 05_12_29W4 | 12/16/2014 | 12/16/2014 | 8 | 6 | 2 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2015 |  | 2/16/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/21/2015 | Connected |  | N
National Grid | LAWRENCE | 637079 | 01841 | 5.76 | Solar | 05_12_7W3 | 09/02/2024 | 09/16/2024 | 5 | 4 | 1 | 09/17/2024 | 09/17/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 629859 | 01453 | 7.6 | Solar | 05_14_43L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 | 08/02/2024 | 8/28/2025 | Y | EXP | 365 | 02/28/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 4/1/2025 | Connected |  | N
National Grid | WORCESTER | 665620 | 01604 | 67.3 | Solar | 05_14_60L3 | 01/22/2025 | 02/14/2025 | 17 | 7 | 10 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 1/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 609579 | 01550 | 13.6 | Solar | 05_14_74L6 | 05/09/2024 | 05/16/2024 | 3 | 0 | 3 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/09/2024 | 8/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | HUBBARDSTON | 606789 | 01452 | 10 | Solar | 05_01_219W6 | 04/26/2024 | 05/16/2024 | 10 | 9 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 | 04/26/2024 | 7/23/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 689710 | 02777 | 5.76 | Solar | 05_01_27W5 | 05/05/2025 | 05/20/2025 | 2 | 0 | 2 | 05/28/2025 | 05/28/2025 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SALEM | 709185 | 01970 | 4.537 | Solar | 05_01_413L4 | 08/06/2025 | 08/26/2025 | 15 | 11 | 4 | 10/28/2025 | 10/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 560920 | 02151 | 5.235 | Solar | 05_01_609W1 | 11/07/2023 | 11/14/2023 | 4 | 3 | 1 | 11/15/2023 | 11/15/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 11/07/2023 | 1/29/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | HAVERHILL | 177145 | 01832 | 15.2 | Solar | 05_05_11W83 | 08/08/2016 | 08/08/2016 | 4 | 4 | 0 | 08/15/2016 | 08/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2016 |  | 8/14/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/5/2017 | 1/5/2017 | 1/6/2017 | Connected |  | N
National Grid | NEWBURY | 176142 | 01950 | 7.75 | Solar | 05_12_29W4 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 398 | 0 | 398 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2015 |  | 7/6/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 7/27/2015 | 7/27/2015 |  | Withdrawn |  | Y
National Grid | LAWRENCE | 647963 | 01841 | 15.2 | Solar | 05_12_7W3 | 10/17/2024 | 11/04/2024 | 12 | 10 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/17/2024 | 1/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 632034 | 01453 | 3.8 | Solar | 05_14_43L6 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2024 | Connected |  | N
National Grid | WORCESTER | 426844 | 01604 | 4998 | Solar | 05_14_60L4 | 05/31/2022 | 07/25/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 05/31/2022 | 10/7/2026 | Y | CMPX | 38 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SOUTHBRIDGE | 614816 | 01550 | 10 | Solar | 05_14_74L6 | 06/04/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 608585 | 01473 | 23 | Solar | 05_01_219W6 | 05/06/2024 | 05/14/2024 | 7 | 4 | 3 | 05/15/2024 | 05/15/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/06/2024 | 6/20/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | SWANSEA | 698095 | 02777 | 13.36 | Solar | 05_01_27W5 | 07/09/2025 | 08/06/2025 | 20 | 16 | 4 | 09/09/2025 | 09/09/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 708616 | 01970 | 24.576 | Solar | 05_01_413L4 | 08/06/2025 | 08/14/2025 | 5 | 2 | 3 | 08/15/2025 | 08/15/2025 | 20 | 5 | 15 | 09/26/2025 | 02/05/2026 | 89 | 32 | 57 |  |  | 0 | 0 | 0 |  | 02/05/2026 | 89 | 32 | 57 |  |  | 0 | 0 | 0 | 2/11/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | REVERE | 566961 | 02151 | 5 | Solar | 05_01_609W1 | 11/08/2023 | 11/09/2023 | 1 | 0 | 1 | 11/13/2023 | 11/13/2023 | 38 | 14 | 24 | 03/01/2024 | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 03/29/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/23/2025 | N | EXP | 365 | 05/31/2024 | 07/05/2024 | 36 | 0 | 36 |  |  | 8/9/2024 | Connected |  | N
National Grid | HAVERHILL | 177194 | 01832 | 28 | Solar | 05_05_11W83 | 10/31/2016 | 10/31/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/6/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 5/18/2017 | 5/18/2017 | 5/22/2017 | Connected |  | N
National Grid | NEWBURY | 176626 | 01951 | 7.6 | Solar | 05_12_29W4 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2016 | 04/15/2016 | 10/30/2017 | Y | EXP | 467 | 04/26/2017 | 08/02/2017 | 68 | 0 | 68 | 4/20/2017 | 4/20/2017 | 8/18/2017 | Connected |  | N
National Grid | LAWRENCE | 649136 | 01841 | 7.6 | Solar | 05_12_7W3 | 11/06/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 632339 | 01453 | 3.8 | Solar | 05_14_43L6 | 09/11/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 | 09/11/2024 | 10/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | WORCESTER | 174776 | 01604 | 3000 | Solar | 05_14_60L4 | 01/22/2013 | 01/22/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2013 | 05/21/2013 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 625512 | 01550 | 5.76 | Solar | 05_14_74L6 | 07/17/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | WESTMINSTER | 636595 | 01473 | 7.6 | Solar | 05_01_219W6 | 08/29/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | SWANSEA | 175928 | 02777 | 99 | Solar | 05_01_2J328 | 08/05/2015 | 08/05/2015 | 2 | 2 | 0 | 08/10/2015 | 08/10/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/11/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 724466 | 01970 | 5.76 | Solar | 05_01_413L4 | 10/06/2025 | 10/13/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/06/2025 | 12/17/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REVERE | 569500 | 02151 | 7.6 | Solar | 05_01_609W1 | 11/27/2023 | 11/29/2023 | 3 | 2 | 1 | 11/30/2023 | 11/30/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | HAVERHILL | 178193 | 01832 | 6.6 | Solar | 05_05_11W83 | 01/02/2018 | 01/02/2018 | 24 | 0 | 24 | 02/07/2018 | 02/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 1/8/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | Connected |  | N
National Grid | NEWBURY | 176880 | 01951 | 10 | Solar | 05_12_29W4 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 | 05/04/2016 | 5/10/2017 | Y | EXP | 349 | 03/22/2017 | 04/10/2017 | 13 | 0 | 13 | 4/20/2017 | 4/20/2017 | 4/25/2017 | Connected |  | N
National Grid | LAWRENCE | 653572 | 01841 | 8.125 | Solar | 05_12_7W3 | 11/22/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/22/2024 | 8/9/2026 | Y | EXP | 365 | 10/01/2025 | 10/29/2025 | 29 | 0 | 29 |  |  | 2/13/2026 | Connected |  | N
National Grid | LEOMINSTER | 637411 | 01453 | 5.76 | Solar | 05_14_43L6 | 09/03/2024 | 09/26/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/03/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | WORCESTER | 175389 | 01602 | 100 | Solar | 05_14_60L4 | 09/11/2014 | 09/11/2014 | 7 | 0 | 7 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 12/19/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/5/2015 | 2/5/2015 | 2/18/2015 | Connected |  | N
National Grid | SOUTHBRIDGE | 629733 | 01550 | 10 | Solar | 05_14_74L6 | 08/02/2024 | 08/13/2024 | 2 | 0 | 2 | 08/14/2024 | 08/14/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 08/02/2024 | 11/25/2025 | Y | EXP | 365 | 11/22/2024 | 12/05/2024 | 14 | 0 | 14 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 656186 | 01473 | 7.6 | Solar | 05_01_219W6 | 11/21/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | SWANSEA | 376505 | 02777 | 43.2 | Solar | 05_01_2J328 | 08/18/2021 | 09/10/2021 | 16 | 6 | 10 |  |  | 200 | 172 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  | 11/20/2023 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | SALEM | 739668 | 01970 | 3.8 | Solar | 05_01_413L4 | 12/11/2025 | 12/22/2025 | 4 | 0 | 4 | 01/22/2026 | 01/22/2026 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 578023 | 02151 | 9.86 | Solar | 05_01_609W1 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 41 | 35 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 178395 | 01832 | 7.6 | Solar | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/11/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | NEWBURY | 177620 | 01950 | 10 | Solar | 05_12_29W4 | 11/08/2017 | 11/08/2017 | 99 | 89 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 655714 | 01841 | 7.6 | Solar | 05_12_7W3 | 11/20/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2025 | Connected |  | N
National Grid | LEOMINSTER | 644208 | 01453 | 5.76 | Solar | 05_14_43L6 | 10/01/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/01/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178375 | 01602 | 7.6 | Solar | 05_14_60L4 | 11/21/2017 | 11/21/2017 | 10 | 0 | 10 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2017 |  | 2/15/2019 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 11/12/2019 | Connected |  | N
National Grid | SOUTHBRIDGE | 630908 | 01550 | 3.8 | Solar | 05_14_74L6 | 08/07/2024 | 11/04/2024 | 1 | 0 | 1 | 11/05/2024 | 11/05/2024 | 32 | 11 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 677866 | 01473 | 13.8 | Solar | 05_01_219W6 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 123 | 103 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 646548 | 02777 | 3.8 | Solar | 05_01_2J328 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 15 | 0 | 15 | 12/05/2024 | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 01/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 744557 | 01904 | 9.423 | Solar | 05_01_413L4 | 01/20/2026 | 01/27/2026 | 8 | 6 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REVERE | 593641 | 02151 | 0 | Battery Add-On | 05_01_609W1 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 | 03/08/2024 | 4/1/2025 | Y | EXP | 365 | 05/24/2024 | 05/23/2024 | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | HAVERHILL | 178392 | 01835 | 10 | Solar | 05_05_11W83 | 03/02/2018 | 03/02/2018 | 41 | 40 | 1 | 04/04/2018 | 04/04/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2018 |  | 3/7/2019 | N | EXP | 175 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 184469 | 01950 | 3.8 | Solar | 05_12_29W4 | 06/07/2018 | 06/07/2018 | 16 | 7 | 9 | 06/29/2018 | 06/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 669707 | 01844 | 3.8 | Solar | 05_12_7W3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 646547 | 01453 | 3.8 | Solar | 05_14_43L6 | 10/21/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 03/15/2025 | 04/10/2025 | 27 | 0 | 27 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178464 | 01602 | 199.8 | Solar | 05_14_60L4 | 01/22/2018 | 01/22/2018 | 0 | 0 | 0 | 03/21/2018 | 03/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/28/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 6/28/2018 | Connected |  | N
National Grid | SOUTHBRIDGE | 637230 | 01550 | 10 | Solar | 05_14_74L6 | 09/03/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 78 | 42 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | HUBBARDSTON | 707464 | 01452 | 12.672 | Solar | 05_01_21W1 | 07/30/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 | 07/30/2025 | 10/14/2026 | Y | EXP | 365 | 02/03/2026 |  | 32 | 0 | 32 |  |  |  | Construction |  | N
National Grid | SWANSEA | 340607 | 02777 | 726.6 | Solar | 05_01_2J335 | 10/13/2021 | 02/28/2022 | 94 | 86 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/01/2022 | 03/01/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2023 | 10/13/2021 | 3/26/2026 | Y | STD | 245 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 746755 | 01970 | 5.76 | Solar | 05_01_413L4 | 01/21/2026 | 01/22/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | REVERE | 598052 | 02151 | 15.2 | Solar | 05_01_609W1 | 03/23/2024 | 03/29/2024 | 5 | 2 | 3 | 04/01/2024 | 04/01/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/23/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/31/2024 | 29 | 0 | 29 |  |  | 10/2/2024 | Connected |  | N
National Grid | HAVERHILL | 178672 | 01832 | 7.6 | Solar | 05_05_11W83 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/26/2019 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 185702 | 01950 | 7.6 | Solar | 05_12_29W4 | 06/13/2018 | 06/13/2018 | 30 | 25 | 5 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 | 06/13/2018 | 9/20/2019 | Y | EXP | 416 | 05/17/2019 | 05/16/2019 | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | METHUEN | 687889 | 01844 | 10 | Solar | 05_12_7W3 | 04/28/2025 | 07/31/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | Y
National Grid | SPENCER | 647008 | 01562 | 5.76 | Solar | 05_14_43L6 | 10/29/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/12/2025 | 11/26/2025 | 168 | 0 | 168 |  |  | 12/10/2025 | Connected |  | N
National Grid | WORCESTER | 178529 | 01602 | 5000 | Solar | 05_14_60L4 | 12/04/2017 | 12/04/2017 | 21 | 21 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2018 | 02/08/2018 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 640464 | 01550 | 10 | Solar | 05_14_74L6 | 09/17/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/17/2024 | 12/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WESTMINSTER | 749988 | 01473 | 5.76 | Solar | 05_01_21W1 | 02/09/2026 | 02/10/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 725024 | 02777 | 7.6 | Solar | 05_01_2J335 | 10/08/2025 | 11/11/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 174325 | 01904 | 2000 | Solar | 05_01_413L4 | 01/18/2012 | 01/18/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 06/19/2014 | 34 | 0 | 34 |  |  | 6/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 634319 | 02151 | 10 | Solar | 05_01_609W1 | 08/21/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 08/21/2024 | 1/27/2026 | Y | EXP | 365 | 04/30/2025 | 11/21/2025 | 206 | 0 | 206 |  |  | 12/4/2025 | Connected |  | N
National Grid | HAVERHILL | 193254 | 01832 | 6 | Solar | 05_05_11W83 | 08/10/2018 | 10/08/2018 | 15 | 15 | 0 | 10/09/2018 | 10/09/2018 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 08/10/2018 | 10/30/2019 | Y | EXP | 378 | 05/08/2019 | 05/07/2019 | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | NEWBURY | 187782 | 01951 | 7.6 | Solar | 05_12_29W4 | 06/25/2018 | 06/25/2018 | 27 | 26 | 1 | 08/06/2018 | 08/06/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 06/25/2018 | 8/8/2019 | Y | EXP | 365 | 12/27/2018 | 01/03/2019 | 7 | 0 | 7 |  |  | 5/10/2019 | Connected |  | N
National Grid | METHUEN | 175084 | 01844 | 144.3 | Solar | 05_12_7W4 | 08/14/2012 | 08/14/2012 | 5 | 0 | 5 | 08/22/2012 | 08/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2013 |  | 11/15/2012 | N | EXP | 88 |  |  | 0 | 0 | 0 | 2/11/2013 | 2/11/2013 | 8/8/2014 | Connected |  | N
National Grid | LEICESTER | 646952 | 01524 | 3.8 | Solar | 05_14_43L6 | 01/13/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 636277 | 01602 | 18.525 | Solar | 05_14_60L4 | 08/29/2024 | 09/04/2024 | 3 | 1 | 2 | 09/05/2024 | 09/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 9/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 645132 | 01550 | 1.74 | Solar | 05_14_74L6 | 10/04/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | HUBBARDSTON | 174335 | 01452 | 2000 | Solar | 05_01_21W1 | 01/25/2012 | 01/25/2012 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2012 | 05/16/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 742117 | 02777 | 20 | Solar | 05_01_2J335 | 12/23/2025 | 01/02/2026 | 6 | 4 | 2 | 01/05/2026 | 01/05/2026 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 174717 | 01902 | 52.8 | Solar | 05_01_413L4 | 01/13/2014 | 01/13/2014 | 6 | 0 | 6 | 01/24/2014 | 01/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2014 |  | 3/31/2014 | N | EXP | 6 |  |  | 0 | 0 | 0 | 3/10/2014 | 3/10/2014 | 7/21/2015 | Connected |  | N
National Grid | REVERE | 651918 | 02151 | 12.54 | Solar | 05_01_609W1 | 11/04/2024 | 12/05/2024 | 7 | 2 | 5 | 12/06/2024 | 12/06/2024 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 320884 | 01832 | 10.56 | Solar | 05_05_11W83 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 191643 | 01950 | 10 | Solar | 05_12_29W4 | 07/24/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 175320 | 01844 | 417.6 | Solar | 05_12_7W4 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | SPENCER | 651431 | 01562 | 7.6 | Solar | 05_14_43L6 | 11/13/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/27/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WORCESTER | 201742 | 01602 | 372 | Solar | 05_14_61L1 | 11/21/2018 | 11/29/2018 | 4 | 4 | 0 | 11/30/2018 | 11/30/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 |  | 7/30/2021 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 645336 | 01507 | 7.6 | Solar | 05_14_74L6 | 10/07/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 174573 | 01473 | 1000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 475993 | 02777 | 15.08 | Solar | 05_01_2J335 | 11/09/2022 | 12/07/2022 | 18 | 17 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 2/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | SWAMPSCOTT | 174814 | 01907 | 60 | Solar | 05_01_413L4 | 07/30/2013 | 07/30/2013 | 6 | 0 | 6 | 08/08/2013 | 08/08/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2013 |  | 1/31/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/11/2013 | 12/11/2013 | Connected |  | N
National Grid | REVERE | 665038 | 02151 | 7.25 | Solar | 05_01_609W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | HAVERHILL | 348833 | 01832 | 499 | Solar | 05_05_11W83 | 04/20/2021 | 05/04/2021 | 9 | 0 | 9 |  |  | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 198918 | 01843 | 7.6 | Solar | 05_12_29W4 | 11/05/2018 | 11/05/2018 | 0 | 0 | 0 | 11/06/2018 | 11/06/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 11/05/2018 | 11/5/2020 | Y | EXP | 45 | 11/15/2019 | 11/27/2019 | 12 | 0 | 12 |  |  | 1/16/2020 | Connected |  | N
National Grid | LAWRENCE | 178244 | 01841 | 153.2 | Solar | 05_12_7W4 | 02/20/2018 | 02/20/2018 | 3 | 0 | 3 | 06/14/2018 | 06/14/2018 | 18 | 14 | 4 | 04/04/2018 | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 |  | 06/14/2018 | 51 | 44 | 7 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/31/2021 | N | EXP | 984 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | SPENCER | 652555 | 01562 | 5.76 | Solar | 05_14_43L6 | 11/06/2024 | 12/02/2024 | 6 | 0 | 6 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 285209 | 01609 | 4.08 | Solar | 05_14_61L1 | 05/18/2020 | 05/20/2020 | 1 | 0 | 1 | 05/21/2020 | 05/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/18/2020 | 4/3/2021 | Y | EXP | 365 | 11/17/2020 | 02/08/2021 | 83 | 0 | 83 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 651851 | 01507 | 10 | Solar | 05_14_74L6 | 11/13/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | HUBBARDSTON | 174572 | 01452 | 1000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 523999 | 02777 | 6.09 | Solar | 05_01_2J335 | 09/14/2023 | 09/15/2023 | 1 | 0 | 1 | 09/18/2023 | 09/18/2023 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175237 | 01902 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 66 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | REVERE | 665954 | 02151 | 10 | Solar | 05_01_609W1 | 01/15/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 524644 | 01832 | 0 | Solar | 05_05_11W83 | 05/09/2023 | 05/10/2023 | 1 | 0 | 1 | 05/11/2023 | 05/11/2023 | 197 | 176 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2024 | Connected |  | N
National Grid | LAWRENCE | 206834 | 01843 | 3.8 | Solar | 05_12_29W4 | 02/15/2019 | 02/28/2019 | 7 | 0 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2019 | Connected |  | N
National Grid | METHUEN | 596446 | 01844 | 6 | Solar | 05_12_7W4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | SPENCER | 652542 | 01562 | 4.35 | Solar | 05_14_43L6 | 11/06/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | WORCESTER | 336498 | 01602 | 10 | Solar | 05_14_61L1 | 06/10/2021 | 08/30/2021 | 56 | 55 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 8/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 653191 | 01550 | 10 | Solar | 05_14_74L6 | 11/12/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 2/26/2026 | Y | EXP | 365 | 05/24/2025 | 11/21/2025 | 182 | 0 | 182 |  |  | 11/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 174571 | 01473 | 2000 | Solar | 05_01_21W1 | 10/11/2011 | 10/11/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/20/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2012 | 10/11/2011 | 10/31/2012 | Y | STD | 38 | 04/09/2013 | 06/21/2013 | 50 | 0 | 50 | 6/21/2013 | 6/21/2013 | 8/7/2013 | Connected |  | N
National Grid | SWANSEA | 645982 | 02777 | 8.32 | Solar | 05_01_2J335 | 10/09/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175236 | 01902 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 66 | 01/28/2016 | 04/01/2016 | 44 | 0 | 44 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | REVERE | 668956 | 02151 | 15.2 | Solar | 05_01_609W1 | 01/30/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/30/2025 | 4/3/2026 | Y | EXP | 365 | 06/14/2025 | 11/24/2025 | 164 | 0 | 164 |  |  | 11/25/2025 | Connected |  | N
National Grid | HAVERHILL | 559394 | 01832 | 5 | Solar | 05_05_11W83 | 10/02/2023 | 10/16/2023 | 10 | 7 | 3 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 10/02/2023 | 11/10/2024 | Y | EXP | 365 | 01/12/2024 | 02/21/2024 | 41 | 0 | 41 |  |  | 5/7/2024 | Connected |  | N
National Grid | LAWRENCE | 224995 | 01843 | 3.8 | Solar | 05_12_29W4 | 06/25/2019 | 07/03/2019 | 5 | 0 | 5 | 07/05/2019 | 07/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 657102 | 01844 | 3.8 | Solar | 05_12_7W4 | 12/02/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 653571 | 01562 | 7.6 | Solar | 05_14_43L6 | 11/13/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 450745 | 01602 | 6 | Solar | 05_14_61L1 | 08/15/2022 | 08/31/2022 | 12 | 10 | 2 | 09/01/2022 | 09/01/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2022 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 657035 | 01550 | 7.6 | Solar | 05_14_74L6 | 11/28/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 86 | 25 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HUBBARDSTON | 174617 | 01452 | 22.8 | Solar | 05_01_21W1 | 12/14/2010 | 12/14/2010 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2011 |  | 2/8/2012 | N | EXP | 39 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/8/2012 | Connected |  | N
National Grid | SWANSEA | 662096 | 02777 | 3.8 | Solar | 05_01_2J335 | 12/20/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | SALEM | 175235 | 01970 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 03/11/2015 | 50 | 0 | 50 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 66 | 01/18/2016 | 04/01/2016 | 51 | 0 | 51 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | REVERE | 675973 | 02151 | 5.76 | Solar | 05_01_609W1 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 83 | 67 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 638473 | 01832 | 10 | Solar | 05_05_11W83 | 09/06/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/06/2024 | 12/26/2025 | Y | EXP | 365 | 12/19/2024 | 02/05/2025 | 49 | 0 | 49 |  |  | 3/27/2025 | Connected |  | N
National Grid | LAWRENCE | 241818 | 01843 | 10 | Solar | 05_12_29W4 | 07/12/2019 | 07/24/2019 | 8 | 8 | 0 | 07/25/2019 | 07/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 2/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2019 | Connected |  | N
National Grid | METHUEN | 317386 | 01844 | 10 | Solar | 05_12_96W1 | 01/27/2021 | 02/02/2021 | 3 | 0 | 3 | 02/03/2021 | 02/03/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 3/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 661414 | 01524 | 5.76 | Solar | 05_14_43L6 | 12/18/2024 | 01/03/2025 | 11 | 7 | 4 | 01/06/2025 | 01/06/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WORCESTER | 407121 | 01602 | 7.54 | Solar | 05_14_61L1 | 03/24/2022 | 04/05/2022 | 9 | 7 | 2 | 04/06/2022 | 04/06/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 03/24/2022 | 8/20/2023 | Y | EXP | 365 | 06/08/2022 | 07/14/2022 | 37 | 0 | 37 |  |  | 9/1/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 682135 | 01550 | 20 | Solar | 05_14_74L6 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 175220 | 01473 | 17.5 | Solar | 05_01_21W1 | 11/03/2014 | 11/03/2014 | 6 | 1 | 5 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 1/30/2015 | N | EXP | 77 |  |  | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 3/8/2016 | Connected |  | N
National Grid | SWANSEA | 662500 | 02777 | 9.75 | Solar | 05_01_2J335 | 12/24/2024 | 01/22/2025 | 13 | 11 | 2 | 01/23/2025 | 01/23/2025 | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175264 | 01902 | 480 | Solar | 05_01_413L4 | 06/10/2014 | 06/10/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/16/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/25/2014 | 12/25/2014 | 0 | 0 | 0 | 3/12/2015 | 06/10/2014 | 12/31/2016 | Y | STD | 66 | 03/29/2016 | 04/01/2016 | 3 | 0 | 3 | 3/31/2016 | 3/31/2016 | 4/1/2016 | Connected |  | N
National Grid | WINTHROP | 679660 | 02152 | 7.6 | Solar | 05_01_609W1 | 03/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 662103 | 01832 | 10 | Solar | 05_05_11W83 | 12/20/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/20/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 254139 | 01843 | 10 | Solar | 05_12_29W4 | 10/11/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/11/2019 | 10/19/2021 | Y | EXP | 365 | 05/27/2020 | 06/12/2020 | 16 | 0 | 16 |  |  | 10/21/2020 | Connected |  | N
National Grid | METHUEN | 329452 | 01844 | 7.6 | Solar | 05_12_96W1 | 02/26/2021 | 03/08/2021 | 5 | 0 | 5 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 664963 | 01562 | 9.86 | Solar | 05_14_43L6 | 01/21/2025 | 02/18/2025 | 7 | 2 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/21/2025 | 3/26/2026 | Y | EXP | 365 | 06/12/2025 | 08/19/2025 | 69 | 0 | 69 |  |  | 8/22/2025 | Connected |  | N
National Grid | WORCESTER | 407034 | 01602 | 9.57 | Solar | 05_14_61L1 | 03/24/2022 | 03/28/2022 | 2 | 1 | 1 | 03/29/2022 | 03/29/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 7/13/2023 | N | EXP | 365 | 06/08/2022 | 07/12/2022 | 35 | 0 | 35 |  |  | 7/23/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 705538 | 01550 | 13.68 | Solar | 05_14_75L1 | 07/18/2025 | 09/15/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HUBBARDSTON | 175263 | 01452 | 1000 | Solar | 05_01_21W1 | 01/13/2015 | 01/13/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 02/20/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 667803 | 02777 | 3.8 | Solar | 05_01_2J335 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 115 | 97 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175396 | 01902 | 480 | Solar | 05_01_413L4 | 11/17/2014 | 11/17/2014 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/24/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 688130 | 02152 | 7.6 | Solar | 05_01_609W1 | 04/28/2025 | 07/10/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 662100 | 01832 | 5.76 | Solar | 05_05_11W83 | 12/20/2024 | 02/11/2025 | 4 | 0 | 4 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | LAWRENCE | 290811 | 01843 | 10 | Solar | 05_12_29W4 | 06/26/2020 | 07/06/2020 | 5 | 0 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 330348 | 01850 | 7.6 | Solar | 05_12_96W1 | 12/08/2020 | 12/29/2020 | 13 | 8 | 5 | 12/30/2020 | 12/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 |  | 12/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | LEICESTER | 665201 | 01524 | 3.8 | Solar | 05_14_43L6 | 01/13/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 01/13/2025 | 3/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 530025 | 01602 | 5.85 | Solar | 05_14_61L1 | 06/08/2023 | 06/28/2023 | 14 | 12 | 2 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2023 | Connected |  | N
National Grid | SOUTHBRIDGE | 717529 | 01550 | 7.6 | Solar | 05_14_75L1 | 09/10/2025 | 09/29/2025 | 3 | 0 | 3 | 10/07/2025 | 10/07/2025 | 16 | 1 | 15 | 11/05/2025 | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 12/01/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTMINSTER | 175903 | 01473 | 224 | Solar | 05_01_21W1 | 09/28/2015 | 09/28/2015 | 0 | 0 | 0 | 09/30/2015 | 09/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 | 09/28/2015 | 10/5/2016 | Y | EXP | 33 | 12/23/2015 | 12/28/2015 | 2 | 0 | 2 | 2/17/2016 | 2/17/2016 | 3/24/2016 | Connected |  | N
National Grid | SWANSEA | 671129 | 02777 | 5.76 | Solar | 05_01_2J335 | 02/10/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 106 | 90 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175474 | 01904 | 984 | Solar | 05_01_413L4 | 12/05/2014 | 12/05/2014 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/09/2015 | 18 | 18 | 0 |  |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 39 | 39 | 0 | 2/5/2016 | 12/05/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | WINTHROP | 713491 | 02152 | 11.4 | Solar | 05_01_609W1 | 08/29/2025 | 09/08/2025 | 5 | 0 | 5 | 09/09/2025 | 09/09/2025 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | HAVERHILL | 663923 | 01832 | 7.6 | Solar | 05_05_11W83 | 01/06/2025 | 01/17/2025 | 4 | 0 | 4 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 | 01/06/2025 | 3/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | LAWRENCE | 302539 | 01843 | 10 | Solar | 05_12_29W4 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | DRACUT | 366061 | 01826 | 6 | Solar | 05_12_96W1 | 08/06/2021 | 01/03/2022 | 18 | 16 | 2 | 09/01/2021 | 09/01/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 | 08/06/2021 | 6/8/2023 | Y | EXP | 365 | 02/11/2022 | 03/29/2022 | 47 | 0 | 47 |  |  | 8/16/2022 | Connected |  | Y
National Grid | SPENCER | 681823 | 01562 | 6.5 | Solar | 05_14_43L6 | 04/02/2025 | 04/18/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 72 | 58 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 535614 | 01602 | 3 | Solar | 05_14_61L1 | 07/04/2023 | 07/10/2023 | 4 | 3 | 1 | 07/11/2023 | 07/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 744459 | 01550 | 0 | Solar | 05_14_75L1 | 01/09/2026 | 01/14/2026 | 2 | 1 | 1 | 01/15/2026 | 01/15/2026 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTMINSTER | 175943 | 01473 | 1000 | Solar | 05_01_21W1 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/26/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2015 | 01/21/2015 | 9/28/2018 | Y | STD | 1134 | 04/09/2018 | 08/27/2018 | 130 | 0 | 130 |  |  | 9/6/2018 | Connected |  | N
National Grid | SWANSEA | 682678 | 02777 | 11.4 | Solar | 05_01_2J335 | 04/03/2025 | 04/23/2025 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | LYNN | 175473 | 01904 | 480 | Solar | 05_01_413L4 | 12/02/2014 | 12/02/2014 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 01/09/2015 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 08/11/2015 | 10/05/2015 | 38 | 1 | 37 | 2/5/2016 | 12/02/2014 | 12/31/2017 | Y | STD | 695 | 05/04/2017 | 12/12/2017 | 147 | 0 | 147 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | WINTHROP | 301762 | 02152 | 2300 | Solar | 05_01_609W2 | 07/27/2020 | 08/03/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/04/2020 | 08/28/2020 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HAVERHILL | 667625 | 01832 | 7.6 | Solar | 05_05_11W83 | 01/24/2025 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | LAWRENCE | 313757 | 01843 | 7.83 | Solar | 05_12_29W4 | 10/20/2020 | 10/21/2020 | 0 | 0 | 0 | 10/22/2020 | 10/22/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 | 10/20/2020 | 8/31/2022 | Y | EXP | 365 | 06/30/2021 | 07/26/2021 | 27 | 0 | 27 |  |  | 9/27/2021 | Connected |  | Y
National Grid | LOWELL | 383495 | 01850 | 9.8 | Solar | 05_12_96W1 | 11/09/2021 | 12/20/2021 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 |  | 12/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2022 | Connected |  | Y
National Grid | LEICESTER | 695537 | 01524 | 7.6 | Solar | 05_14_43L6 | 06/04/2025 | 06/16/2025 | 13 | 11 | 2 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2025 |  | 9/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | WORCESTER | 541415 | 01602 | 11.31 | Solar | 05_14_61L1 | 08/14/2023 | 08/28/2023 | 11 | 10 | 1 | 08/29/2023 | 08/29/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 | 08/14/2023 | 10/18/2024 | Y | EXP | 365 | 01/24/2024 | 02/02/2024 | 10 | 0 | 10 |  |  | 2/6/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 178139 | 01550 | 7.6 | Solar | 05_14_75L1 | 03/22/2018 | 03/22/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 3/28/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 8/5/2019 | Connected |  | N
National Grid | WESTMINSTER | 176216 | 01473 | 1000 | Solar | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 743680 | 02777 | 13.36 | Solar | 05_01_2J335 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175559 | 01902 | 480 | Solar | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 695376 | 02152 | 13.96 | Solar | 05_01_609W2 | 06/01/2025 | 10/21/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 71 | 60 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 712019 | 01832 | 7.329 | Solar | 05_05_11W83 | 08/14/2025 | 09/09/2025 | 3 | 0 | 3 | 09/10/2025 | 09/10/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2026 | Connected |  | N
National Grid | LAWRENCE | 451712 | 01843 | 10 | Solar | 05_12_29W4 | 12/19/2022 | 12/20/2022 | 1 | 0 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 | 12/19/2022 | 9/10/2024 | Y | EXP | 365 | 08/09/2023 | 08/29/2023 | 21 | 0 | 21 |  |  | 9/26/2023 | Connected |  | N
National Grid | DRACUT | 533569 | 01826 | 0 | Solar | 05_12_96W1 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | SPENCER | 704610 | 01562 | 480 | Solar | 05_14_43L8 | 10/17/2025 | 10/31/2025 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 | 11/24/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WORCESTER | 549692 | 01602 | 480 | Solar | 05_14_61L1 | 09/01/2023 | 10/12/2023 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 11/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 184581 | 01507 | 15.2 | Solar | 05_14_75L1 | 07/10/2018 | 07/12/2018 | 1 | 0 | 1 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | WESTMINSTER | 176215 | 01473 | 1000 | Solar | 05_01_21W1 | 07/02/2015 | 07/02/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/03/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 | 07/02/2015 | 10/7/2017 | Y | STD | 598 | 10/11/2017 | 12/21/2017 | 44 | 0 | 44 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 323572 | 02777 | 7.92 | Solar | 05_01_2J345 | 11/03/2020 | 12/07/2020 | 21 | 19 | 2 | 12/08/2020 | 12/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 12/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 175558 | 01907 | 480 | Solar | 05_01_413L4 | 07/30/2014 | 07/30/2014 | 7 | 0 | 7 | 08/11/2014 | 08/11/2014 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/3/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 717106 | 02152 | 3.8 | Solar | 05_01_609W2 | 09/11/2025 | 09/26/2025 | 2 | 0 | 2 | 10/20/2025 | 10/20/2025 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 737037 | 01835 | 15.2 | Solar | 05_05_11W83 | 12/01/2025 | 12/08/2025 | 4 | 2 | 2 | 12/09/2025 | 12/09/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 | 12/01/2025 | 1/13/2027 | Y | EXP | 365 | 01/22/2026 | 02/11/2026 | 21 | 0 | 21 |  |  | 3/3/2026 | Connected |  | N
National Grid | LAWRENCE | 391442 | 01840 | 3.8 | Solar | 05_12_29W4 | 11/24/2021 | 01/07/2022 | 13 | 9 | 4 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 | 11/24/2021 | 8/2/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2022 | Connected |  | Y
National Grid | DRACUT | 562542 | 01826 | 10 | Solar | 05_12_96W1 | 10/17/2023 | 10/20/2023 | 4 | 1 | 3 | 10/23/2023 | 10/23/2023 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 |  | 1/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | SPENCER | 174270 | 01562 | 229.68 | Solar | 05_14_43L8 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 6/26/2013 | Connected |  | N
National Grid | WORCESTER | 587226 | 01602 | 6 | Solar | 05_14_61L1 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 187051 | 01507 | 9.92 | Solar | 05_14_75L1 | 06/04/2018 | 06/04/2018 | 8 | 0 | 8 | 06/16/2018 | 06/16/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2019 | Connected |  | N
National Grid | WESTMINSTER | 176203 | 01473 | 3.8 | Solar | 05_01_21W1 | 04/24/2015 | 04/24/2015 | 2 | 2 | 0 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 | 04/24/2015 | 12/31/2016 | Y | EXP | 597 | 06/17/2016 | 06/15/2016 | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 5/26/2016 | Connected |  | N
National Grid | SWANSEA | 657160 | 02777 | 5.76 | Solar | 05_01_2J345 | 11/26/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 175600 | 01970 | 1000 | Solar | 05_01_413L4 | 08/04/2014 | 08/04/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2014 | 09/15/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 08/04/2014 | 7/30/2018 | Y | STD | 98 | 11/28/2016 | 03/28/2017 | 82 | 0 | 82 |  |  | 7/20/2018 | Connected |  | N
National Grid | WINTHROP | 743472 | 02152 | 10 | Solar | 05_01_609W2 | 01/05/2026 | 01/08/2026 | 3 | 0 | 3 | 01/09/2026 | 01/09/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 | 01/05/2026 | 2/9/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | HAVERHILL | 465846 | 01835 | 0 | Other | 05_05_11W84 | 02/17/2023 | 05/03/2023 | 51 | 43 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2023 | 06/07/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 02/17/2023 | 11/24/2026 | Y | STD | 357 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 424741 | 01843 | 220 | Solar | 05_12_29W4 | 05/23/2022 | 06/15/2022 | 17 | 8 | 9 | 06/16/2022 | 06/16/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 588443 | 01826 | 22.8 | Solar | 05_12_96W1 | 08/05/2024 | 08/19/2024 | 10 | 9 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/05/2024 | 9/27/2025 | Y | EXP | 365 | 12/03/2024 | 01/08/2025 | 37 | 0 | 37 |  |  | 1/21/2025 | Connected |  | Y
National Grid | SPENCER | 176413 | 01562 | 92.4 | Solar | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 0 | 5 | 11/20/2015 | 11/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 |  | 11/18/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 3/3/2016 | 3/3/2016 | 3/3/2016 | Connected |  | N
National Grid | WORCESTER | 597488 | 01602 | 10.075 | Solar | 05_14_61L1 | 03/19/2024 | 03/28/2024 | 7 | 5 | 2 | 03/29/2024 | 03/29/2024 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 03/19/2024 | 7/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | CHARLTON | 203291 | 01507 | 3.8 | Solar | 05_14_75L1 | 12/19/2018 | 12/21/2018 | 1 | 0 | 1 | 12/24/2018 | 12/24/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 177040 | 01473 | 2592 | Solar | 05_01_21W1 | 07/27/2016 | 08/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 5/31/2021 | Y | STD | 1251 | 11/05/2020 | 04/15/2021 | 110 | 0 | 110 | 5/3/2021 | 5/26/2021 | 6/15/2021 | Connected |  | N
National Grid | SWANSEA | 677870 | 02777 | 3.839 | Solar | 05_01_2J349 | 03/13/2025 | 04/07/2025 | 11 | 7 | 4 | 04/07/2025 | 04/07/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 175654 | 01970 | 480 | Solar | 05_01_413L4 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 46 | 8 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2014 |  | 10/31/2014 | N | EXP | 128 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 745987 | 02152 | 4.94 | Solar | 05_01_609W2 | 01/16/2026 | 01/21/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 707245 | 01835 | 250 | Solar | 05_05_11W84 | 12/13/2025 |  | 55 | 48 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 429973 | 01843 | 6 | Solar | 05_12_29W4 | 05/27/2022 | 06/02/2022 | 3 | 1 | 2 | 06/03/2022 | 06/03/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 645728 | 01826 | 5.76 | Solar | 05_12_96W1 | 10/08/2024 | 10/29/2024 | 2 | 1 | 1 | 10/31/2024 | 10/31/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/08/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | LEICESTER | 176854 | 01524 | 92.4 | Solar | 05_14_43L8 | 11/12/2015 | 11/12/2015 | 5 | 5 | 0 | 11/20/2015 | 11/20/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2015 | 11/12/2015 | 11/18/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 608292 | 01603 | 7.6 | Solar | 05_14_61L1 | 05/02/2024 | 05/21/2024 | 3 | 0 | 3 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | CHARLTON | 317751 | 01507 | 9.6 | Solar | 05_14_75L1 | 10/20/2020 | 12/15/2020 | 38 | 37 | 1 | 12/16/2020 | 12/16/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 177038 | 01473 | 800 | Solar | 05_01_21W1 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 534979 | 02725 | 14.21 | Solar | 05_01_2J349 | 06/19/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2023 |  | 8/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | LYNN | 176353 | 01904 | 2500 | Solar | 05_01_413L4 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2015 | 06/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 11/25/2015 | 12/23/2015 | 19 | 0 | 19 | 12/23/2015 | 05/15/2015 | 10/30/2015 | Y | STD | 54 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | WINTHROP | 748805 | 02152 | 17.6 | Solar | 05_01_609W2 | 02/02/2026 | 02/03/2026 | 1 | 0 | 1 | 02/04/2026 | 02/04/2026 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 732923 | 01835 | 998.9 | Solar | 05_05_11W84 | 01/07/2026 |  | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 435355 | 01843 | 7.6 | Solar | 05_12_29W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 242 | 216 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 657458 | 01850 | 3.8 | Solar | 05_12_96W1 | 11/27/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | LEICESTER | 185057 | 01524 | 250 | Solar | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 2 | 0 | 2 | 05/17/2018 | 05/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 618440 | 01603 | 10 | Solar | 05_14_61L1 | 06/17/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 06/17/2024 | 7/23/2025 | Y | EXP | 365 | 08/09/2024 | 10/21/2024 | 74 | 0 | 74 |  |  | 10/25/2024 | Connected |  | N
National Grid | CHARLTON | 330115 | 01507 | 5.76 | Solar | 05_14_75L1 | 12/14/2020 | 02/12/2021 | 41 | 38 | 3 | 02/16/2021 | 02/16/2021 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2021 | 12/14/2020 | 9/2/2022 | Y | EXP | 365 | 05/28/2021 | 09/01/2021 | 95 | 3 | 92 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 177271 | 01473 | 40 | Solar | 05_01_21W1 | 11/14/2016 | 11/14/2016 | 1 | 1 | 0 | 11/16/2016 | 11/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2016 |  | 11/20/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 2/17/2017 | 2/17/2017 | 2/16/2017 | Connected |  | N
National Grid | SWANSEA | 661625 | 02777 | 3.8 | Solar | 05_01_2J349 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176661 | 01970 | 720 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2016 | 06/02/2016 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174115 | 02152 | 2000 | Solar | 05_01_609W2 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 742250 | 01835 | 10 | Solar | 05_05_11W84 | 12/26/2025 | 12/30/2025 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 | 12/26/2025 | 2/13/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 448048 | 01843 | 6 | Solar | 05_12_29W4 | 08/15/2022 | 08/23/2022 | 7 | 6 | 1 | 08/24/2022 | 08/24/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 |  | 10/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | LOWELL | 658693 | 01850 | 5.76 | Solar | 05_12_96W1 | 12/05/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | SPENCER | 184923 | 01562 | 250 | Solar | 05_14_43L8 | 05/10/2018 | 05/10/2018 | 6 | 0 | 6 | 05/18/2018 | 05/18/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2019 | Connected |  | N
National Grid | WORCESTER | 627408 | 01603 | 12.16 | Solar | 05_14_61L1 | 07/24/2024 | 08/01/2024 | 2 | 1 | 1 | 08/02/2024 | 08/02/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 382184 | 01550 | 16.56 | Solar | 05_14_75L1 | 09/15/2021 | 09/17/2021 | 2 | 0 | 2 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | WESTMINSTER | 177846 | 01473 | 1460 | Solar | 05_01_21W1 | 10/17/2017 | 10/17/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 698530 | 02725 | 11.4 | Solar | 05_01_2J353 | 06/27/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SALEM | 176659 | 01970 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174702 | 02152 | 13.5 | Solar | 05_01_609W2 | 01/03/2013 | 01/03/2013 | 16 | 9 | 7 | 01/29/2013 | 01/29/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2013 |  | 3/29/2013 | N | EXP | 55 |  |  | 0 | 0 | 0 | 6/5/2013 | 6/5/2013 | 8/15/2013 | Connected |  | N
National Grid | HAVERHILL | 751362 | 01835 | 11.5 | Solar | 05_05_11W84 | 02/16/2026 | 02/20/2026 | 2 | 0 | 2 | 03/09/2026 | 03/09/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 520372 | 01843 | 6 | Solar | 05_12_29W4 | 04/28/2023 | 05/02/2023 | 3 | 1 | 2 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 672877 | 01850 | 5.76 | Solar | 05_12_96W1 | 02/19/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/19/2025 | 5/16/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | LEICESTER | 194214 | 01542 | 100 | Solar | 05_14_43L8 | 10/15/2018 | 10/15/2018 | 0 | 0 | 0 | 10/16/2018 | 10/16/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 632220 | 01602 | 6 | Solar | 05_14_61L1 | 08/20/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/20/2024 | 1/18/2026 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 383819 | 01550 | 9.8 | Solar | 05_14_75L1 | 10/14/2021 | 12/16/2021 | 4 | 0 | 4 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 178344 | 01473 | 498 | Solar | 05_01_21W1 | 01/11/2018 | 02/12/2018 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2018 | 03/01/2018 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 619089 | 02777 | 5.76 | Solar | 05_01_2J353 | 06/19/2024 | 06/26/2024 | 0 | 0 | 0 | 06/27/2024 | 06/27/2024 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176693 | 01902 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 174879 | 02152 | 1800 | Solar | 05_01_609W2 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 751305 | 01835 | 10 | Solar | 05_05_11W84 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 536037 | 01843 | 3.8 | Solar | 05_12_29W4 | 08/21/2023 | 08/29/2023 | 7 | 5 | 2 | 08/30/2023 | 08/30/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  | 11/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | DRACUT | 644686 | 01826 | 3.8 | Solar | 05_12_9C1 | 10/03/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | Y
National Grid | LEICESTER | 194210 | 01524 | 120 | Solar | 05_14_43L8 | 08/22/2018 | 10/15/2018 | 36 | 0 | 36 | 10/16/2018 | 10/16/2018 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 640683 | 01602 | 4.16 | Solar | 05_14_61L1 | 09/17/2024 | 10/23/2024 | 20 | 17 | 3 | 10/24/2024 | 10/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 12/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | SOUTHBRIDGE | 543272 | 01550 | 160 | Solar | 05_14_75L1 | 08/01/2023 | 08/21/2023 | 14 | 3 | 11 | 08/22/2023 | 08/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 08/01/2023 | 12/31/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 192241 | 01473 | 10 | Solar | 05_01_21W1 | 07/30/2018 | 09/27/2018 | 24 | 23 | 1 | 09/28/2018 | 09/28/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 661853 | 02777 | 5.76 | Solar | 05_01_2J353 | 12/19/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | Y
National Grid | LYNN | 176692 | 01904 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 176737 | 02155 | 496 | Solar | 05_01_609W2 | 10/29/2015 | 10/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2015 | 12/04/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 11/3/2016 | N | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174266 | 01835 | 26 | Solar | 05_05_11W84 | 12/28/2011 | 12/28/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2012 |  | 2/25/2012 | N | EXP | 47 |  |  | 0 | 0 | 0 | 5/8/2012 | 5/8/2012 | 5/16/2012 | Connected |  | N
National Grid | LAWRENCE | 553302 | 01843 | 5 | Solar | 05_12_29W4 | 09/18/2023 | 10/02/2023 | 10 | 8 | 2 | 10/03/2023 | 10/03/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 178026 | 01850 | 166.75 | Solar | 05_12_9C2 | 08/31/2017 | 08/31/2017 | 21 | 20 | 1 | 10/03/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2017 |  | 12/16/2019 | N | EXP | 84 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | SPENCER | 194207 | 01562 | 180 | Solar | 05_14_43L8 | 08/22/2018 | 08/29/2018 | 4 | 0 | 4 | 08/30/2018 | 08/30/2018 | 149 | 0 | 149 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 652584 | 01602 | 3.8 | Solar | 05_14_61L1 | 11/14/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 543762 | 01550 | 220 | Solar | 05_14_75L1 | 07/31/2023 | 08/17/2023 | 13 | 4 | 9 | 08/18/2023 | 08/18/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 07/31/2023 | 12/31/2025 | Y | EXP | 119 | 06/19/2025 | 06/18/2025 | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 192732 | 01473 | 4580 | Solar | 05_01_21W1 | 08/06/2018 | 08/27/2018 | 256 | 20 | 236 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/24/2018 | 10/17/2018 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 692871 | 02725 | 9.28 | Solar | 05_01_2J353 | 05/20/2025 | 06/04/2025 | 2 | 0 | 2 | 06/05/2025 | 06/05/2025 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | LYNN | 176691 | 01904 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/26/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 178301 | 02155 | 1440 | Solar | 05_01_609W2 | 11/16/2017 | 11/16/2017 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/21/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174457 | 01835 | 623 | Solar | 05_05_11W84 | 10/13/2011 | 10/13/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2011 | 12/01/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 | 10/13/2011 | 10/31/2012 | Y | STD | 33 |  |  | 0 | 0 | 0 | 5/30/2013 | 5/30/2013 | 6/13/2013 | Connected |  | N
National Grid | LAWRENCE | 560742 | 01843 | 10 | Solar | 05_12_29W4 | 10/11/2023 | 10/13/2023 | 3 | 2 | 1 | 10/16/2023 | 10/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 1/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | LOWELL | 225166 | 01850 | 0 | Other | 05_12_9C2 | 05/07/2019 | 07/02/2019 | 8 | 7 | 1 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 05/07/2019 | 2/6/2022 | Y | STD | 14 | 07/23/2021 | 07/22/2021 | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | LEICESTER | 194203 | 01524 | 240 | Solar | 05_14_43L8 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 659408 | 01602 | 10 | Solar | 05_14_61L1 | 12/09/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 553986 | 01550 | 10 | Solar | 05_14_75L1 | 09/21/2023 | 10/23/2023 | 22 | 20 | 2 | 10/24/2023 | 10/24/2023 | 90 | 75 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 199985 | 01473 | 7.6 | Solar | 05_01_21W1 | 11/01/2018 | 12/31/2018 | 8 | 0 | 8 | 01/02/2019 | 01/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 728739 | 02725 | 17.6 | Solar | 05_01_2J393 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 53 | 24 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWAMPSCOTT | 176732 | 01902 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 04/20/2016 | 12/31/2020 | Y | STD | 384 | 08/22/2020 | 11/25/2020 | 95 | 0 | 95 | 12/3/2020 | 12/10/2020 | 12/31/2020 | Connected |  | N
National Grid | MEDFORD | 178331 | 02155 | 3000 | Solar | 05_01_609W2 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/19/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 | 11/16/2017 | 3/26/2021 | Y | STD | 564 | 06/05/2020 | 03/05/2021 | 273 | 41 | 232 | 2/18/2021 | 3/4/2021 | 3/12/2021 | Connected |  | N
National Grid | HAVERHILL | 174646 | 01835 | 3000 | Solar | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/17/2013 | 6/30/2014 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 568043 | 01843 | 60 | Solar | 05_12_29W4 | 06/12/2024 | 07/09/2024 | 17 | 9 | 8 | 07/10/2024 | 07/10/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | LOWELL | 290620 | 01850 | 60 | Solar | 05_12_9C2 | 06/05/2020 | 08/10/2020 | 46 | 39 | 7 | 08/11/2020 | 08/11/2020 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 5/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2021 | Connected |  | N
National Grid | LEICESTER | 194190 | 01524 | 240 | Solar | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 661281 | 01610 | 10 | Solar | 05_14_61L1 | 12/17/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 592767 | 01550 | 10 | Solar | 05_14_75L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 200549 | 01473 | 363.2 | Solar | 05_01_21W1 | 04/09/2019 | 06/29/2019 | 22 | 21 | 1 | 07/01/2019 | 07/01/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 648206 | 02726 | 5.76 | Solar | 05_01_2J393 | 10/30/2024 |  | 75 | 71 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 176731 | 01970 | 999 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/02/2016 | 26 | 15 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 | 04/20/2016 | 12/31/2020 | Y | STD | 889 | 08/22/2020 | 12/03/2020 | 103 | 0 | 103 | 12/14/2020 | 12/16/2020 | 12/30/2020 | Connected |  | N
National Grid | MEDFORD | 272136 | 02155 | 5000 | Other | 05_01_609W2 | 03/03/2020 | 03/17/2020 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174647 | 01835 | 3000 | Solar | 05_05_11W84 | 12/17/2013 | 12/17/2013 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2014 | 02/07/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 572629 | 01843 | 10 | Solar | 05_12_29W4 | 12/01/2023 | 12/04/2023 | 1 | 0 | 1 | 12/05/2023 | 12/05/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 12/01/2023 | 1/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | DRACUT | 409266 | 01826 | 17.11 | Solar | 05_12_9C3 | 03/15/2022 | 03/24/2022 | 7 | 2 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | Connected |  | N
National Grid | SPENCER | 193992 | 01562 | 650 | Solar | 05_14_43L8 | 09/11/2018 | 10/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 01/31/2019 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 666707 | 01602 | 7.6 | Solar | 05_14_61L1 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 617236 | 01550 | 10 | Solar | 05_14_75L1 | 06/11/2024 | 06/26/2024 | 1 | 0 | 1 | 06/27/2024 | 06/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | WESTMINSTER | 289979 | 01473 | 0 | Other | 05_01_21W1 | 01/14/2021 | 02/25/2021 | 27 | 18 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 649074 | 02726 | 5.584 | Solar | 05_01_2J393 | 10/23/2024 | 01/01/2025 | 31 | 26 | 5 | 01/02/2025 | 01/02/2025 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 176767 | 01902 | 936 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2019 | 04/20/2016 | 12/18/2020 | Y | STD | 461 | 07/08/2020 | 10/14/2020 | 99 | 5 | 94 |  |  | 12/16/2020 | Connected |  | N
National Grid | MEDFORD | 310476 | 02155 | 10 | Hydro | 05_01_609W2 | 09/03/2020 | 10/07/2020 | 23 | 17 | 6 | 10/08/2020 | 10/08/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | HAVERHILL | 174875 | 01835 | 3000 | Solar | 05_05_11W84 | 09/11/2012 | 09/11/2012 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2012 | 12/24/2012 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/14/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 576101 | 01843 | 6 | Solar | 05_12_29W4 | 12/19/2023 |  | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 175106 | 01826 | 20 | Solar | 05_12_9C4 | 04/18/2013 | 04/18/2013 | 6 | 0 | 6 | 04/30/2013 | 04/30/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2013 |  | 6/21/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 10/28/2013 | 10/28/2013 | 11/12/2013 | Connected |  | N
National Grid | LEICESTER | 194241 | 01524 | 120 | Solar | 05_14_43L8 | 08/23/2018 | 08/29/2018 | 3 | 0 | 3 | 08/30/2018 | 08/30/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 696253 | 01602 | 7.6 | Solar | 05_14_61L1 | 06/05/2025 | 07/08/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 06/05/2025 | 8/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 627744 | 01550 | 10 | Solar | 05_14_75L1 | 07/25/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 | 07/25/2024 | 9/26/2025 | Y | EXP | 365 | 11/01/2024 | 11/08/2024 | 8 | 0 | 8 |  |  | 12/6/2024 | Connected |  | N
National Grid | WESTMINSTER | 306359 | 01473 | 5 | Solar | 05_01_21W1 | 09/10/2020 | 10/06/2020 | 17 | 14 | 3 | 10/07/2020 | 10/07/2020 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/10/2020 | 12/24/2021 | Y | EXP | 365 | 11/09/2021 | 01/25/2022 | 78 | 0 | 78 |  |  | 2/12/2022 | Connected |  | N
National Grid | SWANSEA | 649633 | 02777 | 4.93 | Solar | 05_01_2J393 | 10/25/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 18 | 0 | 18 | 12/17/2024 | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 |  | 08/26/2025 | 173 | 108 | 65 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 176766 | 01970 | 1872 | Solar | 05_01_413L4 | 04/20/2016 | 04/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2016 | 06/02/2016 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 311776 | 02155 | 4990 | Solar | 05_01_609W2 | 10/05/2020 | 10/14/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2020 | 11/09/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 175126 | 01835 | 1656 | Solar | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2013 | 08/20/2012 | 9/8/2017 | Y | STD | 1456 | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 | 8/29/2017 | 8/29/2017 | 8/31/2017 | Connected |  | N
National Grid | LAWRENCE | 599284 | 01843 | 0 | Battery Add-On | 05_12_29W4 | 03/25/2024 | 03/28/2024 | 3 | 1 | 2 | 03/29/2024 | 03/29/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2024 | 03/25/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | LOWELL | 177371 | 01850 | 60 | Solar | 05_12_9C4 | 09/06/2016 | 09/06/2016 | 5 | 5 | 0 | 09/14/2016 | 09/14/2016 | 46 | 45 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/13/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 194218 | 01524 | 300 | Solar | 05_14_43L8 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 | 08/29/2018 | 08/29/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 699828 | 01610 | 240 | Solar | 05_14_61L2 | 08/18/2025 | 09/04/2025 | 10 | 4 | 6 | 09/05/2025 | 09/05/2025 | 34 | 16 | 18 | 11/18/2025 | 02/12/2026 | 59 | 0 | 59 |  |  | 0 | 0 | 0 |  | 02/12/2026 | 59 | 0 | 59 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOUTHBRIDGE | 640887 | 01550 | 5.76 | Solar | 05_14_75L1 | 09/17/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 307858 | 01473 | 15.2 | Solar | 05_01_21W1 | 08/27/2020 | 09/01/2020 | 2 | 0 | 2 | 09/02/2020 | 09/02/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/27/2020 | 11/15/2023 | Y | EXP |  | 06/16/2021 | 01/17/2022 | 216 | 7 | 209 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 654942 | 02777 | 5.76 | Solar | 05_01_2J393 | 11/18/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 122 | 100 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 177502 | 01902 | 2000 |  | 05_01_413L4 | 03/06/2017 | 03/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 356001 | 02155 | 7.68 | Solar | 05_01_609W2 | 05/03/2021 | 05/04/2021 | 0 | 0 | 0 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 5/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | HAVERHILL | 175105 | 01835 | 400 | Solar | 05_05_11W84 | 04/08/2013 | 04/08/2013 | 7 | 2 | 5 | 04/22/2013 | 04/22/2013 | 361 | 0 | 361 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 607416 | 01845 | 0 | Battery Add-On | 05_12_29W4 | 04/29/2024 | 05/23/2024 | 18 | 14 | 4 | 05/24/2024 | 05/24/2024 | 56 | 41 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 248807 | 01850 | 216 | Solar | 05_12_9C4 | 08/14/2019 | 08/30/2019 | 11 | 4 | 7 | 09/03/2019 | 09/03/2019 | 18 | 9 | 9 | 10/09/2019 | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 12/6/2019 | 08/14/2019 | 4/1/2022 | Y | EXP | 43 | 05/07/2021 | 05/14/2021 | 7 | 0 | 7 |  |  | 2/9/2022 | Connected |  | N
National Grid | SPENCER | 195374 | 01562 | 240 | Solar | 05_14_43L8 | 09/12/2018 | 09/21/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175960 | 01602 | 227 | Solar | 05_14_61L2 | 06/04/2015 | 06/04/2015 | 2 | 2 | 0 | 06/08/2015 | 06/08/2015 | 418 | 0 | 418 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 | 06/04/2015 | 6/30/2016 | Y | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 646841 | 01550 | 3.8 | Solar | 05_14_75L1 | 10/29/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | WESTMINSTER | 337144 | 01473 | 1100 | Solar | 05_01_21W1 | 05/14/2021 | 06/23/2021 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/23/2021 | 10/14/2022 | 288 | 171 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 655707 | 02777 | 3.8 | Solar | 05_01_2J393 | 11/20/2024 | 12/06/2024 | 6 | 1 | 5 | 12/09/2024 | 12/09/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 178044 | 01902 | 4900 | Solar | 05_01_413L4 | 05/04/2017 | 05/04/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2017 | 06/02/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/10/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 371839 | 02155 | 15.2 | Solar | 05_01_609W2 | 07/23/2021 | 07/28/2021 | 4 | 3 | 1 | 07/29/2021 | 07/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2022 | Connected |  | N
National Grid | HAVERHILL | 175127 | 01835 | 1760 | Solar | 05_05_11W84 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2012 | 12/24/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 615475 | 01843 | 6 | Solar | 05_12_29W4 | 06/04/2024 | 06/17/2024 | 4 | 0 | 4 | 06/18/2024 | 06/18/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | LOWELL | 562890 | 01850 | 6.96 | Solar | 05_12_9C6 | 12/01/2023 | 12/06/2023 | 4 | 2 | 2 | 12/07/2023 | 12/07/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 12/01/2023 | 1/18/2025 | Y | EXP | 365 | 04/25/2024 | 10/07/2024 | 166 | 0 | 166 |  |  | 8/4/2024 | Connected |  | N
National Grid | LEICESTER | 250814 | 01524 | 230.4 | Solar | 05_14_43L8 | 09/05/2019 | 10/07/2019 | 21 | 17 | 4 | 10/08/2019 | 10/08/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 4/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176749 | 01602 | 6.45 | Solar | 05_14_61L2 | 01/11/2016 | 01/11/2016 | 5 | 5 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 | 01/11/2016 | 1/17/2017 | Y | EXP | 343 | 07/07/2016 | 08/01/2016 | 17 | 0 | 17 | 10/21/2016 | 10/21/2016 | 10/25/2016 | Connected |  | N
National Grid | CHARLTON | 656241 | 01507 | 5.76 | Solar | 05_14_75L1 | 11/22/2024 | 12/30/2024 | 2 | 0 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | WESTMINSTER | 341311 | 01473 | 13.8 | Solar | 05_01_21W1 | 02/09/2021 | 03/08/2021 | 17 | 14 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 9/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 744323 | 02777 | 11.5 | Solar | 05_01_304W2 | 01/09/2026 | 01/12/2026 | 3 | 0 | 3 | 01/27/2026 | 01/27/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 | 01/09/2026 | 2/10/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LYNN | 198216 | 01904 | 3000 | Solar | 05_01_413L4 | 08/13/2020 | 10/15/2020 | 42 | 40 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 11/10/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/13/2020 | 2/16/2025 | Y | STD | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 373050 | 02155 | 7.68 | Solar | 05_01_609W2 | 08/05/2021 | 08/27/2021 | 17 | 16 | 1 | 08/30/2021 | 08/30/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 |  | 1/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2022 | Connected |  | N
National Grid | HAVERHILL | 175229 | 01835 | 483 | Solar | 05_05_11W84 | 01/07/2015 | 01/07/2015 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 5/31/2015 | N | STD | 36 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 | 2/1/2016 | Connected |  | N
National Grid | LAWRENCE | 649937 | 01843 | 7.6 | Solar | 05_12_29W4 | 10/29/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | DRACUT | 603258 | 01826 | 200 | Solar | 05_12_9J1 | 05/13/2024 | 08/09/2024 | 61 | 53 | 8 |  |  | 57 | 51 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 | 05/13/2024 | 4/5/2026 | Y | STD | 147 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | SPENCER | 196059 | 01562 | 2000 | Solar | 05_14_47L1 | 09/21/2018 | 11/07/2018 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2018 | 01/07/2019 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 | 09/21/2018 | 4/14/2026 | Y | STD | 553 | 12/10/2024 |  | 452 | 278 | 174 |  |  |  | Construction |  | N
National Grid | GRAFTON | 206222 | 01519 | 3.8 | Solar | 05_14_61L2 | 02/11/2019 | 02/20/2019 | 5 | 0 | 5 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 656128 | 01550 | 3.8 | Solar | 05_14_75L1 | 11/23/2024 | 01/27/2025 | 7 | 2 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/23/2024 | 3/18/2026 | Y | EXP | 365 | 05/16/2025 | 10/01/2025 | 139 | 0 | 139 |  |  | 6/14/2025 | Connected |  | N
National Grid | WESTMINSTER | 449868 | 01473 | 10 | Solar | 05_01_21W1 | 12/29/2022 | 01/04/2023 | 3 | 0 | 3 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 174551 | 02777 | 1500 | Solar | 05_01_304W2 | 11/16/2011 | 11/16/2011 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2012 | 02/27/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2012 | 11/16/2011 | 10/31/2012 | Y | STD | 62 | 08/08/2013 | 10/18/2013 | 49 | 0 | 49 | 9/24/2013 | 9/24/2013 | 10/11/2013 | Connected |  | N
National Grid | LYNN | 265989 | 01904 | 0 | Other | 05_01_413L4 | 02/27/2020 | 03/17/2020 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2020 | 04/02/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/27/2020 |  | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 413977 | 01907 | 13.05 | Solar | 05_01_609W2 | 06/28/2022 | 07/01/2022 | 3 | 0 | 3 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/28/2022 | 1/18/2024 | Y | EXP | 365 | 01/07/2023 | 01/14/2023 | 8 | 0 | 8 |  |  | 6/29/2023 | Connected |  | N
National Grid | HAVERHILL | 175247 | 01830 | 999 | Solar | 05_05_11W84 | 11/04/2014 | 11/04/2014 | 21 | 19 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2014 | 01/05/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  | 03/14/2017 | 08/29/2017 | 117 | 0 | 117 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 653916 | 01843 | 3.8 | Solar | 05_12_29W4 | 11/15/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/15/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | LOWELL | 619859 | 01850 | 7.6 | Solar | 05_12_9J1 | 06/25/2024 | 06/27/2024 | 4 | 0 | 4 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 | 06/25/2024 | 1/30/2027 | Y | EXP | 73 | 10/01/2025 | 10/18/2025 | 18 | 0 | 18 |  |  |  | Completion Documents |  | Y
National Grid | LEICESTER | 413785 | 01524 | 312.5 | Solar | 05_14_47L1 | 12/01/2022 | 07/12/2023 | 151 | 144 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2023 | 09/15/2023 | 46 | 28 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 | 12/01/2022 | 7/16/2026 | Y | STD | 38 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRAFTON | 318215 | 01519 | 7.6 | Solar | 05_14_61L2 | 10/28/2020 | 11/02/2020 | 2 | 0 | 2 | 11/03/2020 | 11/03/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 657304 | 01507 | 3.8 | Solar | 05_14_75L1 | 11/27/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WESTMINSTER | 452991 | 01473 | 10 | Solar | 05_01_21W1 | 11/02/2022 | 11/09/2022 | 6 | 4 | 2 | 11/10/2022 | 11/10/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/02/2022 | 8/5/2024 | Y | EXP | 365 | 06/16/2023 | 08/03/2023 | 49 | 0 | 49 |  |  | 8/29/2023 | Connected |  | N
National Grid | SWANSEA | 175211 | 02777 | 12.255 | Solar | 05_01_304W2 | 12/04/2012 | 12/04/2012 | 11 | 8 | 3 | 12/21/2012 | 12/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 2/28/2013 | N | EXP | 8 |  |  | 0 | 0 | 0 | 3/8/2013 | 3/8/2013 | 4/22/2013 | Connected |  | N
National Grid | LYNN | 281257 | 01902 | 0 | Other | 05_01_413L4 | 03/17/2020 | 04/24/2020 | 27 | 27 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/09/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/17/2020 | 3/5/2025 | Y | STD | 665 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 461669 | 01907 | 7.68 | Solar | 05_01_609W2 | 10/05/2022 | 10/10/2022 | 3 | 0 | 3 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 10/05/2022 |  | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 175392 | 01985 | 19.13 | Solar | 05_05_11W84 | 09/15/2014 | 09/15/2014 | 13 | 5 | 8 | 10/03/2014 | 10/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2014 |  | 11/28/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 11/20/2015 | Connected |  | N
National Grid | LAWRENCE | 655303 | 01843 | 10 | Solar | 05_12_29W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/19/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | DRACUT | 566018 | 01826 | 200 | Solar | 05_12_9J1 | 11/15/2023 | 12/08/2023 | 16 | 6 | 10 | 12/11/2023 | 12/11/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 174888 | 01562 | 630 | Solar | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2013 | 11/16/2012 | 6/30/2014 | Y | STD | 294 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 426133 | 01590 | 4.06 | Solar | 05_14_61L2 | 04/28/2022 | 05/05/2022 | 5 | 2 | 3 | 05/06/2022 | 05/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 04/28/2022 | 1/3/2024 | Y | EXP | 365 | 12/22/2022 | 01/03/2023 | 13 | 0 | 13 |  |  | 1/7/2023 | Connected |  | N
National Grid | CHARLTON | 662567 | 01507 | 10 | Solar | 05_14_75L1 | 12/26/2024 | 01/21/2025 | 10 | 8 | 2 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/26/2024 | 3/7/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 12/4/2025 | Connected |  | N
National Grid | WESTMINSTER | 367365 | 01473 | 3.8 | Solar | 05_01_21W1 | 07/08/2021 | 07/13/2021 | 3 | 0 | 3 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2022 | Connected |  | N
National Grid | SWANSEA | 175576 | 02777 | 20 | Solar | 05_01_304W2 | 12/09/2014 | 12/09/2014 | 4 | 2 | 2 | 12/16/2014 | 12/16/2014 | 223 | 0 | 223 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2014 |  | 2/28/2015 | N | EXP | 74 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | N
National Grid | LYNN | 280097 | 01904 | 8.64 | Solar | 05_01_413L4 | 02/19/2020 | 02/25/2020 | 3 | 0 | 3 | 02/26/2020 | 02/26/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2020 | 02/19/2020 | 2/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 473722 | 01907 | 8.99 | Solar | 05_01_609W2 | 11/23/2022 | 11/29/2022 | 3 | 1 | 2 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 | 11/23/2022 | 6/8/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 6/16/2023 | Connected |  | Y
National Grid | HAVERHILL | 175810 | 01830 | 5 | Solar | 05_05_11W84 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2015 |  | 10/30/2015 | N | EXP | 143 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 663743 | 01843 | 5.76 | Solar | 05_12_29W4 | 01/03/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/03/2025 | 3/11/2026 | Y | EXP | 365 | 06/26/2025 | 06/28/2025 | 3 | 0 | 3 |  |  | 7/18/2025 | Connected |  | N
National Grid | LOWELL | 175171 | 01850 | 800 | Solar | 05_14_47L1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2012 | 03/05/2013 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 11/16/2012 | 12/31/2016 | Y | STD | 1237 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 501424 | 01562 | 10 | Solar | 05_14_61L2 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 |  | 8/21/2024 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 663641 | 01590 | 15.2 | Solar | 05_14_75L1 | 01/06/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | CHARLTON | 382477 | 01507 | 15.2 | Solar | 05_01_21W1 | 09/29/2021 | 12/29/2021 | 22 | 19 | 3 | 11/02/2021 | 11/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 12/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2022 | Connected |  | N
National Grid | WESTMINSTER | 175728 | 01473 | 1000 | Solar | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 282050 | 02725 | 4950 | Other | 05_01_413L4 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 485301 | 01970 | 11.4 | Solar | 05_01_609W2 | 12/28/2022 |  | 136 | 59 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 175851 | 01907 | 17.6 | Solar | 05_05_11W84 | 05/20/2015 | 05/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 675838 | 01830 | 15.2 | Solar | 05_12_29W4 | 03/05/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 66 | 44 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 625493 | 01843 | 200 | Solar | 05_12_9J1 | 08/06/2024 | 10/14/2024 | 48 | 38 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 175806 | 01850 | 27.6 | Solar | 05_14_47L1 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2015 | 05/15/2015 | 12/31/2016 | Y | EXP | 576 | 05/10/2016 | 05/13/2016 | 3 | 0 | 3 | 7/20/2015 | 7/20/2015 | 7/15/2016 | Connected |  | N
National Grid | SPENCER | 533130 | 01562 | 3.8 | Solar | 05_14_61L2 | 06/14/2023 | 06/15/2023 | 1 | 0 | 1 | 06/16/2023 | 06/16/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 664382 | 01519 | 3.8 | Solar | 05_14_75L1 | 01/08/2025 | 01/15/2025 | 2 | 0 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | CHARLTON | 520923 | 01507 | 0 | Solar | 05_01_21W1 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 349 | 196 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 175727 | 01473 | 1000 | Solar | 05_01_304W2 | 06/02/2014 | 06/02/2014 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 416620 | 02777 | 10 | Solar | 05_01_413L4 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 | 03/14/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2023 | Connected |  | N
National Grid | LYNN | 557260 | 01902 | 0 | Solar | 05_01_609W2 | 09/21/2023 | 10/06/2023 | 11 | 10 | 1 | 10/10/2023 | 10/10/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 175880 | 01907 | 450 | Solar | 05_05_11W84 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 101 | 6 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 680507 | 01985 | 10 | Solar | 05_12_29W4 | 04/09/2025 | 04/29/2025 | 13 | 11 | 2 | 05/21/2025 | 05/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 289689 | 01843 | 12.96 | Solar | 05_12_9J2 | 04/28/2020 | 05/05/2020 | 4 | 1 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | LOWELL | 176540 | 01850 | 1250 | Solar | 05_14_47L1 | 02/10/2016 | 02/10/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/16/2016 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 |  | 2/16/2017 | N | STD | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 552329 | 01524 | 7.6 | Solar | 05_14_61L2 | 09/01/2023 | 09/08/2023 | 5 | 2 | 3 | 09/11/2023 | 09/11/2023 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/01/2023 | 12/2/2024 | Y | EXP | 365 | 03/26/2024 | 05/15/2024 | 51 | 0 | 51 |  |  | 5/21/2024 | Connected |  | N
National Grid | GRAFTON | 667677 | 01519 | 3.8 | Solar | 05_14_75L1 | 01/24/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/24/2025 | 4/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | SOUTHBRIDGE | 536765 | 01550 | 13.8 | Solar | 05_01_21W1 | 07/11/2023 | 11/07/2023 | 82 | 72 | 10 | 11/08/2023 | 11/08/2023 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176224 | 01473 | 7.6 | Solar | 05_01_304W2 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 560222 | 02777 | 7.749 | Solar | 05_01_413L4 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 11/01/2023 | 2/3/2025 | Y | EXP | 365 | 04/18/2024 | 05/29/2024 | 42 | 0 | 42 |  |  | 7/4/2024 | Connected |  | N
National Grid | LYNN | 605267 | 01904 | 20 | Solar | 05_01_609W2 | 04/24/2024 | 05/01/2024 | 5 | 4 | 1 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 176059 | 01907 | 980 | Solar | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/7/2015 | N | STD |  | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 695694 | 01830 | 12.48 | Solar | 05_12_29W4 | 06/03/2025 | 07/14/2025 | 3 | 1 | 2 | 07/21/2025 | 07/21/2025 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 309022 | 01843 | 7.6 | Solar | 05_12_9J2 | 08/26/2020 | 08/27/2020 | 0 | 0 | 0 | 08/28/2020 | 08/28/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | LOWELL | 177495 | 01850 | 12.2 | Solar | 05_14_47L1 | 12/13/2016 | 12/13/2016 | 4 | 4 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/13/2016 | 12/19/2017 | Y | EXP | 363 | 07/05/2017 | 07/24/2017 | 13 | 0 | 13 | 11/13/2017 | 11/13/2017 | 9/25/2017 | Connected |  | N
National Grid | LEICESTER | 568004 | 01524 | 7.6 | Solar | 05_14_61L2 | 11/30/2023 | 12/05/2023 | 3 | 0 | 3 | 12/06/2023 | 12/06/2023 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 678762 | 01519 | 10 | Solar | 05_14_75L1 | 03/18/2025 | 03/24/2025 | 5 | 2 | 3 | 03/25/2025 | 03/25/2025 | 195 | 176 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 620137 | 01550 | 7.6 | Solar | 05_01_21W1 | 06/24/2024 | 07/23/2024 | 5 | 0 | 5 | 07/24/2024 | 07/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 06/24/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WESTMINSTER | 176366 | 01473 | 10 | Solar | 05_01_304W2 | 03/09/2016 | 03/09/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 3/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | SWANSEA | 548793 | 02777 | 15 | Solar | 05_01_413L4 | 08/18/2023 | 08/21/2023 | 1 | 0 | 1 | 08/22/2023 | 08/22/2023 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 08/18/2023 | 10/22/2024 | Y | EXP | 365 | 12/08/2023 | 01/24/2024 | 48 | 3 | 45 |  |  | 2/3/2024 | Connected |  | N
National Grid | LYNN | 646003 | 01904 | 5 | Solar | 05_01_609W2 | 10/10/2024 | 11/04/2024 | 5 | 0 | 5 | 11/05/2024 | 11/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/10/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 176058 | 01907 | 996 | Solar | 05_05_11W84 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 04/29/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 2/24/2016 | 03/27/2015 | 10/15/2017 | Y | STD | 599 | 09/11/2017 | 10/24/2017 | 30 | 0 | 30 | 10/12/2017 | 10/12/2017 | 10/17/2017 | Connected |  | N
National Grid | HAVERHILL | 701469 | 01830 | 7.68 | Solar | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 58 | 25 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 380086 | 01843 | 15.2 | Solar | 05_12_9J2 | 09/05/2021 | 09/27/2021 | 15 | 14 | 1 | 09/28/2021 | 09/28/2021 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | DRACUT | 177505 | 01826 | 7.6 | Solar | 05_14_47L1 | 03/06/2017 | 03/06/2017 | 9 | 3 | 6 | 03/17/2017 | 03/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 | 03/06/2017 | 3/11/2018 | Y | EXP | 355 | 07/10/2017 | 07/31/2017 | 15 | 0 | 15 | 9/8/2017 | 9/8/2017 | 9/8/2017 | Connected |  | N
National Grid | SPENCER | 579602 | 01562 | 8.7 | Solar | 05_14_61L2 | 01/23/2024 | 01/25/2024 | 2 | 0 | 2 | 01/26/2024 | 01/26/2024 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 01/23/2024 | 3/13/2025 | Y | EXP | 365 | 05/16/2024 | 06/08/2024 | 24 | 0 | 24 |  |  | 6/14/2024 | Connected |  | N
National Grid | GRAFTON | 684922 | 01560 | 15.76 | Solar | 05_14_75L1 | 04/15/2025 | 04/21/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 640689 | 01550 | 4.35 | Solar | 05_01_21W1 | 09/17/2024 | 10/08/2024 | 10 | 7 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 12/19/2025 | Y | EXP | 365 | 01/23/2025 | 06/20/2025 | 149 | 0 | 149 |  |  | 6/30/2025 | Connected |  | N
National Grid | WESTMINSTER | 176400 | 01473 | 7.6 | Solar | 05_01_304W2 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/18/2016 | 03/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 |  | 3/19/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | SWANSEA | 555308 | 02777 | 5 | Solar | 05_01_413L4 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 93 | 70 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | LYNN | 656341 | 01902 | 10 | Solar | 05_01_609W2 | 11/22/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 176328 | 01907 | 3.8 | Solar | 05_05_11W84 | 07/20/2015 | 07/20/2015 | 4 | 4 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 07/20/2015 | 7/26/2016 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 5/3/2016 | 5/3/2016 | 5/3/2016 | Connected |  | N
National Grid | HAVERHILL | 701437 | 01830 | 8.64 | Solar | 05_12_29W4 | 06/26/2025 | 07/11/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/26/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2025 | Connected |  | N
National Grid | LAWRENCE | 405582 | 01843 | 0 | Solar | 05_12_9J2 | 01/09/2022 | 01/10/2022 | 1 | 0 | 1 | 01/11/2022 | 01/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177942 | 01850 | 3.8 | Solar | 05_14_47L1 | 06/26/2017 | 06/26/2017 | 6 | 5 | 1 | 07/06/2017 | 07/06/2017 | 163 | 0 | 163 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/2/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 583839 | 01524 | 4.06 | Solar | 05_14_61L2 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/22/2024 | 4/16/2025 | Y | EXP | 365 | 04/16/2024 | 06/18/2024 | 64 | 0 | 64 |  |  | 7/12/2024 | Connected |  | N
National Grid | SUTTON | 717230 | 01590 | 11.5 | Solar | 05_14_75L1 | 09/05/2025 | 09/16/2025 | 14 | 10 | 4 | 10/23/2025 | 10/23/2025 | 56 | 47 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 656080 | 01550 | 3.8 | Solar | 05_01_21W1 | 11/21/2024 | 01/10/2025 | 28 | 22 | 6 | 01/13/2025 | 01/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176463 | 01473 | 7.6 | Solar | 05_01_304W2 | 02/04/2016 | 02/04/2016 | 3 | 3 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/13/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | SOMERSET | 591210 | 02725 | 6 | Solar | 05_01_413L4 | 03/08/2024 | 03/14/2024 | 4 | 0 | 4 | 03/15/2024 | 03/15/2024 | 13 | 10 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | LYNN | 666877 | 01902 | 7.6 | Solar | 05_01_609W2 | 01/21/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 176755 | 01907 | 300 | Solar | 05_05_11W84 | 01/13/2016 | 01/13/2016 | 3 | 3 | 0 | 01/19/2016 | 01/19/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/18/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 710848 | 01830 | 7.6 | Solar | 05_12_29W5 | 08/08/2025 | 09/19/2025 | 3 | 0 | 3 | 09/22/2025 | 09/22/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 714650 | 01843 | 30 | Solar | 05_12_9J2 | 09/19/2025 | 09/24/2025 | 3 | 0 | 3 | 09/25/2025 | 09/25/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | Y
National Grid | LOWELL | 178511 | 01850 | 7.6 | Solar | 05_14_47L1 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/13/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 594483 | 01562 | 7.6 | Solar | 05_14_61L2 | 03/05/2024 | 06/11/2024 | 7 | 5 | 2 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 | 03/05/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | GRAFTON | 733331 | 01560 | 5.76 | Solar | 05_14_75L1 | 11/12/2025 | 12/10/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 659461 | 01550 | 3.8 | Solar | 05_01_21W1 | 12/09/2024 | 01/03/2025 | 17 | 14 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 176489 | 01473 | 7.6 | Solar | 05_01_304W2 | 12/09/2015 | 12/09/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/14/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/1/2016 | Connected |  | N
National Grid | SOMERSET | 592756 | 02725 | 7.6 | Solar | 05_01_413L4 | 02/28/2024 | 05/22/2024 | 53 | 50 | 3 | 05/23/2024 | 05/23/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 02/28/2024 | 12/31/2025 | Y | EXP | 365 | 09/30/2025 | 09/29/2025 | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | LYNN | 673174 | 01902 | 10 | Solar | 05_01_609W2 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 97 | 57 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 177033 | 01907 | 225 | Solar | 05_05_11W84 | 07/26/2016 | 07/26/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 09/15/2016 | 10/13/2016 | 19 | 0 | 19 | 07/28/2016 | 08/25/2016 | 20 | 0 | 20 |  | 10/13/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 742210 | 01985 | 5.76 | Solar | 05_12_29W5 | 12/24/2025 | 12/30/2025 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 30 | 19 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 349109 | 01843 | 150 | Solar | 05_14_12J1 | 03/26/2021 | 04/13/2021 | 11 | 2 | 9 | 06/16/2021 | 06/16/2021 | 109 | 84 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 03/26/2021 | 7/12/2022 | Y | EXP | 147 | 03/13/2022 | 04/07/2022 | 26 | 0 | 26 |  |  | 5/26/2022 | Connected |  | N
National Grid | DRACUT | 183620 | 01826 | 15.2 | Solar | 05_14_47L1 | 06/25/2018 | 06/25/2018 | 0 | 0 | 0 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 | 06/25/2018 |  | Y | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | LEICESTER | 616821 | 01524 | 3.8 | Solar | 05_14_61L2 | 06/10/2024 | 06/25/2024 | 3 | 0 | 3 | 06/26/2024 | 06/26/2024 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 174877 | 01560 | 30 | Solar | 05_14_75L2 | 10/25/2011 | 10/25/2011 | 69 | 0 | 69 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2012 |  | 12/31/2012 | N | EXP | 273 |  |  | 0 | 0 | 0 | 4/16/2012 | 4/16/2012 | 4/17/2012 | Terminated |  | N
National Grid | SOUTHBRIDGE | 659845 | 01550 | 10 | Solar | 05_01_21W1 | 12/11/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WESTMINSTER | 176514 | 01473 | 10 | Solar | 05_01_304W2 | 10/01/2015 | 10/01/2015 | 1 | 1 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2015 |  | 10/10/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/20/2016 | 4/20/2016 | 4/27/2016 | Connected |  | N
National Grid | SOMERSET | 633183 | 02725 | 10 | Solar | 05_01_413L4 | 08/15/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 32 | 25 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 691407 | 01902 | 11.4 | Solar | 05_01_609W2 | 06/03/2025 | 06/10/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 78 | 55 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | WESTFORD | 177209 | 01886 | 10 | Solar | 05_05_11W84 | 06/06/2016 | 06/06/2016 | 1 | 1 | 0 | 06/08/2016 | 06/08/2016 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 |  | 6/12/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 750194 | 01985 | 5.76 | Solar | 05_12_29W5 | 02/09/2026 | 02/10/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 699707 | 01843 | 40.85 | Solar | 05_14_13J2 | 06/19/2025 | 07/08/2025 | 12 | 10 | 2 | 07/09/2025 | 07/09/2025 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 188160 | 01852 | 15.2 | Solar | 05_14_47L1 | 06/14/2018 | 06/14/2018 | 5 | 0 | 5 | 06/25/2018 | 06/25/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 621422 | 01524 | 7.6 | Solar | 05_14_61L2 | 06/28/2024 | 07/05/2024 | 2 | 0 | 2 | 07/08/2024 | 07/08/2024 | 72 | 25 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 175932 | 01560 | 4.3 | Solar | 05_14_75L2 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 | 08/06/2015 | 8/15/2016 | Y | EXP | 349 | 04/25/2016 | 05/17/2016 | 16 | 0 | 16 | 6/20/2016 | 6/20/2016 | 6/22/2016 | Connected |  | N
National Grid | CHARLTON | 661410 | 01507 | 5.76 | Solar | 05_01_21W1 | 12/18/2024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 176877 | 01473 | 995 | Solar | 05_01_304W2 | 05/04/2016 | 05/04/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2016 | 06/20/2016 | 24 | 11 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 |  | 9/1/2018 | N | STD | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 644414 | 02777 | 5.76 | Solar | 05_01_413L4 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/02/2024 | 2/3/2026 | Y | EXP | 365 | 01/04/2025 | 02/11/2025 | 39 | 0 | 39 |  |  | 4/30/2025 | Connected |  | N
National Grid | LYNN | 697495 | 01904 | 11.4 | Solar | 05_01_609W2 | 06/10/2025 | 06/24/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/10/2025 | 8/11/2026 | Y | EXP | 365 | 10/22/2025 | 12/18/2025 | 58 | 0 | 58 |  |  | 11/26/2025 | Connected |  | N
National Grid | LOWELL | 177350 | 01854 | 7.6 | Solar | 05_05_11W84 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/20/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 177658 | 01985 | 66.6 | Solar | 05_12_29W5 | 11/13/2017 | 11/13/2017 | 49 | 49 | 0 | 01/26/2018 | 01/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 4/19/2019 | N | EXP | 445 |  |  | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | LAWRENCE | 174628 | 01843 | 44 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | DRACUT | 189468 | 01826 | 2800 | Solar | 05_14_47L1 | 10/09/2018 | 10/15/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 11/13/2018 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 | 10/09/2018 | 11/20/2025 | Y | STD | 89 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 637450 | 01562 | 6.195 | Solar | 05_14_61L2 | 09/04/2024 | 12/18/2024 | 25 | 21 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | GRAFTON | 176005 | 01519 | 10.32 | Solar | 05_14_75L2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/19/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/8/2016 | Connected |  | N
National Grid | SOUTHBRIDGE | 667337 | 01550 | 10 | Solar | 05_01_21W1 | 01/23/2025 | 02/14/2025 | 7 | 3 | 4 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 4/24/2026 | Y | EXP | 365 | 06/13/2025 | 06/23/2025 | 11 | 0 | 11 |  |  | 6/26/2025 | Connected |  | N
National Grid | WESTMINSTER | 184400 | 01473 | 6 | Solar | 05_01_304W2 | 05/11/2018 | 05/11/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 669910 | 02777 | 7.8 | Solar | 05_01_413L4 | 02/04/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 74 | 57 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 487743 | 01904 | 0 | Other | 05_01_610W3 | 04/26/2023 | 05/08/2023 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2023 | 05/31/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 177712 | 01852 | 1000 | Solar | 05_05_11W84 | 07/25/2017 | 07/25/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2017 | 12/15/2017 | 79 | 0 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 178626 | 01830 |  | Solar | 05_12_29W5 | 03/15/2018 | 03/15/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/21/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174627 | 01843 | 66 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 2/10/2012 | Y | EXP | 176 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 2/10/2012 | Connected |  | N
National Grid | DRACUT | 192934 | 01826 | 7.6 | Solar | 05_14_47L1 | 08/07/2018 | 08/28/2018 | 3 | 3 | 0 | 08/29/2018 | 08/29/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 651306 | 01562 | 7.6 | Solar | 05_14_61L2 | 10/31/2024 | 11/12/2024 | 6 | 1 | 5 | 11/13/2024 | 11/13/2024 | 94 | 73 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 10/31/2024 | 5/20/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 32 | 120 |  |  | 1/7/2026 | Connected |  | N
National Grid | SUTTON | 177911 | 01590 | 7.6 | Solar | 05_14_75L2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/30/2017 | 09/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/21/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBRIDGE | 689892 | 01550 | 3.8 | Solar | 05_01_21W1 | 05/06/2025 | 05/20/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 98 | 88 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 185479 | 01473 | 5 | Solar | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 11 | 7 | 4 | 07/13/2018 | 07/13/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  | 7/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | SOMERSET | 682067 | 02725 | 10 | Solar | 05_01_413L4 | 04/01/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | LYNN | 629414 | 01902 | 4980 | Solar | 05_01_610W3 | 09/23/2024 | 12/05/2024 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2024 | 02/10/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 177736 | 01854 | 3.6 | Solar | 05_05_11W84 | 03/23/2017 | 03/23/2017 | 6 | 6 | 0 | 03/31/2017 | 03/31/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/23/2017 | 3/28/2018 | Y | EXP | 358 | 08/09/2017 | 08/14/2017 | 3 | 0 | 3 | 3/1/2018 | 3/1/2018 | 3/23/2018 | Connected |  | N
National Grid | NEWBURY | 183811 | 01985 | 5 | Solar | 05_12_29W5 | 04/30/2018 | 04/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174626 | 01843 | 15 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | DRACUT | 260717 | 01826 | 20 | Solar | 05_14_47L1 | 10/17/2019 | 12/02/2019 | 29 | 28 | 1 | 12/03/2019 | 12/03/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 10/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 663551 | 01562 | 5.76 | Solar | 05_14_61L2 | 01/03/2025 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 198227 | 01519 | 6 | Solar | 05_14_75L2 | 11/08/2018 | 12/13/2018 | 21 | 17 | 4 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 | 11/08/2018 | 9/16/2019 | Y | EXP | 262 | 04/05/2019 | 04/18/2019 | 13 | 0 | 13 |  |  | 9/10/2019 | Connected |  | N
National Grid | SOUTHBRIDGE | 691681 | 01550 | 11.4 | Solar | 05_01_21W1 | 05/14/2025 | 05/27/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTMINSTER | 185476 | 01473 | 6 | Solar | 05_01_304W2 | 06/26/2018 | 06/26/2018 | 5 | 2 | 3 | 07/05/2018 | 07/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 06/26/2018 | 7/1/2019 | Y | EXP | 343 | 04/10/2019 | 04/18/2019 | 8 | 0 | 8 |  |  | 6/20/2019 | Connected |  | N
National Grid | SOMERSET | 693150 | 02725 | 7.6 | Solar | 05_01_413L4 | 05/21/2025 | 05/28/2025 | 4 | 0 | 4 | 05/29/2025 | 05/29/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 05/21/2025 | 8/11/2026 | Y | EXP | 365 | 11/22/2025 | 11/21/2025 | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | LYNN | 667321 | 01902 | 7.6 | Solar | 05_01_610W3 | 01/22/2025 | 02/25/2025 | 3 | 0 | 3 | 02/06/2025 | 02/06/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/22/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LOWELL | 177848 | 01854 | 300 | Natural Gas | 05_05_11W84 | 04/06/2017 | 04/06/2017 | 54 | 54 | 0 | 06/26/2017 | 06/26/2017 | 189 | 53 | 136 | 08/17/2017 | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  | 10/16/2017 | 40 | 22 | 18 |  |  | 0 | 0 | 0 | 12/15/2017 |  | 4/12/2018 | N | EXP | 118 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 191753 | 01985 | 7.6 | Solar | 05_12_29W5 | 07/24/2018 | 10/03/2018 | 41 | 38 | 3 | 10/04/2018 | 10/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174625 | 01843 | 15 | Solar | 05_14_13J4 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 146 | 12/01/2011 | 12/12/2011 | 7 | 0 | 7 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | DRACUT | 263544 | 01826 | 15 | Solar | 05_14_47L1 | 11/25/2019 | 12/04/2019 | 5 | 0 | 5 | 12/05/2019 | 12/05/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | SPENCER | 667365 | 01562 | 7.6 | Solar | 05_14_61L2 | 01/23/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 200569 | 01519 | 7.6 | Solar | 05_14_75L2 | 11/06/2018 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 701290 | 01550 | 15.2 | Solar | 05_01_21W1 | 06/26/2025 | 07/14/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | WESTMINSTER | 190346 | 01473 | 10 | Solar | 05_01_304W2 | 07/10/2018 | 08/28/2018 | 19 | 0 | 19 | 08/29/2018 | 08/29/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 339091 | 02726 | 4999 | Solar | 05_01_413L6 | 04/07/2021 | 04/28/2021 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2021 | 05/28/2021 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 739544 | 01902 | 15.2 | Solar | 05_01_610W3 | 12/11/2025 | 12/16/2025 | 3 | 0 | 3 | 12/17/2025 | 12/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 | 12/11/2025 | 1/29/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LOWELL | 178036 | 01854 | 9.86 | Solar | 05_05_11W84 | 10/27/2017 | 10/27/2017 | 39 | 39 | 0 | 01/04/2018 | 01/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 |  | 11/5/2018 | N | EXP | 31 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | NEWBURY | 216929 | 01985 | 7.6 | Solar | 05_12_29W5 | 05/07/2019 | 05/08/2019 | 0 | 0 | 0 | 05/09/2019 | 05/09/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/07/2019 | 5/12/2021 | Y | EXP | 365 | 05/27/2020 | 10/24/2020 | 151 | 5 | 146 |  |  | 2/5/2021 | Connected |  | N
National Grid | LAWRENCE | 556428 | 01843 | 480 | Solar | 05_14_13L1 | 11/22/2023 | 12/18/2023 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 02/14/2024 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 310000 | 01852 | 7.6 | Solar | 05_14_47L1 | 09/01/2020 | 09/08/2020 | 3 | 0 | 3 | 09/09/2020 | 09/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2020 | Connected |  | N
National Grid | LEICESTER | 671905 | 01524 | 7.25 | Solar | 05_14_61L2 | 02/13/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | GRAFTON | 266776 | 01519 | 6.67 | Solar | 05_14_75L2 | 11/22/2019 | 11/25/2019 | 0 | 0 | 0 | 11/26/2019 | 11/26/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | SOUTHBRIDGE | 718922 | 01550 | 18.56 | Solar | 05_01_21W1 | 09/14/2025 | 09/29/2025 | 10 | 5 | 5 | 09/30/2025 | 09/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | WESTMINSTER | 287978 | 01473 | 7.6 | Solar | 05_01_304W2 | 04/15/2020 | 05/06/2020 | 11 | 9 | 2 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Connected |  | N
National Grid | SOMERSET | 438733 | 02725 | 0 | Natural Gas | 05_01_413L6 | 08/16/2022 | 10/26/2022 | 49 | 40 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 | 11/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | LYNN | 743645 | 01902 | 11.4 | Solar | 05_01_610W3 | 01/06/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 178046 | 01852 | 3.8 | Solar | 05_05_11W84 | 05/05/2017 | 05/05/2017 | 2 | 2 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2017 |  | 5/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | NEWBURY | 265737 | 01985 | 7.6 | Solar | 05_12_29W5 | 12/04/2019 | 12/10/2019 | 3 | 0 | 3 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 566922 | 01843 | 250 | Solar | 05_14_13L1 | 12/01/2023 | 12/26/2023 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 01/26/2024 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 | 12/01/2023 | 4/17/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | ANDOVER | 320289 | 01810 | 11.4 | Solar | 05_14_47L1 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 2/23/2022 | Y | EXP | 365 | 05/26/2021 | 06/30/2021 | 35 | 0 | 35 |  |  | 9/24/2021 | Connected |  | N
National Grid | SPENCER | 674367 | 01562 | 10 | Solar | 05_14_61L3 | 03/03/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 03/03/2025 | 10/13/2026 | Y | EXP | 365 | 12/31/2025 |  | 66 | 0 | 66 |  |  |  | Construction |  | N
National Grid | SUTTON | 273439 | 01590 | 0 | Solar | 05_14_75L2 | 01/23/2020 | 01/27/2020 | 2 | 2 | 0 | 01/28/2020 | 01/28/2020 | 33 | 29 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 | 01/23/2020 | 1/25/2021 | Y | EXP | 365 | 06/06/2020 | 06/13/2020 | 7 | 0 | 7 |  |  | 6/15/2020 | Connected |  | N
National Grid | CHARLTON | 712833 | 01507 | 7.6 | Solar | 05_01_21W2 | 08/27/2025 | 09/15/2025 | 12 | 9 | 3 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTMINSTER | 322290 | 01473 | 7.6 | Solar | 05_01_304W2 | 02/03/2021 | 03/26/2021 | 35 | 34 | 1 | 03/29/2021 | 03/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 3/25/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175098 | 02777 | 2000 | Solar | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 174375 | 01902 | 600 | Solar | 05_01_610W3 | 05/29/2012 | 05/29/2012 | 11 | 0 | 11 | 06/18/2012 | 06/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 05/29/2012 | 12/31/2016 | Y | EXP | 1388 | 10/01/2015 | 10/09/2015 | 6 | 0 | 6 | 6/3/2012 | 6/3/2012 | 12/24/2015 | Connected |  | N
National Grid | LOWELL | 178101 | 01852 | 3.8 | Solar | 05_05_11W84 | 09/08/2017 | 09/08/2017 | 7 | 7 | 0 | 09/19/2017 | 09/19/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 9/13/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  | 7/25/2018 | Connected |  | N
National Grid | NEWBURY | 289054 | 01985 | 3 | Solar | 05_12_29W5 | 05/06/2020 | 05/11/2020 | 2 | 0 | 2 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 | 05/06/2020 | 10/21/2021 | Y | EXP | 365 | 03/20/2021 | 05/04/2021 | 45 | 0 | 45 |  |  | 5/13/2021 | Connected |  | N
National Grid | LAWRENCE | 580139 | 01843 | 200 | Solar | 05_14_13L1 | 01/15/2024 | 05/15/2024 | 85 | 74 | 11 | 05/16/2024 | 05/16/2024 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 4/20/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | TEWKSBURY | 340844 | 01876 | 0 | Solar | 05_14_47L1 | 02/12/2021 | 03/09/2021 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2021 | 03/29/2021 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 709911 | 01507 | 7.6 | Solar | 05_14_61L3 | 08/05/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 40 | 24 | 16 | 11/19/2025 | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 12/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | GRAFTON | 325076 | 01519 | 7.6 | Solar | 05_14_75L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 720360 | 01550 | 10 | Solar | 05_01_21W2 | 09/19/2025 | 09/25/2025 | 4 | 1 | 3 | 09/26/2025 | 09/26/2025 | 27 | 15 | 12 | 11/21/2025 | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/20/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WESTMINSTER | 324435 | 01473 | 7.6 | Solar | 05_01_304W2 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 175097 | 02777 | 1000 | Solar | 05_01_413L6 | 10/26/2012 | 10/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 | 12/28/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175446 | 01902 | 450 | Solar | 05_01_610W3 | 03/10/2014 | 03/10/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2014 | 04/09/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 03/10/2014 | 6/9/2016 | Y | STD | 546 | 06/20/2016 | 09/08/2016 | 56 | 0 | 56 |  |  | 9/27/2016 | Connected |  | N
National Grid | LOWELL | 178265 | 01852 | 4998 | Solar | 05_05_11W84 | 01/08/2018 | 03/06/2018 | 27 | 20 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/10/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 |  | 7/9/2020 | N | STD | 66 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 450088 | 01830 | 6 | Solar | 05_12_29W5 | 09/20/2022 | 09/21/2022 | 1 | 0 | 1 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 744754 | 01843 | 7.6 | Solar | 05_14_14L1 | 01/12/2026 | 01/13/2026 | 2 | 0 | 2 | 01/29/2026 | 01/29/2026 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 356972 | 01852 | 7.6 | Solar | 05_14_47L1 | 05/20/2021 | 05/21/2021 | 0 | 0 | 0 | 05/24/2021 | 05/24/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 5/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 712782 | 01507 | 11.5 | Solar | 05_14_61L3 | 08/18/2025 | 01/06/2026 | 44 | 43 | 1 | 01/07/2026 | 01/07/2026 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | GRAFTON | 340366 | 01519 | 15.2 | Solar | 05_14_75L2 | 02/03/2021 | 02/22/2021 | 12 | 11 | 1 | 02/23/2021 | 02/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | SOUTHBRIDGE | 749805 | 01550 | 10 | Solar | 05_01_21W2 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTMINSTER | 332953 | 01473 | 7.6 | Solar | 05_01_304W2 | 12/18/2020 | 01/07/2021 | 12 | 11 | 1 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 7/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | SWANSEA | 176301 | 02777 | 1126 | Natural Gas | 05_01_413L6 | 09/11/2015 | 09/11/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2015 | 10/30/2015 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 7/1/2018 | N | STD | 35 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 8/27/2018 | Connected |  | N
National Grid | LYNN | 175731 | 01902 | 499 | Solar | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | TEWKSBURY | 178294 | 01876 | 2050 | Solar | 05_05_11W84 | 11/14/2017 | 11/14/2017 | 49 | 49 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 03/23/2018 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 370923 | 01985 | 3.8 | Solar | 05_12_29W5 | 07/22/2021 | 07/27/2021 | 3 | 0 | 3 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 178225 | 01843 | 10 | Solar | 05_14_14L1 | 01/03/2018 | 01/03/2018 | 38 | 32 | 6 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2018 |  | 1/10/2019 | N | EXP | 31 | 05/09/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 11/15/2018 | Connected |  | N
National Grid | TEWKSBURY | 418273 | 01876 | 500 | Solar | 05_14_47L1 | 09/30/2022 | 02/14/2023 | 89 | 79 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2023 | 03/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 732991 | 01524 | 3.8 | Solar | 05_14_61L3 | 12/23/2025 | 12/29/2025 | 1 | 0 | 1 | 01/15/2026 | 01/15/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 411194 | 01590 | 9.57 | Solar | 05_14_75L2 | 03/21/2022 | 05/10/2022 | 36 | 35 | 1 | 05/11/2022 | 05/11/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 03/21/2022 | 8/26/2023 | Y | EXP | 365 | 08/09/2022 | 08/25/2022 | 17 | 0 | 17 |  |  | 9/15/2022 | Connected |  | N
National Grid | SOUTHBRIDGE | 174330 | 01550 | 14.28 | Solar | 05_01_21W2 | 01/17/2012 | 01/17/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2012 |  | 2/20/2012 | N | EXP | 46 |  |  | 0 | 0 | 0 | 4/30/2012 | 4/30/2012 | 7/18/2012 | Connected |  | N
National Grid | WESTMINSTER | 337127 | 01473 | 9.86 | Solar | 05_01_304W2 | 01/15/2021 | 01/22/2021 | 3 | 0 | 3 | 01/25/2021 | 01/25/2021 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2021 | 01/15/2021 | 1/21/2022 | Y | EXP | 365 | 05/04/2021 | 05/21/2021 | 17 | 0 | 17 |  |  | 8/5/2021 | Connected |  | N
National Grid | SOMERSET | 192559 | 02725 | 5786 | Solar | 05_01_413L6 | 08/23/2018 | 09/17/2018 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 03/28/2019 | 214 | 110 | 104 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175730 | 01902 | 1000 | Solar | 05_01_610W3 | 06/03/2014 | 06/03/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2014 | 06/27/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 | 03/18/2016 | 03/15/2016 | 0 | 0 | 0 | 8/15/2016 | 06/03/2014 | 10/15/2018 | Y | STD | 791 |  |  | 0 | 0 | 0 | 9/7/2018 | 9/13/2018 | 10/5/2018 | Connected |  | N
National Grid | TEWKSBURY | 197466 | 01876 | 480 | Solar | 05_05_11W84 | 01/16/2019 | 02/04/2019 | 12 | 4 | 8 | 02/05/2019 | 02/05/2019 | 23 | 11 | 12 | 04/10/2019 | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 05/07/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 5/4/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 544488 | 01830 | 7.83 | Solar | 05_12_29W5 | 11/20/2023 |  | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 278152 | 01810 | 383 | Solar | 05_14_14L1 | 02/05/2020 | 02/13/2020 | 5 | 0 | 5 | 02/14/2020 | 02/14/2020 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2020 |  | 3/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 466928 | 01876 | 20 | Solar | 05_14_47L1 | 10/24/2022 |  | 226 | 25 | 201 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 746274 | 01524 | 17.86 | Solar | 05_14_61L3 | 01/20/2026 | 02/02/2026 | 9 | 4 | 5 | 02/03/2026 | 02/03/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 420643 | 01590 | 0 | Battery Add-On | 05_14_75L2 | 08/10/2022 | 08/26/2022 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2022 | 09/23/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBRIDGE | 174430 | 01550 | 3000 | Solar | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 374481 | 01473 | 7.6 | Solar | 05_01_304W2 | 08/06/2021 | 09/09/2021 | 23 | 13 | 10 | 09/10/2021 | 09/10/2021 | 139 | 115 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 174130 | 02777 | 2000 | Solar | 05_01_413L7 | 05/01/2012 | 05/01/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2012 | 08/16/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175830 | 01902 | 6 | Solar | 05_01_610W3 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/27/2016 | N | EXP | 34 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 5/12/2016 | Connected |  | N
National Grid | TEWKSBURY | 259604 | 01876 | 7.6 | Solar | 05_05_11W84 | 10/29/2019 | 10/30/2019 | 0 | 0 | 0 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 550054 | 01985 | 6 | Solar | 05_12_29W5 | 08/23/2023 | 08/28/2023 | 3 | 2 | 1 | 08/29/2023 | 08/29/2023 | 25 | 0 | 25 | 10/18/2023 | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 12/04/2023 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 12/27/2023 |  | 1/1/2025 | N | EXP | 365 | 03/14/2024 | 09/11/2024 | 159 | 0 | 159 |  |  | 8/20/2024 | Connected |  | N
National Grid | LAWRENCE | 381249 | 01843 | 10 | Solar | 05_14_14L1 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 9/2/2023 | Y | EXP | 365 | 07/01/2022 | 08/02/2022 | 33 | 0 | 33 |  |  | 10/12/2022 | Connected |  | N
National Grid | TEWKSBURY | 496631 | 01752 | 10 | Solar | 05_14_47L1 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 749217 | 01524 | 23 | Solar | 05_14_61L3 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GRAFTON | 465832 | 01519 | 14.5 | Solar | 05_14_75L2 | 10/20/2022 | 10/31/2022 | 7 | 6 | 1 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2022 | 10/20/2022 | 1/24/2024 | Y | EXP | 365 | 03/22/2023 | 04/05/2023 | 15 | 0 | 15 |  |  | 6/30/2023 | Connected |  | N
National Grid | STURBRIDGE | 174428 | 01566 | 4883 | Solar | 05_01_21W2 | 11/18/2011 | 11/18/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2014 | 03/18/2014 | 0 | 0 | 0 | 3/14/2012 | 11/18/2011 | 6/1/2014 | Y | STD | 89 |  |  | 0 | 0 | 0 | 1/23/2015 | 1/23/2015 | 1/29/2015 | Connected |  | N
National Grid | WESTMINSTER | 382046 | 01473 | 7.6 | Solar | 05_01_304W2 | 01/20/2022 | 02/14/2022 | 17 | 13 | 4 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 178064 | 02725 | 9 | Solar | 05_01_413L7 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 | 09/05/2017 | 09/05/2017 | 140 | 15 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/10/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175905 | 01902 | 5.94 | Solar | 05_01_610W3 | 10/01/2015 | 10/01/2015 | 4 | 4 | 0 | 10/07/2015 | 10/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2015 | 10/01/2015 | 10/6/2016 | Y | EXP | 35 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 | 10/22/2015 | 10/22/2015 | 6/17/2016 | Connected |  | N
National Grid | TEWKSBURY | 274437 | 01876 | 6 | Solar | 05_05_11W84 | 01/30/2020 | 02/11/2020 | 7 | 3 | 4 | 02/12/2020 | 02/12/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/30/2020 | 2/5/2021 | Y | EXP | 365 | 06/25/2020 | 08/12/2020 | 48 | 0 | 48 |  |  | 10/16/2020 | Connected |  | N
National Grid | NEWBURY | 551927 | 01985 | 7.54 | Solar | 05_12_29W5 | 09/28/2023 | 11/15/2023 | 32 | 29 | 3 | 11/16/2023 | 11/16/2023 | 105 | 40 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 469773 | 01810 | 15.2 | Solar | 05_14_14L1 | 10/20/2022 | 11/08/2022 | 14 | 13 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | TEWKSBURY | 543688 | 01876 | 15.2 | Solar | 05_14_47L1 | 07/26/2023 | 07/30/2023 | 3 | 0 | 3 | 07/31/2023 | 07/31/2023 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2024 | Connected |  | N
National Grid | LEICESTER | 176512 | 01524 | 7.6 | Solar | 05_14_61L3 | 03/29/2016 | 03/29/2016 | 2 | 2 | 0 | 04/01/2016 | 04/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 03/29/2016 | 8/4/2017 | Y | EXP | 472 | 08/26/2016 | 01/11/2017 | 92 | 0 | 92 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | GRAFTON | 472086 | 01519 | 15.2 | Solar | 05_14_75L2 | 10/28/2022 | 10/31/2022 | 1 | 0 | 1 | 11/01/2022 | 11/01/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2023 | Connected |  | Y
National Grid | STURBRIDGE | 175244 | 01566 | 684 | Solar | 05_01_21W2 | 08/27/2014 | 08/27/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/09/2014 | 10/06/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2015 | 08/27/2014 | 6/30/2016 | Y | STD | 422 | 02/19/2016 | 06/28/2016 | 88 | 0 | 88 | 6/22/2016 | 6/22/2016 | 6/29/2016 | Connected |  | N
National Grid | WESTMINSTER | 425991 | 01473 | 7.25 | Solar | 05_01_304W2 | 06/26/2022 | 07/18/2022 | 16 | 13 | 3 | 07/19/2022 | 07/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/26/2022 | 4/3/2024 | Y | EXP | 365 | 03/25/2023 | 04/04/2023 | 11 | 0 | 11 |  |  | 4/5/2023 | Connected |  | N
National Grid | SWANSEA | 200645 | 02777 | 20 | Solar | 05_01_413L7 | 02/21/2019 | 04/12/2019 | 36 | 25 | 11 | 04/15/2019 | 04/15/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2019 |  | 4/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | LYNN | 175891 | 01902 | 5 | Solar | 05_01_610W3 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 379 | 0 | 379 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2015 |  | 8/10/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 290789 | 01876 | 10 | Solar | 05_05_11W84 | 05/06/2020 | 05/14/2020 | 5 | 5 | 0 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 | 05/06/2020 | 5/7/2021 | Y | EXP | 365 | 07/02/2020 | 08/31/2020 | 59 | 0 | 59 |  |  | 9/2/2020 | Connected |  | N
National Grid | NEWBURY | 591596 | 01985 | 6 | Solar | 05_12_29W5 | 03/07/2024 | 03/11/2024 | 2 | 0 | 2 | 03/12/2024 | 03/12/2024 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2024 | Connected |  | N
National Grid | LAWRENCE | 668835 | 01843 | 5.76 | Solar | 05_14_14L1 | 01/29/2025 | 02/05/2025 | 5 | 1 | 4 | 02/06/2025 | 02/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 563377 | 01826 | 0 | Solar | 05_14_47L1 | 10/16/2023 | 10/17/2023 | 1 | 0 | 1 | 10/18/2023 | 10/18/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2024 | Connected |  | N
National Grid | LEICESTER | 177202 | 01524 | 3.8 | Solar | 05_14_61L3 | 02/01/2017 | 02/01/2017 | 0 | 0 | 0 | 02/17/2017 | 02/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 7/31/2018 | N | EXP | 525 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | Connected |  | N
National Grid | GRAFTON | 524377 | 01519 | 7.6 | Solar | 05_14_75L2 | 05/15/2023 | 05/18/2023 | 3 | 0 | 3 | 05/19/2023 | 05/19/2023 | 23 | 0 | 23 | 06/26/2023 | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 07/31/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 11/29/2024 | N | EXP | 365 | 11/04/2023 | 12/13/2023 | 40 | 0 | 40 |  |  | 12/28/2023 | Connected |  | Y
National Grid | STURBRIDGE | 175336 | 01566 | 1000 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2015 | 04/13/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 04/07/2016 | 12/22/2016 | 177 | 0 | 177 |  |  | 11/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 427817 | 01473 | 7.54 | Solar | 05_01_304W2 | 08/17/2022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 204724 | 02777 | 7.6 | Solar | 05_01_413L7 | 01/11/2019 | 02/11/2019 | 19 | 10 | 9 | 02/12/2019 | 02/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 | 01/11/2019 | 2/27/2020 | Y | EXP | 365 | 04/18/2019 | 05/28/2019 | 40 | 0 | 40 |  |  | 6/29/2019 | Connected |  | N
National Grid | LYNN | 176131 | 01902 | 19 | Solar | 05_01_610W3 | 04/14/2015 | 04/14/2015 | 1 | 1 | 0 | 04/16/2015 | 04/16/2015 | 445 | 0 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 8/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 292543 | 01876 | 3.8 | Solar | 05_05_11W84 | 06/25/2020 | 06/29/2020 | 1 | 0 | 1 | 06/30/2020 | 06/30/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 06/25/2020 | 8/1/2021 | Y | EXP | 365 | 12/16/2020 | 01/25/2021 | 40 | 0 | 40 |  |  | 2/9/2021 | Connected |  | N
National Grid | NEWBURY | 592433 | 01985 | 6 | Solar | 05_12_29W5 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2024 | Connected |  | N
National Grid | LAWRENCE | 702081 | 01843 | 3.04 | Solar | 05_14_14L1 | 06/30/2025 | 08/05/2025 | 11 | 6 | 5 | 09/25/2025 | 09/25/2025 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 626005 | 01852 | 50 | Solar | 05_14_47L1 | 07/22/2024 | 09/27/2024 | 48 | 39 | 9 | 09/30/2024 | 09/30/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 2/16/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | LEICESTER | 177722 | 01524 | 6 | Solar | 05_14_61L3 | 10/04/2017 | 10/04/2017 | 19 | 17 | 2 | 11/08/2017 | 11/08/2017 | 76 | 0 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 |  | 10/9/2018 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 569622 | 01560 | 6 | Solar | 05_14_75L2 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 175335 | 01566 | 800 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 506760 | 01473 | 18.85 | Solar | 05_01_304W2 | 03/06/2023 | 03/07/2023 | 1 | 0 | 1 | 03/08/2023 | 03/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | SOMERSET | 284646 | 02725 | 9.84 | Solar | 05_01_413L7 | 03/23/2020 | 04/13/2020 | 0 | 0 | 0 | 04/14/2020 | 04/14/2020 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2020 | 03/23/2020 | 4/13/2021 | Y | EXP | 365 | 07/30/2020 | 09/10/2020 | 42 | 5 | 37 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 177663 | 01902 | 4980 | Solar | 05_01_610W3 | 11/13/2017 | 11/13/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2017 | 12/20/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  | 11/19/2018 | N | STD | 125 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 298454 | 01876 | 23.4 | Solar | 05_05_11W84 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | NEWBURY | 601269 | 01985 | 11.4 | Solar | 05_12_29W5 | 04/09/2024 | 06/25/2024 | 44 | 40 | 4 | 06/26/2024 | 06/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 174727 | 01843 | 260 | Solar | 05_14_14L2 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | DRACUT | 627775 | 01826 | 23 | Battery Add-On | 05_14_47L1 | 07/25/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | LEICESTER | 200394 | 01524 | 3.8 | Solar | 05_14_61L3 | 11/05/2018 | 12/17/2018 | 18 | 9 | 9 | 12/18/2018 | 12/18/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 569134 | 01519 | 6 | Solar | 05_14_75L2 | 11/10/2023 | 11/27/2023 | 10 | 4 | 6 | 11/28/2023 | 11/28/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 175334 | 01566 | 800 | Solar | 05_01_21W2 | 01/17/2015 | 01/17/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 514181 | 01473 | 10 | Solar | 05_01_304W2 | 03/23/2023 | 03/24/2023 | 1 | 0 | 1 | 03/27/2023 | 03/27/2023 | 253 | 25 | 228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 449561 | 02777 | 19 | Solar | 05_01_413L7 | 08/04/2022 | 08/12/2022 | 6 | 3 | 3 | 08/15/2022 | 08/15/2022 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2023 | Connected |  | N
National Grid | LYNN | 178300 | 01902 | 4875 | Solar | 05_01_610W3 | 11/16/2017 | 12/18/2017 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 | 01/17/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2018 | 11/16/2017 | 3/31/2023 | Y | STD | 725 | 08/12/2022 | 01/03/2023 | 145 | 0 | 145 | 3/9/2023 | 3/23/2023 | 3/31/2023 | Connected |  | N
National Grid | TEWKSBURY | 318194 | 01876 | 5.76 | Solar | 05_05_11W84 | 10/08/2020 | 10/20/2020 | 7 | 6 | 1 | 10/21/2020 | 10/21/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | HAVERHILL | 603809 | 01830 | 6 | Solar | 05_12_29W5 | 04/16/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 75 | 66 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LAWRENCE | 198677 | 01843 | 0 | Solar | 05_14_14L2 | 11/13/2018 | 12/03/2018 | 11 | 4 | 7 | 12/04/2018 | 12/04/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 636761 | 01826 | 5.76 | Solar | 05_14_47L1 | 08/30/2024 | 09/16/2024 | 2 | 0 | 2 | 09/17/2024 | 09/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 08/30/2024 | 11/25/2025 | Y | EXP | 365 | 02/05/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 4/29/2025 | Connected |  | N
National Grid | LEICESTER | 202318 | 01524 | 7.6 | Solar | 05_14_61L3 | 11/28/2018 | 01/09/2019 | 7 | 0 | 7 | 01/10/2019 | 01/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 | 11/28/2018 | 11/28/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2020 | Connected |  | N
National Grid | GRAFTON | 585135 | 01519 | 10 | Solar | 05_14_75L2 | 01/26/2024 | 02/13/2024 | 12 | 11 | 1 | 02/14/2024 | 02/14/2024 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 01/26/2024 | 3/1/2025 | Y | EXP | 365 | 04/23/2024 | 06/27/2024 | 66 | 0 | 66 |  |  | 6/29/2024 | Connected |  | N
National Grid | STURBRIDGE | 175641 | 01566 | 16 | Solar | 05_01_21W2 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 768 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 10/20/2016 | Connected |  | N
National Grid | WESTMINSTER | 523131 | 01473 | 9.216 | Solar | 05_01_304W2 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 365963 | 02777 | 7.6 | Solar | 05_01_413L7 | 08/10/2021 | 01/05/2022 | 2 | 0 | 2 | 08/13/2021 | 08/13/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 08/10/2021 | 6/3/2023 | Y | EXP | 365 | 03/01/2022 | 03/28/2022 | 28 | 0 | 28 |  |  | 6/15/2022 | Connected |  | N
National Grid | LYNN | 178378 | 01902 | 5000 | Solar | 05_01_610W3 | 11/22/2017 | 11/22/2017 | 44 | 35 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2018 | 02/25/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 322573 | 01876 | 22.05 | Solar | 05_05_11W84 | 02/08/2021 | 02/25/2021 | 11 | 8 | 3 | 02/26/2021 | 02/26/2021 | 66 | 41 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 9/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | Y
National Grid | NEWBURY | 604998 | 01985 | 7.6 | Solar | 05_12_29W5 | 04/18/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | LAWRENCE | 437891 | 01843 | 15.2 | Solar | 05_14_14L2 | 06/15/2022 | 06/23/2022 | 5 | 3 | 2 | 06/24/2022 | 06/24/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | DRACUT | 646391 | 01826 | 5.76 | Solar | 05_14_47L1 | 10/16/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/16/2024 | 12/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | LEICESTER | 205028 | 01524 | 7.6 | Solar | 05_14_61L3 | 01/22/2019 | 02/06/2019 | 10 | 0 | 10 | 02/07/2019 | 02/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 01/22/2019 | 10/21/2020 | Y | EXP | 365 | 04/25/2020 | 05/26/2020 | 31 | 0 | 31 |  |  | 6/18/2020 | Connected |  | N
National Grid | SUTTON | 611949 | 01590 | 3.8 | Solar | 05_14_75L2 | 05/17/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | STURBRIDGE | 176144 | 01566 | 17.6 | Solar | 05_01_21W2 | 06/29/2015 | 06/29/2015 | 6 | 6 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 344 | 02/08/2017 | 02/22/2017 | 9 | 0 | 9 | 7/28/2015 | 7/28/2015 | 3/20/2017 | Connected |  | N
National Grid | WESTMINSTER | 523641 | 01473 | 5 | Solar | 05_01_304W2 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 05/17/2023 | 4/18/2025 | Y | EXP | 465 | 01/10/2024 | 02/23/2024 | 45 | 0 | 45 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 404096 | 02725 | 7.6 | Solar | 05_01_413L7 | 12/30/2021 | 01/26/2022 | 17 | 15 | 2 | 01/27/2022 | 01/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  | 8/2/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | LYNN | 192451 | 01902 | 3780 | Solar | 05_01_610W3 | 09/18/2018 | 10/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2018 | 11/17/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 348299 | 01876 | 433.3 | Solar | 05_05_11W84 | 06/09/2021 | 08/11/2021 | 44 | 35 | 9 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 605339 | 01985 | 5 | Solar | 05_12_29W5 | 04/20/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 72 | 66 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 199222 | 01843 | 820 | Solar | 05_14_14L3 | 11/20/2018 | 11/28/2018 | 3 | 0 | 3 |  |  | 68 | 43 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 653693 | 01826 | 0 | Solar | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 116 | 91 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | LEICESTER | 206502 | 01524 | 7.6 | Solar | 05_14_61L3 | 03/04/2019 | 03/12/2019 | 5 | 0 | 5 | 03/13/2019 | 03/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 645072 | 01590 | 7.6 | Solar | 05_14_75L2 | 10/04/2024 | 10/15/2024 | 2 | 0 | 2 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176181 | 01566 | 2886 | Solar | 05_01_21W2 | 07/06/2015 | 07/06/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/09/2016 | 10/06/2016 | 41 | 0 | 41 | 3/10/2017 | 07/06/2015 | 7/11/2018 | Y | STD | 488 | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 | 3/30/2018 | 3/30/2018 | 4/5/2018 | Connected |  | N
National Grid | WESTMINSTER | 591813 | 01473 | 3.8 | Solar | 05_01_304W2 | 02/26/2024 | 03/07/2024 | 8 | 3 | 5 | 03/08/2024 | 03/08/2024 | 18 | 17 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 | 02/26/2024 | 5/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2024 | Connected |  | N
National Grid | SOMERSET | 436971 | 02725 | 10 | Solar | 05_01_413L7 | 06/10/2022 | 06/13/2022 | 0 | 0 | 0 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | LYNN | 200898 | 01902 | 4998 | Solar | 05_01_610W3 | 11/12/2018 | 11/30/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 01/25/2019 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 383131 | 01876 | 0 | Other | 05_05_11W84 | 11/29/2021 | 03/24/2022 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/25/2022 | 03/27/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 613150 | 01985 | 3.8 | Solar | 05_12_29W5 | 05/23/2024 | 05/28/2024 | 1 | 0 | 1 | 05/29/2024 | 05/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 517633 | 01843 | 72 | Solar | 05_14_16L1 | 04/29/2023 | 01/07/2024 | 172 | 162 | 10 |  |  | 57 | 35 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | TEWKSBURY | 653594 | 01876 | 7.6 | Solar | 05_14_47L1 | 11/12/2024 | 11/14/2024 | 2 | 0 | 2 | 11/15/2024 | 11/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 213800 | 01524 | 6 | Solar | 05_14_61L3 | 04/02/2019 | 04/10/2019 | 6 | 6 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2019 | 04/02/2019 | 7/30/2019 | Y | EXP | 15 | 07/09/2019 | 07/16/2019 | 7 | 0 | 7 |  |  | 7/18/2019 | Connected |  | N
National Grid | GRAFTON | 671138 | 01519 | 10 | Solar | 05_14_75L2 | 02/10/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 81 | 62 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | STURBRIDGE | 176183 | 01566 | 517 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 626207 | 01473 | 10 | Solar | 05_01_304W2 | 07/19/2024 | 09/17/2024 | 31 | 25 | 6 | 09/18/2024 | 09/18/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 477664 | 02777 | 9.57 | Solar | 05_01_413L7 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 | 02/22/2023 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/29/2023 | Connected |  | N
National Grid | LYNN | 370345 | 01902 | 11.4 | Solar | 05_01_610W3 | 07/16/2021 | 08/19/2021 | 24 | 23 | 1 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 07/16/2021 | 7/15/2023 | Y | EXP | 365 | 02/17/2022 | 02/28/2022 | 12 | 0 | 12 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 394593 | 01824 | 78.8 | Solar | 05_05_11W84 | 11/15/2021 | 11/30/2021 | 10 | 2 | 8 | 12/01/2021 | 12/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 | 11/15/2021 | 4/10/2023 | Y | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 2/16/2023 | Connected |  | N
National Grid | HAVERHILL | 624218 | 01830 | 7.6 | Solar | 05_12_29W5 | 07/11/2024 | 09/18/2024 | 25 | 20 | 5 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 12/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | Y
National Grid | LAWRENCE | 174748 | 01843 | 75 | Solar | 05_14_16L1 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 567 | 3 | 564 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2013 |  | 9/1/2014 | N | EXP | 381 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 654681 | 01826 | 22.8 | Solar | 05_14_47L1 | 11/15/2024 | 01/07/2025 | 27 | 25 | 2 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | LEICESTER | 240228 | 01524 | 10 | Solar | 05_14_61L3 | 10/23/2019 | 10/30/2019 | 4 | 0 | 4 | 10/31/2019 | 10/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 672050 | 01519 | 7.6 | Solar | 05_14_75L2 | 02/13/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 176182 | 01566 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 638284 | 01473 | 15.2 | Solar | 05_01_304W2 | 09/09/2024 | 09/23/2024 | 5 | 2 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 11/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | Y
National Grid | SOMERSET | 505691 | 02726 | 15 | Solar | 05_01_413L7 | 03/02/2023 | 04/20/2023 | 34 | 25 | 9 | 04/21/2023 | 04/21/2023 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 |  | 6/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2023 | Connected |  | N
National Grid | LYNN | 382185 | 01902 | 15.2 | Solar | 05_01_610W3 | 09/15/2021 | 12/08/2021 | 3 | 0 | 3 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/15/2021 | 11/3/2023 | Y | EXP | 365 | 09/02/2022 | 10/26/2022 | 55 | 0 | 55 |  |  | 12/13/2022 | Connected |  | N
National Grid | CHELMSFORD | 433811 | 01824 | 10 | Solar | 05_05_11W84 | 05/27/2022 | 07/21/2022 | 0 | 0 | 0 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 | 05/27/2022 | 1/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | NEWBURY | 625525 | 01985 | 5.76 | Solar | 05_12_29W5 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 661964 | 01843 | 6.08 | Solar | 05_14_16L1 | 12/20/2024 | 12/29/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | DRACUT | 655659 | 01826 | 10 | Solar | 05_14_47L1 | 11/20/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/20/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | LEICESTER | 248995 | 01524 | 250 | Solar | 05_14_61L3 | 08/15/2019 | 08/30/2019 | 10 | 2 | 8 | 09/03/2019 | 09/03/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2019 |  | 9/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2020 | Connected |  | N
National Grid | GRAFTON | 466563 | 01560 | 600 | Other | 05_14_75L3 | 04/27/2023 | 06/29/2023 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2023 | 07/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 04/27/2023 | 8/24/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STURBRIDGE | 176214 | 01566 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2015 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 651889 | 01473 | 18.85 | Solar | 05_01_304W2 | 11/27/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | SWANSEA | 594094 | 02777 | 9.86 | Solar | 05_01_413L7 | 03/19/2024 | 04/18/2024 | 22 | 19 | 3 | 04/19/2024 | 04/19/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 423419 | 01904 | 2.33 | Solar | 05_01_610W3 | 02/13/2023 | 02/15/2023 | 2 | 0 | 2 | 02/16/2023 | 02/16/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 433519 | 01824 | 10 | Solar | 05_05_11W84 | 07/14/2022 | 07/21/2022 | 5 | 0 | 5 | 07/22/2022 | 07/22/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2023 | Connected |  | N
National Grid | NEWBURY | 635728 | 01985 | 4.06 | Solar | 05_12_29W5 | 08/27/2024 | 10/04/2024 | 19 | 16 | 3 | 10/07/2024 | 10/07/2024 | 191 | 173 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 642166 | 01843 | 500 | Solar | 05_14_16L2 | 12/23/2024 |  | 298 | 62 | 236 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | DRACUT | 660760 | 01826 | 15.76 | Solar | 05_14_47L1 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | LEICESTER | 256506 | 01524 | 7.6 | Solar | 05_14_61L3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GRAFTON | 748927 | 01560 | 17.3 | Solar | 05_14_75L3 | 02/05/2026 | 02/24/2026 | 12 | 2 | 10 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 176213 | 01566 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 663082 | 01473 | 10 | Solar | 05_01_304W2 | 12/30/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | SWANSEA | 595438 | 02777 | 46 | Solar | 05_01_413L7 | 03/08/2024 | 03/12/2024 | 2 | 0 | 2 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 468590 | 01902 | 16.24 | Solar | 05_01_610W3 | 11/26/2022 | 12/01/2022 | 4 | 2 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2023 | Connected |  | N
National Grid | LOWELL | 471482 | 01852 | 7.6 | Solar | 05_05_11W84 | 11/18/2022 | 11/28/2022 | 6 | 4 | 2 | 11/29/2022 | 11/29/2022 | 393 | 51 | 342 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 644942 | 01985 | 5.76 | Solar | 05_12_29W5 | 10/04/2024 | 02/13/2025 | 5 | 1 | 4 | 02/14/2025 | 02/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LAWRENCE | 637603 | 01843 | 480 | Solar | 05_14_16L2 | 04/11/2025 | 06/23/2025 | 48 | 38 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/24/2025 | 07/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 667332 | 01826 | 7.6 | Solar | 05_14_47L1 | 01/23/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 | 01/23/2025 | 5/1/2026 | Y | EXP | 365 | 10/01/2025 | 11/25/2025 | 56 | 0 | 56 |  |  | 12/4/2025 | Connected |  | N
National Grid | LEICESTER | 278404 | 01524 | 5.76 | Solar | 05_14_61L3 | 04/21/2021 | 04/28/2021 | 4 | 0 | 4 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 12/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2022 | Connected |  | N
National Grid | SUTTON | 752359 | 01590 | 5.76 | Solar | 05_14_75L3 | 02/24/2026 | 02/27/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STURBRIDGE | 176211 | 01566 | 499 | Solar | 05_01_21W2 | 07/02/2015 | 07/02/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 08/09/2016 | 01/19/2017 | 110 | 0 | 110 |  |  | 7/11/2016 | N | STD |  | 01/03/2018 | 04/02/2018 | 50 | 0 | 50 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 672732 | 01472 | 3.8 | Solar | 05_01_304W2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | SWANSEA | 615975 | 02777 | 17.48 | Solar | 05_01_413L7 | 06/10/2024 | 07/11/2024 | 22 | 19 | 3 | 07/12/2024 | 07/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | LYNN | 477503 | 01902 | 7.6 | Solar | 05_01_610W3 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 12/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | LOWELL | 485618 | 01852 | 10 | Solar | 05_05_11W84 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 01/10/2023 | 4/22/2024 | Y | EXP | 365 | 07/04/2023 | 07/12/2023 | 9 | 0 | 9 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 646085 | 01985 | 5.76 | Solar | 05_12_29W5 | 10/10/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | LAWRENCE | 714530 | 01843 | 1000 | Solar | 05_14_16L2 | 10/10/2025 | 11/12/2025 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 691485 | 01826 | 7.6 | Solar | 05_14_47L1 | 05/23/2025 | 06/13/2025 | 6 | 2 | 4 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 293829 | 01524 | 3.8 | Solar | 05_14_61L3 | 06/08/2020 | 06/10/2020 | 1 | 0 | 1 | 06/11/2020 | 06/11/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 06/08/2020 | 11/11/2021 | Y | EXP | 365 | 11/18/2020 | 12/09/2020 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | GRAFTON | 174327 | 01560 | 1500 | Solar | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 176285 | 01566 | 1000 | Solar | 05_01_21W2 | 07/09/2015 | 07/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2015 | 08/07/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/05/2017 | 10/06/2016 | 0 | 0 | 0 | 10/6/2016 | 07/09/2015 | 7/15/2016 | Y | STD | 83 | 08/07/2017 | 10/27/2017 | 57 | 0 | 57 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | WESTMINSTER | 678189 | 01473 | 3.8 | Solar | 05_01_304W2 | 03/14/2025 | 03/20/2025 | 4 | 0 | 4 | 03/21/2025 | 03/21/2025 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | SOMERSET | 623119 | 02725 | 9.86 | Solar | 05_01_413L7 | 07/08/2024 | 07/31/2024 | 14 | 12 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/08/2024 | 8/26/2025 | Y | EXP | 365 | 08/30/2024 | 10/03/2024 | 35 | 0 | 35 |  |  | 10/24/2024 | Connected |  | N
National Grid | LYNN | 494286 | 01905 | 7.6 | Solar | 05_01_610W3 | 02/06/2023 | 02/08/2023 | 2 | 0 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/06/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2023 | Connected |  | Y
National Grid | LOWELL | 494490 | 01852 | 10 | Solar | 05_05_11W84 | 01/26/2023 | 01/30/2023 | 2 | 0 | 2 | 01/31/2023 | 01/31/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/26/2023 | 9/14/2024 | Y | EXP | 365 | 06/24/2023 | 09/14/2023 | 83 | 0 | 83 |  |  | 9/20/2023 | Connected |  | N
National Grid | NEWBURY | 647380 | 01985 | 3.8 | Solar | 05_12_29W5 | 10/15/2024 | 11/01/2024 | 8 | 3 | 5 | 11/04/2024 | 11/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/15/2024 | 11/26/2025 | Y | EXP | 365 | 02/26/2025 | 03/24/2025 | 27 | 0 | 27 |  |  | 3/28/2025 | Connected |  | N
National Grid | LAWRENCE | 174629 | 01843 | 500 | Solar | 05_14_16L2 | 05/17/2011 | 05/17/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2011 | 05/17/2011 | 1/23/2012 | Y | EXP | 217 | 10/19/2011 | 11/18/2011 | 21 | 0 | 21 | 8/6/2012 | 8/6/2012 | 1/23/2012 | Connected |  | N
National Grid | DRACUT | 737669 | 01826 | 13.3 | Solar | 05_14_47L1 | 12/02/2025 |  | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 296132 | 01524 | 5.04 | Solar | 05_14_61L3 | 07/02/2020 | 07/07/2020 | 2 | 0 | 2 | 07/08/2020 | 07/08/2020 | 71 | 50 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2020 |  | 10/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 174326 | 01590 | 1000 | Solar | 05_14_75L3 | 12/20/2011 | 12/20/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 09/04/2014 | 87 | 0 | 87 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 177930 | 01566 | 2000 | Solar | 05_01_21W2 | 04/19/2017 | 04/19/2017 | 235 | 234 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/25/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 694781 | 01473 | 5.76 | Solar | 05_01_304W2 | 06/06/2025 | 06/13/2025 | 5 | 0 | 5 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | SWANSEA | 642171 | 02777 | 23 | Solar | 05_01_413L7 | 10/18/2024 | 10/23/2024 | 4 | 2 | 2 | 10/24/2024 | 10/24/2024 | 70 | 58 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | LYNN | 536407 | 01902 | 15.2 | Solar | 05_01_610W3 | 06/30/2023 | 07/05/2023 | 2 | 1 | 1 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | LOWELL | 515758 | 01851 | 15.2 | Solar | 05_05_11W84 | 07/17/2023 | 04/07/2023 | 1 | 0 | 1 | 07/19/2023 | 07/19/2023 | 100 | 78 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2023 |  | 1/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2024 | Connected |  | N
National Grid | NEWBURY | 650334 | 01985 | 7.6 | Solar | 05_12_29W5 | 11/07/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 11/07/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | LAWRENCE | 177798 | 01843 | 233.1 | Solar | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/18/2017 | 08/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 8/9/2018 | Y | EXP | 336 | 02/12/2018 | 03/07/2018 | 13 | 0 | 13 | 3/9/2018 | 3/9/2018 | 3/9/2018 | Connected |  | N
National Grid | DRACUT | 683265 | 01826 | 4998 | Other | 05_14_47L2 | 10/16/2025 | 12/10/2025 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 | 01/09/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LEICESTER | 302207 | 01524 | 7.6 | Solar | 05_14_61L3 | 08/19/2020 | 08/26/2020 | 4 | 0 | 4 | 08/27/2020 | 08/27/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | GRAFTON | 174961 | 01560 | 60 | Solar | 05_14_75L3 | 03/05/2013 | 03/05/2013 | 4 | 0 | 4 | 03/15/2013 | 03/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2013 | 03/05/2013 | 6/14/2013 | Y | EXP | 18 | 01/30/2014 | 03/11/2014 | 27 | 0 | 27 | 4/24/2014 | 4/24/2014 | 4/24/2014 | Connected |  | N
National Grid | STURBRIDGE | 255873 | 01566 | 5000 | Solar | 05_01_21W2 | 11/20/2019 | 12/01/2019 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2019 | 12/09/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 736690 | 01473 | 21.28 | Solar | 05_01_304W3 | 11/26/2025 | 12/01/2025 | 2 | 0 | 2 | 12/02/2025 | 12/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 691149 | 02777 | 15.2 | Solar | 05_01_413L7 | 05/19/2025 | 05/22/2025 | 3 | 0 | 3 | 05/23/2025 | 05/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | LYNN | 623437 | 01904 | 1.74 | Solar | 05_01_610W3 | 07/09/2024 | 07/19/2024 | 2 | 0 | 2 | 07/22/2024 | 07/22/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 8/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2024 | Connected |  | N
National Grid | LOWELL | 532784 | 01851 | 0 | Other | 05_05_11W84 | 08/15/2023 | 10/05/2023 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2023 | 12/06/2023 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 650659 | 01950 | 8.45 | Solar | 05_12_29W5 | 11/06/2024 | 02/24/2025 | 18 | 14 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 11/06/2024 | 8/15/2026 | Y | EXP | 365 | 09/25/2025 | 11/05/2025 | 42 | 0 | 42 |  |  | 2/6/2026 | Connected |  | N
National Grid | LAWRENCE | 177800 | 01843 | 266.4 | Solar | 05_14_16L2 | 08/03/2017 | 08/03/2017 | 14 | 14 | 0 | 08/24/2017 | 08/24/2017 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 | 08/03/2017 | 11/30/2020 | Y | EXP | 879 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | DRACUT | 733360 | 01826 | 17.28 | Solar | 05_14_47L2 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LEICESTER | 317759 | 01524 | 7.6 | Solar | 05_14_61L3 | 10/29/2020 | 11/02/2020 | 1 | 0 | 1 | 11/03/2020 | 11/03/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/29/2020 |  | Y | EXP | 365 | 04/17/2021 | 09/01/2021 | 136 | 3 | 133 |  |  | 9/8/2021 | Connected |  | N
National Grid | MILLBURY | 175207 | 01527 | 12 | Solar | 05_14_75L3 | 12/04/2012 | 12/04/2012 | 7 | 0 | 7 | 12/17/2012 | 12/17/2012 | 214 | 0 | 214 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 3/1/2013 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 272127 | 01566 | 4950 | Other | 05_01_21W2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTMINSTER | 173709 | 01473 | 3.8 | Solar | 05_01_304W3 | 04/16/2018 | 04/16/2018 | 0 | 0 | 0 | 06/05/2018 | 06/05/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 306145 | 02777 | 0 | Other | 05_01_415L1 | 09/08/2020 | 10/02/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2020 | 10/26/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 |  | Y | STD | 7 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 623866 | 01902 | 3.8 | Solar | 05_01_610W3 | 07/10/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 549535 | 01852 | 0 | Solar | 05_05_11W84 | 08/23/2023 | 08/30/2023 | 6 | 4 | 2 | 08/31/2023 | 08/31/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 654196 | 01985 | 5.76 | Solar | 05_12_29W5 | 11/18/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/18/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2025 | Connected |  | N
National Grid | LAWRENCE | 178588 | 01843 | 350 | Solar | 05_14_16L2 | 03/13/2018 | 03/13/2018 | 1 | 0 | 1 | 05/16/2018 | 05/16/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 12/2/2019 | N | EXP | 551 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | DRACUT | 738477 | 01826 | 18.24 | Solar | 05_14_47L2 | 01/15/2026 | 02/02/2026 | 11 | 8 | 3 | 02/03/2026 | 02/03/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEICESTER | 320644 | 01524 | 3.8 | Solar | 05_14_61L3 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 175812 | 01527 | 17.63 | Solar | 05_14_75L3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 7/13/2015 | 7/13/2015 | 11/20/2015 | Connected |  | N
National Grid | CHARLTON | 293665 | 01507 | 8.4 | Solar | 05_01_21W2 | 06/11/2020 | 06/29/2020 | 11 | 6 | 5 | 06/30/2020 | 06/30/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | WESTMINSTER | 173360 | 01473 | 7.6 | Solar | 05_01_304W3 | 07/31/2018 | 08/06/2018 | 1 | 0 | 1 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 | 07/31/2018 | 8/8/2019 | Y | EXP | 365 | 04/03/2019 | 04/02/2019 | 0 | 0 | 0 |  |  | 4/18/2019 | Connected |  | N
National Grid | SOMERSET | 637437 | 02725 | 499.9 | Solar | 05_01_415L1 | 09/17/2024 | 11/04/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/05/2024 | 03/13/2025 | 87 | 67 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 655947 | 01902 | 10 | Solar | 05_01_610W3 | 11/21/2024 | 01/06/2025 | 16 | 12 | 4 | 01/07/2025 | 01/07/2025 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | LOWELL | 565023 | 01852 | 5 | Solar | 05_05_11W84 | 10/25/2023 | 10/30/2023 | 4 | 2 | 2 | 10/31/2023 | 10/31/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 1/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 664824 | 01985 | 7.6 | Solar | 05_12_29W5 | 01/10/2025 | 02/03/2025 | 10 | 5 | 5 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 | 03/10/2025 | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/07/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2025 | Connected |  | N
National Grid | LAWRENCE | 314332 | 01843 | 10 | Solar | 05_14_16L2 | 10/08/2020 | 10/12/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 1/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 738893 | 01826 | 3.49 | Solar | 05_14_47L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 46 | 31 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEICESTER | 321550 | 01542 | 3.6 | Solar | 05_14_61L3 | 11/09/2020 | 11/12/2020 | 1 | 0 | 1 | 11/13/2020 | 11/13/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/09/2020 | 12/21/2021 | Y | EXP | 365 | 08/06/2021 | 10/11/2021 | 60 | 3 | 57 |  |  | 10/21/2021 | Connected |  | N
National Grid | MILLBURY | 178497 | 01527 | 7.6 | Solar | 05_14_75L3 | 12/04/2017 | 12/04/2017 | 64 | 59 | 5 | 03/26/2018 | 03/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2018 |  | 12/10/2018 | N | EXP | 259 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 336469 | 01566 | 10 | Solar | 05_01_21W2 | 01/22/2021 | 01/10/2022 | 2 | 0 | 2 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/22/2021 | 5/13/2023 | Y | EXP | 365 | 02/22/2022 | 04/11/2022 | 48 | 0 | 48 |  |  | 5/20/2022 | Connected |  | N
National Grid | WESTMINSTER | 175254 | 01473 | 6.88 | Solar | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 5 | 0 | 5 | 11/14/2014 | 11/14/2014 | 147 | 0 | 147 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2014 |  | 1/30/2015 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 656358 | 02777 | 487.5 | Solar | 05_01_415L1 | 12/06/2024 | 02/12/2025 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2025 | 03/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LYNN | 554299 | 01902 | 1999.998 | Solar | 05_01_612W1 | 04/23/2024 | 10/18/2024 | 123 | 116 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CHELMSFORD | 575399 | 01824 | 6 | Solar | 05_05_11W84 | 12/12/2023 | 12/19/2023 | 5 | 2 | 3 | 12/20/2023 | 12/20/2023 | 26 | 6 | 20 | 02/13/2024 | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 03/07/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 2/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 698445 | 01985 | 5.76 | Solar | 05_12_29W5 | 06/18/2025 | 07/18/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 06/18/2025 | 11/14/2026 | Y | EXP | 365 | 09/04/2025 | 09/03/2025 | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | LAWRENCE | 599266 | 01843 | 6 | Solar | 05_14_16L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/26/2024 | 4/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | DRACUT | 175224 | 01826 | 19 | Solar | 05_14_47L2 | 01/06/2015 | 01/06/2015 | 43 | 40 | 3 | 03/11/2015 | 03/11/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 5/1/2015 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 342956 | 01524 | 11.4 | Solar | 05_14_61L3 | 02/18/2021 | 02/19/2021 | 0 | 0 | 0 | 02/22/2021 | 02/22/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/18/2021 | 2/18/2022 | Y | EXP | 365 | 05/26/2021 | 07/08/2021 | 43 | 0 | 43 |  |  | 8/13/2021 | Connected |  | N
National Grid | MILLBURY | 178631 | 01527 | 7.6 | Solar | 05_14_75L3 | 03/15/2018 | 03/15/2018 | 13 | 13 | 0 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 3/21/2019 | N | EXP | 311 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 384247 | 01566 | 0 | Other | 05_01_21W2 | 03/30/2022 | 04/27/2022 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/28/2022 | 06/01/2022 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 175251 | 01475 | 17.2 | Solar | 05_01_304W3 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/19/2016 | Connected |  | N
National Grid | SWANSEA | 697596 | 02777 | 15.08 | Solar | 05_01_415L1 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 553455 | 01902 | 120 | Solar | 05_01_612W1 | 09/11/2023 | 09/29/2023 | 15 | 5 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LOWELL | 626348 | 01852 | 9.92 | Solar | 05_05_11W84 | 07/19/2024 | 07/29/2024 | 2 | 0 | 2 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/19/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/18/2024 | 13 | 0 | 13 |  |  | 10/31/2024 | Connected |  | N
National Grid | NEWBURY | 710194 | 01985 | 240 | Solar | 05_12_29W6 | 08/12/2025 | 09/11/2025 | 21 | 11 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ANDOVER | 639458 | 01810 | 5.76 | Solar | 05_14_16L2 | 09/11/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/11/2024 | 11/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | METHUEN | 175431 | 01844 | 354 | Solar | 05_14_47L2 | 09/18/2014 | 09/18/2014 | 6 | 0 | 6 | 09/29/2014 | 09/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 | 09/18/2014 | 6/1/2015 | Y | EXP | 28 | 10/07/2015 | 11/23/2015 | 31 | 0 | 31 | 11/5/2014 | 11/5/2014 | 11/23/2015 | Connected |  | N
National Grid | LEICESTER | 449817 | 01524 | 9.45 | Solar | 05_14_61L3 | 08/09/2022 | 08/12/2022 | 3 | 0 | 3 | 08/15/2022 | 08/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2022 | 08/09/2022 | 2/24/2024 | Y | EXP | 365 | 01/24/2023 | 02/07/2023 | 15 | 0 | 15 |  |  | 6/8/2023 | Connected |  | N
National Grid | MILLBURY | 199466 | 01527 | 10 | Solar | 05_14_75L3 | 10/25/2018 | 11/01/2018 | 1 | 0 | 1 | 11/02/2018 | 11/02/2018 | 77 | 35 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 396703 | 01507 | 250 | Solar | 05_01_21W2 | 12/27/2021 |  | 215 | 208 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175362 | 01475 | 336 | Solar | 05_01_304W3 | 11/14/2014 | 11/14/2014 | 4 | 1 | 3 | 11/21/2014 | 11/21/2014 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 |  | 3/31/2015 | N | EXP | 76 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 731442 | 02725 | 11.5 | Solar | 05_01_415L1 | 11/13/2025 | 11/20/2025 | 5 | 4 | 1 | 11/21/2025 | 11/21/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 579723 | 01970 | 3000 | Solar | 05_01_612W1 | 04/26/2024 | 10/18/2024 | 120 | 111 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 05/06/2025 | 134 | 115 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 633817 | 01851 | 7.475 | Solar | 05_05_11W84 | 08/20/2024 | 08/23/2024 | 2 | 0 | 2 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 08/20/2024 | 12/18/2025 | Y | EXP | 365 | 01/03/2025 | 01/14/2025 | 12 | 0 | 12 |  |  | 1/23/2025 | Connected |  | N
National Grid | NEWBURY | 720948 | 01985 | 150 | Solar | 05_12_29W6 | 09/23/2025 | 10/31/2025 | 27 | 20 | 7 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LAWRENCE | 671565 | 01843 | 3.8 | Solar | 05_14_16L2 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | DRACUT | 175784 | 01826 | 14 | Solar | 05_14_47L2 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 8/1/2016 | N | EXP | 244 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 9/25/2017 | Connected |  | N
National Grid | LEICESTER | 450807 | 01542 | 5 | Solar | 05_14_61L3 | 09/27/2022 | 09/30/2022 | 4 | 1 | 3 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 09/27/2022 | 1/21/2024 | Y | EXP | 365 | 01/21/2023 | 01/20/2023 | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | MILLBURY | 211523 | 01527 | 23.4 | Solar | 05_14_75L3 | 03/19/2019 | 03/26/2019 | 5 | 3 | 2 | 03/27/2019 | 03/27/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 |  | 3/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2020 | Connected |  | N
National Grid | CHARLTON | 457727 | 01507 | 5.22 | Solar | 05_01_21W2 | 09/27/2022 | 09/30/2022 | 3 | 0 | 3 | 10/03/2022 | 10/03/2022 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/27/2022 | 5/19/2024 | Y | EXP | 365 | 04/21/2023 | 05/19/2023 | 29 | 0 | 29 |  |  | 6/9/2023 | Connected |  | N
National Grid | WINCHENDON | 176069 | 01475 | 6 | Solar | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2015 |  | 6/27/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 7/29/2016 | Connected |  | N
National Grid | SWANSEA | 741796 | 02777 | 10 | Solar | 05_01_415L1 | 12/22/2025 | 12/23/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 729943 | 01970 |  | Battery Add-On | 05_01_612W1 | 10/29/2025 | 11/11/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 | 10/29/2025 | 1/23/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LOWELL | 644735 | 01851 | 3.8 | Solar | 05_05_11W84 | 10/03/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | NEWBURY | 720438 | 01985 | 150 | Solar | 05_12_29W6 | 09/22/2025 | 11/14/2025 | 37 | 29 | 8 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LAWRENCE | 558959 | 01843 | 240 | Solar | 05_14_16L3 | 09/29/2023 | 10/23/2023 | 15 | 5 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 09/29/2023 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | DRACUT | 177603 | 01826 | 12 | Solar | 05_14_47L2 | 07/19/2017 | 07/19/2017 | 11 | 11 | 0 | 08/03/2017 | 08/03/2017 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/24/2018 | N | EXP | 354 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 426525 | 01524 | 10 | Solar | 05_14_61L3 | 05/13/2022 | 05/17/2022 | 2 | 0 | 2 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 | 05/13/2022 | 10/19/2023 | Y | EXP | 365 | 08/16/2022 | 10/19/2022 | 65 | 0 | 65 |  |  | 11/2/2022 | Connected |  | N
National Grid | MILLBURY | 212099 | 01527 | 10 | Solar | 05_14_75L3 | 04/12/2019 | 05/28/2019 | 30 | 30 | 0 | 05/29/2019 | 05/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 | 04/12/2019 | 2/21/2020 | Y | EXP | 259 | 12/19/2019 | 01/29/2020 | 41 | 0 | 41 |  |  | 1/31/2020 | Connected |  | N
National Grid | CHARLTON | 176101 | 01507 | 7.6 | Solar | 05_01_304W3 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 4/19/2016 | Connected |  | N
National Grid | WINCHENDON | 742734 | 01475 | 9.12 | Solar | 05_01_415L1 | 12/30/2025 | 01/05/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 174657 | 02725 | 2000 | Solar | 05_01_612W1 | 03/28/2011 | 03/28/2011 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/28/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 645472 | 01970 | 2.03 | Solar | 05_05_11W84 | 10/31/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 25 | 0 | 25 | 01/17/2025 | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 01/28/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 177264 | 01851 | 784 | Solar | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 664845 | 01950 | 140 | Solar | 05_14_16L3 | 01/13/2025 | 03/19/2025 | 45 | 36 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | LAWRENCE | 178075 | 01843 | 3375 | Solar | 05_14_47L2 | 11/03/2017 | 11/03/2017 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/09/2018 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/8/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 433662 | 01826 | 10 | Solar | 05_14_61L3 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 218706 | 01524 | 7.6 | Solar | 05_14_75L3 | 05/16/2019 | 05/24/2019 | 5 | 0 | 5 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 470048 | 01527 | 20 | Solar | 05_01_21W2 | 10/21/2022 | 10/27/2022 | 4 | 2 | 2 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2022 | 10/21/2022 | 6/11/2024 | Y | EXP | 365 | 05/16/2023 | 06/12/2023 | 28 | 0 | 28 |  |  | 6/21/2023 | Connected |  | N
National Grid | CHARLTON | 176140 | 01507 | 6.88 | Solar | 05_01_304W3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 6/22/2016 | Connected |  | N
National Grid | WINCHENDON | 742683 | 01475 | 7.6 | Solar | 05_01_415L1 | 12/30/2025 | 01/06/2026 | 3 | 1 | 2 | 01/15/2026 | 01/15/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 | 12/30/2025 | 2/17/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SOMERSET | 174753 | 02725 | 24.73 | Solar | 05_01_612W1 | 01/31/2014 | 01/31/2014 | 6 | 0 | 6 | 02/11/2014 | 02/11/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2014 |  | 4/30/2014 | N | EXP | 6 |  |  | 0 | 0 | 0 | 7/10/2014 | 7/10/2014 | 8/26/2014 | Connected |  | N
National Grid | SALEM | 647182 | 01970 | 10 | Solar | 05_05_11W84 | 10/15/2024 | 10/22/2024 | 2 | 0 | 2 | 10/23/2024 | 10/23/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | LOWELL | 177927 | 01851 | 784 | Solar | 05_12_29W6 | 11/08/2016 | 11/08/2016 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 01/18/2017 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2017 |  | 6/15/2018 | N | STD | 262 |  |  | 0 | 0 | 0 |  |  | 6/14/2018 | Connected |  | N
National Grid | NEWBURY | 676981 | 01985 | 750 | Solar | 05_14_16L3 | 04/07/2025 | 06/10/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LAWRENCE | 178312 | 01843 | 7.6 | Solar | 05_14_47L2 | 02/26/2018 | 02/26/2018 | 4 | 4 | 0 | 03/05/2018 | 03/05/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 3/3/2019 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  | 10/11/2019 | Connected |  | N
National Grid | DRACUT | 436374 | 01826 | 3.8 | Solar | 05_14_61L3 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 | 06/21/2022 | 8/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 223770 | 01611 | 10 | Solar | 05_14_75L3 | 06/05/2019 | 06/12/2019 | 4 | 0 | 4 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2019 | 06/05/2019 | 10/20/2021 | Y | EXP | 365 | 09/05/2020 | 09/28/2020 | 23 | 0 | 23 |  |  | 1/8/2021 | Connected |  | N
National Grid | MILLBURY | 479173 | 01527 | 15.2 | Solar | 05_01_21W2 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 176387 | 01507 | 11.4 | Solar | 05_01_304W3 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 260 | 0 | 260 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/6/2017 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 747449 | 01475 | 9.12 | Solar | 05_01_415L1 | 02/11/2026 | 02/12/2026 | 1 | 0 | 1 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOMERSET | 176230 | 02725 | 500 | Solar | 05_01_612W1 | 02/11/2015 | 02/11/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 | 04/09/2015 | 07/24/2015 | 72 | 0 | 72 | 02/23/2015 | 03/24/2015 | 20 | 0 | 20 |  | 07/24/2015 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 652291 | 01970 | 15 | Solar | 05_05_11W84 | 11/05/2024 | 11/20/2024 | 2 | 0 | 2 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/05/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LOWELL | 188370 | 01851 | 7.6 | Solar | 05_12_29W6 | 07/03/2018 | 07/03/2018 | 3 | 0 | 3 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 718425 | 01985 | 12.215 | Solar | 05_14_16L3 | 09/16/2025 | 09/29/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 09/16/2025 | 11/24/2026 | Y | EXP | 365 | 01/22/2026 |  | 44 | 0 | 44 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 178352 | 01843 | 10 | Solar | 05_14_47L2 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  | 3/5/2019 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | DRACUT | 439483 | 01826 | 6 | Solar | 05_14_61L3 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 06/29/2022 | 4/13/2024 | Y | EXP | 365 | 03/15/2023 | 04/12/2023 | 29 | 0 | 29 |  |  | 6/12/2023 | Connected |  | N
National Grid | LEICESTER | 234804 | 01524 | 10 | Solar | 05_14_75L3 | 07/15/2019 | 07/16/2019 | 0 | 0 | 0 | 07/17/2019 | 07/17/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2019 | 07/15/2019 | 12/7/2020 | Y | EXP | 365 | 10/28/2020 | 11/09/2020 | 12 | 0 | 12 |  |  | 11/17/2020 | Connected |  | N
National Grid | MILLBURY | 485085 | 01527 | 6 | Solar | 05_01_21W2 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2023 | Connected |  | N
National Grid | CHARLTON | 176551 | 01507 | 7.6 | Solar | 05_01_304W3 | 10/05/2015 | 10/05/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2015 |  | 10/13/2016 | N | EXP | 364 |  |  | 0 | 0 | 0 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | WINCHENDON | 174212 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176256 | 02777 | 2000 | Solar | 05_01_612W1 | 07/09/2015 | 07/09/2015 | 18 | 18 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/26/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/01/2016 | 07/20/2016 | 12 | 0 | 12 | 7/6/2016 | 07/09/2015 | 8/31/2018 | Y | STD | 786 | 04/30/2018 | 06/05/2018 | 36 | 0 | 36 |  |  | 8/10/2018 | Connected |  | N
National Grid | SALEM | 655751 | 01906 | 11.5 | Solar | 05_05_11W84 | 11/20/2024 | 11/21/2024 | 1 | 0 | 1 | 11/22/2024 | 11/22/2024 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | LOWELL | 195677 | 01851 | 5 | Solar | 05_12_29W6 | 09/11/2018 | 11/09/2018 | 12 | 11 | 1 | 11/13/2018 | 11/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 175900 | 01985 | 100 | Solar | 05_14_16L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/11/2016 | Connected |  | N
National Grid | LAWRENCE | 198160 | 01843 | 7.6 | Solar | 05_14_47L2 | 11/16/2018 | 11/19/2018 | 0 | 0 | 0 | 11/20/2018 | 11/20/2018 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 442804 | 01826 | 7.6 | Solar | 05_14_61L3 | 08/04/2022 | 08/05/2022 | 1 | 0 | 1 | 08/08/2022 | 08/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 260249 | 01524 | 9.86 | Solar | 05_14_75L3 | 10/20/2019 | 11/08/2019 | 14 | 9 | 5 | 11/12/2019 | 11/12/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 10/20/2019 | 10/20/2020 | Y | EXP | 365 | 04/21/2020 | 05/13/2020 | 22 | 0 | 22 |  |  | 8/25/2020 | Connected |  | N
National Grid | MILLBURY | 523512 | 01527 | 4000 | Solar | 05_01_21W2 | 07/06/2023 | 08/28/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2023 | 10/13/2023 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176946 | 01508 | 3.8 | Solar | 05_01_304W3 | 12/21/2016 | 12/21/2016 | 4 | 3 | 1 | 12/28/2016 | 12/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 12/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 8/17/2017 | 8/17/2017 | 8/16/2017 | Connected |  | N
National Grid | WINCHENDON | 174211 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176273 | 02777 | 984 | Solar | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/9/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | SALEM | 657190 | 01970 | 5.76 | Solar | 05_05_11W84 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 11/26/2024 | 2/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | LOWELL | 343901 | 01851 | 7.6 | Solar | 05_12_29W6 | 04/02/2021 | 04/06/2021 | 1 | 0 | 1 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | NEWBURY | 200444 | 01950 | 201.6 | Solar | 05_14_16L3 | 11/05/2018 | 11/08/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 06/13/2019 | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2019 | 11/05/2018 | 11/8/2024 | Y | EXP | 7 | 03/01/2024 | 10/08/2024 | 222 | 182 | 40 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 198970 | 01843 | 7.6 | Solar | 05_14_47L2 | 12/21/2018 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 477774 | 01844 | 11.89 | Solar | 05_14_61L3 | 01/25/2023 | 01/26/2023 | 1 | 0 | 1 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 263447 | 01542 | 10 | Solar | 05_14_75L3 | 11/01/2019 | 11/06/2019 | 2 | 0 | 2 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 11/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2020 | Connected |  | N
National Grid | MILLBURY | 526652 | 01527 | 14.5 | Solar | 05_01_21W2 | 06/27/2023 | 06/28/2023 | 1 | 1 | 0 | 06/29/2023 | 06/29/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 | 06/27/2023 | 7/31/2024 | Y | EXP | 365 | 09/14/2023 | 10/10/2023 | 27 | 0 | 27 |  |  | 10/16/2023 | Connected |  | N
National Grid | CHARLTON | 177867 | 01508 | 7.6 | Solar | 05_01_304W3 | 08/09/2017 | 08/09/2017 | 4 | 4 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/15/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/29/2018 | 3/29/2018 | 3/29/2018 | Connected |  | N
National Grid | WINCHENDON | 174213 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176274 | 02777 | 984 | Solar | 05_01_612W1 | 02/19/2015 | 03/02/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2015 | 03/31/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2016 | 02/19/2015 | 12/31/2019 | Y | STD | 1229 | 06/08/2019 | 06/07/2019 | 0 | 0 | 0 | 10/15/2019 | 12/4/2019 | 12/27/2019 | Connected |  | N
National Grid | SALEM | 672553 | 01970 | 5.76 | Solar | 05_05_11W84 | 02/18/2025 | 04/09/2025 | 2 | 0 | 2 | 04/17/2025 | 04/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 02/18/2025 | 6/10/2026 | Y | EXP | 365 | 08/01/2025 | 07/31/2025 | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | LOWELL | 348179 | 01851 | 499.9 | Solar | 05_12_29W6 | 05/14/2021 |  | 373 | 363 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 202097 | 01950 | 3.8 | Solar | 05_14_16L3 | 11/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 11/27/2018 | 11/27/2020 | Y | EXP | 365 | 07/17/2020 | 08/12/2020 | 26 | 0 | 26 |  |  | 8/17/2020 | Connected |  | N
National Grid | LAWRENCE | 199289 | 01843 | 7.6 | Solar | 05_14_47L2 | 10/24/2018 | 12/20/2018 | 20 | 19 | 1 | 12/21/2018 | 12/21/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 10/24/2018 | 12/20/2019 | Y | EXP | 365 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/15/2019 | Connected |  | N
National Grid | DRACUT | 483461 | 01826 | 10 | Solar | 05_14_61L3 | 12/13/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/13/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2023 | Connected |  | N
National Grid | LEICESTER | 292693 | 01524 | 7.6 | Solar | 05_14_75L3 | 06/23/2020 | 06/24/2020 | 0 | 0 | 0 | 06/25/2020 | 06/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 | 06/23/2020 | 11/26/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2020 | Connected |  | N
National Grid | MILLBURY | 566580 | 01527 | 17.6 | Solar | 05_01_21W2 | 12/14/2023 | 12/27/2023 | 8 | 4 | 4 | 12/28/2023 | 12/28/2023 | 83 | 62 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | CHARLTON | 184779 | 01508 | 249.8 | Solar | 05_01_304W3 | 05/08/2018 | 05/08/2018 | 20 | 4 | 16 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 | 05/08/2018 | 7/16/2020 | Y | EXP | 663 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 174362 | 01475 | 17 | Solar | 05_01_415L1 | 05/17/2012 | 05/17/2012 | 6 | 0 | 6 | 05/30/2012 | 05/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/31/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/7/2012 | 9/7/2012 | 4/1/2013 | Connected |  | N
National Grid | SWANSEA | 176430 | 02777 | 2000 | Solar | 05_01_612W1 | 02/04/2016 | 02/04/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2016 | 03/07/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 709427 | 01970 | 9.56 | Solar | 05_05_11W84 | 08/04/2025 | 08/27/2025 | 4 | 0 | 4 | 09/08/2025 | 09/08/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/04/2025 | 10/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2026 | Connected |  | N
National Grid | LOWELL | 364600 | 01851 | 6 | Solar | 05_12_29W6 | 06/28/2021 | 09/02/2021 | 48 | 47 | 1 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 06/28/2021 | 5/13/2023 | Y | EXP | 365 | 03/24/2022 | 04/21/2022 | 29 | 0 | 29 |  |  | 5/16/2022 | Connected |  | N
National Grid | NEWBURY | 260377 | 01950 | 5 | Solar | 05_14_16L3 | 11/12/2019 | 11/18/2019 | 3 | 0 | 3 | 11/19/2019 | 11/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 | 11/12/2019 | 3/3/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N
National Grid | LAWRENCE | 201008 | 01843 | 10 | Solar | 05_14_47L2 | 03/06/2019 | 03/18/2019 | 7 | 0 | 7 | 03/19/2019 | 03/19/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/06/2019 | 4/3/2020 | Y | EXP | 365 | 09/06/2019 | 09/23/2019 | 17 | 0 | 17 |  |  | 10/25/2019 | Connected |  | N
National Grid | DRACUT | 494773 | 01826 | 6 | Solar | 05_14_61L3 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 10/5/2024 | Y | EXP | 365 | 08/12/2023 | 10/05/2023 | 55 | 0 | 55 |  |  | 10/12/2023 | Connected |  | N
National Grid | LEICESTER | 377474 | 01611 | 237.5 | Solar | 05_14_75L3 | 08/30/2021 | 10/07/2021 | 28 | 18 | 10 | 10/08/2021 | 10/08/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 575102 | 01527 | 9.6 | Solar | 05_01_21W2 | 12/19/2023 | 12/20/2023 | 1 | 1 | 0 | 12/21/2023 | 12/21/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | CHARLTON | 186422 | 01507 | 15.2 | Solar | 05_01_304W3 | 05/25/2018 | 05/25/2018 | 9 | 0 | 9 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 174548 | 01475 | 1000 | Solar | 05_01_415L1 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176700 | 02725 | 1980 | Solar | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/03/2016 | 27 | 21 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 719327 | 01970 | 15.2 | Solar | 05_05_11W84 | 09/16/2025 | 10/06/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 09/16/2025 | 11/26/2026 | Y | EXP | 365 | 11/26/2025 | 01/27/2026 | 63 | 13 | 50 |  |  | 12/31/2025 | Connected |  | N
National Grid | LOWELL | 364264 | 01851 | 0 | Solar | 05_12_29W6 | 07/14/2021 | 07/29/2021 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2021 | 09/01/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 270083 | 01950 | 95.4 | Solar | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 207035 | 01843 | 7.6 | Solar | 05_14_47L2 | 02/10/2019 | 03/20/2019 | 26 | 26 | 0 | 03/21/2019 | 03/21/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 519281 | 01844 | 7.6 | Solar | 05_14_61L3 | 04/26/2023 | 05/02/2023 | 4 | 0 | 4 | 05/03/2023 | 05/03/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 04/26/2023 | 8/2/2024 | Y | EXP | 365 | 09/12/2023 | 10/05/2023 | 24 | 0 | 24 |  |  | 10/16/2023 | Connected |  | N
National Grid | LEICESTER | 387839 | 01524 | 50 | Solar | 05_14_75L3 | 11/01/2021 | 12/16/2021 | 31 | 23 | 8 | 12/17/2021 | 12/17/2021 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2022 | 11/01/2021 | 6/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | Y
National Grid | MILLBURY | 643792 | 01527 | 5.76 | Solar | 05_01_21W2 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | CHARLTON | 200350 | 01507 | 7.6 | Solar | 05_01_304W3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 3/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | WINCHENDON | 174547 | 01475 | 1000 | Solar | 05_01_415L1 | 11/09/2011 | 11/09/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 08/01/2014 | 64 | 0 | 64 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176699 | 02777 | 288 | Solar | 05_01_612W1 | 04/22/2016 | 04/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 05/27/2016 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 724378 | 01970 | 23 | Solar | 05_05_11W84 | 10/06/2025 | 10/21/2025 | 9 | 6 | 3 | 10/22/2025 | 10/22/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | LOWELL | 493073 | 01851 | 0 | Other | 05_12_29W6 | 05/01/2023 | 10/23/2023 | 118 | 109 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 12/09/2023 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 270081 | 01950 | 37.8 | Solar | 05_14_16L3 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2020 |  | 12/17/2024 | N | EXP | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 213962 | 01843 | 0 | Solar | 05_14_47L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  | 4/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | METHUEN | 518138 | 01844 | 10 | Solar | 05_14_61L3 | 04/17/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 396830 | 01524 | 16 | Solar | 05_14_75L3 | 11/24/2021 | 12/22/2021 | 36 | 28 | 8 | 11/30/2021 | 11/30/2021 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 1/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | MILLBURY | 645392 | 01527 | 7.6 | Solar | 05_01_21W2 | 10/07/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 1/22/2026 | Y | EXP | 365 | 06/24/2025 | 07/08/2025 | 15 | 0 | 15 |  |  | 8/23/2025 | Connected |  | N
National Grid | CHARLTON | 201445 | 01507 | 7.6 | Solar | 05_01_304W3 | 11/17/2018 | 12/03/2018 | 7 | 5 | 2 | 12/04/2018 | 12/04/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 10/21/2019 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | WINCHENDON | 174737 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 176920 | 02777 | 3100 | Solar | 05_01_612W1 | 11/16/2015 | 11/16/2015 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 | 12/28/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 04/12/2017 | 05/15/2018 | 275 | 0 | 275 | 8/25/2016 | 11/16/2015 | 10/22/2018 | Y | STD | 788 | 05/02/2018 | 07/05/2018 | 64 | 0 | 64 |  |  | 9/25/2018 | Connected |  | N
National Grid | SWAMPSCOTT | 494888 | 01907 | 1500 | Solar | 05_05_11W85 | 07/12/2023 | 07/28/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2023 | 09/18/2023 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/12/2023 | 10/22/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LOWELL | 573931 | 01851 | 10.47 | Solar | 05_12_29W6 | 11/28/2023 | 12/20/2023 | 16 | 16 | 0 | 12/21/2023 | 12/21/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | NEWBURY | 379349 | 01985 | 5 | Solar | 05_14_16L3 | 10/08/2021 | 01/04/2022 | 2 | 0 | 2 | 10/14/2021 | 10/14/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 2/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | LAWRENCE | 223680 | 01843 | 7 | Solar | 05_14_47L2 | 04/30/2019 | 09/11/2019 | 40 | 36 | 4 | 09/12/2019 | 09/12/2019 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 |  | 9/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2020 | Connected |  | N
National Grid | DRACUT | 543146 | 01826 | 9.6 | Solar | 05_14_61L3 | 08/30/2023 | 09/08/2023 | 6 | 5 | 1 | 09/11/2023 | 09/11/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 08/30/2023 | 11/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2024 | Connected |  | N
National Grid | LEICESTER | 403697 | 01524 | 0 | Solar | 05_14_75L3 | 12/28/2021 | 01/05/2022 | 6 | 2 | 4 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 2/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | MILLBURY | 646994 | 01527 | 7.6 | Solar | 05_01_21W2 | 10/28/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 202103 | 01508 | 3.8 | Solar | 05_01_304W3 | 11/27/2018 | 12/20/2018 | 4 | 0 | 4 | 12/21/2018 | 12/21/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 | 11/27/2018 | 5/14/2020 | Y | EXP | 482 | 11/23/2019 | 01/03/2020 | 41 | 0 | 41 |  |  | 2/27/2020 | Connected |  | N
National Grid | WINCHENDON | 174736 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 177187 | 02777 | 498 | Solar | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 494886 | 01970 | 2000 | Solar | 05_05_11W85 | 07/06/2023 | 08/24/2023 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2023 | 09/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 07/06/2023 | 10/22/2027 | Y | STD | 791 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LOWELL | 610926 | 01851 | 9.57 | Solar | 05_12_29W6 | 05/14/2024 | 08/21/2024 | 5 | 2 | 3 | 08/22/2024 | 08/22/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 10/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | NEWBURY | 405329 | 01985 | 150 | Solar | 05_14_16L3 | 02/16/2022 | 04/04/2022 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 02/16/2022 | 10/26/2024 | Y | STD | 98 | 07/09/2024 | 02/13/2025 | 220 | 19 | 201 |  |  | 10/21/2024 | Connected |  | N
National Grid | LAWRENCE | 248584 | 01843 | 10 | Solar | 05_14_47L2 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 10/21/2019 | N | EXP | 62 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | DRACUT | 543499 | 01826 | 6 | Solar | 05_14_61L3 | 07/28/2023 | 07/31/2023 | 1 | 0 | 1 | 08/01/2023 | 08/01/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 405449 | 01524 | 7.54 | Solar | 05_14_75L3 | 03/01/2022 | 05/05/2022 | 47 | 45 | 2 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 03/01/2022 | 10/1/2023 | Y | EXP | 365 | 09/20/2022 | 09/28/2022 | 9 | 0 | 9 |  |  | 1/17/2023 | Connected |  | N
National Grid | MILLBURY | 662098 | 01527 | 0 | Solar | 05_01_21W2 | 01/09/2025 | 01/10/2025 | 1 | 0 | 1 | 01/13/2025 | 01/13/2025 | 75 | 53 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | CHARLTON | 207293 | 01508 | 10 | Solar | 05_01_304W3 | 01/31/2019 | 02/11/2019 | 6 | 6 | 0 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 01/31/2019 | 10/17/2019 | Y | EXP | 238 | 04/23/2019 | 05/30/2019 | 37 | 0 | 37 |  |  | 6/24/2019 | Connected |  | N
National Grid | WINCHENDON | 174735 | 01475 | 1000 | Solar | 05_01_415L1 | 01/13/2012 | 01/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2012 | 06/13/2012 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/15/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 177186 | 02777 | 498 | Solar | 05_01_612W1 | 08/12/2016 | 08/12/2016 | 30 | 30 | 0 | 09/28/2016 | 09/28/2016 | 116 | 25 | 91 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 711672 | 01970 | 260 | Solar | 05_05_11W85 | 02/03/2026 | 03/05/2026 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 621136 | 01851 | 7.6 | Solar | 05_12_29W6 | 06/27/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | NEWBURY | 513162 | 01985 | 5.67 | Solar | 05_14_16L3 | 04/13/2023 | 04/19/2023 | 3 | 1 | 2 | 04/20/2023 | 04/20/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 04/13/2023 | 6/9/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | LAWRENCE | 283910 | 01843 | 10 | Solar | 05_14_47L2 | 03/17/2020 | 04/01/2020 | 10 | 7 | 3 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2020 | Connected |  | Y
National Grid | METHUEN | 546077 | 01844 | 3.8 | Solar | 05_14_61L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 20 | 1 | 19 | 09/15/2023 | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 10/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 10/6/2023 |  | 12/31/2024 | N | EXP | 365 | 01/20/2024 | 01/19/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 423047 | 01507 | 150 | Solar | 05_14_75L3 | 04/14/2022 | 05/24/2022 | 27 | 19 | 8 | 05/25/2022 | 05/25/2022 | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 |  | 11/27/2023 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  | 10/18/2023 | Connected |  | N
National Grid | MILLBURY | 667331 | 01527 | 10 | Solar | 05_01_21W2 | 01/23/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/23/2025 | 4/7/2026 | Y | EXP | 365 | 08/05/2025 | 10/01/2025 | 58 | 0 | 58 |  |  | 11/20/2025 | Connected |  | N
National Grid | CHARLTON | 209039 | 01508 | 10 | Solar | 05_01_304W3 | 02/19/2019 | 03/29/2019 | 27 | 26 | 1 | 04/01/2019 | 04/01/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 | 02/19/2019 | 5/17/2021 | Y | EXP | 365 | 10/02/2020 | 12/08/2020 | 67 | 0 | 67 |  |  | 4/30/2021 | Connected |  | N
National Grid | WINCHENDON | 175538 | 01475 | 499 | Solar | 05_01_415L1 | 10/06/2014 | 10/06/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 177177 | 02777 | 144 | Solar | 05_01_612W1 | 06/02/2016 | 06/02/2016 | 5 | 5 | 0 | 06/10/2016 | 06/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2016 |  | 6/8/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 | 11/16/2016 | 11/16/2016 | 11/16/2016 | Connected |  | N
National Grid | SALEM | 174338 | 01970 | 260 | Solar | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/1/2013 |  | 2/15/2012 | N | STD | 38 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 5/8/2015 | Connected |  | N
National Grid | LOWELL | 652997 | 01851 | 7.6 | Solar | 05_12_29W6 | 11/14/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/14/2024 | 2/26/2026 | Y | EXP | 365 | 06/12/2025 | 11/26/2025 | 168 | 0 | 168 |  |  | 12/15/2025 | Connected |  | N
National Grid | NEWBURY | 556991 | 01950 | 80 | Solar | 05_14_16L3 | 09/21/2023 | 10/12/2023 | 14 | 3 | 11 |  |  | 93 | 72 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 408613 | 01843 | 15.2 | Solar | 05_14_47L2 | 01/26/2022 | 02/03/2022 | 7 | 6 | 1 | 02/04/2022 | 02/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 7/15/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 566020 | 01826 | 7.6 | Solar | 05_14_61L3 | 11/15/2023 | 12/05/2023 | 13 | 8 | 5 | 12/06/2023 | 12/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/15/2023 | 8/12/2025 | Y | EXP | 365 | 06/06/2024 | 09/16/2024 | 103 | 0 | 103 |  |  | 4/1/2025 | Connected |  | N
National Grid | LEICESTER | 454191 | 01611 | 3.48 | Solar | 05_14_75L3 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | MILLBURY | 670752 | 01527 | 7.6 | Solar | 05_01_21W2 | 02/07/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 219923 | 01507 | 7.6 | Solar | 05_01_304W3 | 06/07/2019 | 06/18/2019 | 6 | 0 | 6 | 06/19/2019 | 06/19/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/07/2019 | 9/16/2020 | Y | EXP | 365 | 05/29/2020 | 06/23/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | WINCHENDON | 175533 | 01475 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 177215 | 02777 | 60 | Solar | 05_01_612W1 | 06/10/2016 | 06/10/2016 | 7 | 7 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 6/18/2017 | N | EXP | 341 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/15/2016 | 11/15/2016 | Connected |  | N
National Grid | SALEM | 174337 | 01970 | 499 | Solar | 05_05_11W85 | 01/27/2012 | 01/27/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 |  | 4/14/2012 | N | STD | 285 |  |  | 0 | 0 | 0 | 1/29/2015 | 1/29/2015 | 2/18/2015 | Connected |  | N
National Grid | LOWELL | 669791 | 01851 | 7.6 | Solar | 05_12_29W6 | 02/04/2025 | 03/19/2025 | 18 | 14 | 4 | 03/20/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | NEWBURY | 556253 | 01950 | 0 | Battery Add-On | 05_14_16L3 | 09/18/2023 | 10/06/2023 | 15 | 14 | 1 | 10/10/2023 | 10/10/2023 | 86 | 69 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2024 | Connected |  | N
National Grid | LAWRENCE | 461606 | 01843 | 7.6 | Solar | 05_14_47L2 | 09/29/2022 | 12/20/2022 | 5 | 0 | 5 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 09/29/2022 | 6/27/2024 | Y | EXP | 365 | 08/10/2023 | 08/22/2023 | 13 | 0 | 13 |  |  | 9/11/2023 | Connected |  | N
National Grid | METHUEN | 561606 | 01844 | 3.8 | Solar | 05_14_61L3 | 10/10/2023 | 10/16/2023 | 5 | 3 | 2 | 10/17/2023 | 10/17/2023 | 34 | 16 | 18 | 12/11/2023 | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 21 | 3 | 18 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 11/30/2025 | N | EXP | 6 | 05/02/2024 | 05/29/2024 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 557324 | 01524 | 3.8 | Solar | 05_14_75L3 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 79 | 24 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 680083 | 01527 | 22.672 | Solar | 05_01_21W2 | 04/15/2025 | 04/25/2025 | 7 | 0 | 7 | 04/28/2025 | 04/28/2025 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | CHARLTON | 219134 | 01507 | 4.56 | Solar | 05_01_304W3 | 07/01/2019 | 08/02/2019 | 22 | 18 | 4 | 08/05/2019 | 08/05/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 | 07/01/2019 | 8/3/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | WINCHENDON | 175532 | 01475 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 177429 | 02777 | 4980 | Solar | 05_01_612W1 | 02/27/2017 | 03/29/2017 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/14/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/27/2017 | 2/28/2020 | Y | STD | 771 | 10/04/2019 | 12/20/2019 | 77 | 0 | 77 |  |  | 1/30/2020 | Connected |  | N
National Grid | SALEM | 174334 | 01970 | 185.6 | Solar | 05_05_11W85 | 01/24/2012 | 01/24/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 2/15/2012 | N | EXP | 31 |  |  | 0 | 0 | 0 | 11/21/2012 | 11/21/2012 | 12/13/2012 | Connected |  | N
National Grid | LOWELL | 674089 | 01851 | 14.82 | Solar | 05_12_29W6 | 02/25/2025 | 03/05/2025 | 7 | 4 | 3 | 03/06/2025 | 03/06/2025 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | NEWBURY | 558659 | 01985 | 200 | Solar | 05_14_16L3 | 10/05/2023 | 10/23/2023 | 12 | 2 | 10 |  |  | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 464397 | 01843 | 9.86 | Solar | 05_14_47L2 | 10/14/2022 | 10/27/2022 | 9 | 0 | 9 | 10/28/2022 | 10/28/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 | 10/14/2022 | 12/5/2023 | Y | EXP | 365 | 01/25/2023 | 02/01/2023 | 8 | 0 | 8 |  |  | 4/7/2023 | Connected |  | N
National Grid | DRACUT | 562630 | 01826 | 10 | Solar | 05_14_61L3 | 10/12/2023 | 11/02/2023 | 15 | 12 | 3 | 11/03/2023 | 11/03/2023 | 87 | 66 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 10/12/2023 | 3/23/2025 | Y | EXP | 365 | 05/16/2024 | 06/03/2024 | 19 | 0 | 19 |  |  | 6/7/2024 | Connected |  | N
National Grid | LEICESTER | 559958 | 01542 | 10 | Solar | 05_14_75L3 | 10/19/2023 | 10/26/2023 | 5 | 4 | 1 | 10/27/2023 | 10/27/2023 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 | 10/19/2023 | 1/7/2025 | Y | EXP | 365 | 03/06/2024 | 03/26/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 680372 | 01527 | 0 | Battery Add-On | 05_01_225W1 | 03/25/2025 | 05/22/2025 | 40 | 36 | 4 | 05/23/2025 | 05/23/2025 | 114 | 96 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 265736 | 01507 | 10 | Solar | 05_01_304W3 | 11/20/2019 | 11/21/2019 | 0 | 0 | 0 | 11/22/2019 | 11/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 | 11/20/2019 | 7/22/2020 | Y | EXP | 365 | 03/28/2020 | 03/30/2020 | 2 | 0 | 2 |  |  | 4/6/2020 | Connected |  | N
National Grid | WINCHENDON | 175531 | 01475 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 |  | 5/1/2016 | N | STD | 177 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 178389 | 02777 | 15.2 | Solar | 05_01_612W1 | 03/01/2018 | 04/03/2018 | 11 | 11 | 0 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 174454 | 01970 | 3260 | Solar | 05_05_11W85 | 07/13/2012 | 07/13/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 657092 | 01851 | 5.76 | Solar | 05_12_2W1 | 11/26/2024 | 01/30/2025 | 2 | 0 | 2 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 | 11/26/2024 | 3/18/2026 | Y | EXP | 365 | 06/14/2025 | 09/12/2025 | 91 | 0 | 91 |  |  |  | Completion Documents |  | Y
National Grid | NEWBURY | 592199 | 01985 | 7.6 | Solar | 05_14_16L3 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 4 | 2 | 2 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 550096 | 01843 | 9.984 | Solar | 05_14_47L2 | 01/10/2024 | 09/07/2023 | 0 | 0 | 0 | 01/23/2024 | 01/23/2024 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2024 | Connected |  | N
National Grid | DRACUT | 573321 | 01826 | 3.8 | Solar | 05_14_61L3 | 01/12/2024 | 01/30/2024 | 11 | 8 | 3 | 01/31/2024 | 01/31/2024 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 01/12/2024 | 4/10/2025 | Y | EXP | 365 | 05/16/2024 | 08/21/2024 | 98 | 0 | 98 |  |  | 8/31/2024 | Connected |  | N
National Grid | BOLTON | 559163 | 01740 | 250 | Solar | 05_14_75L3 | 11/03/2023 | 11/21/2023 | 10 | 0 | 10 |  |  | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 685002 | 01527 | 5000 | Solar | 05_01_225W1 | 12/19/2025 | 01/30/2026 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2026 |  | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 330585 | 01507 | 3.12 | Solar | 05_01_304W3 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 175530 | 01475 | 499 | Solar | 05_01_415L1 | 09/29/2014 | 09/29/2014 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2014 | 11/05/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2015 | 09/29/2014 | 5/1/2016 | Y | STD | 177 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | SWANSEA | 190055 | 02777 | 2000 | Solar | 05_01_612W1 | 07/18/2018 | 09/17/2018 | 160 | 0 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2018 | 01/03/2019 | 144 | 72 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 174708 | 01970 | 500 | Solar | 05_05_11W85 | 06/17/2013 | 06/17/2013 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 724976 | 01851 | 6.72 | Solar | 05_12_2W1 | 10/08/2025 | 10/31/2025 | 15 | 13 | 2 | 11/03/2025 | 11/03/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NEWBURY | 598212 | 01985 | 3.8 | Solar | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 566203 | 01843 | 86.4 | Solar | 05_14_47L2 | 12/05/2023 | 02/20/2024 | 51 | 41 | 10 | 02/21/2024 | 02/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/05/2023 | 2/8/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | Y
National Grid | METHUEN | 581506 | 01844 | 7.6 | Solar | 05_14_61L3 | 01/04/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 538861 | 01523 | 15 | Solar | 05_14_75L3 | 07/12/2023 | 07/17/2023 | 3 | 0 | 3 | 07/18/2023 | 07/18/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2023 | Connected |  | Y
National Grid | MILLBURY | 684346 | 01527 | 7.6 | Solar | 05_01_225W1 | 04/10/2025 | 04/29/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 42 | 29 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | CHARLTON | 331259 | 01507 | 7.6 | Solar | 05_01_304W3 | 01/04/2021 | 01/21/2021 | 12 | 11 | 1 | 01/22/2021 | 01/22/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/04/2021 | 6/24/2023 | Y | EXP | 365 | 03/25/2022 | 06/17/2022 | 85 | 0 | 85 |  |  | 8/30/2022 | Connected |  | N
National Grid | WINCHENDON | 175651 | 01475 | 1000 | Solar | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/29/2018 | Y | STD | 851 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | SWANSEA | 192564 | 02777 | 4950 | Solar | 05_01_612W1 | 08/21/2018 | 08/27/2018 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2018 | 09/28/2018 | 69 | 3 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 175268 | 01970 | 130 | Solar | 05_05_11W85 | 06/20/2014 | 06/20/2014 | 9 | 7 | 2 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 |  | 10/31/2014 | N | EXP | 88 |  |  | 0 | 0 | 0 | 12/8/2014 | 12/8/2014 | 12/22/2014 | Connected |  | N
National Grid | LOWELL | 176002 | 01851 | 8.17 | Solar | 05_12_2W1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 8/19/2016 | Y | EXP | 346 | 08/19/2016 | 09/21/2016 | 22 | 0 | 22 | 5/10/2016 | 5/10/2016 | 10/28/2016 | Connected |  | N
National Grid | NEWBURY | 598082 | 01950 | 3.8 | Solar | 05_14_16L3 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 03/27/2024 | 03/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 600694 | 01843 | 15.2 | Solar | 05_14_47L2 | 04/05/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 582729 | 01826 | 9.86 | Solar | 05_14_61L3 | 02/21/2024 | 04/09/2024 | 34 | 25 | 9 | 04/10/2024 | 04/10/2024 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 542582 | 01740 | 6.67 | Solar | 05_14_75L3 | 08/21/2023 | 09/19/2023 | 21 | 19 | 2 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 692829 | 01527 | 999 | Solar | 05_01_225W1 | 11/18/2025 | 12/09/2025 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 01/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CHARLTON | 449447 | 01507 | 16.896 | Solar | 05_01_304W3 | 08/04/2022 | 08/31/2022 | 19 | 18 | 1 | 09/01/2022 | 09/01/2022 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175652 | 01475 | 499 | Solar | 05_01_415L1 | 12/17/2014 | 12/17/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/17/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | SWANSEA | 205568 | 02777 | 984 | Solar | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 207776 | 01970 | 60 | Solar | 05_05_11W85 | 02/08/2019 | 02/22/2019 | 9 | 4 | 5 | 02/25/2019 | 02/25/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2019 | Connected |  | N
National Grid | LOWELL | 176624 | 01851 | 6 | Solar | 05_12_2W1 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 |  | 4/24/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 623126 | 01985 | 5.76 | Solar | 05_14_16L3 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 | 08/21/2024 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/23/2024 |  | 9/27/2025 | N | EXP | 365 | 09/28/2024 | 02/07/2025 | 133 | 0 | 133 |  |  | 3/12/2025 | Connected |  | N
National Grid | LAWRENCE | 602560 | 01843 | 15.2 | Solar | 05_14_47L2 | 04/08/2024 | 05/07/2024 | 21 | 19 | 2 | 05/08/2024 | 05/08/2024 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2024 |  | 5/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2024 | Connected |  | N
National Grid | DRACUT | 590957 | 01826 | 3.8 | Solar | 05_14_61L3 | 02/29/2024 | 03/06/2024 | 5 | 2 | 3 | 03/07/2024 | 03/07/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 02/29/2024 | 3/21/2025 | Y | EXP | 365 | 05/16/2024 | 05/21/2024 | 6 | 0 | 6 |  |  | 5/23/2024 | Connected |  | N
National Grid | LANCASTER | 574265 | 01523 | 6 | Solar | 05_14_75L3 | 12/04/2023 | 12/06/2023 | 2 | 0 | 2 | 12/07/2023 | 12/07/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 | 12/04/2023 | 3/5/2025 | Y | EXP | 365 | 09/05/2024 | 10/17/2024 | 43 | 0 | 43 |  |  | 10/24/2024 | Connected |  | N
National Grid | MILLBURY | 715560 | 01527 | 13.36 | Solar | 05_01_225W1 | 09/03/2025 | 09/10/2025 | 5 | 1 | 4 | 09/11/2025 | 09/11/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 427594 | 01507 | 15.66 | Solar | 05_01_304W3 | 06/26/2022 | 08/30/2022 | 47 | 44 | 3 | 08/31/2022 | 08/31/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 |  | 10/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175678 | 01475 | 1000 | Solar | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 206008 | 02777 | 500 | Solar | 05_01_612W1 | 02/22/2019 | 03/25/2019 | 21 | 14 | 7 |  |  | 140 | 75 | 65 |  |  | 0 | 0 | 0 | 08/05/2019 | 08/02/2019 | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 291768 | 01970 | 0 | Other | 05_05_11W85 | 10/28/2020 | 12/21/2020 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 01/19/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177088 | 01851 | 432.6 | Solar | 05_12_2W1 | 01/18/2017 | 01/18/2017 | 2 | 0 | 2 | 01/23/2017 | 01/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2017 |  | 1/24/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 8/8/2017 | 8/8/2017 | 8/8/2017 | Connected |  | N
National Grid | NEWBURY | 644209 | 01950 | 5.76 | Solar | 05_14_16L3 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 10/01/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | LAWRENCE | 613760 | 01843 | 5.76 | Solar | 05_14_47L2 | 05/28/2024 | 06/05/2024 | 1 | 0 | 1 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/28/2024 | 11/30/2025 | Y | EXP | 365 | 09/28/2024 | 09/27/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 595150 | 01826 | 7.6 | Solar | 05_14_61L3 | 03/29/2024 | 04/16/2024 | 11 | 7 | 4 | 04/17/2024 | 04/17/2024 | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 592634 | 01451 | 50 | Solar | 05_14_75L3 | 02/26/2024 | 04/03/2024 | 27 | 18 | 9 | 04/04/2024 | 04/04/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 5/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | MILLBURY | 720104 | 01527 | 11.5 | Solar | 05_01_225W1 | 09/18/2025 | 10/16/2025 | 2 | 0 | 2 | 10/23/2025 | 10/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 460302 | 01507 | 13.92 | Solar | 05_01_304W3 | 10/19/2022 | 10/24/2022 | 3 | 0 | 3 | 10/25/2022 | 10/25/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175687 | 01475 | 1000 | Solar | 05_01_415L1 | 12/23/2014 | 12/23/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 | 12/23/2014 | 5/25/2018 | Y | STD | 847 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | Connected |  | N
National Grid | SWANSEA | 318681 | 02777 | 0 | Other | 05_01_612W1 | 11/05/2020 | 12/10/2020 | 23 | 16 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2020 | 12/10/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 398023 | 01970 | 0 | Other | 05_05_11W85 | 12/06/2021 | 02/04/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2022 | 02/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177135 | 01851 | 3.8 | Solar | 05_12_2W1 | 01/24/2017 | 01/24/2017 | 3 | 2 | 1 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2017 |  | 1/29/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/11/2018 | 1/11/2018 | 1/11/2018 | Connected |  | N
National Grid | NEWBURY | 644966 | 01950 | 7.6 | Solar | 05_14_16L3 | 10/04/2024 | 11/11/2024 | 12 | 7 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/04/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LAWRENCE | 634503 | 01843 | 0 | Battery Add-On | 05_14_47L2 | 09/06/2024 | 01/16/2025 | 18 | 13 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 09/06/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | DRACUT | 600825 | 01826 | 7.6 | Solar | 05_14_61L3 | 04/04/2024 | 05/23/2024 | 6 | 6 | 0 | 05/24/2024 | 05/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 04/04/2024 | 6/20/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/18/2025 | Connected |  | N
National Grid | HARVARD | 631905 | 01451 | 14.5 | Solar | 05_14_75L3 | 08/14/2024 | 08/23/2024 | 7 | 4 | 3 | 08/26/2024 | 08/26/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | MILLBURY | 726260 | 01527 | 0 | Battery Add-On | 05_01_225W1 | 10/14/2025 | 10/16/2025 | 2 | 0 | 2 | 10/17/2025 | 10/17/2025 | 76 | 66 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 471063 | 01507 | 6 | Solar | 05_01_304W3 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175706 | 01475 | 1000 | Solar | 05_01_415L1 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/01/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 325150 | 02777 | 0 | Other | 05_01_612W1 | 12/31/2020 | 01/06/2021 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/07/2021 | 01/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 443980 | 01970 | 0 | Other | 05_05_11W85 | 01/30/2023 | 02/14/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2023 | 03/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 177151 | 01851 | 5.2 | Solar | 05_12_2W1 | 08/11/2016 | 08/11/2016 | 3 | 3 | 0 | 08/16/2016 | 08/16/2016 | 203 | 0 | 203 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2016 |  | 8/16/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 649171 | 01950 | 8.7 | Solar | 05_14_16L3 | 10/25/2024 | 11/04/2024 | 3 | 0 | 3 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 10/25/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | LAWRENCE | 638266 | 01843 | 0 | Battery Add-On | 05_14_47L2 | 09/06/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | DRACUT | 611921 | 01826 | 10 | Solar | 05_14_61L3 | 05/22/2024 | 06/21/2024 | 7 | 4 | 3 | 06/24/2024 | 06/24/2024 | 56 | 39 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 644476 | 01740 | 7.6 | Solar | 05_14_75L3 | 10/16/2024 | 11/01/2024 | 3 | 0 | 3 | 11/04/2024 | 11/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | MILLBURY | 739094 | 01527 | 0 | Battery Add-On | 05_01_225W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 526963 | 01507 | 7.6 | Solar | 05_01_304W3 | 05/24/2023 | 06/12/2023 | 13 | 12 | 1 | 06/13/2023 | 06/13/2023 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 176018 | 01475 | 7.6 | Solar | 05_01_415L1 | 03/20/2015 | 03/20/2015 | 2 | 1 | 1 | 03/25/2015 | 03/25/2015 | 343 | 0 | 343 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/20/2015 | N | EXP | 115 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWANSEA | 330507 | 02777 | 15.2 | Solar | 05_01_612W1 | 12/08/2020 | 12/13/2020 | 3 | 0 | 3 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/08/2020 | 2/8/2023 | Y | EXP | 365 | 09/04/2021 | 10/21/2021 | 48 | 0 | 48 |  |  | 3/28/2022 | Connected |  | N
National Grid | SALEM | 668365 | 01970 | 60 | Solar | 05_05_11W85 | 03/05/2025 | 04/11/2025 | 28 | 18 | 10 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | LOWELL | 186237 | 01851 | 3.8 | Solar | 05_12_2W1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEWBURY | 649125 | 01950 | 10 | Solar | 05_14_16L3 | 10/23/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | LAWRENCE | 651318 | 01843 | 10 | Solar | 05_14_47L2 | 11/12/2024 | 01/03/2025 | 3 | 0 | 3 | 01/06/2025 | 01/06/2025 | 25 | 0 | 25 | 02/25/2025 | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 03/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 3/31/2025 | 11/12/2024 | 4/7/2026 | Y | EXP | 365 | 09/10/2025 | 09/16/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | DRACUT | 612901 | 01826 | 7.6 | Solar | 05_14_61L3 | 05/29/2024 | 06/07/2024 | 1 | 0 | 1 | 06/10/2024 | 06/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2024 | 05/29/2024 | 8/5/2025 | Y | EXP | 365 | 01/29/2025 | 01/28/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | LANCASTER | 651164 | 01523 | 9.28 | Solar | 05_14_75L3 | 10/31/2024 | 11/21/2024 | 3 | 1 | 2 | 11/22/2024 | 11/22/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | MILLBURY | 750984 | 01527 | 10 | Solar | 05_01_225W1 | 02/12/2026 | 02/13/2026 | 1 | 0 | 1 | 02/17/2026 | 02/17/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 536757 | 01507 | 10 | Solar | 05_01_304W3 | 06/27/2023 |  | 71 | 25 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 176323 | 01475 | 30 | Solar | 05_01_415L1 | 07/15/2015 | 07/15/2015 | 3 | 3 | 0 | 07/20/2015 | 07/20/2015 | 390 | 0 | 390 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 | 07/15/2015 | 7/20/2017 | Y | EXP | 713 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 7/31/2015 | 7/31/2015 |  | Withdrawn |  | N
National Grid | SWANSEA | 361142 | 02777 | 17.6 | Solar | 05_01_612W1 | 06/07/2021 | 01/07/2022 | 51 | 50 | 1 | 08/18/2021 | 08/18/2021 | 155 | 127 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 703902 | 01970 | 11.52 | Solar | 05_05_17J1 | 07/10/2025 | 08/13/2025 | 10 | 6 | 4 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | LOWELL | 186574 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 2 | 1 | 1 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 652993 | 01950 | 3.84 | Solar | 05_14_16L3 | 11/08/2024 | 11/13/2024 | 2 | 0 | 2 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 662520 | 01843 | 5.76 | Solar | 05_14_47L2 | 12/26/2024 | 02/03/2025 | 7 | 1 | 6 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | METHUEN | 614068 | 01844 | 5.76 | Solar | 05_14_61L3 | 05/29/2024 | 06/18/2024 | 12 | 11 | 1 | 06/20/2024 | 06/20/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/29/2024 | 7/23/2025 | Y | EXP | 365 | 08/29/2024 | 12/03/2024 | 97 | 0 | 97 |  |  | 3/18/2025 | Connected |  | N
National Grid | BOLTON | 671868 | 01740 | 7.6 | Solar | 05_14_75L3 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | N
National Grid | MILLBURY | 174116 | 01527 | 2000 | Solar | 05_01_225W1 | 03/30/2012 | 03/30/2012 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 593460 | 01507 | 7.6 | Solar | 05_01_304W3 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 03/05/2024 | 3/22/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | WINCHENDON | 177175 | 01475 | 22.8 | Solar | 05_01_415L1 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2016 | 06/01/2016 | 6/6/2017 | Y | EXP | 37 | 04/05/2017 | 04/21/2017 | 11 | 0 | 11 | 6/1/2016 | 6/1/2016 | 5/15/2017 | Connected |  | N
National Grid | SOMERSET | 427507 | 02726 | 13 | Solar | 05_01_612W1 | 05/13/2022 | 05/13/2022 | 0 | 0 | 0 | 05/16/2022 | 05/16/2022 | 74 | 55 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 671086 | 01970 | 5.76 | Solar | 05_05_17J1 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | LOWELL | 187385 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/22/2018 | 06/22/2018 | 7 | 4 | 3 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 661655 | 01985 | 5.76 | Solar | 05_14_16L3 | 12/19/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | LAWRENCE | 713199 | 01843 | 20 | Solar | 05_14_47L2 | 08/19/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 70 | 56 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 634009 | 01844 | 10 | Solar | 05_14_61L3 | 09/10/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | LANCASTER | 674866 | 01523 | 3.8 | Solar | 05_14_75L3 | 03/06/2025 | 03/26/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 82 | 70 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174208 | 01527 | 450 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 626487 | 01507 | 7.6 | Solar | 05_01_304W3 | 07/22/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/22/2024 | 12/31/2025 | Y | EXP | 365 | 02/25/2025 | 10/23/2025 | 241 | 0 | 241 |  |  | 11/17/2025 | Connected |  | N
National Grid | WINCHENDON | 177536 | 01475 | 19 | Solar | 05_01_415L1 | 09/14/2017 | 09/14/2017 | 13 | 13 | 0 | 09/28/2017 | 09/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2017 |  | 9/19/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/2/2018 | Connected |  | N
National Grid | SOMERSET | 441942 | 02726 | 7.54 | Solar | 05_01_612W1 | 07/22/2022 | 07/26/2022 | 2 | 1 | 1 | 07/27/2022 | 07/27/2022 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2022 | 07/22/2022 | 9/2/2023 | Y | EXP | 365 | 09/21/2022 | 11/01/2022 | 41 | 0 | 41 |  |  | 1/20/2023 | Connected |  | N
National Grid | SALEM | 691231 | 01970 | 20 | Solar | 05_05_17J1 | 05/13/2025 | 05/20/2025 | 5 | 0 | 5 | 05/21/2025 | 05/21/2025 | 23 | 0 | 23 | 07/29/2025 | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  | 08/20/2025 | 17 | 16 | 1 |  |  | 0 | 0 | 0 | 8/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 188870 | 01851 | 3.8 | Solar | 05_12_2W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/27/2018 | 07/27/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEWBURY | 666095 | 01985 | 5.76 | Solar | 05_14_16L3 | 01/16/2025 | 03/05/2025 | 17 | 12 | 5 | 03/06/2025 | 03/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | LAWRENCE | 714914 | 01843 | 15.2 | Solar | 05_14_47L2 | 09/02/2025 | 09/19/2025 | 11 | 6 | 5 | 09/22/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2026 | Connected |  | N
National Grid | DRACUT | 635906 | 01826 | 5.76 | Solar | 05_14_61L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | BOLTON | 681276 | 01740 | 0 | Solar | 05_14_75L3 | 03/31/2025 | 05/06/2025 | 26 | 23 | 3 | 05/07/2025 | 05/07/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174207 | 01527 | 500 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 628108 | 01566 | 3.8 | Solar | 05_01_304W3 | 07/26/2024 | 08/15/2024 | 1 | 0 | 1 | 08/16/2024 | 08/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | WINCHENDON | 178004 | 01475 | 3500 | Solar | 05_01_415L1 | 04/26/2017 | 04/26/2017 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 474354 | 02726 | 3.8 | Solar | 05_01_612W1 | 11/16/2022 | 12/20/2022 | 23 | 21 | 2 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 11/16/2022 | 3/8/2024 | Y | EXP | 365 | 03/02/2023 | 03/09/2023 | 8 | 0 | 8 |  |  | 4/4/2023 | Connected |  | N
National Grid | SALEM | 702804 | 01970 | 22.04 | Solar | 05_05_17J1 | 07/03/2025 | 07/10/2025 | 4 | 0 | 4 | 07/11/2025 | 07/11/2025 | 71 | 58 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 192482 | 01851 | 7.6 | Solar | 05_12_2W1 | 08/01/2018 | 10/01/2018 | 22 | 22 | 0 | 10/02/2018 | 10/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 08/01/2018 | 4/22/2020 | Y | EXP | 568 | 11/15/2019 | 12/23/2019 | 38 | 0 | 38 |  |  | 1/6/2020 | Connected |  | N
National Grid | NEWBURY | 671508 | 01985 | 10 | Solar | 05_14_16L3 | 02/13/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | LAWRENCE | 733818 | 01843 | 3.8 | Solar | 05_14_48L1 | 11/14/2025 | 12/02/2025 | 1 | 0 | 1 | 01/02/2026 | 01/02/2026 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 637769 | 01826 | 7.6 | Solar | 05_14_61L3 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 682755 | 01740 | 5.76 | Solar | 05_14_75L3 | 04/03/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 174205 | 01527 | 4950 | Solar | 05_01_225W1 | 02/29/2012 | 02/29/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/22/2012 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2012 | 02/29/2012 | 1/1/2013 | Y | STD | 33 | 10/11/2013 | 12/03/2013 | 34 | 0 | 34 | 12/12/2013 | 12/12/2013 | 12/12/2013 | Connected |  | N
National Grid | CHARLTON | 643329 | 01507 | 7.6 | Solar | 05_01_304W3 | 09/27/2024 | 10/23/2024 | 2 | 0 | 2 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | WINCHENDON | 178003 | 01475 | 4500 | Solar | 05_01_415L1 | 04/26/2017 | 05/22/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/13/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2018 | 04/26/2017 | 8/24/2020 | Y | STD | 617 | 02/26/2020 | 08/24/2020 | 180 | 0 | 180 |  |  | 8/24/2020 | Connected |  | N
National Grid | SOMERSET | 497546 | 02726 | 6.528 | Solar | 05_01_612W1 | 03/10/2023 | 03/14/2023 | 2 | 0 | 2 | 03/15/2023 | 03/15/2023 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 |  | 5/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2023 | Connected |  | N
National Grid | SALEM | 640868 | 01970 | 15.2 | Solar | 05_05_17J3 | 11/13/2024 | 11/19/2024 | 5 | 3 | 2 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2025 | Connected |  | N
National Grid | LOWELL | 203384 | 01851 | 10 | Solar | 05_12_2W1 | 02/21/2019 | 02/22/2019 | 0 | 0 | 0 | 02/25/2019 | 02/25/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 682707 | 01830 | 15.2 | Solar | 05_14_16L3 | 04/03/2025 | 04/07/2025 | 2 | 0 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | LAWRENCE | 735545 | 01843 | 200 | Solar | 05_14_48L1 | 11/25/2025 | 01/06/2026 | 27 | 21 | 6 | 01/07/2026 | 01/07/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 641933 | 01826 | 6 | Solar | 05_14_61L3 | 09/20/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/20/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | BOLTON | 691425 | 01740 | 19.195 | Solar | 05_14_75L3 | 05/19/2025 | 06/04/2025 | 10 | 6 | 4 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | MILLBURY | 174229 | 01527 | 26 | Solar | 05_01_225W1 | 12/08/2011 | 12/08/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2012 |  | 12/30/2011 | N | EXP | 76 |  |  | 0 | 0 | 0 | 4/24/2012 | 4/24/2012 | 4/24/2012 | Connected |  | N
National Grid | CHARLTON | 645157 | 01507 | 7.6 | Solar | 05_01_304W3 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WINCHENDON | 178154 | 01475 | 5000 | Solar | 05_01_415L1 | 12/21/2017 | 12/21/2017 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2018 | 02/21/2018 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 522629 | 02726 | 10 | Solar | 05_01_612W1 | 05/10/2023 | 05/15/2023 | 3 | 2 | 1 | 05/16/2023 | 05/16/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2023 | 05/10/2023 | 6/20/2024 | Y | EXP | 365 | 07/07/2023 | 08/08/2023 | 33 | 0 | 33 |  |  | 8/25/2023 | Connected |  | N
National Grid | SALEM | 741251 | 01970 | 7.6 | Solar | 05_05_17J3 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 223128 | 01851 | 120 | Solar | 05_12_2W1 | 04/27/2019 | 05/21/2019 | 17 | 17 | 0 | 05/22/2019 | 05/22/2019 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 8/13/2021 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | HAVERHILL | 682361 | 01832 | 15.2 | Solar | 05_14_16L3 | 04/02/2025 | 04/25/2025 | 16 | 12 | 4 | 04/28/2025 | 04/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | LAWRENCE | 174294 | 01843 | 300 | Solar | 05_14_48L1 | 12/15/2011 | 12/15/2011 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2012 |  | 1/28/2012 | N | EXP | 3 |  |  | 0 | 0 | 0 | 6/1/2012 | 6/1/2012 | 6/4/2012 | Connected |  | N
National Grid | METHUEN | 643919 | 01844 | 7.6 | Solar | 05_14_61L3 | 09/30/2024 | 11/04/2024 | 13 | 11 | 2 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 09/30/2024 | 1/8/2026 | Y | EXP | 365 | 08/07/2025 | 09/06/2025 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 727475 | 01523 | 11.5 | Solar | 05_14_75L3 | 10/17/2025 | 10/24/2025 | 4 | 3 | 1 | 10/27/2025 | 10/27/2025 | 71 | 60 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174878 | 01527 | 1800 | Solar | 05_01_225W1 | 02/06/2013 | 02/06/2013 | 210 | 207 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 655225 | 01507 | 3.8 | Solar | 05_01_304W3 | 11/19/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | WINCHENDON | 178297 | 01475 | 2640 | Solar | 05_01_415L1 | 11/15/2017 | 01/18/2018 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/13/2018 | 25 | 14 | 11 |  |  | 0 | 0 | 0 | 08/14/2018 | 11/06/2018 | 60 | 0 | 60 | 7/6/2018 | 11/15/2017 |  | Y | STD | 966 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 529144 | 02726 | 5.76 | Solar | 05_01_612W1 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 | 06/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | SALEM | 743962 | 01970 | 7.6 | Solar | 05_05_18J5 | 01/07/2026 | 01/09/2026 | 2 | 1 | 1 | 01/12/2026 | 01/12/2026 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 235959 | 01851 | 3.8 | Solar | 05_12_2W1 | 07/22/2019 | 07/25/2019 | 3 | 3 | 0 | 07/26/2019 | 07/26/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2019 |  | 8/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | HAVERHILL | 688012 | 01832 | 7.6 | Solar | 05_14_16L3 | 04/29/2025 | 06/13/2025 | 3 | 0 | 3 | 06/16/2025 | 06/16/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | LAWRENCE | 174816 | 01843 | 3000 | Solar | 05_14_48L1 | 07/31/2013 | 07/31/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2013 | 09/24/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2014 | 07/31/2013 | 9/15/2017 | Y | STD | 1187 |  |  | 0 | 0 | 0 | 9/15/2017 | 9/15/2017 | 9/27/2017 | Connected |  | N
National Grid | DRACUT | 645579 | 01826 | 3.9 | Solar | 05_14_61L3 | 10/08/2024 | 10/17/2024 | 1 | 0 | 1 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/08/2024 | 12/1/2025 | Y | EXP | 365 | 02/13/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/21/2025 | Connected |  | N
National Grid | LANCASTER | 744262 | 01523 | 5.76 | Solar | 05_14_75L3 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 175575 | 01527 | 22.8 | Solar | 05_01_225W1 | 12/09/2014 | 12/09/2014 | 4 | 3 | 1 | 12/16/2014 | 12/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2014 |  | 2/28/2015 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/9/2015 | 4/9/2015 | 9/25/2015 | Connected |  | N
National Grid | CHARLTON | 659616 | 01507 | 6.825 | Solar | 05_01_304W3 | 12/16/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | WINCHENDON | 178454 | 01475 | 4430 | Solar | 05_01_415L1 | 12/01/2017 | 12/01/2017 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2017 | 01/03/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 637211 | 02726 | 3.8 | Solar | 05_01_612W1 | 09/03/2024 | 10/08/2024 | 3 | 2 | 1 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/03/2024 | 11/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 175863 | 01970 | 7.6 | Solar | 05_05_18J5 | 09/21/2015 | 09/21/2015 | 2 | 2 | 0 | 09/25/2015 | 09/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 9/28/2016 | N | EXP | 341 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/23/2015 | 4/29/2016 | Connected |  | N
National Grid | LOWELL | 256763 | 01851 | 5 | Solar | 05_12_2W1 | 10/14/2019 | 10/21/2019 | 4 | 0 | 4 | 10/22/2019 | 10/22/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 | 06/10/2020 | 06/22/2020 | 12 | 0 | 12 |  |  | 7/6/2020 | Connected |  | N
National Grid | HAVERHILL | 708313 | 01832 | 12.54 | Solar | 05_14_16L3 | 07/30/2025 | 09/15/2025 | 26 | 24 | 2 | 09/16/2025 | 09/16/2025 | 53 | 50 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175551 | 01843 | 196 | Solar | 05_14_48L1 | 04/07/2014 | 04/07/2014 | 8 | 0 | 8 | 04/18/2014 | 04/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 |  | 10/1/2014 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/18/2014 | 6/18/2014 | 5/27/2015 | Connected |  | N
National Grid | DRACUT | 647544 | 01826 | 5.76 | Solar | 05_14_61L3 | 10/22/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 10/22/2024 | 2/25/2026 | Y | EXP | 365 | 12/20/2025 | 02/02/2026 | 45 | 0 | 45 |  |  | 2/19/2026 | Connected |  | Y
National Grid | LANCASTER | 194135 | 01523 | 130 | Solar | 05_14_75L4 | 08/23/2018 | 08/24/2018 | 0 | 0 | 0 | 08/27/2018 | 08/27/2018 | 103 | 26 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 175801 | 01527 | 1980 | Solar | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 12/31/2016 | Y | STD | 494 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/22/2016 | 12/22/2016 | 12/27/2016 | Connected |  | N
National Grid | CHARLTON | 667220 | 01507 | 0 | Battery Add-On | 05_01_304W3 | 01/22/2025 | 01/28/2025 | 4 | 0 | 4 | 01/29/2025 | 01/29/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | WINCHENDON | 178578 | 01475 | 4950 | Solar | 05_01_415L1 | 01/30/2018 | 03/14/2018 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/14/2018 | 05/18/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 | 01/30/2018 | 4/22/2022 | Y | STD | 1197 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 640886 | 02726 | 34.6 | Solar | 05_01_612W1 | 09/18/2024 | 10/22/2024 | 23 | 17 | 6 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 176359 | 01970 | 5 | Solar | 05_05_18J5 | 03/07/2016 | 03/07/2016 | 2 | 2 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/07/2016 | 3/13/2017 | Y | EXP | 325 | 07/27/2016 | 08/15/2016 | 13 | 0 | 13 | 4/22/2016 | 4/22/2016 | 10/19/2016 | Connected |  | N
National Grid | LOWELL | 263264 | 01851 | 6 | Solar | 05_12_2W1 | 12/05/2019 | 12/15/2019 | 6 | 0 | 6 | 12/16/2019 | 12/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/05/2019 | 12/5/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2020 | Connected |  | N
National Grid | HAVERHILL | 185025 | 01832 | 14.72 | Solar | 05_14_48L1 | 05/23/2018 | 05/23/2018 | 3 | 0 | 3 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 6/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2018 | Connected |  | N
National Grid | LAWRENCE | 647901 | 01843 | 10 | Solar | 05_14_61L3 | 10/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 311773 | 01844 | 150 | Solar | 05_14_75L4 | 09/10/2020 | 09/16/2020 | 3 | 0 | 3 | 09/17/2020 | 09/17/2020 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 176132 | 01740 | 495 | Solar | 05_01_225W1 | 04/14/2015 | 04/14/2015 | 4 | 4 | 0 | 04/22/2015 | 04/22/2015 | 166 | 0 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 673393 | 01527 | 5.76 | Solar | 05_01_304W3 | 02/25/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 62 | 43 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 178771 | 01507 | 1980 | Solar | 05_01_415L1 | 01/03/2012 | 01/03/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2012 | 09/25/2013 | 402 | 0 | 402 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2014 | 01/03/2012 | 12/31/2016 | Y | STD | 955 | 03/08/2016 | 09/02/2016 | 123 | 0 | 123 | 9/1/2016 | 9/1/2016 | 10/7/2016 | Connected |  | N
National Grid | WINCHENDON | 645430 | 01475 | 10 | Solar | 05_01_612W1 | 10/08/2024 | 10/10/2024 | 2 | 0 | 2 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | SOMERSET | 176564 | 02726 | 42 | Solar | 05_05_18J5 | 12/22/2015 | 12/22/2015 | 22 | 22 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 |  | 12/27/2016 | N | EXP | 335 |  |  | 0 | 0 | 0 | 2/4/2016 | 2/4/2016 | 6/16/2016 | Connected |  | N
National Grid | SALEM | 266036 | 01970 | 7.6 | Solar | 05_12_2W1 | 09/24/2020 | 09/25/2020 | 0 | 0 | 0 | 09/28/2020 | 09/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 | 09/24/2020 | 10/15/2021 | Y | EXP |  | 02/05/2021 | 03/17/2021 | 40 | 0 | 40 |  |  | 3/20/2021 | Connected |  | N
National Grid | LOWELL | 517634 | 01851 | 100 | Solar | 05_14_16L4 | 04/29/2023 | 07/20/2023 | 56 | 46 | 10 |  |  | 118 | 97 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | HAVERHILL | 187781 | 01832 | 179.9 | Solar | 05_14_48L1 | 06/12/2018 | 06/12/2018 | 1 | 0 | 1 | 06/14/2018 | 06/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 11/28/2019 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  | 12/20/2019 | Connected |  | N
National Grid | LAWRENCE | 651538 | 01843 | 7.6 | Solar | 05_14_61L3 | 11/12/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/12/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | METHUEN | 318966 | 01844 | 249 | Solar | 05_14_75L4 | 10/13/2020 | 01/04/2022 | 19 | 12 | 7 | 11/10/2020 | 11/10/2020 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 1/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 176465 | 01523 | 99.9 | Solar | 05_01_225W1 | 02/05/2016 | 02/05/2016 | 0 | 0 | 0 | 02/08/2016 | 02/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 2/13/2017 | N | EXP | 37 |  |  | 0 | 0 | 0 | 11/18/2016 | 11/18/2016 | 11/18/2016 | Connected |  | N
National Grid | MILLBURY | 697399 | 01527 | 8.7 | Solar | 05_01_304W3 | 06/10/2025 | 07/02/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 213693 | 01507 | 30 | Solar | 05_01_415L1 | 03/21/2019 | 05/21/2019 | 43 | 40 | 3 | 05/22/2019 | 05/22/2019 | 267 | 73 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 650021 | 01475 | 4.06 | Solar | 05_01_612W1 | 10/28/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/28/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | SOMERSET | 176988 | 02726 | 3.8 | Solar | 05_05_18J5 | 03/10/2017 | 03/10/2017 | 4 | 2 | 2 | 03/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/15/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 6/5/2017 | 6/5/2017 | 6/7/2017 | Connected |  | N
National Grid | SALEM | 270246 | 01970 | 6.3 | Solar | 05_12_2W1 | 06/02/2020 | 06/04/2020 | 1 | 0 | 1 | 06/05/2020 | 06/05/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/02/2020 | 5/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2021 | Connected |  | N
National Grid | CHELMSFORD | 669042 | 01824 | 0 | Battery Add-On | 05_14_16L4 | 02/03/2025 | 02/05/2025 | 2 | 0 | 2 | 02/06/2025 | 02/06/2025 | 84 | 60 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 191116 | 01832 | 1594 | Solar | 05_14_48L1 | 07/20/2018 | 08/24/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2018 | 10/15/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 07/20/2018 | 3/22/2024 | Y | STD | 275 | 08/29/2023 | 01/05/2024 | 130 | 3 | 127 |  |  | 2/28/2024 | Connected |  | N
National Grid | LAWRENCE | 651823 | 01843 | 5.76 | Solar | 05_14_61L3 | 11/13/2024 | 03/13/2025 | 68 | 63 | 5 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | METHUEN | 379113 | 01844 | 7.6 | Solar | 05_14_75L4 | 11/01/2021 | 01/14/2022 | 52 | 50 | 2 | 01/18/2022 | 01/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 177345 | 01523 | 15.2 | Solar | 05_01_225W1 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/2/2017 | 8/2/2017 | 8/2/2017 | Connected |  | N
National Grid | MILLBURY | 735413 | 01527 | 5.76 | Solar | 05_01_304W3 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | CHARLTON | 214422 | 01507 | 3.655 | Solar | 05_01_415L1 | 03/20/2019 | 06/05/2019 | 23 | 19 | 4 | 06/06/2019 | 06/06/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2019 |  | 9/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 652565 | 01475 | 15.2 | Solar | 05_01_612W1 | 11/13/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 11/13/2024 | 1/8/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/21/2025 | Connected |  | N
National Grid | SOMERSET | 188458 | 02726 | 8.36 | Solar | 05_05_18J5 | 07/05/2018 | 08/03/2018 | 21 | 0 | 21 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 279630 | 01970 | 10 | Solar | 05_12_2W1 | 02/25/2020 | 02/26/2020 | 0 | 0 | 0 | 02/27/2020 | 02/27/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2020 | 02/25/2020 | 2/25/2021 | Y | EXP | 365 | 05/15/2020 | 06/03/2020 | 19 | 0 | 19 |  |  | 6/4/2020 | Connected |  | N
National Grid | CHELMSFORD | 679246 | 01824 | 15.2 | Solar | 05_14_16L4 | 04/02/2025 | 04/14/2025 | 9 | 6 | 3 | 04/15/2025 | 04/15/2025 | 33 | 22 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 357413 | 01832 | 290 | Solar | 05_14_48L1 | 06/24/2021 | 12/01/2021 | 109 | 99 | 10 |  |  | 121 | 96 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2022 | 06/24/2021 | 10/10/2024 | Y | STD | 48 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | LAWRENCE | 651661 | 01843 | 5.76 | Solar | 05_14_61L3 | 11/12/2024 | 02/18/2025 | 58 | 56 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2025 | Connected |  | N
National Grid | METHUEN | 668677 | 01844 | 20 | Solar | 05_14_75L4 | 01/29/2025 | 02/04/2025 | 5 | 2 | 3 | 02/05/2025 | 02/05/2025 | 67 | 25 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 177807 | 01740 | 20 | Solar | 05_01_225W1 | 10/12/2017 | 10/12/2017 | 10 | 0 | 10 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | MILLBURY | 299022 | 01527 | 996 | Solar | 05_01_304W4 | 09/08/2020 | 10/05/2020 | 19 | 14 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/08/2020 | 2/11/2026 | Y | STD | 371 | 05/09/2025 | 11/24/2025 | 223 | 0 | 223 |  |  |  | Completion Documents |  | N
National Grid | STURBRIDGE | 265490 | 01566 | 4950 | Other | 05_01_415L1 | 03/17/2020 | 04/24/2020 | 27 | 24 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/27/2020 | 05/11/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 685264 | 01475 | 15.2 | Solar | 05_01_612W1 | 05/09/2025 | 05/16/2025 | 4 | 0 | 4 | 05/19/2025 | 05/19/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 200437 | 02726 | 10 | Solar | 05_05_18J5 | 11/06/2018 | 02/14/2019 | 58 | 57 | 1 | 02/15/2019 | 02/15/2019 | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 | 11/06/2018 | 12/6/2019 | Y | EXP | 275 | 06/06/2019 | 07/19/2019 | 43 | 0 | 43 |  |  | 8/6/2019 | Connected |  | N
National Grid | SALEM | 281332 | 01970 | 12 | Solar | 05_12_2W1 | 02/27/2020 | 03/04/2020 | 3 | 3 | 0 | 03/05/2020 | 03/05/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2020 |  | 3/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2020 | Connected |  | N
National Grid | CHELMSFORD | 727121 | 01824 | 19 | Solar | 05_14_16L4 | 10/28/2025 | 11/12/2025 | 5 | 0 | 5 | 11/13/2025 | 11/13/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 595357 | 01832 | 9.57 | Solar | 05_14_48L1 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/13/2024 | 4/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | LAWRENCE | 654440 | 01843 | 7.6 | Solar | 05_14_61L3 | 11/14/2024 | 01/29/2025 | 3 | 0 | 3 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | METHUEN | 682085 | 01844 | 15.2 | Solar | 05_14_75L4 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 35 | 17 | 18 | 06/17/2025 | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 28 | 0 | 28 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/03/2025 | 8/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | BOLTON | 178028 | 01740 | 69 | Solar | 05_01_225W1 | 08/31/2017 | 08/31/2017 | 1 | 0 | 1 | 09/05/2017 | 09/05/2017 | 103 | 0 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/6/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 683158 | 01527 | 6.46 | Solar | 05_01_304W4 | 04/06/2025 | 04/25/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 265320 | 01507 | 0 | Other | 05_01_415L1 | 02/14/2020 | 03/23/2020 | 25 | 22 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 | 03/24/2020 | 03/23/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 685677 | 01475 | 4980 | Solar | 05_01_612W1 | 05/06/2025 | 06/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 291755 | 02726 | 7.6 | Solar | 05_05_18J5 | 05/19/2020 | 05/20/2020 | 0 | 0 | 0 | 05/21/2020 | 05/21/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 314997 | 01970 | 3.8 | Solar | 05_12_2W1 | 10/07/2020 | 10/12/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 10/07/2020 | 7/7/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2021 | Connected |  | Y
National Grid | CHELMSFORD | 749081 | 01824 | 120 | Solar | 05_14_16L4 | 02/25/2026 |  | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HAVERHILL | 627023 | 01830 | 10 | Solar | 05_14_48L1 | 07/23/2024 | 08/02/2024 | 4 | 0 | 4 | 08/05/2024 | 08/05/2024 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 07/23/2024 | 9/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | LAWRENCE | 655150 | 01843 | 10 | Solar | 05_14_61L3 | 11/20/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 666789 | 01844 | 7.6 | Solar | 05_14_75L5 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 85 | 65 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 178357 | 01523 | 1980 | Solar | 05_01_225W1 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/07/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 02/27/2015 | 3/6/2019 | Y | STD | 1289 | 11/14/2016 | 01/06/2017 | 36 | 0 | 36 | 12/23/2016 | 12/23/2016 | 12/27/2016 | Connected |  | N
National Grid | MILLBURY | 748378 | 01527 | 5.76 | Solar | 05_01_304W4 | 01/30/2026 | 02/13/2026 | 10 | 8 | 2 | 02/17/2026 | 02/17/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 273360 | 01507 | 5000 | Other | 05_01_415L1 | 03/19/2020 | 03/25/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2020 | 04/07/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 696246 | 01475 | 17.92 | Solar | 05_01_612W1 | 06/19/2025 | 07/15/2025 | 16 | 13 | 3 | 07/16/2025 | 07/16/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 324590 | 02726 | 7.6 | Solar | 05_05_18J5 | 11/25/2020 | 11/30/2020 | 1 | 0 | 1 | 12/01/2020 | 12/01/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 318458 | 01970 | 9.36 | Solar | 05_12_2W1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/10/2020 | 7/8/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2022 | Connected |  | N
National Grid | CHELMSFORD | 748336 | 01824 | 7.6 | Solar | 05_14_16L4 | 01/30/2026 | 02/04/2026 | 3 | 0 | 3 | 02/05/2026 | 02/05/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 632030 | 01832 | 7.6 | Solar | 05_14_48L1 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 657463 | 01843 | 7.6 | Solar | 05_14_61L3 | 11/27/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | DRACUT | 731105 | 01826 | 3.8 | Solar | 05_14_75L5 | 11/03/2025 | 11/04/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 253910 | 01740 | 22.8 | Solar | 05_01_225W1 | 09/13/2019 | 09/19/2019 | 4 | 4 | 0 | 09/20/2019 | 09/20/2019 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2019 |  | 4/15/2021 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  | 1/5/2021 | Connected |  | N
National Grid | GRAFTON | 175804 | 01536 | 990 | Solar | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 308485 | 01507 | 0 | Other | 05_01_415L1 | 09/08/2020 | 09/21/2020 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/09/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 704688 | 01475 | 4980 | Solar | 05_01_612W1 | 08/13/2025 | 08/27/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 467759 | 02726 | 6 | Solar | 05_05_18J5 | 10/14/2022 | 10/21/2022 | 6 | 5 | 1 | 10/24/2022 | 10/24/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 326340 | 01970 | 8.7 | Solar | 05_12_2W1 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 | 02/03/2021 | 1/11/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | CHELMSFORD | 174780 | 01824 | 100 | Solar | 05_14_16L4 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 583 | 7 | 576 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 12/31/2016 | N | EXP | 1222 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 652477 | 01830 | 5.76 | Solar | 05_14_48L1 | 11/19/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 662558 | 01843 | 11.4 | Solar | 05_14_61L3 | 12/27/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/27/2024 | 4/28/2026 | Y | EXP | 365 | 08/19/2025 | 08/19/2025 | 1 | 0 | 1 |  |  | 8/22/2025 | Connected |  | N
National Grid | LOWELL | 732423 | 01850 | 5.76 | Solar | 05_14_75L5 | 11/12/2025 | 11/13/2025 | 4 | 0 | 4 | 11/28/2025 | 11/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HARVARD | 262760 | 01451 | 19.2 | Solar | 05_01_225W1 | 10/29/2019 | 11/04/2019 | 3 | 3 | 0 | 11/05/2019 | 11/05/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2020 | Connected |  | N
National Grid | MILLBURY | 176092 | 01527 | 980 | Solar | 05_01_304W4 | 04/06/2015 | 04/06/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2015 | 04/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 308478 | 01507 | 0 | Other | 05_01_415L1 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 11/17/2020 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 | 2/17/2025 | Y | STD | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 706143 | 01475 | 15.2 | Solar | 05_01_612W1 | 07/21/2025 | 07/22/2025 | 1 | 0 | 1 | 07/23/2025 | 07/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2025 | Connected |  | N
National Grid | SOMERSET | 522489 | 02726 | 6 | Solar | 05_05_18J5 | 07/18/2023 | 08/10/2023 | 18 | 15 | 3 | 08/11/2023 | 08/11/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 07/18/2023 | 10/5/2024 | Y | EXP | 365 | 12/07/2023 | 12/07/2023 | 1 | 0 | 1 |  |  | 12/28/2023 | Connected |  | N
National Grid | SALEM | 328907 | 01970 | 8.64 | Solar | 05_12_2W1 | 12/01/2020 | 12/08/2020 | 4 | 0 | 4 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 12/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2021 | Connected |  | N
National Grid | CHELMSFORD | 174786 | 01824 | 300 | Solar | 05_14_16L4 | 08/06/2013 | 08/06/2013 | 1 | 0 | 1 | 08/07/2013 | 08/07/2013 | 566 | 5 | 561 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2013 |  | 9/14/2014 | N | EXP | 383 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 683789 | 01832 | 5.76 | Solar | 05_14_48L1 | 04/08/2025 | 04/28/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/08/2025 | 7/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | LAWRENCE | 670838 | 01843 | 3.8 | Solar | 05_14_61L3 | 02/07/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 743594 | 01826 | 9 | Solar | 05_14_75L5 | 01/07/2026 | 01/09/2026 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HARVARD | 277546 | 01451 | 9.6 | Solar | 05_01_225W1 | 01/31/2020 | 02/06/2020 | 3 | 0 | 3 | 02/07/2020 | 02/07/2020 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2020 |  | 1/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | Connected |  | N
National Grid | MILLBURY | 176166 | 01527 | 990 | Solar | 05_01_304W4 | 02/27/2015 | 02/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 315126 | 01507 | 0 | Other | 05_01_415L1 | 01/02/2021 | 02/04/2021 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2021 | 03/08/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 709014 | 01475 | 15.76 | Solar | 05_01_612W1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | SOMERSET | 176821 | 02726 | 6 | Solar | 05_05_18J7 | 01/14/2016 | 01/14/2016 | 2 | 2 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/20/2017 | N | EXP | 346 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/6/2016 | Connected |  | N
National Grid | SALEM | 379550 | 01970 | 0 | Solar | 05_12_2W1 | 09/02/2021 | 09/07/2021 | 2 | 0 | 2 | 09/08/2021 | 09/08/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2022 | Connected |  | N
National Grid | CHELMSFORD | 175754 | 01824 | 100 | Solar | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 18 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | HAVERHILL | 705677 | 01832 | 8.027 | Solar | 05_14_48L1 | 07/17/2025 | 08/04/2025 | 7 | 3 | 4 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | LAWRENCE | 672008 | 01843 | 15.2 | Solar | 05_14_61L3 | 02/13/2025 | 03/05/2025 | 14 | 10 | 4 | 03/06/2025 | 03/06/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176870 | 01850 | 7.6 | Solar | 05_14_75L5 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 323 | 09/30/2016 | 10/18/2016 | 11 | 0 | 11 | 4/18/2016 | 4/18/2016 | 10/17/2016 | Connected |  | N
National Grid | BOLTON | 289477 | 01740 | 12 | Solar | 05_01_225W1 | 05/12/2020 | 05/13/2020 | 0 | 0 | 0 | 05/14/2020 | 05/14/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2020 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176228 | 01527 | 6 | Solar | 05_01_304W4 | 09/02/2015 | 09/02/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2015 | 09/02/2015 | 9/12/2016 | Y | EXP | 355 | 07/29/2016 | 08/06/2016 | 6 | 0 | 6 | 9/23/2015 | 9/23/2015 | 8/23/2016 | Connected |  | N
National Grid | CHARLTON | 365577 | 01507 | 7.6 | Solar | 05_01_415L1 | 06/23/2021 | 07/20/2021 | 18 | 14 | 4 | 07/21/2021 | 07/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2021 |  | 9/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | Y
National Grid | WINCHENDON | 721110 | 01475 | 15.2 | Solar | 05_01_612W1 | 09/23/2025 | 09/29/2025 | 3 | 1 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | SOMERSET | 176860 | 02726 | 7.6 | Solar | 05_05_18J7 | 01/20/2016 | 01/20/2016 | 3 | 3 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/25/2017 | N | EXP | 337 |  |  | 0 | 0 | 0 | 7/13/2016 | 7/13/2016 | 7/18/2016 | Connected |  | N
National Grid | SALEM | 387155 | 01970 | 7.6 | Solar | 05_12_2W1 | 10/27/2021 | 11/08/2021 | 9 | 5 | 4 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 | 10/27/2021 | 6/3/2023 | Y | EXP | 365 | 04/22/2022 | 05/26/2022 | 35 | 0 | 35 |  |  | 6/29/2022 | Connected |  | N
National Grid | CHELMSFORD | 175753 | 01824 | 300 | Solar | 05_14_16L4 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 118 | 03/10/2015 | 06/26/2015 | 74 | 0 | 74 | 5/22/2015 | 5/22/2015 | 5/22/2015 | Connected |  | N
National Grid | HAVERHILL | 707574 | 01830 | 17.48 | Solar | 05_14_48L1 | 07/25/2025 | 07/29/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | LAWRENCE | 673460 | 01843 | 13.8 | Solar | 05_14_61L3 | 02/21/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/21/2025 | 5/27/2026 | Y | EXP | 365 | 10/25/2025 | 12/01/2025 | 38 | 0 | 38 |  |  | 12/9/2025 | Connected |  | N
National Grid | DRACUT | 186665 | 01826 | 3.8 | Solar | 05_14_75L5 | 05/30/2018 | 05/30/2018 | 10 | 9 | 1 | 07/11/2018 | 07/11/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 7/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2019 | Connected |  | N
National Grid | BOLTON | 290294 | 01740 | 15.2 | Solar | 05_01_225W1 | 05/04/2020 | 05/11/2020 | 5 | 5 | 0 | 05/12/2020 | 05/12/2020 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | MILLBURY | 176282 | 01527 | 19 | Solar | 05_01_304W4 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | CHARLTON | 377511 | 01507 | 999 | Solar | 05_01_415L1 | 04/26/2022 | 05/18/2022 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/19/2022 | 06/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 616454 | 01475 | 4000 | Solar | 05_01_612W3 | 08/01/2024 | 11/25/2024 | 80 | 70 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 06/30/2025 | 146 | 127 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SOMERSET | 178512 | 02726 | 16.6 | Solar | 05_05_18J7 | 03/08/2018 | 03/08/2018 | 0 | 0 | 0 | 03/12/2018 | 03/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 3/13/2019 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 406678 | 01970 | 15.2 | Solar | 05_12_2W1 | 01/14/2022 | 01/18/2022 | 1 | 0 | 1 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 178333 | 01824 | 7.6 | Solar | 05_14_16L4 | 11/17/2017 | 11/17/2017 | 37 | 36 | 1 | 01/12/2018 | 01/12/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 |  | 11/22/2018 | N | EXP | 31 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 711691 | 01830 | 4.537 | Solar | 05_14_48L1 | 08/15/2025 | 09/04/2025 | 16 | 12 | 4 | 10/01/2025 | 10/01/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 673361 | 01843 | 5.76 | Solar | 05_14_61L3 | 02/21/2025 | 02/26/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 199149 | 01850 | 10 | Solar | 05_14_75L5 | 12/04/2018 | 01/10/2019 | 24 | 16 | 8 | 01/11/2019 | 01/11/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 | 12/04/2018 | 10/2/2019 | Y | EXP | 253 | 05/01/2019 | 06/11/2019 | 41 | 0 | 41 |  |  | 9/3/2019 | Connected |  | N
National Grid | BOLTON | 291401 | 01740 | 0 | Battery Add-On | 05_01_225W1 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 08/27/2020 | 09/10/2020 | 14 | 0 | 14 |  |  | 12/9/2020 | Connected |  | N
National Grid | MILLBURY | 176446 | 01527 | 72 | Solar | 05_01_304W4 | 05/17/2016 | 05/17/2016 | 20 | 20 | 0 | 06/15/2016 | 06/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2016 |  | 5/22/2017 | N | EXP | 332 |  |  | 0 | 0 | 0 | 10/3/2016 | 10/3/2016 | 10/3/2016 | Connected |  | N
National Grid | CHARLTON | 409406 | 01507 | 7.6 | Solar | 05_01_415L1 | 10/28/2022 | 01/24/2023 | 57 | 51 | 6 | 01/25/2023 | 01/25/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 10/28/2022 | 5/29/2024 | Y | EXP | 365 | 04/27/2023 | 06/08/2023 | 43 | 0 | 43 |  |  | 8/24/2023 | Connected |  | N
National Grid | WINCHENDON | 657817 | 01475 | 5.76 | Solar | 05_01_612W3 | 12/02/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 3/5/2026 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SOMERSET | 221739 | 02726 | 0 | Solar | 05_05_18J7 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | SALEM | 415655 | 01970 | 10 | Solar | 05_12_2W1 | 03/14/2022 | 03/23/2022 | 7 | 3 | 4 | 03/24/2022 | 03/24/2022 | 54 | 26 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 178633 | 01824 | 9 | Solar | 05_14_16L4 | 04/09/2018 | 04/09/2018 | 7 | 7 | 0 | 04/25/2018 | 04/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 703899 | 01832 | 6 | Solar | 05_14_48L2 | 07/10/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 | 07/10/2025 | 10/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 673492 | 01843 | 7.6 | Solar | 05_14_61L3 | 02/21/2025 | 03/26/2025 | 15 | 12 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 02/21/2025 | 5/12/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 12/26/2025 | Connected |  | N
National Grid | DRACUT | 217114 | 01826 | 10 | Solar | 05_14_75L5 | 04/10/2019 | 04/25/2019 | 11 | 11 | 0 | 04/26/2019 | 04/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2019 | 04/10/2019 | 3/31/2020 | Y | EXP | 336 | 09/27/2019 | 10/23/2019 | 26 | 0 | 26 |  |  | 10/28/2019 | Connected |  | N
National Grid | HARVARD | 297124 | 01451 | 15.2 | Solar | 05_01_225W1 | 06/20/2020 | 06/23/2020 | 1 | 0 | 1 | 06/24/2020 | 06/24/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | Y
National Grid | MILLBURY | 176464 | 01527 | 4.3 | Solar | 05_01_304W4 | 02/05/2016 | 02/05/2016 | 4 | 4 | 0 | 02/12/2016 | 02/12/2016 | 235 | 0 | 235 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/13/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 414142 | 01566 | 0 | Solar | 05_01_415L1 | 02/24/2022 | 04/15/2022 | 36 | 35 | 1 | 04/19/2022 | 04/19/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 7/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 715711 | 01475 | 7.6 | Solar | 05_01_612W3 | 08/29/2025 | 09/12/2025 | 12 | 9 | 3 | 12/08/2025 | 12/08/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SOMERSET | 636152 | 02726 | 16.24 | Solar | 05_05_18J7 | 08/29/2024 | 09/05/2024 | 5 | 3 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 437523 | 01970 | 15.2 | Solar | 05_12_2W1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 06/14/2022 | 2/29/2024 | Y | EXP | 365 | 01/25/2023 | 04/17/2023 | 83 | 0 | 83 |  |  | 5/22/2023 | Connected |  | N
National Grid | CHELMSFORD | 194082 | 01824 | 9 | Solar | 05_14_16L4 | 09/19/2018 | 10/09/2018 | 1 | 0 | 1 | 10/10/2018 | 10/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 | 09/19/2018 | 10/31/2019 | Y | EXP | 365 | 03/07/2019 | 03/19/2019 | 12 | 0 | 12 |  |  | 5/25/2019 | Connected |  | N
National Grid | HAVERHILL | 730051 | 01830 | 150 | Solar | 05_14_48L2 | 10/30/2025 | 11/24/2025 | 16 | 6 | 10 | 11/25/2025 | 11/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 683655 | 01843 | 5.76 | Solar | 05_14_61L3 | 04/08/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 284540 | 01850 | 5.67 | Solar | 05_14_75L5 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/5/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 310710 | 01740 | 0 | Solar | 05_01_225W1 | 09/14/2020 | 09/21/2020 | 4 | 0 | 4 | 09/22/2020 | 09/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 7/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | MILLBURY | 176619 | 01527 | 10 | Solar | 05_01_304W4 | 04/11/2016 | 04/11/2016 | 2 | 2 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/11/2016 | 10/17/2017 | Y | EXP | 539 | 06/30/2017 | 06/28/2017 | 0 | 0 | 0 | 7/14/2017 | 7/14/2017 | 7/14/2017 | Connected |  | N
National Grid | CHARLTON | 418661 | 01507 | 8.12 | Solar | 05_01_415L1 | 04/20/2022 | 04/21/2022 | 1 | 0 | 1 | 04/22/2022 | 04/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 | 04/20/2022 | 4/12/2024 | Y | EXP | 365 | 04/06/2023 | 04/12/2023 | 7 | 0 | 7 |  |  | 5/15/2023 | Connected |  | N
National Grid | WINCHENDON | 724158 | 01475 | 7.6 | Solar | 05_01_612W3 | 11/05/2025 | 11/05/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 676835 | 02726 | 22.272 | Solar | 05_05_18J7 | 03/10/2025 | 03/21/2025 | 10 | 6 | 4 | 03/24/2025 | 03/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | SALEM | 460824 | 01970 | 6 | Solar | 05_12_2W1 | 09/26/2022 | 09/28/2022 | 2 | 0 | 2 | 09/29/2022 | 09/29/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/26/2022 | 9/3/2024 | Y | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 196414 | 01824 | 9.6 | Solar | 05_14_16L4 | 11/09/2018 | 12/07/2018 | 16 | 15 | 1 | 12/10/2018 | 12/10/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 744896 | 01832 | 10 | Solar | 05_14_48L2 | 01/14/2026 | 01/15/2026 | 9 | 6 | 3 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 689858 | 01843 | 5.76 | Solar | 05_14_61L3 | 05/06/2025 | 06/06/2025 | 3 | 0 | 3 | 06/09/2025 | 06/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 | 05/06/2025 | 7/25/2026 | Y | EXP | 365 | 11/04/2025 | 01/27/2026 | 85 | 2 | 83 |  |  | 12/23/2025 | Connected |  | N
National Grid | LOWELL | 307087 | 01850 | 7.6 | Solar | 05_14_75L5 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 312902 | 01740 | 22.8 | Solar | 05_01_225W1 | 09/15/2020 | 09/16/2020 | 0 | 0 | 0 | 09/17/2020 | 09/17/2020 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 |  | 11/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2021 | Connected |  | N
National Grid | MILLBURY | 178124 | 01527 | 1000 | Solar | 05_01_304W4 | 05/15/2017 | 05/15/2017 | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 05/15/2017 | 6/28/2019 | Y | STD | 596 | 12/13/2018 | 05/23/2019 | 161 | 0 | 161 |  |  | 6/27/2019 | Connected |  | N
National Grid | STURBRIDGE | 429910 | 01566 | 15.2 | Solar | 05_01_415L1 | 05/11/2022 | 05/17/2022 | 5 | 4 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2022 | Connected |  | N
National Grid | WINCHENDON | 737858 | 01475 | 10 | Solar | 05_01_612W3 | 12/03/2025 | 12/10/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOMERSET | 717271 | 02762 | 22.8 | Solar | 05_05_19W72 | 09/06/2025 | 09/09/2025 | 2 | 0 | 2 | 09/10/2025 | 09/10/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 557503 | 01970 | 7.6 | Solar | 05_12_2W1 | 10/18/2023 | 10/23/2023 | 3 | 0 | 3 | 10/24/2023 | 10/24/2023 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 203428 | 01824 | 3.8 | Solar | 05_14_16L4 | 12/27/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176994 | 01832 | 82 | Solar | 05_14_48L2 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2016 |  | 7/25/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/2/2016 | 12/2/2016 | 12/2/2016 | Connected |  | N
National Grid | LAWRENCE | 691695 | 01843 | 11.52 | Solar | 05_14_61L3 | 05/21/2025 | 05/30/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/21/2025 | 7/28/2026 | Y | EXP | 365 | 09/25/2025 | 12/01/2025 | 68 | 0 | 68 |  |  | 12/4/2025 | Connected |  | N
National Grid | LOWELL | 349177 | 01850 | 7.6 | Solar | 05_14_75L5 | 04/15/2021 | 04/26/2021 | 5 | 0 | 5 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2021 |  | 6/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 338763 | 01740 | 7.6 | Solar | 05_01_225W1 | 03/05/2021 | 03/08/2021 | 0 | 0 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 | 03/05/2021 | 3/7/2022 | Y | EXP | 365 | 06/17/2021 | 08/17/2021 | 61 | 0 | 61 |  |  | 8/25/2021 | Connected |  | N
National Grid | MILLBURY | 178699 | 01527 | 2000 | Solar | 05_01_304W4 | 02/07/2018 | 03/26/2018 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2018 | 04/23/2018 | 164 | 42 | 122 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/13/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 435573 | 01566 | 7.6 | Solar | 05_01_415L1 | 06/14/2022 | 06/15/2022 | 1 | 0 | 1 | 06/16/2022 | 06/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 | 06/14/2022 | 6/22/2024 | Y | EXP | 365 | 05/10/2023 | 06/22/2023 | 44 | 0 | 44 |  |  | 6/30/2023 | Connected |  | N
National Grid | WINCHENDON | 174544 | 01475 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 735330 | 02726 | 5.76 | Solar | 05_05_19W72 | 02/03/2026 | 02/11/2026 | 6 | 4 | 2 | 02/12/2026 | 02/12/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 569404 | 01970 | 7.6 | Solar | 05_12_2W1 | 11/27/2023 | 11/28/2023 | 1 | 0 | 1 | 11/29/2023 | 11/29/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/27/2023 | 4/20/2025 | Y | EXP | 365 | 08/07/2024 | 10/24/2024 | 79 | 0 | 79 |  |  | 10/30/2024 | Connected |  | N
National Grid | CHELMSFORD | 290312 | 01824 | 9.6 | Solar | 05_14_16L4 | 05/07/2020 | 05/13/2020 | 3 | 0 | 3 | 05/13/2020 | 05/13/2020 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2020 |  | 4/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | HAVERHILL | 177118 | 01830 | 510 | Solar | 05_14_48L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 701747 | 01843 | 7.6 | Solar | 05_14_61L3 | 06/28/2025 | 07/25/2025 | 9 | 5 | 4 | 08/08/2025 | 08/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 | 06/28/2025 | 9/9/2026 | Y | EXP | 365 | 11/04/2025 | 11/21/2025 | 18 | 0 | 18 |  |  | 12/4/2025 | Connected |  | N
National Grid | LOWELL | 383082 | 01850 | 6 | Solar | 05_14_75L5 | 10/13/2021 | 12/21/2021 | 4 | 0 | 4 | 10/20/2021 | 10/20/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2022 | Connected |  | N
National Grid | HARVARD | 338749 | 01451 | 7.6 | Solar | 05_01_225W1 | 01/26/2021 | 01/29/2021 | 2 | 0 | 2 | 02/01/2021 | 02/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | GRAFTON | 186042 | 01536 | 3400 | Solar | 05_01_304W4 | 06/07/2018 | 07/18/2018 | 28 | 26 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/30/2018 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2019 | 06/07/2018 | 8/4/2023 | Y | STD | 488 | 04/02/2022 | 01/13/2023 | 287 | 0 | 287 | 6/7/2023 | 6/27/2023 | 7/25/2023 | Connected |  | N
National Grid | STURBRIDGE | 466862 | 01566 | 20 | Solar | 05_01_415L1 | 10/10/2022 | 11/03/2022 | 18 | 17 | 1 | 11/04/2022 | 11/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 9/2/2024 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 174543 | 01475 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 740920 | 02726 | 7.6 | Solar | 05_05_19W72 | 12/19/2025 | 12/22/2025 | 1 | 0 | 1 | 12/23/2025 | 12/23/2025 | 49 | 28 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 597666 | 01970 | 3.8 | Solar | 05_12_2W1 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 4/16/2025 | Y | EXP | 365 | 05/24/2024 | 08/21/2024 | 90 | 0 | 90 |  |  | 8/5/2024 | Connected |  | N
National Grid | CHELMSFORD | 337957 | 01824 | 7.6 | Solar | 05_14_16L4 | 01/21/2021 | 02/17/2021 | 18 | 17 | 1 | 02/18/2021 | 02/18/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | HAVERHILL | 177188 | 01832 | 51 | Solar | 05_14_48L2 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 1/21/2018 | N | EXP | 51 |  |  | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 1/8/2018 | Connected |  | N
National Grid | LAWRENCE | 703776 | 01843 | 5.76 | Solar | 05_14_61L3 | 07/09/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 521839 | 01850 | 4.93 | Solar | 05_14_75L5 | 04/26/2023 | 07/17/2023 | 55 | 54 | 1 | 07/18/2023 | 07/18/2023 | 149 | 126 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | LANCASTER | 340547 | 01523 | 10 | Solar | 05_01_225W1 | 03/11/2021 | 03/31/2021 | 13 | 11 | 2 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2021 | 03/11/2021 | 12/8/2022 | Y | EXP | 365 | 08/10/2021 | 10/08/2021 | 57 | 3 | 54 |  |  | 12/1/2021 | Connected |  | N
National Grid | MILLBURY | 189080 | 01527 | 200 | Solar | 05_01_304W4 | 06/25/2018 | 06/25/2018 | 1 | 0 | 1 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 484990 | 01507 | 5.51 | Solar | 05_01_415L1 | 12/15/2022 | 12/26/2022 | 7 | 1 | 6 | 12/27/2022 | 12/27/2022 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2023 | Connected |  | N
National Grid | WINCHENDON | 174542 | 01475 | 2000 | Solar | 05_01_612W3 | 11/16/2011 | 11/16/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 174604 | 02726 | 42 | Solar | 05_05_19W72 | 08/24/2011 | 08/24/2011 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 3/2/2012 | N | EXP | 66 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 6/27/2012 | Connected |  | N
National Grid | SALEM | 641278 | 01970 | 5.76 | Solar | 05_12_2W1 | 09/18/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 11/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | CHELMSFORD | 398325 | 01824 | 9.772 | Solar | 05_14_16L4 | 11/30/2021 | 12/20/2021 | 14 | 13 | 1 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 11/30/2021 | 4/15/2023 | Y | EXP | 365 | 04/12/2022 | 04/13/2022 | 2 | 0 | 2 |  |  | 5/20/2022 | Connected |  | N
National Grid | HAVERHILL | 177362 | 01830 | 150 | Solar | 05_14_48L2 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 | 06/23/2016 | 06/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2016 |  | 6/28/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | LAWRENCE | 717411 | 01843 | 7.6 | Solar | 05_14_61L3 | 09/08/2025 | 09/23/2025 | 23 | 22 | 1 | 11/17/2025 | 11/17/2025 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 543771 | 01826 | 9.6 | Solar | 05_14_75L5 | 08/25/2023 | 08/29/2023 | 2 | 0 | 2 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/25/2023 | 10/17/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | HARVARD | 342501 | 01451 | 0 | Battery Add-On | 05_01_225W1 | 02/17/2021 |  | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONSON | 189157 | 01057 | 200 | Solar | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 498882 | 01566 | 12.6 | Solar | 05_01_415L1 | 04/06/2023 | 04/26/2023 | 14 | 12 | 2 | 04/27/2023 | 04/27/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | WINCHENDON | 174980 | 01475 | 1000 | Solar | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 175180 | 02715 | 3130 | Solar | 05_05_19W72 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2013 | 06/24/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2014 | 05/06/2013 | 7/7/2017 | Y | STD | 99 | 03/17/2017 | 06/30/2017 | 73 | 0 | 73 | 6/29/2017 | 6/29/2017 | 7/13/2017 | Connected |  | N
National Grid | SALEM | 648870 | 01970 | 7.6 | Solar | 05_12_2W1 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 402022 | 01824 | 187.5 | Solar | 05_14_16L4 | 12/20/2021 | 01/06/2022 | 13 | 5 | 8 |  |  | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 11/28/2024 | N | STD | 21 |  |  | 0 | 0 | 0 |  |  | 11/14/2024 | Connected |  | N
National Grid | HAVERHILL | 188201 | 01830 | 150 | Solar | 05_14_48L2 | 06/15/2018 | 06/15/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 12/2/2019 | N | EXP | 524 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | LAWRENCE | 715329 | 01843 | 11.84 | Solar | 05_14_62L2 | 09/02/2025 | 11/07/2025 | 9 | 5 | 4 | 11/10/2025 | 11/10/2025 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 576217 | 01850 | 15.2 | Solar | 05_14_75L5 | 12/06/2023 | 12/27/2023 | 13 | 10 | 3 | 12/28/2023 | 12/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 361381 | 01451 | 7.6 | Solar | 05_01_225W1 | 06/01/2021 | 08/10/2021 | 48 | 46 | 2 | 08/11/2021 | 08/11/2021 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 |  | 9/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | MONSON | 189148 | 01057 | 200 | Solar | 05_01_304W4 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 536279 | 01566 | 7.6 | Solar | 05_01_415L1 | 08/28/2023 | 08/30/2023 | 2 | 0 | 2 | 08/31/2023 | 08/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 175008 | 01475 | 1900 | Solar | 05_01_612W3 | 09/07/2011 | 09/07/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/07/2011 | 11/30/2012 | Y | STD | 12 |  |  | 0 | 0 | 0 | 3/6/2014 | 3/6/2014 | 3/7/2014 | Connected |  | N
National Grid | DIGHTON | 175398 | 02715 | 475 | Solar | 05_05_19W72 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 12/29/2014 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 12/31/2016 | N | STD | 52 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 652022 | 01970 | 5.76 | Solar | 05_12_2W1 | 11/13/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | CHELMSFORD | 418467 | 01824 | 6 | Solar | 05_14_16L4 | 04/08/2022 | 04/11/2022 | 1 | 0 | 1 | 04/12/2022 | 04/12/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/08/2022 | 9/11/2023 | Y | EXP | 365 | 08/09/2022 | 08/29/2022 | 21 | 0 | 21 |  |  | 12/9/2022 | Connected |  | N
National Grid | HAVERHILL | 248292 | 01830 | 7.6 | Solar | 05_14_48L2 | 08/12/2019 | 08/14/2019 | 0 | 0 | 0 | 01/31/2020 | 01/31/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 08/12/2019 | 11/6/2020 | Y | EXP | 365 | 05/27/2020 | 06/11/2020 | 15 | 0 | 15 |  |  | 6/15/2020 | Connected |  | N
National Grid | ANDOVER | 175840 | 01810 | 16 | Solar | 05_14_62L2 | 03/04/2015 | 03/04/2015 | 10 | 6 | 4 | 03/20/2015 | 03/20/2015 | 346 | 0 | 346 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/31/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 584135 | 01850 | 7.6 | Solar | 05_14_75L5 | 02/06/2024 | 02/07/2024 | 1 | 0 | 1 | 02/08/2024 | 02/08/2024 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 5/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2024 | Connected |  | N
National Grid | LANCASTER | 362751 | 01523 | 10 | Solar | 05_01_225W1 | 06/15/2021 | 06/16/2021 | 1 | 0 | 1 | 06/17/2021 | 06/17/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | Y
National Grid | PALMER | 224988 | 01069 | 2.4 | Solar | 05_01_304W4 | 06/25/2019 | 10/15/2019 | 104 | 102 | 2 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 | 06/25/2019 | 6/10/2021 | Y | EXP | 365 | 01/12/2021 | 02/04/2021 | 23 | 0 | 23 |  |  | 2/17/2021 | Connected |  | N
National Grid | CHARLTON | 528584 | 01507 | 11.34 | Solar | 05_01_415L1 | 05/26/2023 | 06/01/2023 | 3 | 0 | 3 | 06/02/2023 | 06/02/2023 | 62 | 44 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | WINCHENDON | 176569 | 01475 | 7.6 | Solar | 05_01_612W3 | 12/24/2015 | 12/24/2015 | 4 | 4 | 0 | 12/31/2015 | 12/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/29/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 9/12/2016 | Connected |  | N
National Grid | DIGHTON | 175613 | 02715 | 258 | Solar | 05_05_19W72 | 12/16/2014 | 12/16/2014 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 655422 | 01970 | 7.6 | Solar | 05_12_2W1 | 11/21/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/21/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | CHELMSFORD | 441231 | 01824 | 6 | Solar | 05_14_16L4 | 07/28/2022 | 07/29/2022 | 1 | 0 | 1 | 08/01/2022 | 08/01/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 | 07/28/2022 | 12/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2023 | Connected |  | N
National Grid | HAVERHILL | 300239 | 01832 | 3.8 | Solar | 05_14_48L2 | 07/17/2020 | 07/27/2020 | 5 | 0 | 5 | 07/28/2020 | 07/28/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 | 07/17/2020 | 6/18/2021 | Y | EXP | 365 | 01/13/2021 | 01/19/2021 | 6 | 0 | 6 |  |  | 2/12/2021 | Connected |  | N
National Grid | ANDOVER | 177883 | 01810 | 20 | Solar | 05_14_62L2 | 10/19/2017 | 10/19/2017 | 58 | 52 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 636786 | 01850 | 10 | Solar | 05_14_75L5 | 08/30/2024 | 09/23/2024 | 3 | 0 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 377961 | 01523 | 7.6 | Solar | 05_01_225W1 | 08/25/2021 | 10/06/2021 | 29 | 28 | 1 | 10/07/2021 | 10/07/2021 | 70 | 47 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 10/5/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 228730 | 01527 | 7.6 | Solar | 05_01_304W4 | 07/05/2019 | 10/03/2019 | 63 | 58 | 5 | 10/04/2019 | 10/04/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 |  | 7/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 572984 | 01566 | 7.6 | Solar | 05_01_415L1 | 11/21/2023 | 11/30/2023 | 10 | 8 | 2 | 07/08/2024 | 07/08/2024 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 11/21/2023 | 8/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | WINCHENDON | 176754 | 01475 | 10 | Solar | 05_01_612W3 | 01/12/2016 | 01/12/2016 | 4 | 4 | 0 | 01/20/2016 | 01/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2016 |  | 1/18/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/27/2016 | 1/27/2016 | 5/27/2016 | Connected |  | N
National Grid | SOMERSET | 175855 | 02726 | 10 | Solar | 05_05_19W72 | 08/03/2015 | 08/03/2015 | 4 | 4 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 8/9/2016 | N | EXP | 343 |  |  | 0 | 0 | 0 | 8/21/2015 | 8/21/2015 | 2/18/2016 | Connected |  | N
National Grid | SALEM | 663678 | 01970 | 7.6 | Solar | 05_12_2W1 | 01/03/2025 | 02/05/2025 | 11 | 6 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 468824 | 01824 | 6.144 | Solar | 05_14_16L4 | 03/22/2023 | 03/24/2023 | 2 | 0 | 2 | 03/27/2023 | 03/27/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/22/2023 | 7/13/2024 | Y | EXP | 365 | 07/06/2023 | 07/13/2023 | 8 | 0 | 8 |  |  | 9/23/2023 | Connected |  | N
National Grid | HAVERHILL | 376194 | 01832 | 7.6 | Solar | 05_14_48L2 | 08/16/2021 | 10/15/2021 | 19 | 18 | 1 | 10/18/2021 | 10/18/2021 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 08/16/2021 | 4/16/2023 | Y | EXP | 365 | 01/12/2022 | 02/09/2022 | 29 | 0 | 29 |  |  | 4/22/2022 | Connected |  | N
National Grid | ANDOVER | 186432 | 01810 | 0 | Solar | 05_14_62L2 | 06/20/2018 | 06/20/2018 | 42 | 35 | 7 | 08/21/2018 | 08/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2019 | Connected |  | N
National Grid | DRACUT | 637007 | 01826 | 5.76 | Solar | 05_14_75L5 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 08/30/2024 | 10/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/19/2025 | 148 | 14 | 134 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 396398 | 01740 | 0 | Solar | 05_01_225W1 | 11/18/2021 | 11/23/2021 | 4 | 2 | 2 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 12/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2022 | Connected |  | N
National Grid | MILLBURY | 242650 | 01527 | 3.8 | Solar | 05_01_304W4 | 07/24/2019 | 08/02/2019 | 6 | 5 | 1 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 07/24/2019 | 8/3/2020 | Y | EXP | 365 | 02/01/2020 | 02/26/2020 | 25 | 0 | 25 |  |  | 3/2/2020 | Connected |  | N
National Grid | CHARLTON | 575137 | 01507 | 6 | Solar | 05_01_415L1 | 12/28/2023 | 01/02/2024 | 2 | 0 | 2 | 01/03/2024 | 01/03/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2024 | 12/28/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 177431 | 01477 | 0 | Solar | 05_01_612W3 | 02/27/2017 | 02/27/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 175893 | 02726 | 7.6 | Solar | 05_05_19W72 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 8/10/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 | 8/31/2015 | 8/31/2015 | 1/28/2016 | Connected |  | N
National Grid | SALEM | 670542 | 01970 | 3.77 | Solar | 05_12_2W1 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | CHELMSFORD | 555930 | 01824 | 10 | Solar | 05_14_16L4 | 09/26/2023 | 09/28/2023 | 2 | 0 | 2 | 09/29/2023 | 09/29/2023 | 21 | 0 | 21 | 12/05/2023 | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 1/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 571517 | 01832 | 3.8 | Solar | 05_14_48L2 | 02/05/2024 | 02/05/2024 | 0 | 0 | 0 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 02/05/2024 | 3/15/2025 | Y | EXP | 365 | 05/30/2024 | 10/29/2024 | 153 | 0 | 153 |  |  | 12/3/2024 | Connected |  | N
National Grid | ANDOVER | 194474 | 01810 | 480 | Solar | 05_14_62L2 | 08/27/2018 | 09/04/2018 | 5 | 5 | 0 | 09/05/2018 | 09/05/2018 | 66 | 0 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 9/4/2020 | N | EXP | 541 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 638053 | 01850 | 10.89 | Solar | 05_14_75L5 | 09/05/2024 | 09/26/2024 | 7 | 3 | 4 | 09/27/2024 | 09/27/2024 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 | 09/05/2024 | 11/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | BOLTON | 416510 | 01740 | 0 | Solar | 05_01_225W1 | 03/09/2022 | 03/10/2022 | 1 | 0 | 1 | 03/11/2022 | 03/11/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 4/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2022 | Connected |  | N
National Grid | MILLBURY | 244233 | 01527 | 3.8 | Solar | 05_01_304W4 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 12/2/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | CHARLTON | 606685 | 01507 | 10 | Solar | 05_01_415L1 | 04/25/2024 | 05/01/2024 | 2 | 0 | 2 | 05/02/2024 | 05/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 177430 | 01475 | 1000 | Solar | 05_01_612W3 | 02/27/2017 | 03/23/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 02/27/2017 | 12/31/2020 | Y | STD | 1142 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 175974 | 02726 | 258 | Solar | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 345 | 0 | 345 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 12/31/2016 | N | EXP | 624 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 706875 | 01970 | 5.76 | Solar | 05_12_2W1 | 07/24/2025 | 08/20/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 07/24/2025 | 9/25/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/17/2025 | Connected |  | N
National Grid | CHELMSFORD | 589144 | 01824 | 3.8 | Solar | 05_14_16L4 | 02/22/2024 | 02/26/2024 | 3 | 1 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 06/19/2024 | 07/25/2024 | 37 | 0 | 37 |  |  | 8/21/2024 | Connected |  | N
National Grid | HAVERHILL | 586282 | 01830 | 15.2 | Solar | 05_14_48L2 | 01/31/2024 | 02/20/2024 | 13 | 10 | 3 | 02/21/2024 | 02/21/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | ANDOVER | 200806 | 01810 | 4.8 | Solar | 05_14_62L2 | 11/08/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2019 |  | 1/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2019 | Connected |  | N
National Grid | DRACUT | 637809 | 01826 | 3.8 | Solar | 05_14_75L5 | 09/04/2024 | 09/18/2024 | 1 | 0 | 1 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 422557 | 01740 | 15.2 | Solar | 05_01_225W1 | 04/14/2022 | 04/20/2022 | 4 | 3 | 1 | 04/21/2022 | 04/21/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  | 5/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2022 | Connected |  | N
National Grid | MILLBURY | 286667 | 01527 | 10 | Solar | 05_01_304W4 | 05/18/2020 | 05/19/2020 | 0 | 0 | 0 | 05/20/2020 | 05/20/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2020 |  | 5/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 612835 | 01566 | 9.86 | Solar | 05_01_415L1 | 05/22/2024 | 06/03/2024 | 6 | 5 | 1 | 06/04/2024 | 06/04/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2024 | Connected |  | N
National Grid | WINCHENDON | 177468 | 01475 | 3150 | Solar | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 33 | 08/29/2019 | 12/26/2019 | 119 | 0 | 119 |  |  | 12/26/2019 | Connected |  | N
National Grid | SOMERSET | 176479 | 02726 | 288 | Solar | 05_05_19W72 | 05/19/2016 | 05/19/2016 | 20 | 20 | 0 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 08/16/2016 | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  | 09/16/2016 | 22 | 7 | 15 |  |  | 0 | 0 | 0 | 3/3/2017 |  | 7/15/2017 | N | EXP | 134 |  |  | 0 | 0 | 0 | 6/28/2017 | 6/28/2017 | 8/3/2017 | Connected |  | N
National Grid | SALEM | 175372 | 01970 | 820 | Natural Gas | 05_12_2W2 | 02/19/2014 | 02/19/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2014 | 03/21/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2014 |  | 7/31/2014 | N | STD | 7 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/3/2015 | Connected |  | N
National Grid | CHELMSFORD | 637093 | 01824 | 10 | Solar | 05_14_16L4 | 09/02/2024 | 09/16/2024 | 1 | 0 | 1 | 09/17/2024 | 09/17/2024 | 20 | 13 | 7 | 12/13/2024 | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 12/30/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/23/2026 | N | EXP | 365 | 06/06/2025 | 06/13/2025 | 8 | 0 | 8 |  |  | 7/9/2025 | Connected |  | N
National Grid | HAVERHILL | 587167 | 01830 | 10.24 | Solar | 05_14_48L2 | 02/01/2024 | 02/08/2024 | 3 | 1 | 2 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 02/01/2024 | 3/6/2026 | Y | EXP | 365 | 07/02/2025 | 07/11/2025 | 10 | 0 | 10 |  |  | 7/15/2025 | Connected |  | N
National Grid | ANDOVER | 233871 | 01810 | 10 | Solar | 05_14_62L2 | 06/06/2019 | 06/28/2019 | 16 | 13 | 3 | 07/01/2019 | 07/01/2019 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | LOWELL | 643195 | 01850 | 7.6 | Solar | 05_14_75L5 | 09/27/2024 | 10/16/2024 | 5 | 2 | 3 | 10/17/2024 | 10/17/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 09/27/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LANCASTER | 424363 | 01523 | 7.6 | Solar | 05_01_225W1 | 05/11/2022 | 05/18/2022 | 6 | 5 | 1 | 05/19/2022 | 05/19/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 8/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | N
National Grid | GRAFTON | 440801 | 01536 | 11.89 | Solar | 05_01_304W4 | 07/27/2022 | 08/01/2022 | 4 | 3 | 1 | 08/02/2022 | 08/02/2022 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | STURBRIDGE | 622514 | 01566 | 3.8 | Solar | 05_01_415L1 | 07/03/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/03/2024 | 8/28/2025 | Y | EXP | 365 | 09/19/2024 | 05/28/2025 | 252 | 0 | 252 |  |  | 8/22/2025 | Connected |  | N
National Grid | WINCHENDON | 177470 | 01475 | 0 | Solar | 05_01_612W3 | 02/28/2017 | 02/28/2017 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2017 | 04/20/2017 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176485 | 02726 | 6 | Solar | 05_05_19W72 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 10/03/2016 | 10/13/2016 | 7 | 0 | 7 | 2/16/2017 | 2/16/2017 | 2/16/2017 | Connected |  | N
National Grid | SALEM | 176003 | 01970 | 9.46 | Solar | 05_12_2W2 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 | 08/11/2015 | 7/27/2018 | Y | EXP | 153 | 11/07/2017 | 05/03/2018 | 177 | 0 | 177 |  |  | 7/25/2018 | Connected |  | N
National Grid | CHELMSFORD | 644852 | 01824 | 7.6 | Solar | 05_14_16L4 | 10/03/2024 | 10/31/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2024 | 10/03/2024 | 12/17/2025 | Y | EXP | 365 | 01/16/2025 | 03/03/2025 | 46 | 0 | 46 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 592029 | 01830 | 3.8 | Solar | 05_14_48L2 | 02/22/2024 | 04/30/2024 | 3 | 0 | 3 | 05/01/2024 | 05/01/2024 | 15 | 10 | 5 | 06/10/2024 | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  | 08/02/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | ANDOVER | 300290 | 01810 | 0 | Solar | 05_14_62L2 | 07/08/2020 | 07/13/2020 | 2 | 2 | 0 | 07/14/2020 | 07/14/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2020 | Connected |  | N
National Grid | LOWELL | 646399 | 01850 | 5.76 | Solar | 05_14_75L5 | 10/16/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/16/2024 | 12/24/2025 | Y | EXP | 365 | 01/16/2025 | 02/18/2025 | 33 | 0 | 33 |  |  | 3/14/2025 | Connected |  | N
National Grid | BOLTON | 428357 | 01740 | 9.57 | Solar | 05_01_225W1 | 05/04/2022 | 05/05/2022 | 1 | 1 | 0 | 05/06/2022 | 05/06/2022 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 | 05/04/2022 | 11/10/2023 | Y | EXP | 365 | 09/30/2022 | 11/09/2022 | 41 | 0 | 41 |  |  | 6/14/2023 | Connected |  | N
National Grid | GRAFTON | 505155 | 01536 | 7.6 | Solar | 05_01_304W4 | 03/09/2023 | 03/20/2023 | 7 | 0 | 7 | 03/21/2023 | 03/21/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2023 | 03/09/2023 | 7/28/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | STURBRIDGE | 625725 | 01566 | 7.6 | Solar | 05_01_415L1 | 07/17/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 10/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | WINCHENDON | 177469 | 01475 | 4979.98 | Solar | 05_01_612W3 | 02/28/2017 | 03/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2017 | 04/20/2017 | 15 | 4 | 11 |  |  | 0 | 0 | 0 | 12/16/2017 | 10/10/2018 | 74 | 0 | 74 | 11/20/2017 | 02/28/2017 | 12/31/2019 | Y | STD | 351 | 09/14/2019 | 12/26/2019 | 103 | 0 | 103 |  |  | 12/26/2019 | Connected |  | N
National Grid | SOMERSET | 176648 | 02726 | 7.6 | Solar | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/23/2017 | Y | EXP | 339 | 07/18/2016 | 07/26/2016 | 6 | 0 | 6 | 3/21/2016 | 3/21/2016 | 10/13/2016 | Connected |  | N
National Grid | SALEM | 198887 | 01970 | 900 | Natural Gas | 05_12_2W2 | 10/19/2018 | 11/09/2018 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 04/02/2019 | 96 | 76 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/19/2018 |  | Y | STD | 365 | 02/25/2020 | 02/24/2020 | 0 | 0 | 0 |  |  | 4/3/2020 | Connected |  | N
National Grid | CHELMSFORD | 666027 | 01824 | 13.36 | Solar | 05_14_16L4 | 01/17/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 28 | 8 | 20 | 04/22/2025 | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 06/05/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 6/10/2025 | 01/17/2025 | 6/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | HAVERHILL | 604752 | 01830 | 10 | Solar | 05_14_48L2 | 04/17/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 04/17/2024 | 8/5/2025 | Y | EXP | 365 | 09/12/2024 | 03/31/2025 | 201 | 0 | 201 |  |  | 4/10/2025 | Connected |  | N
National Grid | ANDOVER | 328453 | 01810 | 0 | Solar | 05_14_62L2 | 11/25/2020 | 01/26/2021 | 39 | 38 | 1 | 01/27/2021 | 01/27/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 6/23/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | DRACUT | 646853 | 01826 | 5.76 | Solar | 05_14_75L5 | 10/29/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | HARVARD | 442327 | 01451 | 15 | Solar | 05_01_225W1 | 07/18/2022 | 07/20/2022 | 3 | 2 | 1 | 07/21/2022 | 07/21/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 |  | 9/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2022 | Connected |  | N
National Grid | GRAFTON | 529519 | 01536 | 12.6 | Solar | 05_01_304W4 | 05/26/2023 | 05/30/2023 | 1 | 0 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2024 | Connected |  | N
National Grid | STURBRIDGE | 645265 | 01566 | 10 | Solar | 05_01_415L1 | 10/07/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | WINCHENDON | 177920 | 01475 | 9765 | Solar | 05_01_612W3 | 10/23/2017 | 11/21/2017 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/19/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/23/2017 |  | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176645 | 02726 | 5 | Solar | 05_05_19W72 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/17/2016 | 2/22/2017 | Y | EXP | 338 | 06/01/2016 | 06/10/2016 | 7 | 0 | 7 | 3/21/2016 | 3/21/2016 | 1/3/2017 | Connected |  | N
National Grid | SALEM | 213359 | 01970 | 0 | Solar | 05_12_2W2 | 03/12/2019 | 03/21/2019 | 6 | 0 | 6 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | LOWELL | 672940 | 01851 | 3.8 | Solar | 05_14_16L4 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 100 | 86 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 619097 | 01832 | 10 | Solar | 05_14_48L2 | 06/20/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 06/20/2024 | 2/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 331152 | 01810 | 0 | Solar | 05_14_62L2 | 12/11/2020 | 12/18/2020 | 4 | 0 | 4 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 | 12/11/2020 | 9/5/2023 | Y | EXP | 475 | 08/15/2021 | 09/16/2021 | 32 | 3 | 29 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 651011 | 01826 | 6 | Solar | 05_14_75L5 | 11/12/2024 | 02/05/2025 | 30 | 25 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | BOLTON | 444227 | 01740 | 7.6 | Solar | 05_01_225W1 | 07/14/2022 | 07/25/2022 | 3 | 0 | 3 | 11/03/2022 | 11/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 07/14/2022 | 8/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2023 | Connected |  | N
National Grid | GRAFTON | 570827 | 01536 | 23 | Solar | 05_01_304W4 | 11/13/2023 | 11/15/2023 | 2 | 0 | 2 | 11/16/2023 | 11/16/2023 | 74 | 50 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | STURBRIDGE | 658052 | 01566 | 20 | Solar | 05_01_415L1 | 12/04/2024 | 12/17/2024 | 9 | 5 | 4 | 12/18/2024 | 12/18/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WINCHENDON | 178258 | 01475 | 4999 | Solar | 05_01_612W3 | 04/17/2018 | 04/17/2018 | 4 | 3 | 1 |  |  | 79 | 67 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176684 | 02726 | 6 | Solar | 05_05_19W72 | 02/18/2016 | 02/18/2016 | 1 | 1 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2016 | 02/18/2016 | 2/24/2017 | Y | EXP | 34 | 07/18/2016 | 08/05/2016 | 14 | 0 | 14 | 12/29/2016 | 12/29/2016 | 1/4/2017 | Connected |  | N
National Grid | SALEM | 676951 | 01970 | 10 | Solar | 05_12_2W2 | 03/10/2025 | 04/03/2025 | 2 | 0 | 2 | 04/14/2025 | 04/14/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | CHELMSFORD | 677854 | 01824 | 7.6 | Solar | 05_14_16L4 | 03/17/2025 | 03/20/2025 | 3 | 0 | 3 | 03/21/2025 | 03/21/2025 | 100 | 80 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 627679 | 01830 | 6 | Solar | 05_14_48L2 | 07/25/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/25/2024 | 8/27/2025 | Y | EXP | 365 | 03/05/2025 | 03/04/2025 | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | ANDOVER | 370322 | 01810 | 7.6 | Solar | 05_14_62L2 | 07/16/2021 |  | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 651149 | 01850 | 5.76 | Solar | 05_14_75L5 | 11/12/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | BOLTON | 460092 | 01740 | 7.6 | Solar | 05_01_225W1 | 09/19/2022 | 10/03/2022 | 10 | 5 | 5 | 10/04/2022 | 10/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 |  | 11/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2023 | Connected |  | N
National Grid | GRAFTON | 616690 | 01536 | 7.6 | Solar | 05_01_304W4 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 24 | 10 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | STURBRIDGE | 657791 | 01566 | 11.5 | Solar | 05_01_415L1 | 12/02/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/02/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | WINCHENDON | 178601 | 01475 | 4998 | Solar | 05_01_612W3 | 04/06/2018 | 04/06/2018 | 22 | 9 | 13 |  |  | 1951 | 0 | 1951 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176701 | 02726 | 12 | Solar | 05_05_19W72 | 10/26/2015 | 10/26/2015 | 9 | 9 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2015 |  | 10/31/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 3/14/2016 | 3/14/2016 | 3/17/2016 | Connected |  | N
National Grid | SALEM | 676829 | 01970 | 7.6 | Solar | 05_12_2W2 | 03/10/2025 | 03/27/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/10/2025 | 6/16/2026 | Y | EXP | 365 | 08/28/2025 | 10/29/2025 | 63 | 0 | 63 |  |  | 11/13/2025 | Connected |  | N
National Grid | CHELMSFORD | 624477 | 01824 | 200 | Solar | 05_14_16L7 | 07/25/2024 | 08/26/2024 | 22 | 16 | 6 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 | 07/25/2024 | 11/21/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 633406 | 01830 | 3.8 | Solar | 05_14_48L2 | 08/20/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 | 08/20/2024 | 1/8/2026 | Y | EXP | 365 | 08/28/2025 | 11/21/2025 | 86 | 0 | 86 |  |  | 12/4/2025 | Connected |  | N
National Grid | ANDOVER | 380185 | 01810 | 7.6 | Solar | 05_14_62L2 | 09/06/2021 |  | 75 | 69 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 654202 | 01850 | 7.6 | Solar | 05_14_75L5 | 11/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/13/2024 | 3/27/2026 | Y | EXP | 365 | 05/24/2025 | 11/17/2025 | 178 | 0 | 178 |  |  | 7/21/2025 | Connected |  | N
National Grid | LANCASTER | 483675 | 01523 | 13.92 | Solar | 05_01_225W1 | 12/14/2022 | 12/20/2022 | 4 | 1 | 3 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 5/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | GRAFTON | 625716 | 01536 | 210 | Solar | 05_01_304W4 | 07/19/2024 | 09/06/2024 | 35 | 28 | 7 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 662122 | 01507 | 3.8 | Solar | 05_01_415L1 | 12/21/2024 | 01/16/2025 | 3 | 0 | 3 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 178726 | 01475 | 4990 | Solar | 05_01_612W3 | 12/20/2017 | 02/14/2018 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 176835 | 02715 | 3.8 | Solar | 05_05_19W72 | 02/29/2016 | 02/29/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/6/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 8/9/2016 | Connected |  | N
National Grid | SALEM | 311130 | 01970 | 7.6 | Solar | 05_12_35J1 | 09/30/2020 | 10/06/2020 | 3 | 0 | 3 | 10/07/2020 | 10/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 346400 | 01824 | 250 | Solar | 05_14_16L7 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 134 | 109 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 641356 | 01830 | 4.64 | Solar | 05_14_48L2 | 09/20/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/20/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | ANDOVER | 394876 | 01810 | 7.6 | Solar | 05_14_62L2 | 11/11/2021 | 12/20/2021 | 27 | 24 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  | 8/2/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 654398 | 01850 | 5.32 | Solar | 05_14_75L5 | 11/14/2024 | 01/06/2025 | 28 | 24 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 3/21/2026 | N | EXP | 365 | 02/21/2025 | 04/29/2025 | 68 | 27 | 41 |  |  | 5/6/2025 | Connected |  | N
National Grid | BOLTON | 484329 | 01740 | 0 | Solar | 05_01_225W1 | 12/09/2022 | 02/10/2023 | 42 | 35 | 7 | 02/13/2023 | 02/13/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 643375 | 01527 | 7.6 | Solar | 05_01_304W4 | 09/27/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/27/2024 | 1/30/2026 | Y | EXP | 365 | 02/26/2025 | 08/21/2025 | 176 | 49 | 127 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 674999 | 01566 | 20 | Solar | 05_01_415L1 | 03/04/2025 | 03/20/2025 | 13 | 8 | 5 | 03/21/2025 | 03/21/2025 | 36 | 15 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/04/2025 | 5/27/2026 | Y | EXP | 365 | 09/30/2025 | 10/08/2025 | 9 | 0 | 9 |  |  | 12/9/2025 | Connected |  | N
National Grid | WINCHENDON | 178725 | 01475 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 176897 | 02726 | 2000 | Solar | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 04/04/2017 | 04/17/2017 | 9 | 0 | 9 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 514805 | 02151 | 6 | Solar | 05_12_35J1 | 04/07/2023 | 04/10/2023 | 1 | 0 | 1 | 04/11/2023 | 04/11/2023 | 25 | 0 | 25 | 06/26/2023 | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  | 08/23/2023 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 8/24/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176414 | 01852 | 480 | Solar | 05_14_18L1 | 11/30/2015 | 11/30/2015 | 0 | 0 | 0 | 12/03/2015 | 12/03/2015 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 6/28/2018 | N | EXP | 786 |  |  | 0 | 0 | 0 |  |  | 6/22/2018 | Connected |  | N
National Grid | HAVERHILL | 642251 | 01830 | 10 | Solar | 05_14_48L2 | 09/25/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 09/25/2024 | 11/27/2025 | Y | EXP | 365 | 03/15/2025 | 09/06/2025 | 176 | 0 | 176 |  |  | 9/18/2025 | Connected |  | N
National Grid | ANDOVER | 404321 | 01810 | 7.6 | Solar | 05_14_62L2 | 01/02/2022 | 01/04/2022 | 1 | 0 | 1 | 01/05/2022 | 01/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 6/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | LOWELL | 657885 | 01850 | 6.38 | Solar | 05_14_75L5 | 12/02/2024 | 01/03/2025 | 4 | 2 | 2 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | HARVARD | 485679 | 01451 | 15.6 | Solar | 05_01_225W1 | 12/15/2022 | 02/09/2023 | 37 | 36 | 1 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2023 | Connected |  | N
National Grid | MILLBURY | 667645 | 01527 | 3.8 | Solar | 05_01_304W4 | 01/24/2025 | 02/05/2025 | 4 | 0 | 4 | 02/06/2025 | 02/06/2025 | 22 | 0 | 22 | 03/11/2025 | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/10/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 675967 | 01507 | 15.2 | Solar | 05_01_415L1 | 03/05/2025 | 03/12/2025 | 5 | 1 | 4 | 03/13/2025 | 03/13/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | WINCHENDON | 178724 | 01475 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 176896 | 02715 | 2000 | Solar | 05_05_19W72 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/19/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 03/23/2017 |  | 254 | 0 | 254 | 9/29/2016 |  | 1/30/2017 | N | STD | 123 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 544704 | 02151 | 100 | Solar | 05_12_35J1 | 08/02/2023 | 10/24/2023 | 57 | 48 | 9 | 10/25/2023 | 10/25/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 9/22/2024 | N | EXP | 86 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | BILLERICA | 177575 | 01821 | 480 | Solar | 05_14_18L1 | 09/19/2017 | 09/19/2017 | 28 | 19 | 9 | 11/03/2017 | 11/03/2017 | 12 | 12 | 0 | 02/09/2018 | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 3/23/2018 |  | 9/24/2018 | N | EXP | 185 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | HAVERHILL | 647358 | 01832 | 15.2 | Solar | 05_14_48L2 | 11/07/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | ANDOVER | 442063 | 01810 | 13.6 | Solar | 05_14_62L2 | 08/02/2022 | 08/03/2022 | 2 | 1 | 1 | 08/04/2022 | 08/04/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 | 08/02/2022 | 8/30/2023 | Y | EXP | 365 | 09/28/2022 | 12/21/2022 | 85 | 0 | 85 |  |  | 1/5/2023 | Connected |  | N
National Grid | DRACUT | 661283 | 01826 | 15.2 | Solar | 05_14_75L5 | 02/11/2025 |  | 101 | 80 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 488296 | 01740 | 0 | Solar | 05_01_225W1 | 12/27/2022 | 01/03/2023 | 4 | 1 | 3 | 01/04/2023 | 01/04/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 670474 | 01527 | 4999.2 | Solar | 05_01_304W5 | 03/20/2025 | 05/12/2025 | 37 | 27 | 10 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | CHARLTON | 681472 | 01507 | 12.18 | Solar | 05_01_415L1 | 04/01/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 111 | 86 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | WINCHENDON | 178723 | 01475 | 4990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/01/2020 | 59 | 3 | 56 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 176981 | 02715 | 5.2 | Solar | 05_05_19W72 | 12/29/2016 | 12/29/2016 | 1 | 1 | 0 | 01/04/2017 | 01/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2017 | 12/29/2016 | 1/7/2018 | Y | EXP | 366 | 05/01/2017 | 06/08/2017 | 27 | 0 | 27 | 6/28/2017 | 6/28/2017 | 6/30/2017 | Connected |  | N
National Grid | REVERE | 598590 | 02151 | 7.6 | Solar | 05_12_35J1 | 03/21/2024 | 03/26/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | BILLERICA | 189998 | 01821 | 15.2 | Solar | 05_14_18L1 | 07/05/2018 | 07/05/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2018 |  | 8/12/2019 | N | EXP | 392 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | HAVERHILL | 648633 | 01832 | 5.76 | Solar | 05_14_48L2 | 11/01/2024 | 12/03/2024 | 13 | 9 | 4 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 470177 | 01810 | 15.2 | Solar | 05_14_62L2 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/21/2022 | 1/20/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | LOWELL | 661713 | 01850 | 3.8 | Solar | 05_14_75L5 | 12/19/2024 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HARVARD | 495716 | 01451 | 0 | Solar | 05_01_225W1 | 01/27/2023 | 02/01/2023 | 4 | 3 | 1 | 02/02/2023 | 02/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | MILLBURY | 686006 | 01527 | 3.8 | Solar | 05_01_304W5 | 04/17/2025 | 04/25/2025 | 5 | 0 | 5 | 04/28/2025 | 04/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STURBRIDGE | 699606 | 01566 | 5.76 | Solar | 05_01_415L1 | 06/20/2025 | 07/07/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 178722 | 01475 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177262 | 02726 | 270 | Solar | 05_05_19W72 | 01/20/2015 | 01/20/2015 | 3 | 0 | 3 | 01/28/2015 | 01/28/2015 | 0 | 0 | 0 | 03/11/2015 | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/17/2015 | 01/20/2015 | 8/28/2017 | Y | EXP | 864 | 05/13/2016 | 06/20/2016 | 24 | 0 | 24 | 11/2/2016 | 11/2/2016 | 11/7/2016 | Connected |  | N
National Grid | REVERE | 632210 | 02151 | 10 | Solar | 05_12_35J1 | 08/13/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/13/2024 | 3/25/2026 | Y | EXP | 365 | 12/21/2024 | 09/10/2025 | 264 | 0 | 264 |  |  | 9/17/2025 | Connected |  | N
National Grid | BILLERICA | 268241 | 01821 | 3.8 | Solar | 05_14_18L1 | 12/05/2019 | 12/10/2019 | 3 | 3 | 0 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2019 |  | 12/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 650991 | 01832 | 5.76 | Solar | 05_14_48L2 | 11/12/2024 | 12/09/2024 | 1 | 0 | 1 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/12/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 481649 | 01810 | 9.984 | Solar | 05_14_62L2 | 01/16/2023 | 01/18/2023 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  | 10/27/2024 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 9/25/2024 | Connected |  | N
National Grid | LOWELL | 654679 | 01850 | 7.6 | Solar | 05_14_75L6 | 11/15/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/15/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BOLTON | 506817 | 01740 | 13.34 | Solar | 05_01_225W1 | 03/20/2023 | 03/23/2023 | 3 | 0 | 3 | 03/24/2023 | 03/24/2023 | 25 | 0 | 25 | 06/21/2023 | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  | 08/09/2023 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 8/14/2024 | N | EXP | 365 | 10/05/2023 | 10/18/2023 | 14 | 0 | 14 |  |  | 10/27/2023 | Connected |  | Y
National Grid | MILLBURY | 755047 | 01527 | 0 | Battery Add-On | 05_01_304W5 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHARLTON | 716574 | 01507 | 21.4 | Solar | 05_01_415L1 | 09/10/2025 | 09/15/2025 | 3 | 0 | 3 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | WINCHENDON | 178721 | 01475 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/14/2018 | 03/12/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 177733 | 02726 | 3.8 | Solar | 05_05_19W72 | 03/22/2017 | 03/22/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/22/2017 | 3/27/2018 | Y | EXP | 363 | 08/09/2017 | 09/12/2017 | 23 | 0 | 23 | 10/16/2017 | 10/16/2017 | 10/18/2017 | Connected |  | N
National Grid | REVERE | 633469 | 02151 | 6 | Solar | 05_12_35J1 | 08/19/2024 | 08/27/2024 | 5 | 0 | 5 | 08/28/2024 | 08/28/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | BILLERICA | 268931 | 01821 | 3.8 | Solar | 05_14_18L1 | 12/18/2019 | 12/18/2019 | 0 | 0 | 0 | 12/19/2019 | 12/19/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 |  | 12/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2020 | Connected |  | N
National Grid | HAVERHILL | 653889 | 01832 | 3.8 | Solar | 05_14_48L2 | 12/04/2024 | 01/21/2025 | 4 | 0 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/04/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | ANDOVER | 483147 | 01810 | 15.2 | Solar | 05_14_62L2 | 12/28/2022 | 01/18/2023 | 14 | 13 | 1 | 01/19/2023 | 01/19/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 737727 | 01844 | 5.76 | Solar | 05_14_75L6 | 12/03/2025 | 12/17/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOLTON | 524294 | 01740 | 15.2 | Solar | 05_01_225W1 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | SUTTON | 174666 | 01590 | 19.99 | Solar | 05_01_304W5 | 12/18/2012 | 12/18/2012 | 8 | 0 | 8 | 01/02/2013 | 01/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 3/8/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 5/22/2013 | 5/22/2013 | 6/11/2013 | Connected |  | N
National Grid | CHARLTON | 308483 | 01507 | 0 | Other | 05_01_415L2 | 08/25/2020 | 09/30/2020 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/25/2020 |  | Y | STD | 77 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WINCHENDON | 178729 | 01475 | 3900 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/12/2018 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 12/20/2017 | 1/24/2025 | Y | STD | 61 | 12/31/2021 | 05/03/2022 | 124 | 78 | 46 |  |  | 1/15/2025 | Connected |  | N
National Grid | SOMERSET | 178080 | 02726 | 2800 | Solar | 05_05_19W72 | 05/08/2017 | 05/08/2017 | 121 | 121 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/29/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2018 | 05/08/2017 | 12/2/2020 | Y | STD | 68 | 10/12/2019 | 09/21/2020 | 346 | 126 | 220 |  |  | 12/7/2020 | Connected |  | N
National Grid | REVERE | 641020 | 02151 | 6 | Solar | 05_12_35J1 | 09/17/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 | 09/17/2024 | 11/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 408871 | 01821 | 0 | Battery Add-On | 05_14_18L1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/06/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 657537 | 01830 | 3.8 | Solar | 05_14_48L2 | 11/28/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 | 05/30/2025 | 12/01/2025 | 186 | 0 | 186 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 489268 | 01810 | 22.75 | Solar | 05_14_62L2 | 01/13/2023 | 01/18/2023 | 3 | 1 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | METHUEN | 174341 | 01844 | 225 | Solar | 05_14_75L6 | 01/30/2012 | 01/30/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOLTON | 556180 | 01740 | 0 | Battery Add-On | 05_01_225W1 | 09/18/2023 | 10/11/2023 | 17 | 16 | 1 | 10/12/2023 | 10/12/2023 | 223 | 205 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 174701 | 01527 | 11.5 | Solar | 05_01_304W5 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 4/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/3/2013 | 6/3/2013 | 6/6/2013 | Connected |  | N
National Grid | CHARLTON | 493328 | 01507 | 499 | Solar | 05_01_415L2 | 02/21/2024 | 07/29/2024 | 109 | 52 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2024 | 08/14/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WINCHENDON | 178728 | 01475 | 1000 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 34 | 9 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 178605 | 02715 | 10 | Solar | 05_05_19W72 | 12/12/2017 | 12/12/2017 | 14 | 0 | 14 | 01/04/2018 | 01/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/18/2018 | N | EXP | 347 | 05/30/2018 | 06/25/2018 | 26 | 0 | 26 |  |  | 7/11/2018 | Connected |  | N
National Grid | REVERE | 664554 | 02151 | 4.64 | Solar | 05_12_35J1 | 01/24/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 | 01/24/2025 | 4/8/2026 | Y | EXP | 365 | 09/23/2025 | 09/22/2025 | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | BILLERICA | 672467 | 01821 | 5.76 | Solar | 05_14_18L1 | 02/17/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | HAVERHILL | 658084 | 01830 | 5.76 | Solar | 05_14_48L2 | 12/03/2024 | 03/17/2025 | 61 | 57 | 4 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 571929 | 01810 | 0 | Solar | 05_14_62L2 | 11/16/2023 | 11/27/2023 | 6 | 0 | 6 | 11/28/2023 | 11/28/2023 | 71 | 51 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | METHUEN | 177114 | 01844 | 3.8 | Solar | 05_14_75L6 | 08/05/2016 | 08/05/2016 | 1 | 1 | 0 | 08/10/2016 | 08/10/2016 | 125 | 0 | 125 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2016 |  | 8/14/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 532056 | 01740 | 15 | Solar | 05_01_225W1 | 06/07/2023 | 06/27/2023 | 13 | 12 | 1 | 06/28/2023 | 06/28/2023 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2024 | Connected |  | N
National Grid | MILLBURY | 174906 | 01527 | 15 | Solar | 05_01_304W5 | 09/14/2012 | 09/14/2012 | 7 | 4 | 3 | 09/26/2012 | 09/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | 27 |  |  | 0 | 0 | 0 | 2/8/2013 | 2/8/2013 | 3/2/2013 | Connected |  | N
National Grid | CHARLTON | 178727 | 01507 | 1990 | Solar | 05_01_612W3 | 12/20/2017 | 02/12/2018 | 45 | 9 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 07/26/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 190436 | 01475 | 250 | Solar | 05_05_19W72 | 07/11/2018 | 08/15/2018 | 5 | 0 | 5 | 08/16/2018 | 08/16/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 175751 | 02726 | 21.07 | Solar | 05_12_35J2 | 10/31/2014 | 10/31/2014 | 6 | 5 | 1 | 11/12/2014 | 11/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2014 | 10/31/2014 | 12/31/2016 | Y | EXP | 757 | 04/29/2016 | 04/30/2016 | 1 | 0 | 1 | 1/28/2015 | 1/28/2015 | 5/20/2016 | Connected |  | N
National Grid | REVERE | 687181 | 02151 | 7.6 | Solar | 05_14_18L1 | 04/23/2025 | 05/12/2025 | 3 | 0 | 3 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 | 06/25/2025 | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 8/4/2025 | 04/23/2025 | 9/4/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 12/3/2025 | Connected |  | N
National Grid | BILLERICA | 660636 | 01821 | 3.8 | Solar | 05_14_48L2 | 12/13/2024 | 03/26/2025 | 56 | 52 | 4 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 12/13/2024 | 5/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 572719 | 01830 | 22.8 | Solar | 05_14_62L2 | 11/20/2023 | 12/11/2023 | 14 | 13 | 1 | 12/12/2023 | 12/12/2023 | 32 | 12 | 20 | 01/31/2024 | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 02/21/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/5/2025 | N | EXP | 365 | 05/18/2024 | 06/28/2024 | 42 | 0 | 42 |  |  | 7/3/2024 | Connected |  | Y
National Grid | ANDOVER | 177251 | 01810 | 6 | Solar | 05_14_75L6 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 241 | 0 | 241 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 535567 | 01844 | 15.12 | Solar | 05_01_225W1 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2023 |  | 10/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | BOLTON | 175169 | 01740 | 20 | Solar | 05_01_304W5 | 11/14/2012 | 11/14/2012 | 7 | 1 | 6 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2013 |  | 1/31/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 2/13/2013 | 2/13/2013 | 4/12/2013 | Connected |  | N
National Grid | SUTTON | 740995 | 01590 | 19 | Solar | 05_01_415L2 | 12/18/2025 | 01/04/2026 | 9 | 5 | 4 | 01/05/2026 | 01/05/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 184650 | 01507 | 990 | Solar | 05_01_612W3 | 05/11/2018 | 05/11/2018 | 1 | 0 | 1 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 06/05/2018 | 06/14/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINCHENDON | 239803 | 01475 | 6 | Solar | 05_05_19W72 | 06/26/2019 | 07/08/2019 | 7 | 3 | 4 | 07/09/2019 | 07/09/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 | 06/26/2019 | 6/26/2020 | Y | EXP | 365 | 11/07/2019 | 12/19/2019 | 42 | 0 | 42 |  |  | 1/21/2020 | Connected |  | N
National Grid | SOMERSET | 240171 | 02726 | 10 | Solar | 05_12_35J2 | 07/11/2019 | 07/19/2019 | 6 | 6 | 0 | 07/22/2019 | 07/22/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 11/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2019 | Connected |  | N
National Grid | REVERE | 705483 | 02151 | 8.32 | Solar | 05_14_18L1 | 07/17/2025 | 08/15/2025 | 8 | 2 | 6 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | BILLERICA | 660965 | 01821 | 3.8 | Solar | 05_14_48L2 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | HAVERHILL | 604796 | 01830 | 0 | Battery Add-On | 05_14_62L2 | 04/22/2024 | 05/20/2024 | 21 | 20 | 1 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177396 | 01810 | 6 | Solar | 05_14_75L6 | 02/21/2017 | 02/21/2017 | 6 | 1 | 5 | 03/01/2017 | 03/01/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2017 | 02/21/2017 | 2/26/2018 | Y | EXP | 36 | 10/16/2017 | 10/20/2017 | 4 | 0 | 4 | 6/27/2017 | 6/27/2017 | 11/2/2017 | Connected |  | N
National Grid | METHUEN | 537573 | 01844 | 50 | Solar | 05_01_225W1 | 06/28/2023 | 01/07/2024 | 130 | 120 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOLTON | 175160 | 01740 | 3000 | Solar | 05_01_304W5 | 08/04/2011 | 08/04/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2011 | 02/24/2012 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/04/2011 | 12/31/2012 | Y | STD | 73 | 11/13/2013 | 03/12/2014 | 80 | 0 | 80 | 2/28/2014 | 2/28/2014 | 3/6/2014 | Connected |  | N
National Grid | SUTTON | 743675 | 01590 | 20.52 | Solar | 05_01_415L2 | 01/06/2026 | 01/12/2026 | 2 | 2 | 0 | 01/13/2026 | 01/13/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHARLTON | 192506 | 01507 | 6.4 | Solar | 05_01_612W3 | 09/17/2018 | 12/14/2018 | 11 | 11 | 0 | 11/05/2018 | 11/05/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 11/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2019 | Connected |  | N
National Grid | WINCHENDON | 278585 | 01475 | 7.6 | Solar | 05_05_19W72 | 04/14/2020 | 04/16/2020 | 2 | 2 | 0 | 04/17/2020 | 04/17/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2020 | 04/14/2020 | 4/15/2021 | Y | EXP | 365 | 06/24/2020 | 08/27/2020 | 64 | 0 | 64 |  |  | 10/5/2020 | Connected |  | Y
National Grid | SOMERSET | 298672 | 02726 | 4.32 | Solar | 05_12_35J2 | 07/10/2020 | 07/17/2020 | 4 | 0 | 4 | 07/20/2020 | 07/20/2020 | 75 | 49 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2020 |  | 3/29/2022 | N | EXP | 545 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 736074 | 02151 | 3.8 | Solar | 05_14_18L2 | 11/24/2025 | 01/06/2026 | 3 | 0 | 3 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 682063 | 01821 | 5.76 | Solar | 05_14_48L2 | 04/01/2025 | 06/10/2025 | 28 | 24 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 | 04/01/2025 | 7/18/2026 | Y | EXP | 365 | 11/21/2025 | 11/21/2025 | 1 | 0 | 1 |  |  | 12/9/2025 | Connected |  | N
National Grid | HAVERHILL | 670001 | 01830 | 5.76 | Solar | 05_14_62L2 | 02/11/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 145 | 127 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 177646 | 01810 | 11.4 | Solar | 05_14_75L6 | 09/26/2017 | 09/26/2017 | 7 | 7 | 0 | 10/06/2017 | 10/06/2017 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 10/2/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 5/17/2018 | Connected |  | N
National Grid | METHUEN | 569141 | 01844 | 7.6 | Solar | 05_01_225W1 | 11/14/2023 | 11/27/2023 | 2 | 0 | 2 | 11/28/2023 | 11/28/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2024 | 11/14/2023 | 1/11/2025 | Y | EXP | 365 | 02/17/2024 | 03/19/2024 | 32 | 0 | 32 |  |  | 4/16/2024 | Connected |  | N
National Grid | LANCASTER | 175680 | 01523 | 97.5 | Solar | 05_01_304W5 | 12/19/2014 | 12/19/2014 | 5 | 0 | 5 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2015 | 12/19/2014 | 12/31/2016 | Y | EXP | 719 | 12/10/2015 | 01/19/2016 | 25 | 0 | 25 | 4/1/2015 | 4/1/2015 | 4/8/2016 | Connected |  | N
National Grid | MILLBURY | 749797 | 01527 | 15.2 | Solar | 05_01_415L2 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/11/2026 | 02/11/2026 | 16 | 10 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 256917 | 01507 | 7.6 | Solar | 05_01_612W3 | 09/27/2019 | 10/01/2019 | 1 | 0 | 1 | 10/02/2019 | 10/02/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | N
National Grid | WINCHENDON | 289859 | 01475 | 10 | Solar | 05_05_19W72 | 06/19/2020 | 07/21/2020 | 21 | 17 | 4 | 07/22/2020 | 07/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 06/19/2020 | 8/1/2021 | Y | EXP | 365 | 01/06/2021 | 02/23/2021 | 48 | 0 | 48 |  |  | 3/9/2021 | Connected |  | N
National Grid | SOMERSET | 457238 | 02726 | 7.6 | Solar | 05_12_35J2 | 09/07/2022 | 09/09/2022 | 2 | 0 | 2 | 09/12/2022 | 09/12/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 11/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | REVERE | 751755 | 02151 | 15.76 | Solar | 05_14_18L2 | 02/18/2026 | 02/20/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 698019 | 01821 | 4.48 | Solar | 05_14_48L2 | 06/12/2025 | 07/29/2025 | 2 | 0 | 2 | 08/11/2025 | 08/11/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 702798 | 01830 | 3 | Solar | 05_14_63L1 | 07/07/2025 | 07/23/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 56 | 44 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 177837 | 01810 | 15.2 | Solar | 05_14_75L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | DRACUT | 574015 | 01826 | 0 | Battery Add-On | 05_01_225W1 | 11/28/2023 | 12/05/2023 | 6 | 5 | 1 | 12/06/2023 | 12/06/2023 | 78 | 62 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | BOLTON | 176351 | 01740 | 7 | Solar | 05_01_304W5 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 575 | 03/17/2016 | 03/25/2016 | 5 | 0 | 5 | 5/10/2016 | 5/10/2016 | 5/12/2016 | Connected |  | N
National Grid | MILLBURY | 751116 | 01527 | 10 | Solar | 05_01_415L2 | 02/13/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHARLTON | 581103 | 01507 | 7.6 | Solar | 05_01_612W3 | 01/25/2024 | 01/29/2024 | 3 | 1 | 2 | 01/30/2024 | 01/30/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/25/2024 | 3/19/2025 | Y | EXP | 365 | 05/21/2024 | 05/20/2024 | 0 | 0 | 0 |  |  | 6/10/2024 | Connected |  | N
National Grid | WINCHENDON | 300899 | 01475 | 10 | Solar | 05_05_19W72 | 09/25/2020 | 11/03/2020 | 26 | 24 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 09/25/2020 | 11/3/2021 | Y | EXP | 365 | 02/05/2021 | 04/06/2021 | 60 | 0 | 60 |  |  | 4/8/2021 | Connected |  | N
National Grid | SOMERSET | 487786 | 02726 | 6 | Solar | 05_12_35J2 | 01/11/2023 | 01/12/2023 | 2 | 1 | 1 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | REVERE | 176623 | 02151 | 3 | Solar | 05_14_18L2 | 04/14/2016 | 04/14/2016 | 2 | 2 | 0 | 04/19/2016 | 04/19/2016 | 144 | 0 | 144 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 4/19/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 707779 | 01821 | 6.08 | Solar | 05_14_48L2 | 07/30/2025 | 08/04/2025 | 3 | 0 | 3 | 08/05/2025 | 08/05/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | HAVERHILL | 710704 | 01830 | 15.32 | Solar | 05_14_63L1 | 08/08/2025 | 08/15/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 192225 | 01844 | 7.6 | Solar | 05_14_75L6 | 07/30/2018 | 09/19/2018 | 2 | 0 | 2 | 09/20/2018 | 09/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 582536 | 01844 | 24.375 | Solar | 05_01_225W1 | 01/12/2024 | 01/17/2024 | 3 | 1 | 2 | 01/18/2024 | 01/18/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | BOLTON | 176378 | 01740 | 16 | Solar | 05_01_304W5 | 11/20/2015 | 11/20/2015 | 1 | 1 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2015 |  | 11/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/2/2016 | 3/2/2016 | 3/9/2016 | Connected |  | N
National Grid | MILLBURY | 174193 | 01527 | 14.19 | Solar | 05_01_415L2 | 03/16/2012 | 03/16/2012 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2012 |  | 4/19/2012 | N | EXP | 53 |  |  | 0 | 0 | 0 | 6/11/2012 | 6/11/2012 | 8/3/2012 | Connected |  | N
National Grid | CHARLTON | 663132 | 01507 | 7.25 | Solar | 05_01_612W3 | 12/31/2024 | 01/08/2025 | 4 | 2 | 2 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/31/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | WINCHENDON | 330085 | 01475 | 6 | Solar | 05_05_19W72 | 01/05/2021 | 01/07/2021 | 1 | 0 | 1 | 01/08/2021 | 01/08/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 | 01/05/2021 |  | Y | EXP | 365 | 05/27/2021 | 07/08/2021 | 42 | 0 | 42 |  |  | 8/6/2021 | Connected |  | N
National Grid | SOMERSET | 684658 | 02726 | 3.8 | Solar | 05_12_35J2 | 04/11/2025 | 05/05/2025 | 1 | 0 | 1 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/11/2025 | 6/9/2026 | Y | EXP | 365 | 10/03/2025 | 12/02/2025 | 61 | 0 | 61 |  |  | 12/3/2025 | Connected |  | N
National Grid | REVERE | 177548 | 02151 | 11.4 | Solar | 05_14_18L2 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/28/2017 | 11/28/2017 | 11/28/2017 | Connected |  | N
National Grid | BILLERICA | 177399 | 01821 | 75 | Solar | 05_14_48L3 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 | 06/29/2016 | 06/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 06/28/2016 | 7/5/2017 | Y | EXP | 31 | 08/03/2016 | 09/21/2016 | 34 | 0 | 34 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | HAVERHILL | 717012 | 01830 | 10 | Solar | 05_14_63L1 | 09/05/2025 | 09/16/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 447195 | 01844 | 10 | Solar | 05_14_75L6 | 08/02/2022 | 08/03/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 601438 | 01844 | 0 | Solar | 05_01_225W1 | 04/03/2024 | 05/02/2024 | 21 | 19 | 2 | 05/03/2024 | 05/03/2024 | 91 | 88 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | HARVARD | 176403 | 01451 | 3.8 | Solar | 05_01_304W5 | 03/11/2016 | 03/11/2016 | 3 | 3 | 0 | 03/17/2016 | 03/17/2016 | 234 | 0 | 234 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 |  | 3/19/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 174546 | 01527 | 2000 | Solar | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | 16 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | CHARLTON | 690406 | 01507 | 7.6 | Solar | 05_01_612W3 | 05/07/2025 | 06/05/2025 | 4 | 0 | 4 | 06/25/2025 | 06/25/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINCHENDON | 331847 | 01475 | 8.75 | Solar | 05_05_19W72 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 | 01/04/2021 |  | Y | EXP | 365 | 08/03/2021 | 08/17/2021 | 15 | 0 | 15 |  |  | 8/26/2021 | Connected |  | N
National Grid | SOMERSET | 173414 | 02726 | 7.6 | Solar | 05_12_35J3 | 04/11/2018 | 04/11/2018 | 0 | 0 | 0 | 05/09/2018 | 05/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 189415 | 02151 | 15.2 | Solar | 05_14_18L2 | 06/27/2018 | 06/27/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 2/21/2020 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | BILLERICA | 196416 | 01821 | 66.6 | Solar | 05_14_48L3 | 09/19/2018 | 10/08/2018 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 7/1/2020 | N | EXP | 46 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 722551 | 01830 | 5.584 | Solar | 05_14_63L1 | 09/29/2025 | 10/07/2025 | 2 | 0 | 2 | 10/08/2025 | 10/08/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 457130 | 01844 | 0 | Other | 05_14_75L6 | 11/15/2022 | 02/08/2023 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2023 | 03/29/2023 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 612134 | 01826 | 50 | Solar | 05_01_225W1 | 05/20/2024 | 05/21/2024 | 1 | 0 | 1 | 05/22/2024 | 05/22/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 7/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2024 | Connected |  | N
National Grid | HARVARD | 178381 | 01451 | 8.96 | Solar | 05_01_304W5 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 02/27/2018 | 02/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 1/21/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 7/31/2018 | Connected |  | N
National Grid | MILLBURY | 174545 | 01527 | 2000 | Solar | 05_01_415L2 | 11/08/2011 | 11/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2013 | 04/16/2013 | 0 | 0 | 0 | 4/9/2013 | 11/08/2011 | 10/31/2012 | Y | STD | 16 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | CHARLTON | 653327 | 01507 | 10 | Solar | 05_01_6J304 | 11/08/2024 | 11/27/2024 | 1 | 0 | 1 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | Y
National Grid | WINCHENDON | 341066 | 01475 | 10 | Solar | 05_05_19W72 | 03/04/2021 | 03/10/2021 | 4 | 1 | 3 | 03/11/2021 | 03/11/2021 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/04/2021 |  | Y | EXP | 365 | 06/04/2021 | 06/03/2021 | 0 | 0 | 0 |  |  | 7/28/2021 | Connected |  | N
National Grid | SOMERSET | 175520 | 02726 | 266 | Solar | 05_12_35J3 | 04/09/2014 | 04/09/2014 | 10 | 4 | 6 | 04/25/2014 | 04/25/2014 | 608 | 2 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2014 | 04/09/2014 | 2/4/2016 | Y | EXP | 639 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 225966 | 02151 | 6 | Solar | 05_14_18L2 | 05/09/2019 | 05/13/2019 | 2 | 1 | 1 | 05/14/2019 | 05/14/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/09/2019 | 7/31/2020 | Y | EXP | 365 | 04/15/2020 | 04/16/2020 | 1 | 0 | 1 |  |  | 4/20/2020 | Connected |  | N
National Grid | BILLERICA | 413354 | 01821 | 3.8 | Solar | 05_14_48L3 | 02/25/2022 | 03/01/2022 | 2 | 0 | 2 | 03/02/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2022 | Connected |  | N
National Grid | HAVERHILL | 722050 | 01830 | 0 | Battery Add-On | 05_14_63L1 | 10/15/2025 | 10/31/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 512343 | 01844 | 5.76 | Solar | 05_14_75L6 | 03/17/2023 | 07/23/2024 | 5 | 3 | 2 | 07/24/2024 | 07/24/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | DRACUT | 631386 | 01826 | 0 | Battery Add-On | 05_01_225W1 | 08/09/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 08/09/2024 | 10/13/2025 | Y | EXP | 45 | 01/07/2025 | 12/22/2025 | 350 | 0 | 350 |  |  | 11/21/2025 | Connected |  | N
National Grid | LANCASTER | 178488 | 01523 | 499.5 | Solar | 05_01_304W5 | 12/01/2017 | 01/23/2018 | 36 | 13 | 23 |  |  | 51 | 51 | 0 | 02/27/2018 | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 03/12/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 8/20/2020 | 12/01/2017 | 9/28/2022 | Y | STD | 55 |  |  | 0 | 0 | 0 |  |  | 9/27/2022 | Connected |  | N
National Grid | MILLBURY | 175243 | 01527 | 17 | Solar | 05_01_415L2 | 08/25/2014 | 08/25/2014 | 7 | 0 | 7 | 09/05/2014 | 09/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/25/2014 | 12/10/2014 | Y | EXP | 7 | 01/14/2015 | 01/06/2015 | 0 | 0 | 0 | 1/13/2015 | 1/13/2015 | 3/6/2015 | Connected |  | N
National Grid | CHARLTON | 728152 | 01507 | 7.98 | Solar | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 7 | 6 | 1 | 12/24/2025 | 12/24/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 387698 | 01603 | 10 | Solar | 05_05_19W72 | 10/15/2021 | 12/29/2021 | 3 | 0 | 3 | 10/21/2021 | 10/21/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 10/15/2021 | 8/18/2023 | Y | EXP | 365 | 05/14/2022 | 07/13/2022 | 61 | 0 | 61 |  |  | 9/23/2022 | Connected |  | N
National Grid | SOMERSET | 177083 | 02726 | 750 | Solar | 05_12_35J3 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/09/2017 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 372933 | 02151 | 7.6 | Solar | 05_14_18L2 | 08/06/2021 | 08/09/2021 | 2 | 1 | 1 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/06/2021 | 3/29/2023 | Y | EXP | 365 | 01/19/2022 | 02/11/2022 | 24 | 0 | 24 |  |  | 12/17/2022 | Connected |  | N
National Grid | BILLERICA | 618825 | 01821 | 7.6 | Solar | 05_14_48L3 | 06/18/2024 | 06/24/2024 | 2 | 0 | 2 | 07/07/2025 | 07/07/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 06/18/2024 | 8/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | HAVERHILL | 725342 | 01830 | 3.8 | Solar | 05_14_63L1 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 51 | 34 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 | 10/09/2025 | 12/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 524863 | 01841 | 7.68 | Solar | 05_14_75L6 | 05/22/2023 | 05/23/2023 | 1 | 0 | 1 | 05/24/2023 | 05/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | Y
National Grid | METHUEN | 635160 | 01844 | 9.88 | Solar | 05_01_225W1 | 08/26/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 10/6/2025 | Y | EXP | 365 | 11/07/2024 | 11/19/2024 | 13 | 0 | 13 |  |  | 2/13/2025 | Connected |  | N
National Grid | BOLTON | 178572 | 01740 | 4980 | Solar | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2018 | 03/07/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2018 | 12/08/2017 | 10/28/2022 | Y | STD | 553 | 01/22/2022 | 05/03/2022 | 102 | 0 | 102 | 9/21/2022 | 10/19/2022 | 10/26/2022 | Connected |  | N
National Grid | MILLBURY | 175323 | 01527 | 630 | Solar | 05_01_415L2 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/19/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 728147 | 01507 | 6.84 | Solar | 05_01_6J312 | 10/21/2025 | 10/26/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | WORCESTER | 484722 | 01610 | 7.6 | Solar | 05_05_19W72 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 215113 | 02726 | 7.6 | Solar | 05_12_35J3 | 05/15/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 59 | 48 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 10/23/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 413120 | 02151 | 15.2 | Solar | 05_14_18L2 | 02/18/2022 | 02/24/2022 | 4 | 2 | 2 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2022 | Connected |  | N
National Grid | BILLERICA | 669659 | 01821 | 0 | Battery Add-On | 05_14_48L3 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 59 | 38 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | HAVERHILL | 738581 | 01830 | 11.5 | Solar | 05_14_63L1 | 12/08/2025 | 12/19/2025 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | METHUEN | 558735 | 01844 | 350 | Solar | 05_14_75L6 | 12/04/2023 | 01/04/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2024 | 01/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 641650 | 01844 | 7.6 | Solar | 05_01_225W1 | 11/13/2024 | 12/05/2024 | 9 | 5 | 4 | 12/06/2024 | 12/06/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | LANCASTER | 178571 | 01523 |  | Solar | 05_01_304W5 | 12/08/2017 | 12/08/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/16/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 175578 | 01527 | 30 | Solar | 05_01_415L2 | 12/09/2014 | 12/09/2014 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 670775 | 01507 | 7.6 | Solar | 05_01_6J312 | 02/07/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2025 | Connected |  | N
National Grid | WORCESTER | 565151 | 01610 | 13.262 | Solar | 05_05_19W72 | 11/15/2023 | 12/06/2023 | 15 | 13 | 2 | 12/07/2023 | 12/07/2023 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 | 11/15/2023 | 2/6/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | DIGHTON | 231907 | 02715 | 5 | Solar | 05_12_35J3 | 05/30/2019 | 06/26/2019 | 4 | 4 | 0 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 653923 | 02151 | 3.8 | Solar | 05_14_18L2 | 11/18/2024 | 12/17/2024 | 6 | 0 | 6 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2025 | Connected |  | N
National Grid | BILLERICA | 691118 | 01821 | 13.8 | Solar | 05_14_48L3 | 05/15/2025 | 05/20/2025 | 3 | 0 | 3 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | HAVERHILL | 175873 | 01830 | 16 | Solar | 05_14_63L1 | 03/09/2015 | 03/09/2015 | 11 | 9 | 2 | 03/26/2015 | 03/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 8/10/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 7/21/2015 | 7/21/2015 | 12/9/2015 | Connected |  | N
National Grid | METHUEN | 597814 | 01844 | 14.3 | Solar | 05_14_75L6 | 03/28/2024 | 04/02/2024 | 4 | 2 | 2 | 04/03/2024 | 04/03/2024 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/28/2024 | 8/11/2025 | Y | EXP | 365 | 02/15/2025 | 03/14/2025 | 28 | 0 | 28 |  |  | 4/4/2025 | Connected |  | N
National Grid | METHUEN | 644960 | 01844 | 8.12 | Solar | 05_01_225W1 | 10/03/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2025 | Connected |  | N
National Grid | LANCASTER | 178681 | 01523 | 4950 | Solar | 05_01_304W5 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 139 | 119 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176201 | 01527 | 2000 | Solar | 05_01_415L2 | 02/11/2015 | 02/11/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 | 12/11/2015 | 02/11/2015 | 2/8/2018 | Y | STD | 79 | 03/20/2018 | 03/20/2018 | 0 | 0 | 0 | 12/13/2017 | 12/13/2017 | 12/31/2017 | Connected |  | N
National Grid | CHARLTON | 187209 | 01507 | 200 | Solar | 05_01_6J316 | 06/05/2018 | 06/05/2018 | 3 | 0 | 3 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 590736 | 01603 | 3.8 | Solar | 05_05_19W72 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 02/22/2024 | 4/4/2025 | Y | EXP | 365 | 05/11/2024 | 05/10/2024 | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | SOMERSET | 270600 | 02726 | 3.8 | Solar | 05_12_35J3 | 01/21/2020 | 03/09/2020 | 32 | 29 | 3 | 03/10/2020 | 03/10/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2020 | 01/21/2020 | 11/1/2022 | Y | EXP | 935 | 10/03/2020 | 12/15/2020 | 73 | 0 | 73 |  |  | 10/26/2022 | Connected |  | N
National Grid | REVERE | 660841 | 02151 | 10 | Solar | 05_14_18L2 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/20/2026 | N | EXP | 365 | 02/21/2025 | 04/16/2025 | 55 | 0 | 55 |  |  | 4/24/2025 | Connected |  | N
National Grid | BILLERICA | 685494 | 01821 | 180 | Solar | 05_14_48L4 | 04/16/2025 | 05/23/2025 | 26 | 17 | 9 | 05/27/2025 | 05/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 04/16/2025 | 6/3/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 176711 | 01830 | 6 | Solar | 05_14_63L1 | 01/07/2016 | 01/07/2016 | 10 | 10 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/13/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 | 5/4/2016 | 5/4/2016 | 5/9/2016 | Connected |  | N
National Grid | METHUEN | 618488 | 01844 | 7.6 | Solar | 05_14_75L6 | 06/28/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | METHUEN | 646978 | 01844 | 10 | Solar | 05_01_225W1 | 10/29/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | BOLTON | 193416 | 01740 | 24 | Solar | 05_01_304W5 | 08/14/2018 | 09/04/2018 | 13 | 0 | 13 | 09/05/2018 | 09/05/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2018 | 08/14/2018 |  | Y | EXP | 427 | 08/21/2019 | 09/11/2019 | 21 | 0 | 21 |  |  | 12/5/2019 | Connected |  | N
National Grid | SUTTON | 176243 | 01590 | 275 | Solar | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/19/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 |  | 10/30/2015 | N | STD | 255 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 599616 | 01507 | 7.6 | Solar | 05_01_6J316 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 96 | 25 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 609919 | 01603 | 6 | Solar | 05_05_19W72 | 05/09/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 59 | 50 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 294945 | 02726 | 10 | Solar | 05_12_35J3 | 06/15/2020 | 06/18/2020 | 2 | 0 | 2 | 06/19/2020 | 06/19/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/15/2020 | 4/8/2022 | Y | EXP | 365 | 01/21/2021 | 02/18/2021 | 28 | 0 | 28 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 669702 | 02151 | 1.74 | Solar | 05_14_18L2 | 02/04/2025 | 02/07/2025 | 3 | 0 | 3 | 02/10/2025 | 02/10/2025 | 133 | 121 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 710023 | 01821 | 240 | Solar | 05_14_48L4 | 08/07/2025 | 09/16/2025 | 27 | 17 | 10 | 09/17/2025 | 09/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 08/07/2025 | 8/28/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 176841 | 01830 | 10 | Solar | 05_14_63L1 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/05/2016 | 05/05/2016 | 449 | 0 | 449 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 7/31/2018 | Y | EXP | 81 | 07/11/2017 | 07/28/2017 | 13 | 0 | 13 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 634167 | 01844 | 7.6 | Solar | 05_14_75L6 | 08/20/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | METHUEN | 648121 | 01844 | 9.88 | Solar | 05_01_225W1 | 10/18/2024 | 11/06/2024 | 13 | 10 | 3 | 11/07/2024 | 11/07/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | BOLTON | 199870 | 01740 | 10 | Solar | 05_01_304W5 | 10/31/2018 | 12/31/2018 | 3 | 1 | 2 | 01/02/2019 | 01/02/2019 | 52 | 47 | 5 | 05/13/2020 | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 06/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/31/2018 | 1/6/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | MILLBURY | 176242 | 01527 | 2000 | Solar | 05_01_415L2 | 04/29/2015 | 04/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 06/01/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/11/2016 | 07/11/2016 | 0 | 0 | 0 | 7/11/2016 | 04/29/2015 | 4/1/2018 | Y | STD | 629 | 07/31/2017 | 02/08/2018 | 126 | 0 | 126 | 3/15/2018 | 3/15/2018 | 3/15/2018 | Connected |  | N
National Grid | CHARLTON | 669726 | 01507 | 3.8 | Solar | 05_01_6J316 | 02/03/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | WORCESTER | 643901 | 01603 | 3.8 | Solar | 05_05_19W72 | 10/01/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 488509 | 02726 | 9.8 | Solar | 05_12_35J3 | 11/23/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/23/2024 | 2/24/2026 | Y | EXP | 365 | 06/12/2025 | 10/02/2025 | 113 | 0 | 113 |  |  | 10/16/2025 | Connected |  | N
National Grid | REVERE | 710356 | 02151 | 8.32 | Solar | 05_14_18L2 | 08/08/2025 | 08/28/2025 | 3 | 2 | 1 | 09/19/2025 | 09/19/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 735933 | 01821 | 10 | Solar | 05_14_48L4 | 11/24/2025 | 11/25/2025 | 2 | 0 | 2 | 12/16/2025 | 12/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 |  | 12/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 177252 | 01832 | 6 | Solar | 05_14_63L1 | 06/14/2016 | 06/14/2016 | 2 | 2 | 0 | 06/17/2016 | 06/17/2016 | 157 | 0 | 157 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 |  | 6/20/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 637971 | 01844 | 7.6 | Solar | 05_14_75L6 | 09/09/2024 | 09/30/2024 | 6 | 5 | 1 | 10/01/2024 | 10/01/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 651005 | 01826 | 7.6 | Solar | 05_01_225W1 | 11/12/2024 | 12/27/2024 | 24 | 20 | 4 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 | 02/27/2025 | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 03/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | BOLTON | 229816 | 01740 | 10 | Solar | 05_01_304W5 | 05/21/2019 | 05/30/2019 | 5 | 0 | 5 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | MILLBURY | 176331 | 01527 | 40 | Solar | 05_01_415L2 | 07/21/2015 | 07/21/2015 | 3 | 3 | 0 | 07/27/2015 | 07/27/2015 | 388 | 0 | 388 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 |  | 7/27/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/7/2015 | 8/7/2015 |  | Withdrawn |  | Y
National Grid | CHARLTON | 710713 | 01507 | 7.6 | Solar | 05_01_6J316 | 08/08/2025 | 09/02/2025 | 1 | 0 | 1 | 09/17/2025 | 09/17/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 679843 | 01603 | 20 | Solar | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 | 03/25/2025 | 6/8/2026 | Y | EXP | 365 | 07/01/2025 | 07/29/2025 | 29 | 0 | 29 |  |  | 8/13/2025 | Connected |  | N
National Grid | DIGHTON | 499811 | 02715 | 50 | Solar | 05_12_35J3 | 02/17/2023 | 05/10/2023 | 56 | 48 | 8 | 05/11/2023 | 05/11/2023 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | REVERE | 690634 | 02151 | 10 | Solar | 05_14_18L3 | 05/08/2025 | 07/01/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 05/08/2025 | 9/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BILLERICA | 176406 | 01821 | 720 | Solar | 05_14_48L4 | 05/09/2016 | 05/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/11/2016 | 07/13/2016 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/16/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177425 | 01832 | 7.6 | Solar | 05_14_63L1 | 12/06/2016 | 12/06/2016 | 3 | 2 | 1 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 365 | 10/16/2017 | 11/16/2017 | 17 | 0 | 17 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | METHUEN | 645604 | 01844 | 11.4 | Solar | 05_14_75L6 | 10/08/2024 |  | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 650897 | 01844 | 11.5 | Solar | 05_01_225W1 | 10/30/2024 | 12/02/2024 | 13 | 10 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | BOLTON | 301583 | 01740 | 7.92 | Solar | 05_01_304W5 | 07/16/2020 | 08/04/2020 | 12 | 12 | 0 | 08/05/2020 | 08/05/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 8/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | MILLBURY | 176584 | 01527 | 9.5 | Solar | 05_01_415L2 | 04/07/2016 | 04/07/2016 | 31 | 31 | 0 | 05/24/2016 | 05/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 04/07/2016 | 4/13/2017 | Y | EXP | 311 | 11/30/2016 | 12/08/2016 | 6 | 0 | 6 | 5/10/2017 | 5/10/2017 | 5/15/2017 | Connected |  | N
National Grid | CHARLTON | 661862 | 01507 | 5.76 | Solar | 05_01_6J318 | 12/19/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WORCESTER | 680454 | 01603 | 17.16 | Solar | 05_05_19W72 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 24 | 1 | 23 | 05/07/2025 | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 05/19/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 7/10/2026 | N | EXP | 365 | 08/21/2025 | 09/03/2025 | 14 | 0 | 14 |  |  | 9/12/2025 | Connected |  | N
National Grid | DIGHTON | 537998 | 02715 | 2.32 | Solar | 05_12_35J3 | 06/30/2023 | 07/05/2023 | 2 | 0 | 2 | 07/06/2023 | 07/06/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 732460 | 02151 | 3.8 | Solar | 05_14_18L3 | 11/10/2025 | 11/12/2025 | 1 | 0 | 1 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 176573 | 01821 | 1462 | Solar | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 177824 | 01832 | 9.6 | Solar | 05_14_63L1 | 06/06/2017 | 06/06/2017 | 3 | 3 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/06/2017 | 6/13/2018 | Y | EXP | 365 | 08/08/2017 | 08/16/2017 | 6 | 0 | 6 | 2/14/2018 | 2/14/2018 | 2/20/2018 | Connected |  | N
National Grid | METHUEN | 652506 | 01844 | 12.18 | Solar | 05_14_75L6 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | METHUEN | 655903 | 01844 | 15 | Solar | 05_01_225W1 | 11/21/2024 | 12/02/2024 | 3 | 1 | 2 | 12/03/2024 | 12/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | HARVARD | 303514 | 01451 | 0 | Other | 05_01_304W5 | 09/15/2020 | 10/09/2020 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 | 11/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 |  | Y | STD | 539 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 176600 | 01527 | 1000 | Solar | 05_01_415L2 | 12/29/2015 | 12/29/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2016 | 01/12/2016 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 03/29/2016 | 07/05/2016 | 66 | 17 | 49 | 7/19/2016 | 12/29/2015 | 1/4/2017 | Y | STD | 169 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/8/2017 | Connected |  | N
National Grid | CHARLTON | 726459 | 01507 | 10 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 694616 | 01603 | 5.76 | Solar | 05_05_19W72 | 05/29/2025 | 06/18/2025 | 3 | 0 | 3 | 06/20/2025 | 06/20/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 601237 | 02726 | 5 | Solar | 05_12_35J3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/09/2024 | 6/4/2025 | Y | EXP | 365 | 09/27/2024 | 11/26/2024 | 61 | 0 | 61 |  |  | 1/30/2025 | Connected |  | N
National Grid | REVERE | 175826 | 02151 | 7.6 | Solar | 05_14_18L3 | 09/18/2015 | 09/18/2015 | 3 | 3 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 09/18/2015 | 9/26/2016 | Y | EXP | 35 | 04/04/2016 | 05/13/2016 | 28 | 0 | 28 | 5/4/2016 | 5/4/2016 | 6/17/2016 | Connected |  | N
National Grid | BILLERICA | 176616 | 01862 | 1335.6 | Solar | 05_14_48L4 | 02/11/2016 | 02/11/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/22/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2016 |  | 2/22/2017 | N | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 178126 | 01832 | 7.6 | Solar | 05_14_63L1 | 07/11/2017 | 07/11/2017 | 3 | 3 | 0 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2017 |  | 7/17/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/18/2017 | Connected |  | N
National Grid | METHUEN | 654188 | 01844 | 7.6 | Solar | 05_14_75L6 | 11/18/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/12/2026 | Y | EXP | 365 | 05/07/2025 | 07/10/2025 | 65 | 0 | 65 |  |  | 7/25/2025 | Connected |  | N
National Grid | METHUEN | 665518 | 01844 | 20 | Solar | 05_01_225W1 | 01/14/2025 | 01/16/2025 | 2 | 0 | 2 | 01/17/2025 | 01/17/2025 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LANCASTER | 311604 | 01532 | 19 | Solar | 05_01_304W5 | 09/09/2020 | 09/14/2020 | 3 | 3 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 09/09/2020 | 6/2/2022 | Y | EXP | 475 | 01/12/2021 | 02/05/2021 | 24 | 0 | 24 |  |  | 4/22/2022 | Connected |  | N
National Grid | MILLBURY | 177235 | 01527 | 54.2 | Solar | 05_01_415L2 | 11/07/2016 | 11/07/2016 | 2 | 2 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2017 |  | 11/13/2017 | N | EXP | 37 |  |  | 0 | 0 | 0 | 5/24/2017 | 5/24/2017 | 5/24/2017 | Connected |  | N
National Grid | CHARLTON | 726456 | 01507 | 13.8 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 704382 | 01603 | 10 | Solar | 05_05_19W72 | 07/11/2025 | 07/28/2025 | 4 | 0 | 4 | 09/03/2025 | 09/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | SOMERSET | 641513 | 02726 | 10 | Solar | 05_12_35J3 | 09/19/2024 | 10/10/2024 | 7 | 6 | 1 | 10/11/2024 | 10/11/2024 | 69 | 45 | 24 | 02/24/2025 | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 |  | 08/05/2025 | 112 | 25 | 87 |  |  | 0 | 0 | 0 | 8/8/2025 | 09/19/2024 | 8/18/2026 | Y | EXP | 365 | 11/04/2025 | 01/27/2026 | 85 | 0 | 85 |  |  | 12/10/2025 | Connected |  | N
National Grid | REVERE | 176859 | 02151 | 30 | Hydrogen | 05_14_18L3 | 01/20/2016 | 01/20/2016 | 1 | 1 | 0 | 01/21/2016 | 01/21/2016 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 11/16/2020 | N | EXP | 1358 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | BILLERICA | 184579 | 01821 | 37.6 | Solar | 05_14_48L4 | 05/07/2018 | 05/07/2018 | 0 | 0 | 0 | 05/17/2018 | 05/17/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 188740 | 01832 | 7.6 | Solar | 05_14_63L1 | 07/10/2018 | 09/04/2018 | 39 | 33 | 6 | 12/17/2018 | 12/17/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 07/10/2018 | 2/18/2020 | Y | EXP | 365 | 05/21/2019 | 07/12/2019 | 52 | 0 | 52 |  |  | 1/10/2020 | Connected |  | N
National Grid | METHUEN | 654316 | 01844 | 8.91 | Solar | 05_14_75L6 | 11/14/2024 | 12/17/2024 | 10 | 6 | 4 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/14/2024 | 2/19/2026 | Y | EXP | 365 | 04/16/2025 |  | 325 | 0 | 325 |  |  | 3/28/2025 | Connected |  | N
National Grid | METHUEN | 665398 | 01844 | 3.8 | Solar | 05_01_225W1 | 01/14/2025 | 02/10/2025 | 6 | 2 | 4 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | LANCASTER | 319874 | 01523 | 15.2 | Solar | 05_01_304W5 | 10/16/2020 | 10/23/2020 | 4 | 4 | 0 | 10/26/2020 | 10/26/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2020 | 10/16/2020 | 3/26/2022 | Y | EXP | 365 | 03/05/2021 | 03/16/2021 | 11 | 0 | 11 |  |  | 9/10/2021 | Connected |  | N
National Grid | SUTTON | 177317 | 01590 | 1393 | Solar | 05_01_415L2 | 02/14/2017 | 03/10/2017 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2017 | 04/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 5/29/2020 | N | STD | 651 | 06/08/2019 | 11/21/2019 | 166 | 0 | 166 |  |  | 6/5/2020 | Connected |  | N
National Grid | CHARLTON | 726402 | 01507 | 10 | Solar | 05_01_6J319 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 721805 | 01603 | 17.1 | Solar | 05_05_19W72 | 09/25/2025 | 09/29/2025 | 2 | 0 | 2 | 09/30/2025 | 09/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | SOMERSET | 200545 | 02726 | 10 | Solar | 05_12_35J4 | 11/08/2018 | 11/28/2018 | 6 | 3 | 3 | 11/29/2018 | 11/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 177535 | 02151 | 999 | Solar | 05_14_18L3 | 09/14/2017 | 09/14/2017 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 11/09/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 9/19/2019 | N | STD | 458 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 191108 | 01821 | 52.2 | Solar | 05_14_48L4 | 07/18/2018 | 08/06/2018 | 13 | 11 | 2 | 08/07/2018 | 08/07/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 194880 | 01830 | 3.8 | Solar | 05_14_63L1 | 08/31/2018 | 10/30/2018 | 7 | 0 | 7 | 10/31/2018 | 10/31/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 657523 | 01844 | 5.76 | Solar | 05_14_75L6 | 11/28/2024 | 12/17/2024 | 3 | 0 | 3 | 12/18/2024 | 12/18/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | METHUEN | 665152 | 01844 | 7.6 | Solar | 05_01_225W1 | 01/13/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 324458 | 01523 | 0 | Solar | 05_01_304W5 | 11/07/2020 | 11/10/2020 | 1 | 0 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 2/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 177363 | 01527 | 6.67 | Solar | 05_01_415L2 | 06/23/2016 | 06/23/2016 | 7 | 7 | 0 | 07/07/2016 | 07/07/2016 | 145 | 0 | 145 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/2/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174966 | 01507 | 154 | Solar | 05_01_6J319 | 09/03/2013 | 09/03/2013 | 9 | 0 | 9 | 09/17/2013 | 09/17/2013 | 353 | 3 | 350 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2013 |  | 8/1/2014 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 557478 | 01603 | 2512 | Solar | 05_05_19W73 | 12/07/2023 | 01/18/2024 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2024 | 05/24/2024 | 89 | 70 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SOMERSET | 314661 | 02726 | 3.8 | Solar | 05_12_35J4 | 10/01/2020 | 10/05/2020 | 1 | 0 | 1 | 10/06/2020 | 10/06/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 | 10/01/2020 | 11/5/2021 | Y | EXP | 365 | 01/21/2021 | 04/08/2021 | 77 | 0 | 77 |  |  | 7/14/2021 | Connected |  | N
National Grid | REVERE | 254107 | 02151 | 100 | Solar | 05_14_18L3 | 11/27/2019 | 12/13/2019 | 9 | 0 | 9 | 12/16/2019 | 12/16/2019 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2020 | 11/27/2019 |  | Y | EXP | 365 | 08/04/2020 | 08/27/2020 | 23 | 0 | 23 |  |  | 9/21/2020 | Connected |  | N
National Grid | BILLERICA | 267314 | 01821 | 37.8 | Solar | 05_14_48L4 | 06/18/2020 | 07/13/2020 | 17 | 17 | 0 | 07/14/2020 | 07/14/2020 | 80 | 57 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2020 |  | 6/22/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | HAVERHILL | 198050 | 01830 | 5 | Solar | 05_14_63L1 | 10/09/2018 | 10/22/2018 | 7 | 6 | 1 | 10/23/2018 | 10/23/2018 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 | 10/09/2018 | 5/22/2019 | Y | EXP | 198 | 01/29/2019 | 02/05/2019 | 7 | 0 | 7 |  |  | 3/15/2019 | Connected |  | N
National Grid | METHUEN | 661225 | 01844 | 5.76 | Solar | 05_14_75L6 | 12/17/2024 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 | 12/17/2024 | 4/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | METHUEN | 666895 | 01844 | 20.48 | Solar | 05_01_225W1 | 01/28/2025 | 02/18/2025 | 14 | 11 | 3 | 02/19/2025 | 02/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | LANCASTER | 339473 | 01523 | 3.8 | Solar | 05_01_304W5 | 01/29/2021 | 03/30/2021 | 38 | 37 | 1 | 03/31/2021 | 03/31/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 01/29/2021 | 7/23/2022 | Y | EXP | 365 | 06/12/2021 | 07/06/2021 | 19 | 0 | 19 |  |  | 7/8/2022 | Connected |  | N
National Grid | SUTTON | 177552 | 01590 | 3500 | Solar | 05_01_415L2 | 05/15/2017 | 06/12/2017 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/14/2017 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2018 | 05/15/2017 | 12/20/2022 | Y | STD | 586 |  |  | 0 | 0 | 0 |  |  | 12/19/2022 | Connected |  | N
National Grid | CHARLTON | 363819 | 01507 | 100 | Solar | 05_01_6J319 | 12/29/2021 | 10/19/2022 | 202 | 202 | 0 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/29/2021 | 12/31/2024 | Y | STD | 13 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | WORCESTER | 733709 | 01610 | 3.8 | Solar | 05_05_19W73 | 11/13/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SWANSEA | 617299 | 02777 | 5.76 | Solar | 05_12_35J4 | 06/14/2024 | 07/16/2024 | 16 | 15 | 1 | 07/17/2024 | 07/17/2024 | 22 | 10 | 12 | 09/06/2024 | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 10/01/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 11/13/2025 | N | EXP | 365 | 02/26/2025 | 11/21/2025 | 269 | 0 | 269 |  |  | 12/6/2025 | Connected |  | N
National Grid | REVERE | 253359 | 02151 | 7.6 | Solar | 05_14_18L3 | 09/24/2019 | 09/25/2019 | 0 | 0 | 0 | 09/26/2019 | 09/26/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 438729 | 01821 | 6 | Solar | 05_14_48L4 | 06/29/2022 | 07/05/2022 | 3 | 0 | 3 | 07/06/2022 | 07/06/2022 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 | 06/29/2022 | 8/25/2023 | Y | EXP | 365 | 10/13/2022 | 10/25/2022 | 13 | 0 | 13 |  |  | 10/31/2022 | Connected |  | Y
National Grid | HAVERHILL | 204929 | 01832 | 7.6 | Solar | 05_14_63L1 | 02/06/2019 | 02/28/2019 | 14 | 7 | 7 | 03/01/2019 | 03/01/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 3/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2019 | Connected |  | N
National Grid | METHUEN | 661267 | 01844 | 2.32 | Solar | 05_14_75L6 | 12/17/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 2/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 670869 | 01844 | 5.76 | Solar | 05_01_225W1 | 02/07/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | BOLTON | 352535 | 01740 | 7.54 | Solar | 05_01_304W5 | 04/14/2021 | 04/15/2021 | 0 | 0 | 0 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 4/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2021 | Connected |  | N
National Grid | SUTTON | 177818 | 01590 | 13.76 | Solar | 05_01_415L2 | 04/04/2017 | 04/04/2017 | 218 | 216 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 650619 | 01507 | 10 | Solar | 05_01_6J319 | 10/30/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/30/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | WORCESTER | 738982 | 01610 | 10 | Solar | 05_05_19W73 | 12/09/2025 | 12/11/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 57 | 3 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 645906 | 02715 | 10 | Solar | 05_12_35J4 | 10/17/2024 | 12/12/2024 | 27 | 25 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 330833 | 02151 | 4125 | Solar | 05_14_18L3 | 12/17/2021 | 01/26/2022 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2022 | 03/02/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 488061 | 01821 | 7.6 | Solar | 05_14_48L4 | 02/24/2023 | 01/01/2023 | 3 | 0 | 3 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/1/2023 | 02/24/2023 | 5/14/2024 | Y | EXP | 365 | 08/12/2023 | 10/09/2023 | 59 | 0 | 59 |  |  | 10/18/2023 | Connected |  | Y
National Grid | HAVERHILL | 205072 | 01832 | 5 | Solar | 05_14_63L1 | 02/07/2019 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 675285 | 01844 | 10 | Solar | 05_14_75L6 | 03/03/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 676081 | 01844 | 20 | Solar | 05_01_225W1 | 03/12/2025 | 04/14/2025 | 24 | 21 | 3 | 04/15/2025 | 04/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | LANCASTER | 397095 | 01523 | 1500 | Solar | 05_01_304W5 | 03/15/2022 |  | 161 | 153 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 177922 | 01590 | 4980 | Solar | 05_01_415L2 | 10/24/2017 | 10/24/2017 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 | 12/08/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 706197 | 01507 | 6.08 | Solar | 05_01_6J319 | 07/21/2025 | 08/07/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2025 | Connected |  | N
National Grid | WORCESTER | 742528 | 01603 | 3.8 | Solar | 05_05_19W73 | 12/30/2025 | 01/05/2026 | 3 | 0 | 3 | 01/06/2026 | 01/06/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SWANSEA | 658236 | 02777 | 3.8 | Solar | 05_12_35J4 | 12/03/2024 |  | 131 | 25 | 106 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 406505 | 02151 | 8.027 | Solar | 05_14_18L3 | 04/19/2022 | 04/27/2022 | 6 | 6 | 0 | 04/28/2022 | 04/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 04/19/2022 | 11/19/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | BILLERICA | 586272 | 01821 | 3.19 | Solar | 05_14_48L4 | 02/07/2024 | 02/12/2024 | 3 | 0 | 3 | 02/13/2024 | 02/13/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2024 | 02/07/2024 | 3/15/2025 | Y | EXP | 365 | 06/06/2024 | 11/02/2024 | 150 | 0 | 150 |  |  | 11/16/2024 | Connected |  | N
National Grid | HAVERHILL | 211661 | 01832 | 5 | Solar | 05_14_63L1 | 03/05/2019 | 03/06/2019 | 0 | 0 | 0 | 03/07/2019 | 03/07/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 676647 | 01844 | 5.8 | Solar | 05_14_75L6 | 03/18/2025 | 03/26/2025 | 8 | 6 | 2 | 04/09/2025 | 04/09/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 681615 | 01844 | 10.64 | Solar | 05_01_225W1 | 04/02/2025 | 04/15/2025 | 10 | 6 | 4 | 04/16/2025 | 04/16/2025 | 62 | 37 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | LANCASTER | 486689 | 01523 | 4999 | Other | 05_01_304W5 | 01/19/2023 | 02/03/2023 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2023 | 03/27/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 178290 | 01527 | 1000 | Solar | 05_01_415L2 | 03/28/2018 | 03/28/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/10/2018 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 504930 | 01507 | 20 | Solar | 05_01_6J326 | 03/01/2023 | 03/21/2023 | 14 | 4 | 10 | 03/22/2023 | 03/22/2023 | 252 | 233 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 750543 | 01603 | 7.6 | Solar | 05_05_19W73 | 02/11/2026 | 02/13/2026 | 2 | 0 | 2 | 02/17/2026 | 02/17/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | DIGHTON | 687658 | 02715 | 7.6 | Solar | 05_12_37J3 | 04/25/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | REVERE | 413213 | 02151 | 9.57 | Solar | 05_14_18L3 | 02/21/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | BILLERICA | 626731 | 01821 | 9.86 | Solar | 05_14_48L4 | 07/22/2024 | 07/31/2024 | 5 | 3 | 2 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/22/2024 | 8/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | HAVERHILL | 219723 | 01832 | 5 | Solar | 05_14_63L1 | 05/01/2019 | 05/01/2019 | 0 | 0 | 0 | 05/02/2019 | 05/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 05/01/2019 | 1/21/2020 | Y | EXP | 263 | 07/16/2019 | 08/12/2019 | 27 | 0 | 27 |  |  | 10/8/2019 | Connected |  | N
National Grid | METHUEN | 693695 | 01844 | 20 | Solar | 05_14_75L6 | 05/29/2025 | 06/04/2025 | 4 | 0 | 4 | 06/05/2025 | 06/05/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2025 | Connected |  | N
National Grid | METHUEN | 683232 | 01844 | 7.6 | Solar | 05_01_225W1 | 04/15/2025 | 07/15/2025 | 29 | 24 | 5 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | BOLTON | 519333 | 01740 | 0 | Battery Add-On | 05_01_304W5 | 04/14/2023 | 04/24/2023 | 5 | 0 | 5 | 04/25/2023 | 04/25/2023 | 226 | 204 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | MILLBURY | 188710 | 01527 | 250 | Solar | 05_01_415L2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 596707 | 01507 | 3.8 | Solar | 05_01_6J326 | 03/13/2024 | 05/08/2024 | 1 | 0 | 1 | 05/09/2024 | 05/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 5/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | WORCESTER | 749683 | 01610 | 23 | Solar | 05_05_19W73 | 02/06/2026 | 02/09/2026 | 1 | 0 | 1 | 02/10/2026 | 02/10/2026 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 177347 | 02777 | 7.6 | Solar | 05_12_37J3 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/17/2017 | 4/17/2017 | 4/24/2017 | Connected |  | N
National Grid | EVERETT | 434023 | 02149 | 0 | Other | 05_14_18L3 | 09/07/2022 | 09/28/2022 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2022 | 10/26/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 637124 | 01821 | 7.6 | Solar | 05_14_48L4 | 09/02/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2024 | 09/02/2024 | 10/29/2025 | Y | EXP | 365 | 06/27/2025 | 06/26/2025 | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | HAVERHILL | 216261 | 01832 | 10 | Solar | 05_14_63L1 | 06/10/2019 | 06/21/2019 | 8 | 2 | 6 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/10/2019 | 9/16/2020 | Y | EXP | 365 | 05/27/2020 | 06/01/2020 | 5 | 0 | 5 |  |  | 7/2/2020 | Connected |  | N
National Grid | METHUEN | 698874 | 01844 | 4200 | Other | 05_14_75L6 | 10/16/2025 | 11/26/2025 | 29 | 22 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2025 | 12/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 714705 | 01844 | 0 | Battery Add-On | 05_01_225W1 | 08/26/2025 | 09/16/2025 | 12 | 9 | 3 | 09/17/2025 | 09/17/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | BOLTON | 525794 | 01740 | 10 | Solar | 05_01_304W5 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 | 07/05/2023 | 10/30/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2024 | Connected |  | N
National Grid | SUTTON | 195208 | 01590 | 6930 | Solar | 05_01_415L2 | 10/01/2018 | 10/22/2018 | 15 | 15 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 12/04/2018 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 650995 | 01507 | 10 | Solar | 05_01_6J326 | 11/07/2024 | 11/25/2024 | 6 | 3 | 3 | 11/26/2024 | 11/26/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WORCESTER | 170590 | 01610 | 15.4 | Solar | 05_05_19W73 | 06/07/2018 | 06/07/2018 | 8 | 8 | 0 | 06/26/2018 | 06/26/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 | 06/07/2018 | 12/24/2019 | Y | EXP | 55 | 07/06/2019 | 08/01/2019 | 26 | 0 | 26 |  |  | 12/11/2019 | Connected |  | N
National Grid | SWANSEA | 178067 | 02777 | 240 | Solar | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 352 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/13/2021 | Connected |  | N
National Grid | EVERETT | 503842 | 02149 | 10 | Solar | 05_14_18L3 | 03/09/2023 | 03/10/2023 | 2 | 1 | 1 | 03/13/2023 | 03/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/09/2023 | 5/25/2024 | Y | EXP | 365 | 09/26/2023 | 10/12/2023 | 17 | 0 | 17 |  |  | 10/16/2023 | Connected |  | N
National Grid | BILLERICA | 668948 | 01821 | 10.44 | Solar | 05_14_48L4 | 02/06/2025 | 02/12/2025 | 4 | 0 | 4 | 02/13/2025 | 02/13/2025 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 10/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | HAVERHILL | 228343 | 01832 | 10 | Solar | 05_14_63L1 | 07/08/2019 | 07/17/2019 | 6 | 6 | 0 | 07/18/2019 | 07/18/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 618791 | 01844 | 160 | Solar | 05_14_76L1 | 07/11/2024 | 11/25/2024 | 94 | 85 | 9 | 11/26/2024 | 11/26/2024 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 8/19/2026 | N | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | DRACUT | 718559 | 01826 | 11.5 | Solar | 05_01_225W1 | 09/11/2025 | 09/16/2025 | 3 | 0 | 3 | 09/17/2025 | 09/17/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | HARVARD | 556313 | 01451 | 15 | Solar | 05_01_304W5 | 09/21/2023 | 10/02/2023 | 7 | 6 | 1 | 10/03/2023 | 10/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2023 |  | 11/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | MILLBURY | 202001 | 01527 | 0 | Solar | 05_01_415L2 | 01/15/2019 | 02/25/2019 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2019 | 06/27/2019 | 87 | 72 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 661648 | 01507 | 5.76 | Solar | 05_01_6J326 | 12/19/2024 | 01/29/2025 | 16 | 11 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | WORCESTER | 170569 | 01603 | 15.4 | Solar | 05_05_19W73 | 07/17/2018 | 08/13/2018 | 19 | 7 | 12 | 08/14/2018 | 08/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 12/24/2019 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  | 12/11/2019 | Connected |  | N
National Grid | DIGHTON | 178098 | 02715 | 240 | Solar | 05_12_37J3 | 09/05/2017 | 09/05/2017 | 45 | 45 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/13/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2018 | 09/05/2017 | 4/15/2021 | Y | STD | 598 | 09/16/2020 | 03/24/2021 | 189 | 0 | 189 |  |  | 4/14/2021 | Connected |  | N
National Grid | WEYMOUTH | 559528 | 02188 | 13.34 | Solar | 05_14_18L3 | 10/03/2023 | 10/12/2023 | 6 | 4 | 2 | 10/13/2023 | 10/13/2023 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 725190 | 01821 | 10 | Solar | 05_14_50L1 | 10/08/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 242735 | 01832 | 10 | Solar | 05_14_63L1 | 08/28/2019 | 08/29/2019 | 1 | 1 | 0 | 08/30/2019 | 08/30/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 | 08/28/2019 | 6/11/2020 | Y | EXP | 365 | 01/16/2020 | 02/20/2020 | 35 | 0 | 35 |  |  | 2/24/2020 | Connected |  | N
National Grid | LAWRENCE | 722747 | 01841 | 22.8 | Solar | 05_14_76L1 | 09/30/2025 | 10/02/2025 | 2 | 0 | 2 | 10/03/2025 | 10/03/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 722322 | 01830 | 20.242 | Solar | 05_01_225W1 | 09/30/2025 | 10/08/2025 | 5 | 0 | 5 | 10/09/2025 | 10/09/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | HARVARD | 566450 | 01451 | 10 | Solar | 05_01_304W5 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 | 01/31/2024 | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 |  | 05/23/2024 | 80 | 55 | 25 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 244622 | 01527 | 10 | Solar | 05_01_415L2 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 9/30/2019 | N | EXP | 56 |  |  | 0 | 0 | 0 |  |  | 9/26/2019 | Connected |  | N
National Grid | CHARLTON | 656764 | 01507 | 3.8 | Solar | 05_01_6J342 | 11/25/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | WORCESTER | 174564 | 01603 | 500 | Solar | 05_05_19W73 | 08/08/2011 | 08/08/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2012 | 08/08/2011 | 10/31/2012 | Y | STD | 229 | 08/27/2012 | 01/18/2013 | 83 | 0 | 83 | 12/5/2012 | 12/5/2012 | 12/10/2012 | Connected |  | N
National Grid | DIGHTON | 464132 | 02715 | 80 | Solar | 05_12_37J3 | 10/26/2022 | 02/14/2023 | 74 | 63 | 11 | 02/15/2023 | 02/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 | 10/26/2022 | 7/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | WEYMOUTH | 587504 | 02188 | 7.25 | Solar | 05_14_18L3 | 02/12/2024 | 02/15/2024 | 3 | 0 | 3 | 02/16/2024 | 02/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/12/2024 | 2/28/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/24/2024 | Connected |  | N
National Grid | BILLERICA | 739126 | 01821 | 0 | Solar | 05_14_50L1 | 01/15/2026 | 01/21/2026 | 3 | 0 | 3 | 01/22/2026 | 01/22/2026 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 239280 | 01810 | 7.6 | Solar | 05_14_63L1 | 06/27/2019 | 07/01/2019 | 2 | 2 | 0 | 07/02/2019 | 07/02/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/27/2019 | 4/22/2020 | Y | EXP | 287 | 01/03/2020 | 01/02/2020 | 0 | 0 | 0 |  |  | 1/10/2020 | Connected |  | N
National Grid | METHUEN | 175917 | 01844 | 1000 | Solar | 05_14_76L1 | 03/12/2015 | 03/12/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2015 | 04/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 |  | 12/14/2016 | N | STD | 442 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 721741 | 01830 | 7.6 | Solar | 05_01_225W1 | 10/05/2025 | 11/12/2025 | 8 | 4 | 4 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | BOLTON | 575814 | 01740 | 0 | Solar | 05_01_304W5 | 01/23/2024 | 03/14/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2024 | 04/11/2024 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 327784 | 01527 | 9.8 | Solar | 05_01_415L2 | 12/28/2020 | 12/31/2020 | 2 | 0 | 2 | 01/04/2021 | 01/04/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  | 2/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 676125 | 01507 | 5.76 | Solar | 05_01_6J342 | 03/06/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | WORCESTER | 174691 | 01603 | 1500 | Solar | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/6/2012 | Connected |  | N
National Grid | SWANSEA | 662378 | 02777 | 10 | Solar | 05_12_37J4 | 01/10/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | EVERETT | 609946 | 02149 | 19.175 | Solar | 05_14_18L3 | 05/14/2024 | 05/28/2024 | 10 | 8 | 2 | 05/29/2024 | 05/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/14/2024 | 7/22/2025 | Y | EXP | 365 | 08/09/2024 | 08/28/2024 | 20 | 0 | 20 |  |  | 9/12/2024 | Connected |  | N
National Grid | BILLERICA | 176001 | 01862 | 20 | Solar | 05_14_50L1 | 06/15/2015 | 06/15/2015 | 16 | 16 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2015 |  | 6/21/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 9/23/2015 | 9/23/2015 | 9/29/2015 | Connected |  | N
National Grid | ANDOVER | 250742 | 01810 | 7.6 | Solar | 05_14_63L1 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 12 | 8 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | METHUEN | 196058 | 01844 | 240 | Solar | 05_14_76L1 | 10/16/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2018 | 11/21/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/16/2018 | 3/9/2027 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 721546 | 01830 | 5.76 | Solar | 05_01_225W1 | 09/30/2025 | 10/06/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | BOLTON | 590002 | 01740 | 7.6 | Solar | 05_01_304W5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 4/22/2025 | Y | EXP | 365 | 08/08/2024 | 10/02/2024 | 56 | 0 | 56 |  |  | 10/11/2024 | Connected |  | N
National Grid | MILLBURY | 349183 | 01527 | 7.6 | Solar | 05_01_415L2 | 05/04/2021 | 05/07/2021 | 2 | 0 | 2 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 10/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2022 | Connected |  | Y
National Grid | CHARLTON | 684243 | 01507 | 77.3 | Solar | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 20 | 9 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 174690 | 01603 | 1000 | Solar | 05_05_19W73 | 04/08/2011 | 04/08/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2012 | 04/08/2011 | 12/31/2012 | Y | STD | 185 | 05/30/2012 | 02/26/2013 | 165 | 0 | 165 | 12/5/2012 | 12/5/2012 | 12/5/2012 | Connected |  | N
National Grid | SWANSEA | 578954 | 02777 | 200 | Solar | 05_12_37W1 | 01/03/2024 | 01/11/2024 | 6 | 0 | 6 | 01/12/2024 | 01/12/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 6/19/2026 | N | EXP | 18 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | EVERETT | 649590 | 02149 | 7.6 | Solar | 05_14_18L3 | 10/24/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 178145 | 01862 | 10 | Solar | 05_14_50L1 | 04/12/2018 | 04/12/2018 | 374 | 34 | 340 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 251517 | 01810 | 7.6 | Solar | 05_14_63L1 | 10/10/2019 | 10/15/2019 | 14 | 12 | 2 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 |  | 10/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 196057 | 01844 | 960 | Solar | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 727783 | 01830 | 5.76 | Solar | 05_01_225W1 | 10/27/2025 | 10/29/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2026 | Connected |  | N
National Grid | BOLTON | 604919 | 01740 | 7.6 | Solar | 05_01_304W5 | 04/19/2024 | 05/09/2024 | 5 | 1 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/19/2024 | 12/31/2025 | Y | EXP | 365 | 09/10/2024 | 12/05/2024 | 87 | 0 | 87 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 356489 | 01527 | 21.36 | Solar | 05_01_415L2 | 05/05/2021 | 05/12/2021 | 4 | 2 | 2 | 05/13/2021 | 05/13/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2021 |  | 1/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2022 | Connected |  | N
National Grid | CHARLTON | 684212 | 01507 | 77.3 | Solar | 05_01_6J356 | 04/21/2025 | 06/02/2025 | 29 | 20 | 9 | 06/03/2025 | 06/03/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 175157 | 01603 | 2000 | Solar | 05_05_19W73 | 07/25/2011 | 07/25/2011 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2011 | 02/25/2014 | 523 | 0 | 523 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 658074 | 02777 | 84.6 | Solar | 05_12_37W1 | 01/09/2025 |  | 287 | 58 | 229 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MEDFORD | 662428 | 02155 | 5.76 | Solar | 05_14_18L3 | 12/23/2024 | 03/12/2025 | 19 | 14 | 5 | 03/13/2025 | 03/13/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 203934 | 01821 | 0 | Battery Add-On | 05_14_50L1 | 12/19/2018 | 12/31/2018 | 6 | 0 | 6 | 01/02/2019 | 01/02/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | ANDOVER | 273652 | 01810 | 10 | Solar | 05_14_63L1 | 02/03/2020 | 02/06/2020 | 2 | 0 | 2 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 196056 | 01844 | 3600 | Solar | 05_14_76L1 | 10/18/2018 | 10/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 10/18/2018 | 3/9/2027 | Y | CMPX | 798 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 174154 | 01830 | 1000 | Solar | 05_01_225W2 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2012 | 06/22/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 608984 | 01523 | 2.61 | Solar | 05_01_304W5 | 05/16/2024 | 06/14/2024 | 21 | 20 | 1 | 06/17/2024 | 06/17/2024 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 396888 | 01527 | 7.68 | Solar | 05_01_415L2 | 01/24/2022 | 01/25/2022 | 1 | 0 | 1 | 01/26/2022 | 01/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2022 | 01/24/2022 | 7/27/2023 | Y | EXP | 365 | 06/30/2022 | 07/26/2022 | 27 | 0 | 27 |  |  | 9/7/2022 | Connected |  | N
National Grid | CHARLTON | 731603 | 01507 | 17.92 | Solar | 05_01_6J356 | 11/07/2025 | 11/14/2025 | 4 | 0 | 4 | 11/17/2025 | 11/17/2025 | 63 | 48 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175622 | 01603 | 996 | Solar | 05_05_19W73 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 06/02/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2015 | 05/05/2014 | 12/31/2016 | Y | STD | 575 | 12/01/2016 | 12/30/2016 | 20 | 0 | 20 | 12/30/2016 | 12/30/2016 | 12/30/2016 | Connected |  | N
National Grid | DIGHTON | 192277 | 02715 | 340 | Solar | 05_12_37W1 | 09/11/2018 | 09/13/2018 | 1 | 0 | 1 | 09/14/2018 | 09/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  | 5/10/2021 | N | EXP | 49 | 02/13/2020 | 05/06/2021 | 449 | 5 | 444 |  |  | 5/19/2021 | Connected |  | N
National Grid | MEDFORD | 679351 | 02155 | 13.25 | Solar | 05_14_18L3 | 03/22/2025 | 03/27/2025 | 4 | 1 | 3 | 03/28/2025 | 03/28/2025 | 55 | 40 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | Y
National Grid | BILLERICA | 213038 | 01862 | 10 | Solar | 05_14_50L1 | 03/08/2019 | 03/11/2019 | 5 | 0 | 5 | 04/08/2019 | 04/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 3/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2019 | Connected |  | N
National Grid | ANDOVER | 282749 | 01810 | 10 | Solar | 05_14_63L1 | 04/09/2020 | 04/21/2020 | 6 | 4 | 2 | 04/22/2020 | 04/22/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 | 04/09/2020 | 3/12/2021 | Y | EXP | 365 | 08/25/2020 | 10/13/2020 | 49 | 0 | 49 |  |  | 10/22/2020 | Connected |  | N
National Grid | LAWRENCE | 245548 | 01841 | 17.6 | Solar | 05_14_76L1 | 07/26/2019 | 07/29/2019 | 0 | 0 | 0 | 07/30/2019 | 07/30/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 |  | 7/26/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 176327 | 01830 | 2800 | Solar | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 7/1/2016 | N | STD | 221 |  |  | 0 | 0 | 0 |  |  | 12/19/2016 | Withdrawn |  | N
National Grid | LANCASTER | 630164 | 01523 | 32.88 | Solar | 05_01_304W5 | 08/05/2024 | 08/07/2024 | 3 | 1 | 2 | 08/08/2024 | 08/08/2024 | 91 | 74 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | MILLBURY | 398624 | 01527 | 19 | Solar | 05_01_415L2 | 12/09/2021 | 12/14/2021 | 3 | 0 | 3 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 2/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2022 | Connected |  | N
National Grid | CHARLTON | 741220 | 01507 | 3.8 | Solar | 05_01_6W1 | 12/18/2025 | 12/23/2025 | 3 | 0 | 3 | 12/24/2025 | 12/24/2025 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 175763 | 01603 | 684 | Solar | 05_05_19W73 | 06/05/2014 | 06/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2014 | 09/04/2014 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 280051 | 02715 | 462.5 | Solar | 05_12_37W1 | 04/24/2020 | 05/12/2020 | 12 | 8 | 4 |  |  | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 178218 | 02148 | 10 | Solar | 05_14_1J1 | 04/13/2018 | 04/13/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 4/21/2019 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 227099 | 01821 | 0 | Solar | 05_14_50L1 | 05/13/2019 | 05/14/2019 | 0 | 0 | 0 | 05/15/2019 | 05/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2019 | Connected |  | N
National Grid | ANDOVER | 287307 | 01810 | 6 | Solar | 05_14_63L1 | 05/06/2020 | 05/08/2020 | 1 | 0 | 1 | 05/11/2020 | 05/11/2020 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 295965 | 01844 | 9.36 | Solar | 05_14_76L1 | 06/11/2020 | 07/06/2020 | 16 | 11 | 5 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | HAVERHILL | 177388 | 01830 | 2800 | Solar | 05_01_225W2 | 07/17/2015 | 07/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/21/2015 | 08/18/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 | 07/17/2015 | 7/20/2018 | Y | STD | 97 | 08/28/2017 | 06/18/2018 | 145 | 0 | 145 |  |  | 7/20/2017 | Connected |  | N
National Grid | LEOMINSTER | 641209 | 01453 | 7.6 | Solar | 05_01_304W5 | 09/18/2024 | 10/08/2024 | 5 | 0 | 5 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 1/13/2026 | Y | EXP | 365 | 04/15/2025 | 08/15/2025 | 123 | 0 | 123 |  |  | 9/30/2025 | Connected |  | N
National Grid | MILLBURY | 423224 | 01527 | 13.12 | Solar | 05_01_415L2 | 04/28/2022 | 05/02/2022 | 2 | 1 | 1 | 05/03/2022 | 05/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174950 | 01507 | 1000 | Solar | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175915 | 01603 | 2000 | Solar | 05_05_19W73 | 03/11/2015 | 03/11/2015 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 04/22/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2016 | 03/11/2015 | 12/31/2017 | Y | STD | 642 | 09/19/2017 | 12/14/2017 | 54 | 0 | 54 | 12/15/2017 | 12/15/2017 | 12/19/2017 | Connected |  | N
National Grid | SWANSEA | 315641 | 02777 | 7.68 | Solar | 05_12_37W1 | 09/28/2020 | 10/19/2020 | 14 | 12 | 2 | 10/20/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 10/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2021 | Connected |  | N
National Grid | MEDFORD | 546449 | 02155 | 4.93 | Solar | 05_14_1J1 | 08/23/2023 | 09/06/2023 | 10 | 9 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 11/18/2024 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | LAWRENCE | 326510 | 01843 | 10 | Solar | 05_14_50L1 | 11/17/2020 | 12/03/2020 | 10 | 8 | 2 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2021 | Connected |  | N
National Grid | ANDOVER | 289256 | 01810 | 3.8 | Solar | 05_14_63L1 | 05/06/2020 | 05/07/2020 | 0 | 0 | 0 | 05/08/2020 | 05/08/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 448164 | 01841 | 30 | Solar | 05_14_76L1 | 07/31/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2022 |  | 10/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 453761 | 01830 | 499 | Solar | 05_01_225W2 | 09/08/2022 | 10/04/2022 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/05/2022 | 10/31/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 643175 | 01453 | 0 | Other | 05_01_304W5 | 12/10/2024 | 01/31/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2025 | 03/10/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 482703 | 01527 | 23.49 | Solar | 05_01_415L2 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/05/2022 | 1/24/2024 | Y | EXP | 365 | 05/05/2023 | 06/08/2023 | 35 | 0 | 35 |  |  | 7/27/2023 | Connected |  | N
National Grid | CHARLTON | 174949 | 01507 | 2000 | Solar | 05_01_6W1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175926 | 01524 | 16 | Solar | 05_05_19W73 | 06/01/2015 | 06/01/2015 | 11 | 11 | 0 | 06/17/2015 | 06/17/2015 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2015 |  | 6/30/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 7/6/2015 | 7/6/2015 |  | Withdrawn |  | N
National Grid | DIGHTON | 563473 | 02715 | 10 | Solar | 05_12_37W1 | 11/15/2023 | 11/16/2023 | 1 | 0 | 1 | 11/17/2023 | 11/17/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2024 | 11/15/2023 | 1/26/2025 | Y | EXP | 365 | 03/14/2024 | 06/14/2024 | 93 | 0 | 93 |  |  | 7/18/2024 | Connected |  | N
National Grid | MEDFORD | 612368 | 02155 | 5.76 | Solar | 05_14_1J1 | 05/20/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | LAWRENCE | 424059 | 01843 | 9.772 | Solar | 05_14_50L1 | 04/24/2022 | 05/05/2022 | 10 | 9 | 1 | 05/06/2022 | 05/06/2022 | 22 | 10 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2022 | 04/24/2022 | 8/11/2023 | Y | EXP | 365 | 07/07/2022 | 08/11/2022 | 36 | 0 | 36 |  |  | 10/21/2022 | Connected |  | N
National Grid | ANDOVER | 292786 | 01810 | 15.705 | Solar | 05_14_63L1 | 09/22/2020 | 03/23/2021 | 126 | 125 | 1 | 03/24/2021 | 03/24/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 10/9/2022 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  | 9/28/2022 | Connected |  | N
National Grid | LAWRENCE | 461652 | 01841 | 0 | Solar | 05_14_76L1 | 09/28/2022 | 10/04/2022 | 4 | 3 | 1 | 10/05/2022 | 10/05/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 582926 | 01830 | 0 | Solar | 05_01_225W3 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 645815 | 01453 | 6.72 | Solar | 05_01_304W5 | 10/09/2024 | 10/17/2024 | 2 | 0 | 2 | 10/18/2024 | 10/18/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 10/09/2024 | 4/16/2026 | Y | EXP | 365 | 03/06/2025 |  | 366 | 0 | 366 |  |  | 6/10/2025 | Connected |  | N
National Grid | SUTTON | 487520 | 01590 | 8.7 | Solar | 05_01_415L2 | 01/06/2023 | 01/12/2023 | 4 | 0 | 4 | 01/13/2023 | 01/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2023 | Connected |  | N
National Grid | CHARLTON | 176281 | 01507 | 16.32 | Solar | 05_01_6W1 | 05/06/2015 | 05/06/2015 | 3 | 3 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/12/2016 | Connected |  | N
National Grid | LEICESTER | 176025 | 01524 | 980 | Solar | 05_05_19W73 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 639527 | 02777 | 7.6 | Solar | 05_12_37W1 | 09/11/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/11/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | MEDFORD | 641339 | 02155 | 7.6 | Solar | 05_14_1J1 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | LAWRENCE | 431159 | 01843 | 15.2 | Solar | 05_14_50L1 | 05/18/2022 | 05/19/2022 | 1 | 0 | 1 | 05/20/2022 | 05/20/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2023 | Connected |  | Y
National Grid | ANDOVER | 306473 | 01810 | 10 | Solar | 05_14_63L1 | 09/18/2020 | 09/24/2020 | 3 | 0 | 3 | 09/25/2020 | 09/25/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 500093 | 01844 | 15.36 | Solar | 05_14_76L1 | 02/07/2023 | 02/24/2023 | 13 | 12 | 1 | 02/27/2023 | 02/27/2023 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 | 02/07/2023 | 6/27/2024 | Y | EXP | 365 | 07/27/2023 | 10/25/2023 | 91 | 0 | 91 |  |  | 10/27/2023 | Connected |  | N
National Grid | HAVERHILL | 676973 | 01830 | 840 | Solar | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2025 | 07/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LANCASTER | 648088 | 01523 | 15.2 | Solar | 05_01_304W5 | 10/21/2024 | 10/23/2024 | 2 | 1 | 1 | 10/24/2024 | 10/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | MILLBURY | 521797 | 01527 | 12.288 | Solar | 05_01_415L2 | 07/10/2023 | 07/12/2023 | 3 | 1 | 2 | 07/13/2023 | 07/13/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 | 07/10/2023 | 9/8/2024 | Y | EXP | 365 | 10/24/2023 | 12/13/2023 | 51 | 0 | 51 |  |  | 7/9/2024 | Connected |  | N
National Grid | CHARLTON | 176484 | 01507 | 7.6 | Solar | 05_01_6W1 | 05/23/2016 | 05/23/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 84 | 0 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 5/30/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 176085 | 01501 | 499 | Solar | 05_05_19W73 | 02/04/2015 | 02/04/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 03/19/2015 | 02/14/2017 | 474 | 0 | 474 | 02/11/2015 | 03/18/2015 | 23 | 0 | 23 |  | 02/14/2017 | 474 | 0 | 474 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 658042 | 02777 | 84.6 | Solar | 05_12_37W1 | 01/09/2025 |  | 93 | 83 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 174789 | 02155 | 60 | Solar | 05_14_1J2 | 06/03/2011 | 06/03/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2011 |  | 3/12/2012 | N | EXP | 147 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 3/12/2012 | Connected |  | N
National Grid | LAWRENCE | 433986 | 01843 | 19 | Solar | 05_14_50L1 | 05/27/2022 | 06/24/2022 | 19 | 18 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2023 | Connected |  | Y
National Grid | ANDOVER | 314982 | 01810 | 9.765 | Solar | 05_14_63L1 | 12/04/2020 | 12/07/2020 | 0 | 0 | 0 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/04/2020 | 11/22/2022 | Y | EXP | 365 | 08/06/2021 | 12/07/2021 | 123 | 63 | 60 |  |  | 12/9/2021 | Connected |  | N
National Grid | METHUEN | 519947 | 01844 | 0 | Solar | 05_14_76L1 | 04/18/2023 | 04/21/2023 | 3 | 0 | 3 | 04/24/2023 | 04/24/2023 | 211 | 192 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | HAVERHILL | 684731 | 01830 | 6.67 | Solar | 05_01_225W3 | 04/11/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 654542 | 01453 | 7.6 | Solar | 05_01_304W5 | 11/18/2024 | 01/06/2025 | 17 | 12 | 5 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | MILLBURY | 557025 | 01527 | 0 | Solar | 05_01_415L2 | 12/22/2023 | 01/02/2024 | 5 | 2 | 3 | 01/03/2024 | 01/03/2024 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | CHARLTON | 300516 | 01507 | 8.64 | Solar | 05_01_6W1 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 8/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | WORCESTER | 176362 | 01603 | 10 | Solar | 05_05_19W73 | 03/08/2016 | 03/08/2016 | 1 | 1 | 0 | 03/11/2016 | 03/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2016 |  | 3/15/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/15/2016 | 7/15/2016 | 7/15/2016 | Connected |  | N
National Grid | DIGHTON | 668952 | 02715 | 7.6 | Solar | 05_12_37W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | MEDFORD | 178293 | 02155 | 160 | Solar | 05_14_1J2 | 11/14/2017 | 11/14/2017 | 35 | 26 | 9 | 01/08/2018 | 01/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2018 |  | 12/23/2019 | N | EXP | 713 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 485562 | 01843 | 15.2 | Solar | 05_14_50L1 | 01/20/2023 | 01/27/2023 | 5 | 5 | 0 | 01/30/2023 | 01/30/2023 | 136 | 25 | 111 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 316168 | 01810 | 7.6 | Solar | 05_14_63L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2020 | 10/21/2020 | 10/21/2021 | Y | EXP | 365 | 02/10/2021 | 04/05/2021 | 54 | 0 | 54 |  |  | 4/27/2021 | Connected |  | N
National Grid | LAWRENCE | 621040 | 01841 | 120 | Solar | 05_14_76L1 | 06/27/2024 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 683667 | 01830 | 10 | Solar | 05_01_225W3 | 04/08/2025 | 06/24/2025 | 25 | 24 | 1 | 08/21/2025 | 08/21/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 04/08/2025 | 9/29/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | LEOMINSTER | 661844 | 01453 | 5.76 | Solar | 05_01_304W5 | 12/19/2024 | 02/24/2025 | 22 | 17 | 5 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 548536 | 01527 | 7.6 | Solar | 05_01_415L2 | 08/25/2023 | 08/29/2023 | 3 | 2 | 1 | 08/30/2023 | 08/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2023 | 08/25/2023 | 11/9/2024 | Y | EXP | 365 | 03/09/2024 | 04/10/2024 | 33 | 0 | 33 |  |  | 6/27/2024 | Connected |  | N
National Grid | CHARLTON | 321984 | 01507 | 250 | Solar | 05_01_6W1 | 07/21/2021 | 08/04/2021 | 10 | 0 | 10 | 08/05/2021 | 08/05/2021 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2021 | 07/21/2021 | 2/2/2023 | Y | EXP | 34 |  |  | 0 | 0 | 0 |  |  | 12/8/2022 | Connected |  | N
National Grid | AUBURN | 176537 | 01501 | 10 | Solar | 05_05_19W73 | 02/10/2016 | 02/10/2016 | 15 | 15 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2016 | 02/10/2016 | 2/16/2017 | Y | EXP | 321 | 08/16/2016 | 08/30/2016 | 10 | 0 | 10 | 10/24/2016 | 10/24/2016 | 10/26/2016 | Connected |  | N
National Grid | DIGHTON | 707738 | 02715 | 7.6 | Solar | 05_12_37W10 | 08/01/2025 | 08/22/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 | 08/01/2025 | 10/17/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | MEDFORD | 504462 | 02155 | 0 | Other | 05_14_1J2 | 09/13/2023 | 11/07/2023 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2023 | 12/09/2023 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 503342 | 01843 | 18.85 | Solar | 05_14_50L1 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | ANDOVER | 327152 | 01810 | 7.6 | Solar | 05_14_63L1 | 12/14/2020 | 12/18/2020 | 3 | 0 | 3 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/14/2020 | 3/2/2022 | Y | EXP | 365 | 09/24/2021 | 10/12/2021 | 18 | 0 | 18 |  |  | 12/9/2021 | Connected |  | N
National Grid | LAWRENCE | 623525 | 01841 | 10 | Solar | 05_14_76L1 | 07/09/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 07/09/2024 | 9/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2025 | Connected |  | N
National Grid | HAVERHILL | 725837 | 01830 | 200 | Solar | 05_01_225W3 | 11/26/2025 | 02/04/2026 | 45 | 39 | 6 | 02/05/2026 | 02/05/2026 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 679629 | 01453 | 3.8 | Solar | 05_01_304W5 | 03/21/2025 | 06/18/2025 | 4 | 0 | 4 | 07/28/2025 | 07/28/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 614260 | 01590 | 6 | Solar | 05_01_415L2 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 7/9/2025 | Y | EXP | 365 | 08/06/2024 | 08/15/2024 | 10 | 0 | 10 |  |  | 12/20/2024 | Connected |  | N
National Grid | CHARLTON | 373959 | 01507 | 3.8 | Solar | 05_01_6W1 | 08/09/2021 | 08/12/2021 | 3 | 0 | 3 | 08/13/2021 | 08/13/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2021 |  | 10/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 176655 | 01603 | 4.25 | Solar | 05_05_19W73 | 04/18/2016 | 04/18/2016 | 2 | 2 | 0 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2016 | 04/18/2016 | 4/24/2017 | Y | EXP | 355 | 05/11/2017 | 05/31/2017 | 13 | 0 | 13 | 6/2/2017 | 6/2/2017 | 6/6/2017 | Connected |  | N
National Grid | DIGHTON | 254430 | 02715 | 3.8 | Solar | 05_12_37W10 | 10/02/2019 | 10/07/2019 | 2 | 0 | 2 | 10/08/2019 | 10/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 685230 | 02148 | 7.68 | Solar | 05_14_1J4 | 04/15/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 | 04/15/2025 | 8/22/2026 | Y | EXP | 365 | 10/30/2025 |  | 128 | 0 | 128 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 520199 | 01843 | 10 | Solar | 05_14_50L1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 103 | 25 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 326918 | 01810 | 9.8 | Solar | 05_14_63L1 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 650180 | 01844 | 5.76 | Solar | 05_14_76L1 | 11/07/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/07/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 740892 | 01830 | 10 | Solar | 05_01_225W3 | 12/19/2025 | 12/23/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 688408 | 01453 | 10 | Solar | 05_01_304W5 | 04/29/2025 | 05/06/2025 | 5 | 2 | 3 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | MILLBURY | 665982 | 01527 | 7.6 | Solar | 05_01_415L2 | 01/15/2025 | 03/21/2025 | 9 | 5 | 4 | 03/24/2025 | 03/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 01/15/2025 | 8/29/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | CHARLTON | 595595 | 01507 | 5.76 | Solar | 05_01_6W1 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177463 | 01603 | 528 | Solar | 05_05_19W73 | 03/01/2017 | 03/01/2017 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2017 | 05/09/2017 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2017 | 03/01/2017 | 5/7/2019 | Y | STD | 782 | 05/22/2018 | 07/30/2018 | 68 | 0 | 68 | 12/6/2018 | 2/15/2019 | 5/7/2019 | Connected |  | N
National Grid | DIGHTON | 313741 | 02715 | 7.6 | Solar | 05_12_37W10 | 10/01/2020 | 10/06/2020 | 2 | 0 | 2 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 10/01/2020 | 11/13/2021 | Y | EXP | 365 | 08/02/2021 | 08/11/2021 | 9 | 0 | 9 |  |  | 9/15/2021 | Connected |  | Y
National Grid | EVERETT | 651856 | 02149 | 3.8 | Solar | 05_14_1J4 | 11/04/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | LAWRENCE | 556272 | 01843 | 0 | Battery Add-On | 05_14_50L1 | 09/18/2023 | 10/10/2023 | 15 | 14 | 1 | 10/11/2023 | 10/11/2023 | 157 | 28 | 129 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 329444 | 01810 | 7.6 | Solar | 05_14_63L1 | 12/29/2020 | 12/31/2020 | 1 | 0 | 1 | 01/04/2021 | 01/04/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/29/2020 | 12/22/2022 | Y | EXP | 365 | 08/06/2021 | 10/12/2021 | 61 | 3 | 58 |  |  | 12/1/2021 | Connected |  | Y
National Grid | METHUEN | 651643 | 01844 | 7.6 | Solar | 05_14_76L1 | 11/13/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/13/2024 | 1/24/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | HAVERHILL | 174136 | 01830 | 1000 | Solar | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 702694 | 01453 | 17.101 | Solar | 05_01_304W5 | 07/08/2025 | 07/14/2025 | 4 | 0 | 4 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | SUTTON | 666943 | 01590 | 10.47 | Solar | 05_01_415L2 | 01/24/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | CHARLTON | 605951 | 01507 | 3.8 | Solar | 05_01_6W1 | 04/23/2024 | 05/01/2024 | 4 | 0 | 4 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177486 | 01603 | 8 | Solar | 05_05_19W73 | 09/23/2016 | 09/23/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/23/2016 | 10/1/2017 | Y | EXP | 367 | 03/31/2017 | 04/13/2017 | 9 | 0 | 9 | 5/1/2017 | 5/1/2017 | 5/3/2017 | Connected |  | N
National Grid | DIGHTON | 532886 | 02764 | 6 | Solar | 05_12_37W10 | 09/13/2023 | 09/19/2023 | 5 | 2 | 3 | 09/20/2023 | 09/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 641530 | 02148 | 11.52 | Solar | 05_14_1J6 | 09/19/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 09/19/2024 | 4/16/2026 | Y | EXP | 365 | 07/08/2025 | 11/21/2025 | 137 | 0 | 137 |  |  | 11/26/2025 | Connected |  | N
National Grid | LAWRENCE | 528645 | 01843 | 9.86 | Solar | 05_14_50L1 | 05/23/2023 | 05/25/2023 | 2 | 0 | 2 | 05/26/2023 | 05/26/2023 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2023 | Connected |  | N
National Grid | ANDOVER | 330332 | 01810 | 9.8 | Solar | 05_14_63L1 | 01/04/2021 | 01/07/2021 | 2 | 0 | 2 | 01/08/2021 | 01/08/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 01/04/2021 | 3/7/2022 | Y | EXP | 365 | 09/14/2021 | 10/14/2021 | 31 | 0 | 31 |  |  | 12/13/2021 | Connected |  | Y
National Grid | METHUEN | 672054 | 01844 | 10 | Solar | 05_14_76L1 | 02/14/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 174125 | 01830 | 3000 | Solar | 05_01_225W3 | 04/06/2012 | 04/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2012 | 06/22/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2013 | 04/06/2012 | 12/1/2012 | Y | STD | 34 | 10/22/2013 | 02/22/2014 | 83 | 0 | 83 | 11/29/2013 | 11/29/2013 | 11/30/2013 | Connected |  | N
National Grid | LANCASTER | 713450 | 01523 | 11.4 | Solar | 05_01_304W5 | 08/20/2025 | 09/04/2025 | 10 | 8 | 2 | 09/05/2025 | 09/05/2025 | 53 | 37 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 12/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | SUTTON | 668885 | 01590 | 10 | Solar | 05_01_415L2 | 01/30/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | CHARLTON | 647056 | 01507 | 10 | Solar | 05_01_6W1 | 10/23/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/23/2024 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2025 | Connected |  | N
National Grid | WORCESTER | 177696 | 01603 | 11.4 | Solar | 05_05_19W73 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/26/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/12/2018 | Connected |  | N
National Grid | DIGHTON | 640115 | 02715 | 3.8 | Solar | 05_12_37W10 | 09/13/2024 | 10/10/2024 | 3 | 0 | 3 | 10/11/2024 | 10/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 09/13/2024 | 12/30/2025 | Y | EXP | 365 | 02/26/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 4/2/2025 | Connected |  | N
National Grid | MALDEN | 746934 | 02148 | 11.4 | Solar | 05_14_1J7 | 01/22/2026 | 02/05/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 534892 | 01843 | 15.2 | Solar | 05_14_50L1 | 06/26/2023 | 06/29/2023 | 4 | 3 | 1 | 06/30/2023 | 06/30/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2023 | Connected |  | N
National Grid | ANDOVER | 335650 | 01810 | 7.6 | Solar | 05_14_63L1 | 01/22/2021 |  | 31 | 31 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 690910 | 01844 | 9.88 | Solar | 05_14_76L1 | 05/09/2025 | 05/29/2025 | 2 | 0 | 2 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/09/2025 | 6/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | HAVERHILL | 174908 | 01832 | 499 | Solar | 05_01_225W3 | 09/14/2012 | 09/14/2012 | 22 | 21 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 654741 | 01523 | 240 | Solar | 05_01_304W6 | 11/15/2024 | 02/10/2025 | 56 | 46 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MILLBURY | 688903 | 01527 | 10 | Solar | 05_01_415L2 | 05/01/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 05/01/2025 | 6/27/2026 | Y | EXP | 365 | 07/31/2025 | 07/30/2025 | 0 | 0 | 0 |  |  | 9/25/2025 | Connected |  | N
National Grid | CHARLTON | 648471 | 01507 | 10 | Solar | 05_01_6W1 | 12/23/2024 | 01/21/2025 | 19 | 15 | 4 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | AUBURN | 177823 | 01501 | 15.2 | Solar | 05_05_19W73 | 06/06/2017 | 06/06/2017 | 4 | 4 | 0 | 06/13/2017 | 06/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 |  | 6/12/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/18/2017 | 10/18/2017 | 10/24/2017 | Connected |  | N
National Grid | DIGHTON | 644021 | 02764 | 23 | Solar | 05_12_37W10 | 10/01/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 10/01/2024 | 3/21/2026 | Y | EXP | 365 | 06/27/2025 | 09/08/2025 | 74 | 0 | 74 |  |  | 10/21/2025 | Connected |  | N
National Grid | EVERETT | 661824 | 02149 | 7.6 | Solar | 05_14_1J7 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/19/2024 | 4/2/2026 | Y | EXP | 365 | 04/30/2025 | 10/07/2025 | 161 | 0 | 161 |  |  | 10/8/2025 | Connected |  | N
National Grid | LAWRENCE | 538685 | 01843 | 15 | Solar | 05_14_50L1 | 07/05/2023 | 07/06/2023 | 1 | 0 | 1 | 07/07/2023 | 07/07/2023 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2023 |  | 10/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2023 | Connected |  | N
National Grid | ANDOVER | 339133 | 01810 | 7.92 | Solar | 05_14_63L1 | 03/26/2021 | 04/06/2021 | 6 | 0 | 6 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 554496 | 01844 | 480 | Solar | 05_14_76L3 | 10/06/2023 | 10/23/2023 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 | 09/25/2024 | 232 | 216 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 10/06/2023 | 10/13/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HAVERHILL | 175018 | 01830 | 500 | Solar | 05_01_225W3 | 10/08/2012 | 10/08/2012 | 7 | 0 | 7 | 10/18/2012 | 10/18/2012 | 286 | 223 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 730087 | 01453 | 10 | Solar | 05_01_304W6 | 10/30/2025 | 10/30/2025 | 2 | 0 | 2 | 11/13/2025 | 11/13/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/30/2025 | 12/12/2026 | Y | EXP | 365 | 02/19/2026 | 02/22/2026 | 4 | 0 | 4 |  |  |  | Completion Documents |  | N
National Grid | MILLBURY | 178200 | 01527 | 4999 | Solar | 05_01_415L3 | 02/15/2018 | 02/22/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2018 | 03/20/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 | 02/15/2018 | 5/22/2026 | Y | STD | 747 | 02/07/2026 |  | 28 | 0 | 28 |  |  |  | Construction |  | N
National Grid | CHARLTON | 650193 | 01507 | 5.76 | Solar | 05_01_6W1 | 11/07/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 11/07/2024 | 3/1/2026 | Y | EXP | 365 | 04/15/2025 | 08/08/2025 | 116 | 0 | 116 |  |  | 10/9/2025 | Connected |  | N
National Grid | WORCESTER | 177995 | 01603 | 20 | Solar | 05_05_19W73 | 10/24/2017 | 10/24/2017 | 8 | 8 | 0 | 11/16/2017 | 11/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2017 |  | 11/1/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 1/5/2018 | Connected |  | N
National Grid | DIGHTON | 652275 | 02764 | 3.8 | Solar | 05_12_37W10 | 11/05/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | EVERETT | 681430 | 02149 | 10 | Solar | 05_14_1J7 | 04/01/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 560942 | 01843 | 0 | Solar | 05_14_50L1 | 11/20/2023 | 11/27/2023 | 4 | 2 | 2 | 11/28/2023 | 11/28/2023 | 67 | 44 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | ANDOVER | 342738 | 01844 | 7.6 | Solar | 05_14_63L1 | 02/24/2021 | 03/16/2021 | 14 | 14 | 0 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 02/24/2021 | 9/17/2022 | Y | EXP | 365 | 08/15/2021 | 09/01/2021 | 16 | 3 | 13 |  |  | 2/2/2022 | Connected |  | N
National Grid | LAWRENCE | 670636 | 01841 | 11.5 | Solar | 05_14_76L3 | 02/14/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 176193 | 01830 | 260 | Solar | 05_01_225W3 | 02/09/2015 | 02/09/2015 | 4 | 0 | 4 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 7/31/2015 | N | EXP | 156 |  |  | 0 | 0 | 0 | 10/7/2015 | 10/7/2015 | 10/7/2015 | Connected |  | N
National Grid | LEOMINSTER | 737133 | 01453 | 17.16 | Solar | 05_01_304W6 | 12/01/2025 | 12/03/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SUTTON | 663974 | 01590 | 200 | Solar | 05_01_415L3 | 01/13/2025 | 02/03/2025 | 15 | 5 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | CHARLTON | 650851 | 01507 | 6.175 | Solar | 05_01_6W1 | 10/30/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/30/2024 | 4/4/2026 | Y | EXP | 365 | 01/23/2025 | 08/08/2025 | 198 | 0 | 198 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 178125 | 01501 | 3.8 | Solar | 05_05_19W73 | 05/12/2017 | 05/12/2017 | 5 | 5 | 0 | 05/22/2017 | 05/22/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/20/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | DIGHTON | 661110 | 02715 | 15.2 | Solar | 05_12_37W10 | 12/19/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 177026 | 02148 | 23 | Solar | 05_14_1J8 | 08/05/2016 | 08/05/2016 | 1 | 0 | 1 | 08/17/2016 | 08/17/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 6/29/2018 | N | EXP | 669 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 566383 | 01843 | 0 | Solar | 05_14_50L1 | 10/26/2023 | 10/27/2023 | 1 | 0 | 1 | 10/30/2023 | 10/30/2023 | 74 | 52 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 379714 | 01810 | 6 | Solar | 05_14_63L1 | 09/20/2021 | 12/09/2021 | 4 | 0 | 4 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 686382 | 01844 | 33.725 | Solar | 05_14_76L3 | 04/21/2025 | 05/13/2025 | 15 | 11 | 4 | 05/14/2025 | 05/14/2025 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 176674 | 01830 | 100 | Solar | 05_01_225W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/10/2017 | N | EXP | 354 |  |  | 0 | 0 | 0 | 1/6/2017 | 1/6/2017 | 1/4/2017 | Connected |  | N
National Grid | LEOMINSTER | 747999 | 01453 | 10 | Solar | 05_01_304W6 | 01/28/2026 | 02/02/2026 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SUTTON | 174387 | 01590 | 2000 | Solar | 05_01_415L3 | 06/01/2012 | 06/01/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2012 | 08/20/2012 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 652101 | 01566 | 7.6 | Solar | 05_01_6W1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/14/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | WORCESTER | 178656 | 01603 | 4875 | Solar | 05_05_19W73 | 02/02/2018 | 02/02/2018 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 667228 | 02777 | 15.2 | Solar | 05_12_37W10 | 02/07/2025 | 02/19/2025 | 7 | 3 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 177189 | 02148 | 23 | Solar | 05_14_1J8 | 08/15/2016 | 08/15/2016 | 1 | 1 | 0 | 08/17/2016 | 08/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 12/21/2017 | N | EXP | 479 |  |  | 0 | 0 | 0 | 11/29/2017 | 11/29/2017 | 11/29/2017 | Connected |  | N
National Grid | LAWRENCE | 569243 | 01843 | 0 | Solar | 05_14_50L1 | 11/06/2023 | 11/08/2023 | 2 | 0 | 2 | 11/09/2023 | 11/09/2023 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 393677 | 01810 | 7.25 | Solar | 05_14_63L1 | 11/05/2021 | 12/13/2021 | 4 | 2 | 2 | 12/14/2021 | 12/14/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 | 11/05/2021 | 7/28/2023 | Y | EXP | 365 | 05/13/2022 | 06/07/2022 | 26 | 0 | 26 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 176961 | 01844 | 0 | Solar | 05_14_76L3 | 07/18/2016 | 07/18/2016 | 2 | 2 | 0 | 07/20/2016 | 07/20/2016 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/23/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 176871 | 01835 | 6 | Solar | 05_01_225W3 | 03/01/2016 | 03/01/2016 | 2 | 2 | 0 | 03/04/2016 | 03/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2016 | 03/01/2016 | 3/7/2017 | Y | EXP | 319 | 07/07/2016 | 07/27/2016 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/19/2017 | Connected |  | N
National Grid | LEOMINSTER | 174356 | 01453 | 143 | Natural Gas | 05_01_304W6 | 05/11/2012 | 05/11/2012 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 174874 | 01590 | 1000 | Solar | 05_01_415L3 | 09/10/2012 | 09/10/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/10/2012 | 6/13/2016 | Y | STD | 136 |  |  | 0 | 0 | 0 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | STURBRIDGE | 654308 | 01566 | 5.76 | Solar | 05_01_6W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/15/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | WORCESTER | 185430 | 01603 | 4998 | Solar | 05_05_19W73 | 05/29/2018 | 05/29/2018 | 61 | 44 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 09/21/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 724792 | 02715 | 15.2 | Solar | 05_12_37W10 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MALDEN | 198686 | 02148 | 7.6 | Solar | 05_14_1J9 | 10/16/2018 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 582479 | 01843 | 6 | Solar | 05_14_50L1 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/01/2024 | 4/12/2025 | Y | EXP | 365 | 06/06/2024 | 07/24/2024 | 49 | 0 | 49 |  |  | 9/21/2024 | Connected |  | N
National Grid | ANDOVER | 410011 | 01810 | 4.8 | Solar | 05_14_63L1 | 02/18/2022 | 02/23/2022 | 2 | 0 | 2 | 02/24/2022 | 02/24/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/18/2022 | 2/7/2024 | Y | EXP | 365 | 05/24/2022 | 06/21/2022 | 29 | 0 | 29 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177296 | 01844 | 60 | Solar | 05_14_76L3 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 9/3/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/27/2017 | 3/27/2017 | 3/27/2017 | Connected |  | N
National Grid | HAVERHILL | 178266 | 01830 | 990 | Solar | 05_01_225W3 | 01/08/2018 | 01/08/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/19/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2018 | 01/08/2018 | 8/17/2020 | Y | STD | 399 | 01/17/2020 | 06/04/2020 | 139 | 0 | 139 | 6/18/2020 | 6/22/2020 | 8/10/2020 | Connected |  | N
National Grid | LEOMINSTER | 174658 | 01453 | 150 | Natural Gas | 05_01_304W6 | 12/10/2012 | 12/10/2012 | 20 | 14 | 6 | 01/10/2013 | 01/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 10/15/2014 | N | EXP | 576 |  |  | 0 | 0 | 0 | 6/15/2015 | 6/15/2015 | 6/30/2015 | Connected |  | N
National Grid | SUTTON | 174907 | 01590 | 1000 | Solar | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 6/13/2016 | Y | STD | 136 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 735202 | 01566 | 23 | Solar | 05_01_6W1 | 11/20/2025 | 11/25/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 188745 | 01501 | 129.6 | Solar | 05_05_19W73 | 06/20/2018 | 06/20/2018 | 10 | 0 | 10 | 08/21/2018 | 08/21/2018 | 32 | 31 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 174415 | 02764 | 833 | Solar | 05_12_37W2 | 06/25/2012 | 06/25/2012 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/05/2012 | 10/05/2012 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 200094 | 02148 | 10 | Solar | 05_14_1J9 | 11/02/2018 | 12/03/2018 | 9 | 2 | 7 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 597748 | 01843 | 1.45 | Solar | 05_14_50L1 | 04/02/2024 | 06/11/2024 | 48 | 47 | 1 | 06/12/2024 | 06/12/2024 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 7/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | ANDOVER | 415153 | 01810 | 9.28 | Solar | 05_14_63L1 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 4/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | METHUEN | 177403 | 01844 | 10 | Solar | 05_14_76L3 | 06/30/2016 | 06/30/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 68 | 0 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 197643 | 01830 | 10 | Solar | 05_01_225W3 | 11/13/2018 | 04/22/2019 | 108 | 103 | 5 | 04/23/2019 | 04/23/2019 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 174996 | 01523 | 1250 | Solar | 05_01_304W6 | 03/08/2013 | 03/08/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2013 | 04/30/2013 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 175328 | 01590 | 540 | Solar | 05_01_415L3 | 11/10/2014 | 11/10/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/17/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 656032 | 01566 | 7.6 | Solar | 05_01_6W2 | 11/21/2024 | 04/07/2025 | 29 | 27 | 2 | 04/08/2025 | 04/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  | 5/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 195428 | 01603 | 1500 | Solar | 05_05_19W73 | 09/13/2017 | 09/25/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 07/29/2019 | 37 | 6 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 174795 | 02715 | 50 | Solar | 05_12_37W2 | 10/02/2009 | 10/02/2009 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2009 |  | 12/31/2012 | N | EXP | 1111 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 202595 | 02155 | 7.6 | Solar | 05_14_1J9 | 02/07/2019 | 02/13/2019 | 4 | 4 | 0 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/07/2019 | 5/28/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 2/11/2020 | Connected |  | N
National Grid | LAWRENCE | 600002 | 01843 | 23 | Solar | 05_14_50L1 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 5/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | Y
National Grid | ANDOVER | 465385 | 01810 | 10 | Solar | 05_14_63L1 | 10/06/2022 |  | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 177899 | 01844 | 8.4 | Solar | 05_14_76L3 | 06/15/2017 | 06/15/2017 | 107 | 107 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/21/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 204026 | 01830 | 500 | Solar | 05_01_225W3 | 01/16/2019 | 02/07/2019 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2019 | 02/27/2019 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175250 | 01453 | 24.94 | Solar | 05_01_304W6 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 11/19/2015 | 11/19/2015 | 11/19/2015 | Connected |  | N
National Grid | SUTTON | 176124 | 01590 | 540 | Solar | 05_01_415L3 | 01/29/2015 | 01/29/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2015 | 03/09/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/29/2015 | 7/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 689362 | 01566 | 990 | Solar | 05_01_6W2 | 06/23/2025 | 09/10/2025 | 55 | 48 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2025 | 09/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WORCESTER | 235724 | 01602 | 7.6 | Solar | 05_05_19W73 | 07/03/2019 | 07/16/2019 | 8 | 8 | 0 | 07/17/2019 | 07/17/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 |  | 10/21/2019 | N | EXP | 82 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | Connected |  | N
National Grid | SWANSEA | 177293 | 02777 | 64 | Solar | 05_12_37W2 | 08/25/2016 | 08/25/2016 | 1 | 0 | 1 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2016 |  | 8/31/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/15/2017 | 11/15/2017 | 11/15/2017 | Connected |  | N
National Grid | MEDFORD | 208645 | 02155 | 10 | Solar | 05_14_1J9 | 02/13/2019 | 02/22/2019 | 5 | 0 | 5 | 02/25/2019 | 02/25/2019 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 604454 | 01843 | 0 | Battery Add-On | 05_14_50L1 | 07/16/2024 | 07/31/2024 | 11 | 9 | 2 | 08/01/2024 | 08/01/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 488617 | 01810 | 6 | Solar | 05_14_63L1 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 | 01/20/2023 | 01/20/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/18/2023 | 7/2/2024 | Y | EXP | 365 | 04/18/2023 | 06/30/2023 | 74 | 0 | 74 |  |  | 7/12/2023 | Connected |  | N
National Grid | METHUEN | 178408 | 01844 | 10 | Solar | 05_14_76L3 | 11/22/2017 | 11/22/2017 | 52 | 51 | 1 | 02/12/2018 | 02/12/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2018 | 11/22/2017 | 12/2/2018 | Y | EXP | 293 | 06/19/2018 | 07/17/2018 | 28 | 0 | 28 |  |  | 8/23/2018 | Connected |  | N
National Grid | HAVERHILL | 233067 | 01830 | 7.6 | Solar | 05_01_225W3 | 07/05/2019 | 07/08/2019 | 0 | 0 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 07/05/2019 | 5/28/2020 | Y | EXP | 365 | 12/17/2019 | 01/24/2020 | 38 | 0 | 38 |  |  | 2/14/2020 | Connected |  | N
National Grid | LEOMINSTER | 175459 | 01453 | 499 | Solar | 05_01_304W6 | 09/19/2014 | 09/19/2014 | 7 | 0 | 7 | 10/01/2014 | 10/01/2014 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 176481 | 01590 | 57.6 | Solar | 05_01_415L3 | 05/20/2016 | 05/20/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 356 | 05/01/2017 | 05/09/2017 | 6 | 0 | 6 | 6/21/2017 | 6/21/2017 | 6/28/2017 | Connected |  | N
National Grid | STURBRIDGE | 742785 | 01566 | 5.76 | Solar | 05_01_6W2 | 12/30/2025 | 01/09/2026 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 29 | 16 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 285962 | 01603 | 15.2 | Solar | 05_05_19W73 | 03/31/2020 | 04/01/2020 | 0 | 0 | 0 | 04/02/2020 | 04/02/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2020 | Connected |  | N
National Grid | DIGHTON | 177365 | 02715 | 390 | Solar | 05_12_37W2 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 06/27/2016 | 06/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2016 | 06/24/2016 | 7/2/2017 | Y | EXP | 29 | 12/12/2016 | 01/28/2017 | 32 | 0 | 32 | 3/10/2017 | 3/10/2017 | 3/9/2017 | Connected |  | N
National Grid | MEDFORD | 301209 | 02155 | 10 | Solar | 05_14_1J9 | 02/03/2021 | 02/08/2021 | 2 | 0 | 2 | 02/09/2021 | 02/09/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2021 | 02/03/2021 | 3/29/2022 | Y | EXP | 365 | 09/02/2021 | 01/27/2022 | 148 | 4 | 144 |  |  | 1/31/2022 | Connected |  | Y
National Grid | LAWRENCE | 606583 | 01843 | 23 | Solar | 05_14_50L1 | 04/25/2024 | 05/03/2024 | 4 | 0 | 4 | 07/29/2024 | 07/29/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | ANDOVER | 491261 | 01810 | 10 | Solar | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 3 | 2 | 1 | 06/06/2023 | 06/06/2023 | 75 | 43 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 199477 | 01844 | 7.6 | Solar | 05_14_76L3 | 11/05/2018 | 11/14/2018 | 5 | 0 | 5 | 11/15/2018 | 11/15/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 231390 | 01830 | 10 | Solar | 05_01_225W3 | 05/28/2019 | 06/27/2019 | 22 | 17 | 5 | 06/28/2019 | 06/28/2019 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 8/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | LEOMINSTER | 175603 | 01453 | 990 | Solar | 05_01_304W6 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2014 | 11/19/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 | 10/15/2014 | 12/31/2016 | Y | STD | 599 | 07/12/2017 | 07/12/2017 | 0 | 0 | 0 | 8/15/2017 | 8/15/2017 | 8/15/2017 | Connected |  | N
National Grid | GRAFTON | 176677 | 01519 | 112 | Solar | 05_01_415L3 | 01/05/2016 | 01/05/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 | 06/28/2016 | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 |  | 09/15/2016 | 55 | 34 | 21 |  |  | 0 | 0 | 0 | 10/31/2016 | 01/05/2016 | 1/11/2018 | Y | EXP | 437 | 07/26/2017 | 07/28/2017 | 2 | 0 | 2 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | STURBRIDGE | 750002 | 01566 | 10 | Solar | 05_01_6W2 | 02/09/2026 | 02/11/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 328690 | 01602 | 8.19 | Solar | 05_05_19W73 | 12/22/2020 | 12/28/2020 | 2 | 2 | 0 | 12/29/2020 | 12/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/22/2020 | 5/30/2022 | Y | EXP | 365 | 03/25/2021 | 04/30/2021 | 36 | 0 | 36 |  |  | 12/13/2021 | Connected |  | N
National Grid | DIGHTON | 252582 | 02764 | 200 | Solar | 05_12_37W2 | 09/06/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 88 | 26 | 62 | 10/30/2019 | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  | 01/21/2020 | 57 | 25 | 32 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 347908 | 02155 | 7.6 | Solar | 05_14_1J9 | 04/06/2021 | 04/14/2021 | 5 | 0 | 5 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2021 | Connected |  | N
National Grid | LAWRENCE | 616825 | 01843 |  | Battery Add-On | 05_14_50L1 | 06/10/2024 | 06/17/2024 | 5 | 0 | 5 | 06/18/2024 | 06/18/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | ANDOVER | 503150 | 01810 | 6 | Solar | 05_14_63L1 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 23 | 0 | 23 | 04/18/2023 | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 05/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 5/18/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 368286 | 01844 | 15.2 | Solar | 05_14_76L3 | 07/07/2021 | 08/18/2021 | 31 | 30 | 1 | 08/19/2021 | 08/19/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2021 | Connected |  | N
National Grid | HAVERHILL | 246795 | 01830 | 10 | Solar | 05_01_225W3 | 11/20/2019 | 03/12/2020 | 76 | 76 | 0 | 03/13/2020 | 03/13/2020 | 68 | 46 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2020 |  | 11/20/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175617 | 01453 | 114 | Solar | 05_01_304W6 | 04/24/2014 | 04/24/2014 | 6 | 0 | 6 | 05/05/2014 | 05/05/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2014 | 04/24/2014 | 9/30/2014 | Y | EXP | 118 | 10/15/2014 | 12/17/2014 | 43 | 0 | 43 | 7/21/2014 | 7/21/2014 | 12/19/2014 | Connected |  | N
National Grid | SUTTON | 178084 | 01590 | 1000 | Solar | 05_01_415L3 | 09/14/2012 | 09/14/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2012 | 09/26/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 | 09/14/2012 | 5/14/2018 | Y | STD | 1736 | 04/13/2015 | 08/29/2017 | 593 | 0 | 593 | 10/19/2017 | 10/19/2017 | 10/19/2017 | Connected |  | N
National Grid | CHARLTON | 166072 | 01507 | 7.6 | Solar | 05_01_6W2 | 04/24/2018 | 04/24/2018 | 9 | 0 | 9 | 07/27/2018 | 07/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2018 |  | 11/18/2020 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | LEICESTER | 342952 | 01611 | 11.4 | Solar | 05_05_19W73 | 02/18/2021 | 02/25/2021 | 4 | 0 | 4 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | SWANSEA | 384625 | 02777 | 298.8 | Solar | 05_12_37W2 | 08/11/2022 | 11/08/2022 | 61 | 51 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2022 | 09/21/2023 | 216 | 197 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 644454 | 02155 | 2.32 | Solar | 05_14_1J9 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 41 | 22 | 19 | 01/09/2025 | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 01/27/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 618866 | 01843 | 23 | Battery Add-On | 05_14_50L1 | 06/18/2024 | 06/24/2024 | 3 | 0 | 3 | 06/25/2024 | 06/25/2024 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | ANDOVER | 515091 | 01810 | 6 | Solar | 05_14_63L1 | 04/03/2023 | 04/05/2023 | 2 | 0 | 2 | 04/06/2023 | 04/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2023 | 04/03/2023 | 9/19/2024 | Y | EXP | 365 | 08/12/2023 | 09/20/2023 | 40 | 0 | 40 |  |  | 9/22/2023 | Connected |  | N
National Grid | METHUEN | 465137 | 01844 | 3.8 | Solar | 05_14_76L3 | 10/07/2022 | 10/11/2022 | 1 | 0 | 1 | 10/12/2022 | 10/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 | 10/07/2022 | 4/30/2024 | Y | EXP | 365 | 04/11/2023 | 04/28/2023 | 18 | 0 | 18 |  |  | 6/6/2023 | Connected |  | N
National Grid | HAVERHILL | 272614 | 01830 | 499.9 | Solar | 05_01_225W3 | 02/20/2020 | 02/27/2020 | 5 | 2 | 3 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 | 02/20/2020 | 4/1/2024 | Y | STD | 1112 | 01/26/2024 | 04/22/2024 | 88 | 36 | 52 |  |  | 3/25/2024 | Connected |  | N
National Grid | LEOMINSTER | 175745 | 01453 | 496.8 | Solar | 05_01_304W6 | 10/28/2014 | 10/28/2014 | 5 | 0 | 5 | 11/05/2014 | 11/05/2014 | 151 | 16 | 135 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  | 3/31/2015 | N | EXP | 27 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 437621 | 01590 | 4482 | Solar | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 03/27/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 174126 | 01566 | 135 | Solar | 05_01_6W2 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2013 |  | 8/9/2012 | N | EXP | 232 |  |  | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 1/6/2014 | Connected |  | N
National Grid | WORCESTER | 342591 | 01603 | 499 | Solar | 05_05_19W73 | 03/22/2021 | 04/22/2021 | 22 | 12 | 10 |  |  | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 648827 | 02715 | 4.35 | Solar | 05_12_37W2 | 10/22/2024 | 11/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | MEDFORD | 647960 | 02155 | 3 | Solar | 05_14_1J9 | 10/17/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/17/2024 | 1/6/2026 | Y | EXP | 365 | 04/15/2025 | 11/13/2025 | 213 | 0 | 213 |  |  | 11/17/2025 | Connected |  | N
National Grid | LAWRENCE | 625996 | 01843 |  | Battery Add-On | 05_14_50L1 | 07/18/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2024 | Connected |  | N
National Grid | ANDOVER | 516114 | 01810 | 7.6 | Solar | 05_14_63L1 | 05/30/2023 | 06/02/2023 | 3 | 1 | 2 | 06/05/2023 | 06/05/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 7/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | LAWRENCE | 478125 | 01841 | 15.2 | Solar | 05_14_76L3 | 12/01/2022 | 12/07/2022 | 4 | 2 | 2 | 12/08/2022 | 12/08/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | HAVERHILL | 291030 | 01830 | 4948 | Other | 05_01_225W3 | 09/15/2020 | 09/24/2020 | 5 | 0 | 5 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/15/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175807 | 01453 | 27.95 | Solar | 05_01_304W6 | 05/15/2015 | 05/15/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2015 |  | 10/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 1/22/2016 | Connected |  | N
National Grid | SUTTON | 437435 | 01590 | 0 | Other | 05_01_415L3 | 02/27/2023 | 03/16/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 04/18/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 174417 | 01566 | 142 | Solar | 05_01_6W2 | 06/21/2012 | 06/21/2012 | 6 | 0 | 6 | 07/03/2012 | 07/03/2012 | 293 | 0 | 293 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/10/2012 | N | EXP | 93 |  |  | 0 | 0 | 0 | 9/25/2012 | 9/25/2012 |  | Withdrawn |  | N
National Grid | WORCESTER | 381880 | 01603 | 7.54 | Solar | 05_05_19W73 | 09/16/2021 | 12/30/2021 | 15 | 13 | 2 | 10/08/2021 | 10/08/2021 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 | 09/16/2021 | 1/20/2023 | Y | EXP | 365 | 01/04/2022 | 01/13/2022 | 10 | 0 | 10 |  |  | 2/4/2022 | Connected |  | N
National Grid | DIGHTON | 742314 | 02715 | 11.5 | Battery Add-On | 05_12_37W3 | 12/26/2025 | 01/05/2026 | 5 | 0 | 5 | 01/06/2026 | 01/06/2026 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MEDFORD | 653186 | 02155 | 6.72 | Solar | 05_14_1J9 | 11/08/2024 | 12/03/2024 | 11 | 8 | 3 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2025 | Connected |  | N
National Grid | LAWRENCE | 644839 | 01843 |  | Battery Add-On | 05_14_50L1 | 10/03/2024 | 10/09/2024 | 4 | 0 | 4 | 10/10/2024 | 10/10/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | ANDOVER | 521435 | 01810 | 10.368 | Solar | 05_14_63L1 | 05/10/2023 | 05/25/2023 | 11 | 8 | 3 | 05/26/2023 | 05/26/2023 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 491622 | 01844 | 6 | Solar | 05_14_76L3 | 01/23/2023 | 01/25/2023 | 2 | 0 | 2 | 01/26/2023 | 01/26/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 | 01/23/2023 | 9/4/2024 | Y | EXP | 365 | 07/01/2023 | 09/05/2023 | 67 | 0 | 67 |  |  | 9/18/2023 | Connected |  | Y
National Grid | HAVERHILL | 310355 | 01830 | 6 | Solar | 05_01_225W3 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 05/25/2021 | 06/15/2021 | 21 | 0 | 21 |  |  | 8/6/2021 | Connected |  | N
National Grid | LANCASTER | 175861 | 01523 | 100 | Solar | 05_01_304W6 | 08/04/2015 | 08/04/2015 | 3 | 3 | 0 | 08/10/2015 | 08/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2015 |  | 8/10/2016 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/19/2015 | 8/19/2015 | 12/18/2015 | Connected |  | N
National Grid | SUTTON | 533391 | 01590 | 16.24 | Solar | 05_01_415L3 | 06/13/2023 | 06/20/2023 | 4 | 2 | 2 | 06/21/2023 | 06/21/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2023 | Connected |  | N
National Grid | CHARLTON | 174924 | 01507 | 75 | Solar | 05_01_6W2 | 02/26/2013 | 02/26/2013 | 5 | 1 | 4 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2013 |  | 7/31/2013 | N | EXP | 7 |  |  | 0 | 0 | 0 | 7/3/2013 | 7/3/2013 | 7/19/2013 | Connected |  | N
National Grid | WORCESTER | 392747 | 01602 | 9.8 | Solar | 05_05_19W73 | 11/24/2021 | 01/06/2022 | 3 | 0 | 3 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWANSEA | 178470 | 02777 | 60 | Solar | 05_12_37W3 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/13/2018 | 03/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2018 |  |  | N | EXP | 692 |  |  | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | MEDFORD | 547517 | 02155 | 360 | Solar | 05_14_211L1 | 09/22/2023 | 10/16/2023 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 | 11/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 09/22/2023 | 7/26/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 690506 | 01843 |  | Solar | 05_14_50L1 | 05/27/2025 | 06/10/2025 | 9 | 5 | 4 | 06/11/2025 | 06/11/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | ANDOVER | 525627 | 01810 | 6 | Solar | 05_14_63L1 | 06/01/2023 | 06/05/2023 | 2 | 1 | 1 | 06/06/2023 | 06/06/2023 | 57 | 38 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 | 06/01/2023 | 10/3/2024 | Y | EXP | 365 | 12/09/2023 | 12/30/2023 | 22 | 3 | 19 |  |  | 1/18/2024 | Connected |  | N
National Grid | LAWRENCE | 559445 | 01841 | 11.05 | Solar | 05_14_76L3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 84 | 29 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 317408 | 01830 | 7.25 | Solar | 05_01_225W3 | 10/16/2020 | 10/20/2020 | 1 | 0 | 1 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175902 | 01453 | 308 | Solar | 05_01_304W6 | 09/28/2015 | 09/28/2015 | 3 | 3 | 0 | 10/02/2015 | 10/02/2015 | 254 | 0 | 254 | 01/04/2016 | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 02/23/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 10/4/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 657366 | 01590 | 7.6 | Solar | 05_01_415L3 | 11/27/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/27/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 175045 | 01566 | 246.5 | Solar | 05_01_6W2 | 09/23/2013 | 09/23/2013 | 6 | 0 | 6 | 10/02/2013 | 10/02/2013 | 335 | 0 | 335 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2014 |  | 9/1/2015 | N | EXP | 526 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 437709 | 01524 | 999 | Solar | 05_05_19W73 | 08/15/2022 | 09/13/2022 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2022 | 10/05/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2024 | 08/15/2022 | 10/31/2025 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 599355 | 02715 | 50 | Solar | 05_12_37W3 | 04/26/2024 | 05/17/2024 | 16 | 8 | 8 | 05/20/2024 | 05/20/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2024 | Connected |  | N
National Grid | MEDFORD | 690375 | 02155 | 875 | Solar | 05_14_211L1 | 06/10/2025 | 08/21/2025 | 50 | 40 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2025 | 09/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | TYNGSBORO | 266407 | 01879 | 17.6 | Solar | 05_14_50L2 | 01/31/2020 | 02/06/2020 | 4 | 3 | 1 | 02/07/2020 | 02/07/2020 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | ANDOVER | 525411 | 01810 | 6 | Solar | 05_14_63L1 | 06/12/2023 | 08/06/2023 | 38 | 33 | 5 | 08/07/2023 | 08/07/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 | 06/12/2023 | 9/23/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 2/21/2024 | Connected |  | N
National Grid | METHUEN | 566963 | 01844 | 7.6 | Solar | 05_14_76L3 | 11/10/2023 | 11/16/2023 | 4 | 1 | 3 | 11/17/2023 | 11/17/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2023 | 11/10/2023 | 5/16/2025 | Y | EXP | 5 | 06/06/2024 | 02/19/2025 | 259 | 0 | 259 |  |  | 3/1/2025 | Connected |  | N
National Grid | HAVERHILL | 337622 | 01830 | 9.57 | Solar | 05_01_225W3 | 03/12/2021 | 03/18/2021 | 3 | 0 | 3 | 03/19/2021 | 03/19/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  | 9/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | LEOMINSTER | 175978 | 01453 | 95 | Solar | 05_01_304W6 | 01/23/2015 | 01/23/2015 | 24 | 22 | 2 | 03/02/2015 | 03/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2015 |  | 6/30/2015 | N | EXP | 84 |  |  | 0 | 0 | 0 | 4/8/2015 | 4/8/2015 | 6/11/2015 | Connected |  | N
National Grid | MILLBURY | 681045 | 01527 | 11.5 | Solar | 05_01_415L3 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2025 | Connected |  | N
National Grid | STURBRIDGE | 175640 | 01566 | 354 | Solar | 05_01_6W2 | 10/20/2014 | 10/20/2014 | 8 | 4 | 4 | 10/31/2014 | 10/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2015 |  | 9/1/2016 | N | EXP | 528 |  |  | 0 | 0 | 0 | 10/23/2014 | 10/23/2014 | 6/16/2016 | Connected |  | N
National Grid | WORCESTER | 461180 | 01603 | 10 | Solar | 05_05_19W73 | 10/18/2022 | 10/20/2022 | 2 | 0 | 2 | 10/21/2022 | 10/21/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2023 | Connected |  | Y
National Grid | DIGHTON | 662041 | 02715 | 11.5 | Solar | 05_12_37W3 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | MALDEN | 724263 | 02148 | 150 | Solar | 05_14_211L1 | 10/06/2025 | 11/06/2025 | 22 | 15 | 7 | 11/07/2025 | 11/07/2025 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | TYNGSBORO | 176393 | 01879 | 56 | Solar | 05_14_50L3 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 9/8/2017 | N | EXP | 576 |  |  | 0 | 0 | 0 | 2/16/2016 | 2/16/2016 | 6/23/2017 | Connected |  | N
National Grid | ANDOVER | 546709 | 01810 | 10 | Solar | 05_14_63L1 | 08/30/2023 |  | 70 | 54 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 591663 | 01844 | 0 | Battery Add-On | 05_14_76L3 | 03/06/2024 | 03/20/2024 | 11 | 9 | 2 | 03/21/2024 | 03/21/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | HAVERHILL | 396879 | 01830 | 1500 | Solar | 05_01_225W3 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 177386 | 01453 | 17.25 | Solar | 05_01_304W6 | 11/29/2016 | 11/29/2016 | 14 | 14 | 0 | 12/20/2016 | 12/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2016 |  | 12/5/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 5/5/2017 | 5/5/2017 | 5/8/2017 | Connected |  | N
National Grid | SUTTON | 174965 | 01590 | 130 | Solar | 05_01_4J324 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2013 |  | 11/29/2013 | N | EXP | 63 |  |  | 0 | 0 | 0 | 2/20/2014 | 2/20/2014 | 2/20/2014 | Connected |  | N
National Grid | STURBRIDGE | 175981 | 01566 | 28 | Solar | 05_01_6W2 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2015 |  | 6/30/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 | 6/23/2015 | 6/23/2015 | 7/7/2015 | Connected |  | N
National Grid | WORCESTER | 480346 | 01603 | 5.22 | Solar | 05_05_19W73 | 01/09/2023 | 01/27/2023 | 13 | 10 | 3 | 01/30/2023 | 01/30/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/09/2023 | 6/23/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2023 | Connected |  | Y
National Grid | DIGHTON | 676058 | 02715 | 45.6 | Solar | 05_12_37W4 | 04/03/2025 | 04/25/2025 | 15 | 11 | 4 | 04/28/2025 | 04/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 735051 | 02155 | 250 | Solar | 05_14_211L1 | 11/27/2025 | 01/20/2026 | 35 | 27 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2026 | 02/02/2026 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | TYNGSBORO | 176499 | 01879 | 98 | Solar | 05_14_50L3 | 02/08/2016 | 02/08/2016 | 5 | 5 | 0 | 02/18/2016 | 02/18/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 4/30/2018 | N | EXP | 794 |  |  | 0 | 0 | 0 | 3/23/2018 | 3/23/2018 | 4/29/2018 | Connected |  | N
National Grid | ANDOVER | 554723 | 01810 | 7.6 | Solar | 05_14_63L1 | 09/27/2023 | 09/28/2023 | 1 | 0 | 1 | 09/29/2023 | 09/29/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 | 09/27/2023 | 12/5/2024 | Y | EXP | 365 | 01/24/2024 | 02/09/2024 | 17 | 0 | 17 |  |  | 3/5/2024 | Connected |  | N
National Grid | METHUEN | 638521 | 01844 | 6 | Solar | 05_14_76L3 | 09/10/2024 | 10/08/2024 | 16 | 11 | 5 | 10/09/2024 | 10/09/2024 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 416915 | 01830 | 9.772 | Solar | 05_01_225W3 | 03/11/2022 | 03/29/2022 | 13 | 12 | 1 | 03/30/2022 | 03/30/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2022 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | LANCASTER | 178598 | 01523 | 2500 | Solar | 05_01_304W6 | 04/06/2018 | 04/06/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/21/2018 | 68 | 53 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 175149 | 01590 | 50 | Solar | 05_01_4J324 | 10/21/2013 | 10/21/2013 | 8 | 0 | 8 | 11/01/2013 | 11/01/2013 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2014 |  | 1/6/2017 | N | EXP | 185 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176334 | 01610 | 6.67 | Solar | 05_01_6W2 | 09/15/2015 | 09/15/2015 | 4 | 4 | 0 | 09/22/2015 | 09/22/2015 | 349 | 0 | 349 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/21/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 482133 | 01602 | 8.12 | Solar | 05_05_19W73 | 12/16/2022 | 12/20/2022 | 3 | 2 | 1 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/16/2022 | 3/20/2024 | Y | EXP | 365 | 02/11/2023 | 03/17/2023 | 35 | 0 | 35 |  |  | 6/16/2023 | Connected |  | N
National Grid | DIGHTON | 748843 | 02715 | 5.76 | Solar | 05_12_37W4 | 02/02/2026 | 02/12/2026 | 7 | 4 | 3 | 02/13/2026 | 02/13/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MEDFORD | 174305 | 02155 | 475 | Solar | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 5/16/2012 | N | EXP | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 202797 | 01879 | 0 | Solar | 05_14_50L3 | 12/06/2018 | 12/18/2018 | 7 | 0 | 7 | 12/19/2018 | 12/19/2018 | 149 | 21 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 570739 | 01810 | 9.28 | Solar | 05_14_63L1 | 11/22/2023 | 11/29/2023 | 5 | 2 | 3 | 11/30/2023 | 11/30/2023 | 30 | 7 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/22/2023 | 1/21/2025 | Y | EXP | 365 | 05/14/2024 | 06/07/2024 | 25 | 0 | 25 |  |  | 6/14/2024 | Connected |  | N
National Grid | METHUEN | 645705 | 01844 | 6.72 | Solar | 05_14_76L3 | 10/08/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/08/2024 | 1/23/2026 | Y | EXP | 365 | 05/10/2025 | 11/21/2025 | 196 | 0 | 196 |  |  | 12/2/2025 | Connected |  | N
National Grid | HAVERHILL | 426808 | 01830 | 9.57 | Solar | 05_01_225W3 | 07/14/2022 | 08/04/2022 | 16 | 9 | 7 | 08/05/2022 | 08/05/2022 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 10/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2023 | Connected |  | N
National Grid | LEOMINSTER | 178682 | 01453 | 4000 | Solar | 05_01_304W6 | 04/11/2018 | 04/11/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 11/05/2018 | 137 | 0 | 137 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLBURY | 178291 | 01527 | 200 | Solar | 05_01_4J324 | 03/28/2018 | 04/20/2018 | 15 | 15 | 0 | 04/20/2018 | 04/20/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 12/2/2019 | N | EXP | 382 |  |  | 0 | 0 | 0 |  |  | 11/7/2019 | Connected |  | N
National Grid | WORCESTER | 176843 | 01610 | 6 | Solar | 05_01_6W2 | 05/02/2016 | 05/02/2016 | 2 | 2 | 0 | 05/05/2016 | 05/05/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2016 | 05/02/2016 | 1/8/2018 | Y | EXP | 66 | 10/31/2016 | 10/25/2016 | 0 | 0 | 0 | 5/31/2017 | 5/31/2017 | 5/31/2017 | Connected |  | N
National Grid | WORCESTER | 484704 | 01603 | 8.7 | Solar | 05_05_19W73 | 01/10/2023 | 01/11/2023 | 1 | 0 | 1 | 01/12/2023 | 01/12/2023 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 | 01/10/2023 | 4/14/2024 | Y | EXP | 365 | 03/04/2023 | 04/13/2023 | 41 | 0 | 41 |  |  | 7/17/2023 | Connected |  | N
National Grid | DIGHTON | 175484 | 02715 | 75 | Natural Gas | 05_12_37W4 | 03/18/2014 | 03/18/2014 | 8 | 2 | 6 | 03/31/2014 | 03/31/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2014 |  | 9/30/2014 | N | EXP | 172 |  |  | 0 | 0 | 0 | 10/15/2014 | 10/15/2014 | 10/28/2014 | Connected |  | N
National Grid | MEDFORD | 175050 | 02155 | 37.8 | Solar | 05_14_211L1 | 08/10/2012 | 08/10/2012 | 5 | 0 | 5 | 08/20/2012 | 08/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/15/2012 | N | EXP | 27 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 12/9/2013 | Connected |  | N
National Grid | TYNGSBORO | 311831 | 01879 | 250 | Solar | 05_14_50L3 | 09/11/2020 | 09/16/2020 | 2 | 0 | 2 | 09/17/2020 | 09/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 8/20/2025 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 572865 | 01810 | 3.8 | Solar | 05_14_63L1 | 11/29/2023 | 12/05/2023 | 4 | 0 | 4 | 12/06/2023 | 12/06/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | METHUEN | 648301 | 01844 | 5.76 | Solar | 05_14_76L3 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | HAVERHILL | 437424 | 01830 | 0 | Other | 05_01_225W3 | 09/22/2022 | 10/18/2022 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 11/09/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 184056 | 01453 | 999 | Battery Add-On | 05_01_304W6 | 05/01/2018 | 05/01/2018 | 6 | 0 | 6 |  |  | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 184789 | 01590 | 249.8 | Solar | 05_01_4J324 | 05/08/2017 | 05/08/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 08/23/2018 | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 |  | 03/12/2019 | 135 | 21 | 114 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177158 | 01608 | 10 | Solar | 05_01_6W2 | 10/26/2016 | 10/26/2016 | 3 | 3 | 0 | 11/01/2016 | 11/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2016 | 10/26/2016 | 11/1/2017 | Y | EXP | 363 | 04/17/2017 | 04/25/2017 | 5 | 0 | 5 | 5/18/2017 | 5/18/2017 | 5/18/2017 | Connected |  | N
National Grid | WORCESTER | 486122 | 01602 | 10 | Solar | 05_05_19W73 | 01/03/2023 | 01/04/2023 | 1 | 0 | 1 | 01/05/2023 | 01/05/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2023 |  | 2/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | DIGHTON | 176729 | 02764 | 150 | Solar | 05_12_37W4 | 04/25/2016 | 04/25/2016 | 1 | 1 | 0 | 04/27/2016 | 04/27/2016 | 279 | 9 | 270 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 |  | 5/1/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 175350 | 02148 | 491 | Solar | 05_14_211L1 | 01/01/2012 | 01/01/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2014 | 01/01/2012 | 12/31/2014 | Y | EXP | 117 | 05/04/2015 | 05/22/2015 | 14 | 0 | 14 | 9/17/2014 | 9/17/2014 | 5/27/2015 | Connected |  | N
National Grid | TYNGSBORO | 406250 | 01879 | 10 | Solar | 05_14_50L3 | 05/04/2022 | 06/06/2022 | 22 | 19 | 3 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 | 05/04/2022 | 5/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | Y
National Grid | ANDOVER | 579133 | 01810 | 9.57 | Solar | 05_14_63L1 | 12/21/2023 | 12/22/2023 | 1 | 0 | 1 | 12/26/2023 | 12/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 655955 | 01844 | 10 | Solar | 05_14_76L3 | 11/21/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | HAVERHILL | 466225 | 01830 | 13.824 | Solar | 05_01_225W3 | 10/18/2022 | 11/01/2022 | 10 | 8 | 2 | 11/02/2022 | 11/02/2022 | 51 | 31 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 2/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2023 | Connected |  | N
National Grid | LEOMINSTER | 184748 | 01453 | 594 | Solar | 05_01_304W6 | 05/31/2018 | 08/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/22/2018 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2019 |  | 8/21/2020 | N | STD | 43 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 197101 | 01590 | 25 | Solar | 05_01_4J324 | 09/27/2018 | 10/04/2018 | 8 | 5 | 3 | 10/11/2018 | 10/11/2018 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 |  | 10/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178137 | 01608 | 3.8 | Solar | 05_01_6W2 | 03/22/2018 | 04/05/2018 | 9 | 9 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/28/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 498979 | 01603 | 7.54 | Solar | 05_05_19W73 | 03/08/2023 | 03/10/2023 | 2 | 0 | 2 | 03/13/2023 | 03/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | N
National Grid | DIGHTON | 177838 | 02764 | 3.8 | Solar | 05_12_37W4 | 10/13/2017 | 10/13/2017 | 11 | 10 | 1 | 10/31/2017 | 10/31/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/18/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 175496 | 02155 | 68.4 | Solar | 05_14_211L1 | 09/25/2014 | 09/25/2014 | 6 | 0 | 6 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 09/25/2014 | 12/31/2014 | Y | EXP | 51 | 01/23/2015 | 02/19/2015 | 18 | 0 | 18 | 2/26/2015 | 2/26/2015 | 4/16/2015 | Connected |  | N
National Grid | TYNGSBORO | 484404 | 01879 | 14.5 | Solar | 05_14_50L3 | 03/06/2023 | 03/24/2023 | 14 | 12 | 2 | 03/27/2023 | 03/27/2023 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 8/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | ANDOVER | 580779 | 01810 | 5.8 | Solar | 05_14_63L1 | 02/08/2024 | 02/21/2024 | 9 | 5 | 4 | 02/22/2024 | 02/22/2024 | 9 | 6 | 3 | 03/29/2024 | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2024 |  | 4/25/2025 | N | EXP | 365 | 06/06/2024 | 02/12/2025 | 126 | 0 | 126 |  |  | 10/29/2024 | Connected |  | N
National Grid | METHUEN | 703835 | 01844 | 6.46 | Solar | 05_14_76L3 | 07/11/2025 | 07/14/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | HAVERHILL | 491913 | 01830 | 3.8 | Solar | 05_01_225W3 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 02/01/2023 | 6/7/2024 | Y | EXP | 365 | 05/02/2023 | 06/08/2023 | 38 | 0 | 38 |  |  | 8/10/2023 | Connected |  | N
National Grid | LANCASTER | 189175 | 01523 | 2050 | Solar | 05_01_304W6 | 09/11/2018 | 10/18/2018 | 23 | 15 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 11/23/2018 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 202335 | 01590 | 72 | Solar | 05_01_4J324 | 11/29/2018 | 12/04/2018 | 2 | 0 | 2 | 12/05/2018 | 12/05/2018 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 12/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178216 | 01609 | 7.6 | Solar | 05_01_6W2 | 04/13/2018 | 04/13/2018 | 14 | 0 | 14 | 05/04/2018 | 05/04/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2018 |  | 4/21/2019 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 578440 | 01603 | 10 | Solar | 05_05_19W73 | 12/20/2023 | 01/03/2024 | 7 | 3 | 4 | 01/04/2024 | 01/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 2/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2024 | Connected |  | N
National Grid | DIGHTON | 233361 | 02715 | 7.6 | Solar | 05_12_37W4 | 07/05/2019 | 07/15/2019 | 5 | 0 | 5 | 07/16/2019 | 07/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/05/2019 | 8/20/2021 | Y | EXP | 365 | 10/15/2020 | 08/09/2021 | 293 | 0 | 293 |  |  | 8/14/2021 | Connected |  | N
National Grid | MEDFORD | 175775 | 02155 | 60 | Solar | 05_14_211L1 | 08/15/2014 | 08/15/2014 | 7 | 0 | 7 | 08/27/2014 | 08/27/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2014 |  | 11/28/2014 | N | EXP | 7 |  |  | 0 | 0 | 0 | 9/19/2014 | 9/19/2014 | 11/24/2014 | Connected |  | N
National Grid | TYNGSBORO | 492109 | 01879 | 9.86 | Solar | 05_14_50L3 | 01/24/2023 | 02/06/2023 | 10 | 9 | 1 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 4/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2023 | Connected |  | N
National Grid | ANDOVER | 580403 | 01810 | 10 | Solar | 05_14_63L1 | 01/12/2024 | 03/04/2024 | 27 | 25 | 2 | 03/05/2024 | 03/05/2024 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 | 01/12/2024 | 4/4/2025 | Y | EXP | 365 | 06/06/2024 | 09/11/2024 | 98 | 0 | 98 |  |  | 10/7/2024 | Connected |  | N
National Grid | METHUEN | 742161 | 01844 | 5.76 | Solar | 05_14_77L1 | 12/24/2025 | 12/29/2025 | 2 | 0 | 2 | 12/30/2025 | 12/30/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 564107 | 01830 | 10 | Solar | 05_01_225W3 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/08/2023 | 1/2/2025 | Y | EXP | 365 | 05/16/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 7/5/2024 | Connected |  | N
National Grid | LEOMINSTER | 202902 | 01453 | 0 | Battery Add-On | 05_01_304W6 | 12/06/2018 | 12/14/2018 | 2 | 0 | 2 | 12/17/2018 | 12/17/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2019 |  | 1/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | Connected |  | N
National Grid | SUTTON | 321058 | 01590 | 75 | Natural Gas | 05_01_4J324 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 187 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | WORCESTER | 178252 | 01610 | 11.4 | Solar | 05_01_6W2 | 03/27/2018 | 04/03/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 | 03/27/2018 | 4/10/2020 | Y | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 3/20/2020 | Connected |  | N
National Grid | WORCESTER | 580411 | 01602 | 3.8 | Solar | 05_05_19W73 | 01/16/2024 | 01/19/2024 | 3 | 0 | 3 | 01/22/2024 | 01/22/2024 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/16/2024 | 2/20/2025 | Y | EXP | 365 | 04/17/2024 | 05/31/2024 | 45 | 0 | 45 |  |  | 10/14/2024 | Connected |  | N
National Grid | DIGHTON | 243069 | 02764 | 7.6 | Solar | 05_12_37W4 | 10/25/2019 | 10/30/2019 | 2 | 0 | 2 | 10/31/2019 | 10/31/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  | 10/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 176422 | 02155 | 2000 | Solar | 05_14_211L1 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 03/08/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/9/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 682703 | 01879 | 0 | Battery Add-On | 05_14_50L3 | 04/03/2025 | 05/02/2025 | 21 | 17 | 4 | 05/05/2025 | 05/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/03/2025 | 7/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | ANDOVER | 590846 | 01810 | 5 | Solar | 05_14_63L1 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/07/2024 | 8/29/2025 | Y | EXP | 365 | 10/03/2024 | 03/07/2025 | 156 | 0 | 156 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 751319 | 01844 | 11.4 | Solar | 05_14_77L1 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 587327 | 01854 | 19 | Solar | 05_01_225W3 | 02/01/2024 | 02/06/2024 | 3 | 1 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 292740 | 01453 | 192 | Solar | 05_01_304W6 | 05/22/2020 | 06/16/2020 | 15 | 11 | 4 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 174963 | 01590 | 60 | Solar | 05_01_4J336 | 08/30/2013 | 08/30/2013 | 7 | 0 | 7 | 09/12/2013 | 09/12/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2013 |  | 11/29/2013 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 2/28/2014 | Connected |  | N
National Grid | WORCESTER | 178734 | 01610 | 3.8 | Solar | 05_01_6W2 | 02/12/2018 | 03/07/2018 | 0 | 0 | 0 | 03/07/2018 | 03/07/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2018 |  | 2/18/2019 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 622852 | 01602 | 10 | Solar | 05_05_19W73 | 07/09/2024 | 08/13/2024 | 4 | 1 | 3 | 08/14/2024 | 08/14/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 250240 | 02715 | 7.6 | Solar | 05_12_37W4 | 08/22/2019 | 09/18/2019 | 18 | 18 | 0 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 6/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 177132 | 02155 | 566.1 | Solar | 05_14_211L1 | 01/23/2017 | 01/23/2017 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/29/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 699800 | 01879 | 9.69 | Solar | 05_14_50L3 | 06/19/2025 | 07/02/2025 | 1 | 0 | 1 | 07/29/2025 | 07/29/2025 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  | 9/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | ANDOVER | 600702 | 01810 | 5 | Solar | 05_14_63L1 | 07/02/2024 | 07/09/2024 | 4 | 0 | 4 | 07/10/2024 | 07/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | LAWRENCE | 176630 | 01841 | 10 | Solar | 05_14_77L1 | 10/15/2015 | 10/15/2015 | 3 | 3 | 0 | 10/21/2015 | 10/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/21/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 8/19/2016 | 8/19/2016 | 8/19/2016 | Connected |  | N
National Grid | LOWELL | 595356 | 01854 | 7.6 | Solar | 05_01_225W3 | 03/15/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 | 03/15/2024 | 4/4/2025 | Y | EXP | 365 | 06/11/2024 | 06/18/2024 | 8 | 0 | 8 |  |  | 6/27/2024 | Connected |  | Y
National Grid | LANCASTER | 294263 | 01523 | 10 | Solar | 05_01_304W6 | 06/02/2020 | 06/15/2020 | 8 | 8 | 0 | 06/16/2020 | 06/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | N
National Grid | SUTTON | 514581 | 01590 | 9.6 | Solar | 05_01_4J336 | 03/30/2023 | 05/30/2023 | 41 | 40 | 1 | 05/31/2023 | 05/31/2023 | 35 | 13 | 22 | 08/07/2023 | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 |  | 03/28/2024 | 162 | 28 | 134 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 197997 | 01610 | 6 | Solar | 05_01_6W2 | 11/05/2018 | 01/14/2019 | 6 | 0 | 6 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 623790 | 01603 | 5.76 | Solar | 05_05_19W73 | 07/10/2024 | 07/30/2024 | 2 | 0 | 2 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 258934 | 02764 | 3.8 | Solar | 05_12_37W4 | 10/12/2019 | 10/14/2019 | 0 | 0 | 0 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 11/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 178607 | 02155 | 150 | Solar | 05_14_211L1 | 12/12/2017 | 12/12/2017 | 24 | 12 | 12 | 01/19/2018 | 01/19/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2018 |  | 12/18/2018 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | TYNGSBORO | 586777 | 01879 | 7.6 | Solar | 05_14_53J1 | 02/26/2024 | 05/08/2024 | 51 | 48 | 3 | 05/09/2024 | 05/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 |  | 5/30/2025 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | ANDOVER | 604153 | 01810 | 5.76 | Solar | 05_14_63L1 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/18/2024 | 5/8/2025 | Y | EXP | 365 | 07/18/2024 | 11/18/2024 | 124 | 0 | 124 |  |  | 2/6/2025 | Connected |  | N
National Grid | LAWRENCE | 176717 | 01841 | 5 | Solar | 05_14_77L1 | 01/11/2016 | 01/11/2016 | 3 | 3 | 0 | 01/15/2016 | 01/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2016 |  | 1/17/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 8/1/2016 | 8/1/2016 | 8/2/2016 | Connected |  | N
National Grid | LOWELL | 614607 | 01854 | 10 | Solar | 05_01_225W3 | 05/31/2024 | 06/06/2024 | 3 | 1 | 2 | 06/07/2024 | 06/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/31/2024 | 6/24/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | LEOMINSTER | 305873 | 01453 | 1750 | Solar | 05_01_304W6 | 10/05/2020 | 10/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2020 | 11/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 616884 | 01590 | 5.76 | Solar | 05_01_4J336 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2024 | Connected |  | N
National Grid | WORCESTER | 204022 | 01610 | 3.8 | Solar | 05_01_6W2 | 02/21/2019 | 03/07/2019 | 10 | 10 | 0 | 03/08/2019 | 03/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 630724 | 01603 | 10 | Solar | 05_05_19W73 | 08/07/2024 | 09/24/2024 | 13 | 10 | 3 | 09/25/2024 | 09/25/2024 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 08/07/2024 | 1/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 323871 | 02715 | 7.6 | Solar | 05_12_37W4 | 01/11/2021 | 01/22/2021 | 7 | 7 | 0 | 01/25/2021 | 01/25/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 1/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 178719 | 02155 | 86.19 | Solar | 05_14_211L1 | 04/12/2018 | 04/12/2018 | 380 | 24 | 356 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 642635 | 01879 | 10 | Solar | 05_14_53J1 | 09/24/2024 |  | 19 | 16 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 614412 | 01840 | 5.76 | Solar | 05_14_63L1 | 05/30/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2025 | Connected |  | N
National Grid | LAWRENCE | 178127 | 01841 | 10 | Solar | 05_14_77L1 | 07/11/2017 | 07/11/2017 | 4 | 4 | 0 | 07/18/2017 | 07/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 |  | 7/17/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/24/2018 | 1/24/2018 | 1/24/2018 | Connected |  | N
National Grid | LOWELL | 622239 | 01854 | 5.76 | Solar | 05_01_225W3 | 07/02/2024 | 07/17/2024 | 1 | 0 | 1 | 07/18/2024 | 07/18/2024 | 50 | 31 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 | 07/02/2024 | 10/10/2025 | Y | EXP | 365 | 12/03/2024 | 12/16/2024 | 14 | 0 | 14 |  |  | 4/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 308498 | 01453 | 4990 | Solar | 05_01_304W6 | 09/14/2020 | 09/28/2020 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/29/2020 | 10/24/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 636567 | 01590 | 10 | Solar | 05_01_4J336 | 08/29/2024 | 09/09/2024 | 3 | 0 | 3 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | WORCESTER | 218065 | 01610 | 792.6 | Solar | 05_01_6W2 | 06/07/2019 | 09/17/2019 | 70 | 69 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/18/2019 | 10/04/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 06/07/2019 | 4/27/2023 | Y | STD | 782 | 06/04/2021 | 03/09/2023 | 644 | 7 | 637 | 3/10/2023 | 4/3/2023 | 4/17/2023 | Connected |  | N
National Grid | WORCESTER | 643457 | 01603 | 7.6 | Solar | 05_05_19W73 | 09/27/2024 | 11/01/2024 | 7 | 2 | 5 | 11/04/2024 | 11/04/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 09/27/2024 | 2/14/2026 | Y | EXP | 365 | 03/19/2025 | 04/21/2025 | 34 | 0 | 34 |  |  | 5/16/2025 | Connected |  | N
National Grid | DIGHTON | 331642 | 02715 | 10 | Solar | 05_12_37W4 | 12/15/2020 | 12/21/2020 | 3 | 0 | 3 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 | 12/15/2020 | 12/16/2021 | Y | EXP | 365 | 04/16/2021 | 05/04/2021 | 18 | 0 | 18 |  |  | 6/28/2021 | Connected |  | N
National Grid | MEDFORD | 185409 | 02155 | 4999 | Solar | 05_14_211L1 | 06/15/2018 | 06/15/2018 | 32 | 32 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2018 | 08/17/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2019 | 06/15/2018 | 8/6/2021 | Y | STD | 498 | 03/04/2020 | 05/27/2021 | 450 | 5 | 445 |  |  | 8/2/2021 | Connected |  | N
National Grid | TYNGSBORO | 699429 | 01879 | 10 | Solar | 05_14_53J1 | 06/18/2025 | 07/03/2025 | 19 | 15 | 4 | 08/12/2025 | 08/12/2025 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | LAWRENCE | 618251 | 01841 | 6 | Solar | 05_14_63L1 | 06/17/2024 | 07/02/2024 | 1 | 0 | 1 | 07/03/2024 | 07/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | LAWRENCE | 196418 | 01841 | 100 | Solar | 05_14_77L1 | 09/19/2018 | 10/04/2018 | 2 | 0 | 2 | 10/05/2018 | 10/05/2018 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 7/6/2020 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 653119 | 01854 | 11.78 | Solar | 05_01_225W3 | 11/08/2024 | 12/02/2024 | 3 | 0 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | LEOMINSTER | 310798 | 01453 | 4990 | Solar | 05_01_304W6 | 09/17/2020 | 09/30/2020 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 636464 | 01590 | 6 | Solar | 05_01_4J336 | 09/16/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WORCESTER | 219190 | 01603 | 3.8 | Solar | 05_01_6W2 | 04/11/2019 | 06/26/2019 | 4 | 0 | 4 | 06/27/2019 | 06/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 646259 | 01603 | 3.8 | Solar | 05_05_19W73 | 10/17/2024 | 12/16/2024 | 7 | 0 | 7 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | DIGHTON | 347803 | 02764 | 4.64 | Solar | 05_12_37W4 | 04/07/2021 | 01/06/2022 | 4 | 0 | 4 | 04/15/2021 | 04/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 1/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2022 | Connected |  | N
National Grid | MEDFORD | 185918 | 02155 | 37.8 | Solar | 05_14_211L1 | 05/22/2018 | 05/22/2018 | 4 | 0 | 4 | 05/30/2018 | 05/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 5/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2019 | Connected |  | N
National Grid | TYNGSBORO | 662479 | 01879 | 7.6 | Solar | 05_14_53J2 | 12/24/2024 | 03/04/2025 | 0 | 0 | 0 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 619181 | 01841 | 10 | Solar | 05_14_63L1 | 06/20/2024 | 07/15/2024 | 4 | 0 | 4 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/20/2024 | 8/23/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | METHUEN | 374425 | 01844 | 7.68 | Solar | 05_14_77L1 | 01/12/2022 | 01/18/2022 | 3 | 0 | 3 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 | 01/12/2022 | 1/14/2024 | Y | EXP | 365 | 05/26/2022 | 01/13/2023 | 232 | 0 | 232 |  |  | 1/25/2023 | Connected |  | N
National Grid | LOWELL | 666473 | 01854 | 18.24 | Solar | 05_01_225W3 | 01/17/2025 | 03/05/2025 | 20 | 15 | 5 | 03/06/2025 | 03/06/2025 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | LEOMINSTER | 348697 | 01453 | 9.28 | Solar | 05_01_304W6 | 04/06/2021 | 04/07/2021 | 0 | 0 | 0 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2022 | Connected |  | N
National Grid | SUTTON | 651217 | 01590 | 7.6 | Solar | 05_01_4J336 | 11/01/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 | 12/31/2024 | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  | 03/25/2025 | 58 | 0 | 58 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | WORCESTER | 236417 | 01603 | 7.6 | Solar | 05_01_6W2 | 06/27/2019 | 07/05/2019 | 5 | 5 | 0 | 07/08/2019 | 07/08/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2019 | 06/27/2019 | 6/27/2020 | Y | EXP | 365 | 03/28/2020 | 04/22/2020 | 25 | 0 | 25 |  |  | 4/24/2020 | Connected |  | N
National Grid | WORCESTER | 653935 | 01603 | 5.76 | Solar | 05_05_19W73 | 11/18/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/18/2024 | 2/6/2026 | Y | EXP | 365 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 4/22/2025 | Connected |  | N
National Grid | SWANSEA | 359749 | 02777 | 15 | Solar | 05_12_37W4 | 08/24/2021 | 04/28/2022 | 168 | 159 | 9 | 04/29/2022 | 04/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 186232 | 02155 | 249.8 | Solar | 05_14_211L1 | 05/24/2018 | 05/24/2018 | 2 | 0 | 2 | 05/31/2018 | 05/31/2018 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 | 05/24/2018 | 8/31/2021 | Y | EXP | 455 |  |  | 0 | 0 | 0 |  |  | 8/20/2021 | Connected |  | N
National Grid | TYNGSBORO | 710450 | 01879 | 10 | Solar | 05_14_53J2 | 08/07/2025 | 09/17/2025 | 4 | 0 | 4 | 09/26/2025 | 09/26/2025 | 19 | 2 | 17 | 10/30/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 622624 | 01841 | 3.8 | Solar | 05_14_63L1 | 07/04/2024 | 07/11/2024 | 2 | 0 | 2 | 07/12/2024 | 07/12/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | METHUEN | 480217 | 01844 | 7.6 | Solar | 05_14_77L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 2 | 19 | 02/23/2023 | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | Y
National Grid | LOWELL | 673213 | 01854 | 23 | Solar | 05_01_225W3 | 02/20/2025 | 05/06/2025 | 52 | 50 | 2 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | LEOMINSTER | 382260 | 01453 | 7.6 | Solar | 05_01_304W6 | 09/15/2021 | 09/17/2021 | 2 | 1 | 1 | 09/20/2021 | 09/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 3/17/2023 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 656746 | 01590 | 5.76 | Solar | 05_01_4J336 | 11/25/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | WORCESTER | 256583 | 01610 | 3.8 | Solar | 05_01_6W2 | 10/08/2019 | 10/09/2019 | 0 | 0 | 0 | 10/10/2019 | 10/10/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 10/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2020 | Connected |  | N
National Grid | WORCESTER | 673697 | 01603 | 3.8 | Solar | 05_05_19W73 | 02/24/2025 | 03/14/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 104 | 90 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 469990 | 02715 | 0 | Solar | 05_12_37W4 | 11/09/2022 | 12/19/2022 | 27 | 26 | 1 | 12/20/2022 | 12/20/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 4/20/2024 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 186708 | 02155 | 249.8 | Solar | 05_14_211L1 | 05/30/2018 | 05/30/2018 | 1 | 0 | 1 | 06/04/2018 | 06/04/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2018 | 05/30/2018 | 10/30/2020 | Y | EXP | 598 | 09/25/2020 | 09/24/2020 | 0 | 0 | 0 |  |  | 10/28/2020 | Connected |  | N
National Grid | TYNGSBORO | 723314 | 01879 | 12.76 | Solar | 05_14_53J2 | 10/01/2025 | 10/17/2025 | 1 | 0 | 1 | 10/30/2025 | 10/30/2025 | 26 | 9 | 17 | 12/12/2025 | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 12/17/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LAWRENCE | 627956 | 01841 | 7.6 | Solar | 05_14_63L1 | 07/26/2024 | 08/07/2024 | 3 | 0 | 3 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/26/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | LAWRENCE | 543280 | 01841 | 240 | Solar | 05_14_77L1 | 08/01/2023 | 08/16/2023 | 11 | 0 | 11 | 08/17/2023 | 08/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 08/01/2023 | 1/10/2026 | Y | EXP | 49 | 04/11/2025 | 04/18/2025 | 8 | 0 | 8 |  |  | 12/31/2025 | Connected |  | N
National Grid | LOWELL | 675974 | 01854 | 5.76 | Solar | 05_01_225W3 | 03/07/2025 | 03/12/2025 | 3 | 0 | 3 | 03/13/2025 | 03/13/2025 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 457862 | 01453 | 1800 | Solar | 05_01_304W6 | 11/03/2022 | 11/17/2022 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 656348 | 01590 | 7.6 | Solar | 05_01_4J336 | 11/22/2024 | 03/04/2025 | 55 | 50 | 5 | 03/05/2025 | 03/05/2025 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | WORCESTER | 265671 | 01603 | 7.6 | Solar | 05_01_6W2 | 12/04/2019 | 12/17/2019 | 9 | 9 | 0 | 12/18/2019 | 12/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2019 |  | 5/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | WORCESTER | 700565 | 01602 | 11.4 | Solar | 05_05_19W73 | 06/24/2025 | 08/01/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 06/24/2025 | 9/7/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | DIGHTON | 541845 | 02715 | 15.66 | Solar | 05_12_37W4 | 07/24/2023 |  | 96 | 70 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 200571 | 02155 | 883.2 | Solar | 05_14_211L1 | 06/04/2019 | 07/29/2019 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2019 | 08/28/2019 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 177566 | 01879 | 15.2 | Solar | 05_14_53J2 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | LAWRENCE | 633390 | 01841 | 5 | Solar | 05_14_63L1 | 08/19/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/19/2024 | 10/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | METHUEN | 576639 | 01844 | 9.984 | Solar | 05_14_77L1 | 12/14/2023 | 01/22/2024 | 24 | 23 | 1 | 01/23/2024 | 01/23/2024 | 82 | 65 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 679537 | 01854 | 15.2 | Solar | 05_01_225W3 | 03/24/2025 | 06/05/2025 | 0 | 0 | 0 | 06/06/2025 | 06/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | LEOMINSTER | 473792 | 01453 | 9.28 | Solar | 05_01_304W6 | 12/07/2022 | 12/14/2022 | 6 | 5 | 1 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2023 | Connected |  | N
National Grid | MILLBURY | 730887 | 01527 | 11.4 | Solar | 05_01_4J339 | 11/03/2025 | 11/04/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 274538 | 01603 | 48 | Natural Gas | 05_01_6W2 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 | 03/08/2021 | 03/08/2021 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 6/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | WORCESTER | 717276 | 01602 | 10 | Solar | 05_05_19W73 | 09/07/2025 | 10/08/2025 | 3 | 0 | 3 | 10/29/2025 | 10/29/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | DIGHTON | 578165 | 02715 | 10 | Solar | 05_12_37W4 | 12/20/2023 | 01/04/2024 | 8 | 8 | 0 | 01/05/2024 | 01/05/2024 | 19 | 0 | 19 | 02/05/2024 | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 03/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/26/2025 | N | EXP | 365 | 03/16/2024 | 07/23/2024 | 130 | 29 | 101 |  |  | 8/5/2024 | Connected |  | N
National Grid | MEDFORD | 203063 | 02155 | 250 | Solar | 05_14_211L1 | 12/06/2018 | 01/02/2019 | 14 | 10 | 4 | 01/03/2019 | 01/03/2019 | 17 | 0 | 17 | 07/12/2019 | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 07/11/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  | 6/9/2021 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | TYNGSBORO | 521243 | 01879 | 10 | Solar | 05_14_53J2 | 05/25/2023 | 05/26/2023 | 1 | 0 | 1 | 05/30/2023 | 05/30/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 635398 | 01841 | 7.6 | Solar | 05_14_63L1 | 08/26/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 110 | 24 | 86 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 579700 | 01844 | 6 | Solar | 05_14_77L1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | LOWELL | 687754 | 01854 | 10 | Solar | 05_01_225W3 | 05/01/2025 | 05/15/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | LEOMINSTER | 570231 | 01453 | 10 | Solar | 05_01_304W6 | 11/16/2023 | 11/21/2023 | 3 | 1 | 2 | 11/22/2023 | 11/22/2023 | 41 | 17 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 11/16/2023 | 1/31/2025 | Y | EXP | 365 | 06/05/2024 | 08/28/2024 | 85 | 0 | 85 |  |  | 9/5/2024 | Connected |  | N
National Grid | SUTTON | 643519 | 01590 | 19 | Solar | 05_01_4J339 | 10/01/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 165 | 146 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 291970 | 01610 | 3.8 | Solar | 05_01_6W2 | 06/16/2020 | 06/17/2020 | 0 | 0 | 0 | 06/18/2020 | 06/18/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2020 |  | 6/16/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 719867 | 01602 | 23 | Solar | 05_05_19W74 | 09/17/2025 | 10/17/2025 | 19 | 17 | 2 | 10/20/2025 | 10/20/2025 | 94 | 84 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SWANSEA | 580959 | 02777 | 23 | Solar | 05_12_37W4 | 01/02/2024 | 03/14/2024 | 44 | 43 | 1 | 03/15/2024 | 03/15/2024 | 41 | 36 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 01/02/2024 | 5/23/2025 | Y | EXP | 365 | 07/03/2024 | 07/18/2024 | 16 | 0 | 16 |  |  | 9/25/2024 | Connected |  | N
National Grid | MEDFORD | 207367 | 02155 | 72 | Solar | 05_14_211L1 | 01/28/2019 | 02/26/2019 | 7 | 2 | 5 | 02/27/2019 | 02/27/2019 | 30 | 21 | 9 | 04/22/2019 | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 |  | 08/08/2019 | 77 | 9 | 68 |  |  | 0 | 0 | 0 | 8/29/2019 | 01/28/2019 | 12/28/2021 | Y | EXP | 739 | 12/10/2021 | 12/09/2021 | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | TYNGSBORO | 538670 | 01879 | 12.76 | Solar | 05_14_53J2 | 09/05/2023 | 02/07/2024 | 105 | 95 | 10 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 | 02/27/2024 | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  | 04/16/2024 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 4/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 637653 | 01841 | 10 | Solar | 05_14_63L1 | 09/04/2024 | 09/19/2024 | 3 | 0 | 3 | 09/20/2024 | 09/20/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 | 09/04/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 598862 | 01841 | 7.6 | Solar | 05_14_77L1 | 04/05/2024 | 04/12/2024 | 5 | 0 | 5 | 04/16/2024 | 04/16/2024 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | LOWELL | 695812 | 01854 | 10 | Solar | 05_01_225W3 | 06/05/2025 | 07/01/2025 | 2 | 0 | 2 | 07/08/2025 | 07/08/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2025 | Connected |  | N
National Grid | LEOMINSTER | 634466 | 01453 | 15.705 | Solar | 05_01_304W6 | 08/27/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2024 | Connected |  | N
National Grid | SUTTON | 647997 | 01590 | 15.2 | Solar | 05_01_4J339 | 10/17/2024 | 11/12/2024 | 17 | 15 | 2 | 11/13/2024 | 11/13/2024 | 74 | 49 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | WORCESTER | 318228 | 01610 | 10 | Solar | 05_01_6W2 | 11/02/2020 | 11/13/2020 | 7 | 6 | 1 | 11/16/2020 | 11/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/02/2020 | 10/14/2022 | Y | EXP | 365 | 07/02/2021 | 10/13/2021 | 104 | 3 | 101 |  |  | 1/10/2022 | Connected |  | N
National Grid | WORCESTER | 721916 | 01602 | 20 | Solar | 05_05_19W74 | 10/16/2025 | 10/22/2025 | 3 | 1 | 2 | 10/23/2025 | 10/23/2025 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 10/16/2025 | 1/8/2027 | Y | EXP | 365 | 01/30/2026 | 02/11/2026 | 13 | 0 | 13 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 608550 | 02764 | 6 | Solar | 05_12_37W4 | 05/03/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/03/2024 | 7/3/2025 | Y | EXP | 365 | 08/20/2024 | 01/20/2025 | 154 | 0 | 154 |  |  | 2/3/2025 | Connected |  | N
National Grid | MEDFORD | 268890 | 02155 | 249.5 | Solar | 05_14_211L1 | 02/21/2020 | 03/27/2020 | 25 | 23 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2020 | 04/24/2020 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 600641 | 01879 | 7.6 | Solar | 05_14_53J2 | 04/12/2024 | 05/30/2024 | 1 | 0 | 1 | 05/31/2024 | 05/31/2024 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 04/12/2024 | 10/4/2025 | Y | EXP | 365 | 08/22/2024 | 09/11/2024 | 21 | 0 | 21 |  |  | 12/6/2024 | Connected |  | N
National Grid | LAWRENCE | 642797 | 01841 | 15.2 | Solar | 05_14_63L1 | 09/25/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 | 09/25/2024 | 5/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | LAWRENCE | 628395 | 01841 | 7.6 | Solar | 05_14_77L1 | 07/29/2024 | 08/02/2024 | 1 | 0 | 1 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 07/29/2024 | 10/8/2025 | Y | EXP | 365 | 10/04/2024 | 11/22/2024 | 50 | 0 | 50 |  |  | 3/13/2025 | Connected |  | Y
National Grid | LOWELL | 711810 | 01854 | 10 | Solar | 05_01_225W3 | 08/13/2025 | 08/26/2025 | 8 | 5 | 3 | 08/27/2025 | 08/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | LEOMINSTER | 644551 | 01453 | 10 | Solar | 05_01_304W6 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 6/19/2026 | Y | EXP | 365 | 11/14/2025 | 02/13/2026 | 92 | 0 | 92 |  |  | 1/14/2026 | Connected |  | N
National Grid | SUTTON | 661902 | 01590 | 5.76 | Solar | 05_01_4J339 | 12/20/2024 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | Y
National Grid | WORCESTER | 324658 | 01610 | 3.8 | Solar | 05_01_6W2 | 11/27/2020 | 12/02/2020 | 2 | 0 | 2 | 12/03/2020 | 12/03/2020 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 727861 | 01603 | 10 | Solar | 05_05_19W74 | 10/21/2025 | 10/23/2025 | 2 | 0 | 2 | 10/24/2025 | 10/24/2025 | 84 | 72 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | DIGHTON | 618725 | 02715 | 6 | Solar | 05_12_37W4 | 06/18/2024 | 07/03/2024 | 5 | 4 | 1 | 07/05/2024 | 07/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  | 7/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | MEDFORD | 316773 | 02155 | 7.6 | Solar | 05_14_211L1 | 11/11/2020 | 11/17/2020 | 3 | 0 | 3 | 11/18/2020 | 11/18/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/11/2020 | 3/13/2022 | Y | EXP | 365 | 05/19/2021 | 11/08/2021 | 174 | 7 | 167 |  |  | 1/11/2022 | Connected |  | N
National Grid | TYNGSBORO | 623222 | 01879 | 3.8 | Solar | 05_14_53J2 | 07/08/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/08/2024 | 8/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | LAWRENCE | 645251 | 01841 | 5.76 | Solar | 05_14_63L1 | 10/07/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/07/2024 | 12/10/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | METHUEN | 642143 | 01844 | 5.76 | Solar | 05_14_77L1 | 09/23/2024 | 11/12/2024 | 14 | 12 | 2 | 11/13/2024 | 11/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2025 | Connected |  | N
National Grid | LOWELL | 718439 | 01854 | 5.76 | Solar | 05_01_225W3 | 09/11/2025 | 09/26/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 37 | 17 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 657952 | 01453 | 10 | Solar | 05_01_304W6 | 12/02/2024 |  | 68 | 63 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SUTTON | 686548 | 01590 | 17.86 | Solar | 05_01_4J339 | 05/30/2025 | 06/05/2025 | 4 | 0 | 4 | 06/06/2025 | 06/06/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | WORCESTER | 325927 | 01610 | 7.68 | Solar | 05_01_6W2 | 01/29/2021 | 02/08/2021 | 5 | 5 | 0 | 02/09/2021 | 02/09/2021 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2021 | Connected |  | N
National Grid | WORCESTER | 731625 | 01603 | 22.8 | Solar | 05_05_19W74 | 11/20/2025 | 11/24/2025 | 2 | 0 | 2 | 11/25/2025 | 11/25/2025 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 637464 | 02764 | 7.6 | Solar | 05_12_37W4 | 09/03/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/03/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | MEDFORD | 343831 | 02155 | 0 | Solar | 05_14_211L1 | 03/12/2021 | 03/15/2021 | 0 | 0 | 0 | 03/16/2021 | 03/16/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 | 03/12/2021 | 9/1/2022 | Y | EXP | 365 | 08/04/2021 | 08/31/2021 | 26 | 3 | 23 |  |  | 3/14/2022 | Connected |  | N
National Grid | TYNGSBORO | 637397 | 01879 | 5.76 | Solar | 05_14_53J2 | 09/03/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 09/03/2024 | 11/1/2025 | Y | EXP | 365 | 05/07/2025 | 05/20/2025 | 14 | 0 | 14 |  |  | 6/13/2025 | Connected |  | N
National Grid | LAWRENCE | 645235 | 01841 | 8.41 | Solar | 05_14_63L1 | 10/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 646859 | 01844 | 7.6 | Solar | 05_14_77L1 | 10/28/2024 | 11/07/2024 | 1 | 0 | 1 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/28/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 724994 | 01854 | 7.6 | Solar | 05_01_225W3 | 10/08/2025 | 10/14/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | LEOMINSTER | 660387 | 01453 | 10 | Solar | 05_01_304W6 | 12/12/2024 | 12/30/2024 | 3 | 1 | 2 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | SUTTON | 699261 | 01590 | 5.76 | Solar | 05_01_4J339 | 06/18/2025 | 07/02/2025 | 33 | 30 | 3 | 08/27/2025 | 08/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | WORCESTER | 336649 | 01610 | 7.6 | Solar | 05_01_6W2 | 01/25/2021 | 01/27/2021 | 1 | 0 | 1 | 01/28/2021 | 01/28/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2021 | 01/25/2021 | 1/26/2022 | Y | EXP | 365 | 05/27/2021 | 05/28/2021 | 1 | 0 | 1 |  |  | 8/11/2021 | Connected |  | N
National Grid | WORCESTER | 741060 | 01603 | 7.6 | Solar | 05_05_19W74 | 12/18/2025 | 12/22/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 639222 | 02715 | 6 | Solar | 05_12_37W4 | 09/10/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/10/2024 | 11/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | MEDFORD | 450750 | 02155 | 11.4 | Solar | 05_14_211L1 | 12/06/2022 | 12/07/2022 | 1 | 0 | 1 | 12/08/2022 | 12/08/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 1/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | Y
National Grid | TYNGSBORO | 639334 | 01879 | 2.32 | Solar | 05_14_53J2 | 09/11/2024 | 09/23/2024 | 2 | 0 | 2 | 09/24/2024 | 09/24/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | LAWRENCE | 649440 | 01841 | 7.6 | Solar | 05_14_63L1 | 11/11/2024 | 12/19/2024 | 11 | 5 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | METHUEN | 647929 | 01844 | 9.6 | Solar | 05_14_77L1 | 10/18/2024 |  | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 294875 | 01854 | 4947 | Other | 05_01_225W4 | 10/05/2020 | 10/07/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2020 | 11/02/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/05/2020 | 9/24/2027 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 667531 | 01453 | 4990 | Other | 05_01_304W6 | 02/25/2025 | 03/31/2025 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/01/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SUTTON | 611044 | 01590 | 6.09 | Solar | 05_01_4J340 | 05/28/2024 | 06/20/2024 | 3 | 0 | 3 | 06/21/2024 | 06/21/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2024 | Connected |  | N
National Grid | WORCESTER | 336435 | 01610 | 10 | Solar | 05_01_6W2 | 03/17/2021 | 03/24/2021 | 4 | 0 | 4 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 748174 | 01603 | 17.48 | Solar | 05_05_19W74 | 01/29/2026 | 02/04/2026 | 3 | 1 | 2 | 02/05/2026 | 02/05/2026 | 21 | 13 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 651801 | 02764 | 7.6 | Solar | 05_12_37W4 | 11/04/2024 | 11/27/2024 | 14 | 10 | 4 | 12/02/2024 | 12/02/2024 | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/04/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | MEDFORD | 398399 | 02155 | 43.2 | Solar | 05_14_211L1 | 12/02/2021 | 12/28/2021 | 19 | 12 | 7 | 12/29/2021 | 12/29/2021 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 2/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | Y
National Grid | TYNGSBORO | 639669 | 01879 | 13.12 | Solar | 05_14_53J2 | 09/12/2024 | 10/03/2024 | 5 | 3 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 | 09/12/2024 | 2/4/2026 | Y | EXP | 365 | 02/20/2025 | 08/18/2025 | 180 | 0 | 180 |  |  | 8/30/2025 | Connected |  | N
National Grid | LAWRENCE | 652252 | 01841 | 10 | Solar | 05_14_63L1 | 11/14/2024 | 12/11/2024 | 7 | 6 | 1 | 12/12/2024 | 12/12/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 654048 | 01844 | 9.6 | Solar | 05_14_77L1 | 11/13/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 627849 | 01854 | 6 | Solar | 05_01_225W4 | 07/27/2024 | 08/08/2024 | 1 | 0 | 1 | 08/09/2024 | 08/09/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 07/27/2024 | 9/24/2025 | Y | EXP | 365 | 11/06/2024 | 11/18/2024 | 13 | 0 | 13 |  |  |  | Completion Documents |  | Y
National Grid | LEOMINSTER | 686174 | 01453 | 20 | Solar | 05_01_304W6 | 04/18/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | SUTTON | 459951 | 01590 | 4999 | Solar | 05_01_525L1 | 11/02/2022 | 11/17/2022 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2022 | 12/15/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 357858 | 01610 | 2.88 | Solar | 05_01_6W2 | 05/20/2021 | 05/25/2021 | 2 | 0 | 2 | 05/26/2021 | 05/26/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2021 |  | 11/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2023 | Connected |  | N
National Grid | WORCESTER | 747749 | 01603 | 3.8 | Solar | 05_05_19W74 | 01/27/2026 | 01/28/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 669101 | 02764 | 4.06 | Solar | 05_12_37W4 | 01/31/2025 | 02/13/2025 | 6 | 2 | 4 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | MEDFORD | 555818 | 02155 | 6 | Solar | 05_14_211L1 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 102 | 25 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 640559 | 01879 | 15.2 | Solar | 05_14_53J2 | 09/24/2024 | 10/03/2024 | 8 | 6 | 2 | 10/04/2024 | 10/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2024 |  | 11/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LAWRENCE | 655004 | 01841 | 3.8 | Solar | 05_14_63L1 | 11/19/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 657225 | 01841 | 6.38 | Solar | 05_14_77L1 | 12/02/2024 | 12/29/2024 | 7 | 3 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/02/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | LOWELL | 665675 | 01854 | 0 | Other | 05_01_225W4 | 07/22/2025 | 09/15/2025 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 712153 | 01453 | 7.6 | Solar | 05_01_304W6 | 08/14/2025 | 09/16/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | SUTTON | 715897 | 01590 | 5.76 | Solar | 05_01_525L1 | 09/01/2025 | 09/19/2025 | 26 | 22 | 4 | 11/13/2025 | 11/13/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 390140 | 01535 | 9.8 | Solar | 05_01_6W2 | 11/11/2021 | 12/16/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 | 11/11/2021 | 6/8/2023 | Y | EXP | 365 | 03/31/2022 | 06/03/2022 | 65 | 0 | 65 |  |  | 7/8/2022 | Connected |  | N
National Grid | WORCESTER | 748734 | 01602 | 10 | Solar | 05_05_19W74 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 677804 | 02715 | 5.8 | Solar | 05_12_37W4 | 03/18/2025 | 03/31/2025 | 1 | 0 | 1 | 04/14/2025 | 04/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2025 | Connected |  | N
National Grid | MEDFORD | 583467 | 02155 | 10 | Solar | 05_14_211L1 | 01/15/2024 | 03/07/2024 | 37 | 28 | 9 | 03/08/2024 | 03/08/2024 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | TYNGSBORO | 642771 | 01879 | 15.2 | Solar | 05_14_53J2 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/25/2024 | 10/24/2025 | Y | EXP | 365 | 01/09/2025 | 06/10/2025 | 153 | 0 | 153 |  |  | 7/1/2025 | Connected |  | N
National Grid | LAWRENCE | 656998 | 01841 | 7.6 | Solar | 05_14_63L1 | 11/26/2024 | 01/03/2025 | 15 | 11 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 11/26/2024 | 4/16/2026 | Y | EXP | 365 | 05/15/2025 | 05/20/2025 | 6 | 0 | 6 |  |  | 9/9/2025 | Connected |  | N
National Grid | METHUEN | 664857 | 01844 | 6.5 | Solar | 05_14_77L1 | 01/09/2025 | 01/23/2025 | 4 | 0 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/09/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | LOWELL | 705025 | 01854 | 0 | Other | 05_01_225W4 | 09/24/2025 | 11/06/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/07/2025 | 12/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEOMINSTER | 711907 | 01453 | 32.5 | Solar | 05_01_304W6 | 08/13/2025 | 08/18/2025 | 3 | 0 | 3 | 08/19/2025 | 08/19/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | WHITINSVILLE | 730670 | 01588 | 15.2 | Solar | 05_01_525L1 | 11/06/2025 | 12/05/2025 | 19 | 16 | 3 | 12/08/2025 | 12/08/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTH BROOKFIELD | 445228 | 01535 | 9.57 | Solar | 05_01_6W2 | 08/03/2022 | 08/09/2022 | 4 | 0 | 4 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 | 08/03/2022 | 5/9/2024 | Y | EXP | 365 | 04/20/2023 | 05/04/2023 | 15 | 0 | 15 |  |  | 5/21/2023 | Connected |  | N
National Grid | WORCESTER | 749533 | 01603 | 10 | Solar | 05_05_19W74 | 02/05/2026 | 02/06/2026 | 3 | 0 | 3 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DIGHTON | 686001 | 02715 | 5.76 | Solar | 05_12_37W4 | 04/17/2025 | 05/21/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | MEDFORD | 590700 | 02155 | 7.6 | Solar | 05_14_211L1 | 03/04/2024 | 03/11/2024 | 5 | 1 | 4 | 03/12/2024 | 03/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | TYNGSBORO | 659995 | 01879 | 12.76 | Solar | 05_14_53J2 | 12/11/2024 | 01/07/2025 | 2 | 0 | 2 | 01/08/2025 | 01/08/2025 | 57 | 33 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 657645 | 01841 | 3.8 | Solar | 05_14_63L1 | 11/29/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/29/2024 | 5/13/2026 | Y | EXP | 365 | 08/19/2025 | 12/01/2025 | 105 | 0 | 105 |  |  | 12/2/2025 | Connected |  | N
National Grid | LAWRENCE | 670340 | 01841 | 7.6 | Solar | 05_14_77L1 | 02/10/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 02/10/2025 | 4/21/2026 | Y | EXP | 365 | 07/24/2025 | 12/22/2025 | 152 | 0 | 152 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 750877 | 01854 | 11.5 | Solar | 05_01_225W4 | 02/12/2026 | 02/17/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEOMINSTER | 722290 | 01453 | 15.76 | Solar | 05_01_304W6 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 10/06/2025 | 10/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | SUTTON | 174425 | 01590 | 1000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 444419 | 01535 | 0 | Other | 05_01_6W2 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/09/2023 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174648 | 01602 | 499 | Solar | 05_05_19W74 | 12/24/2013 | 12/24/2013 | 6 | 0 | 6 | 01/06/2014 | 01/06/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 12/24/2013 | 4/8/2016 | Y | EXP | 81 | 01/28/2016 | 03/25/2016 | 39 | 0 | 39 | 1/25/2016 | 1/25/2016 | 4/14/2016 | Connected |  | N
National Grid | DIGHTON | 708255 | 02764 | 7.6 | Solar | 05_12_37W4 | 07/29/2025 | 08/15/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 6 | 13 | 10/14/2025 | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 11/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 11/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 633351 | 02155 | 7.6 | Solar | 05_14_211L1 | 08/19/2024 | 08/22/2024 | 4 | 0 | 4 | 09/24/2024 | 09/24/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 08/19/2024 | 11/15/2025 | Y | EXP | 365 | 12/19/2024 | 02/24/2025 | 68 | 0 | 68 |  |  | 2/28/2025 | Connected |  | N
National Grid | TYNGSBORO | 670934 | 01879 | 4.56 | Solar | 05_14_53J2 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | LAWRENCE | 657611 | 01841 | 10 | Solar | 05_14_63L1 | 11/29/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/29/2024 | 2/10/2026 | Y | EXP | 365 | 06/14/2025 | 02/03/2026 | 235 | 0 | 235 |  |  | 12/3/2025 | Connected |  | N
National Grid | METHUEN | 699607 | 01844 | 9.28 | Solar | 05_14_77L1 | 06/18/2025 | 07/02/2025 | 2 | 0 | 2 | 09/05/2025 | 09/05/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2026 | Connected |  | N
National Grid | LOWELL | 174798 | 01854 | 400 | Solar | 05_01_225W4 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 367448 | 01453 | 7.6 | Solar | 05_01_3J371 | 07/23/2021 | 12/20/2021 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2022 | Connected |  | N
National Grid | SUTTON | 174424 | 01590 | 1000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 492821 | 01535 | 7.6 | Solar | 05_01_6W2 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 6/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2023 | Connected |  | N
National Grid | WORCESTER | 175198 | 01603 | 2000 | Solar | 05_05_19W74 | 04/26/2011 | 04/26/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2011 | 06/28/2011 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2014 |  | 12/31/2016 | N | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 657513 | 02715 | 3.8 | Solar | 05_12_37W5 | 11/27/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 3/7/2026 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MEDFORD | 635683 | 02155 | 150 | Solar | 05_14_211L1 | 09/11/2024 | 10/04/2024 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2024 | 06/04/2025 | 162 | 75 | 87 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 685070 | 01879 | 13.8 | Solar | 05_14_53J2 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/22/2025 | 6/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LAWRENCE | 660632 | 01841 | 5.76 | Solar | 05_14_63L1 | 12/23/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 705084 | 01841 | 3.8 | Solar | 05_14_77L1 | 07/15/2025 | 08/13/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 | 07/15/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2026 | Connected |  | N
National Grid | LOWELL | 174890 | 01854 | 300 | Solar | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 916 | 0 | 916 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 10/31/2013 | N | EXP | 241 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 728709 | 01453 | 15.76 | Solar | 05_01_3J372 | 12/12/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 53 | 31 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 174422 | 01602 | 3000 | Solar | 05_01_525L1 | 11/23/2011 | 11/23/2011 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 | 11/23/2011 | 10/31/2012 | Y | STD | 34 | 02/13/2014 | 06/13/2014 | 82 | 0 | 82 | 6/16/2014 | 6/16/2014 | 6/16/2014 | Connected |  | N
National Grid | NORTH BROOKFIELD | 558041 | 01535 | 7.6 | Solar | 05_01_6W2 | 09/29/2023 | 10/05/2023 | 4 | 0 | 4 | 10/06/2023 | 10/06/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 09/29/2023 | 11/19/2024 | Y | EXP | 365 | 04/24/2024 | 09/04/2024 | 134 | 0 | 134 |  |  | 9/10/2024 | Connected |  | N
National Grid | WORCESTER | 175717 | 01603 | 1000 | Solar | 05_05_19W74 | 12/26/2014 | 12/26/2014 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 691591 | 02764 | 7.6 | Solar | 05_12_37W5 | 05/14/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MEDFORD | 666071 | 02155 | 0 | Battery Add-On | 05_14_211L1 | 01/15/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 652357 | 01879 | 7.6 | Solar | 05_14_53J3 | 01/22/2025 | 02/19/2025 | 9 | 4 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 | 01/22/2025 | 3/28/2026 | Y | EXP | 365 | 06/12/2025 | 09/18/2025 | 99 | 0 | 99 |  |  | 10/7/2025 | Connected |  | N
National Grid | LAWRENCE | 665076 | 01841 | 0 | Battery Add-On | 05_14_63L1 | 01/10/2025 | 01/14/2025 | 2 | 0 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | METHUEN | 558618 | 01844 | 240 | Solar | 05_14_77L2 | 09/29/2023 | 10/23/2023 | 15 | 6 | 9 | 10/24/2023 | 10/24/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 | 09/29/2023 | 7/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LOWELL | 175026 | 01854 | 400 | Solar | 05_01_225W4 | 10/12/2012 | 10/12/2012 | 7 | 0 | 7 | 10/24/2012 | 10/24/2012 | 704 | 0 | 704 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2013 |  | 6/3/2013 | N | EXP | 91 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 446320 | 01453 | 16.24 | Solar | 05_01_3J372 | 08/30/2022 | 09/15/2022 | 11 | 9 | 2 | 09/16/2022 | 09/16/2022 | 134 | 117 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2023 |  | 6/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | WORCESTER | 175219 | 01610 | 18 | Solar | 05_01_525L1 | 11/03/2014 | 11/03/2014 | 6 | 2 | 4 | 11/13/2014 | 11/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2014 |  | 6/1/2015 | N | EXP | 199 |  |  | 0 | 0 | 0 | 2/18/2015 | 2/18/2015 | 9/30/2015 | Connected |  | N
National Grid | NORTH BROOKFIELD | 536053 | 01535 | 850 | Solar | 05_01_6W2 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 03/28/2024 | 145 | 94 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 175827 | 01602 | 7.6 | Solar | 05_05_19W74 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/24/2015 | 09/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2015 |  | 9/27/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 3/24/2016 | 3/24/2016 | 3/24/2016 | Connected |  | N
National Grid | DIGHTON | 711000 | 02715 | 7.6 | Solar | 05_12_37W5 | 08/11/2025 | 10/03/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 27 | 10 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 08/11/2025 | 1/14/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MEDFORD | 706405 | 02155 | 0 | Solar | 05_14_211L1 | 07/22/2025 | 07/24/2025 | 2 | 0 | 2 | 07/25/2025 | 07/25/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 |  | 10/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | TYNGSBORO | 662820 | 01879 | 9.1 | Solar | 05_14_53J3 | 12/27/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2025 | 12/27/2024 | 4/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | LAWRENCE | 666060 | 01841 | 7.6 | Solar | 05_14_63L1 | 01/15/2025 | 03/11/2025 | 3 | 0 | 3 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 | 01/15/2025 | 4/17/2026 | Y | EXP | 365 | 06/14/2025 | 12/22/2025 | 193 | 0 | 193 |  |  | 12/4/2025 | Connected |  | N
National Grid | METHUEN | 558966 | 01844 | 200 | Solar | 05_14_77L2 | 10/05/2023 | 10/23/2023 | 11 | 2 | 9 | 10/24/2023 | 10/24/2023 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2023 | 10/05/2023 | 3/2/2026 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | LOWELL | 175736 | 01854 | 27 | Solar | 05_01_225W4 | 08/14/2014 | 08/14/2014 | 7 | 0 | 7 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2014 | 08/14/2014 | 11/28/2014 | Y | EXP | 58 | 12/10/2014 | 12/23/2014 | 9 | 0 | 9 | 10/6/2014 | 10/6/2014 | 1/12/2015 | Connected |  | N
National Grid | LEOMINSTER | 446313 | 01453 | 14.5 | Solar | 05_01_3J372 | 08/30/2022 | 10/11/2022 | 28 | 27 | 1 | 10/12/2022 | 10/12/2022 | 46 | 25 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2022 |  | 6/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2024 | Connected |  | N
National Grid | WORCESTER | 175629 | 01610 | 120 | Solar | 05_01_525L1 | 08/06/2014 | 08/06/2014 | 7 | 0 | 7 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2014 |  | 1/30/2015 | N | EXP | 135 |  |  | 0 | 0 | 0 | 9/17/2014 | 9/17/2014 | 2/20/2015 | Connected |  | N
National Grid | NORTH BROOKFIELD | 542169 | 01535 | 7.6 | Solar | 05_01_6W2 | 08/05/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 08/05/2023 | 11/11/2024 | Y | EXP | 365 | 02/16/2024 | 04/11/2024 | 56 | 0 | 56 |  |  | 5/6/2024 | Connected |  | N
National Grid | WORCESTER | 175837 | 01602 | 15.2 | Solar | 05_05_19W74 | 03/04/2015 | 03/04/2015 | 5 | 1 | 4 | 03/12/2015 | 03/12/2015 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 |  | 7/31/2015 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 720644 | 02726 | 8 | Solar | 05_12_37W5 | 10/17/2025 | 01/16/2026 | 3 | 0 | 3 | 01/20/2026 | 01/20/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MEDFORD | 564846 | 02155 | 200 | Solar | 05_14_211L2 | 10/24/2023 | 11/07/2023 | 10 | 0 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 10/24/2023 | 2/16/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | TYNGSBORO | 667264 | 01879 | 7.6 | Solar | 05_14_53J3 | 02/04/2025 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 667679 | 01841 | 7.6 | Solar | 05_14_63L1 | 01/24/2025 | 03/05/2025 | 12 | 8 | 4 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | METHUEN | 733768 | 01844 | 17.48 | Solar | 05_14_77L2 | 11/17/2025 | 12/10/2025 | 2 | 0 | 2 | 12/23/2025 | 12/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 176068 | 01854 | 7.6 | Solar | 05_01_225W4 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 | 06/19/2015 | 6/27/2016 | Y | EXP | 346 | 03/14/2016 | 03/23/2016 | 6 | 0 | 6 | 11/13/2015 | 11/13/2015 | 4/27/2016 | Connected |  | N
National Grid | LEOMINSTER | 649062 | 01453 | 7.6 | Solar | 05_01_3J373 | 10/23/2024 | 11/13/2024 | 7 | 1 | 6 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177746 | 01610 | 15 | Solar | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 48 | 48 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 6/5/2018 | N | EXP | 286 |  |  | 0 | 0 | 0 | 12/26/2017 | 12/26/2017 | 12/26/2017 | Connected |  | N
National Grid | NORTH BROOKFIELD | 581993 | 01535 | 9.86 | Solar | 05_01_6W2 | 01/22/2024 | 01/23/2024 | 1 | 0 | 1 | 01/24/2024 | 01/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2024 | Connected |  | N
National Grid | WORCESTER | 176302 | 01603 | 490 | Solar | 05_05_19W74 | 09/15/2015 | 09/15/2015 | 0 | 0 | 0 | 09/15/2015 | 09/15/2015 | 243 | 0 | 243 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/20/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 722271 | 02715 | 10 | Solar | 05_12_37W5 | 09/26/2025 | 10/03/2025 | 4 | 0 | 4 | 11/20/2025 | 11/20/2025 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 09/26/2025 | 1/7/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MEDFORD | 174740 | 02155 | 5500 | Solar | 05_14_211L2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2013 | 04/04/2013 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 319285 | 01879 | 8.12 | Solar | 05_14_53J4 | 11/12/2020 | 11/17/2020 | 2 | 0 | 2 | 11/18/2020 | 11/18/2020 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2020 | 11/12/2020 | 11/12/2021 | Y | EXP | 365 | 04/14/2021 | 05/20/2021 | 36 | 0 | 36 |  |  | 5/21/2021 | Connected |  | N
National Grid | LAWRENCE | 668519 | 01841 | 7.6 | Solar | 05_14_63L1 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | METHUEN | 750324 | 01844 | 7.6 | Solar | 05_14_77L2 | 02/10/2026 | 02/11/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 176260 | 01854 | 10 | Solar | 05_01_225W4 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 3/17/2016 | Connected |  | N
National Grid | LEOMINSTER | 667941 | 01453 | 5.76 | Solar | 05_01_3J373 | 01/27/2025 | 03/26/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 | 01/27/2025 | 5/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | WORCESTER | 177743 | 01610 | 5 | Solar | 05_01_525L1 | 05/31/2017 | 05/31/2017 | 47 | 47 | 0 | 08/08/2017 | 08/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2017 |  | 5/31/2018 | N | EXP | 281 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/20/2017 | Connected |  | N
National Grid | NORTH BROOKFIELD | 583917 | 01535 | 4.93 | Solar | 05_01_6W2 | 02/09/2024 | 02/14/2024 | 3 | 0 | 3 | 02/15/2024 | 02/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 4/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | WORCESTER | 176535 | 01603 | 6 | Solar | 05_05_19W74 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 6/16/2016 | 6/16/2016 | 6/23/2016 | Connected |  | N
National Grid | DIGHTON | 733641 | 02764 | 5.76 | Solar | 05_12_37W5 | 11/13/2025 | 11/19/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 60 | 50 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MEDFORD | 177013 | 02155 | 7.6 | Solar | 05_14_211L2 | 01/05/2017 | 01/05/2017 | 8 | 8 | 0 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2017 |  | 1/10/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/2/2017 | Connected |  | N
National Grid | TYNGSBORO | 322607 | 01879 | 5 | Solar | 05_14_53J4 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/22/2020 | 4/3/2022 | Y | EXP | 365 | 08/15/2021 | 09/24/2021 | 40 | 3 | 37 |  |  | 11/9/2021 | Connected |  | N
National Grid | METHUEN | 673030 | 01844 | 5.76 | Solar | 05_14_63L1 | 02/19/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | METHUEN | 178138 | 01844 | 3.8 | Solar | 05_14_77L2 | 03/22/2018 | 03/22/2018 | 4 | 4 | 0 | 03/29/2018 | 03/29/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2018 |  | 3/28/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 9/4/2019 | Connected |  | N
National Grid | LOWELL | 176887 | 01854 | 10 | Solar | 05_01_225W4 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 187 | 0 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2015 |  | 11/18/2016 | N | EXP | 35 |  |  | 0 | 0 | 0 | 12/4/2015 | 12/4/2015 |  | Withdrawn |  | N
National Grid | LEOMINSTER | 697845 | 01453 | 7.6 | Solar | 05_01_3J373 | 06/11/2025 | 06/24/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2025 | Connected |  | N
National Grid | WORCESTER | 178239 | 01610 | 2000 | Solar | 05_01_525L1 | 02/20/2018 | 02/20/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2018 |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/25/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 592273 | 01535 | 3 | Solar | 05_01_6W2 | 03/08/2024 | 03/29/2024 | 16 | 13 | 3 | 04/01/2024 | 04/01/2024 | 81 | 67 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 03/08/2024 | 7/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176649 | 01602 | 6 | Solar | 05_05_19W74 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 2/23/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 6/6/2016 | Connected |  | N
National Grid | DIGHTON | 734653 | 02764 | 3.8 | Solar | 05_12_37W5 | 11/18/2025 | 11/19/2025 | 26 | 23 | 3 | 02/11/2026 | 02/11/2026 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MEDFORD | 177845 | 02155 | 910 | Solar | 05_14_211L2 | 10/17/2017 | 10/17/2017 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 | 12/14/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 540408 | 01879 | 6 | Solar | 05_14_53J4 | 07/26/2023 | 08/22/2023 | 20 | 19 | 1 | 08/23/2023 | 08/23/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2023 |  | 12/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 674155 | 01841 | 5.76 | Solar | 05_14_63L1 | 02/25/2025 | 03/06/2025 | 3 | 0 | 3 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 199543 | 01841 | 10 | Solar | 05_14_77L2 | 10/26/2018 | 01/03/2019 | 32 | 28 | 4 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 6/17/2019 | N | EXP | 151 |  |  | 0 | 0 | 0 |  |  | 6/1/2019 | Connected |  | N
National Grid | LOWELL | 176962 | 01854 | 3.8 | Solar | 05_01_225W4 | 07/18/2016 | 07/18/2016 | 1 | 1 | 0 | 07/20/2016 | 07/20/2016 | 254 | 0 | 254 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2016 |  | 7/24/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 737387 | 01453 | 10 | Solar | 05_01_3J374 | 12/02/2025 | 12/04/2025 | 2 | 0 | 2 | 12/05/2025 | 12/05/2025 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 178298 | 01610 | 4980 | Solar | 05_01_525L1 | 11/15/2017 | 01/08/2018 | 34 | 23 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2018 | 02/09/2018 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2018 |  | 12/31/2019 | N | STD | 52 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 605256 | 01535 | 5 | Solar | 05_01_6W2 | 05/01/2024 | 05/02/2024 | 2 | 1 | 1 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 | 05/01/2024 | 6/12/2025 | Y | EXP | 365 | 10/18/2024 | 10/24/2024 | 7 | 0 | 7 |  |  | 10/28/2024 | Connected |  | N
National Grid | LEICESTER | 177123 | 01611 | 3625 | Solar | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 01/04/2017 | 48 | 35 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 6/27/2024 | Y | STD | 44 | 09/29/2023 | 02/05/2024 | 129 | 45 | 84 |  |  | 6/24/2024 | Connected |  | N
National Grid | SOMERSET | 206779 | 02726 | 7.6 | Solar | 05_12_37W5 | 02/11/2019 | 02/14/2019 | 3 | 3 | 0 | 02/15/2019 | 02/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/11/2019 | 5/28/2020 | Y | EXP | 365 | 03/25/2020 | 04/07/2020 | 13 | 0 | 13 |  |  | 5/14/2020 | Connected |  | N
National Grid | MEDFORD | 187599 | 02155 | 240 | Solar | 05_14_211L2 | 06/08/2018 | 06/12/2018 | 3 | 0 | 3 | 06/22/2018 | 06/22/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 |  | 7/10/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2019 | Connected |  | N
National Grid | TYNGSBORO | 589338 | 01879 | 10 | Solar | 05_14_53J4 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/22/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 07/18/2024 | 78 | 0 | 78 |  |  | 8/2/2024 | Connected |  | N
National Grid | LAWRENCE | 674798 | 01841 | 11.4 | Solar | 05_14_63L1 | 04/10/2025 | 04/28/2025 | 10 | 6 | 4 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | LAWRENCE | 416317 | 01841 | 7.68 | Solar | 05_14_77L2 | 03/16/2022 | 03/23/2022 | 5 | 0 | 5 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176995 | 01854 | 6 | Solar | 05_01_225W4 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 242 | 0 | 242 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 |  | 7/25/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 570742 | 01453 | 10 | Solar | 05_01_3J374 | 12/19/2023 | 04/17/2024 | 81 | 77 | 4 | 04/18/2024 | 04/18/2024 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178480 | 01609 | 4999 | Solar | 05_01_525L1 | 04/03/2018 | 04/04/2018 | 12 | 12 | 0 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 607670 | 01585 | 7.6 | Solar | 05_01_6W2 | 04/30/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 19 | 7 | 12 | 06/17/2024 | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 07/24/2024 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 8/1/2024 | 04/30/2024 | 10/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | WORCESTER | 177124 | 01603 | 2000 | Solar | 05_05_19W74 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 01/04/2017 | 49 | 35 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2017 | 10/20/2016 | 4/22/2019 | Y | STD | 64 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 235994 | 02715 | 7.6 | Solar | 05_12_37W5 | 06/21/2019 | 06/28/2019 | 4 | 0 | 4 | 07/01/2019 | 07/01/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 6/21/2020 | Y | EXP | 365 | 03/06/2020 | 03/09/2020 | 3 | 0 | 3 |  |  | 5/1/2020 | Connected |  | N
National Grid | MEDFORD | 190345 | 02155 | 7.6 | Solar | 05_14_211L2 | 07/10/2018 | 07/13/2018 | 2 | 0 | 2 | 07/13/2018 | 07/13/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 590580 | 01879 | 10 | Solar | 05_14_53J4 | 02/23/2024 | 02/27/2024 | 2 | 0 | 2 | 02/28/2024 | 02/28/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/23/2024 | 3/8/2025 | Y | EXP | 365 | 05/02/2024 | 09/11/2024 | 133 | 0 | 133 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 674773 | 01844 | 11.5 | Solar | 05_14_63L1 | 02/27/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | LAWRENCE | 481185 | 01841 | 201.9 | Solar | 05_14_77L2 | 12/20/2022 | 03/14/2023 | 56 | 47 | 9 | 03/15/2023 | 03/15/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2023 | 12/20/2022 | 10/21/2024 | Y | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | LOWELL | 177095 | 01854 | 7.6 | Solar | 05_01_225W4 | 01/20/2017 | 01/20/2017 | 2 | 2 | 0 | 01/25/2017 | 01/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 | 01/20/2017 | 1/28/2018 | Y | EXP | 366 | 06/15/2017 | 07/28/2017 | 30 | 0 | 30 | 8/28/2017 | 8/28/2017 | 8/28/2017 | Connected |  | N
National Grid | LEOMINSTER | 634549 | 01453 | 9.57 | Solar | 05_01_3J374 | 08/22/2024 | 10/14/2024 | 14 | 13 | 1 | 10/15/2024 | 10/15/2024 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 184669 | 01609 | 1800 | Solar | 05_01_525L1 | 05/09/2018 | 05/09/2018 | 4 | 0 | 4 |  |  | 43 | 41 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 616449 | 01562 | 3.8 | Solar | 05_01_6W2 | 06/07/2024 | 06/18/2024 | 2 | 0 | 2 | 06/20/2024 | 06/20/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | WORCESTER | 177288 | 01603 | 233.1 | Solar | 05_05_19W74 | 06/17/2016 | 06/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 09/15/2016 | 21 | 4 | 17 | 06/20/2016 | 07/15/2016 | 18 | 5 | 13 |  | 09/15/2016 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 6/25/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 456275 | 02715 | 10 | Solar | 05_12_37W5 | 09/16/2022 | 10/14/2022 | 19 | 19 | 0 | 10/17/2022 | 10/17/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 2/13/2024 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 193772 | 02155 | 15.2 | Solar | 05_14_211L2 | 08/17/2018 | 08/29/2018 | 7 | 0 | 7 | 08/30/2018 | 08/30/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 598618 | 01879 | 9.56 | Solar | 05_14_53J4 | 03/27/2024 | 04/03/2024 | 5 | 2 | 3 | 04/04/2024 | 04/04/2024 | 24 | 20 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | METHUEN | 677396 | 01844 | 7.6 | Solar | 05_14_63L1 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 656692 | 01844 | 7.6 | Solar | 05_14_77L2 | 11/25/2024 | 01/17/2025 | 22 | 16 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178543 | 01854 | 3.8 | Solar | 05_01_225W4 | 01/29/2018 | 01/29/2018 | 19 | 0 | 19 | 02/27/2018 | 02/27/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2018 |  | 2/4/2019 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 10/24/2018 | Connected |  | N
National Grid | LEOMINSTER | 636727 | 01453 | 10 | Solar | 05_01_3J374 | 08/30/2024 | 09/06/2024 | 4 | 0 | 4 | 11/01/2024 | 11/01/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | WORCESTER | 195871 | 01609 | 2000 | Solar | 05_01_525L1 | 12/04/2018 | 12/24/2018 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2018 | 01/24/2019 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 622524 | 01005 | 10 | Solar | 05_01_6W2 | 07/03/2024 | 07/16/2024 | 3 | 0 | 3 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/29/2025 | Y | EXP | 365 | 10/10/2024 | 10/23/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | WORCESTER | 177465 | 01602 | 192 | Solar | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 42 | 28 | 14 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | DIGHTON | 463128 | 02715 | 15 | Solar | 05_12_37W5 | 10/05/2022 | 10/13/2022 | 5 | 3 | 2 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 1/8/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 240929 | 02155 | 10 | Solar | 05_14_211L2 | 08/07/2019 | 08/13/2019 | 3 | 0 | 3 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | TYNGSBORO | 613386 | 01879 | 10 | Solar | 05_14_53J4 | 05/29/2024 | 06/21/2024 | 2 | 0 | 2 | 06/24/2024 | 06/24/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 679876 | 01844 | 11.5 | Solar | 05_14_63L1 | 03/21/2025 | 04/23/2025 | 23 | 20 | 3 | 04/24/2025 | 04/24/2025 | 68 | 24 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 669826 | 01844 | 3.8 | Solar | 05_14_77L2 | 02/04/2025 | 02/14/2025 | 2 | 0 | 2 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | LOWELL | 194206 | 01854 | 10 | Solar | 05_01_225W4 | 08/22/2018 | 08/13/2019 | 248 | 248 | 0 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 658582 | 01453 | 9.57 | Solar | 05_01_3J374 | 12/05/2024 | 12/19/2024 | 8 | 6 | 2 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | WORCESTER | 385041 | 01609 | 2000 | Solar | 05_01_525L1 | 10/29/2021 | 12/02/2021 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2021 | 01/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 636208 | 01535 | 3.8 | Solar | 05_01_6W2 | 08/28/2024 | 09/09/2024 | 4 | 0 | 4 | 09/10/2024 | 09/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/28/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | WORCESTER | 177464 | 01602 | 96 | Solar | 05_05_19W74 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 13 | 0 | 13 | 06/21/2017 | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  | 06/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 3/7/2018 | N | EXP | 223 |  |  | 0 | 0 | 0 |  |  | 5/22/2018 | Connected |  | N
National Grid | DIGHTON | 499173 | 02764 | 15.2 | Solar | 05_12_37W5 | 03/15/2023 | 03/16/2023 | 1 | 0 | 1 | 03/17/2023 | 03/17/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2023 | 03/15/2023 | 9/1/2024 | Y | EXP | 365 | 07/28/2023 | 08/28/2023 | 32 | 0 | 32 |  |  | 9/20/2023 | Connected |  | N
National Grid | MEDFORD | 254655 | 02155 | 10 | Solar | 05_14_211L2 | 10/01/2019 | 10/04/2019 | 2 | 2 | 0 | 10/07/2019 | 10/07/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/01/2019 | 10/1/2020 | Y | EXP | 365 | 01/09/2020 | 04/17/2020 | 99 | 0 | 99 |  |  | 5/19/2020 | Connected |  | N
National Grid | TYNGSBORO | 622922 | 01879 | 7.6 | Solar | 05_14_53J4 | 07/05/2024 | 08/15/2024 | 2 | 0 | 2 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 07/05/2024 | 8/28/2025 | Y | EXP | 365 | 03/01/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | LAWRENCE | 681026 | 01841 | 11.5 | Solar | 05_14_63L1 | 03/27/2025 | 04/01/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 722072 | 01844 | 11.5 | Solar | 05_14_77L3 | 10/02/2025 | 10/13/2025 | 6 | 3 | 3 | 10/14/2025 | 10/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 199725 | 01854 | 10 | Solar | 05_01_225W4 | 12/11/2018 | 12/19/2018 | 5 | 0 | 5 | 12/20/2018 | 12/20/2018 | 247 | 0 | 247 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 482717 | 01453 | 24.779 | Solar | 05_01_3J375 | 12/05/2022 | 12/08/2022 | 4 | 1 | 3 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 |  | 3/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/8/2023 | Connected |  | N
National Grid | WORCESTER | 406582 | 01609 | 6 | Solar | 05_01_525L1 | 02/09/2022 | 02/14/2022 | 3 | 0 | 3 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/09/2022 | 5/26/2023 | Y | EXP | 365 | 04/29/2022 | 05/19/2022 | 21 | 0 | 21 |  |  | 6/2/2022 | Connected |  | Y
National Grid | NORTH BROOKFIELD | 636971 | 01535 | 3.8 | Solar | 05_01_6W2 | 08/30/2024 | 12/04/2024 | 57 | 56 | 1 | 12/05/2024 | 12/05/2024 | 25 | 0 | 25 | 01/22/2025 | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 02/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 | 05/02/2025 | 05/30/2025 | 29 | 0 | 29 |  |  | 7/10/2025 | Connected |  | N
National Grid | WORCESTER | 177891 | 01602 | 3.8 | Solar | 05_05_19W74 | 04/13/2017 | 04/13/2017 | 6 | 6 | 0 | 04/24/2017 | 04/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2017 |  | 4/18/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 10/27/2017 | Connected |  | N
National Grid | DIGHTON | 506789 | 02764 | 5.04 | Solar | 05_12_37W5 | 05/09/2023 | 05/11/2023 | 2 | 0 | 2 | 05/12/2023 | 05/12/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2023 | Connected |  | N
National Grid | MEDFORD | 368610 | 02155 | 6 | Solar | 05_14_211L2 | 07/12/2021 | 07/13/2021 | 1 | 0 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TYNGSBORO | 639127 | 01879 | 8.7 | Solar | 05_14_53J4 | 09/10/2024 | 10/11/2024 | 3 | 0 | 3 | 10/15/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2024 | Connected |  | N
National Grid | LAWRENCE | 685181 | 01841 | 5.76 | Solar | 05_14_63L1 | 04/15/2025 | 04/25/2025 | 8 | 4 | 4 | 04/28/2025 | 04/28/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 174165 | 01844 | 566 | Solar | 05_14_77L3 | 04/24/2012 | 04/24/2012 | 13 | 0 | 13 | 05/11/2012 | 05/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2012 |  | 7/31/2012 | N | EXP | 111 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 5/21/2013 | Connected |  | N
National Grid | LOWELL | 204484 | 01854 | 0 | Solar | 05_01_225W4 | 01/17/2019 | 02/01/2019 | 9 | 0 | 9 | 02/04/2019 | 02/04/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 575082 | 01453 | 9.6 | Solar | 05_01_3J375 | 03/05/2024 | 03/11/2024 | 4 | 1 | 3 | 03/12/2024 | 03/12/2024 | 4 | 0 | 4 | 03/29/2024 | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 05/07/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 534547 | 01609 | 0 | Solar | 05_01_525L1 | 06/16/2023 | 06/23/2023 | 4 | 3 | 1 | 06/26/2023 | 06/26/2023 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 643927 | 01535 | 5.76 | Solar | 05_01_6W2 | 10/01/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | WORCESTER | 178015 | 01603 | 15.2 | Solar | 05_05_19W74 | 06/29/2017 | 06/29/2017 | 19 | 18 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/4/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOMERSET | 522539 | 02726 | 15.2 | Solar | 05_12_37W5 | 04/28/2023 | 06/07/2023 | 27 | 26 | 1 | 06/08/2023 | 06/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2023 | Connected |  | N
National Grid | MEDFORD | 475793 | 02155 | 3.8 | Solar | 05_14_211L2 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 12/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | TYNGSBORO | 650617 | 01879 | 17.28 | Solar | 05_14_53J4 | 10/29/2024 | 11/01/2024 | 3 | 1 | 2 | 11/04/2024 | 11/04/2024 | 131 | 111 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | LAWRENCE | 692844 | 01841 | 10 | Solar | 05_14_63L1 | 05/20/2025 | 06/23/2025 | 3 | 0 | 3 | 06/24/2025 | 06/24/2025 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 | 05/20/2025 | 8/29/2026 | Y | EXP | 365 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 |  |  | 11/24/2025 | Connected |  | N
National Grid | METHUEN | 177405 | 01844 | 7.6 | Solar | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 |  | 7/5/2017 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 264869 | 01854 | 0 | Solar | 05_01_225W4 | 11/11/2019 | 11/13/2019 | 1 | 0 | 1 | 11/14/2019 | 11/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2019 | 11/11/2019 | 3/16/2021 | Y | EXP | 365 | 06/24/2020 | 06/24/2020 | 0 | 0 | 0 |  |  | 8/14/2020 | Connected |  | N
National Grid | LEOMINSTER | 621063 | 01453 | 7.6 | Solar | 05_01_3J375 | 06/27/2024 | 07/29/2024 | 17 | 16 | 1 | 07/30/2024 | 07/30/2024 | 123 | 25 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 571567 | 01609 | 10 | Solar | 05_01_525L1 | 12/29/2023 | 02/07/2024 | 27 | 26 | 1 | 02/08/2024 | 02/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 12/29/2023 | 2/28/2025 | Y | EXP | 365 | 04/30/2024 | 05/14/2024 | 15 | 0 | 15 |  |  | 7/3/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 655083 | 01535 | 5.76 | Solar | 05_01_6W2 | 11/18/2024 | 01/30/2025 | 40 | 34 | 6 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 5/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | Y
National Grid | WORCESTER | 178164 | 01603 | 617 | Solar | 05_05_19W74 | 02/13/2018 | 02/13/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 | 02/13/2018 | 5/13/2022 | Y | STD | 82 | 05/27/2020 | 08/31/2021 | 461 | 8 | 453 |  |  | 5/13/2022 | Connected |  | N
National Grid | SOMERSET | 563912 | 02726 | 7.6 | Solar | 05_12_37W5 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 11/07/2023 | 1/8/2025 | Y | EXP | 365 | 05/10/2024 | 05/14/2024 | 5 | 0 | 5 |  |  | 5/31/2024 | Connected |  | N
National Grid | MEDFORD | 576580 | 02155 | 0 | Battery Add-On | 05_14_211L2 | 12/07/2023 | 02/08/2024 | 43 | 39 | 4 | 02/09/2024 | 02/09/2024 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 | 12/07/2023 | 4/29/2025 | Y | EXP | 365 | 05/23/2024 | 05/22/2024 | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | TYNGSBORO | 652019 | 01879 | 15.2 | Solar | 05_14_53J4 | 11/04/2024 | 11/20/2024 | 12 | 10 | 2 | 11/21/2024 | 11/21/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 11/04/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | LAWRENCE | 730850 | 01841 | 5.76 | Solar | 05_14_63L1 | 11/03/2025 | 11/10/2025 | 5 | 0 | 5 | 11/12/2025 | 11/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2026 | Connected |  | N
National Grid | LAWRENCE | 177401 | 01841 | 3.44 | Solar | 05_14_77L3 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 288685 | 01854 | 10 | Solar | 05_01_225W4 | 07/20/2020 | 07/27/2020 | 4 | 0 | 4 | 07/28/2020 | 07/28/2020 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/20/2020 | 4/3/2021 | Y | EXP | 365 | 01/20/2021 | 01/26/2021 | 6 | 0 | 6 |  |  | 2/19/2021 | Connected |  | N
National Grid | LEOMINSTER | 643130 | 01453 | 3.8 | Solar | 05_01_3J375 | 09/26/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | WORCESTER | 646275 | 01609 | 5.76 | Solar | 05_01_525L1 | 10/10/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 657449 | 01535 | 3.8 | Solar | 05_01_6W2 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 06/12/2025 | 07/15/2025 | 34 | 0 | 34 |  |  | 7/26/2025 | Connected |  | N
National Grid | WORCESTER | 178152 | 01602 | 2700 | Solar | 05_05_19W74 | 12/21/2017 | 12/21/2017 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2018 | 02/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 | 12/21/2017 | 9/29/2025 | Y | STD | 414 | 06/04/2021 | 12/31/2021 | 211 | 10 | 201 |  |  | 9/4/2025 | Connected |  | N
National Grid | SOMERSET | 575277 | 02726 | 25 | Solar | 05_12_37W5 | 01/08/2024 | 01/22/2024 | 9 | 6 | 3 | 01/23/2024 | 01/23/2024 | 106 | 88 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2024 | Connected |  | N
National Grid | MEDFORD | 644867 | 02155 | 8.45 | Solar | 05_14_211L2 | 10/03/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 3 | 15 | 11/14/2024 | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 12/09/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 12/16/2024 |  | 12/25/2025 | N | EXP | 365 | 01/14/2025 | 03/28/2025 | 74 | 0 | 74 |  |  | 4/2/2025 | Connected |  | N
National Grid | TYNGSBORO | 661153 | 01879 | 10 | Solar | 05_14_53J4 | 12/17/2024 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 646555 | 01841 | 9.86 | Solar | 05_14_63L2 | 10/15/2024 | 10/28/2024 | 6 | 3 | 3 | 10/29/2024 | 10/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/15/2024 | 12/19/2025 | Y | EXP | 365 | 04/01/2025 | 10/15/2025 | 198 | 0 | 198 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 178339 | 01844 | 10 | Solar | 05_14_77L3 | 11/20/2017 | 11/20/2017 | 33 | 32 | 1 | 01/09/2018 | 01/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2018 | 11/20/2017 | 11/25/2018 | Y | EXP | 319 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | LOWELL | 327211 | 01854 | 7.6 | Solar | 05_01_225W4 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/6/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 654226 | 01453 | 10 | Solar | 05_01_3J375 | 11/15/2024 | 01/08/2025 | 13 | 10 | 3 | 01/09/2025 | 01/09/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | WORCESTER | 670518 | 01609 | 3.8 | Solar | 05_01_525L1 | 02/06/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 657837 | 01535 | 3.8 | Solar | 05_01_6W2 | 12/02/2024 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 178213 | 01611 | 2000 | Solar | 05_05_19W74 | 03/26/2018 | 03/26/2018 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 04/30/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 | 03/26/2018 | 5/5/2024 | Y | STD | 555 | 01/14/2022 | 02/01/2024 | 748 | 680 | 68 |  |  | 4/15/2024 | Connected |  | N
National Grid | DIGHTON | 581300 | 02715 | 0 | Battery Add-On | 05_12_37W5 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 64 | 47 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2024 | Connected |  | N
National Grid | MEDFORD | 649505 | 02155 | 8.12 | Solar | 05_14_211L2 | 10/26/2024 | 12/03/2024 | 8 | 6 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | TYNGSBORO | 679548 | 01879 | 10 | Solar | 05_14_53J4 | 03/21/2025 | 04/16/2025 | 16 | 9 | 7 | 05/20/2025 | 05/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 03/21/2025 | 7/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LAWRENCE | 711911 | 01841 | 249 | Solar | 05_14_63L2 | 08/13/2025 | 09/05/2025 | 16 | 7 | 9 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | METHUEN | 188816 | 01844 | 10 | Solar | 05_14_77L3 | 06/21/2018 | 06/21/2018 | 2 | 0 | 2 | 07/11/2018 | 07/11/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 | 06/21/2018 | 7/22/2020 | Y | EXP | 6 | 10/04/2019 | 10/22/2019 | 18 | 0 | 18 |  |  | 7/3/2020 | Connected |  | N
National Grid | LOWELL | 331301 | 01854 | 9.8 | Solar | 05_01_225W4 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 35 | 20 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 5/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 666721 | 01453 | 5.76 | Solar | 05_01_3J375 | 01/20/2025 | 01/30/2025 | 4 | 0 | 4 | 01/31/2025 | 01/31/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 681289 | 01609 | 15 | Solar | 05_01_525L1 | 03/31/2025 | 05/23/2025 | 39 | 35 | 4 | 05/27/2025 | 05/27/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | NORTH BROOKFIELD | 661445 | 01535 | 4.64 | Solar | 05_01_6W2 | 12/18/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 178393 | 01603 | 10 | Solar | 05_05_19W74 | 03/02/2018 | 03/02/2018 | 8 | 0 | 8 | 03/29/2018 | 03/29/2018 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2018 | 03/02/2018 | 3/11/2019 | Y | EXP | 186 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | DIGHTON | 635886 | 02764 | 7.6 | Solar | 05_12_37W5 | 08/29/2024 | 09/16/2024 | 7 | 4 | 3 | 09/17/2024 | 09/17/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MEDFORD | 657556 | 02155 | 10 | Solar | 05_14_211L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/28/2024 | 2/12/2026 | Y | EXP | 365 | 07/30/2025 | 02/02/2026 | 188 | 0 | 188 |  |  | 11/21/2025 | Connected |  | N
National Grid | TYNGSBORO | 703816 | 01879 | 6 | Solar | 05_14_53J4 | 07/09/2025 | 07/23/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | LAWRENCE | 737259 | 01841 | 5.76 | Solar | 05_14_63L2 | 12/01/2025 | 12/03/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | METHUEN | 197115 | 01844 | 3.8 | Solar | 05_14_77L3 | 09/27/2018 | 11/02/2018 | 3 | 3 | 0 | 11/05/2018 | 11/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/27/2018 | 4/22/2020 | Y | EXP | 512 | 11/14/2019 | 11/15/2019 | 1 | 0 | 1 |  |  | 1/22/2020 | Connected |  | N
National Grid | LOWELL | 335169 | 01854 | 5.76 | Solar | 05_01_225W4 | 02/17/2021 | 03/24/2021 | 24 | 24 | 0 | 03/25/2021 | 03/25/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 | 02/17/2021 | 3/24/2022 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 709748 | 01453 | 5.76 | Solar | 05_01_3J375 | 08/07/2025 | 08/12/2025 | 2 | 0 | 2 | 08/13/2025 | 08/13/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 360612 | 01610 | 1625 | Solar | 05_01_525L2 | 09/16/2021 | 12/13/2021 | 60 | 50 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTH BROOKFIELD | 662668 | 01535 | 4.225 | Solar | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 9 | 7 | 2 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | WORCESTER | 178694 | 01602 | 5.2 | Solar | 05_05_19W74 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 03/14/2018 | 03/14/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 2/12/2019 | N | EXP | 286 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 651935 | 02764 | 5.32 | Solar | 05_12_37W5 | 11/04/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 11/04/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | MEDFORD | 659846 | 02155 | 7.6 | Solar | 05_14_211L2 | 12/11/2024 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | TYNGSBORO | 688403 | 01879 | 12.54 | Solar | 05_14_53J5 | 05/05/2025 | 06/09/2025 | 22 | 18 | 4 | 06/10/2025 | 06/10/2025 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 05/05/2025 | 12/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 174297 | 01841 | 1800 | Solar | 05_14_63L2 | 12/23/2011 | 12/23/2011 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2012 | 04/25/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2012 | 12/23/2011 | 9/1/2012 | Y | STD | 114 | 10/21/2013 | 01/02/2014 | 49 | 0 | 49 | 12/31/2013 | 12/31/2013 | 2/7/2014 | Connected |  | N
National Grid | METHUEN | 201056 | 01844 | 7.6 | Solar | 05_14_77L3 | 11/13/2018 | 01/30/2019 | 41 | 34 | 7 | 01/31/2019 | 01/31/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 351150 | 01854 | 7.6 | Solar | 05_01_225W4 | 04/29/2021 | 05/06/2021 | 4 | 0 | 4 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2021 |  | 7/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 648676 | 01453 | 999 | Solar | 05_01_406L1 | 12/11/2024 | 03/07/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2025 | 01/28/2026 | 222 | 203 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WORCESTER | 654404 | 01610 | 996 | Solar | 05_01_525L2 | 04/23/2025 | 06/20/2025 | 40 | 29 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2025 | 07/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NEW BRAINTREE | 662627 | 01531 | 6.825 | Solar | 05_01_6W2 | 12/26/2024 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 12/26/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | WORCESTER | 195446 | 01603 | 2000 | Solar | 05_05_19W74 | 02/07/2020 |  | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 653334 | 02715 | 3.8 | Solar | 05_12_37W5 | 11/08/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | MEDFORD | 672483 | 02155 | 6 | Solar | 05_14_211L2 | 02/18/2025 | 03/25/2025 | 4 | 0 | 4 | 03/26/2025 | 03/26/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 02/18/2025 | 6/6/2026 | Y | EXP | 365 | 10/01/2025 | 01/27/2026 | 119 | 0 | 119 |  |  | 12/4/2025 | Connected |  | N
National Grid | TYNGSBORO | 699286 | 01879 | 7.6 | Solar | 05_14_53J5 | 06/19/2025 | 07/03/2025 | 1 | 0 | 1 | 07/15/2025 | 07/15/2025 | 53 | 38 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | METHUEN | 176912 | 01844 | 10 | Solar | 05_14_63L2 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 253 | 0 | 253 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2016 |  | 5/10/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 251766 | 01844 | 7.6 | Solar | 05_14_77L3 | 09/11/2019 | 09/16/2019 | 2 | 2 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 09/11/2019 | 6/17/2021 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  | 1/26/2021 | Connected |  | N
National Grid | LOWELL | 388913 | 01854 | 10 | Solar | 05_01_225W4 | 11/22/2021 | 01/06/2022 | 5 | 0 | 5 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2021 | 11/22/2021 | 10/26/2023 | Y | EXP | 365 | 04/13/2022 | 10/26/2022 | 197 | 0 | 197 |  |  | 11/14/2022 | Connected |  | N
National Grid | LEOMINSTER | 652194 | 01453 | 0 | Solar | 05_01_406L1 | 12/05/2024 | 12/30/2024 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 02/09/2026 | 276 | 257 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 650533 | 01542 | 4980 | Solar | 05_01_525L2 | 01/13/2025 | 01/29/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/30/2025 | 03/10/2025 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WEST BROOKFIELD | 663489 | 01585 | 3.8 | Solar | 05_01_6W2 | 01/02/2025 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 01/02/2025 | 3/14/2026 | Y | EXP | 365 | 05/16/2025 | 11/21/2025 | 190 | 0 | 190 |  |  | 12/9/2025 | Connected |  | N
National Grid | WORCESTER | 215929 | 01602 | 2970 | Solar | 05_05_19W74 | 04/24/2019 | 05/09/2019 | 11 | 3 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/10/2019 | 06/06/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 730332 | 02715 | 9.6 | Solar | 05_12_37W5 | 10/30/2025 | 10/30/2025 | 5 | 1 | 4 | 11/13/2025 | 11/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MEDFORD | 676121 | 02155 | 11.4 | Solar | 05_14_211L2 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | TYNGSBORO | 381732 | 01879 | 6 | Solar | 05_14_53J5 | 09/23/2021 | 01/03/2022 | 4 | 0 | 4 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 | 09/23/2021 | 5/28/2023 | Y | EXP | 365 | 04/14/2022 | 05/21/2022 | 36 | 0 | 36 |  |  | 6/30/2022 | Connected |  | Y
National Grid | LAWRENCE | 177064 | 01841 | 3.8 | Solar | 05_14_63L2 | 03/20/2017 | 03/20/2017 | 9 | 8 | 1 | 03/31/2017 | 03/31/2017 | 224 | 0 | 224 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 |  | 3/25/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 261453 | 01844 | 7.6 | Solar | 05_14_77L3 | 10/29/2019 | 11/05/2019 | 4 | 0 | 4 | 11/06/2019 | 11/06/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 10/29/2019 | 10/29/2020 | Y | EXP | 365 | 03/04/2020 | 04/08/2020 | 35 | 0 | 35 |  |  | 7/30/2020 | Connected |  | N
National Grid | LOWELL | 421215 | 01854 | 0 | Solar | 05_01_225W4 | 03/31/2022 | 04/04/2022 | 2 | 0 | 2 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 677898 | 01453 | 100 | Solar | 05_01_406L1 | 04/24/2025 | 06/06/2025 | 30 | 20 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LEICESTER | 685405 | 01611 | 10 | Solar | 05_01_525L2 | 06/04/2025 | 06/10/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 | 06/04/2025 | 8/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEST BROOKFIELD | 667926 | 01585 | 7.6 | Solar | 05_01_6W2 | 01/27/2025 | 02/14/2025 | 5 | 0 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WORCESTER | 232600 | 01602 | 15.2 | Solar | 05_05_19W74 | 05/31/2019 | 06/12/2019 | 7 | 0 | 7 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 6/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2020 | Connected |  | N
National Grid | DIGHTON | 174623 | 02779 | 200 | Solar | 05_12_37W6 | 04/14/2011 | 04/14/2011 | 155 | 0 | 155 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2011 |  | 6/29/2012 | N | EXP | 214 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 6/29/2012 | Connected |  | N
National Grid | MEDFORD | 708614 | 02155 | 23 | Solar | 05_14_211L2 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | TYNGSBORO | 522777 | 01879 | 3.8 | Solar | 05_14_53J5 | 05/17/2023 | 05/19/2023 | 2 | 2 | 0 | 05/22/2023 | 05/22/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2023 |  | 7/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | LAWRENCE | 177138 | 01841 | 6 | Solar | 05_14_63L2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2016 |  | 6/6/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 9/28/2016 | 9/28/2016 | 10/4/2016 | Connected |  | N
National Grid | METHUEN | 333029 | 01844 | 7.6 | Solar | 05_14_77L3 | 12/18/2020 | 12/21/2020 | 0 | 0 | 0 | 12/22/2020 | 12/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 443788 | 01854 | 11.02 | Solar | 05_01_225W4 | 07/19/2022 | 07/25/2022 | 4 | 2 | 2 | 07/26/2022 | 07/26/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2022 | 07/19/2022 | 2/2/2024 | Y | EXP | 365 | 02/02/2023 | 02/01/2023 | 0 | 0 | 0 |  |  | 2/28/2023 | Connected |  | N
National Grid | LEOMINSTER | 724654 | 01453 | 23 | Solar | 05_01_406L1 | 10/07/2025 | 10/13/2025 | 3 | 0 | 3 | 10/14/2025 | 10/14/2025 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 715702 | 01537 | 10 | Solar | 05_01_525L2 | 08/29/2025 | 09/26/2025 | 3 | 0 | 3 | 09/29/2025 | 09/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/29/2025 | 11/4/2026 | Y | EXP | 365 | 01/17/2026 |  | 49 | 0 | 49 |  |  |  | Construction |  | N
National Grid | WEST BROOKFIELD | 670286 | 01585 | 3.49 | Solar | 05_01_6W2 | 02/05/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | WORCESTER | 383763 | 01603 | 233.3 | Solar | 05_05_19W74 | 09/27/2021 | 10/12/2021 | 10 | 2 | 8 |  |  | 36 | 4 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 |  | 5/4/2024 | N | STD | 23 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | DIGHTON | 175081 | 02764 | 30 | Solar | 05_12_37W6 | 10/01/2013 | 10/01/2013 | 6 | 0 | 6 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2013 |  | 12/31/2013 | N | EXP | 7 |  |  | 0 | 0 | 0 | 12/23/2013 | 12/23/2013 | 12/27/2013 | Connected |  | N
National Grid | EVERETT | 660873 | 02149 | 5.76 | Solar | 05_14_21L1 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/16/2024 | 4/11/2026 | Y | EXP | 365 | 07/08/2025 |  | 242 | 0 | 242 |  |  |  | Completion Documents |  | Y
National Grid | TYNGSBORO | 500876 | 01879 | 200 | Solar | 05_14_54L3 | 03/31/2023 | 04/17/2023 | 10 | 0 | 10 | 04/18/2023 | 04/18/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 03/31/2023 | 3/2/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | METHUEN | 177698 | 01844 | 7.6 | Solar | 05_14_63L2 | 03/21/2017 | 03/21/2017 | 7 | 7 | 0 | 03/31/2017 | 03/31/2017 | 210 | 0 | 210 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2017 | 03/21/2017 | 3/27/2018 | Y | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 558692 | 01844 | 7.6 | Solar | 05_14_77L3 | 10/03/2023 | 10/05/2023 | 2 | 0 | 2 | 10/06/2023 | 10/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 | 10/03/2023 | 11/16/2024 | Y | EXP | 365 | 05/07/2024 | 07/24/2024 | 79 | 0 | 79 |  |  | 8/9/2024 | Connected |  | N
National Grid | LOWELL | 455958 | 01854 | 9.6 | Solar | 05_01_225W4 | 09/13/2022 | 09/15/2022 | 2 | 0 | 2 | 09/16/2022 | 09/16/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 | 09/13/2022 | 2/3/2024 | Y | EXP | 365 | 02/03/2023 | 02/02/2023 | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | LEOMINSTER | 746404 | 01453 | 20 | Solar | 05_01_406L1 | 01/21/2026 | 01/27/2026 | 4 | 0 | 4 | 01/28/2026 | 01/28/2026 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 719575 | 01537 | 7.6 | Solar | 05_01_525L2 | 10/06/2025 | 11/18/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROOKFIELD | 680789 | 01506 | 15.08 | Solar | 05_01_6W2 | 03/26/2025 | 03/28/2025 | 3 | 1 | 2 | 03/31/2025 | 03/31/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | WORCESTER | 390978 | 01602 | 150 | Solar | 05_05_19W74 | 10/29/2021 | 11/11/2021 | 8 | 0 | 8 |  |  | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2023 | 10/29/2021 | 5/2/2024 | Y | STD | 23 | 11/30/2023 | 01/22/2024 | 54 | 0 | 54 |  |  | 4/30/2024 | Connected |  | N
National Grid | DIGHTON | 177276 | 02715 | 5.2 | Solar | 05_12_37W6 | 02/06/2017 | 02/06/2017 | 4 | 4 | 0 | 02/13/2017 | 02/13/2017 | 194 | 0 | 194 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2017 |  | 2/12/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 706895 | 02149 | 7.6 | Solar | 05_14_21L1 | 07/23/2025 | 10/15/2025 | 7 | 4 | 3 | 11/13/2025 | 11/13/2025 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 07/23/2025 | 12/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | DRACUT | 702988 | 01826 | 11.78 | Solar | 05_14_54L3 | 07/06/2025 | 09/04/2025 | 43 | 42 | 1 | 09/05/2025 | 09/05/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 185125 | 01810 | 7.6 | Solar | 05_14_63L2 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/13/2018 | 06/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2018 |  | 6/17/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | METHUEN | 536046 | 01844 | 900 | Solar | 05_14_77L3 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 12/04/2023 | 67 | 48 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 490204 | 01854 | 7.68 | Solar | 05_01_225W4 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | Y
National Grid | LEOMINSTER | 750264 | 01453 | 5.76 | Solar | 05_01_406L1 | 02/10/2026 | 02/11/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LEICESTER | 729007 | 01524 | 7.6 | Solar | 05_01_525L2 | 10/24/2025 | 10/30/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 62 | 47 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROOKFIELD | 683397 | 01506 | 7.6 | Solar | 05_01_6W2 | 04/07/2025 | 04/24/2025 | 4 | 1 | 3 | 05/08/2025 | 05/08/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/07/2025 | 6/12/2026 | Y | EXP | 365 | 10/02/2025 | 10/03/2025 | 2 | 0 | 2 |  |  | 10/7/2025 | Connected |  | N
National Grid | WORCESTER | 393641 | 01603 | 10 | Solar | 05_05_19W74 | 12/06/2021 | 12/07/2021 | 1 | 0 | 1 | 12/08/2021 | 12/08/2021 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  | 1/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2022 | Connected |  | N
National Grid | DIGHTON | 178386 | 02715 | 7.6 | Solar | 05_12_37W6 | 01/15/2018 | 01/15/2018 | 0 | 0 | 0 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/21/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | EVERETT | 174504 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 734376 | 01826 | 37.82 | Solar | 05_14_54L3 | 11/17/2025 | 11/18/2025 | 1 | 0 | 1 | 11/19/2025 | 11/19/2025 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 188327 | 01810 | 7.6 | Solar | 05_14_63L2 | 06/18/2018 | 06/18/2018 | 7 | 3 | 4 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 6/28/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | METHUEN | 576999 | 01844 | 5.51 | Solar | 05_14_77L3 | 01/16/2024 | 12/14/2023 | 2 | 0 | 2 | 01/19/2024 | 01/19/2024 | 20 | 0 | 20 | 03/22/2024 | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 04/22/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 4/11/2024 | 01/16/2024 | 5/29/2025 | Y | EXP | 365 | 05/18/2024 | 06/06/2024 | 20 | 0 | 20 |  |  | 9/6/2024 | Connected |  | N
National Grid | LOWELL | 502848 | 01854 | 14.79 | Solar | 05_01_225W4 | 04/12/2023 | 04/17/2023 | 3 | 1 | 2 | 04/18/2023 | 04/18/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2023 | 04/12/2023 | 5/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2023 | Connected |  | N
National Grid | LEOMINSTER | 174214 | 01453 | 1000 | Solar | 05_01_406L1 | 12/20/2011 | 12/20/2011 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 730718 | 01537 | 10 | Solar | 05_01_525L2 | 11/02/2025 | 11/03/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 54 | 37 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BROOKFIELD | 687066 | 01506 | 15.2 | Solar | 05_01_6W2 | 04/23/2025 | 05/06/2025 | 9 | 5 | 4 | 05/07/2025 | 05/07/2025 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | WORCESTER | 402596 | 01603 | 2.03 | Solar | 05_05_19W74 | 01/05/2022 | 01/06/2022 | 1 | 0 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 5/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2022 | Connected |  | N
National Grid | DIGHTON | 329274 | 02764 | 5 | Solar | 05_12_37W6 | 01/08/2021 | 01/12/2021 | 1 | 0 | 1 | 01/13/2021 | 01/13/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/08/2021 | 8/3/2022 | Y | EXP | 365 | 06/02/2021 | 12/09/2021 | 191 | 7 | 184 |  |  | 12/22/2021 | Connected |  | N
National Grid | EVERETT | 174509 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 175182 | 01826 | 490 | Solar | 05_14_54L3 | 05/09/2013 | 05/09/2013 | 7 | 0 | 7 | 05/21/2013 | 05/21/2013 | 419 | 4 | 415 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2013 |  | 12/31/2013 | N | EXP | 181 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 188961 | 01810 | 1750 | Solar | 05_14_63L2 | 07/06/2018 | 09/05/2018 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2018 | 10/10/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 | 07/06/2018 | 9/27/2021 | Y | STD | 483 | 06/22/2021 | 08/02/2021 | 42 | 0 | 42 |  |  | 9/22/2021 | Connected |  | N
National Grid | METHUEN | 583929 | 01844 | 5.22 | Solar | 05_14_77L3 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 12 | 0 | 12 | 03/29/2024 | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/01/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 6/25/2025 | N | EXP | 365 | 10/24/2024 | 11/07/2024 | 15 | 0 | 15 |  |  | 12/16/2024 | Connected |  | N
National Grid | LOWELL | 503390 | 01854 | 16.24 | Solar | 05_01_225W4 | 02/20/2023 | 03/16/2023 | 19 | 18 | 1 | 03/17/2023 | 03/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 | 02/20/2023 | 4/26/2024 | Y | EXP | 365 | 07/06/2023 | 08/15/2023 | 41 | 0 | 41 |  |  | 1/31/2024 | Connected |  | N
National Grid | LEOMINSTER | 174473 | 01453 | 32.4 | Solar | 05_01_406L1 | 04/27/2011 | 04/27/2011 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2011 |  | 10/31/2012 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2013 | 1/25/2013 | 7/2/2012 | Connected |  | N
National Grid | CHARLTON | 734531 | 01507 | 11.52 | Solar | 05_01_525L2 | 11/18/2025 | 11/19/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROOKFIELD | 692430 | 01506 | 10 | Solar | 05_01_6W2 | 08/22/2025 | 09/11/2025 | 12 | 9 | 3 | 09/11/2025 | 09/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | WORCESTER | 425019 | 01603 | 7.68 | Solar | 05_05_19W74 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 290 | 270 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 06/27/2022 | 9/13/2024 | Y | EXP | 365 | 11/28/2023 | 01/16/2024 | 50 | 3 | 47 |  |  | 1/20/2024 | Connected |  | N
National Grid | DIGHTON | 454546 | 02715 | 15.744 | Solar | 05_12_37W6 | 08/26/2022 | 09/23/2022 | 20 | 19 | 1 | 09/26/2022 | 09/26/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | EVERETT | 174508 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 175885 | 01826 | 6.75 | Solar | 05_14_54L3 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 |  | 10/30/2015 | N | EXP | 151 |  |  | 0 | 0 | 0 | 8/26/2015 | 8/26/2015 | 9/1/2015 | Connected |  | N
National Grid | ANDOVER | 194325 | 01810 | 7.6 | Solar | 05_14_63L2 | 11/18/2018 | 11/29/2018 | 6 | 0 | 6 | 11/30/2018 | 11/30/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 |  | 11/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | METHUEN | 599934 | 01844 | 15.2 | Solar | 05_14_77L3 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 578035 | 01854 | 8.7 | Solar | 05_01_225W4 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 23 | 0 | 23 | 04/05/2024 | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 09/19/2024 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 5/29/2024 |  | 5/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | LEOMINSTER | 174794 | 01453 | 1000 | Solar | 05_01_406L1 | 07/05/2011 | 07/05/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2012 | 07/05/2011 | 7/24/2012 | Y | STD | 1 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 7/24/2012 | Connected |  | N
National Grid | OXFORD | 751044 | 01537 | 7.6 | Solar | 05_01_525L2 | 02/13/2026 | 02/16/2026 | 2 | 0 | 2 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEST BROOKFIELD | 711191 | 01585 | 5.76 | Solar | 05_01_6W2 | 08/11/2025 | 08/29/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | WORCESTER | 458078 | 01611 | 13 | Solar | 05_05_19W74 | 09/15/2022 | 09/16/2022 | 1 | 0 | 1 | 09/19/2022 | 09/19/2022 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 566763 | 02764 | 7.6 | Solar | 05_12_37W6 | 11/02/2023 | 11/08/2023 | 4 | 2 | 2 | 11/09/2023 | 11/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 174507 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 177008 | 01826 | 494.5 | Solar | 05_14_54L3 | 10/13/2016 | 10/13/2016 | 0 | 0 | 0 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 02/16/2017 | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 | 10/13/2016 | 4/9/2018 | Y | EXP | 374 | 06/01/2017 | 06/01/2017 | 0 | 0 | 0 | 4/3/2018 | 4/3/2018 | 4/3/2018 | Connected |  | N
National Grid | ANDOVER | 195141 | 01810 | 15.2 | Solar | 05_14_63L2 | 09/05/2018 | 10/17/2018 | 31 | 26 | 5 | 10/18/2018 | 10/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2018 |  | 7/5/2019 | N | EXP | 256 |  |  | 0 | 0 | 0 |  |  | 6/21/2019 | Connected |  | N
National Grid | METHUEN | 616157 | 01844 | 13.6 | Solar | 05_14_77L3 | 06/06/2024 | 06/25/2024 | 3 | 1 | 2 | 06/26/2024 | 06/26/2024 | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/06/2024 | 10/12/2025 | Y | EXP | 365 | 10/30/2024 | 01/23/2025 | 86 | 0 | 86 |  |  | 2/13/2025 | Connected |  | N
National Grid | TYNGSBORO | 598623 | 01879 | 15.2 | Solar | 05_01_225W4 | 03/21/2024 | 03/26/2024 | 14 | 12 | 2 | 08/12/2024 | 08/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | LEOMINSTER | 174835 | 01453 | 0 | Solar | 05_01_406L1 | 08/03/2011 | 08/03/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2012 | 08/03/2011 | 12/31/2012 | Y | STD | 277 | 07/09/2012 | 10/18/2012 | 71 | 0 | 71 | 9/27/2012 | 9/27/2012 | 10/16/2012 | Connected |  | N
National Grid | CHARLTON | 174181 | 01507 | 800 | Solar | 05_01_525L2 | 10/14/2011 | 10/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2013 | 10/14/2011 | 3/1/2014 | Y | STD | 325 |  |  | 0 | 0 | 0 | 6/3/2015 | 6/3/2015 | 6/19/2015 | Connected |  | N
National Grid | BROOKFIELD | 742103 | 01506 | 5.76 | Solar | 05_01_6W2 | 12/23/2025 | 12/29/2025 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 532519 | 01602 | 11.4 | Solar | 05_05_19W74 | 06/13/2023 | 06/26/2023 | 8 | 5 | 3 | 06/27/2023 | 06/27/2023 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 8/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | DIGHTON | 591336 | 02715 | 10 | Solar | 05_12_37W6 | 03/27/2024 | 04/01/2024 | 3 | 0 | 3 | 04/02/2024 | 04/02/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/27/2024 | 11/30/2025 | Y | EXP | 365 | 09/19/2024 | 10/02/2025 | 379 | 0 | 379 |  |  | 11/7/2025 | Connected |  | N
National Grid | EVERETT | 174506 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 178419 | 01826 | 19 | Solar | 05_14_54L3 | 01/16/2018 | 01/16/2018 | 23 | 0 | 23 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 1/22/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | ANDOVER | 195563 | 01810 | 180 | Solar | 05_14_63L2 | 09/11/2018 | 10/03/2018 | 15 | 0 | 15 | 10/04/2018 | 10/04/2018 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2020 | Connected |  | N
National Grid | METHUEN | 644945 | 01844 | 3.8 | Solar | 05_14_77L3 | 10/03/2024 | 10/29/2024 | 5 | 1 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  | 1/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | Y
National Grid | TYNGSBORO | 612544 | 01879 | 5.76 | Solar | 05_01_225W4 | 05/21/2024 | 07/01/2024 | 2 | 0 | 2 | 07/02/2024 | 07/02/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 05/21/2024 | 7/31/2025 | Y | EXP | 365 | 09/18/2024 | 09/17/2024 | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | LEOMINSTER | 174948 | 01453 | 1000 | Solar | 05_01_406L1 | 11/18/2011 | 11/18/2011 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2012 | 03/12/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/3/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174180 | 01524 | 1400 | Solar | 05_01_525L2 | 10/17/2011 | 10/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2014 | 10/17/2011 | 12/31/2016 | Y | STD | 123 |  |  | 0 | 0 | 0 | 1/28/2016 | 1/28/2016 | 1/29/2016 | Connected |  | N
National Grid | WEST BROOKFIELD | 716720 | 01585 | 7.6 | Solar | 05_01_7J386 | 09/04/2025 | 09/22/2025 | 5 | 0 | 5 | 10/02/2025 | 10/02/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 09/04/2025 | 11/15/2026 | Y | EXP | 365 | 01/13/2026 | 02/10/2026 | 29 | 0 | 29 |  |  |  | Meter Installation |  | Y
National Grid | WORCESTER | 541084 | 01602 | 10 | Solar | 05_05_19W74 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 58 | 37 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 | 07/18/2023 | 10/18/2024 | Y | EXP | 365 | 10/25/2023 | 01/22/2024 | 90 | 3 | 87 |  |  | 1/25/2024 | Connected |  | N
National Grid | DIGHTON | 596442 | 02764 | 7.6 | Solar | 05_12_37W6 | 03/21/2024 | 03/27/2024 | 4 | 0 | 4 | 03/28/2024 | 03/28/2024 | 101 | 96 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 174505 | 02149 | 33.3 | Solar | 05_14_21L1 | 09/27/2011 | 09/27/2011 | 87 | 0 | 87 | 02/03/2012 | 02/03/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2012 |  | 10/31/2012 | N | EXP | 225 |  |  | 0 | 0 | 0 | 1/29/2013 | 1/29/2013 | 2/12/2013 | Connected |  | N
National Grid | DRACUT | 178410 | 01826 | 34.5 | Solar | 05_14_54L3 | 11/22/2017 | 11/22/2017 | 8 | 0 | 8 | 12/07/2017 | 12/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 |  | 12/2/2018 | N | EXP | 193 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 197393 | 01810 | 7.6 | Solar | 05_14_63L2 | 10/01/2018 | 10/26/2018 | 4 | 4 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 722435 | 01844 | 23 | Solar | 05_14_77L3 | 10/31/2025 | 11/12/2025 | 6 | 1 | 5 | 11/13/2025 | 11/13/2025 | 50 | 28 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | TYNGSBORO | 661154 | 01879 | 2.61 | Solar | 05_01_225W4 | 12/17/2024 | 01/24/2025 | 9 | 4 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 12/17/2024 | 3/14/2026 | Y | EXP | 365 | 05/17/2025 | 05/28/2025 | 12 | 0 | 12 |  |  | 6/7/2025 | Connected |  | N
National Grid | LEOMINSTER | 175031 | 01453 | 1000 | Solar | 05_01_406L1 | 03/21/2013 | 03/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2013 | 05/07/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174550 | 01524 | 39 | Solar | 05_01_525L2 | 07/25/2012 | 07/25/2012 | 7 | 0 | 7 | 08/06/2012 | 08/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 07/25/2012 | 10/31/2012 | Y | EXP | 42 | 03/29/2013 | 03/29/2013 | 0 | 0 | 0 | 3/29/2013 | 3/29/2013 | 4/16/2013 | Connected |  | N
National Grid | WEST BROOKFIELD | 730496 | 01585 | 5.76 | Solar | 05_01_7J386 | 10/30/2025 | 11/01/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 29 | 17 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 543936 | 01603 | 7.68 | Solar | 05_05_19W74 | 07/28/2023 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOMERSET | 633047 | 02726 | 3.8 | Solar | 05_12_37W6 | 08/15/2024 | 08/30/2024 | 3 | 0 | 3 | 09/03/2024 | 09/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 176937 | 02149 | 6 | Solar | 05_14_21L1 | 01/29/2016 | 01/29/2016 | 6 | 6 | 0 | 02/09/2016 | 02/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2016 |  | 2/6/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 6/10/2016 | Connected |  | N
National Grid | DRACUT | 190956 | 01826 | 77 | Solar | 05_14_54L3 | 07/17/2018 | 08/03/2018 | 9 | 6 | 3 | 08/06/2018 | 08/06/2018 | 9 | 0 | 9 | 10/05/2018 | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  | 10/1/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | ANDOVER | 205248 | 01810 | 10 | Solar | 05_14_63L2 | 01/25/2019 | 03/14/2019 | 32 | 26 | 6 | 03/15/2019 | 03/15/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 173451 | 01844 | 11.4 | Solar | 05_14_78L1 | 04/11/2018 | 04/11/2018 | 10 | 5 | 5 | 07/11/2018 | 07/11/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 | 04/11/2018 | 8/30/2019 | Y | EXP | 49 | 04/23/2019 | 04/22/2019 | 0 | 0 | 0 |  |  | 8/8/2019 | Connected |  | N
National Grid | LOWELL | 666188 | 01854 | 10 | Solar | 05_01_225W4 | 01/16/2025 | 02/14/2025 | 5 | 1 | 4 | 02/18/2025 | 02/18/2025 | 103 | 88 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEOMINSTER | 175133 | 01453 | 500 | Solar | 05_01_406L1 | 11/08/2012 | 11/08/2012 | 4 | 0 | 4 | 11/26/2012 | 11/26/2012 | 435 | 0 | 435 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/16/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 174597 | 01524 | 300 | Solar | 05_01_525L2 | 10/13/2011 | 10/13/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2011 | 10/13/2011 | 3/28/2012 | Y | EXP | 99 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 3/28/2012 | Connected |  | N
National Grid | WEST BROOKFIELD | 178422 | 01585 | 4000 | Solar | 05_01_7J386 | 01/16/2018 | 02/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 03/20/2018 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 565988 | 01603 | 10 | Solar | 05_05_19W74 | 11/01/2023 | 11/06/2023 | 3 | 2 | 1 | 11/07/2023 | 11/07/2023 | 57 | 26 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DIGHTON | 635118 | 02764 | 4.35 | Solar | 05_12_37W6 | 08/26/2024 | 10/14/2024 | 5 | 0 | 5 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 178450 | 02149 | 3.8 | Solar | 05_14_21L1 | 11/29/2017 | 11/29/2017 | 39 | 36 | 3 | 01/29/2018 | 01/29/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/31/2020 | N | EXP | 422 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 194950 | 01826 | 10 | Solar | 05_14_54L3 | 10/03/2018 | 10/04/2018 | 0 | 0 | 0 | 10/05/2018 | 10/05/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 |  | 10/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2019 | Connected |  | N
National Grid | ANDOVER | 204947 | 01845 | 3.8 | Solar | 05_14_63L2 | 01/16/2019 | 01/30/2019 | 9 | 8 | 1 | 01/31/2019 | 01/31/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 175869 | 01844 | 22.8 | Solar | 05_14_78L1 | 09/25/2015 | 09/25/2015 | 3 | 3 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/3/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 | 12/7/2015 | 12/7/2015 | 12/7/2015 | Connected |  | N
National Grid | DRACUT | 417558 | 01826 | 4999.2 | Solar | 05_01_226L1 | 04/20/2022 | 06/21/2022 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/20/2022 | 9/27/2027 | Y | STD | 673 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 175340 | 01453 | 1000 | Solar | 05_01_406L1 | 01/16/2015 | 01/16/2015 | 24 | 21 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2015 | 04/21/2015 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 09/30/2015 | 10/29/2015 | 20 | 0 | 20 | 10/29/2015 | 01/16/2015 | 3/31/2018 | Y | STD | 884 |  |  | 0 | 0 | 0 | 7/24/2017 | 7/24/2017 | 3/26/2018 | Connected |  | N
National Grid | CHARLTON | 175312 | 01507 | 1414 | Solar | 05_01_525L2 | 06/27/2014 | 06/27/2014 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2014 | 08/07/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 08/11/2016 | 08/11/2016 | 0 | 0 | 0 | 3/23/2015 | 06/27/2014 | 2/18/2016 | Y | STD | 332 | 03/31/2016 | 06/08/2016 | 47 | 0 | 47 | 8/23/2016 | 8/23/2016 | 8/23/2016 | Connected |  | N
National Grid | WEST BROOKFIELD | 190628 | 01585 | 5 | Solar | 05_01_7J386 | 07/13/2018 | 08/29/2018 | 23 | 0 | 23 | 08/30/2018 | 08/30/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 611840 | 01501 | 3 | Solar | 05_05_19W74 | 05/31/2024 | 06/21/2024 | 7 | 6 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | DIGHTON | 637627 | 02715 | 10 | Solar | 05_12_37W6 | 09/04/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 | 09/04/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | EVERETT | 178635 | 02149 | 0 | Solar | 05_14_21L1 | 04/09/2018 | 04/09/2018 | 6 | 0 | 6 | 04/18/2018 | 04/18/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | Connected |  | N
National Grid | DRACUT | 206827 | 01826 | 0 | Solar | 05_14_54L3 | 01/25/2019 | 02/11/2019 | 10 | 0 | 10 | 07/30/2019 | 07/30/2019 | 249 | 121 | 128 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/14/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 244231 | 01845 | 7.6 | Solar | 05_14_63L2 | 07/23/2019 | 08/02/2019 | 7 | 2 | 5 | 08/05/2019 | 08/05/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  | 8/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | METHUEN | 177087 | 01844 | 170 | Solar | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2016 | 10/14/2016 | 6/11/2019 | Y | EXP | 91 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | DRACUT | 541794 | 01826 | 999 | Solar | 05_01_226L1 | 10/13/2023 | 12/18/2023 | 45 | 36 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2024 | 03/14/2025 | 54 | 0 | 54 | 10/4/2024 | 10/13/2023 | 9/26/2026 | Y | CMPX | 358 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | PEPPERELL | 175439 | 01463 | 1000 | Solar | 05_01_406L1 | 11/24/2014 | 11/24/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 01/02/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2015 |  | 8/30/2016 | N | STD | 411 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 175469 | 01524 | 2250 | Solar | 05_01_525L2 | 11/25/2014 | 11/25/2014 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2014 | 01/06/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 195599 | 01585 | 7.6 | Solar | 05_01_7J386 | 09/11/2018 | 12/03/2018 | 26 | 20 | 6 | 12/04/2018 | 12/04/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 614244 | 01603 | 11.4 | Solar | 05_05_19W74 | 05/30/2024 | 06/11/2024 | 9 | 7 | 2 | 06/12/2024 | 06/12/2024 | 14 | 5 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 | 05/30/2024 | 8/5/2025 | Y | EXP | 365 | 08/29/2024 | 09/24/2024 | 27 | 0 | 27 |  |  | 9/25/2024 | Connected |  | N
National Grid | DIGHTON | 647126 | 02715 | 7.6 | Solar | 05_12_37W6 | 10/23/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | EVERETT | 193380 | 02149 | 7.6 | Solar | 05_14_21L1 | 10/18/2018 | 10/24/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 10/18/2018 | 7/15/2021 | Y | EXP | 365 | 11/14/2020 | 12/10/2020 | 26 | 0 | 26 |  |  | 12/29/2020 | Connected |  | N
National Grid | DRACUT | 292996 | 01826 | 10 | Solar | 05_14_54L3 | 05/21/2020 | 05/22/2020 | 0 | 0 | 0 | 05/26/2020 | 05/26/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2020 |  | 5/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | ANDOVER | 259289 | 01810 | 7.6 | Solar | 05_14_63L2 | 10/17/2019 | 10/22/2019 | 2 | 0 | 2 | 10/23/2019 | 10/23/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 | 10/17/2019 | 7/7/2020 | Y | EXP | 365 | 03/13/2020 | 06/01/2020 | 80 | 0 | 80 |  |  | 6/5/2020 | Connected |  | N
National Grid | METHUEN | 177116 | 01844 | 150 | Solar | 05_14_78L1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2017 | 10/14/2016 | 3/11/2019 | Y | EXP | 774 |  |  | 0 | 0 | 0 |  |  | 2/26/2019 | Connected |  | N
National Grid | DRACUT | 701906 | 01826 | 10.64 | Solar | 05_01_226L1 | 07/05/2025 | 07/23/2025 | 5 | 2 | 3 | 08/04/2025 | 08/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 07/05/2025 | 9/19/2026 | Y | EXP | 365 | 01/13/2026 | 03/05/2026 | 52 | 0 | 52 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 175598 | 01463 | 772.8 | Solar | 05_01_406L1 | 08/01/2014 | 08/01/2014 | 15 | 10 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2014 | 09/22/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2014 |  | 12/31/2016 | N | STD | 739 |  |  | 0 | 0 | 0 | 6/20/2016 | 6/20/2016 | 7/20/2016 | Connected |  | N
National Grid | CHARLTON | 175494 | 01507 | 480 | Solar | 05_01_525L2 | 07/23/2014 | 07/23/2014 | 7 | 0 | 7 | 08/05/2014 | 08/05/2014 | 72 | 0 | 72 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 201180 | 01585 | 5 | Solar | 05_01_7J386 | 11/14/2018 | 11/15/2018 | 7 | 0 | 7 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 11/14/2018 | 11/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | WORCESTER | 616349 | 01603 | 7.6 | Solar | 05_05_19W74 | 06/07/2024 | 08/13/2024 | 5 | 0 | 5 | 08/14/2024 | 08/14/2024 | 13 | 6 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 | 06/07/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | DIGHTON | 176325 | 02715 | 495 | Solar | 05_12_37W7 | 07/14/2015 | 07/14/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/21/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 285172 | 02149 | 5 | Solar | 05_14_21L1 | 04/01/2020 | 05/28/2020 | 5 | 4 | 1 | 05/29/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 | 04/01/2020 | 5/28/2021 | Y | EXP | 365 | 10/24/2020 | 11/19/2020 | 26 | 0 | 26 |  |  | 11/20/2020 | Connected |  | N
National Grid | DRACUT | 299887 | 01826 | 6 | Solar | 05_14_54L3 | 07/07/2020 | 07/09/2020 | 1 | 0 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | ANDOVER | 269213 | 01845 | 9.84 | Solar | 05_14_63L2 | 12/11/2019 | 12/13/2019 | 2 | 2 | 0 | 12/16/2019 | 12/16/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2020 |  | 12/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | METHUEN | 178082 | 01844 | 16.08 | Solar | 05_14_78L1 | 05/09/2017 | 05/09/2017 | 195 | 195 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 723303 | 01826 | 13.611 | Solar | 05_01_226L1 | 10/07/2025 | 10/14/2025 | 2 | 0 | 2 | 10/30/2025 | 10/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 | 10/07/2025 | 12/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | PEPPERELL | 175650 | 01463 | 18 | Solar | 05_01_406L1 | 12/17/2014 | 12/17/2014 | 5 | 1 | 4 | 12/26/2014 | 12/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2015 | 12/17/2014 | 12/31/2016 | Y | EXP | 71 |  |  | 0 | 0 | 0 | 8/30/2016 | 8/30/2016 | 8/30/2016 | Connected |  | N
National Grid | CHARLTON | 175792 | 01507 | 1000 | Solar | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 | 09/16/2015 | 9/23/2016 | Y | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | BROOKFIELD | 227161 | 01515 | 5 | Solar | 05_01_7J386 | 05/20/2019 | 05/28/2019 | 63 | 11 | 52 | 05/29/2019 | 05/29/2019 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 628852 | 01603 | 5 | Solar | 05_05_19W74 | 07/30/2024 | 08/13/2024 | 4 | 3 | 1 | 08/14/2024 | 08/14/2024 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | SOMERSET | 221781 | 02726 | 100 | Solar | 05_12_37W7 | 04/23/2019 | 04/25/2019 | 1 | 0 | 1 | 04/26/2019 | 04/26/2019 | 11 | 3 | 8 | 06/25/2019 | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 07/30/2019 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 8/2/2019 |  | 8/3/2020 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  | 3/9/2020 | Connected |  | N
National Grid | MALDEN | 368249 | 02148 | 7.6 | Solar | 05_14_21L1 | 07/07/2021 | 07/29/2021 | 17 | 16 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2021 |  | 9/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | DRACUT | 301678 | 01826 | 10 | Solar | 05_14_54L3 | 07/16/2020 | 07/21/2020 | 3 | 3 | 0 | 07/22/2020 | 07/22/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | ANDOVER | 278631 | 01810 | 7.6 | Solar | 05_14_63L2 | 03/05/2020 |  | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 178663 | 01844 | 42 | Solar | 05_14_78L1 | 03/16/2018 | 03/16/2018 | 5 | 0 | 5 | 03/23/2018 | 03/23/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 3/21/2019 | N | EXP | 316 | 10/31/2018 | 02/07/2019 | 99 | 0 | 99 |  |  | 5/1/2019 | Connected |  | N
National Grid | DRACUT | 742259 | 01826 | 11.5 | Solar | 05_01_226L1 | 12/26/2025 | 12/30/2025 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PEPPERELL | 175729 | 01463 | 996 | Solar | 05_01_406L1 | 06/03/2014 | 06/03/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2014 | 07/10/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2014 | 06/03/2014 | 4/23/2016 | Y | STD | 516 | 10/20/2015 | 04/27/2016 | 128 | 0 | 128 | 6/5/2014 | 6/5/2014 | 5/12/2016 | Connected |  | N
National Grid | CHARLTON | 175791 | 01507 | 1000 | Solar | 05_01_525L2 | 09/16/2015 | 09/16/2015 | 26 | 26 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 9/23/2016 | N | STD | 148 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 | 11/17/2017 | 11/17/2017 | 11/17/2017 | Connected |  | N
National Grid | NORTH BROOKFIELD | 340849 | 01535 | 15.2 | Solar | 05_01_7J386 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 | 02/05/2021 | 1/20/2023 | Y | EXP | 475 | 10/05/2022 | 11/14/2022 | 41 | 0 | 41 |  |  | 12/21/2022 | Connected |  | N
National Grid | WORCESTER | 647648 | 01603 | 3.8 | Solar | 05_05_19W74 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/16/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | SOMERSET | 448424 | 02726 | 67.3 | Solar | 05_12_37W7 | 08/08/2022 | 08/17/2022 | 7 | 0 | 7 | 08/18/2022 | 08/18/2022 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2022 |  | 12/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | MALDEN | 372068 | 02148 | 15.2 | Solar | 05_14_21L1 | 07/26/2021 | 07/28/2021 | 3 | 2 | 1 | 07/29/2021 | 07/29/2021 | 64 | 43 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 | 07/26/2021 | 9/5/2023 | Y | EXP | 365 | 01/18/2022 | 09/02/2022 | 227 | 0 | 227 |  |  |  | Withdrawn |  | N
National Grid | TYNGSBORO | 320280 | 01879 | 8 | Solar | 05_14_54L3 | 10/20/2020 | 11/10/2020 | 14 | 13 | 1 | 11/12/2020 | 11/12/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 11/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2021 | Connected |  | N
National Grid | ANDOVER | 360395 | 01810 | 8.99 | Solar | 05_14_63L2 | 07/27/2021 | 12/28/2021 | 10 | 8 | 2 | 08/11/2021 | 08/11/2021 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2021 | 07/27/2021 |  | Y | EXP | 365 | 03/08/2022 | 03/30/2022 | 23 | 0 | 23 |  |  | 4/7/2022 | Connected |  | N
National Grid | METHUEN | 178685 | 01844 | 7.6 | Solar | 05_14_78L1 | 12/18/2017 | 12/18/2017 | 8 | 0 | 8 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/24/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | DRACUT | 175223 | 01826 | 5 | Solar | 05_01_226L1 | 01/05/2015 | 01/05/2015 | 28 | 25 | 3 | 02/17/2015 | 02/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2015 |  | 5/31/2015 | N | EXP | 13 |  |  | 0 | 0 | 0 | 5/11/2015 | 5/11/2015 | 2/11/2016 | Connected |  | N
National Grid | PEPPERELL | 175808 | 01463 | 100 | Solar | 05_01_406L1 | 05/18/2015 | 05/18/2015 | 5 | 5 | 0 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2015 |  | 12/31/2016 | N | EXP | 54 |  |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 9/16/2016 | Connected |  | N
National Grid | OXFORD | 176288 | 01540 | 17.4 | Solar | 05_01_525L2 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 394 | 0 | 394 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2015 |  | 7/18/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 341888 | 01535 | 7.6 | Solar | 05_01_7J386 | 02/11/2021 | 02/12/2021 | 0 | 0 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/11/2021 | 7/21/2023 | Y | EXP | 365 | 09/23/2021 | 01/17/2022 | 117 | 4 | 113 |  |  | 10/12/2022 | Connected |  | N
National Grid | LEICESTER | 677411 | 01611 | 5.76 | Solar | 05_05_19W74 | 03/12/2025 | 03/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 476941 | 02764 | 9.074 | Solar | 05_12_37W7 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 11/11/2022 | 1/23/2024 | Y | EXP | 365 | 07/01/2023 | 11/03/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | MALDEN | 403830 | 02148 | 50 | Solar | 05_14_21L1 | 01/11/2022 | 02/02/2022 | 16 | 10 | 6 | 02/03/2022 | 02/03/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 | 01/11/2022 | 10/9/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | TYNGSBORO | 326749 | 01879 | 10 | Solar | 05_14_54L3 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2021 | Connected |  | N
National Grid | ANDOVER | 367847 | 01810 | 7.6 | Solar | 05_14_63L2 | 07/19/2021 | 07/22/2021 | 3 | 0 | 3 | 07/23/2021 | 07/23/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2021 | 07/19/2021 |  | Y | EXP | 365 | 01/21/2022 | 01/24/2022 | 4 | 0 | 4 |  |  | 4/4/2022 | Connected |  | N
National Grid | METHUEN | 188124 | 01844 | 15.2 | Solar | 05_14_78L1 | 06/14/2018 | 06/14/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 175461 | 01826 | 499 | Solar | 05_01_226L1 | 09/23/2014 | 09/23/2014 | 32 | 27 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 | 12/04/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 175875 | 01463 | 2000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | OXFORD | 176669 | 01540 | 499 | Solar | 05_01_525L2 | 10/20/2015 | 10/20/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 11/23/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2016 |  | 10/26/2016 | N | STD | 181 | 08/22/2017 | 11/14/2017 | 52 | 0 | 52 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 627279 | 01585 | 4.06 | Solar | 05_01_7J386 | 07/24/2024 | 07/30/2024 | 3 | 2 | 1 | 07/31/2024 | 07/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 07/24/2024 | 8/13/2025 | Y | EXP | 365 | 10/29/2024 | 10/28/2024 | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | LEICESTER | 685887 | 01611 | 15.2 | Solar | 05_05_19W74 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 656154 | 02715 | 10 | Solar | 05_12_37W7 | 11/25/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | MALDEN | 414979 | 02148 | 15.2 | Solar | 05_14_21L1 | 03/02/2022 | 03/23/2022 | 16 | 15 | 1 | 03/24/2022 | 03/24/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 326283 | 01826 | 11.4 | Solar | 05_14_54L3 | 11/16/2020 | 11/18/2020 | 1 | 0 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 2/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2021 | Connected |  | N
National Grid | ANDOVER | 392062 | 01810 | 8.7 | Solar | 05_14_63L2 | 11/29/2021 | 02/07/2022 | 48 | 44 | 4 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 196115 | 01844 | 10 | Solar | 05_14_78L1 | 09/17/2018 | 10/30/2018 | 19 | 18 | 1 | 10/31/2018 | 10/31/2018 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 09/17/2018 | 5/27/2019 | Y | EXP | 181 | 02/21/2019 | 02/20/2019 | 0 | 0 | 0 |  |  | 5/13/2019 | Connected |  | N
National Grid | DRACUT | 175774 | 01826 | 990 | Solar | 05_01_226L1 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/26/2014 | 09/25/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 10/08/2015 | 10/28/2015 | 13 | 13 | 0 | 12/11/2015 | 08/15/2014 | 7/30/2016 | Y | STD | 232 | 04/06/2016 | 07/28/2016 | 77 | 0 | 77 | 7/21/2016 | 7/21/2016 | 7/28/2016 | Connected |  | N
National Grid | PEPPERELL | 175878 | 01463 | 1000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | LEICESTER | 176811 | 01524 | 2000 | Solar | 05_01_525L2 | 11/05/2015 | 11/05/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2015 | 12/08/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 636729 | 01535 | 5.76 | Solar | 05_01_7J386 | 08/30/2024 | 09/06/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 2/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | N
National Grid | WORCESTER | 688155 | 01603 | 15.58 | Solar | 05_05_19W74 | 04/28/2025 | 05/05/2025 | 5 | 1 | 4 | 05/06/2025 | 05/06/2025 | 37 | 22 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 | 04/28/2025 | 7/11/2026 | Y | EXP | 365 | 08/19/2025 | 10/03/2025 | 46 | 0 | 46 |  |  | 11/1/2025 | Connected |  | N
National Grid | DIGHTON | 304213 | 02764 | 6 | Solar | 05_12_37W8 | 09/24/2020 | 12/23/2020 | 61 | 40 | 21 | 12/24/2020 | 12/24/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 490227 | 02148 | 7.6 | Solar | 05_14_21L1 | 01/06/2023 | 01/09/2023 | 1 | 0 | 1 | 01/10/2023 | 01/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 338222 | 01826 | 11.52 | Solar | 05_14_54L3 | 01/22/2021 | 01/28/2021 | 4 | 4 | 0 | 01/29/2021 | 01/29/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | ANDOVER | 402955 | 01810 | 99.9 | Solar | 05_14_63L2 | 07/12/2022 | 09/07/2022 | 41 | 30 | 11 | 09/08/2022 | 09/08/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 192918 | 01844 | 7.6 | Solar | 05_14_78L1 | 08/07/2018 | 10/26/2018 | 7 | 7 | 0 | 10/29/2018 | 10/29/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 175871 | 01826 | 7.6 | Solar | 05_01_226L1 | 09/25/2015 | 09/25/2015 | 2 | 2 | 0 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 10/4/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 12/2/2015 | 12/2/2015 | 12/2/2015 | Connected |  | N
National Grid | PEPPERELL | 175877 | 01463 | 2000 | Solar | 05_01_406L1 | 03/06/2015 | 03/06/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2015 | 04/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 01/22/2016 | 05/17/2016 | 79 | 0 | 79 | 5/17/2016 | 03/06/2015 | 12/31/2017 | Y | STD | 593 | 03/02/2018 | 03/02/2018 | 0 | 0 | 0 | 12/31/2017 | 12/31/2017 | 12/31/2017 | Connected |  | N
National Grid | LEICESTER | 177650 | 01524 | 500 | Solar | 05_01_525L2 | 09/27/2017 | 09/27/2017 | 63 | 58 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/10/2018 | 02/01/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 654479 | 01535 | 5.76 | Solar | 05_01_7J386 | 11/18/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 690064 | 01603 | 18.62 | Solar | 05_05_19W74 | 05/06/2025 | 05/16/2025 | 7 | 0 | 7 | 05/19/2025 | 05/19/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 05/06/2025 | 6/12/2026 | Y | EXP | 365 | 06/25/2025 | 07/23/2025 | 29 | 0 | 29 |  |  | 9/6/2025 | Connected |  | N
National Grid | SOMERSET | 387541 | 02726 | 7.6 | Solar | 05_12_37W8 | 10/10/2021 |  | 147 | 137 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 626584 | 02148 | 3.8 | Solar | 05_14_21L1 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2024 | 07/22/2024 | 8/29/2025 | Y | EXP | 365 | 09/19/2024 | 10/11/2024 | 23 | 0 | 23 |  |  | 11/22/2024 | Connected |  | N
National Grid | DRACUT | 359718 | 01826 | 54.6 | Solar | 05_14_54L3 | 05/26/2021 | 06/08/2021 | 7 | 1 | 6 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2021 |  | 8/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | ANDOVER | 408867 | 01845 | 0 | Other | 05_14_63L2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 193202 | 01844 | 15.2 | Solar | 05_14_78L1 | 08/10/2018 | 09/10/2018 | 6 | 6 | 0 | 09/11/2018 | 09/11/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2018 | 08/10/2018 | 7/7/2020 | Y | EXP | 5 | 02/14/2019 | 03/11/2019 | 25 | 0 | 25 |  |  | 6/19/2020 | Connected |  | N
National Grid | DRACUT | 176103 | 01826 | 6 | Solar | 05_01_226L1 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/28/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 12/1/2015 | Connected |  | N
National Grid | PEPPERELL | 176149 | 01463 | 6 | Solar | 05_01_406L1 | 08/25/2015 | 08/25/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 606 | 0 | 606 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 9/5/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LEICESTER | 177789 | 01524 | 4500 | Solar | 05_01_525L2 | 06/05/2017 | 06/12/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2017 | 07/05/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 06/05/2017 | 7/15/2020 | Y | STD | 632 | 06/28/2019 | 06/01/2020 | 339 | 0 | 339 |  |  | 7/14/2020 | Connected |  | N
National Grid | BROOKFIELD | 662745 | 01506 | 10 | Solar | 05_01_7J386 | 12/27/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 141 | 117 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 689939 | 01603 | 23.18 | Solar | 05_05_19W74 | 05/06/2025 | 05/21/2025 | 10 | 7 | 3 | 05/22/2025 | 05/22/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 8/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2025 | Connected |  | N
National Grid | DIGHTON | 662091 | 02764 | 3.8 | Solar | 05_12_37W8 | 12/20/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 626563 | 02148 | 0 | Battery Add-On | 05_14_21L1 | 07/23/2024 | 08/14/2024 | 6 | 0 | 6 | 08/15/2024 | 08/15/2024 | 33 | 21 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | DRACUT | 405836 | 01826 | 0 | Battery Add-On | 05_14_54L3 | 01/24/2022 | 02/03/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2022 | 03/02/2022 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 414323 | 01810 | 499 | Solar | 05_14_63L2 | 04/01/2022 | 05/25/2022 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2022 | 06/28/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/01/2022 | 1/20/2025 | Y | STD | 43 | 04/19/2024 | 08/16/2024 | 120 | 28 | 92 |  |  | 1/17/2025 | Connected |  | N
National Grid | METHUEN | 214576 | 01844 | 3 | Solar | 05_14_78L1 | 03/22/2019 | 03/29/2019 | 4 | 0 | 4 | 04/01/2019 | 04/01/2019 | 125 | 25 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 177228 | 01826 | 38 | Solar | 05_01_226L1 | 11/02/2016 | 11/02/2016 | 2 | 2 | 0 | 11/07/2016 | 11/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/8/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | PEPPERELL | 176593 | 01463 | 496 | Solar | 05_01_406L1 | 10/09/2015 | 10/12/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2015 | 06/04/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 07/15/2016 | 06/04/2018 | 44 | 5 | 39 | 2/21/2017 | 10/09/2015 | 1/31/2020 | Y | STD | 982 | 03/14/2019 | 12/02/2019 | 263 | 81 | 182 |  |  | 1/14/2020 | Connected |  | N
National Grid | CHARLTON | 178421 | 01507 | 3375 | Solar | 05_01_525L2 | 01/17/2018 | 02/01/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/26/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2018 | 01/17/2018 | 4/16/2022 | Y | STD | 439 | 03/14/2021 | 12/02/2021 | 264 | 7 | 257 | 12/3/2021 | 12/16/2021 | 12/27/2021 | Connected |  | N
National Grid | WEST BROOKFIELD | 715579 | 01585 | 10 | Solar | 05_01_7J387 | 08/29/2025 | 10/08/2025 | 14 | 11 | 3 | 11/06/2025 | 11/06/2025 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 704932 | 01603 | 17.48 | Solar | 05_05_19W74 | 07/15/2025 | 09/08/2025 | 37 | 32 | 5 | 09/09/2025 | 09/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DIGHTON | 662931 | 02764 | 3.8 | Solar | 05_12_37W8 | 12/30/2024 | 01/16/2025 | 5 | 0 | 5 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MALDEN | 640655 | 02148 | 7.475 | Solar | 05_14_21L1 | 09/17/2024 | 10/03/2024 | 1 | 0 | 1 | 10/04/2024 | 10/04/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/17/2024 | 11/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | TYNGSBORO | 464540 | 01879 | 23.32 | Solar | 05_14_54L3 | 09/29/2022 | 10/04/2022 | 3 | 0 | 3 | 10/05/2022 | 10/05/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2023 | Connected |  | N
National Grid | ANDOVER | 458326 | 01810 | 7.83 | Solar | 05_14_63L2 | 10/27/2022 | 11/21/2022 | 16 | 14 | 2 | 11/22/2022 | 11/22/2022 | 21 | 0 | 21 | 01/17/2023 | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 03/03/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 2/2/2023 |  | 11/30/2024 | N | EXP | 365 | 06/15/2023 | 01/26/2024 | 226 | 3 | 223 |  |  | 3/9/2024 | Connected |  | N
National Grid | METHUEN | 218549 | 01844 | 3 | Solar | 05_14_78L1 | 05/08/2019 | 05/17/2019 | 7 | 7 | 0 | 05/20/2019 | 05/20/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 | 05/08/2019 | 3/31/2020 | Y | EXP | 31 | 10/17/2019 | 10/25/2019 | 8 | 0 | 8 |  |  | 11/1/2019 | Connected |  | N
National Grid | DRACUT | 177520 | 01826 | 1132.2 | Solar | 05_01_226L1 | 09/27/2016 | 09/27/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/27/2016 | 52 | 40 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 176688 | 01463 | 6 | Solar | 05_01_406L1 | 02/18/2016 | 02/18/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2016 |  | 2/24/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 12/1/2016 | 12/1/2016 | 12/1/2016 | Connected |  | N
National Grid | CHARLTON | 185007 | 01507 | 1000 | Solar | 05_01_525L2 | 05/17/2018 | 05/17/2018 | 32 | 15 | 17 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 07/05/2018 | 09/11/2018 | 36 | 5 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 721057 | 01506 | 1.45 | Solar | 05_01_7J387 | 09/23/2025 | 10/02/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 715587 | 01603 | 30 | Solar | 05_05_19W74 | 08/29/2025 | 09/09/2025 | 5 | 3 | 2 | 09/10/2025 | 09/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | DIGHTON | 701523 | 02764 | 6.631 | Solar | 05_12_37W8 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | MALDEN | 647295 | 02148 | 5.76 | Solar | 05_14_21L1 | 10/22/2024 | 11/14/2024 | 4 | 0 | 4 | 11/15/2024 | 11/15/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | DRACUT | 485876 | 01826 | 0 | Solar | 05_14_54L3 | 12/15/2022 | 12/19/2022 | 2 | 0 | 2 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 | 12/15/2022 | 4/26/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 1/17/2024 | Connected |  | N
National Grid | ANDOVER | 480100 | 01810 | 3.8 | Solar | 05_14_63L2 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 104 | 83 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 229113 | 01844 | 7.6 | Solar | 05_14_78L1 | 08/30/2019 | 09/04/2019 | 2 | 2 | 0 | 09/05/2019 | 09/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 |  | 9/1/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2020 | Connected |  | N
National Grid | DRACUT | 177839 | 01826 | 266.4 | Solar | 05_01_226L1 | 10/13/2017 | 10/13/2017 | 54 | 50 | 4 | 01/11/2018 | 01/11/2018 | 0 | 0 | 0 | 02/28/2018 | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 07/26/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 10/21/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 176885 | 01463 | 11.4 | Solar | 05_01_406L1 | 11/12/2015 | 11/12/2015 | 89 | 89 | 0 | 03/25/2016 | 03/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 11/12/2015 | 11/18/2016 | Y | EXP | 22 | 11/09/2016 | 11/16/2016 | 4 | 0 | 4 | 2/7/2017 | 2/7/2017 | 2/7/2017 | Connected |  | N
National Grid | CHARLTON | 186901 | 01507 | 4980 | Solar | 05_01_525L2 | 06/01/2018 | 06/01/2018 | 0 | 0 | 0 |  |  | 54 | 43 | 11 |  |  | 0 | 0 | 0 | 08/17/2018 | 08/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 189805 | 01515 | 10 | Solar | 05_01_7J387 | 07/02/2018 | 07/02/2018 | 4 | 4 | 0 | 10/25/2018 | 10/25/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 | 07/02/2018 | 12/5/2019 | Y | EXP | 398 | 07/17/2019 | 09/04/2019 | 49 | 0 | 49 |  |  | 10/29/2019 | Connected |  | N
National Grid | WORCESTER | 711394 | 01603 | 13.8 | Solar | 05_05_1J1 | 08/12/2025 | 09/11/2025 | 2 | 0 | 2 | 09/19/2025 | 09/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 | 08/12/2025 | 11/24/2026 | Y | EXP | 365 | 01/13/2026 | 02/05/2026 | 24 | 0 | 24 |  |  |  | Completion Documents |  | N
National Grid | DIGHTON | 178254 | 02764 | 33.3 | Solar | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 28 | 0 | 28 | 05/08/2018 | 05/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N
National Grid | MALDEN | 654926 | 02148 | 3.8 | Solar | 05_14_21L1 | 11/20/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | TYNGSBORO | 492260 | 01879 | 14.79 | Solar | 05_14_54L3 | 01/18/2023 | 01/19/2023 | 1 | 0 | 1 |  |  | 222 | 204 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 524456 | 01810 | 3.8 | Solar | 05_14_63L2 | 05/15/2023 | 05/16/2023 | 1 | 0 | 1 | 05/17/2023 | 05/17/2023 | 40 | 17 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 242622 | 01844 | 5 | Solar | 05_14_78L1 | 07/18/2019 | 08/14/2019 | 19 | 19 | 0 | 08/15/2019 | 08/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 7/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2020 | Connected |  | N
National Grid | DRACUT | 177871 | 01826 | 160 | Solar | 05_01_226L1 | 08/11/2017 | 08/11/2017 | 3 | 3 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/16/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 | 1/4/2018 | 1/4/2018 | 1/4/2018 | Connected |  | N
National Grid | PEPPERELL | 177091 | 01463 | 7.6 | Solar | 05_01_406L1 | 01/18/2017 | 01/18/2017 | 4 | 3 | 1 | 01/25/2017 | 01/25/2017 | 139 | 0 | 139 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2017 |  | 1/24/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 190339 | 01507 | 250 | Solar | 05_01_525L2 | 07/10/2018 | 08/20/2018 | 28 | 0 | 28 | 08/21/2018 | 08/21/2018 | 91 | 21 | 70 | 11/20/2018 | 01/03/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  | 01/03/2019 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 189778 | 01083 | 10 | Solar | 05_01_7J387 | 11/13/2018 | 07/02/2018 | 11 | 7 | 4 | 12/04/2018 | 12/04/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2018 |  | 11/13/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 721844 | 01603 | 10 | Solar | 05_05_1J1 | 09/25/2025 | 10/13/2025 | 3 | 0 | 3 | 11/21/2025 | 11/21/2025 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 09/25/2025 | 1/9/2027 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 178283 | 02703 | 133.2 | Solar | 05_12_37W9 | 03/12/2018 | 03/12/2018 | 8 | 0 | 8 | 05/09/2018 | 05/09/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/2/2019 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 1/25/2019 | Connected |  | N
National Grid | EVERETT | 657560 | 02149 | 5.76 | Solar | 05_14_21L1 | 11/28/2024 | 12/13/2024 | 3 | 0 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/28/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | DRACUT | 495148 | 01826 | 15.2 | Solar | 05_14_54L3 | 05/11/2023 | 05/15/2023 | 2 | 0 | 2 | 05/16/2023 | 05/16/2023 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 527876 | 01810 | 3.8 | Solar | 05_14_63L2 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 250354 | 01844 | 7.6 | Solar | 05_14_78L1 | 08/26/2019 | 09/03/2019 | 4 | 4 | 0 | 09/04/2019 | 09/04/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2019 | 08/26/2019 | 8/26/2020 | Y | EXP | 365 | 03/13/2020 | 06/02/2020 | 81 | 0 | 81 |  |  | 7/24/2020 | Connected |  | N
National Grid | DRACUT | 178659 | 01826 | 415 | Solar | 05_01_226L1 | 02/05/2018 | 02/05/2018 | 9 | 0 | 9 | 03/20/2018 | 03/20/2018 | 25 | 0 | 25 | 07/11/2018 | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 08/06/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 8/13/2018 |  | 10/21/2020 | N | EXP | 566 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | PEPPERELL | 177213 | 01463 | 1000 | Solar | 05_01_406L1 | 06/08/2016 | 06/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2016 | 07/26/2016 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/14/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 213652 | 01507 | 7.36 | Solar | 05_01_525L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 190326 | 01585 | 10 | Solar | 05_01_7J387 | 07/13/2018 | 08/24/2018 | 27 | 0 | 27 | 08/27/2018 | 08/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 07/13/2018 |  | Y | EXP | 421 | 10/17/2019 | 10/16/2019 | 0 | 0 | 0 |  |  | 11/6/2019 | Connected |  | N
National Grid | WORCESTER | 470212 | 01603 | 6 | Solar | 05_05_1J1 | 01/24/2023 | 01/26/2023 | 2 | 0 | 2 | 01/27/2023 | 01/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2023 | 01/24/2023 | 6/7/2024 | Y | EXP | 365 | 05/16/2023 | 06/08/2023 | 24 | 0 | 24 |  |  | 7/10/2023 | Connected |  | N
National Grid | ATTLEBORO | 178308 | 02703 | 3807.99 | Natural Gas | 05_12_37W9 | 01/10/2018 | 03/30/2018 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2018 | 04/26/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 |  | 6/7/2019 | N | STD | 149 |  |  | 0 | 0 | 0 | 5/31/2019 | 5/30/2019 | 6/7/2019 | Connected |  | N
National Grid | EVERETT | 668768 | 02149 | 10 | Solar | 05_14_21L1 | 02/04/2025 | 02/26/2025 | 2 | 0 | 2 | 02/27/2025 | 02/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/04/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | DRACUT | 502282 | 01826 | 15.2 | Solar | 05_14_54L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2024 | Connected |  | N
National Grid | ANDOVER | 568866 | 01810 | 10 | Solar | 05_14_63L2 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 36 | 12 | 24 | 04/01/2024 | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 04/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 4/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 253040 | 01844 | 17.6 | Solar | 05_14_78L1 | 09/09/2019 | 09/11/2019 | 1 | 0 | 1 | 09/12/2019 | 09/12/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | DRACUT | 185818 | 01826 | 999 | Solar | 05_01_226L1 | 06/27/2018 | 06/27/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2018 | 07/19/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177278 | 01463 | 1980 | Solar | 05_01_406L1 | 02/08/2017 | 03/27/2017 | 30 | 28 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2017 | 05/04/2017 | 28 | 14 | 14 |  |  | 0 | 0 | 0 | 01/13/2018 | 02/14/2020 | 523 | 0 | 523 | 10/20/2017 | 02/08/2017 | 1/31/2020 | Y | STD | 741 | 05/03/2019 | 01/22/2020 | 263 | 0 | 263 |  |  | 1/22/2020 | Connected |  | N
National Grid | CHARLTON | 272131 | 01507 | 0 | Other | 05_01_525L2 | 02/24/2020 | 04/10/2020 | 33 | 27 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2020 | 05/11/2020 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 196395 | 01083 | 100 | Solar | 05_01_7J387 | 09/19/2018 | 10/01/2018 | 3 | 0 | 3 | 10/02/2018 | 10/02/2018 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 493074 | 01603 | 6 | Solar | 05_05_1J1 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 02/15/2023 | 7/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2024 | Connected |  | N
National Grid | ATTLEBORO | 253372 | 02703 | 7.6 | Solar | 05_12_37W9 | 09/14/2019 | 09/17/2019 | 1 | 1 | 0 | 09/18/2019 | 09/18/2019 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 670942 | 02149 | 11.52 | Solar | 05_14_21L1 | 02/07/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/07/2025 | 4/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | DRACUT | 518526 | 01826 | 8.99 | Solar | 05_14_54L3 | 04/11/2023 | 04/12/2023 | 2 | 1 | 1 | 04/13/2023 | 04/13/2023 | 34 | 12 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2023 | Connected |  | N
National Grid | ANDOVER | 599558 | 01845 | 10.075 | Solar | 05_14_63L2 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | METHUEN | 301330 | 01844 | 7.6 | Solar | 05_14_78L1 | 08/07/2020 | 08/10/2020 | 0 | 0 | 0 | 08/11/2020 | 08/11/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/07/2020 | 8/9/2021 | Y | EXP | 365 | 10/28/2020 | 11/10/2020 | 13 | 0 | 13 |  |  | 1/25/2021 | Connected |  | N
National Grid | DRACUT | 186572 | 01826 | 1590 | Solar | 05_01_226L1 | 04/15/2019 | 06/05/2019 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2019 | 07/02/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177409 | 01463 | 1980 | Solar | 05_01_406L1 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/11/2016 | 12/31/2020 | Y | STD | 365 | 09/29/2020 | 12/02/2020 | 64 | 0 | 64 |  |  | 12/21/2020 | Connected |  | N
National Grid | CHARLTON | 281385 | 01507 | 0 | Other | 05_01_525L2 | 08/31/2020 | 09/24/2020 | 17 | 13 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 198809 | 01535 | 7.6 | Solar | 05_01_7J387 | 10/17/2018 | 11/08/2018 | 5 | 0 | 5 | 11/09/2018 | 11/09/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 647523 | 01603 | 7.6 | Solar | 05_05_1J1 | 10/22/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 10/22/2024 | 2/19/2026 | Y | EXP | 365 | 02/28/2025 | 07/16/2025 | 139 | 0 | 139 |  |  | 7/31/2025 | Connected |  | N
National Grid | ATTLEBORO | 384620 | 02703 | 1266 | Solar | 05_12_37W9 | 08/10/2022 |  | 231 | 63 | 168 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EVERETT | 685406 | 02149 | 5.76 | Solar | 05_14_21L1 | 04/17/2025 | 04/23/2025 | 3 | 0 | 3 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | DRACUT | 543279 | 01826 | 14.79 | Solar | 05_14_54L3 | 07/24/2023 | 07/26/2023 | 2 | 0 | 2 | 07/27/2023 | 07/27/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 | 07/24/2023 | 11/29/2024 | Y | EXP | 365 | 12/04/2023 | 01/16/2024 | 44 | 3 | 41 |  |  | 1/19/2024 | Connected |  | N
National Grid | ANDOVER | 619212 | 01810 | 14.95 | Solar | 05_14_63L2 | 06/22/2024 | 07/23/2024 | 9 | 7 | 2 | 07/24/2024 | 07/24/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 06/22/2024 | 9/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | METHUEN | 339584 | 01844 | 7.6 | Solar | 05_14_78L1 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2021 | Connected |  | N
National Grid | DRACUT | 188134 | 01826 | 1000 | Solar | 05_01_226L1 | 06/18/2018 | 06/18/2018 | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2018 | 07/24/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2019 |  | 9/3/2020 | N | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177477 | 01463 | 20 | Solar | 05_01_406L1 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2016 | 07/06/2016 | 8/31/2017 | Y | EXP | 398 | 06/03/2017 | 08/25/2017 | 58 | 0 | 58 | 8/23/2017 | 8/23/2017 | 8/22/2017 | Connected |  | N
National Grid | CHARLTON | 283873 | 01507 | 0 | Other | 05_01_525L2 | 09/02/2020 | 09/21/2020 | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 224318 | 01506 | 7.6 | Solar | 05_01_7J387 | 05/09/2019 | 05/15/2019 | 4 | 4 | 0 | 05/16/2019 | 05/16/2019 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 05/09/2019 | 2/28/2020 | Y | EXP | 268 | 08/31/2019 | 09/13/2019 | 13 | 0 | 13 |  |  | 11/7/2019 | Connected |  | N
National Grid | WORCESTER | 654221 | 01603 | 9.5 | Solar | 05_05_1J1 | 11/14/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 592425 | 02703 | 6 | Solar | 05_12_37W9 | 03/04/2024 | 03/05/2024 | 1 | 0 | 1 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 03/04/2024 | 3/12/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 699289 | 02149 | 15.2 | Solar | 05_14_21L1 | 06/17/2025 | 06/27/2025 | 6 | 4 | 2 | 06/30/2025 | 06/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | DRACUT | 569398 | 01826 | 7.6 | Solar | 05_14_54L3 | 11/07/2023 | 02/13/2024 | 65 | 63 | 2 | 02/14/2024 | 02/14/2024 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | ANDOVER | 641365 | 01810 | 7.6 | Solar | 05_14_63L2 | 09/18/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | METHUEN | 356821 | 01844 | 7.6 | Solar | 05_14_78L1 | 06/03/2021 | 01/07/2022 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 | 06/03/2021 | 3/8/2023 | Y | EXP | 365 | 01/26/2022 | 03/07/2022 | 41 | 0 | 41 |  |  | 8/11/2022 | Connected |  | Y
National Grid | DRACUT | 213711 | 01826 | 8.64 | Solar | 05_01_226L1 | 03/19/2019 | 03/29/2019 | 8 | 8 | 0 | 04/01/2019 | 04/01/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 |  | 5/30/2019 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | PEPPERELL | 177508 | 01463 | 99.9 | Solar | 05_01_406L1 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2017 |  | 8/31/2017 | N | EXP | 16 |  |  | 0 | 0 | 0 | 8/3/2017 | 8/3/2017 | 8/3/2017 | Connected |  | N
National Grid | OXFORD | 289281 | 01537 | 4950 | Other | 05_01_525L2 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2020 | 06/23/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 256144 | 01585 | 10 | Solar | 05_01_7J387 | 11/07/2019 | 11/07/2019 | 0 | 0 | 0 | 11/08/2019 | 11/08/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2019 | 11/07/2019 | 7/8/2020 | Y | EXP | 365 | 02/14/2020 | 03/03/2020 | 18 | 0 | 18 |  |  | 5/5/2020 | Connected |  | N
National Grid | WORCESTER | 699205 | 01603 | 5.7 | Solar | 05_05_1J1 | 06/30/2025 | 07/11/2025 | 7 | 4 | 3 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ATTLEBORO | 638410 | 02703 | 10 | Solar | 05_12_37W9 | 09/06/2024 | 09/25/2024 | 3 | 0 | 3 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | EVERETT | 720590 | 02149 | 10 | Solar | 05_14_21L2 | 09/19/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 09/19/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | DRACUT | 576984 | 01826 | 0 | Solar | 05_14_54L3 | 12/11/2023 | 12/13/2023 | 2 | 0 | 2 | 12/14/2023 | 12/14/2023 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 646960 | 01810 | 10 | Solar | 05_14_63L2 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | METHUEN | 359517 | 01844 | 15.12 | Solar | 05_14_78L1 | 05/20/2021 | 07/22/2021 | 42 | 35 | 7 | 07/23/2021 | 07/23/2021 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 272824 | 01826 | 3.8 | Solar | 05_01_226L1 | 02/21/2020 | 04/30/2020 | 50 | 49 | 1 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 4/29/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 177726 | 01463 | 7.6 | Solar | 05_01_406L1 | 10/04/2017 | 10/04/2017 | 9 | 8 | 1 | 10/19/2017 | 10/19/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 330996 | 01507 | 9.8 | Solar | 05_01_525L2 | 12/30/2020 | 01/04/2021 | 1 | 0 | 1 | 01/05/2021 | 01/05/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 273828 | 01515 | 7.6 | Solar | 05_01_7J387 | 01/23/2020 | 02/18/2020 | 16 | 14 | 2 | 02/19/2020 | 02/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2020 | 01/23/2020 | 8/12/2021 | Y | EXP | 365 | 02/03/2021 | 03/15/2021 | 40 | 0 | 40 |  |  | 4/7/2021 | Connected |  | N
National Grid | WORCESTER | 357772 | 01603 | 133.2 | Solar | 05_05_1J3 | 07/14/2021 | 08/10/2021 | 19 | 10 | 9 |  |  | 67 | 7 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 07/14/2021 | 3/23/2024 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 639926 | 02703 | 7.6 | Solar | 05_12_37W9 | 09/12/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2025 | Connected |  | N
National Grid | EVERETT | 722100 | 02149 | 3.8 | Solar | 05_14_21L2 | 10/14/2025 | 11/14/2025 | 2 | 0 | 2 | 12/24/2025 | 12/24/2025 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 604615 | 01854 | 17.6 | Solar | 05_14_54L3 | 06/07/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2026 | Connected |  | N
National Grid | ANDOVER | 657546 | 01810 | 5.76 | Solar | 05_14_63L2 | 11/28/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | METHUEN | 377505 | 01844 | 4.93 | Solar | 05_14_78L1 | 09/13/2021 | 01/07/2022 | 2 | 0 | 2 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 | 09/13/2021 |  | Y | EXP | 365 | 02/22/2022 | 03/10/2022 | 16 | 0 | 16 |  |  | 3/29/2022 | Connected |  | N
National Grid | DRACUT | 287295 | 01826 | 200 | Solar | 05_01_226L1 | 04/17/2020 | 05/29/2020 | 27 | 21 | 6 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 |  | 9/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | PEPPERELL | 177741 | 01463 | 1740 | Solar | 05_01_406L1 | 05/30/2017 | 11/01/2017 | 105 | 100 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2017 | 12/06/2017 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 343332 | 01507 | 9.8 | Solar | 05_01_525L2 | 03/05/2021 | 03/16/2021 | 6 | 4 | 2 | 03/17/2021 | 03/17/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 03/05/2021 | 6/20/2022 | Y | EXP | 365 | 08/10/2021 | 09/03/2021 | 23 | 3 | 20 |  |  | 11/5/2021 | Connected |  | N
National Grid | WEST BROOKFIELD | 427946 | 01585 | 11.4 | Solar | 05_01_7J387 | 05/03/2022 | 05/03/2022 | 0 | 0 | 0 | 05/04/2022 | 05/04/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N
National Grid | WORCESTER | 646703 | 01603 | 7.6 | Solar | 05_05_1J3 | 10/25/2024 | 11/12/2024 | 2 | 0 | 2 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 |  | 12/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 650947 | 02703 | 5.76 | Solar | 05_12_37W9 | 11/04/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | EVERETT | 177701 | 02149 | 7.6 | Solar | 05_14_21L2 | 03/21/2017 | 03/21/2017 | 6 | 6 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2017 |  | 3/27/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 10/3/2017 | 10/3/2017 | 10/3/2017 | Connected |  | N
National Grid | LOWELL | 606384 | 01850 |  | Battery Add-On | 05_14_54L3 | 04/24/2024 | 04/29/2024 | 3 | 0 | 3 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 10/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | ANDOVER | 668345 | 01810 | 3.8 | Solar | 05_14_63L2 | 01/28/2025 | 03/17/2025 | 9 | 3 | 6 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/28/2025 | 4/25/2026 | Y | EXP | 365 | 07/24/2025 | 02/02/2026 | 194 | 0 | 194 |  |  | 11/24/2025 | Connected |  | N
National Grid | METHUEN | 402327 | 01844 | 15.2 | Solar | 05_14_78L1 | 12/20/2021 | 12/23/2021 | 3 | 2 | 1 | 12/24/2021 | 12/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 |  | 2/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 314437 | 01826 | 3.8 | Solar | 05_01_226L1 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2021 | Connected |  | N
National Grid | PEPPERELL | 177847 | 01463 | 900 | Solar | 05_01_406L1 | 10/17/2017 | 11/15/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 | 12/11/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/17/2017 | 10/1/2019 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 353809 | 01524 | 15.2 | Solar | 05_01_525L2 | 08/18/2021 | 09/20/2021 | 23 | 22 | 1 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 | 08/18/2021 | 7/15/2023 | Y | EXP | 39 | 02/09/2022 | 03/23/2022 | 43 | 0 | 43 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 496344 | 01506 | 9.86 | Solar | 05_01_7J387 | 02/08/2023 | 02/09/2023 | 1 | 0 | 1 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 | 02/08/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | WORCESTER | 699742 | 01603 | 13.36 | Solar | 05_05_1J4 | 06/27/2025 | 07/01/2025 | 2 | 0 | 2 | 07/02/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/27/2025 | 1/6/2027 | Y | EXP | 365 | 02/11/2026 | 02/19/2026 | 9 | 0 | 9 |  |  |  | Completion Documents |  | Y
National Grid | ATTLEBORO | 368844 | 02703 | 100.8 | Solar | 05_12_3J1 | 08/24/2021 | 09/15/2021 | 15 | 6 | 9 |  |  | 42 | 12 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EVERETT | 424750 | 02149 | 7.6 | Solar | 05_14_21L2 | 07/21/2022 | 08/09/2022 | 13 | 10 | 3 | 08/10/2022 | 08/10/2022 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2023 | Connected |  | N
National Grid | DRACUT | 619582 | 01826 | 0 | Battery Add-On | 05_14_54L3 | 06/21/2024 | 06/25/2024 | 2 | 0 | 2 | 06/26/2024 | 06/26/2024 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | ANDOVER | 682966 | 01810 | 0 | Solar | 05_14_63L2 | 04/07/2025 | 04/25/2025 | 13 | 9 | 4 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 425044 | 01844 | 10 | Solar | 05_14_78L1 | 05/09/2022 | 05/09/2022 | 0 | 0 | 0 | 05/10/2022 | 05/10/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 05/09/2022 | 7/20/2023 | Y | EXP | 365 | 07/16/2022 | 07/18/2022 | 3 | 0 | 3 |  |  | 5/1/2023 | Connected |  | Y
National Grid | DRACUT | 355070 | 01826 | 20 | Solar | 05_01_226L1 | 04/28/2021 | 12/15/2021 | 0 | 0 | 0 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 | 04/28/2021 | 12/2/2022 | Y | EXP | 365 | 11/16/2021 | 11/23/2021 | 8 | 0 | 8 |  |  | 12/21/2021 | Connected |  | N
National Grid | PEPPERELL | 178172 | 01463 | 7800 | Solar | 05_01_406L1 | 03/23/2018 | 03/23/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2018 | 06/26/2018 | 59 | 43 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 449501 | 01542 | 3.8 | Solar | 05_01_525L2 | 05/22/2023 | 09/01/2022 | 2 | 0 | 2 | 05/25/2023 | 05/25/2023 | 53 | 34 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2023 | Connected |  | N
National Grid | WEST BROOKFIELD | 567253 | 01585 | 6 | Solar | 05_01_7J387 | 11/15/2023 | 11/17/2023 | 2 | 0 | 2 | 11/20/2023 | 11/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2024 | Connected |  | N
National Grid | WORCESTER | 744449 | 01603 |  | Battery Add-On | 05_05_1J4 | 01/09/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 368795 | 02703 | 151.2 | Solar | 05_12_3J1 | 07/12/2021 | 08/03/2021 | 16 | 9 | 7 |  |  | 72 | 46 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 | 07/12/2021 | 5/22/2024 | Y | STD | 25 | 01/30/2024 | 01/29/2024 | 0 | 0 | 0 |  |  | 5/16/2024 | Connected |  | N
National Grid | SALEM | 441257 | 01970 | 3.48 | Solar | 05_14_21L2 | 07/15/2022 | 07/19/2022 | 2 | 0 | 2 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2022 | 07/15/2022 | 3/1/2024 | Y | EXP | 365 | 02/17/2023 | 02/28/2023 | 12 | 0 | 12 |  |  | 9/6/2023 | Connected |  | Y
National Grid | LOWELL | 624612 | 01850 | 22.8 | Solar | 05_14_54L3 | 07/15/2024 | 07/17/2024 | 2 | 0 | 2 | 07/18/2024 | 07/18/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 699916 | 01810 | 16.72 | Solar | 05_14_63L2 | 06/23/2025 | 06/27/2025 | 4 | 0 | 4 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 | 06/23/2025 | 8/8/2026 | Y | EXP | 365 | 11/14/2025 | 11/26/2025 | 13 | 0 | 13 |  |  | 12/11/2025 | Connected |  | N
National Grid | METHUEN | 428394 | 01844 | 5.8 | Solar | 05_14_78L1 | 05/09/2022 | 05/11/2022 | 2 | 0 | 2 | 05/12/2022 | 05/12/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2022 |  | 7/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2022 | Connected |  | N
National Grid | DRACUT | 388303 | 01826 | 7.6 | Solar | 05_01_226L1 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 178255 | 01463 | 1375 | Solar | 05_01_406L1 | 04/16/2018 | 04/16/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/09/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/21/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 389963 | 01501 | 6 | Solar | 05_01_525L2 | 11/03/2021 | 01/06/2022 | 5 | 1 | 4 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 586363 | 01585 | 5.76 | Solar | 05_01_7J387 | 02/14/2024 | 02/21/2024 | 4 | 2 | 2 | 02/22/2024 | 02/22/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 02/14/2024 | 4/17/2025 | Y | EXP | 365 | 07/10/2024 | 11/07/2024 | 121 | 0 | 121 |  |  | 10/28/2024 | Connected |  | N
National Grid | WORCESTER | 188562 | 01603 | 15.2 | Solar | 05_05_1J4 | 06/19/2018 | 06/19/2018 | 2 | 0 | 2 | 06/29/2018 | 06/29/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/28/2019 | Connected |  | N
National Grid | ATTLEBORO | 749324 | 02703 | 23 | Solar | 05_12_3J2 | 02/04/2026 | 02/11/2026 | 4 | 0 | 4 | 02/12/2026 | 02/12/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 493449 | 01970 | 6 | Solar | 05_14_21L2 | 02/03/2023 | 02/07/2023 | 2 | 0 | 2 | 02/08/2023 | 02/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 645228 | 01826 | 0 | Battery Add-On | 05_14_54L3 | 10/05/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 83 | 65 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | ANDOVER | 208615 | 01810 | 500 | Solar | 05_14_65L1 | 03/25/2019 | 04/23/2019 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2019 | 03/17/2020 | 213 | 42 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 430404 | 01844 | 6 | Solar | 05_14_78L1 | 05/24/2022 | 06/02/2022 | 7 | 5 | 2 | 06/03/2022 | 06/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2022 | 05/24/2022 | 10/13/2023 | Y | EXP | 365 | 09/28/2022 | 10/12/2022 | 15 | 0 | 15 |  |  | 10/24/2022 | Connected |  | N
National Grid | DRACUT | 471136 | 01826 | 15.2 | Solar | 05_01_226L1 | 11/23/2022 | 11/29/2022 | 3 | 0 | 3 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 1/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2023 | Connected |  | N
National Grid | PEPPERELL | 178479 | 01463 | 5000 | Solar | 05_01_406L1 | 04/03/2018 | 04/03/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 414330 | 01501 | 7.6 | Solar | 05_01_525L2 | 02/25/2022 | 02/28/2022 | 1 | 0 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 6/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2022 | Connected |  | N
National Grid | WEST BROOKFIELD | 622055 | 01585 | 3.8 | Solar | 05_01_7J387 | 07/02/2024 | 07/09/2024 | 1 | 0 | 1 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 07/02/2024 | 7/31/2025 | Y | EXP | 365 | 10/04/2024 | 10/17/2024 | 14 | 0 | 14 |  |  | 11/16/2024 | Connected |  | N
National Grid | WORCESTER | 476497 | 01603 | 240 | Solar | 05_05_2468W1 | 12/07/2022 | 01/06/2023 | 20 | 11 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 | 12/07/2022 | 6/7/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | ATTLEBORO | 647145 | 02703 | 10 | Solar | 05_12_3J2 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | SALEM | 574472 | 01970 | 10 | Solar | 05_14_21L2 | 12/08/2023 | 12/12/2023 | 2 | 0 | 2 | 12/13/2023 | 12/13/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | LOWELL | 657336 | 01850 | 10 | Solar | 05_14_54L3 | 11/27/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/27/2024 | 2/21/2026 | Y | EXP | 365 | 04/24/2025 | 04/23/2025 | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ANDOVER | 653568 | 01810 | 3.8 | Solar | 05_14_65L1 | 11/12/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 499858 | 01830 | 10 | Solar | 05_14_78L1 | 02/16/2023 | 02/23/2023 | 4 | 3 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 3/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | DRACUT | 477267 | 01826 | 17.45 | Solar | 05_01_226L1 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2023 | Connected |  | N
National Grid | PEPPERELL | 178565 | 01463 | 4998 | Solar | 05_01_406L1 | 04/05/2018 | 04/16/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 07/09/2018 | 59 | 35 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 414012 | 01540 | 15.2 | Solar | 05_01_525L2 | 02/24/2022 | 03/01/2022 | 4 | 3 | 1 | 03/02/2022 | 03/02/2022 | 60 | 40 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 628232 | 01585 | 5.76 | Solar | 05_01_7J387 | 07/29/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | WORCESTER | 475897 | 01603 | 240 | Solar | 05_05_2468W1 | 11/18/2022 | 01/17/2023 | 38 | 28 | 10 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 11/18/2022 | 6/12/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 698376 | 02035 | 9.88 | Solar | 05_12_3J2 | 06/13/2025 | 06/27/2025 | 4 | 2 | 2 | 07/09/2025 | 07/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/13/2025 | 8/25/2026 | Y | EXP | 365 | 10/25/2025 | 11/05/2025 | 12 | 0 | 12 |  |  | 11/14/2025 | Connected |  | N
National Grid | SALEM | 644522 | 01970 | 5.76 | Solar | 05_14_21L2 | 10/02/2024 | 10/29/2024 | 10 | 7 | 3 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | DRACUT | 657602 | 01826 | 10 | Solar | 05_14_54L3 | 11/29/2024 | 12/26/2024 | 4 | 0 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/29/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | ANDOVER | 659339 | 01810 | 7.6 | Solar | 05_14_65L1 | 12/10/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 521189 | 01830 | 7.6 | Solar | 05_14_78L1 | 05/02/2023 | 05/03/2023 | 1 | 0 | 1 | 05/04/2023 | 05/04/2023 | 51 | 28 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 7/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | DRACUT | 491024 | 01826 | 10 | Solar | 05_01_226L1 | 03/14/2023 | 03/20/2023 | 4 | 0 | 4 | 03/21/2023 | 03/21/2023 | 55 | 39 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 191612 | 01463 | 272 | Solar | 05_01_406L1 | 11/27/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 108 | 56 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 424701 | 01537 | 3.8 | Solar | 05_01_525L2 | 04/22/2022 | 04/29/2022 | 5 | 3 | 2 | 05/02/2022 | 05/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 646407 | 01506 | 3.8 | Solar | 05_01_7J387 | 10/16/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 51 | 25 | 26 | 02/07/2025 | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 03/14/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 4/10/2025 | 10/16/2024 | 4/11/2026 | Y | EXP | 365 | 05/09/2025 | 09/02/2025 | 117 | 0 | 117 |  |  | 9/4/2025 | Connected |  | N
National Grid | WORCESTER | 509726 | 01603 | 240 | Solar | 05_05_2468W1 | 03/15/2023 | 04/07/2023 | 17 | 7 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 | 03/15/2023 | 9/4/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FOXBOROUGH | 700251 | 02035 | 11.4 | Solar | 05_12_3J2 | 06/23/2025 | 07/23/2025 | 7 | 3 | 4 | 07/24/2025 | 07/24/2025 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 645288 | 01970 | 7.6 | Solar | 05_14_21L2 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | LOWELL | 666604 | 01854 | 0 | Battery Add-On | 05_14_54L3 | 01/17/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | ANDOVER | 657492 | 01810 | 5.76 | Solar | 05_14_65L3 | 11/27/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | HAVERHILL | 559780 | 01830 | 8.505 | Solar | 05_14_78L1 | 11/13/2023 | 11/28/2023 | 10 | 6 | 4 | 11/29/2023 | 11/29/2023 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 11/13/2023 | 2/1/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2024 | Connected |  | N
National Grid | DRACUT | 493769 | 01826 | 24.94 | Solar | 05_01_226L1 | 01/20/2023 | 01/23/2023 | 2 | 1 | 1 | 01/24/2023 | 01/24/2023 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | PEPPERELL | 198041 | 01463 | 15.2 | Solar | 05_01_406L1 | 10/09/2018 | 10/12/2018 | 2 | 0 | 2 | 10/15/2018 | 10/15/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2018 |  | 11/1/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2019 | Connected |  | N
National Grid | CHARLTON | 457878 | 01507 | 3.77 | Solar | 05_01_525L2 | 10/13/2022 | 10/18/2022 | 4 | 1 | 3 | 10/19/2022 | 10/19/2022 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/13/2022 | 8/6/2024 | Y | EXP | 365 | 07/19/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 8/24/2023 | Connected |  | N
National Grid | BROOKFIELD | 655540 | 01506 | 3.8 | Solar | 05_01_7J387 | 11/19/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 10/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | N
National Grid | WORCESTER | 448988 | 01603 | 250 | Solar | 05_05_28W40 | 08/26/2022 | 10/28/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FOXBOROUGH | 672445 | 02035 | 10 | Solar | 05_12_3J6 | 02/17/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SALEM | 649324 | 01970 | 10 | Solar | 05_14_21L2 | 11/05/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | DRACUT | 674675 | 01826 | 10 | Solar | 05_14_54L3 | 03/03/2025 | 03/06/2025 | 3 | 0 | 3 | 03/07/2025 | 03/07/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | ANDOVER | 176146 | 01845 | 1700 | Solar | 05_14_65L3 | 08/24/2015 | 08/24/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/31/2015 | 09/29/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/27/2016 |  | 457 | 21 | 436 | 5/12/2016 |  | 8/12/2016 | N | STD | 92 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAVERHILL | 531489 | 01835 | 15.2 | Solar | 05_14_78L1 | 06/05/2023 | 06/06/2023 | 1 | 0 | 1 | 06/07/2023 | 06/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 532028 | 01826 | 10 | Solar | 05_01_226L1 | 07/07/2023 | 07/11/2023 | 2 | 0 | 2 | 07/12/2023 | 07/12/2023 | 22 | 0 | 22 | 10/02/2023 | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 11/01/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/30/2023 |  | 12/11/2024 | N | EXP | 365 | 12/22/2023 | 01/24/2024 | 34 | 0 | 34 |  |  | 2/1/2024 | Connected |  | Y
National Grid | PEPPERELL | 204158 | 01463 | 306.4 | Solar | 05_01_406L1 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 496520 | 01507 | 15.2 | Solar | 05_01_525L2 | 01/30/2023 | 02/17/2023 | 15 | 14 | 1 | 02/21/2023 | 02/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | WEST BROOKFIELD | 176338 | 01585 | 308 | Solar | 05_01_8J364 | 09/17/2015 | 09/17/2015 | 3 | 3 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2015 |  | 9/22/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 2/8/2016 | 2/8/2016 | 2/12/2016 | Connected |  | N
National Grid | WORCESTER | 696064 | 01603 | 180 | Solar | 05_05_28W40 | 07/21/2025 | 10/21/2025 | 64 | 55 | 9 | 10/22/2025 | 10/22/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 230775 | 02720 | 66.6 | Solar | 05_12_3J6 | 07/16/2020 | 07/31/2020 | 11 | 5 | 6 | 08/03/2020 | 08/03/2020 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2020 |  | 10/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 655399 | 01970 | 4.06 | Solar | 05_14_21L2 | 11/19/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 11/19/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2025 | Connected |  | N
National Grid | LOWELL | 694492 | 01850 | 10 | Solar | 05_14_54L3 | 06/02/2025 | 06/16/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 37 | 23 | 14 | 08/22/2025 | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/21/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 270545 | 01810 | 0 | Solar | 05_14_65L3 | 12/20/2019 | 12/30/2019 | 4 | 0 | 4 | 12/31/2019 | 12/31/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 | 12/20/2019 | 12/20/2020 | Y | EXP | 365 | 03/10/2020 | 04/02/2020 | 23 | 0 | 23 |  |  | 9/14/2020 | Connected |  | N
National Grid | HAVERHILL | 569358 | 01830 | 6.09 | Solar | 05_14_78L1 | 11/14/2023 | 11/20/2023 | 4 | 1 | 3 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 | 11/14/2023 | 1/1/2025 | Y | EXP | 365 | 05/30/2024 | 07/15/2024 | 47 | 0 | 47 |  |  | 7/26/2024 | Connected |  | N
National Grid | DRACUT | 577018 | 01826 | 6.67 | Solar | 05_01_226L1 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 245016 | 01463 | 10 | Solar | 05_01_406L1 | 07/23/2019 | 10/08/2019 | 4 | 3 | 1 | 10/09/2019 | 10/09/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 | 07/23/2019 | 7/7/2020 | Y | EXP | 365 | 02/19/2020 | 02/20/2020 | 1 | 0 | 1 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 514350 | 01537 | 13.92 | Solar | 05_01_525L2 | 04/04/2023 | 04/05/2023 | 1 | 0 | 1 | 04/06/2023 | 04/06/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 680111 | 01506 | 3.8 | Solar | 05_01_8J364 | 03/24/2025 | 04/04/2025 | 1 | 0 | 1 | 04/18/2025 | 04/18/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | WORCESTER | 712877 | 01607 | 3.8 | Solar | 05_05_28W40 | 08/18/2025 | 12/31/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 655816 | 02720 | 7.6 | Solar | 05_12_3J6 | 11/20/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SALEM | 667886 | 01970 | 21.4 | Solar | 05_14_21L2 | 01/26/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/26/2025 | 5/12/2026 | Y | EXP | 365 | 06/26/2025 | 12/22/2025 | 197 | 0 | 197 |  |  | 11/21/2025 | Connected |  | N
National Grid | DRACUT | 696418 | 01826 | 0 | Battery Add-On | 05_14_54L3 | 06/05/2025 | 06/20/2025 | 10 | 6 | 4 | 06/23/2025 | 06/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 330625 | 01810 | 15.2 | Solar | 05_14_65L3 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 613831 | 01835 | 7.6 | Solar | 05_14_78L1 | 05/28/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2024 | Connected |  | N
National Grid | DRACUT | 586042 | 01826 | 8.41 | Solar | 05_01_226L1 | 02/09/2024 | 02/13/2024 | 2 | 0 | 2 | 02/14/2024 | 02/14/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/09/2024 | 3/1/2025 | Y | EXP | 365 | 04/16/2024 | 06/05/2024 | 51 | 0 | 51 |  |  | 6/13/2024 | Connected |  | N
National Grid | PEPPERELL | 281119 | 01463 | 2400 | Natural Gas | 05_01_406L1 | 06/09/2020 | 07/14/2020 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2020 | 08/04/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 06/09/2020 | 9/19/2023 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 572189 | 01540 | 9.28 | Solar | 05_01_525L2 | 01/10/2024 | 03/11/2024 | 41 | 37 | 4 | 03/12/2024 | 03/12/2024 | 40 | 35 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 680491 | 01585 | 3.8 | Solar | 05_01_8J364 | 03/25/2025 | 04/07/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 739135 | 01607 | 20.96 | Solar | 05_05_28W40 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 665449 | 02720 | 5.76 | Solar | 05_12_3J901 | 01/15/2025 | 03/03/2025 | 2 | 0 | 2 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 | 01/15/2025 | 5/10/2026 | Y | EXP | 365 | 07/12/2025 | 10/15/2025 | 96 | 0 | 96 |  |  | 11/26/2025 | Connected |  | N
National Grid | SALEM | 676616 | 01970 | 11.4 | Solar | 05_14_21L2 | 03/27/2025 | 04/11/2025 | 11 | 8 | 3 | 04/14/2025 | 04/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 706271 | 01826 | 3.8 | Solar | 05_14_54L3 | 07/21/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 487600 | 01810 | 7.54 | Solar | 05_14_65L3 | 02/15/2023 | 02/16/2023 | 1 | 0 | 1 | 02/17/2023 | 02/17/2023 | 184 | 162 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 619601 | 01835 | 10 | Solar | 05_14_78L1 | 06/21/2024 | 07/18/2024 | 8 | 6 | 2 | 07/19/2024 | 07/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 | 06/21/2024 | 9/18/2025 | Y | EXP | 365 | 02/28/2025 | 04/21/2025 | 53 | 0 | 53 |  |  | 5/2/2025 | Connected |  | N
National Grid | DRACUT | 623421 | 01826 | 2100 | Solar | 05_01_226L1 | 07/11/2024 |  | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 292506 | 01463 | 0 | Other | 05_01_406L1 | 09/16/2020 | 09/29/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/30/2020 | 10/24/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEICESTER | 572056 | 01524 | 5.22 | Solar | 05_01_525L2 | 11/21/2023 | 11/28/2023 | 4 | 0 | 4 | 11/29/2023 | 11/29/2023 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2024 | 11/21/2023 | 2/17/2025 | Y | EXP | 365 | 06/05/2024 | 07/29/2024 | 55 | 0 | 55 |  |  | 8/29/2024 | Connected |  | N
National Grid | WEST BROOKFIELD | 681766 | 01585 | 3.8 | Solar | 05_01_8J364 | 04/01/2025 | 04/24/2025 | 2 | 0 | 2 | 05/09/2025 | 05/09/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | WORCESTER | 741831 | 01607 | 11.5 | Solar | 05_05_28W40 | 12/22/2025 | 12/26/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 32 | 20 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 670878 | 02720 | 7.6 | Solar | 05_12_3J901 | 02/07/2025 | 03/13/2025 | 13 | 9 | 4 | 03/14/2025 | 03/14/2025 | 117 | 100 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 692133 | 01902 | 10 | Solar | 05_14_21L3 | 05/30/2025 | 07/08/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 | 09/23/2025 | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 10/08/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | DRACUT | 708145 | 01826 | 17.6 | Solar | 05_14_54L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | ANDOVER | 586417 | 01810 | 0 | Battery Add-On | 05_14_65L3 | 01/30/2024 | 02/15/2024 | 12 | 9 | 3 | 02/16/2024 | 02/16/2024 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | HAVERHILL | 625470 | 01835 | 6 | Solar | 05_14_78L1 | 07/17/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 648781 | 01826 | 10 | Solar | 05_01_226L1 | 10/22/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/22/2024 | 12/3/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | PEPPERELL | 295119 | 01463 | 0 | Other | 05_01_406L1 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 574688 | 01507 | 0 | Battery Add-On | 05_01_525L2 | 11/30/2023 | 12/04/2023 | 2 | 0 | 2 | 12/05/2023 | 12/05/2023 | 196 | 25 | 171 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEST BROOKFIELD | 696783 | 01585 | 7.6 | Solar | 05_01_8J364 | 06/23/2025 | 09/18/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174536 | 01607 | 950 | Solar | 05_05_28W40 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 349185 | 02720 | 7.6 | Solar | 05_12_3J903 | 04/28/2021 | 05/03/2021 | 2 | 0 | 2 | 05/04/2021 | 05/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 723479 | 01902 | 20 | Solar | 05_14_21L3 | 10/01/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 712170 | 01854 | 15.2 | Solar | 05_14_54L3 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | ANDOVER | 655978 | 01810 | 3.8 | Solar | 05_14_65L3 | 11/21/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | HAVERHILL | 635771 | 01835 | 5.76 | Solar | 05_14_78L1 | 08/27/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 9/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  | 1/24/2025 | Connected |  | Y
National Grid | DRACUT | 653619 | 01826 | 8.125 | Solar | 05_01_226L1 | 11/12/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 1/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | PEPPERELL | 313292 | 01463 | 10 | Solar | 05_01_406L1 | 10/21/2020 | 10/22/2020 | 0 | 0 | 0 | 10/23/2020 | 10/23/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N
National Grid | OXFORD | 641967 | 01537 | 10 | Solar | 05_01_525L2 | 09/20/2024 | 10/23/2024 | 1 | 0 | 1 | 10/24/2024 | 10/24/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 730871 | 01585 | 15.2 | Solar | 05_01_8J365 | 11/03/2025 | 12/11/2025 | 1 | 1 | 0 | 12/12/2025 | 12/12/2025 | 56 | 24 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 174744 | 01610 | 2000 | Solar | 05_05_28W40 | 07/02/2013 | 07/02/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2013 | 08/09/2013 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2014 | 07/02/2013 | 6/30/2014 | Y | STD | 88 | 03/10/2015 | 04/02/2015 | 16 | 0 | 16 | 4/30/2015 | 4/30/2015 | 5/7/2015 | Connected |  | N
National Grid | FALL RIVER | 584871 | 02720 | 7.6 | Solar | 05_12_3J903 | 02/01/2024 | 02/16/2024 | 12 | 10 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | LYNN | 745622 | 01902 | 7.6 | Solar | 05_14_21L3 | 01/16/2026 | 01/21/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 713352 | 01854 | 10.88 | Solar | 05_14_54L3 | 09/10/2025 | 09/22/2025 | 7 | 3 | 4 | 09/23/2025 | 09/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | ANDOVER | 671344 | 01810 | 5.76 | Solar | 05_14_65L3 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | HAVERHILL | 643912 | 01835 | 7.6 | Solar | 05_14_78L1 | 10/02/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/02/2024 | 12/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | DRACUT | 684832 | 01826 | 17.6 | Solar | 05_01_226L1 | 04/14/2025 | 04/21/2025 | 4 | 1 | 3 | 04/22/2025 | 04/22/2025 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2025 | Connected |  | N
National Grid | PEPPERELL | 350779 | 01463 | 24 | Solar | 05_01_406L1 | 05/05/2021 | 01/07/2022 | 0 | 0 | 0 | 05/07/2021 | 05/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 | 05/05/2021 | 3/9/2023 | Y | EXP | 365 | 01/14/2022 | 01/14/2022 | 1 | 0 | 1 |  |  | 4/5/2022 | Connected |  | N
National Grid | CHARLTON | 645312 | 01507 | 3.8 | Solar | 05_01_525L2 | 10/07/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/07/2024 | 2/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 175033 | 01506 | 900 | Wind | 05_05_28W40 | 03/25/2013 | 03/25/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2013 | 06/14/2013 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/14/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 584595 | 01610 | 5 | Solar | 05_12_3J903 | 02/09/2024 | 02/12/2024 | 2 | 1 | 1 | 02/13/2024 | 02/13/2024 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2024 | 02/09/2024 | 4/23/2025 | Y | EXP | 365 | 08/21/2024 | 10/10/2024 | 51 | 0 | 51 |  |  | 10/4/2024 | Connected |  | N
National Grid | FALL RIVER | 174624 | 02720 | 40 | Solar | 05_14_21L3 | 05/02/2011 | 05/02/2011 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2011 | 05/02/2011 | 1/10/2012 | Y | EXP | 145 | 12/12/2011 | 12/12/2011 | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/10/2012 | Connected |  | N
National Grid | LYNN | 732162 | 01902 | 13.8 | Solar | 05_14_54L3 | 11/06/2025 | 11/07/2025 | 2 | 0 | 2 | 11/19/2025 | 11/19/2025 | 72 | 53 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 673956 | 01854 | 5.76 | Solar | 05_14_65L3 | 02/24/2025 | 03/04/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 02/24/2025 | 4/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | ANDOVER | 643820 | 01810 | 7.6 | Solar | 05_14_78L1 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/26/2025 | 42 | 0 | 42 |  |  |  | Withdrawn |  | Y
National Grid | HAVERHILL | 696444 | 01835 | 9.5 | Solar | 05_01_226L1 | 06/05/2025 | 06/25/2025 | 3 | 0 | 3 | 07/30/2025 | 07/30/2025 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | DRACUT | 419196 | 01826 | 9.28 | Solar | 05_01_406L1 | 04/28/2022 |  | 303 | 21 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 647627 | 01463 | 22.8 | Solar | 05_01_525L2 | 11/06/2024 | 11/12/2024 | 4 | 1 | 3 | 11/13/2024 | 11/13/2024 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 12/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | CHARLTON | 228014 | 01507 | 10 | Solar | 05_05_28W40 | 06/21/2019 | 07/03/2019 | 7 | 7 | 0 | 07/05/2019 | 07/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/21/2019 | 10/10/2019 | Y | EXP | 84 | 08/30/2019 | 09/13/2019 | 14 | 0 | 14 |  |  | 9/23/2019 | Connected |  | N
National Grid | WEST BROOKFIELD | 592529 | 01585 | 3.8 | Solar | 05_12_3J903 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 5/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2024 | Connected |  | N
National Grid | WORCESTER | 175458 | 01610 | 60 | Natural Gas | 05_14_21L3 | 07/17/2014 | 07/17/2014 | 3 | 0 | 3 | 07/24/2014 | 07/24/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2014 |  | 10/31/2014 | N | EXP | 7 |  |  | 0 | 0 | 0 | 11/4/2014 | 11/4/2014 | 11/10/2014 | Connected |  | N
National Grid | FALL RIVER | 725323 | 02720 | 15.2 | Solar | 05_14_55L1 | 10/09/2025 | 10/17/2025 | 5 | 0 | 5 | 10/20/2025 | 10/20/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 12/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | LYNN | 691483 | 01902 | 17.11 | Solar | 05_14_65L3 | 05/13/2025 | 05/16/2025 | 3 | 0 | 3 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 05/13/2025 | 6/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 644842 | 01854 | 5.76 | Solar | 05_14_78L1 | 10/03/2024 | 11/07/2024 | 6 | 0 | 6 | 11/08/2024 | 11/08/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 712303 | 01810 | 22.8 | Solar | 05_01_226L2 | 10/02/2025 | 10/10/2025 | 6 | 4 | 2 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 420713 | 01835 | 240 | Solar | 05_01_406L1 | 06/22/2022 | 10/07/2022 | 74 | 64 | 10 |  |  | 322 | 298 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 651760 | 01826 | 3.8 | Solar | 05_01_525L2 | 11/13/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | PEPPERELL | 206485 | 01463 | 210 | Solar | 05_01_8J365 | 03/19/2019 | 03/22/2019 | 2 | 0 | 2 |  |  | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 | 03/19/2019 | 6/22/2023 | Y | STD | 927 |  |  | 0 | 0 | 0 |  |  | 6/20/2023 | Connected |  | N
National Grid | OXFORD | 225621 | 01540 | 233.3 | Solar | 05_05_28W40 | 06/29/2020 | 07/06/2020 | 5 | 4 | 1 | 07/07/2020 | 07/07/2020 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2020 |  | 8/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | WEST BROOKFIELD | 599564 | 01585 | 3.8 | Solar | 05_12_3J903 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 | 04/04/2024 | 7/21/2025 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | WORCESTER | 176420 | 01610 | 6 | Solar | 05_14_21L3 | 12/07/2015 | 12/07/2015 | 2 | 2 | 0 | 12/10/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 12/13/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/2/2016 | Connected |  | N
National Grid | FALL RIVER | 740761 | 02720 | 15.2 | Solar | 05_14_55L1 | 12/17/2025 | 12/18/2025 | 1 | 0 | 1 | 12/19/2025 | 12/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 1/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 715617 | 01902 | 17.6 | Solar | 05_14_65L3 | 09/08/2025 | 09/10/2025 | 2 | 0 | 2 | 09/11/2025 | 09/11/2025 | 56 | 43 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 649061 | 01852 | 3.8 | Solar | 05_14_78L1 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 725613 | 01845 | 4.56 | Solar | 05_01_226L2 | 10/10/2025 | 10/16/2025 | 1 | 0 | 1 | 10/28/2025 | 10/28/2025 | 49 | 33 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 427518 | 01835 | 996 | Solar | 05_01_406L1 | 12/20/2022 | 04/06/2023 | 73 | 73 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2023 | 05/03/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 654347 | 01826 | 10 | Solar | 05_01_525L2 | 11/14/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/14/2024 | 3/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | PEPPERELL | 594220 | 01463 | 7.6 | Solar | 05_01_8J365 | 03/05/2024 | 03/08/2024 | 3 | 0 | 3 | 03/11/2024 | 03/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2024 | Connected |  | N
National Grid | CHARLTON | 388401 | 01507 | 15.2 | Solar | 05_05_28W40 | 10/13/2021 | 10/20/2021 | 5 | 5 | 0 | 10/21/2021 | 10/21/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 3/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2023 | Connected |  | Y
National Grid | WEST BROOKFIELD | 625884 | 01585 | 5.76 | Solar | 05_12_3J903 | 07/18/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | WORCESTER | 176495 | 01604 | 6 | Solar | 05_14_21L3 | 12/11/2015 | 12/11/2015 | 2 | 2 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2015 |  | 12/16/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 5/10/2016 | 5/10/2016 | 6/22/2016 | Connected |  | N
National Grid | FALL RIVER | 174994 | 02720 | 13 | Solar | 05_14_55L1 | 03/13/2013 | 03/13/2013 | 6 | 0 | 6 | 03/25/2013 | 03/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2013 |  | 6/28/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 4/15/2013 | 4/15/2013 | 6/5/2013 | Connected |  | N
National Grid | LYNN | 727455 | 01902 | 5.76 | Solar | 05_14_65L3 | 10/17/2025 | 10/24/2025 | 3 | 0 | 3 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | LOWELL | 650608 | 01854 | 12.16 | Solar | 05_14_78L1 | 10/29/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 49 | 24 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 738225 | 01845 | 7.6 | Solar | 05_01_226L2 | 12/04/2025 | 01/14/2026 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 433800 | 01835 | 9.984 | Solar | 05_01_406L1 | 06/15/2022 | 06/16/2022 | 1 | 0 | 1 | 06/17/2022 | 06/17/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2022 |  | 2/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 657273 | 01826 | 9.57 | Solar | 05_01_525L2 | 11/29/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/29/2024 | 1/28/2026 | Y | EXP | 365 | 07/02/2025 | 07/14/2025 | 13 | 0 | 13 |  |  | 7/24/2025 | Connected |  | N
National Grid | PEPPERELL | 600333 | 01463 | 10 | Solar | 05_01_8J365 | 03/29/2024 | 04/02/2024 | 2 | 0 | 2 | 04/03/2024 | 04/03/2024 | 15 | 9 | 6 | 05/22/2024 | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/31/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/3/2025 | N | EXP | 365 | 08/13/2024 | 01/16/2025 | 157 | 0 | 157 |  |  | 1/30/2025 | Connected |  | N
National Grid | OXFORD | 531727 | 01537 | 9.984 | Solar | 05_05_28W40 | 06/08/2023 | 06/14/2023 | 4 | 1 | 3 | 06/15/2023 | 06/15/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/08/2023 | 8/17/2024 | Y | EXP | 365 | 08/31/2023 | 09/02/2023 | 3 | 0 | 3 |  |  | 11/15/2023 | Connected |  | N
National Grid | BROOKFIELD | 644776 | 01506 | 3.8 | Solar | 05_12_3J903 | 10/03/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176706 | 01607 | 6.8 | Solar | 05_14_21L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 | 10/27/2015 | 11/2/2016 | Y | EXP | 351 | 05/11/2016 | 05/26/2016 | 11 | 0 | 11 | 11/17/2015 | 11/17/2015 | 10/25/2016 | Connected |  | N
National Grid | FALL RIVER | 177989 | 02720 | 15.2 | Solar | 05_14_55L1 | 08/28/2017 | 08/28/2017 | 27 | 26 | 1 | 10/10/2017 | 10/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/4/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | LYNN | 174723 | 01902 | 35 | Solar | 05_14_66L1 | 07/29/2010 | 07/29/2010 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 | 3/13/2017 | 3/13/2017 |  | Withdrawn |  | Y
National Grid | LOWELL | 650662 | 01854 | 5.76 | Solar | 05_14_78L1 | 11/11/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 11/11/2024 | 1/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | BOXFORD | 743829 | 01921 | 0 | Battery Add-On | 05_01_226L2 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HAVERHILL | 439718 | 01835 | 15.2 | Solar | 05_01_406L1 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | DRACUT | 657862 | 01826 | 10 | Solar | 05_01_525L2 | 12/02/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 12/02/2024 | 4/6/2026 | Y | EXP | 365 | 09/26/2025 | 09/25/2025 | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | PEPPERELL | 645707 | 01463 | 11.5 | Solar | 05_01_8J365 | 10/09/2024 | 11/07/2024 | 2 | 0 | 2 | 11/08/2024 | 11/08/2024 | 18 | 1 | 17 | 01/15/2025 | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 |  | 10/16/2025 | 189 | 80 | 109 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 599193 | 01507 | 7.6 | Solar | 05_05_28W40 | 04/03/2024 | 04/05/2024 | 2 | 0 | 2 | 04/08/2024 | 04/08/2024 | 9 | 4 | 5 | 05/03/2024 | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 05/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 6/13/2025 | N | EXP | 365 | 07/15/2024 | 08/08/2024 | 25 | 0 | 25 |  |  | 8/28/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 657446 | 01535 | 13.775 | Solar | 05_12_3J903 | 11/27/2024 | 12/24/2024 | 11 | 7 | 4 | 12/26/2024 | 12/26/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176926 | 01607 | 10 | Solar | 05_14_21L3 | 11/20/2015 | 11/20/2015 | 2 | 2 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 11/25/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 | 9/14/2016 | Connected |  | N
National Grid | FALL RIVER | 198292 | 02720 | 9.92 | Solar | 05_14_55L1 | 10/11/2018 | 11/01/2018 | 11 | 4 | 7 | 11/02/2018 | 11/02/2018 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2018 |  | 4/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2020 | Connected |  | N
National Grid | LYNN | 178684 | 01902 | 20 | Solar | 05_14_66L1 | 12/18/2017 | 12/18/2017 | 17 | 17 | 0 | 02/01/2018 | 02/01/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2018 |  | 12/24/2018 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  | 5/1/2018 | Connected |  | N
National Grid | LOWELL | 651579 | 01854 | 3.8 | Solar | 05_14_78L1 | 11/12/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/12/2024 | 4/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | ANDOVER | 748763 | 01845 | 24.96 | Solar | 05_01_226L2 | 02/09/2026 | 02/26/2026 | 12 | 8 | 4 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AMESBURY | 483875 | 01913 | 10 | Solar | 05_01_406L1 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 | 02/23/2023 | 7/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2023 | Connected |  | N
National Grid | DRACUT | 666204 | 01826 | 7.6 | Solar | 05_01_525L2 | 01/16/2025 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 680752 | 01463 | 10 | Solar | 05_01_8J365 | 03/26/2025 | 04/03/2025 | 7 | 5 | 2 | 04/04/2025 | 04/04/2025 | 49 | 29 | 20 | 08/04/2025 | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 |  | 10/27/2025 | 58 | 4 | 54 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | CHARLTON | 600530 | 01507 | 7.6 | Solar | 05_05_28W40 | 03/29/2024 | 06/25/2024 | 5 | 1 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2024 | Connected |  | N
National Grid | BROOKFIELD | 668521 | 01506 | 3.8 | Solar | 05_12_3J903 | 01/29/2025 | 02/17/2025 | 3 | 0 | 3 | 02/18/2025 | 02/18/2025 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 01/29/2025 | 6/25/2026 | Y | EXP | 365 | 06/14/2025 | 10/29/2025 | 138 | 0 | 138 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177872 | 01610 | 6 | Solar | 05_14_21L3 | 08/14/2017 | 08/14/2017 | 170 | 0 | 170 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/19/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 247814 | 02720 | 0 | Solar | 05_14_55L1 | 08/22/2019 | 08/22/2019 | 0 | 0 | 0 | 08/23/2019 | 08/23/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/22/2019 | 9/17/2020 | Y | EXP | 365 | 01/11/2020 | 02/07/2020 | 27 | 0 | 27 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 688941 | 01902 | 12.92 | Solar | 05_14_66L1 | 05/08/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | LOWELL | 652420 | 01854 | 3.8 | Solar | 05_14_78L1 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | ANDOVER | 174867 | 01845 | 11 | Solar | 05_01_226L2 | 08/06/2012 | 08/06/2012 | 6 | 0 | 6 | 08/16/2012 | 08/16/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 12/21/2012 | 12/21/2012 | 2/14/2013 | Connected |  | N
National Grid | AMESBURY | 538718 | 01913 | 20.01 | Solar | 05_01_406L1 | 07/05/2023 | 07/11/2023 | 4 | 3 | 1 | 07/12/2023 | 07/12/2023 | 114 | 25 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 670491 | 01826 | 15.04 | Solar | 05_01_525L2 | 02/06/2025 | 06/09/2025 | 11 | 6 | 5 | 06/10/2025 | 06/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | PEPPERELL | 691733 | 01463 | 7.6 | Solar | 05_01_8J365 | 05/14/2025 | 06/03/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 50 | 38 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 604010 | 01537 | 497.5 | Solar | 05_05_28W40 | 04/18/2024 | 05/24/2024 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2024 | 07/17/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 670620 | 01506 | 7.6 | Solar | 05_12_3J903 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | WORCESTER | 177958 | 01610 | 6 | Solar | 05_14_21L3 | 10/26/2017 | 10/26/2017 | 80 | 79 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 310835 | 02720 | 10 | Solar | 05_14_55L1 | 09/03/2020 | 09/08/2020 | 1 | 0 | 1 | 09/09/2020 | 09/09/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2020 |  | 9/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | LYNN | 722850 | 01902 | 16.403 | Solar | 05_14_66L2 | 10/03/2025 | 10/13/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 653219 | 01854 | 6.08 | Solar | 05_14_78L1 | 11/08/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/08/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | BOXFORD | 176589 | 01921 | 19.75 | Solar | 05_01_226L2 | 10/08/2015 | 10/08/2015 | 0 | 0 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2015 |  | 10/14/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 12/24/2015 | 12/24/2015 | 12/24/2015 | Connected |  | N
National Grid | AMESBURY | 550427 | 01913 | 6 | Solar | 05_01_406L1 | 08/23/2023 | 08/25/2023 | 3 | 1 | 2 | 08/28/2023 | 08/28/2023 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 676836 | 01826 | 15.2 | Solar | 05_01_525L2 | 03/10/2025 | 03/26/2025 | 5 | 1 | 4 | 05/19/2025 | 05/19/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | PEPPERELL | 177481 | 01463 | 150 | Solar | 05_01_8J389 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2016 |  | 7/16/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 | 3/20/2017 | 3/20/2017 | 3/20/2017 | Connected |  | N
National Grid | OXFORD | 607518 | 01537 | 5.76 | Solar | 05_05_28W40 | 04/29/2024 | 05/14/2024 | 3 | 0 | 3 | 05/15/2024 | 05/15/2024 | 54 | 45 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 04/29/2024 | 8/20/2025 | Y | EXP | 365 | 10/12/2024 | 01/17/2025 | 98 | 0 | 98 |  |  | 1/24/2025 | Connected |  | Y
National Grid | BROOKFIELD | 676181 | 01585 | 15.2 | Solar | 05_12_3J903 | 03/06/2025 | 04/18/2025 | 31 | 28 | 3 | 04/22/2025 | 04/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178024 | 01610 | 5.47 | Solar | 05_14_21L3 | 08/31/2017 | 08/31/2017 | 29 | 27 | 2 | 10/13/2017 | 10/13/2017 | 78 | 0 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 |  | 9/5/2018 | N | EXP | 324 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 375312 | 02720 | 8.376 | Solar | 05_14_55L1 | 08/17/2021 | 08/19/2021 | 2 | 0 | 2 | 08/20/2021 | 08/20/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 |  | 10/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2022 | Connected |  | N
National Grid | LYNN | 193104 | 01902 | 455 | Solar | 05_14_66L2 | 08/23/2018 | 08/28/2018 | 2 | 0 | 2 |  |  | 101 | 22 | 79 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 655515 | 01854 | 5.76 | Solar | 05_14_78L1 | 11/19/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ANDOVER | 176760 | 01845 | 10 | Solar | 05_01_226L2 | 02/24/2016 | 02/24/2016 | 1 | 1 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2016 | 02/24/2016 | 3/1/2017 | Y | EXP | 331 | 07/06/2016 | 08/27/2016 | 38 | 0 | 38 | 4/4/2016 | 4/4/2016 | 11/4/2016 | Connected |  | N
National Grid | AMESBURY | 586275 | 01913 | 20.01 | Solar | 05_01_406L1 | 02/19/2024 | 04/25/2024 | 48 | 46 | 2 | 04/26/2024 | 04/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 705957 | 01826 | 4980 | Solar | 05_01_525L2 | 08/26/2025 | 09/05/2025 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2025 | 09/26/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 584498 | 01463 | 10 | Solar | 05_01_8J389 | 02/14/2024 | 02/16/2024 | 2 | 0 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | OXFORD | 621029 | 01540 | 6.08 | Solar | 05_05_28W40 | 06/27/2024 | 07/25/2024 | 14 | 12 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 176236 | 01585 | 15 | Solar | 05_12_40J2 | 02/17/2015 | 02/17/2015 | 5 | 0 | 5 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2015 |  | 6/30/2015 | N | EXP | 124 |  |  | 0 | 0 | 0 | 4/1/2015 | 4/1/2015 | 7/2/2015 | Connected |  | N
National Grid | WORCESTER | 178418 | 01607 | 6 | Solar | 05_14_21L3 | 01/16/2018 | 01/16/2018 | 22 | 0 | 22 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2018 |  | 1/22/2019 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  | 6/8/2018 | Connected |  | N
National Grid | FALL RIVER | 379389 | 02720 | 9.57 | Solar | 05_14_55L1 | 09/02/2021 |  | 23 | 23 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 520212 | 01902 | 15.08 | Solar | 05_14_6J1 | 04/19/2023 | 04/20/2023 | 1 | 0 | 1 | 04/21/2023 | 04/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2023 |  | 7/16/2024 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 657540 | 01854 | 10 | Solar | 05_14_78L1 | 11/28/2024 |  | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 177411 | 01845 | 20 | Solar | 05_01_226L2 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/26/2016 | 09/26/2016 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 9/17/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 638065 | 01913 | 10.44 | Solar | 05_01_406L1 | 01/17/2025 | 03/20/2025 | 8 | 3 | 5 | 03/21/2025 | 03/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | DRACUT | 713186 | 01826 | 10 | Solar | 05_01_525L2 | 08/19/2025 |  | 86 | 27 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 176189 | 01463 | 0 | Battery Add-On | 05_01_8W1 | 09/01/2015 | 09/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 10/06/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 5/2/2016 | 09/01/2015 | 9/8/2016 | Y | STD | 129 | 04/19/2017 | 06/08/2017 | 35 | 0 | 35 | 8/1/2017 | 8/1/2017 | 8/29/2017 | Terminated |  | N
National Grid | OXFORD | 636299 | 01537 | 6 | Solar | 05_05_28W40 | 08/29/2024 | 09/24/2024 | 1 | 0 | 1 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 177497 | 01506 | 15.2 | Solar | 05_12_40J2 | 12/14/2016 | 12/14/2016 | 4 | 3 | 1 | 12/20/2016 | 12/20/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2016 | 12/14/2016 | 10/12/2018 | Y | EXP | 66 | 05/28/2016 | 02/03/2017 | 169 | 3 | 166 |  |  | 10/3/2018 | Connected |  | N
National Grid | WORCESTER | 198546 | 01607 | 7.6 | Solar | 05_14_21L3 | 11/16/2018 | 11/21/2018 | 3 | 3 | 0 | 11/26/2018 | 11/26/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 387061 | 02720 | 9.57 | Solar | 05_14_55L1 | 10/07/2021 | 10/14/2021 | 4 | 4 | 0 | 10/15/2021 | 10/15/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | ROCKPORT | 552102 | 01966 | 150 | Solar | 05_14_6J1 | 09/01/2023 | 09/24/2023 | 15 | 6 | 9 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 662302 | 01854 | 5.76 | Solar | 05_14_78L1 | 12/23/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/23/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | ANDOVER | 178118 | 01845 | 10 | Solar | 05_01_226L2 | 05/11/2017 | 05/11/2017 | 4 | 4 | 0 | 05/17/2017 | 05/17/2017 | 181 | 0 | 181 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2017 |  | 5/16/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 641186 | 01841 | 17.11 | Solar | 05_01_406L1 | 09/27/2024 | 10/17/2024 | 13 | 11 | 2 | 10/18/2024 | 10/18/2024 | 30 | 13 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | DRACUT | 492345 | 01826 | 5000 | Solar | 05_01_552L1 | 02/24/2023 | 03/21/2023 | 18 | 9 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2023 | 05/16/2023 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 724366 | 01463 | 3.8 | Solar | 05_01_8W1 | 10/06/2025 | 10/13/2025 | 4 | 1 | 3 | 10/14/2025 | 10/14/2025 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHARLTON | 642560 | 01507 | 10 | Solar | 05_05_28W40 | 09/30/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEST BROOKFIELD | 320446 | 01585 | 8 | Solar | 05_12_40J2 | 10/20/2020 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 305218 | 01604 | 10 | Solar | 05_14_21L3 | 08/31/2020 | 09/03/2020 | 2 | 0 | 2 | 09/04/2020 | 09/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/31/2020 | 8/2/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2021 | Connected |  | N
National Grid | FALL RIVER | 393293 | 02720 | 6.38 | Solar | 05_14_55L1 | 12/17/2021 | 01/06/2022 | 13 | 12 | 1 | 01/07/2022 | 01/07/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2022 |  | 3/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2022 | Connected |  | N
National Grid | ROCKPORT | 635232 | 01966 | 7.6 | Solar | 05_14_6J1 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/26/2024 | 9/30/2025 | Y | EXP | 365 | 06/18/2025 | 06/17/2025 | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | LOWELL | 711464 | 01854 | 7.6 | Solar | 05_14_78L1 | 08/12/2025 | 09/08/2025 | 4 | 0 | 4 | 10/07/2025 | 10/07/2025 | 60 | 47 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178432 | 01845 | 636 | Solar | 05_01_226L2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 650479 | 01841 | 9.423 | Solar | 05_01_406L1 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | DRACUT | 661587 | 01826 | 3.8 | Solar | 05_01_552L1 | 12/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 174487 | 01463 | 300 | Solar | 05_01_8W1 | 11/12/2010 | 11/12/2010 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2011 | 11/12/2010 | 10/31/2012 | Y | EXP | 61 | 05/30/2012 | 07/30/2012 | 41 | 0 | 41 | 1/18/2013 | 1/18/2013 | 8/17/2012 | Connected |  | N
National Grid | OXFORD | 646767 | 01537 | 10 | Solar | 05_05_28W40 | 10/14/2024 | 12/04/2024 | 3 | 0 | 3 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | SPENCER | 336432 | 01562 | 7.44 | Solar | 05_12_40J2 | 01/12/2021 | 01/13/2021 | 0 | 0 | 0 | 01/14/2021 | 01/14/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 | 01/12/2021 | 1/12/2022 | Y | EXP | 365 | 04/21/2021 | 04/20/2021 | 0 | 0 | 0 |  |  | 5/25/2021 | Connected |  | N
National Grid | WORCESTER | 330497 | 01607 | 3.8 | Solar | 05_14_21L3 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 | 12/21/2020 | 9/26/2022 | Y | EXP | 365 | 08/25/2021 | 10/05/2021 | 36 | 0 | 36 |  |  | 6/15/2022 | Connected |  | N
National Grid | FALL RIVER | 479560 | 02720 | 15.2 | Solar | 05_14_55L1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2023 | Connected |  | N
National Grid | ROCKPORT | 653900 | 01966 | 5.76 | Solar | 05_14_6J1 | 11/29/2024 | 12/31/2024 | 9 | 5 | 4 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 723417 | 01854 | 6.282 | Solar | 05_14_78L3 | 10/02/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 43 | 20 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 178743 | 01845 | 990 | Solar | 05_01_226L2 | 05/30/2018 | 07/18/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 08/01/2018 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 658838 | 01841 | 5.76 | Solar | 05_01_406L1 | 12/05/2024 | 12/20/2024 | 5 | 0 | 5 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 12/05/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 694028 | 01826 | 5.76 | Solar | 05_01_552L1 | 05/29/2025 | 08/13/2025 | 51 | 47 | 4 | 08/14/2025 | 08/14/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 | 05/29/2025 | 12/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 175354 | 01463 | 2100 | Solar | 05_01_8W1 | 09/09/2014 | 09/09/2014 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2014 | 10/17/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2015 | 09/09/2014 | 12/31/2016 | Y | STD | 579 | 12/28/2016 | 09/09/2017 | 176 | 0 | 176 | 5/17/2017 | 5/17/2017 | 5/17/2017 | Connected |  | N
National Grid | LEICESTER | 649643 | 01542 | 5.76 | Solar | 05_05_28W40 | 10/24/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 376072 | 01562 | 10 | Solar | 05_12_40J2 | 09/02/2021 | 09/02/2021 | 12 | 10 | 2 | 09/03/2021 | 09/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2021 | 09/02/2021 | 1/28/2023 | Y | EXP | 365 | 12/10/2021 | 01/27/2022 | 49 | 0 | 49 |  |  | 1/31/2022 | Connected |  | N
National Grid | MILLBURY | 406690 | 01527 | 43.2 | Solar | 05_14_21L3 | 01/19/2022 | 01/21/2022 | 3 | 1 | 2 | 01/24/2022 | 01/24/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  | 3/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | FALL RIVER | 572292 | 02720 | 480 | Solar | 05_14_55L1 | 12/07/2023 | 02/01/2024 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2024 | 02/20/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 175682 | 01966 | 115.2 | Solar | 05_14_6J2 | 12/24/2014 | 12/24/2014 | 4 | 0 | 4 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 | 12/24/2014 | 1/19/2016 | Y | EXP | 35 | 11/12/2015 | 09/01/2016 | 200 | 0 | 200 | 2/4/2015 | 2/4/2015 | 12/22/2015 | Connected |  | N
National Grid | LOWELL | 189632 | 01854 | 11.4 | Solar | 05_14_78L3 | 07/10/2019 | 06/29/2018 | 134 | 126 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 185273 | 01845 | 5310 | Solar | 05_01_226L2 | 07/23/2018 | 08/08/2018 | 12 | 12 | 0 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 08/09/2018 | 08/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 660796 | 01841 | 10 | Solar | 05_01_406L1 | 12/16/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | DRACUT | 702237 | 01826 | 21.75 | Solar | 05_01_552L1 | 07/01/2025 | 08/25/2025 | 37 | 32 | 5 | 08/26/2025 | 08/26/2025 | 41 | 22 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 175690 | 01463 | 225 | Solar | 05_01_8W1 | 05/23/2014 | 05/23/2014 | 6 | 0 | 6 | 06/04/2014 | 06/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 |  | 8/29/2014 | N | EXP | 63 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/29/2014 | Connected |  | N
National Grid | OXFORD | 660889 | 01537 | 10 | Solar | 05_05_28W40 | 12/16/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/4/2025 | Connected |  | N
National Grid | SPENCER | 398018 | 01562 | 5.52 | Solar | 05_12_40J2 | 11/29/2021 | 11/30/2021 | 1 | 1 | 0 | 12/01/2021 | 12/01/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 12/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2022 | Connected |  | N
National Grid | WORCESTER | 409499 | 01602 | 6 | Solar | 05_14_21L3 | 04/12/2022 |  | 63 | 27 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 575743 | 02720 | 240 | Solar | 05_14_55L1 | 12/08/2023 | 02/01/2024 | 36 | 25 | 11 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 177413 | 01966 | 3.8 | Solar | 05_14_6J2 | 09/12/2016 | 09/12/2016 | 1 | 1 | 0 | 09/14/2016 | 09/14/2016 | 282 | 0 | 282 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2016 | 09/12/2016 | 11/18/2017 | Y | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 194002 | 01854 | 15.2 | Solar | 05_14_78L3 | 08/20/2018 | 09/04/2018 | 20 | 10 | 10 | 10/11/2018 | 10/11/2018 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 198924 | 01845 | 10 | Solar | 05_01_226L2 | 10/18/2018 | 03/18/2019 | 39 | 35 | 4 | 03/19/2019 | 03/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 | 10/18/2018 | 1/14/2021 | Y | EXP | 365 | 06/03/2020 | 06/18/2020 | 15 | 0 | 15 |  |  | 7/3/2020 | Connected |  | N
National Grid | LAWRENCE | 661695 | 01841 | 10 | Solar | 05_01_406L1 | 12/19/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 705952 | 01826 | 996 | Solar | 05_01_552L1 | 08/14/2025 | 09/02/2025 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2025 | 10/16/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | PEPPERELL | 177625 | 01463 | 0 | Solar | 05_01_8W1 | 05/23/2017 | 05/23/2017 | 12 | 11 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/09/2017 | 07/03/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/28/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 704820 | 01507 | 1.16 | Solar | 05_05_28W40 | 07/14/2025 | 09/22/2025 | 49 | 45 | 4 | 09/23/2025 | 09/23/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2025 | Connected |  | N
National Grid | SPENCER | 420293 | 01562 | 10 | Solar | 05_12_40J2 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2022 | Connected |  | N
National Grid | WORCESTER | 493495 | 01607 | 16680 | Hydro | 05_14_21L3 | 01/19/2023 | 04/17/2023 | 60 | 51 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 06/05/2023 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 640040 | 02720 | 23.8 | Solar | 05_14_55L1 | 09/13/2024 | 09/17/2024 | 3 | 1 | 2 | 09/18/2024 | 09/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | ROCKPORT | 177910 | 01966 | 7.6 | Solar | 05_14_6J2 | 08/16/2017 | 08/16/2017 | 13 | 13 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2017 |  | 8/25/2020 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 194659 | 01854 | 7.6 | Solar | 05_14_78L3 | 08/28/2018 | 09/13/2018 | 8 | 0 | 8 | 09/14/2018 | 09/14/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 204874 | 01845 | 7.6 | Solar | 05_01_226L2 | 12/31/2018 | 01/25/2019 | 17 | 17 | 0 | 01/28/2019 | 01/28/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2019 | Connected |  | N
National Grid | LAWRENCE | 667149 | 01841 | 12.54 | Solar | 05_01_406L1 | 01/22/2025 | 02/13/2025 | 6 | 1 | 5 | 02/14/2025 | 02/14/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 01/22/2025 | 4/16/2026 | Y | EXP | 365 | 07/02/2025 | 10/23/2025 | 114 | 0 | 114 |  |  | 10/24/2025 | Connected |  | N
National Grid | DRACUT | 712983 | 01826 | 7.6 | Solar | 05_01_552L1 | 08/19/2025 | 10/02/2025 | 7 | 3 | 4 | 10/22/2025 | 10/22/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 08/19/2025 | 12/4/2026 | Y | EXP | 365 | 02/03/2026 |  | 32 | 0 | 32 |  |  |  | Construction |  | N
National Grid | PEPPERELL | 178575 | 01463 | 15.2 | Solar | 05_01_8W1 | 12/11/2017 | 12/11/2017 | 12 | 0 | 12 | 01/02/2018 | 01/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/18/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | CHARLTON | 388520 | 01507 | 400 | Solar | 05_05_28W41 | 01/12/2022 | 04/13/2022 | 63 | 51 | 12 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 01/12/2022 | 5/11/2026 | Y | STD | 161 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 418962 | 01562 | 0 | Solar | 05_12_40J2 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  | 4/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2022 | Connected |  | N
National Grid | WORCESTER | 537411 | 01607 | 10 | Solar | 05_14_21L3 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 650727 | 02720 | 23 | Solar | 05_14_55L1 | 10/31/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 10/31/2024 | 4/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2026 | Connected |  | N
National Grid | ROCKPORT | 197441 | 01966 | 3.8 | Solar | 05_14_6J2 | 10/04/2018 |  | 203 | 23 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 264017 | 01852 | 0 | Solar | 05_14_78L3 | 11/05/2019 | 11/08/2019 | 2 | 0 | 2 | 11/12/2019 | 11/12/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 11/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2020 | Connected |  | N
National Grid | ANDOVER | 218005 | 01845 | 15.2 | Solar | 05_01_226L2 | 04/05/2019 | 04/12/2019 | 4 | 0 | 4 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 4/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2019 | Connected |  | N
National Grid | LAWRENCE | 671156 | 01841 | 9.28 | Solar | 05_01_406L1 | 02/10/2025 | 03/15/2025 | 14 | 10 | 4 | 03/17/2025 | 03/17/2025 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 741140 | 01826 | 5.76 | Solar | 05_01_552L1 | 12/18/2025 | 12/19/2025 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 34 | 23 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | PEPPERELL | 178666 | 01463 | 2112 | Solar | 05_01_8W1 | 03/16/2018 | 03/16/2018 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 04/13/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174436 | 01507 | 75 | Solar | 05_05_28W41 | 06/27/2012 | 06/27/2012 | 7 | 0 | 7 | 07/12/2012 | 07/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/22/2012 | N | EXP | 51 |  |  | 0 | 0 | 0 | 9/28/2012 | 9/28/2012 | 12/14/2012 | Connected |  | N
National Grid | SPENCER | 442681 | 01562 | 5.8 | Solar | 05_12_40J2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 | 07/19/2022 | 4/23/2024 | Y | EXP | 365 | 12/22/2022 | 04/24/2023 | 124 | 0 | 124 |  |  | 4/27/2023 | Connected |  | N
National Grid | WORCESTER | 588627 | 01607 | 15 | Solar | 05_14_21L3 | 02/12/2024 | 03/06/2024 | 17 | 15 | 2 | 03/07/2024 | 03/07/2024 | 11 | 8 | 3 | 08/28/2024 | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 10/08/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 9/11/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 654018 | 02720 | 17.6 | Solar | 05_14_55L1 | 11/20/2024 | 12/02/2024 | 6 | 2 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | ROCKPORT | 297222 | 01966 | 249 | Solar | 05_14_6J2 | 06/18/2020 | 06/24/2020 | 4 | 3 | 1 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 299147 | 01854 | 10 | Solar | 05_14_78L3 | 07/13/2020 |  | 33 | 24 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 257041 | 01845 | 4890 | Solar | 05_01_226L2 | 04/13/2020 | 05/19/2020 | 25 | 21 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2020 | 06/18/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 671401 | 01841 | 23 | Solar | 05_01_406L1 | 02/11/2025 | 02/14/2025 | 4 | 1 | 3 | 02/18/2025 | 02/18/2025 | 123 | 102 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 743429 | 01826 | 9 | Solar | 05_01_552L1 | 01/05/2026 | 01/29/2026 | 17 | 17 | 0 | 01/30/2026 | 01/30/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEPPERELL | 193914 | 01463 | 60 | Solar | 05_01_8W1 | 08/20/2018 | 08/29/2018 | 6 | 0 | 6 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 174539 | 01507 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 523300 | 01562 | 10 | Solar | 05_12_40J2 | 05/02/2023 | 05/04/2023 | 2 | 0 | 2 | 05/05/2023 | 05/05/2023 | 160 | 137 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | WORCESTER | 600344 | 01604 | 3.8 | Solar | 05_14_21L3 | 04/05/2024 | 04/09/2024 | 3 | 1 | 2 | 04/10/2024 | 04/10/2024 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 | 04/05/2024 | 5/31/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2024 | Connected |  | N
National Grid | FALL RIVER | 657089 | 02720 | 10 | Solar | 05_14_55L1 | 11/26/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 335011 | 01966 | 166.6 | Solar | 05_14_6J2 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 381009 | 01854 | 7.6 | Solar | 05_14_78L3 | 10/08/2021 | 01/10/2022 | 0 | 0 | 0 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 5/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2022 | Connected |  | N
National Grid | ANDOVER | 312534 | 01845 | 7.6 | Solar | 05_01_226L2 | 10/06/2020 | 10/12/2020 | 3 | 0 | 3 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 10/06/2020 | 10/1/2021 | Y | EXP | 365 | 07/23/2021 | 07/26/2021 | 4 | 0 | 4 |  |  | 8/12/2021 | Connected |  | N
National Grid | LAWRENCE | 676130 | 01841 | 20 | Solar | 05_01_406L1 | 03/07/2025 | 03/17/2025 | 6 | 0 | 6 | 03/18/2025 | 03/18/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 174246 | 01826 | 1000 | Solar | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DUNSTABLE | 192232 | 01827 | 199.8 | Solar | 05_01_8W1 | 08/07/2018 | 08/22/2018 | 10 | 0 | 10 | 08/23/2018 | 08/23/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 08/07/2018 | 2/17/2021 | Y | EXP | 433 | 12/21/2019 | 03/01/2021 | 437 | 268 | 169 |  |  | 3/16/2021 | Connected |  | N
National Grid | OXFORD | 174538 | 01537 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 534135 | 01562 | 14.79 | Solar | 05_12_40J2 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 52 | 29 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2023 | Connected |  | N
National Grid | WORCESTER | 601226 | 01607 | 5 | Solar | 05_14_21L3 | 04/09/2024 | 04/15/2024 | 4 | 0 | 4 | 04/16/2024 | 04/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 04/09/2024 | 4/23/2025 | Y | EXP | 365 | 05/22/2024 | 07/23/2024 | 63 | 0 | 63 |  |  | 8/21/2024 | Connected |  | N
National Grid | FALL RIVER | 674728 | 02720 | 19 | Solar | 05_14_55L1 | 02/28/2025 | 03/05/2025 | 3 | 0 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2025 | Connected |  | N
National Grid | ROCKPORT | 506007 | 01966 | 17.6 | Solar | 05_14_6J2 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2023 | 03/07/2023 | 6/6/2024 | Y | EXP | 365 | 08/12/2023 | 10/11/2023 | 61 | 0 | 61 |  |  | 10/14/2023 | Connected |  | N
National Grid | LOWELL | 405981 | 01854 | 0 | Battery Add-On | 05_14_78L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/04/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 321315 | 01845 | 8.41 | Solar | 05_01_226L2 | 10/23/2020 | 11/18/2020 | 16 | 15 | 1 | 11/19/2020 | 11/19/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/18/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 703419 | 01841 | 7.6 | Solar | 05_01_406L1 | 07/10/2025 | 07/23/2025 | 3 | 0 | 3 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 | 07/10/2025 | 9/8/2026 | Y | EXP | 365 | 11/14/2025 | 12/02/2025 | 19 | 0 | 19 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 174248 | 01826 | 1000 | Solar | 05_01_552L1 | 02/23/2012 | 02/23/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 10/01/2012 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/6/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 206477 | 01463 | 360 | Solar | 05_01_8W1 | 03/21/2019 | 04/02/2019 | 8 | 7 | 1 | 04/03/2019 | 04/03/2019 | 35 | 21 | 14 | 10/16/2019 | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  | 01/23/2020 | 67 | 50 | 17 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 174537 | 01507 | 950 | Solar | 05_05_28W41 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 551438 | 01562 | 10 | Solar | 05_12_40J2 | 11/16/2023 | 11/20/2023 | 2 | 0 | 2 | 11/21/2023 | 11/21/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 1/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2024 | Connected |  | N
National Grid | WORCESTER | 617219 | 01607 | 7.6 | Solar | 05_14_21L3 | 06/11/2024 | 06/28/2024 | 3 | 0 | 3 | 07/01/2024 | 07/01/2024 | 18 | 8 | 10 | 08/16/2024 | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 09/13/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/23/2024 | 06/11/2024 |  | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 690737 | 02720 | 7.6 | Solar | 05_14_55L1 | 05/09/2025 | 05/22/2025 | 5 | 0 | 5 | 06/11/2025 | 06/11/2025 | 44 | 28 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | ROCKPORT | 549133 | 01966 | 6 | Solar | 05_14_6J2 | 09/06/2023 | 09/11/2023 | 4 | 3 | 1 | 09/12/2023 | 09/12/2023 | 46 | 22 | 24 | 11/28/2023 | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 |  | 01/23/2024 | 37 | 3 | 34 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 417105 | 01854 | 362.5 | Solar | 05_14_78L3 | 03/25/2022 | 06/15/2022 | 56 | 47 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/16/2022 | 07/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 334209 | 01845 | 17.6 | Solar | 05_01_226L2 | 01/29/2021 | 02/17/2021 | 12 | 12 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2021 |  | 2/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2021 | Connected |  | N
National Grid | LAWRENCE | 679432 | 01841 | 0 | Battery Add-On | 05_01_406L2 | 04/14/2025 | 04/25/2025 | 7 | 3 | 4 | 04/28/2025 | 04/28/2025 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174527 | 01826 | 1000 | Solar | 05_01_552L1 | 09/12/2011 | 09/12/2011 | 99 | 0 | 99 | 02/06/2012 | 02/06/2012 | 655 | 0 | 655 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 307513 | 01463 | 3.8 | Solar | 05_01_8W1 | 10/21/2020 | 10/26/2020 | 2 | 0 | 2 | 10/27/2020 | 10/27/2020 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 176173 | 01507 | 972 | Solar | 05_05_28W41 | 04/23/2015 | 04/23/2015 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/29/2015 | 05/26/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 11/18/2015 | 12/21/2015 | 22 | 0 | 22 | 1/22/2016 | 04/23/2015 | 9/30/2015 | Y | STD | 114 | 07/12/2016 | 10/17/2016 | 67 | 0 | 67 | 10/21/2016 | 10/21/2016 | 10/28/2016 | Connected |  | N
National Grid | SPENCER | 562901 | 01562 | 9.86 | Solar | 05_12_40J2 | 11/01/2023 | 11/07/2023 | 5 | 2 | 3 | 11/08/2023 | 11/08/2023 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 | 11/01/2023 | 12/28/2024 | Y | EXP | 365 | 03/21/2024 | 04/03/2024 | 14 | 0 | 14 |  |  | 6/22/2024 | Connected |  | N
National Grid | WORCESTER | 632778 | 01607 | 10 | Solar | 05_14_21L3 | 08/14/2024 | 08/26/2024 | 1 | 0 | 1 | 08/27/2024 | 08/27/2024 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N
National Grid | FALL RIVER | 198828 | 02720 | 10 | Solar | 05_14_55L2 | 10/19/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 |  | 7/1/2019 | N | EXP | 23 |  |  | 0 | 0 | 0 |  |  | 6/19/2019 | Connected |  | N
National Grid | ROCKPORT | 582362 | 01966 | 2.9 | Solar | 05_14_6J2 | 01/17/2024 | 01/19/2024 | 2 | 0 | 2 | 01/22/2024 | 01/22/2024 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 483029 | 01854 | 0 | Other | 05_14_78L3 | 01/12/2023 | 02/15/2023 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2023 | 03/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 343268 | 01845 | 10 | Solar | 05_01_226L2 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2021 | Connected |  | N
National Grid | LAWRENCE | 684121 | 01841 | 11.4 | Solar | 05_01_406L2 | 04/14/2025 | 04/18/2025 | 4 | 0 | 4 | 04/22/2025 | 04/22/2025 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174577 | 01826 | 3000 | Solar | 05_01_552L1 | 02/14/2011 | 02/14/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2011 | 03/23/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 2/28/2012 | 02/14/2011 | 12/31/2016 | Y | STD | 1768 | 11/29/2016 | 08/29/2017 | 188 | 0 | 188 | 3/10/2017 | 3/10/2017 | 3/10/2017 | Connected |  | N
National Grid | PEPPERELL | 360536 | 01463 | 7.6 | Solar | 05_01_8W1 | 06/17/2021 | 06/21/2021 | 2 | 0 | 2 | 06/22/2021 | 06/22/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  | 8/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 177659 | 01501 | 240 | Solar | 05_05_28W41 | 11/13/2017 | 11/13/2017 | 51 | 42 | 9 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 11/19/2018 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | SPENCER | 630449 | 01562 | 4.06 | Solar | 05_12_40J2 | 08/06/2024 | 09/17/2024 | 1 | 0 | 1 | 09/18/2024 | 09/18/2024 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | WORCESTER | 639539 | 01610 | 3.8 | Solar | 05_14_21L3 | 09/11/2024 | 10/22/2024 | 26 | 23 | 3 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/11/2024 | 11/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | FALL RIVER | 348152 | 02720 | 7.25 | Solar | 05_14_55L2 | 03/22/2021 | 03/25/2021 | 3 | 3 | 0 | 03/26/2021 | 03/26/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2021 |  | 3/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2021 | Connected |  | N
National Grid | ROCKPORT | 643758 | 01966 | 4.64 | Solar | 05_14_6J2 | 09/30/2024 | 11/12/2024 | 4 | 0 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2025 | Connected |  | N
National Grid | LOWELL | 491978 | 01854 | 7.6 | Solar | 05_14_78L3 | 03/03/2023 | 03/06/2023 | 1 | 0 | 1 | 03/07/2023 | 03/07/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2023 | 03/03/2023 | 6/29/2024 | Y | EXP | 365 | 06/13/2023 | 06/30/2023 | 18 | 0 | 18 |  |  | 7/13/2023 | Connected |  | N
National Grid | ANDOVER | 357623 | 01845 | 9.8 | Solar | 05_01_226L2 | 05/12/2021 | 05/13/2021 | 1 | 1 | 0 | 05/14/2021 | 05/14/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/12/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2021 | Connected |  | N
National Grid | LAWRENCE | 726973 | 01841 | 7.6 | Solar | 05_01_406L2 | 10/16/2025 | 11/13/2025 | 5 | 0 | 5 | 01/06/2026 | 01/06/2026 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | DRACUT | 174632 | 01826 | 1500 | Solar | 05_01_552L1 | 05/13/2013 | 05/13/2013 | 218 | 212 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 396692 | 01463 | 0 | Other | 05_01_8W1 | 09/19/2022 | 10/24/2022 | 24 | 13 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2022 | 11/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 177932 | 01501 | 180 | Solar | 05_05_28W41 | 04/20/2017 | 04/20/2017 | 14 | 13 | 1 | 05/10/2017 | 05/10/2017 | 0 | 0 | 0 | 06/29/2017 | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  | 07/27/2017 | 19 | 1 | 18 |  |  | 0 | 0 | 0 | 9/20/2017 |  | 4/25/2018 | N | EXP | 217 |  |  | 0 | 0 | 0 | 12/8/2017 | 12/8/2017 | 12/15/2017 | Connected |  | N
National Grid | SPENCER | 659692 | 01562 | 7.83 | Solar | 05_12_40J2 | 12/10/2024 | 12/29/2024 | 9 | 4 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/10/2024 | 3/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 646886 | 01607 | 5.76 | Solar | 05_14_21L3 | 10/14/2024 | 12/18/2024 | 37 | 34 | 3 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 553486 | 02720 | 15.2 | Solar | 05_14_55L2 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | Y
National Grid | ROCKPORT | 661733 | 01966 | 10 | Solar | 05_14_6J2 | 12/19/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | DRACUT | 602555 | 01826 | 0 | Battery Add-On | 05_14_78L3 | 04/10/2024 | 05/09/2024 | 20 | 16 | 4 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/10/2024 | 12/31/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 399819 | 01845 | 7.6 | Solar | 05_01_226L2 | 12/16/2021 | 12/20/2021 | 2 | 0 | 2 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 | 12/16/2021 | 6/8/2023 | Y | EXP | 365 | 05/11/2022 | 06/07/2022 | 28 | 0 | 28 |  |  | 6/16/2022 | Connected |  | N
National Grid | LAWRENCE | 174703 | 01841 | 492 | Solar | 05_01_406L2 | 06/10/2013 | 06/10/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2013 | 07/22/2013 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 06/10/2013 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 175566 | 01826 | 997.6 | Solar | 05_01_552L1 | 10/06/2014 | 10/06/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2014 | 11/14/2014 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 9/1/2016 | N | STD | 447 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 396740 | 01463 | 3486 | Other | 05_01_8W1 | 07/07/2023 | 09/05/2023 | 41 | 31 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2023 | 01/22/2024 | 93 | 75 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 178275 | 01501 | 990 | Solar | 05_05_28W41 | 02/21/2018 | 02/21/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 05/08/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 706632 | 01562 | 20.475 | Solar | 05_12_40J2 | 07/22/2025 | 08/14/2025 | 16 | 13 | 3 | 08/15/2025 | 08/15/2025 | 37 | 18 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | WORCESTER | 655534 | 01607 | 3.8 | Solar | 05_14_21L3 | 11/19/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | FALL RIVER | 598369 | 02720 | 14.208 | Solar | 05_14_55L2 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | ROCKPORT | 682496 | 01966 | 15.2 | Solar | 05_14_6J3 | 04/03/2025 | 04/14/2025 | 7 | 5 | 2 | 04/15/2025 | 04/15/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 |  | 7/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 629864 | 01854 | 5.76 | Solar | 05_14_78L3 | 08/02/2024 | 08/29/2024 | 2 | 0 | 2 | 08/30/2024 | 08/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2024 | 08/02/2024 | 9/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | ANDOVER | 401910 | 01845 | 0 | Battery Add-On | 05_01_226L2 | 12/29/2021 | 01/04/2022 | 3 | 0 | 3 | 01/05/2022 | 01/05/2022 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175330 | 01841 | 996 | Solar | 05_01_406L2 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 175715 | 01826 | 1500 | Solar | 05_01_552L1 | 12/30/2014 | 12/30/2014 | 15 | 14 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/22/2015 | 02/24/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 396738 | 01463 | 0 | Other | 05_01_8W1 | 07/13/2022 | 08/16/2022 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2022 | 09/13/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 189617 | 01540 | 249.8 | Solar | 05_05_28W41 | 06/29/2018 | 06/29/2018 | 6 | 5 | 1 | 07/11/2018 | 07/11/2018 | 43 | 21 | 22 | 09/28/2018 | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 |  | 12/07/2018 | 48 | 19 | 29 |  |  | 0 | 0 | 0 | 3/18/2019 | 06/29/2018 | 12/30/2021 | Y | EXP | 389 | 10/23/2021 | 11/19/2021 | 28 | 4 | 24 |  |  | 12/30/2021 | Connected |  | N
National Grid | SPENCER | 713056 | 01562 | 9.772 | Solar | 05_12_40J2 | 10/06/2025 | 10/08/2025 | 2 | 0 | 2 | 10/09/2025 | 10/09/2025 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 |  | 11/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2025 | Connected |  | N
National Grid | WORCESTER | 666729 | 01607 | 7.6 | Solar | 05_14_21L3 | 01/20/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/20/2025 | 4/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | FALL RIVER | 661473 | 02720 | 7.6 | Solar | 05_14_55L2 | 12/18/2024 | 02/21/2025 | 11 | 7 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | ROCKPORT | 285114 | 01966 | 7.6 | Solar | 05_14_6J3 | 04/01/2020 | 04/22/2020 | 1 | 0 | 1 | 04/23/2020 | 04/23/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 636599 | 01854 | 5.76 | Solar | 05_14_78L3 | 08/29/2024 | 09/26/2024 | 7 | 4 | 3 | 09/27/2024 | 09/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 08/29/2024 | 11/25/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | ANDOVER | 426686 | 01845 | 0 | Solar | 05_01_226L2 | 04/27/2022 | 07/21/2022 | 58 | 49 | 9 | 07/22/2022 | 07/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2022 |  | 9/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2022 | Connected |  | N
National Grid | LAWRENCE | 175412 | 01841 | 2000 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 175966 | 01826 | 18 | Solar | 05_01_552L1 | 08/06/2015 | 08/06/2015 | 4 | 4 | 0 | 08/14/2015 | 08/14/2015 | 216 | 0 | 216 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/15/2016 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 398501 | 01463 | 9.8 | Solar | 05_01_8W1 | 02/03/2022 | 05/13/2022 | 3 | 3 | 0 | 05/16/2022 | 05/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 | 02/03/2022 | 8/12/2023 | Y | EXP | 365 | 07/15/2022 | 08/11/2022 | 28 | 0 | 28 |  |  | 9/6/2022 | Connected |  | N
National Grid | OXFORD | 203810 | 01540 | 250 | Solar | 05_05_28W41 | 01/11/2019 | 01/02/2019 | 7 | 4 | 3 | 01/03/2019 | 01/03/2019 | 5 | 0 | 5 | 02/12/2019 | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 03/07/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 556928 | 01562 | 6 | Solar | 05_12_40J4 | 10/27/2023 | 10/30/2023 | 1 | 0 | 1 | 10/31/2023 | 10/31/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 10/27/2023 | 12/7/2024 | Y | EXP | 365 | 03/30/2024 | 06/18/2024 | 81 | 0 | 81 |  |  | 7/11/2024 | Connected |  | N
National Grid | WORCESTER | 649096 | 01607 | 11.5 | Solar | 05_14_24L1 | 10/24/2024 | 12/11/2024 | 4 | 1 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 10/24/2024 | 3/2/2026 | Y | EXP | 395 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 671315 | 02720 | 7.6 | Solar | 05_14_55L2 | 02/11/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 315756 | 01966 | 7.6 | Solar | 05_14_6J3 | 10/13/2020 |  | 39 | 38 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 641351 | 01854 | 5.76 | Solar | 05_14_78L3 | 09/18/2024 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 433783 | 01845 | 15.2 | Solar | 05_01_226L2 | 06/08/2022 | 06/09/2022 | 1 | 0 | 1 | 06/10/2022 | 06/10/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 |  | 7/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | LAWRENCE | 175411 | 01841 | 1992 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 176251 | 01826 | 499 | Solar | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 62 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | PEPPERELL | 408866 | 01463 | 0 | Battery Add-On | 05_01_8W1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 09/02/2022 | 135 | 129 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 646539 | 01540 | 2850 | Solar | 05_05_28W50 | 03/28/2025 | 05/07/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/08/2025 | 06/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SPENCER | 681602 | 01562 | 50 | Solar | 05_12_40L1 | 05/20/2025 | 05/23/2025 | 3 | 0 | 3 | 05/27/2025 | 05/27/2025 | 35 | 10 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | AUBURN | 731515 | 01501 | 15.2 | Solar | 05_14_24L1 | 11/05/2025 | 11/10/2025 | 3 | 0 | 3 | 11/12/2025 | 11/12/2025 | 36 | 15 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 567932 | 02720 | 60 | Solar | 05_14_56L1 | 06/04/2024 | 07/02/2024 | 19 | 12 | 7 | 07/03/2024 | 07/03/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 6/25/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | ROCKPORT | 177072 | 01966 | 75 | Solar | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | CHELMSFORD | 647602 | 01824 | 6 | Solar | 05_14_78L3 | 10/16/2024 | 10/29/2024 | 4 | 0 | 4 | 10/30/2024 | 10/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2025 | Connected |  | N
National Grid | ANDOVER | 435399 | 01845 | 10 | Solar | 05_01_226L2 | 06/23/2022 | 07/21/2022 | 20 | 16 | 4 | 07/22/2022 | 07/22/2022 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2022 |  | 11/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2023 | Connected |  | N
National Grid | LAWRENCE | 175410 | 01841 | 1992 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  | 12/1/2016 | Connected |  | N
National Grid | DRACUT | 176250 | 01826 | 499 | Solar | 05_01_552L1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2015 | 08/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2016 | 07/07/2015 | 10/26/2017 | Y | STD | 62 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 12/27/2017 | Connected |  | N
National Grid | PEPPERELL | 559088 | 01463 | 10 | Solar | 05_01_8W1 | 10/03/2023 | 10/06/2023 | 3 | 0 | 3 | 10/10/2023 | 10/10/2023 | 106 | 28 | 78 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 748496 | 01540 | 11.4 | Solar | 05_05_28W50 | 01/30/2026 | 02/12/2026 | 3 | 0 | 3 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 366436 | 01562 | 6.96 | Solar | 05_12_40L1 | 06/28/2021 | 06/30/2021 | 2 | 0 | 2 | 07/01/2021 | 07/01/2021 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 740250 | 01604 | 10 | Solar | 05_14_24L1 | 12/16/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 52 | 40 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 726653 | 02720 | 11.5 | Solar | 05_14_56L1 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKPORT | 177070 | 01966 | 108 | Solar | 05_14_6J4 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/8/2017 | 3/8/2017 | 3/8/2017 | Connected |  | N
National Grid | CHELMSFORD | 658910 | 01824 | 5.76 | Solar | 05_14_78L3 | 12/06/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/06/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 440673 | 01845 | 9.28 | Solar | 05_01_226L2 | 06/30/2022 | 07/01/2022 | 1 | 0 | 1 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175409 | 01841 | 996 | Solar | 05_01_406L2 | 03/04/2014 | 03/04/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/04/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 176305 | 01826 | 16.5 | Solar | 05_01_552L1 | 02/20/2015 | 02/20/2015 | 10 | 5 | 5 | 03/07/2015 | 03/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2015 |  | 7/31/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 7/29/2015 | Connected |  | N
National Grid | PEPPERELL | 559181 | 01463 | 10 | Solar | 05_01_8W1 | 10/09/2023 | 10/13/2023 | 5 | 4 | 1 | 10/16/2023 | 10/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 10/09/2023 | 12/23/2024 | Y | EXP | 365 | 01/12/2024 | 01/18/2024 | 7 | 0 | 7 |  |  | 3/6/2024 | Connected |  | N
National Grid | OXFORD | 174477 | 01540 | 203 | Solar | 05_05_28W50 | 04/27/2011 | 04/27/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 430455 | 01562 | 15.2 | Solar | 05_12_40L1 | 05/19/2022 | 05/20/2022 | 1 | 0 | 1 | 05/23/2022 | 05/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 7/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2022 | Connected |  | N
National Grid | WORCESTER | 749125 | 01607 | 11.4 | Solar | 05_14_24L1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 725726 | 02720 | 46 | Solar | 05_14_56L1 | 11/12/2025 | 11/14/2025 | 2 | 1 | 1 | 11/17/2025 | 11/17/2025 | 42 | 23 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKPORT | 317552 | 01966 | 33.3 | Solar | 05_14_6J4 | 10/06/2020 | 11/06/2020 | 23 | 15 | 8 | 11/09/2020 | 11/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2021 | Connected |  | N
National Grid | CHELMSFORD | 660373 | 01824 | 7.6 | Solar | 05_14_78L3 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 473320 | 01845 | 3.48 | Solar | 05_01_226L2 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/18/2022 | 4/19/2024 | Y | EXP | 365 | 04/12/2023 | 04/19/2023 | 8 | 0 | 8 |  |  | 6/23/2023 | Connected |  | N
National Grid | LAWRENCE | 175408 | 01840 | 2000 | Solar | 05_01_406L2 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/07/2014 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/03/2014 | 9/14/2016 | Y | STD | 532 | 06/27/2016 | 12/20/2016 | 121 | 0 | 121 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 176428 | 01826 | 10 | Solar | 05_01_552L1 | 02/03/2016 | 02/03/2016 | 3 | 3 | 0 | 02/09/2016 | 02/09/2016 | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2016 |  | 2/9/2017 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 568724 | 01463 | 7.6 | Solar | 05_01_8W1 | 11/10/2023 | 11/15/2023 | 3 | 1 | 2 | 11/16/2023 | 11/16/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 |  | 5/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | OXFORD | 174472 | 01540 | 250 | Solar | 05_05_28W50 | 04/28/2011 | 04/28/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 9/28/2011 | Connected |  | N
National Grid | SPENCER | 434717 | 01562 | 10 | Solar | 05_12_40L1 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 5/15/2024 | N | EXP | 365 | 01/07/2023 | 05/15/2023 | 129 | 0 | 129 |  |  | 5/24/2023 | Connected |  | N
National Grid | WORCESTER | 175186 | 01607 | 335 | Solar | 05_14_24L1 | 11/18/2013 | 11/18/2013 | 1 | 0 | 1 | 11/20/2013 | 11/20/2013 | 494 | 0 | 494 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2013 |  | 4/30/2014 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 738785 | 02720 | 0 | Battery Add-On | 05_14_56L1 | 12/08/2025 | 12/11/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/14/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKPORT | 604190 | 01966 | 6.09 | Solar | 05_14_6J4 | 04/17/2024 | 04/23/2024 | 5 | 2 | 3 | 04/24/2024 | 04/24/2024 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 662183 | 01824 | 3.8 | Solar | 05_14_78L3 | 12/23/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 478031 | 01845 | 4.64 | Solar | 05_01_226L2 | 12/15/2022 | 12/20/2022 | 3 | 0 | 3 | 12/21/2022 | 12/21/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2023 | Connected |  | N
National Grid | LAWRENCE | 175665 | 01841 | 996 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 176541 | 01826 | 900 | Solar | 05_01_552L1 | 02/10/2016 | 02/16/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/08/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 | 02/10/2016 | 2/11/2022 | Y | STD | 1348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 571635 | 01463 | 6 | Solar | 05_01_8W1 | 12/04/2023 | 12/05/2023 | 1 | 0 | 1 | 12/06/2023 | 12/06/2023 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 12/04/2023 | 5/10/2025 | Y | EXP | 365 | 06/08/2024 | 07/17/2024 | 40 | 0 | 40 |  |  | 9/11/2024 | Connected |  | N
National Grid | OXFORD | 174535 | 01540 | 0 | Solar | 05_05_28W50 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2013 | 10/18/2011 | 10/31/2012 | Y | STD | 16 | 11/22/2013 | 12/19/2013 | 18 | 0 | 18 | 12/19/2013 | 12/19/2013 | 12/23/2013 | Connected |  | N
National Grid | SPENCER | 471710 | 01562 | 5.22 | Solar | 05_12_40L1 | 11/14/2022 | 11/22/2022 | 6 | 3 | 3 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/14/2022 | 11/15/2024 | Y | EXP | 365 | 05/17/2023 | 11/06/2023 | 174 | 0 | 174 |  |  | 12/6/2023 | Connected |  | Y
National Grid | WORCESTER | 175755 | 01607 | 325 | Solar | 05_14_24L1 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 18 | 03/10/2015 | 04/24/2015 | 31 | 0 | 31 | 5/22/2015 | 5/22/2015 | 5/26/2015 | Connected |  | N
National Grid | FALL RIVER | 174528 | 02720 | 500 | Solar | 05_14_56L1 | 08/09/2011 | 08/09/2011 | 29 | 0 | 29 | 09/20/2011 | 09/20/2011 | 1281 | 0 | 1281 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2011 |  | 12/31/2016 | N | EXP | 1915 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 659147 | 01966 | 11.4 | Solar | 05_14_6J4 | 12/08/2024 |  | 23 | 18 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 668197 | 01824 | 7.68 | Solar | 05_14_78L3 | 02/03/2025 | 02/25/2025 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | ANDOVER | 488269 | 01845 | 20.591 | Solar | 05_01_226L2 | 12/27/2022 |  | 42 | 41 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 175667 | 01841 | 470 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 176750 | 01826 | 11.4 | Solar | 05_01_552L1 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 265 | 0 | 265 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 |  | 1/17/2017 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 609603 | 01463 | 10 | Solar | 05_01_8W1 | 05/08/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | OXFORD | 175803 | 01540 | 990 | Solar | 05_05_28W50 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 522876 | 01562 | 10 | Solar | 05_12_40L1 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 05/08/2023 | 6/20/2024 | Y | EXP | 365 | 08/19/2023 | 10/18/2023 | 61 | 0 | 61 |  |  | 10/23/2023 | Connected |  | N
National Grid | WORCESTER | 176456 | 01604 | 7.6 | Solar | 05_14_24L1 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2016 |  | 12/14/2016 | N | EXP | 342 |  |  | 0 | 0 | 0 | 6/10/2016 | 6/10/2016 | 6/16/2016 | Connected |  | N
National Grid | FALL RIVER | 290152 | 02720 | 10 | Solar | 05_14_56L1 | 05/01/2020 | 05/04/2020 | 0 | 0 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | ROCKPORT | 665348 | 01966 | 6.09 | Solar | 05_14_6J4 | 01/13/2025 | 03/04/2025 | 18 | 13 | 5 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | CHELMSFORD | 668055 | 01824 | 5.76 | Solar | 05_14_78L3 | 01/27/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 498726 | 01845 | 12.47 | Solar | 05_01_226L2 | 02/02/2023 | 02/06/2023 | 2 | 0 | 2 | 02/07/2023 | 02/07/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | Y
National Grid | LAWRENCE | 175666 | 01843 | 996 | Solar | 05_01_406L2 | 08/08/2014 | 08/08/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2014 | 08/18/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 08/08/2014 | 7/29/2016 | Y | STD | 589 |  |  | 0 | 0 | 0 |  |  | 11/23/2016 | Connected |  | N
National Grid | DRACUT | 177078 | 01826 | 22.8 | Solar | 05_01_552L1 | 10/17/2016 | 10/17/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/17/2016 | 10/23/2017 | Y | EXP | 364 | 03/28/2017 | 05/22/2017 | 38 | 0 | 38 | 8/29/2017 | 8/29/2017 | 9/1/2017 | Connected |  | N
National Grid | PEPPERELL | 616890 | 01463 | 5.76 | Solar | 05_01_8W1 | 06/10/2024 | 06/21/2024 | 1 | 0 | 1 | 06/24/2024 | 06/24/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | OXFORD | 177533 | 01540 | 9.92 | Solar | 05_05_28W50 | 09/11/2017 | 09/11/2017 | 22 | 22 | 0 | 10/13/2017 | 10/13/2017 | 113 | 0 | 113 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 | 09/11/2017 | 11/30/2018 | Y | EXP | 41 | 07/26/2018 | 08/21/2018 | 26 | 0 | 26 |  |  | 11/26/2018 | Connected |  | N
National Grid | SPENCER | 559826 | 01562 |  | Solar | 05_12_40L1 | 10/18/2023 | 10/20/2023 | 3 | 1 | 2 | 10/23/2023 | 10/23/2023 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2024 | Connected |  | N
National Grid | WORCESTER | 176621 | 01607 | 7.6 | Solar | 05_14_24L1 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 08/16/2016 | 08/31/2016 | 11 | 0 | 11 | 3/1/2017 | 3/1/2017 | 3/1/2017 | Connected |  | N
National Grid | FALL RIVER | 339459 | 02720 | 0 | Battery Add-On | 05_14_56L1 | 01/29/2021 | 02/01/2021 | 0 | 0 | 0 | 02/02/2021 | 02/02/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2021 |  | 3/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2022 | Connected |  | N
National Grid | ROCKPORT | 174705 | 01966 | 250 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 192 | 0 | 192 | 07/12/2013 | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  | 09/16/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 8/15/2013 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 685222 | 01824 | 6.282 | Solar | 05_14_78L3 | 04/15/2025 | 04/23/2025 | 5 | 0 | 5 | 04/24/2025 | 04/24/2025 | 65 | 49 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 559025 | 01845 | 9.57 | Solar | 05_01_226L2 | 09/29/2023 | 10/12/2023 | 9 | 8 | 1 | 10/13/2023 | 10/13/2023 | 75 | 52 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 4/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2024 | Connected |  | N
National Grid | LAWRENCE | 175815 | 01841 | 360 | Solar | 05_01_406L2 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 625 | 0 | 625 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 8/24/2018 | N | EXP | 112 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 177415 | 01826 | 995 | Landfill Gas | 05_01_552L1 | 09/15/2016 | 09/26/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2016 | 10/18/2016 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2017 | 09/15/2016 | 11/12/2019 | Y | STD | 928 | 01/09/2019 | 02/24/2019 | 46 | 0 | 46 |  |  | 10/31/2019 | Connected |  | N
National Grid | PEPPERELL | 619190 | 01463 | 5.76 | Solar | 05_01_8W1 | 06/20/2024 | 07/03/2024 | 1 | 0 | 1 | 07/05/2024 | 07/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 177913 | 01540 | 2000 | Solar | 05_05_28W50 | 07/11/2017 | 07/11/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2017 | 08/22/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2018 |  | 6/24/2019 | N | STD | 445 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 608732 | 01562 | 3.8 | Solar | 05_12_40L1 | 05/03/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/03/2024 | 7/9/2025 | Y | EXP | 365 | 08/15/2024 | 11/06/2024 | 83 | 0 | 83 |  |  | 11/20/2024 | Connected |  | N
National Grid | WORCESTER | 176675 | 01604 | 10 | Solar | 05_14_24L1 | 01/04/2016 | 01/04/2016 | 1 | 1 | 0 | 01/06/2016 | 01/06/2016 | 62 | 0 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/10/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 451464 | 02720 | 50 | Solar | 05_14_56L1 | 08/12/2022 | 09/19/2022 | 26 | 16 | 10 |  |  | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 175136 | 01966 | 100 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 714136 | 01824 | 7.6 | Solar | 05_14_78L3 | 08/22/2025 | 10/02/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 79 | 65 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 559004 | 01845 | 30 | Solar | 05_01_226L2 | 09/29/2023 | 10/06/2023 | 5 | 4 | 1 | 10/10/2023 | 10/10/2023 | 117 | 92 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 09/29/2023 | 4/9/2025 | Y | EXP | 365 | 08/21/2024 | 10/17/2024 | 58 | 0 | 58 |  |  | 10/23/2024 | Connected |  | N
National Grid | LAWRENCE | 175945 | 01840 | 1000 | Solar | 05_01_406L2 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 177634 | 01826 | 2000 | Solar | 05_01_552L1 | 07/19/2017 | 08/01/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2017 | 08/21/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 | 07/19/2017 | 6/26/2020 | Y | STD | 645 | 10/29/2019 | 05/20/2020 | 202 | 0 | 202 |  |  | 6/26/2020 | Connected |  | N
National Grid | PEPPERELL | 639442 | 01463 | 5.76 | Solar | 05_01_8W1 | 09/11/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/11/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | OXFORD | 177977 | 01540 | 480 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 19 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 11/28/2018 | 11/27/2018 | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | SPENCER | 640630 | 01562 | 6.09 | Solar | 05_12_40L1 | 09/16/2024 | 11/15/2024 | 30 | 26 | 4 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AUBURN | 177455 | 01501 | 10 | Solar | 05_14_24L1 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 362 | 10/03/2017 | 10/17/2017 | 9 | 0 | 9 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | FALL RIVER | 378880 | 02720 | 15.2 | Solar | 05_14_56L1 | 08/30/2021 | 08/31/2021 | 1 | 0 | 1 | 09/01/2021 | 09/01/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 175134 | 01966 | 100 | Solar | 05_14_6J5 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2013 | 11/11/2012 | 1/31/2013 | Y | EXP | 169 | 02/06/2014 | 04/14/2014 | 45 | 0 | 45 | 8/5/2013 | 8/5/2013 | 4/24/2014 | Connected |  | N
National Grid | CHELMSFORD | 718161 | 01824 | 11.375 | Solar | 05_14_78L3 | 09/10/2025 | 09/24/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | ANDOVER | 550348 | 01845 | 0 | Solar | 05_01_226L2 | 08/24/2023 | 08/25/2023 | 1 | 0 | 1 | 08/28/2023 | 08/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 | 08/24/2023 | 11/10/2024 | Y | EXP | 365 | 06/04/2024 | 06/03/2024 | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | LAWRENCE | 176363 | 01840 | 7.6 | Solar | 05_01_406L2 | 03/08/2016 | 03/08/2016 | 3 | 3 | 0 | 03/15/2016 | 03/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2016 | 03/08/2016 | 1/15/2018 | Y | EXP | 656 | 05/19/2017 | 06/02/2017 | 9 | 0 | 9 | 8/11/2017 | 8/11/2017 | 8/11/2017 | Connected |  | N
National Grid | DRACUT | 177649 | 01826 | 7.6 | Solar | 05_01_552L1 | 09/27/2017 | 09/27/2017 | 8 | 8 | 0 | 10/10/2017 | 10/10/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2017 |  | 10/2/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 6/29/2018 | Connected |  | N
National Grid | PEPPERELL | 645066 | 01463 | 3.8 | Solar | 05_01_8W1 | 10/04/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | AUBURN | 177976 | 01501 | 960 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 |  |  | 0 | 0 | 0 |  |  | 11/27/2018 | Connected |  | N
National Grid | SPENCER | 663214 | 01562 | 4.55 | Solar | 05_12_40L1 | 12/31/2024 | 01/16/2025 | 6 | 0 | 6 | 01/17/2025 | 01/17/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | WORCESTER | 177491 | 01607 | 330 | Solar | 05_14_24L1 | 12/12/2016 | 12/12/2016 | 3 | 3 | 0 | 01/27/2017 | 01/27/2017 | 0 | 0 | 0 | 03/21/2017 | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 |  | 04/19/2017 | 36 | 36 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 3/20/2019 | N | EXP | 622 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | Connected |  | N
National Grid | FALL RIVER | 473878 | 02720 | 22.8 | Solar | 05_14_56L1 | 11/02/2022 | 11/03/2022 | 1 | 0 | 1 | 11/04/2022 | 11/04/2022 | 325 | 266 | 59 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 178531 | 01966 | 60 | Solar | 05_14_6J5 | 12/05/2017 | 12/05/2017 | 18 | 0 | 18 | 01/02/2018 | 01/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 12/10/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/10/2018 | Connected |  | N
National Grid | CHELMSFORD | 723653 | 01824 | 3.8 | Solar | 05_14_78L9 | 10/03/2025 | 10/13/2025 | 5 | 1 | 4 | 10/14/2025 | 10/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 570251 | 01845 | 6 | Solar | 05_01_226L2 | 12/18/2023 | 01/02/2024 | 9 | 3 | 6 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 | 12/18/2023 | 7/31/2025 | Y | EXP | 535 | 05/24/2024 | 08/28/2024 | 97 | 0 | 97 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 176545 | 01840 | 10 | Solar | 05_01_406L2 | 03/31/2016 | 03/31/2016 | 2 | 2 | 0 | 04/05/2016 | 04/05/2016 | 208 | 0 | 208 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 |  | 4/6/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | DRACUT | 178079 | 01826 | 2199 | Solar | 05_01_552L1 | 05/05/2017 | 08/24/2017 | 76 | 75 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2017 | 09/28/2017 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2018 | 05/05/2017 | 6/6/2025 | Y | STD | 144 | 02/21/2020 | 05/08/2024 | 1539 | 15 | 1524 |  |  | 6/25/2025 | Connected |  | N
National Grid | PEPPERELL | 646909 | 01463 | 7.6 | Solar | 05_01_8W1 | 10/31/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/31/2024 | 1/17/2026 | Y | EXP | 365 | 02/15/2025 | 06/04/2025 | 110 | 0 | 110 |  |  | 6/24/2025 | Connected |  | N
National Grid | AUBURN | 177975 | 01501 | 660 | Solar | 05_05_28W50 | 06/27/2017 | 06/27/2017 | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2017 | 08/29/2017 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2018 | 06/27/2017 | 11/30/2018 | Y | STD | 311 | 09/08/2018 | 11/08/2018 | 61 | 0 | 61 |  |  | 11/27/2018 | Connected |  | N
National Grid | SPENCER | 688401 | 01562 | 4.537 | Solar | 05_12_40L1 | 07/09/2025 | 07/25/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | WORCESTER | 177929 | 01604 | 396 | Solar | 05_14_24L1 | 04/19/2017 | 04/19/2017 | 9 | 8 | 1 | 05/02/2017 | 05/02/2017 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2017 | 04/19/2017 | 2/11/2019 | Y | EXP | 67 |  |  | 0 | 0 | 0 |  |  | 2/11/2019 | Connected |  | N
National Grid | FALL RIVER | 604257 | 02720 | 23 | Solar | 05_14_56L1 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 81 | 56 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2025 | Connected |  | N
National Grid | ROCKPORT | 314998 | 01966 | 7.6 | Solar | 05_14_6J5 | 11/03/2020 | 11/05/2020 | 1 | 0 | 1 | 11/06/2020 | 11/06/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/03/2020 |  | Y | EXP | 365 | 04/14/2021 | 06/30/2021 | 77 | 0 | 77 |  |  | 8/10/2021 | Connected |  | N
National Grid | CHELMSFORD | 731066 | 01824 | 240 | Solar | 05_14_78L9 | 11/10/2025 | 12/09/2025 | 19 | 11 | 8 | 12/10/2025 | 12/10/2025 | 18 | 0 | 18 | 02/18/2026 |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | ANDOVER | 599998 | 01845 | 3.8 | Solar | 05_01_226L2 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 | 04/01/2024 | 5/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | LAWRENCE | 178498 | 01840 | 276.4 | Solar | 05_01_406L2 | 01/23/2018 | 02/22/2018 | 0 | 0 | 0 | 02/22/2018 | 02/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 |  | 12/31/2019 | N | EXP | 54 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | DRACUT | 178481 | 01826 | 5000 | Solar | 05_01_552L1 | 04/03/2018 | 04/03/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 651778 | 01463 | 10 | Solar | 05_01_8W1 | 11/13/2024 | 03/06/2025 | 59 | 53 | 6 | 03/07/2025 | 03/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 5/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | AUBURN | 369869 | 01501 | 66.6 | Solar | 05_05_28W50 | 07/22/2021 | 01/04/2022 | 7 | 0 | 7 | 08/02/2021 | 08/02/2021 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2021 |  | 10/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | SPENCER | 622085 | 01562 | 60 | Solar | 05_12_49W2 | 07/08/2024 | 12/12/2024 | 108 | 100 | 8 | 12/13/2024 | 12/13/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 184582 | 01607 | 233.1 | Solar | 05_14_24L1 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/31/2018 | 05/31/2018 | 339 | 66 | 273 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 659758 | 02720 | 23 | Solar | 05_14_56L1 | 12/10/2024 | 12/12/2024 | 2 | 0 | 2 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROCKPORT | 633921 | 01966 | 10 | Solar | 05_14_6J5 | 08/20/2024 | 08/30/2024 | 6 | 0 | 6 | 09/03/2024 | 09/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/20/2024 | 9/17/2025 | Y | EXP | 365 | 12/11/2024 | 02/25/2025 | 77 | 0 | 77 |  |  | 2/28/2025 | Connected |  | N
National Grid | CHELMSFORD | 730658 | 01824 | 11.5 | Solar | 05_14_78L9 | 10/31/2025 | 11/03/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 615849 | 01845 | 3.8 | Solar | 05_01_226L2 | 06/05/2024 | 06/06/2024 | 2 | 0 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2024 | 06/05/2024 | 1/21/2026 | Y | EXP | 365 | 03/06/2025 |  | 366 | 0 | 366 |  |  | 3/18/2025 | Connected |  | N
National Grid | LAWRENCE | 191422 | 01841 | 10 | Solar | 05_01_406L2 | 08/04/2018 | 09/13/2018 | 3 | 3 | 0 | 09/14/2018 | 09/14/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 08/04/2018 | 6/28/2019 | Y | EXP | 275 | 03/26/2019 | 04/01/2019 | 6 | 0 | 6 |  |  | 6/24/2019 | Connected |  | N
National Grid | DRACUT | 178736 | 01826 | 7.6 | Solar | 05_01_552L1 | 02/12/2018 | 03/15/2018 | 0 | 0 | 0 | 03/15/2018 | 03/15/2018 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 2/18/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 684478 | 01463 | 10 | Solar | 05_01_8W1 | 04/11/2025 | 05/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 | 04/11/2025 | 7/30/2026 | Y | EXP | 365 | 10/18/2025 | 10/30/2025 | 13 | 0 | 13 |  |  | 11/26/2025 | Connected |  | N
National Grid | AUBURN | 397063 | 01501 | 1750 | Solar | 05_05_28W50 | 03/14/2022 |  | 162 | 153 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 644663 | 01562 | 10 | Solar | 05_12_49W2 | 10/03/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WORCESTER | 185021 | 01604 | 3.8 | Solar | 05_14_24L1 | 05/10/2018 | 05/10/2018 | 4 | 0 | 4 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 661777 | 02720 | 5.76 | Solar | 05_14_56L1 | 12/19/2024 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 643271 | 01970 | 10 | Solar | 05_14_6J5 | 09/27/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2025 | Connected |  | N
National Grid | CHELMSFORD | 749121 | 01824 | 10 | Solar | 05_14_78L9 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 619525 | 01845 | 7.6 | Solar | 05_01_226L2 | 06/20/2024 | 06/25/2024 | 3 | 1 | 2 | 10/29/2024 | 10/29/2024 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 320744 | 01841 | 10 | Solar | 05_01_406L2 | 11/23/2020 | 01/07/2022 | 1 | 0 | 1 | 11/27/2020 | 11/27/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/23/2020 | 10/10/2022 | Y | EXP | 365 | 01/18/2022 | 03/04/2022 | 46 | 0 | 46 |  |  | 3/30/2022 | Connected |  | Y
National Grid | DRACUT | 178773 | 01826 | 1980 | Solar | 05_01_552L1 | 04/29/2013 | 04/29/2013 | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2013 | 07/22/2013 | 25 | 17 | 8 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 5/21/2014 | 04/29/2013 | 12/31/2016 | Y | STD | 955 | 06/24/2016 | 09/27/2016 | 65 | 0 | 65 | 10/26/2016 | 10/26/2016 | 10/28/2016 | Connected |  | N
National Grid | PEPPERELL | 684348 | 01463 | 3.19 | Solar | 05_01_8W1 | 04/10/2025 | 05/02/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | N
National Grid | AUBURN | 455939 | 01501 | 196.175 | Solar | 05_05_28W50 | 09/02/2022 | 10/04/2022 | 22 | 13 | 9 |  |  | 24 | 7 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 674332 | 01562 | 450 | Solar | 05_12_49W2 | 06/10/2025 | 09/11/2025 | 63 | 54 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2025 | 12/03/2025 | 56 | 37 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WORCESTER | 243846 | 01607 | 0 | Solar | 05_14_24L1 | 07/24/2019 | 07/30/2019 | 3 | 0 | 3 | 07/31/2019 | 07/31/2019 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 07/24/2019 | 7/24/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2020 | Connected |  | N
National Grid | FALL RIVER | 693032 | 02720 | 13.05 | Solar | 05_14_56L1 | 05/20/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/5/2025 | Connected |  | N
National Grid | SALEM | 648222 | 01970 | 10 | Solar | 05_14_6J5 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/30/2024 | 1/3/2026 | Y | EXP | 365 | 04/15/2025 | 05/06/2025 | 22 | 0 | 22 |  |  | 5/23/2025 | Connected |  | N
National Grid | CHELMSFORD | 175382 | 01824 | 18 | Solar | 05_14_78L9 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2014 |  | 9/30/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 9/12/2014 | 9/12/2014 | 10/31/2014 | Connected |  | N
National Grid | ANDOVER | 629731 | 01845 | 10 | Solar | 05_01_226L2 | 08/02/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/02/2024 | 9/11/2025 | Y | EXP | 365 | 10/24/2024 | 11/08/2024 | 16 | 0 | 16 |  |  | 12/21/2024 | Connected |  | N
National Grid | LAWRENCE | 359795 | 01841 | 9.6 | Solar | 05_01_406L2 | 05/21/2021 | 05/24/2021 | 0 | 0 | 0 | 05/25/2021 | 05/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2021 | Connected |  | N
National Grid | DRACUT | 184382 | 01826 | 7.6 | Solar | 05_01_552L1 | 05/02/2018 | 05/02/2018 | 2 | 0 | 2 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 684730 | 01463 | 3.8 | Solar | 05_01_8W1 | 04/11/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | AUBURN | 487714 | 01501 | 3.8 | Solar | 05_05_28W50 | 01/23/2023 | 01/24/2023 | 1 | 0 | 1 | 01/25/2023 | 01/25/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2023 |  | 3/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2023 | Connected |  | N
National Grid | CHARLTON | 730129 | 01507 | 60 | Solar | 05_12_49W2 | 11/10/2025 | 12/24/2025 | 30 | 22 | 8 | 12/26/2025 | 12/26/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 255612 | 01607 | 3.8 | Solar | 05_14_24L1 | 09/23/2019 | 09/24/2019 | 0 | 0 | 0 | 09/25/2019 | 09/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2019 | 09/23/2019 | 5/19/2020 | Y | EXP | 236 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 3/31/2020 | Connected |  | N
National Grid | FALL RIVER | 704185 | 02720 | 15.76 | Solar | 05_14_56L1 | 07/16/2025 | 07/18/2025 | 2 | 0 | 2 | 07/21/2025 | 07/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  | 9/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | SALEM | 660639 | 01970 | 7.6 | Solar | 05_14_6J5 | 12/13/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | CHELMSFORD | 175670 | 01824 | 7.6 | Solar | 05_14_78L9 | 10/21/2014 | 10/21/2014 | 6 | 0 | 6 | 10/30/2014 | 10/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 | 10/21/2014 | 12/31/2016 | Y | EXP | 766 | 06/24/2016 | 06/24/2016 | 0 | 0 | 0 | 2/26/2015 | 2/26/2015 | 8/17/2016 | Connected |  | N
National Grid | ANDOVER | 644163 | 01845 | 5.76 | Solar | 05_01_226L2 | 10/01/2024 | 10/28/2024 | 4 | 1 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/01/2024 | 12/19/2025 | Y | EXP | 365 | 01/16/2025 | 02/11/2025 | 27 | 0 | 27 |  |  | 2/19/2025 | Connected |  | N
National Grid | LAWRENCE | 395838 | 01841 | 9.8 | Solar | 05_01_406L2 | 11/22/2021 | 11/23/2021 | 1 | 0 | 1 | 11/24/2021 | 11/24/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/22/2021 | 6/7/2023 | Y | EXP | 365 | 04/23/2022 | 06/07/2022 | 46 | 0 | 46 |  |  | 6/9/2022 | Connected |  | N
National Grid | DRACUT | 189203 | 01826 | 3.8 | Solar | 05_01_552L1 | 06/26/2018 | 06/26/2018 | 24 | 0 | 24 | 08/15/2018 | 08/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 611947 | 01463 | 240 | Solar | 05_01_8W2 | 06/03/2024 | 08/13/2024 | 49 | 25 | 24 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AUBURN | 521951 | 01501 | 6 | Solar | 05_05_28W50 | 05/03/2023 | 05/05/2023 | 2 | 0 | 2 | 05/08/2023 | 05/08/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 7/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 174825 | 01562 | 164 | Solar | 05_12_49W2 | 07/20/2011 | 07/20/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/24/2012 | N | EXP | 27 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 4/24/2012 | Connected |  | N
National Grid | WORCESTER | 257941 | 01607 | 10 | Solar | 05_14_24L1 | 10/08/2019 | 10/15/2019 | 3 | 0 | 3 | 10/16/2019 | 10/16/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2019 | 10/08/2019 | 10/8/2020 | Y | EXP | 365 | 03/10/2020 | 03/11/2020 | 1 | 0 | 1 |  |  | 5/15/2020 | Connected |  | N
National Grid | FALL RIVER | 688268 | 02720 | 20 | Solar | 05_14_56L2 | 05/01/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SALEM | 664939 | 01970 | 5.76 | Solar | 05_14_6J5 | 01/10/2025 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2025 | 01/10/2025 | 3/11/2026 | Y | EXP | 365 | 04/29/2025 | 05/06/2025 | 8 | 0 | 8 |  |  | 6/17/2025 | Connected |  | Y
National Grid | CHELMSFORD | 176654 | 01824 | 7.6 | Solar | 05_14_78L9 | 04/15/2016 | 04/15/2016 | 1 | 1 | 0 | 04/20/2016 | 04/20/2016 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 4/24/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 648356 | 01845 | 3.8 | Solar | 05_01_226L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | LAWRENCE | 402308 | 01841 | 9.8 | Solar | 05_01_406L2 | 01/24/2022 | 02/01/2022 | 6 | 0 | 6 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 | 01/24/2022 | 8/17/2023 | Y | EXP | 365 | 07/15/2022 | 08/16/2022 | 33 | 0 | 33 |  |  | 9/1/2022 | Connected |  | N
National Grid | DRACUT | 189663 | 01826 | 15.2 | Solar | 05_01_552L1 | 06/29/2018 | 06/29/2018 | 8 | 7 | 1 | 07/13/2018 | 07/13/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 728191 | 01463 | 10 | Solar | 05_01_8W2 | 10/22/2025 | 12/19/2025 | 2 | 0 | 2 | 12/31/2025 | 12/31/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | AUBURN | 537229 | 01501 | 4.93 | Solar | 05_05_28W50 | 08/21/2023 | 08/29/2023 | 7 | 6 | 1 | 08/30/2023 | 08/30/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 175188 | 01562 | 18 | Solar | 05_12_49W2 | 11/19/2013 | 11/19/2013 | 4 | 0 | 4 | 11/26/2013 | 11/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 1/31/2014 | N | EXP | 5 |  |  | 0 | 0 | 0 | 12/17/2013 | 12/17/2013 | 8/1/2014 | Connected |  | N
National Grid | MILLBURY | 415288 | 01527 | 11.4 | Solar | 05_14_24L1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 4/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2022 | Connected |  | N
National Grid | FALL RIVER | 733362 | 02720 | 20 | Solar | 05_14_56L2 | 11/12/2025 | 11/18/2025 | 4 | 0 | 4 | 11/19/2025 | 11/19/2025 | 57 | 41 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SALEM | 177071 | 01970 | 90 | Solar | 05_14_6J6 | 07/29/2016 | 07/29/2016 | 0 | 0 | 0 | 08/02/2016 | 08/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2016 |  | 8/7/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 4/25/2017 | 4/25/2017 | 4/25/2017 | Connected |  | N
National Grid | CHELMSFORD | 176709 | 01824 | 3.8 | Solar | 05_14_78L9 | 10/28/2015 | 10/28/2015 | 3 | 3 | 0 | 11/03/2015 | 11/03/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 |  | 11/3/2016 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 650386 | 01845 | 8.45 | Solar | 05_01_226L2 | 10/29/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/29/2024 | 1/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | LAWRENCE | 414703 | 01841 | 9.86 | Solar | 05_01_406L2 | 02/28/2022 | 03/11/2022 | 9 | 8 | 1 | 03/14/2022 | 03/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 | 02/28/2022 | 8/27/2023 | Y | EXP | 365 | 07/16/2022 | 08/26/2022 | 42 | 0 | 42 |  |  | 3/9/2023 | Connected |  | N
National Grid | DRACUT | 189868 | 01826 | 4800 | Solar | 05_01_552L1 | 09/10/2018 | 10/18/2018 | 26 | 17 | 9 |  |  | 33 | 14 | 19 |  |  | 0 | 0 | 0 | 10/19/2018 | 12/08/2018 | 33 | 14 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 734507 | 01463 | 3.8 | Solar | 05_01_8W2 | 11/18/2025 | 11/19/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  | 3/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 582560 | 01501 | 20 | Battery Add-On | 05_05_28W50 | 01/10/2024 | 01/22/2024 | 7 | 4 | 3 | 04/11/2024 | 04/11/2024 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 6/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2024 | Connected |  | N
National Grid | SPENCER | 177361 | 01562 | 75 | Natural Gas | 05_12_49W2 | 06/22/2016 | 06/22/2016 | 18 | 18 | 0 | 07/20/2016 | 07/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2016 |  | 6/28/2017 | N | EXP | 289 |  |  | 0 | 0 | 0 | 11/17/2016 | 11/17/2016 | 12/7/2016 | Connected |  | N
National Grid | WORCESTER | 426459 | 01607 | 15.2 | Solar | 05_14_24L1 | 05/23/2022 | 06/10/2022 | 14 | 13 | 1 | 06/13/2022 | 06/13/2022 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2022 | 05/23/2022 | 11/14/2023 | Y | EXP | 365 | 10/19/2022 | 11/14/2022 | 27 | 0 | 27 |  |  | 12/15/2022 | Connected |  | N
National Grid | FALL RIVER | 735129 | 02720 | 15.04 | Solar | 05_14_56L2 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SALEM | 600180 | 01970 | 6 | Solar | 05_14_6J6 | 04/06/2024 | 04/09/2024 | 2 | 0 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2024 | Connected |  | N
National Grid | CHELMSFORD | 177476 | 01824 | 10 | Solar | 05_14_78L9 | 07/06/2016 | 07/06/2016 | 1 | 1 | 0 | 07/08/2016 | 07/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 07/06/2016 | 12/12/2017 | Y | EXP | 511 | 05/16/2017 | 06/05/2017 | 13 | 0 | 13 | 7/28/2017 | 7/28/2017 | 7/28/2017 | Connected |  | N
National Grid | ANDOVER | 651609 | 01845 | 10 | Solar | 05_01_226L2 | 11/13/2024 | 12/13/2024 | 2 | 0 | 2 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/13/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | LAWRENCE | 473720 | 01841 | 5.76 | Solar | 05_01_406L2 | 12/08/2022 | 12/12/2022 | 2 | 0 | 2 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 | 12/08/2022 | 4/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2023 | Connected |  | N
National Grid | DRACUT | 195817 | 01826 | 0 | Solar | 05_01_552L1 | 11/07/2018 |  | 151 | 25 | 126 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 741842 | 01463 | 10 | Solar | 05_01_8W2 | 12/25/2025 | 12/30/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AUBURN | 614273 | 01501 | 3.8 | Solar | 05_05_28W50 | 05/30/2024 | 06/05/2024 | 0 | 0 | 0 | 06/06/2024 | 06/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 | 05/30/2024 | 11/30/2025 | Y | EXP | 365 | 07/26/2024 | 09/03/2024 | 40 | 0 | 40 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 186726 | 01535 | 88 | Solar | 05_12_49W2 | 05/31/2018 | 05/31/2018 | 0 | 0 | 0 | 06/04/2018 | 06/04/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 5/26/2020 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  | 6/9/2020 | Connected |  | N
National Grid | WORCESTER | 439488 | 01607 | 5.76 | Solar | 05_14_24L1 | 06/29/2022 | 07/01/2022 | 2 | 0 | 2 | 07/05/2022 | 07/05/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 744768 | 02720 | 0 | Solar | 05_14_56L2 | 02/09/2026 | 02/10/2026 | 1 | 0 | 1 | 02/11/2026 | 02/11/2026 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALEM | 646983 | 01970 | 7.6 | Solar | 05_14_6J6 | 11/22/2024 | 12/12/2024 | 3 | 0 | 3 | 12/13/2024 | 12/13/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/22/2024 | 1/28/2026 | Y | EXP | 365 | 08/26/2025 | 09/17/2025 | 23 | 0 | 23 |  |  | 9/23/2025 | Connected |  | N
National Grid | CHELMSFORD | 177689 | 01824 | 100 | Solar | 05_14_78L9 | 10/03/2017 | 10/03/2017 | 2 | 2 | 0 | 10/27/2017 | 10/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2017 |  | 10/8/2018 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | ANDOVER | 653239 | 01845 | 10 | Solar | 05_01_226L2 | 11/14/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 564813 | 01841 | 7.6 | Solar | 05_01_406L2 | 10/24/2023 | 11/07/2023 | 11 | 10 | 1 | 11/08/2023 | 11/08/2023 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 | 10/24/2023 | 2/2/2025 | Y | EXP | 365 | 05/02/2024 | 09/07/2024 | 129 | 0 | 129 |  |  | 10/8/2024 | Connected |  | N
National Grid | DRACUT | 193213 | 01826 | 2988 | Solar | 05_01_552L1 | 01/09/2019 | 01/30/2019 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2019 | 02/27/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 174185 | 01463 | 91.2 | Solar | 05_01_8W2 | 10/23/2011 | 10/23/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2012 | 10/23/2011 | 5/1/2012 | Y | EXP | 62 | 10/05/2012 | 01/15/2013 | 52 | 0 | 52 | 6/20/2012 | 6/20/2012 | 4/24/2013 | Connected |  | N
National Grid | AUBURN | 619689 | 01501 | 7.6 | Solar | 05_05_28W50 | 06/21/2024 | 07/05/2024 | 6 | 2 | 4 | 07/08/2024 | 07/08/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/21/2024 | 7/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2024 | Connected |  | N
National Grid | SPENCER | 194178 | 01562 | 146 | Solar | 05_12_49W2 | 08/24/2018 | 08/29/2018 | 0 | 0 | 0 | 08/30/2018 | 08/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 5/26/2020 | N | EXP | 417 |  |  | 0 | 0 | 0 |  |  | 7/27/2020 | Connected |  | N
National Grid | WORCESTER | 475619 | 01607 | 100 | Solar | 05_14_24L1 | 11/08/2022 | 12/12/2022 | 23 | 13 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174365 | 02720 | 7.5 | Solar | 05_14_56L2 | 05/21/2012 | 05/21/2012 | 8 | 0 | 8 | 06/05/2012 | 06/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2012 | 05/21/2012 | 8/1/2012 | Y | EXP | 16 | 10/04/2012 | 11/19/2012 | 15 | 0 | 15 | 11/15/2012 | 11/15/2012 | 11/15/2012 | Connected |  | N
National Grid | SALEM | 500858 | 01970 | 60 | Solar | 05_14_6J8 | 02/24/2023 |  | 257 | 163 | 94 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 353172 | 01824 | 3.8 | Solar | 05_14_78L9 | 05/06/2021 | 05/12/2021 | 3 | 0 | 3 | 05/13/2021 | 05/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 654523 | 01845 | 23 | Battery Add-On | 05_01_226L2 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | LAWRENCE | 590501 | 01841 | 5.8 | Solar | 05_01_406L2 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2024 |  | 3/13/2026 | N | EXP | 465 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | DRACUT | 208846 | 01826 | 6 | Solar | 05_01_552L1 | 03/26/2019 |  | 69 | 26 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 174739 | 01463 | 300 | Solar | 05_01_8W2 | 01/15/2013 | 01/15/2013 | 6 | 0 | 6 | 01/25/2013 | 01/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2013 |  | 6/28/2013 | N | EXP | 99 |  |  | 0 | 0 | 0 | 3/26/2013 | 3/26/2013 | 8/20/2013 | Connected |  | N
National Grid | AUBURN | 620166 | 01501 | 7.6 | Solar | 05_05_28W50 | 06/24/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 |  | 8/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | SPENCER | 290730 | 01562 | 100 | Solar | 05_12_49W2 | 05/26/2020 | 06/16/2020 | 15 | 12 | 3 | 06/17/2020 | 06/17/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2020 |  | 8/10/2022 | N | EXP | 625 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | WORCESTER | 511233 | 01607 | 0 | Solar | 05_14_24L1 | 03/15/2023 | 09/28/2023 | 135 | 132 | 3 | 09/29/2023 | 09/29/2023 | 98 | 65 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 175130 | 02720 | 12 | Solar | 05_14_56L2 | 11/02/2012 | 11/02/2012 | 1 | 0 | 1 | 11/20/2012 | 11/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2013 |  | 2/15/2013 | N | EXP | 4 |  |  | 0 | 0 | 0 | 2/19/2013 | 2/19/2013 | 5/7/2013 | Connected |  | N
National Grid | SALEM | 550550 | 01970 | 200 | Solar | 05_14_6J8 | 08/25/2023 | 09/08/2023 | 9 | 1 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 | 08/25/2023 | 6/1/2026 | Y | STD | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 557592 | 01824 | 7.6 | Solar | 05_14_78L9 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 654994 | 01845 | 5.76 | Solar | 05_01_226L2 | 12/02/2024 | 01/01/2025 | 10 | 4 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/02/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 614107 | 01841 | 7.6 | Solar | 05_01_406L2 | 05/30/2024 | 06/12/2024 | 2 | 0 | 2 | 06/13/2024 | 06/13/2024 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2024 |  | 7/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | DRACUT | 220677 | 01826 | 5.12 | Solar | 05_01_552L1 | 05/20/2019 | 08/27/2019 | 68 | 67 | 1 | 08/28/2019 | 08/28/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 174946 | 01463 | 142 | Solar | 05_01_8W2 | 09/24/2012 | 09/24/2012 | 7 | 0 | 7 | 10/04/2012 | 10/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2013 |  | 12/3/2012 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/15/2013 | 1/15/2013 | 2/8/2013 | Connected |  | N
National Grid | AUBURN | 646203 | 01501 | 3.839 | Solar | 05_05_28W50 | 10/10/2024 | 11/06/2024 | 15 | 10 | 5 | 11/07/2024 | 11/07/2024 | 73 | 50 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 291146 | 01562 | 7.54 | Solar | 05_12_49W2 | 05/11/2020 | 05/12/2020 | 0 | 0 | 0 | 05/13/2020 | 05/13/2020 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2020 | 05/11/2020 | 5/11/2021 | Y | EXP | 365 | 09/11/2020 | 09/22/2020 | 11 | 0 | 11 |  |  | 11/18/2020 | Connected |  | N
National Grid | MILLBURY | 532374 | 01527 | 9.765 | Solar | 05_14_24L1 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 21 | 0 | 21 | 08/04/2023 | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 08/24/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 11/29/2024 | N | EXP | 365 | 02/02/2024 | 04/26/2024 | 85 | 0 | 85 |  |  | 5/3/2024 | Connected |  | N
National Grid | FALL RIVER | 177954 | 02720 | 20 | Solar | 05_14_56L2 | 10/23/2017 | 10/23/2017 | 101 | 100 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 579731 | 01970 | 7.6 | Solar | 05_14_6J8 | 12/29/2023 | 01/16/2024 | 11 | 8 | 3 | 01/17/2024 | 01/17/2024 | 33 | 12 | 21 | 04/24/2024 | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 05/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 5/9/2025 | N | EXP | 365 | 05/16/2024 | 06/12/2024 | 28 | 0 | 28 |  |  | 7/6/2024 | Connected |  | N
National Grid | CHELMSFORD | 537415 | 01824 | 8.064 | Solar | 05_14_78L9 | 07/07/2023 | 09/19/2023 | 51 | 50 | 1 | 09/20/2023 | 09/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 | 07/07/2023 | 1/22/2025 | Y | EXP | 365 | 03/14/2024 | 05/15/2024 | 63 | 0 | 63 |  |  | 5/23/2024 | Connected |  | N
National Grid | ANDOVER | 660803 | 01845 | 5.76 | Solar | 05_01_226L2 | 12/18/2024 | 02/11/2025 | 22 | 18 | 4 | 02/12/2025 | 02/12/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 621138 | 01841 | 3.8 | Solar | 05_01_406L2 | 06/27/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2024 | Connected |  | N
National Grid | DRACUT | 231646 | 01826 | 6.4 | Solar | 05_01_552L1 | 07/02/2019 | 07/17/2019 | 10 | 10 | 0 | 07/18/2019 | 07/18/2019 | 53 | 45 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2019 |  | 7/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2020 | Connected |  | N
National Grid | PEPPERELL | 175176 | 01463 | 18 | Solar | 05_01_8W2 | 04/30/2013 | 04/30/2013 | 7 | 1 | 6 | 05/10/2013 | 05/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 |  | 7/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/25/2013 | Connected |  | N
National Grid | AUBURN | 651174 | 01501 | 7.6 | Solar | 05_05_28W50 | 11/11/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 11/11/2024 | 2/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2025 | Connected |  | N
National Grid | SPENCER | 292831 | 01562 | 100 | Solar | 05_12_49W2 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 256 | 26 | 230 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLBURY | 642866 | 01527 | 8.45 | Solar | 05_14_24L1 | 09/25/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 12/2/2025 | Y | EXP | 365 | 01/04/2025 | 01/24/2025 | 21 | 0 | 21 |  |  | 2/3/2025 | Connected |  | N
National Grid | FALL RIVER | 178069 | 02720 | 20 | Solar | 05_14_56L2 | 10/30/2017 | 10/30/2017 | 66 | 66 | 0 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 11/5/2018 | N | EXP | 265 |  |  | 0 | 0 | 0 |  |  | 10/16/2018 | Connected |  | N
National Grid | SALEM | 594507 | 01970 | 3.8 | Solar | 05_14_6J8 | 03/07/2024 | 03/12/2024 | 3 | 0 | 3 | 03/13/2024 | 03/13/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 596726 | 01824 | 10 | Solar | 05_14_78L9 | 04/15/2024 | 04/19/2024 | 5 | 4 | 1 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 04/15/2024 | 6/15/2025 | Y | EXP | 365 | 08/01/2024 | 09/12/2024 | 43 | 0 | 43 |  |  | 10/17/2024 | Connected |  | N
National Grid | ANDOVER | 676260 | 01845 | 7.6 | Solar | 05_01_226L2 | 03/07/2025 |  | 76 | 73 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 668558 | 01841 | 7.6 | Solar | 05_01_406L2 | 01/29/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/14/2026 | Y | EXP | 365 | 07/08/2025 | 12/04/2025 | 150 | 0 | 150 |  |  | 12/24/2025 | Connected |  | N
National Grid | DRACUT | 234351 | 01826 | 10 | Solar | 05_01_552L1 | 07/16/2019 | 07/25/2019 | 7 | 7 | 0 | 07/26/2019 | 07/26/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2020 | Connected |  | N
National Grid | PEPPERELL | 176546 | 01463 | 1992 | Solar | 05_01_8W2 | 04/03/2016 | 04/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2016 | 05/09/2016 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 | 04/03/2016 | 11/14/2018 | Y | STD | 87 |  |  | 0 | 0 | 0 |  |  | 11/14/2018 | Connected |  | N
National Grid | AUBURN | 657561 | 01501 | 5.76 | Solar | 05_05_28W50 | 11/28/2024 | 01/15/2025 | 20 | 16 | 4 | 01/16/2025 | 01/16/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 11/28/2024 | 3/11/2026 | Y | EXP | 365 | 03/20/2025 | 05/29/2025 | 71 | 0 | 71 |  |  | 7/30/2025 | Connected |  | N
National Grid | SPENCER | 371169 | 01562 | 100 | Solar | 05_12_49W2 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2022 | 07/21/2021 | 12/28/2022 | Y | STD | 61 |  |  | 0 | 0 | 0 |  |  | 12/30/2022 | Connected |  | N
National Grid | WORCESTER | 657505 | 01607 | 7.6 | Solar | 05_14_24L1 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 189257 | 02720 | 15.2 | Solar | 05_14_56L2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 06/28/2018 | 06/28/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 637388 | 01970 | 7.6 | Solar | 05_14_6J8 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 647856 | 01824 | 7.6 | Solar | 05_14_78L9 | 10/17/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 684274 | 01845 | 7.6 | Solar | 05_01_226L2 | 04/14/2025 | 04/25/2025 | 8 | 5 | 3 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 678760 | 01841 | 7.6 | Solar | 05_01_406L2 | 03/18/2025 | 05/02/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 | 03/18/2025 | 7/30/2026 | Y | EXP | 365 | 10/30/2025 | 12/02/2025 | 34 | 0 | 34 |  |  | 12/4/2025 | Connected |  | N
National Grid | DRACUT | 256903 | 01826 | 10 | Solar | 05_01_552L1 | 10/09/2019 | 10/11/2019 | 1 | 1 | 0 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2019 | 10/09/2019 | 10/9/2020 | Y | EXP | 365 | 02/05/2020 | 03/02/2020 | 26 | 0 | 26 |  |  | 4/22/2020 | Connected |  | N
National Grid | PEPPERELL | 177041 | 01463 | 4400 | Solar | 05_01_8W2 | 10/18/2016 | 10/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 |  | 10/23/2016 | N | STD | 3 |  |  | 0 | 0 | 0 | 10/26/2016 | 10/26/2016 | 10/26/2016 | Connected |  | N
National Grid | AUBURN | 662945 | 01501 | 6 | Solar | 05_05_28W50 | 12/30/2024 | 04/09/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | SPENCER | 488516 | 01562 | 80 | Solar | 05_12_49W2 | 12/29/2022 | 01/23/2023 | 15 | 6 | 9 | 01/24/2023 | 01/24/2023 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 |  | 3/24/2025 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | Y
National Grid | WORCESTER | 685057 | 01607 | 10 | Solar | 05_14_24L1 | 04/17/2025 |  | 120 | 25 | 95 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 284143 | 02720 | 12 | Solar | 05_14_56L2 | 03/17/2020 | 04/06/2020 | 13 | 13 | 0 | 04/07/2020 | 04/07/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  | 4/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | SALEM | 673283 | 01970 | 6.825 | Solar | 05_14_6J8 | 02/20/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | CHELMSFORD | 655530 | 01824 | 3.8 | Solar | 05_14_78L9 | 11/19/2024 | 01/14/2025 | 5 | 0 | 5 | 01/15/2025 | 01/15/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 11/19/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | ANDOVER | 686777 | 01845 | 19 | Solar | 05_01_226L2 | 04/23/2025 | 05/01/2025 | 6 | 2 | 4 | 05/02/2025 | 05/02/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 706259 | 01844 | 15.2 | Solar | 05_01_406L2 | 07/22/2025 | 07/25/2025 | 3 | 0 | 3 | 07/28/2025 | 07/28/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | DRACUT | 265279 | 01826 | 0 | Other | 05_01_552L1 | 02/24/2020 | 03/17/2020 | 15 | 11 | 4 |  |  | 6 | 6 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 177204 | 01463 | 299.8 | Solar | 05_01_8W2 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 713232 | 01501 | 20 | Solar | 05_05_28W50 | 08/19/2025 | 08/26/2025 | 5 | 0 | 5 | 08/27/2025 | 08/27/2025 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2025 | Connected |  | N
National Grid | SPENCER | 511480 | 01562 | 15.2 | Solar | 05_12_49W2 | 03/22/2023 | 03/23/2023 | 1 | 0 | 1 | 03/24/2023 | 03/24/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 03/22/2023 | 4/26/2024 | Y | EXP | 365 | 07/28/2023 | 08/09/2023 | 13 | 0 | 13 |  |  | 8/14/2023 | Connected |  | N
National Grid | WORCESTER | 686019 | 01602 | 20 | Solar | 05_14_24L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | FALL RIVER | 284117 | 02720 | 11.4 | Solar | 05_14_56L2 | 03/17/2020 |  | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 547089 | 01970 | 240 | Solar | 05_14_70L1 | 12/12/2023 | 02/05/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/06/2024 | 02/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 | 12/12/2023 | 7/21/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | CHELMSFORD | 661689 | 01824 | 5.76 | Solar | 05_14_78L9 | 12/27/2024 | 01/02/2025 | 3 | 0 | 3 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/27/2024 | 2/28/2026 | Y | EXP | 365 | 10/02/2025 | 10/29/2025 | 28 | 0 | 28 |  |  | 12/2/2025 | Connected |  | N
National Grid | ANDOVER | 712231 | 01845 | 17.16 | Solar | 05_01_226L2 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 574156 | 01841 | 480 | Solar | 05_01_406L3 | 12/22/2023 | 01/08/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2024 | 02/06/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 264202 | 01826 | 5000 | Other | 05_01_552L1 | 02/12/2020 | 03/16/2020 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2020 | 04/01/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 204126 | 01463 | 313.2 | Solar | 05_01_8W2 | 12/18/2018 | 01/22/2019 | 21 | 17 | 4 | 01/23/2019 | 01/23/2019 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AUBURN | 409703 | 01501 | 0 | Other | 05_05_28W51 | 03/22/2022 | 04/01/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2022 | 04/05/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2025 | 03/22/2022 | 12/1/2026 | Y | STD | 413 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SPENCER | 559364 | 01562 | 5 | Solar | 05_12_49W2 | 10/17/2023 | 10/19/2023 | 2 | 0 | 2 | 10/20/2023 | 10/20/2023 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 1/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2024 | Connected |  | N
National Grid | WORCESTER | 699938 | 01607 | 15.2 | Solar | 05_14_24L1 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/25/2025 | 8/5/2026 | Y | EXP | 365 | 11/04/2025 | 12/02/2025 | 29 | 0 | 29 |  |  | 12/6/2025 | Connected |  | N
National Grid | FALL RIVER | 285219 | 02720 | 23.78 | Solar | 05_14_56L2 | 03/25/2020 | 04/01/2020 | 4 | 0 | 4 | 04/02/2020 | 04/02/2020 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2020 | Connected |  | N
National Grid | SALEM | 727534 | 01970 | 5.8 | Solar | 05_14_70L1 | 10/18/2025 | 10/23/2025 | 4 | 0 | 4 | 10/24/2025 | 10/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 686572 | 01824 | 4.8 | Solar | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | ANDOVER | 716113 | 01845 | 13.36 | Solar | 05_01_226L2 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 693199 | 01876 | 499 | Other | 05_01_406L3 | 09/03/2025 | 10/17/2025 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 | 11/04/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | DRACUT | 281057 | 01826 | 10 | Solar | 05_01_552L1 | 04/06/2020 |  | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 309736 | 01463 | 7.6 | Solar | 05_01_8W2 | 10/02/2020 | 10/06/2020 | 1 | 0 | 1 | 10/07/2020 | 10/07/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 581883 | 01507 | 100 | Solar | 05_05_28W51 | 01/19/2024 | 02/08/2024 | 14 | 3 | 11 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 7/3/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SPENCER | 628651 | 01562 | 3.8 | Solar | 05_12_49W2 | 08/06/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2024 | Connected |  | N
National Grid | WORCESTER | 704907 | 01607 | 7.6 | Solar | 05_14_24L1 | 07/15/2025 | 09/15/2025 | 6 | 1 | 5 | 09/25/2025 | 09/25/2025 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | FALL RIVER | 315160 | 02720 | 15.2 | Solar | 05_14_56L2 | 09/25/2020 | 10/01/2020 | 3 | 0 | 3 | 10/02/2020 | 10/02/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | SALEM | 742796 | 01970 | 5.76 | Solar | 05_14_70L1 | 01/09/2026 | 01/12/2026 | 21 | 20 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHELMSFORD | 686563 | 01824 | 7.6 | Solar | 05_14_78L9 | 04/21/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 50 | 36 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | ANDOVER | 722437 | 01845 | 15.2 | Solar | 05_01_226L2 | 09/26/2025 | 10/06/2025 | 5 | 3 | 2 | 10/07/2025 | 10/07/2025 | 39 | 22 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 1/1/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2026 | Connected |  | N
National Grid | BILLERICA | 705917 | 01862 | 0 | Other | 05_01_406L3 | 02/02/2026 | 03/04/2026 | 21 | 16 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 288064 | 01826 | 0 | Other | 05_01_552L1 | 05/15/2020 | 05/27/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 09/27/2020 | 24 | 20 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEPPERELL | 382570 | 01463 | 350 | Solar | 05_01_8W2 | 11/11/2021 | 12/16/2021 | 24 | 15 | 9 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 174517 | 01540 | 1000 | Solar | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 54 | 12/10/2012 | 12/13/2012 | 3 | 0 | 3 | 10/18/2013 | 10/18/2013 | 2/22/2013 | Connected |  | N
National Grid | SPENCER | 640219 | 01562 | 3.8 | Solar | 05_12_49W2 | 09/13/2024 | 10/04/2024 | 3 | 0 | 3 | 10/07/2024 | 10/07/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/20/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | WORCESTER | 657917 | 01607 | 3.8 | Solar | 05_14_24L2 | 12/02/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 3/17/2026 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | FALL RIVER | 319343 | 02720 | 15.2 | Solar | 05_14_56L2 | 10/14/2020 | 10/15/2020 | 0 | 0 | 0 | 10/16/2020 | 10/16/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 | 10/14/2020 | 10/15/2021 | Y | EXP | 365 | 01/22/2021 | 02/04/2021 | 13 | 0 | 13 |  |  | 6/7/2021 | Connected |  | N
National Grid | SALEM | 751582 | 01970 | 6.282 | Solar | 05_14_70L1 | 02/18/2026 | 03/03/2026 | 8 | 6 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 715946 | 01824 | 6.84 | Solar | 05_14_78L9 | 09/02/2025 | 09/23/2025 | 14 | 9 | 5 | 09/24/2025 | 09/24/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2026 | Connected |  | N
National Grid | ANDOVER | 730024 | 01845 | 1000 | Solar | 05_01_226L2 | 11/03/2025 | 11/20/2025 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 734311 | 01852 | 7.6 | Solar | 05_01_406L3 | 11/20/2025 | 11/26/2025 | 5 | 2 | 3 | 12/18/2025 | 12/18/2025 | 53 | 35 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 330669 | 01826 | 9.8 | Solar | 05_01_552L1 | 12/09/2020 | 12/17/2020 | 5 | 0 | 5 | 12/18/2020 | 12/18/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | PEPPERELL | 644286 | 01463 | 5.76 | Solar | 05_01_8W2 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/01/2024 | 2/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | OXFORD | 174516 | 01540 | 1000 | Solar | 05_05_28W51 | 11/11/2010 | 11/11/2010 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2011 | 02/08/2011 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2011 | 11/11/2010 | 10/31/2012 | Y | STD | 54 | 10/19/2012 | 12/26/2012 | 30 | 0 | 30 | 1/25/2013 | 1/25/2013 | 2/22/2013 | Connected |  | N
National Grid | SPENCER | 647501 | 01562 | 5.76 | Solar | 05_12_49W2 | 10/22/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/22/2024 | 1/6/2026 | Y | EXP | 365 | 02/12/2025 | 03/01/2025 | 18 | 0 | 18 |  |  | 5/2/2025 | Connected |  | N
National Grid | WORCESTER | 711798 | 01607 | 3.8 | Solar | 05_14_24L2 | 08/13/2025 | 09/05/2025 | 4 | 0 | 4 | 09/22/2025 | 09/22/2025 | 82 | 68 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 08/13/2025 | 1/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | FALL RIVER | 327991 | 02720 | 7.6 | Solar | 05_14_56L2 | 11/24/2020 | 12/02/2020 | 4 | 0 | 4 | 12/03/2020 | 12/03/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 11/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2021 | Connected |  | N
National Grid | SALEM | 175483 | 01970 | 4999 | Solar | 05_14_70L1 | 03/14/2014 | 03/14/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2014 | 05/14/2014 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 246224 | 01824 | 7.6 | Solar | 05_14_7J1 | 08/12/2019 | 08/28/2019 | 12 | 11 | 1 | 08/29/2019 | 08/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 |  | 2/26/2020 | N | EXP | 168 |  |  | 0 | 0 | 0 |  |  | 1/28/2020 | Connected |  | N
National Grid | ANDOVER | 582916 | 01845 | 0 | Solar | 05_01_227W1 | 02/06/2024 | 04/10/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2024 | 04/24/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LOWELL | 745318 | 01852 | 7.98 | Solar | 05_01_406L3 | 01/14/2026 | 01/20/2026 | 5 | 1 | 4 | 03/09/2026 | 03/09/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DRACUT | 346050 | 01826 | 11.4 | Solar | 05_01_552L1 | 03/10/2021 | 03/16/2021 | 3 | 0 | 3 | 03/17/2021 | 03/17/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 7/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2021 | Connected |  | N
National Grid | PEPPERELL | 652196 | 01463 | 7.6 | Solar | 05_01_8W2 | 11/14/2024 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | OXFORD | 174534 | 01540 | 950 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 01/27/2012 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 | 10/18/2011 | 10/31/2012 | Y | STD | 142 | 11/04/2013 | 03/18/2014 | 89 | 0 | 89 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | SPENCER | 688394 | 01562 | 15.2 | Solar | 05_12_49W2 | 04/29/2025 | 05/01/2025 | 2 | 0 | 2 | 05/02/2025 | 05/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 725938 | 01607 | 23.034 | Solar | 05_14_24L2 | 10/21/2025 | 10/27/2025 | 4 | 0 | 4 | 10/28/2025 | 10/28/2025 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 335404 | 02720 | 9.36 | Solar | 05_14_56L2 | 01/06/2021 | 01/25/2021 | 12 | 12 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/06/2021 | 1/24/2022 | Y | EXP | 365 | 05/12/2021 | 06/02/2021 | 21 | 0 | 21 |  |  | 7/23/2021 | Connected |  | N
National Grid | SALEM | 175480 | 01970 | 4999 | Solar | 05_14_70L1 | 03/21/2014 | 03/21/2014 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2014 | 05/14/2014 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/21/2014 | 3/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 663217 | 01824 | 11.5 | Solar | 05_14_7J1 | 01/02/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | ANDOVER | 705049 | 01845 | 15.68 | Solar | 05_01_227W1 | 07/15/2025 | 08/07/2025 | 17 | 11 | 6 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 754135 | 01862 | 11.4 | Solar | 05_01_406L3 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 452168 | 01845 | 5 | Solar | 05_01_552L1 | 10/11/2022 | 11/18/2022 | 27 | 24 | 3 | 11/21/2022 | 11/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 709990 | 01523 | 7.98 | Solar | 05_01_8W2 | 08/06/2025 | 09/18/2025 | 9 | 4 | 5 | 09/19/2025 | 09/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | OXFORD | 174541 | 01540 | 475 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 641227 | 01562 | 0 | Other | 05_12_49W4 | 07/12/2025 | 11/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 725617 | 01607 | 7.6 | Solar | 05_14_24L2 | 11/03/2025 | 11/05/2025 | 2 | 0 | 2 | 11/06/2025 | 11/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 347328 | 02720 | 0 | Solar | 05_14_56L2 | 03/17/2021 | 03/18/2021 | 0 | 0 | 0 | 03/19/2021 | 03/19/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/17/2021 | 3/17/2022 | Y | EXP | 365 | 05/26/2021 | 07/13/2021 | 48 | 0 | 48 |  |  | 7/30/2021 | Connected |  | N
National Grid | SALEM | 176006 | 01970 | 7.6 | Solar | 05_14_70L1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/14/2015 | 08/14/2015 | 375 | 0 | 375 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 |  | 8/19/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 176081 | 01824 | 27 | Solar | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 740278 | 01845 | 0 | Battery Add-On | 05_01_227W1 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 174421 | 01862 | 950 | Solar | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | 135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | ANDOVER | 367879 | 01845 | 7.6 | Solar | 05_01_552L1 | 07/22/2021 | 07/29/2021 | 6 | 5 | 1 | 07/30/2021 | 07/30/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 8/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2021 | Connected |  | N
National Grid | SHIRLEY | 657038 | 01464 | 7.6 | Solar | 05_01_9J302 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 3/19/2026 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | OXFORD | 174540 | 01540 | 950 | Solar | 05_05_28W51 | 10/18/2011 | 10/18/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 736316 | 01562 | 7.6 | Solar | 05_14_24L2 | 11/25/2025 | 12/29/2025 | 5 | 3 | 2 | 02/03/2026 | 02/03/2026 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 363866 | 01607 | 9.8 | Solar | 05_14_56L2 | 06/15/2021 | 06/17/2021 | 2 | 0 | 2 | 06/18/2021 | 06/18/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 |  | 8/26/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2022 | Connected |  | N
National Grid | FALL RIVER | 176041 | 02720 | 11.4 | Solar | 05_14_70L1 | 08/14/2015 | 08/14/2015 | 1 | 1 | 0 | 08/18/2015 | 08/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 8/22/2016 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | PEPPERELL | 176110 | 01463 | 27 | Solar | 05_14_7J3 | 08/20/2015 | 08/20/2015 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/26/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 174132 | 01824 | 300 | Solar | 05_01_227W1 | 05/03/2012 | 05/03/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/29/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 174420 | 01845 | 950 | Solar | 05_01_406L3 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/09/2012 | 10/02/2012 | 60 | 0 | 60 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 06/27/2012 | 10/30/2012 | Y | STD | 135 | 08/21/2013 | 01/17/2014 | 101 | 0 | 101 | 11/12/2013 | 11/12/2013 | 12/9/2013 | Connected |  | N
National Grid | TEWKSBURY | 405685 | 01876 | 9.8 | Solar | 05_01_552L1 | 02/03/2022 | 02/07/2022 | 2 | 0 | 2 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 | 02/03/2022 | 5/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | ANDOVER | 689482 | 01845 | 16.64 | Solar | 05_01_9J302 | 05/06/2025 | 05/12/2025 | 4 | 0 | 4 | 05/13/2025 | 05/13/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | LANCASTER | 174614 | 01523 | 2000 | Wind | 05_05_28W51 | 11/30/2010 | 11/30/2010 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2011 |  | 4/20/2012 | N | STD | 23 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 4/20/2012 | Connected |  | N
National Grid | CHARLTON | 683682 | 01507 | 0 | Other | 05_12_49W4 | 12/29/2025 | 03/02/2026 | 40 | 32 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 743169 | 01562 | 10 | Solar | 05_14_24L2 | 01/02/2026 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 385253 | 01604 | 9.8 | Solar | 05_14_56L2 | 09/29/2021 | 10/04/2021 | 4 | 3 | 1 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2022 | Connected |  | N
National Grid | FALL RIVER | 176226 | 02720 | 10 | Solar | 05_14_70L1 | 09/01/2015 | 09/01/2015 | 1 | 1 | 0 | 09/09/2015 | 09/09/2015 | 358 | 0 | 358 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 |  | 9/12/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEPPERELL | 176421 | 01463 | 25 | Solar | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 2/29/2016 | 2/29/2016 | 3/28/2016 | Connected |  | N
National Grid | CHELMSFORD | 174187 | 01824 | 500 | Solar | 05_01_227W1 | 03/12/2012 | 03/12/2012 | 11 | 0 | 11 | 04/05/2012 | 04/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2013 | 03/12/2012 | 6/1/2012 | Y | EXP | 237 | 07/15/2013 | 09/27/2013 | 53 | 0 | 53 | 9/26/2013 | 9/26/2013 | 9/27/2013 | Connected |  | N
National Grid | ANDOVER | 174918 | 01845 | 13.12 | Solar | 05_01_406L3 | 02/26/2013 | 02/26/2013 | 7 | 2 | 5 | 03/13/2013 | 03/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 |  | 5/31/2013 | N | EXP | 7 |  |  | 0 | 0 | 0 | 9/4/2013 | 9/4/2013 | 11/20/2013 | Connected |  | N
National Grid | BILLERICA | 412613 | 01862 | 10 | Solar | 05_01_552L1 | 03/16/2022 | 03/24/2022 | 6 | 1 | 5 | 03/25/2022 | 03/25/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2022 | 03/16/2022 | 6/15/2023 | Y | EXP | 365 | 05/17/2022 | 06/14/2022 | 29 | 0 | 29 |  |  | 8/11/2022 | Connected |  | N
National Grid | ANDOVER | 578629 | 01845 | 299 | Solar | 05_01_9J303 | 01/29/2024 |  | 470 | 25 | 445 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 175108 | 01453 | 1500 | Solar | 05_05_28W51 | 04/22/2013 | 04/22/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2013 | 06/05/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2013 | 04/22/2013 | 9/2/2013 | Y | STD | 73 | 10/03/2014 | 12/08/2014 | 43 | 0 | 43 | 4/22/2013 | 4/22/2013 | 12/18/2014 | Connected |  | N
National Grid | CHARLTON | 290691 | 01507 | 0 | Battery Add-On | 05_12_49W4 | 05/06/2020 | 05/06/2020 | 0 | 0 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2020 | Connected |  | N
National Grid | SPENCER | 753489 | 01562 | 5.76 | Solar | 05_14_24L2 | 02/27/2026 | 03/03/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 396669 | 01604 | 0 | Other | 05_14_56L2 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 03/02/2022 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 176550 | 02720 | 10 | Solar | 05_14_70L1 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 357 | 09/06/2016 | 09/14/2016 | 6 | 0 | 6 | 12/7/2016 | 12/7/2016 | 12/7/2016 | Connected |  | N
National Grid | SALEM | 176450 | 01970 | 27 | Solar | 05_14_7J3 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2015 |  | 12/13/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 3/28/2016 | 3/28/2016 | 3/1/2016 | Connected |  | N
National Grid | CHELMSFORD | 174231 | 01824 | 2000 | Solar | 05_01_227W1 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 6/19/2014 | 6/19/2014 | 6/19/2014 | Connected |  | N
National Grid | ANDOVER | 175066 | 01845 | 1500 | Solar | 05_01_406L3 | 03/28/2013 | 03/28/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/09/2013 | 06/24/2013 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2014 | 03/28/2013 | 5/11/2018 | Y | STD | 1572 |  |  | 0 | 0 | 0 | 4/16/2018 | 4/16/2018 | 5/10/2018 | Connected |  | N
National Grid | TEWKSBURY | 431528 | 01876 | 15.66 | Solar | 05_01_552L1 | 06/29/2022 | 08/01/2022 | 23 | 22 | 1 | 08/02/2022 | 08/02/2022 | 42 | 21 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/24/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | ANDOVER | 595193 | 01845 | 7.6 | Solar | 05_01_9J303 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 8 | 0 | 8 | 04/23/2024 | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 05/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/15/2025 | N | EXP | 365 | 05/16/2024 | 05/15/2024 | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | LANCASTER | 175675 | 01523 | 500 | Solar | 05_05_28W51 | 10/21/2014 | 10/21/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 11/26/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2015 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 | 1/26/2018 | 1/26/2018 |  | Withdrawn |  | N
National Grid | OXFORD | 357389 | 01540 | 200 | Solar | 05_12_49W4 | 05/28/2021 | 03/18/2022 | 202 | 186 | 16 | 03/21/2022 | 03/21/2022 | 35 | 14 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2022 | 05/28/2021 | 11/25/2023 | Y | EXP | 28 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | SPENCER | 174747 | 01562 | 225 | Solar | 05_14_24L2 | 07/09/2013 | 07/09/2013 | 19 | 11 | 8 | 08/06/2013 | 08/06/2013 | 407 | 1 | 406 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2013 |  | 8/1/2014 | N | EXP | 347 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177569 | 01604 | 15.2 | Solar | 05_14_70L1 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 6/7/2018 | Connected |  | N
National Grid | FALL RIVER | 177511 | 02720 | 27 | Solar | 05_14_7J3 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 | 07/12/2016 | 07/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2016 |  | 7/17/2017 | N | EXP | 37 |  |  | 0 | 0 | 0 | 7/12/2016 | 7/12/2016 | 7/25/2016 | Connected |  | N
National Grid | SALEM | 174595 | 01970 | 82 | Solar | 05_01_227W1 | 10/19/2011 | 10/19/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2011 |  | 2/21/2012 | N | EXP | 62 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 2/21/2012 | Connected |  | N
National Grid | CHELMSFORD | 175246 | 01824 | 800 | Solar | 05_01_406L3 | 11/04/2014 | 11/04/2014 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2014 | 01/05/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 445609 | 01845 | 24 | Solar | 05_01_552L1 | 07/20/2022 | 07/21/2022 | 29 | 20 | 9 | 12/01/2022 | 12/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2022 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2023 | Connected |  | N
National Grid | BILLERICA | 602571 | 01862 | 6 | Solar | 05_01_9J303 | 04/10/2024 | 04/15/2024 | 3 | 0 | 3 | 04/16/2024 | 04/16/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175725 | 01845 | 500 | Solar | 05_05_28W51 | 05/27/2014 | 05/27/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2014 | 07/10/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/27/2014 | 11/28/2014 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 431968 | 01523 | 7.83 | Solar | 05_12_49W4 | 06/30/2022 | 07/05/2022 | 3 | 2 | 1 | 07/06/2022 | 07/06/2022 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 06/30/2022 | 5/22/2024 | Y | EXP | 365 | 11/15/2022 | 05/19/2023 | 186 | 0 | 186 |  |  | 6/17/2023 | Connected |  | N
National Grid | OXFORD | 175759 | 01540 | 225 | Solar | 05_14_24L2 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 18 | 03/11/2015 | 04/24/2015 | 30 | 0 | 30 | 5/26/2015 | 5/26/2015 | 5/26/2015 | Connected |  | N
National Grid | SPENCER | 421208 | 01562 | 15.2 | Solar | 05_14_56L2 | 05/04/2022 | 05/10/2022 | 4 | 0 | 4 | 05/11/2022 | 05/11/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2023 | Connected |  | Y
National Grid | WORCESTER | 177755 | 01604 | 396 | Solar | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 84 | 84 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 | 12/20/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 332646 | 02720 | 7.6 | Solar | 05_14_7J4 | 01/06/2021 | 01/11/2021 | 2 | 0 | 2 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 175314 | 01970 | 594.4 | Solar | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 175510 | 01824 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 632680 | 01845 | 6 | Solar | 05_01_9J303 | 08/14/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | BILLERICA | 176454 | 01862 | 3 | Solar | 05_05_28W51 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 |  | 12/14/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/9/2016 | 9/9/2016 | 9/13/2016 | Connected |  | N
National Grid | ANDOVER | 444421 | 01845 | 0 | Other | 05_12_49W4 | 03/14/2023 | 07/14/2023 | 84 | 74 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 175833 | 01464 | 16.34 | Solar | 05_14_24L2 | 03/03/2015 | 03/03/2015 | 8 | 5 | 3 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2015 |  | 7/14/2015 | N | EXP | 12 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/15/2015 | Connected |  | N
National Grid | OXFORD | 446210 | 01540 | 15.2 | Solar | 05_14_56L2 | 07/22/2022 | 07/22/2022 | 0 | 0 | 0 | 07/25/2022 | 07/25/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2022 |  | 8/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2023 | Connected |  | N
National Grid | SPENCER | 177756 | 01562 | 324 | Solar | 05_14_70L1 | 08/01/2017 | 08/01/2017 | 83 | 83 | 0 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2018 |  | 9/2/2019 | N | STD | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 747655 | 01604 | 3.8 | Solar | 05_14_7L1 | 01/27/2026 | 02/02/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 175313 | 02720 | 587.2 | Solar | 05_01_227W1 | 08/28/2014 | 08/28/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 175509 | 01970 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 448029 | 01824 | 10 | Solar | 05_01_552L1 | 08/10/2022 | 08/15/2022 | 4 | 3 | 1 | 08/16/2022 | 08/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 10/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2022 | Connected |  | N
National Grid | ANDOVER | 645660 | 01845 | 5.76 | Solar | 05_01_9J303 | 10/25/2024 | 11/12/2024 | 7 | 2 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | BILLERICA | 177098 | 01862 | 3 | Solar | 05_05_28W51 | 05/24/2016 | 05/24/2016 | 2 | 2 | 0 | 05/27/2016 | 05/27/2016 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 492195 | 01845 | 750 | Solar | 05_12_49W4 | 04/07/2023 | 06/12/2023 | 44 | 34 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2023 | 07/12/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 178000 | 01523 | 7.6 | Solar | 05_14_24L2 | 10/25/2017 | 10/25/2017 | 62 | 62 | 0 | 02/06/2018 | 02/06/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 11/1/2018 | N | EXP | 267 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 466523 | 01540 | 6 | Solar | 05_14_56L2 | 10/06/2022 | 10/12/2022 | 3 | 1 | 2 | 10/13/2022 | 10/13/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 | 10/06/2022 | 11/10/2023 | Y | EXP | 365 | 12/21/2022 | 12/21/2022 | 1 | 0 | 1 |  |  | 4/14/2023 | Connected |  | N
National Grid | SPENCER | 177965 | 01562 | 480 | Solar | 05_14_70L1 | 04/21/2017 | 04/21/2017 | 25 | 22 | 3 | 05/30/2017 | 05/30/2017 | 189 | 46 | 143 | 10/05/2017 | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 11/17/2017 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 200995 | 01604 | 7.6 | Solar | 05_14_7L1 | 11/14/2018 | 01/09/2019 | 39 | 37 | 2 | 01/10/2019 | 01/10/2019 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2019 |  | 1/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | Connected |  | N
National Grid | FALL RIVER | 175454 | 02720 | 1500 | Solar | 05_01_227W1 | 07/16/2014 | 07/16/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2014 | 08/20/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2014 | 07/16/2014 | 6/1/2016 | Y | STD | 531 | 02/03/2017 | 03/03/2017 | 19 | 0 | 19 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | SALEM | 175505 | 01970 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 460324 | 01824 | 15.66 | Solar | 05_01_552L1 | 10/04/2022 | 10/31/2022 | 19 | 17 | 2 | 11/01/2022 | 11/01/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2023 | Connected |  | N
National Grid | ANDOVER | 650688 | 01845 | 5.76 | Solar | 05_01_9J303 | 11/11/2024 | 01/14/2025 | 0 | 0 | 0 | 01/15/2025 | 01/15/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | BILLERICA | 217169 | 01862 | 240 | Solar | 05_05_28W51 | 05/06/2019 | 05/21/2019 | 8 | 0 | 8 | 05/22/2019 | 05/22/2019 | 15 | 2 | 13 | 07/03/2019 | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 08/29/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 9/4/2019 |  | 6/12/2020 | N | EXP | 366 |  |  | 0 | 0 | 0 |  |  | 4/16/2020 | Connected |  | N
National Grid | SALISBURY | 530784 | 01952 | 7.6 | Solar | 05_12_49W4 | 06/12/2023 | 06/14/2023 | 2 | 0 | 2 | 06/15/2023 | 06/15/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 178611 | 01523 | 0 | Other | 05_14_24L2 | 12/14/2017 | 12/14/2017 | 0 | 0 | 0 | 05/11/2018 | 05/11/2018 | 0 | 0 | 0 | 06/15/2018 | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 |  | 09/18/2018 | 66 | 40 | 26 |  |  | 0 | 0 | 0 | 9/25/2018 |  | 4/30/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N
National Grid | OXFORD | 529680 | 01540 | 7.875 | Solar | 05_14_56L2 | 06/20/2023 | 06/29/2023 | 21 | 16 | 5 | 06/30/2023 | 06/30/2023 | 17 | 0 | 17 | 09/29/2023 | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 11/01/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 10/13/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178438 | 01562 | 7.6 | Solar | 05_14_70L1 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 3/12/2019 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 301380 | 01604 | 3.8 | Solar | 05_14_7L1 | 07/31/2020 | 08/03/2020 | 0 | 0 | 0 | 08/04/2020 | 08/04/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/31/2020 | 5/20/2021 | Y | EXP | 365 | 12/11/2020 | 01/04/2021 | 23 | 0 | 23 |  |  | 5/11/2021 | Connected |  | N
National Grid | FALL RIVER | 175579 | 02720 | 150 | Solar | 05_01_227W1 | 12/10/2014 | 12/10/2014 | 27 | 6 | 21 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 2/28/2015 | N | EXP | 25 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 4/22/2015 | Connected |  | N
National Grid | SALEM | 175504 | 01970 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 546629 | 01824 | 4.64 | Solar | 05_01_552L1 | 08/09/2023 | 08/22/2023 | 9 | 9 | 0 | 08/23/2023 | 08/23/2023 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2023 | 08/09/2023 | 10/10/2024 | Y | EXP | 365 | 10/28/2023 | 01/29/2024 | 94 | 3 | 91 |  |  | 2/1/2024 | Connected |  | N
National Grid | ANDOVER | 678617 | 01845 | 13.36 | Solar | 05_01_9J303 | 03/17/2025 | 04/04/2025 | 2 | 0 | 2 | 04/10/2025 | 04/10/2025 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 | 03/17/2025 | 5/20/2026 | Y | EXP | 365 | 11/07/2025 | 12/01/2025 | 25 | 0 | 25 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 282338 | 01862 | 0 | Other | 05_05_28W51 | 05/18/2020 | 07/16/2020 | 42 | 33 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2020 | 08/11/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2021 | 05/18/2020 | 11/29/2024 | Y | STD | 413 | 04/20/2022 | 03/07/2024 | 688 | 537 | 151 |  |  | 9/20/2024 | Connected |  | N
National Grid | SALISBURY | 618836 | 01952 | 0 | Battery Add-On | 05_12_49W4 | 06/18/2024 | 06/21/2024 | 3 | 1 | 2 | 06/24/2024 | 06/24/2024 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | SHIRLEY | 312556 | 01464 | 7.6 | Solar | 05_14_24L2 | 09/14/2020 | 09/16/2020 | 1 | 0 | 1 | 09/17/2020 | 09/17/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | CHARLTON | 572842 | 01507 | 250 | Solar | 05_14_56L2 | 12/07/2023 | 02/04/2024 | 38 | 29 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178546 | 01562 | 604 | Solar | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 409895 | 01604 | 7.6 | Solar | 05_14_7L1 | 04/14/2022 | 04/21/2022 | 5 | 4 | 1 | 04/22/2022 | 04/22/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176051 | 02720 | 184 | Solar | 05_01_227W1 | 01/12/2015 | 01/12/2015 | 11 | 0 | 11 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2015 |  | 7/31/2015 | N | EXP | 168 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 2/4/2016 | Connected |  | N
National Grid | SALEM | 175540 | 01970 | 1000 | Solar | 05_01_406L3 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 10/1/2016 | N | STD | 429 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 562432 | 01824 | 9.074 | Solar | 05_01_552L1 | 10/16/2023 | 10/19/2023 | 4 | 2 | 2 | 10/20/2023 | 10/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 | 10/16/2023 | 11/19/2024 | Y | EXP | 365 | 12/14/2023 | 02/07/2024 | 56 | 3 | 53 |  |  | 2/8/2024 | Connected |  | N
National Grid | ANDOVER | 608618 | 01845 | 10 | Solar | 05_01_9J306 | 05/03/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2025 | Connected |  | Y
National Grid | BILLERICA | 335842 | 01862 | 5.52 | Solar | 05_05_28W51 | 01/18/2021 | 12/16/2021 | 4 | 0 | 4 | 01/26/2021 | 01/26/2021 | 64 | 40 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2021 | 01/18/2021 | 9/16/2022 | Y | EXP | 365 | 03/31/2022 | 04/12/2022 | 13 | 0 | 13 |  |  | 6/4/2022 | Connected |  | N
National Grid | SALISBURY | 652802 | 01952 | 10 | Solar | 05_12_49W4 | 12/11/2024 | 12/30/2024 | 12 | 9 | 3 | 12/31/2024 | 12/31/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | LANCASTER | 317800 | 01523 | 10 | Solar | 05_14_24L2 | 10/07/2020 | 11/04/2020 | 19 | 17 | 2 | 11/05/2020 | 11/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2021 | Connected |  | N
National Grid | CHARLTON | 581516 | 01507 | 7.6 | Solar | 05_14_56L2 | 01/04/2024 | 01/23/2024 | 12 | 7 | 5 | 01/24/2024 | 01/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 178580 | 01562 | 402 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 25 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 440658 | 01604 | 7.6 | Solar | 05_14_7L1 | 06/29/2022 | 06/30/2022 | 1 | 0 | 1 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/29/2022 | 8/30/2023 | Y | EXP | 365 | 11/02/2022 | 11/08/2022 | 7 | 0 | 7 |  |  | 11/10/2022 | Connected |  | N
National Grid | FALL RIVER | 176714 | 02720 | 15.2 | Solar | 05_01_227W1 | 01/08/2016 | 01/08/2016 | 3 | 3 | 0 | 01/13/2016 | 01/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/13/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/12/2016 | 10/12/2016 | 10/19/2016 | Connected |  | N
National Grid | SALEM | 175653 | 01970 | 684 | Solar | 05_01_406L3 | 05/05/2014 | 05/05/2014 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2014 | 09/04/2014 | 76 | 20 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2015 | 05/05/2014 | 12/30/2015 | Y | STD | 285 | 10/22/2015 | 12/22/2015 | 41 | 0 | 41 | 12/11/2015 | 12/11/2015 | 12/30/2015 | Connected |  | N
National Grid | CHELMSFORD | 568209 | 01824 | 13.05 | Solar | 05_01_552L1 | 11/06/2023 | 11/13/2023 | 4 | 2 | 2 | 11/14/2023 | 11/14/2023 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2024 | Connected |  | N
National Grid | ANDOVER | 610910 | 01845 | 16.4 | Solar | 05_01_9J306 | 05/17/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2024 | Connected |  | N
National Grid | TEWKSBURY | 397056 | 01876 | 625 | Solar | 05_05_28W51 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 657217 | 01952 | 3.8 | Solar | 05_12_49W4 | 11/27/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | LEOMINSTER | 343183 | 01453 | 9.6 | Solar | 05_14_24L2 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2021 | Connected |  | N
National Grid | OXFORD | 600029 | 01540 | 0 | Battery Add-On | 05_14_56L2 | 03/27/2024 | 03/29/2024 | 2 | 0 | 2 | 04/01/2024 | 04/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2024 | Connected |  | N
National Grid | SPENCER | 178577 | 01562 | 316 | Solar | 05_14_70L1 | 01/30/2018 | 01/30/2018 | 24 | 3 | 21 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 628133 | 01604 | 7.6 | Solar | 05_14_7L1 | 07/30/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 177900 | 02720 | 3875 | Solar | 05_01_227W1 | 06/15/2017 | 06/15/2017 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2017 | 09/22/2017 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 06/15/2017 | 6/18/2021 | Y | STD | 34 | 11/04/2020 | 03/12/2021 | 128 | 0 | 128 | 5/20/2021 | 5/28/2021 | 6/11/2021 | Connected |  | N
National Grid | SALEM | 175716 | 01970 | 1000 | Solar | 05_01_406L3 | 12/26/2014 | 12/26/2014 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2015 | 02/13/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2015 |  | 8/1/2016 | N | STD | 31 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 571014 | 01824 | 10 | Solar | 05_01_552L1 | 12/21/2023 | 11/27/2023 | 5 | 0 | 5 | 01/02/2024 | 01/02/2024 | 47 | 27 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 12/21/2023 | 5/3/2025 | Y | EXP | 365 | 06/11/2024 | 08/15/2024 | 66 | 0 | 66 |  |  | 9/24/2024 | Connected |  | N
National Grid | ANDOVER | 665392 | 01845 | 7.6 | Solar | 05_01_9J306 | 01/13/2025 | 02/14/2025 | 19 | 14 | 5 | 02/18/2025 | 02/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 | 01/13/2025 | 4/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 401103 | 01876 | 0 | Other | 05_05_28W51 | 01/04/2022 | 01/27/2022 | 17 | 9 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/28/2022 | 02/02/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 646626 | 01952 | 170 | Solar | 05_12_49W6 | 11/04/2024 | 12/13/2024 | 26 | 17 | 9 | 12/16/2024 | 12/16/2024 | 55 | 31 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 11/04/2024 | 8/3/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LEOMINSTER | 344721 | 01453 | 11.4 | Solar | 05_14_24L2 | 03/02/2021 | 03/03/2021 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 3/2/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHARLTON | 608440 | 01507 | 7.54 | Solar | 05_14_56L2 | 05/03/2024 | 06/26/2024 | 36 | 35 | 1 | 06/27/2024 | 06/27/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 8/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2024 | Connected |  | N
National Grid | SPENCER | 178576 | 01562 | 524 | Solar | 05_14_70L1 | 01/29/2018 | 01/29/2018 | 36 | 31 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/22/2018 | 04/18/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 174732 | 01610 | 32.9 | Solar | 05_14_7L2 | 01/04/2013 | 01/04/2013 | 8 | 0 | 8 | 01/17/2013 | 01/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 | 01/04/2013 | 3/29/2013 | Y | EXP | 11 |  |  | 0 | 0 | 0 | 4/17/2013 | 4/17/2013 | 8/15/2013 | Connected |  | N
National Grid | FALL RIVER | 184857 | 02720 | 4980 | Solar | 05_01_227W1 | 05/09/2018 | 06/06/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2018 | 07/25/2018 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 05/09/2018 | 1/17/2024 | Y | STD | 88 | 08/12/2022 | 01/18/2023 | 160 | 0 | 160 | 12/15/2023 | 12/19/2023 | 12/29/2023 | Connected |  | N
National Grid | SALEM | 175931 | 01970 | 10.75 | Solar | 05_01_406L3 | 08/06/2015 | 08/06/2015 | 2 | 2 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2015 |  | 8/15/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/3/2016 | 2/3/2016 | 1/3/2018 | Connected |  | N
National Grid | CHELMSFORD | 588485 | 01824 | 7.6 | Solar | 05_01_552L1 | 02/12/2024 | 02/15/2024 | 4 | 2 | 2 | 02/16/2024 | 02/16/2024 | 18 | 13 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | ANDOVER | 718328 | 01845 | 7.6 | Solar | 05_01_9J306 | 09/10/2025 | 09/18/2025 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 424613 | 01862 | 10 | Solar | 05_05_28W51 | 04/21/2022 | 04/27/2022 | 4 | 0 | 4 | 04/28/2022 | 04/28/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2022 | 04/21/2022 | 9/20/2023 | Y | EXP | 365 | 08/19/2022 | 09/19/2022 | 32 | 0 | 32 |  |  | 9/27/2022 | Connected |  | Y
National Grid | SALISBURY | 707425 | 01952 | 50 | Solar | 05_12_49W6 | 08/01/2025 | 08/08/2025 | 4 | 2 | 2 | 08/11/2025 | 08/11/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 379424 | 01523 | 7.6 | Solar | 05_14_24L2 | 09/21/2021 | 12/16/2021 | 3 | 0 | 3 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 645686 | 01540 | 23 | Solar | 05_14_56L2 | 10/09/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/09/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178584 | 01562 | 158 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 23 | 3 | 20 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177074 | 01610 | 10 | Solar | 05_14_7L2 | 08/03/2016 | 08/03/2016 | 1 | 1 | 0 | 08/05/2016 | 08/05/2016 | 179 | 0 | 179 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2016 | 08/03/2016 | 8/9/2017 | Y | EXP | 363 | 10/17/2016 | 10/26/2016 | 7 | 0 | 7 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 188006 | 02720 | 11.4 | Solar | 05_01_227W1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 | 06/21/2018 | 06/21/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176139 | 01970 | 8.39 | Solar | 05_01_406L3 | 06/26/2015 | 06/26/2015 | 0 | 0 | 0 | 07/01/2015 | 07/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2015 |  | 7/6/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/3/2015 | 8/3/2015 | 1/28/2016 | Connected |  | N
National Grid | CHELMSFORD | 603808 | 01824 | 10 | Solar | 05_01_552L1 | 04/16/2024 | 05/02/2024 | 5 | 0 | 5 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/16/2024 | 7/22/2025 | Y | EXP | 365 | 08/08/2024 | 09/12/2024 | 36 | 0 | 36 |  |  | 11/22/2024 | Connected |  | N
National Grid | ANDOVER | 595739 | 01845 | 10 | Solar | 05_01_9J307 | 03/15/2024 | 06/11/2024 | 52 | 50 | 2 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | TEWKSBURY | 484084 | 01876 | 126.3 | Solar | 05_05_28W51 | 12/14/2022 | 02/10/2023 | 39 | 29 | 10 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 707396 | 01952 | 67.3 | Solar | 05_12_49W6 | 08/01/2025 | 09/10/2025 | 27 | 18 | 9 | 09/11/2025 | 09/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 408495 | 01523 | 0 | Solar | 05_14_24L2 | 11/29/2022 |  | 220 | 204 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 652213 | 01540 | 7.6 | Solar | 05_14_56L2 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 178616 | 01562 | 444 | Solar | 05_14_70L1 | 01/31/2018 | 01/31/2018 | 35 | 30 | 5 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 |  | 6/8/2020 | N | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177273 | 01610 | 20 | Solar | 05_14_7L2 | 02/06/2017 | 02/06/2017 | 6 | 2 | 4 | 02/14/2017 | 02/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | FALL RIVER | 272564 | 02720 | 0 | Solar | 05_01_227W1 | 02/05/2020 | 02/20/2020 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2020 | 03/13/2020 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2021 | 02/05/2020 | 9/8/2022 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176751 | 01970 | 6 | Solar | 05_01_406L3 | 01/12/2016 | 01/12/2016 | 9 | 9 | 0 | 01/26/2016 | 01/26/2016 | 261 | 0 | 261 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/27/2017 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 613530 | 01824 | 36 | Solar | 05_01_552L1 | 08/18/2024 | 10/28/2024 | 49 | 41 | 8 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ANDOVER | 670182 | 01845 | 10 | Solar | 05_01_9J307 | 02/05/2025 | 04/07/2025 | 5 | 0 | 5 | 04/08/2025 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 646688 | 01876 | 0 | Solar | 05_05_28W51 | 10/11/2024 | 12/09/2024 | 8 | 5 | 3 | 12/10/2024 | 12/10/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/5/2025 | Connected |  | N
National Grid | SALISBURY | 727468 | 01952 | 84.6 | Solar | 05_12_49W6 | 10/20/2025 | 11/10/2025 | 15 | 6 | 9 | 11/12/2025 | 11/12/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LANCASTER | 517472 | 01523 | 8.7 | Solar | 05_14_24L2 | 05/22/2023 | 05/26/2023 | 4 | 0 | 4 | 05/30/2023 | 05/30/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2023 |  | 7/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2023 | Connected |  | Y
National Grid | OXFORD | 670110 | 01540 | 10 | Solar | 05_14_56L2 | 02/05/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | SPENCER | 178720 | 01562 | 1950 | Solar | 05_14_70L1 | 04/12/2018 | 04/12/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 05/26/2018 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  | 7/29/2021 | N | STD | 728 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 177398 | 01604 | 57.6 | Solar | 05_14_7L2 | 06/28/2016 | 06/28/2016 | 7 | 7 | 0 | 07/11/2016 | 07/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2016 |  | 7/5/2017 | N | EXP | 345 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 9/22/2016 | Connected |  | N
National Grid | FALL RIVER | 287827 | 02720 | 4950 | Other | 05_01_227W1 | 05/06/2020 | 05/12/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/13/2020 | 06/02/2020 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176845 | 01970 | 15 | Solar | 05_01_406L3 | 05/02/2016 | 05/02/2016 | 3 | 3 | 0 | 05/06/2016 | 05/06/2016 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2016 |  | 5/8/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 619978 | 01824 | 5.76 | Solar | 05_01_552L1 | 06/24/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 06/24/2024 | 9/12/2025 | Y | EXP | 365 | 11/15/2024 | 01/16/2025 | 63 | 0 | 63 |  |  | 1/24/2025 | Connected |  | N
National Grid | ANDOVER | 175980 | 01845 | 42 | Solar | 05_01_9J315 | 01/23/2015 | 01/23/2015 | 6 | 0 | 6 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2015 |  | 6/30/2015 | N | EXP | 127 |  |  | 0 | 0 | 0 | 8/20/2015 | 8/20/2015 | 8/21/2015 | Connected |  | N
National Grid | BILLERICA | 674818 | 01862 | 7.6 | Solar | 05_05_28W51 | 03/05/2025 | 03/10/2025 | 3 | 0 | 3 | 03/11/2025 | 03/11/2025 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | SALISBURY | 177085 | 01952 | 540 | Solar | 05_12_49W6 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/10/2017 | 50 | 39 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANCASTER | 566273 | 01523 | 4.095 | Solar | 05_14_24L2 | 10/31/2023 | 11/02/2023 | 2 | 0 | 2 | 11/03/2023 | 11/03/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 10/31/2023 | 12/26/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | OXFORD | 684866 | 01540 | 0 | Solar | 05_14_56L2 | 04/14/2025 | 05/20/2025 | 23 | 17 | 6 | 05/21/2025 | 05/21/2025 | 43 | 23 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 7/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | SPENCER | 243050 | 01562 | 7.6 | Solar | 05_14_70L1 | 08/09/2019 | 01/17/2020 | 111 | 111 | 0 | 01/21/2020 | 01/21/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2020 |  | 8/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178230 | 01604 | 7.6 | Solar | 05_14_7L2 | 01/03/2018 | 01/03/2018 | 21 | 15 | 6 | 02/06/2018 | 02/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2018 |  | 1/10/2019 | N | EXP | 337 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 315362 | 02720 | 0 | Other | 05_01_227W1 | 11/05/2020 | 11/12/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 11/30/2020 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/05/2020 | 8/24/2025 | Y | STD | 616 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 176939 | 01970 | 10 | Solar | 05_01_406L3 | 12/16/2016 | 12/16/2016 | 3 | 2 | 1 | 12/22/2016 | 12/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2016 |  | 12/24/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/12/2017 | 7/12/2017 | 7/12/2017 | Connected |  | N
National Grid | CHELMSFORD | 621844 | 01824 | 7.6 | Solar | 05_01_552L1 | 07/01/2024 |  | 86 | 40 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 552028 | 01845 | 5.8 | Solar | 05_01_9J321 | 11/16/2023 | 11/20/2023 | 3 | 1 | 2 | 11/21/2023 | 11/21/2023 | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 176268 | 01862 | 17.6 | Solar | 05_05_2J1 | 02/18/2015 | 02/18/2015 | 4 | 1 | 3 | 02/25/2015 | 02/25/2015 | 480 | 0 | 480 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2015 |  | 7/31/2015 | N | EXP | 154 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 177244 | 01952 | 191 | Solar | 05_12_49W6 | 02/06/2017 | 02/06/2017 | 4 | 0 | 4 | 02/10/2017 | 02/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2017 |  | 2/11/2018 | N | EXP | 361 | 07/27/2017 | 07/31/2017 | 2 | 0 | 2 | 10/5/2017 | 10/5/2017 | 10/18/2017 | Connected |  | N
National Grid | LANCASTER | 638354 | 01523 | 15.356 | Solar | 05_14_24L2 | 09/13/2024 | 09/18/2024 | 3 | 0 | 3 | 09/19/2024 | 09/19/2024 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/13/2024 | 11/1/2025 | Y | EXP | 365 | 12/18/2024 | 03/05/2025 | 78 | 0 | 78 |  |  | 3/11/2025 | Connected |  | N
National Grid | OXFORD | 705068 | 01540 | 17.799 | Solar | 05_14_56L2 | 07/17/2025 | 07/22/2025 | 3 | 0 | 3 | 07/23/2025 | 07/23/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | SPENCER | 295835 | 01562 | 7.6 | Solar | 05_14_70L1 | 06/13/2020 | 06/18/2020 | 3 | 0 | 3 | 06/19/2020 | 06/19/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | WORCESTER | 198767 | 01604 | 13.8 | Solar | 05_14_7L2 | 12/03/2018 | 12/13/2018 | 7 | 0 | 7 | 12/14/2018 | 12/14/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 336841 | 02720 | 6 | Solar | 05_01_227W1 | 02/04/2021 | 02/11/2021 | 4 | 1 | 3 | 02/12/2021 | 02/12/2021 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2021 | 02/04/2021 | 5/1/2022 | Y | EXP | 365 | 07/09/2021 | 10/05/2021 | 74 | 3 | 71 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 177113 | 01970 | 936 | Solar | 05_01_406L3 | 08/04/2016 | 08/04/2016 | 128 | 128 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/14/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 635360 | 01824 | 0 | Solar | 05_01_552L1 | 08/26/2024 | 08/28/2024 | 2 | 0 | 2 | 08/29/2024 | 08/29/2024 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 11/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2024 | Connected |  | N
National Grid | ANDOVER | 642954 | 01845 | 7.6 | Solar | 05_01_9J321 | 09/27/2024 | 10/10/2024 | 4 | 0 | 4 | 10/11/2024 | 10/11/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 484664 | 01862 | 6 | Solar | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 48 | 25 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2023 | 01/31/2023 | 7/26/2024 | Y | EXP | 365 | 07/01/2023 | 07/27/2023 | 27 | 0 | 27 |  |  | 8/2/2023 | Connected |  | N
National Grid | SALISBURY | 273131 | 01952 | 0 | Solar | 05_12_49W6 | 01/14/2020 | 01/14/2020 | 0 | 0 | 0 | 01/15/2020 | 01/15/2020 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2020 |  | 1/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2020 | Connected |  | N
National Grid | LANCASTER | 656616 | 01523 | 9.28 | Solar | 05_14_24L2 | 11/25/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y
National Grid | OXFORD | 707961 | 01540 | 17.6 | Solar | 05_14_56L3 | 08/01/2025 | 08/06/2025 | 3 | 0 | 3 | 08/07/2025 | 08/07/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 08/01/2025 | 10/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SPENCER | 325147 | 01562 | 7.68 | Solar | 05_14_70L1 | 01/06/2021 | 02/17/2021 | 28 | 28 | 0 | 02/18/2021 | 02/18/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2021 |  | 2/17/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 213965 | 01604 | 0 | Solar | 05_14_7L2 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2019 | Connected |  | N
National Grid | ATTLEBORO | 431629 | 02703 | 11.4 | Solar | 05_01_227W1 | 07/13/2022 | 07/15/2022 | 2 | 0 | 2 | 07/18/2022 | 07/18/2022 | 62 | 42 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 177412 | 01970 | 1740 | Solar | 05_01_406L3 | 09/11/2016 | 10/13/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2017 | 09/11/2016 | 8/24/2020 | Y | STD | 993 | 08/29/2019 | 11/22/2019 | 85 | 0 | 85 |  |  | 8/12/2020 | Connected |  | N
National Grid | CHELMSFORD | 641036 | 01824 | 5.76 | Solar | 05_01_552L1 | 09/17/2024 | 10/07/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/17/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | ANDOVER | 175684 | 01845 | 75.6 | Solar | 05_01_9J327 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 102 | 3 | 99 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 12/24/2014 | 5/31/2015 | Y | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 484658 | 01862 | 6 | Solar | 05_05_2J1 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/18/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | SALISBURY | 277189 | 01952 | 3.36 | Solar | 05_12_49W6 | 04/27/2020 | 04/30/2020 | 2 | 0 | 2 | 05/01/2020 | 05/01/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 687682 | 01464 | 15.2 | Solar | 05_14_24L2 | 04/25/2025 | 04/29/2025 | 2 | 0 | 2 | 04/30/2025 | 04/30/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/3/2025 | Connected |  | N
National Grid | OXFORD | 707764 | 01540 | 19.12 | Solar | 05_14_56L3 | 08/06/2025 | 08/27/2025 | 14 | 9 | 5 | 08/28/2025 | 08/28/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SPENCER | 372170 | 01562 | 7.6 | Solar | 05_14_70L1 | 08/09/2021 | 08/10/2021 | 1 | 0 | 1 | 08/11/2021 | 08/11/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 9/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2022 | Connected |  | N
National Grid | WORCESTER | 306671 | 01604 | 9.8 | Solar | 05_14_7L2 | 09/15/2020 | 09/21/2020 | 3 | 0 | 3 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 | 09/15/2020 | 12/14/2022 | Y | EXP | 365 | 06/29/2021 | 08/06/2021 | 38 | 0 | 38 |  |  | 9/10/2021 | Connected |  | Y
National Grid | ATTLEBORO | 441594 | 02703 | 0 | Other | 05_01_227W1 | 09/20/2022 | 10/20/2022 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 177669 | 01970 | 2000 | Solar | 05_01_406L3 | 05/25/2017 | 05/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/26/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 05/25/2017 | 6/29/2020 | Y | STD | 621 | 12/12/2019 | 06/12/2020 | 183 | 0 | 183 |  |  | 6/29/2020 | Connected |  | N
National Grid | CHELMSFORD | 642534 | 01824 | 5.76 | Solar | 05_01_552L1 | 09/24/2024 | 10/08/2024 | 1 | 0 | 1 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 11/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | BOXFORD | 719601 | 01921 | 11.5 | Solar | 05_01_9J337 | 09/23/2025 | 10/23/2025 | 20 | 17 | 3 | 10/24/2025 | 10/24/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 505519 | 01852 | 7.6 | Solar | 05_05_2J1 | 03/15/2023 | 03/22/2023 | 5 | 4 | 1 | 03/23/2023 | 03/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 296513 | 01952 | 3.36 | Solar | 05_12_49W6 | 07/13/2020 | 07/17/2020 | 3 | 0 | 3 | 07/20/2020 | 07/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LEOMINSTER | 707310 | 01453 | 23 | Solar | 05_14_24L2 | 08/04/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2025 | Connected |  | N
National Grid | OXFORD | 725463 | 01540 | 15.2 | Solar | 05_14_56L3 | 10/13/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 401363 | 01562 | 0 | Battery Add-On | 05_14_70L1 | 05/11/2022 | 06/16/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/21/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 345471 | 01609 | 500 | Solar | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 |  |  | 169 | 33 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 477515 | 02703 | 15.2 | Solar | 05_01_227W1 | 11/22/2022 | 11/29/2022 | 4 | 0 | 4 | 11/30/2022 | 11/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | SALEM | 178103 | 01970 | 249.8 | Solar | 05_01_406L3 | 09/08/2017 | 02/12/2018 | 10 | 0 | 10 | 02/12/2018 | 02/12/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 9/16/2019 | N | EXP | 452 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 648467 | 01824 | 0 | Solar | 05_01_552L1 | 10/21/2024 | 10/24/2024 | 4 | 2 | 2 | 10/25/2024 | 10/25/2024 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | BOXFORD | 742840 | 01921 | 11.52 | Solar | 05_01_9J337 | 01/02/2026 | 02/17/2026 | 29 | 25 | 4 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 608945 | 01862 | 10 | Solar | 05_05_2J2 | 05/06/2024 | 05/16/2024 | 1 | 0 | 1 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 05/06/2024 | 6/6/2025 | Y | EXP | 365 | 08/21/2024 | 09/26/2024 | 37 | 0 | 37 |  |  | 10/25/2024 | Connected |  | N
National Grid | SALISBURY | 302107 | 01952 | 86.4 | Solar | 05_12_49W6 | 07/21/2020 | 07/29/2020 | 5 | 0 | 5 | 07/30/2020 | 07/30/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 1/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2021 | Connected |  | N
National Grid | LEOMINSTER | 746949 | 01453 | 0 | Other | 05_14_24L3 | 03/03/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | CHARLTON | 724912 | 01507 | 16 | Solar | 05_14_56L3 | 10/08/2025 | 10/09/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SPENCER | 414875 | 01562 | 15.2 | Solar | 05_14_70L1 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 346665 | 01604 | 250 | Solar | 05_14_7L2 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 193 | 192 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 504134 | 02703 | 7.6 | Solar | 05_01_227W1 | 02/23/2023 |  | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALEM | 178302 | 01970 | 0 | Solar | 05_01_406L3 | 01/09/2018 | 03/09/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/05/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 648713 | 01824 | 10 | Solar | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 44 | 19 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/04/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 | 11/21/2025 | 163 | 0 | 163 |  |  | 12/17/2025 | Connected |  | N
National Grid | BOXFORD | 175283 | 01921 | 42.57 | Solar | 05_01_9J337 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/4/2015 | Connected |  | N
National Grid | TEWKSBURY | 174441 | 01876 | 1875 | Solar | 05_05_2J3 | 06/28/2012 | 06/28/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2012 | 08/21/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/15/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 342002 | 01952 | 40 | Solar | 05_12_49W6 | 03/30/2021 | 04/22/2021 | 14 | 9 | 5 | 04/23/2021 | 04/23/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2021 |  | 7/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2021 | Connected |  | N
National Grid | SHIRLEY | 748273 | 01464 | 170 | Solar | 05_14_24L3 | 02/18/2026 |  | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | OXFORD | 731974 | 01540 | 20 | Solar | 05_14_56L3 | 11/06/2025 | 11/12/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | SPENCER | 419848 | 01562 | 0 | Other | 05_14_70L1 | 06/29/2022 | 07/12/2022 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2022 | 08/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 467964 | 01604 | 15.2 | Solar | 05_14_7L2 | 10/13/2022 | 12/12/2022 | 40 | 39 | 1 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | N
National Grid | ATTLEBORO | 532473 | 02703 | 15.2 | Solar | 05_01_227W1 | 06/08/2023 | 06/12/2023 | 2 | 0 | 2 | 06/13/2023 | 06/13/2023 | 23 | 7 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 9/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2023 | Connected |  | N
National Grid | SALEM | 201189 | 01970 | 3.8 | Solar | 05_01_406L3 | 08/15/2019 | 08/15/2019 | 0 | 0 | 0 | 08/16/2019 | 08/16/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2019 |  | 10/14/2019 | N | EXP | 52 |  |  | 0 | 0 | 0 |  |  | 9/12/2019 | Connected |  | N
National Grid | CHELMSFORD | 648709 | 01824 | 10 | Solar | 05_01_552L1 | 11/04/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | BOXFORD | 236472 | 01921 | 7.6 | Solar | 05_01_9J337 | 07/22/2019 | 07/23/2019 | 0 | 0 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 12/30/2019 | N | EXP | 46 |  |  | 0 | 0 | 0 |  |  | 12/10/2019 | Connected |  | N
National Grid | BILLERICA | 177231 | 01862 | 72 | Solar | 05_05_2J3 | 11/03/2016 | 11/03/2016 | 8 | 8 | 0 | 11/17/2016 | 11/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/03/2016 | 11/9/2017 | Y | EXP | 352 | 03/02/2017 | 03/20/2017 | 12 | 0 | 12 | 5/16/2017 | 5/16/2017 | 5/22/2017 | Connected |  | N
National Grid | SALISBURY | 370832 | 01952 | 250 | Solar | 05_12_49W6 | 08/06/2021 | 08/20/2021 | 10 | 0 | 10 |  |  | 30 | 3 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 | 08/06/2021 | 8/1/2023 | Y | STD | 41 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | LANCASTER | 174751 | 01523 | 150 | Solar | 05_14_24L3 | 07/09/2013 | 07/09/2013 | 18 | 10 | 8 | 08/05/2013 | 08/05/2013 | 568 | 39 | 529 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2013 |  | 9/30/2014 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 734607 | 01540 | 7.6 | Solar | 05_14_56L3 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 444078 | 01562 | 9.8 | Solar | 05_14_70L1 | 07/20/2022 |  | 38 | 26 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 615634 | 01604 | 3.8 | Solar | 05_14_7L2 | 06/05/2024 | 07/16/2024 | 2 | 0 | 2 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 06/05/2024 | 8/26/2025 | Y | EXP | 365 | 11/02/2024 | 11/12/2024 | 11 | 0 | 11 |  |  | 11/13/2024 | Connected |  | N
National Grid | ATTLEBORO | 589295 | 02703 | 14.21 | Solar | 05_01_227W1 | 03/22/2024 | 03/27/2024 | 3 | 0 | 3 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | SALEM | 209264 | 01970 | 17.28 | Solar | 05_01_406L3 | 02/11/2019 | 04/22/2019 | 49 | 49 | 0 | 04/23/2019 | 04/23/2019 | 242 | 241 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2020 |  | 1/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2020 | Connected |  | N
National Grid | CHELMSFORD | 656206 | 01824 | 7.6 | Solar | 05_01_552L1 | 11/22/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/22/2024 | 2/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | BOXFORD | 279312 | 01921 | 7.6 | Solar | 05_01_9J337 | 04/20/2020 | 04/27/2020 | 4 | 4 | 0 | 04/28/2020 | 04/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2020 | Connected |  | N
National Grid | BILLERICA | 555478 | 01862 | 240 | Solar | 05_05_310W3 | 09/15/2023 | 09/29/2023 | 10 | 1 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/15/2023 | 4/18/2026 | Y | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SALISBURY | 647135 | 01952 | 7.6 | Solar | 05_12_49W6 | 10/29/2024 | 10/31/2024 | 17 | 15 | 2 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 175758 | 01523 | 150 | Solar | 05_14_24L3 | 12/29/2014 | 12/29/2014 | 1 | 0 | 1 | 12/30/2014 | 12/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2015 | 12/29/2014 | 6/30/2015 | Y | EXP | 113 | 03/06/2015 | 05/06/2015 | 41 | 0 | 41 | 6/1/2015 | 6/1/2015 | 6/1/2015 | Connected |  | N
National Grid | OXFORD | 736628 | 01540 | 10 | Solar | 05_14_56L3 | 12/29/2025 | 02/13/2026 | 31 | 25 | 6 | 02/17/2026 | 02/17/2026 | 14 | 7 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 578847 | 01562 | 0 | Solar | 05_14_70L1 | 01/22/2024 | 01/24/2024 | 2 | 0 | 2 | 01/25/2024 | 01/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | WORCESTER | 654131 | 01604 | 9.86 | Solar | 05_14_7L2 | 11/21/2024 | 12/13/2024 | 9 | 6 | 3 | 12/16/2024 | 12/16/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/21/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | ATTLEBORO | 591793 | 02703 | 15.2 | Solar | 05_01_227W1 | 02/21/2024 | 03/14/2024 | 16 | 11 | 5 | 03/15/2024 | 03/15/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 243055 | 01970 | 10 | Solar | 05_01_406L3 | 10/07/2019 | 10/14/2019 | 4 | 4 | 0 | 10/15/2019 | 10/15/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 | 10/07/2019 | 10/7/2020 | Y | EXP | 365 | 07/14/2020 | 08/21/2020 | 38 | 0 | 38 |  |  | 9/4/2020 | Connected |  | N
National Grid | CHELMSFORD | 662768 | 01824 | 3.8 | Solar | 05_01_552L1 | 12/27/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 601301 | 01845 | 3.8 | Solar | 05_01_9J337 | 04/10/2024 | 04/30/2024 | 14 | 13 | 1 | 05/01/2024 | 05/01/2024 | 30 | 25 | 5 | 07/24/2024 | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 08/27/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | TEWKSBURY | 744268 | 01876 | 75 | Solar | 05_05_310W3 | 01/09/2026 | 02/11/2026 | 20 | 11 | 9 | 02/12/2026 | 02/12/2026 | 17 | 5 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SALISBURY | 657099 | 01952 | 75 | Solar | 05_12_49W6 | 12/11/2024 | 01/17/2025 | 25 | 16 | 9 | 01/21/2025 | 01/21/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 9/19/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | SHIRLEY | 199628 | 01464 | 3.8 | Solar | 05_14_24L3 | 10/29/2018 | 12/18/2018 | 25 | 24 | 1 | 12/19/2018 | 12/19/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2019 |  | 10/11/2019 | N | EXP | 238 |  |  | 0 | 0 | 0 |  |  | 8/27/2019 | Connected |  | N
National Grid | CHARLTON | 748935 | 01507 | 19 | Solar | 05_14_56L3 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SPENCER | 605258 | 01562 | 10 | Solar | 05_14_70L1 | 05/23/2024 | 05/28/2024 | 2 | 0 | 2 | 05/29/2024 | 05/29/2024 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 718084 | 01604 | 9.6 | Solar | 05_14_7L2 | 09/10/2025 | 10/01/2025 | 1 | 0 | 1 | 10/08/2025 | 10/08/2025 | 37 | 24 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2026 | Connected |  | N
National Grid | SOUTHBOROUGH | 598492 | 01772 | 20 | Solar | 05_01_227W1 | 03/21/2024 | 04/02/2024 | 8 | 6 | 2 | 04/03/2024 | 04/03/2024 | 36 | 29 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | SALEM | 244524 | 01970 | 249.8 | Solar | 05_01_406L3 | 07/22/2019 | 07/26/2019 | 4 | 3 | 1 |  |  | 11 | 5 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 | 07/22/2019 | 11/10/2023 | Y | STD | 278 | 11/01/2022 | 05/03/2023 | 184 | 0 | 184 |  |  | 10/17/2023 | Connected |  | N
National Grid | CHELMSFORD | 668644 | 01824 | 7.6 | Solar | 05_01_552L1 | 01/29/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/29/2025 | 4/1/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | BOXFORD | 652266 | 01921 | 4.225 | Solar | 05_01_9J337 | 11/05/2024 | 11/22/2024 | 4 | 0 | 4 | 11/25/2024 | 11/25/2024 | 83 | 63 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 174781 | 01862 | 480 | Solar | 05_05_310W3 | 07/08/2013 | 07/08/2013 | 8 | 0 | 8 | 07/19/2013 | 07/19/2013 | 0 | 0 | 0 | 11/05/2013 | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  | 01/23/2014 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 2/11/2014 | 07/08/2013 | 12/20/2017 | Y | EXP | 148 | 09/22/2017 | 10/16/2017 | 15 | 0 | 15 | 9/18/2017 | 9/18/2017 | 12/1/2017 | Connected |  | N
National Grid | SALISBURY | 708169 | 01952 | 17.101 | Solar | 05_12_49W6 | 08/22/2025 | 08/28/2025 | 4 | 0 | 4 | 08/29/2025 | 08/29/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | SHIRLEY | 341278 | 01464 | 166.6 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/14/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | OXFORD | 174156 | 01540 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/5/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 605506 | 01562 | 10 | Solar | 05_14_70L1 | 04/23/2024 | 04/26/2024 | 1 | 0 | 1 | 04/29/2024 | 04/29/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/23/2024 | 5/20/2025 | Y | EXP | 365 | 06/26/2024 | 08/09/2024 | 45 | 0 | 45 |  |  | 8/22/2024 | Connected |  | N
National Grid | WORCESTER | 730322 | 01604 | 3.8 | Solar | 05_14_7L2 | 10/31/2025 | 11/05/2025 | 3 | 0 | 3 | 11/06/2025 | 11/06/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | MARLBOROUGH | 623849 | 01752 | 7.6 | Solar | 05_01_227W1 | 07/10/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 343654 | 01970 | 7.6 | Solar | 05_01_406L3 | 03/16/2021 | 03/17/2021 | 0 | 0 | 0 | 03/18/2021 | 03/18/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2021 | 03/16/2021 | 12/8/2022 | Y | EXP | 365 | 07/24/2021 | 12/08/2021 | 138 | 7 | 131 |  |  | 1/4/2022 | Connected |  | N
National Grid | CHELMSFORD | 673877 | 01824 | 10 | Solar | 05_01_552L1 | 02/24/2025 | 03/17/2025 | 3 | 0 | 3 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 653577 | 01921 | 15.2 | Solar | 05_01_9J337 | 11/14/2024 | 11/18/2024 | 2 | 0 | 2 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | BILLERICA | 176778 | 01862 | 576 | Solar | 05_05_310W3 | 11/04/2015 | 11/04/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/06/2015 | 12/09/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 591000 | 01952 | 10 | Solar | 05_12_4J2 | 03/06/2024 | 03/08/2024 | 2 | 0 | 2 | 03/11/2024 | 03/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 341277 | 01523 | 180 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 6/10/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2023 | Connected |  | N
National Grid | OXFORD | 174155 | 01540 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 621445 | 01562 | 18.115 | Solar | 05_14_70L1 | 06/28/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | Y
National Grid | WORCESTER | 711942 | 01604 | 5.76 | Solar | 05_14_7L4 | 08/13/2025 | 09/17/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBOROUGH | 631955 | 01772 | 15.2 | Solar | 05_01_227W1 | 08/23/2024 | 08/28/2024 | 3 | 0 | 3 | 08/29/2024 | 08/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/27/2024 | Connected |  | N
National Grid | SALEM | 353715 | 01970 | 10 | Solar | 05_01_406L3 | 05/18/2022 | 01/06/2022 | 6 | 4 | 2 | 05/26/2022 | 05/26/2022 | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 | 05/18/2022 | 6/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | N
National Grid | CHELMSFORD | 676225 | 01824 | 7.6 | Solar | 05_01_552L1 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2025 | Connected |  | N
National Grid | ANDOVER | 695515 | 01845 | 6.98 | Solar | 05_01_9J337 | 06/02/2025 | 06/20/2025 | 2 | 0 | 2 | 06/26/2025 | 06/26/2025 | 79 | 71 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | LOWELL | 373284 | 01852 | 10 | Solar | 05_05_310W3 | 08/02/2021 | 08/05/2021 | 3 | 2 | 1 | 08/06/2021 | 08/06/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 9/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2022 | Connected |  | N
National Grid | SALISBURY | 605660 | 01952 | 15.2 | Solar | 05_12_4J2 | 05/02/2024 | 05/10/2024 | 7 | 5 | 2 | 05/13/2024 | 05/13/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2024 | 05/02/2024 | 6/20/2025 | Y | EXP | 365 | 10/03/2024 | 12/18/2024 | 77 | 0 | 77 |  |  | 1/10/2025 | Connected |  | N
National Grid | SHIRLEY | 341279 | 01464 | 133.2 | Solar | 05_14_24L3 | 02/12/2021 | 03/04/2021 | 13 | 2 | 11 |  |  | 94 | 78 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2022 | 02/12/2021 | 7/31/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | OXFORD | 174172 | 01540 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 648217 | 01562 | 7.6 | Solar | 05_14_70L1 | 10/30/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 | 10/30/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | WORCESTER | 726965 | 01604 | 0 | Battery Add-On | 05_14_7L4 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 10/23/2025 | 10/23/2025 | 61 | 47 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MARLBOROUGH | 644731 | 01752 | 5.76 | Solar | 05_01_227W1 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2025 | Connected |  | N
National Grid | LYNN | 418004 | 01902 | 15.2 | Solar | 05_01_406L3 | 03/16/2022 | 03/17/2022 | 1 | 0 | 1 | 03/18/2022 | 03/18/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2022 |  | 3/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2022 | Connected |  | N
National Grid | CHELMSFORD | 678598 | 01824 | 5.76 | Solar | 05_01_552L1 | 03/17/2025 | 04/03/2025 | 8 | 6 | 2 | 04/29/2025 | 04/29/2025 | 24 | 0 | 24 | 07/21/2025 | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  | 09/17/2025 | 42 | 0 | 42 |  |  | 0 | 0 | 0 | 9/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 714065 | 01845 | 10 | Solar | 05_01_9J337 | 08/22/2025 | 09/15/2025 | 8 | 2 | 6 | 10/22/2025 | 10/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 11/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | N
National Grid | BILLERICA | 417351 | 01862 | 11.4 | Solar | 05_05_310W3 | 03/28/2022 | 03/29/2022 | 1 | 0 | 1 | 03/30/2022 | 03/30/2022 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 620144 | 01952 | 7.6 | Solar | 05_12_4J2 | 06/25/2024 | 07/10/2024 | 1 | 0 | 1 | 07/11/2024 | 07/11/2024 | 181 | 160 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 605610 | 01523 | 12.35 | Solar | 05_14_24L3 | 04/23/2024 | 05/15/2024 | 11 | 9 | 2 | 05/16/2024 | 05/16/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/23/2024 | 6/7/2025 | Y | EXP | 365 | 07/02/2024 | 07/02/2024 | 1 | 0 | 1 |  |  | 8/8/2024 | Connected |  | N
National Grid | CHARLTON | 174171 | 01507 | 1000 | Solar | 05_14_56L3 | 04/23/2012 | 04/23/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/07/2012 | 07/11/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/12/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 648708 | 01562 | 10 | Solar | 05_14_70L1 | 11/04/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 11/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 731443 | 01604 | 5.76 | Solar | 05_14_7L4 | 11/04/2025 | 11/05/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 26 | 8 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBOROUGH | 645128 | 01772 | 7.6 | Solar | 05_01_227W1 | 10/11/2024 | 11/01/2024 | 2 | 0 | 2 | 11/04/2024 | 11/04/2024 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | LYNN | 428180 | 01902 | 10 | Solar | 05_01_406L3 | 05/04/2022 | 06/10/2022 | 15 | 13 | 2 | 06/13/2022 | 06/13/2022 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 05/04/2022 | 4/3/2024 | Y | EXP | 365 | 03/09/2023 | 04/03/2023 | 26 | 0 | 26 |  |  | 4/12/2023 | Connected |  | N
National Grid | CHELMSFORD | 680821 | 01824 | 20 | Solar | 05_01_552L1 | 03/26/2025 | 04/02/2025 | 6 | 2 | 4 | 04/03/2025 | 04/03/2025 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 | 03/26/2025 | 6/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2026 | Connected |  | N
National Grid | ANDOVER | 731961 | 01845 | 5.76 | Solar | 05_01_9J352 | 11/06/2025 | 11/19/2025 | 4 | 0 | 4 | 12/16/2025 | 12/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 1/16/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 439607 | 01862 | 15.2 | Solar | 05_05_310W3 | 06/23/2022 | 06/29/2022 | 4 | 0 | 4 | 06/30/2022 | 06/30/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2022 |  | 8/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2023 | Connected |  | N
National Grid | SALISBURY | 643453 | 01952 | 5.8 | Solar | 05_12_4J2 | 09/27/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 107 | 83 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LUNENBURG | 656244 | 01462 | 5.76 | Solar | 05_14_24L3 | 11/22/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/22/2024 | 5/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2026 | Connected |  | N
National Grid | OXFORD | 175071 | 01540 | 11.61 | Solar | 05_14_56L3 | 04/08/2013 | 04/08/2013 | 5 | 0 | 5 | 04/17/2013 | 04/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2013 |  | 7/31/2013 | N | EXP | 85 |  |  | 0 | 0 | 0 | 5/7/2013 | 5/7/2013 | 7/29/2013 | Connected |  | N
National Grid | SPENCER | 652988 | 01562 | 3.8 | Solar | 05_14_70L1 | 11/14/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | WORCESTER | 731423 | 01604 | 22.8 | Solar | 05_14_7L4 | 11/05/2025 | 11/12/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 77 | 59 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 660768 | 01772 | 5.76 | Solar | 05_01_227W1 | 12/16/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/16/2024 | 3/11/2026 | Y | EXP | 365 | 05/21/2025 | 05/20/2025 | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | LYNN | 440487 | 01902 | 3.8 | Solar | 05_01_406L3 | 07/01/2022 | 07/05/2022 | 1 | 0 | 1 | 07/06/2022 | 07/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | CHELMSFORD | 682377 | 01824 | 13.36 | Solar | 05_01_552L1 | 04/02/2025 | 07/02/2025 | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 611572 | 01845 | 6 | Solar | 05_01_9J352 | 05/17/2024 | 05/31/2024 | 1 | 0 | 1 | 06/03/2024 | 06/03/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | BILLERICA | 448026 | 01862 | 10 | Solar | 05_05_310W3 | 07/29/2022 | 08/01/2022 | 1 | 0 | 1 | 08/02/2022 | 08/02/2022 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2022 | 07/29/2022 | 9/6/2023 | Y | EXP | 365 | 10/11/2022 | 03/03/2023 | 144 | 0 | 144 |  |  | 3/7/2023 | Connected |  | N
National Grid | SALISBURY | 658811 | 01952 | 5.76 | Solar | 05_12_4J2 | 12/09/2024 | 12/26/2024 | 5 | 0 | 5 | 12/27/2024 | 12/27/2024 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 677775 | 01464 | 13.36 | Solar | 05_14_24L3 | 03/13/2025 | 03/24/2025 | 3 | 0 | 3 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/13/2025 | 6/24/2026 | Y | EXP | 365 | 08/22/2025 | 12/01/2025 | 102 | 0 | 102 |  |  | 1/20/2026 | Connected |  | N
National Grid | OXFORD | 175388 | 01540 | 15.2 | Solar | 05_14_56L3 | 09/10/2014 | 09/10/2014 | 7 | 0 | 7 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2014 |  | 12/1/2014 | N | EXP | 54 |  |  | 0 | 0 | 0 | 10/8/2014 | 10/8/2014 | 12/26/2014 | Connected |  | N
National Grid | SPENCER | 655124 | 01562 | 3.8 | Solar | 05_14_70L1 | 11/20/2024 | 02/25/2025 | 46 | 41 | 5 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 751336 | 01604 | 17.16 | Solar | 05_14_7L4 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SOUTHBOROUGH | 661472 | 01772 | 10 | Solar | 05_01_227W1 | 12/18/2024 | 01/03/2025 | 5 | 0 | 5 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/18/2024 | 2/25/2026 | Y | EXP | 365 | 06/12/2025 | 07/10/2025 | 29 | 0 | 29 |  |  | 7/17/2025 | Connected |  | N
National Grid | LYNN | 473594 | 01902 | 8.41 | Solar | 05_01_406L3 | 12/08/2022 | 12/20/2022 | 8 | 7 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 3/28/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 688712 | 01824 | 15.2 | Solar | 05_01_552L1 | 05/01/2025 | 05/19/2025 | 7 | 3 | 4 | 07/10/2025 | 07/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 8/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | BOXFORD | 636156 | 01921 | 7.6 | Solar | 05_01_9J352 | 09/03/2024 | 09/16/2024 | 3 | 0 | 3 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | BILLERICA | 485238 | 01862 | 15.2 | Solar | 05_05_310W3 | 12/13/2022 | 12/14/2022 | 1 | 0 | 1 | 12/15/2022 | 12/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 |  | 2/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2023 | Connected |  | N
National Grid | SALISBURY | 439647 | 01952 | 480 | Solar | 05_12_51L1 | 02/06/2023 | 02/16/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2023 | 03/21/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 1/19/2027 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 734759 | 01453 | 23 | Solar | 05_14_275L2 | 11/19/2025 | 11/20/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 175526 | 01540 | 750 | Solar | 05_14_56L3 | 07/29/2014 | 07/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/21/2014 | 12/01/2014 | 27 | 1 | 26 | 08/07/2014 | 09/05/2014 | 20 | 0 | 20 |  | 12/01/2014 | 27 | 1 | 26 |  |  | 0 | 0 | 0 | 4/3/2015 | 07/29/2014 | 9/8/2017 | Y | STD | 889 | 02/24/2017 | 09/12/2017 | 138 | 0 | 138 | 8/18/2017 | 8/18/2017 | 9/15/2017 | Connected |  | N
National Grid | SPENCER | 701468 | 01562 | 10.725 | Solar | 05_14_70L1 | 06/26/2025 | 09/03/2025 | 12 | 10 | 2 | 09/04/2025 | 09/04/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2026 | Connected |  | N
National Grid | WORCESTER | 174822 | 01604 | 30 | Solar | 05_14_7L4 | 08/02/2013 | 08/02/2013 | 7 | 1 | 6 | 08/14/2013 | 08/14/2013 | 156 | 3 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2013 |  | 11/29/2013 | N | EXP | 84 |  |  | 0 | 0 | 0 | 12/6/2013 | 12/6/2013 |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 667845 | 01772 | 10 | Solar | 05_01_227W1 | 02/03/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 70 | 49 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 495957 | 01902 | 6.96 | Solar | 05_01_406L3 | 02/03/2023 | 02/08/2023 | 3 | 1 | 2 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/03/2023 | 7/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | N
National Grid | CHELMSFORD | 693410 | 01824 | 4.94 | Solar | 05_01_552L1 | 05/21/2025 | 06/17/2025 | 3 | 0 | 3 | 06/18/2025 | 06/18/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 645610 | 01921 | 3.8 | Solar | 05_01_9J352 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | TEWKSBURY | 556943 | 01876 | 0 | Solar | 05_05_310W3 | 09/20/2023 | 10/05/2023 | 12 | 11 | 1 | 10/06/2023 | 10/06/2023 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  | 3/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/8/2024 | Connected |  | N
National Grid | SALISBURY | 665571 | 01952 | 84.6 | Solar | 05_12_51L1 | 02/14/2025 | 03/28/2025 | 29 | 20 | 9 | 03/31/2025 | 03/31/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2025 |  | 12/31/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LANCASTER | 174700 | 01523 | 595 | Solar | 05_14_275L2 | 01/03/2013 | 01/03/2013 | 7 | 0 | 7 | 01/15/2013 | 01/15/2013 | 332 | 0 | 332 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2013 |  | 5/31/2013 | N | EXP | 29 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 |  | Withdrawn |  | N
National Grid | CHARLTON | 176627 | 01507 | 1000 | Solar | 05_14_56L3 | 10/15/2015 | 10/15/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 11/24/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2017 | 10/15/2015 | 3/22/2019 | Y | STD | 695 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 507609 | 01562 | 450 | Solar | 05_14_70L2 | 07/07/2023 | 07/25/2023 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2023 | 08/21/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 | 07/07/2023 | 1/5/2027 | Y | STD | 38 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WORCESTER | 175002 | 01604 | 150 | Solar | 05_14_7L4 | 09/12/2013 | 09/12/2013 | 6 | 0 | 6 | 09/23/2013 | 09/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2013 |  | 11/29/2013 | N | EXP | 36 |  |  | 0 | 0 | 0 | 2/28/2014 | 2/28/2014 | 3/7/2014 | Connected |  | N
National Grid | SOUTHBOROUGH | 683029 | 01772 | 3.8 | Solar | 05_01_227W1 | 04/04/2025 | 05/13/2025 | 4 | 0 | 4 | 05/14/2025 | 05/14/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 | 04/04/2025 | 6/24/2026 | Y | EXP | 365 | 09/03/2025 | 10/28/2025 | 56 | 0 | 56 |  |  | 11/4/2025 | Connected |  | N
National Grid | BEVERLY | 524689 | 01915 | 0 | Solar | 05_01_406L3 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 199 | 180 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 697891 | 01913 | 15.2 | Solar | 05_01_552L1 | 06/11/2025 | 06/23/2025 | 7 | 4 | 3 | 06/24/2025 | 06/24/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | BOXFORD | 660942 | 01921 | 5.76 | Solar | 05_01_9J352 | 12/16/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | Y
National Grid | TEWKSBURY | 613596 | 01876 | 7.6 | Solar | 05_05_310W3 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | SALISBURY | 703620 | 01952 | 0 | Other | 05_12_51L1 | 09/22/2025 | 11/24/2025 | 41 | 34 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 12/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LEOMINSTER | 174806 | 01453 | 300 | Solar | 05_14_275L2 | 01/23/2013 | 01/23/2013 | 7 | 0 | 7 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2013 |  | 6/28/2013 | N | EXP | 92 |  |  | 0 | 0 | 0 | 3/28/2013 | 3/28/2013 | 8/22/2013 | Connected |  | N
National Grid | OXFORD | 177771 | 01540 | 15.2 | Solar | 05_14_56L3 | 10/10/2017 | 10/10/2017 | 13 | 4 | 9 | 11/06/2017 | 11/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2017 |  | 10/16/2018 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 5/23/2018 | Connected |  | N
National Grid | SPENCER | 708850 | 01562 | 17.16 | Solar | 05_14_70L2 | 08/08/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 19 | 0 | 19 | 10/30/2025 | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 12/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 175524 | 01604 | 500 | Solar | 05_14_7L4 | 07/28/2014 | 07/28/2014 | 7 | 0 | 7 | 08/07/2014 | 08/07/2014 | 0 | 0 | 0 | 09/24/2014 | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 11/06/2014 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 2/6/2015 | 07/28/2014 | 12/31/2016 | Y | EXP | 694 | 05/30/2017 | 06/24/2017 | 19 | 0 | 19 | 8/1/2017 | 8/1/2017 | 8/4/2017 | Connected |  | N
National Grid | SOUTHBOROUGH | 688672 | 01772 | 12.16 | Solar | 05_01_227W1 | 05/07/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | BEVERLY | 526264 | 01915 | 7.6 | Solar | 05_01_406L3 | 05/22/2023 | 05/25/2023 | 3 | 0 | 3 | 05/26/2023 | 05/26/2023 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/22/2023 | 7/9/2024 | Y | EXP | 365 | 08/10/2023 | 09/11/2023 | 33 | 0 | 33 |  |  | 10/4/2023 | Connected |  | N
National Grid | AMESBURY | 703266 | 01913 | 18.829 | Solar | 05_01_552L1 | 07/07/2025 | 07/10/2025 | 3 | 0 | 3 | 07/11/2025 | 07/11/2025 | 71 | 53 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 671945 | 01845 | 3.8 | Solar | 05_01_9J352 | 02/20/2025 | 03/26/2025 | 8 | 4 | 4 | 03/27/2025 | 03/27/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 616124 | 01821 | 15.2 | Solar | 05_05_310W3 | 06/06/2024 | 06/14/2024 | 6 | 4 | 2 | 06/17/2024 | 06/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | SALISBURY | 721660 | 01952 | 38.08 | Solar | 05_12_51L1 | 10/01/2025 | 10/06/2025 | 2 | 0 | 2 | 10/07/2025 | 10/07/2025 | 72 | 60 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LEOMINSTER | 176392 | 01453 | 300 | Solar | 05_14_275L2 | 02/02/2016 | 02/02/2016 | 1 | 1 | 0 | 02/04/2016 | 02/04/2016 | 0 | 0 | 0 | 03/16/2016 | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2016 |  | 9/15/2016 | N | EXP | 183 |  |  | 0 | 0 | 0 | 9/29/2016 | 9/29/2016 | 9/30/2016 | Connected |  | N
National Grid | OXFORD | 177817 | 01540 | 11.4 | Solar | 05_14_56L3 | 04/04/2017 | 04/04/2017 | 2 | 0 | 2 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 |  | 4/10/2018 | N | EXP | 365 |  |  | 0 | 0 | 0 | 9/22/2017 | 9/22/2017 | 9/22/2017 | Connected |  | N
National Grid | SPENCER | 725438 | 01562 | 8.725 | Solar | 05_14_70L2 | 10/14/2025 | 10/22/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 28 | 11 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 | 10/14/2025 | 12/31/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 176047 | 01604 | 42 | Solar | 05_14_7L4 | 01/26/2015 | 01/26/2015 | 4 | 0 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 6/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 3/31/2015 | Connected |  | N
National Grid | SOUTHBOROUGH | 345461 | 01772 | 800 | Solar | 05_01_227W3 | 04/07/2021 | 11/15/2021 | 127 | 122 | 5 |  |  | 101 | 64 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BEVERLY | 568942 | 01915 | 14.79 | Solar | 05_01_406L3 | 11/08/2023 | 11/13/2023 | 2 | 1 | 1 | 11/14/2023 | 11/14/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2023 | 11/08/2023 | 12/20/2024 | Y | EXP | 365 | 02/16/2024 | 02/16/2024 | 1 | 0 | 1 |  |  | 4/3/2024 | Connected |  | N
National Grid | AMESBURY | 712272 | 01913 | 5.76 | Solar | 05_01_552L1 | 08/14/2025 | 09/05/2025 | 3 | 0 | 3 | 12/11/2025 | 12/11/2025 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 722531 | 01921 | 15.36 | Solar | 05_01_9J352 | 09/29/2025 | 10/27/2025 | 19 | 17 | 2 | 10/28/2025 | 10/28/2025 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | BILLERICA | 174829 | 01821 | 270 | Solar | 05_05_310W4 | 12/01/2011 | 12/01/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2012 | 12/01/2011 | 7/9/2012 | Y | EXP | 178 | 06/20/2012 | 06/28/2012 | 6 | 0 | 6 | 8/8/2012 | 8/8/2012 | 7/9/2012 | Connected |  | N
National Grid | SALISBURY | 727172 | 01952 | 10 | Solar | 05_12_51L1 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 11/13/2025 | 11/13/2025 | 23 | 1 | 22 | 01/13/2026 | 01/28/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 01/28/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 3/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SHIRLEY | 177136 | 01464 | 7.6 | Solar | 05_14_275L2 | 05/27/2016 | 05/27/2016 | 1 | 1 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2016 |  | 6/5/2017 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/23/2016 | 9/23/2016 | 9/28/2016 | Connected |  | N
National Grid | OXFORD | 178587 | 01540 | 20 | Solar | 05_14_56L3 | 03/13/2018 | 03/13/2018 | 13 | 0 | 13 | 04/02/2018 | 04/02/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/19/2019 | N | EXP | 312 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 749075 | 01562 | 11.4 | Solar | 05_14_70L2 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 177992 | 01604 | 7.6 | Solar | 05_14_7L4 | 10/24/2017 | 10/24/2017 | 5 | 5 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2017 |  | 11/1/2018 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  | 2/5/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 394134 | 01772 | 700 | Solar | 05_01_227W3 | 01/17/2022 | 05/24/2022 | 87 | 77 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2022 | 06/27/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | BEVERLY | 568197 | 01915 | 0 | Battery Add-On | 05_01_406L3 | 11/02/2023 | 12/13/2023 | 27 | 24 | 3 | 12/14/2023 | 12/14/2023 | 93 | 69 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | AMESBURY | 715142 | 01913 | 0 | Battery Add-On | 05_01_552L1 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | BOXFORD | 743749 | 01921 | 5.7 | Solar | 05_01_9J360 | 01/06/2026 | 01/28/2026 | 2 | 0 | 2 | 02/05/2026 | 02/05/2026 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | BILLERICA | 175196 | 01821 | 100 | Solar | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SALISBURY | 174524 | 01952 | 75 | Natural Gas | 05_12_51L1 | 04/14/2011 | 04/14/2011 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 4/13/2011 | 4/13/2011 | 4/13/2011 | Connected |  | N
National Grid | SHIRLEY | 177161 | 01464 | 80 | Solar | 05_14_275L2 | 10/28/2016 | 10/28/2016 | 2 | 2 | 0 | 11/03/2016 | 11/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 | 10/28/2016 | 11/6/2017 | Y | EXP | 362 | 01/09/2017 | 05/09/2017 | 83 | 0 | 83 | 6/12/2017 | 6/12/2017 | 6/12/2017 | Connected |  | N
National Grid | OXFORD | 189024 | 01540 | 0 | Solar | 05_14_56L3 | 08/24/2018 | 09/26/2018 | 22 | 15 | 7 | 09/27/2018 | 09/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 | 08/24/2018 |  | Y | EXP | 365 | 03/22/2019 | 03/21/2019 | 0 | 0 | 0 |  |  | 7/3/2019 | Connected |  | N
National Grid | SPENCER | 193712 | 01562 | 1491 | Solar | 05_14_70L2 | 09/24/2018 | 11/13/2018 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 04/02/2019 | 145 | 77 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178166 | 01604 | 11.4 | Solar | 05_14_7L4 | 02/14/2018 | 02/14/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2018 |  | 2/20/2019 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  | 10/3/2019 | Connected |  | N
National Grid | MARLBOROUGH | 434882 | 01752 | 2400 | Solar | 05_01_227W3 | 01/12/2023 | 04/25/2023 | 70 | 61 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2023 | 05/23/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BEVERLY | 578775 | 01915 | 6.09 | Solar | 05_01_406L3 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | AMESBURY | 725840 | 01913 | 5.76 | Solar | 05_01_552L1 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | BOXFORD | 177344 | 01921 | 15.2 | Solar | 05_01_9J360 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 1/26/2018 | N | EXP | 422 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 1/9/2018 | Connected |  | N
National Grid | BILLERICA | 175202 | 01821 | 110 | Solar | 05_05_310W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | SALISBURY | 175168 | 01952 | 60 | Solar | 05_12_51L1 | 11/14/2012 | 11/14/2012 | 15 | 9 | 6 | 12/11/2012 | 12/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2013 |  | 1/31/2013 | N | EXP | 41 |  |  | 0 | 0 | 0 | 6/25/2013 | 6/25/2013 | 8/21/2013 | Connected |  | N
National Grid | SHIRLEY | 202349 | 01464 | 7.6 | Solar | 05_14_275L2 | 01/09/2019 | 01/18/2019 | 6 | 0 | 6 | 01/22/2019 | 01/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/09/2019 | 9/16/2020 | Y | EXP | 365 | 04/17/2020 | 05/12/2020 | 25 | 0 | 25 |  |  | 7/25/2020 | Connected |  | N
National Grid | OXFORD | 198628 | 01540 | 20 | Solar | 05_14_56L3 | 10/17/2018 | 10/31/2018 | 3 | 3 | 0 | 11/01/2018 | 11/01/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 1/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | Connected |  | N
National Grid | SPENCER | 256057 | 01562 | 10 | Solar | 05_14_70L2 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2019 | 10/10/2019 | 7/7/2020 | Y | EXP | 365 | 01/29/2020 | 02/25/2020 | 27 | 0 | 27 |  |  | 6/8/2020 | Connected |  | N
National Grid | WORCESTER | 178204 | 01604 | 4000 | Solar | 05_14_7L4 | 02/07/2018 | 02/07/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 04/18/2018 | 28 | 21 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 | 02/07/2018 | 2/25/2021 | Y | STD | 833 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 644479 | 01752 | 160 | Solar | 05_01_227W3 | 10/02/2024 | 01/28/2025 | 77 | 67 | 10 | 01/29/2025 | 01/29/2025 | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BEVERLY | 579001 | 01915 | 140 | Solar | 05_01_406L3 | 12/21/2023 | 01/07/2024 | 10 | 0 | 10 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 681154 | 01913 | 15.2 | Solar | 05_01_552L3 | 03/31/2025 | 04/01/2025 | 1 | 0 | 1 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BOXFORD | 197281 | 01921 | 10 | Solar | 05_01_9J360 | 10/01/2018 | 10/22/2018 | 3 | 3 | 0 | 10/23/2018 | 10/23/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 | 10/01/2018 | 6/4/2019 | Y | EXP | 224 | 03/21/2019 | 03/20/2019 | 0 | 0 | 0 |  |  | 5/4/2019 | Connected |  | N
National Grid | BILLERICA | 175850 | 01821 | 300 | Solar | 05_05_310W4 | 05/20/2015 | 05/20/2015 | 2 | 2 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 | 07/30/2015 | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  | 09/03/2015 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 9/22/2015 |  | 12/31/2016 | N | EXP | 466 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 1/9/2017 | Connected |  | N
National Grid | SALISBURY | 175151 | 01952 | 224 | Solar | 05_12_51L1 | 10/30/2013 | 10/30/2013 | 5 | 0 | 5 | 11/07/2013 | 11/07/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 10/30/2013 | 5/30/2014 | Y | EXP | 17 | 08/04/2014 | 08/04/2014 | 0 | 0 | 0 | 8/6/2014 | 8/6/2014 | 8/7/2014 | Connected |  | N
National Grid | SHIRLEY | 208390 | 01464 | 7.6 | Solar | 05_14_275L2 | 03/01/2019 | 03/04/2019 | 0 | 0 | 0 | 03/05/2019 | 03/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 03/01/2019 | 9/1/2020 | Y | EXP | 414 | 04/18/2020 | 05/06/2020 | 18 | 0 | 18 |  |  | 8/19/2020 | Connected |  | N
National Grid | OXFORD | 203369 | 01540 | 0 | Solar | 05_14_56L3 | 12/12/2018 | 12/24/2018 | 7 | 0 | 7 | 12/26/2018 | 12/26/2018 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | SPENCER | 406289 | 01562 | 0 | Battery Add-On | 05_14_70L2 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 184636 | 01604 | 7.6 | Solar | 05_14_7L4 | 05/10/2018 | 05/10/2018 | 11 | 0 | 11 | 05/17/2018 | 05/17/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2018 | 05/10/2018 | 6/3/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2019 | Connected |  | N
National Grid | MARLBOROUGH | 727101 | 01752 | 3.8 | Solar | 05_01_227W3 | 10/17/2025 | 11/03/2025 | 10 | 5 | 5 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 594064 | 01915 | 7.6 | Solar | 05_01_406L3 | 03/06/2024 | 03/12/2024 | 4 | 0 | 4 | 03/13/2024 | 03/13/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | AMESBURY | 753860 | 01913 | 13.5 | Battery Add-On | 05_01_552L3 | 03/02/2026 |  | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BOXFORD | 232897 | 01921 | 7.6 | Solar | 05_01_9J360 | 06/19/2019 | 07/08/2019 | 12 | 12 | 0 | 07/09/2019 | 07/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 | 06/19/2019 | 7/20/2020 | Y | EXP | 365 | 04/09/2020 | 05/15/2020 | 34 | 0 | 34 |  |  | 5/18/2020 | Connected |  | N
National Grid | BILLERICA | 177333 | 01821 | 784 | Solar | 05_05_310W4 | 08/30/2016 | 08/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2016 | 09/28/2016 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 175845 | 01952 | 401 | Solar | 05_12_51L1 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/22/2015 | 05/22/2015 | 366 | 0 | 366 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 245163 | 01464 | 4990 | Solar | 05_14_275L2 | 03/05/2020 | 03/26/2020 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2020 | 05/21/2020 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 03/05/2020 | 5/15/2030 | Y | STD | 219 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLTON | 213064 | 01507 | 0 | Solar | 05_14_56L3 | 03/11/2019 | 03/21/2019 | 7 | 0 | 7 | 03/22/2019 | 03/22/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  | 4/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | BROOKFIELD | 652181 | 01515 | 7.6 | Solar | 05_14_70L2 | 02/14/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | WORCESTER | 193070 | 01604 | 246.5 | Solar | 05_14_7L4 | 08/08/2018 | 08/22/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/26/2018 | 11/01/2018 | 5 | 1 | 4 | 08/23/2018 | 09/26/2018 | 24 | 6 | 18 |  | 11/01/2018 | 5 | 1 | 4 |  |  | 0 | 0 | 0 | 4/15/2020 | 08/08/2018 | 11/23/2022 | Y | STD | 98 |  |  | 0 | 0 | 0 |  |  | 10/25/2022 | Connected |  | N
National Grid | MARLBOROUGH | 742930 | 01752 |  | Battery Add-On | 05_01_227W3 | 01/02/2026 | 01/06/2026 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 594844 | 01915 | 6 | Solar | 05_01_406L3 | 03/06/2024 | 03/26/2024 | 15 | 12 | 3 | 03/27/2024 | 03/27/2024 | 21 | 17 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 03/06/2024 | 4/30/2025 | Y | EXP | 365 | 06/11/2024 | 08/19/2024 | 70 | 0 | 70 |  |  | 8/20/2024 | Connected |  | N
National Grid | AMESBURY | 174944 | 01913 | 333 | Solar | 05_01_552L3 | 09/29/2011 | 09/29/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2012 | 09/29/2011 | 11/30/2012 | Y | STD | 19 | 07/29/2013 | 09/13/2013 | 33 | 0 | 33 | 9/11/2013 | 9/11/2013 | 9/11/2013 | Connected |  | N
National Grid | BOXFORD | 241416 | 01921 | 7.36 | Solar | 05_01_9J360 | 07/16/2019 | 07/17/2019 | 1 | 1 | 0 | 07/18/2019 | 07/18/2019 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 | 07/16/2019 | 11/9/2020 | Y | EXP | 365 | 08/22/2020 | 10/02/2020 | 41 | 0 | 41 |  |  | 11/4/2020 | Connected |  | N
National Grid | BILLERICA | 177480 | 01862 | 952 | Solar | 05_05_310W4 | 07/07/2016 | 07/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/08/2016 | 09/19/2016 | 50 | 29 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/13/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 175842 | 01952 | 100 | Solar | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2015 | N | EXP |  | 07/28/2016 | 03/12/2015 | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 300662 | 01464 | 7.6 | Solar | 05_14_275L2 | 08/06/2020 | 08/11/2020 | 3 | 1 | 2 | 08/12/2020 | 08/12/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/06/2020 | 12/6/2021 | Y | EXP | 365 | 03/24/2021 | 04/06/2021 | 13 | 0 | 13 |  |  | 10/5/2021 | Connected |  | N
National Grid | OXFORD | 236527 | 01540 | 0 | Solar | 05_14_56L3 | 06/13/2019 | 06/18/2019 | 2 | 0 | 2 | 06/19/2019 | 06/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2019 | 06/13/2019 | 6/13/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2020 | Connected |  | N
National Grid | SPENCER | 679382 | 01562 | 11.5 | Solar | 05_14_70L2 | 03/21/2025 | 03/25/2025 | 2 | 0 | 2 | 03/26/2025 | 03/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2025 | Connected |  | N
National Grid | WORCESTER | 252060 | 01604 | 7.6 | Solar | 05_14_7L4 | 09/11/2019 | 09/18/2019 | 4 | 0 | 4 | 09/19/2019 | 09/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2019 | 09/11/2019 | 9/11/2020 | Y | EXP | 365 | 02/01/2020 | 02/05/2020 | 4 | 0 | 4 |  |  | 2/14/2020 | Connected |  | N
National Grid | MARLBOROUGH | 174232 | 01752 | 2000 | Solar | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 |  | 11/1/2012 | N | STD | 82 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 635916 | 01915 | 6 | Solar | 05_01_406L3 | 08/27/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/27/2024 | 10/8/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/27/2025 | Connected |  | N
National Grid | AMESBURY | 175797 | 01913 | 990 | Solar | 05_01_552L3 | 02/27/2015 | 02/27/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 | 03/09/2015 | 04/06/2015 | 19 | 0 | 19 |  | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 257227 | 01921 | 7.6 | Solar | 05_01_9J360 | 10/14/2019 | 10/15/2019 | 0 | 0 | 0 | 10/16/2019 | 10/16/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 | 10/14/2019 | 10/14/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2020 | Connected |  | N
National Grid | BILLERICA | 374486 | 01821 | 9.6 | Solar | 05_05_310W4 | 08/11/2021 | 08/18/2021 | 5 | 1 | 4 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 08/11/2021 | 12/22/2023 | Y | EXP | 365 | 04/07/2022 | 12/21/2022 | 259 | 0 | 259 |  |  | 1/26/2023 | Connected |  | N
National Grid | SALISBURY | 175841 | 01952 | 100 | Solar | 05_12_51L1 | 03/06/2015 | 03/06/2015 | 5 | 0 | 5 | 03/16/2015 | 03/16/2015 | 756 | 0 | 756 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/06/2015 | 6/29/2018 | Y | EXP | 1128 | 07/28/2016 |  | 416 | 0 | 416 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | SHIRLEY | 348110 | 01464 | 9.8 | Solar | 05_14_275L2 | 04/08/2021 | 04/12/2021 | 1 | 0 | 1 | 04/13/2021 | 04/13/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/12/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 285483 | 01540 | 9.28 | Solar | 05_14_56L3 | 03/27/2020 | 03/31/2020 | 2 | 2 | 0 | 04/01/2020 | 04/01/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 03/27/2020 | 3/31/2021 | Y | EXP | 365 | 06/09/2020 | 06/25/2020 | 16 | 0 | 16 |  |  | 10/7/2020 | Connected |  | N
National Grid | BROOKFIELD | 745032 | 01506 | 10 | Solar | 05_14_70L3 | 01/13/2026 | 01/20/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 277711 | 01604 | 5 | Solar | 05_14_7L4 | 02/06/2020 | 02/18/2020 | 6 | 6 | 0 | 02/19/2020 | 02/19/2020 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 | 02/06/2020 | 2/18/2021 | Y | EXP | 365 | 06/09/2020 | 06/11/2020 | 2 | 0 | 2 |  |  | 6/13/2020 | Connected |  | N
National Grid | MARLBOROUGH | 174230 | 01752 | 2500 | Solar | 05_01_227W3 | 01/31/2012 | 01/31/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2013 | 01/31/2012 | 6/30/2014 | Y | STD | 524 | 01/13/2014 | 07/18/2014 | 127 | 0 | 127 | 1/9/2014 | 1/9/2014 | 1/9/2014 | Connected |  | N
National Grid | BEVERLY | 636073 | 01915 | 7.6 | Solar | 05_01_406L3 | 08/28/2024 | 10/10/2024 | 17 | 13 | 4 | 10/11/2024 | 10/11/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 176143 | 01913 | 76 | Solar | 05_01_552L3 | 06/29/2015 | 06/29/2015 | 1 | 1 | 0 | 07/02/2015 | 07/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 | 06/29/2015 | 7/6/2016 | Y | EXP | 35 | 11/12/2015 | 11/30/2015 | 11 | 0 | 11 | 7/22/2015 | 7/22/2015 | 1/15/2016 | Connected |  | N
National Grid | BOXFORD | 623844 | 01921 | 7.6 | Solar | 05_01_9J360 | 07/10/2024 | 07/16/2024 | 1 | 0 | 1 | 07/17/2024 | 07/17/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2024 | Connected |  | N
National Grid | BILLERICA | 473967 | 01821 | 15.2 | Solar | 05_05_310W4 | 11/03/2022 | 11/08/2022 | 2 | 0 | 2 | 11/09/2022 | 11/09/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2022 |  | 1/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2023 | Connected |  | N
National Grid | SALISBURY | 175920 | 01952 | 9.8 | Solar | 05_12_51L1 | 05/28/2015 | 05/28/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LANCASTER | 574491 | 01523 | 10 | Solar | 05_14_275L2 | 01/12/2024 | 01/22/2024 | 5 | 4 | 1 | 01/23/2024 | 01/23/2024 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/12/2024 | 2/14/2025 | Y | EXP | 365 | 04/24/2024 | 05/07/2024 | 14 | 0 | 14 |  |  | 5/14/2024 | Connected |  | N
National Grid | OXFORD | 290378 | 01540 | 0 | Solar | 05_14_56L3 | 05/04/2020 | 05/12/2020 | 5 | 0 | 5 | 05/13/2020 | 05/13/2020 | 66 | 56 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 11/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | BROOKFIELD | 176707 | 01515 | 3.8 | Solar | 05_14_70L3 | 10/27/2015 | 10/27/2015 | 2 | 2 | 0 | 10/30/2015 | 10/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2015 |  | 11/2/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 4/27/2016 | 4/27/2016 | 7/26/2016 | Connected |  | N
National Grid | WORCESTER | 301879 | 01604 | 0 | Solar | 05_14_7L4 | 07/17/2020 | 07/20/2020 | 0 | 0 | 0 | 07/21/2020 | 07/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2020 | Connected |  | N
National Grid | MARLBOROUGH | 174493 | 01752 | 232 | Solar | 05_01_227W3 | 06/13/2011 | 06/13/2011 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2011 |  | 3/7/2012 | N | STD | 156 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 3/7/2012 | Connected |  | N
National Grid | BEVERLY | 637279 | 01915 | 6 | Solar | 05_01_406L3 | 09/03/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | AMESBURY | 176145 | 01913 | 100 | Solar | 05_01_552L3 | 06/30/2015 | 06/30/2015 | 2 | 2 | 0 | 07/03/2015 | 07/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2015 |  | 7/6/2016 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 2/18/2016 | Connected |  | N
National Grid | ANDOVER | 633459 | 01845 | 5.76 | Solar | 05_01_9J360 | 08/19/2024 | 08/22/2024 | 1 | 0 | 1 | 08/23/2024 | 08/23/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2024 |  | 9/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | CHELMSFORD | 617968 | 01824 | 11.4 | Solar | 05_05_310W4 | 06/14/2024 | 07/03/2024 | 10 | 9 | 1 | 07/05/2024 | 07/05/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 175991 | 01952 | 100 | Solar | 05_12_51L1 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 | 03/26/2015 | 03/26/2015 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 | 03/23/2015 | 5/31/2018 | Y | EXP | 199 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 |  | Withdrawn |  | N
National Grid | LANCASTER | 613959 | 01523 | 10 | Solar | 05_14_275L2 | 05/30/2024 | 06/24/2024 | 11 | 7 | 4 | 06/25/2024 | 06/25/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 317831 | 01540 | 25 | Solar | 05_14_56L3 | 10/07/2020 | 10/09/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | BROOKFIELD | 178184 | 01515 | 3.8 | Solar | 05_14_70L3 | 04/13/2018 | 04/13/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2019 |  | 4/21/2019 | N | EXP | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 311019 | 01604 | 7.6 | Solar | 05_14_7L4 | 09/22/2020 | 09/23/2020 | 0 | 0 | 0 | 09/24/2020 | 09/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 10/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175662 | 01752 | 996 | Solar | 05_01_227W3 | 08/07/2014 | 08/07/2014 | 8 | 4 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 09/19/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 | 08/07/2014 | 6/15/2016 | Y | STD | 422 | 11/03/2015 | 01/30/2016 | 59 | 0 | 59 | 12/31/2015 | 12/31/2015 | 12/31/2015 | Connected |  | N
National Grid | BEVERLY | 638781 | 01915 | 5.76 | Solar | 05_01_406L3 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/09/2024 | 3/5/2026 | Y | EXP | 365 | 06/12/2025 | 12/08/2025 | 180 | 0 | 180 |  |  | 12/1/2025 | Connected |  | N
National Grid | AMESBURY | 176690 | 01913 | 496 | Solar | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/13/2018 | Connected |  | N
National Grid | BOXFORD | 636201 | 01921 | 5.76 | Solar | 05_01_9J360 | 08/28/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 649246 | 01852 | 11.4 | Solar | 05_05_310W4 | 10/26/2024 | 11/19/2024 | 2 | 0 | 2 | 11/20/2024 | 11/20/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 176135 | 01952 | 3520 | Solar | 05_12_51L1 | 04/16/2015 | 04/16/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/20/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 09/06/2017 | 07/27/2018 | 224 | 0 | 224 | 8/4/2016 | 04/16/2015 | 12/31/2020 | Y | STD | 131 | 05/22/2020 | 10/26/2020 | 158 | 5 | 153 |  |  | 12/23/2020 | Connected |  | N
National Grid | AYER | 653578 | 01432 | 16 | Solar | 05_14_275L2 | 11/11/2024 | 11/27/2024 | 12 | 10 | 2 | 12/02/2024 | 12/02/2024 | 102 | 26 | 76 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 318384 | 01540 | 10 | Solar | 05_14_56L3 | 10/09/2020 | 10/14/2020 | 2 | 2 | 0 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | BROOKFIELD | 190106 | 01515 | 6 | Solar | 05_14_70L3 | 07/11/2018 | 07/18/2018 | 0 | 0 | 0 | 07/19/2018 | 07/19/2018 | 49 | 1 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 329558 | 01604 | 7.6 | Solar | 05_14_7L4 | 12/21/2020 | 12/30/2020 | 5 | 0 | 5 | 12/31/2020 | 12/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 | 12/21/2020 | 9/14/2022 | Y | EXP | 365 | 07/20/2021 | 09/10/2021 | 52 | 3 | 49 |  |  | 9/27/2021 | Connected |  | N
National Grid | MARLBOROUGH | 175671 | 01752 | 1008 | Solar | 05_01_227W3 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2014 | 11/19/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 644256 | 01915 | 5.76 | Solar | 05_01_406L3 | 10/01/2024 | 10/25/2024 | 2 | 0 | 2 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/01/2024 | 12/12/2025 | Y | EXP | 365 | 03/19/2025 | 03/20/2025 | 2 | 0 | 2 |  |  | 4/7/2025 | Connected |  | N
National Grid | AMESBURY | 176719 | 01913 | 496 | Solar | 05_01_552L3 | 02/19/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2016 | 03/16/2016 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2016 | 02/19/2016 | 12/28/2018 | Y | STD | 821 | 12/19/2018 | 12/18/2018 | 0 | 0 | 0 |  |  | 12/24/2018 | Connected |  | N
National Grid | BOXFORD | 641893 | 01921 | 5.76 | Solar | 05_01_9J360 | 09/20/2024 | 02/21/2025 | 3 | 0 | 3 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | CHELMSFORD | 744230 | 01824 | 5.76 | Solar | 05_05_310W4 | 01/08/2026 | 01/09/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 30 | 17 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 176345 | 01952 | 6.67 | Solar | 05_12_51L1 | 02/25/2015 | 02/25/2015 | 9 | 5 | 4 | 03/11/2015 | 03/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 02/25/2015 | 12/31/2016 | Y | EXP | 655 | 02/11/2016 | 04/30/2016 | 54 | 0 | 54 | 3/17/2015 | 3/17/2015 | 10/12/2016 | Connected |  | N
National Grid | SHIRLEY | 655738 | 01464 | 3.8 | Solar | 05_14_275L2 | 11/20/2024 | 12/02/2024 | 2 | 0 | 2 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | OXFORD | 347094 | 01540 | 9.966 | Solar | 05_14_56L3 | 03/26/2021 | 04/09/2021 | 10 | 10 | 0 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 | 03/26/2021 | 8/17/2022 | Y | EXP | 365 | 08/04/2021 | 08/12/2021 | 9 | 0 | 9 |  |  | 11/3/2021 | Connected |  | N
National Grid | BROOKFIELD | 253690 | 01506 | 10 | Solar | 05_14_70L3 | 09/17/2019 | 09/30/2019 | 8 | 2 | 6 | 10/01/2019 | 10/01/2019 | 19 | 17 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2019 |  | 9/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/18/2020 | Connected |  | N
National Grid | WORCESTER | 371237 | 01604 | 10 | Solar | 05_14_7L4 | 07/21/2021 | 09/28/2021 | 48 | 38 | 10 | 09/29/2021 | 09/29/2021 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 9/27/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175811 | 01752 | 15.2 | Solar | 05_01_227W3 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2015 |  | 1/5/2018 | N | EXP | 938 |  |  | 0 | 0 | 0 | 6/22/2015 | 6/22/2015 |  | Withdrawn |  | Y
National Grid | BEVERLY | 644606 | 01915 | 10 | Solar | 05_01_406L3 | 10/03/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/03/2024 | 12/2/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177414 | 01913 | 20.2 | Solar | 05_01_552L3 | 09/12/2016 | 09/12/2016 | 10 | 10 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2016 | 09/12/2016 | 9/18/2017 | Y | EXP | 354 | 12/28/2016 | 01/05/2017 | 5 | 0 | 5 | 1/12/2017 | 1/12/2017 | 1/12/2017 | Connected |  | N
National Grid | ANDOVER | 650128 | 01845 | 6 | Solar | 05_01_9J360 | 10/28/2024 | 11/12/2024 | 6 | 0 | 6 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | LOWELL | 343005 | 01852 | 208.2 | Solar | 05_05_310W5 | 02/19/2021 | 03/05/2021 | 9 | 0 | 9 |  |  | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 | 02/19/2021 | 4/3/2027 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SALISBURY | 176394 | 01952 | 10 | Solar | 05_12_51L1 | 02/02/2016 | 02/02/2016 | 4 | 4 | 0 | 02/09/2016 | 02/09/2016 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2016 |  | 2/8/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHIRLEY | 664839 | 01464 | 15.2 | Solar | 05_14_275L2 | 01/10/2025 | 02/11/2025 | 16 | 11 | 5 | 02/12/2025 | 02/12/2025 | 54 | 37 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 | 01/10/2025 | 5/28/2026 | Y | EXP | 365 | 09/30/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 11/4/2025 | Connected |  | N
National Grid | CHARLTON | 365918 | 01507 | 15.36 | Solar | 05_14_56L3 | 06/24/2021 | 06/30/2021 | 4 | 0 | 4 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 313391 | 01506 | 10 | Solar | 05_14_70L3 | 09/17/2020 | 10/27/2020 | 26 | 25 | 1 | 10/28/2020 | 10/28/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | Y
National Grid | WORCESTER | 427409 | 01604 | 60 | Solar | 05_14_7L4 | 05/09/2022 | 05/19/2022 | 8 | 0 | 8 | 05/20/2022 | 05/20/2022 | 35 | 17 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 | 05/09/2022 | 9/22/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2022 | Connected |  | N
National Grid | MARLBOROUGH | 175924 | 01752 | 997.6 | Solar | 05_01_227W3 | 05/29/2015 | 05/29/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2015 | 07/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2016 | 05/29/2015 | 11/30/2015 | Y | STD | 58 |  |  | 0 | 0 | 0 | 8/1/2017 | 8/1/2017 | 8/1/2017 | Connected |  | N
National Grid | BEVERLY | 644594 | 01915 | 10 | Solar | 05_01_406L3 | 10/02/2024 | 11/04/2024 | 4 | 0 | 4 | 11/05/2024 | 11/05/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | AMESBURY | 177614 | 01913 | 1000 | Solar | 05_01_552L3 | 09/22/2017 | 10/09/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2017 | 10/31/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 | 09/22/2017 | 12/21/2020 | Y | STD | 644 | 05/20/2020 | 09/11/2020 | 115 | 5 | 110 |  |  | 12/14/2020 | Connected |  | N
National Grid | BOXFORD | 652574 | 01921 | 8.41 | Solar | 05_01_9J360 | 11/06/2024 | 12/11/2024 | 13 | 7 | 6 | 12/12/2024 | 12/12/2024 | 65 | 50 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 342944 | 01862 | 191.6 | Solar | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 | 02/18/2021 | 3/16/2027 | Y | STD | 488 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SALISBURY | 177713 | 01952 | 108 | Solar | 05_12_51L1 | 07/26/2017 | 07/26/2017 | 30 | 29 | 1 | 09/07/2017 | 09/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 | 07/26/2017 | 7/31/2018 | Y | EXP | 322 | 09/12/2017 | 09/12/2017 | 29 | 29 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | SHIRLEY | 686893 | 01464 | 10 | Solar | 05_14_275L2 | 05/01/2025 | 05/21/2025 | 4 | 0 | 4 | 05/22/2025 | 05/22/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 | 05/01/2025 | 6/17/2026 | Y | EXP | 365 | 10/01/2025 | 10/07/2025 | 7 | 0 | 7 |  |  | 10/11/2025 | Connected |  | N
National Grid | CHARLTON | 378271 | 01507 | 0 | Solar | 05_14_56L3 | 08/26/2021 | 09/14/2021 | 13 | 10 | 3 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 10/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2022 | Connected |  | N
National Grid | BROOKFIELD | 449194 | 01515 | 15.2 | Solar | 05_14_70L3 | 08/03/2022 | 08/11/2022 | 6 | 4 | 2 | 08/12/2022 | 08/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2022 |  | 11/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2023 | Connected |  | N
National Grid | WORCESTER | 521126 | 01604 | 0 | Solar | 05_14_7L4 | 04/24/2023 | 04/28/2023 | 4 | 1 | 3 | 05/01/2023 | 05/01/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2023 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176391 | 01752 | 168 | Solar | 05_01_227W3 | 02/01/2016 | 02/01/2016 | 0 | 0 | 0 | 02/03/2016 | 02/03/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 2/8/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 656827 | 01915 | 7.6 | Solar | 05_01_406L3 | 12/12/2024 | 12/16/2024 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 12/12/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | AMESBURY | 177893 | 01913 | 2490 | Solar | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 |  | 7/9/2020 | N | STD | 685 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 655724 | 01921 | 7.6 | Solar | 05_01_9J360 | 11/20/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 2/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2025 | Connected |  | N
National Grid | LOWELL | 641232 | 01852 | 0 | Other | 05_05_310W5 | 07/12/2025 | 11/23/2025 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 01/27/2026 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | AMESBURY | 177916 | 01913 | 144 | Solar | 05_12_51L1 | 10/20/2017 | 10/20/2017 | 4 | 0 | 4 | 10/27/2017 | 10/27/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2017 |  | 10/28/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 5/29/2018 | Connected |  | N
National Grid | SHIRLEY | 710143 | 01464 | 7.15 | Solar | 05_14_275L2 | 08/07/2025 | 09/11/2025 | 6 | 0 | 6 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | N
National Grid | CHARLTON | 382988 | 01507 | 15.2 | Solar | 05_14_56L3 | 09/19/2021 | 11/09/2021 | 36 | 29 | 7 | 11/10/2021 | 11/10/2021 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 | 09/19/2021 | 3/17/2023 | Y | EXP | 365 | 02/23/2022 | 03/17/2022 | 23 | 0 | 23 |  |  | 4/21/2022 | Connected |  | N
National Grid | BROOKFIELD | 449174 | 01515 | 15.2 | Solar | 05_14_70L3 | 08/03/2022 | 08/19/2022 | 13 | 12 | 1 | 08/22/2022 | 08/22/2022 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2022 | 08/03/2022 | 10/10/2023 | Y | EXP | 365 | 10/19/2022 | 10/28/2022 | 10 | 0 | 10 |  |  | 8/30/2023 | Connected |  | N
National Grid | WORCESTER | 529466 | 01604 | 15.2 | Solar | 05_14_7L4 | 05/26/2023 | 05/30/2023 | 2 | 1 | 1 | 05/31/2023 | 05/31/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2023 |  | 7/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/16/2023 | Connected |  | N
National Grid | MARLBOROUGH | 176808 | 01752 | 13.6 | Solar | 05_01_227W3 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/3/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 667517 | 01915 | 17.3 | Solar | 05_01_406L3 | 01/28/2025 | 02/21/2025 | 18 | 14 | 4 | 02/24/2025 | 02/24/2025 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | AMESBURY | 177892 | 01913 | 4200 | Solar | 05_01_552L3 | 04/13/2017 | 04/21/2017 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2017 | 05/24/2017 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2018 | 04/13/2017 | 6/7/2021 | Y | STD | 685 | 09/23/2020 | 04/14/2021 | 203 | 0 | 203 |  |  | 6/4/2021 | Connected |  | N
National Grid | BOXFORD | 688483 | 01921 | 7.6 | Solar | 05_01_9J360 | 04/29/2025 | 05/14/2025 | 2 | 0 | 2 | 06/02/2025 | 06/02/2025 | 58 | 45 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 322713 | 01824 | 14.805 | Solar | 05_12_51L1 | 11/13/2020 | 11/17/2020 | 1 | 0 | 1 | 11/18/2020 | 11/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/13/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2021 | Connected |  | N
National Grid | SALISBURY | 343628 | 01952 | 499 | Solar | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 |  | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SHIRLEY | 398752 | 01464 | 15.2 | Solar | 05_14_56L3 | 12/01/2021 | 12/02/2021 | 1 | 0 | 1 | 12/03/2021 | 12/03/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2021 |  | 4/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2022 | Connected |  | N
National Grid | OXFORD | 396676 | 01540 | 0 | Battery Add-On | 05_14_70L3 | 07/06/2022 | 08/10/2022 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/16/2022 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 566104 | 01535 | 70 | Solar | 05_14_7L4 | 11/06/2023 | 11/21/2023 | 10 | 0 | 10 | 11/22/2023 | 11/22/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2024 | 11/06/2023 | 5/6/2025 | Y | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | Y
National Grid | WORCESTER | 177274 | 01604 | 0 | Solar | 05_01_227W3 | 02/06/2017 | 02/06/2017 | 45 | 44 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2017 | 04/24/2017 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2019 | 02/06/2017 | 2/18/2023 | Y | STD | 117 | 10/30/2019 | 10/29/2019 | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | MARLBOROUGH | 677208 | 01752 | 10 | Solar | 05_01_406L3 | 03/11/2025 | 03/22/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/11/2025 | 5/29/2026 | Y | EXP | 365 | 07/22/2025 | 07/22/2025 | 1 | 0 | 1 |  |  | 8/13/2025 | Connected |  | N
National Grid | BEVERLY | 177945 | 01915 | 42.3 | Solar | 05_01_552L3 | 08/21/2017 | 08/21/2017 | 57 | 49 | 8 | 11/20/2017 | 11/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2017 |  | 8/26/2018 | N | EXP | 279 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | AMESBURY | 699741 | 01913 | 5.76 | Solar | 05_01_9J360 | 06/19/2025 | 07/02/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 9/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | BOXFORD | 650007 | 01921 | 0 | Other | 05_05_310W5 | 05/02/2025 | 07/11/2025 | 47 | 42 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | CHELMSFORD | 326457 | 01824 | 9.86 | Solar | 05_12_51L1 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 |  | 11/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2021 | Connected |  | N
National Grid | SALISBURY | 616127 | 01952 | 1996 | Solar | 05_14_275L4 | 08/12/2024 | 09/04/2024 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2024 | 09/18/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SHIRLEY | 410771 | 01464 | 10 | Solar | 05_14_56L3 | 02/07/2022 | 02/09/2022 | 3 | 1 | 2 | 02/10/2022 | 02/10/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2022 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2022 | Connected |  | N
National Grid | OXFORD | 431972 | 01540 | 11.4 | Solar | 05_14_70L3 | 05/27/2022 | 06/01/2022 | 2 | 0 | 2 | 06/02/2022 | 06/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2022 |  | 11/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2023 | Connected |  | N
National Grid | NORTH BROOKFIELD | 574923 | 01535 | 10 | Solar | 05_14_7L4 | 04/03/2024 | 12/07/2023 | 5 | 3 | 2 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 04/03/2024 | 5/14/2025 | Y | EXP | 365 | 06/05/2024 | 07/17/2024 | 43 | 0 | 43 |  |  | 7/19/2024 | Connected |  | N
National Grid | WORCESTER | 177337 | 01604 | 16 | Solar | 05_01_227W3 | 09/01/2016 | 09/01/2016 | 12 | 12 | 0 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 9/6/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 3/23/2017 | 3/23/2017 | 3/23/2017 | Connected |  | N
National Grid | MARLBOROUGH | 683569 | 01752 | 15.2 | Solar | 05_01_406L3 | 04/08/2025 | 04/10/2025 | 2 | 0 | 2 | 04/11/2025 | 04/11/2025 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 04/08/2025 | 6/9/2026 | Y | EXP | 365 | 09/19/2025 | 10/27/2025 | 39 | 0 | 39 |  |  | 10/29/2025 | Connected |  | N
National Grid | BEVERLY | 178060 | 01915 | 4980 | Solar | 05_01_552L3 | 09/01/2017 | 09/21/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2017 | 11/03/2017 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2018 | 09/01/2017 | 7/6/2021 | Y | STD | 78 | 04/02/2020 | 09/11/2020 | 163 | 5 | 158 |  |  | 7/6/2021 | Connected |  | N
National Grid | AMESBURY | 701039 | 01913 | 7.6 | Solar | 05_01_9J360 | 06/25/2025 | 07/14/2025 | 4 | 0 | 4 | 07/22/2025 | 07/22/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/25/2025 | 8/14/2026 | Y | EXP | 365 | 10/02/2025 | 10/06/2025 | 5 | 0 | 5 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 720992 | 01921 | 55 | Solar | 05_05_310W5 | 09/22/2025 | 02/04/2026 | 90 | 83 | 7 | 02/05/2026 | 02/05/2026 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BILLERICA | 333031 | 01862 | 100 | Solar | 05_12_51L1 | 03/19/2021 | 12/08/2021 | 11 | 0 | 11 | 04/06/2021 | 04/06/2021 | 129 | 106 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 723192 | 01952 | 10 | Solar | 05_14_275L4 | 10/01/2025 | 10/07/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 | 10/01/2025 | 12/4/2026 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | SHIRLEY | 412304 | 01464 | 7.6 | Solar | 05_14_56L3 | 02/24/2022 | 02/28/2022 | 2 | 0 | 2 | 03/01/2022 | 03/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 02/24/2022 | 6/13/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2022 | Connected |  | N
National Grid | OXFORD | 482365 | 01540 | 7.6 | Solar | 05_14_70L3 | 01/17/2023 | 01/19/2023 | 2 | 0 | 2 | 01/20/2023 | 01/20/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  | 3/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/11/2023 | Connected |  | N
National Grid | SPENCER | 608674 | 01562 | 3.8 | Solar | 05_14_7L4 | 05/03/2024 | 05/16/2024 | 2 | 0 | 2 | 05/17/2024 | 05/17/2024 | 31 | 22 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/03/2024 | 7/16/2025 | Y | EXP | 365 | 10/24/2024 | 11/20/2024 | 28 | 0 | 28 |  |  | 1/23/2025 | Connected |  | N
National Grid | WORCESTER | 184835 | 01604 | 7.6 | Solar | 05_01_227W3 | 05/23/2018 | 05/23/2018 | 8 | 0 | 8 | 06/06/2018 | 06/06/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2018 |  | 8/5/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2018 | Connected |  | N
National Grid | MARLBOROUGH | 684312 | 01752 | 15.2 | Solar | 05_01_406L3 | 04/10/2025 | 04/14/2025 | 2 | 0 | 2 | 04/15/2025 | 04/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | BEVERLY | 178157 | 01915 | 990 | Solar | 05_01_552L3 | 12/22/2017 | 02/05/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 02/28/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 |  | 12/31/2018 | N | STD | 174 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 721533 | 01913 | 5.76 | Solar | 05_01_9J360 | 09/24/2025 | 10/08/2025 | 3 | 0 | 3 | 11/10/2025 | 11/10/2025 | 43 | 26 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 747566 | 01921 | 0 | Battery Add-On | 05_05_310W5 | 01/26/2026 | 01/29/2026 | 3 | 0 | 3 | 01/30/2026 | 01/30/2026 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHELMSFORD | 335686 | 01824 | 7.68 | Solar | 05_12_51L1 | 01/20/2021 | 02/10/2021 | 15 | 14 | 1 | 02/11/2021 | 02/11/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2021 | 01/20/2021 | 2/10/2022 | Y | EXP | 365 | 05/15/2021 | 05/14/2021 | 0 | 0 | 0 |  |  | 5/18/2021 | Connected |  | N
National Grid | SALISBURY | 174182 | 01952 | 190 | Solar | 05_14_275L4 | 11/14/2011 | 11/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 3/19/2012 | N | EXP | 5 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/5/2012 | Connected |  | N
National Grid | SHIRLEY | 466707 | 01464 | 22.8 | Solar | 05_14_56L3 | 10/21/2022 | 10/25/2022 | 2 | 0 | 2 | 10/26/2022 | 10/26/2022 | 325 | 302 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2024 | Connected |  | N
National Grid | OXFORD | 503539 | 01540 | 6.3 | Solar | 05_14_70L3 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 6/22/2024 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 635953 | 01515 | 5.76 | Solar | 05_14_7L4 | 08/28/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/28/2024 | 9/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | WORCESTER | 199446 | 01604 | 250 | Solar | 05_01_227W3 | 10/26/2018 | 10/30/2018 | 1 | 0 | 1 | 10/31/2018 | 10/31/2018 | 10 | 0 | 10 | 11/16/2018 | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  | 01/08/2019 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 685072 | 01752 | 23 | Solar | 05_01_406L3 | 04/15/2025 | 05/08/2025 | 16 | 12 | 4 | 05/09/2025 | 05/09/2025 | 54 | 33 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 | 04/15/2025 | 8/6/2026 | Y | EXP | 365 | 09/19/2025 | 10/07/2025 | 19 | 0 | 19 |  |  | 10/8/2025 | Connected |  | N
National Grid | BEVERLY | 178194 | 01915 | 2450 | Solar | 05_01_552L3 | 01/03/2018 | 02/01/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 04/17/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 01/03/2018 | 3/20/2020 | Y | STD | 423 | 12/06/2019 | 02/19/2020 | 75 | 0 | 75 |  |  | 3/16/2020 | Connected |  | N
National Grid | AMESBURY | 723299 | 01913 | 15.2 | Solar | 05_01_9J360 | 10/01/2025 | 10/09/2025 | 5 | 0 | 5 | 10/10/2025 | 10/10/2025 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 | 10/01/2025 | 11/17/2026 | Y | EXP | 365 | 02/11/2026 | 02/22/2026 | 12 | 0 | 12 |  |  | 2/23/2026 | Connected |  | N
National Grid | ANDOVER | 174443 | 01845 | 30 | Solar | 05_05_310W5 | 07/06/2012 | 07/06/2012 | 8 | 0 | 8 | 07/19/2012 | 07/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 10/4/2012 | 10/4/2012 | 1/9/2013 | Connected |  | N
National Grid | CHELMSFORD | 335860 | 01824 | 5.52 | Solar | 05_12_51L1 | 01/18/2021 | 01/25/2021 | 4 | 0 | 4 | 04/13/2021 | 04/13/2021 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALISBURY | 174265 | 01952 | 19.89 | Solar | 05_14_275L4 | 11/16/2011 | 11/16/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2012 |  | 1/14/2012 | N | EXP | 6 |  |  | 0 | 0 | 0 | 6/26/2012 | 6/26/2012 | 7/16/2012 | Connected |  | N
National Grid | SHIRLEY | 475112 | 01464 | 15.2 | Solar | 05_14_56L3 | 11/07/2022 | 11/08/2022 | 1 | 0 | 1 | 11/09/2022 | 11/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2023 | Connected |  | N
National Grid | CHARLTON | 544628 | 01507 | 0 | Solar | 05_14_70L3 | 07/31/2023 | 08/01/2023 | 1 | 0 | 1 | 08/02/2023 | 08/02/2023 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 |  | 9/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2024 | Connected |  | N
National Grid | NORTH BROOKFIELD | 653448 | 01535 | 7.6 | Solar | 05_14_7L4 | 12/06/2024 | 12/27/2024 | 8 | 2 | 6 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | WORCESTER | 232315 | 01604 | 250 | Solar | 05_01_227W3 | 12/11/2019 | 01/14/2020 | 20 | 15 | 5 | 01/15/2020 | 01/15/2020 | 56 | 36 | 20 | 05/19/2020 | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 |  | 09/16/2020 | 98 | 3 | 95 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 12/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 384307 | 01772 | 75 | Solar | 05_01_406L4 | 10/13/2021 | 11/17/2021 | 24 | 14 | 10 |  |  | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BEVERLY | 178267 | 01915 | 4980 | Solar | 05_01_552L3 | 01/08/2018 | 01/08/2018 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2018 | 03/10/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/14/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 695278 | 01952 | 640 | Solar | 05_01_HT15 | 01/29/2026 |  | 25 | 22 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BOXFORD | 175274 | 01921 | 42.57 | Solar | 05_05_310W5 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 4/30/2015 | Connected |  | N
National Grid | BILLERICA | 377712 | 01862 | 67 | Solar | 05_12_51L1 | 09/10/2021 | 11/17/2021 | 46 | 36 | 10 | 11/18/2021 | 11/18/2021 | 99 | 51 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 09/10/2021 | 4/30/2023 | Y | EXP | 157 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | SALISBURY | 174476 | 01952 | 500 | Solar | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 525009 | 01464 | 13.824 | Solar | 05_14_56L3 | 05/10/2023 | 05/18/2023 | 6 | 4 | 2 | 05/19/2023 | 05/19/2023 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | OXFORD | 655143 | 01540 | 7.6 | Solar | 05_14_70L3 | 11/20/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/20/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | SPENCER | 501405 | 01562 | 180 | Solar | 05_14_8L1 | 05/10/2023 | 05/31/2023 | 14 | 5 | 9 | 06/01/2023 | 06/01/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 05/10/2023 | 3/2/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | WORCESTER | 231499 | 01604 | 250 | Solar | 05_01_227W3 | 12/09/2019 | 01/14/2020 | 19 | 14 | 5 | 03/16/2020 | 03/16/2020 | 15 | 15 | 0 | 05/19/2020 | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 |  | 10/28/2020 | 102 | 3 | 99 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 647870 | 01752 | 5.76 | Solar | 05_01_406L4 | 10/28/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BEVERLY | 178307 | 01915 | 996 | Solar | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/15/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 176249 | 01952 | 140 | Solar | 05_01_HT15 | 07/08/2015 | 07/08/2015 | 2 | 2 | 0 | 07/10/2015 | 07/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 07/08/2015 | 7/13/2016 | Y | EXP | 343 | 12/10/2015 | 03/17/2016 | 66 | 0 | 66 | 8/15/2016 | 8/15/2016 | 8/15/2016 | Connected |  | N
National Grid | BOXFORD | 175639 | 01921 | 16 | Solar | 05_05_310W5 | 10/21/2014 | 10/21/2014 | 5 | 0 | 5 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2014 |  | 2/6/2015 | N | EXP | 92 |  |  | 0 | 0 | 0 | 8/11/2016 | 8/11/2016 | 8/16/2016 | Connected |  | N
National Grid | CHELMSFORD | 495132 | 01824 | 7.6 | Solar | 05_12_51L1 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 65 | 50 | 15 | 06/16/2023 | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  | 08/24/2023 | 37 | 0 | 37 |  |  | 0 | 0 | 0 | 8/10/2023 |  | 12/16/2024 | N | EXP | 365 | 01/03/2024 | 01/02/2024 | 0 | 0 | 0 |  |  | 1/24/2024 | Connected |  | N
National Grid | SALISBURY | 174475 | 01952 | 2000 | Solar | 05_14_275L4 | 07/18/2012 | 07/18/2012 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/26/2012 | 10/17/2012 | 57 | 0 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 557784 | 01464 | 13.8 | Solar | 05_14_56L3 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 42 | 20 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2023 |  | 12/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2024 | Connected |  | N
National Grid | OXFORD | 662120 | 01540 | 7.6 | Solar | 05_14_70L3 | 12/21/2024 |  | 31 | 25 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH BROOKFIELD | 725174 | 01535 | 7.6 | Solar | 05_14_8L1 | 10/08/2025 | 11/17/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 346662 | 01610 | 500 | Solar | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 10 | 0 | 10 |  |  | 240 | 218 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 713750 | 01752 | 17.6 | Solar | 05_01_406L4 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 79 | 66 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 | 08/27/2025 | 1/16/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BEVERLY | 178304 | 01915 | 2780 | Solar | 05_01_552L3 | 01/09/2018 | 03/09/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/07/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2018 |  | 1/15/2019 | N | STD | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 186780 | 01952 | 788 | Solar | 05_01_HT15 | 06/06/2018 | 06/06/2018 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2018 | 08/17/2018 | 46 | 31 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 |  | 12/25/2020 | N | STD | 534 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 175964 | 01921 | 9.25 | Solar | 05_05_310W5 | 06/05/2015 | 06/05/2015 | 1 | 1 | 0 | 06/09/2015 | 06/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 6/30/2016 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/2/2015 | 7/2/2015 | 8/12/2015 | Connected |  | N
National Grid | CHELMSFORD | 518913 | 01824 | 10 | Solar | 05_12_51L1 | 09/29/2023 | 10/06/2023 | 6 | 3 | 3 | 10/10/2023 | 10/10/2023 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175416 | 01810 | 4500 | Solar | 05_14_275L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/17/2014 | 08/14/2014 | 20 | 18 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 | 07/09/2014 | 12/31/2016 | Y | STD | 655 | 08/30/2016 | 01/30/2017 | 102 | 0 | 102 | 12/14/2016 | 12/14/2016 | 12/22/2016 | Connected |  | N
National Grid | SHIRLEY | 546601 | 01464 | 15.08 | Solar | 05_14_56L3 | 08/07/2023 |  | 50 | 26 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 306207 | 01540 | 246.6 | Solar | 05_14_70L4 | 02/03/2021 | 02/17/2021 | 8 | 0 | 8 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 | 02/03/2021 | 7/24/2026 | Y | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTH BROOKFIELD | 728119 | 01535 | 10 | Solar | 05_14_8L1 | 10/21/2025 | 11/03/2025 | 8 | 2 | 6 | 11/04/2025 | 11/04/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 346659 | 01610 | 250 | Solar | 05_01_227W3 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/26/2021 | 04/26/2021 | 92 | 29 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 738891 | 01752 | 10 | Solar | 05_01_406L4 | 12/09/2025 | 12/10/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 | 12/09/2025 | 1/27/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BEVERLY | 178483 | 01915 | 4999 | Solar | 05_01_552L3 | 04/03/2018 | 04/05/2018 | 18 | 18 | 0 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 197318 | 01952 | 200 | Solar | 05_01_HT15 | 10/01/2018 | 10/08/2018 | 5 | 3 | 2 | 10/09/2018 | 10/09/2018 | 63 | 35 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 176107 | 01921 | 250 | Natural Gas | 05_05_310W5 | 06/25/2015 | 06/25/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 6/30/2016 | N | EXP | 329 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/18/2015 | Connected |  | N
National Grid | LOWELL | 521346 | 01852 | 10 | Solar | 05_12_51L1 | 04/26/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176775 | 01843 | 2800 | Solar | 05_14_275L4 | 11/03/2015 | 11/03/2015 | 53 | 53 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2016 | 02/04/2016 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/9/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 587700 | 01464 | 21.735 | Solar | 05_14_56L3 | 02/06/2024 | 02/29/2024 | 16 | 14 | 2 | 03/01/2024 | 03/01/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | AUBURN | 636406 | 01501 | 200 | Solar | 05_14_70L4 | 09/06/2024 | 10/23/2024 | 32 | 23 | 9 | 10/24/2024 | 10/24/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 | 09/06/2024 | 5/30/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | NORTH BROOKFIELD | 748992 | 01535 | 22.14 | Solar | 05_14_8L1 | 02/03/2026 | 02/06/2026 | 3 | 0 | 3 | 02/09/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 361884 | 01610 | 9.8 | Solar | 05_01_227W3 | 06/03/2021 | 06/08/2021 | 3 | 2 | 1 | 06/09/2021 | 06/09/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 8/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 749907 | 01772 | 11.5 | Solar | 05_01_406L4 | 02/06/2026 | 02/25/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BEVERLY | 205262 | 01915 | 7.6 | Solar | 05_01_552L3 | 01/07/2019 | 01/17/2019 | 7 | 0 | 7 | 01/18/2019 | 01/18/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 |  | 2/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2019 | Connected |  | N
National Grid | AMESBURY | 438934 | 01913 | 150 | Solar | 05_01_HT17 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 176261 | 01921 | 6 | Solar | 05_05_310W5 | 09/04/2015 | 09/04/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2015 |  | 9/12/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 9/25/2015 | 9/25/2015 | 2/12/2016 | Connected |  | N
National Grid | BILLERICA | 575451 | 01862 | 3.48 | Solar | 05_12_51L1 | 02/08/2024 | 02/14/2024 | 4 | 0 | 4 | 02/15/2024 | 02/15/2024 | 84 | 79 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2024 |  | 6/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LAWRENCE | 177418 | 01843 | 1050 | Solar | 05_14_275L4 | 12/01/2016 | 12/01/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2016 | 03/03/2017 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 | 12/01/2016 | 1/6/2020 | Y | STD | 62 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 593058 | 01464 | 15.2 | Solar | 05_14_56L3 | 02/27/2024 | 04/09/2024 | 1 | 0 | 1 | 04/10/2024 | 04/10/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 02/27/2024 | 5/8/2025 | Y | EXP | 365 | 05/23/2024 | 12/17/2024 | 209 | 0 | 209 |  |  | 8/3/2024 | Connected |  | N
National Grid | OXFORD | 714533 | 01540 | 500 | Solar | 05_14_70L4 | 10/10/2025 | 11/10/2025 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 12/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BROOKFIELD | 177700 | 01515 | 7.6 | Solar | 05_14_8L1 | 03/21/2017 | 03/21/2017 | 4 | 4 | 0 | 03/28/2017 | 03/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2017 |  | 3/27/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 6/20/2017 | 6/20/2017 | 7/12/2017 | Connected |  | N
National Grid | WORCESTER | 562155 | 01610 | 10 | Solar | 05_01_227W3 | 11/29/2023 | 12/19/2023 | 14 | 10 | 4 | 12/20/2023 | 12/20/2023 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 11/29/2023 | 4/1/2025 | Y | EXP | 365 | 06/18/2024 | 07/10/2024 | 23 | 0 | 23 |  |  | 7/22/2024 | Connected |  | Y
National Grid | MARLBOROUGH | 173764 | 01752 | 10 | Solar | 05_01_406L4 | 04/17/2018 | 04/17/2018 | 0 | 0 | 0 | 07/10/2018 | 07/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 211642 | 01915 | 4980 | Solar | 05_01_552L3 | 02/27/2019 | 04/02/2019 | 24 | 17 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2019 | 04/24/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 320344 | 01913 | 75 | Natural Gas | 05_01_HT20 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | BOXFORD | 185773 | 01921 | 7000 | Solar | 05_05_310W5 | 09/07/2018 |  | 62 | 32 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 578751 | 01862 | 0 | Solar | 05_12_51L1 | 12/19/2023 | 12/22/2023 | 2 | 2 | 0 | 12/26/2023 | 12/26/2023 | 38 | 16 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 2/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | ANDOVER | 177880 | 01810 | 15.2 | Solar | 05_14_275L4 | 10/18/2017 | 10/18/2017 | 7 | 6 | 1 | 10/31/2017 | 10/31/2017 | 102 | 0 | 102 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2017 |  | 10/24/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | SHIRLEY | 597914 | 01464 | 7.68 | Solar | 05_14_56L3 | 05/20/2024 | 08/13/2024 | 19 | 17 | 2 | 08/14/2024 | 08/14/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | AUBURN | 175414 | 01501 | 76 | Solar | 05_14_70L4 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2014 | 07/09/2014 | 11/28/2014 | Y | EXP | 116 | 03/27/2015 | 05/11/2015 | 30 | 0 | 30 | 8/7/2014 | 8/7/2014 | 7/20/2015 | Connected |  | N
National Grid | BROOKFIELD | 178499 | 01506 | 20 | Solar | 05_14_8L1 | 01/23/2018 | 01/23/2018 | 11 | 0 | 11 | 02/08/2018 | 02/08/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 1/29/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 8/2/2018 | Connected |  | N
National Grid | WORCESTER | 612875 | 01610 | 11.5 | Solar | 05_01_227W3 | 05/23/2024 | 05/31/2024 | 5 | 2 | 3 | 06/03/2024 | 06/03/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/23/2024 | 8/8/2025 | Y | EXP | 365 | 06/10/2025 | 08/11/2025 | 63 | 0 | 63 |  |  | 8/16/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174261 | 01752 | 94.25 | Solar | 05_01_406L4 | 02/29/2012 | 02/29/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2012 |  | 6/1/2012 | N | EXP | 122 |  |  | 0 | 0 | 0 | 10/19/2012 | 10/19/2012 | 11/26/2012 | Connected |  | N
National Grid | BEVERLY | 289954 | 01915 | 0 | Other | 05_01_552L3 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2020 | 10/24/2020 | 43 | 27 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 174554 | 01913 | 1333 | Solar | 05_01_HT22 | 10/11/2011 | 10/11/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 225197 | 01921 | 10 | Solar | 05_05_310W5 | 10/28/2019 |  | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 622202 | 01862 | 6 | Solar | 05_12_51L1 | 07/04/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/04/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | LAWRENCE | 178340 | 01843 | 3294 | Solar | 05_14_275L4 | 11/20/2017 | 11/20/2017 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 03/28/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2018 | 11/20/2017 | 12/31/2019 | Y | STD | 39 | 10/11/2019 | 05/20/2020 | 222 | 0 | 222 |  |  | 12/26/2019 | Connected |  | N
National Grid | SHIRLEY | 605204 | 01464 | 10 | Solar | 05_14_56L3 | 04/19/2024 | 04/22/2024 | 1 | 0 | 1 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2024 | Connected |  | N
National Grid | OXFORD | 177237 | 01540 | 472.9 | Solar | 05_14_70L4 | 02/01/2017 | 02/01/2017 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH BROOKFIELD | 184904 | 01535 | 7.6 | Solar | 05_14_8L1 | 05/28/2018 | 05/28/2018 | 1 | 0 | 1 | 05/31/2018 | 05/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 1/8/2020 | N | EXP | 448 | 10/24/2019 | 11/04/2019 | 11 | 0 | 11 |  |  | 11/20/2019 | Connected |  | N
National Grid | WORCESTER | 624233 | 01609 | 10 | Solar | 05_01_227W3 | 07/11/2024 | 08/01/2024 | 1 | 0 | 1 | 08/02/2024 | 08/02/2024 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 07/11/2024 | 9/27/2025 | Y | EXP | 365 | 12/13/2024 | 12/12/2024 | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174250 | 01752 | 95 | Solar | 05_01_406L4 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 6/1/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 6/29/2012 | Connected |  | N
National Grid | BEVERLY | 290420 | 01915 | 0 | Other | 05_01_552L3 | 10/27/2020 | 12/22/2020 | 38 | 30 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2020 | 01/19/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SALISBURY | 178047 | 01952 | 800 | Solar | 05_01_HT22 | 05/05/2017 | 05/30/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2017 | 06/15/2017 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 01/18/2018 | 04/06/2020 | 556 | 0 | 556 | 2/15/2018 | 05/05/2017 | 6/17/2021 | Y | STD | 45 | 10/16/2020 | 04/21/2021 | 187 | 0 | 187 |  |  | 6/2/2021 | Connected |  | N
National Grid | BOXFORD | 233162 | 01921 | 133.2 | Solar | 05_05_310W5 | 03/23/2020 | 03/31/2020 | 3 | 0 | 3 | 04/01/2020 | 04/01/2020 | 13 | 5 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 5/18/2021 | N | EXP | 395 |  |  | 0 | 0 | 0 |  |  | 7/22/2021 | Connected |  | N
National Grid | BILLERICA | 629790 | 01862 | 10 | Solar | 05_12_51L1 | 08/02/2024 | 08/30/2024 | 16 | 14 | 2 | 09/03/2024 | 09/03/2024 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 178415 | 01810 | 6.6 | Solar | 05_14_275L4 | 11/27/2017 | 11/27/2017 | 32 | 31 | 1 | 01/16/2018 | 01/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2018 | 11/27/2017 | 12/3/2018 | Y | EXP | 321 | 06/22/2018 | 08/03/2018 | 42 | 0 | 42 |  |  | 11/15/2018 | Connected |  | N
National Grid | SHIRLEY | 620829 | 01464 | 15.2 | Solar | 05_14_56L3 | 06/28/2024 | 07/11/2024 | 9 | 7 | 2 | 07/12/2024 | 07/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | OXFORD | 204163 | 01540 | 453 | Solar | 05_14_70L4 | 12/18/2018 | 01/10/2019 | 14 | 12 | 2 | 01/11/2019 | 01/11/2019 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 197977 | 01562 | 10 | Solar | 05_14_8L1 | 10/08/2018 | 11/26/2018 | 16 | 16 | 0 | 11/27/2018 | 11/27/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2018 | 10/08/2018 | 8/28/2019 | Y | EXP | 257 | 04/23/2019 | 05/03/2019 | 10 | 0 | 10 |  |  | 7/23/2019 | Connected |  | N
National Grid | WORCESTER | 639462 | 01603 | 7.6 | Solar | 05_01_227W3 | 09/13/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 09/13/2024 | 12/11/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174329 | 01752 | 1750 | Solar | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 9/1/2012 | Y | STD | 88 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 301406 | 01915 | 400 | Natural Gas | 05_01_552L3 | 12/09/2020 | 12/21/2020 | 7 | 0 | 7 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 174342 | 01913 | 7500 | Natural Gas | 05_01_HT25 | 11/08/2010 | 11/08/2010 | 55 | 0 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 11/08/2010 | 10/31/2012 | Y | STD | 42 | 11/10/2011 | 03/05/2012 | 75 | 0 | 75 | 1/24/2013 | 1/24/2013 | 5/7/2013 | Connected |  | N
National Grid | BOXFORD | 250657 | 01921 | 7.6 | Solar | 05_05_310W5 | 08/26/2019 | 11/01/2019 | 0 | 0 | 0 | 11/04/2019 | 11/04/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 651826 | 01862 | 7.6 | Solar | 05_12_51L1 | 11/04/2024 | 11/13/2024 | 5 | 1 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 11/04/2024 | 1/5/2026 | Y | EXP | 365 | 01/23/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 2/22/2025 | Connected |  | N
National Grid | LAWRENCE | 178618 | 01843 | 7.6 | Solar | 05_14_275L4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 | 01/31/2018 | 11/29/2019 | Y | EXP | 631 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | SHIRLEY | 623174 | 01464 | 0 | Solar | 05_14_56L3 | 07/08/2024 | 07/10/2024 | 2 | 0 | 2 | 07/11/2024 | 07/11/2024 | 38 | 23 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 10/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | OXFORD | 613720 | 01537 | 4.06 | Solar | 05_14_70L4 | 05/28/2024 | 07/31/2024 | 5 | 2 | 3 | 08/01/2024 | 08/01/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 05/28/2024 | 10/1/2025 | Y | EXP | 365 | 11/15/2024 | 12/18/2024 | 34 | 0 | 34 |  |  | 1/9/2025 | Connected |  | Y
National Grid | NORTH BROOKFIELD | 199566 | 01535 | 7.6 | Solar | 05_14_8L1 | 10/26/2018 | 11/20/2018 | 13 | 7 | 6 | 11/21/2018 | 11/21/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2018 | 10/26/2018 | 12/11/2019 | Y | EXP | 365 | 06/05/2019 | 06/04/2019 | 0 | 0 | 0 |  |  | 10/15/2019 | Connected |  | N
National Grid | WORCESTER | 646743 | 01610 | 7.6 | Solar | 05_01_227W3 | 10/14/2024 | 11/12/2024 | 11 | 4 | 7 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/14/2024 | 12/24/2025 | Y | EXP | 365 | 02/12/2025 | 03/04/2025 | 21 | 0 | 21 |  |  | 3/11/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174328 | 01752 | 2750 | Solar | 05_01_406L4 | 12/20/2011 | 12/20/2011 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2012 | 12/20/2011 | 6/21/2014 | Y | STD | 57 | 03/10/2014 | 05/15/2014 | 46 | 0 | 46 | 6/24/2014 | 6/24/2014 | 7/2/2014 | Connected |  | N
National Grid | BEVERLY | 366176 | 01915 | 10 | Solar | 05_01_552L3 | 07/30/2021 | 08/05/2021 | 5 | 2 | 3 | 08/06/2021 | 08/06/2021 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  | 10/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2021 | Connected |  | N
National Grid | SALISBURY | 175683 | 01952 | 75.6 | Solar | 05_01_HT26 | 12/24/2014 | 12/24/2014 | 4 | 1 | 3 | 01/02/2015 | 01/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 | 12/24/2014 | 5/31/2015 | Y | EXP | 116 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 10/28/2015 | Connected |  | N
National Grid | BOXFORD | 295368 | 01921 | 8.7 | Solar | 05_05_310W5 | 06/08/2020 | 06/12/2020 | 3 | 2 | 1 | 06/15/2020 | 06/15/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2020 | Connected |  | N
National Grid | BILLERICA | 656752 | 01862 | 7.6 | Solar | 05_12_51L1 | 11/25/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/25/2024 | 2/24/2026 | Y | EXP | 365 | 06/11/2025 | 11/25/2025 | 168 | 0 | 168 |  |  | 12/1/2025 | Connected |  | N
National Grid | LAWRENCE | 187940 | 01843 | 999.9 | Solar | 05_14_275L4 | 06/13/2018 | 06/13/2018 | 4 | 3 | 1 |  |  | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 | 06/13/2018 | 5/17/2021 | Y | STD | 448 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 646412 | 01464 | 10 | Solar | 05_14_56L3 | 10/16/2024 | 11/04/2024 | 2 | 0 | 2 | 11/05/2024 | 11/05/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/16/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | OXFORD | 673217 | 01540 | 960 | Solar | 05_14_70L5 | 05/23/2025 | 06/26/2025 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SPENCER | 256188 | 01562 | 24 | Solar | 05_14_8L1 | 10/20/2019 |  | 99 | 95 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 650217 | 01604 | 17.6 | Solar | 05_01_227W3 | 11/07/2024 | 11/12/2024 | 3 | 0 | 3 | 05/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175286 | 01752 | 19.78 | Solar | 05_01_406L4 | 11/06/2014 | 11/06/2014 | 5 | 3 | 2 | 11/17/2014 | 11/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 1/30/2015 | N | EXP | 71 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 | 4/27/2016 | Connected |  | N
National Grid | BEVERLY | 376647 | 01915 | 3.8 | Solar | 05_01_552L3 | 09/16/2021 | 10/12/2021 | 18 | 17 | 1 | 10/13/2021 | 10/13/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 |  | 10/11/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 535525 | 01913 | 990 | Solar | 05_01_HT26 | 11/21/2023 |  | 117 | 109 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 295196 | 01921 | 0 | Battery Add-On | 05_05_310W5 | 06/06/2020 | 06/10/2020 | 2 | 0 | 2 | 06/11/2020 | 06/11/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2021 | Connected |  | N
National Grid | BILLERICA | 656350 | 01862 | 0 | Battery Add-On | 05_12_51L1 | 11/22/2024 | 11/26/2024 | 2 | 0 | 2 | 11/27/2024 | 11/27/2024 | 188 | 170 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 194215 | 01843 | 325 | Solar | 05_14_275L4 | 08/22/2018 | 08/28/2018 | 3 | 0 | 3 | 08/29/2018 | 08/29/2018 | 101 | 1 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 655111 | 01464 | 5.76 | Solar | 05_14_56L3 | 11/20/2024 | 12/09/2024 | 4 | 0 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 | 11/20/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | OXFORD | 737499 | 01540 | 5.76 | Solar | 05_14_70L5 | 12/02/2025 | 12/03/2025 | 1 | 0 | 1 | 01/13/2026 | 01/13/2026 | 33 | 18 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTH BROOKFIELD | 332871 | 01535 | 7.6 | Solar | 05_14_8L1 | 02/05/2021 | 02/11/2021 | 3 | 0 | 3 | 02/12/2021 | 02/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 661266 | 01604 | 10 | Solar | 05_01_227W3 | 12/17/2024 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/17/2024 | 4/4/2026 | Y | EXP | 365 | 06/11/2025 | 10/20/2025 | 132 | 0 | 132 |  |  | 11/20/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 175331 | 01772 | 3000 | Solar | 05_01_406L4 | 11/11/2014 | 11/11/2014 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 | 12/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 11/11/2014 | 9/14/2016 | Y | STD | 532 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 447837 | 01915 | 7.25 | Solar | 05_01_552L3 | 08/24/2022 | 08/30/2022 | 4 | 0 | 4 | 08/31/2022 | 08/31/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 613305 | 01913 | 870 | Solar | 05_01_HT26 | 06/17/2024 | 07/24/2024 | 25 | 17 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2024 | 09/23/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BOXFORD | 312249 | 01921 | 15.2 | Solar | 05_05_310W5 | 09/11/2020 | 09/14/2020 | 0 | 0 | 0 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 10/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 677578 | 01862 | 3.8 | Solar | 05_12_51L1 | 03/12/2025 | 04/14/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2025 | 03/12/2025 | 6/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2025 | Connected |  | N
National Grid | ANDOVER | 333336 | 01810 | 5.04 | Solar | 05_14_275L4 | 12/21/2020 | 12/22/2020 | 0 | 0 | 0 | 12/23/2020 | 12/23/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 |  | 12/21/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2021 | Connected |  | N
National Grid | SHIRLEY | 660528 | 01464 | 8.12 | Solar | 05_14_56L3 | 12/16/2024 | 12/26/2024 | 7 | 3 | 4 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 175886 | 01540 | 3.8 | Solar | 05_14_70L5 | 05/26/2015 | 05/26/2015 | 0 | 0 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2015 |  | 10/30/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 11/16/2015 | 11/16/2015 | 11/19/2015 | Connected |  | N
National Grid | BROOKFIELD | 342617 | 01515 | 7.6 | Solar | 05_14_8L1 | 04/02/2021 | 04/15/2021 | 8 | 0 | 8 | 04/16/2021 | 04/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2021 | Connected |  | N
National Grid | WORCESTER | 678660 | 01610 | 15.2 | Solar | 05_01_227W3 | 03/17/2025 | 03/25/2025 | 6 | 2 | 4 | 03/26/2025 | 03/26/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | SOUTHBOROUGH | 175395 | 01772 | 10 | Solar | 05_01_406L4 | 09/16/2014 | 09/16/2014 | 7 | 0 | 7 | 09/26/2014 | 09/26/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 547266 | 01915 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 10/06/2023 | 21 | 20 | 1 | 10/10/2023 | 10/10/2023 | 6 | 0 | 6 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 192164 | 01913 | 249.8 | Solar | 05_01_HT27 | 08/06/2018 | 09/04/2018 | 18 | 0 | 18 | 09/05/2018 | 09/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BOXFORD | 333500 | 01921 | 52.2 | Solar | 05_05_310W5 | 03/01/2021 | 12/07/2021 | 9 | 0 | 9 | 03/16/2021 | 03/16/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2021 |  | 10/9/2023 | N | EXP | 75 | 08/19/2021 | 09/15/2021 | 26 | 3 | 23 |  |  | 8/24/2023 | Connected |  | N
National Grid | BILLERICA | 715101 | 01821 | 10 | Solar | 05_12_51L1 | 08/27/2025 | 09/17/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/27/2025 | 11/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 339860 | 01843 | 10 | Solar | 05_14_275L4 | 02/01/2021 | 02/03/2021 | 1 | 0 | 1 | 02/04/2021 | 02/04/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2021 |  | 2/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2021 | Connected |  | N
National Grid | SHIRLEY | 661934 | 01464 | 8.74 | Solar | 05_14_56L3 | 12/20/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/20/2024 | 3/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | OXFORD | 177357 | 01540 | 168 | Solar | 05_14_70L5 | 02/16/2017 | 02/16/2017 | 1 | 0 | 1 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 2/21/2018 | N | EXP | 247 |  |  | 0 | 0 | 0 | 12/28/2017 | 12/28/2017 | 1/8/2018 | Connected |  | N
National Grid | BROOKFIELD | 349605 | 01515 | 6 | Solar | 05_14_8L1 | 04/23/2021 | 01/06/2022 | 2 | 0 | 2 | 04/29/2021 | 04/29/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 711842 | 01610 | 20.9 | Solar | 05_01_227W3 | 08/13/2025 | 08/22/2025 | 6 | 1 | 5 | 08/25/2025 | 08/25/2025 | 90 | 60 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 175686 | 01772 | 17 | Solar | 05_01_406L4 | 12/23/2014 | 12/23/2014 | 8 | 5 | 3 | 01/07/2015 | 01/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2015 |  | 4/30/2015 | N | EXP | 9 |  |  | 0 | 0 | 0 | 2/20/2015 | 2/20/2015 | 11/12/2015 | Connected |  | N
National Grid | BEVERLY | 547263 | 01915 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 10/10/2023 | 23 | 22 | 1 | 10/11/2023 | 10/11/2023 | 5 | 0 | 5 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 12/19/2024 | N | EXP | 365 | 01/18/2024 | 04/22/2024 | 96 | 23 | 73 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 438978 | 01913 | 100 | Solar | 05_01_HT27 | 06/27/2022 | 07/11/2022 | 9 | 0 | 9 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 342922 | 01845 | 203.3 | Solar | 05_05_310W5 | 02/18/2021 | 03/04/2021 | 9 | 0 | 9 |  |  | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 667830 | 01862 | 5.7 | Solar | 05_12_51L2 | 01/24/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 343629 | 01843 | 499 | Solar | 05_14_275L4 | 07/14/2021 | 08/23/2021 | 28 | 19 | 9 |  |  | 28 | 2 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 | 07/14/2021 | 12/9/2023 | Y | STD | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 671510 | 01464 | 10 | Solar | 05_14_56L3 | 02/11/2025 | 02/20/2025 | 6 | 3 | 3 | 02/21/2025 | 02/21/2025 | 161 | 140 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 177550 | 01540 | 10 | Solar | 05_14_70L5 | 05/15/2017 | 05/15/2017 | 4 | 3 | 1 | 05/22/2017 | 05/22/2017 | 189 | 0 | 189 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2017 |  | 5/21/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 396873 | 01562 | 7.6 | Solar | 05_14_8L1 | 12/08/2021 | 01/06/2022 | 5 | 4 | 1 | 12/15/2021 | 12/15/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 734559 | 01603 | 0 | Battery Add-On | 05_01_227W3 | 11/18/2025 | 11/20/2025 | 2 | 0 | 2 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | MARLBOROUGH | 175721 | 01752 | 100 | Solar | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 1/3/2015 | N | EXP | 89 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 | 1/20/2015 | Connected |  | N
National Grid | BEVERLY | 547258 | 01915 | 10 | Solar | 05_01_552L3 | 09/07/2023 | 09/13/2023 | 4 | 3 | 1 | 09/14/2023 | 09/14/2023 | 23 | 0 | 23 | 10/27/2023 | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 11/19/2024 | N | EXP | 365 | 01/18/2024 | 03/07/2024 | 50 | 0 | 50 |  |  | 4/1/2024 | Connected |  | N
National Grid | AMESBURY | 617208 | 01913 | 250 | Solar | 05_01_HT28 | 09/23/2024 | 11/21/2024 | 42 | 32 | 10 |  |  | 86 | 61 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BOXFORD | 396057 | 01921 | 0 | Other | 05_05_310W5 | 01/25/2022 | 02/07/2022 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | CMPX |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 745352 | 01862 | 3.7 | Battery Add-On | 05_12_51L2 | 01/14/2026 | 01/16/2026 | 2 | 0 | 2 | 01/20/2026 | 01/20/2026 | 29 | 11 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 366611 | 01843 | 10 | Solar | 05_14_275L4 | 07/28/2021 | 08/17/2021 | 14 | 13 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | SHIRLEY | 693640 | 01464 | 17.6 | Solar | 05_14_56L3 | 06/03/2025 | 06/05/2025 | 2 | 0 | 2 | 06/06/2025 | 06/06/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | OXFORD | 178469 | 01540 | 11.4 | Solar | 05_14_70L5 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2018 |  | 5/17/2021 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | SPENCER | 426466 | 01562 | 7.6 | Solar | 05_14_8L1 | 06/01/2022 | 06/07/2022 | 4 | 0 | 4 | 06/08/2022 | 06/08/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 177934 | 01610 | 15.2 | Solar | 05_01_23W1 | 06/19/2017 | 06/19/2017 | 27 | 27 | 0 | 07/28/2017 | 07/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2017 |  | 6/25/2018 | N | EXP | 329 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | MARLBOROUGH | 175770 | 01752 | 100 | Solar | 05_01_406L4 | 08/15/2014 | 08/15/2014 | 6 | 0 | 6 | 08/26/2014 | 08/26/2014 | 96 | 0 | 96 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2014 |  | 12/31/2014 | N | EXP | 86 |  |  | 0 | 0 | 0 | 12/26/2014 | 12/26/2014 |  | Withdrawn |  | Y
National Grid | BEVERLY | 561832 | 01915 | 10 | Solar | 05_01_552L3 | 10/10/2023 | 10/11/2023 | 1 | 0 | 1 | 10/12/2023 | 10/12/2023 | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 |  | 1/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2024 | Connected |  | N
National Grid | AMESBURY | 196401 | 01913 | 66.6 | Solar | 05_01_HT28 | 09/19/2018 | 08/01/2019 | 0 | 0 | 0 | 10/09/2018 | 10/09/2018 | 28 | 12 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 |  | 6/30/2020 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 485595 | 01845 | 0 | Solar | 05_05_310W5 | 12/14/2022 | 12/19/2022 | 3 | 2 | 1 | 12/20/2022 | 12/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 2/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N
National Grid | BILLERICA | 753579 | 01821 | 23 | Battery Add-On | 05_12_51L2 | 03/04/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 478526 | 01843 | 22.8 | Solar | 05_14_275L4 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHIRLEY | 707133 | 01464 | 21.38 | Solar | 05_14_56L3 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2026 | Connected |  | N
National Grid | OXFORD | 185699 | 01540 | 360 | Solar | 05_14_70L5 | 05/18/2018 | 05/18/2018 | 53 | 47 | 6 | 06/22/2018 | 06/22/2018 | 29 | 6 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 431131 | 01562 | 6 | Solar | 05_14_8L1 | 05/26/2022 | 05/31/2022 | 2 | 0 | 2 | 06/01/2022 | 06/01/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178256 | 01604 | 900 | Solar | 05_01_23W1 | 04/16/2018 | 04/16/2018 | 15 | 15 | 0 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 04/16/2018 | 8/16/2023 | Y | STD | 118 | 01/13/2021 | 08/03/2023 | 933 | 7 | 926 | 7/21/2023 | 8/3/2023 | 8/14/2023 | Connected |  | N
National Grid | MARLBOROUGH | 176419 | 01752 | 1250 | Solar | 05_01_406L4 | 12/07/2015 | 12/07/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2015 | 01/07/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/13/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 562496 | 01915 | 5 | Solar | 05_01_552L3 | 10/20/2023 | 11/09/2023 | 14 | 11 | 3 | 11/13/2023 | 11/13/2023 | 21 | 0 | 21 | 12/21/2023 | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 |  | 04/15/2024 | 78 | 1 | 77 |  |  | 0 | 0 | 0 | 4/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177112 | 01913 | 4400 | Natural Gas | 05_01_HT31 | 08/08/2016 | 08/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 8/30/2018 | N | STD | 72 | 05/28/2018 | 05/27/2018 | 0 | 0 | 0 |  |  | 2/4/2019 | Connected |  | N
National Grid | BOXFORD | 516469 | 01921 | 6 | Solar | 05_05_310W5 | 04/17/2023 | 04/18/2023 | 1 | 0 | 1 | 04/19/2023 | 04/19/2023 | 89 | 67 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 8/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2023 | Connected |  | N
National Grid | BILLERICA | 176064 | 01862 | 135 | Solar | 05_12_51L2 | 04/02/2015 | 04/02/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 502722 | 01843 | 2000 | Solar | 05_14_275L4 | 03/29/2023 | 08/25/2023 | 103 | 93 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/18/2023 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 | 03/29/2023 | 10/20/2025 | Y | STD | 252 | 01/14/2025 | 08/04/2025 | 203 | 0 | 203 |  |  | 9/30/2025 | Connected |  | N
National Grid | WORCESTER | 717140 | 01602 | 7.6 | Solar | 05_14_56L3 | 09/11/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 09/11/2025 | 11/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2025 | Connected |  | N
National Grid | OXFORD | 304749 | 01540 | 10 | Solar | 05_14_70L5 | 08/12/2020 | 08/17/2020 | 2 | 0 | 2 | 08/18/2020 | 08/18/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2020 | 08/12/2020 | 5/3/2021 | Y | EXP | 365 | 12/11/2020 | 01/05/2021 | 25 | 0 | 25 |  |  | 2/11/2021 | Connected |  | N
National Grid | SPENCER | 507185 | 01562 | 0 | Solar | 05_14_8L1 | 05/02/2023 | 06/12/2023 | 28 | 25 | 3 | 06/13/2023 | 06/13/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 05/02/2023 | 8/11/2025 | Y | EXP | 73 | 04/30/2024 | 05/29/2024 | 30 | 0 | 30 |  |  | 10/1/2024 | Connected |  | N
National Grid | WORCESTER | 385653 | 01604 | 3.8 | Solar | 05_01_23W1 | 11/09/2021 | 01/07/2022 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/09/2021 | 5/7/2023 | Y | EXP | 485 | 04/13/2022 | 04/12/2022 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 176458 | 01772 | 6 | Solar | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 4 | 4 | 0 | 12/15/2015 | 12/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2015 |  | 12/14/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 5/9/2016 | 5/9/2016 | 5/10/2016 | Connected |  | N
National Grid | BEVERLY | 570255 | 01915 | 10 | Solar | 05_01_552L3 | 12/18/2023 | 01/02/2024 | 9 | 7 | 2 | 01/03/2024 | 01/03/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2024 | 12/18/2023 | 2/7/2025 | Y | EXP | 365 | 03/08/2024 | 05/17/2024 | 71 | 0 | 71 |  |  | 10/9/2024 | Connected |  | N
National Grid | AMESBURY | 514546 | 01913 | 0 | Natural Gas | 05_01_HT41 | 05/26/2023 | 06/28/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2023 | 07/21/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 04/09/2024 | 02/21/2025 | 216 | 0 | 216 | 3/20/2024 |  | 10/10/2026 | N | STD | 596 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 553692 | 01845 | 10 | Solar | 05_05_310W5 | 09/12/2023 | 09/18/2023 | 4 | 2 | 2 | 09/19/2023 | 09/19/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 176091 | 01862 | 266 | Solar | 05_12_51L2 | 04/01/2015 | 04/01/2015 | 6 | 0 | 6 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 586162 | 01843 | 1375 | Solar | 05_14_275L4 | 02/05/2024 | 02/22/2024 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2024 | 02/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 701035 | 01603 | 34.5 | Solar | 05_14_57L1 | 07/07/2025 | 07/08/2025 | 1 | 0 | 1 | 07/09/2025 | 07/09/2025 | 62 | 41 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | OXFORD | 339771 | 01540 | 11.4 | Solar | 05_14_70L5 | 02/01/2021 | 06/03/2021 | 85 | 80 | 5 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2022 | Connected |  | Y
National Grid | SPENCER | 519443 | 01562 | 11.375 | Solar | 05_14_8L1 | 09/14/2023 | 09/29/2023 | 11 | 10 | 1 | 10/02/2023 | 10/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 425866 | 01606 | 9.074 | Solar | 05_01_23W1 | 05/05/2022 | 05/09/2022 | 2 | 0 | 2 | 05/10/2022 | 05/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 176491 | 01772 | 2000 | Solar | 05_01_406L4 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 |  | 12/15/2016 | N | STD | 137 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 575455 | 01915 | 15.2 | Solar | 05_01_552L3 | 12/13/2023 | 01/04/2024 | 15 | 8 | 7 | 01/05/2024 | 01/05/2024 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | AMESBURY | 174157 | 01913 | 2016 | Natural Gas | 05_01_HT41 | 04/24/2012 | 04/24/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/09/2012 | 05/13/2012 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2012 |  | 12/31/2016 | N | STD | 1482 |  |  | 0 | 0 | 0 |  |  | 7/14/2017 | Connected |  | N
National Grid | BOXFORD | 574904 | 01921 | 0 | Battery Add-On | 05_05_310W5 | 11/30/2023 | 01/03/2024 | 22 | 13 | 9 | 01/04/2024 | 01/04/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 177119 | 01821 | 390 | Solar | 05_12_51L2 | 10/19/2016 | 10/19/2016 | 4 | 4 | 0 | 10/26/2016 | 10/26/2016 | 319 | 36 | 283 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 603133 | 01843 | 17.6 | Solar | 05_14_275L4 | 04/10/2024 | 04/29/2024 | 13 | 9 | 4 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | WORCESTER | 712528 | 01609 | 0 | Solar | 05_14_57L1 | 08/15/2025 | 08/25/2025 | 6 | 3 | 3 | 08/26/2025 | 08/26/2025 | 71 | 54 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 357954 | 01540 | 0 | Solar | 05_14_70L5 | 05/24/2021 | 05/25/2021 | 0 | 0 | 0 | 05/26/2021 | 05/26/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2021 |  | 5/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2021 | Connected |  | N
National Grid | BROOKFIELD | 537292 | 01515 | 0 | Solar | 05_14_8L1 | 06/28/2023 | 10/19/2023 | 77 | 77 | 0 | 10/20/2023 | 10/20/2023 | 71 | 27 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 445969 | 01610 | 7.6 | Solar | 05_01_23W1 | 07/21/2022 | 07/22/2022 | 1 | 0 | 1 | 07/25/2022 | 07/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  | 8/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 176490 | 01772 | 4000.002 | Solar | 05_01_406L4 | 12/08/2015 | 12/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/05/2016 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 | 12/08/2015 | 2/14/2020 | Y | STD | 85 | 10/16/2019 | 01/14/2020 | 90 | 0 | 90 |  |  | 2/13/2020 | Connected |  | N
National Grid | BEVERLY | 626719 | 01915 | 23 | Solar | 05_01_552L3 | 07/22/2024 | 07/25/2024 | 3 | 0 | 3 | 07/26/2024 | 07/26/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 07/22/2024 | 11/14/2025 | Y | EXP | 365 | 01/18/2025 | 08/11/2025 | 206 | 0 | 206 |  |  | 1/22/2026 | Connected |  | N
National Grid | AMESBURY | 321061 | 01913 | 75 | Natural Gas | 05_01_HT41 | 11/20/2020 | 12/07/2020 | 9 | 0 | 9 |  |  | 29 | 4 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 4/27/2023 | N | STD | 43 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | WESTFORD | 574084 | 01886 | 0 | Battery Add-On | 05_05_310W5 | 11/28/2023 | 11/29/2023 | 1 | 0 | 1 | 11/30/2023 | 11/30/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 3/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2024 | Connected |  | N
National Grid | BILLERICA | 337612 | 01821 | 8.4 | Solar | 05_12_51L2 | 02/01/2021 | 02/04/2021 | 2 | 0 | 2 | 02/05/2021 | 02/05/2021 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 | 02/01/2021 | 9/14/2022 | Y | EXP | 365 | 09/16/2021 | 10/12/2021 | 16 | 0 | 16 |  |  | 12/17/2021 | Connected |  | N
National Grid | LAWRENCE | 626752 | 01843 | 3.8 | Solar | 05_14_275L4 | 07/22/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2024 | 07/22/2024 | 9/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | WORCESTER | 719310 | 01602 | 20.62 | Solar | 05_14_57L1 | 09/16/2025 | 09/17/2025 | 1 | 0 | 1 | 09/18/2025 | 09/18/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 09/16/2025 | 11/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | OXFORD | 425627 | 01540 | 9.8 | Solar | 05_14_70L5 | 05/04/2022 | 05/09/2022 | 3 | 1 | 2 | 05/10/2022 | 05/10/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 05/04/2022 | 1/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2023 | Connected |  | Y
National Grid | NORTH BROOKFIELD | 566189 | 01535 | 5 | Solar | 05_14_8L1 | 11/01/2023 | 11/06/2023 | 3 | 0 | 3 | 11/07/2023 | 11/07/2023 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 | 11/01/2023 | 3/13/2025 | Y | EXP | 365 | 05/15/2024 | 05/31/2024 | 17 | 0 | 17 |  |  | 6/6/2024 | Connected |  | N
National Grid | WORCESTER | 502980 | 01610 | 15.2 | Solar | 05_01_23W1 | 02/21/2023 | 02/22/2023 | 1 | 0 | 1 | 02/23/2023 | 02/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 176531 | 01772 | 252 | Solar | 05_01_406L4 | 12/17/2015 | 12/17/2015 | 27 | 27 | 0 | 01/28/2016 | 01/28/2016 | 192 | 0 | 192 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/22/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 628778 | 01915 | 10 | Solar | 05_01_552L3 | 07/30/2024 | 08/19/2024 | 4 | 0 | 4 | 08/20/2024 | 08/20/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 |  | 1/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | AMESBURY | 174618 | 01913 | 200 | Solar | 05_01_HT42 | 02/07/2011 | 02/07/2011 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2011 | 02/07/2011 | 1/11/2012 | Y | EXP | 245 | 08/02/2011 | 01/28/2012 | 122 | 0 | 122 | 8/3/2012 | 8/3/2012 | 1/11/2012 | Connected |  | N
National Grid | WESTFORD | 624754 | 01886 | 15.3 | Solar | 05_05_310W5 | 07/15/2024 | 07/18/2024 | 3 | 0 | 3 | 07/19/2024 | 07/19/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 9/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2024 | Connected |  | N
National Grid | BILLERICA | 419862 | 01821 | 0 | Other | 05_12_51L2 | 06/14/2022 | 06/28/2022 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2022 | 07/27/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 631814 | 01843 | 7.6 | Solar | 05_14_275L4 | 08/12/2024 | 08/26/2024 | 3 | 0 | 3 | 08/27/2024 | 08/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2024 | 08/12/2024 | 11/24/2025 | Y | EXP | 365 | 01/22/2025 | 01/21/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 733497 | 01609 | 19 | Solar | 05_14_57L1 | 01/02/2026 | 01/28/2026 | 15 | 12 | 3 | 01/29/2026 | 01/29/2026 | 26 | 5 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | OXFORD | 590690 | 01540 | 10 | Solar | 05_14_70L5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 11 | 7 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 581109 | 01515 | 0 | Battery Add-On | 05_14_8L1 | 01/03/2024 | 01/05/2024 | 2 | 0 | 2 | 01/08/2024 | 01/08/2024 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2024 | Connected |  | N
National Grid | WORCESTER | 553654 | 01603 | 3.8 | Solar | 05_01_23W1 | 09/19/2023 | 09/20/2023 | 1 | 0 | 1 | 09/21/2023 | 09/21/2023 | 108 | 28 | 80 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 177404 | 01772 | 6 | Solar | 05_01_406L4 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 | 07/06/2016 | 07/06/2016 | 146 | 0 | 146 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 |  | 7/5/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 652843 | 01915 | 6 | Solar | 05_01_552L3 | 11/07/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AMESBURY | 177587 | 01913 | 300 | Natural Gas | 05_01_HT45 | 05/17/2017 | 05/17/2017 | 18 | 15 | 3 | 06/14/2017 | 06/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 5/23/2018 | N | EXP | 32 |  |  | 0 | 0 | 0 | 4/12/2018 | 4/12/2018 | 4/12/2018 | Connected |  | N
National Grid | WESTFORD | 638803 | 01886 | 10 | Solar | 05_05_310W5 | 09/09/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 09/09/2024 | 1/8/2026 | Y | EXP | 365 | 12/19/2024 | 02/13/2025 | 57 | 0 | 57 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 546247 | 01821 | 9.86 | Solar | 05_12_51L2 | 08/06/2023 | 08/07/2023 | 1 | 0 | 1 | 08/08/2023 | 08/08/2023 | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2023 |  | 10/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2023 | Connected |  | N
National Grid | ANDOVER | 659939 | 01810 | 17.1 | Solar | 05_14_275L4 | 12/11/2024 | 12/16/2024 | 3 | 0 | 3 | 12/17/2024 | 12/17/2024 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 2/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | WORCESTER | 176080 | 01609 | 323 | Solar | 05_14_57L1 | 08/21/2015 | 08/21/2015 | 0 | 0 | 0 | 08/21/2015 | 08/21/2015 | 306 | 14 | 292 | 11/05/2015 | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 |  | 09/23/2016 | 219 | 14 | 205 |  |  | 0 | 0 | 0 | 2/9/2016 | 08/21/2015 | 4/15/2017 | Y | EXP | 431 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 633944 | 01540 | 5.76 | Solar | 05_14_70L5 | 08/20/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 | 08/20/2024 | 10/10/2025 | Y | EXP | 365 | 11/28/2024 | 12/26/2024 | 29 | 0 | 29 |  |  | 1/6/2025 | Connected |  | N
National Grid | BROOKFIELD | 584528 | 01515 | 11.4 | Solar | 05_14_8L1 | 02/01/2024 | 02/12/2024 | 8 | 6 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2024 | Connected |  | N
National Grid | WORCESTER | 622231 | 01603 | 7.6 | Solar | 05_01_23W1 | 07/02/2024 | 07/12/2024 | 4 | 0 | 4 | 07/15/2024 | 07/15/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/02/2024 | 12/31/2025 | Y | EXP | 365 | 05/10/2025 | 11/21/2025 | 196 | 0 | 196 |  |  | 12/22/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177886 | 01752 | 10 | Solar | 05_01_406L4 | 04/11/2017 | 04/11/2017 | 2 | 0 | 2 | 04/14/2017 | 04/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2017 | 04/11/2017 | 4/17/2018 | Y | EXP | 365 | 08/04/2017 | 09/05/2017 | 21 | 0 | 21 | 10/17/2017 | 10/17/2017 | 10/17/2017 | Connected |  | N
National Grid | BEVERLY | 670551 | 01915 | 5.76 | Solar | 05_01_552L3 | 02/06/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 02/06/2025 | 4/4/2026 | Y | EXP | 365 | 07/19/2025 | 08/04/2025 | 17 | 0 | 17 |  |  | 9/25/2025 | Connected |  | N
National Grid | AMESBURY | 265164 | 01913 | 125 | Natural Gas | 05_01_HT46 | 08/10/2020 | 09/16/2020 | 26 | 20 | 6 |  |  | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 638771 | 01886 | 0 | Solar | 05_05_310W5 | 09/09/2024 | 09/11/2024 | 2 | 0 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2024 | Connected |  | N
National Grid | BILLERICA | 652576 | 01821 | 5.76 | Solar | 05_12_51L2 | 11/06/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | ANDOVER | 662699 | 01810 | 7.83 | Solar | 05_14_275L4 | 12/26/2024 | 01/21/2025 | 5 | 1 | 4 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/26/2024 | 3/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | WORCESTER | 176617 | 01602 | 200 | Solar | 05_14_57L1 | 02/17/2016 | 02/17/2016 | 3 | 3 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2016 |  | 2/22/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 5/31/2016 | 5/31/2016 | 5/31/2016 | Connected |  | N
National Grid | OXFORD | 643883 | 01540 | 5.76 | Solar | 05_14_70L5 | 10/01/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROOKFIELD | 593454 | 01515 | 6 | Solar | 05_14_8L1 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2024 | 03/25/2024 | 5/6/2025 | Y | EXP | 365 | 07/31/2024 | 09/19/2024 | 51 | 0 | 51 |  |  | 10/31/2024 | Connected |  | N
National Grid | WORCESTER | 629723 | 01606 | 3.8 | Solar | 05_01_23W1 | 08/02/2024 | 09/18/2024 | 28 | 25 | 3 | 09/19/2024 | 09/19/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2024 |  | 10/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2024 | Connected |  | N
National Grid | MARLBOROUGH | 178569 | 01752 | 10 | Solar | 05_01_406L4 | 12/07/2017 | 12/07/2017 | 17 | 0 | 17 | 01/04/2018 | 01/04/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2018 |  | 12/13/2018 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  | 6/5/2018 | Connected |  | N
National Grid | BEVERLY | 671085 | 01915 | 5.76 | Solar | 05_01_552L3 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | AMESBURY | 372126 | 01913 | 100 | Solar | 05_01_HT46 | 07/28/2021 | 11/08/2021 | 71 | 62 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 657547 | 01886 | 10 | Solar | 05_05_310W5 | 11/28/2024 | 01/14/2025 | 21 | 17 | 4 | 01/15/2025 | 01/15/2025 | 26 | 0 | 26 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 11/28/2024 | 3/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | BILLERICA | 657811 | 01821 | 5.76 | Solar | 05_12_51L2 | 12/02/2024 | 12/20/2024 | 10 | 7 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | ANDOVER | 667969 | 01810 | 7.6 | Solar | 05_14_275L4 | 01/27/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 242635 | 01602 | 0 | Solar | 05_14_57L1 | 07/09/2019 | 07/15/2019 | 3 | 0 | 3 | 07/16/2019 | 07/16/2019 | 12 | 3 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 7/9/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2020 | Connected |  | N
National Grid | OXFORD | 647631 | 01540 | 7.6 | Solar | 05_14_70L5 | 10/21/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROOKFIELD | 607693 | 01506 | 0 | Solar | 05_14_8L1 | 04/30/2024 | 06/11/2024 | 29 | 28 | 1 | 06/12/2024 | 06/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 690729 | 01609 | 7.6 | Solar | 05_01_23W1 | 05/09/2025 | 05/28/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 198666 | 01772 | 6 | Solar | 05_01_406L4 | 12/13/2018 | 12/24/2018 | 6 | 0 | 6 | 12/26/2018 | 12/26/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 692136 | 01915 | 5.76 | Solar | 05_01_552L3 | 06/02/2025 | 06/13/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 06/02/2025 | 8/8/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | AMESBURY | 177605 | 01913 | 1530.048 | Solar | 05_01_HT48 | 09/19/2017 | 02/26/2018 | 102 | 102 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2018 | 06/22/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 | 09/19/2017 | 8/27/2025 | Y | STD | 156 | 10/12/2023 | 08/14/2025 | 672 | 3 | 669 |  |  | 8/28/2025 | Connected |  | N
National Grid | WESTFORD | 661259 | 01886 | 5.76 | Solar | 05_05_310W5 | 12/17/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 | 12/17/2024 | 3/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | BILLERICA | 665914 | 01821 | 18.85 | Solar | 05_12_51L2 | 01/15/2025 | 01/29/2025 | 7 | 2 | 5 | 01/30/2025 | 01/30/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | LAWRENCE | 672950 | 01843 | 15.2 | Solar | 05_14_275L4 | 02/24/2025 | 03/03/2025 | 5 | 2 | 3 | 03/04/2025 | 03/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | WORCESTER | 283707 | 01609 | 600 | Natural Gas | 05_14_57L1 | 12/02/2021 | 01/13/2022 | 30 | 24 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 03/14/2022 | 40 | 19 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 | 12/02/2021 | 11/6/2024 | Y | STD | 279 | 04/04/2024 | 04/18/2024 | 15 | 0 | 15 |  |  | 9/24/2024 | Connected |  | N
National Grid | OXFORD | 613634 | 01540 | 23 | Battery Add-On | 05_14_8L1 | 05/28/2024 | 06/03/2024 | 5 | 3 | 2 | 06/04/2024 | 06/04/2024 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | SPENCER | 707291 | 01562 | 10 | Solar | 05_01_23W1 | 07/24/2025 | 08/19/2025 | 3 | 0 | 3 | 08/25/2025 | 08/25/2025 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 306142 | 01609 | 0 | Other | 05_01_406L4 | 09/16/2020 | 09/30/2020 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/26/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 174385 | 01772 | 2650 | Solar | 05_01_55K11 | 05/31/2012 | 05/31/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2012 | 10/03/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 | 02/18/2015 | 06/29/2016 | 338 | 0 | 338 | 12/23/2014 | 05/31/2012 | 2/3/2016 | Y | STD | 47 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | BEVERLY | 178456 | 01915 | 496 | Solar | 05_01_HT48 | 11/30/2017 | 11/30/2017 | 34 | 12 | 22 |  |  | 51 | 0 | 51 | 03/19/2018 | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 03/23/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AMESBURY | 685105 | 01913 | 9.6 | Solar | 05_05_310W5 | 04/24/2025 | 05/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 |  | 7/16/2026 | N | EXP | 365 | 11/04/2025 | 11/21/2025 | 18 | 0 | 18 |  |  | 2/10/2026 | Connected |  | N
National Grid | WESTFORD | 669158 | 01886 | 8.125 | Solar | 05_12_51L2 | 01/31/2025 | 02/24/2025 | 4 | 0 | 4 | 02/25/2025 | 02/25/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 01/31/2025 | 4/13/2026 | Y | EXP | 365 | 05/16/2025 | 09/03/2025 | 111 | 0 | 111 |  |  | 9/15/2025 | Connected |  | N
National Grid | BILLERICA | 690639 | 01862 | 5.76 | Solar | 05_14_275L4 | 05/09/2025 | 06/02/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 295174 | 01843 | 7.68 | Solar | 05_14_57L1 | 06/05/2020 | 07/09/2020 | 24 | 23 | 1 | 07/10/2020 | 07/10/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | WORCESTER | 648641 | 01609 | 10 | Solar | 05_14_70L5 | 10/21/2024 | 10/31/2024 | 3 | 0 | 3 | 11/01/2024 | 11/01/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 | 10/21/2024 | 12/30/2025 | Y | EXP | 365 | 04/12/2025 | 04/22/2025 | 11 | 0 | 11 |  |  | 4/29/2025 | Connected |  | N
National Grid | OXFORD | 615299 | 01540 | 10 | Solar | 05_14_8L1 | 06/04/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 | 06/04/2024 | 8/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2024 | Connected |  | N
National Grid | BROOKFIELD | 725080 | 01515 | 7.6 | Solar | 05_01_23W1 | 10/08/2025 | 10/20/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2026 | Connected |  | N
National Grid | WORCESTER | 373487 | 01606 | 9.8 | Solar | 05_01_406L4 | 08/05/2021 | 12/13/2021 | 2 | 0 | 2 | 08/10/2021 | 08/10/2021 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 | 08/05/2021 | 11/5/2023 | Y | EXP | 365 | 03/29/2022 | 06/22/2022 | 86 | 0 | 86 |  |  | 2/3/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175669 | 01752 | 1000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | BEVERLY | 722164 | 01915 | 35.705 | Solar | 05_01_HT5 | 09/29/2025 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SALISBURY | 686547 | 01952 | 9.86 | Solar | 05_05_310W6 | 04/24/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 | 04/24/2025 | 7/24/2026 | Y | EXP | 365 | 10/01/2025 |  | 157 | 0 | 157 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 700800 | 01886 | 10 | Solar | 05_12_51L2 | 07/01/2025 | 08/19/2025 | 34 | 31 | 3 | 08/20/2025 | 08/20/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | BILLERICA | 727151 | 01862 | 28 | Solar | 05_14_2J2 | 10/17/2025 | 10/21/2025 | 2 | 0 | 2 | 10/22/2025 | 10/22/2025 | 27 | 8 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ANDOVER | 311522 | 01810 | 11.4 | Solar | 05_14_57L1 | 01/20/2021 | 01/25/2021 | 2 | 0 | 2 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2021 | 01/20/2021 | 4/5/2022 | Y | EXP | 365 | 08/06/2021 | 12/29/2021 | 146 | 7 | 139 |  |  | 2/9/2022 | Connected |  | N
National Grid | WORCESTER | 648920 | 01602 | 5.76 | Solar | 05_14_70L5 | 11/05/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 11/05/2024 | 1/2/2026 | Y | EXP | 365 | 02/12/2025 | 03/06/2025 | 22 | 0 | 22 |  |  | 3/26/2025 | Connected |  | N
National Grid | OXFORD | 616792 | 01540 | 10 | Solar | 05_14_8L1 | 06/11/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 739766 | 01562 | 7.6 | Solar | 05_01_23W2 | 12/11/2025 | 12/12/2025 | 2 | 0 | 2 | 01/27/2026 | 01/27/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WORCESTER | 386256 | 01605 | 7.6 | Solar | 05_01_406L4 | 10/04/2021 |  | 31 | 26 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175699 | 01752 | 629 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N
National Grid | BEVERLY | 724047 | 01915 | 67.3 | Solar | 05_01_HT5 | 10/03/2025 | 10/27/2025 | 15 | 8 | 7 | 10/28/2025 | 10/28/2025 | 88 | 25 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | AMESBURY | 174836 | 01913 | 1450 | Solar | 05_05_310W6 | 08/31/2012 | 08/31/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/12/2012 | 11/27/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 697184 | 01886 | 17.6 | Solar | 05_12_51L3 | 06/11/2025 | 06/16/2025 | 3 | 0 | 3 | 06/17/2025 | 06/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 225517 | 01862 | 23.4 | Solar | 05_14_2J2 | 05/23/2019 | 06/21/2019 | 19 | 12 | 7 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 |  | 7/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/17/2020 | Connected |  | N
National Grid | LAWRENCE | 318483 | 01843 | 20 | Solar | 05_14_57L1 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 |  | 4/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2021 | Connected |  | N
National Grid | WORCESTER | 652490 | 01609 | 7.6 | Solar | 05_14_70L5 | 11/14/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 6/11/2026 | Y | EXP | 365 | 04/01/2025 | 04/23/2025 | 23 | 0 | 23 |  |  | 8/29/2025 | Connected |  | N
National Grid | OXFORD | 646024 | 01540 | 7.6 | Solar | 05_14_8L1 | 10/10/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 36 | 12 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/10/2024 | 1/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | SPENCER | 750192 | 01562 | 11.5 | Battery Add-On | 05_01_23W2 | 02/09/2026 | 02/10/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 398616 | 01609 | 11.4 | Solar | 05_01_406L4 | 07/06/2022 | 07/11/2022 | 3 | 2 | 1 | 07/12/2022 | 07/12/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 175698 | 01772 | 393 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 12/12/2016 | Connected |  | N
National Grid | BEVERLY | 749603 | 01915 | 34.6 | Solar | 05_01_HT5 | 02/05/2026 |  | 20 | 19 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 175281 | 01840 | 42.57 | Solar | 05_05_310W6 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 4/30/2015 | Connected |  | N
National Grid | WESTFORD | 721115 | 01886 | 0 | Solar | 05_12_51L3 | 09/23/2025 | 10/28/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BILLERICA | 196571 | 01821 | 43.2 | Solar | 05_14_2J3 | 10/04/2018 | 11/01/2018 | 18 | 1 | 17 | 11/02/2018 | 11/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2020 | Connected |  | N
National Grid | LAWRENCE | 330673 | 01843 | 15.2 | Solar | 05_14_57L1 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  | 11/3/2022 | N | EXP | 63 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 660576 | 01609 | 4.55 | Solar | 05_14_70L5 | 12/13/2024 | 01/09/2025 | 2 | 0 | 2 | 01/10/2025 | 01/10/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | OXFORD | 651615 | 01540 | 7.6 | Solar | 05_14_8L1 | 11/12/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 32 | 7 | 25 | 03/21/2025 | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 04/28/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | SPENCER | 172485 | 01562 | 6 | Solar | 05_01_23W2 | 04/12/2018 | 04/12/2018 | 9 | 0 | 9 | 06/06/2018 | 06/06/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2018 | 04/12/2018 | 7/23/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2019 | Connected |  | N
National Grid | WORCESTER | 403041 | 01609 | 5.51 | Solar | 05_01_406L4 | 12/28/2021 | 01/03/2022 | 4 | 0 | 4 | 01/04/2022 | 01/04/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 | 12/28/2021 | 9/6/2023 | Y | EXP | 365 | 06/16/2022 | 07/18/2022 | 33 | 0 | 33 |  |  | 10/27/2022 | Connected |  | N
National Grid | SOUTHBOROUGH | 175697 | 01772 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | HAMILTON | 175132 | 01982 | 75 | Solar | 05_01_HT50 | 11/06/2012 | 11/06/2012 | 7 | 7 | 0 | 11/29/2012 | 11/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2013 |  | 1/31/2013 | N | EXP | 6 | 03/14/2013 | 04/24/2013 | 27 | 0 | 27 | 2/20/2014 | 2/20/2014 | 4/2/2014 | Connected |  | N
National Grid | LAWRENCE | 175478 | 01840 | 250 | Solar | 05_05_310W6 | 03/13/2014 | 03/13/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/30/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 174456 | 01886 | 200 | Solar | 05_12_51L3 | 11/04/2011 | 11/04/2011 | 33 | 0 | 33 | 12/27/2011 | 12/27/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2012 |  | 10/31/2012 | N | EXP | 253 |  |  | 0 | 0 | 0 | 1/28/2013 | 1/28/2013 | 2/12/2013 | Connected |  | N
National Grid | BILLERICA | 550449 | 01821 | 50 | Solar | 05_14_2J3 | 08/25/2023 | 09/21/2023 | 18 | 10 | 8 | 09/22/2023 | 09/22/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 | 08/25/2023 | 12/15/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 391848 | 01843 | 0 | Other | 05_14_57L1 | 12/16/2021 | 01/05/2022 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 02/03/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 666064 | 01609 | 6 | Solar | 05_14_70L5 | 01/15/2025 | 02/04/2025 | 5 | 1 | 4 | 02/05/2025 | 02/05/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2025 | 01/15/2025 | 3/20/2026 | Y | EXP | 365 | 04/12/2025 | 07/07/2025 | 87 | 0 | 87 |  |  | 7/15/2025 | Connected |  | N
National Grid | OXFORD | 658814 | 01540 | 0 | Solar | 05_14_8L1 | 12/06/2024 | 01/07/2025 | 21 | 18 | 3 | 01/08/2025 | 01/08/2025 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2025 | Connected |  | N
National Grid | SPENCER | 207061 | 01562 | 15.2 | Solar | 05_01_23W2 | 01/30/2019 | 02/12/2019 | 7 | 0 | 7 | 02/13/2019 | 02/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2019 |  | 2/27/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2019 | Connected |  | N
National Grid | WORCESTER | 409267 | 01609 | 0 | Other | 05_01_406L4 | 02/14/2023 |  | 104 | 46 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 175704 | 01772 | 1750 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 | 11/28/2016 | 11/28/2016 | 11/28/2016 | Connected |  | N
National Grid | HAMILTON | 177349 | 01982 | 88 | Solar | 05_01_HT50 | 11/23/2016 | 11/23/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2016 | 12/05/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 12/3/2017 | N | STD | 26 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176834 | 01840 | 650 | Solar | 05_05_310W6 | 02/29/2016 | 02/29/2016 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2016 | 05/10/2016 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2017 |  | 12/8/2017 | N | STD | 294 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/14/2017 | Connected |  | N
National Grid | WESTFORD | 174970 | 01886 | 85 | Solar | 05_12_51L3 | 09/10/2013 | 09/10/2013 | 7 | 0 | 7 | 09/20/2013 | 09/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2013 |  | 12/31/2013 | N | EXP | 19 |  |  | 0 | 0 | 0 | 3/7/2014 | 3/7/2014 | 4/4/2014 | Connected |  | N
National Grid | BILLERICA | 174787 | 01821 | 100 | Solar | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 0 | 5 | 11/27/2012 | 11/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2013 | 11/11/2012 | 8/11/2013 | Y | EXP | 3 | 03/07/2014 | 12/08/2014 | 187 | 0 | 187 | 4/23/2014 | 4/23/2014 | 4/24/2014 | Connected |  | N
National Grid | LAWRENCE | 467561 | 01843 | 0 | Battery Add-On | 05_14_57L1 | 04/04/2023 | 05/22/2023 | 33 | 23 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 06/23/2023 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 671256 | 01609 | 3.8 | Solar | 05_14_70L5 | 02/11/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 661249 | 01540 | 7.6 | Solar | 05_14_8L1 | 12/20/2024 | 12/27/2024 | 4 | 0 | 4 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | SPENCER | 209250 | 01562 | 9.92 | Solar | 05_01_23W2 | 03/19/2019 | 03/28/2019 | 6 | 0 | 6 | 03/29/2019 | 03/29/2019 | 22 | 19 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2019 | 03/19/2019 | 4/29/2020 | Y | EXP | 365 | 02/22/2020 | 02/21/2020 | 0 | 0 | 0 |  |  | 4/21/2020 | Connected |  | N
National Grid | WORCESTER | 471444 | 01608 | 6.38 | Solar | 05_01_406L4 | 11/01/2022 | 11/14/2022 | 8 | 3 | 5 | 11/15/2022 | 11/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 11/01/2022 | 3/30/2024 | Y | EXP | 365 | 02/23/2023 | 03/30/2023 | 36 | 0 | 36 |  |  | 5/1/2023 | Connected |  | N
National Grid | SOUTHBOROUGH | 175703 | 01772 | 1400 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | HAMILTON | 592110 | 01982 | 60 | Solar | 05_01_HT52 | 03/11/2024 | 03/20/2024 | 8 | 2 | 6 | 03/21/2024 | 03/21/2024 | 154 | 140 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 176890 | 01840 | 54 | Solar | 05_05_310W6 | 11/13/2015 | 11/13/2015 | 24 | 24 | 0 | 12/21/2015 | 12/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2016 |  | 11/21/2016 | N | EXP | 321 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/3/2017 | Connected |  | N
National Grid | WESTFORD | 175113 | 01886 | 19.99 | Solar | 05_12_51L3 | 10/15/2013 | 10/15/2013 | 7 | 0 | 7 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 | 2/12/2014 | 2/12/2014 | 2/24/2014 | Connected |  | N
National Grid | BILLERICA | 175135 | 01862 | 150 | Solar | 05_14_2J4 | 11/11/2012 | 11/11/2012 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 638330 | 01810 | 9.28 | Solar | 05_14_57L1 | 09/09/2024 | 09/24/2024 | 4 | 0 | 4 | 09/25/2024 | 09/25/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 733690 | 01609 | 10 | Solar | 05_14_70L6 | 11/13/2025 | 11/14/2025 | 3 | 0 | 3 | 12/03/2025 | 12/03/2025 | 63 | 25 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAVERHILL | 661637 | 01832 | 10 | Solar | 05_14_8L1 | 12/19/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/19/2024 | 2/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | SPENCER | 310622 | 01562 | 11.4 | Solar | 05_01_23W2 | 06/23/2021 | 06/25/2021 | 2 | 0 | 2 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 489250 | 01608 | 7.6 | Solar | 05_01_406L4 | 05/01/2023 |  | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 175702 | 01772 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | HAMILTON | 175078 | 01982 | 200 | Solar | 05_01_HT55 | 09/24/2013 | 09/24/2013 | 4 | 0 | 4 | 10/02/2013 | 10/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2013 |  | 12/5/2016 | N | EXP | 1141 |  |  | 0 | 0 | 0 | 10/20/2016 | 10/20/2016 | 12/5/2016 | Connected |  | N
National Grid | LAWRENCE | 177181 | 01840 | 650 | Solar | 05_05_310W6 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2016 | 10/18/2016 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2017 | 08/12/2016 | 2/23/2018 | Y | STD | 347 | 07/06/2017 | 12/19/2017 | 109 | 0 | 109 | 2/15/2018 | 2/15/2018 | 2/16/2018 | Connected |  | N
National Grid | WESTFORD | 175187 | 01886 | 60 | Natural Gas | 05_12_51L3 | 11/14/2013 | 11/14/2013 | 6 | 0 | 6 | 11/25/2013 | 11/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2013 |  | 2/17/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 5/1/2014 | 5/1/2014 | 5/27/2014 | Connected |  | N
National Grid | BILLERICA | 186700 | 01821 | 15.2 | Solar | 05_14_2J4 | 06/22/2018 | 06/22/2018 | 0 | 0 | 0 | 06/25/2018 | 06/25/2018 | 11 | 10 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2018 |  | 7/11/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2018 | Connected |  | N
National Grid | ANDOVER | 646518 | 01810 | 10 | Solar | 05_14_57L1 | 10/11/2024 | 10/17/2024 | 3 | 0 | 3 | 10/18/2024 | 10/18/2024 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | WORCESTER | 733043 | 01609 | 22.42 | Solar | 05_14_70L6 | 11/11/2025 | 11/14/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | OXFORD | 669874 | 01540 | 7.6 | Solar | 05_14_8L1 | 02/04/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2025 | Connected |  | N
National Grid | SPENCER | 371778 | 01562 | 11.4 | Solar | 05_01_23W2 | 07/23/2021 | 07/26/2021 | 1 | 0 | 1 | 07/27/2021 | 07/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 |  | 3/24/2023 | N | EXP | 535 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 505438 | 01605 | 15 | Solar | 05_01_406L4 | 03/07/2023 | 03/09/2023 | 2 | 0 | 2 | 03/10/2023 | 03/10/2023 | 117 | 95 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | MARLBOROUGH | 175701 | 01752 | 2000 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 1/28/2016 | Y | STD | 148 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | BEVERLY | 174174 | 01915 | 135 | Solar | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 8/20/2012 | N | EXP | 114 |  |  | 0 | 0 | 0 | 6/12/2015 | 6/12/2015 | 3/2/2013 | Connected |  | N
National Grid | LAWRENCE | 186377 | 01840 | 740 | Solar | 05_05_310W6 | 06/25/2018 | 06/25/2018 | 38 | 28 | 10 | 08/20/2018 | 08/20/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2018 |  | 12/31/2020 | N | EXP | 499 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | WESTFORD | 175468 | 01886 | 4.73 | Solar | 05_12_51L3 | 11/25/2014 | 11/25/2014 | 5 | 0 | 5 | 12/04/2014 | 12/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 11/25/2014 | 4/30/2015 | Y | EXP | 71 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 | 3/9/2015 | 3/9/2015 | 11/23/2015 | Connected |  | N
National Grid | BILLERICA | 586766 | 01821 | 15.76 | Solar | 05_14_2J4 | 05/08/2024 | 06/21/2024 | 30 | 29 | 1 | 06/24/2024 | 06/24/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 9/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | ANDOVER | 651800 | 01810 | 7.6 | Solar | 05_14_57L1 | 11/04/2024 | 01/16/2025 | 4 | 0 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 | 11/04/2024 | 3/12/2026 | Y | EXP | 365 | 05/16/2025 | 11/21/2025 | 190 | 0 | 190 |  |  | 11/24/2025 | Connected |  | N
National Grid | WORCESTER | 175994 | 01609 | 16.35 | Solar | 05_14_70L6 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/16/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 10/6/2016 | 10/6/2016 | 10/6/2016 | Connected |  | N
National Grid | OXFORD | 672761 | 01540 | 10 | Solar | 05_14_8L1 | 02/18/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 83 | 64 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 371327 | 01562 | 19 | Solar | 05_01_23W2 | 07/21/2021 | 08/17/2021 | 19 | 18 | 1 | 08/18/2021 | 08/18/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2021 |  | 9/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | WORCESTER | 536014 | 01605 | 7.6 | Solar | 05_01_406L4 | 06/22/2023 | 08/06/2023 | 4 | 1 | 3 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 06/22/2023 | 7/10/2025 | Y | EXP | 365 | 09/11/2024 | 10/10/2024 | 30 | 0 | 30 |  |  | 10/22/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 175700 | 01772 | 860 | Solar | 05_01_55K11 | 08/12/2014 | 08/12/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2014 | 08/26/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 02/24/2015 | 06/24/2016 | 331 | 0 | 331 | 6/24/2016 | 08/12/2014 | 2/3/2016 | Y | STD | 142 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | Connected |  | N
National Grid | BEVERLY | 174173 | 01915 | 75 | Solar | 05_01_HT59 | 04/27/2012 | 04/27/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 5/15/2012 | N | EXP | 211 |  |  | 0 | 0 | 0 | 2/6/2013 | 2/6/2013 | 3/2/2013 | Connected |  | N
National Grid | LAWRENCE | 254944 | 01840 | 15.2 | Solar | 05_05_310W6 | 09/18/2019 | 09/20/2019 | 1 | 1 | 0 | 09/23/2019 | 09/23/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2019 | 09/18/2019 | 5/11/2020 | Y | EXP | 23 | 11/13/2019 | 01/07/2020 | 55 | 0 | 55 |  |  | 1/14/2020 | Connected |  | N
National Grid | WESTFORD | 177285 | 01886 | 10 | Solar | 05_12_51L3 | 06/16/2016 | 06/16/2016 | 1 | 1 | 0 | 06/20/2016 | 06/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 | 06/16/2016 | 6/21/2017 | Y | EXP | 358 | 11/10/2016 | 01/05/2017 | 36 | 0 | 36 | 1/9/2017 | 1/9/2017 | 1/9/2017 | Connected |  | N
National Grid | BILLERICA | 652372 | 01821 | 116 | Solar | 05_14_2J6 | 05/08/2025 | 09/18/2025 | 91 | 82 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 02/20/2026 |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ANDOVER | 665155 | 01810 | 10 | Solar | 05_14_57L1 | 01/13/2025 | 02/25/2025 | 19 | 15 | 4 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | WORCESTER | 176246 | 01609 | 17.2 | Solar | 05_14_70L6 | 04/30/2015 | 04/30/2015 | 5 | 5 | 0 | 05/13/2015 | 05/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2015 |  | 10/30/2015 | N | EXP | 169 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | OXFORD | 675590 | 01540 | 7.6 | Solar | 05_14_8L1 | 03/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SPENCER | 379039 | 01562 | 15.2 | Solar | 05_01_23W2 | 08/31/2021 | 09/20/2021 | 13 | 13 | 0 | 09/21/2021 | 09/21/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 7/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 543392 | 01602 | 6 | Solar | 05_01_406L4 | 08/11/2023 | 08/14/2023 | 1 | 0 | 1 | 08/15/2023 | 08/15/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2023 |  | 10/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2023 | Connected |  | N
National Grid | MARLBOROUGH | 178660 | 01752 | 1000 | Solar | 05_01_55K11 | 02/06/2018 | 04/06/2018 | 31 | 14 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 05/02/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 | 02/06/2018 | 11/22/2021 | Y | STD | 416 | 01/09/2021 | 10/21/2021 | 285 | 3 | 282 |  |  | 11/3/2021 | Connected |  | N
National Grid | BEVERLY | 674157 | 01915 | 84.6 | Solar | 05_01_HT6 | 03/11/2025 |  | 99 | 48 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 369538 | 01840 | 220 | Solar | 05_05_310W6 | 07/21/2021 | 08/01/2021 | 8 | 0 | 8 |  |  | 31 | 3 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2022 | 07/21/2021 | 7/9/2024 | Y | STD | 44 | 03/23/2024 | 03/27/2024 | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | WESTFORD | 178288 | 01886 | 7.6 | Solar | 05_12_51L3 | 03/28/2018 | 03/28/2018 | 7 | 0 | 7 | 04/09/2018 | 04/09/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 | 03/28/2018 | 7/15/2021 | Y | EXP | 317 |  |  | 0 | 0 | 0 |  |  | 6/22/2021 | Connected |  | N
National Grid | BILLERICA | 418695 | 01821 | 57.6 | Solar | 05_14_2J8 | 03/18/2022 | 04/29/2022 | 29 | 19 | 10 | 05/02/2022 | 05/02/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2022 |  | 4/16/2026 | N | EXP | 184 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LAWRENCE | 673926 | 01843 | 0 | Battery Add-On | 05_14_57L1 | 02/24/2025 | 03/17/2025 | 15 | 12 | 3 | 03/18/2025 | 03/18/2025 | 104 | 82 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2025 |  | 8/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | WORCESTER | 177836 | 01609 | 15.2 | Solar | 05_14_70L6 | 08/09/2017 | 08/09/2017 | 5 | 5 | 0 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/14/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 3/16/2018 | Connected |  | N
National Grid | OXFORD | 685276 | 01540 | 15.76 | Solar | 05_14_8L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 65 | 24 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SPENCER | 485090 | 01562 | 17.45 | Solar | 05_01_23W2 | 12/21/2022 | 12/22/2022 | 1 | 0 | 1 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2023 | Connected |  | N
National Grid | WORCESTER | 579324 | 01602 | 1.45 | Solar | 05_01_406L4 | 02/01/2024 | 04/17/2024 | 27 | 25 | 2 | 04/18/2024 | 04/18/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 | 02/01/2024 | 5/7/2025 | Y | EXP | 365 | 06/05/2024 | 08/29/2024 | 86 | 0 | 86 |  |  | 9/26/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 682705 | 01772 | 24.7 | Solar | 05_01_55W1 | 04/03/2025 | 04/08/2025 | 4 | 1 | 3 | 04/09/2025 | 04/09/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BEVERLY | 175192 | 01915 | 150 | Natural Gas | 05_01_HT61 | 11/21/2013 | 11/21/2013 | 6 | 0 | 6 | 12/04/2013 | 12/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2013 |  | 3/31/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 | 6/2/2014 | 6/2/2014 | 6/2/2014 | Connected |  | N
National Grid | LAWRENCE | 426147 | 01840 | 10 | Solar | 05_05_310W6 | 06/01/2022 | 06/30/2022 | 20 | 18 | 2 | 07/01/2022 | 07/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 | 06/01/2022 | 6/13/2024 | Y | EXP | 365 | 10/11/2022 | 06/14/2023 | 247 | 0 | 247 |  |  | 8/7/2023 | Connected |  | Y
National Grid | WESTFORD | 184467 | 01886 | 51.75 | Solar | 05_12_51L3 | 06/18/2018 | 06/18/2018 | 0 | 0 | 0 | 06/22/2018 | 06/22/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 10/7/2019 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  | 4/17/2019 | Connected |  | N
National Grid | BILLERICA | 194466 | 01821 | 480 | Solar | 05_14_2J8 | 08/27/2018 | 08/28/2018 | 4 | 0 | 4 | 09/24/2018 | 09/24/2018 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 692947 | 01843 | 15.2 | Solar | 05_14_57L1 | 05/20/2025 | 05/27/2025 | 4 | 0 | 4 | 05/28/2025 | 05/28/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | WORCESTER | 189305 | 01609 | 7.6 | Solar | 05_14_70L6 | 06/27/2018 | 06/27/2018 | 9 | 6 | 3 | 09/14/2018 | 09/14/2018 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 658936 | 01540 | 499 | Solar | 05_14_8L2 | 04/08/2025 | 04/24/2025 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2025 | 05/28/2025 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SPENCER | 542998 | 01562 | 22.8 | Solar | 05_01_23W2 | 09/22/2023 | 10/05/2023 | 9 | 8 | 1 | 10/06/2023 | 10/06/2023 | 81 | 34 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 585919 | 01609 | 23.4 | Solar | 05_01_406L4 | 01/31/2024 | 02/23/2024 | 16 | 14 | 2 | 02/26/2024 | 02/26/2024 | 32 | 29 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 714377 | 01772 | 0 | Other | 05_01_55W1 | 09/26/2025 | 11/12/2025 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 12/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HAMILTON | 175436 | 01982 | 150 | Natural Gas | 05_01_HT61 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 | 12/03/2014 | 12/03/2014 | 0 | 0 | 0 | 09/10/2015 | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 |  | 03/16/2016 | 127 | 114 | 13 |  |  | 0 | 0 | 0 | 3/23/2016 |  | 12/31/2016 | N | EXP | 283 |  |  | 0 | 0 | 0 | 4/26/2016 | 4/26/2016 | 5/5/2016 | Connected |  | N
National Grid | LAWRENCE | 618186 | 01840 | 9.765 | Solar | 05_05_310W6 | 07/26/2024 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 184417 | 01886 | 24 | Solar | 05_12_51L3 | 06/22/2018 | 06/22/2018 | 2 | 2 | 0 | 06/27/2018 | 06/27/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2018 |  | 11/1/2019 | N | EXP | 483 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | BILLERICA | 552093 | 01821 | 200 | Solar | 05_14_2J8 | 08/31/2023 | 09/28/2023 | 20 | 10 | 10 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 723177 | 01843 | 17.6 | Solar | 05_14_57L1 | 10/01/2025 | 10/13/2025 | 7 | 3 | 4 | 10/14/2025 | 10/14/2025 | 72 | 61 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 343928 | 01609 | 19 | Solar | 05_14_70L6 | 02/25/2021 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 726407 | 01540 | 7.6 | Solar | 05_14_8L2 | 10/14/2025 | 12/04/2025 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | RUTLAND | 575450 | 01543 | 7.6 | Solar | 05_01_23W2 | 12/04/2023 | 01/09/2024 | 25 | 24 | 1 | 01/10/2024 | 01/10/2024 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 602577 | 01605 | 10 | Solar | 05_01_406L4 | 04/12/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 724459 | 01772 | 7.6 | Solar | 05_01_55W1 | 10/08/2025 | 11/20/2025 | 3 | 0 | 3 | 12/23/2025 | 12/23/2025 | 50 | 34 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 176397 | 01982 | 2649 | Natural Gas | 05_01_HT61 | 03/10/2016 | 03/10/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2016 | 06/13/2016 | 60 | 44 | 16 |  |  | 0 | 0 | 0 | 10/04/2016 | 12/13/2016 | 47 | 13 | 34 | 1/25/2017 | 03/10/2016 | 1/31/2019 | Y | STD | 736 | 01/03/2018 | 07/26/2018 | 204 | 0 | 204 | 1/25/2018 | 1/25/2018 | 1/10/2019 | Connected |  | N
National Grid | LAWRENCE | 631656 | 01840 | 10 | Solar | 05_05_310W6 | 08/09/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 189641 | 01886 | 5 | Solar | 05_12_51L3 | 02/26/2019 | 07/05/2018 | 5 | 0 | 5 | 03/07/2019 | 03/07/2019 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 681059 | 01821 | 10 | Solar | 05_14_2J8 | 04/04/2025 | 04/22/2025 | 3 | 0 | 3 | 05/02/2025 | 05/02/2025 | 45 | 32 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 | 04/04/2025 | 7/15/2026 | Y | EXP | 365 | 11/04/2025 | 11/26/2025 | 23 | 0 | 23 |  |  | 1/30/2026 | Connected |  | N
National Grid | METHUEN | 726835 | 01844 | 17.48 | Solar | 05_14_57L1 | 10/15/2025 | 10/20/2025 | 3 | 0 | 3 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 367044 | 01609 | 19 | Solar | 05_14_70L6 | 06/30/2021 | 07/01/2021 | 1 | 0 | 1 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 726315 | 01540 | 20 | Solar | 05_14_8L2 | 10/14/2025 | 10/24/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 581452 | 01543 | 7.6 | Solar | 05_01_23W2 | 01/04/2024 | 01/17/2024 | 9 | 7 | 2 | 01/18/2024 | 01/18/2024 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 3/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | WORCESTER | 605711 | 01608 | 15.2 | Solar | 05_01_406L4 | 05/03/2024 | 05/09/2024 | 4 | 3 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  | 6/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/2/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 730854 | 01772 | 200 | Solar | 05_01_55W1 | 02/09/2026 |  | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HAMILTON | 419356 | 01982 | 240 | Solar | 05_05_106W42 | 05/26/2022 | 06/13/2022 | 11 | 3 | 8 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2023 | 05/26/2022 | 6/9/2026 | Y | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | LAWRENCE | 638307 | 01840 | 11.517 | Solar | 05_05_310W6 | 09/12/2024 | 10/01/2024 | 4 | 0 | 4 | 10/02/2024 | 10/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 11/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | WESTFORD | 306908 | 01886 | 13.6 | Solar | 05_12_51L3 | 08/14/2020 | 08/18/2020 | 2 | 2 | 0 | 08/19/2020 | 08/19/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2020 |  | 8/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2020 | Connected |  | N
National Grid | BILLERICA | 745534 | 01821 | 999 | Solar | 05_14_2L1 | 02/26/2026 |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 683366 | 01841 | 4998 | Other | 05_14_57L2 | 10/16/2025 | 12/04/2025 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WORCESTER | 412558 | 01609 | 9.8 | Solar | 05_14_70L6 | 03/01/2022 | 03/02/2022 | 1 | 0 | 1 | 03/03/2022 | 03/03/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/01/2022 | 9/20/2023 | Y | EXP | 365 | 08/18/2022 | 09/15/2022 | 29 | 0 | 29 |  |  | 1/4/2023 | Connected |  | N
National Grid | OXFORD | 733514 | 01540 | 15 | Solar | 05_14_8L2 | 11/13/2025 | 11/17/2025 | 1 | 0 | 1 | 12/24/2025 | 12/24/2025 | 35 | 17 | 18 | 03/03/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | RUTLAND | 615221 | 01543 | 9.88 | Solar | 05_01_23W2 | 06/03/2024 | 07/03/2024 | 5 | 2 | 3 | 07/05/2024 | 07/05/2024 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/03/2024 | 7/19/2026 | Y | EXP | 365 | 08/29/2024 | 09/30/2024 | 33 | 0 | 33 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 639121 | 01605 | 10 | Solar | 05_01_406L4 | 09/10/2024 | 09/25/2024 | 4 | 0 | 4 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 740108 | 01745 | 0 | Battery Add-On | 05_01_55W1 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BEVERLY | 175293 | 01915 | 20 | Solar | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2014 |  | 2/27/2015 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/16/2015 | 4/16/2015 | 4/16/2015 | Connected |  | N
National Grid | LAWRENCE | 660473 | 01840 | 5.76 | Solar | 05_05_310W6 | 12/13/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | WESTFORD | 309531 | 01886 | 5.8 | Solar | 05_12_51L3 | 09/01/2020 | 09/02/2020 | 1 | 1 | 0 | 09/03/2020 | 09/03/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2020 |  | 9/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2020 | Connected |  | N
National Grid | BILLERICA | 175307 | 01821 | 910 | Solar | 05_14_2L1 | 06/30/2014 | 06/30/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2016 | 06/30/2014 | 8/3/2021 | Y | STD | 316 | 05/21/2019 | 07/21/2021 | 406 | 4 | 402 |  |  | 8/3/2021 | Connected |  | N
National Grid | LAWRENCE | 740323 | 01841 | 23 | Solar | 05_14_57L2 | 12/15/2025 | 12/17/2025 | 2 | 0 | 2 | 12/18/2025 | 12/18/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 1/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 430494 | 01605 | 15.2 | Solar | 05_14_70L6 | 05/16/2022 | 05/17/2022 | 1 | 0 | 1 | 05/18/2022 | 05/18/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2022 |  | 6/22/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | N
National Grid | OXFORD | 738886 | 01540 | 3.8 | Solar | 05_14_8L2 | 12/09/2025 | 12/11/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RUTLAND | 624586 | 01543 | 21.38 | Solar | 05_01_23W2 | 07/18/2024 | 07/22/2024 | 2 | 0 | 2 | 07/23/2024 | 07/23/2024 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/18/2024 | 9/21/2025 | Y | EXP | 365 | 10/29/2024 | 11/01/2024 | 4 | 0 | 4 |  |  | 5/22/2025 | Connected |  | N
National Grid | FALL RIVER | 646413 | 02721 | 10 | Solar | 05_01_406L4 | 10/18/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 | 10/18/2024 | 2/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 741875 | 01772 | 10 | Solar | 05_01_55W1 | 12/22/2025 | 12/29/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 | 12/22/2025 | 2/6/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | HAMILTON | 175292 | 01982 | 20 | Solar | 05_05_106W42 | 11/07/2014 | 11/07/2014 | 6 | 2 | 4 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 2/27/2015 | N | EXP | 8 |  |  | 0 | 0 | 0 | 2/27/2015 | 2/27/2015 | 4/17/2015 | Connected |  | N
National Grid | CHELMSFORD | 670809 | 01863 | 7.6 | Solar | 05_05_310W6 | 02/07/2025 | 02/27/2025 | 4 | 0 | 4 | 02/28/2025 | 02/28/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 339578 | 01886 | 7.6 | Solar | 05_12_51L3 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  | 11/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2021 | Connected |  | N
National Grid | BILLERICA | 176776 | 01821 | 390 | Solar | 05_14_2L1 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 02/15/2016 | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/24/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 | 11/04/2015 | 6/14/2019 | Y | EXP | 126 | 07/11/2017 | 08/23/2017 | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | LAWRENCE | 750891 | 01841 | 15.2 | Solar | 05_14_57L2 | 02/12/2026 | 02/17/2026 | 2 | 0 | 2 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WORCESTER | 460075 | 01609 | 15.2 | Solar | 05_14_70L6 | 09/19/2022 | 09/22/2022 | 3 | 0 | 3 | 09/23/2022 | 09/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 3/6/2024 | N | EXP | 365 | 01/07/2023 | 03/03/2023 | 56 | 0 | 56 |  |  | 5/24/2023 | Connected |  | N
National Grid | OXFORD | 175079 | 01540 | 300 | Solar | 05_14_8L2 | 09/30/2013 | 09/30/2013 | 7 | 0 | 7 | 10/10/2013 | 10/10/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2013 |  | 12/31/2013 | N | EXP | 11 |  |  | 0 | 0 | 0 | 3/17/2014 | 3/17/2014 | 5/27/2014 | Connected |  | N
National Grid | RUTLAND | 736356 | 01543 | 10 | Solar | 05_01_23W3 | 11/25/2025 | 11/26/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | FALL RIVER | 646924 | 02721 | 5.76 | Solar | 05_01_406L4 | 10/29/2024 | 12/03/2024 | 11 | 5 | 6 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 | 10/29/2024 | 1/24/2026 | Y | EXP | 365 | 02/15/2025 | 02/27/2025 | 13 | 0 | 13 |  |  | 4/12/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 746396 | 01772 | 10 | Solar | 05_01_55W1 | 01/20/2026 | 01/22/2026 | 3 | 0 | 3 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WENHAM | 177918 | 01984 | 312 | Solar | 05_05_106W42 | 10/20/2017 | 10/20/2017 | 5 | 0 | 5 | 11/03/2017 | 11/03/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 |  | 10/28/2018 | N | EXP | 328 |  |  | 0 | 0 | 0 |  |  | 8/3/2018 | Connected |  | N
National Grid | CHELMSFORD | 671407 | 01863 | 7.6 | Solar | 05_05_310W6 | 02/12/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2025 | Connected |  | N
National Grid | WESTFORD | 342563 | 01886 | 7.68 | Solar | 05_12_51L3 | 02/17/2021 | 02/23/2021 | 4 | 4 | 0 | 02/24/2021 | 02/24/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2021 | Connected |  | N
National Grid | BILLERICA | 177005 | 01821 | 720 | Solar | 05_14_2L1 | 10/10/2016 | 10/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 12/15/2016 | 45 | 33 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 10/10/2016 | 10/30/2020 | Y | STD | 77 | 08/06/2019 | 10/16/2020 | 438 | 5 | 433 |  |  | 10/21/2020 | Connected |  | N
National Grid | LAWRENCE | 178144 | 01841 | 0 | Solar | 05_14_57L2 | 04/12/2018 | 04/12/2018 | 10 | 0 | 10 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 10/22/2020 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 2/18/2020 | Connected |  | N
National Grid | WORCESTER | 579214 | 01609 | 34.5 | Solar | 05_14_70L6 | 12/20/2023 |  | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 176483 | 01540 | 6 | Solar | 05_14_8L2 | 05/23/2016 | 05/23/2016 | 0 | 0 | 0 | 05/25/2016 | 05/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/23/2016 | 5/30/2017 | Y | EXP | 358 | 11/28/2016 | 12/14/2016 | 12 | 0 | 12 | 4/20/2017 | 4/20/2017 | 4/26/2017 | Connected |  | N
National Grid | RUTLAND | 743208 | 01543 | 5.76 | Solar | 05_01_23W3 | 01/02/2026 | 01/05/2026 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 650792 | 02721 | 8.41 | Solar | 05_01_406L4 | 11/01/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 751227 | 01772 | 15.76 | Solar | 05_01_55W1 | 02/13/2026 | 02/19/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HAMILTON | 178620 | 01982 | 144 | Solar | 05_05_106W42 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 | 03/05/2018 | 03/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2018 |  | 2/7/2019 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | CHELMSFORD | 706145 | 01824 | 15.356 | Solar | 05_05_310W6 | 07/24/2025 | 07/31/2025 | 5 | 1 | 4 | 08/01/2025 | 08/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 07/24/2025 | 9/9/2026 | Y | EXP | 365 | 10/04/2025 | 11/21/2025 | 49 | 0 | 49 |  |  | 11/24/2025 | Connected |  | N
National Grid | WESTFORD | 354859 | 01886 | 6.38 | Solar | 05_12_51L3 | 04/27/2021 | 04/28/2021 | 1 | 1 | 0 | 04/29/2021 | 04/29/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  | 4/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | BILLERICA | 178330 | 01821 | 7.6 | Solar | 05_14_2L1 | 03/30/2018 | 03/30/2018 | 5 | 0 | 5 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 9/23/2020 | N | EXP | 34 |  |  | 0 | 0 | 0 |  |  | 8/20/2020 | Connected |  | N
National Grid | LAWRENCE | 178697 | 01841 | 7.6 | Solar | 05_14_57L2 | 02/06/2018 | 02/06/2018 | 16 | 0 | 16 | 02/20/2018 | 02/20/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/12/2019 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | Connected |  | N
National Grid | WORCESTER | 588066 | 01602 | 9.765 | Solar | 05_14_70L6 | 02/12/2024 | 02/21/2024 | 7 | 5 | 2 | 02/22/2024 | 02/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/12/2024 | 4/24/2025 | Y | EXP | 365 | 05/23/2024 | 09/13/2024 | 93 | 0 | 93 |  |  | 7/26/2024 | Connected |  | N
National Grid | OXFORD | 178185 | 01540 | 7.6 | Solar | 05_14_8L2 | 04/13/2018 | 04/13/2018 | 5 | 0 | 5 | 04/23/2018 | 04/23/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/21/2019 | N | EXP | 334 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 744673 | 01543 | 20.16 | Solar | 05_01_23W3 | 01/16/2026 | 01/27/2026 | 5 | 3 | 2 | 01/28/2026 | 01/28/2026 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 657763 | 02721 | 10 | Solar | 05_01_406L4 | 12/02/2024 | 01/13/2025 | 16 | 11 | 5 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174218 | 01752 | 11.38 | Solar | 05_01_55W1 | 01/31/2012 | 01/31/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2012 |  | 3/1/2012 | N | EXP | 43 |  |  | 0 | 0 | 0 | 7/23/2012 | 7/23/2012 | 8/7/2012 | Connected |  | N
National Grid | BEVERLY | 212413 | 01915 | 233.3 | Solar | 05_05_106W42 | 03/04/2019 | 03/15/2019 | 8 | 4 | 4 | 03/18/2019 | 03/18/2019 | 7 | 3 | 4 | 04/17/2019 | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 05/07/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 659021 | 01824 | 0 | Other | 05_05_311W1 | 03/31/2025 | 06/18/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2025 | 07/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTFORD | 406056 | 01886 | 0 | Battery Add-On | 05_12_51L3 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 02/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 178690 | 01821 | 240 | Solar | 05_14_2L1 | 12/20/2017 | 12/20/2017 | 0 | 0 | 0 | 12/20/2017 | 12/20/2017 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 273553 | 01841 | 7.6 | Solar | 05_14_57L2 | 01/23/2020 | 02/05/2020 | 8 | 3 | 5 | 02/06/2020 | 02/06/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 | 01/23/2020 | 7/15/2021 | Y | EXP | 365 | 04/06/2021 | 04/15/2021 | 9 | 0 | 9 |  |  | 4/30/2021 | Connected |  | N
National Grid | WORCESTER | 604030 | 01602 | 5 | Solar | 05_14_70L6 | 04/18/2024 | 05/01/2024 | 3 | 0 | 3 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | OXFORD | 178228 | 01540 | 10.4 | Solar | 05_14_8L2 | 01/03/2018 | 01/03/2018 | 15 | 9 | 6 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 1/10/2019 | N | EXP | 346 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | RUTLAND | 174253 | 01543 | 1095 | Solar | 05_01_23W3 | 02/27/2012 | 02/27/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2012 | 05/21/2012 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 683430 | 02721 | 7.6 | Solar | 05_01_406L4 | 04/10/2025 | 04/28/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 | 04/10/2025 | 6/30/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/24/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 174355 | 01772 | 1000 | Solar | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 581461 | 01982 | 6 | Solar | 05_05_106W42 | 02/08/2024 | 02/21/2024 | 8 | 5 | 3 | 02/22/2024 | 02/22/2024 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | TYNGSBORO | 730626 | 01879 | 10 | Solar | 05_05_311W1 | 11/11/2025 | 11/21/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 39 | 23 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 413470 | 01886 | 15.2 | Solar | 05_12_51L3 | 08/16/2022 | 02/26/2022 | 2 | 0 | 2 | 08/19/2022 | 08/19/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2022 |  | 9/27/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 209967 | 01821 | 910 | Solar | 05_14_2L1 | 03/04/2019 | 03/19/2019 | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/20/2019 | 08/22/2019 | 101 | 35 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 277368 | 01841 | 9.84 | Solar | 05_14_57L2 | 02/03/2020 | 02/05/2020 | 1 | 0 | 1 | 02/06/2020 | 02/06/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2020 | 02/03/2020 | 2/3/2021 | Y | EXP | 365 | 07/11/2020 | 07/27/2020 | 16 | 0 | 16 |  |  | 8/18/2020 | Connected |  | N
National Grid | LEOMINSTER | 610202 | 01524 | 4.188 | Solar | 05_14_70L6 | 05/14/2024 | 07/09/2024 | 16 | 9 | 7 | 07/10/2024 | 07/10/2024 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 05/14/2024 | 9/10/2025 | Y | EXP | 365 | 09/26/2024 | 10/24/2024 | 29 | 0 | 29 |  |  | 12/4/2024 | Connected |  | N
National Grid | OXFORD | 178295 | 01540 | 15.2 | Solar | 05_14_8L2 | 11/15/2017 | 11/15/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2018 |  | 11/21/2018 | N | EXP | 153 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 174992 | 01543 | 13.11 | Solar | 05_01_23W3 | 03/11/2013 | 03/11/2013 | 5 | 0 | 5 | 03/20/2013 | 03/20/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2013 |  | 7/5/2013 | N | EXP | 93 |  |  | 0 | 0 | 0 | 4/3/2013 | 4/3/2013 | 5/24/2013 | Connected |  | N
National Grid | FALL RIVER | 694012 | 02724 | 7.6 | Solar | 05_01_406L4 | 05/29/2025 | 06/20/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 05/29/2025 | 8/4/2026 | Y | EXP | 365 | 10/11/2025 | 10/10/2025 | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174354 | 01752 | 2000 | Solar | 05_01_55W1 | 05/17/2012 | 05/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/30/2012 | 08/16/2012 | 54 | 0 | 54 |  |  | 0 | 0 | 0 | 03/28/2014 | 03/28/2014 | 0 | 0 | 0 | 9/12/2013 | 05/17/2012 | 12/31/2012 | Y | STD | 255 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 11/3/2015 | Connected |  | N
National Grid | HAMILTON | 661388 | 01982 | 7.6 | Solar | 05_05_106W42 | 12/24/2024 | 01/29/2025 | 9 | 4 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 | 12/24/2024 | 3/24/2026 | Y | EXP | 365 | 05/02/2025 | 07/16/2025 | 76 | 0 | 76 |  |  | 7/22/2025 | Connected |  | N
National Grid | CHELMSFORD | 175172 | 01863 | 85 | Solar | 05_05_311W1 | 11/16/2012 | 11/16/2012 | 10 | 0 | 10 | 12/05/2012 | 12/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2013 | 11/16/2012 | 4/1/2013 | Y | EXP | 39 |  |  | 0 | 0 | 0 | 2/21/2013 | 2/21/2013 | 7/12/2013 | Connected |  | N
National Grid | WESTFORD | 484468 | 01886 | 0 | Solar | 05_12_51L3 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 76 | 25 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 241760 | 01821 | 7.6 | Solar | 05_14_2L1 | 07/24/2019 | 07/25/2019 | 0 | 0 | 0 | 07/26/2019 | 07/26/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 301130 | 01841 | 10 | Solar | 05_14_57L2 | 08/17/2020 | 08/26/2020 | 7 | 7 | 0 | 08/27/2020 | 08/27/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 08/17/2020 | 8/26/2021 | Y | EXP | 365 | 04/21/2021 | 04/30/2021 | 9 | 0 | 9 |  |  | 5/4/2021 | Connected |  | N
National Grid | WORCESTER | 645607 | 01602 | 5.76 | Solar | 05_14_70L6 | 11/20/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | OXFORD | 190234 | 01540 | 70.2 | Solar | 05_14_8L2 | 08/10/2018 | 08/28/2018 | 11 | 0 | 11 | 08/29/2018 | 08/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 176357 | 01543 | 10 | Solar | 05_01_23W3 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2015 |  | 10/30/2015 | N | EXP | 163 |  |  | 0 | 0 | 0 | 7/23/2015 | 7/23/2015 | 11/24/2015 | Connected |  | N
National Grid | FALL RIVER | 701278 | 02724 | 18.24 | Solar | 05_01_406L4 | 07/02/2025 | 07/17/2025 | 9 | 7 | 2 | 07/18/2025 | 07/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 174384 | 01752 | 4 | Solar | 05_01_55W1 | 05/31/2012 | 05/31/2012 | 7 | 0 | 7 | 06/13/2012 | 06/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2012 |  | 8/31/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 9/24/2012 | Connected |  | N
National Grid | HAMILTON | 663644 | 01982 | 10 | Solar | 05_05_106W42 | 01/03/2025 | 01/16/2025 | 7 | 3 | 4 | 01/17/2025 | 01/17/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/03/2025 | 3/17/2026 | Y | EXP | 365 | 03/08/2025 | 08/12/2025 | 158 | 0 | 158 |  |  | 8/29/2025 | Connected |  | N
National Grid | CHELMSFORD | 177943 | 01863 | 333.2 | Solar | 05_05_311W1 | 08/18/2017 | 08/18/2017 | 127 | 91 | 36 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2018 | 08/18/2017 | 2/10/2021 | Y | EXP | 68 |  |  | 0 | 0 | 0 |  |  | 2/10/2021 | Connected |  | N
National Grid | WESTFORD | 485207 | 01886 | 19 | Solar | 05_12_51L3 | 12/13/2022 | 12/15/2022 | 2 | 0 | 2 | 12/16/2022 | 12/16/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2023 | Connected |  | N
National Grid | BILLERICA | 332924 | 01821 | 10 | Solar | 05_14_2L1 | 12/18/2020 | 12/22/2020 | 1 | 0 | 1 | 12/23/2020 | 12/23/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 307057 | 01841 | 15.2 | Solar | 05_14_57L2 | 08/17/2020 | 08/20/2020 | 2 | 0 | 2 | 08/21/2020 | 08/21/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2020 | Connected |  | N
National Grid | LEICESTER | 650194 | 01524 | 18.24 | Solar | 05_14_70L6 | 10/28/2024 | 10/30/2024 | 2 | 0 | 2 | 10/31/2024 | 10/31/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | OXFORD | 199996 | 01540 | 6 | Solar | 05_14_8L2 | 11/01/2018 | 11/19/2018 | 1 | 0 | 1 | 11/20/2018 | 11/20/2018 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/24/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 176882 | 01543 | 7.53 | Solar | 05_01_23W3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2016 |  | 5/10/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/27/2016 | 10/27/2016 | 10/27/2016 | Connected |  | N
National Grid | FALL RIVER | 710676 | 02721 | 15.58 | Solar | 05_01_406L4 | 08/08/2025 | 08/18/2025 | 5 | 0 | 5 | 08/19/2025 | 08/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174431 | 01752 | 4680 | Solar | 05_01_55W1 | 06/27/2012 | 06/27/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2012 | 10/09/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/27/2012 | 10/12/2017 | Y | STD | 967 | 03/15/2017 | 08/18/2017 | 109 | 0 | 109 | 8/23/2017 | 8/23/2017 | 9/29/2017 | Connected |  | N
National Grid | HAMILTON | 518149 | 01982 | 250 | Natural Gas | 05_05_106W43 | 08/17/2023 | 06/24/2024 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2024 | 07/19/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  | 7/2/2026 | N | STD | 12 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TYNGSBORO | 196371 | 01879 | 100 | Solar | 05_05_311W1 | 09/19/2018 | 10/05/2018 | 7 | 0 | 7 | 10/08/2018 | 10/08/2018 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  | 6/1/2020 | N | EXP | 53 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 517501 | 01886 | 0 | Solar | 05_12_51L3 | 04/06/2023 | 06/02/2023 | 39 | 38 | 1 | 06/05/2023 | 06/05/2023 | 289 | 271 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2024 | 04/06/2023 | 11/30/2025 | Y | EXP | 365 | 10/03/2024 | 11/12/2024 | 41 | 0 | 41 |  |  |  | Withdrawn |  | Y
National Grid | BILLERICA | 337901 | 01821 | 66.6 | Solar | 05_14_2L1 | 01/22/2021 | 02/03/2021 | 7 | 0 | 7 | 02/04/2021 | 02/04/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 4/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2022 | Connected |  | N
National Grid | LAWRENCE | 312114 | 01841 | 13.6 | Solar | 05_14_57L2 | 09/17/2020 | 09/24/2020 | 4 | 0 | 4 | 09/25/2020 | 09/25/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | Y
National Grid | WORCESTER | 661714 | 01602 | 10 | Solar | 05_14_70L6 | 12/19/2024 | 01/27/2025 | 13 | 10 | 3 | 01/28/2025 | 01/28/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | OXFORD | 207111 | 01540 | 7.6 | Solar | 05_14_8L2 | 02/21/2019 | 03/05/2019 | 7 | 0 | 7 | 03/06/2019 | 03/06/2019 | 15 | 8 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 | 02/21/2019 | 7/22/2020 | Y | EXP | 365 | 01/16/2020 | 02/28/2020 | 43 | 0 | 43 |  |  | 6/18/2020 | Connected |  | N
National Grid | RUTLAND | 177039 | 01543 | 800 | Solar | 05_01_23W3 | 07/27/2016 | 07/27/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/26/2016 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2017 | 07/27/2016 | 3/15/2019 | Y | STD | 581 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 716071 | 02721 | 15.2 | Solar | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2026 | Connected |  | Y
National Grid | MARLBOROUGH | 174555 | 01752 | 3000 | Solar | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2013 |  | 10/31/2012 | N | STD | 275 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENHAM | 174885 | 01984 | 40 | Solar | 05_05_106W43 | 02/16/2013 | 02/16/2013 | 7 | 0 | 7 | 02/28/2013 | 02/28/2013 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2013 |  | 5/31/2013 | N | EXP | 59 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 |  | Withdrawn |  | N
National Grid | CHELMSFORD | 233077 | 01863 | 25 | Solar | 05_05_311W1 | 06/19/2019 | 06/20/2019 | 1 | 1 | 0 | 06/21/2019 | 06/21/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | WESTFORD | 592675 | 01886 | 34.5 | Solar | 05_12_51L3 | 02/26/2024 | 02/27/2024 | 1 | 0 | 1 | 02/28/2024 | 02/28/2024 | 26 | 22 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | BILLERICA | 340624 | 01821 | 9.6 | Solar | 05_14_2L1 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 2/4/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 321224 | 01841 | 10 | Solar | 05_14_57L2 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/27/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 672015 | 01602 | 6.08 | Solar | 05_14_70L6 | 02/13/2025 | 02/20/2025 | 4 | 0 | 4 | 02/21/2025 | 02/21/2025 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | OXFORD | 209338 | 01540 | 11.4 | Solar | 05_14_8L2 | 04/22/2019 | 04/26/2019 | 3 | 0 | 3 | 04/29/2019 | 04/29/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/22/2019 | 7/22/2020 | Y | EXP | 365 | 04/25/2020 | 06/12/2020 | 48 | 0 | 48 |  |  | 7/7/2020 | Connected |  | N
National Grid | RUTLAND | 178253 | 01543 | 7.6 | Solar | 05_01_23W3 | 03/27/2018 | 03/27/2018 | 4 | 0 | 4 | 04/03/2018 | 04/03/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  | 4/2/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 715605 | 02720 | 20 | Solar | 05_01_406L4 | 09/02/2025 | 09/09/2025 | 4 | 2 | 2 | 09/10/2025 | 09/10/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 174642 | 01752 | 21 | Solar | 05_01_55W1 | 12/06/2013 | 12/06/2013 | 8 | 0 | 8 | 12/19/2013 | 12/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2013 |  | 1/31/2014 | N | EXP | 43 |  |  | 0 | 0 | 0 | 1/21/2014 | 1/21/2014 | 1/30/2015 | Connected |  | N
National Grid | BEVERLY | 176154 | 01915 | 56 | Solar | 05_05_106W43 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/03/2015 | 09/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/5/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | CHELMSFORD | 251090 | 01863 | 75 | Natural Gas | 05_05_311W1 | 12/06/2019 | 12/26/2019 | 12 | 7 | 5 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2021 | 12/06/2019 | 6/2/2022 | Y | STD | 323 | 08/21/2021 | 03/21/2022 | 213 | 21 | 192 |  |  | 5/5/2022 | Connected |  | Y
National Grid | WESTFORD | 648934 | 01886 | 4.56 | Solar | 05_12_51L3 | 10/23/2024 | 11/13/2024 | 4 | 1 | 3 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | BILLERICA | 346687 | 01821 | 11.31 | Solar | 05_14_2L1 | 03/12/2021 | 04/22/2021 | 27 | 25 | 2 | 04/23/2021 | 04/23/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2021 |  | 4/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | LAWRENCE | 326885 | 01841 | 10 | Solar | 05_14_57L2 | 11/18/2020 | 11/23/2020 | 2 | 0 | 2 | 11/24/2020 | 11/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | LEICESTER | 712233 | 01524 | 17.92 | Solar | 05_14_70L6 | 08/18/2025 | 08/19/2025 | 1 | 0 | 1 | 08/20/2025 | 08/20/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | AUBURN | 212812 | 01501 | 7.6 | Solar | 05_14_8L2 | 03/23/2019 | 03/25/2019 | 0 | 0 | 0 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2019 |  | 8/30/2019 | N | EXP | 155 |  |  | 0 | 0 | 0 |  |  | 8/16/2019 | Connected |  | N
National Grid | RUTLAND | 184545 | 01543 | 7.6 | Solar | 05_01_23W3 | 05/31/2018 | 05/31/2018 | 3 | 0 | 3 | 06/07/2018 | 06/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 730948 | 02721 | 15.2 | Solar | 05_01_406L4 | 11/03/2025 | 11/07/2025 | 4 | 0 | 4 | 11/10/2025 | 11/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | MARLBOROUGH | 174714 | 01752 | 70 | Solar | 05_01_55W1 | 01/09/2014 | 01/09/2014 | 5 | 0 | 5 | 01/17/2014 | 01/17/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2014 | 01/09/2014 | 8/29/2014 | Y | EXP | 219 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 8/6/2015 | Connected |  | N
National Grid | BEVERLY | 176863 | 01915 | 40.25 | Solar | 05_05_106W43 | 01/21/2016 | 01/21/2016 | 4 | 4 | 0 | 01/27/2016 | 01/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 10/18/2016 | 10/18/2016 | 10/24/2016 | Connected |  | N
National Grid | WESTFORD | 287875 | 01886 | 17.7 | Solar | 05_05_311W1 | 04/15/2020 | 06/03/2020 | 8 | 7 | 1 | 06/04/2020 | 06/04/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N
National Grid | WESTFORD | 657644 | 01886 | 10 | Solar | 05_12_51L3 | 11/29/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/29/2024 | 2/19/2026 | Y | EXP | 365 | 06/14/2025 | 09/02/2025 | 81 | 0 | 81 |  |  | 9/11/2025 | Connected |  | N
National Grid | BILLERICA | 650138 | 01821 | 4.48 | Solar | 05_14_2L1 | 10/28/2024 | 11/12/2024 | 8 | 6 | 2 | 11/13/2024 | 11/13/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 332968 | 01841 | 0 | Solar | 05_14_57L2 | 12/18/2020 | 01/04/2021 | 9 | 8 | 1 | 01/05/2021 | 01/05/2021 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2021 | 12/18/2020 | 1/3/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/23/2021 | Connected |  | N
National Grid | WORCESTER | 174143 | 01602 | 2000 | Solar | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 212730 | 01540 | 7.6 | Solar | 05_14_8L2 | 03/20/2019 | 03/28/2019 | 5 | 0 | 5 | 03/29/2019 | 03/29/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 | 03/20/2019 | 6/17/2020 | Y | EXP | 365 | 01/16/2020 | 02/07/2020 | 22 | 0 | 22 |  |  | 4/17/2020 | Connected |  | N
National Grid | RUTLAND | 186320 | 01543 | 3.8 | Solar | 05_01_23W3 | 06/13/2018 | 06/13/2018 | 28 | 0 | 28 | 07/26/2018 | 07/26/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 648624 | 02720 | 4990 | Other | 05_01_408L1 | 02/20/2025 | 04/30/2025 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2025 | 05/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MARLBOROUGH | 174773 | 01752 | 57.5 | Solar | 05_01_55W1 | 01/17/2013 | 01/17/2013 | 10 | 8 | 2 | 02/04/2013 | 02/04/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 5/1/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 5/2/2013 | 5/2/2013 | 10/4/2013 | Connected |  | N
National Grid | HAMILTON | 401104 | 01982 | 0 | Other | 05_05_106W43 | 01/04/2022 | 01/14/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/18/2022 | 01/27/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 389739 | 01863 | 0 | Other | 05_05_311W1 | 11/10/2021 | 01/05/2022 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 671935 | 01886 | 4.537 | Solar | 05_12_51L3 | 02/13/2025 | 03/19/2025 | 5 | 0 | 5 | 03/20/2025 | 03/20/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | BILLERICA | 664682 | 01821 | 4.18 | Solar | 05_14_2L1 | 01/09/2025 | 01/29/2025 | 5 | 0 | 5 | 01/30/2025 | 01/30/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | METHUEN | 335891 | 01844 | 100 | Solar | 05_14_57L2 | 01/11/2021 | 01/25/2021 | 8 | 0 | 8 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 3/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174142 | 01602 | 2000 | Solar | 05_14_70L8 | 04/17/2012 | 04/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2012 |  | 12/3/2012 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | OXFORD | 225186 | 01540 | 7.6 | Solar | 05_14_8L2 | 05/03/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2019 | 05/03/2019 | 10/23/2021 | Y | EXP | 365 | 12/09/2020 | 01/08/2021 | 30 | 0 | 30 |  |  | 5/27/2021 | Connected |  | N
National Grid | RUTLAND | 198437 | 01543 | 3.8 | Solar | 05_01_23W3 | 10/12/2018 |  | 69 | 25 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 175914 | 02721 | 1500 | Solar | 05_01_408L1 | 03/12/2015 | 03/12/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2015 | 05/12/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 | 07/12/2016 | 10/06/2016 | 61 | 0 | 61 | 10/11/2016 | 03/12/2015 | 10/31/2017 | Y | STD | 385 | 06/22/2017 | 02/28/2018 | 165 | 0 | 165 | 10/18/2017 | 10/18/2017 | 11/29/2017 | Connected |  | N
National Grid | MARLBOROUGH | 174943 | 01752 | 3000 | Solar | 05_01_55W1 | 10/02/2011 | 10/02/2011 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 602713 | 01915 | 7.6 | Solar | 05_05_106W43 | 04/09/2024 | 04/13/2024 | 1 | 0 | 1 | 08/07/2024 | 08/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2024 | 04/09/2024 | 8/21/2025 | Y | EXP | 365 | 09/06/2024 | 09/20/2024 | 15 | 0 | 15 |  |  | 10/4/2024 | Connected |  | N
National Grid | CHELMSFORD | 586186 | 01863 | 150 | Solar | 05_05_311W1 | 02/01/2024 | 03/25/2024 | 36 | 28 | 8 | 03/26/2024 | 03/26/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 704327 | 01886 | 15.2 | Solar | 05_12_51L3 | 07/11/2025 | 07/15/2025 | 2 | 0 | 2 | 07/16/2025 | 07/16/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/18/2025 | Connected |  | N
National Grid | BILLERICA | 686313 | 01821 | 15.04 | Solar | 05_14_2L1 | 05/11/2025 | 07/10/2025 | 39 | 38 | 1 | 07/11/2025 | 07/11/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 | 05/11/2025 | 9/2/2026 | Y | EXP | 365 | 12/04/2025 | 02/13/2026 | 72 | 0 | 72 |  |  | 2/17/2026 | Connected |  | N
National Grid | LAWRENCE | 341508 | 01841 | 9.6 | Solar | 05_14_57L2 | 02/10/2021 | 02/16/2021 | 2 | 0 | 2 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 12/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2022 | Connected |  | N
National Grid | WORCESTER | 174574 | 01602 | 999 | Solar | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | STD | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 242394 | 01518 | 3.8 | Solar | 05_14_8L2 | 08/01/2019 | 08/01/2019 | 0 | 0 | 0 | 08/02/2019 | 08/02/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2020 | Connected |  | N
National Grid | RUTLAND | 198669 | 01543 | 5 | Solar | 05_01_23W3 | 10/16/2018 | 02/20/2019 | 87 | 83 | 4 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 193813 | 02721 | 86.4 | Solar | 05_01_408L1 | 08/17/2018 | 08/23/2018 | 3 | 0 | 3 | 08/24/2018 | 08/24/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 174942 | 01752 | 286 | Solar | 05_01_55W1 | 10/05/2011 | 10/05/2011 | 485 | 274 | 211 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 641015 | 01915 | 10 | Solar | 05_05_106W43 | 09/25/2024 | 10/25/2024 | 10 | 9 | 1 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 1/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2025 | Connected |  | N
National Grid | CHELMSFORD | 656819 | 01863 | 10 | Solar | 05_05_311W1 | 11/25/2024 | 02/27/2025 | 40 | 37 | 3 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 710433 | 01886 | 18.34 | Solar | 05_12_51L3 | 08/07/2025 | 08/13/2025 | 4 | 0 | 4 | 08/14/2025 | 08/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | BILLERICA | 709518 | 01821 | 11.4 | Solar | 05_14_2L2 | 08/05/2025 | 09/24/2025 | 34 | 24 | 10 | 09/25/2025 | 09/25/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 449761 | 01841 | 7.6 | Solar | 05_14_57L2 | 08/09/2022 | 08/10/2022 | 1 | 0 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  | 9/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | WORCESTER | 174565 | 01602 | 4999 | Solar | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2012 | 09/21/2012 | 0 | 0 | 0 | 12/12/2012 | 08/05/2011 | 12/1/2014 | Y | STD | 719 | 05/19/2014 | 11/12/2014 | 121 | 0 | 121 | 7/31/2014 | 7/31/2014 | 8/13/2014 | Connected |  | N
National Grid | STURBRIDGE | 278952 | 01566 | 7.6 | Solar | 05_14_8L2 | 02/27/2020 |  | 25 | 25 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 206478 | 01543 | 250 | Solar | 05_01_23W3 | 03/12/2019 | 03/14/2019 | 1 | 1 | 0 |  |  | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2020 | 03/12/2019 | 3/23/2023 | Y | STD | 823 | 10/05/2021 | 08/19/2022 | 319 | 4 | 315 |  |  | 3/9/2023 | Connected |  | N
National Grid | FALL RIVER | 191478 | 02720 | 15.2 | Solar | 05_01_408L1 | 07/23/2018 | 08/29/2018 | 26 | 0 | 26 | 08/30/2018 | 08/30/2018 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175139 | 01752 | 300 | Bio Gas | 05_01_55W1 | 04/23/2013 | 04/23/2013 | 6 | 0 | 6 | 05/02/2013 | 05/02/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2013 |  | 8/30/2013 | N | EXP | 89 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 4/16/2014 | Connected |  | N
National Grid | HAMILTON | 729508 | 01982 | 240 | Solar | 05_05_106W44 | 10/31/2025 | 12/03/2025 | 21 | 12 | 9 | 12/04/2025 | 12/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | CHELMSFORD | 661545 | 01863 | 10 | Solar | 05_05_311W1 | 12/30/2024 | 01/17/2025 | 5 | 0 | 5 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/30/2024 | 6/5/2026 | Y | EXP | 365 | 08/21/2025 | 01/27/2026 | 160 | 0 | 160 |  |  | 12/9/2025 | Connected |  | N
National Grid | WESTFORD | 535949 | 01886 | 150 | Solar | 05_12_51T1 | 06/22/2023 | 12/07/2023 | 115 | 106 | 9 |  |  | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | Y
National Grid | BILLERICA | 740214 | 01821 | 100 | Solar | 05_14_2L2 | 02/13/2026 |  | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 373288 | 01841 | 15.2 | Solar | 05_14_57L2 | 09/08/2021 | 09/22/2021 | 11 | 10 | 1 | 09/23/2021 | 09/23/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2021 |  | 2/1/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 174575 | 01602 | 2000 | Solar | 05_14_70L8 | 09/01/2011 | 09/01/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 290049 | 01566 | 8.19 | Solar | 05_14_8L2 | 06/09/2020 | 06/15/2020 | 3 | 0 | 3 | 06/16/2020 | 06/16/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/09/2020 | 2/25/2022 | Y | EXP | 365 | 04/14/2021 | 09/22/2021 | 161 | 3 | 158 |  |  | 11/17/2021 | Connected |  | Y
National Grid | RUTLAND | 230757 | 01543 | 7.6 | Solar | 05_01_23W3 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2019 |  | 10/15/2019 | N | EXP | 69 |  |  | 0 | 0 | 0 |  |  | 9/10/2019 | Connected |  | N
National Grid | FALL RIVER | 503087 | 02720 | 22.62 | Solar | 05_01_408L1 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2023 |  | 4/3/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175272 | 01752 | 997.6 | Solar | 05_01_55W1 | 06/23/2014 | 06/23/2014 | 7 | 5 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2014 | 08/06/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 06/23/2014 | 6/1/2016 | Y | STD | 469 | 11/29/2016 | 01/16/2017 | 32 | 0 | 32 | 1/13/2017 | 1/13/2017 | 1/13/2017 | Connected |  | N
National Grid | BEVERLY | 738197 | 01915 | 250 | Solar | 05_05_106W44 | 12/24/2025 | 01/13/2026 | 12 | 3 | 9 | 01/14/2026 | 01/14/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 662117 | 01851 | 5.76 | Solar | 05_05_311W1 | 12/21/2024 | 02/12/2025 | 2 | 0 | 2 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | WESTFORD | 703493 | 01886 | 11.4 | Solar | 05_12_51T1 | 07/08/2025 | 07/11/2025 | 3 | 0 | 3 | 07/14/2025 | 07/14/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BILLERICA | 753539 | 01821 | 17.45 | Solar | 05_14_2L2 | 03/03/2026 |  | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 382038 | 01841 | 19.14 | Solar | 05_14_57L2 | 09/14/2021 | 12/16/2021 | 3 | 0 | 3 | 09/20/2021 | 09/20/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  | 6/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 175159 | 01602 | 2000 | Solar | 05_14_70L8 | 08/05/2011 | 08/05/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2012 | 08/11/2014 | 444 | 0 | 444 | 12/12/2012 | 08/05/2011 | 12/31/2012 | Y | STD | 19 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 291189 | 01518 | 7.6 | Solar | 05_14_8L2 | 05/08/2020 | 05/11/2020 | 0 | 0 | 0 | 05/12/2020 | 05/12/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 |  | 5/11/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 424314 | 01543 | 3.8 | Solar | 05_01_23W3 | 04/15/2022 | 05/27/2022 | 1 | 0 | 1 | 05/31/2022 | 05/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2022 | 04/15/2022 | 9/9/2023 | Y | EXP | 365 | 08/25/2022 | 09/07/2022 | 14 | 0 | 14 |  |  | 9/12/2022 | Connected |  | N
National Grid | FALL RIVER | 516424 | 02723 | 7.6 | Solar | 05_01_408L1 | 04/04/2023 | 04/10/2023 | 5 | 4 | 1 | 04/11/2023 | 04/11/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2023 |  | 6/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175296 | 01752 | 19.25 | Solar | 05_01_55W1 | 01/14/2015 | 01/14/2015 | 4 | 2 | 2 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 6/10/2015 | Connected |  | N
National Grid | BEVERLY | 739526 | 01915 | 23.732 | Solar | 05_05_106W44 | 12/11/2025 | 12/16/2025 | 2 | 0 | 2 | 12/17/2025 | 12/17/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | CHELMSFORD | 667325 | 01863 | 14.625 | Solar | 05_05_311W2 | 01/29/2025 | 02/05/2025 | 1 | 0 | 1 | 12/11/2025 | 12/11/2025 | 58 | 47 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTFORD | 710223 | 01886 | 240 | Solar | 05_12_51T1 | 08/26/2025 | 10/13/2025 | 31 | 27 | 4 |  |  | 89 | 75 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BILLERICA | 752200 | 01821 | 16.34 | Solar | 05_14_2L2 | 02/19/2026 | 02/27/2026 | 5 | 2 | 3 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LAWRENCE | 424028 | 01841 | 15.2 | Solar | 05_14_57L2 | 04/14/2022 | 04/15/2022 | 1 | 0 | 1 | 04/19/2022 | 04/19/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/14/2022 | 12/7/2024 | Y | EXP | 365 | 06/09/2023 | 12/05/2023 | 180 | 0 | 180 |  |  | 2/27/2025 | Connected |  | N
National Grid | WORCESTER | 175562 | 01602 | 12 | Solar | 05_14_70L8 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 |  | 10/31/2014 | N | EXP | 59 |  |  | 0 | 0 | 0 | 2/17/2015 | 2/17/2015 | 5/19/2015 | Connected |  | N
National Grid | STURBRIDGE | 296373 | 01566 | 6.93 | Solar | 05_14_8L2 | 06/30/2020 | 07/14/2020 | 10 | 7 | 3 | 07/15/2020 | 07/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  | 6/29/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 527877 | 01543 | 10 | Solar | 05_01_23W3 | 05/31/2023 | 06/05/2023 | 4 | 3 | 1 | 06/06/2023 | 06/06/2023 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 | 05/31/2023 | 8/3/2024 | Y | EXP | 365 | 08/10/2023 | 08/28/2023 | 19 | 0 | 19 |  |  | 10/6/2023 | Connected |  | N
National Grid | FALL RIVER | 567984 | 02723 | 4956 | Solar | 05_01_408L1 | 04/15/2024 |  | 170 | 160 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 175294 | 01752 | 6 | Solar | 05_01_55W1 | 01/13/2015 | 01/13/2015 | 28 | 27 | 1 | 02/25/2015 | 02/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 |  | 5/31/2015 | N | EXP | 95 |  |  | 0 | 0 | 0 | 4/28/2015 | 4/28/2015 | 11/12/2015 | Connected |  | N
National Grid | GLOUCESTER | 174596 | 01930 | 26 | Solar | 05_05_106W44 | 10/18/2011 | 10/18/2011 | 2 | 0 | 2 | 11/15/2011 | 11/15/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2011 |  | 4/13/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 4/13/2012 | Connected |  | N
National Grid | LOWELL | 742966 | 01851 | 7.6 | Solar | 05_05_311W2 | 01/02/2026 | 01/07/2026 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2026 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 720734 | 01886 | 12.564 | Solar | 05_12_51T1 | 09/22/2025 | 10/24/2025 | 13 | 12 | 1 | 12/02/2025 | 12/02/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 178453 | 01821 | 7.6 | Solar | 05_14_2L2 | 11/29/2017 | 11/29/2017 | 38 | 36 | 2 | 01/29/2018 | 01/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2018 | 11/29/2017 | 9/19/2019 | Y | EXP | 597 | 06/06/2018 | 06/20/2018 | 14 | 0 | 14 |  |  | 9/5/2019 | Connected |  | N
National Grid | LAWRENCE | 431905 | 01841 | 7.6 | Solar | 05_14_57L2 | 07/08/2022 | 07/19/2022 | 8 | 7 | 1 | 07/20/2022 | 07/20/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 176311 | 01602 | 5 | Solar | 05_14_70L8 | 02/25/2015 | 02/25/2015 | 8 | 5 | 3 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 |  | 7/31/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 6/11/2015 | 6/11/2015 | 10/2/2015 | Connected |  | N
National Grid | STURBRIDGE | 306308 | 01566 | 7.6 | Solar | 05_14_8L2 | 08/28/2020 | 09/02/2020 | 2 | 0 | 2 | 09/03/2020 | 09/03/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RUTLAND | 575782 | 01543 | 7.83 | Solar | 05_01_23W3 | 12/27/2023 | 12/28/2023 | 1 | 0 | 1 | 12/29/2023 | 12/29/2023 | 22 | 0 | 22 | 02/27/2024 | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 03/27/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 3/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 623841 | 02723 | 10 | Solar | 05_01_408L1 | 07/10/2024 | 07/24/2024 | 5 | 0 | 5 | 07/25/2024 | 07/25/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 07/10/2024 | 12/3/2025 | Y | EXP | 365 | 04/15/2025 | 10/27/2025 | 196 | 0 | 196 |  |  | 10/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175339 | 01752 | 222 | Solar | 05_01_55W1 | 01/20/2015 | 01/20/2015 | 5 | 1 | 4 | 01/28/2015 | 01/28/2015 | 581 | 0 | 581 | 03/27/2015 | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 04/28/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 5/5/2015 | 01/20/2015 | 12/31/2016 | Y | EXP | 66 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 175252 | 01930 | 20.64 | Solar | 05_05_106W44 | 11/05/2014 | 11/05/2014 | 6 | 3 | 3 | 11/17/2014 | 11/17/2014 | 710 | 0 | 710 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2014 |  | 12/1/2017 | N | EXP | 117 |  |  | 0 | 0 | 0 | 1/28/2015 | 1/28/2015 |  | Withdrawn |  | Y
National Grid | CHELMSFORD | 745339 | 01863 | 11.5 | Solar | 05_05_311W2 | 01/14/2026 | 01/16/2026 | 2 | 0 | 2 | 01/28/2026 | 01/28/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTFORD | 737553 | 01886 | 5.76 | Solar | 05_12_51T1 | 12/02/2025 | 12/03/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/25/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BILLERICA | 178471 | 01821 | 7.6 | Solar | 05_14_2L2 | 03/06/2018 | 03/06/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 3/12/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 433175 | 01844 | 10 | Solar | 05_14_57L2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 | 06/17/2022 | 3/19/2024 | Y | EXP | 365 | 03/08/2023 | 03/20/2023 | 13 | 0 | 13 |  |  | 3/27/2023 | Connected |  | Y
National Grid | WORCESTER | 176509 | 01602 | 5.5 | Solar | 05_14_70L8 | 03/28/2016 | 03/28/2016 | 3 | 3 | 0 | 04/01/2016 | 04/01/2016 | 196 | 0 | 196 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2016 |  | 4/3/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 322575 | 01518 | 10 | Solar | 05_14_8L2 | 12/22/2020 | 12/30/2020 | 4 | 0 | 4 | 12/31/2020 | 12/31/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/22/2020 |  | Y | EXP | 365 | 04/14/2021 | 04/26/2021 | 12 | 0 | 12 |  |  | 5/29/2021 | Connected |  | N
National Grid | RUTLAND | 599599 | 01543 | 7.6 | Solar | 05_01_23W3 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 632114 | 02723 | 7.6 | Solar | 05_01_408L1 | 08/21/2024 | 08/27/2024 | 4 | 0 | 4 | 08/28/2024 | 08/28/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 | 08/21/2024 | 9/20/2025 | Y | EXP | 365 | 11/14/2024 | 11/13/2024 | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | MARLBOROUGH | 175831 | 01752 | 135 | Solar | 05_05_321W5 | 09/21/2015 | 09/21/2015 | 2 | 2 | 0 | 09/25/2015 | 09/25/2015 | 623 | 0 | 623 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2015 |  | 6/29/2018 | N | EXP | 995 |  |  | 0 | 0 | 0 | 2/12/2016 | 2/12/2016 | 8/29/2018 | Connected |  | N
National Grid | BEVERLY | 306648 | 01915 | 3.8 | Solar | 05_05_106W44 | 08/13/2020 | 08/17/2020 | 1 | 0 | 1 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 |  | 5/3/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 176966 | 01851 | 6 | Solar | 05_05_311W2 | 10/03/2016 | 10/03/2016 | 0 | 0 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 | 10/03/2016 | 5/12/2017 | Y | EXP | 213 | 11/22/2016 | 11/23/2016 | 1 | 0 | 1 | 5/15/2017 | 5/15/2017 | 5/15/2017 | Connected |  | N
National Grid | WESTFORD | 736911 | 01886 |  | Battery Add-On | 05_12_51T1 | 11/28/2025 | 12/01/2025 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BILLERICA | 184905 | 01821 | 7.6 | Solar | 05_14_2L2 | 06/11/2018 | 06/11/2018 | 1 | 0 | 1 | 06/13/2018 | 06/13/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2018 |  | 6/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 441483 | 01841 | 7.6 | Solar | 05_14_57L2 | 07/19/2022 | 07/20/2022 | 1 | 0 | 1 | 07/21/2022 | 07/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 178536 | 01602 | 15.2 | Solar | 05_14_70L8 | 12/07/2017 | 12/07/2017 | 15 | 0 | 15 | 01/02/2018 | 01/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2018 |  | 3/22/2019 | N | EXP | 443 |  |  | 0 | 0 | 0 |  |  | 12/19/2018 | Connected |  | N
National Grid | STURBRIDGE | 349178 | 01518 | 9.8 | Solar | 05_14_8L2 | 04/16/2021 | 04/26/2021 | 4 | 0 | 4 | 04/27/2021 | 04/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 |  | 6/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RUTLAND | 618070 | 01543 | 6 | Solar | 05_01_23W3 | 06/17/2024 | 07/09/2024 | 8 | 5 | 3 | 07/10/2024 | 07/10/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 651529 | 02723 | 5.76 | Solar | 05_01_408L1 | 11/12/2024 | 12/13/2024 | 7 | 4 | 3 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177841 | 01752 | 4980 | Solar | 05_05_321W5 | 10/17/2017 | 10/17/2017 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 11/15/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 | 10/17/2017 | 4/21/2021 | Y | STD | 336 | 11/06/2020 | 02/25/2021 | 111 | 0 | 111 | 3/17/2021 | 3/16/2021 | 4/21/2021 | Connected |  | N
National Grid | GLOUCESTER | 605320 | 01930 | 5.76 | Solar | 05_05_106W44 | 04/20/2024 | 04/25/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/20/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | CHELMSFORD | 177011 | 01863 | 10 | Solar | 05_05_311W2 | 10/14/2016 | 10/14/2016 | 1 | 1 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2016 | 10/14/2016 | 10/23/2017 | Y | EXP | 364 | 01/20/2017 | 03/02/2017 | 28 | 0 | 28 | 3/29/2017 | 3/29/2017 | 3/31/2017 | Connected |  | N
National Grid | WESTFORD | 750023 | 01886 | 10 | Solar | 05_12_51T1 | 02/09/2026 | 02/11/2026 | 2 | 0 | 2 | 02/12/2026 | 02/12/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TEWKSBURY | 191228 | 01876 | 3 | Solar | 05_14_2L2 | 07/19/2018 | 09/13/2018 | 31 | 25 | 6 | 09/14/2018 | 09/14/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2018 | 07/19/2018 | 10/8/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2019 | Connected |  | N
National Grid | LAWRENCE | 458118 | 01841 | 19 | Solar | 05_14_57L2 | 09/12/2022 | 09/12/2022 | 0 | 0 | 0 | 09/13/2022 | 09/13/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  | 10/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | WORCESTER | 192658 | 01602 | 10 | Solar | 05_14_70L8 | 08/28/2018 | 10/08/2018 | 17 | 17 | 0 | 10/09/2018 | 10/09/2018 | 41 | 27 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 413386 | 01566 | 6 | Solar | 05_14_8L2 | 03/08/2022 | 03/09/2022 | 1 | 0 | 1 | 03/10/2022 | 03/10/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 03/08/2022 | 7/12/2024 | Y | EXP | 365 | 05/09/2023 | 06/08/2023 | 31 | 0 | 31 |  |  | 8/25/2023 | Connected |  | N
National Grid | UXBRIDGE | 631649 | 01569 | 5.12 | Solar | 05_01_23W3 | 08/09/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/09/2024 | 9/25/2025 | Y | EXP | 365 | 01/07/2025 | 05/21/2025 | 135 | 0 | 135 |  |  | 6/4/2025 | Connected |  | N
National Grid | FALL RIVER | 692690 | 02723 | 15.2 | Solar | 05_01_408L1 | 05/19/2025 | 05/23/2025 | 4 | 0 | 4 | 05/27/2025 | 05/27/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | MARLBOROUGH | 184698 | 01752 | 594 | Solar | 05_05_321W5 | 05/31/2018 | 05/31/2018 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/01/2018 | 09/27/2018 | 45 | 22 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 649038 | 01930 | 5.76 | Solar | 05_05_106W44 | 11/04/2024 | 11/20/2024 | 5 | 0 | 5 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 | 11/04/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | LOWELL | 177457 | 01851 | 3.8 | Solar | 05_05_311W2 | 12/07/2016 | 12/07/2016 | 1 | 1 | 0 | 12/12/2016 | 12/12/2016 | 323 | 0 | 323 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2016 | 12/07/2016 | 12/30/2018 | Y | EXP | 745 | 12/27/2017 | 10/26/2018 | 303 | 0 | 303 |  |  | 10/26/2018 | Connected |  | N
National Grid | WESTFORD | 162552 | 01886 | 10 | Solar | 05_12_51T1 | 10/12/2017 | 10/12/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 197063 | 01876 | 7.68 | Solar | 05_14_2L2 | 10/03/2018 | 10/11/2018 | 3 | 3 | 0 | 10/12/2018 | 10/12/2018 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 10/03/2018 | 5/29/2019 | Y | EXP | 225 | 02/01/2019 | 01/31/2019 | 0 | 0 | 0 |  |  | 4/16/2019 | Connected |  | N
National Grid | LAWRENCE | 461886 | 01841 | 7.6 | Solar | 05_14_57L2 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 | 11/29/2022 | 6/15/2024 | Y | EXP | 365 | 06/09/2023 | 06/12/2023 | 4 | 0 | 4 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 259369 | 01602 | 3.8 | Solar | 05_14_70L8 | 10/22/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2020 | Connected |  | N
National Grid | STURBRIDGE | 428539 | 01518 | 7.6 | Solar | 05_14_8L2 | 05/19/2022 | 05/24/2022 | 4 | 3 | 1 | 05/25/2022 | 05/25/2022 | 122 | 105 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2022 | 05/19/2022 | 4/9/2024 | Y | EXP | 365 | 03/15/2023 | 04/08/2023 | 25 | 0 | 25 |  |  | 6/12/2023 | Connected |  | N
National Grid | NORTHBRIDGE | 634790 | 01534 | 10 | Solar | 05_01_23W3 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/22/2024 | 9/24/2025 | Y | EXP | 365 | 10/24/2024 | 03/21/2025 | 149 | 0 | 149 |  |  | 4/12/2025 | Connected |  | N
National Grid | FALL RIVER | 694502 | 02723 | 17.6 | Solar | 05_01_408L1 | 05/28/2025 | 06/09/2025 | 2 | 0 | 2 | 08/18/2025 | 08/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 293617 | 01752 | 0 | Other | 05_05_321W5 | 01/15/2021 | 02/25/2021 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/26/2021 | 05/27/2021 | 63 | 45 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 663614 | 01915 | 4.8 | Solar | 05_05_106W44 | 01/03/2025 | 01/28/2025 | 2 | 0 | 2 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | LOWELL | 177786 | 01851 | 3.8 | Solar | 05_05_311W2 | 06/01/2017 | 06/01/2017 | 7 | 5 | 2 | 06/13/2017 | 06/13/2017 | 198 | 0 | 198 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2017 | 06/01/2017 | 12/28/2018 | Y | EXP | 563 |  |  | 0 | 0 | 0 |  |  | 10/26/2018 | Connected |  | N
National Grid | WESTFORD | 174679 | 01886 | 45 | Solar | 05_12_51T1 | 01/06/2014 | 01/06/2014 | 5 | 0 | 5 | 01/14/2014 | 01/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2014 |  | 3/31/2014 | N | EXP | 69 |  |  | 0 | 0 | 0 | 2/21/2014 | 2/21/2014 | 4/25/2014 | Connected |  | N
National Grid | TEWKSBURY | 198842 | 01876 | 3.8 | Solar | 05_14_2L2 | 12/06/2018 | 12/19/2018 | 8 | 0 | 8 | 12/20/2018 | 12/20/2018 | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 479921 | 01841 | 7.6 | Solar | 05_14_57L2 | 01/04/2023 | 01/09/2023 | 3 | 0 | 3 | 01/10/2023 | 01/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 300909 | 01602 | 0 | Solar | 05_14_70L8 | 07/14/2020 | 08/06/2020 | 17 | 17 | 0 | 08/07/2020 | 08/07/2020 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 8/2/2023 | N | EXP | 75 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STURBRIDGE | 459549 | 01518 | 6 | Solar | 05_14_8L2 | 11/18/2022 | 11/27/2022 | 5 | 0 | 5 | 11/28/2022 | 11/28/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2022 | 11/18/2022 | 5/16/2024 | Y | EXP | 365 | 09/12/2023 | 10/04/2023 | 23 | 0 | 23 |  |  | 10/10/2023 | Connected |  | N
National Grid | NORTHBRIDGE | 667463 | 01534 | 0 | Other | 05_01_23W3 | 02/25/2025 | 03/28/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2025 | 04/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 178274 | 02723 | 4998 | Solar | 05_01_408L2 | 02/21/2018 | 02/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2018 | 05/24/2018 | 67 | 49 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2018 | 02/21/2018 | 12/31/2026 | Y | STD | 798 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MARLBOROUGH | 506986 | 01752 | 13.3 | Solar | 05_05_321W5 | 03/16/2023 | 03/21/2023 | 3 | 0 | 3 | 03/22/2023 | 03/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ESSEX | 689724 | 01929 | 200 | Solar | 05_05_106W44 | 05/08/2025 | 08/26/2025 | 74 | 65 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 178441 | 01851 | 5 | Solar | 05_05_311W2 | 04/02/2018 | 04/02/2018 | 5 | 0 | 5 | 04/10/2018 | 04/10/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 4/8/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 5/29/2019 | Connected |  | N
National Grid | WESTFORD | 175028 | 01886 | 800 | Solar | 05_12_51T1 | 03/20/2013 | 03/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2013 | 05/15/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2013 |  | 6/30/2014 | N | STD | 411 |  |  | 0 | 0 | 0 | 12/27/2013 | 12/27/2013 | 12/30/2013 | Connected |  | N
National Grid | BILLERICA | 250967 | 01821 | 7.6 | Solar | 05_14_2L2 | 08/27/2019 | 08/28/2019 | 1 | 1 | 0 | 08/29/2019 | 08/29/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/27/2019 | 8/28/2020 | Y | EXP | 233 | 01/09/2020 | 03/12/2020 | 62 | 0 | 62 |  |  | 3/24/2020 | Connected |  | N
National Grid | LAWRENCE | 540656 | 01841 | 13.92 | Solar | 05_14_57L2 | 07/24/2023 | 07/27/2023 | 4 | 3 | 1 | 07/28/2023 | 07/28/2023 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 12/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | WORCESTER | 362871 | 01602 | 7.83 | Solar | 05_14_70L8 | 07/09/2021 | 07/13/2021 | 2 | 0 | 2 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 476315 | 01566 | 0 | Solar | 05_14_8L2 | 06/08/2023 | 08/15/2023 | 46 | 45 | 1 | 08/16/2023 | 08/16/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 |  | 9/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBRIDGE | 686697 | 01534 | 7.6 | Solar | 05_01_23W3 | 04/23/2025 |  | 88 | 84 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 578928 | 02723 | 996 | Solar | 05_01_408L2 | 02/29/2024 | 06/07/2024 | 69 | 60 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/10/2024 | 06/18/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MARLBOROUGH | 607105 | 01752 | 10 | Solar | 05_05_321W5 | 04/26/2024 | 06/10/2024 | 18 | 15 | 3 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/17/2024 | Connected |  | N
National Grid | BEVERLY | 691599 | 01915 | 75 | Solar | 05_05_106W45 | 05/20/2025 | 09/25/2025 | 88 | 79 | 9 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | CHELMSFORD | 178533 | 01863 | 110 | Solar | 05_05_311W2 | 12/05/2017 | 12/05/2017 | 26 | 9 | 17 | 01/16/2018 | 01/16/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 |  | 12/11/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  | 12/21/2018 | Connected |  | N
National Grid | WESTFORD | 175161 | 01886 | 75 | Solar | 05_12_51T1 | 07/21/2011 | 07/21/2011 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 324108 | 01876 | 10 | Solar | 05_14_2L2 | 11/09/2020 | 12/07/2020 | 17 | 14 | 3 | 12/08/2020 | 12/08/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 1/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2021 | Connected |  | N
National Grid | LAWRENCE | 570545 | 01841 |  | Battery Add-On | 05_14_57L2 | 11/10/2023 | 11/30/2023 | 14 | 12 | 2 | 12/01/2023 | 12/01/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 11/10/2023 | 2/21/2025 | Y | EXP | 365 | 04/23/2024 | 06/04/2024 | 43 | 0 | 43 |  |  | 6/7/2024 | Connected |  | N
National Grid | LEICESTER | 382224 | 01524 | 15.2 | Solar | 05_14_70L8 | 09/15/2021 | 10/14/2021 | 21 | 19 | 2 | 10/15/2021 | 10/15/2021 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 | 09/15/2021 | 5/2/2023 | Y | EXP | 365 | 04/06/2022 | 05/02/2022 | 27 | 0 | 27 |  |  | 5/20/2022 | Connected |  | N
National Grid | BROOKFIELD | 533125 | 01506 | 10 | Solar | 05_14_8L2 | 06/16/2023 | 06/21/2023 | 2 | 0 | 2 | 06/22/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 | 06/16/2023 | 8/4/2024 | Y | EXP | 365 | 12/06/2023 | 12/26/2023 | 21 | 3 | 18 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 735526 | 01569 | 3.8 | Solar | 05_01_23W4 | 11/21/2025 | 11/24/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 706760 | 02723 | 240 | Solar | 05_01_408L2 | 08/21/2025 | 09/10/2025 | 13 | 8 | 5 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MARLBOROUGH | 612016 | 01752 | 10 | Solar | 05_05_321W5 | 05/17/2024 | 05/23/2024 | 1 | 0 | 1 | 05/24/2024 | 05/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/17/2024 | 7/30/2025 | Y | EXP | 365 | 09/26/2024 | 10/15/2024 | 20 | 0 | 20 |  |  | 10/22/2024 | Connected |  | N
National Grid | BEVERLY | 175777 | 01915 | 85 | Solar | 05_05_106W45 | 08/20/2014 | 08/20/2014 | 7 | 3 | 4 | 09/02/2014 | 09/02/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2014 |  | 12/31/2014 | N | EXP | 112 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 | 12/4/2014 | Connected |  | N
National Grid | LOWELL | 193822 | 01851 | 15.2 | Solar | 05_05_311W2 | 08/17/2018 |  | 82 | 26 | 56 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175487 | 01886 | 495 | Solar | 05_12_51T1 | 07/22/2014 | 07/22/2014 | 7 | 7 | 0 | 08/04/2014 | 08/04/2014 | 554 | 2 | 552 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2014 |  | 1/20/2016 | N | EXP | 51 |  |  | 0 | 0 | 0 | 9/15/2014 | 9/15/2014 |  | Withdrawn |  | Y
National Grid | TEWKSBURY | 394090 | 01876 | 6 | Solar | 05_14_2L2 | 11/29/2021 | 01/07/2022 | 11 | 10 | 1 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 588461 | 01841 | 23 | Solar | 05_14_57L2 | 02/07/2024 | 02/14/2024 | 6 | 4 | 2 | 02/15/2024 | 02/15/2024 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2024 | Connected |  | N
National Grid | WORCESTER | 526597 | 01602 | 15.2 | Solar | 05_14_70L8 | 05/19/2023 | 05/26/2023 | 5 | 5 | 0 | 05/30/2023 | 05/30/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2023 | Connected |  | N
National Grid | WEST BROOKFIELD | 537941 | 01585 | 8.7 | Solar | 05_14_8L2 | 12/04/2023 |  | 42 | 30 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 737971 | 01569 | 3.8 | Solar | 05_01_23W4 | 12/03/2025 | 12/05/2025 | 1 | 0 | 1 | 01/08/2026 | 01/08/2026 | 18 | 5 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/12/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | FALL RIVER | 738783 | 02720 | 7.6 | Solar | 05_01_408L2 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | MARLBOROUGH | 613999 | 01752 | 10 | Solar | 05_05_321W5 | 05/29/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 74 | 25 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GLOUCESTER | 197438 | 01930 | 1400 | Natural Gas | 05_05_106W45 | 09/20/2019 | 11/07/2019 | 33 | 28 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2019 | 12/09/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 191496 | 01851 | 10 | Solar | 05_05_311W2 | 08/01/2018 | 08/21/2018 | 9 | 4 | 5 | 08/22/2018 | 08/22/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 175656 | 01886 | 17.6 | Solar | 05_12_51T1 | 05/13/2014 | 05/13/2014 | 6 | 0 | 6 | 05/22/2014 | 05/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2014 |  | 9/30/2014 | N | EXP | 99 |  |  | 0 | 0 | 0 | 7/22/2014 | 7/22/2014 | 9/2/2014 | Connected |  | N
National Grid | TEWKSBURY | 488662 | 01876 | 22.272 | Solar | 05_14_2L2 | 12/29/2022 | 04/06/2023 | 68 | 59 | 9 | 04/07/2023 | 04/07/2023 | 150 | 133 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 604077 | 01841 | 12.35 | Solar | 05_14_57L2 | 04/18/2024 | 04/29/2024 | 2 | 1 | 1 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 |  | 6/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2024 | Connected |  | N
National Grid | WORCESTER | 529445 | 01602 | 6 | Solar | 05_14_70L8 | 09/06/2023 | 06/06/2023 | 3 | 2 | 1 | 09/12/2023 | 09/12/2023 | 116 | 99 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2024 | Connected |  | N
National Grid | STURBRIDGE | 555249 | 01518 | 5.76 | Solar | 05_14_8L2 | 09/27/2023 | 11/15/2023 | 34 | 30 | 4 | 11/16/2023 | 11/16/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 380094 | 01525 | 7.6 | Solar | 05_01_23W4 | 09/05/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 | 09/05/2021 | 2/15/2023 | Y | EXP | 365 | 01/19/2022 | 02/14/2022 | 27 | 0 | 27 |  |  | 5/27/2022 | Connected |  | N
National Grid | FALL RIVER | 742596 | 02720 | 20 | Solar | 05_01_408L2 | 12/29/2025 | 01/15/2026 | 2 | 0 | 2 | 01/16/2026 | 01/16/2026 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 658795 | 01752 | 7.6 | Solar | 05_05_321W5 | 12/05/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | MANCHESTER | 649212 | 01944 | 3.8 | Solar | 05_05_106W45 | 10/23/2024 | 12/02/2024 | 20 | 17 | 3 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 10/23/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | LOWELL | 255015 | 01851 | 7.6 | Solar | 05_05_311W2 | 09/18/2019 | 10/03/2019 | 0 | 0 | 0 | 10/04/2019 | 10/04/2019 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 |  | 9/18/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2020 | Connected |  | N
National Grid | WESTFORD | 175911 | 01886 | 20 | Solar | 05_12_51T1 | 03/11/2015 | 03/11/2015 | 11 | 8 | 3 | 03/30/2015 | 03/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2015 |  | 7/31/2015 | N | EXP | 122 |  |  | 0 | 0 | 0 | 4/27/2015 | 4/27/2015 | 7/10/2015 | Connected |  | N
National Grid | BILLERICA | 561313 | 01821 | 7.25 | Solar | 05_14_2L2 | 01/03/2024 | 02/20/2024 | 32 | 25 | 7 | 02/21/2024 | 02/21/2024 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 609526 | 01841 | 11.5 | Solar | 05_14_57L2 | 05/08/2024 | 06/07/2024 | 3 | 0 | 3 | 06/10/2024 | 06/10/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 |  | 7/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | WORCESTER | 569114 | 01602 | 0 | Solar | 05_14_70L8 | 11/06/2023 | 11/30/2023 | 17 | 15 | 2 | 12/01/2023 | 12/01/2023 | 54 | 31 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2024 | Connected |  | N
National Grid | STURBRIDGE | 555821 | 01518 | 6 | Solar | 05_14_8L2 | 09/19/2023 | 09/22/2023 | 4 | 3 | 1 | 09/25/2023 | 09/25/2023 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 |  | 12/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2023 | Connected |  | N
National Grid | UXBRIDGE | 494547 | 01525 | 18.432 | Solar | 05_01_23W4 | 01/24/2023 | 05/25/2023 | 85 | 81 | 4 |  |  | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174315 | 02720 | 25 | Solar | 05_01_408L2 | 01/17/2012 | 01/17/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2012 | 01/17/2012 | 3/30/2012 | Y | EXP | 28 | 04/26/2012 | 07/27/2012 | 63 | 0 | 63 | 8/3/2012 | 8/3/2012 | 8/10/2012 | Connected |  | N
National Grid | MARLBOROUGH | 193531 | 01752 | 0 | Solar | 05_05_321W6 | 08/15/2018 | 09/14/2018 | 7 | 0 | 7 | 10/02/2018 | 10/02/2018 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2018 | 08/15/2018 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Terminated |  | N
National Grid | GLOUCESTER | 672503 | 01930 | 5.76 | Solar | 05_05_106W45 | 02/18/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/18/2025 | 5/1/2026 | Y | EXP | 365 | 04/29/2025 | 06/03/2025 | 36 | 0 | 36 |  |  | 10/10/2025 | Connected |  | N
National Grid | CHELMSFORD | 268191 | 01863 | 7.6 | Solar | 05_05_311W2 | 12/09/2019 | 12/15/2019 | 4 | 0 | 4 | 12/16/2019 | 12/16/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2020 |  | 2/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176156 | 01886 | 21.4 | Solar | 05_12_51T1 | 02/03/2015 | 02/03/2015 | 6 | 3 | 3 | 02/12/2015 | 02/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2015 | 02/03/2015 | 7/19/2016 | Y | EXP | 55 | 05/18/2016 | 10/17/2017 | 353 | 0 | 353 | 4/6/2016 | 4/6/2016 | 4/6/2016 | Connected |  | N
National Grid | BILLERICA | 566878 | 01821 | 7.6 | Solar | 05_14_2L2 | 11/03/2023 | 11/27/2023 | 15 | 8 | 7 | 11/28/2023 | 11/28/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/03/2023 | 2/19/2025 | Y | EXP | 365 | 07/29/2024 | 10/08/2024 | 72 | 0 | 72 |  |  | 10/17/2024 | Connected |  | N
National Grid | LAWRENCE | 616733 | 01841 | 23 | Solar | 05_14_57L2 | 06/10/2024 | 06/14/2024 | 4 | 3 | 1 | 06/17/2024 | 06/17/2024 | 84 | 65 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 570311 | 01602 | 7.6 | Solar | 05_14_70L8 | 11/15/2023 | 12/07/2023 | 15 | 13 | 2 | 12/08/2023 | 12/08/2023 | 30 | 8 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 11/15/2023 | 2/20/2025 | Y | EXP | 365 | 03/19/2024 | 03/18/2024 | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | STURBRIDGE | 573304 | 01518 | 10.036 | Solar | 05_14_8L2 | 11/24/2023 | 11/29/2023 | 3 | 0 | 3 | 11/30/2023 | 11/30/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 550048 | 01569 | 9.5 | Solar | 05_01_23W4 | 08/22/2023 | 08/23/2023 | 1 | 0 | 1 | 08/24/2023 | 08/24/2023 | 125 | 106 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 174616 | 02720 | 300 | Solar | 05_01_408L2 | 12/29/2010 | 12/29/2010 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/29/2012 | N | EXP | 336 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/29/2012 | Connected |  | N
National Grid | MARLBOROUGH | 371560 | 01752 | 116.6 | Solar | 05_05_321W6 | 08/04/2021 | 11/03/2021 | 63 | 53 | 10 | 11/04/2021 | 11/04/2021 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 08/04/2021 | 6/26/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GLOUCESTER | 660363 | 01930 | 499.9 | Solar | 05_05_106W46 | 02/06/2025 | 03/27/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2025 | 07/31/2025 | 86 | 67 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 291983 | 01851 | 249 | Solar | 05_05_311W2 | 05/14/2020 | 05/21/2020 | 4 | 0 | 4 | 05/22/2020 | 05/22/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176170 | 01886 | 2.75 | Solar | 05_12_51T1 | 04/22/2015 | 04/22/2015 | 1 | 1 | 0 | 04/24/2015 | 04/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2015 |  | 9/30/2015 | N | EXP | 142 |  |  | 0 | 0 | 0 | 6/1/2015 | 6/1/2015 | 9/24/2015 | Connected |  | N
National Grid | BILLERICA | 583609 | 01821 | 6.67 | Solar | 05_14_2L2 | 04/09/2024 | 03/06/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 71 | 59 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 617530 | 01841 | 15.2 | Solar | 05_14_57L2 | 09/18/2024 |  | 29 | 27 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 597903 | 01602 | 16.4 | Solar | 05_14_70L8 | 03/19/2024 | 03/21/2024 | 2 | 0 | 2 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2024 | Connected |  | N
National Grid | BRIMFIELD | 579143 | 01010 | 10 | Solar | 05_14_8L2 | 01/10/2024 | 01/30/2024 | 14 | 12 | 2 | 01/31/2024 | 01/31/2024 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 6/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N
National Grid | MENDON | 577496 | 01756 | 6 | Solar | 05_01_23W4 | 12/27/2023 | 01/03/2024 | 4 | 0 | 4 | 01/04/2024 | 01/04/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | FALL RIVER | 174615 | 02720 | 585 | Solar | 05_01_408L2 | 12/14/2010 | 12/14/2010 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2011 |  | 2/27/2012 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/27/2012 | Connected |  | N
National Grid | MARLBOROUGH | 366925 | 01752 | 0 | Other | 05_05_321W6 | 07/02/2021 | 07/22/2021 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/23/2021 | 07/30/2021 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 07/02/2021 | 9/4/2026 | Y | STD | 35 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BEVERLY | 660362 | 01915 | 499.9 | Solar | 05_05_106W46 | 02/06/2025 | 03/25/2025 | 32 | 22 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2025 | 07/31/2025 | 88 | 69 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LOWELL | 298911 | 01851 | 24.78 | Solar | 05_05_311W2 | 08/14/2020 | 08/17/2020 | 0 | 0 | 0 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 8/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2021 | Connected |  | N
National Grid | WESTFORD | 176167 | 01886 | 150 | Solar | 05_12_51T1 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 | 04/20/2015 | 04/20/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 |  | 9/30/2015 | N | EXP | 161 |  |  | 0 | 0 | 0 | 6/19/2015 | 6/19/2015 | 11/6/2015 | Connected |  | N
National Grid | TEWKSBURY | 588923 | 01876 | 7.6 | Solar | 05_14_2L2 | 02/28/2024 | 03/05/2024 | 4 | 0 | 4 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 3/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 629694 | 01844 | 10 | Solar | 05_14_57L2 | 08/02/2024 | 08/26/2024 | 8 | 5 | 3 | 08/27/2024 | 08/27/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 | 08/02/2024 | 9/19/2025 | Y | EXP | 365 | 10/24/2024 | 10/30/2024 | 7 | 0 | 7 |  |  | 12/27/2024 | Connected |  | N
National Grid | WORCESTER | 602386 | 01602 | 5.76 | Solar | 05_14_70L8 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 582651 | 01518 | 5.22 | Solar | 05_14_8L2 | 02/01/2024 | 02/06/2024 | 3 | 0 | 3 | 02/07/2024 | 02/07/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 02/01/2024 | 3/27/2025 | Y | EXP | 365 | 04/16/2024 | 08/28/2024 | 135 | 0 | 135 |  |  | 9/19/2024 | Connected |  | N
National Grid | UXBRIDGE | 652348 | 01569 | 7.6 | Solar | 05_01_23W4 | 11/05/2024 | 11/20/2024 | 5 | 1 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/05/2024 | 5/28/2026 | Y | EXP | 365 | 02/25/2025 | 03/06/2025 | 10 | 0 | 10 |  |  | 7/11/2025 | Connected |  | N
National Grid | FALL RIVER | 175628 | 02720 | 1000 | Solar | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 37 | 36 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/03/2014 | 10/29/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/29/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 693648 | 01752 | 10 | Solar | 05_05_321W6 | 05/22/2025 | 06/09/2025 | 1 | 0 | 1 | 06/10/2025 | 06/10/2025 | 24 | 21 | 3 | 08/11/2025 | 09/22/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 09/22/2025 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 9/29/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | GLOUCESTER | 697565 | 01930 | 19 | Solar | 05_05_106W46 | 06/10/2025 | 06/12/2025 | 2 | 0 | 2 | 06/13/2025 | 06/13/2025 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LOWELL | 300432 | 01851 | 10 | Solar | 05_05_311W2 | 07/09/2020 | 07/10/2020 | 0 | 0 | 0 | 07/13/2020 | 07/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2020 | Connected |  | N
National Grid | WESTFORD | 176197 | 01886 | 900 | Solar | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 620853 | 01821 | 5.76 | Solar | 05_14_2L2 | 06/26/2024 | 10/11/2024 | 54 | 50 | 4 | 10/15/2024 | 10/15/2024 | 45 | 25 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 633475 | 01841 | 8.7 | Solar | 05_14_57L2 | 09/20/2024 | 10/22/2024 | 9 | 5 | 4 | 10/23/2024 | 10/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WORCESTER | 625684 | 01602 | 10 | Solar | 05_14_70L8 | 07/17/2024 | 07/25/2024 | 1 | 0 | 1 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2024 | Connected |  | N
National Grid | STURBRIDGE | 591651 | 01518 | 0 | Solar | 05_14_8L2 | 06/25/2024 | 07/02/2024 | 6 | 1 | 5 | 07/02/2024 | 07/02/2024 | 73 | 64 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2024 | Connected |  | N
National Grid | UXBRIDGE | 674211 | 01569 | 5.7 | Solar | 05_01_23W4 | 02/25/2025 | 03/13/2025 | 5 | 0 | 5 | 03/14/2025 | 03/14/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 175735 | 02720 | 500 | Solar | 05_01_408L2 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/19/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 |  | 5/1/2016 | N | STD | 376 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 708564 | 01752 | 10 | Solar | 05_05_321W6 | 07/30/2025 | 08/19/2025 | 5 | 0 | 5 | 09/02/2025 | 09/02/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 | 07/30/2025 | 10/13/2026 | Y | EXP | 365 | 12/10/2025 |  | 87 | 0 | 87 |  |  |  | Construction |  | N
National Grid | BEVERLY | 732455 | 01915 | 15.2 | Solar | 05_05_106W46 | 11/12/2025 | 11/17/2025 | 2 | 0 | 2 | 11/18/2025 | 11/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 328171 | 01851 | 15.2 | Solar | 05_05_311W2 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2022 | Connected |  | N
National Grid | WESTFORD | 176196 | 01886 | 950 | Solar | 05_12_51T1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/14/2015 | 05/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BILLERICA | 644511 | 01821 | 7.6 | Solar | 05_14_2L2 | 10/02/2024 | 10/08/2024 | 2 | 0 | 2 | 10/09/2024 | 10/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LAWRENCE | 637981 | 01841 | 5.2 | Solar | 05_14_57L2 | 09/05/2024 | 10/01/2024 | 2 | 0 | 2 | 10/02/2024 | 10/02/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/05/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | WORCESTER | 651555 | 01602 | 7.6 | Solar | 05_14_70L8 | 11/01/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 11/01/2024 | 2/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | BRIMFIELD | 592133 | 01010 | 10 | Solar | 05_14_8L2 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 743409 | 01756 | 5.76 | Solar | 05_01_24W1 | 01/05/2026 | 01/06/2026 | 2 | 0 | 2 | 01/14/2026 | 01/14/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FALL RIVER | 177703 | 02720 | 1500 | Solar | 05_01_408L2 | 05/25/2017 | 05/25/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/21/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2018 | 05/25/2017 | 6/15/2020 | Y | STD | 435 | 10/03/2019 | 12/27/2019 | 85 | 0 | 85 |  |  | 6/15/2020 | Connected |  | N
National Grid | MARLBOROUGH | 726876 | 01752 | 11.4 | Solar | 05_05_321W6 | 10/15/2025 | 01/14/2026 | 8 | 6 | 2 | 01/15/2026 | 01/15/2026 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 174254 | 01930 | 95 | Solar | 05_05_106W46 | 02/27/2012 | 02/27/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 02/27/2012 | 6/1/2012 | Y | EXP | 194 | 12/04/2012 | 12/17/2012 | 9 | 0 | 9 | 8/14/2012 | 8/14/2012 | 5/3/2013 | Connected |  | N
National Grid | LOWELL | 449265 | 01851 | 10 | Solar | 05_05_311W2 | 08/12/2022 | 08/19/2022 | 5 | 4 | 1 | 08/22/2022 | 08/22/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176186 | 01886 | 112 | Solar | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 9/6/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 4/11/2017 | 4/11/2017 | 4/11/2017 | Connected |  | N
National Grid | TEWKSBURY | 649264 | 01876 | 5.76 | Solar | 05_14_2L2 | 10/30/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 10/30/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | LAWRENCE | 651787 | 01841 | 7.6 | Solar | 05_14_57L2 | 11/04/2024 | 01/24/2025 | 5 | 0 | 5 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 653107 | 01602 | 2.32 | Solar | 05_14_70L8 | 11/14/2024 | 12/23/2024 | 3 | 0 | 3 | 12/24/2024 | 12/24/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2025 | Connected |  | N
National Grid | BRIMFIELD | 595986 | 01010 | 6 | Solar | 05_14_8L2 | 03/25/2024 | 03/27/2024 | 2 | 0 | 2 | 03/28/2024 | 03/28/2024 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 | 03/25/2024 | 5/9/2025 | Y | EXP | 365 | 07/31/2024 | 09/17/2024 | 49 | 0 | 49 |  |  | 10/30/2024 | Connected |  | N
National Grid | BLACKSTONE | 748984 | 01504 | 10.64 | Solar | 05_01_24W1 | 02/03/2026 | 02/04/2026 | 2 | 0 | 2 | 02/12/2026 | 02/12/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FALL RIVER | 178484 | 02720 | 3000 | Solar | 05_01_408L2 | 04/03/2018 | 04/18/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2018 | 05/10/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  | 6/27/2023 | N | STD | 553 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 729816 | 01752 | 23 | Solar | 05_05_321W6 | 10/29/2025 | 11/07/2025 | 6 | 2 | 4 | 11/10/2025 | 11/10/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GLOUCESTER | 175001 | 01930 | 60 | Solar | 05_05_106W46 | 09/11/2013 | 09/11/2013 | 10 | 3 | 7 | 09/26/2013 | 09/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2016 |  | 9/26/2016 | N | EXP | 25 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 9/26/2016 | Connected |  | N
National Grid | LOWELL | 421735 | 01851 | 12 | Solar | 05_05_311W2 | 05/10/2022 | 05/12/2022 | 3 | 2 | 1 | 05/13/2022 | 05/13/2022 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2022 |  | 7/19/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2022 | Connected |  | N
National Grid | WESTFORD | 176185 | 01886 | 112 | Solar | 05_12_51T1 | 08/28/2015 | 08/28/2015 | 3 | 3 | 0 | 09/04/2015 | 09/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 | 08/28/2015 | 9/6/2016 | Y | EXP | 362 | 12/19/2016 | 02/24/2017 | 45 | 0 | 45 | 4/20/2017 | 4/20/2017 | 4/14/2017 | Connected |  | N
National Grid | TEWKSBURY | 654955 | 01876 | 3.8 | Solar | 05_14_2L2 | 11/18/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | LAWRENCE | 662101 | 01841 | 11.5 | Solar | 05_14_57L2 | 12/20/2024 | 12/31/2024 | 6 | 2 | 4 | 01/02/2025 | 01/02/2025 | 52 | 27 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | WORCESTER | 657260 | 01606 | 3.8 | Solar | 05_14_70L8 | 11/27/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/27/2024 | 2/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | Y
National Grid | WARREN | 595888 | 01083 | 7.6 | Solar | 05_14_8L2 | 03/29/2024 | 04/03/2024 | 3 | 0 | 3 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2024 |  | 5/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | MENDON | 196201 | 01756 | 7.6 | Solar | 05_01_24W1 | 09/18/2018 | 10/12/2018 | 3 | 3 | 0 | 10/15/2018 | 10/15/2018 | 57 | 54 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178586 | 02720 | 1.84 | Solar | 05_01_408L2 | 03/13/2018 | 03/13/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2018 |  | 3/19/2019 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 746732 | 01752 | 0 | Battery Add-On | 05_05_321W6 | 01/21/2026 | 01/23/2026 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GLOUCESTER | 273678 | 01930 | 4200 | Solar | 05_05_106W46 | 01/30/2020 | 02/19/2020 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/20/2020 | 03/24/2020 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHELMSFORD | 424366 | 01863 | 0 | Solar | 05_05_311W2 | 04/22/2022 | 04/25/2022 | 2 | 1 | 1 | 04/26/2022 | 04/26/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 176284 | 01886 | 126 | Solar | 05_12_51T1 | 05/07/2015 | 05/07/2015 | 14 | 14 | 0 | 06/01/2015 | 06/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2015 |  | 12/31/2016 | N | EXP | 488 |  |  | 0 | 0 | 0 | 2/12/2016 | 2/12/2016 | 3/13/2017 | Connected |  | N
National Grid | TEWKSBURY | 671209 | 01876 | 10 | Solar | 05_14_2L2 | 02/10/2025 | 02/26/2025 | 3 | 0 | 3 | 02/27/2025 | 02/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LAWRENCE | 663185 | 01841 | 5.76 | Solar | 05_14_57L2 | 01/02/2025 | 02/19/2025 | 13 | 9 | 4 | 02/20/2025 | 02/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | WORCESTER | 672610 | 01605 | 5.76 | Solar | 05_14_70L8 | 02/18/2025 | 03/17/2025 | 8 | 2 | 6 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 5/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2025 | Connected |  | N
National Grid | WARREN | 595649 | 01083 | 10 | Solar | 05_14_8L2 | 03/26/2024 | 04/01/2024 | 4 | 0 | 4 | 04/02/2024 | 04/02/2024 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 | 03/26/2024 | 9/15/2025 | Y | EXP | 485 | 07/25/2024 | 08/08/2025 | 380 | 0 | 380 |  |  | 9/17/2025 | Connected |  | N
National Grid | MENDON | 193107 | 01756 | 10 | Solar | 05_01_24W1 | 08/08/2018 | 10/26/2018 | 38 | 28 | 10 | 10/29/2018 | 10/29/2018 | 36 | 8 | 28 | 11/06/2018 | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 |  | 09/17/2019 | 215 | 8 | 207 |  |  | 0 | 0 | 0 | 12/26/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 312005 | 02720 | 15.2 | Solar | 05_01_408L2 | 09/10/2020 | 09/14/2020 | 1 | 0 | 1 | 09/15/2020 | 09/15/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2020 | Connected |  | N
National Grid | MARLBOROUGH | 174392 | 01752 | 95 | Solar | 05_05_321W6 | 06/07/2012 | 06/07/2012 | 7 | 0 | 7 | 06/21/2012 | 06/21/2012 | 0 | 0 | 0 | 10/17/2012 | 10/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 06/07/2012 | 9/28/2012 | Y | EXP | 75 |  |  | 0 | 0 | 0 | 3/7/2013 | 3/7/2013 | 3/26/2013 | Connected |  | N
National Grid | GLOUCESTER | 396688 | 01930 | 0 | Other | 05_05_106W46 | 01/04/2022 | 01/13/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 01/27/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 441361 | 01851 | 15.2 | Solar | 05_05_311W2 | 06/30/2022 | 07/07/2022 | 4 | 3 | 1 | 07/08/2022 | 07/08/2022 | 79 | 51 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176810 | 01886 | 22.8 | Solar | 05_12_51T1 | 04/27/2016 | 04/27/2016 | 1 | 1 | 0 | 04/29/2016 | 04/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2016 |  | 5/3/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 5/25/2016 | 5/25/2016 | 9/15/2016 | Connected |  | N
National Grid | BILLERICA | 680319 | 01821 | 7.6 | Solar | 05_14_2L2 | 03/25/2025 | 03/28/2025 | 3 | 0 | 3 | 03/31/2025 | 03/31/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | LAWRENCE | 664396 | 01841 | 7.6 | Solar | 05_14_57L2 | 01/08/2025 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 710520 | 01605 | 18.24 | Solar | 05_14_70L8 | 08/07/2025 | 08/14/2025 | 4 | 1 | 3 | 08/15/2025 | 08/15/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | N
National Grid | STURBRIDGE | 599574 | 01518 | 5.85 | Solar | 05_14_8L2 | 04/01/2024 | 04/03/2024 | 3 | 1 | 2 | 04/04/2024 | 04/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 | 04/01/2024 | 5/1/2025 | Y | EXP | 365 | 06/05/2024 | 09/18/2024 | 106 | 0 | 106 |  |  | 10/24/2024 | Connected |  | N
National Grid | MENDON | 261638 | 01756 | 10 | Solar | 05_01_24W1 | 10/25/2019 | 10/28/2019 | 0 | 0 | 0 | 10/29/2019 | 10/29/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 | 10/25/2019 | 10/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2020 | Connected |  | N
National Grid | FALL RIVER | 379733 | 02720 | 15.2 | Solar | 05_01_408L2 | 09/02/2021 | 09/03/2021 | 1 | 0 | 1 | 09/07/2021 | 09/07/2021 | 68 | 26 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 174598 | 01752 | 100 | Solar | 05_05_321W6 | 10/10/2011 | 10/10/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2011 | 10/10/2011 | 5/21/2012 | Y | EXP | 167 | 03/30/2012 | 04/26/2012 | 18 | 0 | 18 | 8/9/2012 | 8/9/2012 | 5/21/2012 | Connected |  | N
National Grid | GLOUCESTER | 410239 | 01930 | 500 | Solar | 05_05_106W46 | 03/10/2022 | 04/06/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/07/2022 | 04/20/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 479117 | 01851 | 7.6 | Solar | 05_05_311W2 | 11/21/2022 | 11/22/2022 | 1 | 0 | 1 | 11/23/2022 | 11/23/2022 | 56 | 32 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2023 |  | 2/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 176960 | 01886 | 45 | Solar | 05_12_51T1 | 07/17/2016 | 07/17/2016 | 1 | 1 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2016 |  | 7/23/2017 | N | EXP | 347 |  |  | 0 | 0 | 0 | 2/13/2017 | 2/13/2017 | 2/13/2017 | Connected |  | N
National Grid | TEWKSBURY | 671910 | 01876 | 150 | Solar | 05_14_2L3 | 02/25/2025 | 03/26/2025 | 22 | 12 | 10 | 03/27/2025 | 03/27/2025 | 47 | 22 | 25 | 03/05/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | Y
National Grid | LAWRENCE | 666605 | 01841 | 17.2 | Solar | 05_14_57L2 | 01/17/2025 | 01/22/2025 | 2 | 0 | 2 | 01/23/2025 | 01/23/2025 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | WORCESTER | 709365 | 01605 | 15.2 | Solar | 05_14_70L8 | 08/04/2025 | 08/07/2025 | 3 | 0 | 3 | 08/08/2025 | 08/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | STURBRIDGE | 602404 | 01518 | 3.8 | Solar | 05_14_8L2 | 04/18/2024 | 04/22/2024 | 2 | 0 | 2 | 04/23/2024 | 04/23/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 293766 | 01756 | 0 | Battery Add-On | 05_01_24W1 | 05/28/2020 | 05/29/2020 | 0 | 0 | 0 | 06/01/2020 | 06/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2020 | 05/28/2020 | 5/28/2021 | Y | EXP | 365 | 09/01/2020 | 09/29/2020 | 28 | 0 | 28 |  |  | 9/30/2020 | Connected |  | N
National Grid | FALL RIVER | 432891 | 02720 | 15.2 | Solar | 05_01_408L2 | 09/15/2022 | 09/15/2022 | 0 | 0 | 0 | 09/16/2022 | 09/16/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2022 |  | 9/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 174635 | 01752 | 9.67 | Solar | 05_05_321W6 | 04/12/2013 | 04/12/2013 | 5 | 0 | 5 | 04/23/2013 | 04/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2013 |  | 7/1/2013 | N | EXP | 34 |  |  | 0 | 0 | 0 | 5/28/2013 | 5/28/2013 | 6/17/2013 | Connected |  | N
National Grid | GLOUCESTER | 431700 | 01930 | 160 | Solar | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 488924 | 01851 | 6.09 | Solar | 05_05_311W2 | 01/25/2023 | 01/31/2023 | 5 | 3 | 2 | 02/01/2023 | 02/01/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2023 |  | 3/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2023 | Connected |  | N
National Grid | WESTFORD | 177027 | 01886 | 731 | Solar | 05_12_51T1 | 03/16/2017 | 03/16/2017 | 12 | 10 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 05/05/2017 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 | 03/16/2017 | 8/18/2021 | Y | STD | 126 | 11/08/2019 | 04/22/2020 | 166 | 0 | 166 |  |  | 8/18/2021 | Connected |  | N
National Grid | TEWKSBURY | 701420 | 01876 | 5.76 | Solar | 05_14_2L3 | 06/26/2025 | 07/31/2025 | 4 | 0 | 4 | 08/01/2025 | 08/01/2025 | 27 | 11 | 16 | 09/22/2025 | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 10/07/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | LAWRENCE | 667168 | 01841 | 10 | Solar | 05_14_57L2 | 01/22/2025 | 02/13/2025 | 2 | 0 | 2 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2025 | Connected |  | N
National Grid | WORCESTER | 709192 | 01605 | 9.425 | Solar | 05_14_71L1 | 08/06/2025 | 10/09/2025 | 5 | 2 | 3 | 10/10/2025 | 10/10/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STURBRIDGE | 603795 | 01518 | 7.6 | Solar | 05_14_8L2 | 04/13/2024 | 05/09/2024 | 3 | 2 | 1 | 05/10/2024 | 05/10/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 429602 | 01756 | 8.7 | Solar | 05_01_24W1 | 06/09/2022 | 06/22/2022 | 8 | 6 | 2 | 06/23/2022 | 06/23/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/09/2022 | 11/30/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | FALL RIVER | 586660 | 02720 | 10 | Solar | 05_01_408L2 | 02/08/2024 | 02/09/2024 | 1 | 0 | 1 | 02/12/2024 | 02/12/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 4/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2024 | Connected |  | N
National Grid | MARLBOROUGH | 174770 | 01752 | 12.9 | Solar | 05_05_321W6 | 01/14/2013 | 01/14/2013 | 5 | 0 | 5 | 01/23/2013 | 01/23/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2013 |  | 4/30/2013 | N | EXP | 46 |  |  | 0 | 0 | 0 | 5/17/2013 | 5/17/2013 | 6/3/2013 | Connected |  | N
National Grid | GLOUCESTER | 431612 | 01930 | 240 | Solar | 05_05_106W46 | 05/20/2022 | 06/21/2022 | 20 | 12 | 8 | 06/22/2022 | 06/22/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/28/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LOWELL | 517555 | 01851 | 15.2 | Solar | 05_05_311W2 | 04/06/2023 | 04/07/2023 | 1 | 0 | 1 | 04/10/2023 | 04/10/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 | 04/06/2023 | 5/10/2024 | Y | EXP | 365 | 07/04/2023 | 11/06/2023 | 126 | 0 | 126 |  |  | 11/14/2023 | Connected |  | N
National Grid | WESTFORD | 177155 | 01886 | 20 | Solar | 05_12_51T1 | 10/24/2016 | 10/24/2016 | 4 | 4 | 0 | 10/28/2016 | 10/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2016 |  | 10/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 12/20/2016 | 12/20/2016 | 12/20/2016 | Connected |  | N
National Grid | TEWKSBURY | 753872 | 01876 | 60 | Solar | 05_14_2L3 | 03/03/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LAWRENCE | 667573 | 01841 | 11.5 | Solar | 05_14_57L2 | 02/03/2025 | 02/06/2025 | 3 | 0 | 3 | 02/07/2025 | 02/07/2025 | 91 | 69 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 6/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | WORCESTER | 715308 | 01605 | 0 | Solar | 05_14_71L1 | 08/28/2025 | 09/02/2025 | 2 | 0 | 2 | 09/03/2025 | 09/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STURBRIDGE | 609010 | 01518 | 5.76 | Solar | 05_14_8L2 | 05/06/2024 | 05/28/2024 | 13 | 10 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 05/06/2024 | 6/24/2025 | Y | EXP | 365 | 07/17/2024 | 10/25/2024 | 101 | 0 | 101 |  |  | 12/21/2024 | Connected |  | N
National Grid | MENDON | 442032 | 01756 | 3.8 | Solar | 05_01_24W1 | 07/27/2022 | 07/29/2022 | 2 | 0 | 2 | 08/01/2022 | 08/01/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2022 |  | 9/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2022 | Connected |  | N
National Grid | FALL RIVER | 620652 | 02720 | 23 | Solar | 05_01_408L2 | 07/03/2024 | 07/11/2024 | 5 | 3 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 07/03/2024 | 8/6/2025 | Y | EXP | 365 | 08/30/2024 | 09/12/2024 | 14 | 0 | 14 |  |  | 1/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 174884 | 01752 | 11 | Solar | 05_05_321W6 | 02/15/2013 | 02/15/2013 | 5 | 0 | 5 | 02/28/2013 | 02/28/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2013 |  | 5/31/2013 | N | EXP | 64 |  |  | 0 | 0 | 0 | 4/29/2013 | 4/29/2013 | 5/22/2013 | Connected |  | N
National Grid | HAMILTON | 537794 | 01982 | 7.6 | Solar | 05_05_106W46 | 07/12/2023 | 07/13/2023 | 1 | 0 | 1 | 07/14/2023 | 07/14/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2023 |  | 8/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | Y
National Grid | LOWELL | 534257 | 01854 | 0 | Solar | 05_05_311W2 | 07/21/2023 | 07/26/2023 | 3 | 1 | 2 | 07/27/2023 | 07/27/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 10/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2024 | Connected |  | N
National Grid | WESTFORD | 177559 | 01886 | 3 | Solar | 05_12_51T1 | 07/13/2017 | 07/13/2017 | 22 | 22 | 0 | 08/15/2017 | 08/15/2017 | 117 | 7 | 110 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/19/2018 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 175901 | 01845 | 224 | Solar | 05_14_2L3 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 | 09/29/2015 | 09/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2015 |  | 10/4/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 | 3/9/2016 | 3/9/2016 | 3/18/2016 | Connected |  | N
National Grid | LAWRENCE | 680865 | 01841 | 12.92 | Solar | 05_14_57L2 | 03/31/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2025 | Connected |  | N
National Grid | WORCESTER | 177528 | 01605 | 66.6 | Solar | 05_14_71L1 | 09/11/2017 | 09/11/2017 | 21 | 20 | 1 | 10/11/2017 | 10/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2017 |  | 6/29/2018 | N | EXP | 26 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | STURBRIDGE | 609653 | 01518 | 7.6 | Solar | 05_14_8L2 | 05/08/2024 | 05/20/2024 | 4 | 0 | 4 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 05/08/2024 | 6/28/2025 | Y | EXP | 365 | 08/29/2024 | 01/07/2025 | 132 | 0 | 132 |  |  | 1/29/2025 | Connected |  | N
National Grid | MENDON | 447540 | 01756 | 3.8 | Solar | 05_01_24W1 | 12/09/2022 | 02/14/2023 | 44 | 42 | 2 | 02/15/2023 | 02/15/2023 | 102 | 81 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2023 | Connected |  | N
National Grid | FALL RIVER | 662427 | 02720 | 9.86 | Solar | 05_01_408L2 | 01/02/2025 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 3/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175073 | 01752 | 9.67 | Solar | 05_05_321W6 | 04/12/2013 | 04/12/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 619984 | 01930 | 50 | Solar | 05_05_106W46 | 07/01/2024 | 09/16/2024 | 53 | 45 | 8 | 09/17/2024 | 09/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2024 |  | 4/11/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/30/2025 | Connected |  | N
National Grid | LOWELL | 538691 | 01854 | 11.05 | Solar | 05_05_311W2 | 10/09/2023 | 10/10/2023 | 1 | 0 | 1 | 10/11/2023 | 10/11/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 178070 | 01886 | 144 | Solar | 05_12_51T1 | 10/31/2017 | 10/31/2017 | 9 | 9 | 0 | 11/20/2017 | 11/20/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2017 |  | 11/6/2018 | N | EXP | 341 |  |  | 0 | 0 | 0 |  |  | 8/27/2018 | Connected |  | N
National Grid | ANDOVER | 176474 | 01845 | 21.8 | Solar | 05_14_2L3 | 03/23/2016 | 03/23/2016 | 3 | 3 | 0 | 03/29/2016 | 03/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 3/29/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | LAWRENCE | 681569 | 01841 | 15.2 | Solar | 05_14_57L2 | 04/01/2025 | 04/07/2025 | 4 | 0 | 4 | 04/08/2025 | 04/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 04/01/2025 | 5/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | N
National Grid | WORCESTER | 178518 | 01605 | 10 | Solar | 05_14_71L1 | 04/04/2018 | 04/04/2018 | 6 | 0 | 6 | 04/13/2018 | 04/13/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 611143 | 01083 | 6 | Solar | 05_14_8L2 | 05/15/2024 | 05/21/2024 | 2 | 0 | 2 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 519419 | 01504 | 12.47 | Solar | 05_01_24W1 | 07/14/2023 | 07/17/2023 | 1 | 0 | 1 | 07/18/2023 | 07/18/2023 | 23 | 0 | 23 | 09/20/2023 | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/20/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/25/2023 |  | 11/26/2024 | N | EXP | 365 | 01/03/2024 | 02/23/2024 | 52 | 0 | 52 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 662789 | 02720 | 9.75 | Solar | 05_01_408L2 | 12/27/2024 | 01/13/2025 | 6 | 0 | 6 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/27/2024 | 5/31/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | MARLBOROUGH | 175167 | 01752 | 15 | Solar | 05_05_321W6 | 11/13/2012 | 11/13/2012 | 6 | 0 | 6 | 11/28/2012 | 11/28/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/4/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 650823 | 01930 | 3.8 | Solar | 05_05_106W46 | 10/30/2024 | 11/20/2024 | 4 | 0 | 4 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 562727 | 01851 | 0 | Battery Add-On | 05_05_311W2 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 4/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2024 | Connected |  | N
National Grid | WESTFORD | 178074 | 01886 | 20 | Solar | 05_12_51T1 | 11/02/2017 | 11/02/2017 | 91 | 91 | 0 | 04/05/2018 | 04/05/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 |  | 11/7/2018 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 176504 | 01845 | 150 | Solar | 05_14_2L3 | 02/09/2016 | 02/09/2016 | 7 | 7 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2016 |  | 2/15/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 12/7/2016 | 12/7/2016 | 11/23/2016 | Connected |  | N
National Grid | LAWRENCE | 688631 | 01841 | 12.92 | Solar | 05_14_57L2 | 05/01/2025 | 05/16/2025 | 2 | 0 | 2 | 05/22/2025 | 05/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | WORCESTER | 184342 | 01606 | 0 | Solar | 05_14_71L1 | 05/18/2018 | 05/18/2018 | 1 | 0 | 1 | 05/22/2018 | 05/22/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2018 |  | 5/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2019 | Connected |  | N
National Grid | STURBRIDGE | 613140 | 01518 | 6 | Solar | 05_14_8L2 | 05/23/2024 | 05/29/2024 | 2 | 0 | 2 | 05/30/2024 | 05/30/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 10/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 525753 | 01756 | 6 | Solar | 05_01_24W1 | 06/21/2023 | 06/21/2023 | 0 | 0 | 0 | 06/22/2023 | 06/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 679369 | 02720 | 3.8 | Solar | 05_01_408L2 | 03/20/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 6/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | MARLBOROUGH | 176164 | 01752 | 990 | Solar | 05_05_321W6 | 02/06/2015 | 02/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/16/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2015 | 02/06/2015 | 12/31/2016 | Y | STD | 53 | 01/12/2017 | 06/15/2017 | 106 | 0 | 106 | 6/5/2017 | 6/5/2017 | 7/6/2017 | Connected |  | N
National Grid | MANCHESTER | 664362 | 01944 | 5.76 | Solar | 05_05_106W46 | 01/08/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/08/2025 | 3/17/2026 | Y | EXP | 365 | 04/15/2025 | 05/13/2025 | 29 | 0 | 29 |  |  | 7/8/2025 | Connected |  | N
National Grid | CHELMSFORD | 581937 | 01863 | 5.376 | Solar | 05_05_311W2 | 01/23/2024 | 02/06/2024 | 11 | 10 | 1 | 02/07/2024 | 02/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/23/2024 | 4/1/2025 | Y | EXP | 365 | 04/30/2024 | 07/03/2024 | 65 | 0 | 65 |  |  | 12/5/2024 | Connected |  | N
National Grid | WESTFORD | 178111 | 01886 | 15 | Solar | 05_12_51T1 | 11/06/2017 | 11/06/2017 | 81 | 80 | 1 | 03/23/2018 | 03/23/2018 | 53 | 0 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 |  | 11/12/2018 | N | EXP | 182 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 176741 | 01810 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 4 | 0 | 11/06/2015 | 11/06/2015 | 424 | 56 | 368 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 9/7/2017 | N | EXP | 582 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | METHUEN | 701934 | 01844 | 19 | Solar | 05_14_57L2 | 07/15/2025 | 07/28/2025 | 8 | 5 | 3 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | WORCESTER | 384672 | 01605 | 144 | Solar | 05_14_71L1 | 10/06/2021 | 12/02/2021 | 38 | 29 | 9 | 12/03/2021 | 12/03/2021 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 | 10/06/2021 | 8/1/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2023 | Connected |  | N
National Grid | STURBRIDGE | 616791 | 01518 | 5.76 | Solar | 05_14_8L2 | 06/10/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2024 |  | 12/6/2025 | N | EXP | 415 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 532272 | 01756 | 7.68 | Solar | 05_01_24W1 | 06/14/2023 | 06/20/2023 | 4 | 0 | 4 | 06/21/2023 | 06/21/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 736063 | 02720 | 10 | Solar | 05_01_412L1 | 11/24/2025 | 12/16/2025 | 1 | 0 | 1 | 01/29/2026 | 01/29/2026 | 26 | 10 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 176377 | 01752 | 792 | Solar | 05_05_321W6 | 11/20/2015 | 11/20/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2015 | 12/14/2015 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ESSEX | 667950 | 01929 | 5.76 | Solar | 05_05_106W46 | 01/27/2025 | 03/28/2025 | 13 | 8 | 5 | 03/31/2025 | 03/31/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LOWELL | 599668 | 01854 | 11 | Solar | 05_05_311W2 | 04/24/2024 | 04/25/2024 | 1 | 0 | 1 | 04/26/2024 | 04/26/2024 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 5/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 178201 | 01886 | 0 | Solar | 05_12_51T1 | 02/15/2018 | 02/15/2018 | 9 | 9 | 0 | 03/08/2018 | 03/08/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2018 |  | 2/21/2019 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  | 5/7/2019 | Connected |  | N
National Grid | ANDOVER | 176838 | 01810 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 312 | 56 | 256 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 | 10/30/2015 | 11/7/2016 | Y | EXP | 278 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 718919 | 01841 | 10 | Solar | 05_14_57L2 | 09/14/2025 | 09/18/2025 | 4 | 0 | 4 | 09/19/2025 | 09/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 11/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | WORCESTER | 514296 | 01605 | 10 | Solar | 05_14_71L1 | 04/03/2023 | 04/06/2023 | 3 | 0 | 3 | 04/07/2023 | 04/07/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STURBRIDGE | 617449 | 01518 | 5.76 | Solar | 05_14_8L2 | 06/12/2024 | 06/28/2024 | 5 | 0 | 5 | 07/01/2024 | 07/01/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 |  | 7/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | UXBRIDGE | 541036 | 01569 | 3.8 | Solar | 05_01_24W1 | 07/18/2023 | 07/19/2023 | 1 | 0 | 1 | 07/20/2023 | 07/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 746938 | 02720 | 5.76 | Solar | 05_01_412L1 | 01/22/2026 | 01/23/2026 | 3 | 0 | 3 | 02/04/2026 | 02/04/2026 | 21 | 5 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 176697 | 01752 | 1872 | Solar | 05_05_321W6 | 04/21/2016 | 04/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/08/2016 | 30 | 22 | 8 |  |  | 0 | 0 | 0 | 03/29/2018 | 05/19/2017 | 0 | 0 | 0 | 5/3/2017 | 04/21/2016 | 9/21/2018 | Y | STD | 56 | 04/12/2018 | 08/10/2018 | 110 | 0 | 110 |  |  | 9/19/2018 | Connected |  | N
National Grid | GLOUCESTER | 688748 | 01930 | 18.24 | Solar | 05_05_106W46 | 04/30/2025 | 05/01/2025 | 1 | 0 | 1 | 05/02/2025 | 05/02/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 | 04/30/2025 | 7/17/2026 | Y | EXP | 365 | 08/15/2025 | 10/08/2025 | 55 | 0 | 55 |  |  | 10/10/2025 | Connected |  | N
National Grid | LOWELL | 609713 | 01851 | 10 | Solar | 05_05_311W2 | 05/08/2024 | 05/16/2024 | 6 | 5 | 1 | 05/17/2024 | 05/17/2024 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 | 05/08/2024 | 7/2/2025 | Y | EXP | 365 | 09/10/2024 | 10/16/2024 | 37 | 0 | 37 |  |  | 2/28/2025 | Connected |  | N
National Grid | WESTFORD | 178526 | 01886 | 3.8 | Solar | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/16/2018 | 05/16/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ANDOVER | 178013 | 01810 | 150 | Solar | 05_14_2L3 | 10/30/2015 | 10/30/2015 | 4 | 0 | 4 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2016 |  | 7/4/2018 | N | EXP | 882 |  |  | 0 | 0 | 0 | 7/18/2017 | 7/18/2017 | 7/16/2017 | Connected |  | N
National Grid | LAWRENCE | 727574 | 01841 | 15.2 | Solar | 05_14_57L2 | 10/19/2025 | 10/22/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | WORCESTER | 543541 | 01605 | 84.6 | Solar | 05_14_71L1 | 07/25/2023 | 08/29/2023 | 26 | 16 | 10 | 08/30/2023 | 08/30/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 617125 | 01570 | 7.6 | Solar | 05_14_8L2 | 06/11/2024 | 06/18/2024 | 1 | 0 | 1 | 06/20/2024 | 06/20/2024 | 10 | 2 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | BLACKSTONE | 553080 | 01504 | 11.5 | Solar | 05_01_24W1 | 09/06/2023 | 09/07/2023 | 1 | 0 | 1 | 09/08/2023 | 09/08/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 748832 | 02720 | 5.76 | Solar | 05_01_412L1 | 02/02/2026 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 177076 | 01752 | 252 | Solar | 05_05_321W6 | 08/03/2016 | 08/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2016 | 08/18/2016 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 | 08/03/2016 | 3/12/2021 | Y | STD | 92 | 06/27/2018 | 12/21/2018 | 177 | 0 | 177 |  |  | 3/4/2021 | Connected |  | N
National Grid | MANCHESTER | 663333 | 01944 | 2.32 | Solar | 05_05_106W81 | 01/02/2025 | 01/23/2025 | 11 | 7 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LOWELL | 611935 | 01851 | 20 | Solar | 05_05_311W2 | 05/22/2024 | 06/24/2024 | 21 | 20 | 1 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | WESTFORD | 178557 | 01886 | 11.4 | Solar | 05_12_51T1 | 04/04/2018 | 04/04/2018 | 11 | 10 | 1 | 05/15/2018 | 05/15/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2018 |  | 4/10/2019 | N | EXP | 323 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 178705 | 01845 | 249.8 | Solar | 05_14_2L3 | 03/21/2018 | 03/21/2018 | 11 | 0 | 11 | 04/05/2018 | 04/05/2018 | 38 | 13 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 3/31/2021 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | LAWRENCE | 710654 | 01841 | 0 | Battery Add-On | 05_14_57L3 | 08/08/2025 | 08/11/2025 | 1 | 0 | 1 | 08/12/2025 | 08/12/2025 | 49 | 34 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WORCESTER | 573060 | 01606 | 0 | Solar | 05_14_71L1 | 12/04/2023 | 12/12/2023 | 6 | 4 | 2 | 12/13/2023 | 12/13/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | WEBSTER | 619063 | 01570 | 5.76 | Solar | 05_14_8L2 | 06/19/2024 | 07/01/2024 | 3 | 0 | 3 | 07/02/2024 | 07/02/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2024 | Connected |  | N
National Grid | UXBRIDGE | 568633 | 01569 | 7.6 | Solar | 05_01_24W1 | 11/21/2023 | 11/30/2023 | 6 | 2 | 4 | 12/01/2023 | 12/01/2023 | 86 | 66 | 20 | 06/05/2024 | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 07/09/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 7/8/2024 |  | 9/12/2025 | N | EXP | 365 | 09/13/2024 | 09/21/2024 | 9 | 0 | 9 |  |  | 10/18/2024 | Connected |  | N
National Grid | FALL RIVER | 752287 | 02720 |  | Battery Add-On | 05_01_412L1 | 02/20/2026 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 178463 | 01752 | 2460 | Solar | 05_05_321W6 | 01/22/2018 | 04/30/2018 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/01/2018 | 05/15/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 | 01/22/2018 | 1/5/2026 | Y | STD | 54 | 04/29/2025 | 06/04/2025 | 37 | 0 | 37 |  |  | 12/15/2025 | Connected |  | N
National Grid | GLOUCESTER | 747295 | 01930 | 10.88 | Solar | 05_05_106W81 | 02/10/2026 | 02/11/2026 | 3 | 1 | 2 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LOWELL | 624368 | 01851 | 10 | Solar | 05_05_311W2 | 07/12/2024 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 189490 | 01886 | 10 | Solar | 05_12_51T1 | 10/09/2018 | 10/11/2018 | 1 | 0 | 1 | 10/12/2018 | 10/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 10/15/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/30/2019 | Connected |  | N
National Grid | ANDOVER | 184041 | 01845 | 73.3 | Solar | 05_14_2L3 | 04/30/2018 | 04/30/2018 | 0 | 0 | 0 | 05/01/2018 | 05/01/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2018 |  | 4/27/2019 | N | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 1/8/2019 | Connected |  | N
National Grid | METHUEN | 712195 | 01844 | 3.8 | Solar | 05_14_57L3 | 08/14/2025 | 09/05/2025 | 25 | 23 | 2 | 10/23/2025 | 10/23/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2025 | 08/14/2025 | 11/17/2026 | Y | EXP | 365 | 01/15/2026 |  | 51 | 0 | 51 |  |  |  | Construction |  | N
National Grid | WORCESTER | 575824 | 01605 | 100 | Solar | 05_14_71L1 | 12/08/2023 | 12/22/2023 | 10 | 3 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 620656 | 01570 | 7.6 | Solar | 05_14_8L2 | 06/27/2024 | 07/16/2024 | 1 | 1 | 0 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 06/27/2024 | 3/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | UXBRIDGE | 582505 | 01569 | 10 | Solar | 05_01_24W1 | 02/16/2024 | 02/23/2024 | 4 | 0 | 4 | 02/26/2024 | 02/26/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 174409 | 02720 | 11.18 | Solar | 05_01_412L1 | 06/20/2012 | 06/20/2012 | 5 | 0 | 5 | 06/29/2012 | 06/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 9/17/2012 | N | EXP | 86 |  |  | 0 | 0 | 0 | 9/19/2012 | 9/19/2012 | 1/3/2013 | Connected |  | N
National Grid | MARLBOROUGH | 189220 | 01752 | 0 | Battery Add-On | 05_05_321W6 | 06/26/2018 | 06/26/2018 | 25 | 0 | 25 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 8/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | GLOUCESTER | 175183 | 01930 | 60 | Natural Gas | 05_05_106W81 | 05/06/2013 | 05/06/2013 | 8 | 0 | 8 | 05/17/2013 | 05/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2013 |  | 9/30/2013 | N | EXP | 53 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/31/2013 | Connected |  | N
National Grid | LOWELL | 663953 | 01851 | 10 | Solar | 05_05_311W2 | 01/06/2025 | 02/13/2025 | 3 | 0 | 3 | 02/14/2025 | 02/14/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | TYNGSBORO | 195069 | 01879 | 0 | Solar | 05_12_51T1 | 09/05/2018 | 10/02/2018 | 10 | 4 | 6 | 10/03/2018 | 10/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2018 | Connected |  | N
National Grid | ANDOVER | 381753 | 01810 | 10 | Solar | 05_14_2L3 | 10/11/2021 | 12/07/2021 | 3 | 1 | 2 | 10/18/2021 | 10/18/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2022 | Connected |  | Y
National Grid | LAWRENCE | 174461 | 01841 | 34.2 | Solar | 05_14_57L3 | 09/01/2011 | 09/01/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 09/01/2011 | 10/31/2012 | Y | EXP | 42 |  |  | 0 | 0 | 0 | 1/10/2013 | 1/10/2013 | 1/25/2013 | Connected |  | N
National Grid | WORCESTER | 608290 | 01605 | 7.6 | Solar | 05_14_71L1 | 05/04/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 | 05/04/2024 | 2/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 621743 | 01570 | 7.6 | Solar | 05_14_8L2 | 07/01/2024 | 07/10/2024 | 3 | 0 | 3 | 07/11/2024 | 07/11/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2024 | Connected |  | N
National Grid | BLACKSTONE | 595776 | 01504 | 3.8 | Solar | 05_01_24W1 | 03/15/2024 | 03/18/2024 | 1 | 0 | 1 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 |  | 3/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2024 | Connected |  | N
National Grid | FALL RIVER | 175205 | 02720 | 1380 | Solar | 05_01_412L1 | 12/07/2012 | 12/07/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 01/15/2013 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 12/07/2012 | 1/20/2016 | Y | STD | 572 | 07/30/2015 | 12/20/2016 | 346 | 0 | 346 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | MARLBOROUGH | 196342 | 01752 | 19.52 | Solar | 05_05_321W6 | 09/27/2018 | 10/04/2018 | 4 | 0 | 4 | 10/04/2018 | 10/04/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 11/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2019 | Connected |  | N
National Grid | ESSEX | 176482 | 01929 | 144 | Solar | 05_05_106W81 | 05/20/2016 | 05/20/2016 | 1 | 1 | 0 | 05/26/2016 | 05/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2016 | 05/20/2016 | 5/30/2017 | Y | EXP | 337 | 10/10/2016 | 11/04/2016 | 18 | 0 | 18 | 12/6/2016 | 12/6/2016 | 12/8/2016 | Connected |  | N
National Grid | LOWELL | 666520 | 01851 | 0 | Battery Add-On | 05_05_311W2 | 02/06/2025 | 02/19/2025 | 8 | 3 | 5 | 02/20/2025 | 02/20/2025 | 57 | 39 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2025 | Connected |  | N
National Grid | WESTFORD | 195777 | 01886 | 147.6 | Solar | 05_12_51T1 | 09/12/2018 | 09/19/2018 | 4 | 0 | 4 | 09/20/2018 | 09/20/2018 | 20 | 0 | 20 | 09/13/2019 | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 09/12/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2019 |  | 12/31/2020 | N | EXP | 172 |  |  | 0 | 0 | 0 |  |  | 12/31/2020 | Connected |  | N
National Grid | ANDOVER | 406001 | 01845 | 0 | Battery Add-On | 05_14_2L3 | 02/01/2022 | 02/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/08/2022 | 02/25/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LAWRENCE | 175011 | 01841 | 235 | Solar | 05_14_57L3 | 08/31/2011 | 08/31/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2011 | 08/31/2011 | 11/30/2012 | Y | EXP | 338 | 01/09/2012 | 01/09/2012 | 0 | 0 | 0 | 6/3/2014 | 6/3/2014 | 5/11/2012 | Connected |  | N
National Grid | WORCESTER | 615033 | 01605 | 7.6 | Solar | 05_14_71L1 | 06/03/2024 | 06/18/2024 | 5 | 0 | 5 | 06/20/2024 | 06/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 7/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | WEBSTER | 622785 | 01570 | 6 | Solar | 05_14_8L2 | 07/05/2024 | 07/18/2024 | 4 | 0 | 4 | 07/19/2024 | 07/19/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 | 07/05/2024 | 8/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | MENDON | 595773 | 01756 | 6.09 | Solar | 05_01_24W1 | 04/08/2024 | 05/17/2024 | 7 | 5 | 2 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 |  | 7/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | FALL RIVER | 175512 | 02720 | 75 | Solar | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 1 | 3 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 |  | 4/30/2015 | N | EXP | 139 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 7/10/2015 | Connected |  | N
National Grid | MARLBOROUGH | 203356 | 01752 | 2600 | Solar | 05_05_321W6 | 12/13/2018 | 02/20/2019 | 69 | 50 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/21/2019 | 03/26/2019 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2020 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 364046 | 01944 | 6.24 | Solar | 05_05_106W81 | 07/12/2021 | 07/13/2021 | 2 | 1 | 1 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2021 | 07/12/2021 | 2/8/2023 | Y | EXP | 365 | 12/03/2021 | 02/08/2022 | 68 | 0 | 68 |  |  | 2/10/2022 | Connected |  | N
National Grid | LOWELL | 667203 | 01851 | 0 | Solar | 05_05_311W2 | 01/23/2025 | 02/13/2025 | 9 | 4 | 5 | 02/14/2025 | 02/14/2025 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | WESTFORD | 204210 | 01886 | 0 | Solar | 05_12_51T1 | 12/20/2018 | 01/03/2019 | 7 | 0 | 7 | 01/04/2019 | 01/04/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 | 12/20/2018 | 1/3/2020 | Y | EXP | 365 | 08/23/2019 | 12/18/2019 | 117 | 0 | 117 |  |  | 7/31/2020 | Connected |  | N
National Grid | ANDOVER | 461779 | 01845 | 0 | Solar | 05_14_2L3 | 09/29/2022 | 09/30/2022 | 1 | 0 | 1 | 10/03/2022 | 10/03/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 1/13/2024 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | LAWRENCE | 175226 | 01841 | 12 | Solar | 05_14_57L3 | 01/06/2015 | 01/06/2015 | 8 | 4 | 4 | 01/17/2015 | 01/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2015 |  | 5/31/2015 | N | EXP | 118 |  |  | 0 | 0 | 0 | 10/1/2015 | 10/1/2015 | 6/6/2016 | Connected |  | N
National Grid | WORCESTER | 646857 | 01605 | 10 | Solar | 05_14_71L1 | 10/29/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2024 | 10/29/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | Y
National Grid | WEBSTER | 626779 | 01570 | 10 | Solar | 05_14_8L2 | 07/22/2024 | 09/27/2024 | 36 | 31 | 5 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 | 07/22/2024 | 1/20/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | MENDON | 612371 | 01756 | 6 | Solar | 05_01_24W1 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 | 05/20/2024 | 7/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2024 | Connected |  | N
National Grid | FALL RIVER | 175511 | 02720 | 140 | Solar | 05_01_412L1 | 12/05/2014 | 12/05/2014 | 4 | 4 | 0 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 12/05/2014 | 4/30/2015 | Y | EXP | 64 | 06/01/2015 | 07/08/2015 | 25 | 0 | 25 | 2/25/2015 | 2/25/2015 | 8/21/2015 | Connected |  | N
National Grid | MARLBOROUGH | 204309 | 01752 | 240 | Solar | 05_05_321W6 | 12/27/2018 | 01/07/2019 | 2 | 0 | 2 | 01/08/2019 | 01/08/2019 | 3 | 0 | 3 | 01/23/2019 | 04/29/2019 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  | 04/29/2019 | 67 | 0 | 67 |  |  | 0 | 0 | 0 | 5/2/2019 |  | 1/21/2020 | N | EXP | 228 |  |  | 0 | 0 | 0 |  |  | 1/23/2020 | Connected |  | N
National Grid | GLOUCESTER | 451467 | 01930 | 5.76 | Solar | 05_05_106W81 | 10/27/2022 | 11/13/2022 | 11 | 9 | 2 | 11/14/2022 | 11/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2022 | Connected |  | Y
National Grid | LOWELL | 727052 | 01851 | 7.6 | Solar | 05_05_311W2 | 10/16/2025 | 10/21/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTFORD | 217096 | 01886 | 0 | Solar | 05_12_51T1 | 04/03/2019 | 04/09/2019 | 3 | 0 | 3 | 04/10/2019 | 04/10/2019 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2019 | Connected |  | N
National Grid | ANDOVER | 743764 | 01845 | 10 | Solar | 05_05_3451W2 | 01/06/2026 | 01/15/2026 | 5 | 4 | 1 | 01/16/2026 | 01/16/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 175693 | 01841 | 18 | Solar | 05_14_57L3 | 05/23/2014 | 05/23/2014 | 5 | 0 | 5 | 06/03/2014 | 06/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2014 |  | 8/29/2014 | N | EXP | 58 |  |  | 0 | 0 | 0 | 7/2/2014 | 7/2/2014 | 10/13/2014 | Connected |  | N
National Grid | WORCESTER | 661800 | 01605 | 7.6 | Solar | 05_14_71L1 | 12/19/2024 | 01/08/2025 | 4 | 0 | 4 | 01/09/2025 | 01/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | WEBSTER | 631949 | 01570 | 7.6 | Solar | 05_14_8L2 | 08/12/2024 | 08/19/2024 | 1 | 0 | 1 | 08/20/2024 | 08/20/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 | 08/12/2024 | 9/3/2025 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | MENDON | 619203 | 01756 | 11.4 | Solar | 05_01_24W1 | 10/28/2024 | 11/14/2024 | 9 | 6 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 | 01/06/2025 | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 01/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/25/2026 | N | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  | 4/10/2025 | Connected |  | N
National Grid | FALL RIVER | 175799 | 02720 | 16 | Solar | 05_01_412L1 | 02/27/2015 | 02/27/2015 | 6 | 1 | 5 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 |  | 7/31/2015 | N | EXP | 141 |  |  | 0 | 0 | 0 |  |  | 12/23/2015 | Connected |  | N
National Grid | MARLBOROUGH | 204297 | 01752 | 108 | Solar | 05_05_321W6 | 01/04/2019 | 01/10/2019 | 3 | 0 | 3 | 01/11/2019 | 01/11/2019 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GLOUCESTER | 456820 | 01930 | 6 | Solar | 05_05_106W81 | 01/26/2023 | 05/02/2023 | 65 | 65 | 0 | 05/03/2023 | 05/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | LOWELL | 587963 | 01851 | 325 | Natural Gas | 05_05_311W3 | 02/23/2024 | 08/02/2024 | 111 | 101 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2024 | 08/27/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  | 7/3/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 221773 | 01886 | 0 | Solar | 05_12_51T1 | 04/23/2019 | 04/30/2019 | 4 | 0 | 4 | 05/01/2019 | 05/01/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/28/2019 | Connected |  | N
National Grid | ANDOVER | 493141 | 01845 | 15.2 | Solar | 05_05_3451W2 | 01/23/2023 | 01/24/2023 | 2 | 1 | 1 | 01/25/2023 | 01/25/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  | 2/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/18/2023 | Connected |  | N
National Grid | LAWRENCE | 177025 | 01841 | 86.4 | Solar | 05_14_57L3 | 03/16/2017 | 03/16/2017 | 6 | 5 | 1 | 03/24/2017 | 03/24/2017 | 229 | 0 | 229 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2017 |  | 3/21/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WORCESTER | 666713 | 01605 | 5.76 | Solar | 05_14_71L1 | 01/20/2025 | 05/02/2025 | 59 | 58 | 1 | 05/02/2025 | 05/02/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 634175 | 01570 | 5.76 | Solar | 05_14_8L2 | 08/22/2024 | 10/23/2024 | 3 | 0 | 3 | 10/24/2024 | 10/24/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 08/22/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2025 | Connected |  | N
National Grid | MENDON | 622805 | 01756 | 5.76 | Solar | 05_01_24W1 | 07/19/2024 | 09/03/2024 | 22 | 21 | 1 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 9/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | FALL RIVER | 177171 | 02720 | 7.6 | Solar | 05_01_412L1 | 01/27/2017 | 01/27/2017 | 4 | 4 | 0 | 02/03/2017 | 02/03/2017 | 200 | 0 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2017 |  | 2/4/2018 | N | EXP | 363 | 06/19/2017 | 08/09/2017 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 204286 | 01752 | 60 | Solar | 05_05_321W6 | 12/27/2018 | 01/25/2019 | 14 | 13 | 1 | 01/11/2019 | 01/11/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2019 | Connected |  | N
National Grid | MANCHESTER | 512760 | 01944 | 6 | Solar | 05_05_106W81 | 07/18/2023 |  | 81 | 79 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PLAINVILLE | 676908 | 02762 | 3.8 | Solar | 05_05_311W3 | 03/10/2025 | 03/22/2025 | 17 | 13 | 4 | 04/29/2025 | 04/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 03/10/2025 | 6/10/2026 | Y | EXP | 365 | 07/19/2025 | 09/18/2025 | 62 | 0 | 62 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 225352 | 01886 | 10 | Solar | 05_12_51T1 | 05/06/2019 | 05/16/2019 | 8 | 8 | 0 | 05/17/2019 | 05/17/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2019 |  | 12/30/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | Y
National Grid | LAWRENCE | 544286 | 01843 | 14.625 | Solar | 05_05_3451W2 | 08/03/2023 | 08/04/2023 | 1 | 0 | 1 | 08/07/2023 | 08/07/2023 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2023 |  | 9/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | LAWRENCE | 198756 | 01841 | 174 | Solar | 05_14_57L3 | 11/06/2018 | 11/27/2018 | 0 | 0 | 0 | 11/28/2018 | 11/28/2018 | 11 | 0 | 11 | 04/15/2019 | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 05/01/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 6/14/2019 |  | 10/15/2020 | N | EXP | 489 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 684738 | 01605 | 5.76 | Solar | 05_14_71L1 | 04/11/2025 | 04/29/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 |  | 6/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | DOUGLAS | 635288 | 01516 | 2.32 | Solar | 05_14_8L2 | 08/26/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/26/2024 | 10/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | MENDON | 634322 | 01756 | 19 | Solar | 05_01_24W1 | 08/21/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  | 9/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/5/2025 | Connected |  | N
National Grid | FALL RIVER | 177168 | 02720 | 4980 | Solar | 05_01_412L1 | 01/26/2017 | 02/01/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2017 | 04/05/2017 | 45 | 33 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2018 |  |  | N | STD | 122 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 263346 | 01752 | 3 | Solar | 05_05_321W6 | 12/13/2019 | 01/14/2020 | 20 | 16 | 4 | 01/15/2020 | 01/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2020 | 12/13/2019 | 12/13/2020 | Y | EXP | 365 | 04/25/2020 | 06/10/2020 | 46 | 0 | 46 |  |  | 6/15/2020 | Connected |  | N
National Grid | MANCHESTER | 607663 | 01944 | 6 | Solar | 05_05_106W81 | 04/30/2024 | 05/16/2024 | 4 | 0 | 4 | 05/17/2024 | 05/17/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 | 04/30/2024 | 7/9/2025 | Y | EXP | 365 | 09/17/2024 | 12/17/2024 | 92 | 0 | 92 |  |  | 1/6/2025 | Connected |  | Y
National Grid | PLAINVILLE | 716400 | 02762 | 17.6 | Solar | 05_05_311W3 | 09/08/2025 | 09/11/2025 | 3 | 0 | 3 | 09/12/2025 | 09/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 189677 | 01886 | 15.2 | Solar | 05_07_2W1 | 06/29/2018 | 06/29/2018 | 8 | 7 | 1 | 07/12/2018 | 07/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | LAWRENCE | 647035 | 01843 | 5.76 | Solar | 05_05_3451W2 | 10/24/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/24/2024 | 1/24/2026 | Y | EXP | 365 | 04/01/2025 | 04/24/2025 | 24 | 0 | 24 |  |  | 5/6/2025 | Connected |  | N
National Grid | LAWRENCE | 232316 | 01841 | 249 | Solar | 05_14_57L3 | 11/19/2019 | 01/09/2020 | 19 | 15 | 4 | 04/02/2020 | 04/02/2020 | 16 | 0 | 16 | 05/21/2020 | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 |  | 10/28/2020 | 100 | 3 | 97 |  |  | 0 | 0 | 0 | 10/13/2020 |  | 12/30/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WORCESTER | 719515 | 01605 | 7.6 | Solar | 05_14_71L3 | 09/16/2025 | 10/02/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 | 09/16/2025 | 12/18/2026 | Y | EXP | 365 | 03/06/2026 |  | 1 | 0 | 1 |  |  |  | Construction |  | N
National Grid | WEBSTER | 638038 | 01570 | 7.6 | Solar | 05_14_8L2 | 09/05/2024 | 10/25/2024 | 22 | 21 | 1 | 10/28/2024 | 10/28/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 634620 | 01756 | 10 | Solar | 05_01_24W1 | 08/22/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 33 | 24 | 9 | 01/24/2025 | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  | 03/11/2025 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 4/8/2026 | N | EXP | 365 | 08/14/2025 | 08/25/2025 | 12 | 0 | 12 |  |  | 9/3/2025 | Connected |  | N
National Grid | FALL RIVER | 177197 | 02720 | 7.6 | Solar | 05_01_412L1 | 11/01/2016 | 11/01/2016 | 3 | 3 | 0 | 11/07/2016 | 11/07/2016 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 11/01/2016 | 5/7/2018 | Y | EXP | 538 | 10/20/2017 | 04/11/2018 | 101 | 0 | 101 |  |  | 5/21/2018 | Connected |  | N
National Grid | MARLBOROUGH | 278122 | 01752 | 0 | Other | 05_05_321W6 | 02/05/2020 | 02/11/2020 | 0 | 0 | 0 | 02/12/2020 | 02/12/2020 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2020 |  | 2/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2020 | Connected |  | N
National Grid | BEVERLY | 630417 | 01915 | 5.76 | Solar | 05_05_106W81 | 08/06/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/06/2024 | 8/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | PLAINVILLE | 718553 | 02762 | 4995 | Other | 05_05_311W3 | 09/29/2025 | 10/30/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 | 12/01/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTFORD | 296127 | 01886 | 9.57 | Solar | 05_07_2W1 | 06/23/2020 | 06/29/2020 | 3 | 0 | 3 | 06/30/2020 | 06/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2020 | Connected |  | N
National Grid | LAWRENCE | 657529 | 01843 | 5.76 | Solar | 05_05_3451W2 | 11/28/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | LAWRENCE | 243897 | 01841 | 0 | Solar | 05_14_57L3 | 07/17/2019 | 08/07/2019 | 14 | 9 | 5 | 08/08/2019 | 08/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2019 | Connected |  | N
National Grid | WORCESTER | 721298 | 01606 | 13.36 | Solar | 05_14_71L3 | 09/23/2025 | 10/06/2025 | 3 | 0 | 3 | 12/05/2025 | 12/05/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEBSTER | 642722 | 01570 | 5.76 | Solar | 05_14_8L2 | 09/25/2024 | 10/09/2024 | 2 | 0 | 2 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/25/2024 | 11/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 639891 | 01756 | 5.76 | Solar | 05_01_24W1 | 09/12/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2024 | 09/12/2024 | 12/10/2025 | Y | EXP | 37 | 01/21/2025 | 10/30/2025 | 283 | 0 | 283 |  |  | 12/5/2025 | Connected |  | N
National Grid | FALL RIVER | 177263 | 02720 | 19 | Solar | 05_01_412L1 | 08/23/2016 | 08/23/2016 | 2 | 2 | 0 | 08/26/2016 | 08/26/2016 | 227 | 0 | 227 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 8/29/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 291242 | 01752 | 750 | Solar | 05_05_321W6 | 07/17/2020 |  | 187 | 66 | 121 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 646610 | 02343 | 7.6 | Solar | 05_05_106W81 | 10/18/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | PLAINVILLE | 725014 | 02762 | 5.76 | Solar | 05_05_311W3 | 10/10/2025 | 10/15/2025 | 2 | 0 | 2 | 10/16/2025 | 10/16/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTFORD | 305147 | 01886 | 7.6 | Solar | 05_07_2W1 | 08/12/2020 | 08/17/2020 | 2 | 0 | 2 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 | 08/12/2020 | 8/1/2021 | Y | EXP | 365 | 01/05/2021 | 01/26/2021 | 21 | 0 | 21 |  |  | 5/4/2021 | Connected |  | N
National Grid | ANDOVER | 574094 | 01845 | 2035 | Solar | 05_05_348W1 | 02/27/2024 | 06/06/2024 | 70 | 61 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2024 | 06/12/2024 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 5/24/2027 | N | STD | 497 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | METHUEN | 242048 | 01844 | 16 | Solar | 05_14_57L3 | 07/09/2019 | 07/23/2019 | 9 | 9 | 0 | 07/24/2019 | 07/24/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 11/11/2019 | N | EXP | 98 |  |  | 0 | 0 | 0 |  |  | 10/28/2019 | Connected |  | N
National Grid | WORCESTER | 176651 | 01605 | 524 | Solar | 05_14_71L3 | 02/17/2016 | 02/17/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2016 | 03/08/2016 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEBSTER | 644467 | 01570 | 3.8 | Solar | 05_14_8L2 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 | 10/02/2024 | 12/9/2025 | Y | EXP | 365 | 09/16/2025 | 09/15/2025 | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | MENDON | 640832 | 01756 | 7.6 | Solar | 05_01_24W1 | 09/17/2024 | 09/25/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  | 1/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2025 | Connected |  | N
National Grid | FALL RIVER | 177697 | 02720 | 3990 | Solar | 05_01_412L1 | 03/21/2017 | 03/21/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 04/24/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/27/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 293133 | 01752 | 8.64 | Solar | 05_05_321W6 | 06/17/2020 | 07/30/2020 | 30 | 28 | 2 | 07/31/2020 | 07/31/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | HOLBROOK | 649794 | 02343 | 7.6 | Solar | 05_05_106W81 | 10/25/2024 | 11/12/2024 | 8 | 2 | 6 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2025 | Connected |  | N
National Grid | PLAINVILLE | 726755 | 02762 | 15.2 | Solar | 05_05_311W3 | 10/15/2025 | 10/21/2025 | 4 | 0 | 4 | 10/22/2025 | 10/22/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | TYNGSBORO | 324728 | 01879 | 7.6 | Solar | 05_07_2W1 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 11/30/2020 | 7/30/2021 | Y | EXP | 365 | 04/27/2021 | 05/19/2021 | 22 | 0 | 22 |  |  | 7/15/2021 | Connected |  | N
National Grid | ANDOVER | 704423 | 01845 | 1900 | Solar | 05_05_348W1 | 02/27/2024 | 06/06/2024 | 70 | 61 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2024 | 06/12/2024 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 5/24/2027 | N | STD | 497 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LAWRENCE | 248827 | 01841 | 0 | Solar | 05_14_57L3 | 08/14/2019 | 08/19/2019 | 3 | 3 | 0 | 08/20/2019 | 08/20/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2019 |  | 9/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2020 | Connected |  | N
National Grid | WORCESTER | 177662 | 01606 | 249 | Solar | 05_14_71L3 | 11/13/2017 | 11/13/2017 | 15 | 5 | 10 | 12/06/2017 | 12/06/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 |  | 12/2/2019 | N | EXP | 711 |  |  | 0 | 0 | 0 |  |  | 12/16/2019 | Connected |  | N
National Grid | WEBSTER | 644598 | 01570 | 10 | Solar | 05_14_8L2 | 10/02/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/02/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | BLACKSTONE | 525277 | 01504 | 7.6 | Solar | 05_07_911W56 | 05/22/2023 | 05/25/2023 | 3 | 0 | 3 | 05/26/2023 | 05/26/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 178538 | 02720 | 7.6 | Solar | 05_01_412L1 | 01/25/2018 | 02/08/2018 | 9 | 0 | 9 | 02/08/2018 | 02/08/2018 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2018 |  | 1/31/2019 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | MARLBOROUGH | 297954 | 01752 | 0 | Other | 05_05_321W6 | 01/02/2021 | 01/28/2021 | 17 | 12 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2021 | 02/26/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 729535 | 02343 | 150 | Solar | 05_05_106W82 | 10/31/2025 | 12/03/2025 | 21 | 14 | 7 | 12/04/2025 | 12/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | FRANKLIN | 739918 | 02038 | 10 | Solar | 05_05_311W3 | 12/12/2025 | 12/17/2025 | 3 | 0 | 3 | 12/18/2025 | 12/18/2025 | 53 | 42 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | TYNGSBORO | 493719 | 01879 | 10 | Solar | 05_07_2W1 | 01/31/2023 | 02/07/2023 | 5 | 4 | 1 | 02/08/2023 | 02/08/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2023 |  | 3/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | ANDOVER | 297184 | 01845 | 10 | Solar | 05_05_348W1 | 08/13/2020 | 08/14/2020 | 1 | 1 | 0 | 08/17/2020 | 08/17/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 |  | 8/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LAWRENCE | 263166 | 01841 | 10 | Solar | 05_14_57L3 | 10/31/2019 | 11/01/2019 | 1 | 1 | 0 | 11/04/2019 | 11/04/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2019 |  | 2/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2020 | Connected |  | N
National Grid | WORCESTER | 378789 | 01606 | 100 | Solar | 05_14_71L3 | 09/03/2021 | 10/06/2021 | 22 | 12 | 10 |  |  | 35 | 4 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 09/03/2021 | 7/9/2023 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | WEBSTER | 648245 | 01570 | 5.76 | Solar | 05_14_8L2 | 10/30/2024 | 11/18/2024 | 5 | 0 | 5 | 11/19/2024 | 11/19/2024 | 25 | 0 | 25 | 01/15/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 2/21/2025 | 10/30/2024 | 2/26/2026 | Y | EXP | 365 | 08/20/2025 | 08/19/2025 | 0 | 0 | 0 |  |  | 9/12/2025 | Connected |  | N
National Grid | UXBRIDGE | 526795 | 01569 | 9.8 | Solar | 05_07_911W56 | 06/20/2023 | 06/22/2023 | 2 | 0 | 2 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 | 06/20/2023 | 8/4/2024 | Y | EXP | 365 | 10/03/2023 | 10/20/2023 | 18 | 0 | 18 |  |  | 4/22/2024 | Connected |  | N
National Grid | FALL RIVER | 184051 | 02720 | 2375 | Solar | 05_01_412L1 | 04/30/2018 | 04/30/2018 | 14 | 13 | 1 |  |  | 27 | 2 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 302294 | 01752 | 16.56 | Solar | 05_05_321W6 | 07/21/2020 | 09/14/2020 | 37 | 36 | 1 | 09/15/2020 | 09/15/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2020 |  | 9/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 189412 | 02343 | 740 | Solar | 05_05_106W82 | 08/08/2018 | 10/17/2018 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 11/15/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 750679 | 02038 | 30 | Solar | 05_05_311W3 | 02/16/2026 | 02/18/2026 | 2 | 0 | 2 | 02/19/2026 | 02/19/2026 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | DUNSTABLE | 494242 | 01827 | 10 | Solar | 05_07_2W1 | 02/07/2023 | 02/09/2023 | 2 | 0 | 2 | 02/10/2023 | 02/10/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2023 | Connected |  | N
National Grid | ANDOVER | 328096 | 01845 | 7.6 | Solar | 05_05_348W1 | 11/24/2020 | 12/14/2020 | 13 | 9 | 4 | 12/15/2020 | 12/15/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 3/2/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N
National Grid | LAWRENCE | 297374 | 01841 | 0 | Solar | 05_14_57L3 | 06/19/2020 | 06/22/2020 | 0 | 0 | 0 | 06/23/2020 | 06/23/2020 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | BROCKTON | 472543 | 02302 | 15.2 | Solar | 05_14_71L3 | 11/22/2022 | 11/28/2022 | 3 | 0 | 3 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2023 | Connected |  | N
National Grid | WEBSTER | 657055 | 01570 | 11.52 | Solar | 05_07_93W42 | 11/26/2024 | 12/30/2024 | 4 | 0 | 4 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 526606 | 01756 | 10 | Solar | 05_07_911W56 | 05/25/2023 | 06/01/2023 | 4 | 0 | 4 | 06/02/2023 | 06/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 | 05/25/2023 | 12/31/2024 | Y | EXP | 365 | 04/26/2024 | 05/14/2024 | 19 | 0 | 19 |  |  |  | Withdrawn |  | N
National Grid | FALL RIVER | 189710 | 02723 | 2000 | Solar | 05_01_412L1 | 07/16/2018 | 08/06/2018 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2018 | 11/30/2018 | 78 | 25 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 309606 | 01752 | 3.8 | Solar | 05_05_321W6 | 10/12/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 27 | 11 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/12/2020 | 12/11/2023 | Y | EXP | 365 | 04/14/2022 | 06/01/2022 | 49 | 0 | 49 |  |  | 11/13/2023 | Connected |  | N
National Grid | HOLBROOK | 203924 | 02343 | 10 | Solar | 05_05_106W82 | 01/10/2019 | 01/23/2019 | 7 | 0 | 7 | 01/24/2019 | 01/24/2019 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175946 | 02093 | 2.4 | Solar | 05_05_311W3 | 03/17/2015 | 03/17/2015 | 3 | 2 | 1 | 03/23/2015 | 03/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 |  | 7/17/2015 | N | EXP | 113 |  |  | 0 | 0 | 0 | 9/22/2016 | 9/22/2016 | 5/5/2017 | Connected |  | N
National Grid | WESTFORD | 512728 | 01886 | 6 | Solar | 05_07_2W1 | 04/11/2023 | 04/14/2023 | 3 | 0 | 3 | 04/18/2023 | 04/18/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ANDOVER | 328332 | 01845 | 15.2 | Solar | 05_05_348W1 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | METHUEN | 297469 | 01844 | 15.2 | Solar | 05_14_57L3 | 06/30/2020 | 07/06/2020 | 3 | 0 | 3 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 |  | 7/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2020 | Connected |  | N
National Grid | BROCKTON | 190889 | 02302 | 100 | Natural Gas | 05_09_1015W1 | 07/17/2018 | 08/29/2018 | 22 | 0 | 22 |  |  | 44 | 20 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2019 |  | 1/13/2023 | N | STD | 365 | 06/04/2021 | 09/08/2021 | 0 | 0 | 0 |  |  | 1/12/2022 | Connected |  | N
National Grid | WEBSTER | 676459 | 01570 | 15.2 | Solar | 05_07_93W42 | 03/10/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | UXBRIDGE | 557901 | 01569 | 9.216 | Solar | 05_07_911W56 | 09/28/2023 | 10/05/2023 | 6 | 3 | 3 | 10/06/2023 | 10/06/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2023 | 09/28/2023 | 12/13/2024 | Y | EXP | 365 | 01/08/2024 | 02/06/2024 | 30 | 0 | 30 |  |  | 4/19/2024 | Connected |  | N
National Grid | FALL RIVER | 202707 | 02723 | 10 | Solar | 05_01_412L1 | 12/06/2018 | 01/14/2019 | 25 | 20 | 5 | 01/15/2019 | 01/15/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2019 | 12/06/2018 | 10/30/2019 | Y | EXP | 28 | 06/26/2019 | 08/26/2019 | 61 | 0 | 61 |  |  | 9/16/2019 | Connected |  | N
National Grid | MARLBOROUGH | 315404 | 01752 | 0 | Other | 05_05_321W6 | 11/05/2020 | 11/13/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2020 | 12/07/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 220893 | 02343 | 489 | Solar | 05_05_106W82 | 04/19/2019 | 04/23/2019 | 1 | 0 | 1 | 04/24/2019 | 04/24/2019 | 10 | 0 | 10 | 05/23/2019 | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 06/11/2019 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176678 | 01752 | 6 | Solar | 05_05_311W3 | 01/04/2016 | 01/04/2016 | 0 | 0 | 0 | 01/06/2016 | 01/06/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2016 |  | 1/11/2017 | N | EXP | 348 |  |  | 0 | 0 | 0 | 7/26/2016 | 7/26/2016 | 8/23/2016 | Connected |  | N
National Grid | TYNGSBORO | 513638 | 01879 | 7.6 | Solar | 05_07_2W1 | 05/01/2023 | 05/19/2023 | 14 | 13 | 1 | 05/22/2023 | 05/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2023 | 05/01/2023 | 8/24/2024 | Y | EXP | 365 | 09/28/2023 | 10/09/2023 | 12 | 0 | 12 |  |  | 10/24/2023 | Connected |  | N
National Grid | ANDOVER | 376877 | 01845 | 15.2 | Solar | 05_05_348W1 | 08/19/2021 | 08/24/2021 | 3 | 3 | 0 | 08/25/2021 | 08/25/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 8/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 299279 | 02351 | 10 | Solar | 05_14_57L3 | 07/01/2020 | 07/07/2020 | 3 | 0 | 3 | 07/08/2020 | 07/08/2020 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 7/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | BROCKTON | 197015 | 02302 | 8980 | Solar | 05_09_1015W1 | 11/06/2018 | 11/08/2018 | 19 | 0 | 19 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 699908 | 01570 | 11.52 | Solar | 05_07_93W42 | 06/25/2025 | 07/15/2025 | 5 | 0 | 5 | 07/25/2025 | 07/25/2025 | 27 | 14 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 06/25/2025 | 9/15/2026 | Y | EXP | 365 | 11/25/2025 | 12/10/2025 | 16 | 0 | 16 |  |  | 12/23/2025 | Connected |  | N
National Grid | UXBRIDGE | 557158 | 01569 | 7.6 | Solar | 05_07_911W56 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 36 | 13 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 306367 | 02723 | 6 | Solar | 05_01_412L1 | 09/18/2020 | 09/21/2020 | 0 | 0 | 0 | 09/22/2020 | 09/22/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2020 |  | 9/20/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 340928 | 01752 | 9.36 | Solar | 05_05_321W6 | 02/06/2021 | 03/26/2021 | 33 | 32 | 1 | 03/29/2021 | 03/29/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2021 |  | 5/21/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2022 | Connected |  | N
National Grid | HOLBROOK | 337864 | 02343 | 7.6 | Solar | 05_05_106W82 | 02/22/2021 | 03/02/2021 | 5 | 0 | 5 | 03/03/2021 | 03/03/2021 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2021 | Connected |  | N
National Grid | MARLBOROUGH | 184521 | 01752 | 17.6 | Solar | 05_05_311W3 | 05/04/2018 | 05/04/2018 | 16 | 2 | 14 | 06/06/2018 | 06/06/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | WESTFORD | 519721 | 01886 | 7.6 | Solar | 05_07_2W1 | 04/24/2023 | 05/25/2023 | 24 | 22 | 2 | 05/26/2023 | 05/26/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2023 | 04/24/2023 | 7/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/22/2023 | Connected |  | N
National Grid | NORTH ADAMS | 475744 | 01247 | 18.846 | Solar | 05_05_348W1 | 12/13/2022 | 12/14/2022 | 1 | 0 | 1 | 12/15/2022 | 12/15/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2023 |  | 1/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2023 | Connected |  | N
National Grid | WHITMAN | 329231 | 02382 | 7.6 | Solar | 05_14_57L3 | 12/03/2020 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 308535 | 02302 | 2125 | Solar | 05_09_1015W1 | 09/30/2020 | 10/07/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2020 | 12/04/2020 | 38 | 21 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 673177 | 01570 | 44.6 | Solar | 05_07_93W43 | 02/20/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 39 | 20 | 19 | 06/02/2025 | 07/28/2025 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  | 07/28/2025 | 39 | 0 | 39 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | Y
National Grid | MENDON | 559201 | 01756 | 7.6 | Solar | 05_07_911W56 | 10/18/2023 | 10/19/2023 | 1 | 0 | 1 | 10/20/2023 | 10/20/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 10/18/2023 | 12/6/2024 | Y | EXP | 365 | 01/25/2024 | 02/16/2024 | 23 | 0 | 23 |  |  | 2/21/2024 | Connected |  | N
National Grid | FALL RIVER | 312153 | 02723 | 5.76 | Solar | 05_01_412L1 | 12/01/2020 | 12/03/2020 | 1 | 0 | 1 | 12/04/2020 | 12/04/2020 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/01/2020 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 370890 | 01752 | 10 | Solar | 05_05_321W6 | 08/10/2021 | 12/13/2021 | 17 | 15 | 2 | 09/03/2021 | 09/03/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 | 08/10/2021 | 7/10/2023 | Y | EXP | 365 | 03/02/2022 | 06/28/2022 | 119 | 0 | 119 |  |  | 7/18/2022 | Connected |  | N
National Grid | HOLBROOK | 379546 | 02343 | 10 | Solar | 05_05_106W82 | 09/09/2021 | 09/28/2021 | 4 | 3 | 1 | 09/29/2021 | 09/29/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2021 | 09/09/2021 | 1/3/2023 | Y | EXP | 365 | 12/04/2021 | 01/03/2022 | 31 | 0 | 31 |  |  | 2/5/2022 | Connected |  | N
National Grid | MARLBOROUGH | 190641 | 01752 | 11.4 | Solar | 05_05_311W3 | 07/13/2018 | 09/10/2018 | 23 | 9 | 14 | 09/11/2018 | 09/11/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 | 07/13/2018 | 10/10/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2019 | Connected |  | N
National Grid | WESTFORD | 530297 | 01886 | 18.85 | Solar | 05_07_2W1 | 06/05/2023 | 06/29/2023 | 17 | 16 | 1 | 06/30/2023 | 06/30/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/20/2023 | Connected |  | N
National Grid | FLORIDA | 661518 | 01247 | 5.76 | Solar | 05_05_348W3 | 12/26/2024 | 01/23/2025 | 8 | 3 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 335256 | 02351 | 250 | Solar | 05_14_57L3 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 347442 | 02302 | 2125 | Solar | 05_09_1015W1 | 04/20/2021 | 05/25/2021 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2021 | 09/01/2021 | 68 | 48 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 174721 | 01570 | 15.8 | Solar | 05_07_93W43 | 01/15/2014 | 01/15/2014 | 6 | 0 | 6 | 01/27/2014 | 01/27/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2014 |  | 3/31/2014 | N | EXP | 61 |  |  | 0 | 0 | 0 | 2/26/2014 | 2/26/2014 | 3/26/2014 | Connected |  | N
National Grid | UXBRIDGE | 529280 | 01569 | 9.28 | Solar | 05_07_911W56 | 06/05/2023 | 06/20/2023 | 11 | 10 | 1 | 06/21/2023 | 06/21/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 | 06/05/2023 | 7/20/2024 | Y | EXP | 365 | 08/01/2023 | 08/11/2023 | 11 | 0 | 11 |  |  | 10/10/2023 | Connected |  | N
National Grid | FALL RIVER | 365160 | 02723 | 15.6 | Solar | 05_01_412L1 | 06/21/2021 | 06/23/2021 | 2 | 0 | 2 | 06/24/2021 | 06/24/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2021 | 06/21/2021 | 11/5/2023 | Y | EXP | 365 | 07/15/2022 | 08/26/2022 | 43 | 0 | 43 |  |  | 12/7/2022 | Connected |  | N
National Grid | MARLBOROUGH | 372950 | 01752 | 3.8 | Solar | 05_05_321W6 | 07/29/2021 | 08/05/2021 | 6 | 3 | 3 | 08/06/2021 | 08/06/2021 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 8/4/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 460340 | 02343 | 5.51 | Solar | 05_05_106W82 | 09/27/2022 | 09/29/2022 | 3 | 1 | 2 | 09/30/2022 | 09/30/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/20/2023 | Connected |  | Y
National Grid | FRANKLIN | 193918 | 02038 | 6 | Solar | 05_05_311W3 | 08/20/2018 | 10/12/2018 | 27 | 24 | 3 | 10/15/2018 | 10/15/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2018 |  | 10/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2019 | Connected |  | N
National Grid | WESTFORD | 585200 | 01886 | 6.09 | Solar | 05_07_2W1 | 01/24/2024 | 01/30/2024 | 4 | 0 | 4 | 01/31/2024 | 01/31/2024 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2024 | 01/24/2024 | 3/9/2025 | Y | EXP | 365 | 04/18/2024 | 05/07/2024 | 20 | 0 | 20 |  |  | 5/14/2024 | Connected |  | N
National Grid | FLORIDA | 661826 | 01247 | 23 | Solar | 05_05_348W3 | 12/19/2024 | 01/07/2025 | 11 | 7 | 4 | 01/08/2025 | 01/08/2025 | 42 | 17 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | WHITMAN | 340473 | 02382 | 7.6 | Solar | 05_14_57L3 | 02/04/2021 | 02/05/2021 | 0 | 0 | 0 | 02/08/2021 | 02/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 |  | 6/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2021 | Connected |  | N
National Grid | BROCKTON | 426233 | 02302 | 5 | Solar | 05_09_1015W1 | 05/23/2022 | 05/31/2022 | 5 | 2 | 3 | 06/01/2022 | 06/01/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 175942 | 01570 | 22.6 | Solar | 05_07_93W43 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 | 01/29/2015 | 01/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2015 |  | 5/31/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 | 6/1/2016 | 6/1/2016 | 6/1/2016 | Connected |  | N
National Grid | MENDON | 543198 | 01756 | 6 | Solar | 05_07_911W56 | 07/27/2023 | 07/28/2023 | 1 | 0 | 1 | 07/31/2023 | 07/31/2023 | 30 | 10 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2023 | 07/27/2023 | 9/16/2024 | Y | EXP | 365 | 10/28/2023 | 11/14/2023 | 18 | 0 | 18 |  |  | 5/31/2024 | Connected |  | N
National Grid | FALL RIVER | 174331 | 02723 | 1500 | Solar | 05_09_508L2 | 01/18/2012 | 01/18/2012 | 224 | 0 | 224 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2013 | 03/29/2013 | 36 | 0 | 36 |  |  | 0 | 0 | 0 | 11/28/2016 | 11/28/2016 | 0 | 0 | 0 | 10/15/2014 | 01/18/2012 | 12/31/2016 | Y | STD | 88 | 10/18/2016 | 01/27/2017 | 68 | 0 | 68 |  |  | 5/1/2017 | Connected |  | N
National Grid | MARLBOROUGH | 374830 | 01752 | 15.2 | Solar | 05_05_321W6 | 08/09/2021 | 09/07/2021 | 20 | 19 | 1 | 09/08/2021 | 09/08/2021 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2021 |  | 11/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2022 | Connected |  | N
National Grid | HOLBROOK | 518145 | 02343 | 14.5 | Solar | 05_05_106W82 | 04/15/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2023 |  | 11/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2024 | Connected |  | N
National Grid | MARLBOROUGH | 194787 | 01752 | 7.6 | Solar | 05_05_311W3 | 08/30/2018 | 11/14/2018 | 29 | 25 | 4 | 11/15/2018 | 11/15/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 585093 | 01886 | 0 | Solar | 05_07_2W1 | 01/23/2024 | 01/24/2024 | 1 | 0 | 1 | 01/25/2024 | 01/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 4/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | FLORIDA | 691917 | 01247 | 150 | Solar | 05_05_348W5 | 05/15/2025 | 07/11/2025 | 38 | 28 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WHITMAN | 449402 | 02382 | 11.4 | Solar | 05_14_57L3 | 08/12/2022 | 08/15/2022 | 1 | 0 | 1 | 08/16/2022 | 08/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 599834 | 02302 | 5000 | Solar | 05_09_1015W1 | 04/26/2024 | 07/02/2024 | 45 | 35 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/03/2024 | 07/12/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEBSTER | 176335 | 01570 | 70 | Solar | 05_07_93W43 | 09/16/2015 | 09/16/2015 | 1 | 1 | 0 | 09/17/2015 | 09/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2015 |  | 9/21/2016 | N | EXP | 355 |  |  | 0 | 0 | 0 | 8/26/2016 | 8/26/2016 | 8/26/2016 | Connected |  | N
National Grid | MENDON | 550779 | 01756 | 6 | Solar | 05_07_911W56 | 08/30/2023 | 01/29/2024 | 101 | 84 | 17 | 01/30/2024 | 01/30/2024 | 43 | 29 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 177065 | 02723 | 230.4 | Solar | 05_09_508L2 | 03/20/2017 | 03/20/2017 | 16 | 16 | 0 | 04/12/2017 | 04/12/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2017 |  | 3/26/2018 | N | EXP | 322 |  |  | 0 | 0 | 0 | 1/8/2018 | 1/8/2018 | 1/8/2018 | Connected |  | N
National Grid | MARLBOROUGH | 411225 | 01752 | 3.8 | Solar | 05_05_321W6 | 02/09/2022 | 02/15/2022 | 5 | 4 | 1 | 02/16/2022 | 02/16/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2022 | Connected |  | N
National Grid | HOLBROOK | 529857 | 02343 | 3.8 | Solar | 05_05_106W82 | 07/06/2023 | 08/03/2023 | 21 | 20 | 1 | 08/04/2023 | 08/04/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/06/2023 | 11/26/2024 | Y | EXP | 365 | 10/24/2023 | 12/01/2023 | 39 | 0 | 39 |  |  | 12/4/2023 | Connected |  | N
National Grid | FRANKLIN | 201858 | 02038 | 10 | Solar | 05_05_311W3 | 11/21/2018 | 01/25/2019 | 19 | 19 | 0 | 01/28/2019 | 01/28/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 |  | 1/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/14/2020 | Connected |  | N
National Grid | WESTFORD | 586498 | 01886 | 10 | Solar | 05_07_2W1 | 02/06/2024 | 02/20/2024 | 10 | 7 | 3 | 02/21/2024 | 02/21/2024 | 144 | 101 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 695873 | 01247 | 15.2 | Solar | 05_05_348W5 | 06/03/2025 | 06/16/2025 | 8 | 5 | 3 | 06/17/2025 | 06/17/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANSON | 374358 | 02341 | 9.86 | Solar | 05_14_57L3 | 08/16/2021 | 08/17/2021 | 1 | 0 | 1 | 08/18/2021 | 08/18/2021 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N
National Grid | BROCKTON | 684896 | 02302 | 17.6 | Solar | 05_09_1015W1 | 04/14/2025 | 05/05/2025 | 7 | 4 | 3 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | LONGMEADOW | 177086 | 01028 | 720 | Solar | 05_07_93W43 | 10/18/2016 | 10/18/2016 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/24/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 553044 | 01756 | 6 | Solar | 05_07_911W56 | 09/05/2023 | 09/06/2023 | 1 | 0 | 1 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 324797 | 02723 | 2999.9 | Solar | 05_09_508L2 | 05/24/2021 | 07/16/2021 | 37 | 27 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2021 | 10/20/2021 | 66 | 46 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2023 | 05/24/2021 | 1/19/2026 | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | MARLBOROUGH | 426220 | 01752 | 3.8 | Solar | 05_05_321W6 | 06/15/2022 | 06/17/2022 | 2 | 0 | 2 | 06/21/2022 | 06/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2022 |  | 8/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2023 | Connected |  | Y
National Grid | HOLBROOK | 569078 | 02343 | 3.8 | Solar | 05_05_106W82 | 11/30/2023 | 12/05/2023 | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 233442 | 02038 | 400 | Solar | 05_05_311W3 | 04/15/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/15/2020 | 11/30/2021 | Y | STD | 12 | 09/08/2021 | 09/07/2021 | 0 | 0 | 0 |  |  | 11/24/2021 | Connected |  | N
National Grid | WESTFORD | 597249 | 01886 | 6.96 | Solar | 05_07_2W1 | 04/18/2024 | 05/10/2024 | 17 | 15 | 2 | 05/13/2024 | 05/13/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2024 | 04/18/2024 | 6/6/2025 | Y | EXP | 365 | 09/12/2024 | 10/15/2024 | 34 | 0 | 34 |  |  | 10/23/2024 | Connected |  | N
National Grid | FLORIDA | 706438 | 01247 | 15.2 | Solar | 05_05_348W5 | 07/22/2025 | 07/28/2025 | 4 | 0 | 4 | 07/29/2025 | 07/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WHITMAN | 388451 | 02382 | 9.8 | Solar | 05_14_57L3 | 11/05/2021 | 12/16/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 11/05/2021 | 7/7/2023 | Y | EXP | 365 | 06/14/2022 | 07/06/2022 | 22 | 0 | 22 |  |  | 9/9/2022 | Connected |  | N
National Grid | BROCKTON | 747515 | 02302 | 11.5 | Solar | 05_09_1015W2 | 01/26/2026 | 01/28/2026 | 4 | 0 | 4 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LONGMEADOW | 177685 | 01028 | 10 | Solar | 05_07_93W43 | 09/29/2017 | 09/29/2017 | 4 | 0 | 4 | 10/06/2017 | 10/06/2017 | 117 | 0 | 117 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 10/7/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 562350 | 01756 | 10 | Solar | 05_07_911W56 | 10/16/2023 | 10/17/2023 | 1 | 0 | 1 | 10/18/2023 | 10/18/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/16/2023 | 7/21/2025 | Y | EXP | 365 | 08/15/2024 | 09/09/2024 | 26 | 0 | 26 |  |  | 6/4/2025 | Connected |  | N
National Grid | FALL RIVER | 577364 | 02723 | 8.832 | Solar | 05_09_508L2 | 12/13/2023 | 01/23/2024 | 26 | 24 | 2 | 01/24/2024 | 01/24/2024 | 34 | 16 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 |  | 4/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2024 | Connected |  | N
National Grid | MARLBOROUGH | 461106 | 01752 | 13.8 | Solar | 05_05_321W6 | 09/26/2022 | 09/30/2022 | 4 | 0 | 4 | 10/03/2022 | 10/03/2022 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 1/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2023 | Connected |  | N
National Grid | HOLBROOK | 580036 | 02343 | 6 | Solar | 05_05_106W82 | 02/02/2024 | 02/06/2024 | 2 | 0 | 2 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/02/2024 | 4/17/2025 | Y | EXP | 365 | 07/17/2024 | 08/27/2024 | 42 | 0 | 42 |  |  | 10/18/2024 | Connected |  | N
National Grid | MARLBOROUGH | 233157 | 01752 | 166.6 | Solar | 05_05_311W3 | 03/25/2020 | 03/31/2020 | 3 | 0 | 3 |  |  | 47 | 30 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 03/25/2020 | 10/20/2021 | Y | STD | 112 | 08/20/2021 | 08/19/2021 | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | WESTFORD | 608256 | 01886 | 15.6 | Solar | 05_07_2W1 | 05/16/2024 | 05/17/2024 | 1 | 0 | 1 | 05/20/2024 | 05/20/2024 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 173748 | 01247 | 5 | Solar | 05_05_348W5 | 05/16/2018 | 05/16/2018 | 16 | 8 | 8 | 06/19/2018 | 06/19/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2018 |  | 7/26/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2018 | Connected |  | N
National Grid | WHITMAN | 396438 | 02382 | 7.6 | Solar | 05_14_57L3 | 11/18/2021 | 12/20/2021 | 22 | 19 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2022 |  | 3/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | BROCKTON | 175710 | 02302 | 499 | Solar | 05_09_1015W2 | 10/25/2014 | 10/25/2014 | 6 | 1 | 5 | 11/04/2014 | 11/04/2014 | 0 | 0 | 0 | 01/14/2015 | 02/24/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 02/24/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 2/24/2015 | 10/25/2014 | 1/19/2016 | Y | EXP | 329 | 07/19/2016 | 10/20/2016 | 65 | 0 | 65 |  |  | 11/14/2016 | Connected |  | N
National Grid | LONGMEADOW | 184675 | 01028 | 1328 | Solar | 05_07_93W43 | 05/09/2018 | 05/09/2018 | 55 | 52 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2018 | 08/30/2018 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2019 |  | 1/2/2021 | N | STD | 654 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 563942 | 01569 | 6 | Solar | 05_07_911W56 | 10/30/2023 | 11/01/2023 | 2 | 1 | 1 | 11/02/2023 | 11/02/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2023 |  | 12/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2024 | Connected |  | N
National Grid | FALL RIVER | 177865 | 02723 | 4000 | Solar | 05_09_508L4 | 06/14/2017 | 01/10/2018 | 144 | 144 | 0 |  |  | 50 | 35 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 | 06/14/2017 | 3/28/2026 | Y | STD | 53 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | MARLBOROUGH | 499131 | 01752 | 13.3 | Solar | 05_05_321W6 | 02/13/2023 | 02/14/2023 | 1 | 0 | 1 | 02/15/2023 | 02/15/2023 | 280 | 29 | 251 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 416537 | 02343 | 200 | Solar | 05_09_702W3 | 03/11/2022 | 03/25/2022 | 10 | 0 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | MARLBOROUGH | 249197 | 01752 | 7.6 | Solar | 05_05_311W3 | 10/03/2019 | 10/11/2019 | 6 | 5 | 1 | 10/15/2019 | 10/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 634810 | 01886 | 10 | Solar | 05_07_2W1 | 08/22/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 174372 | 01247 | 250 | Solar | 05_05_348W5 | 05/23/2012 | 05/23/2012 | 7 | 0 | 7 | 06/06/2012 | 06/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/1/2012 | N | EXP | 41 |  |  | 0 | 0 | 0 | 12/13/2012 | 12/13/2012 | 12/20/2012 | Connected |  | N
National Grid | WHITMAN | 402600 | 02382 | 15 | Solar | 05_14_57L3 | 12/31/2021 | 01/18/2022 | 10 | 6 | 4 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 7/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2022 | Connected |  | N
National Grid | BROCKTON | 175787 | 02302 | 995 | Solar | 05_09_1015W2 | 07/27/2015 | 07/27/2015 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2015 | 09/21/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 02/25/2016 | 05/27/2016 | 64 | 19 | 45 | 9/9/2016 | 07/27/2015 | 10/4/2017 | Y | STD | 39 |  |  | 0 | 0 | 0 | 1/2/2018 | 1/2/2018 | 1/2/2018 | Connected |  | N
National Grid | LONGMEADOW | 188219 | 01028 | 249.8 | Solar | 05_07_93W43 | 06/15/2018 | 06/15/2018 | 7 | 0 | 7 | 07/02/2018 | 07/02/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 568574 | 01569 | 6 | Solar | 05_07_911W56 | 11/08/2023 | 11/13/2023 | 2 | 0 | 2 | 11/14/2023 | 11/14/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FALL RIVER | 176083 | 02723 | 560 | Solar | 05_09_508L4 | 01/30/2015 | 01/30/2015 | 3 | 2 | 1 | 02/06/2015 | 02/06/2015 | 0 | 0 | 0 | 03/13/2017 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 | 01/30/2015 | 12/30/2016 | Y | EXP | 598 | 10/19/2016 | 11/28/2016 | 26 | 0 | 26 | 5/1/2017 | 5/1/2017 | 5/16/2017 | Connected |  | N
National Grid | MARLBOROUGH | 520510 | 01752 | 3.48 | Solar | 05_05_321W6 | 04/28/2023 | 05/02/2023 | 3 | 1 | 2 | 05/03/2023 | 05/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  | 6/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2023 | Connected |  | N
National Grid | HOLBROOK | 751550 | 02343 | 11.5 | Solar | 05_09_702W3 | 02/17/2026 | 02/20/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FRANKLIN | 287957 | 02038 | 200 | Solar | 05_05_311W3 | 04/16/2020 | 06/04/2020 | 32 | 25 | 7 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 04/16/2020 | 9/6/2022 | Y | STD | 3 | 05/10/2022 | 05/09/2022 | 0 | 0 | 0 |  |  | 5/19/2022 | Connected |  | N
National Grid | WESTFORD | 639943 | 01886 | 7.6 | Solar | 05_07_2W1 | 09/12/2024 | 01/29/2025 | 79 | 78 | 1 | 01/30/2025 | 01/30/2025 | 66 | 51 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 174668 | 01247 | 55.2 | Solar | 05_05_348W5 | 06/03/2013 | 06/03/2013 | 7 | 0 | 7 | 06/13/2013 | 06/13/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2013 |  | 9/2/2013 | N | EXP | 63 |  |  | 0 | 0 | 0 | 8/23/2013 | 8/23/2013 | 8/30/2013 | Connected |  | N
National Grid | HANSON | 421328 | 02341 | 0 | Solar | 05_14_57L3 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176163 | 02302 | 990 | Solar | 05_09_1015W2 | 02/06/2015 | 02/06/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/13/2015 | 03/12/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2015 | 02/06/2015 | 12/31/2016 | Y | STD | 529 | 02/21/2017 | 07/03/2017 | 92 | 0 | 92 | 7/20/2017 | 7/20/2017 | 7/20/2017 | Connected |  | N
National Grid | LONGMEADOW | 234837 | 01028 | 7.6 | Solar | 05_07_93W43 | 07/22/2019 | 07/24/2019 | 1 | 0 | 1 | 07/25/2019 | 07/25/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 8/3/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2019 | Connected |  | N
National Grid | MENDON | 570751 | 01756 | 7.6 | Solar | 05_07_911W56 | 11/16/2023 | 11/20/2023 | 2 | 0 | 2 | 11/21/2023 | 11/21/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 176522 | 01364 | 250 | Solar | 05_09_508L4 | 10/05/2015 | 10/05/2015 | 4 | 4 | 0 | 10/14/2015 | 10/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2015 |  | 10/12/2016 | N | EXP | 337 |  |  | 0 | 0 | 0 | 1/4/2016 | 1/4/2016 | 1/20/2016 | Connected |  | N
National Grid | MARLBOROUGH | 530593 | 01752 | 7.6 | Solar | 05_05_321W6 | 06/05/2023 | 06/07/2023 | 2 | 0 | 2 | 06/08/2023 | 06/08/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 06/05/2023 | 8/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | HOLBROOK | 174141 | 02343 | 52.8 | Solar | 05_09_702W3 | 04/13/2012 | 04/13/2012 | 8 | 0 | 8 | 04/27/2012 | 04/27/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 04/13/2012 | 6/1/2012 | Y | EXP | 194 |  |  | 0 | 0 | 0 | 4/29/2013 | 4/29/2013 | 4/29/2013 | Connected |  | N
National Grid | FRANKLIN | 297691 | 02038 | 66.6 | Solar | 05_05_311W3 | 06/30/2020 | 07/27/2020 | 18 | 18 | 0 | 07/28/2020 | 07/28/2020 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2021 | Connected |  | N
National Grid | TYNGSBORO | 642300 | 01879 | 7.6 | Solar | 05_07_2W1 | 09/30/2024 | 10/25/2024 | 4 | 2 | 2 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 178800 | 01247 | 20.16 | Solar | 05_05_348W5 | 02/22/2018 | 02/22/2018 | 29 | 29 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 460840 | 02382 | 0 | Solar | 05_14_57L3 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176318 | 02302 | 497 | Solar | 05_09_1015W2 | 05/11/2015 | 05/11/2015 | 0 | 0 | 0 | 05/12/2015 | 05/12/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 239824 | 01028 | 7.6 | Solar | 05_07_93W43 | 07/24/2019 | 10/03/2019 | 50 | 47 | 3 | 10/04/2019 | 10/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 574093 | 01504 | 9.6 | Solar | 05_07_911W56 | 12/19/2023 | 12/20/2023 | 1 | 1 | 0 | 12/21/2023 | 12/21/2023 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 177660 | 01331 | 15.2 | Solar | 05_09_508L4 | 11/13/2017 | 11/13/2017 | 50 | 50 | 0 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 11/19/2018 | N | EXP | 294 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 543563 | 01752 | 8.7 | Solar | 05_05_321W6 | 08/29/2023 | 09/13/2023 | 11 | 9 | 2 | 09/14/2023 | 09/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2023 | 08/29/2023 | 11/20/2024 | Y | EXP | 365 | 12/13/2023 | 04/01/2024 | 111 | 3 | 108 |  |  | 4/6/2024 | Connected |  | N
National Grid | HOLBROOK | 174501 | 02343 | 230 | Hydro | 05_09_702W3 | 05/08/2009 | 05/08/2009 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2010 |  | 10/31/2012 | N | STD | 93 |  |  | 0 | 0 | 0 | 10/22/2012 | 10/22/2012 | 10/22/2012 | Connected |  | N
National Grid | FRANKLIN | 311908 | 02038 | 10 | Solar | 05_05_311W3 | 09/10/2020 | 09/11/2020 | 0 | 0 | 0 | 09/14/2020 | 09/14/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2020 |  | 9/10/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTFORD | 646480 | 01886 | 10 | Solar | 05_07_2W1 | 10/24/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 | 10/24/2024 | 1/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 187501 | 01247 | 2500 | Solar | 05_05_348W5 | 06/11/2018 | 06/11/2018 | 39 | 37 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 09/21/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 480047 | 02382 | 15.2 | Solar | 05_14_57L3 | 01/13/2023 | 12/05/2022 | 2 | 0 | 2 | 01/19/2023 | 01/19/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 2/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/1/2023 | Connected |  | N
National Grid | BROCKTON | 177617 | 02302 | 10 | Solar | 05_09_1015W2 | 11/07/2017 | 11/07/2017 | 11 | 0 | 11 | 11/27/2017 | 11/27/2017 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/13/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 351890 | 01028 | 7.6 | Solar | 05_07_93W43 | 07/12/2021 | 08/10/2021 | 22 | 21 | 1 | 08/11/2021 | 08/11/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2021 |  | 1/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2022 | Connected |  | N
National Grid | BLACKSTONE | 582602 | 01504 | 13.44 | Solar | 05_07_911W56 | 01/18/2024 | 01/25/2024 | 6 | 3 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 178041 | 01364 | 17.6 | Solar | 05_09_508L4 | 05/01/2017 | 05/01/2017 | 13 | 13 | 0 | 05/18/2017 | 05/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 5/6/2018 | N | EXP | 349 |  |  | 0 | 0 | 0 | 8/9/2017 | 8/9/2017 | 8/9/2017 | Connected |  | N
National Grid | MARLBOROUGH | 555534 | 01752 | 0 | Solar | 05_05_321W6 | 09/14/2023 | 09/18/2023 | 2 | 0 | 2 | 09/19/2023 | 09/19/2023 | 117 | 28 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 174688 | 02343 | 2000 | Solar | 05_09_702W3 | 04/11/2011 | 04/11/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2011 | 10/06/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 06/28/2013 | 09/10/2013 | 50 | 0 | 50 | 8/28/2013 | 8/28/2013 | 9/6/2013 | Connected |  | N
National Grid | FRANKLIN | 328441 | 02038 | 10 | Solar | 05_05_311W3 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2021 |  | 11/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2021 | Connected |  | N
National Grid | WESTFORD | 648675 | 01886 | 5.76 | Solar | 05_07_2W1 | 10/22/2024 | 11/12/2024 | 5 | 0 | 5 | 11/13/2024 | 11/13/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 324729 | 01247 | 15.36 | Solar | 05_05_348W5 | 11/10/2020 | 11/19/2020 | 6 | 3 | 3 | 11/20/2020 | 11/20/2020 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 |  | 11/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2021 | Connected |  | N
National Grid | WHITMAN | 620837 | 02382 | 4.886 | Solar | 05_12_17J6 | 06/26/2024 | 07/11/2024 | 3 | 1 | 2 | 07/12/2024 | 07/12/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/26/2024 | 8/6/2025 | Y | EXP | 365 | 08/30/2024 | 02/12/2025 | 88 | 0 | 88 |  |  | 11/26/2024 | Connected |  | N
National Grid | BROCKTON | 177699 | 02302 | 3000 | Solar | 05_09_1015W2 | 03/21/2017 | 03/21/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/04/2017 | 05/10/2017 | 25 | 12 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 |  | 9/7/2020 | N | STD | 657 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 409784 | 01028 | 7.6 | Solar | 05_07_93W43 | 02/02/2022 | 02/17/2022 | 8 | 0 | 8 | 03/31/2022 | 03/31/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 583692 | 01756 | 7.6 | Solar | 05_07_911W56 | 01/19/2024 | 02/02/2024 | 10 | 8 | 2 | 02/05/2024 | 02/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 | 01/19/2024 | 3/15/2025 | Y | EXP | 365 | 04/17/2024 | 05/14/2024 | 28 | 0 | 28 |  |  | 5/17/2024 | Connected |  | N
National Grid | ATHOL | 178287 | 01331 | 376.6 | Solar | 05_09_508L4 | 03/28/2018 | 03/28/2018 | 16 | 15 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/3/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 561181 | 01752 | 3.8 | Solar | 05_05_321W6 | 10/13/2023 | 10/17/2023 | 2 | 0 | 2 | 10/18/2023 | 10/18/2023 | 21 | 3 | 18 | 12/05/2023 | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  | 01/17/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 2/14/2025 | N | EXP | 365 | 03/13/2024 | 03/28/2024 | 16 | 0 | 16 |  |  | 5/17/2024 | Connected |  | N
National Grid | HOLBROOK | 174687 | 02343 | 1000 | Solar | 05_09_702W3 | 04/11/2011 | 04/11/2011 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2011 | 10/06/2011 | 74 | 0 | 74 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2012 | 04/11/2011 | 12/31/2012 | Y | STD | 278 | 06/28/2013 | 09/10/2013 | 50 | 0 | 50 | 8/28/2013 | 8/28/2013 | 9/6/2013 | Connected |  | N
National Grid | FRANKLIN | 333111 | 02038 | 5.76 | Solar | 05_05_311W3 | 03/22/2021 | 03/24/2021 | 1 | 1 | 0 | 03/25/2021 | 03/25/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 4/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2021 | Connected |  | N
National Grid | WESTFORD | 654539 | 01886 | 3.8 | Solar | 05_07_2W1 | 11/18/2024 | 12/20/2024 | 3 | 0 | 3 | 12/23/2024 | 12/23/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 339532 | 01247 | 7.6 | Solar | 05_05_348W5 | 01/29/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2021 | Connected |  | N
National Grid | WHITMAN | 667327 | 02382 | 9.12 | Solar | 05_12_17J6 | 01/22/2025 | 02/18/2025 | 8 | 3 | 5 | 02/19/2025 | 02/19/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | BROCKTON | 177690 | 02302 | 1230 | Solar | 05_09_1015W2 | 10/03/2017 | 10/03/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 | 11/01/2017 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 414943 | 01028 | 0 | Solar | 05_07_93W43 | 03/01/2022 | 03/08/2022 | 6 | 5 | 1 | 03/09/2022 | 03/09/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2022 |  | 5/15/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 590773 | 01756 | 6 | Solar | 05_07_911W56 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | N
National Grid | ORANGE | 178440 | 01364 | 7.6 | Solar | 05_09_508L4 | 04/02/2018 | 04/02/2018 | 4 | 0 | 4 | 04/09/2018 | 04/09/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2018 |  | 4/15/2019 | N | EXP | 326 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 572760 | 01752 | 6.08 | Solar | 05_05_321W6 | 11/21/2023 | 11/29/2023 | 5 | 0 | 5 | 11/30/2023 | 11/30/2023 | 65 | 45 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2024 |  | 4/10/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 175659 | 02343 | 600 | Solar | 05_09_702W3 | 05/22/2014 | 05/22/2014 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2014 | 07/08/2014 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2015 | 05/22/2014 | 11/28/2016 | Y | STD | 626 | 01/22/2016 | 01/22/2016 | 0 | 0 | 0 | 12/6/2016 | 12/6/2016 | 12/29/2016 | Connected |  | N
National Grid | FRANKLIN | 416970 | 02038 | 19 | Solar | 05_05_311W3 | 03/10/2022 | 03/14/2022 | 2 | 0 | 2 | 03/15/2022 | 03/15/2022 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2022 | 03/10/2022 | 6/3/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2022 | Connected |  | N
National Grid | MEDFORD | 658902 | 02155 | 3.8 | Solar | 05_07_2W1 | 12/06/2024 | 12/17/2024 | 5 | 0 | 5 | 12/18/2024 | 12/18/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 | 12/06/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | NORTH ADAMS | 371812 | 01247 | 7.6 | Solar | 05_05_348W5 | 07/23/2021 | 07/28/2021 | 4 | 3 | 1 | 07/29/2021 | 07/29/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2021 |  | 10/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | N
National Grid | HANSON | 175464 | 02341 | 881.6 | Solar | 05_12_18J3 | 09/22/2014 | 09/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2014 | 10/29/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2015 | 09/22/2014 | 1/1/2016 | Y | STD | 297 | 11/04/2015 | 05/19/2016 | 133 | 0 | 133 | 5/6/2016 | 5/6/2016 | 5/6/2016 | Connected |  | N
National Grid | BROCKTON | 178400 | 02302 | 248 | Solar | 05_09_1015W2 | 04/02/2018 | 04/02/2018 | 4 | 3 | 1 | 04/06/2018 | 04/06/2018 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 04/02/2018 | 4/28/2021 | Y | EXP | 53 | 02/18/2021 | 03/19/2021 | 0 | 0 | 0 |  |  | 4/26/2021 | Connected |  | N
National Grid | LONGMEADOW | 416681 | 01028 | 15.2 | Solar | 05_07_93W43 | 03/09/2022 | 03/10/2022 | 1 | 0 | 1 | 03/11/2022 | 03/11/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UXBRIDGE | 595605 | 01569 | 10 | Solar | 05_07_911W56 | 03/13/2024 | 03/19/2024 | 4 | 0 | 4 | 03/20/2024 | 03/20/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/3/2024 | Connected |  | N
National Grid | ORANGE | 178630 | 01364 | 233.1 | Solar | 05_09_508L4 | 03/15/2018 | 03/15/2018 | 2 | 2 | 0 | 03/21/2018 | 03/21/2018 | 41 | 0 | 41 | 07/30/2018 | 01/18/2019 | 118 | 6 | 112 |  |  | 0 | 0 | 0 |  | 01/18/2019 | 118 | 6 | 112 |  |  | 0 | 0 | 0 | 11/28/2018 | 03/15/2018 | 12/21/2020 | Y | EXP | 581 | 06/30/2020 | 11/04/2020 | 128 | 5 | 123 |  |  | 12/21/2020 | Connected |  | N
National Grid | MARLBOROUGH | 586359 | 01752 | 11.4 | Solar | 05_05_321W6 | 02/20/2024 |  | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 175734 | 02343 | 576 | Solar | 05_09_702W3 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/19/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2015 | 08/11/2014 | 1/31/2018 | Y | STD | 116 |  |  | 0 | 0 | 0 | 4/4/2018 | 4/4/2018 | 5/31/2018 | Connected |  | N
National Grid | MARLBOROUGH | 491445 | 01752 | 15.2 | Solar | 05_05_311W3 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 47 | 25 | 22 | 04/25/2023 | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 5/16/2023 |  | 8/16/2024 | N | EXP | 365 | 07/26/2023 | 08/10/2023 | 16 | 0 | 16 |  |  | 10/16/2023 | Connected |  | Y
National Grid | MEDFORD | 660855 | 02155 | 10 | Solar | 05_07_2W1 | 12/16/2024 |  | 65 | 65 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 421254 | 01247 | 11.6 | Solar | 05_05_348W5 | 04/04/2022 | 04/05/2022 | 1 | 0 | 1 | 04/06/2022 | 04/06/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 | 04/04/2022 | 5/19/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2022 | Connected |  | N
National Grid | ABINGTON | 177673 | 02351 | 100 | Solar | 05_12_18J3 | 07/20/2017 | 07/20/2017 | 23 | 19 | 4 | 08/23/2017 | 08/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2017 |  | 7/26/2018 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 11/9/2018 | Connected |  | N
National Grid | BROCKTON | 339952 | 02302 | 7.6 | Solar | 05_09_1015W2 | 03/05/2021 | 03/10/2021 | 2 | 0 | 2 | 03/11/2021 | 03/11/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 4/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 427434 | 01028 | 0 | Solar | 05_07_93W43 | 04/29/2022 | 07/19/2022 | 54 | 51 | 3 | 07/20/2022 | 07/20/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 |  | 8/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2022 | Connected |  | N
National Grid | MENDON | 596891 | 01756 | 9.8 | Solar | 05_07_911W56 | 03/21/2024 | 04/12/2024 | 16 | 12 | 4 | 04/16/2024 | 04/16/2024 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 | 03/21/2024 | 7/10/2025 | Y | EXP | 365 | 08/21/2024 | 09/18/2024 | 29 | 0 | 29 |  |  | 11/7/2024 | Connected |  | N
National Grid | ATHOL | 178629 | 01331 | 350 | Solar | 05_09_508L4 | 03/15/2018 | 03/15/2018 | 1 | 1 | 0 | 03/20/2018 | 03/20/2018 | 42 | 0 | 42 | 08/22/2018 | 10/11/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  | 10/11/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 3/2/2022 | N | EXP | 77 |  |  | 0 | 0 | 0 |  |  | 12/30/2021 | Connected |  | N
National Grid | MARLBOROUGH | 613120 | 01752 | 3.8 | Solar | 05_05_321W6 | 05/23/2024 | 07/02/2024 | 9 | 6 | 3 | 07/03/2024 | 07/03/2024 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 | 05/23/2024 | 8/22/2025 | Y | EXP | 365 | 11/13/2024 | 11/18/2024 | 6 | 0 | 6 |  |  | 12/2/2024 | Connected |  | N
National Grid | HOLBROOK | 175790 | 02343 | 112 | Solar | 05_09_702W3 | 09/18/2015 | 09/18/2015 | 2 | 2 | 0 | 09/22/2015 | 09/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2015 |  | 9/23/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 4/15/2016 | Connected |  | N
National Grid | FRANKLIN | 503948 | 02038 | 10 | Solar | 05_05_311W3 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 8/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/30/2023 | Connected |  | N
National Grid | BEVERLY | 664192 | 01915 | 15.2 | Solar | 05_07_2W1 | 02/17/2025 |  | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 432298 | 01247 | 10 | Solar | 05_05_348W5 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 | 8/5/2024 | Y | EXP | 365 | 01/07/2023 | 08/03/2023 | 209 | 0 | 209 |  |  | 8/16/2023 | Connected |  | N
National Grid | WHITMAN | 177609 | 02382 | 92 | Solar | 05_12_18J4 | 09/21/2017 | 09/21/2017 | 6 | 5 | 1 | 09/29/2017 | 09/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2017 |  | 9/26/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/18/2017 | 12/18/2017 | 12/29/2017 | Connected |  | N
National Grid | BROCKTON | 562359 | 02301 | 27.3 | Solar | 05_09_1015W2 | 10/19/2023 | 10/20/2023 | 1 | 0 | 1 | 10/23/2023 | 10/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 1/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N
National Grid | LONGMEADOW | 436781 | 01028 | 7.6 | Solar | 05_07_93W43 | 07/05/2022 | 07/06/2022 | 1 | 0 | 1 | 07/07/2022 | 07/07/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2022 | 07/05/2022 | 9/7/2023 | Y | EXP | 365 | 10/12/2022 | 10/26/2022 | 15 | 0 | 15 |  |  | 1/30/2023 | Connected |  | N
National Grid | BLACKSTONE | 596006 | 01504 | 13.05 | Solar | 05_07_911W56 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2024 |  | 4/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2024 | Connected |  | N
National Grid | NEW SALEM | 200188 | 01355 | 376.6 | Solar | 05_09_508L4 | 11/06/2018 | 11/20/2018 | 9 | 8 | 1 | 11/21/2018 | 11/21/2018 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 629015 | 01752 | 23 | Solar | 05_05_321W6 | 07/31/2024 | 08/02/2024 | 2 | 0 | 2 | 08/05/2024 | 08/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2024 | Connected |  | N
National Grid | HOLBROOK | 175865 | 02343 | 1000 | Solar | 05_09_702W3 | 09/22/2015 | 09/22/2015 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2015 | 11/02/2015 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/28/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 559734 | 01752 | 400 | Solar | 05_05_311W3 | 10/12/2023 | 12/08/2023 | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 | 01/26/2024 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 664754 | 01915 | 6.96 | Solar | 05_07_2W1 | 01/09/2025 | 01/14/2025 | 4 | 3 | 1 | 01/15/2025 | 01/15/2025 | 37 | 13 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | NORTH ADAMS | 536018 | 01247 | 150 | Solar | 05_05_348W5 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/20/2023 | 38 | 18 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 177981 | 02382 | 128 | Solar | 05_12_18J4 | 08/24/2017 | 08/24/2017 | 29 | 29 | 0 | 10/09/2017 | 10/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2017 |  | 9/2/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 | 1/25/2018 | 1/25/2018 | 1/25/2018 | Connected |  | N
National Grid | BROCKTON | 632384 | 02302 | 996 | Solar | 05_09_1015W2 | 09/06/2024 | 10/31/2024 | 39 | 29 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/01/2024 | 01/03/2025 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 471854 | 01028 | 0 | Other | 05_07_93W43 | 04/19/2023 | 05/18/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/19/2023 | 06/21/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 600594 | 01569 | 7.6 | Solar | 05_07_911W56 | 03/29/2024 | 05/02/2024 | 23 | 21 | 2 | 05/03/2024 | 05/03/2024 | 46 | 27 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2024 |  | 8/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | ORANGE | 329328 | 01364 | 10 | Solar | 05_09_508L4 | 12/02/2020 | 12/08/2020 | 3 | 0 | 3 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2021 | Connected |  | N
National Grid | MARLBOROUGH | 632634 | 01752 | 9.5 | Solar | 05_05_321W6 | 08/14/2024 | 08/28/2024 | 10 | 7 | 3 | 08/29/2024 | 08/29/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2024 |  | 9/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | HOLBROOK | 176294 | 02343 | 2000 | Solar | 05_09_702W3 | 09/09/2015 | 09/09/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2015 | 10/19/2015 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/15/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 528910 | 02038 | 360 | Solar | 05_05_311W3 | 09/29/2023 | 10/30/2023 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 12/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 683806 | 01915 | 4998 | Other | 05_07_2W1 | 10/16/2025 | 12/04/2025 | 31 | 24 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/05/2025 | 12/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 570717 | 01247 | 0 | Solar | 05_05_348W5 | 11/13/2023 | 12/05/2023 | 6 | 2 | 4 | 12/06/2023 | 12/06/2023 | 43 | 22 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/4/2024 | Connected |  | N
National Grid | HANSON | 185017 | 02341 | 458 | Solar | 05_12_18J4 | 09/21/2018 | 10/01/2018 | 0 | 0 | 0 | 10/02/2018 | 10/02/2018 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 |  | 8/31/2020 | N | EXP | 368 |  |  | 0 | 0 | 0 |  |  | 8/27/2020 | Connected |  | N
National Grid | BROCKTON | 647947 | 02302 | 3.8 | Solar | 05_09_1015W2 | 10/17/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 42 | 18 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/17/2024 | 2/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | LONGMEADOW | 577969 | 01028 | 9.5 | Solar | 05_07_93W43 | 01/24/2024 | 01/26/2024 | 2 | 0 | 2 | 01/29/2024 | 01/29/2024 | 67 | 45 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/20/2024 | Connected |  | N
National Grid | UXBRIDGE | 603373 | 01569 | 3.8 | Solar | 05_07_911W56 | 04/15/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 329634 | 01364 | 15.2 | Solar | 05_09_508L4 | 12/04/2020 | 12/10/2020 | 3 | 0 | 3 | 12/11/2020 | 12/11/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 3/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 650687 | 01752 | 10 | Solar | 05_05_321W6 | 11/11/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 2/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2025 | Connected |  | N
National Grid | HOLBROOK | 176800 | 02343 | 288 | Solar | 05_09_702W3 | 02/25/2016 | 02/25/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 | 07/01/2016 | 08/03/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  | 08/03/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 | 3/13/2017 |  | 6/29/2018 | N | EXP | 473 |  |  | 0 | 0 | 0 | 12/7/2017 | 12/7/2017 | 12/7/2017 | Connected |  | N
National Grid | FRANKLIN | 569808 | 02038 | 6 | Solar | 05_05_311W3 | 11/20/2023 | 11/30/2023 | 8 | 4 | 4 | 12/01/2023 | 12/01/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 | 11/20/2023 | 2/4/2026 | Y | EXP | 73 | 07/25/2024 | 09/12/2024 | 50 | 0 | 50 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 683462 | 01915 | 13.8 | Solar | 05_07_2W1 | 04/07/2025 | 05/15/2025 | 1 | 0 | 1 | 05/16/2025 | 05/16/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTH ADAMS | 579418 | 01247 | 9.984 | Solar | 05_05_348W5 | 02/05/2024 | 02/06/2024 | 2 | 1 | 1 | 02/07/2024 | 02/07/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/30/2024 | Connected |  | N
National Grid | ABINGTON | 177568 | 02351 | 15.2 | Solar | 05_12_18L1 | 09/14/2017 | 09/14/2017 | 9 | 9 | 0 | 09/27/2017 | 09/27/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/19/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 692348 | 02302 | 13.36 | Solar | 05_09_1015W2 | 05/16/2025 | 06/17/2025 | 4 | 0 | 4 | 06/30/2025 | 06/30/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 05/16/2025 | 9/4/2026 | Y | EXP | 365 | 11/14/2025 | 11/26/2025 | 13 | 0 | 13 |  |  | 1/29/2026 | Connected |  | N
National Grid | LONGMEADOW | 580263 | 01028 | 9.984 | Solar | 05_07_93W43 | 01/11/2024 | 02/16/2024 | 26 | 25 | 1 | 02/20/2024 | 02/20/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2024 | Connected |  | N
National Grid | UXBRIDGE | 606521 | 01569 | 6 | Solar | 05_07_911W56 | 04/26/2024 | 05/08/2024 | 2 | 0 | 2 | 05/09/2024 | 05/09/2024 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2024 | 04/26/2024 | 7/11/2025 | Y | EXP | 365 | 08/27/2024 | 10/16/2024 | 51 | 0 | 51 |  |  | 10/22/2024 | Connected |  | N
National Grid | NEW SALEM | 338971 | 01364 | 10 | Solar | 05_09_508L4 | 01/27/2021 | 02/17/2021 | 13 | 13 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 01/27/2021 | 11/24/2022 | Y | EXP | 365 | 09/14/2021 | 11/22/2021 | 70 | 4 | 66 |  |  | 1/26/2022 | Connected |  | N
National Grid | MARLBOROUGH | 654792 | 01752 | 7.6 | Solar | 05_05_321W6 | 12/06/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 12/06/2024 | 2/24/2026 | Y | EXP | 365 | 02/25/2025 | 03/18/2025 | 22 | 0 | 22 |  |  | 4/3/2025 | Connected |  | N
National Grid | HOLBROOK | 176868 | 02343 | 499 | Solar | 05_09_702W3 | 03/01/2016 | 03/01/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2016 | 05/12/2016 | 48 | 33 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/7/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 570780 | 02038 | 10 | Solar | 05_05_311W3 | 11/20/2023 | 11/21/2023 | 1 | 0 | 1 | 11/22/2023 | 11/22/2023 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 | 11/20/2023 | 4/18/2025 | Y | EXP | 365 | 06/08/2024 | 09/03/2024 | 88 | 0 | 88 |  |  | 11/2/2024 | Connected |  | N
National Grid | BEVERLY | 688473 | 01915 | 10 | Solar | 05_07_2W1 | 05/02/2025 | 05/19/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | NORTH ADAMS | 610518 | 01247 | 3.8 | Solar | 05_05_348W5 | 05/14/2024 | 05/20/2024 | 1 | 0 | 1 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WHITMAN | 177563 | 02382 | 10 | Solar | 05_12_18L1 | 07/14/2017 | 07/14/2017 | 9 | 0 | 9 | 01/03/2018 | 01/03/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2018 |  | 9/28/2018 | N | EXP | 245 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174215 | 02302 | 75 | Natural Gas | 05_09_1018K1 | 11/22/2011 | 11/22/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 4/1/2012 | N | EXP | 255 |  |  | 0 | 0 | 0 | 10/2/2012 | 10/2/2012 | 12/3/2013 | Connected |  | N
National Grid | LONGMEADOW | 655884 | 01028 | 8 | Solar | 05_07_93W43 | 11/21/2024 | 12/02/2024 | 3 | 1 | 2 | 12/03/2024 | 12/03/2024 | 25 | 0 | 25 | 02/03/2025 | 02/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  | 02/06/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | MENDON | 606150 | 01756 | 5.76 | Solar | 05_07_911W56 | 04/23/2024 | 05/01/2024 | 4 | 0 | 4 | 05/02/2024 | 05/02/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 344217 | 01364 | 11.4 | Solar | 05_09_508L4 | 02/26/2021 | 03/11/2021 | 8 | 8 | 0 | 03/12/2021 | 03/12/2021 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  | 7/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 666187 | 01752 | 15.2 | Solar | 05_05_321W6 | 01/16/2025 | 01/31/2025 | 10 | 6 | 4 | 02/03/2025 | 02/03/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/28/2025 | Connected |  | N
National Grid | HOLBROOK | 177067 | 02343 | 3276 | Solar | 05_09_702W3 | 03/20/2017 | 03/27/2017 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/27/2017 | 04/07/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2017 | 03/20/2017 | 3/5/2020 | Y | STD | 79 | 04/09/2019 | 06/06/2019 | 58 | 0 | 58 |  |  | 3/5/2020 | Connected |  | N
National Grid | FRANKLIN | 584824 | 02038 | 7.6 | Solar | 05_05_311W3 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 699400 | 01915 | 7.6 | Solar | 05_07_2W1 | 06/18/2025 | 07/03/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 612595 | 01247 | 11.5 | Solar | 05_05_348W5 | 05/21/2024 | 06/14/2024 | 17 | 16 | 1 | 06/17/2024 | 06/17/2024 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | WHITMAN | 178337 | 02382 |  | Solar | 05_12_18L1 | 11/17/2017 | 11/17/2017 | 93 | 92 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/25/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 174343 | 02302 | 2000 | Solar | 05_09_1018K1 | 07/24/2012 | 07/24/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/06/2012 | 10/17/2012 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2014 | 07/24/2012 | 12/31/2016 | Y | STD | 19 | 09/18/2015 | 12/17/2015 | 61 | 0 | 61 | 12/14/2015 | 12/14/2015 | 12/14/2015 | Connected |  | N
National Grid | LONGMEADOW | 658277 | 01028 | 9.57 | Solar | 05_07_93W43 | 12/04/2024 | 01/07/2025 | 20 | 17 | 3 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | MENDON | 610859 | 01756 | 3.8 | Solar | 05_07_911W56 | 05/14/2024 | 05/22/2024 | 1 | 0 | 1 | 05/23/2024 | 05/23/2024 | 15 | 3 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/14/2024 | 6/28/2025 | Y | EXP | 365 | 08/27/2024 | 09/30/2024 | 35 | 0 | 35 |  |  | 10/4/2024 | Connected |  | N
National Grid | ORANGE | 375923 | 01364 | 13.44 | Solar | 05_09_508L4 | 08/14/2021 | 08/18/2021 | 3 | 0 | 3 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 10/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2021 | Connected |  | N
National Grid | MARLBOROUGH | 676082 | 01752 | 5.76 | Solar | 05_05_321W6 | 03/14/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 36 | 17 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/14/2025 | 6/3/2026 | Y | EXP | 365 | 07/04/2025 | 10/20/2025 | 109 | 0 | 109 |  |  | 10/28/2025 | Connected |  | N
National Grid | HOLBROOK | 177395 | 02343 | 995 | Landfill Gas | 05_09_702W3 | 02/21/2017 | 02/21/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/24/2017 | 03/09/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/26/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 603043 | 02038 | 10 | Solar | 05_05_311W3 | 04/17/2024 | 04/22/2024 | 3 | 0 | 3 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 713260 | 01915 | 10 | Solar | 05_07_2W1 | 08/19/2025 | 09/08/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 11/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | LANESBOROUGH | 656260 | 01237 | 4.06 | Solar | 05_05_348W5 | 11/22/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/22/2024 | 3/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | HANSON | 178641 | 02341 | 15.2 | Solar | 05_12_18L1 | 04/10/2018 | 04/10/2018 | 27 | 7 | 20 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/15/2019 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 703664 | 02302 | 18.24 | Solar | 05_09_1019W1 | 07/09/2025 | 07/11/2025 | 2 | 0 | 2 | 07/14/2025 | 07/14/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 8/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LONGMEADOW | 662902 | 01028 | 5.76 | Solar | 05_07_93W43 | 01/22/2025 | 03/11/2025 | 6 | 1 | 5 | 03/12/2025 | 03/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 01/22/2025 | 5/23/2026 | Y | EXP | 365 | 08/08/2025 | 10/27/2025 | 81 | 0 | 81 |  |  | 11/12/2025 | Connected |  | Y
National Grid | UXBRIDGE | 611497 | 01569 | 7.6 | Solar | 05_07_911W56 | 05/16/2024 | 05/20/2024 | 1 | 0 | 1 | 05/21/2024 | 05/21/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 05/16/2024 | 10/4/2025 | Y | EXP | 365 | 09/19/2024 | 02/07/2025 | 142 | 0 | 142 |  |  | 6/10/2025 | Connected |  | N
National Grid | ATHOL | 401107 | 01331 | 0 | Other | 05_09_508L4 | 01/04/2022 | 01/13/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/14/2022 | 02/28/2022 | 30 | 8 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 | 01/04/2022 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 682542 | 01752 | 17.16 | Solar | 05_05_321W6 | 04/03/2025 | 04/09/2025 | 4 | 0 | 4 | 04/10/2025 | 04/10/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 6/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2025 | Connected |  | N
National Grid | HOLBROOK | 177742 | 02343 | 200 | Solar | 05_09_702W3 | 05/30/2017 | 05/30/2017 | 32 | 29 | 3 | 07/17/2017 | 07/17/2017 | 25 | 2 | 23 | 09/05/2017 | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 05/30/2017 | 9/21/2018 | Y | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 9/11/2018 | Connected |  | N
National Grid | FRANKLIN | 625953 | 02038 | 3.8 | Solar | 05_05_311W3 | 07/18/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 07/18/2024 | 9/24/2025 | Y | EXP | 365 | 10/11/2024 | 12/03/2024 | 54 | 0 | 54 |  |  | 12/27/2024 | Connected |  | N
National Grid | BEVERLY | 718315 | 01915 | 11.4 | Solar | 05_07_2W1 | 09/10/2025 | 09/25/2025 | 4 | 0 | 4 | 10/03/2025 | 10/03/2025 | 62 | 48 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LANESBOROUGH | 657468 | 01237 | 8.74 | Solar | 05_05_348W5 | 11/29/2024 | 12/11/2024 | 3 | 0 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/29/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WHITMAN | 230494 | 02382 | 9.92 | Solar | 05_12_18L1 | 06/17/2019 | 06/24/2019 | 5 | 5 | 0 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 | 06/17/2019 | 10/15/2019 | Y | EXP | 16 | 08/16/2019 | 09/09/2019 | 24 | 0 | 24 |  |  | 9/25/2019 | Connected |  | N
National Grid | BROCKTON | 747756 | 02302 | 11.4 | Solar | 05_09_1019W1 | 02/06/2026 | 02/09/2026 | 1 | 0 | 1 | 02/10/2026 | 02/10/2026 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LONGMEADOW | 673264 | 01028 | 7.6 | Solar | 05_07_93W43 | 02/22/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/22/2025 | 4/23/2026 | Y | EXP | 365 | 07/08/2025 | 08/05/2025 | 29 | 0 | 29 |  |  | 8/5/2025 | Connected |  | N
National Grid | MENDON | 616567 | 01756 | 8.505 | Solar | 05_07_911W56 | 06/10/2024 | 06/11/2024 | 2 | 1 | 1 | 06/12/2024 | 06/12/2024 | 96 | 75 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 06/10/2024 | 3/14/2026 | Y | EXP | 365 | 05/20/2025 | 12/22/2025 | 217 | 0 | 217 |  |  | 11/21/2025 | Connected |  | N
National Grid | ORANGE | 431988 | 01364 | 3.8 | Solar | 05_09_508L4 | 06/01/2022 | 06/06/2022 | 3 | 0 | 3 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 06/01/2022 | 12/22/2023 | Y | EXP | 365 | 11/15/2022 | 12/21/2022 | 37 | 0 | 37 |  |  | 1/17/2023 | Connected |  | N
National Grid | MARLBOROUGH | 689399 | 01752 | 17.6 | Solar | 05_05_321W6 | 05/09/2025 | 05/13/2025 | 2 | 0 | 2 | 05/14/2025 | 05/14/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 05/09/2025 | 7/2/2026 | Y | EXP | 365 | 10/01/2025 | 11/21/2025 | 52 | 0 | 52 |  |  | 11/24/2025 | Connected |  | N
National Grid | HOLBROOK | 177860 | 02343 | 6740 | Solar | 05_09_702W3 | 06/13/2017 | 06/13/2017 | 24 | 24 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 08/11/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/18/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 641237 | 02038 | 5.76 | Solar | 05_05_311W3 | 09/18/2024 | 10/08/2024 | 3 | 0 | 3 | 10/09/2024 | 10/09/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 12/4/2025 | Y | EXP | 365 | 02/11/2025 | 03/04/2025 | 22 | 0 | 22 |  |  | 4/1/2025 | Connected |  | N
National Grid | BEVERLY | 685652 | 01915 | 7.6 | Solar | 05_07_2W2 | 04/16/2025 | 05/05/2025 | 2 | 0 | 2 | 06/17/2025 | 06/17/2025 | 55 | 42 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 | 04/16/2025 | 11/14/2026 | Y | EXP | 365 | 02/13/2026 | 03/02/2026 | 18 | 0 | 18 |  |  |  | Completion Documents |  | N
National Grid | ROWE | 666203 | 01367 | 14.06 | Solar | 05_05_348W5 | 01/16/2025 | 02/07/2025 | 16 | 13 | 3 | 02/10/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | WHITMAN | 368295 | 02382 | 53.3 | Solar | 05_12_18L1 | 07/07/2021 | 07/31/2021 | 18 | 9 | 9 | 08/02/2021 | 08/02/2021 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2021 |  | 10/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2021 | Connected |  | N
National Grid | BROCKTON | 174367 | 02302 | 540 | Solar | 05_09_1019W1 | 10/07/2011 | 10/07/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2012 |  | 8/31/2012 | N | STD | 17 |  |  | 0 | 0 | 0 | 12/12/2012 | 12/12/2012 | 12/31/2012 | Connected |  | N
National Grid | LONGMEADOW | 701824 | 01028 | 18.24 | Solar | 05_07_93W43 | 06/30/2025 | 07/09/2025 | 5 | 2 | 3 | 07/10/2025 | 07/10/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | Y
National Grid | UXBRIDGE | 617082 | 01569 | 10 | Solar | 05_07_911W56 | 06/12/2024 | 06/24/2024 | 5 | 0 | 5 | 06/25/2024 | 06/25/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2024 | Connected |  | N
National Grid | ATHOL | 442568 | 01331 | 15.2 | Solar | 05_09_508L4 | 07/07/2022 | 07/08/2022 | 1 | 0 | 1 | 07/11/2022 | 07/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 11/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2022 | Connected |  | N
National Grid | MARLBOROUGH | 729169 | 01752 | 7.6 | Solar | 05_05_321W6 | 10/27/2025 | 10/28/2025 | 1 | 0 | 1 | 11/06/2025 | 11/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2026 | Connected |  | N
National Grid | HOLBROOK | 177957 | 02343 | 1980 | Solar | 05_09_702W3 | 10/23/2017 | 01/11/2018 | 51 | 0 | 51 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/11/2018 | 02/01/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 |  | 10/31/2018 | N | STD | 141 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 645368 | 02038 | 3.8 | Solar | 05_05_311W3 | 10/07/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 63 | 39 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 10/07/2024 | 3/4/2026 | Y | EXP | 365 | 04/30/2025 | 06/05/2025 | 37 | 0 | 37 |  |  | 6/5/2025 | Connected |  | N
National Grid | BEVERLY | 174824 | 01915 | 1000 | Natural Gas | 05_07_2W2 | 07/22/2011 | 07/22/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2011 | 09/07/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2012 |  | 4/17/2012 | N | STD | 46 |  |  | 0 | 0 | 0 | 4/13/2012 | 4/13/2012 | 4/17/2012 | Connected |  | N
National Grid | CHARLEMONT | 687287 | 01339 | 15.76 | Solar | 05_05_348W5 | 04/25/2025 | 04/29/2025 | 2 | 0 | 2 | 04/30/2025 | 04/30/2025 | 48 | 35 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WHITMAN | 396672 | 02382 | 0 | Other | 05_12_18L1 | 01/06/2022 | 01/19/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/20/2022 | 03/01/2022 | 28 | 14 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174910 | 02302 | 2000 | Solar | 05_09_1019W1 | 09/17/2012 | 09/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/27/2012 | 12/03/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 711039 | 01028 | 20 | Solar | 05_07_93W43 | 08/15/2025 | 08/22/2025 | 5 | 0 | 5 | 08/25/2025 | 08/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2026 | Connected |  | N
National Grid | MENDON | 617837 | 01756 | 3.8 | Solar | 05_07_911W56 | 06/13/2024 | 06/27/2024 | 7 | 6 | 1 | 06/28/2024 | 06/28/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/13/2024 | 8/5/2025 | Y | EXP | 365 | 11/06/2024 | 12/11/2024 | 36 | 0 | 36 |  |  | 12/23/2024 | Connected |  | N
National Grid | ATHOL | 455467 | 01331 | 6 | Solar | 05_09_508L4 | 09/07/2022 | 09/12/2022 | 3 | 0 | 3 | 09/13/2022 | 09/13/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 09/07/2022 | 12/31/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2023 | Connected |  | N
National Grid | MARLBOROUGH | 658202 | 01752 | 3.8 | Solar | 05_05_321W9 | 12/03/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 | 12/03/2024 | 3/18/2026 | Y | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WEYMOUTH | 178055 | 02190 | 8140 | Solar | 05_09_702W3 | 07/03/2017 | 07/18/2017 | 8 | 7 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2017 | 08/11/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/11/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 651954 | 02038 | 8.99 | Solar | 05_05_311W3 | 11/04/2024 | 12/03/2024 | 3 | 0 | 3 | 12/04/2024 | 12/04/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 175279 | 01915 | 42.57 | Solar | 05_07_2W2 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 5/1/2015 | Connected |  | N
National Grid | CHARLEMONT | 582192 | 01339 | 75 | Solar | 05_05_348W6 | 01/23/2024 | 02/09/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/23/2026 | N | STD | 413 |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HANSON | 500295 | 02341 | 15.66 | Solar | 05_12_18L1 | 02/10/2023 | 02/15/2023 | 3 | 2 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2023 | Connected |  | N
National Grid | BROCKTON | 175181 | 02302 | 5000 | Solar | 05_09_1019W1 | 05/09/2013 | 05/09/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/21/2013 | 06/24/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/2/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 437923 | 01028 | 250 | Solar | 05_07_94W40 | 09/26/2022 | 10/19/2022 | 16 | 7 | 9 |  |  | 76 | 51 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 09/26/2022 | 5/13/2026 | Y | STD | 224 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | BLACKSTONE | 624249 | 01504 | 11.7 | Solar | 05_07_911W56 | 07/17/2024 | 09/11/2024 | 39 | 36 | 3 | 09/12/2024 | 09/12/2024 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2024 | 07/17/2024 | 11/1/2025 | Y | EXP | 365 | 11/27/2024 | 12/26/2024 | 30 | 0 | 30 |  |  | 12/31/2024 | Connected |  | N
National Grid | ATHOL | 493740 | 01331 | 6 | Solar | 05_09_508L4 | 02/01/2023 | 02/03/2023 | 2 | 0 | 2 | 02/06/2023 | 02/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2023 | 02/01/2023 | 7/31/2024 | Y | EXP | 365 | 07/19/2023 | 08/01/2023 | 14 | 0 | 14 |  |  | 8/10/2023 | Connected |  | N
National Grid | MARLBOROUGH | 737967 | 01752 | 5.76 | Solar | 05_05_321W9 | 12/03/2025 | 12/08/2025 | 2 | 0 | 2 | 01/07/2026 | 01/07/2026 | 26 | 12 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 203390 | 02190 | 1000 | Solar | 05_09_702W3 | 01/11/2019 | 01/25/2019 | 8 | 0 | 8 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 01/28/2019 | 02/25/2019 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 657483 | 01752 | 3.8 | Solar | 05_05_311W3 | 11/27/2024 | 01/06/2025 | 4 | 0 | 4 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 11/27/2024 | 2/20/2026 | Y | EXP | 365 | 03/29/2025 | 03/28/2025 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BEVERLY | 348213 | 01915 | 0 | Battery Add-On | 05_07_2W2 | 03/22/2021 | 03/24/2021 | 1 | 0 | 1 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 6/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HEATH | 664577 | 01346 | 960 | Solar | 05_05_348W6 | 05/19/2025 | 07/09/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 08/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HANSON | 537790 | 02341 | 60 | Solar | 05_12_18L1 | 08/10/2023 | 09/01/2023 | 16 | 7 | 9 | 09/05/2023 | 09/05/2023 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175607 | 02302 | 18 | Solar | 05_09_1019W1 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 | 10/28/2014 | 10/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 10/17/2014 | 12/31/2014 | Y | EXP | 19 | 01/02/2015 | 02/12/2015 | 28 | 0 | 28 | 2/17/2015 | 2/17/2015 | 3/5/2015 | Connected |  | N
National Grid | LONGMEADOW | 645816 | 01028 | 7.6 | Solar | 05_07_94W40 | 10/08/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/08/2024 | 12/11/2026 | Y | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BLACKSTONE | 629127 | 01504 | 11.4 | Solar | 05_07_911W56 | 08/04/2024 | 09/06/2024 | 10 | 8 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 3/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | ATHOL | 492771 | 01331 | 15.2 | Solar | 05_09_508L4 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2023 |  | 3/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2023 | Connected |  | N
National Grid | MARLBOROUGH | 740528 | 01752 |  | Solar | 05_05_321W9 | 12/16/2025 | 12/16/2025 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 31 | 18 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 289276 | 02190 | 0 | Other | 05_09_702W3 | 05/15/2020 | 05/22/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/26/2020 | 06/18/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 673014 | 02038 | 3.8 | Solar | 05_05_311W3 | 02/19/2025 | 03/26/2025 | 17 | 12 | 5 | 04/23/2025 | 04/23/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | BEVERLY | 542638 | 01915 | 0 | Solar | 05_07_2W2 | 07/21/2023 | 07/25/2023 | 2 | 0 | 2 | 07/26/2023 | 07/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 10/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | ROWE | 664576 | 01367 | 960 | Solar | 05_05_348W6 | 06/10/2025 | 07/21/2025 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/22/2025 | 08/04/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 568254 | 02301 | 480 | Solar | 05_12_18L1 | 12/19/2023 | 01/08/2024 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2024 | 02/06/2024 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176846 | 02302 | 25 | Solar | 05_09_1019W1 | 05/03/2016 | 05/03/2016 | 5 | 5 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2016 | 05/03/2016 | 5/8/2017 | Y | EXP | 328 | 10/27/2016 | 11/08/2016 | 8 | 0 | 8 | 11/14/2016 | 11/14/2016 | 11/16/2016 | Connected |  | N
National Grid | LONGMEADOW | 676914 | 01028 | 999.9 | Solar | 05_07_94W40 | 04/08/2025 | 06/10/2025 | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BLACKSTONE | 637096 | 01504 | 5.76 | Solar | 05_07_911W56 | 09/02/2024 | 09/17/2024 | 3 | 0 | 3 | 09/18/2024 | 09/18/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 517452 | 01355 | 15.2 | Solar | 05_09_508L4 | 04/06/2023 | 04/07/2023 | 1 | 0 | 1 | 04/10/2023 | 04/10/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 753309 | 01752 | 11.4 | Solar | 05_05_321W9 | 02/26/2026 | 03/02/2026 | 2 | 0 | 2 | 03/03/2026 | 03/03/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WEYMOUTH | 299108 | 02190 | 0 | Other | 05_09_702W3 | 08/17/2020 | 09/30/2020 | 31 | 29 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/24/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 673800 | 02038 | 7.6 | Solar | 05_05_311W3 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | BEVERLY | 714631 | 01915 | 5.76 | Solar | 05_07_2W2 | 08/27/2025 | 09/05/2025 | 5 | 1 | 4 | 09/08/2025 | 09/08/2025 | 53 | 37 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | CHARLEMONT | 750776 | 01339 | 90 | Solar | 05_05_348W6 | 02/15/2026 |  | 14 | 10 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 591448 | 02301 | 20 | Solar | 05_12_18L1 | 02/20/2024 | 03/27/2024 | 26 | 23 | 3 | 03/28/2024 | 03/28/2024 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 02/20/2024 | 7/13/2025 | Y | EXP | 365 | 07/17/2024 | 08/21/2024 | 36 | 0 | 36 |  |  | 12/20/2024 | Connected |  | N
National Grid | BROCKTON | 176876 | 02302 | 15 | Solar | 05_09_1019W1 | 05/03/2016 | 05/03/2016 | 4 | 4 | 0 | 05/10/2016 | 05/10/2016 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/9/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 728681 | 01028 | 3.8 | Solar | 05_07_94W40 | 10/23/2025 | 10/27/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 | 10/23/2025 | 1/13/2027 | Y | EXP | 365 | 02/06/2026 |  | 29 | 0 | 29 |  |  |  | Construction |  | N
National Grid | BLACKSTONE | 637798 | 01504 | 6 | Solar | 05_07_911W56 | 09/04/2024 | 09/19/2024 | 2 | 0 | 2 | 09/20/2024 | 09/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 525075 | 01364 | 10 | Solar | 05_09_508L4 | 05/19/2023 | 05/26/2023 | 5 | 0 | 5 | 05/30/2023 | 05/30/2023 | 30 | 9 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 | 05/19/2023 | 8/31/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | Y
National Grid | MARLBOROUGH | 174913 | 01752 | 11 | Solar | 05_05_321W9 | 09/19/2012 | 09/19/2012 | 7 | 0 | 7 | 10/01/2012 | 10/01/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2013 |  | 11/20/2012 | N | EXP | 57 |  |  | 0 | 0 | 0 | 3/20/2013 | 3/20/2013 | 4/4/2013 | Connected |  | N
National Grid | WEYMOUTH | 302782 | 02190 | 7.92 | Solar | 05_09_702W3 | 07/24/2020 | 08/26/2020 | 22 | 22 | 0 | 08/27/2020 | 08/27/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 9/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N
National Grid | FRANKLIN | 681814 | 02038 | 5.76 | Solar | 05_05_311W3 | 04/01/2025 | 05/20/2025 | 30 | 25 | 5 | 05/21/2025 | 05/21/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 714789 | 01915 | 240 | Solar | 05_07_3W1 | 08/27/2025 | 09/30/2025 | 23 | 20 | 3 | 10/01/2025 | 10/01/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 08/27/2025 | 9/10/2026 | Y | EXP | 196 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | CHARLEMONT | 752442 | 01339 |  | Battery Add-On | 05_05_348W6 | 02/20/2026 | 02/24/2026 | 2 | 0 | 2 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 611463 | 02301 | 75 | Solar | 05_12_18L1 | 06/13/2024 | 10/03/2024 | 77 | 68 | 9 | 10/04/2024 | 10/04/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 184045 | 02302 | 2500 | Solar | 05_09_1019W1 | 05/22/2018 | 05/22/2018 | 42 | 25 | 17 |  |  | 10 | 9 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2019 | 05/22/2018 | 9/15/2021 | Y | STD | 99 | 05/07/2020 | 07/29/2021 | 185 | 5 | 180 | 7/14/2021 | 8/18/2021 | 9/15/2021 | Connected |  | N
National Grid | LONGMEADOW | 177149 | 01028 | 10 | Solar | 05_07_94W40 | 08/09/2016 | 08/09/2016 | 2 | 2 | 0 | 08/12/2016 | 08/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2016 | 08/09/2016 | 8/15/2017 | Y | EXP | 362 | 10/09/2017 | 11/07/2017 | 15 | 0 | 15 | 11/15/2017 | 11/15/2017 | 11/28/2017 | Connected |  | N
National Grid | MILLVILLE | 641744 | 01529 | 3.8 | Solar | 05_07_911W56 | 09/20/2024 | 09/26/2024 | 4 | 0 | 4 | 09/27/2024 | 09/27/2024 | 77 | 25 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 530576 | 01364 | 10 | Solar | 05_09_508L4 | 06/13/2023 | 06/13/2023 | 5 | 0 | 5 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 | 06/13/2023 | 9/6/2024 | Y | EXP | 365 | 11/10/2023 | 11/09/2023 | 0 | 0 | 0 |  |  | 11/14/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175129 | 01752 | 3000 | Solar | 05_05_321W9 | 10/30/2012 | 10/30/2012 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2012 | 01/02/2013 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2013 | 10/30/2012 | 12/31/2014 | Y | STD | 546 | 06/05/2014 | 04/15/2015 | 213 | 0 | 213 | 4/10/2015 | 4/10/2015 | 4/16/2015 | Connected |  | N
National Grid | WEYMOUTH | 312441 | 02190 | 0 | Other | 05_09_702W3 | 09/22/2020 | 09/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 727492 | 02038 | 20.14 | Solar | 05_05_311W3 | 10/17/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | BEVERLY | 175344 | 01915 | 60 | Solar | 05_07_3W1 | 07/02/2014 | 07/02/2014 | 3 | 0 | 3 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2014 |  | 11/28/2014 | N | EXP | 115 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 1/29/2015 | Connected |  | N
National Grid | CHARLEMONT | 174216 | 01339 | 500 | Solar | 05_05_348W6 | 10/20/2011 | 10/20/2011 | 108 | 0 | 108 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2012 | 10/20/2011 | 1/15/2012 | Y | EXP | 99 | 06/04/2012 | 06/11/2012 | 5 | 0 | 5 | 7/13/2012 | 7/13/2012 | 7/13/2012 | Connected |  | N
National Grid | BROCKTON | 636968 | 02301 | 10 | Solar | 05_12_18L1 | 08/30/2024 | 09/17/2024 | 4 | 0 | 4 | 09/18/2024 | 09/18/2024 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 08/30/2024 | 10/31/2025 | Y | EXP | 365 | 12/19/2024 | 12/18/2024 | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | BROCKTON | 184444 | 02302 | 4998 | Solar | 05_09_1019W1 | 07/10/2018 | 08/02/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/03/2018 | 08/15/2019 | 107 | 4 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2018 |  | 3/1/2021 | N | STD | 795 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 178411 | 01028 | 43.2 | Solar | 05_07_94W40 | 11/27/2017 | 11/27/2017 | 44 | 42 | 2 | 01/31/2018 | 01/31/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/2/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 | 3/28/2018 | 3/28/2018 | 3/30/2018 | Connected |  | N
National Grid | BLACKSTONE | 645973 | 01504 | 10 | Solar | 05_07_911W56 | 10/10/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 545092 | 01331 | 10 | Solar | 05_09_508L4 | 08/31/2023 | 09/05/2023 | 3 | 1 | 2 | 09/06/2023 | 09/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 11/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2023 | Connected |  | N
National Grid | MARLBOROUGH | 175798 | 01752 | 990 | Solar | 05_05_321W9 | 02/27/2015 | 02/27/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/10/2015 | 04/08/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 348650 | 02169 | 7.68 | Solar | 05_09_702W3 | 03/26/2021 | 04/02/2021 | 4 | 3 | 1 | 04/05/2021 | 04/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 4/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | FRANKLIN | 659874 | 02038 | 3.8 | Solar | 05_05_311W4 | 12/11/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/11/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WENHAM | 177010 | 01984 | 720 | Solar | 05_07_3W1 | 10/14/2016 | 10/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/20/2017 | 58 | 44 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 |  | 8/15/2019 | N | STD | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHARLEMONT | 174249 | 01339 | 250 | Solar | 05_05_348W6 | 02/23/2012 | 02/23/2012 | 22 | 0 | 22 | 04/02/2012 | 04/02/2012 | 0 | 0 | 0 | 10/29/2012 | 11/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11/05/2012 | 0 | 0 | 0 | 11/05/2012 | 11/05/2012 | 0 | 0 | 0 | 11/5/2012 |  | 6/1/2012 | N | EXP | 157 |  |  | 0 | 0 | 0 | 12/13/2012 | 12/13/2012 | 12/17/2012 | Connected |  | N
National Grid | BROCKTON | 652042 | 02301 | 7.6 | Solar | 05_12_18L1 | 11/13/2024 | 12/27/2024 | 17 | 12 | 5 | 12/30/2024 | 12/30/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/18/2025 | Connected |  | N
National Grid | BROCKTON | 184560 | 02302 | 990 | Solar | 05_09_1019W1 | 05/09/2018 | 05/09/2018 | 1 | 0 | 1 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 06/15/2018 | 10/29/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 193582 | 01028 | 490 | Solar | 05_07_94W40 | 09/05/2018 | 10/01/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 02/23/2019 | 154 | 83 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 646577 | 01569 | 10 | Solar | 05_07_911W56 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 94 | 84 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 565680 | 01331 | 0 | Solar | 05_09_508L4 | 10/24/2023 | 10/26/2023 | 2 | 0 | 2 | 10/27/2023 | 10/27/2023 | 34 | 11 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2023 |  | 4/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2024 | Connected |  | N
National Grid | MARLBOROUGH | 176436 | 01752 | 6 | Solar | 05_05_321W9 | 03/16/2016 | 03/16/2016 | 6 | 6 | 0 | 03/25/2016 | 03/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/16/2016 | 3/21/2017 | Y | EXP | 343 | 04/19/2016 | 05/31/2016 | 29 | 0 | 29 | 10/28/2016 | 10/28/2016 | 11/1/2016 | Connected |  | N
National Grid | QUINCY | 397106 | 02169 | 3600 | Solar | 05_09_702W3 | 01/31/2022 |  | 52 | 40 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 175299 | 02038 | 300 | Solar | 05_05_311W4 | 01/15/2015 | 01/15/2015 | 3 | 1 | 2 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 2/3/2015 | 2/3/2015 | 9/18/2015 | Connected |  | N
National Grid | WENHAM | 195170 | 01984 | 233.1 | Solar | 05_07_3W1 | 09/13/2018 | 09/25/2018 | 8 | 6 | 2 | 09/26/2018 | 09/26/2018 | 28 | 3 | 25 | 11/20/2018 | 03/11/2019 | 74 | 24 | 50 |  |  | 0 | 0 | 0 |  | 03/11/2019 | 74 | 24 | 50 |  |  | 0 | 0 | 0 | 3/26/2019 |  | 8/21/2020 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | CHARLEMONT | 305614 | 01339 | 175 | Solar | 05_05_348W6 | 08/11/2020 | 09/04/2020 | 18 | 13 | 5 | 09/08/2020 | 09/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  | 1/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 688360 | 02301 | 14.82 | Solar | 05_12_18L1 | 05/12/2025 | 05/22/2025 | 7 | 4 | 3 | 05/23/2025 | 05/23/2025 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 | 05/12/2025 | 7/8/2026 | Y | EXP | 365 | 11/14/2025 | 11/24/2025 | 11 | 0 | 11 |  |  | 11/25/2025 | Connected |  | N
National Grid | BROCKTON | 184704 | 02302 | 4980 | Solar | 05_09_1019W1 | 05/22/2018 | 05/22/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2018 | 08/08/2018 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 191161 | 01028 | 250 | Solar | 05_07_94W40 | 08/04/2018 | 08/24/2018 | 17 | 0 | 17 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  | 4/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLVILLE | 648383 | 01529 | 10 | Solar | 05_07_911W56 | 10/30/2024 | 11/15/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 | 10/30/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | ATHOL | 594830 | 01331 | 10 | Solar | 05_09_508L4 | 03/12/2024 | 04/09/2024 | 21 | 17 | 4 | 04/10/2024 | 04/10/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 03/12/2024 | 4/24/2025 | Y | EXP | 365 | 05/29/2024 | 05/28/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 177451 | 01752 | 4000 | Solar | 05_05_321W9 | 09/20/2016 | 09/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2016 | 12/14/2016 | 57 | 42 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 | 09/20/2016 | 1/31/2023 | Y | STD | 357 | 08/02/2022 | 10/05/2022 | 64 | 0 | 64 |  |  | 1/26/2023 | Connected |  | N
National Grid | QUINCY | 439057 | 02169 | 9.8 | Solar | 05_09_702W3 | 09/14/2022 | 09/23/2022 | 8 | 7 | 1 | 09/26/2022 | 09/26/2022 | 23 | 1 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 12/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/24/2023 | Connected |  | N
National Grid | FRANKLIN | 175990 | 02038 | 12 | Solar | 05_05_311W4 | 03/18/2015 | 03/18/2015 | 4 | 0 | 4 | 03/25/2015 | 03/25/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2015 |  | 12/31/2016 | N | EXP | 631 |  |  | 0 | 0 | 0 | 4/10/2015 | 4/10/2015 | 10/5/2016 | Connected |  | N
National Grid | WENHAM | 348184 | 01984 | 499.9 | Solar | 05_07_3W1 | 06/10/2021 | 07/28/2021 | 33 | 24 | 9 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HEATH | 305559 | 01346 | 125 | Solar | 05_05_348W6 | 08/07/2020 | 09/04/2020 | 20 | 13 | 7 | 09/08/2020 | 09/08/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 1/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 697074 | 02301 | 50 | Solar | 05_12_18L1 | 06/10/2025 | 06/25/2025 | 9 | 9 | 0 | 06/26/2025 | 06/26/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | BROCKTON | 184702 | 02302 | 4980 | Solar | 05_09_1019W1 | 05/25/2018 | 05/25/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/25/2018 | 09/21/2018 | 42 | 16 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 266977 | 01028 | 7.6 | Solar | 05_07_94W40 | 11/26/2019 | 12/02/2019 | 2 | 0 | 2 | 12/03/2019 | 12/03/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2019 | 11/26/2019 | 12/29/2020 | Y | EXP | 365 | 07/21/2020 | 08/12/2020 | 22 | 0 | 22 |  |  | 12/19/2020 | Connected |  | N
National Grid | BLACKSTONE | 650745 | 01504 | 7.6 | Solar | 05_07_911W56 | 11/12/2024 | 01/08/2025 | 27 | 25 | 2 | 01/09/2025 | 01/09/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW SALEM | 627967 | 01355 | 23 | Solar | 05_09_508L4 | 07/26/2024 | 07/31/2024 | 3 | 0 | 3 | 08/01/2024 | 08/01/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2024 | 07/26/2024 | 8/21/2025 | Y | EXP | 365 | 11/13/2024 | 11/20/2024 | 8 | 0 | 8 |  |  | 11/26/2024 | Connected |  | N
National Grid | MARLBOROUGH | 177452 | 01752 | 2000 | Solar | 05_05_321W9 | 09/21/2016 | 09/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/21/2016 | 12/14/2016 | 57 | 42 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2017 | 09/21/2016 | 4/22/2019 | Y | STD | 579 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 440575 | 02169 | 11.4 | Solar | 05_09_702W3 | 09/08/2022 |  | 275 | 63 | 212 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 177257 | 02038 | 396 | Solar | 05_05_311W4 | 08/17/2016 | 08/17/2016 | 2 | 2 | 0 | 08/22/2016 | 08/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 8/23/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 4/21/2017 | 4/21/2017 | 4/28/2017 | Connected |  | N
National Grid | WENHAM | 447713 | 01984 | 50 | Solar | 05_07_3W1 | 07/28/2022 | 10/27/2022 | 64 | 54 | 10 | 10/28/2022 | 10/28/2022 | 33 | 8 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONROE | 381025 | 01350 | 240 | Solar | 05_05_348W6 | 09/09/2021 | 10/14/2021 | 24 | 17 | 7 | 10/15/2021 | 10/15/2021 | 36 | 11 | 25 | 12/29/2021 | 03/03/2022 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  | 03/03/2022 | 45 | 0 | 45 |  |  | 0 | 0 | 0 | 4/20/2022 | 09/09/2021 | 10/9/2024 | Y | EXP | 357 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 649950 | 02301 | 3.77 | Solar | 05_12_18L2 | 10/28/2024 | 01/23/2025 | 29 | 25 | 4 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 10/28/2024 | 3/10/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 184696 | 02302 | 528 | Solar | 05_09_1019W1 | 05/31/2018 | 05/31/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2018 | 07/18/2018 | 15 | 12 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 305003 | 01028 | 6 | Solar | 05_07_94W40 | 10/08/2020 | 10/12/2020 | 1 | 0 | 1 | 10/13/2020 | 10/13/2020 | 26 | 9 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2021 | Connected |  | N
National Grid | UXBRIDGE | 650953 | 01569 | 7.6 | Solar | 05_07_911W56 | 11/11/2024 | 12/04/2024 | 12 | 8 | 4 | 12/05/2024 | 12/05/2024 | 77 | 56 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATHOL | 645655 | 01331 | 7.68 | Solar | 05_09_508L4 | 10/08/2024 | 10/18/2024 | 3 | 0 | 3 | 10/21/2024 | 10/21/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/08/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177554 | 01752 | 15.2 | Solar | 05_05_321W9 | 05/16/2017 | 05/16/2017 | 3 | 3 | 0 | 05/22/2017 | 05/22/2017 | 213 | 0 | 213 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2017 |  | 1/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2020 | Connected |  | N
National Grid | QUINCY | 501750 | 02169 | 7.6 | Solar | 05_09_702W3 | 03/02/2023 | 03/07/2023 | 3 | 0 | 3 | 03/08/2023 | 03/08/2023 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | FRANKLIN | 178581 | 02038 | 10 | Solar | 05_05_311W4 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 11/25/2019 | N | EXP | 614 | 07/28/2018 | 08/29/2018 | 32 | 0 | 32 |  |  | 10/7/2019 | Connected |  | N
National Grid | WENHAM | 478161 | 01984 | 186 | Solar | 05_07_3W1 | 11/19/2022 | 12/14/2022 | 18 | 11 | 7 | 12/15/2022 | 12/15/2022 | 99 | 78 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONROE | 406053 | 01350 | 0 | Battery Add-On | 05_05_348W6 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 03/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 186491 | 02301 | 15.2 | Solar | 05_12_18L2 | 05/29/2018 | 05/29/2018 | 10 | 0 | 10 | 06/13/2018 | 06/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2018 |  | 6/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2018 | Connected |  | N
National Grid | BROCKTON | 196124 | 02302 | 4998 | Solar | 05_09_1019W1 | 09/28/2018 | 10/11/2018 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 12/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 384235 | 01028 | 0 | Other | 05_07_94W40 | 03/30/2022 | 04/13/2022 | 10 | 4 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2022 | 04/27/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 652351 | 01569 | 5.76 | Solar | 05_07_911W56 | 11/19/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 1/28/2026 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW SALEM | 657761 | 01355 | 10 | Solar | 05_09_508L4 | 12/02/2024 | 12/18/2024 | 4 | 0 | 4 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/25/2025 | Connected |  | N
National Grid | MARLBOROUGH | 177672 | 01752 | 2000 | Solar | 05_05_321W9 | 05/25/2017 | 05/25/2017 | 6 | 5 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2017 | 07/07/2017 | 22 | 4 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2017 | 05/25/2017 | 5/1/2020 | Y | STD | 713 | 04/03/2019 | 02/07/2020 | 309 | 0 | 309 | 2/10/2020 | 2/7/2020 | 3/31/2020 | Connected |  | N
National Grid | QUINCY | 504058 | 02169 | 7.6 | Solar | 05_09_702W3 | 02/22/2023 | 03/02/2023 | 6 | 4 | 2 | 03/03/2023 | 03/03/2023 | 78 | 56 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 9/30/2025 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | FRANKLIN | 186667 | 02038 | 7.6 | Solar | 05_05_311W4 | 06/07/2018 | 06/07/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HAMILTON | 489665 | 01982 | 499.9 | Solar | 05_07_3W1 | 01/31/2023 |  | 117 | 99 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HEATH | 422051 | 01346 | 0 | Battery Add-On | 05_05_348W6 | 07/20/2022 | 08/01/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 210634 | 02301 | 9.92 | Solar | 05_12_18L2 | 03/14/2019 | 03/15/2019 | 0 | 0 | 0 | 03/18/2019 | 03/18/2019 | 18 | 15 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2019 |  | 7/26/2019 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  | 7/15/2019 | Connected |  | N
National Grid | BROCKTON | 197531 | 02302 | 4998 | Solar | 05_09_1019W1 | 11/13/2018 | 12/06/2018 | 14 | 13 | 1 |  |  | 33 | 9 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 393066 | 01028 | 420 | Solar | 05_07_94W40 | 02/04/2022 | 02/18/2022 | 10 | 4 | 6 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 652707 | 01504 | 7.6 | Solar | 05_07_911W56 | 11/11/2024 | 12/10/2024 | 3 | 0 | 3 | 12/11/2024 | 12/11/2024 | 36 | 12 | 24 | 02/18/2025 | 04/14/2025 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 04/14/2025 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 4/17/2025 | 11/11/2024 | 4/24/2026 | Y | EXP | 365 | 07/16/2025 | 09/12/2025 | 59 | 0 | 59 |  |  | 11/17/2025 | Connected |  | N
National Grid | ATHOL | 658555 | 01331 | 10 | Solar | 05_09_508L4 | 12/04/2024 | 01/15/2025 | 19 | 13 | 6 | 01/16/2025 | 01/16/2025 | 25 | 0 | 25 | 04/02/2025 | 05/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 05/01/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 5/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 178382 | 01752 | 7.6 | Solar | 05_05_321W9 | 01/15/2018 | 01/15/2018 | 56 | 27 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/21/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 512262 | 02169 | 7.6 | Solar | 05_09_702W3 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 03/24/2023 | 7/13/2024 | Y | EXP | 365 | 07/07/2023 | 07/12/2023 | 6 | 0 | 6 |  |  | 8/23/2023 | Connected |  | N
National Grid | FRANKLIN | 219586 | 02038 | 800 | Solar | 05_05_311W4 | 04/19/2019 | 08/09/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2019 | 10/29/2019 | 54 | 40 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENHAM | 671106 | 01984 | 10 | Solar | 05_07_3W1 | 02/10/2025 | 03/03/2025 | 3 | 0 | 3 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2025 | Connected |  | N
National Grid | CHARLEMONT | 434013 | 01339 | 0 | Battery Add-On | 05_05_348W6 | 07/27/2022 | 08/10/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 302941 | 02301 | 15.2 | Solar | 05_12_18L2 | 07/24/2020 | 07/27/2020 | 0 | 0 | 0 | 07/28/2020 | 07/28/2020 | 36 | 21 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2020 | 07/24/2020 | 6/30/2021 | Y | EXP | 365 | 01/05/2021 | 02/12/2021 | 37 | 0 | 37 |  |  | 2/24/2021 | Connected |  | N
National Grid | BROCKTON | 200718 | 02302 | 4998 | Solar | 05_09_1019W1 | 11/12/2018 | 11/30/2018 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2018 | 12/28/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 473683 | 01028 | 12 | Solar | 05_07_94W40 | 11/29/2022 | 12/30/2022 | 23 | 18 | 5 | 01/03/2023 | 01/03/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2023 |  | 2/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | UXBRIDGE | 653550 | 01569 | 5.7 | Solar | 05_07_911W56 | 11/11/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/11/2024 | 1/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | ATHOL | 674066 | 01331 | 7.6 | Solar | 05_09_508L4 | 03/07/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 42 | 19 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | MARLBOROUGH | 188595 | 01752 | 2178 | Solar | 05_05_321W9 | 06/26/2018 | 06/26/2018 | 15 | 2 | 13 |  |  | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2019 |  | 7/31/2020 | N | STD | 392 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 548337 | 02169 | 7.6 | Solar | 05_09_702W3 | 08/30/2023 |  | 103 | 75 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 681036 | 02038 | 11.5 | Solar | 05_07_3W1 | 03/27/2025 | 04/25/2025 | 21 | 18 | 3 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BEVERLY | 672552 | 01915 | 7.6 | Solar | 05_05_348W6 | 02/18/2025 | 03/25/2025 | 3 | 0 | 3 | 03/26/2025 | 03/26/2025 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | HARDWICK | 304665 | 01037 | 8.99 | Solar | 05_12_18L2 | 08/04/2020 | 08/19/2020 | 11 | 11 | 0 | 08/20/2020 | 08/20/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2020 |  | 8/19/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2020 | Connected |  | N
National Grid | BROCKTON | 216209 | 02301 | 230 | Hydro | 05_09_1019W1 | 05/22/2019 | 07/01/2019 | 27 | 22 | 5 |  |  | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2020 | 05/22/2019 | 2/1/2024 | Y | STD | 519 |  |  | 0 | 0 | 0 |  |  | 10/12/2023 | Connected |  | N
National Grid | BROCKTON | 485684 | 02302 | 15.08 | Solar | 05_07_94W40 | 12/15/2022 | 12/20/2022 | 4 | 2 | 2 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | LONGMEADOW | 653709 | 01028 | 3.8 | Solar | 05_07_911W56 | 11/18/2024 | 12/16/2024 | 5 | 0 | 5 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/18/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | BLACKSTONE | 686497 | 01504 | 19.38 | Solar | 05_09_508L4 | 04/23/2025 | 04/28/2025 | 3 | 0 | 3 | 04/29/2025 | 04/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | ATHOL | 225439 | 01331 | 6 | Solar | 05_05_321W9 | 05/08/2019 | 05/09/2019 | 1 | 1 | 0 | 05/10/2019 | 05/10/2019 | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2019 | 05/08/2019 | 4/14/2020 | Y | EXP | 32 | 10/24/2019 | 11/26/2019 | 33 | 0 | 33 |  |  | 12/16/2019 | Connected |  | N
National Grid | MARLBOROUGH | 642119 | 01752 | 3.8 | Solar | 05_09_702W3 | 09/23/2024 | 10/14/2024 | 5 | 0 | 5 | 10/15/2024 | 10/15/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/23/2024 | 12/15/2025 | Y | EXP | 365 | 02/12/2025 | 02/11/2025 | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | QUINCY | 299754 | 02169 | 10 | Solar | 05_05_311W4 | 09/02/2020 | 09/18/2020 | 11 | 11 | 0 | 09/21/2020 | 09/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2020 | 09/02/2020 | 10/15/2021 | Y | EXP | 365 | 12/29/2020 | 03/01/2021 | 62 | 0 | 62 |  |  | 3/3/2021 | Connected |  | N
National Grid | FRANKLIN | 673424 | 02038 | 0 | Other | 05_07_3W2 | 06/25/2025 | 08/26/2025 | 42 | 32 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WENHAM | 178754 | 01984 | 45 | Solar | 05_05_349W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 38 | 09/25/2012 | 09/12/2012 | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 12/28/2012 | Connected |  | N
National Grid | MONROE | 335872 | 01350 | 100 | Solar | 05_12_18L2 | 01/08/2021 | 01/25/2021 | 9 | 0 | 9 | 01/26/2021 | 01/26/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 12/16/2022 | N | EXP | 275 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | BROCKTON | 252302 | 02301 | 25 | Solar | 05_09_1019W1 | 09/04/2019 | 09/11/2019 | 5 | 5 | 0 | 09/12/2019 | 09/12/2019 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 9/2/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 556280 | 02302 | 10 | Solar | 05_07_94W40 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 09/22/2023 | 11/15/2024 | Y | EXP | 365 | 04/18/2024 | 04/17/2024 | 0 | 0 | 0 |  |  | 4/29/2024 | Connected |  | N
National Grid | LONGMEADOW | 654806 | 01028 | 6.5 | Solar | 05_07_911W56 | 11/16/2024 | 12/03/2024 | 2 | 0 | 2 | 12/04/2024 | 12/04/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/16/2024 | 2/26/2026 | Y | EXP | 365 | 03/22/2025 | 05/15/2025 | 55 | 0 | 55 |  |  | 6/4/2025 | Connected |  | N
National Grid | UXBRIDGE | 691125 | 01569 | 15.96 | Solar | 05_09_508L4 | 05/12/2025 | 05/29/2025 | 7 | 6 | 1 | 05/30/2025 | 05/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2025 | Connected |  | N
National Grid | NEW SALEM | 294931 | 01355 | 8.88 | Solar | 05_05_321W9 | 06/04/2020 | 06/17/2020 | 9 | 9 | 0 | 06/18/2020 | 06/18/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2020 |  | 6/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | MARLBOROUGH | 661629 | 01752 | 5.76 | Solar | 05_09_702W3 | 12/19/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 436246 | 02169 | 9.984 | Solar | 05_05_311W4 | 06/23/2022 | 06/24/2022 | 1 | 0 | 1 | 06/27/2022 | 06/27/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2022 | 06/23/2022 |  | Y | EXP | 365 | 09/15/2022 | 10/18/2022 | 34 | 0 | 34 |  |  | 5/19/2023 | Connected |  | N
National Grid | FRANKLIN | 721369 | 02038 | 360 | Landfill Gas | 05_07_3W2 | 09/29/2025 | 11/24/2025 | 38 | 28 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | WENHAM | 178753 | 01984 | 62 | Solar | 05_05_349W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2012 | 07/05/2012 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2012 | 02/15/2012 | 7/1/2012 | Y | STD | 4 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 12/20/2012 | Connected |  | N
National Grid | MONROE | 363282 | 01350 | 7.6 | Solar | 05_12_18L2 | 06/10/2021 | 06/11/2021 | 1 | 0 | 1 | 06/14/2021 | 06/14/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 8/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2022 | Connected |  | N
National Grid | BROCKTON | 262661 | 02301 | 25 | Solar | 05_09_1019W1 | 10/30/2019 | 11/07/2019 | 6 | 6 | 0 | 11/08/2019 | 11/08/2019 | 50 | 33 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2020 |  | 10/30/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 572349 | 02302 | 3.8 | Solar | 05_07_94W40 | 12/11/2023 | 12/14/2023 | 4 | 3 | 1 | 12/15/2023 | 12/15/2023 | 53 | 30 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 655211 | 01028 | 3.8 | Solar | 05_07_911W56 | 11/19/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/19/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | MILLVILLE | 628497 | 01529 | 437.5 | Solar | 05_09_508L5 | 01/29/2025 | 06/26/2025 | 102 | 93 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NEW SALEM | 311259 | 01355 | 60 | Solar | 05_05_321W9 | 09/18/2020 | 09/29/2020 | 6 | 0 | 6 | 09/30/2020 | 09/30/2020 | 47 | 24 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 |  | 7/20/2022 | N | EXP | 386 |  |  | 0 | 0 | 0 |  |  | 7/1/2022 | Connected |  | N
National Grid | MARLBOROUGH | 663607 | 01752 | 10 | Solar | 05_09_702W3 | 01/03/2025 | 01/15/2025 | 4 | 0 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 01/03/2025 | 5/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2025 | Connected |  | N
National Grid | QUINCY | 644500 | 02169 | 10 | Solar | 05_05_311W4 | 10/02/2024 | 10/28/2024 | 3 | 0 | 3 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/02/2024 | 2/10/2026 | Y | EXP | 425 | 01/07/2025 | 02/13/2025 | 38 | 0 | 38 |  |  |  | Withdrawn |  | N
National Grid | FOXBOROUGH | 177493 | 02035 | 42 | Solar | 05_07_3W2 | 12/13/2016 | 12/13/2016 | 0 | 0 | 0 | 12/13/2016 | 12/13/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2016 |  | 12/18/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 5/11/2017 | 5/11/2017 | 5/17/2017 | Connected |  | N
National Grid | HAMILTON | 178752 | 01982 | 45 | Solar | 05_05_349W1 | 02/15/2012 | 02/15/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2012 | 02/15/2012 | 7/1/2012 | Y | EXP | 93 |  |  | 0 | 0 | 0 | 12/17/2012 | 12/17/2012 | 12/28/2012 | Connected |  | N
National Grid | ROWE | 364985 | 01367 | 43.2 | Solar | 05_12_18L2 | 07/14/2021 | 12/27/2021 | 37 | 27 | 10 | 09/03/2021 | 09/03/2021 | 118 | 101 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 |  | 3/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2022 | Connected |  | N
National Grid | BROCKTON | 262657 | 02301 | 25 | Solar | 05_09_1019W1 | 10/30/2019 | 11/07/2019 | 6 | 6 | 0 | 11/08/2019 | 11/08/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 |  | 10/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 600250 | 02302 | 6.67 | Solar | 05_07_94W40 | 03/29/2024 | 04/03/2024 | 4 | 2 | 2 | 04/04/2024 | 04/04/2024 | 9 | 0 | 9 | 08/27/2024 | 09/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 9/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LONGMEADOW | 657374 | 01028 | 7.6 | Solar | 05_07_911W56 | 11/27/2024 | 01/07/2025 | 17 | 12 | 5 | 01/08/2025 | 01/08/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 697231 | 01504 | 420 | Solar | 05_09_508L5 | 09/11/2025 | 11/24/2025 | 48 | 39 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2025 | 12/23/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ATHOL | 317793 | 01331 | 6 | Solar | 05_05_321W9 | 10/08/2020 | 10/09/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2021 | Connected |  | N
National Grid | MARLBOROUGH | 671862 | 01752 | 5.76 | Solar | 05_09_702W3 | 02/13/2025 | 03/04/2025 | 6 | 3 | 3 | 03/05/2025 | 03/05/2025 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/13/2025 | 5/20/2026 | Y | EXP | 365 | 10/14/2025 | 11/07/2025 | 25 | 0 | 25 |  |  | 11/21/2025 | Connected |  | N
National Grid | QUINCY | 668317 | 02169 | 3.8 | Solar | 05_05_311W4 | 01/30/2025 | 03/19/2025 | 16 | 11 | 5 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | FOXBOROUGH | 178072 | 02035 | 7.6 | Solar | 05_07_3W2 | 11/01/2017 | 11/01/2017 | 9 | 9 | 0 | 11/20/2017 | 11/20/2017 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2017 |  | 11/6/2018 | N | EXP | 35 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENHAM | 587835 | 01984 | 100 | Solar | 05_05_349W1 | 02/29/2024 |  | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ROWE | 374102 | 01367 | 0 | Solar | 05_12_18L2 | 08/05/2021 | 08/06/2021 | 1 | 0 | 1 | 08/09/2021 | 08/09/2021 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2021 | 08/05/2021 | 2/9/2023 | Y | EXP | 365 | 01/06/2022 | 02/09/2022 | 35 | 0 | 35 |  |  | 7/12/2022 | Connected |  | N
National Grid | BROCKTON | 299097 | 02301 | 5.76 | Solar | 05_09_1019W1 | 06/30/2020 | 07/08/2020 | 6 | 2 | 4 | 07/09/2020 | 07/09/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2020 |  | 7/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2020 | Connected |  | N
National Grid | BROCKTON | 645170 | 02302 | 5.76 | Solar | 05_07_94W40 | 10/04/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 10/04/2024 | 12/12/2025 | Y | EXP | 365 | 02/26/2025 | 10/17/2025 | 234 | 0 | 234 |  |  | 10/29/2025 | Connected |  | N
National Grid | LONGMEADOW | 660168 | 01028 | 7.15 | Solar | 05_07_911W56 | 12/12/2024 | 12/24/2024 | 5 | 1 | 4 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 | 12/12/2024 | 3/28/2026 | Y | EXP | 365 | 04/01/2025 | 04/28/2025 | 28 | 0 | 28 |  |  | 6/26/2025 | Connected |  | N
National Grid | MILLVILLE | 175278 | 01529 | 30.42 | Solar | 05_09_508L5 | 08/28/2014 | 08/28/2014 | 6 | 0 | 6 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 4/30/2015 | Connected |  | N
National Grid | ORANGE | 365368 | 01364 | 7.6 | Solar | 05_05_321W9 | 06/23/2021 | 06/28/2021 | 3 | 0 | 3 | 06/29/2021 | 06/29/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2021 |  | 10/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2022 | Connected |  | N
National Grid | MARLBOROUGH | 680545 | 01752 | 5.76 | Solar | 05_09_702W3 | 03/31/2025 | 04/09/2025 | 3 | 0 | 3 | 04/22/2025 | 04/22/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 668726 | 02169 | 5.12 | Solar | 05_05_311W4 | 01/29/2025 | 02/13/2025 | 5 | 2 | 3 | 02/14/2025 | 02/14/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/12/2025 | Connected |  | N
National Grid | FOXBOROUGH | 256122 | 02035 | 6 | Solar | 05_07_3W2 | 11/01/2019 | 11/05/2019 | 1 | 0 | 1 | 11/06/2019 | 11/06/2019 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2019 |  | 4/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2020 | Connected |  | N
National Grid | HAMILTON | 637419 | 01982 | 480 | Solar | 05_05_349W1 | 12/09/2024 | 01/17/2025 | 28 | 18 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2025 | 03/10/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROWE | 628548 | 01367 | 7.6 | Solar | 05_12_18L2 | 07/31/2024 | 09/05/2024 | 17 | 15 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 07/31/2024 | 10/22/2025 | Y | EXP | 365 | 11/21/2024 | 12/02/2024 | 12 | 0 | 12 |  |  | 3/18/2025 | Connected |  | N
National Grid | BROCKTON | 320192 | 02301 | 10 | Solar | 05_09_1019W1 | 10/20/2020 | 10/22/2020 | 2 | 2 | 0 | 10/23/2020 | 10/23/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2020 |  | 11/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 657028 | 02302 | 5.76 | Solar | 05_07_94W40 | 11/26/2024 | 12/23/2024 | 5 | 0 | 5 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/26/2024 | 2/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2025 | Connected |  | N
National Grid | LONGMEADOW | 664806 | 01028 | 7.22 | Solar | 05_07_911W56 | 01/09/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | BLACKSTONE | 177232 | 01504 | 109.9 | Solar | 05_09_508L5 | 11/03/2016 | 11/03/2016 | 1 | 1 | 0 | 11/07/2016 | 11/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2016 |  | 11/9/2017 | N | EXP | 367 |  |  | 0 | 0 | 0 | 1/11/2017 | 1/11/2017 | 1/13/2017 | Connected |  | N
National Grid | ATHOL | 452803 | 01331 | 6 | Solar | 05_05_321W9 | 08/30/2022 | 09/01/2022 | 2 | 0 | 2 | 09/02/2022 | 09/02/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 686524 | 01752 | 15.76 | Solar | 05_09_702W3 | 04/24/2025 | 05/05/2025 | 7 | 4 | 3 | 05/06/2025 | 05/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | QUINCY | 511796 | 02169 | 249 | Solar | 05_05_311W5 | 07/06/2023 | 09/01/2023 | 41 | 32 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 07/06/2023 | 9/3/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | FOXBOROUGH | 374495 | 02035 | 7.6 | Solar | 05_07_3W2 | 08/06/2021 |  | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WENHAM | 478091 | 01984 | 25 | Solar | 05_05_3J1 | 11/17/2022 | 12/12/2022 | 16 | 13 | 3 | 12/13/2022 | 12/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2023 |  | 1/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | CHARLEMONT | 640696 | 01339 | 31.92 | Solar | 05_12_18L2 | 11/25/2024 | 02/03/2025 | 46 | 36 | 10 | 02/04/2025 | 02/04/2025 | 69 | 48 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2025 |  | 6/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | BROCKTON | 412843 | 02301 | 7.6 | Solar | 05_09_1019W1 | 02/17/2022 | 04/21/2022 | 43 | 41 | 2 | 04/22/2022 | 04/22/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2022 |  | 5/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2022 | Connected |  | N
National Grid | BROCKTON | 660479 | 02302 | 3.8 | Solar | 05_07_94W40 | 12/13/2024 | 01/02/2025 | 2 | 0 | 2 | 01/03/2025 | 01/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/13/2024 | 2/25/2026 | Y | EXP | 365 | 08/21/2025 | 02/03/2026 | 167 | 0 | 167 |  |  | 11/24/2025 | Connected |  | N
National Grid | LONGMEADOW | 666003 | 01028 | 10 | Solar | 05_07_911W56 | 01/17/2025 | 02/10/2025 | 4 | 0 | 4 | 02/11/2025 | 02/11/2025 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2025 | Connected |  | N
National Grid | MILLVILLE | 177270 | 01529 | 86.4 | Solar | 05_09_508L5 | 11/10/2016 | 11/10/2016 | 2 | 2 | 0 | 11/15/2016 | 11/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 |  | 11/15/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 1/11/2017 | 1/11/2017 | 1/17/2017 | Connected |  | N
National Grid | ATHOL | 397085 | 01331 | 10 | Solar | 05_05_321W9 | 12/02/2021 | 01/07/2022 | 8 | 5 | 3 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 687069 | 01752 | 4980 | Solar | 05_09_702W3 | 06/03/2025 | 07/09/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/28/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 739106 | 02169 | 10 | Solar | 05_05_311W5 | 12/09/2025 | 12/11/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | FOXBOROUGH | 379106 | 02035 | 11.4 | Solar | 05_07_3W2 | 08/31/2021 | 01/07/2022 | 23 | 21 | 2 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2021 |  | 11/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/6/2022 | Connected |  | N
National Grid | WENHAM | 176725 | 01984 | 500 | Solar | 05_05_3J2 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2016 | 03/29/2016 | 24 | 6 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/28/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HEATH | 647884 | 01346 | 4.06 | Solar | 05_12_18L2 | 10/21/2024 | 11/07/2024 | 10 | 8 | 2 | 11/08/2024 | 11/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/21/2024 | 12/18/2025 | Y | EXP | 365 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | BROCKTON | 610274 | 02301 | 23 | Solar | 05_09_1019W1 | 05/10/2024 | 06/03/2024 | 2 | 0 | 2 | 06/04/2024 | 06/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | BROCKTON | 701575 | 02302 | 10 | Solar | 05_07_94W40 | 08/01/2025 | 09/08/2025 | 24 | 22 | 2 | 09/09/2025 | 09/09/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2025 | Connected |  | N
National Grid | LONGMEADOW | 667424 | 01028 | 10 | Solar | 05_07_911W56 | 02/04/2025 | 03/04/2025 | 10 | 6 | 4 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BLACKSTONE | 177564 | 01504 | 10 | Solar | 05_09_508L5 | 07/14/2017 | 07/14/2017 | 2 | 2 | 0 | 07/19/2017 | 07/19/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 7/22/2018 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  | 10/23/2018 | Connected |  | N
National Grid | ATHOL | 408655 | 01331 | 0 | Solar | 05_05_321W9 | 01/27/2022 | 01/31/2022 | 2 | 0 | 2 | 02/01/2022 | 02/01/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 5/15/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 555621 | 01752 | 12.5 | Solar | 05_09_704W1 | 07/03/2024 | 09/10/2024 | 46 | 39 | 7 | 09/11/2024 | 09/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2024 |  | 3/15/2026 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 158029 | 02169 | 7.6 | Solar | 05_05_311W5 | 01/26/2016 | 01/26/2016 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/1/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 539000 | 02769 | 30 | Solar | 05_07_3W2 | 07/06/2023 | 08/18/2023 | 32 | 22 | 10 | 08/21/2023 | 08/21/2023 | 45 | 26 | 19 | 11/01/2023 | 12/11/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 12/11/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 11/22/2023 |  | 12/25/2024 | N | EXP | 365 | 12/07/2023 | 02/16/2024 | 72 | 3 | 69 |  |  | 4/12/2024 | Connected |  | N
National Grid | BEVERLY | 481302 | 01915 | 5.22 | Solar | 05_05_3J2 | 12/23/2022 | 12/30/2022 | 4 | 2 | 2 | 01/03/2023 | 01/03/2023 | 50 | 29 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2023 | 12/23/2022 | 5/16/2024 | Y | EXP | 365 | 04/29/2023 | 05/15/2023 | 17 | 0 | 17 |  |  | 8/9/2023 | Connected |  | N
National Grid | HEATH | 716971 | 01346 | 7.6 | Solar | 05_12_18L2 | 09/05/2025 | 11/03/2025 | 3 | 0 | 3 | 11/04/2025 | 11/04/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2026 | Connected |  | N
National Grid | BROCKTON | 648922 | 02301 | 9.88 | Solar | 05_09_1019W1 | 10/22/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 1/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | BROCKTON | 419315 | 02302 | 240 | Solar | 05_07_94W41 | 05/26/2022 | 06/13/2022 | 12 | 5 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LONGMEADOW | 670190 | 01028 | 7.6 | Solar | 05_07_911W56 | 02/05/2025 | 03/13/2025 | 16 | 13 | 3 | 03/14/2025 | 03/14/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | BLACKSTONE | 177763 | 01504 | 72 | Solar | 05_09_508L5 | 10/05/2017 | 10/05/2017 | 42 | 42 | 0 | 12/15/2017 | 12/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2017 |  | 10/11/2018 | N | EXP | 297 |  |  | 0 | 0 | 0 | 4/20/2018 | 4/20/2018 | 4/20/2018 | Connected |  | N
National Grid | ATHOL | 448582 | 01331 | 6 | Solar | 05_05_321W9 | 09/27/2022 | 10/21/2022 | 17 | 16 | 1 | 10/24/2022 | 10/24/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 09/27/2022 | 5/3/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2023 | Connected |  | N
National Grid | MARLBOROUGH | 720120 | 01752 | 7.6 | Solar | 05_09_704W1 | 09/18/2025 | 10/03/2025 | 4 | 0 | 4 | 10/20/2025 | 10/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 | 09/18/2025 | 11/13/2026 | Y | EXP | 365 | 01/13/2026 |  | 53 | 0 | 53 |  |  |  | Construction |  | N
National Grid | QUINCY | 175319 | 02169 | 440.8 | Solar | 05_05_311W5 | 08/29/2014 | 08/29/2014 | 6 | 2 | 4 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | REHOBOTH | 566869 | 02769 | 3.8 | Solar | 05_07_3W2 | 11/16/2023 | 11/17/2023 | 1 | 0 | 1 | 11/20/2023 | 11/20/2023 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2024 | Connected |  | N
National Grid | HAMILTON | 572571 | 01982 | 3.19 | Solar | 05_05_3J2 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 12/07/2023 | 1/21/2025 | Y | EXP | 365 | 03/05/2024 | 03/25/2024 | 21 | 0 | 21 |  |  | 3/30/2024 | Connected |  | N
National Grid | HEATH | 672537 | 01346 | 5.76 | Solar | 05_12_19W1 | 02/18/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 4/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 662958 | 02301 | 2.33 | Solar | 05_09_1019W1 | 12/30/2024 | 01/21/2025 | 6 | 2 | 4 | 01/22/2025 | 01/22/2025 | 51 | 30 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | BROCKTON | 175597 | 02302 | 998 | Solar | 05_07_94W41 | 08/01/2014 | 08/01/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2014 | 08/29/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2015 | 08/01/2014 | 1/20/2016 | Y | STD | 296 | 09/14/2016 | 01/17/2017 | 83 | 0 | 83 | 4/5/2017 | 4/5/2017 | 4/5/2017 | Connected |  | N
National Grid | LONGMEADOW | 671505 | 01028 | 7.6 | Solar | 05_07_911W56 | 02/11/2025 | 03/10/2025 | 6 | 2 | 4 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | BLACKSTONE | 177917 | 01504 | 72 | Solar | 05_09_508L5 | 10/20/2017 | 10/20/2017 | 12 | 5 | 7 | 11/14/2017 | 11/14/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2017 |  | 10/28/2018 | N | EXP | 345 |  |  | 0 | 0 | 0 |  |  | 10/11/2018 | Connected |  | N
National Grid | SHUTESBURY | 481212 | 01072 | 0 | Solar | 05_05_321W9 | 11/29/2022 | 12/05/2022 | 4 | 2 | 2 | 12/06/2022 | 12/06/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 724423 | 01752 | 6.08 | Solar | 05_09_704W1 | 10/13/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | QUINCY | 176533 | 02169 | 7.6 | Solar | 05_05_311W5 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 |  | 2/15/2017 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/8/2016 | 7/8/2016 | 7/12/2016 | Connected |  | N
National Grid | REHOBOTH | 622083 | 02769 | 5.76 | Solar | 05_07_3W2 | 07/02/2024 | 07/17/2024 | 3 | 2 | 1 | 07/18/2024 | 07/18/2024 | 22 | 8 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2024 | Connected |  | N
National Grid | HAMILTON | 671968 | 01982 | 5.76 | Solar | 05_05_3J2 | 02/13/2025 | 03/12/2025 | 5 | 0 | 5 | 03/13/2025 | 03/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2025 | Connected |  | N
National Grid | CHARLEMONT | 732034 | 01339 | 5.76 | Solar | 05_12_19W1 | 11/06/2025 | 11/06/2025 | 1 | 0 | 1 | 12/30/2025 | 12/30/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 691667 | 02301 | 0 | Solar | 05_09_1019W1 | 05/14/2025 | 05/20/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 32 | 12 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2025 |  | 7/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2026 | Connected |  | N
National Grid | BROCKTON | 176307 | 02302 | 252 | Solar | 05_07_94W41 | 02/20/2015 | 02/20/2015 | 11 | 5 | 6 | 03/10/2015 | 03/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2015 |  | 9/30/2015 | N | EXP | 19 |  |  | 0 | 0 | 0 | 5/27/2015 | 5/27/2015 | 7/21/2015 | Connected |  | N
National Grid | LONGMEADOW | 672368 | 01028 | 11.4 | Solar | 05_07_911W56 | 02/18/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLVILLE | 177902 | 01529 | 4990 | Solar | 05_09_508L5 | 06/15/2017 | 06/15/2017 | 43 | 43 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2017 | 09/21/2017 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2019 | 06/15/2017 | 11/15/2019 | Y | STD | 255 | 03/06/2019 | 04/19/2019 | 44 | 0 | 44 |  |  | 10/31/2019 | Connected |  | N
National Grid | SHUTESBURY | 480715 | 01072 | 10 | Solar | 05_05_321W9 | 01/30/2023 | 02/01/2023 | 2 | 0 | 2 | 02/02/2023 | 02/02/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 752652 | 01752 | 0 | Battery Add-On | 05_09_704W1 | 02/23/2026 | 03/03/2026 | 5 | 3 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | QUINCY | 177888 | 02169 | 300 | Natural Gas | 05_05_311W5 | 04/11/2017 | 04/11/2017 | 55 | 52 | 3 | 06/30/2017 | 06/30/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2017 |  | 4/17/2018 | N | EXP | 264 |  |  | 0 | 0 | 0 |  |  | 9/27/2018 | Connected |  | N
National Grid | REHOBOTH | 730876 | 02769 | 15.2 | Solar | 05_07_3W2 | 11/03/2025 | 11/06/2025 | 3 | 0 | 3 | 11/07/2025 | 11/07/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2025 | Connected |  | N
National Grid | SAUGUS | 678659 | 01906 | 15.2 | Solar | 05_05_3J2 | 03/17/2025 | 03/21/2025 | 4 | 0 | 4 | 03/24/2025 | 03/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | CHARLEMONT | 174678 | 01339 | 22.8 | Solar | 05_12_19W1 | 12/30/2013 | 12/30/2013 | 286 | 284 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 693043 | 02301 | 10 | Solar | 05_09_1019W1 | 06/06/2025 | 06/12/2025 | 4 | 0 | 4 | 06/13/2025 | 06/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | BROCKTON | 208613 | 02302 | 972 | Solar | 05_07_94W41 | 03/27/2019 | 04/20/2019 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2019 | 05/14/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 676110 | 01028 | 11.4 | Solar | 05_07_911W56 | 03/07/2025 | 03/19/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLVILLE | 178737 | 01529 | 11.4 | Solar | 05_09_508L5 | 02/12/2018 | 02/12/2018 | 0 | 0 | 0 | 03/23/2018 | 03/23/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2018 | 02/12/2018 | 8/12/2019 | Y | EXP | 455 | 03/07/2019 | 03/06/2019 | 0 | 0 | 0 |  |  | 8/3/2019 | Connected |  | N
National Grid | SHUTESBURY | 502463 | 01072 | 6.96 | Solar | 05_05_321W9 | 02/16/2023 | 02/17/2023 | 1 | 0 | 1 | 02/21/2023 | 02/21/2023 | 27 | 5 | 22 | 04/04/2023 | 05/08/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 05/08/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 5/1/2023 |  | 8/16/2024 | N | EXP | 365 | 07/25/2023 | 08/17/2023 | 24 | 0 | 24 |  |  | 8/29/2023 | Connected |  | Y
National Grid | MARLBOROUGH | 174799 | 01752 | 15 | Solar | 05_09_704W1 | 08/29/2012 | 08/29/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2012 |  | 11/16/2012 | N | EXP | 17 |  |  | 0 | 0 | 0 | 12/3/2012 | 12/3/2012 | 1/15/2013 | Connected |  | N
National Grid | QUINCY | 178141 | 02169 | 7.6 | Solar | 05_05_311W5 | 03/22/2018 | 03/22/2018 | 18 | 9 | 9 | 04/05/2018 | 04/05/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2019 |  | 3/28/2019 | N | EXP | 15 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 174402 | 02769 | 116.2 | Solar | 05_07_3W3 | 06/14/2012 | 06/14/2012 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2012 |  | 9/28/2012 | N | EXP | 18 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 11/16/2012 | Connected |  | N
National Grid | SAUGUS | 255162 | 01906 | 15.2 | Solar | 05_05_3J3 | 09/19/2019 | 09/24/2019 | 2 | 0 | 2 | 09/25/2019 | 09/25/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2019 |  | 9/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2020 | Connected |  | N
National Grid | CHARLEMONT | 177346 | 01339 | 7.6 | Solar | 05_12_19W1 | 11/22/2016 | 11/22/2016 | 3 | 3 | 0 | 11/29/2016 | 11/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2016 |  | 11/28/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 1/9/2018 | 1/9/2018 | 8/14/2017 | Connected |  | N
National Grid | BROCKTON | 713220 | 02301 | 11.5 | Solar | 05_09_1019W1 | 08/21/2025 | 08/26/2025 | 3 | 2 | 1 | 08/27/2025 | 08/27/2025 | 47 | 31 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 443997 | 02302 | 0 | Other | 05_07_94W41 | 11/09/2022 |  | 121 | 113 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 682150 | 01028 | 10 | Solar | 05_07_911W56 | 04/19/2025 | 06/03/2025 | 28 | 24 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 189959 | 01504 | 83.3 | Solar | 05_09_508L5 | 08/14/2018 | 08/17/2018 | 0 | 0 | 0 | 08/17/2018 | 08/17/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2018 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2024 | Connected |  | N
National Grid | SHUTESBURY | 520207 | 01072 | 17.98 | Solar | 05_05_321W9 | 04/20/2023 | 04/24/2023 | 2 | 0 | 2 | 04/25/2023 | 04/25/2023 | 252 | 232 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175085 | 01752 | 12.2 | Solar | 05_09_704W1 | 08/14/2012 | 08/14/2012 | 5 | 0 | 5 | 08/22/2012 | 08/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 10/24/2012 | 10/24/2012 | 12/28/2012 | Connected |  | N
National Grid | QUINCY | 178593 | 02169 | 240 | Solar | 05_05_311W5 | 03/14/2018 | 03/14/2018 | 24 | 24 | 0 |  |  | 0 | 0 | 0 | 04/10/2018 | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  | 04/24/2018 | 8 | 8 | 0 |  |  | 0 | 0 | 0 |  |  | 3/20/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 175309 | 02769 | 135 | Solar | 05_07_3W3 | 06/27/2014 | 06/27/2014 | 6 | 1 | 5 | 07/09/2014 | 07/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2014 |  | 12/31/2014 | N | EXP | 145 |  |  | 0 | 0 | 0 | 8/8/2014 | 8/8/2014 | 3/31/2016 | Connected |  | N
National Grid | SAUGUS | 324466 | 01906 | 10 | Solar | 05_05_3J3 | 01/31/2021 | 02/02/2021 | 1 | 0 | 1 | 02/03/2021 | 02/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HEATH | 177551 | 01346 | 3.8 | Solar | 05_12_19W1 | 05/15/2017 | 05/15/2017 | 6 | 5 | 1 | 05/24/2017 | 05/24/2017 | 187 | 0 | 187 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2017 |  | 5/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 661496 | 02301 | 10 | Solar | 05_09_1021W1 | 12/18/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 12/18/2024 | 2/18/2026 | Y | EXP | 365 | 06/11/2025 |  | 269 | 0 | 269 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 589714 | 02302 | 980 | Solar | 05_07_94W41 | 03/20/2024 | 06/25/2024 | 66 | 58 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2024 | 09/16/2024 | 58 | 40 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 683810 | 01028 | 3.8 | Solar | 05_07_911W56 | 04/08/2025 | 05/13/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 04/08/2025 | 8/19/2026 | Y | EXP | 365 | 11/25/2025 | 01/03/2026 | 40 | 0 | 40 |  |  | 1/7/2026 | Connected |  | N
National Grid | BLACKSTONE | 193803 | 01504 | 299.7 | Solar | 05_09_508L5 | 08/17/2018 | 08/23/2018 | 3 | 0 | 3 | 08/24/2018 | 08/24/2018 | 27 | 26 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 08/17/2018 | 11/24/2020 | Y | EXP | 531 |  |  | 0 | 0 | 0 |  |  | 11/24/2020 | Connected |  | N
National Grid | SHUTESBURY | 528272 | 01072 | 10 | Solar | 05_05_321W9 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 24 | 0 | 24 | 08/29/2023 | 10/02/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 10/02/2023 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175122 | 01752 | 3000 | Solar | 05_09_704W1 | 08/17/2012 | 08/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2012 | 11/26/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 178613 | 02169 | 240 | Solar | 05_05_311W5 | 12/14/2017 | 12/14/2017 | 51 | 41 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 178002 | 02769 | 66.6 | Solar | 05_07_3W3 | 04/26/2017 | 04/26/2017 | 1 | 1 | 0 | 04/28/2017 | 04/28/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2017 |  | 5/2/2018 | N | EXP | 366 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 4/10/2018 | Connected |  | N
National Grid | SAUGUS | 327570 | 01906 | 11.4 | Solar | 05_05_3J3 | 03/16/2021 | 04/14/2021 | 21 | 21 | 0 | 04/15/2021 | 04/15/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 10/28/2022 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  | 9/26/2022 | Connected |  | N
National Grid | HEATH | 190922 | 01339 | 7.6 | Solar | 05_12_19W1 | 07/17/2018 | 08/09/2018 | 3 | 0 | 3 | 08/10/2018 | 08/10/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 174199 | 02072 | 450 | Solar | 05_09_1021W1 | 03/22/2012 | 03/22/2012 | 17 | 0 | 17 | 04/16/2012 | 04/16/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2012 |  | 9/30/2012 | N | EXP | 58 |  |  | 0 | 0 | 0 | 12/14/2012 | 12/14/2012 | 12/26/2012 | Connected |  | N
National Grid | BROCKTON | 638244 | 02302 | 990 | Solar | 05_07_94W42 | 07/08/2025 | 08/11/2025 | 23 | 13 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2025 | 09/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LONGMEADOW | 685312 | 01028 | 5.76 | Solar | 05_07_911W56 | 04/15/2025 | 05/13/2025 | 3 | 0 | 3 | 05/20/2025 | 05/20/2025 | 36 | 24 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLVILLE | 345986 | 01529 | 7.68 | Solar | 05_09_508L5 | 03/09/2021 | 03/18/2021 | 7 | 7 | 0 | 03/19/2021 | 03/19/2021 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 |  | 3/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2021 | Connected |  | N
National Grid | SHUTESBURY | 531948 | 01072 | 11.517 | Solar | 05_05_321W9 | 06/08/2023 | 08/08/2023 | 41 | 41 | 0 | 08/09/2023 | 08/09/2023 | 19 | 0 | 19 | 09/14/2023 | 10/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 10/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 10/13/2023 |  | 10/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 175121 | 01752 | 3000 | Solar | 05_09_704W1 | 08/17/2012 | 08/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2012 | 12/03/2012 | 49 | 0 | 49 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 194004 | 02169 | 136 | Solar | 05_05_311W5 | 08/30/2018 | 09/27/2018 | 8 | 5 | 3 | 09/28/2018 | 09/28/2018 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 |  | 12/12/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 204113 | 02771 | 86.6 | Solar | 05_07_3W3 | 01/11/2019 | 01/29/2019 | 11 | 6 | 5 | 01/30/2019 | 01/30/2019 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 358947 | 01906 | 9.54 | Solar | 05_05_3J3 | 05/18/2021 | 05/28/2021 | 7 | 4 | 3 | 06/01/2021 | 06/01/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  | 7/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ADAMS | 205535 | 01220 | 7.6 | Solar | 05_12_19W1 | 06/17/2019 | 06/21/2019 | 3 | 0 | 3 | 06/24/2019 | 06/24/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2019 | 06/17/2019 | 6/17/2020 | Y | EXP | 365 | 09/17/2019 | 10/25/2019 | 38 | 0 | 38 |  |  | 3/20/2020 | Connected |  | N
National Grid | BROCKTON | 174479 | 02301 | 1000 | Solar | 05_09_1021W1 | 04/19/2011 | 04/19/2011 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2012 | 04/19/2011 | 10/31/2012 | Y | STD | 282 | 07/26/2013 | 01/16/2014 | 118 | 0 | 118 | 12/11/2013 | 12/11/2013 | 12/13/2013 | Connected |  | N
National Grid | BROCKTON | 696434 | 02302 | 360 | Solar | 05_07_94W42 | 08/18/2025 |  | 135 | 127 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LONGMEADOW | 691906 | 01028 | 10.56 | Solar | 05_07_911W56 | 05/19/2025 | 05/29/2025 | 4 | 0 | 4 | 06/11/2025 | 06/11/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 8/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | BLACKSTONE | 350599 | 01504 | 6 | Solar | 05_09_508L5 | 04/02/2021 | 04/06/2021 | 1 | 1 | 0 | 04/07/2021 | 04/07/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2021 |  | 7/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/29/2021 | Connected |  | N
National Grid | SHUTESBURY | 540221 | 01072 | 10.15 | Solar | 05_05_321W9 | 07/24/2023 | 07/25/2023 | 2 | 1 | 1 | 07/26/2023 | 07/26/2023 | 72 | 52 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 07/24/2023 | 12/31/2024 | Y | EXP | 365 | 12/14/2023 | 01/14/2024 | 32 | 3 | 29 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 176019 | 01752 | 4500 | Solar | 05_09_704W1 | 03/20/2015 | 03/20/2015 | 17 | 14 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/15/2015 | 05/13/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2016 |  | 4/1/2019 | N | STD | 1132 | 08/04/2018 | 10/18/2018 | 75 | 0 | 75 |  |  | 3/27/2019 | Connected |  | N
National Grid | QUINCY | 200830 | 02169 | 10 | Solar | 05_05_311W5 | 11/09/2018 | 11/20/2018 | 4 | 0 | 4 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  | 12/16/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | SEEKONK | 306165 | 02771 | 100 | Solar | 05_07_3W3 | 10/08/2020 | 01/05/2022 | 27 | 20 | 7 | 11/20/2020 | 11/20/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 11/2/2022 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | SAUGUS | 600188 | 01906 | 10 | Solar | 05_05_3J3 | 03/29/2024 | 04/02/2024 | 3 | 2 | 1 | 04/03/2024 | 04/03/2024 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 4/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2024 | Connected |  | N
National Grid | CHESHIRE | 210103 | 01225 | 57.6 | Solar | 05_12_19W1 | 03/07/2019 | 03/12/2019 | 2 | 0 | 2 | 03/13/2019 | 03/13/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 1/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | STOUGHTON | 175140 | 02072 | 1500 | Solar | 05_09_1021W1 | 04/23/2013 | 04/23/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2013 | 06/14/2013 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/10/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 733055 | 02302 | 620 | Solar | 05_07_94W42 | 01/13/2026 |  | 36 | 30 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LONGMEADOW | 696892 | 01028 | 7.6 | Solar | 05_07_911W56 | 06/16/2025 | 07/15/2025 | 12 | 10 | 2 | 08/07/2025 | 08/07/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2025 | 06/16/2025 | 11/23/2026 | Y | EXP | 365 | 12/12/2025 | 01/03/2026 | 23 | 0 | 23 |  |  | 2/18/2026 | Connected |  | N
National Grid | BLACKSTONE | 433831 | 01504 | 0 | Solar | 05_09_508L5 | 06/02/2022 | 06/22/2022 | 13 | 11 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/24/2023 | Connected |  | N
National Grid | SHUTESBURY | 550614 | 01072 | 3.8 | Solar | 05_05_321W9 | 09/05/2023 | 09/06/2023 | 1 | 0 | 1 | 09/07/2023 | 09/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 09/05/2023 | 10/18/2024 | Y | EXP | 365 | 02/14/2024 | 04/18/2024 | 65 | 0 | 65 |  |  | 4/30/2024 | Connected |  | N
National Grid | MARLBOROUGH | 177556 | 01752 | 10 | Solar | 05_09_704W1 | 05/16/2017 | 05/16/2017 | 6 | 6 | 0 | 05/25/2017 | 05/25/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2017 | 05/16/2017 | 5/22/2018 | Y | EXP | 361 | 07/18/2017 | 07/26/2017 | 6 | 0 | 6 | 12/13/2017 | 12/13/2017 | 12/13/2017 | Connected |  | N
National Grid | QUINCY | 205105 | 02169 | 5 | Solar | 05_05_311W5 | 01/17/2019 | 01/30/2019 | 8 | 8 | 0 | 01/31/2019 | 01/31/2019 | 152 | 0 | 152 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 447739 | 02771 | 66 | Solar | 05_07_3W3 | 07/28/2022 | 11/03/2022 | 68 | 59 | 9 | 11/04/2022 | 11/04/2022 | 126 | 107 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 663788 | 01906 | 10 | Solar | 05_05_3J3 | 01/06/2025 | 01/07/2025 | 3 | 0 | 3 | 04/02/2025 | 04/02/2025 | 25 | 0 | 25 | 06/20/2025 | 07/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 07/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 8/25/2026 | N | EXP | 365 | 09/10/2025 | 12/22/2025 | 104 | 0 | 104 |  |  | 12/17/2025 | Connected |  | N
National Grid | ADAMS | 213005 | 01220 | 60 | Solar | 05_12_19W1 | 03/13/2019 | 03/18/2019 | 3 | 1 | 2 | 03/19/2019 | 03/19/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2019 |  | 1/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2020 | Connected |  | N
National Grid | STOUGHTON | 175353 | 02072 | 996.8 | Solar | 05_09_1021W1 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/10/2014 | 10/09/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2015 | 08/29/2014 | 12/31/2014 | Y | STD | 71 | 08/25/2015 | 11/23/2015 | 61 | 0 | 61 | 11/25/2015 | 11/25/2015 | 11/25/2015 | Connected |  | N
National Grid | BROCKTON | 174339 | 02302 | 1725 | Solar | 05_07_94W42 | 01/30/2012 | 01/30/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/23/2012 | 05/05/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 | 01/30/2012 | 12/31/2016 | Y | STD | 1363 | 08/20/2015 | 03/31/2016 | 151 | 0 | 151 | 4/5/2016 | 4/5/2016 | 4/5/2016 | Connected |  | N
National Grid | LONGMEADOW | 700159 | 01028 | 10 | Solar | 05_07_911W56 | 06/20/2025 | 08/05/2025 | 4 | 0 | 4 | 08/06/2025 | 08/06/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 06/20/2025 | 9/25/2026 | Y | EXP | 365 | 11/25/2025 | 12/16/2025 | 22 | 0 | 22 |  |  | 12/23/2025 | Connected |  | N
National Grid | BLACKSTONE | 457549 | 01504 | 10 | Solar | 05_09_508L5 | 10/17/2022 | 10/19/2022 | 2 | 0 | 2 | 10/20/2022 | 10/20/2022 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 10/17/2022 | 11/28/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2023 | Connected |  | N
National Grid | SHUTESBURY | 573979 | 01072 | 10 | Solar | 05_05_321W9 | 12/11/2023 | 12/12/2023 | 2 | 1 | 1 | 12/13/2023 | 12/13/2023 | 27 | 3 | 24 | 02/27/2024 | 03/27/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 03/27/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 3/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 184600 | 01752 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/12/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/18/2018 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 289784 | 02169 | 8.41 | Solar | 05_05_311W5 | 04/29/2020 | 05/05/2020 | 3 | 0 | 3 | 05/06/2020 | 05/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2020 |  | 4/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2021 | Connected |  | N
National Grid | REHOBOTH | 651204 | 02769 | 5.76 | Solar | 05_07_3W3 | 11/12/2024 | 12/11/2024 | 5 | 0 | 5 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 1/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2025 | Connected |  | N
National Grid | SAUGUS | 663829 | 01906 | 7.6 | Solar | 05_05_3J3 | 01/06/2025 | 01/21/2025 | 5 | 0 | 5 | 01/22/2025 | 01/22/2025 | 30 | 6 | 24 | 04/01/2025 | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 05/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 6/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ADAMS | 384858 | 01220 | 5 | Solar | 05_12_19W1 | 10/26/2021 | 12/21/2021 | 11 | 6 | 5 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 176159 | 02072 | 250 | Solar | 05_09_1021W1 | 02/04/2015 | 02/04/2015 | 3 | 1 | 2 | 02/11/2015 | 02/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2015 |  | 7/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 8/3/2015 | 8/3/2015 | 8/7/2015 | Connected |  | N
National Grid | BROCKTON | 174764 | 02302 | 332 | Solar | 05_07_94W42 | 08/23/2012 | 08/23/2012 | 11 | 3 | 8 | 09/11/2012 | 09/11/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2013 | 08/23/2012 | 11/30/2012 | Y | EXP | 59 | 02/28/2013 | 05/13/2013 | 47 | 0 | 47 | 5/28/2013 | 5/28/2013 | 5/30/2013 | Connected |  | N
National Grid | LONGMEADOW | 719315 | 01028 | 11.5 | Battery Add-On | 05_07_911W56 | 09/16/2025 | 09/22/2025 | 4 | 0 | 4 | 09/23/2025 | 09/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2025 |  | 11/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | MILLVILLE | 481092 | 01529 | 7.6 | Solar | 05_09_508L5 | 12/08/2022 | 12/28/2022 | 14 | 12 | 2 | 12/29/2022 | 12/29/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 |  | 2/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2023 | Connected |  | N
National Grid | SHUTESBURY | 579135 | 01072 | 8.775 | Solar | 05_05_321W9 | 01/03/2024 | 01/11/2024 | 6 | 3 | 3 | 01/12/2024 | 01/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 01/03/2024 | 3/7/2025 | Y | EXP | 365 | 04/09/2024 | 05/07/2024 | 29 | 0 | 29 |  |  | 6/15/2024 | Connected |  | N
National Grid | MARLBOROUGH | 184599 | 01752 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/18/2018 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 12/18/2018 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 324974 | 02169 | 115.2 | Solar | 05_05_311W5 | 11/10/2020 |  | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176128 | 02771 | 225 | Natural Gas | 05_07_3W4 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 | 04/14/2015 | 04/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 9/1/2015 | N | EXP | 138 |  |  | 0 | 0 | 0 | 8/14/2015 | 8/14/2015 | 8/25/2015 | Connected |  | N
National Grid | SAUGUS | 672868 | 01906 | 3.8 | Solar | 05_05_3J3 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ADAMS | 404787 | 01220 | 9.8 | Solar | 05_12_19W1 | 02/03/2022 | 02/07/2022 | 2 | 0 | 2 | 02/08/2022 | 02/08/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 176442 | 02072 | 10 | Solar | 05_09_1021W1 | 05/11/2016 | 05/11/2016 | 2 | 2 | 0 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/11/2016 | 5/17/2017 | Y | EXP | 345 | 09/21/2016 | 10/07/2016 | 12 | 0 | 12 | 11/7/2016 | 11/7/2016 | 11/10/2016 | Connected |  | N
National Grid | BROCKTON | 178270 | 02302 | 936 | Solar | 05_07_94W42 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/21/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 01/09/2018 | 11/30/2020 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  | 11/30/2020 | Connected |  | N
National Grid | LONGMEADOW | 206424 | 01028 | 5.76 | Solar | 05_07_911W57 | 01/22/2019 | 02/06/2019 | 10 | 0 | 10 | 02/07/2019 | 02/07/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 | 01/22/2019 | 2/18/2020 | Y | EXP | 365 | 06/26/2019 | 06/25/2019 | 0 | 0 | 0 |  |  | 7/4/2019 | Connected |  | N
National Grid | UXBRIDGE | 556511 | 01569 | 480 | Solar | 05_09_508L5 | 11/21/2023 |  | 196 | 186 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 626048 | 01072 | 15.08 | Solar | 05_05_321W9 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 34 | 22 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2024 | Connected |  | N
National Grid | MARLBOROUGH | 184598 | 01752 | 2998 | Solar | 05_09_704W1 | 09/13/2018 | 10/13/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/19/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 329523 | 02169 | 100.8 | Solar | 05_05_311W5 | 12/14/2020 | 12/21/2020 | 4 | 0 | 4 | 12/22/2020 | 12/22/2020 | 29 | 9 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 12/14/2020 |  | Y | EXP |  | 04/07/2021 | 12/20/2021 | 257 | 7 | 250 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 177988 | 02771 | 3 | Solar | 05_07_4J1 | 08/28/2017 | 08/28/2017 | 5 | 0 | 5 | 09/07/2017 | 09/07/2017 | 138 | 0 | 138 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/4/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 707934 | 01906 | 7.6 | Solar | 05_05_3J3 | 07/28/2025 | 08/27/2025 | 3 | 0 | 3 | 09/04/2025 | 09/04/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/24/2025 | Connected |  | N
National Grid | NORTH ADAMS | 409848 | 01247 | 8.376 | Solar | 05_12_19W1 | 02/01/2022 | 02/23/2022 | 16 | 15 | 1 | 02/24/2022 | 02/24/2022 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 | 02/01/2022 | 6/27/2023 | Y | EXP | 365 | 04/28/2022 | 06/15/2022 | 49 | 0 | 49 |  |  | 8/24/2022 | Connected |  | N
National Grid | STOUGHTON | 177210 | 02072 | 480 | Solar | 05_09_1021W1 | 06/07/2016 | 06/07/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2016 | 07/12/2016 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/13/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178269 | 02302 | 233.33 | Solar | 05_07_94W42 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/21/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2018 | 01/09/2018 | 12/31/2020 | Y | STD | 477 |  |  | 0 | 0 | 0 | 12/28/2020 | 12/24/2020 | 12/30/2020 | Connected |  | N
National Grid | LONGMEADOW | 257196 | 01028 | 7.6 | Solar | 05_07_911W57 | 10/17/2019 | 10/29/2019 | 7 | 5 | 2 | 10/30/2019 | 10/30/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2019 | 10/17/2019 | 7/21/2020 | Y | EXP | 365 | 01/11/2020 | 02/14/2020 | 34 | 0 | 34 |  |  | 3/2/2020 | Connected |  | N
National Grid | BLACKSTONE | 610542 | 01504 | 2.32 | Solar | 05_09_508L5 | 05/13/2024 | 06/03/2024 | 1 | 0 | 1 | 06/04/2024 | 06/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 05/13/2024 | 6/25/2025 | Y | EXP | 365 | 07/24/2024 | 09/17/2024 | 56 | 0 | 56 |  |  | 9/19/2024 | Connected |  | N
National Grid | SHUTESBURY | 647390 | 01072 | 7.6 | Solar | 05_05_321W9 | 10/22/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/22/2024 | 12/31/2025 | Y | EXP | 365 | 02/13/2025 | 03/03/2025 | 19 | 0 | 19 |  |  | 3/13/2025 | Connected |  | N
National Grid | MARLBOROUGH | 184597 | 01752 | 4998 | Solar | 05_09_704W1 | 09/13/2018 | 10/12/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2018 | 12/19/2018 | 64 | 45 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 355075 | 02169 | 166.6 | Solar | 05_05_311W5 | 05/21/2021 | 06/06/2021 | 9 | 0 | 9 |  |  | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 183802 | 02769 | 10 | Solar | 05_07_4J1 | 06/01/2018 | 06/01/2018 | 10 | 9 | 1 | 06/15/2018 | 06/15/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | LYNN | 737765 | 01905 | 22.8 | Solar | 05_05_4J1 | 12/03/2025 | 12/09/2025 | 4 | 1 | 3 | 12/10/2025 | 12/10/2025 | 59 | 43 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ADAMS | 445004 | 01220 | 10 | Solar | 05_12_19W1 | 07/25/2022 | 08/15/2022 | 15 | 15 | 0 | 08/16/2022 | 08/16/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 | 07/25/2022 | 9/29/2023 | Y | EXP | 365 | 03/23/2023 | 04/21/2023 | 30 | 0 | 30 |  |  | 5/1/2023 | Connected |  | N
National Grid | STOUGHTON | 177312 | 02072 | 1980 | Solar | 05_09_1021W1 | 02/09/2017 | 02/09/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/15/2017 | 02/22/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2018 | 02/09/2017 | 12/30/2021 | Y | STD | 1161 | 07/25/2019 | 11/30/2021 | 860 | 194 | 666 |  |  | 12/13/2021 | Connected |  | N
National Grid | BROCKTON | 178506 | 02302 | 2000 | Solar | 05_07_94W42 | 01/25/2018 | 03/15/2018 | 25 | 13 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/16/2018 | 05/01/2018 | 33 | 15 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 01/25/2018 | 4/21/2023 | Y | STD | 433 | 07/30/2022 | 01/14/2023 | 169 | 0 | 169 |  |  | 5/8/2023 | Connected |  | N
National Grid | LONGMEADOW | 391846 | 01028 | 0 | Other | 05_07_911W57 | 11/13/2021 | 01/05/2022 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 01/26/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILLVILLE | 612129 | 01529 | 6 | Solar | 05_09_508L5 | 05/20/2024 | 06/07/2024 | 2 | 0 | 2 | 06/10/2024 | 06/10/2024 | 66 | 58 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 05/20/2024 | 10/8/2025 | Y | EXP | 365 | 11/20/2024 | 12/03/2024 | 14 | 0 | 14 |  |  | 12/18/2024 | Connected |  | N
National Grid | SHUTESBURY | 656184 | 01002 | 10 | Solar | 05_05_321W9 | 11/21/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | MARLBOROUGH | 300938 | 01752 | 4998 | Solar | 05_09_704W1 | 10/29/2020 | 11/06/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 | 01/05/2021 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 365643 | 02171 | 7.54 | Solar | 05_05_311W5 | 07/07/2021 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 213972 | 02771 | 0 | Solar | 05_07_4J1 | 03/15/2019 | 03/25/2019 | 5 | 0 | 5 | 03/26/2019 | 03/26/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/5/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 375661 | 01905 | 100 | Solar | 05_05_4J1 | 08/18/2021 | 09/08/2021 | 14 | 3 | 11 |  |  | 80 | 47 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 08/18/2021 | 9/28/2023 | Y | STD | 46 | 04/25/2023 | 07/28/2023 | 95 | 75 | 20 |  |  | 9/13/2023 | Connected |  | N
National Grid | NORTH ADAMS | 469141 | 01247 | 10 | Solar | 05_12_19W1 | 10/20/2022 | 10/25/2022 | 3 | 0 | 3 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2022 | 10/20/2022 | 4/11/2024 | Y | EXP | 365 | 04/11/2023 | 04/10/2023 | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | STOUGHTON | 178412 | 02072 | 4980 | Solar | 05_09_1021W1 | 11/27/2017 | 11/27/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/18/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 | 11/27/2017 | 1/27/2021 | Y | STD | 932 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 178702 | 02302 | 358 | Solar | 05_07_94W42 | 02/09/2018 | 02/09/2018 | 10 | 0 | 10 | 03/12/2018 | 03/12/2018 | 44 | 0 | 44 | 06/21/2018 | 07/20/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  | 07/20/2018 | 21 | 4 | 17 |  |  | 0 | 0 | 0 | 8/3/2018 |  | 6/30/2020 | N | EXP | 329 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 406522 | 01028 | 120 | Solar | 05_07_911W57 | 01/13/2022 | 02/04/2022 | 16 | 10 | 6 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 639697 | 01504 | 480 | Solar | 05_09_508L5 | 09/12/2024 | 10/22/2024 | 13 | 7 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHUTESBURY | 661034 | 01002 | 10 | Solar | 05_05_321W9 | 12/17/2024 | 12/30/2024 | 3 | 0 | 3 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 | 12/17/2024 | 2/19/2026 | Y | EXP | 365 | 04/01/2025 | 03/31/2025 | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | MARLBOROUGH | 300932 | 01752 | 2000 | Solar | 05_09_704W1 | 10/29/2020 | 11/18/2020 | 13 | 7 | 6 |  |  | 39 | 21 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | QUINCY | 592139 | 02171 | 6 | Solar | 05_05_311W5 | 02/27/2024 | 03/05/2024 | 5 | 0 | 5 | 03/06/2024 | 03/06/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 | 02/27/2024 | 3/22/2026 | Y | EXP | 365 | 04/17/2024 | 04/16/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 646324 | 02766 | 7.6 | Solar | 05_07_4J1 | 10/10/2024 | 11/26/2024 | 12 | 8 | 4 | 11/27/2024 | 11/27/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/10/2024 | 1/3/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | LYNN | 375655 | 01905 | 50 | Solar | 05_05_4J1 | 08/18/2021 | 09/10/2021 | 16 | 6 | 10 | 09/13/2021 | 09/13/2021 | 288 | 262 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHESHIRE | 490857 | 01225 | 6 | Solar | 05_12_19W1 | 01/19/2023 | 01/20/2023 | 1 | 0 | 1 | 01/23/2023 | 01/23/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 267172 | 02072 | 8.7 | Solar | 05_09_1021W1 | 12/10/2019 | 12/16/2019 | 4 | 4 | 0 | 12/17/2019 | 12/17/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 | 12/10/2019 | 12/10/2020 | Y | EXP | 365 | 04/10/2020 | 05/07/2020 | 27 | 0 | 27 |  |  | 6/12/2020 | Connected |  | N
National Grid | BROCKTON | 208164 | 02302 | 2000 | Solar | 05_07_94W42 | 09/06/2019 | 09/19/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2019 | 10/03/2019 | 9 | 4 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 457927 | 01028 | 0 | Other | 05_07_911W57 | 10/17/2022 | 11/07/2022 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2022 | 11/23/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UXBRIDGE | 178552 | 01569 | 2800 | Solar | 05_09_509L1 | 03/12/2018 | 04/03/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2018 | 05/30/2018 | 41 | 26 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2022 | 03/12/2018 | 7/11/2026 | Y | STD | 11 | 02/19/2026 |  | 16 | 0 | 16 |  |  |  | Construction |  | N
National Grid | SHUTESBURY | 662714 | 01072 | 0 | Solar | 05_05_321W9 | 12/26/2024 | 12/31/2024 | 3 | 0 | 3 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/17/2025 | Connected |  | N
National Grid | MARLBOROUGH | 382341 | 01752 | 10 | Solar | 05_09_704W1 | 10/04/2021 | 01/04/2022 | 5 | 3 | 2 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2021 |  | 12/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/18/2022 | Connected |  | Y
National Grid | QUINCY | 647601 | 02171 | 7.6 | Solar | 05_05_311W5 | 10/18/2024 | 11/19/2024 | 8 | 5 | 3 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | NORTON | 175593 | 02766 | 132 | Solar | 05_07_4J2 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2014 |  | 11/28/2014 | N | EXP | 91 |  |  | 0 | 0 | 0 | 3/16/2015 | 3/16/2015 | 3/16/2015 | Connected |  | N
National Grid | LYNN | 644836 | 01905 | 5.76 | Solar | 05_05_4J1 | 10/15/2024 | 10/31/2024 | 6 | 2 | 4 | 11/01/2024 | 11/01/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | CHESHIRE | 502819 | 01225 | 3.8 | Solar | 05_12_19W1 | 02/23/2023 | 02/27/2023 | 2 | 0 | 2 | 02/28/2023 | 02/28/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 291641 | 02072 | 0 | Other | 05_09_1021W1 | 10/28/2020 | 12/02/2020 | 23 | 17 | 6 |  |  | 7 | 5 | 2 |  |  | 0 | 0 | 0 | 12/03/2020 | 02/08/2021 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 246166 | 02302 | 2000 | Solar | 05_07_94W42 | 08/28/2019 | 09/30/2019 | 22 | 17 | 5 |  |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/14/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LONGMEADOW | 535460 | 01028 | 6.615 | Solar | 05_07_911W57 | 08/04/2023 | 08/08/2023 | 3 | 2 | 1 | 08/09/2023 | 08/09/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 08/04/2023 | 8/31/2024 | Y | EXP | 365 | 10/18/2023 | 11/06/2023 | 20 | 0 | 20 |  |  | 11/9/2023 | Connected |  | N
National Grid | MILLVILLE | 724170 | 01529 |  | Battery Add-On | 05_09_509L1 | 10/17/2025 | 11/03/2025 | 10 | 6 | 4 | 11/04/2025 | 11/04/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SHUTESBURY | 689026 | 01072 | 5.2 | Solar | 05_05_321W9 | 05/05/2025 | 05/06/2025 | 1 | 0 | 1 | 05/07/2025 | 05/07/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 | 05/05/2025 | 8/18/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2025 | Connected |  | N
National Grid | MARLBOROUGH | 460940 | 01752 | 5.22 | Solar | 05_09_704W1 | 10/13/2022 | 10/17/2022 | 2 | 0 | 2 | 10/18/2022 | 10/18/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 |  | 11/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | Y
National Grid | QUINCY | 664880 | 02171 | 7.6 | Solar | 05_05_311W5 | 01/09/2025 | 01/31/2025 | 4 | 0 | 4 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 | 01/09/2025 | 3/19/2026 | Y | EXP | 365 | 03/25/2025 | 09/10/2025 | 170 | 0 | 170 |  |  | 10/14/2025 | Connected |  | N
National Grid | NORTON | 613587 | 02766 | 7.36 | Solar | 05_07_4J2 | 05/28/2024 | 06/05/2024 | 1 | 0 | 1 | 09/26/2024 | 09/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2024 | 05/28/2024 | 10/23/2025 | Y | EXP | 365 | 12/19/2024 | 02/04/2025 | 48 | 0 | 48 |  |  | 2/7/2025 | Connected |  | N
National Grid | LYNN | 177309 | 01905 | 287 | Solar | 05_05_4J2 | 11/17/2016 | 11/17/2016 | 3 | 3 | 0 | 11/22/2016 | 11/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2016 |  | 11/22/2017 | N | EXP | 334 |  |  | 0 | 0 | 0 | 6/21/2017 | 6/21/2017 | 6/22/2017 | Connected |  | N
National Grid | ADAMS | 510472 | 01220 | 6 | Solar | 05_12_19W1 | 04/06/2023 | 04/10/2023 | 2 | 0 | 2 | 04/11/2023 | 04/11/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/17/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 379398 | 02072 | 15.2 | Solar | 05_09_1021W1 | 09/01/2021 | 10/07/2021 | 25 | 24 | 1 | 10/08/2021 | 10/08/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2021 |  | 10/6/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 639911 | 02302 | 5.76 | Solar | 05_07_94W43 | 09/12/2024 | 10/09/2024 | 16 | 12 | 4 | 10/10/2024 | 10/10/2024 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/12/2024 | 12/18/2025 | Y | EXP | 365 | 04/01/2025 | 11/19/2025 | 233 | 0 | 233 |  |  |  | Completion Documents |  | N
National Grid | BELCHERTOWN | 562462 | 01007 | 11.4 | Solar | 05_07_911W57 | 10/20/2023 | 01/04/2024 | 51 | 50 | 1 | 01/05/2024 | 01/05/2024 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 | 10/20/2023 | 4/16/2025 | Y | EXP | 365 | 09/21/2024 | 10/03/2024 | 13 | 0 | 13 |  |  | 11/27/2024 | Connected |  | N
National Grid | BLACKSTONE | 742292 | 01504 | 13.36 | Solar | 05_09_509L1 | 12/26/2025 | 12/30/2025 | 12 | 10 | 2 | 02/26/2026 | 02/26/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHUTESBURY | 711738 | 01072 | 15.2 | Solar | 05_05_321W9 | 08/14/2025 | 08/21/2025 | 5 | 0 | 5 | 08/22/2025 | 08/22/2025 | 62 | 38 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2026 | Connected |  | N
National Grid | MARLBOROUGH | 477733 | 01752 | 0 | Solar | 05_09_704W1 | 11/15/2022 | 11/21/2022 | 4 | 2 | 2 | 11/22/2022 | 11/22/2022 | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  | 1/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2023 | Connected |  | N
National Grid | QUINCY | 703220 | 02171 | 7.6 | Solar | 05_05_311W5 | 07/08/2025 | 07/31/2025 | 2 | 0 | 2 | 08/01/2025 | 08/01/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | NORTON | 625176 | 02766 | 9.57 | Solar | 05_07_4J2 | 07/16/2024 | 08/26/2024 | 2 | 0 | 2 | 08/27/2024 | 08/27/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 | 07/16/2024 | 9/24/2025 | Y | EXP | 365 | 01/28/2025 | 01/27/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | LYNN | 524257 | 01905 | 0 | Other | 05_05_4L1 | 06/07/2023 | 01/10/2025 | 397 | 391 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/13/2025 | 07/25/2025 | 133 | 121 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ADAMS | 519497 | 01220 | 10 | Solar | 05_12_19W1 | 04/26/2023 | 05/09/2023 | 10 | 6 | 4 | 05/10/2023 | 05/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 | 04/26/2023 | 8/25/2024 | Y | EXP | 365 | 01/12/2024 | 03/04/2024 | 53 | 0 | 53 |  |  | 3/8/2024 | Connected |  | N
National Grid | STOUGHTON | 416760 | 02072 | 15.2 | Solar | 05_09_1021W1 | 03/09/2022 |  | 32 | 26 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 736705 | 02302 | 11.5 | Solar | 05_07_94W43 | 11/26/2025 | 11/28/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 534904 | 01007 | 3.84 | Solar | 05_07_911W59 | 06/22/2023 | 06/27/2023 | 3 | 0 | 3 | 06/28/2023 | 06/28/2023 | 72 | 54 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 | 06/22/2023 | 1/28/2025 | Y | EXP | 465 | 06/11/2025 | 08/05/2025 | 56 | 0 | 56 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 174846 | 01504 | 11.83 | Solar | 05_09_509L1 | 01/30/2013 | 01/30/2013 | 7 | 0 | 7 | 02/15/2013 | 02/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2013 |  | 4/30/2013 | N | EXP | 12 |  |  | 0 | 0 | 0 | 5/21/2013 | 5/21/2013 | 5/24/2013 | Connected |  | N
National Grid | SHUTESBURY | 568463 | 01072 | 3250 | Solar | 05_05_332W1 | 01/10/2024 | 05/20/2024 | 90 | 80 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/21/2024 | 08/07/2024 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MARLBOROUGH | 491819 | 01752 | 10 | Solar | 05_09_704W1 | 02/06/2023 | 02/08/2023 | 3 | 2 | 1 | 02/09/2023 | 02/09/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 | 02/06/2023 | 8/1/2024 | Y | EXP | 365 | 06/07/2023 | 08/28/2023 | 83 | 0 | 83 |  |  | 9/6/2023 | Connected |  | N
National Grid | QUINCY | 475389 | 02171 | 0 | Other | 05_05_311W6 | 12/08/2022 | 02/01/2023 | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2023 | 03/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2025 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | NORTON | 662234 | 02766 | 7.6 | Solar | 05_07_4J2 | 12/23/2024 | 01/07/2025 | 1 | 0 | 1 | 01/08/2025 | 01/08/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/23/2024 | 2/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | SAUGUS | 674641 | 01906 | 200 | Solar | 05_05_4L1 | 03/10/2025 | 07/08/2025 | 83 | 73 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ADAMS | 526047 | 01220 | 7.6 | Solar | 05_12_19W1 | 05/12/2023 | 05/15/2023 | 1 | 0 | 1 | 05/16/2023 | 05/16/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  | 11/8/2024 | N | EXP | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 426295 | 02301 | 15.2 | Solar | 05_09_1021W1 | 04/25/2022 | 04/26/2022 | 1 | 0 | 1 | 04/27/2022 | 04/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2022 | 04/25/2022 | 9/21/2023 | Y | EXP | 365 | 08/31/2022 | 09/21/2022 | 22 | 0 | 22 |  |  | 10/12/2022 | Connected |  | N
National Grid | BROCKTON | 742627 | 02302 | 11.5 | Solar | 05_07_94W43 | 12/30/2025 | 01/06/2026 | 4 | 0 | 4 | 01/07/2026 | 01/07/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELCHERTOWN | 177985 | 01007 | 15.36 | Solar | 05_07_911W59 | 08/28/2017 | 08/28/2017 | 143 | 142 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/4/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILLVILLE | 175068 | 01529 | 21.2 | Solar | 05_09_509L1 | 04/01/2013 | 04/01/2013 | 7 | 0 | 7 | 04/11/2013 | 04/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2013 |  | 4/8/2013 | N | EXP | 11 |  |  | 0 | 0 | 0 | 6/17/2013 | 6/17/2013 | 6/26/2013 | Connected |  | N
National Grid | AMHERST | 701040 | 01072 | 20 | Solar | 05_05_332W1 | 06/30/2025 | 07/03/2025 | 3 | 0 | 3 | 07/07/2025 | 07/07/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2025 |  | 8/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | MARLBOROUGH | 582306 | 01752 | 10 | Solar | 05_09_704W1 | 01/22/2024 | 01/25/2024 | 3 | 0 | 3 | 01/26/2024 | 01/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 | 01/22/2024 | 3/9/2025 | Y | EXP | 365 | 09/20/2024 | 10/22/2024 | 33 | 0 | 33 |  |  | 11/12/2024 | Connected |  | N
National Grid | QUINCY | 724550 | 02170 | 20.14 | Solar | 05_05_311W6 | 10/07/2025 | 10/20/2025 | 7 | 3 | 4 | 10/21/2025 | 10/21/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 190363 | 02766 | 7.6 | Solar | 05_07_5W1 | 07/10/2018 | 08/27/2018 | 5 | 4 | 1 | 08/28/2018 | 08/28/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/7/2018 | 07/10/2018 | 5/18/2020 | Y | EXP | 619 | 11/16/2019 | 12/10/2019 | 24 | 0 | 24 |  |  | 12/24/2019 | Connected |  | N
National Grid | SAUGUS | 674581 | 01906 | 200 | Solar | 05_05_4L1 | 03/10/2025 | 07/08/2025 | 83 | 73 | 10 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ADAMS | 559420 | 01220 | 3.8 | Solar | 05_12_19W1 | 10/13/2023 | 10/16/2023 | 1 | 0 | 1 | 10/17/2023 | 10/17/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 480218 | 02301 | 7.6 | Solar | 05_09_1021W1 | 01/09/2023 | 01/10/2023 | 1 | 0 | 1 | 01/11/2023 | 01/11/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 |  | 10/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 751771 | 02301 | 15.58 | Solar | 05_07_94W43 | 02/18/2026 |  | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BELCHERTOWN | 494772 | 01007 | 7.6 | Solar | 05_07_911W59 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2023 | 02/09/2023 | 12/17/2024 | Y | EXP | 365 | 08/09/2023 | 10/06/2023 | 59 | 0 | 59 |  |  | 4/13/2024 | Connected |  | N
National Grid | UPTON | 175266 | 01568 | 480 | Solar | 05_09_509L1 | 06/18/2014 | 06/18/2014 | 6 | 0 | 6 | 06/27/2014 | 06/27/2014 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/28/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 715951 | 01072 | 15.2 | Solar | 05_05_332W1 | 09/02/2025 | 10/03/2025 | 23 | 18 | 5 | 10/06/2025 | 10/06/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MARLBOROUGH | 593171 | 01752 | 0 | Solar | 05_09_704W1 | 02/28/2024 | 03/15/2024 | 12 | 9 | 3 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 4/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | QUINCY | 742327 | 02171 | 5.32 | Solar | 05_05_311W6 | 12/26/2025 | 12/30/2025 | 1 | 0 | 1 | 01/09/2026 | 01/09/2026 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 215677 | 02766 | 10 | Solar | 05_07_5W1 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 708171 | 01905 | 11.4 | Solar | 05_05_4L1 | 07/30/2025 | 08/04/2025 | 3 | 0 | 3 | 08/05/2025 | 08/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ADAMS | 537934 | 01220 | 3.8 | Solar | 05_12_19W1 | 07/06/2023 | 07/07/2023 | 1 | 0 | 1 | 07/10/2023 | 07/10/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 512682 | 02356 | 6 | Solar | 05_09_1021W1 | 04/05/2023 | 04/24/2023 | 12 | 11 | 1 | 04/25/2023 | 04/25/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 177795 | 02322 | 38.2 | Solar | 05_07_94W43 | 08/02/2017 | 08/02/2017 | 6 | 6 | 0 | 08/11/2017 | 08/11/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 | 08/02/2017 | 8/8/2018 | Y | EXP | 358 | 11/27/2017 | 12/06/2017 | 7 | 0 | 7 | 4/6/2018 | 4/6/2018 | 4/17/2018 | Connected |  | N
National Grid | BELCHERTOWN | 594316 | 01007 | 5 | Solar | 05_07_911W59 | 04/01/2024 | 04/15/2024 | 10 | 7 | 3 | 04/16/2024 | 04/16/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 |  | 4/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 175374 | 01756 | 1000 | Solar | 05_09_509L1 | 02/25/2014 | 02/25/2014 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/01/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 | 02/25/2014 | 12/31/2016 | Y | STD | 886 | 01/15/2016 | 05/25/2016 | 89 | 0 | 89 | 12/19/2017 | 12/19/2017 | 5/26/2016 | Connected |  | N
National Grid | SHUTESBURY | 744865 | 01072 | 5.76 | Solar | 05_05_332W1 | 01/12/2026 | 01/13/2026 | 3 | 0 | 3 | 01/26/2026 | 01/26/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MARLBOROUGH | 658352 | 01752 | 15.2 | Solar | 05_09_704W1 | 12/04/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 |  | 3/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | RANDOLPH | 175178 | 02368 | 1073.6 | Solar | 05_05_311W6 | 05/03/2013 | 05/03/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2013 | 07/02/2013 | 32 | 0 | 32 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 3/3/2014 |  | 12/31/2016 | N | STD | 134 |  |  | 0 | 0 | 0 | 12/18/2015 | 12/18/2015 | 12/21/2015 | Connected |  | N
National Grid | NORTON | 242725 | 02766 | 10 | Solar | 05_07_5W1 | 08/13/2019 | 09/04/2019 | 15 | 15 | 0 | 09/05/2019 | 09/05/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 08/13/2019 | 5/1/2020 | Y | EXP | 227 | 11/16/2019 | 12/19/2019 | 33 | 0 | 33 |  |  | 4/1/2020 | Connected |  | N
National Grid | LYNN | 734760 | 01905 | 0 | Battery Add-On | 05_05_4L1 | 11/18/2025 | 11/24/2025 | 3 | 0 | 3 | 11/25/2025 | 11/25/2025 | 44 | 22 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ADAMS | 575819 | 01220 | 6 | Solar | 05_12_19W1 | 12/11/2023 | 12/12/2023 | 2 | 1 | 1 | 12/13/2023 | 12/13/2023 | 46 | 21 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 12/11/2023 | 2/28/2025 | Y | EXP | 365 | 08/22/2024 | 10/23/2024 | 63 | 0 | 63 |  |  | 11/1/2024 | Connected |  | N
National Grid | BROCKTON | 515158 | 02301 | 6 | Solar | 05_09_1021W1 | 04/11/2023 | 04/14/2023 | 3 | 0 | 3 | 04/18/2023 | 04/18/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 382329 | 02301 | 240 | Solar | 05_07_94W43 | 11/11/2021 | 12/13/2021 | 22 | 15 | 7 | 12/14/2021 | 12/14/2021 | 25 | 2 | 23 | 03/01/2022 | 10/11/2022 | 131 | 0 | 131 |  |  | 0 | 0 | 0 |  | 10/11/2022 | 131 | 0 | 131 |  |  | 0 | 0 | 0 | 9/20/2022 | 11/11/2021 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 598335 | 01007 | 3.8 | Solar | 05_07_911W59 | 04/04/2024 | 04/08/2024 | 2 | 0 | 2 | 04/09/2024 | 04/09/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 176790 | 01747 | 7.6 | Solar | 05_09_509L1 | 01/14/2016 | 01/14/2016 | 6 | 6 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2016 | 01/14/2016 | 1/20/2017 | Y | EXP | 332 | 12/15/2016 | 01/10/2017 | 16 | 0 | 16 | 4/12/2017 | 4/12/2017 | 4/14/2017 | Connected |  | N
National Grid | SHUTESBURY | 749635 | 01072 | 20.242 | Solar | 05_05_332W1 | 02/06/2026 | 02/17/2026 | 5 | 3 | 2 | 02/18/2026 | 02/18/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MARLBOROUGH | 658943 | 01752 | 7.6 | Solar | 05_09_704W1 | 12/18/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 12/18/2024 | 2/11/2026 | Y | EXP | 365 | 06/14/2025 | 07/25/2025 | 42 | 0 | 42 |  |  | 7/30/2025 | Connected |  | N
National Grid | RANDOLPH | 176833 | 02368 | 10 | Solar | 05_05_311W6 | 02/28/2016 | 02/28/2016 | 3 | 3 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2016 |  | 3/5/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 7/19/2016 | 7/19/2016 | 7/19/2016 | Connected |  | N
National Grid | NORTON | 450193 | 02766 | 7.6 | Solar | 05_07_5W1 | 08/31/2022 | 09/02/2022 | 2 | 0 | 2 | 09/06/2022 | 09/06/2022 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 08/31/2022 | 3/7/2024 | Y | EXP | 365 | 02/24/2023 | 03/08/2023 | 13 | 0 | 13 |  |  | 3/13/2023 | Connected |  | N
National Grid | LYNN | 745584 | 01905 | 11.4 | Solar | 05_05_4L1 | 01/16/2026 | 01/21/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/10/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ADAMS | 575591 | 01220 | 3.8 | Solar | 05_12_19W1 | 12/13/2023 | 12/14/2023 | 2 | 1 | 1 | 12/15/2023 | 12/15/2023 | 31 | 6 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 570337 | 02072 | 7.6 | Solar | 05_09_1021W1 | 11/20/2023 | 11/29/2023 | 7 | 2 | 5 | 11/30/2023 | 11/30/2023 | 44 | 22 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 386450 | 02301 | 15.2 | Solar | 05_07_94W43 | 10/05/2021 | 01/05/2022 | 63 | 56 | 7 | 01/06/2022 | 01/06/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2022 |  | 2/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/2/2022 | Connected |  | N
National Grid | BELCHERTOWN | 650327 | 01007 | 3.8 | Solar | 05_07_911W59 | 10/31/2024 | 01/17/2025 | 39 | 34 | 5 | 01/21/2025 | 01/21/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 10/31/2024 | 2/26/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | HOPEDALE | 176916 | 01747 | 3.8 | Solar | 05_09_509L1 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2016 |  | 5/10/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 11/2/2016 | 11/2/2016 | 11/2/2016 | Connected |  | N
National Grid | SHUTESBURY | 754353 | 01072 | 96.5 | Solar | 05_05_332W1 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MARLBOROUGH | 672987 | 01752 | 40 | Solar | 05_09_704W1 | 03/13/2025 | 07/03/2025 | 75 | 65 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | Y
National Grid | RANDOLPH | 202096 | 02368 | 450 | Solar | 05_05_311W6 | 11/30/2018 | 12/21/2018 | 15 | 11 | 4 | 12/24/2018 | 12/24/2018 | 92 | 26 | 66 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 586990 | 02766 | 7.6 | Solar | 05_07_5W1 | 02/19/2024 | 06/03/2024 | 73 | 70 | 3 | 06/04/2024 | 06/04/2024 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 02/19/2024 | 8/21/2025 | Y | EXP | 365 | 07/18/2024 | 07/30/2024 | 13 | 0 | 13 |  |  | 10/24/2024 | Connected |  | N
National Grid | SAUGUS | 175527 | 01906 | 1600 | Solar | 05_05_4L1 | 07/29/2014 | 07/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2014 | 09/05/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2015 | 07/29/2014 | 5/1/2016 | Y | STD | 41 | 10/13/2016 | 02/28/2017 | 92 | 0 | 92 | 12/29/2016 | 12/29/2016 | 12/29/2016 | Connected |  | N
National Grid | ADAMS | 597865 | 01220 | 10 | Solar | 05_12_19W1 | 03/21/2024 | 03/25/2024 | 2 | 0 | 2 | 03/26/2024 | 03/26/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/24/2024 | Connected |  | N
National Grid | STOUGHTON | 652961 | 02072 | 3.8 | Solar | 05_09_1021W1 | 11/08/2024 | 11/25/2024 | 4 | 0 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 | 11/08/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | BROCKTON | 417294 | 02301 | 15.2 | Solar | 05_07_94W43 | 03/14/2022 | 03/15/2022 | 1 | 0 | 1 | 03/16/2022 | 03/16/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 5/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | BELCHERTOWN | 699623 | 01007 | 10 | Solar | 05_07_911W77 | 06/18/2025 | 07/02/2025 | 7 | 3 | 4 | 08/05/2025 | 08/05/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 06/18/2025 | 2/3/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MENDON | 177898 | 01756 | 7.6 | Solar | 05_09_509L1 | 06/15/2017 | 06/15/2017 | 10 | 10 | 0 | 06/29/2017 | 06/29/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2017 |  | 6/20/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  | 6/1/2018 | Connected |  | N
National Grid | SHUTESBURY | 175405 | 01072 | 1000 | Solar | 05_05_332W1 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/08/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 03/03/2014 | 7/15/2017 | Y | STD | 69 | 02/27/2017 | 08/03/2017 | 110 | 0 | 110 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | MARLBOROUGH | 692291 | 01752 | 10 | Solar | 05_09_704W1 | 06/06/2025 | 06/18/2025 | 10 | 5 | 5 | 09/17/2025 | 09/17/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | RANDOLPH | 229547 | 02368 | 240 | Solar | 05_05_311W6 | 05/20/2019 | 06/05/2019 | 9 | 4 | 5 | 06/06/2019 | 06/06/2019 | 40 | 27 | 13 | 09/03/2019 | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 |  | 10/07/2019 | 25 | 11 | 14 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 625180 | 02766 | 3.8 | Solar | 05_07_5W1 | 07/16/2024 | 07/29/2024 | 3 | 0 | 3 | 07/30/2024 | 07/30/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 07/16/2024 | 9/9/2025 | Y | EXP | 365 | 12/06/2024 | 12/17/2024 | 12 | 0 | 12 |  |  | 1/8/2025 | Connected |  | N
National Grid | LYNN | 175637 | 01905 | 1000 | Solar | 05_05_4L1 | 10/23/2014 | 10/23/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2014 | 12/03/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2015 | 10/23/2014 | 12/31/2016 | Y | STD | 646 | 04/25/2016 | 04/11/2017 | 240 | 0 | 240 | 4/28/2017 | 4/28/2017 | 4/28/2017 | Connected |  | N
National Grid | CHESHIRE | 599191 | 01225 | 10 | Solar | 05_12_19W1 | 04/18/2024 | 04/24/2024 | 4 | 0 | 4 | 04/25/2024 | 04/25/2024 | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 669278 | 02072 | 2158 | Solar | 05_09_1021W1 | 02/20/2025 | 03/21/2025 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2025 | 04/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 418873 | 02301 | 15.2 | Solar | 05_07_94W43 | 03/21/2022 | 03/22/2022 | 1 | 0 | 1 | 03/23/2022 | 03/23/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2022 |  | 6/30/2023 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  | 7/6/2023 | Connected |  | N
National Grid | BELCHERTOWN | 721880 | 01007 | 5.76 | Solar | 05_07_911W77 | 09/25/2025 | 10/09/2025 | 33 | 31 | 2 | 12/16/2025 | 12/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HOPEDALE | 178670 | 01747 | 4875 | Solar | 05_09_509L1 | 03/19/2018 | 03/19/2018 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2018 | 05/11/2018 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 175441 | 01072 | 1000 | Solar | 05_05_332W1 | 03/03/2014 | 03/03/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/13/2014 | 04/08/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 03/03/2014 | 7/15/2017 | Y | STD | 69 | 02/27/2017 | 08/03/2017 | 110 | 0 | 110 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | MARLBOROUGH | 177766 | 01752 | 2790 | Solar | 05_09_705W1 | 10/05/2017 | 10/24/2017 | 11 | 4 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2017 | 11/15/2017 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 296692 | 02368 | 10 | Solar | 05_05_311W6 | 06/16/2020 | 06/18/2020 | 1 | 0 | 1 | 06/19/2020 | 06/19/2020 | 51 | 26 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2021 | Connected |  | N
National Grid | NORTON | 714659 | 02766 | 10 | Solar | 05_07_5W2 | 08/26/2025 | 09/24/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 | 08/26/2025 | 12/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | SAUGUS | 175843 | 01906 | 998 | Solar | 05_05_4L1 | 05/19/2015 | 05/19/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2015 | 06/23/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 05/20/2015 |  | 711 | 116 | 595 | 4/28/2016 | 05/19/2015 | 10/30/2015 | Y | STD | 181 |  |  | 0 | 0 | 0 | 4/29/2016 | 4/29/2016 |  | Withdrawn |  | N
National Grid | ADAMS | 598390 | 01220 | 5 | Solar | 05_12_19W1 | 03/28/2024 | 04/01/2024 | 2 | 0 | 2 | 04/02/2024 | 04/02/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2024 | 03/28/2024 | 5/16/2025 | Y | EXP | 365 | 09/24/2024 | 12/19/2024 | 87 | 0 | 87 |  |  | 1/9/2025 | Connected |  | Y
National Grid | STOUGHTON | 680701 | 02072 | 7.6 | Solar | 05_09_1021W1 | 03/26/2025 | 06/24/2025 | 5 | 1 | 4 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/3/2025 | Connected |  | N
National Grid | BROCKTON | 420687 | 02302 | 15.2 | Solar | 05_07_94W43 | 03/29/2022 | 03/30/2022 | 1 | 0 | 1 | 03/31/2022 | 03/31/2022 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2022 |  | 4/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/8/2022 | Connected |  | N
National Grid | BELCHERTOWN | 725459 | 01007 | 11.5 | Solar | 05_07_911W77 | 10/11/2025 | 10/14/2025 | 1 | 0 | 1 | 10/15/2025 | 10/15/2025 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 | 10/11/2025 | 11/19/2026 | Y | EXP | 365 | 12/20/2025 | 03/05/2026 | 76 | 0 | 76 |  |  |  | Completion Documents |  | N
National Grid | MENDON | 184655 | 01756 | 990 | Solar | 05_09_509L1 | 05/11/2018 | 06/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2018 | 06/26/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHUTESBURY | 175477 | 01072 | 1000 | Solar | 05_05_332W1 | 03/12/2014 | 03/12/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2014 | 04/08/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 03/12/2014 | 7/31/2017 | Y | STD | 76 | 02/27/2017 | 08/03/2017 | 110 | 0 | 110 | 11/21/2017 | 11/21/2017 | 11/21/2017 | Connected |  | N
National Grid | MARLBOROUGH | 436398 | 01752 | 3373 | Other | 05_09_705W1 | 10/31/2022 | 04/17/2023 | 113 | 107 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 07/12/2023 | 59 | 40 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | RANDOLPH | 311656 | 02368 | 10 | Solar | 05_05_311W6 | 09/22/2020 | 09/24/2020 | 1 | 0 | 1 | 09/25/2020 | 09/25/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 | 09/22/2020 | 9/1/2021 | Y | EXP | 365 | 02/26/2021 | 03/12/2021 | 14 | 0 | 14 |  |  | 4/7/2021 | Connected |  | N
National Grid | NORTON | 716756 | 02766 | 13.8 | Solar | 05_07_5W2 | 09/10/2025 | 11/10/2025 | 40 | 34 | 6 | 11/12/2025 | 11/12/2025 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 176046 | 01906 | 480 | Solar | 05_05_4L1 | 08/18/2015 | 08/18/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 268 | 0 | 268 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHESHIRE | 600347 | 01220 | 7.6 | Solar | 05_12_19W1 | 04/12/2024 | 04/16/2024 | 1 | 0 | 1 | 04/17/2024 | 04/17/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/12/2024 | 5/7/2025 | Y | EXP | 365 | 08/20/2024 | 09/24/2024 | 36 | 0 | 36 |  |  | 10/4/2024 | Connected |  | N
National Grid | EASTON | 475135 | 02356 | 1250 | Solar | 05_09_1021W2 | 12/06/2022 | 01/26/2023 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/27/2023 | 03/03/2023 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2024 | 12/06/2022 | 11/15/2026 | Y | STD | 385 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | BROCKTON | 476653 | 02302 | 0 | Solar | 05_07_94W43 | 02/23/2024 | 07/16/2024 | 63 | 61 | 2 | 07/17/2024 | 07/17/2024 | 57 | 43 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 726046 | 01007 | 5 | Solar | 05_07_911W77 | 10/13/2025 | 11/18/2025 | 17 | 14 | 3 | 11/19/2025 | 11/19/2025 | 41 | 24 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MENDON | 184596 | 01756 | 4998 | Solar | 05_09_509L1 | 09/13/2018 | 10/15/2018 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 | 12/18/2018 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENDELL | 175553 | 01379 | 1000 | Solar | 05_05_332W1 | 04/15/2014 | 04/15/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/25/2014 | 05/15/2014 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2015 | 04/15/2014 | 8/10/2017 | Y | STD | 941 | 12/01/2016 | 07/14/2017 | 154 | 0 | 154 | 7/19/2017 | 7/19/2017 | 7/21/2017 | Connected |  | N
National Grid | MARLBOROUGH | 174661 | 01752 | 1000 | Solar | 05_09_705W1 | 12/11/2012 | 12/26/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2012 | 03/20/2013 | 49 | 0 | 49 |  |  | 0 | 0 | 0 | 02/06/2015 | 05/10/2018 | 176 | 0 | 176 | 2/6/2015 | 12/11/2012 | 12/31/2018 | Y | STD | 1424 | 11/15/2018 | 12/17/2018 | 32 | 0 | 32 |  |  | 12/28/2018 | Connected |  | N
National Grid | RANDOLPH | 473323 | 02368 | 120 | Solar | 05_05_311W6 | 11/14/2022 | 12/13/2022 | 20 | 11 | 9 | 12/14/2022 | 12/14/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 | 11/14/2022 | 7/24/2025 | Y | EXP | 245 | 12/04/2024 | 12/10/2024 | 7 | 0 | 7 |  |  | 2/27/2025 | Connected |  | N
National Grid | NORTON | 747514 | 02766 | 11.5 | Solar | 05_07_5W2 | 01/26/2026 | 01/30/2026 | 3 | 0 | 3 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 176500 | 01906 | 952 | Solar | 05_05_4L1 | 02/09/2016 | 02/09/2016 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/11/2016 | 03/09/2016 | 18 | 0 | 18 |  |  | 0 | 0 | 0 | 08/04/2016 | 08/04/2016 | 1 | 1 | 0 | 9/22/2016 |  | 3/30/2017 | N | STD | 189 |  |  | 0 | 0 | 0 | 3/27/2017 | 3/27/2017 | 3/29/2017 | Connected |  | N
National Grid | CHESHIRE | 608718 | 01225 | 5.76 | Solar | 05_12_19W1 | 05/03/2024 | 05/09/2024 | 0 | 0 | 0 | 05/10/2024 | 05/10/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 | 05/03/2024 | 12/28/2025 | Y | EXP | 365 | 09/25/2024 | 11/28/2024 | 65 | 0 | 65 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 535723 | 02072 | 100 | Solar | 05_09_1021W2 | 06/29/2023 | 08/16/2023 | 33 | 24 | 9 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  | 3/27/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | BROCKTON | 486030 | 02302 | 7.6 | Solar | 05_07_94W43 | 01/12/2023 | 01/18/2023 | 3 | 0 | 3 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 2/17/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2023 | Connected |  | N
National Grid | BELCHERTOWN | 728162 | 01007 | 5.76 | Solar | 05_07_911W77 | 10/21/2025 | 10/23/2025 | 2 | 0 | 2 | 10/24/2025 | 10/24/2025 | 57 | 43 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/26/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MENDON | 184683 | 01756 | 990 | Solar | 05_09_509L1 | 05/14/2018 | 06/04/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2018 | 06/15/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ERVING | 175658 | 01344 | 386 | Solar | 05_05_332W1 | 05/19/2014 | 05/19/2014 | 6 | 0 | 6 | 05/29/2014 | 05/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2014 | 05/19/2014 | 8/14/2015 | Y | EXP | 386 |  |  | 0 | 0 | 0 | 8/12/2014 | 8/12/2014 | 12/14/2016 | Connected |  | N
National Grid | MARLBOROUGH | 175185 | 01752 | 650 | Natural Gas | 05_09_705W1 | 05/10/2013 | 05/23/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2013 | 07/09/2013 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2013 |  | 6/30/2019 | N | STD | 229 |  |  | 0 | 0 | 0 |  |  | 5/17/2019 | Connected |  | N
National Grid | RANDOLPH | 588582 | 02368 | 5 | Solar | 05_05_311W6 | 03/11/2024 | 03/12/2024 | 1 | 0 | 1 | 03/13/2024 | 03/13/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 177291 | 02766 | 23.4 | Solar | 05_07_5W2 | 08/24/2016 | 08/24/2016 | 2 | 2 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2016 |  | 8/30/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/28/2016 | 10/28/2016 | 11/8/2016 | Connected |  | N
National Grid | SAUGUS | 177461 | 01906 | 998 | Solar | 05_05_4L1 | 12/12/2016 | 12/12/2016 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2017 | 12/12/2016 | 3/29/2019 | Y | STD | 813 | 09/01/2017 | 01/12/2018 | 84 | 0 | 84 |  |  | 3/28/2019 | Connected |  | N
National Grid | NORTH ADAMS | 614387 | 01247 | 6 | Solar | 05_12_19W1 | 05/31/2024 | 06/27/2024 | 4 | 3 | 1 | 06/28/2024 | 06/28/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 05/31/2024 | 1/19/2026 | Y | EXP | 365 | 08/22/2024 | 10/31/2024 | 71 | 0 | 71 |  |  | 5/9/2025 | Connected |  | N
National Grid | EASTON | 673634 | 02356 | 720 | Solar | 05_09_1021W2 | 05/27/2025 | 01/14/2026 | 157 | 148 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/15/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | BROCKTON | 491489 | 02302 | 7.6 | Solar | 05_07_94W43 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 34 | 14 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 11/1/2024 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  | 7/27/2024 | Connected |  | N
National Grid | BELCHERTOWN | 740711 | 01007 | 7.6 | Solar | 05_07_911W77 | 12/16/2025 | 12/17/2025 | 1 | 0 | 1 | 01/07/2026 | 01/07/2026 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MENDON | 188851 | 01756 | 4950 | Solar | 05_09_509L1 | 06/27/2018 | 06/27/2018 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2018 | 08/16/2018 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WENDELL | 176529 | 01379 | 7.6 | Solar | 05_05_332W1 | 12/16/2015 | 12/16/2015 | 3 | 3 | 0 | 12/22/2015 | 12/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/22/2016 | N | EXP | 353 |  |  | 0 | 0 | 0 | 8/29/2016 | 8/29/2016 | 8/29/2016 | Connected |  | N
National Grid | MARLBOROUGH | 175602 | 01752 | 5600 | Natural Gas | 05_09_705W1 | 10/17/2014 | 10/17/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2014 | 11/06/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2015 | 10/17/2014 | 12/31/2016 | Y | STD | 695 | 06/09/2015 | 11/17/2015 | 110 | 0 | 110 | 11/11/2015 | 11/11/2015 | 11/30/2015 | Connected |  | N
National Grid | RANDOLPH | 618845 | 02368 | 11.4 | Solar | 05_05_311W6 | 06/18/2024 | 07/09/2024 | 4 | 2 | 2 | 07/10/2024 | 07/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2024 | Connected |  | N
National Grid | NORTON | 202727 | 02766 | 7.6 | Solar | 05_07_5W2 | 12/06/2018 | 12/18/2018 | 7 | 0 | 7 | 12/19/2018 | 12/19/2018 | 201 | 0 | 201 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 |  | 12/6/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 178272 | 01906 | 966.6 | Solar | 05_05_4L1 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/10/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2018 | 01/09/2018 | 3/23/2021 | Y | STD | 757 |  |  | 0 | 0 | 0 | 2/9/2021 | 2/8/2021 | 3/23/2021 | Connected |  | N
National Grid | ADAMS | 619336 | 01220 | 7.6 | Solar | 05_12_19W1 | 06/21/2024 | 07/22/2024 | 4 | 2 | 2 | 07/23/2024 | 07/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 723560 | 02072 | 17.6 | Solar | 05_09_1021W2 | 10/02/2025 | 10/09/2025 | 4 | 0 | 4 | 10/10/2025 | 10/10/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 494553 | 02302 | 19 | Solar | 05_07_94W43 | 01/24/2023 | 01/25/2023 | 2 | 1 | 1 | 01/26/2023 | 01/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 |  | 3/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/15/2023 | Connected |  | N
National Grid | BELCHERTOWN | 742090 | 01007 | 5.76 | Solar | 05_07_911W77 | 12/23/2025 | 12/29/2025 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 23 | 11 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MENDON | 216596 | 01756 | 15.2 | Solar | 05_09_509L1 | 04/01/2019 | 04/09/2019 | 5 | 0 | 5 | 04/10/2019 | 04/10/2019 | 17 | 15 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2019 | 04/01/2019 | 5/6/2020 | Y | EXP | 365 | 08/06/2019 | 08/19/2019 | 13 | 0 | 13 |  |  | 9/18/2019 | Connected |  | N
National Grid | ERVING | 176527 | 01344 | 10 | Solar | 05_05_332W1 | 12/14/2015 | 12/14/2015 | 2 | 2 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2016 |  | 12/20/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 4/25/2016 | 4/25/2016 | 4/27/2016 | Connected |  | N
National Grid | MARLBOROUGH | 175689 | 01752 | 480 | Solar | 05_09_705W1 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 643293 | 02368 | 10 | Solar | 05_05_311W6 | 09/27/2024 | 10/11/2024 | 4 | 0 | 4 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/27/2024 | 11/30/2025 | Y | EXP | 365 | 04/03/2025 | 04/09/2025 | 7 | 0 | 7 |  |  | 9/24/2025 | Connected |  | N
National Grid | NORTON | 292717 | 02766 | 0 | Battery Add-On | 05_07_5W2 | 05/21/2020 | 06/08/2020 | 10 | 10 | 0 | 06/09/2020 | 06/09/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 6/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/12/2020 | Connected |  | N
National Grid | LYNN | 188651 | 01905 | 1380 | Solar | 05_05_4L1 | 07/17/2018 | 08/15/2018 | 21 | 12 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2018 | 09/27/2018 | 33 | 13 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2019 | 07/17/2018 | 1/18/2023 | Y | STD | 36 | 06/05/2021 | 09/29/2022 | 482 | 373 | 109 |  |  | 3/27/2023 | Connected |  | N
National Grid | ADAMS | 630093 | 01220 | 5 | Solar | 05_12_19W1 | 08/13/2024 | 08/19/2024 | 4 | 0 | 4 | 08/20/2024 | 08/20/2024 | 81 | 58 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 724591 | 02072 | 50 | Solar | 05_09_1021W2 | 10/22/2025 | 11/18/2025 | 16 | 8 | 8 | 11/19/2025 | 11/19/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 553165 | 02302 | 10 | Solar | 05_07_94W43 | 09/08/2023 | 11/13/2023 | 44 | 43 | 1 | 11/14/2023 | 11/14/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 |  | 3/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 747142 | 01007 | 11.5 | Solar | 05_07_911W77 | 01/23/2026 | 02/26/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HOPEDALE | 239719 | 01747 | 172.8 | Solar | 05_09_509L1 | 06/24/2019 | 07/11/2019 | 4 | 0 | 4 |  |  | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ERVING | 176965 | 01344 | 7.6 | Solar | 05_05_332W1 | 07/19/2016 | 07/19/2016 | 4 | 4 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2016 | 07/19/2016 | 7/24/2017 | Y | EXP | 353 | 12/05/2016 | 03/13/2017 | 66 | 0 | 66 | 3/17/2017 | 3/17/2017 | 3/17/2017 | Connected |  | N
National Grid | MARLBOROUGH | 175764 | 01752 | 480 | Solar | 05_09_705W1 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 662998 | 02368 | 3.8 | Solar | 05_05_311W6 | 12/30/2024 | 01/22/2025 | 4 | 0 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 | 12/30/2024 | 3/11/2026 | Y | EXP | 365 | 05/06/2025 | 12/22/2025 | 231 | 0 | 231 |  |  | 11/26/2025 | Connected |  | N
National Grid | NORTON | 307448 | 02766 | 8.99 | Solar | 05_07_5W2 | 08/18/2020 | 09/15/2020 | 19 | 19 | 0 | 09/16/2020 | 09/16/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 9/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2021 | Connected |  | N
National Grid | SAUGUS | 206720 | 01906 | 180 | Solar | 05_05_4L1 | 02/13/2019 | 03/07/2019 | 13 | 10 | 3 | 03/08/2019 | 03/08/2019 | 20 | 14 | 6 | 04/11/2019 | 07/17/2019 | 67 | 47 | 20 |  |  | 0 | 0 | 0 |  | 07/17/2019 | 67 | 47 | 20 |  |  | 0 | 0 | 0 | 7/29/2019 |  | 9/10/2020 | N | EXP | 24 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ADAMS | 632559 | 01220 | 5.76 | Solar | 05_12_19W1 | 08/14/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/14/2024 | 10/14/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | BROCKTON | 725386 | 02301 | 184.32 | Solar | 05_09_1021W2 | 10/20/2025 |  | 93 | 25 | 68 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BROCKTON | 560639 | 02302 | 6 | Solar | 05_07_94W43 | 10/23/2023 | 10/25/2023 | 2 | 0 | 2 | 10/26/2023 | 10/26/2023 | 38 | 14 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 10/23/2023 | 1/1/2025 | Y | EXP | 365 | 03/05/2024 | 03/26/2024 | 22 | 0 | 22 |  |  | 4/17/2024 | Connected |  | N
National Grid | BELCHERTOWN | 174896 | 01007 | 13 | Solar | 05_07_911W77 | 08/06/2012 | 08/06/2012 | 6 | 0 | 6 | 08/16/2012 | 08/16/2012 | 142 | 0 | 142 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 246259 | 01756 | 9.84 | Solar | 05_09_509L1 | 10/02/2019 | 10/07/2019 | 3 | 2 | 1 | 10/08/2019 | 10/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 | 10/02/2019 | 5/18/2020 | Y | EXP | 365 | 12/19/2019 | 01/03/2020 | 15 | 0 | 15 |  |  | 5/15/2020 | Connected |  | N
National Grid | WENDELL | 177147 | 01379 | 480 | Solar | 05_05_332W1 | 08/09/2016 | 08/09/2016 | 0 | 0 | 0 | 08/09/2016 | 08/09/2016 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/14/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 178466 | 01752 | 4800 | Solar | 05_09_705W1 | 01/23/2018 | 01/23/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2018 | 03/22/2018 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/29/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 670581 | 02368 | 3.8 | Solar | 05_05_311W6 | 02/06/2025 | 02/18/2025 | 2 | 0 | 2 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2025 | Connected |  | N
National Grid | NORTON | 388130 | 02766 | 3.84 | Solar | 05_07_5W2 | 11/10/2021 | 12/13/2021 | 3 | 0 | 3 | 11/17/2021 | 11/17/2021 | 42 | 22 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 248702 | 01905 | 10 | Solar | 05_05_4L1 | 08/14/2019 | 08/14/2019 | 0 | 0 | 0 | 08/15/2019 | 08/15/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2019 | 08/14/2019 | 9/25/2020 | Y | EXP | 365 | 04/03/2020 | 05/22/2020 | 49 | 0 | 49 |  |  | 7/16/2020 | Connected |  | N
National Grid | NORTH ADAMS | 645102 | 01247 | 3.8 | Solar | 05_12_19W1 | 10/04/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 35 | 11 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2025 | Connected |  | N
National Grid | BROCKTON | 742441 | 02301 | 0 | Battery Add-On | 05_09_1021W2 | 12/29/2025 | 01/02/2026 | 3 | 0 | 3 | 01/22/2026 | 01/22/2026 | 20 | 7 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 572141 | 02302 | 6 | Solar | 05_07_94W43 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  | 1/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2024 | Connected |  | N
National Grid | BELCHERTOWN | 175190 | 01007 | 60 | Solar | 05_07_911W77 | 11/19/2013 | 11/19/2013 | 4 | 0 | 4 | 11/26/2013 | 11/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2014 |  | 1/31/2014 | N | EXP | 33 |  |  | 0 | 0 | 0 | 9/24/2014 | 9/24/2014 | 12/11/2014 | Connected |  | N
National Grid | MENDON | 271263 | 01756 | 25 | Solar | 05_09_509L1 | 12/31/2019 | 01/29/2020 | 19 | 18 | 1 | 01/30/2020 | 01/30/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2020 | Connected |  | N
National Grid | WENDELL | 184667 | 01379 | 2200 | Solar | 05_05_332W1 | 05/09/2018 | 05/09/2018 | 18 | 12 | 6 |  |  | 41 | 35 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 178652 | 01752 | 1125 | Solar | 05_09_705W1 | 12/18/2017 | 12/18/2017 | 30 | 14 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 02/24/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/24/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 671735 | 02368 | 3.8 | Solar | 05_05_311W6 | 02/12/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 | 02/12/2025 | 4/15/2026 | Y | EXP | 365 | 04/30/2025 | 11/21/2025 | 206 | 0 | 206 |  |  | 11/25/2025 | Connected |  | N
National Grid | NORTON | 457785 | 02766 | 10 | Solar | 05_07_5W2 | 09/15/2022 | 09/16/2022 | 1 | 0 | 1 | 09/19/2022 | 09/19/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 375342 | 01905 | 36 | Solar | 05_05_4L1 | 08/18/2021 | 09/10/2021 | 16 | 6 | 10 | 09/13/2021 | 09/13/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2021 |  | 4/7/2023 | N | EXP | 52 |  |  | 0 | 0 | 0 |  |  | 4/19/2023 | Connected |  | N
National Grid | ADAMS | 646486 | 01220 | 5 | Solar | 05_12_19W1 | 10/11/2024 |  | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 174742 | 02072 | 75 | Solar | 05_09_1021W2 | 06/24/2013 | 06/24/2013 | 6 | 0 | 6 | 07/03/2013 | 07/03/2013 | 204 | 0 | 204 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2013 |  | 11/29/2013 | N | EXP | 129 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOLBROOK | 592215 | 02343 | 8.832 | Solar | 05_07_94W43 | 02/28/2024 | 03/22/2024 | 17 | 15 | 2 | 03/25/2024 | 03/25/2024 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 175189 | 01007 | 60 | Solar | 05_07_911W77 | 11/19/2013 | 11/19/2013 | 4 | 0 | 4 | 11/26/2013 | 11/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2014 |  | 1/31/2014 | N | EXP | 33 |  |  | 0 | 0 | 0 | 9/24/2014 | 9/24/2014 | 12/11/2014 | Connected |  | N
National Grid | HOPEDALE | 295754 | 01747 | 7.54 | Solar | 05_09_509L1 | 07/09/2020 | 07/17/2020 | 5 | 0 | 5 | 07/20/2020 | 07/20/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/09/2020 | 5/3/2021 | Y | EXP | 365 | 02/21/2021 | 02/24/2021 | 2 | 0 | 2 |  |  | 4/28/2021 | Connected |  | N
National Grid | WENDELL | 186698 | 01380 | 4560 | Solar | 05_05_332W1 | 06/20/2018 | 07/03/2018 | 9 | 6 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/05/2018 | 08/08/2018 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2019 | 06/20/2018 | 9/30/2024 | Y | STD | 1534 | 01/14/2023 | 09/20/2023 | 250 | 41 | 209 |  |  | 9/30/2024 | Connected |  | N
National Grid | MARLBOROUGH | 184433 | 01752 | 2600 | Solar | 05_09_705W1 | 05/03/2018 | 05/03/2018 | 11 | 1 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2018 | 06/01/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 672840 | 02368 | 3.8 | Solar | 05_05_311W6 | 02/19/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2025 | Connected |  | N
National Grid | NORTON | 465464 | 02766 | 6 | Solar | 05_07_5W2 | 10/20/2022 | 10/25/2022 | 3 | 0 | 3 | 10/26/2022 | 10/26/2022 | 261 | 247 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 434014 | 01906 | 0 | Battery Add-On | 05_05_4L1 | 10/18/2022 | 04/12/2023 | 120 | 112 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2023 | 05/15/2023 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ADAMS | 651448 | 01220 | 3.8 | Solar | 05_12_19W1 | 11/12/2024 | 12/10/2024 | 4 | 0 | 4 | 12/11/2024 | 12/11/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | STOUGHTON | 175262 | 02072 | 1000 | Solar | 05_09_1021W2 | 01/13/2015 | 01/13/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2015 | 02/20/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 599024 | 02351 | 6 | Solar | 05_07_94W43 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2024 | Connected |  | N
National Grid | BELCHERTOWN | 175366 | 01007 | 984 | Solar | 05_07_911W77 | 11/17/2014 | 11/17/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 | 12/23/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BLACKSTONE | 330957 | 01504 | 0 | Solar | 05_09_509L1 | 12/10/2020 | 01/04/2021 | 15 | 11 | 4 | 01/05/2021 | 01/05/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 1/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2021 | Connected |  | N
National Grid | WENDELL | 186842 | 01379 | 2875 | Solar | 05_05_332W1 | 06/11/2018 | 06/11/2018 | 22 | 0 | 22 |  |  | 30 | 5 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 185644 | 01752 | 220 | Solar | 05_09_705W1 | 05/17/2018 | 05/17/2018 | 32 | 17 | 15 | 07/05/2018 | 07/05/2018 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 678199 | 02368 | 13.36 | Solar | 05_05_311W6 | 03/14/2025 | 04/10/2025 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 477574 | 02766 | 10 | Solar | 05_07_5W2 | 11/18/2022 | 11/22/2022 | 2 | 0 | 2 | 11/23/2022 | 11/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/18/2022 | 12/19/2024 | Y | EXP | 365 | 10/26/2023 | 11/29/2023 | 35 | 0 | 35 |  |  | 1/5/2024 | Connected |  | N
National Grid | SAUGUS | 457393 | 01906 | 10 | Solar | 05_05_4L1 | 10/06/2022 | 10/10/2022 | 2 | 0 | 2 | 10/11/2022 | 10/11/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2022 | 10/06/2022 | 2/15/2024 | Y | EXP | 365 | 03/25/2023 | 04/20/2023 | 27 | 0 | 27 |  |  | 4/24/2023 | Connected |  | N
National Grid | ADAMS | 651708 | 01220 | 22.8 | Solar | 05_12_19W1 | 11/03/2024 |  | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 175348 | 02072 | 139.2 | Solar | 05_09_1021W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 |  | 10/31/2014 | N | EXP | 94 |  |  | 0 | 0 | 0 | 7/29/2014 | 7/29/2014 | 12/22/2014 | Connected |  | N
National Grid | ABINGTON | 636421 | 02351 | 23 | Battery Add-On | 05_07_94W43 | 08/29/2024 | 10/14/2024 | 12 | 11 | 1 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  | 11/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2025 | Connected |  | N
National Grid | BELCHERTOWN | 175568 | 01007 | 10 | Solar | 05_07_911W77 | 10/09/2014 | 10/09/2014 | 6 | 0 | 6 | 10/21/2014 | 10/21/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2015 |  | 2/9/2015 | N | EXP | 33 |  |  | 0 | 0 | 0 | 2/4/2015 | 2/4/2015 | 7/27/2016 | Connected |  | N
National Grid | BLACKSTONE | 348410 | 01504 | 9.6 | Solar | 05_09_509L1 | 03/23/2021 | 03/24/2021 | 0 | 0 | 0 | 03/25/2021 | 03/25/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/23/2021 | 3/23/2022 | Y | EXP | 365 | 07/17/2021 | 08/06/2021 | 21 | 0 | 21 |  |  | 8/10/2021 | Connected |  | N
National Grid | WENDELL | 215931 | 01379 | 4990 | Solar | 05_05_332W1 | 08/06/2019 | 08/19/2019 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2019 | 09/12/2019 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MARLBOROUGH | 188655 | 01752 | 3100 | Solar | 05_09_705W1 | 11/16/2018 | 12/03/2018 | 8 | 0 | 8 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 571788 | 02368 | 0 | Other | 05_05_312W1 | 01/11/2024 | 04/22/2025 | 317 | 307 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/23/2025 | 05/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | NORTON | 481663 | 02766 | 7.6 | Solar | 05_07_5W2 | 12/12/2022 | 12/14/2022 | 2 | 0 | 2 | 12/15/2022 | 12/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 | 12/12/2022 | 10/6/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2024 | Connected |  | N
National Grid | LYNN | 668576 | 01905 | 10 | Solar | 05_05_4L1 | 01/29/2025 | 02/13/2025 | 4 | 0 | 4 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | ADAMS | 654963 | 01220 | 22.8 | Solar | 05_12_19W1 | 11/22/2024 | 11/27/2024 | 3 | 2 | 1 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/22/2024 | 3/13/2026 | Y | EXP | 365 | 07/02/2025 | 11/03/2025 | 125 | 0 | 125 |  |  | 7/9/2025 | Connected |  | N
National Grid | STOUGHTON | 175491 | 02072 | 480 | Solar | 05_09_1021W2 | 07/25/2014 | 07/25/2014 | 7 | 0 | 7 | 08/06/2014 | 08/06/2014 | 89 | 0 | 89 | 10/01/2014 | 12/11/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  | 12/11/2014 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 4/1/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 645351 | 02302 | 3.8 | Solar | 05_07_94W43 | 10/08/2024 | 11/04/2024 | 6 | 1 | 5 | 11/05/2024 | 11/05/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/08/2024 | 12/12/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | Y
National Grid | BELCHERTOWN | 177368 | 01007 | 5.2 | Solar | 05_07_911W77 | 09/02/2016 | 09/02/2016 | 1 | 1 | 0 | 09/06/2016 | 09/06/2016 | 101 | 0 | 101 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2016 |  | 9/7/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 356005 | 01756 | 9.8 | Solar | 05_09_509L1 | 06/10/2021 | 12/30/2021 | 3 | 0 | 3 | 06/16/2021 | 06/16/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2021 | 06/10/2021 | 4/21/2023 | Y | EXP | 365 | 03/08/2022 | 04/21/2022 | 45 | 0 | 45 |  |  | 6/7/2022 | Connected |  | N
National Grid | WENDELL | 244271 | 01379 | 0 | Battery Add-On | 05_05_332W1 | 07/30/2019 | 08/02/2019 | 2 | 0 | 2 | 08/05/2019 | 08/05/2019 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  | 10/22/2019 | Connected |  | N
National Grid | MARLBOROUGH | 192888 | 01752 | 1000 | Solar | 05_09_705W1 | 09/07/2018 | 09/25/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 11/07/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 660928 | 02368 | 5.76 | Solar | 05_05_312W1 | 12/16/2024 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 12/16/2024 | 3/19/2026 | Y | EXP | 365 | 05/29/2025 | 05/28/2025 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 517154 | 02766 | 7.875 | Solar | 05_07_5W2 | 04/19/2023 | 04/20/2023 | 1 | 0 | 1 | 04/21/2023 | 04/21/2023 | 45 | 22 | 23 | 07/18/2023 | 08/24/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 08/24/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 8/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 685410 | 01906 | 11.5 | Solar | 05_05_4L1 | 04/15/2025 | 06/02/2025 | 3 | 0 | 3 | 06/03/2025 | 06/03/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 | 04/15/2025 | 7/8/2026 | Y | EXP | 365 | 09/03/2025 | 09/17/2025 | 15 | 0 | 15 |  |  | 9/25/2025 | Connected |  | N
National Grid | NORTH ADAMS | 658152 | 01247 | 10 | Solar | 05_12_19W1 | 12/05/2024 | 12/30/2024 | 8 | 3 | 5 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EASTON | 175711 | 02356 | 499 | Solar | 05_09_1021W2 | 10/25/2014 | 10/25/2014 | 10 | 8 | 2 | 11/10/2014 | 11/10/2014 | 0 | 0 | 0 | 12/24/2014 | 02/24/2015 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 02/24/2015 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 2/24/2015 | 10/25/2014 | 12/31/2016 | Y | EXP | 676 | 10/11/2016 | 11/28/2016 | 32 | 0 | 32 |  |  | 11/14/2016 | Connected |  | N
National Grid | HOLBROOK | 654730 | 02343 | 15.356 | Solar | 05_07_94W43 | 01/08/2025 | 01/21/2025 | 9 | 7 | 2 | 01/22/2025 | 01/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/27/2025 | Connected |  | N
National Grid | BELCHERTOWN | 183971 | 01007 | 9.92 | Solar | 05_07_911W77 | 05/22/2018 | 05/22/2018 | 27 | 13 | 14 | 06/14/2018 | 06/14/2018 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2019 | Connected |  | N
National Grid | BLACKSTONE | 483456 | 01504 | 10 | Solar | 05_09_509L1 | 01/16/2023 | 01/17/2023 | 1 | 0 | 1 | 01/18/2023 | 01/18/2023 | 43 | 24 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 01/16/2023 | 5/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2023 | Connected |  | N
National Grid | WENDELL | 289521 | 01379 | 4990 | Solar | 05_05_332W1 | 05/11/2020 | 05/20/2020 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/21/2020 | 06/23/2020 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 196745 | 01581 | 10 | Solar | 05_09_705W1 | 09/24/2018 | 10/24/2018 | 18 | 17 | 1 | 10/25/2018 | 10/25/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2018 | 09/24/2018 | 3/11/2019 | Y | EXP | 132 | 02/02/2019 | 02/22/2019 | 20 | 0 | 20 |  |  | 3/5/2019 | Connected |  | N
National Grid | RANDOLPH | 739032 | 02368 | 0 | Battery Add-On | 05_05_312W1 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 572680 | 02766 | 5 | Solar | 05_07_5W2 | 12/04/2023 | 12/05/2023 | 1 | 0 | 1 | 12/06/2023 | 12/06/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 12/04/2023 | 2/4/2025 | Y | EXP | 365 | 05/14/2024 | 05/13/2024 | 0 | 0 | 0 |  |  | 5/17/2024 | Connected |  | N
National Grid | SAUGUS | 704849 | 01906 | 23 | Solar | 05_05_4L1 | 07/15/2025 | 08/11/2025 | 19 | 15 | 4 | 08/12/2025 | 08/12/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2025 | Connected |  | Y
National Grid | NORTH ADAMS | 659661 | 01247 | 10 | Solar | 05_12_19W1 | 12/16/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 | 12/16/2024 | 2/21/2026 | Y | EXP | 365 | 07/02/2025 | 11/21/2025 | 143 | 0 | 143 |  |  | 11/26/2025 | Connected |  | N
National Grid | EASTON | 175944 | 02356 | 1000 | Solar | 05_09_1021W2 | 01/21/2015 | 01/21/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2015 | 02/27/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 697835 | 02302 | 14.82 | Solar | 05_07_94W43 | 06/11/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 24 | 12 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2025 | 06/11/2025 | 8/18/2026 | Y | EXP | 365 | 10/30/2025 | 02/11/2026 | 105 | 0 | 105 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 214779 | 01007 | 7.6 | Solar | 05_07_911W77 | 03/21/2019 | 04/10/2019 | 14 | 14 | 0 | 04/11/2019 | 04/11/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2019 |  | 4/14/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 498622 | 01756 | 0 | Solar | 05_09_509L1 | 02/02/2023 | 06/12/2023 | 90 | 88 | 2 | 06/13/2023 | 06/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 8/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2024 | Connected |  | N
National Grid | WENDELL | 294557 | 01379 | 0 | Solar | 05_05_332W1 | 06/04/2020 | 06/11/2020 | 4 | 2 | 2 | 06/12/2020 | 06/12/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 7/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2021 | Connected |  | N
National Grid | WESTBOROUGH | 270599 | 01581 | 2791 | Battery Add-On | 05_09_705W1 | 04/24/2020 | 05/27/2020 | 22 | 18 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/28/2020 | 07/09/2020 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 174200 | 02368 | 260 | Solar | 05_05_312W1 | 03/27/2012 | 03/27/2012 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 03/27/2012 | 10/1/2012 | Y | EXP | 72 | 02/06/2013 | 03/04/2013 | 13 | 0 | 13 | 3/21/2013 | 3/21/2013 | 4/1/2013 | Connected |  | N
National Grid | NORTON | 603025 | 02766 | 10 | Solar | 05_07_5W2 | 04/15/2024 | 04/19/2024 | 4 | 0 | 4 | 04/22/2024 | 04/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2024 | 04/15/2024 | 12/31/2025 | Y | EXP | 485 | 07/17/2024 | 10/03/2024 | 79 | 0 | 79 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 718078 | 01905 | 3.8 | Solar | 05_05_4L2 | 09/10/2025 | 11/04/2025 | 3 | 0 | 3 | 11/05/2025 | 11/05/2025 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 | 09/10/2025 | 1/28/2027 | Y | EXP | 365 | 03/07/2026 |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | CHESHIRE | 667525 | 01225 | 5.76 | Solar | 05_12_19W1 | 01/31/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | EASTON | 176060 | 02356 | 499 | Solar | 05_09_1021W2 | 03/27/2015 | 03/27/2015 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2015 | 05/05/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 07/12/2016 | 10/19/2016 | 69 | 14 | 55 | 11/22/2016 | 03/27/2015 | 5/1/2017 | Y | STD | 16 | 06/19/2017 | 06/09/2017 | 0 | 0 | 0 | 8/11/2017 | 8/11/2017 | 8/24/2017 | Connected |  | N
National Grid | BROCKTON | 707153 | 02302 | 12.92 | Solar | 05_07_94W43 | 07/29/2025 | 08/13/2025 | 10 | 5 | 5 | 08/14/2025 | 08/14/2025 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 10/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | BELCHERTOWN | 240208 | 01007 | 7.68 | Solar | 05_07_911W77 | 07/18/2019 | 07/30/2019 | 7 | 0 | 7 | 07/31/2019 | 07/31/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2019 | Connected |  | N
National Grid | BLACKSTONE | 551035 | 01504 | 7.6 | Solar | 05_09_509L1 | 09/25/2023 | 10/09/2023 | 10 | 4 | 6 | 10/10/2023 | 10/10/2023 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 | 09/25/2023 | 12/9/2024 | Y | EXP | 365 | 04/04/2024 | 04/12/2024 | 9 | 0 | 9 |  |  | 4/19/2024 | Connected |  | N
National Grid | SHUTESBURY | 314484 | 01072 | 7.6 | Solar | 05_05_332W1 | 10/26/2020 | 11/03/2020 | 5 | 3 | 2 | 11/04/2020 | 11/04/2020 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2021 | Connected |  | N
National Grid | WESTBOROUGH | 465809 | 01581 | 0 | Other | 05_09_705W1 | 02/27/2023 | 04/13/2023 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/14/2023 | 05/26/2023 | 31 | 11 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 174427 | 02368 | 600 | Solar | 05_05_312W1 | 11/21/2011 | 11/21/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2012 | 11/21/2011 | 10/31/2012 | Y | STD | 98 | 08/21/2012 | 10/11/2012 | 35 | 0 | 35 | 10/9/2012 | 10/9/2012 | 10/15/2012 | Connected |  | N
National Grid | NORTON | 616727 | 02766 | 3.8 | Solar | 05_07_5W2 | 06/10/2024 | 06/25/2024 | 4 | 0 | 4 | 06/26/2024 | 06/26/2024 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/10/2024 | 12/31/2025 | Y | EXP | 365 | 02/27/2025 | 11/21/2025 | 268 | 0 | 268 |  |  | 12/3/2025 | Connected |  | N
National Grid | SAUGUS | 721576 | 01906 | 200 | Solar | 05_05_4L2 | 10/01/2025 | 02/27/2026 | 98 | 91 | 7 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | CHESHIRE | 668988 | 01225 | 7.6 | Solar | 05_12_19W1 | 02/04/2025 | 02/13/2025 | 7 | 3 | 4 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 176123 | 02301 | 990 | Solar | 05_09_1021W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 02/02/2015 | 12/31/2016 | Y | STD | 51 | 03/24/2017 | 06/30/2017 | 68 | 0 | 68 | 7/20/2017 | 7/20/2017 | 7/20/2017 | Connected |  | N
National Grid | BROCKTON | 719404 | 02302 | 10 | Solar | 05_07_94W43 | 09/16/2025 | 09/30/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 309814 | 01007 | 7.6 | Solar | 05_07_911W77 | 09/10/2020 | 11/05/2020 | 41 | 39 | 2 | 11/06/2020 | 11/06/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2020 | 09/10/2020 | 11/4/2021 | Y | EXP | 365 | 02/03/2021 | 03/24/2021 | 49 | 0 | 49 |  |  | 4/2/2021 | Connected |  | N
National Grid | MENDON | 581714 | 01756 | 10 | Solar | 05_09_509L1 | 01/17/2024 | 01/24/2024 | 5 | 3 | 2 | 01/25/2024 | 01/25/2024 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2024 |  | 3/6/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | WENDELL | 342414 | 01379 | 9.6 | Solar | 05_05_332W1 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2021 |  | 4/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N
National Grid | WESTBOROUGH | 515826 | 01581 | 10 | Solar | 05_09_705W1 | 03/30/2023 | 04/28/2023 | 20 | 18 | 2 | 05/01/2023 | 05/01/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 174993 | 02368 | 100 | Solar | 05_05_312W1 | 03/11/2013 | 03/11/2013 | 4 | 0 | 4 | 03/19/2013 | 03/19/2013 | 978 | 0 | 978 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2013 |  | 12/31/2016 | N | EXP | 1341 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 617723 | 02766 | 6 | Solar | 05_07_5W2 | 06/13/2024 | 08/02/2024 | 8 | 6 | 2 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 |  | 11/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | SAUGUS | 742156 | 01906 | 15.2 | Solar | 05_05_4L2 | 12/24/2025 | 12/30/2025 | 3 | 0 | 3 | 12/31/2025 | 12/31/2025 | 29 | 15 | 14 | 03/03/2026 |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | NORTH ADAMS | 670811 | 01247 | 11.4 | Solar | 05_12_19W1 | 02/12/2025 | 03/19/2025 | 1 | 0 | 1 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 | 05/07/2025 | 05/20/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 05/20/2025 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2025 | Connected |  | N
National Grid | EASTON | 176120 | 02356 | 990 | Solar | 05_09_1021W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2015 | 03/10/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 02/02/2015 | 12/31/2016 | Y | STD | 51 | 03/24/2017 | 06/30/2017 | 68 | 0 | 68 | 7/20/2017 | 7/20/2017 | 7/20/2017 | Connected |  | N
National Grid | HOLBROOK | 556459 | 02343 | 4990 | Solar | 05_07_94W44 | 01/30/2024 | 05/16/2024 | 74 | 64 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 06/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELCHERTOWN | 316230 | 01007 | 7.6 | Solar | 05_07_911W77 | 10/27/2020 | 10/28/2020 | 0 | 0 | 0 | 10/29/2020 | 10/29/2020 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 600486 | 01756 | 10 | Solar | 05_09_509L1 | 05/02/2024 | 08/02/2024 | 63 | 53 | 10 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WENDELL | 376022 | 01379 | 15.2 | Solar | 05_05_332W1 | 08/16/2021 | 08/26/2021 | 8 | 7 | 1 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2021 |  | 11/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2022 | Connected |  | N
National Grid | WESTBOROUGH | 641326 | 01581 | 17.6 | Solar | 05_09_705W1 | 09/18/2024 | 09/20/2024 | 2 | 0 | 2 | 09/23/2024 | 09/23/2024 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 | 09/18/2024 | 11/10/2025 | Y | EXP | 365 | 01/22/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 2/15/2025 | Connected |  | N
National Grid | RANDOLPH | 177043 | 02368 | 792 | Solar | 05_05_312W1 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 02/07/2017 | 69 | 56 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2018 | 10/17/2016 | 3/28/2022 | Y | STD | 12 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 647267 | 02766 | 5.76 | Solar | 05_07_5W2 | 10/16/2024 | 11/18/2024 | 7 | 4 | 3 | 11/19/2024 | 11/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/16/2024 | 1/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | SAUGUS | 174673 | 01906 | 1000 | Solar | 05_05_4L2 | 06/07/2013 | 06/07/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2013 | 09/03/2013 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/2/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 672162 | 01247 | 7.6 | Solar | 05_12_19W1 | 02/20/2025 | 03/05/2025 | 10 | 7 | 3 | 03/06/2025 | 03/06/2025 | 118 | 100 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EASTON | 176199 | 02356 | 1000 | Solar | 05_09_1021W2 | 02/11/2015 | 02/11/2015 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/19/2015 | 03/19/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 736836 | 02302 | 11.5 | Solar | 05_07_94W44 | 11/27/2025 | 02/05/2026 | 3 | 0 | 3 | 02/06/2026 | 02/06/2026 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 330724 | 01007 | 3.8 | Solar | 05_07_911W77 | 01/06/2021 | 01/11/2021 | 2 | 0 | 2 | 01/12/2021 | 01/12/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2021 | Connected |  | N
National Grid | MENDON | 603088 | 01756 | 0 | Solar | 05_09_509L1 | 05/05/2024 | 05/21/2024 | 6 | 3 | 3 | 05/22/2024 | 05/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 | 05/05/2024 | 6/26/2025 | Y | EXP | 365 | 07/16/2024 | 08/15/2024 | 31 | 0 | 31 |  |  | 8/20/2024 | Connected |  | N
National Grid | SHUTESBURY | 386848 | 01072 | 0 | Solar | 05_05_332W1 | 11/10/2021 | 12/27/2021 | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2021 | 02/23/2023 | 288 | 274 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 680002 | 01581 | 23 | Solar | 05_09_705W1 | 03/27/2025 | 04/02/2025 | 4 | 0 | 4 | 04/03/2025 | 04/03/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | RANDOLPH | 177570 | 02368 | 15.2 | Solar | 05_05_312W1 | 09/15/2017 | 09/15/2017 | 8 | 8 | 0 | 09/27/2017 | 09/27/2017 | 124 | 0 | 124 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2017 |  | 9/20/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 662742 | 02766 | 7.6 | Solar | 05_07_5W2 | 12/27/2024 | 02/03/2025 | 4 | 0 | 4 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | SAUGUS | 174672 | 01906 | 1000 | Solar | 05_05_4L2 | 06/07/2013 | 06/07/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/19/2013 | 09/03/2013 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/2/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTH ADAMS | 682844 | 01247 | 11.5 | Solar | 05_12_19W1 | 04/08/2025 | 06/02/2025 | 28 | 24 | 4 | 06/03/2025 | 06/03/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2025 | Connected |  | N
National Grid | STOUGHTON | 177004 | 02072 | 240 | Solar | 05_09_1021W2 | 10/10/2016 | 10/10/2016 | 0 | 0 | 0 | 10/11/2016 | 10/11/2016 | 123 | 19 | 104 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2016 | 10/10/2016 | 10/16/2017 | Y | EXP | 311 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 741096 | 02302 | 10 | Solar | 05_07_94W44 | 12/18/2025 | 12/19/2025 | 1 | 0 | 1 | 12/22/2025 | 12/22/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELCHERTOWN | 369186 | 01007 | 249 | Solar | 05_07_911W77 | 08/03/2021 | 11/03/2021 | 64 | 55 | 9 | 11/04/2021 | 11/04/2021 | 41 | 0 | 41 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2022 | 08/03/2021 | 12/16/2023 | Y | EXP | 455 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 634772 | 01756 | 10 | Solar | 05_09_509L1 | 08/23/2024 | 09/03/2024 | 3 | 0 | 3 | 09/04/2024 | 09/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 | 08/23/2024 | 10/11/2025 | Y | EXP | 365 | 12/07/2024 | 12/13/2024 | 7 | 0 | 7 |  |  | 1/23/2025 | Connected |  | N
National Grid | SHUTESBURY | 424141 | 01072 | 9.984 | Solar | 05_05_332W1 | 05/02/2022 | 05/11/2022 | 8 | 7 | 1 | 05/12/2022 | 05/12/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 |  | 7/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 562198 | 01581 | 100 | Solar | 05_09_705W2 | 10/19/2023 | 11/17/2023 | 19 | 9 | 10 |  |  | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 191397 | 02368 | 7.6 | Solar | 05_05_312W1 | 07/20/2018 | 09/05/2018 | 3 | 3 | 0 | 09/06/2018 | 09/06/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 673253 | 02766 | 10 | Solar | 05_07_5W2 | 02/20/2025 | 02/21/2025 | 1 | 0 | 1 | 02/24/2025 | 02/24/2025 | 61 | 40 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | SAUGUS | 176818 | 01906 | 10 | Solar | 05_05_4L2 | 11/05/2015 | 11/05/2015 | 13 | 13 | 0 | 11/27/2015 | 11/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/11/2016 | N | EXP | 347 |  |  | 0 | 0 | 0 | 5/11/2016 | 5/11/2016 | 5/16/2016 | Connected |  | N
National Grid | ADAMS | 697773 | 01220 | 17.45 | Solar | 05_12_19W1 | 06/11/2025 | 06/17/2025 | 4 | 0 | 4 | 06/18/2025 | 06/18/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2025 |  | 8/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 178231 | 02072 | 5000 | Solar | 05_09_1021W2 | 01/05/2018 | 02/05/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2018 | 03/01/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 | 01/05/2018 | 12/30/2022 | Y | STD | 546 | 01/12/2021 | 10/12/2021 | 272 | 60 | 212 |  |  | 12/22/2022 | Connected |  | N
National Grid | BROCKTON | 174720 | 02302 | 500 | Solar | 05_07_94W44 | 01/14/2014 | 01/14/2014 | 6 | 0 | 6 | 01/24/2014 | 01/24/2014 | 43 | 7 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/1/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 368593 | 01007 | 10 | Solar | 05_07_911W77 | 07/23/2021 | 07/27/2021 | 2 | 0 | 2 | 07/28/2021 | 07/28/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 07/23/2021 | 5/20/2023 | Y | EXP | 365 | 03/09/2022 | 04/25/2022 | 48 | 0 | 48 |  |  | 5/28/2022 | Connected |  | N
National Grid | MENDON | 665284 | 01756 | 11.5 | Solar | 05_09_509L1 | 01/13/2025 | 01/24/2025 | 4 | 0 | 4 | 01/27/2025 | 01/27/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | WENDELL | 477539 | 01379 | 15.2 | Solar | 05_05_332W1 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2023 | Connected |  | N
National Grid | WESTBOROUGH | 577961 | 01581 | 240 | Solar | 05_09_705W2 | 12/15/2023 | 01/07/2024 | 13 | 3 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | RANDOLPH | 196685 | 02368 | 8.7 | Solar | 05_05_312W1 | 09/21/2018 | 10/24/2018 | 3 | 3 | 0 | 10/25/2018 | 10/25/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2018 | 09/21/2018 | 6/10/2019 | Y | EXP | 222 | 03/16/2019 | 03/15/2019 | 0 | 0 | 0 |  |  | 4/19/2019 | Connected |  | N
National Grid | NORTON | 684214 | 02766 | 0 | Solar | 05_07_5W2 | 04/10/2025 |  | 115 | 25 | 90 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177029 | 01906 | 3330 | Solar | 05_05_4L2 | 03/17/2017 | 03/17/2017 | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/30/2017 | 04/27/2017 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2017 | 03/17/2017 | 9/15/2020 | Y | STD | 937 | 03/06/2020 | 05/22/2020 | 77 | 0 | 77 |  |  | 9/10/2020 | Connected |  | N
National Grid | ADAMS | 716680 | 01220 | 17.45 | Solar | 05_12_19W1 | 09/04/2025 | 09/08/2025 | 1 | 0 | 1 | 09/09/2025 | 09/09/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2026 | Connected |  | N
National Grid | STOUGHTON | 178282 | 02072 | 4375 | Solar | 05_09_1021W2 | 02/23/2018 | 02/23/2018 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2018 | 04/25/2018 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2018 |  | 8/18/2021 | N | STD | 975 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLBROOK | 175242 | 02343 | 75 | Solar | 05_07_94W44 | 08/25/2014 | 08/25/2014 | 5 | 0 | 5 | 09/03/2014 | 09/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 12/31/2014 | N | EXP | 14 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 11/17/2014 | Connected |  | N
National Grid | BELCHERTOWN | 397489 | 01007 | 6 | Solar | 05_07_911W77 | 11/30/2021 | 01/10/2022 | 5 | 0 | 5 | 12/08/2021 | 12/08/2021 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2022 | 11/30/2021 |  | Y | EXP | 365 | 03/09/2022 | 03/31/2022 | 23 | 0 | 23 |  |  | 4/12/2022 | Connected |  | N
National Grid | BLACKSTONE | 672867 | 01504 | 10 | Solar | 05_09_509L1 | 02/19/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 | 02/19/2025 | 4/28/2026 | Y | EXP | 365 | 05/07/2025 | 05/24/2025 | 18 | 0 | 18 |  |  | 6/11/2025 | Connected |  | N
National Grid | ORANGE | 481074 | 01364 | 0 | Solar | 05_05_332W1 | 11/29/2022 | 12/01/2022 | 2 | 0 | 2 | 12/02/2022 | 12/02/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 739260 | 01581 | 0 | Battery Add-On | 05_09_705W2 | 12/10/2025 | 01/12/2026 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 200739 | 02368 | 3.8 | Solar | 05_05_312W1 | 11/08/2018 | 01/10/2019 | 26 | 20 | 6 | 01/11/2019 | 01/11/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 11/08/2018 | 5/19/2020 | Y | EXP | 488 | 01/14/2020 | 01/27/2020 | 13 | 0 | 13 |  |  | 2/6/2020 | Connected |  | N
National Grid | NORTON | 711862 | 02766 | 23.18 | Solar | 05_07_5W2 | 08/13/2025 | 08/18/2025 | 3 | 0 | 3 | 08/19/2025 | 08/19/2025 | 54 | 24 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 177623 | 01906 | 11.4 | Solar | 05_05_4L2 | 11/09/2017 | 11/09/2017 | 15 | 14 | 1 | 12/05/2017 | 12/05/2017 | 83 | 0 | 83 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 11/15/2018 | N | EXP | 344 |  |  | 0 | 0 | 0 |  |  | 7/18/2018 | Connected |  | N
National Grid | ADAMS | 719392 | 01220 | 7.6 | Solar | 05_12_19W1 | 09/16/2025 | 09/17/2025 | 1 | 0 | 1 | 09/18/2025 | 09/18/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | STOUGHTON | 178650 | 02072 | 5000 | Solar | 05_09_1021W2 | 12/18/2017 | 12/18/2017 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/23/2018 | 02/14/2018 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175691 | 02302 | 880 | Solar | 05_07_94W44 | 05/28/2014 | 05/28/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2014 | 07/08/2014 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2015 |  | 12/31/2016 | N | STD | 681 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 397300 | 01007 | 3.84 | Solar | 05_07_911W77 | 12/08/2021 | 01/07/2022 | 4 | 0 | 4 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 1/20/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2022 | Connected |  | N
National Grid | MENDON | 678587 | 01756 | 22.8 | Solar | 05_09_509L1 | 04/11/2025 | 05/08/2025 | 18 | 15 | 3 | 05/09/2025 | 05/09/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | ORANGE | 495154 | 01364 | 11.4 | Solar | 05_05_332W1 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 64 | 42 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 |  | 8/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | Y
National Grid | WESTBOROUGH | 747254 | 01581 | 10 | Solar | 05_09_705W2 | 01/23/2026 | 02/03/2026 | 3 | 0 | 3 | 02/11/2026 | 02/11/2026 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 200805 | 02368 | 7.6 | Solar | 05_05_312W1 | 11/08/2018 | 12/19/2018 | 6 | 0 | 6 | 12/20/2018 | 12/20/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2019 | 11/08/2018 | 11/8/2020 | Y | EXP | 365 | 03/04/2020 | 03/25/2020 | 21 | 0 | 21 |  |  | 7/16/2020 | Connected |  | N
National Grid | NORTON | 715852 | 02766 | 3.8 | Solar | 05_07_5W2 | 09/01/2025 | 09/18/2025 | 5 | 0 | 5 | 10/01/2025 | 10/01/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 197071 | 01906 | 240 | Solar | 05_05_4L2 | 09/24/2018 | 10/03/2018 | 1 | 0 | 1 | 10/04/2018 | 10/04/2018 | 39 | 8 | 31 | 12/31/2018 | 02/11/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  | 02/11/2019 | 28 | 8 | 20 |  |  | 0 | 0 | 0 | 3/12/2019 |  | 1/2/2021 | N | EXP | 662 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHESHIRE | 722477 | 01225 | 7.6 | Solar | 05_12_19W1 | 09/30/2025 | 10/03/2025 | 3 | 0 | 3 | 10/06/2025 | 10/06/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/15/2025 | Connected |  | N
National Grid | STOUGHTON | 178718 | 02072 | 4990 | Solar | 05_09_1021W2 | 04/12/2018 | 04/12/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/28/2018 | 53 | 32 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 273969 | 02302 | 7.6 | Solar | 05_07_94W44 | 02/26/2020 | 02/26/2020 | 0 | 0 | 0 | 02/27/2020 | 02/27/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2020 |  | 2/26/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 401108 | 01007 | 4999.2 | Battery Add-On | 05_07_911W77 | 10/25/2022 | 05/22/2023 | 141 | 131 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/23/2023 | 06/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 684381 | 01756 | 10 | Solar | 05_09_509L1 | 04/14/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 506009 | 01364 | 12.564 | Solar | 05_05_332W1 | 05/24/2023 | 09/07/2023 | 71 | 71 | 0 | 09/08/2023 | 09/08/2023 | 104 | 83 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2024 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2024 | Connected |  | N
National Grid | WESTBOROUGH | 174113 | 01581 | 13.54 | Solar | 05_09_705W2 | 03/30/2012 | 03/30/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2012 |  | 5/28/2012 | N | EXP | 6 |  |  | 0 | 0 | 0 | 7/27/2012 | 7/27/2012 | 11/29/2012 | Connected |  | N
National Grid | RANDOLPH | 203444 | 02368 | 0 | Solar | 05_05_312W1 | 12/12/2018 | 12/21/2018 | 6 | 0 | 6 | 12/24/2018 | 12/24/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 679335 | 02766 | 894 | Solar | 05_07_5W3 | 04/15/2025 | 08/20/2025 | 87 | 77 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 199757 | 01905 | 7.6 | Solar | 05_05_4L2 | 11/05/2018 | 12/03/2018 | 3 | 3 | 0 | 12/04/2018 | 12/04/2018 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2018 |  | 12/27/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | Connected |  | N
National Grid | CHESHIRE | 679038 | 01225 | 400 | Solar | 05_12_19W2 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | STOUGHTON | 184852 | 02072 | 1320 | Solar | 05_09_1021W2 | 06/13/2018 | 06/13/2018 | 257 | 6 | 251 |  |  | 5 | 5 | 0 |  |  | 0 | 0 | 0 | 10/04/2018 | 10/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 298308 | 02302 | 96 | Solar | 05_07_94W44 | 06/25/2020 | 07/06/2020 | 7 | 4 | 3 | 07/07/2020 | 07/07/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2020 | 06/25/2020 | 4/26/2022 | Y | EXP | 365 | 03/11/2021 | 04/21/2021 | 41 | 0 | 41 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 414097 | 01007 | 7.68 | Solar | 05_07_911W77 | 04/22/2022 | 04/25/2022 | 1 | 0 | 1 | 04/26/2022 | 04/26/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2022 |  | 6/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 527237 | 01756 | 14.79 | Solar | 05_05_332W1 | 10/25/2023 | 05/28/2023 | 3 | 2 | 1 | 10/31/2023 | 10/31/2023 | 67 | 51 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2023 | 10/25/2023 | 2/19/2025 | Y | EXP | 365 | 03/08/2024 | 03/07/2024 | 0 | 0 | 0 |  |  | 4/8/2024 | Connected |  | N
National Grid | ORANGE | 174190 | 01364 | 1000 | Solar | 05_09_705W2 | 03/15/2012 | 03/15/2012 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 209566 | 01581 | 433.3 | Solar | 05_05_312W1 | 04/24/2019 | 05/06/2019 | 8 | 6 | 2 | 05/30/2019 | 05/30/2019 | 0 | 0 | 0 | 07/12/2019 | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 08/19/2019 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 686437 | 02368 | 3.8 | Solar | 05_07_5W3 | 04/21/2025 | 05/08/2025 | 5 | 0 | 5 | 05/22/2025 | 05/22/2025 | 50 | 36 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 295120 | 02766 | 10 | Solar | 05_05_4L2 | 06/05/2020 | 06/11/2020 | 3 | 2 | 1 | 06/12/2020 | 06/12/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2020 |  | 6/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2020 | Connected |  | N
National Grid | SAUGUS | 174131 | 01906 | 252 | Solar | 05_12_19W2 | 05/03/2012 | 05/03/2012 | 9 | 0 | 9 | 05/18/2012 | 05/18/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/29/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 | 6/20/2013 | 6/20/2013 | 6/28/2013 | Connected |  | N
National Grid | ADAMS | 185016 | 01220 | 1000 | Solar | 05_09_1021W2 | 07/02/2018 | 07/02/2018 | 17 | 16 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2018 | 08/15/2018 | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 404516 | 02072 | 16.08 | Solar | 05_07_94W44 | 01/03/2022 | 01/07/2022 | 4 | 2 | 2 | 01/10/2022 | 01/10/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 425308 | 02351 | 5.76 | Solar | 05_07_911W77 | 04/21/2022 | 05/16/2022 | 3 | 0 | 3 | 05/17/2022 | 05/17/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2022 |  | 6/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2022 | Connected |  | N
National Grid | BELCHERTOWN | 687940 | 01007 | 11.4 | Solar | 05_09_509L1 | 04/29/2025 | 05/23/2025 | 3 | 0 | 3 | 06/05/2025 | 06/05/2025 | 30 | 16 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 | 04/29/2025 | 8/4/2026 | Y | EXP | 365 | 09/18/2025 | 10/07/2025 | 20 | 0 | 20 |  |  | 10/10/2025 | Connected |  | N
National Grid | MENDON | 532571 | 01756 | 10 | Solar | 05_05_332W1 | 06/13/2023 | 06/26/2023 | 8 | 5 | 3 | 06/27/2023 | 06/27/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 | 06/13/2023 | 2/25/2025 | Y | EXP | 365 | 03/26/2024 | 06/06/2024 | 73 | 0 | 73 |  |  | 6/26/2024 | Connected |  | N
National Grid | ORANGE | 174228 | 01364 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 209564 | 01581 | 700 | Solar | 05_05_312W1 | 04/24/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 699809 | 02368 | 23 | Solar | 05_07_5W3 | 06/20/2025 | 09/04/2025 | 6 | 3 | 3 | 09/04/2025 | 09/04/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 06/20/2025 | 11/12/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NORTON | 476141 | 02766 | 6 | Solar | 05_05_4L2 | 12/05/2022 | 12/07/2022 | 2 | 0 | 2 | 12/08/2022 | 12/08/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2023 | 12/05/2022 | 4/30/2024 | Y | EXP | 365 | 04/27/2023 | 04/29/2023 | 3 | 0 | 3 |  |  | 6/16/2023 | Connected |  | N
National Grid | SAUGUS | 175273 | 01906 | 42.57 | Solar | 05_12_19W2 | 08/28/2014 | 08/28/2014 | 6 | 5 | 1 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2014 |  | 11/28/2014 | N | EXP | 71 |  |  | 0 | 0 | 0 | 9/18/2014 | 9/18/2014 | 5/29/2015 | Connected |  | N
National Grid | CHESHIRE | 185567 | 01225 | 1000 | Solar | 05_09_1021W2 | 05/25/2018 | 05/25/2018 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2018 | 08/10/2018 | 26 | 20 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 437242 | 02072 | 6 | Solar | 05_07_94W44 | 06/24/2022 | 06/28/2022 | 2 | 0 | 2 | 06/29/2022 | 06/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 430063 | 02302 | 7.6 | Solar | 05_07_911W77 | 05/18/2022 | 05/20/2022 | 2 | 0 | 2 | 05/23/2022 | 05/23/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2022 | 05/18/2022 | 9/18/2023 | Y | EXP | 365 | 08/18/2022 | 09/08/2022 | 22 | 0 | 22 |  |  | 12/30/2022 | Connected |  | N
National Grid | BELCHERTOWN | 702730 | 01007 | 13.36 | Solar | 05_09_509L1 | 07/07/2025 | 09/25/2025 | 57 | 54 | 3 | 09/26/2025 | 09/26/2025 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | MENDON | 543188 | 01756 | 7.6 | Solar | 05_05_332W1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2023 |  | 9/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2024 | Connected |  | N
National Grid | ORANGE | 174227 | 01364 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 209562 | 01581 | 700 | Solar | 05_05_312W1 | 04/25/2019 | 06/11/2019 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2019 | 07/08/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 706300 | 02368 | 5.76 | Solar | 05_07_5W3 | 07/21/2025 | 08/05/2025 | 3 | 0 | 3 | 08/14/2025 | 08/14/2025 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 | 07/21/2025 | 11/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NORTON | 493344 | 02766 | 10 | Solar | 05_05_4L2 | 01/31/2023 | 02/01/2023 | 1 | 0 | 1 | 02/02/2023 | 02/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 01/31/2023 | 9/19/2024 | Y | EXP | 365 | 09/20/2023 | 11/06/2023 | 48 | 0 | 48 |  |  | 1/18/2024 | Connected |  | N
National Grid | SAUGUS | 177308 | 01906 | 7.6 | Solar | 05_12_19W2 | 11/16/2016 | 11/16/2016 | 3 | 3 | 0 | 11/22/2016 | 11/22/2016 | 136 | 0 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2016 |  | 11/22/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | CHESHIRE | 187314 | 01225 | 3.36 | Solar | 05_09_1021W2 | 06/11/2018 | 06/11/2018 | 10 | 0 | 10 | 08/07/2018 | 08/07/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2018 |  | 8/23/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | Connected |  | N
National Grid | STOUGHTON | 465450 | 02072 | 3.8 | Solar | 05_07_94W44 | 10/03/2022 | 10/04/2022 | 1 | 0 | 1 | 10/05/2022 | 10/05/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 12/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2023 | Connected |  | N
National Grid | BROCKTON | 448503 | 02302 | 6 | Solar | 05_07_911W77 | 11/11/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 | 11/11/2022 | 2/9/2024 | Y | EXP | 365 | 03/22/2023 | 04/03/2023 | 13 | 0 | 13 |  |  | 5/18/2023 | Connected |  | N
National Grid | BELCHERTOWN | 722384 | 01007 | 10 | Solar | 05_09_509L1 | 09/26/2025 | 09/30/2025 | 2 | 0 | 2 | 10/01/2025 | 10/01/2025 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2025 | Connected |  | N
National Grid | UPTON | 553505 | 01568 | 10 | Solar | 05_05_332W1 | 09/13/2023 | 09/20/2023 | 5 | 3 | 2 | 09/21/2023 | 09/21/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2023 | 09/13/2023 | 12/26/2024 | Y | EXP | 365 | 01/30/2024 | 02/27/2024 | 29 | 0 | 29 |  |  | 3/25/2024 | Connected |  | N
National Grid | ORANGE | 174226 | 01364 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 228960 | 01581 | 10 | Solar | 05_05_312W1 | 05/17/2019 | 05/24/2019 | 4 | 0 | 4 | 05/28/2019 | 05/28/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 712288 | 02368 | 990 | Solar | 05_07_5W3 | 11/14/2025 | 03/05/2026 | 73 | 67 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 502806 | 02766 | 6 | Solar | 05_05_4L2 | 02/23/2023 | 02/24/2023 | 1 | 0 | 1 | 02/27/2023 | 02/27/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 4/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | SAUGUS | 315451 | 01906 | 12.48 | Solar | 05_12_19W2 | 10/23/2020 | 10/27/2020 | 1 | 0 | 1 | 10/28/2020 | 10/28/2020 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP | 365 | 03/25/2021 | 06/24/2021 | 91 | 0 | 91 |  |  | 8/14/2021 | Connected |  | N
National Grid | CHESHIRE | 187941 | 01220 | 7.6 | Solar | 05_09_1021W2 | 06/13/2018 | 06/13/2018 | 17 | 13 | 4 | 07/24/2018 | 07/24/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 514367 | 02072 | 19.968 | Solar | 05_07_94W44 | 03/24/2023 | 03/31/2023 | 6 | 5 | 1 | 04/03/2023 | 04/03/2023 | 308 | 55 | 253 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 459507 | 02302 | 6 | Solar | 05_07_911W77 | 09/21/2022 | 09/26/2022 | 3 | 0 | 3 | 09/27/2022 | 09/27/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2022 |  | 4/5/2024 | N | EXP | 475 |  |  | 0 | 0 | 0 |  |  | 3/1/2024 | Connected |  | N
National Grid | BELCHERTOWN | 500677 | 01007 | 999 | Solar | 05_09_509L2 | 08/23/2023 | 12/11/2023 | 74 | 64 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2023 | 01/23/2024 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MENDON | 580306 | 01756 | 7.6 | Solar | 05_05_332W1 | 01/05/2024 | 01/16/2024 | 6 | 1 | 5 | 01/17/2024 | 01/17/2024 | 39 | 25 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | ORANGE | 174225 | 01364 | 1000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 240960 | 01581 | 6 | Solar | 05_05_312W1 | 06/26/2019 | 08/07/2019 | 7 | 7 | 0 | 08/08/2019 | 08/08/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/16/2019 | 06/26/2019 | 5/1/2020 | Y | EXP | 259 | 11/13/2019 | 11/27/2019 | 14 | 0 | 14 |  |  | 12/13/2019 | Connected |  | N
National Grid | RANDOLPH | 717832 | 02368 | 3.8 | Solar | 05_07_5W3 | 09/09/2025 | 10/15/2025 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 524705 | 02766 | 6 | Solar | 05_05_4L2 | 09/15/2023 | 10/08/2023 | 16 | 15 | 1 | 10/10/2023 | 10/10/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2024 | Connected |  | N
National Grid | SAUGUS | 447931 | 01906 | 9.6 | Solar | 05_12_19W2 | 08/19/2022 | 08/22/2022 | 1 | 0 | 1 | 08/23/2022 | 08/23/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 10/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2022 | Connected |  | N
National Grid | CHESHIRE | 201129 | 01225 | 5000 | Solar | 05_09_1021W2 | 05/24/2019 | 06/24/2019 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2019 | 07/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 560318 | 02072 | 7.6 | Solar | 05_07_94W44 | 10/09/2023 | 10/12/2023 | 3 | 0 | 3 | 10/13/2023 | 10/13/2023 | 23 | 6 | 17 | 11/22/2023 | 02/23/2024 | 63 | 3 | 60 |  |  | 0 | 0 | 0 |  | 02/23/2024 | 63 | 3 | 60 |  |  | 0 | 0 | 0 | 3/19/2024 |  | 4/28/2025 | N | EXP | 365 | 04/26/2024 | 05/14/2024 | 19 | 0 | 19 |  |  | 7/11/2024 | Connected |  | N
National Grid | BROCKTON | 513192 | 02302 | 6.38 | Solar | 05_07_911W77 | 06/27/2023 | 04/19/2023 | 22 | 20 | 2 | 07/31/2023 | 07/31/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2023 |  | 9/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/5/2023 | Connected |  | N
National Grid | BELCHERTOWN | 717015 | 01007 | 0 | Battery Add-On | 05_09_509L2 | 09/18/2025 | 09/24/2025 | 4 | 0 | 4 | 09/25/2025 | 09/25/2025 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BLACKSTONE | 582910 | 01504 | 0 | Battery Add-On | 05_05_332W1 | 01/11/2024 | 04/05/2024 | 59 | 54 | 5 | 04/08/2024 | 04/08/2024 | 85 | 79 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 174224 | 01364 | 6000 | Solar | 05_09_705W2 | 02/09/2012 | 02/09/2012 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/9/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 287290 | 01581 | 0 | Solar | 05_05_312W1 | 04/09/2020 | 04/10/2020 | 0 | 0 | 0 | 04/13/2020 | 04/13/2020 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2020 | 04/09/2020 | 4/9/2021 | Y | EXP | 365 | 09/05/2020 | 11/10/2020 | 66 | 0 | 66 |  |  | 2/23/2021 | Connected |  | N
National Grid | RANDOLPH | 719796 | 02368 | 3.8 | Solar | 05_07_5W3 | 09/17/2025 | 12/17/2025 | 61 | 57 | 4 | 12/18/2025 | 12/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 2/11/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTON | 546735 | 02766 | 3 | Solar | 05_05_4L2 | 08/22/2023 | 08/25/2023 | 4 | 3 | 1 | 08/28/2023 | 08/28/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 660697 | 01906 | 11.5 | Solar | 05_12_19W2 | 12/16/2024 | 12/31/2024 | 3 | 0 | 3 | 01/02/2025 | 01/02/2025 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 2/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | ADAMS | 249212 | 01220 | 3 | Solar | 05_09_1021W2 | 08/23/2019 | 08/26/2019 | 0 | 0 | 0 | 08/27/2019 | 08/27/2019 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/23/2019 | 7/8/2020 | Y | EXP | 365 | 05/08/2020 | 06/05/2020 | 28 | 0 | 28 |  |  | 6/8/2020 | Connected |  | N
National Grid | STOUGHTON | 550589 | 02072 | 17.98 | Solar | 05_07_94W44 | 03/07/2024 | 03/15/2024 | 7 | 5 | 2 | 03/18/2024 | 03/18/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2024 | 03/07/2024 | 5/22/2025 | Y | EXP | 365 | 06/14/2024 | 08/29/2024 | 77 | 0 | 77 |  |  | 7/29/2024 | Connected |  | N
National Grid | BROCKTON | 521365 | 02302 | 10 | Solar | 05_07_911W77 | 05/04/2023 | 05/08/2023 | 2 | 0 | 2 | 05/09/2023 | 05/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 | 05/04/2023 | 7/6/2024 | Y | EXP | 365 | 09/06/2023 | 10/02/2023 | 27 | 0 | 27 |  |  | 10/6/2023 | Connected |  | N
National Grid | BELCHERTOWN | 724231 | 01007 | 15.2 | Solar | 05_09_509L2 | 10/06/2025 | 10/20/2025 | 9 | 6 | 3 | 10/21/2025 | 10/21/2025 | 36 | 23 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | MENDON | 581970 | 01756 | 7.6 | Solar | 05_05_332W1 | 01/24/2024 | 01/29/2024 | 4 | 3 | 1 | 01/30/2024 | 01/30/2024 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 01/24/2024 | 5/12/2025 | Y | EXP | 365 | 05/25/2024 | 08/13/2024 | 81 | 0 | 81 |  |  | 9/12/2024 | Connected |  | N
National Grid | ORANGE | 174251 | 01364 | 18 | Solar | 05_09_705W2 | 02/24/2012 | 02/24/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 6/1/2012 | N | EXP | 11 |  |  | 0 | 0 | 0 | 5/21/2012 | 5/21/2012 | 10/19/2012 | Connected |  | N
National Grid | WESTBOROUGH | 289142 | 01581 | 7.6 | Solar | 05_05_312W1 | 04/23/2020 | 06/09/2020 | 31 | 26 | 5 | 06/10/2020 | 06/10/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | RANDOLPH | 727147 | 02368 | 3.8 | Solar | 05_07_5W3 | 10/16/2025 | 10/23/2025 | 7 | 6 | 1 | 12/02/2025 | 12/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 555397 | 02766 | 7.6 | Solar | 05_05_4L2 | 09/21/2023 | 09/25/2023 | 2 | 0 | 2 | 09/26/2023 | 09/26/2023 | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 2/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 663463 | 01906 | 5.76 | Solar | 05_12_19W2 | 01/14/2025 | 01/27/2025 | 3 | 0 | 3 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | CHESHIRE | 284440 | 01225 | 240 | Solar | 05_09_1021W2 | 07/30/2020 | 08/12/2020 | 9 | 3 | 6 |  |  | 82 | 66 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 07/30/2020 | 4/14/2023 | Y | STD | 555 | 10/11/2022 | 01/14/2023 | 96 | 0 | 96 |  |  | 4/13/2023 | Connected |  | N
National Grid | STOUGHTON | 600322 | 02072 | 13.6 | Solar | 05_07_94W44 | 03/29/2024 | 04/17/2024 | 12 | 11 | 1 | 04/18/2024 | 04/18/2024 | 16 | 11 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | BROCKTON | 528287 | 02302 | 10 | Solar | 05_07_911W77 | 06/01/2023 | 06/02/2023 | 1 | 0 | 1 | 06/05/2023 | 06/05/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 11/8/2024 | N | EXP | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 732688 | 01007 | 3.8 | Solar | 05_09_509L2 | 11/10/2025 | 12/10/2025 | 3 | 0 | 3 | 01/16/2026 | 01/16/2026 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | UPTON | 613605 | 01568 | 23 | Solar | 05_05_332W1 | 05/28/2024 | 05/30/2024 | 2 | 0 | 2 | 05/31/2024 | 05/31/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2024 | Connected |  | N
National Grid | ORANGE | 174309 | 01364 | 1800 | Solar | 05_09_705W2 | 12/30/2011 | 12/30/2011 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 293153 | 01581 | 86 | Solar | 05_05_312W1 | 06/08/2020 | 06/24/2020 | 12 | 6 | 6 | 06/25/2020 | 06/25/2020 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 727087 | 02368 | 10 | Solar | 05_07_5W3 | 10/16/2025 | 11/14/2025 | 21 | 18 | 3 | 01/08/2026 | 01/08/2026 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 579332 | 02766 | 10 | Solar | 05_05_4L2 | 01/08/2024 | 01/12/2024 | 4 | 0 | 4 | 01/16/2024 | 01/16/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 01/08/2024 | 4/19/2025 | Y | EXP | 365 | 05/24/2024 | 07/08/2024 | 46 | 0 | 46 |  |  | 9/5/2024 | Connected |  | N
National Grid | SAUGUS | 657267 | 01906 | 5.8 | Solar | 05_12_1J4 | 12/02/2024 | 12/30/2024 | 8 | 4 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2025 | Connected |  | N
National Grid | CHESHIRE | 296791 | 01225 | 7.6 | Solar | 05_09_1021W2 | 07/15/2020 | 07/17/2020 | 1 | 1 | 0 | 07/20/2020 | 07/20/2020 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 07/15/2020 | 7/15/2021 | Y | EXP |  | 10/31/2020 | 03/17/2021 | 137 | 0 | 137 |  |  | 3/19/2021 | Connected |  | N
National Grid | STOUGHTON | 673244 | 02072 | 7.6 | Solar | 05_07_94W44 | 02/20/2025 | 02/27/2025 | 6 | 3 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/2/2025 |  | 4/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | BROCKTON | 528106 | 02302 | 5.8 | Solar | 05_07_911W77 | 09/14/2023 |  | 93 | 76 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 174260 | 01007 | 34.2 | Solar | 05_09_509L2 | 03/02/2012 | 03/02/2012 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2012 |  | 6/1/2012 | N | EXP | 1 |  |  | 0 | 0 | 0 | 5/31/2012 | 5/31/2012 | 7/26/2012 | Connected |  | N
National Grid | MENDON | 644658 | 01756 | 19.544 | Solar | 05_05_332W1 | 10/03/2024 | 10/09/2024 | 5 | 4 | 1 | 10/10/2024 | 10/10/2024 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2024 | Connected |  | N
National Grid | NEW SALEM | 174975 | 01355 | 500 | Solar | 05_09_705W2 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 | 09/20/2011 | 11/30/2012 | Y | STD | 1 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 | 7/23/2013 | 7/23/2013 | 7/30/2013 | Connected |  | N
National Grid | WESTBOROUGH | 299813 | 01581 | 10 | Solar | 05_05_312W1 | 03/03/2021 | 07/08/2020 | 0 | 0 | 0 | 03/04/2021 | 03/04/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 7/8/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2021 | Connected |  | N
National Grid | RANDOLPH | 735536 | 02368 | 5.76 | Solar | 05_07_5W3 | 11/21/2025 | 12/01/2025 | 5 | 0 | 5 | 12/02/2025 | 12/02/2025 | 34 | 13 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTON | 579176 | 02766 | 9.45 | Solar | 05_05_4L2 | 01/04/2024 | 01/30/2024 | 17 | 13 | 4 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 | 01/04/2024 | 3/27/2025 | Y | EXP | 365 | 05/29/2024 | 05/28/2024 | 0 | 0 | 0 |  |  | 6/3/2024 | Connected |  | N
National Grid | SAUGUS | 710218 | 01906 | 150 | Solar | 05_12_1J6 | 08/12/2025 | 10/10/2025 | 41 | 31 | 10 |  |  | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ADAMS | 347980 | 01220 | 7.6 | Solar | 05_09_1021W2 | 04/14/2021 | 12/29/2021 | 2 | 0 | 2 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 | 04/14/2021 | 7/11/2022 | Y | EXP | 365 | 01/04/2022 | 01/14/2022 | 11 | 0 | 11 |  |  | 2/5/2022 | Connected |  | N
National Grid | STOUGHTON | 703314 | 02072 | 7.6 | Solar | 05_07_94W44 | 07/07/2025 | 08/06/2025 | 2 | 0 | 2 | 08/07/2025 | 08/07/2025 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 | 07/07/2025 | 9/30/2026 | Y | EXP | 365 | 12/23/2025 | 01/07/2026 | 16 | 0 | 16 |  |  | 1/13/2026 | Connected |  | N
National Grid | BROCKTON | 550755 | 02302 | 10 | Solar | 05_07_911W77 | 08/30/2023 | 10/12/2023 | 29 | 25 | 4 | 10/13/2023 | 10/13/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 08/30/2023 | 12/9/2024 | Y | EXP | 365 | 01/25/2024 | 02/06/2024 | 13 | 0 | 13 |  |  | 6/14/2024 | Connected |  | N
National Grid | BELCHERTOWN | 174257 | 01007 | 20 | Solar | 05_09_509L2 | 02/29/2012 | 02/29/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2012 |  | 5/14/2012 | N | EXP | 7 |  |  | 0 | 0 | 0 | 5/21/2012 | 5/21/2012 | 10/22/2012 | Connected |  | N
National Grid | MENDON | 673860 | 01756 | 17.6 | Solar | 05_05_332W1 | 02/24/2025 | 02/27/2025 | 3 | 0 | 3 | 02/28/2025 | 02/28/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | ORANGE | 174974 | 01364 | 1500 | Solar | 05_09_705W2 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 | 09/20/2011 | 11/30/2012 | Y | STD | 1 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 | 7/23/2013 | 7/23/2013 | 7/30/2013 | Connected |  | N
National Grid | WESTBOROUGH | 328513 | 01581 | 0 | Solar | 05_05_312W1 | 11/27/2020 | 12/03/2020 | 3 | 0 | 3 | 12/04/2020 | 12/04/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2021 |  | 8/26/2022 | N | EXP | 56 |  |  | 0 | 0 | 0 |  |  | 7/19/2022 | Connected |  | N
National Grid | RANDOLPH | 743435 | 02368 | 5.76 | Solar | 05_07_5W3 | 01/05/2026 | 01/06/2026 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | NORTON | 586858 | 02766 | 6 | Solar | 05_05_4L2 | 04/05/2024 | 04/10/2024 | 3 | 0 | 3 | 04/11/2024 | 04/11/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 345717 | 01970 | 32.4 | Solar | 05_12_1J7 | 03/22/2021 | 04/05/2021 | 9 | 0 | 9 | 04/06/2021 | 04/06/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2021 |  | 6/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/18/2021 | Connected |  | N
National Grid | CHESHIRE | 354411 | 01225 | 9.8 | Solar | 05_09_1021W2 | 04/23/2021 | 04/27/2021 | 1 | 0 | 1 | 04/28/2021 | 04/28/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2021 |  | 6/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 413057 | 02072 | 51.9 | Solar | 05_07_95W1 | 05/02/2022 | 06/08/2022 | 26 | 19 | 7 |  |  | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 561771 | 02302 | 5.8 | Solar | 05_07_911W77 | 11/13/2023 | 11/15/2023 | 2 | 0 | 2 | 11/16/2023 | 11/16/2023 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 174526 | 01007 | 45.6 | Solar | 05_09_509L2 | 10/03/2011 | 10/03/2011 | 11 | 0 | 11 | 10/18/2011 | 10/18/2011 | 505 | 0 | 505 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/30/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MENDON | 676718 | 01756 | 7.6 | Solar | 05_05_332W1 | 03/10/2025 | 03/13/2025 | 3 | 0 | 3 | 03/14/2025 | 03/14/2025 | 85 | 63 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | N
National Grid | ORANGE | 175012 | 01364 | 3000 | Solar | 05_09_705W2 | 08/30/2011 | 08/30/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 338021 | 01581 | 80 | Solar | 05_05_312W1 | 01/21/2021 | 01/26/2021 | 2 | 0 | 2 | 01/27/2021 | 01/27/2021 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2021 | 01/21/2021 | 12/31/2024 | Y | EXP | 386 | 08/26/2024 | 08/26/2024 | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | RANDOLPH | 750771 | 02368 | 23 | Solar | 05_07_5W3 | 02/12/2026 |  | 14 | 12 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTON | 627090 | 02766 | 16 | Solar | 05_05_4L2 | 07/23/2024 | 07/26/2024 | 3 | 1 | 2 | 07/29/2024 | 07/29/2024 | 37 | 25 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SALEM | 522459 | 01970 | 34.6 | Solar | 05_12_1J7 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2023 |  | 6/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2024 | Connected |  | N
National Grid | ADAMS | 419324 | 01220 | 495 | Solar | 05_09_1021W2 | 05/26/2022 | 06/15/2022 | 13 | 8 | 5 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 | 05/26/2022 |  | Y | STD | 365 | 05/08/2024 | 07/02/2024 | 56 | 0 | 56 |  |  | 7/17/2024 | Connected |  | N
National Grid | STOUGHTON | 468958 | 02072 | 250 | Solar | 05_07_95W1 | 11/04/2022 | 11/16/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2022 | 12/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BROCKTON | 563390 | 02302 | 3.8 | Solar | 05_07_911W77 | 10/26/2023 | 10/30/2023 | 2 | 0 | 2 | 10/31/2023 | 10/31/2023 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 174560 | 01007 | 1300 | Solar | 05_09_509L2 | 10/18/2011 | 10/18/2011 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2011 | 02/01/2012 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2012 | 10/18/2011 | 10/31/2012 | Y | STD | 56 | 06/17/2014 | 06/17/2014 | 0 | 0 | 0 | 6/17/2014 | 6/17/2014 | 7/2/2014 | Connected |  | N
National Grid | MENDON | 685827 | 01756 | 11.5 | Solar | 05_05_332W1 | 05/10/2025 | 05/14/2025 | 3 | 1 | 2 | 05/15/2025 | 05/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 175858 | 01364 | 30 | Solar | 05_09_705W2 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 | 08/04/2015 | 08/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2015 | 07/31/2015 | 8/9/2016 | Y | EXP | 357 | 09/01/2016 | 09/14/2016 | 8 | 0 | 8 | 8/18/2015 | 8/18/2015 | 10/12/2016 | Connected |  | N
National Grid | WESTBOROUGH | 343902 | 01581 | 7.6 | Solar | 05_05_312W1 | 02/25/2021 | 02/26/2021 | 0 | 0 | 0 | 03/01/2021 | 03/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2022 | Connected |  | N
National Grid | RANDOLPH | 753188 | 02368 | 3.8 | Solar | 05_07_5W3 | 02/25/2026 | 03/02/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTON | 654765 | 02766 | 11.4 | Solar | 05_05_4L2 | 11/15/2024 | 12/09/2024 | 3 | 0 | 3 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 11/15/2024 | 3/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | SALEM | 644057 | 01970 | 8.027 | Solar | 05_12_1J7 | 10/01/2024 | 10/09/2024 | 2 | 0 | 2 | 10/10/2024 | 10/10/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 | 10/01/2024 | 11/19/2025 | Y | EXP | 365 | 01/23/2025 | 05/02/2025 | 100 | 0 | 100 |  |  | 5/14/2025 | Connected |  | N
National Grid | CHESHIRE | 485106 | 01225 | 7.6 | Solar | 05_09_1021W2 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2023 | 01/12/2023 | 6/13/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2023 | Connected |  | N
National Grid | HANOVER | 716283 | 02339 | 240 | Solar | 05_07_95W1 | 09/23/2025 | 01/12/2026 | 74 | 55 | 19 |  |  | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 582509 | 02302 | 6 | Solar | 05_07_911W77 | 01/12/2024 | 06/25/2024 | 112 | 110 | 2 | 06/26/2024 | 06/26/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 | 01/12/2024 | 7/30/2025 | Y | EXP | 365 | 11/20/2024 | 09/02/2025 | 287 | 0 | 287 |  |  | 9/3/2025 | Connected |  | N
National Grid | BELCHERTOWN | 174662 | 01007 | 11.18 | Solar | 05_09_509L2 | 12/12/2012 | 12/12/2012 | 7 | 0 | 7 | 12/26/2012 | 12/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2013 |  | 3/1/2013 | N | EXP | 7 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 4/22/2013 | Connected |  | N
National Grid | MENDON | 690060 | 01756 | 8.725 | Solar | 05_05_332W1 | 05/14/2025 | 05/20/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2025 | Connected |  | N
National Grid | ORANGE | 175857 | 01364 | 30.1 | Solar | 05_09_705W2 | 07/31/2015 | 07/31/2015 | 0 | 0 | 0 | 08/04/2015 | 08/04/2015 | 235 | 0 | 235 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 |  | 8/9/2016 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 356524 | 01581 | 9.86 | Solar | 05_05_312W1 | 05/06/2021 | 05/07/2021 | 1 | 1 | 0 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 5/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2021 | Connected |  | N
National Grid | RANDOLPH | 175383 | 02368 | 17 | Solar | 05_07_5W3 | 07/09/2014 | 07/09/2014 | 5 | 0 | 5 | 07/17/2014 | 07/17/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 669574 | 02766 | 6.96 | Solar | 05_05_4L2 | 02/05/2025 | 03/06/2025 | 11 | 8 | 3 | 03/07/2025 | 03/07/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2025 | Connected |  | N
National Grid | SALEM | 706419 | 01970 | 300 | Solar | 05_12_1J901 | 10/17/2025 | 12/16/2025 | 38 | 29 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 | 01/08/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | NORTH ADAMS | 522477 | 01247 | 3 | Solar | 05_09_1021W2 | 05/10/2023 | 05/11/2023 | 1 | 0 | 1 | 05/12/2023 | 05/12/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2023 | 05/10/2023 | 7/3/2024 | Y | EXP | 365 | 09/08/2023 | 10/03/2023 | 26 | 0 | 26 |  |  | 10/19/2023 | Connected |  | Y
National Grid | HANOVER | 750713 | 02339 | 7.6 | Solar | 05_07_95W1 | 02/11/2026 | 02/13/2026 | 3 | 0 | 3 | 02/25/2026 | 02/25/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BROCKTON | 590208 | 02302 | 10 | Solar | 05_07_911W77 | 04/11/2024 | 04/15/2024 | 2 | 0 | 2 | 04/16/2024 | 04/16/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 176352 | 01007 | 499 | Solar | 05_09_509L2 | 05/13/2015 | 05/13/2015 | 38 | 38 | 0 | 07/10/2015 | 07/10/2015 | 345 | 0 | 345 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 695224 | 01756 | 20 | Solar | 05_05_332W1 | 05/30/2025 | 06/03/2025 | 2 | 0 | 2 | 06/04/2025 | 06/04/2025 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 |  | 7/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/11/2025 | Connected |  | N
National Grid | NEW SALEM | 177183 | 01355 | 990 | Solar | 05_09_705W2 | 08/12/2016 | 08/16/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/16/2016 | 10/06/2016 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 | 08/12/2016 | 11/30/2020 | Y | STD | 835 | 01/31/2020 | 10/15/2020 | 259 | 5 | 254 |  |  | 11/20/2020 | Connected |  | N
National Grid | WESTBOROUGH | 384619 | 01581 | 400 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 176957 | 02368 | 105 | Solar | 05_07_5W3 | 07/15/2016 | 07/15/2016 | 2 | 2 | 0 | 07/19/2016 | 07/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2016 |  | 2/1/2017 | N | EXP | 196 |  |  | 0 | 0 | 0 | 2/22/2017 | 2/22/2017 | 3/8/2017 | Connected |  | N
National Grid | NORTON | 670699 | 02766 | 7.6 | Solar | 05_05_4L2 | 02/07/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | SALEM | 201985 | 01970 | 7.6 | Solar | 05_12_1J901 | 11/27/2018 | 12/17/2018 | 8 | 0 | 8 | 12/18/2018 | 12/18/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 1/15/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/16/2019 | Connected |  | N
National Grid | ADAMS | 536190 | 01220 | 21.12 | Solar | 05_09_1021W2 | 06/23/2023 | 06/27/2023 | 2 | 0 | 2 | 06/28/2023 | 06/28/2023 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2023 | 06/23/2023 | 9/8/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2024 | Connected |  | N
National Grid | HANOVER | 174195 | 02339 | 250 | Wind | 05_07_95W1 | 03/17/2011 | 03/17/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2012 | 03/17/2011 | 2/28/2020 | Y | STD | 2852 | 07/24/2012 | 10/19/2012 | 61 | 0 | 61 | 12/16/2015 | 12/16/2015 |  | Withdrawn |  | Y
National Grid | BROCKTON | 599815 | 02302 | 10 | Solar | 05_07_911W77 | 03/29/2024 | 04/04/2024 | 4 | 0 | 4 | 04/05/2024 | 04/05/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 5/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 176577 | 01007 | 23 | Solar | 05_09_509L2 | 02/12/2016 | 02/12/2016 | 5 | 5 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 |  | 2/17/2017 | N | EXP | 323 |  |  | 0 | 0 | 0 | 3/31/2016 | 3/31/2016 | 10/6/2016 | Connected |  | N
National Grid | MENDON | 715756 | 01756 | 0 | Solar | 05_05_332W1 | 09/08/2025 | 09/09/2025 | 1 | 0 | 1 | 09/10/2025 | 09/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | NEW SALEM | 177562 | 01355 | 4980 | Solar | 05_09_705W2 | 07/13/2017 | 07/27/2017 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2017 | 08/21/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2017 | 07/13/2017 | 6/1/2021 | Y | STD | 867 | 10/15/2020 | 03/25/2021 | 161 | 0 | 161 |  |  | 4/14/2021 | Connected |  | N
National Grid | WESTBOROUGH | 384617 | 01581 | 400 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 27 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 177737 | 02368 | 10 | Solar | 05_07_5W3 | 03/23/2017 | 03/23/2017 | 2 | 1 | 1 | 03/28/2017 | 03/28/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2017 | 03/23/2017 | 6/30/2018 | Y | EXP | 458 | 12/28/2017 | 01/19/2018 | 14 | 0 | 14 | 4/17/2018 | 4/17/2018 | 6/8/2018 | Connected |  | N
National Grid | NORTON | 671448 | 02766 | 7.6 | Solar | 05_05_4L2 | 02/11/2025 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 360157 | 01902 | 7.6 | Solar | 05_12_1J901 | 07/01/2021 | 07/13/2021 | 6 | 0 | 6 | 07/14/2021 | 07/14/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHESHIRE | 558595 | 01225 | 3.8 | Solar | 05_09_1021W2 | 10/09/2023 | 10/12/2023 | 3 | 0 | 3 | 10/13/2023 | 10/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 10/09/2023 | 12/26/2024 | Y | EXP | 365 | 01/18/2024 | 02/06/2024 | 20 | 0 | 20 |  |  | 3/5/2024 | Connected |  | N
National Grid | HANOVER | 175036 | 02339 | 85 | Solar | 05_07_95W1 | 09/13/2013 | 09/13/2013 | 8 | 0 | 8 | 09/26/2013 | 09/26/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2013 |  | 10/31/2014 | N | EXP | 353 |  |  | 0 | 0 | 0 | 12/1/2014 | 12/1/2014 | 12/19/2014 | Connected |  | N
National Grid | BROCKTON | 603562 | 02302 | 10 | Solar | 05_07_911W77 | 04/15/2024 | 04/18/2024 | 3 | 0 | 3 | 04/19/2024 | 04/19/2024 | 57 | 37 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 177221 | 01007 | 144 | Solar | 05_09_509L2 | 08/16/2016 | 08/16/2016 | 21 | 21 | 0 | 09/15/2016 | 09/15/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2016 |  | 8/21/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 3/30/2017 | 3/30/2017 | 4/5/2017 | Connected |  | N
National Grid | MENDON | 175257 | 01756 | 414 | Solar | 05_05_3337W1 | 01/08/2015 | 01/08/2015 | 9 | 8 | 1 | 01/23/2015 | 01/23/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2015 |  | 6/30/2015 | N | EXP | 13 |  |  | 0 | 0 | 0 | 3/9/2015 | 3/9/2015 | 7/29/2015 | Connected |  | N
National Grid | ORANGE | 177870 | 01364 | 840 | Solar | 05_09_705W2 | 08/09/2017 | 08/22/2017 | 8 | 0 | 8 |  |  | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2018 | 08/09/2017 | 12/16/2021 | Y | STD | 2 | 10/03/2020 | 04/22/2021 | 201 | 0 | 201 | 10/18/2021 | 11/8/2021 | 12/8/2021 | Connected |  | N
National Grid | WESTBOROUGH | 384615 | 01581 | 200 | Solar | 05_05_312W1 | 06/13/2022 | 08/04/2022 | 36 | 28 | 8 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 178514 | 02368 | 10 | Solar | 05_07_5W3 | 03/08/2018 | 03/08/2018 | 25 | 0 | 25 | 04/13/2018 | 04/13/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 | 03/08/2018 | 8/1/2019 | Y | EXP | 447 |  |  | 0 | 0 | 0 |  |  | 8/1/2019 | Connected |  | N
National Grid | NORTON | 672152 | 02766 | 8.376 | Solar | 05_05_4L2 | 02/14/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | LYNN | 382866 | 01902 | 3.8 | Solar | 05_12_1J901 | 10/19/2021 | 01/07/2022 | 15 | 6 | 9 | 11/10/2021 | 11/10/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHESHIRE | 617132 | 01225 | 7.68 | Solar | 05_09_1021W2 | 06/11/2024 | 07/16/2024 | 6 | 5 | 1 | 07/17/2024 | 07/17/2024 | 15 | 0 | 15 | 08/09/2024 | 09/17/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 175318 | 02339 | 440.8 | Solar | 05_07_95W1 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 1/5/2015 | 1/5/2015 | 12/31/2014 | Connected |  | N
National Grid | BROCKTON | 611917 | 02302 | 10 | Solar | 05_07_911W77 | 05/17/2024 | 05/22/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 56 | 37 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 | 05/17/2024 | 9/27/2025 | Y | EXP | 365 | 12/10/2024 | 12/31/2024 | 22 | 0 | 22 |  |  | 1/13/2025 | Connected |  | N
National Grid | BELCHERTOWN | 177259 | 01007 | 65 | Hydro | 05_09_509L2 | 08/19/2016 | 08/19/2016 | 5 | 5 | 0 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2016 | 08/19/2016 | 7/15/2017 | Y | EXP | 241 | 03/02/2017 | 05/08/2017 | 46 | 0 | 46 | 7/26/2017 | 7/26/2017 | 8/3/2017 | Connected |  | N
National Grid | HOPEDALE | 175338 | 01747 | 615 | Solar | 05_05_3337W1 | 01/20/2015 | 01/20/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 03/13/2015 | 05/12/2015 | 40 | 40 | 0 | 01/28/2015 | 02/25/2015 | 19 | 0 | 19 |  | 05/12/2015 | 40 | 40 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 |  | 9/1/2015 | N | STD | 27 |  |  | 0 | 0 | 0 | 9/17/2015 | 9/17/2015 | 9/21/2015 | Connected |  | N
National Grid | ORANGE | 178435 | 01364 | 636 | Solar | 05_09_705W2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 471366 | 01581 | 9.75 | Solar | 05_05_312W1 | 11/09/2022 | 11/21/2022 | 8 | 3 | 5 | 11/22/2022 | 11/22/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  | 1/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | RANDOLPH | 186757 | 02368 | 7.6 | Solar | 05_07_5W3 | 06/18/2018 | 06/18/2018 | 9 | 2 | 7 | 07/02/2018 | 07/02/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 686578 | 02766 | 15.2 | Solar | 05_05_4L2 | 04/21/2025 | 04/25/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 407813 | 01902 | 3.84 | Solar | 05_12_1J901 | 02/04/2022 | 02/08/2022 | 2 | 0 | 2 | 02/09/2022 | 02/09/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 | 02/04/2022 | 7/26/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2022 | Connected |  | N
National Grid | ADAMS | 621482 | 01220 | 5 | Solar | 05_09_1021W2 | 07/02/2024 | 07/19/2024 | 1 | 0 | 1 | 07/22/2024 | 07/22/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2024 | Connected |  | N
National Grid | HANOVER | 177450 | 02339 | 84 | Solar | 05_07_95W1 | 09/20/2016 | 09/20/2016 | 4 | 4 | 0 | 09/26/2016 | 09/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2016 | 09/20/2016 | 9/25/2017 | Y | EXP | 364 |  |  | 0 | 0 | 0 | 5/9/2017 | 5/9/2017 | 5/11/2017 | Connected |  | N
National Grid | BROCKTON | 612964 | 02302 | 7.6 | Solar | 05_07_911W77 | 05/30/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 | 05/30/2024 | 9/5/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | BELCHERTOWN | 177547 | 01007 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 11/07/2017 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 211153 | 02762 | 210 | Natural Gas | 05_05_3337W1 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 8 | 0 | 8 | 12/26/2019 | 04/13/2020 | 75 | 50 | 25 |  |  | 0 | 0 | 0 |  | 04/13/2020 | 75 | 50 | 25 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 186988 | 01364 | 6 | Solar | 05_09_705W2 | 06/20/2018 | 06/20/2018 | 4 | 0 | 4 | 06/28/2018 | 06/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2018 | 06/20/2018 | 8/27/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2019 | Connected |  | N
National Grid | WESTBOROUGH | 501473 | 01581 | 15.2 | Solar | 05_05_312W1 | 02/13/2023 | 02/15/2023 | 2 | 1 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2023 | Connected |  | N
National Grid | RANDOLPH | 188196 | 02368 | 400 | Solar | 05_07_5W3 | 07/10/2018 | 07/18/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/25/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  | 10/25/2018 | 23 | 3 | 20 |  |  | 0 | 0 | 0 | 11/27/2018 | 07/10/2018 | 7/7/2020 | Y | EXP | 435 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 357405 | 02766 | 487.5 | Solar | 05_05_5J2 | 07/14/2021 | 08/11/2021 | 20 | 10 | 10 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2023 | 07/14/2021 | 6/18/2024 | Y | STD | 39 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 526726 | 01902 | 6 | Solar | 05_12_1J901 | 05/25/2023 | 05/30/2023 | 2 | 0 | 2 | 05/31/2023 | 05/31/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2023 | 05/25/2023 | 11/29/2024 | Y | EXP | 365 | 09/06/2023 | 12/15/2023 | 101 | 0 | 101 |  |  | 1/25/2024 | Connected |  | N
National Grid | CHESHIRE | 646564 | 01225 | 3.8 | Solar | 05_09_1021W2 | 10/11/2024 | 10/22/2024 | 3 | 0 | 3 | 10/23/2024 | 10/23/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2024 | 10/11/2024 | 12/2/2025 | Y | EXP | 365 | 02/12/2025 | 03/12/2025 | 29 | 0 | 29 |  |  | 3/19/2025 | Connected |  | Y
National Grid | HANOVER | 185230 | 02339 | 500 | Solar | 05_07_95W1 | 07/30/2018 | 09/24/2018 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/25/2018 | 10/22/2018 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 615066 | 02302 | 10 | Solar | 05_07_911W77 | 06/03/2024 | 06/10/2024 | 1 | 0 | 1 | 06/11/2024 | 06/11/2024 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2024 | 06/03/2024 | 7/31/2025 | Y | EXP | 365 | 11/06/2024 | 12/10/2024 | 35 | 0 | 35 |  |  | 12/19/2024 | Connected |  | N
National Grid | WARE | 177546 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 302661 | 02762 | 210 | Natural Gas | 05_05_3337W1 | 08/05/2020 | 08/14/2020 | 5 | 0 | 5 | 09/17/2020 | 09/17/2020 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2021 | Connected |  | N
National Grid | ORANGE | 189146 | 01364 | 990 | Solar | 05_09_705W2 | 06/28/2018 | 06/28/2018 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2018 | 09/21/2018 | 46 | 0 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 557462 | 01581 | 7.6 | Solar | 05_05_312W1 | 02/23/2024 | 10/03/2023 | 7 | 5 | 2 | 03/06/2024 | 03/06/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/23/2024 | 3/14/2025 | Y | EXP | 365 | 04/20/2024 | 05/20/2024 | 31 | 0 | 31 |  |  | 5/22/2024 | Connected |  | N
National Grid | RANDOLPH | 188743 | 02368 | 7.6 | Solar | 05_07_5W3 | 06/20/2018 | 06/20/2018 | 10 | 8 | 2 | 07/16/2018 | 07/16/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/22/2019 | N | EXP | 365 | 04/24/2019 | 05/08/2019 | 14 | 0 | 14 |  |  | 10/28/2019 | Connected |  | N
National Grid | NORTON | 549181 | 02766 | 7.6 | Solar | 05_05_5J2 | 08/30/2023 | 08/31/2023 | 1 | 0 | 1 | 09/01/2023 | 09/01/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2023 | 08/30/2023 | 1/12/2025 | Y | EXP | 365 | 01/06/2024 | 01/30/2024 | 25 | 0 | 25 |  |  | 6/5/2024 | Connected |  | N
National Grid | LYNN | 557391 | 01902 | 3.36 | Solar | 05_12_1J901 | 09/22/2023 | 11/06/2023 | 30 | 27 | 3 | 11/07/2023 | 11/07/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2023 |  | 12/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2024 | Connected |  | N
National Grid | ADAMS | 649504 | 01220 | 10 | Solar | 05_09_1021W2 | 10/24/2024 | 11/01/2024 | 3 | 0 | 3 | 11/04/2024 | 11/04/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 246486 | 02339 | 18.56 | Solar | 05_07_95W1 | 08/07/2019 | 08/08/2019 | 0 | 0 | 0 | 08/09/2019 | 08/09/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2019 |  | 10/25/2019 | N | EXP | 66 |  |  | 0 | 0 | 0 |  |  | 10/14/2019 | Connected |  | N
National Grid | BROCKTON | 623939 | 02302 | 10 | Solar | 05_07_911W77 | 07/15/2024 | 07/23/2024 | 1 | 0 | 1 | 07/24/2024 | 07/24/2024 | 29 | 16 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177545 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 401972 | 02762 | 100 | Solar | 05_05_3337W1 | 12/17/2021 | 01/06/2022 | 14 | 7 | 7 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2024 |  | 12/8/2025 | N | STD | 85 |  |  | 0 | 0 | 0 |  |  | 12/2/2025 | Connected |  | N
National Grid | ORANGE | 189259 | 01364 | 1518 | Solar | 05_09_705W2 | 07/11/2018 | 08/23/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2018 | 08/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 573957 | 01581 | 0 | Battery Add-On | 05_05_312W1 | 11/28/2023 | 12/28/2023 | 21 | 20 | 1 | 12/29/2023 | 12/29/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2024 | Connected |  | N
National Grid | RANDOLPH | 203646 | 02368 | 5 | Solar | 05_07_5W3 | 01/03/2019 | 01/04/2019 | 0 | 0 | 0 | 01/07/2019 | 01/07/2019 | 136 | 0 | 136 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 644574 | 02703 | 10 | Solar | 05_05_5J2 | 10/02/2024 | 10/28/2024 | 2 | 0 | 2 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 10/02/2024 | 12/11/2025 | Y | EXP | 365 | 01/03/2025 | 02/04/2025 | 33 | 0 | 33 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 561827 | 01902 | 5 | Solar | 05_12_1J901 | 10/16/2023 | 10/25/2023 | 7 | 6 | 1 | 10/26/2023 | 10/26/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/16/2023 | 11/15/2024 | Y | EXP | 365 | 05/01/2024 | 04/30/2024 | 0 | 0 | 0 |  |  | 5/5/2024 | Connected |  | N
National Grid | CHESHIRE | 654399 | 01225 | 7.6 | Solar | 05_09_1021W2 | 11/14/2024 | 12/02/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 11/14/2024 | 3/4/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | HANOVER | 268394 | 02339 | 11.4 | Solar | 05_07_95W1 | 12/05/2019 | 12/05/2019 | 0 | 0 | 0 | 12/06/2019 | 12/06/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2020 | 12/05/2019 | 12/5/2020 | Y | EXP | 365 | 04/14/2020 | 05/20/2020 | 36 | 0 | 36 |  |  | 8/11/2020 | Connected |  | N
National Grid | BROCKTON | 625157 | 02302 | 9.75 | Solar | 05_07_911W77 | 08/02/2024 | 08/12/2024 | 7 | 6 | 1 | 08/13/2024 | 08/13/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 | 08/02/2024 | 9/26/2025 | Y | EXP | 365 | 11/19/2024 | 01/21/2025 | 64 | 0 | 64 |  |  | 1/30/2025 | Connected |  | N
National Grid | WARE | 177544 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 51 | 42 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PLAINVILLE | 412221 | 02762 | 0 | Battery Add-On | 05_05_3337W1 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/14/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 196214 | 01364 | 5 | Solar | 05_09_705W2 | 09/18/2018 | 10/16/2018 | 14 | 8 | 6 | 10/17/2018 | 10/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 11/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2019 | Connected |  | N
National Grid | WESTBOROUGH | 573239 | 01581 | 500 | Solar | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 217727 | 02368 | 10 | Solar | 05_07_5W3 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 65 | 51 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 648314 | 02703 | 7.6 | Solar | 05_05_5J2 | 10/18/2024 | 11/21/2024 | 6 | 2 | 4 | 11/22/2024 | 11/22/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 647807 | 01902 | 6.09 | Solar | 05_12_1J901 | 10/17/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | CHESHIRE | 678811 | 01225 | 15.36 | Solar | 05_09_1021W2 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | HANOVER | 412226 | 02339 | 0 | Battery Add-On | 05_07_95W1 | 07/27/2022 | 08/10/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 627942 | 02302 | 3.8 | Solar | 05_07_911W77 | 07/26/2024 | 08/14/2024 | 3 | 0 | 3 | 08/15/2024 | 08/15/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 10/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2025 | Connected |  | N
National Grid | WARE | 177543 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WRENTHAM | 422055 | 02093 | 0 | Battery Add-On | 05_05_3337W1 | 05/11/2022 | 06/06/2022 | 18 | 10 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2022 | 07/06/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 238155 | 01364 | 25 | Solar | 05_09_705W2 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2019 | 06/18/2019 | 9/1/2020 | Y | EXP | 365 | 03/19/2020 | 06/15/2020 | 88 | 0 | 88 |  |  | 6/23/2020 | Connected |  | N
National Grid | WESTBOROUGH | 573242 | 01581 | 500 | Solar | 05_05_312W1 | 02/08/2024 | 05/15/2024 | 66 | 57 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2024 | 05/29/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 223582 | 02368 | 186.6 | Solar | 05_07_5W3 | 04/29/2019 | 05/21/2019 | 15 | 9 | 6 | 05/22/2019 | 05/22/2019 | 16 | 8 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2019 |  | 5/21/2021 | N | EXP | 72 |  |  | 0 | 0 | 0 |  |  | 6/14/2021 | Connected |  | N
National Grid | ATTLEBORO | 368511 | 02703 | 3.8 | Solar | 05_05_65H4 | 09/15/2021 | 11/08/2021 | 36 | 35 | 1 | 11/09/2021 | 11/09/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  | 1/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2022 | Connected |  | N
National Grid | LYNN | 657771 | 01902 | 5.76 | Solar | 05_12_1J901 | 12/02/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/02/2024 | 3/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | CHESHIRE | 174928 | 01225 | 400 | Solar | 05_09_1102W1 | 08/21/2013 | 08/21/2013 | 6 | 0 | 6 | 08/30/2013 | 08/30/2013 | 183 | 94 | 89 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | EXP |  | 06/20/2017 | 10/02/2017 | 72 | 0 | 72 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 520180 | 02339 | 0 | Solar | 05_07_95W1 | 04/19/2023 | 04/24/2023 | 3 | 0 | 3 | 04/25/2023 | 04/25/2023 | 221 | 202 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 |  | 11/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 636771 | 02302 | 10 | Solar | 05_07_911W77 | 08/30/2024 | 09/13/2024 | 3 | 0 | 3 | 09/16/2024 | 09/16/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/27/2024 | 08/30/2024 | 12/31/2025 | Y | EXP | 365 | 04/15/2025 | 10/10/2025 | 179 | 0 | 179 |  |  | 10/21/2025 | Connected |  | N
National Grid | WARE | 177542 | 01082 | 4000 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 51 | 42 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 | 11/07/2017 | 7/6/2025 | Y | STD | 1146 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | WRENTHAM | 434016 | 02093 | 0 | Battery Add-On | 05_05_3337W1 | 07/06/2022 | 08/01/2022 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2022 | 08/29/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 238143 | 01364 | 25 | Solar | 05_09_705W2 | 06/18/2019 | 07/10/2019 | 15 | 15 | 0 | 07/11/2019 | 07/11/2019 | 13 | 2 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 591712 | 01581 | 8.96 | Solar | 05_05_312W1 | 02/27/2024 | 03/01/2024 | 3 | 1 | 2 | 03/04/2024 | 03/04/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 3/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | RANDOLPH | 225653 | 02368 | 7.6 | Solar | 05_07_5W3 | 06/25/2019 | 06/26/2019 | 0 | 0 | 0 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  | 10/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 700477 | 02703 | 7.6 | Solar | 05_05_6J1 | 06/23/2025 | 07/29/2025 | 1 | 0 | 1 | 08/01/2025 | 08/01/2025 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/31/2026 | N | EXP | 365 | 11/01/2025 |  | 126 | 0 | 126 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 672039 | 01902 | 3.8 | Solar | 05_12_1J901 | 02/13/2025 | 03/10/2025 | 5 | 0 | 5 | 03/11/2025 | 03/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 10/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | ADAMS | 174927 | 01220 | 3000 | Solar | 05_09_1102W1 | 08/21/2013 | 08/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2013 | 02/03/2014 | 104 | 94 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 647801 | 02339 | 5.76 | Solar | 05_07_95W1 | 10/28/2024 | 12/29/2024 | 4 | 0 | 4 | 12/30/2024 | 12/30/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/20/2025 | Connected |  | N
National Grid | BROCKTON | 654197 | 02302 | 5.76 | Solar | 05_07_911W77 | 11/18/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/18/2024 | 2/10/2026 | Y | EXP | 365 | 03/11/2025 | 03/25/2025 | 15 | 0 | 15 |  |  | 7/10/2025 | Connected |  | N
National Grid | WARE | 177577 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WRENTHAM | 639935 | 02093 | 10 | Solar | 05_05_3337W1 | 09/12/2024 | 09/24/2024 | 2 | 0 | 2 | 09/25/2024 | 09/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2024 | 09/12/2024 | 10/28/2025 | Y | EXP | 365 | 11/19/2024 | 01/10/2025 | 53 | 0 | 53 |  |  | 1/17/2025 | Connected |  | N
National Grid | ORANGE | 255796 | 01364 | 10 | Solar | 05_09_705W2 | 10/10/2019 | 10/14/2019 | 1 | 0 | 1 | 10/15/2019 | 10/15/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 | 10/10/2019 | 10/12/2020 | Y | EXP | 365 | 03/07/2020 | 06/16/2020 | 101 | 0 | 101 |  |  | 6/18/2020 | Connected |  | N
National Grid | WESTBOROUGH | 596048 | 01581 | 15.2 | Solar | 05_05_312W1 | 03/12/2024 | 03/18/2024 | 4 | 0 | 4 | 03/19/2024 | 03/19/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2024 | Connected |  | N
National Grid | RANDOLPH | 234633 | 02368 | 10 | Solar | 05_07_5W3 | 06/14/2019 | 06/24/2019 | 6 | 5 | 1 | 06/25/2019 | 06/25/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | FRANKLIN | 742904 | 02038 | 15.2 | Solar | 05_05_6J1 | 01/02/2026 | 01/05/2026 | 1 | 1 | 0 | 01/06/2026 | 01/06/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 682311 | 01902 | 5.76 | Solar | 05_12_1J901 | 04/02/2025 | 04/24/2025 | 2 | 0 | 2 | 04/29/2025 | 04/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/23/2025 | 04/02/2025 | 5/29/2026 | Y | EXP | 365 | 11/19/2025 | 12/02/2025 | 14 | 0 | 14 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 174926 | 01266 | 1000 | Solar | 05_09_1102W1 | 08/21/2013 | 08/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2013 | 02/03/2014 | 104 | 94 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 664678 | 02339 | 9.5 | Solar | 05_07_95W1 | 01/09/2025 | 01/13/2025 | 18 | 14 | 4 | 06/02/2025 | 06/02/2025 | 83 | 69 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 |  | 10/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | HOLBROOK | 658738 | 02343 | 3.8 | Solar | 05_07_911W77 | 12/05/2024 | 01/30/2025 | 30 | 25 | 5 | 01/31/2025 | 01/31/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 177576 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 11/07/2017 | 52 | 42 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2018 | 02/15/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/13/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 621983 | 01756 | 300 | Solar | 05_05_335W1 | 05/30/2025 | 10/15/2025 | 90 | 81 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 11/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ORANGE | 290751 | 01364 | 0 | Other | 05_09_705W2 | 08/17/2020 | 09/21/2020 | 23 | 20 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/13/2020 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 614675 | 01581 | 6 | Solar | 05_05_312W1 | 05/31/2024 | 06/06/2024 | 1 | 0 | 1 | 06/07/2024 | 06/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 | 05/31/2024 | 8/12/2025 | Y | EXP | 365 | 08/22/2024 | 09/10/2024 | 20 | 0 | 20 |  |  | 11/9/2024 | Connected |  | N
National Grid | RANDOLPH | 239082 | 02368 | 10 | Solar | 05_07_5W3 | 10/17/2019 | 10/23/2019 | 3 | 0 | 3 | 10/24/2019 | 10/24/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 2/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176903 | 02771 | 4.73 | Solar | 05_05_6J1 | 03/03/2016 | 03/03/2016 | 18 | 18 | 0 | 03/30/2016 | 03/30/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2016 |  | 3/8/2017 | N | EXP | 336 |  |  | 0 | 0 | 0 | 11/30/2016 | 11/30/2016 | 12/2/2016 | Connected |  | N
National Grid | LYNN | 683766 | 01902 | 7.6 | Solar | 05_12_1J901 | 04/08/2025 | 04/25/2025 | 13 | 11 | 2 | 08/11/2025 | 08/11/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 175525 | 01262 | 336 | Solar | 05_09_1102W1 | 07/28/2014 | 07/28/2014 | 7 | 2 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/07/2014 | 08/21/2014 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2015 |  | 12/31/2016 | N | STD | 556 |  |  | 0 | 0 | 0 | 6/24/2015 | 6/24/2015 |  | Withdrawn |  | N
National Grid | HANOVER | 243592 | 02339 | 999 | Solar | 05_07_95W2 | 07/25/2019 | 08/12/2019 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/13/2019 | 09/04/2019 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2020 | 07/25/2019 | 3/25/2026 | Y | STD | 19 | 07/20/2021 | 09/15/2023 | 788 | 631 | 157 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 660570 | 02302 | 7.6 | Solar | 05_07_911W77 | 12/16/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 177585 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/25/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 728063 | 01756 | 17.875 | Solar | 05_05_335W1 | 10/21/2025 | 10/22/2025 | 1 | 0 | 1 | 10/23/2025 | 10/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 | 10/21/2025 | 12/18/2026 | Y | EXP | 365 | 01/28/2026 | 03/03/2026 | 35 | 0 | 35 |  |  |  | Completion Documents |  | N
National Grid | NEW SALEM | 344387 | 01355 | 9.6 | Solar | 05_09_705W2 | 03/01/2021 | 03/08/2021 | 4 | 4 | 0 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2021 |  | 10/28/2022 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  | 10/26/2022 | Connected |  | N
National Grid | WESTBOROUGH | 654529 | 01581 | 7.6 | Solar | 05_05_312W1 | 11/15/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/20/2025 | Connected |  | N
National Grid | RANDOLPH | 239710 | 02368 | 7.6 | Solar | 05_07_5W3 | 07/09/2019 | 07/30/2019 | 14 | 9 | 5 | 07/31/2019 | 07/31/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2019 | 07/09/2019 | 4/8/2021 | Y | EXP | 365 | 01/06/2021 | 01/21/2021 | 15 | 0 | 15 |  |  | 2/19/2021 | Connected |  | N
National Grid | SEEKONK | 278753 | 02771 | 80 | Solar | 05_05_6J1 | 02/10/2020 | 02/13/2020 | 3 | 2 | 1 | 02/14/2020 | 02/14/2020 | 35 | 13 | 22 | 05/08/2020 | 07/23/2020 | 43 | 2 | 41 |  |  | 0 | 0 | 0 |  | 07/23/2020 | 43 | 2 | 41 |  |  | 0 | 0 | 0 | 8/6/2020 |  | 3/3/2021 | N | EXP | 365 | 09/23/2020 | 11/20/2020 | 58 | 0 | 58 |  |  | 12/23/2020 | Connected |  | N
National Grid | LYNN | 190057 | 01902 | 9 | Solar | 05_12_1J904 | 07/17/2018 | 10/17/2018 | 6 | 0 | 6 | 10/18/2018 | 10/18/2018 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 175696 | 01262 | 500 | Solar | 05_09_1102W1 | 05/28/2014 | 05/28/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2014 | 08/21/2014 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2015 |  | 12/31/2016 | N | STD | 556 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 500843 | 02061 | 987.5 | Solar | 05_07_95W2 | 03/02/2023 | 03/30/2023 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2023 | 04/28/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | HOLBROOK | 661262 | 02343 | 10 | Solar | 05_07_911W77 | 12/17/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARE | 177584 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 732769 | 01756 | 250 | Solar | 05_05_335W1 | 02/02/2026 | 02/16/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2026 |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | ORANGE | 545906 | 01364 | 10 | Solar | 05_09_705W2 | 08/08/2023 | 08/16/2023 | 6 | 3 | 3 | 08/17/2023 | 08/17/2023 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  | 9/19/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2023 | Connected |  | N
National Grid | WESTBOROUGH | 660757 | 01581 | 8.45 | Solar | 05_05_312W1 | 12/31/2024 | 01/15/2025 | 7 | 1 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/31/2024 | 3/4/2026 | Y | EXP | 365 | 06/12/2025 | 08/06/2025 | 56 | 0 | 56 |  |  | 8/14/2025 | Connected |  | N
National Grid | RANDOLPH | 267109 | 02368 | 7.6 | Solar | 05_07_5W3 | 11/25/2019 | 12/02/2019 | 4 | 4 | 0 | 12/03/2019 | 12/03/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2019 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 | 02/07/2020 | 02/06/2020 | 0 | 0 | 0 |  |  | 3/10/2020 | Connected |  | N
National Grid | SEEKONK | 414377 | 02771 | 7.6 | Solar | 05_05_6J1 | 02/28/2022 | 03/02/2022 | 3 | 2 | 1 | 03/03/2022 | 03/03/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 4/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | LYNN | 622616 | 01902 | 5.76 | Solar | 05_12_1J904 | 07/04/2024 | 07/23/2024 | 5 | 0 | 5 | 07/24/2024 | 07/24/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2024 |  | 12/11/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 175694 | 01262 | 500 | Solar | 05_09_1102W1 | 05/28/2014 | 05/28/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2014 | 08/21/2014 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2015 | 05/28/2014 | 11/30/2017 | Y | STD | 89 | 06/20/2017 | 10/02/2017 | 72 | 0 | 72 | 10/11/2017 | 10/11/2017 | 10/11/2017 | Connected |  | N
National Grid | HANOVER | 592315 | 02339 | 150 | Solar | 05_07_95W2 | 02/26/2024 | 05/24/2024 | 63 | 54 | 9 | 05/28/2024 | 05/28/2024 | 361 | 346 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BROCKTON | 665179 | 02302 | 5.76 | Solar | 05_07_911W77 | 01/13/2025 | 01/27/2025 | 4 | 0 | 4 | 01/28/2025 | 01/28/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 01/13/2025 | 3/18/2026 | Y | EXP | 365 | 05/24/2025 | 06/03/2025 | 11 | 0 | 11 |  |  | 7/8/2025 | Connected |  | N
National Grid | WARE | 177583 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/26/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 745530 | 01756 | 23 | Solar | 05_05_335W1 | 01/15/2026 | 01/21/2026 | 3 | 0 | 3 | 01/22/2026 | 01/22/2026 | 21 | 6 | 15 | 03/04/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | ORANGE | 553560 | 01364 | 13.8 | Solar | 05_09_705W2 | 09/21/2023 | 09/25/2023 | 2 | 0 | 2 | 09/26/2023 | 09/26/2023 | 102 | 50 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 676389 | 01581 | 5.76 | Solar | 05_05_312W1 | 03/07/2025 | 03/27/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 278528 | 02368 | 3.8 | Solar | 05_07_5W3 | 03/19/2020 | 04/27/2020 | 25 | 25 | 0 | 04/28/2020 | 04/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/26/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 605232 | 02771 | 8.41 | Solar | 05_05_6J1 | 04/20/2024 | 05/02/2024 | 8 | 4 | 4 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 | 04/20/2024 | 5/29/2025 | Y | EXP | 365 | 07/23/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 8/5/2024 | Connected |  | N
National Grid | SWAMPSCOTT | 698521 | 01907 | 7.6 | Solar | 05_12_21J21 | 06/16/2025 | 07/02/2025 | 4 | 0 | 4 | 07/16/2025 | 07/16/2025 | 74 | 57 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOCKBRIDGE | 175724 | 01262 | 500 | Solar | 05_09_1102W1 | 05/28/2014 | 05/28/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/06/2014 | 08/21/2014 | 52 | 28 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2015 |  | 12/31/2016 | N | STD | 556 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 691137 | 02339 | 23.8 | Solar | 05_07_95W2 | 05/15/2025 | 05/28/2025 | 8 | 4 | 4 | 05/29/2025 | 05/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2025 | 05/15/2025 | 7/29/2026 | Y | EXP | 365 | 09/26/2025 | 11/25/2025 | 61 | 0 | 61 |  |  |  | Completion Documents |  | N
National Grid | BROCKTON | 673231 | 02302 | 15.2 | Solar | 05_07_911W77 | 02/24/2025 | 03/10/2025 | 11 | 8 | 3 | 03/11/2025 | 03/11/2025 | 56 | 37 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2025 | 02/24/2025 | 6/13/2026 | Y | EXP | 365 | 08/20/2025 | 10/07/2025 | 49 | 0 | 49 |  |  | 10/15/2025 | Connected |  | N
National Grid | WARE | 177582 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 173418 | 02019 | 10 | Solar | 05_05_335W1 | 04/11/2018 | 04/11/2018 | 26 | 2 | 24 | 06/14/2018 | 06/14/2018 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2018 |  | 7/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2019 | Connected |  | N
National Grid | ORANGE | 561338 | 01364 | 2.9 | Solar | 05_09_705W2 | 10/13/2023 | 10/17/2023 | 2 | 0 | 2 | 10/18/2023 | 10/18/2023 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2023 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | WESTBOROUGH | 419359 | 01581 | 499 | Solar | 05_05_312W2 | 05/26/2022 | 06/14/2022 | 12 | 7 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/15/2022 | 07/18/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2023 | 05/26/2022 | 7/17/2026 | Y | STD | 196 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 282704 | 02368 | 7.6 | Solar | 05_07_5W3 | 04/06/2020 | 04/08/2020 | 2 | 2 | 0 | 04/09/2020 | 04/09/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2020 | 04/06/2020 | 4/7/2021 | Y | EXP | 365 | 09/23/2020 | 10/08/2020 | 15 | 0 | 15 |  |  | 11/17/2020 | Connected |  | N
National Grid | SEEKONK | 647114 | 02771 | 12 | Solar | 05_05_6J1 | 10/29/2024 | 12/09/2024 | 2 | 0 | 2 | 12/10/2024 | 12/10/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/29/2024 | 2/4/2026 | Y | EXP | 365 | 03/15/2025 | 03/21/2025 | 7 | 0 | 7 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 721276 | 01907 | 5.12 | Solar | 05_12_21J21 | 09/25/2025 | 10/10/2025 | 3 | 0 | 3 | 10/28/2025 | 10/28/2025 | 84 | 75 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | STOCKBRIDGE | 176632 | 01266 | 527 | Solar | 05_09_1102W1 | 10/16/2015 | 10/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 | 11/13/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/25/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 710703 | 02339 | 249 | Solar | 05_07_95W2 | 08/08/2025 | 09/05/2025 | 19 | 9 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BROCKTON | 674714 | 02302 | 7.6 | Solar | 05_07_911W77 | 02/28/2025 | 03/18/2025 | 12 | 8 | 4 | 03/19/2025 | 03/19/2025 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177581 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 174455 | 02019 | 150 | Solar | 05_05_335W1 | 11/28/2011 | 11/28/2011 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2012 |  | 4/1/2012 | N | EXP | 34 |  |  | 0 | 0 | 0 | 9/24/2012 | 9/24/2012 | 8/31/2012 | Connected |  | N
National Grid | ORANGE | 569310 | 01364 | 22.995 | Solar | 05_09_705W2 | 11/07/2023 | 11/20/2023 | 8 | 5 | 3 | 11/21/2023 | 11/21/2023 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2024 | 11/07/2023 | 2/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 561576 | 01581 | 1980 | Solar | 05_05_312W2 | 05/15/2024 | 06/13/2024 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/14/2024 | 07/12/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | RANDOLPH | 282699 | 02368 | 7.6 | Solar | 05_07_5W3 | 04/28/2020 | 04/30/2020 | 2 | 2 | 0 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 | 04/28/2020 | 4/29/2021 | Y | EXP | 365 | 07/29/2020 | 09/15/2020 | 49 | 5 | 44 |  |  | 9/17/2020 | Connected |  | N
National Grid | SEEKONK | 613818 | 02771 | 10 | Solar | 05_05_6J2 | 05/29/2024 | 06/10/2024 | 4 | 2 | 2 | 06/11/2024 | 06/11/2024 | 17 | 8 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 | 05/29/2024 | 7/11/2025 | Y | EXP | 365 | 08/07/2024 | 08/16/2024 | 10 | 0 | 10 |  |  | 10/22/2024 | Connected |  | N
National Grid | LYNN | 736451 | 01902 | 11.78 | Solar | 05_12_21J21 | 11/25/2025 | 12/01/2025 | 4 | 2 | 2 | 12/18/2025 | 12/18/2025 | 35 | 19 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | STOCKBRIDGE | 176724 | 01262 | 668 | Solar | 05_09_1102W1 | 02/23/2016 | 02/23/2016 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2016 | 04/05/2016 | 19 | 9 | 10 |  |  | 0 | 0 | 0 | 09/20/2016 | 01/12/2017 | 77 | 0 | 77 | 11/3/2017 | 02/23/2016 | 10/31/2017 | Y | STD | 3 | 01/05/2018 | 02/09/2018 | 24 | 0 | 24 | 2/12/2018 | 2/12/2018 | 2/16/2018 | Connected |  | N
National Grid | HANOVER | 174810 | 02339 | 250 | Solar | 05_07_95W2 | 01/24/2013 | 01/24/2013 | 10 | 4 | 6 | 02/14/2013 | 02/14/2013 | 403 | 0 | 403 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2013 |  | 5/31/2013 | N | EXP | 66 |  |  | 0 | 0 | 0 | 3/26/2013 | 3/26/2013 |  | Withdrawn |  | Y
National Grid | BROCKTON | 702918 | 02302 | 7.6 | Solar | 05_07_911W77 | 07/08/2025 | 07/21/2025 | 8 | 4 | 4 | 08/07/2025 | 08/07/2025 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 | 07/08/2025 | 8/26/2026 | Y | EXP | 365 | 10/18/2025 | 10/17/2025 | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | WARE | 177580 | 01082 | 4000 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 | 11/07/2017 | 10/8/2025 | Y | STD | 1146 |  |  | 0 | 0 | 0 |  |  | 8/22/2025 | Connected |  | N
National Grid | BELLINGHAM | 174848 | 02019 | 20 | Solar | 05_05_335W1 | 02/05/2013 | 02/05/2013 | 4 | 0 | 4 | 02/19/2013 | 02/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 4/30/2013 | N | EXP | 22 |  |  | 0 | 0 | 0 | 4/8/2013 | 4/8/2013 | 7/2/2013 | Connected |  | N
National Grid | ORANGE | 588507 | 01364 | 10 | Solar | 05_09_705W2 | 02/19/2024 | 02/21/2024 | 2 | 0 | 2 | 02/22/2024 | 02/22/2024 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2024 | Connected |  | N
National Grid | WESTBOROUGH | 590683 | 01581 | 499 | Solar | 05_05_312W2 | 07/08/2024 | 08/26/2024 | 36 | 27 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 10/03/2024 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | RANDOLPH | 297377 | 02368 | 7.6 | Solar | 05_07_5W3 | 07/15/2020 | 07/22/2020 | 4 | 0 | 4 | 07/23/2020 | 07/23/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/15/2020 | 5/28/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2021 | Connected |  | N
National Grid | SEEKONK | 625270 | 02771 | 7.68 | Solar | 05_05_6J2 | 07/16/2024 | 09/03/2024 | 1 | 0 | 1 | 09/04/2024 | 09/04/2024 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | N
National Grid | LYNN | 347227 | 01902 | 5.76 | Solar | 05_12_21J21 | 04/22/2021 | 04/30/2021 | 5 | 3 | 2 | 05/03/2021 | 05/03/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2021 |  | 7/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | N
National Grid | STOCKBRIDGE | 193884 | 01262 | 2000 | Solar | 05_09_1102W1 | 09/25/2018 | 10/01/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/05/2018 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2019 | 09/25/2018 | 2/12/2022 | Y | STD | 714 | 06/16/2021 | 11/03/2021 | 141 | 8 | 133 |  |  | 12/22/2021 | Connected |  | N
National Grid | HANSON | 175381 | 02341 | 1000 | Solar | 05_07_95W2 | 06/26/2014 | 06/26/2014 | 69 | 69 | 0 | 10/06/2014 | 10/06/2014 | 257 | 0 | 257 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2014 |  | 2/27/2015 | N | EXP | 8 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 713269 | 02302 | 6.08 | Solar | 05_07_911W77 | 09/02/2025 |  | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177579 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 174954 | 01756 | 164 | Solar | 05_05_335W1 | 02/27/2013 | 02/27/2013 | 4 | 0 | 4 | 03/11/2013 | 03/11/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2013 | 02/27/2013 | 1/15/2016 | Y | EXP | 129 | 11/04/2015 | 11/09/2015 | 3 | 0 | 3 | 7/30/2013 | 7/30/2013 | 12/29/2015 | Connected |  | N
National Grid | ORANGE | 630170 | 01364 | 8 | Solar | 05_09_705W2 | 12/02/2024 | 01/21/2025 | 7 | 3 | 4 | 01/22/2025 | 01/22/2025 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2025 | 12/02/2024 | 5/8/2026 | Y | EXP | 365 | 08/20/2025 | 09/10/2025 | 22 | 0 | 22 |  |  | 10/21/2025 | Connected |  | Y
National Grid | WESTBOROUGH | 602516 | 01581 | 999 | Solar | 05_05_312W2 | 05/09/2024 | 08/01/2024 | 57 | 47 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2024 | 08/12/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | RANDOLPH | 307716 | 02368 | 3.8 | Solar | 05_07_5W3 | 10/02/2020 | 10/20/2020 | 10 | 7 | 3 | 10/21/2020 | 10/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 | 10/02/2020 | 10/20/2021 | Y | EXP | 365 | 04/17/2021 | 06/10/2021 | 54 | 0 | 54 |  |  | 7/29/2021 | Connected |  | N
National Grid | SEEKONK | 633429 | 02771 | 0 | Battery Add-On | 05_05_6J2 | 09/09/2024 | 09/11/2024 | 2 | 0 | 2 | 09/12/2024 | 09/12/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2024 | Connected |  | N
National Grid | LYNN | 424060 | 01902 | 4.06 | Solar | 05_12_21J21 | 05/04/2022 | 05/09/2022 | 3 | 2 | 1 | 05/10/2022 | 05/10/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2022 |  | 6/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2022 | Connected |  | N
National Grid | STOCKBRIDGE | 199448 | 01262 | 60 | Solar | 05_09_1102W1 | 10/26/2018 | 11/05/2018 | 5 | 1 | 4 | 11/06/2018 | 11/06/2018 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 |  | 1/28/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | HANOVER | 175605 | 02339 | 17.6 | Solar | 05_07_95W2 | 10/16/2014 | 10/16/2014 | 8 | 5 | 3 | 10/29/2014 | 10/29/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2014 |  | 12/31/2014 | N | EXP | 51 |  |  | 0 | 0 | 0 | 1/30/2015 | 1/30/2015 | 2/24/2015 | Connected |  | N
National Grid | BROCKTON | 735724 | 02302 | 11.5 | Solar | 05_07_911W77 | 11/24/2025 | 12/01/2025 | 4 | 0 | 4 | 12/02/2025 | 12/02/2025 | 52 | 25 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 177578 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/24/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 175447 | 01756 | 5000 | Solar | 05_05_335W1 | 03/12/2014 | 03/12/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2014 | 04/11/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/1/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 637215 | 01364 | 5.76 | Solar | 05_09_705W2 | 09/03/2024 | 09/23/2024 | 3 | 0 | 3 | 09/24/2024 | 09/24/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 09/03/2024 | 11/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | WESTBOROUGH | 737811 | 01581 | 480 | Solar | 05_05_312W2 | 02/05/2026 |  | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | RANDOLPH | 308462 | 02368 | 6 | Solar | 05_07_5W3 | 09/24/2020 | 09/28/2020 | 1 | 0 | 1 | 09/29/2020 | 09/29/2020 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/11/2021 | Connected |  | N
National Grid | SEEKONK | 692473 | 02771 | 6.282 | Solar | 05_05_6J2 | 05/17/2025 | 05/21/2025 | 3 | 0 | 3 | 05/22/2025 | 05/22/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | LYNN | 640666 | 01902 | 3.8 | Solar | 05_12_21J21 | 09/16/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2024 |  | 12/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 293359 | 01230 | 20 | Solar | 05_09_1102W1 | 05/27/2020 | 06/01/2020 | 2 | 0 | 2 | 06/02/2020 | 06/02/2020 | 53 | 41 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2020 |  | 6/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/16/2020 | Connected |  | N
National Grid | HANOVER | 175672 | 02339 | 816 | Solar | 05_07_95W2 | 10/21/2014 | 10/21/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2014 | 11/26/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/15/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 524421 | 02302 | 500 | Solar | 05_07_912W21 | 02/15/2024 | 08/26/2024 | 132 | 123 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2024 | 08/30/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARE | 177618 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/25/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 175708 | 01747 | 18 | Solar | 05_05_335W1 | 10/24/2014 | 10/24/2014 | 5 | 3 | 2 | 11/03/2014 | 11/03/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2014 |  | 2/24/2015 | N | EXP | 14 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 8/28/2015 | Connected |  | N
National Grid | ORANGE | 651608 | 01364 | 7.6 | Solar | 05_09_705W2 | 11/05/2024 | 01/10/2025 | 15 | 10 | 5 | 01/13/2025 | 01/13/2025 | 37 | 16 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | WESTBOROUGH | 174332 | 01581 | 300 | Solar | 05_05_312W2 | 01/18/2012 | 01/18/2012 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2012 | 01/18/2012 | 7/1/2012 | Y | EXP | 59 | 09/25/2012 | 11/29/2012 | 29 | 0 | 29 | 1/22/2013 | 1/22/2013 | 2/6/2013 | Connected |  | N
National Grid | RANDOLPH | 327921 | 02368 | 9.8 | Solar | 05_07_5W3 | 12/09/2020 | 12/18/2020 | 6 | 0 | 6 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 | 12/09/2020 | 2/8/2022 | Y | EXP | 365 | 09/29/2021 | 10/22/2021 | 24 | 0 | 24 |  |  | 2/4/2022 | Connected |  | N
National Grid | SEEKONK | 518104 | 02771 | 0 | Other | 05_05_7L1 | 06/30/2023 | 07/17/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2023 | 09/12/2023 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | LYNN | 658658 | 01902 | 7.6 | Solar | 05_12_21J21 | 12/05/2024 | 12/19/2024 | 5 | 0 | 5 | 12/20/2024 | 12/20/2024 | 141 | 118 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 326152 | 01262 | 3 | Solar | 05_09_1102W1 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/18/2021 | Connected |  | N
National Grid | HANOVER | 176618 | 02339 | 1000 | Solar | 05_07_95W2 | 04/12/2016 | 04/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2016 | 05/20/2016 | 27 | 15 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/17/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 690848 | 02302 | 499 | Other | 05_07_912W21 | 07/11/2025 | 08/22/2025 | 30 | 20 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/25/2025 | 09/15/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WARE | 177615 | 01082 | 500 | Solar | 05_09_509L2 | 11/07/2017 | 01/25/2018 | 50 | 42 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2018 | 02/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2018 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 175733 | 01756 | 1000 | Solar | 05_05_335W1 | 08/11/2014 | 08/11/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2014 | 09/09/2014 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2015 | 08/11/2014 | 7/31/2017 | Y | STD | 894 | 05/17/2017 | 07/27/2017 | 49 | 0 | 49 | 8/4/2017 | 8/4/2017 | 8/8/2017 | Connected |  | N
National Grid | ORANGE | 665012 | 01364 | 7.6 | Solar | 05_09_705W2 | 01/10/2025 | 02/12/2025 | 18 | 13 | 5 | 02/13/2025 | 02/13/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 |  | 5/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | WESTBOROUGH | 175072 | 01581 | 95 | Solar | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 5/31/2013 | N | EXP | 78 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 | 4/16/2013 | Connected |  | N
National Grid | RANDOLPH | 352832 | 02368 | 5.76 | Solar | 05_07_5W3 | 06/18/2021 | 06/25/2021 | 5 | 0 | 5 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 680156 | 02771 | 5.22 | Solar | 05_05_7L1 | 04/14/2025 | 07/07/2025 | 3 | 1 | 2 | 07/08/2025 | 07/08/2025 | 36 | 20 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 663402 | 01902 | 3.8 | Solar | 05_12_21J21 | 01/06/2025 | 01/28/2025 | 1 | 0 | 1 | 01/29/2025 | 01/29/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 | 01/06/2025 | 3/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 343180 | 01262 | 7.6 | Solar | 05_09_1102W1 | 02/21/2021 | 02/25/2021 | 3 | 0 | 3 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  | 9/1/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | HANOVER | 178052 | 02339 | 1000 | Solar | 05_07_95W2 | 06/30/2017 | 06/30/2017 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2017 | 08/07/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/5/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 723407 | 02324 | 10 | Solar | 05_07_912W21 | 10/01/2025 | 10/09/2025 | 4 | 0 | 4 | 12/08/2025 | 12/08/2025 | 27 | 17 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WARE | 178148 | 01082 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 175796 | 02019 | 743 | Solar | 05_05_335W1 | 09/16/2015 | 09/16/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 09/16/2015 | 12/22/2017 | Y | STD | 55 | 06/05/2017 | 12/14/2017 | 128 | 0 | 128 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | NEW SALEM | 670913 | 01355 | 10 | Solar | 05_09_705W2 | 04/03/2025 | 04/18/2025 | 11 | 6 | 5 | 04/22/2025 | 04/22/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/13/2025 | Connected |  | Y
National Grid | NORTHBOROUGH | 175174 | 01532 | 95 | Solar | 05_05_312W2 | 11/21/2012 | 11/21/2012 | 9 | 0 | 9 | 12/07/2012 | 12/07/2012 | 74 | 3 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 |  | 2/28/2013 | N | EXP | 14 |  |  | 0 | 0 | 0 | 3/21/2013 | 3/21/2013 |  | Withdrawn |  | Y
National Grid | RANDOLPH | 449261 | 02368 | 6 | Solar | 05_07_5W3 | 08/11/2022 | 08/15/2022 | 3 | 1 | 2 | 08/16/2022 | 08/16/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 | 08/11/2022 | 11/3/2024 | Y | EXP | 365 | 08/11/2023 | 10/06/2023 | 57 | 0 | 57 |  |  | 11/9/2023 | Connected |  | N
National Grid | SEEKONK | 708498 | 02771 | 5.76 | Solar | 05_05_7L1 | 07/30/2025 | 09/01/2025 | 5 | 0 | 5 | 09/02/2025 | 09/02/2025 | 81 | 69 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2025 |  | 12/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LYNN | 704066 | 01902 | 5.76 | Solar | 05_12_21J21 | 07/11/2025 | 07/25/2025 | 3 | 0 | 3 | 08/04/2025 | 08/04/2025 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 460725 | 01262 | 0 | Battery Add-On | 05_09_1102W1 | 09/23/2022 | 10/10/2022 | 11 | 10 | 1 | 10/11/2022 | 10/11/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 |  | 12/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/24/2023 | Connected |  | N
National Grid | HANOVER | 228439 | 02339 | 17.6 | Solar | 05_07_95W2 | 05/15/2019 | 05/16/2019 | 0 | 0 | 0 | 05/17/2019 | 05/17/2019 | 202 | 29 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/10/2019 | Connected |  | N
National Grid | BRIDGEWATER | 741316 | 02324 | 10 | Solar | 05_07_912W21 | 12/19/2025 | 12/26/2025 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 37 | 23 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WARE | 178147 | 01082 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/11/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 175795 | 01747 | 1100 | Solar | 05_05_335W1 | 09/16/2015 | 09/16/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 09/16/2015 | 6/30/2018 | Y | STD | 695 | 06/05/2017 | 12/14/2017 | 128 | 0 | 128 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 538142 | 01364 | 0 | Other | 05_09_705W3 | 07/28/2023 | 10/05/2023 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2023 | 11/03/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 175204 | 01581 | 1800 | Solar | 05_05_312W2 | 12/06/2012 | 12/06/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2012 | 03/21/2013 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/3/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 404526 | 02368 | 10 | Solar | 05_07_5W3 | 01/26/2022 | 02/18/2022 | 17 | 16 | 1 | 02/22/2022 | 02/22/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 | 01/26/2022 | 6/30/2023 | Y | EXP | 365 | 06/16/2022 | 06/28/2022 | 13 | 0 | 13 |  |  | 7/6/2022 | Connected |  | N
National Grid | SEEKONK | 735792 | 02771 | 5.76 | Solar | 05_05_7L1 | 11/24/2025 | 01/16/2026 | 36 | 33 | 3 | 01/20/2026 | 01/20/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | LYNN | 383844 | 01902 | 75 | Solar | 05_12_21J22 | 10/13/2021 | 11/17/2021 | 24 | 14 | 10 |  |  | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 463551 | 01262 | 15.2 | Solar | 05_09_1102W1 | 09/27/2022 | 09/28/2022 | 1 | 0 | 1 | 09/29/2022 | 09/29/2022 | 217 | 37 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANOVER | 279002 | 02339 | 0 | Solar | 05_07_95W2 | 03/13/2020 | 03/16/2020 | 0 | 0 | 0 | 03/17/2020 | 03/17/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2020 | Connected |  | N
National Grid | BRIDGEWATER | 174236 | 02324 | 110 | Solar | 05_07_912W21 | 02/10/2012 | 02/10/2012 | 23 | 0 | 23 | 03/29/2012 | 03/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 4/5/2012 | N | EXP | 251 |  |  | 0 | 0 | 0 | 11/28/2012 | 11/28/2012 | 12/18/2012 | Connected |  | N
National Grid | BELCHERTOWN | 178146 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 175825 | 01756 | 1860 | Solar | 05_05_335W1 | 09/16/2015 | 09/16/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2015 | 10/20/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 09/16/2015 | 12/22/2017 | Y | STD | 55 | 06/05/2017 | 12/14/2017 | 128 | 0 | 128 | 12/20/2017 | 12/20/2017 | 12/22/2017 | Connected |  | N
National Grid | NEW SALEM | 620825 | 01355 | 3602 | Solar | 05_09_705W3 | 12/10/2024 | 05/19/2025 | 110 | 100 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/20/2025 | 07/31/2025 | 50 | 31 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WESTBOROUGH | 175259 | 01581 | 138 | Solar | 05_05_312W2 | 01/07/2015 | 01/07/2015 | 4 | 0 | 4 | 01/14/2015 | 01/14/2015 | 0 | 0 | 0 | 03/11/2015 | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 |  | 06/23/2015 | 70 | 30 | 40 |  |  | 0 | 0 | 0 | 11/2/2015 |  | 12/31/2016 | N | EXP | 425 |  |  | 0 | 0 | 0 | 11/2/2015 | 11/2/2015 | 6/21/2017 | Connected |  | N
National Grid | RANDOLPH | 424661 | 02368 | 11.4 | Solar | 05_07_5W3 | 04/21/2022 | 05/20/2022 | 4 | 1 | 3 | 05/23/2022 | 05/23/2022 | 28 | 8 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 | 04/21/2022 | 8/16/2024 | Y | EXP | 365 | 06/09/2023 | 08/11/2023 | 64 | 0 | 64 |  |  | 9/5/2023 | Connected |  | N
National Grid | SEEKONK | 737182 | 02771 | 15.007 | Solar | 05_05_7L1 | 12/01/2025 | 12/03/2025 | 2 | 0 | 2 | 12/04/2025 | 12/04/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2026 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 693732 | 01902 | 10 | Solar | 05_12_21J25 | 05/29/2025 | 06/23/2025 | 4 | 0 | 4 | 07/16/2025 | 07/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/22/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 486533 | 01262 | 22.8 | Solar | 05_09_1102W1 | 12/19/2022 | 12/20/2022 | 1 | 0 | 1 | 12/21/2022 | 12/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2023 |  | 1/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2023 | Connected |  | N
National Grid | PEMBROKE | 346398 | 02359 | 17.76 | Solar | 05_07_95W2 | 03/11/2021 | 04/07/2021 | 18 | 18 | 0 | 04/08/2021 | 04/08/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 4/6/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 174481 | 02324 | 24 | Solar | 05_07_912W21 | 02/02/2011 | 02/02/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 178151 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 175992 | 01756 | 198 | Solar | 05_05_335W1 | 06/05/2015 | 06/05/2015 | 2 | 2 | 0 | 06/10/2015 | 06/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 06/05/2015 | 6/13/2016 | Y | EXP | 313 | 10/27/2015 | 12/14/2015 | 32 | 0 | 32 | 12/23/2015 | 12/23/2015 | 1/13/2016 | Connected |  | N
National Grid | ERVING | 692494 | 01344 | 11.4 | Solar | 05_09_705W3 | 05/21/2025 | 09/22/2025 | 78 | 75 | 3 | 09/23/2025 | 09/23/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 | 05/21/2025 | 10/14/2026 | Y | EXP | 365 | 01/22/2026 |  | 44 | 0 | 44 |  |  |  | Construction |  | N
National Grid | WESTBOROUGH | 175377 | 01581 | 368 | Solar | 05_05_312W2 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 |  | 11/28/2014 | N | EXP | 122 |  |  | 0 | 0 | 0 | 12/15/2014 | 12/15/2014 | 12/31/2014 | Connected |  | N
National Grid | RANDOLPH | 427346 | 02368 | 6 | Solar | 05_07_5W3 | 05/02/2022 | 05/17/2022 | 1 | 0 | 1 | 05/18/2022 | 05/18/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 740023 | 02771 | 20.52 | Solar | 05_05_7L1 | 12/12/2025 | 12/18/2025 | 3 | 2 | 1 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 683953 | 01901 | 340 | Solar | 05_12_21J27 | 05/07/2025 | 09/10/2025 | 85 | 75 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/11/2025 | 10/15/2025 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | STOCKBRIDGE | 545516 | 01262 | 20 | Solar | 05_09_1102W1 | 09/14/2023 | 09/19/2023 | 3 | 0 | 3 | 09/20/2023 | 09/20/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 1/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/2/2024 | Connected |  | N
National Grid | HANOVER | 348533 | 02339 | 157.52 | Solar | 05_07_95W2 | 03/24/2021 | 07/02/2021 | 70 | 60 | 10 | 07/06/2021 | 07/06/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 174959 | 02324 | 300 | Solar | 05_07_912W21 | 03/04/2013 | 03/04/2013 | 5 | 0 | 5 | 03/14/2013 | 03/14/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2013 | 03/04/2013 | 11/29/2013 | Y | EXP | 228 | 11/19/2013 | 12/02/2013 | 8 | 0 | 8 | 11/5/2013 | 11/5/2013 | 12/12/2013 | Connected |  | N
National Grid | BELCHERTOWN | 178150 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 176694 | 01756 | 750 | Solar | 05_05_335W1 | 04/20/2016 | 04/20/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/26/2016 | 06/09/2016 | 31 | 20 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2017 |  | 4/26/2018 | N | STD | 477 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 702549 | 01364 | 9.5 | Solar | 05_09_705W3 | 07/07/2025 | 07/24/2025 | 2 | 0 | 2 | 08/01/2025 | 08/01/2025 | 4 | 0 | 4 | 09/02/2025 | 08/29/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 08/29/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 | 07/07/2025 | 9/22/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | Y
National Grid | WESTBOROUGH | 175809 | 01581 | 741 | Solar | 05_05_312W2 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 | 05/21/2015 | 05/21/2015 | 0 | 0 | 0 | 07/11/2015 | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 |  | 10/06/2015 | 60 | 28 | 32 |  |  | 0 | 0 | 0 | 10/30/2015 | 05/18/2015 | 12/31/2016 | Y | EXP | 428 | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 | 11/30/2016 | 11/30/2016 | 6/28/2016 | Connected |  | N
National Grid | RANDOLPH | 434012 | 02368 | 0 | Battery Add-On | 05_07_5W3 | 07/28/2022 | 08/11/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 744294 | 02771 | 10 | Solar | 05_05_7L1 | 01/09/2026 | 01/14/2026 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 752641 | 01902 | 60 | Solar | 05_12_21J27 | 02/27/2026 |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | STOCKBRIDGE | 621960 | 01262 | 23 | Solar | 05_09_1102W1 | 07/03/2024 | 07/08/2024 | 2 | 0 | 2 | 07/09/2024 | 07/09/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2024 |  | 8/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2025 | Connected |  | N
National Grid | HANSON | 378618 | 02341 | 15.2 | Solar | 05_07_95W2 | 08/29/2021 | 08/30/2021 | 1 | 0 | 1 | 08/31/2021 | 08/31/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2021 | 08/29/2021 | 8/23/2023 | Y | EXP | 365 | 12/28/2021 | 02/01/2022 | 36 | 0 | 36 |  |  | 10/13/2022 | Connected |  | N
National Grid | BRIDGEWATER | 177268 | 02324 | 10 | Solar | 05_07_912W21 | 11/08/2016 | 11/08/2016 | 1 | 1 | 0 | 11/10/2016 | 11/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/08/2016 | 2/28/2018 | Y | EXP | 463 | 01/18/2018 | 02/01/2018 | 10 | 0 | 10 | 2/16/2018 | 2/16/2018 | 2/16/2018 | Connected |  | N
National Grid | BELCHERTOWN | 178149 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/11/2018 | 37 | 0 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 177352 | 02019 | 10 | Solar | 05_05_335W1 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 | 02/15/2017 | 2/21/2018 | Y | EXP | 362 | 10/31/2017 | 11/29/2017 | 15 | 0 | 15 | 2/20/2018 | 2/20/2018 | 2/26/2018 | Connected |  | N
National Grid | ORANGE | 731901 | 01364 | 19.1 | Solar | 05_09_705W3 | 11/06/2025 | 11/12/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 | 11/06/2025 | 1/22/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHBOROUGH | 176027 | 01532 | 475 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 6 | 2 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 456432 | 02368 | 7.6 | Solar | 05_07_5W3 | 09/16/2022 | 09/20/2022 | 2 | 0 | 2 | 09/21/2022 | 09/21/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 |  | 12/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2023 | Connected |  | N
National Grid | SEEKONK | 751623 | 02771 | 16.72 | Solar | 05_05_7L1 | 02/17/2026 | 02/19/2026 | 2 | 0 | 2 | 02/20/2026 | 02/20/2026 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 174585 | 01905 | 95 | Solar | 05_12_21J27 | 08/30/2011 | 08/30/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2011 |  | 7/10/2012 | N | EXP | 281 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/10/2012 | Connected |  | N
National Grid | STOCKBRIDGE | 645262 | 01262 | 33.15 | Solar | 05_09_1102W1 | 10/07/2024 | 10/08/2024 | 1 | 0 | 1 | 10/09/2024 | 10/09/2024 | 26 | 8 | 18 | 11/22/2024 | 01/07/2025 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  | 01/07/2025 | 29 | 0 | 29 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/22/2026 | N | EXP | 365 | 02/28/2025 | 03/17/2025 | 18 | 0 | 18 |  |  | 4/22/2025 | Connected |  | N
National Grid | HANSON | 396601 | 02341 | 17.76 | Solar | 05_07_95W2 | 12/01/2021 | 01/07/2022 | 7 | 3 | 4 | 12/10/2021 | 12/10/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2022 |  | 3/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2022 | Connected |  | Y
National Grid | WEST BRIDGEWATER | 177901 | 02379 | 300 | Natural Gas | 05_07_912W21 | 06/15/2017 | 06/15/2017 | 6 | 6 | 0 | 06/26/2017 | 06/26/2017 | 141 | 2 | 139 | 08/17/2017 | 09/14/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 09/14/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 6/21/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 178180 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 177810 | 02019 | 7.6 | Solar | 05_05_335W1 | 03/31/2017 | 03/31/2017 | 5 | 2 | 3 | 04/07/2017 | 04/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2017 | 03/31/2017 | 4/5/2018 | Y | EXP | 36 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/14/2017 | 1/30/2018 | Connected |  | N
National Grid | ORANGE | 731745 | 01364 | 0 | Other | 05_09_705W3 | 11/05/2025 | 11/09/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 60 | 49 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 176026 | 01581 | 266 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 7 | 3 | 4 | 04/09/2015 | 04/09/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 03/30/2015 | 8/25/2015 | Y | EXP |  | 03/29/2016 | 06/02/2016 | 45 | 0 | 45 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 479096 | 02368 | 6 | Solar | 05_07_5W3 | 01/16/2023 | 01/17/2023 | 1 | 0 | 1 | 01/18/2023 | 01/18/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 3/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2023 | Connected |  | N
National Grid | SEEKONK | 174357 | 02771 | 12 | Solar | 05_05_7L1 | 05/15/2012 | 05/15/2012 | 7 | 0 | 7 | 05/29/2012 | 05/29/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2012 |  | 7/27/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 9/6/2012 | 9/6/2012 | 11/29/2012 | Connected |  | N
National Grid | LYNN | 223576 | 01905 | 33.3 | Solar | 05_12_21J27 | 04/29/2019 |  | 283 | 51 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 669224 | 01262 | 23 | Solar | 05_09_1102W1 | 01/31/2025 | 02/03/2025 | 1 | 0 | 1 | 02/04/2025 | 02/04/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2025 | Connected |  | N
National Grid | PEMBROKE | 411091 | 02359 | 0 | Solar | 05_07_95W2 | 02/23/2022 | 03/09/2022 | 11 | 2 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 268344 | 02324 | 7.6 | Solar | 05_07_912W21 | 02/03/2020 | 02/06/2020 | 2 | 0 | 2 | 02/07/2020 | 02/07/2020 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2020 | Connected |  | N
National Grid | BELCHERTOWN | 178179 | 01007 | 9380 | Solar | 05_09_509L2 | 04/12/2018 | 04/16/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/06/2018 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/18/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 177897 | 02019 | 10 | Solar | 05_05_335W1 | 06/15/2017 | 06/15/2017 | 6 | 6 | 0 | 06/23/2017 | 06/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2017 | 06/15/2017 | 6/20/2018 | Y | EXP | 357 | 10/31/2017 | 11/29/2017 | 15 | 0 | 15 | 12/20/2017 | 12/20/2017 | 12/27/2017 | Connected |  | N
National Grid | WARWICK | 731618 | 01378 | 11.4 | Solar | 05_09_705W3 | 11/12/2025 | 12/22/2025 | 2 | 0 | 2 | 01/06/2026 | 01/06/2026 | 29 | 15 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 176093 | 01581 | 475 | Solar | 05_05_312W2 | 03/30/2015 | 03/30/2015 | 8 | 0 | 8 | 04/10/2015 | 04/10/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/25/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 509035 | 02368 | 10 | Solar | 05_07_5W3 | 05/02/2023 | 05/11/2023 | 7 | 5 | 2 | 05/12/2023 | 05/12/2023 | 50 | 27 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 | 05/02/2023 | 6/23/2025 | Y | EXP | 365 | 12/02/2023 | 12/02/2023 | 1 | 0 | 1 |  |  | 8/24/2024 | Connected |  | N
National Grid | SEEKONK | 175329 | 02771 | 16 | Solar | 05_05_7L1 | 11/11/2014 | 11/11/2014 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 745655 | 01905 | 15.2 | Solar | 05_12_21J28 | 01/15/2026 |  | 34 | 33 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | STOCKBRIDGE | 682299 | 01262 | 50 | Solar | 05_09_1102W1 | 04/29/2025 | 05/02/2025 | 3 | 0 | 3 | 05/05/2025 | 05/05/2025 | 36 | 11 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 7/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | HANSON | 421168 | 02341 | 0 | Solar | 05_07_95W2 | 07/18/2022 | 08/11/2022 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/12/2022 | 09/09/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 343875 | 02324 | 10 | Solar | 05_07_912W21 | 02/25/2021 | 03/08/2021 | 6 | 3 | 3 | 03/09/2021 | 03/09/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2021 |  | 2/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2021 | Connected |  | N
National Grid | BELCHERTOWN | 178460 | 01007 | 4580 | Solar | 05_09_509L2 | 01/18/2018 | 03/02/2018 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2018 | 04/05/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/27/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178094 | 02019 | 10 | Solar | 05_05_335W1 | 07/10/2017 | 07/10/2017 | 5 | 4 | 1 | 07/17/2017 | 07/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2017 | 07/10/2017 | 7/15/2018 | Y | EXP | 361 |  |  | 0 | 0 | 0 | 9/28/2017 | 9/28/2017 | 10/2/2017 | Connected |  | N
National Grid | ERVING | 741209 | 01344 | 999 | Solar | 05_09_705W3 | 01/13/2026 | 02/04/2026 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2026 | 03/05/2026 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 176785 | 01581 | 726 | Solar | 05_05_312W2 | 01/13/2016 | 01/13/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/19/2016 | 01/27/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2016 | 01/13/2016 | 1/19/2017 | Y | STD | 246 |  |  | 0 | 0 | 0 | 12/22/2016 | 12/22/2016 | 12/22/2016 | Connected |  | N
National Grid | RANDOLPH | 522183 | 02368 | 6 | Solar | 05_07_5W3 | 05/03/2023 | 05/04/2023 | 1 | 0 | 1 | 05/05/2023 | 05/05/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/13/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2023 | Connected |  | N
National Grid | SEEKONK | 175359 | 02771 | 16 | Solar | 05_05_7L1 | 11/11/2014 | 11/11/2014 | 5 | 0 | 5 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2014 |  | 1/30/2015 | N | EXP | 7 |  |  | 0 | 0 | 0 | 1/21/2015 | 1/21/2015 | 6/17/2016 | Connected |  | N
National Grid | LYNN | 176054 | 01905 | 3 | Solar | 05_12_21J28 | 01/30/2015 | 01/30/2015 | 18 | 18 | 0 | 03/02/2015 | 03/02/2015 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 |  | 6/30/2015 | N | EXP | 75 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 685253 | 01262 | 23.78 | Solar | 05_09_1102W1 | 04/16/2025 | 04/25/2025 | 5 | 1 | 4 | 04/28/2025 | 04/28/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2025 | Connected |  | N
National Grid | HANOVER | 456914 | 02339 | 6.96 | Solar | 05_07_95W2 | 09/14/2022 | 09/21/2022 | 6 | 5 | 1 | 09/22/2022 | 09/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2022 | 09/14/2022 | 10/21/2023 | Y | EXP | 365 | 11/05/2022 | 12/21/2022 | 47 | 0 | 47 |  |  | 1/12/2023 | Connected |  | N
National Grid | BRIDGEWATER | 365913 | 02324 | 15.12 | Solar | 05_07_912W21 | 06/24/2021 | 06/30/2021 | 4 | 0 | 4 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  | 10/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2022 | Connected |  | N
National Grid | BELCHERTOWN | 178459 | 01007 | 8730 | Solar | 05_09_509L2 | 01/18/2018 | 03/02/2018 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/02/2018 | 04/05/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/27/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178155 | 02019 | 4400 | Solar | 05_05_335W1 | 12/21/2017 | 12/21/2017 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/29/2018 | 33 | 20 | 13 |  |  | 0 | 0 | 0 | 01/23/2019 | 08/05/2019 | 136 | 68 | 68 | 11/15/2018 | 12/21/2017 | 12/30/2021 | Y | STD | 372 | 03/18/2021 | 10/12/2021 | 203 | 83 | 120 |  |  | 12/15/2021 | Connected |  | N
National Grid | ORANGE | 745794 | 01364 | 11.5 | Solar | 05_09_705W3 | 01/16/2026 | 01/22/2026 | 3 | 0 | 3 | 01/23/2026 | 01/23/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 178271 | 01581 | 766.6 | Solar | 05_05_312W2 | 01/09/2018 | 01/09/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/12/2018 | 03/10/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2018 | 01/09/2018 | 2/26/2021 | Y | STD | 712 | 10/28/2020 | 12/14/2020 | 47 | 0 | 47 | 2/16/2021 | 2/16/2021 | 2/26/2021 | Connected |  | N
National Grid | RANDOLPH | 528175 | 02368 | 7.6 | Solar | 05_07_5W3 | 05/30/2023 | 06/01/2023 | 2 | 0 | 2 | 06/02/2023 | 06/02/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176576 | 02771 | 6 | Solar | 05_05_7L1 | 02/11/2016 | 02/11/2016 | 9 | 9 | 0 | 02/26/2016 | 02/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2016 | 02/11/2016 | 2/17/2017 | Y | EXP | 323 | 08/11/2016 | 08/23/2016 | 8 | 0 | 8 | 10/28/2016 | 10/28/2016 | 11/3/2016 | Connected |  | N
National Grid | LYNN | 649089 | 01902 | 7.475 | Solar | 05_12_21J28 | 10/23/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 37 | 21 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2025 | 10/23/2024 | 2/6/2026 | Y | EXP | 365 | 03/15/2025 | 03/25/2025 | 11 | 0 | 11 |  |  | 5/28/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 268625 | 01262 | 4999 | Solar | 05_09_1103W1 | 03/02/2020 | 05/01/2020 | 42 | 37 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2020 | 05/29/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2021 | 03/02/2020 | 12/14/2026 | Y | STD | 889 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HANOVER | 608928 | 02339 | 14.5 | Solar | 05_07_95W2 | 05/29/2024 | 06/14/2024 | 2 | 0 | 2 | 06/17/2024 | 06/17/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2024 |  | 7/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/15/2024 | Connected |  | N
National Grid | BRIDGEWATER | 380096 | 02324 | 15.2 | Solar | 05_07_912W21 | 09/05/2021 | 09/07/2021 | 1 | 0 | 1 | 09/08/2021 | 09/08/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2021 |  | 9/6/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 178623 | 01007 | 8.96 | Solar | 05_09_509L2 | 02/02/2018 | 02/02/2018 | 27 | 8 | 19 | 03/29/2018 | 03/29/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2018 |  | 2/7/2019 | N | EXP | 314 |  |  | 0 | 0 | 0 |  |  | 8/3/2018 | Connected |  | N
National Grid | BELLINGHAM | 178261 | 02019 | 100 | Solar | 05_05_335W1 | 04/17/2018 | 04/17/2018 | 61 | 15 | 46 | 07/13/2018 | 07/13/2018 | 54 | 54 | 0 | 10/18/2018 | 11/20/2018 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  | 11/20/2018 | 22 | 3 | 19 |  |  | 0 | 0 | 0 | 12/17/2018 | 04/17/2018 | 6/15/2020 | Y | EXP | 329 | 02/11/2020 | 02/13/2020 | 2 | 0 | 2 |  |  | 6/8/2020 | Connected |  | N
National Grid | ORANGE | 747866 | 01364 | 17.6 | Solar | 05_09_705W3 | 01/28/2026 | 02/18/2026 | 14 | 13 | 1 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 351004 | 01581 | 220 | Solar | 05_05_312W2 | 05/20/2021 | 07/22/2021 | 43 | 33 | 10 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 | 05/20/2021 | 11/21/2023 | Y | STD | 263 | 03/30/2023 | 04/15/2023 | 16 | 0 | 16 |  |  | 11/29/2023 | Connected |  | N
National Grid | RANDOLPH | 531563 | 02368 | 100 | Solar | 05_07_5W3 | 06/08/2023 | 09/21/2023 | 72 | 62 | 10 | 09/22/2023 | 09/22/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176575 | 02771 | 6 | Solar | 05_05_7L1 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/17/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 175306 | 01902 | 232 | Solar | 05_12_21J29 | 06/25/2014 | 06/25/2014 | 6 | 0 | 6 | 07/07/2014 | 07/07/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 10/31/2014 | N | EXP | 95 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 12/31/2014 | Connected |  | N
National Grid | STOCKBRIDGE | 530128 | 01262 | 240 | Solar | 05_09_1103W1 | 06/07/2023 | 08/21/2023 | 51 | 40 | 11 |  |  | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2024 | 06/07/2023 | 4/29/2026 | Y | STD | 252 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | HANSON | 644210 | 02341 | 5.76 | Solar | 05_07_95W2 | 10/02/2024 | 11/12/2024 | 19 | 14 | 5 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/02/2024 | 1/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | BRIDGEWATER | 436362 | 02324 | 7.6 | Solar | 05_07_912W21 | 06/08/2022 | 06/09/2022 | 1 | 0 | 1 | 06/10/2022 | 06/10/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 185083 | 01007 | 499.9 | Solar | 05_09_509L2 | 05/11/2018 | 05/11/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/07/2018 | 06/19/2018 | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178447 | 02019 | 1382 | Solar | 05_05_335W1 | 04/03/2018 | 04/03/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2018 | 06/05/2018 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  | 11/19/2021 | N | STD | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 174414 | 01364 | 500 | Solar | 05_09_705W3 | 06/22/2012 | 06/22/2012 | 6 | 0 | 6 | 07/05/2012 | 07/05/2012 | 370 | 0 | 370 | 09/27/2013 | 10/08/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  | 10/08/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 11/5/2013 |  | 12/30/2013 | N | EXP | 55 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 384611 | 01581 | 400 | Solar | 05_05_312W2 | 06/13/2022 | 08/12/2022 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2022 | 09/13/2022 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 536421 | 02368 | 3.8 | Solar | 05_07_5W3 | 07/10/2023 | 07/11/2023 | 1 | 0 | 1 | 07/12/2023 | 07/12/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2023 |  | 8/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 176825 | 02771 | 9 | Solar | 05_05_7L1 | 01/15/2016 | 01/15/2016 | 1 | 1 | 0 | 01/19/2016 | 01/19/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2016 |  | 1/20/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 4/12/2016 | Connected |  | N
National Grid | LYNN | 177206 | 01905 | 133.2 | Solar | 05_12_21J29 | 02/01/2017 | 02/01/2017 | 3 | 2 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/7/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 722382 | 01240 | 11.5 | Solar | 05_09_1103W1 | 09/26/2025 | 10/06/2025 | 4 | 0 | 4 | 10/20/2025 | 10/20/2025 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANOVER | 649658 | 02339 | 10 | Solar | 05_07_95W2 | 10/25/2024 |  | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 456937 | 02324 | 22.8 | Solar | 05_07_912W21 | 09/06/2022 | 09/08/2022 | 3 | 2 | 1 | 09/09/2022 | 09/09/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 |  | 10/11/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 185030 | 01007 | 1000 | Solar | 05_09_509L2 | 06/04/2018 | 06/04/2018 | 5 | 3 | 2 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 07/05/2018 | 07/03/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178478 | 02019 | 270 | Solar | 05_05_335W1 | 04/03/2018 | 04/03/2018 | 1 | 0 | 1 |  |  | 38 | 11 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2018 |  | 11/19/2021 | N | STD | 68 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 174976 | 01364 | 557 | Solar | 05_09_705W3 | 09/20/2011 | 09/20/2011 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2011 | 01/03/2012 | 58 | 0 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2012 |  | 11/30/2012 | N | STD | 1 | 06/04/2013 | 07/25/2013 | 35 | 0 | 35 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 639701 | 01581 | 333 | Solar | 05_05_312W3 | 09/12/2024 | 10/22/2024 | 14 | 8 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2024 | 11/20/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 542276 | 02368 | 9.57 | Solar | 05_07_5W3 | 07/25/2023 | 08/01/2023 | 5 | 4 | 1 | 08/02/2023 | 08/02/2023 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2023 | 07/25/2023 | 8/27/2024 | Y | EXP | 365 | 10/21/2023 | 10/23/2023 | 3 | 0 | 3 |  |  | 10/27/2023 | Connected |  | N
National Grid | SEEKONK | 176855 | 02771 | 10 | Solar | 05_05_7L1 | 11/12/2015 | 11/12/2015 | 3 | 3 | 0 | 11/18/2015 | 11/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2015 |  | 11/18/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 5/27/2016 | Connected |  | N
National Grid | LYNN | 204170 | 01905 | 139.9 | Solar | 05_12_21J29 | 12/18/2018 | 01/09/2019 | 13 | 8 | 5 | 01/10/2019 | 01/10/2019 | 19 | 0 | 19 | 03/11/2019 | 03/21/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 03/21/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 724367 | 01262 | 6.631 | Solar | 05_09_1103W1 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 24 | 16 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  | 11/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANSON | 650272 | 02341 | 12.35 | Solar | 05_07_95W2 | 10/28/2024 | 11/13/2024 | 3 | 1 | 2 | 11/14/2024 | 11/14/2024 | 15 | 2 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2024 | 10/28/2024 | 12/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | BRIDGEWATER | 634696 | 02324 | 30.4 | Solar | 05_07_912W21 | 09/21/2024 |  | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 185029 | 01007 | 500 | Solar | 05_09_509L2 | 05/16/2018 | 06/19/2018 | 23 | 14 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2018 | 07/03/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 178594 | 02019 | 19 | Solar | 05_05_335W1 | 03/14/2018 | 03/14/2018 | 9 | 9 | 0 | 03/30/2018 | 03/30/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2018 |  | 3/20/2019 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 175349 | 01364 | 69.6 | Solar | 05_09_705W3 | 07/09/2014 | 07/09/2014 | 1 | 0 | 1 | 07/10/2014 | 07/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2014 |  | 11/28/2014 | N | EXP | 123 |  |  | 0 | 0 | 0 | 7/28/2014 | 7/28/2014 | 12/16/2016 | Connected |  | N
National Grid | WESTBOROUGH | 676971 | 01581 | 750 | Solar | 05_05_312W3 | 04/08/2025 | 06/26/2025 | 54 | 44 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2025 | 07/23/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 545250 | 02368 | 7.6 | Solar | 05_07_5W3 | 08/02/2023 | 08/07/2023 | 3 | 0 | 3 | 08/08/2023 | 08/08/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/31/2023 | 08/02/2023 | 9/10/2024 | Y | EXP | 365 | 05/02/2024 | 06/18/2024 | 48 | 0 | 48 |  |  | 6/26/2024 | Connected |  | N
National Grid | SEEKONK | 177052 | 02771 | 15.2 | Solar | 05_05_7L1 | 01/11/2017 | 01/11/2017 | 3 | 2 | 1 | 01/17/2017 | 01/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2017 | 01/11/2017 | 1/16/2018 | Y | EXP | 361 | 06/14/2017 | 06/22/2017 | 6 | 0 | 6 | 9/27/2017 | 9/27/2017 | 10/3/2017 | Connected |  | N
National Grid | LYNN | 266087 | 01905 | 6 | Solar | 05_12_21J30 | 10/12/2020 | 10/19/2020 | 5 | 5 | 0 | 10/20/2020 | 10/20/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2020 |  | 10/18/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 731518 | 01240 | 5.76 | Solar | 05_09_1103W1 | 12/05/2025 | 12/09/2025 | 2 | 0 | 2 | 01/02/2026 | 01/02/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2026 | 12/05/2025 | 2/26/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | HANOVER | 654971 | 02339 | 10 | Solar | 05_07_95W2 | 11/19/2024 | 12/19/2024 | 3 | 0 | 3 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/19/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2025 | Connected |  | N
National Grid | BRIDGEWATER | 648012 | 02324 | 10 | Solar | 05_07_912W21 | 10/30/2024 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 185023 | 01007 | 500 | Solar | 05_09_509L2 | 05/10/2018 | 06/26/2018 | 33 | 33 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/27/2018 | 07/03/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 185872 | 02019 | 1000 | Solar | 05_05_335W1 | 07/19/2018 | 07/19/2018 | 15 | 14 | 1 |  |  | 36 | 14 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 | 07/19/2018 | 11/23/2021 | Y | STD | 148 | 11/01/2019 | 07/02/2021 | 609 | 362 | 247 |  |  | 10/22/2021 | Connected |  | N
National Grid | ORANGE | 175976 | 01364 | 920 | Solar | 05_09_705W3 | 01/22/2015 | 01/22/2015 | 9 | 8 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/05/2015 | 03/16/2015 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2015 | 01/22/2015 | 12/31/2016 | Y | STD | 515 | 03/16/2017 | 05/23/2017 | 47 | 0 | 47 | 5/30/2017 | 5/30/2017 | 5/30/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 174837 | 01532 | 30 | Solar | 05_05_312W3 | 09/04/2012 | 09/04/2012 | 6 | 0 | 6 | 09/13/2012 | 09/13/2012 | 433 | 0 | 433 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2012 |  | 12/28/2012 | N | EXP | 24 |  |  | 0 | 0 | 0 | 12/4/2012 | 12/4/2012 |  | Withdrawn |  | Y
National Grid | RANDOLPH | 566616 | 02368 | 0 | Solar | 05_07_5W3 | 10/26/2023 | 10/27/2023 | 1 | 0 | 1 | 08/12/2024 | 08/12/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2024 | Connected |  | N
National Grid | SEEKONK | 177526 | 02771 | 6 | Solar | 05_05_7L1 | 09/30/2016 | 09/30/2016 | 0 | 0 | 0 | 10/04/2016 | 10/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2016 |  | 10/9/2017 | N | EXP | 369 |  |  | 0 | 0 | 0 | 2/13/2017 | 2/13/2017 | 2/16/2017 | Connected |  | N
National Grid | LYNN | 269148 | 01905 | 7.6 | Solar | 05_12_21J30 | 03/16/2020 | 04/01/2020 | 11 | 11 | 0 | 04/02/2020 | 04/02/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2020 |  | 4/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 749095 | 01240 | 70 | Solar | 05_09_1103W1 | 02/06/2026 |  | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PEMBROKE | 665433 | 02359 | 3.8 | Solar | 05_07_95W2 | 01/13/2025 | 01/22/2025 | 5 | 0 | 5 | 01/23/2025 | 01/23/2025 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 664370 | 02324 | 5.76 | Solar | 05_07_912W21 | 01/08/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2025 | Connected |  | N
National Grid | BELCHERTOWN | 192377 | 01007 | 4998 | Solar | 05_09_509L2 | 10/01/2018 | 10/26/2018 | 19 | 10 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 | 01/04/2019 | 45 | 26 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 185870 | 01756 | 1000 | Solar | 05_05_335W1 | 06/07/2018 | 06/07/2018 | 732 | 0 | 732 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 176237 | 01364 | 1000 | Solar | 05_09_705W3 | 02/17/2015 | 02/17/2015 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 175231 | 01581 | 504 | Solar | 05_05_312W3 | 06/10/2014 | 06/10/2014 | 7 | 3 | 4 | 06/23/2014 | 06/23/2014 | 64 | 0 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 561990 | 02368 | 10 | Solar | 05_07_5W3 | 11/01/2023 | 11/02/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2023 | 11/01/2023 | 6/20/2025 | Y | EXP | 465 | 03/14/2024 | 03/16/2024 | 3 | 0 | 3 |  |  | 7/18/2025 | Connected |  | N
National Grid | SEEKONK | 177717 | 02771 | 15.2 | Solar | 05_05_7L1 | 07/27/2017 | 07/27/2017 | 5 | 5 | 0 | 08/03/2017 | 08/03/2017 | 54 | 0 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 8/1/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 346631 | 01902 | 7.6 | Solar | 05_12_21J30 | 03/31/2021 | 04/06/2021 | 3 | 0 | 3 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2021 |  | 6/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 748902 | 01266 | 7.6 | Solar | 05_09_1103W1 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANSON | 671391 | 02341 | 5.76 | Solar | 05_07_95W2 | 02/11/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2025 |  | 5/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2025 | Connected |  | N
National Grid | BRIDGEWATER | 675303 | 02324 | 5.76 | Solar | 05_07_912W21 | 04/03/2025 |  | 76 | 73 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 197687 | 01007 | 3.8 | Solar | 05_09_509L2 | 11/29/2018 | 12/10/2018 | 6 | 0 | 6 | 12/11/2018 | 12/11/2018 | 269 | 0 | 269 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 11/29/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 209959 | 01756 | 1000 | Battery Add-On | 05_05_335W1 | 02/25/2019 | 03/18/2019 | 15 | 6 | 9 |  |  | 139 | 125 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 176267 | 01364 | 1000 | Solar | 05_09_705W3 | 02/17/2015 | 02/17/2015 | 9 | 5 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2015 | 04/01/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 175601 | 01581 | 460 | Solar | 05_05_312W3 | 10/15/2014 | 10/15/2014 | 5 | 0 | 5 | 10/23/2014 | 10/23/2014 | 0 | 0 | 0 | 01/27/2015 | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  | 03/06/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 | 3/20/2015 |  | 1/31/2015 | N | EXP | 48 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 2/4/2016 | Connected |  | N
National Grid | RANDOLPH | 574106 | 02368 | 4.35 | Solar | 05_07_5W3 | 12/13/2023 | 12/19/2023 | 4 | 1 | 3 | 12/20/2023 | 12/20/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 178436 | 02771 | 20 | Solar | 05_05_7L1 | 01/16/2018 | 01/16/2018 | 0 | 0 | 0 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 3/11/2019 | N | EXP | 369 |  |  | 0 | 0 | 0 |  |  | 8/15/2018 | Connected |  | N
National Grid | LYNN | 653772 | 01902 | 20 | Solar | 05_12_21J30 | 11/12/2024 | 11/19/2024 | 5 | 3 | 2 | 11/20/2024 | 11/20/2024 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 752724 | 01262 | 150 | Solar | 05_09_1103W1 | 03/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PEMBROKE | 684271 | 02359 | 17.86 | Solar | 05_07_95W2 | 04/10/2025 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 688640 | 02324 | 10 | Solar | 05_07_912W21 | 05/21/2025 | 05/27/2025 | 3 | 0 | 3 | 05/28/2025 | 05/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/7/2025 | Connected |  | N
National Grid | BELCHERTOWN | 225069 | 01007 | 0 | Solar | 05_09_509L2 | 05/03/2019 | 05/08/2019 | 2 | 0 | 2 | 05/09/2019 | 05/09/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2019 | Connected |  | N
National Grid | MENDON | 297438 | 01756 | 7.6 | Solar | 05_05_335W1 | 07/01/2020 | 07/06/2020 | 2 | 0 | 2 | 07/07/2020 | 07/07/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 07/01/2020 | 6/1/2021 | Y | EXP | 365 | 11/04/2020 | 02/12/2021 | 100 | 0 | 100 |  |  | 6/1/2021 | Connected |  | N
National Grid | ORANGE | 176492 | 01364 | 80 | Solar | 05_09_705W3 | 12/09/2015 | 12/09/2015 | 5 | 5 | 0 | 12/17/2015 | 12/17/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/15/2016 | N | EXP | 331 |  |  | 0 | 0 | 0 | 12/13/2016 | 12/13/2016 | 12/29/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 177986 | 01532 | 366.3 | Solar | 05_05_312W3 | 08/28/2017 | 08/28/2017 | 99 | 96 | 3 | 02/01/2018 | 02/01/2018 | 22 | 0 | 22 | 03/19/2018 | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 04/13/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 4/27/2018 |  | 9/4/2018 | N | EXP | 13 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 583670 | 02368 | 7.6 | Solar | 05_07_5W3 | 02/09/2024 | 02/12/2024 | 1 | 0 | 1 | 02/13/2024 | 02/13/2024 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2024 |  | 3/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 241012 | 02771 | 7.6 | Solar | 05_05_7L1 | 06/26/2019 | 07/03/2019 | 4 | 0 | 4 | 07/05/2019 | 07/05/2019 | 10 | 6 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2019 |  | 7/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2019 | Connected |  | N
National Grid | LYNN | 176503 | 01902 | 64.8 | Solar | 05_12_21J32 | 02/09/2016 | 02/09/2016 | 2 | 2 | 0 | 02/12/2016 | 02/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/15/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 10/13/2016 | 10/13/2016 | 10/19/2016 | Connected |  | N
National Grid | LENOX | 175061 | 01240 | 48.37 | Solar | 05_09_1103W1 | 10/19/2012 | 10/19/2012 | 5 | 0 | 5 | 11/06/2012 | 11/06/2012 | 332 | 0 | 332 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 12/17/2012 | N | EXP | 6 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PEMBROKE | 707155 | 02359 | 6.631 | Solar | 05_07_95W2 | 07/24/2025 | 09/15/2025 | 25 | 20 | 5 | 09/16/2025 | 09/16/2025 | 24 | 9 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2025 | Connected |  | N
National Grid | BRIDGEWATER | 728492 | 02324 | 5.76 | Solar | 05_07_912W21 | 10/22/2025 | 10/24/2025 | 2 | 0 | 2 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | BELCHERTOWN | 244028 | 01007 | 0 | Solar | 05_09_509L2 | 07/22/2019 | 07/30/2019 | 5 | 0 | 5 | 07/31/2019 | 07/31/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2020 | Connected |  | N
National Grid | MENDON | 299593 | 01756 | 1500 | Solar | 05_05_335W1 | 02/08/2021 | 03/17/2021 | 26 | 19 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/18/2021 | 04/13/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ORANGE | 178086 | 01364 | 4995 | Solar | 05_09_705W3 | 05/08/2017 | 06/02/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/26/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 05/08/2017 | 10/27/2021 | Y | STD | 35 | 07/30/2021 | 09/24/2021 | 57 | 3 | 54 |  |  | 10/27/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 319057 | 01532 | 249 | Solar | 05_05_312W3 | 10/13/2020 | 11/04/2020 | 15 | 8 | 7 | 11/18/2020 | 11/18/2020 | 63 | 50 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2023 | Connected |  | N
National Grid | RANDOLPH | 587703 | 02368 | 8.7 | Solar | 05_07_5W3 | 02/08/2024 | 02/16/2024 | 7 | 5 | 2 | 02/20/2024 | 02/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2024 | 02/08/2024 | 3/27/2025 | Y | EXP | 365 | 05/09/2024 | 06/27/2024 | 50 | 0 | 50 |  |  | 6/29/2024 | Connected |  | N
National Grid | SEEKONK | 278241 | 02771 | 12 | Solar | 05_05_7L1 | 02/05/2020 | 02/19/2020 | 9 | 9 | 0 | 02/20/2020 | 02/20/2020 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 196937 | 01902 | 3.84 | Solar | 05_12_21J32 | 11/05/2018 | 11/08/2018 | 3 | 2 | 1 | 11/09/2018 | 11/09/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 175060 | 01262 | 112.23 | Solar | 05_09_1103W1 | 10/18/2012 | 10/18/2012 | 5 | 0 | 5 | 11/06/2012 | 11/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 | 10/18/2012 | 12/17/2012 | Y | EXP | 6 | 08/08/2013 | 08/15/2013 | 5 | 0 | 5 | 4/2/2013 | 4/2/2013 | 5/1/2013 | Connected |  | N
National Grid | HANSON | 438749 | 02341 | 375 | Solar | 05_07_95W3 | 10/10/2022 | 11/07/2022 | 21 | 12 | 9 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BRIDGEWATER | 503065 | 02324 | 1680 | Solar | 05_07_912W55 | 03/31/2023 | 04/17/2023 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2023 | 05/15/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELCHERTOWN | 261448 | 01007 | 7.6 | Solar | 05_09_509L2 | 11/04/2019 | 11/05/2019 | 0 | 0 | 0 | 11/06/2019 | 11/06/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2019 | 11/04/2019 | 11/4/2020 | Y | EXP | 365 | 01/25/2020 | 02/04/2020 | 9 | 0 | 9 |  |  | 5/19/2020 | Connected |  | N
National Grid | BELLINGHAM | 335851 | 02019 | 6.96 | Solar | 05_05_335W1 | 01/18/2021 | 01/26/2021 | 5 | 1 | 4 | 01/27/2021 | 01/27/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2021 | 01/18/2021 | 5/20/2022 | Y | EXP | 365 | 08/21/2021 | 09/29/2021 | 34 | 3 | 31 |  |  | 12/18/2021 | Connected |  | N
National Grid | ORANGE | 178085 | 01364 | 4995 | Solar | 05_09_705W3 | 05/08/2017 | 06/02/2017 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 06/26/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2018 | 05/08/2017 | 10/27/2021 | Y | STD | 77 | 07/30/2021 | 09/24/2021 | 57 | 3 | 54 |  |  | 10/27/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 409851 | 01532 | 86.4 | Solar | 05_05_312W3 | 02/04/2022 | 02/09/2022 | 3 | 0 | 3 | 02/10/2022 | 02/10/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2022 | 02/04/2022 | 1/11/2023 | Y | EXP | 196 | 12/01/2022 | 12/06/2022 | 6 | 6 | 0 |  |  | 1/19/2023 | Connected |  | N
National Grid | RANDOLPH | 599536 | 02368 | 6 | Solar | 05_07_5W3 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 | 03/26/2024 | 7/6/2025 | Y | EXP | 365 | 07/25/2024 | 10/01/2024 | 69 | 0 | 69 |  |  | 12/11/2024 | Connected |  | N
National Grid | SEEKONK | 291280 | 02771 | 6 | Solar | 05_05_7L1 | 05/10/2020 | 05/14/2020 | 3 | 0 | 3 | 05/15/2020 | 05/15/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2020 | Connected |  | N
National Grid | LYNN | 606809 | 01905 | 10 | Solar | 05_12_21J32 | 04/25/2024 |  | 26 | 25 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 175110 | 01240 | 1000 | Solar | 05_09_1103W1 | 04/22/2013 | 04/22/2013 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/03/2013 | 06/13/2013 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 715555 | 02359 | 100 | Solar | 05_07_95W3 | 09/05/2025 | 10/10/2025 | 25 | 17 | 8 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BRIDGEWATER | 644736 | 02324 | 119.9 | Solar | 05_07_912W55 | 10/03/2024 | 08/07/2025 | 208 | 198 | 10 | 08/08/2025 | 08/08/2025 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 7/2/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELCHERTOWN | 291205 | 01007 | 0 | Other | 05_09_509L2 | 09/02/2020 | 09/21/2020 | 11 | 6 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/22/2020 | 10/08/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 388023 | 02019 | 9.8 | Solar | 05_05_335W1 | 10/27/2021 | 11/02/2021 | 4 | 0 | 4 | 11/03/2021 | 11/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 | 10/27/2021 | 5/18/2023 | Y | EXP | 365 | 02/16/2022 | 05/18/2022 | 92 | 0 | 92 |  |  | 6/7/2022 | Connected |  | N
National Grid | ORANGE | 178406 | 01364 | 4990 | Solar | 05_09_705W3 | 04/02/2018 | 04/05/2018 | 3 | 2 | 1 |  |  | 39 | 23 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 552640 | 01532 | 333 | Solar | 05_05_312W3 | 11/21/2023 |  | 192 | 183 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 602927 | 02368 | 7.6 | Solar | 05_07_5W3 | 04/15/2024 | 04/17/2024 | 2 | 0 | 2 | 04/18/2024 | 04/18/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 296695 | 02771 | 11.52 | Solar | 05_05_7L1 | 06/16/2020 | 06/18/2020 | 1 | 0 | 1 | 06/19/2020 | 06/19/2020 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 621560 | 01905 | 10 | Solar | 05_12_21J32 | 07/01/2024 | 07/09/2024 | 1 | 0 | 1 | 07/10/2024 | 07/10/2024 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2024 | Connected |  | N
National Grid | LENOX | 175155 | 01240 | 16.34 | Solar | 05_09_1103W1 | 11/11/2013 | 11/11/2013 | 13 | 6 | 7 | 12/02/2013 | 12/02/2013 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2013 |  | 12/31/2013 | N | EXP | 28 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 734346 | 02339 | 13.3 | Solar | 05_07_95W3 | 11/21/2025 | 11/30/2025 | 4 | 1 | 3 | 12/01/2025 | 12/01/2025 | 65 | 25 | 40 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BRIDGEWATER | 728348 | 02324 | 10 | Solar | 05_07_912W55 | 10/22/2025 | 12/19/2025 | 4 | 0 | 4 | 01/21/2026 | 01/21/2026 | 29 | 20 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | BELCHERTOWN | 292836 | 01007 | 2.16 | Solar | 05_09_509L2 | 06/10/2020 | 06/15/2020 | 2 | 0 | 2 | 06/16/2020 | 06/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2020 | 06/10/2020 | 6/1/2021 | Y | EXP | 365 | 12/15/2020 | 01/05/2021 | 21 | 0 | 21 |  |  | 2/24/2021 | Connected |  | N
National Grid | BELLINGHAM | 392259 | 02019 | 6 | Solar | 05_05_335W1 | 11/23/2021 | 01/07/2022 | 4 | 0 | 4 | 12/01/2021 | 12/01/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2021 |  | 4/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2022 | Connected |  | Y
National Grid | ORANGE | 178430 | 01364 | 636 | Solar | 05_09_705W3 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 582654 | 01581 | 0 | Solar | 05_05_312W3 | 02/02/2024 | 03/21/2024 | 34 | 32 | 2 | 03/22/2024 | 03/22/2024 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 |  | 4/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2024 | Connected |  | N
National Grid | RANDOLPH | 606501 | 02368 | 5.76 | Solar | 05_07_5W3 | 04/24/2024 | 06/05/2024 | 28 | 23 | 5 | 06/06/2024 | 06/06/2024 | 37 | 24 | 13 | 08/16/2024 | 10/25/2024 | 49 | 5 | 44 |  |  | 0 | 0 | 0 |  | 10/25/2024 | 49 | 5 | 44 |  |  | 0 | 0 | 0 | 11/12/2024 | 04/24/2024 | 1/23/2026 | Y | EXP | 365 | 04/30/2025 | 10/23/2025 | 177 | 0 | 177 |  |  | 11/26/2025 | Connected |  | N
National Grid | SEEKONK | 336489 | 02771 | 6 | Solar | 05_05_7L1 | 01/21/2021 | 01/26/2021 | 1 | 1 | 0 | 01/27/2021 | 01/27/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 1/25/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 634661 | 01905 | 5.525 | Solar | 05_12_21J32 | 08/22/2024 | 08/30/2024 | 3 | 0 | 3 | 09/03/2024 | 09/03/2024 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2024 |  | 11/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2025 | Connected |  | Y
National Grid | LENOX | 175358 | 01240 | 19 | Solar | 05_09_1103W1 | 09/12/2014 | 09/12/2014 | 5 | 0 | 5 | 09/22/2014 | 09/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2014 |  | 11/28/2014 | N | EXP | 66 |  |  | 0 | 0 | 0 | 9/23/2014 | 9/23/2014 | 11/13/2014 | Connected |  | N
National Grid | HANSON | 740992 | 02341 | 15.2 | Solar | 05_07_95W3 | 12/17/2025 | 01/06/2026 | 12 | 7 | 5 | 01/07/2026 | 01/07/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 742676 | 02324 | 6.46 | Solar | 05_07_912W55 | 12/30/2025 | 01/05/2026 | 3 | 0 | 3 | 01/21/2026 | 01/21/2026 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 294641 | 01007 | 0 | Solar | 05_09_509L2 | 06/11/2020 | 06/18/2020 | 4 | 0 | 4 | 06/19/2020 | 06/19/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2020 | Connected |  | N
National Grid | BELLINGHAM | 409458 | 02019 | 3.8 | Solar | 05_05_335W1 | 02/10/2022 | 02/14/2022 | 2 | 0 | 2 | 02/15/2022 | 02/15/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 | 02/10/2022 | 11/17/2023 | Y | EXP | 365 | 08/18/2022 | 10/28/2022 | 72 | 0 | 72 |  |  | 12/5/2022 | Connected |  | N
National Grid | ERVING | 178604 | 01344 | 3000 | Solar | 05_09_705W3 | 04/09/2018 | 04/10/2018 | 20 | 20 | 0 |  |  | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 743633 | 01532 | 23 | Battery Add-On | 05_05_312W4 | 01/08/2026 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  | 2/17/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 618898 | 02368 | 13.6 | Solar | 05_07_5W3 | 06/20/2024 | 07/09/2024 | 3 | 0 | 3 | 07/10/2024 | 07/10/2024 | 18 | 7 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/20/2024 | 8/6/2025 | Y | EXP | 365 | 10/17/2024 | 02/05/2025 | 112 | 0 | 112 |  |  | 2/13/2025 | Connected |  | N
National Grid | SEEKONK | 363042 | 02771 | 15.2 | Solar | 05_05_7L1 | 06/09/2021 | 06/30/2021 | 15 | 13 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 1/1/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 1/3/2023 | Connected |  | N
National Grid | LYNN | 659725 | 01905 | 8.7 | Solar | 05_12_21J32 | 12/10/2024 | 12/27/2024 | 5 | 0 | 5 | 12/30/2024 | 12/30/2024 | 98 | 75 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 176106 | 01240 | 30 | Solar | 05_09_1103W1 | 06/25/2015 | 06/25/2015 | 8 | 8 | 0 | 07/08/2015 | 07/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 |  | 6/30/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 7/22/2015 | 7/22/2015 | 3/8/2016 | Connected |  | N
National Grid | PEMBROKE | 742324 | 02359 | 5.76 | Solar | 05_07_95W3 | 12/26/2025 | 12/31/2025 | 3 | 0 | 3 | 01/02/2026 | 01/02/2026 | 17 | 6 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/4/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 749485 | 02324 | 23 | Solar | 05_07_912W55 | 02/05/2026 | 02/06/2026 | 1 | 0 | 1 | 02/09/2026 | 02/09/2026 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 335189 | 01007 | 0 | Solar | 05_09_509L2 | 01/06/2021 | 01/07/2021 | 0 | 0 | 0 | 01/08/2021 | 01/08/2021 | 24 | 8 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2021 |  | 1/6/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2021 | Connected |  | N
National Grid | BELLINGHAM | 470892 | 02019 | 9.984 | Solar | 05_05_335W1 | 10/28/2022 | 11/02/2022 | 3 | 0 | 3 | 11/03/2022 | 11/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 |  | 12/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | ORANGE | 178667 | 01364 | 4990 | Solar | 05_09_705W3 | 03/16/2018 | 04/02/2018 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/02/2018 | 05/30/2018 | 42 | 27 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174127 | 01851 | 13.97 | Solar | 05_05_312W4 | 04/26/2012 | 04/26/2012 | 9 | 0 | 9 | 05/14/2012 | 05/14/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2012 |  | 6/29/2012 | N | EXP | 97 |  |  | 0 | 0 | 0 | 8/29/2012 | 8/29/2012 | 10/10/2012 | Connected |  | N
National Grid | RANDOLPH | 629786 | 02368 | 9.28 | Solar | 05_07_5W3 | 08/02/2024 | 10/03/2024 | 5 | 4 | 1 | 10/04/2024 | 10/04/2024 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2025 | Connected |  | N
National Grid | SEEKONK | 451125 | 02771 | 10 | Solar | 05_05_7L1 | 09/01/2022 | 09/06/2022 | 3 | 1 | 2 | 09/07/2022 | 09/07/2022 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2022 | 09/01/2022 | 10/24/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | LYNN | 691724 | 01905 | 5.76 | Solar | 05_12_21J32 | 05/22/2025 | 05/29/2025 | 2 | 0 | 2 | 06/23/2025 | 06/23/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | LENOX | 204149 | 01240 | 250 | Solar | 05_09_1103W1 | 12/18/2018 | 01/08/2019 | 6 | 0 | 6 | 01/09/2019 | 01/09/2019 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/20/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 260959 | 02341 | 0 | Solar | 05_07_95W3 | 10/23/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2019 | 10/23/2019 | 7/8/2020 | Y | EXP | 365 | 01/31/2020 | 02/19/2020 | 19 | 0 | 19 |  |  | 6/15/2020 | Connected |  | N
National Grid | BRIDGEWATER | 174579 | 02324 | 3000 | Solar | 05_07_912W55 | 11/11/2010 | 11/11/2010 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2011 | 03/28/2011 | 43 | 0 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2013 | 11/11/2010 | 12/31/2016 | Y | STD | 1429 | 12/21/2015 | 04/25/2016 | 84 | 0 | 84 | 5/17/2016 | 5/17/2016 | 5/17/2016 | Connected |  | N
National Grid | BELCHERTOWN | 335107 | 01007 | 10 | Solar | 05_09_509L2 | 01/20/2021 | 01/26/2021 | 3 | 2 | 1 | 01/27/2021 | 01/27/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2021 | 01/20/2021 | 1/25/2022 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2021 | Connected |  | N
National Grid | BELLINGHAM | 477584 | 02019 | 6 | Solar | 05_05_335W1 | 12/21/2022 | 09/25/2023 | 190 | 188 | 2 | 09/26/2023 | 09/26/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2023 |  | 11/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/27/2024 | Connected |  | N
National Grid | ORANGE | 184632 | 01364 | 990 | Solar | 05_09_705W3 | 05/10/2018 | 05/10/2018 | 111 | 0 | 111 |  |  | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174164 | 01581 | 10.75 | Solar | 05_05_312W4 | 04/23/2012 | 04/23/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2012 |  | 6/1/2012 | N | EXP | 83 |  |  | 0 | 0 | 0 | 8/23/2012 | 8/23/2012 | 12/21/2012 | Connected |  | N
National Grid | RANDOLPH | 633007 | 02368 | 10 | Solar | 05_07_5W3 | 08/15/2024 | 09/11/2024 | 3 | 0 | 3 | 09/12/2024 | 09/12/2024 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2024 | 08/15/2024 | 10/31/2025 | Y | EXP | 365 | 12/19/2024 | 01/25/2025 | 38 | 0 | 38 |  |  | 2/11/2025 | Connected |  | N
National Grid | SEEKONK | 380801 | 02771 | 11.4 | Solar | 05_05_7L1 | 09/08/2021 | 09/13/2021 | 4 | 3 | 1 | 09/14/2021 | 09/14/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2021 |  | 5/15/2023 | N | EXP | 43 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 701073 | 01905 | 16.32 | Solar | 05_12_21J32 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | LENOX | 278382 | 01240 | 10 | Solar | 05_09_1103W1 | 04/01/2020 | 04/03/2020 | 1 | 1 | 0 | 04/06/2020 | 04/06/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 04/01/2020 | 4/2/2021 | Y | EXP | 365 | 06/06/2020 | 07/08/2020 | 32 | 0 | 32 |  |  | 8/25/2020 | Connected |  | N
National Grid | HANOVER | 295316 | 02339 | 7.6 | Solar | 05_07_95W3 | 06/08/2020 | 06/10/2020 | 1 | 0 | 1 | 06/11/2020 | 06/11/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2020 | Connected |  | N
National Grid | BRIDGEWATER | 174578 | 02324 | 2000 | Solar | 05_07_912W55 | 01/13/2011 | 01/13/2011 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 352557 | 01007 | 0 | Solar | 05_09_509L2 | 04/20/2021 | 04/22/2021 | 1 | 0 | 1 | 04/23/2021 | 04/23/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2021 |  | 6/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2021 | Connected |  | N
National Grid | MENDON | 478755 | 01756 | 7.6 | Solar | 05_05_335W1 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2023 |  | 7/5/2024 | N | EXP | 365 | 07/07/2023 | 07/06/2023 | 0 | 0 | 0 |  |  | 7/21/2023 | Connected |  | N
National Grid | ERVING | 185922 | 01344 | 480 | Solar | 05_09_705W3 | 07/18/2018 | 07/20/2018 | 1 | 0 | 1 |  |  | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2018 |  | 8/9/2019 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/12/2019 | Connected |  | N
National Grid | WESTBOROUGH | 174274 | 01581 | 1000 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 638210 | 02368 | 7.25 | Solar | 05_07_5W3 | 09/06/2024 | 10/07/2024 | 14 | 12 | 2 | 10/08/2024 | 10/08/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 12/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2025 | Connected |  | N
National Grid | SEEKONK | 393693 | 02771 | 0 | Solar | 05_05_7L1 | 11/05/2021 | 11/10/2021 | 4 | 2 | 2 | 11/12/2021 | 11/12/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 1/18/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 1/3/2023 | Connected |  | N
National Grid | LYNN | 567360 | 01905 | 0 | Other | 05_12_21J33 | 04/18/2024 | 02/28/2025 | 214 | 204 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/03/2025 | 07/31/2025 | 105 | 86 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | LENOX | 314341 | 01240 | 0 | Solar | 05_09_1103W1 | 09/22/2020 | 09/24/2020 | 1 | 1 | 0 | 09/25/2020 | 09/25/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  | 10/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PEMBROKE | 375893 | 02359 | 7.6 | Solar | 05_07_95W3 | 08/13/2021 | 09/14/2021 | 21 | 21 | 0 | 09/15/2021 | 09/15/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 12/27/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | BRIDGEWATER | 175194 | 02324 | 800 | Solar | 05_07_912W55 | 12/03/2013 | 12/03/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2013 | 12/23/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2014 | 12/03/2013 | 4/30/2020 | Y | STD | 1893 | 11/16/2019 | 03/12/2020 | 116 | 0 | 116 | 3/25/2020 | 3/24/2020 | 4/9/2020 | Connected |  | N
National Grid | BELCHERTOWN | 367563 | 01007 | 7.6 | Solar | 05_09_509L2 | 08/19/2021 | 12/07/2021 | 4 | 2 | 2 | 08/27/2021 | 08/27/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2021 | 08/19/2021 | 6/30/2023 | Y | EXP | 365 | 04/22/2022 | 05/23/2022 | 32 | 0 | 32 |  |  | 7/6/2022 | Connected |  | N
National Grid | BELLINGHAM | 498788 | 02019 | 15.2 | Solar | 05_05_335W1 | 02/02/2023 | 02/03/2023 | 1 | 0 | 1 | 02/06/2023 | 02/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2023 |  | 3/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2023 | Connected |  | N
National Grid | WARWICK | 189059 | 01378 | 5000 | Solar | 05_09_705W3 | 06/27/2018 | 06/27/2018 | 20 | 20 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2018 | 08/22/2018 | 19 | 13 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174273 | 01581 | 0 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 63 | 0 | 63 |  |  | 0 | 0 | 0 | 04/12/2012 | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 04/12/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/16/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 644185 | 02368 | 5 | Solar | 05_07_5W3 | 10/02/2024 | 10/15/2024 | 1 | 0 | 1 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 10/02/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | SEEKONK | 397991 | 02771 | 10 | Solar | 05_05_7L1 | 12/06/2021 | 12/07/2021 | 2 | 1 | 1 | 12/08/2021 | 12/08/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2022 |  | 1/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2022 | Connected |  | N
National Grid | LYNN | 595928 | 01905 | 3.8 | Solar | 05_12_21J33 | 03/25/2024 | 03/27/2024 | 2 | 1 | 1 | 03/28/2024 | 03/28/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2024 | Connected |  | N
National Grid | LENOX | 344288 | 01240 | 23.1 | Solar | 05_09_1103W1 | 04/02/2021 | 12/03/2021 | 1 | 1 | 0 | 04/06/2021 | 04/06/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2021 |  | 11/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HANSON | 434010 | 02341 | 0 | Battery Add-On | 05_07_95W3 | 08/08/2022 | 08/17/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/18/2022 | 09/15/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175193 | 02324 | 1000 | Solar | 05_07_912W55 | 12/03/2013 | 12/03/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 | 01/14/2014 | 09/09/2015 | 410 | 59 | 351 | 12/11/2013 | 12/23/2013 | 8 | 0 | 8 |  | 09/09/2015 | 410 | 59 | 351 |  |  | 0 | 0 | 0 | 8/25/2014 | 12/03/2013 | 9/30/2014 | Y | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 396973 | 01007 | 15.2 | Solar | 05_09_509L2 | 01/03/2022 | 01/04/2022 | 1 | 0 | 1 | 01/05/2022 | 01/05/2022 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2022 |  | 3/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | Y
National Grid | BELLINGHAM | 533315 | 02019 | 15.2 | Solar | 05_05_335W1 | 06/30/2023 | 07/03/2023 | 1 | 0 | 1 | 07/05/2023 | 07/05/2023 | 35 | 21 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2023 |  | 9/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2023 | Connected |  | N
National Grid | ATHOL | 191051 | 01331 | 1860 | Solar | 05_09_705W3 | 09/25/2018 | 11/26/2018 | 107 | 0 | 107 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 12/21/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 174272 | 01581 | 1820 | Solar | 05_05_312W4 | 11/01/2011 | 11/01/2011 | 61 | 0 | 61 |  |  | 0 | 0 | 0 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 | 02/13/2012 | 04/11/2012 | 40 | 0 | 40 |  | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2013 | 11/01/2011 | 1/16/2012 | Y | STD | 49 | 10/24/2013 | 12/12/2013 | 33 | 0 | 33 | 2/12/2014 | 2/12/2014 | 4/1/2014 | Connected |  | N
National Grid | RANDOLPH | 646034 | 02368 | 10 | Solar | 05_07_5W3 | 10/10/2024 | 11/04/2024 | 10 | 6 | 4 | 11/05/2024 | 11/05/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 10/10/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2025 | Connected |  | N
National Grid | SEEKONK | 404929 | 02771 | 6 | Solar | 05_05_7L1 | 01/06/2022 | 04/07/2022 | 62 | 61 | 1 | 04/08/2022 | 04/08/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2022 | 01/06/2022 | 7/30/2023 | Y | EXP | 365 | 06/11/2022 | 07/18/2022 | 38 | 0 | 38 |  |  | 8/12/2022 | Connected |  | Y
National Grid | LYNN | 729408 | 01905 | 10 | Solar | 05_12_21J34 | 10/27/2025 | 10/28/2025 | 1 | 0 | 1 | 11/13/2025 | 11/13/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2025 | 10/27/2025 | 12/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STOCKBRIDGE | 394117 | 01262 | 9.765 | Solar | 05_09_1103W1 | 12/10/2021 | 01/04/2022 | 17 | 16 | 1 | 01/05/2022 | 01/05/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 |  | 1/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2022 | Connected |  | N
National Grid | HANOVER | 497568 | 02339 | 17.28 | Solar | 05_07_95W3 | 02/14/2023 | 03/03/2023 | 12 | 10 | 2 | 03/06/2023 | 03/06/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176095 | 02324 | 750 | Wind | 05_07_912W55 | 04/03/2015 | 04/03/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/13/2015 | 05/11/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 07/30/2015 | 01/15/2016 | 115 | 0 | 115 | 3/31/2016 | 04/03/2015 | 10/30/2020 | Y | STD | 1322 | 12/14/2016 | 05/17/2018 | 519 | 0 | 519 | 4/5/2018 | 4/5/2018 | 9/29/2020 | Connected |  | N
National Grid | BELCHERTOWN | 421394 | 01007 | 0 | Solar | 05_09_509L2 | 04/01/2022 | 04/04/2022 | 1 | 0 | 1 | 04/05/2022 | 04/05/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 550748 | 01756 | 3.8 | Solar | 05_05_335W1 | 08/29/2023 | 08/30/2023 | 1 | 0 | 1 | 08/31/2023 | 08/31/2023 | 41 | 16 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 | 08/29/2023 | 1/19/2025 | Y | EXP | 365 | 02/06/2024 | 02/09/2024 | 4 | 0 | 4 |  |  | 4/25/2024 | Connected |  | N
National Grid | ATHOL | 286855 | 01331 | 4990 | Solar | 05_09_705W3 | 07/17/2020 | 08/26/2020 | 28 | 23 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 10/08/2020 | 29 | 13 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 175780 | 01581 | 866 | Solar | 05_05_312W4 | 07/22/2015 | 07/22/2015 | 10 | 10 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/05/2015 | 08/28/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 01/05/2016 | 05/17/2016 | 91 | 10 | 81 | 6/3/2016 | 07/22/2015 | 7/27/2016 | Y | STD | 54 | 11/09/2016 | 01/25/2017 | 50 | 0 | 50 | 1/26/2017 | 1/26/2017 | 2/1/2017 | Connected |  | N
National Grid | RANDOLPH | 646615 | 02368 | 10 | Solar | 05_07_5W3 | 10/17/2024 | 12/09/2024 | 17 | 13 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 10/17/2024 | 1/30/2026 | Y | EXP | 365 | 05/10/2025 | 10/23/2025 | 167 | 0 | 167 |  |  | 11/17/2025 | Connected |  | N
National Grid | SEEKONK | 413667 | 02771 | 15.2 | Solar | 05_05_7L1 | 02/22/2022 | 02/24/2022 | 3 | 2 | 1 | 02/25/2022 | 02/25/2022 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2022 |  | 5/10/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2022 | Connected |  | N
National Grid | LYNN | 554220 | 01902 | 10 | Solar | 05_12_21J34 | 09/28/2023 | 10/05/2023 | 5 | 2 | 3 | 10/06/2023 | 10/06/2023 | 89 | 25 | 64 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 415312 | 01262 | 15.2 | Solar | 05_09_1103W1 | 03/03/2022 | 03/04/2022 | 1 | 0 | 1 | 03/07/2022 | 03/07/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2022 |  | 4/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2022 | Connected |  | N
National Grid | HANSON | 523276 | 02341 | 6.8 | Solar | 05_07_95W3 | 06/05/2023 | 06/06/2023 | 1 | 0 | 1 | 06/07/2023 | 06/07/2023 | 24 | 5 | 19 | 11/24/2023 | 01/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 01/02/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/14/2023 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2024 | Connected |  | N
National Grid | BRIDGEWATER | 176258 | 02324 | 10 | Solar | 05_07_912W55 | 09/03/2015 | 09/03/2015 | 3 | 3 | 0 | 09/11/2015 | 09/11/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 9/12/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/10/2015 | 12/10/2015 | Connected |  | N
National Grid | BELCHERTOWN | 428143 | 01007 | 10 | Solar | 05_09_509L2 | 05/20/2022 | 05/23/2022 | 1 | 0 | 1 | 05/24/2022 | 05/24/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2022 | 05/20/2022 | 10/12/2023 | Y | EXP | 365 | 09/21/2022 | 10/10/2022 | 20 | 0 | 20 |  |  | 11/14/2022 | Connected |  | Y
National Grid | MENDON | 573727 | 01756 | 15.2 | Solar | 05_05_335W1 | 11/28/2023 | 12/12/2023 | 10 | 9 | 1 | 12/13/2023 | 12/13/2023 | 38 | 16 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2024 |  | 2/15/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2024 | Connected |  | N
National Grid | ORANGE | 294566 | 01364 | 0 | Solar | 05_09_705W3 | 09/16/2020 | 10/05/2020 | 13 | 9 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2020 | 10/29/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 176096 | 01581 | 300 | Solar | 05_05_312W4 | 04/03/2015 | 04/03/2015 | 5 | 0 | 5 | 04/13/2015 | 04/13/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2015 |  | 2/7/2018 | N | EXP | 124 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 647936 | 02368 | 10 | Solar | 05_07_5W3 | 10/28/2024 | 11/18/2024 | 3 | 0 | 3 | 11/19/2024 | 11/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 10/28/2024 | 1/14/2026 | Y | EXP | 365 | 06/11/2025 | 10/29/2025 | 141 | 0 | 141 |  |  | 11/14/2025 | Connected |  | N
National Grid | SEEKONK | 418863 | 02771 | 10 | Solar | 05_05_7L1 | 04/28/2022 | 04/29/2022 | 1 | 0 | 1 | 05/02/2022 | 05/02/2022 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 648683 | 01902 | 5.76 | Solar | 05_12_21J34 | 11/06/2024 | 11/20/2024 | 5 | 1 | 4 | 11/21/2024 | 11/21/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2025 | Connected |  | Y
National Grid | LENOX | 515529 | 01240 | 22.8 | Solar | 05_09_1103W1 | 03/29/2023 | 03/31/2023 | 3 | 1 | 2 | 04/03/2023 | 04/03/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2023 |  | 5/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2023 | Connected |  | N
National Grid | PEMBROKE | 597316 | 02359 | 6 | Solar | 05_07_95W3 | 04/04/2024 | 04/22/2024 | 12 | 11 | 1 | 04/23/2024 | 04/23/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | BRIDGEWATER | 176309 | 02324 | 2000 | Solar | 05_07_912W55 | 02/20/2015 | 02/20/2015 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2015 | 04/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/20/2015 | 12/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 448581 | 01007 | 0 | Solar | 05_09_509L2 | 08/11/2022 | 08/29/2022 | 13 | 12 | 1 | 08/30/2022 | 08/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 579748 | 01756 | 10 | Solar | 05_05_335W1 | 02/15/2024 | 02/20/2024 | 2 | 0 | 2 | 02/21/2024 | 02/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 | 02/15/2024 | 5/18/2025 | Y | EXP | 365 | 06/14/2024 | 07/20/2024 | 37 | 0 | 37 |  |  | 9/6/2024 | Connected |  | N
National Grid | ATHOL | 403557 | 01331 | 43.2 | Solar | 05_09_705W3 | 12/28/2021 | 12/29/2021 | 1 | 0 | 1 | 12/30/2021 | 12/30/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2022 |  | 2/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2022 | Connected |  | N
National Grid | WESTBOROUGH | 176165 | 01581 | 850 | Solar | 05_05_312W4 | 04/17/2015 | 04/17/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/22/2015 | 05/07/2015 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 12/22/2015 | 05/11/2016 | 95 | 0 | 95 | 6/3/2016 | 04/17/2015 | 3/17/2017 | Y | STD | 287 | 10/13/2016 | 04/07/2017 | 120 | 0 | 120 | 4/26/2017 | 4/26/2017 | 4/26/2017 | Connected |  | N
National Grid | RANDOLPH | 654753 | 02368 | 5 | Solar | 05_07_5W3 | 11/20/2024 | 12/13/2024 | 10 | 9 | 1 | 12/16/2024 | 12/16/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 |  | 2/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2025 | Connected |  | N
National Grid | SEEKONK | 432931 | 02771 | 8.12 | Solar | 05_05_7L1 | 06/01/2022 | 06/06/2022 | 3 | 0 | 3 | 06/07/2022 | 06/07/2022 | 17 | 0 | 17 | 10/11/2022 | 10/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/31/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 10/31/2022 |  | 11/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | LYNN | 661760 | 01902 | 7.6 | Solar | 05_12_21J34 | 12/19/2024 | 01/22/2025 | 8 | 3 | 5 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 |  | 3/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 538076 | 01240 | 22.8 | Solar | 05_09_1103W1 | 06/30/2023 | 07/03/2023 | 2 | 1 | 1 | 07/05/2023 | 07/05/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2023 |  | 8/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2023 | Connected |  | N
National Grid | HANSON | 606471 | 02341 | 7.6 | Solar | 05_07_95W3 | 04/24/2024 | 07/05/2024 | 43 | 43 | 0 | 07/08/2024 | 07/08/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 04/24/2024 | 11/30/2025 | Y | EXP | 365 | 10/11/2024 | 10/31/2024 | 21 | 0 | 21 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 176308 | 02324 | 1000 | Solar | 05_07_912W55 | 02/20/2015 | 02/20/2015 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/06/2015 | 04/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/20/2015 | 12/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 472374 | 01007 | 3 | Solar | 05_09_509L2 | 01/12/2023 | 01/17/2023 | 2 | 0 | 2 | 01/18/2023 | 01/18/2023 | 77 | 59 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 590034 | 01756 | 10 | Solar | 05_05_335W1 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | ORANGE | 432618 | 01364 | 9.6 | Solar | 05_09_705W3 | 06/22/2022 | 06/24/2022 | 2 | 0 | 2 | 06/27/2022 | 06/27/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 | 06/22/2022 | 1/5/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 176494 | 01581 | 15.25 | Solar | 05_05_312W4 | 12/10/2015 | 12/10/2015 | 29 | 29 | 0 | 01/25/2016 | 01/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 12/15/2016 | N | EXP | 314 |  |  | 0 | 0 | 0 | 2/18/2016 | 2/18/2016 | 2/24/2016 | Connected |  | N
National Grid | RANDOLPH | 656937 | 02368 | 3.8 | Solar | 05_07_5W3 | 11/26/2024 | 12/19/2024 | 6 | 0 | 6 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | SEEKONK | 436671 | 02771 | 0 | Solar | 05_05_7L1 | 06/09/2022 | 06/10/2022 | 1 | 0 | 1 | 06/13/2022 | 06/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/1/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | LYNN | 285404 | 01902 | 7.6 | Solar | 05_12_21J37 | 04/20/2020 | 04/27/2020 | 4 | 4 | 0 | 04/28/2020 | 04/28/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 | 04/20/2020 | 4/26/2021 | Y | EXP | 365 | 12/10/2020 | 02/15/2021 | 67 | 0 | 67 |  |  | 2/22/2021 | Connected |  | N
National Grid | LEE | 612451 | 01240 | 0 | Battery Add-On | 05_09_1103W1 | 06/03/2024 | 06/20/2024 | 13 | 11 | 2 | 06/21/2024 | 06/21/2024 | 82 | 48 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANSON | 642934 | 02341 | 11.5 | Solar | 05_07_95W3 | 09/27/2024 | 10/18/2024 | 7 | 4 | 3 | 10/21/2024 | 10/21/2024 | 23 | 5 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 11/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176425 | 02324 | 1980 | Solar | 05_07_912W55 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 02/29/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2017 | 02/02/2016 | 6/27/2019 | Y | STD | 758 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 478367 | 01007 | 3 | Solar | 05_09_509L2 | 01/20/2023 | 01/23/2023 | 1 | 0 | 1 | 01/24/2023 | 01/24/2023 | 59 | 34 | 25 | 05/01/2023 | 05/31/2023 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  | 05/31/2023 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 5/8/2023 |  | 6/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | BELLINGHAM | 589409 | 02019 | 6 | Solar | 05_05_335W1 | 02/27/2024 | 03/04/2024 | 4 | 0 | 4 | 03/05/2024 | 03/05/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 |  | 11/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2024 | Connected |  | N
National Grid | ORANGE | 453993 | 01364 | 7.6 | Solar | 05_09_705W3 | 09/23/2022 | 09/28/2022 | 3 | 0 | 3 | 09/29/2022 | 09/29/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2022 | 09/23/2022 | 1/19/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/15/2023 | Connected |  | N
National Grid | WESTBOROUGH | 176745 | 01581 | 50.4 | Solar | 05_05_312W4 | 11/02/2015 | 11/02/2015 | 3 | 3 | 0 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 |  | 11/8/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 1/4/2017 | 1/4/2017 | 1/6/2017 | Connected |  | N
National Grid | RANDOLPH | 659867 | 02368 | 2.32 | Solar | 05_07_5W3 | 12/11/2024 | 01/03/2025 | 1 | 0 | 1 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 523179 | 02771 | 6 | Solar | 05_05_7L1 | 05/11/2023 | 05/12/2023 | 1 | 0 | 1 | 05/15/2023 | 05/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 301309 | 01902 | 7.6 | Solar | 05_12_21J37 | 08/13/2020 | 08/17/2020 | 1 | 0 | 1 | 08/18/2020 | 08/18/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2020 |  | 8/1/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 663427 | 01240 | 5.76 | Solar | 05_09_1103W1 | 01/02/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | PEMBROKE | 648548 | 02359 | 10 | Solar | 05_07_95W3 | 11/01/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176424 | 02324 | 1980 | Solar | 05_07_912W55 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 02/29/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2017 | 02/02/2016 | 6/27/2019 | Y | STD | 758 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 484294 | 01007 | 0 | Solar | 05_09_509L2 | 12/09/2022 | 12/15/2022 | 4 | 3 | 1 | 12/16/2022 | 12/16/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELLINGHAM | 592697 | 02019 | 6 | Solar | 05_05_335W1 | 02/28/2024 | 03/04/2024 | 3 | 0 | 3 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 02/28/2024 | 3/12/2025 | Y | EXP | 365 | 06/05/2024 | 06/04/2024 | 0 | 0 | 0 |  |  | 6/8/2024 | Connected |  | N
National Grid | ORANGE | 457131 | 01364 | 160 | Solar | 05_09_705W3 | 09/19/2022 | 10/03/2022 | 10 | 0 | 10 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2024 |  | 1/23/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WESTBOROUGH | 178005 | 01581 | 15.2 | Solar | 05_05_312W4 | 04/27/2017 | 04/27/2017 | 8 | 8 | 0 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2017 |  | 5/2/2018 | N | EXP | 358 |  |  | 0 | 0 | 0 | 8/24/2017 | 8/24/2017 | 8/29/2017 | Connected |  | N
National Grid | RANDOLPH | 664368 | 02368 | 6 | Solar | 05_07_5W3 | 01/08/2025 | 02/04/2025 | 4 | 0 | 4 | 02/05/2025 | 02/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | SEEKONK | 575382 | 02771 | 2.9 | Solar | 05_05_7L1 | 12/26/2023 | 01/03/2024 | 6 | 1 | 5 | 01/04/2024 | 01/04/2024 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | LYNN | 533852 | 01905 | 2.925 | Solar | 05_12_21J37 | 09/20/2023 | 11/16/2023 | 39 | 36 | 3 | 11/17/2023 | 11/17/2023 | 72 | 58 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 4/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2024 | Connected |  | N
National Grid | LENOX | 708681 | 01240 | 17.101 | Solar | 05_09_1103W1 | 08/01/2025 | 08/05/2025 | 2 | 0 | 2 | 08/06/2025 | 08/06/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | HANSON | 653647 | 02341 | 7.6 | Solar | 05_07_95W3 | 11/18/2024 | 12/17/2024 | 2 | 0 | 2 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 3/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176423 | 02324 | 4990 | Solar | 05_07_912W55 | 02/02/2016 | 02/02/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2016 | 02/29/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2017 | 02/02/2016 | 2/25/2022 | Y | STD | 1142 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 504231 | 01007 | 10 | Solar | 05_09_509L2 | 03/09/2023 | 03/10/2023 | 1 | 0 | 1 | 03/13/2023 | 03/13/2023 | 132 | 112 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2023 |  | 11/2/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 610127 | 02019 | 5.76 | Solar | 05_05_335W1 | 05/15/2024 | 05/23/2024 | 3 | 0 | 3 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 |  | 6/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2024 | Connected |  | N
National Grid | ERVING | 506021 | 01344 | 10 | Solar | 05_09_705W3 | 03/27/2023 | 03/28/2023 | 1 | 0 | 1 | 03/29/2023 | 03/29/2023 | 76 | 21 | 55 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 178334 | 01581 | 10 | Solar | 05_05_312W4 | 11/15/2017 | 11/15/2017 | 70 | 59 | 11 | 03/09/2018 | 03/09/2018 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2018 |  | 11/22/2018 | N | EXP | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 674330 | 02368 | 3.8 | Solar | 05_07_5W3 | 02/26/2025 | 04/01/2025 | 4 | 0 | 4 | 04/02/2025 | 04/02/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/28/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2025 | Connected |  | N
National Grid | SEEKONK | 596128 | 02771 | 7.6 | Solar | 05_05_7L1 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 597743 | 01905 | 7.6 | Solar | 05_12_21J37 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 717337 | 01240 | 15.2 | Solar | 05_09_1103W1 | 09/08/2025 | 09/16/2025 | 5 | 1 | 4 | 09/17/2025 | 09/17/2025 | 32 | 19 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 658119 | 02339 | 16.34 | Solar | 05_07_95W3 | 12/03/2024 | 12/11/2024 | 6 | 3 | 3 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/12/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176536 | 02324 | 10 | Solar | 05_07_912W55 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 | 02/09/2016 | 12/15/2017 | Y | EXP | 647 | 02/06/2017 | 02/15/2017 | 7 | 0 | 7 | 8/24/2017 | 8/24/2017 | 8/29/2017 | Connected |  | N
National Grid | BELCHERTOWN | 503874 | 01007 | 14.79 | Solar | 05_09_509L2 | 02/22/2023 | 03/29/2023 | 26 | 25 | 1 | 03/30/2023 | 03/30/2023 | 46 | 29 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  | 6/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2023 | Connected |  | N
National Grid | BELLINGHAM | 624136 | 02019 | 0 | Solar | 05_05_335W1 | 07/11/2024 | 08/01/2024 | 14 | 12 | 2 | 08/02/2024 | 08/02/2024 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2024 | Connected |  | N
National Grid | ORANGE | 528322 | 01364 | 15.08 | Solar | 05_09_705W3 | 06/07/2023 | 06/08/2023 | 1 | 0 | 1 | 06/09/2023 | 06/09/2023 | 178 | 25 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 178679 | 01568 | 15.2 | Solar | 05_05_312W4 | 04/11/2018 | 04/11/2018 | 16 | 0 | 16 | 05/21/2018 | 05/21/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2018 |  | 4/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 11/15/2019 | Connected |  | N
National Grid | RANDOLPH | 675412 | 02368 | 3.8 | Solar | 05_07_5W3 | 03/04/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 59 | 36 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2025 | Connected |  | N
National Grid | SEEKONK | 630256 | 02771 | 7.6 | Solar | 05_05_7L1 | 08/05/2024 | 08/23/2024 | 2 | 0 | 2 | 08/26/2024 | 08/26/2024 | 46 | 27 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/7/2024 | 08/05/2024 | 11/18/2025 | Y | EXP | 365 | 01/15/2025 | 03/13/2025 | 58 | 0 | 58 |  |  | 3/20/2025 | Connected |  | N
National Grid | LYNN | 607086 | 01905 | 3.8 | Solar | 05_12_21J37 | 04/26/2024 | 06/06/2024 | 20 | 17 | 3 | 06/07/2024 | 06/07/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2024 |  | 7/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 710505 | 01240 | 80 | Solar | 05_09_1103W2 | 08/08/2025 | 09/03/2025 | 17 | 8 | 9 | 09/04/2025 | 09/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PEMBROKE | 478187 | 02359 | 120 | Solar | 05_07_95W4 | 12/14/2022 | 03/31/2023 | 72 | 62 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BRIDGEWATER | 177894 | 02324 | 1950 | Solar | 05_07_912W55 | 04/14/2017 | 04/14/2017 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/02/2017 | 05/25/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 515884 | 01082 | 15 | Solar | 05_09_509L2 | 04/18/2023 | 04/20/2023 | 2 | 0 | 2 | 04/21/2023 | 04/21/2023 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  | 12/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELLINGHAM | 641990 | 02019 | 3.8 | Solar | 05_05_335W1 | 09/20/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/20/2024 | 12/4/2025 | Y | EXP | 365 | 12/19/2024 | 01/28/2025 | 41 | 0 | 41 |  |  | 3/6/2025 | Connected |  | N
National Grid | ORANGE | 529380 | 01364 | 7.6 | Solar | 05_09_705W3 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 190317 | 01568 | 3.8 | Solar | 05_05_312W4 | 07/10/2018 | 08/15/2018 | 9 | 2 | 7 | 08/16/2018 | 08/16/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 676051 | 02368 | 11.5 | Solar | 05_07_5W3 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 121 | 98 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 632025 | 02771 | 11.4 | Solar | 05_05_7L1 | 08/12/2024 | 08/15/2024 | 3 | 0 | 3 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | LYNN | 619488 | 01905 | 7.6 | Solar | 05_12_21J37 | 06/20/2024 | 07/01/2024 | 1 | 0 | 1 | 07/02/2024 | 07/02/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 710486 | 01266 | 80 | Solar | 05_09_1103W2 | 08/08/2025 | 09/03/2025 | 17 | 8 | 9 | 09/04/2025 | 09/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANOVER | 478163 | 02339 | 120 | Solar | 05_07_95W4 | 12/14/2022 | 03/31/2023 | 72 | 62 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | BRIDGEWATER | 203795 | 02324 | 7.6 | Solar | 05_07_912W55 | 01/16/2019 | 01/30/2019 | 8 | 0 | 8 | 01/31/2019 | 01/31/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2019 |  | 3/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2019 | Connected |  | N
National Grid | BELCHERTOWN | 518320 | 01007 | 10.73 | Solar | 05_09_509L2 | 04/11/2023 | 04/14/2023 | 3 | 1 | 2 | 04/18/2023 | 04/18/2023 | 32 | 10 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2023 |  | 6/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2023 | Connected |  | Y
National Grid | BELLINGHAM | 658626 | 02019 | 3.8 | Solar | 05_05_335W1 | 12/05/2024 | 01/14/2025 | 4 | 0 | 4 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 | 12/05/2024 | 3/10/2026 | Y | EXP | 365 | 04/15/2025 | 11/21/2025 | 221 | 0 | 221 |  |  | 12/1/2025 | Connected |  | N
National Grid | ORANGE | 546846 | 01364 | 1494 | Solar | 05_09_705W3 | 03/08/2024 | 05/03/2024 | 39 | 31 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/06/2024 | 05/09/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 194239 | 01581 | 15.2 | Solar | 05_05_312W4 | 08/22/2018 | 09/19/2018 | 19 | 19 | 0 | 09/20/2018 | 09/20/2018 | 248 | 0 | 248 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 680201 | 02368 | 7.6 | Solar | 05_07_5W3 | 03/24/2025 | 03/26/2025 | 2 | 0 | 2 | 03/27/2025 | 03/27/2025 | 40 | 22 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 | 03/24/2025 | 7/1/2026 | Y | EXP | 365 | 08/13/2025 | 02/13/2026 | 185 | 0 | 185 |  |  | 12/22/2025 | Connected |  | N
National Grid | SEEKONK | 634301 | 02771 | 3.8 | Solar | 05_05_7L1 | 08/21/2024 | 09/03/2024 | 2 | 0 | 2 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 | 08/21/2024 | 12/31/2025 | Y | EXP | 365 | 12/14/2024 | 01/14/2025 | 32 | 0 | 32 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 626781 | 01905 | 6.72 | Solar | 05_12_21J37 | 07/22/2024 | 08/12/2024 | 1 | 0 | 1 | 08/13/2024 | 08/13/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 718580 | 01240 | 200 | Solar | 05_09_1103W2 | 09/19/2025 | 11/25/2025 | 44 | 36 | 8 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | ROCKLAND | 689008 | 02370 | 20 | Solar | 05_07_95W4 | 06/02/2025 | 06/12/2025 | 8 | 4 | 4 | 06/13/2025 | 06/13/2025 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 216694 | 02324 | 0 | Solar | 05_07_912W55 | 04/02/2019 | 04/09/2019 | 4 | 0 | 4 | 04/10/2019 | 04/10/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2019 | Connected |  | N
National Grid | BELCHERTOWN | 557758 | 01007 | 10 | Solar | 05_09_509L2 | 09/25/2023 | 10/26/2023 | 23 | 20 | 3 | 10/27/2023 | 10/27/2023 | 67 | 46 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 |  | 3/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | BELLINGHAM | 659458 | 02019 | 3.8 | Solar | 05_05_335W1 | 12/09/2024 | 12/11/2024 | 2 | 0 | 2 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 569219 | 01364 | 10 | Solar | 05_09_705W3 | 05/29/2024 | 07/23/2024 | 36 | 36 | 0 | 07/23/2024 | 07/23/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2024 |  | 8/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | WESTBOROUGH | 207296 | 01581 | 15.2 | Solar | 05_05_312W4 | 01/28/2019 | 02/11/2019 | 9 | 0 | 9 | 02/12/2019 | 02/12/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 | 01/28/2019 | 9/23/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 686459 | 02368 | 5.76 | Solar | 05_07_5W3 | 04/21/2025 | 05/12/2025 | 3 | 0 | 3 | 05/13/2025 | 05/13/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/21/2025 | 6/9/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | SEEKONK | 642705 | 02771 | 10 | Solar | 05_05_7L1 | 09/25/2024 | 09/30/2024 | 2 | 0 | 2 | 02/26/2025 | 02/26/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2025 | Connected |  | N
National Grid | LYNN | 642163 | 01905 | 10 | Solar | 05_12_21J37 | 10/01/2024 | 11/12/2024 | 22 | 15 | 7 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 | 10/01/2024 | 3/7/2026 | Y | EXP | 365 | 07/09/2025 | 07/08/2025 | 0 | 0 | 0 |  |  | 12/13/2025 | Connected |  | N
National Grid | LENOX | 727109 | 01240 | 11.4 | Solar | 05_09_1103W2 | 10/16/2025 | 10/22/2025 | 4 | 0 | 4 | 11/04/2025 | 11/04/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 | 10/16/2025 | 12/5/2026 | Y | EXP | 365 | 01/28/2026 | 01/27/2026 | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ROCKLAND | 720878 | 02370 | 15.356 | Solar | 05_07_95W4 | 09/22/2025 | 09/29/2025 | 5 | 0 | 5 | 09/30/2025 | 09/30/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2025 |  | 1/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIDGEWATER | 244408 | 02324 | 4990 | Solar | 05_07_912W55 | 07/22/2019 | 08/26/2019 | 25 | 19 | 6 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 08/27/2019 | 10/02/2019 | 25 | 16 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARE | 528517 | 01082 | 2.32 | Solar | 05_09_509L2 | 07/10/2023 | 07/12/2023 | 3 | 1 | 2 | 07/13/2023 | 07/13/2023 | 89 | 73 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  | 6/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/24/2025 | Connected |  | N
National Grid | BELLINGHAM | 662880 | 02019 | 5.76 | Solar | 05_05_335W1 | 12/27/2024 | 01/13/2025 | 3 | 0 | 3 | 01/14/2025 | 01/14/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 | 12/27/2024 | 2/26/2026 | Y | EXP | 365 | 03/15/2025 | 05/20/2025 | 67 | 0 | 67 |  |  | 7/19/2025 | Connected |  | N
National Grid | ORANGE | 606463 | 01364 | 10 | Solar | 05_09_705W3 | 04/24/2024 | 05/02/2024 | 5 | 0 | 5 | 05/03/2024 | 05/03/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2024 | 04/24/2024 | 6/3/2025 | Y | EXP | 365 | 10/02/2024 | 01/10/2025 | 101 | 0 | 101 |  |  | 1/16/2025 | Connected |  | N
National Grid | WESTBOROUGH | 221730 | 01581 | 0 | Solar | 05_05_312W4 | 06/19/2019 | 06/26/2019 | 3 | 0 | 3 | 06/27/2019 | 06/27/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/19/2019 | 11/8/2020 | Y | EXP | 365 | 07/07/2020 | 10/10/2020 | 96 | 5 | 91 |  |  | 11/12/2020 | Connected |  | N
National Grid | RANDOLPH | 695663 | 02368 | 7.8 | Solar | 05_07_5W3 | 06/02/2025 | 06/16/2025 | 4 | 0 | 4 | 07/22/2025 | 07/22/2025 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 647211 | 02771 | 4.35 | Solar | 05_05_7L1 | 10/15/2024 | 10/16/2024 | 5 | 1 | 4 | 10/29/2024 | 10/29/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2024 | 10/15/2024 | 12/19/2025 | Y | EXP | 365 | 01/15/2025 | 02/11/2025 | 28 | 0 | 28 |  |  | 3/7/2025 | Connected |  | N
National Grid | LYNN | 647804 | 01905 | 5.76 | Solar | 05_12_21J37 | 10/28/2024 | 01/30/2025 | 53 | 50 | 3 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 7/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | LENOX | 727081 | 01240 | 11.4 | Solar | 05_09_1103W2 | 11/15/2025 | 11/25/2025 | 7 | 0 | 7 | 11/26/2025 | 11/26/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANOVER | 731449 | 02339 | 7.6 | Solar | 05_07_95W4 | 11/04/2025 | 11/05/2025 | 3 | 0 | 3 | 12/09/2025 | 12/09/2025 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2026 | 11/04/2025 | 2/5/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | BRIDGEWATER | 287863 | 02324 | 499.9 | Solar | 05_07_912W55 | 04/20/2020 | 05/07/2020 | 13 | 9 | 4 |  |  | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 04/20/2020 | 12/31/2024 | Y | STD | 571 | 02/11/2022 | 02/13/2025 | 1098 | 661 | 437 |  |  | 12/30/2024 | Connected |  | N
National Grid | BELCHERTOWN | 531295 | 01007 | 10 | Solar | 05_09_509L2 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 8/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/25/2023 | Connected |  | N
National Grid | BELLINGHAM | 666700 | 02019 | 7.6 | Solar | 05_05_335W1 | 01/20/2025 | 02/10/2025 | 3 | 0 | 3 | 02/11/2025 | 02/11/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/20/2025 | 3/19/2026 | Y | EXP | 365 | 11/19/2025 | 11/18/2025 | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | ORANGE | 622235 | 01364 | 7.6 | Solar | 05_09_705W3 | 07/02/2024 | 07/12/2024 | 3 | 1 | 2 | 07/15/2024 | 07/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 | 07/02/2024 | 8/14/2025 | Y | EXP | 365 | 10/03/2024 | 01/24/2025 | 114 | 0 | 114 |  |  | 5/20/2025 | Connected |  | N
National Grid | UPTON | 230666 | 01568 | 0 | Solar | 05_05_312W4 | 05/24/2019 | 06/18/2019 | 15 | 10 | 5 | 06/19/2019 | 06/19/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2019 |  | 7/19/2019 | N | EXP | 25 |  |  | 0 | 0 | 0 |  |  | 7/26/2019 | Connected |  | N
National Grid | RANDOLPH | 720806 | 02368 | 6.825 | Solar | 05_07_5W3 | 09/22/2025 | 10/08/2025 | 1 | 0 | 1 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 | 09/22/2025 | 11/4/2026 | Y | EXP | 365 | 12/23/2025 | 01/02/2026 | 11 | 0 | 11 |  |  | 1/6/2026 | Connected |  | N
National Grid | SEEKONK | 665746 | 02771 | 15.2 | Solar | 05_05_7L1 | 01/17/2025 | 01/27/2025 | 5 | 0 | 5 | 01/28/2025 | 01/28/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2025 |  | 4/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | LYNN | 748924 | 01905 | 5.76 | Solar | 05_12_22J1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LENOX | 754724 | 01240 | 173 | Solar | 05_09_1103W2 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | ROCKLAND | 176012 | 02370 | 6 | Solar | 05_07_95W4 | 01/23/2015 | 01/23/2015 | 6 | 2 | 4 | 02/03/2015 | 02/03/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 |  | 6/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 3/27/2015 | 3/27/2015 | 9/24/2015 | Connected |  | N
National Grid | BRIDGEWATER | 300578 | 02324 | 7.6 | Solar | 05_07_912W55 | 07/10/2020 | 07/15/2020 | 2 | 2 | 0 | 07/16/2020 | 07/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 8/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2021 | Connected |  | N
National Grid | BELCHERTOWN | 533647 | 01007 | 10 | Solar | 05_09_509L2 | 06/23/2023 | 06/27/2023 | 3 | 1 | 2 | 06/28/2023 | 06/28/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2023 | 06/23/2023 | 8/16/2024 | Y | EXP | 365 | 09/22/2023 | 10/11/2023 | 20 | 0 | 20 |  |  | 10/26/2023 | Connected |  | N
National Grid | BELLINGHAM | 675278 | 02019 | 7.6 | Solar | 05_05_335W1 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 147 | 124 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 | 03/05/2025 | 10/22/2026 | Y | EXP | 365 | 12/10/2025 | 01/21/2026 | 43 | 0 | 43 |  |  | 1/21/2026 | Connected |  | N
National Grid | ORANGE | 646287 | 01364 | 7.6 | Solar | 05_09_705W3 | 10/10/2024 | 10/18/2024 | 4 | 0 | 4 | 10/21/2024 | 10/21/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2024 | 10/10/2024 | 12/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | WESTBOROUGH | 271250 | 01581 | 400 | Solar | 05_05_312W4 | 01/24/2020 | 01/31/2020 | 5 | 1 | 4 |  |  | 34 | 32 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 | 01/24/2020 | 3/10/2022 | Y | STD | 48 | 08/05/2021 | 08/10/2021 | 6 | 0 | 6 |  |  | 3/7/2022 | Connected |  | N
National Grid | RANDOLPH | 726274 | 02368 | 5.76 | Solar | 05_07_5W3 | 10/14/2025 | 10/24/2025 | 7 | 2 | 5 | 10/27/2025 | 10/27/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2026 | Connected |  | N
National Grid | SEEKONK | 682969 | 02771 | 3.8 | Solar | 05_05_7L1 | 04/04/2025 | 04/24/2025 | 2 | 0 | 2 | 05/06/2025 | 05/06/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2025 | 04/04/2025 | 6/11/2026 | Y | EXP | 365 | 07/26/2025 | 08/20/2025 | 26 | 0 | 26 |  |  | 9/8/2025 | Connected |  | N
National Grid | LYNN | 375833 | 01905 | 8.7 | Solar | 05_12_22J1 | 09/13/2021 | 09/21/2021 | 7 | 6 | 1 | 09/22/2021 | 09/22/2021 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/24/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | LENOX | 174204 | 01240 | 750 | Solar | 05_09_1103W2 | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 176310 | 02339 | 10 | Solar | 05_07_95W4 | 02/23/2015 | 02/23/2015 | 6 | 0 | 6 | 03/04/2015 | 03/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2015 |  | 7/31/2015 | N | EXP | 148 |  |  | 0 | 0 | 0 | 9/1/2016 | 9/1/2016 | 9/7/2016 | Connected |  | N
National Grid | BRIDGEWATER | 318180 | 02324 | 9.28 | Solar | 05_07_912W55 | 10/08/2020 | 10/09/2020 | 0 | 0 | 0 | 10/13/2020 | 10/13/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/8/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 572116 | 01007 | 10 | Solar | 05_09_509L2 | 11/17/2023 | 11/21/2023 | 3 | 2 | 1 | 11/22/2023 | 11/22/2023 | 46 | 22 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/2/2024 | Connected |  | N
National Grid | BELLINGHAM | 685398 | 02019 | 7.6 | Solar | 05_05_335W1 | 04/15/2025 | 05/19/2025 | 8 | 3 | 5 | 05/20/2025 | 05/20/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2025 | 04/15/2025 | 6/11/2026 | Y | EXP | 365 | 06/25/2025 | 08/13/2025 | 50 | 0 | 50 |  |  | 8/15/2025 | Connected |  | N
National Grid | ORANGE | 648204 | 01364 | 3.8 | Solar | 05_09_705W3 | 10/30/2024 | 12/19/2024 | 10 | 5 | 5 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 286836 | 01568 | 15.2 | Solar | 05_05_312W4 | 04/07/2020 | 04/08/2020 | 0 | 0 | 0 | 04/09/2020 | 04/09/2020 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2020 |  | 4/7/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 707573 | 02368 | 5.76 | Solar | 05_07_5W4 | 07/25/2025 | 08/12/2025 | 1 | 0 | 1 | 08/21/2025 | 08/21/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2025 |  | 9/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SEEKONK | 684389 | 02771 | 5.76 | Solar | 05_05_7L1 | 04/18/2025 |  | 109 | 25 | 84 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 659858 | 02152 | 11.52 | Solar | 05_12_22J1 | 12/11/2024 | 01/06/2025 | 5 | 0 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 | 12/11/2024 | 3/21/2026 | Y | EXP | 365 | 06/04/2025 | 09/04/2025 | 93 | 0 | 93 |  |  | 9/8/2025 | Connected |  | N
National Grid | LENOX | 174203 | 01240 | 1000 | Solar | 05_09_1103W2 | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 176762 | 02370 | 5 | Solar | 05_07_95W4 | 02/24/2016 | 02/24/2016 | 2 | 2 | 0 | 02/29/2016 | 02/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2016 |  | 3/1/2017 | N | EXP | 364 |  |  | 0 | 0 | 0 | 7/27/2016 | 7/27/2016 | 8/1/2016 | Connected |  | N
National Grid | BRIDGEWATER | 348228 | 02324 | 15.2 | Solar | 05_07_912W55 | 03/23/2021 | 03/24/2021 | 0 | 0 | 0 | 03/25/2021 | 03/25/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2021 |  | 8/5/2022 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 580279 | 01007 | 5.04 | Solar | 05_09_509L2 | 12/28/2023 | 02/20/2024 | 35 | 33 | 2 | 02/21/2024 | 02/21/2024 | 64 | 60 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MENDON | 692702 | 01756 | 17.875 | Solar | 05_05_335W1 | 05/21/2025 | 05/23/2025 | 2 | 0 | 2 | 07/16/2025 | 07/16/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | WARWICK | 676362 | 01378 | 50 | Solar | 05_09_705W3 | 03/14/2025 | 03/26/2025 | 8 | 4 | 4 | 03/27/2025 | 03/27/2025 | 55 | 32 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/27/2025 | Connected |  | N
National Grid | WESTBOROUGH | 334005 | 01581 | 7.6 | Solar | 05_05_312W4 | 12/28/2020 | 01/07/2021 | 7 | 7 | 0 | 01/08/2021 | 01/08/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 |  | 5/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2021 | Connected |  | N
National Grid | RANDOLPH | 746646 | 02368 | 5.76 | Solar | 05_07_5W4 | 01/21/2026 | 01/28/2026 | 13 | 11 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SEEKONK | 685315 | 02771 | 7.6 | Solar | 05_05_7L1 | 04/22/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 671093 | 02152 | 6.72 | Solar | 05_12_22J2 | 02/10/2025 | 04/09/2025 | 10 | 6 | 4 | 04/10/2025 | 04/10/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | LENOX | 174201 | 01240 | 1000 | Solar | 05_09_1103W2 | 02/09/2012 | 02/09/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 177828 | 02370 | 280 | Solar | 05_07_95W4 | 08/04/2017 | 08/04/2017 | 7 | 7 | 0 | 08/15/2017 | 08/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2017 |  | 8/9/2018 | N | EXP | 338 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/27/2017 | Connected |  | N
National Grid | BRIDGEWATER | 366888 | 02324 | 15.2 | Solar | 05_07_912W55 | 06/30/2021 | 08/02/2021 | 23 | 21 | 2 | 08/03/2021 | 08/03/2021 | 16 | 2 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2021 | 06/30/2021 | 12/21/2022 | Y | EXP | 365 | 10/23/2021 | 12/17/2021 | 56 | 4 | 52 |  |  | 1/10/2023 | Connected |  | N
National Grid | BELCHERTOWN | 597730 | 01007 | 13.8 | Solar | 05_09_509L2 | 03/18/2024 | 03/20/2024 | 2 | 0 | 2 | 03/21/2024 | 03/21/2024 | 16 | 9 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 | 03/18/2024 | 4/17/2025 | Y | EXP | 365 | 05/11/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 5/21/2024 | Connected |  | N
National Grid | HOPEDALE | 718036 | 01747 | 6.84 | Solar | 05_05_335W1 | 09/10/2025 | 09/26/2025 | 11 | 10 | 1 | 09/29/2025 | 09/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/21/2026 | Connected |  | N
National Grid | ORANGE | 676809 | 01364 | 12.6 | Solar | 05_09_705W3 | 03/10/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/5/2025 | Connected |  | N
National Grid | UPTON | 449344 | 01568 | 3.8 | Solar | 05_05_312W4 | 08/04/2022 | 08/09/2022 | 3 | 0 | 3 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2022 |  | 9/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/14/2023 | Connected |  | N
National Grid | RANDOLPH | 177952 | 02368 | 10 | Solar | 05_07_5W4 | 08/24/2017 | 08/24/2017 | 10 | 10 | 0 | 09/08/2017 | 09/08/2017 | 137 | 0 | 137 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2017 |  | 8/29/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 704406 | 02771 | 480 | Solar | 05_05_7L2 | 09/24/2025 | 10/27/2025 | 22 | 15 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2025 | 11/17/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WINTHROP | 547547 | 02152 | 60 | Solar | 05_12_22J2 | 08/11/2023 | 11/27/2023 | 72 | 61 | 11 | 11/28/2023 | 11/28/2023 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  | 3/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 174262 | 01240 | 1250 | Solar | 05_09_1103W2 | 02/29/2012 | 02/29/2012 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2013 |  | 8/1/2012 | N | STD | 239 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ROCKLAND | 221137 | 02370 | 10 | Solar | 05_07_95W4 | 04/24/2019 | 05/06/2019 | 7 | 0 | 7 | 05/07/2019 | 05/07/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 04/24/2019 | 6/9/2020 | Y | EXP | 365 | 10/04/2019 | 10/14/2019 | 10 | 0 | 10 |  |  | 1/21/2020 | Connected |  | N
National Grid | BRIDGEWATER | 439899 | 02324 | 0 | Solar | 05_07_912W55 | 06/24/2022 | 06/30/2022 | 5 | 2 | 3 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/9/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | BELCHERTOWN | 628220 | 01007 | 7.6 | Solar | 05_09_509L2 | 07/30/2024 | 08/02/2024 | 3 | 0 | 3 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2024 | 07/30/2024 | 8/26/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2024 | Connected |  | N
National Grid | MENDON | 359562 | 01756 | 480 | Solar | 05_05_335W2 | 06/18/2021 | 07/07/2021 | 12 | 3 | 9 |  |  | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 06/18/2021 | 9/7/2026 | Y | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | WENDELL | 682591 | 01379 | 11.4 | Solar | 05_09_705W3 | 04/03/2025 | 05/14/2025 | 4 | 0 | 4 | 05/21/2025 | 05/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2025 | 04/03/2025 | 6/24/2026 | Y | EXP | 365 | 09/03/2025 | 09/02/2025 | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | WESTBOROUGH | 376567 | 01581 | 15.2 | Solar | 05_05_312W4 | 09/01/2021 | 01/24/2022 | 98 | 92 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2022 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/26/2022 | Connected |  | N
National Grid | RANDOLPH | 285394 | 02368 | 6 | Solar | 05_07_5W4 | 04/17/2020 | 05/06/2020 | 12 | 12 | 0 | 05/07/2020 | 05/07/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/17/2020 | 5/5/2021 | Y | EXP | 365 | 07/29/2020 | 09/18/2020 | 52 | 5 | 47 |  |  | 9/23/2020 | Connected |  | N
National Grid | SEEKONK | 703981 | 02771 | 150 | Solar | 05_05_7L2 | 07/10/2025 | 10/13/2025 | 63 | 53 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WINTHROP | 663028 | 02152 | 11.52 | Solar | 05_12_22J2 | 12/30/2024 | 01/06/2025 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | LENOX | 174951 | 01240 | 18.06 | Solar | 05_09_1103W2 | 09/27/2012 | 09/27/2012 | 7 | 1 | 6 | 10/10/2012 | 10/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2013 |  | 11/30/2012 | N | EXP | 47 |  |  | 0 | 0 | 0 | 3/25/2013 | 3/25/2013 | 4/22/2013 | Connected |  | N
National Grid | NORWELL | 348314 | 02061 | 366.6 | Solar | 05_07_95W4 | 05/14/2021 | 07/30/2021 | 53 | 40 | 13 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 441068 | 02324 | 13 | Solar | 05_07_912W55 | 08/05/2022 | 08/16/2022 | 8 | 7 | 1 | 08/17/2022 | 08/17/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2022 |  | 9/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2023 | Connected |  | N
National Grid | BELCHERTOWN | 639326 | 01007 | 7.6 | Solar | 05_09_509L2 | 09/13/2024 | 10/02/2024 | 3 | 1 | 2 | 10/03/2024 | 10/03/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/13/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | MENDON | 500304 | 01756 | 3000 | Solar | 05_05_335W2 | 10/05/2023 | 05/16/2024 | 152 | 143 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 05/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WARWICK | 692741 | 01378 | 11.5 | Solar | 05_09_705W3 | 05/22/2025 | 07/11/2025 | 33 | 31 | 2 | 07/14/2025 | 07/14/2025 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 394972 | 01581 | 7.6 | Solar | 05_05_312W4 | 02/11/2022 | 02/14/2022 | 1 | 0 | 1 | 02/15/2022 | 02/15/2022 | 102 | 90 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | RANDOLPH | 286931 | 02368 | 7.6 | Solar | 05_07_5W4 | 04/24/2020 | 04/29/2020 | 3 | 2 | 1 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 |  | 4/28/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 177822 | 02771 | 300 | Natural Gas | 05_05_7L2 | 06/06/2017 | 06/06/2017 | 6 | 0 | 6 | 06/15/2017 | 06/15/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2017 |  | 2/28/2018 | N | EXP | 233 |  |  | 0 | 0 | 0 | 2/26/2018 | 2/26/2018 | 12/29/2017 | Connected |  | N
National Grid | WINTHROP | 199488 | 02152 | 10 | Solar | 05_12_22J3 | 10/26/2018 | 11/27/2018 | 13 | 8 | 5 | 11/28/2018 | 11/28/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 | 10/26/2018 | 12/20/2019 | Y | EXP | 365 | 06/20/2019 | 07/29/2019 | 38 | 0 | 38 |  |  | 10/30/2019 | Connected |  | N
National Grid | LENOX | 175961 | 01240 | 606 | Solar | 05_09_1103W2 | 06/04/2015 | 06/04/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/05/2015 | 07/07/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2016 | 06/04/2015 | 12/7/2017 | Y | STD | 492 | 06/07/2017 | 11/30/2017 | 116 | 0 | 116 | 11/20/2017 | 11/20/2017 | 12/7/2017 | Connected |  | N
National Grid | ROCKLAND | 424551 | 02370 | 20 | Solar | 05_07_95W4 | 05/20/2022 | 06/21/2022 | 21 | 20 | 1 | 06/22/2022 | 06/22/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 9/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2022 | Connected |  | N
National Grid | BRIDGEWATER | 479062 | 02324 | 15.2 | Solar | 05_07_912W55 | 11/21/2022 | 11/28/2022 | 4 | 2 | 2 | 11/29/2022 | 11/29/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2023 |  | 1/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/4/2023 | Connected |  | N
National Grid | BELCHERTOWN | 641583 | 01007 | 11.5 | Solar | 05_09_509L2 | 09/20/2024 | 09/25/2024 | 4 | 2 | 2 | 09/26/2024 | 09/26/2024 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/20/2024 | 12/10/2025 | Y | EXP | 365 | 02/07/2025 | 02/06/2025 | 0 | 0 | 0 |  |  | 2/19/2025 | Connected |  | N
National Grid | MILFORD | 721649 | 01757 | 2.6 | Solar | 05_05_335W2 | 09/29/2025 | 10/10/2025 | 3 | 0 | 3 | 10/30/2025 | 10/30/2025 | 28 | 10 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WARWICK | 697621 | 01378 | 10 | Solar | 05_09_705W3 | 06/10/2025 | 06/24/2025 | 3 | 0 | 3 | 07/15/2025 | 07/15/2025 | 31 | 16 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2025 | 06/10/2025 | 10/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 393761 | 01581 | 15.2 | Solar | 05_05_312W4 | 11/05/2021 | 12/08/2021 | 2 | 0 | 2 | 11/10/2021 | 11/10/2021 | 60 | 26 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 320043 | 02368 | 9.8 | Solar | 05_07_5W4 | 12/23/2020 | 12/30/2020 | 3 | 0 | 3 | 12/31/2020 | 12/31/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 195174 | 02771 | 480 | Solar | 05_05_7L2 | 09/12/2018 | 09/25/2018 | 8 | 5 | 3 | 09/26/2018 | 09/26/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2018 |  | 6/30/2020 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 231769 | 02152 | 6 | Solar | 05_12_22J3 | 06/25/2019 | 07/02/2019 | 5 | 5 | 0 | 07/03/2019 | 07/03/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2019 | 06/25/2019 | 4/16/2020 | Y | EXP | 281 | 01/11/2020 | 01/23/2020 | 12 | 0 | 12 |  |  | 2/6/2020 | Connected |  | N
National Grid | LENOX | 176710 | 01240 | 38.4 | Solar | 05_09_1103W2 | 01/06/2016 | 01/06/2016 | 3 | 3 | 0 | 01/12/2016 | 01/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2016 |  | 1/12/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 8/25/2016 | 8/25/2016 | 9/14/2016 | Connected |  | N
National Grid | ROCKLAND | 503019 | 02370 | 16 | Solar | 05_07_95W4 | 03/17/2023 | 03/21/2023 | 2 | 0 | 2 | 03/22/2023 | 03/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2023 |  | 6/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2023 | Connected |  | N
National Grid | BRIDGEWATER | 497556 | 02324 | 15.66 | Solar | 05_07_912W55 | 02/14/2023 | 03/17/2023 | 22 | 20 | 2 | 03/20/2023 | 03/20/2023 | 29 | 8 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 |  | 5/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/2/2023 | Connected |  | N
National Grid | BELCHERTOWN | 645505 | 01007 | 5.76 | Solar | 05_09_509L2 | 10/17/2024 | 12/13/2024 | 5 | 0 | 5 | 12/16/2024 | 12/16/2024 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 10/17/2024 | 2/15/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | MILFORD | 177589 | 01757 | 7.6 | Solar | 05_05_335W2 | 05/18/2017 | 05/18/2017 | 11 | 11 | 0 | 06/06/2017 | 06/06/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 | 05/18/2017 | 5/24/2018 | Y | EXP | 35 | 08/29/2017 | 10/12/2017 | 30 | 0 | 30 | 11/8/2017 | 11/8/2017 | 11/28/2017 | Connected |  | N
National Grid | ORANGE | 699906 | 01364 | 34.2 | Solar | 05_09_705W3 | 06/23/2025 | 06/24/2025 | 1 | 0 | 1 | 06/25/2025 | 06/25/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 | 06/23/2025 | 8/6/2026 | Y | EXP | 365 | 10/04/2025 | 10/29/2025 | 26 | 0 | 26 |  |  | 12/20/2025 | Connected |  | N
National Grid | WESTBOROUGH | 423473 | 01581 | 15.2 | Solar | 05_05_312W4 | 04/12/2022 | 04/13/2022 | 1 | 0 | 1 | 04/14/2022 | 04/14/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 |  | 5/27/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 431236 | 02368 | 8.12 | Solar | 05_07_5W4 | 05/09/2023 | 05/12/2023 | 3 | 2 | 1 | 05/15/2023 | 05/15/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/09/2023 | 6/20/2024 | Y | EXP | 365 | 12/07/2023 | 12/12/2023 | 6 | 0 | 6 |  |  | 12/18/2023 | Connected |  | N
National Grid | SEEKONK | 348306 | 02771 | 499.9 | Solar | 05_05_7L2 | 05/14/2021 | 07/31/2021 | 53 | 40 | 13 |  |  | 29 | 3 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 659889 | 02152 | 5.76 | Solar | 05_12_22J4 | 12/11/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | N
National Grid | LENOX | 178073 | 01240 | 120.75 | Solar | 05_09_1103W2 | 11/02/2017 | 11/02/2017 | 8 | 8 | 0 | 11/17/2017 | 11/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2017 |  | 11/7/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 | 3/14/2018 | 3/14/2018 | 4/11/2018 | Connected |  | N
National Grid | HANOVER | 544647 | 02339 | 16 | Solar | 05_07_95W4 | 07/31/2023 | 08/07/2023 | 5 | 3 | 2 | 08/08/2023 | 08/08/2023 | 124 | 54 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 564081 | 02324 | 10 | Solar | 05_07_912W55 | 11/07/2023 | 11/09/2023 | 2 | 0 | 2 | 11/13/2023 | 11/13/2023 | 42 | 17 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2024 | 11/07/2023 | 2/12/2025 | Y | EXP | 365 | 05/16/2024 | 07/12/2024 | 58 | 0 | 58 |  |  | 7/22/2024 | Connected |  | N
National Grid | BELCHERTOWN | 659013 | 01007 | 10 | Solar | 05_09_509L2 | 12/06/2024 | 12/16/2024 | 7 | 4 | 3 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | MILFORD | 241367 | 01757 | 10 | Solar | 05_05_335W2 | 07/08/2019 | 07/17/2019 | 7 | 7 | 0 | 07/18/2019 | 07/18/2019 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2019 | 07/08/2019 | 3/17/2020 | Y | EXP | 23 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 705558 | 01364 | 7.6 | Solar | 05_09_705W3 | 07/17/2025 | 09/15/2025 | 40 | 24 | 16 | 09/16/2025 | 09/16/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 436643 | 01581 | 15.2 | Solar | 05_05_312W4 | 06/09/2022 | 06/13/2022 | 2 | 0 | 2 | 06/14/2022 | 06/14/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/6/2022 | Connected |  | N
National Grid | RANDOLPH | 442826 | 02368 | 8.12 | Solar | 05_07_5W4 | 08/09/2022 | 08/11/2022 | 2 | 0 | 2 | 08/12/2022 | 08/12/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2022 |  | 9/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 389716 | 02771 | 0 | Other | 05_05_7L2 | 11/09/2021 | 01/26/2022 | 52 | 43 | 9 |  |  | 43 | 26 | 17 |  |  | 0 | 0 | 0 | 01/27/2022 | 02/25/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 692020 | 02152 | 10 | Solar | 05_12_22J5 | 05/19/2025 | 05/29/2025 | 8 | 5 | 3 | 07/14/2025 | 07/14/2025 | 43 | 30 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 | 05/19/2025 | 9/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LENOX | 320117 | 01240 | 133.3 | Solar | 05_09_1103W2 | 10/19/2020 | 10/27/2020 | 5 | 0 | 5 | 10/28/2020 | 10/28/2020 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  | 1/31/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N
National Grid | HANOVER | 602975 | 02339 | 7.6 | Solar | 05_07_95W4 | 04/10/2024 | 04/23/2024 | 2 | 0 | 2 | 04/24/2024 | 04/24/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 |  | 5/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/11/2025 | Connected |  | N
National Grid | BRIDGEWATER | 613123 | 02324 | 7.6 | Solar | 05_07_912W55 | 05/23/2024 | 06/03/2024 | 3 | 0 | 3 | 06/04/2024 | 06/04/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2024 | Connected |  | N
National Grid | BELCHERTOWN | 668664 | 01007 | 15.2 | Solar | 05_09_509L2 | 02/04/2025 | 02/11/2025 | 6 | 2 | 4 | 02/12/2025 | 02/12/2025 | 27 | 5 | 22 | 03/28/2025 | 04/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 04/15/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 4/22/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 526856 | 01757 | 10 | Solar | 05_05_335W2 | 06/01/2023 | 06/05/2023 | 2 | 0 | 2 | 06/06/2023 | 06/06/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARWICK | 741470 | 01378 | 15.2 | Solar | 05_09_705W3 | 01/05/2026 | 01/07/2026 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 470820 | 01581 | 15.2 | Solar | 05_05_312W4 | 10/24/2022 | 10/25/2022 | 1 | 0 | 1 | 10/26/2022 | 10/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 10/24/2022 | 12/19/2023 | Y | EXP | 365 | 02/15/2023 | 04/27/2023 | 72 | 0 | 72 |  |  | 6/22/2023 | Connected |  | N
National Grid | RANDOLPH | 459057 | 02368 | 6 | Solar | 05_07_5W4 | 09/21/2022 | 09/23/2022 | 2 | 0 | 2 | 09/26/2022 | 09/26/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2022 | 09/21/2022 | 10/2/2024 | Y | EXP | 365 | 06/01/2023 | 09/08/2023 | 100 | 0 | 100 |  |  | 10/20/2023 | Connected |  | N
National Grid | SEEKONK | 432969 | 02771 | 0 | Battery Add-On | 05_05_7L2 | 06/28/2022 | 07/12/2022 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2022 | 08/08/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WINTHROP | 668411 | 02152 | 11.2 | Solar | 05_12_22J5 | 01/28/2025 | 02/11/2025 | 3 | 0 | 3 | 02/12/2025 | 02/12/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 | 01/28/2025 | 4/15/2026 | Y | EXP | 365 | 06/11/2025 | 11/24/2025 | 167 | 0 | 167 |  |  | 11/25/2025 | Connected |  | N
National Grid | LENOX | 509170 | 01240 | 0 | Other | 05_09_1103W2 | 04/21/2023 | 05/11/2023 | 14 | 4 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2023 | 06/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 676721 | 02339 | 7.6 | Solar | 05_07_95W4 | 03/10/2025 | 03/22/2025 | 3 | 0 | 3 | 04/15/2025 | 04/15/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/10/2025 | 6/2/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2025 | Connected |  | N
National Grid | BRIDGEWATER | 706528 | 02324 | 50 | Solar | 05_07_912W55 | 07/29/2025 | 08/20/2025 | 15 | 5 | 10 | 08/21/2025 | 08/21/2025 | 46 | 24 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 672380 | 01007 | 7.6 | Solar | 05_09_509L2 | 02/17/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 27 | 9 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2025 | Connected |  | N
National Grid | MILFORD | 563998 | 01757 | 6.912 | Solar | 05_05_335W2 | 11/06/2023 | 11/13/2023 | 4 | 2 | 2 | 11/14/2023 | 11/14/2023 | 128 | 66 | 62 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ORANGE | 426180 | 01364 | 580 | Solar | 05_09_901W1 | 06/27/2022 | 08/10/2022 | 31 | 23 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/11/2022 | 09/08/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 2/24/2027 | N | STD | 75 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | WESTBOROUGH | 479590 | 01581 | 7.6 | Solar | 05_05_312W4 | 01/05/2023 | 01/10/2023 | 3 | 0 | 3 | 01/11/2023 | 01/11/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 |  | 4/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2023 | Connected |  | N
National Grid | RANDOLPH | 518780 | 02368 | 7.54 | Solar | 05_07_5W4 | 04/24/2023 | 04/26/2023 | 2 | 0 | 2 | 04/27/2023 | 04/27/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 489659 | 02771 | 499.9 | Solar | 05_05_7L2 | 01/31/2023 |  | 116 | 70 | 46 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REVERE | 682616 | 02151 | 5.76 | Solar | 05_12_22J5 | 04/04/2025 | 04/22/2025 | 4 | 0 | 4 | 05/01/2025 | 05/01/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 6/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | LENOX | 593413 | 01240 | 100 | Solar | 05_09_1103W2 | 03/04/2024 | 03/15/2024 | 9 | 0 | 9 | 03/18/2024 | 03/18/2024 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2024 | 03/04/2024 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N
National Grid | ROCKLAND | 723938 | 02370 | 11.4 | Solar | 05_07_95W5 | 10/07/2025 | 10/13/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2025 | 10/07/2025 | 1/12/2027 | Y | EXP | 365 | 02/06/2026 |  | 29 | 0 | 29 |  |  |  | Construction |  | N
National Grid | BRIDGEWATER | 709918 | 02324 | 20 | Solar | 05_07_912W55 | 08/07/2025 | 08/12/2025 | 3 | 0 | 3 | 08/13/2025 | 08/13/2025 | 53 | 25 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 672928 | 01007 | 11.78 | Solar | 05_09_509L2 | 02/19/2025 | 03/17/2025 | 5 | 0 | 5 | 03/18/2025 | 03/18/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 556107 | 01757 | 3.84 | Solar | 05_05_335W2 | 09/22/2023 | 09/25/2023 | 1 | 0 | 1 | 09/26/2023 | 09/26/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 | 09/22/2023 | 11/22/2024 | Y | EXP | 365 | 03/05/2024 | 04/30/2024 | 57 | 0 | 57 |  |  | 5/1/2024 | Connected |  | N
National Grid | ORANGE | 733098 | 01364 | 17.26 | Solar | 05_09_901W1 | 11/17/2025 | 11/18/2025 | 1 | 0 | 1 | 11/19/2025 | 11/19/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 479439 | 01581 | 11.4 | Solar | 05_05_312W4 | 03/29/2023 | 12/07/2022 | 2 | 0 | 2 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2022 |  | 5/11/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | RANDOLPH | 547826 | 02368 | 3 | Solar | 05_07_5W4 | 08/15/2023 | 08/22/2023 | 6 | 5 | 1 | 08/23/2023 | 08/23/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 530753 | 02771 | 80 | Solar | 05_05_7L3 | 06/14/2023 | 03/29/2024 | 197 | 188 | 9 |  |  | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | Y
National Grid | WINTHROP | 177408 | 02152 | 184 | Solar | 05_12_22J7 | 09/09/2016 | 09/09/2016 | 16 | 16 | 0 | 11/09/2016 | 11/09/2016 | 174 | 174 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2017 |  | 11/30/2018 | N | EXP | 529 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 680664 | 01240 | 11.5 | Solar | 05_09_1103W2 | 03/26/2025 | 04/17/2025 | 15 | 12 | 3 | 04/18/2025 | 04/18/2025 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2025 | Connected |  | N
National Grid | ROCKLAND | 174826 | 02370 | 30 | Solar | 05_07_95W5 | 08/22/2011 | 08/22/2011 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2011 |  | 2/10/2012 | N | EXP | 81 |  |  | 0 | 0 | 0 | 8/8/2012 | 8/8/2012 | 2/10/2012 | Connected |  | N
National Grid | BRIDGEWATER | 316462 | 02324 | 250 | Solar | 05_07_912W73 | 10/02/2020 | 10/19/2020 | 10 | 0 | 10 |  |  | 349 | 314 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 | 10/02/2020 | 3/14/2026 | Y | STD | 91 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BELCHERTOWN | 673360 | 01007 | 20 | Solar | 05_09_509L2 | 03/04/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 03/04/2025 | 5/11/2026 | Y | EXP | 365 | 08/23/2025 | 08/22/2025 | 0 | 0 | 0 |  |  | 11/11/2025 | Connected |  | N
National Grid | MILFORD | 601386 | 01757 | 14.175 | Solar | 05_05_335W2 | 04/15/2024 | 04/17/2024 | 2 | 1 | 1 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2024 | 04/15/2024 | 5/6/2025 | Y | EXP | 365 | 05/18/2024 | 06/26/2024 | 40 | 0 | 40 |  |  | 7/4/2024 | Connected |  | N
National Grid | NORTHAMPTON | 174170 | 01060 | 50 | Natural Gas | 05_09_901W1 | 03/14/2012 | 03/14/2012 | 126 | 0 | 126 | 09/18/2012 | 09/18/2012 | 360 | 0 | 360 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2013 |  | 11/30/2012 | N | EXP | 82 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 489567 | 01581 | 15.2 | Solar | 05_05_312W4 | 01/04/2023 | 01/06/2023 | 3 | 2 | 1 | 01/09/2023 | 01/09/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2023 |  | 2/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2023 | Connected |  | N
National Grid | RANDOLPH | 550147 | 02368 | 5 | Solar | 05_07_5W4 | 08/24/2023 | 08/28/2023 | 3 | 1 | 2 | 08/29/2023 | 08/29/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2023 |  | 12/31/2024 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 676975 | 02771 | 750 | Solar | 05_05_7L3 | 04/08/2025 | 06/27/2025 | 55 | 45 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/30/2025 | 07/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WINTHROP | 204747 | 02152 | 168 | Solar | 05_12_22J7 | 12/27/2018 | 12/28/2018 | 0 | 0 | 0 | 12/31/2018 | 12/31/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2019 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2020 | Connected |  | N
National Grid | LENOX | 724819 | 01240 | 20 | Solar | 05_09_1108W1 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANOVER | 175327 | 02339 | 419 | Solar | 05_07_95W5 | 11/10/2014 | 11/10/2014 | 5 | 2 | 3 | 11/19/2014 | 11/19/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2015 | 11/10/2014 | 4/15/2016 | Y | EXP | 457 | 01/30/2017 | 03/22/2017 | 36 | 0 | 36 | 2/4/2015 | 2/4/2015 | 3/30/2017 | Connected |  | N
National Grid | BRIDGEWATER | 489538 | 02324 | 80 | Solar | 05_07_912W73 | 01/06/2023 | 03/16/2023 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 06/13/2023 | 61 | 46 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BELCHERTOWN | 688577 | 01007 | 20.8 | Solar | 05_09_509L2 | 05/12/2025 | 05/20/2025 | 5 | 1 | 4 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/12/2025 | Connected |  | N
National Grid | MILFORD | 640572 | 01757 | 5.76 | Solar | 05_05_335W2 | 09/16/2024 | 09/27/2024 | 1 | 0 | 1 | 09/30/2024 | 09/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 174352 | 01060 | 17 | Solar | 05_09_901W1 | 05/09/2012 | 05/09/2012 | 7 | 0 | 7 | 05/22/2012 | 05/22/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2012 |  | 7/31/2012 | N | EXP | 44 |  |  | 0 | 0 | 0 | 8/30/2012 | 8/30/2012 | 10/11/2012 | Connected |  | N
National Grid | WESTBOROUGH | 501896 | 01581 | 13.975 | Solar | 05_05_312W4 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2023 |  | 4/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/22/2023 | Connected |  | N
National Grid | RANDOLPH | 581941 | 02368 | 8.12 | Solar | 05_07_5W4 | 02/01/2024 | 03/14/2024 | 26 | 25 | 1 | 03/15/2024 | 03/15/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 |  | 3/22/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2024 | Connected |  | N
National Grid | SEEKONK | 690541 | 02771 | 100 | Solar | 05_05_7L3 | 06/10/2025 | 02/18/2026 | 171 | 159 | 12 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WINTHROP | 312766 | 02152 | 3.8 | Solar | 05_12_22J7 | 09/24/2020 | 09/28/2020 | 1 | 0 | 1 | 09/29/2020 | 09/29/2020 | 37 | 20 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LENOX | 730613 | 01240 | 15.68 | Solar | 05_09_1108W1 | 11/03/2025 | 11/19/2025 | 10 | 6 | 4 | 11/20/2025 | 11/20/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HANOVER | 184689 | 02339 | 990 | Solar | 05_07_95W5 | 05/16/2018 | 05/16/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/26/2018 | 08/13/2018 | 34 | 15 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 715590 | 02324 | 0 | Other | 05_07_912W73 | 02/06/2026 |  | 18 | 8 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BELCHERTOWN | 707273 | 01007 | 7.6 | Solar | 05_09_509L2 | 07/24/2025 | 09/25/2025 | 2 | 0 | 2 | 09/26/2025 | 09/26/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 647352 | 01757 | 7.6 | Solar | 05_05_335W2 | 10/17/2024 | 11/07/2024 | 15 | 13 | 2 | 11/08/2024 | 11/08/2024 | 43 | 19 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2025 | 10/17/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | NORTHAMPTON | 174484 | 01060 | 250 | Solar | 05_09_901W1 | 01/25/2011 | 01/25/2011 | 21 | 0 | 21 | 02/24/2011 | 02/24/2011 | 720 | 0 | 720 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2011 |  | 7/29/2012 | N | EXP | 319 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 544251 | 01581 | 14.805 | Solar | 05_05_312W4 | 08/21/2023 | 09/14/2023 | 17 | 13 | 4 | 09/15/2023 | 09/15/2023 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2023 |  | 10/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | RANDOLPH | 589709 | 02368 | 6.96 | Solar | 05_07_5W4 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 28 | 25 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 174699 | 02771 | 60 | Natural Gas | 05_05_7L3 | 01/04/2013 | 01/04/2013 | 13 | 13 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 574519 | 02152 | 7.6 | Solar | 05_12_22J7 | 12/04/2023 | 01/22/2024 | 32 | 25 | 7 | 01/23/2024 | 01/23/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 | 12/04/2023 | 3/15/2025 | Y | EXP | 365 | 07/17/2024 | 07/16/2024 | 0 | 0 | 0 |  |  | 8/30/2024 | Connected |  | N
National Grid | SHEFFIELD | 745628 | 01257 | 0 | Solar | 05_09_1108W1 | 01/16/2026 | 01/21/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORWELL | 287429 | 02061 | 11.4 | Solar | 05_07_95W5 | 04/10/2020 | 04/29/2020 | 11 | 11 | 0 | 04/30/2020 | 04/30/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2020 | 04/10/2020 | 8/10/2021 | Y | EXP | 365 | 08/27/2020 | 09/12/2020 | 16 | 0 | 16 |  |  | 7/13/2021 | Connected |  | N
National Grid | BRIDGEWATER | 748384 | 02324 | 13.8 | Solar | 05_07_912W73 | 01/30/2026 | 02/04/2026 | 3 | 0 | 3 | 02/05/2026 | 02/05/2026 | 20 | 9 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | BELCHERTOWN | 706631 | 01007 | 5.76 | Solar | 05_09_509L2 | 07/22/2025 | 08/19/2025 | 19 | 15 | 4 | 08/20/2025 | 08/20/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2025 | Connected |  | N
National Grid | MILFORD | 668261 | 01757 | 11.5 | Solar | 05_05_335W2 | 02/04/2025 | 02/07/2025 | 3 | 0 | 3 | 02/10/2025 | 02/10/2025 | 48 | 29 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | NORTHAMPTON | 174953 | 01060 | 250 | Solar | 05_09_901W1 | 09/28/2012 | 09/28/2012 | 6 | 0 | 6 | 10/10/2012 | 10/10/2012 | 0 | 0 | 0 | 02/08/2013 | 03/14/2013 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 03/14/2013 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 3/19/2013 | 09/28/2012 | 12/31/2012 | Y | EXP | 78 |  |  | 0 | 0 | 0 | 8/15/2013 | 8/15/2013 | 9/6/2013 | Connected |  | N
National Grid | WESTBOROUGH | 546560 | 01581 | 0 | Solar | 05_05_312W4 | 08/07/2023 | 08/08/2023 | 1 | 0 | 1 | 08/09/2023 | 08/09/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 12/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/1/2024 | Connected |  | N
National Grid | RANDOLPH | 606804 | 02368 | 3.8 | Solar | 05_07_5W4 | 04/25/2024 | 04/29/2024 | 1 | 0 | 1 | 04/30/2024 | 04/30/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2024 | 04/25/2024 | 5/14/2025 | Y | EXP | 365 | 06/13/2024 | 07/19/2024 | 37 | 0 | 37 |  |  | 7/29/2024 | Connected |  | N
National Grid | SEEKONK | 174775 | 02771 | 60 | Natural Gas | 05_05_7L3 | 01/22/2013 | 01/22/2013 | 16 | 13 | 3 | 02/20/2013 | 02/20/2013 | 379 | 0 | 379 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2013 |  | 6/28/2013 | N | EXP | 94 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 657610 | 02152 | 3.8 | Solar | 05_12_22J7 | 11/29/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | SHEFFIELD | 176670 | 01257 | 875 | Solar | 05_09_1108W1 | 10/22/2015 | 10/22/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 11/23/2015 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 04/27/2017 | 09/18/2017 | 99 | 0 | 99 |  |  | 10/27/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 303247 | 02061 | 112.5 | Solar | 05_07_95W5 | 07/28/2020 | 08/12/2020 | 10 | 0 | 10 | 08/13/2020 | 08/13/2020 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 4/20/2025 | N | EXP | 85 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 175352 | 02324 | 499 | Solar | 05_07_912W73 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 712304 | 01007 | 11.5 | Solar | 05_09_509L2 | 08/27/2025 | 09/04/2025 | 5 | 0 | 5 | 09/05/2025 | 09/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | MILFORD | 689317 | 01757 | 10 | Solar | 05_05_335W2 | 05/27/2025 | 06/03/2025 | 4 | 1 | 3 | 06/04/2025 | 06/04/2025 | 33 | 20 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 175972 | 01060 | 176 | Solar | 05_09_901W1 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 | 08/13/2015 | 08/13/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2015 | 08/13/2015 | 8/18/2016 | Y | EXP | 342 | 06/03/2016 | 12/08/2016 | 128 | 0 | 128 | 12/14/2016 | 12/14/2016 | 12/20/2016 | Connected |  | N
National Grid | WESTBOROUGH | 573934 | 01581 | 15.2 | Solar | 05_05_312W4 | 11/28/2023 | 12/13/2023 | 11 | 8 | 3 | 12/14/2023 | 12/14/2023 | 28 | 6 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2024 |  | 5/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/30/2024 | Connected |  | N
National Grid | RANDOLPH | 621041 | 02368 | 7.6 | Solar | 05_07_5W4 | 06/27/2024 | 07/10/2024 | 3 | 0 | 3 | 07/11/2024 | 07/11/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2024 | 06/27/2024 | 8/19/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2024 | Connected |  | N
National Grid | SEEKONK | 174774 | 02771 | 60 | Natural Gas | 05_05_7L3 | 01/22/2013 | 01/22/2013 | 16 | 13 | 3 | 02/20/2013 | 02/20/2013 | 379 | 0 | 379 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2013 |  | 6/28/2013 | N | EXP | 94 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 669460 | 02152 | 3.8 | Solar | 05_12_22J7 | 02/03/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 | 02/03/2025 | 4/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | SHEFFIELD | 188497 | 01257 | 3652 | Solar | 05_09_1108W1 | 06/29/2018 | 06/29/2018 | 22 | 14 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2018 | 09/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 303246 | 02339 | 62.5 | Solar | 05_07_95W5 | 07/28/2020 | 08/12/2020 | 10 | 0 | 10 | 08/13/2020 | 08/13/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2020 |  | 2/17/2025 | N | EXP | 75 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176932 | 02324 | 960 | Solar | 05_07_912W73 | 01/28/2016 | 01/28/2016 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/16/2016 | 03/15/2016 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2017 | 01/28/2016 | 2/14/2025 | Y | STD | 138 | 11/10/2020 | 11/09/2020 | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | BELCHERTOWN | 680003 | 01007 | 4980 | Solar | 05_09_514L1 | 05/06/2025 | 06/03/2025 | 19 | 9 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/04/2025 | 07/02/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 723275 | 01757 | 11.6 | Solar | 05_05_335W2 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 58 | 39 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | NORTHAMPTON | 177558 | 01060 | 22.8 | Solar | 05_09_901W1 | 07/13/2017 | 07/13/2017 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2017 |  | 9/28/2018 | N | EXP | 435 |  |  | 0 | 0 | 0 |  |  | 8/14/2018 | Connected |  | N
National Grid | WESTBOROUGH | 599975 | 01581 | 11.6 | Solar | 05_05_312W4 | 04/04/2024 | 04/17/2024 | 8 | 4 | 4 | 04/18/2024 | 04/18/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2024 | 04/04/2024 | 7/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/25/2024 | Connected |  | N
National Grid | RANDOLPH | 623067 | 02368 | 5.76 | Solar | 05_07_5W4 | 07/08/2024 | 08/02/2024 | 16 | 14 | 2 | 08/05/2024 | 08/05/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2024 | 07/08/2024 | 8/22/2025 | Y | EXP | 365 | 12/03/2024 | 03/06/2025 | 92 | 0 | 92 |  |  | 3/14/2025 | Connected |  | N
National Grid | SEEKONK | 175115 | 02771 | 100 | Solar | 05_05_7L3 | 10/16/2013 | 10/16/2013 | 6 | 0 | 6 | 10/25/2013 | 10/25/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/8/2013 |  | 12/2/2013 | N | EXP | 24 |  |  | 0 | 0 | 0 | 11/14/2013 | 11/14/2013 | 12/31/2013 | Connected |  | N
National Grid | WINTHROP | 176613 | 02152 | 32.4 | Solar | 05_12_22W1 | 02/12/2016 | 02/12/2016 | 3 | 3 | 0 | 02/18/2016 | 02/18/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2016 |  | 8/20/2017 | N | EXP | 478 |  |  | 0 | 0 | 0 | 8/7/2017 | 8/7/2017 | 8/7/2017 | Connected |  | N
National Grid | SHEFFIELD | 206967 | 01257 | 250 | Solar | 05_09_1108W1 | 01/29/2019 | 03/04/2019 | 22 | 17 | 5 | 03/05/2019 | 03/05/2019 | 14 | 2 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 313773 | 02339 | 16 | Solar | 05_07_95W5 | 10/19/2020 | 01/05/2022 | 0 | 0 | 0 | 10/21/2020 | 10/21/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 1/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 178023 | 02324 | 576 | Solar | 05_07_912W73 | 08/30/2017 | 08/30/2017 | 66 | 66 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2017 | 12/27/2017 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/5/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 701470 | 01007 | 0 | Other | 05_09_514L1 | 08/08/2025 | 09/15/2025 | 25 | 14 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/16/2025 | 10/03/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 676136 | 01757 | 17.16 | Solar | 05_05_335W3 | 03/06/2025 | 03/12/2025 | 4 | 0 | 4 | 03/13/2025 | 03/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTHAMPTON | 177588 | 01060 | 4980 | Solar | 05_09_901W1 | 05/17/2017 | 05/17/2017 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/25/2017 | 06/23/2017 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/23/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 603992 | 01581 | 10 | Solar | 05_05_312W4 | 04/17/2024 | 04/18/2024 | 1 | 0 | 1 | 04/19/2024 | 04/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 647448 | 02368 | 6.4 | Solar | 05_07_5W4 | 10/16/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 63 | 52 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 10/16/2024 | 3/7/2026 | Y | EXP | 365 | 06/27/2025 | 06/26/2025 | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | SEEKONK | 175230 | 02771 | 230 | Solar | 05_05_7L3 | 01/07/2015 | 01/07/2015 | 7 | 5 | 2 | 01/19/2015 | 01/19/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2015 |  | 5/31/2015 | N | EXP | 18 |  |  | 0 | 0 | 0 | 3/9/2015 | 3/9/2015 | 7/29/2015 | Connected |  | N
National Grid | WINTHROP | 399139 | 02152 | 5.8 | Solar | 05_12_22W1 | 12/09/2021 | 12/13/2021 | 2 | 0 | 2 | 12/14/2021 | 12/14/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | EGREMONT | 206961 | 01258 | 250 | Solar | 05_09_1108W1 | 01/29/2019 | 02/22/2019 | 17 | 12 | 5 | 02/25/2019 | 02/25/2019 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 322067 | 02339 | 15.36 | Solar | 05_07_95W5 | 10/27/2020 | 10/29/2020 | 1 | 0 | 1 | 10/30/2020 | 10/30/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2021 | Connected |  | N
National Grid | BRIDGEWATER | 316450 | 02324 | 100 | Solar | 05_07_912W73 | 10/02/2020 | 10/19/2020 | 9 | 0 | 9 | 10/20/2020 | 10/20/2020 | 48 | 26 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 |  | 8/19/2022 | N | EXP | 592 |  |  | 0 | 0 | 0 |  |  | 8/10/2022 | Connected |  | N
National Grid | MONSON | 716758 | 01057 | 10 | Solar | 05_09_514L1 | 09/04/2025 | 10/28/2025 | 1 | 0 | 1 | 10/29/2025 | 10/29/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 717407 | 01757 | 11.52 | Solar | 05_05_335W3 | 09/08/2025 | 09/26/2025 | 4 | 0 | 4 | 10/08/2025 | 10/08/2025 | 26 | 13 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 09/08/2025 | 12/18/2026 | Y | EXP | 365 | 02/14/2026 | 03/03/2026 | 18 | 0 | 18 |  |  |  | Meter Installation |  | Y
National Grid | NORTHAMPTON | 178642 | 01060 | 57.6 | Solar | 05_09_901W1 | 04/10/2018 | 04/10/2018 | 7 | 0 | 7 | 04/20/2018 | 04/20/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2018 |  | 4/16/2019 | N | EXP | 293 |  |  | 0 | 0 | 0 |  |  | 11/26/2019 | Connected |  | N
National Grid | WESTBOROUGH | 610948 | 01581 | 8.775 | Solar | 05_05_312W4 | 05/14/2024 | 05/23/2024 | 4 | 3 | 1 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2024 |  | 6/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | RANDOLPH | 652359 | 02368 | 7.6 | Solar | 05_07_5W4 | 11/14/2024 | 12/18/2024 | 6 | 0 | 6 | 12/19/2024 | 12/19/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/14/2024 | 2/14/2026 | Y | EXP | 365 | 05/21/2025 | 11/12/2025 | 176 | 0 | 176 |  |  | 11/13/2025 | Connected |  | N
National Grid | SEEKONK | 216590 | 02771 | 6 | Solar | 05_05_7L3 | 04/04/2019 | 07/11/2019 | 72 | 70 | 2 | 07/12/2019 | 07/12/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 |  | 11/25/2019 | N | EXP | 125 |  |  | 0 | 0 | 0 |  |  | 10/10/2019 | Connected |  | N
National Grid | SWAMPSCOTT | 608123 | 01907 | 2.61 | Solar | 05_12_22W1 | 05/01/2024 | 09/11/2024 | 21 | 20 | 1 | 09/12/2024 | 09/12/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 05/01/2024 | 11/13/2025 | Y | EXP | 365 | 02/27/2025 | 01/22/2026 | 330 | 0 | 330 |  |  | 3/21/2025 | Connected |  | N
National Grid | SHEFFIELD | 438170 | 01257 | 250 | Solar | 05_09_1108W1 | 07/08/2022 | 07/26/2022 | 12 | 3 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2024 | Connected |  | N
National Grid | HANOVER | 344715 | 02339 | 9.6 | Solar | 05_07_95W5 | 03/02/2021 | 03/08/2021 | 3 | 0 | 3 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 8/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 316356 | 02324 | 100 | Solar | 05_07_912W73 | 10/02/2020 | 11/03/2020 | 20 | 14 | 6 | 11/04/2020 | 11/04/2020 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2023 | Connected |  | N
National Grid | PALMER | 721945 | 01069 | 4.93 | Solar | 05_09_514L1 | 09/25/2025 | 10/03/2025 | 3 | 0 | 3 | 10/22/2025 | 10/22/2025 | 15 | 4 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 732633 | 01757 | 10 | Solar | 05_05_335W3 | 11/11/2025 | 01/22/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 193373 | 01060 | 5 | Solar | 05_09_901W1 | 08/13/2018 | 09/27/2018 | 24 | 23 | 1 | 09/28/2018 | 09/28/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2018 | 08/13/2018 | 2/24/2020 | Y | EXP | 5 | 11/01/2019 | 11/04/2019 | 3 | 0 | 3 |  |  | 1/31/2020 | Connected |  | N
National Grid | WESTBOROUGH | 625957 | 01581 | 0 | Solar | 05_05_312W4 | 07/18/2024 | 07/24/2024 | 4 | 0 | 4 | 07/25/2024 | 07/25/2024 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/2/2024 | Connected |  | N
National Grid | RANDOLPH | 654215 | 02368 | 3.8 | Solar | 05_07_5W4 | 11/14/2024 | 12/09/2024 | 5 | 0 | 5 | 12/10/2024 | 12/10/2024 | 39 | 15 | 24 | 02/18/2025 | 03/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 03/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 331769 | 02771 | 9.36 | Solar | 05_05_7L3 | 12/15/2020 | 01/06/2021 | 14 | 10 | 4 | 01/07/2021 | 01/07/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2021 |  | 1/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2021 | Connected |  | N
National Grid | SWAMPSCOTT | 663578 | 01907 | 3.19 | Solar | 05_12_22W1 | 01/03/2025 | 02/05/2025 | 19 | 14 | 5 | 02/06/2025 | 02/06/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 01/03/2025 | 7/8/2026 | Y | EXP | 365 | 08/28/2025 | 11/14/2025 | 79 | 0 | 79 |  |  | 11/26/2025 | Connected |  | N
National Grid | SHEFFIELD | 542209 | 01257 | 1000 | Solar | 05_09_1108W1 | 05/28/2024 |  | 256 | 246 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 424728 | 02339 | 15.2 | Solar | 05_07_95W5 | 04/19/2022 | 04/26/2022 | 6 | 4 | 2 | 04/27/2022 | 04/27/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/25/2022 |  | 6/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2022 | Connected |  | N
National Grid | BRIDGEWATER | 322230 | 02324 | 500 | Solar | 05_07_912W73 | 11/17/2020 |  | 277 | 269 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 725555 | 01069 | 7.6 | Solar | 05_09_514L1 | 10/09/2025 | 10/30/2025 | 2 | 0 | 2 | 11/18/2025 | 11/18/2025 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | UPTON | 746584 | 01568 | 15.2 | Solar | 05_05_335W3 | 01/21/2026 | 01/23/2026 | 2 | 0 | 2 | 01/26/2026 | 01/26/2026 | 29 | 18 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 302123 | 01060 | 2000 | Solar | 05_09_901W1 | 02/19/2021 | 03/30/2021 | 27 | 18 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/31/2021 | 05/13/2021 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 642208 | 01581 | 11.5 | Solar | 05_05_312W4 | 09/23/2024 | 10/03/2024 | 9 | 7 | 2 | 10/04/2024 | 10/04/2024 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 |  | 10/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | RANDOLPH | 675924 | 02368 | 3.8 | Solar | 05_07_5W4 | 03/05/2025 | 03/21/2025 | 29 | 25 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 337135 | 02771 | 499.5 | Solar | 05_05_7L3 | 05/14/2021 | 11/11/2021 | 124 | 115 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 675270 | 01907 | 67.3 | Solar | 05_12_22W2 | 03/11/2025 | 04/15/2025 | 25 | 16 | 9 | 04/16/2025 | 04/16/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2025 |  | 12/31/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SHEFFIELD | 640301 | 01257 | 17.86 | Solar | 05_09_1108W1 | 09/14/2024 | 09/17/2024 | 2 | 0 | 2 | 09/18/2024 | 09/18/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2024 | 09/14/2024 | 10/16/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2025 | Connected |  | N
National Grid | HANOVER | 506126 | 02339 | 10 | Solar | 05_07_95W5 | 03/21/2023 | 01/10/2024 | 202 | 200 | 2 | 01/11/2024 | 01/11/2024 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2024 |  | 4/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/4/2024 | Connected |  | N
National Grid | BRIDGEWATER | 322658 | 02324 | 133.2 | Solar | 05_07_912W73 | 11/05/2020 | 11/13/2020 | 4 | 0 | 4 | 11/16/2020 | 11/16/2020 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2023 | Connected |  | N
National Grid | PALMER | 174238 | 01080 | 2000 | Solar | 05_09_514L1 | 02/15/2012 | 02/15/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/29/2012 | 05/14/2012 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 02/15/2012 | 4/1/2012 | Y | STD | 255 | 12/19/2013 | 01/24/2014 | 23 | 0 | 23 | 12/24/2013 | 12/24/2013 | 12/27/2013 | Connected |  | N
National Grid | MILFORD | 749229 | 01757 | 4.94 | Solar | 05_05_335W3 | 02/09/2026 |  | 13 | 12 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTHAMPTON | 309180 | 01060 | 22.8 | Solar | 05_09_901W1 | 09/17/2020 | 09/23/2020 | 3 | 0 | 3 | 09/24/2020 | 09/24/2020 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2020 |  | 9/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/19/2021 | Connected |  | N
National Grid | WESTBOROUGH | 643250 | 01581 | 10 | Solar | 05_05_312W4 | 09/27/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 | 09/27/2024 | 12/12/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/22/2025 | Connected |  | N
National Grid | RANDOLPH | 688539 | 02368 | 5.76 | Solar | 05_07_5W4 | 05/01/2025 | 06/03/2025 | 1 | 0 | 1 | 06/04/2025 | 06/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 | 05/01/2025 | 8/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 347852 | 02771 | 995 | Solar | 05_05_7L3 | 06/10/2021 | 07/14/2021 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/15/2021 | 08/11/2021 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 685919 | 01902 | 5.76 | Solar | 05_12_22W2 | 04/18/2025 | 05/12/2025 | 2 | 0 | 2 | 05/30/2025 | 05/30/2025 | 59 | 46 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SHEFFIELD | 687036 | 01257 | 23.04 | Solar | 05_09_1108W1 | 05/02/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | HANOVER | 542074 | 02339 | 15.2 | Solar | 05_07_95W5 | 10/18/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 |  | 1/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2024 | Connected |  | N
National Grid | BRIDGEWATER | 377527 | 02324 | 15.2 | Solar | 05_07_912W73 | 08/23/2021 | 08/30/2021 | 4 | 2 | 2 | 09/02/2021 | 09/02/2021 | 55 | 25 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/29/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 175744 | 01080 | 496.8 | Solar | 05_09_514L1 | 10/28/2014 | 10/28/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2014 | 01/14/2015 | 15 | 3 | 12 | 11/05/2014 | 12/05/2014 | 20 | 0 | 20 |  | 01/14/2015 | 15 | 3 | 12 |  |  | 0 | 0 | 0 | 6/5/2015 |  | 2/15/2016 | N | STD | 255 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 174772 | 01568 | 60 | Solar | 05_05_335W3 | 01/17/2013 | 01/17/2013 | 9 | 7 | 2 | 02/01/2013 | 02/01/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2013 |  | 4/15/2013 | N | EXP | 1 |  |  | 0 | 0 | 0 | 7/29/2013 | 7/29/2013 | 8/16/2013 | Connected |  | N
National Grid | NORTHAMPTON | 383931 | 01060 | 20.59 | Solar | 05_09_901W1 | 09/23/2021 | 09/27/2021 | 2 | 0 | 2 | 09/28/2021 | 09/28/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2021 |  | 7/21/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 643356 | 01581 | 15.2 | Solar | 05_05_312W4 | 09/27/2024 | 09/30/2024 | 1 | 0 | 1 | 10/01/2024 | 10/01/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 692971 | 02368 | 3.8 | Solar | 05_07_5W4 | 05/23/2025 | 07/03/2025 | 9 | 7 | 2 | 07/25/2025 | 07/25/2025 | 47 | 25 | 22 | 10/14/2025 | 10/28/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 10/28/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/31/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 422061 | 02771 | 0 | Battery Add-On | 05_05_7L3 | 10/19/2022 | 05/04/2023 | 134 | 125 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/05/2023 | 07/12/2023 | 44 | 24 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 709673 | 01907 | 10 | Solar | 05_12_22W2 | 08/05/2025 | 10/01/2025 | 4 | 0 | 4 | 10/09/2025 | 10/09/2025 | 37 | 26 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SHEFFIELD | 706480 | 01257 | 23 | Solar | 05_09_1108W1 | 07/24/2025 | 07/28/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 |  | 10/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2026 | Connected |  | N
National Grid | HANOVER | 573570 | 02339 | 10 | Solar | 05_07_95W5 | 11/27/2023 | 12/04/2023 | 5 | 3 | 2 | 12/05/2023 | 12/05/2023 | 38 | 19 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 385119 | 02324 | 34.6 | Solar | 05_07_912W73 | 10/07/2021 | 01/06/2022 | 5 | 2 | 3 | 10/18/2021 | 10/18/2021 | 25 | 4 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 |  | 1/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2022 | Connected |  | N
National Grid | PALMER | 175995 | 01069 | 16.98 | Solar | 05_09_514L1 | 06/10/2015 | 06/10/2015 | 6 | 6 | 0 | 06/22/2015 | 06/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/16/2016 | N | EXP | 351 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 1/12/2016 | Connected |  | N
National Grid | UPTON | 175574 | 01568 | 490 | Solar | 05_05_335W3 | 12/05/2014 | 12/05/2014 | 4 | 1 | 3 | 12/12/2014 | 12/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 12/05/2014 | 7/31/2015 | Y | EXP | 156 | 08/24/2015 | 11/16/2015 | 57 | 0 | 57 | 5/7/2015 | 5/7/2015 | 11/20/2015 | Connected |  | N
National Grid | NORTHAMPTON | 457933 | 01060 | 6.67 | Solar | 05_09_901W1 | 09/30/2022 | 10/10/2022 | 6 | 2 | 4 | 10/11/2022 | 10/11/2022 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 09/30/2022 | 3/29/2024 | Y | EXP | 365 | 03/29/2023 | 03/30/2023 | 2 | 0 | 2 |  |  | 5/31/2023 | Connected |  | Y
National Grid | WESTBOROUGH | 650666 | 01581 | 1.74 | Solar | 05_05_312W4 | 10/29/2024 | 12/20/2024 | 28 | 24 | 4 | 12/23/2024 | 12/23/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | RANDOLPH | 695431 | 02368 | 7.6 | Solar | 05_07_5W4 | 06/03/2025 | 07/08/2025 | 2 | 0 | 2 | 07/15/2025 | 07/15/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 458562 | 02771 | 8.99 | Solar | 05_05_7L3 | 09/27/2022 | 10/10/2022 | 8 | 7 | 1 | 10/11/2022 | 10/11/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2022 |  | 11/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2023 | Connected |  | N
National Grid | LYNN | 725517 | 01902 | 5.76 | Solar | 05_12_22W2 | 10/09/2025 | 10/20/2025 | 6 | 1 | 5 | 11/13/2025 | 11/13/2025 | 63 | 47 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | EGREMONT | 706277 | 01258 | 20 | Solar | 05_09_1108W1 | 07/25/2025 | 07/29/2025 | 2 | 0 | 2 | 07/30/2025 | 07/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 |  | 10/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2025 | Connected |  | N
National Grid | HANOVER | 652079 | 02339 | 5.76 | Solar | 05_07_95W5 | 11/14/2024 | 12/17/2024 | 7 | 0 | 7 | 12/18/2024 | 12/18/2024 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/14/2024 | 3/17/2026 | Y | EXP | 365 | 06/12/2025 | 09/18/2025 | 99 | 0 | 99 |  |  | 10/15/2025 | Connected |  | N
National Grid | BRIDGEWATER | 435095 | 02324 | 0 | Other | 05_07_912W73 | 07/05/2022 |  | 210 | 202 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 178634 | 01069 | 2000 | Solar | 05_09_514L1 | 04/09/2018 | 04/20/2018 | 7 | 6 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 07/02/2018 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 175586 | 01568 | 20 | Solar | 05_05_335W3 | 04/18/2014 | 04/18/2014 | 6 | 0 | 6 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2014 | 04/18/2014 | 6/30/2014 | Y | EXP | 45 |  |  | 0 | 0 | 0 | 5/29/2014 | 5/29/2014 | 7/14/2014 | Connected |  | N
National Grid | NORTHAMPTON | 566378 | 01060 | 3.78 | Solar | 05_09_901W1 | 11/13/2023 | 11/14/2023 | 1 | 0 | 1 | 11/15/2023 | 11/15/2023 | 56 | 33 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 652265 | 01581 | 11.5 | Solar | 05_05_312W4 | 11/05/2024 | 01/08/2025 | 2 | 0 | 2 | 01/09/2025 | 01/09/2025 | 66 | 45 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2025 | Connected |  | N
National Grid | RANDOLPH | 696439 | 02368 | 10.64 | Solar | 05_07_5W4 | 06/05/2025 | 07/08/2025 | 2 | 0 | 2 | 07/29/2025 | 07/29/2025 | 45 | 39 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2025 |  | 10/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/3/2025 | Connected |  | N
National Grid | SEEKONK | 530430 | 02771 | 50 | Solar | 05_05_7L3 | 06/14/2023 | 07/25/2023 | 27 | 17 | 10 |  |  | 86 | 61 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 730600 | 01902 | 5 | Solar | 05_12_22W2 | 11/03/2025 | 11/04/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 17 | 0 | 17 | 12/24/2025 | 01/14/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 01/14/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | EGREMONT | 717708 | 01258 | 22.8 | Solar | 05_09_1108W1 | 09/15/2025 | 10/07/2025 | 15 | 13 | 2 | 10/08/2025 | 10/08/2025 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 653287 | 02339 | 10 | Solar | 05_07_95W5 | 11/14/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2025 | 11/14/2024 | 2/5/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/10/2025 | Connected |  | N
National Grid | BRIDGEWATER | 489549 | 02324 | 67.3 | Solar | 05_07_912W73 | 01/06/2023 | 03/16/2023 | 47 | 37 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2023 | 04/13/2023 | 27 | 7 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 193761 | 01069 | 680 | Solar | 05_09_514L1 | 08/22/2018 | 09/19/2018 | 18 | 14 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/20/2018 | 11/03/2018 | 36 | 10 | 26 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 175722 | 01747 | 16 | Solar | 05_05_335W3 | 12/31/2014 | 12/31/2014 | 13 | 11 | 2 | 01/22/2015 | 01/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2015 |  | 5/31/2015 | N | EXP | 117 |  |  | 0 | 0 | 0 | 6/9/2015 | 6/9/2015 | 3/1/2016 | Connected |  | N
National Grid | NORTHAMPTON | 620131 | 01060 | 100 | Solar | 05_09_901W1 | 06/28/2024 | 07/23/2024 | 16 | 7 | 9 | 07/24/2024 | 07/24/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2024 |  | 12/11/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/16/2025 | Connected |  | N
National Grid | WESTBOROUGH | 652105 | 01581 | 10 | Solar | 05_05_312W4 | 11/14/2024 | 01/08/2025 | 24 | 19 | 5 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 705802 | 02368 | 3.8 | Solar | 05_07_5W4 | 07/18/2025 | 09/11/2025 | 2 | 0 | 2 | 09/12/2025 | 09/12/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 530749 | 02771 | 100 | Solar | 05_05_7L3 | 06/14/2023 | 08/09/2023 | 39 | 29 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 735887 | 01902 | 6.84 | Solar | 05_12_22W2 | 11/25/2025 | 11/26/2025 | 1 | 0 | 1 | 02/02/2026 | 02/02/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EGREMONT | 735079 | 01258 | 15 | Solar | 05_09_1108W2 | 11/19/2025 | 11/24/2025 | 3 | 0 | 3 | 11/25/2025 | 11/25/2025 | 33 | 11 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 | 11/19/2025 | 1/21/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | HANOVER | 654880 | 02339 | 5.76 | Solar | 05_07_95W5 | 11/20/2024 | 12/18/2024 | 3 | 0 | 3 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 | 11/20/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | BRIDGEWATER | 676325 | 02324 | 5.76 | Solar | 05_07_912W73 | 03/07/2025 | 03/24/2025 | 76 | 73 | 3 | 09/11/2025 | 09/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 11/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | MONSON | 195866 | 01057 | 13.8 | Solar | 05_09_514L1 | 09/13/2018 | 10/04/2018 | 1 | 0 | 1 | 10/05/2018 | 10/05/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 175805 | 01568 | 54 | Solar | 05_05_335W3 | 03/02/2015 | 03/02/2015 | 26 | 22 | 4 | 04/09/2015 | 04/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 8/31/2015 | N | EXP | 14 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 8/12/2015 | Connected |  | N
National Grid | NORTHAMPTON | 652952 | 01060 | 5.76 | Solar | 05_09_901W1 | 11/07/2024 | 11/19/2024 | 5 | 0 | 5 | 11/20/2024 | 11/20/2024 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | WESTBOROUGH | 654499 | 01581 | 9.88 | Solar | 05_05_312W4 | 11/14/2024 | 12/06/2024 | 10 | 5 | 5 | 12/09/2024 | 12/09/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2025 | Connected |  | N
National Grid | RANDOLPH | 174390 | 02368 | 230 | Solar | 05_07_60J1 | 06/08/2012 | 06/08/2012 | 5 | 0 | 5 | 06/19/2012 | 06/19/2012 | 370 | 0 | 370 | 01/15/2014 | 01/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/15/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 530748 | 02771 | 100 | Solar | 05_05_7L3 | 06/14/2023 | 08/09/2023 | 39 | 29 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 740958 | 01902 | 14.06 | Solar | 05_12_22W2 | 12/19/2025 | 12/26/2025 | 2 | 0 | 2 | 01/12/2026 | 01/12/2026 | 30 | 15 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SHEFFIELD | 174719 | 01257 | 364 | Solar | 05_09_1108W2 | 01/15/2014 | 01/15/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2014 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 656245 | 02339 | 3.8 | Solar | 05_07_95W5 | 11/22/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 |  | 3/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2025 | Connected |  | N
National Grid | BRIDGEWATER | 676145 | 02324 | 5.76 | Solar | 05_07_912W73 | 04/02/2025 | 09/15/2025 | 113 | 110 | 3 | 09/16/2025 | 09/16/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 203931 | 01069 | 10 | Solar | 05_09_514L1 | 02/12/2019 | 02/15/2019 | 3 | 3 | 0 | 02/19/2019 | 02/19/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2019 | 02/12/2019 | 11/11/2019 | Y | EXP | 263 | 08/24/2019 | 09/16/2019 | 23 | 0 | 23 |  |  | 10/9/2019 | Connected |  | N
National Grid | MILFORD | 176241 | 01757 | 1000 | Solar | 05_05_335W3 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 05/29/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 04/28/2015 | 8/31/2017 | Y | STD | 674 | 05/10/2017 | 08/22/2017 | 72 | 0 | 72 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | NORTHAMPTON | 652876 | 01060 | 3.48 | Solar | 05_09_901W1 | 11/08/2024 | 11/19/2024 | 4 | 0 | 4 | 11/20/2024 | 11/20/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 11/08/2024 | 12/24/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | WESTBOROUGH | 664419 | 01581 | 11.5 | Solar | 05_05_312W4 | 01/08/2025 | 03/19/2025 | 3 | 0 | 3 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | RANDOLPH | 322008 | 02368 | 9.84 | Solar | 05_07_60J1 | 10/27/2020 | 10/29/2020 | 1 | 0 | 1 | 10/30/2020 | 10/30/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 10/27/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | SEEKONK | 530747 | 02771 | 100 | Solar | 05_05_7L3 | 06/14/2023 | 08/09/2023 | 39 | 29 | 10 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 749204 | 01902 | 7.6 | Solar | 05_12_22W2 | 02/04/2026 | 02/12/2026 | 2 | 0 | 2 | 02/23/2026 | 02/23/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SHEFFIELD | 174850 | 01257 | 999 | Solar | 05_09_1108W2 | 08/05/2013 | 08/05/2013 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2013 | 10/04/2013 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/23/2014 | 08/05/2013 | 6/30/2014 | Y | STD | 68 | 03/10/2015 | 04/02/2015 | 16 | 0 | 16 | 5/1/2015 | 5/1/2015 | 4/28/2015 | Connected |  | N
National Grid | HANOVER | 666901 | 02339 | 49.4 | Solar | 05_07_95W5 | 01/21/2025 | 03/19/2025 | 41 | 31 | 10 | 03/20/2025 | 03/20/2025 | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | BRIDGEWATER | 670394 | 02324 | 10 | Solar | 05_07_912W74 | 02/06/2025 | 02/18/2025 | 4 | 0 | 4 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 225328 | 01069 | 8.51 | Solar | 05_09_514L1 | 09/06/2019 | 09/09/2019 | 0 | 0 | 0 | 09/10/2019 | 09/10/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2019 | 09/06/2019 | 9/9/2020 | Y | EXP | 365 | 05/29/2020 | 06/11/2020 | 13 | 0 | 13 |  |  | 7/20/2020 | Connected |  | N
National Grid | MILFORD | 176240 | 01757 | 1000 | Solar | 05_05_335W3 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2015 | 05/29/2015 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2015 | 04/28/2015 | 8/31/2017 | Y | STD | 674 | 05/10/2017 | 08/22/2017 | 72 | 0 | 72 | 9/5/2017 | 9/5/2017 | 9/5/2017 | Connected |  | N
National Grid | NORTHAMPTON | 664283 | 01060 | 10 | Solar | 05_09_901W1 | 01/07/2025 | 01/23/2025 | 5 | 0 | 5 | 01/24/2025 | 01/24/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 01/07/2025 | 3/17/2026 | Y | EXP | 365 | 09/19/2025 | 09/18/2025 | 0 | 0 | 0 |  |  | 9/23/2025 | Connected |  | N
National Grid | WESTBOROUGH | 674216 | 01581 | 15.2 | Solar | 05_05_312W4 | 02/25/2025 | 02/27/2025 | 2 | 0 | 2 | 02/28/2025 | 02/28/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2025 |  | 4/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/16/2025 | Connected |  | N
National Grid | ABINGTON | 336920 | 02351 | 8.7 | Solar | 05_07_60J1 | 01/14/2021 | 01/15/2021 | 0 | 0 | 0 | 01/19/2021 | 01/19/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | SEEKONK | 647002 | 02771 | 2.32 | Solar | 05_05_7L3 | 10/24/2024 | 11/26/2024 | 3 | 0 | 3 | 11/27/2024 | 11/27/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SWAMPSCOTT | 192216 | 01907 | 7.6 | Solar | 05_12_22W2 | 07/30/2018 | 07/31/2018 | 0 | 0 | 0 | 08/02/2018 | 08/02/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/30/2018 | 9/30/2019 | Y | EXP | 399 | 03/16/2019 | 03/15/2019 | 0 | 0 | 0 |  |  | 8/21/2019 | Connected |  | N
National Grid | SHEFFIELD | 174893 | 01257 | 280 | Bio Gas | 05_09_1108W2 | 08/20/2013 | 08/20/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2013 | 09/24/2013 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2015 | 08/20/2013 | 9/10/2018 | Y | STD | 1237 | 09/25/2017 | 03/30/2018 | 111 | 0 | 111 |  |  | 9/5/2018 | Connected |  | N
National Grid | HANOVER | 666969 | 02339 | 47.5 | Solar | 05_07_95W5 | 01/21/2025 | 04/14/2025 | 58 | 49 | 9 | 04/15/2025 | 04/15/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2025 | Connected |  | N
National Grid | BRIDGEWATER | 733178 | 02324 | 15.76 | Solar | 05_07_912W74 | 11/19/2025 | 11/20/2025 | 1 | 0 | 1 | 11/21/2025 | 11/21/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2025 |  | 1/28/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WILBRAHAM | 308061 | 01095 | 2500 | Solar | 05_09_514L1 | 09/17/2020 | 10/19/2020 | 21 | 15 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2020 | 11/17/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 176819 | 01568 | 299.7 | Solar | 05_05_335W3 | 11/06/2015 | 11/06/2015 | 0 | 0 | 0 | 11/09/2015 | 11/09/2015 | 0 | 0 | 0 | 02/23/2016 | 03/25/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  | 03/25/2016 | 22 | 1 | 21 |  |  | 0 | 0 | 0 | 5/17/2016 | 11/06/2015 | 4/6/2017 | Y | EXP | 324 | 10/06/2016 | 04/05/2017 | 122 | 0 | 122 | 3/21/2017 | 3/21/2017 | 5/3/2017 | Connected |  | N
National Grid | NORTHAMPTON | 677262 | 01060 | 7.6 | Solar | 05_09_901W1 | 03/11/2025 | 03/17/2025 | 5 | 1 | 4 | 03/18/2025 | 03/18/2025 | 61 | 39 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 | 03/11/2025 | 7/17/2026 | Y | EXP | 365 | 08/30/2025 | 08/29/2025 | 0 | 0 | 0 |  |  | 9/8/2025 | Connected |  | N
National Grid | WESTBOROUGH | 676548 | 01581 | 10 | Solar | 05_05_312W4 | 03/11/2025 | 03/27/2025 | 13 | 8 | 5 | 03/28/2025 | 03/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 4/29/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 336885 | 02351 | 8.7 | Solar | 05_07_60J1 | 01/14/2021 | 01/15/2021 | 0 | 0 | 0 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2021 |  | 1/14/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2021 | Connected |  | N
National Grid | SEEKONK | 673502 | 02771 | 17.11 | Solar | 05_05_7L3 | 02/21/2025 | 04/14/2025 | 36 | 25 | 11 | 04/15/2025 | 04/15/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 5/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/11/2025 | Connected |  | N
National Grid | LYNN | 310486 | 01902 | 7.6 | Solar | 05_12_22W2 | 09/29/2020 | 09/30/2020 | 0 | 0 | 0 | 10/01/2020 | 10/01/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2020 | 09/29/2020 | 9/1/2021 | Y | EXP | 365 | 03/10/2021 | 06/11/2021 | 93 | 0 | 93 |  |  | 7/2/2021 | Connected |  | N
National Grid | SHEFFIELD | 177925 | 01222 | 2079 | Solar | 05_09_1108W2 | 04/17/2017 | 04/17/2017 | 32 | 30 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/02/2017 | 08/15/2017 | 51 | 33 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2018 | 04/17/2017 | 5/7/2021 | Y | STD | 771 | 02/06/2020 | 10/01/2020 | 239 | 9 | 230 | 10/19/2020 | 3/11/2021 | 5/7/2021 | Connected |  | N
National Grid | HANOVER | 666962 | 02339 | 9.5 | Solar | 05_07_95W5 | 01/21/2025 | 02/24/2025 | 4 | 2 | 2 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 | 01/21/2025 | 4/23/2026 | Y | EXP | 365 | 07/02/2025 | 07/05/2025 | 4 | 0 | 4 |  |  | 7/11/2025 | Connected |  | N
National Grid | BRIDGEWATER | 748648 | 02324 | 5.76 | Solar | 05_07_912W74 | 02/02/2026 | 02/03/2026 | 2 | 0 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | PALMER | 373295 | 01069 | 7.6 | Solar | 05_09_514L1 | 09/13/2021 | 10/12/2021 | 20 | 19 | 1 | 10/13/2021 | 10/13/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2021 |  | 10/11/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 176809 | 01568 | 11.4 | Solar | 05_05_335W3 | 04/27/2016 | 04/27/2016 | 8 | 8 | 0 | 05/10/2016 | 05/10/2016 | 184 | 0 | 184 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/3/2017 | N | EXP | 342 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 698154 | 01060 | 7.6 | Solar | 05_09_901W1 | 06/12/2025 | 06/25/2025 | 3 | 0 | 3 | 07/11/2025 | 07/11/2025 | 22 | 9 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | WESTBOROUGH | 681799 | 01581 | 20 | Solar | 05_05_312W4 | 04/02/2025 | 04/07/2025 | 3 | 0 | 3 | 04/08/2025 | 04/08/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2025 |  | 5/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/4/2025 | Connected |  | N
National Grid | ABINGTON | 368498 | 02351 | 7.6 | Solar | 05_07_60J1 | 07/08/2021 | 08/24/2021 | 32 | 31 | 1 | 08/25/2021 | 08/25/2021 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 1/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2022 | Connected |  | N
National Grid | SEEKONK | 681570 | 02771 | 4.64 | Solar | 05_05_7L3 | 03/31/2025 | 04/16/2025 | 1 | 0 | 1 | 04/18/2025 | 04/18/2025 | 60 | 42 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 324111 | 01907 | 66.6 | Solar | 05_12_22W2 | 11/12/2020 | 12/08/2020 | 16 | 12 | 4 | 12/09/2020 | 12/09/2020 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2021 |  | 10/3/2023 | N | EXP | 722 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 178401 | 01222 | 244 | Solar | 05_09_1108W2 | 04/02/2018 | 04/02/2018 | 4 | 0 | 4 | 04/06/2018 | 04/06/2018 | 25 | 15 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 04/02/2018 | 4/20/2021 | Y | EXP | 577 | 05/29/2020 | 10/16/2020 | 141 | 5 | 136 |  |  | 4/12/2021 | Connected |  | N
National Grid | HANOVER | 689624 | 02339 | 20 | Solar | 05_07_95W5 | 05/06/2025 | 05/09/2025 | 3 | 0 | 3 | 05/12/2025 | 05/12/2025 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 | 05/06/2025 | 7/8/2026 | Y | EXP | 365 | 09/11/2025 | 10/24/2025 | 44 | 0 | 44 |  |  | 10/30/2025 | Connected |  | N
National Grid | BRIDGEWATER | 184458 | 02333 | 4950 | Solar | 05_07_912W74 | 05/04/2018 | 05/04/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2018 | 06/15/2018 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2018 |  | 1/25/2021 | N | STD | 837 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 448095 | 01069 | 7.6 | Solar | 05_09_514L1 | 08/03/2022 | 08/10/2022 | 6 | 5 | 1 | 08/11/2022 | 08/11/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 177172 | 01568 | 10 | Solar | 05_05_335W3 | 05/29/2016 | 05/29/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/29/2016 | 6/6/2017 | Y | EXP | 351 | 09/13/2016 | 09/23/2016 | 8 | 0 | 8 | 11/3/2016 | 11/3/2016 | 11/3/2016 | Connected |  | N
National Grid | NORTHAMPTON | 714730 | 01060 | 12.6 | Solar | 05_09_901W1 | 08/26/2025 | 10/21/2025 | 3 | 1 | 2 | 10/22/2025 | 10/22/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 12/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | WESTBOROUGH | 696492 | 01581 | 23 | Solar | 05_05_312W4 | 06/05/2025 | 06/10/2025 | 3 | 0 | 3 | 06/11/2025 | 06/11/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2025 |  | 7/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | ABINGTON | 649092 | 02351 | 10 | Solar | 05_07_60J1 | 11/04/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 691646 | 02771 | 9.28 | Solar | 05_05_7L3 | 07/11/2025 | 08/07/2025 | 17 | 14 | 3 | 08/08/2025 | 08/08/2025 | 69 | 46 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2025 | 07/11/2025 | 12/16/2026 | Y | EXP | 365 | 01/16/2026 | 01/22/2026 | 7 | 0 | 7 |  |  | 2/18/2026 | Connected |  | N
National Grid | LYNN | 436299 | 01902 | 6 | Solar | 05_12_22W2 | 06/21/2022 | 06/22/2022 | 1 | 0 | 1 | 06/23/2022 | 06/23/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2022 | Connected |  | N
National Grid | SHEFFIELD | 178431 | 01222 | 636 | Solar | 05_09_1108W2 | 03/05/2018 | 03/05/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 696791 | 02339 | 15.76 | Solar | 05_07_95W5 | 06/25/2025 | 06/27/2025 | 2 | 0 | 2 | 06/30/2025 | 06/30/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 194382 | 02324 | 2000 | Solar | 05_07_912W74 | 09/17/2018 | 11/08/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/09/2018 | 01/07/2019 | 37 | 8 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2020 |  | 1/7/2020 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 475071 | 01080 | 8.7 | Solar | 05_09_514L1 | 11/10/2022 | 11/17/2022 | 4 | 2 | 2 | 11/18/2022 | 11/18/2022 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 | 11/10/2022 | 4/17/2024 | Y | EXP | 365 | 03/17/2023 | 04/17/2023 | 32 | 0 | 32 |  |  | 7/18/2023 | Connected |  | N
National Grid | UPTON | 177475 | 01568 | 225 | Solar | 05_05_335W3 | 07/06/2016 | 07/06/2016 | 0 | 0 | 0 | 07/07/2016 | 07/07/2016 | 0 | 0 | 0 | 09/06/2016 | 10/04/2016 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  | 10/04/2016 | 20 | 1 | 19 |  |  | 0 | 0 | 0 | 10/28/2016 |  | 2/5/2017 | N | EXP | 1 |  |  | 0 | 0 | 0 | 2/3/2017 | 2/3/2017 | 2/22/2017 | Connected |  | N
National Grid | NORTHAMPTON | 648271 | 01060 | 80 | Solar | 05_09_901W2 | 10/18/2024 | 01/02/2025 | 49 | 39 | 10 | 01/03/2025 | 01/03/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/10/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTBOROUGH | 698560 | 01581 | 6.27 | Solar | 05_05_312W4 | 06/23/2025 | 09/15/2025 | 59 | 55 | 4 | 09/16/2025 | 09/16/2025 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/3/2025 | Connected |  | N
National Grid | ABINGTON | 749114 | 02351 | 11.5 | Solar | 05_07_64J1 | 02/03/2026 | 02/05/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SEEKONK | 712398 | 02771 | 11.136 | Solar | 05_05_7L3 | 08/18/2025 | 09/03/2025 | 2 | 0 | 2 | 09/19/2025 | 09/19/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2025 | 08/18/2025 | 11/3/2026 | Y | EXP | 365 | 12/12/2025 | 12/11/2025 | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | LYNN | 471551 | 01902 | 80 | Solar | 05_12_22W2 | 11/01/2022 | 11/10/2022 | 7 | 0 | 7 | 11/14/2022 | 11/14/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2023 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 178621 | 01257 | 2125 | Solar | 05_09_1108W2 | 02/01/2018 | 02/01/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2018 | 04/17/2018 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 | 02/01/2018 | 3/25/2023 | Y | STD | 322 | 09/06/2019 | 11/03/2021 | 790 | 149 | 641 |  |  | 12/5/2022 | Connected |  | N
National Grid | HANOVER | 637580 | 02339 | 220 | Solar | 05_07_96W40 | 09/05/2024 | 11/07/2024 | 45 | 35 | 10 |  |  | 76 | 57 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HALIFAX | 216496 | 02338 | 201.6 | Solar | 05_07_912W74 | 04/01/2019 | 04/02/2019 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 480347 | 01080 | 7.6 | Battery Add-On | 05_09_514L1 | 11/28/2022 | 12/08/2022 | 9 | 8 | 1 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 178416 | 01757 | 2450 | Solar | 05_05_335W3 | 11/28/2017 | 11/28/2017 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2017 | 01/22/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2018 |  | 4/9/2020 | N | STD | 632 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 691176 | 01060 | 20 | Solar | 05_09_901W2 | 05/13/2025 | 05/20/2025 | 4 | 1 | 3 | 05/21/2025 | 05/21/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 6/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WESTBOROUGH | 699713 | 01581 | 7.6 | Solar | 05_05_312W4 | 06/19/2025 | 07/02/2025 | 5 | 2 | 3 | 07/29/2025 | 07/29/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 | 06/19/2025 | 8/18/2026 | Y | EXP | 365 | 09/13/2025 | 11/05/2025 | 54 | 0 | 54 |  |  | 1/7/2026 | Connected |  | N
National Grid | ABINGTON | 176418 | 02351 | 86.4 | Solar | 05_07_64J1 | 12/03/2015 | 12/03/2015 | 3 | 3 | 0 | 12/08/2015 | 12/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2015 |  | 12/8/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 1/3/2017 | 1/3/2017 | 1/3/2017 | Connected |  | N
National Grid | SEEKONK | 175438 | 02771 | 1000 | Solar | 05_05_7L4 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 12/18/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2015 | 11/24/2014 | 10/1/2027 | Y | STD | 4 | 10/20/2021 |  | 1599 | 1542 | 57 |  |  |  | Construction |  | N
National Grid | LYNN | 479881 | 01902 | 0 | Solar | 05_12_22W2 | 12/02/2022 | 12/07/2022 | 3 | 1 | 2 | 12/08/2022 | 12/08/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 4/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2023 | Connected |  | N
National Grid | SHEFFIELD | 178745 | 01257 | 924 | Solar | 05_09_1108W2 | 05/30/2018 | 07/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/19/2018 | 07/20/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 730114 | 02339 | 12.96 | Solar | 05_07_96W40 | 11/03/2025 |  | 83 | 25 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | HALIFAX | 216492 | 02338 | 201.6 | Solar | 05_07_912W74 | 04/01/2019 | 04/02/2019 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 520289 | 01057 | 12.47 | Solar | 05_09_514L1 | 04/19/2023 | 05/10/2023 | 16 | 13 | 3 | 05/11/2023 | 05/11/2023 | 25 | 7 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 195450 | 01757 | 2450 | Solar | 05_05_335W3 | 11/01/2018 | 12/05/2018 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/08/2019 | 02/05/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 177630 | 01060 | 80.5 | Solar | 05_09_901W2 | 05/23/2017 | 05/23/2017 | 2 | 0 | 2 | 05/26/2017 | 05/26/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 | 05/23/2017 | 5/29/2018 | Y | EXP | 362 | 02/28/2017 | 08/08/2017 | 112 | 0 | 112 |  |  | 5/17/2018 | Connected |  | N
National Grid | WESTBOROUGH | 711356 | 01581 | 13.12 | Solar | 05_05_312W4 | 08/15/2025 | 10/09/2025 | 12 | 10 | 2 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/26/2025 | Connected |  | N
National Grid | ABINGTON | 177292 | 02351 | 20 | Solar | 05_07_64J1 | 08/24/2016 | 08/24/2016 | 2 | 2 | 0 | 08/29/2016 | 08/29/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 417356 | 02771 | 688 | Solar | 05_05_7L4 | 05/18/2022 | 08/23/2022 | 66 | 58 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2022 | 09/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 05/18/2022 | 6/27/2026 | Y | STD | 154 | 10/01/2025 |  | 157 | 131 | 26 |  |  |  | Construction |  | N
National Grid | LYNN | 507161 | 01902 | 4.64 | Solar | 05_12_22W2 | 03/24/2023 | 03/27/2023 | 1 | 0 | 1 | 03/28/2023 | 03/28/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2023 | 03/24/2023 | 7/19/2024 | Y | EXP | 365 | 07/21/2023 | 07/20/2023 | 0 | 0 | 0 |  |  | 7/25/2023 | Connected |  | N
National Grid | SHEFFIELD | 185701 | 01257 | 5000 | Solar | 05_09_1108W2 | 06/25/2018 | 06/25/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2018 | 07/26/2018 | 10 | 8 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 748291 | 02061 | 24.7 | Solar | 05_07_96W40 | 01/29/2026 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | EAST BRIDGEWATER | 216476 | 02333 | 201.6 | Solar | 05_07_912W74 | 04/01/2019 | 04/02/2019 | 1 | 1 | 0 | 04/03/2019 | 04/03/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONSON | 653714 | 01057 | 4990 | Other | 05_09_514L1 | 01/29/2025 |  | 78 | 69 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 207419 | 01568 | 25 | Solar | 05_05_335W3 | 03/04/2019 | 03/05/2019 | 0 | 0 | 0 | 03/06/2019 | 03/06/2019 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2019 | 03/04/2019 | 12/17/2019 | Y | EXP | 272 |  |  | 0 | 0 | 0 |  |  | 7/3/2019 | Connected |  | N
National Grid | NORTHAMPTON | 196403 | 01060 | 72 | Solar | 05_09_901W2 | 09/19/2018 | 09/21/2018 | 1 | 0 | 1 | 09/24/2018 | 09/24/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2018 |  | 2/7/2022 | N | EXP | 493 |  |  | 0 | 0 | 0 |  |  | 1/25/2022 | Connected |  | N
National Grid | WESTBOROUGH | 718516 | 01581 | 15.2 | Solar | 05_05_312W4 | 09/11/2025 | 09/18/2025 | 5 | 0 | 5 | 09/19/2025 | 09/19/2025 | 16 | 1 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2025 |  | 10/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2026 | Connected |  | N
National Grid | ROCKLAND | 177873 | 02370 | 5 | Solar | 05_07_64J1 | 08/14/2017 | 08/14/2017 | 1 | 0 | 1 | 08/16/2017 | 08/16/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 | 08/14/2017 | 8/20/2018 | Y | EXP | 368 | 10/04/2017 | 10/23/2017 | 12 | 0 | 12 | 2/20/2018 | 2/20/2018 | 2/27/2018 | Connected |  | N
National Grid | REHOBOTH | 477446 | 02769 | 6000 | Solar | 05_05_7L4 | 03/09/2023 | 05/03/2023 | 39 | 31 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/04/2023 | 06/01/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SWAMPSCOTT | 527219 | 01907 | 19.43 | Solar | 05_12_22W2 | 06/07/2023 | 06/28/2023 | 13 | 13 | 0 | 06/29/2023 | 06/29/2023 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2023 |  | 7/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/14/2023 | Connected |  | N
National Grid | SHEFFIELD | 249462 | 01257 | 18 | Solar | 05_09_1108W2 | 09/27/2019 | 12/05/2019 | 45 | 41 | 4 | 12/06/2019 | 12/06/2019 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2020 |  | 8/15/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 174256 | 02061 | 135 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | EXP |  |  |  | 0 | 0 | 0 | 9/13/2012 | 9/13/2012 |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 239925 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | PALMER | 655248 | 01080 | 10 | Solar | 05_09_514L1 | 11/19/2024 | 12/04/2024 | 2 | 0 | 2 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 | 11/19/2024 | 1/22/2026 | Y | EXP | 365 | 05/30/2025 | 06/06/2025 | 8 | 0 | 8 |  |  | 10/10/2025 | Connected |  | N
National Grid | UPTON | 213781 | 01568 | 0 | Solar | 05_05_335W3 | 03/14/2019 | 03/21/2019 | 4 | 0 | 4 | 03/22/2019 | 03/22/2019 | 143 | 140 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 11/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | NORTHAMPTON | 277573 | 01060 | 0 | Solar | 05_09_901W2 | 01/31/2020 | 02/14/2020 | 10 | 9 | 1 | 02/18/2020 | 02/18/2020 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2020 |  | 2/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2020 | Connected |  | N
National Grid | WESTBOROUGH | 679646 | 01581 | 0 | Other | 05_05_312W5 | 10/08/2025 | 11/20/2025 | 29 | 19 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 12/17/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | ABINGTON | 281952 | 02351 | 8.12 | Solar | 05_07_65J1 | 03/02/2020 | 03/03/2020 | 0 | 0 | 0 | 03/04/2020 | 03/04/2020 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 |  | 3/2/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/14/2020 | Connected |  | N
National Grid | REHOBOTH | 694249 | 02769 | 11.02 | Solar | 05_05_7L4 | 06/06/2025 | 08/11/2025 | 6 | 2 | 4 | 08/12/2025 | 08/12/2025 | 27 | 12 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 536831 | 01902 | 6 | Solar | 05_12_22W2 | 07/14/2023 | 07/17/2023 | 1 | 0 | 1 | 07/18/2023 | 07/18/2023 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2024 | Connected |  | N
National Grid | NEW MARLBOROUGH | 500745 | 01244 | 11.89 | Solar | 05_09_1108W2 | 05/24/2023 | 07/27/2023 | 42 | 33 | 9 | 07/28/2023 | 07/28/2023 | 77 | 59 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 12/25/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2024 | Connected |  | N
National Grid | NORWELL | 174255 | 02061 | 50 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 7/1/2012 | N | EXP | 164 |  |  | 0 | 0 | 0 | 7/3/2013 | 7/3/2013 | 7/24/2013 | Connected |  | N
National Grid | EAST BRIDGEWATER | 239915 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | PALMER | 693508 | 01069 | 16.34 | Solar | 05_09_514L1 | 06/02/2025 | 06/11/2025 | 6 | 2 | 4 | 06/12/2025 | 06/12/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | UPTON | 212788 | 01568 | 109.9 | Solar | 05_05_335W3 | 03/06/2019 | 03/12/2019 | 4 | 1 | 3 | 03/13/2019 | 03/13/2019 | 6 | 0 | 6 | 04/04/2019 | 08/27/2019 | 102 | 62 | 40 |  |  | 0 | 0 | 0 |  | 08/27/2019 | 102 | 62 | 40 |  |  | 0 | 0 | 0 | 9/12/2019 | 03/06/2019 | 4/14/2021 | Y | EXP | 266 | 02/12/2020 | 08/14/2020 | 184 | 0 | 184 |  |  | 4/14/2021 | Connected |  | N
National Grid | NORTHAMPTON | 590297 | 01060 | 60 | Solar | 05_09_901W2 | 02/20/2024 |  | 46 | 37 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 174692 | 01581 | 4000 |  | 05_05_312W5 | 10/26/2010 | 10/26/2010 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 663732 | 02351 | 2.66 | Solar | 05_07_65J1 | 01/03/2025 | 01/15/2025 | 6 | 0 | 6 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2025 |  | 3/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | SEEKONK | 718894 | 02771 | 22.8 | Solar | 05_05_7L4 | 10/05/2025 | 10/21/2025 | 11 | 9 | 2 | 10/22/2025 | 10/22/2025 | 92 | 25 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 550854 | 01902 | 6 | Solar | 05_12_22W2 | 09/06/2023 | 09/25/2023 | 14 | 13 | 1 | 09/26/2023 | 09/26/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2023 |  | 11/29/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/5/2024 | Connected |  | N
National Grid | SHEFFIELD | 528587 | 01222 | 15.2 | Solar | 05_09_1108W2 | 05/23/2023 | 05/26/2023 | 3 | 0 | 3 | 05/30/2023 | 05/30/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 |  | 8/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | Y
National Grid | NORWELL | 174584 | 02061 | 200 | Solar | 05_07_96W40 | 11/14/2011 | 11/14/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2012 |  | 6/1/2012 | N | EXP | 98 |  |  | 0 | 0 | 0 | 5/31/2012 | 5/31/2012 | 6/1/2012 | Connected |  | N
National Grid | EAST BRIDGEWATER | 239903 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | PALMER | 700089 | 01069 | 996 | Solar | 05_09_516L1 | 08/11/2025 | 08/29/2025 | 14 | 3 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/02/2025 | 09/22/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | UPTON | 212698 | 01568 | 7.6 | Solar | 05_05_335W3 | 11/04/2019 | 11/25/2019 | 13 | 13 | 0 | 11/26/2019 | 11/26/2019 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2019 | 11/04/2019 | 2/18/2021 | Y | EXP | 365 | 05/16/2020 | 06/02/2020 | 17 | 0 | 17 |  |  | 10/20/2020 | Connected |  | N
National Grid | NORTHAMPTON | 687294 | 01060 | 7.6 | Solar | 05_09_901W2 | 04/24/2025 | 05/27/2025 | 1 | 0 | 1 | 06/03/2025 | 06/03/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2025 | Connected |  | N
National Grid | WESTBOROUGH | 174886 | 01581 | 1500 | Solar | 05_05_312W5 | 02/21/2013 | 02/21/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/05/2013 | 04/05/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2013 |  | 8/30/2013 | N | STD | 18 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SCITUATE | 726671 | 02066 | 7.04 | Solar | 05_07_65J1 | 10/17/2025 | 10/30/2025 | 2 | 1 | 1 | 10/31/2025 | 10/31/2025 | 25 | 9 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 736345 | 02769 | 7.6 | Solar | 05_05_7L4 | 11/25/2025 | 12/02/2025 | 4 | 0 | 4 | 12/03/2025 | 12/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2026 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | LYNN | 552910 | 01902 | 14.04 | Solar | 05_12_22W2 | 10/25/2023 | 10/31/2023 | 4 | 1 | 3 | 11/01/2023 | 11/01/2023 | 56 | 32 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 629711 | 01222 | 5.584 | Solar | 05_09_1108W2 | 08/02/2024 | 08/05/2024 | 1 | 0 | 1 | 08/06/2024 | 08/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2024 |  | 9/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 174839 | 02061 | 260 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 2 | 0 | 2 | 04/04/2012 | 04/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/13/2012 |  | 9/11/2012 | N | EXP | 2 |  |  | 0 | 0 | 0 | 9/13/2012 | 9/13/2012 | 8/6/2013 | Connected |  | N
National Grid | EAST BRIDGEWATER | 239897 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | MONSON | 713222 | 01057 | 22.9 | Solar | 05_09_516L1 | 08/25/2025 | 09/15/2025 | 14 | 10 | 4 | 09/16/2025 | 09/16/2025 | 116 | 63 | 53 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 310848 | 01757 | 11.4 | Solar | 05_05_335W3 | 09/04/2020 | 09/10/2020 | 2 | 0 | 2 | 09/11/2020 | 09/11/2020 | 39 | 0 | 39 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 |  | 8/2/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 687680 | 01060 | 7.6 | Solar | 05_09_901W3 | 04/25/2025 | 06/09/2025 | 3 | 0 | 3 | 07/02/2025 | 07/02/2025 | 22 | 9 | 13 | 08/11/2025 | 11/13/2025 | 66 | 42 | 24 |  |  | 0 | 0 | 0 |  | 11/13/2025 | 66 | 42 | 24 |  |  | 0 | 0 | 0 | 11/17/2025 |  | 11/25/2026 | N | EXP | 365 | 02/13/2026 |  | 22 | 0 | 22 |  |  |  | Construction |  | Y
National Grid | WESTBOROUGH | 175128 | 01581 | 750 | Solar | 05_05_312W5 | 07/27/2011 | 07/27/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/24/2011 | 01/23/2013 | 335 | 0 | 335 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2012 | 07/27/2011 | 12/31/2012 | Y | STD | 116 | 03/05/2013 | 04/22/2013 | 29 | 0 | 29 | 6/12/2013 | 6/12/2013 | 7/11/2013 | Connected |  | N
National Grid | COHASSET | 545216 | 02025 | 15.2 | Solar | 05_07_67J1 | 08/01/2023 | 08/02/2023 | 1 | 0 | 1 | 08/03/2023 | 08/03/2023 | 138 | 109 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 4/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | REHOBOTH | 741491 | 02769 | 3.8 | Solar | 05_05_7L4 | 12/19/2025 | 12/23/2025 | 4 | 0 | 4 | 01/28/2026 | 01/28/2026 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/2/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | LYNN | 579935 | 01902 | 7.6 | Solar | 05_12_22W2 | 12/29/2023 | 01/12/2024 | 9 | 7 | 2 | 01/16/2024 | 01/16/2024 | 48 | 28 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 8/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | SHEFFIELD | 646374 | 01257 | 4980 | Solar | 05_09_1108W2 | 11/15/2024 | 12/11/2024 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 01/13/2025 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 174920 | 02061 | 2000 | Solar | 05_07_96W40 | 02/26/2013 | 02/26/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/08/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 239889 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | BRIMFIELD | 714430 | 01010 | 15.58 | Solar | 05_09_516L1 | 08/25/2025 | 08/29/2025 | 4 | 1 | 3 | 09/02/2025 | 09/02/2025 | 18 | 3 | 15 | 10/20/2025 | 10/27/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  | 10/27/2025 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/17/2026 | N | EXP | 365 | 03/05/2026 |  | 2 | 0 | 2 |  |  |  | Construction |  | N
National Grid | MILFORD | 334895 | 01757 | 3.8 | Solar | 05_05_335W3 | 01/05/2021 | 01/06/2021 | 1 | 1 | 0 | 01/07/2021 | 01/07/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2021 | 01/05/2021 | 1/5/2022 | Y | EXP | 365 | 04/21/2021 | 06/02/2021 | 42 | 0 | 42 |  |  | 6/16/2021 | Connected |  | N
National Grid | NORTHAMPTON | 743867 | 01060 | 13.3 | Solar | 05_09_901W3 | 01/07/2026 | 01/21/2026 | 2 | 0 | 2 | 02/13/2026 | 02/13/2026 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 176007 | 01581 | 857.1 | Solar | 05_05_312W5 | 08/12/2015 | 08/12/2015 | 2 | 2 | 0 | 08/20/2015 | 08/20/2015 | 42 | 15 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 606410 | 02025 | 0 | Battery Add-On | 05_07_67J1 | 04/24/2024 |  | 9 | 7 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 744311 | 02769 | 45 | Solar | 05_05_7L4 | 02/03/2026 | 02/23/2026 | 13 | 8 | 5 | 02/24/2026 | 02/24/2026 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 589445 | 01902 | 8.99 | Solar | 05_12_22W2 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 8 | 0 | 8 | 04/30/2024 | 02/21/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  | 02/21/2025 | 26 | 0 | 26 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 7/1/2025 | N | EXP | 365 | 08/20/2024 | 03/03/2025 | 196 | 0 | 196 |  |  | 3/11/2025 | Connected |  | N
National Grid | SHEFFIELD | 663203 | 01257 | 7.6 | Solar | 05_09_1108W2 | 12/31/2024 | 02/10/2025 | 4 | 0 | 4 | 02/11/2025 | 02/11/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 12/31/2024 | 4/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2025 | Connected |  | N
National Grid | NORWELL | 175057 | 02061 | 135 | Solar | 05_07_96W40 | 02/28/2012 | 02/28/2012 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2012 |  | 11/23/2012 | N | EXP | 37 |  |  | 0 | 0 | 0 | 10/18/2012 | 10/18/2012 | 8/15/2013 | Connected |  | N
National Grid | EAST BRIDGEWATER | 239881 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | BRIMFIELD | 724205 | 01010 | 2000 | Solar | 05_09_516L1 | 12/02/2025 | 01/05/2026 | 22 | 13 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2026 | 01/26/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 337021 | 01757 | 7.6 | Solar | 05_05_335W3 | 02/17/2021 | 05/04/2021 | 52 | 47 | 5 | 05/05/2021 | 05/05/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2021 |  | 10/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 747411 | 01062 | 37.6 | Solar | 05_09_901W3 | 01/26/2026 | 01/28/2026 | 2 | 0 | 2 | 01/29/2026 | 01/29/2026 | 18 | 1 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Supplemental Review |  | N
National Grid | WESTBOROUGH | 176852 | 01581 | 60.42 | Solar | 05_05_312W5 | 11/11/2015 | 11/11/2015 | 1 | 1 | 0 | 11/16/2015 | 11/16/2015 | 267 | 0 | 267 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2015 |  | 11/18/2016 | N | EXP | 367 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ABINGTON | 685332 | 02351 | 5.76 | Solar | 05_07_67J1 | 04/15/2025 | 05/02/2025 | 27 | 20 | 7 | 07/15/2025 | 07/15/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 | 04/15/2025 | 9/2/2026 | Y | EXP | 365 | 11/22/2025 | 01/06/2026 | 46 | 0 | 46 |  |  | 1/8/2026 | Connected |  | N
National Grid | SEEKONK | 751511 | 02771 | 15.76 | Solar | 05_05_7L4 | 02/17/2026 | 02/18/2026 | 1 | 0 | 1 | 02/19/2026 | 02/19/2026 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | LYNN | 589414 | 01902 | 5.76 | Solar | 05_12_22W2 | 02/21/2024 | 02/26/2024 | 3 | 0 | 3 | 02/27/2024 | 02/27/2024 | 5 | 1 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 |  | 6/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | NEW MARLBOROUGH | 704626 | 01230 | 10.47 | Solar | 05_09_1108W2 | 07/23/2025 | 09/15/2025 | 37 | 34 | 3 | 09/16/2025 | 09/16/2025 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2025 |  | 11/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | NORWELL | 176574 | 02061 | 57.6 | Solar | 05_07_96W40 | 02/11/2016 | 02/11/2016 | 1 | 1 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2016 |  | 2/17/2017 | N | EXP | 366 |  |  | 0 | 0 | 0 | 11/29/2016 | 11/29/2016 | 12/1/2016 | Connected |  | N
National Grid | EAST BRIDGEWATER | 239875 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 2 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | BRIMFIELD | 745050 | 01010 | 11.5 | Solar | 05_09_516L1 | 01/14/2026 | 01/26/2026 | 5 | 1 | 4 | 02/17/2026 | 02/17/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | UPTON | 345013 | 01568 | 15.12 | Solar | 05_05_335W3 | 03/04/2021 | 03/08/2021 | 1 | 1 | 0 | 03/09/2021 | 03/09/2021 | 20 | 6 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 03/04/2021 | 3/8/2022 | Y | EXP | 365 | 04/22/2021 | 05/26/2021 | 34 | 0 | 34 |  |  | 5/28/2021 | Connected |  | Y
National Grid | NORTHAMPTON | 174610 | 01062 | 22 | Solar | 05_09_901W3 | 10/19/2010 | 10/19/2010 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2010 |  | 1/3/2012 | N | EXP |  |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 1/3/2012 | Connected |  | N
National Grid | WESTBOROUGH | 177275 | 01581 | 4500 | Solar | 05_05_312W5 | 02/06/2017 | 02/06/2017 | 14 | 13 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2017 | 03/02/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/15/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ABINGTON | 736133 | 02351 | 5.76 | Solar | 05_07_69J1 | 11/24/2025 | 11/25/2025 | 3 | 0 | 3 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 | 11/24/2025 | 2/4/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | REHOBOTH | 754964 | 02769 | 23 | Solar | 05_05_7L4 | 03/06/2026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | LYNN | 594697 | 01902 | 6 | Solar | 05_12_22W2 | 03/07/2024 | 03/14/2024 | 5 | 0 | 5 | 03/15/2024 | 03/15/2024 | 5 | 0 | 5 | 05/14/2024 | 06/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 06/05/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 10/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 714255 | 01230 | 22.8 | Solar | 05_09_1108W2 | 09/02/2025 | 09/08/2025 | 3 | 1 | 2 | 09/09/2025 | 09/09/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/8/2025 | Connected |  | N
National Grid | NORWELL | 178356 | 02061 | 358.4 | Solar | 05_07_96W40 | 02/28/2018 | 02/28/2018 | 7 | 0 | 7 | 03/12/2018 | 03/12/2018 | 121 | 17 | 104 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2018 |  | 3/6/2020 | N | EXP | 555 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 239862 | 02333 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | BRIMFIELD | 387138 | 01010 | 0 | Other | 05_05_335W3 | 11/10/2021 | 12/28/2021 | 32 | 24 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/06/2022 | 11/21/2022 | 219 | 211 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 175153 | 01757 | 40 | Solar | 05_09_901W3 | 11/05/2013 | 11/05/2013 | 5 | 0 | 5 | 11/14/2013 | 11/14/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2013 |  | 12/31/2013 | N | EXP | 29 |  |  | 0 | 0 | 0 | 12/9/2013 | 12/9/2013 | 2/28/2014 | Connected |  | N
National Grid | NORTHAMPTON | 177676 | 01060 | 56 | Solar | 05_05_312W5 | 07/21/2017 | 07/21/2017 | 8 | 4 | 4 | 08/03/2017 | 08/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2017 |  | 7/29/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/27/2017 | 12/27/2017 | 12/27/2017 | Connected |  | N
National Grid | WESTBOROUGH | 739310 | 01581 | 11.4 | Solar | 05_07_69J1 | 12/10/2025 | 12/11/2025 | 1 | 0 | 1 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ABINGTON | 174438 | 02351 | 1000 | Solar | 05_05_7L4 | 06/29/2012 | 06/29/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2012 | 08/22/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 602059 | 02769 | 11.6 | Solar | 05_12_22W2 | 04/09/2024 | 04/10/2024 | 1 | 0 | 1 | 04/11/2024 | 04/11/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2024 | 04/09/2024 | 5/29/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 719400 | 01902 | 15.2 | Solar | 05_09_1108W2 | 09/16/2025 | 09/25/2025 | 5 | 1 | 4 | 09/26/2025 | 09/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2025 |  | 2/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/10/2026 | Connected |  | N
National Grid | GREAT BARRINGTON | 178643 | 01230 | 153.2 | Solar | 05_07_96W40 | 12/15/2017 | 12/15/2017 | 31 | 21 | 10 | 02/01/2018 | 02/01/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2018 |  | 12/20/2018 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | ROCKLAND | 239842 | 02370 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 749039 | 02333 | 15.2 | Solar | 05_09_516L1 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | BRIMFIELD | 391814 | 01010 | 1.74 | Solar | 05_05_335W3 | 11/09/2021 | 11/17/2021 | 5 | 4 | 1 | 11/18/2021 | 11/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 5/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2022 | Connected |  | N
National Grid | UPTON | 175539 | 01568 | 0 | Solar | 05_09_901W3 | 12/04/2014 | 12/04/2014 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2014 | 01/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 222837 | 01062 | 144 | Solar | 05_05_312W5 | 04/26/2019 | 06/14/2019 | 22 | 15 | 7 | 06/17/2019 | 06/17/2019 | 5 | 0 | 5 | 07/19/2019 | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  | 09/19/2019 | 44 | 26 | 18 |  |  | 0 | 0 | 0 | 2/26/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 176650 | 01581 | 3 | Solar | 05_07_69J1 | 02/17/2016 | 02/17/2016 | 2 | 2 | 0 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2016 | 02/17/2016 | 2/23/2017 | Y | EXP | 331 | 08/04/2016 | 08/30/2016 | 18 | 0 | 18 | 12/28/2016 | 12/28/2016 | 1/3/2017 | Connected |  | N
National Grid | BROCKTON | 174439 | 02302 | 1000 | Solar | 05_05_7L4 | 06/29/2012 | 06/29/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/13/2012 | 08/22/2012 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/12/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 619036 | 02769 | 10 | Solar | 05_12_22W2 | 06/19/2024 | 06/28/2024 | 3 | 2 | 1 | 07/01/2024 | 07/01/2024 | 28 | 15 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2024 | 06/19/2024 | 8/13/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2025 | Connected |  | N
National Grid | LYNN | 698890 | 01902 | 2250 | Solar | 05_09_1109W1 | 10/23/2025 |  | 53 | 50 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SHEFFIELD | 178649 | 01257 | 72 | Solar | 05_07_96W40 | 12/15/2017 | 12/15/2017 | 23 | 14 | 9 | 01/23/2018 | 01/23/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2018 |  | 12/23/2018 | N | EXP | 333 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | NORWELL | 239819 | 02061 | 22.8 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 754595 | 02333 | 11.4 | Solar | 05_09_516L1 | 03/04/2026 |  | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | BRIMFIELD | 393123 | 01010 | 4990 | Other | 05_05_335W3 | 12/17/2021 | 01/25/2022 | 26 | 17 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2022 | 11/22/2022 | 208 | 201 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 175749 | 01757 | 11.8 | Solar | 05_09_901W3 | 10/30/2014 | 10/30/2014 | 6 | 0 | 6 | 11/10/2014 | 11/10/2014 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 287647 | 01060 | 616 | Solar | 05_05_312W5 | 04/24/2020 | 05/06/2020 | 8 | 3 | 5 |  |  | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2021 |  | 8/24/2022 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 191411 | 01581 | 7.6 | Solar | 05_07_69J1 | 07/20/2018 | 10/05/2018 | 278 | 0 | 278 | 10/11/2018 | 10/11/2018 | 48 | 40 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175437 | 02302 | 1000 | Solar | 05_05_7L4 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 12/18/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2015 |  | 8/30/2016 | N | STD | 382 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 623165 | 02769 | 5.76 | Solar | 05_12_22W2 | 07/08/2024 | 07/16/2024 | 1 | 0 | 1 | 07/17/2024 | 07/17/2024 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 697839 | 01902 | 450 | Solar | 05_09_1109W1 | 09/22/2025 |  | 74 | 70 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | SHEFFIELD | 220756 | 01222 | 105.6 | Solar | 05_07_96W40 | 05/16/2019 | 05/31/2019 | 10 | 1 | 9 | 06/03/2019 | 06/03/2019 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2019 |  | 12/31/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2020 | Connected |  | N
National Grid | NORWELL | 239807 | 02061 | 45.6 | Solar | 05_07_912W74 | 06/25/2019 | 06/29/2019 | 3 | 1 | 2 |  |  | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2019 |  | 5/31/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  | 5/19/2021 | Connected |  | N
National Grid | EAST BRIDGEWATER | 174497 | 02333 | 1000 | Solar | 05_09_516L1 | 07/27/2012 | 07/27/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 10/18/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 411189 | 01521 | 5 | Solar | 05_05_335W3 | 02/10/2022 | 02/22/2022 | 7 | 4 | 3 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 175814 | 01568 | 7.6 | Solar | 05_09_901W3 | 05/18/2015 | 05/18/2015 | 4 | 4 | 0 | 05/28/2015 | 05/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2015 |  | 10/30/2015 | N | EXP | 134 |  |  | 0 | 0 | 0 | 9/10/2015 | 9/10/2015 | 9/10/2015 | Connected |  | N
National Grid | NORTHAMPTON | 287637 | 01062 | 200 | Solar | 05_05_312W5 | 04/13/2020 | 04/17/2020 | 3 | 0 | 3 |  |  | 12 | 1 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2021 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 203334 | 01581 | 3.8 | Solar | 05_07_69J1 | 12/19/2018 | 12/21/2018 | 1 | 0 | 1 | 12/24/2018 | 12/24/2018 | 314 | 0 | 314 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2019 |  | 12/19/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 175433 | 02302 | 1000 | Solar | 05_05_7L4 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 12/18/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 632320 | 02769 | 3.8 | Solar | 05_12_22W2 | 08/14/2024 |  | 27 | 25 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 716992 | 01902 | 4.94 | Solar | 05_09_1109W1 | 10/07/2025 | 10/09/2025 | 2 | 0 | 2 | 10/10/2025 | 10/10/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | MONTEREY | 256924 | 01245 | 24 | Solar | 05_07_96W40 | 11/08/2019 | 11/14/2019 | 2 | 1 | 1 | 11/15/2019 | 11/15/2019 | 47 | 31 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 265791 | 02061 | 10 | Solar | 05_07_912W74 | 11/15/2019 | 11/19/2019 | 2 | 2 | 0 | 11/20/2019 | 11/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2019 |  | 11/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2020 | Connected |  | Y
National Grid | EAST BRIDGEWATER | 174496 | 02333 | 3000 | Solar | 05_09_516L1 | 07/27/2012 | 07/27/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 10/18/2012 | 48 | 0 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2013 | 07/27/2012 | 7/1/2013 | Y | STD | 42 |  |  | 0 | 0 | 0 | 6/19/2014 | 6/19/2014 | 6/19/2014 | Connected |  | N
National Grid | HOLLAND | 417539 | 01521 | 7.6 | Solar | 05_05_335W3 | 01/27/2023 | 03/18/2022 | 1 | 0 | 1 | 01/31/2023 | 01/31/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 01/27/2023 | 6/21/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2023 | Connected |  | Y
National Grid | HOPEDALE | 177682 | 01747 | 90 | Solar | 05_09_901W3 | 07/25/2017 | 07/25/2017 | 7 | 6 | 1 | 08/04/2017 | 08/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 7/31/2018 | N | EXP | 337 |  |  | 0 | 0 | 0 | 3/2/2018 | 3/2/2018 | 3/22/2018 | Connected |  | N
National Grid | NORTHAMPTON | 293197 | 01060 | 7.6 | Solar | 05_05_312W5 | 05/22/2020 |  | 38 | 38 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 369999 | 01581 | 7.6 | Solar | 05_07_69J1 | 07/15/2021 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 175609 | 02302 | 812 | Solar | 05_05_7L4 | 10/17/2014 | 10/17/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2014 | 11/24/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2015 | 10/17/2014 | 3/15/2016 | Y | STD | 334 | 08/12/2016 | 12/20/2016 | 88 | 0 | 88 | 12/28/2016 | 12/28/2016 | 12/28/2016 | Connected |  | N
National Grid | REHOBOTH | 634846 | 02769 | 10 | Solar | 05_12_22W2 | 08/23/2024 | 08/28/2024 | 2 | 0 | 2 | 08/29/2024 | 08/29/2024 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  | 11/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2025 | Connected |  | N
National Grid | LYNN | 728857 | 01902 | 0 | Solar | 05_09_1109W1 | 10/31/2025 | 11/12/2025 | 6 | 4 | 2 | 11/13/2025 | 11/13/2025 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2025 |  | 12/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MONTEREY | 258675 | 01245 | 24 | Solar | 05_07_96W40 | 11/08/2019 | 11/14/2019 | 2 | 1 | 1 | 11/15/2019 | 11/15/2019 | 47 | 34 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 342566 | 02061 | 9.8 | Solar | 05_07_912W74 | 02/26/2021 | 03/08/2021 | 5 | 0 | 5 | 03/09/2021 | 03/09/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 | 02/26/2021 | 12/29/2022 | Y | EXP | 365 | 03/09/2022 | 05/02/2022 | 55 | 0 | 55 |  |  | 11/17/2022 | Connected |  | N
National Grid | EAST BRIDGEWATER | 174495 | 02333 | 1000 | Solar | 05_09_516L1 | 07/27/2012 | 07/27/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 01/16/2013 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 416720 | 01010 | 7.6 | Solar | 05_05_335W3 | 03/15/2022 | 03/17/2022 | 2 | 0 | 2 | 03/18/2022 | 03/18/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2022 | 03/15/2022 |  | Y | EXP | 365 | 01/07/2023 | 02/25/2023 | 50 | 0 | 50 |  |  | 3/8/2023 | Connected |  | N
National Grid | MILFORD | 228970 | 01757 | 303.4 | Solar | 05_09_901W3 | 06/04/2019 | 06/14/2019 | 8 | 6 | 2 | 06/17/2019 | 06/17/2019 | 740 | 415 | 325 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 300962 | 01060 | 3.8 | Solar | 05_05_312W5 | 07/13/2020 | 12/14/2021 | 299 | 114 | 185 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  | 6/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 471403 | 01581 | 6.144 | Solar | 05_07_69J1 | 01/11/2023 | 01/13/2023 | 2 | 0 | 2 | 01/17/2023 | 01/17/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 176622 | 02302 | 10 | Solar | 05_05_7L4 | 04/12/2016 | 04/12/2016 | 1 | 1 | 0 | 04/14/2016 | 04/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/12/2016 | 4/18/2017 | Y | EXP | 357 | 08/11/2016 | 09/06/2016 | 17 | 0 | 17 | 11/10/2016 | 11/10/2016 | 11/14/2016 | Connected |  | N
National Grid | REHOBOTH | 634799 | 02769 | 7.6 | Solar | 05_12_22W2 | 08/22/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 10/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2025 | Connected |  | N
National Grid | LYNN | 736243 | 01902 | 15.3 | Solar | 05_09_1109W1 | 12/11/2025 | 12/16/2025 | 3 | 1 | 2 | 12/17/2025 | 12/17/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 262162 | 01230 | 100 | Solar | 05_07_96W40 | 11/21/2019 | 12/09/2019 | 11 | 5 | 6 | 12/10/2019 | 12/10/2019 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 | 11/21/2019 | 8/25/2022 | Y | EXP | 365 | 07/21/2020 | 07/26/2022 | 736 | 348 | 388 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 385956 | 02061 | 265.35 | Solar | 05_07_912W74 | 12/03/2021 | 02/25/2022 | 58 | 49 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 12/03/2021 | 11/15/2024 | Y | STD | 434 | 02/17/2024 | 09/05/2024 | 202 | 0 | 202 |  |  | 11/13/2024 | Connected |  | N
National Grid | BRIDGEWATER | 174494 | 02324 | 2000 | Solar | 05_09_516L1 | 07/27/2012 | 07/27/2012 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2012 | 01/16/2013 | 93 | 0 | 93 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 427132 | 01010 | 5.376 | Solar | 05_05_335W3 | 04/29/2022 | 05/05/2022 | 5 | 2 | 3 | 05/06/2022 | 05/06/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2022 |  | 6/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/16/2023 | Connected |  | N
National Grid | UPTON | 250724 | 01568 | 10 | Solar | 05_09_901W3 | 08/26/2019 | 09/03/2019 | 4 | 0 | 4 | 09/04/2019 | 09/04/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/23/2019 | Connected |  | N
National Grid | NORTHAMPTON | 697790 | 01060 | 3.84 | Solar | 05_05_312W5 | 06/19/2025 | 07/07/2025 | 4 | 0 | 4 | 07/30/2025 | 07/30/2025 | 43 | 28 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | WESTBOROUGH | 494808 | 01581 | 9.86 | Solar | 05_07_69J1 | 03/31/2023 | 04/03/2023 | 1 | 0 | 1 | 04/04/2023 | 04/04/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177021 | 02302 | 3.8 | Solar | 05_05_7L4 | 01/09/2017 | 01/09/2017 | 5 | 5 | 0 | 01/18/2017 | 01/18/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2017 |  | 1/15/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/6/2017 | 9/6/2017 | 9/6/2017 | Connected |  | N
National Grid | REHOBOTH | 634484 | 02769 | 11.05 | Solar | 05_12_22W2 | 08/21/2024 |  | 41 | 41 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 736815 | 01902 | 5.76 | Solar | 05_09_1109W1 | 11/27/2025 | 12/01/2025 | 1 | 0 | 1 | 01/28/2026 | 01/28/2026 | 27 | 13 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MONTEREY | 262160 | 01245 | 24 | Solar | 05_07_96W40 | 11/21/2019 | 12/09/2019 | 11 | 5 | 6 | 12/10/2019 | 12/10/2019 | 32 | 9 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 11/21/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 399833 | 02061 | 131.66 | Solar | 05_07_912W74 | 12/16/2021 | 01/28/2022 | 30 | 23 | 7 |  |  | 44 | 20 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 12/16/2021 | 11/15/2024 | Y | STD | 434 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N
National Grid | BRIDGEWATER | 174909 | 02324 | 3000 | Solar | 05_09_516L1 | 09/17/2012 | 09/17/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/27/2012 | 01/29/2013 | 67 | 0 | 67 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 438977 | 01521 | 15.2 | Solar | 05_05_335W3 | 06/21/2022 | 06/23/2022 | 2 | 0 | 2 | 06/24/2022 | 06/24/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2022 |  | 8/2/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/10/2022 | Connected |  | N
National Grid | HOPEDALE | 281120 | 01747 | 3 | Solar | 05_09_901W3 | 04/08/2020 | 04/10/2020 | 1 | 1 | 0 | 04/13/2020 | 04/13/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 | 04/08/2020 | 4/9/2021 | Y | EXP | 365 | 08/29/2020 | 09/09/2020 | 11 | 0 | 11 |  |  | 12/14/2020 | Connected |  | N
National Grid | NORTHAMPTON | 737224 | 01060 | 3.8 | Solar | 05_05_313W1 | 12/01/2025 | 01/12/2026 | 2 | 0 | 2 | 01/13/2026 | 01/13/2026 | 36 | 22 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 505549 | 01581 | 7.6 | Solar | 05_07_69J1 | 03/15/2023 | 03/20/2023 | 3 | 0 | 3 | 03/21/2023 | 03/21/2023 | 58 | 38 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2023 | 03/15/2023 | 9/16/2024 | Y | EXP | 365 | 02/02/2024 | 02/12/2024 | 11 | 0 | 11 |  |  | 5/30/2024 | Connected |  | N
National Grid | BROCKTON | 177020 | 02302 | 15.2 | Solar | 05_05_7L4 | 01/09/2017 | 01/09/2017 | 4 | 4 | 0 | 01/17/2017 | 01/17/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2017 |  | 1/15/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 8/15/2017 | 8/15/2017 | 8/21/2017 | Connected |  | N
National Grid | REHOBOTH | 635909 | 02769 | 6 | Solar | 05_12_22W2 | 08/28/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 739922 | 01902 | 23 | Solar | 05_09_1109W1 | 12/15/2025 | 12/16/2025 | 1 | 0 | 1 | 12/17/2025 | 12/17/2025 | 37 | 19 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/24/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 317863 | 01230 | 162.5 | Solar | 05_07_96W40 | 11/16/2020 | 12/02/2020 | 11 | 6 | 5 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 | 11/16/2020 | 9/5/2022 | Y | EXP | 365 | 10/23/2021 | 01/25/2022 | 95 | 0 | 95 |  |  | 7/27/2022 | Connected |  | N
National Grid | NORWELL | 554874 | 02061 | 7.54 | Solar | 05_07_912W74 | 11/15/2023 | 12/12/2023 | 19 | 17 | 2 | 12/13/2023 | 12/13/2023 | 35 | 13 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 2/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2024 | Connected |  | N
National Grid | BRIDGEWATER | 175032 | 02324 | 2000 | Solar | 05_09_516L1 | 03/22/2013 | 03/22/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/03/2013 | 05/14/2013 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2013 | 03/22/2013 | 7/1/2014 | Y | STD | 312 |  |  | 0 | 0 | 0 | 6/19/2014 | 6/19/2014 | 6/19/2014 | Connected |  | N
National Grid | HOLLAND | 447435 | 01521 | 15 | Solar | 05_05_335W3 | 09/16/2022 | 09/19/2022 | 1 | 0 | 1 | 09/20/2022 | 09/20/2022 | 21 | 2 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 09/16/2022 | 12/22/2023 | Y | EXP | 365 | 02/09/2023 | 03/08/2023 | 28 | 0 | 28 |  |  | 3/11/2023 | Connected |  | N
National Grid | UPTON | 312372 | 01568 | 57.6 | Solar | 05_09_901W3 | 09/14/2020 | 01/07/2022 | 1 | 0 | 1 | 09/17/2020 | 09/17/2020 | 59 | 37 | 22 | 12/28/2020 | 02/18/2021 | 35 | 0 | 35 |  |  | 0 | 0 | 0 |  | 02/18/2021 | 35 | 0 | 35 |  |  | 0 | 0 | 0 | 2/23/2021 |  | 7/22/2022 | N | EXP | 495 |  |  | 0 | 0 | 0 |  |  | 6/3/2022 | Connected |  | N
National Grid | NORTHAMPTON | 176924 | 01062 | 28 | Solar | 05_05_313W1 | 11/19/2015 | 11/19/2015 | 3 | 3 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2015 |  | 11/24/2016 | N | EXP | 36 |  |  | 0 | 0 | 0 | 5/26/2016 | 5/26/2016 | 7/6/2016 | Connected |  | N
National Grid | WESTBOROUGH | 519664 | 01581 | 6 | Solar | 05_07_69J1 | 05/01/2023 | 05/02/2023 | 1 | 0 | 1 | 05/03/2023 | 05/03/2023 | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177290 | 02302 | 10 | Solar | 05_05_7L4 | 06/17/2016 | 06/17/2016 | 1 | 1 | 0 | 06/21/2016 | 06/21/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2016 | 06/17/2016 | 6/25/2017 | Y | EXP | 361 | 09/28/2016 | 10/05/2016 | 5 | 0 | 5 | 2/27/2017 | 2/27/2017 | 3/1/2017 | Connected |  | N
National Grid | REHOBOTH | 637467 | 02769 | 5.76 | Solar | 05_12_22W2 | 09/03/2024 | 10/09/2024 | 5 | 0 | 5 | 10/10/2024 | 10/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2024 | 09/03/2024 | 1/8/2026 | Y | EXP | 365 | 12/19/2024 | 08/07/2025 | 232 | 0 | 232 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 741365 | 01902 | 15.007 | Solar | 05_09_1109W1 | 01/05/2026 | 01/07/2026 | 2 | 0 | 2 | 01/08/2026 | 01/08/2026 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 391838 | 01230 | 0 | Other | 05_07_96W40 | 11/15/2021 | 01/04/2022 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 640154 | 02061 | 7.6 | Solar | 05_07_912W74 | 09/16/2024 | 10/25/2024 | 5 | 2 | 3 | 10/28/2024 | 10/28/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2024 | 09/16/2024 | 12/17/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/7/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176049 | 02324 | 0 | Solar | 05_09_516L1 | 01/26/2015 | 01/26/2015 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/03/2015 | 03/04/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 01/26/2015 | 7/31/2015 | Y | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 469257 | 01521 | 11.4 | Solar | 05_05_335W3 | 12/05/2022 | 12/08/2022 | 3 | 0 | 3 | 12/09/2022 | 12/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2023 | 12/05/2022 | 1/13/2024 | Y | EXP | 365 | 03/01/2023 | 04/13/2023 | 44 | 0 | 44 |  |  | 5/10/2023 | Connected |  | N
National Grid | UPTON | 349680 | 01568 | 0 | Solar | 05_09_901W3 | 03/29/2021 | 03/31/2021 | 2 | 2 | 0 | 04/01/2021 | 04/01/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 3/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2021 | Connected |  | N
National Grid | NORTHAMPTON | 177320 | 01060 | 26.6 | Solar | 05_05_313W1 | 02/15/2017 | 02/15/2017 | 5 | 3 | 2 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2017 |  | 2/20/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 | 9/28/2017 | 9/28/2017 | 10/23/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 526991 | 01532 | 14.79 | Solar | 05_07_69J1 | 07/18/2023 | 08/08/2023 | 16 | 15 | 1 | 08/09/2023 | 08/09/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2023 | 07/18/2023 | 10/9/2024 | Y | EXP | 365 | 10/24/2023 | 10/23/2023 | 0 | 0 | 0 |  |  | 10/25/2023 | Connected |  | N
National Grid | BROCKTON | 177356 | 02302 | 22.8 | Solar | 05_05_7L4 | 02/15/2017 | 02/15/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2017 | 02/15/2017 | 2/21/2018 | Y | EXP | 359 | 06/28/2017 | 07/12/2017 | 9 | 0 | 9 | 9/18/2017 | 9/18/2017 | 9/21/2017 | Connected |  | N
National Grid | REHOBOTH | 643815 | 02769 | 3.8 | Solar | 05_12_22W2 | 10/01/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2024 | 10/01/2024 | 12/2/2025 | Y | EXP | 365 | 12/19/2024 | 12/24/2024 | 6 | 0 | 6 |  |  | 2/20/2025 | Connected |  | N
National Grid | LYNN | 174971 | 01902 | 2500 | Solar | 05_09_1109W1 | 09/10/2013 | 09/10/2013 | 87 | 80 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/17/2014 | 02/07/2014 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 09/10/2013 | 12/31/2016 | Y | STD | 918 | 04/12/2016 | 04/11/2016 | 0 | 0 | 0 | 5/6/2016 | 5/6/2016 | 5/6/2016 | Connected |  | N
National Grid | MONTEREY | 434617 | 01245 | 9.57 | Solar | 05_07_96W40 | 06/27/2022 | 06/29/2022 | 2 | 0 | 2 | 06/30/2022 | 06/30/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2022 |  | 8/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2023 | Connected |  | N
National Grid | ROCKLAND | 672443 | 02370 | 10 | Solar | 05_07_912W74 | 02/17/2025 | 03/18/2025 | 1 | 0 | 1 | 03/19/2025 | 03/19/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | BRIDGEWATER | 176192 | 02324 | 496 | Solar | 05_09_516L1 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/03/2015 | 10/14/2015 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/8/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 471899 | 01010 | 15.2 | Solar | 05_05_335W3 | 10/27/2022 | 10/28/2022 | 1 | 0 | 1 | 10/31/2022 | 10/31/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2022 |  | 12/13/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | UPTON | 362762 | 01568 | 7.6 | Solar | 05_09_901W3 | 07/04/2021 | 07/07/2021 | 1 | 0 | 1 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 07/04/2021 | 3/2/2023 | Y | EXP | 365 | 02/25/2022 | 03/01/2022 | 5 | 0 | 5 |  |  | 3/29/2022 | Connected |  | Y
National Grid | NORTHAMPTON | 178346 | 01060 | 56 | Solar | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 29 | 19 | 10 | 02/02/2018 | 02/02/2018 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2018 |  | 1/17/2019 | N | EXP | 325 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 527500 | 01532 | 10 | Solar | 05_07_69J1 | 08/03/2023 | 08/04/2023 | 1 | 0 | 1 | 08/07/2023 | 08/07/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 | 08/03/2023 | 9/7/2024 | Y | EXP | 365 | 09/26/2023 | 09/25/2023 | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | BROCKTON | 177467 | 02302 | 192 | Solar | 05_05_7L4 | 03/01/2017 | 03/01/2017 | 15 | 13 | 2 | 03/23/2017 | 03/23/2017 | 21 | 6 | 15 | 05/03/2017 | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/7/2018 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 6/19/2018 | Connected |  | N
National Grid | REHOBOTH | 644456 | 02769 | 6 | Solar | 05_12_22W2 | 10/02/2024 | 12/06/2024 | 5 | 0 | 5 | 12/09/2024 | 12/09/2024 | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175508 | 01902 | 630 | Solar | 05_09_1109W1 | 12/04/2014 | 12/04/2014 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/30/2015 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 495669 | 01230 | 220 | Solar | 05_07_96W40 | 02/17/2023 | 04/20/2023 | 42 | 34 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/21/2023 | 05/12/2023 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 678442 | 02061 | 7.6 | Solar | 05_07_912W74 | 03/17/2025 | 03/21/2025 | 4 | 0 | 4 | 03/24/2025 | 03/24/2025 | 53 | 35 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EAST BRIDGEWATER | 176367 | 02333 | 10 | Solar | 05_09_516L1 | 03/10/2016 | 03/10/2016 | 2 | 2 | 0 | 03/14/2016 | 03/14/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 |  | 3/15/2017 | N | EXP | 323 |  |  | 0 | 0 | 0 | 4/26/2016 | 4/26/2016 | 11/14/2016 | Connected |  | N
National Grid | BRIMFIELD | 475185 | 01010 | 6.96 | Solar | 05_05_335W3 | 12/21/2022 | 01/03/2023 | 7 | 0 | 7 | 01/04/2023 | 01/04/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2023 | Connected |  | N
National Grid | UPTON | 375735 | 01568 | 8.505 | Solar | 05_09_901W3 | 08/23/2021 | 01/04/2022 | 20 | 17 | 3 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  | 1/3/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 178345 | 01060 | 72 | Solar | 05_05_313W1 | 01/11/2018 | 01/11/2018 | 25 | 15 | 10 | 02/20/2018 | 02/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 |  | 1/17/2019 | N | EXP | 331 |  |  | 0 | 0 | 0 |  |  | 12/20/2018 | Connected |  | N
National Grid | NORTHBOROUGH | 530664 | 01532 | 6 | Solar | 05_07_69J1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  | 8/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177466 | 02302 | 168 | Solar | 05_05_7L4 | 03/01/2017 | 03/01/2017 | 20 | 13 | 7 | 03/23/2017 | 03/23/2017 | 21 | 6 | 15 | 05/03/2017 | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 05/03/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 |  | 3/7/2018 | N | EXP | 38 |  |  | 0 | 0 | 0 |  |  | 7/10/2018 | Connected |  | N
National Grid | REHOBOTH | 647202 | 02769 | 7.6 | Solar | 05_12_22W2 | 10/15/2024 | 11/12/2024 | 17 | 13 | 4 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | LYNN | 175507 | 01902 | 1000 | Solar | 05_09_1109W1 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/30/2015 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2015 |  | 10/1/2016 | N | STD | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 621643 | 01236 | 26.46 | Solar | 05_07_96W40 | 07/18/2024 | 08/13/2024 | 19 | 17 | 2 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2024 | Connected |  | N
National Grid | SCITUATE | 725599 | 02066 | 7.6 | Solar | 05_07_912W74 | 10/10/2025 | 10/22/2025 | 6 | 0 | 6 | 10/23/2025 | 10/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | EAST BRIDGEWATER | 176453 | 02333 | 2000 | Solar | 05_09_516L1 | 12/08/2015 | 12/10/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 01/12/2016 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2017 | 12/08/2015 | 8/14/2020 | Y | STD | 958 | 06/08/2019 | 12/20/2019 | 195 | 0 | 195 |  |  | 8/26/2020 | Connected |  | N
National Grid | WALES | 481179 | 01081 | 16 | Solar | 05_05_335W3 | 11/30/2022 | 12/08/2022 | 7 | 6 | 1 | 12/09/2022 | 12/09/2022 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2023 |  | 3/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | UPTON | 378526 | 01568 | 6 | Solar | 05_09_901W3 | 10/01/2021 | 12/29/2021 | 4 | 0 | 4 | 10/08/2021 | 10/08/2021 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  | 4/16/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2022 | Connected |  | N
National Grid | NORTHAMPTON | 207452 | 01060 | 10 | Solar | 05_05_313W1 | 01/29/2019 | 02/12/2019 | 9 | 0 | 9 | 02/13/2019 | 02/13/2019 | 16 | 13 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2019 |  | 3/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 535779 | 01532 | 8.12 | Solar | 05_07_69J1 | 09/29/2023 | 10/26/2023 | 18 | 16 | 2 | 10/27/2023 | 10/27/2023 | 82 | 28 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178229 | 02302 | 15.2 | Solar | 05_05_7L4 | 01/03/2018 | 01/03/2018 | 38 | 32 | 6 | 03/06/2018 | 03/06/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 1/10/2019 | N | EXP | 39 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | REHOBOTH | 650924 | 02769 | 11.05 | Solar | 05_12_22W2 | 10/30/2024 | 01/30/2025 | 33 | 27 | 6 | 01/31/2025 | 01/31/2025 | 159 | 133 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 175506 | 01902 | 1000 | Solar | 05_09_1109W1 | 12/04/2014 | 12/04/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/30/2015 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/19/2015 |  | 10/1/2016 | N | STD | 47 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 634458 | 01257 | 4.18 | Solar | 05_07_96W40 | 08/26/2024 | 09/05/2024 | 6 | 4 | 2 | 09/06/2024 | 09/06/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2024 | 08/26/2024 | 9/23/2025 | Y | EXP | 365 | 10/09/2024 | 11/01/2024 | 24 | 0 | 24 |  |  | 1/14/2025 | Connected |  | N
National Grid | NORWELL | 279925 | 02061 | 1750 | Solar | 05_07_912W75 | 05/26/2020 | 06/22/2020 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2020 | 07/23/2020 | 23 | 4 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/29/2021 | 05/26/2020 | 4/30/2026 | Y | STD | 399 | 01/10/2024 | 02/13/2025 | 401 | 91 | 310 |  |  |  | Construction |  | N
National Grid | BRIDGEWATER | 177372 | 02324 | 2000 | Solar | 05_09_516L1 | 09/07/2016 | 09/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2016 | 10/24/2016 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2017 |  | 9/13/2017 | N | STD | 126 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 485628 | 01521 | 7.6 | Solar | 05_05_335W3 | 12/27/2022 | 01/03/2023 | 4 | 0 | 4 | 01/04/2023 | 01/04/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2023 |  | 2/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2023 | Connected |  | N
National Grid | MILFORD | 411322 | 01757 | 10 | Solar | 05_09_901W3 | 02/15/2022 | 02/22/2022 | 4 | 0 | 4 | 02/23/2022 | 02/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2022 |  | 4/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2022 | Connected |  | N
National Grid | NORTHAMPTON | 224878 | 01062 | 10 | Solar | 05_05_313W1 | 05/28/2019 | 05/30/2019 | 1 | 0 | 1 | 05/31/2019 | 05/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2019 |  | 6/5/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 567965 | 01532 | 6 | Solar | 05_07_69J1 | 11/10/2023 | 11/27/2023 | 10 | 4 | 6 | 11/28/2023 | 11/28/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2024 | Connected |  | N
National Grid | BROCKTON | 178316 | 02302 | 7.6 | Solar | 05_05_7L4 | 02/26/2018 | 02/26/2018 | 3 | 3 | 0 | 03/16/2018 | 03/16/2018 | 156 | 3 | 153 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2018 |  | 3/4/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 652324 | 02769 | 7.6 | Solar | 05_12_22W2 | 11/05/2024 | 11/15/2024 | 2 | 0 | 2 | 11/18/2024 | 11/18/2024 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2025 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | LYNN | 175548 | 01902 | 33.48 | Solar | 05_09_1109W1 | 04/10/2014 | 04/10/2014 | 6 | 0 | 6 | 04/22/2014 | 04/22/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/5/2014 |  | 7/31/2014 | N | EXP | 87 |  |  | 0 | 0 | 0 | 6/17/2014 | 6/17/2014 | 7/16/2014 | Connected |  | N
National Grid | SHEFFIELD | 647618 | 01257 | 0 | Other | 05_07_96W40 | 11/15/2024 | 12/10/2024 | 15 | 6 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2024 | 05/06/2025 | 100 | 81 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 664427 | 02061 | 4990 | Solar | 05_07_912W75 | 02/13/2025 | 03/10/2025 | 17 | 7 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/11/2025 | 04/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | BRIDGEWATER | 177670 | 02324 | 3000 | Solar | 05_09_516L1 | 05/25/2017 | 05/31/2017 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/31/2017 | 06/15/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2018 |  | 8/27/2020 | N | STD | 811 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WALES | 489672 | 01081 | 0 | Solar | 05_05_335W3 | 01/04/2023 |  | 68 | 45 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | UPTON | 456714 | 01568 | 17.4 | Solar | 05_09_901W3 | 09/06/2022 | 09/08/2022 | 3 | 1 | 2 | 09/09/2022 | 09/09/2022 | 48 | 27 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2022 | 09/06/2022 | 2/7/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2023 | Connected |  | N
National Grid | NORTHAMPTON | 253609 | 01060 | 15.2 | Solar | 05_05_313W1 | 09/11/2019 | 09/16/2019 | 3 | 3 | 0 | 09/17/2019 | 09/17/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2019 |  | 9/10/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 570864 | 01532 | 7.6 | Solar | 05_07_69J1 | 12/06/2023 | 12/12/2023 | 4 | 2 | 2 | 12/13/2023 | 12/13/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 12/06/2023 | 2/28/2025 | Y | EXP | 365 | 04/26/2024 | 05/14/2024 | 19 | 0 | 19 |  |  | 6/20/2024 | Connected |  | N
National Grid | BROCKTON | 194753 | 02302 | 3060 | Solar | 05_05_7L4 | 08/30/2018 | 09/25/2018 | 16 | 4 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2018 | 10/23/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 08/30/2018 | 2/23/2026 | Y | STD | 442 | 06/13/2025 | 12/17/2025 | 188 | 9 | 179 |  |  | 12/30/2025 | Connected |  | N
National Grid | SEEKONK | 655756 | 02771 | 10 | Solar | 05_12_22W2 | 12/02/2024 | 01/06/2025 | 19 | 14 | 5 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | N
National Grid | LYNN | 176190 | 01902 | 496 | Solar | 05_09_1109W1 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 | 09/03/2015 | 09/03/2015 | 359 | 0 | 359 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/8/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 648861 | 01257 | 9.75 | Solar | 05_07_96W40 | 10/22/2024 | 11/19/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 |  | 12/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/6/2025 | Connected |  | N
National Grid | SCITUATE | 738803 | 02066 | 5.76 | Solar | 05_07_912W75 | 12/08/2025 | 12/10/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HALIFAX | 184331 | 02338 | 7.6 | Solar | 05_09_516L1 | 07/09/2018 | 07/09/2018 | 0 | 0 | 0 | 07/10/2018 | 07/10/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2018 |  | 10/18/2019 | N | EXP | 438 |  |  | 0 | 0 | 0 |  |  | 9/9/2019 | Connected |  | N
National Grid | HOLLAND | 493873 | 01521 | 10 | Solar | 05_05_335W3 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 | 02/14/2023 | 10/11/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2023 | Connected |  | N
National Grid | UPTON | 460740 | 01568 | 15.2 | Solar | 05_09_901W3 | 09/28/2022 | 10/03/2022 | 3 | 2 | 1 | 10/04/2022 | 10/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/27/2022 |  | 11/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/31/2023 | Connected |  | N
National Grid | NORTHAMPTON | 259202 | 01062 | 3.8 | Solar | 05_05_313W1 | 10/18/2019 | 10/22/2019 | 1 | 0 | 1 | 10/23/2019 | 10/23/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2019 | 10/18/2019 | 10/18/2020 | Y | EXP | 365 | 02/12/2020 | 04/02/2020 | 50 | 0 | 50 |  |  | 6/3/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 575267 | 01532 | 3.8 | Solar | 05_07_69J1 | 12/15/2023 | 12/19/2023 | 2 | 1 | 1 | 12/20/2023 | 12/20/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 257553 | 02302 | 8.64 | Solar | 05_05_7L4 | 03/17/2020 | 04/03/2020 | 12 | 8 | 4 | 04/06/2020 | 04/06/2020 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 663491 | 02769 | 3.8 | Solar | 05_12_22W2 | 01/02/2025 | 03/07/2025 | 4 | 0 | 4 | 03/10/2025 | 03/10/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 01/02/2025 | 4/11/2026 | Y | EXP | 365 | 06/14/2025 | 11/14/2025 | 154 | 0 | 154 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 176217 | 01902 | 162.4 | Solar | 05_09_1109W1 | 07/07/2015 | 07/07/2015 | 0 | 0 | 0 | 07/07/2015 | 07/07/2015 | 392 | 0 | 392 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2015 |  | 7/12/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 7/22/2015 | 7/22/2015 |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 720193 | 01230 | 94.05 | Solar | 05_07_96W40 | 09/25/2025 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 745573 | 02061 | 12 | Solar | 05_07_912W75 | 01/15/2026 | 01/20/2026 | 3 | 0 | 3 | 02/09/2026 | 02/09/2026 | 17 | 2 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HALIFAX | 188873 | 02338 | 150 | Solar | 05_09_516L1 | 08/14/2018 | 09/04/2018 | 13 | 4 | 9 | 09/05/2018 | 09/05/2018 | 83 | 2 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 523162 | 01083 | 10 | Solar | 05_05_335W3 | 05/08/2023 | 05/09/2023 | 1 | 0 | 1 | 05/10/2023 | 05/10/2023 | 24 | 4 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2023 | 05/08/2023 | 8/23/2024 | Y | EXP | 365 | 08/02/2023 | 10/30/2023 | 90 | 0 | 90 |  |  | 1/9/2024 | Connected |  | N
National Grid | MILFORD | 477384 | 01757 | 10 | Solar | 05_09_901W3 | 04/10/2023 | 04/11/2023 | 1 | 0 | 1 | 04/12/2023 | 04/12/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 317103 | 01060 | 10 | Solar | 05_05_313W1 | 10/05/2020 | 10/08/2020 | 2 | 0 | 2 | 10/09/2020 | 10/09/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 |  | 10/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/22/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 584083 | 01532 | 10.15 | Solar | 05_07_69J1 | 01/19/2024 | 02/28/2024 | 27 | 18 | 9 | 02/29/2024 | 02/29/2024 | 7 | 4 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 | 01/19/2024 | 3/27/2025 | Y | EXP | 365 | 05/24/2024 | 06/05/2024 | 13 | 0 | 13 |  |  | 12/23/2024 | Connected |  | N
National Grid | BROCKTON | 307102 | 02302 | 17.04 | Solar | 05_05_7L4 | 08/17/2020 | 08/27/2020 | 8 | 8 | 0 | 08/28/2020 | 08/28/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/15/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/13/2021 | Connected |  | N
National Grid | REHOBOTH | 669422 | 02769 | 7.6 | Solar | 05_12_22W2 | 02/01/2025 | 03/05/2025 | 4 | 1 | 3 | 03/06/2025 | 03/06/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 | 02/01/2025 | 5/16/2026 | Y | EXP | 365 | 08/19/2025 | 08/25/2025 | 7 | 0 | 7 |  |  | 10/8/2025 | Connected |  | N
National Grid | LYNN | 176998 | 01902 | 113.4 | Solar | 05_09_1109W1 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2016 |  | 7/25/2017 | N | EXP | 33 |  |  | 0 | 0 | 0 | 1/17/2017 | 1/17/2017 | 1/23/2017 | Connected |  | N
National Grid | NORTHAMPTON | 658956 | 01244 | 400 | Solar | 05_07_96W41 | 01/15/2025 | 03/11/2025 | 37 | 28 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/12/2025 | 04/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 |  | 1/28/2026 | N | STD | 49 |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | SCITUATE | 747980 | 02066 | 15.76 | Solar | 05_07_912W75 | 01/28/2026 | 01/30/2026 | 2 | 0 | 2 | 02/02/2026 | 02/02/2026 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2026 |  | 2/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | HALIFAX | 188705 | 02338 | 7999 | Solar | 05_09_516L1 | 09/10/2018 | 09/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/14/2018 | 11/17/2018 | 45 | 26 | 19 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 524693 | 01010 | 15.2 | Solar | 05_05_335W3 | 05/08/2023 | 05/10/2023 | 2 | 0 | 2 | 05/11/2023 | 05/11/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2023 | 05/08/2023 | 12/7/2024 | Y | EXP | 365 | 09/26/2023 | 11/17/2023 | 53 | 0 | 53 |  |  | 1/16/2024 | Connected |  | N
National Grid | UPTON | 479453 | 01568 | 10 | Solar | 05_09_901W3 | 02/27/2023 | 03/01/2023 | 2 | 0 | 2 | 03/02/2023 | 03/02/2023 | 23 | 0 | 23 | 05/26/2023 | 06/28/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  | 06/28/2023 | 12 | 0 | 12 |  |  | 0 | 0 | 0 | 6/20/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 343188 | 01062 | 11.4 | Solar | 05_05_313W1 | 02/21/2021 | 02/22/2021 | 0 | 0 | 0 | 02/23/2021 | 02/23/2021 | 121 | 73 | 48 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/21/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 591557 | 01532 | 3.8 | Solar | 05_07_69J1 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2024 | 02/22/2024 | 6/19/2025 | Y | EXP | 365 | 06/29/2024 | 11/01/2024 | 126 | 0 | 126 |  |  | 3/7/2025 | Connected |  | N
National Grid | BROCKTON | 321328 | 02302 | 7.6 | Solar | 05_05_7L4 | 11/06/2020 | 11/12/2020 | 2 | 0 | 2 | 11/13/2020 | 11/13/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2020 | 11/06/2020 | 12/22/2022 | Y | EXP | 365 | 03/03/2022 | 03/22/2022 | 20 | 0 | 20 |  |  | 5/31/2022 | Connected |  | Y
National Grid | SEEKONK | 669921 | 02771 | 3.8 | Solar | 05_12_22W2 | 02/04/2025 | 02/19/2025 | 4 | 0 | 4 | 02/20/2025 | 02/20/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2025 | Connected |  | N
National Grid | SWAMPSCOTT | 177410 | 01907 | 1980 | Solar | 05_09_1109W1 | 09/11/2016 | 09/11/2016 | 22 | 22 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/13/2016 | 11/01/2016 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2017 | 09/11/2016 | 4/30/2021 | Y | STD | 171 | 09/06/2019 | 01/05/2021 | 487 | 5 | 482 |  |  | 4/16/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 174570 | 01230 | 900 | Wind | 05_07_96W41 | 05/17/2011 | 05/17/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 174220 | 02061 | 500 | Solar | 05_07_912W75 | 02/09/2012 | 02/09/2012 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 189866 | 02338 | 4000 | Solar | 05_09_516L1 | 08/06/2018 | 10/05/2018 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/08/2018 | 12/15/2018 | 51 | 30 | 21 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 532580 | 01010 | 16.4 | Solar | 05_05_335W3 | 06/23/2023 | 06/26/2023 | 1 | 0 | 1 | 06/27/2023 | 06/27/2023 | 253 | 233 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/21/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2024 | Connected |  | N
National Grid | UPTON | 494316 | 01568 | 5 | Solar | 05_09_901W3 | 01/26/2023 | 01/27/2023 | 1 | 0 | 1 | 01/30/2023 | 01/30/2023 | 20 | 2 | 18 | 03/02/2023 | 03/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  | 03/23/2023 | 13 | 0 | 13 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 7/24/2024 | N | EXP | 365 | 07/12/2023 | 07/25/2023 | 14 | 0 | 14 |  |  | 8/3/2023 | Connected |  | Y
National Grid | NORTHAMPTON | 381762 | 01060 | 15.2 | Solar | 05_05_313W1 | 09/13/2021 | 10/04/2021 | 15 | 14 | 1 | 10/05/2021 | 10/05/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2021 |  | 1/17/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 592814 | 01532 | 9.984 | Solar | 05_07_69J1 | 03/18/2024 | 03/20/2024 | 3 | 1 | 2 | 03/21/2024 | 03/21/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2024 |  | 3/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | BROCKTON | 326927 | 02302 | 7.6 | Solar | 05_05_7L4 | 11/18/2020 | 11/19/2020 | 0 | 0 | 0 | 11/20/2020 | 11/20/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2020 | 11/18/2020 | 8/13/2022 | Y | EXP | 435 | 04/08/2021 | 04/23/2021 | 15 | 0 | 15 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 686814 | 02769 | 5.76 | Solar | 05_12_22W2 | 04/22/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/22/2025 | Connected |  | N
National Grid | LYNN | 177611 | 01902 | 212.75 | Solar | 05_09_1109W1 | 09/21/2017 | 09/21/2017 | 22 | 0 | 22 | 10/24/2017 | 10/24/2017 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2018 | 09/21/2017 | 2/14/2019 | Y | EXP | 219 |  |  | 0 | 0 | 0 |  |  | 3/1/2019 | Connected |  | N
National Grid | GREAT BARRINGTON | 176361 | 01230 | 0 | Solar | 05_07_96W41 | 03/09/2016 | 03/09/2016 | 0 | 0 | 0 | 03/10/2016 | 03/10/2016 | 0 | 0 | 0 | 04/18/2016 | 06/17/2016 | 42 | 12 | 30 |  |  | 0 | 0 | 0 |  | 06/17/2016 | 42 | 12 | 30 |  |  | 0 | 0 | 0 | 7/6/2016 | 03/09/2016 | 9/8/2017 | Y | EXP | 429 | 06/22/2017 | 08/10/2017 | 34 | 0 | 34 | 8/29/2017 | 8/29/2017 | 8/29/2017 | Connected |  | N
National Grid | COHASSET | 174219 | 02025 | 2000 | Solar | 05_07_912W75 | 02/09/2012 | 02/09/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/22/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 197062 | 02338 | 450 | Solar | 05_09_516L1 | 11/27/2018 | 12/05/2018 | 5 | 0 | 5 | 12/06/2018 | 12/06/2018 | 34 | 17 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 565699 | 01083 | 6 | Solar | 05_05_335W3 | 11/07/2023 | 11/16/2023 | 6 | 4 | 2 | 11/17/2023 | 11/17/2023 | 27 | 6 | 21 | 01/31/2024 | 03/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 2/16/2024 |  | 2/21/2025 | N | EXP | 365 | 05/18/2024 | 06/08/2024 | 22 | 0 | 22 |  |  | 6/18/2024 | Connected |  | N
National Grid | UPTON | 510764 | 01568 | 7.54 | Solar | 05_09_901W3 | 05/10/2023 | 05/15/2023 | 3 | 0 | 3 | 05/16/2023 | 05/16/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/30/2023 | Connected |  | N
National Grid | NORTHAMPTON | 414064 | 01060 | 15.2 | Solar | 05_05_313W1 | 02/24/2022 | 02/28/2022 | 3 | 2 | 1 | 03/01/2022 | 03/01/2022 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 601320 | 01532 | 7.6 | Solar | 05_07_69J1 | 04/10/2024 | 04/16/2024 | 3 | 0 | 3 | 04/17/2024 | 04/17/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2024 | Connected |  | N
National Grid | BROCKTON | 335356 | 02302 | 24.36 | Solar | 05_05_7L4 | 05/05/2021 | 05/07/2021 | 1 | 0 | 1 | 05/10/2021 | 05/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2021 |  | 11/9/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2021 | Connected |  | N
National Grid | SEEKONK | 694314 | 02771 | 3.8 | Solar | 05_12_22W2 | 05/29/2025 | 06/23/2025 | 3 | 0 | 3 | 06/30/2025 | 06/30/2025 | 38 | 24 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 177728 | 01902 | 4930 | Solar | 05_09_1109W1 | 10/04/2017 | 10/04/2017 | 42 | 41 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/06/2017 | 01/11/2018 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 | 10/04/2017 | 6/30/2021 | Y | STD | 692 | 10/26/2019 | 04/12/2021 | 534 | 228 | 306 |  |  | 6/15/2021 | Connected |  | N
National Grid | SHEFFIELD | 177045 | 01257 | 696 | Solar | 05_07_96W41 | 10/17/2016 | 10/17/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2016 | 01/23/2017 | 59 | 44 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 | 10/17/2016 | 10/15/2021 | Y | STD | 225 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 174653 | 02025 | 225 | Solar | 05_07_912W75 | 08/21/2012 | 08/21/2012 | 8 | 0 | 8 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2012 |  | 11/1/2012 | N | EXP | 4 |  |  | 0 | 0 | 0 | 12/28/2012 | 12/28/2012 | 12/28/2012 | Connected |  | N
National Grid | HALIFAX | 197057 | 02338 | 850 | Solar | 05_09_516L1 | 10/29/2018 | 11/26/2018 | 107 | 7 | 100 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/25/2019 | 02/27/2019 | 21 | 8 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WALES | 607126 | 01081 | 20 | Solar | 05_05_335W3 | 05/14/2024 | 05/28/2024 | 9 | 7 | 2 | 05/29/2024 | 05/29/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2024 |  | 6/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2024 | Connected |  | N
National Grid | HOPEDALE | 529560 | 01747 | 10 | Solar | 05_09_901W3 | 06/15/2023 | 06/22/2023 | 4 | 2 | 2 | 06/23/2023 | 06/23/2023 | 18 | 2 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2023 | 06/15/2023 | 8/28/2024 | Y | EXP | 365 | 08/30/2023 | 08/29/2023 | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | NORTHAMPTON | 430956 | 01060 | 15.2 | Solar | 05_05_313W1 | 05/16/2022 | 05/18/2022 | 2 | 0 | 2 | 05/19/2022 | 05/19/2022 | 111 | 92 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2022 | 05/16/2022 | 7/27/2024 | Y | EXP | 365 | 02/07/2023 | 07/25/2023 | 169 | 0 | 169 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 610713 | 01532 | 3.8 | Solar | 05_07_69J1 | 05/14/2024 | 05/17/2024 | 1 | 0 | 1 | 05/20/2024 | 05/20/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 339999 | 02302 | 15.2 | Solar | 05_05_7L4 | 02/11/2021 | 02/23/2021 | 7 | 7 | 0 | 02/24/2021 | 02/24/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 |  | 2/23/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2021 | Connected |  | N
National Grid | REHOBOTH | 701684 | 02769 | 15.2 | Solar | 05_12_22W2 | 06/27/2025 | 07/02/2025 | 3 | 0 | 3 | 07/03/2025 | 07/03/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 178063 | 01907 | 2000 | Solar | 05_09_1109W1 | 09/05/2017 | 09/05/2017 | 15 | 8 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2017 | 10/18/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 | 09/05/2017 | 11/11/2021 | Y | STD | 797 | 01/07/2021 | 04/16/2021 | 99 | 0 | 99 |  |  | 10/18/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 178632 | 01230 | 10 | Solar | 05_07_96W41 | 03/15/2018 | 03/15/2018 | 4 | 4 | 0 | 03/23/2018 | 03/23/2018 | 402 | 0 | 402 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2018 |  | 3/21/2019 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 175062 | 02025 | 2500 | Solar | 05_07_912W75 | 02/09/2012 | 02/09/2012 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 | 4/11/2014 | 02/09/2012 | 3/15/2013 | Y | STD | 392 | 06/03/2015 | 10/31/2015 | 104 | 0 | 104 | 10/22/2012 | 10/22/2012 | 8/11/2015 | Connected |  | N
National Grid | HALIFAX | 199732 | 02338 | 450 | Solar | 05_09_516L1 | 10/31/2018 | 11/08/2018 | 5 | 0 | 5 | 11/09/2018 | 11/09/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 609328 | 01521 | 7.6 | Solar | 05_05_335W3 | 05/07/2024 | 06/11/2024 | 1 | 0 | 1 | 06/12/2024 | 06/12/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2024 | 05/07/2024 | 7/15/2025 | Y | EXP | 365 | 12/11/2024 | 02/28/2025 | 80 | 0 | 80 |  |  | 3/7/2025 | Connected |  | N
National Grid | UPTON | 567873 | 01568 | 22.8 | Solar | 05_09_901W3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2024 |  | 1/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | NORTHAMPTON | 492962 | 01060 | 14.5 | Solar | 05_05_313W1 | 02/01/2023 | 02/02/2023 | 1 | 0 | 1 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2023 | 02/01/2023 | 9/8/2024 | Y | EXP | 365 | 05/11/2023 | 09/06/2023 | 119 | 0 | 119 |  |  | 1/27/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 617998 | 01532 | 5.76 | Solar | 05_07_69J1 | 06/14/2024 | 06/24/2024 | 1 | 0 | 1 | 06/25/2024 | 06/25/2024 | 17 | 0 | 17 | 07/25/2024 | 08/27/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 08/27/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 8/26/2024 | 06/14/2024 | 8/27/2025 | Y | EXP | 365 | 10/03/2024 | 10/29/2024 | 27 | 0 | 27 |  |  | 11/14/2024 | Connected |  | N
National Grid | BROCKTON | 342021 | 02302 | 18 | Solar | 05_05_7L4 | 02/12/2021 | 02/25/2021 | 7 | 3 | 4 | 02/26/2021 | 02/26/2021 | 36 | 18 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2021 | Connected |  | N
National Grid | REHOBOTH | 705143 | 02769 | 6 | Solar | 05_12_22W2 | 07/15/2025 | 07/30/2025 | 1 | 0 | 1 | 08/11/2025 | 08/11/2025 | 58 | 47 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | LYNN | 178062 | 01902 | 1000 | Solar | 05_09_1109W1 | 09/05/2017 | 09/05/2017 | 15 | 8 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/26/2017 | 10/18/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2018 | 09/05/2017 | 7/30/2021 | Y | STD | 797 | 12/13/2019 | 04/02/2021 | 476 | 301 | 175 |  |  | 7/12/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 200495 | 01230 | 7.5 | Solar | 05_07_96W41 | 11/13/2018 | 04/11/2019 | 0 | 0 | 0 | 04/12/2019 | 04/12/2019 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2019 |  | 5/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2019 | Connected |  | N
National Grid | COHASSET | 175432 | 02025 | 1000 | Solar | 05_07_912W75 | 11/24/2014 | 11/24/2014 | 5 | 3 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/03/2014 | 12/24/2014 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2015 |  | 8/30/2016 | N | STD | 389 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 200636 | 02338 | 1560 | Solar | 05_09_516L1 | 12/06/2018 | 01/28/2019 | 103 | 26 | 77 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/29/2019 | 03/13/2019 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/1/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 611557 | 01521 | 7.6 | Solar | 05_05_335W3 | 05/16/2024 | 05/23/2024 | 2 | 0 | 2 | 05/24/2024 | 05/24/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 |  | 12/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 613757 | 01568 | 13.53 | Solar | 05_09_901W3 | 05/29/2024 | 06/05/2024 | 6 | 4 | 2 | 06/06/2024 | 06/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2024 |  | 6/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/14/2024 | Connected |  | N
National Grid | NORTHAMPTON | 557386 | 01060 | 17.4 | Solar | 05_05_313W1 | 09/22/2023 | 10/11/2023 | 12 | 9 | 3 | 10/12/2023 | 10/12/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 632302 | 01532 | 3.8 | Solar | 05_07_69J1 | 08/13/2024 | 09/10/2024 | 4 | 0 | 4 | 09/11/2024 | 09/11/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 08/13/2024 | 11/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/1/2025 | Connected |  | N
National Grid | BROCKTON | 342835 | 02302 | 11.4 | Solar | 05_05_7L4 | 02/18/2021 | 02/25/2021 | 4 | 0 | 4 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 |  | 11/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2021 | Connected |  | N
National Grid | REHOBOTH | 705139 | 02769 | 5.76 | Solar | 05_12_22W2 | 07/15/2025 | 07/31/2025 | 1 | 0 | 1 | 08/07/2025 | 08/07/2025 | 54 | 25 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | LYNN | 178278 | 01902 | 10 | Solar | 05_09_1109W1 | 02/23/2018 | 02/23/2018 | 5 | 5 | 0 | 03/07/2018 | 03/07/2018 | 143 | 0 | 143 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 2/28/2019 | N | EXP | 358 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NEW MARLBOROUGH | 263280 | 01230 | 0 | Other | 05_07_96W41 | 10/31/2019 | 01/21/2020 | 44 | 39 | 5 | 01/22/2020 | 01/22/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2020 |  | 10/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/23/2020 | Connected |  | N
National Grid | COHASSET | 175660 | 02025 | 480 | Solar | 05_07_912W75 | 05/22/2014 | 05/22/2014 | 6 | 0 | 6 | 06/03/2014 | 06/03/2014 | 115 | 0 | 115 | 06/27/2014 | 11/18/2014 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  | 11/18/2014 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 2/16/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 301303 | 02338 | 6.48 | Solar | 05_09_516L1 | 07/15/2020 | 07/16/2020 | 0 | 0 | 0 | 07/17/2020 | 07/17/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2020 |  | 7/15/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WALES | 611117 | 01081 | 8.36 | Solar | 05_05_335W3 | 05/15/2024 | 05/21/2024 | 4 | 2 | 2 | 05/22/2024 | 05/22/2024 | 45 | 31 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2024 |  | 8/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2024 | Connected |  | N
National Grid | MILFORD | 639898 | 01757 | 2.61 | Solar | 05_09_901W3 | 09/12/2024 | 10/24/2024 | 2 | 0 | 2 | 10/25/2024 | 10/25/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  | 12/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 553637 | 01060 | 160 | Solar | 05_05_313W1 | 09/11/2023 | 09/24/2023 | 9 | 0 | 9 | 09/25/2023 | 09/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 09/11/2023 | 1/5/2026 | Y | EXP | 28 |  |  | 0 | 0 | 0 |  |  | 6/10/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 634714 | 01532 | 5.76 | Solar | 05_07_69J1 | 08/22/2024 | 09/06/2024 | 2 | 0 | 2 | 09/09/2024 | 09/09/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2024 | 08/22/2024 | 11/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 355588 | 02302 | 8.7 | Solar | 05_05_7L4 | 05/25/2021 | 12/22/2021 | 5 | 2 | 3 | 06/04/2021 | 06/04/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2021 | 05/25/2021 | 3/1/2023 | Y | EXP | 365 | 12/24/2021 | 02/24/2022 | 63 | 0 | 63 |  |  | 3/5/2022 | Connected |  | N
National Grid | REHOBOTH | 704803 | 02769 | 5 | Solar | 05_12_22W2 | 07/14/2025 | 07/25/2025 | 29 | 24 | 5 | 09/17/2025 | 09/17/2025 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | LYNN | 178503 | 01902 | 37.8 | Solar | 05_09_1109W1 | 01/24/2018 | 01/24/2018 | 26 | 1 | 25 | 03/20/2018 | 03/20/2018 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 |  | 1/30/2019 | N | EXP | 315 |  |  | 0 | 0 | 0 |  |  | 12/5/2018 | Connected |  | N
National Grid | NEW MARLBOROUGH | 288906 | 01230 | 24 | Solar | 05_07_96W41 | 05/08/2020 | 05/11/2020 | 1 | 1 | 0 | 05/12/2020 | 05/12/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 5/11/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/21/2020 | Connected |  | N
National Grid | COHASSET | 176117 | 02025 | 10 | Solar | 05_07_912W75 | 08/20/2015 | 08/20/2015 | 0 | 0 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2015 |  | 8/29/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 3/28/2016 | Connected |  | N
National Grid | HALIFAX | 350119 | 02338 | 5.8 | Solar | 05_09_516L1 | 03/31/2021 | 04/01/2021 | 0 | 0 | 0 | 04/02/2021 | 04/02/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 | 03/31/2021 | 9/24/2022 | Y | EXP | 365 | 07/14/2021 | 09/22/2021 | 70 | 3 | 67 |  |  | 12/8/2021 | Connected |  | Y
National Grid | WALES | 654695 | 01081 | 5.76 | Solar | 05_05_335W3 | 12/05/2024 | 12/30/2024 | 6 | 2 | 4 | 12/31/2024 | 12/31/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 | 12/05/2024 | 4/14/2026 | Y | EXP | 365 | 09/04/2025 | 10/16/2025 | 43 | 0 | 43 |  |  | 10/23/2025 | Connected |  | N
National Grid | UPTON | 652534 | 01568 | 11.5 | Solar | 05_09_901W3 | 11/06/2024 | 11/12/2024 | 3 | 0 | 3 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 1/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/26/2025 | Connected |  | N
National Grid | NORTHAMPTON | 555486 | 01060 | 240 | Solar | 05_05_313W1 | 09/15/2023 | 10/13/2023 | 19 | 10 | 9 | 10/16/2023 | 10/16/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2023 | 09/15/2023 | 6/17/2025 | Y | EXP | 252 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 637696 | 01532 | 3.8 | Solar | 05_07_69J1 | 09/04/2024 | 09/18/2024 | 2 | 0 | 2 | 09/19/2024 | 09/19/2024 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 | 09/04/2024 | 10/9/2025 | Y | EXP | 365 | 03/20/2025 | 03/19/2025 | 0 | 0 | 0 |  |  | 4/4/2025 | Connected |  | N
National Grid | BROCKTON | 372768 | 02302 | 15.2 | Solar | 05_05_7L4 | 07/29/2021 |  | 45 | 37 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 709020 | 02769 | 5.76 | Solar | 05_12_22W2 | 08/01/2025 | 09/02/2025 | 3 | 0 | 3 | 09/03/2025 | 09/03/2025 | 31 | 15 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2025 |  | 10/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LYNN | 186212 | 01092 | 7.6 | Solar | 05_09_1109W1 | 05/24/2018 | 05/24/2018 | 11 | 0 | 11 | 06/12/2018 | 06/12/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2018 |  | 10/28/2019 | N | EXP | 467 |  |  | 0 | 0 | 0 |  |  | 9/27/2019 | Connected |  | N
National Grid | NEW MARLBOROUGH | 295339 | 01259 | 10 | Solar | 05_07_96W41 | 06/13/2020 | 06/18/2020 | 3 | 0 | 3 | 06/19/2020 | 06/19/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/19/2020 | Connected |  | N
National Grid | COHASSET | 176426 | 02025 | 6.45 | Solar | 05_07_912W75 | 02/03/2016 | 02/03/2016 | 5 | 5 | 0 | 02/11/2016 | 02/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 | 02/03/2016 | 2/9/2017 | Y | EXP | 338 | 10/04/2016 | 10/12/2016 | 5 | 0 | 5 | 10/19/2016 | 10/19/2016 | 10/25/2016 | Connected |  | N
National Grid | HALIFAX | 375386 | 02338 | 10 | Solar | 05_09_516L1 | 08/24/2021 | 08/25/2021 | 2 | 1 | 1 | 08/26/2021 | 08/26/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 |  | 10/3/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2021 | Connected |  | N
National Grid | WALES | 663902 | 01081 | 18.2 | Solar | 05_05_335W3 | 01/08/2025 | 01/10/2025 | 2 | 0 | 2 | 01/13/2025 | 01/13/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2025 | 01/08/2025 | 3/4/2026 | Y | EXP | 365 | 05/07/2025 | 05/07/2025 | 1 | 0 | 1 |  |  | 5/10/2025 | Connected |  | N
National Grid | MILFORD | 666190 | 01757 | 5.76 | Solar | 05_09_901W3 | 01/22/2025 | 02/19/2025 | 5 | 0 | 5 | 02/20/2025 | 02/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | NORTHAMPTON | 584740 | 01062 | 9.28 | Solar | 05_05_313W1 | 01/23/2024 | 01/30/2024 | 6 | 5 | 1 | 01/31/2024 | 01/31/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/12/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 645123 | 01532 | 10 | Solar | 05_07_69J1 | 10/07/2024 | 10/15/2024 | 2 | 0 | 2 | 01/07/2025 | 01/07/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2024 | 10/07/2024 | 2/20/2026 | Y | EXP | 365 | 06/10/2025 | 07/02/2025 | 23 | 0 | 23 |  |  | 7/18/2025 | Connected |  | N
National Grid | BROCKTON | 384910 | 02302 | 9.86 | Solar | 05_05_7L4 | 09/28/2021 | 01/06/2022 | 9 | 7 | 2 | 10/12/2021 | 10/12/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2021 |  | 12/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2022 | Connected |  | N
National Grid | REHOBOTH | 708270 | 02769 | 5.76 | Solar | 05_12_22W2 | 07/29/2025 | 08/26/2025 | 3 | 0 | 3 | 08/27/2025 | 08/27/2025 | 46 | 32 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 11/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | LYNN | 191267 | 01902 | 4400 | Solar | 05_09_1109W1 | 07/25/2018 | 08/16/2018 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2018 | 11/27/2018 | 69 | 26 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 336643 | 01236 | 250 | Solar | 05_07_96W41 | 01/28/2021 | 02/03/2021 | 3 | 0 | 3 | 02/04/2021 | 02/04/2021 | 42 | 20 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 176814 | 02025 | 6.75 | Solar | 05_07_912W75 | 11/05/2015 | 11/05/2015 | 15 | 15 | 0 | 11/30/2015 | 11/30/2015 | 504 | 1 | 503 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2015 | 11/05/2015 | 11/10/2016 | Y | EXP | 331 |  |  | 0 | 0 | 0 | 12/15/2015 | 12/15/2015 |  | Withdrawn |  | Y
National Grid | HALIFAX | 419691 | 02338 | 0 | Solar | 05_09_516L1 | 03/24/2022 | 04/15/2022 | 17 | 16 | 1 | 04/19/2022 | 04/19/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 672737 | 01010 | 15.2 | Solar | 05_05_335W3 | 02/20/2025 | 02/25/2025 | 3 | 0 | 3 | 02/26/2025 | 02/26/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2025 | Connected |  | N
National Grid | UPTON | 670750 | 01568 | 9.6 | Solar | 05_09_901W3 | 02/12/2025 | 02/21/2025 | 7 | 3 | 4 | 02/24/2025 | 02/24/2025 | 38 | 20 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | NORTHAMPTON | 607157 | 01060 | 9.135 | Solar | 05_05_313W1 | 04/27/2024 | 06/24/2024 | 39 | 34 | 5 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 8/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 659777 | 01532 | 7.6 | Solar | 05_07_69J1 | 12/11/2024 | 01/21/2025 | 3 | 0 | 3 | 01/22/2025 | 01/22/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/3/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | BROCKTON | 430893 | 02302 | 6.67 | Solar | 05_05_7L4 | 06/16/2022 | 06/21/2022 | 2 | 0 | 2 | 06/22/2022 | 06/22/2022 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 7/28/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2022 | Connected |  | N
National Grid | REHOBOTH | 739114 | 02769 | 17.92 | Solar | 05_12_22W2 | 12/17/2025 | 12/22/2025 | 3 | 2 | 1 | 12/23/2025 | 12/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/15/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | LYNN | 197613 | 01902 | 875 | Solar | 05_09_1109W1 | 11/14/2018 | 11/29/2018 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 | 01/15/2019 | 31 | 12 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 336658 | 01230 | 66.6 | Solar | 05_07_96W41 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 3/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 177046 | 02025 | 1350 | Solar | 05_07_912W75 | 10/17/2016 | 10/17/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/23/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 461539 | 02324 | 10 | Solar | 05_09_516L1 | 02/22/2023 | 02/23/2023 | 1 | 0 | 1 | 02/24/2023 | 02/24/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/21/2023 | Connected |  | N
National Grid | WALES | 678931 | 01081 | 5.76 | Solar | 05_05_335W3 | 03/18/2025 | 04/01/2025 | 4 | 0 | 4 | 04/09/2025 | 04/09/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/8/2025 | 03/18/2025 | 6/2/2026 | Y | EXP | 365 | 08/28/2025 | 10/18/2025 | 52 | 0 | 52 |  |  | 10/29/2025 | Connected |  | N
National Grid | UPTON | 671633 | 01568 | 17.6 | Solar | 05_09_901W3 | 02/18/2025 | 03/03/2025 | 10 | 6 | 4 | 03/04/2025 | 03/04/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2025 | Connected |  | N
National Grid | NORTHAMPTON | 624536 | 01060 | 3.78 | Solar | 05_05_313W1 | 07/12/2024 | 07/26/2024 | 3 | 1 | 2 | 07/29/2024 | 07/29/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2024 | 07/12/2024 | 9/28/2025 | Y | EXP | 365 | 10/03/2024 | 10/24/2024 | 22 | 0 | 22 |  |  | 11/26/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 666267 | 01532 | 7.6 | Solar | 05_07_69J1 | 01/16/2025 | 02/13/2025 | 5 | 0 | 5 | 02/14/2025 | 02/14/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/16/2025 | 3/31/2026 | Y | EXP | 365 | 09/24/2025 | 10/23/2025 | 30 | 0 | 30 |  |  | 10/27/2025 | Connected |  | N
National Grid | BROCKTON | 432869 | 02302 | 7.6 | Solar | 05_05_7L4 | 07/04/2022 | 07/06/2022 | 2 | 0 | 2 | 07/07/2022 | 07/07/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2022 | 07/04/2022 | 8/15/2024 | Y | EXP | 365 | 10/14/2022 | 12/21/2022 | 69 | 0 | 69 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 174620 | 02769 | 60 | Solar | 05_12_22W3 | 02/18/2011 | 02/18/2011 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2011 |  | 1/6/2012 | N | EXP | 248 |  |  | 0 | 0 | 0 | 8/6/2012 | 8/6/2012 | 1/6/2012 | Connected |  | N
National Grid | LYNN | 204820 | 01902 | 0 | Solar | 05_09_1109W1 | 01/03/2019 | 01/11/2019 | 5 | 0 | 5 | 01/14/2019 | 01/14/2019 | 16 | 16 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2019 | 01/03/2019 | 5/12/2020 | Y | EXP | 365 | 03/13/2020 | 03/27/2020 | 14 | 0 | 14 |  |  | 4/20/2020 | Connected |  | N
National Grid | NEW MARLBOROUGH | 336653 | 01230 | 233.2 | Solar | 05_07_96W41 | 01/15/2021 | 01/26/2021 | 5 | 0 | 5 | 01/27/2021 | 01/27/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 177125 | 02025 | 1560 | Solar | 05_07_912W75 | 10/20/2016 | 10/20/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 | 11/22/2016 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2017 | 10/20/2016 | 12/31/2020 | Y | STD | 945 | 05/20/2020 | 12/12/2020 | 207 | 5 | 202 |  |  | 12/31/2020 | Connected |  | N
National Grid | HALIFAX | 485570 | 02338 | 0 | Solar | 05_09_516L1 | 12/14/2022 | 12/16/2022 | 2 | 0 | 2 | 12/19/2022 | 12/19/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2023 |  | 6/17/2024 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | BRIMFIELD | 680330 | 01010 | 10 | Solar | 05_05_335W3 | 03/25/2025 | 05/01/2025 | 26 | 23 | 3 | 05/02/2025 | 05/02/2025 | 19 | 1 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/3/2025 | 03/25/2025 | 7/21/2026 | Y | EXP | 365 | 09/13/2025 | 12/02/2025 | 81 | 0 | 81 |  |  | 12/11/2025 | Connected |  | N
National Grid | UPTON | 683804 | 01568 | 15.2 | Solar | 05_09_901W3 | 04/10/2025 | 04/18/2025 | 5 | 0 | 5 | 04/22/2025 | 04/22/2025 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2025 |  | 6/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/19/2025 | Connected |  | N
National Grid | NORTHAMPTON | 645344 | 01062 | 5.76 | Solar | 05_05_313W1 | 10/07/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2024 | 10/07/2024 | 12/16/2025 | Y | EXP | 365 | 01/16/2025 | 02/13/2025 | 29 | 0 | 29 |  |  | 2/19/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 714327 | 01532 | 7.6 | Solar | 05_07_69J1 | 08/25/2025 | 09/11/2025 | 11 | 6 | 5 | 09/12/2025 | 09/12/2025 | 94 | 77 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 476815 | 02302 | 13 | Solar | 05_05_7L4 | 12/02/2022 | 12/07/2022 | 3 | 0 | 3 | 12/08/2022 | 12/08/2022 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/18/2023 | 12/02/2022 | 8/11/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/23/2023 | Connected |  | N
National Grid | REHOBOTH | 174619 | 02769 | 350 | Solar | 05_12_22W3 | 02/18/2011 | 02/18/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2011 |  | 2/7/2012 | N | EXP | 29 |  |  | 0 | 0 | 0 | 8/3/2012 | 8/3/2012 | 2/7/2012 | Connected |  | N
National Grid | SWAMPSCOTT | 214597 | 01907 | 10 | Solar | 05_09_1109W1 | 04/01/2019 | 04/12/2019 | 8 | 1 | 7 | 04/15/2019 | 04/15/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2019 | 04/01/2019 | 4/22/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2019 | Connected |  | N
National Grid | MONTEREY | 341800 | 01245 | 11.4 | Solar | 05_07_96W41 | 02/11/2021 | 02/17/2021 | 2 | 0 | 2 | 02/18/2021 | 02/18/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 177212 | 02025 | 1000 | Solar | 05_07_912W75 | 06/07/2016 | 06/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2016 | 07/26/2016 | 32 | 14 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2017 | 06/07/2016 | 4/5/2019 | Y | STD | 778 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 576582 | 02338 | 10 | Solar | 05_09_516L1 | 01/03/2024 | 01/08/2024 | 4 | 2 | 2 | 01/09/2024 | 01/09/2024 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  | 2/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/14/2024 | Connected |  | N
National Grid | BRIMFIELD | 683416 | 01010 | 10 | Solar | 05_05_335W3 | 04/07/2025 | 04/11/2025 | 4 | 0 | 4 | 04/14/2025 | 04/14/2025 | 64 | 49 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/24/2025 | 04/07/2025 | 7/30/2026 | Y | EXP | 365 | 11/04/2025 | 12/02/2025 | 29 | 0 | 29 |  |  | 12/11/2025 | Connected |  | N
National Grid | MILFORD | 694423 | 01757 | 0 | Solar | 05_09_901W3 | 06/02/2025 | 06/05/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | NORTHAMPTON | 646139 | 01060 | 5.76 | Solar | 05_05_313W1 | 10/22/2024 | 11/12/2024 | 7 | 0 | 7 | 11/13/2024 | 11/13/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 10/22/2024 | 1/3/2026 | Y | EXP | 365 | 01/16/2025 | 02/27/2025 | 42 | 0 | 42 |  |  | 3/15/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 177066 | 01532 | 3.8 | Solar | 05_07_6W1 | 03/20/2017 | 03/20/2017 | 7 | 7 | 0 | 03/30/2017 | 03/30/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2017 | 03/20/2017 | 3/26/2018 | Y | EXP | 357 | 08/15/2017 | 09/01/2017 | 13 | 0 | 13 | 11/7/2017 | 11/7/2017 | 11/7/2017 | Connected |  | N
National Grid | BROCKTON | 497589 | 02302 | 10 | Solar | 05_05_7L4 | 02/10/2023 | 02/13/2023 | 1 | 0 | 1 | 02/14/2023 | 02/14/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/10/2023 | 6/8/2024 | Y | EXP | 365 | 05/06/2023 | 06/08/2023 | 34 | 0 | 34 |  |  | 7/18/2023 | Connected |  | N
National Grid | SEEKONK | 178037 | 02771 | 11.4 | Solar | 05_12_22W3 | 10/27/2017 | 10/27/2017 | 4 | 4 | 0 | 11/13/2017 | 11/13/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2017 |  | 11/5/2018 | N | EXP | 357 |  |  | 0 | 0 | 0 |  |  | 7/3/2018 | Connected |  | N
National Grid | SWAMPSCOTT | 292538 | 01907 | 7.6 | Solar | 05_09_1109W1 | 06/02/2020 | 06/15/2020 | 9 | 9 | 0 | 06/16/2020 | 06/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 6/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2020 | Connected |  | N
National Grid | NEW MARLBOROUGH | 352066 | 01259 | 7.6 | Solar | 05_07_96W41 | 04/21/2021 | 04/22/2021 | 0 | 0 | 0 | 04/23/2021 | 04/23/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2021 |  | 4/22/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2021 | Connected |  | N
National Grid | COHASSET | 178020 | 02025 | 828 | Solar | 05_07_912W75 | 06/29/2017 | 06/29/2017 | 48 | 48 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2017 | 11/27/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2018 | 06/29/2017 | 8/12/2021 | Y | STD | 57 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 596959 | 02338 | 23 | Solar | 05_09_516L1 | 03/14/2024 | 03/18/2024 | 2 | 0 | 2 | 03/19/2024 | 03/19/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/27/2024 | 03/14/2024 | 4/8/2025 | Y | EXP | 365 | 06/15/2024 | 06/14/2024 | 0 | 0 | 0 |  |  | 2/12/2025 | Connected |  | N
National Grid | BRIMFIELD | 686253 | 01010 | 11.52 | Solar | 05_05_335W3 | 04/18/2025 | 05/19/2025 | 4 | 0 | 4 | 06/04/2025 | 06/04/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | UPTON | 634775 | 01568 | 140 | Solar | 05_09_905W1 | 09/03/2024 | 10/09/2024 | 26 | 17 | 9 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2025 | 09/03/2024 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | NORTHAMPTON | 651516 | 01060 | 7.6 | Solar | 05_05_313W1 | 11/13/2024 | 01/15/2025 | 24 | 17 | 7 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 177084 | 01532 | 180 | Solar | 05_07_6W1 | 10/18/2016 | 10/18/2016 | 0 | 0 | 0 | 10/27/2017 | 10/27/2017 | 18 | 0 | 18 | 01/12/2018 | 02/16/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 02/16/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 3/30/2018 | 10/18/2016 | 6/9/2021 | Y | EXP | 651 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 531460 | 02302 | 15 | Solar | 05_05_7L4 | 07/03/2023 | 07/05/2023 | 2 | 1 | 1 | 07/06/2023 | 07/06/2023 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2023 |  | 8/16/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/11/2023 | Connected |  | N
National Grid | SEEKONK | 290037 | 02771 | 7.68 | Solar | 05_12_22W3 | 07/08/2020 | 07/15/2020 | 4 | 0 | 4 | 07/16/2020 | 07/16/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2020 | 07/08/2020 | 2/3/2022 | Y | EXP | 365 | 01/20/2021 | 03/22/2021 | 61 | 0 | 61 |  |  | 1/3/2022 | Connected |  | N
National Grid | SWAMPSCOTT | 301413 | 01907 | 10 | Solar | 05_09_1109W1 | 08/15/2020 | 09/03/2020 | 14 | 14 | 0 | 09/04/2020 | 09/04/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2020 |  | 9/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N
National Grid | NEW MARLBOROUGH | 409713 | 01259 | 7.6 | Solar | 05_07_96W41 | 02/08/2022 | 02/11/2022 | 4 | 3 | 1 | 02/14/2022 | 02/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2022 |  | 3/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/10/2022 | Connected |  | N
National Grid | COHASSET | 178158 | 02025 | 4950 | Solar | 05_07_912W75 | 12/22/2017 | 12/22/2017 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/09/2018 | 02/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2018 | 12/22/2017 | 12/18/2019 | Y | STD | 539 |  |  | 0 | 0 | 0 | 12/17/2019 | 12/16/2019 | 12/18/2019 | Connected |  | N
National Grid | HALIFAX | 600197 | 02338 | 0 | Solar | 05_09_516L1 | 04/18/2024 | 04/25/2024 | 5 | 3 | 2 | 04/26/2024 | 04/26/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2024 |  | 8/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOLLAND | 692742 | 01521 | 12.92 | Solar | 05_05_335W3 | 05/20/2025 | 06/02/2025 | 6 | 3 | 3 | 06/03/2025 | 06/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2025 | Connected |  | N
National Grid | UPTON | 662850 | 01568 | 100 | Solar | 05_09_905W1 | 12/30/2024 | 02/14/2025 | 32 | 22 | 10 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 653530 | 01060 | 10 | Solar | 05_05_313W1 | 11/18/2024 | 12/23/2024 | 6 | 0 | 6 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2025 | 11/18/2024 | 2/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 178014 | 01532 | 3.8 | Solar | 05_07_6W1 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/4/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 544824 | 02188 | 7.6 | Solar | 05_05_7L4 | 08/02/2023 | 08/07/2023 | 3 | 0 | 3 | 08/08/2023 | 08/08/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/5/2023 | 08/02/2023 | 10/9/2024 | Y | EXP | 365 | 11/10/2023 | 01/05/2024 | 57 | 3 | 54 |  |  | 2/3/2024 | Connected |  | N
National Grid | REHOBOTH | 547388 | 02769 | 130 | Solar | 05_12_22W5 | 08/11/2023 | 11/27/2023 | 72 | 61 | 11 | 11/28/2023 | 11/28/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | Y
National Grid | SWAMPSCOTT | 318967 | 01907 | 10 | Solar | 05_09_1109W1 | 10/13/2020 | 10/19/2020 | 4 | 4 | 0 | 10/20/2020 | 10/20/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/18/2020 |  | 10/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/21/2020 | Connected |  | N
National Grid | NEW MARLBOROUGH | 458657 | 01259 | 300 | Solar | 05_07_96W41 | 10/26/2022 | 12/19/2022 | 36 | 26 | 10 |  |  | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 264571 | 02025 | 7.6 | Solar | 05_07_912W75 | 11/14/2019 | 12/10/2019 | 17 | 16 | 1 | 12/11/2019 | 12/11/2019 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2020 | 11/14/2019 | 11/14/2020 | Y | EXP | 365 | 07/29/2020 | 08/15/2020 | 17 | 0 | 17 |  |  | 10/7/2020 | Connected |  | N
National Grid | HALIFAX | 623374 | 02338 | 10 | Solar | 05_09_516L1 | 07/09/2024 | 10/28/2024 | 49 | 45 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/28/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIMFIELD | 699488 | 01010 | 17.6 | Solar | 05_05_335W3 | 07/23/2025 | 07/30/2025 | 5 | 0 | 5 | 07/31/2025 | 07/31/2025 | 26 | 11 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 9/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | UPTON | 662255 | 01568 | 160 | Solar | 05_09_905W1 | 12/30/2024 | 02/14/2025 | 32 | 23 | 9 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | NORTHAMPTON | 655152 | 01060 | 7.6 | Solar | 05_05_313W1 | 11/19/2024 | 12/26/2024 | 6 | 0 | 6 | 12/27/2024 | 12/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178018 | 01532 | 7.6 | Solar | 05_07_6W1 | 06/29/2017 | 06/29/2017 | 4 | 3 | 1 | 07/06/2017 | 07/06/2017 | 140 | 0 | 140 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/4/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 554638 | 02184 | 20 | Solar | 05_05_7L4 | 09/11/2023 | 09/13/2023 | 2 | 0 | 2 | 09/14/2023 | 09/14/2023 | 113 | 96 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/21/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2024 | Connected |  | N
National Grid | REHOBOTH | 656725 | 02769 | 1.6 | Solar | 05_12_22W5 | 11/25/2024 | 12/24/2024 | 15 | 10 | 5 | 12/26/2024 | 12/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2025 |  | 2/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SWAMPSCOTT | 321762 | 01907 | 7.83 | Solar | 05_09_1109W1 | 10/26/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 10/28/2020 | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/7/2021 | Connected |  | N
National Grid | MONTEREY | 470354 | 01245 | 150 | Solar | 05_07_96W41 | 10/25/2022 | 03/17/2023 | 97 | 87 | 10 |  |  | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 271025 | 02025 | 7.6 | Solar | 05_07_912W75 | 01/30/2020 | 02/18/2020 | 11 | 11 | 0 | 02/19/2020 | 02/19/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2020 |  | 2/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 641124 | 02338 | 7.475 | Solar | 05_09_516L1 | 09/18/2024 | 10/08/2024 | 5 | 1 | 4 | 10/09/2024 | 10/09/2024 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 | 09/18/2024 | 11/25/2025 | Y | EXP | 365 | 01/30/2025 | 02/03/2025 | 5 | 0 | 5 |  |  | 6/10/2025 | Connected |  | N
National Grid | BRIMFIELD | 708240 | 01010 | 10 | Solar | 05_05_335W3 | 07/29/2025 | 09/09/2025 | 3 | 0 | 3 | 09/10/2025 | 09/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2025 | 07/29/2025 | 10/20/2026 | Y | EXP | 365 | 12/12/2025 | 01/27/2026 | 47 | 0 | 47 |  |  | 12/13/2025 | Connected |  | N
National Grid | UPTON | 726288 | 01568 | 0 | Battery Add-On | 05_09_905W1 | 10/14/2025 | 10/16/2025 | 2 | 0 | 2 | 10/17/2025 | 10/17/2025 | 95 | 25 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTHAMPTON | 660905 | 01060 | 10 | Solar | 05_05_313W1 | 12/16/2024 | 02/18/2025 | 5 | 0 | 5 | 02/19/2025 | 02/19/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 190503 | 01532 | 7.6 | Solar | 05_07_6W1 | 07/11/2018 | 08/16/2018 | 8 | 8 | 0 | 08/17/2018 | 08/17/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 578325 | 02188 | 0 | Solar | 05_05_7L4 | 12/15/2023 | 12/21/2023 | 4 | 3 | 1 | 12/22/2023 | 12/22/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 174345 | 02769 | 7.5 | Natural Gas | 05_12_2340 | 08/17/2010 | 08/17/2010 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/08/2010 | 10/21/2010 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2011 |  | 12/31/2016 | N | STD | 2145 |  |  | 0 | 0 | 0 | 4/19/2011 | 4/19/2011 |  | Withdrawn |  | Y
National Grid | WINTHROP | 321529 | 02152 | 17.98 | Solar | 05_09_1109W1 | 11/12/2020 | 11/18/2020 | 3 | 1 | 2 | 11/19/2020 | 11/19/2020 | 22 | 2 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/13/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 490600 | 01230 | 20.01 | Solar | 05_07_96W41 | 01/09/2023 | 01/19/2023 | 8 | 7 | 1 | 01/20/2023 | 01/20/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | COHASSET | 296274 | 02025 | 1500 | Solar | 05_07_912W75 | 07/10/2020 | 07/30/2020 | 14 | 9 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/31/2020 | 08/13/2020 | 10 | 3 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 | 07/10/2020 | 5/24/2023 | Y | STD | 56 | 07/26/2022 | 05/12/2023 | 290 | 0 | 290 |  |  | 5/24/2023 | Connected |  | N
National Grid | HALIFAX | 641914 | 02338 | 10 | Solar | 05_09_516L1 | 09/20/2024 | 10/25/2024 | 3 | 0 | 3 | 10/28/2024 | 10/28/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 | 09/20/2024 | 12/11/2025 | Y | EXP | 365 | 02/26/2025 | 02/25/2025 | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | HOLLAND | 710659 | 01521 | 23 | Solar | 05_05_335W3 | 08/12/2025 | 08/18/2025 | 4 | 0 | 4 | 08/19/2025 | 08/19/2025 | 34 | 18 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2026 | Connected |  | N
National Grid | UPTON | 739273 | 01568 |  | Solar | 05_09_905W1 | 12/31/2025 |  | 43 | 33 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | NORTHAMPTON | 662299 | 01060 | 0 | Solar | 05_05_313W1 | 01/09/2025 | 01/22/2025 | 8 | 4 | 4 | 01/23/2025 | 01/23/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/5/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 208280 | 01532 | 3.8 | Solar | 05_07_6W1 | 02/05/2019 | 02/13/2019 | 5 | 0 | 5 | 02/14/2019 | 02/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 597739 | 02188 | 10 | Solar | 05_05_7L4 | 03/20/2024 | 04/18/2024 | 21 | 18 | 3 | 04/19/2024 | 04/19/2024 | 9 | 3 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2024 |  | 5/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/17/2024 | Connected |  | N
National Grid | REHOBOTH | 175070 | 02769 | 200 | Solar | 05_12_2340 | 04/04/2013 | 04/04/2013 | 6 | 0 | 6 | 04/16/2013 | 04/16/2013 | 276 | 0 | 276 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/31/2013 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WINTHROP | 333580 | 02152 | 0 | Solar | 05_09_1109W1 | 12/30/2020 | 12/31/2020 | 0 | 0 | 0 | 01/04/2021 | 01/04/2021 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2021 |  | 6/5/2022 | N | EXP | 48 |  |  | 0 | 0 | 0 |  |  | 5/24/2022 | Connected |  | N
National Grid | MONTEREY | 583288 | 01245 | 0 | Battery Add-On | 05_07_96W41 | 01/12/2024 | 02/01/2024 | 13 | 10 | 3 | 02/02/2024 | 02/02/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2024 | 01/12/2024 | 3/29/2025 | Y | EXP | 365 | 05/08/2024 | 05/07/2024 | 0 | 0 | 0 |  |  | 5/8/2024 | Connected |  | N
National Grid | COHASSET | 434834 | 02025 | 3.8 | Solar | 05_07_912W75 | 09/20/2022 | 09/22/2022 | 2 | 0 | 2 | 09/23/2022 | 09/23/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2022 | 09/20/2022 | 2/10/2024 | Y | EXP | 365 | 02/01/2023 | 02/08/2023 | 8 | 0 | 8 |  |  | 4/28/2023 | Connected |  | N
National Grid | HALIFAX | 648806 | 02338 | 5.76 | Solar | 05_09_516L1 | 11/01/2024 | 11/19/2024 | 3 | 0 | 3 | 11/20/2024 | 11/20/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 11/01/2024 | 1/9/2026 | Y | EXP | 365 | 05/03/2025 | 05/08/2025 | 6 | 0 | 6 |  |  | 5/16/2025 | Connected |  | N
National Grid | BRIMFIELD | 717022 | 01010 | 4.94 | Solar | 05_05_335W3 | 09/05/2025 | 09/24/2025 | 1 | 0 | 1 | 10/22/2025 | 10/22/2025 | 39 | 28 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  | 1/7/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/16/2026 | Connected |  | N
National Grid | UPTON | 174897 | 01568 | 32.46 | Solar | 05_09_905W1 | 08/07/2012 | 08/07/2012 | 6 | 0 | 6 | 08/17/2012 | 08/17/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 3/15/2013 | 3/15/2013 | 4/3/2013 | Connected |  | N
National Grid | NORTHAMPTON | 668429 | 01060 | 17.225 | Solar | 05_05_313W1 | 02/04/2025 | 02/26/2025 | 15 | 10 | 5 | 02/27/2025 | 02/27/2025 | 30 | 11 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/29/2025 | Connected |  | Y
National Grid | NORTHBOROUGH | 209081 | 01532 | 7.6 | Solar | 05_07_6W1 | 03/01/2019 | 03/12/2019 | 6 | 0 | 6 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WEYMOUTH | 617561 | 02188 | 6 | Solar | 05_05_7L4 | 06/12/2024 | 07/02/2024 | 2 | 0 | 2 | 07/03/2024 | 07/03/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 | 06/12/2024 | 10/23/2025 | Y | EXP | 45 | 08/20/2024 | 08/19/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 739425 | 02771 | 10.26 | Solar | 05_12_23H2 | 12/15/2025 | 12/16/2025 | 1 | 0 | 1 | 12/17/2025 | 12/17/2025 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2025 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REVERE | 335591 | 02151 | 7.6 | Solar | 05_09_1109W1 | 01/07/2021 | 01/25/2021 | 11 | 11 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 |  | 6/7/2022 | N | EXP | 445 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 656393 | 01257 | 0 | Other | 05_07_96W41 | 02/14/2025 | 03/20/2025 | 24 | 14 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2025 | 04/17/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | COHASSET | 437722 | 02025 | 6 | Solar | 05_07_912W75 | 06/24/2022 | 06/28/2022 | 2 | 0 | 2 | 06/29/2022 | 06/29/2022 | 49 | 25 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2022 | 06/24/2022 | 12/21/2023 | Y | EXP | 365 | 12/22/2022 | 12/21/2022 | 0 | 0 | 0 |  |  | 1/26/2023 | Connected |  | N
National Grid | HALIFAX | 655409 | 02338 | 5.76 | Solar | 05_09_516L1 | 11/19/2024 | 12/18/2024 | 5 | 0 | 5 | 12/19/2024 | 12/19/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 11/19/2024 | 2/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/3/2025 | Connected |  | N
National Grid | HOLLAND | 720448 | 01521 | 10 | Solar | 05_05_335W3 | 09/22/2025 | 10/03/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 12 | 2 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 09/22/2025 | 11/18/2026 | Y | EXP | 365 | 01/15/2026 | 02/10/2026 | 27 | 0 | 27 |  |  | 2/14/2026 | Connected |  | N
National Grid | UPTON | 175420 | 01568 | 200 | Solar | 05_09_905W1 | 07/18/2014 | 07/18/2014 | 570 | 570 | 0 | 11/01/2016 | 11/01/2016 | 153 | 152 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/31/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 677961 | 01060 | 15.76 | Solar | 05_05_313W1 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 |  | 5/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 224808 | 01532 | 3.8 | Solar | 05_07_6W1 | 08/08/2019 | 08/13/2019 | 2 | 0 | 2 | 08/14/2019 | 08/14/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2019 |  | 8/17/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | WEYMOUTH | 644469 | 02188 | 7.6 | Solar | 05_05_7L4 | 10/02/2024 | 10/09/2024 | 3 | 0 | 3 | 10/10/2024 | 10/10/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 299137 | 02769 | 8 | Solar | 05_12_23H2 | 06/30/2020 | 07/29/2020 | 20 | 16 | 4 | 07/30/2020 | 07/30/2020 | 58 | 41 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/29/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REVERE | 364015 | 02151 | 0 | Solar | 05_09_1109W1 | 06/15/2021 | 07/06/2021 | 15 | 12 | 3 | 07/07/2021 | 07/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2021 |  | 9/20/2022 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MONTEREY | 443129 | 01245 | 15.2 | Solar | 05_07_96W42 | 07/11/2022 | 07/12/2022 | 1 | 0 | 1 | 07/13/2022 | 07/13/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 |  | 8/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2023 | Connected |  | N
National Grid | COHASSET | 473559 | 02025 | 10 | Solar | 05_07_912W75 | 11/17/2022 | 11/22/2022 | 3 | 0 | 3 | 11/23/2022 | 11/23/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2022 | 11/17/2022 | 6/27/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2023 | Connected |  | N
National Grid | HALIFAX | 666620 | 02338 | 10 | Solar | 05_09_516L1 | 01/18/2025 | 02/20/2025 | 5 | 1 | 4 | 02/21/2025 | 02/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/15/2025 | Connected |  | N
National Grid | HOLLAND | 195290 | 01521 | 0 | Other | 05_05_335W4 | 12/05/2018 | 03/18/2019 | 69 | 45 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/19/2019 | 04/24/2019 | 26 | 24 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2019 |  | 5/17/2026 | N | STD | 63 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | UPTON | 176063 | 01568 | 45 | Solar | 05_09_905W1 | 04/01/2015 | 04/01/2015 | 5 | 0 | 5 | 04/09/2015 | 04/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 4/12/2015 | N | EXP | 1 |  |  | 0 | 0 | 0 | 4/24/2015 | 4/24/2015 | 10/9/2015 | Connected |  | N
National Grid | NORTHAMPTON | 686739 | 01060 | 7.6 | Solar | 05_05_313W1 | 04/23/2025 |  | 84 | 80 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 235878 | 01532 | 7.6 | Solar | 05_07_6W1 | 07/05/2019 | 08/09/2019 | 25 | 25 | 0 | 08/12/2019 | 08/12/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2019 |  | 8/25/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/21/2020 | Connected |  | N
National Grid | WEYMOUTH | 648237 | 02188 | 7.6 | Solar | 05_05_7L4 | 10/30/2024 | 11/27/2024 | 6 | 0 | 6 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2025 | 10/30/2024 | 1/21/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | SEEKONK | 627048 | 02771 | 5 | Solar | 05_12_23H2 | 07/23/2024 | 07/25/2024 | 2 | 0 | 2 | 07/26/2024 | 07/26/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2024 |  | 8/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/9/2024 | Connected |  | N
National Grid | MANCHESTER | 451140 | 01944 | 7.6 | Solar | 05_09_1109W1 | 09/01/2022 | 09/08/2022 | 5 | 3 | 2 | 09/09/2022 | 09/09/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/28/2022 | 09/01/2022 | 12/22/2023 | Y | EXP | 365 | 11/15/2022 | 12/21/2022 | 37 | 0 | 37 |  |  | 2/8/2023 | Connected |  | N
National Grid | NORTHAMPTON | 739875 | 01244 | 15.2 | Solar | 05_07_96W43 | 12/12/2025 |  | 56 | 56 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | COHASSET | 475256 | 02025 | 3.8 | Solar | 05_07_912W75 | 11/22/2022 | 11/28/2022 | 3 | 0 | 3 | 11/29/2022 | 11/29/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/3/2023 |  | 5/21/2024 | N | EXP | 365 | 04/26/2023 | 05/19/2023 | 24 | 0 | 24 |  |  | 6/13/2023 | Connected |  | N
National Grid | HALIFAX | 669170 | 02338 | 10 | Solar | 05_09_516L1 | 01/31/2025 | 02/21/2025 | 4 | 0 | 4 | 02/24/2025 | 02/24/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2025 |  | 3/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/6/2025 | Connected |  | N
National Grid | WALES | 731683 | 01081 | 10 | Solar | 05_05_335W4 | 11/05/2025 | 11/05/2025 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 40 | 23 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | UPTON | 204335 | 01568 | 233.1 | Solar | 05_09_905W1 | 01/07/2019 | 01/18/2019 | 8 | 2 | 6 | 01/22/2019 | 01/22/2019 | 70 | 48 | 22 | 05/22/2019 | 08/27/2019 | 68 | 7 | 61 |  |  | 0 | 0 | 0 |  | 08/27/2019 | 68 | 7 | 61 |  |  | 0 | 0 | 0 | 9/12/2019 |  | 8/3/2020 | N | EXP | 172 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 699455 | 01060 | 16.403 | Solar | 05_05_313W1 | 07/03/2025 | 07/09/2025 | 3 | 0 | 3 | 07/10/2025 | 07/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 | 07/03/2025 | 8/11/2026 | Y | EXP | 365 | 10/03/2025 | 10/02/2025 | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 310769 | 01532 | 10 | Solar | 05_07_6W1 | 10/13/2020 | 10/20/2020 | 4 | 0 | 4 | 10/21/2020 | 10/21/2020 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2020 | 10/13/2020 | 12/1/2022 | Y | EXP | 365 | 06/02/2022 | 07/21/2022 | 50 | 0 | 50 |  |  | 9/22/2022 | Connected |  | Y
National Grid | WEYMOUTH | 659231 | 02188 | 12.35 | Solar | 05_05_7L4 | 12/10/2024 | 12/30/2024 | 13 | 11 | 2 | 12/31/2024 | 12/31/2024 | 83 | 61 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 5/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/12/2026 | Connected |  | N
National Grid | REHOBOTH | 429415 | 02769 | 10 | Solar | 05_12_23H3 | 06/28/2022 | 06/30/2022 | 2 | 0 | 2 | 07/01/2022 | 07/01/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2022 | Connected |  | Y
National Grid | MANCHESTER | 383151 | 01944 | 0 | Solar | 05_09_1109W1 | 09/21/2021 | 09/27/2021 | 5 | 4 | 1 | 09/28/2021 | 09/28/2021 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2021 |  | 10/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/19/2021 | Connected |  | N
National Grid | MONTEREY | 174137 | 01245 | 20.5 | Solar | 05_07_96W43 | 04/06/2012 | 04/06/2012 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2012 |  | 6/4/2012 | N | EXP | 59 |  |  | 0 | 0 | 0 | 1/4/2013 | 1/4/2013 | 1/11/2013 | Connected |  | N
National Grid | NORWELL | 477830 | 02061 | 10 | Solar | 05_07_912W75 | 01/16/2023 | 01/17/2023 | 1 | 0 | 1 | 01/18/2023 | 01/18/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/16/2023 |  | 4/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2023 | Connected |  | N
National Grid | HALIFAX | 697076 | 02338 | 12.35 | Solar | 05_09_516L1 | 06/19/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/2/2025 |  | 12/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/12/2026 | Connected |  | N
National Grid | HOLLAND | 738359 | 01521 | 11.5 | Solar | 05_05_335W4 | 12/05/2025 | 12/09/2025 | 2 | 0 | 2 | 12/10/2025 | 12/10/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 217557 | 01757 | 7.6 | Solar | 05_09_905W1 | 04/30/2020 | 05/04/2020 | 2 | 2 | 0 | 05/05/2020 | 05/05/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2020 | 04/30/2020 | 5/3/2021 | Y | EXP | 365 | 09/09/2020 | 09/08/2020 | 0 | 0 | 0 |  |  | 12/4/2020 | Connected |  | N
National Grid | NORTHAMPTON | 737612 | 01060 | 17.16 | Solar | 05_05_313W1 | 12/02/2025 | 12/08/2025 | 4 | 0 | 4 | 12/09/2025 | 12/09/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2026 |  | 2/9/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | NORTHBOROUGH | 316632 | 01532 | 3.8 | Solar | 05_07_6W1 | 11/03/2020 | 11/09/2020 | 3 | 0 | 3 | 11/10/2020 | 11/10/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 662401 | 02188 | 5.51 | Solar | 05_05_7L4 | 12/26/2024 | 01/29/2025 | 15 | 5 | 10 | 01/30/2025 | 01/30/2025 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/26/2024 | 2/3/2026 | Y | EXP | 365 | 02/27/2025 | 02/26/2025 | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | REHOBOTH | 641448 | 02769 | 11.4 | Solar | 05_12_23H3 | 09/19/2024 | 09/24/2024 | 4 | 0 | 4 | 12/03/2024 | 12/03/2024 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/24/2024 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | MANCHESTER | 532774 | 01944 | 15.2 | Solar | 05_09_1109W1 | 06/09/2023 | 06/12/2023 | 1 | 0 | 1 | 06/13/2023 | 06/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONTEREY | 176289 | 01245 | 18.4 | Solar | 05_07_96W43 | 07/10/2015 | 07/10/2015 | 11 | 11 | 0 | 07/28/2015 | 07/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2015 | 07/10/2015 | 7/18/2016 | Y | EXP | 347 | 01/20/2015 | 09/03/2015 | 156 | 11 | 145 | 8/15/2016 | 8/15/2016 | 8/15/2016 | Connected |  | N
National Grid | NORWELL | 493922 | 02061 | 10 | Solar | 05_07_912W75 | 01/31/2023 | 02/02/2023 | 2 | 0 | 2 | 02/03/2023 | 02/03/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 696525 | 02338 | 13.36 | Solar | 05_09_516L1 | 06/30/2025 | 07/08/2025 | 4 | 3 | 1 | 07/09/2025 | 07/09/2025 | 34 | 19 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2025 |  | 9/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WALES | 743765 | 01081 | 60 | Solar | 05_05_335W4 | 01/06/2026 | 02/06/2026 | 19 | 10 | 9 | 02/09/2026 | 02/09/2026 | 20 | 5 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HOPEDALE | 253402 | 01747 | 10 | Solar | 05_09_905W1 | 09/30/2019 | 10/01/2019 | 1 | 1 | 0 | 10/02/2019 | 10/02/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2019 | 09/30/2019 | 5/21/2020 | Y | EXP |  | 12/19/2019 | 12/18/2019 | 0 | 0 | 0 |  |  | 12/19/2019 | Connected |  | N
National Grid | NORTHAMPTON | 614470 | 01060 | 240 | Solar | 05_05_313W2 | 06/07/2024 | 07/09/2024 | 20 | 13 | 7 |  |  | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2025 | 06/07/2024 | 2/21/2027 | Y | STD | 364 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | NORTHBOROUGH | 319521 | 01532 | 6.48 | Solar | 05_07_6W1 | 10/27/2020 | 11/13/2020 | 11 | 9 | 2 | 11/16/2020 | 11/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2020 |  | 11/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/17/2021 | Connected |  | Y
National Grid | WEYMOUTH | 685042 | 02188 | 22.8 | Solar | 05_05_7L4 | 04/14/2025 | 04/22/2025 | 5 | 0 | 5 | 04/23/2025 | 04/23/2025 | 33 | 16 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  | 7/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | REHOBOTH | 176130 | 02769 | 7.1 | Solar | 05_12_23W1 | 04/14/2015 | 04/14/2015 | 1 | 0 | 1 | 04/15/2015 | 04/15/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2015 |  | 8/31/2015 | N | EXP | 136 |  |  | 0 | 0 | 0 | 7/2/2015 | 7/2/2015 | 7/6/2015 | Connected |  | N
National Grid | MANCHESTER | 573964 | 01944 | 10 | Solar | 05_09_1109W1 | 11/29/2023 | 11/30/2023 | 2 | 1 | 1 | 12/01/2023 | 12/01/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 1/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 177100 | 01230 | 20 | Solar | 05_07_96W43 | 05/26/2016 | 05/26/2016 | 3 | 3 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2016 |  | 5/31/2017 | N | EXP | 352 |  |  | 0 | 0 | 0 | 9/2/2016 | 9/2/2016 | 9/2/2016 | Connected |  | N
National Grid | NORWELL | 577395 | 02061 | 6.144 | Solar | 05_07_912W75 | 01/03/2024 | 01/08/2024 | 4 | 2 | 2 | 01/09/2024 | 01/09/2024 | 24 | 1 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2024 | 01/03/2024 | 2/25/2025 | Y | EXP | 365 | 07/30/2024 | 09/13/2024 | 44 | 0 | 44 |  |  | 8/3/2024 | Connected |  | N
National Grid | HALIFAX | 701480 | 02338 | 9.57 | Solar | 05_09_516L1 | 06/26/2025 | 07/14/2025 | 1 | 0 | 1 | 07/17/2025 | 07/17/2025 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2025 |  | 8/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2025 | Connected |  | N
National Grid | WALES | 750231 | 01081 | 5.76 | Solar | 05_05_335W4 | 02/10/2026 | 02/13/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | MILFORD | 280785 | 01757 | 3.8 | Solar | 05_09_905W1 | 03/03/2020 | 03/25/2020 | 16 | 16 | 0 | 03/26/2020 | 03/26/2020 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/30/2020 | 03/03/2020 | 3/25/2021 | Y | EXP | 365 | 10/08/2020 | 10/26/2020 | 18 | 0 | 18 |  |  | 10/28/2020 | Connected |  | N
National Grid | NORTHAMPTON | 621987 | 01060 | 300 | Solar | 05_05_313W2 | 05/30/2025 | 10/15/2025 | 94 | 85 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2025 | 11/03/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBOROUGH | 477444 | 01532 | 10 | Solar | 05_07_6W1 | 12/20/2022 | 12/26/2022 | 4 | 0 | 4 | 12/27/2022 | 12/27/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2023 | 12/20/2022 | 9/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2023 | Connected |  | N
National Grid | WEYMOUTH | 686152 | 02188 | 24.7 | Solar | 05_05_7L4 | 04/18/2025 | 04/28/2025 | 4 | 0 | 4 | 04/29/2025 | 04/29/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/9/2025 | Connected |  | N
National Grid | REHOBOTH | 177338 | 02769 | 433 | Solar | 05_12_23W1 | 09/01/2016 | 09/01/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/06/2016 | 11/18/2016 | 51 | 46 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/6/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MANCHESTER | 588172 | 01944 | 15.2 | Solar | 05_09_1109W1 | 02/06/2024 | 02/08/2024 | 2 | 0 | 2 | 02/09/2024 | 02/09/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2024 | Connected |  | Y
National Grid | MONTEREY | 177286 | 01245 | 0 | Solar | 05_07_96W43 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 | 06/16/2016 | 06/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2016 |  | 6/21/2017 | N | EXP | 288 |  |  | 0 | 0 | 0 | 3/16/2017 | 3/16/2017 | 3/21/2017 | Connected |  | N
National Grid | NORWELL | 612382 | 02061 | 7.6 | Solar | 05_07_912W75 | 05/20/2024 | 05/28/2024 | 3 | 0 | 3 | 05/29/2024 | 05/29/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 | 05/20/2024 | 8/22/2025 | Y | EXP | 365 | 09/07/2024 | 10/18/2024 | 42 | 0 | 42 |  |  | 12/7/2024 | Connected |  | N
National Grid | HALIFAX | 708954 | 02338 | 15.2 | Solar | 05_09_516L1 | 08/01/2025 | 08/07/2025 | 4 | 0 | 4 | 08/08/2025 | 08/08/2025 | 45 | 34 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIMFIELD | 176021 | 01010 | 820 | Natural Gas | 05_05_335W4 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 05/20/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 |  | 12/31/2016 | N | STD | 438 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | MILFORD | 309324 | 01757 | 6 | Solar | 05_09_905W1 | 08/31/2020 | 09/03/2020 | 2 | 0 | 2 | 09/04/2020 | 09/04/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2020 | 08/31/2020 | 11/8/2021 | Y | EXP | 365 | 09/10/2021 | 10/01/2021 | 19 | 0 | 19 |  |  | 10/27/2021 | Connected |  | Y
National Grid | NORTHAMPTON | 664586 | 01060 | 960 | Solar | 05_05_313W2 | 05/19/2025 | 07/10/2025 | 34 | 24 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/11/2025 | 08/07/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBOROUGH | 645162 | 01532 | 3.8 | Solar | 05_07_6W1 | 10/07/2024 | 10/28/2024 | 4 | 0 | 4 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2024 | 10/07/2024 | 12/4/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | WEYMOUTH | 691988 | 02191 | 15.2 | Solar | 05_05_7L4 | 06/02/2025 | 06/04/2025 | 2 | 1 | 1 | 06/05/2025 | 06/05/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2025 |  | 7/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | REHOBOTH | 178391 | 02769 | 476 | Solar | 05_12_23W1 | 03/02/2018 | 03/02/2018 | 4 | 0 | 4 | 03/08/2018 | 03/08/2018 | 58 | 37 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 12/31/2020 | N | EXP | 487 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 597196 | 01906 | 6 | Solar | 05_09_1109W1 | 03/20/2024 | 03/21/2024 | 1 | 0 | 1 | 03/22/2024 | 03/22/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 |  | 5/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 177295 | 01230 | 12.8 | Solar | 05_07_96W43 | 08/26/2016 | 08/26/2016 | 0 | 0 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2016 | 08/26/2016 | 9/3/2017 | Y | EXP | 338 | 02/24/2017 | 02/24/2017 | 0 | 0 | 0 | 8/10/2017 | 8/10/2017 | 8/10/2017 | Connected |  | N
National Grid | NORWELL | 618832 | 02061 | 10 | Solar | 05_07_912W75 | 06/18/2024 | 07/09/2024 | 2 | 0 | 2 | 07/10/2024 | 07/10/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2024 | 06/18/2024 | 8/22/2025 | Y | EXP | 365 | 10/04/2024 | 10/21/2024 | 18 | 0 | 18 |  |  | 11/15/2024 | Connected |  | N
National Grid | HALIFAX | 716785 | 02338 | 12 | Solar | 05_09_516L1 | 09/08/2025 | 10/06/2025 | 3 | 2 | 1 | 11/04/2025 | 11/04/2025 | 19 | 5 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/3/2025 |  | 12/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | BRIMFIELD | 176865 | 01010 | 820 | Natural Gas | 05_05_335W4 | 03/23/2015 | 03/23/2015 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/26/2015 | 05/20/2015 | 38 | 0 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2015 |  | 1/27/2016 | N | STD | 99 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | MILFORD | 337254 | 01757 | 0 | Solar | 05_09_905W1 | 01/21/2021 | 01/26/2021 | 2 | 1 | 1 | 01/27/2021 | 01/27/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2021 |  | 1/25/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2021 | Connected |  | N
National Grid | NORTHAMPTON | 670266 | 01060 | 960 | Solar | 05_05_313W2 | 10/01/2025 | 11/23/2025 | 35 | 25 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 | 12/23/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBOROUGH | 661199 | 01532 | 5.76 | Solar | 05_07_6W1 | 12/17/2024 | 01/10/2025 | 6 | 0 | 6 | 01/13/2025 | 01/13/2025 | 25 | 0 | 25 | 03/07/2025 | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  | 04/08/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 | 4/14/2025 | 12/17/2024 | 4/21/2026 | Y | EXP | 365 | 05/29/2025 | 10/02/2025 | 127 | 0 | 127 |  |  | 11/24/2025 | Connected |  | N
National Grid | WEYMOUTH | 701920 | 02189 | 23 | Solar | 05_05_7L4 | 06/30/2025 | 07/28/2025 | 18 | 16 | 2 | 07/29/2025 | 07/29/2025 | 18 | 0 | 18 | 08/27/2025 | 09/11/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 09/11/2025 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 10/6/2026 | N | EXP | 365 | 11/01/2025 | 11/19/2025 | 19 | 0 | 19 |  |  | 11/26/2025 | Connected |  | N
National Grid | REHOBOTH | 194458 | 02769 | 720 | Solar | 05_12_23W1 | 01/15/2019 | 02/26/2019 | 28 | 20 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/27/2019 | 03/25/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 608340 | 01906 | 15.2 | Solar | 05_09_1109W1 | 05/02/2024 | 05/15/2024 | 10 | 9 | 1 | 05/16/2024 | 05/16/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 177460 | 01230 | 20 | Solar | 05_07_96W43 | 12/09/2016 | 12/09/2016 | 0 | 0 | 0 | 12/12/2016 | 12/12/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2016 |  | 12/17/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 | 1/30/2017 | 1/30/2017 | 2/9/2017 | Connected |  | N
National Grid | NORWELL | 620094 | 02061 | 6 | Solar | 05_07_912W75 | 07/08/2024 | 07/26/2024 | 1 | 0 | 1 | 07/29/2024 | 07/29/2024 | 36 | 25 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 |  | 10/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2024 | Connected |  | N
National Grid | HALIFAX | 440640 | 02338 | 1940 | Solar | 05_09_516L2 | 11/07/2022 | 05/15/2023 | 128 | 118 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/16/2023 | 06/12/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | HOLLAND | 177364 | 01521 | 50 | Solar | 05_05_335W4 | 06/24/2016 | 06/24/2016 | 1 | 1 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2016 |  | 7/2/2017 | N | EXP | 36 |  |  | 0 | 0 | 0 | 1/20/2017 | 1/20/2017 | 1/24/2017 | Connected |  | N
National Grid | MILFORD | 343658 | 01757 | 7.6 | Solar | 05_09_905W1 | 03/08/2021 | 04/22/2021 | 31 | 26 | 5 | 04/23/2021 | 04/23/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 737222 | 01060 | 0 | Battery Add-On | 05_05_313W2 | 12/01/2025 | 12/02/2025 | 1 | 0 | 1 |  |  | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHBOROUGH | 678608 | 01532 | 15.925 | Solar | 05_07_6W1 | 03/17/2025 | 04/03/2025 | 7 | 4 | 3 | 04/04/2025 | 04/04/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2025 | 03/17/2025 | 6/4/2026 | Y | EXP | 365 | 09/03/2025 | 11/20/2025 | 79 | 0 | 79 |  |  | 12/26/2025 | Connected |  | N
National Grid | WEYMOUTH | 712964 | 02188 | 21.4 | Solar | 05_05_7L4 | 08/18/2025 | 08/20/2025 | 2 | 0 | 2 | 08/21/2025 | 08/21/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2025 |  | 9/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/17/2025 | Connected |  | N
National Grid | SEEKONK | 194758 | 02771 | 375 | Natural Gas | 05_12_23W1 | 10/12/2018 | 10/31/2018 | 12 | 0 | 12 |  |  | 51 | 27 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2020 |  | 12/31/2020 | N | STD | 365 | 10/28/2020 | 10/27/2020 | 0 | 0 | 0 | 10/28/2020 | 12/17/2020 | 12/17/2020 | Connected |  | N
National Grid | SAUGUS | 614859 | 01906 | 15 | Solar | 05_09_1109W1 | 06/03/2024 | 06/05/2024 | 3 | 2 | 1 | 06/06/2024 | 06/06/2024 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/8/2024 |  | 8/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 177937 | 01230 | 18 | Solar | 05_07_96W43 | 06/20/2017 | 06/20/2017 | 7 | 7 | 0 | 06/29/2017 | 06/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2017 |  | 6/25/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 | 11/14/2017 | 11/14/2017 | 12/5/2017 | Connected |  | N
National Grid | NORWELL | 647227 | 02061 | 4956 | Solar | 05_07_912W75 | 11/15/2024 | 12/18/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2024 | 01/27/2025 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HALIFAX | 175165 | 02338 | 1000 | Solar | 05_09_516L2 | 05/10/2011 | 05/10/2011 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/27/2011 | 07/07/2011 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 05/10/2011 | 12/31/2012 | Y | STD | 129 | 10/07/2013 | 12/13/2013 | 46 | 0 | 46 | 12/17/2013 | 12/17/2013 | 12/27/2013 | Connected |  | N
National Grid | WALES | 324127 | 01081 | 10 | Solar | 05_05_335W4 | 11/30/2020 | 12/02/2020 | 1 | 0 | 1 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2021 | 11/30/2020 |  | Y | EXP | 365 | 05/14/2021 | 05/13/2021 | 0 | 0 | 0 |  |  | 7/16/2021 | Connected |  | N
National Grid | MILFORD | 375139 | 01757 | 11.4 | Solar | 05_09_905W1 | 08/10/2021 | 09/09/2021 | 22 | 21 | 1 | 09/10/2021 | 09/10/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2021 |  | 11/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/23/2022 | Connected |  | N
National Grid | NORTHAMPTON | 174471 | 01060 | 285 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | NORTHBOROUGH | 679356 | 01532 | 3.8 | Solar | 05_07_6W1 | 03/20/2025 | 07/10/2025 | 3 | 0 | 3 | 07/29/2025 | 07/29/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 03/20/2025 | 9/10/2026 | Y | EXP | 365 | 10/01/2025 | 09/30/2025 | 0 | 0 | 0 |  |  | 10/28/2025 | Connected |  | N
National Grid | WEYMOUTH | 714365 | 02188 | 11.4 | Solar | 05_05_7L4 | 08/28/2025 | 09/17/2025 | 5 | 0 | 5 | 10/01/2025 | 10/01/2025 | 22 | 7 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 | 08/28/2025 | 11/6/2026 | Y | EXP | 365 | 12/06/2025 | 01/23/2026 | 49 | 0 | 49 |  |  | 1/26/2026 | Connected |  | N
National Grid | REHOBOTH | 219650 | 02769 | 7.6 | Solar | 05_12_23W1 | 04/24/2019 | 05/01/2019 | 5 | 5 | 0 | 05/02/2019 | 05/02/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/3/2019 | 04/24/2019 | 6/11/2020 | Y | EXP | 365 | 02/25/2020 | 03/10/2020 | 14 | 0 | 14 |  |  | 5/15/2020 | Connected |  | Y
National Grid | SAUGUS | 617730 | 01906 | 3.42 | Solar | 05_09_1109W1 | 06/13/2024 | 06/20/2024 | 2 | 0 | 2 | 06/21/2024 | 06/21/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MONTEREY | 203231 | 01245 | 10 | Solar | 05_07_96W43 | 01/15/2019 | 01/30/2019 | 9 | 0 | 9 | 01/31/2019 | 01/31/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2019 | 01/15/2019 | 2/25/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2019 | Connected |  | N
National Grid | NORWELL | 651650 | 02061 | 10 | Solar | 05_07_912W75 | 11/13/2024 | 12/11/2024 | 7 | 3 | 4 | 12/12/2024 | 12/12/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2025 | 11/13/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HALIFAX | 175255 | 02338 | 480 | Solar | 05_09_516L2 | 01/07/2015 | 01/07/2015 | 10 | 8 | 2 | 01/23/2015 | 01/23/2015 | 464 | 0 | 464 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2015 |  | 12/31/2016 | N | EXP | 653 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 324890 | 01083 | 3.8 | Solar | 05_05_335W4 | 12/04/2020 | 12/08/2020 | 1 | 0 | 1 | 12/09/2020 | 12/09/2020 | 31 | 13 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2021 | Connected |  | N
National Grid | HOPEDALE | 419834 | 01747 | 10 | Solar | 05_09_905W1 | 04/13/2022 | 04/14/2022 | 1 | 0 | 1 | 04/15/2022 | 04/15/2022 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2022 | 04/13/2022 | 8/17/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/7/2022 | Connected |  | N
National Grid | NORTHAMPTON | 174470 | 01060 | 95 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/20/2012 | Connected |  | N
National Grid | NORTHBOROUGH | 676966 | 01532 | 999.9 | Solar | 05_07_6W2 | 04/08/2025 | 06/10/2025 | 43 | 34 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/11/2025 | 07/10/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WEYMOUTH | 738773 | 02188 | 15.76 | Solar | 05_05_7L5 | 12/08/2025 | 12/11/2025 | 3 | 0 | 3 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 2/23/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REHOBOTH | 306578 | 02769 | 6 | Solar | 05_12_23W1 | 09/04/2020 | 09/10/2020 | 2 | 0 | 2 | 09/11/2020 | 09/11/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2020 | 09/04/2020 | 9/1/2021 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2021 | Connected |  | N
National Grid | SAUGUS | 640176 | 01906 | 10 | Solar | 05_09_1109W1 | 09/16/2024 | 10/15/2024 | 2 | 1 | 1 | 10/16/2024 | 10/16/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2024 |  | 11/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | Y
National Grid | GREAT BARRINGTON | 202681 | 01230 | 10 | Solar | 05_07_96W43 | 12/12/2018 | 01/10/2019 | 16 | 14 | 2 | 01/11/2019 | 01/11/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/16/2019 |  | 7/1/2019 | N | EXP | 166 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | NORWELL | 653187 | 02061 | 5.76 | Solar | 05_07_912W75 | 11/08/2024 | 11/25/2024 | 8 | 4 | 4 | 11/26/2024 | 11/26/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2025 | 11/08/2024 | 1/29/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/29/2025 | Connected |  | N
National Grid | HALIFAX | 176291 | 02338 | 21.4 | Solar | 05_09_516L2 | 07/10/2015 | 07/10/2015 | 1 | 1 | 0 | 07/14/2015 | 07/14/2015 | 302 | 0 | 302 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 7/18/2016 | N | EXP | 354 |  |  | 0 | 0 | 0 | 7/30/2015 | 7/30/2015 |  | Withdrawn |  | Y
National Grid | WARREN | 402412 | 01083 | 0 | Battery Add-On | 05_05_335W4 | 02/01/2022 | 02/09/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/10/2022 | 11/22/2022 | 196 | 194 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 468492 | 01747 | 10 | Solar | 05_09_905W1 | 11/02/2022 | 11/03/2022 | 1 | 0 | 1 | 11/04/2022 | 11/04/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2022 | 11/02/2022 | 1/4/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2023 | Connected |  | N
National Grid | NORTHAMPTON | 174469 | 01060 | 120 | Solar | 05_05_313W2 | 05/06/2011 | 05/06/2011 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2011 | 05/06/2011 | 10/31/2012 | Y | EXP | 429 | 05/07/2012 | 07/19/2012 | 50 | 0 | 50 | 9/20/2012 | 9/20/2012 | 8/13/2012 | Connected |  | N
National Grid | NORTHBOROUGH | 177666 | 01532 | 3.8 | Solar | 05_07_6W2 | 05/24/2017 | 05/24/2017 | 3 | 3 | 0 | 05/31/2017 | 05/31/2017 | 207 | 0 | 207 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2017 |  | 5/30/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 747491 | 02188 | 5.76 | Solar | 05_05_7L5 | 01/26/2026 | 02/03/2026 | 5 | 3 | 2 | 02/04/2026 | 02/04/2026 | 21 | 7 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SEEKONK | 430334 | 02771 | 6 | Solar | 05_12_23W1 | 06/07/2022 | 06/14/2022 | 5 | 3 | 2 | 06/15/2022 | 06/15/2022 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 12/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 640782 | 01906 | 10 | Solar | 05_09_1109W1 | 09/17/2024 | 09/25/2024 | 2 | 0 | 2 | 09/26/2024 | 09/26/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2024 | 09/17/2024 | 11/1/2025 | Y | EXP | 365 | 02/19/2025 | 02/18/2025 | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 300341 | 01230 | 30 | Solar | 05_07_96W43 | 07/11/2020 | 11/10/2020 | 85 | 71 | 14 | 11/12/2020 | 11/12/2020 | 16 | 3 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2020 | 07/11/2020 | 7/9/2021 | Y | EXP | 365 | 02/18/2021 | 04/07/2021 | 48 | 0 | 48 |  |  | 6/4/2021 | Connected |  | N
National Grid | NORWELL | 670177 | 02061 | 6 | Solar | 05_07_912W75 | 02/05/2025 | 03/04/2025 | 11 | 7 | 4 | 03/05/2025 | 03/05/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  | 6/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2025 | Connected |  | N
National Grid | HALIFAX | 177637 | 02338 | 8730 | Solar | 05_09_516L2 | 07/20/2017 | 09/05/2017 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/05/2017 | 09/28/2017 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2018 |  | 3/19/2021 | N | STD | 652 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 521118 | 01083 | 6 | Solar | 05_05_335W4 | 05/03/2023 | 05/08/2023 | 3 | 0 | 3 | 05/09/2023 | 05/09/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 484829 | 01757 | 120 | Solar | 05_09_905W1 | 12/21/2022 | 03/06/2023 | 49 | 38 | 11 |  |  | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 176385 | 01060 | 480 | Solar | 05_05_313W2 | 12/01/2015 | 12/01/2015 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2015 | 12/18/2015 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2016 |  | 8/1/2017 | N | STD | 326 |  |  | 0 | 0 | 0 | 6/21/2017 | 6/21/2017 | 7/6/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 199236 | 01532 | 10 | Solar | 05_07_6W2 | 11/13/2018 | 01/28/2019 | 49 | 45 | 4 | 01/29/2019 | 01/29/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 153683 | 02191 | 15.2 | Solar | 05_05_7L5 | 02/02/2017 | 02/02/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2017 |  | 2/2/2018 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 630162 | 02769 | 6 | Solar | 05_12_23W1 | 08/05/2024 | 09/04/2024 | 8 | 5 | 3 | 09/05/2024 | 09/05/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2024 | 08/05/2024 | 10/1/2025 | Y | EXP | 365 | 12/18/2024 | 03/27/2025 | 100 | 0 | 100 |  |  | 4/8/2025 | Connected |  | N
National Grid | SAUGUS | 646157 | 01906 | 20 | Solar | 05_09_1109W1 | 10/10/2024 | 10/14/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NEW MARLBOROUGH | 342336 | 01259 | 7.6 | Solar | 05_07_96W43 | 02/16/2021 | 02/17/2021 | 0 | 0 | 0 | 02/18/2021 | 02/18/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2021 | 02/16/2021 | 1/9/2023 | Y | EXP | 45 | 09/14/2021 | 10/11/2021 | 28 | 0 | 28 |  |  | 12/5/2022 | Connected |  | N
National Grid | NORWELL | 670583 | 02061 | 17.16 | Solar | 05_07_912W75 | 02/17/2025 | 02/21/2025 | 5 | 2 | 3 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2025 | Connected |  | N
National Grid | HALIFAX | 177767 | 02338 | 5000 | Solar | 05_09_516L2 | 10/06/2017 | 11/08/2017 | 17 | 17 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/08/2017 | 12/13/2017 | 23 | 5 | 18 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 566642 | 01083 | 7.6 | Solar | 05_05_335W4 | 11/15/2023 | 11/27/2023 | 7 | 0 | 7 | 11/28/2023 | 11/28/2023 | 59 | 40 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 11/15/2023 | 3/8/2025 | Y | EXP | 365 | 07/17/2024 | 08/09/2024 | 24 | 0 | 24 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 485578 | 01747 | 120 | Solar | 05_09_905W1 | 12/21/2022 | 03/07/2023 | 50 | 40 | 10 |  |  | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 177359 | 01060 | 10.5 | Solar | 05_05_313W2 | 06/21/2016 | 06/21/2016 | 3 | 3 | 0 | 06/28/2016 | 06/28/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2016 | 06/21/2016 | 6/28/2017 | Y | EXP | 344 | 11/01/2016 | 12/07/2016 | 24 | 0 | 24 | 1/17/2017 | 1/17/2017 | 1/23/2017 | Connected |  | N
National Grid | NORTHBOROUGH | 205952 | 01532 | 13.6 | Solar | 05_07_6W2 | 02/14/2019 | 02/20/2019 | 2 | 1 | 1 | 02/21/2019 | 02/21/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 22 | 05/16/2019 | 06/06/2019 | 21 | 0 | 21 |  |  | 8/16/2019 | Connected |  | N
National Grid | WEYMOUTH | 173295 | 02191 | 3.8 | Solar | 05_05_7L5 | 07/10/2018 | 07/19/2018 | 6 | 0 | 6 | 07/20/2018 | 07/20/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 649256 | 02769 | 11.4 | Solar | 05_12_23W1 | 11/18/2024 | 12/04/2024 | 1 | 0 | 1 | 12/05/2024 | 12/05/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | Y
National Grid | SAUGUS | 651583 | 01906 | 23 | Solar | 05_09_1109W1 | 11/05/2024 | 11/07/2024 | 3 | 1 | 2 | 11/08/2024 | 11/08/2024 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 3/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/24/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 344801 | 01230 | 15.2 | Solar | 05_07_96W43 | 03/03/2021 | 03/09/2021 | 3 | 0 | 3 | 03/10/2021 | 03/10/2021 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2021 | Connected |  | N
National Grid | NORWELL | 677740 | 02061 | 11.52 | Solar | 05_07_912W75 | 03/13/2025 | 03/19/2025 | 4 | 0 | 4 | 03/20/2025 | 03/20/2025 | 77 | 57 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2025 |  | 8/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2025 | Connected |  | N
National Grid | HANSON | 186081 | 02341 | 4950 | Solar | 05_09_516L2 | 05/24/2018 | 05/24/2018 | 31 | 30 | 1 |  |  | 13 | 10 | 3 |  |  | 0 | 0 | 0 | 07/25/2018 | 07/24/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 575857 | 01083 | 3.77 | Solar | 05_05_335W4 | 12/20/2023 | 12/27/2023 | 3 | 1 | 2 | 12/28/2023 | 12/28/2023 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2024 |  | 6/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 545579 | 01757 | 4.06 | Solar | 05_09_905W1 | 08/09/2023 | 08/10/2023 | 1 | 0 | 1 | 08/11/2023 | 08/11/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2023 | 08/09/2023 | 9/13/2024 | Y | EXP | 365 | 10/10/2023 | 10/09/2023 | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | NORTHAMPTON | 178636 | 01060 | 10 | Solar | 05_05_313W2 | 04/09/2018 | 04/09/2018 | 8 | 0 | 8 | 04/20/2018 | 04/20/2018 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2018 |  | 4/15/2019 | N | EXP | 215 |  |  | 0 | 0 | 0 |  |  | 6/12/2019 | Connected |  | N
National Grid | MARLBOROUGH | 296209 | 01752 | 12 | Solar | 05_07_6W2 | 06/12/2020 | 06/29/2020 | 10 | 6 | 4 | 06/30/2020 | 06/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2020 |  | 10/25/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 174188 | 02191 | 2000 | Solar | 05_05_7L5 | 03/14/2012 | 03/14/2012 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 688318 | 02769 | 7.6 | Solar | 05_12_23W1 | 04/29/2025 | 05/29/2025 | 1 | 0 | 1 | 05/30/2025 | 05/30/2025 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 04/29/2025 | 7/9/2026 | Y | EXP | 365 | 10/18/2025 | 12/02/2025 | 46 | 0 | 46 |  |  | 12/4/2025 | Connected |  | N
National Grid | SAUGUS | 651917 | 01902 | 10 | Solar | 05_09_1109W1 | 11/04/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2024 |  | 1/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 376126 | 01230 | 19 | Solar | 05_07_96W43 | 08/16/2021 | 08/18/2021 | 2 | 0 | 2 | 08/19/2021 | 08/19/2021 | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2021 |  | 1/26/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/28/2022 | Connected |  | N
National Grid | NORWELL | 703294 | 02061 | 10 | Solar | 05_07_912W75 | 07/07/2025 | 08/04/2025 | 2 | 0 | 2 | 08/05/2025 | 08/05/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2025 | 07/07/2025 | 9/9/2026 | Y | EXP | 365 | 09/24/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 10/10/2025 | Connected |  | N
National Grid | HALIFAX | 486284 | 02338 | 7.6 | Solar | 05_09_516L2 | 01/17/2023 | 01/18/2023 | 1 | 0 | 1 | 01/19/2023 | 01/19/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/22/2023 | 01/17/2023 | 11/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/5/2024 | Connected |  | N
National Grid | WARREN | 600151 | 01083 | 6 | Solar | 05_05_335W4 | 04/01/2024 | 04/03/2024 | 2 | 0 | 2 | 04/04/2024 | 04/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2024 | 04/01/2024 | 4/19/2025 | Y | EXP | 365 | 07/23/2024 | 07/22/2024 | 0 | 0 | 0 |  |  | 8/2/2024 | Connected |  | N
National Grid | MILFORD | 675548 | 01757 | 11.5 | Solar | 05_09_905W1 | 03/04/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 |  | 5/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2025 | Connected |  | N
National Grid | NORTHAMPTON | 188768 | 01060 | 120 | Solar | 05_05_313W2 | 07/04/2018 | 07/04/2018 | 8 | 0 | 8 | 07/18/2018 | 07/18/2018 | 276 | 26 | 250 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WESTBOROUGH | 410224 | 01581 | 15.2 | Solar | 05_07_6W2 | 02/03/2022 | 04/05/2022 | 43 | 25 | 18 | 04/06/2022 | 04/06/2022 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 174912 | 02191 | 1000 | Solar | 05_05_7L5 | 09/18/2012 | 09/18/2012 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/28/2012 | 12/26/2012 | 44 | 0 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2013 | 09/18/2012 | 6/30/2014 | Y | STD | 181 | 05/05/2014 | 07/17/2014 | 50 | 0 | 50 | 7/2/2014 | 7/2/2014 | 7/15/2014 | Connected |  | N
National Grid | REHOBOTH | 659868 | 02769 | 2.32 | Solar | 05_12_23W2 | 12/11/2024 | 01/06/2025 | 1 | 0 | 1 | 01/07/2025 | 01/07/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 652064 | 01906 | 10 | Solar | 05_09_1109W1 | 11/05/2024 | 12/19/2024 | 2 | 0 | 2 | 12/20/2024 | 12/20/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2025 | 11/05/2024 | 2/6/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | NEW MARLBOROUGH | 500310 | 01259 | 8.7 | Solar | 05_07_96W43 | 02/17/2023 | 02/21/2023 | 1 | 0 | 1 | 02/22/2023 | 02/22/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2023 |  | 8/1/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/25/2023 | Connected |  | N
National Grid | NORWELL | 714206 | 02061 | 11.5 | Solar | 05_07_912W75 | 08/25/2025 | 09/16/2025 | 2 | 0 | 2 | 09/19/2025 | 09/19/2025 | 30 | 17 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 | 08/25/2025 | 11/12/2026 | Y | EXP | 365 | 11/26/2025 | 01/29/2026 | 65 | 0 | 65 |  |  | 2/3/2026 | Connected |  | N
National Grid | HALIFAX | 498553 | 02338 | 5000 | Solar | 05_09_516L2 | 06/01/2023 | 07/17/2023 | 30 | 21 | 9 |  |  | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 621415 | 01083 | 16 | Solar | 05_05_335W4 | 07/02/2024 | 07/12/2024 | 7 | 5 | 2 | 07/15/2024 | 07/15/2024 | 40 | 26 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2024 |  | 9/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 679353 | 01757 | 12.215 | Solar | 05_09_905W1 | 03/20/2025 | 04/01/2025 | 4 | 0 | 4 | 04/24/2025 | 04/24/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2025 |  | 6/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2025 | Connected |  | N
National Grid | NORTHAMPTON | 205688 | 01060 | 250 | Solar | 05_05_313W2 | 01/10/2019 | 01/16/2019 | 2 | 0 | 2 | 01/17/2019 | 01/17/2019 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 481330 | 01532 | 15.2 | Solar | 05_07_6W2 | 11/30/2022 | 12/05/2022 | 3 | 2 | 1 | 12/06/2022 | 12/06/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 6/9/2025 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WEYMOUTH | 175170 | 02191 | 1500 | Solar | 05_05_7L5 | 11/15/2012 | 11/15/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2012 | 01/07/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/22/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 669124 | 02771 | 7.6 | Solar | 05_12_23W2 | 02/04/2025 | 02/24/2025 | 3 | 0 | 3 | 02/25/2025 | 02/25/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2025 |  | 4/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | SAUGUS | 653655 | 01906 | 23 | Solar | 05_09_1109W1 | 11/12/2024 | 11/27/2024 | 12 | 10 | 2 | 12/02/2024 | 12/02/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 511876 | 01230 | 13.6 | Solar | 05_07_96W43 | 03/17/2023 | 04/04/2023 | 13 | 11 | 2 | 04/05/2023 | 04/05/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2023 |  | 6/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/29/2023 | Connected |  | N
National Grid | NORWELL | 728843 | 02061 | 15.2 | Solar | 05_07_912W75 | 10/27/2025 | 11/04/2025 | 5 | 1 | 4 | 11/05/2025 | 11/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2026 | Connected |  | Y
National Grid | HALIFAX | 663930 | 02338 | 10 | Solar | 05_09_516L2 | 01/06/2025 | 01/14/2025 | 5 | 3 | 2 | 01/15/2025 | 01/15/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | WARREN | 630854 | 01083 | 3.8 | Solar | 05_05_335W4 | 08/07/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 710970 | 01757 | 7.6 | Solar | 05_09_905W1 | 08/11/2025 | 09/23/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 20 | 4 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/2/2026 | Connected |  | N
National Grid | NORTHAMPTON | 306227 | 01060 | 11.4 | Solar | 05_05_313W2 | 08/11/2020 | 08/13/2020 | 1 | 0 | 1 | 08/14/2020 | 08/14/2020 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2020 |  | 8/12/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/17/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 489983 | 01532 | 15.2 | Solar | 05_07_6W2 | 01/05/2023 | 01/06/2023 | 1 | 0 | 1 | 01/09/2023 | 01/09/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2023 |  | 2/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | WEYMOUTH | 175303 | 02191 | 4800 | Solar | 05_05_7L5 | 06/24/2014 | 06/24/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/02/2014 | 08/04/2014 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 712857 | 02769 | 3.8 | Solar | 05_12_23W2 | 08/18/2025 | 09/19/2025 | 15 | 11 | 4 | 10/22/2025 | 10/22/2025 | 30 | 12 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 668424 | 01906 | 10 | Solar | 05_09_1109W1 | 01/28/2025 | 02/24/2025 | 15 | 11 | 4 | 02/25/2025 | 02/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 541284 | 01257 | 15.2 | Solar | 05_07_96W43 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/23/2023 |  | 9/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2023 | Connected |  | N
National Grid | NORWELL | 750336 | 02061 | 20.9 | Solar | 05_07_913W17 | 02/11/2026 | 02/27/2026 | 11 | 9 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HALIFAX | 719487 | 02338 | 17.16 | Solar | 05_09_516L3 | 09/16/2025 | 09/22/2025 | 4 | 0 | 4 | 09/23/2025 | 09/23/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 10/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WARREN | 653665 | 01083 | 7.6 | Solar | 05_05_335W4 | 11/15/2024 | 04/08/2025 | 80 | 75 | 5 | 04/09/2025 | 04/09/2025 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 672161 | 01757 | 217.3 | Solar | 05_09_909W1 | 02/25/2025 | 03/14/2025 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2025 | 04/18/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2025 |  | 6/20/2026 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 318450 | 01060 | 15.2 | Solar | 05_05_313W2 | 10/09/2020 | 10/14/2020 | 1 | 0 | 1 | 10/15/2020 | 10/15/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/4/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 494588 | 01532 | 9.86 | Solar | 05_07_6W2 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 | 02/09/2023 | 6/22/2024 | Y | EXP | 365 | 06/09/2023 | 06/22/2023 | 14 | 0 | 14 |  |  | 7/29/2023 | Connected |  | N
National Grid | WEYMOUTH | 175591 | 02191 | 1670 | Solar | 05_05_7L5 | 04/23/2014 | 04/23/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/05/2014 | 06/02/2014 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2014 | 04/23/2014 | 12/31/2016 | Y | STD | 757 | 10/19/2015 | 02/18/2016 | 82 | 0 | 82 | 12/21/2015 | 12/21/2015 | 12/24/2015 | Connected |  | N
National Grid | REHOBOTH | 726137 | 02769 | 15.2 | Solar | 05_12_23W2 | 12/15/2025 | 12/18/2025 | 3 | 0 | 3 | 12/19/2025 | 12/19/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2026 |  | 1/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 669592 | 01906 | 9.12 | Solar | 05_09_1109W1 | 02/03/2025 | 02/11/2025 | 6 | 2 | 4 | 02/12/2025 | 02/12/2025 | 48 | 24 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | NEW MARLBOROUGH | 562218 | 01230 | 17.45 | Solar | 05_07_96W43 | 10/12/2023 | 11/06/2023 | 17 | 15 | 2 | 11/07/2023 | 11/07/2023 | 42 | 24 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2024 |  | 1/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/25/2024 | Connected |  | N
National Grid | NORWELL | 749667 | 02061 | 15.76 | Solar | 05_07_913W17 | 02/06/2026 | 02/10/2026 | 2 | 0 | 2 | 02/11/2026 | 02/11/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HALIFAX | 752069 | 02338 | 15.2 | Solar | 05_09_516L3 | 02/19/2026 | 03/03/2026 | 6 | 2 | 4 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WARREN | 673496 | 01083 | 3.8 | Solar | 05_05_335W4 | 03/04/2025 | 03/10/2025 | 4 | 0 | 4 | 03/11/2025 | 03/11/2025 | 97 | 74 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/8/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/23/2025 | Connected |  | N
National Grid | HOPEDALE | 693642 | 01747 | 5.7 | Solar | 05_09_909W1 | 05/23/2025 | 10/23/2025 | 3 | 0 | 3 | 11/17/2025 | 11/17/2025 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 | 05/23/2025 | 12/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 323644 | 01060 | 7.6 | Solar | 05_05_313W2 | 02/23/2021 | 02/24/2021 | 0 | 0 | 0 | 02/25/2021 | 02/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2021 |  | 2/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 515717 | 01532 | 7.6 | Solar | 05_07_6W2 | 03/30/2023 | 03/31/2023 | 1 | 0 | 1 | 04/03/2023 | 04/03/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2023 |  | 5/8/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | WEYMOUTH | 175813 | 02191 | 40 | Solar | 05_05_7L5 | 05/18/2015 | 05/18/2015 | 3 | 3 | 0 | 05/27/2015 | 05/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 10/30/2015 | N | EXP | 144 |  |  | 0 | 0 | 0 | 6/24/2015 | 6/24/2015 | 11/23/2015 | Connected |  | N
National Grid | REHOBOTH | 727782 | 02769 | 6 | Solar | 05_12_23W2 | 10/20/2025 | 10/21/2025 | 1 | 0 | 1 | 10/22/2025 | 10/22/2025 | 23 | 8 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/24/2025 |  | 12/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 688366 | 01906 | 5.76 | Solar | 05_09_1109W1 | 04/29/2025 | 06/13/2025 | 1 | 0 | 1 | 06/23/2025 | 06/23/2025 | 29 | 16 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/6/2025 |  | 9/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | GREAT BARRINGTON | 583818 | 01230 | 21.735 | Solar | 05_07_96W43 | 01/19/2024 | 02/13/2024 | 18 | 16 | 2 | 02/14/2024 | 02/14/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/15/2024 | Connected |  | N
National Grid | NORWELL | 175351 | 02061 | 440.8 | Solar | 05_07_913W17 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2014 |  | 12/31/2014 | N | EXP | 56 |  |  | 0 | 0 | 0 | 12/23/2014 | 12/23/2014 | 12/31/2014 | Connected |  | N
National Grid | STOUGHTON | 174531 | 02072 | 1000 | Solar | 05_09_516L3 | 06/23/2011 | 06/23/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2011 | 08/04/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 06/23/2011 | 10/31/2012 | Y | STD | 68 | 10/21/2013 | 12/30/2013 | 47 | 0 | 47 | 7/24/2012 | 7/24/2012 | 12/27/2013 | Connected |  | N
National Grid | WARREN | 682810 | 01083 | 7.6 | Solar | 05_05_335W4 | 04/07/2025 | 05/06/2025 | 2 | 0 | 2 | 05/07/2025 | 05/07/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 | 04/07/2025 | 8/1/2026 | Y | EXP | 365 | 08/08/2025 | 08/24/2025 | 17 | 0 | 17 |  |  | 11/25/2025 | Connected |  | N
National Grid | MILFORD | 709319 | 01757 | 2.66 | Solar | 05_09_909W1 | 08/04/2025 | 10/28/2025 | 9 | 5 | 4 | 10/29/2025 | 10/29/2025 | 49 | 30 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 | 08/04/2025 | 2/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 326856 | 01060 | 8.4 | Solar | 05_05_313W2 | 12/03/2020 | 12/08/2020 | 2 | 0 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 12/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 520867 | 01532 | 10.15 | Solar | 05_07_6W2 | 05/05/2023 | 05/08/2023 | 1 | 0 | 1 | 05/09/2023 | 05/09/2023 | 20 | 3 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2023 |  | 6/12/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | WEYMOUTH | 175956 | 02191 | 239.8 | Solar | 05_05_7L5 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 07/18/2015 | 08/14/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 08/14/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/11/2015 |  | 6/30/2016 | N | EXP | 293 |  |  | 0 | 0 | 0 | 7/27/2016 | 7/27/2016 | 8/4/2016 | Connected |  | N
National Grid | REHOBOTH | 749919 | 02769 | 11.5 | Solar | 05_12_23W2 | 02/06/2026 | 02/11/2026 | 3 | 0 | 3 | 02/12/2026 | 02/12/2026 | 16 | 7 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 697491 | 01906 | 15.2 | Solar | 05_09_1109W1 | 06/10/2025 | 06/24/2025 | 3 | 0 | 3 | 06/25/2025 | 06/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 7/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/24/2025 | Connected |  | N
National Grid | MONTEREY | 600468 | 01245 | 0 | Solar | 05_07_96W43 | 05/03/2024 | 06/26/2024 | 36 | 34 | 2 | 06/27/2024 | 06/27/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/16/2024 |  | 8/28/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | NORWELL | 176799 | 02061 | 11.4 | Solar | 05_07_913W17 | 02/25/2016 | 02/25/2016 | 4 | 4 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2016 |  | 3/2/2017 | N | EXP | 363 |  |  | 0 | 0 | 0 | 11/3/2016 | 11/3/2016 | 11/7/2016 | Connected |  | N
National Grid | STOUGHTON | 174530 | 02072 | 1000 | Solar | 05_09_516L3 | 06/23/2011 | 06/23/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2011 | 08/04/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 06/23/2011 | 10/31/2012 | Y | STD | 68 | 10/21/2013 | 12/30/2013 | 47 | 0 | 47 | 7/24/2012 | 7/24/2012 | 12/27/2013 | Connected |  | N
National Grid | WARREN | 690548 | 01092 | 12.16 | Solar | 05_05_335W4 | 05/08/2025 | 05/21/2025 | 1 | 0 | 1 | 06/26/2025 | 06/26/2025 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2025 |  | 7/29/2026 | N | EXP | 365 | 09/09/2025 | 10/23/2025 | 45 | 0 | 45 |  |  | 1/3/2026 | Connected |  | N
National Grid | MILFORD | 177590 | 01757 | 6 | Solar | 05_09_909W1 | 05/18/2017 | 05/18/2017 | 63 | 63 | 0 | 08/21/2017 | 08/21/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2017 |  | 5/27/2018 | N | EXP | 272 |  |  | 0 | 0 | 0 | 2/15/2018 | 2/15/2018 | 2/15/2018 | Connected |  | N
National Grid | NORTHAMPTON | 334003 | 01060 | 10 | Solar | 05_05_313W2 | 12/30/2020 | 01/05/2021 | 2 | 0 | 2 | 01/06/2021 | 01/06/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 649005 | 01532 | 11.4 | Solar | 05_07_6W2 | 10/23/2024 | 11/11/2024 | 5 | 0 | 5 | 11/12/2024 | 11/12/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 | 10/23/2024 | 3/13/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | WEYMOUTH | 175955 | 02191 | 59.4 | Solar | 05_05_7L5 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 | 06/02/2015 | 06/02/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2015 |  | 6/30/2016 | N | EXP | 388 |  |  | 0 | 0 | 0 | 6/15/2015 | 6/15/2015 | 3/18/2016 | Connected |  | N
National Grid | SEEKONK | 175967 | 02771 | 11.4 | Solar | 05_12_23W2 | 08/06/2015 | 08/06/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2015 |  | 8/17/2016 | N | EXP | 344 |  |  | 0 | 0 | 0 | 4/6/2016 | 4/6/2016 | 4/26/2016 | Connected |  | N
National Grid | SAUGUS | 698592 | 01906 | 20 | Solar | 05_09_1109W1 | 06/16/2025 | 06/17/2025 | 1 | 0 | 1 | 06/18/2025 | 06/18/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2025 |  | 7/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2025 | Connected |  | N
National Grid | NEW MARLBOROUGH | 622833 | 01259 | 10 | Solar | 05_07_96W43 | 08/07/2024 | 08/13/2024 | 4 | 2 | 2 | 08/14/2024 | 08/14/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 |  | 9/18/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/25/2025 | Connected |  | N
National Grid | NORWELL | 177304 | 02061 | 650 | Solar | 05_07_913W17 | 11/15/2016 | 11/15/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2016 | 12/20/2016 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2017 | 11/15/2016 | 7/10/2018 | Y | STD | 441 | 10/09/2017 | 07/02/2018 | 266 | 0 | 266 |  |  | 7/9/2018 | Connected |  | N
National Grid | STOUGHTON | 174529 | 02072 | 1000 | Solar | 05_09_516L3 | 06/27/2011 | 06/27/2011 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2011 | 08/04/2011 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 06/27/2011 | 10/31/2012 | Y | STD | 68 | 10/21/2013 | 12/30/2013 | 47 | 0 | 47 | 7/24/2012 | 7/24/2012 | 12/27/2013 | Connected |  | N
National Grid | WARREN | 741154 | 01083 | 5.76 | Solar | 05_05_335W5 | 12/18/2025 | 12/18/2025 | 3 | 0 | 3 | 01/15/2026 | 01/15/2026 | 18 | 3 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | HOPEDALE | 178523 | 01747 | 66.6 | Solar | 05_09_909W1 | 04/04/2018 | 04/04/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/10/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 375628 | 01062 | 43.2 | Solar | 05_05_313W2 | 08/18/2021 | 11/20/2021 | 65 | 57 | 8 | 11/22/2021 | 11/22/2021 | 22 | 0 | 22 | 08/05/2022 | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  | 10/19/2022 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 1/5/2023 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/27/2025 | Connected |  | N
National Grid | WESTBOROUGH | 662609 | 01581 | 3.77 | Solar | 05_07_6W2 | 12/31/2024 | 02/07/2025 | 5 | 1 | 4 | 02/10/2025 | 02/10/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2025 | Connected |  | N
National Grid | WEYMOUTH | 176853 | 02191 | 1000 | Solar | 05_05_7L5 | 11/12/2015 | 11/12/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2015 | 12/16/2015 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/18/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 176687 | 02771 | 6 | Solar | 05_12_23W2 | 02/18/2016 | 02/18/2016 | 2 | 2 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 2/24/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/25/2016 | 8/25/2016 | 8/25/2016 | Connected |  | N
National Grid | SAUGUS | 698183 | 01906 | 15.2 | Solar | 05_09_1109W1 | 06/13/2025 | 07/07/2025 | 7 | 4 | 3 | 07/08/2025 | 07/08/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2025 |  | 8/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/10/2025 | Connected |  | N
National Grid | MONTEREY | 628857 | 01245 | 10 | Solar | 05_07_96W43 | 07/30/2024 | 08/07/2024 | 1 | 0 | 1 | 08/08/2024 | 08/08/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2024 | 07/30/2024 | 10/19/2025 | Y | EXP | 45 | 12/19/2024 | 01/27/2025 | 40 | 0 | 40 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 178049 | 02061 | 56 | Solar | 05_07_913W17 | 05/05/2017 | 05/05/2017 | 43 | 42 | 1 | 07/10/2017 | 07/10/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2017 |  | 5/13/2018 | N | EXP | 3 |  |  | 0 | 0 | 0 | 9/8/2017 | 9/8/2017 | 10/30/2017 | Connected |  | N
National Grid | STOUGHTON | 174718 | 02072 | 1000 | Solar | 05_09_516L3 | 01/14/2014 | 01/14/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2014 | 02/12/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 01/14/2014 | 2/24/2016 | Y | STD | 67 |  |  | 0 | 0 | 0 | 1/14/2014 | 1/14/2014 | 12/31/2015 | Connected |  | N
National Grid | WARREN | 753812 | 01083 |  | Battery Add-On | 05_05_335W5 | 03/02/2026 | 03/04/2026 | 2 | 0 | 2 | 03/05/2026 | 03/05/2026 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | HOPEDALE | 184686 | 01747 | 66.6 | Solar | 05_09_909W1 | 05/07/2018 | 05/07/2018 | 20 | 0 | 20 | 06/07/2018 | 06/07/2018 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2018 |  | 6/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 380928 | 01062 | 0 | Solar | 05_05_313W2 | 09/27/2021 | 12/16/2021 | 2 | 0 | 2 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/7/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 175158 | 01532 | 95 | Solar | 05_07_70J1 | 08/20/2012 | 08/20/2012 | 7 | 0 | 7 | 08/30/2012 | 08/30/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2012 |  | 11/1/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 | 4/2/2013 | 4/2/2013 | 6/18/2013 | Connected |  | N
National Grid | WEYMOUTH | 176997 | 02191 | 10 | Solar | 05_05_7L5 | 07/19/2016 | 07/19/2016 | 3 | 3 | 0 | 07/25/2016 | 07/25/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2016 | 07/19/2016 | 7/25/2017 | Y | EXP | 355 | 09/29/2016 | 10/11/2016 | 7 | 0 | 7 | 3/1/2017 | 3/1/2017 | 3/3/2017 | Connected |  | N
National Grid | REHOBOTH | 176722 | 02769 | 7.6 | Solar | 05_12_23W2 | 02/22/2016 | 02/22/2016 | 0 | 0 | 0 | 02/23/2016 | 02/23/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/29/2016 |  | 2/28/2017 | N | EXP | 365 |  |  | 0 | 0 | 0 | 8/17/2016 | 8/17/2016 | 8/19/2016 | Connected |  | N
National Grid | SAUGUS | 702327 | 01906 | 11.4 | Solar | 05_09_1109W1 | 07/01/2025 | 07/11/2025 | 7 | 6 | 1 | 07/14/2025 | 07/14/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/21/2025 |  | 8/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 633759 | 01230 | 15.2 | Solar | 05_07_96W43 | 08/26/2024 | 09/03/2024 | 6 | 5 | 1 | 09/04/2024 | 09/04/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 |  | 9/23/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/20/2024 | Connected |  | N
National Grid | NORWELL | 208597 | 02061 | 1000 | Solar | 05_07_913W17 | 03/22/2019 | 04/23/2019 | 20 | 11 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/24/2019 | 05/15/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 174716 | 02072 | 1000 | Solar | 05_09_516L3 | 01/13/2014 | 01/13/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2014 | 02/12/2014 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2014 | 01/13/2014 | 12/30/2015 | Y | STD | 551 |  |  | 0 | 0 | 0 | 1/13/2014 | 1/13/2014 | 12/31/2015 | Connected |  | N
National Grid | WARREN | 176052 | 01083 | 4.5 | Solar | 05_05_335W5 | 01/29/2015 | 01/29/2015 | 4 | 4 | 0 | 02/05/2015 | 02/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2015 |  | 6/30/2015 | N | EXP | 126 |  |  | 0 | 0 | 0 | 2/24/2015 | 2/24/2015 | 9/25/2015 | Connected |  | N
National Grid | MILFORD | 185190 | 01757 | 467 | Solar | 05_09_909W1 | 05/15/2018 | 05/15/2018 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/08/2018 | 06/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2018 |  | 3/2/2020 | N | STD | 445 |  |  | 0 | 0 | 0 |  |  | 12/30/2019 | Connected |  | N
National Grid | NORTHAMPTON | 478391 | 01060 | 0 | Other | 05_05_313W2 | 12/02/2022 | 04/07/2023 | 75 | 75 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/10/2023 | 10/26/2023 | 138 | 119 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 713540 | 01581 | 5.76 | Solar | 05_07_712J1 | 08/20/2025 | 09/19/2025 | 4 | 0 | 4 | 11/21/2025 | 11/21/2025 | 21 | 4 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2025 | 08/20/2025 | 1/2/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WEYMOUTH | 177503 | 02191 | 22.8 | Solar | 05_05_7L5 | 03/06/2017 | 03/06/2017 | 9 | 7 | 2 | 03/17/2017 | 03/17/2017 | 258 | 0 | 258 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2017 |  | 3/11/2018 | N | EXP | 355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 177143 | 02769 | 6 | Solar | 05_12_23W2 | 05/27/2016 | 05/27/2016 | 0 | 0 | 0 | 06/01/2016 | 06/01/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/27/2016 | 8/1/2017 | Y | EXP | 47 | 05/31/2017 | 06/14/2017 | 10 | 0 | 10 | 6/29/2017 | 6/29/2017 | 7/10/2017 | Connected |  | N
National Grid | SAUGUS | 722739 | 01906 | 15.2 | Solar | 05_09_1109W1 | 10/02/2025 | 10/07/2025 | 3 | 0 | 3 | 10/08/2025 | 10/08/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 644492 | 01257 | 9.86 | Solar | 05_07_96W43 | 10/08/2024 | 10/15/2024 | 2 | 0 | 2 | 10/16/2024 | 10/16/2024 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 225530 | 02061 | 3.8 | Solar | 05_07_913W17 | 03/05/2020 |  | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 175449 | 02072 | 990 | Solar | 05_09_516L3 | 03/12/2014 | 03/12/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/24/2014 | 04/21/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 | 03/12/2014 | 2/9/2016 | Y | STD | 314 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WARREN | 176094 | 01092 | 84 | Solar | 05_05_335W5 | 04/02/2015 | 04/02/2015 | 2 | 0 | 2 | 04/13/2015 | 04/13/2015 | 165 | 0 | 165 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2015 |  | 8/7/2015 | N | EXP | 116 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 185248 | 01757 | 4675 | Solar | 05_09_909W1 | 09/26/2018 | 10/08/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/09/2018 | 11/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 09/26/2018 | 1/16/2024 | Y | STD | 93 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 548448 | 01060 | 10 | Solar | 05_05_313W2 | 09/21/2023 | 09/22/2023 | 1 | 0 | 1 | 09/25/2023 | 09/25/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/17/2023 |  | 10/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/30/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 751944 | 01532 | 13.36 | Solar | 05_07_712J1 | 02/18/2026 | 02/24/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PEMBROKE | 177805 | 02359 | 496 | Solar | 05_05_7L5 | 10/12/2017 | 10/12/2017 | 30 | 23 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/08/2017 | 01/05/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2018 |  | 7/26/2019 | N | STD | 368 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 177796 | 02769 | 15.2 | Solar | 05_12_23W2 | 08/03/2017 | 08/03/2017 | 9 | 8 | 1 | 08/16/2017 | 08/16/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/17/2017 |  | 8/8/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  | 10/10/2018 | Connected |  | N
National Grid | SAUGUS | 725271 | 01906 | 21.38 | Solar | 05_09_1109W1 | 10/09/2025 | 10/13/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2026 | Connected |  | N
National Grid | GREAT BARRINGTON | 647263 | 01230 | 10 | Solar | 05_07_96W43 | 10/15/2024 | 11/15/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 46 | 23 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 412720 | 02061 | 243.3 | Solar | 05_07_913W17 | 02/16/2022 | 03/31/2022 | 30 | 21 | 9 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 | 02/16/2022 | 5/21/2025 | Y | STD | 56 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 175626 | 02072 | 990 | Solar | 05_09_516L3 | 08/05/2014 | 08/05/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/15/2014 | 09/15/2014 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/18/2016 | 12/14/2016 | 39 | 0 | 39 | 4/1/2015 | 08/05/2014 | 5/3/2017 | Y | STD | 763 | 10/18/2016 | 05/02/2017 | 133 | 0 | 133 | 4/21/2017 | 4/21/2017 | 5/3/2017 | Connected |  | N
National Grid | WARREN | 176171 | 01092 | 6 | Solar | 05_05_335W5 | 04/23/2015 | 04/23/2015 | 3 | 2 | 1 | 04/28/2015 | 04/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2015 |  | 8/31/2015 | N | EXP | 124 |  |  | 0 | 0 | 0 | 6/17/2015 | 6/17/2015 | 10/26/2015 | Connected |  | N
National Grid | MILFORD | 232983 | 01757 | 0 | Solar | 05_09_909W1 | 06/03/2019 | 06/12/2019 | 6 | 0 | 6 | 06/13/2019 | 06/13/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 11/7/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/9/2019 | Connected |  | N
National Grid | NORTHAMPTON | 571722 | 01062 | 10 | Solar | 05_05_313W2 | 11/21/2023 | 12/11/2023 | 14 | 11 | 3 | 12/12/2023 | 12/12/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/7/2024 | Connected |  | N
National Grid | MARLBOROUGH | 174588 | 01752 | 30 | Solar | 05_07_712J1 | 08/29/2011 | 08/29/2011 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2011 |  | 8/4/2012 | N | EXP | 264 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | BROCKTON | 177987 | 02302 | 15.2 | Solar | 05_05_7L5 | 08/28/2017 | 08/28/2017 | 35 | 31 | 4 | 10/20/2017 | 10/20/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2017 |  | 9/4/2018 | N | EXP | 319 |  |  | 0 | 0 | 0 | 12/11/2017 | 12/11/2017 | 12/19/2017 | Connected |  | N
National Grid | REHOBOTH | 177866 | 02769 | 3.8 | Solar | 05_12_23W2 | 06/15/2017 | 06/15/2017 | 6 | 6 | 0 | 06/23/2017 | 06/23/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2017 | 06/15/2017 | 6/20/2018 | Y | EXP | 357 | 01/18/2018 | 03/28/2018 | 37 | 0 | 37 |  |  | 5/30/2018 | Connected |  | N
National Grid | SAUGUS | 469582 | 01906 | 20.88 | Solar | 05_09_1109W2 | 10/19/2022 | 10/24/2022 | 4 | 2 | 2 | 10/25/2022 | 10/25/2022 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 7/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SHEFFIELD | 466090 | 01257 | 10 | Solar | 05_07_913W17 | 10/13/2022 | 10/18/2022 | 3 | 0 | 3 | 10/19/2022 | 10/19/2022 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 |  | 11/17/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/28/2022 | Connected |  | N
National Grid | NORWELL | 176191 | 02061 | 496 | Solar | 05_09_516L3 | 07/24/2015 | 07/24/2015 | 0 | 0 | 0 | 09/03/2015 | 09/03/2015 | 233 | 0 | 233 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/8/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 176259 | 02072 | 18.06 | Solar | 05_05_335W5 | 09/04/2015 | 09/04/2015 | 4 | 4 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2015 |  | 9/12/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 12/23/2015 | 12/23/2015 | 12/23/2015 | Connected |  | N
National Grid | WARREN | 253195 | 01083 | 0 | Solar | 05_09_909W1 | 09/09/2019 | 09/10/2019 | 0 | 0 | 0 | 09/11/2019 | 09/11/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2019 |  | 9/8/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2020 | Connected |  | N
National Grid | MILFORD | 574880 | 01757 | 0 | Solar | 05_05_313W2 | 11/30/2023 | 12/12/2023 | 9 | 6 | 3 | 12/13/2023 | 12/13/2023 | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 175363 | 01096 | 5 | Solar | 05_07_712J1 | 11/14/2014 | 11/14/2014 | 4 | 0 | 4 | 11/21/2014 | 11/21/2014 | 442 | 0 | 442 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2014 |  | 1/31/2015 | N | EXP | 67 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 178457 | 01532 | 480 | Solar | 05_05_7L5 | 11/30/2017 | 11/30/2017 | 35 | 0 | 35 | 01/23/2018 | 01/23/2018 | 26 | 9 | 17 | 04/13/2018 | 06/11/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 |  | 06/11/2018 | 41 | 21 | 20 |  |  | 0 | 0 | 0 | 6/29/2018 |  | 4/15/2020 | N | EXP | 16 |  |  | 0 | 0 | 0 |  |  | 6/17/2020 | Connected |  | N
National Grid | BROCKTON | 177978 | 02302 | 7.6 | Solar | 05_12_23W2 | 06/28/2017 | 06/28/2017 | 5 | 2 | 3 | 07/06/2017 | 07/06/2017 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2017 |  | 7/3/2018 | N | EXP | 361 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 600570 | 02771 | 360 | Solar | 05_09_1109W2 | 06/03/2024 | 08/08/2024 | 46 | 38 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2024 | 08/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 06/03/2024 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | SAUGUS | 651477 | 01906 | 11.5 | Solar | 05_07_96W43 | 12/23/2024 | 02/12/2025 | 21 | 16 | 5 | 02/13/2025 | 02/13/2025 | 24 | 2 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2025 |  | 3/31/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2025 | Connected |  | N
National Grid | MONTEREY | 501289 | 01245 | 7.6 | Solar | 05_07_913W17 | 04/21/2023 | 04/24/2023 | 1 | 0 | 1 | 04/25/2023 | 04/25/2023 | 158 | 133 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 177905 | 02061 | 10 | Solar | 05_09_516L3 | 08/15/2017 | 08/15/2017 | 118 | 118 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/20/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 176534 | 02072 | 6 | Solar | 05_05_335W5 | 02/09/2016 | 02/09/2016 | 3 | 3 | 0 | 02/16/2016 | 02/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/8/2016 | 02/09/2016 | 2/15/2017 | Y | EXP | 344 | 05/11/2016 | 05/13/2016 | 2 | 0 | 2 | 5/1/2017 | 5/1/2017 | 5/5/2017 | Connected |  | N
National Grid | WARREN | 338313 | 01083 | 7.6 | Solar | 05_09_909W1 | 01/22/2021 | 01/25/2021 | 0 | 0 | 0 | 01/26/2021 | 01/26/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2021 |  | 3/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/27/2021 | Connected |  | N
National Grid | MILFORD | 644993 | 01757 | 8.7 | Solar | 05_05_313W2 | 10/04/2024 | 10/24/2024 | 3 | 1 | 2 | 10/25/2024 | 10/25/2024 | 47 | 23 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2025 |  | 1/22/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/10/2025 | Connected |  | N
National Grid | NORTHAMPTON | 175397 | 01060 | 475.2 | Solar | 05_07_712J1 | 11/17/2014 | 11/17/2014 | 4 | 0 | 4 | 11/24/2014 | 11/24/2014 | 242 | 4 | 238 | 07/31/2015 | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  | 11/16/2015 | 73 | 0 | 73 |  |  | 0 | 0 | 0 |  |  | 2/15/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 178485 | 01581 | 1000 | Solar | 05_05_7L5 | 04/03/2018 | 04/03/2018 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/25/2018 | 08/24/2018 | 44 | 26 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 194862 | 02302 | 17.6 | Solar | 05_12_23W2 | 10/08/2018 | 10/17/2018 | 6 | 0 | 6 | 10/18/2018 | 10/18/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2018 | 10/08/2018 | 6/15/2021 | Y | EXP | 53 | 12/18/2019 | 02/24/2020 | 68 | 0 | 68 |  |  | 6/2/2021 | Connected |  | N
National Grid | REHOBOTH | 725534 | 02769 | 15.2 | Solar | 05_09_1109W2 | 10/09/2025 | 10/21/2025 | 7 | 3 | 4 | 10/22/2025 | 10/22/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SAUGUS | 712799 | 01906 | 15.2 | Solar | 05_07_96W43 | 08/18/2025 |  | 12 | 11 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 588598 | 01230 | 0 | Solar | 05_07_913W17 | 02/07/2024 | 02/29/2024 | 15 | 13 | 2 | 03/01/2024 | 03/01/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2024 | 02/07/2024 | 5/21/2025 | Y | EXP | 365 | 09/05/2024 | 10/03/2024 | 29 | 0 | 29 |  |  | 10/4/2024 | Connected |  | N
National Grid | NORWELL | 178097 | 02061 | 4000 | Solar | 05_09_516L3 | 07/11/2017 | 07/27/2017 | 12 | 12 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/27/2017 | 08/22/2017 | 18 | 11 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2018 | 07/11/2017 | 8/20/2021 | Y | STD | 14 | 09/07/2019 | 04/29/2020 | 236 | 77 | 159 | 7/1/2021 | 7/29/2021 | 8/20/2021 | Connected |  | N
National Grid | STOUGHTON | 177176 | 02072 | 20.2 | Solar | 05_05_335W5 | 06/01/2016 | 06/01/2016 | 2 | 2 | 0 | 06/03/2016 | 06/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2016 | 06/01/2016 | 6/6/2017 | Y | EXP | 335 | 10/11/2016 | 10/11/2016 | 0 | 0 | 0 | 10/21/2016 | 10/21/2016 | 10/25/2016 | Connected |  | N
National Grid | WARREN | 483548 | 01092 | 3.8 | Solar | 05_09_909W1 | 12/20/2022 | 12/22/2022 | 2 | 0 | 2 | 12/23/2022 | 12/23/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2023 | 12/20/2022 | 6/30/2024 | Y | EXP | 365 | 05/16/2023 | 06/30/2023 | 45 | 0 | 45 |  |  | 7/25/2023 | Connected |  | N
National Grid | MILFORD | 666566 | 01757 | 3.8 | Solar | 05_05_313W2 | 01/17/2025 | 03/20/2025 | 10 | 6 | 4 | 03/21/2025 | 03/21/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | NORTHAMPTON | 176074 | 01062 | 7.6 | Solar | 05_07_712J1 | 08/19/2015 | 08/19/2015 | 3 | 3 | 0 | 08/24/2015 | 08/24/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 08/19/2015 | 8/24/2016 | Y | EXP | 35 | 01/11/2016 | 02/19/2016 | 27 | 0 | 27 | 5/16/2016 | 5/16/2016 | 5/20/2016 | Connected |  | N
National Grid | NORTHBOROUGH | 210282 | 01532 | 5 | Solar | 05_12_23W2 | 02/26/2019 | 03/05/2019 | 5 | 5 | 0 | 03/06/2019 | 03/06/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2019 | 02/26/2019 | 12/30/2019 | Y | EXP | 27 | 10/03/2019 | 11/26/2019 | 54 | 0 | 54 |  |  | 12/6/2019 | Connected |  | N
National Grid | BROCKTON | 174779 | 02302 | 1000 | Solar | 05_09_1109W2 | 01/21/2013 | 01/21/2013 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/07/2013 | 04/03/2013 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 717157 | 02771 | 10 | Solar | 05_07_96W43 | 09/08/2025 | 09/17/2025 | 6 | 4 | 2 | 09/18/2025 | 09/18/2025 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | SAUGUS | 666358 | 01906 | 5.76 | Solar | 05_07_913W17 | 01/17/2025 | 02/07/2025 | 4 | 0 | 4 | 02/10/2025 | 02/10/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2025 | 01/17/2025 | 3/19/2026 | Y | EXP | 365 | 06/21/2025 | 06/20/2025 | 0 | 0 | 0 |  |  | 7/31/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 178130 | 01230 | 3500 | Solar | 05_09_516L3 | 07/12/2017 | 08/22/2017 | 29 | 28 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/22/2017 | 09/13/2017 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 07/12/2017 | 6/10/2020 | Y | STD | 469 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SCITUATE | 177435 | 02066 | 366.3 | Solar | 05_05_335W5 | 06/29/2016 | 06/29/2016 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/06/2016 | 07/15/2016 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2016 | 06/29/2016 | 7/5/2017 | Y | STD | 232 | 03/08/2017 | 06/30/2017 | 80 | 0 | 80 | 8/16/2017 | 8/16/2017 | 8/16/2017 | Connected |  | N
National Grid | STOUGHTON | 498813 | 02072 | 6 | Solar | 05_09_909W1 | 02/03/2023 | 02/06/2023 | 1 | 0 | 1 | 02/07/2023 | 02/07/2023 | 66 | 48 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 5/31/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2023 | Connected |  | N
National Grid | WARREN | 708079 | 01092 | 11.05 | Solar | 05_05_313W2 | 08/12/2025 | 08/13/2025 | 1 | 0 | 1 | 08/14/2025 | 08/14/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 |  | 9/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | MILFORD | 176275 | 01757 | 10 | Solar | 05_07_712J1 | 05/01/2015 | 05/01/2015 | 70 | 70 | 0 | 08/18/2015 | 08/18/2015 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2015 | 05/01/2015 | 2/2/2019 | Y | EXP | 1242 | 11/10/2016 | 11/22/2016 | 7 | 0 | 7 |  |  | 1/31/2019 | Connected |  | N
National Grid | NORTHAMPTON | 178474 | 01062 | 636 | Solar | 05_05_7L5 | 03/07/2018 | 03/07/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/12/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 246187 | 01581 | 10 | Solar | 05_12_23W2 | 07/30/2019 | 10/07/2019 | 48 | 47 | 1 | 10/08/2019 | 10/08/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2019 |  | 7/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/19/2020 | Connected |  | N
National Grid | BROCKTON | 174778 | 02302 | 3000 | Solar | 05_09_1109W2 | 01/21/2013 | 01/21/2013 | 9 | 1 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/04/2013 | 04/03/2013 | 33 | 0 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | REHOBOTH | 710503 | 02769 | 11.5 | Solar | 05_07_96W44 | 08/07/2025 | 08/11/2025 | 2 | 0 | 2 | 08/12/2025 | 08/12/2025 | 141 | 25 | 116 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 684049 | 01906 | 22.8 | Solar | 05_07_913W17 | 04/09/2025 | 04/15/2025 | 4 | 0 | 4 | 04/16/2025 | 04/16/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2025 |  | 5/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/26/2025 | Connected |  | Y
National Grid | GREAT BARRINGTON | 178276 | 01230 | 825 | Solar | 05_09_516L3 | 02/22/2018 | 02/23/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/23/2018 | 04/06/2018 | 19 | 12 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 177723 | 02061 | 33.3 | Solar | 05_05_335W5 | 10/03/2017 | 10/03/2017 | 3 | 0 | 3 | 10/04/2017 | 10/04/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2017 |  | 10/9/2018 | N | EXP | 37 |  |  | 0 | 0 | 0 | 2/26/2018 | 2/26/2018 | 3/6/2018 | Connected |  | N
National Grid | STOUGHTON | 507310 | 02072 | 3.8 | Solar | 05_09_909W1 | 04/28/2023 | 05/01/2023 | 1 | 0 | 1 | 05/02/2023 | 05/02/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 711406 | 01083 | 5.76 | Solar | 05_05_313W2 | 08/13/2025 | 08/26/2025 | 11 | 7 | 4 | 09/16/2025 | 09/16/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/9/2025 | 08/13/2025 | 11/6/2026 | Y | EXP | 365 | 12/16/2025 | 12/15/2025 | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | MILFORD | 176437 | 01757 | 10 | Solar | 05_07_712J1 | 03/16/2016 | 03/16/2016 | 3 | 3 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/16/2016 | 3/21/2017 | Y | EXP | 343 | 12/14/2016 | 01/05/2017 | 14 | 0 | 14 | 1/19/2017 | 1/19/2017 | 1/23/2017 | Connected |  | N
National Grid | NORTHAMPTON | 178744 | 01062 | 726 | Solar | 05_05_7L5 | 05/29/2018 | 05/29/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2018 | 07/20/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2019 |  | 5/15/2020 | N | STD | 469 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 247703 | 01532 | 7.6 | Solar | 05_12_23W2 | 08/08/2019 | 09/11/2019 | 23 | 19 | 4 | 09/12/2019 | 09/12/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2019 | 08/08/2019 | 6/15/2021 | Y | EXP | 365 | 02/01/2020 | 03/03/2020 | 31 | 0 | 31 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 174851 | 02302 | 499 | Solar | 05_09_1109W2 | 08/06/2013 | 08/06/2013 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/20/2013 | 09/29/2014 | 275 | 0 | 275 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2015 | 08/06/2013 | 2/5/2016 | Y | STD | 364 | 09/02/2016 | 12/05/2016 | 62 | 0 | 62 | 11/7/2016 | 11/7/2016 | 11/14/2016 | Connected |  | N
National Grid | REHOBOTH | 174399 | 02769 | 13 | Solar | 05_07_96W44 | 06/15/2012 | 06/15/2012 | 5 | 0 | 5 | 06/26/2012 | 06/26/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2012 |  | 8/31/2012 | N | EXP | 59 |  |  | 0 | 0 | 0 | 10/2/2012 | 10/2/2012 | 11/29/2012 | Connected |  | N
National Grid | SAUGUS | 725102 | 01906 | 20.9 | Solar | 05_07_913W17 | 10/08/2025 | 10/10/2025 | 2 | 0 | 2 | 10/14/2025 | 10/14/2025 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 178306 | 01236 | 4750 | Solar | 05_09_516L3 | 01/09/2018 | 03/09/2018 | 41 | 31 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/04/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 178221 | 02061 | 15.2 | Solar | 05_05_335W5 | 04/13/2018 | 04/13/2018 | 13 | 0 | 13 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2018 |  | 4/21/2019 | N | EXP | 318 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | STOUGHTON | 514076 | 02072 | 9.86 | Solar | 05_09_909W1 | 04/14/2023 | 04/19/2023 | 2 | 0 | 2 | 04/20/2023 | 04/20/2023 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/24/2023 | 04/14/2023 | 6/6/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 8/28/2023 | Connected |  | N
National Grid | WARREN | 718595 | 01083 | 9.75 | Solar | 05_05_313W2 | 09/11/2025 | 11/17/2025 | 19 | 17 | 2 | 11/18/2025 | 11/18/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | MILFORD | 177178 | 01757 | 3.8 | Solar | 05_07_712J1 | 06/05/2016 | 06/05/2016 | 8 | 8 | 0 | 06/20/2016 | 06/20/2016 | 154 | 0 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2016 |  | 6/12/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 187621 | 01062 | 4998 | Solar | 05_05_7L5 | 06/10/2018 | 06/10/2018 | 57 | 3 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/30/2018 | 09/27/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 261261 | 01532 | 7.6 | Solar | 05_12_23W2 | 10/21/2019 | 10/24/2019 | 3 | 2 | 1 | 10/25/2019 | 10/25/2019 | 8 | 2 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2019 |  | 11/7/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/31/2020 | Connected |  | N
National Grid | BROCKTON | 174847 | 02302 | 30 | Solar | 05_09_1109W2 | 02/04/2013 | 02/04/2013 | 5 | 0 | 5 | 02/19/2013 | 02/19/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2013 |  | 4/30/2013 | N | EXP | 43 |  |  | 0 | 0 | 0 | 5/16/2013 | 5/16/2013 | 6/10/2013 | Connected |  | N
National Grid | REHOBOTH | 177157 | 02769 | 20.5 | Solar | 05_07_96W44 | 10/26/2016 | 10/26/2016 | 7 | 7 | 0 | 11/04/2016 | 11/04/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2016 |  | 10/31/2017 | N | EXP | 361 |  |  | 0 | 0 | 0 | 2/22/2017 | 2/22/2017 | 2/28/2017 | Connected |  | N
National Grid | SAUGUS | 720064 | 01906 | 25 | Solar | 05_07_913W18 | 09/18/2025 | 09/25/2025 | 5 | 3 | 2 | 09/26/2025 | 09/26/2025 | 84 | 69 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GREAT BARRINGTON | 178303 | 01236 | 6400 | Solar | 05_09_516L3 | 01/09/2018 | 03/09/2018 | 35 | 12 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2018 | 04/04/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 189831 | 02061 | 10 | Solar | 05_05_335W5 | 07/05/2018 | 07/05/2018 | 7 | 0 | 7 | 08/21/2018 | 08/21/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 | 07/05/2018 | 8/21/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/28/2019 | Connected |  | N
National Grid | STOUGHTON | 540910 | 02072 | 6 | Solar | 05_09_909W1 | 08/11/2023 | 08/17/2023 | 5 | 2 | 3 | 08/18/2023 | 08/18/2023 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/19/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 553649 | 01083 | 160 | Solar | 05_05_313W3 | 09/11/2023 | 09/29/2023 | 14 | 5 | 9 | 10/02/2023 | 10/02/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2023 | 09/11/2023 | 4/26/2027 | Y | EXP | 217 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | Y
National Grid | MILFORD | 190446 | 01757 | 15.2 | Solar | 05_07_712J1 | 07/11/2018 | 08/10/2018 | 8 | 0 | 8 | 08/13/2018 | 08/13/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2018 |  | 8/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/29/2019 | Connected |  | N
National Grid | NORTHAMPTON | 200359 | 01060 | 15.2 | Solar | 05_05_7L5 | 11/05/2018 | 11/08/2018 | 3 | 3 | 0 | 11/09/2018 | 11/09/2018 | 54 | 38 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2019 | 11/05/2018 | 10/14/2019 | Y | EXP | 256 | 05/08/2019 | 06/12/2019 | 35 | 0 | 35 |  |  | 7/20/2019 | Connected |  | N
National Grid | NORTHBOROUGH | 267636 | 01532 | 3.8 | Solar | 05_12_23W2 | 12/04/2019 | 12/10/2019 | 3 | 0 | 3 | 12/11/2019 | 12/11/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/04/2019 | 6/3/2021 | Y | EXP | 365 | 11/04/2020 | 01/19/2021 | 76 | 0 | 76 |  |  | 4/14/2021 | Connected |  | N
National Grid | BROCKTON | 175315 | 02302 | 499 | Solar | 05_09_1109W2 | 08/29/2014 | 08/29/2014 | 6 | 0 | 6 | 09/10/2014 | 09/10/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2014 | 08/29/2014 | 6/1/2016 | Y | EXP | 588 | 06/14/2016 | 10/19/2016 | 87 | 0 | 87 | 7/6/2016 | 7/6/2016 | 10/26/2016 | Connected |  | N
National Grid | REHOBOTH | 202211 | 02769 | 233.3 | Solar | 05_07_96W44 | 09/12/2019 | 09/20/2019 | 5 | 0 | 5 | 09/23/2019 | 09/23/2019 | 4 | 2 | 2 | 10/30/2019 | 11/25/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 17 | 0 | 17 |  |  | 0 | 0 | 0 | 12/10/2019 |  | 8/31/2021 | N | EXP | 395 | 10/13/2020 | 01/06/2021 | 85 | 0 | 85 |  |  | 2/24/2021 | Connected |  | N
National Grid | SAUGUS | 177500 | 01906 | 6 | Solar | 05_07_913W18 | 03/03/2017 | 03/03/2017 | 45 | 38 | 7 | 05/09/2017 | 05/09/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2017 | 03/03/2017 | 3/11/2018 | Y | EXP | 36 | 01/12/2018 | 02/16/2018 | 24 | 0 | 24 | 2/28/2018 | 2/28/2018 | 3/6/2018 | Connected |  | N
National Grid | GREAT BARRINGTON | 184046 | 01230 | 4998 | Solar | 05_09_516L3 | 05/16/2018 | 05/16/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/13/2018 | 07/11/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 196600 | 02061 | 106.6 | Solar | 05_05_335W5 | 09/21/2018 | 11/02/2018 | 26 | 9 | 17 | 11/05/2018 | 11/05/2018 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2018 |  | 11/29/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2019 | Connected |  | N
National Grid | STOUGHTON | 549354 | 02072 | 2.61 | Solar | 05_09_909W1 | 09/12/2023 | 09/29/2023 | 13 | 8 | 5 | 10/02/2023 | 10/02/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2023 | 09/12/2023 | 12/7/2024 | Y | EXP | 365 | 03/07/2024 | 03/06/2024 | 0 | 0 | 0 |  |  | 4/3/2024 | Connected |  | N
National Grid | WARREN | 174179 | 01083 | 54 | Solar | 05_05_313W3 | 03/06/2012 | 03/06/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2012 |  | 8/1/2012 | N | EXP | 54 |  |  | 0 | 0 | 0 | 6/8/2012 | 6/8/2012 | 10/2/2012 | Connected |  | N
National Grid | MILFORD | 194058 | 01757 | 9.92 | Solar | 05_07_712J1 | 08/21/2018 | 10/04/2018 | 31 | 24 | 7 | 10/11/2018 | 10/11/2018 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 |  | 11/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/2/2019 | Connected |  | N
National Grid | NORTHAMPTON | 231935 | 01062 | 500 | Solar | 05_05_7L5 | 06/25/2019 | 07/29/2019 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/30/2019 | 08/30/2019 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 269234 | 01581 | 7.6 | Solar | 05_12_23W2 | 12/26/2019 | 01/06/2020 | 5 | 0 | 5 | 01/07/2020 | 01/07/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2020 | 12/26/2019 | 3/12/2021 | Y | EXP | 365 | 10/03/2020 | 01/18/2021 | 107 | 0 | 107 |  |  | 2/5/2021 | Connected |  | N
National Grid | BROCKTON | 175709 | 02302 | 250 | Solar | 05_09_1109W2 | 10/27/2014 | 10/27/2014 | 7 | 1 | 6 | 11/05/2014 | 11/05/2014 | 0 | 0 | 0 | 01/03/2015 | 02/24/2015 | 34 | 0 | 34 |  |  | 0 | 0 | 0 |  | 02/24/2015 | 34 | 0 | 34 |  |  | 0 | 0 | 0 | 2/24/2015 | 10/27/2014 | 6/1/2016 | Y | EXP | 463 | 06/14/2016 | 10/19/2016 | 87 | 0 | 87 |  |  | 10/26/2016 | Connected |  | N
National Grid | REHOBOTH | 202209 | 02769 | 366.6 | Solar | 05_07_96W44 | 04/12/2019 | 04/18/2019 | 4 | 2 | 2 | 04/19/2019 | 04/19/2019 | 12 | 9 | 3 | 06/14/2019 | 07/01/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 07/01/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 7/26/2019 |  | 4/2/2021 | N | EXP | 4 | 10/13/2020 | 01/06/2021 | 85 | 0 | 85 |  |  | 2/24/2021 | Connected |  | N
National Grid | SAUGUS | 246680 | 01906 | 99.9 | Solar | 05_07_913W18 | 08/20/2019 | 03/02/2020 | 21 | 17 | 4 | 03/03/2020 | 03/03/2020 | 170 | 100 | 70 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2021 | Connected |  | Y
National Grid | SHEFFIELD | 183826 | 01257 | 3.8 | Solar | 05_09_516L3 | 04/25/2018 | 04/25/2018 | 9 | 0 | 9 | 07/30/2018 | 07/30/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 261005 | 02061 | 7.6 | Solar | 05_05_335W5 | 10/23/2019 | 10/23/2019 | 0 | 0 | 0 | 10/24/2019 | 10/24/2019 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2019 |  | 10/22/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/12/2020 | Connected |  | N
National Grid | STOUGHTON | 555710 | 02072 | 5 | Solar | 05_09_909W1 | 09/15/2023 | 09/19/2023 | 2 | 0 | 2 | 09/20/2023 | 09/20/2023 | 20 | 0 | 20 | 10/24/2023 | 12/06/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 12/06/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 12/11/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 174194 | 01083 | 22.5 | Solar | 05_05_313W3 | 03/19/2012 | 03/19/2012 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2012 |  | 6/4/2012 | N | EXP | 1 |  |  | 0 | 0 | 0 | 6/12/2012 | 6/12/2012 | 7/25/2012 | Connected |  | N
National Grid | MILFORD | 204159 | 01757 | 213.2 | Solar | 05_07_712J1 | 12/18/2018 | 01/24/2019 | 23 | 16 | 7 | 01/25/2019 | 01/25/2019 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 288310 | 01062 | 0 | Other | 05_05_7L5 | 05/07/2020 | 08/26/2020 | 78 | 72 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2020 | 04/29/2021 | 166 | 34 | 132 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 291136 | 01532 | 10 | Solar | 05_12_23W2 | 07/30/2020 | 11/24/2020 | 79 | 76 | 3 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 07/30/2020 | 10/13/2021 | Y | EXP | 365 | 03/25/2021 | 05/27/2021 | 63 | 0 | 63 |  |  | 6/3/2021 | Connected |  | N
National Grid | BROCKTON | 176202 | 02302 | 150 | Solar | 05_09_1109W2 | 04/24/2015 | 04/24/2015 | 0 | 0 | 0 | 04/27/2015 | 04/27/2015 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2015 |  | 12/31/2016 | N | EXP | 571 |  |  | 0 | 0 | 0 | 7/10/2015 | 7/10/2015 |  | Withdrawn |  | N
National Grid | REHOBOTH | 211150 | 02769 | 262.5 | Natural Gas | 05_07_96W44 | 09/13/2019 | 11/05/2019 | 36 | 27 | 9 | 11/06/2019 | 11/06/2019 | 8 | 0 | 8 | 01/03/2020 | 04/27/2020 | 79 | 46 | 33 |  |  | 0 | 0 | 0 |  | 04/27/2020 | 79 | 46 | 33 |  |  | 0 | 0 | 0 | 5/5/2020 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/26/2020 | Connected |  | N
National Grid | SAUGUS | 318701 | 01906 | 7.6 | Solar | 05_07_913W18 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 |  | Y | EXP | 365 | 03/17/2021 | 04/06/2021 | 20 | 0 | 20 |  |  | 8/15/2021 | Connected |  | N
National Grid | SHEFFIELD | 184047 | 01257 | 4998 | Solar | 05_09_516L3 | 05/16/2018 | 05/16/2018 | 27 | 24 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/12/2018 | 07/11/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 287738 | 02061 | 8 | Solar | 05_05_335W5 | 04/14/2020 | 04/14/2020 | 0 | 0 | 0 | 04/15/2020 | 04/15/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2020 |  | 4/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2020 | Connected |  | N
National Grid | STOUGHTON | 571152 | 02072 | 10 | Solar | 05_09_909W1 | 11/28/2023 | 12/12/2023 | 11 | 8 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 | 11/28/2023 | 2/9/2025 | Y | EXP | 365 | 05/03/2024 | 05/02/2024 | 0 | 0 | 0 |  |  | 5/10/2024 | Connected |  | N
National Grid | WARREN | 174244 | 01082 | 10.32 | Solar | 05_05_313W3 | 02/22/2012 | 02/22/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2012 |  | 5/15/2012 | N | EXP | 14 |  |  | 0 | 0 | 0 | 6/18/2012 | 6/18/2012 | 7/26/2012 | Connected |  | N
National Grid | MILFORD | 293251 | 01757 | 7.6 | Solar | 05_07_712J1 | 07/30/2020 | 09/21/2020 | 34 | 27 | 7 | 09/22/2020 | 09/22/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2020 | 07/30/2020 | 7/29/2021 | Y | EXP | 365 | 12/15/2020 | 01/08/2021 | 24 | 0 | 24 |  |  | 2/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 298439 | 01062 | 3.8 | Solar | 05_05_7L5 | 07/13/2020 | 07/14/2020 | 0 | 0 | 0 | 07/15/2020 | 07/15/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2020 |  | 7/13/2021 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 296623 | 01532 | 0 | Solar | 05_12_23W2 | 06/16/2020 | 07/07/2020 | 14 | 14 | 0 | 07/08/2020 | 07/08/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2020 |  | 8/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2021 | Connected |  | N
National Grid | ABINGTON | 176379 | 02351 | 275 | Solar | 05_09_1109W2 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 | 11/24/2015 | 11/24/2015 | 0 | 0 | 0 | 03/28/2016 | 05/10/2016 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 05/10/2016 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 5/24/2016 | 11/24/2015 | 12/29/2017 | Y | EXP | 584 | 02/22/2017 | 09/08/2017 | 138 | 0 | 138 | 11/17/2017 | 11/17/2017 | 11/16/2017 | Connected |  | N
National Grid | SEEKONK | 265059 | 02771 | 400 | Solar | 05_07_96W44 | 11/13/2019 | 11/21/2019 | 5 | 3 | 2 | 04/08/2020 | 04/08/2020 | 0 | 0 | 0 | 04/08/2020 | 06/23/2020 | 52 | 0 | 52 |  |  | 0 | 0 | 0 |  | 06/23/2020 | 52 | 0 | 52 |  |  | 0 | 0 | 0 | 7/9/2020 |  | 6/18/2021 | N | EXP | 365 | 11/10/2020 | 06/11/2021 | 213 | 0 | 213 |  |  | 6/22/2021 | Connected |  | N
National Grid | SAUGUS | 513459 | 01906 | 10 | Solar | 05_07_913W18 | 03/28/2023 | 03/29/2023 | 1 | 0 | 1 | 03/30/2023 | 03/30/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/28/2023 | 6/6/2024 | Y | EXP | 365 | 07/20/2023 | 08/11/2023 | 23 | 0 | 23 |  |  | 8/24/2023 | Connected |  | N
National Grid | SHEFFIELD | 187500 | 01257 | 4998 | Solar | 05_09_516L3 | 06/10/2018 | 06/10/2018 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/18/2018 | 10/12/2018 | 62 | 28 | 34 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 319815 | 02061 | 9.8 | Solar | 05_05_335W5 | 11/02/2020 | 11/04/2020 | 1 | 0 | 1 | 11/05/2020 | 11/05/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2020 | 11/02/2020 | 1/7/2022 | Y | EXP | 365 | 03/23/2021 | 09/24/2021 | 184 | 3 | 181 |  |  | 1/3/2022 | Connected |  | Y
National Grid | STOUGHTON | 585752 | 02072 | 5 | Solar | 05_09_909W1 | 02/23/2024 | 03/04/2024 | 7 | 5 | 2 | 03/05/2024 | 03/05/2024 | 16 | 14 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/21/2024 | Connected |  | N
National Grid | PALMER | 174490 | 01069 | 1000 | Solar | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 324110 | 01757 | 7.6 | Solar | 05_07_712J1 | 11/25/2020 | 12/02/2020 | 3 | 0 | 3 | 12/03/2020 | 12/03/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2021 | 11/25/2020 | 1/25/2022 | Y | EXP | 365 | 08/12/2021 | 09/22/2021 | 36 | 3 | 33 |  |  | 10/6/2021 | Connected |  | N
National Grid | NORTHAMPTON | 297893 | 01060 | 4500 | Other | 05_05_7L5 | 11/18/2020 | 01/25/2021 | 44 | 37 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/26/2021 | 02/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2022 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 371674 | 01532 | 7.6 | Solar | 05_12_23W2 | 08/02/2021 | 01/04/2022 | 2 | 0 | 2 | 08/05/2021 | 08/05/2021 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 196116 | 02302 | 4998 | Solar | 05_09_1109W2 | 09/28/2018 | 10/11/2018 | 30 | 21 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2018 | 12/12/2018 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 287104 | 02771 | 300 | Solar | 05_07_96W44 | 04/11/2020 | 04/22/2020 | 7 | 3 | 4 |  |  | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 523764 | 01906 | 10 | Solar | 05_07_913W18 | 05/17/2023 | 05/18/2023 | 1 | 0 | 1 | 05/19/2023 | 05/19/2023 | 23 | 6 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2023 | 05/17/2023 | 10/25/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | SHEFFIELD | 196531 | 01257 | 3 | Solar | 05_09_516L3 | 01/14/2019 |  | 180 | 26 | 154 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 341876 | 02061 | 7.6 | Solar | 05_05_335W5 | 03/19/2021 | 03/24/2021 | 2 | 0 | 2 | 03/25/2021 | 03/25/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/4/2021 |  | 6/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2021 | Connected |  | N
National Grid | STOUGHTON | 645469 | 02072 | 7.6 | Solar | 05_09_909W1 | 10/14/2024 | 10/21/2024 | 1 | 0 | 1 | 10/22/2024 | 10/22/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2024 | 10/14/2024 | 11/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2025 | Connected |  | N
National Grid | WARREN | 174489 | 01082 | 2000 | Solar | 05_05_313W3 | 07/26/2012 | 07/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2012 | 10/09/2012 | 42 | 0 | 42 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/1/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 324131 | 01757 | 5.76 | Solar | 05_07_712J1 | 04/07/2021 | 04/09/2021 | 1 | 0 | 1 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2021 |  | 4/8/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 303042 | 01062 | 0 | Solar | 05_05_7L5 | 07/24/2020 | 07/30/2020 | 3 | 0 | 3 | 07/31/2020 | 07/31/2020 | 6 | 3 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/11/2020 |  | 7/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/7/2020 | Connected |  | N
National Grid | NORTHBOROUGH | 374128 | 01532 | 10 | Solar | 05_12_23W2 | 09/17/2021 | 01/05/2022 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2021 | 09/17/2021 | 4/7/2023 | Y | EXP | 365 | 02/22/2022 | 03/22/2022 | 28 | 0 | 28 |  |  | 6/8/2022 | Connected |  | N
National Grid | BROCKTON | 210723 | 02302 | 10 | Solar | 05_09_1109W2 | 03/01/2019 | 05/22/2019 | 58 | 32 | 26 | 05/23/2019 | 05/23/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/5/2019 | 03/01/2019 | 1/29/2020 | Y | EXP | 238 | 09/13/2019 | 11/13/2019 | 61 | 0 | 61 |  |  | 12/5/2019 | Connected |  | N
National Grid | REHOBOTH | 289008 | 02769 | 200 | Solar | 05_07_96W44 | 05/14/2020 | 05/21/2020 | 4 | 0 | 4 |  |  | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/10/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 608352 | 01906 | 10 | Solar | 05_07_913W18 | 05/04/2024 | 05/13/2024 | 1 | 0 | 1 | 10/08/2024 | 10/08/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 | 05/04/2024 | 11/13/2025 | Y | EXP | 365 | 12/26/2024 | 02/11/2025 | 48 | 0 | 48 |  |  | 2/19/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 198034 | 01230 | 2400 | Solar | 05_09_516L3 | 10/25/2018 | 11/26/2018 | 19 | 15 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2018 | 06/15/2019 | 238 | 125 | 113 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 384000 | 02339 | 6 | Solar | 05_05_335W5 | 09/29/2021 | 12/16/2021 | 3 | 0 | 3 | 10/05/2021 | 10/05/2021 | 26 | 4 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 647431 | 02072 | 100 | Solar | 05_09_909W1 | 10/16/2024 | 11/12/2024 | 18 | 9 | 9 |  |  | 28 | 3 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 174916 | 01083 | 760 | Solar | 05_05_313W3 | 02/14/2013 | 02/14/2013 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/28/2013 | 04/09/2013 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2013 |  | 6/30/2014 | N | STD | 255 |  |  | 0 | 0 | 0 | 12/30/2014 | 12/30/2014 | 12/31/2014 | Connected |  | N
National Grid | MILFORD | 330887 | 01757 | 15.2 | Solar | 05_07_712J1 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/20/2021 | 12/10/2020 | 12/4/2022 | Y | EXP | 365 | 09/03/2021 | 10/08/2021 | 36 | 0 | 36 |  |  | 12/2/2022 | Connected |  | N
National Grid | NORTHAMPTON | 306988 | 01062 | 11.4 | Solar | 05_05_7L5 | 09/11/2020 | 09/16/2020 | 2 | 2 | 0 | 09/17/2020 | 09/17/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/7/2020 | 09/11/2020 | 9/15/2021 | Y | EXP | 365 | 02/04/2021 | 04/07/2021 | 62 | 0 | 62 |  |  | 8/17/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 380188 | 01532 | 9.8 | Solar | 05_12_23W2 | 09/18/2021 | 12/08/2021 | 2 | 0 | 2 | 09/22/2021 | 09/22/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 278010 | 02302 | 57.6 | Solar | 05_09_1109W2 | 02/05/2020 | 02/14/2020 | 7 | 4 | 3 | 02/18/2020 | 02/18/2020 | 21 | 0 | 21 | 05/04/2020 | 11/05/2020 | 131 | 101 | 30 |  |  | 0 | 0 | 0 |  | 11/05/2020 | 131 | 101 | 30 |  |  | 0 | 0 | 0 | 11/12/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/13/2021 | Connected |  | N
National Grid | REHOBOTH | 296764 | 02769 | 10 | Solar | 05_07_96W44 | 06/16/2020 | 06/23/2020 | 4 | 0 | 4 | 06/24/2020 | 06/24/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2020 | 06/16/2020 | 10/25/2023 | Y | EXP | 365 | 12/15/2020 | 01/15/2021 | 31 | 0 | 31 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 645918 | 01906 | 10 | Solar | 05_07_913W18 | 10/18/2024 | 11/06/2024 | 4 | 0 | 4 | 11/07/2024 | 11/07/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/10/2024 | 10/18/2024 | 12/18/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 198660 | 01230 | 10 | Solar | 05_09_516L3 | 10/16/2018 | 10/26/2018 | 5 | 5 | 0 | 10/29/2018 | 10/29/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/5/2018 | 10/16/2018 | 4/30/2019 | Y | EXP | 176 | 01/15/2019 | 01/28/2019 | 13 | 0 | 13 |  |  | 3/26/2019 | Connected |  | N
National Grid | HANOVER | 389597 | 02339 | 9.8 | Solar | 05_05_335W5 | 11/09/2021 | 12/13/2021 | 1 | 0 | 1 | 11/12/2021 | 11/12/2021 | 41 | 25 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 11/09/2021 | 12/22/2023 | Y | EXP | 365 | 04/09/2022 | 12/21/2022 | 257 | 0 | 257 |  |  | 2/24/2023 | Connected |  | N
National Grid | STOUGHTON | 647909 | 02072 | 7.6 | Solar | 05_09_909W1 | 10/21/2024 | 11/13/2024 | 4 | 0 | 4 | 11/14/2024 | 11/14/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2024 | 10/21/2024 | 1/28/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/7/2025 | Connected |  | N
National Grid | WARREN | 176105 | 01010 | 20 | Solar | 05_05_313W3 | 06/24/2015 | 06/24/2015 | 3 | 3 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2015 |  | 6/30/2016 | N | EXP | 365 |  |  | 0 | 0 | 0 | 11/3/2015 | 11/3/2015 | 11/4/2015 | Connected |  | N
National Grid | MILFORD | 382577 | 01757 | 240 | Solar | 05_07_712J1 | 11/11/2021 | 12/13/2021 | 21 | 15 | 6 |  |  | 40 | 2 | 38 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 330889 | 01060 | 4946 | Solar | 05_05_7L5 | 02/05/2021 | 03/16/2021 | 26 | 21 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/17/2021 | 04/13/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 393404 | 01532 | 7.25 | Solar | 05_12_23W2 | 12/13/2021 | 01/10/2022 | 6 | 3 | 3 | 12/21/2021 | 12/21/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2022 | 12/13/2021 | 8/2/2023 | Y | EXP | 365 | 05/06/2022 | 06/03/2022 | 29 | 0 | 29 |  |  | 8/11/2022 | Connected |  | N
National Grid | BROCKTON | 318410 | 02302 | 249 | Solar | 05_09_1109W2 | 10/13/2020 | 10/27/2020 | 9 | 0 | 9 |  |  | 22 | 1 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 364705 | 02771 | 72 | Solar | 05_07_96W44 | 06/28/2021 | 07/22/2021 | 17 | 9 | 8 | 07/23/2021 | 07/23/2021 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2021 |  | 4/9/2023 | N | EXP | 586 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | SAUGUS | 666514 | 01906 | 7.6 | Solar | 05_07_913W18 | 01/17/2025 | 02/12/2025 | 3 | 0 | 3 | 02/13/2025 | 02/13/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 6/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 256705 | 01230 | 2800 | Solar | 05_09_516L3 | 01/16/2020 | 03/24/2020 | 46 | 46 | 0 |  |  | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 03/25/2020 | 04/28/2020 | 23 | 9 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HANOVER | 397308 | 02339 | 5.51 | Solar | 05_05_335W5 | 01/28/2022 | 01/31/2022 | 1 | 0 | 1 | 02/01/2022 | 02/01/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/18/2022 | 01/28/2022 | 11/24/2023 | Y | EXP | 365 | 08/03/2022 | 11/08/2022 | 98 | 0 | 98 |  |  | 1/9/2023 | Connected |  | N
National Grid | STOUGHTON | 657538 | 02072 | 7.6 | Solar | 05_09_909W1 | 11/28/2024 | 01/15/2025 | 4 | 0 | 4 | 01/16/2025 | 01/16/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2025 |  | 2/27/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/15/2025 | Connected |  | N
National Grid | WARREN | 177233 | 01083 | 156 | Solar | 05_05_313W3 | 11/04/2016 | 11/04/2016 | 1 | 1 | 0 | 11/08/2016 | 11/08/2016 | 240 | 0 | 240 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2016 |  | 11/12/2017 | N | EXP | 368 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 492024 | 01757 | 6 | Solar | 05_07_712J1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | NORTHAMPTON | 342714 | 01060 | 7.6 | Solar | 05_05_7L5 | 03/08/2021 | 04/14/2021 | 27 | 27 | 0 | 04/15/2021 | 04/15/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/21/2021 |  | 5/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 438832 | 01532 | 15.2 | Solar | 05_12_23W2 | 06/20/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/25/2023 | Connected |  | Y
National Grid | BROCKTON | 346175 | 02302 | 9.6 | Solar | 05_09_1109W2 | 03/10/2021 | 03/15/2021 | 2 | 2 | 0 | 03/16/2021 | 03/16/2021 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 3/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 391836 | 02769 | 0 | Other | 05_07_96W44 | 11/15/2021 | 01/04/2022 | 34 | 25 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2022 | 01/26/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 667301 | 01906 | 15.2 | Solar | 05_07_913W18 | 02/03/2025 | 02/11/2025 | 7 | 4 | 3 | 02/12/2025 | 02/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 4/7/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 268866 | 01230 | 5.76 | Solar | 05_09_516L3 | 12/12/2019 | 12/16/2019 | 2 | 1 | 1 | 12/17/2019 | 12/17/2019 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2020 |  | 9/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 527637 | 02061 | 10.15 | Solar | 05_05_335W5 | 06/07/2023 |  | 91 | 73 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 657908 | 02072 | 22.8 | Solar | 05_09_909W1 | 12/11/2024 | 12/17/2024 | 4 | 0 | 4 | 12/18/2024 | 12/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/5/2025 | Connected |  | N
National Grid | PALMER | 177390 | 01069 | 15.2 | Solar | 05_05_313W3 | 02/16/2017 | 02/16/2017 | 4 | 3 | 1 | 02/23/2017 | 02/23/2017 | 274 | 0 | 274 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2017 |  | 2/21/2018 | N | EXP | 362 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 513457 | 01757 | 0 | Solar | 05_07_712J1 | 03/21/2023 |  | 144 | 128 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 366959 | 01062 | 9.8 | Solar | 05_05_7L5 | 07/30/2021 | 12/14/2021 | 3 | 0 | 3 | 08/05/2021 | 08/05/2021 | 22 | 3 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/14/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 471801 | 01532 | 3.8 | Solar | 05_12_23W2 | 11/21/2022 | 11/27/2022 | 4 | 0 | 4 | 11/28/2022 | 11/28/2022 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 372263 | 02302 | 72 | Solar | 05_09_1109W2 | 07/27/2021 | 09/17/2021 | 12 | 2 | 10 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SEEKONK | 477628 | 02771 | 15.2 | Solar | 05_07_96W44 | 11/15/2022 | 11/17/2022 | 2 | 0 | 2 | 11/18/2022 | 11/18/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/15/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 669216 | 01906 | 8.74 | Solar | 05_07_913W18 | 01/31/2025 | 02/14/2025 | 6 | 1 | 5 | 02/18/2025 | 02/18/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 311809 | 01257 | 0 | Other | 05_09_516L3 | 09/22/2020 | 09/30/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/01/2020 | 10/27/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORWELL | 531921 | 02061 | 6 | Solar | 05_05_335W5 | 06/09/2023 | 06/13/2023 | 2 | 0 | 2 | 06/14/2023 | 06/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/30/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/26/2023 | Connected |  | N
National Grid | STOUGHTON | 660016 | 02072 | 5.76 | Solar | 05_09_909W1 | 12/11/2024 | 12/23/2024 | 4 | 0 | 4 | 12/24/2024 | 12/24/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2025 | 12/11/2024 | 2/11/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 177966 | 01083 | 480 | Solar | 05_05_313W3 | 04/21/2017 | 04/21/2017 | 197 | 194 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/29/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 559691 | 01757 | 8.19 | Solar | 05_07_712J1 | 10/24/2023 | 10/26/2023 | 3 | 1 | 2 | 10/27/2023 | 10/27/2023 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 383572 | 01060 | 15.2 | Solar | 05_05_7L5 | 09/21/2021 | 12/09/2021 | 3 | 0 | 3 | 09/27/2021 | 09/27/2021 | 23 | 3 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 527299 | 01532 | 16 | Solar | 05_12_23W2 | 11/01/2023 | 05/24/2023 | 1 | 0 | 1 | 11/03/2023 | 11/03/2023 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2023 |  | 12/10/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2023 | Connected |  | N
National Grid | BROCKTON | 375639 | 02302 | 7.6 | Solar | 05_09_1109W2 | 08/12/2021 | 09/24/2021 | 30 | 29 | 1 | 09/27/2021 | 09/27/2021 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/2/2021 |  | 9/23/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 495553 | 02769 | 23.808 | Solar | 05_07_96W44 | 01/27/2023 | 03/07/2023 | 27 | 26 | 1 | 03/08/2023 | 03/08/2023 | 86 | 64 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/8/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 679409 | 01906 | 11.5 | Solar | 05_07_913W18 | 03/20/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/24/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 347568 | 01230 | 7.6 | Solar | 05_09_516L3 | 05/11/2021 | 05/11/2021 | 1 | 0 | 1 | 05/12/2021 | 05/12/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2021 |  | 6/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 534064 | 02061 | 7.25 | Solar | 05_05_335W5 | 06/20/2023 | 07/03/2023 | 9 | 7 | 2 | 07/05/2023 | 07/05/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2023 | 06/20/2023 | 11/26/2024 | Y | EXP | 365 | 11/28/2023 | 11/29/2023 | 2 | 0 | 2 |  |  | 12/7/2023 | Connected |  | N
National Grid | STOUGHTON | 663194 | 02072 | 7.6 | Solar | 05_09_909W1 | 01/06/2025 | 01/30/2025 | 9 | 4 | 5 | 01/31/2025 | 01/31/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2025 |  | 4/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/1/2025 | Connected |  | N
National Grid | WARREN | 178354 | 01083 | 480 | Solar | 05_05_313W3 | 02/27/2018 | 02/27/2018 | 2 | 2 | 0 | 03/02/2018 | 03/02/2018 | 169 | 9 | 160 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/5/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 528274 | 01757 | 6 | Solar | 05_07_712J1 | 05/30/2023 | 06/01/2023 | 3 | 2 | 1 | 06/02/2023 | 06/02/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2023 | 05/30/2023 | 9/28/2024 | Y | EXP | 365 | 09/06/2023 | 09/27/2023 | 22 | 0 | 22 |  |  | 10/6/2023 | Connected |  | N
National Grid | NORTHAMPTON | 428659 | 01060 | 0 | Other | 05_05_7L5 | 10/05/2022 | 01/04/2023 | 59 | 49 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/05/2023 | 02/02/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 570482 | 01532 | 6 | Solar | 05_12_23W2 | 11/22/2023 | 11/28/2023 | 3 | 1 | 2 | 11/29/2023 | 11/29/2023 | 27 | 6 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2024 | 11/22/2023 | 1/10/2025 | Y | EXP | 365 | 04/03/2024 | 04/03/2024 | 1 | 0 | 1 |  |  | 4/10/2024 | Connected |  | N
National Grid | EAST BRIDGEWATER | 377006 | 02333 | 51.9 | Solar | 05_09_1109W2 | 10/01/2021 | 12/28/2021 | 23 | 13 | 10 | 11/05/2021 | 11/05/2021 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 |  | 12/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/13/2022 | Connected |  | N
National Grid | SEEKONK | 541172 | 02771 | 7.56 | Solar | 05_07_96W44 | 07/17/2023 | 07/19/2023 | 2 | 0 | 2 | 07/20/2023 | 07/20/2023 | 72 | 51 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2023 |  | 11/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/6/2024 | Connected |  | N
National Grid | SAUGUS | 684887 | 01906 | 9.423 | Solar | 05_07_913W18 | 04/14/2025 | 10/10/2025 | 6 | 4 | 2 | 11/26/2025 | 11/26/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/15/2025 |  | 1/8/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/9/2026 | Connected |  | N
National Grid | GREAT BARRINGTON | 375844 | 01230 | 7.6 | Solar | 05_09_516L3 | 08/13/2021 |  | 31 | 26 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 579839 | 02061 | 1.74 | Solar | 05_05_335W5 | 01/17/2024 | 01/23/2024 | 4 | 0 | 4 | 01/24/2024 | 01/24/2024 | 28 | 13 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 695565 | 02072 | 7.68 | Solar | 05_09_909W1 | 06/10/2025 | 07/14/2025 | 1 | 0 | 1 | 07/16/2025 | 07/16/2025 | 29 | 14 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/29/2025 |  | 9/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/5/2025 | Connected |  | N
National Grid | WARREN | 196299 | 01083 | 236 | Solar | 05_05_313W3 | 11/14/2018 | 11/20/2018 | 3 | 0 | 3 | 11/21/2018 | 11/21/2018 | 18 | 2 | 16 | 06/11/2019 | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 06/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 571401 | 01757 | 7.6 | Solar | 05_07_712J1 | 12/05/2023 | 12/08/2023 | 3 | 0 | 3 | 12/11/2023 | 12/11/2023 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 443865 | 01060 | 10 | Solar | 05_05_7L5 | 08/04/2022 | 08/09/2022 | 4 | 3 | 1 | 08/10/2022 | 08/10/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2022 |  | 10/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/27/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 575934 | 01532 | 9.86 | Solar | 05_12_23W2 | 12/15/2023 | 12/20/2023 | 3 | 2 | 1 | 12/21/2023 | 12/21/2023 | 21 | 1 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 12/15/2023 | 5/22/2025 | Y | EXP | 365 | 05/21/2024 | 06/04/2024 | 15 | 0 | 15 |  |  | 9/26/2024 | Connected |  | Y
National Grid | BROCKTON | 376995 | 02302 | 28.8 | Solar | 05_09_1109W2 | 09/20/2021 | 09/29/2021 | 7 | 5 | 2 | 09/30/2021 | 09/30/2021 | 27 | 4 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  | 12/8/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2022 | Connected |  | N
National Grid | SEEKONK | 586854 | 02771 | 0 | Battery Add-On | 05_07_96W44 | 01/31/2024 | 02/20/2024 | 13 | 11 | 2 | 02/21/2024 | 02/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/7/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/14/2024 | Connected |  | N
National Grid | SAUGUS | 699708 | 01906 | 5.76 | Solar | 05_07_913W18 | 06/24/2025 | 07/21/2025 | 7 | 3 | 4 | 09/10/2025 | 09/10/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/19/2025 | Connected |  | N
National Grid | EGREMONT | 615473 | 01258 | 15.2 | Solar | 05_09_516L3 | 06/06/2024 | 06/10/2024 | 2 | 0 | 2 | 06/11/2024 | 06/11/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2024 |  | 7/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/21/2024 | Connected |  | N
National Grid | NORWELL | 586068 | 02061 | 0 | Battery Add-On | 05_05_335W5 | 01/29/2024 | 02/05/2024 | 6 | 3 | 3 | 02/06/2024 | 02/06/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 700054 | 02072 | 11.5 | Solar | 05_09_909W1 | 06/20/2025 | 06/25/2025 | 3 | 0 | 3 | 06/26/2025 | 06/26/2025 | 32 | 16 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2025 |  | 8/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/2/2025 | Connected |  | N
National Grid | WARREN | 196297 | 01083 | 496 | Solar | 05_05_313W3 | 11/15/2018 | 11/20/2018 | 2 | 0 | 2 | 11/21/2018 | 11/21/2018 | 20 | 2 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 626740 | 01757 | 7.6 | Solar | 05_07_712J1 | 07/22/2024 | 07/30/2024 | 1 | 0 | 1 | 07/31/2024 | 07/31/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 447033 | 01062 | 7.296 | Solar | 05_05_7L5 | 08/03/2022 | 08/05/2022 | 3 | 2 | 1 | 08/08/2022 | 08/08/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2022 | 08/03/2022 | 2/2/2024 | Y | EXP | 365 | 01/28/2023 | 01/27/2023 | 0 | 0 | 0 |  |  | 2/24/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 594738 | 01532 | 2.4 | Solar | 05_12_23W2 | 03/15/2024 | 04/01/2024 | 12 | 10 | 2 | 04/02/2024 | 04/02/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/16/2024 |  | 4/26/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 383564 | 02302 | 25 | Solar | 05_09_1109W2 | 09/23/2021 | 12/15/2021 | 2 | 0 | 2 | 09/28/2021 | 09/28/2021 | 49 | 27 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2021 |  | 12/11/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/1/2022 | Connected |  | Y
National Grid | SEEKONK | 604122 | 02771 | 53.58 | Solar | 05_07_96W44 | 04/16/2024 | 07/03/2024 | 54 | 46 | 8 | 07/05/2024 | 07/05/2024 | 39 | 32 | 7 | 08/29/2024 | 11/21/2024 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  | 11/21/2024 | 59 | 25 | 34 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 715057 | 01906 | 6.46 | Solar | 05_07_913W18 | 08/28/2025 | 09/18/2025 | 3 | 0 | 3 | 09/26/2025 | 09/26/2025 | 97 | 82 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 661579 | 01230 | 5.76 | Solar | 05_09_516L3 | 12/18/2024 | 01/13/2025 | 5 | 0 | 5 | 01/14/2025 | 01/14/2025 | 28 | 4 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2025 |  | 3/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 588787 | 02061 | 3.8 | Solar | 05_05_335W5 | 02/22/2024 | 02/26/2024 | 2 | 0 | 2 | 02/27/2024 | 02/27/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2024 |  | 3/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2024 | Connected |  | N
National Grid | STOUGHTON | 721445 | 02072 | 10 | Solar | 05_09_909W2 | 09/24/2025 | 10/04/2025 | 6 | 0 | 6 | 10/22/2025 | 10/22/2025 | 22 | 6 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2025 | 09/24/2025 | 12/10/2026 | Y | EXP | 365 | 01/15/2026 |  | 51 | 0 | 51 |  |  |  | Construction |  | N
National Grid | WARREN | 201086 | 01083 | 2460 | Solar | 05_05_313W3 | 02/20/2019 | 01/15/2020 | 226 | 26 | 200 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/21/2020 | 08/19/2020 | 148 | 0 | 148 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 642715 | 01757 | 4.64 | Solar | 05_07_712J1 | 09/25/2024 | 01/03/2025 | 4 | 0 | 4 | 01/06/2025 | 01/06/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/17/2025 | Connected |  | N
National Grid | NORTHAMPTON | 457493 | 01062 | 10 | Solar | 05_05_7L5 | 10/19/2022 | 11/04/2022 | 12 | 10 | 2 | 11/07/2022 | 11/07/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  | 12/8/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/21/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 620744 | 01532 | 7.6 | Solar | 05_12_23W2 | 06/27/2024 | 07/15/2024 | 3 | 0 | 3 | 07/16/2024 | 07/16/2024 | 15 | 0 | 15 | 08/21/2024 | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  | 09/17/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 9/23/2024 | 06/27/2024 | 10/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2025 | Connected |  | N
National Grid | BROCKTON | 409466 | 02302 | 7.6 | Solar | 05_09_1109W2 | 01/31/2022 | 02/01/2022 | 1 | 0 | 1 | 02/02/2022 | 02/02/2022 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2022 |  | 3/18/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2022 | Connected |  | N
National Grid | REHOBOTH | 706541 | 02769 | 7.6 | Solar | 05_07_96W44 | 07/25/2025 | 08/08/2025 | 9 | 5 | 4 | 08/11/2025 | 08/11/2025 | 34 | 21 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 701972 | 01906 | 16.32 | Solar | 05_07_913W47 | 06/30/2025 | 07/01/2025 | 1 | 0 | 1 | 07/02/2025 | 07/02/2025 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2025 |  | 8/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 174563 | 01230 | 4950 | Solar | 05_09_516L4 | 08/22/2011 | 08/22/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2011 | 12/16/2011 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/22/2011 | 4/1/2014 | Y | STD | 383 |  |  | 0 | 0 | 0 | 5/14/2014 | 5/14/2014 | 5/30/2014 | Connected |  | N
National Grid | NORWELL | 598467 | 02061 | 12.288 | Solar | 05_05_335W5 | 05/01/2024 | 05/20/2024 | 2 | 0 | 2 | 05/21/2024 | 05/21/2024 | 15 | 5 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2024 | 05/01/2024 | 11/30/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 175368 | 02072 | 34.2 | Solar | 05_09_909W2 | 02/06/2014 | 02/06/2014 | 5 | 0 | 5 | 02/14/2014 | 02/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2014 |  | 5/30/2014 | N | EXP | 98 |  |  | 0 | 0 | 0 | 2/25/2014 | 2/25/2014 | 6/17/2014 | Connected |  | N
National Grid | WARREN | 650146 | 01083 | 10 | Solar | 05_07_712J1 | 11/07/2024 | 11/20/2024 | 3 | 0 | 3 | 11/21/2024 | 11/21/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2025 |  | 1/17/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 486773 | 01757 | 8.12 | Solar | 05_05_7L5 | 01/19/2023 | 02/01/2023 | 9 | 7 | 2 | 02/02/2023 | 02/02/2023 | 21 | 4 | 17 | 03/09/2023 | 03/24/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  | 03/24/2023 | 8 | 0 | 8 |  |  | 0 | 0 | 0 | 3/24/2023 |  | 10/3/2024 | N | EXP | 365 | 08/03/2023 | 10/04/2023 | 63 | 0 | 63 |  |  | 10/10/2023 | Connected |  | N
National Grid | NORTHAMPTON | 621777 | 01062 | 23 | Solar | 05_12_23W2 | 07/01/2024 | 07/03/2024 | 2 | 0 | 2 | 07/05/2024 | 07/05/2024 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2024 |  | 8/8/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 490673 | 01532 | 15.2 | Solar | 05_09_1109W2 | 01/27/2023 | 01/30/2023 | 1 | 0 | 1 | 01/31/2023 | 01/31/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/1/2023 | 01/27/2023 | 5/22/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/10/2023 | Connected |  | N
National Grid | BROCKTON | 715186 | 02302 | 53.58 | Solar | 05_07_96W44 | 08/27/2025 |  | 25 | 24 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N |  |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 725705 | 02769 | 10 | Solar | 05_07_913W47 | 10/10/2025 | 11/24/2025 | 1 | 0 | 1 | 12/18/2025 | 12/18/2025 | 25 | 10 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | SAUGUS | 175054 | 01906 | 4950 | Solar | 05_09_516L4 | 08/22/2011 | 08/22/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2011 | 12/16/2011 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/22/2011 | 11/30/2012 | Y | STD | 14 |  |  | 0 | 0 | 0 | 5/14/2014 | 5/14/2014 | 5/30/2014 | Connected |  | N
National Grid | EGREMONT | 603443 | 01258 | 5.76 | Solar | 05_05_335W5 | 04/16/2024 | 04/18/2024 | 2 | 0 | 2 | 04/19/2024 | 04/19/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2024 | 04/16/2024 | 11/30/2025 | Y | EXP | 365 | 07/24/2024 | 08/28/2024 | 36 | 0 | 36 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 177387 | 02061 | 0 | Solar | 05_09_909W2 | 11/30/2016 | 11/30/2016 | 0 | 0 | 0 | 12/01/2016 | 12/01/2016 | 295 | 0 | 295 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/6/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 288940 | 02072 | 11.4 | Solar | 05_05_313W3 | 04/22/2020 | 04/30/2020 | 6 | 6 | 0 | 05/01/2020 | 05/01/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2020 |  | 4/29/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/1/2020 | Connected |  | N
National Grid | WARREN | 656337 | 01092 | 3.48 | Solar | 05_07_712J1 | 11/22/2024 | 02/13/2025 | 11 | 8 | 3 | 02/14/2025 | 02/14/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2025 | 11/22/2024 | 4/10/2026 | Y | EXP | 365 | 05/17/2025 | 08/08/2025 | 84 | 0 | 84 |  |  | 9/12/2025 | Connected |  | N
National Grid | MILFORD | 492065 | 01757 | 7.6 | Solar | 05_05_7L5 | 03/23/2023 | 01/24/2023 | 3 | 3 | 0 | 03/29/2023 | 03/29/2023 | 33 | 12 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/24/2023 |  | 5/15/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/10/2023 | Connected |  | N
National Grid | NORTHAMPTON | 621470 | 01060 | 7.6 | Solar | 05_12_23W2 | 06/28/2024 | 07/15/2024 | 4 | 1 | 3 | 07/16/2024 | 07/16/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2024 | 06/28/2024 | 8/27/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/8/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 505807 | 01532 | 20 | Solar | 05_09_1109W2 | 03/16/2023 | 03/21/2023 | 3 | 0 | 3 | 03/22/2023 | 03/22/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/20/2023 |  | 11/27/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2023 | Connected |  | N
National Grid | BROCKTON | 697797 | 02302 | 320 | Solar | 05_07_97W1 | 08/18/2025 |  | 136 | 129 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | REHOBOTH | 727210 | 02769 | 7.6 | Solar | 05_07_913W47 | 10/16/2025 | 10/23/2025 | 3 | 0 | 3 | 11/13/2025 | 11/13/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/11/2025 | 10/16/2025 | 12/22/2026 | Y | EXP | 365 | 02/28/2026 |  | 7 | 0 | 7 |  |  |  | Construction |  | N
National Grid | SAUGUS | 175083 | 01906 | 4000 | Solar | 05_09_516L4 | 08/22/2011 | 08/22/2011 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2011 | 12/16/2011 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/14/2013 | 08/22/2011 | 11/30/2012 | Y | STD | 14 |  |  | 0 | 0 | 0 | 5/14/2014 | 5/14/2014 | 5/30/2014 | Connected |  | N
National Grid | EGREMONT | 629221 | 01258 | 7.6 | Solar | 05_05_335W5 | 08/02/2024 | 08/16/2024 | 2 | 0 | 2 | 08/19/2024 | 08/19/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 184687 | 02061 | 990 | Solar | 05_09_909W2 | 05/14/2018 | 06/04/2018 | 1 | 0 | 1 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2019 |  | 7/22/2020 | N | STD | 546 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 387185 | 02072 | 8.12 | Solar | 05_05_313W3 | 11/29/2021 | 01/07/2022 | 11 | 4 | 7 | 12/15/2021 | 12/15/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 664339 | 01083 | 7.6 | Solar | 05_07_712J1 | 01/07/2025 | 01/31/2025 | 6 | 0 | 6 | 02/03/2025 | 02/03/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/19/2025 |  | 3/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2025 | Connected |  | N
National Grid | MILFORD | 493282 | 01757 | 50 | Solar | 05_05_7L5 | 03/22/2023 | 04/24/2023 | 22 | 13 | 9 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 627380 | 01060 | 6.4 | Solar | 05_12_23W2 | 07/24/2024 | 08/21/2024 | 17 | 14 | 3 | 08/22/2024 | 08/22/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/4/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 511135 | 01532 | 15.2 | Solar | 05_09_1109W2 | 03/15/2023 | 03/16/2023 | 2 | 1 | 1 | 03/17/2023 | 03/17/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2023 |  | 4/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/27/2023 | Connected |  | N
National Grid | EAST BRIDGEWATER | 697784 | 02333 | 240 | Solar | 05_07_97W1 | 08/07/2025 |  | 143 | 136 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SEEKONK | 735275 | 02771 | 10 | Solar | 05_07_913W47 | 11/20/2025 | 11/21/2025 | 18 | 18 | 0 | 01/21/2026 | 01/21/2026 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | SAUGUS | 397235 | 01906 | 2125 | Solar | 05_09_516L4 | 03/14/2022 |  | 162 | 153 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 639115 | 01230 | 7.6 | Solar | 05_05_335W5 | 09/10/2024 | 10/28/2024 | 13 | 9 | 4 | 10/29/2024 | 10/29/2024 | 42 | 25 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORWELL | 190049 | 02061 | 990 | Solar | 05_09_909W2 | 08/28/2018 | 11/26/2018 | 59 | 28 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2018 | 03/22/2019 | 81 | 62 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/23/2021 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 415225 | 02072 | 15.2 | Solar | 05_05_313W3 | 03/03/2022 |  | 36 | 26 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 666538 | 01083 | 11.5 | Solar | 05_07_712J1 | 01/17/2025 | 02/07/2025 | 14 | 10 | 4 | 02/10/2025 | 02/10/2025 | 56 | 34 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 | 01/17/2025 | 9/29/2026 | Y | EXP | 365 | 10/24/2025 | 11/13/2025 | 21 | 0 | 21 |  |  | 11/15/2025 | Connected |  | Y
National Grid | MILFORD | 517932 | 01757 | 13.05 | Solar | 05_05_7L5 | 04/10/2023 | 04/13/2023 | 3 | 2 | 1 | 04/14/2023 | 04/14/2023 | 54 | 30 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/7/2023 |  | 7/20/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/26/2023 | Connected |  | N
National Grid | NORTHAMPTON | 641554 | 01062 | 6.72 | Solar | 05_12_23W2 | 09/19/2024 | 10/15/2024 | 5 | 3 | 2 | 10/16/2024 | 10/16/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2024 | 09/19/2024 | 1/16/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 513251 | 01532 | 20 | Solar | 05_09_1109W2 | 03/20/2023 | 04/24/2023 | 25 | 23 | 2 | 04/25/2023 | 04/25/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2023 |  | 7/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/7/2023 | Connected |  | N
National Grid | BROCKTON | 730347 | 02302 | 5.76 | Solar | 05_07_97W1 | 10/30/2025 | 11/04/2025 | 3 | 0 | 3 | 11/05/2025 | 11/05/2025 | 58 | 39 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/3/2026 |  | 2/6/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | REHOBOTH | 175615 | 02769 | 27.3 | Solar | 05_07_913W47 | 12/16/2014 | 12/16/2014 | 4 | 3 | 1 | 12/23/2014 | 12/23/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2015 |  | 4/15/2015 | N | EXP | 1 |  |  | 0 | 0 | 0 | 2/19/2015 | 2/19/2015 | 7/2/2015 | Connected |  | N
National Grid | SAUGUS | 397233 | 01906 | 2000 | Solar | 05_09_516L4 | 03/14/2022 |  | 166 | 157 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 640988 | 01258 | 6 | Solar | 05_05_335W5 | 09/17/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2024 | 09/17/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/14/2025 | Connected |  | N
National Grid | RANDOLPH | 197016 | 02368 | 7.6 | Solar | 05_09_909W2 | 09/26/2018 | 10/16/2018 | 6 | 0 | 6 | 10/22/2018 | 10/22/2018 | 19 | 19 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2018 | 09/26/2018 | 12/4/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/26/2019 | Connected |  | N
National Grid | STOUGHTON | 420767 | 02072 | 15.2 | Solar | 05_05_313W3 | 03/30/2022 | 03/31/2022 | 1 | 0 | 1 | 04/01/2022 | 04/01/2022 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2022 |  | 5/7/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/15/2022 | Connected |  | N
National Grid | WARREN | 680819 | 01083 | 15.76 | Solar | 05_07_712J1 | 03/31/2025 | 04/03/2025 | 3 | 0 | 3 | 04/04/2025 | 04/04/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | MILFORD | 571548 | 01757 | 3.77 | Solar | 05_05_7L5 | 12/07/2023 | 12/08/2023 | 1 | 0 | 1 | 12/11/2023 | 12/11/2023 | 21 | 3 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/11/2024 | 12/07/2023 | 1/21/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/30/2024 | Connected |  | N
National Grid | NORTHAMPTON | 643916 | 01062 | 5.76 | Solar | 05_12_23W2 | 10/01/2024 | 10/22/2024 | 1 | 0 | 1 | 10/23/2024 | 10/23/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/25/2024 |  | 12/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/21/2025 | Connected |  | Y
National Grid | NORTHBOROUGH | 525221 | 01532 | 15.2 | Solar | 05_09_1109W2 | 06/13/2023 | 06/14/2023 | 1 | 0 | 1 | 06/15/2023 | 06/15/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2023 |  | 7/21/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/16/2023 | Connected |  | N
National Grid | BROCKTON | 754294 | 02302 | 10 | Solar | 05_07_97W1 | 03/03/2026 | 03/05/2026 | 2 | 0 | 2 | 03/06/2026 | 03/06/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | REHOBOTH | 177424 | 02769 | 7.6 | Solar | 05_07_913W47 | 12/06/2016 | 12/06/2016 | 2 | 2 | 0 | 12/09/2016 | 12/09/2016 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2016 | 12/06/2016 | 12/12/2017 | Y | EXP | 365 |  |  | 0 | 0 | 0 | 5/2/2017 | 5/2/2017 | 5/2/2017 | Connected |  | N
National Grid | SAUGUS | 397228 | 01906 | 2125 | Solar | 05_09_516L4 | 03/15/2022 |  | 166 | 158 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 642723 | 01230 | 0 | Solar | 05_05_335W5 | 09/25/2024 | 09/26/2024 | 1 | 0 | 1 | 09/27/2024 | 09/27/2024 | 93 | 36 | 57 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 197077 | 02368 | 6 | Solar | 05_09_909W2 | 12/07/2018 | 01/10/2019 | 5 | 0 | 5 | 01/11/2019 | 01/11/2019 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2019 | 12/07/2018 | 1/28/2020 | Y | EXP | 365 | 03/20/2019 | 03/19/2019 | 0 | 0 | 0 |  |  | 7/16/2019 | Connected |  | N
National Grid | STOUGHTON | 437383 | 02072 | 15.2 | Solar | 05_05_313W3 | 06/13/2022 | 06/14/2022 | 1 | 0 | 1 | 06/15/2022 | 06/15/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2022 |  | 8/25/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2022 | Connected |  | N
National Grid | WARREN | 715090 | 01010 | 3.8 | Solar | 05_07_712J1 | 08/28/2025 | 10/01/2025 | 3 | 0 | 3 | 10/23/2025 | 10/23/2025 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 | 08/28/2025 | 12/16/2026 | Y | EXP | 365 | 02/07/2026 | 02/06/2026 | 0 | 0 | 0 |  |  | 2/23/2026 | Connected |  | N
National Grid | MILFORD | 570949 | 01757 | 0 | Solar | 05_05_7L5 | 11/13/2023 | 11/17/2023 | 4 | 3 | 1 | 11/20/2023 | 11/20/2023 | 45 | 18 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/16/2024 | Connected |  | N
National Grid | NORTHAMPTON | 645402 | 01060 | 7.6 | Solar | 05_12_23W2 | 10/08/2024 | 11/05/2024 | 4 | 0 | 4 | 11/06/2024 | 11/06/2024 | 23 | 0 | 23 | 12/31/2024 | 01/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  | 01/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 | 1/27/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 558449 | 01532 | 6 | Solar | 05_09_1109W2 | 10/12/2023 | 10/13/2023 | 1 | 0 | 1 | 10/16/2023 | 10/16/2023 | 32 | 13 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2023 | 10/12/2023 | 12/31/2024 | Y | EXP | 365 | 01/19/2024 | 01/18/2024 | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 177953 | 02302 | 109.25 | Solar | 05_07_97W1 | 08/24/2017 | 08/24/2017 | 5 | 5 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/2/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 12/18/2017 | 12/18/2017 | 12/21/2017 | Connected |  | N
National Grid | REHOBOTH | 322312 | 02769 | 7.6 | Solar | 05_07_913W47 | 10/28/2020 | 10/29/2020 | 0 | 0 | 0 | 10/30/2020 | 10/30/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2020 |  | 10/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2021 | Connected |  | N
National Grid | SAUGUS | 419520 | 01906 | 4250 | Natural Gas | 05_09_522L2 | 08/26/2022 | 11/02/2022 | 46 | 37 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2022 | 12/23/2022 | 35 | 16 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2025 | 08/26/2022 | 11/4/2026 | Y | STD | 69 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | GREAT BARRINGTON | 646004 | 01230 | 9.88 | Solar | 05_05_335W5 | 10/09/2024 | 10/11/2024 | 2 | 0 | 2 | 10/15/2024 | 10/15/2024 | 45 | 21 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/26/2024 |  | 12/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/29/2025 | Connected |  | N
National Grid | RANDOLPH | 295561 | 02368 | 0 | Battery Add-On | 05_09_909W2 | 06/10/2020 | 07/20/2020 | 27 | 25 | 2 | 07/21/2020 | 07/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/14/2020 |  | 7/20/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/9/2020 | Connected |  | N
National Grid | STOUGHTON | 619299 | 02072 | 50 | Solar | 05_05_313W3 | 06/26/2024 | 07/24/2024 | 19 | 12 | 7 | 07/25/2024 | 07/25/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2024 |  | 11/15/2025 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WARREN | 721528 | 01010 | 13.3 | Wind | 05_07_712J1 | 09/24/2025 | 10/09/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 61 | 52 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 572861 | 01757 | 15.2 | Solar | 05_05_7L5 | 11/28/2023 | 11/29/2023 | 2 | 1 | 1 | 11/30/2023 | 11/30/2023 | 42 | 17 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2024 | 11/28/2023 | 2/11/2025 | Y | EXP | 365 | 03/05/2024 | 04/18/2024 | 45 | 0 | 45 |  |  | 6/4/2024 | Connected |  | N
National Grid | NORTHAMPTON | 652136 | 01060 | 3.8 | Solar | 05_12_23W2 | 11/14/2024 | 01/17/2025 | 27 | 21 | 6 | 01/21/2025 | 01/21/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 11/14/2024 | 4/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 541112 | 01532 | 20 | Solar | 05_09_1109W2 | 08/09/2023 | 09/06/2023 | 18 | 18 | 0 | 09/07/2023 | 09/07/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2023 |  | 10/28/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2023 | Connected |  | N
National Grid | BROCKTON | 177991 | 02302 | 15.2 | Solar | 05_07_97W1 | 10/24/2017 | 10/24/2017 | 14 | 14 | 0 | 11/27/2017 | 11/27/2017 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2017 |  | 11/1/2018 | N | EXP | 339 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 326056 | 02769 | 7.6 | Solar | 05_07_913W47 | 12/10/2020 | 12/18/2020 | 5 | 0 | 5 | 12/21/2020 | 12/21/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 734667 | 01906 | 420 | Solar | 05_09_522L2 | 12/11/2025 |  | 30 | 25 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | GREAT BARRINGTON | 646404 | 01230 | 3.8 | Solar | 05_05_335W5 | 10/25/2024 | 11/13/2024 | 3 | 0 | 3 | 11/14/2024 | 11/14/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2024 | 10/25/2024 | 12/31/2025 | Y | EXP | 365 | 02/13/2025 | 03/18/2025 | 34 | 0 | 34 |  |  | 4/1/2025 | Connected |  | N
National Grid | RANDOLPH | 341230 | 02368 | 14.88 | Solar | 05_09_909W2 | 04/07/2021 | 04/09/2021 | 2 | 1 | 1 | 04/12/2021 | 04/12/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2021 |  | 7/30/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2021 | Connected |  | N
National Grid | STOUGHTON | 620202 | 02072 | 3.8 | Solar | 05_05_313W3 | 06/24/2024 | 08/13/2024 | 35 | 30 | 5 | 08/14/2024 | 08/14/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 9/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | WARREN | 370680 | 01585 | 675 | Solar | 05_07_75W1 | 08/12/2021 | 09/10/2021 | 20 | 13 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 08/12/2021 | 6/12/2026 | Y | STD | 518 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | MILFORD | 579230 | 01757 | 19.215 | Solar | 05_05_7L5 | 01/12/2024 | 01/18/2024 | 3 | 0 | 3 | 01/19/2024 | 01/19/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2024 | Connected |  | N
National Grid | NORTHAMPTON | 658919 | 01062 | 3.8 | Solar | 05_12_23W2 | 12/06/2024 | 01/08/2025 | 15 | 9 | 6 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 | 12/06/2024 | 2/25/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/19/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 577919 | 01532 | 10 | Solar | 05_09_1109W2 | 12/15/2023 | 01/25/2024 | 27 | 22 | 5 | 01/26/2024 | 01/26/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/21/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BROCKTON | 178414 | 02302 | 7.6 | Solar | 05_07_97W1 | 11/27/2017 | 11/27/2017 | 28 | 27 | 1 | 01/09/2018 | 01/09/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2018 |  | 12/3/2018 | N | EXP | 327 |  |  | 0 | 0 | 0 |  |  | 4/30/2019 | Connected |  | N
National Grid | REHOBOTH | 500931 | 02769 | 15.2 | Solar | 05_07_913W47 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/25/2023 | Connected |  | N
National Grid | SAUGUS | 176904 | 01906 | 468 | Solar | 05_09_522L2 | 03/03/2016 | 03/03/2016 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2016 | 03/24/2016 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2016 |  | 12/28/2016 | N | STD | 163 |  |  | 0 | 0 | 0 | 8/1/2016 | 8/1/2016 | 1/5/2017 | Connected |  | N
National Grid | GREAT BARRINGTON | 668548 | 01230 | 10 | Solar | 05_05_335W5 | 01/29/2025 | 02/28/2025 | 3 | 0 | 3 | 03/03/2025 | 03/03/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 5/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/15/2025 | Connected |  | N
National Grid | RANDOLPH | 359928 | 02368 | 8.12 | Solar | 05_09_909W2 | 06/22/2021 | 06/25/2021 | 3 | 0 | 3 | 06/28/2021 | 06/28/2021 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 | 06/22/2021 | 1/14/2023 | Y | EXP | 365 | 11/16/2021 | 11/15/2021 | 0 | 0 | 0 |  |  | 3/3/2022 | Connected |  | N
National Grid | STOUGHTON | 675814 | 02072 | 5.76 | Solar | 05_05_313W3 | 03/05/2025 | 03/11/2025 | 4 | 0 | 4 | 03/12/2025 | 03/12/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 4/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/23/2025 | Connected |  | N
National Grid | LONGMEADOW | 347679 | 01028 | 812.5 | Solar | 05_07_75W1 | 04/22/2021 | 09/10/2021 | 98 | 87 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/13/2021 | 10/07/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/13/2022 | 04/22/2021 | 3/14/2026 | Y | STD | 518 | 02/01/2025 |  | 398 | 196 | 202 |  |  |  | Construction |  | N
National Grid | MILFORD | 649782 | 01757 | 2.32 | Solar | 05_05_7L5 | 11/06/2024 | 01/29/2025 | 3 | 0 | 3 | 01/30/2025 | 01/30/2025 | 59 | 37 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 | 11/06/2024 | 8/14/2026 | Y | EXP | 365 | 12/19/2025 | 01/19/2026 | 32 | 0 | 32 |  |  | 2/11/2026 | Connected |  | N
National Grid | NORTHAMPTON | 667502 | 01060 | 11.4 | Solar | 05_12_23W2 | 02/04/2025 | 05/20/2025 | 33 | 25 | 8 | 05/21/2025 | 05/21/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 595672 | 01532 | 498 | Solar | 05_09_1109W2 | 06/11/2024 | 07/11/2024 | 21 | 11 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/12/2024 | 08/08/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BROCKTON | 189885 | 02302 | 7.6 | Solar | 05_07_97W1 | 07/03/2018 | 07/03/2018 | 14 | 11 | 3 | 09/20/2018 | 09/20/2018 | 32 | 0 | 32 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 574370 | 02769 | 8.448 | Solar | 05_07_913W47 | 02/07/2024 | 02/12/2024 | 3 | 1 | 2 | 02/13/2024 | 02/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 | 02/07/2024 | 3/1/2025 | Y | EXP | 365 | 04/16/2024 | 04/16/2024 | 1 | 0 | 1 |  |  | 6/18/2024 | Connected |  | N
National Grid | SAUGUS | 188191 | 01906 | 480 | Solar | 05_09_522L2 | 09/17/2018 | 09/21/2018 | 3 | 1 | 2 |  |  | 54 | 27 | 27 | 12/27/2018 | 03/08/2019 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  | 03/08/2019 | 49 | 39 | 10 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 678267 | 01258 | 0 | Battery Add-On | 05_05_335W5 | 03/14/2025 | 08/22/2025 | 111 | 109 | 2 | 08/25/2025 | 08/25/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 |  | 10/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2025 | Connected |  | N
National Grid | RANDOLPH | 442267 | 02368 | 22.8 | Solar | 05_09_909W2 | 07/07/2022 | 07/12/2022 | 4 | 3 | 1 | 07/13/2022 | 07/13/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/10/2022 | 07/07/2022 | 9/3/2023 | Y | EXP | 365 | 10/13/2022 | 10/20/2022 | 8 | 0 | 8 |  |  | 11/8/2022 | Connected |  | N
National Grid | STOUGHTON | 684650 | 02072 | 20 | Solar | 05_05_313W3 | 04/11/2025 | 06/13/2025 | 2 | 0 | 2 | 06/16/2025 | 06/16/2025 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/24/2025 |  | 7/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/17/2025 | Connected |  | N
National Grid | LONGMEADOW | 174532 | 01028 | 520 | Solar | 05_07_75W1 | 02/18/2011 | 02/18/2011 | 71 | 0 | 71 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2011 | 05/05/2012 | 232 | 0 | 232 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2012 |  | 10/31/2012 | N | STD | 168 |  |  | 0 | 0 | 0 | 3/6/2013 | 3/6/2013 | 3/6/2013 | Connected |  | N
National Grid | MILFORD | 672543 | 01757 | 13.05 | Solar | 05_05_7L5 | 02/18/2025 | 03/04/2025 | 3 | 0 | 3 | 03/05/2025 | 03/05/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/3/2025 |  | 4/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2025 | Connected |  | N
National Grid | NORTHAMPTON | 669318 | 01060 | 10 | Solar | 05_12_23W2 | 01/31/2025 | 04/17/2025 | 21 | 17 | 4 | 04/18/2025 | 04/18/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 597071 | 01532 | 10 | Solar | 05_09_1109W2 | 03/19/2024 | 03/25/2024 | 4 | 3 | 1 | 03/26/2024 | 03/26/2024 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/4/2024 | 03/19/2024 | 4/5/2025 | Y | EXP | 365 | 07/17/2024 | 08/21/2024 | 36 | 0 | 36 |  |  | 8/3/2024 | Connected |  | N
National Grid | STOUGHTON | 190453 | 02072 | 5 | Solar | 05_07_97W1 | 07/11/2018 | 08/13/2018 | 9 | 0 | 9 | 08/14/2018 | 08/14/2018 | 3 | 0 | 3 | 09/26/2018 | 10/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 10/30/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 11/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2019 | Connected |  | N
National Grid | REHOBOTH | 631809 | 02769 | 9.6 | Solar | 05_07_913W47 | 08/12/2024 | 08/19/2024 | 4 | 1 | 3 | 08/20/2024 | 08/20/2024 | 26 | 18 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 202531 | 01906 | 486 | Solar | 05_09_522L2 | 12/06/2018 | 12/12/2018 | 3 | 0 | 3 | 12/13/2018 | 12/13/2018 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2019 |  | 8/28/2020 | N | EXP | 439 |  |  | 0 | 0 | 0 |  |  | 7/21/2020 | Connected |  | N
National Grid | GREAT BARRINGTON | 681982 | 01230 | 5.76 | Solar | 05_05_335W5 | 04/02/2025 | 04/16/2025 | 4 | 0 | 4 | 04/28/2025 | 04/28/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 | 04/02/2025 | 8/14/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/26/2025 | Connected |  | N
National Grid | RANDOLPH | 445340 | 02368 | 7.6 | Solar | 05_09_909W2 | 08/25/2022 | 08/30/2022 | 3 | 0 | 3 | 08/31/2022 | 08/31/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2022 | 08/25/2022 | 8/10/2024 | Y | EXP | 365 | 04/25/2023 | 08/09/2023 | 107 | 0 | 107 |  |  | 8/16/2023 | Connected |  | N
National Grid | STOUGHTON | 695134 | 02072 | 16.34 | Solar | 05_05_313W3 | 06/02/2025 | 06/05/2025 | 3 | 0 | 3 | 06/06/2025 | 06/06/2025 | 31 | 17 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2025 | Connected |  | N
National Grid | LONGMEADOW | 175513 | 01028 | 250 | Solar | 05_07_75W1 | 03/26/2014 | 03/26/2014 | 6 | 0 | 6 | 04/04/2014 | 04/04/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2014 |  | 7/31/2014 | N | EXP | 9 |  |  | 0 | 0 | 0 | 6/12/2014 | 6/12/2014 | 3/13/2015 | Connected |  | N
National Grid | MILFORD | 676722 | 01757 | 3.77 | Solar | 05_05_7L5 | 03/12/2025 | 03/19/2025 | 5 | 3 | 2 | 03/20/2025 | 03/20/2025 | 100 | 80 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2025 |  | 10/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2026 | Connected |  | N
National Grid | NORTHAMPTON | 674054 | 01060 | 5.76 | Solar | 05_12_23W2 | 03/07/2025 | 03/19/2025 | 8 | 1 | 7 | 03/20/2025 | 03/20/2025 | 44 | 29 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2025 |  | 7/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 599630 | 01532 | 8.41 | Solar | 05_09_1109W2 | 04/05/2024 | 04/12/2024 | 5 | 0 | 5 | 04/16/2024 | 04/16/2024 | 35 | 26 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2024 | 04/05/2024 | 6/25/2025 | Y | EXP | 365 | 08/17/2024 | 08/26/2024 | 10 | 0 | 10 |  |  | 9/20/2024 | Connected |  | N
National Grid | STOUGHTON | 197323 | 02072 | 3.8 | Solar | 05_07_97W1 | 11/09/2018 | 11/20/2018 | 4 | 0 | 4 | 11/21/2018 | 11/21/2018 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 11/18/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/24/2021 | Connected |  | N
National Grid | REHOBOTH | 632274 | 02769 | 3.8 | Solar | 05_07_913W47 | 09/05/2024 | 09/09/2024 | 3 | 1 | 2 | 09/10/2024 | 09/10/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 324800 | 01906 | 432 | Solar | 05_09_522L2 | 05/24/2021 | 06/23/2021 | 21 | 10 | 11 |  |  | 26 | 3 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SHEFFIELD | 710894 | 01257 | 12.54 | Solar | 05_05_335W5 | 08/13/2025 | 08/18/2025 | 2 | 0 | 2 | 08/19/2025 | 08/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2026 | Connected |  | N
National Grid | RANDOLPH | 460987 | 02368 | 5.8 | Solar | 05_09_909W2 | 11/10/2022 | 11/17/2022 | 4 | 0 | 4 | 11/18/2022 | 11/18/2022 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2022 |  | 12/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2023 | Connected |  | N
National Grid | STOUGHTON | 704593 | 02072 | 21.52 | Solar | 05_05_313W3 | 07/14/2025 | 07/23/2025 | 7 | 2 | 5 | 07/24/2025 | 07/24/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2025 | 07/14/2025 | 8/27/2026 | Y | EXP | 365 | 12/17/2025 | 02/06/2026 | 52 | 0 | 52 |  |  | 2/9/2026 | Connected |  | N
National Grid | LONGMEADOW | 178019 | 01028 | 300 | Natural Gas | 05_07_75W1 | 06/29/2017 | 06/29/2017 | 8 | 6 | 2 | 07/13/2017 | 07/13/2017 | 177 | 0 | 177 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/7/2017 |  | 7/5/2018 | N | EXP | 332 |  |  | 0 | 0 | 0 | 8/18/2017 | 8/18/2017 | 12/20/2018 | Connected |  | N
National Grid | MILFORD | 680204 | 01757 | 12.18 | Solar | 05_05_7L5 | 03/24/2025 | 04/17/2025 | 4 | 0 | 4 | 05/12/2025 | 05/12/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/16/2025 | 03/24/2025 | 9/23/2026 | Y | EXP | 365 | 12/05/2025 | 02/03/2026 | 61 | 0 | 61 |  |  | 2/4/2026 | Connected |  | N
National Grid | NORTHAMPTON | 679427 | 01062 | 6 | Solar | 05_12_23W2 | 03/24/2025 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 599473 | 01532 | 11.4 | Solar | 05_09_1109W2 | 03/26/2024 | 04/11/2024 | 12 | 10 | 2 | 04/12/2024 | 04/12/2024 | 32 | 23 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/30/2024 |  | 6/25/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/15/2024 | Connected |  | N
National Grid | AVON | 197198 | 02322 | 7.6 | Solar | 05_07_97W1 | 09/28/2018 | 10/17/2018 | 4 | 3 | 1 | 10/18/2018 | 10/18/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2018 | 09/28/2018 | 9/30/2019 | Y | EXP | 346 | 07/18/2019 | 08/07/2019 | 19 | 0 | 19 |  |  | 9/6/2019 | Connected |  | N
National Grid | REHOBOTH | 636932 | 02769 | 10 | Solar | 05_07_913W47 | 08/30/2024 | 09/12/2024 | 1 | 0 | 1 | 09/13/2024 | 09/13/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/30/2024 | 10/9/2025 | Y | EXP | 365 | 01/28/2025 | 01/27/2025 | 0 | 0 | 0 |  |  | 2/4/2025 | Connected |  | N
National Grid | SAUGUS | 382245 | 01906 | 366.6 | Solar | 05_09_522L2 | 01/19/2022 | 02/09/2022 | 16 | 12 | 4 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2023 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 738968 | 01258 | 15.2 | Solar | 05_05_335W5 | 12/09/2025 | 12/11/2025 | 2 | 0 | 2 | 12/12/2025 | 12/12/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2026 |  | 1/15/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/3/2026 | Connected |  | N
National Grid | RANDOLPH | 472683 | 02368 | 10 | Solar | 05_09_909W2 | 03/21/2023 | 03/23/2023 | 2 | 0 | 2 | 03/24/2023 | 03/24/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/21/2023 | 6/12/2024 | Y | EXP | 365 | 08/01/2023 | 08/04/2023 | 4 | 0 | 4 |  |  | 10/10/2023 | Connected |  | N
National Grid | STOUGHTON | 714034 | 02072 | 10.15 | Solar | 05_05_313W3 | 08/25/2025 | 09/02/2025 | 4 | 2 | 2 | 09/03/2025 | 09/03/2025 | 61 | 42 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2025 |  | 12/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/23/2025 | Connected |  | N
National Grid | LONGMEADOW | 178739 | 01028 | 249 | Solar | 05_07_75W1 | 04/18/2018 | 04/18/2018 | 31 | 0 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/24/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 681007 | 01757 | 7.6 | Solar | 05_05_7L5 | 03/27/2025 | 04/08/2025 | 1 | 0 | 1 | 04/17/2025 | 04/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/15/2025 | 03/27/2025 | 6/2/2026 | Y | EXP | 365 | 08/08/2025 | 08/14/2025 | 7 | 0 | 7 |  |  | 9/4/2025 | Connected |  | N
National Grid | NORTHAMPTON | 679874 | 01060 | 15.58 | Solar | 05_12_23W2 | 03/21/2025 | 03/26/2025 | 3 | 0 | 3 | 03/27/2025 | 03/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2025 |  | 7/2/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/18/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 604624 | 01532 | 7.6 | Solar | 05_09_1109W2 | 04/17/2024 | 04/22/2024 | 1 | 0 | 1 | 04/23/2024 | 04/23/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2024 | 04/17/2024 | 5/9/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2024 | Connected |  | N
National Grid | AVON | 202819 | 02322 | 7.6 | Solar | 05_07_97W1 | 01/21/2019 | 01/30/2019 | 7 | 7 | 0 | 01/31/2019 | 01/31/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/7/2019 | 01/21/2019 | 3/26/2020 | Y | EXP | 413 | 11/07/2019 | 01/10/2020 | 64 | 0 | 64 |  |  | 1/21/2020 | Connected |  | N
National Grid | REHOBOTH | 660301 | 02769 | 7.6 | Solar | 05_07_913W47 | 12/12/2024 | 12/30/2024 | 5 | 0 | 5 | 12/31/2024 | 12/31/2024 | 40 | 16 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2025 | 12/12/2024 | 5/7/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/23/2025 | Connected |  | N
National Grid | SAUGUS | 174112 | 01906 | 695 | Solar | 05_09_522L4 | 03/28/2012 | 03/28/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/18/2012 | 07/02/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/10/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 727130 | 01230 | 5.76 | Solar | 05_05_335W9 | 10/16/2025 | 10/24/2025 | 5 | 2 | 3 | 10/27/2025 | 10/27/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/21/2025 | 10/16/2025 | 12/4/2026 | Y | EXP | 365 | 01/15/2026 | 02/09/2026 | 26 | 0 | 26 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 543487 | 02368 | 3 | Solar | 05_09_909W2 | 07/28/2023 | 08/01/2023 | 2 | 0 | 2 | 08/02/2023 | 08/02/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2023 |  | 9/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/6/2023 | Connected |  | N
National Grid | STOUGHTON | 729724 | 02072 | 12.16 | Solar | 05_05_313W3 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 11/06/2025 | 11/06/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2025 |  | 12/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | LONGMEADOW | 290740 | 01028 | 7.6 | Solar | 05_07_75W1 | 05/11/2020 | 05/22/2020 | 8 | 7 | 1 | 05/26/2020 | 05/26/2020 | 95 | 72 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/5/2020 |  | 11/29/2021 | N | EXP | 45 |  |  | 0 | 0 | 0 |  |  | 11/19/2021 | Connected |  | N
National Grid | MILFORD | 685707 | 01757 | 17.6 | Solar | 05_05_7L5 | 04/22/2025 | 05/02/2025 | 7 | 2 | 5 | 05/05/2025 | 05/05/2025 | 45 | 27 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2025 |  | 7/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2025 | Connected |  | N
National Grid | NORTHAMPTON | 315692 | 01062 | 3.8 | Solar | 05_12_23W3 | 10/08/2020 | 10/13/2020 | 1 | 0 | 1 | 10/14/2020 | 10/14/2020 | 26 | 6 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 10/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 636931 | 01532 | 23 | Solar | 05_09_1109W2 | 08/30/2024 | 09/04/2024 | 2 | 0 | 2 | 09/05/2024 | 09/05/2024 | 12 | 4 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2024 | 08/30/2024 | 10/1/2025 | Y | EXP | 365 | 10/18/2024 | 10/21/2024 | 4 | 0 | 4 |  |  | 1/23/2025 | Connected |  | N
National Grid | AVON | 205636 | 02322 | 13.8 | Solar | 05_07_97W1 | 01/29/2019 | 01/30/2019 | 0 | 0 | 0 | 01/31/2019 | 01/31/2019 | 4 | 2 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 | 01/29/2019 | 10/23/2020 | Y | EXP | 434 | 11/07/2019 | 01/16/2020 | 70 | 0 | 70 |  |  | 10/5/2020 | Connected |  | N
National Grid | SEEKONK | 666314 | 02771 | 10 | Solar | 05_07_913W47 | 01/17/2025 | 03/24/2025 | 9 | 5 | 4 | 03/25/2025 | 03/25/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2025 | 01/17/2025 | 6/12/2026 | Y | EXP | 365 | 05/22/2025 | 10/02/2025 | 134 | 0 | 134 |  |  | 12/10/2025 | Connected |  | N
National Grid | SAUGUS | 174111 | 01906 | 695 | Solar | 05_09_522L4 | 03/28/2012 | 03/28/2012 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/18/2012 | 07/02/2012 | 29 | 0 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/10/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 752839 | 01257 | 3.8 | Solar | 05_05_335W9 | 02/24/2026 | 02/25/2026 | 1 | 0 | 1 | 02/26/2026 | 02/26/2026 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 581268 | 02368 | 11.5 | Solar | 05_09_909W2 | 01/11/2024 | 01/16/2024 | 2 | 0 | 2 | 01/17/2024 | 01/17/2024 | 98 | 77 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 |  | 6/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2024 | Connected |  | N
National Grid | STOUGHTON | 174586 | 02072 | 155 | Solar | 05_05_313W4 | 08/30/2011 | 08/30/2011 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2011 |  | 10/31/2012 | N | EXP | 335 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 7/3/2012 | Connected |  | N
National Grid | LONGMEADOW | 429417 | 01028 | 480 | Solar | 05_07_75W1 | 06/06/2022 | 07/01/2022 | 18 | 12 | 6 |  |  | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/26/2025 |  |  | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 701181 | 01757 | 23 | Solar | 05_05_7L5 | 06/25/2025 | 07/02/2025 | 4 | 2 | 2 | 07/03/2025 | 07/03/2025 | 66 | 50 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2025 |  | 10/15/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2026 | Connected |  | N
National Grid | NORTHAMPTON | 324075 | 01060 | 1.92 | Solar | 05_12_23W3 | 11/19/2020 | 11/24/2020 | 2 | 0 | 2 | 11/25/2020 | 11/25/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 642460 | 01532 | 12 | Solar | 05_09_1109W2 | 10/07/2024 | 10/23/2024 | 11 | 10 | 1 | 10/24/2024 | 10/24/2024 | 79 | 56 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2025 |  | 2/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/22/2025 | Connected |  | N
National Grid | STOUGHTON | 208541 | 02072 | 10 | Solar | 05_07_97W1 | 02/14/2019 | 02/21/2019 | 4 | 4 | 0 | 02/22/2019 | 02/22/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/27/2019 | 02/14/2019 | 9/30/2019 | Y | EXP | 215 | 06/21/2019 | 08/09/2019 | 49 | 0 | 49 |  |  | 8/21/2019 | Connected |  | N
National Grid | SEEKONK | 672325 | 02771 | 10 | Solar | 05_07_913W47 | 02/17/2025 | 03/19/2025 | 1 | 0 | 1 | 03/20/2025 | 03/20/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 | 02/17/2025 | 6/27/2026 | Y | EXP | 365 | 10/01/2025 | 10/22/2025 | 22 | 0 | 22 |  |  | 11/12/2025 | Connected |  | N
National Grid | SAUGUS | 184584 | 01906 | 15.2 | Solar | 05_09_522L4 | 07/15/2018 | 08/14/2018 | 21 | 0 | 21 | 08/15/2018 | 08/15/2018 | 304 | 0 | 304 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 751774 | 01230 | 5.76 | Solar | 05_05_335W9 | 02/18/2026 | 02/24/2026 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | RANDOLPH | 584005 | 02368 | 3.465 | Solar | 05_09_909W2 | 02/27/2024 | 03/05/2024 | 5 | 1 | 4 | 03/06/2024 | 03/06/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2024 |  | 6/13/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/4/2024 | Connected |  | N
National Grid | STOUGHTON | 174651 | 02072 | 125 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | LONGMEADOW | 591631 | 01028 | 7.6 | Solar | 05_07_75W1 | 02/23/2024 | 03/04/2024 | 6 | 0 | 6 | 03/05/2024 | 03/05/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/15/2024 | 02/23/2024 | 11/9/2025 | Y | EXP | 365 | 08/06/2024 | 09/17/2024 | 43 | 0 | 43 |  |  | 4/30/2025 | Connected |  | N
National Grid | HOPEDALE | 716378 | 01747 | 0 | Solar | 05_05_7L5 | 09/03/2025 | 09/16/2025 | 8 | 6 | 2 | 09/17/2025 | 09/17/2025 | 59 | 41 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2025 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | NORTHAMPTON | 490744 | 01060 | 7.6 | Solar | 05_12_23W3 | 02/14/2023 | 02/15/2023 | 1 | 0 | 1 | 02/16/2023 | 02/16/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/24/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 648977 | 01532 | 11.89 | Solar | 05_09_1109W2 | 10/22/2024 | 11/14/2024 | 4 | 1 | 3 | 11/15/2024 | 11/15/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2024 | 10/22/2024 | 12/26/2025 | Y | EXP | 365 | 03/26/2025 | 04/04/2025 | 10 | 0 | 10 |  |  | 4/14/2025 | Connected |  | N
National Grid | STOUGHTON | 208421 | 02072 | 10 | Solar | 05_07_97W1 | 03/18/2019 | 03/19/2019 | 0 | 0 | 0 | 03/20/2019 | 03/20/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2019 | 03/18/2019 | 9/2/2020 | Y | EXP | 527 | 03/04/2020 | 05/12/2020 | 69 | 0 | 69 |  |  | 5/13/2020 | Connected |  | N
National Grid | REHOBOTH | 672195 | 02769 | 7.6 | Solar | 05_07_913W47 | 02/14/2025 | 03/14/2025 | 4 | 0 | 4 | 03/17/2025 | 03/17/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2025 |  | 5/4/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/9/2025 | Connected |  | N
National Grid | SAUGUS | 244368 | 01906 | 4400 | Solar | 05_09_522L4 | 10/03/2019 | 10/23/2019 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/24/2019 | 11/22/2019 | 21 | 14 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2022 | 10/03/2019 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 174306 | 01230 | 95 | Solar | 05_05_335W9 | 01/06/2012 | 01/06/2012 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/27/2012 | 01/06/2012 | 5/7/2012 | Y | EXP | 1 | 06/06/2012 | 06/18/2012 | 8 | 0 | 8 | 7/16/2012 | 7/16/2012 | 7/24/2012 | Connected |  | N
National Grid | RANDOLPH | 605020 | 02368 | 5 | Solar | 05_09_909W2 | 04/18/2024 | 05/06/2024 | 2 | 0 | 2 | 05/07/2024 | 05/07/2024 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 174650 | 02072 | 110 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | LONGMEADOW | 592939 | 01028 | 6 | Solar | 05_07_75W1 | 03/26/2024 | 04/03/2024 | 7 | 3 | 4 | 04/04/2024 | 04/04/2024 | 10 | 5 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2024 | 03/26/2024 | 5/7/2025 | Y | EXP | 365 | 06/01/2024 | 10/28/2024 | 140 | 0 | 140 |  |  | 10/19/2024 | Connected |  | N
National Grid | MILFORD | 719525 | 01757 | 15.2 | Solar | 05_05_7L5 | 09/16/2025 | 10/16/2025 | 20 | 16 | 4 | 10/17/2025 | 10/17/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/23/2026 | Connected |  | N
National Grid | NORTHAMPTON | 531279 | 01060 | 7.6 | Solar | 05_12_23W3 | 06/12/2023 |  | 44 | 27 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHBOROUGH | 653559 | 01532 | 11.5 | Solar | 05_09_1109W2 | 11/11/2024 | 12/29/2024 | 11 | 6 | 5 | 12/30/2024 | 12/30/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2025 |  | 2/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | AVON | 229376 | 02322 | 3.8 | Solar | 05_07_97W1 | 03/05/2020 |  | 170 | 126 | 44 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | REHOBOTH | 685308 | 02769 | 7.6 | Solar | 05_07_913W47 | 04/15/2025 | 05/02/2025 | 17 | 16 | 1 | 06/24/2025 | 06/24/2025 | 48 | 33 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 710987 | 01906 | 5.76 | Solar | 05_09_523L1 | 08/11/2025 | 09/25/2025 | 2 | 0 | 2 | 10/29/2025 | 10/29/2025 | 32 | 15 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2025 | 08/11/2025 | 1/9/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | STOCKBRIDGE | 176265 | 01266 | 200 | Solar | 05_05_335W9 | 09/09/2015 | 09/09/2015 | 3 | 3 | 0 | 09/14/2015 | 09/14/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2015 |  | 9/14/2016 | N | EXP | 362 |  |  | 0 | 0 | 0 | 3/22/2016 | 3/22/2016 | 4/8/2016 | Connected |  | N
National Grid | RANDOLPH | 643025 | 02368 | 6 | Solar | 05_09_909W2 | 09/26/2024 | 10/29/2024 | 3 | 0 | 3 | 10/30/2024 | 10/30/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 09/26/2024 | 12/7/2025 | Y | EXP | 365 | 02/12/2025 | 02/11/2025 | 0 | 0 | 0 |  |  | 2/21/2025 | Connected |  | N
National Grid | STOUGHTON | 174730 | 02072 | 100 | Solar | 05_05_313W4 | 08/22/2012 | 08/22/2012 | 7 | 0 | 7 | 09/04/2012 | 09/04/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 12/12/2013 | 12/12/2013 | 12/13/2013 | Connected |  | N
National Grid | LONGMEADOW | 604070 | 01028 | 10 | Solar | 05_07_75W1 | 04/15/2024 | 04/24/2024 | 4 | 0 | 4 | 04/25/2024 | 04/25/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2024 |  | 7/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/1/2024 | Connected |  | N
National Grid | HOPEDALE | 724146 | 01747 | 5.76 | Solar | 05_05_7L5 | 10/06/2025 | 10/16/2025 | 6 | 4 | 2 | 10/17/2025 | 10/17/2025 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 11/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/29/2025 | Connected |  | N
National Grid | NORTHAMPTON | 561352 | 01060 | 6.175 | Solar | 05_12_23W3 | 11/21/2023 | 11/22/2023 | 1 | 0 | 1 | 11/24/2023 | 11/24/2023 | 64 | 41 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 655413 | 01752 | 5.76 | Solar | 05_09_1109W2 | 11/19/2024 | 12/30/2024 | 13 | 8 | 5 | 12/31/2024 | 12/31/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 2/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 229007 | 02072 | 7.6 | Solar | 05_07_97W1 | 10/15/2019 | 10/22/2019 | 4 | 0 | 4 | 10/23/2019 | 10/23/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2019 |  | 5/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SEEKONK | 683802 | 02771 | 4998 | Other | 05_07_913W67 | 10/16/2025 | 12/11/2025 | 38 | 28 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2025 | 01/09/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | SAUGUS | 713845 | 01906 | 10 | Solar | 05_09_523L1 | 08/21/2025 | 12/18/2025 | 2 | 0 | 2 | 12/19/2025 | 12/19/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2026 |  | 1/22/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 176493 | 01230 | 9.75 | Solar | 05_05_335W9 | 12/10/2015 | 12/10/2015 | 20 | 20 | 0 | 01/11/2016 | 01/11/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2016 |  | 12/15/2016 | N | EXP | 331 |  |  | 0 | 0 | 0 | 3/8/2016 | 3/8/2016 | 3/8/2016 | Connected |  | N
National Grid | RANDOLPH | 644471 | 02368 | 3.8 | Solar | 05_09_909W2 | 10/02/2024 | 11/05/2024 | 5 | 0 | 5 | 11/06/2024 | 11/06/2024 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 174769 | 02072 | 110 | Solar | 05_05_313W4 | 08/27/2012 | 08/27/2012 | 10 | 4 | 6 | 09/13/2012 | 09/13/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 12/10/2013 | 12/10/2013 | 12/13/2013 | Connected |  | N
National Grid | LONGMEADOW | 710142 | 01028 | 15.76 | Solar | 05_07_75W1 | 08/15/2025 | 08/20/2025 | 3 | 0 | 3 | 08/21/2025 | 08/21/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2025 |  | 10/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/27/2025 | Connected |  | N
National Grid | HOPEDALE | 722765 | 01747 | 7.6 | Solar | 05_05_7L5 | 09/29/2025 | 10/06/2025 | 10 | 8 | 2 | 12/02/2025 | 12/02/2025 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 588883 | 01062 | 7.6 | Solar | 05_12_23W3 | 02/29/2024 | 04/09/2024 | 27 | 25 | 2 | 04/10/2024 | 04/10/2024 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/18/2024 | 02/29/2024 | 5/1/2025 | Y | EXP | 365 | 08/20/2024 | 09/06/2024 | 18 | 0 | 18 |  |  | 12/31/2024 | Connected |  | N
National Grid | MARLBOROUGH | 660763 | 01752 | 10 | Solar | 05_09_1109W2 | 12/16/2024 | 01/01/2025 | 6 | 0 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/19/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 234729 | 02072 | 7.6 | Solar | 05_07_97W1 | 08/02/2019 | 08/05/2019 | 0 | 0 | 0 | 08/06/2019 | 08/06/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2019 | 08/02/2019 | 10/2/2020 | Y | EXP | 365 | 03/28/2020 | 05/08/2020 | 41 | 0 | 41 |  |  | 7/16/2020 | Connected |  | N
National Grid | REHOBOTH | 752733 | 02769 | 3.8 | Solar | 05_07_913W67 | 02/23/2026 | 02/26/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 715780 | 01906 | 18.846 | Solar | 05_09_523L1 | 09/02/2025 | 09/09/2025 | 5 | 0 | 5 | 09/10/2025 | 09/10/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/6/2025 |  | 10/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | EGREMONT | 177054 | 01258 | 8 | Solar | 05_05_335W9 | 01/12/2017 | 01/12/2017 | 18 | 17 | 1 | 02/08/2017 | 02/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2017 |  | 1/17/2018 | N | EXP | 342 |  |  | 0 | 0 | 0 | 6/1/2017 | 6/1/2017 | 6/9/2017 | Connected |  | N
National Grid | RANDOLPH | 645789 | 02368 | 5.76 | Solar | 05_09_909W2 | 10/08/2024 | 10/30/2024 | 4 | 0 | 4 | 10/31/2024 | 10/31/2024 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2024 | 10/08/2024 | 12/8/2025 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/27/2025 | Connected |  | N
National Grid | STOUGHTON | 175199 | 02072 | 125 | Solar | 05_05_313W4 | 08/21/2012 | 08/21/2012 | 7 | 0 | 7 | 08/31/2012 | 08/31/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2013 |  | 12/14/2012 | N | EXP | 115 |  |  | 0 | 0 | 0 | 10/29/2013 | 10/29/2013 | 10/29/2013 | Connected |  | N
National Grid | WILBRAHAM | 699462 | 01095 | 7.6 | Solar | 05_07_75W3 | 06/18/2025 | 10/20/2025 | 1 | 0 | 1 | 10/21/2025 | 10/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HOPEDALE | 197724 | 01747 | 1700 | Solar | 05_05_8L1 | 10/25/2018 | 11/14/2018 | 13 | 4 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2018 | 12/14/2018 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 | 10/25/2018 | 12/21/2026 | Y | STD | 365 | 02/04/2023 |  | 1127 | 1003 | 124 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 592548 | 01062 | 6 | Solar | 05_12_23W3 | 04/03/2024 | 04/04/2024 | 1 | 0 | 1 | 04/05/2024 | 04/05/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2024 |  | 4/19/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 670821 | 01752 | 13.92 | Solar | 05_09_1109W2 | 02/07/2025 | 02/14/2025 | 6 | 2 | 4 | 02/18/2025 | 02/18/2025 | 37 | 14 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/15/2025 |  | 4/21/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/20/2025 | Connected |  | N
National Grid | STOUGHTON | 244985 | 02072 | 8.82 | Solar | 05_07_97W1 | 08/20/2019 | 08/23/2019 | 3 | 3 | 0 | 08/26/2019 | 08/26/2019 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/11/2019 | 08/20/2019 | 4/23/2020 | Y | EXP | 225 | 10/23/2019 | 11/08/2019 | 16 | 0 | 16 |  |  | 12/18/2019 | Connected |  | N
National Grid | REHOBOTH | 754679 | 02769 |  | Battery Add-On | 05_07_913W67 | 03/05/2026 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 746511 | 01906 | 11.52 | Solar | 05_09_523L1 | 01/20/2026 | 01/22/2026 | 2 | 0 | 2 | 01/23/2026 | 01/23/2026 | 17 | 4 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GREAT BARRINGTON | 178035 | 01230 | 20 | Solar | 05_05_335W9 | 10/26/2017 | 10/26/2017 | 67 | 67 | 0 | 02/13/2018 | 02/13/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/13/2018 |  | 11/1/2018 | N | EXP | 261 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 664224 | 02368 | 7.6 | Solar | 05_09_909W2 | 01/07/2025 | 03/11/2025 | 5 | 0 | 5 | 03/12/2025 | 03/12/2025 | 36 | 19 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2025 | 01/07/2025 | 7/11/2026 | Y | EXP | 365 | 10/23/2025 | 10/30/2025 | 8 | 0 | 8 |  |  | 11/7/2025 | Connected |  | N
National Grid | STOUGHTON | 176206 | 02072 | 15.6 | Solar | 05_05_313W4 | 04/24/2015 | 04/24/2015 | 6 | 6 | 0 | 05/05/2015 | 05/05/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/12/2015 |  | 8/31/2015 | N | EXP | 111 |  |  | 0 | 0 | 0 | 3/23/2016 | 3/23/2016 | 3/23/2016 | Connected |  | N
National Grid | WILBRAHAM | 735531 | 01095 | 10 | Solar | 05_07_75W3 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 | 01/06/2026 | 01/06/2026 | 19 | 7 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | HOPEDALE | 696703 | 01747 | 5.76 | Solar | 05_05_8L1 | 06/25/2025 | 09/22/2025 | 54 | 51 | 3 | 09/23/2025 | 09/23/2025 | 69 | 66 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2026 | 06/25/2025 | 1/22/2027 | Y | EXP | 365 | 03/04/2026 |  | 3 | 0 | 3 |  |  |  | Construction |  | N
National Grid | NORTHAMPTON | 615559 | 01060 | 5.76 | Solar | 05_12_23W3 | 06/04/2024 | 06/17/2024 | 1 | 0 | 1 | 06/18/2024 | 06/18/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/3/2024 |  | 11/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MARLBOROUGH | 689094 | 01752 | 11.4 | Solar | 05_09_1109W2 | 05/01/2025 | 05/02/2025 | 1 | 0 | 1 | 05/05/2025 | 05/05/2025 | 19 | 2 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  | 6/10/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/8/2025 | Connected |  | N
National Grid | STOUGHTON | 249024 | 02072 | 6 | Solar | 05_07_97W1 | 09/25/2019 | 10/16/2019 | 14 | 14 | 0 | 10/17/2019 | 10/17/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 9/24/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2020 | Connected |  | N
National Grid | SEEKONK | 754242 | 02771 | 7.6 | Solar | 05_07_913W67 | 03/03/2026 |  | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | SAUGUS | 174525 | 01906 | 582 | Solar | 05_09_523L1 | 10/11/2011 | 10/11/2011 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/2/2012 |  | 10/31/2012 | N | EXP | 9 |  |  | 0 | 0 | 0 | 8/31/2012 | 8/31/2012 | 8/31/2012 | Connected |  | N
National Grid | GREAT BARRINGTON | 178508 | 01230 | 5.06 | Solar | 05_05_335W9 | 03/07/2018 | 03/07/2018 | 5 | 0 | 5 | 03/15/2018 | 03/15/2018 | 85 | 0 | 85 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/11/2018 |  | 3/13/2019 | N | EXP | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 672634 | 02368 | 7.6 | Solar | 05_09_909W2 | 02/18/2025 | 03/14/2025 | 5 | 0 | 5 | 03/17/2025 | 03/17/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/10/2025 | 02/18/2025 | 4/15/2026 | Y | EXP | 365 | 08/07/2025 | 08/06/2025 | 0 | 0 | 0 |  |  | 8/8/2025 | Connected |  | N
National Grid | STOUGHTON | 176862 | 02072 | 10 | Solar | 05_05_313W4 | 01/21/2016 | 01/21/2016 | 3 | 3 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2016 |  | 1/26/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/16/2016 | 3/16/2016 | 7/19/2016 | Connected |  | N
National Grid | PALMER | 175816 | 01080 | 360 | Solar | 05_07_75W3 | 07/27/2015 | 07/27/2015 | 2 | 2 | 0 | 07/30/2015 | 07/30/2015 | 554 | 0 | 554 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2015 |  | 9/6/2017 | N | EXP | 768 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 744004 | 01747 | 8.36 | Solar | 05_05_8L1 | 01/07/2026 | 01/08/2026 | 2 | 0 | 2 | 01/22/2026 | 01/22/2026 | 13 | 1 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2026 |  | 2/19/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NORTHAMPTON | 650584 | 01060 | 3.8 | Solar | 05_12_23W3 | 10/30/2024 | 11/26/2024 | 5 | 2 | 3 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2025 |  | 2/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | MARLBOROUGH | 695481 | 01752 | 10.47 | Solar | 05_09_1109W2 | 06/09/2025 | 06/20/2025 | 4 | 0 | 4 | 07/02/2025 | 07/02/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/25/2025 | 06/09/2025 | 7/29/2026 | Y | EXP | 365 | 10/07/2025 | 10/06/2025 | 0 | 0 | 0 |  |  | 10/9/2025 | Connected |  | N
National Grid | AVON | 276855 | 02322 | 10 | Solar | 05_07_97W1 | 03/06/2020 | 04/24/2020 | 36 | 35 | 1 | 04/27/2020 | 04/27/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 03/06/2020 | 3/9/2021 | Y | EXP | 365 | 07/29/2020 | 08/28/2020 | 30 | 0 | 30 |  |  | 10/7/2020 | Connected |  | N
National Grid | ATTLEBORO | 176468 | 02703 | 6 | Solar | 05_07_913W67 | 03/17/2016 | 03/17/2016 | 2 | 2 | 0 | 03/22/2016 | 03/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 | 03/17/2016 | 3/23/2017 | Y | EXP | 345 | 01/25/2017 | 02/11/2017 | 13 | 0 | 13 | 3/15/2017 | 3/15/2017 | 3/17/2017 | Connected |  | N
National Grid | SAUGUS | 175114 | 01906 | 750 | Solar | 05_09_523L1 | 10/10/2013 | 10/10/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 | 01/11/2014 | 04/21/2014 | 67 | 0 | 67 | 10/22/2013 | 12/05/2013 | 30 | 0 | 30 |  | 04/21/2014 | 67 | 0 | 67 |  |  | 0 | 0 | 0 | 5/15/2014 | 10/10/2013 | 6/1/2016 | Y | STD | 748 | 04/22/2016 | 08/19/2016 | 82 | 0 | 82 | 8/22/2016 | 8/22/2016 | 8/22/2016 | Connected |  | N
National Grid | GREAT BARRINGTON | 188692 | 01230 | 499.5 | Solar | 05_05_335W9 | 11/17/2018 | 01/08/2019 | 33 | 25 | 8 | 01/09/2019 | 01/09/2019 | 22 | 4 | 18 | 03/01/2019 | 07/02/2019 | 87 | 53 | 34 |  |  | 0 | 0 | 0 |  | 07/02/2019 | 87 | 53 | 34 |  |  | 0 | 0 | 0 | 7/11/2019 | 11/17/2018 | 1/18/2021 | Y | EXP | 273 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 680727 | 02368 | 10 | Solar | 05_09_909W2 | 03/26/2025 | 04/22/2025 | 2 | 0 | 2 | 05/23/2025 | 05/23/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/23/2025 | 03/26/2025 | 7/1/2026 | Y | EXP | 365 | 07/31/2025 | 07/30/2025 | 0 | 0 | 0 |  |  | 9/20/2025 | Connected |  | N
National Grid | STOUGHTON | 177487 | 02072 | 5.2 | Solar | 05_05_313W4 | 09/23/2016 | 09/23/2016 | 3 | 3 | 0 | 09/29/2016 | 09/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/11/2016 |  | 10/1/2017 | N | EXP | 355 |  |  | 0 | 0 | 0 | 5/10/2017 | 5/10/2017 | 5/12/2017 | Connected |  | N
National Grid | WILBRAHAM | 178407 | 01095 | 498 | Solar | 05_07_75W3 | 04/02/2018 | 04/02/2018 | 12 | 3 | 9 |  |  | 67 | 42 | 25 | 08/20/2018 | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 |  | 10/16/2018 | 41 | 14 | 27 |  |  | 0 | 0 | 0 | 11/28/2018 |  | 10/1/2019 | N | STD | 37 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 176350 | 01747 | 40 | Solar | 05_05_8L1 | 05/13/2015 | 05/13/2015 | 2 | 2 | 0 | 05/18/2015 | 05/18/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2015 | 05/13/2015 | 12/31/2016 | Y | EXP | 514 | 11/05/2015 | 02/03/2016 | 59 | 0 | 59 | 2/4/2016 | 2/4/2016 | 2/16/2016 | Connected |  | N
National Grid | NORTHAMPTON | 654021 | 01060 | 7.6 | Solar | 05_12_23W3 | 11/13/2024 | 11/26/2024 | 5 | 0 | 5 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2025 | 11/13/2024 | 1/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/26/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 696964 | 01532 | 25 | Solar | 05_09_1109W2 | 06/08/2025 | 06/11/2025 | 3 | 0 | 3 | 06/12/2025 | 06/12/2025 | 27 | 5 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/13/2025 | Connected |  | Y
National Grid | AVON | 323027 | 02322 | 9.8 | Solar | 05_07_97W1 | 11/24/2020 | 11/30/2020 | 2 | 0 | 2 | 12/01/2020 | 12/01/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/30/2020 | 11/24/2020 | 11/23/2022 | Y | EXP | 365 | 08/18/2021 | 10/12/2021 | 54 | 3 | 51 |  |  | 12/22/2021 | Connected |  | N
National Grid | ATTLEBORO | 189720 | 02703 | 15.2 | Solar | 05_07_913W67 | 06/29/2018 | 06/29/2018 | 10 | 0 | 10 | 08/30/2018 | 08/30/2018 | 182 | 0 | 182 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2018 |  | 6/29/2020 | N | EXP | 5 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SAUGUS | 177654 | 01906 | 1986 | Solar | 05_09_523L1 | 11/09/2017 | 11/28/2017 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/28/2017 | 12/20/2017 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/22/2018 | 11/09/2017 | 4/17/2024 | Y | STD | 1211 |  |  | 0 | 0 | 0 |  |  | 12/29/2023 | Connected |  | N
National Grid | EGREMONT | 273947 | 01258 | 7.6 | Solar | 05_05_335W9 | 01/23/2020 | 04/14/2020 | 42 | 35 | 7 | 04/15/2020 | 04/15/2020 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2020 | 01/23/2020 | 5/4/2022 | Y | EXP | 365 | 07/31/2021 | 10/04/2021 | 63 | 3 | 60 |  |  | 12/8/2021 | Connected |  | N
National Grid | RANDOLPH | 418955 | 02368 | 3900 | Solar | 05_09_909W3 | 04/14/2022 | 06/02/2022 | 33 | 25 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/03/2022 | 07/01/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 | 04/14/2022 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | STOUGHTON | 186922 | 02072 | 230 | Solar | 05_05_313W4 | 06/01/2018 | 06/01/2018 | 4 | 0 | 4 | 06/15/2018 | 06/15/2018 | 26 | 0 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  | 12/17/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/1/2020 | Connected |  | N
National Grid | PALMER | 184781 | 01080 | 18.9 | Solar | 05_07_75W3 | 06/06/2018 | 06/06/2018 | 48 | 35 | 13 | 08/02/2018 | 08/02/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  | 8/14/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/15/2019 | Connected |  | N
National Grid | MILFORD | 263147 | 01757 | 2000 | Solar | 05_05_8L1 | 06/15/2020 | 07/17/2020 | 24 | 19 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/20/2020 | 08/11/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 655704 | 01060 | 3.77 | Solar | 05_12_23W3 | 11/25/2024 | 12/23/2024 | 10 | 4 | 6 | 01/02/2025 | 01/02/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2025 |  | 3/25/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 696836 | 01532 | 15.2 | Solar | 05_09_1109W2 | 06/06/2025 | 06/12/2025 | 3 | 0 | 3 | 06/13/2025 | 06/13/2025 | 19 | 6 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2025 |  | 7/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/22/2025 | Connected |  | N
National Grid | AVON | 324428 | 02322 | 7.6 | Solar | 05_07_97W1 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 | 11/30/2020 | 4/30/2022 | Y | EXP | 365 | 10/07/2021 | 10/12/2021 | 5 | 0 | 5 |  |  | 3/4/2022 | Connected |  | N
National Grid | ATTLEBORO | 204378 | 02703 | 13.8 | Solar | 05_07_913W67 | 02/26/2019 | 03/12/2019 | 9 | 9 | 0 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2019 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2019 | Connected |  | N
National Grid | SAUGUS | 177719 | 01906 | 3.8 | Solar | 05_09_523L1 | 07/27/2017 | 07/27/2017 | 9 | 9 | 0 | 08/09/2017 | 08/09/2017 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2017 |  | 8/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 273620 | 01258 | 486.6 | Solar | 05_05_335W9 | 01/16/2020 | 01/24/2020 | 1 | 0 | 1 | 01/27/2020 | 01/27/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 2/26/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 602108 | 02368 | 499 | Solar | 05_09_909W3 | 07/29/2024 | 08/08/2024 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/09/2024 | 08/15/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | STOUGHTON | 189709 | 02072 | 381.5 | Natural Gas | 05_05_313W4 | 07/03/2018 | 07/03/2018 | 32 | 23 | 9 |  |  | 24 | 0 | 24 | 10/19/2018 | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 10/30/2019 |  | 5/13/2020 | N | STD | 41 |  |  | 0 | 0 | 0 |  |  | 12/31/2019 | Connected |  | N
National Grid | WILBRAHAM | 318608 | 01095 | 2.4 | Solar | 05_07_75W3 | 10/16/2020 | 10/22/2020 | 3 | 0 | 3 | 10/23/2020 | 10/23/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/2/2020 |  | 12/7/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 285550 | 01747 | 10 | Solar | 05_05_8L1 | 05/06/2020 | 05/08/2020 | 1 | 0 | 1 | 05/11/2020 | 05/11/2020 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2020 | 05/06/2020 | 5/6/2021 | Y | EXP | 365 | 09/30/2020 | 10/22/2020 | 22 | 0 | 22 |  |  | 10/28/2020 | Connected |  | N
National Grid | NORTHAMPTON | 649403 | 01060 | 9.57 | Solar | 05_12_24J1 | 10/24/2024 | 11/13/2024 | 12 | 9 | 3 | 11/14/2024 | 11/14/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/9/2024 |  | 12/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/6/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 697254 | 01532 | 13.8 | Solar | 05_09_1109W2 | 06/16/2025 | 07/02/2025 | 1 | 0 | 1 | 07/11/2025 | 07/11/2025 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | AVON | 325702 | 02322 | 7.6 | Solar | 05_07_97W1 | 12/07/2020 | 12/08/2021 | 4 | 0 | 4 | 12/14/2020 | 12/14/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2021 | 12/07/2020 | 8/8/2023 | Y | EXP | 365 | 03/31/2022 | 04/25/2022 | 26 | 0 | 26 |  |  | 4/10/2023 | Connected |  | N
National Grid | ATTLEBORO | 207438 | 02703 | 3.8 | Solar | 05_07_913W67 | 01/29/2019 | 02/12/2019 | 9 | 0 | 9 | 02/13/2019 | 02/13/2019 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/12/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/18/2019 | Connected |  | N
National Grid | SAUGUS | 178249 | 01906 | 4000 | Solar | 05_09_523L1 | 03/27/2018 | 04/12/2018 | 11 | 11 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/12/2018 | 06/13/2018 | 44 | 31 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2018 | 03/27/2018 | 12/27/2024 | Y | STD | 81 |  |  | 0 | 0 | 0 |  |  | 11/12/2024 | Connected |  | N
National Grid | SHEFFIELD | 282586 | 01257 | 240 | Solar | 05_05_335W9 | 03/05/2020 | 03/10/2020 | 2 | 0 | 2 | 03/11/2020 | 03/11/2020 | 29 | 7 | 22 | 04/22/2020 | 05/28/2020 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 05/28/2020 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 5/28/2020 |  | 12/27/2025 | N | EXP | 2 | 12/23/2020 | 11/06/2025 | 1778 | 1600 | 178 |  |  | 12/31/2025 | Connected |  | N
National Grid | RANDOLPH | 726797 | 02368 | 12.6 | Solar | 05_09_909W3 | 10/15/2025 | 10/27/2025 | 12 | 7 | 5 | 11/25/2025 | 11/25/2025 | 68 | 50 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | STOUGHTON | 191688 | 02072 | 133.2 | Solar | 05_05_313W4 | 07/24/2018 | 09/05/2018 | 26 | 17 | 9 | 09/06/2018 | 09/06/2018 | 27 | 3 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2018 |  | 9/30/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 378486 | 01069 | 5.76 | Solar | 05_07_75W3 | 09/08/2021 | 09/13/2021 | 3 | 0 | 3 | 09/14/2021 | 09/14/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 452367 | 01747 | 8.832 | Solar | 05_05_8L1 | 09/02/2022 | 09/07/2022 | 2 | 0 | 2 | 09/08/2022 | 09/08/2022 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/4/2022 | 09/02/2022 | 1/18/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/3/2023 | Connected |  | Y
National Grid | WILLIAMSBURG | 177484 | 01039 | 19.7 | Solar | 04_04_101L2 | 09/22/2016 | 09/22/2016 | 1 | 1 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/3/2016 | 09/22/2016 | 10/1/2017 | Y | EXP | 363 | 02/21/2017 | 03/16/2017 | 17 | 0 | 17 | 1/4/2017 | 1/4/2017 | 3/21/2017 | Connected |  | N
National Grid | MARLBOROUGH | 698403 | 01752 | 10.4 | Solar | 05_09_1109W2 | 06/13/2025 |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 330177 | 02322 | 12 | Solar | 05_07_97W1 | 12/07/2020 | 04/01/2021 | 82 | 79 | 3 | 04/02/2021 | 04/02/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2021 |  | 6/8/2022 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 288745 | 02703 | 6.96 | Solar | 05_07_913W67 | 04/21/2020 | 04/28/2020 | 5 | 5 | 0 | 04/29/2020 | 04/29/2020 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2020 |  | 6/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SAUGUS | 187670 | 01906 | 1350 | Solar | 05_09_523L1 | 06/26/2018 | 06/28/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2018 | 07/06/2018 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/20/2019 |  | 6/23/2021 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 378195 | 01258 | 11.4 | Solar | 05_05_335W9 | 08/26/2021 | 09/20/2021 | 16 | 15 | 1 | 09/21/2021 | 09/21/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/1/2021 |  | 11/29/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/7/2022 | Connected |  | N
National Grid | RANDOLPH | 735135 | 02368 | 0 | Solar | 05_09_909W3 | 11/29/2025 | 12/02/2025 | 2 | 0 | 2 | 12/03/2025 | 12/03/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 1/21/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | STOUGHTON | 285220 | 02072 | 15.2 | Solar | 05_05_313W4 | 03/25/2020 | 03/30/2020 | 2 | 0 | 2 | 03/31/2020 | 03/31/2020 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/24/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/31/2020 | Connected |  | N
National Grid | PALMER | 391865 | 01069 | 0 | Other | 05_07_75W3 | 01/18/2022 | 01/28/2022 | 8 | 1 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2022 | 02/25/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 466729 | 01757 | 100 | Solar | 05_05_8L1 | 10/07/2022 | 11/10/2022 | 24 | 15 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 12/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GOSHEN | 265329 | 01032 | 15.2 | Solar | 04_04_101L2 | 11/15/2019 | 11/18/2019 | 0 | 0 | 0 | 11/19/2019 | 11/19/2019 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/16/2019 |  | 11/16/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2020 | Connected |  | N
National Grid | MARLBOROUGH | 710770 | 01752 | 10 | Solar | 05_09_1109W2 | 08/08/2025 | 08/15/2025 | 5 | 0 | 5 | 08/18/2025 | 08/18/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2025 | 08/08/2025 | 10/17/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/14/2025 | Connected |  | N
National Grid | AVON | 329783 | 02322 | 3.8 | Solar | 05_07_97W1 | 01/18/2021 | 01/27/2021 | 7 | 4 | 3 | 01/28/2021 | 01/28/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2021 | 01/18/2021 | 1/27/2022 | Y | EXP | 365 | 04/27/2021 | 05/21/2021 | 24 | 0 | 24 |  |  | 9/1/2021 | Connected |  | N
National Grid | ATTLEBORO | 306593 | 02703 | 10 | Solar | 05_07_913W67 | 09/28/2020 | 10/01/2020 | 2 | 0 | 2 | 10/02/2020 | 10/02/2020 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2020 | 09/28/2020 | 9/1/2021 | Y | EXP | 365 | 03/17/2021 | 04/07/2021 | 21 | 0 | 21 |  |  | 5/13/2021 | Connected |  | N
National Grid | GLOUCESTER | 192640 | 01930 | 250 | Solar | 05_09_523L1 | 08/10/2018 | 09/04/2018 | 15 | 0 | 15 | 09/05/2018 | 09/05/2018 | 81 | 44 | 37 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 478522 | 01258 | 7.6 | Solar | 05_05_335W9 | 01/11/2023 | 01/12/2023 | 1 | 0 | 1 | 01/13/2023 | 01/13/2023 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/14/2023 |  | 8/9/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/17/2023 | Connected |  | Y
National Grid | RANDOLPH | 174696 | 02368 | 2266 | Solar | 05_09_909W3 | 12/26/2012 | 12/26/2012 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/09/2013 | 03/20/2013 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 10/06/2014 | 10/06/2014 | 0 | 0 | 0 | 8/22/2013 | 12/26/2012 | 12/31/2016 | Y | STD | 1227 | 11/26/2014 | 02/12/2016 | 300 | 0 | 300 | 2/26/2016 | 2/26/2016 | 2/26/2016 | Connected |  | N
National Grid | STOUGHTON | 286585 | 02072 | 250 | Solar | 05_05_313W4 | 04/07/2020 | 04/11/2020 | 2 | 0 | 2 | 04/13/2020 | 04/13/2020 | 7 | 1 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/2/2020 |  | 6/13/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/9/2021 | Connected |  | N
National Grid | WILBRAHAM | 412236 | 01095 | 0 | Battery Add-On | 05_07_75W3 | 10/02/2022 | 11/15/2022 | 31 | 21 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/16/2022 | 08/03/2023 | 178 | 158 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | HOPEDALE | 480136 | 01747 | 15.2 | Solar | 05_05_8L1 | 11/24/2022 | 12/06/2022 | 8 | 5 | 3 | 12/07/2022 | 12/07/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/9/2023 |  | 1/14/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/20/2023 | Connected |  | N
National Grid | WILLIAMSBURG | 278387 | 01096 | 15.2 | Solar | 04_04_101L2 | 02/26/2020 | 03/03/2020 | 3 | 0 | 3 | 03/04/2020 | 03/04/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/22/2020 |  | 2/5/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2020 | Connected |  | N
National Grid | MARLBOROUGH | 718525 | 01752 | 0 | Solar | 05_09_1109W2 | 09/12/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 39 | 24 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2025 |  | 11/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/26/2026 | Connected |  | N
National Grid | AVON | 336662 | 02322 | 10 | Solar | 05_07_97W1 | 02/05/2021 | 02/12/2021 | 5 | 5 | 0 | 02/16/2021 | 02/16/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 | 02/05/2021 | 2/11/2022 | Y | EXP | 365 | 04/17/2021 | 05/10/2021 | 23 | 0 | 23 |  |  | 5/12/2021 | Connected |  | N
National Grid | ATTLEBORO | 327515 | 02703 | 7.68 | Solar | 05_07_913W67 | 11/20/2020 | 12/15/2020 | 15 | 12 | 3 | 12/16/2020 | 12/16/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/8/2021 |  | 12/10/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/13/2021 | Connected |  | N
National Grid | NANTUCKET | 227774 | 02554 | 5000 | Solar | 05_09_523L1 | 07/17/2019 | 08/16/2019 | 22 | 16 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/19/2019 | 09/09/2019 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SHEFFIELD | 544198 | 01257 | 10 | Solar | 05_05_335W9 | 10/17/2023 | 10/20/2023 | 3 | 2 | 1 | 10/23/2023 | 10/23/2023 | 22 | 5 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 174741 | 02368 | 3000 | Solar | 05_09_909W3 | 01/16/2013 | 01/16/2013 | 37 | 31 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 326590 | 02072 | 11.4 | Solar | 05_05_313W4 | 11/17/2020 | 11/20/2020 | 2 | 0 | 2 | 11/23/2020 | 11/23/2020 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/22/2020 | 11/17/2020 | 9/9/2022 | Y | EXP | 365 | 06/12/2021 | 08/31/2021 | 80 | 3 | 77 |  |  | 9/13/2021 | Connected |  | N
National Grid | BELCHERTOWN | 579567 | 01007 | 4.35 | Solar | 05_07_75W3 | 01/18/2024 | 01/19/2024 | 1 | 0 | 1 | 01/22/2024 | 01/22/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2024 |  | 2/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/9/2024 | Connected |  | N
National Grid | HOPEDALE | 492352 | 01747 | 4999 | Other | 05_05_8L1 | 02/22/2023 | 03/08/2023 | 11 | 2 | 9 |  |  | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 282436 | 01039 | 15.2 | Solar | 04_04_101L2 | 03/05/2020 | 03/09/2020 | 1 | 1 | 0 | 03/10/2020 | 03/10/2020 | 4 | 1 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/13/2020 |  | 8/30/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/13/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 721721 | 01532 | 20 | Solar | 05_09_1109W2 | 09/24/2025 | 09/26/2025 | 2 | 0 | 2 | 09/29/2025 | 09/29/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2025 |  | 10/28/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2025 | Connected |  | N
National Grid | AVON | 342575 | 02322 | 7.6 | Solar | 05_07_97W1 | 02/24/2021 | 03/02/2021 | 3 | 0 | 3 | 03/03/2021 | 03/03/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/13/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 336550 | 02703 | 7.6 | Solar | 05_07_913W67 | 02/19/2021 | 02/25/2021 | 3 | 0 | 3 | 02/26/2021 | 02/26/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/31/2021 | 02/19/2021 | 2/9/2023 | Y | EXP | 365 | 11/25/2021 | 01/10/2022 | 47 | 0 | 47 |  |  | 4/14/2022 | Connected |  | N
National Grid | NANTUCKET | 331603 | 02554 | 8.88 | Solar | 05_09_523L1 | 12/14/2020 | 01/05/2021 | 14 | 11 | 3 | 01/06/2021 | 01/06/2021 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2021 |  | 1/4/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/10/2021 | Connected |  | N
National Grid | EGREMONT | 591098 | 01258 | 7.6 | Solar | 05_05_335W9 | 03/04/2024 | 03/07/2024 | 3 | 0 | 3 | 03/08/2024 | 03/08/2024 | 5 | 4 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2024 | 03/04/2024 | 5/10/2025 | Y | EXP | 365 | 06/13/2024 | 08/21/2024 | 70 | 0 | 70 |  |  | 11/12/2024 | Connected |  | N
National Grid | RANDOLPH | 174919 | 02368 | 3000 | Solar | 05_09_909W3 | 02/26/2013 | 02/26/2013 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/07/2013 | 04/08/2013 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/29/2013 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 346371 | 02072 | 250 | Solar | 05_05_313W4 | 04/07/2021 | 04/23/2021 | 9 | 0 | 9 | 04/30/2021 | 04/30/2021 | 26 | 2 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 680142 | 01095 | 11.5 | Solar | 05_07_75W3 | 03/26/2025 | 03/31/2025 | 3 | 0 | 3 | 04/01/2025 | 04/01/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 10/13/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/12/2025 | Connected |  | N
National Grid | HOPEDALE | 571237 | 01747 | 5 | Solar | 05_05_8L1 | 12/05/2023 | 02/12/2024 | 47 | 37 | 10 | 02/13/2024 | 02/13/2024 | 12 | 5 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2024 | 12/05/2023 | 3/20/2025 | Y | EXP | 365 | 08/03/2024 | 08/02/2024 | 0 | 0 | 0 |  |  | 9/12/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 284042 | 01096 | 2850 | Solar | 04_04_101L2 | 08/04/2020 | 08/14/2020 | 8 | 3 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/17/2020 | 10/06/2020 | 35 | 18 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/13/2021 | 08/04/2020 | 6/4/2025 | Y | STD | 572 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHBOROUGH | 641155 | 01532 | 2500 | Solar | 05_09_1109W3 | 11/04/2024 | 01/30/2025 | 58 | 48 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/31/2025 | 03/06/2025 | 25 | 5 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Study |  | N
National Grid | AVON | 366170 | 02322 | 6 | Solar | 05_07_97W1 | 06/25/2021 | 06/30/2021 | 4 | 2 | 2 | 07/01/2021 | 07/01/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2021 |  | 8/10/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/20/2021 | Connected |  | N
National Grid | ATTLEBORO | 347865 | 02703 | 9.8 | Solar | 05_07_913W67 | 04/20/2021 | 12/29/2021 | 3 | 0 | 3 | 04/27/2021 | 04/27/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/15/2021 | 04/20/2021 | 2/1/2023 | Y | EXP | 365 | 04/15/2022 | 10/04/2022 | 172 | 0 | 172 |  |  | 11/21/2022 | Connected |  | N
National Grid | NANTUCKET | 345778 | 02554 | 130 | Solar | 05_09_523L1 | 03/09/2021 | 03/23/2021 | 10 | 0 | 10 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2022 | 03/09/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 605877 | 01230 | 8.41 | Solar | 05_05_335W9 | 04/23/2024 | 05/24/2024 | 1 | 0 | 1 | 05/28/2024 | 05/28/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/17/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 174914 | 02368 | 21 | Solar | 05_09_909W3 | 09/19/2012 | 09/19/2012 | 7 | 0 | 7 | 10/01/2012 | 10/01/2012 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/14/2012 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 471917 | 02072 | 3.8 | Solar | 05_05_313W4 | 11/08/2022 | 11/14/2022 | 3 | 0 | 3 | 11/15/2022 | 11/15/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 638260 | 01069 | 990 | Solar | 05_07_75W5 | 05/08/2025 | 07/09/2025 | 40 | 30 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/10/2025 | 07/29/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | MILFORD | 643534 | 01757 | 7.6 | Solar | 05_05_8L1 | 09/27/2024 | 11/19/2024 | 6 | 3 | 3 | 11/20/2024 | 11/20/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/10/2025 | Connected |  | N
National Grid | GOSHEN | 349242 | 01032 | 19.72 | Solar | 04_04_101L2 | 03/26/2021 | 04/16/2021 | 14 | 14 | 0 | 04/20/2021 | 04/20/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/7/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/31/2021 | Connected |  | N
National Grid | NORTHBOROUGH | 711945 | 01532 | 10 | Solar | 05_09_1109W3 | 08/13/2025 | 09/03/2025 | 5 | 0 | 5 | 09/30/2025 | 09/30/2025 | 25 | 10 | 15 | 11/20/2025 | 12/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 12/22/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 12/23/2025 |  | 12/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | AVON | 392185 | 02322 | 6 | Solar | 05_07_97W1 | 11/18/2021 | 01/05/2022 | 3 | 0 | 3 | 11/23/2021 | 11/23/2021 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2021 | 11/18/2021 | 2/9/2023 | Y | EXP | 365 | 01/19/2022 | 02/08/2022 | 21 | 0 | 21 |  |  | 2/12/2022 | Connected |  | N
National Grid | ATTLEBORO | 356589 | 02703 | 9.8 | Solar | 05_07_913W67 | 05/05/2021 | 06/10/2021 | 1 | 0 | 1 | 06/11/2021 | 06/11/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2021 | 05/05/2021 | 12/23/2022 | Y | EXP | 365 | 11/02/2021 | 12/23/2021 | 52 | 0 | 52 |  |  | 3/25/2022 | Connected |  | N
National Grid | NANTUCKET | 345775 | 02554 | 150 | Solar | 05_09_523L1 | 03/09/2021 | 03/23/2021 | 10 | 0 | 10 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 03/09/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 618857 | 01230 | 15.2 | Solar | 05_05_335W9 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 175023 | 02368 | 21 | Solar | 05_09_909W3 | 09/19/2012 | 09/19/2012 | 7 | 0 | 7 | 10/01/2012 | 10/01/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2012 | 09/19/2012 | 12/14/2012 | Y | EXP | 65 |  |  | 0 | 0 | 0 | 10/12/2012 | 10/12/2012 | 3/21/2013 | Connected |  | N
National Grid | STOUGHTON | 483268 | 02072 | 10 | Solar | 05_05_313W4 | 12/14/2022 | 12/20/2022 | 4 | 0 | 4 | 12/21/2022 | 12/21/2022 | 28 | 4 | 24 | 02/06/2023 | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 |  | 03/20/2023 | 30 | 0 | 30 |  |  | 0 | 0 | 0 | 3/23/2023 |  | 4/25/2024 | N | EXP | 365 | 04/08/2023 | 04/26/2023 | 19 | 0 | 19 |  |  | 7/20/2023 | Connected |  | N
National Grid | WILBRAHAM | 747001 | 01095 | 11.5 | Solar | 05_07_75W5 | 01/22/2026 | 02/27/2026 | 25 | 23 | 2 | 03/02/2026 | 03/02/2026 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 645422 | 01757 | 2.03 | Solar | 05_05_8L1 | 10/18/2024 | 11/14/2024 | 3 | 0 | 3 | 11/15/2024 | 11/15/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/27/2024 | 10/18/2024 | 1/2/2026 | Y | EXP | 365 | 03/06/2025 | 07/18/2025 | 135 | 0 | 135 |  |  | 8/1/2025 | Connected |  | N
National Grid | GOSHEN | 362967 | 01032 | 19.99 | Solar | 04_04_101L2 | 06/10/2021 | 07/01/2021 | 16 | 13 | 3 | 07/02/2021 | 07/02/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/4/2021 |  | 8/20/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2021 | Connected |  | N
National Grid | MARLBOROUGH | 724129 | 01752 | 23.034 | Solar | 05_09_1109W3 | 10/07/2025 | 10/13/2025 | 3 | 1 | 2 | 10/14/2025 | 10/14/2025 | 86 | 71 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2026 | 10/07/2025 | 3/4/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | AVON | 445564 | 02322 | 10 | Solar | 05_07_97W1 | 08/01/2022 | 08/02/2022 | 1 | 0 | 1 | 08/03/2022 | 08/03/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2022 | 08/01/2022 | 3/1/2024 | Y | EXP | 365 | 03/02/2023 | 03/01/2023 | 0 | 0 | 0 |  |  | 3/7/2023 | Connected |  | N
National Grid | ATTLEBORO | 398831 | 02703 | 9.8 | Solar | 05_07_913W67 | 12/20/2021 | 12/21/2021 | 1 | 0 | 1 | 12/22/2021 | 12/22/2021 | 25 | 8 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2022 | 12/20/2021 | 2/24/2024 | Y | EXP | 365 | 06/30/2022 | 02/22/2023 | 238 | 0 | 238 |  |  | 4/19/2023 | Connected |  | N
National Grid | NANTUCKET | 345769 | 02554 | 103.3 | Solar | 05_09_523L1 | 03/09/2021 | 03/23/2021 | 10 | 0 | 10 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 03/09/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 668172 | 01230 | 10 | Solar | 05_05_335W9 | 01/27/2025 | 02/20/2025 | 1 | 0 | 1 | 02/21/2025 | 02/21/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 | 01/27/2025 | 4/1/2026 | Y | EXP | 365 | 09/11/2025 | 11/26/2025 | 77 | 0 | 77 |  |  | 12/4/2025 | Connected |  | N
National Grid | RANDOLPH | 175173 | 02368 | 19 | Solar | 05_09_909W3 | 11/20/2012 | 11/20/2012 | 7 | 0 | 7 | 12/05/2012 | 12/05/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/12/2013 |  | 2/28/2013 | N | EXP | 16 |  |  | 0 | 0 | 0 | 2/12/2013 | 2/12/2013 | 7/24/2013 | Connected |  | N
National Grid | STOUGHTON | 521440 | 02072 | 6.175 | Solar | 05_05_313W4 | 06/12/2023 | 06/13/2023 | 1 | 0 | 1 | 06/14/2023 | 06/14/2023 | 78 | 57 | 21 | 10/11/2023 | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  | 10/31/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 | 11/6/2023 |  | 11/18/2024 | N | EXP | 365 | 03/26/2024 | 04/11/2024 | 17 | 0 | 17 |  |  | 5/3/2024 | Connected |  | N
National Grid | WILBRAHAM | 174838 | 01095 | 75 | Solar | 05_07_75W5 | 08/28/2012 | 08/28/2012 | 6 | 0 | 6 | 09/10/2012 | 09/10/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/17/2012 | 08/28/2012 | 12/27/2012 | Y | EXP | 1 | 04/10/2013 | 04/22/2013 | 7 | 0 | 7 | 4/23/2013 | 4/23/2013 | 6/3/2013 | Connected |  | N
National Grid | HOPEDALE | 709801 | 01747 | 7.6 | Solar | 05_05_8L1 | 08/05/2025 | 09/16/2025 | 2 | 0 | 2 | 09/17/2025 | 09/17/2025 | 52 | 24 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 404153 | 01053 | 28.71 | Solar | 04_04_101L2 | 03/11/2022 | 03/14/2022 | 1 | 0 | 1 | 03/15/2022 | 03/15/2022 | 19 | 8 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2022 |  | 4/23/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/5/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 725591 | 01532 | 15.2 | Solar | 05_09_1109W3 | 11/19/2025 | 11/24/2025 | 3 | 0 | 3 | 11/25/2025 | 11/25/2025 | 6 | 1 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 12/9/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AVON | 466464 | 02322 | 10 | Solar | 05_07_97W1 | 10/12/2022 | 10/13/2022 | 1 | 0 | 1 | 10/14/2022 | 10/14/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/14/2022 | 10/12/2022 | 6/14/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/28/2023 | Connected |  | N
National Grid | ATTLEBORO | 417002 | 02703 | 9.84 | Solar | 05_07_913W67 | 03/10/2022 | 03/11/2022 | 1 | 0 | 1 | 03/14/2022 | 03/14/2022 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/16/2022 |  | 5/4/2023 | N | EXP | 4 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 345736 | 02554 | 233.3 | Solar | 05_09_523L1 | 03/09/2021 | 03/23/2021 | 10 | 0 | 10 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 03/09/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | EGREMONT | 669026 | 01252 | 0 | Battery Add-On | 05_05_335W9 | 02/04/2025 | 02/11/2025 | 5 | 1 | 4 | 02/12/2025 | 02/12/2025 | 59 | 36 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2025 |  | 5/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2025 | Connected |  | N
National Grid | RANDOLPH | 175545 | 02368 | 990 | Solar | 05_09_909W3 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 6/10/2015 | 12/05/2014 | 12/31/2016 | Y | STD | 57 |  |  | 0 | 0 | 0 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | STOUGHTON | 540566 | 02072 | 480 | Solar | 05_05_313W4 | 09/18/2023 | 12/06/2023 | 54 | 46 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/07/2023 | 02/21/2024 | 51 | 32 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 174929 | 01095 | 990 | Solar | 05_07_75W5 | 08/22/2013 | 08/22/2013 | 6 | 0 | 6 | 09/03/2013 | 09/03/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/28/2014 | 08/22/2013 | 1/31/2014 | Y | EXP | 3 | 11/05/2014 | 12/18/2014 | 29 | 0 | 29 | 12/16/2014 | 12/16/2014 | 12/30/2014 | Connected |  | N
National Grid | HOPEDALE | 729560 | 01747 | 17.6 | Solar | 05_05_8L2 | 10/28/2025 | 11/04/2025 | 5 | 1 | 4 | 11/05/2025 | 11/05/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2025 |  | 2/20/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Meter Installation |  | Y
National Grid | NORTHAMPTON | 411210 | 01053 | 20 | Solar | 04_04_101L2 | 02/10/2022 | 02/11/2022 | 1 | 0 | 1 | 02/14/2022 | 02/14/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/9/2022 |  | 3/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 731155 | 01532 | 27.188 | Solar | 05_09_1109W3 | 11/07/2025 | 11/10/2025 | 1 | 0 | 1 | 11/12/2025 | 11/12/2025 | 40 | 20 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/13/2026 |  | 2/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | AVON | 475958 | 02322 | 3.8 | Solar | 05_07_97W1 | 06/07/2023 | 11/13/2023 | 108 | 106 | 2 | 11/14/2023 | 11/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/28/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 432815 | 02703 | 0 | Solar | 05_07_913W67 | 06/09/2022 | 06/10/2022 | 1 | 0 | 1 | 06/13/2022 | 06/13/2022 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 | 06/09/2022 | 10/11/2023 | Y | EXP | 365 | 09/15/2022 | 10/11/2022 | 27 | 0 | 27 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 345735 | 02554 | 180 | Solar | 05_09_523L1 | 03/09/2021 | 03/23/2021 | 10 | 0 | 10 |  |  | 58 | 32 | 26 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/2/2022 | 03/09/2021 |  | Y | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 670686 | 01230 | 7.68 | Solar | 05_05_335W9 | 02/07/2025 | 03/26/2025 | 4 | 0 | 4 | 03/27/2025 | 03/27/2025 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/8/2025 |  | 4/18/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/14/2025 | Connected |  | N
National Grid | RANDOLPH | 175546 | 02368 | 852 | Solar | 05_09_909W3 | 12/05/2014 | 12/05/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2014 | 01/13/2015 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 10/19/2016 | 10/19/2016 | 0 | 0 | 0 | 6/10/2015 | 12/05/2014 | 12/31/2016 | Y | STD | 57 |  |  | 0 | 0 | 0 | 7/6/2017 | 7/6/2017 | 7/6/2017 | Connected |  | N
National Grid | STOUGHTON | 551451 | 02072 | 250 | Solar | 05_05_313W4 | 09/18/2023 | 12/26/2023 | 67 | 58 | 9 | 12/27/2023 | 12/27/2023 | 38 | 17 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2024 |  | 1/20/2026 | N | EXP | 33 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WILBRAHAM | 175391 | 01095 | 266 | Solar | 05_07_75W5 | 09/12/2014 | 09/12/2014 | 6 | 0 | 6 | 09/23/2014 | 09/23/2014 | 0 | 0 | 0 | 02/27/2015 | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  | 04/01/2015 | 22 | 0 | 22 |  |  | 0 | 0 | 0 | 4/14/2015 |  | 12/31/2016 | N | EXP | 627 |  |  | 0 | 0 | 0 | 6/16/2015 | 6/16/2015 | 3/7/2017 | Connected |  | N
National Grid | HOPEDALE | 174346 | 01747 | 26 | Solar | 05_05_8L2 | 07/28/2010 | 07/28/2010 | 28 | 0 | 28 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 10/31/2012 | N | EXP | 42 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 422444 | 01096 | 49.68 | Solar | 04_04_101L2 | 04/14/2022 | 09/09/2022 | 101 | 91 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2023 | 04/14/2022 | 1/11/2024 | Y | STD | 28 | 07/21/2023 | 09/21/2023 | 63 | 0 | 63 |  |  | 11/17/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 747700 | 01532 | 5.76 | Solar | 05_09_1109W3 | 01/27/2026 | 01/30/2026 | 2 | 0 | 2 | 02/06/2026 | 02/06/2026 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | AVON | 508496 | 02322 | 6 | Solar | 05_07_97W1 | 03/23/2023 | 04/12/2023 | 15 | 12 | 3 | 04/13/2023 | 04/13/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/16/2023 | 03/23/2023 | 10/3/2024 | Y | EXP | 365 | 08/01/2023 | 10/04/2023 | 65 | 0 | 65 |  |  | 11/1/2023 | Connected |  | N
National Grid | ATTLEBORO | 467208 | 02703 | 5 | Solar | 05_07_913W67 | 11/10/2022 | 11/14/2022 | 1 | 0 | 1 | 11/15/2022 | 11/15/2022 | 20 | 1 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 365209 | 02554 | 15.2 | Solar | 05_09_523L1 | 06/23/2021 | 06/25/2021 | 2 | 0 | 2 | 06/28/2021 | 06/28/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2021 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | LENOX | 684075 | 01240 | 10 | Solar | 05_05_335W9 | 04/09/2025 | 04/30/2025 | 3 | 0 | 3 | 05/12/2025 | 05/12/2025 | 70 | 55 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2025 |  | 9/11/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/6/2025 | Connected |  | N
National Grid | RANDOLPH | 175567 | 02368 | 5.5 | Solar | 05_09_909W3 | 10/08/2014 | 10/08/2014 | 6 | 0 | 6 | 10/20/2014 | 10/20/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/2/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 619949 | 02072 | 11.5 | Solar | 05_05_313W4 | 06/24/2024 | 06/26/2024 | 4 | 0 | 4 | 11/27/2024 | 11/27/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/26/2024 | 06/24/2024 | 1/28/2026 | Y | EXP | 365 | 02/25/2025 | 02/24/2025 | 0 | 0 | 0 |  |  | 6/4/2025 | Connected |  | N
National Grid | WILBRAHAM | 175879 | 01095 | 446.4 | Solar | 05_07_75W5 | 03/09/2015 | 03/09/2015 | 4 | 0 | 4 | 03/16/2015 | 03/16/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2015 |  | 9/30/2015 | N | EXP | 182 |  |  | 0 | 0 | 0 | 4/6/2015 | 4/6/2015 | 3/30/2017 | Connected |  | N
National Grid | HOPEDALE | 174706 | 01747 | 1500 | Solar | 05_05_8L2 | 06/10/2013 | 06/10/2013 | 12 | 6 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/28/2013 | 09/03/2013 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/30/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 436989 | 01096 | 17.6 | Solar | 04_04_101L2 | 06/28/2022 | 07/05/2022 | 5 | 3 | 2 | 07/06/2022 | 07/06/2022 | 31 | 10 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/19/2022 |  | 8/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/13/2022 | Connected |  | N
National Grid | NORTHBOROUGH | 752097 | 01532 | 4.8 | Solar | 05_09_1109W3 | 02/19/2026 | 02/26/2026 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | AVON | 507261 | 02322 | 6 | Solar | 05_07_97W1 | 03/23/2023 | 03/28/2023 | 3 | 0 | 3 | 03/29/2023 | 03/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2023 | 03/23/2023 | 9/11/2024 | Y | EXP | 365 | 07/20/2023 | 09/08/2023 | 51 | 0 | 51 |  |  | 9/21/2023 | Connected |  | N
National Grid | NORTON | 524728 | 02766 | 14.976 | Solar | 05_07_913W67 | 07/11/2023 | 05/23/2023 | 5 | 4 | 1 | 07/18/2023 | 07/18/2023 | 48 | 27 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2023 |  | 10/4/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/11/2023 | Connected |  | N
National Grid | NANTUCKET | 470981 | 02554 | 15.2 | Solar | 05_09_523L1 | 11/08/2022 | 11/09/2022 | 1 | 0 | 1 | 11/10/2022 | 11/10/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 697113 | 01266 | 250 | Solar | 05_05_336W1 | 07/17/2025 | 08/26/2025 | 27 | 19 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/27/2025 | 09/23/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | RANDOLPH | 175781 | 02368 | 16 | Solar | 05_09_909W3 | 07/22/2015 | 07/22/2015 | 4 | 4 | 0 | 07/28/2015 | 07/28/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2015 |  | 3/18/2016 | N | EXP | 218 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/23/2016 | Connected |  | N
National Grid | STOUGHTON | 655214 | 02072 | 10 | Solar | 05_05_313W4 | 11/19/2024 | 12/10/2024 | 2 | 0 | 2 | 12/11/2024 | 12/11/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | WILBRAHAM | 176324 | 01095 | 50 | Solar | 05_07_75W5 | 07/16/2015 | 07/16/2015 | 3 | 3 | 0 | 07/21/2015 | 07/21/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/28/2015 |  | 7/21/2016 | N | EXP | 359 |  |  | 0 | 0 | 0 | 2/24/2016 | 2/24/2016 | 2/24/2016 | Connected |  | N
National Grid | HOPEDALE | 175369 | 01747 | 648 | Solar | 05_05_8L2 | 02/10/2014 | 02/10/2014 | 5 | 0 | 5 | 02/19/2014 | 02/19/2014 | 0 | 0 | 0 | 04/09/2014 | 05/27/2014 | 32 | 8 | 24 |  |  | 0 | 0 | 0 |  | 05/27/2014 | 32 | 8 | 24 |  |  | 0 | 0 | 0 | 5/28/2014 | 02/10/2014 | 10/14/2014 | Y | EXP | 139 | 10/28/2014 | 11/08/2014 | 9 | 0 | 9 | 12/23/2014 | 12/23/2014 | 12/29/2014 | Connected |  | N
National Grid | GOSHEN | 472903 | 01032 | 20 | Solar | 04_04_101L2 | 11/02/2022 | 11/08/2022 | 5 | 4 | 1 | 11/09/2022 | 11/09/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 12/21/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/7/2023 | Connected |  | N
National Grid | NORTHBOROUGH | 174135 | 01532 | 12 | Solar | 05_09_1109W3 | 05/08/2012 | 05/08/2012 | 7 | 0 | 7 | 05/21/2012 | 05/21/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2012 |  | 7/10/2012 | N | EXP | 14 |  |  | 0 | 0 | 0 | 8/29/2012 | 8/29/2012 | 11/20/2012 | Connected |  | N
National Grid | AVON | 522517 | 02322 | 10 | Solar | 05_07_97W1 | 06/01/2023 | 08/21/2023 | 55 | 55 | 0 | 08/22/2023 | 08/22/2023 | 40 | 7 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 595908 | 02766 | 10 | Solar | 05_07_913W67 | 03/18/2024 | 03/19/2024 | 1 | 0 | 1 | 03/20/2024 | 03/20/2024 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/25/2024 |  | 3/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/20/2024 | Connected |  | N
National Grid | NANTUCKET | 478811 | 02554 | 10 | Solar | 05_09_523L1 | 02/09/2023 | 02/13/2023 | 2 | 0 | 2 | 02/14/2023 | 02/14/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/20/2023 |  | 3/22/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/22/2023 | Connected |  | N
National Grid | GREAT BARRINGTON | 174349 | 01230 | 60 | Solar | 05_05_336W1 | 07/24/2012 | 07/24/2012 | 9 | 0 | 9 | 08/06/2012 | 08/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 | 07/24/2012 | 11/30/2012 | Y | EXP | 12 | 02/05/2013 | 04/11/2013 | 38 | 0 | 38 | 4/22/2013 | 4/22/2013 | 4/23/2013 | Connected |  | N
National Grid | RANDOLPH | 177781 | 02368 | 8.8 | Solar | 05_09_909W3 | 06/01/2017 | 06/01/2017 | 4 | 4 | 0 | 06/07/2017 | 06/07/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 | 06/01/2017 | 6/6/2018 | Y | EXP | 363 | 08/24/2017 | 08/28/2017 | 2 | 0 | 2 | 9/1/2017 | 9/1/2017 | 9/1/2017 | Connected |  | N
National Grid | STOUGHTON | 674719 | 02072 | 3.8 | Solar | 05_05_313W4 | 02/27/2025 | 03/19/2025 | 80 | 80 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 176443 | 01069 | 360 | Solar | 05_07_75W5 | 05/15/2016 | 05/15/2016 | 21 | 21 | 0 | 06/15/2016 | 06/15/2016 | 97 | 0 | 97 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/21/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | HOPEDALE | 175518 | 01747 | 495 | Solar | 05_05_8L2 | 04/01/2014 | 04/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2014 | 07/11/2014 | 61 | 32 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2016 | 04/01/2014 | 12/29/2017 | Y | STD | 652 | 03/28/2017 | 12/18/2017 | 177 | 0 | 177 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | WILLIAMSBURG | 531486 | 01039 | 5.584 | Solar | 04_04_101L2 | 06/26/2023 | 08/28/2023 | 44 | 44 | 0 | 08/29/2023 | 08/29/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2023 |  | 10/6/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/30/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 174186 | 01532 | 11.61 | Solar | 05_09_1109W3 | 10/31/2011 | 10/31/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2012 |  | 5/1/2012 | N | EXP | 41 |  |  | 0 | 0 | 0 | 5/17/2012 | 5/17/2012 | 7/16/2012 | Connected |  | N
National Grid | AVON | 526253 | 02322 | 10 | Solar | 05_07_97W1 | 05/26/2023 |  | 82 | 80 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 607609 | 02766 | 7.56 | Solar | 05_07_913W67 | 04/30/2024 | 05/06/2024 | 3 | 0 | 3 | 05/07/2024 | 05/07/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/20/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 548426 | 02554 | 11.6 | Solar | 05_09_523L1 | 10/12/2023 | 10/16/2023 | 2 | 0 | 2 | 10/17/2023 | 10/17/2023 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/9/2023 | 10/12/2023 | 11/29/2024 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/8/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 174446 | 01230 | 82 | Solar | 05_05_336W1 | 07/10/2012 | 07/10/2012 | 6 | 0 | 6 | 07/20/2012 | 07/20/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/12/2012 |  | 11/30/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 10/3/2012 | 10/3/2012 | 12/31/2012 | Connected |  | N
National Grid | RANDOLPH | 177869 | 02368 | 176 | Solar | 05_09_909W3 | 08/09/2017 | 08/09/2017 | 15 | 15 | 0 | 08/24/2017 | 08/24/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2017 |  | 8/15/2018 | N | EXP | 348 |  |  | 0 | 0 | 0 | 3/2/2018 | 3/2/2018 | 3/2/2018 | Connected |  | N
National Grid | STOUGHTON | 731390 | 02072 | 3.8 | Solar | 05_05_313W4 | 11/04/2025 | 11/05/2025 | 1 | 0 | 1 | 12/03/2025 | 12/03/2025 | 38 | 25 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 177908 | 01095 | 112 | Solar | 05_07_75W5 | 08/16/2017 | 08/16/2017 | 9 | 9 | 0 | 08/29/2017 | 08/29/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2017 |  | 8/21/2018 | N | EXP | 356 |  |  | 0 | 0 | 0 | 12/19/2017 | 12/19/2017 | 12/21/2017 | Connected |  | N
National Grid | MILFORD | 175517 | 01757 | 495 | Solar | 05_05_8L2 | 04/01/2014 | 04/01/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/11/2014 | 07/11/2014 | 61 | 32 | 29 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2016 | 04/01/2014 | 12/29/2017 | Y | STD | 652 | 03/28/2017 | 12/18/2017 | 177 | 0 | 177 | 12/28/2017 | 12/28/2017 | 12/28/2017 | Connected |  | N
National Grid | WILLIAMSBURG | 606670 | 01096 | 20 | Solar | 04_04_101L2 | 04/29/2024 | 05/01/2024 | 3 | 1 | 2 | 05/02/2024 | 05/02/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2024 |  | 5/14/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/4/2024 | Connected |  | N
National Grid | NORTHBOROUGH | 174715 | 01532 | 2000 | Solar | 05_09_1109W3 | 01/13/2014 | 01/13/2014 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2014 | 02/10/2014 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/29/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 538902 | 02322 | 10 | Solar | 05_07_97W1 | 07/10/2023 | 08/31/2023 | 35 | 34 | 1 | 09/01/2023 | 09/01/2023 | 70 | 52 | 18 | 01/31/2024 | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  | 03/04/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 4/3/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 617786 | 02766 | 10 | Solar | 05_07_913W67 | 06/13/2024 | 07/09/2024 | 2 | 0 | 2 | 07/10/2024 | 07/10/2024 | 40 | 25 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 550086 | 02554 | 7.6 | Solar | 05_09_523L1 | 08/29/2023 | 09/06/2023 | 5 | 3 | 2 | 09/07/2023 | 09/07/2023 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 174601 | 01266 | 155 | Solar | 05_05_336W1 | 09/22/2011 | 09/22/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/23/2011 |  | 4/5/2012 | N | EXP | 134 |  |  | 0 | 0 | 0 | 8/9/2012 | 8/9/2012 | 4/5/2012 | Connected |  | N
National Grid | RANDOLPH | 177939 | 02368 | 4536 | Solar | 05_09_909W3 | 06/22/2017 | 06/22/2017 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/29/2017 | 07/19/2017 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 7/2/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 452182 | 02072 | 999 | Solar | 05_05_314W1 | 08/25/2022 | 10/06/2023 | 278 | 268 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2023 | 02/27/2024 | 96 | 80 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 12/11/2026 | N | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WILBRAHAM | 178077 | 01095 | 15.2 | Solar | 05_07_75W5 | 11/03/2017 | 11/03/2017 | 55 | 55 | 0 | 01/29/2018 | 01/29/2018 | 47 | 0 | 47 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2018 |  | 11/27/2020 | N | EXP | 283 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 175536 | 01757 | 1500 | Solar | 05_05_8L2 | 10/02/2014 | 10/02/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2014 | 11/06/2014 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 12/31/2016 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 659599 | 01096 | 12.5 | Solar | 04_04_101L2 | 12/11/2024 | 12/30/2024 | 13 | 10 | 3 | 12/31/2024 | 12/31/2024 | 67 | 45 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2025 |  | 4/16/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/17/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 174895 | 01532 | 3000 | Solar | 05_09_1109W3 | 08/20/2013 | 08/20/2013 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/29/2013 | 10/01/2013 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 3/31/2014 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 546614 | 02322 | 3.8 | Solar | 05_07_97W1 | 08/16/2023 | 08/17/2023 | 1 | 0 | 1 | 08/18/2023 | 08/18/2023 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/12/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 645668 | 02766 | 10 | Solar | 05_07_913W67 | 10/25/2024 | 11/13/2024 | 2 | 0 | 2 | 11/14/2024 | 11/14/2024 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/18/2024 |  | 12/27/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/8/2025 | Connected |  | N
National Grid | NANTUCKET | 584933 | 02554 | 7.6 | Solar | 05_09_523L1 | 01/30/2024 |  | 66 | 65 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 175145 | 01230 | 85 | Solar | 05_05_336W1 | 04/25/2013 | 04/25/2013 | 6 | 0 | 6 | 05/06/2013 | 05/06/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2013 |  | 7/1/2013 | N | EXP | 13 |  |  | 0 | 0 | 0 | 9/13/2013 | 9/13/2013 | 9/20/2013 | Connected |  | N
National Grid | RANDOLPH | 178010 | 02368 | 1000 | Solar | 05_09_909W3 | 04/28/2017 | 04/28/2017 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/07/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 5/6/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 432400 | 02072 | 999 | Solar | 05_05_314W1 | 08/25/2022 | 10/24/2023 | 289 | 279 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/25/2023 | 02/27/2024 | 85 | 65 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/18/2025 |  | 12/10/2026 | N | STD | 28 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | Y
National Grid | WILBRAHAM | 187201 | 01095 | 490 | Solar | 05_07_75W5 | 06/18/2019 | 06/22/2019 | 3 | 0 | 3 | 06/24/2019 | 06/24/2019 | 30 | 26 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2019 |  | 8/11/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 177787 | 01757 | 3.8 | Solar | 05_05_8L2 | 06/01/2017 | 06/01/2017 | 3 | 3 | 0 | 06/07/2017 | 06/07/2017 | 202 | 0 | 202 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2017 |  | 6/7/2018 | N | EXP | 364 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 690788 | 01053 | 17.6 | Solar | 04_04_101L2 | 05/10/2025 | 05/19/2025 | 6 | 2 | 4 | 05/20/2025 | 05/20/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2025 |  | 6/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2025 | Connected |  | N
National Grid | NORTHBOROUGH | 175059 | 01532 | 18.7 | Solar | 05_09_1109W3 | 10/18/2012 | 10/18/2012 | 5 | 0 | 5 | 11/06/2012 | 11/06/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 12/17/2012 | N | EXP | 6 |  |  | 0 | 0 | 0 | 3/27/2014 | 3/27/2014 | 5/1/2013 | Connected |  | N
National Grid | AVON | 548604 | 02322 | 10 | Solar | 05_07_97W1 | 08/23/2023 | 08/29/2023 | 4 | 0 | 4 | 08/30/2023 | 08/30/2023 | 90 | 66 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/17/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTON | 652373 | 02766 | 5.76 | Solar | 05_07_913W67 | 11/14/2024 | 12/17/2024 | 12 | 7 | 5 | 12/18/2024 | 12/18/2024 | 62 | 32 | 30 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/26/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 594318 | 02554 | 10 | Solar | 05_09_523L1 | 03/04/2024 | 08/07/2024 | 108 | 106 | 2 | 08/08/2024 | 08/08/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 8/29/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/26/2024 | Connected |  | N
National Grid | GREAT BARRINGTON | 175407 | 01236 | 170 | Solar | 05_05_336W1 | 03/04/2014 | 03/04/2014 | 6 | 0 | 6 | 03/13/2014 | 03/13/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2014 |  | 9/30/2014 | N | EXP | 182 |  |  | 0 | 0 | 0 | 5/13/2014 | 5/13/2014 | 10/21/2014 | Connected |  | N
National Grid | RANDOLPH | 178009 | 02368 | 3995 | Solar | 05_09_909W3 | 04/28/2017 | 04/28/2017 | 15 | 11 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/22/2017 | 06/07/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/1/2017 | 04/28/2017 | 6/10/2019 | Y | STD |  |  |  | 0 | 0 | 0 |  |  | 5/3/2019 | Connected |  | N
National Grid | STOUGHTON | 749495 | 02072 | 150 | Solar | 05_05_314W1 | 02/17/2026 |  | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | PALMER | 187901 | 01080 | 240 | Solar | 05_07_75W5 | 06/13/2018 | 06/13/2018 | 10 | 7 | 3 | 08/06/2018 | 08/06/2018 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/10/2018 |  | 2/29/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2020 | Connected |  | N
National Grid | MILFORD | 185888 | 01757 | 9.6 | Solar | 05_05_8L2 | 06/08/2018 | 06/08/2018 | 25 | 14 | 11 | 07/18/2018 | 07/18/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/1/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 713236 | 01096 | 18.24 | Solar | 04_04_101L2 | 08/19/2025 | 09/10/2025 | 13 | 8 | 5 | 09/11/2025 | 09/11/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2025 |  | 10/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | WESTBOROUGH | 175099 | 01581 | 16.5 | Solar | 05_09_1109W3 | 10/29/2012 | 10/29/2012 | 0 | 0 | 0 | 11/19/2012 | 11/19/2012 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2013 |  | 1/31/2013 | N | EXP | 15 |  |  | 0 | 0 | 0 | 4/29/2013 | 4/29/2013 | 4/3/2013 | Connected |  | N
National Grid | AVON | 569520 | 02322 | 7.6 | Solar | 05_07_97W1 | 11/21/2023 | 12/12/2023 | 15 | 14 | 1 | 12/13/2023 | 12/13/2023 | 31 | 7 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 1/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/29/2024 | Connected |  | N
National Grid | NORTON | 521849 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 620490 | 02554 | 4.16 | Solar | 05_09_523L1 | 06/25/2024 | 07/02/2024 | 1 | 0 | 1 | 07/03/2024 | 07/03/2024 | 77 | 55 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/14/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 175585 | 01266 | 170 | Solar | 05_05_336W1 | 04/24/2014 | 04/24/2014 | 3 | 0 | 3 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/13/2014 | 04/24/2014 | 10/31/2014 | Y | EXP | 171 |  |  | 0 | 0 | 0 | 5/13/2014 | 5/13/2014 | 2/17/2015 | Connected |  | N
National Grid | RANDOLPH | 178190 | 02368 | 1600 | Solar | 05_09_909W3 | 01/02/2018 | 02/02/2018 | 22 | 12 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/02/2018 | 03/13/2018 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2018 | 01/02/2018 | 3/11/2020 | Y | STD | 484 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 348940 | 02072 | 100 | Solar | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/11/2021 | 05/11/2021 | 40 | 15 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/14/2021 |  | 7/19/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 252794 | 01080 | 7.6 | Solar | 05_07_75W5 | 10/07/2019 | 10/11/2019 | 3 | 0 | 3 | 10/15/2019 | 10/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/22/2019 |  | 10/14/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 204908 | 01757 | 16.4 | Solar | 05_05_8L2 | 12/28/2018 | 02/13/2019 | 31 | 28 | 3 | 02/14/2019 | 02/14/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2019 |  | 2/19/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/12/2019 | Connected |  | N
National Grid | GOSHEN | 744341 | 01032 | 20 | Solar | 04_04_101L3 | 01/13/2026 | 01/15/2026 | 2 | 0 | 2 | 01/16/2026 | 01/16/2026 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 2/18/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 175179 | 01581 | 20 | Solar | 05_09_1109W3 | 05/03/2013 | 05/03/2013 | 7 | 0 | 7 | 05/15/2013 | 05/15/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/1/2013 |  | 5/11/2013 | N | EXP | 51 |  |  | 0 | 0 | 0 | 7/22/2013 | 7/22/2013 | 7/25/2013 | Connected |  | N
National Grid | AVON | 572609 | 02322 | 6 | Solar | 05_07_97W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/26/2024 | 12/07/2023 | 4/3/2025 | Y | EXP | 365 | 04/25/2024 | 06/18/2024 | 55 | 0 | 55 |  |  | 8/5/2024 | Connected |  | N
National Grid | NORTON | 521835 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/23/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 626300 | 02554 | 3.8 | Solar | 05_09_523L1 | 07/19/2024 | 03/10/2025 | 26 | 25 | 1 | 03/11/2025 | 03/11/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/7/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | GREAT BARRINGTON | 175785 | 01230 | 42 | Solar | 05_05_336W1 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 | 07/27/2015 | 07/27/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/30/2015 |  | 8/1/2016 | N | EXP | 368 |  |  | 0 | 0 | 0 | 2/18/2016 | 2/18/2016 | 2/19/2016 | Connected |  | N
National Grid | RANDOLPH | 178376 | 02368 | 4950 | Solar | 05_09_909W3 | 11/21/2017 | 12/20/2017 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2017 | 01/22/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/12/2018 | 11/21/2017 | 9/29/2022 | Y | STD | 171 | 01/27/2021 | 09/22/2022 | 604 | 156 | 448 |  |  | 9/29/2022 | Connected |  | N
National Grid | STOUGHTON | 348897 | 02072 | 150 | Solar | 05_05_314W1 | 03/25/2021 | 04/30/2021 | 25 | 16 | 9 | 05/03/2021 | 05/03/2021 | 46 | 8 | 38 | 07/21/2021 | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 |  | 01/11/2022 | 120 | 7 | 113 |  |  | 0 | 0 | 0 | 1/12/2022 |  | 3/14/2023 | N | EXP | 365 | 01/10/2023 | 01/10/2023 | 1 | 0 | 1 |  |  | 4/5/2023 | Connected |  | N
National Grid | WILBRAHAM | 285958 | 01095 | 249 | Solar | 05_07_75W5 | 04/27/2020 | 05/29/2020 | 23 | 16 | 7 | 06/01/2020 | 06/01/2020 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2020 | 04/27/2020 | 1/29/2026 | Y | EXP | 253 | 12/03/2024 | 12/18/2025 | 381 | 309 | 72 |  |  | 12/26/2025 | Connected |  | N
National Grid | MILFORD | 230608 | 01757 | 17.6 | Solar | 05_05_8L2 | 05/24/2019 | 06/05/2019 | 6 | 0 | 6 | 06/06/2019 | 06/06/2019 | 47 | 26 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/13/2019 | 05/24/2019 | 7/15/2020 | Y | EXP | 365 | 11/07/2019 | 01/22/2020 | 76 | 0 | 76 |  |  | 2/12/2020 | Connected |  | N
National Grid | GOSHEN | 745617 | 01032 | 25 | Solar | 04_04_101L3 | 02/03/2026 | 02/04/2026 | 1 | 0 | 1 | 02/05/2026 | 02/05/2026 | 19 | 3 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | WESTBOROUGH | 175341 | 01581 | 2000 | Solar | 05_09_1109W3 | 06/27/2014 | 06/27/2014 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/07/2014 | 07/09/2014 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2014 | 06/27/2014 | 12/31/2016 | Y | STD | 886 | 01/04/2016 | 05/05/2016 | 84 | 0 | 84 | 5/6/2016 | 5/6/2016 | 5/6/2016 | Connected |  | N
National Grid | AVON | 575266 | 02322 | 3.19 | Solar | 05_07_97W1 | 12/20/2023 | 01/02/2024 | 6 | 1 | 5 | 01/03/2024 | 01/03/2024 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2024 | 12/20/2023 | 2/14/2025 | Y | EXP | 365 | 05/02/2024 | 06/25/2024 | 55 | 0 | 55 |  |  | 7/10/2024 | Connected |  | N
National Grid | NORTON | 521247 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 628030 | 02554 | 30.8 | Solar | 05_09_523L1 | 09/24/2024 | 09/27/2024 | 3 | 0 | 3 | 09/30/2024 | 09/30/2024 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2024 |  | 12/2/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/6/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 175970 | 01230 | 56 | Solar | 05_05_336W1 | 08/11/2015 | 08/11/2015 | 0 | 0 | 0 | 08/12/2015 | 08/12/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2015 | 08/11/2015 | 8/17/2015 | Y | EXP | 8 | 12/16/2015 | 03/11/2016 | 58 | 0 | 58 | 2/9/2016 | 2/9/2016 | 3/28/2016 | Connected |  | N
National Grid | RANDOLPH | 178364 | 02368 | 7.6 | Solar | 05_09_909W3 | 03/30/2018 | 03/30/2018 | 5 | 0 | 5 | 04/09/2018 | 04/09/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2018 |  | 11/15/2019 | N | EXP | 568 |  |  | 0 | 0 | 0 |  |  | 10/8/2019 | Connected |  | N
National Grid | STOUGHTON | 580711 | 02072 | 150 | Solar | 05_05_314W1 | 01/07/2024 | 02/07/2024 | 21 | 11 | 10 |  |  | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 331898 | 01095 | 15.2 | Solar | 05_07_75W5 | 12/15/2020 | 12/16/2020 | 0 | 0 | 0 | 12/17/2020 | 12/17/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/19/2021 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2021 | Connected |  | N
National Grid | MILFORD | 229911 | 01757 | 10 | Solar | 05_05_8L2 | 06/19/2019 | 06/26/2019 | 4 | 0 | 4 | 06/27/2019 | 06/27/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/18/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 568300 | 01039 | 15.95 | Solar | 04_04_101L3 | 11/02/2023 | 11/09/2023 | 5 | 3 | 2 | 11/13/2023 | 11/13/2023 | 34 | 10 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 1/30/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/25/2024 | Connected |  | N
National Grid | WESTBOROUGH | 176066 | 01581 | 499 | Solar | 05_09_1109W3 | 06/18/2015 | 06/18/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2015 | 07/21/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2016 |  | 6/27/2016 | N | STD | 11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 591148 | 02322 | 6 | Solar | 05_07_97W1 | 03/11/2024 | 03/14/2024 | 3 | 0 | 3 | 03/15/2024 | 03/15/2024 | 3 | 1 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2024 | 03/11/2024 | 6/20/2025 | Y | EXP | 365 | 05/09/2024 | 08/08/2024 | 92 | 0 | 92 |  |  | 10/22/2024 | Connected |  | N
National Grid | NORTON | 521153 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 643993 | 02554 | 10 | Solar | 05_09_523L1 | 10/01/2024 | 10/10/2024 | 5 | 3 | 2 | 10/11/2024 | 10/11/2024 | 20 | 3 | 17 | 11/22/2024 | 12/29/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 12/29/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 1/15/2025 |  | 1/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/19/2025 | Connected |  | N
National Grid | STOCKBRIDGE | 178537 | 01266 | 486 | Solar | 05_05_336W1 | 01/25/2018 | 01/25/2018 | 24 | 0 | 24 | 03/05/2018 | 03/05/2018 | 103 | 0 | 103 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 1/31/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 187389 | 02368 | 72 | Solar | 05_09_909W3 | 06/07/2018 | 06/07/2018 | 14 | 4 | 10 | 06/28/2018 | 06/28/2018 | 36 | 0 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2018 |  | 8/19/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/19/2019 | Connected |  | N
National Grid | STOUGHTON | 650009 | 02072 | 0 | Other | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILBRAHAM | 467612 | 01095 | 0 | Other | 05_07_75W5 | 11/15/2022 | 01/23/2023 | 46 | 36 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 01/24/2023 | 02/21/2023 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 297939 | 01757 | 10 | Solar | 05_05_8L2 | 06/23/2020 | 06/29/2020 | 3 | 0 | 3 | 06/30/2020 | 06/30/2020 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2020 |  | 8/1/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/29/2021 | Connected |  | N
National Grid | WILLIAMSBURG | 176375 | 01096 | 284 | Solar | 04_04_101L4 | 05/06/2016 | 05/06/2016 | 1 | 1 | 0 | 05/10/2016 | 05/10/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/13/2016 |  | 5/14/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 9/15/2016 | 9/15/2016 | 12/29/2016 | Connected |  | N
National Grid | WESTBOROUGH | 176065 | 01581 | 499 | Solar | 05_09_1109W3 | 06/18/2015 | 06/18/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/23/2015 | 07/21/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2016 |  | 6/27/2016 | N | STD | 11 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 594854 | 02322 | 5 | Solar | 05_07_97W1 | 03/16/2024 | 03/19/2024 | 2 | 0 | 2 | 03/20/2024 | 03/20/2024 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2024 | 03/16/2024 | 4/8/2025 | Y | EXP | 365 | 04/26/2024 | 05/10/2024 | 15 | 0 | 15 |  |  | 5/14/2024 | Connected |  | N
National Grid | NORTON | 521138 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 666039 | 02554 | 15.2 | Solar | 05_09_523L1 | 01/15/2025 | 01/22/2025 | 6 | 2 | 4 | 06/23/2025 | 06/23/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/22/2025 |  | 7/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/29/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 188185 | 01236 | 249.8 | Solar | 05_05_336W1 | 06/15/2018 | 06/15/2018 | 7 | 0 | 7 | 07/02/2018 | 07/02/2018 | 20 | 19 | 1 | 08/03/2018 | 11/01/2018 | 63 | 43 | 20 |  |  | 0 | 0 | 0 |  | 11/01/2018 | 63 | 43 | 20 |  |  | 0 | 0 | 0 | 11/21/2018 |  | 4/14/2020 | N | EXP | 51 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 189354 | 02368 | 10 | Solar | 05_09_909W3 | 06/29/2018 | 06/29/2018 | 15 | 0 | 15 | 08/23/2018 | 08/23/2018 | 81 | 21 | 60 | 11/19/2018 | 01/18/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 |  | 01/18/2019 | 40 | 0 | 40 |  |  | 0 | 0 | 0 | 12/19/2018 |  | 12/18/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/1/2019 | Connected |  | Y
National Grid | STOUGHTON | 650006 | 02072 | 0 | Other | 05_05_314W2 | 05/02/2025 | 07/11/2025 | 46 | 39 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/14/2025 | 08/27/2025 | 32 | 17 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILBRAHAM | 624944 | 01095 | 7.6 | Solar | 05_07_75W5 | 07/15/2024 | 07/28/2024 | 3 | 0 | 3 | 07/29/2024 | 07/29/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 319548 | 01757 | 499 | Solar | 05_05_8L2 | 10/16/2020 | 12/14/2020 | 39 | 32 | 7 | 12/15/2020 | 12/15/2020 | 88 | 71 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 176861 | 01039 | 27 | Solar | 04_04_101L4 | 01/20/2016 | 01/20/2016 | 1 | 1 | 0 | 01/22/2016 | 01/22/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/4/2016 |  | 1/26/2017 | N | EXP | 357 |  |  | 0 | 0 | 0 | 5/18/2016 | 5/18/2016 | 6/13/2016 | Connected |  | N
National Grid | WESTBOROUGH | 176151 | 01581 | 2000 | Solar | 05_09_1109W3 | 08/26/2015 | 08/26/2015 | 1 | 1 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/01/2015 | 10/06/2015 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 | 08/26/2015 | 11/2/2017 | Y | STD | 64 | 06/20/2017 | 10/31/2017 | 91 | 0 | 91 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | AVON | 598614 | 02322 | 7.6 | Solar | 05_07_97W1 | 03/26/2024 | 03/27/2024 | 1 | 0 | 1 | 03/28/2024 | 03/28/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/6/2024 | Connected |  | N
National Grid | NORTON | 521117 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 670416 | 02554 | 7.6 | Solar | 05_09_523L1 | 02/06/2025 | 02/21/2025 | 5 | 1 | 4 | 02/24/2025 | 02/24/2025 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/28/2025 |  | 4/23/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/28/2025 | Connected |  | N
National Grid | GREAT BARRINGTON | 260025 | 01230 | 250 | Solar | 05_05_336W1 | 02/11/2020 | 11/04/2019 | 12 | 11 | 1 | 11/05/2019 | 11/05/2019 | 81 | 34 | 47 | 03/30/2020 | 08/05/2020 | 91 | 1 | 90 |  |  | 0 | 0 | 0 |  | 08/05/2020 | 91 | 1 | 90 |  |  | 0 | 0 | 0 | 9/2/2020 |  | 9/7/2022 | N | EXP | 365 | 08/24/2021 | 08/23/2021 | 0 | 0 | 0 |  |  | 10/14/2021 | Connected |  | N
National Grid | RANDOLPH | 190337 | 02368 | 3800 | Solar | 05_09_909W3 | 08/16/2018 | 08/27/2018 | 3 | 0 | 3 |  |  | 8 | 8 | 0 |  |  | 0 | 0 | 0 | 08/29/2018 | 09/07/2018 | 7 | 7 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 746953 | 02072 | 3.8 | Solar | 05_05_314W2 | 01/22/2026 | 01/23/2026 | 2 | 0 | 2 | 02/03/2026 | 02/03/2026 | 18 | 4 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/4/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 634969 | 01080 | 7.6 | Solar | 05_07_75W5 | 08/26/2024 | 10/03/2024 | 2 | 0 | 2 | 10/04/2024 | 10/04/2024 | 64 | 28 | 36 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 08/26/2024 | 1/23/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/16/2025 | Connected |  | N
National Grid | MILFORD | 375663 | 01757 | 240 | Solar | 05_05_8L2 | 08/18/2021 | 09/08/2021 | 14 | 3 | 11 |  |  | 59 | 5 | 54 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 08/18/2021 | 2/23/2024 | Y | STD | 532 | 04/14/2023 | 04/20/2023 | 7 | 0 | 7 |  |  | 5/10/2023 | Connected |  | N
National Grid | NORTHAMPTON | 467030 | 01053 | 7.6 | Solar | 04_04_101L4 | 10/20/2022 | 11/10/2022 | 16 | 15 | 1 | 11/14/2022 | 11/14/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2022 |  | 5/24/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/11/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 176519 | 01772 | 1920 | Solar | 05_09_1109W3 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2015 | 11/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/01/2015 | 8/31/2018 | Y | STD | 872 | 08/09/2016 | 01/19/2017 | 164 | 0 | 164 |  |  | 8/6/2018 | Connected |  | N
National Grid | AVON | 608388 | 02322 | 5.76 | Solar | 05_07_97W1 | 05/02/2024 | 05/09/2024 | 2 | 0 | 2 | 05/10/2024 | 05/10/2024 | 23 | 12 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/14/2024 | 05/02/2024 | 7/22/2025 | Y | EXP | 365 | 10/10/2024 | 02/19/2025 | 133 | 0 | 133 |  |  | 2/28/2025 | Connected |  | N
National Grid | NORTON | 521110 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/22/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 687300 | 02554 | 10 | Solar | 05_09_523L1 | 04/24/2025 |  | 61 | 58 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 259098 | 01230 | 233.2 | Solar | 05_05_336W1 | 10/09/2019 | 10/23/2019 | 6 | 3 | 3 | 10/24/2019 | 10/24/2019 | 45 | 20 | 25 | 02/14/2020 | 04/22/2020 | 46 | 13 | 33 |  |  | 0 | 0 | 0 |  | 04/22/2020 | 46 | 13 | 33 |  |  | 0 | 0 | 0 | 6/4/2020 |  | 12/31/2020 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 194600 | 02368 | 4950 | Solar | 05_09_909W3 | 10/11/2018 | 11/01/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/02/2018 | 01/18/2019 | 50 | 32 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 174569 | 02072 | 1000 | Solar | 05_05_314W2 | 04/17/2011 | 04/17/2011 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/10/2012 | 04/17/2011 | 10/31/2012 | Y | STD | 264 | 05/07/2012 | 07/23/2012 | 52 | 0 | 52 | 8/6/2012 | 8/6/2012 | 8/17/2012 | Connected |  | N
National Grid | PALMER | 516245 | 01080 | 75 | Solar | 05_07_75W7 | 04/28/2023 | 01/06/2024 | 172 | 162 | 10 | 01/08/2024 | 01/08/2024 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/6/2025 |  | 7/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 375359 | 01757 | 400 | Solar | 05_05_8L2 | 09/10/2021 | 10/15/2021 | 24 | 16 | 8 |  |  | 54 | 21 | 33 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/8/2022 | 09/10/2021 | 5/3/2024 | Y | STD | 532 | 02/24/2023 | 04/24/2023 | 60 | 0 | 60 |  |  | 4/16/2024 | Connected |  | N
National Grid | WILLIAMSBURG | 618888 | 01039 | 50 | Solar | 04_04_101L4 | 06/19/2024 | 07/31/2024 | 29 | 22 | 7 | 08/01/2024 | 08/01/2024 | 16 | 0 | 16 | 09/17/2024 | 10/22/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  | 10/22/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 | 1/24/2025 | 06/19/2024 | 2/3/2026 | Y | EXP | 28 | 12/17/2025 | 12/16/2025 | 0 | 0 | 0 |  |  | 2/3/2026 | Connected |  | N
National Grid | SOUTHBOROUGH | 176518 | 01772 | 1980 | Solar | 05_09_1109W3 | 10/01/2015 | 10/01/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/06/2015 | 11/03/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/01/2015 | 10/11/2016 | Y | STD | 183 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | AVON | 610295 | 02322 | 3.8 | Solar | 05_07_97W1 | 05/14/2024 | 05/20/2024 | 2 | 0 | 2 | 05/21/2024 | 05/21/2024 | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/10/2024 | 05/14/2024 | 6/17/2025 | Y | EXP | 365 | 09/12/2024 | 10/30/2024 | 49 | 0 | 49 |  |  | 11/8/2024 | Connected |  | N
National Grid | NORTON | 519326 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/25/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 739960 | 02554 | 23 | Solar | 05_09_523L1 | 12/17/2025 | 12/23/2025 | 4 | 1 | 3 | 12/24/2025 | 12/24/2025 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/23/2026 |  | 1/29/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2026 | Connected |  | Y
National Grid | STOCKBRIDGE | 390062 | 01266 | 9.8 | Solar | 05_05_336W1 | 11/11/2021 | 02/02/2022 | 56 | 53 | 3 | 02/03/2022 | 02/03/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/28/2022 | 11/11/2021 | 1/2/2024 | Y | EXP | 365 | 05/25/2022 | 12/21/2022 | 211 | 0 | 211 |  |  | 1/13/2023 | Connected |  | N
National Grid | RANDOLPH | 194591 | 02368 | 4000 | Solar | 05_09_909W3 | 10/09/2018 | 10/17/2018 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/18/2018 | 12/01/2018 | 29 | 10 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 177081 | 02072 | 600 | Solar | 05_05_314W2 | 10/18/2016 | 10/18/2016 | 5 | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/26/2016 | 01/13/2017 | 53 | 46 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2017 | 10/18/2016 | 3/6/2021 | Y | STD | 1355 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILBRAHAM | 515428 | 01095 | 200 | Solar | 05_07_75W7 | 04/03/2023 | 04/20/2023 | 12 | 3 | 9 | 04/21/2023 | 04/21/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2025 |  | 7/3/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 414390 | 01757 | 0 | Other | 05_05_8L2 | 05/09/2022 | 06/21/2022 | 30 | 22 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/22/2022 | 07/20/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 650916 | 01053 | 50 | Solar | 04_04_101L4 | 11/01/2024 | 01/07/2025 | 43 | 33 | 10 | 01/08/2025 | 01/08/2025 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2025 |  | 2/26/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/30/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 176672 | 01772 | 1000 | Solar | 05_09_1109W3 | 10/23/2015 | 10/23/2015 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/30/2015 | 11/30/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/11/2016 | 10/23/2015 | 11/16/2017 | Y | STD | 584 | 02/21/2017 | 10/31/2017 | 174 | 0 | 174 | 11/8/2017 | 11/8/2017 | 11/8/2017 | Connected |  | N
National Grid | AVON | 618593 | 02322 | 10 | Solar | 05_07_97W1 | 06/17/2024 | 07/01/2024 | 6 | 4 | 2 | 07/02/2024 | 07/02/2024 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2024 | 06/17/2024 | 7/31/2025 | Y | EXP | 365 | 09/19/2024 | 09/18/2024 | 0 | 0 | 0 |  |  | 1/31/2025 | Connected |  | N
National Grid | NORTON | 536065 | 02766 | 25 | Solar | 05_07_913W69 | 07/21/2023 | 08/25/2023 | 26 | 16 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/28/2023 | 10/20/2023 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2025 |  | 4/23/2026 | N | STD | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 742265 | 02554 | 13.262 | Solar | 05_09_523L2 | 02/10/2026 | 02/12/2026 | 2 | 0 | 2 | 02/13/2026 | 02/13/2026 | 15 | 7 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | GREAT BARRINGTON | 408869 | 01230 | 0 | Battery Add-On | 05_05_336W1 | 02/11/2022 | 02/18/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/22/2022 | 11/22/2022 | 190 | 183 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 198406 | 02368 | 3400 | Solar | 05_09_909W3 | 11/19/2018 | 12/03/2018 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/04/2018 | 10/08/2019 | 191 | 25 | 166 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 177785 | 02072 | 56 | Solar | 05_05_314W2 | 06/01/2017 | 06/01/2017 | 4 | 3 | 1 | 06/08/2017 | 06/08/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/9/2017 |  | 6/7/2018 | N | EXP | 363 |  |  | 0 | 0 | 0 | 3/22/2018 | 3/22/2018 | 4/2/2018 | Connected |  | N
National Grid | WILBRAHAM | 676560 | 01095 | 11.5 | Solar | 05_07_75W7 | 03/07/2025 | 03/13/2025 | 4 | 0 | 4 | 03/14/2025 | 03/14/2025 | 119 | 96 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/9/2025 | 03/07/2025 | 9/30/2026 | Y | EXP | 365 | 11/18/2025 |  | 109 | 0 | 109 |  |  |  | Construction |  | N
National Grid | MILFORD | 650173 | 01757 | 6.09 | Solar | 05_05_8L2 | 10/28/2024 | 12/09/2024 | 5 | 1 | 4 | 12/10/2024 | 12/10/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/21/2025 | 10/28/2024 | 1/27/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 680837 | 01039 | 4.8 | Solar | 04_04_101L4 | 04/14/2025 | 05/28/2025 | 30 | 27 | 3 | 05/29/2025 | 05/29/2025 | 41 | 18 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/31/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/13/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 178222 | 01772 | 7.6 | Solar | 05_09_1109W3 | 04/13/2018 | 04/13/2018 | 24 | 0 | 24 | 05/18/2018 | 05/18/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/18/2018 |  | 10/21/2019 | N | EXP | 521 |  |  | 0 | 0 | 0 |  |  | 9/11/2019 | Connected |  | N
National Grid | RANDOLPH | 623636 | 02368 | 7.6 | Solar | 05_07_97W1 | 07/09/2024 | 07/10/2024 | 1 | 0 | 1 | 09/23/2024 | 09/23/2024 | 26 | 9 | 17 | 11/20/2024 | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  | 12/05/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 7/10/2024 |  | 12/17/2025 | N | EXP | 365 | 04/24/2025 | 08/07/2025 | 106 | 0 | 106 |  |  | 8/22/2025 | Connected |  | N
National Grid | NORTON | 174674 | 02766 | 170 | Solar | 05_07_913W69 | 06/03/2013 | 06/03/2013 | 9 | 2 | 7 | 06/17/2013 | 06/17/2013 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/22/2013 |  | 5/30/2014 | N | EXP | 312 |  |  | 0 | 0 | 0 | 7/30/2013 | 7/30/2013 | 6/2/2014 | Connected |  | N
National Grid | NANTUCKET | 743707 | 02554 | 5.76 | Solar | 05_09_523L2 | 01/06/2026 | 01/07/2026 | 2 | 0 | 2 | 01/21/2026 | 01/21/2026 | 14 | 1 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2026 |  | 3/3/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | EGREMONT | 571863 | 01252 | 9.86 | Solar | 05_05_336W1 | 12/07/2023 | 12/12/2023 | 3 | 0 | 3 | 12/13/2023 | 12/13/2023 | 28 | 5 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2024 | 12/07/2023 | 3/8/2025 | Y | EXP | 365 | 07/30/2024 | 08/26/2024 | 28 | 0 | 28 |  |  | 9/13/2024 | Connected |  | N
National Grid | RANDOLPH | 198758 | 02368 | 3500 | Solar | 05_09_909W3 | 11/26/2018 | 11/28/2018 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/29/2018 | 02/07/2019 | 52 | 31 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 178034 | 02072 | 92 | Solar | 05_05_314W2 | 10/26/2017 | 10/26/2017 | 5 | 0 | 5 | 11/13/2017 | 11/13/2017 | 98 | 0 | 98 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/15/2017 |  | 11/1/2018 | N | EXP | 351 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILBRAHAM | 704582 | 01095 | 480 | Solar | 05_07_75W7 | 10/02/2025 | 10/31/2025 | 20 | 10 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/03/2025 |  | 83 | 25 | 58 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | MILFORD | 660293 | 01757 | 7.6 | Solar | 05_05_8L2 | 12/12/2024 | 01/08/2025 | 15 | 11 | 4 | 01/09/2025 | 01/09/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/20/2025 | 12/12/2024 | 3/11/2026 | Y | EXP | 365 | 03/14/2025 | 03/13/2025 | 0 | 0 | 0 |  |  | 3/19/2025 | Connected |  | Y
National Grid | WILLIAMSBURG | 177037 | 01039 | 396 | Solar | 04_04_101L5 | 07/26/2016 | 07/26/2016 | 4 | 4 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/02/2016 | 10/10/2016 | 48 | 23 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/25/2017 | 07/26/2016 | 8/1/2017 | Y | STD | 188 | 05/12/2017 | 06/29/2017 | 33 | 0 | 33 | 6/27/2017 | 6/27/2017 | 7/5/2017 | Connected |  | N
National Grid | SOUTHBOROUGH | 178562 | 01772 | 2500 | Solar | 05_09_1109W3 | 04/05/2018 | 04/05/2018 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 07/21/2018 | 64 | 48 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/11/2019 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 633020 | 02072 | 10 | Solar | 05_07_97W1 | 08/15/2024 | 09/03/2024 | 4 | 0 | 4 | 09/04/2024 | 09/04/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/16/2024 | 08/15/2024 | 10/21/2025 | Y | EXP | 365 | 11/16/2024 | 02/04/2025 | 81 | 0 | 81 |  |  | 2/24/2025 | Connected |  | N
National Grid | NORTON | 176150 | 02766 | 100 | Solar | 05_07_913W69 | 08/28/2015 | 08/28/2015 | 0 | 0 | 0 | 08/31/2015 | 08/31/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/1/2015 |  | 9/5/2016 | N | EXP | 37 |  |  | 0 | 0 | 0 | 2/4/2016 | 2/4/2016 | 3/9/2016 | Connected |  | N
National Grid | NANTUCKET | 174902 | 02554 | 1000 | Solar | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 | 02/15/2014 | 03/26/2014 | 25 | 0 | 25 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | GREAT BARRINGTON | 720890 | 01230 | 5.76 | Solar | 05_05_336W1 | 09/25/2025 | 10/06/2025 | 6 | 3 | 3 | 10/07/2025 | 10/07/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/3/2025 |  | 12/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2026 | Connected |  | N
National Grid | RANDOLPH | 227986 | 02368 | 10 | Solar | 05_09_909W3 | 06/27/2019 | 07/08/2019 | 5 | 0 | 5 | 07/09/2019 | 07/09/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/23/2019 | 06/27/2019 | 6/27/2020 | Y | EXP | 365 | 12/06/2019 | 12/20/2019 | 14 | 0 | 14 |  |  | 1/17/2020 | Connected |  | N
National Grid | STOUGHTON | 187658 | 02072 | 100 | Solar | 05_05_314W2 | 06/26/2018 | 06/26/2018 | 0 | 0 | 0 | 07/02/2018 | 07/02/2018 | 153 | 22 | 131 | 08/15/2018 | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  | 10/11/2018 | 40 | 18 | 22 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 176521 | 01007 | 112 | Solar | 05_07_75W7 | 10/05/2015 | 10/05/2015 | 2 | 2 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/12/2015 | 10/05/2015 | 10/12/2016 | Y | EXP | 335 | 03/14/2016 | 04/30/2016 | 33 | 0 | 33 | 5/9/2016 | 5/9/2016 | 5/20/2016 | Connected |  | N
National Grid | MILFORD | 695741 | 01757 | 22.8 | Solar | 05_05_8L2 | 06/17/2025 | 06/30/2025 | 8 | 6 | 2 | 07/01/2025 | 07/01/2025 | 21 | 6 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2025 |  | 8/20/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2025 | Connected |  | N
National Grid | WILLIAMSBURG | 177131 | 01039 |  |  | 04_04_101L5 | 07/26/2016 | 07/26/2016 | 123 | 0 | 123 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/1/2017 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | SOUTHBOROUGH | 178617 | 01772 | 11.4 | Solar | 05_09_1109W3 | 01/31/2018 | 01/31/2018 | 20 | 0 | 20 | 03/07/2018 | 03/07/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/7/2018 |  | 9/16/2020 | N | EXP | 336 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 634838 | 02072 | 10 | Solar | 05_07_97W1 | 08/23/2024 | 09/05/2024 | 2 | 0 | 2 | 09/06/2024 | 09/06/2024 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/17/2024 |  | 10/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/4/2025 | Connected |  | N
National Grid | NORTON | 176571 | 02766 | 300 | Solar | 05_07_913W69 | 02/10/2016 | 02/10/2016 | 1 | 1 | 0 | 02/12/2016 | 02/12/2016 | 180 | 0 | 180 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/16/2017 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 174901 | 02554 | 1000 | Solar | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 |  |  | 0 | 0 | 0 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | GREAT BARRINGTON | 735490 | 01230 | 5.76 | Solar | 05_05_336W2 | 11/21/2025 | 11/24/2025 | 4 | 0 | 4 | 12/30/2025 | 12/30/2025 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 | 11/21/2025 | 1/28/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Construction |  | N
National Grid | RANDOLPH | 271260 | 02368 | 25 | Solar | 05_09_909W3 | 12/31/2019 | 01/29/2020 | 19 | 18 | 1 | 01/30/2020 | 01/30/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/11/2020 |  | 1/4/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/28/2020 | Connected |  | N
National Grid | STOUGHTON | 229154 | 02072 | 7.6 | Solar | 05_05_314W2 | 05/18/2019 | 05/23/2019 | 3 | 0 | 3 | 05/24/2019 | 05/24/2019 | 15 | 9 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/18/2019 |  | 8/30/2019 | N | EXP | 73 |  |  | 0 | 0 | 0 |  |  | 8/12/2019 | Connected |  | N
National Grid | BELCHERTOWN | 177482 | 01007 | 57.6 | Solar | 05_07_75W7 | 09/21/2016 | 09/21/2016 | 4 | 4 | 0 | 09/27/2016 | 09/27/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/19/2016 |  | 9/27/2017 | N | EXP | 343 |  |  | 0 | 0 | 0 | 4/10/2017 | 4/10/2017 | 4/13/2017 | Connected |  | N
National Grid | MILFORD | 715379 | 01757 | 960 | Solar | 05_05_8L3 | 09/22/2025 | 10/06/2025 | 8 | 5 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/07/2025 | 10/27/2025 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | WILLIAMSBURG | 178585 | 01039 | 1000 | Solar | 04_04_101L5 | 01/31/2018 | 01/31/2018 | 17 | 10 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/08/2018 | 03/12/2018 | 3 | 3 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2018 | 01/31/2018 | 12/20/2019 | Y | STD | 387 | 05/22/2019 | 12/03/2019 | 195 | 0 | 195 |  |  | 12/13/2019 | Connected |  | N
National Grid | SOUTHBOROUGH | 178691 | 01772 | 304 | Solar | 05_09_1109W3 | 12/20/2017 | 12/20/2017 | 10 | 0 | 10 | 02/01/2018 | 02/01/2018 | 8 | 0 | 8 | 03/20/2018 | 04/18/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  | 04/18/2018 | 21 | 0 | 21 |  |  | 0 | 0 | 0 | 6/4/2018 |  | 12/26/2018 | N | EXP | 25 |  |  | 0 | 0 | 0 |  |  | 5/31/2019 | Connected |  | N
National Grid | STOUGHTON | 637440 | 02072 | 5.76 | Solar | 05_07_97W1 | 09/03/2024 | 09/27/2024 | 2 | 0 | 2 | 09/30/2024 | 09/30/2024 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/4/2024 | 09/03/2024 | 12/11/2025 | Y | EXP | 365 | 06/12/2025 | 12/08/2025 | 180 | 0 | 180 |  |  | 12/11/2025 | Connected |  | N
National Grid | NORTON | 177261 | 02766 | 448 | Solar | 05_07_913W69 | 08/18/2016 | 08/18/2016 | 26 | 7 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 09/27/2016 | 11/28/2016 | 41 | 38 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/6/2017 |  | 7/1/2018 | N | STD | 36 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 174900 | 02554 | 1000 | Solar | 05_09_523L2 | 10/25/2011 | 10/25/2011 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/22/2011 | 02/26/2012 | 63 | 0 | 63 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/24/2012 | 10/25/2011 | 11/30/2012 | Y | STD | 98 |  |  | 0 | 0 | 0 | 3/25/2014 | 3/25/2014 | 4/25/2014 | Connected |  | N
National Grid | GREAT BARRINGTON | 749467 | 01230 | 240 | Solar | 05_05_336W2 | 02/17/2026 |  | 13 | 3 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Application |  | N
National Grid | RANDOLPH | 288067 | 02368 | 4950 | Other | 05_09_909W3 | 05/15/2020 | 05/29/2020 | 8 | 0 | 8 |  |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 06/01/2020 | 07/30/2020 | 43 | 25 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 342097 | 02072 | 3.84 | Solar | 05_05_314W2 | 02/12/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 178042 | 01069 | 960 | Solar | 05_07_75W7 | 05/01/2017 | 05/01/2017 | 15 | 13 | 2 |  |  | 0 | 0 | 0 | 07/12/2017 | 07/27/2017 | 11 | 0 | 11 | 05/22/2017 | 06/16/2017 | 18 | 4 | 14 |  | 07/27/2017 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 10/27/2017 | 05/01/2017 | 7/31/2020 | Y | STD | 761 | 08/20/2019 | 06/03/2020 | 286 | 0 | 286 | 6/4/2020 | 7/27/2020 | 8/4/2020 | Connected |  | N
National Grid | MILFORD | 734928 | 01757 | 480 | Solar | 05_05_8L3 | 11/21/2025 | 12/18/2025 | 16 | 6 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/19/2025 | 02/12/2026 | 37 | 21 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Group Study |  | N
National Grid | NORTHAMPTON | 203329 | 01053 | 10 | Solar | 04_04_101L5 | 01/04/2019 | 01/15/2019 | 6 | 0 | 6 | 01/16/2019 | 01/16/2019 | 23 | 10 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 197783 | 01772 | 240 | Solar | 05_09_1109W3 | 10/05/2018 | 11/05/2018 | 189 | 21 | 168 |  |  | 23 | 10 | 13 |  |  | 0 | 0 | 0 | 11/05/2018 | 01/05/2019 | 40 | 21 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 638291 | 02072 | 5.76 | Solar | 05_07_97W1 | 09/06/2024 | 10/28/2024 | 27 | 25 | 2 | 10/29/2024 | 10/29/2024 | 18 | 0 | 18 | 12/12/2024 | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 |  | 03/05/2025 | 56 | 0 | 56 |  |  | 0 | 0 | 0 | 9/16/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTON | 177260 | 02766 | 180 | Solar | 05_07_913W69 | 08/18/2016 | 08/18/2016 | 6 | 6 | 0 | 08/29/2016 | 08/29/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/26/2016 | 08/18/2016 | 8/24/2017 | Y | EXP | 332 | 07/18/2017 | 08/03/2017 | 12 | 0 | 12 | 9/25/2017 | 9/25/2017 | 9/25/2017 | Connected |  | N
National Grid | NANTUCKET | 175923 | 02554 | 2000 | Solar | 05_09_523L2 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2015 | 06/29/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/23/2016 | 04/04/2016 | 28 | 0 | 28 | 4/4/2016 | 05/29/2015 | 3/31/2018 | Y | STD | 726 | 09/26/2017 | 02/05/2018 | 83 | 0 | 83 | 3/30/2018 | 3/30/2018 | 3/30/2018 | Connected |  | N
National Grid | GREAT BARRINGTON | 174788 | 01230 | 26.5 | Solar | 05_05_336W2 | 06/09/2011 | 06/09/2011 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2011 | 06/09/2011 | 1/23/2012 | Y | EXP | 18 | 12/29/2011 | 01/18/2012 | 12 | 0 | 12 | 8/7/2012 | 8/7/2012 | 1/23/2012 | Connected |  | N
National Grid | RANDOLPH | 332573 | 02368 | 3.48 | Solar | 05_09_909W3 | 01/11/2021 | 01/15/2021 | 3 | 0 | 3 | 01/19/2021 | 01/19/2021 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/17/2021 | 01/11/2021 |  | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/7/2021 | Connected |  | N
National Grid | STOUGHTON | 366728 | 02072 | 7.6 | Solar | 05_05_314W2 | 06/29/2021 | 08/26/2021 | 41 | 38 | 3 | 08/27/2021 | 08/27/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/1/2021 | 06/29/2021 | 12/2/2023 | Y | EXP | 365 | 01/06/2022 | 10/31/2022 | 299 | 0 | 299 |  |  | 1/25/2023 | Connected |  | N
National Grid | PALMER | 194829 | 01069 | 600 | Solar | 05_07_75W7 | 09/19/2018 | 10/01/2018 | 5 | 2 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/02/2018 | 11/06/2018 | 59 | 7 | 52 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 743045 | 01757 | 17.1 | Solar | 05_05_8L3 | 01/02/2026 | 01/07/2026 | 3 | 0 | 3 | 01/08/2026 | 01/08/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/27/2026 |  | 1/30/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | GOSHEN | 560671 | 01096 | 20.88 | Solar | 04_04_101L5 | 10/04/2023 | 10/12/2023 | 6 | 4 | 2 | 10/13/2023 | 10/13/2023 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/20/2023 |  | 11/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 199441 | 01772 | 10 | Solar | 05_09_1109W3 | 11/08/2018 | 11/27/2018 | 8 | 3 | 5 | 11/28/2018 | 11/28/2018 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/21/2018 |  | 12/20/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 639754 | 02072 | 5.76 | Solar | 05_07_97W1 | 09/12/2024 | 10/04/2024 | 1 | 0 | 1 | 10/07/2024 | 10/07/2024 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 178329 | 02703 | 249 | Solar | 05_07_913W69 | 03/30/2018 | 03/30/2018 | 19 | 0 | 19 | 04/27/2018 | 04/27/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 4/4/2019 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 175922 | 02554 | 2000 | Solar | 05_09_523L2 | 05/29/2015 | 05/29/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/01/2015 | 06/29/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 | 02/23/2016 | 04/04/2016 | 28 | 0 | 28 | 4/4/2016 | 05/29/2015 | 3/31/2018 | Y | STD | 726 | 09/26/2017 | 02/05/2018 | 83 | 0 | 83 | 2/13/2018 | 2/13/2018 | 3/30/2018 | Connected |  | N
National Grid | GREAT BARRINGTON | 412214 | 01230 | 0 | Battery Add-On | 05_05_336W2 | 03/04/2022 | 03/18/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/21/2022 | 04/08/2022 | 15 | 1 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 345682 | 02368 | 49.08 | Solar | 05_09_909W3 | 03/08/2021 | 03/15/2021 | 4 | 0 | 4 |  |  | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/14/2022 |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOUGHTON | 375524 | 02072 | 7.6 | Solar | 05_05_314W2 | 08/12/2021 | 09/02/2021 | 16 | 15 | 1 | 09/03/2021 | 09/03/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/12/2021 |  | 11/7/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/9/2022 | Connected |  | N
National Grid | PALMER | 362507 | 01069 | 900 | Solar | 05_07_75W7 | 09/23/2021 | 01/31/2022 | 88 | 78 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/01/2022 | 02/25/2022 | 17 | 1 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 175284 | 01757 | 30.96 | Solar | 05_05_8L3 | 09/02/2014 | 09/02/2014 | 4 | 0 | 4 | 09/09/2014 | 09/09/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/22/2014 |  | 11/28/2014 | N | EXP | 67 |  |  | 0 | 0 | 0 | 9/22/2014 | 9/22/2014 | 8/20/2015 | Connected |  | N
National Grid | NORTHAMPTON | 585339 | 01053 | 7.6 | Solar | 04_04_101L5 | 02/06/2024 | 02/09/2024 | 3 | 0 | 3 | 02/12/2024 | 02/12/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/26/2024 |  | 3/24/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 213059 | 01772 | 10 | Solar | 05_09_1109W3 | 04/01/2019 | 04/03/2019 | 2 | 2 | 0 | 04/04/2019 | 04/04/2019 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/9/2019 | 04/01/2019 | 11/5/2019 | Y | EXP | 21 | 05/22/2019 | 06/25/2019 | 34 | 0 | 34 |  |  | 8/10/2019 | Connected |  | N
National Grid | STOUGHTON | 643312 | 02072 | 3.8 | Solar | 05_07_97W1 | 09/27/2024 | 10/24/2024 | 3 | 0 | 3 | 10/25/2024 | 10/25/2024 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/27/2024 | 09/27/2024 | 12/24/2025 | Y | EXP | 365 | 04/03/2025 | 06/02/2025 | 61 | 0 | 61 |  |  | 6/19/2025 | Connected |  | N
National Grid | ATTLEBORO | 178612 | 02703 | 166.5 | Solar | 05_07_913W69 | 12/14/2017 | 12/14/2017 | 31 | 11 | 20 | 01/31/2018 | 01/31/2018 | 45 | 0 | 45 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/31/2018 |  | 12/19/2018 | N | EXP | 322 |  |  | 0 | 0 | 0 |  |  | 12/6/2018 | Connected |  | N
National Grid | NANTUCKET | 176072 | 02554 | 11.4 | Solar | 05_09_523L2 | 06/19/2015 | 06/19/2015 | 5 | 5 | 0 | 06/30/2015 | 06/30/2015 | 119 | 0 | 119 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 6/28/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 529975 | 01230 | 950 | Solar | 05_05_336W2 | 01/29/2024 | 05/16/2024 | 76 | 66 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/17/2024 | 05/29/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 357554 | 02368 | 8.99 | Solar | 05_09_909W3 | 05/11/2021 | 05/17/2021 | 4 | 4 | 0 | 05/18/2021 | 05/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/25/2021 |  | 5/17/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/10/2021 | Connected |  | N
National Grid | STOUGHTON | 375292 | 02072 | 15.2 | Solar | 05_05_314W2 | 08/11/2021 | 12/27/2021 | 12 | 8 | 4 | 08/30/2021 | 08/30/2021 | 32 | 7 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/10/2021 |  | 1/5/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/6/2022 | Connected |  | N
National Grid | BELCHERTOWN | 367269 | 01007 | 7.6 | Solar | 05_07_75W7 | 07/15/2021 | 07/30/2021 | 12 | 11 | 1 | 08/02/2021 | 08/02/2021 | 24 | 3 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/3/2021 |  | 10/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/3/2022 | Connected |  | N
National Grid | MILFORD | 175623 | 01757 | 996 | Solar | 05_05_8L3 | 05/05/2014 | 05/05/2014 | 7 | 0 | 7 | 05/15/2014 | 05/15/2014 | 0 | 0 | 0 | 07/30/2014 | 09/03/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 09/03/2014 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 1/28/2015 | 05/05/2014 | 12/31/2016 | Y | EXP | 73 | 09/17/2015 | 12/18/2015 | 63 | 0 | 63 | 12/21/2015 | 12/21/2015 | 12/21/2015 | Connected |  | N
National Grid | WILLIAMSBURG | 744620 | 01096 | 20 | Solar | 04_04_101L6 | 01/13/2026 | 01/29/2026 | 2 | 0 | 2 | 01/30/2026 | 01/30/2026 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 3/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | SOUTHBOROUGH | 218174 | 01772 | 15.37 | Solar | 05_09_1109W3 | 04/10/2019 | 04/12/2019 | 2 | 2 | 0 | 04/15/2019 | 04/15/2019 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/17/2019 |  | 7/30/2019 | N | EXP | 14 |  |  | 0 | 0 | 0 |  |  | 6/24/2019 | Connected |  | N
National Grid | STOUGHTON | 655942 | 02072 | 7.6 | Solar | 05_07_97W1 | 11/21/2024 | 12/16/2024 | 6 | 0 | 6 | 12/17/2024 | 12/17/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2025 |  | 2/12/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/21/2025 | Connected |  | N
National Grid | NORTON | 199038 | 02766 | 72 | Solar | 05_07_913W69 | 02/01/2019 | 03/15/2019 | 28 | 20 | 8 | 03/18/2019 | 03/18/2019 | 26 | 14 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/29/2019 |  | 7/31/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/30/2020 | Connected |  | N
National Grid | NANTUCKET | 176501 | 02554 | 10 | Solar | 05_09_523L2 | 02/09/2016 | 02/09/2016 | 18 | 18 | 0 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/25/2016 |  | 2/15/2017 | N | EXP | 296 |  |  | 0 | 0 | 0 | 4/25/2016 | 4/25/2016 | 9/28/2016 | Connected |  | N
National Grid | STOCKBRIDGE | 529971 | 01266 | 950 | Solar | 05_05_336W2 | 09/21/2023 | 03/14/2024 | 119 | 109 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/15/2024 | 05/29/2024 | 52 | 41 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2025 | 09/21/2023 | 1/6/2026 | Y | STD | 343 | 09/25/2025 | 12/19/2025 | 86 | 14 | 72 |  |  | 12/31/2025 | Connected |  | N
National Grid | RANDOLPH | 426237 | 02368 | 7.6 | Solar | 05_09_909W3 | 04/28/2022 | 04/29/2022 | 1 | 0 | 1 | 05/02/2022 | 05/02/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/27/2022 | 04/28/2022 | 8/11/2023 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2022 | Connected |  | Y
National Grid | STOUGHTON | 375895 | 02072 | 9.6 | Solar | 05_05_314W2 | 08/13/2021 | 09/15/2021 | 22 | 21 | 1 | 09/16/2021 | 09/16/2021 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/6/2021 | 08/13/2021 | 5/7/2023 | Y | EXP | 365 | 04/07/2022 | 04/27/2022 | 21 | 0 | 21 |  |  | 5/27/2022 | Connected |  | N
National Grid | BELCHERTOWN | 430213 | 01007 | 3.8 | Solar | 05_07_75W7 | 05/25/2022 | 05/26/2022 | 1 | 0 | 1 | 05/27/2022 | 05/27/2022 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 | 05/25/2022 | 6/7/2024 | Y | EXP | 365 | 12/01/2022 | 06/08/2023 | 190 | 0 | 190 |  |  | 6/14/2023 | Connected |  | N
National Grid | MILFORD | 176343 | 01757 | 1000 | Solar | 05_05_8L3 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2015 | 03/30/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 174904 | 01039 | 900 | Wind | 04_04_101L6 | 10/07/2011 | 10/07/2011 | 594 | 389 | 205 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 11/30/2012 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | SOUTHBOROUGH | 222580 | 01772 | 0 | Solar | 05_09_1109W3 | 04/25/2019 | 05/06/2019 | 6 | 0 | 6 | 05/07/2019 | 05/07/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/29/2019 | 04/25/2019 | 3/10/2020 | Y | EXP | 365 | 11/19/2019 | 11/18/2019 | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | STOUGHTON | 657156 | 02072 | 7.6 | Solar | 05_07_97W1 | 11/26/2024 | 12/24/2024 | 4 | 0 | 4 | 12/26/2024 | 12/26/2024 | 47 | 25 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2025 | 11/26/2024 | 3/24/2026 | Y | EXP | 365 | 05/14/2025 | 11/07/2025 | 178 | 0 | 178 |  |  | 12/3/2025 | Connected |  | N
National Grid | ATTLEBORO | 202031 | 02703 | 100 | Solar | 05_07_913W69 | 11/26/2018 | 12/05/2018 | 7 | 2 | 5 | 12/06/2018 | 12/06/2018 | 20 | 7 | 13 | 02/15/2019 | 03/25/2019 | 25 | 6 | 19 |  |  | 0 | 0 | 0 |  | 03/25/2019 | 25 | 6 | 19 |  |  | 0 | 0 | 0 | 4/19/2019 | 11/26/2018 | 10/30/2020 | Y | EXP | 332 |  |  | 0 | 0 | 0 |  |  | 10/26/2020 | Connected |  | N
National Grid | NANTUCKET | 176515 | 02554 | 5 | Solar | 05_09_523L2 | 10/01/2015 | 10/01/2015 | 1 | 1 | 0 | 10/06/2015 | 10/06/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 | 10/01/2015 | 10/10/2016 | Y | EXP | 353 | 08/12/2016 | 09/13/2016 | 21 | 0 | 21 | 10/23/2015 | 10/23/2015 | 10/11/2016 | Connected |  | N
National Grid | EGREMONT | 581882 | 01252 | 240 | Solar | 05_05_336W2 | 01/19/2024 | 02/08/2024 | 13 | 3 | 10 |  |  | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 428923 | 02368 | 23 | Solar | 05_09_909W3 | 05/09/2022 | 05/19/2022 | 2 | 1 | 1 | 06/12/2024 | 06/12/2024 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/19/2022 |  | 7/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2024 | Connected |  | N
National Grid | STOUGHTON | 420913 | 02072 | 15.2 | Solar | 05_05_314W2 | 06/17/2022 | 06/22/2022 | 2 | 0 | 2 | 06/23/2022 | 06/23/2022 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/27/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 480025 | 01007 | 86 | Solar | 05_07_75W7 | 11/30/2022 | 12/29/2022 | 20 | 10 | 10 |  |  | 25 | 1 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | MILFORD | 176342 | 01757 | 2000 | Solar | 05_05_8L3 | 02/20/2015 | 02/20/2015 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/04/2015 | 03/30/2015 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NORTHAMPTON | 350253 | 01060 | 7.6 | Solar | 04_04_101L6 | 04/05/2021 | 04/06/2021 | 1 | 1 | 0 | 04/07/2021 | 04/07/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/14/2021 |  | 4/5/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/30/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 265046 | 01772 | 10 | Solar | 05_09_1109W3 | 11/12/2019 | 11/26/2019 | 9 | 6 | 3 | 11/27/2019 | 11/27/2019 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 |  | 11/12/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/9/2020 | Connected |  | N
National Grid | STOUGHTON | 666717 | 02072 | 3.8 | Solar | 05_07_97W1 | 01/20/2025 | 02/10/2025 | 16 | 12 | 4 | 02/11/2025 | 02/11/2025 | 52 | 32 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/30/2025 |  | 5/6/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/22/2025 | Connected |  | N
National Grid | ATTLEBORO | 207895 | 02703 | 480 | Solar | 05_07_913W69 | 02/07/2019 | 02/25/2019 | 10 | 1 | 9 | 02/26/2019 | 02/26/2019 | 51 | 29 | 22 | 05/10/2019 | 06/25/2019 | 32 | 3 | 29 |  |  | 0 | 0 | 0 |  | 06/25/2019 | 32 | 3 | 29 |  |  | 0 | 0 | 0 | 6/26/2019 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 176837 | 02554 | 10 | Solar | 05_09_523L2 | 02/29/2016 | 02/29/2016 | 2 | 2 | 0 | 03/03/2016 | 03/03/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2016 |  | 3/6/2017 | N | EXP | 328 |  |  | 0 | 0 | 0 | 4/12/2016 | 4/12/2016 | 7/18/2016 | Connected |  | N
National Grid | STOCKBRIDGE | 739626 | 01266 | 17.6 | Solar | 05_05_336W3 | 12/11/2025 | 12/16/2025 | 3 | 0 | 3 | 12/17/2025 | 12/17/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/12/2026 |  | 1/13/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 435182 | 02368 | 15.2 | Solar | 05_09_909W3 | 06/09/2022 | 06/14/2022 | 3 | 0 | 3 | 06/15/2022 | 06/15/2022 | 26 | 1 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/26/2022 |  | 7/30/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/13/2023 | Connected |  | Y
National Grid | STOUGHTON | 430664 | 02072 | 5.04 | Solar | 05_05_314W2 | 06/03/2022 | 06/06/2022 | 1 | 0 | 1 | 06/07/2022 | 06/07/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/28/2022 | 06/03/2022 | 12/12/2023 | Y | EXP | 365 | 12/13/2022 | 01/03/2023 | 22 | 0 | 22 |  |  | 1/5/2023 | Connected |  | N
National Grid | BELCHERTOWN | 500180 | 01007 | 120 | Solar | 05_07_75W7 | 02/13/2023 | 02/22/2023 | 6 | 0 | 6 | 02/23/2023 | 02/23/2023 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2025 |  | 4/15/2026 | N | EXP | 119 |  |  | 0 | 0 | 0 |  |  | 12/31/2025 | Connected |  | N
National Grid | MILFORD | 176408 | 01757 | 8.25 | Solar | 05_05_8L3 | 05/09/2016 | 05/09/2016 | 3 | 3 | 0 | 05/16/2016 | 05/16/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/6/2016 | 05/09/2016 | 5/16/2017 | Y | EXP | 344 | 08/04/2016 | 08/20/2016 | 12 | 0 | 12 | 10/11/2016 | 10/11/2016 | 10/11/2016 | Connected |  | N
National Grid | NORTHAMPTON | 360480 | 01053 | 7.6 | Solar | 04_04_101L6 | 05/27/2021 | 06/01/2021 | 1 | 0 | 1 | 06/02/2021 | 06/02/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2021 |  | 7/13/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/20/2021 | Connected |  | N
National Grid | SOUTHBOROUGH | 265790 | 01772 | 9.8 | Solar | 05_09_1109W3 | 11/25/2019 | 12/03/2019 | 4 | 0 | 4 | 12/04/2019 | 12/04/2019 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/10/2020 | 11/25/2019 | 11/25/2020 | Y | EXP | 365 | 05/01/2020 | 06/26/2020 | 56 | 0 | 56 |  |  | 7/2/2020 | Connected |  | N
National Grid | STOUGHTON | 684485 | 02072 | 7.6 | Solar | 05_07_97W1 | 04/11/2025 | 04/25/2025 | 9 | 6 | 3 | 04/28/2025 | 04/28/2025 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/22/2025 |  | 8/5/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/3/2025 | Connected |  | N
National Grid | ATTLEBORO | 213840 | 02703 | 250 | Solar | 05_07_913W69 | 04/08/2019 | 04/17/2019 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/18/2019 | 05/10/2019 | 17 | 3 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 176923 | 02554 | 10.32 | Solar | 05_09_523L2 | 11/18/2015 | 11/18/2015 | 3 | 3 | 0 | 11/24/2015 | 11/24/2015 | 65 | 0 | 65 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/14/2015 |  | 11/24/2016 | N | EXP | 346 |  |  | 0 | 0 | 0 | 12/14/2015 | 12/14/2015 |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 741975 | 01230 | 9.56 | Solar | 05_05_336W3 | 12/23/2025 | 12/29/2025 | 2 | 0 | 2 | 01/15/2026 | 01/15/2026 | 20 | 8 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/19/2026 |  | 3/5/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | RANDOLPH | 485087 | 02368 | 6 | Solar | 05_09_909W3 | 02/08/2023 | 02/09/2023 | 1 | 0 | 1 | 02/10/2023 | 02/10/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/22/2023 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 643694 | 02072 | 19 | Solar | 05_05_314W2 | 09/30/2024 | 10/22/2024 | 16 | 14 | 2 | 10/23/2024 | 10/23/2024 | 24 | 5 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/4/2024 |  | 12/9/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BELCHERTOWN | 516478 | 01007 | 150 | Solar | 05_07_75W7 | 04/07/2023 | 04/21/2023 | 9 | 0 | 9 |  |  | 23 | 2 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 178027 | 01757 | 57.6 | Solar | 05_05_8L3 | 08/31/2017 | 08/31/2017 | 29 | 28 | 1 | 10/16/2017 | 10/16/2017 | 112 | 0 | 112 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/16/2017 |  | 11/30/2018 | N | EXP | 41 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | WILLIAMSBURG | 398235 | 01039 | 20 | Solar | 04_04_101L6 | 11/30/2021 | 01/04/2022 | 7 | 6 | 1 | 12/10/2021 | 12/10/2021 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/4/2022 |  | 3/10/2024 | N | EXP | 77 |  |  | 0 | 0 | 0 |  |  | 4/12/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 288929 | 01772 | 1000 | Solar | 05_09_1109W3 | 06/26/2020 | 07/15/2020 | 13 | 8 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 07/16/2020 | 08/08/2020 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 684712 | 02368 | 11.5 | Solar | 05_07_97W1 | 04/18/2025 | 05/06/2025 | 15 | 10 | 5 | 05/07/2025 | 05/07/2025 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/4/2025 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 239659 | 02703 | 250 | Solar | 05_07_913W69 | 06/21/2019 | 06/29/2019 | 5 | 0 | 5 | 07/01/2019 | 07/01/2019 | 16 | 3 | 13 | 08/01/2019 | 11/25/2019 | 80 | 42 | 38 |  |  | 0 | 0 | 0 |  | 11/25/2019 | 80 | 42 | 38 |  |  | 0 | 0 | 0 | 1/6/2020 | 06/21/2019 | 1/6/2023 | Y | EXP | 662 | 02/04/2021 | 11/03/2022 | 638 | 544 | 94 |  |  | 12/5/2022 | Connected |  | N
National Grid | NANTUCKET | 177944 | 02554 | 432.9 | Solar | 05_09_523L2 | 08/18/2017 | 10/06/2017 | 10 | 0 | 10 | 09/05/2017 | 09/05/2017 | 26 | 0 | 26 | 01/03/2018 | 01/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  | 01/19/2018 | 11 | 0 | 11 |  |  | 0 | 0 | 0 | 4/6/2018 | 08/18/2017 | 1/31/2020 | Y | EXP | 56 |  |  | 0 | 0 | 0 |  |  | 1/15/2020 | Connected |  | N
National Grid | EGREMONT | 753274 | 01252 | 11.5 | Solar | 05_05_336W3 | 02/26/2026 | 03/03/2026 | 2 | 0 | 2 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | RANDOLPH | 520969 | 02368 | 6 | Solar | 05_09_909W3 | 06/02/2023 | 06/05/2023 | 1 | 0 | 1 | 06/06/2023 | 06/06/2023 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2023 |  | 7/23/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 674379 | 02072 | 15.356 | Solar | 05_05_314W2 | 03/11/2025 | 03/17/2025 | 4 | 0 | 4 | 03/18/2025 | 03/18/2025 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/21/2025 |  | 5/1/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/14/2025 | Connected |  | N
National Grid | BELCHERTOWN | 661275 | 01007 | 10 | Solar | 05_07_75W7 | 12/17/2024 | 01/10/2025 | 5 | 0 | 5 | 01/13/2025 | 01/13/2025 | 27 | 2 | 25 | 03/03/2025 | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 02/28/2025 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/5/2025 | 12/17/2024 | 3/19/2026 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/18/2025 | Connected |  | N
National Grid | MILFORD | 188158 | 01757 | 4482 | Solar | 05_05_8L3 | 06/29/2018 | 07/19/2018 | 12 | 0 | 12 |  |  | 49 | 26 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/30/2020 | 06/29/2018 | 11/8/2024 | Y | STD | 147 | 09/17/2022 | 06/20/2023 | 277 | 268 | 9 |  |  | 10/25/2024 | Connected |  | N
National Grid | GOSHEN | 490698 | 01032 | 19 | Solar | 04_04_101L6 | 02/09/2023 | 02/13/2023 | 3 | 1 | 2 | 02/14/2023 | 02/14/2023 | 22 | 0 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/17/2023 |  | 4/7/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/13/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 305086 | 01772 | 0 | Solar | 05_09_1109W3 | 08/05/2020 | 08/17/2020 | 8 | 8 | 0 | 08/18/2020 | 08/18/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2020 | 08/05/2020 | 8/16/2021 | Y | EXP | 365 | 12/30/2020 | 01/25/2021 | 26 | 0 | 26 |  |  | 7/15/2021 | Connected |  | N
National Grid | RANDOLPH | 727914 | 02368 | 13.36 | Solar | 05_07_97W2 | 10/21/2025 | 10/25/2025 | 18 | 18 | 0 | 01/22/2026 | 01/22/2026 | 31 | 19 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 316717 | 02766 | 12 | Solar | 05_07_913W69 | 10/02/2020 | 10/09/2020 | 5 | 4 | 1 | 10/13/2020 | 10/13/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/17/2020 | 10/02/2020 | 1/24/2022 | Y | EXP | 365 | 12/13/2020 | 12/30/2020 | 17 | 0 | 17 |  |  | 9/15/2021 | Connected |  | N
National Grid | NANTUCKET | 178173 | 02554 | 3190 | Solar | 05_09_523L2 | 03/23/2018 | 04/06/2018 | 9 | 9 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/06/2018 | 04/28/2018 | 10 | 0 | 10 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 175844 | 01230 | 17.6 | Solar | 05_05_336W3 | 05/19/2015 | 05/19/2015 | 0 | 0 | 0 | 05/22/2015 | 05/22/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/28/2015 |  | 10/30/2015 | N | EXP | 155 |  |  | 0 | 0 | 0 | 7/20/2015 | 7/20/2015 | 3/28/2016 | Connected |  | N
National Grid | RANDOLPH | 531637 | 02368 | 15.2 | Solar | 05_09_909W3 | 06/06/2023 | 06/12/2023 | 5 | 4 | 1 | 06/13/2023 | 06/13/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/17/2023 |  | 8/5/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/1/2023 | Connected |  | N
National Grid | STOUGHTON | 683056 | 02072 | 15.2 | Solar | 05_05_314W2 | 04/07/2025 | 04/10/2025 | 3 | 0 | 3 | 04/11/2025 | 04/11/2025 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2025 |  | 5/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/16/2025 | Connected |  | N
National Grid | BELCHERTOWN | 340182 | 01007 | 100 | Solar | 05_07_797W1 | 02/04/2021 | 02/17/2021 | 7 | 0 | 7 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/6/2021 |  | 10/18/2026 | N | EXP | 586 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | MILFORD | 204801 | 01757 | 20 | Solar | 05_05_8L3 | 12/27/2018 | 01/10/2019 | 8 | 3 | 5 | 01/11/2019 | 01/11/2019 | 6 | 4 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/5/2019 |  | 2/4/2020 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/28/2019 | Connected |  | N
National Grid | WILLIAMSBURG | 572025 | 01096 | 22.8 | Solar | 04_04_101L6 | 11/17/2023 | 11/20/2023 | 1 | 0 | 1 | 11/21/2023 | 11/21/2023 | 25 | 3 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/5/2024 |  | 2/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/11/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 305047 | 01772 | 0 | Solar | 05_09_1109W3 | 08/05/2020 | 08/17/2020 | 8 | 8 | 0 | 08/18/2020 | 08/18/2020 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/28/2020 |  | 8/16/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/12/2020 | Connected |  | N
National Grid | RANDOLPH | 727611 | 02368 | 15.2 | Solar | 05_07_97W2 | 10/20/2025 | 10/24/2025 | 4 | 0 | 4 | 10/27/2025 | 10/27/2025 | 40 | 24 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2025 |  | 1/2/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 322406 | 02703 | 7.6 | Solar | 05_07_913W69 | 11/30/2020 | 12/03/2020 | 2 | 0 | 2 | 12/04/2020 | 12/04/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 6/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 178640 | 02554 | 1000 | Solar | 05_09_523L2 | 04/09/2018 | 04/16/2018 | 4 | 3 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/16/2018 | 06/14/2018 | 43 | 27 | 16 |  |  | 0 | 0 | 0 | 07/10/2020 | 10/02/2020 | 60 | 3 | 57 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | STOCKBRIDGE | 176070 | 01266 | 3.8 | Solar | 05_05_336W3 | 06/19/2015 | 06/19/2015 | 6 | 6 | 0 | 06/30/2015 | 06/30/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/2/2015 |  | 6/27/2016 | N | EXP | 361 |  |  | 0 | 0 | 0 | 8/4/2015 | 8/4/2015 | 3/22/2016 | Connected |  | N
National Grid | RANDOLPH | 532258 | 02368 | 10 | Solar | 05_09_909W3 | 06/07/2023 | 06/22/2023 | 10 | 0 | 10 | 06/23/2023 | 06/23/2023 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/20/2023 |  | 7/26/2024 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/1/2023 | Connected |  | N
National Grid | STOUGHTON | 741732 | 02072 | 7.6 | Solar | 05_05_314W3 | 12/22/2025 | 01/02/2026 | 7 | 6 | 1 | 01/05/2026 | 01/05/2026 | 32 | 18 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | PALMER | 729872 | 01069 | 7.6 | Solar | 05_07_797W1 | 10/29/2025 | 12/01/2025 | 1 | 0 | 1 | 01/06/2026 | 01/06/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2026 | 10/29/2025 | 2/5/2027 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Design |  | N
National Grid | MILFORD | 210131 | 01757 | 13.8 | Solar | 05_05_8L3 | 03/04/2019 | 03/12/2019 | 5 | 0 | 5 | 03/13/2019 | 03/13/2019 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/29/2019 | 03/04/2019 | 3/27/2020 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/24/2019 | Connected |  | N
National Grid | WILLIAMSBURG | 609956 | 01096 | 22.8 | Solar | 04_04_101L6 | 05/09/2024 | 05/14/2024 | 3 | 1 | 2 | 05/15/2024 | 05/15/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/31/2024 |  | 7/17/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/31/2024 | Connected |  | N
National Grid | SOUTHBOROUGH | 322044 | 01772 | 9.86 | Solar | 05_09_1109W3 | 10/27/2020 | 11/03/2020 | 4 | 2 | 2 | 11/04/2020 | 11/04/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/30/2020 |  | 11/3/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/28/2021 | Connected |  | N
National Grid | STOUGHTON | 743893 | 02072 | 11.5 | Solar | 05_07_97W2 | 01/07/2026 | 01/12/2026 | 3 | 0 | 3 | 01/13/2026 | 01/13/2026 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/2/2026 |  | 2/27/2027 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | ATTLEBORO | 337225 | 02703 | 250 | Solar | 05_07_913W69 | 02/09/2021 | 02/17/2021 | 4 | 0 | 4 | 02/18/2021 | 02/18/2021 | 23 | 0 | 23 | 04/06/2021 | 09/21/2021 | 117 | 82 | 35 |  |  | 0 | 0 | 0 |  | 09/21/2021 | 117 | 82 | 35 |  |  | 0 | 0 | 0 | 10/6/2021 | 02/09/2021 | 2/22/2024 | Y | EXP | 245 | 02/17/2022 | 08/03/2023 | 533 | 493 | 40 |  |  | 9/5/2023 | Connected |  | N
National Grid | NANTUCKET | 178675 | 02554 | 2500 | Solar | 05_09_523L2 | 04/10/2018 | 04/20/2018 | 6 | 6 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 04/20/2018 | 09/06/2018 | 97 | 54 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 176556 | 01230 | 11.4 | Solar | 05_05_336W3 | 10/07/2015 | 10/07/2015 | 1 | 1 | 0 | 10/09/2015 | 10/09/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/23/2015 |  | 10/13/2016 | N | EXP | 356 |  |  | 0 | 0 | 0 | 3/11/2016 | 3/11/2016 | 3/17/2016 | Connected |  | N
National Grid | RANDOLPH | 535697 | 02368 | 151.9 | Solar | 05_09_909W3 | 06/29/2023 | 07/14/2023 | 10 | 0 | 10 |  |  | 39 | 15 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/29/2024 |  | 5/2/2025 | N | STD | 119 |  |  | 0 | 0 | 0 |  |  | 3/28/2025 | Connected |  | N
National Grid | STOUGHTON | 749261 | 02072 |  | Battery Add-On | 05_05_314W3 | 02/04/2026 | 02/06/2026 | 2 | 0 | 2 | 02/09/2026 | 02/09/2026 | 17 | 0 | 17 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/6/2026 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | BELCHERTOWN | 174862 | 01007 | 1000 | Solar | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 |  | 12/31/2012 | N | STD | 178 |  |  | 0 | 0 | 0 |  |  | 8/11/2015 | Withdrawn |  | N
National Grid | MILFORD | 258893 | 01757 | 0 | Solar | 05_05_8L3 | 10/08/2019 | 10/09/2019 | 0 | 0 | 0 | 10/10/2019 | 10/10/2019 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/10/2019 |  | 12/13/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/11/2019 | Connected |  | N
National Grid | WILLIAMSBURG | 659236 | 01096 | 20 | Solar | 04_04_101L6 | 12/09/2024 | 12/16/2024 | 5 | 4 | 1 | 12/17/2024 | 12/17/2024 | 25 | 0 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/30/2025 |  | 2/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/31/2025 | Connected |  | N
National Grid | SOUTHBOROUGH | 327873 | 01772 | 7.6 | Solar | 05_09_1109W3 | 11/23/2020 | 12/09/2020 | 10 | 9 | 1 | 12/10/2020 | 12/10/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/7/2021 |  | 12/9/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/27/2021 | Connected |  | N
National Grid | BRIDGEWATER | 743754 | 02324 | 5.76 | Solar | 05_07_97W2 | 01/06/2026 | 01/07/2026 | 3 | 0 | 3 | 02/27/2026 | 02/27/2026 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 355909 | 02766 | 480 | Solar | 05_07_913W69 | 06/01/2021 | 06/24/2021 | 17 | 9 | 8 | 06/25/2021 | 06/25/2021 | 33 | 10 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/29/2021 | 06/01/2021 | 12/8/2024 | Y | EXP | 322 | 02/01/2022 | 02/13/2025 | 1108 | 720 | 388 |  |  | 10/21/2024 | Connected |  | N
National Grid | NANTUCKET | 184809 | 02554 | 990 | Solar | 05_09_523L2 | 06/12/2018 | 06/12/2018 | 28 | 1 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | GREAT BARRINGTON | 176828 | 01230 | 7.6 | Solar | 05_05_336W3 | 01/18/2016 | 01/18/2016 | 5 | 5 | 0 | 01/26/2016 | 01/26/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/9/2016 |  | 1/24/2017 | N | EXP | 35 |  |  | 0 | 0 | 0 | 10/10/2016 | 10/10/2016 | 10/13/2016 | Connected |  | N
National Grid | RANDOLPH | 546867 | 02368 | 9.86 | Solar | 05_09_909W3 | 08/09/2023 | 08/10/2023 | 1 | 0 | 1 | 08/11/2023 | 08/11/2023 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/6/2023 | 08/09/2023 | 9/30/2024 | Y | EXP | 365 | 10/19/2023 | 10/24/2023 | 6 | 0 | 6 |  |  | 3/20/2024 | Connected |  | N
National Grid | STOUGHTON | 174313 | 02072 | 95 | Solar | 05_05_314W3 | 01/11/2012 | 01/11/2012 | 27 | 0 | 27 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/19/2012 |  | 5/1/2012 | N | EXP | 12 |  |  | 0 | 0 | 0 | 8/27/2012 | 8/27/2012 | 9/10/2012 | Connected |  | N
National Grid | BELCHERTOWN | 174861 | 01007 | 3000 | Solar | 05_07_797W1 | 08/03/2012 | 08/03/2012 | 11 | 9 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/21/2012 | 11/24/2012 | 50 | 0 | 50 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2013 | 08/03/2012 | 6/1/2014 | Y | STD | 339 |  |  | 0 | 0 | 0 | 8/7/2012 | 8/7/2012 | 8/11/2015 | Connected |  | N
National Grid | MILFORD | 282466 | 01757 | 7.6 | Solar | 05_05_8L3 | 04/14/2020 | 04/21/2020 | 4 | 4 | 0 | 04/22/2020 | 04/22/2020 | 12 | 0 | 12 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/7/2020 | 04/14/2020 | 4/20/2021 | Y | EXP | 365 | 01/21/2021 | 02/08/2021 | 18 | 0 | 18 |  |  | 2/9/2021 | Connected |  | N
National Grid | NORTHAMPTON | 692607 | 01053 | 100 | Solar | 04_04_101L7 | 05/21/2025 | 06/27/2025 | 24 | 14 | 10 | 06/30/2025 | 06/30/2025 | 16 | 0 | 16 | 08/11/2025 | 09/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  | 09/08/2025 | 20 | 0 | 20 |  |  | 0 | 0 | 0 | 9/15/2025 |  | 9/30/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 331061 | 01581 | 106.4 | Solar | 05_09_1109W3 | 12/16/2020 | 01/15/2021 | 20 | 12 | 8 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/23/2021 | 12/16/2020 | 6/23/2023 | Y | STD | 62 |  |  | 0 | 0 | 0 |  |  | 6/23/2023 | Connected |  | N
National Grid | BRIDGEWATER | 745164 | 02324 | 11.4 | Solar | 05_07_97W2 | 01/13/2026 | 01/15/2026 | 2 | 0 | 2 | 02/04/2026 | 02/04/2026 | 19 | 4 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Conditional Approval |  | N
National Grid | ATTLEBORO | 432258 | 02703 | 10 | Solar | 05_07_913W69 | 06/02/2022 | 06/07/2022 | 3 | 0 | 3 | 06/08/2022 | 06/08/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/8/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 199150 | 02554 | 7.6 | Solar | 05_09_523L2 | 10/22/2018 | 10/24/2018 | 2 | 2 | 0 | 10/25/2018 | 10/25/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/29/2018 |  | 10/7/2019 | N | EXP | 343 |  |  | 0 | 0 | 0 |  |  | 8/29/2019 | Connected |  | N
National Grid | STOCKBRIDGE | 176881 | 01266 | 3.8 | Solar | 05_05_336W3 | 05/04/2016 | 05/04/2016 | 3 | 3 | 0 | 05/10/2016 | 05/10/2016 | 173 | 0 | 173 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2016 |  | 5/10/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 585251 | 02368 | 7.6 | Solar | 05_09_909W3 | 02/02/2024 | 02/16/2024 | 10 | 9 | 1 | 02/20/2024 | 02/20/2024 | 7 | 3 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOUGHTON | 189184 | 02072 | 15.2 | Solar | 05_05_314W3 | 06/26/2018 | 06/26/2018 | 15 | 9 | 6 | 07/23/2018 | 07/23/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/15/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | PALMER | 175221 | 01069 | 19 | Solar | 05_07_797W1 | 11/03/2014 | 11/03/2014 | 7 | 4 | 3 | 11/14/2014 | 11/14/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/19/2014 |  | 1/30/2015 | N | EXP | 72 |  |  | 0 | 0 | 0 | 8/5/2015 | 8/5/2015 | 5/10/2016 | Connected |  | N
National Grid | MILFORD | 301078 | 01757 | 7.6 | Solar | 05_05_8L3 | 07/14/2020 | 07/17/2020 | 2 | 0 | 2 | 07/20/2020 | 07/20/2020 | 15 | 0 | 15 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/12/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WILLIAMSBURG | 706278 | 01039 | 50 | Solar | 04_04_101L7 | 08/08/2025 | 08/14/2025 | 3 | 0 | 3 | 08/15/2025 | 08/15/2025 | 19 | 0 | 19 | 09/18/2025 | 10/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  | 10/22/2025 | 24 | 0 | 24 |  |  | 0 | 0 | 0 | 10/29/2025 |  | 11/3/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | WESTBOROUGH | 342184 | 01581 | 6.96 | Solar | 05_09_1109W3 | 02/15/2021 | 02/16/2021 | 0 | 0 | 0 | 02/17/2021 | 02/17/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/11/2021 |  | 2/15/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/3/2021 | Connected |  | N
National Grid | BRIDGEWATER | 751626 | 02324 | 3.8 | Solar | 05_07_97W2 | 02/17/2026 | 02/23/2026 | 3 | 0 | 3 | 03/04/2026 | 03/04/2026 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | NORTON | 435270 | 02766 | 0 | Solar | 05_07_913W69 | 06/09/2022 | 07/11/2022 | 21 | 20 | 1 | 07/12/2022 | 07/12/2022 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 |  | 8/6/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 5/9/2023 | Connected |  | N
National Grid | NANTUCKET | 241092 | 02554 | 10.32 | Solar | 05_09_523L2 | 07/24/2019 | 07/26/2019 | 1 | 0 | 1 | 07/29/2019 | 07/29/2019 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2019 | 07/24/2019 | 1/11/2021 | Y | EXP | 365 | 02/07/2020 | 02/06/2020 | 0 | 0 | 0 |  |  | 12/18/2020 | Connected |  | N
National Grid | GREAT BARRINGTON | 176974 | 01230 | 6.45 | Solar | 05_05_336W3 | 10/06/2016 | 10/06/2016 | 5 | 5 | 0 | 10/17/2016 | 10/17/2016 | 61 | 0 | 61 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/21/2016 |  | 10/12/2017 | N | EXP | 356 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 587581 | 02368 | 15.2 | Solar | 05_09_909W3 | 02/02/2024 | 02/06/2024 | 2 | 1 | 1 | 02/07/2024 | 02/07/2024 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/23/2024 |  | 3/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/22/2025 | Connected |  | Y
National Grid | STOUGHTON | 202461 | 02072 | 75 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 176671 | 01007 | 499 | Solar | 05_07_797W1 | 10/22/2015 | 10/22/2015 | 2 | 2 | 0 | 10/27/2015 | 10/27/2015 | 127 | 0 | 127 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/28/2016 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 310170 | 01757 | 10 | Solar | 05_05_8L3 | 10/06/2020 | 10/09/2020 | 2 | 0 | 2 | 10/13/2020 | 10/13/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/6/2020 |  | 1/28/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NORTHAMPTON | 725845 | 01053 | 11.2 | Solar | 04_04_101L7 | 10/31/2025 | 12/22/2025 | 32 | 27 | 5 | 12/23/2025 | 12/23/2025 | 49 | 33 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 344660 | 01581 | 10 | Solar | 05_09_1109W3 | 03/04/2021 | 03/22/2021 | 12 | 12 | 0 | 03/23/2021 | 03/23/2021 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/14/2021 |  | 6/22/2022 | N | EXP | 425 |  |  | 0 | 0 | 0 |  |  | 5/11/2022 | Connected |  | N
National Grid | BRIDGEWATER | 175563 | 02324 | 14.8 | Solar | 05_07_97W2 | 07/31/2014 | 07/31/2014 | 7 | 0 | 7 | 08/12/2014 | 08/12/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/2/2014 | 07/31/2014 | 10/31/2014 | Y | EXP | 59 | 10/07/2015 | 10/13/2015 | 3 | 0 | 3 | 10/26/2015 | 10/26/2015 | 10/26/2015 | Connected |  | N
National Grid | NORTON | 556059 | 02766 | 0 | Solar | 05_07_913W69 | 09/15/2023 | 09/19/2023 | 2 | 0 | 2 |  |  | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 294435 | 02554 | 5 | Solar | 05_09_523L2 | 07/17/2020 | 07/27/2020 | 5 | 0 | 5 | 07/28/2020 | 07/28/2020 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/20/2020 | 07/17/2020 | 5/3/2021 | Y | EXP | 365 | 04/23/2021 | 05/05/2021 | 12 | 0 | 12 |  |  | 6/9/2021 | Connected |  | N
National Grid | STOCKBRIDGE | 177174 | 01266 | 10 | Solar | 05_05_336W3 | 05/31/2016 | 05/31/2016 | 1 | 1 | 0 | 06/02/2016 | 06/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/20/2016 | 05/31/2016 | 6/6/2017 | Y | EXP | 351 | 11/03/2016 | 12/07/2016 | 22 | 0 | 22 | 7/17/2017 | 7/17/2017 | 7/19/2017 | Connected |  | N
National Grid | RANDOLPH | 606572 | 02368 | 23 | Solar | 05_09_909W3 | 04/25/2024 | 05/01/2024 | 5 | 3 | 2 | 05/02/2024 | 05/02/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  | 6/4/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/14/2024 | Connected |  | N
National Grid | STOUGHTON | 202201 | 02072 | 120 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 176910 | 01009 | 499 | Solar | 05_07_797W1 | 03/08/2016 | 03/08/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/09/2016 | 03/18/2016 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/5/2016 | 03/08/2016 | 12/15/2017 | Y | STD | 528 | 11/10/2016 | 08/09/2017 | 185 | 0 | 185 | 12/21/2016 | 12/21/2016 | 12/8/2017 | Connected |  | N
National Grid | MILFORD | 317491 | 01757 | 50 | Solar | 05_05_8L3 | 10/06/2020 | 10/15/2020 | 5 | 0 | 5 | 10/16/2020 | 10/16/2020 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/5/2020 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/2/2021 | Connected |  | N
National Grid | NORTHAMPTON | 751868 | 01053 | 7.6 | Solar | 04_04_101L7 | 02/26/2026 | 03/06/2026 | 4 | 2 | 2 | 03/09/2026 | 03/09/2026 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Screening |  | N
National Grid | WESTBOROUGH | 346854 | 01581 | 4980 | Solar | 05_09_1109W3 | 12/15/2022 | 05/12/2023 | 101 | 93 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/15/2023 | 11/02/2023 | 119 | 100 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BRIDGEWATER | 175584 | 02324 | 17 | Solar | 05_07_97W2 | 04/18/2014 | 04/18/2014 | 6 | 0 | 6 | 04/30/2014 | 04/30/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/1/2014 |  | 6/30/2014 | N | EXP | 6 |  |  | 0 | 0 | 0 | 6/23/2014 | 6/23/2014 | 7/10/2014 | Connected |  | N
National Grid | NORTON | 593534 | 02766 | 8.19 | Solar | 05_07_913W69 | 03/18/2024 | 04/24/2024 | 26 | 23 | 3 | 04/25/2024 | 04/25/2024 | 10 | 1 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/10/2024 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | NANTUCKET | 294038 | 02554 | 9.84 | Solar | 05_09_523L2 | 08/05/2020 | 08/11/2020 | 3 | 0 | 3 | 08/12/2020 | 08/12/2020 | 9 | 0 | 9 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2020 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | STOCKBRIDGE | 177982 | 01266 | 168 | Solar | 05_05_336W3 | 08/28/2017 | 08/28/2017 | 5 | 5 | 0 | 09/05/2017 | 09/05/2017 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/8/2017 |  | 9/2/2018 | N | EXP | 359 |  |  | 0 | 0 | 0 | 2/7/2018 | 2/7/2018 | 2/20/2018 | Connected |  | N
National Grid | RANDOLPH | 610184 | 02368 | 10 | Solar | 05_09_909W3 | 05/16/2024 | 06/05/2024 | 14 | 13 | 1 | 06/06/2024 | 06/06/2024 | 11 | 0 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/27/2024 |  | 7/1/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/16/2024 | Connected |  | N
National Grid | STOUGHTON | 203268 | 02072 | 105 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 186863 | 01007 | 4998 | Solar | 05_07_797W1 | 05/31/2018 | 05/31/2018 | 47 | 4 | 43 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 08/08/2018 | 09/04/2018 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/8/2019 |  | 11/30/2020 | N | STD | 261 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 375559 | 01757 | 100 | Solar | 05_05_8L3 | 08/18/2021 | 09/08/2021 | 14 | 3 | 11 |  |  | 59 | 28 | 31 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/26/2022 | 08/18/2021 | 3/23/2023 | Y | STD | 196 | 01/25/2023 | 04/20/2023 | 85 | 59 | 26 |  |  | 5/12/2023 | Connected |  | N
National Grid | WILLIAMSBURG | 175677 | 01096 | 499 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 359175 | 01581 | 9.6 | Solar | 05_09_1109W3 | 05/19/2021 | 06/09/2021 | 14 | 13 | 1 | 06/10/2021 | 06/10/2021 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/15/2021 |  | 7/18/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/21/2021 | Connected |  | N
National Grid | BRIDGEWATER | 175767 | 02324 | 5000 | Solar | 05_07_97W2 | 06/12/2014 | 06/12/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 06/20/2014 | 07/17/2014 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/27/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | ATTLEBORO | 598040 | 02703 | 7.6 | Solar | 05_07_913W69 | 03/22/2024 | 03/26/2024 | 2 | 0 | 2 | 03/27/2024 | 03/27/2024 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/1/2024 |  | 4/16/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 6/11/2024 | Connected |  | N
National Grid | NANTUCKET | 297681 | 02554 | 3.36 | Solar | 05_09_523L2 | 06/22/2020 | 06/29/2020 | 4 | 0 | 4 | 06/30/2020 | 06/30/2020 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/21/2020 |  | 5/28/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 1/20/2021 | Connected |  | N
National Grid | EGREMONT | 178390 | 01252 | 15.2 | Solar | 05_05_336W3 | 03/01/2018 | 03/01/2018 | 0 | 0 | 0 | 03/16/2018 | 03/16/2018 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/21/2018 | 03/01/2018 | 10/31/2019 | Y | EXP | 589 |  |  | 0 | 0 | 0 |  |  | 10/24/2019 | Connected |  | N
National Grid | RANDOLPH | 611991 | 02368 | 7.6 | Solar | 05_09_909W3 | 05/19/2024 | 05/21/2024 | 3 | 2 | 1 | 05/22/2024 | 05/22/2024 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/11/2024 |  | 6/20/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/9/2024 | Connected |  | N
National Grid | STOUGHTON | 203267 | 02072 | 105 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 188766 | 01007 | 200 | Solar | 05_07_797W1 | 06/21/2018 | 06/21/2018 | 3 | 0 | 3 | 07/02/2018 | 07/02/2018 | 30 | 6 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/22/2018 |  | 8/21/2019 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/11/2019 | Connected |  | N
National Grid | MILFORD | 376662 | 01757 | 7.6 | Solar | 05_05_8L3 | 08/19/2021 | 08/26/2021 | 6 | 5 | 1 | 08/27/2021 | 08/27/2021 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/26/2021 | 08/19/2021 | 10/1/2022 | Y | EXP | 365 | 09/14/2021 | 09/30/2021 | 17 | 0 | 17 |  |  | 10/7/2021 | Connected |  | N
National Grid | NORTHAMPTON | 175676 | 01053 | 1596 | Solar | 04_04_101L7 | 10/28/2014 | 10/28/2014 | 2 | 1 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/31/2014 | 12/12/2014 | 28 | 9 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 360945 | 01581 | 10 | Solar | 05_09_1109W3 | 06/30/2021 | 01/10/2022 | 4 | 0 | 4 | 07/08/2021 | 07/08/2021 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/9/2021 | 06/30/2021 | 1/11/2023 | Y | EXP | 365 | 12/23/2021 | 01/10/2022 | 19 | 0 | 19 |  |  | 1/24/2022 | Connected |  | Y
National Grid | BRIDGEWATER | 175765 | 02324 | 16.01 | Solar | 05_07_97W2 | 06/06/2014 | 06/06/2014 | 5 | 2 | 3 | 06/16/2014 | 06/16/2014 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/11/2014 |  | 8/29/2014 | N | EXP | 49 |  |  | 0 | 0 | 0 | 7/11/2014 | 7/11/2014 | 8/15/2014 | Connected |  | N
National Grid | ATTLEBORO | 648653 | 02703 | 10 | Solar | 05_07_913W69 | 10/21/2024 | 11/15/2024 | 1 | 0 | 1 | 11/18/2024 | 11/18/2024 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/2/2025 |  | 1/24/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 3/18/2025 | Connected |  | N
National Grid | NANTUCKET | 299534 | 02554 | 0 | Solar | 05_09_523L2 | 07/02/2020 | 08/11/2020 | 27 | 25 | 2 | 08/12/2020 | 08/12/2020 | 8 | 0 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/25/2020 | 07/02/2020 | 8/11/2021 | Y | EXP | 365 | 10/08/2020 | 10/21/2020 | 13 | 0 | 13 |  |  | 10/21/2020 | Connected |  | N
National Grid | STOCKBRIDGE | 178449 | 01266 | 7.6 | Solar | 05_05_336W3 | 11/29/2017 | 11/29/2017 | 45 | 42 | 3 | 02/06/2018 | 02/06/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/6/2018 |  | 12/5/2018 | N | EXP | 32 |  |  | 0 | 0 | 0 |  |  | 11/26/2018 | Connected |  | N
National Grid | RANDOLPH | 617800 | 02368 | 10 | Solar | 05_09_909W3 | 06/13/2024 | 06/24/2024 | 3 | 0 | 3 | 06/25/2024 | 06/25/2024 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2024 | 06/13/2024 | 7/30/2025 | Y | EXP | 365 | 08/22/2024 | 08/23/2024 | 2 | 0 | 2 |  |  | 1/7/2025 | Connected |  | N
National Grid | STOUGHTON | 203266 | 02072 | 60 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 35 | 15 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 316478 | 01009 | 100 | Solar | 05_07_797W1 | 10/02/2020 | 11/03/2020 | 20 | 14 | 6 | 11/04/2020 | 11/04/2020 | 37 | 15 | 22 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/31/2020 |  | 8/19/2022 | N | EXP | 592 |  |  | 0 | 0 | 0 |  |  | 8/1/2022 | Connected |  | N
National Grid | MILFORD | 404485 | 01757 | 16.08 | Solar | 05_05_8L3 | 01/08/2022 | 01/18/2022 | 6 | 2 | 4 | 01/19/2022 | 01/19/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/15/2022 |  | 3/31/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/4/2022 | Connected |  | N
National Grid | WILLIAMSBURG | 175674 | 01039 | 499 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 6 | 0 | 6 | 10/31/2014 | 10/31/2014 | 4 | 0 | 4 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/30/2015 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 368959 | 01581 | 20 | Solar | 05_09_1109W3 | 02/16/2022 | 02/18/2022 | 2 | 0 | 2 | 02/22/2022 | 02/22/2022 | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2022 |  | 4/14/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/22/2022 | Connected |  | N
National Grid | BRIDGEWATER | 176090 | 02324 | 7.6 | Solar | 05_07_97W2 | 02/02/2015 | 02/02/2015 | 5 | 1 | 4 | 02/10/2015 | 02/10/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/25/2015 | 02/02/2015 | 6/30/2015 | Y | EXP | 125 | 11/04/2015 | 11/04/2015 | 0 | 0 | 0 | 4/20/2015 | 4/20/2015 | 11/9/2015 | Connected |  | N
National Grid | NORTON | 665212 | 02766 | 10 | Solar | 05_07_913W69 | 01/13/2025 | 01/29/2025 | 4 | 0 | 4 | 01/30/2025 | 01/30/2025 | 44 | 25 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 326990 | 02554 | 0 | Solar | 05_09_523L2 | 11/20/2020 | 12/08/2020 | 10 | 8 | 2 | 12/09/2020 | 12/09/2020 | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 1/6/2021 |  | 12/6/2021 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 2/22/2021 | Connected |  | N
National Grid | GREAT BARRINGTON | 178445 | 01236 | 7.6 | Solar | 05_05_336W3 | 04/03/2018 | 04/03/2018 | 4 | 4 | 0 | 04/10/2018 | 04/10/2018 | 81 | 0 | 81 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5/9/2018 |  | 4/9/2019 | N | EXP | 335 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | RANDOLPH | 619298 | 02368 | 11.5 | Solar | 05_09_909W3 | 06/20/2024 | 06/24/2024 | 2 | 0 | 2 | 06/25/2024 | 06/25/2024 | 22 | 11 | 11 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/29/2024 |  | 7/31/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 12/5/2024 | Connected |  | N
National Grid | STOUGHTON | 203263 | 02072 | 90 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | PALMER | 331425 | 01009 | 3286 | Solar | 05_07_797W1 | 01/15/2021 | 02/16/2021 | 20 | 12 | 8 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 02/17/2021 | 08/03/2021 | 117 | 93 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/30/2022 | 01/15/2021 | 11/7/2024 | Y | STD | 7 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 426000 | 01757 | 11.89 | Solar | 05_05_8L3 | 06/28/2022 | 07/20/2022 | 15 | 14 | 1 | 07/21/2022 | 07/21/2022 | 20 | 0 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/18/2022 |  | 8/29/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 11/8/2022 | Connected |  | N
National Grid | GOSHEN | 175673 | 01032 | 3024 | Solar | 04_04_101L7 | 10/22/2014 | 10/22/2014 | 3 | 0 | 3 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 9/2/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 420606 | 01581 | 15.2 | Solar | 05_09_1109W3 | 03/29/2022 | 04/04/2022 | 4 | 3 | 1 | 04/05/2022 | 04/05/2022 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/12/2022 |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | BRIDGEWATER | 176247 | 02324 | 3780 | Solar | 05_07_97W2 | 05/01/2015 | 05/01/2015 | 2 | 2 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 10/30/2015 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | ATTLEBORO | 668774 | 02703 | 0 | Solar | 05_07_915W35 | 01/29/2025 | 02/04/2025 | 5 | 2 | 3 | 02/05/2025 | 02/05/2025 | 25 | 2 | 23 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 3/18/2025 |  | 4/14/2026 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Completion Documents |  | N
National Grid | NANTUCKET | 437714 | 02554 | 10 | Solar | 05_09_523L2 | 07/07/2022 | 07/12/2022 | 3 | 0 | 3 | 07/13/2022 | 07/13/2022 | 16 | 0 | 16 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/5/2022 | 07/07/2022 | 4/6/2024 | Y | EXP | 365 | 12/22/2022 | 04/05/2023 | 105 | 0 | 105 |  |  | 4/11/2023 | Connected |  | N
National Grid | GREAT BARRINGTON | 183593 | 01230 | 6 | Solar | 05_05_336W3 | 05/23/2018 | 05/23/2018 | 19 | 13 | 6 | 06/21/2018 | 06/21/2018 | 24 | 0 | 24 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/3/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y
National Grid | RANDOLPH | 631438 | 02368 | 0 | Solar | 05_09_909W3 | 08/09/2024 | 08/15/2024 | 5 | 2 | 3 | 08/16/2024 | 08/16/2024 | 5 | 0 | 5 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2024 |  | 9/5/2025 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 10/7/2024 | Connected |  | N
National Grid | STOUGHTON | 203260 | 02072 | 60 | Solar | 05_05_314W3 | 11/28/2018 | 12/27/2018 | 10 | 5 | 5 | 12/28/2018 | 12/28/2018 | 36 | 16 | 20 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 363047 | 01007 | 30 | Solar | 05_07_797W1 | 07/19/2021 | 08/04/2021 | 12 | 6 | 6 | 08/05/2021 | 08/05/2021 | 50 | 25 | 25 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 10/20/2021 |  | 11/16/2022 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 8/19/2022 | Connected |  | Y
National Grid | MILFORD | 466376 | 01757 | 5.76 | Solar | 05_05_8L3 | 11/16/2022 | 11/21/2022 | 3 | 0 | 3 | 11/22/2022 | 11/22/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/29/2022 | 11/16/2022 | 2/29/2024 | Y | EXP | 365 | 02/25/2023 | 02/27/2023 | 3 | 0 | 3 |  |  | 5/23/2023 | Connected |  | N
National Grid | GOSHEN | 177279 | 01032 | 3600 | Solar | 04_04_101L7 | 02/08/2017 | 02/08/2017 | 136 | 134 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2/14/2018 | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | WESTBOROUGH | 428708 | 01581 | 11.4 | Solar | 05_09_1109W3 | 05/05/2022 | 05/09/2022 | 2 | 0 | 2 | 05/10/2022 | 05/10/2022 | 14 | 0 | 14 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6/1/2022 |  | 7/12/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 7/27/2022 | Connected |  | N
National Grid | BRIDGEWATER | 176316 | 02324 | 3780 | Solar | 05_07_97W2 | 05/08/2015 | 05/08/2015 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 05/12/2015 | 06/09/2015 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/1/2016 | 05/08/2015 | 11/9/2017 | Y | STD | 647 | 06/28/2017 | 10/24/2017 | 81 | 0 | 81 | 10/25/2017 | 10/25/2017 | 11/7/2017 | Connected |  | N
National Grid | ATTLEBORO | 722967 | 02703 | 20 | Solar | 05_07_915W35 | 09/30/2025 | 10/16/2025 | 10 | 5 | 5 | 10/17/2025 | 10/17/2025 | 81 | 75 | 6 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Pending Withdraw |  | N
National Grid | NANTUCKET | 459546 | 02554 | 150 | Solar | 05_09_523L2 | 09/23/2022 | 11/03/2022 | 28 | 17 | 11 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 11/13/2023 | 09/23/2022 | 11/28/2025 | Y | STD | 119 | 02/11/2025 | 02/10/2025 | 0 | 0 | 0 |  |  | 11/25/2025 | Connected |  | N
National Grid | EGREMONT | 188704 | 01252 | 10 | Solar | 05_05_336W3 | 07/06/2018 | 08/10/2018 | 1 | 1 | 0 | 08/13/2018 | 08/13/2018 | 2 | 0 | 2 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/27/2018 | 07/06/2018 | 8/26/2019 | Y | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 4/23/2019 | Connected |  | N
National Grid | RANDOLPH | 632702 | 02368 | 7.6 | Solar | 05_09_909W3 | 08/14/2024 | 08/20/2024 | 2 | 1 | 1 | 08/21/2024 | 08/21/2024 | 7 | 0 | 7 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 8/30/2024 | 08/14/2024 | 9/4/2025 | Y | EXP | 365 | 10/10/2024 | 10/23/2024 | 14 | 0 | 14 |  |  | 1/30/2025 | Connected |  | N
National Grid | STOUGHTON | 222595 | 02072 | 432 | Solar | 05_05_314W3 | 04/25/2019 | 05/03/2019 | 6 | 5 | 1 |  |  | 13 | 0 | 13 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/20/2019 | 04/25/2019 | 12/12/2024 | Y | STD | 274 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | BELCHERTOWN | 383230 | 01007 | 3000 | Solar | 05_07_797W1 | 03/11/2022 | 03/25/2022 | 10 | 0 | 10 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 03/28/2022 | 05/20/2022 | 39 | 20 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | N | STD |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | MILFORD | 478397 | 01757 | 15 | Solar | 05_05_8L3 | 01/18/2023 | 01/20/2023 | 2 | 0 | 2 | 01/23/2023 | 01/23/2023 | 21 | 0 | 21 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2/24/2023 | 01/18/2023 | 4/18/2024 | Y | EXP | 365 | 03/29/2023 | 04/13/2023 | 16 | 0 | 16 |  |  | 10/7/2023 | Connected |  | N
National Grid | WILLIAMSBURG | 177334 | 01096 | 27 | Solar | 04_04_101L7 | 08/31/2016 | 08/31/2016 | 2 | 2 | 0 | 09/02/2016 | 09/02/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/21/2016 |  | 9/5/2017 | N | EXP | 349 |  |  | 0 | 0 | 0 | 11/22/2016 | 11/22/2016 | 11/28/2016 | Connected |  | N
National Grid | WESTBOROUGH | 437566 | 01581 | 15.2 | Solar | 05_09_1109W3 | 06/14/2022 | 06/16/2022 | 3 | 2 | 1 | 06/17/2022 | 06/17/2022 | 19 | 0 | 19 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 7/19/2022 |  | 12/4/2023 | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  | 9/2/2023 | Connected |  | N
National Grid | BRIDGEWATER | 176580 | 02324 | 3.8 | Solar | 05_07_97W2 | 04/05/2016 | 04/05/2016 | 1 | 1 | 0 | 04/07/2016 | 04/07/2016 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 4/26/2016 | 04/05/2016 | 4/11/2017 | Y | EXP | 35 | 09/15/2016 | 10/18/2016 | 22 | 0 | 22 | 8/11/2016 | 8/11/2016 | 12/2/2016 | Connected |  | N
National Grid | NORTON | 156595 | 02766 | 15.2 | Solar | 05_07_915W35 | 08/23/2017 | 08/23/2017 | 1 | 0 | 1 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 8/23/2018 | N | EXP |  |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | N
National Grid | NANTUCKET | 459446 | 02554 | 100 | Solar | 05_09_523L2 | 09/23/2022 | 11/14/2022 | 34 | 24 | 10 |  |  | 18 | 0 | 18 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 12/8/2023 | 09/23/2022 | 2/5/2025 | Y | STD | 41 |  |  | 0 | 0 | 0 |  |  | 2/7/2025 | Connected |  | Y
National Grid | GREAT BARRINGTON | 194481 | 01230 | 7.6 | Solar | 05_05_336W3 | 08/28/2018 | 09/24/2018 | 8 | 8 | 0 | 09/25/2018 | 09/25/2018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 9/25/2018 |  |  | N | EXP | 365 |  |  | 0 | 0 | 0 |  |  |  | Withdrawn |  | Y